## Cover Sheet Tables 1-12
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines Appendix D, Section 1.2
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | PacifiCorp
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2023
Reporting Period quarter |  | Q4
Date Modified |  | 2024-02-01

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitiativeObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
PacifiCorp | 2023-11-01 | Project |  | 2023-12-31 | Risk modeling using WRRM | Risk and Risk Components Calculation. Cost tracked on Table 11. | Identify the specific assets associated with the risk, the areas of risk, and the consequence of an ignition or wildfire in that area | Risk Methodology and Assessment | 6 | Risk and Risk Components Calculation |  | 6.2.2 | RA-01 | PacifiCorp_Risk Methodology and Assessment_Risk and Risk Components Calculation_RA-01_2023 | 79 | TBD | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Identification of circuits with highest ignition risk | Delivery of RAIL and RAVE model (WRRM component) | Finalized composite risk score variables and weighting for subsequent calculations | Ranked composite risk scores available for use | N/A | Complete | [5 empty] | Kevin Benson | kevin.benson@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Risk map refresh | Proposed Updates to the HFTD. Cost tracked on Table 11. | Continue evaluating the HFRA and update its boundaries on a regular cycle | Risk Methodology and Assessment | 6 | Top Risk Areas within the HFRA |  | 6.4.1 | RA-02 | PacifiCorp_Risk Methodology and Assessment_Top Risk Areas within the HFRA_RA-02_2023 | 90 | TBD | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Testing of proposed changes completed and validated by 3rd party reviewer | Scoping started | Opened RFP for independent reviewer | Draft maps completed for review and internal validation | Revised scope of RFP for new posting based on lack of responses to initial RFP | Complete | [5 empty] | Kevin Benson | kevin.benson@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Line Rebuild | Line Rebuild program - Covered Conductor installation. Includes undergrounding. Tracking of line miles. Cost tracked on Table 11. | Address the potential that incidental object contact will result in a fault event | Grid Design, Operations, and Maintenance | 8.1 | Line Rebuild - Covered conductor installation |  | 8.1.2.1 | GH-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Line Rebuild - Covered conductor installation_GH-01_2023 | 138 | TBD | No | line miles | 130 | 18.6 | 44 | 104 | 130 | 18.6 | 42.2 | 63.8 | 101 | N/A | N/A | N/A | N/A | N/A | Delayed | Contract partner obtained for resources in 2024.​ Critical permits needed in 2024 were started in 2023. ​ |  |  |  |  | Kevin Schiedler | kevin.schiedler@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Targeted Pole Replacement | Distribution Pole Replacement. Tracking of units. Cost tracked on Table 11 under Line Rebuild program | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | Grid Design, Operations, and Maintenance | 8.1 | Distribution Pole Replacement |  | 8.1.2.3 | GH-02 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Pole Replacement_GH-02_2023 | 140 | TBD | No | poles | 2600 | 349 | 880 | 2040 | 2600 | 349 | 635 | 878 | 1592 | N/A | N/A | N/A | N/A | N/A | Delayed | Contract partner obtained for resources in 2024.​ Critical permits needed in 2024 were started in 2023. ​ |  |  |  |  | Kevin Schiedler | kevin.schiedler@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Transmission Pole Replacement | Transmission Pole Replacement Tracking of units. Cost tracked on Table 11 under Line Rebuild program | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | Grid Design, Operations, and Maintenance | 8.1 | Transmission Pole Replacement |  | 8.1.2.4 | GH-03 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Pole Replacement_GH-03_2023 | 140 | TBD | No | poles | 260 | 0 | 75 | 150 | 260 | 0 | 97 | 122 | 165 | N/A | N/A | N/A | N/A | N/A | Delayed | Contract partner obtained for resources in 2024.​ Critical permits needed in 2024 were started in 2023. ​ |  |  |  |  | Kevin Schiedler | kevin.schiedler@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Relay/Recloser/CB Replacements / Upgrade | Relay/Recloser/CB Replacements / Upgrade. Tracking of units. Cost tracked on Table 11. | Enhances fault detection capabilities, reduce fault isolation time, improve fault location and record availability, and speed up restoration efforts | Grid Design, Operations, and Maintenance | 8.1 | Installation of system automation equipment |  | 8.1.2.8 | GH-04 | PacifiCorp_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GH-04_2023 | 141 | TBD | No | devices | 40 | 10 | 22 | 36 | 40 | 10 | 20 | 25 | 36 | N/A | N/A | N/A | N/A | N/A | Delayed | 2024 scope of work and resources are ready for work to start in Q1 2024 |  |  |  |  | Kevin Schiedler | kevin.schiedler@pacificorp.com
PacifiCorp | 2023-11-01 | Project |  | 2024-12-31 | Expulsion fuse replacement | Tracking of units. Cost tracked on Table 11. | Install new and CAL FIRE-approved non expulsion fuses including power fuses and current limiting fuses to replace existing expulsion fuse equipment | Grid Design, Operations, and Maintenance | 8.1 | Expulsion fuse replacement |  | 8.1.2.12 | GH-05 | PacifiCorp_Grid Design, Operations, and Maintenance_Expulsion fuse replacement_GH-05_2023 | 143 | TBD | No | Fuse locations | 5000 | 1455 | 1800 | 4100 | 5000 | 1455 | 1663 | 2271 | 4147 | N/A | N/A | N/A | N/A | N/A | Delayed | 2024 material is available for work in Q1 2024. |  |  |  |  | Kevin Schiedler | kevin.schiedler@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Transmission Patrol inspections | Transmission Patrol Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Transmission Patrol inspections |  | 8.1.3.1 | AI-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Patrol inspections_AI-01_2023 | 146 | TBD | No | Inspection Count | 11754 | 587.7 | 5727 | 9343 | 11754 | 788 | 8596 | 10829 | 11678 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian Pagel | brian.pagel@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Distribution Patrol Inspections | Distribution Patrol Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Distribution Patrol Inspections |  | 8.1.3.1 | AI-02 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Patrol Inspections_AI-02_2023 | 146 | TBD | No | Inspection Count | 50474 | 4268.3365 | 14431 | 36057 | 50474 | 4916 | 28773 | 43321 | 50444 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian Pagel | brian.pagel@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Transmission Detail Inspections | Transmission Detail Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Transmission Detail Inspections |  | 8.1.3.2 | AI-03 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Detail Inspections_AI-03_2023 | 148 | TBD | No | Inspection Count | 2715 | 81.45 | 453 | 1810 | 2715 | 638 | 1870 | 2113 | 2714 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian Pagel | brian.pagel@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Distribution Detail Inspections | Distribution Detail Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Distribution Detail Inspections |  | 8.1.3.2 | AI-04 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Detail Inspections_AI-04_2023 | 148 | TBD | No | Inspection Count | 8662 | 2174.643 | 3260 | 6501 | 8662 | 4523 | 8108 | 8621 | 8627 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian Pagel | brian.pagel@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Transmission Intrusive Pole Inspections | Transmission Intrusive Pole Inspections - Transmission and Distribution Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Transmission Intrusive Pole Inspections |  | 8.1.3.3 | AI-05 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Intrusive Pole Inspections_AI-05_2023 | 150 | TBD | No | Inspection Count | 935 | 0 | 0 | 561 | 935 | 0 | 0 | 123 | 935 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian Pagel | brian.pagel@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Distribution Intrusive Pole Inspections | Distribution Intrusive Pole Inspections - Transmission and Distribution Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Distribution Intrusive Pole Inspections |  | 8.1.3.3 | AI-06 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Intrusive Pole Inspections_AI-06_2023 | 150 | TBD | No | Inspection Count | 2404 | 0 | 298 | 1562 | 2404 | 770 | 798 | 2395 | 2398 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian Pagel | brian.pagel@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Enhanced (Infrared) Inspections in Transmission Lines | Enhanced (Infrared) Inspections in Transmission Lines. Tracking of line miles. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Enhanced (Infrared) Inspections in Transmission Lines |  | 8.1.3.6 | AI-07 | PacifiCorp_Grid Design, Operations, and Maintenance_Enhanced (Infrared) Inspections in Transmission Lines_AI-07_2023 | 154 | TBD | No | line miles | 700 | 120 | 700 | 700 | 700 | 259 | 700 | 700 | 700 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Pilot |  |  | Enhanced (Infrared) Inspections in Distribution Lines | Enhanced (Infrared) Inspections in Distribution Lines. Tracking of line miles. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Enhanced (Infrared) Inspections in Distribution Lines |  | 8.1.3.5 | AI-08 | PacifiCorp_Grid Design, Operations, and Maintenance_Enhanced (Infrared) Inspections in Distribution Lines_AI-08_2023 | 153 | TBD | No | line miles | 810 | 0 | 0 | 810 | 810 | 0 | 0 | 757 | 757 | N/A | N/A | N/A | N/A | N/A | Delayed | The contractor procured a drone to utilize for inspections required within at least 1mi line of sight visibility to the vehicle access. ​ Locations identified inaccessible to a vehicle and a drone will be combined with the Transmission IR aerial inspections. |  |  |  |  | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Substation Inspections | Substation Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Substation Inspections |  | 8.1.3.4 | AI-11 | PacifiCorp_Grid Design, Operations, and Maintenance_Substation Inspections_AI-11_2023 | 151 | TBD | No | Inspection Count | 451 | 167 | 225 | 393 | 451 | 165 | 223 | 393 | 449 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Jon Connelly | jonathan.connelly@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | QA/QC of Asset Inspections | QA/QC of Asset Inspections |  | Grid Design, Operations, and Maintenance | 8.1 | Quality Assurance and Quality Control |  | 8.1.6 | AI-12 | PacifiCorp_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control_AI-12_2023 | 160 | TBD | No | Inspection Count | 736 | 147 | 294 | 514 | 736 | 259 | 433 | 667 | 775 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian Pagel | brian.pagel@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | EFR Settings |  |  | Grid Design, Operations, and Maintenance | 8.1 | Equipment Settings to Reduce Wildfire Risk |  | 8.1.8.1 | GO-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Equipment Settings to Reduce Wildfire Risk _GO-01_2023 | 186 | TBD | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Planned | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Installation of weather stations | Tracking of units. Cost tracked on Table 11. |  | Situational Awareness and Forecasting | 8.3 | Environmental monitoring systems |  | 8.3.2 | SA-01 | PacifiCorp_Situational Awareness and Forecasting_Environmental monitoring systems_SA-01_2023 | 213 | TBD | No | Unit | 12 | 0 | 8 | 11 | 12 | 0 | 9 | 15 | 15 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Kevin Schiedler | kevin.schiedler@pacificorp.com
PacifiCorp | 2023-11-01 | Project |  | 2024-12-31 | Wildfire Detection Network | Install up to 8 advanced wildfire detection cameras | Install 8 high-definition, pan/ tilt/ zoom wildfire detection cameras to fill in the "gaps" in the existing camera network within Pacific Power's California service territory | Situational Awareness and Forecasting | 8.3 | Ignition Detection Systems |  | 8.3.4.1 | SA-04 | PacifiCorp_Situational Awareness and Forecasting_Ignition Detection Systems_SA-04_2023 | 224 | N/A | No | Unit | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Project |  | 2026-12-31 | Advanced Forecasting and Situational Awareness | Implement improvements to weather forecasting systems | * Improve integration of weather data into PacifiCorp's systems * Full integration of 30-year historic weather data analysis into operational and planning processes * Develop WRF ensemble configuration and self-organizing map forecast system * Continue optimization and improvement of machine learning (ML) models' access to 30-year historic weather data analysis. | Situational Awareness and Forecasting | 8.3 | Weather Forecasting |  | 8.3.5.3 | SA-05 | PacifiCorp_Situational Awareness and Forecasting_Weather Forecasting_N/A_2023 | 216 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | * Improve integration of weather data into PacifiCorp's systems * Full integration of 30-year historic weather data analysis into operational and planning processes * Develop WRF ensemble configuration and self-organizing map forecast system * Continue optimization and improvement of machine learning (ML) models' access to 30-year historic weather data analysis | * Additional testing and configuration to shorten model run times complete. * Updated post-processing order to shorten upload time to PacifiCorp systems | * Full integration of 30-year historic weather data analysis into operational and planning processes * Continue optimization and improvement of machine learning (ML) models' access to 30-year historic weather data analysis (ongoing) | * Configuration of self-organizing map forecast system complete * Continue optimization and improvement of machine learning (ML) models' access to 30-year historic weather data analysis (ongoing) | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Project |  | 2023-12-31 | Public Safety Partner Portal | Develop a web-based portal for Public Safety Partners with critical facility/ infrastructure data for use during PSPS events | Develop a web-based application that hosts key information from PacifiCorp's IT systems about customers identified as critical facilities or infrastructure for use by public safety partners during PSPS events. | Emergency Preparedness | 8.4 | Messaging |  | 8.4.4.2 | EP-03 | PacifiCorp_Emergency Preparedness_Messaging_EP-03_2023 | 256 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Testing and implementation of full portal functionality complete | End user storyboarding and wireframing 50% complete | End user storyboarding and wireframing complete | N/A | Web-based portal application complete | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Risk Spend Efficiency (RSE) Modeling Implementation | Risk Spend Efficiency (RSE) Modeling Implementation | Provide risk spend efficiency calculations for proposed mitigations | Risk Methodology and Assessment | 6 | Other Key Metrics |  | 6.4.3 | RA-03 | PacifiCorp_Risk Evaluation_Mitigation Selection Process_RA-01_2023 | 92 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Risk Spend Efficiency Capabilities Implemented | Project planning and scoping completed | Finalized requirements with Technosylva for integration into future WFA-E product portfolio Finalized internal RSE methodology including calculations and preliminary assumed effectiveness values for mitigations | Testing RSE capability in WFA-E | Completed testing of RSE capability in WFA-E. Initiated User Acceptance Testing and business validation | Complete | [5 empty] | Kevin Benson | kevin.benson@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Public Safety Power Shutoff (PSPS) Risk Assessment Solution | Public Safety Power Shutoff (PSPS) Risk Assessment Solution | Implement capability to calculate PSPS risks and risk components | Risk Methodology and Assessment | 6 | Risk and Risk Components Calculation |  | 6.1.1 | RA-01 | PacifiCorp_Risk Methodology and Assessment_Risk and Risk Components Calculation_RA-01_2023 | 66 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Solution in testing stage | Project scoped | Finalized requirements for internal development of PSPS risk assessment Selected variables to include in calculations | Initiated development of PSPS risk calculations including input data collection and historical PSPS event data for validation | Continued development of PSPS risk calculations and input data processing and clean-up | Complete | [5 empty] | Kevin Benson | kevin.benson@pacificorp.com
PacifiCorp | 2023-11-01 | Pilot |  | 2024-12-31 | Distribution Fault Anticipation (DFA) Sensor Pilot | To pilot the use of DFA technology (in partnership with Texas A&M) | Install continuous monitoring sensors to preemptively identify equipment along distribution circuits that could cause an outage. | Situational Awareness and Forecasting | 8.3 | Grid monitoring systems |  | 8.3.3.1 | SA-02 | PacifiCorp_Situational Awareness and Forecasting_DFA_SA-02_2023 | 194 | N/A | No | Unit | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Weather Station Maintenance | Annual maintenance and calibration of weather station fleet | Ensure each weather station is operational and reporting correct and accurate data. | Grid Design, Operations, and Maintenance | 8.1 | Equipment Maintenance and Repair |  | 8.1.4 | MA-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Equipment Maintenance and Repair_SA-01_2023 | 166 | N/A | No | Unit | 93 | 0 | 60 | 93 | 93 | 0 | 72 | 93 | 93 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Detailed Inspection – Distribution | Detailed inspections for vegetation clearances around distribution electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks. | Vegetation Management | 8.2 | Detailed Inspection – Distribution |  | 8.2.2.1 | VM-01 | PacifiCorp_Vegetation Management_Detailed Inspection – Distribution_VM-01_2023 | 166 | N/A | Yes | Line miles | 829 | 0 | 450 | 700 | 829 | 461 | 599 | 740 | 829 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian King | brian.king@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Detailed Inspection - Transmission | Detailed inspections for vegetation clearances around transmission electric lines. | To eliminate vegetation-related reliability (cascading outages), safety, and wildfire ignition risks. | Vegetation Management | 8.2 | Detailed Inspection - Transmission |  | 8.2.2.2 | VM-02 | PacifiCorp_Vegetation Management_Detailed Inspection - Transmission_VM-02_2023 | 170 | N/A | Yes | Line miles | 264 | 0 | 158 | 211 | 264 | 149 | 182 | 235 | 264 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian King | brian.king@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Patrol Inspection - Distribution | Patrol (ground) inspections for vegetation clearances around distribution electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks by addressing vegetation conditions that require corrective action prior to the next scheduled work. | Vegetation Management | 8.2 | Patrol Inspection - Distribution |  | 8.2.3.3 | VM-03 | PacifiCorp_Vegetation Management_Patrol Inspection - Distribution_VM-03_2023 | 172 | N/A | Yes | Line miles | 1027 | 0 | 820 | 1027 | 1027 | 543 | 954 | 1027 | 1027 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian King | brian.king@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Patrol Inspection - Transmission | Patrol (ground) inspections for vegetation clearances around transmission electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks by addressing vegetation conditions that require corrective action while maintaining compliance with applicable Public Resource Codes, NERC requirements, and as described in the Vegetation SOP | Vegetation Management | 8.2 | Patrol Inspection - Transmission |  | 8.2.2.4 | VM-04 | PacifiCorp_Vegetation Management_Patrol Inspection - Transmission_VM-04_2023 | 174 | N/A | Yes | Line miles | 329 | 0 | 296 | 329 | 329 | 159 | 329 | 329 | 329 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Brian King | brian.king@pacificorp.com
PacifiCorp | 2023-11-01 | Project |  | 2023-12-31 | Smoke and Air Quality Sensors | Install 20 intelligent smoke and particulate sensors in the highest fire risk areas of PacifiCorp's CA service territory. | Install 20 intelligent smoke and particulate sensors in the highest fire risk areas of its CA service territory to support continued evaluation of the durability and accuracy of the sensors to support the DHS wildland fire sensor program. | Situational Awareness and Forecasting | 8.3 | Smoke and Air Quality Sensors |  | 8.3.4.1 | SA-03 | PacifiCorp_Situational Awareness and Forecasting_Smoke and Air Quality Sensors_SA-03_2023 | 198 | N/A | No | Unit | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | N/A | N/A | N/A | N/A | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | External collaboration and coordination | To enhance awareness of PSPS plan and understanding of roles and responsibilities. | To enhance awareness of PSPS plan and understanding of roles and responsibilities. | Emergency Preparedness | 8.4 | External Collaboration and Coordination |  | 8.4.2.3 | EP-02 | PacifiCorp_Emergency Preparedness_External Collaboration and Coordination_EP-02_2023 | 227 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Conduct 1: Functional exercise, tabletop exercise, workshop, and preparedness fair/ CRC demo. | Conducted 1 tabletop exercise and 1 workshop | Conducted 1 functional exercise | N/A | N/A | Complete | [5 empty] | Nora Yotsov | eleonore.yotsov@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | Partner with public safety partners in communities throughout California regarding wildfire safety and preparedness and PSPS. | Public Outreach and Education Awareness Program | Partner with public safety partners in communities throughout California regarding wildfire safety and preparedness and PSPS. | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | CO-01 | PacifiCorp_Community Outreach and Engagement_Public Outreach and Education Awareness Program_CO-01_2023 | 267 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Conduct 1 pre and post-fire season customer sur survey | Conducted pre-fire season customer surveys | Pre-season customer survey report complete | N/A | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Project |  | 2025-10-31 | Partner with public safety partners in communities throughout California regarding wildfire safety and preparedness and PSPS. | Public Outreach and Education Awareness Program | Partner with public safety partners in communities throughout California regarding wildfire safety and preparedness and PSPS. | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | CO-03 | PacifiCorp_Community Outreach and Engagement_Public Outreach and Education Awareness Program_CO-03_2023 | 267 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completion of updates to wildfire safety website, wildfire safety email blast | N/A | Website updates and wildfire safety email blast complete | N/A | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Project |  | 2025-10-31 | Engagement with Access and Functional Needs Populations | To deliver consistent services and resource offerings to AFN customers | Increase outreach to AFN populations | Community Outreach and Engagement | 8.5 | Engagement with Access and Functional Needs Populations |  | 8.5.3 | CO-02 | PacifiCorp_Community Outreach and Engagement_Engagement with Access and Functional Needs Populations_CO-02_2023 | 272 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Provide medical certificate in 1 additional language | N/A | Medical certificate application available in Spanish | N/A | N/A | Complete | [5 empty] | Megan Buckner | megan.bucker@pacificorp.com
PacifiCorp | 2023-11-01 | Program |  |  | cFCI Maintenance & Support | Maintain and support cFCI software/firmware, user interface, and troubleshooting/debugging hardware issues. | Maintain a high number of online sensors to support outage responses and fault location in wildfire areas (FHCA and COC) | Grid Design, Operations, and Maintenance | 8.1 | Equipment Settings to Reduce Wildfire Risk |  | 8.1.8.1 | GO-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Equipment Settings to Reduce Wildfire Risk_GO-01_2023 | 166 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Update all ZM1's to firmware 2.1.0.2 and get the online % to 98%. | Working through software bugs with current firmware version. | Piloted a handful of devices with new firmware to vet updates. | Began updating ZM1's with newest firmware. Online % is at 95%. | All online ZM1's have been updated to latest firmware. Have begun the TLS enabling process on those devices. | Complete | [5 empty] | Daniel Bosco | Daniel.Bosco@pacificorp.com
Note on C2: Author: Select cells for dropdown list.

## Table 2
| Utility | PacifiCorp | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-02-01 | HWW = High wind warning
RFW = Red flag warning
[10 empty] | Actuals | [15 empty] | Note: These columns are placeholders for future QR submissions. | [7 empty] | Projected
| Table 2: Performance Metrics | [8 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 14 | 0 | 0 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 3 | 0 | 0 | 3 | 6 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 2 | 0 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 105 | 50 | 51 | 48 | 74 | 29 | 51 | 146 | 55 | 22 | 3 | 2 | 33 | 13 | 18 | 14 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 6 | 2 | 4 | 2 | 9 | 8 | 1 | 8 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 18 | 2 | 0 | 1 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 5 | 2 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 2 | 0 | 0 | 11 | 2 | 0 | 0 | 7 | 15 | 1 | 0 | 0 | 119 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 5 | 2 | [11 empty] | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | 92 | 116 | 123 | 118 | 146 | 117 | 97 | 160 | 106 | 53 | 36 | 1 | 216 | 208 | 175 | 120 | [11 empty] | Number of events
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 20 | 3 | 1 | 4 | 4 | 1 | 1 | 15 | 4 | 1 | 1 | 6 | 4 | 0 | 0 | 1 | [11 empty] | Number of events
|  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | 10 | 8 | 10 | 6 | 10 | 7 | 5 | 13 | 9 | 6 | 3 | 6 | 22 | 7 | 6 | 4 | [11 empty] | Number of events
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 4 | 4 | 10 | 9 | 4 | 4 | 9 | 9 | 4 | 9 | 2 | 0 | 4 | 4 | 4 | 1 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 12 | 14 | 14 | 9 | 11 | 11 | 9 | 7 | 5 | 6 | 25 | 6 | 9 | 17 | 23 | 12 | [11 empty] | Number of events
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 27 | 12 | 8 | 4 | 18 | 5 | 4 | 33 | 11 | 4 | 0 | 13 | 8 | 0 | 2 | 4 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 2 | 35 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 8 | 13 | 5 | 12 | 20 | 9 | 10 | 37 | 9 | 16 | 9 | 51 | 49 | 14 | 8 | 14 | [11 empty] | Number of events
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 2 | 2 | 2 | Number of events | PacifiCorp does not currently have modeled forecasts for these outages. Projected value assumes the same number of outages as in 2022.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 2 | 2 | 2 | Number of events | PacifiCorp does not currently have modeled forecasts for these outages. Projected value assumes the same number of outages as in 2022.
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 0 | [8 empty] | 13 | 13 | 13 | Number of events | PacifiCorp does not currently have modeled forecasts for these outages. Projected value assumes the same number of outages as in 2022.
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A | [27 empty] | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 420; Actuals 2: 252; Actuals 3: 360; Actuals 4: 4536 |  |  |  | hours
|  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 888; Actuals 2: 919.2; Actuals 3: 11352; Actuals 4: 11164.8 |  |  |  | hours
|  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 696; Actuals 2: NA; Actuals 3: NA; Actuals 4: 6672 |  |  |  | hours
|  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 715.2; Actuals 2: NA; Actuals 3: NA; Actuals 4: 6672 |  |  |  | hours
|  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 336; Actuals 2: 384; Actuals 3: 72; Actuals 4: 708 |  |  |  | hours
|  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 1002; Actuals 2: 2112; Actuals 3: 1224; Actuals 4: 3768 |  |  |  | hours
|  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 24; Actuals 2: 4728; Actuals 3: 144; Actuals 4: 336 |  |  |  | hours
|  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 24; Actuals 2: 4728; Actuals 3: 144; Actuals 4: 336 |  |  |  | hours
|  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours | bar: Actuals 1 to Actuals 4
|  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | [27 empty] | hours | bar: Actuals 1 to Actuals 4
|  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 432; Actuals 2: 0; Actuals 3: 384; Actuals 4: 336 |  |  |  | hours
|  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 432; Actuals 2: 0; Actuals 3: 384; Actuals 4: 336 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 10104; Actuals 2: 9912; Actuals 3: 3360; Actuals 4: 13104 |  |  |  | hours
|  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 18624; Actuals 2: 19944; Actuals 3: 24864; Actuals 4: 101520 |  |  |  | hours
|  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 14736; Actuals 2: 17496; Actuals 3: 21576; Actuals 4: 16440 |  |  |  | hours
|  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 16560; Actuals 2: 18864; Actuals 3: 21576; Actuals 4: 84667.2 |  |  |  | hours
|  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 11952; Actuals 2: 15984; Actuals 3: 17736; Actuals 4: 20148 |  |  |  | hours
|  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 16665.6; Actuals 2: 25369.2; Actuals 3: 22680; Actuals 4: 24609.6 |  |  |  | hours
|  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 19848; Actuals 2: 7272; Actuals 3: 1752; Actuals 4: 8736 |  |  |  | hours
|  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 21352.8; Actuals 2: 42663.6; Actuals 3: 11322; Actuals 4: 26352 |  |  |  | hours
|  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 41016; Actuals 2: 28344; Actuals 3: NA; Actuals 4: 47016 |  |  |  | hours
|  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 108840; Actuals 2: 28344; Actuals 3: NA; Actuals 4: 47016 |  |  |  | hours
|  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 15000; Actuals 2: 7152; Actuals 3: 26712; Actuals 4: 4920 |  |  |  | hours
|  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 20112; Actuals 2: 17859.6; Actuals 3: 29832; Actuals 4: 21192 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 87024; Actuals 2: 52572; Actuals 3: 22824; Actuals 4: 98808 |  |  |  | hours
|  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | Actuals 1: 128808; Actuals 2: 136536; Actuals 3: 95976; Actuals 4: 140568 |  |  |  | hours
|  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 61344; Actuals 2: 18084; Actuals 3: 21576; Actuals 4: 16056 |  |  |  | hours
|  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | Actuals 1: 142344; Actuals 2: 19656; Actuals 3: 21888; Actuals 4: 16296 |  |  |  | hours
|  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 17976; Actuals 2: 16416; Actuals 3: 17928; Actuals 4: 24300 |  |  |  | hours
|  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | Actuals 1: 99840; Actuals 2: 102772.8; Actuals 3: 104991.6; Actuals 4: 134544 |  |  |  | hours
|  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 19968; Actuals 2: 43104; Actuals 3: 56688; Actuals 4: 46896 |  |  |  | hours
|  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | Actuals 1: 56976; Actuals 2: 145992; Actuals 3: 148584; Actuals 4: 150511.2 |  |  |  | hours
|  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 25440; Actuals 2: 60504; Actuals 3: NA; Actuals 4: 150552 |  |  |  | hours
|  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | Actuals 1: 25440; Actuals 2: 60504; Actuals 3: NA; Actuals 4: 150552 |  |  |  | hours
|  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 15144; Actuals 2: 92208; Actuals 3: 60936; Actuals 4: 22152 |  |  |  | hours
|  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | Actuals 1: 99430.8; Actuals 2: 92424; Actuals 3: 110271.6; Actuals 4: 103804.8 |  |  |  | hours
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Number of orders |  | Not able to provide at this time. PacifiCorp does not currently issue vegetation management work at the task by task level with specific "work orders", but rather at the circuit level. That being said, PacifiCorp does identify vegetation management activities at the work location level within its mobile data management software. PacifiCorp is currently reviewing its data to identify a process to more accurately identify work locations that may be "open"/unresolved considering limitations and other variables within its mobile data management software. PacifiCorp does not assign completion date requirements at the work location level.
|  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | [27 empty] | Number of orders |  | Not able to provide at this time. PacifiCorp does not currently issue vegetation management work at the task by task level with specific "work orders", but rather at the circuit level. That being said, PacifiCorp does identify vegetation management activities at the work location level within its mobile data management software. PacifiCorp is currently reviewing its data to identify a process to more accurately identify work locations that may be "open"/unresolved considering limitations and other variables within its mobile data management software. PacifiCorp does not assign completion date requirements at the work location level.
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 4: 12161; Actuals 1: 13899; Actuals 2: 13435; Actuals 3: 13131; Actuals 4: 12865 |  |  |  | Number of orders
|  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 4: 53; Actuals 1: 115; Actuals 2: 90; Actuals 3: 113; Actuals 4: 118 |  |  |  | Number of orders
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: 2; Actuals 2: 4; Actuals 3: 4; Actuals 4: 0 |  |  |  | Hours
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of fatalities
|  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of injuries
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 1000
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of structures
|  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of structures
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 3 | 8 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 5 | 5 | 1 | 0.03 | 1 | 0 | [11 empty] | Acres
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 2 | 4 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Number of ignitions
|  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 1 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | [11 empty] | Number of ignitions
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 2579 | 8470 | 3392 | 6206 | 3323 | 7241 | 9349 | 0 | 1313 | 8472 | 8927 | 47 | 1354 | 12907 | 4627 | 50 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 1628 | 89 | 1020 | 947 | 1900 | 1554 | 4 | 27 | 481 | 2533 | 1085 | 1498 | 1351 | 1925 | 1537 | 1 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 30 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 101 | 28 | 14 | 102 | 119 | 169 | 7 | 0 | 44 | 190 | 120 | 113 | 48 | 101 | 130 | 32 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 79.3283 | 301.5732 | 148.5721 | 277.7206 | 114.1864 | 235.7866 | 423.2307 | 0 | 44.9089 | 297.7934 | 411.9111 | 2.2075 | 36.8431 | 501.8336 | 222.0168 | 1.4875 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 63.39 | 4.2594 | 44.8167 | 50.3761 | 64.7108 | 67.8843 | 0.13135 | 1.2926 | 12.458 | 79.8948 | 62.9138 | 69.7687 | 36.8431 | 77.4827 | 75.154 | 0.027248 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7794 | 83.8064 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 49.2255 | 24.3427 | 14.3811 | 42.4241 | 51.9623 | 93.4586 | 2.809 | 0 | 16.6965 | 79.4446 | 62.8062 | 61.5021 | 1.2946 | 3.0029 | 5.4622 | 1.5759 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 38 | 14 | 22 | 14 | 17 | 45 | 3 | 0 | 16 | 48 | 20 | 25 | 24 | 26 | 7 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 514 | 23 | 554 | 358 | 783 | 677 | 0 | 23 | 323 | 1479 | 409 | 524 | 789 | 824 | 432 | 2 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 6 | 0 | 2 | 2 | 6 | 11 | 0 | 0 | 5 | 11 | 5 | 12 | 3 | 3 | 11 | 1 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 193 | 11 | 198 | 155 | 335 | 195 | 0 | 1 | 51 | 320 | 183 | 261 | 145 | 265 | 285 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 1 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 2 | 3 | 1 | 1 | 4 | 2 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 982 | 0 | 0 | 167 | 879 | 0 | 0 | 45 | 941 | 0 | 0 | 104 | 931 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 4 | 4 | 0 | 0 | 126 | 419 | 0 | 1 | 320 | 0 | 0 | 0 | 104 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 23 | 4 | 0 | 0 | 6 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 35.7956 | 0 | 0 | 6.9852 | 29.8586 | 0 | 0 | 2.1332 | 33.2084 | 0 | 0 | 2.906 | 35.931 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0.16045 | 0.16855 | 0 | 0 | 5.2277 | 14.672 | 0 | 0.019145 | 12.842 | 0 | 0 | 0 | 2.906 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 32.1878 | 0 | 0 | 17.9285 | 5.2152 | 0 | 0 | 0.1677 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 1 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 6 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 3 | 4 | 0 | 0 | 63 | 174 | 0 | 0 | 134 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 | 0 | 0 | 0 | 30 | 72 | 0 | 0 | 65 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 4537 | 5577 | 4628 | 17564 | 6972 | 4075 | 12401 | 8253 | 6508 | 1903 | 13874 | 3991 | 3458 | 10019 | 9921 | 7073 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 1441 | 4280 | 3754 | 273 | 1293 | 1343 | 2835 | 2528 | 2216 | 2154 | 1341 | 57 | 3838 | 1688 | 573 | 8 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 64 | 238 | 392 | 42 | 53 | 100 | 191 | 220 | 88 | 282 | 52 | 55 | 199 | 73 | 104 | 10 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 169.8134 | 183.6261 | 209.7333 | 607.227 | 220.9141 | 133.4113 | 570.4041 | 406.9474 | 281.1882 | 73.2631 | 599.0697 | 183.6275 | 133.8173 | 408.1634 | 463.3994 | 310.729 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 70.0922 | 166.4924 | 197.7294 | 12.2699 | 48.4138 | 48.0439 | 129.4298 | 115.6299 | 112.891 | 66.9203 | 58.4475 | 2.4853 | 166.9677 | 65.8557 | 27.5597 | 0.48141 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 4.7155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.349 | 3.6537 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 40.2115 | 130.8143 | 202.624 | 37.6543 | 37.3227 | 48.0399 | 126.1231 | 123.414 | 42.378 | 124.4164 | 38.0007 | 52.139 | 9.106 | 2.5009 | 4.3377 | 0.50503 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 55 | 112 | 78 | 16 | 37 | 42 | 42 | 48 | 70 | 31 | 36 | 2 | 81 | 34 | 8 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 415 | 1744 | 838 | 158 | 588 | 711 | 946 | 709 | 577 | 1374 | 363 | 29 | 1594 | 716 | 196 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 13 | 20 | 33 | 1 | 6 | 5 | 10 | 14 | 3 | 14 | 1 | 5 | 13 | 5 | 5 | 1 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 210 | 636 | 902 | 49 | 197 | 138 | 482 | 480 | 453 | 414 | 145 | 8 | 467 | 279 | 86 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 2 | 13 | 3 | 0 | 1 | 4 | 3 | 1 | 0 | 4 | 0 | 0 | 8 | 1 | 4 | 3 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 625 | 4269 | 0 | 2047 | 128 | 5054 | 1082 | 200 | 0 | 5327 | 0 | 200 | 328 | 4578 | 385 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 739 | 108 | 135 | 386 | 401 | 548 | 6 | 348 | 462 | 527 | 346 | 711 | 328 | 952 | 189 | 669 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 1622 | 3124 | 0 | 721 | 1613 | 3136 | 0 | 619 | 4529 | 0 | 0 | 611 | 1 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 30 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 38 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 31.5915 | 233.4004 | 0 | 129.4241 | 8.1241 | 288.1146 | 61.5448 | 12.8794 | 0 | 318.8503 | 0 | 12.8794 | 15.1556 | 295.1773 | 22.5571 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 41.3002 | 6.4247 | 7.8091 | 34.3734 | 22.0989 | 30.582 | 0.44052 | 31.3994 | 28.148 | 30.1501 | 26.9273 | 32.2433 | 15.1556 | 45.509 | 9.4743 | 41.3888 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 109.4084 | 374.0537 | 0 | 86.9698 | 109.4084 | 374.0537 | 0 | 106.553 | 435.113 | 0 | 0 | 99.7818 | 47.2348 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 25.6468 | 0 | 78.2808 | 0 | 0 | 0 | 0 | 0 | 1.7068 | 0.034838 | 0 | 0 | 1.9008 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 3 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 13 | 0 | 1 | 0 | 7 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 2 | 0 | 28 | 171 | 3 | 7 | 1 | 12 | 5 | 8 | 0 | 43 | 3 | 7 | 44 | 151 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 5 | 0 | 36 | 202 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 64 | 5 | 0 | 22 | 172 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 753 | 0 | 0 | 0 | 496 | 257 | 0 | 0 | 496 | 0 | 0 | 43 | 452 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 260 | 9 | 1 | 1 | 112 | 157 | 0 | 0 | 74 | 197 | 0 | 0 | 43 | 191 | 4 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 239 | 257 | 0 | 0 | 239 | 257 | 0 | 0 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 39.6943 | 0 | 0 | 0 | 25.3447 | 14.3496 | 0 | 0 | 25.3447 | 0 | 0 | 1.7223 | 23.2764 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 14.5171 | 0.48285 | 0.055835 | 0.055835 | 6.2535 | 8.7661 | 0 | 0 | 4.1318 | 10.9799 | 0 | 0 | 1.7223 | 9.5727 | 0.16021 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 93.5272 | 78.2808 | 0 | 0 | 93.5272 | 78.2808 | 0 | 0 | 171.808 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 78.2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 8 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 457 | 3404 | 0 | 3294 | 623 | 4007 | 1133 | 1328 | 1131 | 3888 | 1209 | 1527 | 417 | 2778 | 1848 | 849 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 418 | 712 | 455 | 202 | 112 | 1122 | 526 | 385 | 164 | 537 | 956 | 512 | 267 | 89 | 173 | 741 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 794 | 5006 | 0 | 1634 | 789 | 3918 | 0 | 1832 | 3974 | 0 | 0 | 1758 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 7 | 0 | 61 | 20 | 0 | 0 | 0 | 66 | 2 | 4 | 0 | 0 | 28 | [11 empty] | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 25.1395 | 217.8381 | 0 | 206.5046 | 33.5622 | 270.1722 | 65.0259 | 79.4804 | 64.7931 | 248.296 | 68.3847 | 106.2417 | 21.6231 | 175.8587 | 127.2586 | 51.1151 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 23.3696 | 43.2218 | 50.6165 | 14.0859 | 7.4204 | 62.2509 | 29.9904 | 22.4988 | 19.5522 | 33.2651 | 99.0876 | 20.5875 | 13.6324 | 4.5531 | 8.8138 | 47.1244 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 107.9819 | 472.4462 | 0 | 165.8985 | 108.0466 | 394.6036 | 0 | 148.2353 | 491.4828 | 0 | 0 | 150.8632 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 20.0362 | 0 | 111.6309 | 33.3501 | 0 | 0 | 0 | 77.8426 | 1.0214 | 0.07021 | 0 | 0 | 1.4463 | [11 empty] | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 5 | 3 | 3 | 2 | 3 | 56 | 0 | 2 | 3 | 16 | 49 | 23 | 0 | 0 | 6 | 11 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 6 | 11 | 44 | 72 | 80 | 202 | 22 | 3 | 18 | 48 | 61 | 122 | 1 | 0 | 46 | 191 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 3 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 1 | 0 | 1 | 43 | 0 | 179 | 0 | 0 | 0 | 104 | 77 | 77 | 2 | 0 | 10 | 118 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | [11 empty] | # of findings from these asset inspections
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 27 | 15 | 18 | 14 | 9 | 53 | 3 | 1 | 14 | 41 | 22 | 27 | 22 | 28 | 23 | 6 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 734 | 315 | 51 | 58 | 294 | 622 | 344 | 221 | 483 | 600 | 736 | 508 | 336 | 608 | 111 | 556 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 4 | 3 | 1 | 0 | 0 | 1 | 5 | 2 | 2 | 4 | 8 | 1 | 2 | 8 | 0 | 16 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 251 | 89 | 36 | 36 | 143 | 500 | 209 | 502 | 240 | 287 | 291 | 590 | 435 | 397 | 42 | 649 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 3 | 0 | 1 | 0 | 0 | 3 | 1 | 6 | 2 | 1 | 0 | 4 | 2 | 3 | 1 | 6 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 145 | 75 | 4 | 3 | 2 | 44 | 25 | 7 | 5 | 9 | 37 | 13 | 41 | 63 | 8 | 25 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 30 | 9 | 3 | 0 | 2 | 6 | 14 | 22 | 4 | 23 | 68 | 32 | 61 | 26 | 16 | 5 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 46 | 93 | 74 | 40 | 33 | 37 | 48 | 28 | 66 | 45 | 29 | 12 | 49 | 71 | 59 | 14 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 942 | 413 | 216 | 142 | 862 | 2158 | 920 | 1013 | 1289 | 1267 | 893 | 483 | 813 | 953 | 797 | 310 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 12 | 11 | 2 | 0 | 12 | 10 | 6 | 9 | 17 | 24 | 15 | 12 | 14 | 5 | 4 | 2 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 376 | 185 | 104 | 69 | 634 | 1776 | 666 | 927 | 631 | 622 | 490 | 552 | 908 | 504 | 463 | 206 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 2 | 3 | 0 | 0 | 4 | 10 | 7 | 7 | 11 | 5 | 3 | 1 | 4 | 3 | 5 | 2 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 1 | 1 | 3 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 12 | 1 | 3 | 1 | 7 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 5 | 2 | 77 | 7 | 8 | 41 | 186 | 73 | 68 | 9 | 27 | 38 | 80 | 19 | 5 | 33 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 7 | 2 | 8 | 7 | 18 | 2 | 4 | 37 | 7 | 12 | 31 | 86 | 119 | 72 | 16 | 52 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 1 | 0 | 2 | 0 | 0 | 1 | 22 | 12 | 5 | 1 | 1 | 0 | 9 | 10 | 0 | 3 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 24 | 3 | 50 | 0 | 0 | 2 | 15 | 0 | 3 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 4 | 3 | 2 | 1 | 2 | 22 | 33 | 1 | 1 | 3 | 47 | 38 | 1 | 4 | 2 | 15 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 7 | 112 | 55 | 11 | 5 | 159 | 77 | 24 | 37 | 52 | 37 | 25 | 93 | 20 | 12 | 37 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 13 | 129 | 18 | 10 | 14 | 169 | 15 | 7 | 24 | 16 | 12 | 30 | 181 | 12 | 28 | 47 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | [11 empty] | # of asset inspection findings which have been fixed
x | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | Actuals 2: 5341; Actuals 3: 2930; Actuals 4: 925; Actuals 1: 2838; Actuals 2: 2340; Actuals 3: 3966; Actuals 4: 1023 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of trees found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal).
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | Actuals 2: 3340; Actuals 3: 1668; Actuals 4: 2071; Actuals 1: 2377; Actuals 2: 2408; Actuals 3: 399; Actuals 4: 1346 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | Actuals 2: 321; Actuals 3: 234; Actuals 4: 24; Actuals 1: 2; Actuals 2: 195; Actuals 3: 64; Actuals 4: 361 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | Actuals 2: 452; Actuals 3: 289; Actuals 4: 87; Actuals 1: 139; Actuals 2: 565; Actuals 3: 162; Actuals 4: 68 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | Actuals 2: 240; Actuals 3: 907; Actuals 4: 92; Actuals 1: 973; Actuals 2: 265; Actuals 3: 3438; Actuals 4: 296 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | Actuals 2: 2041; Actuals 3: 2230; Actuals 4: 3318; Actuals 1: 4287; Actuals 2: 6483; Actuals 3: 2884; Actuals 4: 6451 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | Actuals 2: 101; Actuals 3: 17; Actuals 4: 19; Actuals 1: 47; Actuals 2: 243; Actuals 3: 243; Actuals 4: 350 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | Actuals 2: 335; Actuals 3: 269; Actuals 4: 321; Actuals 1: 165; Actuals 2: 91; Actuals 3: 9; Actuals 4: 755 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | Actuals 2: 0; Actuals 3: 0; Actuals 4: 0; Actuals 1: 165; Actuals 2: 23; Actuals 3: 1; Actuals 4: 12 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | Actuals 2: 156; Actuals 3: 8; Actuals 4: 57; Actuals 1: 0; Actuals 2: 35; Actuals 3: 0; Actuals 4: 14 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | [27 empty] | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | Actuals 2: 57; Actuals 3: 3; Actuals 4: 1; Actuals 1: 3; Actuals 2: 23; Actuals 3: 0; Actuals 4: 3 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | [27 empty] | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | Actuals 2: 24; Actuals 3: 79; Actuals 4: 535; Actuals 1: 65; Actuals 2: 32; Actuals 3: 127; Actuals 4: 410 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2022.
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A | Actuals 1: N/A; Actuals 2: N/A; Actuals 3: N/A; Actuals 4: N/A; Actuals 1: N/A; Actuals 2: N/A; Actuals 3: N/A; Actuals 4: N/A; Actuals 1: N/A; Actuals 2: N/A; Actuals 3: N/A; Actuals 4: N/A |  |  |  | Percentage of customers notified of evacuation | PacifiCorp does not have authority to order evacuations. This is a local jurisdiction Incident Command authority. Local jurisdictions use their own alert and warning system to execute evacuation orders.

## Table 3
Utility | PacifiCorp
Table No. | 3
Date Modified | 2024-02-01
[5 empty] | Actual | [7 empty] | Note: These columns are placeholders for future QR submissions. | [7 empty] | Projected
Table 3: List and description of additional metrics |  |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
PC3a | Events Recorded with Fire Reference: Not Fire Season |  | Data source is outage reporting system in which outage makes reference to fire in comment or outage cause | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Actual 1: 0; Actual 2: 3; Actual 3: 0; Actual 4: 7; Actual 1: 0; Actual 2: 0; Actual 3: 0; Actual 4: 0 | 2 | 2 | 2
PC3b | Events Recorded with Fire Reference: Fire Season |  | Data source is outage reporting system in which outage makes reference to fire in comment or outage cause | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Actual 1: 0; Actual 2: 0; Actual 3: 0; Actual 4: 0; Actual 1: 0; Actual 2: 0; Actual 3: 0; Actual 4: 0 | 0 | 0 | 0
PC4a | Events Recorded with Fire Reference: damage fire, equipment fire, pole fire: Not Fire Season |  | Subset of PC3 where record makes reference to utility equipment or key components | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Actual 1: 0; Actual 2: 3; Actual 3: 0; Actual 4: 2; Actual 1: 0; Actual 2: 0; Actual 3: 0; Actual 4: 0 | 1 | 1 | 1
PC4b | Events Recorded with Fire Reference: damage fire, equipment fire, pole fire: Fire Season |  | Subset of PC3 where record makes reference to utility equipment or key components | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Actual 1: 0; Actual 2: 0; Actual 3: 0; Actual 4: 0; Actual 1: 0; Actual 2: 0; Actual 3: 0; Actual 4: 0 | 0 | 0 | 0
PC5 | Wire down risks |  | Data source is outage reporting system in which cause code or comments would result in downed conductor during fire season | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Actual 1: 0; Actual 2: 0; Actual 3: 7; Actual 4: 18; Actual 1: 59; Actual 2: 7; Actual 3: 6; Actual 4: 5 | 6 | 6 | 6
PC6 | Wire down trend |  | Reduction in quantity of wire down events, year over year, during the designated fire season period | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Actual 1: 0; Actual 2: 0; Actual 3: -1; Actual 4: 18; Actual 1: 59; Actual 2: 7; Actual 3: -1; Actual 4: -13 | 4 | 4 | 4

## Table 4
Utility | PacifiCorp
Table No. | 4
Date Modified | 2024-02-01
Note: These columns are placeholders for future QR submissions.
Table 4: Weather patterns |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Metric type | # | Metric name | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 0; 3: 916; 4: 0; 1: 0; 2: 0; 3: 956; 4: 435 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 0; 3: 125; 4: 0; 1: 0; 2: 0; 3: 55; 4: 9 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 1: 0; 2: 0; 3: 1365; 4: 0; 1: 0; 2: 0; 3: 1461; 4: 1356 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 0; 3: 0; 4: 0; 1: 624; 2: 0; 3: 0; 4: 0 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 0; 3: 0; 4: 0; 1: 62; 2: 0; 3: 0; 4: 0 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 1: 0; 2: 0; 3: 0; 4: 607; 1: 550; 2: 0; 3: 0; 4: 0 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 1: 0; 2: 0; 3: 916; 4: 0; 1: 624; 2: 0; 3: 956 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 1: 0; 2: 0; 3: 125; 4: 0; 1: 62; 2: 0; 3: 55; 4: 9 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 1: 0; 2: 0; 3: 1365; 4: 607; 1: 550; 2: 0; 3: 1461; 4: 1356 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 3: 70177.249 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110. |  | FPI began full operation in Q3 2023 and data for previous quarters and years are not available.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 3: 6292.637 | Fire potential index overhead circuit mile days, see above for definition |  | FPI began full operation in Q3 2023 and data for previous quarters and years are not available.
| 4.c. | Fire potential index circuit mile days - non-HFTD | 3: 67352.841 | Fire potential index overhead circuit mile days, see above for definition |  | FPI began full operation in Q3 2023 and data for previous quarters and years are not available.
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed) | [18 empty] | N/A

## Table 5
| Utility | PacifiCorp | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-02-01 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[8 empty] | Actual number of risk events | [15 empty] | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 2; Actual number of risk events Q4: 1 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 4; Actual number of risk events Q2: 4; Actual number of risk events Q3: 3; Actual number of risk events Q4: 11; Actual number of risk events Q1: 21; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 3 | 29 | 29 | 29 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 11; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 3; Actual number of risk events Q2: 3; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 5; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 6; Actual number of risk events Q1: 13; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 4; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 5; Actual number of risk events Q2: 12; Actual number of risk events Q3: 19; Actual number of risk events Q4: 5; Actual number of risk events Q1: 4; Actual number of risk events Q2: 5; Actual number of risk events Q3: 18; Actual number of risk events Q4: 11 | 43 | 43 | 43 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 2; Actual number of risk events Q3: 4; Actual number of risk events Q4: 3; Actual number of risk events Q1: 4; Actual number of risk events Q2: 7; Actual number of risk events Q3: 2; Actual number of risk events Q4: 1 | 12 | 12 | 12 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 1; Actual number of risk events Q3: 2; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 3; Actual number of risk events Q2: 0; Actual number of risk events Q3: 3; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 6; Actual number of risk events Q3: 3; Actual number of risk events Q4: 2; Actual number of risk events Q1: 0; Actual number of risk events Q2: 5; Actual number of risk events Q3: 3; Actual number of risk events Q4: 0 | 12 | 12 | 12 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 21; Actual number of risk events Q2: 20; Actual number of risk events Q3: 15; Actual number of risk events Q4: 79; Actual number of risk events Q1: 82; Actual number of risk events Q2: 14; Actual number of risk events Q3: 9; Actual number of risk events Q4: 17 | 134 | 134 | 134 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 29; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 4 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 4; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD |  | Actual number of risk events Q1: 15; Actual number of risk events Q2: 24; Actual number of risk events Q3: 12; Actual number of risk events Q4: 12; Actual number of risk events Q1: 27; Actual number of risk events Q2: 13; Actual number of risk events Q3: 11; Actual number of risk events Q4: 5 | 52 | 52 | 52 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD |  | Actual number of risk events Q1: 19; Actual number of risk events Q2: 20; Actual number of risk events Q3: 14; Actual number of risk events Q4: 19; Actual number of risk events Q1: 34; Actual number of risk events Q2: 12; Actual number of risk events Q3: 8; Actual number of risk events Q4: 14 | 73 | 73 | 73 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 3; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD |  | Actual number of risk events Q1: 29; Actual number of risk events Q2: 23; Actual number of risk events Q3: 38; Actual number of risk events Q4: 31; Actual number of risk events Q1: 38; Actual number of risk events Q2: 41; Actual number of risk events Q3: 17; Actual number of risk events Q4: 25 | 136 | 136 | 136 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 4; Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 4; Actual number of risk events Q4: 0 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrester | Distribution | Non-HFTD |  | Actual number of risk events Q1: 1; Actual number of risk events Q2: 3; Actual number of risk events Q3: 2; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 2; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 13 | 13 | 13 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrester | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 1; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD |  | Actual number of risk events Q1: 9; Actual number of risk events Q2: 10; Actual number of risk events Q3: 15; Actual number of risk events Q4: 4; Actual number of risk events Q1: 10; Actual number of risk events Q2: 28; Actual number of risk events Q3: 13; Actual number of risk events Q4: 8 | 39 | 39 | 39 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 6; Actual number of risk events Q2: 10; Actual number of risk events Q3: 5; Actual number of risk events Q4: 10; Actual number of risk events Q1: 11; Actual number of risk events Q2: 4; Actual number of risk events Q3: 8; Actual number of risk events Q4: 2 | 24 | 24 | 24 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD |  | Actual number of risk events Q1: 3; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 5; Actual number of risk events Q2: 9; Actual number of risk events Q3: 4; Actual number of risk events Q4: 1 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 2; Actual number of risk events Q4: 2; Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 39; Actual number of risk events Q3: 9; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 3; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD |  | Actual number of risk events Q1: 30; Actual number of risk events Q2: 36; Actual number of risk events Q3: 30; Actual number of risk events Q4: 29; Actual number of risk events Q1: 24; Actual number of risk events Q2: 23; Actual number of risk events Q3: 50; Actual number of risk events Q4: 22 | 116 | 116 | 116 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 1; Actual number of risk events Q2: 1; Actual number of risk events Q3: 6; Actual number of risk events Q4: 2 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 1; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD |  | Actual number of risk events Q1: 18; Actual number of risk events Q2: 10; Actual number of risk events Q3: 21; Actual number of risk events Q4: 70; Actual number of risk events Q1: 94; Actual number of risk events Q2: 4; Actual number of risk events Q3: 18; Actual number of risk events Q4: 15 | 136 | 136 | 136 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 26; Actual number of risk events Q2: 2; Actual number of risk events Q3: 3; Actual number of risk events Q4: 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 2; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 |  | Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0; Actual number of risk events Q1: 0; Actual number of risk events Q2: 0; Actual number of risk events Q3: 0; Actual number of risk events Q4: 0 | 0 | 0 | 0 | # risk events (excluding ignitions)

## Table 6
| Utility | PacifiCorp | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-02-01 | Data from 2015 - 2021 should be actual numbers. 2022 and 2023 should be projected. In future submissions update projected numbers with actuals
[7 empty] | Actual number of ignitions | [15 empty] | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 2; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 2; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 2 | 2 | 2 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 1; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment/facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 1; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and brushing | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and brushing | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and brushing | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and brushing | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and brushing | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and brushing | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrestor | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrestor | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrestor | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrestor | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrestor | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrestor | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 1; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 1 | 1 | 1 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0; Actual number of ignitions Q1: 0; Actual number of ignitions Q2: 0; Actual number of ignitions Q3: 0; Actual number of ignitions Q4: 0 | 0 | 0 | 0 | # ignitions

## Table 7
| Utility | PacifiCorp
| Table No. | 7
| Date Modified | 2024-02-01
[7 empty] | Actual | [15 empty] | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q4: 23.22; Actual Q1: 23.27; Actual Q2: 23.29; Actual Q3: 23.29; Actual Q4: 23.33 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q4: 23.31; Actual Q1: 23.21; Actual Q2: 23.28; Actual Q3: 23.31; Actual Q4: 23.31 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q4: 390.11; Actual Q1: 390.21; Actual Q2: 390.31; Actual Q3: 390.37; Actual Q4: 390.49 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q4: 319.74; Actual Q1: 319.21; Actual Q2: 319.59; Actual Q3: 319.61; Actual Q4: 319.51 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q4: 165.54; Actual Q1: 165.53; Actual Q2: 165.55; Actual Q3: 165.57; Actual Q4: 165.57 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 782.74; Actual Q1: 779.68; Actual Q2: 779.72; Actual Q3: 779.05; Actual Q4: 779.21 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q4: 4.54; Actual Q1: 4.54; Actual Q2: 4.54; Actual Q3: 4.54; Actual Q4: 4.54 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0.03; Actual Q1: 0.03; Actual Q2: 0.03; Actual Q3: 0.03; Actual Q4: 0.03 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q4: 324.56; Actual Q1: 324.67; Actual Q2: 324.39; Actual Q3: 324.38; Actual Q4: 323.88 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 92.02; Actual Q1: 91.95; Actual Q2: 91.93; Actual Q3: 91.92; Actual Q4: 91.57 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 206.92; Actual Q1: 207.03; Actual Q2: 206.94; Actual Q3: 206.99; Actual Q4: 206.7 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 145.41; Actual Q1: 145.51; Actual Q2: 145.51; Actual Q3: 145.47; Actual Q4: 145.47 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q4: 34.58; Actual Q1: 34.77; Actual Q2: 34.81; Actual Q3: 34.81; Actual Q4: 34.81 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 5.7; Actual Q1: 5.58; Actual Q2: 5.59; Actual Q3: 5.59; Actual Q4: 5.59 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q4: 1.12; Actual Q1: 1.12; Actual Q2: 1.12; Actual Q3: 1.12; Actual Q4: 1.12 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q4: 1.75; Actual Q1: 1.75; Actual Q2: 1.75; Actual Q3: 1.75; Actual Q4: 1.75 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q4: 66.66; Actual Q1: 66.66; Actual Q2: 66.72; Actual Q3: 66.72; Actual Q4: 66.72 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q4: 97.49; Actual Q1: 97.49; Actual Q2: 97.44; Actual Q3: 97.44; Actual Q4: 97.44 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q4: 23.01; Actual Q1: 23.01; Actual Q2: 23.01; Actual Q3: 23.01; Actual Q4: 23.01 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 196.09; Actual Q1: 196.09; Actual Q2: 196.09; Actual Q3: 196.09; Actual Q4: 196.09 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q4: 0.7; Actual Q1: 0.7; Actual Q2: 0.7; Actual Q3: 0.7; Actual Q4: 0.7 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q4: 81.4; Actual Q1: 81.4; Actual Q2: 81.39; Actual Q3: 81.39; Actual Q4: 81.39 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 69.65; Actual Q1: 69.65; Actual Q2: 69.65; Actual Q3: 69.65; Actual Q4: 69.73 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 57.43; Actual Q1: 57.43; Actual Q2: 57.44; Actual Q3: 57.44; Actual Q4: 57.44 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 111.81; Actual Q1: 111.81; Actual Q2: 111.81; Actual Q3: 111.81; Actual Q4: 111.81 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q4: 15.42; Actual Q1: 15.42; Actual Q2: 15.44; Actual Q3: 15.44; Actual Q4: 15.44 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 7.86; Actual Q1: 7.86; Actual Q2: 7.85; Actual Q3: 7.85; Actual Q4: 7.85 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q4: 17.28; Actual Q1: 17.3; Actual Q2: 17.34; Actual Q3: 17.46; Actual Q4: 17.63 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q4: 11.61; Actual Q1: 11.6; Actual Q2: 11.62; Actual Q3: 11.63; Actual Q4: 11.65 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q4: 78.58; Actual Q1: 79.04; Actual Q2: 79.19; Actual Q3: 79.52; Actual Q4: 79.51 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q4: 45.66; Actual Q1: 45.92; Actual Q2: 45.86; Actual Q3: 45.96; Actual Q4: 45.99 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q4: 22.55; Actual Q1: 22.7; Actual Q2: 23.29; Actual Q3: 23.41; Actual Q4: 23.51 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 55.96; Actual Q1: 56.14; Actual Q2: 56.3; Actual Q3: 56.37; Actual Q4: 56.47 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q4: 1.41; Actual Q1: 1.42; Actual Q2: 1.42; Actual Q3: 1.41; Actual Q4: 1.41 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0.01; Actual Q1: 0.01; Actual Q2: 0.01; Actual Q3: 0.01; Actual Q4: 0.01 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q4: 221.36; Actual Q1: 221.42; Actual Q2: 221.53; Actual Q3: 221.87; Actual Q4: 223.36 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 27.98; Actual Q1: 27.99; Actual Q2: 28.03; Actual Q3: 27.88; Actual Q4: 28.04 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 63.17; Actual Q1: 63.2; Actual Q2: 63.2; Actual Q3: 63.24; Actual Q4: 63.55 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 30.08; Actual Q1: 30.08; Actual Q2: 30.12; Actual Q3: 30.22; Actual Q4: 30.19 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q4: 51.09; Actual Q1: 51.08; Actual Q2: 51.23; Actual Q3: 51.22; Actual Q4: 51.06 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 3.54; Actual Q1: 3.54; Actual Q2: 3.54; Actual Q3: 3.55; Actual Q4: 3.56 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q4: 131; Actual Q1: 130; Actual Q2: 128; Actual Q3: 126; Actual Q4: 125 |  |  |  | Number of critical facilities
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q4: 81; Actual Q1: 81; Actual Q2: 81; Actual Q3: 83; Actual Q4: 82 |  |  |  | Number of critical facilities
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q4: 208; Actual Q1: 209; Actual Q2: 207; Actual Q3: 205; Actual Q4: 204 |  |  |  | Number of critical facilities
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q4: 162; Actual Q1: 163; Actual Q2: 162; Actual Q3: 161; Actual Q4: 164 |  |  |  | Number of critical facilities
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q4: 155; Actual Q1: 156; Actual Q2: 156; Actual Q3: 156; Actual Q4: 157 |  |  |  | Number of critical facilities
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 178; Actual Q1: 176; Actual Q2: 177; Actual Q3: 172; Actual Q4: 169 |  |  |  | Number of critical facilities
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q4: 4; Actual Q1: 4; Actual Q2: 4; Actual Q3: 4; Actual Q4: 4 |  |  |  | Number of critical facilities
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q4: 282; Actual Q1: 283; Actual Q2: 289; Actual Q3: 289; Actual Q4: 290 |  |  |  | Number of critical facilities
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 55; Actual Q1: 55; Actual Q2: 55; Actual Q3: 54; Actual Q4: 54 |  |  |  | Number of critical facilities
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 106; Actual Q1: 105; Actual Q2: 106; Actual Q3: 104; Actual Q4: 104 |  |  |  | Number of critical facilities
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 51; Actual Q1: 51; Actual Q2: 52; Actual Q3: 52; Actual Q4: 51 |  |  |  | Number of critical facilities
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q4: 37; Actual Q1: 38; Actual Q2: 37; Actual Q3: 36; Actual Q4: 36 |  |  |  | Number of critical facilities
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 14; Actual Q1: 14; Actual Q2: 14; Actual Q3: 14; Actual Q4: 14 |  |  |  | Number of critical facilities
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical facilities
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q4: 2972; Actual Q1: 2976; Actual Q2: 2977; Actual Q3: 2981; Actual Q4: 2976 |  |  |  | Number of residential customers
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q4: 2508; Actual Q1: 2510; Actual Q2: 2510; Actual Q3: 2514; Actual Q4: 2521 |  |  |  | Number of residential customers
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q4: 7734; Actual Q1: 7736; Actual Q2: 7742; Actual Q3: 7730; Actual Q4: 7739 |  |  |  | Number of residential customers
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q4: 2635; Actual Q1: 2634; Actual Q2: 2633; Actual Q3: 2633; Actual Q4: 2632 |  |  |  | Number of residential customers
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q4: 2365; Actual Q1: 2367; Actual Q2: 2373; Actual Q3: 2425; Actual Q4: 2425 |  |  |  | Number of residential customers
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 2477; Actual Q1: 2479; Actual Q2: 2477; Actual Q3: 2422; Actual Q4: 2417 |  |  |  | Number of residential customers
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q4: 139; Actual Q1: 139; Actual Q2: 138; Actual Q3: 138; Actual Q4: 138 |  |  |  | Number of residential customers
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q4: 10732; Actual Q1: 10731; Actual Q2: 10747; Actual Q3: 10664; Actual Q4: 10662 |  |  |  | Number of residential customers
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 574; Actual Q1: 574; Actual Q2: 574; Actual Q3: 559; Actual Q4: 555 |  |  |  | Number of residential customers
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 3221; Actual Q1: 3224; Actual Q2: 3234; Actual Q3: 3200; Actual Q4: 3208 |  |  |  | Number of residential customers
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 630; Actual Q1: 632; Actual Q2: 631; Actual Q3: 602; Actual Q4: 601 |  |  |  | Number of residential customers
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q4: 927; Actual Q1: 927; Actual Q2: 927; Actual Q3: 928; Actual Q4: 928 |  |  |  | Number of residential customers
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 67; Actual Q1: 68; Actual Q2: 68; Actual Q3: 64; Actual Q4: 67 |  |  |  | Number of residential customers
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of residential customers
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q4: 359; Actual Q1: 360; Actual Q2: 356; Actual Q3: 354; Actual Q4: 353 |  |  |  | Number of commercial customers
|  | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q4: 533; Actual Q1: 533; Actual Q2: 533; Actual Q3: 532; Actual Q4: 533 |  |  |  | Number of commercial customers
|  | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q4: 1342; Actual Q1: 1342; Actual Q2: 1344; Actual Q3: 1340; Actual Q4: 1340 |  |  |  | Number of commercial customers
|  | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q4: 971; Actual Q1: 973; Actual Q2: 976; Actual Q3: 969; Actual Q4: 969 |  |  |  | Number of commercial customers
|  | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q4: 565; Actual Q1: 566; Actual Q2: 566; Actual Q3: 565; Actual Q4: 567 |  |  |  | Number of commercial customers
|  | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 977; Actual Q1: 978; Actual Q2: 979; Actual Q3: 978; Actual Q4: 980 |  |  |  | Number of commercial customers
|  | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q4: 30; Actual Q1: 30; Actual Q2: 30; Actual Q3: 30; Actual Q4: 30 |  |  |  | Number of commercial customers
|  | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of commercial customers
|  | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q4: 1928; Actual Q1: 1930; Actual Q2: 1944; Actual Q3: 1936; Actual Q4: 1941 |  |  |  | Number of commercial customers
|  | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 303; Actual Q1: 306; Actual Q2: 312; Actual Q3: 306; Actual Q4: 306 |  |  |  | Number of commercial customers
|  | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 598; Actual Q1: 601; Actual Q2: 603; Actual Q3: 599; Actual Q4: 602 |  |  |  | Number of commercial customers
|  | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 242; Actual Q1: 242; Actual Q2: 242; Actual Q3: 233; Actual Q4: 234 |  |  |  | Number of commercial customers
|  | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q4: 124; Actual Q1: 125; Actual Q2: 129; Actual Q3: 127; Actual Q4: 127 |  |  |  | Number of commercial customers
|  | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 67; Actual Q1: 67; Actual Q2: 69; Actual Q3: 65; Actual Q4: 64 |  |  |  | Number of commercial customers
|  | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
|  | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of commercial customers
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q4: 64; Actual Q1: 69; Actual Q2: 68; Actual Q3: 117; Actual Q4: 118 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q4: 49; Actual Q1: 50; Actual Q2: 51; Actual Q3: 128; Actual Q4: 140 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q4: 176; Actual Q1: 186; Actual Q2: 196; Actual Q3: 294; Actual Q4: 312 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q4: 51; Actual Q1: 54; Actual Q2: 59; Actual Q3: 67; Actual Q4: 72 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q4: 40; Actual Q1: 42; Actual Q2: 41; Actual Q3: 67; Actual Q4: 70 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 54; Actual Q1: 57; Actual Q2: 57; Actual Q3: 70; Actual Q4: 75 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 2; Actual Q4: 2 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q4: 241; Actual Q1: 253; Actual Q2: 252; Actual Q3: 278; Actual Q4: 289 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 7; Actual Q1: 10; Actual Q2: 12; Actual Q3: 14; Actual Q4: 15 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 86; Actual Q1: 92; Actual Q2: 92; Actual Q3: 105; Actual Q4: 111 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 4; Actual Q1: 6; Actual Q2: 7; Actual Q3: 13; Actual Q4: 14 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q4: 9; Actual Q1: 8; Actual Q2: 8; Actual Q3: 11; Actual Q4: 11 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers belonging to access and functional needs populations
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q4: 6; Actual Q1: 6; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5 |  |  |  | Number of substations
|  | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | [19 empty] | Number of substations | bar: Actual Q4 to Actual Q4
|  | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q4: 0; Actual Q1: 1; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 7; Actual Q1: 7; Actual Q2: 7; Actual Q3: 7; Actual Q4: 7 |  |  |  | Number of substations
|  | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | [19 empty] | Number of substations | bar: Actual Q4 to Actual Q4
|  | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | [19 empty] | Number of substations | bar: Actual Q4 to Actual Q4
|  | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q4: 6; Actual Q1: 6; Actual Q2: 9; Actual Q3: 9; Actual Q4: 9 |  |  |  | Number of weather stations
|  | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q4: 9; Actual Q1: 9; Actual Q2: 10; Actual Q3: 10; Actual Q4: 10 |  |  |  | Number of weather stations
|  | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q4: 5; Actual Q1: 4; Actual Q2: 4; Actual Q3: 4; Actual Q4: 4 |  |  |  | Number of weather stations
|  | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q4: 10; Actual Q1: 11; Actual Q2: 11; Actual Q3: 17; Actual Q4: 17 |  |  |  | Number of weather stations
|  | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q4: 12; Actual Q1: 12; Actual Q2: 15; Actual Q3: 16; Actual Q4: 16 |  |  |  | Number of weather stations
|  | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q4: 5; Actual Q1: 5; Actual Q2: 5; Actual Q3: 5; Actual Q4: 5 |  |  |  | Number of weather stations
|  | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q4: 11; Actual Q1: 11; Actual Q2: 13; Actual Q3: 13; Actual Q4: 13 |  |  |  | Number of weather stations
|  | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q4: 19; Actual Q1: 19; Actual Q2: 19; Actual Q3: 18; Actual Q4: 18 |  |  |  | Number of weather stations
|  | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q4: 3; Actual Q1: 3; Actual Q2: 3; Actual Q3: 3; Actual Q4: 3 |  |  |  | Number of weather stations
|  | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q4: 3; Actual Q1: 3; Actual Q2: 3; Actual Q3: 3; Actual Q4: 3 |  |  |  | Number of weather stations
|  | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 8
| Utility | PacifiCorp |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2024-02-01 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | [15 empty] | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.05; Actual Q2: 0.02; Actual Q3: 0; Actual Q4: 0.04 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: -0.1; Actual Q2: 0.07; Actual Q3: 0.03; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.1; Actual Q2: 0.1; Actual Q3: 0.06; Actual Q4: 0.12 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: -0.53; Actual Q2: 0.38; Actual Q3: 0.02; Actual Q4: -0.1 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: -0.01; Actual Q2: 0.02; Actual Q3: 0.02; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: -3.06; Actual Q2: 0.04; Actual Q3: -0.67; Actual Q4: 0.16 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.11; Actual Q2: -0.28; Actual Q3: -0.01; Actual Q4: -0.5 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: -0.07; Actual Q2: -0.02; Actual Q3: -0.01; Actual Q4: -0.35 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.11; Actual Q2: -0.09; Actual Q3: 0.05; Actual Q4: -0.29 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.1; Actual Q2: 0; Actual Q3: -0.04; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.19; Actual Q2: 0.04; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: -0.12; Actual Q2: 0.01; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.06; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: -0.05; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: -0.01; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0.08 |  |  |  | Circuit miles
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.01; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.02; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: -0.01; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.02; Actual Q2: 0.04; Actual Q3: 0.12; Actual Q4: 0.17 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: -0.01; Actual Q2: 0.02; Actual Q3: 0.01; Actual Q4: 0.02 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.46; Actual Q2: 0.15; Actual Q3: 0.33; Actual Q4: -0.01 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.26; Actual Q2: -0.06; Actual Q3: 0.1; Actual Q4: 0.03 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.15; Actual Q2: 0.59; Actual Q3: 0.12; Actual Q4: 0.1 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.18; Actual Q2: 0.16; Actual Q3: 0.07; Actual Q4: 0.1 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.01; Actual Q2: 0; Actual Q3: -0.01; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.06; Actual Q2: 0.11; Actual Q3: 0.34; Actual Q4: 1.49 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.01; Actual Q2: 0.04; Actual Q3: -0.15; Actual Q4: 0.16 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0.03; Actual Q2: 0; Actual Q3: 0.04; Actual Q4: 0.31 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.04; Actual Q3: 0.1; Actual Q4: -0.03 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: -0.01; Actual Q2: 0.15; Actual Q3: -0.01; Actual Q4: -0.16 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.01; Actual Q4: 0.01 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: -1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 1; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 1; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 3; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 1; Actual Q2: 4; Actual Q3: 3; Actual Q4: 0; Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 2; Actual Q3: 2; Actual Q4: 0; Actual Q1: -1; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 9; Actual Q3: 1; Actual Q4: 0; Actual Q1: 1; Actual Q2: 0; Actual Q3: 6; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 1; Actual Q2: 5; Actual Q3: 1; Actual Q4: 0; Actual Q1: 0; Actual Q2: 3; Actual Q3: 1; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 3; Actual Q3: 2; Actual Q4: 0; Actual Q1: 0; Actual Q2: 2; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 1; Actual Q2: 5; Actual Q3: 5; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: -1; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 9
| Utility | PacifiCorp
| Table No. | 9
| Date Modified | 2024-02-01
[7 empty] | Actual | [15 empty] | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0.01; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.001; Actual Q3: 0.003; Actual Q4: 0.42 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0.004; Actual Q3: 0.004; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | Actual Q1: 7.77; Actual Q2: 11.23; Actual Q3: 3.19; Actual Q4: 4.68; Actual Q1: 59.13; Actual Q2: 38.09; Actual Q3: 31.7; Actual Q4: 25.17 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 1.61; Actual Q2: 0.08; Actual Q3: 1.58; Actual Q4: 3.04; Actual Q1: 26.96; Actual Q2: 9.54; Actual Q3: 17.98; Actual Q4: 17.2 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 3.15; Actual Q3: 10.48; Actual Q4: 2.99; Actual Q1: 17.31; Actual Q2: 4.91; Actual Q3: 0; Actual Q4: 3.3 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0.08; Actual Q3: 1.39; Actual Q4: 2.86; Actual Q1: 18.22; Actual Q2: 2.9; Actual Q3: 2.53; Actual Q4: 10.75 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | Actual Q1: 2.54; Actual Q2: 2.16; Actual Q3: 4.79; Actual Q4: 0.75; Actual Q1: 15; Actual Q2: 9.68; Actual Q3: 2.86; Actual Q4: 0.1 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0.03; Actual Q2: 0.02; Actual Q3: 0; Actual Q4: 0; Actual Q1: 1.76; Actual Q2: 1.74; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0.07; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Circuit miles
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 3; Actual Q2: 3; Actual Q3: 3; Actual Q4: 3 |  |  |  | Number of substations
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 4; Actual Q2: 1; Actual Q3: 3; Actual Q4: 4 |  |  |  | Number of substations
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 4; Actual Q2: 4; Actual Q3: 3; Actual Q4: 4 |  |  |  | Number of substations
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 1; Actual Q2: 1; Actual Q3: 0; Actual Q4: 1 |  |  |  | Number of substations
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 3; Actual Q2: 3; Actual Q3: 3; Actual Q4: 3 |  |  |  | Number of substations
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 1; Actual Q1: 2; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 1; Actual Q3: 0; Actual Q4: 1 |  |  |  | Number of substations
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 2; Actual Q2: 2; Actual Q3: 2; Actual Q4: 3 |  |  |  | Number of substations
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 1; Actual Q2: 1; Actual Q3: 1; Actual Q4: 1 |  |  |  | Number of substations
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of substations
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 3; Actual Q2: 3; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 2; Actual Q2: 2; Actual Q3: 1; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 5; Actual Q2: 5; Actual Q3: 5; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 1; Actual Q2: 3; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 1; Actual Q2: 2; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of weather stations

## Table 10
Utility | PacifiCorp |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2024-02-01 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | [15 empty] | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Metric type | # | Wind Warning Status | Metric name | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW only | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW & RFW | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 2 | 2 | 2 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | All (regardless of RFW/HWW status) | Frequency of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.b. | RFW only | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW only | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW & RFW | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 20 | 20 | 20 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | All (regardless of RFW/HWW status) | Scope of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
| 1.c. | RFW only | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW only | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW & RFW | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 200 | 200 | 200 | Customer hours per year
|  | All (regardless of RFW/HWW status) | Duration of PSPS events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Customer hours per year
| 1.d. | RFW only | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 11; Actual Q4: 0 | 15 | 15 | 15 | Number of events
|  | HWW only | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 2 | 2 | 2 | Number of events
|  | HWW & RFW | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 2 | 2 | 2 | Number of events
|  | None | Frequency of fast-trip events (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 173; Actual Q4: 0 | 70 | 70 | 70 | Number of events
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 10834; Actual Q4: 0 | 44000 | 44000 | 44000 | Circuit mile days
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 6200 | 6200 | 6200 | Circuit mile days
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 6200 | 6200 | 6200 | Circuit mile days
|  | None | Circuit mile days with fast-trip settings enabled (total) | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 20000; Actual Q4: 0 | 200000 | 200000 | 200000 | Circuit mile days
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | Actual Q1: 28516; Actual Q2: 24345.5014; Actual Q3: 57416; Actual Q4: 99102; Actual Q1: 28309; Actual Q2: 51591; Actual Q3: 1573254; Actual Q4: 13335.81 | 52344.8753 | 52344.8753 | 52344.8753 | Total customer hours of planned outages per year
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | Actual Q1: 91213; Actual Q2: 8935.5333; Actual Q3: 143778; Actual Q4: 152359; Actual Q1: 311344; Actual Q2: 24979; Actual Q3: 100840; Actual Q4: 17012.77 | 99071.3833 | 99071.3833 | 99071.3833 | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Total customer hours of outages due to fast-trip per year
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | Actual Q1: 153; Actual Q2: 77; Actual Q3: 151; Actual Q4: 247.3597; Actual Q1: 436.674; Actual Q2: 98.44; Actual Q3: 2152.3; Actual Q4: 0.65 | 157.0899 | 157.0899 | 157.0899 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | Actual Q1: 153; Actual Q2: 77; Actual Q3: 125; Actual Q4: 247.3597; Actual Q1: 436.674; Actual Q2: 98.44; Actual Q3: 2152.3; Actual Q4: 0.65 | 150.5899 | 150.5899 | 150.5899 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | Actual Q1: 1.47; Actual Q2: 0.012; Actual Q3: 0.83; Actual Q4: 0.017469; Actual Q1: 0.38387; Actual Q2: 0.82; Actual Q3: 2.1; Actual Q4: 0.3 | 0.58237 | 0.58237 | 0.58237 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | Actual Q1: 1.47; Actual Q2: 0.012; Actual Q3: 0.78; Actual Q4: 0.017469; Actual Q1: 0.38387; Actual Q2: 0.82; Actual Q3: 2.1; Actual Q4: 0.3 | 0.56987 | 0.56987 | 0.56987 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 10000 | 10000 | 10000 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
| 4.b. | N/A | # of medical baseline customers impacted by PSPS | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
| 4.c. | N/A | # of customers notified prior to initiation of PSPS event | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 10000 | 10000 | 10000 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
| 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 | 0 | 0 | 0 | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | Actual Q1: 0; Actual Q2: 0; Actual Q3: 2559; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of customers
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | =1.c. / RFW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | =1.c. / HWW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | =1.c. / FPI OH circuit mile days in time period
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0; Actual Q1: 0; Actual Q2: 0; Actual Q3: 0; Actual Q4: 0 |  |  |  | Number of risk events

## Table 11
Utility | PacifiCorp | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2024-02-01 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actual | [15 empty] | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Grid Design, Operations, and Maintenance | Transmission Patrol inspections | AI-01 | Equipment failure | N/A | 2019 |  | N/A | [6 empty] | 196 |  |  |  | 77 |  |  |  | 34 | 34 |  |  | 144 | 144 |  |  | 93 |  |  |  | 93 |  |  |  | 93 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Distribution Patrol Inspections | AI-02 | Equipment failure | N/A | 2019 |  | N/A | [6 empty] | 323 |  |  |  | 181 |  |  |  | 247 | 247 |  |  | 289 | 289 |  |  | 308 |  |  |  | 308 |  |  |  | 308 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Transmission Detail Inspections | AI-03 | Equipment failure | N/A | 2019 |  | N/A | [6 empty] | 32 |  |  |  | 51 |  |  |  | 27 |  |  |  | 53 |  |  |  | 137 |  |  |  | 137 |  |  |  | 137 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Distribution Detail Inspections | AI-04 | Equipment failure | N/A | 2019 |  | N/A | [6 empty] | 181 |  |  |  | 211 |  |  |  | 168 |  |  |  | 204 |  |  |  | 203 |  |  |  | 203 |  |  |  | 203 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Transmission Intrusive Pole Inspections | AI-05 | [27 empty] | 171 |  |  |  | 171 |  |  |  | 171 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Distribution Intrusive Pole Inspections | AI-06 | Equipment failure | N/A | 2019 |  | N/A | [6 empty] | 81 |  |  |  | 109 |  |  |  | 149 |  |  |  | 125 |  |  |  | 90 |  |  |  | 90 |  |  |  | 90 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Enhanced IR Inspections in transmission lines | AI-07 | Equipment failure | N/A | 2019 | 2022 GRC | N/A | [6 empty] | 193 |  |  |  | 167 |  |  |  | 80 |  |  |  | 73 |  |  |  | 90 |  |  |  | 90 |  |  |  | 90 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Enhanced IR Inspections in distribution lines | AI-08 |  |  |  | 2022 GRC | N/A | [22 empty] | 125 |  |  |  | 130 | [5 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | LiDAR inspections of distribution electric lines and equipment | AI-09 | Equipment failure | N/A | 2019 | NA | NA | [6 empty] | 185 | [25 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | LiDAR inspections of transmission electric lines and equipment | AI-10 | Equipment failure | N/A | 2018 | 2022 GRC | NA | In Compliance | GO 95; GO 165 |  |  |  |  | 269 |  |  |  | 9 | [21 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Substation Inspections | AI-11 | Equipment failure | N/A | 2019 |  | N/A | [6 empty] | 180 |  |  |  | 163 |  |  |  | 163 |  |  |  | 188 |  |  |  | 179 |  |  |  | 179 |  |  |  | 179 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Quality assurance / quality control | AI-12 | Equipment failure | N/A | 2019 | 2022 GRC | N/A | [10 empty] | 36 |  |  |  | 50 |  |  |  | 37 |  |  |  | 36 |  |  |  | 36 |  |  |  | 36 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Community Outreach and Engagement | Public outreach and education awareness program | CO-01 | PSPS - for sectionalization, etc. |  | 2020 | 2022 GRC | NA | [10 empty] | 36 |  |  |  | 58 |  |  |  | 103 |  |  |  | 90 |  |  |  | 90 |  |  |  | 90
Community Outreach and Engagement | Engagement with access and functional needs populations | CO-02
Community Outreach and Engagement | Collaboration on local wildfire mitigation planning | CO-03
Community Outreach and Engagement | Best practice sharing with other utilities | CO-04
Overview of the Service Territory | Environmental compliance and permitting | EC-01
Emergency Preparedness | Emergency preparedness plan | EP-01 | [27 empty] | 50 |  |  |  | 50 |  |  |  | 50
Emergency Preparedness | External collaboration and coordination | EP-02 |  |  |  | NA | NA | [18 empty] | 31 | 31 |  |  | 30 |  |  |  | 30 |  |  |  | 30
Emergency Preparedness | Public emergency communication strategy | EP-03 | PSPS - for sectionalization, etc. | N/A |  | N/A | N/A | [18 empty] | 1 | 1 | 106 |  | 4
Emergency Preparedness | Preparedness and planning for service restoration | EP-04
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | EP-05 | N/A | N/A | 2021 | 2022 GRC | NA | [14 empty] | 149 |  |  |  | 356 |  |  |  | 150
Grid Design, Operations, and Maintenance | Line Rebuild - Covered conductor installation | GH-01 | Contact with vegetation | Wire-to-wire contact |  | 2022 GRC | NA | [8 empty] | 4325 | 4325 |  |  | 19922 | 19922 |  |  | 52500 | 52500 |  |  | 83000 | 83000 | 313 | 313 |  | 62000 | 313 | 313 | 62000 | 62000 | 313 | 313
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | GH-02 | Contact with vegetation |  | 2019 | 2022 GRC | NA | In Compliance | GO 95; GO 165 | [6 empty] | 245 | 245
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | GH-03
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GH-04 | Equipment failure | Wire-to-wire contact |  | 2022 GRC | NA |  |  |  |  | 2714 |  |  |  | 3947 | 3947 |  |  | 2062 | 2062 |  |  | 7183 |  |  |  | 10000 |  |  |  | 5000 |  |  |  | 2500
Grid Design, Operations, and Maintenance | Expulsion Fuse Replacement | GH-05 | Contact with vegetation |  |  | 2022 GRC | NA | [16 empty] | 2516 | 2516 |  |  | 10000 |  |  |  | 1000
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | GH-06
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | GH-07
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GH-08 | N/A | N/A |  | 2022 GRC | NA
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | GH-09 | Contact with vegetation | N/A |  | 2022 GRC | NA
Grid Design, Operations, and Maintenance | Traditional overhead hardening | GH-10
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots | GH-11
Grid Design, Operations, and Maintenance | Microgrids | GH-12
Grid Design, Operations, and Maintenance | Line removals (in HFTD) | GH-13
Grid Design, Operations, and Maintenance | Workforce Planning | GH-14
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk (Grid Ops): EFR and Fault Indicators | GO-01 | Contact with vegetation | N/A | 2019 | 2022 GRC | N/A | [12 empty] | 276 |  |  |  | 1067 |  |  |  | 150 |  | 50
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications (Grid Ops): Patrols | GO-02 | PSPS - for sectionalization, etc. | N/A |  | 2022 GRC | NA | [18 empty] | 581 |  |  |  | 600 |  |  |  | 600 |  |  |  | 600
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications (Grid Ops): Suppression | GO-03 |  |  | 2019 | N/A | N/A |  |  |  |  | 300
Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk (Grid Ops) | GO-04
Situational Awareness and Forecasting | Maintenance: Weather Station | MA-01 | [27 empty] | 245 |  |  |  | 285 |  |  |  | 325
Grid Design, Operations, and Maintenance | Maintenance:Equipment inspections, maintenance, and repair: Circuit breakers | MA-02 | Equipment failure | N/A | 2019 |  | N/A | [8 empty] | 52 |  | 96 |  | 233 |  | 47 |  | 14 |  | 96
Grid Design, Operations, and Maintenance | Maintenance: Equipment inspections, maintenance, and repair: Crossarm | MA-03 | Contact with vegetation | N/A |  |  | N/A | [8 empty] | 272 |  |  |  | 686 |  |  |  | 697
PSPS | Protocols on PSPS | PS-01 | PSPS - for sectionalization, etc. | N/A |  | 2022 GRC | NA | [10 empty] | 945 |  |  |  | 801 | 801 | [6 empty] | 850 |  |  |  | 800 |  |  |  | 750
Risk Methodology and Assessment | Risk and Risk Component Calculation | RA-01 | [27 empty] | 130 |  |  |  | 130 |  |  |  | 130
Risk Methodology and Assessment | Top Risk Areas within the HFRA | RA-02 | [27 empty] | 45
Risk Methodology and Assessment | Other Key Metrics | RA-03 | [15 empty] | 186 |  |  |  | 188 |  |  |  | 58 |  |  |  | 50 |  |  |  | 40 |  |  |  | 40
Risk Methodology and Assessment | Enterprise System for Risk Assessment | RA-04 | Equipment failure | N/A | 2019 | 2022 GRC | N/A | [20 empty] | 99 |  | 5 |  | 149 |  | 8 |  | 104 |  | 8
Situational Awareness and Forecasting | Environmental monitoring systems | SA-01 | Other contact with object | Equipment failure | 2019 | 2022 GRC | N/A |  |  |  |  | 128 |  |  |  | 170 |  | 44 |  | 190 |  | 36 |  | 800 |  | 222 |  | 240 |  |  |  | 160 |  |  |  | 120
Situational Awareness and Forecasting | Grid monitoring systems | SA-02 | Other contact with object | Equipment failure | 2019 | 2022 GRC | N/A | [12 empty] | 140 |  | 30 |  |  |  | 193 |  |  |  | 39 |  |  |  | 39
Situational Awareness and Forecasting | Smoke and Air Quality Sensors | SA-03 | [25 empty] | 64 |  | 6 |  | 13 |  | 2
Situational Awareness and Forecasting | Wildfire Detection Cameras | SA-04 | [25 empty] | 320 |  |  |  | 985 |  | 80 |  |  |  | 80
Situational Awareness and Forecasting | Weather Forecasting | SA-05 | [15 empty] | 19 | [7 empty] | 99 |  | 26 |  | 94 |  | 12 |  | 103 |  | 12 |  | 103
Situational Awareness and Forecasting | Fire potential index | SA-06 | Contact with vegetation | N/A |  | 2022 GRC | N/A | [16 empty] | 20 |  | 98 |  | 2 |  | 96 |  | 1 |  | 96 |  | 1 |  | 96
Vegetation Management and Inspection | Vegetation Inspections: Detailed Inspection – Distribution | VM-01 | Contact with vegetation | N/A | 2019 | 2022 GRC | NA | [6 empty] | 1637 | [7 empty] | 9121 |  |  |  | 6881 |  |  |  | 280 |  |  |  | 294 |  |  |  | 278
Vegetation Management and Inspection | Vegetation Inspections: Detailed Inspection - Transmission | VM-02 | Contact with vegetation |  | 2019 | 2022 GRC | NA | [6 empty] | 1151 | [7 empty] | 29 |  |  |  | 840 |  |  |  | 70 |  |  |  | 157 |  |  |  | 72
Vegetation Management and Inspection | Vegetation Inspections: Patrol Inspection - Distribution | VM-03 | Contact with vegetation | N/A |  | 2022 GRC | NA | [10 empty] | 299 |  |  |  | 246 |  |  |  | 374 |  |  |  | 375 | 375 |  |  | 316 | 316 |  |  | 336 | 336
Vegetation Management and Inspection | Vegetation Inspections: Patrol Inspection - Transmission | VM-04 | Contact with vegetation | N/A |  | 2022 GRC | NA | [14 empty] | 120 |  |  |  | 23 |  |  |  | 120 | 120 |  |  | 20 | 20 |  |  | 120 | 120
Vegetation Management and Inspection | Pole clearing | VM-05 | [11 empty] | 1770 | [15 empty] | 374 |  |  |  | 374 |  |  |  | 374
Vegetation Management and Inspection | Clearance - Distribution | VM-06 | Contact with vegetation | N/A | 2019 | 2022 GRC | NA | [6 empty] | 3821 |  |  |  | 6699 |  |  |  | 6639 |  |  |  | 8696 |  |  |  | 15915 |  |  |  | 15087 |  |  |  | 15241
Vegetation Management and Inspection | Clearance - Transmission | VM-07 | Contact with vegetation | N/A | 2019 | 2022 GRC | NA | [22 empty] | 1405 |  |  |  | 1904 |  |  |  | 1416
Vegetation Management and Inspection | Fall-in mitigation | VM-08 | [27 empty] | 500 | 500 |  |  | 30 | 30 |  |  | 20 | 20
Vegetation Management and Inspection | Remote sensing inspections of vegetation around distribution electric lines and equipment | VM-09 | Equipment failure | N/A | 2019 | 2022 GRC | NA | In Compliance | GO 95 | [12 empty] | 34 |  |  |  | 34
Vegetation Management and Inspection | Remote sensing inspections of vegetation around transmission electric lines and equipment | VM-10 | Equipment failure | N/A | 2019 | 2022 GRC | NA | In Compliance | GO 95; GO 165 | [12 empty] | 10 |  |  |  | 10
Vegetation Management and Inspection | Quality assurance / quality control | VM-11 | [27 empty] | 135 |  |  |  | 135 |  |  |  | 135
Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development | WP-01 | N/A | N/A | 2020 | 2022 GRC | NA | [10 empty] | 181 |  |  |  | 215 |  |  |  | 52 |  |  |  | 500 |  |  |  | 520 |  |  |  | 544
Wildfire Mitigation Strategy Development | Identifying and Evaluating Mitigation Initiatives | WP-02 | N/A | N/A | 2021 |  | NA | [22 empty] | 100 |  |  |  | 100 |  |  |  | 100

## Table 12
Utility | PacifiCorp | Notes:
Table No. | 12
Date Modified | 2024-02-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | Method of Verification | Comments
Grid Design, Operations, and Maintenance | Line Rebuild - Covered conductor installation | GH-01 | Quantitative | line miles | 44 | 104 | 130 | 20 | 50 | 80 | 80 | Quantitative
Grid Design, Operations, and Maintenance | Distribution Pole Replacement | GH-02 | Quantitative | poles | 880 | 2040 | 2600 | 400 | 1000 | 1600 | 1600 | Quantitative
Grid Design, Operations, and Maintenance | Transmission Pole Replacement | GH-03 | Quantitative | poles | 75 | 150 | 260 | 40 | 100 | 160 | 160 | Quantitative
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GH-04 | Quantitative | devices | 22 | 36 | 40 | 5 | 15 | 20 | 10 | Quantitative
Grid Design, Operations, and Maintenance | Expulsion fuse replacement | GH-05 | Quantitative | Fuse locations | 1800 | 4100 | 5000 | 100 | 250 | 500 | 0 | Quantitative
Situational Awareness and Forecasting | Environmental monitoring systems | SA-01 | Quantitative | Weather station unit | 8 | 11 | 12 | 2 | 6 | 8 | 6 | Quantitative
Grid Design, Operations, and Maintenance | Transmission Patrol inspections | AI-01 | Quantitative | Inspection Counts | 5726.538 | 9343.0152 | 11754 | 5862.9537 | 9565.5815 | 12034 | 12030 | Quantitative
Grid Design, Operations, and Maintenance | Distribution Patrol Inspections | AI-02 | Quantitative | Inspection Counts | 14430.6216 | 36056.6487 | 50474 | 13230.4047 | 33057.7619 | 46276 | 50485 | Quantitative
Grid Design, Operations, and Maintenance | Transmission Detail Inspections | AI-03 | Quantitative | Inspection Counts | 453.3245 | 1810.3298 | 2715 | 272.3287 | 1087.5315 | 1631 | 540 | Quantitative
Grid Design, Operations, and Maintenance | Distribution Detail Inspections | AI-04 | Quantitative | Inspection Counts | 3259.8655 | 6501.1462 | 8662 | 3263.6289 | 6508.6516 | 8672 | 10135 | Quantitative
Grid Design, Operations, and Maintenance | Transmission Intrusive Pole Inspections | AI-05 | Quantitative | Inspection Counts | 0 | 561 | 935 | 0 | 469.8 | 783 | 960 | Quantitative
Grid Design, Operations, and Maintenance | Distribution Intrusive Pole Inspections | AI-06 | Quantitative | Inspection Counts | 298.4202 | 1561.7681 | 2404 | 313.1922 | 1639.0769 | 2523 | 3173 | Quantitative
Grid Design, Operations, and Maintenance | Enhanced (Infrared) Inspections in Transmission Lines | AI-07 | Quantitative | line miles | 125 | 131 | 701 | 125 | 131 | 701 | 701 | Quantitative
Grid Design, Operations, and Maintenance | Enhanced (Infrared) Inspections in Distribution Lines | AI-08 | Quantitative | line miles | 0 | 814 | 814 | 0 | 814 | 814 | TBD | Quantitative
Grid Design, Operations, and Maintenance | Substation Inspections | AI-11 | Quantitative | Inspection Counts | 225 | 393 | 451 |  |  |  |  | Quantitative
Grid Design, Operations, and Maintenance | QA/QC (Asset Inspections) | IN-14 | Quantitative | Inspection Counts | 534 | 734 | 841 |  |  |  |  | Quantitative
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk | GO-01 | Quantitative | devices |  |  | TBD |  |  | TBD | TBD
Risk Methodology and Assessment | Risk and Risk Components Calculation | RA-01 | Qualitative |  | Delivery of RAIL and RAVE models (WRRM components) | Ignition risk calculation completed and validated | Circuit Ignition Risk Scores Calculated |  | Update and refine model as needed | Circuit Ignition Risk Scores Calculated | Circuit Ignition Risk Scores Calculated | Qualitative: Table showing Ignition Risk scores Changes to model: Notes and slides from Committee showing recommendations and approvals
Risk Methodology and Assessment | Top Risk Areas within the HFRA | RA-02 | Qualitative |  | Requirements and scope of work for third-party reviewer completed Analysis process developed | Third-party reviewer on boarded Analysis completed | Testing of proposed changes completed and validated by 3rd party reviewer |  |  | Subject to regulatory approval, new maps used for program planning and execution | Maps used for program planning and execution | Qualitative: Completed report from 3rd party reviewer
Risk Methodology and Assessment | Other Key Metrics | RA-03 | Qualitative |  | Calculation and model inputs validated | RSE Model Implemented | RSE Capabilities used for annual planning | RSE calculated for possible mitigations | Update and refine model as needed | RSE calculated for possible mitigations | RSE calculated for possible mitigations | Qualitative: Approval of mitigation calculations RSE of proposed mitigations
Risk Methodology and Assessment | Public Safety Power Shutoff (PSPS) RIsk Assessment Solution |  | Qualitative |  | Requirements complete and solution selected | Development Complete | Testing underway | PSPS risk calculation completed and validated | Update and refine model as needed | PSPS Risk Recalculation | PSPS Risk Recalculation | Qualitative: Table showing Ignition Risk scores Changes to model: Notes and slides from Committee showing recommendations and approvals
Emergency Preparedness | Messaging | EP-03 | Qualitative | N/A | Storyboarding and wireframing complete; ability to view critical facility data in development environment available | Prototype delivered; event and event area creation functionality delivered | Full portal functionality and QA testing delivered; ability to set up notification preferences by event area available | N/A; project complete | N/A; project complete | N/A; project complete | N/A; project complete | Screenshots, portal documentation
Situational Awareness and Forecasting | Ignition Detection Systems | SA-04 | Quantitative | Units | 0 | 0 | 2 | 0 | 0 | 6 | 0 | Number of units installed
Situational Awareness and Forecasting | Weather Forecasting | SA-09 | Qualitative | N/A | Addition of forecast variables completed to include modified HDW index visualization. |  | Self-organizing map forecast system implemented; 30-year weather data reanalysis fully integrated into operational and planning processes |  |  | WRF ensemble implementation complete | Implementation of machine learning models to bias correct WRF forecasts complete | Project documentation
Vegetation Management | Detailed Inspection – Distribution | VM-01 | Quantitative | Line miles | 450 | 700 | 829 | 524 | 786 | 874 | 826 | Inspection records, billing, project closeout documentation, and field verification
Vegetation Management | Detailed Inspection - Transmission | VM-02 | Quantitative | Line miles | 158 | 211 | 264 | 361 | 482 | 602 | 270 | Inspection records, billing, project closeout documentation, and field verification
Vegetation Management | Patrol Inspection - Distribution | VM-03 | Quantitative | Line miles | 820 | 1027 | 1027 | 578 | 865 | 865 | 922 | Inspection records, billing, project closeout documentation, and field verification
Vegetation Management | Patrol Inspection - Transmission | VM-04 | Quantitative | Line miles | 296 | 329 | 329 | 99 | 99 | 99 | 329 | Inspection records, billing, project closeout documentation, and field verification
Situational Awareness and Forecasting | Smoke and Air Quality Sensors | SA-03 | Quantitative | Unit | 20 | 20 | 20 | 0 | 0 | 0 | 0 | Number of units installed
Emergency Preparedness | External Collaboration and Coordination | EP-02 | Qualitative | N/A | Conduct: 1 TableTop eXercise (TTX) | 0 | Conduct: 1 Functional Exercise (FE) 1 workshop | Conduct: 1 TableTop eXercise (TTX) | 0 | Conduct: 1 Functional Exercise (FE) 1 workshop | Conduct: 1 TableTop eXercise (TTX) 1 Functional Exercise (FE) 1 workshop | After Action Report and Improvement Plan (AAR/IP); Workshop presentation materials
Community Outreach and Engagement | Public Outreach and Education Awareness Program | CO-01 | Qualitative | N/A | Complete annual pre-fire season wildfire awareness survey | 0 | Complete annual post-fire season wildfire awareness survey | Complete annual pre-fire season wildfire awareness survey | 0 | Complete annual post-fire season wildfire awareness survey | Complete annual pre and post-wildfire season awareness surveys | Survey results
Community Outreach and Engagement | Public Outreach and Education Awareness Program | CO-03 | Qualitative | N/A | Run pre-fire season paid and social media (Facebook, Twitter, etc.) ads. | Run fire season paid and social media (Facebook, Twitter, etc.) ads. | Run post-fire season paid and social media (Facebook, Twitter, etc.) ads. | Run pre-fire season paid and social media (Facebook, Twitter, etc.) ads. | Run fire season paid and social media (Facebook, Twitter, etc.) ads. | Run post-fire season paid and social media (Facebook, Twitter, etc.) ads. | Complete annual paid and social media ad campaign cycle. | Records of produced outreach materials and invoices.
Community Outreach and Engagement | Engagement with Access and Functional Needs Populations | CO-02 | Qualitative | N/A | 0 | 0 | Publish medical certificate in 1 additional language | 0 | 0 | Publish medical certificate in 1 additional language | Publish medical certificate in 1 additional language | Review of website and back end logs
Situational Awareness and Forecasting | Distribution Fault Anticipation (DFA) Sensor Pilot | SA-02 | Quantitative | Units | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Number of units installed

## Table 13
Utility | PacifiCorp |  | Note: Provide a listing (as rows) of all work orders / notifications for corrective work on electric circuits that were open as of the end of the quarter.
Table No. | 13
Date Modified | 2024-02-01
Table 13: Open work orders / notifications
a. Work order number | b. Equipment Type | c. HFTD Tier | d. Line type | e. Date the work order was originally opened | f. Due date of the original work order | g. GO 95 rule 18 priority level of the original work order | h. Optional utility-specific repair priority | i. Date(s) the work order was reinspected or modified (if applicable) | j. Due date of the work order after it was reinspected or modified (if applicable) | k. Priority of the work order after it was reinspected or modified (if applicable) | l. Reason for reinspection (if applicable)
541116418-77418-DETAIL-04_17_2019-SVCWIND-1^06142012.0122002 | OTHER | CA-NON-TIER | Distribution | 2019-04-17 | 2024-03-17 | 2
370227409-30020-ADMIN-04_01_2020-POLEDERP-1^06142012.0124305 | POLE | CA-NON-TIER | Distribution | 2020-04-01 | 2023-04-01 | 2
341576079-31180-DETAIL-04_22_2019-SVCROAD-1^06142012.0126105 | OTHER | CA-NON-TIER | Distribution | 2019-04-22 | 2024-03-22 | 2
549448374-36341-DETAIL-04_12_2022-SVCROAD-1^06142012.0130400 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
357909214-35700-DETAIL-04_12_2022-GO95MLD-1^06142012.0130402 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
980401454-32503-DETAIL-04_12_2022-GO95BLTC-1^06142012.0130405 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
406957344-41460-DETAIL-04_12_2022-GO95MLD-1^06142012.0130413 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
512265164-61291-DETAIL-04_12_2022-SVCENTCO-1^06142012.0130414 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
3373803-73029-DETAIL-04_12_2022-SVCWIND-2^06142012.0130505 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
673117701-54529-DETAIL-04_12_2022-GO95MLD-1^06142012.0130506 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
610733440-12621-DETAIL-04_12_2022-SVCWIND-1^06142012.0130507 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
650638364-40829-DETAIL-04_11_2022-SVCENTCO-1^06142012.0130811 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
650638364-40829-DETAIL-04_11_2022-SVCWIND-1^06142012.0130811 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
822261591-66929-DETAIL-04_11_2022-GO95MLD-1^06142012.0130812 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
822261591-66929-DETAIL-04_11_2022-XARMSPCR-1^06142012.0130812 | CROSSARM | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
639588311-23351-DETAIL-04_11_2022-CLRTOUCH-1^06142012.0130900 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
17387070-87329-DETAIL-04_11_2022-GO95MLD-1^06142012.0130904 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
799986794-99682-DETAIL-04_12_2022-GO95MLD-1^06142012.0131302 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
906740354-11252-DETAIL-04_12_2022-GO95HV-1^06142012.0131402 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
46151364-52840-DETAIL-04_12_2022-GO95HV-1^06142012.0131404 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
46151364-52840-DETAIL-04_12_2022-GO95MLD-1^06142012.0131404 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
779988084-15632-DETAIL-04_12_2022-GO95MLD-1^06142012.0131405 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
36108894-73229-AUDIT-05_12_2022-CLRTOPOL-1^06142012.0131500 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
14252771-10429-DETAIL-04_19_2022-GO95MLD-1^06142012.0132806 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
116330241-58129-DETAIL-04_18_2022-GO95HV-1^06142012.0132808 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2027-04-18 | 3
248879780-87129-DETAIL-04_19_2022-GO95MLD-1^06142012.0132809 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
248879780-87129-DETAIL-04_19_2022-GO95TCH-1^06142012.0132809 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
515003451-24329-DETAIL-04_18_2022-GO95MLD-1^06142012.0132813 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
440017730-84329-DETAIL-04_19_2022-GUYHINS-1^06142012.0132816 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
928491721-93129-DETAIL-04_19_2022-GO95HV-1^06142012.0132901 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
928491721-93129-DETAIL-04_19_2022-GUYHINS-1^06142012.0132901 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
166314665-83429-DETAIL-04_19_2022-GO95MLD-1^06142012.0132902 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
166314665-83429-DETAIL-04_19_2022-SVCRUBLG-1^06142012.0132902 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
616622914-27129-DETAIL-04_19_2022-GO95MLD-1^06142012.0132906 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
593948164-64129-DETAIL-04_19_2022-SVCENTCO-1^06142012.0131707 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
864977424-10929-DETAIL-04_13_2022-GO95MLD-1^06142012.0133610 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
864977424-10929-DETAIL-04_13_2022-GUYHINS-1^06142012.0133610 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
551386210-34429-DETAIL-04_18_2022-CLMBHAZ-1^06142012.0133701 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
110515654-69150-DETAIL-04_18_2022-GO95TCH-1^06142012.0133704 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
297440894-6740-DETAIL-04_18_2022-GO95HV-1^06142012.0133705 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2027-04-18 | 3
297440894-6740-DETAIL-04_18_2022-SVCWIND-1^06142012.0133705 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
877083603-12252-DETAIL-04_18_2022-GO95MLD-1^06142012.0133707 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
641194583-58929-DETAIL-04_18_2022-GO95MLD-1^06142012.0133708 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
664472790-24221-DETAIL-04_18_2022-GUYHINS-1^06142012.0133710 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
596504911-43301-DETAIL-04_18_2022-GO95HV-1^06142012.0133804 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2027-04-18 | 3
854566254-27372-DETAIL-04_18_2022-GO95HV-1^06142012.0133805 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2027-04-18 | 3
660209151-41129-DETAIL-04_18_2022-GO95MLD-1^06142012.0133902 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
648400743-57829-DETAIL-03_28_2016-SVCWIND-1^06142012.0148701 | OTHER | CA-NON-TIER | Distribution | 2016-03-28 | 2021-02-28 | 2
350940014-6290-DETAIL-04_14_2022-GO95MLD-1^06142012.0134502 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
695425361-20901-AUDIT-05_03_2022-SVCENTBK-1^06142012.0134601 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
792312311-32529-DETAIL-04_18_2022-GO95MLD-1^06142012.0134807 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
799330301-96782-DETAIL-04_19_2022-ANCHIDLE-1^06142012.0134904 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
298428773-36040-DETAIL-04_21_2022-GO95HV-1^06142012.0135000 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
871044243-7722-DETAIL-04_14_2022-ANCHIDLE-1^06142012.0135401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
862592163-16302-DETAIL-04_14_2022-GO95CL10-1^06142012.0135502 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
862592163-16302-DETAIL-04_14_2022-SVCROAD-1^06142012.0135502 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
339240023-86780-DETAIL-04_14_2022-GO95MLD-1^06142012.0135503 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
339240023-86780-DETAIL-04_14_2022-SVCROAD-1^06142012.0135503 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
650176953-95081-DETAIL-04_21_2022-GO95HV-1^06142012.0245802 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
768231113-14302-DETAIL-04_21_2022-ABNDEQPM-1^06142012.0246802 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
59128218-93929-DETAIL-11_03_2021-GO95TCH-1^06142012.0147907 | OTHER | CA-NON-TIER | Distribution | 2021-11-03 | 2024-11-03 | 2
228706349-47660-DETAIL-03_14_2016-SVCWIND-1^06142012.0148908 | OTHER | CA-NON-TIER | Distribution | 2016-03-14 | 2021-02-14 | 2
594189163-62201-DETAIL-04_21_2022-GO95HV-1^06142012.0245901 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
290665533-50029-DETAIL-04_21_2022-ABNDEQPM-1^06142012.0247300 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
541536333-65829-DETAIL-04_21_2022-GO95HV-1^06142012.0247301 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
78694963-85110-DETAIL-04_21_2022-GO95HV-1^06142012.0247601 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
290665533-50029-DETAIL-04_21_2022-GO95HV-1^06142012.0247300 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
541536333-65829-DETAIL-04_21_2022-GO95MLD-1^06142012.0247301 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
513625303-99591-DETAIL-04_14_2022-GO95MLD-1^06142012.0247900 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
408979001-71101-DETAIL-03_27_2023-GO95HV-1^06142016.0052700 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
857782501-26501-DETAIL-03_28_2023-GO95BLTC-1^06142016.0052901 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
857782501-26501-DETAIL-03_28_2023-GO95MLD-1^06142016.0052901 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
798595741-46514-DETAIL-03_28_2023-GO95MLD-1^06142016.0053300 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
798595741-46514-DETAIL-03_28_2023-GRDRODHI-1^06142016.0053300 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
25844841-66841-DETAIL-03_27_2023-GO95HV-1^06142016.0053501 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
48849061-13161-DETAIL-03_30_2023-GO95MLD-1^06142016.0054008 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
48849061-13161-DETAIL-03_30_2023-SVCENTCO-1^06142016.0054008 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
595017381-70684-DETAIL-03_28_2023-GO95HV-1^06142016.0054200 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
810965519-98519-DETAIL-03_30_2023-GO95MLD-1^06142016.0054300 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
810965519-98519-DETAIL-03_30_2023-GO95TCH-1^06142016.0054300 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
763873701-26701-DETAIL-03_30_2023-GO95MLD-1^06142016.0055005 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
106095974-8084-DETAIL-03_29_2023-GO95MLD-1^06142016.0084400 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
15851624-24624-DETAIL-03_28_2023-GO95MLD-1^06142016.0084701 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
564106824-58824-DETAIL-03_29_2023-GO95HV-1^06142016.0084706 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
955890924-13924-DETAIL-03_29_2023-GO95HV-1^06142016.0084707 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
955890924-13924-DETAIL-03_29_2023-GO95MLD-1^06142016.0084707 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
797715924-17924-DETAIL-02_13_2018-SVCROAD-1^06142016.0084708 | OTHER | CA-NON-TIER | Distribution | 2018-02-13 | 2023-01-13 | 2
682349924-11024-DETAIL-03_29_2023-GO95MLD-1^06142016.0084709 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
560580491-5191-DETAIL-03_27_2023-ABNDEQPM-1^06142016.0082903 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
560580491-5191-DETAIL-03_27_2023-GO95MLD-1^06142016.0082903 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
826205234-27234-DETAIL-03_29_2023-GUYHINS-1^06142016.0083400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
686933654-94654-DETAIL-03_28_2023-GO95MLD-1^06142016.0083807 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
408012504-92473-DETAIL-03_29_2023-SVCROAD-1^06142016.0084602 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
187865670-22629-DETAIL-04_27_2022-GO95HV-1^06143012.0240800 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
926342090-18329-ADMIN-10_24_2022-CUTOUTAR-1^06143012.0240801 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-10-24 | 2025-10-24 | 2
135593701-53629-DETAIL-04_27_2022-GRDRODHI-1^06143012.0241100 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
101157939-62529-DETAIL-04_26_2022-GO95HV-1^06143012.0241301 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
818964091-63329-DETAIL-04_27_2022-GO95MLD-1^06143012.0241800 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
510316851-61329-DETAIL-04_27_2022-GRDRODHI-1^06143012.0241802 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
814144219-12529-DETAIL-04_27_2022-GO95MLD-1^06143012.0242300 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
134770851-18629-DETAIL-04_27_2022-GO95HV-1^06143012.0243100 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
112319249-52729-DETAIL-04_27_2022-GO95HV-1^06143012.0243300 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
744707784-7629-DETAIL-04_26_2022-GO95MLD-1^06143012.0239000 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
744707784-7629-DETAIL-04_26_2022-GUYSLACK-1^06143012.0239000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
744707784-7629-ADMIN-10_24_2022-ANCPUCO-1^06143012.0239000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-10-24 | 2025-10-24 | 2
792910294-27629-DETAIL-04_26_2022-GO95MLD-1^06143012.0239001 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
959492898-83629-DETAIL-04_28_2022-GO95HV-1^06143012.0246401 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
376406299-81729-DETAIL-04_28_2022-GO95MLD-1^06143012.0246602 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
33847599-74629-DETAIL-04_28_2022-GO95MLD-1^06143012.0244400 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
91583311-28629-DETAIL-05_02_2022-GO95MLD-1^06143012.0244800 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
33951480-42480-DETAIL-05_02_2022-GO95MLD-1^06143012.0244900 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
520832371-78329-DETAIL-05_02_2022-GO95MLD-1^06143012.0245200 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
952283568-72129-DETAIL-04_28_2022-GO95MLD-1^06143012.0245300 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
613707878-99429-DETAIL-04_28_2022-GO95MLD-1^06143012.0245301 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
311997529-86429-DETAIL-04_28_2022-GO95MLD-1^06143012.0246500 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
232289549-1729-DETAIL-04_28_2022-GO95MLD-1^06143012.0246701 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
59538079-62729-DETAIL-05_02_2022-GO95MLD-1^06143012.0246801 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
546861589-19629-DETAIL-05_02_2022-GO95HV-1^06143012.0246900 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
410983203-36529-DETAIL-04_27_2022-GO95MLD-1^06143012.0254803 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
410983203-36529-DETAIL-04_27_2022-GO95MLD-2^06143012.0254803 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
290933274-59529-DETAIL-04_28_2022-GO95HV-1^06143012.0254900 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
297091423-31529-DETAIL-04_25_2022-GO95MLD-1^06143012.0255000 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
52308754-37429-DETAIL-04_25_2022-GO95MLD-1^06143012.0255003 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
949907743-20529-DETAIL-04_25_2022-GUYHINS-1^06143012.0255203 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
673174673-35529-DETAIL-04_25_2022-GO95HV-1^06143012.0255300 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
382792873-48329-DETAIL-04_27_2022-GO95MLD-1^06143012.0255600 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
331848364-24129-DETAIL-05_02_2022-GO95MLD-1^06143012.0255800 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
344175454-58529-DETAIL-04_28_2022-GO95MLD-1^06143012.0255801 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
98534414-99129-DETAIL-04_28_2022-GO95MLD-1^06143012.0255802 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
962287694-81829-DETAIL-04_25_2022-GO95HV-1^06143012.0256001 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
819689623-27629-DETAIL-04_20_2022-GO95MLD-1^06143012.0365200 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
698064963-17529-DETAIL-04_20_2022-GO95HV-1^06143012.0365400 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
698064963-17529-DETAIL-04_20_2022-GO95MLD-1^06143012.0365400 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
347436773-45729-DETAIL-04_21_2022-GO95CL10-1^06143012.0365500 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
347436773-45729-DETAIL-04_21_2022-GO95MLD-1^06143012.0365500 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
440361903-38729-DETAIL-04_21_2022-GO95MLD-1^06143012.0365702 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
377060493-18729-DETAIL-04_21_2022-GO95MLD-1^06143012.0365802 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
707063223-1829-DETAIL-04_25_2022-GO95MLD-1^06143012.0365900 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
864096713-70829-DETAIL-04_25_2022-GO95MLD-1^06143012.0365901 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
602070504-96429-DETAIL-04_20_2022-GO95MLD-1^06143012.0362101 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
602070504-96429-DETAIL-04_20_2022-GRDRODHI-1^06143012.0362101 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
659989953-66229-DETAIL-04_20_2022-GO95TCH-1^06143012.0362501 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
252272204-51629-DETAIL-05_04_2022-GO95MLD-1^06143013.0192700 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
252272204-51629-DETAIL-05_04_2022-GRDRODHI-1^06143013.0192700 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
20404931-35931-DETAIL-04_04_2023-GO95HV-1^06143013.0237001 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
315231874-6729-DETAIL-05_04_2022-GO95HV-1^06143013.0191902 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
50930654-9029-DETAIL-05_02_2022-GO95MLD-1^06143013.0192401 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
747483804-39529-DETAIL-05_04_2022-GO95MLD-1^06143013.0192600 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
252272204-51629-DETAIL-05_04_2022-GO95HV-1^06143013.0192700 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
839059494-23222-DETAIL-02_14_2018-SVCWIND-1^06143013.0238601 | OTHER | CA-TIER-2 | Distribution | 2018-02-14 | 2023-01-14 | 2
131164484-15429-DETAIL-04_04_2023-GUYHINS-1^06143013.0239001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-04 | 2026-04-04 | 2
871862474-2429-DETAIL-04_04_2023-GO95MLD-1^06143013.0241001 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2026-04-04 | 2
871862474-2429-ADMIN-04_21_2023-GO95TCH-1^06143013.0241001 | OTHER | CA-TIER-2 | Distribution | 2023-04-21 | 2026-04-21 | 2
290193326-90426-DETAIL-04_03_2023-CLRTOUCH-1^06143013.0333701 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
563657981-67861-DTLSB-03_29_2022-GO95HV-1^06144006.0105901 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
220183391-42616-DTLSB-03_29_2022-GO95HV-1^06144006.0107902 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
388254953-40740-DTLSB-03_28_2022-GO95HV-1^06144006.0153100 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
388254953-40740-DTLSB-03_28_2022-XARMSPCR-1^06144006.0153100 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
572781111-20271-DTLSB-03_29_2022-GO95HV-1^06144006.0105400 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
572781111-20271-DTLSB-03_29_2022-POLETOP-1^06144006.0105400 | POLE | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
528048551-29611-DTLSB-03_29_2022-GO95HV-1^06144006.0105900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
889363851-32582-DTLSB-03_29_2022-GO95HV-1^06144006.0106901 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
220183391-42616-DTLSB-03_29_2022-INSULDMG-1^06144006.0107902 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
843959871-48132-DTLSB-03_29_2022-GO95HV-1^06144006.0109900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
540585861-7731-DTLSB-03_29_2022-XARMSPCR-1^06144006.0109901 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
374565663-58620-DTLSB-03_30_2022-XARMSPCR-1^06144006.0197900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
995903053-17343-DTLSB-03_30_2022-XARMSPCR-1^06144006.0198900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
310299003-44450-DTLSB-03_31_2022-GO95HV-1^06144006.0209000 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
427229503-17580-DTLSB-03_30_2022-GO95HV-1^06144006.0209800 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
339471823-87880-DTLSB-03_31_2022-GO95HV-1^06144006.0210000 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
981553763-81703-DTLSB-03_29_2022-GO95HV-1^06144006.0210401 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
831565383-40692-DTLSB-03_30_2022-GO95TCH-1^06144006.0191601 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
906244163-50679-DTLSB-03_30_2022-CONDFRAY-1^06144006.0192601 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
906244163-50679-DTLSB-03_30_2022-GO95HV-1^06144006.0192601 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
27475285-69285-DTLSB-03_30_2022-GO95HV-1^06144006.0192800 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
149450963-71290-DTLSB-03_30_2022-GO95HV-1^06144006.0193500 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
585830153-43191-DTLSB-03_30_2022-GO95HV-1^06144006.0193602 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
141543161-22089-DETAIL-01_31_2023-COPLLEAN-1^06146002.0101200 | POLE | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
824341663-92972-DTLSB-03_28_2022-GO95HV-1^06144006.0222901 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
250827333-75980-DTLSB-03_28_2022-POLETOP-1^06144006.0224700 | POLE | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
220709613-34360-DTLSB-03_28_2022-GO95HV-1^06144006.0225701 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
376850686-26120-DETAIL-01_25_2017-POLETOP-1^06144006.0230500 | POLE | CA-NON-TIER | Distribution | 2017-01-25 | 2021-12-25 | 2
383239406-79630-DTLSB-03_24_2022-GUYSLACK-1^06144006.0233300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-24 | 2025-03-24 | 2
383239406-79630-DTLSB-03_24_2022-XARMSPCR-1^06144006.0233300 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-24 | 2025-03-24 | 2
399386656-31999-DTLSB-03_24_2022-GO95HV-1^06144006.0235200 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
88147406-90520-DTLSB-03_24_2022-GO95HV-1^06144006.0241000 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
221722118-78060-DTLSB-03_24_2022-GO95HV-1^06144006.0253900 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
890656013-15392-DETAIL-02_09_2023-GO95MLD-1^06146004.0078001 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
632841503-69351-DETAIL-02_09_2023-GO95MLD-1^06146004.0078101 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
878389523-83952-DETAIL-02_08_2023-GO95MLD-1^06146004.0080001 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
79525823-2710-DETAIL-02_08_2023-GO95MLD-1^06146004.0081000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
944017423-72613-DETAIL-02_08_2023-GO95MLD-1^06146004.0081001 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
481388533-17051-DETAIL-02_08_2023-GO95MLD-1^06146004.0082000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
48878833-48450-DETAIL-02_09_2023-GO95MLD-1^06146004.0083000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
424907943-50080-DETAIL-02_09_2023-GO95MLD-1^06146004.0085002 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
718231143-62471-DETAIL-02_09_2023-GO95MLD-1^06146004.0086000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
718231143-62471-DETAIL-02_09_2023-GO95MLD-2^06146004.0086000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
344253653-20990-DETAIL-02_09_2023-GO95MLD-1^06146004.0087000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
275728353-63410-DETAIL-02_09_2023-GO95MLD-1^06146004.0088000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
199943149-70640-DETAIL-02_10_2022-GO95MLD-1^06146005.0010701 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
431241910-32479-DETAIL-02_15_2022-GO95HV-1^06146005.0024000 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
816163600-2479-DETAIL-02_16_2022-GO95HV-1^06146005.0024001 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
42003100-42579-DETAIL-02_16_2022-ABNDEQPM-1^06146005.0025000 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
148192799-76590-DETAIL-02_16_2022-GO95HV-1^06146005.0025300 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
443503489-73099-DETAIL-02_10_2022-GO95HV-1^06146005.0025900 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
20946887-3740-DETAIL-02_10_2022-INSULDMG-1^06146005.0027900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
615543477-2331-DETAIL-02_10_2022-GO95MLD-1^06146005.0029901 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
264467969-41809-DETAIL-02_14_2022-GO95HV-1^06146005.0030501 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
273629088-81479-DETAIL-02_14_2022-GUYSLACK-1^06146005.0032200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
78657887-40987-DETAIL-02_14_2022-GO95HV-1^06146005.0035602 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
414853228-87279-DETAIL-02_14_2022-GO95HV-1^06146005.0036200 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
518914939-10109-DETAIL-02_17_2022-GO95MLD-1^06146005.0110002 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
47099819-9219-DETAIL-02_17_2022-XARMBRAC-1^06146005.0110003 | CROSSARM | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
296321449-58879-DETAIL-02_17_2022-GO95MLD-1^06146005.0110503 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
296321449-58879-DETAIL-02_17_2022-GO95TCH-1^06146005.0110503 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
129604289-23319-DETAIL-02_17_2022-SVCRUBLG-1^06146005.0112000 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
894078069-7879-DETAIL-02_17_2022-GO95MLD-1^06146005.0113500 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
774793649-78722-DETAIL-02_17_2022-GO95MLD-1^06146005.0118000 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
751135419-92061-DETAIL-03_03_2022-GO95HV-1^06146005.0120100 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
620523579-12431-DETAIL-03_03_2022-GO95HV-1^06146005.0120800 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
190822119-55479-DETAIL-03_03_2022-GO95MLD-1^06146005.0121000 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
177342000-20020-DETAIL-03_03_2022-ABNDEQPM-1^06146005.0122000 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
177342000-20020-DETAIL-03_03_2022-GO95MLD-1^06146005.0122000 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
142907174-22880-DTLSB-03_22_2022-GO95HV-1^06146005.0134001 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
137782853-58380-DTLSB-03_22_2022-GO95HV-1^06146005.0136102 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
226909423-76879-DTLSB-03_23_2022-CONDFRAY-1^06146005.0137100 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
22220644-67950-DTLSB-03_22_2022-GO95MLD-1^06146005.0137202 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
326198103-67070-DTLSB-03_23_2022-ABNDEQPM-1^06146005.0137300 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
326198103-67070-DTLSB-03_23_2022-GO95HV-1^06146005.0137300 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
326198103-67070-DTLSB-03_23_2022-GO95MLD-1^06146005.0137300 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
101091593-69240-DTLSB-03_23_2022-GUYHINS-1^06146005.0137401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
101091593-69240-DTLSB-03_23_2022-SVCROAD-1^06146005.0137401 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
37190539-72809-DETAIL-02_23_2022-GO95MLD-1^06146005.0099900 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
37190539-72809-DETAIL-02_23_2022-GO95TCH-1^06146005.0099900 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
794534298-81309-DETAIL-02_23_2022-INSULDMG-1^06146005.0101601 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
702831754-36321-DETAIL-02_21_2022-GO95HV-1^06146005.0170501 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
145278264-48980-DETAIL-02_21_2022-GO95MLD-1^06146005.0170700 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
524345575-39511-DETAIL-02_28_2022-GO95HV-1^06146005.0179201 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
524427016-69016-DETAIL-02_23_2022-GO95TCH-1^06146005.0203701 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
420520065-99379-DETAIL-02_23_2022-GO95HV-1^06146005.0203801 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
420520065-99379-DETAIL-02_23_2022-GRDRODHI-1^06146005.0203801 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
775118864-47422-DETAIL-02_28_2022-GO95HV-1^06146005.0205600 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
775118864-47422-DETAIL-02_28_2022-GO95MLD-1^06146005.0205600 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
916684384-69302-DETAIL-02_21_2022-ANCHIDLE-1^06146005.0205601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
50470485-72650-DETAIL-02_21_2022-GO95HV-1^06146005.0206100 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
192908505-73979-DETAIL-02_21_2022-GO95HV-1^06146005.0206303 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
387589085-40440-DETAIL-02_21_2022-GO95HV-1^06146005.0206402 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
742649665-7731-DETAIL-02_21_2022-INSULDMG-1^06146005.0203800 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
420520065-99379-DETAIL-02_23_2022-GO95MLD-1^06146005.0203801 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
166110484-77810-DETAIL-02_28_2022-CLRTOUCH-1^06146005.0206700 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
53766225-550-DETAIL-02_21_2022-GO95STUB-1^06146005.0207001 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
774510331-52331-DETAIL-02_22_2022-GUYHINS-1^06146005.0212401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
623939131-41231-DETAIL-02_22_2022-GO95HV-1^06146005.0213401 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2027-02-22 | 3
727311333-22991-DETAIL-02_24_2022-GO95HV-1^06146005.0214401 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
165330313-81510-DETAIL-02_24_2022-GUYSLACK-1^06146005.0217700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
49524724-16950-DETAIL-02_24_2022-GO95MLD-1^06146005.0218700 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
782186214-35342-DETAIL-02_24_2022-GO95HV-1^06146005.0218701 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
77503368-93368-DTLSB-03_16_2022-GO95HV-1^06146005.0220401 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2027-03-16 | 3
280412494-41594-DTLSB-03_17_2022-GO95BLTC-1^06146005.0221700 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
347123694-28694-DTLSB-03_17_2022-GO95MLD-1^06146005.0221701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
260830764-89500-DETAIL-02_23_2022-GO95MLD-1^06146005.0281500 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
841491371-34371-DETAIL-02_24_2022-GUYHINS-1^06146005.0218000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
41544863-51879-DETAIL-02_22_2022-GO95MLD-1^06146005.0218401 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
280412494-41594-DTLSB-03_17_2022-GUYHINS-1^06146005.0221700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
191499973-46330-DTLSB-03_16_2022-GO95MLD-1^06146005.0221900 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
308202523-61450-DTLSB-03_17_2022-COPLLEAN-1^06146005.0221902 | POLE | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
460231323-66721-DTLSB-03_17_2022-CONDFRAY-1^06146005.0221903 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
460231323-66721-DTLSB-03_17_2022-GO95MLD-1^06146005.0221903 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
156824164-390-DTLSB-03_16_2022-GO95HV-1^06146005.0222400 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2027-03-16 | 3
242637154-15680-DETAIL-02_23_2022-GO95HV-1^06146005.0281501 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
641277874-49361-DETAIL-02_23_2022-GO95HV-1^06146005.0283401 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
305451274-33379-DETAIL-02_23_2022-GO95MLD-1^06146005.0284301 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
254241526-56990-DTLSB-03_23_2022-ABNDEQPM-1^06146005.0243100 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
493508073-30099-DTLSB-03_23_2022-GO95MLD-1^06146005.0243202 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
537649553-31653-DTLSB-03_23_2022-GO95HV-1^06146005.0243400 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
965523321-27763-DETAIL-03_08_2022-GO95HV-1^06146006.0070901 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
642107491-96961-DETAIL-03_08_2022-CUTOUTAR-1^06146006.0070902 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
642107491-96961-DETAIL-03_08_2022-GO95BLTC-1^06146006.0070902 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
80068220-20210-DETAIL-03_08_2022-GO95HV-1^06146006.0073901 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
670393711-60131-DETAIL-03_07_2022-GO95MLD-1^06146006.0074500 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
714504861-11461-DETAIL-03_07_2022-GO95HV-1^06146006.0074501 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
456820460-24121-DETAIL-03_02_2022-GO95MLD-1^06146006.0075000 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
258920031-25690-DETAIL-03_02_2022-GO95MLD-1^06146006.0075100 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
889228154-482-DTLSB-03_22_2022-GO95MLD-1^06146005.0243800 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
667362414-11514-DETAIL-03_01_2022-GO95MLD-1^06146006.0092600 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
611565398-30379-DETAIL-03_02_2022-GO95MLD-1^06146006.0184900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
671421488-32241-DETAIL-03_02_2022-GO95MLD-1^06146006.0185900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
650058499-99881-DETAIL-03_08_2022-GO95MLD-1^06146006.0213401 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
66133888-88380-DETAIL-03_08_2022-ABNDEQPM-1^06146006.0214402 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
66133888-88380-DETAIL-03_08_2022-GO95MLD-1^06146006.0214402 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
833444519-46202-DETAIL-03_09_2022-GO95MLD-1^06146006.0283701 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
833444519-46202-DETAIL-03_09_2022-GUYHINS-1^06146006.0283701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
950873389-1033-DETAIL-03_09_2022-GO95HV-1^06146006.0299700 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
318366660-67260-ADMIN-01_11_2022-POLEDERP-1^06147001.0105400 | POLE | CA-NON-TIER | Distribution | 2022-01-11 | 2025-01-11 | 2
270478708-96210-ADMIN-01_11_2022-POLEDERP-1^06147001.0106500 | POLE | CA-NON-TIER | Distribution | 2022-01-11 | 2025-01-11 | 2
709793930-92551-DETAIL-01_26_2023-GO95MLD-2^06147003.0141100 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
548894450-91741-DETAIL-01_26_2023-GO95CL10-1^06147003.0142101 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
735674140-13711-DETAIL-01_26_2023-GO95HV-1^06147003.0142502 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
54647700-69160-DETAIL-01_26_2023-GO95HV-1^06147003.0142504 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
197406300-73230-DETAIL-01_26_2023-GO95HV-1^06147003.0142600 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
549453100-83441-DETAIL-01_26_2023-GO95HV-1^06147003.0142601 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
987352486-83486-DETAIL-01_26_2023-GO95MLD-1^06147003.0167901 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
69187890-58190-DETAIL-03_07_2022-GO95TCH-1^06146006.0077900 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
823474650-67772-DETAIL-03_07_2022-INSULDMG-1^06146006.0078501 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
823474650-67772-DETAIL-03_07_2022-INSULDMG-2^06146006.0078501 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
15379180-17989-DETAIL-03_07_2022-GUYHINS-1^06146006.0079500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
15379180-17989-DETAIL-03_07_2022-INSULDMG-1^06146006.0079500 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
821758906-87162-DETAIL-02_06_2023-GO95MLD-1^06147002.0318900 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
188598568-44179-DETAIL-02_03_2022-GO95MLD-1^06147005.0260400 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
603920320-71479-DETAIL-02_02_2022-GO95MLD-1^06147005.0260501 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
130582510-72379-DETAIL-02_02_2022-ABNDEQPM-1^06147005.0260503 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
49095329-81209-DETAIL-01_31_2022-GO95MLD-1^06147005.0260601 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
439582539-86609-DETAIL-02_02_2022-GO95MLD-1^06147005.0261500 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
720700179-66279-DETAIL-01_31_2022-GO95MLD-1^06147005.0261601 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
167765159-10309-DETAIL-01_31_2022-GO95MLD-1^06147005.0261700 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
706650078-4279-DETAIL-02_02_2022-GO95HV-1^06147005.0262200 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
141862569-15209-DETAIL-01_31_2022-SVCENTCO-1^06147005.0262601 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
915311189-94209-DETAIL-01_31_2022-GO95MLD-1^06147005.0262603 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
150980299-37209-DETAIL-02_01_2022-GO95MLD-2^06147005.0262704 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
111079698-12879-DETAIL-01_31_2022-GO95MLD-1^06147005.0265801 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
42231334-85379-DETAIL-02_02_2022-SVCENTCO-1^06147005.0266202 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
411583888-65888-DETAIL-02_01_2022-SVCENTCO-1^06147005.0266308 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
610821178-48979-DETAIL-02_02_2022-GO95MLD-1^06147005.0267200 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
569721919-23099-DETAIL-09_29_2021-SVCROAD-1^06147005.0047200 | OTHER | CA-NON-TIER | Distribution | 2021-09-29 | 2024-09-29 | 2
537309872-75009-DTLSB-03_18_2019-SVCROAD-1^06147005.0219502 | OTHER | CA-NON-TIER | Distribution | 2019-03-18 | 2024-02-18 | 2
498050742-38099-DTLSB-02_27_2019-ENCHRW-1^06147005.0220302 | OTHER | CA-NON-TIER | Distribution | 2019-02-27 | 2024-01-27 | 2
101186448-609-DETAIL-02_03_2022-GO95HV-1^06147005.0260000 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2027-02-03 | 3
447416728-41099-DETAIL-02_03_2022-GO95MLD-1^06147005.0260300 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
863052778-23099-DETAIL-02_02_2022-GO95MLD-1^06147005.0260500 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
545779964-31109-DETAIL-02_15_2022-GO95HV-1^06147005.0330700 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
748129544-10109-DETAIL-02_15_2022-GO95MLD-1^06147005.0331400 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
650705154-51109-DETAIL-02_15_2022-GO95HV-1^06147005.0331700 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
793872834-18009-DETAIL-02_15_2022-INSULDMG-1^06147005.0332300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
106573174-57189-DETAIL-02_15_2022-GRDRODHI-1^06147005.0332601 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
971257585-53109-DETAIL-02_15_2022-GO95TCH-1^06147005.0332700 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
646447484-29279-DETAIL-02_15_2022-GO95MLD-1^06147005.0332702 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
346556284-37009-DETAIL-02_15_2022-INSULDMG-1^06147005.0333201 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
202187914-95009-DETAIL-02_15_2022-GO95HV-1^06147005.0334102 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
377562874-13109-DETAIL-02_15_2022-GO95MLD-1^06147005.0334700 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
524140474-64109-DETAIL-02_15_2022-GO95HV-1^06147005.0334702 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
858491704-82779-DETAIL-02_15_2022-GO95BLTC-1^06147005.0335000 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
805944190-77512-DETAIL-02_10_2022-GO95HV-1^06147005.0360300 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
805944190-77512-DETAIL-02_10_2022-GUYHINS-1^06147005.0360300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
878054320-47079-DETAIL-02_16_2022-GO95MLD-1^06147005.0360700 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
957452111-4243-DETAIL-02_14_2022-GO95HV-1^06147005.0360901 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
397596653-1199-DETAIL-02_09_2022-GO95HV-1^06147005.0284400 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
289781273-89099-DETAIL-02_09_2022-GO95MLD-1^06147005.0287400 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
793490883-29099-DETAIL-02_09_2022-GO95MLD-1^06147005.0288400 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
221463046-8199-DETAIL-02_15_2022-GO95HV-1^06147005.0330200 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
707777554-48009-DETAIL-02_15_2022-GO95MLD-1^06147005.0330201 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
707777554-48009-DETAIL-02_15_2022-GO95TCH-1^06147005.0330201 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
480149354-26579-DETAIL-02_15_2022-CLRTOUCH-1^06147005.0330500 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
480149354-26579-DETAIL-02_15_2022-GO95MLD-1^06147005.0330500 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
805944190-77512-DETAIL-02_10_2022-GO95MLD-1^06147005.0360300 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
805944190-77512-DETAIL-02_10_2022-GO95TCH-1^06147005.0360300 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
228683444-43164-DETAIL-02_16_2022-GUYSLACK-1^06147005.0363560-A | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
328520678-80678-DETAIL-02_09_2022-GO95MLD-1^06147005.0365201 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
328520678-80678-DETAIL-02_09_2022-GO95TCH-1^06147005.0365201 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
853533258-85562-DETAIL-02_16_2022-GO95BLTC-1^06147005.0367200 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
784582060-81142-DETAIL-02_17_2022-GO95HV-1^06147005.0367901 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
243659888-3280-DETAIL-02_10_2022-GO95HV-1^06147005.0368100 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
616239370-12831-DETAIL-02_17_2022-GO95MLD-1^06147005.0369100 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
814517010-23442-DETAIL-02_16_2022-GO95HV-1^06147005.0369901 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
776114510-50222-DETAIL-02_16_2022-GO95MLD-1^06147005.0369902 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
49081590-34590-DETAIL-02_16_2022-GO95HV-1^06147005.0369903 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
817672890-27789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153001 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
872179020-53889-DETAIL-01_09_2023-GO95HV-1^06148003.0153300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
525122080-85789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154100 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
434001670-55789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
502853450-94789-DETAIL-01_09_2023-GO95HV-1^06148003.0154300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
686266160-35789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154302 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
418621520-43789-DETAIL-01_09_2023-GO95HV-1^06148003.0156300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
259701530-73789-DETAIL-01_09_2023-GO95MLD-1^06148003.0156301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
570033820-13789-DETAIL-01_09_2023-GO95MLD-1^06148003.0157300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
804559110-32789-DETAIL-01_09_2023-GO95MLD-1^06148003.0158300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
58616859-94489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0174000 | POLE | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
447250159-53489-DETAIL-01_26_2023-CONDFRAY-1^06148003.0174100 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
490145909-28461-DETAIL-01_25_2023-GO95MLD-1^06148003.0265001 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
96192260-20579-DETAIL-01_24_2023-GO95HV-1^06148003.0265500 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
96192260-20579-DETAIL-01_24_2023-GO95MLD-1^06148003.0265500 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
96192260-20579-DETAIL-01_24_2023-GRDRODHI-1^06148003.0265500 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
959789779-63653-DETAIL-01_24_2023-GO95HV-1^06148003.0265501 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
720628359-12379-DETAIL-01_30_2023-GO95BLTC-1^06148003.0295401 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
720628359-12379-DETAIL-01_30_2023-GO95MLD-1^06148003.0295401 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
505151649-7679-DETAIL-01_30_2023-ABNDEQPM-1^06148003.0295402 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
822753719-54379-DETAIL-01_30_2023-GO95MLD-1^06148003.0295501 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
259549849-29990-DETAIL-01_25_2023-COPLLEAN-1^06148003.0355301 | POLE | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
941019959-1203-DETAIL-01_25_2023-GRDRODHI-1^06148003.0355501 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
941019959-1203-AUDIT-02_06_2023-GO95HV-1^06148003.0355501 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
941019959-1203-AUDIT-02_06_2023-GRDRODHI-1^06148003.0355501 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
642791511-98089-DETAIL-01_24_2023-GO95MLD-1^06148003.0240200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
292623311-55089-DETAIL-01_24_2023-GO95MLD-1^06148003.0243400 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
494595155-73989-DETAIL-01_24_2023-GO95MLD-1^06148003.0248500 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
638904651-74089-DETAIL-01_24_2023-GO95MLD-1^06148003.0248501 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
225050031-99579-DETAIL-01_24_2023-GO95MLD-1^06148003.0249501 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
619480261-9289-DETAIL-01_24_2023-GO95MLD-1^06148003.0249502 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
433478259-99279-DETAIL-01_24_2023-GO95HV-1^06148003.0257601 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
433478259-99279-DETAIL-01_24_2023-GO95MLD-1^06148003.0257601 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
514012539-88891-DETAIL-01_24_2023-INSULDMG-1^06148003.0265400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
514012539-88891-DETAIL-01_24_2023-INSULDMG-2^06148003.0265400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
53154578-35578-DETAIL-01_16_2023-GO95MLD-1^06148004.0165301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
53154578-35578-DETAIL-01_16_2023-GO95TCH-1^06148004.0165301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
911087461-86879-DETAIL-01_24_2023-COPLLEAN-1^06148004.0182200 | POLE | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
911087461-86879-DETAIL-01_24_2023-GO95MLD-1^06148004.0182200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
406432384-7989-DETAIL-01_24_2023-CONDFRAY-1^06148004.0182201 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
721781521-18379-DETAIL-01_24_2023-GO95HV-1^06148004.0182203 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
246769105-26889-DETAIL-01_10_2023-GO95MLD-1^06148004.0183201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
246769105-26889-DETAIL-01_10_2023-SVCSVC-1^06148004.0183201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
72765124-41379-DETAIL-01_16_2023-GO95TCH-1^06148004.0162302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
876075484-75909-DETAIL-01_16_2023-GO95HV-1^06148004.0163200 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
387241904-81279-DETAIL-01_16_2023-GO95MLD-1^06148004.0163303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
387241904-81279-DETAIL-01_16_2023-GO95MLD-2^06148004.0163303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
797710824-3579-DETAIL-01_16_2023-GO95MLD-1^06148004.0163304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
299242151-28451-DETAIL-01_16_2023-GO95MLD-1^06148004.0164120 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
287185054-79989-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192701 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
500625636-38989-DETAIL-01_23_2023-GO95MLD-1^06148004.0192900 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
390516191-55179-DETAIL-01_23_2023-GO95BLTC-1^06148004.0192903 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
626270154-69589-DETAIL-01_23_2023-GRDRODHI-1^06148004.0193002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
568363054-39689-DETAIL-01_23_2023-GO95MLD-1^06148004.0193003 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
480886004-62979-DETAIL-01_23_2023-GO95MLD-1^06148004.0193200 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
256266141-23189-DETAIL-01_23_2023-GO95HV-1^06148004.0193202 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
331697604-40540-DETAIL-01_23_2023-GO95MLD-1^06148004.0193700 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
762469876-12976-DETAIL-01_23_2023-GO95TCH-1^06148004.0193701 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
535532334-57689-DETAIL-01_23_2023-GO95MLD-1^06148004.0196000 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
43261524-76689-DETAIL-01_23_2023-GO95HV-1^06148004.0197001 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
567072805-90109-DETAIL-01_19_2023-GO95MLD-1^06148004.0199601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
9996305-30189-DETAIL-01_23_2023-GO95MLD-1^06148004.0192404 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
2514386-77179-DETAIL-01_23_2023-ABNDEQPM-1^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
2514386-77179-DETAIL-01_23_2023-GO95HV-1^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
2514386-77179-DETAIL-01_23_2023-GO95MLD-1^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
2514386-77179-DETAIL-01_23_2023-GRDRODHI-2^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
403845295-89-DETAIL-01_23_2023-GO95MLD-1^06148004.0192700 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
390516191-55179-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192903 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
626270154-69589-DETAIL-01_23_2023-GO95CL10-1^06148004.0193002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
626270154-69589-DETAIL-01_23_2023-GO95MLD-1^06148004.0193002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
331697604-40540-DTLSB-03_12_2018-GO95CLSV-1^06148004.0193700 | OTHER | CA-NON-TIER | Distribution | 2018-03-12 | 2023-02-12 | 2
762469876-12976-DETAIL-01_23_2023-GO95MLD-1^06148004.0193701 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
468054034-17689-DETAIL-01_23_2023-GO95MLD-1^06148004.0196002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
758896411-48109-ADMIN-01_17_2023-ENCHRW-1^06148004.0219500 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
758896411-48109-AUDIT-02_16_2023-GO95CLSV-1^06148004.0219500 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
910943803-99279-DETAIL-01_18_2023-GO95CL10-1^06148004.0220300 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
405058381-9579-DETAIL-01_18_2023-GO95MLD-1^06148004.0220301 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
623198271-22379-DETAIL-01_17_2023-GO95MLD-1^06148004.0220501 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
425267583-30209-DETAIL-01_17_2023-GO95MLD-1^06148004.0220601 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
12948131-50209-DETAIL-01_17_2023-GO95MLD-1^06148004.0220602 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
358491331-73079-DETAIL-01_17_2023-GO95CL10-1^06148004.0220701 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
358491331-73079-DETAIL-01_17_2023-GO95MLD-1^06148004.0220701 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
593232111-87679-DETAIL-01_17_2023-SVCROAD-1^06148004.0220702 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
876130821-41209-DETAIL-01_17_2023-GO95HV-1^06148004.0220800 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
310282351-14450-DETAIL-01_18_2023-GO95MLD-2^06148004.0221001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
490469561-75419-DTLSB-11_08_2021-SVCENTBK-1^06148004.0310103 | OTHER | CA-NON-TIER | Distribution | 2021-11-08 | 2024-11-08 | 2
295572123-83809-DETAIL-08_25_2021-SVCWIND-1^06148004.0353206 | OTHER | CA-NON-TIER | Distribution | 2021-08-25 | 2024-08-25 | 2
798114330-94582-DETAIL-08_30_2021-SVCROAD-1^06148004.0354600 | OTHER | CA-NON-TIER | Distribution | 2021-08-30 | 2024-08-30 | 2
12885596-21646-DETAIL-09_09_2021-GO95MLD-1^06148004.0355002 | OTHER | CA-NON-TIER | Distribution | 2021-09-09 | 2026-09-09 | 3
343565206-21366-DETAIL-09_27_2021-GO95MLD-1^06148004.0356202 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
780633844-20253-DETAIL-09_27_2021-SVCROAD-1^06148004.0356300 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
618646698-79589-DETAIL-10_28_2021-ENCHRW-1^06148005.0254700 | OTHER | CA-NON-TIER | Distribution | 2021-10-28 | 2024-10-28 | 2
104792999-6509-DETAIL-10_28_2021-ENCHRW-1^06148005.0255100 | OTHER | CA-NON-TIER | Distribution | 2021-10-28 | 2024-10-28 | 2
104792999-6509-DETAIL-10_28_2021-ENCHRW-2^06148005.0255100 | OTHER | CA-NON-TIER | Distribution | 2021-10-28 | 2024-10-28 | 2
1249911-18309-DETAIL-01_17_2023-GO95TCH-1^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-GRDRODHI-1^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-SVCROAD-1^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
554945733-3679-DETAIL-01_17_2023-GO95MLD-1^06148004.0227101 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
113402533-53309-DETAIL-01_17_2023-GUYSLACK-1^06148004.0227700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
750468333-93309-DETAIL-01_17_2023-GO95HV-1^06148004.0227800 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
911233854-1710-DETAIL-11_16_2022-ABNDEQPM-1^06238004.0155200 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
840817605-89010-DETAIL-11_16_2022-SVCWIND-1^06238004.0155241 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
840817605-89010-DETAIL-11_16_2022-SVCWIND-2^06238004.0155241 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
495058394-19010-DETAIL-11_16_2022-GO95MLD-1^06238004.0156240 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
796668894-98010-DETAIL-11_16_2022-GO95MLD-1^06238004.0156242 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
71354384-75710-DETAIL-11_16_2022-GO95HV-1^06238004.0156402 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
870980354-25990-DETAIL-02_23_2021-GO95MLD-1^06239002.0063607 | OTHER | CA-NON-TIER | Distribution | 2021-02-23 | 2024-02-23 | 2
392870195-94200-DETAIL-02_23_2021-GO95MLD-1^06239002.0063611 | OTHER | CA-NON-TIER | Distribution | 2021-02-23 | 2024-02-23 | 2
546906558-85740-ADMIN-06_01_2023-POLEREPL-1^06239002.0180902 | POLE | CA-TIER-2 | Distribution | 2023-06-01 | 2024-06-01 | 2
383734838-45250-DETAIL-03_11_2021-GO95MLD-1^06239003.0016102 | OTHER | CA-TIER-2 | Distribution | 2021-03-11 | 2024-03-11 | 2
383734838-45250-DETAIL-12_06_2023-POLEREST-1^06239003.0016102 | POLE | CA-TIER-2 | Distribution | 2023-12-06 | 2024-03-05 | 1
763231414-26890-DETAIL-03_11_2021-GO95MLD-1^06239003.0016510 | OTHER | CA-TIER-2 | Distribution | 2021-03-11 | 2024-03-11 | 2
531079135-63600-DETAIL-03_10_2021-GO95MLD-1^06239003.0016717 | OTHER | CA-TIER-2 | Distribution | 2021-03-10 | 2026-03-10 | 3
910279616-76786-DETAIL-09_27_2021-SVCROAD-2^06148004.0356301 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
974678536-72670-DETAIL-01_24_2022-GO95TCH-1^06239004.0254500 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
286775236-60670-AUDIT-02_10_2022-ANCHIDLE-1^06239004.0255000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-02-10 | 2025-02-10 | 2
813919516-67170-DETAIL-01_19_2022-SVCWIND-1^06239004.0255040 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
771025414-68431-DETAIL-01_18_2022-SVCROOF-1^06239004.0255101 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
324980206-90510-DETAIL-11_10_2022-SVCROAD-1^06238004.0223704 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
797352398-66440-DETAIL-11_17_2022-GO95HV-1^06238004.0224100 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2027-11-17 | 3
338006476-10710-DETAIL-11_10_2022-GO95MLD-1^06238004.0224803 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
978597606-9210-DETAIL-11_10_2022-GO95HV-1^06238004.0224900 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
724672846-58310-DETAIL-11_10_2022-GO95TCH-1^06238004.0225700 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
58815951-19850-DETAIL-11_17_2022-GRDRODHI-1^06238004.0271642 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
637334801-85250-DETAIL-11_17_2022-SVCROAD-1^06238004.0272801 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
798638111-750-DETAIL-11_17_2022-GO95MLD-1^06238004.0273702 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2027-11-17 | 3
264735926-63370-DETAIL-01_19_2022-GO95HV-1^06239004.0255144 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2027-01-19 | 3
50413766-44770-DETAIL-01_18_2022-SVCWIND-1^06239004.0256110 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
869368509-38190-DETAIL-01_24_2022-SVCWIND-1^06239004.0256113 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
285270254-76860-DETAIL-01_24_2022-SVCENTCO-1^06239004.0256203 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
329366836-15570-DETAIL-01_19_2022-GO95HV-1^06239004.0256207 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2027-01-19 | 3
168464088-44390-DETAIL-01_19_2022-SVCWIND-1^06239004.0256213 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
754357698-86390-DETAIL-01_19_2022-GO95HV-1^06239004.0256214 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2027-01-19 | 3
248341098-91098-DETAIL-01_24_2022-SVCWIND-1^06239004.0256401 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
248341098-91098-DETAIL-01_24_2022-SVCWIND-3^06239004.0256401 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
796025820-69001-DETAIL-01_17_2022-SVCWIND-1^06239004.0256404 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
883705780-54890-DETAIL-01_17_2022-SVCWIND-1^06239004.0256407 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
615861183-57550-DETAIL-01_17_2022-GO95HV-1^06239004.0256501 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2027-01-17 | 3
777668416-97480-DETAIL-01_17_2022-SVCWIND-1^06239004.0256546 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
196306326-56470-DETAIL-01_24_2022-GO95MLD-1^06239004.0257700 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
817001398-93898-DETAIL-01_12_2022-GO95HV-1^06239004.0257702 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2027-01-12 | 3
551277364-32460-DETAIL-01_12_2022-SVCENTCO-1^06239004.0257804 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
240082246-15670-DETAIL-01_18_2022-GO95BLTC-1^06239004.0257840 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
357545834-52660-DETAIL-01_18_2022-GO95BLTC-1^06239004.0257900 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
2842796-10170-DETAIL-01_18_2022-CLMBHAZ-1^06239004.0257941 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
638692800-80690-DETAIL-01_25_2022-GO95HV-1^06239004.0258004 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
537637740-2590-DETAIL-01_25_2022-GO95MLD-1^06239004.0258005 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
137131940-61590-DETAIL-01_25_2022-GO95MLD-1^06239004.0258006 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
506235205-5270-DETAIL-01_25_2022-GO95BLTC-1^06239004.0258301 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
459355356-35770-DETAIL-01_25_2022-GO95BLTC-1^06239004.0258400 | OTHER | CA-TIER-3 | Distribution | 2022-01-25 | 2027-01-25 | 3
459355356-35770-DETAIL-01_25_2022-GO95MLD-1^06239004.0258400 | OTHER | CA-TIER-3 | Distribution | 2022-01-25 | 2025-01-25 | 2
292534261-41711-DETAIL-01_25_2022-SVCWIND-1^06239004.0258440 | OTHER | CA-TIER-3 | Distribution | 2022-01-25 | 2025-01-25 | 2
467430376-92780-DETAIL-11_15_2022-SVCWIND-1^06239004.0364401 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
747267431-38211-DETAIL-11_14_2022-SVCWIND-1^06239004.0364600 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
348887133-86521-DETAIL-11_14_2022-GO95CL10-1^06239004.0364706 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
744033483-12221-DETAIL-11_14_2022-SVCWIND-1^06239004.0364802 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
905663973-39021-DETAIL-11_14_2022-GO95CL10-1^06239004.0364803 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
45658623-12721-DETAIL-11_14_2022-GO95TCH-1^06239004.0364804 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
248352185-75241-DETAIL-11_15_2022-GO95HV-1^06239004.0365500 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2027-11-15 | 3
956510374-62260-DETAIL-01_18_2022-SVCWIND-1^06239004.0256106 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
905947374-6160-DETAIL-01_18_2022-GO95TCH-1^06239004.0256107 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
923766926-22370-DETAIL-01_18_2022-SVCENTCO-1^06239004.0256111 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
869368509-38190-DETAIL-01_24_2022-SVCRUBLG-1^06239004.0256113 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
441478085-52470-DETAIL-01_18_2022-GO95MLD-1^06239004.0256200 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
453495056-6271-DETAIL-11_14_2022-GO95TCH-1^06239004.0367941 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
65505056-69171-AUDIT-12_07_2022-GO95TCH-1^06239004.0367944 | OTHER | CA-TIER-2 | Distribution | 2022-12-07 | 2025-12-07 | 2
65127516-63081-DETAIL-11_14_2022-SVCWIND-1^06239004.0367945 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
9677113-16650-DETAIL-01_17_2022-GO95BLTC-1^06239004.0256907 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2027-01-17 | 3
822697682-80472-ADMIN-07_11_2023-POLEREPL-1^06239004.0256940 | POLE | CA-TIER-2 | Distribution | 2023-07-11 | 2024-07-11 | 2
993285001-5501-DETAIL-01_25_2022-GO95MLD-1^06239004.0257040 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
121338399-48790-DETAIL-01_24_2022-GO95MLD-1^06239004.0257101 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
844856295-63470-DETAIL-01_18_2022-GO95TCH-1^06239004.0257103 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
124330715-16470-DETAIL-01_24_2022-GO95MLD-1^06239004.0257104 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
7519041-95211-DETAIL-01_25_2022-GO95BLTC-1^06239004.0257244 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
772718281-11801-DETAIL-01_25_2022-GO95CL10-1^06239004.0257342 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
840579195-99351-DETAIL-11_15_2022-SVCWIND-1^06239004.0368901 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
514186515-20569-DETAIL-04_24_2023-GO95HV-1^06240004.0061100 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
260512225-12275-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061102 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
492251139-22370-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061106 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
545984213-31230-DETAIL-04_25_2023-GO95MLD-1^06240004.0061602 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2028-04-25 | 3
666633573-76430-DETAIL-04_27_2023-GO95MLD-1^06240004.0061700 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
632074653-19830-DETAIL-04_27_2023-GO95MLD-1^06240004.0061702 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
315056623-27630-DETAIL-04_27_2023-GO95MLD-1^06240004.0061703 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
644548613-230-DETAIL-04_25_2023-GO95MLD-1^06240004.0062600 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
364782013-56630-DETAIL-04_25_2023-GO95MLD-1^06240004.0062601 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
413533213-3630-DETAIL-04_25_2023-GO95MLD-1^06240004.0062702 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
300458783-85530-DETAIL-04_25_2023-GO95MLD-1^06240004.0062704 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
300458783-85530-DETAIL-04_25_2023-GO95TCH-1^06240004.0062704 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
292285509-97419-DETAIL-04_25_2023-SVCROAD-1^06240004.0064803 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
991229733-35730-DETAIL-04_25_2023-RISECLMB-1^06240004.0064804 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
519222943-12730-DETAIL-04_25_2023-RISEGRD-1^06240004.0064903 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
151064883-13430-AUDIT-07_05_2023-POLESTEP-1^06240004.0065100 | POLE | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
364273133-6230-DETAIL-04_26_2023-GO95HV-1^06240004.0065102 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
731790413-27130-DETAIL-04_24_2023-GO95BLTC-1^06240004.0065400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
731790413-27130-DETAIL-04_24_2023-GO95MLD-1^06240004.0065400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
510977353-19330-DETAIL-04_25_2023-GO95MLD-1^06240004.0065905 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
169046143-13721-DETAIL-11_14_2022-GO95TCH-1^06239004.0364801 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
169046143-13721-DETAIL-11_14_2022-SVCWIND-1^06239004.0364801 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
474432336-31661-DETAIL-11_16_2022-GO95MLD-1^06239004.0365501 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
896617526-63961-DETAIL-11_14_2022-GO95TCH-1^06239004.0365700 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
973909138-350-DTLSB-05_05_2021-GO95MLD-1^06240003.0081700 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2024-05-05 | 2
457510128-6150-DTLSB-05_05_2021-GO95MLD-1^06240003.0081702 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2024-05-05 | 2
963202048-74350-DTLSB-05_05_2021-ABNDEQPM-1^06240003.0081802 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2026-05-05 | 3
694529995-31270-DTLSB-05_03_2021-GO95MLD-1^06240003.0181600 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
176764705-24270-DTLSB-05_03_2021-GO95MLD-1^06240003.0182601 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
856067846-13080-DETAIL-04_26_2023-GO95MLD-1^06240004.0050004 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
693602216-94980-DETAIL-05_01_2023-GO95MLD-1^06240004.0050140 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
936510216-32980-DETAIL-05_01_2023-GO95MLD-1^06240004.0050142 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
896026976-29080-DETAIL-04_26_2023-SVCDEFLC-1^06240004.0051000 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
654179707-64970-DETAIL-04_26_2023-GO95MLD-1^06240004.0060100 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
101350607-84970-DETAIL-04_27_2023-CLRTOUCH-1^06240004.0060203 | CONDUCTOR | CA-TIER-2 | Distribution | 2023-04-27 | 2024-04-27 | 2
200687838-93170-DETAIL-01_23_2023-GO95MLD-1^06240004.0080002 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
450510623-85630-DETAIL-04_25_2023-GO95MLD-1^06240004.0062701 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
836603229-50770-DETAIL-04_26_2023-SVCENTCO-1^06240004.0063100 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
19071749-82370-DETAIL-04_26_2023-GO95MLD-1^06240004.0063101 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
612838678-33778-DETAIL-04_26_2023-GO95HV-1^06240004.0063104 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
262862697-39970-DETAIL-04_26_2023-GO95MLD-1^06240004.0063202 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
480089259-27370-DETAIL-04_26_2023-SVCENTCO-1^06240004.0063206 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
904239093-36430-DETAIL-04_25_2023-GO95MLD-1^06240004.0063700 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
430432817-9870-DETAIL-04_26_2023-GO95MLD-1^06240004.0064102 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
430432817-9870-DETAIL-04_26_2023-GO95TCH-1^06240004.0064102 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
497392204-54103-DETAIL-04_26_2023-GO95HV-1^06240004.0064104 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
355015239-44770-DETAIL-04_26_2023-GO95MLD-1^06240004.0064203 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
110457259-13870-DETAIL-04_26_2023-GO95MLD-1^06240004.0064204 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
734150340-4630-DETAIL-01_17_2023-GO95MLD-1^06240004.0085044 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
734150340-4630-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085044 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
980427192-50470-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085101 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
959133402-37370-DETAIL-01_17_2023-GUYHINS-1^06240004.0085302 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
931107092-96370-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085303 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
124211572-55370-DETAIL-01_18_2023-SVCDEFLC-1^06240004.0085304 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
145199605-45530-DETAIL-01_17_2023-GO95TCH-1^06240004.0085341 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
205049311-17030-DETAIL-01_18_2023-GO95CL10-1^06240004.0085400 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2028-01-18 | 3
429070508-73330-DETAIL-01_18_2023-GO95MLD-1^06240004.0085606 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
892468185-73530-DETAIL-01_18_2023-GO95MLD-1^06240004.0086240 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
374620858-8740-DETAIL-01_16_2023-GO95HV-1^06240004.0091604 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2028-01-16 | 3
663362409-31173-DETAIL-01_12_2023-GO95MLD-1^06240004.0092101 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
178877481-85830-DETAIL-01_11_2023-ABNDEQPM-1^06240004.0092204 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
332838129-34473-DETAIL-01_18_2023-GO95TCH-1^06240004.0092300 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
660273109-50473-DETAIL-01_18_2023-GO95MLD-1^06240004.0092302 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
893478694-61794-DETAIL-01_11_2023-GO95HV-1^06240004.0092306 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
669328988-52940-DETAIL-01_16_2023-SVCWIND-1^06240004.0092500 | OTHER | CA-TIER-3 | Distribution | 2023-01-16 | 2026-01-16 | 2
229769878-73840-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0092506 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
229769878-73840-DETAIL-01_16_2023-SVCROAD-1^06240004.0092506 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
677611608-97050-DETAIL-01_16_2023-GO95MLD-1^06240004.0093500 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
554804066-42880-DETAIL-01_11_2023-GO95MLD-1^06240004.0094004 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
75042973-58450-DETAIL-01_09_2023-GO95MLD-1^06240004.0095701 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2028-01-09 | 3
763930275-33530-DETAIL-01_17_2023-GO95HV-1^06240004.0086241 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
763930275-33530-DETAIL-01_17_2023-GO95MLD-1^06240004.0086241 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
155870422-13370-DETAIL-01_23_2023-RISECLMB-1^06240004.0087000 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
860375798-83730-DETAIL-01_12_2023-GO95TCH-1^06240004.0089501 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
47284744-66060-DETAIL-01_11_2023-SVCDEFLC-1^06240004.0098005 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
757940848-60830-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0098206 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
842096049-57330-DETAIL-01_09_2023-GO95MLD-1^06240004.0098403 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
547464608-92350-DETAIL-01_09_2023-GO95MLD-1^06240004.0098600 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
743916779-55353-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0099001 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
33213714-99660-DETAIL-01_11_2023-SVCENTCO-1^06240004.0099004 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
766221624-61090-DETAIL-01_11_2023-GO95MLD-1^06240004.0099005 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
359676701-87680-DETAIL-03_21_2023-GO95HV-1^06240004.0163600 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
567809923-86480-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0163601 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
66355563-54980-DETAIL-03_21_2023-GO95MLD-1^06240004.0163602 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
279401196-17310-DETAIL-03_21_2023-GO95HV-1^06240004.0163605 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
279401196-17310-DETAIL-03_21_2023-GUYHINS-2^06240004.0163605 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
990074506-98310-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0163607 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
688622223-55780-DETAIL-03_27_2023-GO95MLD-1^06240004.0163611 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
378286658-36350-DETAIL-03_21_2023-GO95MLD-1^06240004.0163703 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
873228383-34380-DETAIL-04_19_2023-GO95MLD-1^06240004.0163800 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
736512018-55150-DETAIL-04_12_2023-GO95MLD-1^06240004.0163901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
281951809-67170-DETAIL-03_22_2023-GO95MLD-1^06240004.0164301 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
281951809-67170-DETAIL-03_22_2023-GRDRODHI-3^06240004.0164301 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
245959370-82970-DETAIL-03_28_2023-GO95MLD-1^06240004.0165503 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
603032780-77270-DETAIL-04_19_2023-GO95MLD-1^06240004.0165506 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
801882231-89180-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0165540 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
925988918-48240-DETAIL-03_23_2023-GO95MLD-1^06240004.0165601 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
987259911-56970-DETAIL-04_17_2023-GO95MLD-1^06240004.0165641 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
622785331-95080-DETAIL-04_17_2023-GO95BLTC-1^06240004.0165643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
897459310-8070-DETAIL-03_29_2023-SVCDEFLC-1^06240004.0165707 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
705999990-38670-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0165708 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
635907348-57720-DETAIL-01_10_2023-GO95MLD-1^06240004.0098300 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
178938638-30130-DETAIL-01_09_2023-GO95MLD-1^06240004.0098400 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
257910668-27343-DETAIL-01_09_2023-GO95MLD-1^06240004.0098402 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
710094148-40350-DETAIL-03_21_2023-GUYHINS-1^06240004.0162603 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
326423368-35650-DETAIL-03_21_2023-GO95HV-1^06240004.0162643 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
895612633-80280-DETAIL-03_21_2023-GO95MLD-1^06240004.0162700 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
244463208-57240-DETAIL-03_21_2023-ABNDEQPM-1^06240004.0162703 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
587253983-66380-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0163500 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
138006878-74840-DETAIL-03_27_2023-GO95TCH-1^06240004.0163501 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
364175297-46240-DETAIL-03_27_2023-GO95HV-1^06240004.0163502 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
364175297-46240-DETAIL-03_27_2023-GO95MLD-1^06240004.0163502 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
651565833-2880-DETAIL-03_23_2023-GO95MLD-1^06240004.0163504 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
636383136-44410-DETAIL-03_27_2023-GO95MLD-1^06240004.0163505 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
66355563-54980-DETAIL-03_21_2023-GO95TCH-1^06240004.0163602 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
398506286-9210-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0163603 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
445323300-46870-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0166705 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
925054519-20470-DETAIL-03_29_2023-GO95HV-1^06240004.0166841 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2028-03-29 | 3
925054519-20470-DETAIL-03_29_2023-GO95MLD-1^06240004.0166841 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
683344569-42370-DETAIL-03_29_2023-GO95MLD-1^06240004.0166842 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
318312388-59770-DETAIL-04_12_2023-SVCDEFLC-2^06240004.0166901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
318312388-59770-DETAIL-04_12_2023-SVCENTCO-1^06240004.0166901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
33796397-64670-DETAIL-04_12_2023-GO95HV-1^06240004.0166902 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
251764928-54170-DETAIL-03_28_2023-GO95TCH-1^06240004.0166905 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
251764928-54170-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0166905 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
64820063-82380-DETAIL-03_22_2023-GO95MLD-1^06240004.0167000 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
633510681-70080-DETAIL-03_27_2023-GO95MLD-1^06240004.0167005 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
774502352-96780-DETAIL-03_27_2023-GO95TCH-1^06240004.0167245 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
853910491-22080-DETAIL-04_11_2023-GO95MLD-1^06240004.0167302 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
693368121-99970-DETAIL-03_22_2023-GO95MLD-1^06240004.0167306 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
338918142-86780-DETAIL-03_22_2023-SVCWIND-1^06240004.0167341 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
850452241-94680-DETAIL-03_21_2023-GO95MLD-1^06240004.0167342 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
657507920-92170-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0167400 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
404766230-80870-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0167401 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
404766230-80870-DETAIL-04_12_2023-SVCDEFLC-2^06240004.0167401 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
955803518-25670-DETAIL-04_11_2023-GO95HV-1^06240004.0167402 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2028-04-11 | 3
955803518-25670-DETAIL-04_11_2023-GO95MLD-1^06240004.0167402 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
868928573-33480-DETAIL-04_11_2023-SVCENTCO-1^06240004.0167406 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
318312388-59770-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0166901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
33796397-64670-DETAIL-04_12_2023-GO95MLD-1^06240004.0166902 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
30748950-270-DETAIL-04_12_2023-GO95MLD-1^06240004.0167702 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
181798893-993-DETAIL-04_12_2023-GO95MLD-1^06240004.0167703 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
181798893-993-DETAIL-04_12_2023-RISEGRD-1^06240004.0167703 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
372540369-65170-DETAIL-03_28_2023-GO95HV-1^06240004.0167800 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
56243918-93670-DETAIL-04_12_2023-GO95HV-1^06240004.0167900 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
56243918-93670-DETAIL-04_12_2023-GO95TCH-1^06240004.0167900 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
646938453-98880-DETAIL-03_27_2023-GO95HV-1^06240004.0168002 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
501959531-9180-DETAIL-04_10_2023-GO95MLD-1^06240004.0168041 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
501959531-9180-DETAIL-04_10_2023-SVCRUBLG-1^06240004.0168041 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
279024491-79480-DETAIL-04_10_2023-GO95TCH-1^06240004.0168045 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
951220914-3760-DETAIL-03_22_2023-GO95HV-1^06240004.0167143 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
951220914-3760-DETAIL-03_22_2023-GO95MLD-1^06240004.0167143 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
278932831-54080-DETAIL-03_22_2023-SVCDEFLC-2^06240004.0167200 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
395095243-1780-DETAIL-03_22_2023-SVCWIND-1^06240004.0167202 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
516792832-82880-DETAIL-03_22_2023-GO95MLD-1^06240004.0167204 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
577993399-1570-DETAIL-04_11_2023-GO95MLD-1^06240004.0167207 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
598165850-99870-DETAIL-03_22_2023-GO95MLD-1^06240004.0167208 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
598165850-99870-DETAIL-03_22_2023-GUYHINS-1^06240004.0167208 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
102877192-21880-DETAIL-03_27_2023-SVCWIND-1^06240004.0167209 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
452855181-40780-DETAIL-03_22_2023-GO95MLD-1^06240004.0167242 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
774502352-96780-DETAIL-03_27_2023-SVCWIND-1^06240004.0167245 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
358281493-580-DETAIL-03_21_2023-GO95MLD-1^06240004.0167301 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
279024491-79480-DETAIL-04_10_2023-GO95MLD-1^06240004.0168045 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
196210244-97170-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0168046 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
38355002-2880-DETAIL-04_10_2023-GO95HV-1^06240004.0168100 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2028-04-10 | 3
187697492-1980-DETAIL-04_10_2023-GO95MLD-1^06240004.0168104 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
822781140-55170-DETAIL-04_10_2023-GO95MLD-1^06240004.0168106 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
629220837-81837-DETAIL-04_10_2023-GO95MLD-1^06240004.0168109 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
349405651-55380-DETAIL-04_10_2023-GO95MLD-1^06240004.0168142 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
961384991-64780-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0168144 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
200955732-46780-DETAIL-04_10_2023-GO95TCH-1^06240004.0168146 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
326594073-9380-DETAIL-04_10_2023-GO95TCH-1^06240004.0168200 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
326594073-9380-DETAIL-04_10_2023-GUYHINS-1^06240004.0168200 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
258784231-21880-DETAIL-04_10_2023-GO95MLD-1^06240004.0168202 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
92738193-40630-DETAIL-04_19_2023-GO95HV-1^06240004.0172840 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
915879023-26230-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0172942 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
777146113-17130-DETAIL-04_20_2023-GO95MLD-1^06240004.0172943 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
241282521-79580-DETAIL-04_10_2023-SVCWIND-1^06240004.0169044 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
526880731-61680-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0169045 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
526880731-61680-DETAIL-04_10_2023-SVCDEFLC-2^06240004.0169045 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
635450440-8870-DETAIL-04_10_2023-GUYHINS-1^06240004.0169101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
584588073-92680-DETAIL-04_10_2023-GO95MLD-1^06240004.0169102 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
768938633-61880-DETAIL-04_10_2023-GO95MLD-1^06240004.0169108 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
918863281-44780-DETAIL-03_22_2023-GUYHINS-1^06240004.0169143 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
718262203-81130-DETAIL-04_20_2023-GO95MLD-1^06240004.0173940 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
788467624-87503-DETAIL-04_20_2023-GO95MLD-1^06240004.0175900 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
744849581-75730-DETAIL-01_25_2023-SVCDEFLC-1^06240004.0186800 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
438075681-25730-DETAIL-01_25_2023-GO95HV-1^06240004.0186801 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2028-01-25 | 3
265631291-95730-DETAIL-01_25_2023-SVCDEFLC-1^06240004.0186900 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2026-01-25 | 2
854051131-3330-DETAIL-01_23_2023-GO95HV-1^06240004.0188440 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2028-01-23 | 3
957838261-42130-DETAIL-01_23_2023-GO95MLD-1^06240004.0188642 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
275472101-26230-DETAIL-01_23_2023-GO95MLD-1^06240004.0189340 | OTHER | CA-TIER-3 | Distribution | 2023-01-23 | 2026-01-23 | 2
254431831-41630-DETAIL-01_23_2023-GO95MLD-1^06240004.0189703 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2028-01-23 | 3
961896551-18430-DTLSB-05_10_2021-GO95TCH-1^06240004.0200700 | OTHER | CA-TIER-3 | Distribution | 2021-05-10 | 2024-05-10 | 2
616026391-36530-DTLSB-05_06_2021-ABNDEQPM-1^06240004.0204701 | OTHER | CA-TIER-2 | Distribution | 2021-05-06 | 2026-05-06 | 3
657101531-16130-DTLSB-05_10_2021-SVCDEFLC-1^06240004.0207500 | OTHER | CA-TIER-3 | Distribution | 2021-05-10 | 2024-05-10 | 2
672110636-41340-DTLSB-05_10_2021-GO95MLD-1^06240004.0213940 | OTHER | CA-TIER-2 | Distribution | 2021-05-10 | 2024-05-10 | 2
393525851-11730-DETAIL-01_23_2023-SVCDEFLC-1^06240004.0189700 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
961896551-18430-DTLSB-05_10_2021-GO95MLD-1^06240004.0200700 | OTHER | CA-TIER-3 | Distribution | 2021-05-10 | 2024-05-10 | 2
308819706-45989-DTLSB-05_10_2021-GO95TCH-1^06240004.0210802 | OTHER | CA-TIER-2 | Distribution | 2021-05-10 | 2024-05-10 | 2
999436015-39540-DTLSB-05_05_2021-ABNDEQPM-2^06240004.0218900 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2026-05-05 | 3
263056064-55519-ADMIN-07_12_2023-POLEREPL-1^06240008.0298701 | POLE | CA-NON-TIER | Distribution | 2023-07-12 | 2026-07-12 | 2
205772662-32031-DETAIL-02_08_2022-GO95BLTC-1^06241004.0180101 | OTHER | CA-TIER-2 | Distribution | 2022-02-08 | 2027-02-08 | 3
104323982-17031-DETAIL-02_08_2022-GO95TCH-1^06241004.0181200 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2025-02-08 | 2
104323982-17031-DETAIL-02_08_2022-GUYHINS-1^06241004.0181200 | ANCHOR/GUY | CA-TIER-3 | Distribution | 2022-02-08 | 2025-02-08 | 2
799487483-81490-DETAIL-04_25_2023-GO95MLD-1^06241004.0313100 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
702750559-57559-DETAIL-04_25_2023-SVCROAD-1^06241004.0313240 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
953335973-83390-DETAIL-04_25_2023-GO95MLD-1^06241004.0314002 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
866982864-24131-DETAIL-05_10_2022-CLMBHAZ-1^06241005.0010301 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
916477036-80471-DETAIL-05_10_2022-GO95MLD-1^06241005.0012645 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
306440296-13671-DETAIL-05_03_2022-GO95MLD-1^06241005.0012704 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
306440296-13671-DETAIL-05_03_2022-GO95TCH-1^06241005.0012704 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
132133714-19241-DETAIL-05_03_2022-GO95MLD-1^06241005.0012705 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
132133714-19241-DETAIL-05_03_2022-GO95TCH-1^06241005.0012705 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
378767486-29381-DETAIL-05_04_2022-GO95MLD-1^06241005.0012741 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
602271544-9731-DETAIL-05_03_2022-GO95MLD-1^06241005.0012801 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
522749643-78021-DETAIL-05_09_2022-SVCROAD-1^06241005.0013405 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
2185984-97331-DETAIL-05_09_2022-GO95MLD-1^06241005.0013442 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
2185984-97331-DETAIL-05_09_2022-SVCROAD-1^06241005.0013442 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
823275746-94971-DETAIL-05_03_2022-GUYHINS-1^06241005.0013503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
377793804-18631-DETAIL-05_09_2022-GO95MLD-1^06241005.0013506 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
535236715-11832-DETAIL-05_18_2022-RISEBKSP-1^06241005.0026005 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
558287836-50542-DETAIL-05_18_2022-GO95MLD-1^06241005.0026100 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
531459484-69222-DETAIL-05_17_2022-GO95HV-1^06241005.0026203 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
111297244-1022-DETAIL-05_17_2022-GO95HV-1^06241005.0026303 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
178988704-78822-DETAIL-05_17_2022-GO95MLD-1^06241005.0026305 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
410245864-93532-DETAIL-05_17_2022-GO95MLD-1^06241005.0026403 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
502953146-80542-DETAIL-05_17_2022-GUYNOINS-1^06241005.0026404 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
364759195-23632-DETAIL-05_17_2022-GO95GUYP-1^06241005.0026405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
785498078-15042-DETAIL-05_17_2022-GO95MLD-1^06241005.0026406 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
185148080-64052-DETAIL-05_17_2022-GO95MLD-1^06241005.0026441 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
185148080-64052-DETAIL-05_17_2022-SVCROOF-1^06241005.0026441 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
188486073-75161-DETAIL-05_17_2022-SVCWIND-1^06241005.0026504 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
661290846-41542-DETAIL-05_16_2022-CLMBHAZ-1^06241005.0027202 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
661290846-41542-DETAIL-05_16_2022-GO95MLD-1^06241005.0027202 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
520540844-8032-DETAIL-05_16_2022-GO95TCH-1^06241005.0027203 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
91852328-58752-DETAIL-05_16_2022-GO95TCH-1^06241005.0027204 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
722239785-97532-DETAIL-05_16_2022-GO95MLD-1^06241005.0027206 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
18482708-44708-DETAIL-05_16_2022-SVCROOF-1^06241005.0027210 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
508258209-63052-DETAIL-05_16_2022-SVCENTCO-1^06241005.0027244 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
340993429-68052-DETAIL-05_16_2022-GO95MLD-1^06241005.0027245 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
382650055-85232-DETAIL-05_16_2022-ABNDEQPM-1^06241005.0027400 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
604088376-25742-DETAIL-05_17_2022-GO95HV-1^06241005.0027403 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
259920953-2361-DETAIL-05_12_2022-GO95MLD-1^06241005.0027840 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
353915092-76241-DETAIL-05_12_2022-GO95MLD-1^06241005.0027902 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
818338265-23332-DETAIL-05_16_2022-GUYHINS-1^06241005.0028405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
244106715-86032-DETAIL-05_16_2022-GO95HV-1^06241005.0028406 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
244106715-86032-DETAIL-05_16_2022-GO95TCH-1^06241005.0028406 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
208796080-8352-DETAIL-05_10_2022-GO95TCH-1^06241005.0028440 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
208796080-8352-DETAIL-05_10_2022-SVCROOF-1^06241005.0028440 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
208796080-8352-DETAIL-05_10_2022-SVCWIND-1^06241005.0028440 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
112637070-16352-DETAIL-05_10_2022-GO95MLD-1^06241005.0028442 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
562703182-26241-DETAIL-05_12_2022-GUYHINS-1^06241005.0028801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
534768972-15241-DETAIL-05_12_2022-GO95MLD-1^06241005.0028902 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
756059522-52241-DETAIL-05_12_2022-GO95MLD-1^06241005.0028903 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
187024132-42641-DETAIL-05_12_2022-GO95TCH-1^06241005.0028904 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
599642919-79852-DETAIL-05_12_2022-LIGHT-1^06241005.0029001 | CONNECTION DEVICE | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
342719733-40121-DETAIL-06_06_2022-GO95MLD-1^06241005.0059304 | OTHER | CA-TIER-2 | Distribution | 2022-06-06 | 2027-06-06 | 3
398986349-27841-DETAIL-06_01_2022-GO95MLD-1^06241005.0091001 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
955265359-43251-DETAIL-06_01_2022-GO95MLD-1^06241005.0092001 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
400799330-52571-DETAIL-06_01_2022-GO95BLTC-1^06241005.0092102 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
400799330-52571-DETAIL-06_01_2022-GO95TCH-1^06241005.0092102 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
693801949-40041-DETAIL-06_01_2022-GO95BLTC-1^06241005.0092201 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
693801949-40041-DETAIL-06_01_2022-GO95BLTC-2^06241005.0092201 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
327967990-9861-DETAIL-06_01_2022-GO95HV-1^06241005.0092304 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
434744629-46021-DETAIL-06_01_2022-GO95HV-1^06241005.0092401 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
528411029-42452-DETAIL-05_16_2022-GUYHINS-1^06241005.0027142 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
99907490-99352-DETAIL-05_16_2022-GUYHINS-1^06241005.0027143 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
99907490-99352-DETAIL-05_16_2022-SVCWIND-1^06241005.0027143 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
882579839-10352-DETAIL-05_16_2022-GO95MLD-1^06241005.0027144 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
44458140-68852-DETAIL-05_18_2022-GO95MLD-1^06241005.0028242 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
44458140-68852-DETAIL-05_18_2022-GO95TCH-1^06241005.0028242 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
159463329-34329-DETAIL-01_27_2022-GO95BLTC-1^06241005.0117609 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2027-01-27 | 3
587210352-87684-DETAIL-01_27_2022-GUYHINS-4^06241005.0117611 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
284409200-92032-DETAIL-01_10_2022-SVCENTCO-1^06241005.0117703 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
304011808-13808-DETAIL-01_10_2022-GO95MLD-1^06241005.0117704 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
304011808-13808-DETAIL-01_10_2022-SVCWIND-1^06241005.0117704 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
325428740-72532-AUDIT-02_03_2022-GUYNOINS-1^06241005.0117705 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-02-03 | 2025-02-03 | 2
501994201-26632-DETAIL-01_10_2022-GO95HV-1^06241005.0117707 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2027-01-10 | 3
95792214-8912-DETAIL-01_26_2022-SVCROOF-1^06241005.0118303 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
836361064-26312-DETAIL-01_26_2022-GO95MLD-1^06241005.0118304 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
228137744-48622-DETAIL-01_26_2022-SVCENTCO-1^06241005.0118403 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
781617354-24722-DETAIL-01_26_2022-GO95TCH-1^06241005.0119400 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
877003933-32302-DETAIL-01_26_2022-GO95MLD-1^06241005.0119402 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
877003933-32302-DETAIL-01_26_2022-GO95TCH-1^06241005.0119402 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
469233321-27452-DETAIL-01_26_2022-GO95MLD-1^06241005.0119403 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
442470390-16832-DETAIL-01_26_2022-GO95MLD-1^06241005.0119500 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
442470390-16832-DETAIL-01_26_2022-SVCRUBLG-1^06241005.0119500 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
198040674-59922-DETAIL-01_20_2022-GO95MLD-1^06241005.0119700 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
203113891-97152-DETAIL-01_20_2022-GO95MLD-1^06241005.0119803 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
754472418-74902-DETAIL-01_27_2022-GO95TCH-1^06241005.0120200 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
451071137-74742-DETAIL-01_20_2022-GO95HV-1^06241005.0121101 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2027-01-20 | 3
451071137-74742-DETAIL-01_20_2022-GO95MLD-1^06241005.0121101 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
722035805-16442-DETAIL-01_20_2022-GO95HV-1^06241005.0121202 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2027-01-20 | 3
8546859-55791-DETAIL-01_10_2022-POLESTEP-1^06241005.0157102 | POLE | CA-TIER-3 | Distribution | 2022-01-10 | 2025-01-10 | 2
118095679-24191-DETAIL-01_10_2022-GO95MLD-1^06241005.0157200 | OTHER | CA-TIER-3 | Distribution | 2022-01-10 | 2027-01-10 | 3
624446210-70611-DETAIL-01_10_2022-GO95MLD-1^06241005.0157500 | OTHER | CA-TIER-3 | Distribution | 2022-01-10 | 2025-01-10 | 2
435627889-2191-DETAIL-01_10_2022-GO95MLD-1^06241005.0158501 | OTHER | CA-TIER-3 | Distribution | 2022-01-10 | 2025-01-10 | 2
435627889-2191-DETAIL-01_10_2022-GRDRODHI-1^06241005.0158501 | OTHER | CA-TIER-3 | Distribution | 2022-01-10 | 2025-01-10 | 2
949446307-19418-DETAIL-01_13_2022-GRDRODHI-1^06241005.0169600 | OTHER | CA-TIER-3 | Distribution | 2022-01-13 | 2025-01-13 | 2
569752290-44011-DETAIL-01_11_2022-GO95MLD-1^06241005.0224901 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2027-01-11 | 3
720202301-85179-DETAIL-01_10_2022-POLESTEP-1^06241005.0225801 | POLE | CA-TIER-3 | Distribution | 2022-01-10 | 2025-01-10 | 2
994588711-41811-DETAIL-01_10_2022-GO95MLD-1^06241005.0226700 | OTHER | CA-TIER-3 | Distribution | 2022-01-10 | 2025-01-10 | 2
708636791-20321-DETAIL-01_11_2022-GO95MLD-1^06241005.0228600 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2025-01-11 | 2
330917121-73121-DETAIL-01_11_2022-GO95MLD-1^06241005.0229101 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2025-01-11 | 2
787676235-2661-DETAIL-02_08_2022-GO95HV-1^06241005.0230200 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
502414774-51961-DETAIL-02_07_2022-GRDRODHI-1^06241005.0230700 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
657879593-98030-AUDIT-07_05_2023-GUYNOINS-1^06241005.0255200 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
479923836-56401-DETAIL-05_04_2023-GO95MLD-1^06241005.0255601 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2028-05-04 | 3
531208836-83501-DETAIL-05_04_2023-GO95MLD-1^06241005.0255602 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2028-05-04 | 3
47537374-89630-DETAIL-04_27_2023-GO95HV-1^06241005.0255903 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2028-04-27 | 3
303507738-69050-DETAIL-04_27_2023-GO95MLD-1^06241005.0255940 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
614961934-18930-DETAIL-04_27_2023-GO95MLD-1^06241005.0256441 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
32021036-9511-DETAIL-04_27_2023-GO95MLD-1^06241005.0256702 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
23113424-74930-DETAIL-04_27_2023-GRDRODHI-1^06241005.0257440 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
286116949-1320-DETAIL-01_26_2023-GO95MLD-1^06241005.0260206 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2028-01-26 | 3
483513959-37510-DETAIL-01_26_2023-SVCDEFLC-1^06241005.0262200 | OTHER | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
961932539-13610-DETAIL-01_26_2023-GO95MLD-1^06241005.0262203 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2026-01-26 | 2
420340389-33010-DETAIL-01_26_2023-GO95BLTC-1^06241005.0262204 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2028-01-26 | 3
913605953-69802-DETAIL-01_26_2022-GO95MLD-1^06241005.0119401 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
877003933-32302-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0119402 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
174319523-3002-DETAIL-01_26_2022-GO95MLD-1^06241005.0119405 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
349650471-45042-DETAIL-01_26_2022-GO95MLD-1^06241005.0119502 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
315936651-60942-DETAIL-01_20_2022-GO95MLD-1^06241005.0119801 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
118788699-2799-DETAIL-01_20_2022-GO95MLD-1^06241005.0119802 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
492325451-51242-DETAIL-01_20_2022-GO95MLD-1^06241005.0119804 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
336128298-74702-DETAIL-01_27_2022-ABNDEQPM-1^06241005.0120100 | OTHER | CA-TIER-3 | Distribution | 2022-01-27 | 2027-01-27 | 3
632275384-90789-DETAIL-01_27_2022-POLESTEP-1^06241005.0120103 | POLE | CA-TIER-3 | Distribution | 2022-01-27 | 2025-01-27 | 2
727746605-13342-DETAIL-01_20_2022-GO95MLD-1^06241005.0121300 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
895889007-38138-DETAIL-01_20_2022-GO95MLD-1^06241005.0121302 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2027-01-20 | 3
354032245-44142-DETAIL-01_20_2022-GO95MLD-1^06241005.0121303 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
824887234-79234-DETAIL-05_11_2022-GUYHINS-1^06241005.0130507 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
824887234-79234-AUDIT-06_07_2022-GUYHINS-1^06241005.0130507 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-07 | 2025-06-07 | 2
601668053-12051-DETAIL-05_05_2022-GO95TCH-1^06241005.0130700 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
432153515-24489-DETAIL-08_05_2021-XARMSPCR-1^06241009.0238900 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-05 | 2024-08-05 | 2
532517879-12309-DETAIL-04_07_2021-GO95MLD-1^06241009.0281500 | OTHER | CA-TIER-2 | Distribution | 2021-04-07 | 2026-04-07 | 3
493884668-79019-DETAIL-04_08_2021-GO95MLD-1^06241009.0297000 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
414035328-24019-DETAIL-12_01_2023-POLEREPL-1^06241009.0298200 | POLE | CA-TIER-2 | Distribution | 2023-12-01 | 2024-12-01 | 2
856486918-55489-DETAIL-04_07_2021-GO95MLD-1^06241009.0299401 | OTHER | CA-TIER-2 | Distribution | 2021-04-07 | 2026-04-07 | 3
326773098-20089-DETAIL-04_12_2021-GO95MLD-1^06241009.0324301 | OTHER | CA-TIER-2 | Distribution | 2021-04-12 | 2026-04-12 | 3
468592623-65649-DETAIL-05_05_2022-GO95MLD-1^06241005.0130704 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
143064089-31581-DETAIL-01_11_2022-GO95HV-1^06241005.0153300 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2027-01-11 | 3
589542509-34091-DETAIL-01_11_2022-SVCENTCO-1^06241005.0153400 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2025-01-11 | 2
627260049-89871-DETAIL-01_11_2022-POLESTEP-1^06241005.0153503 | POLE | CA-TIER-3 | Distribution | 2022-01-11 | 2025-01-11 | 2
404371109-85281-DETAIL-01_27_2022-RISEGRD-1^06241005.0153800 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
375001339-49981-DETAIL-01_11_2022-GO95MLD-1^06241005.0154000 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2025-01-11 | 2
977339789-8391-DETAIL-01_10_2022-GO95MLD-1^06241005.0157300 | OTHER | CA-TIER-3 | Distribution | 2022-01-10 | 2027-01-10 | 3
906556828-33651-DETAIL-01_13_2022-GO95MLD-1^06241005.0163900 | OTHER | CA-TIER-2 | Distribution | 2022-01-13 | 2025-01-13 | 2
264347698-75341-DETAIL-01_13_2022-GO95HV-1^06241005.0169601 | OTHER | CA-TIER-3 | Distribution | 2022-01-13 | 2027-01-13 | 3
581929061-50521-DETAIL-01_11_2022-ABNDEQPM-1^06241005.0229600 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2027-01-11 | 3
78078381-27121-DETAIL-02_08_2022-GO95HV-1^06241005.0230302 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
78078381-27121-DETAIL-02_08_2022-GO95MLD-1^06241005.0230302 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
614239844-83861-DETAIL-02_07_2022-GO95MLD-1^06241005.0230701 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
149012743-18141-DETAIL-06_16_2022-COPLLEAN-1^06242005.0193101 | POLE | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
149012743-18141-DETAIL-06_16_2022-GO95MLD-1^06242005.0193101 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
149012743-18141-DETAIL-06_16_2022-GO95STUB-1^06242005.0193101 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
435870323-80041-DETAIL-06_16_2022-GUYNOINS-1^06242005.0196000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
435870323-80041-DETAIL-06_16_2022-GUYNOINS-2^06242005.0196000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
995790074-88461-DETAIL-06_23_2022-GO95HV-1^06242005.0199700 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
465265264-65161-DTLSB-07_26_2022-GO95HV-1^06242005.0200501 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2027-07-26 | 3
57950444-58061-DTLSB-07_26_2022-GO95MLD-1^06242005.0202500 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2025-07-26 | 2
635565664-17861-DTLSB-08_02_2022-RISEGRD-1^06242005.0202700 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
467795914-74830-DETAIL-05_02_2023-GO95MLD-1^06241005.0252142 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
826168879-39879-DETAIL-05_03_2023-GO95MLD-1^06241005.0252200 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
828854553-63130-DETAIL-05_03_2023-GO95HV-1^06241005.0252400 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
578374114-2230-DETAIL-05_02_2023-GO95MLD-1^06241005.0363702 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2028-05-02 | 3
142079978-7113-DTLSB-07_20_2022-SVCROOF-1^06242005.0283504 | OTHER | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
830383888-57113-DTLSB-07_20_2022-GO95MLD-1^06242005.0283603 | OTHER | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
659756428-16213-DTLSB-07_20_2022-GO95MLD-1^06242005.0284400 | OTHER | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
450958568-64113-DTLSB-07_20_2022-GUYNOINS-1^06242005.0284500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
450958568-64113-DTLSB-07_20_2022-GUYNOINS-2^06242005.0284500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
856530555-86602-DETAIL-06_09_2022-GO95MLD-1^06242005.0290200 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2025-06-09 | 2
815529126-2742-DETAIL-06_09_2022-GO95MLD-1^06242005.0293000 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2025-06-09 | 2
48191526-33642-DETAIL-06_09_2022-GO95TCH-1^06242005.0293001 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2025-06-09 | 2
738703919-93919-DETAIL-06_09_2022-GO95HV-1^06242005.0293030 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2027-06-09 | 3
770319745-40669-DETAIL-06_16_2022-GO95MLD-1^06242005.0308502 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
11203265-12902-DETAIL-06_09_2022-GO95HV-1^06242005.0309200 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2027-06-09 | 3
413384528-93919-DETAIL-08_02_2021-GO95MLD-1^06241008.0072001 | OTHER | CA-NON-TIER | Distribution | 2021-08-02 | 2026-08-02 | 3
976100356-85356-DETAIL-05_24_2022-SVCENTCO-1^06242005.0355030 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
486001863-71751-DETAIL-05_24_2022-GO95MLD-1^06242005.0356002 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
496105513-72551-DETAIL-05_24_2022-GUYNOINS-1^06242005.0356004 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
74354263-55351-DETAIL-05_24_2022-GO95MLD-1^06242005.0356006 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
58105693-67471-DETAIL-05_24_2022-GO95MLD-1^06242005.0356040 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
245953223-67361-DETAIL-05_24_2022-SVCROAD-1^06242005.0356101 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
246698773-91971-DETAIL-05_24_2022-GO95MLD-1^06242005.0356140 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
627916433-69651-DETAIL-05_24_2022-SVCWIND-1^06242005.0357002 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
498801633-79551-DETAIL-05_24_2022-GO95MLD-1^06242005.0358000 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
71305783-46461-DETAIL-05_24_2022-GO95HV-1^06242005.0358003 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2027-05-24 | 3
71305783-46461-DETAIL-05_24_2022-GO95MLD-1^06242005.0358003 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
288124444-54319-DETAIL-08_02_2021-GUYNOINS-1^06241009.0116700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2021-08-02 | 2024-08-02 | 2
551756571-38319-DETAIL-08_02_2021-SVCWIND-1^06241009.0120501 | OTHER | CA-NON-TIER | Distribution | 2021-08-02 | 2024-08-02 | 2
908949445-51699-DETAIL-04_07_2021-GO95MLD-1^06241009.0151501 | OTHER | CA-TIER-2 | Distribution | 2021-04-07 | 2026-04-07 | 3
896145353-93769-DETAIL-04_07_2021-GO95MLD-1^06241009.0155901 | OTHER | CA-NON-TIER | Distribution | 2021-04-07 | 2026-04-07 | 3
887689684-6619-DETAIL-04_07_2021-XARMSPCR-1^06241009.0156502 | CROSSARM | CA-NON-TIER | Distribution | 2021-04-07 | 2024-04-07 | 2
524844393-18519-ADMIN-08_21_2023-POLEREPL-1^06241009.0216100 | POLE | CA-TIER-2 | Distribution | 2023-08-21 | 2024-08-21 | 2
990274774-21619-DETAIL-07_27_2021-POLETOP-1^06241009.0223101 | POLE | CA-NON-TIER | Distribution | 2021-07-27 | 2024-07-27 | 2
789097839-56919-DETAIL-08_05_2021-XARMSPCR-1^06241009.0254000 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-05 | 2024-08-05 | 2
297177738-14019-DETAIL-04_08_2021-GO95MLD-1^06241009.0298003 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
533190035-49369-DETAIL-02_03_2021-GO95MLD-1^06242009.0050101 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
131865485-16769-DETAIL-02_03_2021-GO95MLD-1^06242009.0051102 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
765254795-98119-DETAIL-02_03_2021-GO95HV-1^06242009.0051201 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
852811545-69769-DETAIL-02_03_2021-GO95MLD-1^06242009.0052101 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
86299555-219-DETAIL-02_03_2021-GO95TCH-1^06242009.0054000 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2024-02-03 | 2
537508344-5219-DETAIL-02_03_2021-GO95TCH-1^06242009.0055301 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2024-02-03 | 2
130499965-84219-DETAIL-02_03_2021-GO95HV-1^06242009.0055402 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
180752504-59219-DETAIL-02_08_2021-GO95TCH-1^06242009.0055501 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
488880014-41319-DETAIL-02_08_2021-GO95HV-1^06242009.0055701 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
380581907-39919-DETAIL-02_08_2021-GO95TCH-1^06242009.0065700 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
672004998-20969-DETAIL-02_03_2021-GO95MLD-1^06242009.0066000 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
249790488-69869-DETAIL-02_03_2021-GO95MLD-1^06242009.0066102 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
104258388-28869-DETAIL-02_03_2021-GO95MLD-1^06242009.0066103 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2024-02-03 | 2
453627908-32019-DETAIL-02_08_2021-GO95MLD-1^06242009.0066503 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
633207637-48019-DETAIL-02_08_2021-GUYNOINS-1^06242009.0066600 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
656298228-23019-DETAIL-02_08_2021-GO95HV-1^06242009.0066701 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
709480918-70741-DETAIL-02_08_2021-GO95MLD-1^06242009.0067500 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
709480918-70741-DETAIL-02_08_2021-GO95TCH-1^06242009.0067500 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
558069874-66469-DETAIL-02_05_2021-GO95HV-1^06242009.0119703 | OTHER | CA-TIER-2 | Distribution | 2021-02-05 | 2026-02-05 | 3
369923174-51399-DETAIL-02_05_2021-SVCWIND-1^06242009.0120501 | OTHER | CA-NON-TIER | Distribution | 2021-02-05 | 2024-02-05 | 2
262772734-51119-DETAIL-02_10_2021-GO95MLD-1^06242009.0208701 | OTHER | CA-NON-TIER | Distribution | 2021-02-10 | 2026-02-10 | 3
351321384-70119-ADMIN-08_02_2023-POLEREPL-1^06242009.0209703 | POLE | CA-NON-TIER | Distribution | 2023-08-02 | 2026-08-02 | 2
235981961-56819-ADMIN-08_02_2023-POLEREPL-1^06242009.0220502 | POLE | CA-NON-TIER | Distribution | 2023-08-02 | 2026-08-02 | 2
785531800-12279-ADMIN-08_02_2023-POLEREPL-1^06242009.0220600 | POLE | CA-NON-TIER | Distribution | 2023-08-02 | 2026-08-02 | 2
73964028-53913-DTLSB-07_20_2022-GO95MLD-1^06242005.0284101 | OTHER | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
798049819-23913-DTLSB-07_20_2022-GO95MLD-1^06242005.0286240 | OTHER | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
551708455-55602-DETAIL-06_09_2022-GO95HV-1^06242005.0290100 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2027-06-09 | 3
856530555-86602-DETAIL-06_09_2022-GO95HV-1^06242005.0290200 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2027-06-09 | 3
194642418-76998-DETAIL-06_09_2022-GO95HV-1^06242005.0292000 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2027-06-09 | 3
890234153-99151-DETAIL-05_24_2022-GO95MLD-1^06242005.0356104 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
502588683-19261-DETAIL-05_24_2022-GO95MLD-1^06242005.0356108 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
814343413-94561-DETAIL-05_24_2022-GO95MLD-1^06242005.0356201 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
332751923-70161-DETAIL-05_24_2022-GO95MLD-1^06242005.0357000 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
627916433-69651-DETAIL-05_24_2022-SVCROOF-1^06242005.0357002 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
616379223-58551-DETAIL-05_24_2022-GO95MLD-1^06242005.0357005 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
759297119-84912-AUDIT-06_14_2022-GO95HV-1^06242005.0361000 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2027-06-14 | 3
780126299-78812-DETAIL-05_25_2022-GO95MLD-1^06242005.0361001 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
313745004-64162-DETAIL-05_25_2022-GO95MLD-1^06242005.0361040 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
470574894-56062-DETAIL-05_25_2022-SVCWIND-1^06242005.0361042 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
448063308-49129-DETAIL-08_03_2021-ENCHRW-1^06242009.0281202 | OTHER | CA-NON-TIER | Distribution | 2021-08-03 | 2024-08-03 | 2
42797478-76919-DETAIL-08_11_2021-XARMSPCR-1^06242009.0284502 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-11 | 2024-08-11 | 2
496032216-25062-DETAIL-05_23_2022-SVCENTBK-1^06242005.0369500 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
712816766-93852-DETAIL-05_23_2022-SVCWIND-2^06242005.0369601 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
982120135-62714-DETAIL-05_23_2022-GO95HV-1^06242005.0369640 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2027-05-23 | 3
55056834-6112-DETAIL-06_16_2022-GO95MLD-1^06242006.0243800 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
176143424-58512-DETAIL-06_16_2022-GO95MLD-1^06242006.0244801 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
888889414-89129-DETAIL-06_16_2022-GO95MLD-1^06242006.0245701 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
194361014-29129-DETAIL-06_16_2022-SVCENTCO-1^06242006.0246600 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
173666014-98129-DETAIL-06_16_2022-GO95HV-1^06242006.0246601 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2027-06-16 | 3
251235071-91079-DETAIL-02_16_2021-GO95MLD-1^06242008.0176400 | OTHER | CA-TIER-2 | Distribution | 2021-02-16 | 2026-02-16 | 3
446334491-69119-DETAIL-08_24_2021-GO95HV-1^06242008.0190800 | OTHER | CA-NON-TIER | Distribution | 2021-08-24 | 2026-08-24 | 3
624987804-67319-DETAIL-02_10_2021-ABNDEQPM-1^06242009.0028802 | OTHER | CA-TIER-2 | Distribution | 2021-02-10 | 2026-02-10 | 3
600222590-89529-DTLSB-09_06_2022-GO95MLD-1^06243004.0066300 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
698454613-65719-AUDIT-03_09_2021-XARMSPCR-1^06242009.0038400 | CROSSARM | CA-NON-TIER | Distribution | 2021-03-09 | 2024-03-09 | 2
466364549-86619-DETAIL-02_09_2021-GO95HV-1^06242009.0041200 | OTHER | CA-TIER-2 | Distribution | 2021-02-09 | 2026-02-09 | 3
108674915-2099-DETAIL-02_03_2021-GO95MLD-1^06242009.0050200 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
108674915-2099-DETAIL-02_03_2021-GO95TCH-1^06242009.0050200 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2024-02-03 | 2
193259725-47499-DETAIL-02_03_2021-GO95MLD-1^06242009.0051101 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
765254795-98119-DETAIL-02_03_2021-GO95MLD-1^06242009.0051201 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
258769675-41219-DETAIL-02_03_2021-GO95HV-1^06242009.0052100 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
86299555-219-DETAIL-02_03_2021-GO95MLD-1^06242009.0054000 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
639366601-24342-DTLSB-09_06_2022-GO95HV-1^06243004.0069501 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2027-09-06 | 3
8251094-91094-DTLSB-08_24_2022-GO95MLD-1^06243004.0070301 | OTHER | CA-TIER-2 | Distribution | 2022-08-24 | 2025-08-24 | 2
217679432-87989-DTLSB-08_23_2022-GO95HV-1^06243004.0073400 | OTHER | CA-TIER-2 | Distribution | 2022-08-23 | 2027-08-23 | 3
465553662-23552-DTLSB-08_10_2022-ABNDEQPM-1^06243004.0075301 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2027-08-10 | 3
497233915-72219-DETAIL-02_02_2021-GRDRODHI-1^06242009.0059204 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
889060498-98919-DETAIL-02_08_2021-GO95HV-1^06242009.0064700 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
605696348-61019-DETAIL-02_08_2021-GO95MLD-1^06242009.0066504 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
423080058-82019-DETAIL-02_08_2021-GO95MLD-1^06242009.0066601 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
710385137-8019-DETAIL-02_08_2021-GO95HV-1^06242009.0066603 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
325829768-19469-DETAIL-02_03_2021-GO95HV-1^06242009.0067102 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
418191487-35599-DTLSB-08_29_2022-GO95TCH-1^06243004.0100200 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
220990968-13329-DTLSB-08_29_2022-GO95HV-1^06243004.0100701 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2027-08-29 | 3
220990968-13329-DTLSB-08_29_2022-GO95MLD-1^06243004.0100701 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
714842678-31499-DTLSB-08_29_2022-GO95MLD-1^06243004.0100801 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
795620607-50429-DTLSB-08_29_2022-GO95MLD-1^06243004.0101402 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
779825258-88979-DTLSB-08_29_2022-GO95MLD-1^06243004.0105300 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
784736177-99229-DTLSB-08_24_2022-GO95HV-1^06243004.0106000 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2027-08-24 | 3
784736177-99229-DTLSB-08_24_2022-GO95MLD-1^06243004.0106000 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
364897177-92429-DTLSB-08_24_2022-GO95HV-1^06243004.0106001 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2027-08-24 | 3
552437767-13429-DTLSB-08_24_2022-GO95HV-1^06243004.0106003 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2027-08-24 | 3
399811315-6569-DETAIL-02_08_2021-GO95MLD-1^06242009.0084400 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
35025583-48869-DETAIL-02_08_2021-GUYNOINS-1^06242009.0085000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
554710177-10079-DTLSB-08_24_2022-GO95MLD-1^06243004.0156901 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
517328518-58499-DTLSB-08_25_2022-RISEGRD-1^06243004.0157900 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2025-08-25 | 2
273995729-91039-DTLSB-08_01_2022-CONDCOIL-1^06243004.0160700 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
55260409-5899-DTLSB-08_01_2022-GO95MLD-1^06243004.0162700 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
824412219-63379-DTLSB-08_01_2022-GO95MLD-1^06243004.0163641 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
389888669-26929-DTLSB-07_28_2022-GO95MLD-1^06243004.0165500 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
389888669-26929-DTLSB-07_28_2022-GRDRODHI-1^06243004.0165500 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
718627219-3929-DTLSB-08_03_2022-GO95HV-1^06243004.0166201 | OTHER | CA-NON-TIER | Distribution | 2022-08-03 | 2027-08-03 | 3
424857559-14929-DTLSB-07_28_2022-GO95HV-1^06243004.0166401 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2027-07-28 | 3
918207049-12342-DTLSB-07_28_2022-GO95MLD-1^06243004.0166700 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
673955979-40689-DTLSB-07_28_2022-GO95MLD-1^06243004.0167501 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
616272872-56872-DTLSB-07_28_2022-GO95HV-1^06243004.0168601 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2027-07-28 | 3
243797675-10775-DTLSB-07_28_2022-GO95MLD-1^06243004.0168602 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
506439499-37189-DTLSB-08_10_2022-GO95MLD-1^06243004.0174001 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
547689979-6729-DTLSB-08_10_2022-GO95HV-1^06243004.0176000 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2027-08-10 | 3
496867709-75269-DTLSB-08_10_2022-GO95MLD-1^06243004.0176301 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
437794305-61143-DTLSB-08_09_2022-GO95HV-1^06243004.0177041 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2027-08-09 | 3
893597939-47829-DTLSB-08_10_2022-CONDCOIL-1^06243004.0177200 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
454782229-19479-DTLSB-08_01_2022-GO95MLD-1^06243004.0177401 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
669344019-5829-DTLSB-08_01_2022-GUYSLACK-1^06243004.0177700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
372719279-10269-DTLSB-08_01_2022-GO95MLD-1^06243004.0178502 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
719936999-75889-DTLSB-08_08_2022-GO95MLD-1^06243004.0178900 | OTHER | CA-NON-TIER | Distribution | 2022-08-08 | 2025-08-08 | 2
232430408-49829-DTLSB-07_19_2022-GRDRODHI-1^06243004.0190000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
107267408-20929-DTLSB-07_19_2022-GO95MLD-1^06243004.0191000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
680629528-60929-DTLSB-06_30_2022-GO95MLD-1^06243004.0192000 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2025-06-30 | 2
982756848-64669-DTLSB-06_30_2022-GO95MLD-1^06243004.0192300 | OTHER | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
596996889-64089-DTLSB-08_04_2022-GRDRODHI-2^06243004.0212201 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2025-08-04 | 2
658140789-32139-DTLSB-08_03_2022-XARMSPCR-1^06243004.0214802 | CROSSARM | CA-NON-TIER | Distribution | 2022-08-03 | 2025-08-03 | 2
658140789-32139-DTLSB-08_03_2022-XARMSPCR-2^06243004.0214802 | CROSSARM | CA-NON-TIER | Distribution | 2022-08-03 | 2025-08-03 | 2
666600660-16039-DTLSB-08_09_2022-GO95MLD-1^06243004.0219400 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
30907650-53099-DTLSB-08_09_2022-GO95MLD-1^06243004.0219401 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
792580589-67339-DTLSB-08_25_2022-XARMSPCR-1^06243004.0233501 | CROSSARM | CA-NON-TIER | Distribution | 2022-08-25 | 2025-08-25 | 2
838711869-36339-DTLSB-08_23_2022-GO95MLD-1^06243004.0234200 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
448836338-45038-DTLSB-08_23_2022-GO95MLD-1^06243004.0234201 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
69196889-19989-DTLSB-08_22_2022-GO95MLD-1^06243004.0235700 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2025-08-22 | 2
377067479-9779-DTLSB-08_22_2022-ABNDEQPM-1^06243004.0236703 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2027-08-22 | 3
563204839-42389-DTLSB-08_23_2022-GO95MLD-1^06243004.0237103 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
872963219-61889-DTLSB-08_23_2022-GO95BLTC-1^06243004.0237200 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2027-08-23 | 3
324272919-32089-DTLSB-09_06_2022-GO95MLD-1^06243004.0065500 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
569206351-76539-DTLSB-08_09_2022-GO95MLD-1^06243004.0283800 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
702791551-73389-DTLSB-08_04_2022-GO95MLD-1^06243004.0283801 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2025-08-04 | 2
860308751-7539-DTLSB-08_04_2022-GO95HV-1^06243004.0283900 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2027-08-04 | 3
843343951-37539-DTLSB-08_04_2022-GO95HV-1^06243004.0283901 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2027-08-04 | 3
41250351-74099-DTLSB-08_09_2022-GO95MLD-1^06243004.0284000 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
489905471-49439-DTLSB-08_09_2022-GO95HV-1^06243004.0284040 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2027-08-09 | 3
64716741-77539-DTLSB-08_04_2022-ABNDEQPM-1^06243004.0284903 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2027-08-04 | 3
90228151-57489-DTLSB-08_09_2022-GO95MLD-1^06243004.0285000 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
847102870-79279-DTLSB-09_06_2022-GO95MLD-1^06243004.0066200 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
286074240-49529-DTLSB-09_06_2022-GO95MLD-1^06243004.0066203 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2027-09-06 | 3
753930061-41242-DTLSB-08_31_2022-GO95MLD-1^06243004.0066642 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
459722838-54758-DTLSB-08_30_2022-GO95MLD-1^06243004.0090800 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
636009687-26329-DTLSB-08_30_2022-GO95HV-1^06243004.0090901 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2027-08-30 | 3
677075678-35329-DTLSB-08_30_2022-GO95MLD-1^06243004.0092900 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
926329241-58539-DTLSB-08_04_2022-GO95MLD-1^06243004.0285900 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2025-08-04 | 2
565264091-97799-DTLSB-08_08_2022-GO95HV-1^06243004.0286240 | OTHER | CA-NON-TIER | Distribution | 2022-08-08 | 2027-08-08 | 3
565264091-97799-DTLSB-08_08_2022-GO95MLD-1^06243004.0286240 | OTHER | CA-NON-TIER | Distribution | 2022-08-08 | 2025-08-08 | 2
252676461-59309-AUDIT-11_01_2022-GO95BLTC-1^06243004.0286903 | OTHER | CA-NON-TIER | Distribution | 2022-11-01 | 2025-11-01 | 2
191762349-98539-DTLSB-08_04_2022-GO95HV-1^06243004.0286904 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2027-08-04 | 3
19637661-83639-DTLSB-07_18_2022-GO95MLD-1^06243004.0302401 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
675438161-64639-DTLSB-07_21_2022-GO95MLD-1^06243004.0302403 | OTHER | CA-TIER-2 | Distribution | 2022-07-21 | 2025-07-21 | 2
707692103-37369-DTLSB-06_30_2022-GO95MLD-1^06243004.0302800 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2027-06-30 | 3
514342971-63639-DTLSB-07_18_2022-GO95MLD-1^06243004.0303401 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2027-07-18 | 3
822374034-4699-DTLSB-09_07_2022-GRDRODHI-1^06243005.0010101 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
115404717-93329-DTLSB-08_30_2022-GO95MLD-1^06243004.0097900 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
409335949-51169-DTLSB-09_08_2022-GO95MLD-1^06243004.0098700 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
367622987-10199-DTLSB-08_30_2022-GO95MLD-1^06243004.0099501 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
367622987-10199-DTLSB-08_30_2022-SVCENTCO-1^06243004.0099501 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
359614807-9329-DTLSB-08_30_2022-GUYNOINS-1^06243004.0099601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
418191487-35599-DTLSB-08_29_2022-GO95MLD-1^06243004.0100200 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
513759398-77402-DTLSB-08_29_2022-GO95MLD-1^06243004.0100800 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
369733027-71429-DTLSB-08_24_2022-GO95HV-1^06243004.0103200 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2027-08-24 | 3
595728487-51329-DTLSB-08_24_2022-GO95MLD-1^06243004.0105200 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
578917767-82429-DTLSB-08_24_2022-GUYNOINS-1^06243004.0106002 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
578917767-82429-DTLSB-08_24_2022-GUYNOINS-2^06243004.0106002 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
17333152-49828-DTLSB-08_24_2022-GO95HV-1^06243004.0106300 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2027-08-24 | 3
853583544-95839-DTLSB-09_08_2022-GUYNOINS-1^06243005.0037300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
532264959-45959-DTLSB-09_27_2022-GO95MLD-1^06243005.0037700 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
104089095-8689-DTLSB-09_08_2022-GO95MLD-1^06243005.0038001 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
596667865-69979-DTLSB-09_08_2022-GO95MLD-1^06243005.0038100 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
596667865-69979-DTLSB-09_08_2022-GRDRODHI-1^06243005.0038100 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
538709674-70839-DTLSB-09_08_2022-GO95HV-1^06243005.0038101 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2027-09-08 | 3
538709674-70839-DTLSB-09_08_2022-GO95MLD-1^06243005.0038101 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
550036459-74052-DTLSB-08_08_2022-GUYNOINS-1^06243004.0172001 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-08 | 2025-08-08 | 2
124053949-63852-DTLSB-08_08_2022-GO95HV-1^06243004.0172100 | OTHER | CA-NON-TIER | Distribution | 2022-08-08 | 2027-08-08 | 3
850565909-30829-DTLSB-08_08_2022-ABNDEQPM-1^06243004.0173501 | OTHER | CA-NON-TIER | Distribution | 2022-08-08 | 2027-08-08 | 3
26944159-77729-DTLSB-08_10_2022-GO95HV-1^06243004.0174101 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2027-08-10 | 3
342910689-69189-DTLSB-08_10_2022-GO95MLD-1^06243004.0175002 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
228878871-39969-DTLSB-09_29_2022-ABNDEQPM-1^06243005.0077401 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2027-09-29 | 3
860487990-65209-DTLSB-09_29_2022-GO95HV-1^06243005.0089201 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2027-09-29 | 3
860487990-65209-DTLSB-09_29_2022-GO95MLD-1^06243005.0089201 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
325638479-11389-DTLSB-08_08_2022-ABNDEQPM-1^06243004.0177902 | OTHER | CA-NON-TIER | Distribution | 2022-08-08 | 2027-08-08 | 3
719936999-75889-DTLSB-08_08_2022-GO95HV-1^06243004.0178900 | OTHER | CA-NON-TIER | Distribution | 2022-08-08 | 2027-08-08 | 3
375451355-62669-DTLSB-08_11_2022-GO95MLD-1^06243004.0179400 | OTHER | CA-NON-TIER | Distribution | 2022-08-11 | 2025-08-11 | 2
746778459-68289-DTLSB-08_01_2022-GO95MLD-1^06243004.0179800 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
469014249-68829-DTLSB-08_01_2022-XARMSPCR-1^06243004.0179802 | CROSSARM | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
232430408-49829-DTLSB-07_19_2022-GO95MLD-1^06243004.0190000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
634345098-29829-DTLSB-07_19_2022-GO95HV-1^06243004.0190001 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
658416258-57189-DTLSB-06_30_2022-GO95MLD-1^06243004.0191300 | OTHER | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
473619000-60199-DTLSB-08_03_2022-GO95HV-1^06243004.0211801 | OTHER | CA-NON-TIER | Distribution | 2022-08-03 | 2027-08-03 | 3
286440468-12369-DTLSB-09_29_2022-SVCENTCO-1^06243005.0089202 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
65673608-80499-DTLSB-09_29_2022-GO95MLD-1^06243005.0089204 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
153301008-26139-DTLSB-09_26_2022-GO95MLD-1^06243005.0089701 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
481703748-92939-DTLSB-09_29_2022-GO95HV-1^06243005.0090801 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2027-09-29 | 3
475064038-93939-DTLSB-09_29_2022-GO95MLD-1^06243005.0092902 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
704685718-24939-DTLSB-10_03_2022-INSULDMG-1^06243005.0093900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
430048159-98669-DTLSB-09_22_2022-GO95HV-1^06243005.0099000 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
285847921-10499-DTLSB-08_09_2022-CLRTOUCH-1^06243004.0281200 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
272087731-5539-DTLSB-08_09_2022-GO95MLD-1^06243004.0282401 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
265475811-86489-DTLSB-08_09_2022-GO95HV-1^06243004.0282402 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2027-08-09 | 3
937271961-95389-DTLSB-08_04_2022-GO95MLD-1^06243004.0283702 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2025-08-04 | 2
782499161-44599-DTLSB-08_09_2022-GO95MLD-1^06243004.0284440 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
377169604-38369-DTLSB-09_21_2022-GO95MLD-1^06243005.0109500 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2025-09-21 | 2
885749451-51551-DTLSB-09_20_2022-GO95HV-1^06243005.0110301 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
658497613-79639-DTLSB-09_19_2022-GO95HV-1^06243005.0110901 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
624532264-77799-DTLSB-09_20_2022-GO95MLD-1^06243005.0111200 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
303003654-55639-DTLSB-09_20_2022-GO95HV-1^06243005.0111202 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
972712553-49639-DTLSB-09_19_2022-GO95HV-1^06243005.0111901 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
131012137-96879-DTLSB-09_20_2022-GO95MLD-1^06243005.0112100 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
114568927-35764-DTLSB-09_20_2022-GO95HV-1^06243005.0112101 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
579297993-78979-DTLSB-09_19_2022-GO95HV-1^06243005.0115902 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
579297993-78979-DTLSB-09_19_2022-GO95MLD-1^06243005.0115902 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
325290763-11299-DTLSB-09_21_2022-GO95MLD-1^06243005.0116400 | OTHER | CA-TIER-2 | Distribution | 2022-09-21 | 2025-09-21 | 2
596583043-67639-DTLSB-09_21_2022-GO95MLD-1^06243005.0116700 | OTHER | CA-TIER-2 | Distribution | 2022-09-21 | 2025-09-21 | 2
673036843-38639-DTLSB-09_21_2022-GO95MLD-1^06243005.0116900 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2025-09-21 | 2
875049633-27739-DTLSB-09_20_2022-GO95MLD-1^06243005.0017803 | OTHER | CA-TIER-2 | Distribution | 2022-09-20 | 2025-09-20 | 2
761334473-56739-DTLSB-09_21_2022-GUYNOINS-1^06243005.0018701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-09-21 | 2025-09-21 | 2
869224504-46089-DTLSB-09_20_2022-GO95MLD-1^06243005.0018800 | OTHER | CA-TIER-2 | Distribution | 2022-09-20 | 2025-09-20 | 2
339907121-67889-DTLSB-09_09_2022-GRDRODHI-1^06243005.0019500 | OTHER | CA-TIER-2 | Distribution | 2022-09-09 | 2025-09-09 | 2
339907121-67889-DTLSB-09_09_2022-GRDRODHI-2^06243005.0019500 | OTHER | CA-TIER-2 | Distribution | 2022-09-09 | 2025-09-09 | 2
83199124-94422-DTLSB-09_20_2022-GO95MLD-1^06243005.0019740 | OTHER | CA-TIER-2 | Distribution | 2022-09-20 | 2025-09-20 | 2
619179764-98739-DTLSB-09_27_2022-ABNDEQPM-1^06243005.0020600 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2027-09-27 | 3
861375064-72812-DTLSB-09_27_2022-GO95MLD-1^06243005.0020601 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
530813500-65500-DTLSB-09_19_2022-GO95HV-1^06243005.0025020 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
822902600-83600-DTLSB-09_19_2022-GO95HV-1^06243005.0025122 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
822902600-83600-DTLSB-09_19_2022-GO95MLD-1^06243005.0025122 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
537093221-15869-DTLSB-09_27_2022-GO95TCH-1^06243005.0026601 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
648797088-77708-DTLSB-09_08_2022-GO95HV-1^06243005.0038500 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2027-09-08 | 3
351915375-3399-DTLSB-09_08_2022-GO95MLD-1^06243005.0039100 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
347686738-78808-DTLSB-09_27_2022-GUYHINS-1^06243005.0039701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
21836836-48836-DTLSB-09_27_2022-GO95MLD-1^06243005.0039903 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
21836836-48836-DTLSB-09_27_2022-GUYSLACK-1^06243005.0039903 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
951868118-54939-DTLSB-09_26_2022-GO95HV-1^06243005.0043000 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
403560158-39302-DTLSB-09_26_2022-INSULDMG-1^06243005.0044201 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
622585338-81502-DTLSB-09_26_2022-GO95HV-1^06243005.0045500 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
981254188-21402-DTLSB-09_26_2022-GO95HV-1^06243005.0047502 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
981254188-21402-DTLSB-09_26_2022-XARMSPCR-1^06243005.0047502 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
964563588-54202-DTLSB-09_26_2022-GO95HV-1^06243005.0048501 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
872942778-36002-DTLSB-09_27_2022-GO95MLD-1^06243005.0049400 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
812246763-96429-DTLSB-09_06_2023-GO95HV-1^06243007.0185601 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
298938073-67429-DTLSB-09_06_2023-GO95HV-1^06243007.0186600 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
247755083-73109-DTLSB-09_06_2023-GO95MLD-1^06243007.0188501 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
925213013-15589-DTLSB-09_06_2023-GO95MLD-1^06243007.0189300 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
776582433-81529-DTLSB-09_06_2023-GO95HV-1^06243007.0202501 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
307153118-80309-DTLSB-09_29_2022-GO95MLD-1^06243005.0089700 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
936197890-46498-DTLSB-09_29_2022-GO95MLD-1^06243005.0092801 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
936197890-46498-DTLSB-09_29_2022-GO95MLD-2^06243005.0092801 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
824524249-29669-DTLSB-09_22_2022-GO95HV-1^06243005.0099001 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
357595768-95039-DTLSB-09_20_2022-GO95MLD-1^06243005.0103501 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
616614709-13339-DTLSB-09_22_2022-GO95MLD-1^06243005.0104000 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
712623099-3339-DTLSB-09_22_2022-GO95HV-1^06243005.0104001 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
117972248-76939-DTLSB-09_22_2022-GO95HV-1^06243005.0104002 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
443749988-78939-DTLSB-10_03_2022-GO95HV-1^06243005.0107001 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2027-10-03 | 3
873419122-80222-DTLSB-09_21_2022-GO95MLD-1^06243005.0108520 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2025-09-21 | 2
593401318-23039-DTLSB-09_21_2022-GO95MLD-1^06243005.0108700 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2025-09-21 | 2
358462638-67798-DTLSB-09_21_2022-GO95HV-1^06243005.0108801 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2027-09-21 | 3
215060268-21139-DTLSB-09_19_2022-GO95STUB-1^06243005.0108901 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
740670538-73598-DTLSB-09_08_2022-GO95HV-1^06243005.0108902 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2027-09-08 | 3
740670538-73598-DTLSB-09_08_2022-XARMSPCR-1^06243005.0108902 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
260296088-20039-DTLSB-09_20_2022-GO95MLD-1^06243005.0109201 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
471930898-2139-DTLSB-09_19_2022-GO95MLD-1^06243005.0109900 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
698961754-95639-DTLSB-09_20_2022-GO95MLD-1^06243005.0110201 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
885749451-51551-DTLSB-09_20_2022-GO95BLTC-1^06243005.0110301 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
235012877-73877-DTLSB-09_20_2022-GO95HV-1^06243005.0110420 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
800125573-66029-DTLSB-09_05_2023-GO95HV-1^06243008.0264901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
531041253-98639-DTLSB-09_19_2022-GO95MLD-1^06243005.0113900 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
673036843-38639-DTLSB-09_21_2022-GO95HV-1^06243005.0116900 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2027-09-21 | 3
981519123-30739-DTLSB-09_21_2022-GO95HV-1^06243005.0116901 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2027-09-21 | 3
981519123-30739-DTLSB-09_21_2022-GO95MLD-1^06243005.0116901 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2025-09-21 | 2
844098805-93905-DTLSB-09_21_2022-GO95HV-1^06243005.0117800 | OTHER | CA-TIER-2 | Distribution | 2022-09-21 | 2027-09-21 | 3
451972713-50469-DTLSB-09_21_2022-GO95MLD-1^06243005.0118900 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2025-09-21 | 2
462021129-18989-DTLSB-06_29_2022-GO95HV-1^06243005.0130000 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2027-06-29 | 3
462021129-18989-DTLSB-06_29_2022-GO95MLD-1^06243005.0130000 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
586320079-82389-DTLSB-06_29_2022-GO95HV-1^06243005.0130500 | OTHER | CA-TIER-2 | Distribution | 2022-06-29 | 2027-06-29 | 3
641149919-65439-DTLSB-06_29_2022-GO95MLD-1^06243005.0131200 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
345255449-33799-DTLSB-06_29_2022-GO95MLD-1^06243005.0133300 | OTHER | CA-TIER-2 | Distribution | 2022-06-29 | 2025-06-29 | 2
480020288-42611-DETAIL-05_30_2023-GO95MLD-1^06243009.0010700 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
902253138-5211-DETAIL-05_30_2023-SVCDEFLC-2^06243009.0010702 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
455756128-67711-DETAIL-05_30_2023-UNIGRDSG-1^06243009.0010703 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
709961459-21821-DETAIL-05_30_2023-SVCDEFLC-2^06243009.0010802 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
436636508-36239-DTLSB-09_29_2022-GO95MLD-1^06243005.0186500 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
436636508-36239-DTLSB-09_29_2022-GRDRODHI-1^06243005.0186500 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
591450249-69189-DTLSB-09_22_2022-GO95BLTC-1^06243005.0216800 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
591450249-69189-DTLSB-09_22_2022-GO95HV-1^06243005.0216800 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
591450249-69189-DTLSB-09_22_2022-GRDRODHI-1^06243005.0216800 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
993537739-58239-DTLSB-09_22_2022-POLETOP-1^06243005.0216901 | POLE | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
596245509-39339-DTLSB-06_30_2022-GO95MLD-1^06243005.0233100 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2025-06-30 | 2
312253409-79029-DETAIL-06_05_2023-GO95STUB-1^06243009.0024404 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
971137852-77852-DETAIL-06_05_2023-GO95HV-1^06243009.0024420 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
965678953-40268-DETAIL-06_06_2023-GO95MLD-1^06243009.0024501 | OTHER | CA-NON-TIER | Distribution | 2023-06-06 | 2026-06-06 | 2
46351050-65669-DETAIL-06_06_2023-GO95BLTC-1^06243009.0025000 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
46351050-65669-DETAIL-06_06_2023-GUYHINS-1^06243009.0025000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
13363631-83229-DETAIL-06_06_2023-GO95MLD-1^06243009.0025005 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
337921690-61361-DETAIL-06_06_2023-GO95MLD-1^06243009.0025040 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
434875339-43989-DETAIL-06_02_2023-SVCROAD-1^06243009.0025104 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
201958572-22639-DTLSB-07_18_2022-GO95HV-1^06243005.0256301 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2027-07-18 | 3
965038632-68632-DTLTRT-07_18_2022-GO95HV-1^06243005.0258700 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2027-07-18 | 3
186362353-25429-DTLSB-08_25_2023-GO95HV-1^06243007.0180901 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
673531983-97429-DTLSB-09_06_2023-GO95HV-1^06243007.0187500 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
178793749-94229-DETAIL-06_02_2023-GO95MLD-1^06243009.0026202 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
761413981-5229-DETAIL-06_02_2023-GO95MLD-1^06243009.0026203 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
761413981-5229-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026203 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
721516589-64229-DETAIL-06_02_2023-GO95MLD-1^06243009.0026303 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
137361391-59129-DETAIL-06_05_2023-GO95MLD-1^06243009.0026305 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
684199119-95229-DETAIL-06_02_2023-CLMBHAZ-1^06243009.0026306 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
71744831-50211-DETAIL-06_02_2023-GUYNOINS-1^06243009.0026320 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
391688749-48521-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0026400 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
177554359-18879-DETAIL-06_05_2023-GUYHINS-1^06243009.0026402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
177554359-18879-DETAIL-06_05_2023-SVCROAD-1^06243009.0026402 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
128219699-61229-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026403 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
499192181-80829-DTLSB-09_28_2023-GO95HV-1^06243008.0107700 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
600655631-41829-DTLSB-09_07_2023-GO95HV-1^06243008.0109800 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
897105781-11829-DTLSB-09_28_2023-GO95HV-1^06243008.0110801 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
391094623-99629-DTLSB-09_28_2023-GO95HV-1^06243008.0112900 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
455056534-98629-DTLSB-09_07_2023-GO95HV-1^06243008.0118800 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
231170844-94629-DTLSB-09_07_2023-GO95HV-1^06243008.0120600 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
314760344-31629-DTLSB-09_07_2023-ABNDEQPM-1^06243008.0121601 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
10876383-92629-DTLSB-09_07_2023-GO95MLD-1^06243008.0124202 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2026-09-07 | 2
687954540-18871-DETAIL-05_31_2023-GO95MLD-1^06243009.0026502 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
106290661-20801-DETAIL-05_31_2023-GO95CL10-1^06243009.0026503 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2028-05-31 | 3
147707980-73001-DETAIL-06_05_2023-GO95MLD-1^06243009.0026505 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
147707980-73001-DETAIL-06_05_2023-SVCROOF-1^06243009.0026505 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
929033032-29589-DTLSB-08_24_2023-GO95MLD-1^06243008.0174901 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2028-08-24 | 3
763169762-64929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176100 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
208267552-73929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176300 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
934448852-51929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176400 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
80086013-20209-DTLSB-09_05_2023-GO95MLD-1^06243008.0178500 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
463019842-209-DTLSB-08_30_2023-GO95MLD-1^06243008.0179701 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2028-08-30 | 3
487940592-68829-DTLSB-08_24_2023-GO95HV-1^06243008.0186501 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2028-08-24 | 3
857940392-8829-DTLSB-08_24_2023-GUYNOINS-1^06243008.0187500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
859332073-34073-DTLSB-08_30_2023-GO95HV-1^06243008.0205700 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2028-08-30 | 3
284887372-78679-DTLSB-08_30_2023-GO95MLD-1^06243008.0205800 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
484414072-45929-DTLSB-08_30_2023-GO95MLD-1^06243008.0206900 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
143969920-33229-DETAIL-06_05_2023-SVCWIND-1^06243009.0027409 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
712473389-38821-DETAIL-06_01_2023-GO95HV-1^06243009.0028401 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
573453608-68399-DETAIL-06_01_2023-GO95MLD-1^06243009.0028404 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
228953231-17129-DETAIL-06_01_2023-GO95TCH-1^06243009.0028409 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
990468598-7129-DETAIL-06_01_2023-GRDRODHI-1^06243009.0028411 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
990468598-7129-DETAIL-06_01_2023-GRDRODHI-2^06243009.0028411 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
672688288-88999-DETAIL-06_01_2023-GO95MLD-1^06243009.0028412 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
672688288-88999-DETAIL-06_01_2023-GRDRODHI-2^06243009.0028412 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
486908607-36129-DETAIL-06_01_2023-GO95HV-1^06243009.0028414 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
872078781-48111-DETAIL-06_05_2023-GO95MLD-1^06243009.0028417 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
980073760-90169-DETAIL-06_05_2023-GO95TCH-1^06243009.0023300 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
629929509-52031-DETAIL-06_05_2023-GO95MLD-1^06243009.0023302 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
319387570-61679-DETAIL-06_06_2023-RISEBKSP-1^06243009.0023540 | OTHER | CA-NON-TIER | Distribution | 2023-06-06 | 2026-06-06 | 2
592944749-60989-DETAIL-06_02_2023-GO95MLD-1^06243009.0024200 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
524996789-50689-DETAIL-06_05_2023-GO95MLD-1^06243009.0024205 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
480064729-71129-DETAIL-06_05_2023-GO95MLD-1^06243009.0024206 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
320790499-63821-DETAIL-06_05_2023-GO95MLD-1^06243009.0024301 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
320790499-63821-DETAIL-06_05_2023-GO95TCH-1^06243009.0024301 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
964923401-50611-DETAIL-05_31_2023-GUYHINS-1^06243009.0028505 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
647962280-78929-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0028506 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
389631870-19399-DETAIL-06_01_2023-SVCWIND-1^06243009.0028510 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
400264781-40111-DETAIL-05_30_2023-GO95MLD-1^06243009.0029703 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
654409901-9599-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0029705 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
654409901-9599-DETAIL-05_30_2023-SVCWIND-1^06243009.0029705 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
272177150-97761-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0029706 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
272177150-97761-DETAIL-05_30_2023-SVCDEFLC-2^06243009.0029706 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
213004391-10701-DETAIL-05_30_2023-GO95MLD-1^06243009.0029709 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
213004391-10701-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0029709 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
840499590-94189-DETAIL-05_30_2023-GO95MLD-1^06243009.0029800 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
519010384-68989-DTLSB-07_25_2023-SVCDEFLC-1^06243009.0053501 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
709132974-58479-DTLSB-07_25_2023-GO95MLD-1^06243009.0053502 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
633571963-48429-DTLSB-07_25_2023-GO95MLD-1^06243009.0054300 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
338714504-58081-DTLSB-07_25_2023-ENCHRW-1^06243009.0054400 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
108038263-87429-DTLSB-07_25_2023-GO95MLD-1^06243009.0054401 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
319984853-93189-DTLSB-07_25_2023-ENCHRW-1^06243009.0054403 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
304675743-68799-DTLSB-07_26_2023-GO95HV-1^06243009.0054600 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
304675743-68799-DTLSB-07_26_2023-GO95MLD-1^06243009.0054600 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
219642799-50129-DETAIL-06_05_2023-GO95MLD-1^06243009.0024401 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
46351050-65669-DETAIL-06_06_2023-GO95MLD-1^06243009.0025000 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
13363631-83229-DETAIL-06_06_2023-SVCENTCO-1^06243009.0025005 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
764753759-31079-DETAIL-06_02_2023-GO95MLD-1^06243009.0025101 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2026-06-02 | 2
994335151-89129-DETAIL-06_05_2023-GO95HV-1^06243009.0025410 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
375869169-40129-DETAIL-06_05_2023-GO95MLD-1^06243009.0025413 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
122641429-57279-DETAIL-06_05_2023-GO95MLD-1^06243009.0025414 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
718127461-11811-DETAIL-05_31_2023-GO95MLD-1^06243009.0025500 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
906907159-88989-DETAIL-06_06_2023-GO95TCH-1^06243009.0026000 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
212253591-43229-DETAIL-06_06_2023-GO95MLD-1^06243009.0026001 | OTHER | CA-NON-TIER | Distribution | 2023-06-06 | 2026-06-06 | 2
80128089-67269-DETAIL-06_05_2023-GO95HV-1^06243009.0026003 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2028-06-05 | 3
80128089-67269-DETAIL-06_05_2023-GO95MLD-1^06243009.0026003 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
304675743-68799-DTLSB-07_26_2023-SVCDEFLC-1^06243009.0054600 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
305458264-75429-DTLSB-07_26_2023-GO95HV-1^06243009.0054701 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2028-07-26 | 3
604799933-20529-DTLSB-07_26_2023-XARMSPCR-1^06243009.0055001 | CROSSARM | CA-TIER-2 | Distribution | 2023-07-26 | 2024-07-26 | 2
723424174-60879-DTLSB-07_26_2023-GO95MLD-1^06243009.0055702 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2026-07-26 | 2
452680324-95429-DTLSB-07_26_2023-GO95HV-1^06243009.0055902 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2028-07-26 | 3
379832404-66779-DTLSB-07_26_2023-GO95MLD-1^06243009.0056000 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
120356244-39581-DTLSB-07_25_2023-GO95MLD-1^06243009.0056403 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
448795593-20571-DTLSB-07_25_2023-GO95HV-1^06243009.0056502 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2028-07-25 | 3
154700374-5981-DTLSB-07_25_2023-GO95MLD-1^06243009.0056600 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
786415514-76429-DTLSB-07_26_2023-GO95HV-1^06243009.0058900 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2028-07-26 | 3
824930404-56889-DTLSB-07_26_2023-GO95HV-1^06243009.0059901 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2028-07-26 | 3
824930404-56889-DTLSB-07_26_2023-GO95MLD-1^06243009.0059901 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2026-07-26 | 2
765043453-96171-DTLSB-08_01_2023-GO95HV-1^06243009.0074000 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
765043453-96171-DTLSB-08_01_2023-GO95MLD-1^06243009.0074000 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
202998723-59529-DTLSB-08_01_2023-GO95HV-1^06243009.0076003 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
498865098-40309-DETAIL-06_05_2023-GO95TCH-1^06243009.0026004 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
293166084-11181-DTLSB-07_31_2023-GO95MLD-1^06243009.0087602 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
886183534-44699-DTLSB-07_31_2023-GO95MLD-1^06243009.0087603 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
826504133-36979-DTLSB-08_16_2023-GO95MLD-1^06243009.0105000 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2028-08-16 | 3
679439893-92429-DTLSB-08_23_2023-GO95MLD-1^06243009.0109400 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
601121916-88962-DTLSB-08_23_2023-GO95MLD-1^06243009.0111440 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
533297316-7121-DTLSB-08_29_2023-GO95MLD-1^06243009.0114800 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
411559669-32599-DETAIL-06_02_2023-GO95CLSV-1^06243009.0027306 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
800232429-48579-DETAIL-06_05_2023-CLMBTRE-1^06243009.0027400 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
800232429-48579-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0027400 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
800232429-48579-DETAIL-06_05_2023-SVCDEFLC-2^06243009.0027400 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
455243246-22229-DETAIL-06_05_2023-GO95HV-1^06243009.0027403 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
455243246-22229-DETAIL-06_05_2023-GO95MLD-1^06243009.0027403 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
44945819-7799-DETAIL-06_05_2023-GO95BLTC-1^06243009.0026100 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2028-06-05 | 3
609576899-9799-DETAIL-06_02_2023-GO95MLD-1^06243009.0026200 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
761413981-5229-DETAIL-06_02_2023-GO95HV-1^06243009.0026203 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2028-06-02 | 3
88920509-95389-DETAIL-06_02_2023-GO95MLD-1^06243009.0026205 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2026-06-02 | 2
88920509-95389-DETAIL-06_02_2023-GUYHINS-1^06243009.0026205 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-02 | 2026-06-02 | 2
16848229-20199-DETAIL-06_02_2023-GO95HV-1^06243009.0026208 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2028-06-02 | 3
16848229-20199-DETAIL-06_02_2023-GO95MLD-1^06243009.0026208 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2026-06-02 | 2
942784339-37499-DETAIL-06_02_2023-GO95HV-1^06243009.0026301 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2028-06-02 | 3
942784339-37499-DETAIL-06_02_2023-GO95MLD-1^06243009.0026301 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
721516589-64229-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026303 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
682034499-38599-DETAIL-06_02_2023-GO95MLD-1^06243009.0026304 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
684199119-95229-DETAIL-06_02_2023-GO95TCH-1^06243009.0026306 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
391688749-48521-DETAIL-06_05_2023-GO95MLD-1^06243009.0026400 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
391688749-48521-DETAIL-06_05_2023-SVCWIND-1^06243009.0026400 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
268600319-34179-DETAIL-06_05_2023-GO95MLD-1^06243009.0026401 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
177554359-18879-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0026402 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
541598909-19129-DETAIL-06_02_2023-GO95MLD-1^06243009.0026404 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
470205968-36968-DETAIL-06_02_2023-GO95MLD-1^06243009.0026409 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
440131131-60229-DETAIL-05_31_2023-GO95MLD-1^06243009.0026410 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2028-05-31 | 3
863664953-94953-DETAIL-05_31_2023-GO95MLD-1^06243009.0026411 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
632816251-93501-DETAIL-05_31_2023-CLMBTRE-1^06243009.0026500 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
632816251-93501-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0026500 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
687954540-18871-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0026502 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
106290661-20801-DETAIL-05_31_2023-GO95HV-1^06243009.0026503 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2028-05-31 | 3
22008250-55489-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0026504 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
848090209-18579-DETAIL-06_05_2023-GO95MLD-1^06243009.0027300 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
848090209-18579-DETAIL-06_05_2023-SVCWIND-1^06243009.0027300 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
920150879-98129-DETAIL-06_02_2023-GO95MLD-1^06243009.0027302 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2028-06-02 | 3
643954486-80571-DETAIL-06_02_2023-GO95TCH-1^06243009.0027305 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
202998723-59529-DTLSB-08_01_2023-GO95MLD-1^06243009.0076003 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
592163944-1899-DTLSB-08_01_2023-GO95MLD-1^06243009.0076100 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
751840913-37299-DTLSB-08_01_2023-ABNDEQPM-1^06243009.0077000 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
386201483-74499-DTLSB-08_01_2023-GO95HV-1^06243009.0078000 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
733162913-98529-DTLSB-08_01_2023-GO95STUB-1^06243009.0078001 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
930257763-42529-DTLSB-07_31_2023-GO95HV-1^06243009.0081301 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
688784703-82529-DTLSB-07_31_2023-GO95MLD-1^06243009.0081302 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
722211503-7789-DTLSB-07_31_2023-GO95HV-1^06243009.0082500 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
722211503-7789-AUDIT-09_21_2023-GO95MLD-1^06243009.0082500 | OTHER | CA-TIER-2 | Distribution | 2023-09-21 | 2026-09-21 | 2
539899084-79181-DTLSB-07_26_2023-GO95MLD-1^06243009.0082600 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
669850713-70529-DTLSB-07_26_2023-GO95MLD-1^06243009.0082700 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
413641283-50529-DTLSB-07_26_2023-GO95MLD-1^06243009.0082901 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
114906303-82479-DTLSB-07_31_2023-GO95HV-1^06243009.0084000 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
486633364-60589-DTLSB-07_31_2023-GO95MLD-1^06243009.0085301 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
96510544-85879-DTLSB-07_31_2023-SVCDEFLC-1^06243009.0087400 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
249342383-14529-DTLSB-07_31_2023-GO95MLD-1^06243009.0087501 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
187815611-76611-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026420 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
187815611-76611-DETAIL-06_02_2023-SVCWIND-1^06243009.0026420 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
753082402-23541-DETAIL-05_31_2023-GO95MLD-1^06243009.0026501 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
753082402-23541-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0026501 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
127478562-63869-DETAIL-07_12_2023-GO95MLD-1^06243008.0056900 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
38224431-14489-DTLSB-09_05_2023-GO95MLD-1^06243008.0089101 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
166870591-36729-DTLSB-09_05_2023-ENCHRW-1^06243008.0092502 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
293738011-62829-DTLSB-09_05_2023-ABNDEQPM-1^06243008.0093300 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
34231511-32989-DTLSB-09_05_2023-GO95MLD-1^06243008.0094200 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
689106101-5669-DTLSB-09_05_2023-GO95MLD-1^06243008.0096600 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
122419691-78729-DTLSB-09_28_2023-GO95MLD-1^06243008.0101600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2026-09-28 | 2
740169081-27799-DTLSB-09_28_2023-GO95HV-1^06243008.0106600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
88888961-41789-DETAIL-06_06_2023-GO95MLD-1^06243009.0027000 | OTHER | CA-NON-TIER | Distribution | 2023-06-06 | 2026-06-06 | 2
180710601-30769-DETAIL-06_06_2023-GO95MLD-1^06243009.0027001 | OTHER | CA-NON-TIER | Distribution | 2023-06-06 | 2026-06-06 | 2
920150879-98129-DETAIL-06_02_2023-SVCWIND-1^06243009.0027302 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2026-06-02 | 2
482377858-25129-DETAIL-06_02_2023-SVCWIND-1^06243009.0027304 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2026-06-02 | 2
331728904-54629-DTLSB-09_07_2023-GO95HV-1^06243008.0128000 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
609784873-72899-DTLSB-08_25_2023-GO95MLD-1^06243008.0132100 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
969667163-60029-DTLSB-08_25_2023-GO95HV-1^06243008.0133403 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
640222533-54029-DTLSB-08_25_2023-GO95HV-1^06243008.0137700 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
527347643-94429-DTLSB-09_07_2023-GO95HV-1^06243008.0139900 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
443929352-2393-DTLSB-09_05_2023-GO95MLD-1^06243008.0161800 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
608509722-67601-DTLSB-09_05_2023-GO95HV-1^06243008.0161901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
608509722-67601-DTLSB-09_05_2023-GO95MLD-1^06243008.0161901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
643954486-80571-DETAIL-06_02_2023-GO95MLD-1^06243009.0027305 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
643954486-80571-AUDIT-07_27_2023-GO95HV-1^06243009.0027305 | OTHER | CA-NON-TIER | Distribution | 2023-07-27 | 2028-07-27 | 3
750589009-55229-DETAIL-06_02_2023-GO95MLD-1^06243009.0027309 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2026-06-02 | 2
800232429-48579-DETAIL-06_05_2023-GO95MLD-1^06243009.0027400 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
728848591-91229-DETAIL-06_05_2023-GO95MLD-1^06243009.0027401 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
605265471-32229-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0027404 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
235075256-22579-DETAIL-06_05_2023-GO95MLD-1^06243009.0027405 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
143969920-33229-DETAIL-06_05_2023-GO95CLSV-1^06243009.0027409 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
571497232-54851-DTLSB-09_05_2023-GO95HV-1^06243008.0162900 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
291730032-83021-DTLSB-09_05_2023-GO95HV-1^06243008.0162901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
409603842-90713-DTLSB-09_05_2023-GO95MLD-1^06243008.0163901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
940980012-94789-DTLSB-08_24_2023-GRDRODHI-1^06243008.0171700 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
495387609-72229-DETAIL-06_05_2023-GO95MLD-1^06243009.0027410 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
665318666-17589-DETAIL-06_05_2023-SVCDEFLC-2^06243009.0027411 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
871355048-95129-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0027412 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
366087189-3229-DETAIL-06_02_2023-CLMBTRE-1^06243009.0027414 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
438063851-68829-DETAIL-06_05_2023-GO95TCH-1^06243009.0027420 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
108878380-44461-DETAIL-05_31_2023-GO95TCH-1^06243009.0027501 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
48387892-74379-DTLSB-08_30_2023-GO95MLD-1^06243008.0207600 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2028-08-30 | 3
292465543-1079-DTLSB-09_05_2023-GO95MLD-1^06243008.0235100 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
901054953-74341-DTLSB-09_05_2023-GO95MLD-1^06243008.0240900 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
961041983-23029-DTLSB-08_25_2023-GO95MLD-1^06243008.0241800 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
973457393-86699-DTLSB-09_08_2023-GO95MLD-1^06243008.0262800 | OTHER | CA-TIER-2 | Distribution | 2023-09-08 | 2028-09-08 | 3
730281003-16889-DTLSB-09_05_2023-GO95MLD-1^06243008.0263800 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
773570893-16799-DTLSB-09_08_2023-GO95MLD-1^06243008.0263801 | OTHER | CA-TIER-2 | Distribution | 2023-09-08 | 2028-09-08 | 3
984907198-24779-DETAIL-01_21_2021-GO95HV-1^06243008.0301400 | OTHER | CA-TIER-2 | Distribution | 2021-01-21 | 2026-01-21 | 3
419845200-48929-DETAIL-06_05_2023-GO95TCH-1^06243009.0027503 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
263018130-29929-DETAIL-05_31_2023-GO95TCH-1^06243009.0027601 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
876566711-37231-DETAIL-05_31_2023-GO95MLD-1^06243009.0027606 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2028-05-31 | 3
876566711-37231-DETAIL-05_31_2023-GUYHINS-1^06243009.0027606 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
411749400-16161-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0027610 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
592908910-2261-DETAIL-05_31_2023-GO95MLD-1^06243009.0027611 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
592908910-2261-DETAIL-05_31_2023-GO95TCH-1^06243009.0027611 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
592908910-2261-DETAIL-05_31_2023-GUYHINS-1^06243009.0027611 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
932526561-82531-DETAIL-05_30_2023-GRDRODHI-1^06243009.0027900 | OTHER | CA-NON-TIER | Distribution | 2023-05-30 | 2026-05-30 | 2
749709631-58111-DETAIL-06_01_2023-GO95TCH-1^06243009.0028503 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
496426809-30621-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0010500 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
357544349-17721-DETAIL-06_01_2023-GO95TCH-1^06243009.0010502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
357544349-17721-DETAIL-06_01_2023-SVCROAD-1^06243009.0010502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
604071069-42821-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0010504 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
77694798-42899-DETAIL-06_01_2023-GO95MLD-1^06243009.0010507 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
23210659-44189-DETAIL-06_01_2023-GO95MLD-1^06243009.0010601 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
23210659-44189-DETAIL-06_01_2023-GRDRODHI-1^06243009.0010601 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
689133729-72521-DETAIL-06_01_2023-GO95MLD-1^06243009.0010602 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
902253138-5211-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0010702 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
455756128-67711-DETAIL-05_30_2023-GUYHINS-1^06243009.0010703 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
455756128-67711-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0010703 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
709961459-21821-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0010802 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
468711798-39399-DETAIL-05_30_2023-GO95MLD-1^06243009.0010806 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
30113649-98721-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0011502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
118454949-82721-DETAIL-06_01_2023-GO95HV-1^06243009.0011600 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
169204228-57929-DETAIL-05_30_2023-GO95HV-1^06243009.0011801 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
565389029-80189-DETAIL-06_14_2023-GO95MLD-1^06243009.0022000 | OTHER | CA-NON-TIER | Distribution | 2023-06-14 | 2026-06-14 | 2
6415179-46241-DETAIL-06_02_2023-GO95MLD-1^06243009.0025102 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2028-06-02 | 3
89093901-57229-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0025103 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
434875339-43989-DETAIL-06_02_2023-GO95MLD-1^06243009.0025104 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
391505939-53989-DETAIL-06_02_2023-GO95HV-1^06243009.0025200 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2028-06-02 | 3
30683571-41589-DETAIL-06_02_2023-GO95MLD-1^06243009.0025202 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
32832111-66229-DETAIL-06_02_2023-GO95MLD-1^06243009.0025205 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
703542461-59679-DETAIL-06_05_2023-GO95HV-1^06243009.0025300 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
245851840-37679-DETAIL-05_31_2023-GO95MLD-1^06243009.0025401 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
411159269-30229-DETAIL-05_31_2023-GO95MLD-1^06243009.0025402 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
411159269-30229-DETAIL-05_31_2023-GO95TCH-1^06243009.0025402 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
432248049-47679-DETAIL-06_05_2023-GO95MLD-1^06243009.0025403 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
399920369-45299-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0025406 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
505191313-6529-DTLSB-08_31_2023-GO95HV-1^06243007.0293401 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
625795093-50789-DTLSB-08_31_2023-GO95MLD-1^06243007.0293700 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2026-08-31 | 2
96949313-92499-DTLSB-08_31_2023-GO95MLD-1^06243007.0320200 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2026-08-31 | 2
799533733-50729-DTLSB-09_07_2023-GO95HV-1^06243008.0023001 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
509517293-91729-DTLSB-08_31_2023-GO95HV-1^06243008.0025900 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
958132114-8629-DTLSB-09_07_2023-GO95MLD-1^06243008.0026000 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2026-09-07 | 2
947231752-68009-DETAIL-07_12_2023-GO95MLD-1^06243008.0054700 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
701655981-91631-DTLSB-09_05_2023-GUYNOINS-1^06243008.0092500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
293738011-62829-DTLSB-09_05_2023-GO95MLD-1^06243008.0093300 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
297788991-50369-DTLSB-09_05_2023-GO95HV-1^06243008.0095601 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
689106101-5669-DTLSB-09_05_2023-SVCDEFLC-1^06243008.0096600 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
50560451-17729-DTLSB-09_28_2023-GO95HV-1^06243008.0097600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
50560451-17729-DTLSB-09_28_2023-GO95MLD-1^06243008.0097600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2026-09-28 | 2
57709191-78999-DTLSB-09_28_2023-GO95MLD-1^06243008.0102501 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2026-09-28 | 2
400388271-79729-DTLSB-09_28_2023-GO95HV-1^06243008.0103600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
658525023-1029-DTLSB-08_25_2023-GO95HV-1^06243008.0133401 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
721154638-39039-DTLSB-09_19_2022-GO95MLD-1^06243005.0104900 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
213062019-1599-DTLSB-10_03_2022-GO95MLD-1^06243005.0105101 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
493448188-98039-DTLSB-09_19_2022-GO95MLD-1^06243005.0105900 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
47689409-90179-DTLSB-09_19_2022-GO95BLTC-1^06243005.0105901 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
38440378-47039-DTLSB-09_19_2022-GO95MLD-1^06243005.0105904 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
430046618-38939-DTLSB-10_03_2022-GO95HV-1^06243005.0106001 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2027-10-03 | 3
548246748-60769-DTLSB-09_20_2022-GO95MLD-1^06243005.0106502 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
75301018-58939-DTLSB-10_03_2022-GO95HV-1^06243005.0107000 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2027-10-03 | 3
75301018-58939-DTLSB-10_03_2022-GO95MLD-1^06243005.0107000 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
318959111-9601-DETAIL-06_01_2023-GO95MLD-1^06243009.0028511 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
450227592-21541-DETAIL-05_31_2023-GO95MLD-1^06243009.0028603 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3
355690351-60199-DETAIL-05_31_2023-GO95MLD-1^06243009.0028608 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
790745840-11061-DETAIL-05_31_2023-GO95BLTC-1^06243009.0028613 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3
790745840-11061-DETAIL-05_31_2023-GO95HV-1^06243009.0028613 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3
790745840-11061-DETAIL-05_31_2023-GO95MLD-1^06243009.0028613 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
376112575-62450-DETAIL-06_01_2023-GO95MLD-1^06243009.0029500 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
644600661-36611-DETAIL-06_01_2023-GO95MLD-1^06243009.0029502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
284590951-89511-DETAIL-06_01_2023-GO95MLD-1^06243009.0029503 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
624532264-77799-DTLSB-09_20_2022-GO95HV-1^06243005.0111200 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
931661694-7669-DTLSB-09_20_2022-GO95MLD-1^06243005.0111300 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
531041253-98639-DTLSB-09_19_2022-GO95HV-1^06243005.0113900 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
443929352-2393-DTLSB-09_05_2023-GO95HV-1^06243008.0161800 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
144945522-94131-DTLSB-09_05_2023-GO95HV-1^06243008.0161900 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
695674832-67761-DTLSB-09_05_2023-GO95HV-1^06243008.0162801 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
571497232-54851-DTLSB-09_05_2023-GO95MLD-1^06243008.0162900 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
237702842-41309-DTLSB-08_24_2023-GO95HV-1^06243008.0170601 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2028-08-24 | 3
940980012-94789-DTLSB-08_24_2023-GO95MLD-1^06243008.0171700 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
428116512-89829-DTLSB-08_24_2023-GUYNOINS-1^06243008.0172701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
428116512-89829-DTLSB-08_24_2023-GUYNOINS-2^06243008.0172701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
67531412-98241-DTLSB-08_30_2023-SVCDEFLC-1^06243008.0173100 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
850662392-8599-DTLSB-08_25_2023-GO95BLTC-1^06243008.0175500 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
613690852-34929-DTLSB-08_30_2023-GO95HV-1^06243008.0176201 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2028-08-30 | 3
613690852-34929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176201 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
250361152-41929-AUDIT-10_09_2023-GO95HV-1^06243008.0176500 | OTHER | CA-TIER-2 | Distribution | 2023-10-09 | 2028-10-09 | 3
447034132-21389-DTLSB-08_22_2023-GO95MLD-1^06243008.0180200 | OTHER | CA-TIER-2 | Distribution | 2023-08-22 | 2028-08-22 | 3
298120222-45829-AUDIT-10_09_2023-XARMSPCR-1^06243008.0180300 | CROSSARM | CA-TIER-2 | Distribution | 2023-10-09 | 2024-10-09 | 2
857940392-8829-DTLSB-08_24_2023-GUYNOINS-2^06243008.0187500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
284887372-78679-DTLSB-08_30_2023-SVCWIND-1^06243008.0205800 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
917198162-44989-DTLSB-08_30_2023-GO95MLD-1^06243008.0207900 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
675098153-50029-DTLSB-09_05_2023-GO95HV-1^06243008.0235000 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
782952593-50799-DTLSB-08_25_2023-GO95MLD-1^06243008.0240800 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2026-08-25 | 2
588807041-53701-DETAIL-06_01_2023-GO95MLD-1^06243009.0029504 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
588807041-53701-DETAIL-06_01_2023-GUYHINS-1^06243009.0029504 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
315176475-88475-DETAIL-06_01_2023-GO95MLD-1^06243009.0029505 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
315176475-88475-AUDIT-08_01_2023-GO95CL10-1^06243009.0029505 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
315176475-88475-AUDIT-08_01_2023-GO95MLD-1^06243009.0029505 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
864607391-5601-DETAIL-05_31_2023-GO95HV-1^06243009.0029600 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3
368127760-8929-DETAIL-05_31_2023-GO95MLD-1^06243009.0029601 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
468565211-83301-DETAIL-05_30_2023-GO95TCH-1^06243009.0029700 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
989774611-16201-DETAIL-05_30_2023-SVCRUBLG-1^06243009.0029702 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
464658558-51539-DTLSB-06_30_2022-GO95MLD-1^06243005.0140901 | OTHER | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
205782409-60539-DTLSB-06_30_2022-GO95MLD-1^06243005.0142700 | OTHER | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
992653539-539-DTLSB-06_29_2022-GO95MLD-1^06243005.0143502 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
151845369-30499-DTLSB-07_18_2022-GO95MLD-1^06243005.0144100 | OTHER | CA-NON-TIER | Distribution | 2022-07-18 | 2025-07-18 | 2
151845369-30499-DTLSB-07_18_2022-GRDRODHI-2^06243005.0144100 | OTHER | CA-NON-TIER | Distribution | 2022-07-18 | 2025-07-18 | 2
323075249-39439-DTLSB-06_29_2022-GO95MLD-1^06243005.0144401 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
66613209-66439-DTLSB-06_29_2022-GO95MLD-1^06243005.0146001 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
782250699-86439-DTLSB-06_29_2022-GO95MLD-1^06243005.0146100 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
815546129-98239-DTLSB-09_22_2022-GO95HV-1^06243005.0166001 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
631411219-59239-DTLSB-09_22_2022-XARMSPCR-1^06243005.0166100 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
876101808-93398-DTLSB-09_22_2022-GO95HV-1^06243005.0167601 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
157254159-78669-DTLSB-09_22_2022-GO95HV-1^06243005.0168902 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
226285818-52299-DTLSB-09_29_2022-GO95MLD-1^06243005.0185600 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
496426809-30621-DETAIL-06_01_2023-GO95MLD-1^06243009.0010500 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
496426809-30621-DETAIL-06_01_2023-SVCDEFLC-2^06243009.0010500 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
258815889-13721-DETAIL-06_01_2023-GO95MLD-1^06243009.0010506 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
77694798-42899-DETAIL-06_01_2023-GO95HV-1^06243009.0010507 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
77694798-42899-DETAIL-06_01_2023-GO95TCH-1^06243009.0010507 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
23210659-44189-DETAIL-06_01_2023-GO95TCH-1^06243009.0010601 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
23210659-44189-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0010601 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
689133729-72521-DETAIL-06_01_2023-GO95HV-1^06243009.0010602 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
295633489-87199-DTLSB-06_30_2022-GO95MLD-1^06243005.0233300 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2027-06-30 | 3
658642736-39498-DTLSB-06_30_2022-GO95HV-1^06243005.0235401 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2027-06-30 | 3
770610238-46528-DTLSB-07_21_2022-GO95MLD-1^06243005.0235901 | OTHER | CA-NON-TIER | Distribution | 2022-07-21 | 2025-07-21 | 2
566716209-94339-DTLSB-07_18_2022-GO95MLD-1^06243005.0237200 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
126622028-25339-DTLSB-06_30_2022-GO95HV-1^06243005.0237401 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2027-06-30 | 3
337800098-85099-DTLSB-07_19_2022-GO95MLD-1^06243005.0245000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
744690451-22539-DTLSB-07_19_2022-GO95MLD-1^06243005.0249000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
744690451-22539-DTLSB-07_19_2022-GRDRODHI-1^06243005.0249000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
707499246-49599-DTLSB-07_18_2022-GO95MLD-1^06243005.0250803 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
30113649-98721-DETAIL-06_01_2023-GO95MLD-1^06243009.0011502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
733182339-29221-DETAIL-06_01_2023-GO95MLD-1^06243009.0012502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
542548528-2108-AUDIT-08_29_2023-ABNDEQPM-1^06243009.0020002 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2026-08-29 | 2
835900291-81291-DETAIL-06_20_2023-GO95MLD-1^06243009.0022801 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
101519219-32129-DETAIL-06_05_2023-GO95MLD-1^06243009.0023301 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
213191299-48179-DETAIL-06_05_2023-GO95MLD-1^06243009.0023303 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
219642799-50129-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0024401 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
535467823-89269-DTLSB-07_18_2022-GO95MLD-1^06243005.0250805 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
452813863-639-DTLSB-07_18_2022-GO95MLD-1^06243005.0250901 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
859969613-17539-DTLSB-07_18_2022-GO95MLD-1^06243005.0252600 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
310444885-48289-DTLSB-07_18_2022-GO95MLD-1^06243005.0253503 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
782202762-72639-DTLSB-07_18_2022-GO95HV-1^06243005.0255300 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2027-07-18 | 3
10245262-13639-DTLSB-07_18_2022-GO95MLD-1^06243005.0255400 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2027-07-18 | 3
716474472-42639-DTLSB-07_18_2022-GO95MLD-1^06243005.0256300 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
596996889-64089-DTLSB-08_04_2022-GO95MLD-1^06243004.0212201 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2025-08-04 | 2
861387690-64989-DTLSB-08_09_2022-GO95MLD-1^06243004.0217402 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
829372120-58672-DTLSB-08_25_2022-GO95MLD-1^06243004.0218900 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2025-08-25 | 2
968741130-46039-DTLSB-08_09_2022-GO95MLD-1^06243004.0218902 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
472059230-36389-DTLSB-08_09_2022-GO95MLD-1^06243004.0218903 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
818234389-97339-DTLSB-08_23_2022-XARMSPCR-1^06243004.0233600 | CROSSARM | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
448836338-45038-DTLSB-08_23_2022-GO95CL10-1^06243004.0234201 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2027-08-23 | 3
397580970-75339-DTLSB-09_01_2022-GO95MLD-1^06243004.0234500 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
176387070-48989-DTLSB-09_01_2022-GO95MLD-1^06243004.0234501 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
892688239-54339-DTLSB-08_23_2022-ABNDEQPM-1^06243004.0236200 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2027-08-23 | 3
872963219-61889-DTLSB-08_23_2022-GO95MLD-1^06243004.0237200 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
132898799-23339-DTLSB-08_23_2022-RISEGRD-1^06243004.0238000 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
179581689-91289-DTLSB-08_23_2022-GO95MLD-1^06243004.0238001 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
448611889-3339-DTLSB-08_23_2022-XARMSPCR-1^06243004.0238002 | CROSSARM | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
530515759-31379-DTLSB-08_23_2022-GO95MLD-1^06243004.0238101 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
530515759-31379-AUDIT-10_31_2022-GRDRODHI-1^06243004.0238101 | OTHER | CA-NON-TIER | Distribution | 2022-10-31 | 2025-10-31 | 2
151755970-23439-DTLSB-08_22_2022-CONDCOIL-1^06243004.0239400 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2025-08-22 | 2
151755970-23439-DTLSB-08_22_2022-GO95MLD-1^06243004.0239400 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2025-08-22 | 2
13841769-68789-DTLSB-08_22_2022-GO95MLD-1^06243004.0239700 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2025-08-22 | 2
321161840-96439-DTLSB-08_22_2022-ABNDEQPM-1^06243004.0240841 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2027-08-22 | 3
819212540-50439-DTLSB-08_22_2022-ABNDEQPM-1^06243004.0240900 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2027-08-22 | 3
223049180-68439-DTLSB-08_25_2022-GO95HV-1^06243004.0256840 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2027-08-25 | 3
409575631-60489-DTLSB-08_09_2022-GO95MLD-1^06243004.0281100 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
286440468-12369-DTLSB-09_29_2022-GO95MLD-1^06243005.0089202 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
851461330-70871-DETAIL-05_30_2023-GO95MLD-1^06243009.0029906 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
171099412-71969-DETAIL-05_30_2023-GUYHINS-1^06243009.0029907 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
890239043-81489-DETAIL-06_27_2023-GO95MLD-1^06243009.0032800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
890239043-81489-DETAIL-06_27_2023-GRDRODHI-2^06243009.0032800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
216910583-77561-DETAIL-06_13_2023-GO95MLD-1^06243009.0037601 | OTHER | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
170835173-48489-DETAIL-06_14_2023-GO95HV-1^06243009.0038000 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
405609403-32099-DETAIL-06_13_2023-GRDRODHI-2^06243009.0038500 | OTHER | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
110240203-77329-DETAIL-06_13_2023-GO95MLD-1^06243009.0039500 | OTHER | CA-NON-TIER | Distribution | 2023-06-13 | 2028-06-13 | 3
115838693-97329-DETAIL-06_13_2023-GO95MLD-1^06243009.0039501 | OTHER | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
323502703-96329-DETAIL-06_27_2023-GO95MLD-1^06243009.0041800 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
323502703-96329-DETAIL-06_27_2023-GRDRODHI-1^06243009.0041800 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
447563311-64539-DTLSB-08_09_2022-GRDBROKE-1^06243004.0284500 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
252676461-59309-DTLSB-08_04_2022-GO95MLD-1^06243004.0286903 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2025-08-04 | 2
374407090-7489-DTLSB-08_10_2022-GO95MLD-1^06243004.0287900 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
614535649-82339-DTLSB-09_22_2022-GO95MLD-1^06243005.0100000 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
597576478-94939-DTLSB-09_22_2022-INSULDMG-1^06243005.0100002 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
849685468-35939-DTLSB-09_22_2022-GO95MLD-1^06243005.0101001 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
902883639-71209-DTLSB-09_19_2022-GO95MLD-1^06243005.0101801 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
493174188-7039-DTLSB-09_20_2022-GO95MLD-1^06243005.0102501 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
632390078-56039-DTLSB-09_20_2022-GO95MLD-1^06243005.0102503 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
239292729-99039-AUDIT-11_02_2022-GO95MLD-1^06243005.0102901 | OTHER | CA-NON-TIER | Distribution | 2022-11-02 | 2025-11-02 | 2
579377298-90289-DTLSB-09_22_2022-GO95MLD-1^06243005.0103100 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
357595768-95039-DTLSB-09_20_2022-GO95HV-1^06243005.0103501 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
534753038-95589-DTLSB-09_19_2022-GO95MLD-1^06243005.0103902 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
96978748-69039-DTLSB-09_19_2022-GO95MLD-1^06243005.0103903 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2027-09-19 | 3
418650028-27939-DTLSB-10_03_2022-INSULDMG-1^06243005.0105001 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
418650028-27939-DTLSB-10_03_2022-INSULDMG-2^06243005.0105001 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
318447258-1769-DTLSB-09_20_2022-XARMBRAC-1^06243005.0105501 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
47689409-90179-DTLSB-09_19_2022-INSULDMG-1^06243005.0105901 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
93715228-97939-DTLSB-10_03_2022-INSULDMG-1^06243005.0106000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
34630028-83189-DTLSB-09_20_2022-GO95MLD-1^06243005.0106501 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
385015328-52039-DTLSB-09_21_2022-GO95MLD-1^06243005.0108601 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2025-09-21 | 2
842963828-92039-DTLSB-09_21_2022-GO95HV-1^06243005.0108602 | OTHER | CA-NON-TIER | Distribution | 2022-09-21 | 2027-09-21 | 3
813726768-41039-DTLSB-09_20_2022-GO95HV-1^06243005.0109401 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
923845138-79998-DTLSB-09_20_2022-GO95HV-1^06243005.0109402 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2027-09-20 | 3
637849342-19479-DTLSB-09_06_2023-GRDRODHI-1^06243007.0202302 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
637849342-19479-DTLSB-09_06_2023-GRDRODHI-2^06243007.0202302 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
553457833-62109-DTLSB-09_06_2023-ABNDEQPM-1^06243007.0202700 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
196002303-84589-DTLSB-09_06_2023-GO95MLD-1^06243007.0203000 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
793862539-4241-DETAIL-06_02_2023-GO95MLD-1^06243009.0025106 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2028-06-02 | 3
475149091-13099-DETAIL-06_02_2023-GO95MLD-1^06243009.0025201 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
30683571-41589-DETAIL-06_02_2023-RISEBKSP-1^06243009.0025202 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
703542461-59679-DETAIL-06_05_2023-GO95MLD-1^06243009.0025300 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
69254239-65299-DETAIL-05_31_2023-GO95MLD-1^06243009.0025404 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
543193740-96679-DETAIL-05_31_2023-GO95HV-1^06243009.0025407 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2028-05-31 | 3
470977029-71089-DETAIL-05_31_2023-GO95HV-1^06243009.0025408 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2028-05-31 | 3
755709239-229-DETAIL-06_05_2023-GO95HV-1^06243009.0025412 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2028-06-05 | 3
752579970-41070-DTLSB-10_03_2022-GO95MLD-1^06243005.0121820 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2025-10-03 | 2
304964676-16676-DTLSB-10_03_2022-GO95HV-1^06243005.0121900 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2027-10-03 | 3
304964676-16676-DTLSB-10_03_2022-GO95MLD-1^06243005.0121900 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2025-10-03 | 2
304964676-16676-DTLSB-10_03_2022-GO95TCH-1^06243005.0121900 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2025-10-03 | 2
217870199-41779-DTLSB-06_29_2022-GO95MLD-1^06243005.0131001 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
287712531-81639-DTLSB-06_30_2022-GO95MLD-1^06243004.0302600 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2025-06-30 | 2
401114141-17369-DTLSB-07_18_2022-GO95MLD-1^06243004.0304400 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
822374034-4699-DTLSB-09_07_2022-GO95MLD-1^06243005.0010101 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
682628654-14739-DTLSB-09_07_2022-ABNDEQPM-1^06243005.0010700 | OTHER | CA-NON-TIER | Distribution | 2022-09-07 | 2027-09-07 | 3
146646154-3889-DTLSB-09_07_2022-GO95MLD-1^06243005.0011700 | OTHER | CA-NON-TIER | Distribution | 2022-09-07 | 2025-09-07 | 2
221537744-40789-DTLSB-09_07_2022-GO95MLD-1^06243005.0015500 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
808856047-69047-DTLSB-09_09_2022-GO95MLD-1^06243005.0016400 | OTHER | CA-TIER-2 | Distribution | 2022-09-09 | 2025-09-09 | 2
206586993-15289-AUDIT-10_31_2022-GO95MLD-1^06243005.0016802 | OTHER | CA-TIER-2 | Distribution | 2022-10-31 | 2027-10-31 | 3
930285146-16146-DTLTRT-06_29_2022-GO95HV-1^06243005.0132001 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2027-06-29 | 3
151845369-30499-DTLSB-07_18_2022-GRDRODHI-1^06243005.0144100 | OTHER | CA-NON-TIER | Distribution | 2022-07-18 | 2025-07-18 | 2
468119069-87439-DTLSB-07_18_2022-GO95MLD-1^06243005.0144101 | OTHER | CA-NON-TIER | Distribution | 2022-07-18 | 2025-07-18 | 2
600927959-8439-DTLSB-07_18_2022-GO95HV-1^06243005.0144200 | OTHER | CA-NON-TIER | Distribution | 2022-07-18 | 2027-07-18 | 3
723320439-89439-DTLSB-06_29_2022-GO95MLD-1^06243005.0144400 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
614895978-27439-DTLSB-07_21_2022-POLETOP-1^06243005.0145000 | POLE | CA-NON-TIER | Distribution | 2022-07-21 | 2025-07-21 | 2
611158168-17439-DTLSB-07_21_2022-POLETOP-1^06243005.0146000 | POLE | CA-NON-TIER | Distribution | 2022-07-21 | 2025-07-21 | 2
719227028-51339-DTLSB-09_22_2022-XARMSPCR-1^06243005.0167500 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
472511933-13639-DTLSB-09_20_2022-GO95MLD-1^06243005.0016902 | OTHER | CA-NON-TIER | Distribution | 2022-09-20 | 2025-09-20 | 2
666229551-81651-DTLSB-09_20_2022-GO95TCH-1^06243005.0017802 | OTHER | CA-TIER-2 | Distribution | 2022-09-20 | 2025-09-20 | 2
98016213-36529-DTLSB-08_31_2023-GO95HV-1^06243007.0293301 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
380888403-35529-DTLSB-08_31_2023-GO95HV-1^06243007.0293601 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
242896923-11189-DTLSB-08_31_2023-ABNDEQPM-1^06243007.0294200 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
19738813-10629-DTLSB-08_31_2023-GO95HV-1^06243007.0320101 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
901594903-59529-DTLSB-08_31_2023-GO95HV-1^06243007.0320400 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
287263093-68079-DTLSB-08_31_2023-GO95MLD-1^06243007.0320401 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2026-08-31 | 2
208212583-19529-DTLSB-08_31_2023-GO95HV-1^06243007.0320601 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
691558036-69036-DTLSB-08_31_2023-GO95HV-1^06243008.0025700 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
212253591-43229-DETAIL-06_06_2023-GO95CL10-1^06243009.0026001 | OTHER | CA-NON-TIER | Distribution | 2023-06-06 | 2028-06-06 | 3
498865098-40309-DETAIL-06_05_2023-GO95MLD-1^06243009.0026004 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
44945819-7799-DETAIL-06_05_2023-GO95BLTC-2^06243009.0026100 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2028-06-05 | 3
44945819-7799-DETAIL-06_05_2023-GO95MLD-1^06243009.0026100 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2028-06-05 | 3
668408614-65269-DTLSB-09_27_2022-GO95MLD-1^06243005.0026800 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
386316144-62939-DTLSB-09_26_2022-GO95MLD-1^06243005.0030503 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
69438228-42339-DTLSB-09_22_2022-GO95MLD-1^06243005.0167600 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
826428769-68669-DTLSB-09_22_2022-GO95HV-1^06243005.0168901 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
915690598-46239-DTLSB-09_28_2022-CONDFRAY-1^06243005.0187601 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-09-28 | 2025-09-28 | 2
382603478-69399-DTLSB-09_29_2022-GO95MLD-1^06243005.0192501 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
591450249-69189-DTLSB-09_22_2022-GO95MLD-1^06243005.0216800 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2025-09-22 | 2
993537739-58239-DTLSB-09_22_2022-GO95HV-1^06243005.0216901 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
58323049-48339-DTLSB-06_30_2022-GO95MLD-1^06243005.0234301 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2025-06-30 | 2
503807619-74339-DTLSB-06_30_2022-GUYHINS-1^06243005.0237202 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-30 | 2025-06-30 | 2
126622028-25339-DTLSB-06_30_2022-GO95MLD-1^06243005.0237401 | OTHER | CA-TIER-2 | Distribution | 2022-06-30 | 2025-06-30 | 2
154631498-6339-DTLSB-06_30_2022-GO95MLD-1^06243005.0237600 | OTHER | CA-NON-TIER | Distribution | 2022-06-30 | 2027-06-30 | 3
295659398-36339-DTLSB-06_30_2022-GO95HV-1^06243005.0237601 | OTHER | CA-NON-TIER | Distribution | 2022-06-30 | 2027-06-30 | 3
101337489-45689-DTLSB-07_18_2022-GO95MLD-1^06243005.0240000 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
66953174-64174-DTLSB-07_18_2022-GUYHINS-1^06243005.0240001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
375114119-2439-DTLSB-06_29_2022-GO95HV-1^06243005.0240901 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2027-06-29 | 3
551856636-52709-DTLSB-06_29_2022-GO95MLD-1^06243005.0240902 | OTHER | CA-NON-TIER | Distribution | 2022-06-29 | 2025-06-29 | 2
647061638-28199-DTLSB-07_19_2022-GO95MLD-1^06243005.0244000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
877071744-12939-DTLSB-09_27_2022-XARMSPCR-1^06243005.0030504 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
139747824-78839-DTLSB-09_08_2022-GO95HV-1^06243005.0034701 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2027-09-08 | 3
535182761-94761-DTLSB-09_08_2022-GO95MLD-1^06243005.0034820 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2027-09-08 | 3
295634105-89579-DTLSB-09_08_2022-CLRTOUCH-2^06243005.0037200 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
853583544-95839-DTLSB-09_08_2022-GUYNOINS-2^06243005.0037300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
363859955-92839-DTLSB-09_08_2022-GO95MLD-1^06243005.0038400 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
427442092-48429-DTLSB-09_01_2022-GO95MLD-1^06243004.0058001 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
263733251-79389-DTLSB-09_07_2022-GO95MLD-1^06243004.0060400 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
854804219-45219-DTLSB-09_07_2022-GO95HV-1^06243004.0060502 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2027-09-07 | 3
748667660-40279-DTLSB-09_08_2022-GO95MLD-1^06243004.0061600 | OTHER | CA-TIER-2 | Distribution | 2022-09-08 | 2025-09-08 | 2
202965528-86529-DTLSB-09_07_2022-GUYNOINS-1^06243004.0061603 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
202965528-86529-DTLSB-09_07_2022-GUYNOINS-2^06243004.0061603 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
825669990-28589-DTLSB-09_07_2022-GO95MLD-1^06243004.0062500 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
288627548-85529-DTLSB-09_07_2022-GO95HV-1^06243004.0062501 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2027-09-07 | 3
591818921-66189-DTLSB-09_06_2022-GO95MLD-1^06243004.0063100 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
344520961-8379-DTLSB-09_22_2022-GO95TCH-1^06243004.0063400 | OTHER | CA-TIER-2 | Distribution | 2022-09-22 | 2025-09-22 | 2
861157078-15529-DTLSB-09_26_2022-GO95HV-1^06243004.0063402 | OTHER | CA-TIER-2 | Distribution | 2022-09-26 | 2027-09-26 | 3
55833341-4652-DTLSB-09_20_2022-GO95MLD-1^06243004.0063440 | OTHER | CA-TIER-2 | Distribution | 2022-09-20 | 2025-09-20 | 2
872963219-61889-DTLSB-08_23_2022-GO95HV-1^06243004.0237200 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2027-08-23 | 3
965357819-23389-DTLSB-08_23_2022-GO95MLD-1^06243004.0237300 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
501059030-37439-DTLSB-08_23_2022-GO95MLD-1^06243004.0240100 | OTHER | CA-NON-TIER | Distribution | 2022-08-23 | 2025-08-23 | 2
748004891-35629-DTLSB-09_06_2022-GO95MLD-1^06243004.0063501 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
77438931-50442-DTLSB-08_31_2022-GO95MLD-1^06243004.0063640 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
321458831-27242-DTLSB-08_31_2022-GO95MLD-1^06243004.0063643 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
321458831-27242-DTLSB-08_31_2022-GRDRODHI-1^06243004.0063643 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
321458831-27242-DTLSB-08_31_2022-GRDRODHI-2^06243004.0063643 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
613414681-41199-DTLSB-08_31_2022-GO95MLD-1^06243004.0063740 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
748212571-59442-DTLSB-09_06_2022-GO95MLD-1^06243004.0064240 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
541042080-62979-DTLSB-08_31_2022-GO95MLD-1^06243004.0064400 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
845531290-50479-DTLSB-08_25_2022-GO95MLD-1^06243004.0256841 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2025-08-25 | 2
845531290-50479-DTLSB-08_25_2022-GRDRODHI-1^06243004.0256841 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2025-08-25 | 2
579673401-1489-DTLSB-08_25_2022-GO95MLD-1^06243004.0280500 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2025-08-25 | 2
285847921-10499-DTLSB-08_09_2022-GO95MLD-1^06243004.0281200 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
285847921-10499-DTLSB-08_09_2022-GUYSLACK-1^06243004.0281200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
285847921-10499-ADMIN-11_18_2022-GO95HV-1^06243004.0281200 | OTHER | CA-NON-TIER | Distribution | 2022-11-18 | 2027-11-18 | 3
544721681-59539-DTLSB-08_09_2022-GO95HV-1^06243004.0282400 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2027-08-09 | 3
265475811-86489-DTLSB-08_09_2022-GO95MLD-1^06243004.0282402 | OTHER | CA-NON-TIER | Distribution | 2022-08-09 | 2025-08-09 | 2
266814938-90518-DTLSB-08_31_2022-GUYNOINS-2^06243004.0064602 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
128808451-35742-DTLSB-08_31_2022-GO95MLD-1^06243004.0064640 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
337812981-57942-DTLSB-09_06_2022-GO95MLD-1^06243004.0065240 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
669150061-77342-DTLSB-08_31_2022-GO95HV-1^06243004.0065341 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2027-08-31 | 3
12401009-33089-DTLSB-09_06_2022-GO95MLD-1^06243004.0065401 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
507698744-59744-DTLTRT-09_06_2022-GO95TCH-1^06243004.0065402 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
157884363-41429-DETAIL-06_27_2023-SVCDEFLC-1^06243009.0047900 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
157884363-41429-DETAIL-06_27_2023-SVCWIND-1^06243009.0047900 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
412582163-42479-DETAIL-06_27_2023-GO95MLD-1^06243009.0047901 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
968845314-56699-DTLSB-07_25_2023-GO95MLD-1^06243009.0052501 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
139977174-49429-DTLSB-07_25_2023-SVCDEFLC-1^06243009.0053002 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
139977174-49429-DTLSB-07_25_2023-SVCDEFLC-2^06243009.0053002 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
609420473-59429-DTLSB-07_25_2023-GO95MLD-1^06243009.0053003 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
441105877-27877-DTLSB-07_25_2023-GUYHINS-1^06243009.0053500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
519010384-68989-DTLSB-07_25_2023-GO95MLD-1^06243009.0053501 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
519010384-68989-DTLSB-07_25_2023-GO95TCH-1^06243009.0053501 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
846447711-85499-DTLSB-08_31_2022-GO95MLD-1^06243004.0067601 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
676161491-29789-DTLSB-08_31_2022-GO95MLD-1^06243004.0067642 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
591411721-25452-DTLSB-08_31_2022-GO95MLD-1^06243004.0067643 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
682882212-13629-DTLSB-08_31_2022-GO95MLD-1^06243004.0067740 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
830850579-71529-DTLSB-09_01_2022-GO95HV-1^06243004.0068101 | OTHER | CA-TIER-2 | Distribution | 2022-09-01 | 2027-09-01 | 3
236002721-27452-DTLSB-08_31_2022-GUYNOINS-1^06243004.0069040 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-31 | 2025-08-31 | 2
236002721-27452-DTLSB-08_31_2022-GUYNOINS-2^06243004.0069040 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-31 | 2025-08-31 | 2
901719694-99694-DTLSB-08_24_2022-GO95HV-1^06243004.0072402 | OTHER | CA-TIER-2 | Distribution | 2022-08-24 | 2027-08-24 | 3
217679432-87989-DTLSB-08_23_2022-GO95MLD-1^06243004.0073400 | OTHER | CA-TIER-2 | Distribution | 2022-08-23 | 2025-08-23 | 2
383383902-81269-DTLSB-10_03_2022-GO95MLD-1^06243004.0074301 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2025-10-03 | 2
680000952-79089-DTLSB-08_10_2022-ABNDEQPM-1^06243004.0076200 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2027-08-10 | 3
610793082-21729-DTLSB-08_10_2022-GO95HV-1^06243004.0076402 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2027-08-10 | 3
257296092-11729-DTLSB-08_10_2022-GUYNOINS-2^06243004.0076500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-08-10 | 2025-08-10 | 2
421163362-33489-DTLSB-08_24_2022-GO95MLD-1^06243004.0078503 | OTHER | CA-TIER-2 | Distribution | 2022-08-24 | 2025-08-24 | 2
298983462-53729-DTLSB-08_24_2022-GO95HV-1^06243004.0078600 | OTHER | CA-TIER-2 | Distribution | 2022-08-24 | 2027-08-24 | 3
385576412-87629-DTLSB-08_10_2022-GRDRODHI-1^06243004.0079002 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2025-08-10 | 2
465959252-4729-DTLSB-08_24_2022-GO95HV-1^06243004.0079701 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2027-08-24 | 3
655850611-33379-DTLSB-08_24_2022-GO95MLD-1^06243004.0079702 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
826762742-54729-DTLSB-08_24_2022-GUYSLACK-1^06243004.0079801 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
598799732-25882-DTLSB-09_01_2022-GO95HV-1^06243004.0080900 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2027-09-01 | 3
603961262-40529-DTLSB-09_01_2022-INSULDMG-1^06243004.0083900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
508971862-98679-DTLSB-09_01_2022-INSULDMG-1^06243004.0084903 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
633744813-30499-DTLSB-09_28_2022-GO95HV-1^06243004.0085000 | OTHER | CA-NON-TIER | Distribution | 2022-09-28 | 2027-09-28 | 3
137126992-68429-DTLSB-09_01_2022-GRDRODHI-1^06243004.0088900 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
127005383-64429-DTLSB-08_30_2022-GO95HV-1^06243004.0089501 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2027-08-30 | 3
731928178-40802-DTLSB-09_26_2022-INSULDMG-1^06243005.0049401 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
361536478-81202-DTLSB-09_26_2022-GO95HV-1^06243005.0049501 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
702044258-73102-DTLSB-09_26_2022-GO95HV-1^06243005.0049502 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
87783348-43139-DTLSB-10_03_2022-GO95HV-1^06243005.0052801 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2027-10-03 | 3
624468078-23139-DTLSB-09_26_2022-GO95HV-1^06243005.0058900 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
750805088-15579-DTLSB-09_26_2022-GUYHINS-1^06243005.0059800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
830255990-88409-DTLSB-09_29_2022-GO95HV-1^06243005.0088200 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2027-09-29 | 3
307230518-76139-DTLSB-09_29_2022-INSULDMG-1^06243005.0088301 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
475196638-87509-DTLSB-09_29_2022-GO95MLD-1^06243005.0088302 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
475196638-87509-DTLSB-09_29_2022-GUYHINS-1^06243005.0088302 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
64985488-14139-DTLSB-09_29_2022-GUYNOINS-1^06243005.0089203 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-09-29 | 2025-09-29 | 2
108957958-5139-DTLSB-09_29_2022-GO95HV-1^06243005.0089300 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2027-09-29 | 3
822374034-4699-DTLSB-09_07_2022-GRDRODHI-2^06243005.0010101 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
306409584-51689-DTLSB-09_09_2022-GO95MLD-1^06243005.0011301 | OTHER | CA-TIER-2 | Distribution | 2022-09-09 | 2025-09-09 | 2
193032444-6199-DTLSB-09_19_2022-GO95HV-1^06243005.0014200 | OTHER | CA-TIER-2 | Distribution | 2022-09-19 | 2027-09-19 | 3
193032444-6199-DTLSB-09_19_2022-GO95MLD-1^06243005.0014200 | OTHER | CA-TIER-2 | Distribution | 2022-09-19 | 2025-09-19 | 2
745313203-84599-DTLSB-09_09_2022-GO95MLD-1^06243005.0016401 | OTHER | CA-TIER-2 | Distribution | 2022-09-09 | 2025-09-09 | 2
259497031-77739-DTLSB-09_20_2022-GO95HV-1^06243005.0017801 | OTHER | CA-TIER-2 | Distribution | 2022-09-20 | 2027-09-20 | 3
124188623-28739-DTLSB-09_20_2022-COPLLEAN-1^06243005.0017900 | POLE | CA-TIER-2 | Distribution | 2022-09-20 | 2025-09-20 | 2
761334473-56739-DTLSB-09_21_2022-GUYNOINS-2^06243005.0018701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-09-21 | 2025-09-21 | 2
309588363-67739-DTLSB-09_20_2022-GO95MLD-1^06243005.0019700 | OTHER | CA-TIER-2 | Distribution | 2022-09-20 | 2025-09-20 | 2
678396564-88739-DTLSB-09_27_2022-GO95MLD-1^06243005.0021502 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
678396564-88739-DTLSB-09_27_2022-GRDRODHI-1^06243005.0021502 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
574887421-48421-DTLSB-09_22_2022-GO95HV-1^06243005.0022200 | OTHER | CA-NON-TIER | Distribution | 2022-09-22 | 2027-09-22 | 3
409643375-34375-DTLSB-10_03_2022-GO95HV-1^06243005.0023300 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2027-10-03 | 3
670336375-17375-DTLSB-10_03_2022-GO95HV-1^06243005.0023301 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2027-10-03 | 3
730864708-23039-DTLSB-10_03_2022-GO95MLD-1^06243005.0023800 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
599089303-42739-DTLSB-10_03_2022-GO95MLD-1^06243005.0023802 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
688382693-87289-DTLSB-10_03_2022-GO95MLD-1^06243005.0023803 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
207472963-96689-DTLSB-10_03_2022-GO95MLD-1^06243005.0023901 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
245770904-15122-DTLSB-10_03_2022-GO95HV-1^06243005.0024801 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2027-10-03 | 3
530813500-65500-DTLSB-09_19_2022-GO95MLD-1^06243005.0025020 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
731978500-79500-DTLSB-09_19_2022-GO95MLD-1^06243005.0025021 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
386316144-62939-DTLSB-09_26_2022-GO95STUB-1^06243005.0030503 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
520169108-21789-DTLSB-08_30_2022-CLRTOUCH-1^06243004.0093800 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
571500238-11989-DTLSB-09_27_2022-GO95MLD-1^06243004.0094901 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
248328237-80889-DTLSB-08_30_2022-GO95HV-1^06243004.0096800 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2027-08-30 | 3
211844047-58329-DTLSB-08_30_2022-GO95MLD-1^06243004.0097801 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
620457648-94139-DTLSB-09_29_2022-GO95HV-1^06243005.0089401 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2027-09-29 | 3
310708238-35139-DTLSB-09_29_2022-GO95HV-1^06243005.0089500 | OTHER | CA-NON-TIER | Distribution | 2022-09-29 | 2027-09-29 | 3
647061638-28199-DTLSB-07_19_2022-GRDRODHI-1^06243005.0244000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
707499246-49599-DTLSB-07_18_2022-GRDRODHI-1^06243005.0250803 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
707499246-49599-AUDIT-07_27_2022-GO95HV-1^06243005.0250803 | OTHER | CA-TIER-2 | Distribution | 2022-07-27 | 2027-07-27 | 3
99365104-35669-DTLSB-07_18_2022-GO95HV-1^06243005.0254400 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2027-07-18 | 3
575147072-81639-DTLSB-07_18_2022-GO95MLD-1^06243005.0257300 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
157997809-85239-ADMIN-04_12_2023-POLEREPL-1^06243006.0300200 | POLE | CA-NON-TIER | Distribution | 2023-04-12 | 2026-04-12 | 2
462726413-69429-DTLSB-09_06_2023-GO95HV-1^06243007.0171100 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
292945813-80979-DTLSB-09_06_2023-ABNDEQPM-1^06243007.0171101 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
292945813-80979-AUDIT-10_09_2023-GO95BLTC-1^06243007.0171101 | OTHER | CA-TIER-2 | Distribution | 2023-10-09 | 2028-10-09 | 3
609890837-42837-DTLSB-08_25_2023-GO95MLD-1^06243007.0180900 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2026-08-25 | 2
690604244-41939-DTLSB-09_27_2022-XARMSPCR-1^06243005.0031400 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
598841934-90939-DTLSB-09_27_2022-XARMBRAC-1^06243005.0032401 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
785160954-65689-DTLSB-09_27_2022-GO95MLD-1^06243005.0033300 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
346211124-50939-DTLSB-09_27_2022-XARMSPCR-1^06243005.0033400 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
383157961-61869-DTLSB-09_19_2022-GO95MLD-1^06243005.0034001 | OTHER | CA-NON-TIER | Distribution | 2022-09-19 | 2025-09-19 | 2
202926524-48839-DTLSB-09_08_2022-INSULDMG-1^06243005.0034500 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
295634105-89579-DTLSB-09_08_2022-CLRTOUCH-1^06243005.0037200 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
17333152-49828-DTLSB-08_24_2022-GO95MLD-1^06243004.0106300 | OTHER | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
521015213-86239-DTLSB-08_11_2022-GO95HV-1^06243004.0131102 | OTHER | CA-NON-TIER | Distribution | 2022-08-11 | 2027-08-11 | 3
81313653-55139-DTLSB-08_22_2022-GRDBROKE-1^06243004.0136101 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2025-08-22 | 2
215006073-30799-DTLSB-08_25_2022-GO95MLD-1^06243004.0137001 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2025-08-25 | 2
676878213-70189-DTLSB-08_22_2022-GO95MLD-1^06243004.0139100 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2025-08-22 | 2
55833341-4652-DTLSB-09_20_2022-GO95TCH-1^06243004.0063440 | OTHER | CA-TIER-2 | Distribution | 2022-09-20 | 2025-09-20 | 2
957331741-93552-DTLSB-08_31_2022-GO95MLD-1^06243004.0063541 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
570589631-28452-DTLSB-08_31_2022-GUYNOINS-1^06243004.0063642 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
570589631-28452-DTLSB-08_31_2022-GUYNOINS-2^06243004.0063642 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
377532760-64629-DTLSB-08_31_2022-GO95MLD-1^06243004.0063701 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2027-08-31 | 3
184295171-76789-DTLSB-08_31_2022-GO95MLD-1^06243004.0063741 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
184295171-76789-DTLSB-08_31_2022-SVCROAD-1^06243004.0063741 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
422375198-48599-DTLSB-08_31_2022-GO95MLD-1^06243004.0064500 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
266814938-90518-DTLSB-08_31_2022-GUYNOINS-1^06243004.0064602 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
128808451-35742-DTLSB-08_31_2022-GUYHINS-1^06243004.0064640 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
115518471-10442-DTLSB-09_06_2022-GO95HV-1^06243004.0065340 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2027-09-06 | 3
128571580-79529-DTLSB-09_06_2022-GO95HV-1^06243004.0066201 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2027-09-06 | 3
304757375-41699-DETAIL-02_03_2021-GO95MLD-1^06242009.0054400 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2024-02-03 | 2
116035368-30629-AUDIT-02_22_2021-GO95HV-1^06242009.0054901 | OTHER | CA-TIER-2 | Distribution | 2021-02-22 | 2026-02-22 | 3
957065180-95769-DETAIL-02_02_2021-GO95HV-1^06242009.0055203 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
689298444-65219-DETAIL-02_03_2021-GO95TCH-1^06242009.0055302 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2024-02-03 | 2
737693690-99789-DTLSB-09_06_2022-GO95MLD-1^06243004.0066301 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
210452681-66489-DTLSB-08_31_2022-GO95MLD-1^06243004.0066640 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
910497981-39689-DTLSB-08_31_2022-GO95MLD-1^06243004.0066641 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
406430991-93769-DTLSB-08_31_2022-GO95MLD-1^06243004.0066700 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
956024650-53529-DTLSB-09_06_2022-GO95MLD-1^06243004.0067102 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
89989031-74469-DTLSB-09_06_2022-GO95HV-1^06243004.0067400 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2027-09-06 | 3
908320721-48529-DTLSB-08_31_2022-GO95MLD-1^06243004.0067600 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
535663919-8529-DTLSB-08_31_2022-GO95MLD-1^06243004.0067602 | OTHER | CA-TIER-2 | Distribution | 2022-08-31 | 2025-08-31 | 2
377585274-12499-DETAIL-02_03_2021-GO95MLD-1^06242009.0055400 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2024-02-03 | 2
377585274-12499-DETAIL-02_03_2021-GO95TCH-1^06242009.0055400 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2024-02-03 | 2
649305594-46219-DETAIL-02_02_2021-GO95MLD-1^06242009.0056200 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
475695435-26219-DETAIL-02_02_2021-GO95MLD-1^06242009.0056201 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
342877345-7219-ADMIN-03_03_2023-POLEREPL-1^06242009.0057300 | POLE | CA-TIER-2 | Distribution | 2023-03-03 | 2024-03-03 | 2
835971479-38529-DTLSB-09_06_2022-GO95MLD-1^06243004.0069400 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2025-09-06 | 2
664898169-10099-DTLSB-09_06_2022-ABNDEQPM-1^06243004.0069401 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2027-09-06 | 3
982865201-55269-DTLSB-09_06_2022-GO95TCH-1^06243004.0069500 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2025-09-06 | 2
177037853-62239-DTLSB-08_11_2022-GRDBROKE-1^06243004.0139802 | OTHER | CA-NON-TIER | Distribution | 2022-08-11 | 2025-08-11 | 2
122159163-73589-DTLSB-08_11_2022-GO95MLD-1^06243004.0139901 | OTHER | CA-NON-TIER | Distribution | 2022-08-11 | 2025-08-11 | 2
641680899-78239-DTLSB-08_25_2022-GO95MLD-1^06243004.0147142 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2025-08-25 | 2
597211308-43542-DTLSB-08_24_2022-GUYLOINS-1^06243004.0156900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-24 | 2025-08-24 | 2
941871786-22786-DTLSB-08_01_2022-CONDCOIL-1^06243004.0161640 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
824412219-63379-DTLSB-08_01_2022-ABNDEQPM-1^06243004.0163641 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2027-08-01 | 3
424857559-14929-DTLSB-07_28_2022-GO95MLD-1^06243004.0166401 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
222772879-55909-DTLSB-07_28_2022-GO95MLD-1^06243004.0167500 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
243797675-10775-DTLSB-07_28_2022-GO95HV-1^06243004.0168602 | OTHER | CA-NON-TIER | Distribution | 2022-07-28 | 2027-07-28 | 3
789395859-79929-DTLSB-07_28_2022-GUYNOINS-1^06243004.0168902 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
369948119-29929-DTLSB-07_28_2022-GUYSLACK-1^06243004.0169902 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
295634105-89579-DTLSB-09_08_2022-GO95MLD-1^06243005.0037200 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2027-09-08 | 3
257296092-11729-DTLSB-08_10_2022-GUYNOINS-1^06243004.0076500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-08-10 | 2025-08-10 | 2
151327052-68629-DTLSB-08_10_2022-GO95HV-1^06243004.0077202 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2027-08-10 | 3
136181682-19089-DTLSB-08_24_2022-ABNDEQPM-1^06243004.0077402 | OTHER | CA-TIER-2 | Distribution | 2022-08-24 | 2027-08-24 | 3
424608192-96989-DTLSB-08_10_2022-GO95MLD-1^06243004.0078101 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2025-08-10 | 2
424608192-96989-DTLSB-08_10_2022-SVCROAD-1^06243004.0078101 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2025-08-10 | 2
361971692-90589-DTLSB-08_10_2022-GO95MLD-1^06243004.0078103 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2025-08-10 | 2
385576412-87629-DTLSB-08_10_2022-GRDRODHI-2^06243004.0079002 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2025-08-10 | 2
935618342-22729-DTLSB-08_24_2022-GO95MLD-1^06243004.0079400 | OTHER | CA-TIER-2 | Distribution | 2022-08-24 | 2025-08-24 | 2
795967102-15489-DTLSB-08_24_2022-GO95MLD-1^06243004.0079401 | OTHER | CA-TIER-2 | Distribution | 2022-08-24 | 2025-08-24 | 2
655850611-33379-AUDIT-10_31_2022-GRDRODHI-1^06243004.0079702 | OTHER | CA-NON-TIER | Distribution | 2022-10-31 | 2025-10-31 | 2
508971862-98679-DTLSB-09_01_2022-GO95MLD-1^06243004.0084903 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
847682972-75089-DTLSB-08_30_2022-GO95MLD-1^06243004.0086600 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
485459595-27872-DTLSB-08_10_2022-GO95HV-1^06243004.0087040 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2027-08-10 | 3
812681805-62569-DTLSB-09_01_2022-GO95MLD-1^06243004.0087140 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
695216350-55569-DTLSB-08_30_2022-GO95HV-1^06243004.0087700 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2027-08-30 | 3
652889482-88429-DTLSB-09_01_2022-GO95HV-1^06243004.0087901 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2027-09-01 | 3
970624997-80019-DETAIL-02_08_2021-GO95MLD-1^06242009.0067901 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
575725968-58469-DETAIL-02_03_2021-GO95HV-1^06242009.0068101 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
575725968-58469-DETAIL-02_03_2021-GO95MLD-1^06242009.0068101 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
938629738-5019-DETAIL-02_04_2021-GO95MLD-1^06242009.0068702 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2024-02-04 | 2
929555897-35019-DETAIL-02_04_2021-GO95MLD-1^06242009.0068803 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
887974934-10869-DETAIL-02_04_2021-GO95TCH-1^06242009.0068904 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2024-02-04 | 2
758556159-30869-DETAIL-02_04_2021-GO95TCH-1^06242009.0069600 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2024-02-04 | 2
149401664-35389-DTLSB-08_31_2023-GO95MLD-1^06243008.0025801 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
849763493-75629-DTLSB-08_31_2023-GO95MLD-1^06243008.0025802 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
24923753-87629-DTLSB-09_07_2023-GO95HV-1^06243008.0026100 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
112481173-37629-DTLSB-09_07_2023-GO95HV-1^06243008.0026200 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
237720273-96629-DTLSB-09_07_2023-GO95HV-1^06243008.0026301 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
306231916-3916-DTLSB-08_31_2023-GO95HV-1^06243008.0026600 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
608686921-97921-DTLSB-08_31_2023-GO95MLD-1^06243008.0027900 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
362044152-99431-DETAIL-07_12_2023-GO95MLD-1^06243008.0054800 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
541598909-19129-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026404 | OTHER | CA-NON-TIER | Distribution | 2023-06-02 | 2026-06-02 | 2
440131131-60229-DETAIL-05_31_2023-CLMBTRE-1^06243009.0026410 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
440131131-60229-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0026410 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
811020997-90499-ADMIN-03_01_2023-POLEREPL-1^06242009.0069906 | POLE | CA-TIER-2 | Distribution | 2023-03-01 | 2024-03-01 | 2
661852583-68869-DETAIL-02_08_2021-GO95MLD-1^06242009.0082000 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
365736783-57119-DETAIL-02_08_2021-GO95HV-1^06242009.0082001 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2026-02-08 | 3
365736783-57119-DETAIL-02_08_2021-GO95MLD-1^06242009.0082001 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
137126992-68429-DTLSB-09_01_2022-GO95MLD-1^06243004.0088900 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
137126992-68429-DTLSB-09_01_2022-GRDRODHI-2^06243004.0088900 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
137126992-68429-DTLSB-09_01_2022-SVCROAD-1^06243004.0088900 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
520169108-21789-DTLSB-08_30_2022-GO95MLD-1^06243004.0093800 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
533523728-53889-DTLSB-09_01_2022-GO95MLD-1^06243004.0095900 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
237428117-30389-DTLSB-09_01_2022-GO95MLD-1^06243004.0099600 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
817795165-44519-DETAIL-02_05_2021-GO95MLD-1^06242009.0125200 | OTHER | CA-TIER-2 | Distribution | 2021-02-05 | 2024-02-05 | 2
650982720-70819-DETAIL-02_15_2021-SVCROAD-1^06242009.0159900 | OTHER | CA-NON-TIER | Distribution | 2021-02-15 | 2024-02-15 | 2
140041974-91119-DETAIL-02_17_2021-SVCENTCO-1^06242009.0207500 | OTHER | CA-TIER-2 | Distribution | 2021-02-17 | 2024-02-17 | 2
262772734-51119-DETAIL-02_10_2021-CLRTOUCH-1^06242009.0208701 | CONDUCTOR | CA-NON-TIER | Distribution | 2021-02-10 | 2024-02-10 | 2
262772734-51119-DETAIL-02_10_2021-GO95CLSV-1^06242009.0208701 | OTHER | CA-NON-TIER | Distribution | 2021-02-10 | 2024-02-10 | 2
262772734-51119-DETAIL-02_10_2021-XARMSPCR-1^06242009.0208701 | CROSSARM | CA-NON-TIER | Distribution | 2021-02-10 | 2024-02-10 | 2
385652594-11119-ADMIN-08_02_2023-POLEREPL-1^06242009.0209700 | POLE | CA-NON-TIER | Distribution | 2023-08-02 | 2026-08-02 | 2
21954980-34309-DETAIL-02_17_2021-XARMSPCR-1^06242009.0221600 | CROSSARM | CA-NON-TIER | Distribution | 2021-02-17 | 2024-02-17 | 2
654452740-73079-ADMIN-07_24_2023-POLEREPL-1^06242009.0246903 | POLE | CA-NON-TIER | Distribution | 2023-07-24 | 2026-07-24 | 2
648847996-15599-DETAIL-08_24_2021-SVCDEFLC-1^06242009.0248903 | OTHER | CA-NON-TIER | Distribution | 2021-08-24 | 2024-08-24 | 2
932045978-86029-DETAIL-08_03_2021-GO95HV-1^06242009.0280211 | OTHER | CA-NON-TIER | Distribution | 2021-08-03 | 2026-08-03 | 3
932045978-86029-DETAIL-08_03_2021-GO95MLD-1^06242009.0280211 | OTHER | CA-NON-TIER | Distribution | 2021-08-03 | 2024-08-03 | 2
932045978-86029-DETAIL-08_03_2021-XARMSPCR-1^06242009.0280211 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-03 | 2024-08-03 | 2
61656285-46029-DETAIL-08_03_2021-GO95MLD-1^06242009.0281301 | OTHER | CA-NON-TIER | Distribution | 2021-08-03 | 2024-08-03 | 2
61656285-46029-DETAIL-08_03_2021-XARMSPCR-1^06242009.0281301 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-03 | 2024-08-03 | 2
388202543-57699-DTLSB-08_22_2022-GO95MLD-1^06243004.0136102 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2025-08-22 | 2
533981605-51821-DTLSB-08_22_2022-GO95MLD-1^06243004.0137400 | OTHER | CA-NON-TIER | Distribution | 2022-08-22 | 2025-08-22 | 2
172199263-43239-DTLSB-08_11_2022-GO95MLD-1^06243004.0139900 | OTHER | CA-NON-TIER | Distribution | 2022-08-11 | 2025-08-11 | 2
833836179-20339-DTLSB-08_25_2022-GO95HV-1^06243004.0145200 | OTHER | CA-NON-TIER | Distribution | 2022-08-25 | 2027-08-25 | 3
120091328-41089-DETAIL-04_12_2021-GO95MLD-1^06241009.0323301 | OTHER | CA-TIER-2 | Distribution | 2021-04-12 | 2026-04-12 | 3
716052981-6981-DETAIL-04_12_2021-GO95BLTC-1^06241009.0323602 | OTHER | CA-TIER-2 | Distribution | 2021-04-12 | 2026-04-12 | 3
789973046-22299-DETAIL-04_08_2021-GO95MLD-1^06241009.0326607 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2026-04-08 | 3
338783004-48129-DETAIL-06_16_2022-GO95MLD-1^06242006.0247600 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
742781711-63711-DTLSB-08_31_2023-GO95MLD-1^06242007.0068401 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2026-08-31 | 2
496087051-16469-DETAIL-02_16_2021-GO95MLD-1^06242008.0161200 | OTHER | CA-TIER-2 | Distribution | 2021-02-16 | 2026-02-16 | 3
446334491-69119-DETAIL-08_24_2021-GO95MLD-1^06242008.0190800 | OTHER | CA-NON-TIER | Distribution | 2021-08-24 | 2024-08-24 | 2
446334491-69119-DETAIL-08_24_2021-XARMSPCR-1^06242008.0190800 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-24 | 2024-08-24 | 2
631618026-91419-DETAIL-02_15_2021-GO95TCH-1^06242009.0028400 | OTHER | CA-TIER-2 | Distribution | 2021-02-15 | 2024-02-15 | 2
395911159-40589-DTLSB-08_10_2022-ABNDEQPM-1^06243004.0175101 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2027-08-10 | 3
569798729-36889-DTLSB-08_10_2022-ABNDEQPM-1^06243004.0175501 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2027-08-10 | 3
569798729-36889-DTLSB-08_10_2022-GO95HV-1^06243004.0175501 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2027-08-10 | 3
446632594-61839-DTLSB-09_08_2022-GO95MLD-1^06243005.0038103 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
806044284-76679-DTLSB-09_08_2022-ABNDEQPM-1^06243005.0038300 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2027-09-08 | 3
806044284-76679-DTLSB-09_08_2022-GO95MLD-1^06243005.0038300 | OTHER | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
801345485-62839-DTLSB-09_08_2022-POLETOP-1^06243005.0038401 | POLE | CA-NON-TIER | Distribution | 2022-09-08 | 2025-09-08 | 2
247735315-53839-DTLSB-09_27_2022-GO95HV-1^06243005.0038600 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2027-09-27 | 3
226594537-90399-DTLSB-09_27_2022-GRDRODHI-1^06243005.0038701 | OTHER | CA-NON-TIER | Distribution | 2022-09-27 | 2025-09-27 | 2
896690005-33089-DTLSB-10_03_2022-GO95MLD-1^06243005.0039000 | OTHER | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
665520568-27602-DTLSB-09_26_2022-INSULDMG-1^06243005.0044000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
301635149-25269-DTLSB-08_10_2022-GO95MLD-1^06243004.0176300 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
649305594-46219-DETAIL-02_02_2021-GO95HV-1^06242009.0056200 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
615446074-34219-DETAIL-02_02_2021-GO95HV-1^06242009.0057104 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
646669294-87219-DETAIL-02_02_2021-GO95HV-1^06242009.0057201 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
832002463-20541-DETAIL-05_23_2022-GRDRODHI-1^06242004.0310903 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
476653543-68241-DETAIL-05_23_2022-GO95MLD-1^06242004.0311603 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
285139944-18651-DETAIL-05_24_2022-GO95MLD-1^06242004.0313801 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
758109315-36861-DTLSB-07_25_2022-SVCENTCO-1^06242005.0130000 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2025-07-25 | 2
660968074-20961-DTLSB-07_19_2022-GO95HV-1^06242005.0130601 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
88031294-8629-DTLSB-07_28_2022-GO95HV-1^06242005.0139500 | OTHER | CA-TIER-2 | Distribution | 2022-07-28 | 2027-07-28 | 3
869895219-7219-DTLSB-07_25_2022-GO95MLD-1^06242005.0139630 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2025-07-25 | 2
60624094-21251-DTLSB-07_25_2022-ABNDEQPM-1^06242005.0146001 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2027-07-25 | 3
942889344-28361-ADMIN-07_21_2023-POLEREPL-1^06242005.0149100 | POLE | CA-TIER-2 | Distribution | 2023-07-21 | 2024-07-21 | 2
231639734-17361-DTLSB-07_25_2022-GO95HV-1^06242005.0149101 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2027-07-25 | 3
738296453-98051-DTLSB-07_25_2022-GRDRODHI-1^06242005.0159001 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2025-07-25 | 2
197249488-79488-DTLSB-08_02_2022-GO95TCH-1^06242005.0160600 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
652050384-36055-DTLSB-08_02_2022-GO95MLD-1^06242005.0160601 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
685475843-97843-DTLSB-08_02_2022-GO95MLD-1^06242005.0176300 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
106784783-81351-DTLSB-07_26_2022-GO95HV-1^06242005.0177102 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2027-07-26 | 3
846294603-45451-DTLSB-08_02_2022-SVCNEUT-1^06242005.0177201 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
455692673-74341-DETAIL-06_16_2022-GO95HV-1^06242005.0190300 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2027-06-16 | 3
665874873-29241-DETAIL-06_16_2022-GO95MLD-1^06242005.0191301 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
224541143-40241-DETAIL-06_16_2022-GO95HV-1^06242005.0193100 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2027-06-16 | 3
380581907-39919-DETAIL-02_08_2021-GO95MLD-1^06242009.0065700 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
434510589-48929-DTLSB-07_28_2022-GUYNOINS-1^06243004.0168803 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
452277369-69929-DTLSB-07_28_2022-GUYNOINS-1^06243004.0168901 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-28 | 2025-07-28 | 2
66557209-77929-DTLSB-08_11_2022-CONDCOIL-1^06243004.0169800 | OTHER | CA-NON-TIER | Distribution | 2022-08-11 | 2025-08-11 | 2
318138099-68089-DTLSB-08_11_2022-GO95MLD-1^06243004.0169801 | OTHER | CA-NON-TIER | Distribution | 2022-08-11 | 2025-08-11 | 2
237485459-51269-DTLSB-09_01_2022-GO95MLD-1^06243004.0172000 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2025-09-01 | 2
550036459-74052-DTLSB-08_08_2022-GUYNOINS-2^06243004.0172001 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-08 | 2025-08-08 | 2
789660419-49729-DTLSB-08_08_2022-GUYSLACK-1^06243004.0172302 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-08 | 2025-08-08 | 2
61656285-46029-DETAIL-03_20_2023-POLEREPL-1^06242009.0281301 | POLE | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
966773099-19879-ADMIN-07_28_2023-POLEREPL-1^06242009.0286700 | POLE | CA-NON-TIER | Distribution | 2023-07-28 | 2026-07-28 | 2
615871175-64038-ADMIN-07_28_2023-POLEREPL-1^06242009.0286800 | POLE | CA-NON-TIER | Distribution | 2023-07-28 | 2026-07-28 | 2
9461253-40899-DETAIL-01_20_2021-SVCROAD-1^06242009.0297111 | OTHER | CA-NON-TIER | Distribution | 2021-01-20 | 2024-01-20 | 2
649235877-78019-DETAIL-02_04_2021-GO95HV-1^06242009.0067700 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
947364408-70869-DETAIL-02_04_2021-GO95TCH-1^06242009.0067701 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2024-02-04 | 2
835949064-82361-DTLSB-07_26_2022-GO95HV-1^06242005.0200500 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2027-07-26 | 3
935066468-67468-DTLSB-07_26_2022-GO95HV-1^06242005.0200502 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2027-07-26 | 3
372674094-90261-DTLSB-07_26_2022-SVCROAD-1^06242005.0200703 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2025-07-26 | 2
611627704-90261-DTLSB-07_26_2022-GO95HV-1^06242005.0209700 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2027-07-26 | 3
79478774-41261-DTLSB-08_02_2022-SVCENTCO-1^06242005.0212000 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
321795084-85151-DTLSB-07_21_2022-GO95MLD-1^06242005.0221240 | OTHER | CA-TIER-2 | Distribution | 2022-07-21 | 2025-07-21 | 2
793289284-92951-DTLSB-07_21_2022-GO95MLD-1^06242005.0222240 | OTHER | CA-TIER-2 | Distribution | 2022-07-21 | 2025-07-21 | 2
857635290-39561-DTLSB-07_27_2022-GO95STUB-1^06242005.0257000 | OTHER | CA-TIER-2 | Distribution | 2022-07-27 | 2025-07-27 | 2
230067377-90869-DETAIL-02_04_2021-GUYNOINS-1^06242009.0067702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2021-02-04 | 2024-02-04 | 2
822529398-213-DTLSB-07_20_2022-GO95MLD-1^06242005.0283100 | OTHER | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
685018098-26013-DTLSB-07_20_2022-GO95MLD-1^06242005.0283200 | OTHER | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
513296468-62513-DTLSB-07_26_2022-GO95MLD-1^06242005.0283400 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2025-07-26 | 2
513296468-62513-DTLSB-07_26_2022-GRDRODHI-1^06242005.0283400 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2025-07-26 | 2
58569318-81113-DTLSB-07_20_2022-GO95MLD-1^06242005.0283502 | OTHER | CA-TIER-2 | Distribution | 2022-07-20 | 2025-07-20 | 2
513737673-96119-DETAIL-02_08_2021-GO95MLD-1^06242009.0083100 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
83787558-20658-DETAIL-02_08_2021-SVCROAD-1^06242009.0084200 | OTHER | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
35025583-48869-DETAIL-02_08_2021-GUYNOINS-2^06242009.0085000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2021-02-08 | 2024-02-08 | 2
445850576-41769-DETAIL-02_05_2021-XARMSPCR-1^06242009.0117800 | CROSSARM | CA-NON-TIER | Distribution | 2021-02-05 | 2024-02-05 | 2
58096435-32769-DETAIL-02_05_2021-GO95HV-1^06242009.0119700 | OTHER | CA-TIER-2 | Distribution | 2021-02-05 | 2026-02-05 | 3
264263374-30519-DETAIL-02_05_2021-GO95HV-1^06242009.0119702 | OTHER | CA-TIER-2 | Distribution | 2021-02-05 | 2026-02-05 | 3
971546714-15729-ADMIN-11_11_2022-POLEREPL-1^06242009.0298209 | POLE | CA-NON-TIER | Distribution | 2022-11-11 | 2025-11-11 | 2
473388171-76329-ADMIN-11_15_2022-POLEREPL-1^06242009.0298804 | POLE | CA-NON-TIER | Distribution | 2022-11-15 | 2025-11-15 | 2
654233861-42389-DETAIL-01_19_2021-SVCENTCO-1^06242009.0299008 | OTHER | CA-NON-TIER | Distribution | 2021-01-19 | 2024-01-19 | 2
756201973-82269-ADMIN-11_10_2022-POLEREPL-1^06242009.0326301 | POLE | CA-NON-TIER | Distribution | 2022-11-10 | 2025-11-10 | 2
226016821-15389-ADMIN-11_10_2022-POLEREPL-1^06242009.0327401 | POLE | CA-NON-TIER | Distribution | 2022-11-10 | 2025-11-10 | 2
686781063-93929-ADMIN-11_11_2022-POLEREPL-1^06242009.0328900 | POLE | CA-NON-TIER | Distribution | 2022-11-11 | 2025-11-11 | 2
372899500-25399-ADMIN-11_11_2022-POLEREPL-1^06242009.0328901 | POLE | CA-NON-TIER | Distribution | 2022-11-11 | 2025-11-11 | 2
162955720-29329-DETAIL-08_16_2021-GO95HV-1^06242009.0330905 | OTHER | CA-NON-TIER | Distribution | 2021-08-16 | 2026-08-16 | 3
162955720-29329-DETAIL-08_16_2021-XARMSPCR-1^06242009.0330905 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-16 | 2024-08-16 | 2
840357799-21829-DTLSB-08_08_2022-GUYMARK-1^06243004.0173700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-08 | 2025-08-08 | 2
178198519-28842-AUDIT-09_13_2022-INSULDMG-1^06243004.0173902 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-13 | 2025-09-13 | 2
48191526-33642-DETAIL-06_09_2022-GO95MLD-1^06242005.0293001 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2025-06-09 | 2
801387414-46381-DETAIL-06_16_2022-GO95MLD-1^06242005.0306900 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
770319745-40669-DETAIL-06_16_2022-POLESTEP-1^06242005.0308502 | POLE | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
45532275-43902-DETAIL-06_09_2022-GO95HV-1^06242005.0309301 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2027-06-09 | 3
62678516-78932-DETAIL-06_03_2022-GO95HV-1^06242005.0326300 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2027-06-03 | 3
423427871-15031-DETAIL-06_03_2022-GO95MLD-1^06242005.0331200 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2025-06-03 | 2
842621481-62041-DETAIL-06_03_2022-ANCHIDLE-1^06242005.0331600 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-03 | 2025-06-03 | 2
972869921-80901-DETAIL-05_31_2022-GO95MLD-1^06242005.0334801 | OTHER | CA-TIER-2 | Distribution | 2022-05-31 | 2025-05-31 | 2
264871463-19251-DETAIL-05_31_2022-GO95MLD-1^06242005.0334803 | OTHER | CA-TIER-2 | Distribution | 2022-05-31 | 2025-05-31 | 2
264871463-19251-DETAIL-05_31_2022-POLESTEP-1^06242005.0334803 | POLE | CA-TIER-2 | Distribution | 2022-05-31 | 2025-05-31 | 2
956941723-80341-DETAIL-05_31_2022-SVCROAD-1^06242005.0334804 | OTHER | CA-TIER-2 | Distribution | 2022-05-31 | 2025-05-31 | 2
768682571-36819-DETAIL-02_17_2021-XARMSPCR-1^06242009.0221502 | CROSSARM | CA-NON-TIER | Distribution | 2021-02-17 | 2024-02-17 | 2
506962677-68645-DETAIL-01_26_2023-SVCDEFLC-1^06241005.0267100 | OTHER | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
853458664-50922-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0118440 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
618439754-50922-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0118441 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
819240650-11732-DETAIL-01_26_2022-GO95TCH-1^06241005.0118502 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
819240650-11732-DETAIL-01_26_2022-SVCWIND-1^06241005.0118502 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
346552588-92588-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0118506 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
715779130-97232-DETAIL-01_26_2022-GO95MLD-1^06241005.0118507 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
956167380-80532-DETAIL-01_26_2022-GO95MLD-1^06241005.0118604 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
835992679-63420-DETAIL-01_25_2023-GO95MLD-1^06241005.0268101 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
527638291-76970-DETAIL-02_08_2022-GO95MLD-1^06241005.0275800 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2025-02-08 | 2
248722571-52770-DETAIL-02_08_2022-GO95MLD-1^06241005.0275902 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
21954980-34309-DETAIL-02_17_2021-GO95MLD-1^06242009.0221600 | OTHER | CA-NON-TIER | Distribution | 2021-02-17 | 2024-02-17 | 2
829266640-31669-ADMIN-07_24_2023-POLEREPL-1^06242009.0246902 | POLE | CA-NON-TIER | Distribution | 2023-07-24 | 2026-07-24 | 2
435576823-70589-DETAIL-08_12_2021-GO95CLSV-1^06242009.0276202 | OTHER | CA-NON-TIER | Distribution | 2021-08-12 | 2024-08-12 | 2
904854149-83029-DETAIL-08_03_2021-SVCROAD-1^06242009.0280108 | OTHER | CA-NON-TIER | Distribution | 2021-08-03 | 2024-08-03 | 2
196752938-33938-ADMIN-06_21_2023-POLEREPL-1^06242009.0280602 | POLE | CA-NON-TIER | Distribution | 2023-06-21 | 2026-06-21 | 2
732086253-72251-DETAIL-05_31_2022-GO95MLD-1^06242005.0336500 | OTHER | CA-TIER-2 | Distribution | 2022-05-31 | 2025-05-31 | 2
293912113-70871-DETAIL-05_24_2022-GO95MLD-1^06242005.0355041 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
496105513-72551-DETAIL-05_24_2022-GUYNOINS-2^06242005.0356004 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
857374293-47571-DETAIL-05_24_2022-GO95MLD-1^06242005.0356042 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
245953223-67361-DETAIL-05_24_2022-GO95MLD-1^06242005.0356101 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
574740413-48261-DETAIL-05_24_2022-GO95MLD-1^06242005.0356103 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
437277904-36430-DETAIL-05_04_2023-GO95MLD-1^06241005.0364304 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
327544204-60430-DETAIL-05_04_2023-GO95MLD-1^06241005.0364400 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
218532503-71030-DETAIL-05_01_2023-GO95MLD-1^06241005.0364401 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
876579416-68640-DETAIL-05_03_2023-GO95MLD-1^06241005.0364802 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
292002324-32530-DETAIL-05_01_2023-GO95TCH-1^06241005.0365101 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
247158994-33430-DETAIL-05_01_2023-GO95MLD-1^06241005.0365200 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
247158994-33430-DETAIL-05_01_2023-SVCDEFLC-1^06241005.0365200 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
682230194-92330-DETAIL-05_01_2023-GO95MLD-1^06241005.0365206 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
277838964-88030-DETAIL-05_02_2023-GO95MLD-1^06241005.0365602 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
423073314-80230-DETAIL-05_03_2023-GO95TCH-1^06241005.0365803 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
636098506-22640-DETAIL-05_03_2023-GO95MLD-1^06241005.0365804 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
523673804-18130-DETAIL-05_03_2023-GO95MLD-1^06241005.0365901 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
61498398-69398-DTLSB-08_10_2022-GO95MLD-1^06243004.0177040 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
931797429-77829-DTLSB-08_10_2022-GO95MLD-1^06243004.0177201 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
209695529-15089-DTLSB-08_10_2022-GO95MLD-1^06243004.0177202 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
55519709-57209-DTLSB-08_11_2022-GO95MLD-1^06243004.0177301 | OTHER | CA-NON-TIER | Distribution | 2022-08-11 | 2025-08-11 | 2
51296079-39442-DTLSB-08_10_2022-GO95MLD-1^06243004.0177402 | OTHER | CA-NON-TIER | Distribution | 2022-08-10 | 2025-08-10 | 2
13777419-74829-DTLSB-08_01_2022-GO95MLD-1^06243004.0177701 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
13777419-74829-DTLSB-08_01_2022-GRDRODHI-1^06243004.0177701 | OTHER | CA-NON-TIER | Distribution | 2022-08-01 | 2025-08-01 | 2
56958068-32502-DTLSB-09_26_2022-GO95HV-1^06243005.0044100 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
326957038-40702-DTLSB-09_26_2022-GO95HV-1^06243005.0044500 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
557123808-10902-DTLSB-09_26_2022-ABNDEQPM-1^06243005.0045502 | OTHER | CA-NON-TIER | Distribution | 2022-09-26 | 2027-09-26 | 3
86186398-49502-DTLSB-09_26_2022-XARMBRAC-1^06243005.0046501 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
964563588-54202-DTLSB-09_26_2022-XARMSPCR-1^06243005.0048501 | CROSSARM | CA-NON-TIER | Distribution | 2022-09-26 | 2025-09-26 | 2
772004372-58831-DETAIL-05_05_2022-GO95MLD-1^06241005.0130705 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
142994032-7931-DETAIL-05_11_2022-GO95MLD-1^06241005.0130800 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
30402148-62148-DETAIL-05_05_2022-RISEGRD-1^06241005.0131400 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
644633194-88151-AUDIT-06_07_2022-CLMBHAZ-1^06241005.0131500 | OTHER | CA-TIER-2 | Distribution | 2022-06-07 | 2025-06-07 | 2
877624782-49831-DETAIL-05_05_2022-GO95BLTC-1^06241005.0131505 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2027-05-05 | 3
494709073-98151-DETAIL-05_11_2022-GO95GUYP-1^06241005.0131902 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
341218243-90982-DETAIL-05_05_2022-GO95MLD-1^06241005.0132604 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
324818103-87941-DETAIL-05_11_2022-ANCHIDLE-1^06241005.0132801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
275032983-8951-DETAIL-05_11_2022-GO95MLD-1^06241005.0132803 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
914656193-22741-DETAIL-05_11_2022-GO95MLD-1^06241005.0132804 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
132225013-99941-DETAIL-05_11_2022-GO95MLD-1^06241005.0132900 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
884518799-26524-DETAIL-05_05_2022-GRDRODHI-1^06241005.0133501 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
740060799-22431-DETAIL-05_05_2022-GO95MLD-1^06241005.0133502 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
986244798-71919-DETAIL-08_11_2021-XARMSPCR-1^06242009.0287100 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-11 | 2024-08-11 | 2
451540802-54179-ADMIN-11_09_2022-POLEREPL-1^06242009.0324100 | POLE | CA-NON-TIER | Distribution | 2022-11-09 | 2025-11-09 | 2
896179901-95829-ADMIN-11_09_2022-POLEREPL-1^06242009.0326202 | POLE | CA-NON-TIER | Distribution | 2022-11-09 | 2025-11-09 | 2
339553131-96209-DETAIL-01_20_2021-RISEGRD-1^06242009.0326402 | OTHER | CA-NON-TIER | Distribution | 2021-01-20 | 2024-01-20 | 2
339553131-96209-ADMIN-02_05_2021-POLETOP-1^06242009.0326402 | POLE | CA-NON-TIER | Distribution | 2021-02-05 | 2024-02-05 | 2
179107250-68322-DETAIL-05_26_2022-GUYNOINS-1^06242005.0361103 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
179107250-68322-DETAIL-05_26_2022-GUYNOINS-2^06242005.0361103 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
291488958-39404-DETAIL-05_26_2022-GO95MLD-1^06242005.0361145 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
681752448-2684-DETAIL-05_25_2022-GO95MLD-1^06242005.0361146 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
759058724-83362-DETAIL-05_25_2022-GO95MLD-1^06242005.0362042 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
690220134-78861-DETAIL-02_07_2022-GO95MLD-1^06241005.0230801 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
93241224-17761-DETAIL-02_07_2022-GO95MLD-1^06241005.0230802 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2027-02-07 | 3
15066844-62961-DETAIL-02_07_2022-SVCENTCO-1^06241005.0232402 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
884824614-15961-DETAIL-02_07_2022-GO95MLD-1^06241005.0232501 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
394988294-61161-DETAIL-02_08_2022-GO95MLD-1^06241005.0233202 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2025-02-08 | 2
583784474-61261-DETAIL-02_07_2022-SVCENTCO-1^06241005.0234500 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
243266409-47919-DETAIL-08_18_2021-SVCDEFLC-1^06241009.0365701 | OTHER | CA-NON-TIER | Distribution | 2021-08-18 | 2024-08-18 | 2
867145189-12199-ADMIN-07_21_2023-POLEREPL-1^06241009.0365800 | POLE | CA-NON-TIER | Distribution | 2023-07-21 | 2026-07-21 | 2
389320411-51611-DTLSB-08_01_2022-GRDRODHI-1^06242004.0193642 | OTHER | CA-TIER-2 | Distribution | 2022-08-01 | 2025-08-01 | 2
746304153-94051-DETAIL-05_23_2022-ENCHRW-1^06242004.0310600 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
337333843-241-DETAIL-05_19_2022-SVCENTCO-1^06242004.0310801 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2025-05-19 | 2
929149783-12441-DETAIL-05_23_2022-SVCENTCO-1^06242004.0310802 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
878722170-55332-DETAIL-05_26_2022-GO95TCH-1^06242005.0362102 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
718277159-95412-DETAIL-05_19_2022-GO95TCH-1^06242005.0363202 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2025-05-19 | 2
183833433-14841-DETAIL-05_19_2022-ABNDEQPM-1^06242005.0365100 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2027-05-19 | 3
275977223-929-ADMIN-11_10_2022-POLEREPL-1^06242009.0326500 | POLE | CA-NON-TIER | Distribution | 2022-11-10 | 2025-11-10 | 2
431680937-71448-ADMIN-11_11_2022-POLEREPL-1^06242009.0329900 | POLE | CA-NON-TIER | Distribution | 2022-11-11 | 2025-11-11 | 2
139963037-47719-DETAIL-08_23_2021-XARMSPCR-1^06242009.0354002 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-23 | 2024-08-23 | 2
314660363-48960-ADMIN-09_18_2023-SVCDRIVE-1^06243001.0125302 | OTHER | CA-NON-TIER | Distribution | 2023-09-18 | 2026-09-18 | 2
617782058-32869-DTLSB-08_29_2022-GO95HV-1^06243004.0038801 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2027-08-29 | 3
617782058-32869-DTLSB-08_29_2022-GO95TCH-1^06243004.0038801 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
507857318-47769-DTLSB-08_29_2022-GO95MLD-1^06243004.0049000 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
964501776-60642-DETAIL-05_24_2022-GUYHINS-1^06242005.0367800 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
583326816-96352-DETAIL-05_23_2022-GO95SVC-1^06242005.0368604 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
377793804-18631-DETAIL-05_09_2022-GUYHINS-1^06241005.0013506 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
860596378-64798-DETAIL-05_10_2022-GUYHINS-1^06241005.0013620 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
611126065-52341-DETAIL-05_03_2022-GO95TCH-1^06241005.0013642 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
611126065-52341-DETAIL-05_03_2022-GUYHINS-1^06241005.0013642 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
611126065-52341-DETAIL-05_03_2022-SVCWIND-1^06241005.0013642 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
904344566-18271-DETAIL-05_09_2022-SVCRUBLG-1^06241005.0014500 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
387332536-87570-DETAIL-05_04_2022-GO95MLD-1^06241005.0015800 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
325107818-65890-DETAIL-05_04_2022-ABNDEQPM-1^06241005.0016740 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2027-05-04 | 3
693786726-57369-DETAIL-05_04_2022-GO95MLD-1^06241005.0016802 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
125289351-40831-DETAIL-05_18_2022-GUYHINS-1^06241005.0022000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
472776843-38241-DETAIL-02_08_2022-GO95BLTC-1^06241004.0182200 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
472776843-38241-DETAIL-02_08_2022-GUYHINS-1^06241004.0182200 | ANCHOR/GUY | CA-TIER-3 | Distribution | 2022-02-08 | 2025-02-08 | 2
472776843-38241-DETAIL-02_08_2022-GUYHINS-2^06241004.0182200 | ANCHOR/GUY | CA-TIER-3 | Distribution | 2022-02-08 | 2025-02-08 | 2
369208263-14130-DETAIL-05_03_2023-GO95MLD-1^06241005.0252502 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
848374894-71430-DETAIL-05_03_2023-GO95MLD-1^06241005.0252600 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
511755164-88230-DETAIL-05_03_2023-GUYNOINS-1^06241005.0252601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
734953334-10230-DETAIL-05_03_2023-SVCDEFLC-1^06241005.0253500 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
356267454-44230-DETAIL-05_03_2023-ABNDEQPM-1^06241005.0253600 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
724109603-39451-DTLSB-07_21_2022-RISEGRD-1^06242005.0212200 | OTHER | CA-TIER-2 | Distribution | 2022-07-21 | 2025-07-21 | 2
122450283-23441-DTLSB-07_21_2022-GO95MLD-1^06242005.0222101 | OTHER | CA-TIER-2 | Distribution | 2022-07-21 | 2025-07-21 | 2
846441873-2341-DTLSB-07_21_2022-GO95MLD-1^06242005.0223101 | OTHER | CA-TIER-2 | Distribution | 2022-07-21 | 2025-07-21 | 2
133302774-67851-DTLSB-07_25_2022-GO95STUB-1^06242005.0238901 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2025-07-25 | 2
833296024-37261-AUDIT-09_12_2022-GO95MLD-1^06242005.0239600 | OTHER | CA-TIER-2 | Distribution | 2022-09-12 | 2025-09-12 | 2
571737110-40261-DTLSB-07_27_2022-GO95HV-1^06242005.0255001 | OTHER | CA-TIER-2 | Distribution | 2022-07-27 | 2027-07-27 | 3
100227630-63371-DTLSB-08_03_2022-GO95HV-1^06242005.0258801 | OTHER | CA-TIER-2 | Distribution | 2022-08-03 | 2027-08-03 | 3
412959152-45341-DETAIL-05_17_2022-GO95MLD-1^06241005.0026506 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
412959152-45341-DETAIL-05_17_2022-GO95TCH-1^06241005.0026506 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
899451671-15731-DETAIL-05_17_2022-GO95HV-1^06241005.0026507 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
769250203-47151-DETAIL-05_17_2022-GO95MLD-1^06241005.0026509 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
104840984-12831-DETAIL-05_09_2022-GUYHINS-1^06241005.0012603 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
244714204-19531-DETAIL-05_09_2022-GO95HV-1^06241005.0012604 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
244714204-19531-DETAIL-05_09_2022-GO95MLD-1^06241005.0012604 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
796871715-47851-DETAIL-05_09_2022-GUYHINS-1^06241005.0012643 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
14360394-50431-DETAIL-05_03_2022-GO95MLD-1^06241005.0012700 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
14360394-50431-DETAIL-05_03_2022-GO95TCH-1^06241005.0012700 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
270491234-31731-DETAIL-05_03_2022-SVCWIND-1^06241005.0012701 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
6608504-831-DETAIL-05_03_2022-GO95MLD-1^06241005.0012706 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
267685397-37397-DETAIL-04_27_2023-GO95MLD-1^06241005.0257300 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
539121224-31530-DETAIL-04_27_2023-GO95MLD-1^06241005.0257900 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
483513959-37510-DETAIL-01_26_2023-GO95MLD-1^06241005.0262200 | OTHER | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
420340389-33010-DETAIL-01_26_2023-GO95MLD-1^06241005.0262204 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2026-01-26 | 2
420340389-33010-DETAIL-01_26_2023-SVCDEFLC-1^06241005.0262204 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2026-01-26 | 2
922603123-95120-DETAIL-05_02_2023-GO95TCH-1^06241005.0360801 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
6133884-15330-DETAIL-05_02_2023-GO95MLD-1^06241005.0360903 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
992814976-56976-DETAIL-05_04_2023-GO95TCH-1^06241005.0363300 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
501095384-3330-DETAIL-05_04_2023-GO95BLTC-1^06241005.0363400 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2028-05-04 | 3
114756876-39369-DETAIL-05_04_2023-GO95MLD-1^06241005.0363402 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
893385083-98520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363502 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
537729214-93130-DETAIL-05_02_2023-GO95MLD-1^06241005.0363600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
268979683-80561-DETAIL-05_12_2022-GO95MLD-1^06241005.0027940 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
744126090-96052-DETAIL-05_18_2022-GO95MLD-1^06241005.0028043 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
598145250-69852-DETAIL-05_18_2022-GO95HV-1^06241005.0028044 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
598145250-69852-DETAIL-05_18_2022-GO95TCH-1^06241005.0028044 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
93700345-57432-DETAIL-05_18_2022-GUYHINS-1^06241005.0028100 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
93700345-57432-DETAIL-05_18_2022-SVCWIND-2^06241005.0028100 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
228202168-73690-DETAIL-05_04_2022-GO95HV-1^06241005.0015641 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2027-05-04 | 3
325107818-65890-DETAIL-05_04_2022-GO95MLD-1^06241005.0016740 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
561549866-31070-DETAIL-05_04_2022-GUYNOINS-1^06241005.0018840 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
397347141-2831-DETAIL-05_17_2022-GO95MLD-1^06241005.0020402 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
166115001-69931-DETAIL-05_18_2022-GO95HV-1^06241005.0023102 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
631651951-6311-DETAIL-05_17_2022-GO95STUB-1^06241005.0023301 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
596996889-64089-DTLSB-08_04_2022-GRDRODHI-1^06243004.0212201 | OTHER | CA-NON-TIER | Distribution | 2022-08-04 | 2025-08-04 | 2
629229878-96512-DTLSB-08_29_2022-GO95HV-1^06243004.0035300 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2027-08-29 | 3
396045450-65450-DTLTRT-08_29_2022-GUYHINS-1^06243004.0036402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
861269088-33612-DTLSB-08_29_2022-GO95HV-1^06243004.0037300 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2027-08-29 | 3
931628298-79612-DTLSB-08_29_2022-GUYHINS-1^06243004.0038400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
676515881-76099-DTLSB-09_06_2022-GO95MLD-1^06243004.0050400 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2027-09-06 | 3
676515881-76099-DTLSB-09_06_2022-GRDRODHI-2^06243004.0050400 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2025-09-06 | 2
676515881-76099-DTLSB-09_06_2022-GRDRODHI-3^06243004.0050400 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2025-09-06 | 2
676515881-76099-DTLSB-09_06_2022-GRDRODHI-4^06243004.0050400 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2025-09-06 | 2
105216672-90529-DTLSB-09_06_2022-GO95HV-1^06243004.0054000 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2027-09-06 | 3
50751272-11899-DTLSB-09_09_2022-GO95MLD-1^06243004.0054100 | OTHER | CA-NON-TIER | Distribution | 2022-09-09 | 2025-09-09 | 2
192533032-48982-DTLSB-09_06_2022-GO95HV-1^06243004.0054101 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2027-09-06 | 3
530510402-38429-DTLSB-09_01_2022-GO95HV-1^06243004.0058000 | OTHER | CA-NON-TIER | Distribution | 2022-09-01 | 2027-09-01 | 3
828582164-67432-DETAIL-05_11_2022-GO95MLD-1^06241005.0029101 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
828582164-67432-DETAIL-05_11_2022-SVCROOF-1^06241005.0029101 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
648212434-43922-DETAIL-05_11_2022-GO95MLD-1^06241005.0029102 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
648212434-43922-DETAIL-05_11_2022-GUYHINS-1^06241005.0029102 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
240072194-63832-DETAIL-05_11_2022-GO95HV-1^06241005.0029103 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
60359604-2922-DETAIL-05_11_2022-GO95MLD-1^06241005.0029104 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
379534264-2889-DETAIL-05_11_2022-SVCRUBLG-1^06241005.0029107 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
379534264-2889-DETAIL-05_11_2022-SVCWIND-2^06241005.0029107 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
531620854-11332-DETAIL-05_11_2022-SVCRUBLG-1^06241005.0029201 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
492159983-62321-DETAIL-05_10_2022-GO95MLD-1^06241005.0029204 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
204823272-86299-DETAIL-05_17_2022-GO95BLTC-1^06241005.0026402 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
204823272-86299-DETAIL-05_17_2022-GUYHINS-1^06241005.0026402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
410245864-93532-DETAIL-05_17_2022-GO95HV-1^06241005.0026403 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
614138285-98502-DETAIL-06_03_2022-GO95MLD-1^06242005.0321700 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2027-06-03 | 3
614138285-98502-DETAIL-06_03_2022-GO95TCH-1^06242005.0321700 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2025-06-03 | 2
786488666-39652-DETAIL-06_03_2022-ABNDEQPM-1^06242005.0323701 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2027-06-03 | 3
525085666-47342-DETAIL-06_03_2022-GO95MLD-1^06242005.0323800 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2025-06-03 | 2
937114166-27142-DETAIL-06_03_2022-GO95HV-1^06242005.0323805 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2027-06-03 | 3
738836156-48642-DETAIL-06_03_2022-GO95MLD-1^06242005.0323901 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2025-06-03 | 2
342696006-30942-DETAIL-06_03_2022-GO95MLD-1^06242005.0324800 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2025-06-03 | 2
62678516-78932-DETAIL-06_03_2022-COPLLEAN-1^06242005.0326300 | POLE | CA-TIER-2 | Distribution | 2022-06-03 | 2025-06-03 | 2
648965559-14251-DETAIL-06_06_2022-GO95HV-1^06242005.0329201 | OTHER | CA-TIER-2 | Distribution | 2022-06-06 | 2027-06-06 | 3
254218231-95811-DETAIL-06_06_2022-GO95MLD-1^06242005.0330101 | OTHER | CA-TIER-2 | Distribution | 2022-06-06 | 2027-06-06 | 3
374633321-59401-DETAIL-06_03_2022-GUYNOINS-1^06242005.0331001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-03 | 2025-06-03 | 2
728997031-80531-DETAIL-06_06_2022-SVCROAD-1^06242005.0331102 | OTHER | CA-TIER-2 | Distribution | 2022-06-06 | 2025-06-06 | 2
633510681-70080-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167005 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
633510681-70080-DETAIL-03_27_2023-SVCENTCO-1^06240004.0167005 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
889857653-49280-DETAIL-03_27_2023-GO95TCH-1^06240004.0167009 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
889857653-49280-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167009 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
580976323-97323-DETAIL-03_27_2023-ENCHRW-1^06240004.0167030 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
386901350-50570-DETAIL-03_27_2023-GUYNOINS-1^06240004.0167040 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
640218151-29180-DETAIL-03_27_2023-GO95TCH-1^06240004.0167041 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
640218151-29180-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167041 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
8281781-36680-DETAIL-03_27_2023-GUYNOINS-1^06240004.0164605 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
391615878-49840-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0164607 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
943422039-59252-DETAIL-05_16_2022-GO95MLD-1^06241005.0027145 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
632724856-29742-DETAIL-05_16_2022-ENCHRW-1^06241005.0027205 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
332107829-58829-DETAIL-05_16_2022-GO95MLD-1^06241005.0027207 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
332107829-58829-DETAIL-05_16_2022-GUYHINS-1^06241005.0027207 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
332107829-58829-AUDIT-06_28_2022-GO95HV-1^06241005.0027207 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
984032489-91252-DETAIL-05_16_2022-GO95MLD-1^06241005.0027240 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
977885079-21252-DETAIL-05_16_2022-GO95MLD-1^06241005.0027241 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
508258209-63052-DETAIL-05_16_2022-GO95MLD-1^06241005.0027244 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
494064629-18052-DETAIL-05_16_2022-SVCENTCO-1^06241005.0027246 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
968258530-86152-DETAIL-05_16_2022-GO95MLD-1^06241005.0027440 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
259920953-2361-DETAIL-05_12_2022-GO95TCH-1^06241005.0027840 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
780539292-26241-DETAIL-05_12_2022-POLESTEP-1^06241005.0027903 | POLE | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
653043290-47670-DETAIL-03_29_2023-GO95HV-1^06240004.0167407 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2028-03-29 | 3
687984290-19670-DETAIL-03_21_2023-GO95MLD-1^06240004.0167411 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
406980263-10680-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0167413 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
516954791-21780-DETAIL-03_21_2023-GO95MLD-1^06240004.0167415 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
42362859-58470-DETAIL-03_21_2023-GO95MLD-1^06240004.0167416 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
277492210-11170-DETAIL-03_21_2023-GO95MLD-1^06240004.0167417 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
277492210-11170-DETAIL-03_21_2023-GO95TCH-1^06240004.0167417 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
637043361-8280-DETAIL-03_21_2023-GO95TCH-1^06240004.0167441 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
558953990-69770-DETAIL-04_12_2023-SVCROOF-1^06240004.0167501 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
133947108-20670-DETAIL-04_11_2023-GO95MLD-1^06240004.0167502 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
101966518-87870-DETAIL-04_11_2023-GO95MLD-1^06240004.0167503 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
745869738-85170-DETAIL-04_11_2023-GUYHINS-1^06240004.0167504 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
379809694-73130-DETAIL-05_02_2023-RISEGRD-1^06241005.0365601 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
198486505-84330-DETAIL-05_03_2023-GO95MLD-1^06241005.0365701 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
257353545-32830-DETAIL-05_03_2023-GO95HV-1^06241005.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
423073314-80230-DETAIL-05_03_2023-GO95MLD-1^06241005.0365803 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
166918643-78030-DETAIL-05_01_2023-GO95MLD-1^06241005.0366100 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
531343554-63130-DETAIL-05_01_2023-GUYHINS-1^06241005.0366102 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
535398883-87030-DETAIL-05_02_2023-GO95MLD-1^06241005.0366603 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
184540064-58030-DETAIL-05_02_2023-GO95MLD-1^06241005.0366700 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
687446524-75130-DETAIL-05_03_2023-GO95MLD-1^06241005.0367900 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
446518284-47330-DETAIL-05_03_2023-SVCDEFLC-1^06241005.0367902 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
542044638-25638-DETAIL-06_09_2022-GUYNOINS-1^06241006.0115700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-09 | 2025-06-09 | 2
196210244-97170-DETAIL-03_27_2023-GUYHINS-1^06240004.0168046 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
38355002-2880-DETAIL-04_10_2023-GO95MLD-1^06240004.0168100 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2028-04-10 | 3
629220837-81837-DETAIL-04_10_2023-SVCRUBLG-1^06240004.0168109 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
349405651-55380-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168142 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
200955732-46780-DETAIL-04_10_2023-GO95MLD-1^06240004.0168146 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
251764928-54170-DETAIL-03_28_2023-GO95MLD-1^06240004.0166905 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
65776718-14170-DETAIL-03_28_2023-GO95MLD-1^06240004.0166906 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
64820063-82380-DETAIL-03_22_2023-GO95HV-1^06240004.0167000 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
496435030-25470-DETAIL-03_27_2023-GO95MLD-1^06240004.0167002 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
673966860-74570-DETAIL-03_27_2023-GO95MLD-1^06240004.0167008 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
627715401-52970-DETAIL-03_22_2023-GO95MLD-1^06240004.0167101 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
627715401-52970-DETAIL-03_22_2023-GO95TCH-1^06240004.0167101 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
812461543-53602-DETAIL-01_26_2022-GO95MLD-1^06241005.0118404 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
169717633-64302-DETAIL-01_26_2022-SVCENTCO-1^06241005.0118405 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
893811750-74732-DETAIL-01_26_2022-GO95MLD-1^06241005.0118501 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
893811750-74732-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0118501 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
819240650-11732-DETAIL-01_26_2022-GO95HV-1^06241005.0118502 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2027-01-26 | 3
899571789-39552-DETAIL-05_18_2022-GO95MLD-1^06241005.0028243 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
899571789-39552-DETAIL-05_18_2022-SVCENTCO-1^06241005.0028243 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
899571789-39552-DETAIL-05_18_2022-SVCROOF-1^06241005.0028243 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
373059153-22909-DETAIL-05_11_2022-GO95MLD-1^06241005.0028244 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
492551849-50552-DETAIL-05_11_2022-GO95MLD-1^06241005.0028245 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
503001149-2152-DETAIL-05_16_2022-GO95BLTC-1^06241005.0028252 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
60844305-3632-DETAIL-05_16_2022-ENCHRW-1^06241005.0028300 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
693368121-99970-DETAIL-03_22_2023-GO95TCH-1^06240004.0167306 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
469810059-59470-DETAIL-03_21_2023-GO95MLD-1^06240004.0167308 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
281159569-85470-DETAIL-04_11_2023-GO95MLD-1^06240004.0167403 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
868928573-33480-DETAIL-04_11_2023-GO95MLD-1^06240004.0167406 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
687984290-19670-DETAIL-03_21_2023-GO95HV-1^06240004.0167411 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
406980263-10680-DETAIL-03_21_2023-SVCRUBLG-1^06240004.0167413 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
516954791-21780-DETAIL-03_21_2023-GO95TCH-1^06240004.0167415 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
516954791-21780-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0167415 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
42362859-58470-DETAIL-03_21_2023-GO95TCH-1^06240004.0167416 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
133947108-20670-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0167502 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
745869738-85170-DETAIL-04_11_2023-GO95MLD-1^06240004.0167504 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
24201314-12419-DETAIL-02_17_2021-GUYNOINS-1^06242009.0029203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2021-02-17 | 2024-02-17 | 2
507857318-47769-DTLSB-08_29_2022-GO95TCH-1^06243004.0049000 | OTHER | CA-NON-TIER | Distribution | 2022-08-29 | 2025-08-29 | 2
676515881-76099-DTLSB-09_06_2022-GO95HV-1^06243004.0050400 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2027-09-06 | 3
676515881-76099-DTLSB-09_06_2022-GRDRODHI-1^06243004.0050400 | OTHER | CA-NON-TIER | Distribution | 2022-09-06 | 2025-09-06 | 2
192533032-48982-DTLSB-09_06_2022-INSULDMG-1^06243004.0054101 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-09-06 | 2025-09-06 | 2
537993283-12599-DTLSB-08_30_2022-GO95MLD-1^06243004.0059200 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
537993283-12599-DTLSB-08_30_2022-GO95TCH-1^06243004.0059200 | OTHER | CA-NON-TIER | Distribution | 2022-08-30 | 2025-08-30 | 2
504756418-47529-DTLSB-09_08_2022-GO95HV-1^06243004.0060600 | OTHER | CA-TIER-2 | Distribution | 2022-09-08 | 2027-09-08 | 3
711889271-8342-DTLSB-09_08_2022-GO95HV-1^06243004.0060700 | OTHER | CA-TIER-2 | Distribution | 2022-09-08 | 2027-09-08 | 3
536171281-59489-DTLSB-09_06_2022-GO95MLD-1^06243004.0062100 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
319139880-41629-DTLSB-09_06_2022-GO95MLD-1^06243004.0062201 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
43746470-11089-DTLSB-09_06_2022-GO95MLD-1^06243004.0063300 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
213428878-26170-DETAIL-01_23_2023-GO95MLD-1^06240004.0080100 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
163413999-75530-DETAIL-01_26_2023-GUYHINS-1^06240004.0080201 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
266546388-29170-DETAIL-01_23_2023-SVCROAD-1^06240004.0080204 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
199250528-14370-DETAIL-01_23_2023-GO95MLD-1^06240004.0080206 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
199250528-14370-DETAIL-01_23_2023-POLESTEP-1^06240004.0080206 | POLE | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
117889248-67370-DETAIL-01_23_2023-GO95MLD-1^06240004.0080207 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
121056589-65530-DETAIL-01_24_2023-GO95HV-1^06240004.0080302 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
121056589-65530-DETAIL-01_24_2023-GO95MLD-1^06240004.0080302 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
450539936-10840-DETAIL-01_19_2023-GO95MLD-1^06240004.0080440 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
627531698-93920-DETAIL-01_19_2023-GO95MLD-1^06240004.0080500 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
627531698-93920-DETAIL-01_19_2023-GO95STUB-1^06240004.0080500 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
751728588-76130-DETAIL-01_24_2023-GO95MLD-1^06240004.0080700 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
305874438-60130-DETAIL-01_19_2023-GO95MLD-1^06240004.0080900 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
843503530-26470-DETAIL-04_10_2023-GO95MLD-1^06240004.0168300 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
941558360-3870-DETAIL-04_10_2023-GO95MLD-1^06240004.0168304 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
941558360-3870-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168304 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
682365361-11980-DETAIL-04_10_2023-SVCWIND-1^06240004.0168308 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
429853879-96170-DETAIL-04_11_2023-GO95MLD-1^06240004.0168402 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2028-04-11 | 3
816303449-5570-DETAIL-04_10_2023-SVCROOF-1^06240004.0168407 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
760946451-85880-DETAIL-04_11_2023-GO95MLD-1^06240004.0168408 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
617732813-60680-DETAIL-04_11_2023-GO95TCH-1^06240004.0168410 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
698978613-77580-DETAIL-04_11_2023-GO95MLD-1^06240004.0168411 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
116573013-15580-DETAIL-04_11_2023-GO95MLD-1^06240004.0168412 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
698966288-89670-DETAIL-04_12_2023-SVCENTBK-1^06240004.0168501 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
971559509-85870-DETAIL-04_11_2023-SVCWIND-1^06240004.0168505 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
20030163-31430-DETAIL-05_01_2023-GO95MLD-1^06240004.0064541 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
927187968-15070-DETAIL-01_17_2023-GO95MLD-1^06240004.0083101 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
235374876-54940-DETAIL-01_17_2023-GO95MLD-1^06240004.0083203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
235374876-54940-DETAIL-01_17_2023-GUYHINS-1^06240004.0083203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
235374876-54940-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0083203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
774677226-96840-DETAIL-01_17_2023-GO95MLD-1^06240004.0083300 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
386041398-76570-DETAIL-01_17_2023-GO95MLD-1^06240004.0083303 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
657875816-87540-DETAIL-01_17_2023-GO95TCH-1^06240004.0083340 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
967263773-84930-DETAIL-04_25_2023-GO95MLD-1^06240004.0064701 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
216643453-68830-DETAIL-04_25_2023-GO95MLD-1^06240004.0064703 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
991229733-35730-DETAIL-04_25_2023-GO95MLD-1^06240004.0064804 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
241578203-42590-DETAIL-04_25_2023-GO95HV-1^06240004.0064900 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2028-04-25 | 3
879176025-7842-DETAIL-01_20_2022-GO95MLD-1^06241005.0121301 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
842122522-52884-DETAIL-01_20_2022-GO95MLD-1^06241005.0122100 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
824887234-79234-DETAIL-05_11_2022-GO95MLD-1^06241005.0130507 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
460160742-49931-DETAIL-05_05_2022-GUYHINS-1^06241005.0131504 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
461243363-44151-DETAIL-05_11_2022-GO95HV-1^06241005.0131901 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
936447263-62151-DETAIL-05_11_2022-GO95MLD-1^06241005.0131903 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
845274974-29432-DETAIL-05_11_2022-GO95GUYP-1^06241005.0131905 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
189816313-43041-DETAIL-05_11_2022-GO95TCH-1^06241005.0133902 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
826575110-19752-DETAIL-05_10_2022-GUYHINS-1^06241005.0029341 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
117961620-34852-DETAIL-05_10_2022-GO95MLD-1^06241005.0029441 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
773444321-8808-DETAIL-05_03_2022-GO95MLD-1^06241005.0029502 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
88176502-93541-DETAIL-05_03_2022-ABNDEQPM-1^06241005.0029503 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2027-05-03 | 3
170640212-28370-DETAIL-01_23_2023-GO95MLD-1^06240004.0087002 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
609766018-16730-DETAIL-01_16_2023-SVCROAD-1^06240004.0089503 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
434408098-90330-DETAIL-01_16_2023-CLMBHAZ-1^06240004.0089505 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
60527055-4570-DETAIL-01_16_2023-GO95HV-1^06240004.0089506 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2028-01-16 | 3
60527055-4570-DETAIL-01_16_2023-SVCROAD-1^06240004.0089506 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
569392921-34921-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0089507 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
536130238-88730-DETAIL-01_12_2023-SVCROOF-1^06240004.0089600 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
250810149-33683-DETAIL-01_12_2023-GO95MLD-1^06240004.0090100 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
931440929-97583-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0090102 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
238392341-89130-DETAIL-01_12_2023-GO95MLD-1^06240004.0090501 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2028-01-12 | 3
454714718-74150-DETAIL-01_16_2023-ABNDEQPM-1^06240004.0090502 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2028-01-16 | 3
607630748-42740-DETAIL-01_16_2023-GO95HV-1^06240004.0090503 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2028-01-16 | 3
18208963-12980-DETAIL-04_20_2023-GO95MLD-1^06240004.0176300 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
1823003-11590-DETAIL-04_20_2023-GO95CL10-1^06240004.0176404 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
1823003-11590-DETAIL-04_20_2023-GO95MLD-1^06240004.0176404 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
1823003-11590-DETAIL-04_20_2023-SVCROAD-1^06240004.0176404 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
188529451-52230-DETAIL-04_20_2023-GO95HV-1^06240004.0176501 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
370630851-21230-DETAIL-04_17_2023-GO95HV-1^06240004.0176503 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
500768921-85130-DETAIL-04_17_2023-ABNDEQPM-1^06240004.0176701 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
500768921-85130-DETAIL-04_17_2023-GO95MLD-1^06240004.0176701 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
567428960-79830-DETAIL-04_17_2023-POLETOP-1^06240004.0176703 | POLE | CA-TIER-2 | Distribution | 2023-04-17 | 2024-04-17 | 2
567428960-79830-DETAIL-04_17_2023-XARMSPCR-1^06240004.0176703 | CROSSARM | CA-TIER-2 | Distribution | 2023-04-17 | 2024-04-17 | 2
941404691-32330-DETAIL-04_17_2023-GO95MLD-1^06240004.0176802 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
263317043-73760-DETAIL-01_10_2023-GO95MLD-1^06240004.0097042 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
202174733-11760-DETAIL-01_10_2023-GO95MLD-1^06240004.0097140 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
202174733-11760-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0097140 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
361773233-50760-DETAIL-01_10_2023-GO95MLD-1^06240004.0097141 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
361773233-50760-DETAIL-01_10_2023-POLESTEP-1^06240004.0097141 | POLE | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
354381038-79830-DETAIL-01_19_2023-RISEGRD-1^06240004.0081700 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
274967218-17830-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081701 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
274967218-17830-DETAIL-01_19_2023-SVCDEFLC-2^06240004.0081701 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
778608288-17070-DETAIL-01_17_2023-GO95MLD-1^06240004.0082202 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
774008336-86569-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0082203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
774008336-86569-DETAIL-01_17_2023-SVCDEFLC-2^06240004.0082203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
434203944-89362-DETAIL-05_26_2022-GO95MLD-1^06242005.0360140 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
393640245-98872-DETAIL-05_25_2022-GO95MLD-1^06242005.0360144 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
393640245-98872-DETAIL-05_25_2022-SVCENTCO-1^06242005.0360144 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
393640245-98872-DETAIL-05_25_2022-SVCENTCO-2^06242005.0360144 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
256665721-31132-DETAIL-05_26_2022-GO95MLD-1^06242005.0360240 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
759297119-84912-DETAIL-05_25_2022-GO95MLD-1^06242005.0361000 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
451407814-96162-DETAIL-05_25_2022-GO95MLD-1^06242005.0361041 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
470574894-56062-DETAIL-05_25_2022-GO95MLD-1^06242005.0361042 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
557833410-97932-DETAIL-05_26_2022-GO95MLD-1^06242005.0361101 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
559585610-69922-DETAIL-05_26_2022-GO95MLD-1^06242005.0361105 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
291488958-39404-DETAIL-05_26_2022-SVCWIND-1^06242005.0361145 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
570199974-6062-DETAIL-05_25_2022-GO95STUB-1^06242005.0362040 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
759834034-92743-DETAIL-09_27_2021-SVCWIND-1^06148004.0356307 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
792393905-2489-DETAIL-10_28_2021-ENCHRW-1^06148005.0146103 | OTHER | CA-NON-TIER | Distribution | 2021-10-28 | 2024-10-28 | 2
696953244-87479-DETAIL-10_18_2021-SVCROAD-1^06148005.0180200 | OTHER | CA-NON-TIER | Distribution | 2021-10-18 | 2024-10-18 | 2
106236104-71889-ADMIN-02_28_2023-POLEDERP-1^06148005.0232900 | POLE | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
423941189-45199-DETAIL-10_27_2021-SVCROAD-1^06148005.0262201 | OTHER | CA-NON-TIER | Distribution | 2021-10-27 | 2024-10-27 | 2
716800977-28370-DTLSB-04_27_2021-ENCHRW-1^06236005.0113900 | OTHER | CA-TIER-2 | Distribution | 2021-04-27 | 2024-04-27 | 2
880220144-52030-DTLSB-04_29_2021-COPLLEAN-1^06236005.0333500 | POLE | CA-TIER-2 | Distribution | 2021-04-29 | 2024-04-29 | 2
333406454-30630-ADMIN-05_14_2021-COPLLEAN-1^06236005.0336700 | POLE | CA-TIER-2 | Distribution | 2021-05-14 | 2024-05-14 | 2
580095019-60240-ADMIN-08_21_2023-POLEREPL-1^06237004.0077301 | POLE | CA-TIER-2 | Distribution | 2023-08-21 | 2024-08-21 | 2
715466268-64043-DETAIL-01_11_2023-SVCENTCO-1^06240004.0099100 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
459698874-93460-DETAIL-01_10_2023-SVCENTCO-1^06240004.0099201 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
459698874-93460-DETAIL-01_10_2023-SVCROAD-1^06240004.0099201 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
698511403-89960-DETAIL-01_11_2023-GO95MLD-1^06240004.0099241 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
392161634-12190-DETAIL-05_08_2023-GUYHINS-1^06240004.0100007 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
122398574-92740-DETAIL-05_08_2023-GO95MLD-1^06240004.0100101 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
338128505-93140-DETAIL-05_08_2023-GUYHINS-1^06240004.0102003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
256268675-72040-DETAIL-05_08_2023-RISEGRD-1^06240004.0103001 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
192243540-29783-DETAIL-01_12_2023-GO95MLD-1^06240004.0090101 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
931440929-97583-DETAIL-01_12_2023-SVCDEFLC-2^06240004.0090102 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
574127149-25173-DETAIL-01_12_2023-RISEBKSP-1^06240004.0091000 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
855404249-45873-DETAIL-01_12_2023-GO95HV-1^06240004.0091400 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2028-01-12 | 3
264735926-63370-DETAIL-01_19_2022-SVCWIND-1^06239004.0255144 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
233693436-40470-DETAIL-01_19_2022-GO95HV-1^06239004.0255146 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2027-01-19 | 3
702255521-23801-DETAIL-01_19_2022-SVCWIND-1^06239004.0255244 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
755580684-23360-DETAIL-01_19_2022-GO95MLD-1^06239004.0255301 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
73472308-98290-AUDIT-06_28_2022-GO95MLD-1^06239004.0255340 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
517569550-89201-DETAIL-01_12_2022-GO95TCH-1^06239004.0255341 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
551948440-66201-DETAIL-01_12_2022-GO95TCH-1^06239004.0255342 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
833812631-14711-DETAIL-01_19_2022-POLESTEP-1^06239004.0255346 | POLE | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
433323321-31201-DETAIL-01_12_2022-GO95HV-1^06239004.0255441 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2027-01-12 | 3
171071001-59201-DETAIL-01_12_2022-SVCRUBLG-1^06239004.0255443 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
780410581-21411-DETAIL-01_17_2022-GO95MLD-1^06239004.0255446 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
359454613-12590-DETAIL-04_20_2023-SVCDEFLC-1^06240004.0172500 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
140689351-65730-DETAIL-04_20_2023-GO95MLD-1^06240004.0172701 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
739010701-50630-DETAIL-04_19_2023-GO95MLD-1^06240004.0172802 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
767659701-97930-DETAIL-04_20_2023-GO95MLD-1^06240004.0172901 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
35980501-5930-DETAIL-04_20_2023-GO95MLD-1^06240004.0172902 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
943537763-50930-DETAIL-04_20_2023-GO95MLD-1^06240004.0173941 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
943537763-50930-AUDIT-06_12_2023-RISEGRD-1^06240004.0173941 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
98432090-33030-DETAIL-04_17_2023-GO95HV-1^06240004.0175504 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
811134628-94043-ADMIN-09_19_2022-GUYHINS-1^06240004.0214541 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-09-19 | 2025-09-19 | 2
61004014-94740-ADMIN-03_27_2023-POLEREPL-1^06240004.0217902 | POLE | CA-TIER-2 | Distribution | 2023-03-27 | 2024-03-27 | 2
586417130-10520-DTLSB-05_12_2021-GO95MLD-1^06240004.0272000 | OTHER | CA-TIER-2 | Distribution | 2021-05-12 | 2024-05-12 | 2
735701505-2770-DETAIL-01_17_2022-GO95MLD-1^06239004.0256604 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
52499796-8080-DETAIL-01_24_2022-GO95MLD-1^06239004.0256647 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
584332076-46880-DETAIL-01_17_2022-POLESTEP-1^06239004.0256651 | POLE | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
530345266-65770-DETAIL-01_17_2022-SVCWIND-1^06239004.0256652 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
457684650-36301-ADMIN-05_22_2023-POLEREPL-1^06239004.0135006 | POLE | CA-TIER-2 | Distribution | 2023-05-22 | 2024-05-22 | 2
614873221-67201-DETAIL-03_29_2021-SVCROAD-1^06239004.0135048 | OTHER | CA-TIER-2 | Distribution | 2021-03-29 | 2024-03-29 | 2
614873221-67201-DETAIL-03_29_2021-SVCROAD-2^06239004.0135048 | OTHER | CA-TIER-2 | Distribution | 2021-03-29 | 2024-03-29 | 2
956337271-91801-ADMIN-05_22_2023-POLEREPL-1^06239004.0135141 | POLE | CA-TIER-2 | Distribution | 2023-05-22 | 2024-05-22 | 2
250205177-41590-DETAIL-03_30_2021-GO95CLSV-1^06239004.0243941 | OTHER | CA-TIER-2 | Distribution | 2021-03-30 | 2024-03-30 | 2
281951809-67170-DETAIL-03_22_2023-GRDRODHI-4^06240004.0164301 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
595466569-86569-DETAIL-01_18_2023-GO95HV-1^06240004.0093402 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2028-01-18 | 3
595466569-86569-DETAIL-01_18_2023-GO95MLD-1^06240004.0093402 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
809063348-50350-DETAIL-01_09_2023-GO95MLD-1^06240004.0094800 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
809063348-50350-DETAIL-01_09_2023-GO95TCH-1^06240004.0094800 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
443097938-99250-DETAIL-01_09_2023-GO95HV-1^06240004.0094801 | OTHER | CA-TIER-3 | Distribution | 2023-01-09 | 2028-01-09 | 3
764221548-43350-DETAIL-01_09_2023-GO95HV-1^06240004.0094901 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2028-01-09 | 3
979389058-15350-DETAIL-01_09_2023-GO95HV-1^06240004.0094902 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2028-01-09 | 3
680378534-260-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0095204 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
987643823-25650-DETAIL-01_09_2023-GO95MLD-1^06240004.0095700 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
351076343-54950-DETAIL-01_09_2023-GO95HV-1^06240004.0095800 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2028-01-09 | 3
991620148-59550-DETAIL-01_09_2023-GO95MLD-1^06240004.0096500 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
713329821-44101-DETAIL-01_25_2022-GO95BLTC-1^06239004.0258441 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
265614404-64560-DETAIL-01_25_2022-SVCWIND-1^06239004.0258500 | OTHER | CA-TIER-3 | Distribution | 2022-01-25 | 2025-01-25 | 2
223736211-37650-DETAIL-01_18_2022-GO95BLTC-1^06239004.0258700 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
921335305-67170-DETAIL-01_18_2022-GO95BLTC-1^06239004.0258741 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
921335305-67170-DETAIL-01_18_2022-GO95CL10-1^06239004.0258741 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
921335305-67170-DETAIL-01_18_2022-SVCNEUT-1^06239004.0258741 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
40254444-38660-DETAIL-01_18_2022-GO95MLD-1^06239004.0258802 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
264735926-63370-DETAIL-01_19_2022-GO95MLD-1^06239004.0255144 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
666076916-38270-DETAIL-01_19_2022-SVCENTCO-1^06239004.0255145 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
494699034-74660-DETAIL-01_19_2022-GO95HV-1^06239004.0255202 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2027-01-19 | 3
113026208-76208-DETAIL-01_19_2022-SVCWIND-1^06239004.0255204 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
781920921-62011-DETAIL-01_19_2022-SVCWIND-1^06239004.0255242 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
940688292-26092-DETAIL-01_20_2022-GO95MLD-1^06241005.0115541 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
759107313-78014-DETAIL-01_27_2022-SVCROAD-2^06241005.0115602 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
33012443-22174-DETAIL-01_13_2022-SVCROAD-1^06241005.0115608 | OTHER | CA-TIER-2 | Distribution | 2022-01-13 | 2025-01-13 | 2
233236181-49042-DETAIL-01_27_2022-GO95TCH-1^06241005.0116500 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
311790152-76004-DETAIL-01_27_2022-ABNDEQPM-1^06241005.0116602 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2027-01-27 | 3
876095313-34494-DETAIL-01_20_2022-GUYHINS-2^06241005.0116608 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
894649221-54032-DETAIL-01_26_2022-GO95MLD-1^06241005.0117400 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
21749073-91212-DETAIL-01_26_2022-GO95HV-1^06241005.0117402 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2027-01-26 | 3
939646813-43802-DETAIL-01_26_2022-GO95TCH-1^06241005.0117403 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
110619611-31932-DETAIL-01_26_2022-GO95HV-1^06241005.0117405 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2027-01-26 | 3
110619611-31932-DETAIL-01_26_2022-SVCWIND-1^06241005.0117405 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
916373640-67532-DETAIL-01_26_2022-GO95MLD-1^06241005.0117501 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
574979079-4071-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
574979079-4071-DETAIL-01_25_2023-COPLLEAN-1^06148003.0355700 | POLE | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
422878189-54670-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355903 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
815329460-46542-DETAIL-01_25_2023-GO95MLD-1^06148003.0356900 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
920301819-29612-DETAIL-01_24_2023-GO95HV-1^06148003.0368901 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
920301819-29612-DETAIL-01_24_2023-GO95MLD-1^06148003.0368901 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
489475360-72889-AUDIT-01_18_2023-GO95HV-1^06148004.0139000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
635651741-78989-ADMIN-03_10_2023-GO95CL10-1^06148004.0148200 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
813767351-58989-AUDIT-01_18_2023-SVCROAD-1^06148004.0149200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
374096973-69109-DETAIL-01_16_2023-GO95HV-1^06148004.0150000 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
302898230-4789-DETAIL-01_09_2023-GO95MLD-1^06148003.0155300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
418621520-43789-DETAIL-01_09_2023-GO95MLD-1^06148003.0156300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
262938960-29790-DETAIL-01_24_2022-GO95MLD-1^06239004.0256204 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
262938960-29790-DETAIL-01_24_2022-SVCWIND-1^06239004.0256204 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
329366836-15570-DETAIL-01_19_2022-GO95MLD-1^06239004.0256207 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
751955006-63370-DETAIL-01_24_2022-GO95MLD-1^06239004.0256208 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
751955006-63370-DETAIL-01_24_2022-SVCROOF-1^06239004.0256208 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
793327204-34360-DETAIL-01_24_2022-SVCWIND-1^06239004.0256209 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
201714994-72360-DETAIL-01_18_2022-GO95MLD-1^06239004.0256210 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
201714994-72360-DETAIL-01_18_2022-GO95TCH-1^06239004.0256210 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
201714994-72360-DETAIL-01_18_2022-SVCWIND-1^06239004.0256210 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
385996515-15870-DETAIL-01_24_2022-GO95MLD-1^06239004.0256211 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
385996515-15870-DETAIL-01_24_2022-SVCWIND-1^06239004.0256211 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
596883106-24261-DETAIL-11_15_2022-GO95MLD-1^06239004.0365600 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
932847578-58578-DETAIL-01_16_2023-GO95MLD-1^06148004.0165302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
751740215-73779-DETAIL-01_16_2023-GO95MLD-1^06148004.0165304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
751740215-73779-DETAIL-01_16_2023-RISEBKSP-1^06148004.0165304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
310145405-74879-DETAIL-01_16_2023-GO95MLD-1^06148004.0165305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
87574840-25840-DETAIL-01_16_2023-GO95TCH-1^06148004.0166200 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
545648575-61909-DETAIL-01_16_2023-POLETOP-1^06148004.0166305 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
244519479-84680-DETAIL-01_24_2023-COPLLEAN-1^06148003.0265502 | POLE | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
864769069-76589-DETAIL-01_30_2023-GO95MLD-1^06148003.0295400 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
505151649-7679-DETAIL-01_30_2023-GO95BLTC-1^06148003.0295402 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
822753719-54379-DETAIL-01_30_2023-GO95BLTC-1^06148003.0295501 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
919750699-25589-DETAIL-01_30_2023-CONDFRAY-1^06148003.0295601 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
437624993-41790-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355003 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
621314168-5130-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0099000 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
743916779-55353-DETAIL-01_10_2023-SVCDEFLC-2^06240004.0099001 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
412781893-85380-DETAIL-01_11_2023-POLESTEP-1^06240004.0099003 | POLE | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
244899528-58830-DETAIL-01_11_2023-SVCDEFLC-1^06240004.0099006 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
713276544-82760-DETAIL-01_11_2023-GO95MLD-1^06240004.0099042 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
554572814-50560-AUDIT-02_07_2023-SVCROAD-1^06240004.0099045 | OTHER | CA-TIER-2 | Distribution | 2023-02-07 | 2026-02-07 | 2
558618254-86860-DETAIL-01_11_2023-GO95TCH-1^06240004.0099141 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
566637345-70240-DETAIL-05_08_2023-SVCROAD-1^06240004.0100012 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
34374854-21740-DETAIL-05_08_2023-GO95MLD-1^06240004.0100401 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
368636265-66940-DETAIL-05_08_2023-GO95MLD-1^06240004.0100402 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
891505538-16550-DETAIL-05_08_2023-GO95MLD-1^06240004.0100500 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
949933615-66909-DETAIL-01_16_2023-GO95MLD-1^06148004.0164140 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
471956314-86909-DETAIL-01_16_2023-GUYHINS-1^06148004.0164200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
246769105-26889-ADMIN-03_10_2023-GO95CL10-1^06148004.0183201 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
455444505-86079-DETAIL-01_10_2023-GO95MLD-1^06148004.0183203 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
455444505-86079-ADMIN-03_10_2023-GO95CL10-1^06148004.0183203 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
70749994-76889-DETAIL-01_10_2023-GO95MLD-1^06148004.0183204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
521679055-47889-AUDIT-02_06_2023-GO95MLD-1^06148004.0184203 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
215173555-81579-DETAIL-01_10_2023-GO95MLD-1^06148004.0184204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
822696061-61879-DETAIL-01_10_2023-GO95MLD-1^06148004.0184205 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
685097671-95989-DETAIL-01_10_2023-GO95TCH-1^06148004.0186201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
692654924-82909-DETAIL-01_16_2023-GO95MLD-1^06148004.0164301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
157384174-72689-DETAIL-01_16_2023-GO95HV-1^06148004.0164303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
284210447-27140-DETAIL-03_25_2021-GO95MLD-1^06240002.0315203 | OTHER | CA-TIER-2 | Distribution | 2021-03-25 | 2026-03-25 | 3
24962027-95140-DETAIL-03_25_2021-GO95MLD-1^06240002.0317110 | OTHER | CA-TIER-2 | Distribution | 2021-03-25 | 2024-03-25 | 2
495656938-73340-DTLSB-05_03_2021-GO95HV-1^06240003.0075000 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2026-05-03 | 3
925496148-18340-DTLSB-05_03_2021-GO95MLD-1^06240003.0076100 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2026-05-03 | 3
675650958-98340-DTLSB-05_03_2021-GO95MLD-1^06240003.0076102 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
946060668-80440-DTLSB-05_03_2021-GO95MLD-1^06240003.0077201 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
155019378-38440-DTLSB-05_03_2021-GO95MLD-1^06240003.0078300 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
395015888-24540-DTLSB-05_03_2021-GO95MLD-1^06240003.0078400 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
898298008-17050-DTLSB-05_05_2021-GO95MLD-1^06240003.0080601 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2024-05-05 | 2
973909138-350-DTLSB-05_05_2021-GO95HV-1^06240003.0081700 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2026-05-05 | 3
973909138-350-DTLSB-05_05_2021-GO95MLD-2^06240003.0081700 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2024-05-05 | 2
796248368-51450-DTLSB-05_05_2021-GO95HV-1^06240003.0082900 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2026-05-05 | 3
567072805-90109-DETAIL-01_19_2023-SVCROAD-1^06148004.0199601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
645638125-68179-DETAIL-01_19_2023-ABNDEQPM-1^06148004.0199801 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
453083105-96109-DETAIL-01_23_2023-CONDFRAY-1^06148004.0200001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
260773315-36879-DETAIL-01_23_2023-GO95MLD-1^06148004.0200200 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
189044191-18779-DETAIL-01_19_2023-GO95MLD-1^06148004.0200600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
777276726-72479-DETAIL-01_24_2023-GO95CL10-1^06148004.0182101 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
777276726-72479-DETAIL-01_24_2023-GO95MLD-1^06148004.0182101 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
911087461-86879-DETAIL-01_24_2023-ABNDEQPM-1^06148004.0182200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
911087461-86879-DETAIL-01_24_2023-GO95TCH-1^06148004.0182200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
203607075-64889-DETAIL-01_10_2023-GO95HV-1^06148004.0182202 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2028-01-10 | 3
721781521-18379-DETAIL-01_24_2023-GO95MLD-1^06148004.0182203 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
699172542-96989-DETAIL-01_10_2023-GO95MLD-1^06148004.0182206 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
583706414-13421-DETAIL-05_09_2022-ABNDEQPM-1^06241005.0011402 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
474067312-55211-DETAIL-05_09_2022-CLMBHAZ-1^06241005.0011502 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
880821956-50661-DETAIL-05_09_2022-GO95TCH-1^06241005.0011645 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
381174364-78031-DETAIL-05_09_2022-GO95MLD-1^06241005.0011705 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
907037805-37241-DETAIL-05_09_2022-GO95HV-1^06241005.0011707 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
907037805-37241-DETAIL-05_09_2022-GO95MLD-1^06241005.0011707 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
236817316-39971-DETAIL-05_10_2022-GO95MLD-1^06241005.0011743 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
31501234-22721-DETAIL-05_10_2022-GO95MLD-1^06241005.0012404 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
680107253-86128-DETAIL-05_10_2022-GUYHINS-1^06241005.0012405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
439350454-57721-DETAIL-05_10_2022-GO95MLD-1^06241005.0012409 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
923218366-48061-DETAIL-05_10_2022-GO95MLD-1^06241005.0012500 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
407611256-41661-DETAIL-05_09_2022-GO95MLD-1^06241005.0012501 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
760753708-87081-ADMIN-01_11_2022-POLEDERP-1^06147001.0106501 | POLE | CA-NON-TIER | Distribution | 2022-01-11 | 2025-01-11 | 2
813031981-45242-DETAIL-03_01_2022-GO95TCH-1^06146006.0069400 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
642107491-96961-DETAIL-03_08_2022-GO95MLD-1^06146006.0070902 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
808380699-14122-DETAIL-03_08_2022-COPLLEAN-1^06146006.0070903 | POLE | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
214397900-9150-DETAIL-03_08_2022-COPLLEAN-1^06146006.0071900 | POLE | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
714504861-11461-DETAIL-03_07_2022-GO95MLD-1^06146006.0074501 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
2612320-94499-DETAIL-03_08_2022-GO95HV-1^06146006.0074900 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
258920031-25690-DETAIL-03_02_2022-GO95HV-1^06146006.0075100 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
258920031-25690-DETAIL-03_02_2022-GO95TCH-1^06146006.0075100 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
148701950-50890-DETAIL-03_02_2022-GO95HV-1^06146006.0075101 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
64504551-83180-DETAIL-03_02_2022-GO95MLD-1^06146006.0075200 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
534543100-22321-DETAIL-03_08_2022-GO95MLD-1^06146006.0075501 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
43261524-76689-DETAIL-01_23_2023-GO95MLD-1^06148004.0197001 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
220278255-65579-DETAIL-01_18_2023-GO95MLD-2^06148004.0207701 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
277165745-9-DETAIL-01_18_2023-GO95MLD-1^06148004.0207800 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
489594245-40009-DETAIL-01_18_2023-GO95HV-1^06148004.0207900 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
489594245-40009-DETAIL-01_18_2023-GO95MLD-1^06148004.0207900 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
955473781-2779-AUDIT-02_16_2023-ABNDEQPM-1^06148004.0207901 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
533794125-85009-DETAIL-01_19_2023-COPLLEAN-1^06148004.0208601 | POLE | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
763712606-95379-DETAIL-01_19_2023-GO95BLTC-1^06148004.0209400 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
66981733-50309-DETAIL-01_18_2023-CONDFRAY-1^06148004.0210001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
984194113-89079-DETAIL-01_19_2023-GO95MLD-1^06148004.0210500 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
984194113-89079-DETAIL-01_19_2023-GO95MLD-2^06148004.0210500 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
243654341-18779-DETAIL-01_19_2023-SVCROAD-1^06148004.0210600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
965465209-45763-DETAIL-03_09_2022-GUYHINS-1^06146006.0164200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
23467968-56050-DETAIL-03_02_2022-GO95HV-1^06146006.0185800 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
671421488-32241-DETAIL-03_02_2022-SVCENTCO-1^06146006.0185900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
987352486-83486-DETAIL-01_26_2023-GO95TCH-1^06147003.0167901 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
214953930-5450-DETAIL-01_26_2023-GO95BLTC-1^06147003.0234500 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
214953930-5450-DETAIL-01_26_2023-GO95MLD-1^06147003.0234500 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
65878920-84180-DETAIL-01_26_2023-GO95CL10-1^06147003.0234600 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
856816210-35182-DETAIL-01_26_2023-GO95HV-1^06147003.0235701 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
950454000-79623-DETAIL-01_26_2023-GO95HV-1^06147003.0235900 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
551260300-94141-DETAIL-01_24_2023-GO95HV-1^06147003.0249900 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
548486190-51541-DETAIL-01_24_2023-GO95MLD-1^06147003.0249901 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
664225708-54921-DETAIL-03_02_2022-GO95MLD-1^06146006.0186900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
804839993-47430-DETAIL-04_25_2023-GO95MLD-1^06240004.0062705 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
94019936-18570-DETAIL-01_18_2022-GO95MLD-1^06239004.0257842 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
638692800-80690-DETAIL-01_25_2022-GO95MLD-1^06239004.0258004 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
137131940-61590-DETAIL-01_25_2022-GO95HV-1^06239004.0258006 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
954510988-80988-DETAIL-01_25_2022-SVCROAD-1^06239004.0258009 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
506235205-5270-DETAIL-01_25_2022-GO95MLD-1^06239004.0258301 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
506235205-5270-DETAIL-01_25_2022-GO95TCH-1^06239004.0258301 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
713329821-44101-DETAIL-01_25_2022-GO95MLD-1^06239004.0258441 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
265614404-64560-DETAIL-01_25_2022-GO95BLTC-1^06239004.0258500 | OTHER | CA-TIER-3 | Distribution | 2022-01-25 | 2027-01-25 | 3
381777815-32870-DETAIL-01_18_2022-SVCWIND-1^06239004.0258740 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
750483076-98770-DETAIL-01_18_2022-GO95BLTC-1^06239004.0258842 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
750483076-98770-DETAIL-01_18_2022-GO95MLD-1^06239004.0258842 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
416972476-13070-DETAIL-01_18_2022-GO95BLTC-1^06239004.0258941 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
626138399-15279-DETAIL-02_01_2022-GO95BLTC-1^06147005.0262705 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2027-02-01 | 3
626138399-15279-DETAIL-02_01_2022-GO95MLD-1^06147005.0262705 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
876983069-18179-DETAIL-01_31_2022-GO95MLD-1^06147005.0262707 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
740993769-79379-DETAIL-01_31_2022-GO95HV-1^06147005.0262708 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2027-01-31 | 3
740993769-79379-DETAIL-01_31_2022-GO95MLD-1^06147005.0262708 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
864535566-42902-DETAIL-02_06_2023-GO95MLD-1^06147002.0318901 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
765850756-21002-DETAIL-02_01_2023-GO95MLD-1^06147002.0319100 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
447349306-47501-DETAIL-02_06_2023-GUYSLACK-1^06147002.0319900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
898677329-19122-DETAIL-01_25_2023-ABNDEQPM-1^06147003.0023901 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
898677329-19122-DETAIL-01_25_2023-GO95MLD-1^06147003.0023901 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
623091941-2201-ADMIN-03_06_2023-GO95HV-1^06147003.0112000 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
633491479-50151-DETAIL-01_24_2023-GO95CL10-1^06147003.0129600 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
310282351-14450-DETAIL-01_18_2023-GO95TCH-1^06148004.0221001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
938754064-17609-DETAIL-01_18_2023-GO95HV-1^06148004.0221004 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
65211113-32209-DETAIL-01_17_2023-GO95MLD-1^06148004.0221700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
319285034-9579-DETAIL-01_17_2023-GO95MLD-2^06148004.0222700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
815023224-38279-DETAIL-01_18_2023-GO95HV-1^06148004.0207500 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
815023224-38279-DETAIL-01_18_2023-GO95MLD-1^06148004.0207500 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
815023224-38279-DETAIL-01_18_2023-GO95MLD-2^06148004.0207500 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
872484884-58789-DETAIL-01_19_2023-INSULDMG-1^06148004.0207601 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
984444755-90009-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
984444755-90009-DETAIL-01_18_2023-CONDFRAY-2^06148004.0207700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
220278255-65579-DETAIL-01_18_2023-COPLLEAN-1^06148004.0207701 | POLE | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
220278255-65579-DETAIL-01_18_2023-GO95HV-1^06148004.0207701 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
605386429-12209-DETAIL-01_31_2022-GO95MLD-1^06147005.0260600 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
199697339-42209-AUDIT-03_10_2022-GO95MLD-1^06147005.0260700 | OTHER | CA-NON-TIER | Distribution | 2022-03-10 | 2025-03-10 | 2
685720868-50279-DETAIL-02_02_2022-GO95HV-1^06147005.0261300 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
439670278-11979-DETAIL-02_02_2022-GO95HV-1^06147005.0261400 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
439670278-11979-DETAIL-02_02_2022-GO95MLD-1^06147005.0261400 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
439582539-86609-DETAIL-02_02_2022-ABNDEQPM-1^06147005.0261500 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
9948349-50309-DETAIL-01_31_2022-GO95MLD-1^06147005.0261701 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
600506049-71309-DETAIL-01_31_2022-XARMSPCR-1^06147005.0261702 | CROSSARM | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
657639478-49809-DETAIL-02_02_2022-SVCENTBK-1^06147005.0262301 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
121980929-89479-DETAIL-02_02_2022-SVCRUBLG-1^06147005.0262401 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
590340109-97209-DETAIL-02_01_2022-GO95HV-1^06147005.0262701 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2027-02-01 | 3
150980299-37209-DETAIL-02_01_2022-GO95MLD-1^06147005.0262704 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
279401196-17310-DETAIL-03_21_2023-GO95MLD-1^06240004.0163605 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
279401196-17310-DETAIL-03_21_2023-GUYHINS-1^06240004.0163605 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
611816-2410-DETAIL-03_27_2023-GO95MLD-1^06240004.0163608 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
5705003-24480-DETAIL-03_21_2023-GO95MLD-1^06240004.0163702 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
897252593-49380-DETAIL-03_21_2023-GO95MLD-1^06240004.0163705 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
573380213-70780-DETAIL-03_28_2023-GO95HV-1^06240004.0163900 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
560341048-7550-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0163941 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
837130658-89550-DETAIL-04_12_2023-RISEBKSP-1^06240004.0163942 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
594877859-16870-DETAIL-03_22_2023-GO95MLD-1^06240004.0164300 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
281951809-67170-DETAIL-03_22_2023-GRDRODHI-1^06240004.0164301 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
281951809-67170-DETAIL-03_22_2023-GRDRODHI-2^06240004.0164301 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
722168649-90870-DETAIL-03_22_2023-GO95TCH-1^06240004.0164302 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
56185653-6360-DETAIL-02_09_2023-GO95MLD-1^06146004.0089000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
360636412-88500-DETAIL-02_08_2023-GO95HV-1^06146002.0276901 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
351741922-76790-DETAIL-02_08_2023-GO95CL10-1^06146002.0277900 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
704395573-89631-DETAIL-02_09_2023-GO95MLD-1^06146004.0065201 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
164660373-8110-DETAIL-02_09_2023-GO95MLD-1^06146004.0065300 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
514769363-31491-DETAIL-02_09_2023-GO95MLD-1^06146004.0065401 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
34438183-96930-DETAIL-02_09_2023-GO95MLD-1^06146004.0066000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
10128383-35469-DETAIL-02_09_2023-GO95HV-1^06146004.0076600 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
10128383-35469-DETAIL-02_09_2023-GO95MLD-1^06146004.0076600 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
498488633-89171-DETAIL-02_09_2023-GO95CL10-1^06146004.0101000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
498488633-89171-DETAIL-02_09_2023-GO95MLD-1^06146004.0101000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
234920824-85170-DETAIL-02_09_2023-GO95MLD-1^06146004.0161900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
858491704-82779-DETAIL-02_15_2022-GO95MLD-1^06147005.0335000 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
660121464-16109-DETAIL-02_15_2022-POLETOP-1^06147005.0335900 | POLE | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
258882894-90979-DETAIL-02_15_2022-ABNDEQPM-1^06147005.0336200 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
554074169-21579-DETAIL-02_01_2022-GO95MLD-1^06147005.0265402 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2027-02-01 | 3
119672490-30590-DETAIL-01_31_2022-GO95HV-1^06147005.0265704 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2027-01-31 | 3
119672490-30590-DETAIL-01_31_2022-GO95TCH-1^06147005.0265704 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
656662781-34781-DETAIL-01_31_2022-GO95MLD-1^06147005.0265804 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
997358828-67409-DETAIL-02_02_2022-SVCENTCO-1^06147005.0266201 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
933232878-11979-DETAIL-02_01_2022-SVCENTCO-1^06147005.0266300 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
220765549-16779-DETAIL-02_01_2022-GO95MLD-1^06147005.0266303 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2027-02-01 | 3
961463968-93409-DETAIL-02_01_2022-GO95MLD-1^06147005.0266404 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
414853228-87279-DETAIL-02_14_2022-GO95MLD-1^06146005.0036200 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
774931683-64709-DETAIL-02_14_2022-SVCROAD-1^06146005.0036500 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
149692583-9609-DETAIL-02_14_2022-GO95HV-1^06146005.0036601 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
318774796-57796-DETAIL-02_14_2022-GO95MLD-1^06146005.0036703 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
318774796-57796-DETAIL-02_14_2022-GUYHINS-1^06146005.0036703 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
219797596-59596-DETAIL-02_14_2022-GO95MLD-1^06146005.0036803 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
859427603-96709-DETAIL-02_14_2022-GO95HV-1^06146005.0037202 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
724669951-40051-DETAIL-02_14_2022-SVCRUBLG-1^06146005.0037204 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
977814308-55779-DETAIL-02_14_2022-GO95MLD-1^06146005.0037301 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
977814308-55779-DETAIL-02_14_2022-GO95TCH-1^06146005.0037301 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
819860609-85479-DETAIL-02_23_2022-GO95MLD-1^06146005.0046200 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
692548743-31079-DETAIL-02_23_2022-ABNDEQPM-1^06146005.0046502 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
240497846-46679-DETAIL-10_18_2021-GO95CL10-1^06148005.0298902 | OTHER | CA-NON-TIER | Distribution | 2021-10-18 | 2026-10-18 | 3
240497846-46679-DETAIL-10_18_2021-SVCROAD-1^06148005.0298902 | OTHER | CA-NON-TIER | Distribution | 2021-10-18 | 2024-10-18 | 2
686446436-81699-DETAIL-10_12_2021-ENCHRW-1^06148005.0322903 | OTHER | CA-NON-TIER | Distribution | 2021-10-12 | 2024-10-12 | 2
428048231-66999-DETAIL-03_16_2022-POLETOP-1^06148006.0308100 | POLE | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
713952756-39850-DTLSB-04_22_2021-GO95MLD-1^06236005.0114700 | OTHER | CA-TIER-2 | Distribution | 2021-04-22 | 2024-04-22 | 2
358491331-73079-DETAIL-01_17_2023-GO95TCH-1^06148004.0220701 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
593232111-87679-DETAIL-01_17_2023-GO95MLD-1^06148004.0220702 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
876130821-41209-DETAIL-01_17_2023-COPLLEAN-1^06148004.0220800 | POLE | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
971142383-71209-DETAIL-01_17_2023-GO95HV-1^06148004.0220801 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
344302683-10209-DETAIL-01_17_2023-GO95MLD-1^06148004.0220900 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
726466048-74291-DETAIL-03_03_2022-GO95MLD-1^06146005.0123901 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
251285110-72479-DETAIL-02_15_2022-GO95HV-1^06146005.0023001 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
883380453-47955-DETAIL-02_16_2022-GO95HV-1^06146005.0023401 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
42003100-42579-DETAIL-02_16_2022-GO95MLD-1^06146005.0025000 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
912975489-382-DETAIL-02_16_2022-GO95HV-1^06146005.0025002 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
503250109-65481-DETAIL-02_16_2022-GUYHINS-1^06146005.0025400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
566665909-34361-DETAIL-02_16_2022-GO95TCH-1^06146005.0025402 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
8851697-11449-DETAIL-02_10_2022-GO95HV-1^06146005.0026900 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
475777089-11479-DETAIL-02_16_2022-GO95HV-1^06146005.0027001 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
20946887-3740-DETAIL-02_10_2022-GO95HV-1^06146005.0027900 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
156425739-56579-DETAIL-02_16_2022-GO95MLD-1^06146005.0028000 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
241598977-70080-DETAIL-02_10_2022-GO95HV-1^06146005.0029900 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
748129544-10109-DETAIL-02_15_2022-GO95HV-1^06147005.0331400 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
106573174-57189-DETAIL-02_15_2022-GO95TCH-1^06147005.0332601 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
428672334-96009-DETAIL-02_15_2022-GO95MLD-1^06147005.0334300 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
377562874-13109-DETAIL-02_15_2022-GO95HV-1^06147005.0334700 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
670138055-36679-DETAIL-02_15_2022-GO95HV-1^06147005.0334701 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
641527874-40399-DETAIL-02_15_2022-GO95MLD-1^06147005.0335700 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
547777774-20399-DETAIL-02_15_2022-GO95HV-1^06147005.0335701 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
258882894-90979-DETAIL-02_15_2022-GO95HV-1^06147005.0336200 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
957452111-4243-DETAIL-02_14_2022-GO95MLD-1^06147005.0360901 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
328520678-80678-DETAIL-02_09_2022-GUYHINS-1^06147005.0365201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
733517231-51711-DETAIL-02_16_2022-INSULDMG-1^06147005.0365900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
853533258-85562-DETAIL-02_16_2022-GO95HV-1^06147005.0367200 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
733802958-20009-DETAIL-02_22_2022-GO95HV-1^06146005.0105000 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2027-02-22 | 3
54952068-63909-DETAIL-02_28_2022-GO95HV-1^06146005.0108401 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
710622309-64479-DETAIL-02_17_2022-GO95MLD-1^06146005.0109502 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
124034359-16679-DETAIL-02_17_2022-GO95MLD-1^06146005.0111001 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
894078069-7879-DETAIL-02_17_2022-GO95HV-1^06146005.0113500 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
361514805-72319-DTLSB-03_21_2022-GO95BLTC-1^06146005.0142801 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
361514805-72319-DTLSB-03_21_2022-GO95MLD-1^06146005.0142801 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
835735696-37696-DTLSB-03_21_2022-GO95MLD-1^06146005.0142802 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
799666663-14319-DTLSB-03_21_2022-POLETOP-1^06146005.0143702 | POLE | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
766748095-66602-DTLSB-03_21_2022-GO95HV-1^06146005.0145500 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
171056385-69310-DTLSB-03_21_2022-GO95HV-1^06146005.0145501 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
35549286-55971-DETAIL-11_14_2022-GO95CL10-1^06239004.0365741 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
35549286-55971-DETAIL-11_14_2022-GUYHINS-1^06239004.0365741 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
705389866-58261-DETAIL-11_14_2022-GO95CL10-1^06239004.0365802 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
358093516-99871-DETAIL-11_14_2022-SVCWIND-2^06239004.0365842 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
565555763-58330-DETAIL-04_26_2023-GO95MLD-1^06240004.0066001 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
73200753-74330-DETAIL-05_01_2023-GO95MLD-1^06240004.0066005 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
403207076-10176-DETAIL-04_26_2023-SVCDEFLC-1^06240004.0067004 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
232985663-98330-DETAIL-05_01_2023-GO95MLD-1^06240004.0067100 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
164367003-70060-DETAIL-01_12_2023-GO95HV-1^06240004.0072341 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2028-01-12 | 3
164367003-70060-DETAIL-01_12_2023-GO95MLD-1^06240004.0072341 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
957702004-8360-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0076300 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
792910294-27629-DETAIL-04_26_2022-GRDRODHI-1^06143012.0239001 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
981364994-5229-DETAIL-04_26_2022-GO95HV-1^06143012.0239203 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
223545664-22329-DETAIL-04_26_2022-GO95MLD-1^06143012.0239305 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
167742084-21629-DETAIL-04_27_2022-GO95TCH-1^06143012.0239601 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
789751459-92729-DETAIL-04_28_2022-GO95MLD-1^06143012.0243400 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
805917449-72729-DETAIL-04_28_2022-GO95HV-1^06143012.0243401 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
673344169-53729-DETAIL-04_28_2022-GO95MLD-1^06143012.0243500 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
911854979-84229-AUDIT-05_03_2022-GO95MLD-1^06143012.0243602 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
260322149-92529-DETAIL-04_28_2022-GO95HV-1^06143012.0243801 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
717938211-31429-DETAIL-05_02_2022-SVCNEUT-1^06143012.0244000 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
169987091-18729-DETAIL-04_27_2022-GO95MLD-1^06143012.0244005 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
137137698-66529-DETAIL-04_27_2022-SVCNEUT-1^06143012.0244101 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
808817875-96322-DETAIL-02_21_2022-GO95HV-1^06146005.0206600 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
166110484-77810-AUDIT-03_30_2022-GO95MLD-1^06146005.0206700 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
166110484-77810-AUDIT-04_04_2022-CUTOUTAR-1^06146005.0206700 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
755744785-8071-DETAIL-02_21_2022-GO95HV-1^06146005.0207000 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
801858574-60892-DETAIL-02_28_2022-GO95HV-1^06146005.0207700 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
774510331-52331-DETAIL-02_22_2022-GO95MLD-1^06146005.0212401 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
206919786-34886-DETAIL-02_24_2022-GO95MLD-1^06146005.0214402 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
206919786-34886-DETAIL-02_24_2022-SVCROAD-1^06146005.0214402 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
22220644-67950-DTLSB-03_22_2022-GUYHINS-1^06146005.0137202 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
22220644-67950-DTLSB-03_22_2022-SVCROAD-1^06146005.0137202 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
101091593-69240-DTLSB-03_23_2022-GO95MLD-1^06146005.0137401 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
938772344-4692-DTLSB-03_22_2022-GO95MLD-1^06146005.0138201 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
938772344-4692-DTLSB-03_22_2022-SVCRUBLG-1^06146005.0138201 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
925694605-15605-DETAIL-05_02_2022-GO95MLD-1^06143012.0247100 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
256539189-63829-DETAIL-04_28_2022-GO95MLD-1^06143012.0247700 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
429416569-22829-DETAIL-04_28_2022-GO95MLD-1^06143012.0247704 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
571646643-68429-DETAIL-05_02_2022-GO95MLD-1^06143012.0247902 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
559001849-41329-DETAIL-05_04_2022-GO95HV-1^06143012.0248700 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
14732830-32929-DETAIL-05_04_2022-GO95HV-1^06143012.0249600 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
14732830-32929-DETAIL-05_04_2022-GO95MLD-1^06143012.0249600 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
288209179-77129-DETAIL-05_04_2022-GO95MLD-1^06143012.0249701 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
336636524-7229-DETAIL-04_25_2022-GRDRODHI-1^06143012.0250000 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
844846075-74529-DETAIL-04_26_2022-GO95HV-1^06143012.0250601 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
704476594-81229-DETAIL-04_25_2022-GO95HV-1^06143012.0251200 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
294570874-58229-DETAIL-04_25_2022-GO95MLD-1^06143012.0251605 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
237941928-84579-DETAIL-03_09_2022-GO95MLD-1^06147006.0181001 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
353910358-80479-DETAIL-03_09_2022-GO95MLD-1^06147006.0181202 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
417349378-38079-DETAIL-03_09_2022-ABNDEQPM-1^06147006.0181203 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
963604258-28179-DETAIL-03_09_2022-GO95TCH-1^06147006.0182000 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
423912404-16089-DETAIL-03_16_2022-GO95MLD-1^06147006.0190500 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
423912404-16089-DETAIL-03_16_2022-GUYHINS-1^06147006.0190500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
802649158-90079-DETAIL-03_09_2022-GO95MLD-1^06147006.0192902 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
564786249-89779-DETAIL-02_28_2022-ABNDEQPM-1^06147006.0300000 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
595244459-39301-DETAIL-02_28_2022-GO95MLD-1^06147006.0305104 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
73416699-91500-DETAIL-02_28_2022-GO95HV-1^06147006.0307101 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
709957261-49851-DETAIL-03_07_2022-GO95HV-1^06147006.0316101 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
709957261-49851-DETAIL-03_07_2022-GO95MLD-1^06147006.0316101 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
516959397-60497-DETAIL-04_26_2022-GO95MLD-1^06143012.0256301 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
961295184-17629-DETAIL-04_28_2022-GO95MLD-1^06143012.0256600 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
297091423-31529-DETAIL-04_25_2022-GRDRODHI-1^06143012.0255000 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
673174673-35529-DETAIL-04_25_2022-GO95MLD-1^06143012.0255300 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
627848253-55429-DETAIL-04_27_2022-GO95MLD-1^06143012.0255701 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
249770414-96229-DETAIL-04_25_2022-GO95MLD-1^06143012.0256202 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
53771083-11429-DETAIL-04_28_2022-GO95MLD-1^06143012.0256503 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
836123583-89329-DETAIL-04_28_2022-GO95HV-1^06143012.0256602 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
595905834-34229-DETAIL-04_26_2022-GO95MLD-1^06143012.0257403 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
450342225-65129-DETAIL-04_26_2022-GO95HV-1^06143012.0257404 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
450342225-65129-DETAIL-04_26_2022-GO95MLD-1^06143012.0257404 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
24290384-47429-DETAIL-04_26_2022-GRDRODHI-1^06143012.0258203 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
562298504-54129-DETAIL-04_26_2022-GO95MLD-1^06143012.0258300 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
191499973-46330-DTLSB-03_16_2022-GRDRODHI-1^06146005.0221900 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
557442973-35151-DTLSB-03_16_2022-GUYSLACK-1^06146005.0221901 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
460231323-66721-DTLSB-03_17_2022-CLRTOUCH-1^06146005.0221903 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
460231323-66721-DTLSB-03_17_2022-GUYSLACK-1^06146005.0221903 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
156824164-390-DTLSB-03_16_2022-GO95TCH-1^06146005.0222400 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
586610454-81791-DTLSB-03_16_2022-GO95HV-1^06146005.0222402 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2027-03-16 | 3
424659703-80779-DTLSB-03_17_2022-GO95BLTC-1^06146005.0222701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
424659703-80779-DTLSB-03_17_2022-GO95MLD-1^06146005.0222701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
424659703-80779-DTLSB-03_17_2022-GO95STUB-1^06146005.0222701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
424659703-80779-DTLSB-03_17_2022-GUYHINS-1^06146005.0222701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
883149524-81472-DTLSB-03_17_2022-CUTOUTAR-1^06146005.0222901 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
883149524-81472-DTLSB-03_17_2022-GO95MLD-1^06146005.0222901 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
775212813-28679-DTLSB-03_21_2022-ABNDEQPM-1^06146005.0227200 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
423515264-95264-DETAIL-04_20_2022-GO95MLD-1^06143012.0363100 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
423515264-95264-DETAIL-04_20_2022-GRDRODHI-1^06143012.0363100 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
962620623-88629-DETAIL-04_20_2022-GO95HV-1^06143012.0363301 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
697094043-24729-DETAIL-04_21_2022-GO95MLD-1^06143012.0363500 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
847599074-46429-DETAIL-04_21_2022-SVCNEUT-1^06143012.0363700 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
315780993-95629-DETAIL-04_20_2022-GO95MLD-1^06143012.0366005 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
594374201-51429-DETAIL-04_20_2022-GO95MLD-1^06143012.0366006 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
229031393-44629-DETAIL-04_20_2022-GUYSLACK-1^06143012.0366007 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
391597026-70126-DETAIL-04_20_2022-GO95MLD-1^06143012.0366100 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
785429221-4729-DETAIL-04_20_2022-GO95MLD-1^06143012.0367001 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
785429221-4729-ADMIN-10_24_2022-XARMBRAC-1^06143012.0367001 | CROSSARM | CA-NON-TIER | Distribution | 2022-10-24 | 2025-10-24 | 2
4976294-96629-DETAIL-04_20_2022-GO95TCH-1^06143012.0369001 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
729134485-76410-DETAIL-11_10_2022-GO95HV-1^06238004.0222501 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
729134485-76410-DETAIL-11_10_2022-GO95HV-2^06238004.0222501 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
373467235-30310-DETAIL-11_10_2022-GO95HV-1^06238004.0222502 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
680397926-54310-DETAIL-11_18_2022-GO95HV-1^06238004.0222900 | OTHER | CA-TIER-2 | Distribution | 2022-11-18 | 2027-11-18 | 3
362291138-49340-DETAIL-11_17_2022-GO95MLD-1^06238004.0223300 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
209476776-63410-DETAIL-11_10_2022-SVCENTCO-1^06238004.0223540 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
599704676-7710-DETAIL-11_10_2022-GUYLOINS-1^06238004.0223702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
930992555-78310-DETAIL-11_10_2022-GRDRODHI-1^06238004.0223801 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
102985826-15310-DETAIL-11_10_2022-POLESTEP-1^06238004.0224901 | POLE | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
906035635-91310-DETAIL-11_10_2022-GO95MLD-1^06238004.0225600 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
418207646-63610-DETAIL-11_10_2022-GO95MLD-1^06238004.0225702 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
152996721-64150-DETAIL-11_17_2022-GUYLOINS-1^06238004.0270540 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
406957344-41460-DETAIL-04_12_2022-GO95TCH-1^06142012.0130413 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
406957344-41460-DETAIL-04_12_2022-GUYSLACK-1^06142012.0130413 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
226360343-71129-DETAIL-04_12_2022-GUYSLACK-1^06142012.0130504 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
3373803-73029-DETAIL-04_12_2022-SVCWIND-1^06142012.0130505 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
673117701-54529-DETAIL-04_12_2022-GRDRODHI-1^06142012.0130506 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
73203095-829-DETAIL-04_11_2022-GO95MLD-1^06142012.0130605 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
378316543-66129-DETAIL-04_12_2022-GO95MLD-1^06142012.0130606 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
378316543-66129-DETAIL-04_12_2022-SVCENTCO-1^06142012.0130606 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
735281150-91311-DETAIL-04_12_2022-GO95MLD-1^06142012.0130508 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
574173338-77471-DETAIL-04_12_2022-SVCENTCO-1^06142012.0130509 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
378316543-66129-DETAIL-04_12_2022-SVCENTCO-2^06142012.0130606 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
325646684-74729-DETAIL-04_12_2022-POLESTEP-1^06142012.0130608 | POLE | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
549125377-75377-DETAIL-04_03_2023-GO95HV-1^06143013.0333801 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
549125377-75377-DETAIL-04_03_2023-GO95MLD-1^06143013.0333801 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
263007377-37377-DETAIL-04_03_2023-RISESTRP-1^06143013.0333802 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
431079546-23129-DETAIL-04_05_2023-SVCDEFLC-1^06143014.0132001 | OTHER | CA-TIER-2 | Distribution | 2023-04-05 | 2026-04-05 | 2
953701183-42933-DETAIL-04_04_2023-GO95HV-1^06143014.0141001 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
240426316-31280-DETAIL-04_03_2023-GO95MLD-1^06143014.0146102 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2026-04-03 | 2
756404523-72071-DETAIL-04_03_2023-GO95HV-1^06143014.0162200 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
28300813-6670-DETAIL-04_03_2023-GO95HV-1^06143014.0173200 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
636724253-5651-DETAIL-04_03_2023-GO95HV-1^06143014.0176201 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
828859205-35892-DETAIL-04_03_2023-GO95HV-1^06143014.0181300 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
383325463-57329-DETAIL-04_03_2023-GO95TCH-1^06143014.0213700 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2026-04-03 | 2
523461793-74801-DETAIL-04_03_2023-ABNDEQPM-1^06143014.0213901 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
352846883-62129-DETAIL-04_12_2022-GO95MLD-1^06142012.0131505 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
385210623-43229-DETAIL-04_12_2022-GO95MLD-1^06142012.0131508 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
859132830-81429-DETAIL-04_11_2022-GO95MLD-1^06142012.0131600 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
859132830-81429-DETAIL-04_11_2022-GO95TCH-1^06142012.0131600 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
850341785-24829-DETAIL-04_13_2022-GO95MLD-1^06142012.0131607 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
850341785-24829-DETAIL-04_13_2022-GRDRODHI-1^06142012.0131607 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
392787165-73329-DETAIL-04_13_2022-POLESTEP-1^06142012.0131608 | POLE | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
392787165-73329-DETAIL-04_13_2022-SVCENTCO-1^06142012.0131608 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
954575690-54829-DETAIL-04_13_2022-GO95MLD-1^06142012.0131610 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
682291674-74229-DETAIL-04_13_2022-GO95MLD-1^06142012.0131617 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
427573083-40529-DETAIL-04_13_2022-GO95MLD-1^06142012.0131619 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
593948164-64129-DETAIL-04_19_2022-GUYHINS-1^06142012.0131707 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
948139574-79723-DETAIL-02_23_2022-GO95MLD-1^06146005.0285502 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
664209964-83921-DETAIL-02_24_2022-ABNDEQPM-1^06146005.0286600 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
485380914-9951-DETAIL-02_24_2022-GO95MLD-1^06146005.0286602 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
581676784-86481-DETAIL-02_24_2022-GO95HV-1^06146005.0287600 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
271149724-17610-DETAIL-02_24_2022-GO95HV-1^06146005.0288500 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
127917034-73999-DETAIL-02_24_2022-GO95HV-1^06146005.0289600 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
127917034-73999-DETAIL-02_24_2022-GO95MLD-1^06146005.0289600 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
665832024-71021-DETAIL-02_21_2022-GO95MLD-1^06146005.0297800 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
345586034-96690-DETAIL-02_21_2022-GRDRODHI-1^06146005.0297801 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
345586034-96690-DETAIL-02_21_2022-GRDRODHI-2^06146005.0297801 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
834242819-46919-DETAIL-02_21_2022-GO95MLD-1^06146005.0297901 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
965631270-3863-DETAIL-03_01_2022-GO95MLD-1^06146006.0052602 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
256404770-80190-DETAIL-03_01_2022-SVCROAD-1^06146006.0052603 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
283640303-59529-DETAIL-04_13_2022-SVCWIND-1^06142012.0131708 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
859890784-16529-DETAIL-04_14_2022-SVCWIND-1^06142012.0131709 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
859890784-16529-DETAIL-04_14_2022-SVCWIND-2^06142012.0131709 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
488455625-16829-DETAIL-04_11_2022-SVCWIND-2^06142012.0131710 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
202591533-2829-DETAIL-04_19_2022-GUYNOINS-1^06142012.0131712 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
240849953-92829-DETAIL-04_18_2022-GO95MLD-1^06142012.0131713 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
240849953-92829-DETAIL-04_18_2022-GRDRODHI-1^06142012.0131713 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
363579850-73950-DETAIL-04_19_2022-GUYNOINS-1^06142012.0131742 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
998765375-40229-DETAIL-04_11_2022-CLRTOUCH-1^06142012.0131801 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
716115674-56829-DETAIL-04_19_2022-GO95MLD-1^06142012.0131804 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
716115674-56829-DETAIL-04_19_2022-GRDRODHI-1^06142012.0131804 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
465090434-41829-DETAIL-04_19_2022-SVCWIND-1^06142012.0131805 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
374998653-18920-DTLSB-03_28_2022-POLETOP-1^06144006.0153101 | POLE | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
173400443-74610-DTLSB-03_24_2022-GO95HV-1^06144006.0153201 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
173400443-74610-DTLSB-03_24_2022-XARMSPCR-1^06144006.0153201 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-24 | 2025-03-24 | 2
185150333-79220-DTLSB-03_24_2022-GO95HV-1^06144006.0153400 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
618783903-2631-DTLSB-03_24_2022-GO95HV-1^06144006.0154901 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
455822456-75989-DTLSB-03_29_2022-GO95MLD-1^06144006.0162000 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
455822456-75989-DTLSB-03_29_2022-GUYHINS-1^06144006.0162000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
374998653-18920-DTLSB-03_28_2022-XARMSPCR-1^06144006.0153101 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
778164143-41232-DTLSB-03_24_2022-GO95HV-1^06144006.0153300 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
995450154-43989-DTLSB-03_29_2022-GO95MLD-1^06144006.0161000 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
995450154-43989-DTLSB-03_29_2022-GO95TCH-1^06144006.0161000 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
189664604-65430-DETAIL-04_19_2022-GRDRODHI-1^06142012.0133903 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
553413424-93329-DETAIL-04_21_2022-GO95MLD-1^06142012.0134002 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
553413424-93329-DETAIL-04_21_2022-GUYHINS-1^06142012.0134002 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
600746460-71429-DETAIL-04_19_2022-GO95MLD-1^06142012.0132909 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
471029245-55141-DETAIL-04_19_2022-GUYHINS-1^06142012.0132913 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
968764124-23473-DETAIL-04_13_2022-GO95MLD-1^06142012.0133400 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
505113600-11029-DETAIL-03_20_2017-SVCWIND-1^06142012.0133501 | OTHER | CA-NON-TIER | Distribution | 2017-03-20 | 2022-02-20 | 2
997361875-45753-DETAIL-04_13_2022-GO95MLD-1^06142012.0133601 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
624933954-24741-DETAIL-04_13_2022-SVCROOF-1^06142012.0133609 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
486135210-70451-DETAIL-04_18_2022-GO95CLSV-1^06142012.0133700 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
486135210-70451-DETAIL-04_18_2022-SVCWIND-1^06142012.0133700 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
641194583-58929-DETAIL-04_18_2022-XARMSPCR-1^06142012.0133708 | CROSSARM | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
14715359-54489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0174101 | POLE | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
700939649-3489-DETAIL-01_26_2023-GO95HV-1^06148003.0174200 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
989006429-35323-DETAIL-01_26_2023-GO95MLD-1^06148003.0204602 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
575026769-85489-DETAIL-01_26_2023-GO95MLD-1^06148003.0204800 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
945833569-36489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0204801 | POLE | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
252476849-53589-DETAIL-01_30_2023-GO95HV-1^06148003.0205000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
357228539-23589-DETAIL-01_30_2023-GO95HV-1^06148003.0205101 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
912278029-39389-ADMIN-04_26_2023-POLEREPL-1^06148001.0253200 | POLE | CA-NON-TIER | Distribution | 2023-04-26 | 2026-04-26 | 2
775308970-80179-DTLSB-06_23_2020-UNIGRDSG-1^06148001.0341600 | OTHER | CA-NON-TIER | Distribution | 2020-06-23 | 2023-06-23 | 2
887886829-81689-DETAIL-01_30_2023-COPLLEAN-1^06148002.0131400 | POLE | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
887886829-81689-DETAIL-01_30_2023-INSULDMG-1^06148002.0131400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
538110869-97589-DETAIL-01_30_2023-GO95MLD-1^06148002.0149400 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
39335353-82430-DETAIL-04_14_2022-GO95HV-1^06142012.0137301 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
80932313-99610-DETAIL-04_14_2022-GUYLOINS-1^06142012.0137400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
143229269-21369-DETAIL-04_21_2022-GO95HV-1^06142012.0139302 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
766256424-11139-DETAIL-11_05_2021-GO95HV-1^06142012.0144200 | OTHER | CA-NON-TIER | Distribution | 2021-11-05 | 2026-11-05 | 3
925702949-35229-DETAIL-11_10_2021-SVCROAD-1^06142012.0146504 | OTHER | CA-NON-TIER | Distribution | 2021-11-10 | 2024-11-10 | 2
421695248-7970-DETAIL-11_03_2021-GO95TCH-1^06142012.0146700 | OTHER | CA-NON-TIER | Distribution | 2021-11-03 | 2024-11-03 | 2
648400743-57829-DETAIL-11_10_2021-SVCROAD-1^06142012.0148701 | OTHER | CA-NON-TIER | Distribution | 2021-11-10 | 2024-11-10 | 2
296060523-16129-DETAIL-03_21_2016-SVCWIND-1^06142012.0149700 | OTHER | CA-NON-TIER | Distribution | 2016-03-21 | 2021-02-21 | 2
296060523-16129-DETAIL-11_08_2021-GO95CLSV-1^06142012.0149700 | OTHER | CA-NON-TIER | Distribution | 2021-11-08 | 2024-11-08 | 2
122654453-19860-DTLSB-03_30_2022-GO95MLD-1^06144006.0193800 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
597634473-72301-DTLSB-03_30_2022-XARMSPCR-1^06144006.0196900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
302505053-2540-DTLSB-03_30_2022-GO95HV-1^06144006.0201900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
451953852-95911-DTLSB-03_30_2022-GO95HV-1^06144006.0203900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
558574643-96751-DTLSB-03_30_2022-GO95HV-1^06144006.0205901 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
558574643-96751-DTLSB-03_30_2022-INSULDMG-1^06144006.0205901 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
928531932-90152-DTLTRT-03_30_2022-GO95HV-1^06144006.0206900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
930684673-8562-DTLSB-03_29_2022-GO95HV-1^06144006.0210600 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
343159703-57979-DTLSB-03_30_2022-GO95MLD-1^06144006.0210900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
289997123-52130-DTLSB-03_29_2022-ABNDEQPM-1^06144006.0212900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
39132663-9230-DTLSB-03_29_2022-GO95HV-1^06144006.0210500 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
93463683-2930-DTLSB-03_29_2022-GO95HV-1^06144006.0210700 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
822565724-47139-DETAIL-11_15_2021-ABNDEQPM-1^06142013.0052200 | OTHER | CA-NON-TIER | Distribution | 2021-11-15 | 2026-11-15 | 3
14135775-38429-DETAIL-11_15_2021-GO95HV-1^06142013.0052201 | OTHER | CA-NON-TIER | Distribution | 2021-11-15 | 2026-11-15 | 3
14135775-38429-DETAIL-11_15_2021-GO95MLD-1^06142013.0052201 | OTHER | CA-NON-TIER | Distribution | 2021-11-15 | 2026-11-15 | 3
339653914-67129-DETAIL-11_15_2021-UNIGRDSG-1^06142013.0062201 | OTHER | CA-NON-TIER | Distribution | 2021-11-15 | 2024-11-15 | 2
317449141-11241-ADMIN-01_06_2022-POLEDERP-1^06142015.0034902 | POLE | CA-TIER-2 | Distribution | 2022-01-06 | 2023-01-06 | 2
279128771-10871-ADMIN-04_19_2022-POLEDERP-1^06142015.0036902 | POLE | CA-TIER-2 | Distribution | 2022-04-19 | 2023-04-19 | 2
522967961-64364-DETAIL-03_23_2023-GO95MLD-1^06142016.0050006 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
627732161-33204-DETAIL-03_23_2023-GO95MLD-1^06142016.0050101 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
426999161-76284-DETAIL-03_27_2023-GO95BLTC-1^06142016.0050201 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
426999161-76284-DETAIL-03_27_2023-GO95MLD-1^06142016.0050201 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
372097073-49920-DTLSB-03_23_2022-GO95HV-1^06146005.0247901 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
874830053-54342-DTLSB-03_23_2022-GO95MLD-1^06146005.0250900 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
74871754-95500-DETAIL-02_28_2022-INSULDMG-1^06146005.0270600 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
196155834-27630-DETAIL-02_28_2022-GO95STUB-1^06146005.0271600 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
991487344-15333-DETAIL-02_28_2022-ABNDEQPM-1^06146005.0273600 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
991487344-15333-DETAIL-02_28_2022-XARMSPCR-1^06146005.0273600 | CROSSARM | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
615284463-65679-DETAIL-03_02_2022-GO95MLD-1^06146005.0278900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
285871371-83620-DETAIL-03_02_2022-GO95HV-1^06146006.0075300 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
799009571-92182-DETAIL-03_02_2022-GO95TCH-1^06146006.0075301 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
413325030-49360-DETAIL-03_08_2022-GO95MLD-1^06146006.0075901 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
658882761-40001-DETAIL-03_02_2022-GO95MLD-1^06146006.0076300 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
786855541-80852-DETAIL-03_08_2022-CUTOUTAR-1^06146006.0076502 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
768439801-77644-DETAIL-03_30_2023-GO95MLD-1^06142016.0055102 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
232845901-57901-DETAIL-03_30_2023-GUYHINS-1^06142016.0055103 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
593370241-23241-DETAIL-03_30_2023-GO95HV-1^06142016.0055201 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
994836983-3083-DETAIL-03_30_2023-GO95HV-1^06142016.0058001 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
350741283-27283-DETAIL-03_30_2023-GO95HV-1^06142016.0059000 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
165520683-44683-DETAIL-03_30_2023-GO95MLD-1^06142016.0059004 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
530109683-22783-DETAIL-03_30_2023-ENCHRW-2^06142016.0059005 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
112627883-42983-DETAIL-03_30_2023-GO95HV-1^06142016.0059100 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
67408203-6303-DETAIL-03_23_2023-GO95MLD-1^06142016.0080707 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
148588861-86094-ADMIN-04_21_2023-GO95TCH-1^06142016.0054004 | OTHER | CA-NON-TIER | Distribution | 2023-04-21 | 2026-04-21 | 2
385808961-10061-DETAIL-03_30_2023-SVCDEFLC-1^06142016.0054006 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
616768261-2361-DETAIL-03_30_2023-GO95TCH-1^06142016.0054010 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
221722118-78060-DTLSB-03_24_2022-XARMSPCR-1^06144006.0253900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-24 | 2025-03-24 | 2
44794088-24940-DTLSB-03_24_2022-GO95HV-1^06144006.0254902 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
122896003-58579-DTLSB-03_31_2022-GO95HV-1^06144006.0298700 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
208155693-42579-DTLSB-03_29_2022-RISEGRD-1^06144006.0298701 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
208155693-42579-ADMIN-06_30_2023-POLEDERP-1^06144006.0298701 | POLE | CA-NON-TIER | Distribution | 2023-06-30 | 2026-06-30 | 2
581022191-66681-DTLSB-03_30_2022-SVCROAD-1^06144007.0312501 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
309408436-58436-DTLTRT-03_31_2022-GO95TCH-1^06144007.0314100 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
891416591-74492-ADMIN-06_15_2022-CUTOUTAR-1^06145001.0139500 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-06-15 | 2025-06-15 | 2
368031352-79310-DETAIL-02_08_2023-GO95HV-1^06145002.0047801 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
515113672-68979-DTLSB-03_23_2022-GO95MLD-1^06145006.0172600 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
515113672-68979-DTLSB-03_23_2022-GO95TCH-1^06145006.0172600 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
406753752-20679-DTLSB-03_31_2022-GO95MLD-1^06145006.0177100 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
851191724-44724-DETAIL-03_28_2023-GO95MLD-1^06142016.0084704 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
682349924-11024-DETAIL-03_29_2023-SVCROAD-1^06142016.0084709 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
742819454-94554-DETAIL-03_28_2023-GO95MLD-1^06142016.0084806 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
233824254-49254-DETAIL-03_28_2023-GO95TCH-1^06142016.0084804 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
233824254-49254-DETAIL-03_28_2023-SVCDEFLC-1^06142016.0084804 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
472653794-60894-DETAIL-03_30_2023-ABNDEQPM-1^06142016.0084909 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
950229814-61914-DETAIL-03_29_2023-GO95MLD-1^06142016.0085002 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
5377114-30214-DETAIL-03_29_2023-GO95HV-1^06142016.0085101 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
5377114-30214-DETAIL-03_29_2023-INSULDMG-1^06142016.0085101 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
76823134-98134-DETAIL-03_29_2023-GO95HV-1^06142016.0085400 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
850950784-12884-DETAIL-02_05_2018-SVCWIND-1^06142016.0084903 | OTHER | CA-NON-TIER | Distribution | 2018-02-05 | 2023-01-05 | 2
822182984-24094-DETAIL-03_29_2023-GO95MLD-1^06142016.0084904 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
982120135-62714-AUDIT-06_14_2022-GO95MLD-1^06242005.0369640 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
731747046-94562-DETAIL-05_23_2022-POLESTEP-1^06242005.0369703 | POLE | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
194361014-29129-DETAIL-06_16_2022-GO95HV-1^06242006.0246600 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2027-06-16 | 3
194361014-29129-DETAIL-06_16_2022-GO95MLD-1^06242006.0246600 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
338783004-48129-DETAIL-06_16_2022-GO95HV-1^06242006.0247600 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2027-06-16 | 3
224507399-85119-DETAIL-07_22_2021-GO95HV-1^06241008.0304500 | OTHER | CA-NON-TIER | Distribution | 2021-07-22 | 2026-07-22 | 3
224507399-85119-DETAIL-07_22_2021-XARMSPCR-1^06241008.0304500 | CROSSARM | CA-NON-TIER | Distribution | 2021-07-22 | 2024-07-22 | 2
695662022-58869-DETAIL-07_26_2021-XARMSPCR-1^06241009.0101640 | CROSSARM | CA-NON-TIER | Distribution | 2021-07-26 | 2024-07-26 | 2
963514182-96869-DETAIL-07_26_2021-GO95HV-1^06241009.0105640 | OTHER | CA-NON-TIER | Distribution | 2021-07-26 | 2026-07-26 | 3
963514182-96869-DETAIL-07_26_2021-XARMSPCR-1^06241009.0105640 | CROSSARM | CA-NON-TIER | Distribution | 2021-07-26 | 2024-07-26 | 2
930762403-53729-DETAIL-03_06_2017-SVCWIND-1^06142012.0130611 | OTHER | CA-NON-TIER | Distribution | 2017-03-06 | 2022-02-06 | 2
96837294-6229-DETAIL-04_11_2022-GO95MLD-1^06142012.0130612 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
415284634-73129-DETAIL-03_16_2017-SVCWIND-1^06142012.0130614 | OTHER | CA-NON-TIER | Distribution | 2017-03-16 | 2022-02-16 | 2
694667934-66829-DETAIL-04_11_2022-SVCENTCO-1^06142012.0130702 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
875815951-69829-DETAIL-04_11_2022-GO95MLD-1^06142012.0130703 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
95452204-6729-DETAIL-04_11_2022-GO95HV-1^06142012.0130707 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
95452204-6729-DETAIL-04_11_2022-GO95MLD-1^06142012.0130707 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
57768820-11929-DETAIL-04_11_2022-CLMBHAZ-1^06142012.0130708 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
498993564-92029-DETAIL-04_11_2022-GO95MLD-1^06142012.0130710 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
132922781-24429-DETAIL-04_11_2022-GO95BLTC-1^06142012.0130800 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
822261591-66929-DETAIL-04_11_2022-GUYSLACK-1^06142012.0130812 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
791188675-81229-DETAIL-04_11_2022-GO95TCH-1^06142012.0130840 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
588250781-2029-DETAIL-04_11_2022-GO95MLD-1^06142012.0130906 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
362291083-53029-DETAIL-04_11_2022-POLETOP-1^06142012.0130907 | POLE | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
223091464-5329-DETAIL-04_11_2022-GO95HV-1^06142012.0130910 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
445444204-36301-DETAIL-04_12_2022-ABNDEQPM-1^06142012.0131304 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
906740354-11252-DETAIL-04_12_2022-GO95MLD-1^06142012.0131402 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
993661863-85743-DETAIL-04_12_2022-GO95HV-1^06142012.0131511 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
392787165-73329-DETAIL-04_13_2022-ABNDEQPM-1^06142012.0131608 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
392787165-73329-DETAIL-04_13_2022-SVCWIND-1^06142012.0131608 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
682997657-13229-DETAIL-04_13_2022-GO95SVC-1^06142012.0131609 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
862390155-2729-DETAIL-04_19_2022-GO95MLD-1^06142012.0131809 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
118618281-90829-DETAIL-04_19_2022-POLETOP-1^06142012.0131814 | POLE | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
916097805-95129-DETAIL-04_19_2022-GO95MLD-1^06142012.0131901 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
10422360-53129-DETAIL-04_19_2022-GO95HV-1^06142012.0131907 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
10422360-53129-DETAIL-04_19_2022-SVCROAD-1^06142012.0131907 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
720023955-93029-DETAIL-04_11_2022-GO95MLD-1^06142012.0131912 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
219380424-87229-DETAIL-04_19_2022-GO95HV-1^06142012.0131913 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
774242550-46929-DETAIL-04_19_2022-GO95MLD-1^06142012.0131915 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
659304984-49029-DETAIL-04_19_2022-GO95MLD-1^06142012.0131916 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
165030444-29-DETAIL-04_13_2022-SVCROAD-1^06142012.0132404 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
258599403-12390-DETAIL-04_12_2022-XARMSPCR-1^06142012.0132503 | CROSSARM | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
664472790-24221-DETAIL-04_18_2022-GO95MLD-1^06142012.0133710 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
24410653-6170-DETAIL-04_18_2022-SVCRUBLG-1^06142012.0133712 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
24410653-6170-DETAIL-04_18_2022-SVCWIND-1^06142012.0133712 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
255489321-31690-DETAIL-04_18_2022-GO95MLD-1^06142012.0133807 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
255489321-31690-DETAIL-04_18_2022-GO95STUB-1^06142012.0133807 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
889841041-2292-DETAIL-04_18_2022-GO95HV-1^06142012.0133808 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2027-04-18 | 3
889841041-2292-DETAIL-04_18_2022-GO95MLD-1^06142012.0133808 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
686097683-68171-DETAIL-04_19_2022-CLMBHAZ-1^06142012.0133900 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
660209151-41129-DETAIL-04_18_2022-GO95HV-1^06142012.0133902 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2027-04-18 | 3
189664604-65430-DETAIL-04_19_2022-GO95MLD-1^06142012.0133903 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
189664604-65430-DETAIL-04_19_2022-GO95TCH-1^06142012.0133903 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
302363693-37440-DETAIL-04_21_2022-GO95HV-1^06142012.0134000 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
554934461-36461-DETAIL-03_23_2023-GO95MLD-1^06142016.0051001 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
712238591-42691-DETAIL-03_23_2023-GO95MLD-1^06142016.0051002 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
150876693-5190-DETAIL-04_21_2022-GO95HV-1^06142012.0247700 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
963703373-80753-DETAIL-04_14_2022-GO95HV-1^06142012.0247901 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
609441028-41721-DETAIL-11_11_2021-GO95MLD-1^06142013.0174601 | OTHER | CA-NON-TIER | Distribution | 2021-11-11 | 2024-11-11 | 2
716148626-69961-DETAIL-11_15_2021-UNIGRDSG-1^06142013.0180402 | OTHER | CA-NON-TIER | Distribution | 2021-11-15 | 2024-11-15 | 2
317449141-11241-DTLSB-04_16_2014-GUYNOINS-1^06142015.0034902 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2014-04-16 | 2019-03-16 | 2
858455931-76931-DETAIL-03_23_2023-GO95MLD-1^06142016.0050002 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
372744261-16261-DETAIL-03_27_2023-ABNDEQPM-1^06142016.0050600 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
562003791-76791-DETAIL-03_23_2023-GO95MLD-1^06142016.0051004 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
245861860-68514-ADMIN-02_06_2018-COPLLEAN-1^06142016.0051005 | POLE | CA-NON-TIER | Distribution | 2018-02-06 | 2023-01-06 | 2
393002381-29914-DETAIL-02_05_2018-SVCWIND-1^06142016.0054104 | OTHER | CA-NON-TIER | Distribution | 2018-02-05 | 2023-01-05 | 2
962168828-59828-DETAIL-03_30_2023-GO95BLTC-1^06142016.0055001 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
962168828-59828-DETAIL-03_30_2023-GO95MLD-1^06142016.0055001 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
787605301-47401-DETAIL-03_30_2023-GO95MLD-1^06142016.0055002 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
768439801-77644-DETAIL-03_30_2023-COPLLEAN-1^06142016.0055102 | POLE | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
660983302-18302-DETAIL-03_30_2023-GO95HV-1^06142016.0056001 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
530109683-22783-DETAIL-03_30_2023-ENCHRW-1^06142016.0059005 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
298439623-12723-DETAIL-03_23_2023-GO95MLD-1^06142016.0081700 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
298439623-12723-DETAIL-03_23_2023-GRDRODHI-1^06142016.0081700 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
76390823-72823-DETAIL-03_23_2023-GO95MLD-1^06142016.0081703 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
819388553-15443-DETAIL-03_23_2023-GO95MLD-1^06142016.0081803 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
587856314-33414-DETAIL-03_27_2023-SVCROAD-1^06142016.0082805 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
822182984-24094-DETAIL-03_29_2023-SVCROAD-1^06142016.0084904 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
46356594-49849-DETAIL-03_30_2023-GO95MLD-1^06142016.0084908 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
46356594-49849-DETAIL-03_30_2023-GO95TCH-1^06142016.0084908 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
302532614-86614-DETAIL-03_29_2023-GO95HV-1^06142016.0085000 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
115041114-83114-DETAIL-03_29_2023-GO95HV-1^06142016.0085100 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
76823134-98134-DETAIL-03_29_2023-GO95MLD-1^06142016.0085400 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
76823134-98134-AUDIT-04_12_2023-SVCDEFLC-1^06142016.0085400 | OTHER | CA-NON-TIER | Distribution | 2023-04-12 | 2026-04-12 | 2
41845934-1044-DETAIL-03_29_2023-GO95MLD-1^06142016.0085501 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
724521634-24634-DETAIL-03_29_2023-CLRTOUCH-1^06142016.0085601 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
910548734-58153-ADMIN-04_21_2023-GO95TCH-1^06142016.0085701 | OTHER | CA-NON-TIER | Distribution | 2023-04-21 | 2026-04-21 | 2
553854954-65094-DETAIL-03_30_2023-GUYNOINS-1^06142016.0085805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
955145984-17984-DETAIL-04_09_2019-SVCROAD-1^06142016.0175802 | OTHER | CA-NON-TIER | Distribution | 2019-04-09 | 2024-03-09 | 2
652454230-66629-DETAIL-04_26_2022-GO95HV-1^06143012.0240000 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
466845800-16629-DETAIL-04_26_2022-GO95HV-1^06143012.0240100 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
229137100-85629-DETAIL-04_26_2022-GO95HV-1^06143012.0240101 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
229137100-85629-DETAIL-04_26_2022-GO95MLD-1^06143012.0240101 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
614637549-59529-DETAIL-04_26_2022-GO95MLD-1^06143012.0240300 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
279215650-44629-DETAIL-04_26_2022-GO95MLD-1^06143012.0240301 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
63333669-59429-DETAIL-04_27_2022-GO95MLD-1^06143012.0240400 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
896358589-50629-DETAIL-04_27_2022-GO95HV-1^06143012.0240500 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
762398708-81629-DETAIL-05_02_2022-GO95MLD-1^06143012.0244202 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
977081728-32629-DETAIL-04_27_2022-GO95MLD-1^06143012.0244300 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
798544348-92629-DETAIL-04_27_2022-POLETOP-1^06143012.0244303 | POLE | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
177369944-27529-DETAIL-04_27_2022-GO95MLD-1^06143012.0251901 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
287305174-48529-DETAIL-04_25_2022-GO95HV-1^06143012.0253201 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
287305174-48529-DETAIL-04_25_2022-GO95MLD-1^06143012.0253201 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
873484664-12529-DETAIL-04_25_2022-GO95MLD-1^06143012.0253301 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
998419154-86129-DETAIL-04_25_2022-GO95MLD-1^06143012.0253401 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
142211583-88729-DETAIL-04_25_2022-GO95MLD-1^06143012.0253502 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
679519073-82329-DETAIL-04_25_2022-GO95HV-1^06143012.0253601 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
767270705-33329-DETAIL-04_25_2022-GO95HV-1^06143012.0253640 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
553238373-44329-DETAIL-04_25_2022-CLMBHAZ-1^06143012.0253700 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
553238373-44329-DETAIL-04_25_2022-SVCROAD-1^06143012.0253700 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
6480891-89329-DETAIL-05_02_2022-GO95CL10-1^06143012.0246800 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
526802079-88629-DETAIL-05_02_2022-GO95MLD-1^06143012.0246802 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
156565904-16129-DETAIL-04_25_2022-GRDRODHI-1^06143012.0259100 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
927703333-79229-DETAIL-04_19_2022-GO95TCH-2^06143012.0360004 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
407613294-39429-DETAIL-04_19_2022-GO95MLD-1^06143012.0360100 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
809222994-61629-DETAIL-04_19_2022-GO95HV-1^06143012.0361100 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
115174817-16829-DETAIL-04_20_2022-GO95HV-1^06143012.0361300 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
484633453-44729-DETAIL-04_20_2022-GO95MLD-1^06143012.0362500 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
697094043-24729-DETAIL-04_21_2022-GO95BLTC-1^06143012.0363500 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
847599074-46429-DETAIL-04_21_2022-SVCWIND-1^06143012.0363700 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
961449764-36029-DETAIL-04_25_2022-GO95MLD-1^06143012.0363900 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
277175074-72529-DETAIL-04_21_2022-GO95HV-1^06143012.0363901 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
854381883-75629-DETAIL-04_20_2022-GO95MLD-1^06143012.0364000 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
854381883-75629-DETAIL-04_20_2022-GO95TCH-1^06143012.0364000 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
116291444-72629-DETAIL-04_20_2022-SVCROAD-1^06143012.0369002 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
151933785-47629-AUDIT-05_12_2022-GO95MLD-1^06143012.0364240 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
56305443-82929-DETAIL-04_20_2022-GO95MLD-1^06143012.0364502 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
56305443-82929-DETAIL-04_20_2022-SVCROAD-1^06143012.0364502 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
370260344-86729-DETAIL-04_21_2022-GO95MLD-1^06143012.0364600 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
370260344-86729-DETAIL-04_21_2022-GRDRODHI-1^06143012.0364600 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
221769753-67529-DETAIL-04_20_2022-GO95HV-1^06143012.0365300 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
42721353-40729-DETAIL-04_20_2022-GO95HV-1^06143012.0365301 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
656256931-89931-DETAIL-04_20_2022-GO95MLD-1^06143012.0365302 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
440361903-38729-DETAIL-04_21_2022-GUYHINS-1^06143012.0365702 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
440361903-38729-DETAIL-04_21_2022-INSULDMG-1^06143012.0365702 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
707063223-1829-DETAIL-04_25_2022-GRDRODHI-1^06143012.0365900 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
132028934-36229-DETAIL-04_20_2022-GO95MLD-1^06143012.0366003 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
815438613-27742-DETAIL-04_04_2023-ABNDEQPM-1^06143014.0217900 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
530356083-93811-DETAIL-04_04_2023-SVCENTCO-1^06143014.0219702 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2026-04-04 | 2
961891363-10239-DETAIL-04_03_2023-GO95MLD-1^06143013.0333600 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
40770663-75829-AUDIT-04_12_2023-GO95MLD-1^06143013.0336600 | OTHER | CA-NON-TIER | Distribution | 2023-04-12 | 2026-04-12 | 2
669370446-26331-DETAIL-04_05_2023-SVCDEFLC-1^06143014.0132002 | OTHER | CA-TIER-2 | Distribution | 2023-04-05 | 2026-04-05 | 2
240426316-31280-DETAIL-04_03_2023-GO95HV-1^06143014.0146102 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
938933383-61992-DETAIL-04_03_2023-GO95HV-1^06143014.0181301 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
815438613-27742-DETAIL-04_04_2023-GO95MLD-1^06143014.0217900 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2026-04-04 | 2
746216573-25841-DETAIL-04_04_2023-GO95HV-1^06143014.0224701 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
937417383-22492-DETAIL-04_04_2023-GO95HV-1^06143014.0225800 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
737170953-78621-DETAIL-04_06_2023-GO95MLD-1^06143014.0230500 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
313224153-18160-DETAIL-04_06_2023-GO95HV-1^06143014.0232500 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
455822456-75989-DTLSB-03_29_2022-GUYSLACK-1^06144006.0162000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
395286966-57140-DTLSB-03_31_2022-GO95HV-1^06144006.0162001 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
395286966-57140-DTLSB-03_31_2022-GO95MLD-1^06144006.0162001 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
296142986-3830-DTLSB-03_28_2022-GO95TCH-1^06144006.0163001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
296142986-3830-DTLSB-03_28_2022-GO95MLD-1^06144006.0163001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
729341976-49901-DTLSB-03_28_2022-GO95MLD-1^06144006.0163003 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
496288836-5071-DTLSB-03_28_2022-GO95MLD-1^06144006.0163004 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
10803036-56569-DTLSB-03_28_2022-GO95MLD-1^06144006.0163005 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
62596286-74680-DTLSB-03_28_2022-GO95MLD-1^06144006.0164004 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
358746636-15300-DTLSB-03_28_2022-GO95HV-1^06144006.0164005 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
147472346-93190-DTLSB-03_28_2022-GO95MLD-1^06144006.0164100 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
654669896-64191-DTLSB-03_29_2022-GO95MLD-1^06144006.0165002 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
296142986-3830-DTLSB-03_28_2022-GRDRODHI-1^06144006.0163001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
343159703-57979-DTLSB-03_30_2022-GO95HV-1^06144006.0210900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
289192173-24630-DTLSB-03_29_2022-XARMSPCR-1^06144006.0211900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
289997123-52130-DTLSB-03_29_2022-GO95HV-1^06144006.0212900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
156854463-60390-DTLSB-03_29_2022-GUYLOINS-1^06144006.0213900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
220709613-34360-DTLSB-03_28_2022-POLETOP-1^06144006.0225701 | POLE | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
63338978-50180-DTLSB-03_24_2022-GO95HV-1^06144006.0254900 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
122896003-58579-DTLSB-03_31_2022-GO95MLD-1^06144006.0298700 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
208155693-42579-DTLSB-03_29_2022-GO95HV-1^06144006.0298701 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
208155693-42579-DTLSB-03_29_2022-GO95MLD-1^06144006.0298701 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
24623481-19470-DTLSB-03_31_2022-GO95MLD-1^06144007.0312401 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
717223581-59379-ADMIN-10_27_2022-POLEREPL-1^06144007.0313500 | POLE | CA-NON-TIER | Distribution | 2022-10-27 | 2025-10-27 | 2
466275492-91279-DTLSB-03_31_2022-GO95MLD-1^06145006.0207600 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
645991833-64679-DTLSB-03_31_2022-GO95HV-1^06145006.0223501 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
528873533-96979-DTLSB-03_31_2022-GO95TCH-1^06145006.0223502 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
701805633-6979-DTLSB-03_31_2022-GO95MLD-1^06145006.0224500 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
31311803-39779-AUDIT-04_12_2022-GUYHINS-1^06145006.0280800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
726993233-43691-DTLSB-03_31_2022-GO95HV-1^06145006.0287601 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
391446341-35840-DETAIL-01_31_2023-GO95MLD-1^06146002.0035900 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
99062791-40240-DETAIL-02_01_2023-GO95HV-1^06146002.0072900 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
463720221-51431-DETAIL-02_01_2023-GO95HV-1^06146002.0074500 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
287190261-98779-DETAIL-02_01_2023-GO95MLD-1^06146002.0081100 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
350912681-71979-DETAIL-01_31_2023-ABNDEQPM-1^06146002.0097100 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
526515324-61311-DETAIL-02_09_2023-GO95HV-1^06146004.0161901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
344626024-72090-DETAIL-02_09_2023-GO95MLD-1^06146004.0162900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
599653034-25911-DETAIL-02_09_2023-GO95MLD-1^06146004.0163901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
187644544-17330-DETAIL-02_09_2023-GO95MLD-1^06146004.0165901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
443333569-29201-DETAIL-02_16_2022-GO95HV-1^06146005.0010101 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
26283239-47870-DETAIL-02_10_2022-GO95HV-1^06146005.0010801 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
811729677-38832-DETAIL-02_10_2022-GO95MLD-1^06146005.0010901 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
629125809-91841-DETAIL-02_16_2022-GO95HV-1^06146005.0015100 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
182667539-65920-DETAIL-02_09_2022-GO95HV-1^06146005.0015702 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
4744857-21309-DETAIL-02_09_2022-GO95MLD-1^06146005.0016900 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
115907697-42960-DETAIL-02_17_2022-GO95HV-1^06146005.0017402 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
403089087-50379-DETAIL-02_17_2022-GO95HV-1^06146005.0017600 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
178887268-19109-DETAIL-02_22_2022-GO95HV-1^06146005.0096300 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2027-02-22 | 3
199943149-70640-DETAIL-02_10_2022-GUYHINS-1^06146005.0010701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
72086584-97584-DETAIL-02_10_2022-GO95MLD-1^06146005.0010702 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
134633129-7570-DETAIL-02_10_2022-GO95TCH-1^06146005.0010900 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
781818719-35142-DETAIL-02_10_2022-GO95HV-1^06146005.0010903 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
256437810-81190-DETAIL-02_10_2022-GO95HV-1^06146005.0012901 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
760368861-25881-DETAIL-02_16_2022-SVCROAD-1^06146005.0013000 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
331824579-71270-DETAIL-02_10_2022-GO95MLD-1^06146005.0014901 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
809252499-88822-DETAIL-02_16_2022-GO95HV-1^06146005.0015101 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
918134509-23679-DETAIL-02_16_2022-GO95MLD-1^06146005.0015201 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
935203949-17382-DETAIL-02_09_2022-GO95TCH-1^06146005.0015701 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
182667539-65920-DETAIL-02_09_2022-GO95MLD-1^06146005.0015702 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
944619269-75379-DETAIL-02_14_2022-GUYHINS-1^06146005.0030500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
447621168-2709-DETAIL-02_14_2022-GO95HV-1^06146005.0031300 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
98640858-61709-DETAIL-02_14_2022-GO95HV-1^06146005.0031402 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
273629088-81479-DETAIL-02_14_2022-GO95TCH-1^06146005.0032200 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
672473253-3879-DETAIL-02_14_2022-GO95MLD-1^06146005.0033500 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
672473253-3879-DETAIL-02_14_2022-SVCRUBLG-1^06146005.0033500 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
719426244-21809-DETAIL-02_14_2022-GO95HV-1^06146005.0035100 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
18209749-33279-DETAIL-02_14_2022-ABNDEQPM-1^06146005.0035500 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
78657887-40987-DETAIL-02_14_2022-GO95MLD-1^06146005.0035602 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
368928896-39896-DETAIL-02_14_2022-GO95HV-1^06146005.0036603 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
320544896-25896-DETAIL-02_14_2022-GO95MLD-1^06146005.0036604 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
318774796-57796-DETAIL-02_14_2022-GO95TCH-1^06146005.0036703 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
440720550-43390-DTLSB-03_21_2022-GO95HV-1^06146005.0146200 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
637177119-9119-DETAIL-03_03_2022-GO95MLD-1^06146005.0117900 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
215108619-22550-DETAIL-03_03_2022-GO95HV-1^06146005.0120101 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
915214929-98192-DETAIL-03_03_2022-CLRTOUCH-1^06146005.0120301 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
434960479-43190-DETAIL-03_03_2022-GO95MLD-1^06146005.0120702 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
522339669-38101-DETAIL-03_08_2022-SVCENTCO-1^06146005.0125700 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
68747208-7379-DETAIL-03_03_2022-GO95HV-1^06146005.0126900 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
270552070-38210-DETAIL-03_03_2022-GO95MLD-1^06146005.0127003 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
526248649-8011-DETAIL-03_03_2022-SVCROAD-1^06146005.0127402 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
440720550-43390-DTLSB-03_21_2022-GO95MLD-1^06146005.0146200 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
865187726-56389-DTLSB-03_21_2022-GO95MLD-1^06146005.0146301 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
959170934-9643-DTLSB-03_22_2022-GO95MLD-1^06146005.0148901 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
239433633-13870-DETAIL-04_14_2022-COPLLEAN-1^06146005.0150100 | POLE | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
489396883-65319-DTLSB-03_21_2022-GO95MLD-1^06146005.0140800 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
337645475-83319-DTLSB-03_21_2022-INSULDMG-1^06146005.0141901 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
835735696-37696-DTLSB-03_21_2022-ABNDEQPM-1^06146005.0142802 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
134745373-28779-DTLSB-03_31_2022-CLRTOUCH-1^06146005.0143703 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
779429655-79932-DTLSB-03_21_2022-GO95MLD-1^06146005.0144600 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
779429655-79932-DTLSB-03_21_2022-GO95TCH-1^06146005.0144600 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
900974516-83332-DTLSB-03_21_2022-GO95HV-1^06146005.0145300 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
222090306-48260-DTLSB-03_21_2022-GO95HV-1^06146005.0145400 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
159003975-17000-DTLSB-03_21_2022-GO95MLD-1^06146005.0145600 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
274353211-58710-DTLSB-03_21_2022-GO95HV-1^06146005.0146000 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
103351001-5540-DTLSB-03_21_2022-GO95HV-1^06146005.0146002 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2027-03-21 | 3
652480033-15979-DETAIL-02_24_2022-GO95MLD-1^06146005.0214600 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
700908136-72099-DTLSB-03_17_2022-CLRTOUCH-1^06146005.0227800 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
700908136-72099-DTLSB-03_17_2022-GO95MLD-1^06146005.0227800 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
296164443-63830-DTLSB-03_22_2022-GO95MLD-1^06146005.0235400 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
296164443-63830-DTLSB-03_22_2022-GO95TCH-1^06146005.0235400 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
460495135-29979-DTLSB-03_22_2022-GO95HV-1^06146005.0235401 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
164544133-43279-AUDIT-03_02_2017-SVCROAD-1^06146005.0214501 | OTHER | CA-NON-TIER | Distribution | 2017-03-02 | 2022-02-02 | 2
164544133-43279-DETAIL-02_24_2022-GO95MLD-1^06146005.0214501 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
639166423-95051-DETAIL-02_24_2022-GRDRODHI-1^06146005.0214700 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
951864870-69870-DETAIL-02_24_2022-GO95MLD-1^06146005.0214711 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
686754873-22581-DETAIL-02_24_2022-ABNDEQPM-1^06146005.0214900 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
578727703-19999-DETAIL-02_22_2022-GO95HV-1^06146005.0217401 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2027-02-22 | 3
165330313-81510-DETAIL-02_24_2022-ABNDEQPM-1^06146005.0217700 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
116128464-35060-DTLSB-03_16_2022-ABNDEQPM-1^06146005.0222401 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2027-03-16 | 3
116128464-35060-DTLSB-03_16_2022-GO95MLD-1^06146005.0222401 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
346611003-62390-DTLSB-03_17_2022-CONDFRAY-1^06146005.0222900 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
883149524-81472-DTLSB-03_17_2022-GO95BLTC-1^06146005.0222901 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
768650803-29902-DTLSB-03_17_2022-XARMSPCR-1^06146005.0224900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
906886223-62352-DTLSB-03_22_2022-GO95MLD-1^06146005.0234101 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
906886223-62352-DTLSB-03_22_2022-GUYHINS-1^06146005.0234101 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
205055633-65240-DTLSB-03_22_2022-GO95BLTC-1^06146005.0234300 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
434072335-1679-DTLSB-03_22_2022-GO95HV-1^06146005.0234301 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
582189513-25081-DTLSB-03_22_2022-GO95HV-1^06146005.0235302 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
117090753-6560-DTLSB-03_17_2022-GO95TCH-1^06146005.0236400 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
69949653-73390-DTLSB-03_17_2022-GO95HV-1^06146005.0239900 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
874520310-39642-DETAIL-03_07_2022-GO95MLD-1^06146006.0076900 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
221729940-55009-DETAIL-03_07_2022-GO95HV-1^06146006.0076904 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
107674680-15340-DETAIL-03_07_2022-ENCHRW-1^06146006.0076905 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
69187890-58190-DETAIL-03_07_2022-CLRTOUCH-1^06146006.0077900 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
515943460-61391-DETAIL-03_07_2022-GO95HV-1^06146006.0078500 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
515943460-61391-DETAIL-03_07_2022-INSULDMG-1^06146006.0078500 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
15379180-17989-DETAIL-03_07_2022-GO95MLD-1^06146006.0079500 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
15379180-17989-DETAIL-03_07_2022-INSULDMG-2^06146006.0079500 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
723138801-85201-DETAIL-03_01_2022-SVCROAD-1^06146006.0083800 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
508828931-20361-DETAIL-03_07_2022-GO95MLD-1^06146006.0084700 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
508828931-20361-DETAIL-03_07_2022-GUYHINS-1^06146006.0084700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
429941154-66280-DETAIL-02_23_2022-GO95HV-1^06146005.0284302 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
610196810-80321-DETAIL-03_02_2022-GO95HV-1^06146006.0075504 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
78577290-42010-DETAIL-03_07_2022-GO95HV-1^06146006.0075600 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
326641600-41370-DETAIL-03_07_2022-GO95HV-1^06146006.0075601 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
182423270-91820-DETAIL-03_07_2022-GO95HV-1^06146006.0075700 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
413325030-49360-DETAIL-03_08_2022-GO95HV-1^06146006.0075901 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
818483753-69452-DETAIL-09_10_2020-SVCROAD-1^06147001.0188600 | OTHER | CA-NON-TIER | Distribution | 2020-09-10 | 2023-09-10 | 2
526594585-10411-DETAIL-02_07_2023-GO95HV-1^06147002.0047400 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
276684455-19010-DETAIL-02_07_2023-GO95HV-1^06147002.0047900 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
174234146-67210-DETAIL-02_06_2023-GO95TCH-1^06147002.0070000 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
45349666-55340-DETAIL-02_06_2023-GO95MLD-1^06147002.0070001 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
415386575-44960-DETAIL-02_07_2023-GO95HV-1^06147002.0095100 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
493223865-85661-DETAIL-02_07_2023-GO95HV-1^06147002.0096300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
153520698-39690-DETAIL-03_08_2022-XARMSPCR-1^06146006.0214501 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
833444519-46202-DETAIL-03_09_2022-GO95HV-1^06146006.0283701 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
186409839-74820-DETAIL-03_09_2022-INSULDMG-1^06146006.0283801 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
950873389-1033-DETAIL-03_09_2022-GUYSLACK-1^06146006.0299700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
648128480-20171-DETAIL-03_19_2015-SVCWIND-2^06147001.0060800 | OTHER | CA-NON-TIER | Distribution | 2015-03-19 | 2020-02-19 | 2
554308039-74299-DETAIL-02_06_2019-SVCROAD-1^06147004.0014902 | OTHER | CA-NON-TIER | Distribution | 2019-02-06 | 2024-01-06 | 2
39852152-78099-DETAIL-01_29_2019-GO95MLD-1^06147004.0350401 | OTHER | CA-NON-TIER | Distribution | 2019-01-29 | 2023-12-29 | 2
870775965-65699-DETAIL-10_14_2021-RISEBKSP-1^06147005.0010900 | OTHER | CA-NON-TIER | Distribution | 2021-10-14 | 2024-10-14 | 2
923035571-49281-DETAIL-10_07_2021-SVCWIND-1^06147005.0043900 | OTHER | CA-NON-TIER | Distribution | 2021-10-07 | 2024-10-07 | 2
709793930-92551-DETAIL-01_26_2023-ABNDEQPM-1^06147003.0141100 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
540219059-85879-DETAIL-01_31_2022-GO95MLD-1^06147005.0262709 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
355455379-56379-DETAIL-01_31_2022-GO95MLD-1^06147005.0262804 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2027-01-31 | 3
253365159-84279-DETAIL-01_31_2022-GO95HV-1^06147005.0262900 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2027-01-31 | 3
901732468-21379-DETAIL-02_02_2022-CLRTOUCH-1^06147005.0263202 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
9238709-66809-DETAIL-02_02_2022-SVCENTCO-1^06147005.0263203 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
216159859-84379-DETAIL-02_02_2022-GO95MLD-1^06147005.0263301 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
516673409-74379-DETAIL-02_01_2022-GO95MLD-1^06147005.0263701 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
397422689-70279-DETAIL-02_01_2022-GO95HV-1^06147005.0263800 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2027-02-01 | 3
334641180-28780-DETAIL-01_26_2023-CONDFRAY-1^06147003.0142100 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
724350120-73191-DETAIL-01_26_2023-GUYSLACK-1^06147003.0142401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
934189650-71172-DETAIL-01_26_2023-ABNDEQPM-1^06147003.0143500 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
634848769-39209-DETAIL-01_31_2022-GO95MLD-1^06147005.0262800 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
355455379-56379-DETAIL-01_31_2022-GO95HV-1^06147005.0262804 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2027-01-31 | 3
253365159-84279-DETAIL-01_31_2022-GO95MLD-1^06147005.0262900 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
901732468-21379-DETAIL-02_02_2022-GO95MLD-1^06147005.0263202 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
824854698-49879-AUDIT-03_10_2022-GO95MLD-1^06147005.0267301 | OTHER | CA-NON-TIER | Distribution | 2022-03-10 | 2025-03-10 | 2
74057758-93679-DETAIL-02_02_2022-GO95HV-1^06147005.0267305 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
74057758-93679-DETAIL-02_02_2022-GO95MLD-1^06147005.0267305 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
211799678-19479-DETAIL-02_02_2022-CLRTOUCH-1^06147005.0268100 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
253829058-96289-DETAIL-02_02_2022-GO95HV-1^06147005.0268205 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
253829058-96289-DETAIL-02_02_2022-GO95MLD-1^06147005.0268205 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
536929718-79409-DETAIL-02_02_2022-XARMSPCR-1^06147005.0268301 | CROSSARM | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
218232709-13509-DETAIL-02_02_2022-GO95HV-1^06147005.0269201 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
615894160-92409-DETAIL-02_01_2022-SVCROOF-1^06147005.0266500 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
694978798-96309-DETAIL-02_09_2022-GO95MLD-1^06147005.0266800 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
463197448-7779-DETAIL-02_02_2022-GO95MLD-1^06147005.0267204 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
890565198-42579-DETAIL-02_01_2022-SVCENTCO-1^06147005.0267302 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
103303629-27409-DETAIL-02_01_2022-SVCWIND-1^06147005.0267304 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
536290808-76379-DETAIL-02_02_2022-ABNDEQPM-1^06147005.0268101 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
536290808-76379-DETAIL-02_02_2022-GO95MLD-1^06147005.0268101 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
411384238-1509-DETAIL-02_02_2022-SVCWIND-1^06147005.0268202 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
85167138-66289-DETAIL-02_02_2022-SVCENTCO-1^06147005.0268207 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
575395893-32979-DETAIL-02_03_2022-GO95MLD-1^06147005.0270301 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2027-02-03 | 3
771167343-83209-DETAIL-02_03_2022-INSULDMG-1^06147005.0270600 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
802734433-16209-DETAIL-02_03_2022-GO95MLD-1^06147005.0270800 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
853533258-85562-DETAIL-02_16_2022-GO95MLD-1^06147005.0367200 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
46633140-48040-DETAIL-02_16_2022-GO95HV-1^06147005.0368900 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
69196690-9190-DETAIL-02_16_2022-GO95HV-1^06147005.0369500 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
354569878-46409-DETAIL-03_09_2022-GO95MLD-1^06147006.0182100 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
423912404-16089-DETAIL-03_16_2022-GO95HV-1^06147006.0190500 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2027-03-16 | 3
361461068-99289-DETAIL-03_09_2022-GO95MLD-1^06147006.0192900 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
692284568-27409-DETAIL-03_09_2022-GO95MLD-1^06147006.0192901 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
802649158-90079-DETAIL-03_09_2022-GO95HV-1^06147006.0192902 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
564786249-89779-DETAIL-02_28_2022-GO95MLD-1^06147006.0300000 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
690627041-46079-DETAIL-02_28_2022-GO95HV-1^06147006.0300001 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
48005260-27940-DETAIL-03_02_2022-POLETOP-1^06147006.0307800 | POLE | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
596803994-5109-DETAIL-02_15_2022-GO95TCH-1^06147005.0337903 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
796719671-16282-DETAIL-03_07_2022-GO95MLD-1^06147006.0316200 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
162202421-90900-DETAIL-03_01_2022-GO95HV-1^06147006.0318101 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
58308001-66270-DETAIL-03_01_2022-GO95HV-1^06147006.0319200 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
141757831-32289-DETAIL-03_01_2022-GO95HV-1^06147006.0319202 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
991003321-91289-DETAIL-03_02_2022-GO95MLD-1^06147006.0319600 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
777595850-99222-AUDIT-04_04_2022-GO95HV-1^06147006.0319900 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
670584260-14431-DETAIL-03_02_2022-GO95HV-1^06147006.0320800 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
429957449-47589-DETAIL-01_30_2023-GO95HV-1^06148002.0149402 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
577721398-17881-DETAIL-02_02_2023-GO95HV-1^06148002.0287100 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
600505803-68511-DETAIL-02_02_2023-GO95HV-1^06148002.0337200 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
488387883-23161-DETAIL-02_02_2023-GO95HV-1^06148002.0337402 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
443594023-88501-DETAIL-02_02_2023-INSULDMG-1^06148002.0337601 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
508834588-32781-DETAIL-02_06_2023-GO95MLD-1^06148002.0285301 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
750456103-98261-DETAIL-02_06_2023-GUYSLACK-1^06148002.0286100 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
525615703-36611-DETAIL-02_06_2023-INSULDMG-1^06148002.0286101 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
134686099-69489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0208400 | POLE | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
662574410-60889-DETAIL-01_30_2023-GO95MLD-1^06148003.0223500 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
75922980-65599-DETAIL-01_30_2023-GO95TCH-1^06148003.0223501 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
142026310-99789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223600 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
565868210-30889-DETAIL-01_30_2023-GO95MLD-1^06148003.0223601 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
948105200-58789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223800 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
379793100-28789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223901 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
583123811-29089-DETAIL-01_24_2023-CONDFRAY-1^06148003.0240100 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
642791511-98089-DETAIL-01_24_2023-GRDRODHI-1^06148003.0240200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
867283120-92789-DETAIL-01_09_2023-GO95MLD-1^06148003.0158301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
688239680-91789-DETAIL-01_09_2023-GO95MLD-1^06148003.0159300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
575026769-85489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0204800 | POLE | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
131203977-46977-DETAIL-01_26_2023-GO95MLD-1^06148003.0204901 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
333726789-87899-DETAIL-01_26_2023-GO95TCH-1^06148003.0206401 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
457278699-589-DETAIL-01_26_2023-GO95MLD-1^06148003.0209400 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
237817143-92779-AUDIT-02_17_2023-GUYHINS-1^06148004.0157301 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-17 | 2026-02-17 | 2
800000764-23579-DETAIL-01_16_2023-GO95MLD-1^06148004.0160300 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
52188434-41479-DETAIL-01_16_2023-GO95MLD-2^06148004.0160302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
872098266-80366-DETAIL-01_16_2023-GO95BLTC-1^06148004.0160303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
872098266-80366-DETAIL-01_16_2023-GO95MLD-1^06148004.0160303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
205514366-16366-DETAIL-01_16_2023-GO95HV-1^06148004.0160304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
865219459-92412-DETAIL-01_25_2023-GO95HV-1^06148003.0355400 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
649401669-25281-DETAIL-01_25_2023-GO95HV-1^06148003.0355500 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
364450605-19809-DETAIL-01_16_2023-GO95HV-1^06148004.0167301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
364450605-19809-DETAIL-01_16_2023-GO95MLD-1^06148004.0167301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
364450605-19809-DETAIL-01_16_2023-GO95TCH-1^06148004.0167301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
364450605-19809-DETAIL-01_16_2023-GRDRODHI-1^06148004.0167301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
811910845-89379-DETAIL-01_10_2023-GO95BLTC-1^06148004.0170300 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2028-01-10 | 3
612493551-65879-DETAIL-01_10_2023-GO95HV-1^06148004.0170301 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2028-01-10 | 3
443259831-8279-DETAIL-01_17_2023-GO95BLTC-1^06148004.0174302 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
443259831-8279-DETAIL-01_17_2023-GO95MLD-1^06148004.0174302 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
649401669-25281-DETAIL-01_25_2023-INSULDMG-1^06148003.0355500 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
458069169-27221-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
662777284-43579-DETAIL-01_16_2023-GO95MLD-1^06148004.0164304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
310145405-74879-DETAIL-01_16_2023-GO95BLTC-1^06148004.0165305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
310145405-74879-DETAIL-01_16_2023-SVCROAD-1^06148004.0165305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
414178835-12779-DETAIL-01_16_2023-GO95MLD-1^06148004.0165306 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
414178835-12779-DETAIL-01_16_2023-SVCROAD-1^06148004.0165306 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
414178835-12779-DETAIL-01_16_2023-SVCROAD-2^06148004.0165306 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
414338345-88345-DETAIL-01_16_2023-GO95MLD-1^06148004.0165307 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
612493551-65879-DETAIL-01_10_2023-GO95MLD-1^06148004.0170301 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
612493551-65879-DETAIL-01_10_2023-GRDRODHI-1^06148004.0170301 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
604570584-52584-DETAIL-01_17_2023-GO95MLD-1^06148004.0174303 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
265220486-14379-DETAIL-01_17_2023-GO95HV-1^06148004.0175000 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
265220486-14379-DETAIL-01_17_2023-GO95MLD-1^06148004.0175000 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
265220486-14379-DETAIL-01_17_2023-GO95MLD-2^06148004.0175000 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
246769105-26889-DETAIL-01_10_2023-GO95TCH-1^06148004.0183201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
455444505-86079-ADMIN-01_10_2023-ENCHRW-1^06148004.0183203 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
521679055-47889-DETAIL-01_10_2023-EQUIPOIL-1^06148004.0184203 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
685097671-95989-DETAIL-01_10_2023-GRDRODHI-1^06148004.0186201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
345261786-26379-DETAIL-01_10_2023-GO95MLD-1^06148004.0187204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
345261786-26379-DETAIL-01_10_2023-GO95MLD-2^06148004.0187204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
704567781-40881-DETAIL-01_10_2023-GO95MLD-2^06148004.0187206 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
439508719-64819-DETAIL-01_10_2023-GO95MLD-1^06148004.0189205 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
180456054-43089-DETAIL-01_23_2023-GO95MLD-1^06148004.0191501 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
958070056-47779-DETAIL-01_24_2023-GO95MLD-1^06148004.0191900 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
426985984-88689-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
598769744-15189-DETAIL-01_23_2023-GO95MLD-1^06148004.0192003 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
736809193-17309-DETAIL-01_19_2023-CONDFRAY-1^06148004.0210602 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
191266144-28144-DETAIL-01_19_2023-GO95HV-1^06148004.0210801 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
938281254-92254-DETAIL-01_19_2023-GO95MLD-1^06148004.0210901 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
19704063-71779-DETAIL-01_18_2023-GO95MLD-1^06148004.0211000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
338665213-56579-DETAIL-01_19_2023-SVCROAD-1^06148004.0212601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
187360763-54309-DETAIL-01_18_2023-GO95HV-1^06148004.0213000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
109420054-88779-AUDIT-02_06_2023-GUYHINS-1^06148004.0214600 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
664838463-35309-DETAIL-01_18_2023-GO95MLD-1^06148004.0215001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-CONDFRAY-3^06148004.0215002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-GO95MLD-1^06148004.0215002 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
981280733-16309-DETAIL-01_18_2023-GO95HV-1^06148004.0215101 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
72454614-79779-DETAIL-01_18_2023-GO95MLD-1^06148004.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
220278255-65579-DETAIL-01_18_2023-GO95MLD-1^06148004.0207701 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
489594245-40009-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207900 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
394165985-58109-DETAIL-01_18_2023-GO95HV-1^06148004.0208001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
66981733-50309-DETAIL-01_18_2023-CONDFRAY-2^06148004.0210001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
66981733-50309-DETAIL-01_18_2023-CONDFRAY-3^06148004.0210001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
243654341-18779-DETAIL-01_19_2023-GO95MLD-1^06148004.0210600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
433070803-42779-AUDIT-02_16_2023-ABNDEQPM-1^06148004.0210800 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
938281254-92254-DETAIL-01_19_2023-GO95MLD-2^06148004.0210901 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
773469183-46279-DETAIL-01_18_2023-GO95MLD-1^06148004.0212001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
338665213-56579-DETAIL-01_19_2023-GO95MLD-1^06148004.0212601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
729610831-74309-DETAIL-01_18_2023-COPLLEAN-1^06148004.0214001 | POLE | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
729610831-74309-DETAIL-01_18_2023-GO95HV-1^06148004.0214001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
344302683-10209-DETAIL-01_17_2023-GRDBROKE-1^06148004.0220900 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
182719803-41379-DETAIL-01_17_2023-GO95MLD-1^06148004.0220901 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
310282351-14450-DETAIL-01_18_2023-GO95MLD-1^06148004.0221001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
854546984-25089-DETAIL-01_18_2023-GO95MLD-1^06148004.0221200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
854546984-25089-DETAIL-01_18_2023-GO95MLD-2^06148004.0221200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
854546984-25089-DETAIL-01_18_2023-GO95TCH-1^06148004.0221200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
319285034-9579-DETAIL-01_17_2023-GO95MLD-1^06148004.0222700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
22550001-92209-DETAIL-01_17_2023-GO95HV-1^06148004.0222702 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
22550001-92209-DETAIL-01_17_2023-GO95MLD-1^06148004.0222702 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
246751583-81079-DETAIL-01_17_2023-GO95BLTC-1^06148004.0222704 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
246751583-81079-DETAIL-01_17_2023-SVCROAD-1^06148004.0222704 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
327196574-31430-DTLSB-04_29_2021-SVCDEFLC-1^06236005.0334601 | OTHER | CA-TIER-2 | Distribution | 2021-04-29 | 2024-04-29 | 2
34761884-32884-DETAIL-11_17_2022-SVCSVC-1^06238004.0271700 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
112440971-99950-DETAIL-11_17_2022-GRDRODHI-1^06238004.0271740 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
112440971-99950-DETAIL-11_17_2022-GRDRODHI-2^06238004.0271740 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
735481021-25350-DETAIL-11_17_2022-GO95HV-1^06238004.0272701 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2027-11-17 | 3
637334801-85250-DETAIL-11_17_2022-SVCROAD-2^06238004.0272801 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
133847981-28150-DETAIL-11_17_2022-SVCENTCO-1^06238004.0273801 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
880717653-93679-DETAIL-01_17_2023-GO95MLD-1^06148004.0227801 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
880717653-93679-DETAIL-01_17_2023-GO95TCH-1^06148004.0227801 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
353184241-45499-DETAIL-01_17_2023-COPLLEAN-1^06148004.0229200 | POLE | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
415655503-47309-DETAIL-01_17_2023-GO95BLTC-1^06148004.0229700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
460608821-54879-DTLSB-11_01_2021-GO95BLTC-1^06148004.0242605 | OTHER | CA-NON-TIER | Distribution | 2021-11-01 | 2026-11-01 | 3
460608821-54879-DTLSB-11_01_2021-GO95HV-1^06148004.0242605 | OTHER | CA-NON-TIER | Distribution | 2021-11-01 | 2026-11-01 | 3
503276620-350-DTLSB-04_13_2021-RISEBKSP-1^06238004.0010500 | OTHER | CA-TIER-2 | Distribution | 2021-04-13 | 2024-04-13 | 2
561797162-41650-ADMIN-08_21_2023-POLEREPL-1^06238004.0027101 | POLE | CA-TIER-2 | Distribution | 2023-08-21 | 2024-08-21 | 2
851992146-72610-DTLSB-04_15_2021-GO95MLD-1^06238004.0117102 | OTHER | CA-TIER-2 | Distribution | 2021-04-15 | 2024-04-15 | 2
612211265-23265-DETAIL-11_16_2022-SVCENTCO-1^06238004.0150002 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
817044704-20010-DETAIL-11_16_2022-GO95HV-1^06238004.0150101 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
539172184-58810-DETAIL-11_16_2022-GO95MLD-1^06238004.0150200 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
486459344-71010-DETAIL-11_16_2022-GO95TCH-1^06238004.0152001 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
53425034-12810-DETAIL-11_16_2022-GO95HV-1^06238004.0152202 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
967968354-2010-DETAIL-11_16_2022-GO95MLD-1^06238004.0156202 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
607086574-8010-DETAIL-11_16_2022-GO95HV-1^06238004.0156241 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
537257984-16710-DETAIL-11_16_2022-GO95HV-1^06238004.0156400 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
134466835-81110-DETAIL-11_18_2022-RISEGRD-1^06238004.0157340 | OTHER | CA-TIER-2 | Distribution | 2022-11-18 | 2025-11-18 | 2
780410581-21411-DETAIL-01_17_2022-GO95TCH-1^06239004.0255446 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
152154020-9901-DETAIL-01_19_2022-SVCROAD-1^06239004.0255447 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
999289336-36280-DETAIL-01_12_2022-GO95HV-1^06239004.0255542 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2027-01-12 | 3
231441074-52260-DETAIL-01_12_2022-GO95MLD-1^06239004.0255546 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
231441074-52260-DETAIL-01_12_2022-SVCENTCO-1^06239004.0255546 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
787247896-60370-DETAIL-01_12_2022-GO95TCH-1^06239004.0255548 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
709197374-90860-DETAIL-01_24_2022-GRDRODHI-1^06239004.0255700 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
341955554-87260-DETAIL-01_24_2022-GO95MLD-1^06239004.0255701 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
341955554-87260-DETAIL-01_24_2022-GO95TCH-1^06239004.0255701 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
636832115-96470-DETAIL-01_25_2022-GO95TCH-1^06239004.0256001 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
578384299-62190-DETAIL-01_18_2022-SVCWIND-1^06239004.0256103 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
919550591-47050-DETAIL-11_17_2022-GO95MLD-1^06238004.0273740 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
573046089-57089-DETAIL-03_31_2021-SVCROAD-1^06239004.0244309 | OTHER | CA-TIER-2 | Distribution | 2021-03-31 | 2024-03-31 | 2
759153688-75390-AUDIT-04_28_2021-SVCROAD-1^06239004.0244411 | OTHER | CA-TIER-2 | Distribution | 2021-04-28 | 2024-04-28 | 2
500072895-72170-DETAIL-01_19_2022-GO95HV-1^06239004.0254200 | OTHER | CA-TIER-3 | Distribution | 2022-01-19 | 2027-01-19 | 3
799694754-56860-DETAIL-01_19_2022-SVCWIND-1^06239004.0254201 | OTHER | CA-TIER-3 | Distribution | 2022-01-19 | 2025-01-19 | 2
694555215-58770-DETAIL-01_19_2022-SVCROAD-1^06239004.0254203 | OTHER | CA-TIER-3 | Distribution | 2022-01-19 | 2025-01-19 | 2
127554056-24970-DETAIL-01_19_2022-GO95MLD-1^06239004.0254241 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
127554056-24970-DETAIL-01_19_2022-GRDRODHI-1^06239004.0254241 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
482476655-94870-DETAIL-01_24_2022-GO95TCH-1^06239004.0254401 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
482476655-94870-DETAIL-01_24_2022-POLESTEP-1^06239004.0254401 | POLE | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
482476655-94870-DETAIL-01_24_2022-SVCWIND-1^06239004.0254401 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
78497811-38601-DETAIL-01_19_2022-GUYLOINS-1^06239004.0255243 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
541397736-27470-DETAIL-01_19_2022-GO95MLD-1^06239004.0255245 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
424795646-14770-DETAIL-01_19_2022-SVCROAD-1^06239004.0255246 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
445376466-40070-DETAIL-01_19_2022-GO95HV-1^06239004.0255304 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2027-01-19 | 3
833812631-14711-DETAIL-01_19_2022-GO95MLD-1^06239004.0255346 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
541889790-5890-DETAIL-01_19_2022-SVCENTCO-1^06239004.0255400 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
746812831-16201-DETAIL-01_12_2022-GO95MLD-1^06239004.0255440 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
171071001-59201-DETAIL-01_12_2022-GO95MLD-1^06239004.0255443 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
152154020-9901-DETAIL-01_19_2022-GO95MLD-1^06239004.0255447 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
234937884-39260-DETAIL-01_12_2022-GO95HV-1^06239004.0255547 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2027-01-12 | 3
234937884-39260-DETAIL-01_12_2022-GO95TCH-1^06239004.0255547 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
787247896-60370-DETAIL-01_12_2022-SVCROAD-1^06239004.0255548 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
648574205-86941-DETAIL-11_14_2022-SVCWIND-1^06239004.0365701 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
2043666-28061-DETAIL-11_14_2022-GO95MLD-1^06239004.0365801 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
358093516-99871-DETAIL-11_14_2022-SVCWIND-1^06239004.0365842 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
246416025-45451-DETAIL-11_14_2022-GO95BLTC-1^06239004.0365903 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
672345376-54461-DETAIL-11_14_2022-GO95CL10-1^06239004.0365904 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
904663135-151-DETAIL-11_14_2022-GO95CL10-1^06239004.0365908 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
580267526-1371-DETAIL-11_14_2022-SVCWIND-2^06239004.0365940 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
352730046-94671-DETAIL-11_14_2022-GO95TCH-1^06239004.0365944 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
88713355-76451-DETAIL-11_15_2022-GO95MLD-1^06239004.0366601 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
379275255-38361-DETAIL-11_15_2022-GO95MLD-1^06239004.0366604 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
438189085-7851-DETAIL-11_15_2022-GO95CL10-1^06239004.0366701 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2027-11-15 | 3
378723475-30751-DETAIL-11_15_2022-GO95MLD-1^06239004.0366703 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
960029775-58170-DTLSB-05_03_2021-GO95MLD-1^06240003.0180501 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
154172015-9270-DTLSB-05_03_2021-GO95MLD-1^06240003.0182701 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
226496815-74370-DTLSB-05_03_2021-GO95MLD-1^06240003.0183801 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
311972225-78370-DTLSB-05_03_2021-GO95MLD-1^06240003.0184900 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
460719445-18670-DTLSB-05_03_2021-GO95MLD-1^06240003.0184902 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
748087896-21280-DETAIL-04_06_2021-GO95MLD-1^06240003.0368002 | OTHER | CA-TIER-2 | Distribution | 2021-04-06 | 2024-04-06 | 2
922668726-56080-DETAIL-04_06_2021-GO95MLD-1^06240003.0368101 | OTHER | CA-TIER-2 | Distribution | 2021-04-06 | 2024-04-06 | 2
856067846-13080-DETAIL-04_26_2023-GO95CL10-1^06240004.0050004 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
887183848-34850-DETAIL-04_26_2023-GO95MLD-1^06240004.0050041 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
975048126-41480-DETAIL-05_01_2023-GO95MLD-1^06240004.0050100 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
772718281-11801-DETAIL-01_25_2022-GO95MLD-1^06239004.0257342 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
842222571-6701-DETAIL-01_25_2022-SVCWIND-1^06239004.0257343 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
317098231-39750-AUDIT-12_07_2022-GO95MLD-1^06239004.0361003 | OTHER | CA-TIER-2 | Distribution | 2022-12-07 | 2025-12-07 | 2
191580928-3390-DETAIL-11_09_2022-GUYHINS-1^06239004.0361300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
620533898-38290-DETAIL-11_09_2022-GO95MLD-1^06239004.0361402 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
620533898-38290-DETAIL-11_09_2022-GUYHINS-1^06239004.0361402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
806020133-56721-DETAIL-11_09_2022-GO95TCH-1^06239004.0361404 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
806020133-56721-DETAIL-11_09_2022-SVCROAD-1^06239004.0361404 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
806020133-56721-ADMIN-11_15_2022-GO95HV-1^06239004.0361404 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2027-11-15 | 3
436386316-87480-DETAIL-11_15_2022-GO95MLD-1^06239004.0362001 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
293309732-20832-DETAIL-11_09_2022-ABNDEQPM-1^06239004.0362407 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
86120140-89020-DETAIL-11_09_2022-SVCWIND-1^06239004.0362500 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
778831351-36511-DETAIL-11_09_2022-GUYHINS-1^06239004.0362602 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
387785316-51908-DETAIL-11_14_2022-GO95TCH-1^06239004.0363200 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
201300976-75571-DETAIL-11_14_2022-GO95TCH-1^06239004.0365901 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
672345376-54461-ADMIN-11_15_2022-GO95HV-1^06239004.0365904 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2027-11-15 | 3
672345376-54461-AUDIT-11_15_2022-GO95HV-1^06239004.0365904 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2027-11-15 | 3
904663135-151-DETAIL-11_14_2022-GO95TCH-1^06239004.0365908 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
580267526-1371-DETAIL-11_14_2022-SVCWIND-1^06239004.0365940 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
352730046-94671-DETAIL-11_14_2022-GO95HV-1^06239004.0365944 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
378723475-30751-DETAIL-11_15_2022-SVCRUBLG-1^06239004.0366703 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
600794156-21661-DETAIL-11_15_2022-SVCWIND-1^06239004.0366804 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
40222666-88861-DETAIL-11_14_2022-SVCWIND-1^06239004.0366903 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
1019036-91371-DETAIL-11_15_2022-GO95MLD-1^06239004.0367702 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
288102866-30771-DETAIL-11_14_2022-ABNDEQPM-1^06239004.0367843 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
453495056-6271-DETAIL-11_14_2022-GO95MLD-1^06239004.0367941 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
286190518-90370-DETAIL-01_23_2023-GO95MLD-1^06240004.0081200 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
369090838-36370-DETAIL-01_23_2023-GRDRODHI-1^06240004.0081201 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
311394818-48970-DETAIL-01_23_2023-GO95TCH-1^06240004.0081202 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
433057508-10170-DETAIL-01_24_2023-ABNDEQPM-1^06240004.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
433057508-10170-DETAIL-01_24_2023-GO95BLTC-1^06240004.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
796110406-73840-DETAIL-01_19_2023-GO95MLD-1^06240004.0081302 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
9658378-96920-DETAIL-01_19_2023-GO95MLD-1^06240004.0081641 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
9658378-96920-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081641 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
354381038-79830-DETAIL-01_19_2023-GO95MLD-1^06240004.0081700 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
274967218-17830-DETAIL-01_19_2023-GO95TCH-1^06240004.0081701 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
507026169-80430-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081800 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
813471508-87270-DETAIL-01_17_2023-GO95MLD-1^06240004.0082201 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
241578203-42590-DETAIL-04_25_2023-GO95MLD-1^06240004.0064900 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
519222943-12730-DETAIL-04_25_2023-GO95HV-1^06240004.0064903 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2028-04-25 | 3
364273133-6230-DETAIL-04_26_2023-POLETOP-1^06240004.0065102 | POLE | CA-TIER-2 | Distribution | 2023-04-26 | 2024-04-26 | 2
676698158-62130-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0083500 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
396048134-71303-DETAIL-01_17_2023-GO95MLD-1^06240004.0084040 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
868284834-79003-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0084042 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
525091215-70489-DETAIL-01_18_2023-GO95MLD-1^06240004.0084600 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
457815289-74810-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085041 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
932180009-6220-DETAIL-01_17_2023-GO95MLD-1^06240004.0085042 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
512640620-35730-DETAIL-01_17_2023-GO95MLD-1^06240004.0085043 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
266488948-79163-DETAIL-01_16_2023-SVCWIND-1^06240004.0090504 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
150021238-30740-DETAIL-01_16_2023-GO95HV-1^06240004.0090505 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2028-01-16 | 3
150021238-30740-DETAIL-01_16_2023-POLESTEP-1^06240004.0090505 | POLE | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
403930650-32583-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0090540 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
104865740-48483-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0090541 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
574127149-25173-DETAIL-01_12_2023-GO95MLD-1^06240004.0091000 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
86246675-76770-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079502 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
305253141-60433-DETAIL-01_24_2023-GO95MLD-1^06240004.0079503 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
711833951-2433-DETAIL-01_24_2023-POLESTEP-1^06240004.0079504 | POLE | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
849528521-40333-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079505 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
480943823-75243-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079700 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
391588628-75450-DETAIL-01_09_2023-GO95MLD-1^06240004.0097502 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
948924608-9550-DETAIL-01_09_2023-GO95HV-1^06240004.0097504 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2028-01-09 | 3
720526038-88750-DETAIL-01_09_2023-GO95HV-1^06240004.0097602 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2028-01-09 | 3
395451178-88150-DETAIL-01_09_2023-GO95MLD-1^06240004.0097701 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
395451178-88150-DETAIL-01_09_2023-SVCDEFLC-1^06240004.0097701 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
244203328-77830-DETAIL-01_11_2023-GO95MLD-1^06240004.0098001 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
686710018-46830-DETAIL-01_11_2023-GO95MLD-1^06240004.0098003 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
47284744-66060-DETAIL-01_11_2023-GO95TCH-1^06240004.0098005 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
769433398-91970-DETAIL-01_23_2023-GO95MLD-1^06240004.0083000 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
901819753-60430-DETAIL-01_17_2023-GO95MLD-1^06240004.0083043 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
927187968-15070-DETAIL-01_17_2023-POLESTEP-1^06240004.0083101 | POLE | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
500495266-80840-DETAIL-01_17_2023-GO95MLD-1^06240004.0083140 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
736510418-55150-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0091500 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
614322168-99740-DETAIL-01_16_2023-GO95HV-1^06240004.0091603 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2028-01-16 | 3
86898489-4273-DETAIL-01_11_2023-GO95BLTC-1^06240004.0092203 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
588245071-24480-DTLSB-05_03_2021-GO95HV-1^06240004.0134100 | OTHER | CA-TIER-3 | Distribution | 2021-05-03 | 2026-05-03 | 3
287059941-64720-DTLSB-05_03_2021-GO95HV-1^06240004.0134101 | OTHER | CA-TIER-3 | Distribution | 2021-05-03 | 2026-05-03 | 3
937343481-29480-DTLSB-05_03_2021-GO95HV-1^06240004.0136100 | OTHER | CA-TIER-3 | Distribution | 2021-05-03 | 2026-05-03 | 3
914971501-97580-DTLSB-05_03_2021-GO95HV-1^06240004.0139302 | OTHER | CA-TIER-3 | Distribution | 2021-05-03 | 2026-05-03 | 3
461159446-3340-DTLSB-05_04_2021-RISEGRD-1^06240004.0152600 | OTHER | CA-TIER-2 | Distribution | 2021-05-04 | 2024-05-04 | 2
136389448-61470-DETAIL-03_23_2023-GO95MLD-1^06240004.0160300 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
136389448-61470-DETAIL-03_23_2023-GO95TCH-1^06240004.0160300 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
136389448-61470-DETAIL-03_23_2023-SVCWIND-1^06240004.0160300 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
86898489-4273-DETAIL-01_11_2023-GO95TCH-1^06240004.0092203 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
371039593-96550-DETAIL-01_09_2023-SVCDEFLC-1^06240004.0096604 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
437032753-68780-DETAIL-01_10_2023-GUYHINS-1^06240004.0097001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
234928153-29760-DETAIL-01_10_2023-GO95HV-1^06240004.0097040 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2028-01-10 | 3
234928153-29760-DETAIL-01_10_2023-GO95MLD-1^06240004.0097040 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
234928153-29760-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0097040 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
361773233-50760-DETAIL-01_10_2023-POLETOP-1^06240004.0097141 | POLE | CA-TIER-2 | Distribution | 2023-01-10 | 2024-01-10 | 2
795379913-71660-DETAIL-01_10_2023-POLESTEP-1^06240004.0097143 | POLE | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
500134968-36920-DETAIL-01_10_2023-GO95HV-1^06240004.0097200 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2028-01-10 | 3
18718316-82240-DETAIL-01_10_2023-RISEGRD-1^06240004.0097202 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
774405524-70760-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0097300 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
699568338-78250-DETAIL-05_08_2023-GO95MLD-1^06240004.0100501 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
705999990-38670-DETAIL-04_19_2023-SVCWIND-1^06240004.0165708 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
982487914-84999-DETAIL-04_17_2023-GO95CL10-1^06240004.0165750 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
982487914-84999-DETAIL-04_17_2023-GO95MLD-1^06240004.0165750 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
335068058-25970-DETAIL-04_12_2023-GO95MLD-1^06240004.0165804 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
335068058-25970-DETAIL-04_12_2023-GO95TCH-1^06240004.0165804 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
335068058-25970-DETAIL-04_12_2023-SVCWIND-1^06240004.0165804 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
857023568-4450-DETAIL-03_28_2023-GO95MLD-1^06240004.0165840 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
857023568-4450-DETAIL-03_28_2023-SVCWIND-1^06240004.0165840 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
270644919-16270-DETAIL-03_29_2023-GO95MLD-1^06240004.0165841 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
270644919-16270-DETAIL-03_29_2023-GO95TCH-1^06240004.0165841 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
694430629-49070-DETAIL-04_12_2023-GO95MLD-1^06240004.0165900 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
887585549-91230-DETAIL-03_22_2023-GO95MLD-1^06240004.0164303 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
18413323-6480-DETAIL-03_23_2023-GO95HV-1^06240004.0164600 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2028-03-23 | 3
683437243-52280-DETAIL-03_27_2023-GO95MLD-1^06240004.0164603 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
237495403-88680-DETAIL-03_28_2023-GUYHINS-1^06240004.0164604 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
79123001-50970-DETAIL-03_22_2023-GO95MLD-1^06240004.0166101 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
79123001-50970-DETAIL-03_22_2023-SVCRUBLG-1^06240004.0166101 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
636548079-40570-DETAIL-03_22_2023-GO95HV-1^06240004.0166102 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
591558790-79270-DETAIL-03_22_2023-SVCDEFLC-2^06240004.0166104 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
957553731-45080-DETAIL-03_22_2023-SVCENTCO-1^06240004.0166105 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
664194000-42370-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166202 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
279709423-46680-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166203 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
966628763-41980-DETAIL-03_27_2023-GO95CL10-1^06240004.0164608 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
966628763-41980-DETAIL-03_27_2023-GO95MLD-1^06240004.0164608 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
708882413-73180-DETAIL-04_19_2023-GO95MLD-1^06240004.0164800 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
738086358-6050-DETAIL-03_28_2023-GO95TCH-1^06240004.0164841 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
385177378-1550-DETAIL-04_19_2023-GO95MLD-1^06240004.0164846 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
385177378-1550-DETAIL-04_19_2023-GUYHINS-1^06240004.0164846 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
745358513-34180-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0164900 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
213625583-74680-DETAIL-03_22_2023-GO95MLD-1^06240004.0165301 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
228127509-71570-DETAIL-03_28_2023-ABNDEQPM-1^06240004.0165501 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
622785331-95080-DETAIL-04_17_2023-GO95CL10-1^06240004.0165643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
622785331-95080-DETAIL-04_17_2023-GO95HV-1^06240004.0165643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
862460663-10380-DETAIL-03_29_2023-SVCDEFLC-1^06240004.0165701 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
61996389-34370-DETAIL-03_28_2023-GO95HV-1^06240004.0167541 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
176215011-36780-DETAIL-04_17_2023-SVCWIND-2^06240004.0167543 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
734638989-67170-DETAIL-04_11_2023-GO95TCH-1^06240004.0167548 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
350294799-58170-DETAIL-03_28_2023-RISECLMB-1^06240004.0167549 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
788703292-24292-DETAIL-04_19_2023-GO95MLD-1^06240004.0167550 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
788703292-24292-DETAIL-04_19_2023-RISEGRD-1^06240004.0167550 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
740251193-22193-DETAIL-04_12_2023-GO95HV-1^06240004.0167605 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
86165630-27870-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166103 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
591558790-79270-DETAIL-03_22_2023-GO95MLD-1^06240004.0166104 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
591558790-79270-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166104 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
957553731-45080-DETAIL-03_22_2023-GO95TCH-1^06240004.0166105 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
35983081-79380-DETAIL-03_22_2023-GO95TCH-1^06240004.0166140 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
935643511-11180-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167103 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
326594073-9380-DETAIL-04_10_2023-GO95MLD-1^06240004.0168200 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
289551370-61970-DETAIL-04_10_2023-GO95TCH-1^06240004.0168204 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
567226522-85780-DETAIL-04_11_2023-GO95MLD-1^06240004.0168241 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
715758381-73480-DETAIL-04_10_2023-GO95MLD-1^06240004.0168242 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
843503530-26470-DETAIL-04_10_2023-SVCROAD-1^06240004.0168300 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
481973979-37570-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168305 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
318008961-4980-DETAIL-04_10_2023-GO95MLD-1^06240004.0168307 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
318008961-4980-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168307 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
682365361-11980-DETAIL-04_10_2023-GO95MLD-1^06240004.0168308 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
682365361-11980-DETAIL-04_10_2023-SVCROOF-1^06240004.0168308 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
176215011-36780-DETAIL-04_17_2023-SVCWIND-1^06240004.0167543 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
912219292-10392-DETAIL-04_17_2023-GO95MLD-1^06240004.0167551 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
740251193-22193-DETAIL-04_12_2023-GO95MLD-1^06240004.0167605 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
891190580-14670-DETAIL-04_12_2023-GO95MLD-1^06240004.0167700 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
337237760-3870-DETAIL-04_12_2023-SVCWIND-1^06240004.0167701 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
584588073-92680-DETAIL-04_10_2023-SVCWIND-1^06240004.0169102 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
445452261-78380-DETAIL-04_10_2023-GO95TCH-1^06240004.0169103 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
812303973-91680-DETAIL-04_10_2023-GO95MLD-1^06240004.0169105 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
852529250-18170-DETAIL-04_10_2023-GO95MLD-1^06240004.0169107 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
450239781-15480-DETAIL-04_10_2023-GO95MLD-1^06240004.0169109 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
86565588-6799-DETAIL-03_22_2023-SVCWIND-1^06240004.0169142 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
918863281-44780-DETAIL-03_22_2023-GO95TCH-1^06240004.0169143 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
918712298-37070-DETAIL-03_28_2023-GO95HV-1^06240004.0169504 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
602295238-46670-DETAIL-03_28_2023-GO95MLD-1^06240004.0169506 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
835770848-48670-DETAIL-03_28_2023-GO95TCH-1^06240004.0169507 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
835770848-48670-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0169507 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
508246828-55670-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0169509 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
113600818-55770-DETAIL-04_12_2023-ABNDEQPM-1^06240004.0169510 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
343990278-48770-DETAIL-04_11_2023-RISEGRD-1^06240004.0169511 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
312609058-93270-DETAIL-04_11_2023-GO95MLD-1^06240004.0168508 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
653037698-70770-DETAIL-04_11_2023-GO95HV-1^06240004.0168509 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2028-04-11 | 3
545274592-41880-DETAIL-04_10_2023-GO95TCH-1^06240004.0169005 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
969189331-27280-DETAIL-03_22_2023-GO95TCH-2^06240004.0169006 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
574879811-3580-DETAIL-03_22_2023-GO95MLD-1^06240004.0169041 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
218483550-46830-DETAIL-04_17_2023-GO95MLD-1^06240004.0176804 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
252873131-60430-DETAIL-04_17_2023-SVCDEFLC-1^06240004.0176902 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
836614210-12730-DETAIL-04_17_2023-GO95MLD-1^06240004.0176941 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
466443101-63330-DETAIL-04_19_2023-GO95MLD-1^06240004.0177804 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
283110220-62630-DETAIL-04_17_2023-SVCDEFLC-1^06240004.0177940 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
222715264-3690-DETAIL-03_23_2023-GO95MLD-1^06240004.0178302 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
370809073-24390-DETAIL-03_23_2023-GUYNOINS-1^06240004.0178303 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
874852711-45330-DETAIL-04_17_2023-GO95MLD-1^06240004.0178900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
461712600-64070-DETAIL-04_10_2023-GO95MLD-1^06240004.0169208 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
691429680-54870-DETAIL-04_11_2023-GO95CLSV-1^06240004.0169302 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
227524121-18580-DETAIL-04_11_2023-GO95MLD-1^06240004.0169341 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
986449181-89020-DTLSB-05_11_2021-GO95MLD-1^06240004.0272800 | OTHER | CA-TIER-3 | Distribution | 2021-05-11 | 2024-05-11 | 2
79966902-23520-DTLSB-05_11_2021-GO95MLD-1^06240004.0277440 | OTHER | CA-TIER-2 | Distribution | 2021-05-11 | 2024-05-11 | 2
277313613-49080-DETAIL-01_25_2023-GO95MLD-1^06240005.0016101 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
229078143-12180-DETAIL-01_25_2023-RISECLMB-1^06240005.0016201 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
49172771-61963-DETAIL-01_25_2023-GO95MLD-1^06240005.0128900 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
308478551-43863-DETAIL-01_24_2023-GO95MLD-1^06240005.0129903 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
395932870-3019-DETAIL-08_06_2021-GO95CL10-1^06240007.0072100 | OTHER | CA-NON-TIER | Distribution | 2021-08-06 | 2024-08-06 | 2
587533402-70119-DETAIL-08_18_2021-XARMSPCR-1^06240008.0062002 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-18 | 2024-08-18 | 2
219076792-90519-DETAIL-08_11_2021-XARMSPCR-1^06240008.0133901 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-11 | 2024-08-11 | 2
139670583-73419-DETAIL-08_11_2021-POLETOP-1^06240008.0155000 | POLE | CA-NON-TIER | Distribution | 2021-08-11 | 2024-08-11 | 2
283955453-46290-DETAIL-04_20_2023-GO95HV-1^06240004.0176201 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
982943843-5290-DETAIL-04_20_2023-GO95HV-1^06240004.0176203 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
622778365-96151-DETAIL-05_03_2022-GO95MLD-1^06241005.0012502 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
622778365-96151-DETAIL-05_03_2022-SVCROAD-1^06241005.0012502 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
815858395-55251-DETAIL-05_09_2022-SVCROAD-1^06241005.0012543 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
763445544-3131-DETAIL-05_03_2022-GO95MLD-1^06241005.0012601 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
993172049-50870-DTLSB-05_05_2021-GO95MLD-1^06240004.0221900 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2026-05-05 | 3
993172049-50870-DTLSB-05_05_2021-GO95TCH-1^06240004.0221900 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2024-05-05 | 2
281590352-80520-DTLSB-05_12_2021-GO95CL10-1^06240004.0271142 | OTHER | CA-TIER-2 | Distribution | 2021-05-12 | 2024-05-12 | 2
281590352-80520-DTLSB-05_12_2021-GO95MLD-1^06240004.0271142 | OTHER | CA-TIER-2 | Distribution | 2021-05-12 | 2024-05-12 | 2
379493881-32920-AUDIT-06_22_2021-GUYHINS-1^06240004.0272703 | ANCHOR/GUY | CA-TIER-3 | Distribution | 2021-06-22 | 2024-06-22 | 2
986449181-89020-DTLSB-05_11_2021-GO95HV-1^06240004.0272800 | OTHER | CA-TIER-3 | Distribution | 2021-05-11 | 2026-05-11 | 3
77920721-40020-DTLSB-05_13_2021-RISEGRD-1^06240004.0274500 | OTHER | CA-TIER-2 | Distribution | 2021-05-13 | 2024-05-13 | 2
657407392-87080-DETAIL-01_25_2023-GO95TCH-1^06240005.0015000 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2026-01-25 | 2
649486253-25341-DETAIL-02_08_2022-GO95MLD-1^06241004.0182303 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2025-02-08 | 2
346908833-43890-DETAIL-04_25_2023-GO95MLD-1^06241004.0314000 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
64448663-64290-DETAIL-04_25_2023-GO95MLD-1^06241004.0314003 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
149940304-46490-DETAIL-04_25_2023-GO95TCH-1^06241004.0314100 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
134023553-21090-DETAIL-04_25_2023-GO95MLD-1^06241004.0314101 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
547217412-48811-DETAIL-05_11_2022-GO95MLD-1^06241005.0010000 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
547217412-48811-DETAIL-05_11_2022-GO95TCH-1^06241005.0010000 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
463186873-12121-DETAIL-05_10_2022-GO95MLD-1^06241005.0010405 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
157603186-21661-DETAIL-05_09_2022-RISEGRD-1^06241005.0010502 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
11898536-98471-DETAIL-05_03_2022-ANCHIDLE-1^06241005.0010640 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
221038724-75421-DETAIL-05_10_2022-GO95MLD-1^06241005.0011404 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
221038724-75421-DETAIL-05_10_2022-SVCENTCO-1^06241005.0011404 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
223806702-29141-DETAIL-05_17_2022-GO95MLD-1^06241005.0026510 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
143558603-61361-DETAIL-05_17_2022-GO95MLD-1^06241005.0026600 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
779828743-43061-DETAIL-05_12_2022-GO95MLD-1^06241005.0026942 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
134228433-43861-DETAIL-05_12_2022-GO95MLD-1^06241005.0026943 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
595126819-90952-DETAIL-05_18_2022-GO95BLTC-1^06241005.0027000 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
595126819-90952-DETAIL-05_18_2022-GO95HV-1^06241005.0027000 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
40014166-72542-DETAIL-05_16_2022-GO95MLD-1^06241005.0027004 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
726927344-94522-DETAIL-05_18_2022-GO95MLD-1^06241005.0027005 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
415116184-55331-DETAIL-05_03_2022-GUYNOINS-1^06241005.0012707 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
435822144-71431-DETAIL-05_03_2022-GO95MLD-1^06241005.0012708 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
782829574-53231-DETAIL-05_03_2022-GUYHINS-1^06241005.0012710 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
731455734-11721-DETAIL-05_09_2022-ABNDEQPM-1^06241005.0012711 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
731751496-33481-DETAIL-05_10_2022-SVCWIND-1^06241005.0012742 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
67047011-78131-DETAIL-05_18_2022-ABNDEQPM-1^06241005.0024103 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
67047011-78131-DETAIL-05_18_2022-SVCCOMMD-1^06241005.0024103 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
688463486-31742-DETAIL-05_11_2022-GO95BLTC-1^06241005.0028104 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
75247744-80232-DETAIL-05_18_2022-SVCWIND-1^06241005.0028105 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
837523159-41552-DETAIL-05_18_2022-SVCWIND-1^06241005.0028142 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
190609539-53952-DETAIL-05_18_2022-GO95MLD-1^06241005.0028143 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
606301860-15352-DETAIL-05_16_2022-GO95MLD-1^06241005.0028145 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
300040359-81352-DETAIL-05_16_2022-GO95MLD-1^06241005.0028149 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
44458140-68852-DETAIL-05_18_2022-POLESTEP-1^06241005.0028242 | POLE | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
492551849-50552-DETAIL-05_11_2022-GO95HV-1^06241005.0028245 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
772364351-43311-DETAIL-05_17_2022-SVCNEUT-1^06241005.0024400 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
739814741-86111-DETAIL-05_17_2022-GO95STUB-1^06241005.0024402 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
364759195-23632-DETAIL-05_17_2022-GO95GUYP-2^06241005.0026405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
160959172-17341-DETAIL-05_17_2022-GO95MLD-1^06241005.0026408 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
160959172-17341-DETAIL-05_17_2022-SVCWIND-1^06241005.0026408 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
769250203-47151-DETAIL-05_17_2022-GO95HV-1^06241005.0026509 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
541842596-23596-DETAIL-05_19_2022-GO95MLD-1^06241005.0026602 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2025-05-19 | 2
541842596-23596-DETAIL-05_19_2022-GRDRODHI-1^06241005.0026602 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2025-05-19 | 2
279072752-97641-DETAIL-05_12_2022-GO95MLD-1^06241005.0026900 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
960325221-79082-DETAIL-05_12_2022-GO95MLD-1^06241005.0026941 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
595126819-90952-DETAIL-05_18_2022-GO95MLD-1^06241005.0027000 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
595126819-90952-DETAIL-05_18_2022-GO95TCH-1^06241005.0027000 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
774427015-77015-DETAIL-05_18_2022-SVCCOMMD-1^06241005.0027002 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
774427015-77015-DETAIL-05_18_2022-SVCCOMMD-2^06241005.0027002 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
776496100-41061-DETAIL-06_01_2022-GO95MLD-1^06241005.0092500 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
148821319-53021-DETAIL-06_01_2022-GO95TCH-1^06241005.0092501 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
78421209-50921-DETAIL-06_02_2022-GO95BLTC-1^06241005.0092700 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2027-06-02 | 3
504776689-21841-DETAIL-06_02_2022-GO95BLTC-1^06241005.0092901 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2027-06-02 | 3
504776689-21841-DETAIL-06_02_2022-GO95TCH-1^06241005.0092901 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
734976650-87471-DETAIL-06_01_2022-GUYHINS-1^06241005.0093300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
329582460-52461-DETAIL-06_02_2022-GO95HV-1^06241005.0095900 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2027-06-02 | 3
329582460-52461-DETAIL-06_02_2022-GO95MLD-1^06241005.0095900 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
268979683-80561-DETAIL-05_12_2022-GO95HV-1^06241005.0027940 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
163537137-77400-DETAIL-05_18_2022-GUYHINS-1^06241005.0028003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
600011690-31452-DETAIL-05_18_2022-POLESTEP-1^06241005.0028042 | POLE | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
93700345-57432-DETAIL-05_18_2022-SVCENTCO-1^06241005.0028100 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
330641275-78432-DETAIL-05_11_2022-GO95TCH-1^06241005.0028306 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
708107086-28742-DETAIL-05_16_2022-GO95TCH-1^06241005.0028308 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
825459805-54032-DETAIL-05_16_2022-GO95MLD-1^06241005.0028309 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
825459805-54032-DETAIL-05_16_2022-SVCENTCO-1^06241005.0028309 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
697450474-93332-DETAIL-05_16_2022-GO95MLD-1^06241005.0028311 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
287380100-8752-DETAIL-05_10_2022-GO95MLD-1^06241005.0028340 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
183700580-14752-DETAIL-05_10_2022-GO95MLD-1^06241005.0028343 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
192702366-95842-DETAIL-05_16_2022-GO95MLD-1^06241005.0028402 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
977638205-43632-DETAIL-05_16_2022-ENCHRW-1^06241005.0028403 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
747817585-25532-DETAIL-05_10_2022-GO95MLD-1^06241005.0028404 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
818338265-23332-DETAIL-05_16_2022-GO95MLD-1^06241005.0028405 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
244106715-86032-DETAIL-05_16_2022-GO95MLD-1^06241005.0028406 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
924418734-44651-DETAIL-05_03_2022-GO95MLD-1^06241005.0029604 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
763330503-27051-DETAIL-05_12_2022-GO95MLD-1^06241005.0029902 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
82466240-57601-DETAIL-06_02_2022-GO95HV-1^06241005.0030701 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2027-06-02 | 3
56894049-87291-DETAIL-06_01_2022-GO95HV-1^06241005.0034701 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
876040808-21613-DETAIL-06_01_2022-GRDRODHI-1^06241005.0034702 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
387090444-77331-DETAIL-06_09_2022-SVCROAD-1^06241005.0064900 | OTHER | CA-TIER-2 | Distribution | 2022-06-09 | 2025-06-09 | 2
690800259-4889-DETAIL-06_02_2022-GO95HV-1^06241005.0090800 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2027-06-02 | 3
690800259-4889-DETAIL-06_02_2022-GO95MLD-1^06241005.0090800 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
398986349-27841-DETAIL-06_01_2022-GO95BLTC-1^06241005.0091001 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
65576280-38861-DETAIL-06_01_2022-LIGHT-1^06241005.0091200 | CONNECTION DEVICE | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
439999729-78731-DETAIL-06_02_2022-GUYNOINS-1^06241005.0091801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
955265359-43251-DETAIL-06_01_2022-GO95BLTC-1^06241005.0092001 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
400799330-52571-DETAIL-06_01_2022-SVCWIND-1^06241005.0092102 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
324758730-7132-DETAIL-01_26_2022-GO95MLD-1^06241005.0117502 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
977258750-92232-DETAIL-01_27_2022-GO95MLD-1^06241005.0117506 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
812071-43732-DETAIL-01_10_2022-GO95MLD-1^06241005.0117600 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
584151570-1332-DETAIL-01_10_2022-SVCROAD-1^06241005.0117602 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
37728334-19861-DETAIL-02_07_2022-GO95MLD-1^06241005.0232404 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
798714234-44061-DETAIL-02_07_2022-POLESTEP-1^06241005.0232700 | POLE | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
38837194-9261-DETAIL-02_07_2022-GO95TCH-1^06241005.0235601 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
373892504-57561-DETAIL-02_07_2022-GO95MLD-1^06241005.0235901 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2027-02-07 | 3
965889980-85561-DETAIL-05_25_2022-CLMBHAZ-1^06241005.0241801 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
476765740-54371-DETAIL-05_25_2022-GO95TCH-1^06241005.0242300 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
794397604-19730-DETAIL-05_02_2023-GO95MLD-1^06241005.0252041 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
794397604-19730-DETAIL-05_02_2023-GUYHINS-1^06241005.0252041 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
152515944-64630-DETAIL-05_02_2023-GO95MLD-1^06241005.0360904 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
359966244-82630-DETAIL-05_02_2023-GO95MLD-1^06241005.0361900 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
303831764-33630-DETAIL-05_02_2023-GO95MLD-1^06241005.0361901 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
469823933-82420-DETAIL-05_02_2023-GO95MLD-1^06241005.0362902 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
161598624-42530-DETAIL-05_02_2023-GO95MLD-1^06241005.0363501 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
99014180-91632-DETAIL-01_26_2022-GO95TCH-1^06241005.0118605 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
818032532-9463-DETAIL-01_26_2022-GO95MLD-1^06241005.0118606 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2027-01-26 | 3
954110388-54998-DETAIL-01_10_2022-CLMBHAZ-1^06241005.0118700 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
688554880-86732-DETAIL-01_10_2022-GUYHINS-1^06241005.0118701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
77381490-59932-DETAIL-01_10_2022-GO95MLD-1^06241005.0118702 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
487889634-16032-DETAIL-01_27_2022-SVCDEFLC-1^06241005.0119200 | OTHER | CA-TIER-3 | Distribution | 2022-01-27 | 2025-01-27 | 2
85126034-73132-DETAIL-01_26_2022-GO95MLD-1^06241005.0119203 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
357126904-68512-DETAIL-01_26_2022-SVCROAD-2^06241005.0119301 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
537729214-93130-DETAIL-05_02_2023-GO95BLTC-1^06241005.0363600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2028-05-02 | 3
537729214-93130-AUDIT-07_10_2023-SVCDEFLC-1^06241005.0363600 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
793752773-4520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363601 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
637996134-38130-DETAIL-05_02_2023-GO95TCH-1^06241005.0363700 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
915422463-82520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363701 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
776957053-52520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363703 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
378086253-41520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363704 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
691997683-82512-DETAIL-01_26_2022-GO95HV-1^06241005.0119303 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2027-01-26 | 3
41199014-6322-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0119304 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
387342414-93322-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0119305 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
531343554-63130-DETAIL-05_01_2023-GO95MLD-1^06241005.0366102 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
27765924-36930-DETAIL-05_01_2023-GO95MLD-1^06241005.0366200 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
27765924-36930-DETAIL-05_01_2023-SVCDEFLC-1^06241005.0366200 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
746396674-41130-DETAIL-05_02_2023-GO95HV-1^06241005.0366600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2028-05-02 | 3
746396674-41130-DETAIL-05_02_2023-GO95MLD-1^06241005.0366600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
487892513-58530-DETAIL-05_02_2023-GO95MLD-1^06241005.0366604 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
108864345-93730-DETAIL-05_03_2023-SVCENTCO-1^06241005.0367901 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
821320707-67681-DETAIL-06_07_2022-SVCENTCO-1^06241006.0017900 | OTHER | CA-TIER-2 | Distribution | 2022-06-07 | 2025-06-07 | 2
44926493-56219-DETAIL-08_05_2021-UNIGRDSG-1^06241009.0115202 | OTHER | CA-NON-TIER | Distribution | 2021-08-05 | 2024-08-05 | 2
288124444-54319-DETAIL-08_02_2021-GUYNOINS-2^06241009.0116700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2021-08-02 | 2024-08-02 | 2
247691903-64219-DETAIL-08_05_2021-XARMSPCR-1^06241009.0118200 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-05 | 2024-08-05 | 2
576054553-26051-DETAIL-05_11_2022-GO95MLD-1^06241005.0133901 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
795415129-61172-DETAIL-05_05_2022-GO95MLD-1^06241005.0136601 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
983690426-13789-DETAIL-04_12_2021-GO95MLD-1^06241009.0326400 | OTHER | CA-TIER-2 | Distribution | 2021-04-12 | 2024-04-12 | 2
195764656-27079-DETAIL-04_12_2021-GO95MLD-1^06241009.0326501 | OTHER | CA-TIER-2 | Distribution | 2021-04-12 | 2026-04-12 | 3
789973046-22299-DETAIL-04_08_2021-GRDRODHI-1^06241009.0326607 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
789973046-22299-DETAIL-04_08_2021-SVCROAD-1^06241009.0326607 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
877733706-43579-DETAIL-04_08_2021-GO95HV-1^06241009.0326800 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2026-04-08 | 3
877733706-43579-DETAIL-04_08_2021-GO95MLD-1^06241009.0326800 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2026-04-08 | 3
839899343-46241-DTLSB-08_25_2022-ABNDEQPM-1^06242005.0081500 | OTHER | CA-TIER-2 | Distribution | 2022-08-25 | 2027-08-25 | 3
155751694-46261-DETAIL-02_07_2022-GO95HV-1^06241005.0236701 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2027-02-07 | 3
155751694-46261-DETAIL-02_07_2022-GO95MLD-1^06241005.0236701 | OTHER | CA-TIER-3 | Distribution | 2022-02-07 | 2025-02-07 | 2
836962550-20571-DETAIL-05_25_2022-SVCWIND-1^06241005.0241300 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
965889980-85561-DETAIL-05_25_2022-POLESTEP-1^06241005.0241801 | POLE | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
57042733-57030-AUDIT-06_08_2023-GO95CL10-1^06241005.0250003 | OTHER | CA-TIER-2 | Distribution | 2023-06-08 | 2028-06-08 | 3
21575423-42420-DETAIL-05_02_2023-GUYNOINS-1^06241005.0250004 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
21575423-42420-DETAIL-05_02_2023-GUYNOINS-2^06241005.0250004 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
523970224-91930-DETAIL-05_03_2023-RISEGRD-1^06241005.0252140 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
747751344-81861-DTLSB-07_19_2022-GO95GUYP-1^06242005.0131800 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
711484024-60861-DTLSB-07_19_2022-GO95HV-1^06242005.0131801 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
88031294-8629-DTLSB-07_28_2022-GO95BLTC-1^06242005.0139500 | OTHER | CA-TIER-2 | Distribution | 2022-07-28 | 2027-07-28 | 3
231911553-62219-DETAIL-08_02_2021-ENCHRW-1^06241009.0122100 | OTHER | CA-NON-TIER | Distribution | 2021-08-02 | 2024-08-02 | 2
231911553-62219-DETAIL-08_02_2021-SVCWIND-1^06241009.0122100 | OTHER | CA-NON-TIER | Distribution | 2021-08-02 | 2024-08-02 | 2
512731254-40519-DETAIL-04_07_2021-XARMSPCR-1^06241009.0154702 | CROSSARM | CA-NON-TIER | Distribution | 2021-04-07 | 2024-04-07 | 2
896145353-93769-DETAIL-04_07_2021-XARMSPCR-1^06241009.0155901 | CROSSARM | CA-NON-TIER | Distribution | 2021-04-07 | 2024-04-07 | 2
361415634-5399-ADMIN-07_18_2023-POLEREPL-1^06241009.0220501 | POLE | CA-NON-TIER | Distribution | 2023-07-18 | 2026-07-18 | 2
181955823-36519-ADMIN-08_02_2023-POLEREPL-1^06241009.0224300 | POLE | CA-NON-TIER | Distribution | 2023-08-02 | 2026-08-02 | 2
361307313-74551-DETAIL-05_05_2022-GO95MLD-1^06241005.0130100 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
583934713-23551-DETAIL-05_05_2022-GRDRODHI-1^06241005.0130101 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
583934713-23551-DETAIL-05_05_2022-GUYHINS-1^06241005.0130101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
174670324-11551-DETAIL-05_05_2022-GO95TCH-1^06241005.0130505 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
824887234-79234-DETAIL-05_11_2022-GO95BLTC-1^06241005.0130507 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
614624770-29791-DTLSB-07_27_2022-GO95HV-1^06242005.0266800 | OTHER | CA-TIER-2 | Distribution | 2022-07-27 | 2027-07-27 | 3
282485493-11030-DETAIL-05_03_2023-GO95MLD-1^06241005.0254204 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
344316764-43630-DETAIL-05_03_2023-GO95MLD-1^06241005.0254301 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
406591645-29830-DETAIL-04_27_2023-GO95MLD-1^06241005.0254641 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
202124574-49130-DETAIL-04_27_2023-GO95MLD-1^06241005.0254800 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
657879593-98030-DETAIL-05_03_2023-GO95MLD-1^06241005.0255200 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
321965736-78301-DETAIL-04_27_2023-GO95MLD-1^06241005.0255500 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
52894544-76030-DETAIL-04_27_2023-GO95MLD-1^06241005.0255803 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
402238984-50730-DETAIL-04_27_2023-GO95MLD-1^06241005.0255902 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2028-04-27 | 3
684186079-7079-DETAIL-04_27_2023-GO95HV-1^06241005.0255904 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2028-04-27 | 3
122094546-76511-DETAIL-04_27_2023-GO95MLD-1^06241005.0256601 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
686511814-16430-DETAIL-04_27_2023-GO95MLD-1^06241005.0256900 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
956941723-80341-DETAIL-05_31_2022-GO95MLD-1^06242005.0334804 | OTHER | CA-TIER-2 | Distribution | 2022-05-31 | 2025-05-31 | 2
776957053-52520-DETAIL-05_02_2023-SVCROAD-1^06241005.0363703 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
692024624-930-DETAIL-05_01_2023-GO95MLD-1^06241005.0364301 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
812756223-35030-DETAIL-05_01_2023-GO95MLD-1^06241005.0364302 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
88310614-19430-DETAIL-05_04_2023-GO95MLD-1^06241005.0364402 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
952184736-70040-DETAIL-05_02_2023-GO95MLD-1^06241005.0364600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2028-05-02 | 3
993511306-57540-DETAIL-05_03_2023-GO95HV-1^06241005.0364803 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
501531093-9220-DETAIL-05_03_2023-GRDRODHI-1^06241005.0364900 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
292002324-32530-DETAIL-05_01_2023-GO95MLD-1^06241005.0365101 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
914683966-93840-DETAIL-05_01_2023-GO95MLD-1^06241005.0365102 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
454982033-6030-DETAIL-05_01_2023-GO95MLD-1^06241005.0365201 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
165039523-45030-DETAIL-05_01_2023-GO95MLD-1^06241005.0365205 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
411946116-56640-DETAIL-05_01_2023-SVCROAD-1^06241005.0365300 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
826575110-19752-DETAIL-05_10_2022-GO95MLD-1^06241005.0029341 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
396122130-60432-DETAIL-01_26_2022-GO95MLD-1^06241005.0118505 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
715779130-97232-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0118507 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
960544701-59799-DETAIL-01_26_2022-GO95MLD-1^06241005.0118510 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
960544701-59799-DETAIL-01_26_2022-SVCWIND-1^06241005.0118510 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
703889731-22332-DETAIL-01_26_2022-GO95MLD-1^06241005.0118603 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
703889731-22332-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0118603 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
818032532-9463-DETAIL-01_26_2022-GO95HV-1^06241005.0118606 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2027-01-26 | 3
79528898-24502-DETAIL-01_27_2022-SVCDEFLC-1^06241005.0119000 | OTHER | CA-TIER-3 | Distribution | 2022-01-27 | 2025-01-27 | 2
357126904-68512-DETAIL-01_26_2022-SVCROAD-1^06241005.0119301 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
861816214-70812-DETAIL-01_26_2022-GO95MLD-1^06241005.0119309 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
759058724-83362-DETAIL-05_25_2022-GO95STUB-1^06242005.0362042 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
878722170-55332-DETAIL-05_26_2022-GO95MLD-1^06242005.0362102 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
957758860-86922-DETAIL-05_26_2022-GO95MLD-1^06242005.0362103 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
433234519-95722-DETAIL-05_25_2022-GO95SVC-1^06242005.0362105 | OTHER | CA-TIER-2 | Distribution | 2022-05-25 | 2025-05-25 | 2
107656724-15362-DETAIL-05_26_2022-GO95MLD-1^06242005.0362241 | OTHER | CA-TIER-2 | Distribution | 2022-05-26 | 2025-05-26 | 2
718277159-95412-DETAIL-05_19_2022-GRDRODHI-1^06242005.0363202 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2025-05-19 | 2
940765396-65972-DETAIL-05_19_2022-GO95TCH-1^06242005.0367500 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2025-05-19 | 2
899826726-77262-DETAIL-05_23_2022-GO95MLD-1^06242005.0368500 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
667351526-78162-DETAIL-05_19_2022-GO95TCH-1^06242005.0368503 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2025-05-19 | 2
829847215-61714-DETAIL-05_23_2022-SVCRUBLG-1^06242005.0368641 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
769781196-44462-DETAIL-05_23_2022-ANCHIDLE-1^06242005.0369600 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
712816766-93852-DETAIL-05_23_2022-SVCWIND-1^06242005.0369601 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
30131388-40489-DETAIL-04_08_2021-GO95MLD-1^06241009.0326902 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2026-04-08 | 3
763855318-96019-DETAIL-04_12_2021-GO95MLD-1^06241009.0327000 | OTHER | CA-TIER-2 | Distribution | 2021-04-12 | 2026-04-12 | 3
814343914-88019-DETAIL-04_08_2021-GO95MLD-1^06241009.0327802 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2026-04-08 | 3
535917768-99019-DETAIL-04_08_2021-GO95HV-1^06241009.0327901 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2026-04-08 | 3
181056073-76073-DETAIL-05_05_2022-GO95MLD-1^06241005.0136702 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
605768356-34371-DETAIL-05_11_2022-GO95MLD-1^06241005.0149500 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
253920786-48471-DETAIL-05_11_2022-GO95GUYP-1^06241005.0149501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
253920786-48471-DETAIL-05_11_2022-GO95GUYP-2^06241005.0149501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
765639029-11871-DETAIL-01_11_2022-GO95HV-1^06241005.0152402 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2027-01-11 | 3
683816880-73801-DETAIL-01_11_2022-GO95HV-1^06241005.0153102 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2027-01-11 | 3
179751535-78932-DETAIL-05_18_2022-GO95MLD-1^06241005.0027006 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
999392676-4742-DETAIL-05_11_2022-GO95HV-1^06241005.0029206 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
799408620-43852-DETAIL-05_10_2022-GRDBROKE-1^06241005.0029340 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
674230744-1132-DETAIL-05_10_2022-ENCHRW-1^06241005.0029403 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
674230744-1132-DETAIL-05_10_2022-GO95HV-1^06241005.0029403 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
725543522-62741-DETAIL-05_03_2022-GO95MLD-1^06241005.0029602 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
924418734-44651-DETAIL-05_03_2022-RISEGRD-1^06241005.0029604 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
518508479-42391-DETAIL-06_01_2022-GO95HV-1^06241005.0031700 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
956455860-51901-DETAIL-06_02_2022-GO95MLD-1^06241005.0031701 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
187016518-25752-DETAIL-05_18_2022-GO95MLD-1^06241005.0027007 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
283639344-70522-DETAIL-05_18_2022-GO95MLD-1^06241005.0027008 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
493926755-22532-DETAIL-05_18_2022-GO95HV-1^06241005.0027011 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
410888024-39779-DETAIL-02_15_2021-SVCROAD-1^06242009.0028401 | OTHER | CA-NON-TIER | Distribution | 2021-02-15 | 2024-02-15 | 2
624987804-67319-DETAIL-02_10_2021-GO95TCH-1^06242009.0028802 | OTHER | CA-TIER-2 | Distribution | 2021-02-10 | 2024-02-10 | 2
707256704-46519-DETAIL-02_17_2021-GO95HV-1^06242009.0029204 | OTHER | CA-TIER-2 | Distribution | 2021-02-17 | 2026-02-17 | 3
528662539-63289-DETAIL-02_09_2021-GO95MLD-1^06242009.0044100 | OTHER | CA-NON-TIER | Distribution | 2021-02-09 | 2024-02-09 | 2
304499635-91219-DETAIL-02_03_2021-GO95MLD-1^06242009.0050100 | OTHER | CA-TIER-2 | Distribution | 2021-02-03 | 2026-02-03 | 3
789973046-22299-DETAIL-04_08_2021-GO95TCH-1^06241009.0326607 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
789973046-22299-DETAIL-04_08_2021-GRDRODHI-2^06241009.0326607 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
93700345-57432-DETAIL-05_18_2022-SVCWIND-1^06241005.0028100 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
688463486-31742-DETAIL-05_11_2022-GO95HV-1^06241005.0028104 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
688463486-31742-DETAIL-05_11_2022-GO95MLD-1^06241005.0028104 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
75247744-80232-DETAIL-05_18_2022-GUYHINS-1^06241005.0028105 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
660599190-13861-DETAIL-06_06_2022-GO95MLD-1^06241005.0099300 | OTHER | CA-TIER-2 | Distribution | 2022-06-06 | 2025-06-06 | 2
474822851-81011-DETAIL-06_07_2022-GO95MLD-1^06241005.0109701 | OTHER | CA-TIER-2 | Distribution | 2022-06-07 | 2025-06-07 | 2
245127244-51371-DETAIL-01_20_2022-GO95BLTC-1^06241005.0114500 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2027-01-20 | 3
245127244-51371-DETAIL-01_20_2022-GUYHINS-1^06241005.0114500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
759107313-78014-DETAIL-01_27_2022-SVCROAD-1^06241005.0115602 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
922508313-91434-DETAIL-01_27_2022-SVCENTCO-1^06241005.0115604 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
273082443-87514-DETAIL-01_13_2022-GO95MLD-1^06241005.0115605 | OTHER | CA-TIER-2 | Distribution | 2022-01-13 | 2025-01-13 | 2
497641172-55604-DETAIL-01_27_2022-GUYHINS-1^06241005.0115701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
103858313-62354-DETAIL-01_27_2022-GO95BLTC-1^06241005.0115702 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2027-01-27 | 3
435249654-66471-DETAIL-01_27_2022-GO95BLTC-1^06241005.0114600 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2027-01-27 | 3
739840443-78664-DETAIL-01_27_2022-GUYHINS-1^06241005.0115501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
741854603-32541-DETAIL-05_05_2022-GUYHINS-1^06241005.0134102 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
941221029-68503-DETAIL-05_05_2022-GO95MLD-1^06241005.0135600 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
795415129-61172-DETAIL-05_05_2022-GO95TCH-1^06241005.0136601 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
503625249-6781-DETAIL-05_05_2022-GUYHINS-1^06241005.0136700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
815857073-87073-DETAIL-05_05_2022-GUYHINS-1^06241005.0136703 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
715104427-94618-DETAIL-01_13_2022-ABNDEQPM-1^06241005.0150700 | OTHER | CA-TIER-3 | Distribution | 2022-01-13 | 2027-01-13 | 3
41632359-33271-DETAIL-01_27_2022-GO95MLD-1^06241005.0152600 | OTHER | CA-TIER-3 | Distribution | 2022-01-27 | 2025-01-27 | 2
513193819-31471-DETAIL-01_27_2022-GO95MLD-1^06241005.0152701 | OTHER | CA-TIER-3 | Distribution | 2022-01-27 | 2025-01-27 | 2
701618809-57281-DETAIL-01_26_2022-GO95MLD-1^06241005.0153100 | OTHER | CA-TIER-3 | Distribution | 2022-01-26 | 2025-01-26 | 2
866578990-85001-DETAIL-01_11_2022-GO95MLD-1^06241005.0153101 | OTHER | CA-TIER-3 | Distribution | 2022-01-11 | 2027-01-11 | 3
739255820-49211-DETAIL-01_10_2022-GO95HV-1^06241005.0156400 | OTHER | CA-TIER-3 | Distribution | 2022-01-10 | 2027-01-10 | 3
87862184-44532-DETAIL-05_16_2022-GO95MLD-1^06241005.0028310 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
822363586-48042-DETAIL-05_19_2022-ENCHRW-1^06241005.0028400 | OTHER | CA-TIER-2 | Distribution | 2022-05-19 | 2025-05-19 | 2
277013105-92732-DETAIL-05_18_2022-SVCWIND-1^06241005.0026004 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
535236715-11832-DETAIL-05_18_2022-ENCHRW-1^06241005.0026005 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
535236715-11832-DETAIL-05_18_2022-GO95MLD-1^06241005.0026005 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
233167026-35442-DETAIL-05_18_2022-GO95MLD-1^06241005.0026101 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
711104525-33932-DETAIL-05_18_2022-GO95MLD-1^06241005.0026105 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
775261684-9222-DETAIL-05_17_2022-ABNDEQPM-1^06241005.0026204 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
174107234-65922-DETAIL-05_17_2022-GRDRODHI-1^06241005.0026301 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
178988704-78822-DETAIL-05_17_2022-SVCWIND-1^06241005.0026305 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
192702366-95842-DETAIL-05_16_2022-ENCHRW-1^06241005.0028402 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
747817585-25532-DETAIL-05_10_2022-GO95TCH-1^06241005.0028404 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
244106715-86032-DETAIL-05_16_2022-GUYHINS-1^06241005.0028406 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
208796080-8352-DETAIL-05_10_2022-GO95HV-1^06241005.0028440 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
208796080-8352-DETAIL-05_10_2022-GO95MLD-1^06241005.0028440 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
69706870-96352-DETAIL-05_10_2022-GO95MLD-1^06241005.0028441 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
112637070-16352-DETAIL-05_10_2022-GO95BLTC-1^06241005.0028442 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
112637070-16352-DETAIL-05_10_2022-GO95TCH-1^06241005.0028442 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
756059522-52241-DETAIL-05_12_2022-GUYHINS-1^06241005.0028903 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
379534264-2889-DETAIL-05_11_2022-SVCWIND-1^06241005.0029107 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
36629314-50422-DETAIL-05_11_2022-GO95MLD-1^06241005.0029109 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
13281114-17922-DETAIL-05_11_2022-GO95MLD-1^06241005.0029110 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
13281114-17922-DETAIL-05_11_2022-SVCWIND-1^06241005.0029110 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
826575110-19752-DETAIL-05_10_2022-GO95HV-1^06241005.0029341 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
646669294-87219-DETAIL-02_02_2021-GO95MLD-1^06242009.0057201 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
580138634-27219-DETAIL-02_02_2021-GO95HV-1^06242009.0057302 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
624595155-12219-DETAIL-02_02_2021-GO95TCH-1^06242009.0058400 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
34819244-38219-DETAIL-02_02_2021-ABNDEQPM-1^06242009.0058703 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
328615814-13219-DETAIL-02_02_2021-GO95MLD-1^06242009.0059203 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
497233915-72219-DETAIL-02_02_2021-GO95MLD-1^06242009.0059204 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
151904464-34361-DTLSB-07_19_2022-GO95HV-1^06242005.0146500 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
421127934-4061-DTLSB-07_19_2022-ABNDEQPM-1^06242005.0146801 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
199011024-31361-DTLSB-07_25_2022-GO95HV-1^06242005.0149000 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2027-07-25 | 3
199011024-31361-DTLSB-07_25_2022-GO95MLD-1^06242005.0149000 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2025-07-25 | 2
113668216-69889-DETAIL-04_08_2021-SVCSVC-1^06241009.0326702 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
430600658-45899-DETAIL-04_08_2021-GO95MLD-1^06241009.0326900 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
430600658-45899-DETAIL-04_08_2021-GRDRODHI-1^06241009.0326900 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
971239044-50144-DETAIL-04_08_2021-GO95MLD-1^06241009.0326903 | OTHER | CA-TIER-2 | Distribution | 2021-04-08 | 2024-04-08 | 2
858184619-39491-DTLSB-08_02_2022-GRDBROKE-1^06242004.0190101 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
950474609-81681-DTLSB-08_03_2022-GRDRODHI-1^06242004.0192300 | OTHER | CA-TIER-2 | Distribution | 2022-08-03 | 2025-08-03 | 2
56909367-90467-DTLSB-08_02_2022-GO95MLD-1^06242004.0193300 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
389320411-51611-DTLSB-08_01_2022-GRDRODHI-2^06242004.0193642 | OTHER | CA-TIER-2 | Distribution | 2022-08-01 | 2025-08-01 | 2
814528889-69391-DTLSB-08_02_2022-GO95TCH-1^06242004.0194301 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
929149783-12441-DETAIL-05_23_2022-GO95MLD-1^06242004.0310802 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
459918801-96030-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0177702 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
892073333-53890-DETAIL-03_23_2023-GUYNOINS-1^06240004.0178200 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
892073333-53890-DETAIL-03_23_2023-GUYNOINS-2^06240004.0178200 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
370809073-24390-DETAIL-03_23_2023-GO95MLD-1^06240004.0178303 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
874852711-45330-DETAIL-04_17_2023-GO95HV-1^06240004.0178900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
306383463-6190-DETAIL-03_23_2023-GO95TCH-1^06240004.0179201 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
91761335-36275-DETAIL-03_23_2023-GO95HV-1^06240004.0179203 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2028-03-23 | 3
901061021-49530-DETAIL-01_26_2023-GRDRODHI-1^06240004.0186341 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2026-01-26 | 2
265631291-95730-DETAIL-01_25_2023-GO95MLD-1^06240004.0186900 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2026-01-25 | 2
154183401-61530-DETAIL-01_23_2023-GO95MLD-1^06240004.0187340 | OTHER | CA-TIER-3 | Distribution | 2023-01-23 | 2026-01-23 | 2
160431861-82730-DETAIL-01_25_2023-GO95HV-1^06240004.0187701 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2028-01-25 | 3
178953321-31330-DETAIL-01_26_2023-GO95HV-1^06240004.0188441 | OTHER | CA-TIER-2 | Distribution | 2023-01-26 | 2028-01-26 | 3
297954124-36932-DETAIL-05_18_2022-GO95MLD-1^06241005.0027013 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
297954124-36932-DETAIL-05_18_2022-GRDRODHI-1^06241005.0027013 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
337797595-66632-DETAIL-05_18_2022-GO95MLD-1^06241005.0027015 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
706984529-45452-DETAIL-05_16_2022-GO95MLD-1^06241005.0027141 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
528411029-42452-DETAIL-05_16_2022-GO95CLSV-1^06241005.0027142 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
330998460-18801-DETAIL-06_02_2022-GO95MLD-1^06241005.0031703 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
277081250-57701-DETAIL-06_02_2022-GO95MLD-1^06241005.0031704 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
56894049-87291-DETAIL-06_01_2022-RISEGRD-1^06241005.0034701 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
876040808-21613-DETAIL-06_01_2022-GO95MLD-1^06241005.0034702 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
876040808-21613-DETAIL-06_01_2022-RISEGRD-1^06241005.0034702 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
794690014-79241-DETAIL-06_02_2022-GO95MLD-1^06241005.0037900 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
822072033-27721-DETAIL-06_02_2022-GO95TCH-1^06241005.0059101 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
419291821-86180-DETAIL-04_11_2023-GO95MLD-1^06240004.0169404 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
419291821-86180-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0169404 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
419291821-86180-DETAIL-04_11_2023-SVCENTCO-1^06240004.0169404 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
953919851-80280-DETAIL-04_11_2023-SVCENTCO-1^06240004.0169408 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
918712298-37070-DETAIL-03_28_2023-GO95MLD-1^06240004.0169504 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
602295238-46670-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0169506 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
835770848-48670-DETAIL-03_28_2023-SVCENTCO-1^06240004.0169507 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
508246828-55670-DETAIL-03_28_2023-GO95MLD-1^06240004.0169509 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
145701299-56370-DETAIL-03_28_2023-GUYNOINS-2^06240004.0169543 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
398134749-75470-DETAIL-03_28_2023-GO95MLD-1^06240004.0169640 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
764157138-74470-DETAIL-03_28_2023-GO95MLD-1^06240004.0169700 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
864951588-91569-DETAIL-03_28_2023-GO95HV-1^06240004.0169800 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
360854809-63231-DETAIL-06_01_2022-GUYNOINS-1^06241005.0092204 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
388616729-25221-DETAIL-06_01_2022-GO95MLD-1^06241005.0092205 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
901648069-91251-DETAIL-06_01_2022-GO95BLTC-1^06241005.0092300 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
901648069-91251-DETAIL-06_01_2022-GUYHINS-1^06241005.0092300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
210475519-48431-DETAIL-06_01_2022-GO95BLTC-1^06241005.0092303 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
91607229-65121-DETAIL-06_01_2022-GO95BLTC-1^06241005.0092400 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
148821319-53021-DETAIL-06_01_2022-GO95BLTC-1^06241005.0092501 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
504776689-21841-DETAIL-06_02_2022-GO95MLD-1^06241005.0092901 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
249933269-98751-DETAIL-06_02_2022-GO95HV-1^06241005.0092903 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2027-06-02 | 3
942145549-94631-DETAIL-06_01_2022-GUYHINS-1^06241005.0093001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-01 | 2025-06-01 | 2
734976650-87471-DETAIL-06_01_2022-GO95BLTC-1^06241005.0093300 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
372801848-49961-DETAIL-06_03_2022-GO95HV-1^06241005.0100002 | OTHER | CA-TIER-2 | Distribution | 2022-06-03 | 2027-06-03 | 3
987169941-99711-DETAIL-06_07_2022-GO95MLD-1^06241005.0109700 | OTHER | CA-TIER-2 | Distribution | 2022-06-07 | 2025-06-07 | 2
5465273-56390-DETAIL-03_23_2023-ABNDEQPM-1^06240004.0176401 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2028-03-23 | 3
355280151-71230-DETAIL-04_17_2023-GO95MLD-1^06240004.0176502 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
329537631-67130-DETAIL-04_17_2023-GO95MLD-1^06240004.0176601 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
500768921-85130-DETAIL-04_17_2023-GO95HV-1^06240004.0176701 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
90946875-39875-DETAIL-04_17_2023-GO95BLTC-1^06240004.0176803 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
657765011-79030-DETAIL-04_17_2023-GO95MLD-1^06240004.0176900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
657765011-79030-DETAIL-04_17_2023-SVCDEFLC-1^06240004.0176900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
836614210-12730-DETAIL-04_17_2023-GRDRODHI-1^06240004.0176941 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
818288573-29980-DETAIL-04_20_2023-GO95MLD-1^06240004.0177200 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
227533257-53257-DETAIL-04_20_2023-GRDRODHI-1^06240004.0177202 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
459658880-69930-DETAIL-04_19_2023-GO95BLTC-1^06240004.0177701 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
459658880-69930-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0177701 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
60624094-21251-DTLSB-07_25_2022-GO95STUB-1^06242005.0146001 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2025-07-25 | 2
151904464-34361-DTLSB-07_19_2022-GO95MLD-1^06242005.0146500 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
559212444-26061-DTLSB-07_19_2022-ABNDEQPM-1^06242005.0146800 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
421127934-4061-DTLSB-07_19_2022-GO95MLD-1^06242005.0146801 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
721719144-80751-DTLSB-07_25_2022-GO95MLD-1^06242005.0148200 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2025-07-25 | 2
133571063-70151-DTLSB-07_25_2022-ABNDEQPM-1^06242005.0159000 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2027-07-25 | 3
710454894-23251-DTLSB-08_02_2022-GO95MLD-1^06242005.0177101 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
846294603-45451-DTLSB-08_02_2022-GO95HV-1^06242005.0177201 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2027-08-02 | 3
448125554-7851-DTLSB-07_26_2022-GO95MLD-1^06242005.0178000 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2025-07-26 | 2
896754334-90751-DTLSB-07_26_2022-GO95MLD-1^06242005.0178001 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2025-07-26 | 2
110517054-13851-DTLSB-07_26_2022-GO95STUB-1^06242005.0178002 | OTHER | CA-TIER-2 | Distribution | 2022-07-26 | 2025-07-26 | 2
915196224-27855-DTLSB-08_02_2022-GO95MLD-1^06242005.0178500 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
979309036-56119-ADMIN-07_19_2023-POLEREPL-1^06240009.0134100 | POLE | CA-NON-TIER | Distribution | 2023-07-19 | 2026-07-19 | 2
568010526-39279-DETAIL-09_08_2021-GO95MLD-1^06240009.0149001 | OTHER | CA-NON-TIER | Distribution | 2021-09-08 | 2026-09-08 | 3
568010526-39279-DETAIL-04_04_2022-POLETOP-1^06240009.0149001 | POLE | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
568010526-39279-DETAIL-04_04_2022-XARMSPCR-1^06240009.0149001 | CROSSARM | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
79638843-60580-DTLSB-05_13_2021-GO95MLD-1^06241003.0329100 | OTHER | CA-TIER-2 | Distribution | 2021-05-13 | 2024-05-13 | 2
156130343-22751-DETAIL-02_08_2022-GO95HV-1^06241004.0180000 | OTHER | CA-TIER-2 | Distribution | 2022-02-08 | 2027-02-08 | 3
15279803-35941-DETAIL-02_08_2022-GO95BLTC-1^06241004.0181101 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
136538972-94031-DETAIL-02_08_2022-GO95GUYP-1^06241004.0181102 | ANCHOR/GUY | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
136538972-94031-DETAIL-02_08_2022-GO95GUYP-2^06241004.0181102 | ANCHOR/GUY | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
104323982-17031-DETAIL-02_08_2022-GO95BLTC-1^06241004.0181200 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2027-02-08 | 3
430890524-96931-DETAIL-05_09_2022-GO95MLD-1^06241005.0012606 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
193960266-77271-DETAIL-05_09_2022-GO95MLD-1^06241005.0012641 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
790235282-1880-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168000 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
790235282-1880-DETAIL-04_10_2023-SVCDEFLC-2^06240004.0168000 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
470835171-14380-DETAIL-03_27_2023-GO95TCH-1^06240004.0168044 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
203273870-33970-DETAIL-04_11_2023-GO95TCH-1^06240004.0169407 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
953919851-80280-DETAIL-04_11_2023-GO95MLD-1^06240004.0169408 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
901375451-59180-DETAIL-04_11_2023-SVCWIND-1^06240004.0169409 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
476316491-64480-DETAIL-04_11_2023-GO95MLD-1^06240004.0169411 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
244774768-22570-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0169500 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
989651188-85070-DETAIL-03_28_2023-GO95MLD-1^06240004.0169502 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
343252448-96670-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0169503 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
657407392-87080-DETAIL-01_25_2023-SVCDEFLC-1^06240005.0015000 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2026-01-25 | 2
229078143-12180-DETAIL-01_25_2023-RISEGRD-1^06240005.0016201 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
49172771-61963-DETAIL-01_25_2023-SVCDEFLC-1^06240005.0128900 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
28667661-82263-DETAIL-01_25_2023-SVCDEFLC-1^06240005.0128902 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
95960671-73263-DETAIL-01_24_2023-SVCDEFLC-1^06240005.0129900 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
912836682-40519-DETAIL-08_11_2021-XARMSPCR-1^06240008.0131800 | CROSSARM | CA-NON-TIER | Distribution | 2021-08-11 | 2024-08-11 | 2
261639383-30419-DETAIL-09_07_2021-XARMSPCR-1^06240008.0219801 | CROSSARM | CA-NON-TIER | Distribution | 2021-09-07 | 2024-09-07 | 2
232342204-64579-DETAIL-09_01_2021-ENCHRW-1^06240008.0298500 | OTHER | CA-NON-TIER | Distribution | 2021-09-01 | 2024-09-01 | 2
446876554-91619-DETAIL-08_31_2021-POLETOP-1^06240009.0012900 | POLE | CA-NON-TIER | Distribution | 2021-08-31 | 2024-08-31 | 2
383171044-90099-ADMIN-07_20_2023-POLEREPL-1^06240009.0029900 | POLE | CA-NON-TIER | Distribution | 2023-07-20 | 2026-07-20 | 2
325428740-72532-DETAIL-01_10_2022-GO95MLD-1^06241005.0117705 | OTHER | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
697969590-43532-DETAIL-01_10_2022-POLESTEP-1^06241005.0117709 | POLE | CA-TIER-2 | Distribution | 2022-01-10 | 2025-01-10 | 2
699996784-52212-DETAIL-01_26_2022-GO95MLD-1^06241005.0118301 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
699996784-52212-DETAIL-01_26_2022-RISEGRD-1^06241005.0118301 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
699996784-52212-DETAIL-01_26_2022-SVCROAD-1^06241005.0118301 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
95792214-8912-DETAIL-01_26_2022-GO95MLD-1^06241005.0118303 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
95792214-8912-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0118303 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
209565014-14222-DETAIL-01_26_2022-GO95MLD-1^06241005.0118305 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
209565014-14222-DETAIL-01_26_2022-SVCROAD-1^06241005.0118305 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
563908773-38773-DETAIL-01_26_2022-SVCDEFLC-1^06241005.0118306 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
282485493-11030-DETAIL-05_03_2023-GO95CLSV-1^06241005.0254204 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
406591645-29830-DETAIL-04_27_2023-GRDRODHI-1^06241005.0254641 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
523970224-91930-DETAIL-05_03_2023-GO95MLD-1^06241005.0252140 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
207401714-78830-DETAIL-05_03_2023-GO95MLD-1^06241005.0252141 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
828854553-63130-DETAIL-05_03_2023-GO95MLD-1^06241005.0252400 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
328615103-17430-DETAIL-05_03_2023-GO95MLD-1^06241005.0252401 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
511755164-88230-DETAIL-05_03_2023-GUYNOINS-2^06241005.0252601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
231588113-83030-DETAIL-05_03_2023-GO95MLD-1^06241005.0253703 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
702913303-41030-DETAIL-05_03_2023-GO95MLD-1^06241005.0254200 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
17292064-48130-DETAIL-05_03_2023-GO95MLD-1^06241005.0254203 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
143939252-1529-DETAIL-01_27_2022-RISECLMB-1^06241005.0117610 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
587210352-87684-DETAIL-01_27_2022-GUYHINS-1^06241005.0117611 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
587210352-87684-DETAIL-01_27_2022-GUYHINS-2^06241005.0117611 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
587210352-87684-DETAIL-01_27_2022-GUYHINS-3^06241005.0117611 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
483407502-87452-DETAIL-01_13_2022-GO95MLD-1^06241005.0117640 | OTHER | CA-TIER-2 | Distribution | 2022-01-13 | 2025-01-13 | 2
761185093-95390-DETAIL-04_20_2023-POLETOP-1^06240004.0171300 | POLE | CA-TIER-2 | Distribution | 2023-04-20 | 2024-04-20 | 2
986284801-4230-DETAIL-04_20_2023-GO95HV-1^06240004.0171601 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
292315291-49430-DETAIL-04_19_2023-GO95MLD-1^06240004.0171801 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
776399661-9730-DETAIL-04_19_2023-SVCWIND-1^06240004.0171900 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
353174591-80530-DETAIL-04_19_2023-GO95MLD-1^06240004.0171902 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
681017803-70230-DETAIL-04_19_2023-GO95MLD-1^06240004.0171903 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
337217509-67509-DETAIL-04_19_2023-GO95MLD-1^06240004.0171904 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
918774504-55903-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0171941 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
750672031-38630-DETAIL-04_20_2023-GO95MLD-1^06240004.0172700 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
530856721-7630-DETAIL-04_20_2023-ABNDEQPM-1^06240004.0172702 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
739010701-50630-DETAIL-04_19_2023-RISEGRD-1^06240004.0172802 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
474067312-55211-DETAIL-05_09_2022-GO95MLD-1^06241005.0011502 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
343555001-72031-DETAIL-05_18_2022-GO95HV-1^06241005.0023101 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
748194031-66331-DETAIL-05_18_2022-GO95HV-1^06241005.0024101 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
321208391-88931-DETAIL-05_18_2022-GO95MLD-1^06241005.0024140 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
206197264-49232-DETAIL-05_18_2022-GO95MLD-1^06241005.0025102 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
690869596-30342-DETAIL-05_17_2022-GO95MLD-1^06241005.0025202 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
469130996-28242-DETAIL-05_17_2022-GO95MLD-1^06241005.0025203 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
221689163-64851-DETAIL-05_12_2022-GO95HV-1^06241005.0025500 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
535236715-11832-DETAIL-05_18_2022-GO95HV-1^06241005.0026005 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
474067312-55211-DETAIL-05_09_2022-GO95TCH-1^06241005.0011502 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
54776225-54351-DETAIL-05_09_2022-GO95HV-1^06241005.0011541 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
309024766-84571-DETAIL-05_09_2022-GO95MLD-1^06241005.0011641 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
521844420-11470-DETAIL-03_27_2023-GO95MLD-1^06240004.0167104 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
294624151-5180-DETAIL-03_27_2023-POLETOP-1^06240004.0167144 | POLE | CA-TIER-2 | Distribution | 2023-03-27 | 2024-03-27 | 2
278932831-54080-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0167200 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
278932831-54080-DETAIL-03_22_2023-SVCWIND-1^06240004.0167200 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
102877192-21880-DETAIL-03_27_2023-GO95MLD-1^06240004.0167209 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
858338512-75780-DETAIL-03_22_2023-GO95MLD-1^06240004.0167240 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
920451008-74670-DETAIL-04_17_2023-SVCDEFLC-1^06240004.0165703 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
897459310-8070-DETAIL-03_29_2023-SVCDEFLC-2^06240004.0165707 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
219342309-2270-DETAIL-03_29_2023-SVCWIND-1^06240004.0165740 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
219342309-2270-AUDIT-05_22_2023-SVCROAD-1^06240004.0165740 | OTHER | CA-TIER-2 | Distribution | 2023-05-22 | 2026-05-22 | 2
661292529-37270-DETAIL-03_29_2023-GO95MLD-1^06240004.0165744 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2028-03-29 | 3
290151339-78270-DETAIL-03_29_2023-GO95MLD-1^06240004.0165745 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
270068784-24499-DETAIL-04_19_2023-GO95MLD-1^06240004.0165748 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
270068784-24499-ENHANCED-07_27_2023-IRSPOTOH-1^06240004.0165748 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2024-07-27 | 2
639928567-73670-DETAIL-03_28_2023-GO95MLD-1^06240004.0165800 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
459384087-14670-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0165802 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
335068058-25970-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0165804 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
706177888-67570-DETAIL-04_17_2023-GUYHINS-1^06240004.0165805 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
270644919-16270-DETAIL-03_29_2023-POLESTEP-1^06240004.0165841 | POLE | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
573660998-59070-DETAIL-04_12_2023-GO95MLD-1^06240004.0165902 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
157921136-2661-DETAIL-05_09_2022-GO95MLD-1^06241005.0011643 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
381174364-78031-DETAIL-05_09_2022-POLESTEP-1^06241005.0011705 | POLE | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
907037805-37241-DETAIL-05_09_2022-SVCROOF-1^06241005.0011707 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
907037805-37241-DETAIL-05_09_2022-SVCWIND-1^06241005.0011707 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
878634914-54421-DETAIL-05_09_2022-GUYHINS-1^06241005.0012402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
413425840-77028-DETAIL-05_10_2022-GO95MLD-1^06241005.0012403 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
680107253-86128-DETAIL-05_10_2022-GO95MLD-1^06241005.0012405 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
448512093-27321-DETAIL-05_10_2022-SVCROAD-1^06241005.0012406 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
580020393-15321-DETAIL-05_10_2022-GO95MLD-1^06241005.0012407 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
439350454-57721-DETAIL-05_10_2022-GO95HV-1^06241005.0012409 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
426565206-79561-DETAIL-05_09_2022-GO95MLD-1^06241005.0012540 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
80555285-27851-DETAIL-05_09_2022-GUYHINS-1^06241005.0012544 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
763445544-3131-DETAIL-05_03_2022-GO95TCH-1^06241005.0012601 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
279709423-46680-DETAIL-03_22_2023-GO95MLD-1^06240004.0166203 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
112292551-35180-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0166301 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
949792741-12180-DETAIL-03_21_2023-CLMBHAZ-1^06240004.0166304 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
949792741-12180-DETAIL-03_21_2023-SVCROOF-1^06240004.0166304 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
536428272-83302-DETAIL-03_22_2023-GO95MLD-1^06240004.0166306 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
501080272-66880-DETAIL-03_28_2023-GO95MLD-1^06240004.0166400 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
884870580-42670-DETAIL-04_12_2023-GO95MLD-1^06240004.0166402 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
406857680-19770-DETAIL-04_12_2023-GO95HV-1^06240004.0166500 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
577396250-32870-DETAIL-04_12_2023-GO95STUB-1^06240004.0166504 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
71652830-93170-DETAIL-04_12_2023-GO95MLD-1^06240004.0166507 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
349021370-54870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166508 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
467960938-26343-DETAIL-04_12_2023-SVCROOF-1^06240004.0166509 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
233236181-49042-DETAIL-01_27_2022-GO95BLTC-1^06241005.0116500 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2027-01-27 | 3
214659072-79223-DETAIL-01_27_2022-SVCROAD-1^06241005.0116605 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
876095313-34494-DETAIL-01_20_2022-GUYHINS-1^06241005.0116608 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
898201172-64684-DETAIL-01_27_2022-GUYHINS-1^06241005.0116702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
898201172-64684-DETAIL-01_27_2022-GUYHINS-2^06241005.0116702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
395177332-72203-DETAIL-01_27_2022-SVCROAD-1^06241005.0117606 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
516383780-86432-DETAIL-01_27_2022-GO95BLTC-1^06241005.0117607 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2027-01-27 | 3
837523159-41552-DETAIL-05_18_2022-GO95MLD-1^06241005.0028142 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
190609539-53952-DETAIL-05_18_2022-GO95TCH-1^06241005.0028143 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
606301860-15352-DETAIL-05_16_2022-GO95CL10-1^06241005.0028145 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
606301860-15352-DETAIL-05_16_2022-POLESTEP-1^06241005.0028145 | POLE | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
777907979-55352-DETAIL-05_16_2022-GUYHINS-1^06241005.0028147 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
300040359-81352-DETAIL-05_16_2022-GO95TCH-1^06241005.0028149 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
411981968-5270-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0168400 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
427006608-64770-DETAIL-04_11_2023-GO95HV-1^06240004.0168403 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2028-04-11 | 3
198012122-62880-DETAIL-04_11_2023-GO95MLD-1^06240004.0168405 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
880259410-78370-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0168406 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
816303449-5570-DETAIL-04_10_2023-SVCWIND-1^06240004.0168407 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
649895841-52880-DETAIL-04_11_2023-GO95MLD-1^06240004.0168413 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
275009669-76470-DETAIL-04_11_2023-GO95MLD-1^06240004.0168414 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
328193518-46370-DETAIL-04_13_2023-SVCDEFLC-1^06240004.0168502 | OTHER | CA-TIER-2 | Distribution | 2023-04-13 | 2026-04-13 | 2
545172148-81270-DETAIL-04_11_2023-GUYNOINS-1^06240004.0168507 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
653037698-70770-DETAIL-04_11_2023-SVCWIND-1^06240004.0168509 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
980450708-81670-DETAIL-03_28_2023-GO95MLD-1^06240004.0168902 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
64472204-71259-DETAIL-04_12_2023-GO95HV-1^06240004.0166601 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
64472204-71259-DETAIL-04_12_2023-SVCENTCO-1^06240004.0166601 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
259645324-66324-DETAIL-04_12_2023-GO95HV-1^06240004.0166610 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
29261841-49280-DETAIL-04_17_2023-GO95MLD-1^06240004.0166641 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
29261841-49280-DETAIL-04_17_2023-GUYHINS-1^06240004.0166641 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
401781783-6550-DETAIL-04_17_2023-RISEGRD-1^06240004.0166642 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
288969418-94670-DETAIL-04_17_2023-GO95MLD-1^06240004.0166700 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
777300119-20465-DETAIL-04_12_2023-GO95MLD-1^06240004.0166701 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
62426070-74270-DETAIL-04_12_2023-GO95MLD-1^06240004.0166703 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
164918120-40870-DETAIL-04_12_2023-GO95BLTC-1^06240004.0166704 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
164918120-40870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166704 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
40626528-59870-DETAIL-03_29_2023-GO95MLD-1^06240004.0166900 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
864951588-91569-DETAIL-03_28_2023-GO95MLD-1^06240004.0169800 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
996126361-23430-DETAIL-04_20_2023-GO95MLD-1^06240004.0170602 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
661655811-24630-DETAIL-04_20_2023-GO95MLD-1^06240004.0170701 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
824898221-23030-DETAIL-04_19_2023-GO95MLD-1^06240004.0170900 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
761185093-95390-DETAIL-04_20_2023-INSULDMG-2^06240004.0171300 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2023-04-20 | 2024-04-20 | 2
99765261-50430-DETAIL-04_20_2023-GO95HV-1^06240004.0171600 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
559833491-28530-DETAIL-04_19_2023-GO95TCH-1^06240004.0171901 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
500413643-86330-DETAIL-04_19_2023-GO95MLD-1^06240004.0171940 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
918774504-55903-DETAIL-04_19_2023-GO95MLD-1^06240004.0171941 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
91761335-36275-DETAIL-03_23_2023-GO95MLD-1^06240004.0179203 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
642095181-75430-DETAIL-01_25_2023-GO95HV-1^06240004.0184641 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2028-01-25 | 3
901061021-49530-DETAIL-01_26_2023-GO95MLD-1^06240004.0186341 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2026-01-26 | 2
943946698-37570-DETAIL-04_19_2023-GO95HV-2^06240004.0164405 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
247337193-30080-DETAIL-04_19_2023-GO95MLD-1^06240004.0164500 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
171905963-1380-DETAIL-04_19_2023-GO95HV-1^06240004.0164503 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
239845283-34680-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0164506 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
18413323-6480-DETAIL-03_23_2023-GO95MLD-1^06240004.0164600 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
782675398-24750-DETAIL-03_29_2023-GO95MLD-1^06240004.0164740 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
952795588-25550-DETAIL-03_29_2023-POLESTEP-1^06240004.0164844 | POLE | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
524219883-56680-DETAIL-03_22_2023-GO95MLD-1^06240004.0165300 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
524219883-56680-DETAIL-03_22_2023-RISEGRD-1^06240004.0165300 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
680039673-73380-DETAIL-04_19_2023-GO95MLD-1^06240004.0165401 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
680039673-73380-DETAIL-04_19_2023-RISEGRD-1^06240004.0165401 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
506063273-61380-DETAIL-04_19_2023-GO95MLD-1^06240004.0165403 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
913258219-12570-DETAIL-04_10_2023-GO95MLD-1^06240004.0169203 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
239632110-86070-DETAIL-04_10_2023-GO95MLD-1^06240004.0169207 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
715308961-20061-DETAIL-04_11_2023-GO95MLD-1^06240004.0169310 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
648151361-87680-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0169402 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
648151361-87680-DETAIL-04_11_2023-SVCWIND-1^06240004.0169402 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
360691820-76870-DETAIL-04_11_2023-SVCWIND-1^06240004.0169403 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
360691820-76870-AUDIT-05_22_2023-SVCDEFLC-1^06240004.0169403 | OTHER | CA-TIER-2 | Distribution | 2023-05-22 | 2026-05-22 | 2
31297210-39370-DETAIL-04_11_2023-RISEGRD-1^06240004.0169406 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
657392968-41570-DETAIL-03_28_2023-GO95MLD-1^06240004.0167802 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
406204828-10770-DETAIL-03_28_2023-GO95MLD-1^06240004.0167804 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
56243918-93670-DETAIL-04_12_2023-GO95HV-2^06240004.0167900 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
153792948-43970-DETAIL-03_28_2023-GO95MLD-1^06240004.0167901 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
151288024-16641-DETAIL-05_03_2022-GO95MLD-1^06241005.0012802 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
761931125-27941-DETAIL-05_04_2022-GO95MLD-1^06241005.0012841 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
814451734-95621-DETAIL-05_09_2022-GO95MLD-1^06241005.0013402 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
814451734-95621-DETAIL-05_09_2022-GUYHINS-1^06241005.0013402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
120846945-44451-DETAIL-05_03_2022-GO95MLD-1^06241005.0013500 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
823275746-94971-ADMIN-11_03_2023-ANCPUCO-1^06241005.0013503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-11-03 | 2024-11-03 | 2
740398465-55661-DETAIL-05_03_2022-GO95MLD-1^06241005.0013505 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
733312146-55871-DETAIL-05_03_2022-GO95MLD-1^06241005.0013540 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
848725314-66831-DETAIL-05_09_2022-GO95MLD-1^06241005.0013608 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
860596378-64798-DETAIL-05_10_2022-SVCWIND-1^06241005.0013620 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
964306105-66941-DETAIL-05_03_2022-GUYLOINS-1^06241005.0013640 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
611126065-52341-DETAIL-05_03_2022-GO95HV-1^06241005.0013642 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2027-05-03 | 3
558945956-63940-DETAIL-01_17_2023-GO95MLD-1^06240004.0083201 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
235374876-54940-DETAIL-01_17_2023-GO95HV-1^06240004.0083203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
774677226-96840-ADMIN-09_11_2023-POLEDERP-1^06240004.0083300 | POLE | CA-TIER-2 | Distribution | 2023-09-11 | 2028-09-11 | 3
657875816-87540-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0083340 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
149138968-3130-DETAIL-01_19_2023-GO95TCH-1^06240004.0083501 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
53557939-95330-DETAIL-01_19_2023-GO95MLD-1^06240004.0083503 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
397234089-30330-DETAIL-01_19_2023-GO95MLD-1^06240004.0083600 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
697735889-53430-DETAIL-01_18_2023-SVCDEFLC-1^06240004.0083702 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
923675935-1040-DETAIL-01_18_2023-GO95MLD-1^06240004.0083800 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
125387048-78070-DETAIL-01_17_2023-GO95MLD-1^06240004.0084302 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
333016308-88030-DETAIL-01_18_2023-SVCDEFLC-1^06240004.0084601 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
792574918-22869-DETAIL-02_04_2021-SVCENTCO-1^06242009.0068500 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2024-02-04 | 2
637863778-31869-DETAIL-02_04_2021-GO95MLD-1^06242009.0068501 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
11520478-17019-DETAIL-02_04_2021-GO95MLD-1^06242009.0068601 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
790419438-74019-DETAIL-02_04_2021-GO95MLD-1^06242009.0069701 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
365736783-57119-ADMIN-03_02_2023-POLEREPL-1^06242009.0082001 | POLE | CA-TIER-2 | Distribution | 2023-03-02 | 2024-03-02 | 2
37718394-22161-DTLSB-07_27_2022-GO95MLD-1^06242005.0266903 | OTHER | CA-TIER-2 | Distribution | 2022-07-27 | 2025-07-27 | 2
937856261-23811-DTLSB-07_27_2022-GO95MLD-1^06242005.0268303 | OTHER | CA-TIER-2 | Distribution | 2022-07-27 | 2025-07-27 | 2
1723158-49913-DTLSB-07_21_2022-GO95MLD-1^06242005.0282600 | OTHER | CA-TIER-2 | Distribution | 2022-07-21 | 2025-07-21 | 2
660273109-50473-DETAIL-01_18_2023-SVCROOF-1^06240004.0092302 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
110469498-80050-DETAIL-01_16_2023-GO95MLD-1^06240004.0092505 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
229769878-73840-DETAIL-01_16_2023-GO95TCH-1^06240004.0092506 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
229769878-73840-DETAIL-01_16_2023-SVCDEFLC-2^06240004.0092506 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
880984038-38640-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0092540 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
587235888-89963-DETAIL-01_12_2023-GRDRODHI-1^06240004.0093200 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
605035639-96770-DETAIL-03_23_2023-SVCDEFLC-1^06240004.0161401 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
786122268-81570-DETAIL-03_23_2023-SVCDEFLC-1^06240004.0161402 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
27043288-44570-DETAIL-03_23_2023-GUYHINS-1^06240004.0161405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
518110264-90960-AUDIT-06_12_2023-RISEGRD-1^06240004.0161406 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
965901429-3770-DETAIL-04_20_2023-GRDRODHI-1^06240004.0162201 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
136389448-61470-DETAIL-03_23_2023-GRDRODHI-1^06240004.0160300 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
11298228-5370-DETAIL-03_23_2023-GO95MLD-1^06240004.0160302 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2028-03-23 | 3
780845423-45680-DETAIL-04_17_2023-GUYHINS-1^06240004.0160802 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
503050223-22680-DETAIL-04_17_2023-GO95HV-1^06240004.0160803 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
135071564-43564-DETAIL-04_17_2023-GO95MLD-1^06240004.0160900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
786122268-81570-DETAIL-03_23_2023-SVCDEFLC-2^06240004.0161402 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
786122268-81570-DETAIL-03_23_2023-SVCWIND-1^06240004.0161402 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
518110264-90960-DETAIL-03_23_2023-GO95MLD-1^06240004.0161406 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
965901429-3770-DETAIL-04_20_2023-GO95MLD-1^06240004.0162201 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
827050653-70653-DETAIL-03_27_2023-GO95BLTC-1^06240004.0162503 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
833084323-27180-DETAIL-03_21_2023-GO95TCH-1^06240004.0162601 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
710094148-40350-DETAIL-03_21_2023-GO95MLD-1^06240004.0162603 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
311394818-48970-DETAIL-01_23_2023-GO95MLD-1^06240004.0081202 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
357237728-33370-DETAIL-01_23_2023-GO95HV-1^06240004.0081204 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2028-01-23 | 3
433057508-10170-DETAIL-01_24_2023-GO95HV-1^06240004.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
433057508-10170-DETAIL-01_24_2023-GO95MLD-1^06240004.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
620919626-58740-DETAIL-01_19_2023-GO95MLD-1^06240004.0081440 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
252286748-79930-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081500 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
232323349-23173-DETAIL-01_12_2023-RISEGRD-1^06240004.0091001 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
57227839-68773-DETAIL-01_16_2023-GO95MLD-1^06240004.0091403 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
272102909-73173-DETAIL-01_16_2023-GO95MLD-1^06240004.0091502 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
272102909-73173-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0091502 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
820435704-65704-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0091503 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
605460208-81650-DETAIL-01_09_2023-SVCDEFLC-1^06240004.0097500 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
82643198-87550-DETAIL-01_09_2023-SVCDEFLC-1^06240004.0097505 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
761612948-91850-DETAIL-01_09_2023-ABNDEQPM-1^06240004.0097605 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2028-01-09 | 3
686710018-46830-DETAIL-01_11_2023-GO95MLD-2^06240004.0098003 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
342516373-22960-DETAIL-01_11_2023-GO95HV-1^06240004.0098144 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
342516373-22960-DETAIL-01_11_2023-GO95MLD-1^06240004.0098144 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
757940848-60830-DETAIL-01_10_2023-GO95TCH-1^06240004.0098206 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
244758524-19960-DETAIL-01_11_2023-SVCDEFLC-1^06240004.0098207 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
49601419-17670-DETAIL-04_19_2023-GO95MLD-1^06240004.0164401 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
34066709-95670-DETAIL-04_19_2023-GO95MLD-1^06240004.0164403 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
943946698-37570-DETAIL-04_19_2023-GO95HV-1^06240004.0164405 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
969189331-27280-DETAIL-03_22_2023-GO95TCH-1^06240004.0169006 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
900920211-24580-DETAIL-03_22_2023-GO95MLD-1^06240004.0169040 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
574879811-3580-DETAIL-03_22_2023-GO95BLTC-1^06240004.0169041 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
566153022-26780-DETAIL-04_10_2023-GO95TCH-1^06240004.0169042 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
566153022-26780-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0169042 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
566153022-26780-DETAIL-04_10_2023-SVCDEFLC-2^06240004.0169042 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
291317699-67699-DETAIL-04_10_2023-GUYHINS-1^06240004.0169046 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
635450440-8870-DETAIL-04_10_2023-GO95MLD-1^06240004.0169101 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
528405420-52470-DETAIL-03_27_2023-GO95MLD-1^06240004.0167105 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
670358610-69370-DETAIL-03_27_2023-GO95MLD-1^06240004.0167107 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
986931581-86380-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167141 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
566153022-26780-DETAIL-04_10_2023-GO95MLD-1^06240004.0169042 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
781552301-51580-DETAIL-04_10_2023-GO95MLD-1^06240004.0169043 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
241282521-79580-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0169044 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
753653689-84370-DETAIL-03_28_2023-GO95MLD-1^06240004.0169540 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
753653689-84370-DETAIL-03_28_2023-GO95TCH-1^06240004.0169540 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
145701299-56370-DETAIL-03_28_2023-GUYNOINS-1^06240004.0169543 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
77522768-41070-DETAIL-04_12_2023-SVCWIND-1^06240004.0169600 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
329220608-33170-DETAIL-03_28_2023-GO95HV-1^06240004.0169900 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
329220608-33170-DETAIL-03_28_2023-GO95MLD-1^06240004.0169900 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
924293921-55630-DETAIL-04_20_2023-GO95MLD-1^06240004.0170700 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
761185093-95390-DETAIL-04_20_2023-INSULDMG-1^06240004.0171300 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2023-04-20 | 2024-04-20 | 2
824885076-58870-DETAIL-11_15_2022-GO95TCH-1^06239004.0364300 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
355673936-9380-DETAIL-11_15_2022-GO95MLD-1^06239004.0364402 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
107037933-49921-DETAIL-11_14_2022-GO95MLD-1^06239004.0364702 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
302903703-37421-DETAIL-11_14_2022-GO95HV-1^06239004.0364705 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2027-11-14 | 3
686978587-88970-DETAIL-04_26_2023-ENCHRW-1^06240004.0064202 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
686978587-88970-DETAIL-04_26_2023-GO95MLD-1^06240004.0064202 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
544342143-94330-DETAIL-05_01_2023-GO95MLD-1^06240004.0064601 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
358966183-96930-DETAIL-04_25_2023-GO95MLD-1^06240004.0064700 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
358966183-96930-DETAIL-04_25_2023-SVCDEFLC-1^06240004.0064700 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
482738073-61930-DETAIL-04_25_2023-GO95MLD-1^06240004.0064702 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
643151903-92130-DETAIL-04_25_2023-GO95MLD-1^06240004.0064801 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
292285509-97419-DETAIL-04_25_2023-GO95MLD-1^06240004.0064803 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2028-04-25 | 3
956958429-74330-DETAIL-01_18_2023-GO95MLD-1^06240004.0084702 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
228960382-85370-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085102 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
959133402-37370-DETAIL-01_17_2023-GO95MLD-1^06240004.0085302 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
931107092-96370-DETAIL-01_17_2023-GO95MLD-1^06240004.0085303 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
145199605-45530-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085341 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
695928692-89370-DETAIL-01_18_2023-GO95MLD-1^06240004.0085401 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
227352128-97330-DETAIL-01_18_2023-GO95MLD-1^06240004.0085602 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
535443198-31730-DETAIL-01_18_2023-GO95HV-1^06240004.0085603 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2028-01-18 | 3
19099405-1530-DETAIL-01_17_2023-GO95HV-1^06240004.0086141 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
19099405-1530-DETAIL-01_17_2023-GO95MLD-1^06240004.0086141 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
892468185-73530-DETAIL-01_18_2023-SVCDEFLC-1^06240004.0086240 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
325843571-25601-DETAIL-01_25_2022-GO95CL10-1^06239004.0257440 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
699669484-82360-DETAIL-01_12_2022-GO95MLD-1^06239004.0257504 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
699669484-82360-DETAIL-01_12_2022-SVCENTCO-1^06239004.0257504 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
668837915-43370-DETAIL-01_24_2022-SVCENTCO-1^06239004.0257604 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
345925815-35870-DETAIL-01_24_2022-GO95MLD-1^06239004.0257606 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
179576951-72450-DETAIL-01_12_2022-GO95HV-1^06239004.0257607 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2027-01-12 | 3
143694-36860-DETAIL-01_12_2022-GO95MLD-1^06239004.0257608 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
563515646-65680-DETAIL-01_17_2022-GO95TCH-1^06239004.0257640 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
943693294-59460-ADMIN-09_19_2022-GO95MLD-1^06239004.0257704 | OTHER | CA-TIER-2 | Distribution | 2022-09-19 | 2025-09-19 | 2
186515406-42370-DETAIL-01_12_2022-GO95HV-1^06239004.0257803 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2027-01-12 | 3
186515406-42370-DETAIL-01_12_2022-GO95MLD-1^06239004.0257803 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
602030444-43860-DETAIL-01_12_2022-GO95TCH-1^06239004.0257806 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
745680919-57070-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0165901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
463618668-53870-DETAIL-04_12_2023-GO95MLD-1^06240004.0165906 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
636490870-79570-DETAIL-03_27_2023-GO95TCH-1^06240004.0166000 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
860010230-57870-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166100 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
338128505-93140-DETAIL-05_08_2023-GUYHINS-2^06240004.0102003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
279869075-20040-DETAIL-05_08_2023-SVCDEFLC-1^06240004.0103000 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
404055861-52480-DTLSB-05_03_2021-GO95MLD-1^06240004.0133100 | OTHER | CA-TIER-3 | Distribution | 2021-05-03 | 2024-05-03 | 2
434634181-28480-DTLSB-05_03_2021-ENCHRW-1^06240004.0136101 | OTHER | CA-TIER-3 | Distribution | 2021-05-03 | 2024-05-03 | 2
334874591-72580-DTLSB-05_03_2021-GO95HV-1^06240004.0137202 | OTHER | CA-TIER-3 | Distribution | 2021-05-03 | 2026-05-03 | 3
13834601-16580-DTLSB-05_03_2021-GO95HV-1^06240004.0138201 | OTHER | CA-TIER-3 | Distribution | 2021-05-03 | 2026-05-03 | 3
676495490-23869-DTLSB-05_06_2021-COPLLEAN-1^06240004.0152411 | POLE | CA-TIER-3 | Distribution | 2021-05-06 | 2024-05-06 | 2
823278728-33170-DETAIL-04_26_2023-GO95TCH-1^06240004.0063103 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
612838678-33778-DETAIL-04_26_2023-SVCENTCO-1^06240004.0063104 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
173903839-90370-DETAIL-04_26_2023-ABNDEQPM-1^06240004.0063200 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
781690723-7230-DETAIL-04_25_2023-GO95MLD-1^06240004.0063601 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
564024053-94730-DETAIL-04_25_2023-GO95MLD-1^06240004.0063801 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
679257943-72730-DETAIL-04_25_2023-GO95TCH-1^06240004.0063803 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
147223368-33470-DETAIL-04_26_2023-GO95MLD-1^06240004.0064001 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
872466569-80470-DETAIL-04_26_2023-GO95MLD-1^06240004.0064200 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
950055566-38770-DETAIL-11_15_2022-GO95HV-1^06239004.0363302 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2027-11-15 | 3
512571883-48821-DETAIL-11_09_2022-GO95MLD-1^06239004.0363500 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
149550143-96021-DETAIL-11_14_2022-GUYHINS-1^06239004.0363700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
716306493-23721-DETAIL-11_14_2022-GO95TCH-1^06239004.0363900 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
371507118-32309-DETAIL-05_18_2022-GO95MLD-1^06241005.0025103 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
504020846-62868-DETAIL-05_12_2022-GO95MLD-1^06241005.0025602 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
504020846-62868-DETAIL-05_12_2022-GUYHINS-1^06241005.0025602 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
636046638-96638-DETAIL-05_12_2022-GO95MLD-1^06241005.0025605 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
914521398-16652-DETAIL-05_18_2022-ABNDEQPM-1^06241005.0026001 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
914521398-16652-DETAIL-05_18_2022-GO95HV-1^06241005.0026001 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
458608059-35152-DETAIL-05_16_2022-GO95MLD-1^06241005.0028251 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
458608059-35152-DETAIL-05_16_2022-SVCENTBK-1^06241005.0028251 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
458608059-35152-DETAIL-05_16_2022-SVCROAD-1^06241005.0028251 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
226180795-99532-DETAIL-05_16_2022-ENCHRW-1^06241005.0028301 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
708107086-28742-DETAIL-05_16_2022-GO95MLD-1^06241005.0028308 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
708107086-28742-DETAIL-05_16_2022-GUYHINS-1^06241005.0028308 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
715020308-97660-DETAIL-01_24_2023-GO95BLTC-1^06240004.0079405 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
715020308-97660-DETAIL-01_24_2023-GO95MLD-1^06240004.0079405 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
758847233-18243-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079600 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
497672561-6433-DETAIL-01_24_2023-ABNDEQPM-1^06240004.0079702 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
200269423-37243-DETAIL-01_24_2023-SVCROAD-1^06240004.0079800 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
780833015-69270-DETAIL-01_24_2023-GO95MLD-1^06240004.0079801 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
631638878-18920-DETAIL-01_19_2023-GO95MLD-1^06240004.0079840 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
675650958-98340-DTLSB-05_03_2021-GRDRODHI-1^06240003.0076102 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
395015888-24540-DTLSB-05_03_2021-GO95HV-1^06240003.0078400 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2026-05-03 | 3
395015888-24540-DTLSB-05_03_2021-GRDRODHI-1^06240003.0078400 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
747959188-90940-DTLSB-05_03_2021-GO95MLD-1^06240003.0079400 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
611623298-18940-DTLSB-05_05_2021-GO95MLD-1^06240003.0079500 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2024-05-05 | 2
311735853-67821-DETAIL-11_09_2022-GO95TCH-1^06239004.0362400 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
39707532-69532-DETAIL-11_09_2022-POLESTEP-1^06239004.0362404 | POLE | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
778831351-36511-DETAIL-11_09_2022-GO95MLD-1^06239004.0362602 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
488675323-62921-DETAIL-11_09_2022-GO95MLD-1^06239004.0362603 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
387785316-51908-DETAIL-11_14_2022-GO95MLD-1^06239004.0363200 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
836443876-27880-DETAIL-11_14_2022-SVCWIND-1^06239004.0363202 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
512571883-48821-DETAIL-11_09_2022-GO95TCH-1^06239004.0363500 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
15267283-50921-DETAIL-11_09_2022-GO95CL10-1^06239004.0363602 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
315339443-3721-DETAIL-11_09_2022-GO95MLD-1^06239004.0363603 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
315339443-3721-ADMIN-11_15_2022-GO95TCH-1^06239004.0363603 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
315339443-3721-AUDIT-11_15_2022-GO95TCH-1^06239004.0363603 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
516819268-20190-DETAIL-11_15_2022-GO95MLD-1^06239004.0364400 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
65505056-69171-DETAIL-11_14_2022-GO95MLD-1^06239004.0367944 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
563679215-11751-DETAIL-11_15_2022-GO95CL10-1^06239004.0368906 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2027-11-15 | 3
455658288-71550-DTLSB-05_05_2021-GO95HV-1^06240003.0053100 | OTHER | CA-TIER-2 | Distribution | 2021-05-05 | 2026-05-05 | 3
294644048-54340-DTLSB-05_03_2021-GO95MLD-1^06240003.0075001 | OTHER | CA-TIER-2 | Distribution | 2021-05-03 | 2024-05-03 | 2
455465513-49560-DETAIL-01_12_2023-SVCROAD-1^06240004.0076341 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
18734461-74533-DETAIL-01_24_2023-GO95MLD-1^06240004.0077941 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
574467261-42533-DETAIL-01_24_2023-GO95MLD-1^06240004.0077942 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
385252943-58243-DETAIL-01_24_2023-GO95HV-1^06240004.0078601 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2028-01-24 | 3
738747298-38070-DETAIL-01_23_2023-SVCDEFLC-1^06240004.0079100 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
733529874-50160-DETAIL-01_24_2023-GO95MLD-1^06240004.0079300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
733529874-50160-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
695524444-96060-DETAIL-01_24_2023-GO95MLD-1^06240004.0079401 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
480388800-93070-DETAIL-04_12_2023-GUYHINS-1^06240004.0166503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
480388800-93070-DETAIL-04_12_2023-GUYHINS-2^06240004.0166503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
938362990-99270-DETAIL-04_12_2023-GO95BLTC-1^06240004.0166511 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
53447961-52980-DETAIL-04_17_2023-GO95MLD-1^06240004.0166540 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
398102401-53401-DETAIL-04_17_2023-GO95MLD-1^06240004.0166611 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
401781783-6550-DETAIL-04_17_2023-SVCROAD-1^06240004.0166642 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
786104514-22799-DETAIL-04_17_2023-GO95MLD-1^06240004.0166643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
786104514-22799-DETAIL-04_17_2023-SVCWIND-1^06240004.0166643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
786104514-22799-DETAIL-04_17_2023-SVCWIND-2^06240004.0166643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
452556801-40399-DETAIL-04_17_2023-GO95MLD-1^06240004.0166644 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
452556801-40399-DETAIL-04_17_2023-RISEGRD-1^06240004.0166644 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
100743301-96080-DETAIL-04_17_2023-GO95MLD-1^06240004.0166645 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
445323300-46870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166705 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
875049161-84261-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166208 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
112292551-35180-DETAIL-03_21_2023-SVCDEFLC-2^06240004.0166301 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
92945831-8080-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0166303 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
949792741-12180-DETAIL-03_21_2023-SVCWIND-1^06240004.0166304 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
3583480-7270-DETAIL-03_21_2023-GO95TCH-1^06240004.0166305 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
3583480-7270-DETAIL-03_21_2023-GUYHINS-1^06240004.0166305 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
3583480-7270-DETAIL-03_21_2023-SVCROAD-1^06240004.0166305 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
536428272-83302-DETAIL-03_22_2023-GO95HV-1^06240004.0166306 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
455550172-20880-DETAIL-03_22_2023-GO95MLD-1^06240004.0166310 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
884870580-42670-DETAIL-04_12_2023-SVCENTCO-1^06240004.0166402 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
854512820-86870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166502 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
759092936-90680-DETAIL-01_17_2022-GO95TCH-1^06239004.0256654 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
321911343-71450-DETAIL-01_17_2022-GO95TCH-1^06239004.0256701 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
46714394-78460-DETAIL-01_17_2022-SVCENTCO-1^06239004.0256702 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
60058436-51570-DETAIL-01_17_2022-GO95HV-1^06239004.0256741 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2027-01-17 | 3
584482933-48950-DETAIL-01_17_2022-GO95CL10-1^06239004.0256801 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2027-01-17 | 3
941253564-87760-DETAIL-01_17_2022-SVCWIND-1^06239004.0256905 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
739821823-91750-DETAIL-01_17_2022-SVCWIND-1^06239004.0256906 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
554446146-73161-DETAIL-11_14_2022-GO95MLD-1^06239004.0366907 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
804983116-1861-DETAIL-11_16_2022-GO95TCH-1^06239004.0367800 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
883723306-55971-DETAIL-11_16_2022-GO95MLD-1^06239004.0367842 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
437884246-99681-DETAIL-11_15_2022-GO95MLD-1^06239004.0367844 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
483561235-40151-DETAIL-11_15_2022-GO95TCH-1^06239004.0367902 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
778608288-17070-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0082202 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
778608288-17070-DETAIL-01_17_2023-SVCDEFLC-2^06240004.0082202 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
496255146-40940-DETAIL-01_17_2023-GO95TCH-1^06240004.0082204 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
496255146-40940-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0082204 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
251044808-50170-DETAIL-01_19_2023-GO95TCH-1^06240004.0082401 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
251044808-50170-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0082401 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
688128728-38830-DETAIL-01_19_2023-GO95HV-1^06240004.0082506 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2028-01-19 | 3
688128728-38830-DETAIL-01_19_2023-GO95MLD-1^06240004.0082506 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
688128728-38830-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0082506 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
367335318-16830-DETAIL-01_19_2023-GO95MLD-1^06240004.0082601 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
566587268-65440-DETAIL-11_18_2022-GO95MLD-1^06238004.0223409 | OTHER | CA-TIER-2 | Distribution | 2022-11-18 | 2025-11-18 | 2
299017425-58210-DETAIL-11_10_2022-SVCWIND-1^06238004.0223601 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
355481605-26210-DETAIL-11_10_2022-GO95MLD-1^06238004.0223703 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
324980206-90510-DETAIL-11_10_2022-GRDRODHI-1^06238004.0223704 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
586261976-10600-DETAIL-03_09_2021-XARMSPCR-1^06239003.0016913 | CROSSARM | CA-NON-TIER | Distribution | 2021-03-09 | 2024-03-09 | 2
589488802-63750-DETAIL-03_03_2021-POLESTEP-1^06239003.0018404 | POLE | CA-NON-TIER | Distribution | 2021-03-03 | 2024-03-03 | 2
589488802-63750-DETAIL-03_03_2021-XARMSPCR-1^06239003.0018404 | CROSSARM | CA-NON-TIER | Distribution | 2021-03-03 | 2024-03-03 | 2
589488802-63750-DETAIL-03_03_2021-XARMSPCR-2^06239003.0018404 | CROSSARM | CA-NON-TIER | Distribution | 2021-03-03 | 2024-03-03 | 2
510220936-51900-DETAIL-03_02_2021-GO95HV-1^06239003.0018602 | OTHER | CA-NON-TIER | Distribution | 2021-03-02 | 2026-03-02 | 3
510220936-51900-DETAIL-03_02_2021-XARMSPCR-1^06239003.0018602 | CROSSARM | CA-NON-TIER | Distribution | 2021-03-02 | 2024-03-02 | 2
736467651-88401-DETAIL-03_24_2021-SVCROAD-1^06239004.0135146 | OTHER | CA-TIER-2 | Distribution | 2021-03-24 | 2024-03-24 | 2
390948740-86201-DETAIL-03_24_2021-SVCWIND-1^06239004.0136217 | OTHER | CA-TIER-2 | Distribution | 2021-03-24 | 2024-03-24 | 2
848010196-31180-DETAIL-03_30_2021-ENCHRW-1^06239004.0244800 | OTHER | CA-TIER-2 | Distribution | 2021-03-30 | 2024-03-30 | 2
609895596-50280-ADMIN-09_19_2022-GO95MLD-1^06239004.0245905 | OTHER | CA-TIER-2 | Distribution | 2022-09-19 | 2027-09-19 | 3
213997056-34870-DETAIL-01_19_2022-SVCWIND-1^06239004.0254140 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
596510386-34970-DETAIL-01_19_2022-GO95MLD-1^06239004.0254144 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
853126776-84870-DETAIL-01_19_2022-GO95MLD-1^06239004.0254240 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2027-01-19 | 3
754901508-71508-DETAIL-01_24_2022-CLMBHAZ-1^06239004.0254400 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
482476655-94870-DETAIL-01_24_2022-GO95MLD-1^06239004.0254401 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
140765245-36245-DETAIL-01_24_2022-SVCWIND-1^06239004.0254406 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
188781926-6640-DETAIL-01_17_2023-GO95MLD-1^06240004.0083041 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
607382919-48670-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0060401 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
397275904-87904-DETAIL-04_24_2023-GO95MLD-1^06240004.0061002 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
289982187-53970-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061203 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
839266937-41970-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
545984213-31230-DETAIL-04_25_2023-GRDRODHI-1^06240004.0061602 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
83020933-30730-DETAIL-05_01_2023-GO95MLD-1^06240004.0061801 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
83020933-30730-DETAIL-05_01_2023-SVCDEFLC-1^06240004.0061801 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
393087418-12170-DETAIL-04_24_2023-GO95MLD-1^06240004.0062103 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
964126619-270-DETAIL-04_24_2023-GO95MLD-1^06240004.0062200 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
283068933-41330-DETAIL-04_25_2023-GO95TCH-1^06240004.0062602 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
857574491-54650-DETAIL-11_17_2022-SVCROAD-1^06238004.0274800 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
153399971-54150-DETAIL-11_17_2022-SVCDECK-1^06238004.0274801 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
218655681-52650-DETAIL-11_17_2022-GO95MLD-1^06238004.0274803 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
672978193-97763-DETAIL-11_17_2022-GO95MLD-1^06238004.0274903 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
915286171-44380-DETAIL-06_17_2023-POLEREPL-1^06239001.0047700 | POLE | CA-TIER-2 | Distribution | 2023-06-17 | 2024-06-17 | 2
814224061-24280-ADMIN-06_08_2023-POLEREPL-1^06239002.0047402 | POLE | CA-TIER-2 | Distribution | 2023-06-08 | 2024-06-08 | 2
870980354-25990-DETAIL-02_23_2021-XARMSPCR-1^06239002.0063607 | CROSSARM | CA-NON-TIER | Distribution | 2021-02-23 | 2024-02-23 | 2
392870195-94200-DETAIL-02_23_2021-XARMSPCR-1^06239002.0063611 | CROSSARM | CA-NON-TIER | Distribution | 2021-02-23 | 2024-02-23 | 2
53014774-82390-DETAIL-02_24_2021-GO95MLD-1^06239002.0067807 | OTHER | CA-TIER-2 | Distribution | 2021-02-24 | 2024-02-24 | 2
965901429-3770-DETAIL-04_20_2023-GRDRODHI-2^06240004.0162201 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
650855233-13880-DETAIL-03_27_2023-GO95BLTC-1^06240004.0162501 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
60988283-27980-DETAIL-03_21_2023-GO95MLD-1^06240004.0162502 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
833084323-27180-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0162601 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
81850088-2750-ADMIN-03_21_2023-POLEREPL-1^06240004.0162640 | POLE | CA-TIER-2 | Distribution | 2023-03-21 | 2024-03-21 | 2
767709178-87650-DETAIL-03_21_2023-GO95CL10-1^06240004.0162642 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
767709178-87650-DETAIL-03_21_2023-GO95HV-1^06240004.0162642 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
326423368-35650-DETAIL-03_21_2023-GUYHINS-1^06240004.0162643 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
244463208-57240-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0162703 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
501551528-1340-DETAIL-03_21_2023-GUYNOINS-1^06240004.0162705 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
910378506-92370-DETAIL-01_24_2022-GO95MLD-1^06239004.0254402 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
591343819-79290-DETAIL-01_24_2022-SVCWIND-1^06239004.0255100 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
184515631-5801-DETAIL-01_25_2022-SVCWIND-1^06239004.0255141 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
322926381-79111-DETAIL-01_18_2022-GO95MLD-1^06239004.0255143 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
919993696-17280-AUDIT-06_28_2022-GO95TCH-1^06239004.0256655 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
321911343-71450-DETAIL-01_17_2022-SVCWIND-1^06239004.0256701 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
664605046-12570-DETAIL-01_17_2022-SVCENTCO-1^06239004.0256744 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
198889506-56180-DETAIL-01_17_2022-SVCRUBLG-1^06239004.0256745 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
621394333-26350-DETAIL-01_17_2022-GO95MLD-1^06239004.0256805 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
941253564-87760-DETAIL-01_17_2022-SVCRUBLG-1^06239004.0256905 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
993285001-5501-DETAIL-01_25_2022-SVCROOF-1^06239004.0257040 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
993285001-5501-DETAIL-01_25_2022-SVCWIND-1^06239004.0257040 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
555898263-65490-ADMIN-05_30_2023-POLEREPL-1^06239002.0272400 | POLE | CA-TIER-2 | Distribution | 2023-05-30 | 2024-05-30 | 2
369312066-33410-DETAIL-03_15_2021-GUYHINS-1^06239003.0016504 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2021-03-15 | 2024-03-15 | 2
859680606-54600-DETAIL-03_15_2021-GO95TCH-1^06239003.0016507 | OTHER | CA-TIER-2 | Distribution | 2021-03-15 | 2024-03-15 | 2
586261976-10600-DETAIL-03_09_2021-GO95HV-1^06239003.0016913 | OTHER | CA-NON-TIER | Distribution | 2021-03-09 | 2026-03-09 | 3
589488802-63750-DETAIL-03_03_2021-GO95MLD-1^06239003.0018404 | OTHER | CA-NON-TIER | Distribution | 2021-03-03 | 2024-03-03 | 2
519974165-32700-DETAIL-03_16_2021-SVCROAD-1^06239003.0243904 | OTHER | CA-TIER-2 | Distribution | 2021-03-16 | 2024-03-16 | 2
369776064-87290-DETAIL-03_22_2021-GO95MLD-1^06239003.0252801 | OTHER | CA-TIER-2 | Distribution | 2021-03-22 | 2024-03-22 | 2
632447241-70850-DTLSB-05_19_2021-GO95MLD-1^06239004.0017000 | OTHER | CA-TIER-3 | Distribution | 2021-05-19 | 2024-05-19 | 2
271605593-51250-DETAIL-03_24_2021-SVCWIND-1^06239004.0134143 | OTHER | CA-TIER-2 | Distribution | 2021-03-24 | 2024-03-24 | 2
240082246-15670-DETAIL-01_18_2022-SVCROAD-1^06239004.0257840 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
94019936-18570-DETAIL-01_18_2022-GO95BLTC-1^06239004.0257842 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
693602216-94980-DETAIL-05_01_2023-GRDRODHI-1^06240004.0050140 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
572198636-28980-DETAIL-05_01_2023-SVCDEFLC-1^06240004.0050141 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
299265658-5850-DETAIL-04_26_2023-GO95MLD-1^06240004.0050144 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
353483896-44280-DETAIL-04_26_2023-GO95MLD-1^06240004.0051001 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
666803259-86510-DETAIL-05_01_2023-GO95HV-1^06240004.0051440 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2028-05-01 | 3
146901476-62680-DETAIL-05_01_2023-GO95MLD-1^06240004.0052300 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
489751986-41780-DETAIL-05_01_2023-GO95MLD-1^06240004.0052301 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
912521697-54970-DETAIL-04_26_2023-GO95MLD-1^06240004.0060101 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
912521697-54970-DETAIL-04_26_2023-SVCROAD-1^06240004.0060101 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
918756399-54970-DETAIL-04_27_2023-GO95MLD-1^06240004.0060202 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
246751583-81079-DETAIL-01_17_2023-GO95TCH-1^06148004.0222704 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
251547031-4609-DETAIL-01_18_2023-GO95MLD-1^06148004.0223001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
251547031-4609-DETAIL-01_18_2023-GO95MLD-2^06148004.0223001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
438374811-88309-ADMIN-10_09_2019-COPLLEAN-1^06148004.0226000 | POLE | CA-NON-TIER | Distribution | 2019-10-09 | 2022-10-09 | 2
501618523-63209-DETAIL-01_17_2023-GO95HV-1^06148004.0227100 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
554945733-3679-DETAIL-01_17_2023-GO95MLD-2^06148004.0227101 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
880717653-93679-DETAIL-01_17_2023-COPLLEAN-1^06148004.0227801 | POLE | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
880717653-93679-DETAIL-01_17_2023-GO95MLD-2^06148004.0227801 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
960361113-96309-DETAIL-01_17_2023-GO95HV-1^06148004.0228700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
415655503-47309-DETAIL-01_17_2023-GO95MLD-1^06148004.0229700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
415655503-47309-DETAIL-01_17_2023-GO95MLD-2^06148004.0229700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
182382903-99720-ADMIN-03_07_2023-POLEDERP-1^06148004.0291500 | POLE | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
973358154-46760-DETAIL-01_12_2022-GO95TCH-1^06239004.0255605 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
709197374-90860-DETAIL-01_24_2022-GO95MLD-1^06239004.0255700 | OTHER | CA-TIER-3 | Distribution | 2022-01-24 | 2025-01-24 | 2
97051878-95590-DETAIL-01_24_2022-GO95MLD-1^06239004.0256002 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2027-01-24 | 3
97051878-95590-DETAIL-01_24_2022-SVCENTCO-1^06239004.0256002 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
785868109-63890-DETAIL-01_24_2022-SVCENTCO-1^06239004.0256003 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
234086986-54070-DETAIL-01_18_2022-GO95MLD-1^06239004.0256101 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
578384299-62190-DETAIL-01_18_2022-GO95HV-1^06239004.0256103 | OTHER | CA-TIER-2 | Distribution | 2022-01-18 | 2027-01-18 | 3
750483076-98770-DETAIL-01_18_2022-GO95CL10-1^06239004.0258842 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2027-01-18 | 3
416972476-13070-DETAIL-01_18_2022-GO95TCH-1^06239004.0258941 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
143489585-29570-DETAIL-01_18_2022-SVCWIND-1^06239004.0259700 | OTHER | CA-TIER-3 | Distribution | 2022-01-18 | 2025-01-18 | 2
191580928-3390-DETAIL-11_09_2022-GO95MLD-1^06239004.0361300 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
613051756-40780-DETAIL-11_15_2022-GUYNOINS-1^06239004.0362100 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
509773733-29230-DETAIL-04_26_2023-GO95MLD-1^06240004.0065103 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
316804743-54279-AUDIT-07_05_2023-RISEGRD-1^06240004.0065901 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
689753063-85190-DETAIL-04_25_2023-POLETOP-1^06240004.0065902 | POLE | CA-TIER-2 | Distribution | 2023-04-25 | 2024-04-25 | 2
938539443-11330-DETAIL-04_26_2023-GO95MLD-1^06240004.0066003 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
345214053-43330-DETAIL-05_01_2023-GO95MLD-1^06240004.0066004 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
239338578-94678-DETAIL-04_26_2023-GO95MLD-1^06240004.0067002 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
232985663-98330-DETAIL-05_01_2023-XARMSPCR-1^06240004.0067100 | CROSSARM | CA-TIER-2 | Distribution | 2023-05-01 | 2024-05-01 | 2
136214573-62960-DETAIL-01_12_2023-GO95MLD-1^06240004.0072343 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
406397463-71860-DETAIL-01_12_2023-GO95MLD-1^06240004.0073340 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
457101853-67760-DETAIL-01_12_2023-GO95HV-1^06240004.0073342 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2028-01-12 | 3
758558494-21360-DETAIL-01_12_2023-GO95MLD-1^06240004.0074300 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
598769744-15189-DETAIL-01_23_2023-GO95TCH-1^06148004.0192003 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
598769744-15189-DETAIL-01_23_2023-SVCENTCO-1^06148004.0192003 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
589087435-48779-DETAIL-01_23_2023-GO95MLD-1^06148004.0192101 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
398308494-34189-DETAIL-01_23_2023-GO95HV-1^06148004.0192102 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
690849516-53379-DETAIL-01_23_2023-GO95MLD-1^06148004.0192104 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
21223755-48179-DETAIL-01_18_2023-GO95HV-1^06148004.0204000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
21223755-48179-DETAIL-01_18_2023-GO95MLD-1^06148004.0204000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
653137285-56579-DETAIL-01_19_2023-GO95TCH-1^06148004.0204200 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
322193475-24109-DETAIL-01_19_2023-COPLLEAN-1^06148004.0204301 | POLE | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
879162174-67879-DETAIL-01_19_2023-GO95BLTC-1^06148004.0204601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
24249945-63679-DETAIL-01_19_2023-GO95MLD-1^06148004.0204602 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
566554395-66079-DETAIL-01_18_2023-GO95BLTC-1^06148004.0205000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
611126065-52341-DETAIL-05_03_2022-GO95MLD-1^06241005.0013642 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
611126065-52341-DETAIL-05_03_2022-GUYHINS-2^06241005.0013642 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
833940824-731-DETAIL-05_03_2022-GO95MLD-1^06241005.0013701 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
553226026-67261-DETAIL-05_10_2022-GUYHINS-1^06241005.0013800 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
848196593-49721-DETAIL-05_09_2022-GO95MLD-1^06241005.0014400 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
904344566-18271-DETAIL-05_09_2022-GO95MLD-1^06241005.0014500 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
619927239-32943-DETAIL-05_04_2022-GO95HV-1^06241005.0014801 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2027-05-04 | 3
666192945-98432-DETAIL-05_18_2022-SVCENTCO-1^06241005.0027012 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
297954124-36932-DETAIL-05_18_2022-GUYHINS-1^06241005.0027013 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
913272954-73022-DETAIL-05_16_2022-GO95MLD-1^06241005.0027100 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
487351829-16452-DETAIL-05_16_2022-GO95MLD-1^06241005.0027140 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
487351829-16452-DETAIL-05_16_2022-GUYHINS-1^06241005.0027140 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
706984529-45452-DETAIL-05_16_2022-GO95TCH-1^06241005.0027141 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
72454614-79779-DETAIL-01_18_2023-GO95MLD-2^06148004.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
779052414-16689-DETAIL-01_23_2023-GO95MLD-1^06148004.0199000 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
567072805-90109-DETAIL-01_19_2023-GO95MLD-2^06148004.0199601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
707808905-98009-DETAIL-01_19_2023-GO95HV-1^06148004.0199701 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
554324204-44279-DETAIL-01_19_2023-GO95HV-1^06148004.0200004 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
954916105-78109-DETAIL-01_23_2023-GO95HV-1^06148004.0200100 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
189044191-18779-ADMIN-03_10_2023-GO95CL10-1^06148004.0200600 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
653137285-56579-DETAIL-01_19_2023-GO95HV-1^06148004.0204200 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
653137285-56579-DETAIL-01_19_2023-GO95MLD-1^06148004.0204200 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
72454614-79779-DETAIL-01_18_2023-GO95TCH-1^06148004.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
72454614-79779-DETAIL-01_18_2023-GUYHINS-1^06148004.0215200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
322603701-14701-DETAIL-01_18_2023-GO95TCH-1^06148004.0215201 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
460207664-6810-DETAIL-11_16_2022-GO95HV-1^06238004.0153000 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
142555954-74910-DETAIL-11_16_2022-GO95HV-1^06238004.0154000 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
673859151-62209-DETAIL-01_17_2023-GO95HV-1^06148004.0222705 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
723797451-53609-DETAIL-01_17_2023-COPLLEAN-1^06148004.0223003 | POLE | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
723797451-53609-DETAIL-01_17_2023-GO95HV-1^06148004.0223003 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
564330844-19179-DETAIL-01_17_2023-GO95MLD-1^06148004.0223500 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
564330844-19179-DETAIL-01_17_2023-GO95MLD-2^06148004.0223500 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
286029511-81979-DETAIL-01_17_2023-GO95MLD-1^06148004.0225001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
286029511-81979-DETAIL-01_17_2023-SVCROAD-1^06148004.0225001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
438374811-88309-DETAIL-01_17_2023-CONDFRAY-2^06148004.0226000 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-GO95MLD-1^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-GO95MLD-2^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
704567781-40881-DETAIL-01_10_2023-GO95MLD-1^06148004.0187206 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
395076619-31719-DETAIL-01_10_2023-GO95MLD-1^06148004.0189204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
426985984-88689-DETAIL-01_23_2023-GO95MLD-1^06148004.0192002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
321533495-93189-DETAIL-01_23_2023-GO95TCH-1^06148004.0192100 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
690849516-53379-DETAIL-01_23_2023-SVCROAD-1^06148004.0192104 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
307092451-81189-DETAIL-01_23_2023-GO95CL10-1^06148004.0192201 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
229582911-30789-DETAIL-01_23_2023-GO95HV-1^06148004.0192300 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
2514386-77179-DETAIL-01_23_2023-GRDRODHI-1^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
971719134-61089-DETAIL-01_23_2023-GO95MLD-1^06148004.0192500 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
32540934-2089-DETAIL-01_23_2023-GO95MLD-1^06148004.0192501 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
443601764-42089-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192502 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
443601764-42089-DETAIL-01_23_2023-GO95HV-1^06148004.0192502 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
109420054-88779-DETAIL-01_19_2023-GO95MLD-1^06148004.0214600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
881550413-30279-DETAIL-01_18_2023-CONDFRAY-1^06148004.0215002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-CONDFRAY-2^06148004.0215002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-GO95MLD-2^06148004.0215002 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-GO95TCH-1^06148004.0215002 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
981280733-16309-DETAIL-01_18_2023-CONDFRAY-1^06148004.0215101 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
383003071-51079-DETAIL-01_19_2023-GO95TCH-1^06148004.0215600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
225471651-21389-DETAIL-01_18_2023-GO95MLD-1^06148004.0219000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
758896411-48109-DETAIL-01_17_2023-SVCENTCO-1^06148004.0219500 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
405058381-9579-DETAIL-01_18_2023-GO95TCH-1^06148004.0220301 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
27956181-71799-DETAIL-01_18_2023-GUYSLACK-1^06148004.0220400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
12948131-50209-DETAIL-01_17_2023-GO95HV-1^06148004.0220602 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
516642426-28470-DETAIL-01_24_2022-GO95MLD-1^06239004.0257205 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
858274775-64270-DETAIL-01_18_2022-GUYNOINS-2^06239004.0257207 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-18 | 2025-01-18 | 2
149244089-59090-DETAIL-01_19_2022-GO95MLD-1^06239004.0257209 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
910825495-98270-DETAIL-01_25_2022-GO95TCH-1^06239004.0257301 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
772718281-11801-DETAIL-01_25_2022-GO95BLTC-1^06239004.0257342 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
969087471-12901-DETAIL-01_25_2022-GO95BLTC-1^06239004.0257441 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
529054051-79401-DETAIL-01_25_2022-GO95BLTC-1^06239004.0257442 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2027-01-25 | 3
529054051-79401-DETAIL-01_25_2022-GO95MLD-1^06239004.0257442 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
141561426-13370-DETAIL-01_12_2022-GO95MLD-1^06239004.0257603 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
702567153-26750-DETAIL-01_24_2022-SVCENTCO-1^06239004.0257605 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
563515646-65680-DETAIL-01_17_2022-GO95HV-1^06239004.0257640 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2027-01-17 | 3
563515646-65680-DETAIL-01_17_2022-GO95MLD-1^06239004.0257640 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
252055586-42861-DETAIL-11_15_2022-GO95MLD-1^06239004.0366802 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
600794156-21661-DETAIL-11_15_2022-GO95MLD-1^06239004.0366804 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
915228226-81481-DETAIL-11_16_2022-GO95MLD-1^06239004.0366840 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
754357698-86390-DETAIL-01_19_2022-GO95MLD-1^06239004.0256214 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
645131730-15690-DETAIL-01_19_2022-GO95HV-1^06239004.0256302 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2027-01-19 | 3
477907435-10570-DETAIL-01_24_2022-GO95MLD-1^06239004.0256307 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
248341098-91098-DETAIL-01_24_2022-SVCWIND-2^06239004.0256401 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
883705780-54890-DETAIL-01_17_2022-GO95TCH-1^06239004.0256407 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
547385671-21550-DETAIL-01_17_2022-GO95MLD-1^06239004.0256504 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
676279125-83770-DETAIL-01_17_2022-GO95MLD-1^06239004.0256602 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
731238996-49970-DETAIL-01_17_2022-SVCWIND-1^06239004.0256646 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
530345266-65770-DETAIL-01_17_2022-GO95HV-1^06239004.0256652 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2027-01-17 | 3
771181821-85689-DTLSB-03_12_2018-ENCHRW-1^06148003.0139101 | OTHER | CA-NON-TIER | Distribution | 2018-03-12 | 2023-02-12 | 2
66905481-21789-DETAIL-01_09_2023-GO95MLD-1^06148003.0140301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
73225391-13079-DETAIL-01_09_2023-GO95HV-1^06148003.0140302 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
867375851-97379-DETAIL-01_09_2023-GO95BLTC-1^06148003.0141300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
96516561-19689-DETAIL-01_09_2023-GO95MLD-1^06148003.0141301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
885582501-80789-DETAIL-01_09_2023-GO95TCH-1^06148003.0142300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
143266651-61579-DETAIL-01_09_2023-GRDRODHI-1^06148003.0143200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
428730061-77079-DETAIL-01_09_2023-GO95MLD-1^06148003.0143201 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
665961991-10789-DETAIL-01_09_2023-GO95TCH-1^06148003.0143300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
620126644-86644-DETAIL-01_09_2023-GO95MLD-1^06148003.0144201 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
860832561-15689-DETAIL-01_09_2023-GO95TCH-1^06148003.0149100 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
817672890-27789-DETAIL-01_09_2023-GO95HV-1^06148003.0153001 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
149617545-50779-DETAIL-01_18_2023-GO95HV-1^06148004.0207000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
149617545-50779-DETAIL-01_18_2023-XARMBRAC-1^06148004.0207000 | CROSSARM | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
616782635-19109-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
112370225-17079-DETAIL-01_18_2023-GO95HV-1^06148004.0207100 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
977348665-69109-ADMIN-01_18_2023-ENCHRW-1^06148004.0207201 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
720766155-36789-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207400 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
720766155-36789-DETAIL-01_18_2023-COPLLEAN-1^06148004.0207400 | POLE | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
984444755-90009-DETAIL-01_18_2023-CONDFRAY-3^06148004.0207700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
220278255-65579-DETAIL-01_18_2023-GO95BLTC-1^06148004.0207701 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
307092451-81189-DETAIL-01_23_2023-GO95MLD-1^06148004.0192201 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
229582911-30789-DETAIL-01_23_2023-GO95MLD-1^06148004.0192300 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
185489324-27379-ADMIN-03_10_2023-GO95CL10-1^06148004.0192401 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
625875344-14979-DETAIL-02_14_2022-CLRTOUCH-1^06147005.0347000 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
372688836-60936-DETAIL-02_10_2022-GO95MLD-1^06147005.0347003 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
681532836-24836-DETAIL-02_10_2022-GO95HV-1^06147005.0347102 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
532670634-22634-DETAIL-02_10_2022-GO95HV-1^06147005.0348203 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
532670634-22634-DETAIL-02_10_2022-GO95MLD-1^06147005.0348203 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
344055636-28636-DETAIL-02_10_2022-GO95MLD-1^06147005.0348205 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
122174542-66509-DETAIL-02_14_2022-GO95HV-1^06147005.0350601 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
576331780-94179-DETAIL-02_10_2022-GO95MLD-1^06147005.0350901 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
576331780-94179-DETAIL-02_10_2022-GRDRODHI-2^06147005.0350901 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
317934648-77279-DETAIL-02_14_2022-GO95MLD-1^06147005.0351700 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
850878808-57099-DETAIL-02_10_2022-GO95MLD-1^06147005.0355100 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
870815908-64099-DETAIL-02_10_2022-GO95MLD-1^06147005.0355200 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
844905674-78630-DTLSB-04_29_2021-GO95TCH-1^06236005.0334602 | OTHER | CA-TIER-2 | Distribution | 2021-04-29 | 2024-04-29 | 2
729998211-79811-DTLSB-04_20_2021-SVCROAD-1^06237004.0171701 | OTHER | CA-TIER-2 | Distribution | 2021-04-20 | 2024-04-20 | 2
753979529-21040-ADMIN-08_21_2023-POLEREPL-1^06237004.0171807 | POLE | CA-TIER-2 | Distribution | 2023-08-21 | 2024-08-21 | 2
664671230-23170-DETAIL-03_17_2021-GO95MLD-1^06238003.0015602 | OTHER | CA-TIER-2 | Distribution | 2021-03-17 | 2024-03-17 | 2
664671230-23170-DETAIL-03_17_2021-SVCROAD-1^06238003.0015602 | OTHER | CA-TIER-2 | Distribution | 2021-03-17 | 2024-03-17 | 2
427130178-36440-DTLSB-04_15_2021-GO95MLD-1^06238004.0145900 | OTHER | CA-TIER-2 | Distribution | 2021-04-15 | 2024-04-15 | 2
788523894-79910-DETAIL-11_16_2022-GO95HV-1^06238004.0150001 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
134366684-9810-DETAIL-11_16_2022-GO95MLD-1^06238004.0152200 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
53425034-12810-DETAIL-11_16_2022-GUYLOINS-1^06238004.0152202 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
568691524-61810-DETAIL-11_16_2022-GUYHINS-1^06238004.0152203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
568691524-61810-AUDIT-12_07_2022-ANCHIDLE-1^06238004.0152203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-12-07 | 2025-12-07 | 2
69417784-78810-DETAIL-11_16_2022-GO95HV-1^06238004.0152204 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2027-11-16 | 3
77883994-55700-DETAIL-02_02_2023-XARMBRAC-1^06148002.0337901 | CROSSARM | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
642514763-81361-DETAIL-02_06_2023-GO95HV-1^06148002.0338001 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
391816441-65279-DETAIL-01_10_2023-GO95MLD-1^06148003.0139100 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
892288760-20492-DETAIL-03_02_2022-GO95HV-1^06147006.0320801 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
301851891-92891-DETAIL-03_02_2022-GO95HV-1^06147006.0320900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
301851891-92891-DETAIL-03_02_2022-GO95MLD-1^06147006.0320900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
596423820-12201-DETAIL-03_01_2022-GO95MLD-1^06147006.0321204 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
298267350-30679-DETAIL-03_02_2022-GO95HV-1^06147006.0321300 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
983151760-8903-DETAIL-03_02_2022-GO95HV-1^06147006.0321301 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
187612040-26330-DETAIL-03_02_2022-GO95MLD-1^06147006.0321400 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
478434335-48335-ADMIN-09_16_2021-XARMSPCR-1^06147014.0010501 | CROSSARM | CA-NON-TIER | Distribution | 2021-09-16 | 2024-09-16 | 2
391816441-65279-DETAIL-01_10_2023-GO95MLD-2^06148003.0139100 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
927487811-27233-DETAIL-01_24_2023-GO95HV-1^06240004.0079740 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
927487811-27233-DETAIL-01_24_2023-GO95MLD-1^06240004.0079740 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
211330805-38270-DETAIL-01_24_2023-GO95MLD-1^06240004.0079804 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
339192096-42280-DETAIL-01_24_2023-GO95MLD-1^06240004.0079901 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
7474213-69933-DETAIL-01_24_2023-GO95MLD-1^06240004.0079902 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
363001009-16530-DETAIL-01_23_2023-GO95BLTC-1^06240004.0080003 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2028-01-23 | 3
363001009-16530-DETAIL-01_23_2023-SVCDEFLC-1^06240004.0080003 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
568539596-2840-DETAIL-01_26_2023-GUYHINS-1^06240004.0080200 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
117889248-67370-DETAIL-01_23_2023-SVCROAD-1^06240004.0080207 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
450539936-10840-DETAIL-01_19_2023-RISECLMB-1^06240004.0080440 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
749522669-54230-DETAIL-01_19_2023-GO95HV-1^06240004.0080802 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2028-01-19 | 3
286190518-90370-DETAIL-01_23_2023-POLESTEP-1^06240004.0081200 | POLE | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
867375851-97379-DETAIL-01_09_2023-GO95TCH-1^06148003.0141300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
143266651-61579-DETAIL-01_09_2023-GO95MLD-1^06148003.0143200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
428730061-77079-DETAIL-01_09_2023-GRDRODHI-1^06148003.0143201 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
428730061-77079-DETAIL-01_09_2023-SVCCOMMD-1^06148003.0143201 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
329335790-96789-DETAIL-01_09_2023-GO95HV-1^06148003.0153000 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
329335790-96789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153000 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
311847980-26789-DETAIL-01_09_2023-GO95HV-1^06148003.0153100 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
311847980-26789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153100 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
984073630-93889-DETAIL-01_09_2023-GO95HV-1^06148003.0153301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
502853450-94789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
314511040-44789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
517498699-48701-DETAIL-01_24_2023-GO95HV-1^06148003.0259000 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
45839834-80934-DETAIL-01_31_2022-GO95MLD-1^06147005.0264702 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
61110239-77979-DETAIL-01_31_2022-GO95MLD-1^06147005.0264800 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
358221648-22409-DETAIL-02_01_2022-SVCROOF-1^06147005.0265301 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
928174188-88079-DETAIL-02_01_2022-SVCENTCO-1^06147005.0265302 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
701374737-35737-DETAIL-02_09_2022-GO95MLD-1^06147005.0279702 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
373782384-31679-DETAIL-02_09_2022-GO95MLD-1^06147005.0279800 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
373782384-31679-DETAIL-02_09_2022-GUYHINS-1^06147005.0279800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
816634065-31209-DETAIL-02_03_2022-GO95HV-1^06147005.0288002 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2027-02-03 | 3
816634065-31209-DETAIL-02_03_2022-SVCROAD-1^06147005.0288002 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
221463046-8199-DETAIL-02_15_2022-GO95MLD-1^06147005.0330200 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
221463046-8199-DETAIL-02_15_2022-INSULDMG-1^06147005.0330200 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
480149354-26579-DETAIL-02_15_2022-SVCENTCO-1^06147005.0330500 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
404410731-8089-DETAIL-01_24_2023-CONDFRAY-1^06148003.0241301 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
292623311-55089-DETAIL-01_24_2023-GRDRODHI-1^06148003.0243400 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
391250611-91611-DETAIL-01_24_2023-GO95MLD-1^06148003.0248401 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
48516217-54644-DETAIL-01_24_2023-ABNDEQPM-1^06148003.0249400 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
859197585-11989-DETAIL-01_24_2023-GO95MLD-1^06148003.0249402 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
452583749-23289-DETAIL-01_24_2023-GO95HV-1^06148003.0257700 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
126148308-6870-DETAIL-02_02_2023-GO95HV-1^06148002.0287001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
152893203-67290-DETAIL-02_02_2023-GO95HV-1^06148002.0337700 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
73225391-13079-DETAIL-01_09_2023-GO95MLD-1^06148003.0140302 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
807894671-59689-DETAIL-01_09_2023-GO95MLD-1^06148003.0141200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
807894671-59689-DETAIL-01_09_2023-GO95MLD-2^06148003.0141200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
659910746-62206-DETAIL-09_28_2021-SVCWIND-1^06148004.0356006 | OTHER | CA-NON-TIER | Distribution | 2021-09-28 | 2024-09-28 | 2
846960094-38686-DETAIL-09_27_2021-GO95CL10-1^06148004.0356209 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2026-09-27 | 3
910279616-76786-DETAIL-09_27_2021-SVCROAD-1^06148004.0356301 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
982650767-11613-DETAIL-11_17_2022-GUYHINS-1^06238004.0273900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
58505481-45150-AUDIT-12_07_2022-POLESTEP-1^06238004.0274802 | POLE | CA-TIER-2 | Distribution | 2022-12-07 | 2025-12-07 | 2
99041370-8-DETAIL-11_17_2022-COPLLEAN-1^06238004.0274901 | POLE | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
607779526-66470-DETAIL-11_17_2022-GO95HV-1^06238004.0287400 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2027-11-17 | 3
278404222-27950-DETAIL-03_03_2021-XARMSPCR-1^06239002.0060202 | CROSSARM | CA-NON-TIER | Distribution | 2021-03-03 | 2024-03-03 | 2
506129224-990-ADMIN-05_26_2023-POLEREPL-2^06239002.0063605 | POLE | CA-NON-TIER | Distribution | 2023-05-26 | 2026-05-26 | 2
327941333-74679-DTLSB-11_11_2021-CUTOUTAR-1^06148004.0303402 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2021-11-11 | 2024-11-11 | 2
947984720-52609-ADMIN-03_07_2023-POLEDERP-1^06148004.0337600 | POLE | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
777133633-22709-DETAIL-08_30_2021-SVCWIND-1^06148004.0354410 | OTHER | CA-NON-TIER | Distribution | 2021-08-30 | 2024-08-30 | 2
274511410-70079-ADMIN-02_22_2023-POLEDERP-1^06148004.0354501 | POLE | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
12885596-21646-DETAIL-09_09_2021-SVCROAD-1^06148004.0355002 | OTHER | CA-NON-TIER | Distribution | 2021-09-09 | 2024-09-09 | 2
469656106-52336-DETAIL-09_27_2021-SVCROOF-1^06148004.0355204 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
777955324-82143-DETAIL-09_27_2021-GO95MLD-1^06148004.0355415 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
42651956-18716-DETAIL-09_09_2021-SVCROAD-1^06148004.0356000 | OTHER | CA-NON-TIER | Distribution | 2021-09-09 | 2024-09-09 | 2
764918144-64779-DETAIL-02_15_2022-GO95MLD-1^06147005.0337901 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
625875344-14979-DETAIL-02_14_2022-GO95MLD-1^06147005.0347000 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
144044936-16936-DETAIL-02_10_2022-GO95HV-1^06147005.0347004 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
344055636-28636-DETAIL-02_10_2022-GO95HV-1^06147005.0348205 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
749867336-79336-DETAIL-02_10_2022-GO95MLD-1^06147005.0349402 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
463181600-88509-DETAIL-02_10_2022-GO95HV-1^06147005.0350603 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
831292390-18509-DETAIL-02_10_2022-GO95HV-1^06147005.0350900 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
576331780-94179-DETAIL-02_10_2022-GO95HV-1^06147005.0350901 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
576331780-94179-DETAIL-02_10_2022-GRDRODHI-1^06147005.0350901 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
285862708-66099-DETAIL-02_10_2022-GO95MLD-1^06147005.0355000 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
826302808-17099-DETAIL-02_10_2022-GO95MLD-1^06147005.0355101 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
494227640-55579-DETAIL-02_09_2022-GO95MLD-1^06147005.0357800 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
295615477-96477-ADMIN-03_10_2023-GO95CL10-1^06148004.0160305 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
680192377-64377-DETAIL-01_16_2023-GO95MLD-1^06148004.0161305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
876075484-75909-DETAIL-01_16_2023-COPLLEAN-1^06148004.0163200 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
876075484-75909-DETAIL-01_16_2023-GUYSLACK-1^06148004.0163200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
483198524-55909-DETAIL-01_16_2023-GO95TCH-1^06148004.0163302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
246289704-63909-DETAIL-01_16_2023-GO95HV-1^06148004.0164100 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
246289704-63909-DETAIL-01_16_2023-GO95MLD-1^06148004.0164100 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
246289704-63909-DETAIL-01_16_2023-GO95MLD-2^06148004.0164100 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
299242151-28451-DETAIL-01_16_2023-GO95BLTC-1^06148004.0164120 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
299242151-28451-DETAIL-01_16_2023-GO95MLD-2^06148004.0164120 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
949933615-66909-DETAIL-01_16_2023-GO95TCH-1^06148004.0164140 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
471956314-86909-DETAIL-01_16_2023-GO95MLD-1^06148004.0164200 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
283285740-21409-DETAIL-03_02_2022-GO95HV-1^06146006.0076201 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
658882761-40001-DETAIL-03_02_2022-GRDRODHI-1^06146006.0076300 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
221476260-6860-DETAIL-03_07_2022-GO95HV-1^06146006.0076801 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
612204000-5521-DETAIL-03_07_2022-GO95BLTC-1^06146006.0076901 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
612204000-5521-DETAIL-03_07_2022-GO95MLD-1^06146006.0076901 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
126124860-54870-DETAIL-03_07_2022-GO95HV-1^06146006.0076902 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
107674680-15340-DETAIL-03_07_2022-GO95MLD-1^06146006.0076905 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
107674680-15340-DETAIL-03_07_2022-GRDRODHI-1^06146006.0076905 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
129531055-74070-DETAIL-02_07_2023-GO95HV-1^06147002.0097300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
312364171-8771-DETAIL-02_06_2023-GO95BLTC-1^06147002.0162100 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
651479536-22109-DETAIL-02_02_2023-GO95HV-1^06147002.0175901 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
54767466-44289-DETAIL-02_06_2023-GO95MLD-1^06147002.0200600 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
679530496-24361-DETAIL-02_06_2023-GO95MLD-1^06147002.0302200 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
644589296-55761-DETAIL-02_01_2023-XARMBRAC-1^06147002.0310500 | CROSSARM | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
574269526-59571-DETAIL-02_01_2023-GO95HV-1^06147002.0319500 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
957829458-59858-DETAIL-01_31_2023-GO95MLD-1^06147002.0349500 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
763119849-31891-DETAIL-01_25_2023-INSULDMG-1^06147003.0025400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
259103359-84890-DETAIL-01_25_2023-GO95HV-1^06147003.0025600 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
631305459-34241-DETAIL-01_25_2023-GO95HV-1^06147003.0025801 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
250975969-58090-DETAIL-01_25_2023-GO95HV-1^06147003.0025901 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
627560629-37741-DETAIL-01_25_2023-GO95MLD-1^06147003.0027500 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
664993709-7621-DETAIL-01_25_2023-GO95MLD-1^06147003.0027501 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
513060900-28900-DETAIL-01_24_2023-GO95TCH-1^06147003.0129501 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
633491479-50151-DETAIL-01_24_2023-GO95MLD-1^06147003.0129600 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
709793930-92551-DETAIL-01_26_2023-GO95MLD-1^06147003.0141100 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
754291754-95589-DETAIL-01_16_2023-GO95MLD-1^06148004.0164203 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
662777284-43579-DETAIL-01_16_2023-GO95HV-1^06148004.0164304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
662777284-43579-DETAIL-01_16_2023-GO95TCH-1^06148004.0164304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
478779220-60879-ADMIN-01_16_2023-GO95HV-1^06148004.0164308 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
478779220-60879-DETAIL-01_16_2023-GO95MLD-1^06148004.0164308 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
478779220-60879-DETAIL-01_16_2023-GO95MLD-2^06148004.0164308 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
901429295-70395-DETAIL-01_30_2023-GO95MLD-1^06148003.0223400 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
8305000-9789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223700 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
702887300-49789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223701 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
797174590-77789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223900 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
116242721-22579-DETAIL-01_24_2023-GO95MLD-1^06148003.0240000 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
583123811-29089-DETAIL-01_24_2023-GO95HV-1^06148003.0240100 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
355182964-58209-AUDIT-10_20_2021-SVCROAD-1^06147005.0087200 | OTHER | CA-NON-TIER | Distribution | 2021-10-20 | 2024-10-20 | 2
875720568-1042-ADMIN-02_12_2020-POLEDERP-1^06147005.0165903 | POLE | CA-NON-TIER | Distribution | 2020-02-12 | 2023-02-12 | 2
323542918-4870-DTLSB-02_18_2019-SVCDRIVE-1^06147005.0166502 | OTHER | CA-NON-TIER | Distribution | 2019-02-18 | 2024-01-18 | 2
975193187-25583-ADMIN-02_12_2020-POLEDERP-1^06147005.0166901 | POLE | CA-NON-TIER | Distribution | 2020-02-12 | 2023-02-12 | 2
246685148-40609-DETAIL-02_03_2022-GO95HV-1^06147005.0260001 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2027-02-03 | 3
903570938-70609-DETAIL-02_03_2022-GO95HV-1^06147005.0260100 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2027-02-03 | 3
903570938-70609-DETAIL-02_03_2022-GO95MLD-1^06147005.0260100 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
800369938-24779-DETAIL-02_03_2022-GO95MLD-1^06147005.0260200 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
717651370-98771-DETAIL-08_31_2020-GO95BLTC-1^06147001.0106801 | OTHER | CA-NON-TIER | Distribution | 2020-08-31 | 2025-08-31 | 3
440374834-34090-AUDIT-09_24_2020-GUYSLACK-1^06147001.0309500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2020-09-24 | 2023-09-24 | 2
383003071-51079-DETAIL-01_19_2023-GO95HV-1^06148004.0215600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
383003071-51079-DETAIL-01_19_2023-GO95MLD-1^06148004.0215600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
554531004-54209-ADMIN-01_19_2023-ENCHRW-1^06148004.0216601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
372725224-96179-DETAIL-01_19_2023-GO95MLD-1^06148004.0216701 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
225471651-21389-DETAIL-01_18_2023-GO95MLD-2^06148004.0219000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
653137285-56579-DETAIL-01_19_2023-GO95MLD-2^06148004.0204200 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
879162174-67879-DETAIL-01_19_2023-GO95MLD-1^06148004.0204601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
417652965-55109-DETAIL-01_19_2023-GO95MLD-1^06148004.0204603 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
417652965-55109-DETAIL-01_19_2023-GO95MLD-2^06148004.0204603 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
112370225-17079-DETAIL-01_18_2023-INSULDMG-1^06148004.0207100 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
308411105-49109-DETAIL-01_18_2023-COPLLEAN-1^06148004.0207101 | POLE | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
436529965-89109-DETAIL-01_18_2023-GO95MLD-1^06148004.0207301 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
720766155-36789-DETAIL-01_18_2023-GO95MLD-1^06148004.0207400 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
934189650-71172-DETAIL-01_26_2023-GRDRODHI-1^06147003.0143500 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
489952386-23386-DETAIL-01_26_2023-GO95HV-1^06147003.0168900 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
144923488-86780-DETAIL-01_30_2023-GO95MLD-1^06147003.0191000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
65878920-84180-DETAIL-01_26_2023-GO95MLD-1^06147003.0234600 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
176947210-54720-DETAIL-01_26_2023-GO95HV-1^06147003.0234601 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
392683550-49440-DETAIL-01_24_2023-GO95MLD-1^06147003.0249800 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
551260300-94141-DETAIL-01_24_2023-GO95MLD-1^06147003.0249900 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
599951468-21211-DETAIL-01_30_2023-GO95HV-1^06147003.0302800 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
39852152-78099-DETAIL-01_29_2019-GRDRODHI-1^06147004.0350401 | OTHER | CA-NON-TIER | Distribution | 2019-01-29 | 2023-12-29 | 2
951839052-19099-DETAIL-01_29_2019-GO95MLD-1^06147004.0350500 | OTHER | CA-NON-TIER | Distribution | 2019-01-29 | 2023-12-29 | 2
916931256-68199-DETAIL-10_13_2021-SVCROAD-1^06147005.0022003 | OTHER | CA-NON-TIER | Distribution | 2021-10-13 | 2024-10-13 | 2
850064195-24652-DETAIL-02_07_2023-GO95HV-1^06147002.0047300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
143465485-15080-DETAIL-02_07_2023-GO95HV-1^06147002.0047401 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
174234146-67210-DETAIL-02_06_2023-GO95MLD-1^06147002.0070000 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
572933085-16271-DETAIL-02_07_2023-GO95HV-1^06147002.0094100 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
768508151-1561-DETAIL-02_06_2023-GO95BLTC-1^06147002.0162101 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
378480644-63644-DETAIL-02_06_2023-GO95CL10-1^06147002.0162102 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
378480644-63644-DETAIL-02_06_2023-GO95MLD-1^06147002.0162102 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
8948796-20689-DETAIL-02_02_2023-GO95CL10-1^06147002.0172800 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
8948796-20689-DETAIL-02_02_2023-GO95MLD-1^06147002.0172800 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
144879586-85079-DETAIL-02_06_2023-GO95MLD-1^06147002.0200200 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
679530496-24361-DETAIL-02_06_2023-ABNDEQPM-1^06147002.0302200 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
977293595-83393-DETAIL-02_01_2023-GO95MLD-1^06147002.0310000 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
494227640-55579-DETAIL-02_09_2022-GO95HV-1^06147005.0357800 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
290037280-55509-DETAIL-02_09_2022-XARMSPCR-1^06147005.0357902 | CROSSARM | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
792664190-33172-DETAIL-02_10_2022-GO95MLD-1^06147005.0360202 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
131609820-56089-DETAIL-02_28_2022-GO95HV-1^06147006.0308100 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
207154661-41340-DETAIL-02_28_2022-GO95HV-1^06147006.0311901 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
759027411-38579-AUDIT-02_22_2017-SVCROAD-1^06147006.0314901 | OTHER | CA-NON-TIER | Distribution | 2017-02-22 | 2022-01-22 | 2
991003321-91289-DETAIL-03_02_2022-CLRTOUCH-1^06147006.0319600 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
466167090-57931-DETAIL-03_02_2022-GO95HV-1^06147006.0320701 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
968283645-60573-DETAIL-03_01_2022-GO95HV-1^06147006.0321000 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
603995340-71811-DETAIL-03_01_2022-GO95HV-1^06147006.0321100 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
876626450-71842-DETAIL-03_02_2022-GO95HV-1^06147006.0321401 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
792664190-33172-DETAIL-02_10_2022-GO95TCH-1^06147005.0360202 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2025-02-10 | 2
498920231-60671-DTLSB-03_23_2022-CONDFRAY-1^06146005.0242100 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
498920231-60671-DTLSB-03_23_2022-GO95HV-1^06146005.0242100 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
575319014-11271-DTLSB-03_22_2022-ABNDEQPM-1^06146005.0242901 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
575319014-11271-DTLSB-03_22_2022-GO95BLTC-1^06146005.0242901 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
926178395-28542-DTLSB-03_23_2022-GO95HV-1^06146005.0243201 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
911818733-14882-DTLSB-03_22_2022-GO95MLD-1^06146005.0243900 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
587237983-25091-DTLSB-03_23_2022-GO95MLD-1^06146005.0247801 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
783409483-87142-DTLSB-03_23_2022-GO95HV-1^06146005.0247900 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
894836844-39512-DETAIL-02_28_2022-ANCHIDLE-1^06146005.0272601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
991487344-15333-DETAIL-02_28_2022-XARMSPCR-2^06146005.0273600 | CROSSARM | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
172248263-23079-DETAIL-03_02_2022-GO95MLD-1^06146005.0278901 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
305261443-66250-DETAIL-03_02_2022-GO95HV-1^06146005.0279900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
327919604-74779-DETAIL-02_03_2022-GO95MLD-1^06147005.0270201 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
575395893-32979-DETAIL-02_03_2022-INSULDMG-1^06147005.0270301 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
891782883-10579-DETAIL-02_03_2022-GO95MLD-1^06147005.0270402 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
802734433-16209-DETAIL-02_03_2022-INSULDMG-1^06147005.0270800 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
338650024-69079-DETAIL-02_09_2022-GUYHINS-1^06147005.0274700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
913195574-67882-DETAIL-02_09_2022-RISECLMB-1^06147005.0277700 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
15354184-81079-DETAIL-02_09_2022-GO95MLD-1^06147005.0277802 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
747631874-79679-DETAIL-02_09_2022-ENCHRW-1^06147005.0278800 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
516673409-74379-DETAIL-02_01_2022-GO95HV-1^06147005.0263701 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2027-02-01 | 3
397422689-70279-DETAIL-02_01_2022-GO95MLD-1^06147005.0263800 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2027-02-01 | 3
386646999-59979-DETAIL-01_31_2022-GO95MLD-1^06147005.0263806 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
694525279-27379-DETAIL-02_01_2022-SVCROAD-1^06147005.0264600 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
815329460-46542-DETAIL-01_25_2023-GO95TCH-1^06148003.0356900 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
906223471-35279-DETAIL-01_11_2023-SVCROAD-1^06148004.0133200 | OTHER | CA-NON-TIER | Distribution | 2023-01-11 | 2026-01-11 | 2
887057583-6679-DETAIL-01_11_2023-SVCROAD-1^06148004.0137200 | OTHER | CA-NON-TIER | Distribution | 2023-01-11 | 2026-01-11 | 2
887057583-6679-AUDIT-01_18_2023-SVCROAD-1^06148004.0137200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
22347603-9279-DETAIL-01_11_2023-SVCROAD-1^06148004.0139200 | OTHER | CA-NON-TIER | Distribution | 2023-01-11 | 2026-01-11 | 2
620195621-17479-ADMIN-01_12_2023-ENCHRW-1^06148004.0140200 | OTHER | CA-NON-TIER | Distribution | 2023-01-12 | 2026-01-12 | 2
629846721-85089-ADMIN-01_12_2023-ENCHRW-1^06148004.0142200 | OTHER | CA-NON-TIER | Distribution | 2023-01-12 | 2026-01-12 | 2
52188434-41479-AUDIT-02_16_2023-ABNDEQPM-1^06148004.0160302 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
205514366-16366-DETAIL-01_16_2023-GO95MLD-1^06148004.0160304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
295615477-96477-DETAIL-01_16_2023-GO95MLD-1^06148004.0160305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
572952227-24227-DETAIL-01_16_2023-GO95MLD-1^06148004.0161304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
13866733-78679-DETAIL-04_14_2022-GO95HV-1^06146005.0153000 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
212371043-28050-DETAIL-04_14_2022-GO95HV-1^06146005.0153100 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
430593883-80379-DETAIL-04_14_2022-GO95HV-1^06146005.0155901 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
190572364-89909-DETAIL-04_14_2022-SVCENTCO-1^06146005.0155902 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
645630963-70861-DETAIL-04_14_2022-GO95HV-1^06146005.0158300 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
119717064-48289-DETAIL-02_24_2022-GO95MLD-1^06146005.0160100 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
119717064-48289-DETAIL-02_24_2022-SVCROAD-1^06146005.0160100 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
689957954-42081-DETAIL-02_24_2022-GUYSLACK-1^06146005.0160101 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
796710144-85282-DETAIL-02_24_2022-GO95HV-1^06146005.0161101 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
845234334-68442-DETAIL-02_24_2022-GO95MLD-1^06146005.0163100 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
379777734-36330-DETAIL-02_24_2022-CONDFRAY-1^06146005.0163101 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
821826013-78362-DETAIL-02_22_2022-GO95MLD-1^06146005.0165403 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2027-02-22 | 3
625148304-26360-DETAIL-01_12_2023-GO95MLD-1^06240004.0076301 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
700016313-72660-DETAIL-01_12_2023-GO95MLD-1^06240004.0076340 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
854603392-19933-DETAIL-01_24_2023-GO95TCH-1^06240004.0078500 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
928336936-71480-DETAIL-01_24_2023-GO95MLD-1^06240004.0078600 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
716568165-90770-DETAIL-01_24_2023-GO95MLD-1^06240004.0078800 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
738747298-38070-DETAIL-01_23_2023-GO95MLD-1^06240004.0079100 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
738747298-38070-DETAIL-01_23_2023-POLETOP-1^06240004.0079100 | POLE | CA-TIER-2 | Distribution | 2023-01-23 | 2024-01-23 | 2
695524444-96060-DETAIL-01_24_2023-GRDRODHI-1^06240004.0079401 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
695524444-96060-DETAIL-01_24_2023-GRDRODHI-2^06240004.0079401 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
994076064-38960-DETAIL-01_24_2023-GO95MLD-1^06240004.0079406 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
637478461-43433-DETAIL-01_24_2023-GO95HV-1^06240004.0079501 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2028-01-24 | 3
639166423-95051-DETAIL-02_24_2022-GO95MLD-1^06146005.0214700 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
951864870-69870-DETAIL-02_24_2022-GO95TCH-1^06146005.0214711 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
403744953-42450-DETAIL-02_24_2022-GO95HV-1^06146005.0214901 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
349122566-64899-DETAIL-02_24_2022-GO95MLD-1^06146005.0215000 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
349122566-64899-DETAIL-02_24_2022-SVCROAD-1^06146005.0215000 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
754293653-54279-DETAIL-02_22_2022-GO95HV-1^06146005.0215400 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2027-02-22 | 3
161721293-44600-DETAIL-02_24_2022-GO95HV-1^06146005.0215700 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
103351001-5540-DTLSB-03_21_2022-XARMSPCR-1^06146005.0146002 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
865187726-56389-DTLSB-03_21_2022-SVCROAD-1^06146005.0146301 | OTHER | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
890073013-17592-DETAIL-02_21_2022-SVCROAD-1^06146005.0164003 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
728524943-43601-DETAIL-02_22_2022-SVCRUBLG-1^06146005.0165402 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
821826013-78362-DETAIL-02_22_2022-GUYSLACK-1^06146005.0165403 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
813046020-26242-DETAIL-03_07_2022-ABNDEQPM-1^06146006.0066700 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
813046020-26242-DETAIL-03_07_2022-GO95BLTC-1^06146006.0066700 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
542547351-67431-DETAIL-03_01_2022-GRDRODHI-1^06146006.0068900 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
813031981-45242-DETAIL-03_01_2022-GO95MLD-1^06146006.0069400 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
182475940-96940-DETAIL-03_08_2022-GUYHINS-1^06146006.0070501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
887281040-23040-DETAIL-03_08_2022-GO95TCH-1^06146006.0070502 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
763303481-94779-DETAIL-03_08_2022-GO95MLD-1^06146006.0070700 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
368017295-39310-DTLSB-03_17_2022-GO95HV-1^06146005.0240901 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
378334331-9330-DTLSB-03_22_2022-GO95HV-1^06146005.0241901 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
378334331-9330-DTLSB-03_22_2022-INSULDMG-1^06146005.0241901 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
800198651-24292-DTLSB-03_23_2022-GO95HV-1^06146005.0242000 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
299455133-8540-DTLSB-03_23_2022-GO95MLD-1^06146005.0242700 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
779927979-73279-DETAIL-02_22_2022-GO95TCH-1^06146005.0096302 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
900142993-87209-DETAIL-02_22_2022-GO95MLD-1^06146005.0096400 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
564675373-36809-DETAIL-02_22_2022-GO95HV-1^06146005.0096700 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2027-02-22 | 3
170554803-7279-DETAIL-02_22_2022-GO95MLD-1^06146005.0096800 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
26416729-88079-AUDIT-04_04_2022-GO95HV-1^06146005.0098302 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
84688227-46120-DETAIL-03_03_2022-GO95MLD-1^06146005.0128901 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
176946727-54720-DETAIL-03_08_2022-GO95HV-1^06146005.0129901 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
794517223-88972-DTLSB-03_22_2022-CLRTOUCH-1^06146005.0130700 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
794517223-88972-DTLSB-03_22_2022-GO95MLD-1^06146005.0130700 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
794517223-88972-DTLSB-03_22_2022-GUYHINS-1^06146005.0130700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
188942313-30130-DTLSB-03_22_2022-GO95HV-1^06146005.0130900 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
795631263-25472-DTLSB-03_22_2022-GO95TCH-1^06146005.0133002 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
841491371-34371-DETAIL-02_24_2022-GO95MLD-1^06146005.0218000 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
460495135-29979-DTLSB-03_22_2022-GUYHINS-1^06146005.0235401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
117090753-6560-DTLSB-03_17_2022-GO95MLD-1^06146005.0236400 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
93009843-81730-DTLSB-03_17_2022-GO95MLD-1^06146005.0236902 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
867186494-91512-DTLSB-03_17_2022-ABNDEQPM-1^06146005.0238900 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
583573833-59391-DTLSB-03_17_2022-INSULDMG-1^06146005.0239600 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
816658635-81735-DTLSB-03_17_2022-GO95MLD-1^06146005.0240400 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
816658635-81735-DTLSB-03_17_2022-GO95TCH-1^06146005.0240400 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
816658635-81735-DTLSB-03_17_2022-GUYHINS-1^06146005.0240400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
184535115-28920-DTLSB-03_17_2022-ABNDEQPM-1^06146005.0240600 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
184535115-28920-DTLSB-03_17_2022-GO95HV-1^06146005.0240600 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
964711105-24363-DTLSB-03_17_2022-GO95HV-1^06146005.0240701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
397422689-70279-DETAIL-02_01_2022-GUYHINS-1^06147005.0263800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
592331439-37809-DETAIL-02_02_2022-GO95TCH-1^06147005.0264101 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
970101448-38289-DETAIL-02_01_2022-GO95MLD-1^06147005.0264303 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
216110409-16389-DETAIL-01_31_2022-GO95MLD-1^06147005.0264500 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
958201979-39289-DETAIL-01_31_2022-GO95HV-1^06147005.0264900 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2027-01-31 | 3
188384368-29079-DETAIL-02_01_2022-GO95MLD-1^06147005.0265405 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
188384368-29079-DETAIL-02_01_2022-SVCWIND-1^06147005.0265405 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
546944058-85979-DETAIL-02_01_2022-GO95MLD-1^06147005.0265406 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
243183958-33979-DETAIL-02_01_2022-GO95HV-1^06147005.0265408 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2027-02-01 | 3
119672490-30590-DETAIL-01_31_2022-GO95MLD-1^06147005.0265704 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
748986849-38679-DETAIL-01_31_2022-GO95HV-1^06147005.0265800 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2027-01-31 | 3
748986849-38679-DETAIL-01_31_2022-GO95MLD-1^06147005.0265800 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
801323423-16379-DETAIL-02_03_2022-GO95MLD-1^06147005.0270900 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
338650024-69079-DETAIL-02_09_2022-GO95MLD-1^06147005.0274700 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
338650024-69079-DETAIL-02_09_2022-GO95TCH-1^06147005.0274700 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
913195574-67882-DETAIL-02_09_2022-GO95TCH-1^06147005.0277700 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
15354184-81079-DETAIL-02_09_2022-GO95HV-1^06147005.0277802 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
475022194-92279-DETAIL-01_31_2022-GO95MLD-1^06147005.0279600 | OTHER | CA-NON-TIER | Distribution | 2022-01-31 | 2025-01-31 | 2
701374737-35737-DETAIL-02_09_2022-ABNDEQPM-1^06147005.0279702 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
701374737-35737-DETAIL-02_09_2022-GO95HV-1^06147005.0279702 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
450559364-54479-DETAIL-02_09_2022-GO95BLTC-1^06147005.0282000 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
450559364-54479-DETAIL-02_09_2022-GO95MLD-1^06147005.0282000 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
450559364-54479-DETAIL-02_09_2022-GRDRODHI-1^06147005.0282000 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
788891553-11209-DETAIL-02_09_2022-GO95MLD-1^06147005.0283400 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
69898834-71934-DTLSB-03_31_2022-GO95HV-1^06145006.0218100 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
528873533-96979-DTLSB-03_31_2022-ENCHRW-1^06145006.0223502 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
31311803-39779-DTLSB-03_24_2022-CLRTOUCH-1^06145006.0280800 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-24 | 2025-03-24 | 2
31311803-39779-DTLSB-03_24_2022-GO95MLD-1^06145006.0280800 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2025-03-24 | 2
40259583-8979-DTLSB-03_24_2022-GO95HV-1^06145006.0280801 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
756812343-88479-DTLSB-03_31_2022-GO95MLD-1^06145006.0287801 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
570144293-79979-DTLSB-03_31_2022-GO95MLD-1^06145006.0299500 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
41674993-31979-DTLSB-03_31_2022-GO95TCH-1^06145006.0299501 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
41674993-31979-DTLSB-03_31_2022-GUYHINS-1^06145006.0299501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
199260071-9240-DETAIL-02_01_2023-GO95HV-1^06146002.0062300 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
650109321-51981-DETAIL-02_01_2023-GO95MLD-1^06146002.0074600 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
599587531-13911-DETAIL-02_01_2023-GO95HV-1^06146002.0075301 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
794517223-88972-DTLSB-03_22_2022-GO95TCH-1^06146005.0130700 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
240722613-73380-DTLSB-03_22_2022-ABNDEQPM-1^06146005.0130801 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
240722613-73380-DTLSB-03_22_2022-GO95MLD-1^06146005.0130801 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
701326954-9121-DTLSB-03_22_2022-GO95MLD-1^06146005.0133000 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
747092139-23139-DTLTRT-03_22_2022-GUYNOINS-1^06146005.0133004 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
906549974-38952-DTLSB-03_22_2022-GO95HV-1^06146005.0135000 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
795237713-61972-DTLSB-03_22_2022-GO95HV-1^06146005.0137200 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
22220644-67950-DTLSB-03_22_2022-GO95HV-1^06146005.0137202 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
421520668-60668-DETAIL-02_22_2022-SVCROAD-1^06146005.0165601 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
375721373-27420-DETAIL-02_22_2022-GO95MLD-1^06146005.0169500 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
375721373-27420-DETAIL-02_22_2022-GRDRODHI-1^06146005.0169500 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
27411273-42970-DETAIL-02_22_2022-SVCENTBK-1^06146005.0169600 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
519458416-38101-DTLSB-03_28_2022-GO95MLD-1^06144006.0164001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
519458416-38101-DTLSB-03_28_2022-GO95TCH-1^06144006.0164001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
665835536-81021-DTLSB-03_28_2022-GO95HV-1^06144006.0164006 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
654916486-77491-DTLSB-03_28_2022-GO95CL10-1^06144006.0168001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
654916486-77491-DTLSB-03_28_2022-GRDRODHI-1^06144006.0168001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
569280483-88571-DTLSB-03_30_2022-GO95HV-1^06144006.0191600 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
358071673-78800-DTLSB-03_30_2022-GO95MLD-1^06144006.0192600 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
906244163-50679-DTLSB-03_30_2022-GO95MLD-1^06144006.0192601 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
906244163-50679-DTLSB-03_30_2022-GUYSLACK-1^06144006.0192601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
888707185-60285-DTLSB-03_30_2022-GO95HV-1^06144006.0192700 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
27475285-69285-DTLSB-03_30_2022-GO95MLD-1^06144006.0192800 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
342225090-56190-DTLSB-03_30_2022-GO95MLD-1^06144006.0193501 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
69949653-73390-DTLSB-03_17_2022-GO95MLD-1^06146005.0239900 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
69949653-73390-DTLSB-03_17_2022-SVCROAD-1^06146005.0239900 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
816658635-81735-DTLSB-03_17_2022-GO95HV-1^06146005.0240400 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
220006335-22435-DTLSB-03_17_2022-GO95HV-1^06146005.0240601 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
677159881-32251-DETAIL-03_01_2022-GO95MLD-1^06146006.0053401 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
140306311-39480-DETAIL-03_01_2022-GO95HV-1^06146006.0053600 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
856150941-56672-DETAIL-03_01_2022-GO95BLTC-1^06146006.0054201 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
856150941-56672-DETAIL-03_01_2022-GO95MLD-1^06146006.0054201 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
856150941-56672-DETAIL-03_01_2022-INSULDMG-1^06146006.0054201 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
353207231-20700-DETAIL-03_08_2022-GO95MLD-1^06146006.0060100 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
251870621-59790-DETAIL-03_07_2022-GO95HV-1^06146006.0063300 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
251870621-59790-DETAIL-03_07_2022-GO95MLD-1^06146006.0063300 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
867678891-1222-DETAIL-03_07_2022-GO95MLD-1^06146006.0065400 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
165429452-81610-DETAIL-02_08_2023-GO95BLTC-1^06145002.0047800 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
156854463-60390-DTLSB-03_29_2022-GO95HV-1^06144006.0213900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
156854463-60390-DTLSB-03_29_2022-GO95MLD-1^06144006.0213900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
350071523-29890-DTLSB-03_28_2022-POLETOP-1^06144006.0216900 | POLE | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
983151223-8903-DTLSB-03_28_2022-INSULDMG-1^06144006.0217900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
380397813-17830-ADMIN-10_27_2023-POLEREPL-1^06144006.0218900 | POLE | CA-NON-TIER | Distribution | 2023-10-27 | 2026-10-27 | 2
71394683-51200-DTLSB-03_28_2022-GO95HV-1^06144006.0220901 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
71394683-51200-DTLSB-03_28_2022-GUYLOINS-1^06144006.0220901 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
165429452-81610-DETAIL-02_08_2023-GO95MLD-1^06145002.0047800 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
421437103-11179-DTLSB-03_23_2022-GO95HV-1^06145006.0173800 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
226545582-20079-DTLSB-03_24_2022-GO95MLD-1^06145006.0210000 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
22382176-83989-DETAIL-01_17_2023-CONDFRAY-1^06148004.0175001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
275013566-23989-DETAIL-01_17_2023-GO95HV-1^06148004.0175200 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
180651025-42009-DETAIL-01_16_2023-COPLLEAN-1^06148004.0177101 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
677568135-52009-DETAIL-01_16_2023-COPLLEAN-1^06148004.0177200 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
529958635-13009-DETAIL-01_16_2023-COPLLEAN-1^06148004.0177300 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
86357154-49909-DETAIL-01_16_2023-INSULDMG-1^06148004.0177301 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
298799715-88909-DETAIL-01_16_2023-COPLLEAN-1^06148004.0179300 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
113965564-73479-DETAIL-01_16_2023-SVCROAD-1^06148004.0179301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
993326006-57689-DETAIL-01_10_2023-GO95MLD-1^06148004.0180201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
519764185-84479-DETAIL-01_10_2023-GO95MLD-1^06148004.0187200 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
519764185-84479-ADMIN-03_10_2023-GO95CL10-1^06148004.0187200 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
16724645-58889-DETAIL-01_10_2023-GO95MLD-1^06148004.0187203 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
401974173-24250-DETAIL-02_09_2023-GO95MLD-1^06146004.0065101 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
575924853-45671-DETAIL-02_09_2023-GO95MLD-1^06146004.0065400 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
200633763-78840-DETAIL-02_09_2023-GO95MLD-1^06146004.0066700 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
757121563-38571-DETAIL-02_09_2023-GO95MLD-1^06146004.0066701 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
92130843-47030-DETAIL-02_09_2023-GO95MLD-1^06146004.0066800 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
343335043-31390-DETAIL-02_09_2023-GO95MLD-1^06146004.0067901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
529074763-63711-DETAIL-02_09_2023-GO95MLD-1^06146004.0076800 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
746174593-61841-DETAIL-02_09_2023-GO95MLD-1^06146004.0077200 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
629655493-29241-DETAIL-02_09_2023-GO95MLD-1^06146004.0077400 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
153838793-6890-DETAIL-02_09_2023-GO95MLD-1^06146004.0077500 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
77524493-59500-DETAIL-02_09_2023-GO95MLD-1^06146004.0077601 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
124546103-82070-DETAIL-02_09_2023-GO95MLD-1^06146004.0078000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
312875624-72029-DETAIL-05_04_2022-SVCNEUT-1^06143013.0190401 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
600831394-39629-DETAIL-05_04_2022-GUYHINS-1^06143013.0190501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
674784334-18229-DETAIL-05_04_2022-GO95MLD-1^06143013.0190602 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
513131154-84729-DETAIL-05_04_2022-GO95MLD-1^06143013.0190802 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
969597924-20829-DETAIL-05_02_2022-GO95MLD-1^06143013.0191302 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
521426614-79729-DETAIL-05_02_2022-GO95MLD-1^06143013.0191500 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
86423704-18729-DETAIL-05_04_2022-GO95MLD-1^06143013.0191600 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
609515587-55587-DETAIL-05_04_2022-GO95MLD-1^06143013.0191601 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
351307794-57729-DETAIL-05_04_2022-GO95HV-1^06143013.0191700 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
425405884-17729-DETAIL-05_04_2022-GO95HV-1^06143013.0191800 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
496700574-85729-DETAIL-05_02_2022-GO95HV-1^06143013.0191900 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
312768164-90829-DETAIL-05_02_2022-GO95HV-1^06143013.0192301 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
747483804-39529-DETAIL-05_04_2022-SVCNEUT-1^06143013.0192600 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
350912681-71979-DETAIL-01_31_2023-GO95MLD-1^06146002.0097100 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
574997491-89479-DETAIL-01_31_2023-GO95CL10-1^06146002.0153701 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
498374562-99071-DETAIL-02_08_2023-GO95HV-1^06146002.0272100 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
419336542-67570-DETAIL-02_08_2023-GO95HV-1^06146002.0274700 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
742110332-70731-DETAIL-02_08_2023-GO95MLD-1^06146002.0274901 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
831290101-20492-DETAIL-01_31_2023-GO95MLD-1^06146002.0153500 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
959516781-69479-DETAIL-01_31_2023-GO95MLD-1^06146002.0153700 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
574997491-89479-DETAIL-01_31_2023-GO95MLD-1^06146002.0153701 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
345562542-26690-DETAIL-02_08_2023-GO95HV-1^06146002.0274800 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
614241522-26621-DETAIL-02_08_2023-GO95MLD-1^06146002.0334300 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
955586122-90243-DETAIL-02_08_2023-GO95MLD-1^06146002.0335301 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
985911973-26913-DETAIL-02_09_2023-GO95MLD-1^06146004.0065100 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
745311161-5941-DETAIL-03_08_2022-GO95MLD-1^06146006.0060700 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
251870621-59790-DETAIL-03_07_2022-GUYHINS-1^06146006.0063300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
413348501-10460-DETAIL-03_07_2022-GO95HV-1^06146006.0064300 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
339335331-24880-DETAIL-03_07_2022-GO95HV-1^06146006.0065502 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
371248189-23120-DETAIL-03_07_2022-GO95HV-1^06146006.0065701 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
858762879-81982-DETAIL-03_07_2022-SVCENTCO-1^06146006.0065801 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
712031850-78551-DETAIL-03_07_2022-GO95MLD-1^06146006.0066001 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
813046020-26242-DETAIL-03_07_2022-GO95MLD-1^06146006.0066700 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
754634031-81861-DETAIL-03_07_2022-GO95MLD-1^06146006.0067002 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
542547351-67431-DETAIL-03_01_2022-GO95MLD-1^06146006.0068900 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
53256931-56061-DETAIL-03_07_2022-INSULDMG-1^06146006.0084701 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
667362414-11514-DETAIL-03_01_2022-GO95BLTC-1^06146006.0092600 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
240810804-4580-DETAIL-02_24_2022-GO95HV-1^06146005.0286601 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
229337214-48960-DETAIL-02_24_2022-GO95HV-1^06146005.0287501 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
807318204-60212-DETAIL-02_24_2022-GO95MLD-1^06146005.0287901 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
982914504-33899-DETAIL-02_24_2022-GO95TCH-1^06146005.0287902 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
869798934-64999-DETAIL-02_24_2022-GO95HV-1^06146005.0289501 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
528532224-7211-DETAIL-02_24_2022-GO95HV-1^06146005.0289602 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
916139894-91792-DETAIL-02_21_2022-GO95HV-1^06146005.0297900 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
677159881-32251-DETAIL-03_01_2022-GO95TCH-1^06146006.0053401 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
579088211-96881-ADMIN-07_04_2022-POLEDERP-1^06146006.0054000 | POLE | CA-NON-TIER | Distribution | 2022-07-04 | 2025-07-04 | 2
807406191-95212-DETAIL-03_01_2022-SVCENTCO-1^06146006.0054100 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
636540611-95879-DETAIL-03_01_2022-GO95MLD-1^06146006.0054102 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
173092121-42410-DETAIL-03_01_2022-GO95MLD-1^06146006.0055200 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
598992401-67311-DTLSB-03_29_2022-GO95MLD-1^06144006.0102900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
108564033-24940-DETAIL-04_06_2023-GO95HV-1^06143014.0232701 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
492241556-52529-DETAIL-04_06_2023-GRDRODHI-1^06143014.0232800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
635670793-17751-DETAIL-04_06_2023-ABNDEQPM-1^06143014.0234700 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
754813113-41061-ADMIN-04_21_2023-GO95TCH-1^06143014.0235802 | OTHER | CA-TIER-2 | Distribution | 2023-04-21 | 2026-04-21 | 2
401213923-20950-DETAIL-04_06_2023-GUYHINS-1^06143014.0236702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
60492413-54470-DETAIL-04_06_2023-GO95MLD-1^06143014.0236800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
719646384-40484-DETAIL-03_28_2023-GO95HV-1^06143016.0322101 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
815944931-27342-DTLSB-03_29_2022-GO95HV-1^06144006.0035100 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
815944931-27342-DTLSB-03_29_2022-GUYSLACK-1^06144006.0035100 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
763174131-17389-DTLSB-03_29_2022-GO95HV-1^06144006.0098800 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
42911721-67740-DTLSB-03_29_2022-GO95HV-1^06144006.0100901 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
53772211-1360-DTLSB-03_29_2022-GO95HV-1^06144006.0101900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
787381353-4353-DETAIL-02_16_2022-SVCENTCO-1^06146005.0022400 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
353707103-100-DETAIL-02_09_2023-GO95MLD-1^06146004.0077300 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
744016303-71841-DETAIL-02_09_2023-GO95MLD-1^06146004.0077301 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
81118993-95710-DETAIL-02_09_2023-GO95MLD-1^06146004.0078100 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
86296023-32220-DETAIL-02_08_2023-GO95MLD-1^06146004.0079000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
143018823-78880-DETAIL-02_08_2023-GO95MLD-1^06146004.0080000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
565774733-30661-DETAIL-02_08_2023-GO95MLD-1^06146004.0083001 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
267304143-78800-DETAIL-02_09_2023-GO95MLD-1^06146004.0084000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
824982243-68282-DETAIL-02_09_2023-GO95MLD-1^06146004.0085000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
424907943-50080-DETAIL-02_09_2023-INSULDMG-1^06146004.0085002 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
498488633-89171-DETAIL-02_09_2023-GO95TCH-1^06146004.0101000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
923764724-52532-DETAIL-02_09_2023-GO95MLD-1^06146004.0160900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
902996338-62629-DETAIL-04_27_2022-GO95MLD-1^06143012.0244304 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
786558309-11829-DETAIL-04_28_2022-GO95HV-1^06143012.0244500 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
13026519-14229-DETAIL-05_02_2022-GO95MLD-1^06143012.0244501 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
200340869-67629-DETAIL-05_02_2022-GO95MLD-1^06143012.0244600 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
277721499-47929-DETAIL-04_27_2022-GO95MLD-1^06143012.0240501 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
134119429-48329-DETAIL-04_27_2022-GRDRODHI-1^06143012.0240601 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
134119429-48329-DETAIL-04_27_2022-SVCROAD-1^06143012.0240601 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
926342090-18329-DETAIL-04_27_2022-CUTOUTAR-1^06143012.0240801 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
522408421-93629-DETAIL-04_27_2022-GO95HV-1^06143012.0241000 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
479348011-88529-DETAIL-04_27_2022-GO95HV-1^06143012.0241001 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
792615791-72629-DETAIL-04_27_2022-GO95MLD-1^06143012.0241200 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
185034190-83629-DETAIL-04_27_2022-GRDRODHI-1^06143012.0241601 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
220606141-58529-DETAIL-04_27_2022-GO95MLD-1^06143012.0241701 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
818964091-63329-DETAIL-04_27_2022-SVCNEUT-1^06143012.0241800 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
693615042-15529-DETAIL-04_27_2022-GO95MLD-1^06143012.0243000 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
700290849-13529-DETAIL-04_28_2022-GO95HV-1^06143012.0243800 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
188841309-54429-DETAIL-04_28_2022-GO95MLD-1^06143012.0243802 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
112307191-20829-DETAIL-05_02_2022-GO95MLD-1^06143012.0244100 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
137137698-66529-DETAIL-04_27_2022-GO95MLD-1^06143012.0244101 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
879480958-88229-DETAIL-05_02_2022-GO95MLD-1^06143012.0244302 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
200340869-67629-DETAIL-05_02_2022-GRDRODHI-1^06143012.0244600 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
337112869-75129-DETAIL-05_02_2022-GO95MLD-1^06143012.0244701 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
690681250-46129-DETAIL-05_02_2022-GO95MLD-1^06143012.0244801 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
952283568-72129-DETAIL-04_28_2022-GO95HV-1^06143012.0245300 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
544483250-39429-DETAIL-05_02_2022-GO95HV-1^06143012.0245400 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
282555460-68629-DETAIL-05_02_2022-SVCROAD-1^06143012.0245800 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
164830414-54210-DETAIL-02_09_2023-GO95MLD-1^06146004.0160901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
526515324-61311-DETAIL-02_09_2023-GO95MLD-1^06146004.0161901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
344626024-72090-DETAIL-02_09_2023-GO95HV-1^06146004.0162900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
779473434-62032-DETAIL-02_09_2023-GO95MLD-1^06146004.0164900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
461605734-15521-DETAIL-02_09_2023-GO95MLD-1^06146004.0165900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
461605734-15521-DETAIL-02_09_2023-GRDRODHI-1^06146004.0165900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
276052544-97510-DETAIL-02_09_2023-GO95MLD-1^06146004.0166900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
674763343-11641-DETAIL-02_09_2023-INSULDMG-1^06146004.0176300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
294064463-79230-DETAIL-02_09_2023-GO95MLD-1^06146004.0177200 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
294064463-79230-ADMIN-03_06_2023-GO95TCH-1^06146004.0177200 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
482773969-35151-DETAIL-02_16_2022-GO95HV-1^06146005.0010100 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
964030289-27363-DETAIL-02_16_2022-GO95MLD-1^06146005.0010300 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
601023599-56829-DETAIL-05_02_2022-GO95MLD-1^06143012.0246901 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
925694605-15605-DETAIL-05_02_2022-CLRTOUCH-1^06143012.0247100 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
854274429-65329-DETAIL-04_28_2022-GO95MLD-1^06143012.0247400 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
610766411-49129-DETAIL-05_02_2022-GO95MLD-1^06143012.0247800 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
599603921-90229-DETAIL-05_02_2022-GO95TCH-1^06143012.0247901 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
450430869-88329-DETAIL-04_28_2022-GO95MLD-1^06143012.0248403 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
683362424-16429-DETAIL-04_27_2022-GO95MLD-1^06143012.0253900 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
484263964-89729-DETAIL-04_21_2022-GO95HV-1^06143012.0254000 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
973772673-95529-DETAIL-04_25_2022-GO95MLD-1^06143012.0254400 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
388632204-43204-DETAIL-04_25_2022-GO95MLD-1^06143012.0254602 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
17814825-86329-DETAIL-04_27_2022-GO95TCH-1^06143012.0254705 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
77129703-96529-DETAIL-04_27_2022-GO95MLD-1^06143012.0254804 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
815835603-78142-DETAIL-02_22_2022-GO95MLD-1^06146005.0165404 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
280249568-69568-DETAIL-02_22_2022-INSULDMG-1^06146005.0165600 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
421520668-60668-DETAIL-02_22_2022-GUYHINS-1^06146005.0165601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
257348294-43590-DETAIL-02_21_2022-GO95CL10-1^06146005.0167200 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
544019995-46231-DETAIL-02_21_2022-INSULDMG-1^06146005.0170300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
774464535-78189-DETAIL-02_22_2022-GO95MLD-1^06146005.0170400 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
947761009-55009-DETAIL-02_21_2022-GO95HV-1^06146005.0170701 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
531926554-55221-DETAIL-02_21_2022-GO95HV-1^06146005.0171600 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
549625195-5541-DETAIL-02_28_2022-GO95MLD-1^06146005.0176101 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
737231465-70721-DETAIL-02_23_2022-GO95MLD-1^06146005.0200500 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
130950635-47079-DETAIL-02_23_2022-GO95MLD-1^06146005.0202701 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
742649665-7731-DETAIL-02_21_2022-GO95HV-1^06146005.0203800 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
752491174-15629-DETAIL-04_20_2022-SVCENTCO-1^06143012.0364002 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
747914904-88329-DETAIL-04_28_2022-ABNDEQPM-1^06143012.0256603 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
670192869-84869-DETAIL-04_26_2022-GO95MLD-1^06143012.0257302 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
918469493-37629-DETAIL-04_26_2022-CLRTOUCH-1^06143012.0257502 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
69780505-37129-DETAIL-04_26_2022-RISEGRD-1^06143012.0258201 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
487976594-8429-DETAIL-04_25_2022-GO95MLD-1^06143012.0258202 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
24290384-47429-DETAIL-04_26_2022-GO95MLD-1^06143012.0258203 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
156565904-16129-DETAIL-04_25_2022-GO95MLD-1^06143012.0259100 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
746167311-71629-DETAIL-04_19_2022-GO95MLD-1^06143012.0360000 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
746167311-71629-DETAIL-04_19_2022-GRDRODHI-1^06143012.0360000 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
927703333-79229-DETAIL-04_19_2022-GO95CL10-1^06143012.0360004 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
927703333-79229-DETAIL-04_19_2022-GO95TCH-1^06143012.0360004 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
222667223-10629-DETAIL-04_27_2022-GO95HV-1^06143012.0254901 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
222667223-10629-DETAIL-04_27_2022-GO95MLD-1^06143012.0254901 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
480727694-51229-DETAIL-04_25_2022-GO95MLD-1^06143012.0251101 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
30810703-95329-DETAIL-04_25_2022-GO95MLD-1^06143012.0252700 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
562860264-99129-DETAIL-04_25_2022-GO95MLD-1^06143012.0253300 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
426931054-49229-DETAIL-04_25_2022-GO95MLD-1^06143012.0253500 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
142211583-88729-DETAIL-04_25_2022-GO95TCH-1^06143012.0253502 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
257274773-3329-DETAIL-04_25_2022-POLETOP-1^06143012.0253600 | POLE | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
679519073-82329-DETAIL-04_25_2022-GO95MLD-1^06143012.0253601 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
175917923-7329-DETAIL-04_27_2022-GO95MLD-1^06143012.0254702 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
517711934-74229-DETAIL-04_27_2022-GO95MLD-1^06143012.0254704 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
678211843-98161-DTLSB-03_30_2022-ABNDEQPM-1^06144006.0193600 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
485899803-93351-DTLSB-03_30_2022-ABNDEQPM-1^06144006.0194900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
283033556-86220-DTLSB-03_28_2022-GO95TCH-1^06144006.0165003 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
604381566-38079-DTLSB-03_28_2022-GO95HV-1^06144006.0166000 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
909700606-59872-DTLSB-03_28_2022-GO95BLTC-1^06144006.0166001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
909700606-59872-DTLSB-03_28_2022-GO95HV-1^06144006.0166001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
120898296-99860-DTLSB-03_28_2022-GO95MLD-1^06144006.0168000 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
654916486-77491-DTLSB-03_28_2022-GO95MLD-1^06144006.0168001 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
831565383-40692-DTLSB-03_30_2022-GO95HV-1^06144006.0191601 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
831565383-40692-DTLSB-03_30_2022-GO95MLD-1^06144006.0191601 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
714160973-94861-DTLSB-03_30_2022-XARMSPCR-1^06144006.0195900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
374565663-58620-DTLSB-03_30_2022-GO95MLD-1^06144006.0197900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
551312086-62086-DETAIL-04_20_2022-GO95HV-1^06143012.0366500 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
551312086-62086-DETAIL-04_20_2022-GO95MLD-1^06143012.0366500 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
4976294-96629-DETAIL-04_20_2022-GO95MLD-1^06143012.0369001 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
823695444-81229-DETAIL-04_20_2022-GO95MLD-1^06143012.0369003 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
823695444-81229-DETAIL-04_20_2022-SVCROAD-1^06143012.0369003 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
79501724-3029-DETAIL-05_04_2022-GO95MLD-1^06143013.0190400 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
600831394-39629-DETAIL-05_04_2022-GO95MLD-1^06143013.0190501 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
392161044-4729-DETAIL-05_04_2022-GO95HV-1^06143013.0190701 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
20108764-93429-DETAIL-05_04_2022-GO95HV-1^06143013.0190800 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
931396544-89729-DETAIL-05_02_2022-GO95HV-1^06143013.0191400 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
649878914-59729-DETAIL-05_02_2022-GO95MLD-1^06143013.0191501 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
601704606-66606-DETAIL-05_02_2022-GO95MLD-1^06143013.0191502 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
875848557-46042-DETAIL-02_09_2022-GO95HV-1^06146005.0015900 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
764761507-63379-DETAIL-02_17_2022-GO95HV-1^06146005.0017001 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
738079077-29279-DETAIL-02_10_2022-GO95HV-1^06146005.0017801 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
787381353-4353-DETAIL-02_16_2022-GO95MLD-1^06146005.0022400 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
653785410-3579-DETAIL-02_15_2022-GO95MLD-1^06146005.0023000 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
900142993-87209-DETAIL-02_22_2022-GO95HV-1^06146005.0096400 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2027-02-22 | 3
109919809-94809-DETAIL-02_22_2022-ENCHRW-1^06146005.0097800 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
237377073-89209-DETAIL-02_23_2022-GO95HV-1^06146005.0098700 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
723797498-2309-DETAIL-02_23_2022-GO95HV-1^06146005.0101500 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
752802898-88109-DETAIL-02_23_2022-GO95MLD-1^06146005.0101501 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
389543828-27419-DETAIL-02_23_2022-GO95MLD-1^06146005.0101600 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
889301248-95379-DETAIL-02_28_2022-GO95MLD-1^06146005.0104001 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
389385127-87127-DETAIL-01_16_2023-GO95MLD-1^06148004.0162300 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
72765124-41379-DETAIL-01_16_2023-GO95MLD-1^06148004.0162302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
315371766-72989-DETAIL-01_17_2023-GO95HV-1^06148004.0175300 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
48048851-32989-DETAIL-01_17_2023-GO95HV-1^06148004.0175302 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
977740661-56989-DETAIL-01_16_2023-INSULDMG-1^06148004.0176300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
930704435-2009-DETAIL-01_16_2023-GO95HV-1^06148004.0177100 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
298799715-88909-DETAIL-01_16_2023-GO95MLD-1^06148004.0179300 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
94262081-379-DETAIL-01_24_2023-GO95MLD-1^06148004.0182000 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
420814456-98279-DETAIL-01_24_2023-GO95HV-1^06148004.0182002 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
420814456-98279-DETAIL-01_24_2023-GO95MLD-1^06148004.0182002 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
777276726-72479-DETAIL-01_24_2023-COPLLEAN-1^06148004.0182101 | POLE | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
889432605-38279-DETAIL-01_24_2023-GO95MLD-1^06148004.0182103 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
116299534-73160-DETAIL-04_12_2022-SVCWIND-1^06142012.0132505 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
19856601-53840-DETAIL-04_12_2022-XARMSPCR-1^06142012.0132507 | CROSSARM | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
824382223-39172-DETAIL-04_12_2022-GO95MLD-1^06142012.0132509 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
972064662-48583-DETAIL-04_13_2022-GO95MLD-1^06142012.0132601 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
48240441-18729-AUDIT-05_12_2022-GUYHINS-1^06142012.0132707 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
426869895-29329-DETAIL-04_13_2022-GO95MLD-1^06142012.0132711 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
332668840-58729-DETAIL-04_18_2022-SVCWIND-1^06142012.0132801 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
14252771-10429-DETAIL-04_19_2022-CLRTOUCH-1^06142012.0132806 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
195457281-79729-DETAIL-04_21_2022-GO95TCH-1^06142012.0132807 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
116330241-58129-DETAIL-04_18_2022-GO95MLD-1^06142012.0132808 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
688248653-78481-DETAIL-04_19_2022-GO95MLD-1^06142012.0132810 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
688248653-78481-DETAIL-04_19_2022-GUYNOINS-1^06142012.0132810 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
25224548-98970-DETAIL-03_28_2023-SVCDEFLC-1^06142016.0083709 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
912199254-32354-DETAIL-03_28_2023-GO95HV-1^06142016.0083801 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
472421554-14554-DETAIL-03_28_2023-GO95MLD-1^06142016.0083805 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
486362114-36114-DETAIL-03_27_2023-GO95MLD-1^06142016.0082803 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
646911214-38214-ADMIN-04_21_2023-GO95TCH-1^06142016.0082804 | OTHER | CA-NON-TIER | Distribution | 2023-04-21 | 2026-04-21 | 2
587856314-33414-DETAIL-03_27_2023-GO95HV-1^06142016.0082805 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
587856314-33414-DETAIL-03_27_2023-GO95MLD-1^06142016.0082805 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
587856314-33414-DETAIL-03_27_2023-GRDRODHI-1^06142016.0082805 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
532251514-14514-DETAIL-03_27_2023-GO95MLD-1^06142016.0082806 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
369308514-50614-DETAIL-03_28_2023-SVCDEFLC-1^06142016.0082807 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
858553614-15614-DETAIL-03_27_2023-GO95HV-1^06142016.0082900 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
379107674-76774-DETAIL-03_28_2023-GO95MLD-1^06142016.0083907 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
862390155-2729-DETAIL-04_19_2022-GO95TCH-1^06142012.0131809 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
883669438-95529-DETAIL-04_19_2022-GO95MLD-1^06142012.0131900 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
10422360-53129-DETAIL-04_19_2022-CLRTOUCH-1^06142012.0131907 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
774242550-46929-DETAIL-04_19_2022-GO95HV-1^06142012.0131915 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
21564734-14450-DETAIL-04_13_2022-GO95MLD-1^06142012.0132400 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
967489504-98673-DETAIL-04_13_2022-SVCROAD-1^06142012.0132401 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
407217334-86029-DETAIL-04_13_2022-GO95MLD-1^06142012.0132405 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
19856601-53840-DETAIL-04_12_2022-GO95MLD-1^06142012.0132507 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
98134960-96630-DETAIL-03_20_2017-SVCENTCO-1^06142012.0132610 | OTHER | CA-NON-TIER | Distribution | 2017-03-20 | 2022-02-20 | 2
150952841-49729-DETAIL-04_18_2022-GO95MLD-1^06142012.0132700 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
948535454-58629-DETAIL-04_18_2022-GO95MLD-1^06142012.0132705 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2027-04-18 | 3
637152423-86051-DETAIL-04_18_2022-SVCROOF-1^06142012.0132804 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2025-04-18 | 2
510329763-26991-DETAIL-04_13_2022-GO95MLD-1^06142012.0134600 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
792312311-32529-DETAIL-04_18_2022-GO95HV-1^06142012.0134807 | OTHER | CA-NON-TIER | Distribution | 2022-04-18 | 2027-04-18 | 3
524374881-10611-DETAIL-04_19_2022-GO95MLD-1^06142012.0134901 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
24039591-80870-DETAIL-04_19_2022-GO95MLD-1^06142012.0134903 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
24039591-80870-DETAIL-04_19_2022-POLETOP-1^06142012.0134903 | POLE | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
862592163-16302-DETAIL-04_14_2022-GO95MLD-1^06142012.0135502 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
862592163-16302-DETAIL-04_14_2022-INSULDMG-1^06142012.0135502 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
797096253-53929-DETAIL-04_14_2022-GO95HV-1^06142012.0136501 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
827870093-75682-DETAIL-04_14_2022-GO95HV-1^06142012.0136502 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
859720873-63392-DETAIL-04_14_2022-GO95HV-1^06142012.0136503 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
551642363-2441-DETAIL-04_14_2022-INSULDMG-1^06142012.0137500 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
407613294-39429-DETAIL-04_19_2022-XARMSPCR-1^06143012.0360100 | CROSSARM | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
85770544-53629-DETAIL-04_20_2022-GO95MLD-1^06143012.0360501 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
250550115-62115-DETAIL-04_19_2022-GO95MLD-1^06143012.0361102 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
250550115-62115-DETAIL-04_19_2022-GO95TCH-1^06143012.0361102 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
332021863-57329-DETAIL-04_20_2022-SVCROAD-1^06143012.0361500 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
409069164-60264-DETAIL-04_20_2022-GO95HV-1^06143012.0364100 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
433867743-729-DETAIL-04_20_2022-GO95MLD-1^06143012.0364302 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
910478743-12729-DETAIL-04_21_2022-GO95HV-1^06143012.0364500 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
966051213-91729-DETAIL-04_20_2022-GO95HV-1^06143012.0364501 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
78923651-58729-DETAIL-04_20_2022-GO95MLD-1^06143012.0365000 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
563674113-96629-DETAIL-04_20_2022-GUYSLACK-1^06143012.0365100 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
623418203-26329-DETAIL-04_20_2022-GO95MLD-1^06143012.0365102 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
355959091-22191-DETAIL-03_23_2023-SVCROAD-1^06142016.0051100 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
325351211-92211-DETAIL-03_23_2023-GO95HV-1^06142016.0051105 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2028-03-23 | 3
325351211-92211-DETAIL-03_23_2023-GO95MLD-1^06142016.0051105 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
161372531-8834-DETAIL-03_27_2023-GO95MLD-1^06142016.0052100 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
161372531-8834-DETAIL-03_27_2023-GRDRODHI-1^06142016.0052100 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
333239961-71061-DETAIL-03_27_2023-GO95HV-1^06142016.0052202 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
887170281-42281-DETAIL-03_27_2023-GO95HV-1^06142016.0052400 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
857782501-26501-DETAIL-03_28_2023-ABNDEQPM-1^06142016.0052901 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
318334701-85801-DETAIL-03_29_2023-GO95MLD-1^06142016.0053000 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
382641121-75121-DETAIL-03_28_2023-GO95MLD-1^06142016.0053007 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
708984164-86164-DETAIL-03_28_2023-GO95MLD-1^06142016.0053301 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
432779741-22841-DETAIL-03_28_2023-GO95MLD-1^06142016.0053500 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
166314665-83429-DETAIL-04_19_2022-GO95TCH-1^06142012.0132902 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
616622914-27129-DETAIL-04_19_2022-GO95HV-1^06142012.0132906 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
539703304-57129-DETAIL-04_19_2022-GO95MLD-1^06142012.0132908 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
25270683-52429-DETAIL-04_19_2022-GO95HV-1^06142012.0132907 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
25270683-52429-DETAIL-04_19_2022-GO95MLD-1^06142012.0132907 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
25270683-52429-DETAIL-04_19_2022-SVCWIND-1^06142012.0132907 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
969926220-1273-DETAIL-04_14_2022-GO95HV-1^06142012.0133500 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
315787520-19660-DETAIL-04_12_2022-GO95MLD-1^06142012.0133502 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
978456821-45793-DETAIL-04_12_2022-GO95MLD-1^06142012.0133505 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
498605413-43029-DETAIL-04_13_2022-GO95MLD-1^06142012.0133606 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
624933954-24741-DETAIL-04_13_2022-ANCHIDLE-1^06142012.0133609 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
864977424-10929-DETAIL-04_13_2022-GO95HV-1^06142012.0133610 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
132922781-24429-DETAIL-04_11_2022-GO95MLD-1^06142012.0130800 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
221202220-52929-DETAIL-04_11_2022-GO95CL10-1^06142012.0130801 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
898708873-41929-DETAIL-04_11_2022-GO95GUYP-1^06142012.0130805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
800986614-1029-DETAIL-04_11_2022-GO95TCH-1^06142012.0130810 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
650638364-40829-DETAIL-04_11_2022-GO95MLD-1^06142012.0130811 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
132922781-24429-DETAIL-04_11_2022-XARMSPCR-1^06142012.0130800 | CROSSARM | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
132922781-24429-ADMIN-10_03_2022-POLEDERP-1^06142012.0130800 | POLE | CA-NON-TIER | Distribution | 2022-10-03 | 2025-10-03 | 2
497555554-12929-DETAIL-04_11_2022-SVCWIND-1^06142012.0130802 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
898708873-41929-DETAIL-04_11_2022-GUYHINS-1^06142012.0130805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
7670444-41029-DETAIL-04_11_2022-GO95MLD-1^06142012.0130809 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
650638364-40829-DETAIL-04_11_2022-GO95MLD-2^06142012.0130811 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
492241556-52529-DETAIL-04_06_2023-RISEGRD-1^06143014.0232800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
461377293-54421-DETAIL-04_06_2023-GO95MLD-1^06143014.0233800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
937892213-34992-DETAIL-04_06_2023-GO95HV-1^06143014.0235800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
401213923-20950-DETAIL-04_06_2023-GO95HV-1^06143014.0236702 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
60492413-54470-DETAIL-04_06_2023-SVCDEFLC-1^06143014.0236800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
960651505-29929-DETAIL-04_06_2023-GUYHINS-1^06143014.0237700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
589954683-33291-DETAIL-04_05_2023-GO95MLD-1^06143014.0240801 | OTHER | CA-TIER-2 | Distribution | 2023-04-05 | 2026-04-05 | 2
868382711-229-DETAIL-04_05_2023-GO95BLTC-1^06143014.0241800 | OTHER | CA-TIER-2 | Distribution | 2023-04-05 | 2028-04-05 | 3
970534524-23934-ADMIN-09_16_2022-POLEDERP-1^06143015.0349001 | POLE | CA-TIER-2 | Distribution | 2022-09-16 | 2023-09-16 | 2
815944931-27342-DTLSB-03_29_2022-GO95MLD-1^06144006.0035100 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
618347221-4431-DTLSB-03_29_2022-GO95HV-1^06144006.0099900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
659536911-86901-DTLSB-03_29_2022-GO95HV-1^06144006.0100900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
437353-70453-DETAIL-03_23_2023-GO95MLD-1^06142016.0081800 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
614493828-5828-DETAIL-03_23_2023-GO95HV-1^06142016.0081802 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2028-03-23 | 3
383394753-20774-DETAIL-03_27_2023-GO95MLD-1^06142016.0081806 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
795795953-27953-DETAIL-03_23_2023-GO95MLD-1^06142016.0081901 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
537197583-86683-DETAIL-03_23_2023-SVCDEFLC-1^06142016.0081903 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
698409783-96883-DETAIL-03_23_2023-GO95MLD-1^06142016.0081904 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
682855060-5734-DETAIL-03_27_2023-CLRTOPOL-1^06142016.0082701 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
532251514-14514-DETAIL-03_27_2023-GO95HV-1^06142016.0082806 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
369308514-50614-DETAIL-03_28_2023-GO95MLD-1^06142016.0082807 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
811287614-20714-DETAIL-03_27_2023-GO95MLD-1^06142016.0082901 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
487966134-48134-DETAIL-03_27_2023-GO95MLD-1^06142016.0082905 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
852825596-61562-DETAIL-03_29_2023-GO95MLD-1^06142016.0083500 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
219797596-59596-DETAIL-02_14_2022-GO95HV-1^06146005.0036803 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
5631409-86909-DETAIL-03_03_2022-GO95HV-1^06146005.0124400 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
482767869-25151-DETAIL-03_03_2022-GO95MLD-1^06146005.0125400 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
520617769-74779-DETAIL-03_08_2022-GO95MLD-1^06146005.0125701 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
270552070-38210-DETAIL-03_03_2022-GO95TCH-1^06146005.0127003 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
172212140-16379-DETAIL-03_03_2022-GO95HV-1^06146005.0127501 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
183552799-34379-DETAIL-03_03_2022-GO95HV-1^06146005.0127800 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
639644347-50079-DETAIL-03_03_2022-GO95HV-1^06146005.0127900 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
84688227-46120-DETAIL-03_03_2022-GO95HV-1^06146005.0128901 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
677194619-4879-DETAIL-02_14_2022-GO95MLD-1^06146005.0037200 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2025-02-14 | 2
779456983-64189-DETAIL-02_23_2022-GO95HV-1^06146005.0046000 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
188668458-14009-DETAIL-02_23_2022-GO95HV-1^06146005.0046901 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
974626063-58129-DETAIL-07_01_2020-GO95MLD-1^06142012.0011801 | OTHER | CA-NON-TIER | Distribution | 2020-07-01 | 2025-07-01 | 3
726224121-27229-DETAIL-06_29_2020-SVCROAD-1^06142012.0118504 | OTHER | CA-NON-TIER | Distribution | 2020-06-29 | 2023-06-29 | 2
727464179-88291-DETAIL-04_18_2019-SVCROAD-1^06142012.0125202 | OTHER | CA-NON-TIER | Distribution | 2019-04-18 | 2024-03-18 | 2
52281664-70950-DETAIL-04_12_2022-POLESTEP-1^06142012.0130401 | POLE | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
500219483-87471-DETAIL-04_12_2022-SVCENTCO-1^06142012.0130403 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
74639654-29300-DETAIL-04_12_2022-GO95MLD-1^06142012.0130410 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
321721166-90029-DETAIL-07_01_2020-GO95MLD-1^06142012.0014101 | OTHER | CA-NON-TIER | Distribution | 2020-07-01 | 2023-07-01 | 2
918391279-36902-ADMIN-06_30_2020-POLEDERP-1^06142012.0106400 | POLE | CA-NON-TIER | Distribution | 2020-06-30 | 2023-06-30 | 2
541116418-77418-DETAIL-04_17_2019-SVCROOF-1^06142012.0122002 | OTHER | CA-NON-TIER | Distribution | 2019-04-17 | 2024-03-17 | 2
306789841-51941-DETAIL-03_27_2023-GO95MLD-1^06142016.0053700 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
194227761-19761-DETAIL-03_29_2023-SVCDEFLC-1^06142016.0054002 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
476020291-16014-DETAIL-03_23_2023-GO95MLD-1^06142016.0051103 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
88547311-9311-DETAIL-03_27_2023-GO95TCH-1^06142016.0051201 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
88547311-9311-DETAIL-03_27_2023-GUYHINS-1^06142016.0051201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
393208411-49411-DETAIL-03_27_2023-SVCDEFLC-1^06142016.0051203 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
789179331-80431-DETAIL-03_27_2023-GO95MLD-1^06142016.0052003 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
498179531-90631-DETAIL-03_27_2023-GO95HV-1^06142016.0052102 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
333239961-71061-DETAIL-03_27_2023-GO95MLD-1^06142016.0052202 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
796643081-95081-DETAIL-03_27_2023-GUYHINS-1^06142016.0052300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
288510381-11381-DETAIL-03_27_2023-GO95HV-1^06142016.0052500 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
69308381-99381-DETAIL-03_27_2023-SVCENTCO-1^06142016.0052502 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
86918111-68111-DETAIL-04_21_2022-GO95HV-1^06142012.0139200 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
194947643-88929-DETAIL-04_21_2022-CLMBHAZ-1^06142012.0139300 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
194947643-88929-DETAIL-04_21_2022-GO95MLD-1^06142012.0139300 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
194947643-88929-DETAIL-04_21_2022-GUYHINS-1^06142012.0139300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
599221873-33511-DETAIL-04_21_2022-GO95HV-1^06142012.0139402 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
888393003-10282-DETAIL-04_21_2022-GO95MLD-1^06142012.0139404 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
472933454-53841-DETAIL-11_08_2021-SVCROAD-1^06142012.0145801 | OTHER | CA-NON-TIER | Distribution | 2021-11-08 | 2024-11-08 | 2
220126504-56529-DETAIL-11_08_2021-SVCRUBLG-1^06142012.0146702 | OTHER | CA-NON-TIER | Distribution | 2021-11-08 | 2024-11-08 | 2
423329150-74928-DETAIL-11_03_2021-GO95TCH-1^06142012.0146808 | OTHER | CA-NON-TIER | Distribution | 2021-11-03 | 2024-11-03 | 2
664227948-97229-DETAIL-03_28_2016-SVCWIND-1^06142012.0148601 | OTHER | CA-NON-TIER | Distribution | 2016-03-28 | 2021-02-28 | 2
625438355-52229-DETAIL-04_26_2022-GO95MLD-1^06143012.0236400 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
625438355-52229-AUDIT-05_03_2022-GO95TCH-1^06143012.0236400 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
471739777-79777-DETAIL-04_26_2022-GO95MLD-1^06143012.0236501 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
249141454-2429-DETAIL-04_26_2022-GO95MLD-1^06143012.0237000 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
1770654-26229-DETAIL-04_26_2022-GO95CL10-1^06143012.0239201 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
1770654-26229-DETAIL-04_26_2022-GO95MLD-1^06143012.0239201 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
981364994-5229-DETAIL-04_26_2022-GO95TCH-1^06143012.0239203 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
223545664-22329-DETAIL-04_26_2022-SVCROAD-1^06143012.0239305 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
241555619-92329-DETAIL-04_27_2022-GO95MLD-1^06143012.0240600 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
134119429-48329-DETAIL-04_27_2022-GO95MLD-1^06143012.0240601 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
532086261-81629-DETAIL-04_27_2022-GO95TCH-1^06143012.0240700 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
458522260-92229-DETAIL-04_27_2022-GO95MLD-1^06143012.0240701 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
132922781-24429-DETAIL-04_11_2022-POLETOP-1^06142012.0130800 | POLE | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
378316543-66129-DETAIL-04_12_2022-SVCWIND-1^06142012.0130606 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
325646684-74729-DETAIL-04_12_2022-GO95MLD-1^06142012.0130608 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
325646684-74729-DETAIL-04_12_2022-GO95TCH-1^06142012.0130608 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
964215064-93729-DETAIL-04_12_2022-SVCWIND-1^06142012.0130610 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
415284634-73129-DETAIL-04_11_2022-SVCENTCO-1^06142012.0130614 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
694667934-66829-DETAIL-04_11_2022-GO95MLD-1^06142012.0130702 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
694667934-66829-DETAIL-04_11_2022-GO95TCH-1^06142012.0130702 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
694667934-66829-DETAIL-04_11_2022-SVCRUBLG-1^06142012.0130702 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
655896363-80929-DETAIL-04_11_2022-SVCENTCO-1^06142012.0130704 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
663657505-46129-DETAIL-04_26_2022-GO95CL10-1^06143012.0235300 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
473725035-1729-DETAIL-04_26_2022-GO95MLD-1^06143012.0236305 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
37762334-97929-DETAIL-04_26_2022-GO95MLD-1^06143012.0237300 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
883931294-97629-DETAIL-04_26_2022-GO95HV-1^06143012.0238000 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
152200774-99629-DETAIL-04_26_2022-GO95MLD-1^06143012.0238300 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
744200674-30429-DETAIL-04_26_2022-GO95MLD-1^06143012.0238301 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
438704844-1629-DETAIL-04_26_2022-GO95MLD-1^06143012.0238401 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
826935204-41229-DETAIL-04_26_2022-GO95MLD-1^06143012.0238402 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
226500314-80729-DETAIL-04_26_2022-ABNDEQPM-1^06143012.0238500 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
895700534-78534-DETAIL-03_29_2023-GO95MLD-1^06142016.0085402 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
37987634-33675-DETAIL-03_29_2023-GO95TCH-1^06142016.0085602 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
473725035-1729-DETAIL-04_26_2022-CLMBHAZ-1^06143012.0236305 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
89984728-22909-DETAIL-02_28_2022-GO95HV-1^06146005.0106701 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
191493818-96809-DETAIL-02_17_2022-GO95HV-1^06146005.0106800 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
521768718-69709-DETAIL-02_17_2022-GO95MLD-1^06146005.0106900 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
973342638-11909-DETAIL-02_28_2022-GO95HV-1^06146005.0107601 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
901402018-58219-DETAIL-02_17_2022-GO95HV-1^06146005.0109100 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
376952465-39219-DETAIL-02_17_2022-GO95MLD-1^06146005.0109101 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
376952465-39219-DETAIL-02_17_2022-GRDRODHI-1^06146005.0109101 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
755345003-57909-DETAIL-02_17_2022-XARMSPCR-1^06146005.0109400 | CROSSARM | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
186064413-55909-DETAIL-02_17_2022-GO95HV-1^06146005.0109401 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
498505213-91999-DETAIL-02_17_2022-GO95HV-1^06146005.0109402 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2027-02-17 | 3
498505213-91999-DETAIL-02_17_2022-GO95MLD-1^06146005.0109402 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
498505213-91999-DETAIL-02_17_2022-GO95MLD-2^06146005.0109402 | OTHER | CA-NON-TIER | Distribution | 2022-02-17 | 2025-02-17 | 2
954575690-54829-DETAIL-04_13_2022-GO95HV-1^06142012.0131610 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
123012774-5129-DETAIL-04_19_2022-GO95MLD-1^06142012.0131706 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
283640303-59529-DETAIL-04_13_2022-GO95MLD-1^06142012.0131708 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
488455625-16829-DETAIL-04_11_2022-CLRTOUCH-1^06142012.0131710 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
488455625-16829-DETAIL-04_11_2022-SVCENTCO-1^06142012.0131710 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
488455625-16829-DETAIL-04_11_2022-SVCWIND-1^06142012.0131710 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
202591533-2829-DETAIL-04_19_2022-GUYHINS-1^06142012.0131712 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
998765375-40229-DETAIL-04_11_2022-GO95HV-1^06142012.0131801 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
917130613-31129-DETAIL-04_19_2022-GO95MLD-1^06142012.0131803 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
465090434-41829-DETAIL-04_19_2022-GO95MLD-1^06142012.0131805 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
465090434-41829-DETAIL-04_19_2022-SVCROAD-1^06142012.0131805 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
465090434-41829-DETAIL-04_19_2022-SVCWIND-2^06142012.0131805 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
481834381-26731-DETAIL-05_31_2023-GO95MLD-1^06243009.0028605 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
355690351-60199-DETAIL-05_31_2023-GO95HV-1^06243009.0028608 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3
861137908-36929-DTLSB-08_09_2023-GO95MLD-1^06243009.0153500 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
783079318-3589-DTLSB-08_16_2023-GO95MLD-1^06243009.0153800 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
415763728-70989-DTLSB-08_16_2023-GO95HV-1^06243009.0154400 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2028-08-16 | 3
765055228-60929-DTLSB-08_08_2023-GUYNOINS-2^06243009.0154500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
974313798-6929-DTLSB-08_16_2023-GO95MLD-1^06243009.0154601 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
334261918-93779-DTLSB-08_09_2023-ABNDEQPM-1^06243009.0155601 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
67238698-46929-DTLSB-08_16_2023-GO95MLD-1^06243009.0155901 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
994410138-6829-DTLSB-08_10_2023-GO95MLD-1^06243009.0156001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
831303158-53929-DTLSB-08_03_2023-GO95MLD-1^06243009.0156401 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2028-08-03 | 3
679439893-92429-DTLSB-08_23_2023-GO95HV-1^06243009.0109400 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
59987334-81629-DTLSB-08_02_2023-GO95MLD-1^06243009.0196601 | OTHER | CA-NON-TIER | Distribution | 2023-08-02 | 2026-08-02 | 2
326826344-22629-DTLSB-07_27_2023-GO95MLD-1^06243009.0196703 | OTHER | CA-NON-TIER | Distribution | 2023-07-27 | 2026-07-27 | 2
350942754-13629-DTLSB-07_27_2023-GO95MLD-1^06243009.0196800 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
457128854-49629-DTLSB-07_27_2023-GO95MLD-1^06243009.0196902 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
361685854-83629-DTLSB-07_27_2023-GUYNOINS-1^06243009.0196904 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
453976354-63629-DTLSB-07_27_2023-GO95MLD-1^06243009.0196905 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
476260874-99979-DTLSB-07_31_2023-GUYHINS-1^06243009.0198800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-07-31 | 2026-07-31 | 2
653540667-91099-DTLSB-08_17_2023-SVCDEFLC-1^06243009.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
140474407-53829-DTLSB-08_21_2023-GUYNOINS-1^06243009.0216000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
908615169-58169-DTLSB-08_21_2023-GO95MLD-1^06243009.0216005 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
537247597-81109-DTLSB-08_21_2023-GO95MLD-1^06243009.0219000 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
456607790-55532-DTLSB-07_19_2023-GO95MLD-1^06243010.0020100 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
456607790-55532-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0020100 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
692733380-11129-DTLSB-07_19_2023-GO95HV-1^06243010.0020200 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
519464102-24888-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0020203 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
95453986-93788-DTLSB-07_19_2023-GO95MLD-1^06243010.0020204 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
217129180-89899-DTLSB-07_19_2023-GO95HV-1^06243010.0020300 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
217129180-89899-DTLSB-07_19_2023-GO95MLD-1^06243010.0020300 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
217129180-89899-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0020300 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
475167819-69029-DTLSB-07_18_2023-GO95HV-1^06243010.0020401 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
187640091-63542-DTLSB-07_24_2023-GO95HV-1^06243010.0021001 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
187640091-63542-DTLSB-07_24_2023-GO95MLD-1^06243010.0021001 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
530917278-31929-DTLSB-08_03_2023-GO95HV-1^06243009.0157400 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2028-08-03 | 3
340740238-94189-DTLSB-08_10_2023-GO95MLD-1^06243009.0158001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
39042838-92699-DTLSB-08_23_2023-GO95MLD-1^06243009.0158900 | OTHER | CA-TIER-2 | Distribution | 2023-08-23 | 2026-08-23 | 2
39042838-92699-DTLSB-08_23_2023-GUYHINS-1^06243009.0158900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-23 | 2026-08-23 | 2
254676048-12929-DTLSB-08_23_2023-GO95MLD-1^06243009.0158901 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
721209088-72929-DTLSB-08_08_2023-GO95MLD-1^06243009.0159502 | OTHER | CA-NON-TIER | Distribution | 2023-08-08 | 2028-08-08 | 3
446422651-55311-DETAIL-05_31_2023-GO95MLD-1^06243009.0028610 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
790745840-11061-DETAIL-05_31_2023-GO95TCH-1^06243009.0028613 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
966321926-4926-DETAIL-05_31_2023-GO95HV-1^06243009.0028614 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3
966321926-4926-DETAIL-05_31_2023-GO95MLD-1^06243009.0028614 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
188606911-16879-DETAIL-05_30_2023-GO95HV-1^06243009.0028901 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
45261909-77129-DETAIL-06_01_2023-GO95MLD-1^06243009.0029400 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
668984615-67615-DETAIL-06_01_2023-GO95TCH-1^06243009.0029501 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
644600661-36611-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0029502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
644600661-36611-DETAIL-06_01_2023-SVCWIND-1^06243009.0029502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
315176475-88475-AUDIT-07_27_2023-GO95BLTC-1^06243009.0029505 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
762785871-19911-DETAIL-06_01_2023-GO95MLD-1^06243009.0029507 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
989774611-16201-DETAIL-05_30_2023-GO95MLD-1^06243009.0029702 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
421420004-72479-DTLSB-08_01_2023-GO95MLD-1^06243009.0172900 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
637984824-87589-DTLSB-07_25_2023-GO95MLD-1^06243009.0172901 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
252483444-24729-DTLSB-07_31_2023-GO95MLD-1^06243009.0172902 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
383557664-69629-DTLSB-07_27_2023-GO95MLD-1^06243009.0186001 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
90041454-87985-DTLSB-08_02_2023-GO95MLD-1^06243009.0186500 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
347989775-21875-DTLSB-07_27_2023-GO95MLD-1^06243009.0187101 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
540304964-59089-DTLSB-07_27_2023-GO95MLD-1^06243009.0187301 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
370671044-53099-DTLSB-07_27_2023-GO95MLD-1^06243009.0187402 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
859130310-18929-DETAIL-05_30_2023-GO95HV-1^06243009.0029802 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
953119961-62811-DETAIL-05_30_2023-ENCHRW-1^06243009.0029904 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
3987120-12861-DETAIL-05_30_2023-GO95MLD-1^06243009.0029905 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
3987120-12861-DETAIL-05_30_2023-GUYHINS-1^06243009.0029905 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
272634032-81641-DETAIL-05_30_2023-GO95MLD-1^06243009.0029920 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
272634032-81641-DETAIL-05_30_2023-GRDRODHI-1^06243009.0029920 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
890239043-81489-DETAIL-06_27_2023-GO95HV-1^06243009.0032800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
890239043-81489-DETAIL-06_27_2023-GRDRODHI-1^06243009.0032800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
405609403-32099-DETAIL-06_13_2023-GO95MLD-1^06243009.0038500 | OTHER | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
405609403-32099-DETAIL-06_13_2023-GRDRODHI-1^06243009.0038500 | OTHER | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
542930083-2429-DETAIL-06_15_2023-GO95MLD-1^06243009.0039000 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2026-06-15 | 2
157884363-41429-DETAIL-06_27_2023-SVCDEFLC-2^06243009.0047900 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
942161473-29429-DTLSB-07_25_2023-GO95MLD-1^06243009.0053004 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
441105877-27877-DTLSB-07_25_2023-GUYHINS-2^06243009.0053500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
319984853-93189-DTLSB-07_25_2023-GO95MLD-1^06243009.0054403 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
388019633-61189-DTLSB-07_26_2023-GO95MLD-1^06243009.0055000 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
388019633-61189-DTLSB-07_26_2023-GRDRODHI-1^06243009.0055000 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
388019633-61189-DTLSB-07_26_2023-GRDRODHI-2^06243009.0055000 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
533835374-39479-DTLSB-07_25_2023-GO95MLD-1^06243009.0055500 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
84350104-90181-DTLSB-07_25_2023-GO95MLD-1^06243009.0055701 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
428786964-27789-DTLSB-07_26_2023-GO95HV-1^06243009.0055703 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2028-07-26 | 3
428786964-27789-DTLSB-07_26_2023-GO95MLD-1^06243009.0055703 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2026-07-26 | 2
329563494-92589-DTLSB-07_25_2023-GO95MLD-1^06243009.0056400 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
448795593-20571-DTLSB-07_25_2023-INSULDMG-1^06243009.0056502 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
154700374-5981-DTLSB-07_25_2023-GRDRODHI-1^06243009.0056600 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
154700374-5981-DTLSB-07_25_2023-GRDRODHI-2^06243009.0056600 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
154700374-5981-DTLSB-07_25_2023-SVCENTCO-1^06243009.0056600 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
415917893-21289-DTLSB-07_26_2023-GO95MLD-1^06243009.0059900 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2026-07-26 | 2
592163944-1899-DTLSB-08_01_2023-GO95HV-1^06243009.0076100 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
331483324-6989-DTLSB-08_01_2023-ABNDEQPM-1^06243009.0076200 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
471345453-18529-DTLSB-07_31_2023-GO95MLD-1^06243009.0080000 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
825829993-63529-DTLSB-07_31_2023-GO95MLD-1^06243009.0080100 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
665503903-33529-DTLSB-07_31_2023-GO95MLD-1^06243009.0081201 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
877462193-52529-DTLSB-07_31_2023-GO95MLD-1^06243009.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
921623763-81529-DTLSB-07_31_2023-GO95MLD-1^06243009.0081501 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
539899084-79181-AUDIT-10_09_2023-RISEBKSP-1^06243009.0082600 | OTHER | CA-TIER-2 | Distribution | 2023-10-09 | 2026-10-09 | 2
561958383-51529-DTLSB-07_26_2023-GO95MLD-1^06243009.0082603 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
245585973-5161-DTLSB-07_26_2023-GO95HV-1^06243009.0082900 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
416681824-31729-DTLSB-07_27_2023-ABNDEQPM-1^06243009.0187501 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
808165276-37276-DTLSB-08_01_2023-GO95MLD-1^06243009.0187503 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
965916864-97729-DTLSB-07_27_2023-GO95MLD-1^06243009.0187600 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
346590884-14279-DTLSB-07_27_2023-GO95MLD-1^06243009.0187702 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
525519734-28729-DTLSB-08_01_2023-GO95HV-1^06243009.0187802 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
413218134-78729-DTLSB-08_01_2023-GO95HV-1^06243009.0187900 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
351538414-64729-DTLSB-08_01_2023-GO95HV-1^06243009.0189902 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
502743516-34516-DTLSB-08_09_2023-GO95MLD-1^06243009.0190701 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
142594694-35629-DTLSB-08_09_2023-GO95MLD-1^06243009.0194200 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
527491044-52629-DTLSB-07_27_2023-GUYNOINS-1^06243009.0195700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
553653624-54629-DTLSB-08_09_2023-GO95HV-1^06243009.0196000 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
553653624-54629-DTLSB-08_09_2023-GO95MLD-1^06243009.0196000 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
773831134-50629-DTLSB-08_07_2023-GO95MLD-1^06243009.0196201 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
410298734-60629-DTLSB-08_07_2023-GO95MLD-1^06243009.0196401 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
633773403-66529-DTLSB-07_31_2023-GO95HV-1^06243009.0084100 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
268484203-76529-DTLSB-07_31_2023-GO95STUB-1^06243009.0085100 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
579636244-44471-DTLSB-07_31_2023-GO95HV-1^06243009.0085101 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
579636244-44471-DTLSB-07_31_2023-GO95MLD-1^06243009.0085101 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
491923554-88471-DTLSB-07_31_2023-GO95MLD-1^06243009.0085200 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
649259564-96529-DTLSB-07_31_2023-GO95MLD-1^06243009.0086200 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
96510544-85879-DTLSB-07_31_2023-SVCNEUT-1^06243009.0087400 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
63481083-74529-DTLSB-07_31_2023-GO95MLD-1^06243009.0087500 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
220291173-91799-DTLSB-07_31_2023-GO95MLD-1^06243009.0087600 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
886183534-44699-DTLSB-07_31_2023-GO95HV-1^06243009.0087603 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
238991563-84529-DTLSB-07_26_2023-GO95MLD-1^06243009.0087800 | OTHER | CA-NON-TIER | Distribution | 2023-07-26 | 2026-07-26 | 2
800256663-35529-DTLSB-07_26_2023-GO95HV-1^06243009.0087902 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
800256663-35529-DTLSB-07_26_2023-GO95MLD-1^06243009.0087902 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
840262876-78869-DTLSB-08_16_2023-GO95MLD-1^06243009.0104201 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2028-08-16 | 3
644138927-20829-DTLSB-08_21_2023-INSULDMG-1^06243009.0219200 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
154476807-20679-DTLSB-08_21_2023-GO95HV-1^06243009.0219804 | OTHER | CA-TIER-2 | Distribution | 2023-08-21 | 2028-08-21 | 3
568176985-92768-ADMIN-06_30_2022-POLEREPL-1^06243009.0220700 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
568176985-92768-DTLSB-08_21_2023-GO95HV-1^06243009.0220700 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
449555437-83322-DTLSB-08_21_2023-GUYHINS-1^06243009.0222200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
343666524-77524-DTLSB-08_10_2023-GUYHINS-1^06243009.0225700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
320129424-40524-DTLSB-08_10_2023-GO95HV-1^06243009.0226700 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2028-08-10 | 3
898312217-78222-DTLSB-08_10_2023-GO95MLD-1^06243009.0227800 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
771237369-9369-DTLSB-08_23_2023-GO95CLSV-1^06243009.0231600 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
771237369-9369-DTLSB-08_23_2023-SVCWIND-1^06243009.0231600 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
609681979-2689-DTLSB-08_15_2023-GO95MLD-1^06243009.0232001 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
678288189-63229-DTLSB-08_15_2023-SVCNEUT-1^06243009.0232003 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
312324003-42599-DTLSB-08_23_2023-GO95MLD-1^06243009.0109401 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
231592603-33429-DTLSB-08_23_2023-GO95MLD-1^06243009.0109402 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
445134286-3779-DTLSB-08_29_2023-GO95HV-1^06243009.0110300 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
681693796-35796-DTLSB-08_23_2023-GO95HV-1^06243009.0110340 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
303478696-40796-DTLSB-08_29_2023-GO95HV-1^06243009.0110341 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
951490270-82633-DTLSB-08_29_2023-GO95TCH-1^06243009.0117400 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
828366986-78189-DTLSB-08_29_2023-SVCDEFLC-2^06243009.0117401 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
328776236-17279-DTLSB-08_24_2023-GO95MLD-1^06243009.0118601 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
545587866-3089-DTLSB-08_24_2023-GO95MLD-1^06243009.0118603 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
667551236-40329-DTLSB-08_24_2023-GO95MLD-1^06243009.0119500 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
806503823-55329-DTLSB-08_29_2023-GO95HV-1^06243009.0120101 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
838302813-95329-DTLSB-08_29_2023-GO95MLD-1^06243009.0121001 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
253004103-15329-DTLSB-08_29_2023-GO95MLD-1^06243009.0121201 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
917126223-23329-AUDIT-10_10_2023-GO95BLTC-1^06243009.0121400 | OTHER | CA-NON-TIER | Distribution | 2023-10-10 | 2028-10-10 | 3
917126223-23329-AUDIT-10_10_2023-GO95MLD-1^06243009.0121400 | OTHER | CA-NON-TIER | Distribution | 2023-10-10 | 2026-10-10 | 2
974125799-2879-DTLSB-08_15_2023-GO95MLD-1^06243009.0232103 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
592395199-13229-DTLSB-08_03_2023-GO95MLD-1^06243009.0232105 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
951543821-94821-DTLSB-08_03_2023-GO95MLD-1^06243009.0232502 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
740729491-18669-DTLSB-08_23_2023-GO95MLD-1^06243009.0232600 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
729336706-92488-DTLSB-08_14_2023-GO95HV-1^06243009.0236700 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
851057811-19482-DTLSB-08_14_2023-GO95MLD-1^06243009.0238400 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
851057811-19482-DTLSB-08_14_2023-GUYHINS-1^06243009.0238400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
508063619-16029-AUDIT-10_09_2023-GO95HV-1^06243009.0242700 | OTHER | CA-NON-TIER | Distribution | 2023-10-09 | 2028-10-09 | 3
766141229-36679-DTLSB-08_15_2023-GO95MLD-1^06243009.0243601 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
298361119-63029-DTLSB-08_14_2023-GO95HV-1^06243009.0244101 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
296192290-57199-DTLSB-08_14_2023-GO95MLD-1^06243009.0244405 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
651650419-86042-DTLSB-08_14_2023-GRDRODHI-1^06243009.0244900 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
20750621-70889-DTLSB-08_15_2023-GO95BLTC-1^06243009.0245500 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2028-08-15 | 3
235914551-54789-DTLSB-08_14_2023-GO95MLD-1^06243009.0246000 | OTHER | CA-TIER-2 | Distribution | 2023-08-14 | 2028-08-14 | 3
823344649-57989-DTLSB-08_14_2023-GO95HV-1^06243009.0246101 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
126905179-82029-DTLSB-08_14_2023-GO95MLD-1^06243009.0246103 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
118144135-14302-DTLSB-08_15_2023-SVCDEFLC-1^06243009.0261001 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
257823735-45429-DTLSB-08_15_2023-GO95MLD-1^06243009.0261002 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
797988988-17342-DTLSB-08_15_2023-SVCDEFLC-1^06243009.0261003 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
797988988-17342-DTLSB-08_15_2023-SVCDEFLC-2^06243009.0261003 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
477921505-2599-DTLSB-08_15_2023-GO95HV-1^06243009.0262301 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2028-08-15 | 3
477921505-2599-DTLSB-08_15_2023-GO95MLD-1^06243009.0262301 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
835634685-22599-DTLSB-08_15_2023-SVCENTCO-1^06243009.0262400 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
929308339-48029-DTLSB-08_17_2023-INSULDMG-1^06243009.0130000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
29301959-85289-DTLSB-08_29_2023-GUYLOINS-1^06243009.0130900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
50515680-80399-DTLSB-08_17_2023-GO95MLD-1^06243009.0131003 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
300344880-79029-DTLSB-08_17_2023-GO95MLD-1^06243009.0131200 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
25090050-1129-DTLSB-08_17_2023-GUYNOINS-2^06243009.0131502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
442719271-59269-AUDIT-10_09_2023-GO95HV-1^06243009.0131800 | OTHER | CA-NON-TIER | Distribution | 2023-10-09 | 2028-10-09 | 3
281640789-51309-DTLSB-08_17_2023-GO95HV-1^06243009.0132501 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
500477819-49929-DTLSB-08_30_2023-GO95MLD-1^06243009.0137403 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
296102961-80679-DTLSB-08_08_2023-GO95MLD-1^06243009.0140601 | OTHER | CA-NON-TIER | Distribution | 2023-08-08 | 2026-08-08 | 2
679796131-3029-DTLSB-08_03_2023-GO95MLD-1^06243009.0141200 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2028-08-03 | 3
969220670-7129-DTLSB-08_03_2023-GO95MLD-1^06243009.0142101 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
547834090-4489-DTLSB-08_03_2023-GO95MLD-1^06243009.0145001 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
44035459-28289-DTLSB-08_03_2023-GO95MLD-1^06243009.0147001 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
138149858-60889-DTLSB-08_09_2023-GO95MLD-1^06243009.0150200 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
18883718-19829-DTLSB-08_09_2023-GO95MLD-1^06243009.0150302 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
592797918-39829-DTLSB-08_09_2023-GO95MLD-1^06243009.0150303 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
904583715-98429-DTLSB-08_15_2023-GO95MLD-1^06243009.0262700 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
904583715-98429-AUDIT-10_09_2023-GO95HV-1^06243009.0262700 | OTHER | CA-NON-TIER | Distribution | 2023-10-09 | 2028-10-09 | 3
380477814-27429-DTLSB-08_15_2023-GO95MLD-1^06243009.0263300 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
20207107-96589-DTLSB-08_15_2023-GO95MLD-1^06243009.0263301 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2028-08-15 | 3
545039676-59879-DTLSB-08_15_2023-GO95MLD-1^06243009.0263800 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2028-08-15 | 3
545039676-59879-DTLSB-08_15_2023-SVCDEFLC-1^06243009.0263800 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
989224523-2399-DTLSB-08_07_2023-GO95HV-1^06243009.0280801 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
676376611-9529-DTLSB-08_16_2023-GUYNOINS-1^06243009.0281801 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
552135201-79529-DTLSB-08_16_2023-GO95MLD-1^06243009.0281900 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
191248889-41029-DETAIL-01_12_2021-SVCWIND-1^06243009.0294302 | OTHER | CA-TIER-2 | Distribution | 2021-01-12 | 2024-01-12 | 2
297257809-36499-DETAIL-01_11_2021-GO95MLD-1^06243009.0303200 | OTHER | CA-TIER-2 | Distribution | 2021-01-11 | 2024-01-11 | 2
355969659-18629-DETAIL-02_04_2021-GO95MLD-1^06243009.0323300 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
414755229-6089-DETAIL-02_04_2021-GO95MLD-1^06243009.0324304 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
743499801-55632-DTLSB-07_19_2023-GO95MLD-1^06243010.0020001 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
623601309-26978-DTLSB-08_10_2023-GO95MLD-1^06243009.0152001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
961096308-43289-DTLSB-08_09_2023-GO95HV-1^06243009.0152400 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
961096308-43289-DTLSB-08_09_2023-SVCDEFLC-1^06243009.0152400 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
251241409-30778-DTLSB-08_10_2023-GO95MLD-1^06243009.0153000 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
939680509-75578-DTLSB-08_10_2023-GO95MLD-1^06243009.0154001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
748764928-20929-DTLSB-08_16_2023-GO95MLD-1^06243009.0154300 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
415763728-70989-DTLSB-08_16_2023-ABNDEQPM-1^06243009.0154400 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2028-08-16 | 3
765055228-60929-DTLSB-08_08_2023-GUYNOINS-1^06243009.0154500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
974313798-6929-DTLSB-08_16_2023-GRDRODHI-1^06243009.0154601 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
386117387-30929-DTLSB-08_08_2023-GO95MLD-1^06243009.0155400 | OTHER | CA-NON-TIER | Distribution | 2023-08-08 | 2026-08-08 | 2
382467928-16929-DTLSB-08_08_2023-SVCROAD-1^06243009.0155600 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
536486078-12889-DTLSB-08_03_2023-GO95MLD-1^06243009.0156500 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
536486078-12889-DTLSB-08_03_2023-SVCROAD-1^06243009.0156500 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
530917278-31929-DTLSB-08_03_2023-INSULDMG-1^06243009.0157400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
582367027-99829-DTLSB-08_16_2023-GUYNOINS-1^06243009.0169000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
187640091-63542-DTLSB-07_24_2023-GRDRODHI-1^06243010.0021001 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
991326421-83342-DTLSB-07_20_2023-GO95HV-1^06243010.0021200 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
172027480-75332-DTLSB-07_19_2023-GO95MLD-1^06243010.0021201 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
178665150-34732-DTLSB-07_19_2023-GO95MLD-1^06243010.0021202 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
70207160-34232-DTLSB-07_19_2023-GO95MLD-1^06243010.0021203 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
918940650-41129-DTLSB-07_19_2023-GO95MLD-1^06243010.0021402 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
155955429-14479-DTLSB-07_18_2023-GO95MLD-1^06243010.0021404 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
577843500-46832-DTLSB-07_19_2023-GO95HV-1^06243010.0022201 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
636422470-11132-DTLSB-07_19_2023-GO95MLD-1^06243010.0022202 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
836410950-2232-DTLSB-07_19_2023-RISEGRD-1^06243010.0022300 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
355834540-51232-DTLSB-07_19_2023-GO95MLD-1^06243010.0022301 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
727673811-59352-DTLSB-07_24_2023-GO95MLD-1^06243010.0023300 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
882821149-20129-DTLSB-07_20_2023-GO95MLD-2^06243010.0023401 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
882821149-20129-DTLSB-07_20_2023-GRDRODHI-1^06243010.0023401 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
791629699-76899-DTLSB-07_24_2023-GO95MLD-1^06243010.0024301 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
641662159-39029-DTLSB-07_24_2023-GO95HV-1^06243010.0024402 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
441327020-94989-DTLSB-07_20_2023-GO95MLD-1^06243010.0027300 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
398381290-36489-DTLSB-07_19_2023-GO95MLD-1^06243010.0027400 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
831611340-8879-DTLSB-07_17_2023-GO95MLD-1^06243010.0028101 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
582367027-99829-DTLSB-08_16_2023-GUYNOINS-2^06243009.0169000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
606090414-22729-DTLSB-08_01_2023-GO95HV-1^06243009.0173602 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
411422814-72729-DTLSB-08_01_2023-XARMSPCR-1^06243009.0173701 | CROSSARM | CA-TIER-2 | Distribution | 2023-08-01 | 2024-08-01 | 2
90041454-87985-DTLSB-08_02_2023-SVCDEFLC-1^06243009.0186500 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
548560364-20381-DTLSB-07_27_2023-SVCWIND-1^06243009.0187102 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
532776364-65699-DTLSB-07_27_2023-GO95MLD-1^06243009.0187103 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
710108544-30729-DTLSB-07_27_2023-GO95MLD-1^06243009.0187302 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
370671044-53099-DTLSB-07_27_2023-SVCDEFLC-1^06243009.0187402 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
31814524-61729-DTLSB-07_27_2023-GO95HV-1^06243009.0187500 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
416681824-31729-DTLSB-07_27_2023-GO95MLD-1^06243009.0187501 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
641683875-15875-DTLSB-07_27_2023-GO95MLD-1^06243009.0187504 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
51233774-57299-DTLSB-07_27_2023-GO95MLD-1^06243009.0187602 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
739287754-7729-DTLSB-08_01_2023-SVCDEFLC-1^06243009.0187701 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
873243634-16299-DTLSB-08_01_2023-GO95MLD-1^06243009.0187801 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
325461964-37729-DTLSB-07_31_2023-GO95MLD-1^06243009.0188600 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
696128584-46729-DTLSB-08_01_2023-GO95MLD-1^06243009.0188701 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
408101594-65729-DTLSB-08_01_2023-GO95MLD-1^06243009.0189803 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
972160814-65629-DTLSB-08_09_2023-GO95MLD-1^06243009.0190500 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
286670616-81616-DTLSB-08_09_2023-GO95MLD-1^06243009.0191701 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
110229804-37629-DTLSB-08_09_2023-GO95MLD-1^06243009.0193300 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
967554324-5629-DTLSB-08_09_2023-GO95MLD-1^06243009.0196100 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
959117324-40629-DTLSB-08_07_2023-GO95HV-1^06243009.0196202 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
539838210-762-DTLSB-07_19_2023-GO95MLD-1^06243010.0034000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
539838210-762-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0034000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
728421699-8029-DTLSB-07_18_2023-GO95MLD-1^06243010.0037400 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
566666751-10582-DTLSB-07_18_2023-GO95MLD-1^06243010.0037801 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
520905170-31662-DTLSB-07_18_2023-SVCRUBLG-1^06243010.0038303 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
480408789-65742-DTLSB-07_18_2023-GO95HV-1^06243010.0038401 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
782959069-7029-DTLSB-07_19_2023-GO95HV-1^06243010.0039001 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
391307811-15582-DTLSB-07_19_2023-GO95HV-1^06243010.0039103 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
402091769-15642-DTLSB-07_19_2023-GO95MLD-1^06243010.0039104 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
236646300-57029-DTLSB-07_19_2023-GO95MLD-1^06243010.0039200 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
560729139-37029-DTLSB-07_19_2023-GO95MLD-1^06243010.0039204 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
879548049-28942-DTLSB-07_19_2023-GO95CL10-1^06243010.0039206 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
175214289-77029-DTLSB-07_18_2023-GO95MLD-1^06243010.0039305 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
252923239-58742-DTLSB-07_18_2023-SVCDEFLC-1^06243010.0039500 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
518936440-31162-DTLSB-07_18_2023-SVCDEFLC-1^06243010.0039502 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
811824334-41629-DTLSB-08_07_2023-GO95HV-1^06243009.0196501 | OTHER | CA-NON-TIER | Distribution | 2023-08-07 | 2028-08-07 | 3
59987334-81629-DTLSB-08_02_2023-GO95HV-1^06243009.0196601 | OTHER | CA-NON-TIER | Distribution | 2023-08-02 | 2028-08-02 | 3
579074441-7882-DTLSB-07_31_2023-GO95MLD-1^06243009.0196701 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
119427744-82629-DTLSB-07_27_2023-GO95HV-1^06243009.0196801 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
457128854-49629-DTLSB-07_27_2023-GO95MLD-2^06243009.0196902 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
361685854-83629-DTLSB-07_27_2023-GUYNOINS-2^06243009.0196904 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
453976354-63629-DTLSB-07_27_2023-GO95HV-1^06243009.0196905 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
983378754-10629-DTLSB-08_07_2023-GO95MLD-1^06243009.0197001 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
476260874-99979-DTLSB-07_31_2023-GO95MLD-1^06243009.0198800 | OTHER | CA-NON-TIER | Distribution | 2023-07-31 | 2028-07-31 | 3
132507637-63479-DTLTRT-08_21_2023-SVCDEFLC-1^06243009.0213400 | OTHER | CA-TIER-2 | Distribution | 2023-08-21 | 2026-08-21 | 2
863647187-20989-DTLSB-08_17_2023-GO95BLTC-1^06243009.0214301 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
863647187-20989-DTLSB-08_17_2023-GO95MLD-1^06243009.0214301 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
653540667-91099-DTLSB-08_17_2023-GO95HV-1^06243009.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
134175447-35669-DTLSB-08_16_2023-GO95MLD-1^06243009.0218940 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
537247597-81109-DTLSB-08_21_2023-GUYHINS-1^06243009.0219000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
644138927-20829-DTLSB-08_21_2023-GO95HV-1^06243009.0219200 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
29322767-35199-DTLSB-08_21_2023-GO95MLD-1^06243009.0219700 | OTHER | CA-TIER-2 | Distribution | 2023-08-21 | 2028-08-21 | 3
29322767-35199-DTLSB-08_21_2023-SVCDEFLC-1^06243009.0219700 | OTHER | CA-TIER-2 | Distribution | 2023-08-21 | 2026-08-21 | 2
105017367-8829-ADMIN-06_30_2022-POLEREPL-1^06243009.0219802 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
105017367-8829-DTLSB-08_21_2023-XARMBRAC-1^06243009.0219802 | CROSSARM | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
812981187-25822-ADMIN-06_30_2022-POLEREPL-1^06243009.0219803 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
812981187-25822-DTLSB-08_21_2023-GO95HV-1^06243009.0219803 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
700707307-87829-DTLSB-08_21_2023-GO95MLD-1^06243009.0220800 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
343666524-77524-DTLSB-08_10_2023-GO95MLD-1^06243009.0225700 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
771237369-9369-DTLSB-08_23_2023-SVCDEFLC-1^06243009.0231600 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
713366269-59269-DTLSB-08_03_2023-GO95MLD-1^06243009.0231700 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2028-08-03 | 3
155990269-42269-DTLSB-08_03_2023-GO95MLD-1^06243009.0231800 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
155990269-42269-DTLSB-08_03_2023-SVCNEUT-1^06243009.0231800 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
575401169-52169-DTLSB-08_03_2023-GO95HV-1^06243009.0231900 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2028-08-03 | 3
678288189-63229-DTLSB-08_15_2023-GO95MLD-1^06243009.0232003 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
984102540-23262-DTLSB-07_18_2023-GO95HV-1^06243010.0039601 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
144964360-68362-DTLSB-07_18_2023-GO95MLD-1^06243010.0039801 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
197328589-56642-DTLSB-07_19_2023-GO95HV-1^06243010.0104900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
170301679-85679-DTLSB-07_19_2023-ABNDEQPM-1^06243010.0105900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
170301679-85679-DTLSB-07_19_2023-GO95MLD-1^06243010.0105900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
170301679-85679-DTLSB-07_19_2023-GRDRODHI-1^06243010.0105900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
571040769-6029-DTLSB-07_19_2023-GO95HV-1^06243010.0105901 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
209391431-42431-DTLSB-07_19_2023-GO95MLD-1^06243010.0108901 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
601159694-86794-DTLSB-07_25_2023-GO95MLD-1^06243010.0109200 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
241017049-65852-DTLSB-07_25_2023-GO95HV-1^06243010.0110201 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
594828369-38352-DTLSB-07_27_2023-GO95HV-1^06243010.0110500 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
318521070-42972-DTLSB-07_24_2023-GO95MLD-1^06243010.0110700 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
706265629-61552-DTLSB-07_24_2023-GO95MLD-1^06243010.0110800 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
382153090-30589-DTLSB-07_24_2023-GO95MLD-1^06243010.0110801 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
494506980-93672-DTLSB-07_24_2023-SVCDEFLC-1^06243010.0110802 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
12274430-64272-DTLSB-07_24_2023-GO95MLD-1^06243010.0110803 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
12274430-64272-DTLSB-07_24_2023-SVCDEFLC-1^06243010.0110803 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
180166050-1472-DTLSB-07_19_2023-GO95HV-1^06243010.0110907 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
792789590-5572-DTLSB-07_24_2023-GO95MLD-1^06243010.0111800 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
942283570-30572-DTLSB-07_24_2023-SVCDEFLC-1^06243010.0111801 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
39663970-94499-DTLSB-07_24_2023-GO95MLD-1^06243010.0112801 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
845116230-4272-DTLSB-07_24_2023-GO95MLD-1^06243010.0112901 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
150263753-84890-DTLSB-07_17_2023-GO95MLD-1^06243010.0116500 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
297886740-56172-DTLSB-07_25_2023-GO95MLD-1^06243010.0116800 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
813776320-96962-DTLSB-07_17_2023-GO95MLD-1^06243010.0117700 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
21184000-96172-DTLSB-07_17_2023-GO95HV-1^06243010.0117801 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
878960530-34299-DTLSB-07_17_2023-SVCRUBLG-1^06243010.0117802 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
985717690-61962-DTLSB-07_17_2023-GO95MLD-1^06243010.0118201 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
198934520-36472-DTLSB-07_17_2023-GO95MLD-1^06243010.0118900 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
242152070-63029-DTLSB-07_17_2023-GO95MLD-1^06243010.0119002 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
80182955-19289-DTLSB-08_02_2023-GO95HV-1^06243010.0130400 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
265493708-31329-DTLSB-08_07_2023-GO95MLD-1^06243010.0131000 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
493814308-78702-DTLSB-08_07_2023-ABNDEQPM-1^06243010.0131001 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
493814308-78702-DTLSB-08_07_2023-GO95MLD-1^06243010.0131001 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
695510355-52668-DTLSB-08_02_2023-GO95HV-1^06243010.0131105 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
160447788-86679-DTLSB-08_02_2023-GO95HV-1^06243010.0131201 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
536426378-16179-DTLSB-08_02_2023-GO95HV-1^06243010.0131300 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
536426378-16179-DTLSB-08_02_2023-GO95MLD-1^06243010.0131300 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
751569350-61229-DTLSB-08_03_2023-INSULDMG-1^06243009.0232301 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
607558391-30491-DTLSB-08_14_2023-GO95HV-1^06243009.0236902 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
216575606-6668-DTLSB-08_14_2023-GO95HV-1^06243009.0241800 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
518907831-85789-DTLSB-08_14_2023-GO95MLD-1^06243009.0242300 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
304739299-27029-DTLSB-08_14_2023-GO95HV-1^06243009.0242900 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
872456400-71029-DTLSB-08_14_2023-INSULDMG-1^06243009.0245300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
872456400-71029-DTLSB-08_14_2023-INSULDMG-2^06243009.0245300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
964799700-51029-DTLSB-08_14_2023-INSULDMG-1^06243009.0245301 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
20750621-70889-DTLSB-08_15_2023-GO95MLD-1^06243009.0245500 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
121475103-37103-DTLSB-08_14_2023-GO95MLD-1^06243009.0246002 | OTHER | CA-TIER-2 | Distribution | 2023-08-14 | 2028-08-14 | 3
257235591-51282-DTLSB-08_14_2023-GO95MLD-1^06243009.0246104 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
582852706-4298-DTLSB-08_16_2023-GUYHINS-1^06243009.0246200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
760145948-36329-ADMIN-12_02_2022-POLEREPL-1^06243009.0256200 | POLE | CA-NON-TIER | Distribution | 2022-12-02 | 2025-12-02 | 2
475827506-82599-DTLSB-08_15_2023-GO95MLD-1^06243009.0261000 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
198687194-76429-DTLSB-08_15_2023-GO95MLD-1^06243009.0262200 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
835634685-22599-DTLSB-08_15_2023-GO95MLD-1^06243009.0262400 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
114234958-44329-DTLSB-08_02_2023-GO95MLD-1^06243010.0131400 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
54761075-71329-DTLSB-08_02_2023-GO95TCH-1^06243010.0132100 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
433181375-54189-DTLSB-08_02_2023-GO95MLD-1^06243010.0132101 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
433181375-54189-DTLSB-08_02_2023-GUYHINS-1^06243010.0132101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
434147539-20639-DTLSB-08_02_2023-GO95TCH-1^06243010.0132143 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
622618915-80329-DTLSB-08_02_2023-GO95HV-1^06243010.0132303 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
84720448-94989-DTLSB-08_02_2023-GO95MLD-1^06243010.0132400 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
904583715-98429-DTLSB-08_15_2023-SVCDEFLC-1^06243009.0262700 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
904583715-98429-DTLSB-08_15_2023-SVCENTCO-1^06243009.0262700 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
392806926-27926-DTLSB-08_15_2023-GO95MLD-1^06243009.0263302 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
505786394-79429-DTLSB-08_15_2023-GO95MLD-1^06243009.0263801 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
787563348-42899-DTLSB-08_15_2023-GO95MLD-1^06243009.0267001 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
791784713-90489-DTLSB-08_10_2023-GO95MLD-1^06243009.0276100 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
951388821-89529-DTLSB-08_16_2023-GUYNOINS-1^06243009.0281802 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
605147931-629-DTLSB-08_07_2023-GO95HV-1^06243009.0281804 | OTHER | CA-NON-TIER | Distribution | 2023-08-07 | 2028-08-07 | 3
807229931-49529-DTLSB-08_07_2023-GO95STUB-1^06243009.0281805 | OTHER | CA-NON-TIER | Distribution | 2023-08-07 | 2026-08-07 | 2
654706843-78189-DTLSB-08_16_2023-GO95MLD-1^06243009.0283200 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
504294483-32452-DTLSB-08_16_2023-SVCDEFLC-1^06243009.0283600 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
362854203-15589-DTLSB-08_16_2023-GO95HV-1^06243009.0283601 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2028-08-16 | 3
320830463-2199-DTLSB-08_16_2023-RISEGRD-1^06243009.0284200 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
707214863-3979-DTLSB-08_21_2023-GO95HV-1^06243009.0286901 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
882247005-329-DTLSB-08_02_2023-GO95MLD-1^06243010.0134100 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
549780174-8229-DTLSB-08_16_2023-GO95HV-1^06243010.0134200 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2028-08-16 | 3
350112414-10432-DTLSB-07_20_2023-GO95MLD-1^06243010.0141600 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
443767393-59393-DTLSB-07_20_2023-GO95HV-1^06243010.0142703 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
909822683-33683-DTLSB-07_20_2023-GO95MLD-1^06243010.0143702 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
72444574-82179-DTLSB-07_20_2023-SVCDEFLC-1^06243010.0144400 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
307034483-35980-DTLSB-07_20_2023-GO95MLD-1^06243010.0145700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
497552134-84879-DTLSB-08_07_2023-GO95MLD-1^06243010.0148100 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
497552134-84879-DTLSB-08_07_2023-GO95TCH-1^06243010.0148100 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
170309454-70229-DTLSB-07_17_2023-GUYNOINS-2^06243010.0148703 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
247121484-12229-DTLSB-07_17_2023-GUYNOINS-1^06243010.0148803 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
247121484-12229-DTLSB-07_17_2023-GUYNOINS-2^06243010.0148803 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
85796774-52229-DTLSB-07_17_2023-GO95HV-1^06243010.0148804 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
80932284-22229-DTLSB-07_17_2023-GO95HV-1^06243010.0148900 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
457345184-55289-DTLSB-07_17_2023-GO95MLD-1^06243010.0149400 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
435319434-18689-DTLSB-07_17_2023-GO95MLD-1^06243010.0149401 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
867019594-82229-DTLSB-07_17_2023-GO95MLD-1^06243010.0149900 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
558244884-42229-DTLSB-07_17_2023-GO95MLD-1^06243010.0149901 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
114966953-44292-DTLSB-08_02_2023-GO95HV-1^06243010.0156200 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
218103913-48792-DTLSB-07_27_2023-GO95MLD-1^06243010.0156701 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
949819423-61992-DTLSB-07_27_2023-GO95MLD-1^06243010.0156702 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
854116473-21592-DTLSB-07_26_2023-SVCENTCO-1^06243010.0156800 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
691291343-10292-DTLSB-08_01_2023-GO95HV-1^06243010.0157201 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
143740433-99992-DTLSB-08_02_2023-GO95HV-1^06243010.0157202 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
721074303-62792-DTLSB-08_01_2023-GO95MLD-1^06243010.0158301 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
721074303-62792-DTLSB-08_01_2023-SVCDEFLC-1^06243010.0158301 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
412935661-60582-DTLSB-08_01_2023-GO95MLD-1^06243010.0159601 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
79567813-19813-DTLTRT-07_26_2023-GO95HV-1^06243010.0159703 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
460032913-66731-AUDIT-09_05_2023-GO95TCH-1^06243010.0159800 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
707214863-3979-DTLSB-08_21_2023-GO95MLD-1^06243009.0286901 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
285926408-27929-DETAIL-01_12_2021-SVCROAD-1^06243009.0293602 | OTHER | CA-TIER-2 | Distribution | 2021-01-12 | 2024-01-12 | 2
285926408-27929-DETAIL-01_12_2021-SVCWIND-1^06243009.0293602 | OTHER | CA-TIER-2 | Distribution | 2021-01-12 | 2024-01-12 | 2
177919949-81629-AUDIT-04_05_2021-GRDRODHI-1^06243009.0321000 | OTHER | CA-TIER-2 | Distribution | 2021-04-05 | 2024-04-05 | 2
142918658-74629-DETAIL-02_22_2021-GO95MLD-1^06243009.0322301 | OTHER | CA-TIER-2 | Distribution | 2021-02-22 | 2026-02-22 | 3
103529559-54629-DETAIL-02_04_2021-SVCENTCO-1^06243009.0323200 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2024-02-04 | 2
682273511-90129-DTLSB-07_19_2023-GO95MLD-1^06243010.0020000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
389046231-58231-DETAIL-09_20_2023-POLEREPL-1^06243010.0020003 | POLE | CA-TIER-2 | Distribution | 2023-09-20 | 2024-09-20 | 2
524098910-70189-DTLSB-07_19_2023-SVCENTCO-1^06243010.0021400 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
827785830-50129-DTLSB-07_24_2023-GO95HV-1^06243010.0021701 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
505493081-16342-DTLSB-07_24_2023-GO95HV-1^06243010.0022100 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
793023671-65042-DTLSB-07_19_2023-GO95HV-1^06243010.0022200 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
577843500-46832-DTLSB-07_19_2023-GO95MLD-1^06243010.0022201 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
496662753-32292-DTLSB-07_27_2023-GO95MLD-1^06243010.0159900 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
496662753-32292-DTLSB-07_27_2023-RISEGRD-1^06243010.0159900 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
159744355-71678-DTLSB-08_08_2023-GO95MLD-1^06243010.0230002 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
873641344-13299-DTLSB-08_08_2023-GO95MLD-1^06243010.0231101 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
403650464-96129-DTLSB-08_08_2023-GUYNOINS-1^06243010.0237400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
196614404-37689-DTLSB-08_07_2023-GO95MLD-1^06243010.0239400 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
644310644-71489-DTLSB-08_09_2023-GO95MLD-1^06243010.0247800 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
225402434-55412-DTLSB-08_09_2023-GO95HV-1^06243010.0248701 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
225402434-55412-DTLSB-08_09_2023-GO95MLD-1^06243010.0248701 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
406850134-73029-DTLSB-08_09_2023-GO95MLD-1^06243010.0249600 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
430190320-16769-DTLSB-08_08_2023-GO95MLD-1^06243010.0260401 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
626930919-23842-DTLSB-08_08_2023-GO95HV-1^06243010.0260901 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
159980588-95642-DTLSB-08_08_2023-GO95HV-1^06243010.0264900 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
834822685-31679-DTLSB-08_08_2023-GO95MLD-1^06243010.0277300 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
882821149-20129-DTLSB-07_20_2023-GO95MLD-1^06243010.0023401 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
975529269-7579-DTLSB-07_24_2023-GO95MLD-1^06243010.0024403 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
688597758-98758-DTLSB-07_24_2023-GO95HV-1^06243010.0025700 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
870190770-47199-DTLSB-07_25_2023-GO95BLTC-1^06243010.0026200 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
870190770-47199-DTLSB-07_25_2023-GO95HV-1^06243010.0026200 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
870190770-47199-DTLSB-07_25_2023-GO95MLD-1^06243010.0026200 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
994504990-79789-DTLSB-07_20_2023-GO95MLD-1^06243010.0026402 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
128855166-73669-DTLSB-07_27_2023-GO95MLD-1^06243010.0029100 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
241112060-25489-DTLSB-07_19_2023-GO95MLD-1^06243010.0035000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
566575019-57042-DTLSB-07_18_2023-GO95HV-1^06243010.0035501 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
430291109-51042-DTLSB-07_18_2023-GO95HV-1^06243010.0037500 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
407513280-5762-DTLSB-07_18_2023-GO95HV-1^06243010.0037602 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
407513280-5762-DTLSB-07_18_2023-GO95MLD-1^06243010.0037602 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
885366720-31762-DTLSB-07_18_2023-GO95MLD-1^06243010.0037901 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
448758859-55342-DTLSB-07_19_2023-GO95HV-1^06243010.0038000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
448758859-55342-DTLSB-07_19_2023-GO95MLD-1^06243010.0038000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
494333375-60589-DTLSB-08_08_2023-SVCDEFLC-1^06243010.0277400 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
196635991-21429-DETAIL-02_02_2021-GRDRODHI-1^06243010.0356400 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
939777601-7699-DETAIL-02_04_2021-GO95HV-1^06243010.0357200 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
939777601-7699-DETAIL-02_04_2021-SVCRUBLG-1^06243010.0357200 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2024-02-04 | 2
136665521-32682-DETAIL-02_02_2021-RISEGRD-1^06243010.0358600 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
572852370-19329-DETAIL-02_02_2021-GO95MLD-1^06243010.0359300 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
520905170-31662-DTLSB-07_18_2023-GO95MLD-1^06243010.0038303 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
520905170-31662-DTLSB-07_18_2023-SVCWIND-1^06243010.0038303 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
50914499-63899-DTLSB-07_18_2023-GO95MLD-1^06243010.0038400 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
365841010-29172-DTLSB-07_20_2023-SVCDEFLC-1^06243010.0038700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
449557370-25162-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0039101 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
748972621-72682-DTLSB-07_19_2023-GO95MLD-1^06243010.0039102 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
449721381-94982-DTLSB-07_19_2023-GO95MLD-1^06243010.0039205 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
387730060-33429-DETAIL-02_02_2021-GO95HV-1^06243010.0359400 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
225619090-83429-DETAIL-02_02_2021-GO95HV-1^06243010.0359600 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
225619090-83429-ADMIN-03_03_2023-POLEREPL-1^06243010.0359600 | POLE | CA-TIER-2 | Distribution | 2023-03-03 | 2024-03-03 | 2
416093980-4429-DETAIL-02_02_2021-GO95HV-1^06243010.0359601 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
129903611-23309-DETAIL-02_04_2021-ABNDEQPM-1^06243010.0369902 | OTHER | CA-TIER-2 | Distribution | 2021-02-04 | 2026-02-04 | 3
871067759-36689-DETAIL-04_07_2022-POLEREPL-1^06244005.0232001 | POLE | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
567119115-97489-DETAIL-06_07_2023-ABNDEQPM-1^06244006.0010601 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
567119115-97489-DETAIL-06_07_2023-GO95MLD-1^06244006.0010601 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2026-06-07 | 2
75410344-65599-DETAIL-07_12_2023-GO95MLD-1^06244008.0228200 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
153432064-24789-DETAIL-07_12_2023-GO95HV-1^06244008.0271300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
153432064-24789-DETAIL-07_12_2023-SVCDEFLC-1^06244008.0271300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
108056934-22122-DETAIL-07_13_2023-GO95MLD-1^06244008.0271600 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
467666254-19632-DETAIL-07_13_2023-GO95MLD-1^06244008.0272200 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
879548049-28942-DTLSB-07_19_2023-GO95MLD-1^06243010.0039206 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
594032350-89862-DTLSB-07_18_2023-SVCWIND-1^06243010.0039207 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
297895210-54662-DTLSB-07_18_2023-GO95MLD-1^06243010.0039300 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
301425500-95462-DTLSB-07_18_2023-GO95MLD-1^06243010.0039301 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
583323230-66762-DTLSB-07_19_2023-GO95TCH-1^06243010.0039302 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
511017179-50742-DTLSB-07_18_2023-GO95MLD-1^06243010.0039303 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
675615400-11362-DTLSB-07_18_2023-GO95MLD-1^06243010.0039304 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
175214289-77029-DTLSB-07_18_2023-GO95HV-1^06243010.0039305 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
252923239-58742-DTLSB-07_18_2023-GO95MLD-1^06243010.0039500 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
708278750-91362-DTLSB-07_18_2023-GO95HV-1^06243010.0039701 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
156471560-76362-DTLSB-07_18_2023-GO95HV-1^06243010.0039800 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
144964360-68362-DTLSB-07_18_2023-GO95HV-1^06243010.0039801 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
197328589-56642-DTLSB-07_19_2023-GO95MLD-1^06243010.0104900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
170301679-85679-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0105900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
478079166-81266-DTLSB-07_25_2023-GO95MLD-1^06243010.0109300 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
277897014-13114-DTLSB-07_25_2023-GO95MLD-1^06243010.0110202 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
812999844-96532-DETAIL-07_13_2023-GO95MLD-1^06244008.0272201 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
276580202-28010-DETAIL-07_13_2023-GO95HV-1^06244008.0272202 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
746805014-58722-DETAIL-07_12_2023-GO95MLD-1^06244008.0276701 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
746805014-58722-DETAIL-07_12_2023-SVCDEFLC-1^06244008.0276701 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
500741814-87129-DETAIL-07_13_2023-ENCHRW-1^06244008.0278500 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
500741814-87129-DETAIL-07_13_2023-GO95MLD-1^06244008.0278500 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
919646164-97129-DETAIL-07_12_2023-GO95MLD-1^06244008.0279700 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
919646164-97129-DETAIL-07_12_2023-GO95TCH-1^06244008.0279700 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
52167894-63129-DETAIL-07_11_2023-GO95MLD-1^06244008.0281004 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
52167894-63129-DETAIL-07_11_2023-SVCDEFLC-1^06244008.0281004 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
141595274-27532-DETAIL-07_13_2023-GO95MLD-1^06244008.0281100 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
141595274-27532-DETAIL-07_13_2023-RISEGRD-1^06244008.0281100 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
14515764-38822-DETAIL-07_11_2023-XARMSPCR-1^06244008.0284101 | CROSSARM | CA-TIER-2 | Distribution | 2023-07-11 | 2024-07-11 | 2
626656134-45032-DETAIL-07_11_2023-GO95MLD-1^06244008.0285100 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
471831024-81832-DETAIL-07_11_2023-GO95MLD-1^06244008.0285102 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
760034954-42622-DETAIL-07_11_2023-GO95HV-1^06244008.0285103 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
742068395-43732-DETAIL-07_11_2023-GO95MLD-1^06244008.0285200 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
689696184-22-DETAIL-07_11_2023-GO95MLD-1^06244008.0286300 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
35136124-35129-DETAIL-07_12_2023-GO95HV-1^06244008.0289300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
35136124-35129-DETAIL-07_12_2023-GO95MLD-1^06244008.0289300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
488474276-56972-DETAIL-07_10_2023-GO95HV-1^06244008.0290200 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2028-07-10 | 3
488474276-56972-DETAIL-07_10_2023-GO95MLD-1^06244008.0290200 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2028-07-10 | 3
589235276-55972-DETAIL-07_10_2023-GO95HV-1^06244008.0290201 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2028-07-10 | 3
924297259-87029-DTLSB-07_27_2023-GO95HV-1^06243010.0110401 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
594828369-38352-DTLSB-07_27_2023-GO95MLD-1^06243010.0110500 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
571073619-31252-DTLSB-07_24_2023-GO95MLD-1^06243010.0110600 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
494506980-93672-DTLSB-07_24_2023-SVCROAD-1^06243010.0110802 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
844380330-62372-DTLSB-07_24_2023-GO95MLD-1^06243010.0110900 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
876349840-87872-DTLSB-07_24_2023-GO95MLD-1^06243010.0110902 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
968447150-13472-DTLSB-07_27_2023-GO95MLD-1^06243010.0111500 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
845116230-4272-DTLSB-07_24_2023-GO95HV-1^06243010.0112901 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
297886740-56172-DTLSB-07_25_2023-ABNDEQPM-1^06243010.0116800 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
297886740-56172-DTLSB-07_25_2023-GO95HV-1^06243010.0116800 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
930788530-47772-DTLSB-07_17_2023-GO95HV-1^06243010.0118200 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
930788530-47772-DTLSB-07_17_2023-GO95MLD-1^06243010.0118200 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
985717690-61962-DTLSB-07_17_2023-ABNDEQPM-1^06243010.0118201 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
385948279-29952-DTLSB-07_17_2023-GO95HV-1^06243010.0119100 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
715162950-11862-DTLSB-07_26_2023-GO95HV-1^06243010.0119400 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
181576308-17702-DTLSB-08_07_2023-GO95MLD-1^06243010.0130000 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
118042495-90069-DETAIL-07_11_2023-GO95MLD-1^06244008.0291001 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2028-07-11 | 3
887188586-47972-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0291401 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2028-07-11 | 3
455765871-79669-DETAIL-07_11_2023-GO95MLD-1^06244008.0292001 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2026-07-11 | 2
661930926-94982-DETAIL-07_11_2023-GO95MLD-1^06244008.0292601 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
639493656-46772-DETAIL-07_11_2023-GO95MLD-1^06244008.0293000 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
493383701-22742-DETAIL-07_11_2023-GO95HV-1^06244008.0294000 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
508383371-39202-DETAIL-07_10_2023-GO95MLD-1^06244008.0302001 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
132495933-28280-DTLSB-08_02_2023-GO95MLD-1^06243010.0130500 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
121266595-3329-DTLSB-08_07_2023-GO95MLD-1^06243010.0131101 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
661816135-81329-DTLSB-08_02_2023-GO95MLD-1^06243010.0131104 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
695510355-52668-DTLSB-08_02_2023-GO95MLD-1^06243010.0131105 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
432949183-40283-DTLSB-08_02_2023-SVCROAD-1^06243010.0131205 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
432949183-40283-DTLSB-08_02_2023-SVCROAD-2^06243010.0131205 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
571463845-8799-DTLSB-08_02_2023-GO95MLD-1^06243010.0131402 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
508383371-39202-AUDIT-08_29_2023-GO95TCH-1^06244008.0302001 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
595593091-63502-DETAIL-07_10_2023-GO95MLD-1^06244008.0305100 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2028-07-10 | 3
595593091-63502-DETAIL-07_10_2023-GO95TCH-1^06244008.0305100 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
965669201-41389-DETAIL-07_10_2023-GO95MLD-1^06244008.0306200 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
965669201-41389-DETAIL-07_10_2023-GO95TCH-1^06244008.0306200 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
557935071-1402-DETAIL-07_10_2023-GO95MLD-1^06244008.0307201 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
543071811-10479-DETAIL-07_10_2023-GO95MLD-1^06244008.0307202 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
97369351-10848-DETAIL-07_10_2023-GO95MLD-1^06244008.0307204 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
509688837-25289-DTLSB-08_02_2023-GO95HV-1^06243010.0131404 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
509688837-25289-DTLSB-08_02_2023-GO95MLD-1^06243010.0131404 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
433181375-54189-DTLSB-08_02_2023-SVCDEFLC-1^06243010.0132101 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
433181375-54189-DTLSB-08_02_2023-SVCROAD-1^06243010.0132101 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
156119585-42329-DTLSB-08_02_2023-SVCDEFLC-1^06243010.0132102 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
294441885-72329-DTLSB-08_02_2023-GO95MLD-1^06243010.0132200 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
41833835-1329-DTLSB-08_02_2023-GO95MLD-1^06243010.0132300 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
670634851-39102-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0308000 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
451122436-47982-DETAIL-07_18_2023-GO95MLD-1^06244008.0310300 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
679260385-56385-DETAIL-06_28_2023-GO95MLD-1^06244008.0310901 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
692130406-40272-DETAIL-07_05_2023-GO95HV-1^06244008.0311900 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
692130406-40272-DETAIL-07_05_2023-GO95MLD-1^06244008.0311900 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
909240896-40582-DETAIL-06_28_2023-GO95MLD-1^06244008.0312800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
978171386-55482-DETAIL-06_28_2023-GO95HV-1^06244008.0312801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
628468697-37692-DETAIL-07_05_2023-GO95MLD-1^06244008.0316840 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
222497627-44692-DETAIL-07_05_2023-GO95MLD-1^06244008.0317840 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
610015081-29129-DETAIL-07_05_2023-GUYNOINS-1^06244008.0320700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-07-05 | 2026-07-05 | 2
105210781-95342-DETAIL-07_13_2023-GO95MLD-1^06244008.0320801 | OTHER | CA-NON-TIER | Distribution | 2023-07-13 | 2026-07-13 | 2
365235786-50182-DETAIL-07_11_2023-GO95HV-1^06244008.0321900 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2028-07-11 | 3
534744246-98982-DETAIL-07_05_2023-ABNDEQPM-1^06244008.0322700 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
534744246-98982-DETAIL-07_05_2023-GO95HV-1^06244008.0322700 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
114495718-49692-DETAIL-07_05_2023-GO95HV-1^06244008.0322740 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
285683546-11489-DETAIL-07_11_2023-GO95MLD-1^06244008.0322901 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2028-07-11 | 3
631215991-84213-DETAIL-07_06_2023-GO95MLD-1^06244008.0325800 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2028-07-06 | 3
806831391-33213-DETAIL-07_06_2023-GO95MLD-1^06244008.0325903 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2026-07-06 | 2
966738836-78129-DETAIL-07_06_2023-GO95MLD-1^06244008.0326700 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
353341967-26692-DETAIL-07_06_2023-GO95CL10-1^06244008.0326740 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2028-07-06 | 3
353341967-26692-DETAIL-07_06_2023-GO95MLD-1^06244008.0326740 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
651114995-96172-DETAIL-07_07_2023-GO95MLD-1^06244008.0327500 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
257931995-25172-DETAIL-07_13_2023-GO95MLD-1^06244008.0327501 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
812838005-50329-DTLSB-08_02_2023-GO95MLD-1^06243010.0133200 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
882247005-329-DTLSB-08_02_2023-GRDRODHI-1^06243010.0134100 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
429009674-39229-DTLSB-08_16_2023-GO95HV-1^06243010.0134201 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2028-08-16 | 3
429355164-96229-DTLSB-08_09_2023-GO95HV-1^06243010.0135000 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
87232764-37229-DTLSB-08_09_2023-GO95MLD-1^06243010.0135001 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
62629174-57229-DTLSB-08_02_2023-GO95MLD-1^06243010.0135002 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
421676875-98229-DTLSB-08_16_2023-GO95MLD-1^06243010.0135200 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
858649314-78332-DTLSB-07_24_2023-GO95MLD-1^06243010.0141700 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
803016314-42812-DTLSB-07_20_2023-GO95MLD-1^06243010.0142600 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
803016314-42812-DTLSB-07_20_2023-SVCDEFLC-1^06243010.0142600 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
59532393-7534-DTLSB-07_20_2023-GO95MLD-1^06243010.0142704 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
912607583-29583-DTLSB-07_20_2023-GO95HV-1^06243010.0144701 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
842538383-79383-DTLSB-07_20_2023-GO95HV-1^06243010.0146700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
842538383-79383-DTLSB-07_20_2023-GO95MLD-1^06243010.0146700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
94657653-98653-DTLSB-07_20_2023-GO95MLD-1^06243010.0146702 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
555580653-61653-DTLSB-07_20_2023-GO95HV-1^06243010.0147700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
789554573-36640-DETAIL-07_07_2023-GO95MLD-1^06244008.0328300 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
844367566-27772-DETAIL-07_13_2023-GO95MLD-1^06244008.0328700 | OTHER | CA-NON-TIER | Distribution | 2023-07-13 | 2026-07-13 | 2
237641808-18692-DETAIL-07_13_2023-GO95HV-1^06244008.0328740 | OTHER | CA-NON-TIER | Distribution | 2023-07-13 | 2028-07-13 | 3
237641808-18692-DETAIL-07_13_2023-GO95MLD-1^06244008.0328740 | OTHER | CA-NON-TIER | Distribution | 2023-07-13 | 2026-07-13 | 2
86518011-77632-DETAIL-07_07_2023-GRDRODHI-1^06244008.0329801 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
495877901-78599-DETAIL-07_06_2023-GRDRODHI-1^06244008.0329901 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
943169156-28129-DETAIL-07_06_2023-GO95MLD-1^06244008.0329902 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2028-07-06 | 3
20913590-4532-DETAIL-07_06_2023-GO95MLD-1^06244008.0329903 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2026-07-06 | 2
20913590-4532-DETAIL-07_06_2023-SVCROAD-1^06244008.0329903 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2026-07-06 | 2
733126964-80722-DETAIL-07_07_2023-GO95TCH-1^06244008.0330200 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
313849664-49822-DETAIL-07_07_2023-GO95HV-1^06244008.0330401 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2028-07-07 | 3
258099104-35962-DETAIL-07_07_2023-GO95MLD-1^06244008.0330501 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
555633876-18876-DETAIL-07_07_2023-GO95MLD-1^06244008.0330700 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
351639544-56522-DETAIL-07_06_2023-GO95MLD-1^06244008.0330900 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
213711464-88622-DETAIL-07_12_2023-GO95HV-1^06244008.0332900 | OTHER | CA-NON-TIER | Distribution | 2023-07-12 | 2028-07-12 | 3
213711464-88622-DETAIL-07_12_2023-POLETOP-1^06244008.0332900 | POLE | CA-NON-TIER | Distribution | 2023-07-12 | 2026-07-12 | 2
333727553-38553-DTLSB-07_20_2023-GO95MLD-1^06243010.0147701 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
278427243-50343-DTLSB-07_17_2023-GO95MLD-1^06243010.0148600 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
37705664-61229-DTLSB-07_20_2023-GUYNOINS-1^06243010.0148700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
37705664-61229-DTLSB-07_20_2023-GUYNOINS-2^06243010.0148700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
976494801-35241-DTLSB-07_17_2023-GO95MLD-1^06243010.0148702 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
170309454-70229-DTLSB-07_17_2023-GUYNOINS-1^06243010.0148703 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
943620124-91229-DTLSB-07_17_2023-GO95MLD-1^06243010.0148801 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
457345184-55289-DTLSB-07_17_2023-RISEGRD-1^06243010.0149400 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
230836163-62492-DTLSB-08_02_2023-GO95MLD-1^06243010.0156100 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
728923003-23792-DTLSB-08_01_2023-GO95HV-1^06243010.0157200 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
296514583-45692-DTLSB-08_01_2023-GO95MLD-1^06243010.0158400 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
673384983-78799-DTLSB-08_01_2023-GO95MLD-1^06243010.0159700 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
52445811-74082-DTLSB-07_26_2023-GUYNOINS-1^06243010.0159702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
52445811-74082-DTLSB-07_26_2023-GUYNOINS-2^06243010.0159702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
406332894-49129-DTLSB-08_08_2023-GO95TCH-1^06243010.0230000 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
552389314-29129-DTLSB-08_08_2023-GO95HV-1^06243010.0230001 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
213711464-88622-DETAIL-07_12_2023-XARMSPCR-1^06244008.0332900 | CROSSARM | CA-NON-TIER | Distribution | 2023-07-12 | 2026-07-12 | 2
340196794-13129-DETAIL-07_11_2023-XARMSPCR-1^06244008.0333900 | CROSSARM | CA-TIER-2 | Distribution | 2023-07-11 | 2024-07-11 | 2
838216285-38788-DETAIL-07_11_2023-SVCENTBK-1^06244008.0333901 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2026-07-11 | 2
584644045-17132-DETAIL-07_12_2023-GO95MLD-1^06244008.0335200 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
683845615-18329-DETAIL-07_07_2023-GO95MLD-1^06244008.0335700 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
278219754-23722-DETAIL-07_13_2023-GO95HV-1^06244008.0337700 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
594196944-36622-DETAIL-07_13_2023-GO95HV-1^06244008.0337701 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
892973804-22622-DETAIL-07_13_2023-GO95MLD-1^06244008.0337901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
225223835-2699-DETAIL-07_13_2023-GO95MLD-1^06244008.0339900 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
802957764-95922-DETAIL-07_13_2023-GO95HV-1^06244008.0339902 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
371386504-45132-DETAIL-07_13_2023-GO95MLD-1^06244008.0343800 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
728076505-2129-DETAIL-07_13_2023-GO95MLD-1^06244008.0343900 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
940537684-96032-DETAIL-07_13_2023-GO95MLD-1^06244008.0343901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
516876002-79498-DETAIL-07_13_2023-GO95HV-1^06244008.0343903 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
425448705-70832-DETAIL-07_13_2023-SVCENTCO-1^06244008.0344900 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
614676314-58129-DTLSB-08_08_2023-GO95HV-1^06243010.0231102 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
403650464-96129-DTLSB-08_08_2023-GUYNOINS-2^06243010.0237400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
112052454-97129-DTLSB-08_07_2023-GO95HV-1^06243010.0238401 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
196614404-37689-DTLSB-08_07_2023-SVCDEFLC-1^06243010.0239400 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
837953544-22129-DTLSB-08_09_2023-GO95HV-1^06243010.0247801 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
837953544-22129-DTLSB-08_09_2023-GO95MLD-1^06243010.0247801 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
663947534-12129-DTLSB-08_09_2023-GO95HV-1^06243010.0248700 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
449817929-19929-DTLSB-08_09_2023-GO95MLD-1^06243010.0249702 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
213748305-28732-DETAIL-07_13_2023-GO95MLD-1^06244008.0344901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
312159038-10138-DETAIL-07_05_2023-GO95MLD-1^06244009.0019100 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
239426138-56138-DETAIL-06_28_2023-GO95MLD-1^06244009.0113301 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
991610238-50238-DETAIL-06_28_2023-GO95HV-1^06244009.0113600 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
510285538-56538-DETAIL-06_28_2023-XARMSPCR-1^06244009.0115200 | CROSSARM | CA-TIER-2 | Distribution | 2023-06-28 | 2024-06-28 | 2
54014171-45582-DETAIL-07_05_2023-GO95MLD-1^06244009.0124300 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
791374251-78382-DETAIL-07_05_2023-SVCDEFLC-1^06244009.0126301 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
597244699-69529-DETAIL-01_25_2021-GO95MLD-1^06243010.0254101 | OTHER | CA-TIER-2 | Distribution | 2021-01-25 | 2024-01-25 | 2
4453850-7089-DTLSB-08_08_2023-GO95MLD-1^06243010.0260400 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
421495288-28642-DTLSB-08_08_2023-XARMSPCR-1^06243010.0264901 | CROSSARM | CA-TIER-2 | Distribution | 2023-08-08 | 2024-08-08 | 2
494333375-60589-DTLSB-08_08_2023-GO95MLD-1^06243010.0277400 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
731887296-49296-DTLSB-08_08_2023-GO95MLD-1^06243010.0279703 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
196635991-21429-DETAIL-02_02_2021-GO95MLD-1^06243010.0356400 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
175863751-73482-DETAIL-07_05_2023-GO95HV-1^06244009.0127301 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
296484099-71112-DETAIL-07_05_2023-GO95MLD-1^06244009.0130000 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
716180789-10912-DETAIL-07_03_2023-GO95HV-1^06244009.0130001 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
88173739-90312-DETAIL-07_05_2023-GO95MLD-1^06244009.0132300 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
759619338-438-DETAIL-06_28_2023-GO95HV-1^06244009.0143501 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
257070138-61138-DETAIL-06_28_2023-GO95MLD-1^06244009.0143800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
901610592-32699-DETAIL-06_26_2023-GO95MLD-1^06244009.0195002 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
615458773-4229-DETAIL-06_21_2023-GO95MLD-1^06244009.0198202 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
416401303-83692-DETAIL-06_21_2023-GO95TCH-1^06244009.0198370 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
527472951-13423-DETAIL-06_13_2023-GO95HV-1^06244009.0225401 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
598172682-52069-DETAIL-06_28_2023-GO95HV-1^06244009.0228800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
895327779-73112-DETAIL-06_29_2023-GO95MLD-1^06244009.0241000 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
267773109-26212-DETAIL-07_03_2023-GO95MLD-1^06244009.0243500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
776297019-26312-DETAIL-07_03_2023-GO95MLD-1^06244009.0243502 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
434782779-34112-DETAIL-06_29_2023-GO95MLD-1^06244009.0244305 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
202559949-36229-DETAIL-07_03_2023-CUTOUTAR-2^06244009.0244600 | LIGHTNING ARRESTER | CA-TIER-2 | Distribution | 2023-07-03 | 2024-07-03 | 2
268465690-10429-ADMIN-03_03_2023-POLEREPL-1^06243010.0357300 | POLE | CA-TIER-2 | Distribution | 2023-03-03 | 2024-03-03 | 2
373011140-41429-DETAIL-02_02_2021-GO95HV-1^06243010.0357402 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
912062700-28979-DETAIL-02_02_2021-GO95HV-1^06243010.0358502 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
798831770-83099-DETAIL-02_02_2021-GO95MLD-1^06243010.0359302 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
221537960-63429-DETAIL-02_02_2021-GO95HV-1^06243010.0359402 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2026-02-02 | 3
773722231-15429-DETAIL-02_02_2021-GO95MLD-1^06243010.0361401 | OTHER | CA-TIER-2 | Distribution | 2021-02-02 | 2024-02-02 | 2
101783676-84539-ENHANCED-08_21_2023-XARMSPCR-1^06244004.0205341 | CROSSARM | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
498895621-3639-ADMIN-04_26_2023-POLEREPL-1^06244005.0234901 | POLE | CA-NON-TIER | Distribution | 2023-04-26 | 2026-04-26 | 2
410749063-97339-DETAIL-04_07_2022-POLEREPL-1^06244005.0235502 | POLE | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
875034205-38439-DETAIL-06_07_2023-GO95HV-1^06244006.0010600 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
567119115-97489-DETAIL-06_07_2023-GO95HV-1^06244006.0010601 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
116362695-88439-DETAIL-06_07_2023-GO95HV-1^06244006.0011700 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
202559949-36229-DETAIL-07_03_2023-SVCROAD-1^06244009.0244600 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
774572549-61512-DETAIL-07_03_2023-GO95HV-1^06244009.0245400 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
491860108-20329-DETAIL-07_03_2023-GO95HV-1^06244009.0251400 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
901830048-37112-DETAIL-07_03_2023-GO95MLD-1^06244009.0251800 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
176823648-59212-DETAIL-06_28_2023-GO95HV-1^06244009.0252301 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
421128688-32102-DETAIL-07_03_2023-GO95MLD-1^06244009.0252500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
381793248-58202-DETAIL-07_03_2023-GO95MLD-1^06244009.0252700 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
123021895-59439-DETAIL-06_07_2023-GO95HV-1^06244006.0012800 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
969217135-13989-DETAIL-06_07_2023-GO95MLD-1^06244006.0025800 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
69843024-93399-DETAIL-07_12_2023-GO95MLD-1^06244008.0228001 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
624598134-82522-DETAIL-07_12_2023-GO95MLD-1^06244008.0228100 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
982669814-13332-DETAIL-07_12_2023-RISEGRD-1^06244008.0229000 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
153432064-24789-DETAIL-07_12_2023-GO95MLD-1^06244008.0271300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
309761399-43399-DETAIL-07_12_2023-ENCHRW-1^06244008.0274400 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
76433054-26129-DETAIL-07_12_2023-GO95MLD-1^06244008.0274501 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
773508648-43202-DETAIL-07_03_2023-GO95MLD-1^06244009.0252701 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
828570838-40329-DETAIL-07_03_2023-GO95MLD-1^06244009.0253401 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
454831298-84718-DETAIL-06_29_2023-GO95HV-1^06244009.0254800 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
51001388-45412-DETAIL-06_29_2023-GUYHINS-1^06244009.0254801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
199542698-8299-DETAIL-06_28_2023-GO95MLD-1^06244009.0255001 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
878774168-12512-DETAIL-07_03_2023-GO95HV-1^06244009.0255500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
878774168-12512-DETAIL-07_03_2023-GO95MLD-1^06244009.0255500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
763196498-45612-DETAIL-06_29_2023-GO95MLD-1^06244009.0255700 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
881536115-31932-DETAIL-07_12_2023-GO95MLD-1^06244008.0276702 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
695613514-47129-AUDIT-08_29_2023-GO95HV-1^06244008.0277700 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2028-08-29 | 3
310516464-36822-DETAIL-07_12_2023-XARMSPCR-1^06244008.0277702 | CROSSARM | CA-TIER-2 | Distribution | 2023-07-12 | 2024-07-12 | 2
272726594-61669-DETAIL-07_12_2023-GO95MLD-1^06244008.0286100 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
730405726-61672-DETAIL-07_11_2023-GO95MLD-1^06244008.0291000 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2026-07-11 | 2
118042495-90069-DETAIL-07_11_2023-GO95HV-1^06244008.0291001 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2028-07-11 | 3
912352071-60213-DETAIL-07_11_2023-GO95MLD-1^06244008.0292000 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2026-07-11 | 2
493383701-22742-DETAIL-07_11_2023-GO95HV-2^06244008.0294000 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
289243181-78442-DETAIL-07_10_2023-GO95MLD-1^06244008.0300001 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
812463028-14028-DETAIL-07_10_2023-GO95HV-1^06244008.0304001 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2028-07-10 | 3
812463028-14028-DETAIL-07_10_2023-GO95MLD-1^06244008.0304001 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
812463028-14028-DETAIL-07_10_2023-GO95TCH-1^06244008.0304001 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
595593091-63502-DETAIL-07_10_2023-SVCDEFLC-1^06244008.0305100 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
495919641-72102-DETAIL-07_10_2023-GO95MLD-1^06244008.0306202 | OTHER | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
763196498-45612-DETAIL-06_29_2023-RISEGRD-1^06244009.0255700 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
656695328-55012-DETAIL-06_29_2023-GO95MLD-1^06244009.0257701 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
988302238-94989-DETAIL-06_29_2023-GO95MLD-1^06244009.0258800 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
92810039-88369-DETAIL-07_03_2023-GO95MLD-1^06244009.0269500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
730260690-2922-DETAIL-06_27_2023-GO95BLTC-1^06244009.0270200 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
730260690-2922-DETAIL-06_27_2023-GO95MLD-1^06244009.0270200 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
589147957-30057-DETAIL-06_27_2023-GO95BLTC-1^06244009.0270201 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
589147957-30057-DETAIL-06_27_2023-GO95MLD-1^06244009.0270201 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
331772590-32-DETAIL-06_27_2023-GO95CL10-1^06244009.0271800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
276771750-23522-DETAIL-06_27_2023-SVCDEFLC-1^06244009.0272100 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
859781710-54032-DETAIL-06_27_2023-SVCDEFLC-1^06244009.0273100 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
618271961-42632-DETAIL-06_21_2023-GO95MLD-1^06244009.0282001 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2026-06-21 | 2
697351551-80432-DETAIL-06_15_2023-GO95MLD-1^06244009.0282100 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2026-06-15 | 2
697351551-80432-AUDIT-08_01_2023-GO95HV-1^06244009.0282100 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
45079451-64329-DETAIL-06_21_2023-GO95HV-1^06244009.0282101 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2028-06-21 | 3
69311280-3332-DETAIL-06_21_2023-GO95MLD-1^06244009.0283202 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
360216001-22632-DETAIL-06_15_2023-GO95MLD-1^06244009.0285000 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
586296690-55822-DETAIL-06_27_2023-SVCDEFLC-1^06244009.0285002 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
883334417-35369-AUDIT-08_22_2023-GO95MLD-1^06244009.0287000 | OTHER | CA-NON-TIER | Distribution | 2023-08-22 | 2026-08-22 | 2
292322721-25329-DETAIL-06_27_2023-GO95MLD-1^06244009.0287200 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
615963911-85199-DETAIL-06_27_2023-GO95MLD-1^06244009.0289200 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
560824531-72852-AUDIT-08_01_2023-GO95HV-1^06244009.0290700 | OTHER | CA-NON-TIER | Distribution | 2023-08-01 | 2028-08-01 | 3
610527431-1852-DETAIL-06_15_2023-GO95MLD-1^06244009.0290701 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
495919641-72102-DETAIL-07_10_2023-GUYNOINS-1^06244008.0306202 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
495919641-72102-DETAIL-07_10_2023-GUYNOINS-2^06244008.0306202 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-07-10 | 2026-07-10 | 2
222074421-89602-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0309000 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
767072231-25702-DETAIL-07_11_2023-GO95MLD-1^06244008.0309001 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
823070401-48502-DETAIL-07_11_2023-GO95MLD-1^06244008.0309002 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
612201177-14669-DETAIL-07_18_2023-SVCDEFLC-1^06244008.0310200 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
451122436-47982-DETAIL-07_18_2023-GO95TCH-1^06244008.0310300 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
978171386-55482-DETAIL-06_28_2023-GO95MLD-1^06244008.0312801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
425978186-13782-DETAIL-07_18_2023-GO95HV-1^06244008.0314500 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
610015081-29129-DETAIL-07_05_2023-GUYNOINS-2^06244008.0320700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-07-05 | 2026-07-05 | 2
778006186-81182-DETAIL-07_11_2023-GO95MLD-1^06244008.0320800 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2028-07-11 | 3
105210781-95342-DETAIL-07_13_2023-SVCDEFLC-1^06244008.0320801 | OTHER | CA-NON-TIER | Distribution | 2023-07-13 | 2026-07-13 | 2
690819066-79282-DETAIL-07_11_2023-GO95MLD-1^06244008.0321901 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2026-07-11 | 2
180278108-98692-DETAIL-07_05_2023-GO95HV-1^06244008.0323740 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
410347021-29752-DETAIL-06_15_2023-GO95MLD-1^06244009.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
799577194-68194-DETAIL-06_15_2023-GO95MLD-1^06244009.0291702 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
446575152-70952-DETAIL-06_21_2023-GO95MLD-1^06244009.0293700 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
446575152-70952-DETAIL-06_21_2023-SVCDEFLC-1^06244009.0293700 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2026-06-21 | 2
923769141-57329-DETAIL-06_08_2023-GRDRODHI-1^06244009.0296103 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
923769141-57329-DETAIL-06_08_2023-GRDRODHI-2^06244009.0296103 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
103372951-90942-DETAIL-06_08_2023-GO95MLD-1^06244009.0297300 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
63670551-29329-DETAIL-06_08_2023-GO95HV-1^06244009.0297301 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
297838564-82048-DETAIL-06_08_2023-GUYHINS-1^06244009.0297400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-08 | 2026-06-08 | 2
777664141-73652-DETAIL-06_21_2023-GO95MLD-1^06244009.0298301 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
472253533-55452-DETAIL-06_26_2023-SVCENTCO-1^06244009.0301600 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
30501703-41152-DETAIL-06_26_2023-GO95HV-1^06244009.0301700 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
85010703-91152-DETAIL-06_26_2023-GO95MLD-1^06244009.0302700 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
135550313-78499-DETAIL-06_26_2023-GO95MLD-1^06244009.0302800 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
335238003-62152-DETAIL-06_26_2023-GO95MLD-1^06244009.0302802 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
584732801-56213-DETAIL-07_06_2023-GO95MLD-1^06244008.0325700 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2026-07-06 | 2
624519626-65582-DETAIL-07_06_2023-GO95MLD-1^06244008.0329603 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2028-07-06 | 3
750351146-40672-DETAIL-07_07_2023-GO95HV-1^06244008.0329800 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2028-07-07 | 3
495877901-78599-DETAIL-07_06_2023-GO95MLD-1^06244008.0329901 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
42780084-86922-DETAIL-07_07_2023-SVCDEFLC-1^06244008.0330300 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
258099104-35962-DETAIL-07_07_2023-GO95HV-1^06244008.0330501 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2028-07-07 | 3
583003084-87732-DETAIL-07_07_2023-GO95MLD-1^06244008.0330800 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2028-07-07 | 3
999391625-37232-DETAIL-07_07_2023-GO95TCH-1^06244008.0331700 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
977974534-54222-DETAIL-07_11_2023-GO95MLD-1^06244008.0332800 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2026-07-11 | 2
388526124-74922-DETAIL-07_11_2023-GO95HV-1^06244008.0332801 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2028-07-11 | 3
213711464-88622-DETAIL-07_12_2023-GO95MLD-1^06244008.0332900 | OTHER | CA-NON-TIER | Distribution | 2023-07-12 | 2026-07-12 | 2
838216285-38788-DETAIL-07_11_2023-GO95MLD-1^06244008.0333901 | OTHER | CA-NON-TIER | Distribution | 2023-07-11 | 2026-07-11 | 2
640311655-37132-DETAIL-07_12_2023-GO95MLD-1^06244008.0334200 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
568229725-84132-DETAIL-07_07_2023-GO95MLD-1^06244008.0335401 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
937461265-87032-DETAIL-07_07_2023-GO95MLD-1^06244008.0336100 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
265659933-61452-DETAIL-06_26_2023-GO95MLD-1^06244009.0303100 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2028-06-26 | 3
265659933-61452-DETAIL-06_26_2023-GO95TCH-1^06244009.0303100 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2026-06-26 | 2
370734323-35652-DETAIL-06_26_2023-GO95MLD-1^06244009.0303802 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
186298823-48152-DETAIL-06_26_2023-GO95HV-1^06244009.0304905 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
186298823-48152-DETAIL-06_26_2023-GO95MLD-1^06244009.0304905 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
692277033-41252-DETAIL-06_21_2023-GO95MLD-1^06244009.0307902 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
670811913-22352-DETAIL-06_15_2023-GO95HV-1^06244009.0308800 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2028-06-15 | 3
18050723-88752-DETAIL-06_21_2023-GO95HV-1^06244009.0309400 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
590352165-21129-DETAIL-07_07_2023-GO95MLD-1^06244008.0337100 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
34280515-80129-DETAIL-07_07_2023-GO95MLD-1^06244008.0338200 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
34280515-80129-DETAIL-07_07_2023-GRDRODHI-1^06244008.0338200 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
472222994-30032-DETAIL-07_13_2023-GO95MLD-1^06244008.0344800 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
755772204-50332-DETAIL-07_13_2023-GO95HV-1^06244008.0344801 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
425448705-70832-DETAIL-07_13_2023-GO95MLD-1^06244008.0344900 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
213748305-28732-DETAIL-07_13_2023-GO95HV-1^06244008.0344901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
940909138-69138-DETAIL-06_28_2023-GO95MLD-1^06244009.0114501 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
510285538-56538-DETAIL-06_28_2023-GO95HV-1^06244009.0115200 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
923250521-75182-DETAIL-07_05_2023-GO95MLD-1^06244009.0124100 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
131740002-33392-DETAIL-07_05_2023-SVCDEFLC-1^06244009.0124301 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
649308171-33599-DETAIL-07_05_2023-GO95HV-1^06244009.0128400 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
543095109-30312-DETAIL-07_05_2023-GO95HV-1^06244009.0131201 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
167937019-512-DETAIL-07_05_2023-GO95MLD-1^06244009.0131401 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
28455423-51852-DETAIL-06_21_2023-GO95MLD-1^06244009.0309500 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
384385303-21352-DETAIL-06_15_2023-GO95MLD-1^06244009.0309801 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2028-06-15 | 3
812131603-54299-DETAIL-06_15_2023-GO95MLD-1^06244009.0309802 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2026-06-15 | 2
533487581-2052-DETAIL-06_26_2023-GO95MLD-1^06244009.0310701 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2026-06-26 | 2
30902771-18952-DETAIL-06_26_2023-GO95HV-1^06244009.0310900 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2028-06-26 | 3
347899611-50652-DETAIL-06_29_2023-GO95MLD-1^06244009.0325101 | OTHER | CA-NON-TIER | Distribution | 2023-06-29 | 2026-06-29 | 2
690163522-76599-DETAIL-06_08_2023-ABNDEQPM-1^06244009.0325700 | OTHER | CA-TIER-2 | Distribution | 2023-06-08 | 2028-06-08 | 3
683861591-82352-DETAIL-06_29_2023-GO95HV-1^06244009.0326301 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
845910564-25488-DETAIL-06_08_2023-GO95HV-1^06244009.0326600 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
6088862-32952-DETAIL-06_08_2023-GO95HV-1^06244009.0327801 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
752597161-43052-DETAIL-06_08_2023-GUYHINS-1^06244009.0328401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
572439170-21332-DETAIL-06_15_2023-GO95HV-1^06244009.0335103 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2028-06-15 | 3
670617930-8232-DETAIL-06_15_2023-GO95MLD-1^06244009.0335500 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
6691020-68922-DETAIL-06_08_2023-GO95HV-1^06244009.0335601 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
938176180-27332-DETAIL-06_15_2023-GO95MLD-1^06244009.0336100 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
658517410-57932-DETAIL-06_08_2023-GO95HV-1^06244009.0336601 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
889466642-11288-DETAIL-07_05_2023-GO95MLD-1^06244009.0132000 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
836158199-1712-DETAIL-07_05_2023-GO95MLD-1^06244009.0132700 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
871784029-7912-DETAIL-07_05_2023-GO95MLD-1^06244009.0133200 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
871784029-7912-DETAIL-07_05_2023-SVCDEFLC-1^06244009.0133200 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
394923213-56892-DETAIL-06_26_2023-SVCDEFLC-1^06244009.0195000 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
736127392-24492-DETAIL-06_26_2023-SVCDEFLC-1^06244009.0195001 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
615458773-4229-DETAIL-06_21_2023-RISEGRD-1^06244009.0198202 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
910148903-17492-DETAIL-06_21_2023-RISEGRD-1^06244009.0198300 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
779114409-49812-DETAIL-06_29_2023-GO95MLD-1^06244009.0240300 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
295620849-24012-DETAIL-06_29_2023-GO95MLD-1^06244009.0241100 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
474617379-66712-DETAIL-07_05_2023-GO95MLD-1^06244009.0241900 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
69050909-65229-DETAIL-06_29_2023-GO95HV-1^06244009.0243201 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
983097969-77489-AUDIT-08_29_2023-GO95MLD-1^06244009.0244100 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2028-08-29 | 3
847706689-77112-DETAIL-07_03_2023-GO95BLTC-1^06244009.0244303 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
280959509-44212-DETAIL-07_03_2023-GO95MLD-1^06244009.0244400 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
14885820-53322-DETAIL-06_08_2023-GO95MLD-1^06244009.0336602 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
762185258-12358-DETAIL-06_21_2023-GO95MLD-1^06244009.0337502 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2026-06-21 | 2
651281210-15199-DETAIL-06_21_2023-GO95MLD-1^06244009.0337701 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2026-06-21 | 2
930275890-98632-DETAIL-06_15_2023-GO95MLD-1^06244009.0339100 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
816477089-45612-DETAIL-06_12_2023-GO95MLD-1^06244009.0360003 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
481446123-87971-DETAIL-06_12_2023-GO95BLTC-1^06244009.0360004 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
481446123-87971-DETAIL-06_12_2023-GO95HV-1^06244009.0360004 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
481446123-87971-DETAIL-06_12_2023-GO95MLD-1^06244009.0360004 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
659484549-34222-DETAIL-06_12_2023-GO95TCH-1^06244009.0360100 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
91468349-73312-DETAIL-06_12_2023-GO95MLD-1^06244009.0360103 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
91468349-73312-DETAIL-06_12_2023-GO95TCH-1^06244009.0360103 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
236637590-30722-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361104 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
183514299-46699-DETAIL-06_12_2023-SVCROAD-1^06244009.0361105 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
514520942-75479-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361203 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
911504089-74122-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361207 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
556613289-19622-DETAIL-06_12_2023-GO95MLD-1^06244009.0361208 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
21081389-84112-DETAIL-06_20_2023-GO95MLD-1^06244009.0361401 | OTHER | CA-NON-TIER | Distribution | 2023-06-20 | 2026-06-20 | 2
294727479-79522-DETAIL-06_28_2023-GO95HV-1^06244009.0362000 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
492284659-25422-DETAIL-06_28_2023-GO95MLD-1^06244009.0362101 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
731019299-20499-DETAIL-06_12_2023-GO95MLD-1^06244009.0362200 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
54578589-47112-DETAIL-06_12_2023-XARMSPCR-1^06244009.0362201 | CROSSARM | CA-TIER-2 | Distribution | 2023-06-12 | 2024-06-12 | 2
407908459-22329-DETAIL-06_12_2023-GO95MLD-1^06244009.0362203 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
879852709-30912-DETAIL-06_12_2023-GO95MLD-1^06244009.0362301 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2028-06-12 | 3
879852709-30912-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0362301 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
514470020-26222-DETAIL-06_12_2023-GUYHINS-1^06244009.0362302 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
839071879-13112-DETAIL-06_12_2023-GO95MLD-1^06244009.0362306 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
386712940-33122-DETAIL-06_20_2023-SVCDEFLC-2^06244009.0362320 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
767481110-41329-DETAIL-06_28_2023-GO95MLD-1^06244009.0363000 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
574745800-37399-DETAIL-06_28_2023-GO95MLD-1^06244009.0363200 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
202559949-36229-DETAIL-07_03_2023-GO95MLD-1^06244009.0244600 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
901770549-61599-DETAIL-07_03_2023-GO95MLD-1^06244009.0245500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
421128688-32102-DETAIL-07_03_2023-GO95CL10-1^06244009.0252500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
773508648-43202-DETAIL-07_03_2023-GO95HV-1^06244009.0252701 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
860713768-7312-DETAIL-06_28_2023-GO95MLD-1^06244009.0253200 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
853537128-22212-DETAIL-07_03_2023-GO95MLD-1^06244009.0253402 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
19205278-29112-DETAIL-07_03_2023-GO95MLD-1^06244009.0253600 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
991741559-47512-DETAIL-06_28_2023-GO95MLD-1^06244009.0363301 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
991741559-47512-DETAIL-06_28_2023-GUYHINS-1^06244009.0363301 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
691436830-64669-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0363302 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
461395779-30022-DETAIL-06_12_2023-GO95MLD-1^06244009.0363501 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
461395779-30022-DETAIL-06_12_2023-GUYHINS-1^06244009.0363501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
261480528-26612-DETAIL-06_12_2023-GUYHINS-2^06244009.0363700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
426769629-70579-DETAIL-06_28_2023-SVCDEFLC-1^06244009.0364300 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
434104478-85799-DETAIL-06_12_2023-GO95MLD-1^06244009.0365501 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
434104478-85799-DETAIL-06_12_2023-GUYHINS-1^06244009.0365501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
191962149-32869-DETAIL-06_12_2023-GO95MLD-1^06244009.0365502 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
191962149-32869-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0365502 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
503786588-73212-DETAIL-06_12_2023-GO95HV-1^06244009.0365600 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
503786588-73212-DETAIL-06_12_2023-GO95MLD-1^06244009.0365600 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
468840921-94921-DETAIL-06_28_2023-GO95TCH-1^06244009.0365800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
810844148-7712-DETAIL-06_28_2023-GO95MLD-1^06244009.0254000 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
680386708-39602-DETAIL-06_29_2023-GO95HV-1^06244009.0254202 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
69672678-28512-DETAIL-06_29_2023-GO95HV-1^06244009.0254603 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
737052178-10212-DETAIL-06_29_2023-GO95HV-1^06244009.0254700 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
454831298-84718-DETAIL-06_29_2023-GO95MLD-1^06244009.0254800 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
1240588-62612-DETAIL-06_29_2023-GO95HV-1^06244009.0255701 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
711175058-25479-DETAIL-06_28_2023-GO95MLD-1^06244009.0256000 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
656695328-55012-DETAIL-06_29_2023-RISEBKSP-1^06244009.0257701 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
827177529-19369-DETAIL-07_03_2023-GO95HV-1^06244009.0269401 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
636812517-76369-DETAIL-06_21_2023-GO95MLD-1^06244009.0270000 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
432036220-84132-DETAIL-06_27_2023-ABNDEQPM-1^06244009.0272000 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
507241300-9122-DETAIL-06_27_2023-GO95MLD-1^06244009.0272102 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
244067051-12232-DETAIL-06_21_2023-GO95HV-1^06244009.0282200 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2028-06-21 | 3
244067051-12232-DETAIL-06_21_2023-GO95MLD-1^06244009.0282200 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
244067051-12232-DETAIL-06_21_2023-SVCENTBK-1^06244009.0282200 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
497712370-9232-DETAIL-06_21_2023-GO95HV-1^06244009.0282202 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2028-06-21 | 3
505861158-78229-DETAIL-06_28_2023-SVCDEFLC-1^06244009.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
505861158-78229-DETAIL-06_28_2023-SVCDEFLC-2^06244009.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
620990588-68229-AUDIT-07_13_2023-GO95MLD-1^06244009.0365901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
146344788-49229-DETAIL-06_28_2023-GO95HV-1^06244009.0368800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
870935323-62852-DETAIL-06_13_2023-GO95MLD-1^06244010.0220400 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
113639773-10452-DETAIL-06_13_2023-GO95MLD-1^06244010.0221100 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
603456293-14252-DETAIL-06_13_2023-GO95MLD-1^06244010.0221400 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
176110793-85252-DETAIL-06_13_2023-GO95MLD-1^06244010.0223501 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
361195853-4752-DETAIL-06_13_2023-GO95MLD-1^06244010.0225501 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
361195853-4752-DETAIL-06_13_2023-SVCDEFLC-1^06244010.0225501 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
720977643-10552-DETAIL-06_13_2023-GO95HV-1^06244010.0227301 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
226883223-35079-DETAIL-06_13_2023-GO95MLD-1^06244010.0228200 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
674139351-36742-AUDIT-08_01_2023-SVCROAD-1^06244010.0243002 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
623534871-8442-DETAIL-06_19_2023-GO95MLD-1^06244010.0243200 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
946496141-75799-DETAIL-06_19_2023-GO95HV-1^06244010.0244000 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
943092151-22429-DETAIL-06_19_2023-ABNDEQPM-1^06244010.0244400 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
811148862-23952-DETAIL-06_19_2023-GO95MLD-1^06244010.0250100 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
72982593-36252-DETAIL-06_20_2023-GO95MLD-1^06244010.0250103 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
67529802-2902-DETAIL-06_19_2023-GO95MLD-1^06244010.0250401 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
568575463-62352-DETAIL-06_19_2023-GO95MLD-1^06244010.0250500 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
301956163-90352-DETAIL-06_19_2023-GO95MLD-1^06244010.0250501 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
307309202-80052-DETAIL-06_19_2023-GUYNOINS-2^06244010.0250503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
284516112-852-DETAIL-06_19_2023-GO95HV-1^06244010.0251300 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
839102370-1332-DETAIL-06_21_2023-GO95HV-1^06244009.0283201 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2028-06-21 | 3
586296690-55822-DETAIL-06_27_2023-GO95MLD-1^06244009.0285002 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
586296690-55822-DETAIL-06_27_2023-SVCWIND-1^06244009.0285002 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
286774821-22132-DETAIL-06_27_2023-GO95HV-1^06244009.0286100 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2028-06-27 | 3
266252311-33832-DETAIL-06_27_2023-XARMSPCR-1^06244009.0288201 | CROSSARM | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
560824531-72852-DETAIL-06_15_2023-GO95MLD-1^06244009.0290700 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
466702917-85369-DETAIL-06_08_2023-GO95MLD-1^06244009.0292602 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
123921641-84852-DETAIL-06_08_2023-GO95HV-1^06244009.0292701 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
177842911-83452-DETAIL-06_08_2023-GO95MLD-1^06244009.0293600 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
485165701-56352-DETAIL-06_08_2023-GO95MLD-1^06244009.0294501 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
702031901-7252-DETAIL-06_08_2023-GO95HV-1^06244009.0294502 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
923769141-57329-DETAIL-06_08_2023-GO95MLD-1^06244009.0296103 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
923769141-57329-DETAIL-06_08_2023-GRDRODHI-3^06244009.0296103 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
901844191-77942-DETAIL-06_08_2023-GO95HV-1^06244009.0296400 | OTHER | CA-TIER-2 | Distribution | 2023-06-08 | 2028-06-08 | 3
297838564-82048-DETAIL-06_08_2023-GO95MLD-1^06244009.0297400 | OTHER | CA-TIER-2 | Distribution | 2023-06-08 | 2026-06-08 | 2
471103521-85299-DETAIL-06_08_2023-GO95HV-1^06244009.0299000 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
756190423-9329-DETAIL-06_26_2023-GO95HV-1^06244009.0300300 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
450821592-20152-DETAIL-06_26_2023-GO95HV-1^06244009.0300600 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
472253533-55452-DETAIL-06_26_2023-GO95MLD-1^06244009.0301600 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
335238003-62152-DETAIL-06_26_2023-GRDRODHI-1^06244009.0302802 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
370734323-35652-DETAIL-06_26_2023-GO95HV-1^06244009.0303802 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
923727713-7152-DETAIL-06_26_2023-GO95MLD-1^06244009.0303903 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
1230992-799-DETAIL-06_15_2023-GO95MLD-1^06244009.0307600 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
17157822-10652-DETAIL-06_19_2023-GO95MLD-1^06244010.0251301 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
480821863-1852-DETAIL-06_20_2023-GO95HV-1^06244010.0252301 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
175033612-73052-DETAIL-06_19_2023-GO95MLD-1^06244010.0252700 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
463861912-34052-DETAIL-06_19_2023-GO95HV-1^06244010.0252801 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
976415583-59052-DETAIL-06_20_2023-GO95MLD-1^06244010.0253501 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
976415583-59052-DETAIL-06_20_2023-RISEGRD-1^06244010.0253501 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
142076553-20352-AUDIT-08_22_2023-GO95MLD-1^06244010.0255302 | OTHER | CA-NON-TIER | Distribution | 2023-08-22 | 2026-08-22 | 2
926497555-19555-DETAIL-06_20_2023-SVCDEFLC-1^06244010.0256300 | OTHER | CA-NON-TIER | Distribution | 2023-06-20 | 2026-06-20 | 2
660641333-83952-DETAIL-06_20_2023-GO95MLD-1^06244010.0256500 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
22941813-75752-DETAIL-06_20_2023-GO95MLD-1^06244010.0256502 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
334713046-94046-DETAIL-06_20_2023-GO95MLD-1^06244010.0256600 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
73151122-92852-DETAIL-06_20_2023-SVCDEFLC-1^06244010.0258501 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
73151122-92852-DETAIL-06_20_2023-SVCDEFLC-2^06244010.0258501 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
225879843-58429-DETAIL-06_26_2023-GO95MLD-1^06244010.0259100 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2026-06-26 | 2
225879843-58429-DETAIL-06_26_2023-GRDRODHI-1^06244010.0259100 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2026-06-26 | 2
189786243-55329-DETAIL-06_15_2023-GO95HV-1^06244009.0307601 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2028-06-15 | 3
18050723-88752-DETAIL-06_21_2023-GO95TCH-1^06244009.0309400 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2026-06-21 | 2
28455423-51852-DETAIL-06_21_2023-ABNDEQPM-1^06244009.0309500 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
786626503-57452-DETAIL-06_21_2023-GO95MLD-1^06244009.0309501 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
282266573-58352-DETAIL-06_21_2023-GO95HV-1^06244009.0309601 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
282266573-58352-DETAIL-06_21_2023-RISEGRD-1^06244009.0309601 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2026-06-21 | 2
970359393-62252-DETAIL-06_15_2023-RISEGRD-1^06244009.0309701 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
384385303-21352-DETAIL-06_15_2023-RISEGRD-1^06244009.0309801 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2026-06-15 | 2
265220555-71555-DETAIL-06_20_2023-GO95MLD-1^06244010.0259600 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
537527992-24752-DETAIL-06_20_2023-GO95BLTC-1^06244010.0259700 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
262855931-12852-DETAIL-06_19_2023-GO95MLD-1^06244010.0263502 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
890408721-65399-DETAIL-06_19_2023-GO95MLD-1^06244010.0264501 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
308654791-80452-DETAIL-06_20_2023-GO95MLD-1^06244010.0269201 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
558447123-11553-DETAIL-06_07_2023-GO95MLD-1^06244010.0271700 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
536846863-73853-DETAIL-06_07_2023-GO95MLD-1^06244010.0271802 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
274589131-19099-DETAIL-06_26_2023-GO95MLD-1^06244009.0310601 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2028-06-26 | 3
380633311-50252-DETAIL-06_26_2023-GO95HV-1^06244009.0310602 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2028-06-26 | 3
687265191-53052-DETAIL-06_26_2023-GO95MLD-1^06244009.0310700 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2026-06-26 | 2
533487581-2052-DETAIL-06_26_2023-GO95BLTC-1^06244009.0310701 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2028-06-26 | 3
342776961-3061-DETAIL-06_26_2023-GO95HV-1^06244009.0325601 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
54422801-43552-DETAIL-06_29_2023-GO95MLD-1^06244009.0326300 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
897525301-66279-DETAIL-06_08_2023-GO95MLD-1^06244009.0327501 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
352334061-96852-DETAIL-06_08_2023-GO95HV-1^06244009.0327802 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
191263351-74852-DETAIL-06_08_2023-GO95MLD-1^06244009.0328900 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
878902940-65532-DETAIL-06_15_2023-GO95HV-1^06244009.0335301 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2028-06-15 | 3
28158110-14329-DETAIL-06_08_2023-GO95HV-1^06244009.0335700 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2028-06-08 | 3
907153980-49432-DETAIL-06_15_2023-GO95HV-1^06244009.0336102 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2028-06-15 | 3
722162310-42522-DETAIL-06_08_2023-GO95MLD-1^06244009.0336800 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
866194000-69122-DETAIL-06_08_2023-GO95MLD-1^06244009.0336900 | OTHER | CA-NON-TIER | Distribution | 2023-06-08 | 2026-06-08 | 2
299547710-20232-DETAIL-06_21_2023-GO95HV-1^06244009.0336901 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
446987080-60532-DETAIL-06_15_2023-GO95HV-1^06244009.0337100 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2028-06-15 | 3
446987080-60532-DETAIL-06_15_2023-GO95MLD-1^06244009.0337100 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
609186758-81858-DETAIL-06_21_2023-GO95HV-1^06244009.0337600 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
843594020-42232-DETAIL-06_21_2023-GO95HV-1^06244009.0337900 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
843594020-42232-DETAIL-06_21_2023-GO95MLD-1^06244009.0337900 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
883370920-30232-DETAIL-06_21_2023-GO95HV-1^06244009.0337901 | OTHER | CA-NON-TIER | Distribution | 2023-06-21 | 2028-06-21 | 3
38150590-77632-DETAIL-06_15_2023-GO95HV-1^06244009.0338101 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2028-06-15 | 3
19856788-86840-DETAIL-06_27_2023-GO95TCH-1^06244009.0346700 | OTHER | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
462452928-35612-DETAIL-07_15_2022-UNIGRDSG-1^06244009.0355300 | OTHER | CA-TIER-2 | Distribution | 2022-07-15 | 2025-07-15 | 2
462452928-35612-DETAIL-06_20_2023-GO95MLD-1^06244009.0355300 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
796593118-96512-DETAIL-06_20_2023-SVCENTCO-1^06244009.0356001 | OTHER | CA-NON-TIER | Distribution | 2023-06-20 | 2026-06-20 | 2
806223619-83912-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0360002 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
734387299-12712-DETAIL-06_12_2023-GO95MLD-1^06244009.0360102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
734387299-12712-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0360102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
609171629-24999-DETAIL-06_12_2023-GO95HV-1^06244009.0361102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
609171629-24999-DETAIL-06_12_2023-GO95MLD-1^06244009.0361102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
536846863-73853-DETAIL-06_07_2023-GUYLOINS-1^06244010.0271802 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
248520383-86653-DETAIL-06_13_2023-GO95HV-1^06244010.0272700 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
297951363-22653-DETAIL-06_07_2023-GO95HV-1^06244010.0272900 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
838878443-6289-DETAIL-06_07_2023-GO95MLD-1^06244010.0275401 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
388511333-58779-DETAIL-06_07_2023-GO95MLD-1^06244010.0275502 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
933636913-42753-DETAIL-06_07_2023-SVCROAD-1^06244010.0275600 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
913699143-33353-DETAIL-06_07_2023-GO95MLD-1^06244010.0275703 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
913699143-33353-DETAIL-06_07_2023-SVCDEFLC-1^06244010.0275703 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
913699143-33353-DETAIL-06_07_2023-SVCWIND-1^06244010.0275703 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
759143570-68668-DETAIL-06_07_2023-GO95HV-1^06244010.0276601 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
722007743-49979-DETAIL-06_07_2023-XARMSPCR-1^06244010.0276800 | CROSSARM | CA-TIER-2 | Distribution | 2023-06-07 | 2024-06-07 | 2
150072533-98429-DETAIL-06_07_2023-GO95MLD-1^06244010.0276801 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
309499043-60399-DETAIL-06_07_2023-GO95HV-1^06244010.0279600 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
99959729-31599-DETAIL-06_13_2023-GO95HV-1^06244010.0285800 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
505417489-89892-DETAIL-06_13_2023-GO95HV-1^06244010.0287900 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
723669786-26378-DETAIL-06_14_2023-GO95HV-1^06244010.0288500 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
857189169-78792-DETAIL-06_13_2023-GO95HV-1^06244010.0288901 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
57223439-89692-DETAIL-06_14_2023-GO95HV-1^06244010.0289500 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
406204735-39872-DETAIL-06_06_2023-GO95MLD-1^06244010.0342401 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
142798126-66372-DETAIL-06_06_2023-GO95HV-1^06244010.0342403 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
575782825-20872-DETAIL-06_06_2023-GO95HV-1^06244010.0342500 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
707775395-98899-DETAIL-05_30_2023-GO95MLD-1^06244010.0344300 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
327325305-90672-DETAIL-06_06_2023-GO95HV-1^06244010.0344501 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
74605926-56472-DETAIL-05_30_2023-GO95MLD-1^06244010.0344900 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
74605926-56472-DETAIL-05_30_2023-GUYHINS-1^06244010.0344900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
988122404-49962-DETAIL-05_30_2023-GO95HV-1^06244010.0344901 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
983077804-48962-DETAIL-05_30_2023-GO95HV-1^06244010.0344902 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
983077804-48962-DETAIL-05_30_2023-GO95MLD-1^06244010.0344902 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
134005385-55172-DETAIL-05_30_2023-GO95MLD-1^06244010.0345401 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
435441514-17072-DETAIL-06_06_2023-GO95MLD-1^06244010.0346302 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
609171629-24999-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
226215619-52329-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361205 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
616467809-71912-DETAIL-06_12_2023-GO95MLD-1^06244009.0361206 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
857751159-21612-DETAIL-06_20_2023-GO95MLD-1^06244009.0361402 | OTHER | CA-NON-TIER | Distribution | 2023-06-20 | 2028-06-20 | 3
407908459-22329-DETAIL-06_12_2023-GO95BLTC-1^06244009.0362203 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
450003639-57822-DETAIL-06_12_2023-GO95MLD-1^06244009.0362300 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
514470020-26222-AUDIT-08_22_2023-GO95MLD-1^06244009.0362302 | OTHER | CA-NON-TIER | Distribution | 2023-08-22 | 2026-08-22 | 2
645175499-57222-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0362303 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
11411119-76212-DETAIL-06_12_2023-GO95MLD-1^06244009.0362304 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
375390840-45669-DETAIL-06_20_2023-GO95HV-1^06244009.0362308 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
386712940-33122-DETAIL-06_20_2023-SVCDEFLC-1^06244009.0362320 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
849401149-20412-DETAIL-06_12_2023-GO95MLD-1^06244009.0362400 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
6963318-16512-DETAIL-06_20_2023-GO95MLD-1^06244009.0362500 | OTHER | CA-NON-TIER | Distribution | 2023-06-20 | 2026-06-20 | 2
129171379-28622-DETAIL-06_28_2023-GO95MLD-1^06244009.0363001 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
852487800-51329-DETAIL-06_28_2023-GO95MLD-1^06244009.0363100 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
857785630-84669-DETAIL-06_12_2023-GO95HV-1^06244009.0363400 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
455674083-50145-DETAIL-06_12_2023-GO95MLD-1^06244009.0363402 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
67997030-22869-DETAIL-06_12_2023-GO95MLD-1^06244009.0363403 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
461395779-30022-DETAIL-06_12_2023-GUYHINS-2^06244009.0363501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
260254518-11612-DETAIL-06_12_2023-GUYHINS-1^06244009.0363600 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
260254518-11612-DETAIL-06_12_2023-GUYHINS-2^06244009.0363600 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
283522134-60462-DETAIL-05_30_2023-GO95HV-1^06244010.0346800 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
876017114-12529-DETAIL-06_14_2023-GO95CL10-1^06244010.0347103 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
307669586-84189-DETAIL-06_06_2023-GO95MLD-1^06244010.0347200 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
851914744-33529-DETAIL-05_30_2023-GO95MLD-1^06244010.0347403 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
635993806-92109-DETAIL-06_06_2023-GO95MLD-1^06244010.0347601 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
652987636-24469-DETAIL-06_14_2023-SVCENTCO-1^06244010.0348100 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
826791055-88872-DETAIL-06_14_2023-GO95MLD-1^06244010.0348104 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
261480528-26612-DETAIL-06_12_2023-GUYHINS-1^06244009.0363700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
426769629-70579-DETAIL-06_28_2023-GO95HV-1^06244009.0364300 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
505861158-78229-DETAIL-06_28_2023-GO95MLD-1^06244009.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
505861158-78229-DETAIL-06_28_2023-GRDRODHI-1^06244009.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
62854868-58229-DETAIL-06_12_2023-GO95MLD-1^06244009.0365802 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
903121578-18229-DETAIL-06_28_2023-GO95HV-1^06244009.0367700 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
304102723-26352-DETAIL-06_13_2023-GO95HV-1^06244010.0228300 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
674139351-36742-AUDIT-08_01_2023-GO95HV-1^06244010.0243002 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
389623066-85282-DETAIL-06_14_2023-RISEBKSP-1^06244010.0349300 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
712683445-83529-DETAIL-06_06_2023-GO95MLD-1^06244010.0349600 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
533511811-49279-DETAIL-06_14_2023-GO95MLD-1^06244010.0352600 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
471233961-2052-DETAIL-06_14_2023-SVCDEFLC-1^06244010.0352700 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
574786571-74052-DETAIL-06_15_2023-XARMSPCR-1^06244010.0358900 | CROSSARM | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
258303674-71109-DETAIL-10_19_2022-GO95HV-1^06244011.0012701 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
548644174-91109-DETAIL-10_19_2022-GO95HV-1^06244011.0013700 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
836876254-72109-DETAIL-10_19_2022-GO95HV-1^06244011.0016702 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
946496141-75799-DETAIL-06_19_2023-GUYHINS-1^06244010.0244000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
946496141-75799-DETAIL-06_19_2023-SVCROAD-1^06244010.0244000 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
478546981-67742-DETAIL-06_19_2023-GO95MLD-1^06244010.0244300 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
1449191-97942-DETAIL-06_19_2023-GO95MLD-1^06244010.0244402 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
959920701-91252-DETAIL-06_19_2023-GO95MLD-1^06244010.0244600 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
397515533-34952-DETAIL-06_20_2023-GO95MLD-1^06244010.0250101 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
163081912-56979-DETAIL-06_19_2023-GO95HV-1^06244010.0250202 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
496074692-88952-DETAIL-06_19_2023-GO95MLD-1^06244010.0250502 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
496074692-88952-DETAIL-06_19_2023-GUYHINS-1^06244010.0250502 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
307309202-80052-DETAIL-06_19_2023-GUYNOINS-1^06244010.0250503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
655616822-1652-DETAIL-06_19_2023-GO95HV-1^06244010.0251200 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
998024302-37429-DETAIL-06_19_2023-GO95HV-1^06244010.0251601 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
189151512-33052-DETAIL-06_19_2023-GO95MLD-1^06244010.0251700 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
984063453-29252-DETAIL-06_20_2023-GO95HV-1^06244010.0253300 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
44840773-75852-DETAIL-06_20_2023-GO95MLD-1^06244010.0253500 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
131385504-68699-DETAIL-10_19_2022-GO95MLD-1^06244011.0024200 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2025-10-19 | 2
133102904-94109-DETAIL-10_19_2022-GO95HV-1^06244011.0029400 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
259226088-8088-DETAIL-10_19_2022-GO95HV-1^06244011.0029401 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
778021184-58779-DETAIL-02_28_2019-SVCROAD-1^06245001.0071400 | OTHER | CA-NON-TIER | Distribution | 2019-02-28 | 2024-01-28 | 2
805506159-46249-DETAIL-06_22_2023-GO95MLD-1^06245005.0071000 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
805506159-46249-DETAIL-06_22_2023-GO95MLD-2^06245005.0071000 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
422274004-12203-DETAIL-06_22_2023-GO95MLD-1^06245005.0075000 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
613415822-12852-DETAIL-06_19_2023-POLETOP-1^06244010.0253901 | POLE | CA-TIER-2 | Distribution | 2023-06-19 | 2024-06-19 | 2
429411032-85852-DETAIL-06_20_2023-GO95MLD-1^06244010.0255300 | OTHER | CA-NON-TIER | Distribution | 2023-06-20 | 2026-06-20 | 2
459933132-30999-DETAIL-06_20_2023-GO95HV-1^06244010.0255301 | OTHER | CA-NON-TIER | Distribution | 2023-06-20 | 2028-06-20 | 3
659900103-72652-DETAIL-06_20_2023-GO95MLD-1^06244010.0256402 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
829102832-43652-DETAIL-06_20_2023-GO95HV-1^06244010.0256403 | OTHER | CA-NON-TIER | Distribution | 2023-06-20 | 2028-06-20 | 3
660641333-83952-DETAIL-06_20_2023-SVCDEFLC-1^06244010.0256500 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
659737829-14249-DETAIL-06_22_2023-GO95MLD-1^06245005.0076000 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
602240059-92249-DETAIL-06_22_2023-GO95MLD-1^06245005.0078202 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
821328479-80249-DETAIL-06_22_2023-GO95MLD-1^06245005.0078204 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
503779259-23249-DETAIL-06_22_2023-SVCROAD-1^06245005.0078205 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
944318449-48183-DETAIL-06_22_2023-GO95MLD-1^06245005.0078206 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
35273869-30299-DETAIL-06_22_2023-GO95MLD-1^06245005.0079000 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
413785798-81249-DETAIL-06_22_2023-GO95HV-1^06245005.0079004 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
581532139-27383-DETAIL-06_22_2023-GO95MLD-1^06245005.0079140 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
777910249-79149-DETAIL-06_22_2023-GUYSLACK-1^06245005.0079200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
6685529-39149-DETAIL-06_22_2023-GO95MLD-1^06245005.0079500 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
3385649-16149-DETAIL-05_04_2023-GO95HV-1^06245005.0085201 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
371333379-16079-DETAIL-05_04_2023-GO95MLD-1^06245005.0088300 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
56795755-57549-DETAIL-05_18_2023-GO95HV-1^06245005.0159300 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
879873555-77549-DETAIL-05_18_2023-GO95MLD-1^06245005.0159400 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
101917668-27349-DETAIL-05_25_2023-GO95MLD-1^06245005.0170001 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
193251078-74889-DETAIL-05_25_2023-GO95MLD-1^06245005.0170401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2028-05-25 | 3
140264555-55555-DETAIL-06_20_2023-GO95MLD-1^06244010.0257500 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
518651793-86252-DETAIL-06_20_2023-SVCDEFLC-1^06244010.0258504 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
225879843-58429-DETAIL-06_26_2023-GRDRODHI-2^06244010.0259100 | OTHER | CA-NON-TIER | Distribution | 2023-06-26 | 2026-06-26 | 2
265220555-71555-DETAIL-06_20_2023-GO95HV-1^06244010.0259600 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
32290682-33752-DETAIL-06_20_2023-GO95MLD-1^06244010.0259601 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
537527992-24752-DETAIL-06_20_2023-GO95MLD-1^06244010.0259700 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
782561202-51252-DETAIL-06_19_2023-GO95MLD-1^06244010.0261400 | OTHER | CA-NON-TIER | Distribution | 2023-06-19 | 2026-06-19 | 2
193251078-74889-DETAIL-05_25_2023-SVCROAD-1^06245005.0170401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
659431598-94679-DETAIL-05_23_2023-GO95MLD-1^06245005.0170700 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
336913068-17569-DETAIL-05_23_2023-GO95HV-1^06245005.0170800 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
778257188-16989-DETAIL-05_23_2023-SVCROAD-1^06245005.0170901 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
79604328-17783-DETAIL-05_23_2023-GO95HV-1^06245005.0181940 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
131838258-22689-DETAIL-05_23_2023-GRDRODHI-1^06245005.0183801 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
386614598-46449-DETAIL-05_23_2023-SVCROAD-1^06245005.0185901 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
178429208-76449-DETAIL-05_23_2023-GUYNOINS-1^06245005.0186900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
286929331-87429-DETAIL-06_19_2023-GO95MLD-1^06244010.0263500 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
262855931-12852-DETAIL-06_19_2023-SVCDEFLC-1^06244010.0263502 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
890408721-65399-DETAIL-06_19_2023-GRDRODHI-1^06244010.0264501 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
6998521-28752-DETAIL-06_20_2023-GO95MLD-1^06244010.0265400 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
881744113-65262-DETAIL-06_15_2023-GO95HV-1^06244010.0269001 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2028-06-15 | 3
449693991-41452-DETAIL-06_20_2023-GO95HV-1^06244010.0269200 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
421866783-76853-DETAIL-06_07_2023-GO95MLD-1^06244010.0270801 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
326288723-89453-DETAIL-06_07_2023-GO95MLD-1^06244010.0271800 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
326288723-89453-DETAIL-06_07_2023-SVCDEFLC-1^06244010.0271800 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
364288373-4853-DETAIL-06_07_2023-GO95MLD-1^06244010.0271801 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
248520383-86653-DETAIL-06_13_2023-GO95MLD-1^06244010.0272700 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
194338143-96399-DETAIL-06_07_2023-GO95MLD-1^06244010.0272800 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
194338143-96399-DETAIL-06_07_2023-GRDRODHI-1^06244010.0272800 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
453536151-40529-DETAIL-06_07_2023-GO95HV-1^06244010.0273700 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
569198628-65449-DETAIL-05_23_2023-SVCDEFLC-1^06245005.0187901 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
438093688-57269-DETAIL-05_23_2023-GO95MLD-1^06245005.0189801 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
34134778-27269-DETAIL-05_23_2023-GO95HV-1^06245005.0189802 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
26648948-3449-DETAIL-05_23_2023-GO95MLD-1^06245005.0189902 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
322415238-59449-DETAIL-05_24_2023-GO95MLD-1^06245005.0192101 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
515585988-25269-DETAIL-05_24_2023-GO95MLD-1^06245005.0192102 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
537873898-15269-DETAIL-05_24_2023-GO95HV-1^06245005.0192300 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
915794908-2349-DETAIL-05_22_2023-SVCROAD-1^06245005.0197000 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
714864643-1529-DETAIL-06_07_2023-GO95TCH-1^06244010.0273800 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
54552693-53453-DETAIL-06_07_2023-GO95MLD-1^06244010.0273802 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
419210151-70529-DETAIL-06_07_2023-GO95HV-1^06244010.0273803 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
872820653-19199-DETAIL-06_07_2023-GO95MLD-1^06244010.0275500 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
933636913-42753-DETAIL-06_07_2023-GO95MLD-1^06244010.0275600 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
330672073-45653-DETAIL-06_07_2023-GO95HV-1^06244010.0275602 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
556104783-15979-DETAIL-06_07_2023-GO95MLD-1^06244010.0276602 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
309499043-60399-DETAIL-06_07_2023-GO95MLD-1^06244010.0279600 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
644677243-51529-DETAIL-06_13_2023-GO95MLD-1^06244010.0285801 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
226188259-25792-DETAIL-06_14_2023-GO95MLD-1^06244010.0288300 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
137899349-13792-DETAIL-06_14_2023-GO95HV-1^06244010.0288301 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
303116739-91792-DETAIL-06_14_2023-GO95HV-1^06244010.0288400 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
290712989-16892-DETAIL-06_13_2023-GO95HV-1^06244010.0288900 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
843734491-7242-DETAIL-06_13_2023-GO95MLD-1^06244010.0289800 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
205847095-17172-DETAIL-06_06_2023-GO95MLD-1^06244010.0340501 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
826374446-61672-DETAIL-06_06_2023-GO95MLD-1^06244010.0342300 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
425868538-69779-DETAIL-05_25_2023-CLMBTRE-1^06245005.0199401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
425868538-69779-DETAIL-05_25_2023-GO95HV-1^06245005.0199401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2028-05-25 | 3
425868538-69779-DETAIL-05_25_2023-GRDRODHI-2^06245005.0199401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
493472538-65349-DETAIL-05_25_2023-GO95MLD-1^06245005.0199402 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2028-05-25 | 3
493472538-65349-DETAIL-05_25_2023-SVCENTCO-1^06245005.0199402 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
715783638-34349-DETAIL-05_25_2023-GO95MLD-1^06245005.0200401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
237085058-68049-DETAIL-05_18_2023-GO95MLD-1^06245005.0218001 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
46920068-57049-DETAIL-05_18_2023-GO95MLD-1^06245005.0219002 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
287691338-62598-DETAIL-05_18_2023-GO95HV-1^06245005.0225001 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
429700998-94049-DETAIL-05_11_2023-GO95MLD-1^06245005.0226000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
751739898-2899-DETAIL-05_18_2023-GO95MLD-1^06245005.0226001 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
358397965-17599-DETAIL-05_24_2023-GO95MLD-1^06245005.0228000 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
358397965-17599-DETAIL-05_24_2023-GUYHINS-1^06245005.0228000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
128744008-80599-DETAIL-05_11_2023-SVCROAD-1^06245005.0228003 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
774411105-42549-DETAIL-05_18_2023-GO95HV-1^06245005.0229400 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
309002115-55549-DETAIL-05_18_2023-GO95HV-1^06245005.0229700 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
589380649-33749-DETAIL-05_11_2023-GO95HV-1^06245005.0230001 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
239654569-51749-DETAIL-05_11_2023-GO95HV-1^06245005.0233000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
679874089-69649-DETAIL-05_11_2023-GO95MLD-1^06245005.0234000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
247809424-96698-DETAIL-05_11_2023-GO95MLD-1^06245005.0234001 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
299190713-70649-DETAIL-05_11_2023-SVCENTCO-1^06245005.0235000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
299190713-70649-DETAIL-05_11_2023-SVCENTCO-2^06245005.0235000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
662120189-29649-DETAIL-05_11_2023-GO95HV-1^06245005.0235003 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
593709213-30649-DETAIL-05_11_2023-ABNDEQPM-1^06245005.0238000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
923428259-9999-DETAIL-05_11_2023-GO95MLD-1^06245005.0238001 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
923428259-9999-DETAIL-05_11_2023-GUYNOINS-1^06245005.0238001 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
195118319-16749-DETAIL-05_22_2023-GO95MLD-1^06245005.0261000 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
195118319-16749-DETAIL-05_22_2023-SVCROAD-1^06245005.0261000 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
145988860-36749-DETAIL-05_22_2023-SVCROAD-1^06245005.0263000 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
609468699-34289-DETAIL-05_22_2023-GO95HV-1^06245005.0264004 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
609468699-34289-DETAIL-05_22_2023-GO95MLD-1^06245005.0264004 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
466108639-74749-DETAIL-05_11_2023-GO95HV-1^06245005.0264201 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
328631036-32529-DETAIL-06_06_2023-RISEBKSP-1^06244010.0342302 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
724558445-82529-DETAIL-06_06_2023-ENCHRW-1^06244010.0345300 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
583898036-65282-DETAIL-06_06_2023-GO95MLD-1^06244010.0345400 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
963511904-81499-DETAIL-06_06_2023-GO95HV-1^06244010.0346000 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
109817374-60572-DETAIL-06_06_2023-GO95MLD-1^06244010.0346300 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
283522134-60462-DETAIL-05_30_2023-GO95MLD-1^06244010.0346800 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
307669586-84189-DETAIL-06_06_2023-GO95HV-1^06244010.0347200 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
849038385-49072-DETAIL-06_06_2023-GUYLOINS-1^06244010.0347400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
62097004-43529-DETAIL-05_30_2023-GO95HV-1^06244010.0347500 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
119454256-75772-DETAIL-06_06_2023-GO95MLD-1^06244010.0347600 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
389623066-85282-DETAIL-06_14_2023-GO95MLD-1^06244010.0349300 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
411334556-56082-DETAIL-06_14_2023-GO95MLD-1^06244010.0349302 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
180019824-75162-DETAIL-06_06_2023-GO95MLD-1^06244010.0349602 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
941648752-2352-DETAIL-06_14_2023-GO95MLD-1^06244010.0352101 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
69750852-22352-DETAIL-06_14_2023-GO95MLD-1^06244010.0352200 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
69750852-22352-DETAIL-06_14_2023-SVCDEFLC-1^06244010.0352200 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
4024403-5675-DETAIL-06_14_2023-GO95MLD-1^06244010.0352201 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
382667320-40420-DETAIL-06_14_2023-SVCDEFLC-1^06244010.0352220 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
854097459-13056-DETAIL-06_14_2023-GO95MLD-1^06244010.0354700 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
876854921-83252-DETAIL-06_15_2023-GO95MLD-1^06244010.0356701 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
876854921-83252-DETAIL-06_15_2023-GRDRODHI-1^06244010.0356701 | OTHER | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
574786571-74052-DETAIL-06_15_2023-INSULDMG-1^06244010.0358900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-06-15 | 2026-06-15 | 2
496855594-44109-DETAIL-10_19_2022-GO95MLD-1^06244011.0010500 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
648054494-31599-DETAIL-10_19_2022-GO95MLD-1^06244011.0010502 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2025-10-19 | 2
204084229-36649-DETAIL-05_22_2023-GO95MLD-1^06245005.0265001 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
521053460-7649-DETAIL-05_11_2023-GO95MLD-1^06245005.0265300 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
310131970-17953-DETAIL-05_22_2023-SVCDEFLC-1^06245005.0266040 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
59033839-28649-DETAIL-05_11_2023-GUYNOINS-1^06245005.0266900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
59033839-28649-DETAIL-05_11_2023-GUYNOINS-2^06245005.0266900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
39030379-55769-DETAIL-05_22_2023-GO95MLD-1^06245005.0272100 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
887587678-89789-DETAIL-05_22_2023-GO95MLD-1^06245005.0274102 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
12876338-82748-DETAIL-05_22_2023-GUYHINS-1^06245005.0276200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
673491258-57399-DETAIL-05_22_2023-GO95BLTC-1^06245005.0279900 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
806203788-51889-DETAIL-05_22_2023-GO95MLD-1^06245005.0280401 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
630433329-85753-DETAIL-05_18_2023-INSULDMG-1^06245005.0282940 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
864771134-31169-DETAIL-05_24_2023-GO95MLD-1^06245005.0290802 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
540208234-59173-DETAIL-05_24_2023-GO95MLD-1^06245005.0293841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
428291644-51199-DETAIL-05_24_2023-GO95HV-1^06245005.0294840 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
428291644-51199-DETAIL-05_24_2023-GO95MLD-1^06245005.0294840 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
214783864-23109-DETAIL-10_25_2022-GO95HV-1^06244011.0017900 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
348172454-92109-DETAIL-10_25_2022-GO95HV-1^06244011.0017901 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
248423494-77009-DETAIL-10_19_2022-ABNDEQPM-1^06244011.0023200 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
426591534-60599-DETAIL-10_19_2022-GO95MLD-1^06244011.0025200 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
450330288-66611-ADMIN-07_31_2023-POLEDMRS-1^06245002.0033901 | POLE | CA-NON-TIER | Distribution | 2023-07-31 | 2026-07-31 | 2
337370964-4669-ADMIN-07_19_2023-XARMBRAC-1^06245004.0327702 | CROSSARM | CA-NON-TIER | Distribution | 2023-07-19 | 2026-07-19 | 2
396804629-84249-DETAIL-06_22_2023-INSULDMG-1^06245005.0074002 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
479005139-52779-DETAIL-06_22_2023-GO95MLD-1^06245005.0075002 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
898220409-38589-DETAIL-06_22_2023-GO95MLD-1^06245005.0076001 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
345326929-93249-DETAIL-06_22_2023-GO95MLD-1^06245005.0077000 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
45360289-35889-DETAIL-06_22_2023-GO95MLD-1^06245005.0077201 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
839038679-56179-DETAIL-06_22_2023-GO95MLD-1^06245005.0077203 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
839038679-56179-DETAIL-06_22_2023-SVCROAD-1^06245005.0077203 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
62188799-10249-DETAIL-06_22_2023-GO95MLD-1^06245005.0078201 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
602240059-92249-DETAIL-06_22_2023-COPLLEAN-1^06245005.0078202 | POLE | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
503779259-23249-DETAIL-06_22_2023-GO95MLD-1^06245005.0078205 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
944318449-48183-DETAIL-06_22_2023-SVCROAD-1^06245005.0078206 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
738685229-76383-DETAIL-06_22_2023-GO95MLD-1^06245005.0079040 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
738685229-76383-DETAIL-06_22_2023-GRDRODHI-1^06245005.0079040 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
738685229-76383-DETAIL-06_22_2023-GRDRODHI-2^06245005.0079040 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
78148259-80683-DETAIL-06_22_2023-GO95MLD-1^06245005.0079042 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
721403039-41249-DETAIL-06_22_2023-GO95MLD-1^06245005.0079100 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
428291644-51199-DETAIL-05_24_2023-INSULDMG-1^06245005.0294840 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
428291644-51199-DETAIL-05_24_2023-SVCROAD-1^06245005.0294840 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
241966444-53273-DETAIL-05_24_2023-GO95HV-1^06245005.0294842 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
240089654-7273-DETAIL-05_24_2023-GO95HV-1^06245005.0295840 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
608943844-96273-DETAIL-05_24_2023-GO95MLD-1^06245005.0295841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
4691764-58149-DETAIL-05_24_2023-GO95HV-1^06245005.0295900 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
606541654-51373-DETAIL-05_24_2023-GO95HV-1^06245005.0296841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
513773194-1089-DETAIL-05_24_2023-GO95MLD-1^06245005.0296900 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
447259454-53373-DETAIL-05_24_2023-GO95HV-1^06245005.0297841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
930573094-92489-DETAIL-05_24_2023-CLRTOUCH-1^06245005.0298700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
289447329-7353-DETAIL-05_22_2023-GO95HV-1^06245005.0299240 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
297281818-23149-DETAIL-05_18_2023-GO95MLD-1^06245005.0299601 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
988226838-82149-DETAIL-05_18_2023-GO95MLD-1^06245005.0299700 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
371117164-47373-DETAIL-05_24_2023-GO95MLD-1^06245005.0299841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
744077464-84973-DETAIL-07_06_2023-GO95MLD-1^06245005.0300941 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
918221884-68973-DETAIL-07_06_2023-INSULDMG-1^06245005.0301940 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
438553149-77383-DETAIL-06_22_2023-GO95MLD-1^06245005.0079241 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
6734559-58583-DETAIL-06_22_2023-GO95MLD-1^06245005.0079540 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
722269959-58149-DETAIL-06_22_2023-GO95HV-1^06245005.0079601 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
781877669-26289-AUDIT-07_05_2023-GUYLOINS-1^06245005.0079700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-07-05 | 2026-07-05 | 2
948308609-34199-DETAIL-05_04_2023-GO95MLD-1^06245005.0080202 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
948308609-34199-DETAIL-05_04_2023-GRDRODHI-1^06245005.0080202 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
948308609-34199-DETAIL-05_04_2023-GRDRODHI-2^06245005.0080202 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
818718869-9149-DETAIL-05_25_2023-GO95MLD-1^06245005.0080700 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2028-05-25 | 3
818718869-9149-DETAIL-05_25_2023-SVCROAD-1^06245005.0080700 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
310899839-17149-DETAIL-05_04_2023-INSULDMG-1^06245005.0082201 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
371333379-16079-DETAIL-05_04_2023-GO95HV-1^06245005.0088300 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
365000745-86549-DETAIL-05_18_2023-GO95HV-1^06245005.0159201 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
673781968-78349-DETAIL-05_23_2023-GO95HV-1^06245005.0170201 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
155815418-60679-DETAIL-05_24_2023-GO95MLD-1^06245005.0181000 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
131838258-22689-DETAIL-05_23_2023-GO95MLD-1^06245005.0183801 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
763992468-17449-DETAIL-05_23_2023-GO95MLD-1^06245005.0185900 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
104594474-97973-DETAIL-07_06_2023-INSULDMG-1^06245005.0301941 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
460208914-40249-DETAIL-07_06_2023-GO95MLD-1^06245005.0307900 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
863707714-31173-DETAIL-07_06_2023-GO95MLD-1^06245005.0308940 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
147447004-21169-DETAIL-07_06_2023-GUYNOINS-2^06245005.0309900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
887796944-30249-DETAIL-07_06_2023-GO95MLD-1^06245005.0309901 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
511640854-95149-DETAIL-05_22_2023-GO95HV-1^06245005.0329203 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
221161954-98799-DETAIL-05_22_2023-GO95MLD-1^06245005.0329300 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
503255798-90449-DETAIL-05_22_2023-GO95HV-1^06245005.0339904 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
232534459-67813-DETAIL-05_04_2023-GO95MLD-1^06245006.0130940 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
424422808-16349-DETAIL-05_04_2023-GO95HV-1^06245006.0135800 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
226394964-72064-DETAIL-05_04_2023-GO95MLD-1^06245006.0136940 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
182659878-78349-DETAIL-05_04_2023-INSULDMG-1^06245006.0138900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
414207688-4969-DETAIL-05_11_2023-GO95HV-1^06245006.0139001 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
414207688-4969-AUDIT-07_13_2023-GO95BLTC-1^06245006.0139001 | OTHER | CA-NON-TIER | Distribution | 2023-07-13 | 2028-07-13 | 3
127849678-39349-DETAIL-05_04_2023-INSULDMG-1^06245006.0139900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
682831193-11343-DETAIL-05_04_2023-GO95MLD-1^06245006.0139940 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
466158954-38749-DETAIL-05_08_2023-GO95MLD-1^06245006.0213601 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2026-05-08 | 2
634143415-8473-DETAIL-05_08_2023-GO95MLD-1^06245006.0215040 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2026-05-08 | 2
584861015-37473-DETAIL-05_08_2023-GO95MLD-1^06245006.0215140 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2026-05-08 | 2
584861015-37473-AUDIT-07_25_2023-RISECLMB-1^06245006.0215140 | OTHER | CA-NON-TIER | Distribution | 2023-07-25 | 2026-07-25 | 2
751409105-53473-DETAIL-05_11_2023-GO95HV-1^06245006.0216040 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
179820174-84199-DETAIL-05_08_2023-GO95MLD-1^06245006.0217402 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2026-05-08 | 2
414148374-73799-DETAIL-05_08_2023-GO95MLD-1^06245006.0219200 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2026-05-08 | 2
945158294-11579-DETAIL-05_08_2023-GO95HV-1^06245006.0219303 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2028-05-08 | 3
763992468-17449-DETAIL-05_23_2023-SVCROAD-1^06245005.0185900 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
178429208-76449-DETAIL-05_23_2023-GUYNOINS-2^06245005.0186900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
274799128-6449-DETAIL-05_23_2023-SVCROAD-1^06245005.0187900 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
733517602-93569-DETAIL-05_25_2023-GO95MLD-1^06245005.0189401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
136619438-84449-DETAIL-05_23_2023-GO95MLD-1^06245005.0189500 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
597441738-43579-DETAIL-05_23_2023-GO95MLD-1^06245005.0189501 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
320810338-91099-DETAIL-05_23_2023-GO95MLD-1^06245005.0189503 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
804750258-14079-DETAIL-05_23_2023-GO95MLD-1^06245005.0189702 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
34134778-27269-DETAIL-05_23_2023-GO95MLD-1^06245005.0189802 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
167108962-12669-DETAIL-05_23_2023-GO95HV-1^06245005.0189804 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
878239588-92383-DETAIL-05_23_2023-GO95HV-1^06245005.0189900 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
878239588-92383-DETAIL-05_23_2023-GO95MLD-1^06245005.0189900 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
26648948-3449-DETAIL-05_23_2023-CLMBTRE-1^06245005.0189902 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
901783608-53449-DETAIL-05_23_2023-SVCENTCO-1^06245005.0189904 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
915794908-2349-DETAIL-05_22_2023-GO95MLD-1^06245005.0197000 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
425868538-69779-DETAIL-05_25_2023-GRDRODHI-1^06245005.0199401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
798921216-46149-DETAIL-04_05_2023-GUYHINS-1^06245006.0220000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
736091910-53910-DETAIL-04_05_2023-GO95TCH-1^06245006.0220004 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
854861145-44479-DETAIL-04_05_2023-GO95MLD-1^06245006.0220040 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
309441999-40289-DETAIL-04_04_2023-GO95MLD-1^06245006.0220100 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
309441999-40289-DETAIL-04_04_2023-SVCNEUT-1^06245006.0220100 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
520756611-15489-DETAIL-04_05_2023-GO95MLD-1^06245006.0220103 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
520756611-15489-DETAIL-04_05_2023-SVCDEFLC-1^06245006.0220103 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
520756611-15489-DETAIL-04_05_2023-SVCDEFLC-2^06245006.0220103 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
435687148-26089-DETAIL-05_25_2023-GO95MLD-1^06245005.0199800 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
872900628-41449-DETAIL-05_25_2023-ENCHRW-1^06245005.0200400 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
352231828-95199-DETAIL-05_25_2023-GO95MLD-1^06245005.0200403 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
630771748-76979-DETAIL-05_25_2023-GO95MLD-1^06245005.0200700 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
899676258-36349-DETAIL-05_25_2023-GO95HV-1^06245005.0200800 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2028-05-25 | 3
61671338-31149-DETAIL-05_18_2023-GO95MLD-1^06245005.0214001 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
403043048-20149-DETAIL-05_18_2023-GO95HV-1^06245005.0215001 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
403043048-20149-DETAIL-05_18_2023-GO95MLD-1^06245005.0215001 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
520756611-15489-DETAIL-04_05_2023-SVCROAD-1^06245006.0220103 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
520756611-15489-DETAIL-04_05_2023-XARMSPCR-1^06245006.0220103 | CROSSARM | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
528379220-73149-DETAIL-04_04_2023-GUYHINS-1^06245006.0220201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
927402660-34149-DETAIL-04_04_2023-GUYNOINS-1^06245006.0220203 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
373944299-54149-DETAIL-04_04_2023-GO95MLD-1^06245006.0220204 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
487349539-19613-DETAIL-04_04_2023-GO95MLD-1^06245006.0220242 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
386849051-65049-DETAIL-04_04_2023-SVCDEFLC-1^06245006.0221101 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
295896930-1999-DETAIL-04_04_2023-GO95CL10-1^06245006.0221102 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2028-04-04 | 3
878066820-86049-DETAIL-04_04_2023-SVCDEFLC-1^06245006.0221103 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
338508588-10613-DETAIL-04_04_2023-SVCROAD-1^06245006.0221141 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
884674538-37538-DETAIL-04_04_2023-GO95MLD-1^06245006.0221300 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
659080761-25049-DETAIL-04_04_2023-SVCROAD-1^06245006.0222002 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
978741810-28699-DETAIL-04_03_2023-GUYHINS-1^06245006.0222101 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
978741810-28699-DETAIL-04_03_2023-GUYHINS-2^06245006.0222101 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
678016910-42049-DETAIL-04_03_2023-GO95MLD-1^06245006.0222104 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
34150691-41599-DETAIL-04_03_2023-GO95MLD-1^06245006.0222105 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
953130258-29049-DETAIL-05_18_2023-GO95MLD-1^06245005.0217000 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
214238578-46049-DETAIL-05_18_2023-GO95HV-1^06245005.0222000 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
793804178-56889-DETAIL-05_18_2023-GO95MLD-1^06245005.0223000 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
302981778-30279-DETAIL-05_18_2023-GO95MLD-1^06245005.0223001 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
108076108-84049-DETAIL-05_11_2023-GO95MLD-1^06245005.0227000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
358397965-17599-DETAIL-05_24_2023-SVCNEUT-1^06245005.0228000 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
953398765-60549-DETAIL-05_24_2023-GUYNOINS-1^06245005.0228001 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
28263118-3049-DETAIL-05_11_2023-GUYNOINS-1^06245005.0228002 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
128744008-80599-DETAIL-05_11_2023-GO95MLD-1^06245005.0228003 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
55481955-30549-DETAIL-05_24_2023-GO95MLD-1^06245005.0229001 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
573702275-80549-DETAIL-05_11_2023-GO95HV-1^06245005.0229101 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
611272795-51549-DETAIL-05_11_2023-GO95HV-1^06245005.0229200 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
664228395-31549-DETAIL-05_11_2023-GO95HV-1^06245005.0229201 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
383699895-81549-DETAIL-05_18_2023-GO95HV-1^06245005.0229301 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
486145705-12549-DETAIL-05_18_2023-GO95HV-1^06245005.0229401 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
314615115-93549-DETAIL-05_18_2023-GO95HV-1^06245005.0229500 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
975903079-62613-DETAIL-04_03_2023-ABNDEQPM-1^06245006.0222140 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
555312789-85379-DETAIL-04_04_2023-GO95TCH-1^06245006.0222141 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
999047208-78013-DETAIL-04_03_2023-GO95HV-1^06245006.0222143 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
711980799-913-DETAIL-04_03_2023-SVCENTCO-1^06245006.0222144 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
17821501-28049-DETAIL-04_04_2023-SVCDEFLC-1^06245006.0222202 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
517046439-19613-DETAIL-04_04_2023-GO95MLD-1^06245006.0222240 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
452981969-18049-DETAIL-04_04_2023-GO95MLD-1^06245006.0222241 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
477934929-53749-DETAIL-05_11_2023-GO95HV-1^06245005.0230002 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
299190713-70649-DETAIL-05_11_2023-GO95MLD-1^06245005.0235000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
462671570-66953-DETAIL-05_22_2023-GO95HV-1^06245005.0262040 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
973422849-55749-DETAIL-05_11_2023-GO95HV-1^06245005.0264000 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
902902149-94109-AUDIT-06_22_2023-GO95HV-1^06245005.0264002 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
978117009-56749-DETAIL-05_22_2023-GUYNOINS-1^06245005.0264003 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
978117009-56749-DETAIL-05_22_2023-GUYNOINS-2^06245005.0264003 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
978117009-56749-DETAIL-05_22_2023-GUYNOINS-3^06245005.0264003 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
384108609-60613-DETAIL-04_04_2023-GUYHINS-1^06245006.0222243 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
273682099-16513-DETAIL-04_04_2023-GRDRODHI-1^06245006.0222244 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
626635981-31149-DETAIL-04_04_2023-GO95MLD-1^06245006.0222300 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
250638011-52293-DETAIL-04_03_2023-GO95MLD-1^06245006.0222302 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
139598001-70149-DETAIL-04_04_2023-GO95MLD-1^06245006.0222400 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2028-04-04 | 3
328059771-1149-DETAIL-04_04_2023-GO95HV-1^06245006.0222401 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2028-04-04 | 3
607035940-78593-DETAIL-04_03_2023-GO95MLD-1^06245006.0223001 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
282385369-91313-DETAIL-04_03_2023-GO95HV-1^06245006.0223042 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
363401959-50313-DETAIL-04_03_2023-GO95MLD-1^06245006.0223043 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
373792966-25966-DETAIL-04_03_2023-GO95MLD-1^06245006.0223045 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
790273793-6303-DETAIL-04_03_2023-GO95MLD-1^06245006.0223046 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
731504500-2379-DETAIL-04_03_2023-SVCDEFLC-1^06245006.0223100 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
235132830-22049-DETAIL-04_03_2023-SVCDEFLC-1^06245006.0223101 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
119731959-78513-DETAIL-04_03_2023-GO95HV-1^06245006.0223141 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
119731959-78513-DETAIL-04_03_2023-GUYHINS-1^06245006.0223141 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
318448550-46279-DETAIL-05_11_2023-GO95MLD-1^06245005.0264300 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
391800845-70845-DETAIL-05_11_2023-GO95MLD-1^06245005.0264500 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
655202409-95649-DETAIL-05_22_2023-GO95MLD-1^06245005.0265000 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
655202409-95649-DETAIL-05_22_2023-SVCWIND-1^06245005.0265000 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
68136649-75649-DETAIL-05_22_2023-SVCWIND-1^06245005.0266000 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
121896978-48499-DETAIL-05_22_2023-GO95MLD-1^06245005.0274202 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
121896978-48499-DETAIL-05_22_2023-INSULDMG-1^06245005.0274202 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
12876338-82748-DETAIL-05_22_2023-GO95MLD-1^06245005.0276200 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
123053179-28413-DETAIL-04_03_2023-GO95HV-1^06245006.0223142 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
965567459-45413-DETAIL-04_03_2023-GUYHINS-1^06245006.0223143 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
678474569-86413-DETAIL-04_03_2023-GUYHINS-1^06245006.0223144 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
466480420-33049-DETAIL-04_03_2023-GO95TCH-1^06245006.0223200 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
597863379-40513-DETAIL-04_03_2023-GO95MLD-1^06245006.0223242 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
553170638-94228-DETAIL-04_13_2023-GO95MLD-1^06245006.0223400 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
553170638-94228-DETAIL-04_13_2023-GRDRODHI-1^06245006.0223400 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
718785988-77949-DETAIL-04_13_2023-ENCHRW-1^06245006.0223800 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
185009460-55199-DETAIL-04_03_2023-GO95MLD-1^06245006.0224002 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
305662060-32379-DETAIL-04_03_2023-GO95MLD-1^06245006.0224101 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
670342880-71093-DETAIL-04_03_2023-GO95HV-1^06245006.0224102 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
670342880-71093-DETAIL-04_03_2023-GO95MLD-1^06245006.0224102 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
873281880-71049-DETAIL-04_03_2023-GO95MLD-1^06245006.0224103 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
78299861-50569-DETAIL-04_03_2023-GO95HV-1^06245006.0224200 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
992085140-65309-DETAIL-04_03_2023-GO95MLD-1^06245006.0224203 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
944759608-49-DETAIL-04_13_2023-GO95MLD-1^06245006.0225503 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
157497858-9279-DETAIL-05_11_2023-GO95MLD-1^06245005.0276900 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
673491258-57399-DETAIL-05_22_2023-GO95MLD-1^06245005.0279900 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
806203788-51889-DETAIL-05_22_2023-GRDRODHI-1^06245005.0280401 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
806203788-51889-DETAIL-05_22_2023-GRDRODHI-2^06245005.0280401 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
903379538-32149-DETAIL-05_18_2023-GO95HV-1^06245005.0283901 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2028-05-18 | 3
995537368-88599-DETAIL-05_18_2023-GO95MLD-1^06245005.0284900 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
912693934-41169-DETAIL-05_24_2023-GUYNOINS-1^06245005.0290801 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
338995824-25173-DETAIL-05_24_2023-GO95MLD-1^06245005.0290841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
522140424-89149-AUDIT-07_05_2023-GO95MLD-1^06245005.0290901 | OTHER | CA-NON-TIER | Distribution | 2023-07-05 | 2026-07-05 | 2
374329524-23173-DETAIL-05_24_2023-GO95MLD-1^06245005.0290940 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
930994614-29149-DETAIL-05_24_2023-GO95MLD-1^06245005.0291801 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
697988534-36173-DETAIL-05_24_2023-GO95HV-1^06245005.0292841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
697988534-36173-DETAIL-05_24_2023-GO95MLD-1^06245005.0292841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
711843105-57105-DETAIL-05_24_2023-GO95TCH-1^06245005.0294800 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
795124444-64273-DETAIL-05_24_2023-GO95TCH-1^06245005.0294841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
241966444-53273-DETAIL-05_24_2023-GO95MLD-1^06245005.0294842 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
241966444-53273-DETAIL-05_24_2023-GRDBROKE-1^06245005.0294842 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
513773194-1089-DETAIL-05_24_2023-GO95HV-1^06245005.0296900 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
748008254-73373-DETAIL-05_24_2023-GO95MLD-1^06245005.0297840 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
39133234-35773-DETAIL-05_24_2023-GRDRODHI-1^06245005.0298500 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
930573094-92489-DETAIL-05_24_2023-GO95TCH-1^06245005.0298700 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
282073864-6373-DETAIL-05_24_2023-GO95CL10-1^06245005.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
282073864-6373-DETAIL-05_24_2023-GO95MLD-1^06245005.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
402350164-14373-DETAIL-05_24_2023-GO95MLD-1^06245005.0298842 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
731858729-64153-DETAIL-05_22_2023-GO95HV-1^06245005.0299241 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
862372528-93679-DETAIL-05_22_2023-GO95MLD-1^06245005.0299300 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
75165509-2753-DETAIL-05_22_2023-GO95MLD-1^06245005.0299340 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
357404448-14149-DETAIL-05_18_2023-GO95MLD-1^06245005.0299502 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
775376664-16373-DETAIL-05_24_2023-GO95MLD-1^06245005.0299843 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
955662794-61073-DETAIL-07_06_2023-GO95MLD-1^06245005.0303940 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
779941694-81073-AUDIT-07_13_2023-GO95HV-1^06245005.0304941 | OTHER | CA-NON-TIER | Distribution | 2023-07-13 | 2028-07-13 | 3
793659794-73073-DETAIL-07_06_2023-GO95HV-1^06245005.0305942 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2028-07-06 | 3
862312818-15949-DETAIL-04_06_2023-GO95MLD-1^06245006.0225504 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
88703018-23783-DETAIL-04_13_2023-GO95MLD-1^06245006.0225540 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
890944418-9949-DETAIL-04_06_2023-GO95HV-1^06245006.0225602 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2028-04-06 | 3
890944418-9949-DETAIL-04_06_2023-GO95MLD-1^06245006.0225602 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
127756308-59949-DETAIL-04_06_2023-GO95MLD-1^06245006.0225603 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
970381158-38999-DETAIL-04_13_2023-GO95MLD-1^06245006.0225900 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
895712648-46949-DETAIL-04_13_2023-GO95MLD-1^06245006.0225901 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
206564949-85089-DETAIL-04_05_2023-GO95MLD-1^06245006.0226003 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
89006345-27345-DETAIL-04_05_2023-GO95MLD-1^06245006.0226007 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
410915829-90343-DETAIL-04_05_2023-GO95MLD-1^06245006.0226100 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
999092901-90653-DETAIL-04_05_2023-GUYHINS-1^06245006.0226140 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
661358761-32053-DETAIL-04_05_2023-GO95MLD-1^06245006.0226141 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
284223011-73653-DETAIL-04_05_2023-SVCROAD-1^06245006.0226143 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
811146621-75653-DETAIL-04_05_2023-GO95MLD-1^06245006.0226240 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
811146621-75653-DETAIL-04_05_2023-SVCENTCO-1^06245006.0226240 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
833929479-13979-DETAIL-04_13_2023-CLRTOPOL-1^06245006.0227000 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
833929479-13979-DETAIL-04_13_2023-GO95HV-1^06245006.0227000 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2028-04-13 | 3
592236159-78149-DETAIL-05_16_2023-GO95HV-1^06245006.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
929161001-59149-DETAIL-04_05_2023-SVCENTCO-1^06245006.0227240 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
94376963-83679-DETAIL-04_05_2023-GO95MLD-1^06245006.0227301 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2028-04-05 | 3
183576209-71249-DETAIL-04_05_2023-GUYNOINS-2^06245006.0227305 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
135997880-86179-DETAIL-04_13_2023-GO95CL10-1^06245006.0227401 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2028-04-13 | 3
665954129-5943-DETAIL-04_06_2023-GO95MLD-1^06245006.0227403 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
194473391-61499-DETAIL-04_13_2023-GO95TCH-1^06245006.0228001 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
7267814-28073-DETAIL-07_06_2023-GO95MLD-1^06245005.0307940 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
147447004-21169-DETAIL-07_06_2023-GUYNOINS-1^06245005.0309900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
330475934-55149-DETAIL-05_22_2023-GO95MLD-1^06245005.0329200 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
61044444-75149-DETAIL-05_22_2023-GO95MLD-1^06245005.0329201 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2026-05-22 | 2
98011564-26149-DETAIL-05_22_2023-GO95HV-1^06245005.0329400 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
124944464-56149-DETAIL-05_22_2023-GO95MLD-1^06245005.0329401 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
186910079-1653-DETAIL-05_22_2023-GO95HV-1^06245005.0337941 | OTHER | CA-NON-TIER | Distribution | 2023-05-22 | 2028-05-22 | 3
788919728-55349-DETAIL-05_04_2023-GO95HV-1^06245006.0135701 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
404591850-58149-DETAIL-04_13_2023-GO95MLD-1^06245006.0228003 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
253039689-40789-DETAIL-04_13_2023-GO95MLD-1^06245006.0228004 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
761952779-97149-DETAIL-04_13_2023-GO95MLD-1^06245006.0228005 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
631935791-77149-DETAIL-04_13_2023-GO95MLD-1^06245006.0228006 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
38837879-18889-DETAIL-04_13_2023-GO95MLD-1^06245006.0228404 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
10778088-32983-DETAIL-04_13_2023-GO95MLD-1^06245006.0228541 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
41263240-31579-DETAIL-04_13_2023-GO95MLD-1^06245006.0229000 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
964322041-57599-DETAIL-04_13_2023-GO95HV-1^06245006.0229002 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2028-04-13 | 3
949841108-10299-DETAIL-05_04_2023-GO95MLD-1^06245006.0135900 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
905280079-53013-DETAIL-05_04_2023-GO95HV-1^06245006.0135940 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
171116778-12379-DETAIL-05_04_2023-GO95MLD-1^06245006.0136500 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
393419778-81899-DETAIL-05_04_2023-GO95MLD-1^06245006.0136600 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
182659878-78349-DETAIL-05_04_2023-INSULDMG-2^06245006.0138900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-04 | 2026-05-04 | 2
127591324-78749-DETAIL-05_08_2023-CLMBTRE-1^06245006.0215000 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2026-05-08 | 2
584861015-37473-DETAIL-05_08_2023-GO95HV-1^06245006.0215140 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2028-05-08 | 3
455577724-9889-DETAIL-05_08_2023-GO95MLD-1^06245006.0215401 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2026-05-08 | 2
751409105-53473-DETAIL-05_11_2023-GO95MLD-1^06245006.0216040 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2026-05-11 | 2
678011425-78473-DETAIL-05_11_2023-GO95HV-1^06245006.0216041 | OTHER | CA-NON-TIER | Distribution | 2023-05-11 | 2028-05-11 | 3
945158294-11579-DETAIL-05_08_2023-GO95MLD-1^06245006.0219303 | OTHER | CA-NON-TIER | Distribution | 2023-05-08 | 2028-05-08 | 3
543940201-95149-DETAIL-04_05_2023-GO95MLD-1^06245006.0220002 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2028-04-05 | 3
543940201-95149-DETAIL-04_05_2023-SVCENTCO-1^06245006.0220002 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
736091910-53910-DETAIL-04_05_2023-GO95MLD-1^06245006.0220004 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
978747846-61946-DETAIL-04_05_2023-SVCROAD-1^06245006.0220005 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
520756611-15489-DETAIL-04_05_2023-SVCENTCO-1^06245006.0220103 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
858340541-14149-DETAIL-04_05_2023-GO95TCH-1^06245006.0220200 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
528379220-73149-DETAIL-04_04_2023-GO95MLD-1^06245006.0220201 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
528379220-73149-DETAIL-04_04_2023-GUYHINS-2^06245006.0220201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
542286709-23149-DETAIL-04_04_2023-GO95MLD-1^06245006.0220240 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
616353839-10713-DETAIL-04_04_2023-GO95MLD-1^06245006.0220241 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
585892559-62713-DETAIL-04_04_2023-GUYHINS-1^06245006.0220340 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
478411730-28779-DETAIL-04_04_2023-GO95MLD-1^06245006.0221002 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
295896930-1999-DETAIL-04_04_2023-GUYHINS-1^06245006.0221102 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
478043771-85899-DETAIL-04_13_2023-GO95MLD-1^06245006.0229004 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2028-04-13 | 3
964620121-86489-DETAIL-04_05_2023-ABNDEQPM-1^06245006.0229201 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2028-04-05 | 3
386025971-11249-DETAIL-04_13_2023-GO95MLD-1^06245006.0229300 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
491466248-4949-DETAIL-04_13_2023-GO95MLD-1^06245006.0229600 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2028-04-13 | 3
457408313-2343-DETAIL-06_22_2023-GO95HV-1^06245006.0230740 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
457408313-2343-DETAIL-06_22_2023-INSULDMG-1^06245006.0230740 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
23212028-42179-DETAIL-06_22_2023-GO95MLD-1^06245006.0230800 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2028-06-22 | 3
984387023-41399-DETAIL-07_03_2023-GO95MLD-1^06245006.0230801 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2028-07-03 | 3
400777438-72289-DETAIL-07_07_2023-GO95MLD-1^06245006.0230901 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
854863928-26449-DETAIL-06_22_2023-GO95MLD-1^06245006.0231800 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
742472339-52913-DETAIL-07_06_2023-GO95MLD-1^06245006.0231940 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
759369038-43349-DETAIL-07_03_2023-GO95HV-1^06245006.0232000 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2028-07-03 | 3
630004259-79349-DETAIL-05_16_2023-GO95MLD-1^06245006.0240900 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
276445278-61689-DETAIL-04_18_2023-GO95MLD-1^06245006.0242000 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
284418818-89569-DETAIL-04_06_2023-GO95MLD-1^06245006.0244400 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2028-04-06 | 3
535710388-25099-DETAIL-04_18_2023-GO95MLD-1^06245006.0246001 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2028-04-18 | 3
788097358-53249-DETAIL-04_06_2023-GO95MLD-1^06245006.0249000 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2028-04-06 | 3
284829268-64249-DETAIL-04_06_2023-GO95HV-1^06245006.0249100 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2028-04-06 | 3
74689009-69299-DETAIL-04_06_2023-GO95MLD-1^06245006.0249700 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
949519900-77923-DETAIL-04_18_2023-GO95MLD-1^06245006.0250941 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
877372099-74923-DETAIL-04_18_2023-GO95MLD-1^06245006.0250942 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
152988819-25413-DETAIL-04_18_2023-GO95MLD-1^06245006.0251900 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2028-04-18 | 3
522318789-94549-DETAIL-04_18_2023-GO95MLD-1^06245006.0251901 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
541016140-93623-DETAIL-04_18_2023-GO95MLD-1^06245006.0256940 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
878066820-86049-DETAIL-04_04_2023-GO95MLD-1^06245006.0221103 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
878066820-86049-DETAIL-04_04_2023-SVCDEFLC-2^06245006.0221103 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
338508588-10613-DETAIL-04_04_2023-GO95MLD-1^06245006.0221141 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
338508588-10613-DETAIL-04_04_2023-SVCENTCO-1^06245006.0221141 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
207042341-9289-DETAIL-04_04_2023-GO95MLD-1^06245006.0221204 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
313357521-2149-DETAIL-04_04_2023-GO95MLD-1^06245006.0221301 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
471660281-29079-DETAIL-04_04_2023-GO95MLD-1^06245006.0221303 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2028-04-04 | 3
686784991-93993-DETAIL-04_03_2023-SVCROAD-1^06245006.0222000 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
595894330-62523-DETAIL-04_18_2023-GO95HV-1^06245006.0256941 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2028-04-18 | 3
350607350-9723-DETAIL-04_18_2023-GO95MLD-1^06245006.0258940 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
596767001-3023-DETAIL-04_13_2023-GO95MLD-1^06245006.0260841 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
867626850-87189-DETAIL-04_18_2023-GO95MLD-1^06245006.0260900 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
400255331-80123-DETAIL-04_20_2023-GO95MLD-1^06245006.0261842 | OTHER | CA-NON-TIER | Distribution | 2023-04-20 | 2026-04-20 | 2
400255331-80123-DETAIL-04_20_2023-GO95MLD-2^06245006.0261842 | OTHER | CA-NON-TIER | Distribution | 2023-04-20 | 2026-04-20 | 2
116950010-89549-DETAIL-04_18_2023-GO95MLD-1^06245006.0261902 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
119341410-8499-DETAIL-04_18_2023-GO95MLD-1^06245006.0264802 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
335407120-19549-DETAIL-04_18_2023-GO95MLD-1^06245006.0264900 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
335407120-19549-DETAIL-04_18_2023-SVCDEFLC-1^06245006.0264900 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
359094070-36999-DETAIL-04_03_2023-GO95MLD-1^06245006.0265200 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
27604520-6549-DETAIL-04_03_2023-GO95MLD-1^06245006.0265201 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
627649510-75999-DETAIL-04_03_2023-GO95MLD-1^06245006.0265300 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
627649510-75999-DETAIL-04_03_2023-GO95TCH-1^06245006.0265300 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
832940680-56549-DETAIL-04_03_2023-GO95HV-1^06245006.0265401 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2028-04-03 | 3
832940680-56549-DETAIL-04_03_2023-GO95MLD-1^06245006.0265401 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
587617360-58549-DETAIL-05_16_2023-GO95MLD-1^06245006.0265701 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
47803001-92649-DETAIL-04_18_2023-GRDRODHI-1^06245006.0265901 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
439040700-9549-DETAIL-04_18_2023-GO95MLD-1^06245006.0265902 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
29723800-17089-DETAIL-04_03_2023-GO95MLD-1^06245006.0266302 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
29723800-17089-DETAIL-04_03_2023-XARMSPCR-1^06245006.0266302 | CROSSARM | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
427900041-59823-DETAIL-04_18_2023-GO95MLD-1^06245006.0266941 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
432045151-13033-DETAIL-04_18_2023-GO95MLD-1^06245006.0268942 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
209303691-51233-DETAIL-04_18_2023-GO95MLD-1^06245006.0269940 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
659080761-25049-DETAIL-04_04_2023-SVCDEFLC-1^06245006.0222002 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
659080761-25049-DETAIL-04_04_2023-SVCDEFLC-2^06245006.0222002 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
79644090-97889-DETAIL-04_04_2023-GO95MLD-1^06245006.0222004 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
978741810-28699-DETAIL-04_03_2023-GO95MLD-1^06245006.0222101 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
34150691-41599-DETAIL-04_03_2023-SVCDEFLC-1^06245006.0222105 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
555312789-85379-DETAIL-04_04_2023-GO95MLD-1^06245006.0222141 | OTHER | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
711980799-913-DETAIL-04_03_2023-GO95MLD-1^06245006.0222144 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
139598001-70149-DETAIL-04_04_2023-GUYLOINS-1^06245006.0222400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-04 | 2026-04-04 | 2
835940449-79913-DETAIL-04_03_2023-GO95MLD-1^06245006.0223041 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
790273793-6303-AUDIT-05_04_2023-GO95HV-1^06245006.0223046 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
461433980-93323-DETAIL-04_05_2023-GO95MLD-1^06245006.0223047 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
705252699-17613-DETAIL-04_03_2023-GO95MLD-1^06245006.0223140 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
119731959-78513-DETAIL-04_03_2023-GO95TCH-1^06245006.0223141 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
119731959-78513-DETAIL-04_03_2023-GUYHINS-2^06245006.0223141 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
678474569-86413-AUDIT-06_12_2023-SVCENTCO-1^06245006.0223144 | OTHER | CA-NON-TIER | Distribution | 2023-06-12 | 2026-06-12 | 2
266408589-63513-DETAIL-04_03_2023-GO95MLD-1^06245006.0223241 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
266408589-63513-DETAIL-04_03_2023-SVCDEFLC-1^06245006.0223241 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
597863379-40513-DETAIL-04_03_2023-SVCDEFLC-1^06245006.0223242 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
337862978-24999-DETAIL-04_13_2023-GO95TCH-1^06245006.0223801 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
506450511-39293-DETAIL-04_05_2023-GO95MLD-1^06245006.0224000 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
296070141-56693-DETAIL-04_03_2023-SVCWIND-1^06245006.0224100 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
673855570-71799-DETAIL-04_03_2023-GO95MLD-1^06245006.0224104 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
654401089-57353-DETAIL-05_10_2023-GO95MLD-1^06245006.0270400 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
611709689-82789-DETAIL-05_10_2023-GO95MLD-1^06245006.0270401 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
139070744-49399-DETAIL-05_09_2023-GO95TCH-1^06245006.0270801 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
218555315-1553-DETAIL-05_09_2023-GO95MLD-1^06245006.0270841 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
524893638-88628-DETAIL-05_09_2023-SVCDEFLC-1^06245006.0270902 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
527252030-57799-DETAIL-05_09_2023-GO95MLD-1^06245006.0270904 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
431968274-26973-DETAIL-05_09_2023-GO95HV-1^06245006.0270905 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
431968274-26973-DETAIL-05_09_2023-GUYHINS-1^06245006.0270905 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
961764865-50853-DETAIL-05_09_2023-GO95MLD-1^06245006.0270942 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
435948950-92853-DETAIL-05_10_2023-INSULDMG-1^06245006.0271400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
589756700-64469-DETAIL-05_10_2023-GO95HV-1^06245006.0271401 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
610196341-67468-DETAIL-05_10_2023-GO95MLD-1^06245006.0271402 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
408325314-60343-DETAIL-05_09_2023-RISEGRD-1^06245006.0271700 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
168400264-30949-DETAIL-05_09_2023-GO95MLD-1^06245006.0271803 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
378259444-80269-DETAIL-05_09_2023-GO95MLD-1^06245006.0271902 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
65602276-44276-DETAIL-05_09_2023-GUYHINS-1^06245006.0271940 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
757270250-31799-DETAIL-04_06_2023-GO95MLD-1^06245006.0224300 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
757270250-31799-DETAIL-04_06_2023-SVCENTCO-1^06245006.0224300 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
992184221-69049-DETAIL-04_13_2023-GO95MLD-1^06245006.0224400 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
615690711-2979-DETAIL-04_13_2023-GO95TCH-1^06245006.0224401 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
727212698-32789-DETAIL-04_13_2023-GO95HV-1^06245006.0224900 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2028-04-13 | 3
837186865-98865-DETAIL-04_05_2023-GO95MLD-1^06245006.0225001 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
776371669-33189-DETAIL-04_05_2023-CLMBTRE-1^06245006.0225002 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
675578281-58553-DETAIL-04_05_2023-GO95HV-1^06245006.0225040 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2028-04-05 | 3
675578281-58553-DETAIL-04_05_2023-GO95TCH-1^06245006.0225040 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
675578281-58553-DETAIL-04_05_2023-SVCWIND-1^06245006.0225040 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
240640030-82249-DETAIL-04_06_2023-GO95HV-1^06245006.0225401 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2028-04-06 | 3
814379928-27499-DETAIL-04_06_2023-GO95HV-1^06245006.0225905 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2028-04-06 | 3
814379928-27499-DETAIL-04_06_2023-GO95MLD-1^06245006.0225905 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
593500979-98149-DETAIL-04_05_2023-SVCRUBLG-1^06245006.0226000 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
593500979-98149-DETAIL-04_05_2023-SVCWIND-1^06245006.0226000 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
702524851-93899-DETAIL-04_05_2023-CLMBTRE-1^06245006.0226001 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
65602276-44276-DETAIL-05_09_2023-SVCENTCO-1^06245006.0271940 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
245147235-92653-DETAIL-05_09_2023-GO95MLD-1^06245006.0271944 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
271494934-32489-DETAIL-05_10_2023-GO95MLD-1^06245006.0272702 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
759233633-86849-DETAIL-05_10_2023-GUYHINS-1^06245006.0272802 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
182925505-6453-DETAIL-05_09_2023-SVCDEFLC-1^06245006.0272842 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
108923594-57153-DETAIL-05_09_2023-GO95MLD-1^06245006.0272843 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
108923594-57153-DETAIL-05_09_2023-GO95TCH-1^06245006.0272843 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
378969624-31343-DETAIL-05_09_2023-SVCDEFLC-1^06245006.0272901 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
397238080-55049-DETAIL-05_09_2023-GO95MLD-1^06245006.0272903 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
3344464-58879-DETAIL-05_25_2023-GO95MLD-1^06245006.0273401 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
646674764-83849-DETAIL-05_25_2023-GO95MLD-1^06245006.0273500 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
161194464-14849-DETAIL-05_10_2023-GO95MLD-1^06245006.0273600 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
257592384-34849-DETAIL-05_10_2023-GO95MLD-1^06245006.0273602 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
515623263-2699-DETAIL-05_10_2023-GO95MLD-1^06245006.0273703 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
673799693-98849-DETAIL-05_10_2023-XARMSPCR-1^06245006.0273800 | CROSSARM | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
69043753-69833-DETAIL-05_10_2023-GO95HV-1^06245006.0273802 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
69043753-69833-DETAIL-05_10_2023-SVCENTCO-1^06245006.0273802 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
486407503-18849-DETAIL-05_09_2023-GO95MLD-1^06245006.0273803 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
797475714-97849-DETAIL-05_10_2023-GO95HV-1^06245006.0273804 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
485281893-13543-DETAIL-05_09_2023-GO95MLD-1^06245006.0273805 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
340730739-8913-DETAIL-05_09_2023-GO95BLTC-1^06245006.0273943 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
340730739-8913-DETAIL-05_09_2023-GO95MLD-1^06245006.0273943 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
722366584-27253-DETAIL-05_10_2023-GO95HV-1^06245006.0273944 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
107221334-10799-DETAIL-05_10_2023-CLRTOUCH-1^06245006.0274600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
5136791-20653-DETAIL-04_05_2023-GO95TCH-1^06245006.0226040 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
661358761-32053-DETAIL-04_05_2023-SVCDEFLC-1^06245006.0226141 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
288282601-32653-DETAIL-04_05_2023-GO95MLD-1^06245006.0226142 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
438181621-5653-DETAIL-04_05_2023-GO95MLD-1^06245006.0226144 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
58930148-74949-DETAIL-04_06_2023-GO95MLD-1^06245006.0226500 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
833929479-13979-DETAIL-04_13_2023-GO95MLD-1^06245006.0227000 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
592236159-78149-DETAIL-05_16_2023-GO95MLD-1^06245006.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
801409051-39149-DETAIL-04_05_2023-GO95MLD-1^06245006.0227241 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
167399871-59889-DETAIL-04_05_2023-GO95MLD-1^06245006.0227302 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
214182219-7099-DETAIL-04_05_2023-GO95MLD-1^06245006.0227304 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
183576209-71249-DETAIL-04_05_2023-GUYNOINS-1^06245006.0227305 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
475997081-52789-DETAIL-04_13_2023-GO95MLD-1^06245006.0227306 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
135997880-86179-DETAIL-04_13_2023-GO95MLD-1^06245006.0227401 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
337341710-12249-DETAIL-04_13_2023-GO95HV-1^06245006.0227402 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2028-04-13 | 3
783232209-54073-DETAIL-04_13_2023-GO95MLD-1^06245006.0228002 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
253039689-40789-DETAIL-04_13_2023-SVCROAD-1^06245006.0228004 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
107221334-10799-DETAIL-05_10_2023-GO95MLD-1^06245006.0274600 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
639920174-29849-DETAIL-05_15_2023-SVCDEFLC-1^06245006.0274700 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
885747025-59553-DETAIL-05_15_2023-SVCENTCO-1^06245006.0274743 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
700019344-54753-DETAIL-05_15_2023-GO95MLD-1^06245006.0274745 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
700019344-54753-DETAIL-05_15_2023-GUYSLACK-1^06245006.0274745 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
334533964-3953-DETAIL-05_15_2023-GO95MLD-1^06245006.0274840 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
522506364-47953-DETAIL-05_15_2023-GO95HV-1^06245006.0274843 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
558988644-69653-DETAIL-05_10_2023-GO95MLD-1^06245006.0274845 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
253039689-40789-DETAIL-04_13_2023-SVCROAD-2^06245006.0228004 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
886752719-81579-DETAIL-04_05_2023-GO95MLD-1^06245006.0228302 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
2593431-67689-DETAIL-04_05_2023-SVCDEFLC-1^06245006.0228303 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
68052340-31249-DETAIL-04_13_2023-GO95MLD-1^06245006.0228401 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
331457998-78683-DETAIL-04_13_2023-XARMSPCR-1^06245006.0228640 | CROSSARM | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
626847999-13489-DETAIL-04_13_2023-GO95MLD-1^06245006.0229001 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
964322041-57599-DETAIL-04_13_2023-GO95MLD-1^06245006.0229002 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
359740233-2233-DETAIL-04_05_2023-GO95HV-1^06245006.0229100 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2028-04-05 | 3
561851904-8389-DETAIL-05_10_2023-GO95MLD-1^06245006.0274902 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
850336404-98653-DETAIL-05_10_2023-GUYHINS-1^06245006.0274941 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
850336404-98653-DETAIL-05_10_2023-SVCDEFLC-1^06245006.0274941 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
111461425-3653-DETAIL-05_10_2023-GO95TCH-1^06245006.0274942 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
713435710-51653-DETAIL-05_23_2023-GO95MLD-1^06245006.0275441 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
202317364-2388-DETAIL-05_23_2023-GO95MLD-1^06245006.0275502 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
380586847-70947-DETAIL-05_15_2023-GO95MLD-1^06245006.0275702 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
828445793-47789-DETAIL-05_15_2023-GO95MLD-1^06245006.0275803 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
389892125-65125-DETAIL-05_10_2023-GO95HV-1^06245006.0275810 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
38721204-25073-DETAIL-05_15_2023-GO95HV-1^06245006.0275841 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
329052724-15279-DETAIL-05_15_2023-GO95MLD-1^06245006.0275842 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
344007173-81849-DETAIL-05_15_2023-GO95MLD-1^06245006.0275901 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
534212663-32849-DETAIL-05_15_2023-GO95MLD-1^06245006.0275903 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
162366189-74569-DETAIL-05_15_2023-GO95TCH-1^06245006.0275906 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
162366189-74569-DETAIL-05_15_2023-SVCDEFLC-1^06245006.0275906 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
255352474-41873-DETAIL-05_15_2023-GO95MLD-1^06245006.0275941 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
831289383-53903-DETAIL-05_10_2023-GO95MLD-1^06245006.0275942 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
196563909-15649-DETAIL-05_17_2023-GO95BLTC-1^06245006.0276101 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
467822744-80749-DETAIL-05_17_2023-GO95MLD-1^06245006.0276400 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
467822744-80749-DETAIL-05_17_2023-RISEGRD-1^06245006.0276400 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
844977463-90749-DETAIL-05_17_2023-GO95MLD-1^06245006.0276403 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
961867714-39379-DETAIL-05_17_2023-GO95MLD-1^06245006.0276440 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
88910884-41073-DETAIL-05_17_2023-GO95MLD-1^06245006.0276441 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
88910884-41073-DETAIL-05_17_2023-XARMSPCR-1^06245006.0276441 | CROSSARM | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
522543503-22373-DETAIL-05_15_2023-GO95MLD-1^06245006.0276700 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
764320484-58749-DETAIL-05_15_2023-GO95MLD-1^06245006.0276800 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
262698893-8749-DETAIL-05_15_2023-GO95MLD-1^06245006.0276801 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
281752673-88749-DETAIL-05_15_2023-GO95MLD-1^06245006.0276900 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
281752673-88749-DETAIL-05_15_2023-SVCDEFLC-1^06245006.0276900 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
641634503-30849-DETAIL-05_15_2023-GO95MLD-1^06245006.0276902 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
453948534-56773-DETAIL-05_15_2023-GO95MLD-1^06245006.0276940 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
359740233-2233-DETAIL-04_05_2023-GO95MLD-1^06245006.0229100 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
61821583-32583-DETAIL-04_05_2023-SVCDEFLC-1^06245006.0229203 | OTHER | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
719732908-21783-DETAIL-04_13_2023-GO95MLD-1^06245006.0229640 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
614141708-10783-DETAIL-04_13_2023-GO95MLD-1^06245006.0229641 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
903939218-32783-DETAIL-04_13_2023-GO95MLD-1^06245006.0229740 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
655524118-31089-DETAIL-07_03_2023-GO95BLTC-1^06245006.0230100 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2028-07-03 | 3
655524118-31089-DETAIL-07_03_2023-GO95TCH-1^06245006.0230100 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2026-07-03 | 2
133428108-10589-DETAIL-07_03_2023-GO95BLTC-1^06245006.0230200 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2028-07-03 | 3
133428108-10589-DETAIL-07_03_2023-GO95MLD-1^06245006.0230200 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2026-07-03 | 2
133428108-10589-DETAIL-07_03_2023-GO95MLD-2^06245006.0230200 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2026-07-03 | 2
342225499-76449-DETAIL-07_03_2023-GO95MLD-1^06245006.0230900 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2026-07-03 | 2
419773248-82079-DETAIL-07_03_2023-GO95MLD-1^06245006.0231101 | OTHER | CA-NON-TIER | Distribution | 2023-07-03 | 2026-07-03 | 2
531294528-85449-DETAIL-06_22_2023-GUYSLACK-1^06245006.0231700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
771069329-27813-DETAIL-06_22_2023-GO95MLD-1^06245006.0231840 | OTHER | CA-NON-TIER | Distribution | 2023-06-22 | 2026-06-22 | 2
70319659-42789-DETAIL-07_06_2023-GO95MLD-1^06245006.0231902 | OTHER | CA-NON-TIER | Distribution | 2023-07-06 | 2026-07-06 | 2
702536518-60379-DETAIL-07_07_2023-GO95TCH-1^06245006.0232902 | OTHER | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
453948534-56773-DETAIL-05_15_2023-GO95TCH-1^06245006.0276940 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
811058681-58319-DETAIL-05_16_2023-GO95MLD-1^06245006.0277200 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
264479098-93898-DETAIL-05_16_2023-GO95MLD-1^06245006.0277300 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
818447449-75649-DETAIL-05_16_2023-GO95HV-1^06245006.0277401 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
503156684-19973-DETAIL-05_16_2023-GO95MLD-1^06245006.0277440 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
503156684-19973-DETAIL-05_16_2023-XARMBRAC-1^06245006.0277440 | CROSSARM | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
308713443-61749-DETAIL-05_16_2023-CLMBTRE-1^06245006.0277600 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
308713443-61749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277600 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
5244383-22749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277700 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
860605723-66749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277805 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
5189643-17749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277900 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
90119013-65089-DETAIL-05_15_2023-GO95MLD-1^06245006.0277901 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
432269133-6963-DETAIL-05_15_2023-ABNDEQPM-1^06245006.0277903 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
194305073-2289-DETAIL-05_16_2023-GO95MLD-1^06245006.0278601 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
864044783-2749-DETAIL-05_16_2023-SVCDEFLC-1^06245006.0278700 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
732499508-42349-DETAIL-04_18_2023-GO95TCH-1^06245006.0240000 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
276445278-61689-DETAIL-04_18_2023-GO95HV-1^06245006.0242000 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2028-04-18 | 3
643726038-349-DETAIL-04_06_2023-GO95HV-1^06245006.0245101 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2028-04-06 | 3
747680558-70349-DETAIL-04_18_2023-GO95MLD-1^06245006.0246000 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
581114819-70913-DETAIL-04_18_2023-GO95MLD-1^06245006.0247040 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
527860698-81349-DETAIL-04_06_2023-INSULDMG-1^06245006.0248000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
318989529-44549-DETAIL-04_18_2023-GO95MLD-1^06245006.0252900 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
386221319-24549-DETAIL-04_18_2023-GO95MLD-1^06245006.0253900 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
610552439-10179-DETAIL-04_18_2023-GO95MLD-1^06245006.0254900 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
249059010-28323-DETAIL-04_18_2023-XARMSPCR-1^06245006.0254940 | CROSSARM | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
343100330-77423-DETAIL-04_06_2023-GO95MLD-1^06245006.0255940 | OTHER | CA-NON-TIER | Distribution | 2023-04-06 | 2026-04-06 | 2
141682120-84423-DETAIL-04_18_2023-GO95MLD-1^06245006.0255942 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
942133444-93549-DETAIL-04_18_2023-GO95MLD-1^06245006.0259900 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
459253750-32823-DETAIL-04_18_2023-GO95MLD-1^06245006.0259942 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
459253750-32823-DETAIL-04_18_2023-GO95MLD-2^06245006.0259942 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
122896590-16379-DETAIL-04_13_2023-GO95MLD-1^06245006.0260800 | OTHER | CA-NON-TIER | Distribution | 2023-04-13 | 2026-04-13 | 2
518063064-13973-DETAIL-05_16_2023-RISEGRD-1^06245006.0278843 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
309563393-71479-DETAIL-05_16_2023-GO95HV-1^06245006.0278905 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
309563393-71479-DETAIL-05_16_2023-GO95MLD-1^06245006.0278905 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
683177143-90479-DETAIL-05_16_2023-GO95MLD-1^06245006.0278906 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
822087074-35973-DETAIL-05_16_2023-SVCDEFLC-1^06245006.0279841 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
721184490-6049-DETAIL-05_17_2023-GO95HV-1^06245006.0345700 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
188247440-41589-DETAIL-05_17_2023-GO95MLD-1^06245006.0346401 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
336756060-85049-DETAIL-05_17_2023-GO95HV-1^06245006.0346700 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
104203221-96023-DETAIL-04_20_2023-GO95MLD-1^06245006.0260840 | OTHER | CA-NON-TIER | Distribution | 2023-04-20 | 2026-04-20 | 2
969247591-11789-DETAIL-04_20_2023-GO95CL10-1^06245006.0261841 | OTHER | CA-NON-TIER | Distribution | 2023-04-20 | 2028-04-20 | 3
969247591-11789-DETAIL-04_20_2023-RISEGRD-1^06245006.0261841 | OTHER | CA-NON-TIER | Distribution | 2023-04-20 | 2026-04-20 | 2
364365219-56813-DETAIL-04_18_2023-GO95MLD-1^06245006.0262840 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
364365219-56813-DETAIL-04_18_2023-XARMSPCR-1^06245006.0262840 | CROSSARM | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
373556700-49549-DETAIL-04_18_2023-SVCWIND-1^06245006.0263801 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
93753411-15733-DETAIL-04_18_2023-GO95MLD-1^06245006.0263840 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
551772530-40649-DETAIL-04_18_2023-GO95HV-1^06245006.0264801 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2028-04-18 | 3
785301770-64049-DETAIL-05_17_2023-GO95HV-1^06245006.0347801 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
602696309-80549-DETAIL-05_17_2023-GO95HV-1^06245006.0350300 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
151544303-77303-DETAIL-05_24_2023-GO95HV-1^06245006.0352200 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2028-05-24 | 3
654896879-7789-DETAIL-05_17_2023-GO95MLD-1^06245006.0352500 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
283586019-39889-DETAIL-05_09_2023-GO95MLD-1^06245006.0362400 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
565788719-1389-ADMIN-06_30_2022-POLEREPL-1^06245007.0218700 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
201796096-62523-ADMIN-04_05_2023-XARMSPCR-1^06245007.0223548 | CROSSARM | CA-NON-TIER | Distribution | 2023-04-05 | 2026-04-05 | 2
194828569-21479-DETAIL-01_24_2014-POLEDERP-1^06245007.0275140 | POLE | CA-NON-TIER | Distribution | 2014-01-24 | 2018-12-24 | 2
122577521-62833-DETAIL-04_18_2023-GO95HV-1^06245006.0264840 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2028-04-18 | 3
122577521-62833-DETAIL-04_18_2023-INSULDMG-1^06245006.0264840 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
187778811-58733-DETAIL-04_18_2023-INSULDMG-1^06245006.0264841 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
832940680-56549-DETAIL-04_03_2023-INSULDMG-1^06245006.0265401 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
841187512-39512-DETAIL-04_18_2023-GO95MLD-1^06245006.0265904 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
426545130-27549-DETAIL-04_03_2023-GO95MLD-1^06245006.0267400 | OTHER | CA-NON-TIER | Distribution | 2023-04-03 | 2026-04-03 | 2
177543851-38923-DETAIL-04_18_2023-GO95HV-1^06245006.0267940 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2028-04-18 | 3
987878851-83923-DETAIL-04_18_2023-GO95MLD-1^06245006.0267941 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
359236149-87699-DETAIL-10_06_2022-GO95HV-1^06245010.0082800 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
184653341-58209-DETAIL-10_25_2022-GO95HV-1^06245010.0159100 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
249813111-82209-DETAIL-10_06_2022-GO95MLD-1^06245010.0160301 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
646924811-3209-DETAIL-10_06_2022-GO95HV-1^06245010.0160302 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
767206821-12209-DETAIL-10_06_2022-GO95HV-1^06245010.0160700 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
11043091-81999-DETAIL-10_06_2022-GO95HV-1^06245010.0162101 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
861121671-3209-DETAIL-10_06_2022-GUYHINS-1^06245010.0165000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
502035099-60209-DETAIL-10_06_2022-GO95MLD-1^06245010.0179300 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
451600999-11699-DETAIL-10_06_2022-GO95HV-1^06245010.0179800 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
379090431-75209-DETAIL-10_06_2022-GO95HV-1^06245010.0210301 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
427719551-94099-DETAIL-10_06_2022-SVCENTBK-1^06245010.0211400 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
337336991-76209-DETAIL-10_06_2022-GO95HV-1^06245010.0212600 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
30300681-77549-DETAIL-04_18_2023-GO95MLD-1^06245006.0268940 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2026-04-18 | 2
432045151-13033-DETAIL-04_18_2023-GO95HV-1^06245006.0268942 | OTHER | CA-NON-TIER | Distribution | 2023-04-18 | 2028-04-18 | 3
593406123-12949-DETAIL-05_09_2023-GO95MLD-1^06245006.0270800 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
593406123-12949-DETAIL-05_09_2023-SVCROAD-1^06245006.0270800 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
218555315-1553-DETAIL-05_09_2023-GO95HV-1^06245006.0270841 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
664887975-90953-DETAIL-05_09_2023-GO95MLD-1^06245006.0270941 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
535732768-22513-DETAIL-05_09_2023-GO95MLD-1^06245006.0270943 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
651687380-37779-DETAIL-05_10_2023-ABNDEQPM-1^06245006.0271201 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
435948950-92853-DETAIL-05_10_2023-ABNDEQPM-1^06245006.0271400 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
574157055-96199-DETAIL-05_10_2023-CLRTOUCH-1^06245006.0271642 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
574157055-96199-DETAIL-05_10_2023-GO95MLD-1^06245006.0271642 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
574157055-96199-DETAIL-05_10_2023-SVCROAD-1^06245006.0271642 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
408325314-60343-DETAIL-05_09_2023-RISEBKSP-1^06245006.0271700 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
311980014-62343-DETAIL-05_09_2023-SVCDEFLC-1^06245006.0271701 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
311980014-62343-DETAIL-05_09_2023-SVCROAD-1^06245006.0271701 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
168400264-30949-DETAIL-05_09_2023-GO95HV-1^06245006.0271803 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
361193191-7209-DETAIL-10_06_2022-GO95MLD-1^06245010.0212601 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
783840671-99209-DETAIL-10_06_2022-GO95MLD-1^06245010.0213800 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
783840671-99209-DETAIL-10_06_2022-GO95STUB-1^06245010.0213800 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
456414951-20309-DETAIL-10_06_2022-GO95MLD-1^06245010.0213900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
456414951-20309-DETAIL-10_06_2022-SVCWIND-1^06245010.0213900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
494984341-15299-DETAIL-10_06_2022-GO95HV-1^06245010.0218900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
494984341-15299-DETAIL-10_06_2022-GO95MLD-1^06245010.0218900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
494984341-15299-DETAIL-10_06_2022-GO95TCH-1^06245010.0218900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
506020961-18399-DETAIL-10_06_2022-GO95MLD-1^06245010.0220900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
998391571-78579-DETAIL-10_06_2022-GO95HV-1^06245010.0220902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
998391571-78579-DETAIL-10_06_2022-GO95MLD-1^06245010.0220902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
998391571-78579-DETAIL-10_06_2022-GRDRODHI-2^06245010.0220902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
366706684-31599-DETAIL-05_09_2023-GO95MLD-1^06245006.0271804 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
543472024-98553-DETAIL-05_09_2023-GO95MLD-1^06245006.0271942 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
600863144-16779-DETAIL-05_10_2023-GO95MLD-1^06245006.0272701 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
777432754-1179-DETAIL-05_10_2023-GO95MLD-1^06245006.0272801 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
777432754-1179-DETAIL-05_10_2023-SVCROAD-1^06245006.0272801 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
759233633-86849-DETAIL-05_10_2023-GO95HV-1^06245006.0272802 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2028-05-10 | 3
182925505-6453-DETAIL-05_09_2023-GO95MLD-1^06245006.0272842 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
182925505-6453-DETAIL-05_09_2023-SVCWIND-1^06245006.0272842 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
182925505-6453-DETAIL-05_09_2023-SVCWIND-2^06245006.0272842 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
912079384-50153-DETAIL-05_09_2023-GO95MLD-1^06245006.0272940 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
903898778-86113-DETAIL-05_09_2023-GO95MLD-1^06245006.0272942 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
615791395-70053-DETAIL-05_09_2023-GO95MLD-1^06245006.0272943 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
240960779-91779-DETAIL-05_25_2023-SVCDEFLC-1^06245006.0273300 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
579896264-97889-DETAIL-05_10_2023-GO95MLD-1^06245006.0273603 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
650036371-43469-DETAIL-05_10_2023-GO95MLD-1^06245006.0273707 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
673799693-98849-DETAIL-05_10_2023-SVCDEFLC-1^06245006.0273800 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
789047883-91889-DETAIL-10_25_2022-ABNDEQPM-1^06245010.0293001 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
789047883-91889-DETAIL-10_25_2022-GO95HV-1^06245010.0293001 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
484614721-39999-DETAIL-10_25_2022-GO95MLD-1^06245010.0294100 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2025-10-25 | 2
632652533-38309-DETAIL-10_25_2022-GO95HV-1^06245010.0294201 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
378724961-21409-DETAIL-10_19_2022-GO95HV-1^06245010.0297801 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
460095593-1309-DETAIL-10_25_2022-GO95HV-1^06245010.0313100 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
168945383-21309-DETAIL-10_25_2022-GO95HV-1^06245010.0314200 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
596509383-41309-DETAIL-10_25_2022-GO95HV-1^06245010.0314201 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
650961043-20289-DETAIL-10_25_2022-ABNDEQPM-1^06245010.0317301 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
846161423-73309-DETAIL-10_25_2022-GO95HV-1^06245010.0319500 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
165125733-26309-DETAIL-10_25_2022-GUYNOINS-2^06245010.0322801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-25 | 2025-10-25 | 2
704592073-25489-DETAIL-10_25_2022-GO95MLD-1^06245010.0323600 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2025-10-25 | 2
377993204-57579-DETAIL-08_12_2020-GO95TCH-1^06246001.0130900 | OTHER | CA-NON-TIER | Distribution | 2020-08-12 | 2023-08-12 | 2
673799693-98849-DETAIL-05_10_2023-SVCRUBLG-1^06245006.0273800 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
417520934-84653-DETAIL-05_09_2023-GO95MLD-1^06245006.0273841 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
626654934-75343-DETAIL-05_10_2023-GO95MLD-1^06245006.0273902 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
287474521-30049-DETAIL-05_10_2023-RISEGRD-1^06245006.0273903 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
840588105-453-DETAIL-05_09_2023-GO95MLD-1^06245006.0273940 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
814527454-27753-DETAIL-05_09_2023-GO95MLD-1^06245006.0273942 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
814527454-27753-DETAIL-05_09_2023-GUYHINS-1^06245006.0273942 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
814527454-27753-DETAIL-05_09_2023-SVCDEFLC-1^06245006.0273942 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
381882136-68730-ADMIN-07_14_2020-ENCHRW-1^06246001.0176403 | OTHER | CA-NON-TIER | Distribution | 2020-07-14 | 2023-07-14 | 2
596166660-80001-ADMIN-08_13_2020-GUYSLACK-1^06246001.0301900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2020-08-13 | 2023-08-13 | 2
280437536-90420-ADMIN-01_20_2022-POLETOP-1^06246002.0134201 | POLE | CA-NON-TIER | Distribution | 2022-01-20 | 2025-01-20 | 2
985595113-75459-DETAIL-07_15_2022-POLEREPL-1^06246004.0170002 | POLE | CA-NON-TIER | Distribution | 2022-07-15 | 2025-07-15 | 2
93992050-96559-DETAIL-07_05_2023-POLEREPL-1^06246006.0011500 | POLE | CA-NON-TIER | Distribution | 2023-07-05 | 2026-07-05 | 2
45762611-76373-DETAIL-06_13_2023-POLEREPL-1^06246006.0013501 | POLE | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
570066818-82409-DETAIL-11_09_2022-GO95MLD-1^06246007.0061501 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
144349140-17189-DETAIL-11_07_2022-GO95MLD-1^06246008.0012401 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
144349140-17189-DETAIL-11_07_2022-GRDRODHI-1^06246008.0012401 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
853433210-44269-DETAIL-11_07_2022-GO95TCH-1^06246008.0016300 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
525945876-96479-DETAIL-11_02_2022-GO95HV-1^06246008.0023100 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
940636816-75509-DETAIL-11_02_2022-GO95HV-1^06246008.0024401 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
699650500-40669-DETAIL-11_09_2022-GO95MLD-1^06246008.0027600 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
699650500-40669-DETAIL-11_09_2022-GO95MLD-2^06246008.0027600 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
321010870-25509-DETAIL-11_09_2022-GRDRODHI-1^06246008.0027603 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
894201846-74509-DETAIL-11_09_2022-GO95HV-1^06246008.0027604 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
206644756-54509-DETAIL-11_07_2022-GO95HV-1^06246008.0028601 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
222720730-42989-DETAIL-11_07_2022-GO95MLD-1^06246008.0028701 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
107766890-3869-DETAIL-11_09_2022-ABNDEQPM-1^06246008.0043200 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
722366584-27253-DETAIL-05_10_2023-CLRTOPOL-1^06245006.0273944 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
592996105-94453-DETAIL-05_10_2023-GO95MLD-1^06245006.0274740 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
192892455-80753-DETAIL-05_15_2023-SVCDEFLC-1^06245006.0274742 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
885747025-59553-DETAIL-05_15_2023-GUYHINS-1^06245006.0274743 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
885747025-59553-DETAIL-05_15_2023-SVCROOF-1^06245006.0274743 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
738561045-43379-DETAIL-05_25_2023-GO95MLD-1^06245006.0274744 | OTHER | CA-NON-TIER | Distribution | 2023-05-25 | 2026-05-25 | 2
561851904-8389-DETAIL-05_10_2023-GO95TCH-1^06245006.0274902 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
983753416-8223-DETAIL-05_10_2023-GO95MLD-1^06245006.0274940 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
111461425-3653-DETAIL-05_10_2023-GO95MLD-1^06245006.0274942 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
718682844-43849-DETAIL-05_23_2023-GO95MLD-1^06245006.0275401 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
150743394-62073-DETAIL-05_23_2023-GO95HV-1^06245006.0275440 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2028-05-23 | 3
150743394-62073-DETAIL-05_23_2023-GO95MLD-1^06245006.0275440 | OTHER | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
55141553-10749-DETAIL-05_17_2023-GO95MLD-1^06245006.0275500 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
202317364-2388-DETAIL-05_23_2023-CLRTOUCH-1^06245006.0275502 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-05-23 | 2026-05-23 | 2
112425744-30389-DETAIL-05_15_2023-GO95HV-1^06245006.0275800 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
107766890-3869-DETAIL-11_09_2022-GO95HV-1^06246008.0043200 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
854080680-70609-DETAIL-11_08_2022-GO95HV-1^06246008.0043300 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
96464880-32609-DETAIL-11_09_2022-GO95MLD-1^06246008.0046200 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
849522041-86709-DETAIL-11_02_2022-SVCENTCO-1^06246008.0050700 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
473398640-84899-DETAIL-11_02_2022-GO95MLD-1^06246008.0050702 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
889288240-709-DETAIL-10_27_2022-GO95HV-1^06246008.0050704 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
971877811-26709-DETAIL-11_02_2022-SVCENTCO-1^06246008.0051601 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
534002121-66709-DETAIL-11_02_2022-GO95MLD-1^06246008.0051603 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
534002121-66709-DETAIL-11_02_2022-GO95TCH-1^06246008.0051603 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
382695370-99-DETAIL-11_02_2022-GO95HV-1^06246008.0052601 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
382695370-99-DETAIL-11_02_2022-GO95MLD-1^06246008.0052601 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
783723731-45709-DETAIL-11_02_2022-GO95MLD-1^06246008.0053500 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
246462624-949-DETAIL-05_15_2023-GO95MLD-1^06245006.0275804 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
38721204-25073-DETAIL-05_15_2023-GO95MLD-1^06245006.0275841 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
717981323-72849-DETAIL-05_15_2023-XARMSPCR-1^06245006.0275900 | CROSSARM | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
717981323-72849-DETAIL-05_15_2023-XARMSPCR-2^06245006.0275900 | CROSSARM | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
162366189-74569-DETAIL-05_15_2023-GO95MLD-1^06245006.0275906 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
271764984-96873-DETAIL-05_15_2023-GO95HV-1^06245006.0275940 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
255352474-41873-DETAIL-05_15_2023-INSULDMG-1^06245006.0275941 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
255352474-41873-DETAIL-05_15_2023-INSULDMG-2^06245006.0275941 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
447779990-41709-DETAIL-11_02_2022-GO95HV-1^06246008.0054501 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
338857411-52709-DETAIL-11_08_2022-GO95MLD-1^06246008.0057501 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
775485121-46799-DETAIL-11_08_2022-GO95HV-1^06246008.0057502 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
897346541-71099-DETAIL-11_10_2022-GO95HV-1^06246008.0058300 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
344180031-24709-DETAIL-11_07_2022-ABNDEQPM-1^06246008.0059400 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
298129871-56809-DETAIL-10_26_2022-ABNDEQPM-1^06246008.0062100 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
831289383-53903-DETAIL-05_10_2023-SVCDEFLC-1^06245006.0275942 | OTHER | CA-NON-TIER | Distribution | 2023-05-10 | 2026-05-10 | 2
196563909-15649-DETAIL-05_17_2023-GO95HV-1^06245006.0276101 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
262698893-8749-DETAIL-05_15_2023-SVCDEFLC-1^06245006.0276801 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
429111663-94489-DETAIL-05_15_2023-GO95MLD-1^06245006.0276805 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
423942783-89749-DETAIL-05_15_2023-GO95MLD-1^06245006.0276806 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
362419484-80849-DETAIL-05_15_2023-CLMBTRE-1^06245006.0276807 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
730203803-22999-DETAIL-05_15_2023-GO95HV-1^06245006.0276903 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
756912531-97989-DETAIL-10_26_2022-SVCENTBK-1^06246008.0063300 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
630513901-21499-DETAIL-11_08_2022-GO95MLD-1^06246008.0066600 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
167651161-62809-DETAIL-11_08_2022-GO95MLD-1^06246008.0067700 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
694771131-18709-DETAIL-10_27_2022-GO95HV-1^06246008.0069801 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
482014120-87609-DETAIL-11_02_2022-GO95HV-1^06246008.0105701 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
774297318-24589-DETAIL-11_01_2022-GO95MLD-1^06246009.0076200 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
787848628-72189-DETAIL-10_18_2022-GO95HV-1^06246009.0078100 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
271525659-46059-DETAIL-05_15_2023-GO95MLD-1^06245006.0276905 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2028-05-15 | 3
727096834-79873-DETAIL-05_15_2023-GUYHINS-1^06245006.0276944 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
547732114-31173-DETAIL-05_15_2023-GUYNOINS-1^06245006.0276946 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
900312714-99073-DETAIL-05_15_2023-GO95MLD-1^06245006.0276947 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
811058681-58319-DETAIL-05_16_2023-GO95HV-1^06245006.0277200 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
859660369-48649-DETAIL-05_16_2023-GO95MLD-1^06245006.0277400 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
79309604-32704-DETAIL-05_16_2023-ABNDEQPM-1^06245006.0277402 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
633200344-51749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277500 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
787848628-72189-DETAIL-10_18_2022-GO95MLD-1^06246009.0078100 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
787848628-72189-DETAIL-10_18_2022-GO95STUB-1^06246009.0078100 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
368326158-94379-DETAIL-10_31_2022-GUYHINS-2^06246009.0091700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-31 | 2025-10-31 | 2
140676234-89209-DETAIL-11_08_2022-POLESTEP-1^06246009.0098301 | POLE | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
104761344-28209-DETAIL-11_08_2022-GO95STUB-1^06246009.0099201 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
332644474-38379-DETAIL-11_08_2022-GO95TCH-1^06246009.0103400 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
364826514-38699-DETAIL-11_08_2022-SVCROAD-1^06246009.0105300 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
644289398-25869-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0109300 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
171511634-60299-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110200 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
920496848-67569-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110201 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
113276144-66069-DETAIL-11_03_2022-GO95HV-1^06246009.0110301 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
810909063-49379-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110500 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
489483793-7799-DETAIL-05_16_2023-GO95MLD-1^06245006.0277804 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
90119013-65089-DETAIL-05_15_2023-GRDRODHI-1^06245006.0277901 | OTHER | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
90119013-65089-DETAIL-05_15_2023-GUYHINS-1^06245006.0277901 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-05-15 | 2026-05-15 | 2
367207434-13749-DETAIL-05_16_2023-SVCROAD-1^06245006.0278703 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
560038234-43749-DETAIL-05_16_2023-GO95TCH-1^06245006.0278704 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
379703238-54238-DETAIL-05_16_2023-SVCROAD-1^06245006.0278705 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
531932124-67299-DETAIL-05_16_2023-GO95MLD-1^06245006.0278706 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
531932124-67299-DETAIL-05_16_2023-GO95TCH-1^06245006.0278706 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
400212714-58689-DETAIL-05_16_2023-GO95MLD-1^06245006.0278904 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
752750510-50992-DETAIL-05_16_2023-SVCDEFLC-1^06245006.0279800 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2026-05-16 | 2
276225483-93749-DETAIL-05_16_2023-GO95HV-1^06245006.0279801 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
777694373-82873-DETAIL-05_16_2023-GO95HV-1^06245006.0279901 | OTHER | CA-NON-TIER | Distribution | 2023-05-16 | 2028-05-16 | 3
141565160-23589-DETAIL-05_17_2023-CLRTOUCH-1^06245006.0345302 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
646220000-56049-DETAIL-05_17_2023-GO95HV-1^06245006.0345800 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
279773191-31523-DETAIL-05_17_2023-GO95MLD-1^06245006.0346400 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
188241470-44049-DETAIL-05_17_2023-XARMBRAC-1^06245006.0347800 | CROSSARM | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
393412650-94049-DETAIL-05_17_2023-GO95HV-1^06245006.0347802 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
276415080-13049-DETAIL-05_17_2023-GO95HV-1^06245006.0349600 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
389168390-63049-DETAIL-05_17_2023-GO95HV-1^06245006.0349700 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
988911149-70549-DETAIL-05_17_2023-GO95HV-1^06245006.0350200 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
128985309-85599-DETAIL-05_17_2023-GO95MLD-1^06245006.0350400 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2026-05-17 | 2
146303403-64403-DETAIL-05_24_2023-GO95MLD-1^06245006.0352201 | OTHER | CA-NON-TIER | Distribution | 2023-05-24 | 2026-05-24 | 2
438696559-62549-DETAIL-05_17_2023-GO95HV-1^06245006.0352600 | OTHER | CA-NON-TIER | Distribution | 2023-05-17 | 2028-05-17 | 3
830563629-79439-DETAIL-05_09_2023-GO95HV-1^06245006.0362300 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
802641353-29379-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110501 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
75094963-79379-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110600 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
589020933-30909-DETAIL-11_03_2022-GO95HV-1^06246009.0111202 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
659045923-54779-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0112100 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
688106583-51479-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0114600 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
163321293-67279-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0114700 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
793847304-43079-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0115701 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
277671913-84909-DETAIL-11_01_2022-GO95MLD-1^06246009.0120200 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
926603603-75909-DETAIL-11_01_2022-ABNDEQPM-1^06246009.0121201 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2027-11-01 | 3
336404363-76009-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128700 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
30438443-69799-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128702 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
976827393-45009-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128802 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
917092589-24779-DETAIL-11_03_2022-GUYHINS-1^06246009.0130907 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
602667589-57409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0132200 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
715982739-49449-DETAIL-05_09_2023-GO95HV-1^06245006.0363101 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
671105829-10549-DETAIL-05_09_2023-GO95HV-1^06245006.0363300 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
835868169-8249-ADMIN-06_30_2022-POLEREPL-1^06245007.0218701 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
671416205-98241-DETAIL-10_06_2022-GO95HV-1^06245010.0066300 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
260993469-8109-DETAIL-10_06_2022-GO95HV-1^06245010.0083700 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
916130411-14599-DETAIL-10_06_2022-GO95MLD-1^06245010.0153000 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
174534501-70309-DETAIL-10_25_2022-GO95HV-1^06245010.0158000 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
483411570-77509-DETAIL-11_01_2022-GO95CL10-1^06246009.0132700 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2027-11-01 | 3
337724219-21509-DETAIL-10_20_2022-ANCHIDLE-1^06246009.0133400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
594886559-85779-DETAIL-10_20_2022-GO95HV-1^06246009.0133401 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2027-10-20 | 3
340511519-27509-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0135600 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
188539549-3699-DETAIL-10_20_2022-GO95MLD-1^06246009.0136300 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
683401280-73169-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0138100 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
629105569-61489-DETAIL-11_07_2022-GO95MLD-1^06246009.0138101 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
723130269-72509-DETAIL-11_03_2022-GUYHINS-2^06246009.0149900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
20499039-91279-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0237201 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
114362219-23409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0239500 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
434593019-32499-DETAIL-10_27_2022-GO95MLD-1^06246009.0239501 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
345396349-5409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0241802 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
442496309-16409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0241900 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
547578809-39389-DETAIL-10_27_2022-GO95HV-1^06246009.0243500 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
797495451-38889-DETAIL-10_05_2022-GRDRODHI-1^06246010.0054300 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
385097431-5709-DETAIL-10_05_2022-SVCWIND-1^06246010.0055200 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
401949581-43709-DETAIL-10_04_2022-GO95HV-1^06246010.0083400 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2027-10-04 | 3
778564621-1709-DETAIL-10_04_2022-GO95MLD-1^06246010.0083500 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
645006311-71709-DETAIL-10_04_2022-SVCRUBLG-1^06246010.0084401 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
997143801-53209-DETAIL-10_06_2022-GO95HV-1^06245010.0161200 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
475180319-91209-DETAIL-10_19_2022-GO95HV-1^06245010.0208000 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
302315231-95209-DETAIL-10_06_2022-GO95HV-1^06245010.0211300 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
427719551-94099-DETAIL-10_06_2022-GO95MLD-1^06245010.0211400 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
528138121-26209-DETAIL-10_06_2022-GO95HV-1^06245010.0211401 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
274939181-40799-DETAIL-10_06_2022-GO95MLD-1^06245010.0212700 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
993838871-53989-DETAIL-10_06_2022-GO95MLD-1^06245010.0212901 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
277171191-65709-DETAIL-10_05_2022-GO95HV-1^06246010.0085901 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2027-10-05 | 3
461382191-59589-DETAIL-10_05_2022-GO95HV-1^06246010.0085902 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2027-10-05 | 3
461382191-59589-DETAIL-10_05_2022-GO95MLD-1^06246010.0085902 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
702550313-76499-DETAIL-10_05_2022-GO95MLD-1^06246010.0088600 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
118918421-46709-DETAIL-10_05_2022-GO95HV-1^06246010.0089400 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2027-10-05 | 3
261347523-15089-DETAIL-10_05_2022-GO95MLD-1^06246010.0090300 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
252571638-45878-DETAIL-10_06_2022-GO95TCH-1^06245010.0213700 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
291691121-14879-DETAIL-10_06_2022-ABNDEQPM-1^06245010.0213701 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
367867471-33209-DETAIL-10_06_2022-GO95MLD-1^06245010.0213805 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
302619251-81689-DETAIL-10_06_2022-GO95MLD-1^06245010.0213902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
992363661-18209-DETAIL-10_06_2022-GO95HV-1^06245010.0220901 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
998391571-78579-DETAIL-10_06_2022-GRDRODHI-1^06245010.0220902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
299231033-8309-DETAIL-10_25_2022-GO95HV-1^06245010.0294200 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
783383723-78309-DETAIL-10_25_2022-GO95HV-1^06245010.0294302 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
37925122-73399-DETAIL-10_25_2022-GO95HV-1^06245010.0294303 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
287166551-74789-DETAIL-10_25_2022-GO95MLD-1^06245010.0295400 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2025-10-25 | 2
287166551-74789-DETAIL-10_25_2022-GRDRODHI-1^06245010.0295400 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2025-10-25 | 2
805507206-24748-DETAIL-10_25_2022-GO95HV-1^06245010.0295402 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
133072306-61648-DETAIL-10_25_2022-GO95HV-1^06245010.0295500 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
682183433-50089-DETAIL-10_05_2022-GO95MLD-1^06246010.0090400 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
566387217-52317-DETAIL-10_05_2022-GO95MLD-1^06246010.0093203 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
946971703-50979-DETAIL-10_05_2022-GO95MLD-1^06246010.0094100 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
713107461-87461-DETAIL-10_05_2022-GO95HV-1^06246010.0094300 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2027-10-05 | 3
713107461-87461-DETAIL-10_05_2022-GO95MLD-1^06246010.0094300 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
242099951-81409-DETAIL-10_19_2022-GO95HV-1^06245010.0297900 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
117562383-27309-DETAIL-10_19_2022-GO95MLD-1^06245010.0298801 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2025-10-19 | 2
409191133-67379-DETAIL-10_19_2022-GO95MLD-1^06245010.0298900 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2025-10-19 | 2
892058283-81309-DETAIL-10_25_2022-GO95HV-1^06245010.0315200 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
924591763-86279-DETAIL-10_25_2022-GO95HV-1^06245010.0316303 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
165125733-26309-DETAIL-10_25_2022-GUYNOINS-1^06245010.0322801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-25 | 2025-10-25 | 2
822968393-44309-DETAIL-10_25_2022-GO95HV-1^06245010.0322802 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
616371134-11989-DETAIL-07_15_2020-GO95HV-1^06246001.0172600 | OTHER | CA-NON-TIER | Distribution | 2020-07-15 | 2025-07-15 | 3
912419378-75082-ADMIN-01_25_2022-POLETOP-1^06246001.0334601 | POLE | CA-NON-TIER | Distribution | 2022-01-25 | 2025-01-25 | 2
722307888-94881-ADMIN-01_25_2022-POLETOP-1^06246001.0335700 | POLE | CA-NON-TIER | Distribution | 2022-01-25 | 2025-01-25 | 2
805247108-31289-DETAIL-11_09_2022-GO95MLD-1^06246007.0063400 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
313728161-80509-DETAIL-11_07_2022-GO95HV-1^06246008.0010900 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
144349140-17189-DETAIL-11_07_2022-GRDRODHI-2^06246008.0012401 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
831328203-779-DETAIL-10_05_2022-GO95MLD-1^06246010.0094401 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
544284133-28799-DETAIL-10_04_2022-GO95MLD-1^06246010.0098001 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
644474893-64189-DETAIL-10_04_2022-GO95MLD-1^06246010.0098200 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
947795033-35019-AUDIT-12_06_2022-GO95MLD-1^06246010.0130000 | OTHER | CA-TIER-2 | Distribution | 2022-12-06 | 2025-12-06 | 2
983396123-94019-DETAIL-10_18_2022-GO95MLD-1^06246010.0130002 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
118616248-56248-DETAIL-10_17_2022-GO95TCH-1^06246010.0143101 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
342960990-71909-DETAIL-10_17_2022-GO95STUB-1^06246010.0154000 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
297887691-58199-DETAIL-10_04_2022-GO95MLD-1^06246010.0154201 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
222746441-1909-DETAIL-10_17_2022-GO95BLTC-1^06246010.0154202 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
222746441-1909-DETAIL-10_17_2022-GO95MLD-1^06246010.0154202 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
456794401-34909-DETAIL-10_04_2022-GO95MLD-1^06246010.0156301 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
245177061-21161-DETAIL-10_04_2022-GO95HV-1^06246010.0159420 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2027-10-04 | 3
245177061-21161-DETAIL-10_04_2022-GO95MLD-1^06246010.0159420 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
186462109-66709-DETAIL-10_05_2022-GO95HV-1^06246010.0167900 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2027-10-05 | 3
320293980-3079-DETAIL-10_04_2022-ABNDEQPM-1^06246010.0168901 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2027-10-04 | 3
436439281-16809-DETAIL-10_04_2022-ABNDEQPM-1^06246010.0169600 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2027-10-04 | 3
490641220-18589-DETAIL-10_04_2022-GO95MLD-1^06246010.0169700 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
580736710-94809-AUDIT-12_06_2022-GO95MLD-1^06246010.0217200 | OTHER | CA-TIER-2 | Distribution | 2022-12-06 | 2025-12-06 | 2
402513510-42289-DETAIL-10_17_2022-GO95MLD-1^06246010.0217201 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
531015236-35409-DETAIL-11_07_2022-GO95HV-1^06246008.0012500 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
746708300-95409-DETAIL-11_07_2022-GO95MLD-1^06246008.0014301 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
211012830-17479-DETAIL-11_09_2022-SVCROAD-1^06246008.0026601 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
619578236-52499-DETAIL-11_09_2022-GO95MLD-1^06246008.0026603 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
336826500-67479-DETAIL-11_09_2022-GO95MLD-1^06246008.0027602 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
321010870-25509-DETAIL-11_09_2022-GO95MLD-1^06246008.0027603 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
516463770-32509-DETAIL-11_07_2022-SVCENTBK-1^06246008.0028901 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
327183876-8409-DETAIL-11_07_2022-GO95HV-1^06246008.0029401 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
671189266-78409-DETAIL-11_07_2022-GO95HV-1^06246008.0029500 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
681081266-98409-DETAIL-11_07_2022-GO95HV-1^06246008.0029600 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
461471540-61799-DETAIL-11_08_2022-GO95HV-1^06246008.0041400 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
552392870-38009-DETAIL-11_08_2022-GO95MLD-1^06246008.0043301 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
631141880-33499-DETAIL-11_10_2022-GO95MLD-1^06246008.0044301 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
129241780-2609-DETAIL-11_09_2022-ABNDEQPM-1^06246008.0045300 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
402513510-42289-DETAIL-10_17_2022-GO95MLD-2^06246010.0217201 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
150435430-90879-DETAIL-10_17_2022-GO95MLD-1^06246010.0217204 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
705655501-76501-DETAIL-10_17_2022-GO95HV-1^06246010.0217208 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
293954780-90809-DETAIL-10_17_2022-GO95MLD-1^06246010.0218300 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
984170191-55019-DETAIL-10_18_2022-GO95TCH-1^06246010.0240901 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
921696670-50099-DETAIL-10_18_2022-GO95BLTC-1^06246010.0241901 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
868498800-68399-DETAIL-11_09_2022-GO95MLD-1^06246008.0046202 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
473398640-84899-DETAIL-11_02_2022-GO95TCH-1^06246008.0050702 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
413378011-6709-DETAIL-11_02_2022-GO95MLD-1^06246008.0051500 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
413378011-6709-DETAIL-11_02_2022-GO95TCH-1^06246008.0051500 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
19152801-29489-DETAIL-11_02_2022-GO95MLD-1^06246008.0051501 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
846467890-31709-DETAIL-11_02_2022-GO95HV-1^06246008.0054502 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
361260351-25709-DETAIL-11_08_2022-GO95TCH-1^06246008.0056400 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
989357771-44709-DETAIL-11_08_2022-GO95MLD-1^06246008.0057400 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
338857411-52709-DETAIL-11_08_2022-GRDRODHI-1^06246008.0057501 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
775485121-46799-DETAIL-11_08_2022-GO95MLD-1^06246008.0057502 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
216658201-96389-DETAIL-10_26_2022-GO95HV-1^06246008.0061101 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
835968861-76219-DETAIL-10_18_2022-GO95HV-1^06246010.0283500 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
67148471-96219-DETAIL-10_18_2022-GO95HV-1^06246010.0284801 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
929771371-94219-DETAIL-10_18_2022-GO95HV-1^06246010.0284901 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
44697491-29219-DETAIL-10_18_2022-GO95MLD-1^06246010.0331900 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
367315178-72910-DTLSB-02_02_2023-SVCSVC-1^06247001.0010200 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
137445278-48180-DTLSB-02_02_2023-GRDRODHI-1^06247001.0010202 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
137445278-48180-DTLSB-02_02_2023-GRDRODHI-2^06247001.0010202 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
374166758-49420-DTLSB-02_02_2023-GO95MLD-1^06247001.0010500 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
184692811-31999-DETAIL-10_26_2022-ABNDEQPM-1^06246008.0062101 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
781613001-7809-DETAIL-10_26_2022-GO95HV-1^06246008.0062103 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
617154201-54809-DETAIL-11_10_2022-ABNDEQPM-1^06246008.0063001 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
564565971-18699-DETAIL-11_07_2022-ABNDEQPM-1^06246008.0063003 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
977177691-36809-DETAIL-10_26_2022-ABNDEQPM-1^06246008.0063101 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
756912531-97989-DETAIL-10_26_2022-GO95MLD-1^06246008.0063300 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
758472371-65999-DETAIL-10_27_2022-GO95TCH-1^06246008.0065101 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
374166758-49420-DTLSB-02_02_2023-GRDRODHI-1^06247001.0010500 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
686340488-50181-DTLSB-02_01_2023-GO95HV-1^06247001.0010901 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
686340488-50181-DTLSB-02_01_2023-INSULDMG-1^06247001.0010901 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
299755578-8740-DTLSB-02_01_2023-GO95HV-1^06247001.0011900 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
28272258-64670-DTLSB-02_02_2023-GO95MLD-1^06247001.0013000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
544319248-22431-DTLSB-01_26_2023-GO95HV-1^06247001.0015901 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
754495348-66461-DTLSB-01_26_2023-GO95MLD-1^06247001.0016900 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
920187338-91312-DTLSB-01_26_2023-GUYSLACK-1^06247001.0017905 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
758472371-65999-DETAIL-10_27_2022-SVCENTCO-1^06246008.0065101 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
748220191-15279-DETAIL-11_08_2022-GO95MLD-1^06246008.0066700 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
283299811-53089-DETAIL-10_27_2022-GO95HV-1^06246008.0067702 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
283299811-53089-DETAIL-10_27_2022-GO95MLD-1^06246008.0067702 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
492721431-97709-DETAIL-10_27_2022-GO95HV-1^06246008.0069800 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
143581960-45609-DETAIL-11_02_2022-GO95HV-1^06246008.0101800 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
393559920-8609-DETAIL-11_02_2022-GO95HV-1^06246008.0106700 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
585095830-68609-DETAIL-11_02_2022-GO95HV-1^06246008.0107700 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
588361350-79609-DETAIL-11_09_2022-GO95MLD-1^06246008.0108700 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
588361350-79609-DETAIL-11_09_2022-SVCWIND-1^06246008.0108700 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
6050440-39609-DETAIL-11_02_2022-GO95HV-1^06246008.0109701 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
652333546-79509-DETAIL-11_02_2022-GO95HV-1^06246008.0110700 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
957534818-42309-DETAIL-11_01_2022-GO95HV-1^06246009.0073100 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2027-11-01 | 3
368326158-94379-DETAIL-10_31_2022-GUYHINS-1^06246009.0091700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-31 | 2025-10-31 | 2
749830708-44351-DTLSB-02_06_2023-GO95MLD-1^06247001.0019201 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
873757416-37389-DTLSB-02_02_2023-GO95MLD-1^06247001.0120501 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
174603221-879-DTLSB-02_09_2023-GO95MLD-1^06247001.0129000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
646248769-45061-DETAIL-02_23_2023-GO95HV-1^06247001.0179900 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
476850649-56241-DETAIL-02_22_2023-GUYNOINS-1^06247001.0194401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
372151849-90020-AUDIT-03_08_2023-GO95HV-1^06247001.0194500 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
530976289-66521-DETAIL-02_23_2023-GO95HV-1^06247001.0209200 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
985297209-33413-DETAIL-02_23_2023-XARMBRAC-1^06247001.0209401 | CROSSARM | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
605354029-6121-DETAIL-09_11_2020-CONDFRAY-1^06247001.0239501 | CONDUCTOR | CA-NON-TIER | Distribution | 2020-09-11 | 2023-09-11 | 2
896112821-63912-DETAIL-02_27_2023-GO95HV-1^06247001.0299000 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
853358831-68062-DETAIL-02_23_2023-GO95HV-1^06247001.0299400 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
681668681-74961-DETAIL-02_13_2023-GO95MLD-1^06247002.0018100 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
682946623-34171-DETAIL-02_22_2023-GO95HV-1^06247002.0030601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
941332443-69503-DETAIL-02_22_2023-GO95HV-1^06247002.0031800 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
319039283-37560-DETAIL-02_22_2023-GO95MLD-1^06247002.0032100 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
658797162-60262-DETAIL-10_31_2022-GO95HV-1^06246009.0091702 | OTHER | CA-TIER-2 | Distribution | 2022-10-31 | 2027-10-31 | 3
958732578-35379-DETAIL-10_31_2022-GO95HV-1^06246009.0097500 | OTHER | CA-TIER-2 | Distribution | 2022-10-31 | 2027-10-31 | 3
340109625-70089-DETAIL-11_08_2022-GO95MLD-1^06246009.0099300 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
232401405-75209-DETAIL-11_08_2022-ABNDEQPM-1^06246009.0104300 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
781907248-12209-DETAIL-11_03_2022-GO95HV-1^06246009.0105600 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
461516944-46069-DETAIL-11_03_2022-GO95HV-1^06246009.0110300 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
59408473-68379-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0111600 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
589343493-81791-DETAIL-02_22_2023-GO95MLD-1^06247002.0032700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
589343493-81791-DETAIL-02_22_2023-GRDRODHI-1^06247002.0032700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
799018963-96389-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049200 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
799018963-96389-DETAIL-02_22_2023-GO95MLD-1^06247002.0049200 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
480338063-14251-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049201 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
402402953-11550-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049300 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
122533521-59299-DETAIL-02_21_2023-DISTHDWR-1^06247002.0094501 | CONNECTION DEVICE | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
105621922-62240-DETAIL-02_21_2023-GO95HV-1^06247002.0095000 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
611472932-35221-DETAIL-02_21_2023-CONDFRAY-1^06247002.0095400 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
998335421-5299-DETAIL-02_21_2023-GO95MLD-1^06247002.0095500 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
942542822-30803-DETAIL-02_21_2023-GO95HV-1^06247002.0096002 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
80496892-31779-DETAIL-02_14_2023-GO95MLD-1^06247002.0112900 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
149619052-13390-DETAIL-02_13_2023-GO95HV-1^06247002.0117700 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
297002231-15979-DETAIL-02_13_2023-GRDRODHI-1^06247002.0125500 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
833541936-61302-DETAIL-02_13_2023-GO95MLD-1^06247002.0134401 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
150056226-45790-DETAIL-02_15_2023-GO95HV-1^06247002.0144501 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
934915793-71909-DETAIL-10_27_2022-GO95HV-1^06246009.0113000 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
635722793-97379-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0115700 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
513292314-32909-DETAIL-11_01_2022-SVCENTCO-1^06246009.0118200 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
787782013-49299-DETAIL-11_01_2022-GO95MLD-1^06246009.0121202 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
830326323-80009-DETAIL-10_26_2022-GO95HV-1^06246009.0124201 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
340456853-42009-DETAIL-10_26_2022-GO95HV-1^06246009.0125501 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
803909363-21009-DETAIL-10_26_2022-GO95HV-1^06246009.0126601 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
734727663-17009-DETAIL-10_26_2022-GO95HV-1^06246009.0126700 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
958552043-69989-DETAIL-10_26_2022-GO95MLD-1^06246009.0127702 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
595727273-72099-DETAIL-10_26_2022-GO95HV-1^06246009.0127703 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
723978073-56009-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128701 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
34489383-48599-DETAIL-10_26_2022-GO95MLD-1^06246009.0128806 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
130429903-52579-DETAIL-10_26_2022-GO95MLD-1^06246009.0129903 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
188287853-96630-DETAIL-02_16_2023-GO95HV-1^06247002.0161000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
489396583-97861-DETAIL-02_16_2023-GO95BLTC-1^06247002.0161102 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
489396583-97861-DETAIL-02_16_2023-GO95MLD-1^06247002.0161102 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
645557273-20761-DETAIL-02_16_2023-GO95MLD-1^06247002.0161103 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
481352833-26051-DETAIL-02_16_2023-GO95HV-1^06247002.0163000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
780948823-69132-DETAIL-02_16_2023-ABNDEQPM-1^06247002.0165400 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
780948823-69132-DETAIL-02_16_2023-SVCROAD-1^06247002.0165400 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
668410813-48631-DETAIL-02_16_2023-GO95MLD-1^06247002.0166101 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
641528053-58461-DETAIL-02_20_2023-GUYNOINS-1^06247002.0207000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
548530063-42541-DETAIL-02_20_2023-GO95MLD-1^06247002.0207200 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
548530063-42541-DETAIL-02_20_2023-SVCROAD-1^06247002.0207200 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
273844573-24410-DETAIL-02_20_2023-GO95MLD-1^06247002.0207400 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
859384893-66779-DETAIL-02_20_2023-GO95MLD-1^06247002.0207500 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
123692104-63560-DETAIL-02_15_2023-CONDFRAY-3^06247002.0232600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
123692104-63560-DETAIL-02_15_2023-GO95MLD-1^06247002.0232600 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
927633057-63057-DETAIL-02_15_2023-GO95MLD-1^06247002.0232702 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
346460464-87290-DETAIL-02_15_2023-CLRTOUCH-1^06247002.0233500 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
717784094-99871-DETAIL-02_15_2023-GO95TCH-1^06247002.0235703 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
649524694-49681-DETAIL-02_15_2023-GO95MLD-1^06247002.0235704 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
657093144-29001-DETAIL-02_15_2023-GO95HV-1^06247002.0236500 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
935700424-89679-DETAIL-02_15_2023-GO95TCH-1^06247002.0237600 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
799856344-69482-DETAIL-02_14_2023-CLRTOUCH-1^06247002.0242801 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
799856344-69482-DETAIL-02_14_2023-GO95MLD-1^06247002.0242801 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
799856344-69482-AUDIT-02_21_2023-GRDRODHI-1^06247002.0242801 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
437389803-47909-DETAIL-11_03_2022-GUYHINS-1^06246009.0130900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
917092589-24779-DETAIL-11_03_2022-GUYHINS-2^06246009.0130907 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
766428879-46409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0131000 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
209176979-66409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0131001 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
132899163-23479-DETAIL-11_07_2022-GO95MLD-1^06246009.0131900 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
693707679-17409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0132100 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
191129149-91509-ADMIN-04_13_2023-POLEREPL-1^06246009.0132500 | POLE | CA-TIER-2 | Distribution | 2023-04-13 | 2024-04-13 | 2
483411570-77509-DETAIL-11_01_2022-GO95MLD-1^06246009.0132700 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
934993719-88389-DETAIL-10_20_2022-ABNDEQPM-1^06246009.0133200 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2027-10-20 | 3
870646109-41509-DETAIL-10_20_2022-ANCHIDLE-1^06246009.0133402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
720592670-20899-DETAIL-11_01_2022-GO95MLD-1^06246009.0133702 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
347817019-40079-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0134600 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
398365629-66509-DETAIL-10_20_2022-GO95MLD-1^06246009.0135402 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
407032339-48509-DETAIL-10_20_2022-ABNDEQPM-1^06246009.0136301 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2027-10-20 | 3
118179601-30701-DETAIL-10_20_2022-GO95MLD-1^06246009.0136400 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
756475459-36179-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0136600 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
810173260-76260-DETAIL-10_26_2022-GUYHINS-1^06246009.0136902 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
723130269-72509-DETAIL-11_03_2022-GO95HV-1^06246009.0149900 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
723130269-72509-DETAIL-11_03_2022-GUYHINS-1^06246009.0149900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
145779966-55280-DETAIL-02_20_2023-GO95HV-1^06247002.0296101 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
962105838-37753-DETAIL-02_20_2023-GRDRODHI-1^06247002.0296600 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
287804836-48720-DETAIL-02_20_2023-GUYHINS-1^06247002.0297402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
381703226-20730-DETAIL-02_20_2023-CONDFRAY-1^06247002.0297502 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
185916916-45620-DETAIL-02_20_2023-GO95HV-1^06247002.0297600 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
736569028-78721-DETAIL-02_20_2023-GO95HV-1^06247002.0297701 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
581447188-72281-DETAIL-02_20_2023-GO95MLD-1^06247002.0297900 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
450845986-35111-DETAIL-02_21_2023-GO95HV-1^06247002.0299700 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
994798358-58143-DETAIL-02_20_2023-GO95MLD-1^06247002.0325700 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
330935748-39770-DETAIL-02_20_2023-ABNDEQPM-1^06247002.0326800 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
379803015-28533-ADMIN-08_17_2022-POLEREPL-1^06247004.0076540 | POLE | CA-NON-TIER | Distribution | 2022-08-17 | 2025-08-17 | 2
382777939-2173-DETAIL-06_29_2023-POLEREPL-1^06247005.0209800 | POLE | CA-NON-TIER | Distribution | 2023-06-29 | 2026-06-29 | 2
663172973-3189-DETAIL-06_30_2023-POLEREPL-1^06247005.0214702 | POLE | CA-NON-TIER | Distribution | 2023-06-30 | 2026-06-30 | 2
260901058-56959-ADMIN-08_17_2022-POLEREPL-1^06247005.0266400 | POLE | CA-NON-TIER | Distribution | 2022-08-17 | 2025-08-17 | 2
802939785-8309-ADMIN-08_09_2023-POLEREPL-2^06247006.0267300 | POLE | CA-NON-TIER | Distribution | 2023-08-09 | 2026-08-09 | 2
279785639-72499-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0236101 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
434593019-32499-DETAIL-10_27_2022-GO95HV-1^06246009.0239501 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
876067529-82699-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0241700 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
547578809-39389-DETAIL-10_27_2022-GO95MLD-1^06246009.0243500 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
802647731-87189-DETAIL-10_05_2022-GO95MLD-1^06246010.0055201 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
645006311-71709-DETAIL-10_04_2022-GO95MLD-1^06246010.0084401 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
645006311-71709-DETAIL-10_04_2022-GRDRODHI-1^06246010.0084401 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
747329891-72199-DETAIL-10_05_2022-GO95MLD-1^06246010.0086600 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
35939503-88189-DETAIL-10_05_2022-GO95MLD-1^06246010.0093202 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
566387217-52317-DETAIL-10_05_2022-GO95HV-1^06246010.0093203 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2027-10-05 | 3
148710192-6609-AUDIT-12_06_2022-GO95MLD-1^06246010.0095000 | OTHER | CA-TIER-2 | Distribution | 2022-12-06 | 2025-12-06 | 2
197418956-33309-ADMIN-08_09_2023-POLEREPL-2^06247006.0267403 | POLE | CA-NON-TIER | Distribution | 2023-08-09 | 2026-08-09 | 2
17659031-66368-ADMIN-08_09_2023-POLEREPL-2^06247006.0267501 | POLE | CA-NON-TIER | Distribution | 2023-08-09 | 2026-08-09 | 2
32899585-35309-ADMIN-08_09_2023-POLEREPL-2^06247006.0268302 | POLE | CA-NON-TIER | Distribution | 2023-08-09 | 2026-08-09 | 2
240098270-4370-DETAIL-06_13_2023-POLEREPL-2^06247006.0361602 | POLE | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
129585809-16809-DETAIL-06_13_2023-POLEREPL-1^06247006.0362101 | POLE | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
917960866-38319-DETAIL-10_24_2022-GO95HV-1^06247008.0301900 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
439864466-18319-DETAIL-10_24_2022-GO95HV-1^06247008.0301901 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
605692592-76489-DETAIL-10_05_2022-GO95MLD-1^06246010.0097000 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
151693383-52609-DETAIL-10_04_2022-GO95MLD-1^06246010.0098101 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
588097681-97119-DETAIL-11_01_2022-GO95HV-1^06246010.0133800 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2027-11-01 | 3
535092552-62019-DETAIL-10_17_2022-GO95MLD-1^06246010.0143300 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
408199970-41099-DETAIL-10_17_2022-GO95CL10-1^06246010.0144102 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
247924071-79499-DETAIL-10_04_2022-GO95MLD-1^06246010.0150400 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
613028885-3319-DETAIL-10_24_2022-COPLLEAN-1^06247008.0303300 | POLE | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
909973055-91319-DETAIL-10_24_2022-GO95HV-1^06247008.0303400 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
613192606-90379-DETAIL-10_24_2022-GO95HV-1^06247008.0314903 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
339910316-2989-DETAIL-10_24_2022-GO95MLD-1^06247008.0315201 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
658413705-43879-DETAIL-10_24_2022-SVCENTCO-1^06247008.0315302 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
531814186-71319-DETAIL-10_24_2022-GO95HV-1^06247008.0315303 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
379474805-39379-DETAIL-10_24_2022-GO95MLD-1^06247008.0315305 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
958986135-83199-DETAIL-10_24_2022-GO95STUB-1^06247008.0315500 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
569934095-95319-DETAIL-10_24_2022-GO95HV-1^06247008.0316000 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
739075750-73979-DETAIL-11_07_2022-GO95HV-1^06247008.0361000 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
640297076-99319-DETAIL-10_24_2022-GO95HV-1^06247009.0248300 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
58406226-70419-DETAIL-10_24_2022-GO95HV-1^06247009.0249301 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
877692883-37299-DTLSB-02_07_2023-GO95MLD-1^06248001.0154304 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
304643713-76650-DTLSB-02_08_2023-GO95MLD-1^06248001.0155203 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
121716393-25360-DTLSB-02_07_2023-GO95HV-1^06248001.0155300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
541128684-96679-DTLSB-02_07_2023-GO95HV-1^06248001.0156101 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
663576673-41289-DTLSB-02_08_2023-GO95MLD-1^06248001.0157000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
820196514-58762-DTLSB-02_07_2023-ABNDEQPM-1^06248001.0157201 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
437693294-89790-DTLSB-02_07_2023-GO95HV-1^06248001.0157202 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
504079304-981-DTLSB-02_07_2023-GO95HV-1^06248001.0157203 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
793161404-66679-DTLSB-02_07_2023-GO95BLTC-1^06248001.0158100 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
793161404-66679-DTLSB-02_07_2023-GO95TCH-1^06248001.0158100 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
814247675-90342-DTLSB-02_08_2023-GO95MLD-1^06248001.0163401 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
905081371-22252-DTLSB-02_16_2023-GO95MLD-1^06248001.0197000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
336388562-28080-DTLSB-02_16_2023-GO95MLD-1^06248001.0203701 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
636767432-289-DTLSB-02_16_2023-GO95TCH-1^06248001.0209201 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
864209735-73379-DTLSB-02_16_2023-GO95MLD-1^06248001.0210100 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
190613978-6830-DTLSB-02_08_2023-GO95HV-1^06248001.0227901 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
937811298-11992-DTLSB-02_08_2023-GO95MLD-1^06248001.0227902 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
152483734-59099-DTLSB-02_09_2023-GO95MLD-1^06248001.0228501 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
103766071-96809-DETAIL-10_04_2022-GO95MLD-1^06246010.0150501 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
444387880-10909-DETAIL-10_17_2022-GO95HV-1^06246010.0153101 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
400672170-3289-DETAIL-10_17_2022-GO95HV-1^06246010.0153103 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
256984821-30909-DETAIL-10_17_2022-GO95TCH-1^06246010.0154100 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
82994131-25499-DETAIL-10_17_2022-GO95MLD-1^06246010.0154102 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
641453661-26189-DETAIL-10_17_2022-GO95STUB-1^06246010.0154104 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
908605391-80909-DETAIL-11_08_2022-SVCENTCO-1^06246010.0154200 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
222746441-1909-DETAIL-10_17_2022-GO95HV-1^06246010.0154202 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
582115851-45899-DETAIL-10_17_2022-GO95MLD-1^06246010.0156103 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
429259250-72809-DETAIL-10_18_2022-GO95HV-1^06246010.0215000 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
599492640-64679-DETAIL-10_17_2022-GO95MLD-1^06246010.0217000 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
402513510-42289-DETAIL-10_17_2022-GO95HV-1^06246010.0217201 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
469130392-70392-DTLSB-02_14_2023-GO95MLD-1^06248001.0228503 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
44337409-4809-DTLSB-02_13_2023-GO95MLD-1^06248001.0229140 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
784329078-42942-DTLSB-02_09_2023-GO95HV-1^06248001.0229401 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
559505688-43451-DTLSB-02_09_2023-GO95HV-1^06248001.0229501 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
943291898-58803-DTLSB-02_14_2023-GO95MLD-1^06248001.0229600 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
577332808-31681-DTLSB-02_08_2023-GO95MLD-1^06248001.0229701 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
707755803-50499-DTLSB-02_02_2023-GO95MLD-1^06248001.0254001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
958107903-95379-DTLSB-01_30_2023-GO95MLD-1^06248001.0255004 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
25683014-45679-DTLSB-01_30_2023-GO95MLD-1^06248001.0256000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
533223013-74879-AUDIT-02_07_2023-GO95HV-1^06248001.0256002 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
504118524-95789-DTLSB-01_30_2023-GO95HV-1^06248001.0257000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
564946764-21061-DTLSB-02_06_2023-GO95MLD-1^06248001.0257200 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
200054934-86640-DTLSB-01_30_2023-GO95MLD-1^06248001.0257500 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
264197834-25100-DTLSB-01_30_2023-GO95HV-1^06248001.0258500 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
719277843-42079-DTLSB-01_30_2023-GO95MLD-1^06248001.0259002 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
419662504-82770-DTLSB-01_30_2023-GO95MLD-1^06248001.0259100 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
402513510-42289-DETAIL-10_17_2022-GO95TCH-1^06246010.0217201 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
328684240-21809-DETAIL-10_17_2022-GO95HV-1^06246010.0217203 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
718578991-57669-DETAIL-10_17_2022-GO95HV-1^06246010.0218000 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
788195170-12999-DETAIL-10_18_2022-GO95BLTC-1^06246010.0241902 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
355149471-25219-DETAIL-10_18_2022-GO95HV-1^06246010.0284800 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
948544664-64909-DETAIL-10_19_2022-GO95HV-1^06246010.0329501 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
201785008-95969-DTLSB-09_03_2020-ENCHRW-1^06246011.0366240 | OTHER | CA-TIER-2 | Distribution | 2020-09-03 | 2023-09-03 | 2
885075738-53372-DTLSB-02_02_2023-GO95MLD-1^06247001.0014301 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
749830708-44351-DTLSB-02_06_2023-GO95TCH-1^06247001.0019201 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
809697678-69822-DETAIL-02_05_2018-ENCHRW-1^06247001.0019902 | OTHER | CA-NON-TIER | Distribution | 2018-02-05 | 2023-01-05 | 2
583151688-34191-DETAIL-02_23_2023-GO95HV-1^06247001.0089300 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
331526308-92079-DETAIL-02_23_2023-GO95CL10-1^06247001.0089500 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
331526308-92079-DETAIL-02_23_2023-GO95MLD-1^06247001.0089500 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
76798206-11100-DTLSB-02_02_2023-GO95MLD-1^06247001.0121600 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
480939321-60421-DTLSB-02_09_2023-GO95MLD-1^06247001.0129002 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
124162859-17760-DETAIL-02_23_2023-GO95HV-1^06247001.0179700 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
733717019-95179-DETAIL-02_22_2023-GO95HV-1^06247001.0194000 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
800011198-80782-DETAIL-02_22_2023-GO95HV-1^06247001.0198001 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
574337088-9671-DETAIL-02_22_2023-INSULDMG-1^06247001.0199000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
136356878-29480-DETAIL-02_22_2023-INSULDMG-1^06247001.0201000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
233813148-72570-DETAIL-02_23_2023-GO95MLD-1^06247001.0208000 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
937593714-77714-DTLSB-01_30_2023-GO95TCH-1^06248001.0259201 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
242872093-45780-DTLSB-01_30_2023-GO95MLD-1^06248001.0259400 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
110715124-60350-DTLSB-01_30_2023-GO95HV-1^06248001.0259501 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
876752553-5779-DTLSB-02_06_2023-GO95MLD-1^06248001.0262000 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
75837083-17079-DTLSB-02_02_2023-ABNDEQPM-1^06248001.0269001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
75837083-17079-DTLSB-02_02_2023-GO95MLD-1^06248001.0269001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
300680503-11240-DTLSB-02_13_2023-GO95MLD-1^06248001.0272901 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
777735391-19879-DTLSB-02_13_2023-GO95HV-1^06248001.0276000 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
797539473-19882-DETAIL-02_05_2018-ENCHRW-1^06248001.0276600 | OTHER | CA-NON-TIER | Distribution | 2018-02-05 | 2023-01-05 | 2
338390502-60380-DTLSB-02_13_2023-GO95HV-1^06248001.0277001 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
493170804-63661-DTLSB-02_09_2023-GO95HV-1^06248001.0277600 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
768512714-60602-AUDIT-04_28_2023-GO95MLD-1^06248001.0277601 | OTHER | CA-NON-TIER | Distribution | 2023-04-28 | 2026-04-28 | 2
403052633-73950-DTLSB-02_13_2023-GO95MLD-1^06248001.0278201 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
422711052-14570-DTLSB-02_13_2023-GO95MLD-1^06248001.0278304 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
77191680-26880-DTLSB-02_09_2023-GO95MLD-1^06248001.0279220 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
696919919-60101-DETAIL-02_23_2023-GO95HV-1^06247001.0209500 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
682253219-9571-DETAIL-02_23_2023-INSULDMG-1^06247001.0209501 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
269116449-3779-DETAIL-09_11_2020-CONDFRAY-1^06247001.0245402 | CONDUCTOR | CA-NON-TIER | Distribution | 2020-09-11 | 2023-09-11 | 2
129609421-1170-DETAIL-02_27_2023-XARMBRAC-1^06247001.0299200 | CROSSARM | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
30708261-300-ADMIN-07_17_2023-CONDFRAY-1^06247001.0349500 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-07-17 | 2026-07-17 | 2
681668681-74961-DETAIL-02_13_2023-CLRTOUCH-1^06247002.0018100 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
722969591-88689-DETAIL-02_22_2023-GO95HV-1^06247002.0030001 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
682946623-34171-DETAIL-02_22_2023-GO95MLD-1^06247002.0030601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
467882533-22331-DETAIL-02_22_2023-GO95MLD-1^06247002.0031600 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
338210453-91180-DETAIL-02_22_2023-GO95HV-1^06247002.0031801 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
83674553-15620-DETAIL-02_22_2023-GO95HV-1^06247002.0031900 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
319039283-37560-DETAIL-02_22_2023-GRDRODHI-1^06247002.0032100 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
96062272-28430-DETAIL-02_21_2023-CONDFRAY-1^06247002.0045401 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
150752232-68090-DETAIL-02_21_2023-GO95HV-1^06247002.0095200 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
933973412-71972-DETAIL-02_21_2023-GO95MLD-1^06247002.0096000 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
269879964-30010-DTLSB-02_09_2023-ABNDEQPM-1^06248001.0279742 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
269879964-30010-DTLSB-02_09_2023-ANCHIDLE-1^06248001.0279742 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
269879964-30010-DTLSB-02_09_2023-GO95HV-1^06248001.0279742 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
175227004-9004-DTLSB-02_13_2023-GO95MLD-1^06248001.0279743 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
897897801-34199-DTLSB-02_20_2023-GO95HV-1^06248001.0286600 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
38579092-46830-DTLSB-02_16_2023-GO95MLD-1^06248001.0288000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
771130981-40212-DTLSB-02_20_2023-GO95MLD-1^06248001.0288403 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
655462616-74616-DTLSB-02_16_2023-GO95MLD-1^06248001.0299002 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
268072153-39079-DTLSB-02_16_2023-GO95MLD-1^06248001.0299200 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
419986666-27666-DTLSB-02_15_2023-GO95MLD-1^06248001.0305001 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
729970666-71666-DTLSB-02_15_2023-GO95HV-1^06248001.0307101 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
206921011-73240-DTLSB-02_15_2023-GO95MLD-1^06248001.0309500 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
686175311-92671-DTLSB-02_15_2023-GO95HV-1^06248001.0309601 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
984287021-73213-DTLSB-02_15_2023-SVCROAD-1^06248001.0309800 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
56438543-48560-DTLSB-02_16_2023-GO95MLD-1^06248001.0334901 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
612893513-15921-DTLSB-02_14_2023-GO95MLD-1^06248001.0339401 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
243445383-92180-DTLSB-02_14_2023-GO95HV-1^06248001.0339702 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
558335602-42651-DTLSB-02_20_2023-GO95TCH-1^06248001.0340900 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
60260503-14270-DTLSB-02_14_2023-GO95HV-1^06248001.0341700 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
532204242-78421-DTLSB-02_20_2023-GO95HV-1^06248001.0345800 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
532204242-78421-DTLSB-02_20_2023-GO95MLD-1^06248001.0345800 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
561998340-44761-DTLSB-02_14_2023-GO95MLD-1^06248001.0347600 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
561998340-44761-AUDIT-02_22_2023-GO95HV-1^06248001.0347600 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
348806223-83190-DTLSB-02_14_2023-GO95MLD-1^06248001.0347601 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
189948443-62630-DTLSB-02_14_2023-GO95MLD-1^06248001.0349501 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
166184735-92910-DTLSB-02_02_2023-GO95MLD-1^06248001.0360900 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
166184735-92910-DTLSB-02_02_2023-SVCROAD-1^06248001.0360900 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
288594316-7489-DTLSB-01_31_2023-GO95MLD-1^06248001.0367800 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
42508626-84540-DTLSB-01_31_2023-GO95HV-1^06248001.0367809 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
42508626-84540-DTLSB-01_31_2023-GUYHINS-1^06248001.0367809 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
984670736-68813-DTLSB-01_31_2023-GO95MLD-1^06248001.0367901 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
296314126-61930-DTLSB-01_31_2023-GO95HV-1^06248001.0367905 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
577034102-51581-ADMIN-02_14_2023-GO95HV-1^06247002.0113101 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
762441152-68391-DETAIL-02_13_2023-GO95HV-1^06247002.0118701 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
297002231-15979-DETAIL-02_13_2023-GO95MLD-1^06247002.0125500 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
597354686-23001-DETAIL-02_13_2023-GO95HV-1^06247002.0134601 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
597354686-23001-DETAIL-02_13_2023-GO95MLD-1^06247002.0134601 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
559734276-54651-DETAIL-02_15_2023-GO95HV-1^06247002.0142900 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
852437684-35062-DETAIL-02_15_2023-GO95HV-1^06247002.0144301 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
604335794-68211-DETAIL-02_15_2023-CLRTOUCH-1^06247002.0144500 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
201642826-59440-DETAIL-02_15_2023-GO95MLD-1^06247002.0144700 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
44062536-81540-DETAIL-02_15_2023-GO95HV-1^06247002.0144800 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
397457943-29650-AUDIT-02_21_2023-GUYLOINS-1^06247002.0160000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
645557273-20761-DETAIL-02_16_2023-GO95BLTC-1^06247002.0161103 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
645557273-20761-DETAIL-02_16_2023-GRDRODHI-1^06247002.0161103 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
535104064-51289-DETAIL-02_16_2023-GO95MLD-1^06247002.0164002 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
780948823-69132-DETAIL-02_16_2023-ABNDEQPM-2^06247002.0165400 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
989995904-32433-DETAIL-02_16_2023-GO95HV-1^06247002.0165601 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
649855824-52881-DETAIL-02_16_2023-GO95HV-1^06247002.0165800 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
787817203-18952-DETAIL-02_16_2023-GO95HV-1^06247002.0166000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
987134303-67123-DETAIL-02_16_2023-GO95MLD-1^06247002.0166001 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
957119713-143-DETAIL-02_14_2023-GO95HV-1^06247002.0214700 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
701743954-53779-DETAIL-02_16_2023-GO95MLD-1^06247002.0217900 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
123692104-63560-DETAIL-02_15_2023-CONDFRAY-1^06247002.0232600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
123692104-63560-DETAIL-02_15_2023-CONDFRAY-2^06247002.0232600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
123692104-63560-DETAIL-02_15_2023-CONDFRAY-4^06247002.0232600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
351948696-76890-DTLSB-01_31_2023-GO95MLD-1^06248001.0367906 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
880828156-76662-DTLSB-01_31_2023-GO95MLD-1^06248001.0367908 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
751701365-8261-DTLSB-02_01_2023-GO95MLD-1^06248001.0368000 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
734220465-47979-DTLSB-02_01_2023-GO95MLD-1^06248001.0368001 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
315357875-82560-DTLSB-02_01_2023-GO95BLTC-1^06248001.0368101 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
315357875-82560-DTLSB-02_01_2023-GO95HV-1^06248001.0368101 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
116096985-42060-DTLSB-02_02_2023-GO95MLD-1^06248001.0368102 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
419830485-33870-DTLSB-02_02_2023-SVCENTCO-1^06248001.0368104 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
524959446-32311-DETAIL-02_15_2023-GO95MLD-1^06247002.0232700 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
927633057-63057-DETAIL-02_15_2023-GO95CL10-1^06247002.0232702 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
346460464-87290-DETAIL-02_15_2023-SVCROAD-1^06247002.0233500 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
462662284-66721-DETAIL-02_15_2023-GO95HV-1^06247002.0235601 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
463303796-88031-DETAIL-02_15_2023-GO95MLD-1^06247002.0235801 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
296035314-95730-DETAIL-02_15_2023-GO95MLD-1^06247002.0236701 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
57463444-53460-DETAIL-02_16_2023-GO95HV-1^06247002.0238500 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
583777824-25491-DETAIL-02_14_2023-GO95HV-1^06247002.0240501 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
210449505-27050-DTLSB-02_01_2023-ENCHRW-1^06248001.0368301 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
963916995-20263-DTLSB-02_01_2023-GO95MLD-1^06248001.0368302 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
791182866-74662-DTLSB-02_01_2023-GO95MLD-1^06248001.0368701 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
778294276-38232-DTLSB-02_01_2023-SVCROAD-1^06248001.0368904 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
185153626-89220-DTLSB-01_31_2023-GO95MLD-1^06248001.0369500 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
293124226-30379-DTLSB-02_01_2023-GRDBROKE-1^06248001.0369600 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
305491966-16450-DTLSB-02_01_2023-GO95MLD-1^06248001.0369601 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
305491966-16450-DTLSB-02_01_2023-SVCDEFLC-1^06248001.0369601 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
676034716-75579-DTLSB-01_31_2023-GO95MLD-1^06248001.0369701 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
685897466-20171-DTLSB-01_31_2023-GO95HV-1^06248001.0369704 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
685897466-20171-DTLSB-01_31_2023-GO95MLD-1^06248001.0369704 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
685897466-20171-DTLSB-01_31_2023-GO95TCH-1^06248001.0369704 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
171455186-28510-DTLSB-01_31_2023-GO95MLD-1^06248001.0369706 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
712095378-91851-DTLSB-01_30_2023-GO95HV-1^06248001.0369710 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
712095378-91851-DTLSB-01_30_2023-GO95MLD-1^06248001.0369710 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
876925476-7752-DTLSB-01_30_2023-GO95MLD-1^06248001.0369711 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
476887254-36579-DETAIL-02_14_2023-GO95MLD-1^06247002.0242900 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
22826160-4089-DETAIL-02_16_2023-GO95MLD-1^06247002.0278901 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
501223218-30271-DETAIL-02_20_2023-GO95MLD-1^06247002.0297400 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
287804836-48720-DETAIL-02_20_2023-GO95MLD-1^06247002.0297402 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
381703226-20730-DETAIL-02_20_2023-GO95HV-1^06247002.0297502 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
871043888-50389-DETAIL-02_20_2023-GO95MLD-1^06247002.0320100 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
871043888-50389-DETAIL-02_20_2023-GUYHINS-1^06247002.0320100 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
376130549-69359-ADMIN-07_26_2022-POLEREPL-1^06247005.0057300 | POLE | CA-NON-TIER | Distribution | 2022-07-26 | 2025-07-26 | 2
976973730-4299-ADMIN-07_22_2022-POLEREPL-1^06247005.0205301 | POLE | CA-NON-TIER | Distribution | 2022-07-22 | 2025-07-22 | 2
751812150-99559-ADMIN-07_22_2022-POLEREPL-1^06247005.0205401 | POLE | CA-NON-TIER | Distribution | 2022-07-22 | 2025-07-22 | 2
609298304-38189-ADMIN-07_07_2023-POLEREPL-1^06247005.0300502 | POLE | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
291257374-43659-ADMIN-07_07_2023-POLEREPL-1^06247005.0302500 | POLE | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
966177945-70319-DETAIL-10_24_2022-GO95HV-1^06247008.0191000 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
300352575-87319-DETAIL-10_24_2022-GO95HV-1^06247008.0304100 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
231779806-5319-DETAIL-10_24_2022-GO95MLD-1^06247008.0315200 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
339910316-2989-DETAIL-10_24_2022-GO95HV-1^06247008.0315201 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
745608796-5889-DETAIL-10_24_2022-GO95HV-1^06247008.0315300 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
745608796-5889-DETAIL-10_24_2022-GO95MLD-1^06247008.0315300 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
543014506-19631-DTLSB-01_30_2023-GO95MLD-1^06248001.0369800 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
300518706-26140-DTLSB-02_01_2023-GO95MLD-1^06248001.0369807 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
263566413-30423-AUDIT-03_07_2023-GUYNOINS-1^06248001.0369820 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
857022533-60689-ADMIN-02_24_2023-POLEREPL-1^06248004.0332701 | POLE | CA-TIER-2 | Distribution | 2023-02-24 | 2024-02-24 | 2
354003699-58143-ADMIN-02_24_2023-POLEREPL-1^06248004.0353341 | POLE | CA-TIER-2 | Distribution | 2023-02-24 | 2024-02-24 | 2
666638739-99473-ADMIN-04_27_2023-POLEREPL-1^06248007.0132001 | POLE | CA-NON-TIER | Distribution | 2023-04-27 | 2026-04-27 | 2
752516993-31093-ADMIN-04_27_2023-POLEREPL-1^06248007.0243301 | POLE | CA-NON-TIER | Distribution | 2023-04-27 | 2026-04-27 | 2
210173509-37473-ADMIN-04_26_2023-POLEREPL-1^06248007.0244900 | POLE | CA-NON-TIER | Distribution | 2023-04-26 | 2026-04-26 | 2
320785503-68649-DETAIL-03_16_2023-GO95HV-1^07113001.0040403 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
836720470-15649-DETAIL-03_16_2023-GO95HV-1^07113001.0042501 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
836720470-15649-DETAIL-03_16_2023-GO95MLD-1^07113001.0042501 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
935263150-96649-DETAIL-03_16_2023-SVCDEFLC-1^07113001.0042502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
658413705-43879-DETAIL-10_24_2022-GO95MLD-1^06247008.0315302 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
514527825-74479-DETAIL-10_24_2022-GO95STUB-1^06247008.0315400 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
958986135-83199-DETAIL-10_24_2022-GO95MLD-1^06247008.0315500 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
928899896-9979-DETAIL-10_24_2022-GO95MLD-1^06247009.0247500 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
884040023-57299-DTLSB-02_07_2023-SVCROAD-1^06248001.0154303 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
250282783-56199-DTLSB-02_07_2023-GO95MLD-1^06248001.0156201 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
820196514-58762-DTLSB-02_07_2023-GO95MLD-1^06248001.0157201 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
314744494-51060-DTLSB-02_07_2023-GO95HV-1^06248001.0158102 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
122211924-3660-DTLSB-02_07_2023-GO95MLD-1^06248001.0158200 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
185015744-43220-DTLSB-02_07_2023-SVCENTCO-1^06248001.0158300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
309266265-45950-DTLSB-02_08_2023-GO95HV-1^06248001.0164401 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
973806655-74483-DTLSB-02_08_2023-GO95MLD-1^06248001.0166400 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
675857112-40051-DTLSB-02_16_2023-GO95HV-1^06248001.0209001 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
636767432-289-DTLSB-02_16_2023-GO95MLD-1^06248001.0209201 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
248467292-8292-DTLSB-02_09_2023-GUYNOINS-1^06248001.0228600 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
133284898-83970-DTLSB-02_08_2023-GRDRODHI-1^06248001.0228900 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
44337409-4809-DTLSB-02_13_2023-GO95HV-1^06248001.0229140 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
77851893-4700-DTLSB-02_06_2023-GO95MLD-1^06248001.0243100 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
543753983-79279-DTLSB-02_02_2023-GO95MLD-1^06248001.0250000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
657226673-44101-DTLSB-02_06_2023-GO95HV-1^06248001.0256900 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
772926554-71512-DTLSB-02_06_2023-GO95HV-1^06248001.0257001 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
804803754-80702-DTLSB-01_30_2023-GO95HV-1^06248001.0257002 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
548697413-81479-DTLSB-01_30_2023-GO95MLD-1^06248001.0257004 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
605801380-1749-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0042601 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
134526310-3649-DETAIL-03_16_2023-GO95MLD-1^07113001.0043501 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
717153908-66908-DETAIL-03_16_2023-GO95MLD-1^07113001.0043502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
507479578-82678-DETAIL-03_16_2023-ENCHRW-1^07113001.0043503 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
817988410-73449-DETAIL-03_16_2023-GO95MLD-1^07113001.0045500 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
817988410-73449-DETAIL-03_16_2023-GUYHINS-1^07113001.0045500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
650499560-45849-DETAIL-03_21_2023-GO95HV-1^07113001.0049200 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
856598583-75749-DETAIL-03_21_2023-GO95HV-1^07113001.0053800 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
927753733-85239-DETAIL-03_21_2023-GO95MLD-1^07113001.0055500 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
745913313-31439-DETAIL-03_21_2023-GUYHINS-1^07113001.0056500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
729330686-83159-DETAIL-03_21_2023-ABNDEQPM-1^07113001.0056501 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
968527623-13049-DETAIL-03_21_2023-CLRTOUCH-1^07113001.0056504 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
997862064-51149-DETAIL-03_21_2023-ABNDEQPM-1^07113001.0057500 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
997862064-51149-DETAIL-03_21_2023-GO95HV-1^07113001.0057500 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
694807454-42749-DETAIL-03_21_2023-GO95HV-1^07113001.0057501 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
694807454-42749-DETAIL-03_21_2023-GO95MLD-1^07113001.0057501 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
151609833-20239-DETAIL-03_21_2023-GO95HV-1^07113001.0058501 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
151609833-20239-DETAIL-03_21_2023-GUYHINS-1^07113001.0058501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
488732093-51749-DETAIL-03_21_2023-GUYHINS-1^07113001.0058504 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
612842733-92733-DETAIL-03_21_2023-GUYHINS-1^07113001.0058601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
469225214-82049-DETAIL-03_16_2023-GO95HV-1^07113001.0059602 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
241732556-36059-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0059700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
241732556-36059-DETAIL-03_16_2023-GO95MLD-1^07113001.0059700 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
562600584-90049-ADMIN-07_14_2022-COPLLEAN-1^07113001.0175400 | POLE | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
194217664-58730-DTLSB-02_06_2023-GO95HV-1^06248001.0257201 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
194217664-58730-DTLSB-02_06_2023-GO95MLD-1^06248001.0257201 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
101960373-88189-DTLSB-02_06_2023-GO95MLD-1^06248001.0257800 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
722239533-34879-DTLSB-01_30_2023-GO95HV-1^06248001.0258000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
571526063-48189-DTLSB-02_06_2023-GO95HV-1^06248001.0258701 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
719277843-42079-DTLSB-01_30_2023-GO95HV-1^06248001.0259002 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
719277843-42079-DTLSB-01_30_2023-GO95TCH-1^06248001.0259002 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
274870243-93879-DTLSB-01_30_2023-GO95HV-1^06248001.0259003 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
274870243-93879-DTLSB-01_30_2023-GO95MLD-1^06248001.0259003 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
419662504-82770-DTLSB-01_30_2023-SVCROAD-1^06248001.0259100 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
330047104-32470-DTLSB-01_30_2023-CONDCOIL-1^06248001.0259101 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
53205924-22750-DTLSB-02_06_2023-GO95HV-1^06248001.0259203 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
552799451-79941-DTLSB-02_06_2023-GO95MLD-1^06248001.0259600 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
921044660-6660-DTLSB-02_08_2023-GO95HV-1^06248001.0260001 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
320304394-79160-DTLSB-02_09_2023-GO95MLD-1^06248001.0260900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
876752553-5779-DTLSB-02_06_2023-GO95TCH-1^06248001.0262000 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
340630532-73049-ADMIN-05_20_2022-GO95HV-1^07113002.0181106 | OTHER | CA-NON-TIER | Distribution | 2022-05-20 | 2027-05-20 | 3
79023173-83339-DETAIL-03_16_2023-GO95CL10-1^07114001.0205002 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
425749113-2259-DETAIL-03_20_2023-GO95TCH-1^07114001.0206001 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
249512923-71259-DETAIL-03_16_2023-SVCDEFLC-1^07114001.0206040 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
662430643-46249-DETAIL-03_16_2023-CUTOUTAR-1^07114001.0206100 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
648812223-41259-DETAIL-03_16_2023-SVCDEFLC-3^07114001.0206140 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
441659173-66249-DETAIL-03_20_2023-GO95HV-1^07114001.0206202 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
544313963-17879-DTLSB-02_02_2023-GO95HV-1^06248001.0266000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
621105063-76879-DTLSB-02_02_2023-GO95HV-1^06248001.0267000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
591750684-39301-DTLSB-02_02_2023-GO95HV-1^06248001.0267002 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
923432973-58779-DTLSB-02_02_2023-GO95MLD-1^06248001.0268000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
606261473-96279-DTLSB-02_02_2023-GO95MLD-1^06248001.0268001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
881681581-3562-DTLSB-02_14_2023-GO95MLD-1^06248001.0275001 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
605334373-45121-DTLSB-02_20_2023-GO95MLD-1^06248001.0275002 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
969555653-42773-DTLSB-02_13_2023-GO95TCH-1^06248001.0276400 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
441659173-66249-DETAIL-03_20_2023-GO95MLD-1^07114001.0206202 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
436195543-58549-DETAIL-03_14_2023-GO95HV-1^07114001.0275401 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
44967753-22849-DETAIL-03_14_2023-SVCDEFLC-1^07114001.0275402 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
801770213-22339-DETAIL-03_14_2023-GO95MLD-1^07114001.0275403 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
801770213-22339-DETAIL-03_14_2023-GO95TCH-1^07114001.0275403 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
127389073-30539-DETAIL-03_14_2023-GO95MLD-1^07114001.0276300 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
127389073-30539-DETAIL-03_14_2023-SVCDEFLC-1^07114001.0276300 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
797539473-19882-DTLSB-02_09_2023-GO95MLD-1^06248001.0276600 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
386409084-50630-DTLSB-02_13_2023-GO95MLD-1^06248001.0276740 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
224497643-78160-AUDIT-03_08_2023-GO95MLD-1^06248001.0277302 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
480745162-87551-DTLSB-02_13_2023-GO95MLD-1^06248001.0278301 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
783147474-54842-DTLSB-02_13_2023-GO95HV-1^06248001.0278740 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
357487201-56500-DTLSB-02_13_2023-GO95MLD-1^06248001.0279000 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
321626152-47460-DTLSB-02_13_2023-GO95MLD-1^06248001.0279301 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
605546004-51221-DTLSB-02_09_2023-GO95HV-1^06248001.0279601 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
217786823-31839-DETAIL-03_14_2023-GO95MLD-1^07114001.0276305 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
34853713-68739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276307 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
533872253-93139-DETAIL-03_14_2023-CLMBHAZ-1^07114001.0276406 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
82668533-96739-DETAIL-03_14_2023-GO95HV-1^07114001.0276500 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
82668533-96739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276500 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
323678083-22049-DETAIL-03_14_2023-GUYSLACK-1^07114001.0276502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
868530053-52249-DETAIL-03_14_2023-GO95HV-1^07114001.0276503 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
589498553-7639-DETAIL-03_14_2023-GO95MLD-1^07114001.0276504 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
268715604-71410-DTLSB-02_09_2023-GO95HV-1^06248001.0279602 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
58105331-56241-AUDIT-02_22_2023-GO95HV-1^06248001.0279921 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
339822634-64080-DTLSB-02_20_2023-GO95MLD-1^06248001.0284601 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
618067151-17331-DTLSB-02_20_2023-GO95MLD-1^06248001.0287400 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
276564771-72199-DTLSB-02_20_2023-GO95HV-1^06248001.0288400 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
45292561-51979-DTLSB-02_20_2023-GO95HV-1^06248001.0289200 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
116472971-1189-DTLSB-02_16_2023-GO95HV-1^06248001.0299300 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
870541841-18679-DTLSB-02_16_2023-GO95TCH-1^06248001.0299600 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
532385693-15739-DETAIL-03_14_2023-GO95HV-1^07114001.0276600 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
532385693-15739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276600 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
169960563-349-DETAIL-03_14_2023-GO95MLD-1^07114001.0277501 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
894419123-49949-DETAIL-03_14_2023-CLRTOUCH-1^07114001.0277503 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
822486023-50049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277504 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
925288993-4339-DETAIL-03_14_2023-ABNDEQPM-1^07114001.0277604 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
670449313-74449-DETAIL-03_14_2023-GO95HV-1^07114001.0277607 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
670449313-74449-DETAIL-03_14_2023-SVCROAD-1^07114001.0277607 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
73325613-10259-DETAIL-03_14_2023-SVCDEFLC-1^07114001.0277700 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
754181803-3049-DETAIL-03_14_2023-SVCDEFLC-1^07114001.0277701 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
482909773-85749-DETAIL-03_14_2023-GO95MLD-1^07114001.0277800 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
118497593-63749-DETAIL-03_14_2023-GUYNOINS-1^07114001.0278900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
646933783-64049-DETAIL-03_14_2023-GO95MLD-1^07114001.0278902 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
563275008-36008-DETAIL-03_16_2023-GO95HV-1^07114001.0281602 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
242770747-47259-DETAIL-03_16_2023-GO95HV-1^07114001.0281640 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
735701683-47749-DETAIL-03_16_2023-GO95TCH-1^07114001.0281703 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
713306043-44949-DETAIL-03_16_2023-GO95MLD-1^07114001.0282403 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
837571408-72408-DETAIL-03_16_2023-CLMBTRE-1^07114001.0282604 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
4642574-99259-DETAIL-03_16_2023-GO95HV-1^07114001.0282640 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
681366264-17049-DETAIL-03_14_2023-CLMBTRE-1^07114001.0283200 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
531222524-21149-DETAIL-03_20_2023-SVCDEFLC-1^07114001.0283301 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
506249154-80149-DETAIL-03_16_2023-GO95MLD-1^07114001.0283304 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
277786744-81149-DETAIL-03_16_2023-ABNDEQPM-1^07114001.0283305 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
434662124-23539-DETAIL-03_20_2023-GO95MLD-1^07114001.0283307 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
356717214-12149-DETAIL-03_16_2023-GO95HV-1^07114001.0283308 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
356717214-12149-DETAIL-03_16_2023-GO95MLD-1^07114001.0283308 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
356717214-12149-DETAIL-03_16_2023-GUYHINS-1^07114001.0283308 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
353643394-30049-DETAIL-03_15_2023-GO95MLD-1^07114001.0284201 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
284772464-89049-DETAIL-03_15_2023-GO95HV-1^07114001.0284202 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
97001434-3849-DETAIL-03_14_2023-GO95MLD-1^07114001.0284206 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
208374521-21050-DTLSB-02_15_2023-GO95MLD-1^06248001.0308200 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
210128191-37850-DTLSB-02_15_2023-GO95HV-1^06248001.0308203 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
150492401-64990-DTLSB-02_15_2023-GO95MLD-1^06248001.0308300 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
917522801-24502-DTLSB-02_15_2023-GO95HV-1^06248001.0309400 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
729268611-6901-DTLSB-02_15_2023-GO95HV-1^06248001.0309600 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
109366811-42450-DTLSB-02_15_2023-GO95HV-1^06248001.0309700 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
984287021-73213-DTLSB-02_15_2023-GO95HV-1^06248001.0309800 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
684843353-30171-DTLSB-02_16_2023-GO95MLD-1^06248001.0334900 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
56438543-48560-DTLSB-02_16_2023-ABNDEQPM-1^06248001.0334901 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
632701831-17199-DTLSB-02_14_2023-INSULDMG-1^06248001.0339801 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
558335602-42651-DTLSB-02_20_2023-GO95MLD-1^06248001.0340900 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
673089523-72941-DTLTRT-02_14_2023-GO95BLTC-1^06248001.0342701 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
13967892-87892-DTLTRT-02_14_2023-GO95BLTC-1^06248001.0342702 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
993924742-20043-DTLSB-02_20_2023-SVCDEFLC-1^06248001.0344800 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
357410003-75400-DTLSB-02_14_2023-GO95MLD-1^06248001.0346901 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
189948443-62630-DTLSB-02_14_2023-CLRTOUCH-1^06248001.0349501 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
526929034-65811-DTLSB-02_06_2023-GO95MLD-1^06248001.0353800 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
166184735-92910-DTLSB-02_02_2023-SVCENTBK-1^06248001.0360900 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
554934385-95551-DTLSB-02_02_2023-ENCHRW-1^06248001.0360901 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
854567000-95100-DTLSB-01_30_2023-GUYLOINS-1^06248001.0366900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
165647376-52710-DTLSB-01_31_2023-GO95HV-1^06248001.0367801 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
156865376-1390-DTLSB-01_31_2023-GO95MLD-1^06248001.0367804 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
215972096-36950-DTLSB-01_31_2023-SVCENTCO-1^06248001.0367805 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
750262276-22851-DTLSB-01_31_2023-GUYHINS-1^06248001.0367807 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
525927674-62259-DETAIL-03_15_2023-SVCDEFLC-1^07114001.0284301 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
794359904-89549-DETAIL-03_15_2023-GO95MLD-1^07114001.0284304 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
511942124-68049-DETAIL-03_20_2023-GO95MLD-1^07114001.0284305 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
645992814-11849-DETAIL-03_20_2023-GO95MLD-1^07114001.0284306 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
729469404-20149-DETAIL-03_20_2023-SVCWIND-1^07114001.0284308 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
998037034-21139-DETAIL-03_20_2023-GO95MLD-1^07114001.0284402 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
958482644-53259-DETAIL-03_20_2023-GO95MLD-1^07114001.0285100 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
641251134-76049-DETAIL-03_20_2023-GO95HV-1^07114001.0285300 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
908018694-9339-DETAIL-03_20_2023-SVCDEFLC-1^07114001.0285301 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
633935834-82259-DETAIL-03_16_2023-SVCDEFLC-1^07114001.0298902 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
610112214-42249-DETAIL-03_16_2023-CLMBTRE-1^07114001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
610112214-42249-DETAIL-03_16_2023-GO95HV-1^07114001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
967853093-62249-DETAIL-03_16_2023-GO95TCH-1^07114001.0299702 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
13502633-92049-DETAIL-03_16_2023-GO95MLD-1^07114001.0299801 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
726604724-82249-DETAIL-03_16_2023-SVCDEFLC-1^07114001.0299802 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
726604724-82249-DETAIL-03_16_2023-SVCENTCO-1^07114001.0299802 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
499256003-12249-DETAIL-03_16_2023-GO95HV-1^07114001.0299806 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
366393444-44259-DETAIL-03_15_2023-SVCDEFLC-2^07114001.0325306 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
513733185-48749-DETAIL-03_15_2023-GO95HV-1^07114001.0327000 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
130421324-97449-DETAIL-03_15_2023-SVCENTCO-1^07114001.0335900 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
105178184-98849-DETAIL-03_15_2023-GO95HV-1^07114001.0339404 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
8523504-18849-DETAIL-03_15_2023-GO95HV-1^07114001.0339500 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
169522597-70849-DETAIL-03_15_2023-GUYHINS-1^07114001.0341100 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
750262276-22851-AUDIT-02_07_2023-GO95MLD-1^06248001.0367807 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
947315956-99523-DTLSB-01_30_2023-GO95MLD-1^06248001.0367903 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
9014886-56549-DTLSB-01_31_2023-GO95MLD-1^06248001.0367904 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
9014886-56549-DTLSB-01_31_2023-SVCENTCO-1^06248001.0367904 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
296314126-61930-DTLSB-01_31_2023-GO95MLD-1^06248001.0367905 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
315357875-82560-DTLSB-02_01_2023-GO95MLD-1^06248001.0368101 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
532146226-67979-DTLSB-01_31_2023-GO95MLD-1^06248001.0368803 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
488157116-45861-DTLSB-01_31_2023-GUYHINS-1^06248001.0368808 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
460839856-51956-DTLSB-01_30_2023-GO95MLD-1^06248001.0368906 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
907479025-34162-DTLSB-02_01_2023-GO95HV-1^06248001.0369201 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
174578905-23410-DTLSB-02_01_2023-ABNDEQPM-1^06248001.0369300 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
885889655-60172-DTLSB-02_01_2023-GO95MLD-1^06248001.0369304 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
293124226-30379-DTLSB-02_01_2023-GO95MLD-1^06248001.0369600 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
737958266-34221-DTLSB-02_01_2023-GO95TCH-1^06248001.0369603 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
570851006-92671-DTLSB-02_01_2023-ABNDEQPM-1^06248001.0369709 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
876925476-7752-DTLSB-01_30_2023-SVCWIND-1^06248001.0369711 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
751354976-31161-DTLSB-01_30_2023-GO95MLD-1^06248001.0369712 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
209684996-86550-DTLSB-01_30_2023-GO95MLD-1^06248001.0369801 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
942074336-25103-DTLSB-01_30_2023-GO95MLD-1^06248001.0369802 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
97110436-82279-DTLSB-01_31_2023-GO95TCH-1^06248001.0369803 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
177299296-69920-DTLSB-02_01_2023-GO95MLD-1^06248001.0369806 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
772921416-60512-DTLSB-01_30_2023-GO95BLTC-1^06248001.0369900 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
792917956-40672-DTLSB-01_30_2023-ABNDEQPM-1^06248001.0369901 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
104333746-81379-DTLSB-02_01_2023-GO95HV-1^06248001.0369903 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
602926537-73949-DETAIL-03_15_2023-GO95HV-1^07114001.0341600 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
988508837-41849-DETAIL-03_15_2023-SVCENTCO-1^07114001.0342201 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
625442707-96849-DETAIL-03_15_2023-GO95MLD-1^07114001.0342203 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
693108937-93949-DETAIL-03_15_2023-GO95HV-1^07114001.0342701 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
804344765-18765-DETAIL-03_15_2023-GO95MLD-1^07114001.0343103 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
206045157-22849-DETAIL-03_15_2023-GUYHINS-1^07114001.0343201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
561170835-39059-DETAIL-03_15_2023-SVCENTCO-1^07114001.0348200 | OTHER | CA-TIER-2 | Distribution | 2023-03-15 | 2026-03-15 | 2
691293780-99239-DETAIL-07_14_2022-GO95MLD-1^07116001.0040200 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
159575610-6459-DETAIL-07_14_2022-GO95MLD-1^07116001.0040402 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
135628220-92359-DETAIL-07_14_2022-GO95MLD-1^07116001.0040500 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
29314580-75249-DETAIL-07_14_2022-GO95MLD-1^07116001.0040505 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
274523380-67249-DETAIL-07_14_2022-SVCWIND-1^07116001.0040506 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
338762130-72359-DETAIL-07_14_2022-SVCWIND-1^07116001.0041500 | OTHER | CA-TIER-2 | Distribution | 2022-07-14 | 2025-07-14 | 2
222254818-94359-DETAIL-05_16_2022-GO95HV-1^07116001.0059000 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
631484698-16249-DETAIL-05_10_2022-GO95MLD-1^07116001.0059301 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
334590248-28459-DETAIL-05_10_2022-GO95TCH-1^07116001.0059340 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
104333746-81379-DTLSB-02_01_2023-GO95TCH-1^06248001.0369903 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
600522756-98511-DTLSB-02_01_2023-GO95MLD-1^06248001.0369906 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
966902071-91173-DTLSB-02_15_2023-GO95MLD-1^06248002.0340401 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
134184641-29370-DTLSB-02_15_2023-GO95MLD-1^06248002.0349500 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
458787028-34079-ADMIN-02_24_2023-POLEREPL-1^06248004.0361142 | POLE | CA-TIER-2 | Distribution | 2023-02-24 | 2024-02-24 | 2
903589821-7273-ADMIN-04_27_2023-POLEREPL-1^06248007.0223102 | POLE | CA-NON-TIER | Distribution | 2023-04-27 | 2026-04-27 | 2
112964341-62159-DETAIL-03_16_2023-ENCHRW-1^07113001.0040502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
112964341-62159-DETAIL-03_16_2023-SVCENTCO-1^07113001.0040502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
815207180-77149-DETAIL-03_16_2023-GO95MLD-1^07113001.0042500 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
836720470-15649-DETAIL-03_16_2023-SVCROAD-1^07113001.0042501 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
687665710-24649-DETAIL-03_16_2023-GO95HV-1^07113001.0042504 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
838431011-55159-DETAIL-03_16_2023-GO95TCH-1^07113001.0042506 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
422029880-16649-DETAIL-03_16_2023-GO95TCH-1^07113001.0042600 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
605801380-1749-DETAIL-03_16_2023-GUYHINS-1^07113001.0042601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
381276728-17728-DETAIL-05_10_2022-GO95TCH-1^07116001.0059342 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
34067098-6249-DETAIL-05_10_2022-ABNDEQPM-1^07116001.0059404 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2027-05-10 | 3
810976490-8539-DETAIL-05_11_2022-GUYHINS-1^07116001.0059601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
323277288-5249-DETAIL-05_11_2022-SVCNEUT-1^07116001.0059800 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
911320218-79139-DETAIL-05_10_2022-GO95MLD-1^07116001.0087400 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
790535268-2659-DETAIL-05_10_2022-GO95HV-1^07116001.0087604 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
191544988-51659-DETAIL-05_10_2022-GO95HV-1^07116001.0088400 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
598342849-30659-DETAIL-04_28_2022-GO95MLD-1^07116001.0090300 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
507479578-82678-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0043503 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
667492620-69249-DETAIL-03_16_2023-GO95MLD-1^07113001.0043505 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
240988908-39908-DETAIL-03_16_2023-GO95MLD-1^07113001.0043507 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
478015170-82649-AUDIT-04_20_2023-SVCDEFLC-1^07113001.0044500 | OTHER | CA-NON-TIER | Distribution | 2023-04-20 | 2026-04-20 | 2
376448404-5159-DETAIL-03_16_2023-GO95MLD-1^07113001.0044502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
930141000-11639-DETAIL-03_16_2023-SVCNEUT-1^07113001.0044600 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
325747100-52649-DETAIL-03_16_2023-GO95MLD-1^07113001.0044601 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
543464189-7189-DETAIL-03_16_2023-GO95CL10-1^07113001.0044906 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
543464189-7189-DETAIL-03_16_2023-GO95MLD-1^07113001.0044906 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
324817739-33749-DETAIL-03_21_2023-SVCROOF-1^07113001.0056503 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
968527623-13049-DETAIL-03_21_2023-GO95MLD-1^07113001.0056504 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
329356333-73749-DETAIL-03_21_2023-GO95BLTC-1^07113001.0056600 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
184699403-92749-DETAIL-03_21_2023-GO95MLD-1^07113001.0057503 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
488732093-51749-DETAIL-03_21_2023-GO95MLD-1^07113001.0058504 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
612842733-92733-DETAIL-03_21_2023-GO95TCH-1^07113001.0058601 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
149165073-60749-DETAIL-03_21_2023-GO95MLD-1^07113001.0059400 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
733260289-76149-DETAIL-04_28_2022-GO95MLD-1^07116001.0090301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
103698331-92559-DETAIL-05_16_2022-GO95MLD-1^07116001.0090600 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
695401181-13959-DETAIL-05_16_2022-GRDRODHI-1^07116001.0090800 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
376564181-56249-DETAIL-05_16_2022-GO95MLD-1^07116001.0090801 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
376564181-56249-DETAIL-05_16_2022-SVCNEUT-1^07116001.0090801 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
635358990-15359-DETAIL-05_16_2022-ABNDEQPM-1^07116001.0090900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
635358990-15359-DETAIL-05_16_2022-GUYSLACK-1^07116001.0090900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
875587959-67949-DETAIL-04_28_2022-GO95HV-1^07116001.0091300 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
833596979-34559-DETAIL-05_10_2022-GO95CL10-1^07116001.0091400 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
833596979-34559-DETAIL-05_10_2022-GO95MLD-1^07116001.0091400 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
80643456-25012-DETAIL-05_10_2022-GO95MLD-1^07116001.0091401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
63708869-12949-ADMIN-10_23_2023-POLEDERP-1^07116001.0091500 | POLE | CA-TIER-2 | Distribution | 2023-10-23 | 2024-10-23 | 2
843143401-76959-DETAIL-05_16_2022-GO95TCH-1^07116001.0091900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
906836221-20559-DETAIL-05_16_2022-GO95HV-1^07116001.0091901 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
906836221-20559-DETAIL-05_16_2022-GO95MLD-1^07116001.0091901 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
124193591-51559-DETAIL-05_16_2022-GO95HV-1^07116001.0091902 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
958707009-11559-DETAIL-05_16_2022-GO95MLD-1^07116001.0091904 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
287487659-92659-DETAIL-04_28_2022-GO95MLD-1^07116001.0092200 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
689934311-89959-DETAIL-04_28_2022-ABNDEQPM-1^07116001.0092400 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
221284461-79449-DETAIL-05_10_2022-SVCNEUT-1^07116001.0092401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
71249331-12559-DETAIL-05_12_2022-GO95HV-1^07116001.0092800 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
795069089-21759-DETAIL-05_10_2022-GO95MLD-1^07116001.0093102 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
901582313-749-DETAIL-03_16_2023-ABNDEQPM-1^07113001.0059502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
79023173-83339-DETAIL-03_16_2023-GO95HV-1^07114001.0205002 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
88577043-28649-DETAIL-03_16_2023-GUYHINS-1^07114001.0206000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
480543533-27249-DETAIL-03_16_2023-GO95HV-1^07114001.0206003 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
662430643-46249-DETAIL-03_16_2023-SVCENTCO-1^07114001.0206100 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
648812223-41259-DETAIL-03_16_2023-SVCDEFLC-1^07114001.0206140 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
648812223-41259-DETAIL-03_16_2023-SVCDEFLC-2^07114001.0206140 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
487099943-38749-DETAIL-03_20_2023-GO95MLD-1^07114001.0206200 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
86369793-60549-DETAIL-03_16_2023-GO95MLD-1^07114001.0208002 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
86369793-60549-DETAIL-03_16_2023-SVCDEFLC-1^07114001.0208002 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
292566233-53339-DETAIL-03_14_2023-GO95HV-1^07114001.0275300 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
292566233-53339-DETAIL-03_14_2023-SVCDEFLC-1^07114001.0275300 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
88859944-53044-DETAIL-03_14_2023-GUYHINS-1^07114001.0275400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
436195543-58549-DETAIL-03_14_2023-GO95MLD-1^07114001.0275401 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
436195543-58549-DETAIL-03_14_2023-GUYHINS-1^07114001.0275401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
44967753-22849-DETAIL-03_14_2023-GO95MLD-1^07114001.0275402 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
44967753-22849-DETAIL-03_14_2023-SVCDEFLC-2^07114001.0275402 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
504011173-53839-DETAIL-03_14_2023-GO95HV-1^07114001.0276301 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
504011173-53839-DETAIL-03_14_2023-GO95MLD-1^07114001.0276301 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
739267393-6649-DETAIL-03_14_2023-GO95MLD-1^07114001.0276302 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
490847043-47339-DETAIL-03_14_2023-GO95MLD-1^07114001.0276401 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
299599463-89139-DETAIL-03_14_2023-GO95MLD-1^07114001.0276402 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
661228079-1549-DETAIL-05_10_2022-GO95MLD-1^07116001.0093104 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
410837759-84339-DETAIL-04_28_2022-GO95MLD-1^07116001.0093201 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
821192669-65059-DETAIL-04_28_2022-GO95MLD-1^07116001.0093202 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
821192669-65059-DETAIL-04_28_2022-SVCENTCO-1^07116001.0093202 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
730114300-21449-DETAIL-04_28_2022-GO95MLD-1^07116001.0093301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
730114300-21449-DETAIL-04_28_2022-GO95TCH-1^07116001.0093301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
695534121-18943-DETAIL-05_12_2022-GO95CL10-1^07116001.0093700 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
695534121-18943-DETAIL-05_12_2022-GO95MLD-1^07116001.0093700 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
695534121-18943-DETAIL-05_12_2022-SVCNEUT-1^07116001.0093700 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
751786131-40331-DETAIL-05_12_2022-GO95TCH-1^07116001.0093800 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
223592381-4481-DETAIL-05_10_2022-GO95MLD-1^07116001.0093801 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
711016360-72759-DETAIL-04_28_2022-GO95HV-1^07116001.0094200 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
865004411-52849-DETAIL-05_16_2022-GO95HV-1^07116001.0094201 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
865004411-52849-DETAIL-05_16_2022-GO95MLD-1^07116001.0094201 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
368084071-20649-DETAIL-04_28_2022-GO95MLD-1^07116001.0094400 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
740926443-96608-DETAIL-04_28_2022-GO95MLD-1^07116001.0094401 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
441286663-18239-DETAIL-03_14_2023-GO95MLD-1^07114001.0276403 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
533872253-93139-DETAIL-03_14_2023-GO95MLD-1^07114001.0276406 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
476905423-68949-DETAIL-03_14_2023-SVCENTCO-1^07114001.0276408 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
350520403-3239-DETAIL-03_14_2023-GO95MLD-1^07114001.0276409 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
690941203-70439-DETAIL-03_14_2023-GO95HV-1^07114001.0276410 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
690941203-70439-DETAIL-03_14_2023-GO95MLD-1^07114001.0276410 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
323678083-22049-DETAIL-03_14_2023-GO95HV-1^07114001.0276502 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
108862643-61849-DETAIL-03_14_2023-GO95HV-1^07114001.0276505 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
368644463-54739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276506 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
368644463-54739-DETAIL-03_14_2023-SVCDEFLC-1^07114001.0276506 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
198857413-20049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277502 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
206702963-71049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277600 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
363564723-90049-DETAIL-03_14_2023-GO95HV-1^07114001.0277602 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
363564723-90049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277602 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
25509503-51049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277605 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
204717793-42049-DETAIL-03_14_2023-GO95HV-1^07114001.0277608 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
984181048-13048-DETAIL-05_10_2022-GO95MLD-1^07116001.0094700 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
611870848-33848-DETAIL-05_12_2022-GO95MLD-1^07116001.0094800 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
733365151-57149-DETAIL-05_10_2022-GO95MLD-1^07116001.0095102 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
891110231-92759-DETAIL-05_10_2022-GUYHINS-1^07116001.0095103 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
355768306-17538-DETAIL-04_28_2022-GO95MLD-1^07116001.0095300 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
976627643-74318-DETAIL-04_28_2022-GO95TCH-1^07116001.0095401 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
951740948-71948-DETAIL-05_10_2022-GO95MLD-1^07116001.0095700 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
948498906-10098-DETAIL-05_09_2022-GO95HV-1^07116001.0096101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
948498906-10098-DETAIL-05_09_2022-GO95MLD-1^07116001.0096101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
668501461-39559-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096201 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
29644606-18078-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096206 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
126883506-31878-DETAIL-05_09_2022-GO95MLD-1^07116001.0096301 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
864265743-51459-DETAIL-04_28_2022-GO95HV-1^07116001.0096304 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
864265743-51459-DETAIL-04_28_2022-GO95MLD-1^07116001.0096304 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
864265743-51459-DETAIL-04_28_2022-SVCNEUT-1^07116001.0096304 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
487176771-3249-DETAIL-05_09_2022-GUYHINS-1^07116001.0097001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
685074806-86898-DETAIL-05_09_2022-GO95HV-1^07116001.0097100 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
892221906-5328-DETAIL-05_09_2022-GO95HV-1^07116001.0097101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
892221906-5328-DETAIL-05_09_2022-GO95MLD-1^07116001.0097101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
193880106-72106-DETAIL-05_09_2022-GUYHINS-1^07116001.0097102 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
872480471-9949-DETAIL-05_09_2022-GO95TCH-1^07116001.0097200 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
308716221-45659-DETAIL-05_09_2022-GO95HV-1^07116001.0097300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
753446206-99248-DETAIL-05_09_2022-CLMBHAZ-1^07116001.0098102 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
447676106-40318-DETAIL-05_09_2022-GO95MLD-1^07116001.0098104 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
299736571-91339-DETAIL-05_09_2022-GO95MLD-1^07116001.0098201 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
946271651-15659-DETAIL-05_09_2022-GO95MLD-1^07116001.0098301 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
773234151-64612-DETAIL-05_02_2022-GO95MLD-1^07116001.0099100 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
236590891-88659-DETAIL-05_09_2022-GO95MLD-1^07116001.0099300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
682407571-46949-DETAIL-05_09_2022-GO95MLD-1^07116001.0099302 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
659504792-55901-DETAIL-05_05_2022-GO95MLD-1^07116001.0100000 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
706160382-66831-DETAIL-05_05_2022-GO95MLD-1^07116001.0100001 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
706160382-66831-DETAIL-05_05_2022-GRDRODHI-1^07116001.0100001 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
199168482-46240-DETAIL-05_02_2022-GO95HV-1^07116001.0100102 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2027-05-02 | 3
125226416-62470-DETAIL-05_05_2022-GO95MLD-1^07116001.0100103 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
995855342-39539-DETAIL-05_09_2022-GO95SVC-1^07116001.0100200 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
204906452-80240-DETAIL-05_05_2022-GO95MLD-1^07116001.0101000 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
99981252-55740-ADMIN-10_24_2023-POLEREPL-1^07116001.0101001 | POLE | CA-TIER-2 | Distribution | 2023-10-24 | 2024-10-24 | 2
602643762-46659-DETAIL-05_02_2022-GO95HV-1^07116001.0101301 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2027-05-02 | 3
602643762-46659-DETAIL-05_02_2022-GO95MLD-1^07116001.0101301 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
754181803-3049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277701 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
756729493-93049-DETAIL-03_14_2023-SVCDEFLC-1^07114001.0278800 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
756729493-93049-DETAIL-03_14_2023-SVCDEFLC-2^07114001.0278800 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
870864943-30249-DETAIL-03_16_2023-GO95HV-1^07114001.0280700 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
915749884-21984-DETAIL-03_14_2023-GO95HV-1^07114001.0281201 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
915749884-21984-DETAIL-03_14_2023-GO95MLD-1^07114001.0281201 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
675380084-88838-DETAIL-03_14_2023-GO95MLD-1^07114001.0281202 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
916964008-15008-DETAIL-03_16_2023-GO95HV-1^07114001.0281600 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
563275008-36008-DETAIL-03_16_2023-SVCENTCO-1^07114001.0281602 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
735701683-47749-DETAIL-03_16_2023-GUYHINS-1^07114001.0281703 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
164092914-83149-DETAIL-03_20_2023-GO95HV-1^07114001.0282302 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
164092914-83149-DETAIL-03_20_2023-SVCRUBLG-1^07114001.0282302 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
693435643-5149-DETAIL-03_16_2023-ENCHRW-1^07114001.0282400 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
371215134-22639-DETAIL-03_20_2023-GO95MLD-1^07114001.0282401 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
179295604-36649-DETAIL-03_16_2023-GO95MLD-1^07114001.0282402 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
837571408-72408-DETAIL-03_16_2023-ABNDEQPM-1^07114001.0282604 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
712699094-149-DETAIL-03_20_2023-CLMBTRE-1^07114001.0283300 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
454528524-24549-DETAIL-03_20_2023-GO95HV-1^07114001.0283402 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
454528524-24549-DETAIL-03_20_2023-GO95MLD-1^07114001.0283402 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
542275154-9049-DETAIL-03_14_2023-GO95MLD-1^07114001.0284204 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
655863244-88839-DETAIL-03_14_2023-GO95MLD-1^07114001.0284205 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
356246814-16049-DETAIL-03_20_2023-GO95MLD-1^07114001.0284302 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
645992814-11849-DETAIL-03_20_2023-GO95HV-1^07114001.0284306 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
729469404-20149-DETAIL-03_20_2023-GO95MLD-1^07114001.0284308 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
306134834-33149-DETAIL-03_20_2023-GO95MLD-1^07114001.0284401 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
777236814-42749-DETAIL-03_20_2023-SVCDEFLC-1^07114001.0285400 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
781798804-60349-DETAIL-03_20_2023-GO95MLD-1^07114001.0285402 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
566515824-81249-DETAIL-03_16_2023-SVCDEFLC-1^07114001.0299800 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
544281055-86449-DETAIL-03_15_2023-GO95CL10-1^07114001.0325100 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
901226358-25259-DETAIL-03_15_2023-GO95MLD-1^07114001.0325200 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
142593612-7680-DETAIL-05_02_2022-GO95MLD-1^07116001.0101400 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
892007492-95692-DETAIL-04_28_2022-GO95MLD-1^07116001.0101501 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
360982752-78700-DETAIL-04_28_2022-GO95MLD-1^07116001.0101502 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
578543302-61481-DETAIL-05_02_2022-GO95MLD-1^07116001.0102100 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
959120492-56643-DETAIL-05_02_2022-GO95MLD-1^07116001.0102101 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
136788154-37713-DETAIL-05_02_2022-GO95MLD-1^07116001.0102200 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
120579602-22760-DETAIL-04_28_2022-GO95BLTC-1^07116001.0102500 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
822521459-64759-DETAIL-05_02_2022-GO95HV-1^07116001.0167902 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2027-05-02 | 3
366393444-44259-DETAIL-03_15_2023-SVCDEFLC-1^07114001.0325306 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
227604895-57449-DETAIL-03_15_2023-GO95MLD-1^07114001.0326001 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
455857225-69749-DETAIL-03_15_2023-GUYNOINS-1^07114001.0326201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
165347305-84449-DETAIL-03_15_2023-GO95MLD-1^07114001.0328001 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
501442724-21949-DETAIL-03_15_2023-GUYHINS-1^07114001.0335801 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
130421324-97449-DETAIL-03_15_2023-GO95MLD-1^07114001.0335900 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
296176934-65049-DETAIL-03_15_2023-CLRTOUCH-1^07114001.0336900 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
64256171-12349-DETAIL-05_02_2022-GO95MLD-1^07116001.0167905 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
64256171-12349-DETAIL-05_02_2022-SVCENTCO-1^07116001.0167905 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
774838371-36239-DETAIL-05_02_2022-GO95TCH-1^07116001.0168904 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
323062961-32159-DETAIL-05_02_2022-GO95TCH-1^07116001.0168905 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
323062961-32159-DETAIL-05_02_2022-SVCNEUT-1^07116001.0168905 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
323062961-32159-DETAIL-05_02_2022-SVCWIND-1^07116001.0168905 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
264728101-17759-DETAIL-05_02_2022-GO95HV-1^07116001.0169900 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2027-05-02 | 3
747930561-4419-DETAIL-07_11_2022-GO95MLD-1^07116007.0012500 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
948611943-49479-DETAIL-07_11_2022-GO95MLD-1^07116007.0016200 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
905630983-87419-DETAIL-07_11_2022-GO95HV-1^07116007.0016401 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
743153391-30719-DETAIL-07_11_2022-GO95HV-1^07116007.0016501 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
786473203-60519-DETAIL-07_11_2022-GUYHINS-1^07116007.0017300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
617962303-19079-DETAIL-07_11_2022-GRDRODHI-1^07116007.0019302 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
292254033-26419-DETAIL-07_11_2022-GO95MLD-1^07116007.0019500 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
169680468-21099-DETAIL-06_20_2022-GO95MLD-1^07116007.0020101 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
263709373-52819-DETAIL-06_20_2022-GO95MLD-1^07116007.0020102 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
217125168-8689-DETAIL-06_20_2022-GO95TCH-1^07116007.0020200 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
781707404-2719-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0020400 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
468023294-80719-DETAIL-06_21_2022-GO95MLD-1^07116007.0020601 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
426786058-86799-DETAIL-06_20_2022-GO95BLTC-1^07116007.0021002 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2027-06-20 | 3
426786058-86799-DETAIL-06_20_2022-GUYHINS-1^07116007.0021002 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
388342383-15189-DETAIL-06_15_2022-GRDRODHI-1^07116007.0021006 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
747283408-23819-DETAIL-06_15_2022-GUYHINS-1^07116007.0021007 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
747283408-23819-DETAIL-06_15_2022-GUYHINS-2^07116007.0021007 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
730905588-98499-DETAIL-06_20_2022-GUYHINS-1^07116007.0021100 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
85272843-90819-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0021405 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
80119334-72719-DETAIL-06_21_2022-GO95TCH-1^07116007.0021501 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
96524324-5719-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0021602 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
16975018-36819-DETAIL-06_20_2022-GO95MLD-1^07116007.0022200 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
858708953-56819-DETAIL-06_21_2022-GO95MLD-1^07116007.0022301 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
860782353-20819-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0022401 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
252549924-54719-DETAIL-06_21_2022-ENCHRW-1^07116007.0022500 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
324983414-17849-DETAIL-03_15_2023-GO95TCH-1^07114001.0338500 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
850691204-5139-AUDIT-03_22_2023-GO95HV-1^07114001.0338501 | OTHER | CA-NON-TIER | Distribution | 2023-03-22 | 2028-03-22 | 3
8523504-18849-DETAIL-03_15_2023-GO95MLD-1^07114001.0339500 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
933778517-3739-DETAIL-03_15_2023-GUYHINS-1^07114001.0340800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
934354827-85949-DETAIL-03_15_2023-GO95MLD-1^07114001.0340801 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
973289557-61849-DETAIL-03_15_2023-SVCENTCO-1^07114001.0342200 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
988508837-41849-DETAIL-03_15_2023-SVCDEFLC-1^07114001.0342201 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
899895947-64949-DETAIL-03_15_2023-GO95HV-1^07114001.0342802 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
252549924-54719-DETAIL-06_21_2022-GO95MLD-1^07116007.0022500 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
656107514-14719-DETAIL-06_21_2022-RISEBKSP-1^07116007.0022504 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
230018423-33789-DETAIL-06_20_2022-GUYHINS-1^07116007.0023003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
394785203-47819-DETAIL-06_21_2022-GO95HV-1^07116007.0023303 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
250192598-31089-DETAIL-06_13_2022-GUYHINS-1^07116007.0024100 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
586832694-67519-DETAIL-06_15_2022-GO95HV-1^07116007.0026300 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
267401193-73320-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0026900 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
162458693-69220-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0026901 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
899895947-64949-DETAIL-03_15_2023-GO95MLD-1^07114001.0342802 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
981736127-62849-DETAIL-03_15_2023-GO95HV-1^07114001.0343200 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
360305677-44849-DETAIL-03_15_2023-GO95HV-1^07114001.0346301 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
275387797-17349-AUDIT-04_20_2023-GO95HV-1^07114001.0347200 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
74172557-65039-DETAIL-03_15_2023-GO95CL10-1^07114001.0347201 | OTHER | CA-TIER-2 | Distribution | 2023-03-15 | 2028-03-15 | 3
913490657-75849-DETAIL-03_15_2023-GO95HV-1^07114001.0347202 | OTHER | CA-TIER-2 | Distribution | 2023-03-15 | 2028-03-15 | 3
4178087-29249-DETAIL-03_15_2023-SVCENTCO-1^07114001.0347203 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
966977177-15849-DETAIL-03_15_2023-GO95MLD-1^07114001.0347301 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
990329933-7519-DETAIL-06_15_2022-GO95MLD-1^07116007.0028300 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
761022953-51519-DETAIL-06_15_2022-GO95MLD-1^07116007.0028401 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
356862443-31189-DETAIL-06_13_2022-GO95MLD-1^07116007.0028404 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
531381153-79079-DETAIL-06_13_2022-GO95HV-1^07116007.0029002 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
395061543-72499-DETAIL-06_13_2022-GO95MLD-1^07116007.0029101 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
368253713-19689-DETAIL-06_13_2022-GO95TCH-1^07116007.0029400 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
368253713-19689-DETAIL-06_13_2022-GUYHINS-1^07116007.0029400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
113302233-26519-DETAIL-06_13_2022-GO95MLD-1^07116007.0029401 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
225131001-43359-DETAIL-07_14_2022-GO95MLD-1^07116001.0040301 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
402931880-83359-DETAIL-07_14_2022-GO95TCH-1^07116001.0040303 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
326822350-74359-DETAIL-07_14_2022-SVCENTCO-1^07116001.0040304 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
138125920-23359-DETAIL-07_14_2022-GO95MLD-1^07116001.0040400 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
881897170-55249-DETAIL-07_14_2022-GO95MLD-1^07116001.0040603 | OTHER | CA-TIER-2 | Distribution | 2022-07-14 | 2025-07-14 | 2
15601260-60359-DETAIL-07_14_2022-GO95MLD-1^07116001.0040701 | OTHER | CA-TIER-2 | Distribution | 2022-07-14 | 2025-07-14 | 2
419236908-89459-DETAIL-05_16_2022-GO95MLD-1^07116001.0059200 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
80552008-559-DETAIL-05_16_2022-GO95MLD-1^07116001.0059300 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
80552008-559-DETAIL-05_16_2022-POLETOP-1^07116001.0059300 | POLE | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
165995738-7459-DETAIL-05_10_2022-SVCRUBLG-1^07116001.0059302 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
428584218-36459-DETAIL-05_10_2022-GUYLOINS-1^07116001.0059401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
563683890-26459-DETAIL-05_10_2022-GO95MLD-1^07116001.0059402 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2027-05-10 | 3
396296100-9059-DETAIL-05_10_2022-GO95MLD-1^07116001.0059403 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
396296100-9059-AUDIT-05_24_2022-GO95HV-1^07116001.0059403 | OTHER | CA-NON-TIER | Distribution | 2022-05-24 | 2027-05-24 | 3
34067098-6249-DETAIL-05_10_2022-GO95MLD-1^07116001.0059404 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
34067098-6249-DETAIL-05_10_2022-GUYHINS-1^07116001.0059404 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
34067098-6249-DETAIL-05_10_2022-GUYNOINS-1^07116001.0059404 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
939888238-56859-DETAIL-05_10_2022-GO95MLD-1^07116001.0059500 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
810976490-8539-DETAIL-05_11_2022-GO95HV-1^07116001.0059601 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
323277288-5249-DETAIL-05_11_2022-GO95MLD-1^07116001.0059800 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
860415749-16349-DETAIL-04_28_2022-SVCDEFLC-1^07116001.0087603 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
318707048-80659-DETAIL-05_10_2022-GO95HV-1^07116001.0089400 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
736714748-20989-DETAIL-06_20_2022-GUYHINS-2^07116007.0038400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
59181148-14679-DETAIL-06_20_2022-GUYHINS-1^07116007.0038401 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
553606328-6179-DETAIL-06_20_2022-GUYHINS-1^07116007.0039204 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
553606328-6179-DETAIL-06_20_2022-GUYHINS-2^07116007.0039204 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
416936208-34219-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0039800 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
149129987-72099-DETAIL-06_23_2022-GO95HV-1^07116007.0102100 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
229797067-78219-DETAIL-06_23_2022-GO95HV-1^07116007.0103000 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
664376557-90270-DETAIL-06_23_2022-GO95HV-1^07116007.0103103 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
565477327-30319-DETAIL-06_23_2022-GO95MLD-1^07116007.0103300 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2025-06-23 | 2
128294337-99219-DETAIL-06_22_2022-GO95HV-1^07116007.0104201 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
932695758-97379-DETAIL-06_22_2022-GO95BLTC-1^07116007.0105102 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
64606358-5319-DETAIL-06_22_2022-GO95HV-1^07116007.0105103 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
267108077-93799-DETAIL-06_22_2022-ABNDEQPM-1^07116007.0108201 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
659729987-91099-DETAIL-07_06_2022-GO95TCH-1^07116007.0108306 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
500489526-61088-DETAIL-06_22_2022-SVCROAD-1^07116007.0110304 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
115031427-87119-DETAIL-06_28_2022-SVCROAD-1^07116007.0110305 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
826029279-25559-DETAIL-05_16_2022-GO95HV-1^07116001.0090400 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
569450461-93559-DETAIL-05_16_2022-GUYNOINS-1^07116001.0090401 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
695401181-13959-DETAIL-05_16_2022-GO95HV-1^07116001.0090800 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
695401181-13959-DETAIL-05_16_2022-GO95MLD-1^07116001.0090800 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
635358990-15359-DETAIL-05_16_2022-GO95TCH-1^07116001.0090900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
913639009-33449-DETAIL-05_16_2022-GO95MLD-1^07116001.0090901 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
971116123-17159-DETAIL-05_16_2022-GO95MLD-1^07116001.0090902 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
841915689-16559-DETAIL-05_10_2022-GO95HV-1^07116001.0091302 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
80643456-25012-DETAIL-05_10_2022-GO95HV-1^07116001.0091401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
843143401-76959-DETAIL-05_16_2022-GO95MLD-1^07116001.0091900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
843143401-76959-DETAIL-05_16_2022-SVCNEUT-1^07116001.0091900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
124193591-51559-DETAIL-05_16_2022-GO95MLD-1^07116001.0091902 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
221284461-79449-DETAIL-05_10_2022-GO95HV-1^07116001.0092401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
221284461-79449-DETAIL-05_10_2022-GO95MLD-1^07116001.0092401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
71249331-12559-DETAIL-05_12_2022-GUYSLACK-1^07116001.0092800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
821192669-65059-DETAIL-04_28_2022-GO95CL10-1^07116001.0093202 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
933519384-71484-DETAIL-06_22_2022-SVCWIND-1^07116007.0110313 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
995467827-86199-DETAIL-06_28_2022-GO95MLD-1^07116007.0110402 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
995467827-86199-DETAIL-06_28_2022-GUYHINS-1^07116007.0110402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
499016747-58119-DETAIL-06_22_2022-GUYHINS-1^07116007.0110403 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
382319037-19119-DETAIL-06_22_2022-GO95MLD-1^07116007.0111300 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
656517867-10589-DETAIL-06_22_2022-GO95TCH-1^07116007.0111302 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
595720357-12099-DETAIL-06_22_2022-GO95MLD-1^07116007.0111305 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
949521709-71699-DETAIL-06_22_2022-GUYHINS-1^07116007.0111406 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
821192669-65059-DETAIL-04_28_2022-GO95TCH-1^07116001.0093202 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
821192669-65059-DETAIL-04_28_2022-GUYHINS-1^07116001.0093202 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
730114300-21449-DETAIL-04_28_2022-GO95HV-1^07116001.0093301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
730114300-21449-DETAIL-04_28_2022-SVCNEUT-1^07116001.0093301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
223592381-4481-DETAIL-05_10_2022-GRDRODHI-1^07116001.0093801 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
868725021-29350-DETAIL-05_12_2022-GO95MLD-1^07116001.0093802 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
853184051-64959-DETAIL-05_12_2022-GO95MLD-1^07116001.0093803 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
237271520-32520-DETAIL-05_10_2022-GO95MLD-1^07116001.0093805 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
998635078-67019-DETAIL-06_28_2022-GO95MLD-1^07116007.0111507 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
933147848-76019-DETAIL-06_16_2022-GUYHINS-1^07116007.0112505 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
933147848-76019-DETAIL-06_16_2022-GUYHINS-2^07116007.0112505 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
606146598-96019-DETAIL-06_15_2022-GO95MLD-1^07116007.0112506 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
284005148-47479-DETAIL-06_15_2022-GO95MLD-1^07116007.0112507 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
284005148-47479-DETAIL-06_15_2022-SVCROOF-1^07116007.0112507 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
632298508-39019-DETAIL-06_15_2022-GO95MLD-1^07116007.0112603 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
446262259-97789-DETAIL-06_15_2022-GO95TCH-1^07116007.0112606 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
462760441-14959-DETAIL-05_10_2022-GO95MLD-1^07116001.0093900 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
462760441-14959-DETAIL-05_10_2022-GUYSLACK-1^07116001.0093900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
462760441-14959-DETAIL-05_10_2022-SVCWIND-1^07116001.0093900 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
758059570-3759-DETAIL-04_28_2022-GO95MLD-1^07116001.0094100 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
758059570-3759-DETAIL-04_28_2022-SVCENTCO-1^07116001.0094100 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
182901370-76349-DETAIL-05_10_2022-GO95HV-1^07116001.0094102 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
715291101-74549-DETAIL-05_10_2022-GO95HV-1^07116001.0094104 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
865004411-52849-DETAIL-05_16_2022-GUYHINS-1^07116001.0094201 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
409291071-86559-DETAIL-04_28_2022-GO95MLD-1^07116001.0094402 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
409291071-86559-DETAIL-04_28_2022-GO95TCH-1^07116001.0094402 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
611870848-33848-DETAIL-05_12_2022-GO95HV-1^07116001.0094800 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
460327208-47208-DETAIL-05_10_2022-GO95MLD-1^07116001.0094900 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
18885208-56208-DETAIL-05_10_2022-GO95HV-1^07116001.0094901 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2027-05-10 | 3
18885208-56208-DETAIL-05_10_2022-GO95MLD-1^07116001.0094901 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
891110231-92759-DETAIL-05_10_2022-CLMBHAZ-1^07116001.0095103 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
891110231-92759-DETAIL-05_10_2022-GO95TCH-1^07116001.0095103 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
897653919-16389-DETAIL-06_15_2022-GO95MLD-1^07116007.0112804 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
521868119-64689-DETAIL-06_15_2022-GO95MLD-1^07116007.0112808 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
601984395-86395-DETAIL-06_14_2022-GO95MLD-1^07116007.0113510 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
233390089-43119-DETAIL-06_16_2022-SVCROAD-2^07116007.0113512 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
276743188-55119-DETAIL-06_14_2022-GO95MLD-1^07116007.0113517 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
783342029-20119-DETAIL-06_16_2022-SVCROAD-1^07116007.0113603 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
790234399-74019-DETAIL-06_14_2022-GO95MLD-1^07116007.0113609 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
287596228-43919-DETAIL-06_14_2022-GO95MLD-1^07116007.0113804 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
593305869-72119-DETAIL-06_13_2022-SVCROAD-1^07116007.0114508 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
266705109-119-DETAIL-06_16_2022-SVCWIND-1^07116007.0114600 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
44572049-1019-AUDIT-08_16_2022-GO95MLD-1^07116007.0114700 | OTHER | CA-TIER-2 | Distribution | 2022-08-16 | 2025-08-16 | 2
261897548-5919-DETAIL-06_08_2022-GO95MLD-1^07116007.0114902 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
489617661-16761-DETAIL-06_08_2022-SVCROAD-1^07116007.0114920 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
660111161-47699-DETAIL-06_14_2022-ABNDEQPM-1^07116007.0115300 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2027-06-14 | 3
660111161-47699-DETAIL-06_14_2022-GO95MLD-1^07116007.0115300 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
905798214-85619-DETAIL-06_08_2022-GO95MLD-1^07116007.0115703 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
847241743-15338-DETAIL-04_28_2022-GO95MLD-1^07116001.0095301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
976627643-74318-DETAIL-04_28_2022-GO95MLD-1^07116001.0095401 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
285997948-29948-DETAIL-05_10_2022-GO95MLD-1^07116001.0095702 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
428328301-17859-DETAIL-05_09_2022-GO95TCH-1^07116001.0096200 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
409461706-95768-ADMIN-10_24_2023-POLEREPL-1^07116001.0096202 | POLE | CA-TIER-2 | Distribution | 2023-10-24 | 2024-10-24 | 2
545238706-5798-DETAIL-05_09_2022-GO95HV-1^07116001.0096203 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
29644606-18078-DETAIL-05_09_2022-GO95MLD-1^07116001.0096206 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
315901943-16198-DETAIL-05_09_2022-GO95MLD-1^07116001.0096207 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
315901943-16198-DETAIL-05_09_2022-SVCROAD-1^07116001.0096207 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
734857843-51468-DETAIL-05_09_2022-GO95MLD-1^07116001.0096300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
734857843-51468-DETAIL-05_09_2022-SVCROAD-1^07116001.0096300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
539603843-36058-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096302 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
244581331-32459-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096400 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
487176771-3249-DETAIL-05_09_2022-GO95GUYP-1^07116001.0097001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
487176771-3249-DETAIL-05_09_2022-GO95HV-1^07116001.0097001 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
620923184-99789-DETAIL-06_08_2022-SVCROAD-2^07116007.0116701 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
974641734-8199-DETAIL-06_13_2022-ABNDEQPM-1^07116007.0116900 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
905672634-36619-DETAIL-06_13_2022-ABNDEQPM-1^07116007.0117901 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
443134139-29399-DETAIL-07_06_2022-GO95MLD-1^07116007.0141402 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
496455339-97199-DETAIL-07_06_2022-GO95MLD-1^07116007.0141602 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
150237179-32619-DETAIL-07_06_2022-ENCHRW-1^07116007.0142300 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
715984949-42619-DETAIL-07_06_2022-GO95MLD-1^07116007.0142302 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
108045679-51619-DETAIL-07_06_2022-GO95MLD-1^07116007.0142403 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
487176771-3249-DETAIL-05_09_2022-GO95MLD-1^07116001.0097001 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
193880106-72106-DETAIL-05_09_2022-GO95MLD-1^07116001.0097102 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
193880106-72106-DETAIL-05_09_2022-GRDRODHI-1^07116001.0097102 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
308716221-45659-DETAIL-05_09_2022-GO95MLD-1^07116001.0097300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
753446206-99248-DETAIL-05_09_2022-GO95MLD-1^07116001.0098102 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
877951206-95118-DETAIL-05_09_2022-GO95MLD-1^07116001.0098105 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
585401406-92898-DETAIL-05_09_2022-GO95MLD-1^07116001.0098202 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
702919099-84659-DETAIL-05_09_2022-GO95HV-1^07116001.0098302 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
975451008-84419-DETAIL-06_23_2022-GO95HV-1^07116007.0152503 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
236226708-81589-DETAIL-06_28_2022-GO95MLD-1^07116007.0155400 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
143405978-72419-DETAIL-06_28_2022-CLMBHAZ-1^07116007.0155401 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
143405978-72419-DETAIL-06_28_2022-GO95TCH-1^07116007.0155401 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
160101878-82789-DETAIL-06_28_2022-GO95MLD-1^07116007.0155404 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
473440088-71419-DETAIL-06_28_2022-GUYHINS-2^07116007.0155405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
331919428-91419-DETAIL-06_28_2022-GO95TCH-1^07116007.0155407 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
224184963-57099-DETAIL-06_27_2022-GO95MLD-1^07116007.0155501 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
224184963-57099-DETAIL-06_27_2022-GRDRODHI-1^07116007.0155501 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
944506283-65519-DETAIL-06_27_2022-GO95MLD-1^07116007.0155502 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
569786153-78419-DETAIL-06_27_2022-GO95MLD-1^07116007.0155506 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
898787533-93689-DETAIL-06_27_2022-GO95HV-1^07116007.0155507 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
898787533-93689-DETAIL-06_27_2022-GO95MLD-1^07116007.0155507 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
959158794-20894-DETAIL-06_27_2022-SVCENTCO-1^07116007.0155511 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
460721844-48419-AUDIT-07_25_2022-GO95HV-1^07116007.0155601 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2027-07-25 | 3
548740873-94989-DETAIL-06_27_2022-GO95MLD-1^07116007.0155701 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
6395306-46788-DETAIL-05_09_2022-GO95HV-1^07116001.0099101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
6395306-46788-DETAIL-05_09_2022-GO95MLD-1^07116001.0099101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
263734101-89659-DETAIL-05_09_2022-GO95MLD-1^07116001.0099102 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
345737782-90790-DETAIL-05_02_2022-GO95MLD-1^07116001.0100101 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
995855342-39539-DETAIL-05_09_2022-GO95MLD-1^07116001.0100200 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
3193652-11309-DETAIL-05_02_2022-GO95MLD-1^07116001.0101300 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
721706780-95078-DETAIL-05_02_2022-GO95MLD-1^07116001.0102000 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
136788154-37713-DETAIL-05_02_2022-SVCROAD-1^07116001.0102200 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
120579602-22760-DETAIL-04_28_2022-GO95HV-1^07116001.0102500 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
376619792-58920-DETAIL-04_28_2022-GO95MLD-1^07116001.0102505 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
981780420-74903-DETAIL-05_02_2022-GO95MLD-1^07116001.0150800 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
737308720-95821-DETAIL-05_02_2022-GO95HV-1^07116001.0151800 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2027-05-02 | 3
737308720-95821-DETAIL-05_02_2022-GO95MLD-1^07116001.0151800 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
301375192-81940-DETAIL-05_02_2022-GO95HV-1^07116001.0152900 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2027-05-02 | 3
405883559-74059-DETAIL-05_02_2022-GO95MLD-1^07116001.0166901 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
597935359-84759-DETAIL-05_02_2022-GO95HV-1^07116001.0167903 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2027-05-02 | 3
296872141-91159-DETAIL-05_02_2022-GUYHINS-1^07116001.0167904 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
296872141-91159-DETAIL-05_02_2022-SVCWIND-1^07116001.0167904 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
64256171-12349-DETAIL-05_02_2022-GUYHINS-1^07116001.0167905 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
646120280-75759-DETAIL-05_02_2022-GO95TCH-1^07116001.0168903 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
774838371-36239-DETAIL-05_02_2022-GO95MLD-1^07116001.0168904 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
323062961-32159-DETAIL-05_02_2022-GO95MLD-1^07116001.0168905 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
578087721-52159-DETAIL-05_02_2022-GO95MLD-1^07116001.0169802 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
693629611-38299-DETAIL-07_11_2022-GUYHINS-1^07116007.0010500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
963297433-38599-DETAIL-06_27_2022-GO95HV-1^07116007.0155802 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
963297433-38599-DETAIL-06_27_2022-GO95MLD-1^07116007.0155802 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
281660693-59419-DETAIL-06_27_2022-GO95TCH-1^07116007.0156501 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
637538083-30399-DETAIL-06_27_2022-GO95HV-1^07116007.0156602 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
937723093-99689-DETAIL-06_27_2022-GO95MLD-1^07116007.0156703 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
763029558-95419-DETAIL-06_28_2022-GO95MLD-1^07116007.0157401 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
752315764-70519-DETAIL-06_27_2022-GO95MLD-1^07116007.0157502 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
595093764-73469-DETAIL-06_27_2022-GO95HV-1^07116007.0157504 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
735977388-48388-DETAIL-07_11_2022-GO95MLD-1^07116007.0010600 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
814108803-89803-DETAIL-07_11_2022-GO95HV-1^07116007.0014500 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
276840281-54419-DETAIL-07_11_2022-GO95MLD-1^07116007.0014600 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
743153391-30719-DETAIL-07_11_2022-ABNDEQPM-1^07116007.0016501 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
747513-49419-DETAIL-07_11_2022-GO95HV-1^07116007.0017101 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
786473203-60519-DETAIL-07_11_2022-GUYHINS-2^07116007.0017300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
617962303-19079-DETAIL-07_11_2022-GO95HV-1^07116007.0019302 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
617962303-19079-DETAIL-07_11_2022-GO95MLD-1^07116007.0019302 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
681656632-50409-DETAIL-07_11_2022-GO95TCH-1^07116007.0019403 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
181876578-96699-DETAIL-06_20_2022-GO95MLD-1^07116007.0020201 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
181876578-96699-DETAIL-06_20_2022-SVCRUBLG-1^07116007.0020201 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
302773324-51719-DETAIL-06_21_2022-GO95MLD-1^07116007.0020502 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
388342383-15189-DETAIL-06_15_2022-GO95MLD-1^07116007.0021006 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
992360487-62819-DETAIL-06_20_2022-GO95MLD-1^07116007.0021101 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2027-06-20 | 3
492984804-18730-DETAIL-06_21_2022-GO95MLD-1^07116007.0021601 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
725767477-9289-DETAIL-06_15_2022-GUYHINS-1^07116007.0022003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
143844904-86589-DETAIL-06_28_2022-GO95MLD-1^07116007.0158500 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
143844904-86589-DETAIL-06_28_2022-SVCROAD-1^07116007.0158500 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
526859278-56419-DETAIL-06_27_2022-GO95MLD-1^07116007.0159401 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
809500114-87419-DETAIL-06_28_2022-SVCROOF-1^07116007.0159500 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
343441356-95519-DETAIL-07_06_2022-GO95HV-1^07116007.0166202 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
319854728-30640-DETAIL-07_06_2022-GO95STUB-1^07116007.0219602 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
714810865-23468-DETAIL-07_11_2022-GO95MLD-1^07116008.0060000 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
561053634-3551-DETAIL-07_10_2023-GO95HV-1^07117001.0246040 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2028-07-10 | 3
316487373-819-DETAIL-06_21_2022-GO95MLD-1^07116007.0022402 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
176118604-76730-DETAIL-06_21_2022-GO95MLD-1^07116007.0022505 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
315315193-39819-DETAIL-06_20_2022-GO95MLD-1^07116007.0023102 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
209680538-86819-DETAIL-06_21_2022-GO95HV-1^07116007.0023401 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
782756214-36719-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0023601 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
250192598-31089-DETAIL-06_13_2022-GO95MLD-1^07116007.0024100 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
397364924-58719-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0024900 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
887430243-89519-DETAIL-06_13_2022-GUYNOINS-1^07116007.0025002 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
561053634-3551-DETAIL-07_10_2023-GO95MLD-1^07117001.0246040 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
198454184-830-DETAIL-07_10_2023-GO95CL10-1^07117001.0246102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2028-07-10 | 3
198454184-830-DETAIL-07_10_2023-GO95TCH-1^07117001.0246102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
129695164-25170-DETAIL-07_10_2023-GO95MLD-1^07117001.0246104 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
903984054-10742-DETAIL-07_10_2023-GO95HV-1^07117001.0246105 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2028-07-10 | 3
108732244-12649-DETAIL-07_10_2023-GO95MLD-1^07117001.0247002 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
922762764-67922-DETAIL-07_10_2023-GO95MLD-1^07117001.0247101 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
447153654-57401-DETAIL-07_10_2023-GO95MLD-1^07117001.0247102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
447153654-57401-DETAIL-07_10_2023-GO95TCH-1^07117001.0247102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
308817255-86249-DETAIL-05_05_2022-SVCROAD-1^07117001.0290101 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
983785578-57199-DETAIL-05_04_2022-GO95CL10-1^07117001.0300801 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2027-05-04 | 3
983785578-57199-DETAIL-05_04_2022-GO95MLD-1^07117001.0300801 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
983785578-57199-DETAIL-05_04_2022-SVCNEUT-1^07117001.0300801 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
150020718-92373-DETAIL-05_04_2022-GO95MLD-1^07117001.0300902 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
128297098-11873-DETAIL-05_04_2022-GO95MLD-1^07117001.0300903 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
128297098-11873-DETAIL-05_04_2022-GRDRODHI-1^07117001.0300903 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
406221113-22089-DETAIL-06_13_2022-GUYHINS-1^07116007.0025005 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
702199403-97379-DETAIL-06_15_2022-GO95BLTC-1^07116007.0027401 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
702199403-97379-DETAIL-06_15_2022-GO95MLD-1^07116007.0027401 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
702199403-97379-DETAIL-06_15_2022-GRDRODHI-1^07116007.0027401 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
852044973-54499-DETAIL-06_15_2022-GO95HV-1^07116007.0028500 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
898433773-6779-DETAIL-06_13_2022-GO95MLD-1^07116007.0029000 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
395061543-72499-DETAIL-06_13_2022-GRDRODHI-1^07116007.0029101 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
632155043-71519-DETAIL-06_22_2022-GO95MLD-1^07116007.0029502 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
206892463-58179-DETAIL-06_15_2022-GO95BLTC-1^07116007.0029503 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
206892463-58179-DETAIL-06_15_2022-GO95MLD-1^07116007.0029503 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
736714748-20989-DETAIL-06_20_2022-GUYHINS-1^07116007.0038400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
59181148-14679-DETAIL-06_20_2022-GO95MLD-1^07116007.0038401 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
25172008-9689-DETAIL-06_20_2022-GUYHINS-1^07116007.0039101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
454772428-74599-DETAIL-06_20_2022-GO95MLD-1^07116007.0039205 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
149129987-72099-DETAIL-06_23_2022-ABNDEQPM-1^07116007.0102100 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
149129987-72099-DETAIL-06_23_2022-GO95MLD-1^07116007.0102100 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2025-06-23 | 2
660777447-48219-DETAIL-06_23_2022-GO95HV-1^07116007.0103001 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
461510757-19219-DETAIL-06_23_2022-ABNDEQPM-1^07116007.0103101 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
7974427-34899-DETAIL-06_22_2022-ABNDEQPM-1^07116007.0103200 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
277117017-87209-DETAIL-06_23_2022-ABNDEQPM-1^07116007.0103201 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
669960737-699-DETAIL-06_22_2022-GO95MLD-1^07116007.0104400 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
387448088-84319-DETAIL-06_22_2022-GO95MLD-1^07116007.0106200 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
800249238-71370-DETAIL-06_22_2022-SVCROAD-1^07116007.0108240 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
998928287-82319-DETAIL-07_06_2022-GO95MLD-1^07116007.0108305 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
621812594-29431-DETAIL-05_04_2022-GUYHINS-1^07117001.0301701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
60598668-97873-DETAIL-05_12_2022-GO95MLD-1^07117001.0301902 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
245710388-14249-DETAIL-05_16_2022-GO95MLD-1^07117001.0302100 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
687258888-93249-DETAIL-05_16_2022-GO95MLD-1^07117001.0302200 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
687258888-93249-DETAIL-05_16_2022-SVCNEUT-1^07117001.0302200 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
527386415-79859-DETAIL-05_12_2022-GO95HV-1^07117001.0302701 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
811660144-90459-DETAIL-05_12_2022-GO95MLD-1^07117001.0302801 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
609218778-72249-DETAIL-05_12_2022-SVCNEUT-1^07117001.0302804 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
14823358-38659-DETAIL-05_16_2022-GO95HV-1^07117001.0303300 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
274021598-23249-DETAIL-05_12_2022-GO95MLD-1^07117001.0303702 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
41816358-22459-DETAIL-05_16_2022-GUYHINS-1^07117001.0304400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
32512905-75159-DETAIL-05_05_2022-GO95MLD-1^07117001.0304700 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
587537456-39359-DETAIL-05_16_2022-GO95HV-1^07117001.0305600 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
86462414-34688-DETAIL-05_16_2022-GO95MLD-1^07117001.0306501 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
86462414-34688-DETAIL-05_16_2022-GRDRODHI-1^07117001.0306501 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
292542528-20459-DETAIL-05_16_2022-GO95MLD-1^07117001.0306600 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
519185525-11459-DETAIL-05_16_2022-GO95MLD-1^07117001.0307200 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
798792606-17439-DETAIL-05_05_2022-GO95HV-1^07117001.0308000 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2027-05-05 | 3
798792606-17439-DETAIL-05_05_2022-SVCENTCO-1^07117001.0308000 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
933549448-22259-DETAIL-05_05_2022-GO95HV-1^07117001.0308001 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2027-05-05 | 3
933549448-22259-DETAIL-05_05_2022-GO95MLD-1^07117001.0308001 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
933549448-22259-DETAIL-05_05_2022-SVCWIND-1^07117001.0308001 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
682536725-22159-DETAIL-05_05_2022-GO95MLD-1^07117001.0308006 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
682536725-22159-DETAIL-05_05_2022-SVCENTCO-1^07117001.0308006 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
875748978-14319-DETAIL-06_28_2022-GO95MLD-1^07116007.0109208 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
605535967-48319-DETAIL-06_28_2022-GO95MLD-1^07116007.0109209 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
53949207-1219-DETAIL-06_28_2022-GO95MLD-1^07116007.0110201 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
630371367-22200-DETAIL-06_22_2022-SVCROAD-1^07116007.0110203 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
699717637-17119-DETAIL-06_28_2022-GO95MLD-1^07116007.0110306 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
627005426-66368-DETAIL-06_22_2022-GO95MLD-1^07116007.0110308 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
341254747-7799-DETAIL-06_22_2022-GO95TCH-1^07116007.0110309 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
645966678-73119-DETAIL-06_28_2022-GO95MLD-1^07116007.0110400 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
499016747-58119-DETAIL-06_22_2022-GO95TCH-1^07116007.0110403 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
499016747-58119-AUDIT-06_29_2022-GO95MLD-1^07116007.0110403 | OTHER | CA-TIER-2 | Distribution | 2022-06-29 | 2025-06-29 | 2
656517867-10589-DETAIL-06_22_2022-GO95MLD-1^07116007.0111302 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
605289267-38379-DETAIL-06_22_2022-GO95TCH-1^07116007.0111304 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
323065717-99119-DETAIL-06_22_2022-GO95TCH-1^07116007.0111306 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
296703777-59119-DETAIL-06_22_2022-GO95MLD-1^07116007.0111401 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
296703777-59119-DETAIL-06_22_2022-GUYHINS-1^07116007.0111401 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
132451919-58019-DETAIL-06_28_2022-GO95TCH-1^07116007.0111503 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
998635078-67019-DETAIL-06_28_2022-GO95TCH-1^07116007.0111507 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
490818864-42379-DETAIL-06_20_2022-GUYHINS-1^07116007.0111801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
415193608-46919-DETAIL-06_20_2022-SVCENTCO-1^07116007.0111901 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
673623758-65499-DETAIL-06_15_2022-ABNDEQPM-1^07116007.0111905 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
673623758-65499-DETAIL-06_15_2022-GUYHINS-1^07116007.0111905 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
441936257-22879-DETAIL-06_14_2022-GO95MLD-1^07116007.0112300 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
827566668-83079-DETAIL-06_28_2022-GO95MLD-1^07116007.0112502 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
632298508-39019-DETAIL-06_15_2022-SVCWIND-1^07116007.0112603 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
170883105-2059-DETAIL-05_05_2022-GO95MLD-1^07117001.0308007 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
170883105-2059-DETAIL-05_05_2022-SVCNEUT-1^07117001.0308007 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
62387068-26959-DETAIL-05_05_2022-GO95MLD-1^07117001.0308300 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
72174104-67659-DETAIL-05_16_2022-GUYHINS-1^07117001.0313700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
978308124-90559-DETAIL-05_16_2022-ABNDEQPM-1^07117001.0314601 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
58804924-80959-DETAIL-05_16_2022-GO95MLD-1^07117001.0315501 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
931839514-93259-DETAIL-05_16_2022-GO95TCH-1^07117001.0316800 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
188692054-67759-DETAIL-05_17_2022-GUYSLACK-1^07117001.0317500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
507596974-13259-DETAIL-05_16_2022-GUYNOINS-1^07117001.0317941 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
432227390-24159-DETAIL-05_17_2022-CLRTOUCH-1^07117001.0319301 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
391722834-41739-DETAIL-05_17_2022-GO95MLD-1^07117001.0319501 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
66718224-66259-DETAIL-05_17_2022-GO95MLD-1^07117001.0319502 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
19719090-14949-DETAIL-05_11_2022-CLMBHAZ-1^07117001.0320403 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
996638334-46259-DETAIL-05_17_2022-ABNDEQPM-1^07117001.0320500 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
996638334-46259-DETAIL-05_17_2022-GO95TCH-1^07117001.0320500 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
124504563-85359-DETAIL-05_17_2022-GUYHINS-1^07117001.0321201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
552811573-25359-DETAIL-05_11_2022-GO95HV-1^07117001.0321340 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2027-05-11 | 3
552811573-25359-DETAIL-05_11_2022-GO95MLD-1^07117001.0321340 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2027-05-11 | 3
499339703-9149-DETAIL-05_11_2022-GO95HV-1^07117001.0321401 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
731606903-93939-DETAIL-05_11_2022-GO95MLD-1^07117001.0321404 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
731606903-93939-DETAIL-05_11_2022-SVCNEUT-1^07117001.0321404 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
673286673-46359-DETAIL-05_11_2022-GUYHINS-1^07117001.0322202 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
116687883-37259-DETAIL-05_11_2022-GO95MLD-1^07117001.0323102 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2027-05-11 | 3
632915828-67259-DETAIL-03_08_2023-GO95MLD-1^07117002.0193200 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
432394158-78979-DETAIL-06_15_2022-GO95BLTC-1^07116007.0112705 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
432394158-78979-DETAIL-06_15_2022-GUYHINS-1^07116007.0112705 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
543976949-76919-DETAIL-06_15_2022-GO95TCH-1^07116007.0112801 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
862266899-10019-DETAIL-06_15_2022-GUYHINS-1^07116007.0112805 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
862266899-10019-DETAIL-06_15_2022-GUYHINS-2^07116007.0112805 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
208108758-33099-DETAIL-06_15_2022-GO95MLD-1^07116007.0112807 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
521868119-64689-DETAIL-06_15_2022-GO95TCH-1^07116007.0112808 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
521868119-64689-DETAIL-06_15_2022-GRDRODHI-1^07116007.0112808 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
521868119-64689-DETAIL-06_15_2022-GRDRODHI-2^07116007.0112808 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
29900468-2799-DETAIL-06_15_2022-GO95TCH-1^07116007.0112809 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
913757288-13799-DETAIL-06_15_2022-GO95TCH-1^07116007.0112903 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
913757288-13799-DETAIL-06_15_2022-GUYHINS-1^07116007.0112903 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
48132797-42219-DETAIL-06_14_2022-SVCROAD-1^07116007.0113301 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
454363627-34199-DETAIL-06_14_2022-GUYHINS-1^07116007.0113402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
624655976-43686-DETAIL-06_14_2022-GO95TCH-1^07116007.0113421 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
233390089-43119-DETAIL-06_16_2022-GO95MLD-1^07116007.0113512 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
233390089-43119-DETAIL-06_16_2022-SVCROAD-1^07116007.0113512 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
844394659-34019-DETAIL-06_14_2022-GO95TCH-1^07116007.0113702 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
844394659-34019-DETAIL-06_14_2022-SVCWIND-1^07116007.0113702 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
819977918-73919-DETAIL-06_08_2022-SVCROAD-1^07116007.0113903 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
964535063-65063-DETAIL-06_13_2022-GO95HV-1^07116007.0114720 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
79657038-64489-DETAIL-06_13_2022-GUYHINS-1^07116007.0114812 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
733121484-94619-DETAIL-06_08_2022-GUYNOINS-1^07116007.0115707 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
101114404-62619-DETAIL-06_08_2022-GO95MLD-1^07116007.0115802 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
479028418-99653-DETAIL-03_08_2023-GO95HV-1^07117002.0193201 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
977863555-5133-DETAIL-03_06_2023-GO95MLD-1^07117002.0194001 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
799279195-833-DETAIL-03_01_2023-SVCENTCO-1^07117002.0195003 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
985132668-93113-DETAIL-03_01_2023-GO95MLD-1^07117002.0195100 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
793354535-92733-DETAIL-03_01_2023-GO95MLD-1^07117002.0195102 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
250939488-41863-DETAIL-03_01_2023-GO95MLD-1^07117002.0195200 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
528908345-69933-DETAIL-03_01_2023-GO95MLD-1^07117002.0195203 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
44096745-55733-DETAIL-03_01_2023-GO95MLD-1^07117002.0195207 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
44096745-55733-DETAIL-03_01_2023-GUYHINS-1^07117002.0195207 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
44096745-55733-DETAIL-03_01_2023-SVCROAD-1^07117002.0195207 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
675160235-62733-DETAIL-03_01_2023-GO95MLD-1^07117002.0195208 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
395532565-65733-DETAIL-03_01_2023-GO95MLD-1^07117002.0196202 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
956857275-69949-DETAIL-03_01_2023-GO95MLD-1^07117002.0196203 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
103871565-76549-DETAIL-03_01_2023-GO95MLD-1^07117002.0196204 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
508115445-96249-DETAIL-03_01_2023-SVCROAD-1^07117002.0196207 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
215147838-14391-DETAIL-03_01_2023-SVCDEFLC-1^07117002.0196240 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
10776604-14619-DETAIL-06_08_2022-GO95MLD-1^07116007.0115806 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
10776604-14619-DETAIL-06_08_2022-GUYHINS-1^07116007.0115806 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
323092764-61619-DETAIL-06_08_2022-ABNDEQPM-1^07116007.0115813 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2027-06-08 | 3
620923184-99789-DETAIL-06_08_2022-GUYHINS-1^07116007.0116701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
620923184-99789-DETAIL-06_08_2022-SVCROAD-1^07116007.0116701 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
615856614-82619-DETAIL-06_08_2022-GO95TCH-1^07116007.0116802 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
848991734-33499-DETAIL-06_13_2022-ABNDEQPM-1^07116007.0117900 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
637237221-4899-DETAIL-07_06_2022-GO95MLD-1^07116007.0140400 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
13160985-84233-DETAIL-03_06_2023-SVCENTCO-1^07117002.0196300 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
357617035-74533-DETAIL-03_01_2023-GO95MLD-1^07117002.0197206 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
895347715-62833-DETAIL-03_01_2023-GO95MLD-1^07117002.0197300 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
895347715-62833-DETAIL-03_01_2023-RISESTRP-1^07117002.0197300 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
213072049-40059-DETAIL-03_01_2023-GO95MLD-1^07117002.0197303 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
213072049-40059-DETAIL-03_01_2023-GO95TCH-1^07117002.0197303 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
136285215-42833-DETAIL-03_08_2023-GO95MLD-1^07117002.0198000 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
136285215-42833-DETAIL-03_08_2023-GO95TCH-1^07117002.0198000 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
637237221-4899-DETAIL-07_06_2022-GRDRODHI-1^07116007.0140400 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
228459229-90619-DETAIL-07_06_2022-GO95HV-1^07116007.0140501 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
126760959-41619-DETAIL-07_06_2022-GO95HV-1^07116007.0141400 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
715984949-42619-DETAIL-07_06_2022-GRDRODHI-1^07116007.0142302 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
992098969-12619-DETAIL-07_06_2022-GO95TCH-1^07116007.0142402 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
108045679-51619-DETAIL-07_06_2022-GO95TCH-1^07116007.0142403 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
565238208-92889-DETAIL-06_23_2022-GO95MLD-1^07116007.0152401 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2025-06-23 | 2
842035118-48089-DETAIL-06_23_2022-ABNDEQPM-1^07116007.0153500 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
888357115-51733-DETAIL-03_08_2023-GO95MLD-1^07117002.0198140 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
874885655-15733-DETAIL-03_01_2023-GO95MLD-1^07117002.0198303 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
618004741-49973-DETAIL-03_02_2023-GO95MLD-1^07117002.0200200 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
230266141-48373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
838892251-14573-DETAIL-03_02_2023-SVCDEFLC-1^07117002.0200301 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
838892251-14573-DETAIL-03_02_2023-SVCENTCO-1^07117002.0200301 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
976650441-9373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200302 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
649420451-61773-DETAIL-03_02_2023-GO95MLD-1^07117002.0200304 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
776728461-39208-DETAIL-06_23_2022-GO95MLD-1^07116007.0153700 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2025-06-23 | 2
339808198-73789-DETAIL-06_28_2022-GO95MLD-1^07116007.0155402 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
473440088-71419-DETAIL-06_28_2022-GUYHINS-1^07116007.0155405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
917956228-30489-DETAIL-06_28_2022-GO95MLD-1^07116007.0155406 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
187948673-25519-DETAIL-06_27_2022-GO95MLD-1^07116007.0155500 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
743423881-45519-DETAIL-06_27_2022-GO95HV-1^07116007.0155509 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
460721844-48419-DETAIL-06_27_2022-GO95MLD-1^07116007.0155601 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
367737963-29248-DETAIL-06_27_2022-ABNDEQPM-1^07116007.0155640 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
796032341-79419-DETAIL-06_27_2022-GO95HV-1^07116007.0156502 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
850742823-10519-DETAIL-06_27_2022-GO95MLD-1^07116007.0156504 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
637538083-30399-DETAIL-06_27_2022-GO95MLD-1^07116007.0156602 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
118664243-37599-DETAIL-06_27_2022-GO95MLD-1^07116007.0156700 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
759030394-55179-DETAIL-06_27_2022-GO95MLD-1^07116007.0156901 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
991677671-19310-DETAIL-06_27_2022-ABNDEQPM-1^07116007.0156904 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
474479468-36419-DETAIL-06_28_2022-GO95MLD-1^07116007.0157400 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
29961994-33994-DETAIL-06_28_2022-ENCHRW-1^07116007.0157404 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
215447704-76419-DETAIL-06_27_2022-GO95MLD-1^07116007.0157500 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
866162751-40519-DETAIL-06_27_2022-GO95HV-1^07116007.0157506 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
866174643-10099-DETAIL-06_27_2022-GO95MLD-1^07116007.0157902 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
124309223-96419-DETAIL-06_27_2022-GO95MLD-1^07116007.0158501 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
809500114-87419-DETAIL-06_28_2022-GO95MLD-1^07116007.0159500 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
526263764-7419-DETAIL-06_28_2022-GO95MLD-1^07116007.0159501 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
605808686-48579-DETAIL-07_06_2022-GO95HV-1^07116007.0166201 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
605808686-48579-DETAIL-07_06_2022-GO95MLD-1^07116007.0166201 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
734413803-73803-DETAIL-03_02_2023-SVCENTCO-1^07117002.0200308 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
448306141-67373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200340 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
43831131-50573-DETAIL-03_09_2023-GO95MLD-1^07117002.0201101 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
213428831-30373-DETAIL-03_09_2023-GO95MLD-1^07117002.0201140 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
682879741-87973-DETAIL-03_02_2023-GO95MLD-1^07117002.0201202 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
682879741-87973-DETAIL-03_02_2023-SVCROAD-1^07117002.0201202 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
798126751-73573-DETAIL-03_02_2023-SVCDEFLC-1^07117002.0201305 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
564591324-2240-DETAIL-03_02_2023-GO95MLD-1^07117002.0201307 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
779516951-21473-DETAIL-03_02_2023-GO95MLD-1^07117002.0201308 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
779516951-21473-DETAIL-03_02_2023-GRDRODHI-1^07117002.0201308 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
970224274-30374-DETAIL-03_02_2023-GO95MLD-1^07117002.0202300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
883143271-53473-DETAIL-03_02_2023-GO95MLD-1^07117002.0202304 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
155060424-79140-DETAIL-03_02_2023-CLMBHAZ-1^07117002.0203203 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
155060424-79140-DETAIL-03_02_2023-GO95TCH-1^07117002.0203203 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
322350681-31173-DETAIL-03_02_2023-GO95CL10-1^07117002.0203300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
322350681-31173-DETAIL-03_02_2023-GO95MLD-1^07117002.0203300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
304370581-56259-DETAIL-03_02_2023-GO95CL10-1^07117002.0203301 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
304370581-56259-DETAIL-03_02_2023-GO95MLD-1^07117002.0203301 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
621144343-72831-DETAIL-03_02_2023-GO95HV-1^07117002.0204203 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
583430443-6059-DETAIL-03_06_2023-GO95MLD-1^07117002.0204204 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2028-03-06 | 3
738547461-58939-DETAIL-03_02_2023-GO95MLD-1^07117002.0204300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
252373528-17443-DETAIL-03_09_2023-SVCENTCO-1^07117002.0205201 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
821256781-75473-DETAIL-03_06_2023-SVCENTCO-1^07117002.0205205 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
400796143-72550-DETAIL-03_06_2023-GO95MLD-1^07117002.0205207 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
196342536-37399-DETAIL-07_06_2022-GO95MLD-1^07116007.0167101 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
798788756-77399-DETAIL-07_06_2022-GO95MLD-1^07116007.0167200 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
809156286-10379-DETAIL-07_06_2022-GO95HV-1^07116007.0168000 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
700130086-17519-DETAIL-07_06_2022-GO95MLD-1^07116007.0168001 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
147364196-27519-DETAIL-07_06_2022-GO95HV-1^07116007.0168101 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
14439996-57519-DETAIL-07_06_2022-GO95STUB-1^07116007.0168102 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
950790806-67519-DETAIL-07_06_2022-GO95HV-1^07116007.0169201 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
319854728-30640-DETAIL-07_06_2022-GO95MLD-1^07116007.0219602 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
549992088-89043-DETAIL-03_09_2023-GO95MLD-1^07117002.0205209 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
775410088-89343-DETAIL-03_09_2023-GO95TCH-1^07117002.0206201 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
877805469-42173-DETAIL-03_08_2023-GO95TCH-1^07117002.0206702 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
332442599-20973-DETAIL-03_08_2023-GO95MLD-1^07117002.0206704 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
145759974-32074-DETAIL-03_09_2023-GO95MLD-1^07117002.0207100 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
448681668-16549-DETAIL-03_09_2023-GRDRODHI-1^07117002.0207242 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
789754329-56973-DETAIL-03_08_2023-GO95BLTC-1^07117002.0207501 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
789754329-56973-DETAIL-03_08_2023-GUYHINS-1^07117002.0207501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
900082558-71540-DETAIL-07_06_2022-GO95MLD-1^07116007.0219900 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
640013513-80409-DETAIL-07_11_2022-GO95MLD-1^07116008.0060101 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
576151923-86419-DETAIL-07_11_2022-GO95HV-1^07116008.0060200 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
611456779-88619-DETAIL-07_11_2022-GO95MLD-1^07116008.0070700 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
538689629-68619-DETAIL-07_11_2022-GO95HV-1^07116008.0070701 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
546346209-979-DETAIL-07_11_2022-GO95MLD-1^07116008.0071500 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
377207599-9619-DETAIL-07_11_2022-GO95HV-1^07116008.0071501 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
905623039-30399-DETAIL-07_11_2022-GO95HV-1^07116008.0071503 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
929363354-18059-DETAIL-05_04_2022-GO95MLD-1^07117001.0180000 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
129831544-92270-ADMIN-10_26_2023-POLEREPL-1^07117001.0245040 | POLE | CA-TIER-2 | Distribution | 2023-10-26 | 2024-10-26 | 2
198454184-830-DETAIL-07_10_2023-SVCNEUT-1^07117001.0246102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
290790174-2530-DETAIL-07_10_2023-GO95MLD-1^07117001.0246103 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
447153654-57401-DETAIL-07_10_2023-GRDRODHI-1^07117001.0247102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
447153654-57401-DETAIL-07_10_2023-SVCENTBK-1^07117001.0247102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
210373664-20050-DETAIL-07_10_2023-GO95MLD-1^07117001.0247104 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
679755679-33173-DETAIL-03_08_2023-GO95HV-1^07117002.0207601 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
679755679-33173-DETAIL-03_08_2023-GO95MLD-1^07117002.0207601 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
679755679-33173-DETAIL-03_08_2023-GUYHINS-1^07117002.0207601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
703212619-99039-DETAIL-03_08_2023-SVCNEUT-1^07117002.0207602 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
314874849-6073-DETAIL-03_08_2023-GO95MLD-1^07117002.0207700 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
888877889-49873-DETAIL-03_08_2023-GO95MLD-1^07117002.0207702 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
973861359-59073-DETAIL-03_07_2023-GUYHINS-1^07117002.0207802 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
617481448-94243-DETAIL-03_09_2023-GO95CL10-1^07117002.0208102 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2028-03-09 | 3
617481448-94243-DETAIL-03_09_2023-GO95MLD-1^07117002.0208102 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
220092558-73949-DETAIL-03_09_2023-GO95MLD-1^07117002.0208201 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
843213748-29443-DETAIL-03_06_2023-GO95HV-1^07117002.0208301 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2028-03-06 | 3
318863679-68873-DETAIL-03_07_2023-GO95MLD-1^07117002.0208700 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
713647878-77043-DETAIL-03_09_2023-GO95MLD-1^07117002.0209105 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
886999211-10320-DETAIL-03_08_2023-GO95MLD-1^07117002.0210206 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
718988796-55353-DETAIL-03_13_2023-GO95MLD-1^07117002.0210207 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2026-03-13 | 2
656590351-62520-DETAIL-03_07_2023-GUYHINS-1^07117002.0210300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
444479671-78520-DETAIL-03_07_2023-GO95MLD-1^07117002.0210400 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
450243561-15520-DETAIL-03_07_2023-GO95MLD-1^07117002.0210401 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
564884631-18259-DETAIL-03_07_2023-GO95MLD-1^07117002.0210402 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
115931461-34939-DETAIL-03_07_2023-GO95HV-1^07117002.0210403 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2028-03-07 | 3
577329491-49620-DETAIL-03_07_2023-GO95MLD-1^07117002.0210500 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
698817181-55620-DETAIL-03_07_2023-SVCENTCO-1^07117002.0210501 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
515793731-53743-DETAIL-03_07_2023-GO95MLD-1^07117002.0210700 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
502251121-16820-DETAIL-03_08_2023-GO95HV-1^07117002.0211100 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
215873624-13950-DETAIL-07_10_2023-GO95HV-1^07117001.0247300 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2028-07-10 | 3
308817255-86249-DETAIL-05_05_2022-GO95MLD-1^07117001.0290101 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
308817255-86249-DETAIL-05_05_2022-GUYHINS-1^07117001.0290101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
144704548-99673-DETAIL-05_12_2022-GO95MLD-1^07117001.0301900 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
60598668-97873-DETAIL-05_12_2022-GUYHINS-1^07117001.0301902 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
527386415-79859-DETAIL-05_12_2022-GO95MLD-1^07117001.0302701 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
527386415-79859-DETAIL-05_12_2022-GUYHINS-1^07117001.0302701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
909675115-7359-DETAIL-05_12_2022-ABNDEQPM-1^07117001.0302800 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
490214021-25320-DETAIL-03_08_2023-GRDRODHI-1^07117002.0211101 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
21935111-31320-DETAIL-03_08_2023-GO95BLTC-1^07117002.0211103 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
21935111-31320-DETAIL-03_08_2023-GO95MLD-1^07117002.0211103 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
897080301-6720-DETAIL-03_08_2023-GO95MLD-1^07117002.0211104 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
274668501-23720-DETAIL-03_08_2023-GO95MLD-1^07117002.0211200 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
642869331-92920-DETAIL-03_07_2023-GO95MLD-1^07117002.0211201 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
423746651-49420-DETAIL-03_07_2023-GRDRODHI-1^07117002.0211300 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
648813343-55018-DETAIL-03_08_2023-SVCNEUT-1^07117002.0212002 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
274656388-8359-DETAIL-05_12_2022-GO95HV-1^07117001.0302803 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
609218778-72249-DETAIL-05_12_2022-GO95MLD-1^07117001.0302804 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
14823358-38659-DETAIL-05_16_2022-ABNDEQPM-1^07117001.0303300 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
956298558-53249-DETAIL-05_16_2022-GO95MLD-1^07117001.0303401 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
665685288-92249-DETAIL-05_12_2022-GO95MLD-1^07117001.0303703 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
723765846-19359-DETAIL-05_16_2022-GO95MLD-1^07117001.0304600 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
723765846-19359-DETAIL-05_16_2022-GRDRODHI-1^07117001.0304600 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
78465993-68788-DETAIL-05_16_2022-GO95MLD-1^07117001.0306500 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
62117331-98331-DETAIL-03_08_2023-GO95MLD-1^07117002.0212004 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
767027443-82418-DETAIL-03_08_2023-GUYHINS-1^07117002.0213000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
734775969-13833-DETAIL-03_14_2023-GO95BLTC-1^07117002.0270601 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2028-03-14 | 3
734775969-13833-DETAIL-03_14_2023-GO95MLD-1^07117002.0270601 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
734775969-13833-DETAIL-03_14_2023-GO95TCH-1^07117002.0270601 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
834542279-18833-DETAIL-03_14_2023-GO95MLD-1^07117002.0271600 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
991208238-7300-DETAIL-03_14_2023-GO95HV-1^07117002.0274700 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2028-03-14 | 3
793044638-57300-DETAIL-03_14_2023-GO95MLD-1^07117002.0275700 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
859864149-75549-DETAIL-03_14_2023-GO95MLD-1^07117002.0285900 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
729732029-26549-DETAIL-03_14_2023-GUYLOINS-1^07117002.0286801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
704501219-6549-DETAIL-03_14_2023-GO95MLD-1^07117002.0286900 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
717784199-70333-DETAIL-03_13_2023-GO95HV-1^07117002.0289502 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2028-03-13 | 3
717784199-70333-DETAIL-03_13_2023-GO95MLD-1^07117002.0289502 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2026-03-13 | 2
930571273-24753-DETAIL-03_01_2023-GO95MLD-1^07117002.0305900 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
853280068-76459-DETAIL-04_24_2023-GO95HV-1^07117003.0010700 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
104242278-96459-DETAIL-04_24_2023-GRDRODHI-1^07117003.0011700 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
529842571-73571-DETAIL-05_05_2022-GO95MLD-1^07117001.0307002 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
245744775-89359-DETAIL-05_05_2022-GO95HV-1^07117001.0307100 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2027-05-05 | 3
874201760-80459-DETAIL-05_16_2022-GO95MLD-1^07117001.0307101 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
798792606-17439-DETAIL-05_05_2022-GO95MLD-1^07117001.0308000 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
973522006-33939-DETAIL-05_05_2022-GO95MLD-1^07117001.0308002 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2027-05-05 | 3
170883105-2059-AUDIT-05_24_2022-SVCENTCO-1^07117001.0308007 | OTHER | CA-TIER-2 | Distribution | 2022-05-24 | 2025-05-24 | 2
62387068-26959-DETAIL-05_05_2022-GO95TCH-1^07117001.0308300 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
810058476-89159-DETAIL-05_05_2022-GUYLOINS-1^07117001.0308301 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
955152735-94159-DETAIL-05_05_2022-GO95MLD-1^07117001.0309000 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
911940904-87659-DETAIL-05_16_2022-GO95MLD-1^07117001.0313800 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
662119534-54249-DETAIL-05_16_2022-GO95MLD-1^07117001.0316501 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
194739644-37759-DETAIL-05_16_2022-GO95MLD-1^07117001.0317501 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
591763764-45259-DETAIL-05_16_2022-GO95MLD-1^07117001.0317600 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
231959954-43549-DETAIL-05_17_2022-GO95MLD-1^07117001.0318600 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
231959954-43549-DETAIL-05_17_2022-GO95TCH-1^07117001.0318600 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
972175954-55259-DETAIL-05_17_2022-GO95MLD-1^07117001.0318601 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
433587888-81823-DETAIL-03_20_2023-GO95MLD-1^07117003.0016800 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
433587888-81823-DETAIL-03_20_2023-GRDRODHI-1^07117003.0016800 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
167118265-12663-DETAIL-04_24_2023-GO95HV-1^07117003.0022000 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
64858865-13663-DETAIL-04_24_2023-GO95MLD-1^07117003.0024101 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
127965075-11763-DETAIL-04_24_2023-GO95HV-1^07117003.0025100 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
311428785-55459-DETAIL-04_24_2023-GO95HV-1^07117003.0027401 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
536760575-28663-DETAIL-04_24_2023-GO95TCH-1^07117003.0082400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
677196265-15663-DETAIL-04_24_2023-GO95MLD-1^07117003.0088000 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
998235033-46033-DETAIL-03_14_2023-GO95MLD-1^07117003.0092002 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
558277775-87263-DETAIL-04_24_2023-GO95HV-1^07117003.0101600 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
558277775-87263-DETAIL-04_24_2023-GO95MLD-1^07117003.0101600 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
509553835-28063-DETAIL-04_24_2023-GO95HV-1^07117003.0105600 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
188644808-52223-DETAIL-03_14_2023-GO95MLD-1^07117003.0112602 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
132331798-17123-DETAIL-03_14_2023-GO95MLD-1^07117003.0112604 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
132331798-17123-DETAIL-03_14_2023-GO95TCH-1^07117003.0112604 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
726495948-53023-DETAIL-03_14_2023-GO95MLD-1^07117003.0113704 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
87256538-48923-DETAIL-03_14_2023-GO95MLD-1^07117003.0113800 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
643432318-48223-DETAIL-03_14_2023-SVCENTCO-1^07117003.0114901 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
3803328-73923-DETAIL-03_20_2023-GUYHINS-1^07117004.0061800 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
529814031-30089-DETAIL-07_12_2022-GO95HV-1^07117007.0053000 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
529814031-30089-DETAIL-07_12_2022-GO95MLD-1^07117007.0053000 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2025-07-12 | 2
982735801-57619-DETAIL-07_12_2022-GO95MLD-1^07117007.0054000 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2025-07-12 | 2
343961490-67619-DETAIL-07_12_2022-ABNDEQPM-1^07117007.0054100 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
8399550-45340-DETAIL-07_12_2022-ABNDEQPM-1^07117007.0076301 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
323673490-74159-DETAIL-05_17_2022-GO95MLD-1^07117001.0319300 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
432227390-24159-DETAIL-05_17_2022-GO95MLD-1^07117001.0319301 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
145929694-69759-DETAIL-05_17_2022-GO95HV-1^07117001.0319403 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2027-05-17 | 3
145929694-69759-DETAIL-05_17_2022-GO95MLD-1^07117001.0319403 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
408639764-74249-DETAIL-05_17_2022-GO95MLD-1^07117001.0319404 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
92117993-60859-DETAIL-05_11_2022-GO95HV-1^07117001.0320401 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
19719090-14949-DETAIL-05_11_2022-GO95MLD-1^07117001.0320403 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
722138114-70249-DETAIL-05_11_2022-GO95MLD-1^07117001.0320404 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
137806183-6359-DETAIL-05_11_2022-GO95TCH-1^07117001.0322200 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
673286673-46359-DETAIL-05_11_2022-GO95HV-1^07117001.0322202 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2027-05-11 | 3
416974133-39259-DETAIL-05_11_2022-GO95MLD-1^07117001.0326001 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
632915828-67259-DETAIL-03_08_2023-GO95HV-1^07117002.0193200 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
867255255-84033-DETAIL-03_06_2023-GO95MLD-1^07117002.0195000 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2028-03-06 | 3
93184385-99733-DETAIL-03_01_2023-GO95MLD-1^07117002.0195002 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
528908345-69933-DETAIL-03_01_2023-SVCDEFLC-1^07117002.0195203 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
638796141-82050-DETAIL-07_08_2022-GO95HV-1^07117007.0089840 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
903700500-45269-DETAIL-07_08_2022-GO95MLD-1^07117007.0090600 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2025-07-08 | 2
903700500-45269-DETAIL-07_08_2022-GRDRODHI-1^07117007.0090600 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2025-07-08 | 2
430817230-46619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0091601 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
151810390-19189-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0091603 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
28731960-62619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0092802 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
883749319-45819-DETAIL-07_12_2022-GO95HV-1^07117007.0133400 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
131212339-66819-DETAIL-07_12_2022-GO95MLD-1^07117007.0136101 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2025-07-12 | 2
223569139-64773-DETAIL-03_01_2023-GO95MLD-1^07117002.0195206 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
192531085-79133-DETAIL-03_01_2023-GO95MLD-1^07117002.0196201 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
773942945-7633-DETAIL-03_01_2023-GO95MLD-1^07117002.0196205 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
221961054-82060-DETAIL-03_01_2023-GO95MLD-1^07117002.0196206 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
508115445-96249-DETAIL-03_01_2023-GO95TCH-1^07117002.0196207 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
215147838-14391-DETAIL-03_01_2023-SVCDEFLC-2^07117002.0196240 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
503720875-17733-DETAIL-03_01_2023-GO95MLD-1^07117002.0196302 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
503720875-17733-DETAIL-03_01_2023-SVCENTCO-1^07117002.0196302 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
589464321-25719-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150000 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
624282581-5719-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150100 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
624282581-5719-DETAIL-07_05_2022-GO95MLD-1^07117007.0150100 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2025-07-05 | 2
941327511-59250-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150101 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
723974501-94719-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150103 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
991715824-10819-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0169101 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
613459301-97050-DETAIL-07_07_2022-GO95MLD-1^07117007.0169600 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
782999081-37389-DETAIL-07_07_2022-GO95MLD-1^07117007.0169604 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2025-07-07 | 2
238597635-27533-DETAIL-03_01_2023-GO95MLD-1^07117002.0197205 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
357617035-74533-DETAIL-03_01_2023-SVCNEUT-1^07117002.0197206 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
926416705-21733-ADMIN-11_16_2023-POLEREPL-1^07117002.0197241 | POLE | CA-TIER-2 | Distribution | 2023-11-16 | 2024-11-16 | 2
647060875-60059-DETAIL-03_01_2023-GO95MLD-1^07117002.0197301 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
274035818-3763-DETAIL-03_08_2023-GO95HV-1^07117002.0198101 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
747716725-92433-DETAIL-03_02_2023-GO95MLD-1^07117002.0198200 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
270981249-75773-DETAIL-03_02_2023-GUYNOINS-1^07117002.0198201 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
283091625-35433-DETAIL-03_02_2023-GUYHINS-1^07117002.0198203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
171010965-7415-DETAIL-03_02_2023-GRDRODHI-1^07117002.0198204 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
846455065-45733-DETAIL-03_01_2023-GO95MLD-1^07117002.0198302 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
170943686-98355-DETAIL-03_02_2023-GO95MLD-1^07117002.0198304 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
963396745-64733-DETAIL-03_02_2023-GO95MLD-1^07117002.0198305 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
197732698-61263-DETAIL-03_09_2023-GO95MLD-1^07117002.0199100 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
230266141-48373-DETAIL-03_02_2023-GO95HV-1^07117002.0200300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
649420451-61773-DETAIL-03_02_2023-GO95TCH-1^07117002.0200304 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
908001381-31050-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0169701 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
669622861-8719-DETAIL-07_08_2022-GO95MLD-1^07117007.0169803 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2025-07-08 | 2
110416563-63663-DETAIL-07_07_2022-GO95HV-1^07117007.0225930 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
166417101-47599-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0226200 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
48138651-29689-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0226701 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
885040411-89109-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0227201 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
572324131-30089-DETAIL-05_25_2023-GO95HV-1^07117007.0227501 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2028-05-25 | 3
59606891-24819-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0228100 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
728271391-68573-DETAIL-03_09_2023-GO95MLD-1^07117002.0201100 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
769948952-52052-DETAIL-03_02_2023-GO95HV-1^07117002.0201200 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
113184771-89073-DETAIL-03_02_2023-GO95MLD-1^07117002.0201203 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
422253871-13473-DETAIL-03_02_2023-GO95MLD-1^07117002.0201303 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
422253871-13473-DETAIL-03_02_2023-SVCDEFLC-1^07117002.0201303 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
779516951-21473-DETAIL-03_02_2023-SVCDEFLC-1^07117002.0201308 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
134762121-98473-DETAIL-03_09_2023-GUYLOINS-1^07117002.0202101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
287860761-64819-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0229000 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
273996941-94819-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0229102 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
338588340-59819-DETAIL-07_05_2022-GO95MLD-1^07117007.0260001 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2025-07-05 | 2
338588340-59819-DETAIL-07_05_2022-GRDRODHI-1^07117007.0260001 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2025-07-05 | 2
220903740-44880-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0260700 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
869331358-52358-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0349000 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
869331358-52358-DETAIL-07_05_2022-GO95HV-1^07117007.0349000 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
268395645-59903-DETAIL-07_05_2022-GO95HV-1^07117007.0349702 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
877089521-15673-DETAIL-03_02_2023-GO95MLD-1^07117002.0202200 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
526121471-17773-DETAIL-03_09_2023-GO95MLD-1^07117002.0203100 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
155060424-79140-DETAIL-03_02_2023-GO95HV-1^07117002.0203203 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
611527961-64073-DETAIL-03_02_2023-GUYHINS-1^07117002.0203204 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
902648611-38473-DETAIL-03_09_2023-GO95MLD-1^07117002.0203207 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
426436061-92773-DETAIL-03_06_2023-ENCHRW-1^07117002.0204200 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
821256781-75473-DETAIL-03_06_2023-SVCDEFLC-1^07117002.0205205 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
140102398-42143-DETAIL-03_09_2023-GO95MLD-1^07117002.0205208 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
77115130-70919-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0350400 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
742240650-2340-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0350701 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
164813559-29919-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0322303 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
906853395-78352-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0323400 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
674419395-41941-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0324400 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
438875495-72669-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0324501 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
927360701-1749-DETAIL-03_20_2023-SVCDEFLC-1^07119004.0349400 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
274675581-54239-DTLSB-04_05_2022-GO95MLD-1^07216001.0030002 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
890498571-82349-DTLSB-04_05_2022-GO95CL10-1^07216001.0030004 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
377473610-26259-DTLSB-04_05_2022-GO95HV-1^07216001.0030006 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
486593470-5470-DTLSB-04_05_2022-CLMBHAZ-1^07216001.0030040 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
259217611-55049-DTLSB-04_05_2022-GO95HV-1^07216001.0030100 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
694932420-37449-DTLSB-04_05_2022-GO95MLD-1^07216001.0030105 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
34751591-87549-DTLSB-04_05_2022-GO95MLD-1^07216001.0030301 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
708892660-649-DTLSB-04_05_2022-GO95HV-1^07216001.0030302 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
708892660-649-DTLSB-04_05_2022-GO95MLD-1^07216001.0030302 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
708892660-649-DTLSB-04_05_2022-SVCENTCO-1^07216001.0030302 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
972068861-16049-DTLSB-04_06_2022-GO95MLD-1^07216001.0030303 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
923259971-24359-DTLSB-04_06_2022-GO95HV-1^07216001.0030402 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
925748164-79164-DTLSB-04_12_2022-GO95SVC-1^07216001.0030406 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
546128900-13249-DTLSB-04_05_2022-GO95HV-1^07216001.0031002 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
517077141-60359-DTLSB-04_05_2022-GO95MLD-1^07216001.0031006 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
884087010-89149-DTLSB-04_05_2022-GO95MLD-1^07216001.0031100 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
140102398-42143-DETAIL-03_09_2023-SVCNEUT-1^07117002.0205208 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
514988968-87943-DETAIL-03_09_2023-GO95MLD-1^07117002.0205210 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
465443938-7643-DETAIL-03_14_2023-GO95MLD-1^07117002.0205240 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
823181068-13543-DETAIL-03_06_2023-GO95MLD-1^07117002.0206203 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
823181068-13543-DETAIL-03_06_2023-GUYHINS-1^07117002.0206203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
464336682-93473-DETAIL-03_09_2023-GO95MLD-1^07117002.0206240 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
877805469-42173-DETAIL-03_08_2023-GO95MLD-1^07117002.0206702 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
679973499-41973-DETAIL-03_08_2023-GO95HV-1^07117002.0206703 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
679973499-41973-DETAIL-03_08_2023-GO95MLD-1^07117002.0206703 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
332442599-20973-DETAIL-03_08_2023-GUYHINS-1^07117002.0206704 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
145759974-32074-DETAIL-03_09_2023-GO95HV-1^07117002.0207100 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2028-03-09 | 3
320769258-92743-DETAIL-03_09_2023-GUYNOINS-1^07117002.0207141 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
641334732-31880-DETAIL-03_06_2023-GO95MLD-1^07117002.0207240 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
448681668-16549-DETAIL-03_09_2023-GO95MLD-1^07117002.0207242 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
425781908-64143-DETAIL-03_06_2023-GO95MLD-1^07117002.0207301 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
217644519-85973-DETAIL-03_08_2023-GO95MLD-1^07117002.0207600 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
703212619-99039-DETAIL-03_08_2023-GO95MLD-1^07117002.0207602 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
339339141-6880-DETAIL-03_07_2023-GO95MLD-1^07117002.0207704 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
973861359-59073-DETAIL-03_07_2023-GO95MLD-1^07117002.0207802 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
973861359-59073-DETAIL-03_07_2023-GO95TCH-1^07117002.0207802 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
890976109-63973-DETAIL-03_08_2023-GO95MLD-1^07117002.0207803 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
707103809-43809-DETAIL-03_09_2023-GO95MLD-1^07117002.0208103 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
843213748-29443-DETAIL-03_06_2023-GO95MLD-1^07117002.0208301 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
554637931-7150-DETAIL-03_06_2023-GO95MLD-1^07117002.0208340 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
884087010-89149-DTLSB-04_05_2022-SVCWIND-1^07216001.0031100 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
723695900-88049-DTLSB-04_05_2022-GO95MLD-1^07216001.0031101 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
577086291-88359-DTLSB-04_06_2022-SVCROAD-1^07216001.0031200 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
958928450-50049-DTLSB-04_05_2022-GO95HV-1^07216001.0031202 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
958928450-50049-DTLSB-04_05_2022-GO95MLD-1^07216001.0031202 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
618459040-35949-DTLTRT-04_06_2022-SVCENTCO-1^07216001.0031300 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
34621830-74649-DTLSB-04_06_2022-GO95HV-1^07216001.0031301 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
34621830-74649-DTLSB-04_06_2022-GO95MLD-1^07216001.0031301 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
34621830-74649-DTLSB-04_06_2022-SVCNEUT-1^07216001.0031301 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
85749080-18139-DTLSB-04_06_2022-GO95MLD-1^07216001.0031400 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
85749080-18139-DTLSB-04_06_2022-GO95TCH-1^07216001.0031400 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
409285081-30739-DTLSB-04_05_2022-GO95HV-1^07216001.0032001 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
582223851-97939-DTLSB-04_05_2022-GO95MLD-1^07216001.0032003 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
582223851-97939-DTLSB-04_05_2022-GO95TCH-1^07216001.0032003 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
756988471-48549-DTLSB-04_05_2022-GO95MLD-1^07216001.0032103 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
329711920-96549-DTLTRT-04_06_2022-SVCNEUT-1^07216001.0032204 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
672833431-55259-DTLSB-04_07_2022-GO95MLD-1^07216001.0033105 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
493135961-10359-DTLSB-04_06_2022-GO95TCH-1^07216001.0033201 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
895036201-62359-DTLSB-04_12_2022-GO95HV-1^07216001.0033300 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
895036201-62359-DTLSB-04_12_2022-GO95MLD-1^07216001.0033300 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
864921121-83259-DTLSB-04_07_2022-ABNDEQPM-1^07216001.0034003 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
738223190-5149-DTLSB-04_07_2022-GO95MLD-1^07216001.0034100 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
833618680-32359-DTLSB-04_12_2022-GO95MLD-1^07216001.0034300 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
961548992-24253-DTLSB-04_07_2022-GO95TCH-1^07216001.0034803 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
225308998-72143-DETAIL-03_09_2023-ENCHRW-1^07117002.0209102 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
392687578-34343-DETAIL-03_09_2023-GO95MLD-1^07117002.0209104 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
392687578-34343-DETAIL-03_09_2023-GO95TCH-1^07117002.0209104 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
790122168-56943-DETAIL-03_09_2023-GO95MLD-1^07117002.0209106 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
47587978-70843-DETAIL-03_09_2023-GO95MLD-1^07117002.0209108 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
496099979-56873-DETAIL-03_07_2023-GO95MLD-1^07117002.0209701 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
822488001-52220-DETAIL-03_08_2023-GO95MLD-1^07117002.0210203 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
656590351-62520-DETAIL-03_07_2023-GO95BLTC-1^07117002.0210300 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2028-03-07 | 3
115931461-34939-DETAIL-03_07_2023-GO95MLD-1^07117002.0210403 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
115931461-34939-DETAIL-03_07_2023-GO95TCH-1^07117002.0210403 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
577329491-49620-DETAIL-03_07_2023-GUYHINS-1^07117002.0210500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
734980971-90620-DETAIL-03_07_2023-GO95MLD-1^07117002.0210600 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
502251121-16820-DETAIL-03_08_2023-GO95MLD-1^07117002.0211100 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
520050671-52620-DETAIL-03_08_2023-GO95MLD-1^07117002.0211102 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
897080301-6720-DETAIL-03_08_2023-SVCNEUT-1^07117002.0211104 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
568902441-38420-DETAIL-03_07_2023-GO95MLD-1^07117002.0211202 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
89854838-63559-DTLSB-04_06_2022-GUYNOINS-1^07216001.0035402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
786594635-45352-DTLSB-04_07_2022-GUYSLACK-1^07216001.0035541 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
177589638-30738-DTLSB-04_07_2022-GUYNOINS-1^07216001.0035542 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
284593456-16020-DTLSB-04_07_2022-ABNDEQPM-1^07216001.0035600 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
283594212-82139-DTLTRT-04_07_2022-GO95MLD-1^07216001.0035601 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
713929122-34839-DTLTRT-04_07_2022-GO95MLD-1^07216001.0035605 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
943691362-28413-DTLSB-04_07_2022-GO95HV-1^07216001.0035806 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
278472522-27320-DTLSB-04_07_2022-SVCNEUT-1^07216001.0035901 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
893832678-72559-DTLSB-04_11_2022-GO95HV-1^07216001.0036300 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
365229788-60039-DTLSB-04_11_2022-GO95MLD-1^07216001.0036301 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
166242148-5739-DTLTRT-04_11_2022-GO95MLD-1^07216001.0036406 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
673886051-17839-DTLSB-04_06_2022-GO95MLD-1^07216001.0036503 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
370792672-28059-DTLSB-04_12_2022-GO95HV-1^07216001.0036701 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
907589628-97459-DTLSB-04_12_2022-GO95HV-1^07216001.0037200 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
108980408-31559-DTLSB-04_12_2022-GO95HV-1^07216001.0037202 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
332321648-74639-DTLSB-04_11_2022-GO95MLD-1^07216001.0037303 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
687048658-20449-DTLSB-04_11_2022-GO95MLD-1^07216001.0037305 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
302608538-65539-DTLSB-04_12_2022-GO95HV-1^07216001.0037400 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
302608538-65539-DTLSB-04_12_2022-GO95MLD-1^07216001.0037400 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
246646478-9639-DTLTRT-04_12_2022-GO95HV-1^07216001.0037401 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
310249448-64739-DTLSB-04_11_2022-GO95MLD-1^07216001.0037500 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
111116731-77239-DTLTRT-04_11_2022-GO95MLD-1^07216001.0037502 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
630374232-31549-DTLSB-04_11_2022-GO95MLD-1^07216001.0037505 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
630374232-31549-DTLSB-04_11_2022-SVCNEUT-1^07216001.0037505 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
227008921-37349-DTLTRT-04_11_2022-SVCNEUT-1^07216001.0037601 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
20475111-62449-DTLSB-04_11_2022-GO95MLD-1^07216001.0037603 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
20475111-62449-DTLSB-04_11_2022-SVCENTCO-1^07216001.0037603 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
603954089-42863-DTLSB-04_12_2022-GO95MLD-1^07216001.0037701 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
445453601-46301-DTLSB-04_11_2022-SVCENTCO-1^07216001.0037703 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
875332252-37749-DTLSB-04_12_2022-GO95HV-1^07216001.0037704 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
875332252-37749-DTLSB-04_12_2022-GO95MLD-1^07216001.0037704 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
861609376-73476-DTLSB-04_12_2022-GO95HV-1^07216001.0038302 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
648813343-55018-DETAIL-03_08_2023-GO95MLD-1^07117002.0212002 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
648813343-55018-DETAIL-03_08_2023-GO95TCH-1^07117002.0212002 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
425579493-41918-DETAIL-03_08_2023-GO95MLD-1^07117002.0212003 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
605065249-3733-DETAIL-03_13_2023-GO95HV-1^07117002.0270501 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2028-03-13 | 3
605065249-3733-DETAIL-03_13_2023-GO95MLD-1^07117002.0270501 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2028-03-13 | 3
386094579-79133-DETAIL-03_13_2023-GO95HV-1^07117002.0289602 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2028-03-13 | 3
675713995-90833-DETAIL-03_01_2023-SVCENTCO-1^07117002.0305903 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
570972615-57363-DETAIL-04_24_2023-GO95HV-1^07117003.0020000 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
808836875-98663-DETAIL-04_24_2023-GO95HV-1^07117003.0025101 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
808836875-98663-DETAIL-04_24_2023-GO95MLD-1^07117003.0025101 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
614323785-25459-DETAIL-04_24_2023-GO95MLD-1^07117003.0027300 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
311428785-55459-DETAIL-04_24_2023-GO95MLD-1^07117003.0027401 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
76168385-6459-DETAIL-04_24_2023-GO95MLD-1^07117003.0028500 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
465628368-26459-DETAIL-04_24_2023-GO95MLD-1^07117003.0029700 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
536760575-28663-DETAIL-04_24_2023-GO95MLD-1^07117003.0082400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
241598765-49765-DETAIL-04_24_2023-GO95MLD-1^07117003.0082401 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
386141655-52663-DETAIL-04_24_2023-GO95HV-1^07117003.0085200 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
266070565-84663-DETAIL-04_24_2023-GO95MLD-1^07117003.0087000 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
760671275-5263-DETAIL-03_14_2023-GO95HV-1^07117003.0092001 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2028-03-14 | 3
386656305-24763-DETAIL-03_14_2023-GUYHINS-1^07117003.0093000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
386656305-24763-DETAIL-03_14_2023-SVCDEFLC-1^07117003.0093000 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
625822675-70363-DETAIL-03_20_2023-GO95HV-1^07117003.0093101 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2028-03-20 | 3
238603515-64763-DETAIL-03_20_2023-GO95MLD-1^07117003.0093102 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
115654185-14363-DETAIL-03_20_2023-SVCDEFLC-1^07117003.0094000 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
31341935-65063-DETAIL-04_24_2023-GO95HV-1^07117003.0104700 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
646379935-7063-DETAIL-04_24_2023-GO95MLD-1^07117003.0105601 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
998172008-93223-DETAIL-03_14_2023-SVCENTCO-1^07117003.0112603 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
302752668-47023-DETAIL-03_14_2023-GO95MLD-1^07117003.0113703 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
479946719-71824-DETAIL-03_14_2023-GUYHINS-1^07117003.0114800 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
479946719-71824-DETAIL-03_14_2023-SVCNEUT-1^07117003.0114800 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
643432318-48223-DETAIL-03_14_2023-GO95MLD-1^07117003.0114901 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
833381408-29823-DETAIL-03_20_2023-GO95MLD-1^07117004.0060700 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
595116592-34349-DTLSB-04_12_2022-GO95HV-1^07216001.0038603 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
595116592-34349-DTLSB-04_12_2022-GO95MLD-1^07216001.0038603 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
210244082-87349-DTLSB-04_12_2022-GO95MLD-1^07216001.0038701 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
754529072-8859-DTLSB-04_12_2022-GO95HV-1^07216001.0038702 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
584336568-7449-DTLSB-04_12_2022-GO95MLD-1^07216001.0039303 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
186432521-55820-DTLSB-04_12_2022-GO95MLD-1^07216001.0039503 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
265260091-17459-DTLSB-04_12_2022-GO95MLD-1^07216001.0039504 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
950743221-36923-DTLSB-04_12_2022-GO95MLD-1^07216001.0039600 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
783956418-41323-DETAIL-03_20_2023-GO95MLD-1^07117004.0061700 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
3803328-73923-DETAIL-03_20_2023-SVCENTCO-1^07117004.0061800 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
226646765-87765-DETAIL-03_20_2023-GO95MLD-1^07117004.0061830 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
343961490-67619-DETAIL-07_12_2022-SVCROAD-1^07117007.0054100 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2025-07-12 | 2
299828640-6619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0091600 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
111987180-16619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0092701 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
46812480-64779-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0093900 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
743154620-74619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0094100 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
968271021-24719-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150102 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
495672171-56719-DETAIL-07_07_2022-GO95HV-1^07117007.0152002 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
934227441-71699-DETAIL-07_07_2022-GO95HV-1^07117007.0152100 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
387393431-49719-DETAIL-07_07_2022-GO95HV-1^07117007.0168600 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
176262991-73819-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0227200 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
885040411-89109-DETAIL-05_25_2023-CONDCOIL-1^07117007.0227201 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2024-05-25 | 2
391351061-4819-DETAIL-05_25_2023-GO95HV-1^07117007.0227202 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2028-05-25 | 3
636285441-52819-DETAIL-05_25_2023-RISEGRD-1^07117007.0227400 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
906152341-22819-DETAIL-07_05_2022-GO95MLD-1^07117007.0227500 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2025-07-05 | 2
572324131-30089-DETAIL-05_25_2023-POLEREPL-1^07117007.0227501 | POLE | CA-TIER-2 | Distribution | 2023-05-25 | 2024-05-25 | 2
228954591-92099-DETAIL-05_25_2023-GO95HV-1^07117007.0227600 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2028-05-25 | 3
38544281-38169-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0227601 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
303100430-96819-DETAIL-07_07_2022-SVCWIND-1^07117007.0260901 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2025-07-07 | 2
187651250-97819-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0261301 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
386405701-71919-DETAIL-07_07_2022-GO95HV-1^07117007.0278901 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
500046711-61669-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0279000 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
396173378-44378-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0279001 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
95698331-92919-DETAIL-07_06_2022-ABNDEQPM-1^07117007.0279703 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
993078951-31919-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0279903 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
390290824-15919-DETAIL-07_05_2022-GO95HV-1^07117007.0349001 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
184389645-65920-DETAIL-07_05_2022-GO95HV-1^07117007.0349701 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
982750645-36803-DETAIL-07_05_2022-GO95HV-1^07117007.0349703 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
742761760-27340-DETAIL-07_05_2022-GO95HV-1^07117007.0350501 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
79732681-85259-DETAIL-03_20_2023-ABNDEQPM-1^07118004.0020500 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2028-03-20 | 3
199144894-65259-DETAIL-03_20_2023-ABNDEQPM-1^07118004.0020501 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2028-03-20 | 3
835046079-66919-DETAIL-07_12_2022-GO95HV-1^07118006.0258001 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
74641669-86919-DETAIL-07_12_2022-GO95HV-1^07118006.0258002 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
772200295-32669-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0322300 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
157872195-2669-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0322301 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
890498571-82349-DTLSB-04_05_2022-GO95MLD-1^07216001.0030004 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
78580211-52010-DTLSB-04_12_2022-GO95HV-1^07216001.0039602 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
809585081-17749-DTLSB-04_12_2022-GO95TCH-1^07216001.0039603 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
710679875-81151-DTLSB-04_12_2022-GO95TCH-1^07216001.0039606 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
69714092-37190-DTLSB-04_11_2022-GO95HV-1^07216001.0039900 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
707888945-49439-DTLSB-04_04_2022-GO95HV-1^07216001.0046302 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
707888945-49439-DTLSB-04_04_2022-GO95MLD-1^07216001.0046302 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
707888945-49439-DTLSB-04_04_2022-SVCENTCO-1^07216001.0046302 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
530695226-80259-DTLSB-04_04_2022-GO95HV-1^07216001.0047200 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
642355910-56339-DTLSB-04_05_2022-GO95HV-1^07216001.0030008 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
642355910-56339-DTLSB-04_05_2022-GO95MLD-1^07216001.0030008 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
551056010-65159-DTLSB-04_05_2022-GO95HV-1^07216001.0030009 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
765280685-4291-DTLSB-04_04_2022-GO95HV-1^07216001.0030010 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
765280685-4291-DTLSB-04_04_2022-GO95MLD-1^07216001.0030010 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
486593470-5470-DTLSB-04_05_2022-GO95CL10-1^07216001.0030040 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
259217611-55049-DTLSB-04_05_2022-GO95MLD-1^07216001.0030100 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
34751591-87549-DTLSB-04_05_2022-GO95HV-1^07216001.0030301 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
171878015-69239-DTLSB-04_04_2022-GO95HV-1^07216001.0047202 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
171878015-69239-DTLSB-04_04_2022-GO95MLD-1^07216001.0047202 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
780118505-53239-DTLSB-04_04_2022-GO95MLD-1^07216001.0047203 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
898157045-40439-DTLSB-04_04_2022-GO95MLD-1^07216001.0048100 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
898157045-40439-DTLSB-04_04_2022-SVCENTCO-1^07216001.0048100 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
504285983-47059-DTLSB-04_04_2022-GO95TCH-1^07216001.0048101 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
933426635-47049-DTLSB-04_04_2022-GO95MLD-1^07216001.0048104 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
393164175-6339-DTLSB-04_06_2022-GO95TCH-1^07216001.0048401 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
997977465-99359-DTLSB-04_06_2022-GO95STUB-1^07216001.0048402 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
600473555-69949-DTLSB-04_06_2022-GO95MLD-1^07216001.0048403 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
838939475-54849-DTLSB-04_06_2022-GO95TCH-1^07216001.0048601 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
965871425-8639-DTLSB-04_04_2022-GO95HV-1^07216001.0049000 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
965871425-8639-DTLSB-04_04_2022-GO95MLD-1^07216001.0049000 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
418109715-17859-DTLSB-04_04_2022-GO95CL10-1^07216001.0049002 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
418109715-17859-DTLSB-04_04_2022-GO95HV-1^07216001.0049002 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
418109715-17859-DTLSB-04_04_2022-GO95MLD-1^07216001.0049002 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
605324555-89149-DTLSB-04_05_2022-GO95MLD-1^07216001.0049101 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
187890745-249-DTLSB-04_05_2022-GO95MLD-1^07216001.0049102 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
338436336-32249-DTLSB-04_07_2022-GO95MLD-1^07216001.0049202 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
338436336-32249-DTLSB-04_07_2022-GUYHINS-1^07216001.0049202 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
585982485-50239-DTLSB-04_07_2022-GO95HV-1^07216001.0049203 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
373768600-85155-DTLSB-04_06_2022-GO95MLD-1^07216001.0049304 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
978618895-6349-DTLSB-04_06_2022-GO95HV-1^07216001.0049306 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
493399865-29359-DTLSB-04_06_2022-GO95HV-1^07216001.0049505 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
493399865-29359-DTLSB-04_06_2022-GO95MLD-1^07216001.0049505 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
628307011-93859-DETAIL-04_14_2022-GO95STUB-1^07216001.0100001 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
496995700-59749-DETAIL-04_14_2022-CLMBHAZ-1^07216001.0100100 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
496995700-59749-DETAIL-04_14_2022-GO95MLD-1^07216001.0100100 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
184733930-2849-DETAIL-04_14_2022-ANCHIDLE-1^07216001.0100200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
184733930-2849-DETAIL-04_14_2022-GO95MLD-1^07216001.0100200 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
953537638-8638-DETAIL-04_14_2022-GO95HV-1^07216001.0100202 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
60033401-61739-DETAIL-04_13_2022-GO95HV-1^07216001.0100300 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
241127611-82259-DETAIL-04_13_2022-GO95MLD-1^07216001.0100400 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
241127611-82259-DETAIL-04_13_2022-GO95TCH-1^07216001.0100400 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
644622050-37859-DETAIL-04_13_2022-GRDBROKE-1^07216001.0100402 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
545495730-22949-DETAIL-04_13_2022-CLMBHAZ-1^07216001.0100403 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
545495730-22949-DETAIL-04_13_2022-CLRTOUCH-1^07216001.0100403 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
545495730-22949-DETAIL-04_13_2022-GO95MLD-1^07216001.0100403 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
545495730-22949-DETAIL-04_13_2022-GO95TCH-1^07216001.0100403 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
545495730-22949-DETAIL-04_13_2022-SVCROOF-1^07216001.0100403 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
160759584-3259-DETAIL-04_13_2022-SVCENTCO-1^07216001.0100500 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
338140182-48049-DETAIL-04_13_2022-GO95HV-1^07216001.0100801 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
338140182-48049-DETAIL-04_13_2022-GUYSLACK-1^07216001.0100801 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
616347421-29949-DETAIL-04_13_2022-GO95MLD-1^07216001.0100900 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
616347421-29949-DETAIL-04_13_2022-SVCWIND-1^07216001.0100900 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
844528664-95159-DETAIL-04_13_2022-GO95MLD-1^07216001.0100901 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
320184504-55059-DETAIL-04_13_2022-GO95HV-1^07216001.0100902 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
702388252-57159-DETAIL-04_13_2022-GO95MLD-1^07216001.0100903 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
641873862-44761-DETAIL-04_13_2022-CLMBHAZ-1^07216001.0100904 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
641873862-44761-DETAIL-04_13_2022-GO95HV-1^07216001.0100904 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
569901577-4388-DETAIL-04_14_2022-GO95MLD-1^07216001.0101100 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
30942751-76859-DETAIL-04_14_2022-GO95MLD-1^07216001.0101101 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
30942751-76859-DETAIL-04_14_2022-SVCNEUT-1^07216001.0101101 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
265585280-80059-DETAIL-04_14_2022-GO95MLD-1^07216001.0101200 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
176482054-44054-DETAIL-04_14_2022-GO95MLD-1^07216001.0101202 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
73149358-40458-DETAIL-04_14_2022-GRDRODHI-1^07216001.0101204 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
510325750-72949-DTLSB-04_06_2022-GO95MLD-1^07216001.0030400 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
923259971-24359-DTLSB-04_06_2022-SVCENTCO-1^07216001.0030402 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
41443965-12939-DTLSB-04_06_2022-GO95MLD-1^07216001.0030405 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
546128900-13249-DTLSB-04_05_2022-GO95MLD-1^07216001.0031002 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
546128900-13249-DTLSB-04_05_2022-SVCROAD-1^07216001.0031002 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
71056031-46749-DTLSB-04_05_2022-GO95MLD-1^07216001.0031009 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
723695900-88049-DTLSB-04_05_2022-ABNDEQPM-1^07216001.0031101 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
707135440-69939-DTLTRT-04_05_2022-GO95TCH-1^07216001.0031203 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
929479640-88149-DETAIL-04_05_2022-SVCROAD-1^07216001.0031204 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
618459040-35949-DTLTRT-04_06_2022-GO95TCH-1^07216001.0031300 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
618459040-35949-DTLTRT-04_06_2022-SVCROAD-1^07216001.0031300 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
85749080-18139-DTLSB-04_06_2022-SVCENTCO-1^07216001.0031400 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
409285081-30739-DTLSB-04_05_2022-GO95MLD-1^07216001.0032001 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
409285081-30739-DTLSB-04_05_2022-GO95TCH-1^07216001.0032001 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
998129741-15963-DTLSB-04_05_2022-ABNDEQPM-1^07216001.0032004 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
275793290-33439-DTLSB-04_05_2022-GO95MLD-1^07216001.0032005 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
359078421-82359-DTLSB-04_05_2022-GO95MLD-1^07216001.0032101 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
756988471-48549-DTLSB-04_05_2022-GO95TCH-1^07216001.0032103 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2025-04-05 | 2
383204030-27739-DTLSB-04_06_2022-GO95MLD-1^07216001.0032203 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
383204030-27739-DTLSB-04_06_2022-GO95TCH-1^07216001.0032203 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
75749790-38259-DTLSB-04_07_2022-GO95MLD-1^07216001.0033107 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
547525541-10939-DTLSB-04_07_2022-GO95HV-1^07216001.0033108 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
547525541-10939-DTLSB-04_07_2022-GO95MLD-1^07216001.0033108 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
527433081-95249-DTLSB-04_12_2022-GO95MLD-1^07216001.0033202 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
423181477-55477-DETAIL-04_14_2022-GUYSLACK-1^07216001.0101206 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
457771640-34859-DETAIL-04_14_2022-GUYLOINS-1^07216001.0101208 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
69795081-3449-DETAIL-04_13_2022-GO95MLD-1^07216001.0101302 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
201490084-70259-DETAIL-04_21_2022-GO95MLD-1^07216001.0101700 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
43968711-6539-DETAIL-04_19_2022-GO95HV-1^07216001.0101800 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
43968711-6539-DETAIL-04_19_2022-GO95MLD-1^07216001.0101800 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
495829981-68859-DETAIL-04_13_2022-GUYLOINS-1^07216001.0102300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
777114471-88859-DETAIL-04_14_2022-GO95TCH-1^07216001.0102302 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
824903080-37739-DTLSB-04_12_2022-GO95MLD-1^07216001.0034004 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
959342480-75259-DTLSB-04_07_2022-ABNDEQPM-1^07216001.0034005 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
137075870-23239-DTLSB-04_07_2022-GO95MLD-1^07216001.0034101 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
961548992-24253-DTLSB-04_07_2022-GO95HV-1^07216001.0034803 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
743429338-42831-DTLSB-04_06_2022-GO95MLD-1^07216001.0035000 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
89854838-63559-DTLSB-04_06_2022-GO95HV-1^07216001.0035402 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
89854838-63559-DTLSB-04_06_2022-GO95MLD-1^07216001.0035402 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
349586703-73690-DTLSB-04_06_2022-GO95HV-1^07216001.0035441 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
372626061-66420-DETAIL-04_13_2022-SVCNEUT-1^07216001.0102304 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
586586881-61749-DETAIL-04_19_2022-GO95HV-1^07216001.0102305 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
851357051-19859-DETAIL-04_19_2022-GUYHINS-1^07216001.0102306 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
629097602-88549-DETAIL-04_19_2022-GO95TCH-1^07216001.0102502 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
83275717-28717-DETAIL-04_13_2022-GO95MLD-1^07216001.0102503 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
342518588-12688-DETAIL-04_27_2022-GO95MLD-1^07216001.0102507 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
342518588-12688-DETAIL-04_27_2022-GO95TCH-1^07216001.0102507 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
342518588-12688-DETAIL-04_27_2022-SVCENTCO-1^07216001.0102507 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
349586703-73690-DTLSB-04_06_2022-GO95MLD-1^07216001.0035441 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
453964176-66449-DTLSB-04_06_2022-GO95MLD-1^07216001.0035501 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
178862102-72439-DTLSB-04_07_2022-GO95MLD-1^07216001.0035503 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
786594635-45352-DTLSB-04_07_2022-GUYNOINS-1^07216001.0035541 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
713929122-34839-DTLTRT-04_07_2022-RISEBKSP-1^07216001.0035605 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
713929122-34839-DTLTRT-04_07_2022-SVCNEUT-1^07216001.0035605 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
94336832-1739-DTLSB-04_07_2022-GO95MLD-1^07216001.0035606 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
379137445-65559-DTLSB-04_07_2022-GUYSLACK-1^07216001.0035640 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
342518588-12688-DETAIL-04_27_2022-SVCROAD-1^07216001.0102507 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
218613371-81949-DETAIL-04_27_2022-GO95MLD-1^07216001.0102602 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
218613371-81949-DETAIL-04_27_2022-SVCENTCO-1^07216001.0102602 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
567739751-3649-DETAIL-04_27_2022-GO95MLD-1^07216001.0102603 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
348267374-62159-DETAIL-04_21_2022-GO95HV-1^07216001.0102701 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
655690392-59849-DETAIL-04_19_2022-GO95MLD-1^07216001.0102803 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
148107054-159-DETAIL-04_19_2022-GO95HV-1^07216001.0102806 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
766080121-90439-DETAIL-04_19_2022-GO95MLD-1^07216001.0102900 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
578740141-38859-DETAIL-04_13_2022-ABNDEQPM-1^07216001.0103303 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
235156091-99539-DETAIL-04_13_2022-CLMBHAZ-1^07216001.0103304 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
235156091-99539-DETAIL-04_13_2022-GO95MLD-1^07216001.0103304 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
235156091-99539-DETAIL-04_13_2022-GO95TCH-1^07216001.0103304 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
847185651-60149-DETAIL-04_19_2022-GO95HV-1^07216001.0103401 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
129508710-96859-DETAIL-04_13_2022-ABNDEQPM-1^07216001.0103501 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
129508710-96859-DETAIL-04_13_2022-GUYSLACK-1^07216001.0103501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
785190342-91939-DETAIL-04_19_2022-GO95MLD-1^07216001.0103602 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
708843742-69439-DTLSB-04_07_2022-GO95HV-1^07216001.0035701 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
708843742-69439-DTLSB-04_07_2022-GO95MLD-1^07216001.0035701 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
841251062-27522-DTLSB-04_07_2022-GO95HV-1^07216001.0035804 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
841251062-27522-DTLSB-04_07_2022-GO95MLD-1^07216001.0035804 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
838489252-26322-DTLSB-04_07_2022-GUYNOINS-1^07216001.0035805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
943691362-28413-DTLSB-04_07_2022-CLRTOUCH-1^07216001.0035806 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
288674312-6330-DTLSB-04_07_2022-GO95MLD-1^07216001.0035807 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
646585012-88361-DTLSB-04_07_2022-GO95MLD-1^07216001.0035808 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
278472522-27320-DTLSB-04_07_2022-SVCROAD-1^07216001.0035901 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
81279208-37939-DTLSB-04_13_2022-GO95MLD-1^07216001.0036201 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
757543068-34559-DTLSB-04_11_2022-GRDRODHI-1^07216001.0036400 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
874228268-58439-DTLSB-04_11_2022-GO95MLD-1^07216001.0036403 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
303831658-45349-DTLSB-04_11_2022-GO95MLD-1^07216001.0036404 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
673886051-17839-DTLSB-04_06_2022-GO95HV-1^07216001.0036503 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
487949101-47559-DTLSB-04_11_2022-GO95TCH-1^07216001.0036601 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
875399281-58859-DTLSB-04_12_2022-GO95MLD-1^07216001.0036700 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
370792672-28059-DTLSB-04_12_2022-GO95MLD-1^07216001.0036701 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
941416398-14003-DTLSB-04_12_2022-GO95HV-1^07216001.0037302 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
332321648-74639-DTLSB-04_11_2022-GO95TCH-1^07216001.0037303 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
246646478-9639-DTLTRT-04_12_2022-GO95TCH-1^07216001.0037401 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
310249448-64739-DTLSB-04_11_2022-GRDRODHI-1^07216001.0037500 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
111116731-77239-DTLTRT-04_11_2022-GRDRODHI-1^07216001.0037502 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
227008921-37349-DTLTRT-04_11_2022-GO95MLD-1^07216001.0037601 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
73396236-84559-DTLSB-04_12_2022-GO95MLD-1^07216001.0037700 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
603954089-42863-DTLSB-04_12_2022-GO95HV-1^07216001.0037701 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
445453601-46301-DTLSB-04_11_2022-GO95MLD-1^07216001.0037703 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
875332252-37749-DTLSB-04_12_2022-SVCROAD-1^07216001.0037704 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
861609376-73476-DTLSB-04_12_2022-GO95MLD-1^07216001.0038302 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
109104752-54559-DTLSB-04_12_2022-GO95HV-1^07216001.0038500 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
701929352-12259-DTLSB-04_12_2022-GO95MLD-1^07216001.0038600 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
210244082-87349-DTLSB-04_12_2022-GO95HV-1^07216001.0038701 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
754529072-8859-DTLSB-04_12_2022-CLMBHAZ-1^07216001.0038702 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
754529072-8859-DTLSB-04_12_2022-GO95MLD-1^07216001.0038702 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
799977582-59682-DTLSB-04_11_2022-GO95TCH-1^07216001.0038800 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
78580211-52010-DTLSB-04_12_2022-GO95MLD-1^07216001.0039602 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2025-04-12 | 2
164316091-14459-DTLSB-04_12_2022-ABNDEQPM-1^07216001.0039605 | OTHER | CA-NON-TIER | Distribution | 2022-04-12 | 2027-04-12 | 3
608515341-80921-DTLSB-04_11_2022-GO95MLD-1^07216001.0039607 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
608515341-80921-DTLSB-04_11_2022-GUYHINS-1^07216001.0039607 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
527453561-57011-DTLSB-04_11_2022-GO95TCH-1^07216001.0039703 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
527453561-57011-DTLSB-04_11_2022-GUYHINS-1^07216001.0039703 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
999886894-1059-DETAIL-04_21_2022-GO95HV-1^07216001.0103705 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
747953152-81551-DETAIL-04_26_2022-GO95HV-1^07216001.0104001 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
747953152-81551-AUDIT-05_11_2022-GO95MLD-1^07216001.0104001 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
563436832-22861-DETAIL-04_25_2022-GO95HV-1^07216001.0104002 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
798102931-89859-ADMIN-10_23_2023-POLEDERP-1^07216001.0104301 | POLE | CA-NON-TIER | Distribution | 2023-10-23 | 2026-10-23 | 2
243972491-959-DETAIL-04_19_2022-SVCENTCO-1^07216001.0104303 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
492594621-20959-DETAIL-04_13_2022-SVCROAD-1^07216001.0104304 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
283694211-25949-DETAIL-04_19_2022-GO95HV-1^07216001.0104400 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
283694211-25949-DETAIL-04_19_2022-GO95MLD-1^07216001.0104400 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
545036201-8059-DETAIL-04_19_2022-GO95HV-1^07216001.0104401 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
445518691-3159-DETAIL-04_20_2022-GO95MLD-1^07216001.0104701 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
800669632-24539-DETAIL-04_20_2022-GUYHINS-1^07216001.0104702 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
577455264-56159-DETAIL-04_20_2022-GO95HV-1^07216001.0104803 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
243782051-89049-DETAIL-04_20_2022-GO95TCH-1^07216001.0104902 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
59163124-63549-DETAIL-04_14_2022-GO95HV-1^07216001.0105201 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
59163124-63549-DETAIL-04_14_2022-GO95MLD-1^07216001.0105201 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
477430582-90739-DETAIL-04_14_2022-GO95MLD-1^07216001.0105301 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
666244874-41159-DETAIL-04_19_2022-GO95MLD-1^07216001.0105303 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
788223552-15449-DETAIL-04_14_2022-GO95MLD-1^07216001.0105309 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
337459831-51549-DETAIL-04_20_2022-GO95MLD-1^07216001.0105801 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
713971761-15159-DETAIL-04_20_2022-GO95MLD-1^07216001.0105901 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
724144755-17755-DETAIL-04_26_2022-GO95MLD-1^07216001.0106000 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
536058432-19839-DETAIL-04_14_2022-GO95MLD-1^07216001.0106302 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
46668694-8959-DETAIL-04_14_2022-GO95MLD-1^07216001.0106303 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
527453561-57011-DTLSB-04_11_2022-SVCROAD-1^07216001.0039703 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
661428382-4593-DTLSB-04_11_2022-GO95MLD-1^07216001.0039801 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
661428382-4593-DTLSB-04_11_2022-SVCROAD-1^07216001.0039801 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
163162351-93300-DTLSB-04_11_2022-GO95MLD-1^07216001.0039802 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
330764226-10770-DTLSB-04_11_2022-GO95MLD-1^07216001.0039803 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
228929106-37760-DTLSB-04_11_2022-GO95HV-1^07216001.0039804 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2027-04-11 | 3
228929106-37760-DTLSB-04_11_2022-SVCRUBLG-1^07216001.0039804 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
391576455-8455-DTLSB-04_11_2022-GO95MLD-1^07216001.0039902 | OTHER | CA-NON-TIER | Distribution | 2022-04-11 | 2025-04-11 | 2
616892034-65449-DETAIL-04_14_2022-GO95MLD-1^07216001.0106402 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
150952328-33328-DETAIL-04_25_2022-GO95MLD-1^07216001.0107040 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
811508781-24732-DETAIL-04_25_2022-GO95MLD-1^07216001.0107100 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
741133091-65631-DETAIL-04_19_2022-ABNDEQPM-1^07216001.0107104 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
741133091-65631-DETAIL-04_19_2022-GO95CL10-1^07216001.0107104 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
69676121-4190-DETAIL-04_25_2022-GO95HV-1^07216001.0107105 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
434045222-80049-DETAIL-04_20_2022-GO95MLD-1^07216001.0107700 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
214497141-68149-DETAIL-04_20_2022-CLMBHAZ-1^07216001.0107804 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
905052695-7059-DTLSB-04_04_2022-GO95HV-1^07216001.0046301 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
707888945-49439-DTLSB-04_04_2022-SVCNEUT-1^07216001.0046302 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
24935325-17539-DTLSB-04_04_2022-GO95MLD-1^07216001.0047201 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
24935325-17539-DTLSB-04_04_2022-GUYHINS-1^07216001.0047201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
503680395-6039-DTLSB-04_04_2022-ABNDEQPM-1^07216001.0047205 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
503680395-6039-DTLSB-04_04_2022-GO95MLD-1^07216001.0047205 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
503680395-6039-AUDIT-05_12_2022-SVCNEUT-1^07216001.0047205 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
336323395-38339-DTLSB-04_06_2022-GO95MLD-1^07216001.0047500 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
504285983-47059-DTLSB-04_04_2022-GO95HV-1^07216001.0048101 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
148757745-94059-DTLSB-04_04_2022-GO95MLD-1^07216001.0048102 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
159508756-64059-DTLSB-04_04_2022-GO95MLD-1^07216001.0048103 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
698931825-36749-DTLSB-04_04_2022-GO95CL10-1^07216001.0048105 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
319625485-87249-DTLSB-04_07_2022-CLRTOUCH-1^07216001.0048300 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
319625485-87249-DTLSB-04_07_2022-GO95SVC-1^07216001.0048300 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
997977465-99359-DTLSB-04_06_2022-GO95HV-1^07216001.0048402 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
838939475-54849-DTLSB-04_06_2022-GO95MLD-1^07216001.0048601 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2025-04-06 | 2
439829255-24059-DTLSB-04_04_2022-SVCROAD-1^07216001.0049001 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
418109715-17859-DTLSB-04_04_2022-CLMBHAZ-1^07216001.0049002 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
82949115-62949-DTLSB-04_04_2022-GO95HV-1^07216001.0049006 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2027-04-04 | 3
82949115-62949-DTLSB-04_04_2022-GO95TCH-1^07216001.0049006 | OTHER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
605324555-89149-DTLSB-04_05_2022-GO95HV-1^07216001.0049101 | OTHER | CA-NON-TIER | Distribution | 2022-04-05 | 2027-04-05 | 3
338436336-32249-DTLSB-04_07_2022-GO95HV-1^07216001.0049202 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
585982485-50239-DTLSB-04_07_2022-GO95MLD-1^07216001.0049203 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
4408646-11349-DTLSB-04_07_2022-GO95MLD-1^07216001.0049204 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2025-04-07 | 2
214497141-68149-DETAIL-04_20_2022-GO95HV-1^07216001.0107804 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
214497141-68149-DETAIL-04_20_2022-GO95MLD-1^07216001.0107804 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
214497141-68149-DETAIL-04_20_2022-GO95TCH-1^07216001.0107804 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
440218724-97890-DETAIL-04_21_2022-GO95HV-1^07216001.0108002 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
163072965-85949-DETAIL-04_20_2022-GO95HV-1^07216001.0108003 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
163072965-85949-DETAIL-04_20_2022-GO95MLD-1^07216001.0108003 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
213722613-67613-DETAIL-04_19_2022-CLRTOUCH-1^07216001.0108100 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
618078062-27331-DETAIL-04_19_2022-GO95MLD-1^07216001.0108102 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
606931011-61271-DTLSB-04_06_2022-GO95HV-1^07216001.0049301 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
373768600-85155-DTLSB-04_06_2022-GO95HV-1^07216001.0049304 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
978618895-6349-AUDIT-04_19_2022-GO95CL10-1^07216001.0049306 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
109317005-7049-DTLSB-04_06_2022-GO95HV-1^07216001.0049501 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
877564105-39359-DTLSB-04_06_2022-GO95HV-1^07216001.0049504 | OTHER | CA-NON-TIER | Distribution | 2022-04-06 | 2027-04-06 | 3
825490209-91482-ADMIN-04_07_2023-DISTHDWR-1^07216001.0093204 | CONNECTION DEVICE | CA-NON-TIER | Distribution | 2023-04-07 | 2026-04-07 | 2
469223797-61268-DETAIL-04_14_2022-GO95HV-1^07216001.0100000 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
628307011-93859-DETAIL-04_14_2022-GO95MLD-1^07216001.0100001 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
618078062-27331-DETAIL-04_19_2022-SVCNEUT-1^07216001.0108102 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
85655731-30573-DETAIL-04_19_2022-GO95HV-1^07216001.0108103 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
564080229-90229-DETAIL-04_20_2022-GUYHINS-1^07216001.0108600 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
316023704-79760-DETAIL-04_21_2022-GO95TCH-1^07216001.0109101 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
797274604-35582-DETAIL-04_21_2022-GO95HV-1^07216001.0109200 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
53081321-28550-DETAIL-04_19_2022-ABNDEQPM-1^07216001.0109202 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
391214785-52740-DETAIL-04_26_2022-CLRTOUCH-1^07216001.0150300 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
22214444-37950-DETAIL-04_26_2022-GO95MLD-1^07216001.0150402 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
152011765-40890-DETAIL-04_26_2022-GO95MLD-1^07216001.0150602 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
307686035-26750-DETAIL-04_22_2022-CLRTOPOL-1^07216001.0151001 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
263125424-89500-DETAIL-04_22_2022-GO95MLD-1^07216001.0151100 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
13826485-6679-DETAIL-04_22_2022-GO95MLD-1^07216001.0151201 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
359497125-6800-DETAIL-04_22_2022-GO95HV-1^07216001.0151503 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
359497125-6800-DETAIL-04_22_2022-GO95MLD-1^07216001.0151503 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
213361794-65650-DETAIL-04_22_2022-CLMBHAZ-1^07216001.0151505 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
923880464-15632-DETAIL-04_22_2022-GO95HV-1^07216001.0151508 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
506743704-30049-DETAIL-04_22_2022-SVCROAD-1^07216001.0151603 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
79841625-64010-DETAIL-04_22_2022-GO95HV-1^07216001.0152000 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
79841625-64010-DETAIL-04_22_2022-GO95MLD-1^07216001.0152000 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
816390334-51152-DETAIL-04_22_2022-GO95MLD-1^07216001.0152002 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
83635845-21620-DETAIL-04_25_2022-GO95MLD-1^07216001.0152201 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
694692835-84291-DETAIL-04_25_2022-GO95MLD-1^07216001.0152205 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
633960505-1451-DETAIL-04_25_2022-GO95TCH-1^07216001.0152300 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
79186825-3410-DETAIL-04_25_2022-GO95MLD-1^07216001.0152401 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
715352980-75249-DETAIL-04_14_2022-GO95MLD-1^07216001.0100102 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
715352980-75249-DETAIL-04_14_2022-SVCNEUT-1^07216001.0100102 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
329415871-51549-DETAIL-04_14_2022-GO95MLD-1^07216001.0100201 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
953537638-8638-DETAIL-04_14_2022-GO95MLD-1^07216001.0100202 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
60033401-61739-DETAIL-04_13_2022-GO95MLD-1^07216001.0100300 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
241127611-82259-DETAIL-04_13_2022-GRDRODHI-1^07216001.0100400 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
545495730-22949-DETAIL-04_13_2022-SVCNEUT-1^07216001.0100403 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
427667164-46059-DETAIL-04_13_2022-GO95HV-1^07216001.0100700 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
338140182-48049-DETAIL-04_13_2022-GO95MLD-1^07216001.0100801 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
338140182-48049-DETAIL-04_13_2022-RISEBKSP-1^07216001.0100801 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
616347421-29949-DETAIL-04_13_2022-GRDRODHI-1^07216001.0100900 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
641873862-44761-DETAIL-04_13_2022-GO95MLD-1^07216001.0100904 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
73149358-40458-DETAIL-04_14_2022-GO95MLD-1^07216001.0101204 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
73149358-40458-DETAIL-04_14_2022-SVCNEUT-1^07216001.0101204 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
423181477-55477-DETAIL-04_14_2022-GO95MLD-1^07216001.0101206 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
183823461-14859-DETAIL-04_14_2022-SVCROAD-1^07216001.0101207 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
569855791-66649-DETAIL-04_13_2022-GO95HV-1^07216001.0101300 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
569855791-66649-DETAIL-04_13_2022-GO95MLD-1^07216001.0101300 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
69795081-3449-DETAIL-04_13_2022-SVCNEUT-1^07216001.0101302 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
69795081-3449-DETAIL-04_13_2022-SVCROAD-1^07216001.0101302 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
468288910-35739-DETAIL-04_13_2022-GO95MLD-1^07216001.0101400 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
468288910-35739-DETAIL-04_13_2022-GRDRODHI-1^07216001.0101400 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
524053923-63923-DETAIL-04_13_2022-GUYHINS-1^07216001.0101402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
496424923-34923-DETAIL-04_13_2022-GUYHINS-1^07216001.0101403 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
133566290-13449-DETAIL-04_13_2022-GO95MLD-1^07216001.0101440 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
323781251-6970-ADMIN-10_23_2023-POLEDERP-1^07216001.0101502 | POLE | CA-NON-TIER | Distribution | 2023-10-23 | 2026-10-23 | 2
201490084-70259-DETAIL-04_21_2022-GO95HV-1^07216001.0101700 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
929822971-30639-DETAIL-04_13_2022-GO95MLD-1^07216001.0102301 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
22312951-44050-DETAIL-04_19_2022-GUYLOINS-1^07216001.0102303 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
372626061-66420-DETAIL-04_13_2022-GO95HV-1^07216001.0102304 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2027-04-13 | 3
372626061-66420-DETAIL-04_13_2022-GO95MLD-1^07216001.0102304 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
586586881-61749-DETAIL-04_19_2022-SVCROAD-1^07216001.0102305 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
890645684-41159-DETAIL-04_25_2022-GO95TCH-1^07216001.0152402 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
875888658-93138-DETAIL-04_26_2022-GO95HV-1^07216001.0152600 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
502991386-82881-DETAIL-04_25_2022-ANCHIDLE-1^07216001.0152602 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
502991386-82881-DETAIL-04_25_2022-GO95MLD-1^07216001.0152602 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
241920105-87180-DETAIL-04_25_2022-GO95MLD-1^07216001.0152701 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
634414486-71751-DETAIL-04_25_2022-GO95HV-1^07216001.0152702 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
634414486-71751-DETAIL-04_25_2022-GO95MLD-1^07216001.0152702 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
655025305-7891-DETAIL-04_25_2022-GRDRODHI-1^07216001.0152800 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
958454420-10049-DETAIL-04_19_2022-GO95MLD-1^07216001.0102400 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
629097602-88549-DETAIL-04_19_2022-GO95HV-1^07216001.0102502 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
629097602-88549-DETAIL-04_19_2022-GO95MLD-1^07216001.0102502 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
629097602-88549-DETAIL-04_19_2022-SVCNEUT-1^07216001.0102502 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
828818481-90159-DETAIL-04_27_2022-GO95HV-1^07216001.0102506 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
828818481-90159-DETAIL-04_27_2022-GO95MLD-1^07216001.0102506 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
865547182-1349-DETAIL-04_19_2022-GO95MLD-1^07216001.0102600 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
567739751-3649-DETAIL-04_27_2022-GO95TCH-1^07216001.0102603 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
567739751-3649-DETAIL-04_27_2022-SVCROAD-1^07216001.0102603 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
348267374-62159-DETAIL-04_21_2022-GO95MLD-1^07216001.0102701 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
926762191-88059-DETAIL-04_21_2022-GO95MLD-1^07216001.0102702 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
1501351-2159-DETAIL-04_21_2022-GO95MLD-1^07216001.0102705 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
15757992-18059-DETAIL-04_19_2022-GO95MLD-1^07216001.0102801 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
723613831-67139-DETAIL-04_21_2022-GO95MLD-1^07216001.0102802 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
33208314-70339-DETAIL-04_19_2022-ABNDEQPM-1^07216001.0102805 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
33208314-70339-DETAIL-04_19_2022-GO95MLD-1^07216001.0102805 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
262989234-54400-DETAIL-04_21_2022-GO95MLD-1^07216001.0153101 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
29939454-49500-DETAIL-04_21_2022-GO95MLD-1^07216001.0153301 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
253480975-99590-DETAIL-04_21_2022-GO95TCH-1^07216001.0153303 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
638503216-81651-DETAIL-04_21_2022-GO95MLD-1^07216001.0153402 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
756179565-39871-DETAIL-04_21_2022-CLMBHAZ-1^07216001.0153403 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
756179565-39871-DETAIL-04_21_2022-GO95CL10-1^07216001.0153403 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
756179565-39871-DETAIL-04_21_2022-GO95HV-1^07216001.0153403 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
948736054-94323-DETAIL-04_21_2022-GO95HV-1^07216001.0153501 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
170664095-5210-DETAIL-04_21_2022-SVCNEUT-1^07216001.0153602 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
246734344-90880-DETAIL-04_21_2022-GO95TCH-1^07216001.0153603 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
456522524-11821-DETAIL-04_21_2022-GO95TCH-1^07216001.0153605 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
490200754-79461-DETAIL-04_26_2022-GO95MLD-1^07216001.0153700 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
968048694-29273-DETAIL-04_26_2022-GO95MLD-1^07216001.0153702 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
541256724-10431-DETAIL-04_21_2022-SVCENTCO-1^07216001.0154400 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
825560746-72682-DETAIL-04_21_2022-GO95MLD-1^07216001.0154600 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
460081004-62721-DETAIL-04_26_2022-COPLLEAN-1^07216001.0154802 | POLE | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
148107054-159-DETAIL-04_19_2022-GO95MLD-1^07216001.0102806 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
766080121-90439-DETAIL-04_19_2022-SVCNEUT-1^07216001.0102900 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
600327231-79059-DETAIL-04_19_2022-GUYHINS-1^07216001.0102902 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
612902614-1159-DETAIL-04_19_2022-GO95MLD-1^07216001.0102903 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
318599501-40959-DETAIL-04_13_2022-GUYLOINS-1^07216001.0103301 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
27632891-80739-DETAIL-04_13_2022-GO95MLD-1^07216001.0103302 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
709521904-53551-DETAIL-04_13_2022-GO95MLD-1^07216001.0103500 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
611698902-60159-DETAIL-04_21_2022-ABNDEQPM-1^07216001.0103703 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
999886894-1059-DETAIL-04_21_2022-GO95MLD-1^07216001.0103705 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
662470764-18411-DETAIL-04_21_2022-GO95MLD-1^07216001.0103706 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
887363061-43539-DETAIL-04_14_2022-GO95MLD-1^07216001.0104200 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
530252741-65959-DETAIL-04_19_2022-GO95MLD-1^07216001.0104300 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
492594621-20959-DETAIL-04_13_2022-SVCENTCO-1^07216001.0104304 | OTHER | CA-NON-TIER | Distribution | 2022-04-13 | 2025-04-13 | 2
885035942-12372-DETAIL-04_20_2022-GO95MLD-1^07216001.0104600 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
800669632-24539-DETAIL-04_20_2022-SVCENTCO-1^07216001.0104702 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
577455264-56159-DETAIL-04_20_2022-GUYSLACK-1^07216001.0104803 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
645348101-55159-DETAIL-04_20_2022-GO95MLD-1^07216001.0104900 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
185842722-69520-DETAIL-04_25_2022-GO95HV-1^07216001.0105002 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
185842722-69520-DETAIL-04_25_2022-GO95MLD-1^07216001.0105002 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
571419842-64271-DETAIL-04_25_2022-GO95HV-1^07216001.0105004 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
488130684-81659-DETAIL-04_14_2022-GO95HV-1^07216001.0105200 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
488130684-81659-DETAIL-04_14_2022-GO95MLD-1^07216001.0105200 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
477430582-90739-DETAIL-04_14_2022-GO95TCH-1^07216001.0105301 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
334915924-25449-DETAIL-04_14_2022-RISEBKSP-1^07216001.0105305 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
460081004-62721-DETAIL-04_26_2022-GO95HV-1^07216001.0154802 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
667558724-90531-DETAIL-04_26_2022-GO95MLD-1^07216001.0154901 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
962775531-54653-DETAIL-04_26_2022-ABNDEQPM-1^07216001.0154903 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
962775531-54653-DETAIL-04_26_2022-GO95HV-1^07216001.0154903 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
511165342-58491-DETAIL-04_26_2022-SVCROAD-1^07216001.0154906 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
469501444-97031-DETAIL-04_21_2022-CLRTOUCH-1^07216001.0155401 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
425831946-56880-DETAIL-04_21_2022-GO95HV-1^07216001.0155500 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
425831946-56880-DETAIL-04_21_2022-GO95MLD-1^07216001.0155500 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
642284935-71061-DETAIL-04_26_2022-GO95MLD-1^07216001.0155802 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
642284935-71061-DETAIL-04_26_2022-SVCENTCO-1^07216001.0155802 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
163198634-55300-DETAIL-04_26_2022-GO95MLD-1^07216001.0155901 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
15581712-84289-DETAIL-04_25_2022-GO95TCH-1^07216001.0155904 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
658280194-28059-ADMIN-10_13_2023-POLEDERP-1^07216001.0156400 | POLE | CA-NON-TIER | Distribution | 2023-10-13 | 2026-10-13 | 2
459432526-27221-DETAIL-04_22_2022-GO95MLD-1^07216001.0156500 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
186143154-51720-DETAIL-04_22_2022-GO95HV-1^07216001.0156603 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
695887262-40501-DETAIL-04_26_2022-GO95MLD-1^07216001.0156900 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
337459831-51549-DETAIL-04_20_2022-GO95HV-1^07216001.0105801 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
11162591-25849-DETAIL-04_20_2022-GO95MLD-1^07216001.0105802 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
49172061-25159-DETAIL-04_20_2022-GUYLOINS-1^07216001.0105900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
713971761-15159-DETAIL-04_20_2022-SVCYARD-1^07216001.0105901 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
828602351-40449-DETAIL-04_20_2022-GO95MLD-1^07216001.0105902 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
828602351-40449-DETAIL-04_20_2022-GO95TCH-1^07216001.0105902 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
670120261-25049-DETAIL-04_14_2022-GO95MLD-1^07216001.0106306 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
670120261-25049-DETAIL-04_14_2022-GO95TCH-1^07216001.0106306 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
670120261-25049-DETAIL-04_14_2022-SVCNEUT-1^07216001.0106306 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
805111854-81649-DETAIL-04_14_2022-GO95MLD-1^07216001.0106400 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
337347041-84549-DETAIL-04_20_2022-GO95CL10-1^07216001.0106803 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
337347041-84549-DETAIL-04_20_2022-GO95MLD-1^07216001.0106803 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
3621522-68609-DETAIL-04_25_2022-SVCRUBLG-1^07216001.0107000 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
760102291-67681-DETAIL-04_25_2022-SVCYARD-1^07216001.0107003 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
904888035-85275-DETAIL-04_25_2022-GO95MLD-1^07216001.0107004 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
964776471-52863-DETAIL-04_25_2022-GO95HV-1^07216001.0107005 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
921720345-72522-DETAIL-04_22_2022-GO95MLD-1^07216001.0157601 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
801234041-82093-DETAIL-04_22_2022-GO95MLD-1^07216001.0157602 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
335413704-56449-DETAIL-04_20_2022-CLMBHAZ-1^07216001.0157800 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
335413704-56449-DETAIL-04_20_2022-GO95MLD-1^07216001.0157800 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
826608795-57482-DETAIL-04_20_2022-GO95HV-1^07216001.0158800 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
908137595-84362-DETAIL-04_20_2022-GO95MLD-1^07216001.0158801 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
701521685-44521-DETAIL-04_20_2022-GRDRODHI-1^07216001.0158803 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
745099825-61841-DETAIL-04_20_2022-GO95MLD-1^07216001.0158900 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
821387821-2562-DETAIL-04_25_2022-ANCHIDLE-1^07216001.0107006 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
821387821-2562-DETAIL-04_25_2022-GO95MLD-1^07216001.0107006 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
150952328-33328-DETAIL-04_25_2022-GRDRODHI-1^07216001.0107040 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
150952328-33328-DETAIL-04_25_2022-GUYLOINS-1^07216001.0107040 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
361317871-74900-DETAIL-04_25_2022-RISEBKSP-1^07216001.0107102 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
741133091-65631-DETAIL-04_19_2022-GO95HV-1^07216001.0107104 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
741133091-65631-DETAIL-04_19_2022-GO95MLD-1^07216001.0107104 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
741133091-65631-DETAIL-04_19_2022-XARMSPCR-1^07216001.0107104 | CROSSARM | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
938375244-15992-DETAIL-04_19_2022-GO95HV-1^07216001.0107200 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
860113444-61649-DETAIL-04_14_2022-GO95MLD-1^07216001.0107400 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2025-04-14 | 2
407008281-83239-DETAIL-04_20_2022-GO95STUB-1^07216001.0107800 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
573059294-8159-DETAIL-04_20_2022-ABNDEQPM-1^07216001.0107802 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
317197381-87159-DETAIL-04_20_2022-GO95HV-1^07216001.0107805 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
585703222-48891-DETAIL-04_19_2022-GO95MLD-1^07216001.0108000 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
88841222-3020-DETAIL-04_19_2022-GO95HV-1^07216001.0108001 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
163072965-85949-DETAIL-04_20_2022-SVCNEUT-1^07216001.0108003 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
213722613-67613-DETAIL-04_19_2022-GO95HV-1^07216001.0108100 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
213722613-67613-DETAIL-04_19_2022-GO95MLD-1^07216001.0108100 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2025-04-19 | 2
761714404-17481-DETAIL-04_21_2022-GO95TCH-1^07216001.0108101 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
724881744-30749-DETAIL-04_19_2022-GO95HV-1^07216001.0108201 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
903194924-39442-DETAIL-04_19_2022-GO95CL10-1^07216001.0108202 | OTHER | CA-NON-TIER | Distribution | 2022-04-19 | 2027-04-19 | 3
214948614-84450-DETAIL-04_21_2022-GO95HV-1^07216001.0109100 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
214948614-84450-DETAIL-04_21_2022-GO95MLD-1^07216001.0109100 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
316023704-79760-DETAIL-04_21_2022-GO95MLD-1^07216001.0109101 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
316023704-79760-DETAIL-04_21_2022-SVCNEUT-1^07216001.0109101 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
391214785-52740-DETAIL-04_26_2022-GO95MLD-1^07216001.0150300 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
899133444-35422-DETAIL-04_26_2022-GO95MLD-1^07216001.0150303 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
899133444-35422-DETAIL-04_26_2022-SVCENTCO-1^07216001.0150303 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
466816945-13531-DETAIL-04_26_2022-GO95MLD-1^07216001.0150304 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
388404115-13938-DETAIL-04_26_2022-GO95MLD-1^07216001.0150400 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
709685544-27451-DETAIL-04_22_2022-GO95MLD-1^07216001.0150503 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
366190466-97110-DETAIL-04_22_2022-GO95MLD-1^07216001.0150601 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
152011765-40890-DETAIL-04_26_2022-GO95TCH-1^07216001.0150602 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
307686035-26750-DETAIL-04_22_2022-GUYSLACK-1^07216001.0151001 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
5996075-13619-DETAIL-04_22_2022-GO95MLD-1^07216001.0151002 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
5996075-13619-DETAIL-04_22_2022-GO95MLD-2^07216001.0151002 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
5996075-13619-DETAIL-04_22_2022-GUYHINS-1^07216001.0151002 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
380111945-31630-DETAIL-04_22_2022-GO95MLD-1^07216001.0151004 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
380111945-31630-DETAIL-04_22_2022-GO95TCH-1^07216001.0151004 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
13826485-6679-DETAIL-04_22_2022-GUYHINS-1^07216001.0151201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
298129265-39840-DETAIL-04_20_2022-GO95MLD-1^07216001.0158901 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
298129265-39840-DETAIL-04_20_2022-GO95TCH-1^07216001.0158901 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
208072121-3393-DETAIL-04_20_2022-SVCROAD-1^07216001.0159801 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
728793095-77701-DETAIL-04_20_2022-GO95MLD-1^07216001.0159803 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
308837214-33750-DTLSB-07_14_2022-ABNDEQPM-1^07216001.0210606 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2027-07-14 | 3
937705624-30692-DTLSB-07_13_2022-SVCROAD-1^07216001.0210701 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
683739804-81771-DTLSB-07_13_2022-SVCROAD-1^07216001.0210710 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
604108903-54811-DTLSB-07_14_2022-GO95MLD-1^07216001.0210801 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
230666215-69770-DTLSB-07_14_2022-GO95HV-1^07216001.0211540 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2027-07-14 | 3
733998634-3049-DTLSB-07_13_2022-GO95MLD-1^07216001.0211605 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
632502166-73166-DTLSB-07_14_2022-GO95MLD-1^07216001.0212400 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
661032044-99511-DTLSB-07_14_2022-GO95MLD-1^07216001.0212601 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
877037821-96128-DTLSB-07_13_2022-GO95MLD-1^07216001.0212602 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
672510475-58059-DTLSB-07_14_2022-ABNDEQPM-1^07216001.0212640 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2027-07-14 | 3
70523595-42890-DTLSB-07_14_2022-GO95MLD-1^07216001.0212700 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
193930821-65928-DTLSB-07_14_2022-GO95MLD-1^07216001.0212701 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
86510443-8320-DTLSB-07_13_2022-GO95MLD-1^07216001.0213601 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
289949921-93428-DTLSB-07_13_2022-SVCROAD-1^07216001.0213604 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
979035221-92103-DTLSB-07_13_2022-GUYNOINS-2^07216001.0213700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
254320431-62090-DTLSB-07_13_2022-GO95HV-1^07216001.0213703 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
463685691-90431-DTLSB-07_13_2022-GUYNOINS-1^07216001.0213800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
463685691-90431-DTLSB-07_13_2022-GUYNOINS-2^07216001.0213800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
449976831-97220-DTLSB-07_13_2022-GO95HV-1^07216001.0213801 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
449976831-97220-DTLSB-07_13_2022-GO95MLD-1^07216001.0213801 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
478086705-64141-DETAIL-04_22_2022-SVCNEUT-1^07216001.0151202 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
496542655-16271-DETAIL-04_22_2022-GO95MLD-1^07216001.0151203 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
496542655-16271-DETAIL-04_22_2022-GO95TCH-1^07216001.0151203 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
435760195-78590-DETAIL-04_22_2022-GO95HV-1^07216001.0151205 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
435760195-78590-DETAIL-04_22_2022-GO95MLD-1^07216001.0151205 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
545056915-96839-DETAIL-04_26_2022-GO95HV-1^07216001.0151402 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
545056915-96839-DETAIL-04_26_2022-GO95MLD-1^07216001.0151402 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
883406484-51172-DETAIL-04_22_2022-GO95MLD-1^07216001.0151504 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
449976831-97220-DTLSB-07_13_2022-GUYSLACK-1^07216001.0213801 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
795106853-58572-DTLSB-07_13_2022-GO95TCH-1^07216001.0214504 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
419714643-44770-DTLSB-07_13_2022-GO95HV-1^07216001.0214505 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
419714643-44770-DTLSB-07_13_2022-GUYSLACK-1^07216001.0214505 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
10847101-80869-DTLSB-07_13_2022-SVCNEUT-1^07216001.0214803 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
947557011-3223-DTLSB-07_13_2022-GO95MLD-1^07216001.0214804 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
980232592-72620-DTLSB-07_13_2022-GO95MLD-1^07216001.0215300 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
801211090-17722-DTLSB-07_13_2022-GO95MLD-1^07216001.0215900 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
761157332-21720-DTLSB-07_13_2022-ABNDEQPM-1^07216001.0215901 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
508142245-45245-DTLSB-07_13_2022-GO95MLD-1^07216001.0215902 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
508142245-45245-DTLSB-07_13_2022-GO95TCH-1^07216001.0215902 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
702412783-9321-DTLSB-07_13_2022-GO95MLD-1^07216001.0215903 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
215622025-65365-DTLSB-07_13_2022-ABNDEQPM-1^07216001.0215920 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
215622025-65365-DTLSB-07_13_2022-GRDRODHI-1^07216001.0215920 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
215622025-65365-DTLSB-07_13_2022-GRDRODHI-2^07216001.0215920 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
544427465-26039-DTLSB-02_21_2023-GO95HV-1^07216001.0280600 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
544427465-26039-DTLSB-02_21_2023-GO95MLD-1^07216001.0280600 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
856954855-6249-DTLSB-02_21_2023-GO95MLD-1^07216001.0280604 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
573024956-52049-DTLSB-02_22_2023-GO95MLD-1^07216001.0280700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
883600687-86418-DTLSB-02_22_2023-GO95HV-1^07216001.0280704 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
883600687-86418-DTLSB-02_22_2023-GO95MLD-1^07216001.0280704 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
973929126-88483-DETAIL-02_21_2023-SVCWIND-1^07216001.0280770 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
189436485-8049-DTLSB-02_21_2023-GO95MLD-1^07216001.0281602 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
189436485-8049-DTLSB-02_21_2023-SVCENTCO-1^07216001.0281602 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
213361794-65650-DETAIL-04_22_2022-GO95MLD-1^07216001.0151505 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
923880464-15632-DETAIL-04_22_2022-ANCHIDLE-1^07216001.0151508 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
923880464-15632-DETAIL-04_22_2022-GO95MLD-1^07216001.0151508 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
913316214-28214-DETAIL-04_22_2022-GO95MLD-1^07216001.0151513 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
694692835-84291-DETAIL-04_25_2022-GUYSLACK-1^07216001.0152205 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
635649605-16751-DETAIL-04_25_2022-SVCROAD-1^07216001.0152302 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
145453425-97080-DETAIL-04_25_2022-GO95MLD-1^07216001.0152304 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
614003508-58070-DETAIL-04_25_2022-GO95HV-1^07216001.0152406 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2027-04-25 | 3
387952004-13640-AUDIT-05_12_2022-GO95MLD-1^07216001.0152502 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
179946614-51720-DETAIL-04_25_2022-GO95MLD-1^07216001.0152505 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
502991386-82881-DETAIL-04_25_2022-SVCNEUT-1^07216001.0152602 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
883387576-80172-DETAIL-04_26_2022-GO95MLD-1^07216001.0152603 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
238751308-32308-DETAIL-04_26_2022-GO95MLD-1^07216001.0152604 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
559395284-29351-DETAIL-04_26_2022-GO95TCH-1^07216001.0152605 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
655025305-7891-DETAIL-04_25_2022-GO95MLD-1^07216001.0152800 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
253480975-99590-DETAIL-04_21_2022-GO95MLD-1^07216001.0153303 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
478108386-5439-DTLSB-02_21_2023-GO95MLD-1^07216001.0281604 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
42210456-15540-DTLSB-02_21_2023-CLMBTRE-1^07216001.0281704 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
42210456-15540-DTLSB-02_21_2023-GO95MLD-1^07216001.0281704 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
635504726-64451-DTLSB-02_21_2023-GO95MLD-1^07216001.0281901 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
165188796-60259-DTLSB-02_21_2023-GO95MLD-1^07216001.0283502 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
200327046-37740-DTLSB-02_21_2023-GO95MLD-1^07216001.0283503 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
372895766-96720-DTLSB-02_21_2023-GO95MLD-1^07216001.0284503 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
989590966-75733-DTLSB-02_21_2023-GO95MLD-1^07216001.0284504 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
948507046-45223-DETAIL-04_21_2022-GO95HV-1^07216001.0153305 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
948507046-45223-DETAIL-04_21_2022-GO95MLD-1^07216001.0153305 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
955729326-41343-DETAIL-04_21_2022-SVCROAD-1^07216001.0153400 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
756179565-39871-DETAIL-04_21_2022-GO95MLD-1^07216001.0153403 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
948736054-94323-DETAIL-04_21_2022-GO95MLD-1^07216001.0153501 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
170664095-5210-DETAIL-04_21_2022-GO95MLD-1^07216001.0153602 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
220187034-160-DETAIL-04_21_2022-GO95MLD-1^07216001.0153604 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
867431284-89212-DETAIL-04_26_2022-POLESTEP-1^07216001.0153701 | POLE | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
44138736-25049-DTLSB-02_22_2023-GO95MLD-1^07216001.0287700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
965392366-32649-DTLSB-02_21_2023-SVCENTCO-1^07216001.0287701 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
282546916-25539-DTLSB-02_21_2023-GO95TCH-1^07216001.0287703 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
70516396-26539-DTLSB-02_21_2023-CLRTOUCH-1^07216001.0287704 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
788226370-97370-DTLSB-02_22_2023-GO95MLD-1^07216001.0288601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
580233085-84649-DTLSB-02_22_2023-GO95MLD-1^07216001.0288700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
549280546-77549-DTLSB-02_22_2023-GO95MLD-1^07216001.0288702 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
385369205-79759-DTLSB-02_22_2023-GO95MLD-1^07216001.0289100 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
998141854-20439-DETAIL-04_21_2022-GO95HV-1^07216001.0153703 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
998141854-20439-DETAIL-04_21_2022-GO95MLD-1^07216001.0153703 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
401164874-29850-ADMIN-10_13_2023-POLEDERP-1^07216001.0153705 | POLE | CA-NON-TIER | Distribution | 2023-10-13 | 2026-10-13 | 2
240350936-58180-DETAIL-04_21_2022-GUYSLACK-1^07216001.0154501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
825560746-72682-DETAIL-04_21_2022-GO95STUB-1^07216001.0154600 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
825560746-72682-DETAIL-04_21_2022-RISEBKSP-1^07216001.0154600 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
65513864-73880-DETAIL-04_21_2022-GO95HV-1^07216001.0154603 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
155141014-5590-DETAIL-04_26_2022-GO95HV-1^07216001.0154800 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
882908585-54939-DTLSB-02_22_2023-GO95MLD-1^07216001.0289102 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
901166670-69098-DTLSB-02_22_2023-GO95HV-1^07216001.0289601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
715538570-10670-DTLSB-02_22_2023-GO95MLD-1^07216001.0289604 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
74397256-37643-DTLSB-02_22_2023-GO95MLD-1^07216001.0289700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
296338233-84339-DETAIL-03_15_2023-CLRTOPOL-1^07216001.0290600 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
285927345-76639-DETAIL-03_13_2023-GO95MLD-1^07216001.0290601 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
75202485-95239-DETAIL-03_15_2023-GO95CL10-1^07216001.0290604 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
622696893-67939-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0290605 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
622696893-67939-DETAIL-03_13_2023-CLRTOPOL-2^07216001.0290605 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
23949206-87158-DETAIL-03_13_2023-CLMBTRE-1^07216001.0290606 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
23949206-87158-DETAIL-03_13_2023-GO95MLD-1^07216001.0290606 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
27951343-55639-DETAIL-03_01_2023-GO95MLD-1^07216001.0290705 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
701607514-4539-DETAIL-03_13_2023-GO95HV-1^07216001.0290707 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
701607514-4539-DETAIL-03_13_2023-GUYHINS-1^07216001.0290707 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
931883049-98759-DETAIL-03_01_2023-SVCENTCO-1^07216001.0290743 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
812843183-94649-DETAIL-03_13_2023-GO95MLD-1^07216001.0290802 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
407191004-5560-DETAIL-04_26_2022-GO95HV-1^07216001.0154801 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
407191004-5560-DETAIL-04_26_2022-GO95MLD-1^07216001.0154801 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
667558724-90531-DETAIL-04_26_2022-GO95HV-1^07216001.0154901 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
691347234-35891-DETAIL-04_26_2022-GO95HV-1^07216001.0154902 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
691347234-35891-DETAIL-04_26_2022-GO95MLD-1^07216001.0154902 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
511165342-58491-DETAIL-04_26_2022-GO95MLD-1^07216001.0154906 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
987291545-45545-DETAIL-04_21_2022-GO95MLD-1^07216001.0155300 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
901367244-34332-DETAIL-04_21_2022-GO95HV-1^07216001.0155400 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
901367244-34332-DETAIL-04_21_2022-GO95MLD-1^07216001.0155400 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
469501444-97031-DETAIL-04_21_2022-GO95HV-1^07216001.0155401 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2027-04-21 | 3
469501444-97031-DETAIL-04_21_2022-GO95MLD-1^07216001.0155401 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
722479955-33481-DETAIL-04_26_2022-GO95MLD-1^07216001.0155702 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
712287755-90451-DETAIL-04_26_2022-GO95HV-1^07216001.0155801 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
712287755-90451-DETAIL-04_26_2022-GO95MLD-1^07216001.0155801 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
642284935-71061-DETAIL-04_26_2022-GO95HV-1^07216001.0155802 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
299728044-71740-DETAIL-04_26_2022-GO95MLD-1^07216001.0155900 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
930444453-52939-DETAIL-03_13_2023-GO95MLD-1^07216001.0290805 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
845084755-18939-DETAIL-03_02_2023-GO95MLD-1^07216001.0290902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
845084755-18939-DETAIL-03_02_2023-GO95MLD-2^07216001.0290902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
83265633-88249-DETAIL-03_15_2023-GO95MLD-1^07216001.0291500 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
83265633-88249-DETAIL-03_15_2023-GUYHINS-1^07216001.0291500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
150328463-3049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291501 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
962610363-23049-DETAIL-03_15_2023-GO95MLD-1^07216001.0291502 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
199421635-19039-DETAIL-03_15_2023-GO95MLD-1^07216001.0291503 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
214311602-44150-DETAIL-04_25_2022-GUYSLACK-1^07216001.0155903 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
638497738-48738-DETAIL-04_26_2022-GO95HV-1^07216001.0155941 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
793816776-17472-DETAIL-04_22_2022-GO95MLD-1^07216001.0156401 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
459432526-27221-DETAIL-04_22_2022-GO95HV-1^07216001.0156500 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
459432526-27221-ADMIN-06_27_2023-POLEDERP-1^07216001.0156500 | POLE | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
841838786-3249-DETAIL-04_22_2022-GO95HV-1^07216001.0156501 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
197870964-10530-DETAIL-04_22_2022-GO95MLD-1^07216001.0156601 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
99544985-79440-DETAIL-04_22_2022-GO95HV-1^07216001.0156604 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
801234041-82093-DETAIL-04_22_2022-GO95HV-1^07216001.0157602 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
210493095-78050-DETAIL-04_22_2022-GO95HV-1^07216001.0157603 | OTHER | CA-NON-TIER | Distribution | 2022-04-22 | 2027-04-22 | 3
210493095-78050-DETAIL-04_22_2022-GUYSLACK-1^07216001.0157603 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
517353394-63501-DETAIL-04_20_2022-GO95HV-1^07216001.0157701 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
585899305-85191-DETAIL-04_20_2022-GO95MLD-1^07216001.0157703 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
335413704-56449-DETAIL-04_20_2022-GO95CL10-1^07216001.0157800 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
233845204-43570-DETAIL-04_20_2022-GO95HV-1^07216001.0157801 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
623081405-3939-DETAIL-03_15_2023-SVCDEFLC-1^07216001.0291506 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
459960559-1859-DETAIL-03_13_2023-SVCENTCO-1^07216001.0291540 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
558577353-63049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291603 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
879541943-24049-DETAIL-03_15_2023-GO95MLD-1^07216001.0291605 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
664123753-3859-DETAIL-03_15_2023-CLRTOPOL-1^07216001.0291606 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
809444713-36049-DETAIL-03_01_2023-GO95MLD-1^07216001.0291702 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
858818363-17649-DETAIL-03_01_2023-GO95MLD-1^07216001.0291707 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
233845204-43570-DETAIL-04_20_2022-GO95MLD-1^07216001.0157801 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
418164074-45949-DETAIL-04_20_2022-GO95MLD-1^07216001.0157900 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
418164074-45949-DETAIL-04_20_2022-SVCNEUT-1^07216001.0157900 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
15804286-25549-DETAIL-04_25_2022-GO95SVC-1^07216001.0158041 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
701521685-44521-DETAIL-04_20_2022-GO95MLD-1^07216001.0158803 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
371359575-65949-DETAIL-04_20_2022-GO95MLD-1^07216001.0158804 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
298129265-39840-DETAIL-04_20_2022-GO95CL10-1^07216001.0158901 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
113527415-87259-DETAIL-04_20_2022-GO95HV-1^07216001.0158902 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
113527415-87259-DETAIL-04_20_2022-GO95MLD-1^07216001.0158902 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
308907855-55750-DETAIL-04_21_2022-GO95MLD-1^07216001.0158903 | OTHER | CA-NON-TIER | Distribution | 2022-04-21 | 2025-04-21 | 2
849753386-8452-DETAIL-04_25_2022-GO95MLD-1^07216001.0159040 | OTHER | CA-NON-TIER | Distribution | 2022-04-25 | 2025-04-25 | 2
99104108-92360-DETAIL-04_22_2022-GUYHINS-1^07216001.0159042 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-22 | 2025-04-22 | 2
29712655-5500-DETAIL-04_20_2022-GO95TCH-1^07216001.0159700 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
626415965-8965-DETAIL-04_20_2022-GO95MLD-1^07216001.0159701 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
208072121-3393-DETAIL-04_20_2022-GO95MLD-1^07216001.0159801 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
461492095-12521-DETAIL-04_20_2022-GO95MLD-1^07216001.0159802 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2025-04-20 | 2
17211054-18549-DETAIL-03_01_2023-SVCNEUT-1^07216001.0291801 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
885032364-55839-DETAIL-03_01_2023-GO95CL10-1^07216001.0291802 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
885032364-55839-DETAIL-03_01_2023-GO95MLD-1^07216001.0291802 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
505698263-23239-DETAIL-03_02_2023-GO95MLD-1^07216001.0291803 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
628960783-67049-DETAIL-03_01_2023-GO95MLD-1^07216001.0291804 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
628960783-67049-DETAIL-03_01_2023-SVCWIND-1^07216001.0291804 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
591445659-90759-DETAIL-03_02_2023-GO95MLD-1^07216001.0291902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
829746499-13059-DETAIL-03_02_2023-SVCENTCO-1^07216001.0291941 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
284713175-19020-DETAIL-04_20_2022-ABNDEQPM-1^07216001.0159805 | OTHER | CA-NON-TIER | Distribution | 2022-04-20 | 2027-04-20 | 3
623094398-34749-DETAIL-07_14_2022-GO95MLD-1^07216001.0162605 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
585995913-14391-ADMIN-06_27_2023-DISTHDWR-1^07216001.0165000 | CONNECTION DEVICE | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
19004572-31083-ADMIN-11_06_2023-POLEDERP-1^07216001.0176010 | POLE | CA-NON-TIER | Distribution | 2023-11-06 | 2026-11-06 | 2
668819542-69520-DTLSB-07_14_2022-GO95MLD-1^07216001.0210400 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
74377139-73138-DTLSB-07_14_2022-GO95HV-1^07216001.0210402 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2027-07-14 | 3
266788574-36600-DTLSB-07_14_2022-SVCENTCO-1^07216001.0210501 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
225614884-2860-DTLSB-07_14_2022-GO95MLD-1^07216001.0210503 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
398567274-18050-DTLSB-07_13_2022-GO95MLD-1^07216001.0210706 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
92455624-2330-DTLSB-07_13_2022-SVCROAD-1^07216001.0210709 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
367670523-18110-DTLSB-07_14_2022-GO95MLD-1^07216001.0210800 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
708051924-74241-DTLSB-07_14_2022-CLRTOUCH-1^07216001.0211502 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
949177193-26123-DTLSB-07_13_2022-ABNDEQPM-1^07216001.0211600 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
122175154-660-DTLSB-07_13_2022-ABNDEQPM-1^07216001.0211602 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
799431344-18982-DTLSB-07_13_2022-GO95HV-1^07216001.0211603 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
733998634-3049-DTLSB-07_13_2022-GO95HV-1^07216001.0211605 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
599107797-30639-DETAIL-03_02_2023-GO95MLD-1^07216001.0292401 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
662284669-27349-DETAIL-03_01_2023-GO95MLD-1^07216001.0292500 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
284597003-44049-DETAIL-03_02_2023-GUYHINS-1^07216001.0292506 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
800860489-2049-DETAIL-03_01_2023-SVCROAD-1^07216001.0292540 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
51453459-50559-DETAIL-03_01_2023-GO95MLD-1^07216001.0292541 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
51453459-50559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292541 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
139682759-21859-DETAIL-03_13_2023-SVCENTCO-1^07216001.0292544 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
226594413-6649-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0292600 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
351381593-14239-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0292602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
351381593-14239-DETAIL-03_01_2023-GO95MLD-1^07216001.0292602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
505764733-29649-DETAIL-03_01_2023-GO95MLD-1^07216001.0292603 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
505764733-29649-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292603 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
510778048-46359-DETAIL-03_01_2023-GO95MLD-1^07216001.0292604 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
200002559-90559-DETAIL-03_01_2023-SVCWIND-2^07216001.0292640 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
801273259-11559-DETAIL-03_01_2023-GO95MLD-1^07216001.0292641 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
801273259-11559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292641 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
585716356-42392-DTLSB-07_13_2022-ABNDEQPM-1^07216001.0211700 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
149502364-92290-DTLSB-07_13_2022-GO95MLD-1^07216001.0212603 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
217781921-31998-DTLSB-07_13_2022-GO95HV-1^07216001.0212604 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
967309538-56758-DTLSB-07_13_2022-GO95MLD-1^07216001.0213603 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
289949921-93428-DTLSB-07_13_2022-GO95HV-1^07216001.0213604 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
289949921-93428-DTLSB-07_13_2022-GO95MLD-1^07216001.0213604 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
289949921-93428-DTLSB-07_13_2022-GO95TCH-1^07216001.0213604 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
979035221-92103-DTLSB-07_13_2022-GUYNOINS-1^07216001.0213700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
137297781-99690-DTLTRT-07_13_2022-GO95HV-1^07216001.0213702 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
137297781-99690-DTLTRT-07_13_2022-GO95MLD-1^07216001.0213702 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
884399066-25272-DTLSB-07_13_2022-GO95MLD-1^07216001.0214502 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
270142973-68010-ADMIN-10_13_2023-POLEDERP-1^07216001.0214802 | POLE | CA-NON-TIER | Distribution | 2023-10-13 | 2026-10-13 | 2
10847101-80869-DTLSB-07_13_2022-GO95MLD-1^07216001.0214803 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
10847101-80869-DTLSB-07_13_2022-GO95TCH-1^07216001.0214803 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
719223463-58771-DTLSB-07_13_2022-GO95MLD-1^07216001.0214902 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
719223463-58771-DTLSB-07_13_2022-SVCNEUT-1^07216001.0214902 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
895155936-29549-DETAIL-03_01_2023-GO95TCH-1^07216001.0292701 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
502410062-52149-DETAIL-03_02_2023-GO95MLD-1^07216001.0292900 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
312578277-69349-DETAIL-03_13_2023-SVCDEFLC-1^07216001.0293300 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
810475677-1849-DETAIL-03_09_2023-GO95MLD-1^07216001.0293302 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
874203348-49886-DETAIL-03_09_2023-SVCDEFLC-1^07216001.0293340 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
874203348-49886-DETAIL-03_09_2023-SVCENTBK-1^07216001.0293340 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
706506007-70839-DETAIL-03_13_2023-GO95CL10-1^07216001.0293402 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
567925032-30720-DTLSB-07_13_2022-GO95MLD-1^07216001.0214903 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
567925032-30720-DTLSB-07_13_2022-GO95TCH-1^07216001.0214903 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
980232592-72620-DTLSB-07_13_2022-GO95HV-1^07216001.0215300 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
801211090-17722-DTLSB-07_13_2022-GO95HV-1^07216001.0215900 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
761157332-21720-DTLSB-07_13_2022-SVCENTCO-1^07216001.0215901 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
702412783-9321-DTLSB-07_13_2022-GO95HV-1^07216001.0215903 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2027-07-13 | 3
215622025-65365-DTLSB-07_13_2022-GO95MLD-1^07216001.0215920 | OTHER | CA-NON-TIER | Distribution | 2022-07-13 | 2025-07-13 | 2
209529155-32859-DTLSB-02_21_2023-GUYHINS-1^07216001.0280502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
53694636-82859-DTLSB-02_21_2023-GO95MLD-1^07216001.0280503 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
300634255-16339-DTLSB-02_21_2023-GO95HV-1^07216001.0280601 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
246516346-85249-DTLSB-02_21_2023-GO95MLD-1^07216001.0280603 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
21280906-79249-DTLSB-02_21_2023-GO95HV-1^07216001.0280605 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
21280906-79249-DTLSB-02_21_2023-GO95MLD-1^07216001.0280605 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
481430235-65249-DTLSB-02_22_2023-GO95HV-1^07216001.0280701 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
883600687-86418-DTLSB-02_22_2023-RISEGRD-1^07216001.0280704 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
397733413-24413-DTLSB-02_21_2023-SVCROAD-1^07216001.0280730 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
706506007-70839-DETAIL-03_13_2023-SVCENTBK-1^07216001.0293402 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
706506007-70839-DETAIL-03_13_2023-SVCWIND-1^07216001.0293402 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
935872817-78349-DETAIL-03_13_2023-GO95MLD-1^07216001.0293403 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
433673003-67349-DETAIL-03_01_2023-GO95HV-1^07216001.0293501 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
678652613-97349-DETAIL-03_01_2023-GO95HV-1^07216001.0293503 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
678652613-97349-DETAIL-03_01_2023-GO95MLD-1^07216001.0293503 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
160332993-68739-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
160332993-68739-DETAIL-03_01_2023-GO95CL10-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
160332993-68739-DETAIL-03_01_2023-GO95MLD-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
914782523-90239-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0293602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
914782523-90239-DETAIL-03_01_2023-GO95MLD-1^07216001.0293602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
15531018-92189-DETAIL-03_09_2023-GO95MLD-1^07216001.0293603 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
75851489-57439-DETAIL-03_09_2023-GO95MLD-1^07216001.0293605 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
611018789-67249-DETAIL-03_09_2023-GO95MLD-1^07216001.0293606 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
807489399-96049-DETAIL-03_09_2023-GO95MLD-1^07216001.0293607 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
12462686-28649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293900 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
12462686-28649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293900 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
63546876-72349-DETAIL-03_02_2023-GO95MLD-1^07216001.0293901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
63546876-72349-DETAIL-03_02_2023-GO95MLD-2^07216001.0293901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
63546876-72349-DETAIL-03_02_2023-SVCWIND-1^07216001.0293901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
787058179-64279-DETAIL-03_02_2023-GO95MLD-1^07216001.0293902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
541867836-72649-DETAIL-03_02_2023-SVCENTBK-1^07216001.0293903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
565660026-78649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293904 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
163746816-48459-DETAIL-03_02_2023-CLMBTRE-1^07216001.0293905 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
676429458-75461-DTLSB-02_21_2023-SVCENTBK-1^07216001.0281640 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
676429458-75461-DTLSB-02_21_2023-SVCWIND-1^07216001.0281640 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
219486106-88339-DTLSB-02_21_2023-GO95MLD-1^07216001.0281701 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
303930566-65749-DTLSB-02_21_2023-GO95MLD-1^07216001.0281800 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
521982786-52001-DTLSB-02_21_2023-GO95MLD-1^07216001.0281801 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
833034181-35149-DTLSB-02_21_2023-GO95CL10-1^07216001.0281900 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
420727196-17370-DTLSB-02_21_2023-GO95HV-1^07216001.0283500 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
420727196-17370-DTLSB-02_21_2023-GO95MLD-1^07216001.0283500 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
539283776-16531-DTLSB-02_21_2023-GO95MLD-1^07216001.0283504 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
236666070-60508-DTLSB-02_22_2023-GO95MLD-1^07216001.0285503 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
214220470-51470-DTLSB-02_22_2023-GO95MLD-1^07216001.0285507 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
35873208-71308-DTLSB-02_22_2023-GO95MLD-1^07216001.0285602 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
91511155-81649-DTLSB-02_22_2023-ABNDEQPM-1^07216001.0287604 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
70516396-26539-DTLSB-02_21_2023-GO95TCH-1^07216001.0287704 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
417456025-34539-DTLSB-02_21_2023-SVCENTCO-1^07216001.0287707 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
999654415-52833-DTLSB-02_21_2023-GO95TCH-1^07216001.0287708 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
250005856-71749-DETAIL-03_02_2023-GO95MLD-1^07216001.0293907 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
480153809-88849-DETAIL-03_02_2023-GO95MLD-1^07216001.0293909 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
701244619-20649-DETAIL-03_02_2023-GO95HV-1^07216001.0293911 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
701244619-20649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293911 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
716208487-75249-DETAIL-03_08_2023-GO95MLD-1^07216001.0294200 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
662315177-26811-DETAIL-03_08_2023-GO95MLD-1^07216001.0294303 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
202077547-749-DETAIL-03_09_2023-GO95HV-1^07216001.0294306 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
372732887-58339-DETAIL-03_13_2023-GUYHINS-1^07216001.0294400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
999654415-52833-DTLSB-02_21_2023-SVCROAD-1^07216001.0287708 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
964498435-54933-DTLSB-02_22_2023-GO95MLD-1^07216001.0287804 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
964498435-54933-DTLSB-02_22_2023-GO95TCH-1^07216001.0287804 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
365479595-81439-DTLSB-02_22_2023-GO95MLD-1^07216001.0287805 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
3262142-92142-DETAIL-02_22_2023-GO95TCH-1^07216001.0287806 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
788226370-97370-DTLSB-02_22_2023-SVCENTCO-1^07216001.0288601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
743978495-77849-DETAIL-03_15_2023-SVCENTBK-1^07216001.0290501 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
296338233-84339-DETAIL-03_15_2023-GO95MLD-1^07216001.0290600 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
324207217-97559-DETAIL-03_09_2023-CLRTOPOL-1^07216001.0294401 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
324207217-97559-DETAIL-03_09_2023-SVCWIND-1^07216001.0294401 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
637905216-47139-DETAIL-03_13_2023-SVCENTBK-1^07216001.0294407 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
789028878-42559-DETAIL-03_09_2023-CLMBTRE-1^07216001.0294408 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
476678336-72559-DETAIL-03_07_2023-GO95MLD-1^07216001.0294410 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
118322428-36495-DETAIL-03_09_2023-SVCENTCO-1^07216001.0294441 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
925451495-31839-DETAIL-03_09_2023-CLRTOPOL-1^07216001.0294501 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
747810789-35451-DETAIL-03_09_2023-GUYHINS-1^07216001.0294502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
296338233-84339-DETAIL-03_15_2023-SVCENTCO-1^07216001.0290600 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
285815705-6049-DETAIL-03_15_2023-GO95MLD-1^07216001.0290602 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
285815705-6049-DETAIL-03_15_2023-SVCENTBK-1^07216001.0290602 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
622696893-67939-DETAIL-03_13_2023-GO95BLTC-1^07216001.0290605 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
23949206-87158-DETAIL-03_13_2023-SVCWIND-1^07216001.0290606 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
106236199-99759-DETAIL-03_13_2023-SVCENTCO-1^07216001.0290640 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
535308475-2139-DETAIL-03_13_2023-GO95MLD-1^07216001.0290700 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
535308475-2139-DETAIL-03_13_2023-GUYHINS-1^07216001.0290700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
535308475-2139-DETAIL-03_13_2023-SVCWIND-1^07216001.0290700 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
682272074-28849-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0290701 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
682272074-28849-DETAIL-03_13_2023-SVCNEUT-1^07216001.0290701 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
900298124-72049-DETAIL-03_13_2023-SVCWIND-1^07216001.0290702 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
842699644-53639-DETAIL-03_01_2023-GO95MLD-1^07216001.0290704 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
27951343-55639-DETAIL-03_01_2023-GO95CL10-1^07216001.0290705 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
306982009-50859-DETAIL-03_13_2023-SVCENTBK-1^07216001.0290740 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
265340104-22849-DETAIL-03_13_2023-SVCWIND-1^07216001.0290800 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
747810789-35451-DETAIL-03_09_2023-SVCENTBK-1^07216001.0294502 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
775564069-98622-DETAIL-03_09_2023-GO95MLD-1^07216001.0294503 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
647889535-88971-DETAIL-03_09_2023-GO95MLD-1^07216001.0294504 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
647889535-88971-DETAIL-03_09_2023-GUYHINS-1^07216001.0294504 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
630204439-98249-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0294506 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
111515229-96839-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0294508 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
111515229-96839-DETAIL-03_07_2023-GO95CL10-1^07216001.0294508 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
111515229-96839-DETAIL-03_07_2023-GO95MLD-1^07216001.0294508 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
461995235-51939-DETAIL-03_07_2023-GUYHINS-1^07216001.0294509 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
813959629-84249-DETAIL-03_09_2023-GO95MLD-1^07216001.0294601 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
131361125-39249-DETAIL-03_09_2023-SVCNEUT-1^07216001.0294602 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
634524499-85349-DETAIL-02_27_2023-SVCENTCO-1^07216001.0294603 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
426980219-40580-DETAIL-02_27_2023-GO95MLD-1^07216001.0294605 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
426980219-40580-DETAIL-02_27_2023-GO95TCH-1^07216001.0294605 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
608502393-26349-DETAIL-02_23_2023-GO95MLD-1^07216001.0294607 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
879364178-77093-DETAIL-02_23_2023-SVCENTCO-1^07216001.0294643 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
487839993-8049-DETAIL-03_13_2023-GO95MLD-1^07216001.0290801 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
192489763-49139-DETAIL-03_15_2023-GO95MLD-1^07216001.0290804 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
150328463-3049-DETAIL-03_15_2023-GUYHINS-1^07216001.0291501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
962610363-23049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291502 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
188472925-2939-DETAIL-03_15_2023-GO95MLD-1^07216001.0291504 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
575644525-83549-DETAIL-03_15_2023-GO95MLD-1^07216001.0291505 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
623081405-3939-DETAIL-03_15_2023-GO95MLD-1^07216001.0291506 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
253350183-59649-DETAIL-03_02_2023-GO95MLD-1^07216001.0291601 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
104630956-86649-DETAIL-02_23_2023-GO95MLD-1^07216001.0294704 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
104630956-86649-DETAIL-02_23_2023-GO95TCH-1^07216001.0294704 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
552467374-53349-DETAIL-02_27_2023-GO95MLD-1^07216001.0294709 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
826047485-15349-DETAIL-02_27_2023-ABNDEQPM-1^07216001.0294740 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
826047485-15349-DETAIL-02_27_2023-GO95TCH-1^07216001.0294740 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
826047485-15349-DETAIL-02_27_2023-RISEGRD-1^07216001.0294740 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
965243889-52349-DETAIL-03_02_2023-GO95MLD-1^07216001.0294901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
398176809-5139-DETAIL-03_02_2023-CLRTOPOL-1^07216001.0294902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
398176809-5139-DETAIL-03_02_2023-GO95MLD-1^07216001.0294902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
826802979-24359-DETAIL-03_02_2023-GO95HV-1^07216001.0294903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
826802979-24359-DETAIL-03_02_2023-GO95MLD-1^07216001.0294903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
592368258-89258-DETAIL-03_08_2023-GO95MLD-1^07216001.0295302 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
994355854-4258-DETAIL-03_08_2023-GO95MLD-1^07216001.0295304 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
994355854-4258-DETAIL-03_08_2023-SVCNEUT-1^07216001.0295304 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
454627277-78277-DETAIL-03_08_2023-GO95MLD-1^07216001.0295305 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
454627277-78277-DETAIL-03_08_2023-GUYSLACK-1^07216001.0295305 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
664123753-3859-DETAIL-03_15_2023-CLRTOPOL-2^07216001.0291606 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
664123753-3859-DETAIL-03_15_2023-GO95MLD-1^07216001.0291606 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
593149569-2859-DETAIL-03_13_2023-SVCENTBK-1^07216001.0291642 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
472634083-17049-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
472634083-17049-DETAIL-03_01_2023-GO95CL10-1^07216001.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
472634083-17049-DETAIL-03_01_2023-GO95HV-1^07216001.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
472634083-17049-DETAIL-03_01_2023-SVCENTCO-1^07216001.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
575519823-45139-DETAIL-03_01_2023-GUYHINS-1^07216001.0291704 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
32509753-15049-DETAIL-03_01_2023-GO95MLD-1^07216001.0291706 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
32509753-15049-DETAIL-03_01_2023-SVCENTCO-1^07216001.0291706 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
321491353-77759-DETAIL-03_02_2023-GO95HV-1^07216001.0291708 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
239740469-37459-DETAIL-03_01_2023-SVCWIND-1^07216001.0291740 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
907066233-56649-DETAIL-03_13_2023-GO95MLD-1^07216001.0291800 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
885032364-55839-DETAIL-03_01_2023-GO95TCH-1^07216001.0291802 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
252371009-86009-DETAIL-03_01_2023-SVCWIND-1^07216001.0291820 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
484229379-87459-DETAIL-03_01_2023-GO95MLD-1^07216001.0291840 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
352793095-70559-DETAIL-03_09_2023-GO95MLD-1^07216001.0295306 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
69561148-94110-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295343 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
920719815-60939-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0295402 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
146744478-94478-DETAIL-03_07_2023-SVCWIND-1^07216001.0295403 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
504479365-22449-DETAIL-03_09_2023-SVCWIND-1^07216001.0295404 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
205818365-72749-DETAIL-03_09_2023-GO95HV-1^07216001.0295406 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
205818365-72749-DETAIL-03_09_2023-SVCENTBK-1^07216001.0295406 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
939948028-74731-DETAIL-03_09_2023-SVCENTBK-1^07216001.0295440 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
638530575-7039-DETAIL-03_09_2023-GO95HV-1^07216001.0295500 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
703546070-9249-DETAIL-03_09_2023-SVCWIND-1^07216001.0295501 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
440289785-90139-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295502 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
207141163-24958-DETAIL-03_08_2023-GO95CLSV-1^07216001.0295504 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
497402440-5559-DETAIL-03_08_2023-GUYHINS-1^07216001.0295506 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
12192063-84578-DETAIL-03_08_2023-SVCRUBLG-1^07216001.0295507 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
713016385-46761-DETAIL-03_09_2023-GUYHINS-1^07216001.0295508 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
713016385-46761-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295508 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
484229379-87459-DETAIL-03_01_2023-SVCWIND-1^07216001.0291840 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
484229379-87459-DETAIL-03_01_2023-SVCWIND-2^07216001.0291840 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
591445659-90759-DETAIL-03_02_2023-CLRTOPOL-1^07216001.0291902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
555749845-99459-DETAIL-03_02_2023-GO95HV-1^07216001.0291903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
342290269-99659-DETAIL-03_02_2023-ABNDEQPM-1^07216001.0291940 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
829746499-13059-DETAIL-03_02_2023-SVCDEFLC-1^07216001.0291941 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
715582969-18459-DETAIL-03_02_2023-SVCENTCO-1^07216001.0291943 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
599107797-30639-DETAIL-03_02_2023-SVCROAD-1^07216001.0292401 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
599107797-30639-AUDIT-03_06_2023-SVCENTBK-1^07216001.0292401 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
270609723-11939-DETAIL-03_13_2023-GO95MLD-1^07216001.0292502 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
699465723-24839-DETAIL-03_02_2023-GO95MLD-1^07216001.0292503 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
699465723-24839-DETAIL-03_02_2023-SVCROAD-1^07216001.0292503 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
357169143-65049-DETAIL-03_01_2023-GO95MLD-1^07216001.0292505 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
284597003-44049-DETAIL-03_02_2023-GO95MLD-1^07216001.0292506 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
816900893-41649-DETAIL-03_02_2023-GO95HV-1^07216001.0292507 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
548484453-76939-DETAIL-03_08_2023-GO95MLD-1^07216001.0295600 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
411432436-89739-DETAIL-03_08_2023-GO95TCH-1^07216001.0295601 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
519939641-58039-DETAIL-03_08_2023-CLMBHAZ-1^07216001.0295603 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
519939641-58039-DETAIL-03_08_2023-CLRTOPOL-1^07216001.0295603 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
2155446-37249-DETAIL-03_08_2023-GO95TCH-1^07216001.0295605 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
268186317-29317-DETAIL-02_27_2023-GO95MLD-1^07216001.0295701 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
268186317-29317-DETAIL-02_27_2023-SVCWIND-1^07216001.0295701 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
175245981-53749-DETAIL-02_27_2023-GO95MLD-1^07216001.0295702 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
649282233-14639-DETAIL-02_27_2023-GO95MLD-1^07216001.0295703 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
732125390-30311-DETAIL-02_23_2023-GO95HV-1^07216001.0295706 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
732125390-30311-DETAIL-02_23_2023-GO95MLD-1^07216001.0295706 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
732125390-30311-DETAIL-02_23_2023-GRDRODHI-1^07216001.0295706 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
406879366-60449-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0295708 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
406879366-60449-DETAIL-02_23_2023-GO95MLD-1^07216001.0295708 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
158772585-84139-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0295901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
158772585-84139-DETAIL-03_06_2023-GO95MLD-1^07216001.0295901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
816900893-41649-DETAIL-03_02_2023-GO95MLD-1^07216001.0292507 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
51453459-50559-DETAIL-03_01_2023-SVCWIND-1^07216001.0292541 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
51453459-50559-DETAIL-03_01_2023-SVCWIND-2^07216001.0292541 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
226594413-6649-DETAIL-03_01_2023-GO95MLD-1^07216001.0292600 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
865940103-93649-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0292601 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
351381593-14239-DETAIL-03_01_2023-GO95TCH-1^07216001.0292602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
200002559-90559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292640 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
200002559-90559-DETAIL-03_01_2023-SVCWIND-1^07216001.0292640 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
188936383-40749-DETAIL-03_01_2023-GO95MLD-1^07216001.0292700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
895155936-29549-DETAIL-03_01_2023-GO95MLD-1^07216001.0292701 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
975698599-76939-DETAIL-03_02_2023-GO95MLD-1^07216001.0292901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
678938429-82239-DETAIL-03_02_2023-GO95TCH-1^07216001.0292902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
810475677-1849-DETAIL-03_09_2023-GO95CL10-1^07216001.0293302 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
810475677-1849-DETAIL-03_09_2023-GO95TCH-1^07216001.0293302 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
395389808-69776-DETAIL-03_09_2023-GO95TCH-1^07216001.0293341 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
706506007-70839-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0293402 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
158772585-84139-DETAIL-03_06_2023-SVCWIND-1^07216001.0295901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
626915355-14249-DETAIL-03_02_2023-GO95MLD-1^07216001.0295902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
965349645-72359-DETAIL-03_02_2023-GO95MLD-1^07216001.0295906 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
292361035-13139-DETAIL-03_02_2023-GO95MLD-1^07216001.0295908 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
601422425-96011-DETAIL-03_07_2023-GO95MLD-1^07216001.0296100 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
246782895-50459-DETAIL-03_07_2023-GO95HV-1^07216001.0296300 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
388208695-90459-DETAIL-03_07_2023-GO95MLD-1^07216001.0296302 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
796460515-3639-DETAIL-03_07_2023-GO95MLD-1^07216001.0296303 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
830387435-5539-DETAIL-03_08_2023-GO95MLD-1^07216001.0296304 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
738938015-53449-DETAIL-03_08_2023-GO95MLD-1^07216001.0296305 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
438065885-82549-DETAIL-03_08_2023-SVCWIND-1^07216001.0296400 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
552412425-58839-DETAIL-03_08_2023-SVCNEUT-1^07216001.0296401 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
884619735-17939-DETAIL-03_08_2023-GO95MLD-1^07216001.0296402 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
698588078-14749-DETAIL-03_09_2023-GO95MLD-1^07216001.0296403 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
698588078-14749-DETAIL-03_09_2023-GO95TCH-1^07216001.0296403 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
465286455-15649-DETAIL-03_09_2023-SVCDEFLC-1^07216001.0296405 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
935872817-78349-DETAIL-03_13_2023-GUYHINS-1^07216001.0293403 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
93727479-94759-DETAIL-03_02_2023-GO95MLD-1^07216001.0293408 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
597473373-82839-DETAIL-03_13_2023-GO95TCH-1^07216001.0293410 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
707112858-45641-DETAIL-03_13_2023-GO95TCH-1^07216001.0293440 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
509750759-6149-DETAIL-03_01_2023-GO95MLD-1^07216001.0293502 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
509750759-6149-DETAIL-03_01_2023-GRDRODHI-1^07216001.0293502 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
509750759-6149-DETAIL-03_01_2023-SVCWIND-1^07216001.0293502 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
121384598-52160-DETAIL-03_09_2023-CLMBTRE-1^07216001.0293504 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
160332993-68739-DETAIL-03_01_2023-GO95HV-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
160332993-68739-DETAIL-03_01_2023-SVCNEUT-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
551244563-21639-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0293601 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
551244563-21639-DETAIL-03_01_2023-GO95HV-1^07216001.0293601 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
914782523-90239-DETAIL-03_01_2023-GO95TCH-1^07216001.0293602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
914782523-90239-DETAIL-03_01_2023-SVCNEUT-1^07216001.0293602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
75851489-57439-DETAIL-03_09_2023-GO95TCH-1^07216001.0293605 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
80758849-12610-DETAIL-03_09_2023-SVCWIND-1^07216001.0293608 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
875232135-13449-DETAIL-03_08_2023-GUYLOINS-1^07216001.0296408 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
675766486-16768-DETAIL-03_08_2023-GUYHINS-1^07216001.0296409 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
298312576-24649-DETAIL-03_08_2023-GO95HV-1^07216001.0296410 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
298312576-24649-DETAIL-03_08_2023-GO95MLD-1^07216001.0296410 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
766354296-18149-DETAIL-03_06_2023-RISEBKSP-1^07216001.0296603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
890910364-1349-DETAIL-03_08_2023-GO95MLD-1^07216001.0296605 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
632901770-5639-DETAIL-03_06_2023-GO95HV-1^07216001.0296606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
632901770-5639-DETAIL-03_06_2023-GO95TCH-1^07216001.0296606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
632901770-5639-DETAIL-03_06_2023-GUYHINS-1^07216001.0296606 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
632901770-5639-DETAIL-03_06_2023-SVCDEFLC-1^07216001.0296606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
124997486-42270-DETAIL-02_27_2023-GO95MLD-1^07216001.0296700 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
86462896-249-DETAIL-03_06_2023-GO95MLD-1^07216001.0296705 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
82750425-71239-DETAIL-03_06_2023-SVCENTCO-1^07216001.0296706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
423706611-55670-DETAIL-02_27_2023-GO95MLD-1^07216001.0296708 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
423706611-55670-DETAIL-02_27_2023-RISESTRP-1^07216001.0296708 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
423706611-55670-DETAIL-02_27_2023-RISESTRP-2^07216001.0296708 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
70023123-37390-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0293609 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
70023123-37390-DETAIL-03_07_2023-GO95MLD-1^07216001.0293609 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
541867836-72649-DETAIL-03_02_2023-GO95CL10-1^07216001.0293903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
541867836-72649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
541867836-72649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
565660026-78649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293904 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
750097866-71349-DETAIL-03_02_2023-CLMBHAZ-1^07216001.0293908 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
480153809-88849-DETAIL-03_02_2023-SVCWIND-1^07216001.0293909 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
237299559-12349-DETAIL-03_02_2023-CLMBHAZ-1^07216001.0293910 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
237299559-12349-DETAIL-03_02_2023-GO95MLD-1^07216001.0293910 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
716208487-75249-DETAIL-03_08_2023-SVCWIND-1^07216001.0294200 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
539831647-57249-DETAIL-03_08_2023-GO95MLD-1^07216001.0294201 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
662315177-26811-DETAIL-03_08_2023-SVCDEFLC-1^07216001.0294303 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
662315177-26811-DETAIL-03_08_2023-SVCENTBK-1^07216001.0294303 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
554669518-68666-DETAIL-03_08_2023-SVCWIND-1^07216001.0294340 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
372732887-58339-DETAIL-03_13_2023-GO95MLD-1^07216001.0294400 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
324207217-97559-DETAIL-03_09_2023-GO95MLD-1^07216001.0294401 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
308664377-77559-DETAIL-03_09_2023-SVCWIND-1^07216001.0294402 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
736959249-18349-DETAIL-03_13_2023-SVCDEFLC-1^07216001.0294403 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
939573607-98349-DETAIL-03_13_2023-GO95HV-1^07216001.0294405 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
637905216-47139-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0294407 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
637905216-47139-DETAIL-03_13_2023-GO95CL10-1^07216001.0294407 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
53271526-82249-DETAIL-02_27_2023-GO95HV-1^07216001.0296800 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
692201718-73718-DETAIL-03_06_2023-GO95CL10-1^07216001.0296803 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
692201718-73718-DETAIL-03_06_2023-SVCENTCO-1^07216001.0296803 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
334791616-52549-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0296804 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
334791616-52549-DETAIL-03_06_2023-GO95MLD-1^07216001.0296804 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
334791616-52549-DETAIL-03_06_2023-SVCENTCO-1^07216001.0296804 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
162767036-85100-DETAIL-02_23_2023-GO95MLD-1^07216001.0296805 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
406757318-95753-DETAIL-02_27_2023-GO95TCH-1^07216001.0296843 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
556113810-60651-DETAIL-02_23_2023-SVCDEFLC-1^07216001.0296902 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
761019800-84349-DETAIL-02_23_2023-SVCENTCO-1^07216001.0296904 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
761019800-84349-DETAIL-02_23_2023-SVCWIND-1^07216001.0296904 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
212848316-30350-DETAIL-02_23_2023-GO95TCH-1^07216001.0296906 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
354220187-459-DETAIL-03_07_2023-GO95MLD-1^07216001.0297300 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
772381685-19359-DETAIL-03_07_2023-GO95HV-1^07216001.0297301 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
591758745-36639-DETAIL-03_07_2023-GO95HV-1^07216001.0297302 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
925451495-31839-DETAIL-03_09_2023-GO95MLD-1^07216001.0294501 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
630204439-98249-DETAIL-03_07_2023-GO95CL10-1^07216001.0294506 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
890583928-68203-DETAIL-03_07_2023-GO95MLD-1^07216001.0294544 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
813959629-84249-DETAIL-03_09_2023-GO95HV-1^07216001.0294601 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
813959629-84249-DETAIL-03_09_2023-GUYHINS-1^07216001.0294601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
131361125-39249-DETAIL-03_09_2023-GO95MLD-1^07216001.0294602 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
131361125-39249-DETAIL-03_09_2023-GO95TCH-1^07216001.0294602 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
634524499-85349-DETAIL-02_27_2023-GO95HV-1^07216001.0294603 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
496787666-47371-DETAIL-03_09_2023-GO95MLD-1^07216001.0294606 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
571537865-79271-DETAIL-02_23_2023-GO95MLD-1^07216001.0294608 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
827185679-83559-DETAIL-02_27_2023-GO95MLD-1^07216001.0294609 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
879364178-77093-DETAIL-02_23_2023-GO95TCH-1^07216001.0294643 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
3224355-71839-DETAIL-02_23_2023-GO95MLD-1^07216001.0294705 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
3224355-71839-DETAIL-02_23_2023-SVCENTCO-1^07216001.0294705 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
428785395-1449-DETAIL-02_23_2023-GO95MLD-1^07216001.0294706 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
9356745-43349-DETAIL-02_27_2023-GO95HV-1^07216001.0294707 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
991914475-18359-DETAIL-03_07_2023-GO95HV-1^07216001.0297401 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
872726375-56149-DETAIL-03_07_2023-GO95MLD-1^07216001.0297403 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
138474528-24139-DETAIL-03_06_2023-GO95MLD-1^07216001.0297500 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
138474528-24139-DETAIL-03_06_2023-GUYHINS-1^07216001.0297500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
138474528-24139-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297500 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
675507665-40139-DETAIL-03_07_2023-GO95MLD-1^07216001.0297505 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
794452101-63101-DETAIL-03_08_2023-GUYHINS-1^07216001.0297506 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
883317001-48001-DETAIL-03_08_2023-GO95HV-1^07216001.0297509 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
883317001-48001-DETAIL-03_08_2023-GO95MLD-1^07216001.0297509 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
63949358-96849-DETAIL-03_08_2023-GO95MLD-1^07216001.0297600 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
356074455-97149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297601 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
698164489-68249-DETAIL-03_06_2023-GO95MLD-1^07216001.0297603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
698164489-68249-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
597879960-31939-DETAIL-03_06_2023-GO95MLD-1^07216001.0297605 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
764841216-77139-DETAIL-02_28_2023-GO95MLD-1^07216001.0297700 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
57694116-91249-DETAIL-02_28_2023-GO95MLD-1^07216001.0297701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
57694116-91249-DETAIL-02_28_2023-SVCWIND-1^07216001.0297701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
136125046-65149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
136125046-65149-DETAIL-03_06_2023-GRDRODHI-1^07216001.0297706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
885449980-40849-DETAIL-03_06_2023-GO95MLD-1^07216001.0297708 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
924391436-16939-DETAIL-02_27_2023-GO95MLD-1^07216001.0297800 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
635304390-62249-DETAIL-02_27_2023-GO95MLD-1^07216001.0297807 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
164164217-56217-DETAIL-02_27_2023-GO95MLD-1^07216001.0297810 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
563998896-22839-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0297901 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
9356745-43349-DETAIL-02_27_2023-GO95MLD-1^07216001.0294707 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
558855475-83349-DETAIL-02_27_2023-GO95MLD-1^07216001.0294708 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
371302479-17859-DETAIL-03_02_2023-GO95MLD-1^07216001.0294900 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
544063754-83028-DETAIL-03_08_2023-GO95MLD-1^07216001.0295300 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
544063754-83028-DETAIL-03_08_2023-GO95TCH-1^07216001.0295300 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
743413358-97088-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0295301 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
592368258-89258-DETAIL-03_08_2023-GO95HV-1^07216001.0295302 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
592368258-89258-DETAIL-03_08_2023-SVCNEUT-1^07216001.0295302 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
578096337-46559-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295307 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
668605455-82449-DETAIL-03_13_2023-GO95MLD-1^07216001.0295400 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
144614035-52239-DETAIL-03_13_2023-SVCENTCO-1^07216001.0295401 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
144614035-52239-DETAIL-03_13_2023-SVCWIND-1^07216001.0295401 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
146744478-94478-DETAIL-03_07_2023-GO95CL10-1^07216001.0295403 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
504479365-22449-DETAIL-03_09_2023-GO95MLD-1^07216001.0295404 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
611751080-21559-DETAIL-03_09_2023-GO95MLD-1^07216001.0295405 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
205818365-72749-DETAIL-03_09_2023-GO95MLD-1^07216001.0295406 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
291484906-4849-DETAIL-02_23_2023-GO95CL10-1^07216001.0297903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
654495276-86891-DETAIL-02_27_2023-GO95MLD-1^07216001.0297906 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
761047358-48358-DETAIL-03_07_2023-GO95MLD-1^07216001.0298405 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
63419495-48359-DETAIL-03_07_2023-GO95HV-1^07216001.0298406 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
833539094-21194-DETAIL-02_28_2023-GO95HV-1^07216001.0298504 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
858379979-34349-DETAIL-02_28_2023-GO95HV-1^07216001.0298505 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
188605489-96239-DETAIL-02_28_2023-SVCENTCO-1^07216001.0298506 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
390942439-73349-DETAIL-03_06_2023-GO95MLD-1^07216001.0298509 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
638530575-7039-DETAIL-03_09_2023-GO95MLD-1^07216001.0295500 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
638530575-7039-DETAIL-03_09_2023-GUYHINS-1^07216001.0295500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
703546070-9249-DETAIL-03_09_2023-GUYHINS-1^07216001.0295501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
440289785-90139-DETAIL-03_09_2023-GUYHINS-1^07216001.0295502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
207141163-24958-DETAIL-03_08_2023-GO95HV-1^07216001.0295504 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
207141163-24958-DETAIL-03_08_2023-GO95MLD-1^07216001.0295504 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
497402440-5559-DETAIL-03_08_2023-GO95CL10-1^07216001.0295506 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
497402440-5559-DETAIL-03_08_2023-GO95MLD-1^07216001.0295506 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
804627468-20168-DETAIL-02_28_2023-GO95MLD-1^07216001.0298601 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
812279609-89049-DETAIL-02_28_2023-CLRTOUCH-1^07216001.0298605 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
785350468-22468-DETAIL-02_28_2023-GO95MLD-1^07216001.0298606 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
785350468-22468-DETAIL-02_28_2023-GUYHINS-1^07216001.0298606 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
569075719-38249-DETAIL-02_28_2023-GO95MLD-1^07216001.0298607 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
455553348-76238-DETAIL-03_02_2023-SVCENTCO-1^07216001.0298640 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
455553348-76238-DETAIL-03_02_2023-SVCRUBLG-1^07216001.0298640 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
455553348-76238-DETAIL-03_02_2023-SVCWIND-1^07216001.0298640 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
834743018-96612-DETAIL-03_02_2023-GO95MLD-1^07216001.0298643 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
774843918-33039-DETAIL-02_28_2023-GO95TCH-1^07216001.0298701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
510533138-74138-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0298707 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
510533138-74138-DETAIL-02_28_2023-SVCWIND-1^07216001.0298707 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
222615328-65558-DETAIL-02_28_2023-SVCWIND-1^07216001.0298740 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
242070466-78049-DETAIL-02_28_2023-GO95MLD-1^07216001.0298800 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
242070466-78049-DETAIL-02_28_2023-GO95TCH-1^07216001.0298800 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
452971556-32459-DETAIL-02_27_2023-GO95MLD-1^07216001.0298802 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
226046686-49639-DETAIL-02_27_2023-GO95MLD-1^07216001.0298805 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
226046686-49639-DETAIL-02_27_2023-GUYHINS-1^07216001.0298805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
226046686-49639-DETAIL-02_27_2023-GUYHINS-2^07216001.0298805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
809597945-18039-DETAIL-02_27_2023-GO95MLD-1^07216001.0298806 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
809597945-18039-DETAIL-02_27_2023-SVCWIND-1^07216001.0298806 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
471183193-55193-DETAIL-02_23_2023-GO95MLD-1^07216001.0298809 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
131514982-15982-DETAIL-02_27_2023-GO95TCH-1^07216001.0298811 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
688965238-80399-DETAIL-02_27_2023-GO95TCH-1^07216001.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
713016385-46761-DETAIL-03_09_2023-GO95TCH-1^07216001.0295508 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
638399404-41551-DETAIL-03_09_2023-SVCENTBK-1^07216001.0295540 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
411432436-89739-AUDIT-03_06_2023-GUYHINS-1^07216001.0295601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
519939641-58039-DETAIL-03_08_2023-GO95MLD-1^07216001.0295603 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
720372751-65559-DETAIL-02_27_2023-GO95MLD-1^07216001.0295606 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
562419431-34531-DETAIL-02_27_2023-SVCROAD-1^07216001.0295640 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
268186317-29317-DETAIL-02_27_2023-GO95TCH-1^07216001.0295701 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
649282233-14639-DETAIL-02_27_2023-GO95MLD-2^07216001.0295703 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
688965238-80399-DETAIL-02_27_2023-SVCDEFLC-1^07216001.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
688965238-80399-DETAIL-02_27_2023-SVCDEFLC-2^07216001.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
688965238-80399-DETAIL-02_27_2023-SVCENTCO-2^07216001.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
867402406-34406-DETAIL-02_23_2023-GO95HV-1^07216001.0298901 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
887194521-83282-DETAIL-02_23_2023-GO95TCH-1^07216001.0298903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
887194521-83282-DETAIL-02_23_2023-SVCENTCO-1^07216001.0298903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
512653095-84691-DETAIL-02_23_2023-GO95MLD-1^07216001.0298904 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
165602176-89610-DETAIL-02_23_2023-GO95MLD-1^07216001.0298905 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
252445866-98649-DETAIL-02_23_2023-GO95MLD-1^07216001.0298907 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
252445866-98649-DETAIL-02_23_2023-SVCDEFLC-1^07216001.0298907 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
252445866-98649-DETAIL-02_23_2023-SVCROAD-1^07216001.0298907 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
349608800-24690-DETAIL-02_23_2023-SVCNEUT-1^07216001.0298909 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
349608800-24690-AUDIT-03_06_2023-SVCRUBLG-1^07216001.0298909 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
303650029-10449-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299400 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
303650029-10449-DETAIL-02_28_2023-GO95MLD-1^07216001.0299400 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
396489119-56849-DETAIL-02_28_2023-GO95MLD-1^07216001.0299500 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
553652259-31239-DETAIL-02_28_2023-GO95HV-1^07216001.0299600 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
822334889-90639-DETAIL-02_28_2023-GO95MLD-1^07216001.0299601 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
751216829-25039-DETAIL-02_28_2023-GO95MLD-1^07216001.0299602 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
439709434-40534-DETAIL-02_23_2023-GO95MLD-1^07216001.0299604 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
660057518-37049-DETAIL-02_28_2023-SVCNEUT-1^07216001.0299605 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
464391899-87649-DETAIL-02_28_2023-GO95MLD-1^07216001.0299607 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
656174001-53301-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299700 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
928729426-60849-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
928729426-60849-DETAIL-02_28_2023-GO95MLD-1^07216001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
559582561-85139-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299702 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
559582561-85139-DETAIL-02_28_2023-GO95MLD-1^07216001.0299702 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
559582561-85139-DETAIL-02_28_2023-SVCDEFLC-1^07216001.0299702 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
87526959-14949-DETAIL-02_28_2023-GO95TCH-1^07216001.0299703 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
450303289-64289-DETAIL-02_23_2023-GO95MLD-1^07216001.0295705 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
56634246-11760-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0295707 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
56634246-11760-DETAIL-02_23_2023-GO95MLD-1^07216001.0295707 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
282785936-44359-DETAIL-02_23_2023-GO95MLD-1^07216001.0295801 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
333923871-96249-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0295802 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
333923871-96249-DETAIL-03_06_2023-GO95MLD-1^07216001.0295802 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
468220828-79943-DETAIL-03_06_2023-SVCENTBK-1^07216001.0295840 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
158772585-84139-DETAIL-03_06_2023-SVCNEUT-1^07216001.0295901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
626915355-14249-DETAIL-03_02_2023-CLRTOPOL-1^07216001.0295902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
626915355-14249-DETAIL-03_02_2023-SVCWIND-1^07216001.0295902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
653558906-14939-DETAIL-03_06_2023-GO95CL10-1^07216001.0295904 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
393084837-65948-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0295905 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
965349645-72359-DETAIL-03_02_2023-SVCNEUT-1^07216001.0295906 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
84607045-92359-DETAIL-03_02_2023-GO95MLD-1^07216001.0295907 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
292361035-13139-DETAIL-03_02_2023-GUYHINS-1^07216001.0295908 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
801933528-30124-DETAIL-03_06_2023-SVCENTBK-1^07216001.0295941 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
364320095-5239-DETAIL-03_07_2023-GO95MLD-1^07216001.0296301 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
830387435-5539-DETAIL-03_08_2023-GO95TCH-1^07216001.0296304 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
438065885-82549-DETAIL-03_08_2023-SVCDEFLC-1^07216001.0296400 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
438065885-82549-DETAIL-03_08_2023-SVCNEUT-1^07216001.0296400 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
552412425-58839-DETAIL-03_08_2023-GO95MLD-1^07216001.0296401 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
103334665-63139-DETAIL-03_09_2023-GO95MLD-1^07216001.0296404 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
465286455-15649-DETAIL-03_09_2023-GO95MLD-1^07216001.0296405 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
31224770-85649-DETAIL-03_08_2023-GO95MLD-1^07216001.0296407 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
875232135-13449-DETAIL-03_08_2023-GO95MLD-1^07216001.0296408 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
675766486-16768-DETAIL-03_08_2023-GO95MLD-1^07216001.0296409 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
280021388-33159-DETAIL-03_08_2023-SVCDEFLC-1^07216001.0296501 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
194224238-78316-DETAIL-03_08_2023-SVCDEFLC-1^07216001.0296541 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
609887708-90466-DETAIL-03_08_2023-SVCROAD-1^07216001.0296542 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
910483224-57472-DETAIL-03_08_2023-GO95TCH-1^07216001.0296543 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
790641349-32139-DETAIL-02_28_2023-GO95MLD-1^07216001.0299704 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
851544651-40349-DETAIL-02_23_2023-GO95MLD-1^07216001.0299708 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
649476326-25349-DETAIL-02_28_2023-GO95TCH-1^07216001.0299711 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
406523055-91549-DETAIL-02_28_2023-GO95MLD-1^07216001.0299801 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
991808058-6668-DETAIL-02_28_2023-GRDRODHI-1^07216001.0299802 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
641272135-90349-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299803 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
641272135-90349-DETAIL-02_28_2023-GO95MLD-1^07216001.0299803 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
641272135-90349-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299803 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
766354296-18149-DETAIL-03_06_2023-GO95MLD-1^07216001.0296603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
953287325-33933-DETAIL-03_06_2023-SVCDEFLC-1^07216001.0296604 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
632901770-5639-DETAIL-03_06_2023-SVCWIND-1^07216001.0296606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
782596386-5359-DETAIL-02_27_2023-GO95HV-1^07216001.0296702 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
782596386-5359-DETAIL-02_27_2023-SVCWIND-1^07216001.0296702 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
82750425-71239-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0296706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
53271526-82249-DETAIL-02_27_2023-GO95MLD-1^07216001.0296800 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
481620293-51293-DETAIL-02_23_2023-GO95MLD-1^07216001.0299807 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
732782415-74415-DETAIL-02_28_2023-GO95MLD-1^07216001.0299808 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
37371054-18139-ADMIN-05_20_2022-GO95HV-1^07216001.0309901 | OTHER | CA-NON-TIER | Distribution | 2022-05-20 | 2027-05-20 | 3
292429438-59559-ADMIN-10_25_2023-EARMSPCR-1^07217001.0024401 | OTHER | CA-NON-TIER | Distribution | 2023-10-25 | 2026-10-25 | 2
507779012-45843-DETAIL-05_09_2022-GUYHINS-1^07217001.0120300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-09 | 2025-05-09 | 2
674791612-35843-DETAIL-05_09_2022-GUYHINS-1^07217001.0120301 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-09 | 2025-05-09 | 2
832643411-93959-ADMIN-11_21_2023-POLEREPL-1^07217001.0120501 | POLE | CA-NON-TIER | Distribution | 2023-11-21 | 2026-11-21 | 2
582559031-81549-DETAIL-05_04_2022-GUYLOINS-1^07217001.0120502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
277274010-58349-DETAIL-05_04_2022-GO95MLD-1^07217001.0120504 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
64705427-25427-DETAIL-05_04_2022-GUYHINS-1^07217001.0120507 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
842245333-45439-DETAIL-05_12_2022-GO95HV-1^07217001.0120901 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
96367802-90159-DETAIL-05_03_2022-GUYHINS-1^07217001.0121001 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
904041032-69059-DETAIL-05_09_2022-GUYNOINS-1^07217001.0121203 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-09 | 2025-05-09 | 2
589634531-92649-DETAIL-05_05_2022-CLRTOUCH-1^07217001.0121500 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
161937162-59843-DETAIL-05_03_2022-GO95MLD-1^07217001.0122002 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
345881402-60159-DETAIL-05_05_2022-GO95HV-1^07217001.0122102 | OTHER | CA-NON-TIER | Distribution | 2022-05-05 | 2027-05-05 | 3
141355326-89239-DETAIL-03_06_2023-GO95HV-1^07216001.0296801 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
141355326-89239-DETAIL-03_06_2023-GO95MLD-1^07216001.0296801 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
692201718-73718-DETAIL-03_06_2023-GO95MLD-1^07216001.0296803 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
820043616-79662-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0296807 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
820043616-79662-DETAIL-03_06_2023-GO95MLD-1^07216001.0296807 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
406757318-95753-DETAIL-02_27_2023-SVCENTBK-1^07216001.0296843 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
273647412-89412-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0296901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
556113810-60651-DETAIL-02_23_2023-CLMBTRE-1^07216001.0296902 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
761019800-84349-DETAIL-02_23_2023-GO95MLD-1^07216001.0296904 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
224343440-41160-DETAIL-02_23_2023-SVCENTCO-1^07216001.0296905 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
212848316-30350-DETAIL-02_23_2023-SVCENTCO-1^07216001.0296906 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
212848316-30350-DETAIL-02_23_2023-SVCENTCO-2^07216001.0296906 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
664174124-22921-DETAIL-02_23_2023-SVCENTCO-1^07216001.0296941 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
772381685-19359-DETAIL-03_07_2023-GO95MLD-1^07216001.0297301 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
386205655-89649-DETAIL-03_07_2023-GO95BLTC-1^07216001.0297402 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
386205655-89649-DETAIL-03_07_2023-GO95MLD-1^07216001.0297402 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
814724120-8742-DETAIL-03_07_2023-GO95MLD-1^07216001.0297405 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
138474528-24139-DETAIL-03_06_2023-GO95HV-1^07216001.0297500 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
471971079-67539-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0297502 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
471971079-67539-DETAIL-03_06_2023-GO95MLD-1^07216001.0297502 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
537994925-36249-DETAIL-03_08_2023-GO95MLD-1^07216001.0297504 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
537994925-36249-DETAIL-03_08_2023-GUYHINS-1^07216001.0297504 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
886121016-48149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297510 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
63949358-96849-AUDIT-03_21_2023-GO95HV-1^07216001.0297600 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
187195641-79049-DETAIL-05_04_2022-GUYSLACK-1^07217001.0122400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
657713861-68639-DETAIL-05_04_2022-GO95MLD-1^07217001.0123400 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
661073993-59253-DETAIL-05_03_2022-DISTHDWR-1^07217001.0136600 | CONNECTION DEVICE | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
661073993-59253-DETAIL-05_03_2022-GO95MLD-1^07217001.0136600 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
75325082-86082-DETAIL-05_03_2022-GO95MLD-1^07217001.0136702 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
438166933-12059-DETAIL-05_04_2022-SVCENTCO-1^07217001.0137200 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
413309313-91460-DETAIL-05_12_2022-GO95HV-1^07217001.0137402 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
413309313-91460-DETAIL-05_12_2022-GO95MLD-1^07217001.0137402 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
698164489-68249-DETAIL-03_06_2023-GO95TCH-1^07216001.0297603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
980779261-68149-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297604 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
494037606-87149-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0297606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
494037606-87149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
494037606-87149-DETAIL-03_06_2023-GUYHINS-1^07216001.0297606 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
764841216-77139-DETAIL-02_28_2023-GUYHINS-1^07216001.0297700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
57694116-91249-DETAIL-02_28_2023-GUYHINS-1^07216001.0297701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
505584631-40849-DETAIL-03_06_2023-GO95MLD-1^07216001.0297702 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
920576670-19670-DETAIL-05_12_2022-GUYNOINS-1^07217001.0137404 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
566265603-91353-DETAIL-05_12_2022-GO95MLD-1^07217001.0137501 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
566265603-91353-DETAIL-05_12_2022-GUYHINS-1^07217001.0137501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
566265603-91353-DETAIL-05_12_2022-SVCNEUT-1^07217001.0137501 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
531824163-77953-DETAIL-05_12_2022-GO95MLD-1^07217001.0137600 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
624518253-96953-DETAIL-05_12_2022-ANCHIDLE-1^07217001.0137601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
624518253-96953-DETAIL-05_12_2022-GO95MLD-1^07217001.0137601 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
660882773-60053-DETAIL-05_12_2022-CLRTOUCH-1^07217001.0138401 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
678148400-30733-ADMIN-11_08_2023-POLETOP-1^07217001.0151500 | POLE | CA-NON-TIER | Distribution | 2023-11-08 | 2026-11-08 | 2
248016788-25123-DETAIL-04_26_2022-GO95MLD-1^07217001.0230001 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2025-04-26 | 2
474905038-35923-DETAIL-05_02_2022-GO95MLD-1^07217001.0230002 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
738215148-54023-DETAIL-05_02_2022-GO95MLD-1^07217001.0230700 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
901427648-43059-DETAIL-05_02_2022-GRDRODHI-1^07217001.0230701 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
730298058-36023-DETAIL-05_02_2022-GO95MLD-1^07217001.0230801 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2027-05-02 | 3
315900398-223-DETAIL-05_04_2022-GO95MLD-1^07217001.0237100 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
495753258-83423-DETAIL-05_11_2022-GO95MLD-1^07217001.0238440 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
495753258-83423-DETAIL-05_11_2022-SVCNEUT-1^07217001.0238440 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
819408778-99023-DETAIL-05_12_2022-GUYSLACK-1^07217001.0238500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
262564258-85423-DETAIL-05_12_2022-SVCROAD-1^07217001.0238640 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
385686068-88023-DETAIL-05_05_2022-CONDCOIL-1^07217001.0238701 | OTHER | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
385686068-88023-DETAIL-05_05_2022-GO95TCH-1^07217001.0238701 | OTHER | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
37204078-20123-DETAIL-05_12_2022-GO95MLD-1^07217001.0239500 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
543343143-97649-DETAIL-04_27_2022-GO95MLD-1^07217001.0240300 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
397565983-13159-DETAIL-05_03_2022-GO95MLD-1^07217001.0246600 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
505584631-40849-DETAIL-03_06_2023-SVCWIND-1^07216001.0297702 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
315541538-94839-DETAIL-03_06_2023-GO95MLD-1^07216001.0297704 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
315541538-94839-DETAIL-03_06_2023-GO95TCH-1^07216001.0297704 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
811680946-59149-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0297705 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
136125046-65149-DETAIL-03_06_2023-GO95HV-1^07216001.0297706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
136125046-65149-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
951661438-91008-DETAIL-03_06_2023-SVCWIND-1^07216001.0297741 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
36910528-80468-DETAIL-03_06_2023-SVCWIND-1^07216001.0297742 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
924391436-16939-DETAIL-02_27_2023-GO95HV-1^07216001.0297800 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
488315705-32249-DETAIL-02_28_2023-GO95MLD-1^07216001.0297804 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
276444661-12459-DETAIL-02_27_2023-GO95MLD-1^07216001.0297806 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
635304390-62249-DETAIL-02_27_2023-SVCWIND-1^07216001.0297807 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
255867706-60339-DETAIL-02_27_2023-GO95MLD-1^07216001.0297808 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
255867706-60339-DETAIL-02_27_2023-SVCWIND-1^07216001.0297808 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
774038556-59049-DETAIL-02_27_2023-GO95HV-1^07216001.0297809 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
313810864-63249-DETAIL-02_27_2023-GO95MLD-1^07216001.0297811 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
19797823-2159-DETAIL-05_03_2022-GO95HV-1^07217001.0246602 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
876954113-11249-DETAIL-05_03_2022-GO95MLD-1^07217001.0246700 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
707004693-15059-DETAIL-05_03_2022-GO95MLD-1^07217001.0246900 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
98934659-86159-DETAIL-05_03_2022-GO95MLD-1^07217001.0247202 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
534190159-95159-DETAIL-05_03_2022-GO95MLD-1^07217001.0247301 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
374873739-63159-DETAIL-05_03_2022-GO95CL10-1^07217001.0247402 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
374873739-63159-DETAIL-05_03_2022-GO95MLD-1^07217001.0247402 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
374873739-63159-DETAIL-05_03_2022-GUYLOINS-1^07217001.0247402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
747135439-41249-DETAIL-05_03_2022-GO95MLD-1^07217001.0247500 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
114072428-8979-DETAIL-05_03_2022-SVCENTCO-1^07217001.0247541 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
992411599-72159-DETAIL-05_03_2022-CLRTOUCH-1^07217001.0247640 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
165460903-51159-DETAIL-05_03_2022-GO95MLD-1^07217001.0247801 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
659668993-43059-DETAIL-05_04_2022-GO95TCH-1^07217001.0247902 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
50440679-71859-DETAIL-05_03_2022-CLRTOUCH-1^07217001.0248002 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
50440679-71859-DETAIL-05_03_2022-GO95MLD-1^07217001.0248002 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
50440679-71859-DETAIL-05_03_2022-SVCENTCO-1^07217001.0248002 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
313810864-63249-DETAIL-02_27_2023-SVCNEUT-1^07216001.0297811 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
563998896-22839-DETAIL-02_23_2023-GO95CL10-1^07216001.0297901 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
503715096-87781-DETAIL-02_27_2023-SVCDEFLC-1^07216001.0297902 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
291484906-4849-DETAIL-02_23_2023-SVCENTCO-1^07216001.0297903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
733090030-48049-DETAIL-02_27_2023-GO95MLD-1^07216001.0297905 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
910099054-35393-DETAIL-02_23_2023-GO95MLD-1^07216001.0297907 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
641003518-83950-DETAIL-02_27_2023-GO95TCH-1^07216001.0297944 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
670967418-85250-DETAIL-02_23_2023-SVCENTCO-1^07216001.0297945 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
510319248-39248-DETAIL-02_27_2023-CLRTOPOL-1^07216001.0297970 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
926556165-26842-DETAIL-03_06_2023-GO95HV-1^07216001.0298402 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
168899665-87359-DETAIL-03_06_2023-GO95MLD-1^07216001.0298404 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
761047358-48358-DETAIL-03_07_2023-GO95HV-1^07216001.0298405 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
761047358-48358-DETAIL-03_07_2023-GO95TCH-1^07216001.0298405 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
63419495-48359-DETAIL-03_07_2023-GO95MLD-1^07216001.0298406 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
218771099-44450-DETAIL-02_28_2023-GO95MLD-1^07216001.0298501 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
833539094-21194-DETAIL-02_28_2023-GO95MLD-1^07216001.0298504 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
858379979-34349-DETAIL-02_28_2023-GO95MLD-1^07216001.0298505 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
188605489-96239-DETAIL-02_28_2023-GO95MLD-1^07216001.0298506 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
828675069-17449-DETAIL-02_28_2023-GO95MLD-1^07216001.0298508 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
145462279-47249-DETAIL-03_02_2023-GO95TCH-1^07216001.0298600 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
804627468-20168-DETAIL-02_28_2023-GUYHINS-1^07216001.0298601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
746701568-12568-DETAIL-02_28_2023-GO95MLD-1^07216001.0298603 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
746701568-12568-DETAIL-02_28_2023-GUYHINS-1^07216001.0298603 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
50440679-71859-DETAIL-05_03_2022-SVCWIND-1^07217001.0248002 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
463546669-32249-DETAIL-05_03_2022-GO95MLD-1^07217001.0248102 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
463546669-32249-DETAIL-05_03_2022-SVCNEUT-1^07217001.0248102 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
666179069-2249-ADMIN-11_27_2023-POLEDERP-1^07217001.0248105 | POLE | CA-NON-TIER | Distribution | 2023-11-27 | 2026-11-27 | 2
923556643-28941-DETAIL-05_04_2022-GO95MLD-1^07217001.0248601 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
621997539-38539-DETAIL-05_04_2022-GO95MLD-1^07217001.0248602 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
331415489-36933-DETAIL-05_12_2022-GO95MLD-1^07217001.0249300 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
864952589-55933-DETAIL-05_12_2022-GO95HV-1^07217001.0249301 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
746701568-12568-DETAIL-02_28_2023-GUYHINS-2^07216001.0298603 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
450306309-19939-DETAIL-02_28_2023-GO95MLD-1^07216001.0298604 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
812279609-89049-DETAIL-02_28_2023-GO95MLD-1^07216001.0298605 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
785350468-22468-DETAIL-02_28_2023-CLRTOUCH-1^07216001.0298606 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
569075719-38249-DETAIL-02_28_2023-GO95HV-1^07216001.0298607 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
521870399-69901-DETAIL-02_28_2023-RISEGRD-1^07216001.0298608 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
455553348-76238-DETAIL-03_02_2023-GO95TCH-1^07216001.0298640 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
105847528-54668-DETAIL-02_28_2023-GO95TCH-1^07216001.0298644 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
864952589-55933-DETAIL-05_12_2022-GUYSLACK-1^07217001.0249301 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
439961613-8641-DETAIL-05_04_2022-GO95MLD-1^07217001.0249801 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
271268403-40641-DETAIL-05_04_2022-ABNDEQPM-1^07217001.0249804 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2027-05-04 | 3
787890983-72441-DETAIL-05_04_2022-GO95MLD-1^07217001.0249900 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2027-05-04 | 3
691648823-31453-DETAIL-04_27_2022-GO95MLD-1^07217001.0262000 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
155857613-9353-DETAIL-04_27_2022-GO95HV-1^07217001.0262001 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
484325013-97353-DETAIL-04_27_2022-GO95CL10-1^07217001.0262100 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
266260953-76953-DETAIL-04_27_2022-GO95MLD-1^07217001.0262200 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
430439743-23953-DETAIL-04_27_2022-GO95TCH-1^07217001.0262203 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
366317371-92153-DETAIL-04_28_2022-GUYHINS-1^07217001.0262300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
948119013-35853-DETAIL-04_27_2022-GO95HV-1^07217001.0262304 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
974577343-38153-DETAIL-04_27_2022-GO95BLTC-1^07217001.0262403 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
976874333-66153-DETAIL-04_27_2022-GO95MLD-1^07217001.0262404 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
847761183-16753-DETAIL-04_27_2022-GO95TCH-1^07217001.0262405 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
955816393-48253-DETAIL-04_27_2022-SVCROAD-1^07217001.0263003 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
194723403-50653-DETAIL-04_27_2022-GO95MLD-1^07217001.0263300 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
222807139-8549-DETAIL-02_28_2023-GO95MLD-1^07216001.0298702 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
584105401-16591-DETAIL-03_01_2023-GO95HV-1^07216001.0298704 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
584105401-16591-DETAIL-03_01_2023-GO95MLD-1^07216001.0298704 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
179145246-68049-DETAIL-02_28_2023-SVCENTCO-1^07216001.0298705 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
449399538-79639-DETAIL-02_28_2023-GO95TCH-1^07216001.0298742 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
944363512-93389-DETAIL-02_27_2023-GO95HV-1^07216001.0298801 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
944363512-93389-DETAIL-02_27_2023-GO95MLD-1^07216001.0298801 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
452971556-32459-DETAIL-02_27_2023-CLRTOPOL-1^07216001.0298802 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
881270005-76849-DETAIL-02_27_2023-SVCENTCO-1^07216001.0298804 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
226046686-49639-DETAIL-02_27_2023-SVCWIND-1^07216001.0298805 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
809597945-18039-DETAIL-02_27_2023-CLMBTRE-1^07216001.0298806 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
564826093-47038-DETAIL-02_23_2023-CLRTOUCH-1^07216001.0298808 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
564826093-47038-DETAIL-02_23_2023-GO95MLD-1^07216001.0298808 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
437151346-55349-DETAIL-02_23_2023-GO95MLD-1^07216001.0298810 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
437151346-55349-DETAIL-02_23_2023-GO95TCH-1^07216001.0298810 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
790317128-32219-DETAIL-02_28_2023-GO95TCH-1^07216001.0298840 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
688965238-80399-DETAIL-02_27_2023-SVCENTCO-1^07216001.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
887194521-83282-DETAIL-02_23_2023-GO95MLD-1^07216001.0298903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
165602176-89610-DETAIL-02_23_2023-CLMBHAZ-1^07216001.0298905 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
165602176-89610-DETAIL-02_23_2023-GO95HV-1^07216001.0298905 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
165602176-89610-DETAIL-02_23_2023-GO95TCH-1^07216001.0298905 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
890878505-51349-DETAIL-02_23_2023-ABNDEQPM-1^07216001.0298906 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
349608800-24690-DETAIL-02_23_2023-GO95MLD-1^07216001.0298909 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
303650029-10449-DETAIL-02_28_2023-GO95HV-1^07216001.0299400 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
702247901-49059-DETAIL-04_27_2022-GO95STUB-1^07217001.0264000 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
903409253-19153-DETAIL-04_27_2022-GO95MLD-1^07217001.0264002 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
337015661-72843-DETAIL-04_27_2022-GO95MLD-1^07217001.0264302 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
979858203-70959-DETAIL-04_27_2022-GO95MLD-1^07217001.0264303 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
55376759-16678-DETAIL-04_27_2022-GO95MLD-1^07217001.0264304 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
601810659-5768-DETAIL-04_28_2022-CONDCOIL-1^07217001.0265301 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
640743601-98059-DETAIL-05_04_2022-GO95MLD-1^07217001.0266300 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
678903991-65643-DETAIL-05_11_2022-GO95HV-1^07217001.0269300 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2027-05-11 | 3
553652259-31239-DETAIL-02_28_2023-GO95MLD-1^07216001.0299600 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
553652259-31239-DETAIL-02_28_2023-GO95TCH-1^07216001.0299600 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
822334889-90639-DETAIL-02_28_2023-GO95MLD-2^07216001.0299601 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
751216829-25039-DETAIL-02_28_2023-GO95HV-1^07216001.0299602 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
660057518-37049-DETAIL-02_28_2023-GO95HV-1^07216001.0299605 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
660057518-37049-DETAIL-02_28_2023-GO95MLD-1^07216001.0299605 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
656174001-53301-DETAIL-02_28_2023-SVCDEFLC-1^07216001.0299700 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
163717971-53643-DETAIL-05_12_2022-SVCWIND-1^07217001.0269401 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
601865363-68453-DETAIL-05_12_2022-GO95TCH-1^07217001.0269402 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
789220671-76533-DETAIL-04_28_2022-GO95MLD-1^07217001.0360000 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
179970041-7143-DETAIL-05_11_2022-GO95HV-1^07217001.0360840 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2027-05-11 | 3
621202164-31883-ADMIN-10_10_2023-POLEREPL-1^07218001.0087502 | POLE | CA-NON-TIER | Distribution | 2023-10-10 | 2026-10-10 | 2
818281441-469-DTLTRT-10_24_2022-GO95MLD-1^668001/00 1/024 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
818281441-469-DTLTRT-10_24_2022-GUYHINS-1^668001/00 1/024 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
959870934-58499-DTLTRT-11_15_2022-GO95HV-1^668001/00 1/043 | OTHER | CA-TIER-2 | Transmission | 2022-11-15 | 2027-11-15 | 3
358076479-51669-DTLTRT-11_15_2022-GO95HV-1^668001/00 1/048 | OTHER | CA-TIER-2 | Transmission | 2022-11-15 | 2027-11-15 | 3
85218943-51689-DTLTRT-11_07_2022-GO95HV-1^668001/00 10/030 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2027-11-07 | 3
566490951-94369-DTLTRT-10_24_2022-GO95MLD-1^668001/00 11/024 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
621562851-61131-DETAIL-12_22_2022-GO95MLD-1^668001/00 13/023 | OTHER | CA-NON-TIER | Transmission | 2022-12-22 | 2025-12-22 | 2
320857180-20209-DTLTRT-10_26_2022-GO95MLD-1^668001/00 13/028 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
179822991-43999-DTLTRT-11_07_2022-GO95HV-1^668001/00 13/029 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2027-11-07 | 3
970746179-15299-DTLTRT-11_10_2022-GO95HV-1^668001/00 13/038 | OTHER | CA-TIER-2 | Transmission | 2022-11-10 | 2027-11-10 | 3
306527538-60263-DETAIL-10_25_2022-GO95HV-1^668001/00 13/046 | OTHER | CA-TIER-2 | Transmission | 2022-10-25 | 2027-10-25 | 3
928729426-60849-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
771795238-94349-DETAIL-02_23_2023-ABNDEQPM-1^07216001.0299705 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
202652778-6838-DETAIL-02_23_2023-GO95MLD-1^07216001.0299707 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
697969085-78949-DETAIL-02_23_2023-GO95MLD-1^07216001.0299710 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
649476326-25349-DETAIL-02_28_2023-GUYHINS-1^07216001.0299711 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
321965929-33459-DETAIL-02_28_2023-GO95TCH-1^07216001.0299740 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
321965929-33459-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299740 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
991808058-6668-DETAIL-02_28_2023-GO95MLD-1^07216001.0299802 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
641272135-90349-DETAIL-02_28_2023-GO95HV-1^07216001.0299803 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
485607465-60349-DETAIL-02_28_2023-CLMBTRE-1^07216001.0299804 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
485607465-60349-DETAIL-02_28_2023-GO95HV-1^07216001.0299804 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
23192375-47049-DETAIL-03_15_2023-CLMBHAZ-1^07216001.0299805 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
23192375-47049-DETAIL-03_15_2023-GO95HV-1^07216001.0299805 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
148487690-3639-DETAIL-06_28_2021-GO95TCH-1^07217001.0118700 | OTHER | CA-NON-TIER | Distribution | 2021-06-28 | 2024-06-28 | 2
125041842-9843-DETAIL-05_05_2022-GO95HV-1^07217001.0120200 | OTHER | CA-NON-TIER | Distribution | 2022-05-05 | 2027-05-05 | 3
95227091-41059-DETAIL-05_09_2022-GUYNOINS-1^07217001.0120303 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-09 | 2025-05-09 | 2
866338354-89999-DTLTRT-10_27_2022-GUYNOINS-1^668001/00 13A/031 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-27 | 2025-10-27 | 2
866338354-89999-DTLTRT-10_27_2022-GUYNOINS-2^668001/00 13A/031 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-27 | 2025-10-27 | 2
452390701-73999-DTLTRT-11_07_2022-GO95MLD-1^668001/00 14/029 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
393401173-85469-DTLTRT-11_07_2022-GO95BLTC-1^668001/00 14/030 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2027-11-07 | 3
393401173-85469-DTLTRT-11_07_2022-GO95MLD-1^668001/00 14/030 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
446534746-46746-DTLTRT-11_17_2022-GO95MLD-1^668001/00 14/046 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
266873219-71473-DTLTRT-11_17_2022-GO95HV-1^668001/00 14A/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
263548429-42473-DTLTRT-11_17_2022-GO95HV-1^668001/00 15/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
332215591-27059-DETAIL-05_05_2022-GUYSLACK-1^07217001.0120400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
21564181-76059-DETAIL-05_05_2022-COPLLEAN-1^07217001.0120500 | POLE | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
582559031-81549-DETAIL-05_04_2022-GO95MLD-1^07217001.0120502 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
79664771-45339-DETAIL-05_09_2022-SVCROAD-1^07217001.0120900 | OTHER | CA-NON-TIER | Distribution | 2022-05-09 | 2025-05-09 | 2
842245333-45439-DETAIL-05_12_2022-GO95MLD-1^07217001.0120901 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
337209562-19843-DETAIL-05_03_2022-GO95HV-1^07217001.0121000 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
589634531-92649-DETAIL-05_05_2022-GO95MLD-1^07217001.0121500 | OTHER | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
48542202-11159-DETAIL-05_03_2022-GO95HV-1^07217001.0122003 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
398594481-2209-DETAIL-12_20_2022-UBPBGYSL-1^668001/00 18/028 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-20 | 2025-12-20 | 2
604131985-82985-DTLTRT-11_07_2022-GO95MLD-1^668001/00 18/031 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
981161603-64309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 19/030 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
392163998-80599-DETAIL-11_15_2022-GUYNOINS-1^668001/00 19/045 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-15 | 2025-11-15 | 2
191697019-91573-DTLTRT-11_17_2022-GO95HV-1^668001/00 19/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
837092141-31222-DETAIL-12_19_2022-GO95HV-1^668001/00 2/024 | OTHER | CA-NON-TIER | Transmission | 2022-12-19 | 2027-12-19 | 3
14928168-67843-DETAIL-12_22_2022-GRDRODHI-1^668001/00 2/032 | OTHER | CA-NON-TIER | Transmission | 2022-12-22 | 2025-12-22 | 2
578684449-46573-DTLTRT-11_17_2022-GO95HV-1^668001/00 20A/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
739110002-85359-DETAIL-05_03_2022-GO95HV-1^07217001.0122100 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
665981142-10159-DETAIL-05_05_2022-GO95HV-1^07217001.0122200 | OTHER | CA-NON-TIER | Distribution | 2022-05-05 | 2027-05-05 | 3
187195641-79049-DETAIL-05_04_2022-GO95MLD-1^07217001.0122400 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
626878141-1849-DETAIL-05_04_2022-GO95MLD-1^07217001.0122401 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
505414134-48733-DETAIL-05_03_2022-GO95MLD-1^07217001.0123001 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
286069034-4820-DETAIL-05_03_2022-GO95HV-1^07217001.0123002 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
569917873-83253-DETAIL-05_03_2022-GO95HV-1^07217001.0134800 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
569917873-83253-DETAIL-05_03_2022-GO95MLD-1^07217001.0134800 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
254818183-16253-DETAIL-05_03_2022-GO95TCH-1^07217001.0135701 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
909068693-68253-DETAIL-05_03_2022-GO95MLD-1^07217001.0136601 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
218843813-3059-DETAIL-05_04_2022-GO95HV-1^07217001.0137000 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2027-05-04 | 3
218843813-3059-DETAIL-05_04_2022-GO95MLD-1^07217001.0137000 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
634434543-93953-DETAIL-05_05_2022-GO95MLD-1^07217001.0137300 | OTHER | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
827914273-99953-DETAIL-05_12_2022-GUYNOINS-1^07217001.0137401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
920576670-19670-DETAIL-05_12_2022-GO95MLD-1^07217001.0137404 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
129156853-45953-DETAIL-05_12_2022-ABNDEQPM-1^07217001.0137500 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
129156853-45953-DETAIL-05_12_2022-GO95TCH-1^07217001.0137500 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
566265603-91353-DETAIL-05_12_2022-CLRTOUCH-1^07217001.0137501 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
566265603-91353-DETAIL-05_12_2022-GO95GUYP-1^07217001.0137501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
531824163-77953-DETAIL-05_12_2022-GO95HV-1^07217001.0137600 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
298862523-89853-DETAIL-05_03_2022-GO95MLD-1^07217001.0137700 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
75488754-64871-DETAIL-05_04_2022-GO95HV-1^07217001.0139000 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2027-05-04 | 3
400268258-96723-ADMIN-10_31_2023-POLEREPL-1^07217001.0148040 | POLE | CA-NON-TIER | Distribution | 2023-10-31 | 2026-10-31 | 2
675722828-82828-ADMIN-12_29_2022-POLEREPL-1^07217001.0227040 | POLE | CA-NON-TIER | Distribution | 2022-12-29 | 2025-12-29 | 2
502045270-97369-DTLTRT-10_24_2022-GO95HV-1^668001/00 24/022 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2027-10-24 | 3
502045270-97369-DTLTRT-10_24_2022-GUYHINS-3^668001/00 24/022 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
502045270-97369-DETAIL-12_19_2022-GUYHINS-3^668001/00 24/022 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-19 | 2025-12-19 | 2
794604550-59679-DTLTRT-10_24_2022-GO95HV-1^668001/00 3/023 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2027-10-24 | 3
108106870-10779-DTLTRT-10_24_2022-GO95HV-1^668001/00 4/023 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2027-10-24 | 3
179008721-44209-DTLTRT-10_27_2022-GO95MLD-1^668001/00 4/029 | OTHER | CA-NON-TIER | Transmission | 2022-10-27 | 2025-10-27 | 2
612593103-85009-DTLTRT-11_07_2022-GO95MLD-1^668001/00 5/030 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
31872591-10609-DTLTRT-11_07_2022-GO95HV-1^668001/00 5/032 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2027-11-07 | 3
31872591-10609-DTLTRT-11_07_2022-GO95MLD-1^668001/00 5/032 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
87665190-38369-DETAIL-10_24_2022-ANCHIDLE-1^668001/00 6/023 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
802240241-79899-DTLTRT-10_27_2022-GO95MLD-1^668001/00 6/029 | OTHER | CA-NON-TIER | Transmission | 2022-10-27 | 2025-10-27 | 2
789834401-4662-DTLTRT-10_24_2022-GO95MLD-1^668001/00 7/023 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
585249973-70883-DTLTRT-11_07_2022-GO95MLD-1^668001/00 7/031 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
238217911-20970-DTLTRT-10_24_2022-GUYHINS-3^668001/00 8/023 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
238217911-20970-DETAIL-12_20_2022-GO95HV-1^668001/00 8/023 | OTHER | CA-NON-TIER | Transmission | 2022-12-20 | 2027-12-20 | 3
763756231-67991-DTLTRT-10_24_2022-GO95MLD-1^668001/00 9/024 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
945808738-95323-DETAIL-04_28_2022-GO95TCH-1^07217001.0230000 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
248016788-25123-DETAIL-04_26_2022-GO95HV-1^07217001.0230001 | OTHER | CA-NON-TIER | Distribution | 2022-04-26 | 2027-04-26 | 3
123516098-87123-DETAIL-04_27_2022-GO95MLD-1^07217001.0237101 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
166918238-67323-DETAIL-05_12_2022-GO95MLD-1^07217001.0237400 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
166918238-67323-DETAIL-05_12_2022-SVCNEUT-1^07217001.0237400 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
130557618-90323-DETAIL-05_04_2022-GO95MLD-1^07217001.0237700 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
841749528-33159-DETAIL-04_27_2022-GO95HV-1^07217001.0238300 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
883701528-74323-DETAIL-05_12_2022-GO95MLD-1^07217001.0238401 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
883701528-74323-DETAIL-05_12_2022-GO95TCH-1^07217001.0238401 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
819408778-99023-DETAIL-05_12_2022-GO95HV-1^07217001.0238500 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
236113078-29023-DETAIL-05_05_2022-GO95TCH-1^07217001.0238702 | OTHER | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
37204078-20123-DETAIL-05_12_2022-CLRTOUCH-1^07217001.0239500 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
61747583-52159-DETAIL-05_03_2022-GO95MLD-1^07217001.0246601 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
19797823-2159-DETAIL-05_03_2022-GO95MLD-1^07217001.0246602 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
695755813-1959-DETAIL-05_03_2022-ABNDEQPM-1^07217001.0246800 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
695755813-1959-DETAIL-05_03_2022-GO95MLD-1^07217001.0246800 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
443796761-1999-DTLTRT-11_07_2022-GO95MLD-1^668001/00 9/029 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
493535233-67009-DTLTRT-11_07_2022-GO95HV-1^668001/00 9/030 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2027-11-07 | 3
704658345-78345-DETAIL-11_17_2022-GO95HV-1^668001/06 1X2/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
284314564-6983-DTLTRT-11_17_2022-GO95HV-1^668001/06 2/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
560541204-68083-DTLTRT-11_17_2022-GUYHINS-1^668001/06 7/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
26691084-24269-DRONE_HY-09_21_2023-GO95HV-1^668002/00 1/001 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
881946201-18369-DRONE_HY-09_21_2023-GO95HV-1^668002/00 10/069 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
665080454-65969-DETAIL-03_08_2023-GO95HV-1^668002/00 11/034 | OTHER | CA-TIER-2 | Transmission | 2023-03-08 | 2028-03-08 | 3
411175129-82179-DRONE_HY-09_13_2023-GO95HV-1^668002/00 11/077 | OTHER | CA-TIER-2 | Transmission | 2023-09-13 | 2028-09-13 | 3
285001068-69743-DRONE_HY-09_21_2023-INSULBRK-1^668002/00 11A/001 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-09-21 | 2024-09-21 | 2
507691148-28469-DRONE_HY-09_14_2023-GO95HV-1^668002/00 12/012 | OTHER | CA-NON-TIER | Transmission | 2023-09-14 | 2028-09-14 | 3
910207911-91469-DETAIL-02_23_2023-GO95HV-1^668002/00 12/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
528229139-70069-DRONE_HY-09_14_2023-GO95HV-1^668002/00 12/041 | OTHER | CA-TIER-2 | Transmission | 2023-09-14 | 2028-09-14 | 3
747506958-85423-DRONE_HY-09_14_2023-GO95HV-1^668002/00 13/012 | OTHER | CA-NON-TIER | Transmission | 2023-09-14 | 2028-09-14 | 3
389556421-22619-DRONE_HY-09_22_2023-XARMBRAC-1^668002/00 14/072 | CROSSARM | CA-TIER-2 | Transmission | 2023-09-22 | 2028-09-22 | 3
707004693-15059-DETAIL-05_03_2022-GO95TCH-1^07217001.0246900 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
906110753-47159-DETAIL-05_03_2022-GO95MLD-1^07217001.0247200 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
98934659-86159-DETAIL-05_03_2022-CLMBHAZ-1^07217001.0247202 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
534190159-95159-DETAIL-05_03_2022-GO95HV-1^07217001.0247301 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
367969849-18959-DETAIL-05_03_2022-GO95MLD-1^07217001.0247401 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
374873739-63159-DETAIL-05_03_2022-ANCPUCO-1^07217001.0247402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
374873739-63159-DETAIL-05_03_2022-GO95HV-1^07217001.0247402 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2027-05-03 | 3
374873739-63159-DETAIL-05_03_2022-GUYHINS-1^07217001.0247402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
374873739-63159-DETAIL-05_03_2022-GUYNOINS-1^07217001.0247402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
290134019-84159-DETAIL-05_03_2022-GUYLOINS-1^07217001.0247441 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
728279523-43159-ADMIN-10_27_2023-POLEREPL-1^07217001.0247501 | POLE | CA-NON-TIER | Distribution | 2023-10-27 | 2026-10-27 | 2
165460903-51159-DETAIL-05_03_2022-GO95TCH-1^07217001.0247801 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
659668993-43059-DETAIL-05_04_2022-GO95MLD-1^07217001.0247902 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
973695553-12859-DETAIL-05_04_2022-GUYSLACK-1^07217001.0248000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
844029779-91859-ADMIN-11_27_2023-POLEDERP-1^07217001.0248001 | POLE | CA-NON-TIER | Distribution | 2023-11-27 | 2026-11-27 | 2
274323368-64079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 14/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
929789549-19769-ADMIN-08_03_2023-INSULDMG-1^668002/00 15/049 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-08-03 | 2024-08-03 | 2
192490768-40179-DRONE_HY-09_22_2023-GUYSLACK-1^668002/00 15/076 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-22 | 2024-09-22 | 2
525312651-47369-DETAIL-03_09_2023-GO95HV-1^668002/00 16/004 | OTHER | CA-NON-TIER | Transmission | 2023-03-09 | 2028-03-09 | 3
91220239-78769-DETAIL-02_15_2023-GO95HV-1^668002/00 16/014 | OTHER | CA-NON-TIER | Transmission | 2023-02-15 | 2028-02-15 | 3
849562902-28969-DRONE_HY-08_31_2023-DISTHDWR-1^668002/00 16/031 | CONNECTION DEVICE | CA-TIER-2 | Transmission | 2023-08-31 | 2024-08-31 | 2
544382559-29769-DETAIL-06_08_2023-XARMSPCR-1^668002/00 16/049 | CROSSARM | CA-TIER-2 | Transmission | 2023-06-08 | 2024-06-08 | 2
50440679-71859-DETAIL-05_03_2022-GO95TCH-1^07217001.0248002 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
296893783-18159-DETAIL-05_03_2022-GO95TCH-1^07217001.0248104 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
91954259-17159-DETAIL-05_03_2022-GO95MLD-1^07217001.0248200 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
985219863-62049-DETAIL-05_03_2022-GO95MLD-1^07217001.0248300 | OTHER | CA-NON-TIER | Distribution | 2022-05-03 | 2025-05-03 | 2
926646123-42741-DETAIL-05_04_2022-SVCNEUT-1^07217001.0248704 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
864952589-55933-DETAIL-05_12_2022-GO95MLD-1^07217001.0249301 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
709038063-12151-DETAIL-05_04_2022-SVCROOF-1^07217001.0249800 | OTHER | CA-TIER-2 | Distribution | 2022-05-04 | 2025-05-04 | 2
708015711-5443-DETAIL-05_04_2022-GO95MLD-1^07217001.0259902 | OTHER | CA-NON-TIER | Distribution | 2022-05-04 | 2025-05-04 | 2
780138493-44553-DETAIL-04_27_2022-INSULDMG-1^07217001.0261000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
366317371-92153-DETAIL-04_28_2022-CLRTOUCH-1^07217001.0262300 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
366317371-92153-DETAIL-04_28_2022-GO95MLD-1^07217001.0262300 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
222300481-16843-DETAIL-04_28_2022-GO95MLD-1^07217001.0262301 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
775226613-46853-DETAIL-04_27_2022-GO95HV-1^07217001.0262303 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
515634371-74843-DETAIL-04_27_2022-GO95MLD-1^07217001.0262306 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
623883111-71943-DETAIL-04_27_2022-GO95HV-1^07217001.0263001 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
653257033-43453-DETAIL-04_27_2022-GRDRODHI-1^07217001.0263100 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
967390479-23269-DRONE_HY-09_21_2023-GO95HV-1^668002/00 16/066 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
324825542-39870-DRONE_HY-09_19_2023-GO95HV-1^668002/00 16/071 | OTHER | CA-TIER-2 | Transmission | 2023-09-19 | 2028-09-19 | 3
843513721-98779-DRONE_HY-09_19_2023-COPLLEAN-1^668002/00 17/003 | POLE | CA-NON-TIER | Transmission | 2023-09-19 | 2026-09-19 | 2
211939961-87369-DETAIL-03_09_2023-GO95HV-1^668002/00 17/004 | OTHER | CA-NON-TIER | Transmission | 2023-03-09 | 2028-03-09 | 3
133076909-52869-DRONE_HY-09_14_2023-GO95HV-1^668002/00 17/015 | OTHER | CA-NON-TIER | Transmission | 2023-09-14 | 2028-09-14 | 3
563779128-35079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 17/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
55885559-98769-DETAIL-02_15_2023-GO95HV-1^668002/00 18/014 | OTHER | CA-NON-TIER | Transmission | 2023-02-15 | 2028-02-15 | 3
487609958-32569-DRONE_HY-09_14_2023-GO95HV-1^668002/00 18/048 | OTHER | CA-TIER-2 | Transmission | 2023-09-14 | 2028-09-14 | 3
915274043-25453-DETAIL-04_27_2022-GO95HV-1^07217001.0263200 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
194723403-50653-DETAIL-04_27_2022-GO95HV-1^07217001.0263300 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
916627271-48449-DETAIL-04_27_2022-GO95MLD-1^07217001.0263301 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
483958101-943-DETAIL-04_27_2022-SVCDEFLC-1^07217001.0264001 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
958744311-86943-DETAIL-04_27_2022-GO95MLD-1^07217001.0264003 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
958744311-86943-DETAIL-04_27_2022-GO95TCH-1^07217001.0264003 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
958744311-86943-DETAIL-04_27_2022-SVCDEFLC-1^07217001.0264003 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
549497451-30843-DETAIL-04_27_2022-GO95MLD-1^07217001.0264004 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
878297551-38743-DETAIL-04_27_2022-GO95CL10-1^07217001.0264100 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2027-04-27 | 3
465191403-53853-DETAIL-04_27_2022-SVCROOF-1^07217001.0264202 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
525638641-36743-DETAIL-04_27_2022-GO95MLD-1^07217001.0264203 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
85808241-95743-DETAIL-04_27_2022-GO95MLD-1^07217001.0264204 | OTHER | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
337015661-72843-DETAIL-04_27_2022-CLRTOUCH-1^07217001.0264302 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
55376759-16678-DETAIL-04_27_2022-GUYSLACK-1^07217001.0264304 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
960038659-88238-DETAIL-04_27_2022-GUYNOINS-1^07217001.0264340 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-04-27 | 2025-04-27 | 2
683178173-59469-DETAIL-06_20_2023-CONDLOOS-1^668002/00 19/045 | CONDUCTOR | CA-TIER-2 | Transmission | 2023-06-20 | 2024-06-20 | 2
166030043-37940-DRONE_HY-09_14_2023-GO95HV-1^668002/00 19/055 | OTHER | CA-TIER-3 | Transmission | 2023-09-14 | 2028-09-14 | 3
442502136-52560-DETAIL-07_09_2018-GO95STUB-1^668002/00 19X/054 | OTHER | CA-TIER-3 | Transmission | 2018-07-09 | 2023-06-09 | 2
531297279-44869-DRONE_HY-09_14_2023-GO95HV-1^668002/00 5/016 | OTHER | CA-NON-TIER | Transmission | 2023-09-14 | 2028-09-14 | 3
449945344-55669-DRONE_HY-09_29_2023-INSULBRK-1^668002/00 6/011 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-09-29 | 2028-09-29 | 3
191432041-38869-DRONE_HY-09_03_2023-GO95HV-1^668002/00 6/017 | OTHER | CA-NON-TIER | Transmission | 2023-09-03 | 2028-09-03 | 3
159542153-61069-DETAIL-03_08_2023-GO95BLTC-1^668002/00 6/032 | OTHER | CA-TIER-2 | Transmission | 2023-03-08 | 2026-03-08 | 2
1643808-41469-DRONE_HY-09_12_2023-INSULDMG-1^668002/00 7/012 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-09-12 | 2028-09-12 | 3
229239593-90069-DRONE_HY-09_14_2023-GO95HV-1^668002/00 8/020 | OTHER | CA-NON-TIER | Transmission | 2023-09-14 | 2028-09-14 | 3
148899671-44469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 9/006 | CROSSARM | CA-NON-TIER | Transmission | 2023-09-12 | 2028-09-12 | 3
3345101-11469-DETAIL-02_23_2023-GO95HV-1^668002/00 9/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
351639731-40369-DRONE_HY-09_16_2023-GO95HV-1^668002/00 9/061 | OTHER | CA-TIER-2 | Transmission | 2023-09-16 | 2028-09-16 | 3
847046054-43250-DRONE_HY-09_20_2023-GO95HV-1^668002/00 9C/058 | OTHER | CA-TIER-2 | Transmission | 2023-09-20 | 2028-09-20 | 3
56490293-95859-DETAIL-01_31_2023-GRDRODHI-1^668002/07 17/002 | OTHER | CA-TIER-2 | Transmission | 2023-01-31 | 2026-01-31 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-2^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
601810659-5768-DETAIL-04_28_2022-GO95MLD-1^07217001.0265301 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
369091331-3743-DETAIL-04_28_2022-GO95HV-1^07217001.0265302 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
369091331-3743-DETAIL-04_28_2022-GO95MLD-1^07217001.0265302 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
446806121-32743-DETAIL-04_28_2022-SVCROAD-1^07217001.0265400 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
748243621-88643-DETAIL-04_28_2022-GO95HV-1^07217001.0265403 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2027-04-28 | 3
782642606-71634-DETAIL-05_11_2022-GO95TCH-1^07217001.0269302 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
601865363-68453-DETAIL-05_12_2022-CLRTOUCH-1^07217001.0269402 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
24122403-41353-DETAIL-04_28_2022-GO95MLD-1^07217001.0269600 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
715018536-36473-ADMIN-05_20_2022-GO95HV-1^07217001.0275000 | OTHER | CA-NON-TIER | Distribution | 2022-05-20 | 2027-05-20 | 3
243249845-2645-DETAIL-07_14_2022-SVCROAD-1^07217001.0345040 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
789220671-76533-DETAIL-04_28_2022-GO95TCH-1^07217001.0360000 | OTHER | CA-NON-TIER | Distribution | 2022-04-28 | 2025-04-28 | 2
290743751-19143-DETAIL-05_11_2022-SVCWIND-1^07217001.0360300 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
682165051-48143-DETAIL-05_11_2022-GO95MLD-1^07217001.0360802 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
682165051-48143-DETAIL-05_11_2022-SVCDEFLC-1^07217001.0360802 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
682165051-48143-DETAIL-05_11_2022-SVCDEFLC-2^07217001.0360802 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
179970041-7143-DETAIL-05_11_2022-GO95TCH-1^07217001.0360840 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
372753991-65991-ADMIN-08_04_2023-POLEREPL-1^07218001.0219500 | POLE | CA-NON-TIER | Distribution | 2023-08-04 | 2026-08-04 | 2
153471741-38690-DTLTRT-10_24_2022-GO95HV-1^668001/00 11/023 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2027-10-24 | 3
538645071-62369-DTLTRT-10_24_2022-GO95MLD-1^668001/00 12/024 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
538364670-42329-DTLTRT-10_26_2022-GO95HV-1^668001/00 12/028 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2027-10-26 | 3
866338354-89999-DTLTRT-10_27_2022-GUYNOINS-3^668001/00 13A/031 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-27 | 2025-10-27 | 2
193754063-96399-DTLTRT-11_14_2022-GO95HV-1^668001/00 14/041 | OTHER | CA-TIER-2 | Transmission | 2022-11-14 | 2027-11-14 | 3
456205871-81209-DETAIL-12_20_2022-CLRTOUCH-1^668001/00 17/028 | CONDUCTOR | CA-NON-TIER | Transmission | 2022-12-20 | 2025-12-20 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-3^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-5^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
551094510-39070-DTLTRT-11_16_2022-GO95HV-1^668003/00 12X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
415594390-80370-DTLTRT-11_16_2022-GO95HV-1^668003/00 14X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
398579100-37370-DTLTRT-11_16_2022-GO95HV-1^668003/00 17X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
946257990-98040-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 5X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
946257990-98040-DTLTRT-11_16_2022-GUYNOINS-2^668003/00 5X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
440264480-55670-DTLTRT-11_16_2022-GO95HV-1^668003/00 7X/002 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
318923400-34070-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 8X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
38176059-48159-ADMIN-09_01_2022-POLEDERP-1^668004/00 12/024 | POLE | CA-NON-TIER | Transmission | 2022-09-01 | 2025-09-01 | 2
945076758-76969-DTLTRT-06_30_2022-GO95HV-1^668005/00 1/031 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
652021908-17269-DTLTRT-07_05_2022-GO95HV-1^668005/00 1/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
652021908-17269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 1/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
76571108-13469-DTLTRT-07_06_2022-GO95HV-1^668005/00 1/037 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
862652364-8469-DTLTRT-07_20_2022-GO95HV-1^668005/00 1/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
660862736-25319-ADMIN-11_30_2017-POLEDERP-1^668005/00 1/066 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
704942093-73309-DTLTRT-11_07_2022-GO95HV-1^668001/00 17/030 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2027-11-07 | 3
723775003-24309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 18/030 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
136829511-53880-DTLTRT-10_24_2022-GO95HV-1^668001/00 19/023 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2027-10-24 | 3
653682981-52209-DTLTRT-10_26_2022-GO95MLD-1^668001/00 19/028 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
392163998-80599-DETAIL-11_15_2022-GUYHINS-1^668001/00 19/045 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-15 | 2025-11-15 | 2
371124223-75309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 2/031 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
14928168-67843-DTLTRT-11_07_2022-GO95MLD-1^668001/00 2/032 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
14928168-67843-DTLTRT-11_07_2022-GUYSLACK-1^668001/00 2/032 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
13004688-64519-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/072 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
440679059-59919-ADMIN-07_27_2021-INSULDMG-1^668005/00 1/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
974713941-87219-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
725614684-68519-DTLTRT-08_17_2022-UBPBXARM-1^668005/00 1/095 | CROSSARM | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
785277398-13959-DTLTRT-06_30_2022-ABNDEQPM-1^668005/00 10/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
523657688-80369-DTLTRT-07_05_2022-GO95HV-1^668005/00 10/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
120774096-86119-ADMIN-11_30_2017-POLEDERP-1^668005/00 10/062 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
14928168-67843-ADMIN-12_22_2022-GUYSLACK-1^668001/00 2/032 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-22 | 2025-12-22 | 2
958988999-27673-DTLTRT-11_15_2022-GO95HV-1^668001/00 2/048 | OTHER | CA-TIER-2 | Transmission | 2022-11-15 | 2027-11-15 | 3
494050629-43573-DTLTRT-11_17_2022-GO95HV-1^668001/00 20/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
983037808-86563-DTLTRT-11_17_2022-GO95HV-1^668001/00 22/045 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
502045270-97369-DTLTRT-10_24_2022-GO95BLTC-1^668001/00 24/022 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2027-10-24 | 3
502045270-97369-DTLTRT-10_24_2022-GO95MLD-1^668001/00 24/022 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
502045270-97369-DTLTRT-10_24_2022-GUYHINS-2^668001/00 24/022 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
502045270-97369-DTLTRT-10_24_2022-GUYHINS-4^668001/00 24/022 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
59347615-44619-DETAIL-08_11_2019-POLEDERP-1^668005/00 10/096 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
659406248-64719-DTLTRT-08_18_2022-GRDRODHI-1^668005/00 10/098 | OTHER | CA-NON-TIER | Transmission | 2022-08-18 | 2025-08-18 | 2
845417682-71369-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 10A/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
213774098-82069-DTLTRT-06_30_2022-GO95MLD-1^668005/00 11/031 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
253329148-45159-ADMIN-08_05_2020-ABNDEQPM-1^668005/00 11/036 | OTHER | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
234989578-7469-DTLTRT-07_06_2022-GO95HV-1^668005/00 11/037 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
965850161-66469-DTLTRT-07_20_2022-GO95HV-1^668005/00 11/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
588082218-27519-DETAIL-08_01_2022-GO95HV-1^668005/00 11/072 | OTHER | CA-NON-TIER | Transmission | 2022-08-01 | 2027-08-01 | 3
184719579-25819-ADMIN-05_15_2021-TRETRCLR-1^668005/00 11/077 | OTHER | CA-NON-TIER | Transmission | 2021-05-15 | 2024-05-15 | 2
184719579-25819-ADMIN-05_24_2021-INSULDMG-1^668005/00 11/077 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
262546251-11119-ADMIN-08_05_2020-POLEDERP-1^668005/00 11/082 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
73253903-33519-ADMIN-06_15_2021-INSULDMG-1^668005/00 11/093 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
846877540-41159-DTLTRT-07_05_2022-GO95MLD-1^668005/00 12/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
502045270-97369-DETAIL-12_19_2022-GUYHINS-1^668001/00 24/022 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-19 | 2025-12-19 | 2
502045270-97369-DETAIL-12_19_2022-GUYHINS-2^668001/00 24/022 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-19 | 2025-12-19 | 2
716419200-78469-DETAIL-12_19_2022-ANCHIDLE-1^668001/00 25/022 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-19 | 2025-12-19 | 2
716419200-78469-DETAIL-12_19_2022-GRDRODHI-1^668001/00 25/022 | OTHER | CA-NON-TIER | Transmission | 2022-12-19 | 2025-12-19 | 2
385701375-71375-DTLTRT-11_17_2022-GUYHINS-1^668001/00 3X/049 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
385701375-71375-DTLTRT-11_17_2022-GUYHINS-2^668001/00 3X/049 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
385701375-71375-DTLTRT-11_17_2022-GUYHINS-3^668001/00 3X/049 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
385701375-71375-DTLTRT-11_17_2022-GUYHINS-4^668001/00 3X/049 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
726059743-56309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 4/031 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
31872591-10609-DTLTRT-11_07_2022-GO95BLTC-1^668001/00 5/032 | OTHER | CA-NON-TIER | Transmission | 2022-11-07 | 2027-11-07 | 3
762850524-5679-DTLTRT-11_14_2022-GO95HV-1^668001/00 5/042 | OTHER | CA-TIER-2 | Transmission | 2022-11-14 | 2027-11-14 | 3
641740458-40163-DTLTRT-11_17_2022-GO95HV-1^668001/00 5/046 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
876843441-10999-DTLTRT-10_27_2022-GO95MLD-1^668001/00 7/029 | OTHER | CA-NON-TIER | Transmission | 2022-10-27 | 2025-10-27 | 2
238217911-20970-DTLTRT-10_24_2022-GUYHINS-1^668001/00 8/023 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
238217911-20970-DTLTRT-10_24_2022-GUYHINS-2^668001/00 8/023 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
340786221-26580-DTLTRT-10_24_2022-GO95MLD-1^668001/00 9/023 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
340786221-26580-DTLTRT-10_24_2022-UBPBCTGD-1^668001/00 9/023 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
481961610-76273-DTLTRT-11_17_2022-GO95HV-1^668001/00 9A/048 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
551606264-83983-DTLTRT-11_17_2022-GO95MLD-1^668001/06 1/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
798651231-35369-DRONE_HY-09_19_2023-COPLLEAN-1^668002/00 1/004 | POLE | CA-NON-TIER | Transmission | 2023-09-19 | 2026-09-19 | 2
741603209-36469-DETAIL-02_15_2023-GO95BLTC-1^668002/00 10/014 | OTHER | CA-NON-TIER | Transmission | 2023-02-15 | 2028-02-15 | 3
779315401-41469-DETAIL-02_23_2023-GO95HV-1^668002/00 10/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
792908434-35969-DETAIL-03_08_2023-GO95HV-1^668002/00 10/034 | OTHER | CA-TIER-2 | Transmission | 2023-03-08 | 2028-03-08 | 3
774700925-76950-DRONE_HY-09_16_2023-UGEQRUST-1^668002/00 10/058 | TRANSFORMER | CA-TIER-2 | Transmission | 2023-09-16 | 2028-09-16 | 3
526912313-53519-DTLTRT-08_17_2022-POLETOP-1^668005/00 12/093 | POLE | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
867576958-78859-DTLTRT-06_30_2022-GO95MLD-1^668005/00 13/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
241092944-21619-DTLTRT-08_17_2022-GO95HV-1^668005/00 13/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2027-08-17 | 3
589250919-77691-ADMIN-12_21_2022-GUYSLACK-1^668005/00 13A/028 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
639221478-869-DTLTRT-06_30_2022-GO95MLD-1^668005/00 14/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
642588399-89169-ADMIN-12_21_2022-GO95MLD-1^668005/00 14/033 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
391808933-4519-ADMIN-05_20_2021-POLETOP-1^668005/00 14/093 | POLE | CA-NON-TIER | Transmission | 2021-05-20 | 2024-05-20 | 2
506152954-87519-ADMIN-11_18_2022-POLEDERP-1^668005/00 14/094 | POLE | CA-NON-TIER | Transmission | 2022-11-18 | 2025-11-18 | 2
231392499-40269-DTLTRT-07_05_2022-GO95HV-1^668005/00 15/033 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
231392499-40269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 15/033 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
248144023-15419-DTLTRT-08_16_2022-GO95HV-1^668005/00 15/091 | OTHER | CA-NON-TIER | Transmission | 2022-08-16 | 2027-08-16 | 3
248144023-15419-DTLTRT-08_16_2022-GO95MLD-1^668005/00 15/091 | OTHER | CA-NON-TIER | Transmission | 2022-08-16 | 2025-08-16 | 2
248144023-15419-DTLTRT-08_16_2022-GRDRODHI-1^668005/00 15/091 | OTHER | CA-NON-TIER | Transmission | 2022-08-16 | 2025-08-16 | 2
85379488-49520-DTLTRT-06_28_2022-GO95MLD-1^668005/00 16/027 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
398159588-62169-DTLTRT-06_30_2022-GO95HV-1^668005/00 16/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
712251775-26619-ADMIN-07_27_2021-INSULDMG-1^668005/00 16/096 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
396876381-5469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 11/006 | CROSSARM | CA-NON-TIER | Transmission | 2023-09-12 | 2028-09-12 | 3
503703429-18769-DRONE_HY-09_14_2023-GO95HV-1^668002/00 13/014 | OTHER | CA-NON-TIER | Transmission | 2023-09-14 | 2028-09-14 | 3
601772693-80269-DETAIL-06_20_2023-GUYNOINS-1^668002/00 13/045 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-06-20 | 2026-06-20 | 2
945072849-96069-DRONE_HY-09_14_2023-GO95HV-1^668002/00 14/042 | OTHER | CA-TIER-2 | Transmission | 2023-09-14 | 2028-09-14 | 3
174466439-98769-ADMIN-08_03_2023-INSULDMG-1^668002/00 14/049 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-08-03 | 2024-08-03 | 2
879822212-16469-DRONE_HY-09_12_2023-POLETOP-1^668002/00 15/006 | POLE | CA-NON-TIER | Transmission | 2023-09-12 | 2028-09-12 | 3
118321139-58769-DETAIL-02_15_2023-GO95HV-1^668002/00 15/014 | OTHER | CA-NON-TIER | Transmission | 2023-02-15 | 2028-02-15 | 3
79489183-74969-DETAIL-02_08_2023-GO95HV-1^668002/00 15/018 | OTHER | CA-NON-TIER | Transmission | 2023-02-08 | 2028-02-08 | 3
404293295-66619-ADMIN-06_15_2021-INSULDMG-1^668005/00 18/096 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
920488276-91719-ADMIN-07_29_2021-INSULDMG-1^668005/00 18/097 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-29 | 2024-07-29 | 2
252204106-96619-ADMIN-06_15_2021-INSULDMG-1^668005/00 19/096 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
448704470-43069-DTLTRT-07_15_2022-GO95HV-1^668005/00 2/047 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
885396288-80619-ADMIN-10_08_2020-POLEDERP-1^668005/00 2/074 | POLE | CA-NON-TIER | Transmission | 2020-10-08 | 2023-10-08 | 2
8781459-31719-ADMIN-05_24_2021-INSULDMG-1^668005/00 2/076 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
580752329-12669-DRONE_HY-09_14_2023-GO95HV-1^668002/00 15/039 | OTHER | CA-TIER-2 | Transmission | 2023-09-14 | 2028-09-14 | 3
639235893-98769-DRONE_HY-09_20_2023-GO95HV-1^668002/00 15/063 | OTHER | CA-TIER-3 | Transmission | 2023-09-20 | 2028-09-20 | 3
849562902-28969-DETAIL-03_08_2023-TRNSNUTS-1^668002/00 16/031 | CONNECTION DEVICE | CA-TIER-2 | Transmission | 2023-03-08 | 2024-03-08 | 2
324825542-39869-DRONE_HY-09_19_2023-GO95HV-1^668002/00 16/071 | OTHER | CA-TIER-2 | Transmission | 2023-09-19 | 2028-09-19 | 3
324825542-39869-DRONE_HY-09_19_2023-XARMBRAC-1^668002/00 16/071 | CROSSARM | CA-TIER-2 | Transmission | 2023-09-19 | 2028-09-19 | 3
247828349-29769-DETAIL-02_15_2023-GO95HV-1^668002/00 17/014 | OTHER | CA-NON-TIER | Transmission | 2023-02-15 | 2028-02-15 | 3
154317471-83469-DRONE_HY-09_20_2023-GO95HV-1^668002/00 17/070 | OTHER | CA-TIER-2 | Transmission | 2023-09-20 | 2028-09-20 | 3
964754271-97369-DETAIL-03_09_2023-GO95HV-1^668002/00 18/004 | OTHER | CA-NON-TIER | Transmission | 2023-03-09 | 2028-03-09 | 3
619183079-47291-DRONE_HY-09_14_2023-GO95HV-1^668002/00 18/024 | OTHER | CA-NON-TIER | Transmission | 2023-09-14 | 2028-09-14 | 3
678569170-12269-DRONE_HY-09_11_2023-INSULDMG-1^668002/00 18/025 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-09-11 | 2026-09-11 | 2
793208429-61630-DRONE_HY-09_13_2023-GO95HV-1^668002/00 18/060 | OTHER | CA-TIER-2 | Transmission | 2023-09-13 | 2028-09-13 | 3
100751181-58369-DETAIL-03_09_2023-GO95HV-1^668002/00 19/004 | OTHER | CA-NON-TIER | Transmission | 2023-03-09 | 2028-03-09 | 3
586334494-44269-DETAIL-05_26_2022-GO95HV-1^668002/00 2/001 | OTHER | CA-TIER-3 | Transmission | 2022-05-26 | 2027-05-26 | 3
864521598-12079-DRONE_HY-09_22_2023-GO95HV-1^668002/00 2/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-22 | 2028-09-22 | 3
321913391-83179-DETAIL-05_09_2022-GO95HV-1^668002/00 20/050 | OTHER | CA-TIER-2 | Transmission | 2022-05-09 | 2027-05-09 | 3
823874069-80379-DRONE_HY-09_16_2023-GO95HV-1^668002/00 20/060 | OTHER | CA-TIER-2 | Transmission | 2023-09-16 | 2028-09-16 | 3
159863568-36079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 21/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
19372158-55169-DRONE_HY-09_11_2023-INSULDMG-1^668002/00 22/023 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-09-11 | 2028-09-11 | 3
754234178-56079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 22/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
206576059-24479-DRONE_HY-09_13_2023-GO95HV-1^668002/00 3/078 | OTHER | CA-TIER-2 | Transmission | 2023-09-13 | 2028-09-13 | 3
759370921-77869-DRONE_HY-09_03_2023-XARMSPCR-1^668002/00 4/017 | CROSSARM | CA-NON-TIER | Transmission | 2023-09-03 | 2026-09-03 | 2
504335064-14969-DETAIL-03_08_2023-GO95HV-1^668002/00 4/034 | OTHER | CA-TIER-2 | Transmission | 2023-03-08 | 2028-03-08 | 3
109884463-90869-DRONE_HY-09_20_2023-XARMBRAC-1^668002/00 4/064 | CROSSARM | CA-TIER-2 | Transmission | 2023-09-20 | 2024-09-20 | 2
814187078-12169-DETAIL-03_09_2023-GO95HV-1^668002/00 5/023 | OTHER | CA-NON-TIER | Transmission | 2023-03-09 | 2028-03-09 | 3
330611974-25469-DETAIL-03_08_2023-UBPRMSHD-1^668002/00 5/034 | CONNECTION DEVICE | CA-TIER-2 | Transmission | 2023-03-08 | 2024-03-08 | 2
671267829-31130-DRONE_HY-09_25_2023-GO95HV-1^668002/00 5/060 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2028-09-25 | 3
114448991-70469-DETAIL-02_23_2023-GO95HV-1^668002/00 7/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
899823993-98469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 8/007 | CROSSARM | CA-NON-TIER | Transmission | 2023-09-12 | 2026-09-12 | 2
386929498-93769-DRONE_HY-09_11_2023-INSULDMG-1^668002/00 8/013 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-09-11 | 2028-09-11 | 3
272561601-90469-DETAIL-02_23_2023-GO95HV-1^668002/00 8/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
535834089-93819-ADMIN-05_24_2021-INSULDMG-1^668005/00 2/077 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
33473365-82619-DTLTRT-08_17_2022-GO95HV-1^668005/00 2/096 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2027-08-17 | 3
763514979-81269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 20/033 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
646164629-83959-DTLTRT-06_30_2022-GO95HV-1^668005/00 21/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
646164629-83959-DTLTRT-06_30_2022-GO95MLD-1^668005/00 21/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
43656915-52269-DTLTRT-07_05_2022-GO95HV-1^668005/00 3/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
966001668-56369-DTLTRT-07_06_2022-GO95MLD-1^668005/00 3/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
496480979-47769-DETAIL-02_15_2023-GRDRODHI-1^668002/00 9/014 | OTHER | CA-NON-TIER | Transmission | 2023-02-15 | 2028-02-15 | 3
933644503-77969-DETAIL-02_08_2023-INSULDMG-1^668002/00 9/019 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-02-08 | 2026-02-08 | 2
433449734-53030-DETAIL-04_13_2023-GUYNOINS-1^668002/00 9A/058 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-04-13 | 2026-04-13 | 2
958231879-16330-DETAIL-05_03_2023-GUYNOINS-1^668002/01 11/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-05-03 | 2026-05-03 | 2
237045863-11470-DETAIL-01_31_2023-GO95HV-1^668002/07 16/001 | OTHER | CA-TIER-2 | Transmission | 2023-01-31 | 2028-01-31 | 3
734226600-26070-DTLTRT-11_16_2022-GO95HV-1^668003/00 10X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-4^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
782567918-83469-DTLTRT-07_06_2022-GO95HV-1^668005/00 3/037 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
438056618-32769-DTLTRT-07_07_2022-UBPBXARM-1^668005/00 3/041 | CROSSARM | CA-NON-TIER | Transmission | 2022-07-07 | 2025-07-07 | 2
19138340-7269-ADMIN-08_05_2020-POLEDERP-1^668005/00 3/051 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
597167674-68469-DTLTRT-07_20_2022-GO95HV-1^668005/00 3/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
728706-38119-ADMIN-11_30_2017-POLEDERP-1^668005/00 3/063 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
77149886-69419-DTLTRT-07_27_2022-POLETOP-1^668005/00 3/070 | POLE | CA-NON-TIER | Transmission | 2022-07-27 | 2025-07-27 | 2
677378269-71719-DETAIL-07_28_2022-GO95MLD-1^668005/00 3/076 | OTHER | CA-NON-TIER | Transmission | 2022-07-28 | 2025-07-28 | 2
740023151-28219-ADMIN-12_31_2018-POLEREPL-1^668005/00 3/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
374973143-26419-ADMIN-06_15_2021-INSULDMG-1^668005/00 3/092 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
64429563-88919-DETAIL-08_17_2022-GO95MLD-1^668005/00 3/094 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
847333024-29519-ADMIN-07_27_2021-INSULDMG-1^668005/00 3/095 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
238393216-18619-ADMIN-07_27_2021-INSULDMG-1^668005/00 3/097 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
549869080-70180-DTLTRT-06_27_2022-GO95HV-1^668005/00 3A/025 | OTHER | CA-NON-TIER | Transmission | 2022-06-27 | 2027-06-27 | 3
341937059-68059-DETAIL-06_28_2022-GO95MLD-1^668005/00 3X/026 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
263829048-29069-DTLTRT-06_30_2022-GO95HV-1^668005/00 4/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
437364738-18269-DTLTRT-07_05_2022-GO95HV-1^668005/00 4/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
437364738-18269-AUDIT-08_02_2022-GUYNOINS-1^668005/00 4/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-02 | 2025-08-02 | 2
437364738-18269-AUDIT-08_02_2022-GUYSLACK-1^668005/00 4/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-02 | 2025-08-02 | 2
417526801-67271-DETAIL-07_06_2022-GO95HV-1^668005/00 4/038 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
417526801-67271-AUDIT-08_02_2022-SVCROAD-1^668005/00 4/038 | OTHER | CA-NON-TIER | Transmission | 2022-08-02 | 2025-08-02 | 2
417526801-67271-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 4/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
617777094-98469-DTLTRT-07_20_2022-GO95HV-1^668005/00 4/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
839794095-36669-ADMIN-05_24_2021-INSULDMG-1^668005/00 4/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
804928046-16319-ADMIN-11_30_2017-POLEDERP-1^668005/00 4/066 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
595340756-76419-ADMIN-11_30_2017-POLEDERP-1^668005/00 4/069 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-6^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
821395310-47070-DTLTRT-11_16_2022-GO95HV-1^668003/00 11X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
53985910-70170-DTLTRT-11_16_2022-GO95HV-1^668003/00 13X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
246900900-91370-DTLTRT-11_16_2022-GO95HV-1^668003/00 15X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
416873980-44679-DTLTRT-11_16_2022-GO95MLD-1^668003/00 2X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
313275390-31340-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 3X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
681183470-670-DTLTRT-11_16_2022-GO95HV-1^668003/00 3X/002 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
849646190-37970-DTLTRT-11_16_2022-GO95HV-1^668003/00 4X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
589421180-91340-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 4X/002 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
946257990-98040-DTLTRT-11_16_2022-GO95HV-1^668003/00 5X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
222354480-93670-DTLTRT-11_16_2022-GO95HV-1^668003/00 5X/002 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
909400590-32070-DTLTRT-11_16_2022-GO95HV-1^668003/00 6X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
878242880-84670-DTLTRT-11_16_2022-GO95HV-1^668003/00 6X/002 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
318923400-34070-DTLTRT-11_16_2022-GO95HV-1^668003/00 8X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
107921900-15070-DTLTRT-11_16_2022-GO95HV-1^668003/00 9X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
177999036-45459-ADMIN-09_26_2022-UBPBXARM-1^668004/00 1/025 | CROSSARM | CA-NON-TIER | Transmission | 2022-09-26 | 2025-09-26 | 2
305066329-57159-ADMIN-07_24_2020-POLEDERP-1^668004/00 10/024 | POLE | CA-NON-TIER | Transmission | 2020-07-24 | 2023-07-24 | 2
125204743-5598-ADMIN-07_24_2020-POLEDERP-1^668004/00 4/025 | POLE | CA-NON-TIER | Transmission | 2020-07-24 | 2023-07-24 | 2
715148266-52759-ADMIN-03_31_2022-INSULDMG-1^668004/00 6/017 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-03-31 | 2025-03-31 | 2
652021908-17269-DTLTRT-07_05_2022-GO95BLTC-1^668005/00 1/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
729363448-80569-DTLTRT-07_06_2022-GO95MLD-1^668005/00 1/038 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
841253960-3069-AUDIT-08_29_2022-GO95HV-1^668005/00 1/047 | OTHER | CA-NON-TIER | Transmission | 2022-08-29 | 2027-08-29 | 3
26088180-15169-DTLTRT-07_18_2022-GO95HV-1^668005/00 1/049 | OTHER | CA-NON-TIER | Transmission | 2022-07-18 | 2027-07-18 | 3
7883440-3019-ADMIN-05_24_2021-INSULDMG-1^668005/00 4/080 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
574770541-5219-DETAIL-08_15_2022-GO95HV-1^668005/00 4/086 | OTHER | CA-NON-TIER | Transmission | 2022-08-15 | 2027-08-15 | 3
782174153-56419-DTLTRT-08_16_2022-POLETOP-1^668005/00 4/092 | POLE | CA-NON-TIER | Transmission | 2022-08-16 | 2025-08-16 | 2
943079326-48619-DETAIL-08_11_2019-POLEDERP-1^668005/00 4/097 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
653353338-85969-DTLTRT-06_28_2022-ENCHRW-1^668005/00 5/027 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
653353338-85969-DTLTRT-06_28_2022-XARMBRAC-1^668005/00 5/027 | CROSSARM | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
101004320-64069-DETAIL-07_15_2022-GO95HV-1^668005/00 5/047 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
646545995-86669-ADMIN-07_30_2021-INSULDMG-2^668005/00 5/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-30 | 2024-07-30 | 2
846967306-90769-ADMIN-07_30_2021-INSULDMG-1^668005/00 5/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-30 | 2024-07-30 | 2
943129906-25769-ADMIN-05_24_2021-INSULDMG-1^668005/00 5/061 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
353226146-56319-ADMIN-11_30_2017-POLEDERP-1^668005/00 5/066 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
758640858-63519-ADMIN-12_31_2018-POLEDERP-1^668005/00 5/071 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
892532726-77769-DETAIL-07_25_2022-GO95HV-1^668005/00 1/062 | OTHER | CA-NON-TIER | Transmission | 2022-07-25 | 2027-07-25 | 3
320165151-75019-ADMIN-07_27_2021-INSULDMG-1^668005/00 1/081 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
8645721-73219-DTLTRT-08_15_2022-GUYSLACK-1^668005/00 1/086 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-15 | 2025-08-15 | 2
969697962-31319-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/088 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
751232583-99419-ADMIN-06_15_2021-INSULDMG-1^668005/00 1/093 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
725614684-68519-ADMIN-07_27_2021-INSULDMG-1^668005/00 1/095 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
725614684-68519-DTLTRT-08_17_2022-GO95MLD-1^668005/00 1/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
978875306-37619-ADMIN-06_15_2021-INSULDMG-1^668005/00 1/097 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
521644820-5269-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 10/034 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
373724260-75369-ADMIN-08_05_2020-POLEDERP-1^668005/00 10/052 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
555923951-46469-DTLTRT-07_20_2022-GO95HV-1^668005/00 10/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
623039326-47769-ADMIN-05_24_2021-INSULDMG-1^668005/00 10/061 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
684804121-84119-ADMIN-05_24_2021-INSULDMG-1^668005/00 10/083 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
659406248-64719-DTLTRT-08_18_2022-GO95MLD-1^668005/00 10/098 | OTHER | CA-NON-TIER | Transmission | 2022-08-18 | 2025-08-18 | 2
76329608-29769-ADMIN-12_21_2022-GUYHINS-1^668005/00 11/032 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
115306559-68169-ADMIN-12_21_2022-GO95HV-1^668005/00 11/033 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2027-12-21 | 3
316473631-15119-ADMIN-07_27_2021-INSULDMG-1^668005/00 11/083 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
22509001-47219-ADMIN-12_31_2018-POLEREPL-1^668005/00 11/086 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
22509001-47219-DTLTRT-08_15_2022-POLETOP-1^668005/00 11/086 | POLE | CA-NON-TIER | Transmission | 2022-08-15 | 2025-08-15 | 2
960731252-80319-ADMIN-12_27_2018-POLEREPL-1^668005/00 11/087 | POLE | CA-NON-TIER | Transmission | 2018-12-27 | 2023-11-27 | 2
194601591-37119-ADMIN-08_05_2020-POLEDERP-1^668005/00 5/084 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
387931973-76419-ADMIN-06_15_2021-INSULDMG-1^668005/00 5/092 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
213760735-33619-DTLTRT-08_17_2022-GO95HV-1^668005/00 5/096 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2027-08-17 | 3
521568568-61169-AUDIT-08_02_2022-XARMBRAC-1^668005/00 6/032 | CROSSARM | CA-NON-TIER | Transmission | 2022-08-02 | 2025-08-02 | 2
257440269-83269-DTLTRT-07_05_2022-GO95HV-1^668005/00 6/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
257440269-83269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 6/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
895067204-59469-DTLTRT-07_20_2022-GO95HV-1^668005/00 6/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
16979116-21769-ADMIN-05_24_2021-INSULDMG-1^668005/00 6/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
719570266-17419-ADMIN-11_30_2017-POLEDERP-1^668005/00 6/069 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
889472999-60019-ADMIN-06_15_2021-INSULDMG-1^668005/00 6/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
317226001-77119-ADMIN-08_05_2020-POLEDERP-1^668005/00 6/084 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
317226001-77119-DTLTRT-08_04_2022-GUYHINS-1^668005/00 6/084 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-04 | 2025-08-04 | 2
707259392-43319-ADMIN-06_15_2021-INSULDMG-1^668005/00 6/088 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
624826183-7419-DTLTRT-08_16_2022-POLETOP-1^668005/00 6/092 | POLE | CA-NON-TIER | Transmission | 2022-08-16 | 2025-08-16 | 2
75679945-73619-ADMIN-07_27_2021-INSULDMG-1^668005/00 6/096 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
967460597-43719-ADMIN-07_29_2021-INSULDMG-1^668005/00 6/098 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-29 | 2024-07-29 | 2
967460597-43719-DTLTRT-08_18_2022-GO95HV-1^668005/00 6/098 | OTHER | CA-NON-TIER | Transmission | 2022-08-18 | 2027-08-18 | 3
846356618-15959-DTLTRT-07_06_2022-GRDRODHI-1^668005/00 7/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
504487824-7519-ADMIN-11_18_2022-POLEDERP-1^668005/00 11/094 | POLE | CA-NON-TIER | Transmission | 2022-11-18 | 2025-11-18 | 2
694839435-10919-DTLTRT-08_18_2022-GO95HV-1^668005/00 11/096 | OTHER | CA-NON-TIER | Transmission | 2022-08-18 | 2027-08-18 | 3
818495418-69769-DTLTRT-06_30_2022-GO95MLD-1^668005/00 12/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
846877540-41159-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 12/034 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
239570371-37469-DTLTRT-07_20_2022-GO95HV-1^668005/00 12/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
992882179-56819-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 12/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-03 | 2025-08-03 | 2
903423561-61119-DTLTRT-08_04_2022-GUYHINS-1^668005/00 12/082 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-04 | 2025-08-04 | 2
903423561-61119-DTLTRT-08_04_2022-GUYSLACK-1^668005/00 12/082 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-04 | 2025-08-04 | 2
164764341-45119-ADMIN-08_05_2020-POLEDERP-1^668005/00 12/083 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
964146508-92369-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 13/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
641058373-54419-ADMIN-11_07_2022-POLEDERP-1^668005/00 13/091 | POLE | CA-NON-TIER | Transmission | 2022-11-07 | 2025-11-07 | 2
642588399-89169-ADMIN-12_21_2022-XARMBRAC-1^668005/00 14/033 | CROSSARM | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
1852273-79419-ENHANCED-07_21_2020-POLEDERP-1^668005/00 14/092 | POLE | CA-NON-TIER | Transmission | 2020-07-21 | 2023-07-21 | 2
391808933-4519-DTLTRT-08_17_2022-UBPBXARM-1^668005/00 14/093 | CROSSARM | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
254759124-41619-DTLTRT-08_17_2022-GO95HV-1^668005/00 14/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2027-08-17 | 3
335920711-25469-DTLTRT-07_20_2022-GO95HV-1^668005/00 7/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
884864916-59119-ADMIN-11_30_2017-POLEDERP-1^668005/00 7/063 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
702096556-17319-ADMIN-11_30_2017-POLEDERP-1^668005/00 7/066 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
334783196-10419-DTLTRT-07_26_2022-INSULDMG-1^668005/00 7/067 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-07-26 | 2025-07-26 | 2
899890468-4519-ADMIN-12_31_2018-POLEDERP-1^668005/00 7/071 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
280523978-2169-DTLTRT-06_30_2022-GO95MLD-1^668005/00 15/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
248144023-15419-ADMIN-06_15_2021-INSULDMG-1^668005/00 15/091 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
908430639-80269-DTLTRT-07_05_2022-GO95HV-1^668005/00 16/033 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
230274649-30719-ADMIN-06_24_2021-POLEDERP-1^668005/00 16/075 | POLE | CA-NON-TIER | Transmission | 2021-06-24 | 2024-06-24 | 2
6952356-58819-DETAIL-08_18_2022-GO95CL10-1^668005/00 16/097 | OTHER | CA-NON-TIER | Transmission | 2022-08-18 | 2025-08-18 | 2
629769885-46619-ADMIN-06_15_2021-INSULDMG-1^668005/00 17/096 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
800616191-62219-ADMIN-06_15_2021-INSULDMG-1^668005/00 7/085 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
282887671-95219-ADMIN-06_15_2021-INSULDMG-1^668005/00 7/086 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
521231512-69219-ADMIN-06_15_2021-INSULDMG-1^668005/00 7/087 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
521231512-69219-DTLTRT-08_15_2022-GO95HV-1^668005/00 7/087 | OTHER | CA-NON-TIER | Transmission | 2022-08-15 | 2027-08-15 | 3
676703974-10619-DTLTRT-08_17_2022-UBPBCTGD-1^668005/00 7/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
612042055-71919-DTLTRT-08_17_2022-GO95HV-1^668005/00 7/096 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2027-08-17 | 3
984474435-32619-ADMIN-07_27_2021-INSULDMG-1^668005/00 18/095 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
341532538-48069-DETAIL-06_30_2022-GO95HV-1^668005/00 2/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
351659886-59669-ADMIN-05_24_2021-INSULDMG-1^668005/00 2/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
17731646-8769-ADMIN-07_30_2021-INSULDMG-1^668005/00 2/062 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-30 | 2024-07-30 | 2
74321076-78319-ADMIN-11_30_2017-POLEDERP-1^668005/00 2/067 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
182791969-12969-DETAIL-08_02_2022-GO95HV-1^668005/00 7X/077 | OTHER | CA-NON-TIER | Transmission | 2022-08-02 | 2027-08-02 | 3
136337600-76159-DTLTRT-07_05_2022-GO95HV-1^668005/00 8/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
834339328-58369-DTLTRT-07_06_2022-GO95HV-1^668005/00 8/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
650948587-21519-ADMIN-11_30_2017-POLEDERP-1^668005/00 8/070 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
650948587-21519-DTLTRT-07_27_2022-POLETOP-1^668005/00 8/070 | POLE | CA-NON-TIER | Transmission | 2022-07-27 | 2025-07-27 | 2
340260784-55719-DTLTRT-08_17_2022-GO95MLD-1^668005/00 8/094 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
561581869-89919-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 2/079 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-03 | 2025-08-03 | 2
793797551-67219-ADMIN-12_31_2018-POLEREPL-1^668005/00 2/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
99559872-61319-ADMIN-12_31_2018-POLEREPL-1^668005/00 2/088 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
508676516-77619-ADMIN-07_27_2021-INSULDMG-1^668005/00 2/097 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
646164629-83959-DTLTRT-06_30_2022-GO95BLTC-1^668005/00 21/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
427015438-5969-DETAIL-06_28_2022-GO95MLD-1^668005/00 3/026 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
370510318-63719-DTLTRT-08_18_2022-GO95HV-1^668005/00 8/098 | OTHER | CA-NON-TIER | Transmission | 2022-08-18 | 2027-08-18 | 3
164101020-54269-DTLTRT-07_05_2022-GO95HV-1^668005/00 9/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
205465429-70919-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 9/078 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-03 | 2025-08-03 | 2
464531090-11019-DETAIL-12_31_2018-POLEREPL-1^668005/00 9/079 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
392890933-419-DTLTRT-08_16_2022-GO95HV-1^668005/00 9/090 | OTHER | CA-NON-TIER | Transmission | 2022-08-16 | 2027-08-16 | 3
416147894-50619-DETAIL-08_17_2022-GO95HV-1^668005/00 9/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2027-08-17 | 3
620579949-16769-ADMIN-06_15_2021-POLEDERP-1^668005/03 10/004 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
64094449-3869-ADMIN-06_15_2021-POLEDERP-1^668005/03 10/005 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
140309459-86769-DTLTRT-10_10_2022-POLEDERP-1^668005/03 12/004 | POLE | CA-NON-TIER | Transmission | 2022-10-10 | 2025-10-10 | 2
745274169-67769-ADMIN-04_16_2019-POLEREPL-1^668005/03 14/004 | POLE | CA-NON-TIER | Transmission | 2019-04-16 | 2024-03-16 | 2
768286448-86069-ADMIN-06_15_2021-POLEDERP-1^668005/03 18/002 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
793578783-83898-ADMIN-06_15_2021-POLEDERP-1^668005/03 18/003 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
541312289-72769-ADMIN-08_11_2019-POLEDERP-1^668005/03 3/004 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
541312289-72769-DTLTRT-10_11_2022-GO95HV-1^668005/03 3/004 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
74234608-37669-DTLTRT-10_11_2022-GO95MLD-1^668005/03 4/003 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2025-10-11 | 2
403472409-23769-ADMIN-08_11_2019-POLEDERP-1^668005/03 4/004 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
638418219-63769-ADMIN-02_07_2022-POLEDERP-1^668005/03 5/004 | POLE | CA-NON-TIER | Transmission | 2022-02-07 | 2025-02-07 | 2
58139215-71869-DTLTRT-10_10_2022-GO95HV-1^668005/03 7/005 | OTHER | CA-NON-TIER | Transmission | 2022-10-10 | 2027-10-10 | 3
247872599-25769-ADMIN-02_07_2022-POLEDERP-1^668005/03 8/004 | POLE | CA-NON-TIER | Transmission | 2022-02-07 | 2025-02-07 | 2
966639568-63259-DTLTRT-10_11_2022-GO95HV-1^668005/03 9/003 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
511000839-75769-DTLTRT-10_10_2022-GO95HV-1^668005/03 9/004 | OTHER | CA-NON-TIER | Transmission | 2022-10-10 | 2027-10-10 | 3
730281043-3243-DETAIL-10_12_2022-GO95HV-1^668005/08 8X5/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
159437443-25643-DETAIL-10_12_2022-GUYHINS-1^668005/08 8X7/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
159437443-25643-DETAIL-10_12_2022-GUYHINS-3^668005/08 8X7/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
159437443-25643-DETAIL-10_12_2022-GUYHINS-4^668005/08 8X7/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
520575753-22953-DETAIL-10_12_2022-GUYHINS-1^668005/08 8X8/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
14568933-86280-DTLTRT-09_25_2023-GO95HV-1^668010/00 1/004 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2028-09-25 | 3
605354734-60180-DTLTRT-09_27_2023-GO95MLD-1^668010/00 1/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
450087538-68069-DTLTRT-06_30_2022-GO95MLD-1^668005/00 3/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
782567918-83469-DTLTRT-07_06_2022-GO95MLD-1^668005/00 3/037 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
580009365-76569-ADMIN-11_30_2017-POLEDERP-1^668005/00 3/057 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
18901286-79669-ADMIN-05_24_2021-INSULDMG-1^668005/00 3/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
728706-38119-DTLTRT-07_25_2022-POLETOP-1^668005/00 3/063 | POLE | CA-NON-TIER | Transmission | 2022-07-25 | 2025-07-25 | 2
77149886-69419-ADMIN-11_30_2017-POLEDERP-1^668005/00 3/070 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
260256969-10019-DTLTRT-08_03_2022-GO95HV-1^668005/00 3/079 | OTHER | CA-NON-TIER | Transmission | 2022-08-03 | 2027-08-03 | 3
321481731-84219-ADMIN-06_15_2021-INSULDMG-1^668005/00 3/086 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
847333024-29519-DTLTRT-08_17_2022-GO95HV-1^668005/00 3/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2027-08-17 | 3
91669975-27819-DTLTRT-08_17_2022-GO95MLD-1^668005/00 3/096 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
666175239-67239-DETAIL-08_17_2022-GO95MLD-1^668005/00 3X/094 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
455743818-68969-DTLTRT-06_30_2022-GO95MLD-1^668005/00 4/031 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
928015420-14069-DTLTRT-07_15_2022-GO95HV-1^668005/00 4/047 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
775078606-40769-ADMIN-05_24_2021-INSULDMG-1^668005/00 4/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
587682099-47819-ADMIN-06_24_2021-INSULDMG-1^668005/00 4/078 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-24 | 2024-06-24 | 2
293723679-30019-ADMIN-05_24_2021-INSULDMG-1^668005/00 4/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
806127861-86019-ADMIN-07_27_2021-INSULDMG-1^668005/00 4/081 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
653353338-85969-DTLTRT-06_28_2022-GO95HV-1^668005/00 5/027 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2027-06-28 | 3
653353338-85969-DTLTRT-06_28_2022-GO95MLD-1^668005/00 5/027 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
56437859-13269-DTLTRT-07_05_2022-GO95HV-1^668005/00 5/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
895162648-48269-DTLTRT-07_05_2022-GO95HV-1^668005/00 5/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
408785888-87369-DTLTRT-07_06_2022-GO95HV-1^668005/00 5/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
36089801-20911-ADMIN-07_04_2022-POLEDERP-1^668005/00 5/038 | POLE | CA-NON-TIER | Transmission | 2022-07-04 | 2025-07-04 | 2
36089801-20911-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 5/038 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
308345061-61030-DTLTRT-10_30_2023-GUYLOINS-1^668010/00 1/014 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-30 | 2026-10-30 | 2
60980975-24190-DTLTRT-10_31_2023-GO95HV-1^668010/00 1/017 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
849774085-21479-DTLTRT-11_01_2023-GO95HV-1^668010/00 1/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
138340549-35900-DTLTRT-10_26_2023-GUYLOINS-1^668010/00 1/023 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
138340549-35900-DTLTRT-10_26_2023-GUYLOINS-2^668010/00 1/023 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
399901221-61769-DTLTRT-10_05_2023-GO95MLD-1^668010/00 1/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
399901221-61769-DTLTRT-10_05_2023-SVCROAD-1^668010/00 1/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
394634371-66579-DTLTRT-10_04_2023-GO95MLD-1^668010/00 1/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
236888910-40169-DTLTRT-07_15_2022-GO95HV-1^668005/00 5/048 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
236888910-40169-DTLTRT-07_15_2022-UBPRMSHD-1^668005/00 5/048 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2022-07-15 | 2025-07-15 | 2
13599681-64469-DTLTRT-07_20_2022-GO95MLD-1^668005/00 5/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2025-07-20 | 2
824673794-29469-DTLTRT-07_20_2022-GO95HV-1^668005/00 5/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
579286256-36419-DETAIL-07_27_2022-GO95HV-1^668005/00 5/069 | OTHER | CA-NON-TIER | Transmission | 2022-07-27 | 2027-07-27 | 3
855689779-50019-ADMIN-06_15_2021-INSULDMG-1^668005/00 5/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
244256192-42319-ADMIN-06_15_2021-INSULDMG-1^668005/00 5/088 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
31737743-7540-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
558464254-8040-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
515655185-5769-DTLTRT-11_03_2023-GO95MLD-1^668010/00 1/037 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
415034995-56360-DTLTRT-10_09_2023-GUYHINS-1^668010/00 1/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
192745448-7169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 1/045 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
318662544-58469-DTLTRT-09_25_2023-GO95TCH-1^668010/00 10/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2026-09-25 | 2
74647123-44570-DTLTRT-09_26_2023-GO95HV-1^668010/00 10/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
708848154-59519-ADMIN-08_11_2019-POLEDERP-1^668005/00 5/095 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
829007598-8369-DETAIL-07_06_2022-GO95HV-1^668005/00 6/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
427584130-5069-DTLTRT-07_15_2022-GO95HV-1^668005/00 6/047 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
599146991-84469-AUDIT-08_29_2022-GO95HV-1^668005/00 6/054 | OTHER | CA-NON-TIER | Transmission | 2022-08-29 | 2027-08-29 | 3
90412435-3569-DTLTRT-07_20_2022-GO95HV-1^668005/00 6/056 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
126931225-42669-DTLTRT-07_21_2022-GUYSLACK-1^668005/00 6/058 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-07-21 | 2025-07-21 | 2
719570266-17419-DTLTRT-07_27_2022-POLETOP-1^668005/00 6/069 | POLE | CA-NON-TIER | Transmission | 2022-07-27 | 2025-07-27 | 2
230439944-61780-DTLTRT-09_27_2023-GO95MLD-1^668010/00 10/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
334687266-53479-DTLTRT-11_01_2023-GO95HV-1^668010/00 10/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
91726933-35779-DTLTRT-10_19_2023-GO95MLD-1^668010/00 10/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
582254773-17640-DTLTRT-10_04_2023-GO95MLD-1^668010/00 10/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
582254773-17640-DTLTRT-10_04_2023-INSULDMG-1^668010/00 10/029 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
576986961-88140-DTLTRT-10_03_2023-GO95HV-1^668010/00 10/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
297936813-5140-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 10/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
122497377-40519-ADMIN-11_30_2017-POLEDERP-1^668005/00 6/070 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
279641631-10119-DTLTRT-08_04_2022-GO95HV-1^668005/00 6/082 | OTHER | CA-NON-TIER | Transmission | 2022-08-04 | 2027-08-04 | 3
601530954-43119-ADMIN-06_15_2021-INSULDMG-1^668005/00 6/094 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
833206964-79519-ADMIN-07_27_2021-INSULDMG-1^668005/00 6/095 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
88670411-8119-ADMIN-08_05_2020-POLEDERP-1^668005/00 6A/084 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
846356618-15959-DTLTRT-07_06_2022-GO95HV-1^668005/00 7/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
846356618-15959-DTLTRT-07_06_2022-GO95MLD-1^668005/00 7/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
335920711-25469-DTLTRT-07_20_2022-GO95MLD-1^668005/00 7/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2025-07-20 | 2
924510516-27669-ADMIN-05_24_2021-INSULDMG-1^668005/00 7/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
694379788-66519-DTLTRT-07_28_2022-GUYSLACK-1^668005/00 7/072 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-07-28 | 2025-07-28 | 2
177701189-80719-ADMIN-05_24_2021-INSULDMG-1^668005/00 7/076 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
216715300-80019-ADMIN-06_15_2021-INSULDMG-1^668005/00 7/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
506499844-53540-DTLTRT-10_02_2023-GO95HV-1^668010/00 10/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
937784506-80460-DTLTRT-10_12_2023-GO95HV-1^668010/00 10/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
937784506-80460-DTLTRT-10_12_2023-GO95MLD-1^668010/00 10/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
62310008-76069-DTLTRT-10_11_2023-GO95MLD-1^668010/00 10/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
142040518-5169-DTLTRT-10_23_2023-GO95HV-1^668010/00 10/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
142040518-5169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 10/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
181128184-32240-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 10A/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
660711464-30880-DTLTRT-09_27_2023-GO95MLD-1^668010/00 11/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
843274411-4119-ADMIN-12_31_2018-POLEREPL-1^668005/00 7/083 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
871205111-58119-ADMIN-08_05_2020-POLEDERP-1^668005/00 7/084 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
683677398-90498-DETAIL-08_17_2022-GO95MLD-1^668005/00 7/094 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
676703974-10619-DTLTRT-08_17_2022-GO95MLD-1^668005/00 7/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
612042055-71919-ADMIN-07_27_2021-INSULDMG-1^668005/00 7/096 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
136337600-76159-DTLTRT-07_05_2022-GO95MLD-1^668005/00 8/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
294736160-49269-ADMIN-08_05_2020-POLEDERP-1^668005/00 8/051 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
695792297-13779-DTLTRT-10_24_2023-GO95HV-1^668010/00 11/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
665832106-41990-DTLTRT-10_18_2023-GO95HV-1^668010/00 11/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
348953118-32630-DTLTRT-10_18_2023-GO95HV-1^668010/00 11/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
995571705-90890-DTLTRT-10_31_2023-GO95HV-1^668010/00 11/017 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
614874848-24679-DTLTRT-11_02_2023-GO95MLD-1^668010/00 11/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
32610481-85130-DTLTRT-10_05_2023-GO95MLD-1^668010/00 11/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
449832883-46579-AUDIT-11_10_2023-INSULDMG-1^668010/00 11/029 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-11-10 | 2026-11-10 | 2
331211971-66240-DTLTRT-10_03_2023-GO95MLD-1^668010/00 11/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
740415916-67669-ADMIN-05_24_2021-INSULDMG-1^668005/00 8/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
427958856-47319-ADMIN-11_30_2017-POLEDERP-1^668005/00 8/066 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
101950940-90019-ADMIN-06_15_2021-INSULDMG-1^668005/00 8/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
107683022-319-ADMIN-12_31_2018-POLEREPL-1^668005/00 8/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
392724784-92119-ADMIN-07_27_2021-INSULDMG-1^668005/00 8/095 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
392724784-92119-DTLTRT-08_17_2022-GO95MLD-1^668005/00 8/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
619307588-32959-DTLTRT-06_30_2022-GO95MLD-1^668005/00 9/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
619307588-32959-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 9/032 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
838498341-6469-DTLTRT-07_20_2022-GO95HV-1^668005/00 9/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
842102516-18669-ADMIN-05_24_2021-INSULDMG-1^668005/00 9/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
490413016-27769-ADMIN-05_24_2021-INSULDMG-1^668005/00 9/061 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
570144866-77319-ADMIN-11_30_2017-POLEDERP-1^668005/00 9/066 | POLE | CA-NON-TIER | Transmission | 2017-11-30 | 2022-10-30 | 2
291013163-73440-DTLTRT-10_02_2023-GO95HV-1^668010/00 11/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
736793804-4340-DTLTRT-10_04_2023-GO95HV-1^668010/00 11/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
736793804-4340-DTLTRT-10_04_2023-GUYHINS-1^668010/00 11/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
736793804-4340-DTLTRT-10_04_2023-GUYHINS-2^668010/00 11/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
98501075-4779-DTLTRT-10_10_2023-GO95MLD-1^668010/00 11/037 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
22443326-3960-DTLTRT-10_09_2023-GUYHINS-1^668010/00 11/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
232544276-50269-DTLTRT-10_09_2023-GO95MLD-1^668010/00 11/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
464531090-11019-DTLTRT-08_03_2022-POLETOP-1^668005/00 9/079 | POLE | CA-NON-TIER | Transmission | 2022-08-03 | 2025-08-03 | 2
348136981-46219-DTLTRT-08_15_2022-ANCHIDLE-1^668005/00 9/086 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-15 | 2025-08-15 | 2
761348222-20319-ADMIN-12_31_2018-POLEREPL-1^668005/00 9/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
16708513-8419-DTLTRT-08_16_2022-POLETOP-1^668005/00 9/092 | POLE | CA-NON-TIER | Transmission | 2022-08-16 | 2025-08-16 | 2
416147894-50619-DETAIL-08_17_2022-GO95MLD-1^668005/00 9/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-17 | 2025-08-17 | 2
416147894-50619-AUDIT-08_29_2022-GO95BLTC-1^668005/00 9/095 | OTHER | CA-NON-TIER | Transmission | 2022-08-29 | 2025-08-29 | 2
735273849-81769-ADMIN-08_11_2019-POLEDERP-1^668005/03 1/004 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
580632406-89069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 11/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
426230963-92340-DTLTRT-10_19_2023-GUYNOINS-1^668010/00 11A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
623827891-22340-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 11A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
623827891-22340-DTLTRT-10_03_2023-GUYNOINS-2^668010/00 11A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
975935786-33590-DTLTRT-10_16_2023-GO95HV-1^668010/00 11X/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
486288671-69470-DTLTRT-10_16_2023-GO95HV-1^668010/00 12/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
795171614-81469-DTLTRT-09_26_2023-SVCROAD-1^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
597666959-46769-ADMIN-06_15_2021-POLEDERP-1^668005/03 11/004 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
285226779-28769-ADMIN-01_02_2020-POLEDERP-1^668005/03 15/004 | POLE | CA-NON-TIER | Transmission | 2020-01-02 | 2023-01-02 | 2
573487674-81598-ADMIN-06_15_2021-POLEDERP-1^668005/03 16/005 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
573487674-81598-DTLTRT-10_10_2022-GO95HV-1^668005/03 16/005 | OTHER | CA-NON-TIER | Transmission | 2022-10-10 | 2027-10-10 | 3
181288489-78769-ADMIN-04_16_2019-POLEREPL-1^668005/03 17/004 | POLE | CA-NON-TIER | Transmission | 2019-04-16 | 2024-03-16 | 2
768286448-86069-DTLTRT-10_11_2022-GO95HV-1^668005/03 18/002 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
854360988-66669-DTLTRT-10_11_2022-GO95HV-1^668005/03 3/003 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
74234608-37669-DTLTRT-10_11_2022-GO95HV-1^668005/03 4/003 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
58139215-71869-ADMIN-05_15_2021-POLEDERP-1^668005/03 7/005 | POLE | CA-NON-TIER | Transmission | 2021-05-15 | 2024-05-15 | 2
343230929-12869-ADMIN-06_15_2021-POLEDERP-1^668005/03 8/005 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
343230929-12869-DTLTRT-10_10_2022-GO95HV-1^668005/03 8/005 | OTHER | CA-NON-TIER | Transmission | 2022-10-10 | 2027-10-10 | 3
511000839-75769-ADMIN-02_07_2022-POLEDERP-1^668005/03 9/004 | POLE | CA-NON-TIER | Transmission | 2022-02-07 | 2025-02-07 | 2
530417643-48379-DTLTRT-09_26_2023-GO95HV-1^668010/00 12/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
817970416-89990-DTLTRT-10_18_2023-GO95HV-1^668010/00 12/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
576015949-88630-DTLTRT-10_25_2023-GO95HV-1^668010/00 12/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
624513615-27890-AUDIT-11_10_2023-GO95HV-1^668010/00 12/017 | OTHER | CA-TIER-2 | Transmission | 2023-11-10 | 2028-11-10 | 3
876866739-88979-DTLTRT-10_26_2023-GO95HV-1^668010/00 12/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
448783463-29779-DTLTRT-10_19_2023-GO95MLD-1^668010/00 12/024 | OTHER | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
789259021-75330-DTLTRT-10_05_2023-GUYHINS-1^668010/00 12/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
550968603-53903-DETAIL-10_12_2022-GO95HV-1^668005/08 8X1/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
552138813-10323-DETAIL-10_12_2022-GO95HV-1^668005/08 8X2/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
285658633-67833-DETAIL-10_12_2022-GO95HV-1^668005/08 8X3/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
24604433-49633-DETAIL-10_12_2022-GO95HV-1^668005/08 8X4/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
771378443-743-DETAIL-10_12_2022-GO95HV-1^668005/08 8X6/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
159437443-25643-DETAIL-10_12_2022-GO95HV-1^668005/08 8X7/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
159437443-25643-DETAIL-10_12_2022-GUYHINS-2^668005/08 8X7/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
520575753-22953-DETAIL-10_12_2022-GO95HV-1^668005/08 8X8/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
140955893-42740-DTLTRT-10_04_2023-GO95HV-1^668010/00 12/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
817917591-47579-DTLTRT-10_03_2023-GUYHINS-1^668010/00 12/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
17909742-72540-DTLTRT-10_03_2023-GO95HV-1^668010/00 12/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
161210264-55740-DTLTRT-10_02_2023-GO95MLD-1^668010/00 12/034 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2026-10-02 | 2
170154546-28769-DTLTRT-10_09_2023-GO95HV-1^668010/00 12/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
865845684-51569-DTLTRT-10_10_2023-RISEBKSP-1^668010/00 12/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
865845684-51569-DTLTRT-10_10_2023-RISEGRD-1^668010/00 12/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
454372218-36069-DTLTRT-10_11_2023-GO95HV-1^668010/00 12/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
250547013-90113-DTLTRT-10_10_2023-GUYNOINS-2^668010/00 12A/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
250547013-90113-DTLTRT-10_10_2023-GUYNOINS-4^668010/00 12A/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
284928581-79470-DTLTRT-10_16_2023-GO95HV-1^668010/00 13/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
603038734-86379-DTLTRT-09_26_2023-GO95MLD-1^668010/00 13/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
587377753-73670-DTLTRT-09_26_2023-GO95HV-1^668010/00 13/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
972361816-35000-DTLTRT-10_18_2023-GO95HV-1^668010/00 13/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
501555801-18330-DTLTRT-10_30_2023-GO95HV-1^668010/00 13/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
600730915-37979-DTLTRT-10_31_2023-GO95BLTC-1^668010/00 13/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
851095596-99079-DTLTRT-11_01_2023-GO95HV-1^668010/00 13/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
824194268-38620-DTLTRT-11_02_2023-GO95HV-1^668010/00 13/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
847603133-50540-DTLTRT-10_19_2023-XARMSPCR-1^668010/00 13/024 | CROSSARM | CA-TIER-2 | Transmission | 2023-10-19 | 2024-10-19 | 2
893010450-4930-DTLTRT-11_03_2023-GO95HV-1^668010/00 13/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
397010541-56430-DTLTRT-10_05_2023-GO95HV-1^668010/00 13/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
520575753-22953-DETAIL-10_12_2022-GUYHINS-2^668005/08 8X8/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
520575753-22953-DETAIL-10_12_2022-GUYHINS-3^668005/08 8X8/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
520575753-22953-DETAIL-10_12_2022-GUYHINS-4^668005/08 8X8/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
575737673-52879-DTLTRT-09_27_2023-GO95HV-1^668010/00 1/006 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
5779135-17569-DTLTRT-10_17_2023-CLMBTRE-1^668010/00 1/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
308345061-61030-DTLTRT-10_30_2023-GO95HV-1^668010/00 1/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
975611084-95979-DTLTRT-10_30_2023-GO95HV-1^668010/00 1/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
926219268-9479-DTLTRT-11_02_2023-GO95HV-1^668010/00 1/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
138340549-35900-DTLTRT-10_26_2023-GUYLOINS-3^668010/00 1/023 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
747492319-1630-DTLTRT-10_19_2023-GO95HV-1^668010/00 1/026 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
173537351-36579-DTLTRT-10_05_2023-GO95HV-1^668010/00 1/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
394634371-66579-DTLTRT-10_04_2023-GO95HV-1^668010/00 1/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2028-10-04 | 3
599842902-58340-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 1/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
531002633-85940-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2028-10-02 | 3
515655185-5769-DTLTRT-11_03_2023-GO95HV-1^668010/00 1/037 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
415034995-56360-DTLTRT-10_09_2023-GO95HV-1^668010/00 1/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
419608113-48369-DTLTRT-10_11_2023-GO95MLD-1^668010/00 1/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
477594402-61321-DTLTRT-10_16_2023-GO95HV-1^668010/00 10/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
318662544-58469-DTLTRT-09_25_2023-GO95MLD-1^668010/00 10/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2026-09-25 | 2
297880096-95890-DTLTRT-10_18_2023-GO95HV-1^668010/00 10/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
217982008-22979-DTLTRT-10_18_2023-GO95HV-1^668010/00 10/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
113006475-76979-DTLTRT-10_31_2023-GO95HV-1^668010/00 10/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
541149306-79700-DTLTRT-11_01_2023-GO95HV-1^668010/00 10/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
397010541-56430-DTLTRT-10_05_2023-GO95MLD-1^668010/00 13/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
183880633-73240-DTLTRT-10_05_2023-GO95MLD-1^668010/00 13/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
183880633-73240-DTLTRT-10_05_2023-GRDRODHI-1^668010/00 13/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
232319566-68060-DTLTRT-10_09_2023-GO95MLD-1^668010/00 13/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
232319566-68060-DTLTRT-10_09_2023-GUYHINS-1^668010/00 13/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
232319566-68060-DTLTRT-10_09_2023-GUYHINS-2^668010/00 13/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
232319566-68060-DTLTRT-10_09_2023-GUYHINS-3^668010/00 13/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
277401545-85269-DTLTRT-10_10_2023-GO95HV-1^668010/00 13/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
883793136-44560-DTLTRT-10_12_2023-GO95HV-1^668010/00 13/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
454472038-51030-DETAIL-10_17_2023-GUYHINS-2^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-5^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-6^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
906086291-62570-DTLTRT-10_16_2023-GO95HV-1^668010/00 14/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
702188384-98980-DTLTRT-09_27_2023-GO95MLD-1^668010/00 14/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
297583238-81730-DTLTRT-10_18_2023-GO95HV-1^668010/00 14/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
965491739-46130-DETAIL-10_26_2023-GUYHINS-1^668010/00 14/021 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
965491739-46130-DETAIL-10_26_2023-GUYHINS-2^668010/00 14/021 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
965491739-46130-DETAIL-10_26_2023-GUYHINS-3^668010/00 14/021 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
55123269-29979-DTLTRT-10_26_2023-GO95HV-1^668010/00 14/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
352998851-30-DTLTRT-11_03_2023-GO95HV-1^668010/00 14/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
588874984-87840-DTLTRT-10_02_2023-GO95HV-1^668010/00 14/034 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2028-10-02 | 3
588874984-87840-DTLTRT-10_02_2023-GO95MLD-1^668010/00 14/034 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2028-10-02 | 3
713446664-81350-DTLTRT-11_03_2023-GO95HV-1^668010/00 14/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
409651476-10160-DTLTRT-10_09_2023-ABNDEQPM-1^668010/00 14/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
608576506-89169-DTLTRT-10_09_2023-GO95CL10-1^668010/00 14/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
508668155-75269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 14/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
610112246-68560-DTLTRT-10_12_2023-GO95HV-1^668010/00 14/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
325555928-94169-DTLTRT-10_11_2023-GO95HV-1^668010/00 14/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
325555928-94169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 14/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
66051028-28169-DTLTRT-10_10_2023-GO95HV-1^668010/00 14/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
360667163-89469-DTLTRT-09_26_2023-GO95MLD-1^668010/00 15/003 | OTHER | CA-NON-TIER | Transmission | 2023-09-26 | 2026-09-26 | 2
618874754-67780-DTLTRT-09_26_2023-GO95HV-1^668010/00 15/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
274361883-82680-DTLTRT-09_27_2023-GO95HV-1^668010/00 15/006 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
274361883-82680-DTLTRT-09_27_2023-GUYNOINS-2^668010/00 15/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
274361883-82680-DTLTRT-09_27_2023-GUYNOINS-3^668010/00 15/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
306909694-90779-DTLTRT-10_17_2023-GUYHINS-2^668010/00 15/007 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
649702636-18100-DTLTRT-10_18_2023-GO95HV-1^668010/00 15/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
153089721-43430-DTLTRT-10_30_2023-GO95HV-1^668010/00 15/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
621503174-13080-DTLTRT-10_31_2023-GO95HV-1^668010/00 15/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
704376146-34200-DTLTRT-11_01_2023-GO95HV-1^668010/00 15/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
612740571-84579-DTLTRT-10_05_2023-GO95HV-1^668010/00 15/027 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
42656361-19530-DTLTRT-10_05_2023-GO95HV-1^668010/00 15/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
569450033-14940-DTLTRT-10_04_2023-GO95HV-1^668010/00 15/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2028-10-04 | 3
48774962-96340-DTLTRT-10_03_2023-GO95MLD-1^668010/00 15/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
172964363-72340-DTLTRT-10_05_2023-INSULDMG-1^668010/00 15/032 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-10-05 | 2024-10-05 | 2
494152419-68979-DTLTRT-10_26_2023-GO95HV-1^668010/00 10/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
91726933-35779-DTLTRT-10_19_2023-GO95HV-1^668010/00 10/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
21780139-54130-DTLTRT-11_03_2023-GO95HV-1^668010/00 10/026 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
582254773-17640-DTLTRT-10_04_2023-GO95HV-1^668010/00 10/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
297936813-5140-DTLTRT-10_03_2023-GO95MLD-1^668010/00 10/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
506499844-53540-DTLTRT-10_02_2023-GO95MLD-1^668010/00 10/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
716846955-20650-DTLTRT-10_10_2023-GO95MLD-1^668010/00 10/037 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
688514466-80269-DTLTRT-10_09_2023-GO95HV-1^668010/00 10/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
796551319-93479-DTLTRT-11_01_2023-GUYNOINS-1^668010/00 10A/018 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-01 | 2026-11-01 | 2
181128184-32240-DTLTRT-10_04_2023-GUYNOINS-2^668010/00 10A/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
700104508-27820-DTLTRT-10_17_2023-GUYNOINS-1^668010/00 10XB/009 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
700104508-27820-DTLTRT-10_17_2023-GUYNOINS-2^668010/00 10XB/009 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
700104508-27820-DTLTRT-10_17_2023-GUYNOINS-3^668010/00 10XB/009 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
216091161-29470-DTLTRT-10_16_2023-GO95HV-1^668010/00 11/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
766339812-44469-DTLTRT-10_16_2023-GO95MLD-1^668010/00 11/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2026-10-16 | 2
680819384-24180-DTLTRT-09_26_2023-GO95HV-1^668010/00 11/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
660711464-30880-DTLTRT-09_27_2023-GO95HV-1^668010/00 11/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
614874848-24679-DTLTRT-11_02_2023-GO95CL10-1^668010/00 11/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
614874848-24679-DTLTRT-11_02_2023-GO95TCH-1^668010/00 11/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
893496869-91579-DTLTRT-10_26_2023-GO95BLTC-1^668010/00 11/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
893496869-91579-DTLTRT-10_26_2023-GO95MLD-1^668010/00 11/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
154286043-26240-DTLTRT-10_19_2023-GUYNOINS-1^668010/00 11/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
647873680-64579-DTLTRT-11_03_2023-GO95HV-1^668010/00 11/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
32610481-85130-DTLTRT-10_05_2023-GUYHINS-1^668010/00 11/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
449832883-46579-DTLTRT-10_04_2023-GO95HV-1^668010/00 11/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
291013163-73440-DTLTRT-10_02_2023-GO95MLD-1^668010/00 11/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
736793804-4340-DTLTRT-10_04_2023-GO95MLD-1^668010/00 11/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
98501075-4779-AUDIT-11_10_2023-GO95HV-1^668010/00 11/037 | OTHER | CA-NON-TIER | Transmission | 2023-11-10 | 2028-11-10 | 3
22443326-3960-DTLTRT-10_09_2023-GO95HV-1^668010/00 11/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
22443326-3960-DTLTRT-10_09_2023-GO95MLD-1^668010/00 11/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
172964363-72340-DTLTRT-10_05_2023-INSULDMG-2^668010/00 15/032 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-10-05 | 2024-10-05 | 2
602757874-56350-DTLTRT-11_03_2023-GUYHINS-1^668010/00 15/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
4965955-10160-DTLTRT-10_09_2023-GO95HV-1^668010/00 15/037 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
62650565-47669-DTLTRT-10_10_2023-GO95HV-1^668010/00 15/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
103416856-47069-DTLTRT-10_12_2023-GO95HV-1^668010/00 15/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
103416856-47069-DTLTRT-10_12_2023-SVCDEFLC-1^668010/00 15/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
813837536-88069-DTLTRT-10_23_2023-GO95HV-1^668010/00 15/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
810428131-67570-DTLTRT-10_16_2023-GO95MLD-1^668010/00 15X/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2026-10-16 | 2
205782076-59690-DTLTRT-10_24_2023-GO95HV-1^668010/00 16/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
252453848-37730-DTLTRT-10_18_2023-GO95HV-1^668010/00 16/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
471774794-20280-DTLTRT-10_31_2023-GO95HV-1^668010/00 16/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
405358446-40390-DTLTRT-11_01_2023-GO95HV-1^668010/00 16/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
486265249-15879-DTLTRT-10_19_2023-GO95HV-1^668010/00 16/025 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
248587889-30430-DTLTRT-11_03_2023-UBPBXARM-1^668010/00 16/026 | CROSSARM | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
417836643-66940-DTLTRT-10_04_2023-GO95MLD-1^668010/00 16/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
232544276-50269-DTLTRT-10_09_2023-ABNDEQPM-1^668010/00 11/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
232544276-50269-DTLTRT-10_09_2023-GO95HV-1^668010/00 11/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
120302116-46460-DTLTRT-10_12_2023-GO95HV-1^668010/00 11/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
580632406-89069-DTLTRT-10_12_2023-GO95BLTC-1^668010/00 11/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
580632406-89069-DTLTRT-10_12_2023-GRDRODHI-1^668010/00 11/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
580632406-89069-DTLTRT-10_12_2023-GRDRODHI-2^668010/00 11/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
426230963-92340-DTLTRT-10_19_2023-GUYNOINS-2^668010/00 11A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
426230963-92340-DTLTRT-10_19_2023-GUYNOINS-3^668010/00 11A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
426230963-92340-DTLTRT-10_19_2023-GUYNOINS-4^668010/00 11A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
623827891-22340-DTLTRT-10_03_2023-GUYNOINS-3^668010/00 11A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
619782632-42540-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 11A/031 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
619782632-42540-DTLTRT-10_03_2023-GUYNOINS-2^668010/00 11A/031 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
676724434-28440-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 11A/035 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
795171614-81469-DTLTRT-09_26_2023-ANCHIDLE-1^668010/00 12/004 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
795171614-81469-DTLTRT-09_26_2023-GO95MLD-1^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
413002572-47340-DTLTRT-10_03_2023-GO95HV-1^668010/00 16/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
930958624-83040-DTLTRT-10_02_2023-UBPBCTGD-1^668010/00 16/034 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2026-10-02 | 2
550518575-62269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 16/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
891682866-18069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 16/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
813480148-44169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 16/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
585217838-67169-DTLTRT-10_10_2023-GO95HV-1^668010/00 16/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
585217838-67169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 16/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
925143064-580-DTLTRT-09_27_2023-GO95MLD-1^668010/00 16X/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-1^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-2^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-3^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-5^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-6^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
214019768-47179-DTLTRT-10_17_2023-GO95STUB-1^668010/00 16X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
755437474-77580-DTLTRT-10_17_2023-GO95MLD-1^668010/00 17/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
400279999-9869-DTLTRT-11_03_2023-GO95MLD-1^668010/00 17/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
795171614-81469-DTLTRT-09_26_2023-GRDRODHI-1^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
795171614-81469-DTLTRT-09_26_2023-GRDRODHI-2^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
795171614-81469-DTLTRT-09_26_2023-GRDRODHI-3^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
771930464-46880-DTLTRT-09_27_2023-GO95MLD-1^668010/00 12/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
543900018-25630-DTLTRT-10_18_2023-GO95HV-1^668010/00 12/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
539682300-1930-DTLTRT-11_03_2023-GO95HV-1^668010/00 12/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
539682300-1930-DTLTRT-11_03_2023-GO95MLD-1^668010/00 12/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
140955893-42740-DTLTRT-10_04_2023-GO95MLD-1^668010/00 12/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
817917591-47579-DTLTRT-10_03_2023-GO95HV-1^668010/00 12/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
917176334-14150-DTLTRT-11_03_2023-GO95HV-1^668010/00 12/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
170154546-28769-DTLTRT-10_09_2023-GO95MLD-1^668010/00 12/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
752733326-2769-DTLTRT-10_12_2023-GO95HV-1^668010/00 12/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
752733326-2769-DTLTRT-10_12_2023-GO95MLD-1^668010/00 12/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
454372218-36069-DTLTRT-10_11_2023-GO95MLD-1^668010/00 12/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
636745389-11239-DTLTRT-10_05_2023-GUYHINS-1^668010/00 17/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
636745389-11239-AUDIT-11_20_2023-GO95HV-1^668010/00 17/028 | OTHER | CA-TIER-2 | Transmission | 2023-11-20 | 2028-11-20 | 3
484367544-12940-DTLTRT-10_02_2023-GRDRODHI-1^668010/00 17/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
317150685-28260-DTLTRT-10_09_2023-GO95MLD-1^668010/00 17/037 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
709710348-37169-DTLTRT-10_10_2023-GO95HV-1^668010/00 17/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
356532509-5530-DTLTRT-11_03_2023-GO95MLD-1^668010/00 17A/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
991471489-63439-DTLTRT-10_05_2023-GUYSLACK-1^668010/00 17A/028 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-05 | 2026-10-05 | 2
623734781-6779-DTLTRT-10_16_2023-GO95HV-1^668010/00 18/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
36287608-43169-DTLTRT-10_10_2023-GUYNOINS-1^668010/00 12/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
375097031-17330-DTLTRT-10_05_2023-GUYHINS-1^668010/00 12A/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
375097031-17330-DTLTRT-10_05_2023-GUYNOINS-1^668010/00 12A/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
250547013-90113-DTLTRT-10_10_2023-GUYNOINS-1^668010/00 12A/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
250547013-90113-DTLTRT-10_10_2023-GUYNOINS-3^668010/00 12A/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
274472706-76790-DTLTRT-10_17_2023-GUYHINS-1^668010/00 12X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
977593628-56920-DTLTRT-10_17_2023-GO95MLD-1^668010/00 12X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
603038734-86379-DTLTRT-09_26_2023-GUYHINS-1^668010/00 13/004 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
587377753-73670-DTLTRT-09_26_2023-GO95STUB-1^668010/00 13/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
600730915-37979-DTLTRT-10_31_2023-GO95HV-1^668010/00 13/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
770938026-44000-DTLTRT-11_01_2023-GO95HV-1^668010/00 13/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
288502019-1900-DTLTRT-10_26_2023-GO95HV-1^668010/00 13/021 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
990666832-67579-DTLTRT-10_03_2023-GO95HV-1^668010/00 13/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
775253052-45540-DTLTRT-10_03_2023-GO95HV-1^668010/00 13/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
635791764-25740-DTLTRT-10_04_2023-GO95HV-1^668010/00 13/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
232319566-68060-DTLTRT-10_09_2023-GUYHINS-4^668010/00 13/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
277401545-85269-DTLTRT-10_10_2023-INSULDMG-1^668010/00 13/040 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
932367616-29069-DTLTRT-10_23_2023-GO95HV-1^668010/00 13/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
627705743-33470-DTLTRT-09_26_2023-SVCDEFLC-1^668010/00 13A/003 | OTHER | CA-NON-TIER | Transmission | 2023-09-26 | 2026-09-26 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-1^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-3^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-4^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
300480741-74979-DTLTRT-10_30_2023-GO95HV-1^668010/00 18/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
926664576-30400-DTLTRT-11_02_2023-GO95HV-1^668010/00 18/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
953151503-32840-DTLTRT-10_19_2023-GO95HV-1^668010/00 18/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
922908111-28030-DTLTRT-10_05_2023-GO95MLD-1^668010/00 18/027 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
875045411-15930-DTLTRT-10_05_2023-GO95HV-1^668010/00 18/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
751995102-87340-DTLTRT-10_03_2023-GO95HV-1^668010/00 18/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
273322676-35069-DTLTRT-10_23_2023-GO95HV-1^668010/00 18/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
425119286-11060-DTLTRT-10_23_2023-GUYNOINS-1^668010/00 18A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
425119286-11060-DTLTRT-10_23_2023-GUYNOINS-3^668010/00 18A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
586551626-27000-DTLTRT-10_17_2023-ABNDEQPM-1^668010/00 18X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
68044301-74769-DTLTRT-09_25_2023-GO95MLD-1^668010/00 19/001 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-GUYHINS-2^668010/00 19/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-SVCROAD-1^668010/00 19/001 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
675695223-80370-AUDIT-11_20_2023-ABNDEQPM-1^668010/00 19/002 | OTHER | CA-NON-TIER | Transmission | 2023-11-20 | 2028-11-20 | 3
415606353-37779-DTLTRT-09_27_2023-GO95HV-1^668010/00 19/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
410479685-80479-DTLTRT-11_01_2023-GO95HV-1^668010/00 19/017 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
565629076-24400-DTLTRT-11_02_2023-GO95HV-1^668010/00 19/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
222136384-15540-DTLTRT-10_04_2023-GO95HV-1^668010/00 19/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
817810501-4970-DTLTRT-09_25_2023-GUYNOINS-3^668010/00 19A/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
817810501-4970-DTLTRT-09_25_2023-GUYNOINS-4^668010/00 19A/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
817810501-4970-DTLTRT-09_25_2023-POLETOP-1^668010/00 19A/001 | POLE | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
361667406-60460-DTLTRT-10_09_2023-GUYNOINS-1^668010/00 1A/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
667571355-4090-DTLTRT-09_26_2023-GUYHINS-1^668010/00 1X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
180370408-37720-DTLTRT-10_17_2023-GO95MLD-1^668010/00 1X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
119221653-39470-DTLTRT-09_26_2023-GO95MLD-1^668010/00 14/003 | OTHER | CA-NON-TIER | Transmission | 2023-09-26 | 2026-09-26 | 2
783001936-56190-DTLTRT-10_24_2023-GO95HV-1^668010/00 14/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
376243402-86179-DTLTRT-10_24_2023-GO95HV-1^668010/00 14/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
352998851-30-DTLTRT-11_03_2023-GO95MLD-1^668010/00 14/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
627139451-85530-DTLTRT-10_05_2023-GO95HV-1^668010/00 14/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
378546542-57769-DTLTRT-10_03_2023-GO95HV-1^668010/00 14/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
859604145-59869-DTLTRT-10_10_2023-GO95HV-1^668010/00 14/037 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
658840323-35570-DTLTRT-10_24_2023-UBPBCTGD-1^668010/00 2/003 | OTHER | CA-NON-TIER | Transmission | 2023-10-24 | 2026-10-24 | 2
222774143-19280-DTLTRT-09_25_2023-GO95MLD-1^668010/00 2/004 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
222774143-19280-DTLTRT-09_25_2023-INSULDMG-1^668010/00 2/004 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
564695422-869-DTLTRT-09_26_2023-GO95STUB-1^668010/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
425969995-41479-DTLTRT-11_01_2023-GO95HV-1^668010/00 2/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
265727378-26020-DTLTRT-11_02_2023-GO95HV-1^668010/00 2/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
425982859-85830-DTLTRT-10_26_2023-GO95HV-1^668010/00 2/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
587138888-40930-DTLTRT-10_19_2023-GO95HV-1^668010/00 2/025 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
587138888-40930-DTLTRT-10_19_2023-GO95MLD-1^668010/00 2/025 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
587138888-40930-DTLTRT-10_19_2023-UBPBXARM-1^668010/00 2/025 | CROSSARM | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
656973429-26469-DTLTRT-10_19_2023-GO95HV-1^668010/00 2/026 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
656973429-26469-DTLTRT-10_19_2023-GO95MLD-1^668010/00 2/026 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
658617539-92469-DTLTRT-11_03_2023-GO95HV-1^668010/00 2/027 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
780753141-21230-DTLTRT-10_05_2023-GO95MLD-1^668010/00 2/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
63515461-58140-DTLTRT-10_05_2023-GO95HV-1^668010/00 2/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
63515461-58140-DTLTRT-10_05_2023-GO95MLD-1^668010/00 2/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
108459372-78579-DTLTRT-10_03_2023-GO95MLD-1^668010/00 2/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
530394763-13640-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
880540605-72150-DTLTRT-11_03_2023-GO95HV-1^668010/00 2/037 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
836783816-66460-DTLTRT-10_09_2023-GO95HV-1^668010/00 2/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
836783816-66460-DTLTRT-10_09_2023-GUYHINS-1^668010/00 2/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
727934726-82260-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
727934726-82260-DTLTRT-10_09_2023-GUYHINS-2^668010/00 2/039 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
612218986-57069-DTLTRT-10_12_2023-GO95HV-1^668010/00 2/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
612218986-57069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 2/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
735109948-14169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 2/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
113029358-86169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 2/045 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
153297724-96980-DTLTRT-09_27_2023-GUYNOINS-1^668010/00 20/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
153297724-96980-DTLTRT-09_27_2023-GUYNOINS-2^668010/00 20/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
645335066-93400-DTLTRT-10_18_2023-GO95HV-1^668010/00 20/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
186054094-81640-DTLTRT-10_04_2023-GO95HV-1^668010/00 20/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
409651476-10160-DTLTRT-10_09_2023-GO95HV-1^668010/00 14/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
608576506-89169-DTLTRT-10_09_2023-GO95MLD-1^668010/00 14/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
573251026-9069-DTLTRT-10_23_2023-GO95MLD-1^668010/00 14/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
342732473-73669-DTLTRT-10_16_2023-GO95HV-1^668010/00 15/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
911967893-78379-DTLTRT-09_27_2023-GO95HV-1^668010/00 15/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
274361883-82680-DTLTRT-09_27_2023-GUYNOINS-1^668010/00 15/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
306909694-90779-DTLTRT-10_17_2023-GO95MLD-1^668010/00 15/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
306909694-90779-DTLTRT-10_17_2023-GUYHINS-1^668010/00 15/007 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
128392835-87990-DTLTRT-10_31_2023-GO95HV-1^668010/00 15/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
253736939-53579-DTLTRT-10_19_2023-GO95MLD-1^668010/00 15/025 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
42656361-19530-DTLTRT-10_05_2023-GO95MLD-1^668010/00 15/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
602757874-56350-DTLTRT-11_03_2023-GO95HV-1^668010/00 15/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
337351086-79869-DTLTRT-10_09_2023-GO95MLD-1^668010/00 15/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
193102326-54779-DTLTRT-10_09_2023-GO95MLD-1^668010/00 15/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
186054094-81640-DTLTRT-10_04_2023-GO95MLD-1^668010/00 20/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
321130656-4300-DTLTRT-10_24_2023-GUYHINS-1^668010/00 20X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
549585199-69930-DTLTRT-10_25_2023-GO95HV-1^668010/00 21/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
753125456-67979-DTLTRT-11_02_2023-GO95HV-1^668010/00 21/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
753125456-67979-DTLTRT-11_02_2023-GO95MLD-1^668010/00 21/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
603641516-8800-DTLTRT-10_17_2023-GO95HV-1^668010/00 21X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
492964581-2830-DTLTRT-10_30_2023-GO95HV-1^668010/00 22/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
27189926-4000-DTLTRT-10_17_2023-GUYHINS-2^668010/00 22X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
417966664-18780-DTLTRT-10_17_2023-GO95MLD-1^668010/00 23/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
466280629-57569-DTLTRT-10_25_2023-GO95BLTC-1^668010/00 23/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
287040149-96130-DTLTRT-10_18_2023-GO95HV-1^668010/00 26/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
66370126-61560-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2A/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
909771188-78020-DTLTRT-10_17_2023-GO95MLD-1^668010/00 2X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
729339242-46170-DTLTRT-09_26_2023-GO95HV-1^668010/00 3/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
608718254-63980-DTLTRT-09_27_2023-GO95HV-1^668010/00 3/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
193102326-54779-DTLTRT-10_09_2023-UBPBCTGD-1^668010/00 15/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
103416856-47069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 15/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
348689838-97169-DTLTRT-10_10_2023-GO95HV-1^668010/00 15/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
998279446-26260-DTLTRT-10_23_2023-GUYNOINS-1^668010/00 15A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
998279446-26260-DTLTRT-10_23_2023-GUYNOINS-2^668010/00 15A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
998279446-26260-DTLTRT-10_23_2023-GUYNOINS-3^668010/00 15A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
810428131-67570-DTLTRT-10_16_2023-GO95BLTC-1^668010/00 15X/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
65393783-62870-DTLTRT-09_26_2023-GO95MLD-1^668010/00 16/003 | OTHER | CA-NON-TIER | Transmission | 2023-09-26 | 2026-09-26 | 2
261923164-26880-DTLTRT-09_26_2023-GO95HV-1^668010/00 16/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
920473993-5780-DTLTRT-09_27_2023-GO95HV-1^668010/00 16/006 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
203380454-88169-DTLTRT-10_17_2023-GO95MLD-1^668010/00 16/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
26192945-1090-DTLTRT-10_31_2023-GO95BLTC-1^668010/00 16/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
26192945-1090-DTLTRT-10_31_2023-GO95MLD-1^668010/00 16/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2026-10-31 | 2
582999556-87200-DTLTRT-11_01_2023-GO95HV-1^668010/00 16/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
444050909-48530-DTLTRT-10_26_2023-GO95MLD-1^668010/00 16/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
444050909-48530-DTLTRT-10_26_2023-RISEGRD-1^668010/00 16/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
248587889-30430-DTLTRT-11_03_2023-GO95HV-1^668010/00 16/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
192566181-54030-DTLTRT-10_05_2023-GO95MLD-1^668010/00 16/027 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
808168371-65579-DTLTRT-10_05_2023-GO95HV-1^668010/00 16/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
930958624-83040-DTLTRT-10_02_2023-GO95MLD-1^668010/00 16/034 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2026-10-02 | 2
429722294-73769-DTLTRT-11_03_2023-GO95HV-1^668010/00 16/036 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
429722294-73769-DTLTRT-11_03_2023-GO95MLD-1^668010/00 16/036 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
336121706-75160-DTLTRT-10_09_2023-GO95MLD-1^668010/00 16/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
946303495-59190-DTLTRT-10_24_2023-GO95MLD-1^668010/00 3/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
115282156-47300-DTLTRT-11_01_2023-GO95HV-1^668010/00 3/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
188645803-34179-DTLTRT-11_02_2023-GO95HV-1^668010/00 3/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
306089261-25579-DTLTRT-10_05_2023-GO95HV-1^668010/00 3/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
693679632-88340-DTLTRT-10_03_2023-GO95HV-1^668010/00 3/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
211927193-9579-DTLTRT-10_02_2023-GO95MLD-1^668010/00 3/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
405634836-93560-DTLTRT-10_09_2023-GO95HV-1^668010/00 3/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
405634836-93560-DTLTRT-10_09_2023-GO95MLD-1^668010/00 3/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
405634836-93560-DTLTRT-10_09_2023-GUYHINS-1^668010/00 3/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
556894515-61269-DTLTRT-10_10_2023-GO95HV-1^668010/00 3/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
379660306-21169-DTLTRT-10_12_2023-GO95HV-1^668010/00 3/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
602709846-76560-DTLTRT-10_09_2023-GUYNOINS-1^668010/00 3A/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
602709846-76560-DTLTRT-10_09_2023-GUYNOINS-2^668010/00 3A/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
581221268-84270-DTLTRT-10_10_2023-GUYNOINS-1^668010/00 3A/045 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
685345601-4469-DTLTRT-09_25_2023-GUYHINS-1^668010/00 4/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
685345601-4469-DTLTRT-09_25_2023-GUYHINS-2^668010/00 4/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
124521753-67270-AUDIT-11_10_2023-XARMSPCR-1^668010/00 4/005 | CROSSARM | CA-TIER-2 | Transmission | 2023-11-10 | 2024-11-10 | 2
196028399-93430-DTLTRT-10_18_2023-GO95HV-1^668010/00 4/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
411134088-85430-DTLTRT-11_02_2023-GO95HV-1^668010/00 4/021 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
669753789-6930-DTLTRT-10_26_2023-GO95MLD-1^668010/00 4/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
928199969-42730-DTLTRT-10_19_2023-GO95HV-1^668010/00 4/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
99537359-79630-DTLTRT-11_03_2023-GO95MLD-1^668010/00 4/027 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
883425671-32330-DTLTRT-10_05_2023-GO95MLD-1^668010/00 4/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
59036723-89840-AUDIT-11_16_2023-GO95CN-1^668010/00 4/032 | OTHER | CA-TIER-2 | Transmission | 2023-11-16 | 2026-11-16 | 2
941133984-77469-DTLTRT-10_04_2023-GUYHINS-1^668010/00 4/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
393774456-31660-DTLTRT-10_09_2023-GO95HV-1^668010/00 4/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
642130396-72360-DTLTRT-10_09_2023-GO95HV-1^668010/00 4/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
256281698-36169-DTLTRT-10_10_2023-GUYHINS-1^668010/00 4/045 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
256281698-36169-DTLTRT-10_10_2023-GUYHINS-2^668010/00 4/045 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
120980001-51970-DTLTRT-09_25_2023-GUYNOINS-2^668010/00 4A/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
766992346-58069-DTLTRT-10_25_2023-GO95MLD-1^668010/00 16/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2026-10-25 | 2
246779621-89670-DTLTRT-10_16_2023-GO95HV-1^668010/00 16X/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
742865886-64890-DTLTRT-10_17_2023-GUYHINS-4^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
214019768-47179-DTLTRT-10_17_2023-GO95HV-1^668010/00 16X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2028-10-17 | 3
632937093-4970-DTLTRT-09_26_2023-GO95HV-1^668010/00 17/003 | OTHER | CA-NON-TIER | Transmission | 2023-09-26 | 2028-09-26 | 3
265282474-55469-DTLTRT-09_26_2023-GO95MLD-1^668010/00 17/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
755437474-77580-DTLTRT-10_17_2023-SVCDEFLC-1^668010/00 17/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
980844258-79730-DTLTRT-10_18_2023-GO95HV-1^668010/00 17/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
431884079-50830-DTLTRT-10_25_2023-GO95HV-1^668010/00 17/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
858119666-46300-DTLTRT-11_01_2023-GO95HV-1^668010/00 17/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
780547289-51900-DTLTRT-10_26_2023-GO95HV-1^668010/00 17/021 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
788854981-25030-DTLTRT-10_05_2023-GO95HV-1^668010/00 17/027 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
636745389-11239-DTLTRT-10_05_2023-GO95MLD-1^668010/00 17/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
960517582-57340-DTLTRT-10_03_2023-GO95HV-1^668010/00 17/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
960517582-57340-DTLTRT-10_03_2023-GO95MLD-1^668010/00 17/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
834290834-50140-DTLTRT-10_02_2023-GO95BLTC-1^668010/00 17/034 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2028-10-02 | 3
317150685-28260-DTLTRT-10_09_2023-GO95HV-1^668010/00 17/037 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
180978656-65069-DTLTRT-10_23_2023-GO95HV-1^668010/00 17/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
924628801-97670-DTLTRT-10_16_2023-GO95HV-1^668010/00 17X/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
924628801-97670-DTLTRT-10_16_2023-GO95MLD-1^668010/00 17X/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2026-10-16 | 2
65793078-21430-DTLTRT-10_30_2023-GO95HV-1^668010/00 17X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-30 | 2028-10-30 | 3
50506503-17779-DTLTRT-09_27_2023-GO95HV-1^668010/00 18/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
28979899-54430-DTLTRT-10_26_2023-GO95MLD-1^668010/00 18/021 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
809811779-55879-DTLTRT-10_19_2023-ABNDEQPM-1^668010/00 18/025 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
21900619-5469-DTLTRT-11_03_2023-GO95MLD-1^668010/00 18/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
21900619-5469-DTLTRT-11_03_2023-UBPBCTGD-1^668010/00 18/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
240665133-82540-DTLTRT-10_02_2023-GO95MLD-1^668010/00 18/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
415467954-66469-DTLTRT-10_02_2023-GO95MLD-1^668010/00 18/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
273322676-35069-DTLTRT-10_23_2023-GO95MLD-1^668010/00 18/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
273322676-35069-DTLTRT-10_23_2023-GUYHINS-1^668010/00 18/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
376242584-10820-DTLTRT-11_01_2023-GUYNOINS-1^668010/00 18A/017 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-01 | 2026-11-01 | 2
320642394-17150-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 4A/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
320642394-17150-DTLTRT-10_04_2023-GUYNOINS-2^668010/00 4A/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
320642394-17150-DTLTRT-10_04_2023-GUYNOINS-3^668010/00 4A/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
405037321-27469-DTLTRT-09_25_2023-GO95MLD-1^668010/00 5/001 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
405037321-27469-DTLTRT-09_25_2023-GRDRODHI-1^668010/00 5/001 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
405037321-27469-DTLTRT-09_25_2023-GRDRODHI-3^668010/00 5/001 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
405037321-27469-DTLTRT-09_25_2023-GRDRODHI-4^668010/00 5/001 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
572941493-22209-DTLTRT-09_25_2023-GO95HV-1^668010/00 5/003 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2028-09-25 | 3
572941493-22209-DTLTRT-09_25_2023-GUYHINS-3^668010/00 5/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
630378283-98869-DTLTRT-09_25_2023-GO95MLD-1^668010/00 5/004 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
630378283-98869-DTLTRT-09_25_2023-GO95TCH-1^668010/00 5/004 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
512100119-4030-DTLTRT-10_25_2023-GO95HV-1^668010/00 5/013 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
762624894-93090-DTLTRT-10_31_2023-GO95HV-1^668010/00 5/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
309191928-56800-DTLTRT-11_02_2023-GUYHINS-2^668010/00 5/020 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
309191928-56800-DTLTRT-11_02_2023-GUYHINS-3^668010/00 5/020 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
620509399-1579-DTLTRT-10_26_2023-GO95MLD-1^668010/00 5/023 | OTHER | CA-NON-TIER | Transmission | 2023-10-26 | 2026-10-26 | 2
981374259-99769-DTLTRT-10_19_2023-GO95HV-1^668010/00 5/026 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
876629679-54579-DTLTRT-11_02_2023-GO95MLD-1^668010/00 5/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
784289501-18730-DTLTRT-10_04_2023-GO95MLD-1^668010/00 5/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
170451253-29669-DTLTRT-10_04_2023-GO95BLTC-1^668010/00 5/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
458520984-14269-DTLTRT-10_11_2023-GO95HV-1^668010/00 5/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
805075068-16169-DTLTRT-10_11_2023-GO95HV-1^668010/00 5/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
438039618-35120-DTLTRT-10_17_2023-GUYHINS-2^668010/00 5X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
562888512-37750-DTLTRT-09_25_2023-GO95HV-1^668010/00 6/002 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2028-09-25 | 3
562888512-37750-DTLTRT-09_25_2023-GO95MLD-1^668010/00 6/002 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
562888512-37750-DTLTRT-09_25_2023-GRDRODHI-1^668010/00 6/002 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
332794423-50970-DTLTRT-09_25_2023-GO95HV-1^668010/00 6/003 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2028-09-25 | 3
271437193-15569-DTLTRT-09_26_2023-GO95HV-1^668010/00 6/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
271437193-15569-DTLTRT-09_26_2023-GO95MLD-1^668010/00 6/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
509377848-3130-DTLTRT-10_18_2023-GO95MLD-1^668010/00 6/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
144252176-31500-DTLTRT-11_01_2023-GO95HV-1^668010/00 6/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
343757879-44830-DTLTRT-10_26_2023-GO95HV-1^668010/00 6/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
425119286-11060-DTLTRT-10_23_2023-GUYNOINS-2^668010/00 18A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
425119286-11060-DTLTRT-10_23_2023-GUYNOINS-4^668010/00 18A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
250632834-56980-DTLTRT-09_27_2023-GO95MLD-1^668010/00 18X/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
68044301-74769-DTLTRT-09_25_2023-GO95BLTC-1^668010/00 19/001 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2028-09-25 | 3
68044301-74769-DTLTRT-09_25_2023-GUYHINS-1^668010/00 19/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-GUYHINS-3^668010/00 19/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-GUYHINS-4^668010/00 19/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
675695223-80370-DTLTRT-09_25_2023-GO95HV-1^668010/00 19/002 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2028-09-25 | 3
675695223-80370-AUDIT-11_10_2023-GUYHINS-1^668010/00 19/002 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-11-10 | 2026-11-10 | 2
675695223-80370-AUDIT-11_10_2023-INSULDMG-1^668010/00 19/002 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-11-10 | 2026-11-10 | 2
480770414-2180-DTLTRT-09_26_2023-GO95HV-1^668010/00 19/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
598205686-62321-DTLTRT-11_01_2023-GO95HV-1^668010/00 19/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
463432189-12530-DETAIL-10_19_2023-GO95MLD-1^668010/00 19/025 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
817810501-4970-DTLTRT-09_25_2023-GUYNOINS-1^668010/00 19A/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
817810501-4970-DTLTRT-09_25_2023-GUYNOINS-2^668010/00 19A/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
63664801-29080-DTLTRT-09_27_2023-GO95MLD-1^668010/00 19X/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
667571355-4090-DTLTRT-09_26_2023-GUYHINS-2^668010/00 1X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
667571355-4090-DTLTRT-09_26_2023-GUYHINS-3^668010/00 1X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
180370408-37720-DTLTRT-10_17_2023-GO95HV-1^668010/00 1X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
564695422-869-DTLTRT-09_26_2023-GO95MLD-1^668010/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
205808878-41321-DTLTRT-10_18_2023-GO95HV-1^668010/00 2/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
351764394-26979-DTLTRT-10_30_2023-GO95HV-1^668010/00 2/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
288600585-17190-DTLTRT-10_31_2023-GO95HV-1^668010/00 2/017 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
800854549-17630-DTLTRT-10_19_2023-GO95MLD-1^668010/00 2/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
780753141-21230-DTLTRT-10_05_2023-GO95HV-1^668010/00 2/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
918090032-68340-DTLTRT-10_03_2023-GO95HV-1^668010/00 2/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
826206264-50140-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
826206264-50140-DTLTRT-10_02_2023-GRDRODHI-1^668010/00 2/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
158523173-6040-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2028-10-02 | 3
158523173-6040-DTLTRT-10_02_2023-GO95MLD-1^668010/00 2/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-02 | 2026-10-02 | 2
836783816-66460-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
533501549-50230-DTLTRT-11_02_2023-TRNSCENT-1^668010/00 6/025 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2023-11-02 | 2026-11-02 | 2
533501549-50230-DTLTRT-11_02_2023-UBPBXARM-1^668010/00 6/025 | CROSSARM | CA-NON-TIER | Transmission | 2023-11-02 | 2026-11-02 | 2
779773513-49579-DTLTRT-10_02_2023-GO95MLD-1^668010/00 6/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
79694563-75440-DTLTRT-10_04_2023-GO95MLD-1^668010/00 6/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
577210816-29360-DTLTRT-10_09_2023-GO95HV-1^668010/00 6/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
441753055-25269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 6/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
376473136-80169-DTLTRT-10_12_2023-GO95MLD-1^668010/00 6/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
351253541-17270-AUDIT-11_10_2023-GO95HV-1^668010/00 7/001 | OTHER | CA-NON-TIER | Transmission | 2023-11-10 | 2028-11-10 | 3
422741214-47280-DTLTRT-09_27_2023-GO95MLD-1^668010/00 7/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
795067968-64330-DTLTRT-10_18_2023-GO95HV-1^668010/00 7/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
626741686-8500-DTLTRT-11_01_2023-GO95HV-1^668010/00 7/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
16219169-52330-DTLTRT-11_02_2023-GO95HV-1^668010/00 7/025 | OTHER | CA-NON-TIER | Transmission | 2023-11-02 | 2028-11-02 | 3
24238730-61830-DTLTRT-11_03_2023-GO95HV-1^668010/00 7/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
160219841-77530-DTLTRT-10_05_2023-GO95HV-1^668010/00 7/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
371190453-72569-DTLTRT-10_05_2023-GO95HV-1^668010/00 7/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
371190453-72569-DTLTRT-10_05_2023-INSULDMG-2^668010/00 7/029 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-10-05 | 2024-10-05 | 2
511657662-90440-DTLTRT-10_03_2023-GO95HV-1^668010/00 7/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
291173-63040-DTLTRT-10_03_2023-GO95MLD-1^668010/00 7/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
701638575-94269-DTLTRT-10_10_2023-GUYHINS-1^668010/00 7/041 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
955420331-6040-DTLTRT-10_03_2023-GUYNOINS-2^668010/00 7A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
989712101-470-DTLTRT-10_16_2023-GO95HV-1^668010/00 8/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
727934726-82260-DTLTRT-10_09_2023-GUYHINS-1^668010/00 2/039 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
659421095-91269-DTLTRT-10_10_2023-GO95HV-1^668010/00 2/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
659421095-91269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 2/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
659421095-91269-DTLTRT-10_10_2023-INSULDMG-1^668010/00 2/041 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
617226473-85179-DTLTRT-09_27_2023-GUYHINS-1^668010/00 20/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
617226473-85179-DTLTRT-09_27_2023-GUYHINS-2^668010/00 20/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
617226473-85179-DTLTRT-09_27_2023-GUYHINS-3^668010/00 20/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
153297724-96980-DTLTRT-09_27_2023-GUYNOINS-3^668010/00 20/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
200313884-99569-DTLTRT-10_17_2023-GO95HV-1^668010/00 20/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2028-10-17 | 3
200313884-99569-DTLTRT-10_17_2023-GO95MLD-1^668010/00 20/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
200313884-99569-DTLTRT-10_17_2023-SVCDEFLC-1^668010/00 20/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
321130656-4300-DTLTRT-10_24_2023-GUYHINS-2^668010/00 20X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
321130656-4300-DTLTRT-10_24_2023-GUYHINS-3^668010/00 20X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
180077786-58869-DTLTRT-10_18_2023-GO95MLD-1^668010/00 21/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2026-10-18 | 2
180077786-58869-DTLTRT-10_18_2023-GRDRODHI-1^668010/00 21/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2026-10-18 | 2
903964079-73979-DTLTRT-10_30_2023-GO95HV-1^668010/00 21/013 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
663013867-87620-DTLTRT-10_24_2023-GO95HV-1^668010/00 8/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
625419245-21390-DTLTRT-10_31_2023-GO95HV-1^668010/00 8/017 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
494220799-28979-DTLTRT-10_26_2023-GO95HV-1^668010/00 8/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
557031171-47730-DTLTRT-10_05_2023-GO95MLD-1^668010/00 8/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
367169863-59540-DTLTRT-10_04_2023-GO95HV-1^668010/00 8/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2028-10-04 | 3
367169863-59540-DTLTRT-10_04_2023-GO95MLD-1^668010/00 8/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
746638341-97040-DTLTRT-10_03_2023-GO95HV-1^668010/00 8/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
578475572-87579-DTLTRT-10_03_2023-GO95HV-1^668010/00 8/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
883116734-80679-DTLTRT-10_02_2023-SVCROAD-1^668010/00 8/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
281130504-59269-DTLTRT-10_04_2023-GO95HV-1^668010/00 8/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
790324864-82750-DTLTRT-11_03_2023-GO95MLD-1^668010/00 8/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
706197814-3269-DTLTRT-10_11_2023-GUYHINS-1^668010/00 8/040 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
944538756-51169-DTLTRT-10_11_2023-GUYHINS-1^668010/00 8/043 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
943118403-22140-DTLTRT-10_19_2023-GO95HV-1^668010/00 8A/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
943118403-22140-DTLTRT-10_19_2023-GO95MLD-1^668010/00 8A/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
416852571-38730-DTLTRT-10_30_2023-GO95HV-1^668010/00 21/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
753125456-67979-DTLTRT-11_02_2023-GRDRODHI-1^668010/00 21/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
27189926-4000-DTLTRT-10_17_2023-GO95HV-1^668010/00 22X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
27189926-4000-DTLTRT-10_17_2023-GUYHINS-1^668010/00 22X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
466280629-57569-DTLTRT-10_25_2023-GO95MLD-1^668010/00 23/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2026-10-25 | 2
727116676-22400-DTLTRT-10_17_2023-GO95HV-1^668010/00 24X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
17308195-80990-DTLTRT-10_17_2023-CLMBTRE-1^668010/00 25/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
477910389-12430-DTLTRT-10_18_2023-GO95HV-1^668010/00 3/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
776719151-60140-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 8A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
368861862-29769-DTLTRT-10_16_2023-GO95HV-1^668010/00 9/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2028-10-16 | 3
229547814-18880-DTLTRT-09_25_2023-GO95MLD-1^668010/00 9/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2026-09-25 | 2
125096477-44879-DTLTRT-10_24_2023-GO95HV-1^668010/00 9/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
369253856-33479-DTLTRT-11_01_2023-GUYHINS-1^668010/00 9/018 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-01 | 2026-11-01 | 2
673825139-10230-DTLTRT-11_02_2023-GO95HV-1^668010/00 9/023 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
255145251-65140-DTLTRT-10_03_2023-GO95MLD-1^668010/00 9/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
414335954-13180-DTLTRT-10_30_2023-GO95HV-1^668010/00 3/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
56170249-45630-DTLTRT-11_03_2023-GO95HV-1^668010/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
4049971-52240-DTLTRT-10_05_2023-GO95HV-1^668010/00 3/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
906359354-74940-DTLTRT-10_04_2023-INSULDMG-1^668010/00 3/036 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
888304764-24269-DTLTRT-10_11_2023-GO95MLD-1^668010/00 3/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
49277688-56169-DTLTRT-10_10_2023-GUYHINS-1^668010/00 3/045 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
868687563-50480-DTLTRT-09_25_2023-GUYNOINS-1^668010/00 3A/004 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
581221268-84270-DTLTRT-10_10_2023-GUYNOINS-2^668010/00 3A/045 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
193263105-71290-DTLTRT-10_16_2023-GO95HV-1^668010/00 3X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
193263105-71290-DTLTRT-10_16_2023-GO95MLD-1^668010/00 3X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2026-10-16 | 2
193263105-71290-DTLTRT-10_16_2023-RISEGRD-1^668010/00 3X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2026-10-16 | 2
452286508-62120-DTLTRT-10_17_2023-GO95HV-1^668010/00 3X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
685345601-4469-DTLTRT-09_25_2023-GUYHINS-3^668010/00 4/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
124521753-67270-DTLTRT-09_26_2023-GO95HV-1^668010/00 4/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
126277464-71080-DTLTRT-09_27_2023-GO95MLD-1^668010/00 4/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
426097037-95720-DTLTRT-10_24_2023-GO95HV-1^668010/00 4/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
170577034-10940-DTLTRT-10_04_2023-GUYHINS-1^668010/00 9/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
105023984-46850-DETAIL-11_03_2023-GUYHINS-3^668010/00 9/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
607730256-11269-DTLTRT-10_09_2023-GO95MLD-1^668010/00 9/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
54203595-44269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 9/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-1^668010/00 9/041 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-2^668010/00 9/041 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-3^668010/00 9/041 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
978055818-25169-DTLTRT-10_23_2023-GO95HV-1^668010/00 9/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
347794984-74980-DTLTRT-10_31_2023-GO95HV-1^668010/00 4/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
627786866-81400-DTLTRT-11_01_2023-GO95HV-1^668010/00 4/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
122641518-24120-DTLTRT-11_02_2023-GO95HV-1^668010/00 4/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
669753789-6930-DTLTRT-10_26_2023-GO95HV-1^668010/00 4/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
669753789-6930-DTLTRT-10_26_2023-RISEGRD-1^668010/00 4/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
819344349-17730-DTLTRT-10_19_2023-GO95HV-1^668010/00 4/026 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
99537359-79630-DTLTRT-11_03_2023-GO95HV-1^668010/00 4/027 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
945459481-37240-DTLTRT-10_05_2023-GO95HV-1^668010/00 4/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
978055818-25169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 9/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
115894088-87320-DTLTRT-10_17_2023-GO95MLD-1^668010/00 9X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
115894088-87320-DTLTRT-10_17_2023-GRDRODHI-1^668010/00 9X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
139232022-7940-DTLTRT-10_17_2023-GUYNOINS-2^668010/00 9XB/009 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
139232022-7940-DTLTRT-10_17_2023-GUYNOINS-4^668010/00 9XB/009 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
842842629-63300-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/005 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
230540189-94870-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
945459481-37240-DTLTRT-10_05_2023-GO95MLD-1^668010/00 4/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
106479642-39340-DTLTRT-10_03_2023-GO95HV-1^668010/00 4/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
388615603-84569-DTLTRT-10_02_2023-GO95BLTC-1^668010/00 4/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
388615603-84569-DTLTRT-10_02_2023-GO95HV-1^668010/00 4/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
388615603-84569-DTLTRT-10_02_2023-RISEGRD-1^668010/00 4/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
494481684-20240-DTLTRT-10_02_2023-GO95HV-1^668010/00 4/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
475746923-51240-DTLTRT-10_04_2023-GO95BLTC-1^668010/00 4/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
475746923-51240-DTLTRT-10_04_2023-GO95MLD-1^668010/00 4/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
941133984-77469-DTLTRT-10_04_2023-GO95MLD-1^668010/00 4/036 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2028-10-04 | 3
941133984-77469-DTLTRT-10_04_2023-GUYHINS-2^668010/00 4/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
642130396-72360-DTLTRT-10_09_2023-GO95MLD-1^668010/00 4/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
162109935-31269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 4/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
250644526-42169-DTLTRT-10_23_2023-GO95HV-1^668010/00 4/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
250644526-42169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 4/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
2550968-83169-DTLTRT-10_11_2023-GO95HV-1^668010/00 4/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
230540189-94870-DTLTRT-09_29_2020-INSULBRK-1^668018/00 1/007 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2020-09-29 | 2023-09-29 | 2 | B | 2023-01-06 | 2021-09-29 | B | Condition was originally classified as COOTHER, B priority condition with due date of 9/29/2023. Condition was reclassified on 01/06/2023 to INSULDMG, B priority condition via desktop audit; new condition code reduced due date based on type and HFTD Tier;
558777618-31860-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
23011868-58882-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
23011868-63400-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
23011868-72400-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
486856056-96650-DTLTRT-10_01_2020-GO95HV-1^668018/00 11/001 | OTHER | CA-TIER-2 | Transmission | 2020-10-01 | 2025-10-01 | 3
725004818-91860-DTLTRT-09_30_2020-GO95HV-1^668018/00 11/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
868454798-63114-DETAIL-05_26_2022-GO95HV-1^668018/00 11/003 | OTHER | CA-TIER-2 | Transmission | 2022-05-26 | 2027-05-26 | 3
835152229-50680-DETAIL-09_29_2020-GO95HV-1^668018/00 11/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
946379528-23860-DTLTRT-09_30_2020-GO95HV-1^668018/00 12/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
36843439-61679-DETAIL-09_29_2020-GO95HV-1^668018/00 12/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
125987169-62870-DTLTRT-09_29_2020-GO95HV-1^668018/00 16/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
107576178-54609-DTLTRT-09_30_2020-GO95HV-1^668018/00 2/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
192941739-51000-DETAIL-09_29_2020-ANCHIDLE-1^668018/00 2/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2020-09-29 | 2023-09-29 | 2
192941739-1000-DTLTRT-09_29_2020-GO95HV-1^668018/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
192941739-51000-DETAIL-09_29_2020-GO95HV-1^668018/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
968216199-14000-DETAIL-09_29_2020-GO95HV-1^668018/00 2/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
968216199-72879-DETAIL-09_29_2020-GO95HV-1^668018/00 2/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
632580298-66390-DTLTRT-09_30_2020-GO95HV-1^668018/00 3/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
250146279-35520-DTLTRT-09_30_2020-GO95HV-1^668018/00 5/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
250146279-74520-DTLTRT-09_30_2020-GO95HV-1^668018/00 5/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
346078518-43170-DTLTRT-09_30_2020-GO95HV-1^668018/00 6/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
2550968-83169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 4/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
256281698-36169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 4/045 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
120980001-51970-DTLTRT-09_25_2023-GUYNOINS-1^668010/00 4A/001 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
320642394-17150-DTLTRT-10_04_2023-GO95MLD-1^668010/00 4A/036 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
405037321-27469-DTLTRT-09_25_2023-GRDRODHI-2^668010/00 5/001 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
572941493-22209-DTLTRT-09_25_2023-GUYHINS-1^668010/00 5/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
572941493-22209-DTLTRT-09_25_2023-GUYHINS-2^668010/00 5/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
630378283-98869-DTLTRT-09_25_2023-ANCHIDLE-1^668010/00 5/004 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
309191928-56800-DTLTRT-11_02_2023-GUYHINS-1^668010/00 5/020 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
473294059-13730-DTLTRT-10_26_2023-GO95HV-1^668010/00 5/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
889136179-32579-DTLTRT-10_19_2023-GO95HV-1^668010/00 5/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
981374259-99769-DTLTRT-10_19_2023-GO95MLD-1^668010/00 5/026 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
784289501-18730-DTLTRT-10_04_2023-GO95HV-1^668010/00 5/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2028-10-04 | 3
478742443-54879-DTLTRT-10_03_2023-GO95MLD-1^668010/00 5/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
478742443-54879-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 5/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
21313983-29579-DTLTRT-10_02_2023-GO95HV-1^668010/00 5/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
233481279-95670-DETAIL-09_29_2020-GO95HV-1^668018/00 6/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
364780888-28870-DTLTRT-09_30_2020-GO95HV-1^668018/00 7/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
944267718-4170-DTLTRT-09_30_2020-GO95HV-1^668018/00 7/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
260352998-76760-DTLTRT-09_30_2020-GO95HV-1^668018/00 8/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
272573908-97760-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
675253539-55500-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
923386709-51679-DETAIL-09_29_2020-GO95HV-1^668018/00 9/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
708555291-35570-DTLTRT-11_16_2022-GO95HV-1^668026/02 2/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
708555291-35570-DTLTRT-11_16_2022-GUYNOINS-1^668026/02 2/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
881115190-29669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 1/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-11 | 2028-10-11 | 3
224883036-33131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
224883036-5960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
378850066-24880-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
524825426-92279-DRONE_HY-09_26_2023-GO95HV-1^668033/00 10/002 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
813037370-38669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 10/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-11 | 2028-10-11 | 3
296134458-34279-DRONE_HY-09_28_2023-GO95HV-1^668033/00 11/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-28 | 2028-09-28 | 3
170451253-29669-DTLTRT-10_04_2023-GO95MLD-1^668010/00 5/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
190819614-1450-DTLTRT-11_03_2023-GO95HV-1^668010/00 5/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
393995066-63660-DTLTRT-10_09_2023-GO95HV-1^668010/00 5/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
393995066-63660-DTLTRT-10_09_2023-GO95MLD-1^668010/00 5/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
458520984-14269-DTLTRT-10_11_2023-GO95MLD-1^668010/00 5/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
743671136-22169-DTLTRT-10_23_2023-GO95HV-1^668010/00 5/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
106456795-26590-DTLTRT-09_27_2023-RISEGRD-1^668010/00 5X/008 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
438039618-35120-DTLTRT-10_17_2023-GUYHINS-1^668010/00 5X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
964343990-98669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 12/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-11 | 2028-10-11 | 3
972278754-81569-DRONE_HY-10_12_2023-XARMSPCR-1^668033/00 12/023 | CROSSARM | CA-TIER-2 | Transmission | 2023-10-12 | 2024-10-12 | 2
59934178-36869-DRONE_HY-09_29_2023-GO95HV-1^668033/00 14/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-29 | 2028-09-29 | 3
90384273-83649-DRONE_HY-10_17_2023-GO95HV-1^668033/00 14/037 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
575191478-40070-DRONE_HY-09_28_2023-GO95HV-1^668033/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-28 | 2028-09-28 | 3
681354739-15379-DRONE_HY-10_16_2023-GO95HV-1^668033/00 2/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
541618446-77960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
16689319-91415-DRONE_HY-11_03_2023-GO95HV-1^668033/00 2X/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
532543651-20569-DRONE_HY-10_13_2023-GO95HV-1^668033/00 3/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-13 | 2028-10-13 | 3
679514901-65569-DRONE_HY-10_06_2023-GO95HV-1^668033/00 4/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-06 | 2028-10-06 | 3
621985754-2980-DRONE_HY-10_18_2023-GO95HV-1^668033/00 4/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
606249279-93330-DRONE_HY-11_13_2023-GO95HV-1^668033/00 4/030 | OTHER | CA-TIER-2 | Transmission | 2023-11-13 | 2028-11-13 | 3
863978670-27930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 4/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
626571-56730-DRONE_HY-10_26_2023-GO95HV-1^668033/00 4/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
785734006-34931-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
785734006-63931-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
422398605-18079-DTLTRT-10_24_2023-GO95MLD-1^668010/00 6/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
784749416-31990-DTLTRT-11_01_2023-GO95MLD-1^668010/00 6/010 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2026-11-01 | 2
890850136-22479-DTLTRT-11_01_2023-GO95HV-1^668010/00 6/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
21572199-830-DTLTRT-10_19_2023-GO95HV-1^668010/00 6/024 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2028-10-19 | 3
210848343-52540-DTLTRT-10_05_2023-GO95MLD-1^668010/00 6/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
264249911-14930-DTLTRT-10_03_2023-GO95HV-1^668010/00 6/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
779773513-49579-DTLTRT-10_02_2023-GO95HV-1^668010/00 6/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
79694563-75440-DTLTRT-10_04_2023-GO95HV-1^668010/00 6/035 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
976385534-22669-DTLTRT-11_03_2023-GO95HV-1^668010/00 6/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
976385534-22669-DTLTRT-11_03_2023-GO95MLD-1^668010/00 6/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
493398785-44369-DTLTRT-10_10_2023-GO95HV-1^668010/00 6/037 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
694413976-57179-DTLTRT-10_09_2023-GO95HV-1^668010/00 6/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
441753055-25269-DTLTRT-10_10_2023-GUYHINS-1^668010/00 6/041 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
680424536-91169-DTLTRT-10_23_2023-GO95HV-1^668010/00 6/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
680424536-91169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 6/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
543919678-95169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 6/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
543919678-95169-DTLTRT-10_11_2023-GRDRODHI-1^668010/00 6/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
385597165-63160-DTLTRT-11_03_2023-GUYNOINS-1^668010/00 6A/041 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
196963848-44220-DTLTRT-10_17_2023-GO95HV-1^668010/00 6X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
8616422-26379-DTLTRT-09_25_2023-GO95MLD-1^668010/00 7/002 | OTHER | CA-NON-TIER | Transmission | 2023-09-25 | 2026-09-25 | 2
601415679-63930-DTLTRT-10_19_2023-GO95MLD-1^668010/00 7/026 | OTHER | CA-NON-TIER | Transmission | 2023-10-19 | 2026-10-19 | 2
160219841-77530-DTLTRT-10_05_2023-GO95MLD-1^668010/00 7/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
371190453-72569-DTLTRT-10_05_2023-INSULDMG-1^668010/00 7/029 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-10-05 | 2024-10-05 | 2
488321221-37579-DTLTRT-10_03_2023-GUYHINS-1^668010/00 7/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
511657662-90440-DTLTRT-10_03_2023-GO95MLD-1^668010/00 7/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
291173-63040-DTLTRT-10_03_2023-GO95HV-1^668010/00 7/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
41808286-760-DTLTRT-10_09_2023-GO95HV-1^668010/00 7/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
41808286-760-DTLTRT-10_09_2023-GO95MLD-1^668010/00 7/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
41808286-760-DTLTRT-10_09_2023-UBPBCTGD-1^668010/00 7/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
90730026-10460-DTLTRT-10_09_2023-GO95MLD-1^668010/00 7/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
546150346-71169-DTLTRT-10_23_2023-GO95HV-1^668010/00 7/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
612491893-2369-DRONE_HY-11_15_2023-GO95HV-1^668033/00 5/035 | OTHER | CA-TIER-2 | Transmission | 2023-11-15 | 2028-11-15 | 3
550542026-82080-DRONE_HY-11_10_2023-GO95HV-1^668033/00 5/048 | OTHER | CA-TIER-2 | Transmission | 2023-11-10 | 2028-11-10 | 3
550542026-83080-DRONE_HY-11_10_2023-GO95HV-1^668033/00 5/048 | OTHER | CA-TIER-2 | Transmission | 2023-11-10 | 2028-11-10 | 3
150347940-64670-DRONE_HY-10_18_2023-GO95HV-1^668033/00 6/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
688257588-77260-DRONE_HY-10_16_2023-GO95HV-1^668033/00 9/003 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
281183823-2970-DRONE_HY-10_10_2023-GO95HV-1^668033/00 9/018 | OTHER | CA-TIER-2 | Transmission | 2023-10-10 | 2028-10-10 | 3
299499755-81869-DRONE_HY-10_17_2023-GO95HV-1^668033/00 9/040 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
476848521-28930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 9A/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
388956747-98919-ENHANCED-06_21_2022-IRSPOTOH-1^668036/00 1/036 | OTHER | CA-NON-TIER | Transmission | 2022-06-21 | 2025-06-21 | 2
751904989-7419-ADMIN-11_21_2022-POLEDERP-1^668036/00 12/045 | POLE | CA-TIER-2 | Transmission | 2022-11-21 | 2023-11-21 | 2
751904989-7419-ADMIN-11_21_2022-POLEDERP-2^668036/00 12/045 | POLE | CA-TIER-2 | Transmission | 2022-11-21 | 2023-11-21 | 2
220562058-66719-DETAIL-08_14_2023-POLETOP-1^668036/00 8/050 | POLE | CA-TIER-2 | Transmission | 2023-08-14 | 2024-08-14 | 2
832028220-68069-DTLTRT-06_01_2021-GO95MLD-1^668041/00 1/002 | OTHER | CA-NON-TIER | Transmission | 2021-06-01 | 2024-06-01 | 2
319858993-4769-ADMIN-01_16_2019-POLEDERP-2^668041/00 1/011 | POLE | CA-NON-TIER | Transmission | 2019-01-16 | 2023-12-16 | 2
955420331-6040-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 7A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
745205933-91321-DTLTRT-09_26_2023-GO95HV-1^668010/00 8/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
307611124-11480-DTLTRT-09_27_2023-GO95MLD-1^668010/00 8/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
702760978-77569-DTLTRT-10_18_2023-GO95HV-1^668010/00 8/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
846583268-49800-DETAIL-11_02_2023-GUYHINS-1^668010/00 8/020 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
650234950-71830-DTLTRT-11_03_2023-GO95HV-1^668010/00 8/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
650234950-71830-DTLTRT-11_03_2023-GO95MLD-1^668010/00 8/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
650234950-71830-DTLTRT-11_03_2023-GRDRODHI-1^668010/00 8/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
746638341-97040-DTLTRT-10_03_2023-GUYHINS-1^668010/00 8/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
982169336-65460-DTLTRT-10_09_2023-GO95HV-1^668010/00 8/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
706197814-3269-ADMIN-10_11_2023-GO95MLD-1^668010/00 8/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
732020895-74269-DTLTRT-10_10_2023-GO95HV-1^668010/00 8/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
732020895-74269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 8/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
785883256-30169-DTLTRT-10_12_2023-GO95MLD-1^668010/00 8/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
944538756-51169-DTLTRT-10_11_2023-GO95HV-1^668010/00 8/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
79025024-64234-DTLTRT-06_08_2021-GO95HV-1^668041/00 1/014 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
719327068-16159-DTLTRT-06_09_2021-INSULBRK-1^668041/00 1/017 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
719327068-16159-DTLTRT-06_09_2021-UBPBCTGD-1^668041/00 1/017 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
558214470-16221-DTLTRT-06_15_2021-GO95HV-1^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
558214470-16221-DTLTRT-06_15_2021-GO95MLD-2^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
558214470-16221-DTLTRT-06_15_2021-GRDRODHI-1^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
927688224-86869-ADMIN-06_18_2021-POLEDERP-1^668041/00 10/012 | POLE | CA-NON-TIER | Transmission | 2021-06-18 | 2024-06-18 | 2
944538756-51169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 8/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
481324011-90470-DTLTRT-10_16_2023-UBPBCTGD-1^668010/00 9/001 | OTHER | CA-NON-TIER | Transmission | 2023-10-16 | 2026-10-16 | 2
930679463-67421-DTLTRT-09_26_2023-GO95MLD-1^668010/00 9/003 | OTHER | CA-NON-TIER | Transmission | 2023-09-26 | 2026-09-26 | 2
229547814-18880-DTLTRT-09_25_2023-GO95HV-1^668010/00 9/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2028-09-25 | 3
124332333-76280-DTLTRT-09_27_2023-GO95HV-1^668010/00 9/006 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
342560234-42580-DTLTRT-09_27_2023-GO95MLD-1^668010/00 9/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
460738598-98430-DTLTRT-10_18_2023-GO95HV-1^668010/00 9/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
460738598-98430-DTLTRT-10_18_2023-GO95MLD-1^668010/00 9/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2026-10-18 | 2
117392338-36238-DTLTRT-06_08_2021-GO95HV-1^668041/00 10/013 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
130266238-36138-DTLTRT-06_08_2021-GO95HV-1^668041/00 11/013 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
433382260-82169-DTLTRT-06_01_2021-GUYNOINS-1^668041/00 11A/002 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-01 | 2024-06-01 | 2
131148121-36369-DTLTRT-06_02_2021-GO95HV-1^668041/00 12/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
175759948-6848-DTLTRT-06_08_2021-GO95HV-1^668041/00 12/013 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
490899301-13469-DTLTRT-06_16_2021-GUYNOINS-1^668041/00 12/023 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-16 | 2024-06-16 | 2
672390424-37841-ADMIN-02_26_2021-COPLLEAN-1^668041/00 12/028 | POLE | CA-NON-TIER | Transmission | 2021-02-26 | 2024-02-26 | 2
150653365-98790-DTLTRT-10_31_2023-GO95HV-1^668010/00 9/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
928080258-99479-DTLTRT-10_26_2023-GO95MLD-1^668010/00 9/021 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
604489309-15030-DTLTRT-10_26_2023-GO95HV-1^668010/00 9/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
427078643-94340-DTLTRT-10_02_2023-GO95HV-1^668010/00 9/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
105023984-46850-DETAIL-11_03_2023-GUYHINS-1^668010/00 9/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
105023984-46850-DETAIL-11_03_2023-GUYHINS-2^668010/00 9/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
309340196-1860-DTLTRT-10_09_2023-GO95MLD-1^668010/00 9/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
607730256-11269-DTLTRT-10_09_2023-GO95HV-1^668010/00 9/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
49478444-96150-DTLTRT-10_11_2023-GO95HV-1^668010/00 9/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
49478444-96150-DTLTRT-10_11_2023-GUYHINS-1^668010/00 9/040 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
658178398-7069-DTLTRT-10_11_2023-GO95HV-1^668010/00 9/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
978055818-25169-DTLTRT-10_23_2023-UBPBXARM-1^668010/00 9/044 | CROSSARM | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
838686523-47140-DTLTRT-10_19_2023-GUYNOINS-1^668010/00 9A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
115894088-87320-DTLTRT-10_17_2023-GRDRODHI-2^668010/00 9X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
363578602-24940-DTLTRT-10_17_2023-INSULDMG-1^668010/00 9XA/009 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
569346528-81069-ADMIN-12_12_2023-POLEREPL-1^668041/00 14/014 | POLE | CA-NON-TIER | Transmission | 2023-12-12 | 2026-12-12 | 2
598214343-4259-DTLTRT-06_07_2021-GO95MLD-2^668041/00 15/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2024-06-07 | 2
629376684-59869-DTLTRT-06_07_2021-GO95HV-1^668041/00 16/012 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
15979660-74369-DTLTRT-06_15_2021-GO95HV-1^668041/00 16/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
646739609-41969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 17/017 | POLE | CA-NON-TIER | Transmission | 2021-02-24 | 2024-02-24 | 2
20965819-71969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 18/017 | POLE | CA-NON-TIER | Transmission | 2021-02-24 | 2024-02-24 | 2
214964603-54769-ADMIN-01_07_2021-POLEDERP-1^668041/00 2/011 | POLE | CA-NON-TIER | Transmission | 2021-01-07 | 2024-01-07 | 2
594767444-31969-ADMIN-08_11_2019-POLEDERP-1^668041/00 2/013 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
585509378-39069-DTLTRT-06_09_2021-ANCHIDLE-1^668041/00 2/016 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
767639029-32969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 2/018 | POLE | CA-NON-TIER | Transmission | 2021-02-24 | 2024-02-24 | 2
486945200-76369-DTLTRT-06_15_2021-GO95HV-1^668041/00 20/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
522468519-78959-DTLTRT-06_01_2021-GO95HV-1^668041/00 3/001 | OTHER | CA-NON-TIER | Transmission | 2021-06-01 | 2026-06-01 | 3
522468519-78959-DTLTRT-06_01_2021-GO95MLD-1^668041/00 3/001 | OTHER | CA-NON-TIER | Transmission | 2021-06-01 | 2024-06-01 | 2
583902501-28369-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/006 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
272157782-3569-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
221349033-38669-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
347686913-94769-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
640047254-61969-ADMIN-08_11_2019-POLEDERP-1^668041/00 3/013 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
35153213-54259-DTLTRT-06_17_2021-GO95MLD-1^668041/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2021-06-17 | 2024-06-17 | 2
856429770-66269-DTLTRT-06_02_2021-GO95HV-1^668041/00 5/004 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
708016031-82159-DTLTRT-06_03_2021-GO95HV-1^668041/00 5/006 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
139232022-7940-DTLTRT-10_17_2023-GUYNOINS-1^668010/00 9XB/009 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
139232022-7940-DTLTRT-10_17_2023-GUYNOINS-3^668010/00 9XB/009 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
680169628-76360-DETAIL-03_03_2020-GRDSHDBK-1^668014/00 7/053 | OTHER | CA-TIER-3 | Transmission | 2020-03-03 | 2025-03-03 | 3
237364878-89960-DTLTRT-09_30_2020-GO95HV-1^668018/00 1/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
842842629-44300-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/005 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
230540189-78300-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
868454798-67594-DETAIL-05_26_2022-GO95HV-1^668018/00 11/003 | OTHER | CA-TIER-2 | Transmission | 2022-05-26 | 2027-05-26 | 3
835152229-50680-DETAIL-09_29_2020-GUYHINS-1^668018/00 11/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2020-09-29 | 2023-09-29 | 2
609110749-37770-DETAIL-09_29_2020-GO95HV-1^668018/00 13/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
905731499-32970-DTLTRT-09_29_2020-GO95HV-1^668018/00 16/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
192941739-1000-DTLTRT-09_29_2020-ANCHIDLE-1^668018/00 2/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2020-09-29 | 2023-09-29 | 2
875477510-68870-DTLTRT-09_29_2020-GO95HV-1^668018/00 4/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
40070728-12760-DTLTRT-09_30_2020-GO95HV-1^668018/00 8/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
40070728-12760-DTLTRT-09_30_2020-POLETOP-1^668018/00 8/003 | POLE | CA-TIER-2 | Transmission | 2020-09-30 | 2023-09-30 | 2
378571548-97620-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
708016031-82159-DTLTRT-06_03_2021-UNIGRDSG-1^668041/00 5/006 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2024-06-03 | 2
363765761-35469-DTLTRT-06_03_2021-GO95HV-1^668041/00 5/007 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
39784913-21669-DTLTRT-06_04_2021-GO95HV-1^668041/00 5/009 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
680106823-46769-DTLTRT-06_07_2021-GO95HV-1^668041/00 5/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
564141538-94688-DTLTRT-06_08_2021-UBBRACE-1^668041/00 5/013 | CROSSARM | CA-NON-TIER | Transmission | 2021-06-08 | 2024-06-08 | 2
567325788-169-DTLTRT-06_10_2021-ANCHIDLE-1^668041/00 5/016 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-10 | 2024-06-10 | 2
760158388-19869-ADMIN-04_13_2021-COPLLEAN-1^668041/00 5/017 | POLE | CA-NON-TIER | Transmission | 2021-04-13 | 2024-04-13 | 2
214249139-65169-DTLTRT-06_10_2021-GO95HV-1^668041/00 5/018 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
382193809-2269-DTLTRT-06_14_2021-GO95HV-1^668041/00 5/021 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
396064621-9881-DTLTRT-06_15_2021-GO95HV-1^668041/00 5/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
325731043-19870-ADMIN-02_17_2022-INSULDMG-1^668041/00 5/027 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-17 | 2025-02-17 | 2
557184444-43951-DTLTRT-06_21_2021-GO95HV-1^668041/00 5/028 | OTHER | CA-NON-TIER | Transmission | 2021-06-21 | 2026-06-21 | 3
557184444-43951-ADMIN-02_01_2022-POLEDERP-1^668041/00 5/028 | POLE | CA-NON-TIER | Transmission | 2022-02-01 | 2025-02-01 | 2
690692741-72369-DTLTRT-06_02_2021-GO95HV-1^668041/00 6/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
94706741-9369-DTLTRT-06_03_2021-GO95MLD-1^668041/00 6/006 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2024-06-03 | 2
184279808-46069-DTLTRT-06_10_2021-GO95HV-1^668041/00 6/015 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
257059733-25490-ADMIN-02_26_2021-INSULDMG-1^668041/00 6/026 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-02-26 | 2024-02-26 | 2
891309443-48392-ADMIN-02_17_2022-INSULDMG-1^668041/00 6/027 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-17 | 2025-02-17 | 2
449197054-98601-DTLTRT-06_21_2021-GO95HV-1^668041/00 6/028 | OTHER | CA-NON-TIER | Transmission | 2021-06-21 | 2026-06-21 | 3
449197054-98601-ADMIN-02_01_2022-POLEDERP-1^668041/00 6/028 | POLE | CA-NON-TIER | Transmission | 2022-02-01 | 2025-02-01 | 2
849012669-69-DTLTRT-06_01_2021-GO95MLD-1^668041/00 7/001 | OTHER | CA-NON-TIER | Transmission | 2021-06-01 | 2024-06-01 | 2
71828990-67269-DTLTRT-06_02_2021-GO95HV-1^668041/00 7/004 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
610116518-72869-DTLTRT-06_10_2021-GO95HV-1^668041/00 7/015 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
211573643-96259-ADMIN-02_26_2021-INSULDMG-1^668041/00 7/026 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-02-26 | 2024-02-26 | 2
15244453-63889-ADMIN-02_17_2022-INSULDMG-1^668041/00 7/027 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-17 | 2025-02-17 | 2
784898612-62742-DTLTRT-06_22_2021-LIGHT-1^668041/00 7/030 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2021-06-22 | 2024-06-22 | 2
799259371-4369-DTLTRT-06_02_2021-GO95HV-1^668041/00 8/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
675253539-25500-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
576087181-15570-DETAIL-11_16_2022-GUYNOINS-1^668026/01 2/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
576087181-15570-DETAIL-11_16_2022-GUYNOINS-2^668026/01 2/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
224883036-3131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
378850066-29060-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
378850066-53880-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
156252576-83540-DRONE_HY-10_25_2023-GO95HV-1^668033/00 10/001 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
524825426-92279-DRONE_HY-10_16_2023-GO95HV-1^668033/00 10/002 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
994584355-4869-DRONE_HY-10_17_2023-GO95HV-1^668033/00 11/039 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
972278754-81569-DRONE_HY-10_12_2023-GO95HV-1^668033/00 12/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
474687708-67760-DRONE_HY-10_18_2023-GO95HV-1^668033/00 15/004 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
541618446-22331-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
541618446-72331-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
222965188-5279-DRONE_HY-09_29_2023-GO95HV-1^668033/00 3/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-29 | 2028-09-29 | 3
421127660-35930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 3/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
679514901-75570-DRONE_HY-10_06_2023-GO95HV-1^668033/00 4/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-06 | 2028-10-06 | 3
47127222-94569-DTLTRT-06_04_2021-GO95HV-1^668041/00 8/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
586716214-95869-ADMIN-06_18_2021-POLEDERP-1^668041/00 8/012 | POLE | CA-NON-TIER | Transmission | 2021-06-18 | 2024-06-18 | 2
714032839-43669-DTLTRT-06_09_2021-GO95HV-1^668041/00 8/014 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
225587959-85169-DTLTRT-06_10_2021-GO95HV-1^668041/00 8/018 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
271330629-16069-DTLTRT-06_14_2021-GO95HV-1^668041/00 8/021 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
745032589-49859-DTLTRT-06_01_2021-GO95MLD-1^668041/00 9/001 | OTHER | CA-NON-TIER | Transmission | 2021-06-01 | 2024-06-01 | 2
313130691-7469-DTLTRT-06_03_2021-GO95HV-1^668041/00 9/007 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
335700332-35569-DTLTRT-06_04_2021-GO95HV-1^668041/00 9/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
436258503-70769-DTLTRT-06_08_2021-GO95HV-1^668041/00 9/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
626175053-28769-DTLTRT-06_07_2021-GO95HV-1^668041/00 9/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
807645114-26869-ADMIN-06_18_2021-POLEDERP-1^668041/00 9/012 | POLE | CA-NON-TIER | Transmission | 2021-06-18 | 2024-06-18 | 2
589201708-16869-DTLTRT-06_09_2021-GO95HV-1^668041/00 9/016 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
108971580-39355-ADMIN-02_01_2022-INSULDMG-2^668041/00 9/029 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-01 | 2025-02-01 | 2
26122899-79732-DETAIL-11_01_2023-POLEREPL-1^668044/00 1/055 | POLE | CA-TIER-2 | Transmission | 2023-11-01 | 2024-11-01 | 2
26122899-87670-DETAIL-11_01_2023-POLEREPL-1^668044/00 1/055 | POLE | CA-TIER-2 | Transmission | 2023-11-01 | 2024-11-01 | 2
977066209-909-DETAIL-12_21_2022-UBPRMSHD-1^668075/00 1/025 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
795742660-50660-DTLTRT-10_26_2022-GO95MLD-1^668075/00 1/028 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
29337610-77310-DETAIL-12_22_2022-UBPRMSHD-1^668075/00 10/026 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2022-12-22 | 2025-12-22 | 2
87604999-35399-DTLTRT-10_25_2022-GO95HV-1^668075/00 11/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
87604999-35399-DTLTRT-10_25_2022-GO95MLD-1^668075/00 11/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
87609620-46120-DTLTRT-11_16_2022-GO95HV-1^668075/00 11/026 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2027-11-16 | 3
915656899-42609-DTLTRT-10_25_2022-GO95HV-1^668075/00 12/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
53105629-78329-DTLTRT-10_25_2022-GO95HV-1^668075/00 13/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
521472210-78110-DTLTRT-11_16_2022-UBPBCTGD-1^668075/00 13/026 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2025-11-16 | 2
521472210-78110-DETAIL-12_22_2022-GRDRODHI-1^668075/00 13/026 | OTHER | CA-NON-TIER | Transmission | 2022-12-22 | 2025-12-22 | 2
505398239-86639-DTLTRT-10_25_2022-GO95MLD-1^668075/00 15/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
973216199-14099-DTLTRT-10_25_2022-GO95MLD-1^668075/00 17/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
689443434-26280-DRONE_HY-10_18_2023-GO95HV-1^668033/00 4/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
520611664-29040-DRONE_HY-10_27_2023-GO95HV-1^668033/00 4/037 | OTHER | CA-TIER-2 | Transmission | 2023-10-27 | 2028-10-27 | 3
877301966-24660-DRONE_HY-10_12_2023-GUYSLACK-1^668033/00 4/044 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-12 | 2024-10-12 | 2
877301966-39831-DRONE_HY-10_12_2023-GUYSLACK-1^668033/00 4/044 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-12 | 2024-10-12 | 2
877301966-931-DRONE_HY-10_12_2023-GUYSLACK-1^668033/00 4/044 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-12 | 2024-10-12 | 2
785734006-91860-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
726458001-35569-DRONE_HY-10_06_2023-GO95HV-1^668033/00 5/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-06 | 2028-10-06 | 3
726458001-35570-DRONE_HY-10_06_2023-GO95HV-1^668033/00 5/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-06 | 2028-10-06 | 3
266529476-10909-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/044 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
266529476-68131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/044 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
516804006-32231-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
516804006-53860-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
150347940-64669-DRONE_HY-10_18_2023-GO95HV-1^668033/00 6/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
56941126-43531-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
56941126-91960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
719117230-90730-DETAIL-12_22_2022-UBPRMSHD-1^668075/00 17/026 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2022-12-22 | 2025-12-22 | 2
471250249-22749-DTLTRT-10_25_2022-GO95HV-1^668075/00 18/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
368245249-60749-DETAIL-12_20_2022-GO95TCH-1^668075/00 19/025 | OTHER | CA-NON-TIER | Transmission | 2022-12-20 | 2025-12-20 | 2
866155159-82259-DETAIL-12_22_2022-GUYNOINS-1^668075/00 19A/025 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-12-22 | 2025-12-22 | 2
74403029-59529-DTLTRT-10_25_2022-GO95HV-1^668075/00 2/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
253197140-66540-DTLTRT-11_16_2022-GO95HV-1^668075/00 2/027 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2027-11-16 | 3
846567029-97629-DTLTRT-10_25_2022-GO95MLD-1^668075/00 3/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
56941126-93531-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
110359745-22869-DRONE_HY-10_17_2023-GO95HV-1^668033/00 8/040 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
942001116-52279-DRONE_HY-09_26_2023-GO95HV-1^668033/00 9/002 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
734349136-49920-DRONE_HY-10_12_2023-GO95HV-1^668033/00 9/043 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
734349136-92560-DRONE_HY-10_12_2023-GO95HV-1^668033/00 9/043 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
490156254-99719-ADMIN-04_25_2018-POLEREPL-1^668036/00 10/032 | POLE | CA-NON-TIER | Transmission | 2018-04-25 | 2023-03-25 | 2
257187213-46019-ADMIN-11_10_2020-POLEDERP-1^668036/00 10/055 | POLE | CA-NON-TIER | Transmission | 2020-11-10 | 2023-11-10 | 2
926458488-88119-ADMIN-08_10_2021-XARMSPCR-1^668036/00 11/020 | CROSSARM | CA-NON-TIER | Transmission | 2021-08-10 | 2024-08-10 | 2
682465129-52419-DETAIL-11_14_2023-INSULBRK-1^668036/00 14/044 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-11-14 | 2026-11-14 | 2
5672018-40819-DETAIL-11_14_2023-INSULBRK-1^668036/00 17/050 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-11-14 | 2024-11-14 | 2
573957698-15719-DETAIL-08_14_2023-POLETOP-1^668036/00 5/050 | POLE | CA-TIER-2 | Transmission | 2023-08-14 | 2024-08-14 | 2
707777058-52819-DETAIL-11_14_2023-INSULBRK-1^668036/00 5/051 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-11-14 | 2026-11-14 | 2
135787739-83919-ADMIN-10_28_2022-UBPBXARM-1^668036/00 5/053 | CROSSARM | CA-NON-TIER | Transmission | 2022-10-28 | 2025-10-28 | 2
153330331-9619-DETAIL-08_11_2023-POLEREPL-1^668036/00 6/049 | POLE | CA-TIER-2 | Transmission | 2023-08-11 | 2024-08-11 | 2
259703669-72069-DTLTRT-10_25_2022-GO95HV-1^668075/00 3/026 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
119719140-49540-DTLTRT-11_16_2022-GO95MLD-1^668075/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2025-11-16 | 2
482513970-82470-DTLTRT-10_26_2022-GO95MLD-1^668075/00 4/028 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
250519359-61959-DTLTRT-10_25_2022-GO95HV-1^668075/00 5/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
250519359-61959-DETAIL-12_21_2022-UBPRMSHD-1^668075/00 5/025 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
965660099-6699-DTLTRT-10_25_2022-GO95MLD-1^668075/00 5/026 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
314169180-53580-DTLTRT-10_26_2022-GUYSLACK-1^668075/00 6/028 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
145214479-82079-DTLTRT-10_25_2022-GO95HV-1^668075/00 7/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
145214479-82079-DTLTRT-10_25_2022-GRDRODHI-1^668075/00 7/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
38920300-62800-DTLTRT-10_25_2022-GO95MLD-1^668075/00 7/026 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
307829090-69090-DTLTRT-11_16_2022-GO95MLD-1^668075/00 7/027 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2025-11-16 | 2
395843789-26289-DETAIL-10_25_2022-GUYSLACK-1^668075/00 9/025 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
395843789-26289-DETAIL-10_25_2022-GUYSLACK-2^668075/00 9/025 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
330075365-24919-ADMIN-08_09_2019-TRNSLOOS-1^668078/00 4/002 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2019-08-09 | 2022-08-09 | 2
776395400-58722-DETAIL-04_25_2022-POLEREPL-1^668087/00 6/007 | POLE | CA-NON-TIER | Transmission | 2022-04-25 | 2025-04-25 | 2
262503418-47200-ENHANCED-01_13_2022-IRSPOTOH-1^668087/00 8/002 | OTHER | CA-NON-TIER | Transmission | 2022-01-13 | 2025-01-13 | 2
989459749-40849-ADMIN-08_14_2023-POLEREPL-1^668087/01 3/001 | POLE | CA-NON-TIER | Transmission | 2023-08-14 | 2026-08-14 | 2
262189751-69619-DETAIL-08_11_2023-POLETOP-1^668036/00 8/049 | POLE | CA-TIER-2 | Transmission | 2023-08-11 | 2024-08-11 | 2
601809733-82869-DTLTRT-06_07_2021-GO95HV-1^668041/00 1/012 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
239426058-53069-DTLTRT-06_10_2021-GO95HV-1^668041/00 1/015 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
719327068-16159-DTLTRT-06_09_2021-UNIGRDSG-1^668041/00 1/017 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
28177719-74169-DTLTRT-06_10_2021-GO95HV-1^668041/00 1/018 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
558214470-16221-DTLTRT-06_15_2021-CLRTOUCH-1^668041/00 1/022 | CONDUCTOR | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
558214470-16221-DTLTRT-06_15_2021-GO95MLD-1^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
558214470-16221-DTLTRT-06_15_2021-GRDRODHI-2^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
47640553-68769-DTLTRT-06_07_2021-GO95HV-1^668041/00 10/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
702056718-10969-DTLTRT-06_09_2021-COPLLEAN-1^668041/00 10/017 | POLE | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
407780811-95369-DTLTRT-06_02_2021-GO95HV-1^668041/00 11/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
218153009-33169-DTLTRT-06_01_2021-GUYNOINS-1^668041/00 11B/002 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-01 | 2024-06-01 | 2
758352138-27069-ADMIN-01_31_2023-POLEDERP-1^668041/00 12/015 | POLE | CA-NON-TIER | Transmission | 2023-01-31 | 2026-01-31 | 2
673344589-60069-DTLTRT-06_14_2021-GO95HV-1^668041/00 12/019 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
490899301-13469-DTLTRT-06_16_2021-GUYNOINS-2^668041/00 12/023 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-16 | 2024-06-16 | 2
700216310-42269-DTLTRT-06_02_2021-GO95HV-1^668041/00 13/003 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
403724939-21269-DTLTRT-06_14_2021-GO95HV-1^668041/00 13/020 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
909315933-33769-ADMIN-04_16_2019-POLEDERP-1^668041/00 14/010 | POLE | CA-NON-TIER | Transmission | 2019-04-16 | 2024-03-16 | 2
551396564-68869-DTLTRT-06_07_2021-GO95HV-1^668041/00 14/012 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
664626469-41269-DTLTRT-06_14_2021-GO95HV-1^668041/00 14/020 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
598214343-4259-ADMIN-04_16_2019-POLEDERP-1^668041/00 15/010 | POLE | CA-NON-TIER | Transmission | 2019-04-16 | 2024-03-16 | 2
598214343-4259-DTLTRT-06_07_2021-GO95BLTC-1^668041/00 15/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
598214343-4259-DTLTRT-06_07_2021-GO95MLD-1^668041/00 15/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2024-06-07 | 2
598214343-4259-DTLTRT-06_07_2021-GUYLOINS-1^668041/00 15/010 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-07 | 2024-06-07 | 2
62308650-14369-DTLTRT-06_15_2021-GO95HV-1^668041/00 15/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
263980893-70369-DTLTRT-06_23_2021-COPLLEAN-1^668041/00 15/032 | POLE | CA-NON-TIER | Transmission | 2021-06-23 | 2024-06-23 | 2
172029423-91869-DTLTRT-06_07_2021-GO95HV-1^668041/00 16/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
188461738-82069-DTLTRT-06_10_2021-ANCHIDLE-1^668041/00 16/014 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-10 | 2024-06-10 | 2
385004123-52869-DTLTRT-06_07_2021-GO95HV-1^668041/00 17/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
564523158-75858-ADMIN-10_22_2020-POLEDERP-1^668041/00 17/013 | POLE | CA-NON-TIER | Transmission | 2020-10-22 | 2023-10-22 | 2
509183170-15369-DTLTRT-06_15_2021-GO95HV-1^668041/00 17/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
214964603-54769-ADMIN-01_07_2021-POLEDERP-2^668041/00 2/011 | POLE | CA-NON-TIER | Transmission | 2021-01-07 | 2024-01-07 | 2
105220633-33869-ADMIN-06_18_2021-POLEDERP-1^668041/00 2/012 | POLE | CA-NON-TIER | Transmission | 2021-06-18 | 2024-06-18 | 2
594767444-31969-DTLTRT-06_08_2021-GO95HV-1^668041/00 2/013 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
585509378-39069-DTLTRT-06_09_2021-GO95HV-1^668041/00 2/016 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
350441839-9169-DTLTRT-06_14_2021-GO95HV-1^668041/00 2/020 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
889134000-17369-DTLTRT-06_15_2021-GO95HV-1^668041/00 21/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
36328941-64469-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/007 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
553642103-20669-DTLTRT-06_04_2021-GO95HV-1^668041/00 3/009 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
50345243-93869-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/012 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
819562788-74069-ADMIN-07_24_2020-POLEDERP-1^668041/00 3/015 | POLE | CA-NON-TIER | Transmission | 2020-07-24 | 2023-07-24 | 2
240178078-94869-DTLTRT-06_10_2021-GO95HV-1^668041/00 3/016 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
35153213-54259-DTLTRT-06_17_2021-GO95HV-1^668041/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2021-06-17 | 2026-06-17 | 3
35153213-54259-DTLTRT-06_17_2021-SVCROAD-1^668041/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2021-06-17 | 2024-06-17 | 2
770328001-91369-DTLTRT-06_02_2021-GO95HV-1^668041/00 4/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
470877513-75769-DTLTRT-06_07_2021-GO95HV-1^668041/00 4/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
229398153-44869-ADMIN-06_18_2021-POLEDERP-1^668041/00 4/012 | POLE | CA-NON-TIER | Transmission | 2021-06-18 | 2024-06-18 | 2
293953728-4978-ADMIN-08_11_2019-POLEDERP-1^668041/00 4/013 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
327581721-18681-ADMIN-03_03_2021-UBBRACE-1^668041/00 4/022 | CROSSARM | CA-NON-TIER | Transmission | 2021-03-03 | 2024-03-03 | 2
708016031-82159-DTLTRT-06_03_2021-GO95MLD-1^668041/00 5/006 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2024-06-03 | 2
438432192-93569-DTLTRT-06_04_2021-GO95HV-1^668041/00 5/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
529581263-94869-ADMIN-06_18_2021-POLEDERP-1^668041/00 5/012 | POLE | CA-NON-TIER | Transmission | 2021-06-18 | 2024-06-18 | 2
564141538-94688-ADMIN-08_11_2019-POLEDERP-1^668041/00 5/013 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
749648829-60769-DTLTRT-06_08_2021-GO95HV-1^668041/00 5/014 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
719280998-6069-ADMIN-07_24_2020-POLEDERP-1^668041/00 5/015 | POLE | CA-NON-TIER | Transmission | 2020-07-24 | 2023-07-24 | 2
567325788-169-DTLTRT-06_10_2021-GO95HV-1^668041/00 5/016 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
449795833-84669-DTLTRT-06_23_2021-GO95MLD-1^668041/00 5/032 | OTHER | CA-NON-TIER | Transmission | 2021-06-23 | 2024-06-23 | 2
449795833-84669-DTLTRT-06_23_2021-UBPBXARM-1^668041/00 5/032 | CROSSARM | CA-NON-TIER | Transmission | 2021-06-23 | 2024-06-23 | 2
305093502-34569-DTLTRT-06_04_2021-GO95HV-1^668041/00 6/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
734839223-51669-DTLTRT-06_04_2021-GRDRODHI-1^668041/00 6/009 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2024-06-04 | 2
446507549-13969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 6/018 | POLE | CA-NON-TIER | Transmission | 2021-02-24 | 2024-02-24 | 2
703166581-56281-ADMIN-02_18_2022-INSULDMG-1^668041/00 6/022 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-18 | 2025-02-18 | 2
914690043-96269-ADMIN-03_02_2021-COPLLEAN-1^668041/00 6/032 | POLE | CA-NON-TIER | Transmission | 2021-03-02 | 2024-03-02 | 2
776349483-89669-DTLTRT-06_08_2021-GO95HV-1^668041/00 7/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
890862438-3688-DTLTRT-06_08_2021-GO95HV-1^668041/00 7/013 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
598893539-58569-DTLTRT-06_09_2021-GO95HV-1^668041/00 7/014 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
639581401-84161-DTLTRT-06_15_2021-GO95HV-1^668041/00 7/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
361974233-92669-DTLTRT-06_04_2021-GO95HV-1^668041/00 8/009 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
108230228-81588-ADMIN-08_11_2019-POLEDERP-1^668041/00 8/013 | POLE | CA-NON-TIER | Transmission | 2019-08-11 | 2022-08-11 | 2
648557608-31169-ADMIN-07_24_2020-POLEDERP-1^668041/00 8/016 | POLE | CA-NON-TIER | Transmission | 2020-07-24 | 2023-07-24 | 2
307332918-53869-DTLTRT-06_09_2021-GO95HV-1^668041/00 9/015 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
918451009-83069-DTLTRT-06_14_2021-ANCHIDLE-1^668041/00 9/020 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-14 | 2024-06-14 | 2
918451009-83069-DTLTRT-06_14_2021-GO95HV-1^668041/00 9/020 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
317961201-76161-DTLTRT-06_15_2021-GO95HV-1^668041/00 9/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
108971580-39355-ADMIN-04_05_2021-INSULBRK-1^668041/00 9/029 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-04-05 | 2024-04-05 | 2
492714493-7369-ADMIN-03_02_2021-COPLLEAN-1^668041/00 9/033 | POLE | CA-NON-TIER | Transmission | 2021-03-02 | 2024-03-02 | 2
503209716-8169-DETAIL-05_09_2022-GO95HV-1^668047/00 1/030 | OTHER | CA-TIER-2 | Transmission | 2022-05-09 | 2027-05-09 | 3
744624199-67699-DTLTRT-10_25_2022-GO95HV-1^668075/00 10/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
861430700-25600-DTLTRT-10_26_2022-GUYNOINS-1^668075/00 10A/028 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
748792720-99120-DTLTRT-10_26_2022-GO95MLD-1^668075/00 11/027 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
521472210-78110-DTLTRT-11_16_2022-GO95MLD-1^668075/00 13/026 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2025-11-16 | 2
102455030-77740-DTLTRT-10_26_2022-GO95HV-1^668075/00 13/027 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2027-10-26 | 3
102455030-77740-DTLTRT-10_26_2022-UBPBGYSL-1^668075/00 13/027 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
747865140-87540-DTLTRT-10_26_2022-GO95MLD-1^668075/00 14/027 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
232400513-91023-DTLTRT-10_24_2022-GO95HV-1^668075/00 16/024 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2027-10-24 | 3
807892099-15399-DTLTRT-10_24_2022-GO95HV-1^668075/00 17/024 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2027-10-24 | 3
807892099-15399-DTLTRT-10_24_2022-GO95MLD-1^668075/00 17/024 | OTHER | CA-NON-TIER | Transmission | 2022-10-24 | 2025-10-24 | 2
719117230-90730-DTLTRT-11_16_2022-GO95MLD-1^668075/00 17/026 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2025-11-16 | 2
368245249-60749-DTLTRT-10_25_2022-GO95MLD-1^668075/00 19/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
846567029-97629-DTLTRT-10_25_2022-GO95HV-1^668075/00 3/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
846567029-97629-DETAIL-12_21_2022-GO95BLTC-1^668075/00 3/025 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2027-12-21 | 3
108545959-73859-DTLTRT-10_25_2022-GO95HV-1^668075/00 4/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
804297869-15269-DTLTRT-10_25_2022-GO95HV-1^668075/00 6/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2027-10-25 | 3
314169180-53580-DTLTRT-10_26_2022-UBPBGYSL-1^668075/00 6/028 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-26 | 2025-10-26 | 2
145214479-82079-DTLTRT-10_25_2022-GO95MLD-1^668075/00 7/025 | OTHER | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
38920300-62800-DTLTRT-10_25_2022-UBPRMSHD-1^668075/00 7/026 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
156512980-17780-DETAIL-12_22_2022-GO95HV-1^668075/00 7/028 | OTHER | CA-NON-TIER | Transmission | 2022-12-22 | 2027-12-22 | 3
839259300-23800-DTLTRT-10_26_2022-GO95HV-1^668075/00 8/027 | OTHER | CA-NON-TIER | Transmission | 2022-10-26 | 2027-10-26 | 3
395843789-26289-DETAIL-10_25_2022-GUYHINS-1^668075/00 9/025 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-25 | 2025-10-25 | 2
649455610-69010-DTLTRT-11_16_2022-GO95HV-1^668075/00 9/026 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2027-11-16 | 3
649455610-69010-DTLTRT-11_16_2022-GO95MLD-1^668075/00 9/026 | OTHER | CA-NON-TIER | Transmission | 2022-11-16 | 2025-11-16 | 2
525113935-43919-ADMIN-09_14_2023-POLEREPL-1^668078/00 2/002 | POLE | CA-NON-TIER | Transmission | 2023-09-14 | 2026-09-14 | 2
330075365-24919-ADMIN-08_09_2019-TRNSBOND-1^668078/00 4/002 | OTHER | CA-NON-TIER | Transmission | 2019-08-09 | 2022-08-09 | 2
654854780-10139-ADMIN-04_21_2023-POLEREPL-1^668087/00 3/025 | POLE | CA-NON-TIER | Transmission | 2023-04-21 | 2026-04-21 | 2
235075256-22579-DETAIL-06_05_2023-SVCWIND-1^06243009.0027405 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
143969920-33229-DETAIL-06_05_2023-GO95MLD-1^06243009.0027409 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
665318666-17589-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0027411 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
438063851-68829-DETAIL-06_05_2023-GO95MLD-1^06243009.0027420 | OTHER | CA-NON-TIER | Distribution | 2023-06-05 | 2026-06-05 | 2
511782271-32301-DETAIL-05_31_2023-GO95MLD-1^06243009.0027500 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
511782271-32301-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0027500 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
511782271-32301-DETAIL-05_31_2023-SVCWIND-1^06243009.0027500 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
108878380-44461-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0027501 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
517627043-8269-DTLSB-08_24_2023-GO95MLD-1^06243009.0116900 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
409491520-46060-DTLSB-08_29_2023-GO95MLD-1^06243009.0117201 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
828366986-78189-DTLSB-08_29_2023-GO95TCH-1^06243009.0117401 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
828366986-78189-DTLSB-08_29_2023-SVCDEFLC-1^06243009.0117401 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
632342276-89189-DTLSB-08_29_2023-GO95MLD-1^06243009.0118400 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
961015216-10389-DTLSB-08_24_2023-GO95MLD-1^06243009.0118600 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
545587866-3089-DTLSB-08_24_2023-CLRTOUCH-1^06243009.0118603 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
317356906-58229-DTLSB-08_29_2023-GO95MLD-1^06243009.0119401 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
506209626-94689-DTLSB-08_24_2023-GO95MLD-1^06243009.0119502 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
870207646-28229-DTLSB-08_24_2023-GO95MLD-1^06243009.0119503 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
870207646-28229-DTLSB-08_24_2023-SVCDEFLC-1^06243009.0119503 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
121722166-49229-DTLSB-08_24_2023-SVCDEFLC-1^06243009.0119602 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
654704466-82329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120100 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
806503823-55329-DTLSB-08_29_2023-GO95BLTC-1^06243009.0120101 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
806503823-55329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120101 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
269874560-50861-DETAIL-05_31_2023-CLMBTRE-1^06243009.0027600 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
263018130-29929-DETAIL-05_31_2023-GO95MLD-1^06243009.0027601 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2028-05-31 | 3
293179071-69929-DETAIL-05_31_2023-GO95MLD-1^06243009.0027602 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
474169781-51601-DETAIL-05_31_2023-GO95MLD-1^06243009.0027605 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2028-05-31 | 3
876566711-37231-DETAIL-05_31_2023-SVCROAD-1^06243009.0027606 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
208848291-98929-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0027607 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
132492021-4021-DETAIL-05_31_2023-SVCROAD-1^06243009.0027612 | OTHER | CA-NON-TIER | Distribution | 2023-05-31 | 2026-05-31 | 2
251359638-738-DETAIL-06_01_2023-GO95MLD-1^06243009.0028300 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
485419896-8599-DTLSB-08_29_2023-GO95MLD-1^06243009.0120302 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
441242436-21329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120400 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
478822603-76299-DTLSB-08_29_2023-GO95MLD-1^06243009.0121102 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
161689143-49379-DTLSB-08_29_2023-GO95MLD-1^06243009.0121300 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
514582783-23769-DTLSB-08_29_2023-GO95MLD-1^06243009.0123401 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2026-08-29 | 2
604326763-94329-DTLSB-08_29_2023-GO95MLD-1^06243009.0123503 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2028-08-29 | 3
319769243-679-DTLSB-08_29_2023-GO95MLD-1^06243009.0123504 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2028-08-29 | 3
29301959-85289-DTLSB-08_29_2023-GO95HV-1^06243009.0130900 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
29301959-85289-DTLSB-08_29_2023-GO95STUB-1^06243009.0130900 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
706118169-19029-DTLSB-08_17_2023-GO95MLD-1^06243009.0131002 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
706118169-19029-DTLSB-08_17_2023-SVCDEFLC-1^06243009.0131002 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
300344880-79029-DTLSB-08_17_2023-GO95HV-1^06243009.0131200 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
678147265-98265-DTLSB-08_17_2023-GO95MLD-1^06243009.0131201 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
371132991-26689-DTLSB-08_17_2023-GO95MLD-1^06243009.0131300 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
25090050-1129-DTLSB-08_17_2023-GUYNOINS-1^06243009.0131502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
673747869-75129-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0028302 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
156482028-64889-DETAIL-06_01_2023-GO95MLD-1^06243009.0028303 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
712473389-38821-DETAIL-06_01_2023-GO95MLD-1^06243009.0028401 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
162793106-76129-DETAIL-06_01_2023-GO95MLD-1^06243009.0028402 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
573453608-68399-DETAIL-06_01_2023-GO95HV-1^06243009.0028404 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
990468598-7129-DETAIL-06_01_2023-GUYHINS-1^06243009.0028411 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
672688288-88999-DETAIL-06_01_2023-GRDRODHI-1^06243009.0028412 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
3633766-31969-DETAIL-06_01_2023-GO95HV-1^06243009.0028415 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
413642519-98399-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0028418 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
749709631-58111-DETAIL-06_01_2023-GO95MLD-1^06243009.0028503 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
749709631-58111-DETAIL-06_01_2023-GUYHINS-1^06243009.0028503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
964923401-50611-DETAIL-05_31_2023-GO95HV-1^06243009.0028505 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3
73603850-60129-DTLSB-08_17_2023-GO95MLD-1^06243009.0131503 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
768628189-80129-DTLSB-08_17_2023-GO95MLD-1^06243009.0131600 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
766508810-1309-DTLSB-08_17_2023-GO95MLD-1^06243009.0131602 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
990407171-17882-DTLSB-08_17_2023-GO95HV-1^06243009.0131801 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
281640789-51309-DTLSB-08_17_2023-GO95MLD-1^06243009.0132501 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
704993151-30582-DTLSB-08_23_2023-GO95MLD-1^06243009.0133000 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
803295009-96942-DTLSB-08_23_2023-GO95HV-1^06243009.0133001 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
85408179-68929-DTLSB-08_17_2023-GO95HV-1^06243009.0134500 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
573143809-72209-DTLSB-08_17_2023-GO95HV-1^06243009.0136401 | OTHER | CA-TIER-2 | Distribution | 2023-08-17 | 2028-08-17 | 3
573143809-72209-DTLSB-08_17_2023-GO95MLD-1^06243009.0136401 | OTHER | CA-TIER-2 | Distribution | 2023-08-17 | 2028-08-17 | 3
99310291-94229-DTLSB-08_08_2023-GO95MLD-1^06243009.0140701 | OTHER | CA-NON-TIER | Distribution | 2023-08-08 | 2026-08-08 | 2
687064149-75149-DTLSB-08_10_2023-GO95MLD-1^06243009.0141001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
886707981-49382-DTLSB-09_28_2023-GO95MLD-1^06243009.0147700 | OTHER | CA-NON-TIER | Distribution | 2023-09-28 | 2026-09-28 | 2
886707981-49382-DETAIL-12_22_2023-POLEREPL-1^06243009.0147700 | POLE | CA-NON-TIER | Distribution | 2023-12-22 | 2026-12-22 | 2
852377489-61178-DTLSB-08_10_2023-GO95MLD-1^06243009.0150000 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
961096308-43289-DTLSB-08_09_2023-GO95MLD-1^06243009.0152400 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
964923401-50611-DETAIL-05_31_2023-GO95MLD-1^06243009.0028505 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
811857280-59861-DETAIL-06_01_2023-GO95MLD-1^06243009.0028509 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
35843201-80031-DETAIL-05_31_2023-GO95MLD-1^06243009.0028600 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
759873120-97929-DETAIL-05_30_2023-GO95HV-1^06243009.0028602 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
481834381-26731-DETAIL-05_31_2023-GO95HV-1^06243009.0028605 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3

## Table 14
Utility | PacifiCorp
Table No. | 14
Date Modified
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Non-HFTD Distribution
HFTD 2 Distribution
HFTD 3 Distribution
Non-HFTD Transmission
HFTD 2 Transmission
HFTD 3 Transmission

## Table 15
Utility | PacifiCorp
Table No. | 15
Date Modified
Table 15: Top Risk Circuit Scores
*EC to add all other risk categories to right of last required category.
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS