## Slide 1
Wildfire Mitigation Plan
Quarterly Notification Letter
Initiatives Update
Bear Valley Electric Service, Inc.
Q2 2022
Q1 2023

## Slide 2: WMP Activity Summary
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Not Currently Scheduled*
Situational Awareness & Forecasting
Risk Methodology & Assessment
(*) Not Currently Scheduled – BVES included this Status Icon to indicate where an initiative is not currently identified for this WMP cycle, or, that it is not applicable (BVES does not own or operate assets equal to or greater than 65kV).
Risk Methodology and Assessment
RMA_1
Overview of the Service Territory
Environmental Compliance and Permitting
ST_1
Wildfire Mitigation Strategy Development
Wildfire Mitigation Strategy Development
WMSD_1
Public Outreach and Education Awareness Program
COE_1
Engagement with Access and Functional Needs Populations
COE_2
Collaboration on Local Wildfire Mitigation Planning
COE_3
Best Practice Sharing with Other Utilities
COE_4
Environmental Monitoring Systems
SAF_1
Grid Monitoring Systems
SAF_2
Grid Monitoring Systems
SAF_3
Ignition Detection Systems
SAF_4
Weather Forecasting
SAF_5
Fire Potential Index
SAF_6
Emergency Preparedness
Public Emergency Communication Strategy
EP_3
Customer Support in Wildfire and PSPS Emergencies
EP_5
Preparedness and Planning for Service Restoration
EP_4
Emergency Preparedness Plan
EP_1
External Collaboration and Coordination
EP_2
Community Outreach & Engagement
Vegetation Management & Inspections
Vegetation Inspections
VM_1
Vegetation Inspection
VM_2
Vegetation Inspection
VM_3
Vegetation Inspection
VM_4
Vegetation Inspection
VM_5
Vegetation Inspection
VM_6
Pole Clearing
VM_7
Wood and Slash Management
VM_8
Clearance
VM_9
Fall-In Mitigation
VM_10
Substation Defensible Space
VM_11
High-Risk Species
VM_12
Fire-Resilient Right-of-Ways
VM_13
Emergency Response Vegetation Management
VM_14
Vegetation Management Enterprise System
VM_15
Quality Assurance / Quality Control
VM_16
Open Work Orders
VM_17
Workforce Planning
VM_18

## Slide 3: WMP Activity Summary
On Track
Off Track
Completed/Ongoing
Not Started
Ahead of Plan
Not Currently Scheduled*
Grid Design, Operations & Maintenance
(*) Not Currently Scheduled – BVES included this Status Icon to indicate where an initiative is not currently identified for this WMP cycle, or, that it is not applicable (BVES does not own or operate assets equal to or greater than 65kV).
Covered Conductor Installation
GD_1
Covered Conductor Installation
GD_2
Installation of System Automation Equipment
GD_14
Installation of System Automation Equipment
GD_15
Microgrids
GD_10
Microgrids
GD_11
Installation of System Automation Equipment
GD_12
Installation of System Automation Equipment
GD_13
Installation of System Automation Equipment
GD_16
Installation of System Automation Equipment
GD_17
Line Removals (In HFTD)
GD_18
Other Grid Topology Improvements to Minimize Risk of Ignition
GD_19
Other Grid Topology Improvements to Mitigate or Reduce PSPS Risk
GD_20
Other Technologies and Systems Not Listed Above
GD_21
Other Technologies and Systems Not Listed Above
GD_22
Other Technologies and Systems Not Listed Above
GD_23
Other Technologies and Systems Not Listed Above
GD_24
Asset Inspection
GD_25
Asset Inspection
GD_26
Asset Inspection
GD_27
Asset Inspection
GD_28
Asset Inspection
GD_29
Undergrounding of Electric Lines and/or Equipment
GD_3
Asset Inspection
GD_30
Asset Inspection
GD_31
Asset Inspection
GD_32
Equipment Maintenance and Repair
GD_33
Asset Management and Inspection Enterprise System(s)
GD_34
Quality Assurance / Quality Control
GD_35
Open Work Orders
GD_36
Equipment Settings to Reduce Wildfire Risk
GD_37
Grid Response Procedures and Notifications
GD_38
Personnel Work Procedures and Training in Conditions of Elevated Fire Risk
GD_39
Distribution Pole Replacement and Reinforcement
GD_4
Workforce Planning
GD_40
Distribution Pole Replacement and Reinforcement
GD_5
Distribution Pole Replacement and Reinforcement
GD_6
Transmission Pole/Tower Replacement and Reinforcement
GD_7
Traditional Overhead Hardening
GD_8
Emerging Grid Hardening Technology Installations and Pilots
GD_9

## Slide 4: WMP Activities Status vs. WMP Activity Goals
Risk Methodology & Assessment
On Track
Off Track
Completed
Not Started
Ahead of Plan
Risk Methodology and Assessment
RMA_1
Technosylva Contractor Program
On Going
Contracting with Risk Mapping Resource:
2023 Goal: For 2023 BVES plans to continue its work with Technosylva to maintain its real time risk mapping capabilities with accurate electrical system inputs.
Key Actions: Regular meetings to discuss program status with Technosylva.
Overview of the Service Territory
Environmental Compliance and Permitting
ST_1
On Going
Environmental Compliance and Permitting:
2023 Goal: Environmental Compliance and Permitting is an as needed program for BVES. When new projects are launched BVES relies on its environmental consultant to confirm all permitting requirements for the projects. The consultant also verifies that all current BVES facilities have their appropriate permits.
Key Actions: Ongoing review of permitting for BVES facilities.
Wildfire Mitigation Strategy Development
Wildfire Mitigation Strategy Development
WMSD_1
On Going
Wildfire Mitigation Strategy Development:
2023 Goal: For 2023 BVES plans to develop and issue its WMP for approval. Following approval, the WMP will be posted to its website for public viewing.
Key Actions: BVES is in the final drafting stages of its WMP to be submitted to EnergySafety for approval on May 8th 2023.

## Slide 5: WMP Activities Status vs. WMP Activity Goals
Emergency Preparedness
Public Emergency Communication Strategy
EP_3
Established / Ongoing
Customer Support in Wildfire and PSPS Emergencies
EP_5
Established / Ongoing
Preparedness and Planning for Service Restoration
EP_4
Established / Ongoing
Emergency Preparedness Plan
EP_1
Established / Ongoing
Emergency Preparedness and Response Program and PSPS Plan:
Volume vs 2023 Goal: BVES did not record an emergency in Q1 of 2022. This means that the use of the Emergency Preparedness & Response Program was not required. BVES continues to review the effectiveness of its PSPS Plans and its Emergency Response through internal review and desktop exercises.
External Collaboration and Coordination
EP_2
Established / Ongoing
Community Outreach & Engagement
Collaboration on Local Wildfire Mitigation Planning
COE_3
On Track
Collaboration on Local Wildfire Mitigation Planning:
Volume vs 2023 Goal: BVES plans to engage with Local Support (Fire Department & Forest Service) on a regular basis to discuss project statuses as well as general needs and gaps for the upcoming fire season
Key Actions: BVES established plans to engage in coordination efforts based on PSPS activations, which will include suppression agencies.
Public Outreach and Education Awareness Program
COE_1
Exceeded Target
Public Outreach and Education Awareness Program:
Volume vs Q1 2023 Goal: BVES had planned to conduct at a minimum of 90 outreach activities. BVES recorded 153 outreach activities 170% of target for Q1.
Key Actions: Grizzly Newspaper advertisements are posted during the week (M-F) for either WMP or PSPS and BVES will have 1 advertisement broadcasted each month.
Engagement with Access and Function Needs (AFN) Populations:
Volume vs 2023 Goal: BVES has an established program in place to identify AFN customers and provide assistance during PSPS.
Key Actions: BVES continues to evaluate the functionality of its AFN program as it relates to PSPS and wildfire events. BVES verified the AFN list, and associated needs twice per month for 6 verifications in Q1.
Engagement with Access and Functional Needs Populations
COE_2
On Track
Best Practice Sharing with Other Utilities:
Volume vs 2023 Goal: BVES plans to evaluate the available working groups and conferences and make determinations on which groups/conferences add the most value to their wildfire program.
Key Actions: BVES has begun to review available working groups and conferences. BVES was able to attend 13 different subject matter working groups in Q1.
Best Practice Sharing with Other Utilities
COE_4
On Track
On Track
Off Track
Completed
Not Started
Ahead of Plan

## Slide 6: WMP Activities Status vs. WMP Activity Goals
Grid Design, Operations & Maintenance
Covered Conductor Replacement Program:
Volume vs Q1 2023 Goal: BVES planned to complete a total of 1.5 circuit miles by the end of Q1. BVES was able to complete 1.98 circuit miles by Q1.
Key Actions: BVES was able to complete 1.98 circuit miles of covered conductor instillation. BVES is currently ahead of projection for 2023.
Covered Conductor Installation
GD_1
Covered Conductor Replacement Program
Ahead of Plan
Covered Conductor Installation
GD_2
Radford Line Replacement Project
On Track
Radford Line Replacement Project:
Volume vs 2023 Goal: BVES plans to complete the Radford Line covered conductor project in 2023. BVES plans to replace 1 circuit mile in Q3 and 1.7 circuit miles in Q4, for a total of 2.7 circuit miles replaced.
Key Actions: No replacements are schedule until Q3. BVES continues to discuss status with the Forest Service.
Microgrids
GD_10
Bear Valley Solar Energy Project
Not Started
Bear Valley Solar Energy Project:
Volume vs 2023 Goal: The Bear Valley Solar Energy Project is not scheduled for construction in 2023.
Key Actions: BVES working to establish a Purchase & Sales Agreement with the developer and file an application with the CPUC in 2023.
Microgrids
GD_11
Energy Storage Project
Not Started
Bear Valley Energy Storage Project:
Volume vs 2023 Goal: The Energy Storage Project is not scheduled for construction in 2023.
Key Actions: BVES working to establish a Purchase & Sales Agreement with the developer and file an application with the CPUC in 2023.
Installation of System Automation Equipment
GD_12
Substation Automation
On Track
Substation Automation:
Volume vs 2023 Goal: BVES plans to connect and automate 2 substations to SCADA in Q3 and 1 substation in Q4, for a total of 3 substations in 2023.
Key Actions: No substation automation and connections are schedule until Q3.
Installation of System Automation Equipment
GD_13
Switch and Field Device Automation
On Track
Switch and Field Device Automation:
Volume vs 2023 Goal: BVES plans to connect and automate 6 Field Switches to SCADA in Q3 and 7 Field Switches in Q4, for a total of 13 Field Switches in 2023.
Key Actions: No Field Switches automation and connections are schedule until Q3.
Installation of System Automation Equipment
GD_14
Capacitor Bank Upgrade Project
On Track
Capacitor Bank Upgrade Project:
Volume vs 2023 Goal: BVES plans to connect and automate 6 Capacitor Banks to SCADA in Q4 for a total of 6 Capacitor Banks in 2023.
Key Actions: No Capacitor Banks automation and connections are schedule until Q4.
Installation of System Automation Equipment
GD_15
Fuse TripSaver Automation
On Track
Fuse TripSaver Automation:
Volume vs 2023 Goal: BVES plans to connect and automate 10 Fuse TripSavers to SCADA in Q4, for a total of 10 Fuse TripSavers in 2023.
Key Actions: No Fuse TripSavers automation and connections are schedule until Q4.
On Track
Off Track
Completed
Not Started
Ahead of Plan

## Slide 7: WMP Activities Status vs. WMP Activity Goals
Grid Design, Operations & Maintenance
Installation of System Automation Equipment
GD_16
Server Room
On Track
Server Room:
Volume vs 2023 Goal: BVES plans to install a Server Room at its main office in 2023.
Key Actions: The project is on schedule for completion in 2023.
Installation of System Automation Equipment
GD_17
Distribution Management Center
Not Started
Distribution Management Center:
Volume vs 2023 Goal: The Distribution Management Center Project is not scheduled for 2023.
Key Actions: No construction action will be taken on this program in 2023. BVES will perform project planning in 2023.
Line Removals (In HFTD)
GD_18
No Planned Projects
Line Removals (In HFTD):
Volume vs 2023 Goal: BVES does not have any planned line removals in HFTD in 2023.
Key Actions: N/A.
Covered Conductor Replacement Program:
Volume vs Q1 2023 Goal: BVES planned to complete zero tree attachment removals in Q1. BVES was able to complete 2 tree attachments removals by the end of Q1. BVES plans to remove 100 tree attachment removals in 2023.
Key Actions: BVES was able to complete 2 tree attachment removals. BVES is currently ahead of projection for 2023.
Other Grid Topology Improvements to Minimize Risk of Ignition
GD_19
Tree Attachment Removal Program
Ahead of Plan
Other Grid Topology Improvements to Mitigate or Reduce PSPS Risk
GD_20
Captured Through Other Programs
Other Grid Topology Improvements to Mitigate or Reduce PSPS Risk:
Volume vs Goal: The objectives of this initiative are achieved through BVES's installation of system automation equipment initiatives.
Key Actions: N/A.
Other Technologies and Systems Not Listed Above
GD_21
BVPP Phase 4 Upgrade Project
Not Started
BVPP Phase 4 Upgrade Project:
Volume vs 2023 Goal: The BVPP Phase 4 Upgrade Project is not scheduled for 2023.
Key Actions: No construction action will be taken on this program in 2023. BVES will perform project planning in 2023.
Other Technologies and Systems Not Listed Above
GD_22
Safety and Technical Upgrades to Maltby Substation
Not Started
Safety and Technical Upgrades to Maltby Substation:
Volume vs 2023 Goal: The Safety and Technical Upgrades to Maltby Substation is not scheduled for 2023.
Key Actions: No action will be taken on this program in 2023. BVES will perform project planning in 2023.
Other Technologies and Systems Not Listed Above
GD_23
Safety and Technical Upgrades to Lake Substation
Not Started
Safety and Technical Upgrades to Lake Substation:
Volume vs 2023 Goal: The Safety and Technical Upgrades to Lake Substation is not scheduled for 2023.
Key Actions: No action will be taken on this program in 2023. BVES will perform project planning in 2023.
Other Technologies and Systems Not Listed Above
GD_24
Safety and Technical Upgrades to Village Substation
Not Started
Safety and Technical Upgrades to Village Substation:
Volume vs 2023 Goal: The Safety and Technical Upgrades to Village Substation is not scheduled for 2023.
Key Actions: No action will be taken on this program in 2023. BVES will perform project planning in 2023.
On Track
Off Track
Completed
Not Started
Ahead of Plan

## Slide 8: WMP Activities Status vs. WMP Activity Goals
Grid Design, Operations & Maintenance
Detailed Inspection:
Volume vs Q1 2023 Goal: BVES planned to complete a total of 55 circuit miles of inspection by the end of Q1. BVES was able to complete 57 circuit miles by Q1.
Key Actions: BVES was able to complete 57 circuit miles of inspection. BVES is currently ahead of projection for 2023.
Asset Inspection
GD_25
Detailed Inspection
Ahead of Plan
Patrol Inspection:
Volume vs Q1 2023 Goal: BVES planned to complete a total of 52 circuit miles of inspection by the end of Q1. BVES was able to complete 71 circuit miles by Q1.
Key Actions: BVES was able to complete 71 circuit miles of inspection. BVES is currently ahead of projection for 2023.
Asset Inspection
GD_26
Patrol Inspection
Ahead of Plan
Asset Inspection
GD_27
UAV Thermography
On Track
UAV Thermography:
Volume vs 2023 Goal: BVES plans to conduct 206.7 circuit miles of inspection in Q3. BVES annual target is 206.7 circuit miles in 2023
Key Actions: No circuit miles were inspected in Q1.
Asset Inspection
GD_28
UAV HD Photography / Videography
On Track
UAV HD Photography / Videography:
Volume vs 2023 Goal: BVES plans to conduct 206.7 circuit miles of inspection in Q3. BVES annual target is 206.7 circuit miles in 2023
Key Actions: No circuit miles were inspected in Q1.
Asset Inspection
GD_29
LiDAR Inspection
On Track
LiDAR Inspection:
Volume vs 2023 Goal: BVES plans to conduct 206.7 circuit miles of inspection in Q3. BVES annual target is 206.7 circuit miles in 2023
Key Actions: No circuit miles were inspected in Q1.
Minor Undergrounding Upgrades Projects:
Volume vs 2023 Goal: BVES conducts undergrounding on an as needed basis. There were no proposed or initiated undergrounding projects in Q1.
Key Actions: No undergrounding projects were proposed or initiated in Q1
Undergrounding of Electric Lines and/or Equipment
GD_3
Minor Undergrounding Upgrades Projects
Ahead of Plan
Asset Inspection
GD_30
3rd Party Ground Patrol
On Track
3rd Party Ground Patrol:
Volume vs 2023 Goal: BVES plans to conduct 206.7 circuit miles of inspection in Q3. BVES annual target is 206.7 circuit miles in 2023
Key Actions: No circuit miles were inspected in Q1.
Asset Inspection
GD_31
Intrusive Pole Inspection
On Track
Intrusive Pole Inspection:
Volume vs 2023 Goal: BVES plans to conduct 850 poles intrusively inspected in Q3. BVES annual target is 850 poles intrusively inspected in 2023
Key Actions: No poles were inspected in Q1.
Asset Inspection
GD_32
Substation Inspections
On Track
Substation Inspections:
Volume vs Q1 2023 Goal: BVES planned to complete 36 substation inspections in Q1. BVES was able to complete 36 substation inspections in Q1
Key Actions: BVES was able to complete 36 substation inspections. BVES is currently on track for its target in 2023
Equipment Maintenance and Repair
GD_33
On Track
Equipment Maintenance and Repair:
Volume vs 2023 Goal: This is an as needed program for BVES and covers all maintenance of equipment in BVES service territory.
Key Actions: BVES performed as needed maintenance throughout the first quarter of 2023.
On Track
Off Track
Completed
Not Started
Ahead of Plan

## Slide 9: WMP Activities Status vs. WMP Activity Goals
Grid Design, Operations & Maintenance
Asset Quality Assurance / Quality Control:
Volume vs Q1 2023 Goal: BVES planned to complete a total of 5 asset QC’s on WMP work by the end of Q1. BVES was able to complete 5 QC’s by Q1.
Key Actions: BVES was able to complete 5 asset QC’s. BVES is currently on track for 2023.
Quality Assurance / Quality Control
GD_35
Asset Quality Assurance / Quality Control
On Track
Asset Management and Inspection Enterprise System(s)
GD_34
Distribution Management Center
Asset Management and Inspection Enterprise System(s):
Volume vs 2023 Goal: The Asset Management and Inspection Enterprise System is an ongoing activity for BVES. Currently its systems are standalone but due to BVES’s size this is not a major concern.
Key Actions: BVES continue to evaluate the need for automate and master systems as it relates to asset management and inspection.
Asset Open Work Orders:
Volume vs 2023 Goal: For 2023 BVES has a goal to have no work orders exceeding the GO 95 timeframe.
Key Actions: BVES did not have any work orders that exceeded the GO 95 timeframe in Q1.
Open Work Orders
GD_36
Asset Open Work Orders
On Track
Equipment Settings to Reduce Wildfire Risk:
Volume vs 2023 Goal: For 2023 BVES plans to review its equipment settings on a regular basis and evaluate the need for modified settings.
Key Actions: BVES reviewed the equipment settings in Q1.
Equipment Settings to Reduce Wildfire Risk
GD_37
On Track
Grid Response Procedures and Notifications:
Volume vs 2023 Goal: For 2023 BVES plans to review and if necessary, update its procedure. This will be an annual process
Key Actions: BVES began to review its procedure in Q1.
Grid Response Procedures and Notifications
GD_38
On Track
Personnel Work Procedures and Training in Conditions of Elevated Fire Risk:
Volume vs 2023 Goal: For 2023 BVES plans to review and if necessary, update its procedure. This will be an annual process. BVES will also verify the training of all responsible staff members.
Key Actions: BVES began to review its procedure in Q1.
Personnel Work Procedures and Training in Conditions of Elevated Fire Risk
GD_39
On Track
Distribution Pole Replacement and Reinforcement:
Volume vs 2023 Goal: BVES planned to complete a total of 25 pole replacements in Q1. BVES was able to complete 58 total pole replacements.
Key Actions: BVES was able to complete 58 pole replacements in Q1, placing the program 32 poles ahead of schedule.
Distribution Pole Replacement and Reinforcement
GD_4
Distribution Pole Replacement and Reinforcement
On Track
Asset Workforce Planning:
Volume vs 2023 Goal: For 2023 BVES has a goal to verify that the wildfire related positions are appropriately staffed. This review is conducted quarterly
Key Actions: BVES reviewed and verified that the appropriate staffing levels exist for wildfire related positions.
Workforce Planning
GD_40
Asset Workforce Planning
On Track
Distribution Pole Replacement and Reinforcement
(Radford Line Replacement Project):
Volume vs 2023 Goal: BVES planned to replace 0 poles in Q1. The program target for Radford Line Replacement Project pole replacement is 70 by the end of 2023
Key Actions: BVES scheduled zero pole replacements in Q1. The pole replacement schedule for Radford is contingent on the US Forest Service permitting process.
Distribution Pole Replacement and Reinforcement
GD_5
Radford Line Replacement Project
On Track
On Track
Off Track
Completed
Not Started
Ahead of Plan

## Slide 10: WMP Activities Status vs. WMP Activity Goals
Grid Design, Operations & Maintenance
Asset Quality Assurance / Quality Control:
Volume vs Q1 2023 Goal: BVES planned to complete a total of 250 poles hardened with Wire Mesh in Q1. BVES was able to complete 500 poles hardened with Wire Mesh Q1.
Key Actions: BVES was able to complete 500 poles hardened with Wire Mesh. BVES has completed its target for 2023.
Distribution Pole Replacement and Reinforcement
GD_6
Evacuation Route Hardening Project
Complete
Transmission Pole/Tower Replacement and Reinforcement
GD_7
Not Applicable
Transmission Pole/Tower Replacement and Reinforcement:
Volume vs 2023 Goal: BVES does not own or operate any transmission assets.
Key Actions: N/A.
Traditional Overhead Hardening:
Volume vs 2023 Goal: This is an as needed program for BVES. There is a budget allocation for the year based on history but no specifically tracked tasks. Overhead hardening work is performed as needed in response to inspection findings and emergent conditions.
Key Actions: BVES conducted as needed maintenance throughout Q1.
Traditional Overhead Hardening
GD_8
On Track
Emerging Grid Hardening Technology Installations and Pilots
GD_9
Not Started
Emerging Grid Hardening Technology Installations and Pilots:
Volume vs 2023 Goal: Currently no projects in the initiative. BVES will discuss opportunities with partner utilities on the effectiveness of such technologies.
Key Actions: No project activity is planned for 2023 in this area.
On Track
Off Track
Completed
Not Started
Ahead of Plan
Not Currently Scheduled*

## Slide 11: WMP Activities Status vs. WMP Activity Goals
Situational Awareness & Forecasting
Advanced Weather Monitoring and Weather Stations:
Volume vs 2023 Goal: BVES completed the installation of all planned Weather Stations in 2022. This program has transitioned to maintaining normal operation of said equipment.
Key Actions: BVES determined all the maintenance needs of the weather equipment were met in Q1.
Environmental Monitoring Systems
SAF_1
Advanced Weather Monitoring and Weather Stations
On Track
HD ALERTWildfire Cameras:
Volume vs 2023 Goal: BVES completed the installation of all planned HD ALERTWildfire Cameras in 2022. BVES provides O&M support as requested by USCD (HD ALERTWildfire Camera owner).
Key Actions: All cameras are in operation providing complete and overlapping coverage of the BVES service territory.
Ignition Detection Systems
SAF_4
HD ALERTWildfire Cameras
Complete
Fault Indicator Instillation:
Volume vs Q1 2023 Goal: BVES planned to complete a total of 5 fault indicator installations by the end of Q1. BVES was able to complete 35 installations by Q1.
Key Actions: BVES was able to complete 35 fault indicator installations. BVES is currently ahead of plan for 2023.
Grid Monitoring Systems
SAF_2
Fault Indicator Instillation
Ahead of Plan
Grid Monitoring Systems
SAF_3
Online Diagnostic System
On Track
Online Diagnostic System:
Volume vs 2023 Goal: BVES plans to install online diagnostic capabilities on 1 circuit in 2023, and that will occur in Q4.
Key Actions: No online diagnostic capability installation are schedule until Q4.
Weather Forecasting
SAF_5
On Track
Weather Forecasting:
Volume vs 2023 Goal: BVES employs a weather consultant and uses Technoslyva’s WFA-E application as its modeling software for wildfire spread potential based off current weather conditions.
Key Actions: This is an ongoing effort that continued throughout Q1.
Fire Potential Index
SAF_6
On Track
Fire Potential Index:
Volume vs 2023 Goal: BVES is currently using NFDRS for its FPI but is transitioning to have Technosylva develop a BVES specific FPI.
Key Actions: BVES is worked with Technosylva to develop a scope of work for the FPI development project.
On Track
Off Track
Completed
Not Started
Ahead of Plan

## Slide 12: WMP Activities Status vs. WMP Activity Goals
Vegetation Management & Inspection
Detailed Inspection:
Volume vs Q1 2023 Goal: BVES planned to complete a total of 55 circuit miles of inspection by the end of Q1. BVES was able to complete 57 circuit miles by Q1.
Key Actions: BVES was able to complete 57 circuit miles of inspection. BVES is currently ahead of projection for 2023.
Vegetation Inspections
VM_1
Detailed Inspection
Ahead of Plan
Patrol Inspection:
Volume vs Q1 2023 Goal: BVES planned to complete a total of 52 circuit miles of inspection by the end of Q1. BVES was able to complete 71 circuit miles by Q1.
Key Actions: BVES was able to complete 71 circuit miles of inspection. BVES is currently ahead of projection for 2023.
Vegetation Inspection
VM_2
Patrol Inspection
Ahead of Plan
Vegetation Inspection
VM_3
UAV HD Photography / Videography
On Track
UAV HD Photography / Videography:
Volume vs 2023 Goal: BVES plans to conduct 206.7 circuit miles of inspection in Q3. BVES annual target is 206.7 circuit miles in 2023.
Key Actions: No circuit miles were inspected in Q1.
Vegetation Inspection
VM_4
LiDAR Inspection
On Track
LiDAR Inspection:
Volume vs 2023 Goal: BVES plans to conduct 206.7 circuit miles of inspection in Q3. BVES annual target is 206.7 circuit miles in 2023.
Key Actions: No circuit miles were inspected in Q1.
Vegetation Inspection
VM_5
3rd Party Ground Patrol
On Track
3rd Party Ground Patrol:
Volume vs 2023 Goal: BVES plans to conduct 206.7 circuit miles of inspection in Q3. BVES annual target is 206.7 circuit miles in 2023.
Key Actions: No circuit miles were inspected in Q1.
Vegetation Inspection
VM_6
Substation Inspections
On Track
Substation Inspections:
Volume vs Q1 2023 Goal: BVES planned to complete 36 substation inspections in Q1. BVES was able to complete 36 substation inspections in Q1.
Key Actions: BVES was able to complete 36 substation inspections. BVES is currently on track for its target in 2023.
Pole Clearing
VM_7
On Track
Pole Clearing:
Volume vs 2023 Goal: BVES has an established pole clearing program. Throughout the year BVES reviews the procedure and updates it if the need arises.
Key Actions: BVES continues to evaluate where pole clearing is necessary and takes action.
Wood and Slash Management
VM_8
On Track
Wood and Slash Management:
Volume vs 2023 Goal: BVES contracts its vegetation clearing to a 3rd party contractor. The contractor is responsible for meeting the waste removal requirements.
Key Actions: BVES verified that the contractor adhered to the waste removal requirements outlined in the contract.
Clearance
VM_9
Off Track
Vegetation Clearance:
Volume vs Q1 2023 Goal: BVES planned to complete 18 circuit mils of clearing in Q1. BVES was able to complete 13 circuit miles in Q1
Key Actions: BVES was able to complete 13 circuit miles. In Q1 BVES experienced significantly higher than average storm weather and snow accumulation, which significantly hindered vegetation clearance work. BVES is confident it will achieve it will make up the missed 5 circuit miles and achieve its annual target.
Fall-In Mitigation
VM_10
Ahead of Plan
Fall-In Mitigation:
Volume vs Q1 2023 Goal: BVES planned to complete 18 tree remediation's or removal’s to prevent fall-in in Q1. BVES was able to complete 32 tree remediation's or removal’s in Q1.
Key Actions: BVES was able to complete 32 remediation's or removals. BVES is currently ahead of plan for its target in 2023.
On Track
Off Track
Completed
Not Started
Ahead of Plan

## Slide 13: WMP Activities Status vs. WMP Activity Goals
Vegetation Management & Inspection
Substation Defensible Space:
Volume vs Q1 2023 Goal: BVES’s contracted vegetation resource conducts regular clearing to verify compliance with the GO requirements. BVES’s Substation Inspection program verifies compliance.
Key Actions: BVES was able to complete 36 substation inspections and had zero planned abetments for Q1 of 2023.
Substation Defensible Space
VM_11
On Track
High-Risk Species
VM_12
On Track
High-Risk Species:
Volume vs 2023 Goal: BVES conducts as needed remediation of high-risk species in its service territory. There are no specific program targets for 2023.
Key Actions: BVES will take action as inspection findings and VM crews identify high-risk specifies throughout 2023.
Fire-Resilient Right-of-Ways
VM_13
On Track
Fire-Resilient Right-of-Ways:
Volume vs 2023 Goal: BVES’s contracted vegetation resource (forester) conducts regular inspections to verify compliance with requirements and to seek opportunities to make right of ways more resilient.
Key Actions: BVES will take action vegetation resource’s recommendations in this area.
Vegetation Management Enterprise System
VM_15
On Track
Vegetation Management Enterprise System:
Volume vs 2023 Goal: The Vegetation Management Enterprise System is an ongoing activity for BVES. Currently its systems are standalone but due to BVES’s size this is not a major concern.
Key Actions: BVES continue to evaluate the need for automated and master systems as it relates to vegetation management.
Vegetation Management Quality Assurance / Quality Control:
Volume vs Q1 2023 Goal: BVES planned to complete 2 vegetation management audits by the end of Q1 (annual audit and quarterly audit). BVES was able to complete the 2 audits by Q1.
Key Actions: BVES was able to complete the 2 audits. BVES is currently on track complete its audits per its schedule for 2023.
Quality Assurance / Quality Control
VM_16
Vegetation Management Quality Assurance / Quality Control
On Track
Vegetation Management Open Work Orders:
Volume vs 2023 Goal: For 2023 BVES has a goal to have no work orders exceeding the GO 95 Rule 18 corrective action timeframe.
Key Actions: BVES did not have any work orders that exceeded the GO 95 timeframe in Q1.
Open Work Orders
VM_17
Vegetation Management Open Work Orders
On Track
Vegetation Management Workforce Planning:
Volume vs 2023 Goal: For 2023 BVES has a goal to verify that the wildfire related positions are appropriately staffed. This review is conducted quarterly
Key Actions: BVES reviewed and verified that the appropriate staffing levels exist for wildfire related positions.
Workforce Planning
VM_18
Vegetation Management Workforce Planning
On Track
Emergency Response Vegetation Management:
Volume vs 2023 Goal: BVES’s contracted vegetation contractor’s crews are contractually available on an as needed basis for disaster or emergency event vegetation management.
Key Actions: BVES mobilize and dispatch VM crews as needed in 2023.
Emergency Response Vegetation Management
VM_14
On Track
On Track
Off Track
Completed
Not Started
Ahead of Plan