## Slide 1: SDG&E’s 2023 Wildfire Mitigation Plan 1st Quarter Progress Update
(All data as of March 31st, 2023)

## Slide 2: 2023 Wildfire Mitigation Plan Activities Q1 Summary
8.1.2.1
Distribution OH Hardening - Covered Conductor
WMP.455
8.1.2.2
Strategic Undergrounding
WMP.473
8.1.2.5.1
Distribution OH System Hardening
WMP.475
8.1.2.5.2
Transmission OH Hardening
WMP.543
8.1.2.5.2
Transmission OH Hardening - Distribution Underbuild
WMP.545
8.2.2.1
Distribution Veg Detailed Inspections
WMP.494
8.1.2.8.1
Advanced Protection
WMP.463
8.1.2.8.2
Early Fault Detection
WMP.1195
8.1.2.8.3
Distribution communications reliability improvements
WMP.549
8.1.4.3
Capacitor maintenance and replacement program
WMP.453
8.1.4.4
Expulsion fuse replacement
WMP.459
8.1.4.5
Maintenance, repair, and replacement of connectors, incl. hotline clamps
WMP.464
8.1.4.6
Lightning arrestor removal and replacement
WMP.550
8.1.2.10.1
Avian Protection
WMP.972
8.1.2.10.2
Strategic Pole Replacement Program
WMP.1189
8.1.2.11.1
PSPS sectionalizing enhancements
WMP.461
8.1.2.11.2
Fixed Power Backup
WMP. 468
8.1.3.1
Distribution Overhead Detailed Inspections
WMP.478
8.1.3.2
Transmission Overhead Detailed Inspections
WMP.479
8.1.3.3
Distribution Infrared Inspections
WMP.481
8.1.3.4
Transmission Infrared Inspections
WMP.482
8.1.3.5
Distribution wood pole intrusive
WMP.483
8.1.3.6
Transmission wood pole intrusive
WMP.1190
8.1.3.7
Drone Assessments
WMP.552
8.1.3.8
Distribution Overhead Patrol Inspections
WMP.488
8.1.3.9
Transmission Overhead Patrol Inspections
WMP.489
8.1.3.10
Transmission 69kV Tier 3 Visual Inspections
WMP.555
8.1.3.11
Substation Patrol inspections
WMP.492
8.1.6.1
QA/QC of Transmission Inspections
WMP.1191
8.1.6.2
QA/QC of Distribution Detailed Inspections
WMP.491
8.1.6.3
QA/QC of Distribution Drone Assessments
WMP.1192
8.1.6.4
QA/QC of Wood Pole Intrusive (Transmission & Distribution)
WMP.1193
8.1.6.5
QA/QC of Substation Inspections
WMP.1194
8.2.3
Fuels management program
WMP.497
8.2.3.1
Pole Clearing
WMP.512
8.2.2.2
Off-Cycle patrol
WMP.508
8.2.3.3
Clearance
WMP.501
8.25
QA/QC Vegetation Management
WMP.505
8.3.2.1.3
Air Quality Index
WMP.970
8.1 - Grid Design, Operations, & Maintenance
8.2 – Vegetation Management
& Inspection
8.3 – Situational Awareness
& Forecasting

## Slide 3: Q1 Activity Status vs 2023 Goals
8.1.2.1
3.78
Miles
6% Distribution OH Hardening - Covered Conductor
Volume vs 2023 Goal: 3.78 of 60 miles covered conductor (6%)
Key Actions: Program on track.
8.1.2.5.1
1.31
Miles
69% Distribution overhead system hardening
Volume vs 2023 Goal: 1.31 of 1.9 miles hardened (69%)
Key Actions: Program on track.
8.1.2.5.2
1.07
Miles
15% Overhead transmission fire hardening (Distribution Underbuilt)
Volume vs 2023 Goal: 1.07 of 7.1 miles hardened (15%)
Key Actions: Program on track.
8.1.2.8.2
0
Nodes
8.1.2.2
4.38
Miles
5% Strategic Undergrounding
Volume vs 2023 Goal: 4.38 of 84.43 miles UG (5%)
Key Actions: Program on track.
8.1.2.5.2
3.36
Miles
24% Transmission overhead system hardening
Volume vs 2023 Goal: 3.36 of 14.1 miles hardened (24%)
Key Actions: Program on track.
8.1.2.8.1
0
Circuits
8.1.2.8.3
2
Base Stations
6% Distribution communications reliability improvements
Volume vs 2023 Goal: 2 of 35 base stations (6%)
Key Actions: Program on track.
8.1 – Grid Design, Operations, and Maintenance
0% Advanced Protection
Volume vs 2023 Goal: 0 of 5 circuits enabled (0%)
Key Actions: Program not started.
8.1.4.3
7
Capacitors
47% Capacitor maintenance and replacement program - SCADA capacitors
Volume vs 2023 Goal: 7 of 15 SCADA capacitors (47%)
Key Actions: Program on track.
0% Early Fault Detection
Volume vs 2023 Goal: 0 of 60 nodes enabled (0%)
Key Actions: Program not started.
All data is up to date as of March 31, 2023
8.1.4.4
2
Fuses
5% Expulsion fuse replacement
Volume vs 2023 Goal: 2 of 40 expulsion fuses (5%)
Key Actions: Program on track.

## Slide 4: Q1 Activity Status vs 2023 Goals
8.1.4.6
578
Arrestors
31% Lightning arrester removal and replacement
Volume vs 2023 Goal: 578 of 1,848 lightning arrestors replaced (31%)
Key Actions: Program on track.
8.1.2.10.2
0
Miles
0% Strategic Pole Replacement Program
Volume vs 2023 Goal: 0 of 60 poles (0%)
Key Actions: Program not started.
8.1.3.1
4,326
Structures
8.1.4.5
71
Hotline Clamps
28% Maintenance, repair, and replacement of connectors, including hotline clamps
Volume vs 2023 Goal: 71 of 250 hotline clamps (28%)
Key Actions: Program on track.
8.1.2.10.1
81
Poles
41% Avian Protection
Volume vs 2023 Goal: 81 of 200 poles (41%)
Key Actions: Program on track.
0% PSPS sectionalizing enhancements
Volume vs 2023 Goal: 0 of 10 sectionalizing devices (0%)
Key Actions: Program not started.
8.1.3.2
130
Structures
1% Transmission overhead detailed inspections
Volume vs 2023 Goal: 130 of 2,387 structures inspected (1%)
Key Actions: Program on track.
8.1 – Grid Design, Operations, and Maintenance (2 of 4)
13% Standby Power Program
Volume vs 2023 Goal: 38 of 300 generators (13%)
Key Actions: Program on track.
8.1.3.3
2,989
Structures
39% Distribution overhead detailed inspections
Volume vs 2023 Goal: 4,326 of 11,100 structures inspected (39%)
Key Actions: Program on track.
8.1.2.11.1
0
Switches
8.1.2.11.2
38
Generators
31% Distribution Infrared Inspections
Volume vs 2023 Goal: 2,989 of 9,578 structures inspected (31%)
Key Actions: Program on track.
All data is up to date as of March 31, 2023
8.1.3.4
0
Structures
0% Transmission Infrared Inspections
Volume vs 2023 Goal: 0 of 6,179 structures inspected (0%)
Key Actions: Program not started.

## Slide 5: Q1 Activity Status vs 2023 Goals
8.1.3.8
24,998
Structures
8.1.3.11
92
Structures
8.1.3.5
53
Structures
106% Distribution Wood Pole Intrusive
Volume vs 2023 Goal: 53 of 50 structures inspected (106%)
Key Actions: Program complete.
8.1.3.7
604
Structures
4% Drone assessments of distribution infrastructure
Volume vs 2023 Goal: 604 of 13,692 structures inspected (4%)
Key Actions: Program on track.
49% Patrol inspections of transmission electric lines and equipment
Volume vs 2023 Goal: 3,120 of 6,337 structures inspected (49%)
Key Actions: Program on track.
8.1.6.1
100%
Findings
100% QA/QC of Transmission Inspections
Volume vs 2023 Goal: 100% of 100% findings (100%)
Key Actions: Program on track.
8.1 – Grid Design, Operations, and Maintenance (3 of 4)
0% Additional Transmission Aerial 69kV Tier 3 Visual Inspection
Volume vs 2023 Goal: 0 of 1,632 structures inspected (0%)
Key Actions: Program not started.
8.1.6.2
8
Structures
24% Substation inspections
Volume vs 2023 Goal: 92 of 384 structures inspected (24%)
Key Actions: Program on track.
8.1.3.9
3,120
Structures
8.1.3.10
0
Structures
5% QA/QC of Distribution Detailed Inspections
Volume vs 2023 Goal: 8 of 160 structures inspected (5%)
Key Actions: Program on track.
29% Patrol inspections of distribution electric lines and equipment
Volume vs 2023 Goal: 24,998 of 86,880 structures inspected (29%)
Key Actions: Program on track.
All data is up to date as of March 31, 2023
8.1.3.6
1
Structures
1% Transmission Wood Pole Intrusive
Volume vs 2023 Goal: 1 of 73 structures inspected (1%)
Key Actions: Program on track.
8.1.6.3
604
Structures
4% QA/QC of Distribution Drone Inspections
Volume vs 2023 Goal: 604 of 13,692 structures inspected (4%)
Key Actions: Program on track.

## Slide 6: Q1 Activity Status vs 2023 Goals
8.3.2.1.3
2
Sensors
8.1.6.4
20
Structures
24% Continuous monitoring sensors - Air Quality Index
Volume vs 2023 Goal: 2 of 6 air quality sensors installed (24%)
Key Actions: Program on track.
8.1 – Grid Design, Operations, and Maintenance (4 of 4) 8.3 – Situational Awareness and Forecasting
8.1.6.5
0
Structures
0% QA/QC of Substation Inspections
Volume vs 2023 Goal: 0 of 18 structures inspected (0%)
Key Actions: Program not started.
167% QA/QC of Wood Pole Intrusive Inspections
Volume vs 2023 Goal: 20 of 12 structures inspected (167%)
Key Actions: Program ahead of plan.
All data is up to date as of March 31, 2023

## Slide 7: Q1 Activity Status vs 2023 Goals
8.2.2.1
116,089
Inspections
24% Detailed inspections of vegetation around distribution electric lines and equipment
Volume vs 2023 Goal: 116,089 of 485,400 trees inspected (24%)
Key Actions: Program on track.
8.2.3
71
Poles Cleared
14% Fuels management and reduction of "slash" from vegetation management activities
Volume vs 2023 Goal: 71 of 500 poles cleared (14%)
Key Actions: Program on track.
8.2.3.1
13,096
Poles Brushed
25% Vegetation management to achieve clearances around electric lines and equipment
Volume vs 2023 Goal: 13,096 of 33,010 poles brushed (25%)
Key Actions: Program on track.
8.2.5
23,217
Inspections
20% QA/QC of Vegetation Management Inspections
Volume vs 2023 Goal: 23,217 of 72,810 inspections (20%)
Key Actions: Program on track.
8.2.2.2
25
Vegetation Management Areas
24% Removal and remediation of trees with strike potential to electric lines and equipment
Volume vs 2023 Goal: 25 of 106 Vegetation Management Areas Completed (24%)
Key Actions: Program on track.
8.2.3.3
2,423
Trees
8.2 – Vegetation Management and Inspection
22% Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Volume vs 2023 Goal: 2,423 of 11,200 trees trimmed/removed (22%)
Key Actions: Program on track.
All data is up to date as of March 31, 2023