## Bay
iTreeRecsID | Source | Circuit type | sAcctType | PRIORITY | Tree_Type | TRIM_TYPE | sWorkReq | ActualTrimCode | Tree_Qty | Region | Division | sCity | sCountyCode | scircuit | CIRCUIT | sNotification | Completion status - field | Constraint? | dtInspDate | dtWorkDate | Due date per compliance | Business Days Between Work Date and Compliance Date | Timeliness status | Location_Lat | Location_Long | Tree_Lat | Tree_Long | iHFTDTier | iRefusalID | sDocNumber | REFUSAL_TYPE | sRefusalStatus | dtResolved | Reason for Completion after Compliance Due Date
-1056012138 | VMS | Distribution | M | Priority 2 (P2) | Palm-Fan | ZRC to 11 | EBMI1032544 | RD1 | 1 | Bay | MI | FREMONT | AL | 0012221106 | NEWARK 1106 | O | Complete | Constraint_ITS_past | 2023-10-06 | 2024-01-05 | 2023-12-13 | -18 | 3. Non-timely worked |  |  | 37.529985610 | -121.991117890 |  | 617513 | ACC031151759 | Access Issue | CLOSE | 2023-11-08 | Additional Constraint due to Customer Refusal
-1056012508 | VMS | Distribution | M | Priority 2 (P2) | Pistache | ZRC 12+ | EBMI1032544 | RD2 | 1 | Bay | MI | FREMONT | AL | 0012221106 | NEWARK 1106 | O | Complete | Constraint_ITS_past | 2023-10-06 | 2024-01-05 | 2023-12-13 | -18 | 3. Non-timely worked |  |  | 37.529729340 | -121.994675030 |  | 617512 | ACC031151617 | Access Issue | CLOSE | 2023-11-08 | Additional Constraint due to Customer Refusal
-1057123338 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC to 11 | PEPE1081734 | RD1 | 1 | Bay | PE | SAN MATEO | SM | 0024110405 | HILLSDALE 0405 | O | Complete | Constraint_ITS_past | 2023-02-16 | 2023-04-12 | 2023-03-28 | -12 | 3. Non-timely worked |  |  | 37.538715000 | -122.321060000 |  | 585435 | RFT228093227 | Refusal | CLOSE | 2023-02-28 | Additional Constraint due to Customer Surgery
-1056004923 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | PEPE1085824 | RD2 | 1 | Bay | PE | MENLO PARK | SM | 0024130401 | MENLO 0401 | O | Complete | Constraint_ITS_past | 2023-10-12 | 2024-01-08 | 2023-12-20 | -14 | 3. Non-timely worked |  |  | 37.434972230 | -122.186258380 |  | 619054 | OTT109150300 | Other | CLOSE | 2023-11-20 | Additional constraint due to line clearance.
-1056065823 | VMS | Distribution | M | Priority 2 (P2) | Pittosporum | ZRC to 11 | PEPE1084779 | RD1 | 1 | Bay | PE | REDWOOD CIT | SM | 0024180405 | SAN CARLOS 0405 | O | Complete | No Constraint | 2023-08-25 | 2023-09-26 | 2023-09-25 | -2 | 3. Non-timely worked |  |  | 37.484956000 | -122.244896000 | [6 empty] | Additional constraint due to line kill.
-1056065824 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | PEPE1084779 | RD2 | 1 | Bay | PE | REDWOOD CIT | SM | 0024180405 | SAN CARLOS 0405 | O | Complete | No Constraint | 2023-08-25 | 2023-09-26 | 2023-09-25 | -2 | 3. Non-timely worked |  |  | 37.484956000 | -122.244896000 | [6 empty] | Additional constraint due to line kill.
-1056708865 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | PEPE1082204 | RD1 | 1 | Bay | PE | MENLO PARK | SM | 0024130404 | MENLO 0404 | O | Complete | No Constraint | 2023-03-08 | 2023-04-06 | 2023-04-05 | -2 | 3. Non-timely worked |  |  | 37.435665480 | -122.198554060 | [6 empty] | Additional constraint due to refusal.
-1056043079 | VMS | Distribution | M | Priority 2 (P2) | Alder | ZRC to 11 | PEPE1084973 | RD1 | 1 | Bay | PE | LA HONDA | SM | 0024101103 | HALF MOON BAY 1103 | O | Complete | No Constraint | 2023-09-12 | 2023-10-20 | 2023-10-10 | -9 | 3. Non-timely worked |  |  | 37.315881900 | -122.274409480 | 2 | [5 empty] | Additional constraint due to traffic control required.
-1056247974 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZMAJOR R2 | PEPE1083084 | POJ | 1 | Bay | PE | SOUTH SAN F | SM | 0022641105 | DALY CITY 1105 | O | Complete | No Constraint | 2023-05-20 | 2023-06-24 | 2023-06-20 | -4 | 3. Non-timely worked |  |  | 37.669162160 | -122.452077410 | [6 empty] | Additional constraint not submitted by vendor before work.
-1056021902 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | PEPE1085129 | RD1 | 1 | Bay | PE | SKY LONDA | SM | 0024251101 | WOODSIDE 1101 | O | Complete | No Constraint | 2023-10-02 | 2023-10-31 | 2023-10-30 | -2 | 3. Non-timely worked |  |  | 37.387957640 | -122.269858090 | 3 | [5 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056017860 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC to 11 | PEPE1085186 | RD1 | 1 | Bay | PE | SAN CARLOS | SM | 0024180402 | SAN CARLOS 0402 | O | Complete | No Constraint | 2023-10-04 | 2023-11-02 | 2023-11-01 | -2 | 3. Non-timely worked |  |  | 37.501430480 | -122.260869280 | [6 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056017861 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC to 11 | PEPE1085186 | RD1 | 1 | Bay | PE | SAN CARLOS | SM | 0024180402 | SAN CARLOS 0402 | O | Complete | No Constraint | 2023-10-04 | 2023-11-02 | 2023-11-01 | -2 | 3. Non-timely worked |  |  | 37.501442740 | -122.260850350 | [6 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056027157 | VMS | Distribution | M | Priority 2 (P2) | Palm-Fan | ZRC 12+ | PEPE1085099 | RD2 | 1 | Bay | PE | EAST PALO A | SM | 0024020405 | BELL HAVEN 0405 | O | Complete | No Constraint | 2023-09-25 | 2023-10-31 | 2023-10-23 | -7 | 3. Non-timely worked |  |  | 37.463979490 | -122.128502240 | [6 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056023762 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | PEPE1085148 | RD2 | 1 | Bay | PE | WOODSIDE | SM | 0024251101 | WOODSIDE 1101 | O | Complete | No Constraint | 2023-09-28 | 2023-10-27 | 2023-10-26 | -2 | 3. Non-timely worked |  |  | 37.383842490 | -122.250807350 | 3 | [5 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056023765 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | PEPE1085148 | RD2 | 1 | Bay | PE | WOODSIDE | SM | 0024251101 | WOODSIDE 1101 | O | Complete | No Constraint | 2023-09-28 | 2023-10-27 | 2023-10-26 | -2 | 3. Non-timely worked |  |  | 37.386260000 | -122.246878000 | 3 | [5 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056152695 | VMS | Distribution | M | Priority 2 (P2) | Monterey Cypress | ZMAJOR R4 | PESF1015128 | MA4 | 1 | Bay | SF | SAN FRANCIS | SF | 0022480402 | CASTRO 0402 | O | Complete | No Constraint | 2023-07-06 | 2023-08-04 | 2023-08-03 | -2 | 3. Non-timely worked |  |  | 37.747677930 | -122.438356460 | [6 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056040080 | VMS | Distribution | M | Priority 2 (P2) | Monterey Cypress | ZPRUNE R4 | PESF1015204 | NWK | 1 | Bay | SF | SAN FRANCIS | SF | 0022100401 | SUBSTATION H 0401 | O | Complete | No Constraint | 2023-09-14 | 2023-10-20 | 2023-10-12 | -7 | 3. Non-timely worked |  |  | 37.715938590 | -122.428566830 | [6 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056276979 | VMS | Distribution | M | Priority 2 (P2) | Monterey Cypress | ZRC to 11 | PESF1015021 | RD1 | 1 | Bay | SF | SAN FRANCIS | SF | 0022550402 | 21ST AVENUE 0402 | O | Complete | No Constraint | 2023-05-05 | 2023-06-07 | 2023-06-05 | -3 | 3. Non-timely worked |  |  | 37.753010540 | -122.472561940 | [6 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056277235 | VMS | Distribution | M | Priority 2 (P2) | Monterey Pine | ZRC to 11 | PESF1015021 | RD1 | 1 | Bay | SF | SAN FRANCIS | SF | 0022550402 | 21ST AVENUE 0402 | O | Complete | No Constraint | 2023-05-05 | 2023-06-07 | 2023-06-05 | -3 | 3. Non-timely worked |  |  | 37.752567250 | -122.471513410 | [6 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056026138 | VMS | Distribution | M | Priority 2 (P2) | Brisbane Box | ZRC to 11 | PESF1015245 | RD1 | 1 | Bay | SF | DALY CITY | SM | 0022470402 | ACTON 0402 | O | Complete | No Constraint | 2023-09-26 | 2023-11-01 | 2023-10-24 | -7 | 3. Non-timely worked |  |  | 37.705487540 | -122.460172500 | [6 empty] | BIlling delay; vendor failed to bill close tree with correct completion date
-1056015758 | VMS | Distribution | M | Priority 2 (P2) | Willow | ZRC 12+ | PEPE1085221 | NW | 1 | Bay | PE | BURLINGAME | SM | 0024050402 | BURLINGAME 0402 | O | Complete | No Constraint | 2023-10-05 | 2023-11-08 | 2023-11-02 | -5 | 3. Non-timely worked |  |  | 37.579657700 | -122.380567020 | [6 empty] | Closed as complete on arrival by vendor.
-1056040426 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | PEPE1084998 | NWK | 1 | Bay | PE | WOODSIDE | SM | 0024251104 | WOODSIDE 1104 | O | Complete | No Constraint | 2023-09-14 | 2023-11-01 | 2023-10-12 | -15 | 3. Non-timely worked |  |  | 37.429309240 | -122.259764810 | [6 empty] | Completed late by vendor.
-1056033458 | VMS | Distribution | M | Priority 2 (P2) | Pine | ZRC to 11 | PEPE1085038 | NW | 1 | Bay | PE | DALY CITY | SM | 0022641104 | DALY CITY 1104 | O | Complete | No Constraint | 2023-09-19 | 2023-10-18 | 2023-10-17 | -2 | 3. Non-timely worked |  |  | 37.657040450 | -122.472847140 | [6 empty] | Completed timely as P1 on 10/11 # PEPE1085251
-1056026547 | VMS | Distribution | M | Priority 2 (P2) | Black Walnut | ZRC 12+ | EBMI1032521 | NWK | 1 | Bay | MI | DUBLIN | AL | 0014232104 | SAN RAMON 2104 | O | Complete | No Constraint | 2023-09-26 | 2023-10-25 | 2023-10-24 | -2 | 3. Non-timely worked |  |  | 37.714979330 | -121.932735910 | [6 empty] | Data entry delay. Unit field checked and noted as completed on 10/24
-1056054890 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC 12+ | PEPE1084843 | NWK | 1 | Bay | PE | SAN CARLOS | SM | 0024180404 | SAN CARLOS 0404 | O | Complete | No Constraint | 2023-08-31 | 2023-10-05 | 2023-09-29 | -5 | 3. Non-timely worked |  |  | 37.501076980 | -122.267458450 | [6 empty] | Delayed due to traffoc control approval.
-1056016318 | VMS | Distribution | M | Priority 2 (P2) | Blue Gum | ZFELL R1 | PEPE1085223 | NW | 1 | Bay | PE | MOSS BEACH | SM | 0024101102 | HALF MOON BAY 1102 | O | Complete | No Constraint | 2023-10-05 | 2023-11-08 | 2023-11-02 | -5 | 3. Non-timely worked |  |  | 37.529047440 | -122.484830770 | 3 | [5 empty] | GGNRA. Vendor reported tree complete on arrival.
-1056117757 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | PEPE1084142 | NWK | 1 | Bay | PE | LA HONDA | SM | 0028881103 | ALPINE-MENLO | O | Complete | No Constraint | 2023-07-14 | 2023-12-12 | 2023-08-11 | -88 | 3. Non-timely worked |  |  | 37.300395170 | -122.265630070 | 2 | [5 empty] | Reported complete by vendor 8/11/23 via email. Closed late as No Work.
-1056076056 | VMS | Distribution | M | Priority 2 (P2) | Blue Gum | ZRC 12+ | PEPE1084607 | NW | 1 | Bay | PE | SAN BRUNO | SM | 0022721106 | SNEATH LANE 1106 | O | Complete | Constraint_ITS_past | 2023-08-17 | 2023-11-07 | 2023-11-06 | -2 | 3. Non-timely worked |  |  | 37.630285530 | -122.438879540 |  | 612676 | RFT905090418 | Refusal | CLOSE | 2023-10-09 | Tree was trimmed 10/6/23 per ITS record. Crew that closed it as No Work found it to be complete on arrival. Data entry delay.
-1056039911 | VMS | Distribution | M | Priority 2 (P2) | Birch | ZRC 12+ | PEPE1084969 | NWK | 1 | Bay | PE | MENLO PARK | SM | 0024020405 | BELL HAVEN 0405 | O | Complete | No Constraint | 2023-09-14 | 2023-11-01 | 2023-10-12 | -15 | 3. Non-timely worked |  |  | 37.464067630 | -122.170900700 | [6 empty] | Trees mitigated with P1's at same address on 9/14.
-1056039922 | VMS | Distribution | M | Priority 2 (P2) | Birch | ZRC 12+ | PEPE1084969 | NWK | 1 | Bay | PE | MENLO PARK | SM | 0024020405 | BELL HAVEN 0405 | O | Complete | No Constraint | 2023-09-14 | 2023-11-01 | 2023-10-12 | -15 | 3. Non-timely worked |  |  | 37.464076630 | -122.170886390 | [6 empty] | Trees mitigated with P1's at same address on 9/14.
-1056024097 | VMS | Distribution | M | Priority 2 (P2) | Brush (misc) | ZR CLEAR | PEPE1085148 | BPG | 1 | Bay | PE | PORTOLA VAL | SM | 0024251101 | WOODSIDE 1101 | O | Complete | No Constraint | 2023-09-28 | 2023-10-27 | 2023-10-26 | -2 | 3. Non-timely worked |  |  | 37.389588310 | -122.239829270 | 3 | [5 empty] | Unit completed late by vendor.
-1056115454 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZFELL R5 | PEPE1084160 | FT5 | 1 | Bay | PE | MONTARA | SM | 0024101102 | HALF MOON BAY 1102 | O | Complete | No Constraint | 2023-07-17 | 2023-08-29 | 2023-08-14 | -12 | 3. Non-timely worked |  |  | 37.533734750 | -122.492076250 | 3 | [5 empty] | Unit completed late by vendor.
-1056190448 | VMS | Distribution | M | Priority 2 (P2) | Willow | ZMAJOR R1 | PEPE1083596 | MA1 | 1 | Bay | PE | PESCADERO | SM | 0024101103 | HALF MOON BAY 1103 | O | Complete | No Constraint | 2023-06-14 | 2023-10-09 | 2023-07-14 | -62 | 3. Non-timely worked |  |  | 37.270158650 | -122.384919640 | 2 | [5 empty] | Unit completed late by vendor.
-1056095942 | VMS | Distribution | M | Priority 2 (P2) | Canyon Live Oak | ZMAJOR R2 | PEPE1084368 | MA2 | 1 | Bay | PE | ATHERTON | SM | 0024090404 | GLENWOOD 0404 | O | Complete | No Constraint | 2023-08-01 | 2023-08-30 | 2023-08-29 | -2 | 3. Non-timely worked |  |  | 37.463579110 | -122.209533270 | [6 empty] | Unit completed late by vendor.
-1057864738 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZPRUNE R3 | PEPE1081519 | MN3 | 1 | Bay | PE | REDWOOD CIT | SM | 0024251102 | WOODSIDE 1102 | O | Complete | No Constraint | 2023-01-17 | 2023-02-16 | 2023-02-14 | -3 | 3. Non-timely worked |  |  | 37.455635320 | -122.242414800 | [6 empty] | Unit completed late by vendor.
-1056024026 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZPRUNE R3 | PEPE1085148 | MN3 | 1 | Bay | PE | PORTOLA VAL | SM | 0024251101 | WOODSIDE 1101 | O | Complete | No Constraint | 2023-09-28 | 2023-10-27 | 2023-10-26 | -2 | 3. Non-timely worked |  |  | 37.389296520 | -122.240107000 | 3 | [5 empty] | Unit completed late by vendor.
-1056226684 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | EBDI1043227 | RD1 | 1 | Bay | DI | MARTINEZ | CC | 0014101105 | ALHAMBRA 1105 | O | Complete | Constraint_ITS_past | 2023-06-01 | 2023-09-06 | 2023-08-25 | -9 | 3. Non-timely worked |  |  | 37.959762000 | -122.109297000 |  | 602302 | RFT602140641 | Refusal | CLOSE | 2023-07-28 | Vendor Billing Error
-1056273886 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | EBDI1042911 | RD2 | 1 | Bay | DI | WALNUT CREE | CC | 0012022215 | CLAYTON 2215 | O | Complete | Constraint_ITS_past | 2023-05-09 | 2023-08-21 | 2023-08-14 | -6 | 3. Non-timely worked |  |  | 37.957171200 | -122.030232870 |  | 602468 | RFT605204335 | Refusal | CLOSE | 2023-07-17 | Vendor Billing Error
-1056052554 | VMS | Distribution | M | Priority 2 (P2) | Black Walnut | ZRC 12+ | EBDI1043489 | RD2 | 1 | Bay | DI | LAFAYETTE | CC | 0014671102 | SOBRANTE 1102 | O | Complete | Constraint_ITS_past | 2023-09-05 | 2024-08-07 | 2023-12-13 | -171 | 3. Non-timely worked |  |  | 37.905941860 | -122.156920820 | 2 | 614689 | RFT927085451 | Refusal | CLOSE | 2023-11-13 | Vendor Billing Error
-1056089504 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | EBDI1043324 | NWK | 1 | Bay | DI | DANVILLE | CC | 0014692101 | RESEARCH 2101 | O | Complete | No Constraint | 2023-08-07 | 2023-09-06 | 2023-09-05 | -2 | 3. Non-timely worked |  |  | 37.807135990 | -121.983050030 | [6 empty] | Vendor Billing Error
-1056060928 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | EBDI1043458 | NWK | 1 | Bay | DI | ALAMO | CC | 0013580401 | ROBLES 0401 | O | Complete | No Constraint | 2023-08-30 | 2023-10-04 | 2023-09-28 | -5 | 3. Non-timely worked |  |  | 37.858747140 | -122.036133140 | [6 empty] | Vendor Billing Error
-1056056107 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | EBDI1043458 | NWK | 1 | Bay | DI | ALAMO | CC | 0013580401 | ROBLES 0401 | O | Complete | No Constraint | 2023-08-31 | 2023-10-09 | 2023-09-29 | -7 | 3. Non-timely worked |  |  | 37.857140460 | -122.033668030 | [6 empty] | Vendor Billing Error
-1056056113 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | EBDI1043458 | NWK | 1 | Bay | DI | ALAMO | CC | 0013580401 | ROBLES 0401 | O | Complete | No Constraint | 2023-08-31 | 2023-10-09 | 2023-09-29 | -7 | 3. Non-timely worked |  |  | 37.857203750 | -122.033457820 | [6 empty] | Vendor Billing Error
-1056056131 | VMS | Distribution | M | Priority 2 (P2) | Fruit Tree | ZRC to 11 | EBDI1043458 | NWK | 1 | Bay | DI | ALAMO | CC | 0013580401 | ROBLES 0401 | O | Complete | No Constraint | 2023-08-31 | 2023-10-09 | 2023-09-29 | -7 | 3. Non-timely worked |  |  | 37.857224640 | -122.033401480 | [6 empty] | Vendor Billing Error
-1056053006 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | EBDI1043484 | NWK | 1 | Bay | DI | MARTINEZ | CC | 0014101105 | ALHAMBRA 1105 | O | Complete | No Constraint | 2023-09-05 | 2023-10-09 | 2023-10-03 | -5 | 3. Non-timely worked |  |  | 37.975033540 | -122.127091490 | 2 | [5 empty] | Vendor Billing Error
-1056052844 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | EBDI1043486 | RD1 | 1 | Bay | DI | CONCORD | CC | 0014652109 | TIDEWATER 2109 | O | Complete | No Constraint | 2023-09-05 | 2023-10-04 | 2023-10-03 | -2 | 3. Non-timely worked |  |  | 37.949244360 | -122.017166950 | [6 empty] | Vendor Billing Error
-1056053040 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | EBDI1043484 | RD1 | 1 | Bay | DI | MARTINEZ | CC | 0014101105 | ALHAMBRA 1105 | O | Complete | No Constraint | 2023-09-05 | 2023-10-04 | 2023-10-03 | -2 | 3. Non-timely worked |  |  | 37.976039280 | -122.125795180 | 2 | [5 empty] | Vendor Billing Error
-1056055025 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | EBDI1043480 | RD2 | 1 | Bay | DI | WALNUT CREE | CC | 0013532112 | LAKEWOOD 2112 | O | Complete | No Constraint | 2023-08-31 | 2023-10-02 | 2023-09-29 | -2 | 3. Non-timely worked |  |  | 37.922321140 | -122.046195340 | [6 empty] | Vendor Billing Error
-1056052517 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC to 11 | EBMI1032465 | RD1 | 1 | Bay | MI | FREMONT | AL | 0013501111 | JARVIS 1111 | O | Complete | No Constraint | 2023-09-05 | 2023-10-04 | 2023-10-03 | -2 | 3. Non-timely worked |  |  | 37.578404230 | -121.997502640 | [6 empty] | Vendor Billing Error
-1056052089 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | EBMI1032468 | RD2 | 1 | Bay | MI | PLEASANTON | CC | 0014052103 | NORTH DUBLIN 2103 | O | Complete | No Constraint | 2023-09-05 | 2023-10-05 | 2023-10-03 | -3 | 3. Non-timely worked |  |  | 37.741573040 | -121.870036760 | 2 | [5 empty] | Vendor Billing Error
-1056044358 | VMS | Distribution | M | Priority 2 (P2) | Evergreen Ash | ZRC 12+ | EBMI1032488 | RD2 | 1 | Bay | MI | FREMONT | AL | 0014722109 | DIXON LANDING 2109 | O | Complete | No Constraint | 2023-09-11 | 2023-10-10 | 2023-10-09 | -2 | 3. Non-timely worked |  |  | 37.478948690 | -121.919096020 | [6 empty] | Vendor Billing Error
-1056044677 | VMS | Distribution | M | Priority 2 (P2) | Raywood Ash | ZRC 12+ | EBMI1032488 | RD2 | 1 | Bay | MI | FREMONT | AL | 0014722109 | DIXON LANDING 2109 | O | Complete | No Constraint | 2023-09-11 | 2023-10-10 | 2023-10-09 | -2 | 3. Non-timely worked |  |  | 37.475035160 | -121.912945420 | [6 empty] | Vendor Billing Error
-1056044924 | VMS | Distribution | M | Priority 2 (P2) | Evergreen Ash | ZRC 12+ | EBMI1032484 | RD2 | 1 | Bay | MI | UNION CITY | AL | 0014471108 | DUMBARTON 1108 | O | Complete | No Constraint | 2023-09-11 | 2023-10-10 | 2023-10-09 | -2 | 3. Non-timely worked |  |  | 37.589666070 | -122.047354170 | [6 empty] | Vendor Billing Error
-1056442583 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZOVPR to20 | PEPE1082586 | NWK | 1 | Bay | PE | SAN MATEO | SM | 0024040403 | BERESFORD 0403 | O | Complete | Constraint_ITS_past | 2023-03-31 | 2023-11-07 | 2023-10-13 | -18 | 3. Non-timely worked |  |  | 37.556509000 | -122.328380000 |  | 596072 | RFT428095527 | Refusal | CLOSE | 2023-06-22 | Vendor data entry delay.
-1056219477 | VMS | Distribution | M | Priority 2 (P2) | Liq Ambar (Sw Gum) | ZRC to 11 | PEPE1083332 | RD1 | 1 | Bay | PE | MENLO PARK | SM | 0024020404 | BELL HAVEN 0404 | O | Complete | Constraint_ITS_past | 2023-06-07 | 2023-09-11 | 2023-07-07 | -47 | 3. Non-timely worked | [5 empty] | 599631 | RFT516125404 | Refusal | CLOSE | 2023-06-02 | Vendor data entry delay.
-1056021943 | VMS | Distribution | M | Priority 2 (P2) | Palm-Date | ZRC 12+ | PEPE1085157 | RD2 | 1 | Bay | PE | PACIFICA | SM | 0022811102 | PACIFICA 1102 | O | Complete | No Constraint | 2023-10-02 | 2023-10-31 | 2023-10-30 | -2 | 3. Non-timely worked |  |  | 37.604189570 | -122.489022290 | [6 empty] | Vendor failed to complete timely
-1055971646 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZMOV to 60 | PEPE1085777 | UOC | 1 | Bay | PE | WOODSIDE | SM | 0024251101 | WOODSIDE 1101 | O | Complete | No Constraint | 2023-11-29 | 2023-12-29 | 2023-12-28 | -2 | 3. Non-timely worked |  |  | 37.387576860 | -122.255736860 | 3 | [5 empty] | Vendor failed to complete timely
-1056021795 | VMS | Distribution | M | Priority 2 (P2) | Pine | ZRC to 11 | PESF1015233 | RD1 | 1 | Bay | SF | SAN FRANCIS | SF | 0022270403 | SUBSTATION M 0403 | O | Complete | No Constraint | 2023-10-02 | 2023-10-31 | 2023-10-30 | -2 | 3. Non-timely worked |  |  | 37.736293510 | -122.448583430 | [6 empty] | Vendor failed to complete timely
-1056016706 | VMS | Distribution | M | Priority 2 (P2) | Willow | ZRC 12+ | PEPE1085216 | RD2 | 1 | Bay | PE | HALF MOON B | SM | 0024101101 | HALF MOON BAY 1101 | O | Complete | No Constraint | 2023-10-05 | 2023-11-03 | 2023-11-02 | -2 | 3. Non-timely worked |  |  | 37.491949960 | -122.386486170 | 2 | [5 empty] | Vendor failed to complete timely and traffic issue
-1056008985 | VMS | Distribution | M | Priority 2 (P2) | Casuarina | ZRC 12+ | PEPE1085271 | RD2 | 1 | Bay | PE | BURLINGAME | SM | 0024050405 | BURLINGAME 0405 | O | Complete | No Constraint | 2023-10-11 | 2023-11-20 | 2023-11-08 | -9 | 3. Non-timely worked |  |  | 37.588910200 | -122.366913330 |  | Access Issue | ACC109144417 |  |  |  | Vendor failed to complete timely and traffic issue
-1056079507 | VMS | Distribution | M | Priority 2 (P2) | Monterey Pine | ZMAJOR R4 | EBDI1043356 | MA4 | 1 | Bay | DI | ORINDA | CC | 0013801103 | MORAGA 1103 | O | Complete | No Constraint | 2023-08-15 | 2023-09-22 | 2023-09-13 | -8 | 3. Non-timely worked |  |  | 37.851297600 | -122.155852070 | [6 empty] | Vendor failed to complete timely.
-1056072260 | VMS | Distribution | M | Priority 2 (P2) | Ash | ZRC 12+ | EBDI1043395 | RD2 | 1 | Bay | DI | CONCORD | CC | 0012022217 | CLAYTON 2217 | O | Complete | No Constraint | 2023-08-22 | 2023-09-22 | 2023-09-20 | -3 | 3. Non-timely worked |  |  | 37.961044840 | -122.001368240 | [6 empty] | Vendor failed to complete timely.
-1056948225 | VMS | Distribution | M | Priority 2 (P2) | Blue Gum | ZRC to 11 | PEPE1081915 | RD1 | 1 | Bay | PE | BURLINGAME | SM | 0024192102 | SAN MATEO 2102 | O | Complete | No Constraint | 2023-02-27 | 2023-03-30 | 2023-03-27 | -4 | 3. Non-timely worked |  |  | 37.591785470 | -122.358310790 | [6 empty] | Vendor failed to complete timely.
-1056950028 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC to 11 | PEPE1081914 | RD1 | 1 | Bay | PE | SAN MATEO | SM | 0024190409 | SAN MATEO 0409 | O | Complete | No Constraint | 2023-02-27 | 2023-03-30 | 2023-03-27 | -4 | 3. Non-timely worked |  |  | 37.576675960 | -122.330399980 | [6 empty] | Vendor failed to complete timely.
-1056151904 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | PEPE1083938 | RD1 | 1 | Bay | PE | BRISBANE | SM | 0022571109 | EAST GRAND 1109 | O | Complete | No Constraint | 2023-07-06 | 2023-08-14 | 2023-08-03 | -8 | 3. Non-timely worked |  |  | 37.677755810 | -122.398582830 | [6 empty] | Vendor failed to complete timely.
-1056151906 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | PEPE1083938 | RD1 | 1 | Bay | PE | BRISBANE | SM | 0022571109 | EAST GRAND 1109 | O | Complete | No Constraint | 2023-07-06 | 2023-08-16 | 2023-08-03 | -10 | 3. Non-timely worked |  |  | 37.677749120 | -122.398606040 | [6 empty] | Vendor failed to complete timely.
-1055975401 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | PEPE1085776 | RD1 | 1 | Bay | PE | ATHERTON | SM | 0024160406 | REDWOOD CITY 0406 | O | Complete | No Constraint | 2023-11-21 | 2024-01-02 | 2023-12-21 | -9 | 3. Non-timely worked |  |  | 37.464920500 | -122.212655950 | [6 empty] | Vendor failed to complete timely.
-1056673281 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | PEPE1082215 | RD2 | 1 | Bay | PE | WOODSIDE | SM | 0024251101 | WOODSIDE 1101 | O | Complete | No Constraint | 2023-03-09 | 2023-04-07 | 2023-04-06 | -2 | 3. Non-timely worked |  |  | 37.385909200 | -122.261291400 | 3 | [5 empty] | Vendor failed to complete timely.
-1056448799 | VMS | Distribution | M | Priority 2 (P2) | Red Gum | ZRC 12+ | PEPE1082575 | RD2 | 1 | Bay | PE | SAN MATEO | SM | 0024030403 | BELMONT 0403 | O | Complete | No Constraint | 2023-03-30 | 2023-04-28 | 2023-04-27 | -2 | 3. Non-timely worked |  |  | 37.528194910 | -122.292514530 | [6 empty] | Vendor failed to complete timely.
-1056400132 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | PEPE1082609 | RD2 | 1 | Bay | PE | PACIFICA | SM | 0022721107 | SNEATH LANE 1107 | O | Complete | No Constraint | 2023-04-11 | 2023-05-13 | 2023-05-09 | -4 | 3. Non-timely worked |  |  | 37.634007000 | -122.475222920 | 2 | [5 empty] | Vendor failed to complete timely.
-1056172338 | VMS | Distribution | M | Priority 2 (P2) | Monterey Pine | ZRC 12+ | PEPE1083921 | RD2 | 1 | Bay | PE | PACIFICA | SM | 0022811102 | PACIFICA 1102 | O | Complete | No Constraint | 2023-06-21 | 2023-07-22 | 2023-07-20 | -2 | 3. Non-timely worked |  |  | 37.621519000 | -122.478663000 | 3 | [5 empty] | Vendor failed to complete timely.
-1056049440 | VMS | Distribution | M | Priority 2 (P2) | Acacia | ZRC 12+ | PEPE1084944 | RD2 | 1 | Bay | PE | REDWOOD CIT | SM | 0024251104 | WOODSIDE 1104 | O | Complete | No Constraint | 2023-09-07 | 2023-10-06 | 2023-10-05 | -2 | 3. Non-timely worked |  |  | 37.450183710 | -122.254975960 | [6 empty] | Vendor failed to complete timely.
-1056023543 | VMS | Distribution | M | Priority 2 (P2) | Chinese Elm | ZRC 12+ | PEPE1085146 | RD2 | 1 | Bay | PE | MILLBRAE | SM | 0022691108 | MILLBRAE 1108 | O | Complete | No Constraint | 2023-09-28 | 2023-10-30 | 2023-10-26 | -3 | 3. Non-timely worked |  |  | 37.610650000 | -122.418440490 | [6 empty] | Vendor failed to complete timely.
-1056022604 | VMS | Distribution | M | Priority 2 (P2) | Elm, American | ZRC 12+ | PEPE1085154 | RD2 | 1 | Bay | PE | BURLINGAME | SM | 0022691107 | MILLBRAE 1107 | O | Complete | No Constraint | 2023-09-29 | 2023-10-28 | 2023-10-27 | -1 | 3. Non-timely worked |  |  | 37.590628950 | -122.376773790 | [6 empty] | Vendor failed to complete timely.
-1056043678 | VMS | Distribution | M | Priority 2 (P2) | Monterey Cypress | ZRC to 11 | PESF1015205 | RD1 | 1 | Bay | SF | SAN FRANCIS | SF | 0022011113 | MISSION 1113 | O | Complete | No Constraint | 2023-09-12 | 2023-10-31 | 2023-10-10 | -16 | 3. Non-timely worked |  |  | 37.763617710 | -122.442048410 | [6 empty] | Vendor failed to complete timely/Traffic control needed
-1056001504 | VMS | Distribution | M | Priority 2 (P2) | Palm | ZRC to 11 | PEPE1085556 | RD1 | 1 | Bay | PE | REDWOOD CIT | SM | 0024080401 | EMERALD LAKE 0401 | O | Complete | No Constraint | 2023-10-17 | 2023-11-16 | 2023-11-15 | -2 | 3. Non-timely worked |  |  | 37.457757000 | -122.267194000 | 2 | [5 empty] | Vendor failed to complete timely; not reported complete 11/15/23.
-1056040500 | VMS | Distribution | M | Priority 2 (P2) | Silver Dollar Gum | ZRC 12+ | PEPE1084983 | NWK | 1 | Bay | PE | PESCADERO | SM | 0024101103 | HALF MOON BAY 1103 | O | Complete | No Constraint | 2023-09-13 | 2023-10-20 | 2023-10-11 | -8 | 3. Non-timely worked |  |  | 37.327100050 | -122.363854100 | 2 | [5 empty] | Vendor indicated constraint that was not valid and not applied.
-1056174620 | VMS | Distribution | M | Priority 2 (P2) | Monterey Cypress | ZRC to 11 | PEPE1083700 | RD1 | 1 | Bay | PE | PESCADERO | SM | 0024101103 | HALF MOON BAY 1103 | O | Complete | No Constraint | 2023-06-20 | 2023-08-02 | 2023-07-19 | -11 | 3. Non-timely worked |  |  | 37.259679520 | -122.322367000 | 2 | [5 empty] | Vendor reported complete on arrival and closed late. Data entry delay.
-1056029802 | VMS | Distribution | M | Priority 2 (P2) | Oak | ZRC to 11 | PEPE1085083 | RD1 | 1 | Bay | PE | SAN CARLOS | SM | 0024031103 | BELMONT 1103 | O | Complete | No Constraint | 2023-09-21 | 2023-10-31 | 2023-10-19 | -9 | 3. Non-timely worked |  |  | 37.496435850 | -122.279889380 | 2 | [5 empty] | Vendor reported complete on arrival when field checked 10/31.
-1056026170 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | PESF1015247 | RD2 | 1 | Bay | SF | SAN FRANCIS | SF | 0022280408 | SUBSTATION N 0408 | O | Complete | No Constraint | 2023-09-26 | 2023-10-31 | 2023-10-24 | -6 | 3. Non-timely worked |  |  | 37.748922190 | -122.463370450 | [6 empty] | Vendor reported completed 10/24/23; delayed closure.
-1056074933 | VMS | Distribution | M | Priority 2 (P2) | Monterey Pine | ZRC to 11 | PEPE1084659 | RD1 | 1 | Bay | PE | REDWOOD CIT | SM | 0024251104 | WOODSIDE 1104 | O | Complete | No Constraint | 2023-08-18 | 2023-10-12 | 2023-10-09 | -4 | 3. Non-timely worked |  |  | 37.458808170 | -122.256421630 | 2 | [5 empty] | Vendor reported tree complete 9/18 via email. Closed with incorrect date. Data entry delay.
-1056021461 | VMS | Distribution | M | Priority 2 (P2) | Red Ironbark | ZRC 12+ | PEPE1085158 | RD2 | 1 | Bay | PE | PORTOLA VAL | SM | 0024131102 | MENLO 1102 | O | Complete | No Constraint | 2023-10-02 | 2023-10-31 | 2023-10-30 | -2 | 3. Non-timely worked |  |  | 37.400901370 | -122.192696380 | [6 empty] | Vendor worked 10/31/23; Vendor failed to complete timely.
-1056021701 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | PEPE1085159 | RD2 | 1 | Bay | PE | SAN BRUNO | SM | 0022691108 | MILLBRAE 1108 | O | Complete | No Constraint | 2023-10-02 | 2023-10-31 | 2023-10-30 | -2 | 3. Non-timely worked |  |  | 37.618799220 | -122.424204670 | [6 empty] | Vendor worked 10/31/23; Vendor failed to complete timely.
-1056021916 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | PEPE1085129 | RD2 | 1 | Bay | PE | SKY LONDA | SM | 0024251101 | WOODSIDE 1101 | O | Complete | No Constraint | 2023-10-02 | 2023-10-31 | 2023-10-30 | -2 | 3. Non-timely worked |  |  | 37.388058000 | -122.269922000 | 3 | [5 empty] | Vendor worked 10/31/23; Vendor failed to complete timely.
-1056021917 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | PEPE1085159 | RD2 | 1 | Bay | PE | SAN BRUNO | SM | 0022691108 | MILLBRAE 1108 | O | Complete | No Constraint | 2023-10-02 | 2023-11-01 | 2023-10-30 | -3 | 3. Non-timely worked |  |  | 37.616141020 | -122.422239260 | [6 empty] | Vendor worked 11/01/23; Vendor failed to complete timely.
-1056022558 | VMS | Distribution | M | Priority 2 (P2) | Mulberry | ZRC 12+ | EBMI1032535 | NWK | 1 | Bay | MI | PLEASANTON | AL | 0014502109 | VINEYARD 2109 | O | Complete | No Constraint | 2023-09-29 | 2023-11-01 | 2023-10-27 | -4 | 3. Non-timely worked |  |  | 37.672258140 | -121.878857580 | [6 empty] | Worked as a P1. Data entry delay.
-1056023136 | VMS | Distribution | M | Priority 2 (P2) | Pistache | ZRC 12+ | EBMI1032535 | NWK | 1 | Bay | MI | PLEASANTON | AL | 0014502109 | VINEYARD 2109 | O | Complete | No Constraint | 2023-09-29 | 2023-11-01 | 2023-10-27 | -4 | 3. Non-timely worked |  |  | 37.672245620 | -121.880293020 | [6 empty] | Worked as a P1. P2 work request edited after due date. Data entry delay.

## Central Coast
iTreeRecsID | Source | Circuit type | sAcctType | PRIORITY | Tree_Type | TRIM_TYPE | sWorkReq | ActualTrimCode | Tree_Qty | Region | Division | sCity | sCountyCode | scircuit | CIRCUIT | sNotification | Completion status - field | Constraint? | dtInspDate | dtWorkDate | Due date per compliance | Business Days Between Work Date and Compliance Date | Timeliness status | Location_Lat | Location_Long | Tree_Lat | Tree_Long | iHFTDTier | iRefusalID | sDocNumber | REFUSAL_TYPE | sRefusalStatus | dtResolved | Reason for Completion after Compliance Due Date
-1056151389 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | CCCC1165735 | RD1 | 1 | Central Coast | CC | APTOS | SZ | 0083692104 | ROB ROY 2104 | O | Complete | Constraint_ITS_past | 2023-07-06 | 2023-09-08 | 2023-09-05 | -4 | 3. Non-timely worked |  |  | 37.001804060 | -121.871820790 | 3 | 608949 | ACC803160721 | Access Issue | CLOSE | 2023-08-07 | Data Entry Error. Tree was completed on time and verified via field check.
-1056095351 | VMS | Distribution | M | Priority 2 (P2) | Maple | ZRC 12+ | CCCC1166358 | RD2 | 1 | Central Coast | CC | SCOTTS VALL | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | Constraint_ITS_past | 2023-08-01 | 2024-04-05 | 2024-03-18 | -15 | 3. Non-timely worked |  |  | 37.072999270 | -121.989742730 | 3 | 612241 | GCD829103759 | Encroachment Permit | RSLVD | 2024-02-02 | Vendor Billing Error
-1056107759 | VMS | Distribution | M | Priority 2 (P2) | Oak | ZMAJOR R2 | CCCC1166209 | MA2 | 1 | Central Coast | CC | CORRALITOS | SZ | 0083692104 | ROB ROY 2104 | O | Complete | No Constraint | 2023-07-21 | 2023-08-21 | 2023-08-18 | -2 | 3. Non-timely worked |  |  | 37.040651100 | -121.813715430 | 3 | [5 empty] | Vendor Billing Error
-1056476954 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZMAJOR R3 | CCCC1163351 | MA3 | 1 | Central Coast | CC | SOQUEL | SZ | 0083252106 | PAUL SWEET 2106 | O | Complete | No Constraint | 2023-03-23 | 2023-04-24 | 2023-04-20 | -3 | 3. Non-timely worked |  |  | 37.050318080 | -121.928704270 | 3 | [5 empty] | Unit completed late by vendor.
-1056554235 | VMS | Distribution | M | Priority 2 (P2) | Monterey Cypress | ZPRUNE R1 | CCCC1162694 | MN1 | 1 | Central Coast | CC | APTOS | SZ | 0083252106 | PAUL SWEET 2106 | O | Complete | No Constraint | 2023-03-14 | 2023-04-23 | 2023-04-11 | -9 | 3. Non-timely worked |  |  | 36.978473890 | -121.918505210 | [6 empty] | Vendor Billing Error
-1056229124 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC to 11 | CCCC1164832 | RD1 | 1 | Central Coast | CC | APTOS | SZ | 0083692104 | ROB ROY 2104 | O | Complete | No Constraint | 2023-05-31 | 2023-07-10 | 2023-06-29 | -8 | 3. Non-timely worked |  |  | 36.992191880 | -121.841799180 | 2 | [5 empty] | Vendor Billing Error
-1056116418 | VMS | Distribution | M | Priority 2 (P2) | Tan Oak | ZRC to 11 | CCCC1166083 | RD1 | 1 | Central Coast | CC | BEN LOMOND | SZ | 0083622105 | CAMP EVERS 2105 | O | Complete | No Constraint | 2023-07-13 | 2023-08-23 | 2023-08-10 | -10 | 3. Non-timely worked |  |  | 37.097048800 | -122.102298370 | 3 | [5 empty] | Vendor Billing Error
-1056097599 | VMS | Distribution | M | Priority 2 (P2) | Cedar | ZRC to 11 | CCCC1166401 | RD1 | 1 | Central Coast | CC | WATSONVILLE | SZ | 0083692104 | ROB ROY 2104 | O | Complete | No Constraint | 2023-07-26 | 2023-08-30 | 2023-08-23 | -6 | 3. Non-timely worked |  |  | 37.021053180 | -121.827417140 | 3 | [5 empty] | Vendor Billing Error
-1056081561 | VMS | Distribution | M | Priority 2 (P2) | Oak | ZRC to 11 | CCCC1166633 | RD1 | 1 | Central Coast | CC | SOQUEL | SZ | 0083252106 | PAUL SWEET 2106 | O | Complete | No Constraint | 2023-08-14 | 2023-09-13 | 2023-09-12 | -2 | 3. Non-timely worked |  |  | 37.025271940 | -121.932581900 | 3 | [5 empty] | Vendor Billing Error
-1056073601 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | CCCC1166802 | RD1 | 1 | Central Coast | CC | APTOS | SZ | 0083692105 | ROB ROY 2105 | O | Complete | No Constraint | 2023-08-21 | 2023-10-18 | 2023-09-19 | -22 | 3. Non-timely worked |  |  | 36.967626790 | -121.881677310 | 2 | [5 empty] | Vendor Billing Error
-1055978682 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | CCCC1168041 | RD1 | 1 | Central Coast | CC | BOULDER CRE | SZ | 0082841102 | BIG BASIN 1102 | O | Complete | No Constraint | 2023-11-14 | 2024-01-17 | 2023-12-14 | -25 | 3. Non-timely worked |  |  | 37.136602870 | -122.141731240 | 3 | [5 empty] | Vendor Billing Error
-1055978774 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | CCCC1168041 | RD1 | 1 | Central Coast | CC | BOULDER CRE | SZ | 0082841102 | BIG BASIN 1102 | O | Complete | No Constraint | 2023-11-14 | 2024-01-17 | 2023-12-14 | -25 | 3. Non-timely worked |  |  | 37.132969670 | -122.138609880 | 3 | [5 empty] | Vendor Billing Error
-1057054468 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | CCCC1162391 | RD2 | 1 | Central Coast | CC | CORRALITOS | SZ | 0083192101 | GREEN VALLEY 2101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.005194870 | -121.768709560 | 2 | [5 empty] | Vendor Billing Error
-1056052970 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | CECC1004124 | RD2 | 1 | Central Coast | CC | SANTA CRUZ | SZ | 0083622104 | CAMP EVERS 2104 | O | Complete | No Constraint | 2023-06-23 | 2023-09-07 | 2023-07-24 | -34 | 3. Non-timely worked |  |  | 37.023834050 | -121.988415400 | 3 | [5 empty] | Vendor Billing Error
-1056165243 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | CCCC1165364 | RD2 | 1 | Central Coast | CC | BOULDER CRE | SZ | 0082841101 | BIG BASIN 1101 | O | Complete | No Constraint | 2023-06-23 | 2023-08-11 | 2023-07-24 | -15 | 3. Non-timely worked |  |  | 37.150026890 | -122.104637200 | 3 | [5 empty] | Vendor Billing Error
-1056034037 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | CCCC1167308 | RD2 | 1 | Central Coast | CC | WATSONVILLE | SZ | 0083192101 | GREEN VALLEY 2101 | O | Complete | No Constraint | 2023-09-18 | 2023-10-17 | 2023-10-16 | -2 | 3. Non-timely worked |  |  | 37.005332230 | -121.722673400 | 3 | [5 empty] | Unit completed late by vendor.
-1056028445 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | CCCC1167382 | RD2 | 1 | Central Coast | CC | BROOKDALE | SZ | 0083041101 | BEN LOMOND 1101 | O | Complete | No Constraint | 2023-09-21 | 2023-11-28 | 2023-10-19 | -29 | 3. Non-timely worked |  |  | 37.107177000 | -122.108142000 | 3 | [5 empty] | Vendor Billing Error
-1056028444 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | CCCC1167382 | RD2 | 1 | Central Coast | CC | BROOKDALE | SZ | 0083041101 | BEN LOMOND 1101 | O | Complete | No Constraint | 2023-09-22 | 2023-11-28 | 2023-10-20 | -28 | 3. Non-timely worked |  |  | 37.107451730 | -122.107927090 | 3 | [5 empty] | Vendor Billing Error
-1055993155 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | CCCC1167838 | RD2 | 1 | Central Coast | CC | CASTROVILLE | MO | 0182381101 | DOLAN ROAD 1101 | O | Complete | No Constraint | 2023-10-24 | 2023-12-05 | 2023-11-22 | -10 | 3. Non-timely worked |  |  | 36.795047090 | -121.718174060 | [6 empty] | Vendor Billing Error
-1056229125 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | CCCC1164832 | U02 | 1 | Central Coast | CC | APTOS | SZ | 0083692104 | ROB ROY 2104 | O | Complete | No Constraint | 2023-05-31 | 2023-07-08 | 2023-06-29 | -7 | 3. Non-timely worked |  |  | 36.991629820 | -121.841085280 | 2 | [5 empty] | Vendor Billing Error
-1057842929 | VMS | Distribution | M | Priority 2 (P2) | Vine | Br Trim | DADA1076221 | BT | 1 | Central Coast | DA | LOS GATOS | SC | 0083771102 | VASONA 1102 | O | Complete | Constraint_ITS_past | 2023-01-18 | 2023-03-29 | 2023-02-15 | -31 | 3. Non-timely worked |  |  | 37.243248000 | -121.963718000 |  | 547248 | CLR629110606 | Clearance Request | CLOSE | 2022-03-29 | Unit completed late by vendor.
-1057844417 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | Side | DADA1076213 | NW | 1 | Central Coast | DA | SARATOGA | SC | 0083371106 | SARATOGA 1106 | O | Complete | Constraint_ITS_past | 2023-01-18 | 2023-04-17 | 2023-02-15 | -44 | 3. Non-timely worked |  |  | 37.246956000 | -122.009945000 |  | 559379 | CLR912083010 | Clearance Request | CLOSE | 2022-09-15 | Unit completed late by vendor.
-1057843095 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | FP-Trim B | DADA1076219 | NWK | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | Constraint_ITS_past | 2023-01-18 | 2023-07-10 | 2023-02-15 | -104 | 3. Non-timely worked |  |  | 37.352861000 | -122.070479000 |  | 540392 | CLR523161534 | Clearance Request | CLOSE | 2022-07-09 | Unit completed late by vendor.
-1058064364 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | Side | DADA1075866 | SD | 1 | Central Coast | DA | SUNNYVALE | SC | 0083671113 | WOLFE 1113 | O | Complete | Constraint_ITS_past | 2023-01-04 | 2023-07-12 | 2023-02-02 | -115 | 3. Non-timely worked |  |  | 37.358181000 | -122.036455000 |  | 564192 | CLR014100546 | Clearance Request | CLOSE | 2022-10-21 | Unit completed late by vendor.
-1056218485 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZR PRUNE | DADA1077270 | BP1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-07 | 2023-07-11 | 2023-07-07 | -3 | 3. Non-timely worked |  |  | 37.163221990 | -121.981160180 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056196334 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZR PRUNE | DADA1077297 | BP1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-08 | 2023-07-12 | 2023-07-10 | -3 | 3. Non-timely worked |  |  | 37.153830000 | -121.987490000 | 3 | [5 empty] | Unit completed late by vendor.
-1057066830 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZR CLEAR | DADA1076430 | BPG | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-02-20 | 2023-03-31 | 2023-03-20 | -10 | 3. Non-timely worked |  |  | 37.157127240 | -122.019059040 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056032834 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZR CLEAR | DADA1077902 | BPG | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.250012750 | -122.067994770 | 3 | [5 empty] | Unit completed late by vendor.
-1056220750 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZMAJOR R1 | DADA1077270 | MA1 | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-06 | 2023-07-11 | 2023-07-06 | -4 | 3. Non-timely worked |  |  | 37.133593890 | -121.975088920 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056070654 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZMAJOR R1 | DADA1077705 | MA1 | 1 | Central Coast | DA | LOS GATOS | SZ | 0083481110 | STELLING 1110 | O | Complete | No Constraint | 2023-08-23 | 2023-11-01 | 2023-09-21 | -30 | 3. Non-timely worked |  |  | 37.253238430 | -122.117138380 | 3 | [5 empty] | Unit completed late by vendor.
-1056032826 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R1 | DADA1077902 | MA1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.249838720 | -122.068019110 | 3 | [5 empty] | Unit completed late by vendor.
-1056032828 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R1 | DADA1077902 | MA1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.249774260 | -122.068058890 | 3 | [5 empty] | Unit completed late by vendor.
-1056032829 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R1 | DADA1077902 | MA1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.249756540 | -122.068073820 | 3 | [5 empty] | Unit completed late by vendor.
-1056032832 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R1 | DADA1077902 | MA1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.250000870 | -122.067953790 | 3 | [5 empty] | Unit completed late by vendor.
-1056032833 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R1 | DADA1077902 | MA1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.250032080 | -122.067992420 | 3 | [5 empty] | Unit completed late by vendor.
-1056032835 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R1 | DADA1077902 | MA1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.250034510 | -122.067906140 | 3 | [5 empty] | Unit completed late by vendor.
-1056032831 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R2 | DADA1077902 | MA2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.249675460 | -122.068043460 | 3 | [5 empty] | Unit completed late by vendor.
-1056032836 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R3 | DADA1077902 | MA3 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2024-04-02 | 2023-10-17 | -121 | 3. Non-timely worked |  |  | 37.250094840 | -122.067959350 | 3 | [5 empty] | Unit completed late by vendor.
-1056002064 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZMAJOR R3 | DADA1078153 | MA3 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481109 | STELLING 1109 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.295164880 | -122.060626620 | 2 | [5 empty] | Unit completed late by vendor.
-1056199419 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R4 | DADA1077306 | MA4 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-06-08 | 2023-07-31 | 2023-07-10 | -16 | 3. Non-timely worked |  |  | 37.265039830 | -122.100675360 | 2 | [5 empty] | Unit completed late by vendor.
-1056062312 | VMS | Distribution | M | Priority 2 (P2) | Locust, Black | ZPRUNE R1 | DADA1077730 | MN1 | 1 | Central Coast | DA | SAN JOSE | SC | 0083771103 | VASONA 1103 | O | Complete | No Constraint | 2023-08-29 | 2023-09-28 | 2023-09-27 | -2 | 3. Non-timely worked |  |  | 37.269903920 | -121.984669690 | [6 empty] | Unit completed late by vendor.
-1057283493 | VMS | Distribution | M | Priority 2 (P2) | Olive | ZRC to 11 | DADA1076418 | NWK | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481111 | STELLING 1111 | O | Complete | No Constraint | 2023-02-13 | 2024-02-07 | 2023-03-14 | -237 | 3. Non-timely worked |  |  | 37.335295460 | -122.072752340 | [6 empty] | Unit completed late by vendor.
-1057285715 | VMS | Distribution | M | Priority 2 (P2) | Palm-Date | ZRC 12+ | DADA1076419 | NWK | 1 | Central Coast | DA | SAN JOSE | SC | 0083481107 | STELLING 1107 | O | Complete | No Constraint | 2023-02-13 | 2024-02-07 | 2023-03-14 | -237 | 3. Non-timely worked |  |  | 37.310879320 | -122.030146560 | [6 empty] | Unit completed late by vendor.
-1056383432 | VMS | Distribution | M | Priority 2 (P2) | Cypress | ZRC 12+ | DADA1076902 | NWK | 1 | Central Coast | DA | LOS ALTOS H | SC | 0082161102 | LOYOLA 1102 | O | Complete | No Constraint | 2023-04-17 | 2023-06-05 | 2023-05-15 | -16 | 3. Non-timely worked |  |  | 37.373929150 | -122.141731510 | [6 empty] | Unit Constrained due to Storm Access.
-1056383437 | VMS | Distribution | M | Priority 2 (P2) | Red Ironbark | ZRC 12+ | DADA1076902 | NWK | 1 | Central Coast | DA | LOS ALTOS H | SC | 0082161102 | LOYOLA 1102 | O | Complete | No Constraint | 2023-04-17 | 2023-06-05 | 2023-05-15 | -16 | 3. Non-timely worked |  |  | 37.374160850 | -122.141877960 | [6 empty] | Unit Constrained due to Storm Access.
-1056359413 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1076927 | NWK | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-04-19 | 2023-05-18 | 2023-05-17 | -2 | 3. Non-timely worked |  |  | 37.105433670 | -121.946874640 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056359653 | VMS | Distribution | M | Priority 2 (P2) | Cypress | ZRC to 11 | DADA1076928 | NWK | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-04-19 | 2023-05-18 | 2023-05-17 | -2 | 3. Non-timely worked |  |  | 37.157530040 | -121.987371290 | 3 | [5 empty] | Unit completed late by vendor.
-1056359832 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1076927 | NWK | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-04-19 | 2023-05-18 | 2023-05-17 | -2 | 3. Non-timely worked |  |  | 37.105761680 | -121.946469340 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056347675 | VMS | Distribution | M | Priority 2 (P2) | Bigleaf Maple | ZRC 12+ | DADA1076936 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-04-21 | 2023-05-23 | 2023-05-19 | -3 | 3. Non-timely worked |  |  | 37.264401510 | -122.099964370 | 2 | [5 empty] | Unit completed late by vendor.
-1056255535 | VMS | Distribution | M | Priority 2 (P2) | Ash | ZRC to 11 | DADA1077097 | NWK | 1 | Central Coast | DA | SAN JOSE | SC | 0083771108 | VASONA 1108 | O | Complete | No Constraint | 2023-05-16 | 2023-06-17 | 2023-06-14 | -3 | 3. Non-timely worked |  |  | 37.249601200 | -121.942060730 | [6 empty] | Unit Constrained due to Storm Access.
-1056240896 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077126 | NWK | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-05-23 | 2024-02-07 | 2023-06-22 | -165 | 3. Non-timely worked |  |  | 37.340846440 | -122.065900130 | [6 empty] | Unit completed late by vendor.
-1056239477 | VMS | Distribution | M | Priority 2 (P2) | Avocado | ZRC to 11 | DADA1077115 | NWK | 1 | Central Coast | DA | SAN JOSE | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-05-24 | 2023-06-26 | 2023-06-23 | -2 | 3. Non-timely worked |  |  | 37.295385030 | -121.972864140 | [6 empty] | Unit completed late by vendor.
-1056230978 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077192 | NWK | 1 | Central Coast | DA | CAMPBELL | SC | 0082921104 | EL PATIO 1104 | O | Complete | No Constraint | 2023-05-30 | 2023-07-19 | 2023-06-28 | -16 | 3. Non-timely worked |  |  | 37.287569390 | -121.924846810 | [6 empty] | Unit completed late by vendor.
-1056228894 | VMS | Distribution | M | Priority 2 (P2) | Canyon Live Oak | ZPRUNE R2 | DADA1077194 | NWK | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-31 | 2023-07-12 | 2023-06-29 | -10 | 3. Non-timely worked |  |  | 37.136584700 | -121.946529030 | 3 | [5 empty] | Unit completed late by vendor.
-1056228970 | VMS | Distribution | M | Priority 2 (P2) | Oak | ZPRUNE R1 | DADA1077194 | NWK | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-31 | 2023-07-12 | 2023-06-29 | -10 | 3. Non-timely worked |  |  | 37.224404830 | -121.978723600 | [6 empty] | Unit completed late by vendor.
-1056229090 | VMS | Distribution | M | Priority 2 (P2) | Birch | ZRC to 11 | DADA1077192 | NWK | 1 | Central Coast | DA | CAMPBELL | SC | 0082921104 | EL PATIO 1104 | O | Complete | No Constraint | 2023-05-31 | 2023-07-13 | 2023-06-29 | -11 | 3. Non-timely worked |  |  | 37.282069210 | -121.929138220 | [6 empty] | Unit completed late by vendor.
-1056227487 | VMS | Distribution | M | Priority 2 (P2) | Liq Ambar (Sw Gum) | ZRC to 11 | DADA1077328 | NWK | 1 | Central Coast | DA | SAN JOSE | SC | 0083371109 | SARATOGA 1109 | O | Complete | No Constraint | 2023-06-01 | 2023-07-12 | 2023-06-30 | -9 | 3. Non-timely worked |  |  | 37.279992040 | -121.983801660 | [6 empty] | Unit completed late by vendor.
-1056225359 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077202 | NWK | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-02 | 2023-07-10 | 2023-07-03 | -6 | 3. Non-timely worked |  |  | 37.344586350 | -122.091913330 | [6 empty] | Unit completed late by vendor.
-1056175739 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZRC to 11 | DADA1077387 | NWK | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-05 | 2023-07-10 | 2023-07-05 | -4 | 3. Non-timely worked |  |  | 37.166214090 | -122.029079750 | 3 | [5 empty] | Unit completed late by vendor.
-1056223681 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZPRUNE R4 | DADA1077270 | NWK | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-05 | 2023-07-11 | 2023-07-05 | -5 | 3. Non-timely worked |  |  | 37.185146490 | -122.003264270 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056219849 | VMS | Distribution | M | Priority 2 (P2) | Ailanthus | ZRC to 11 | DADA1077267 | NWK | 1 | Central Coast | DA | SUNNYVALE | SC | 0083611105 | BRITTON 1105 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.370763150 | -122.026434200 | [6 empty] | Unit completed late by vendor.
-1056220589 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077270 | NWK | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-06 | 2023-07-11 | 2023-07-06 | -4 | 3. Non-timely worked |  |  | 37.122192230 | -121.955129140 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056217822 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZRC to 11 | DADA1077270 | NWK | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-07 | 2023-07-11 | 2023-07-07 | -3 | 3. Non-timely worked |  |  | 37.127826780 | -121.948193750 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056217897 | VMS | Distribution | M | Priority 2 (P2) | Tan Oak | ZRC to 11 | DADA1077270 | NWK | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-07 | 2023-07-11 | 2023-07-07 | -3 | 3. Non-timely worked |  |  | 37.128187560 | -121.948367030 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056218565 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077276 | NWK | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.339748550 | -122.082875810 | [6 empty] | Unit Constrained due to Storm Access.
-1056200393 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077276 | NWK | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-08 | 2023-07-11 | 2023-07-10 | -2 | 3. Non-timely worked |  |  | 37.339241690 | -122.095882950 | [6 empty] | Unit Constrained due to Storm Access.
-1056087653 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077635 | NWK | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-08-08 | 2024-02-07 | 2023-09-06 | -111 | 3. Non-timely worked |  |  | 37.156066940 | -122.018739740 | 3 | [5 empty] | Unit completed late by vendor.
-1056031885 | VMS | Distribution | M | Priority 2 (P2) | Silver Maple | ZRC to 11 | DADA1077901 | NWK | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0082031107 | MOUNTAIN VIEW 1107 | O | Complete | No Constraint | 2023-09-20 | 2023-10-19 | 2023-10-18 | -2 | 3. Non-timely worked |  |  | 37.374882230 | -122.079052140 | [6 empty] | Unit completed late by vendor.
-1056003461 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | DADA1078118 | NWK | 1 | Central Coast | DA | MONTE SEREN | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.242717980 | -121.998282630 | 2 | [5 empty] | Unit completed late by vendor.
-1056002462 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | DADA1078150 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083371106 | SARATOGA 1106 | O | Complete | No Constraint | 2023-10-16 | 2023-11-20 | 2023-11-14 | -5 | 3. Non-timely worked |  |  | 37.277144930 | -122.019812950 | [6 empty] | Unit completed late by vendor.
-1056002479 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | DADA1078150 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083371106 | SARATOGA 1106 | O | Complete | No Constraint | 2023-10-16 | 2023-11-20 | 2023-11-14 | -5 | 3. Non-timely worked |  |  | 37.277158770 | -122.019810170 | [6 empty] | Unit completed late by vendor.
-1056002484 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | DADA1078150 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083371106 | SARATOGA 1106 | O | Complete | No Constraint | 2023-10-16 | 2023-11-20 | 2023-11-14 | -5 | 3. Non-timely worked |  |  | 37.277244730 | -122.019695960 | [6 empty] | Unit completed late by vendor.
-1056002765 | VMS | Distribution | M | Priority 2 (P2) | Unknown | ZRC to 11 | DADA1078151 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-10-16 | 2023-11-20 | 2023-11-14 | -5 | 3. Non-timely worked |  |  | 37.279279110 | -121.996163580 | [6 empty] | Unit completed late by vendor.
-1056002872 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DADA1078127 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-16 | 2023-11-20 | 2023-11-14 | -5 | 3. Non-timely worked |  |  | 37.265125390 | -122.049247460 | 2 | [5 empty] | Unit completed late by vendor.
-1056001917 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | DADA1078158 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-17 | 2023-11-20 | 2023-11-15 | -4 | 3. Non-timely worked |  |  | 37.266630370 | -122.049524780 | 2 | [5 empty] | Unit completed late by vendor.
-1055999294 | VMS | Distribution | M | Priority 2 (P2) | Silver Dollar Gum | ZRC 12+ | DADA1078190 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-18 | 2023-11-28 | 2023-11-16 | -9 | 3. Non-timely worked |  |  | 37.266520480 | -122.049487920 | 2 | [5 empty] | Unit completed late by vendor.
-1055996037 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1078215 | NWK | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481104 | STELLING 1104 | O | Complete | No Constraint | 2023-10-19 | 2023-11-20 | 2023-11-17 | -2 | 3. Non-timely worked |  |  | 37.338767420 | -122.063855600 | [6 empty] | Unit completed late by vendor.
-1055997015 | VMS | Distribution | M | Priority 2 (P2) | Podocarpus | ZRC to 11 | DADA1078219 | NWK | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-20 | 2023-11-22 | 2023-11-20 | -3 | 3. Non-timely worked |  |  | 37.277710990 | -122.031112460 | [6 empty] | Unit completed late by vendor.
-1055997019 | VMS | Distribution | M | Priority 2 (P2) | Mulberry | ZRC to 11 | DADA1078218 | NWK | 1 | Central Coast | DA | SUNNYVALE | SC | 0082031110 | MOUNTAIN VIEW 1110 | O | Complete | No Constraint | 2023-10-20 | 2023-11-27 | 2023-11-20 | -6 | 3. Non-timely worked |  |  | 37.364736540 | -122.054031930 | [6 empty] | Unit completed late by vendor.
-1055997109 | VMS | Distribution | M | Priority 2 (P2) | Pistache | ZRC to 11 | DADA1078212 | NWK | 1 | Central Coast | DA | SUNNYVALE | SC | 0083481113 | STELLING 1113 | O | Complete | No Constraint | 2023-10-20 | 2023-11-28 | 2023-11-20 | -7 | 3. Non-timely worked |  |  | 37.346900620 | -122.048521450 | [6 empty] | Unit completed late by vendor.
-1055997115 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZPRUNE R5 | DADA1078207 | NWK | 1 | Central Coast | DA | SAN JOSE | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-10-20 | 2023-11-27 | 2023-11-20 | -6 | 3. Non-timely worked |  |  | 37.289706980 | -121.983061010 | [6 empty] | Unit completed late by vendor.
-1055995768 | VMS | Distribution | M | Priority 2 (P2) | Red Ironbark | ZRC to 11 | DADA1078228 | NWK | 1 | Central Coast | DA | LOS GATOS | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-10-23 | 2023-11-22 | 2023-11-21 | -2 | 3. Non-timely worked |  |  | 37.253201410 | -121.988134930 | [6 empty] | Unit completed late by vendor.
-1055995769 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | DADA1078231 | NWK | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481104 | STELLING 1104 | O | Complete | No Constraint | 2023-10-23 | 2023-11-27 | 2023-11-21 | -5 | 3. Non-timely worked |  |  | 37.344427370 | -122.066708240 | [6 empty] | Unit completed late by vendor.
-1055995773 | VMS | Distribution | M | Priority 2 (P2) | Red Ironbark | ZRC to 11 | DADA1078228 | NWK | 1 | Central Coast | DA | LOS GATOS | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-10-23 | 2023-11-22 | 2023-11-21 | -2 | 3. Non-timely worked |  |  | 37.253159000 | -121.988086000 | [6 empty] | Unit completed late by vendor.
-1055992567 | VMS | Distribution | M | Priority 2 (P2) | Spruce | ZRC to 11 | DADA1078285 | NWK | 1 | Central Coast | DA | SAN JOSE | SC | 0083371113 | SARATOGA 1113 | O | Complete | No Constraint | 2023-10-25 | 2023-11-29 | 2023-11-27 | -3 | 3. Non-timely worked |  |  | 37.294469260 | -122.024148480 | [6 empty] | Unit completed late by vendor.
-1055999624 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZOVPR 60+ | DADA1078155 | OP8 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-10-18 | 2023-11-17 | 2023-11-16 | -2 | 3. Non-timely worked |  |  | 37.155655140 | -121.990865780 | 3 | [5 empty] | Unit completed late by vendor.
-1055996996 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZOVPR 60+ | DADA1078217 | OP8 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-10-20 | 2023-11-21 | 2023-11-20 | -2 | 3. Non-timely worked |  |  | 37.155498780 | -121.989493800 | 3 | [5 empty] | Unit completed late by vendor.
-1057519584 | VMS | Distribution | M | Priority 2 (P2) | Privet | P1RC-11.9 | DADA1076316 | POA | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0083631108 | WHISMAN 1108 | O | Complete | No Constraint | 2023-01-31 | 2023-03-31 | 2023-03-01 | -23 | 3. Non-timely worked |  |  | 37.406838000 | -122.084936000 | [6 empty] | Unit Constrained due to Storm Access.
-1056611396 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZRC to 11 | DADA1076513 | POA | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-03-13 | 2023-06-23 | 2023-04-10 | -55 | 3. Non-timely worked |  |  | 37.150008520 | -121.972657120 | 3 | [5 empty] | Unit completed late by vendor.
-1056255070 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077097 | POA | 1 | Central Coast | DA | LOS GATOS | SC | 0083771108 | VASONA 1108 | O | Complete | No Constraint | 2023-05-16 | 2023-06-17 | 2023-06-14 | -3 | 3. Non-timely worked |  |  | 37.245065510 | -121.952636860 | [6 empty] | Unit Constrained due to Storm Access.
-1056231801 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077193 | POA | 1 | Central Coast | DA | SAN JOSE | SC | 0082921103 | EL PATIO 1103 | O | Complete | No Constraint | 2023-05-30 | 2023-06-30 | 2023-06-28 | -3 | 3. Non-timely worked |  |  | 37.313261970 | -121.956206570 | [6 empty] | Unit Constrained due to Storm Access.
-1056232081 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077193 | POA | 1 | Central Coast | DA | SAN JOSE | SC | 0082921103 | EL PATIO 1103 | O | Complete | No Constraint | 2023-05-30 | 2023-06-30 | 2023-06-28 | -3 | 3. Non-timely worked |  |  | 37.312715600 | -121.955618450 | [6 empty] | Unit Constrained due to Storm Access.
-1056232084 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077193 | POA | 1 | Central Coast | DA | SAN JOSE | SC | 0082921103 | EL PATIO 1103 | O | Complete | No Constraint | 2023-05-30 | 2023-06-30 | 2023-06-28 | -3 | 3. Non-timely worked |  |  | 37.312722820 | -121.955600480 | [6 empty] | Unit Constrained due to Storm Access.
-1057521876 | VMS | Distribution | M | Priority 2 (P2) | Cottonwood, Black | ZRC to 11 | DADA1076316 | RD1 | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0083631108 | WHISMAN 1108 | O | Complete | No Constraint | 2023-01-31 | 2023-03-31 | 2023-03-01 | -23 | 3. Non-timely worked |  |  | 37.403800000 | -122.067752670 | [6 empty] | Unit Constrained due to Storm Access.
-1057452925 | VMS | Distribution | M | Priority 2 (P2) | Silver Dollar Gum | ZRC to 11 | DADA1076337 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0083771102 | VASONA 1102 | O | Complete | No Constraint | 2023-02-03 | 2023-03-08 | 2023-03-06 | -3 | 3. Non-timely worked |  |  | 37.236469390 | -121.953588330 | [6 empty] | Unit Constrained due to Storm Access.
-1057435425 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC to 11 | DADA1076368 | RD1 | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0083631108 | WHISMAN 1108 | O | Complete | No Constraint | 2023-02-06 | 2023-03-08 | 2023-03-07 | -2 | 3. Non-timely worked |  |  | 37.404498360 | -122.088011790 | [6 empty] | Unit Constrained due to Storm Access.
-1057435595 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC to 11 | DADA1076368 | RD1 | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0083631108 | WHISMAN 1108 | O | Complete | No Constraint | 2023-02-06 | 2023-03-08 | 2023-03-07 | -2 | 3. Non-timely worked |  |  | 37.404517400 | -122.088339760 | [6 empty] | Unit Constrained due to Storm Access.
-1057366995 | VMS | Distribution | M | Priority 2 (P2) | Evergreen Ash | ZRC to 11 | DADA1076367 | RD1 | 1 | Central Coast | DA | SAN JOSE | SC | 0083371109 | SARATOGA 1109 | O | Complete | No Constraint | 2023-02-08 | 2023-09-28 | 2023-03-09 | -146 | 3. Non-timely worked |  |  | 37.277933740 | -121.987253740 | [6 empty] | Unit completed late by vendor.
-1057146800 | VMS | Distribution | M | Priority 2 (P2) | Canyon Live Oak | ZRC to 11 | DADA1076415 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-16 | 2023-03-31 | 2023-03-17 | -11 | 3. Non-timely worked |  |  | 37.220205340 | -121.936490430 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1057146803 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC to 11 | DADA1076415 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-16 | 2023-03-31 | 2023-03-17 | -11 | 3. Non-timely worked |  |  | 37.220219720 | -121.936473910 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1057147496 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC to 11 | DADA1076415 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-16 | 2023-03-31 | 2023-03-17 | -11 | 3. Non-timely worked |  |  | 37.220192600 | -121.936478150 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1057088730 | VMS | Distribution | M | Priority 2 (P2) | Chinese Elm | ZRC to 11 | DADA1076421 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371109 | SARATOGA 1109 | O | Complete | No Constraint | 2023-02-17 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.280358080 | -121.969980430 | [6 empty] | Unit Constrained due to Storm Access.
-1057103537 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076415 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-17 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.222720200 | -121.954396920 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1057068823 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076422 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082160401 | LOYOLA 0401 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.376006800 | -122.103990530 | [6 empty] | Unit Constrained due to Storm Access.
-1057070927 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076422 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082160401 | LOYOLA 0401 | O | Complete | No Constraint | 2023-02-20 | 2023-03-30 | 2023-03-20 | -9 | 3. Non-timely worked |  |  | 37.365051070 | -122.098768910 | [6 empty] | Unit Constrained due to Storm Access.
-1057070965 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076422 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082160401 | LOYOLA 0401 | O | Complete | No Constraint | 2023-02-20 | 2023-03-30 | 2023-03-20 | -9 | 3. Non-timely worked |  |  | 37.365048810 | -122.098686250 | [6 empty] | Unit Constrained due to Storm Access.
-1057073532 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1076422 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082160401 | LOYOLA 0401 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.371548450 | -122.103781640 | [6 empty] | Unit Constrained due to Storm Access.
-1057073557 | VMS | Distribution | M | Priority 2 (P2) | Tallow, Chinese | ZRC to 11 | DADA1076422 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082160401 | LOYOLA 0401 | O | Complete | No Constraint | 2023-02-20 | 2023-03-30 | 2023-03-20 | -9 | 3. Non-timely worked |  |  | 37.369378460 | -122.102562330 | [6 empty] | Unit Constrained due to Storm Access.
-1057074681 | VMS | Distribution | M | Priority 2 (P2) | Crape Myrtle | ZRC to 11 | DADA1076421 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371109 | SARATOGA 1109 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.280185290 | -121.969934840 | [6 empty] | Unit Constrained due to Storm Access.
-1057075944 | VMS | Distribution | M | Priority 2 (P2) | Black Walnut | ZRC to 11 | DADA1076423 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.225810940 | -121.962526460 | [6 empty] | Unit Constrained due to Storm Access.
-1057075954 | VMS | Distribution | M | Priority 2 (P2) | Palm-Queen | ZRC to 11 | DADA1076423 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.226161000 | -121.966915000 | [6 empty] | Unit Constrained due to Storm Access.
-1057075958 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1076423 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-30 | 2023-03-20 | -9 | 3. Non-timely worked |  |  | 37.224947640 | -121.965423970 | [6 empty] | Unit Constrained due to Storm Access.
-1057075959 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1076423 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-30 | 2023-03-20 | -9 | 3. Non-timely worked |  |  | 37.224974720 | -121.965399810 | [6 empty] | Unit Constrained due to Storm Access.
-1057075960 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1076423 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-30 | 2023-03-20 | -9 | 3. Non-timely worked |  |  | 37.224945120 | -121.965414690 | [6 empty] | Unit Constrained due to Storm Access.
-1057053779 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076431 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-21 | 2023-03-29 | 2023-03-21 | -7 | 3. Non-timely worked |  |  | 37.215275540 | -121.953567660 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1057053780 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076431 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-21 | 2023-03-27 | 2023-03-21 | -5 | 3. Non-timely worked |  |  | 37.215294440 | -121.953593320 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1056937273 | VMS | Distribution | M | Priority 2 (P2) | Norfolk Island Pine | ZRC to 11 | DADA1076447 | RD1 | 1 | Central Coast | DA | SUNNYVALE | SC | 0083481111 | STELLING 1111 | O | Complete | No Constraint | 2023-02-27 | 2023-03-28 | 2023-03-27 | -2 | 3. Non-timely worked |  |  | 37.348703200 | -121.944299220 | [6 empty] | Unit Constrained due to Storm Access.
-1056938007 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076447 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481111 | STELLING 1111 | O | Complete | No Constraint | 2023-02-27 | 2023-03-28 | 2023-03-27 | -2 | 3. Non-timely worked |  |  | 37.334208060 | -122.062899140 | [6 empty] | Unit Constrained due to Storm Access.
-1056818121 | VMS | Distribution | M | Priority 2 (P2) | Madrone | ZRC to 11 | DADA1076487 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-03-06 | 2023-04-04 | 2023-04-03 | -2 | 3. Non-timely worked |  |  | 37.144698070 | -121.980466330 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056818162 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DADA1076499 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083671105 | WOLFE 1105 | O | Complete | No Constraint | 2023-03-06 | 2023-04-04 | 2023-04-03 | -2 | 3. Non-timely worked |  |  | 37.312161630 | -122.014455180 | [6 empty] | Unit Constrained due to Storm Access.
-1056609776 | VMS | Distribution | M | Priority 2 (P2) | Elm | ZRC to 11 | DADA1076509 | RD1 | 1 | Central Coast | DA | SAN JOSE | SC | 0082921108 | EL PATIO 1108 | O | Complete | No Constraint | 2023-03-13 | 2023-04-11 | 2023-04-10 | -2 | 3. Non-timely worked |  |  | 37.315332230 | -121.943953510 | [6 empty] | Unit completed late by vendor.
-1056462531 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076650 | RD1 | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-03-27 | 2023-04-25 | 2023-04-24 | -2 | 3. Non-timely worked |  |  | 37.160731480 | -122.015386480 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056418367 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC to 11 | DADA1076787 | RD1 | 1 | Central Coast | DA | REDWOOD EST | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-04-06 | 2023-05-05 | 2023-05-04 | -2 | 3. Non-timely worked |  |  | 37.152272920 | -121.996938200 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056378974 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | DADA1076923 | RD1 | 1 | Central Coast | DA | MONTE SEREN | SC | 0083371106 | SARATOGA 1106 | O | Complete | No Constraint | 2023-04-17 | 2023-05-17 | 2023-05-15 | -3 | 3. Non-timely worked |  |  | 37.231600970 | -121.992266610 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1056365596 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1076928 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-04-18 | 2023-05-17 | 2023-05-16 | -2 | 3. Non-timely worked |  |  | 37.158772260 | -121.984656230 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056366038 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1076928 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-04-18 | 2023-05-17 | 2023-05-16 | -2 | 3. Non-timely worked |  |  | 37.154639850 | -121.982089380 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056359359 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | DADA1076938 | RD1 | 1 | Central Coast | DA | LOS ALTOS H | SC | 0082161102 | LOYOLA 1102 | O | Complete | No Constraint | 2023-04-19 | 2023-05-19 | 2023-05-17 | -3 | 3. Non-timely worked |  |  | 37.352688110 | -122.148249850 | [6 empty] | Unit Constrained due to Storm Access.
-1056359647 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC to 11 | DADA1076938 | RD1 | 1 | Central Coast | DA | LOS ALTOS H | SC | 0082161102 | LOYOLA 1102 | O | Complete | No Constraint | 2023-04-19 | 2023-05-19 | 2023-05-17 | -3 | 3. Non-timely worked |  |  | 37.352931200 | -122.145419840 | [6 empty] | Unit Constrained due to Storm Access.
-1056359684 | VMS | Distribution | M | Priority 2 (P2) | Dawn Redwood | ZRC to 11 | DADA1076923 | RD1 | 1 | Central Coast | DA | MONTE SEREN | SC | 0083371106 | SARATOGA 1106 | O | Complete | No Constraint | 2023-04-19 | 2023-05-18 | 2023-05-17 | -2 | 3. Non-timely worked |  |  | 37.233277890 | -121.987638410 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1056347194 | VMS | Distribution | M | Priority 2 (P2) | Other | ZRC to 11 | DADA1076945 | RD1 | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-04-21 | 2023-05-22 | 2023-05-19 | -2 | 3. Non-timely worked |  |  | 37.108077700 | -121.947976050 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056301351 | VMS | Distribution | M | Priority 2 (P2) | Italian Stone Pine | ZRC to 11 | DADA1076985 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082031105 | MOUNTAIN VIEW 1105 | O | Complete | No Constraint | 2023-04-26 | 2023-05-25 | 2023-05-24 | -2 | 3. Non-timely worked |  |  | 37.383706240 | -122.107757330 | [6 empty] | Unit Constrained due to Storm Access.
-1056274926 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077043 | RD1 | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-08 | 2023-06-07 | 2023-06-06 | -2 | 3. Non-timely worked |  |  | 37.106725780 | -121.916199780 | 3 | [5 empty] | Unit completed late by vendor.
-1056271930 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077046 | RD1 | 1 | Central Coast | DA | SAN JOSE | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-05-09 | 2023-06-08 | 2023-06-07 | -2 | 3. Non-timely worked |  |  | 37.299060970 | -121.974087150 | [6 empty] | Unit completed late by vendor.
-1056237190 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077136 | RD1 | 1 | Central Coast | DA | SAN JOSE | SC | 0082921103 | EL PATIO 1103 | O | Complete | No Constraint | 2023-05-25 | 2023-07-12 | 2023-06-26 | -13 | 3. Non-timely worked |  |  | 37.297939970 | -121.947092910 | [6 empty] | Unit completed late by vendor.
-1056231634 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077194 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-30 | 2023-07-12 | 2023-06-28 | -11 | 3. Non-timely worked |  |  | 37.166217840 | -121.974969470 | 3 | [5 empty] | Unit completed late by vendor.
-1056231709 | VMS | Distribution | M | Priority 2 (P2) | Acacia | ZRC to 11 | DADA1077194 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-30 | 2023-07-12 | 2023-06-28 | -11 | 3. Non-timely worked |  |  | 37.173337440 | -121.986873450 | 3 | [5 empty] | Unit completed late by vendor.
-1056231710 | VMS | Distribution | M | Priority 2 (P2) | Acacia | ZRC to 11 | DADA1077194 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-30 | 2023-07-12 | 2023-06-28 | -11 | 3. Non-timely worked |  |  | 37.173293550 | -121.986873700 | 3 | [5 empty] | Unit completed late by vendor.
-1056231711 | VMS | Distribution | M | Priority 2 (P2) | Acacia | ZRC to 11 | DADA1077194 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-30 | 2023-07-12 | 2023-06-28 | -11 | 3. Non-timely worked |  |  | 37.173343010 | -121.986785700 | 3 | [5 empty] | Unit completed late by vendor.
-1056231780 | VMS | Distribution | M | Priority 2 (P2) | Acacia | ZRC to 11 | DADA1077194 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-30 | 2023-07-12 | 2023-06-28 | -11 | 3. Non-timely worked |  |  | 37.167915600 | -121.974370060 | 3 | [5 empty] | Unit completed late by vendor.
-1056231800 | VMS | Distribution | M | Priority 2 (P2) | Pear | ZRC to 11 | DADA1077194 | RD1 | 1 | Central Coast | DA | SUNNYVALE | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-30 | 2023-07-12 | 2023-06-28 | -11 | 3. Non-timely worked |  |  | 37.216399680 | -121.985601670 | 2 | [5 empty] | Unit completed late by vendor.
-1056225482 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077315 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082031107 | MOUNTAIN VIEW 1107 | O | Complete | No Constraint | 2023-05-31 | 2023-07-01 | 2023-06-29 | -2 | 3. Non-timely worked |  |  | 37.358897650 | -122.091067530 | [6 empty] | Unit completed late by vendor.
-1056229971 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC to 11 | DADA1077194 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-05-31 | 2023-07-12 | 2023-06-29 | -10 | 3. Non-timely worked |  |  | 37.217187070 | -121.972729500 | 2 | [5 empty] | Unit completed late by vendor.
-1056227483 | VMS | Distribution | M | Priority 2 (P2) | Tan Oak | ZRC to 11 | DADA1077327 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082241106 | LOS ALTOS 1106 | O | Complete | No Constraint | 2023-06-01 | 2023-07-01 | 2023-06-30 | -1 | 3. Non-timely worked |  |  | 37.149756020 | -121.979390810 | 3 | [5 empty] | Unit completed late by vendor.
-1056220660 | VMS | Distribution | M | Priority 2 (P2) | Tan Oak | ZRC to 11 | DADA1077271 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-06-02 | 2023-07-12 | 2023-07-03 | -8 | 3. Non-timely worked |  |  | 37.376696170 | -122.040300540 | [6 empty] | Unit Constrained due to Storm Access.
-1056225387 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077270 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-02 | 2023-07-06 | 2023-07-03 | -4 | 3. Non-timely worked |  |  | 37.161922460 | -121.981268450 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056221173 | VMS | Distribution | M | Priority 2 (P2) | Oak | ZRC to 11 | DADA1077269 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481110 | STELLING 1110 | O | Complete | No Constraint | 2023-06-05 | 2023-07-10 | 2023-07-05 | -4 | 3. Non-timely worked |  |  | 37.295862210 | -122.105506210 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1056221582 | VMS | Distribution | M | Priority 2 (P2) | Palm-Fan | ZRC to 11 | DADA1077268 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481111 | STELLING 1111 | O | Complete | No Constraint | 2023-06-05 | 2023-07-12 | 2023-07-05 | -6 | 3. Non-timely worked |  |  | 37.333045460 | -122.067547430 | [6 empty] | Unit completed late by vendor.
-1056221592 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | ZRC to 11 | DADA1077270 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-05 | 2023-07-10 | 2023-07-05 | -4 | 3. Non-timely worked |  |  | 37.180262990 | -122.003908170 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056221641 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077270 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-05 | 2023-07-11 | 2023-07-05 | -5 | 3. Non-timely worked |  |  | 37.125664480 | -121.938551200 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056223586 | VMS | Distribution | M | Priority 2 (P2) | Podocarpus | ZRC to 11 | DADA1077268 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481111 | STELLING 1111 | O | Complete | No Constraint | 2023-06-05 | 2023-07-11 | 2023-07-05 | -5 | 3. Non-timely worked |  |  | 37.343502080 | -122.082432000 | [6 empty] | Unit completed late by vendor.
-1056194580 | VMS | Distribution | M | Priority 2 (P2) | Oak | ZRC to 11 | DADA1077389 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481110 | STELLING 1110 | O | Complete | No Constraint | 2023-06-06 | 2023-07-10 | 2023-07-06 | -3 | 3. Non-timely worked |  |  | 37.296109260 | -122.111423330 | 2 | [5 empty] | Unit completed late by vendor.
-1056219738 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC to 11 | DADA1077270 | RD1 | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.133059480 | -121.969060620 | 3 | [5 empty] | Unit completed late by vendor.
-1056219830 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC to 11 | DADA1077270 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-06 | 2023-07-10 | 2023-07-06 | -3 | 3. Non-timely worked |  |  | 37.181573240 | -122.002005810 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056219931 | VMS | Distribution | M | Priority 2 (P2) | Mulberry | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.343517020 | -122.087437560 | [6 empty] | Unit Constrained due to Storm Access.
-1056219996 | VMS | Distribution | M | Priority 2 (P2) | Pin Oak | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-06 | 2023-07-13 | 2023-07-06 | -6 | 3. Non-timely worked |  |  | 37.343214830 | -122.085947070 | [6 empty] | Unit completed late by vendor.
-1056220062 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077269 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481110 | STELLING 1110 | O | Complete | No Constraint | 2023-06-06 | 2023-07-10 | 2023-07-06 | -3 | 3. Non-timely worked |  |  | 37.308561170 | -122.071107800 | [6 empty] | Unit Constrained due to Storm Access.
-1056220191 | VMS | Distribution | M | Priority 2 (P2) | Palm | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.343944780 | -122.084616010 | [6 empty] | Unit Constrained due to Storm Access.
-1056220517 | VMS | Distribution | M | Priority 2 (P2) | Mulberry | ZRC to 11 | DADA1077278 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.295454820 | -121.966714570 | [6 empty] | Unit completed late by vendor.
-1056220607 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077278 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.295468880 | -121.966782870 | [6 empty] | Unit completed late by vendor.
-1056220611 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077278 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.295486020 | -121.966691770 | [6 empty] | Unit completed late by vendor.
-1056220616 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077278 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.295462230 | -121.966615480 | [6 empty] | Unit completed late by vendor.
-1056220638 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077278 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.295462560 | -121.966986220 | [6 empty] | Unit completed late by vendor.
-1056220652 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077278 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.295445590 | -121.967244510 | [6 empty] | Unit completed late by vendor.
-1056220670 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1077278 | RD1 | 1 | Central Coast | DA | CAMPBELL | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.295446540 | -121.967519460 | [6 empty] | Unit completed late by vendor.
-1056220730 | VMS | Distribution | M | Priority 2 (P2) | Plum | ZRC to 11 | DADA1077270 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-06 | 2023-07-11 | 2023-07-06 | -4 | 3. Non-timely worked |  |  | 37.161197090 | -121.977740540 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056218279 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.340596190 | -122.101857890 | [6 empty] | Unit Constrained due to Storm Access.
-1056218280 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.340606450 | -122.101923750 | [6 empty] | Unit Constrained due to Storm Access.
-1056218281 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.340600710 | -122.101936360 | [6 empty] | Unit Constrained due to Storm Access.
-1056218303 | VMS | Distribution | M | Priority 2 (P2) | Chestnut | ZRC to 11 | DADA1077270 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-07 | 2023-07-11 | 2023-07-07 | -3 | 3. Non-timely worked |  |  | 37.138545370 | -121.967997740 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056218716 | VMS | Distribution | M | Priority 2 (P2) | Plum | ZRC to 11 | DADA1077270 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-07 | 2023-07-11 | 2023-07-07 | -3 | 3. Non-timely worked |  |  | 37.161661030 | -121.977669880 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056218794 | VMS | Distribution | M | Priority 2 (P2) | Liq Ambar (Sw Gum) | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.340217720 | -122.082553750 | [6 empty] | Unit completed late by vendor.
-1056218800 | VMS | Distribution | M | Priority 2 (P2) | Blackwood Acacia | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.340295270 | -122.082763610 | [6 empty] | Unit Constrained due to Storm Access.
-1056218815 | VMS | Distribution | M | Priority 2 (P2) | Privet | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.340522410 | -122.082569670 | [6 empty] | Unit Constrained due to Storm Access.
-1056218817 | VMS | Distribution | M | Priority 2 (P2) | Privet | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.340528570 | -122.082565830 | [6 empty] | Unit Constrained due to Storm Access.
-1056218818 | VMS | Distribution | M | Priority 2 (P2) | Privet | ZRC to 11 | DADA1077276 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481108 | STELLING 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.340533700 | -122.082568490 | [6 empty] | Unit Constrained due to Storm Access.
-1056199436 | VMS | Distribution | M | Priority 2 (P2) | Madrone | ZRC to 11 | DADA1077297 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-08 | 2023-07-11 | 2023-07-10 | -2 | 3. Non-timely worked |  |  | 37.167066600 | -121.994283650 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056199471 | VMS | Distribution | M | Priority 2 (P2) | Bigleaf Maple | ZRC to 11 | DADA1077297 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-08 | 2023-07-11 | 2023-07-10 | -2 | 3. Non-timely worked |  |  | 37.165994410 | -121.996019140 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056199834 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZRC to 11 | DADA1077297 | RD1 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-06-08 | 2023-07-12 | 2023-07-10 | -3 | 3. Non-timely worked |  |  | 37.127212490 | -121.943557720 | 3 | [5 empty] | Unit completed late by vendor.
-1056070337 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077725 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371105 | SARATOGA 1105 | O | Complete | No Constraint | 2023-08-23 | 2023-09-22 | 2023-09-21 | -2 | 3. Non-timely worked |  |  | 37.269469810 | -122.043863530 | 2 | [5 empty] | Unit completed late by vendor.
-1056053842 | VMS | Distribution | M | Priority 2 (P2) | Chestnut | ZRC to 11 | DADA1077739 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481110 | STELLING 1110 | O | Complete | No Constraint | 2023-09-01 | 2023-10-05 | 2023-10-02 | -4 | 3. Non-timely worked |  |  | 37.316690030 | -122.071743970 | [6 empty] | Unit completed late by vendor.
-1056050043 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC to 11 | DADA1077793 | RD1 | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0082031107 | MOUNTAIN VIEW 1107 | O | Complete | No Constraint | 2023-09-07 | 2023-10-06 | 2023-10-05 | -2 | 3. Non-timely worked |  |  | 37.377531200 | -122.092214500 | [6 empty] | Unit completed late by vendor.
-1056050182 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077793 | RD1 | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0082031107 | MOUNTAIN VIEW 1107 | O | Complete | No Constraint | 2023-09-07 | 2023-10-06 | 2023-10-05 | -2 | 3. Non-timely worked |  |  | 37.379136080 | -122.092277890 | [6 empty] | Unit completed late by vendor.
-1056050480 | VMS | Distribution | M | Priority 2 (P2) | Chinese Elm | ZRC to 11 | DADA1077793 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082031107 | MOUNTAIN VIEW 1107 | O | Complete | No Constraint | 2023-09-07 | 2023-10-06 | 2023-10-05 | -2 | 3. Non-timely worked |  |  | 37.366447480 | -122.089750460 | [6 empty] | Unit completed late by vendor.
-1056044904 | VMS | Distribution | M | Priority 2 (P2) | Camphor | ZRC to 11 | DADA1077793 | RD1 | 1 | Central Coast | DA | LOS ALTOS | SC | 0082031107 | MOUNTAIN VIEW 1107 | O | Complete | No Constraint | 2023-09-11 | 2023-10-13 | 2023-10-09 | -5 | 3. Non-timely worked |  |  | 37.364681770 | -122.084558990 | [6 empty] | Unit completed late by vendor.
-1056043168 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077814 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-12 | 2023-10-16 | 2023-10-10 | -5 | 3. Non-timely worked |  |  | 37.250193720 | -122.019502860 | 2 | [5 empty] | Unit completed late by vendor.
-1056043218 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077814 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-12 | 2023-10-16 | 2023-10-10 | -5 | 3. Non-timely worked |  |  | 37.251025450 | -122.020376080 | 2 | [5 empty] | Unit completed late by vendor.
-1056033518 | VMS | Distribution | M | Priority 2 (P2) | Modesto Ash | ZRC to 11 | DADA1077901 | RD1 | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0082031107 | MOUNTAIN VIEW 1107 | O | Complete | No Constraint | 2023-09-19 | 2023-10-24 | 2023-10-17 | -6 | 3. Non-timely worked |  |  | 37.374176400 | -122.082705670 | [6 empty] | Unit completed late by vendor.
-1056033709 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077902 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2023-12-15 | 2023-10-17 | -44 | 3. Non-timely worked |  |  | 37.241597710 | -122.021567290 | 2 | [5 empty] | Unit completed late by vendor.
-1056033710 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077902 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2023-12-14 | 2023-10-17 | -43 | 3. Non-timely worked |  |  | 37.241614030 | -122.021555820 | 2 | [5 empty] | Unit completed late by vendor.
-1056033711 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077902 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2023-12-14 | 2023-10-17 | -43 | 3. Non-timely worked |  |  | 37.241665460 | -122.021198990 | 2 | [5 empty] | Unit completed late by vendor.
-1056033712 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077902 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2023-12-15 | 2023-10-17 | -44 | 3. Non-timely worked |  |  | 37.241415850 | -122.020281180 | 2 | [5 empty] | Unit completed late by vendor.
-1056033713 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077902 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2023-12-14 | 2023-10-17 | -43 | 3. Non-timely worked |  |  | 37.241419530 | -122.020299150 | 2 | [5 empty] | Unit completed late by vendor.
-1056033714 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1077902 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371107 | SARATOGA 1107 | O | Complete | No Constraint | 2023-09-19 | 2023-12-14 | 2023-10-17 | -43 | 3. Non-timely worked |  |  | 37.241622240 | -122.020574370 | 2 | [5 empty] | Unit completed late by vendor.
-1056027914 | VMS | Distribution | M | Priority 2 (P2) | Maple | ZRC to 11 | DADA1077926 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083671109 | WOLFE 1109 | O | Complete | No Constraint | 2023-09-25 | 2023-10-24 | 2023-10-23 | -2 | 3. Non-timely worked |  |  | 37.314105540 | -122.023632310 | [6 empty] | Unit completed late by vendor.
-1056002067 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1078153 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481109 | STELLING 1109 | O | Complete | No Constraint | 2023-10-12 | 2024-02-12 | 2023-11-09 | -68 | 3. Non-timely worked |  |  | 37.294077650 | -122.062319170 | 2 | [5 empty] | Unit completed late by vendor.
-1056002062 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC to 11 | DADA1078153 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481109 | STELLING 1109 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.295485410 | -122.060917350 | 2 | [5 empty] | Unit completed late by vendor.
-1056002065 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1078153 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481109 | STELLING 1109 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.295064140 | -122.060578950 | 2 | [5 empty] | Unit completed late by vendor.
-1056002066 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1078153 | RD1 | 1 | Central Coast | DA | CUPERTINO | SC | 0083481109 | STELLING 1109 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.295160270 | -122.060493100 | 2 | [5 empty] | Unit completed late by vendor.
-1056003416 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1078118 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.271467730 | -122.005186750 | [6 empty] | Unit completed late by vendor.
-1056003460 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1078118 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.243235750 | -121.997301440 | 2 | [5 empty] | Unit completed late by vendor.
-1056003463 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1078118 | RD1 | 1 | Central Coast | DA | MONTE SEREN | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.242748890 | -121.998291120 | 2 | [5 empty] | Unit completed late by vendor.
-1055998873 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1078194 | RD1 | 1 | Central Coast | DA | MONTE SEREN | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-10-18 | 2023-11-17 | 2023-11-16 | -2 | 3. Non-timely worked |  |  | 37.248802940 | -121.994204470 | [6 empty] | Unit completed late by vendor.
-1055997611 | VMS | Distribution | M | Priority 2 (P2) | Chinese Elm | ZRC to 11 | DADA1078200 | RD1 | 1 | Central Coast | DA | SUNNYVALE | SC | 0083481113 | STELLING 1113 | O | Complete | No Constraint | 2023-10-19 | 2023-11-20 | 2023-11-17 | -2 | 3. Non-timely worked |  |  | 37.347616680 | -122.046676720 | [6 empty] | Unit completed late by vendor.
-1055997702 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DADA1078207 | RD1 | 1 | Central Coast | DA | SAN JOSE | SC | 0083371111 | SARATOGA 1111 | O | Complete | No Constraint | 2023-10-19 | 2023-12-13 | 2023-11-17 | -19 | 3. Non-timely worked |  |  | 37.289975660 | -121.982557480 | [6 empty] | Unit completed late by vendor.
-1055998150 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DADA1078195 | RD1 | 1 | Central Coast | DA | SARATOGA | SC | 0083371106 | SARATOGA 1106 | O | Complete | No Constraint | 2023-10-19 | 2023-11-20 | 2023-11-17 | -2 | 3. Non-timely worked |  |  | 37.276179080 | -122.025147040 | [6 empty] | Unit completed late by vendor.
-1055992717 | VMS | Distribution | M | Priority 2 (P2) | Liq Ambar (Sw Gum) | ZRC to 11 | DADA1078254 | RD1 | 1 | Central Coast | DA | SAN JOSE | SC | 0082921104 | EL PATIO 1104 | O | Complete | No Constraint | 2023-10-25 | 2023-12-13 | 2023-11-27 | -13 | 3. Non-timely worked |  |  | 37.285935050 | -121.917940490 | [6 empty] | Unit completed late by vendor.
-1057476556 | VMS | Distribution | M | Priority 2 (P2) | Cedar | ZRC 12+ | DADA1076335 | RD2 | 1 | Central Coast | DA | MONTE SEREN | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-02-02 | 2023-03-08 | 2023-03-03 | -4 | 3. Non-timely worked |  |  | 37.250706560 | -121.993824790 | [6 empty] | Unit Constrained due to Storm Access.
-1057054361 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DADA1076431 | RD2 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-27 | 2023-03-20 | -6 | 3. Non-timely worked |  |  | 37.219561750 | -121.944693220 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1057073542 | VMS | Distribution | M | Priority 2 (P2) | Palm-Fan | ZRC 12+ | DADA1076423 | RD2 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.227026680 | -121.955908430 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1057075615 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | DADA1076423 | RD2 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021101 | LOS GATOS 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-30 | 2023-03-20 | -9 | 3. Non-timely worked |  |  | 37.226917500 | -121.953325430 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1056412607 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DADA1076786 | RD2 | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-04-07 | 2023-05-09 | 2023-05-05 | -3 | 3. Non-timely worked |  |  | 37.133618920 | -122.003157530 | 3 | [5 empty] | Unit completed late by vendor.
-1056380883 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC 12+ | DADA1076928 | RD2 | 1 | Central Coast | DA | LOS GATOS | SZ | 0082021106 | LOS GATOS 1106 | O | Complete | No Constraint | 2023-04-17 | 2023-05-17 | 2023-05-15 | -3 | 3. Non-timely worked |  |  | 37.174059450 | -122.069379980 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056382354 | VMS | Distribution | M | Priority 2 (P2) | Monterey Pine | ZRC 12+ | DADA1076909 | RD2 | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-04-17 | 2023-05-17 | 2023-05-15 | -3 | 3. Non-timely worked |  |  | 37.117001190 | -122.004609250 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056221654 | VMS | Distribution | M | Priority 2 (P2) | Chinese Elm | ZRC 12+ | DADA1077277 | RD2 | 1 | Central Coast | DA | SAN JOSE | SC | 0083371113 | SARATOGA 1113 | O | Complete | No Constraint | 2023-06-05 | 2023-07-11 | 2023-07-05 | -5 | 3. Non-timely worked |  |  | 37.297732760 | -122.024083490 | [6 empty] | Unit completed late by vendor.
-1056218593 | VMS | Distribution | M | Priority 2 (P2) | Madrone | ZRC 12+ | DADA1077271 | RD2 | 1 | Central Coast | DA | LOS GATOS | SC | 0082021107 | LOS GATOS 1107 | O | Complete | No Constraint | 2023-06-07 | 2023-07-10 | 2023-07-07 | -2 | 3. Non-timely worked |  |  | 37.177991770 | -121.950647400 | 3 | [5 empty] | Unit Constrained due to Storm Access.
-1056012147 | VMS | Distribution | M | Priority 2 (P2) | Olive | ZRC 12+ | DADA1078025 | RD2 | 1 | Central Coast | DA | SAN JOSE | SC | 0829211119 | EL PATIO 1119 | O | Complete | No Constraint | 2023-10-06 | 2023-11-07 | 2023-11-03 | -3 | 3. Non-timely worked |  |  | 37.280735000 | -121.925019000 | [6 empty] | Unit completed late by vendor.
-1056008269 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DADA1078118 | RD2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371104 | SARATOGA 1104 | O | Complete | No Constraint | 2023-10-10 | 2023-11-08 | 2023-11-07 | -2 | 3. Non-timely worked |  |  | 37.243039800 | -122.000572530 | 2 | [5 empty] | Unit completed late by vendor.
-1056003613 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DADA1078115 | RD2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.262542790 | -122.039100570 | 2 | [5 empty] | Unit completed late by vendor.
-1056003673 | VMS | Distribution | M | Priority 2 (P2) | Italian Stone Pine | ZRC 12+ | DADA1078115 | RD2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.260465350 | -122.043953150 | 2 | [5 empty] | Unit completed late by vendor.
-1056002690 | VMS | Distribution | M | Priority 2 (P2) | Cedar | ZRC 12+ | DADA1078158 | RD2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-16 | 2023-11-17 | 2023-11-14 | -4 | 3. Non-timely worked |  |  | 37.265361950 | -122.048849470 | 2 | [5 empty] | Unit completed late by vendor.
-1056002699 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DADA1078158 | RD2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-16 | 2023-11-17 | 2023-11-14 | -4 | 3. Non-timely worked |  |  | 37.265431720 | -122.049038230 | 2 | [5 empty] | Unit completed late by vendor.
-1056002802 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC 12+ | DADA1078158 | RD2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-16 | 2023-11-16 | 2023-11-14 | -3 | 3. Non-timely worked |  |  | 37.264962960 | -122.049323900 | 2 | [5 empty] | Unit completed late by vendor.
-1055999437 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC 12+ | DADA1078163 | RD2 | 1 | Central Coast | DA | MONTE SEREN | SC | 0083371106 | SARATOGA 1106 | O | Complete | No Constraint | 2023-10-18 | 2023-11-17 | 2023-11-16 | -2 | 3. Non-timely worked |  |  | 37.230228410 | -121.990458070 | 2 | [5 empty] | Unit completed late by vendor.
-1055999631 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DADA1078158 | RD2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-18 | 2023-11-20 | 2023-11-16 | -3 | 3. Non-timely worked |  |  | 37.265965680 | -122.038586070 | 2 | [5 empty] | Unit completed late by vendor.
-1055997424 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | DADA1078205 | RD2 | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-10-19 | 2023-11-21 | 2023-11-17 | -3 | 3. Non-timely worked |  |  | 37.159226900 | -122.018886500 | 3 | [5 empty] | Unit completed late by vendor.
-1055997425 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | DADA1078205 | RD2 | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-10-19 | 2023-11-21 | 2023-11-17 | -3 | 3. Non-timely worked |  |  | 37.159102200 | -122.018702400 | 3 | [5 empty] | Unit completed late by vendor.
-1055998108 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DADA1078190 | RD2 | 1 | Central Coast | DA | SARATOGA | SC | 0083371103 | SARATOGA 1103 | O | Complete | No Constraint | 2023-10-19 | 2023-11-21 | 2023-11-17 | -3 | 3. Non-timely worked |  |  | 37.258763350 | -122.041507220 | 2 | [5 empty] | Unit completed late by vendor.
-1055996853 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | DADA1078216 | RD2 | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-10-20 | 2023-11-21 | 2023-11-20 | -2 | 3. Non-timely worked |  |  | 37.136901070 | -121.985531890 | 3 | [5 empty] | Unit completed late by vendor.
-1055995770 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | DADA1078231 | RD2 | 1 | Central Coast | DA | LOS ALTOS | SC | 0083481104 | STELLING 1104 | O | Complete | No Constraint | 2023-10-23 | 2023-11-27 | 2023-11-21 | -5 | 3. Non-timely worked |  |  | 37.344326260 | -122.066686280 | [6 empty] | Unit completed late by vendor.
-1055970612 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZRC 12+ | DADA1078488 | RD2 | 1 | Central Coast | DA | LOS ALTOS H | SC | 0082161102 | LOYOLA 1102 | O | Complete | No Constraint | 2023-11-30 | 2023-12-30 | 2023-12-29 | -1 | 3. Non-timely worked |  |  | 37.357488410 | -122.134387410 | [6 empty] | Unit completed late by vendor.
-1055970621 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZRC 12+ | DADA1078488 | RD2 | 1 | Central Coast | DA | LOS ALTOS H | SC | 0082161102 | LOYOLA 1102 | O | Complete | No Constraint | 2023-11-30 | 2023-12-30 | 2023-12-29 | -1 | 3. Non-timely worked |  |  | 37.357448380 | -122.134370160 | [6 empty] | Unit completed late by vendor.
-1055970652 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZRC 12+ | DADA1078488 | RD2 | 1 | Central Coast | DA | LOS ALTOS H | SC | 0082161102 | LOYOLA 1102 | O | Complete | No Constraint | 2023-11-30 | 2023-12-30 | 2023-12-29 | -1 | 3. Non-timely worked |  |  | 37.357548100 | -122.134338550 | [6 empty] | Unit completed late by vendor.
-1057471529 | VMS | Distribution | M | Priority 2 (P2) | Modesto Ash | RC to 11.9 | DADA1076329 | U01 | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0083631108 | WHISMAN 1108 | O | Complete | No Constraint | 2023-02-02 | 2023-03-08 | 2023-03-03 | -4 | 3. Non-timely worked |  |  | 37.406604000 | -122.087267000 | [6 empty] | Unit Constrained due to Storm Access.
-1057522510 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | DADA1076313 | U02 | 1 | Central Coast | DA | MOUNTAIN VI | SC | 0083631106 | WHISMAN 1106 | O | Complete | No Constraint | 2023-01-31 | 2023-03-02 | 2023-03-01 | -2 | 3. Non-timely worked |  |  | 37.408555840 | -122.075076620 | [6 empty] | Unit Constrained due to Storm Access.
-1055998565 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | ZMOV to 20 | DADA1078184 | UOA | 1 | Central Coast | DA | LOS GATOS | SZ | 0083622106 | CAMP EVERS 2106 | O | Complete | No Constraint | 2023-10-18 | 2023-12-05 | 2023-11-16 | -14 | 3. Non-timely worked |  |  | 37.144756490 | -121.994553210 | 3 | [5 empty] | Unit completed late by vendor.
-1055986482 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC 12+ | CCLP1082461 | RD2 | 1 | Central Coast | LP | ARROYO GRAN | SL | 0182601104 | OCEANO 1104 | O | Complete | Constraint_ITS_past | 2023-10-31 | 2024-07-26 | 2024-01-25 | -132 | 3. Non-timely worked |  |  | 35.137451000 | -120.565606000 | 2 | 619797 | RFT129092659 | Refusal | CLOSE | 2023-12-01 | Vendor Billing error.
-1057072047 | VMS | Distribution | M | Priority 2 (P2) | Holly Oak | TopDirecti | DASJ1077267 | NW | 1 | Central Coast | SJ | SAN JOSE | SC | 0083701101 | STONE 1101 | O | Complete | Constraint_ITS_past | 2023-02-20 | 2024-02-07 | 2023-03-20 | -233 | 3. Non-timely worked |  |  | 37.296283000 | -121.908343000 |  | 569217 | RFT108170349 | Refusal | CLOSE | 2023-02-15 | Unit completed late by vendor.
-1057072044 | VMS | Distribution | M | Priority 2 (P2) | Locust, Black | Top | DASJ1077267 | NWK | 1 | Central Coast | SJ | SAN JOSE | SC | 0083701101 | STONE 1101 | O | Complete | Constraint_ITS_past | 2023-02-20 | 2023-07-12 | 2023-03-20 | -83 | 3. Non-timely worked |  |  | 37.296280000 | -121.908596000 |  | 569217 | RFT108170349 | Refusal | CLOSE | 2023-02-15 | Unit completed late by vendor.
-1056266227 | VMS | Distribution | M | Priority 2 (P2) | Monterey Pine | ZRC to 11 | DASJ1077745 | NWK | 1 | Central Coast | SJ | SAN JOSE | SC | 0082952106 | EDENVALE 2106 | O | Complete | Constraint_ITS_past | 2023-05-11 | 2024-01-25 | 2023-07-19 | -137 | 3. Non-timely worked |  |  | 37.245499000 | -121.842244000 |  | 602888 | RFT609143741 | Refusal | CLOSE | 2023-06-16 | Unit completed late by vendor.
-1056248809 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC to 11 | DASJ1077795 | NWK | 1 | Central Coast | SJ | MORGAN HILL | SC | 0083242110 | MORGAN HILL 2110 | O | Complete | Constraint_ITS_past | 2023-05-19 | 2024-01-25 | 2023-10-18 | -72 | 3. Non-timely worked |  |  | 37.120617000 | -121.650753000 |  | 603740 | ACC621160453 | Access Issue | CLOSE | 2023-09-20 | Unit completed late by vendor.
-1056249011 | VMS | Distribution | M | Priority 2 (P2) | Pine | ZRC to 11 | DASJ1077837 | RD1 | 1 | Central Coast | SJ | MORGAN HILL | SC | 0083242111 | MORGAN HILL 2111 | O | Complete | Constraint_ITS_past | 2023-05-18 | 2023-07-12 | 2023-06-28 | -11 | 3. Non-timely worked |  |  | 37.104030000 | -121.748398870 | 2 | 601051 | NST519085234 | Nest Review | CLOSE | 2023-05-30 | Unit completed late by vendor.
-1056221884 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | DASJ1077866 | RD1 | 1 | Central Coast | SJ | GILROY | SC | 0083182103 | LLAGAS 2103 | O | Complete | Constraint_ITS_past | 2023-06-05 | 2023-07-12 | 2023-07-11 | -2 | 3. Non-timely worked |  |  | 37.046992060 | -121.628800080 | 2 | 602790 | RPT608130904 | Riparian | CLOSE | 2023-06-09 | Unit completed late by vendor.
-1057072046 | VMS | Distribution | M | Priority 2 (P2) | Holly Oak | TopDirecti | DASJ1077267 | TD | 1 | Central Coast | SJ | SAN JOSE | SC | 0083701101 | STONE 1101 | O | Complete | Constraint_ITS_past | 2023-02-20 | 2023-07-12 | 2023-03-20 | -83 | 3. Non-timely worked |  |  | 37.296278000 | -121.908382000 |  | 569217 | RFT108170349 | Refusal | CLOSE | 2023-02-15 | Unit completed late by vendor.
-1055983767 | VMS | Distribution | M | Priority 2 (P2) | Oak | ZMAJOR R1 | DASJ1078898 | MA1 | 1 | Central Coast | SJ | MORGAN HILL | SC | 0083242111 | MORGAN HILL 2111 | O | Complete | No Constraint | 2023-11-03 | 2024-01-22 | 2023-12-06 | -34 | 3. Non-timely worked |  |  | 37.082295700 | -121.785069230 | 3 | [5 empty] | Unit completed late by vendor.
-1055999379 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZPRUNE R3 | DASJ1078766 | MN3 | 1 | Central Coast | SJ | GILROY | SC | 0083182105 | LLAGAS 2105 | O | Complete | No Constraint | 2023-10-18 | 2023-11-21 | 2023-11-16 | -4 | 3. Non-timely worked |  |  | 36.981068070 | -121.578008490 | [6 empty] | Unit constrained due to Line Kill request.
-1056165109 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | DASJ1077961 | NW | 1 | Central Coast | SJ | GILROY | SC | 0083182102 | LLAGAS 2102 | O | Complete | No Constraint | 2023-05-23 | 2023-06-28 | 2023-06-22 | -5 | 3. Non-timely worked |  |  | 37.008175240 | -121.558446960 | [6 empty] | Unit completed late by vendor.
-1056233192 | VMS | Distribution | M | Priority 2 (P2) | Elm | ZRC to 11 | DASJ1077829 | NWK | 1 | Central Coast | SJ | SAN JOSE | SC | 0082012102 | EVERGREEN 2102 | O | Complete | No Constraint | 2023-05-26 | 2023-06-28 | 2023-06-27 | -2 | 3. Non-timely worked |  |  | 37.322462110 | -121.845273550 | [6 empty] | Unit completed late by vendor.
-1056229909 | VMS | Distribution | M | Priority 2 (P2) | Hackberry | ZRC to 11 | DASJ1077842 | NWK | 1 | Central Coast | SJ | GILROY | SC | 0083182103 | LLAGAS 2103 | O | Complete | No Constraint | 2023-05-31 | 2023-07-06 | 2023-06-29 | -6 | 3. Non-timely worked |  |  | 37.024132380 | -121.570587370 | [6 empty] | Unit completed late by vendor.
-1056230321 | VMS | Distribution | M | Priority 2 (P2) | Pepper Tree | ZRC to 11 | DASJ1077839 | NWK | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-05-31 | 2023-07-12 | 2023-06-29 | -10 | 3. Non-timely worked |  |  | 37.334667870 | -121.948205890 | [6 empty] | Unit completed late by vendor.
-1056227471 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | DASJ1077857 | NWK | 1 | Central Coast | SJ | GILROY | SC | 0083182103 | LLAGAS 2103 | O | Complete | No Constraint | 2023-06-01 | 2023-07-06 | 2023-06-30 | -5 | 3. Non-timely worked |  |  | 37.008219390 | -121.558427110 | [6 empty] | Unit completed late by vendor.
-1056227777 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DASJ1077852 | NWK | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-01 | 2023-07-17 | 2023-06-30 | -12 | 3. Non-timely worked |  |  | 37.334201920 | -121.930876730 | [6 empty] | Unit completed late by vendor.
-1056219717 | VMS | Distribution | M | Priority 2 (P2) | Silver Maple | ZRC to 11 | DASJ1077878 | NWK | 1 | Central Coast | SJ | MILPITAS | SC | 0082831105 | MILPITAS 1105 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.452145610 | -121.895124640 | [6 empty] | Unit completed late by vendor.
-1056219981 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZPRUNE R3 | DASJ1077876 | NWK | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.334132340 | -121.932667410 | [6 empty] | Unit completed late by vendor.
-1056218613 | VMS | Distribution | M | Priority 2 (P2) | Oak | ZRC to 11 | DASJ1077908 | NWK | 1 | Central Coast | SJ | SAN MARTIN | SC | 0083242110 | MORGAN HILL 2110 | O | Complete | No Constraint | 2023-06-07 | 2023-07-10 | 2023-07-07 | -2 | 3. Non-timely worked |  |  | 37.081186630 | -121.611380040 | [6 empty] | Unit completed late by vendor.
-1056218826 | VMS | Distribution | M | Priority 2 (P2) | Magnolia | ZRC to 11 | DASJ1077876 | NWK | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-07 | 2024-02-14 | 2023-07-07 | -159 | 3. Non-timely worked |  |  | 37.331987060 | -121.932263030 | [6 empty] | Unit completed late by vendor.
-1056105617 | VMS | Distribution | M | Priority 2 (P2) | Pepper Tree | ZRC 12+ | DASJ1078211 | NWK | 1 | Central Coast | SJ | MILPITAS | SC | 0088012102 | DIXON LANDING 2102 | O | Complete | No Constraint | 2023-07-25 | 2023-08-26 | 2023-08-22 | -4 | 3. Non-timely worked |  |  | 37.435842660 | -121.913747880 | [6 empty] | Unit completed late by vendor.
-1056072397 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | P1RC 12+ | DASJ1078360 | POB | 1 | Central Coast | SJ | SAN JOSE | SC | 0083531107 | MC KEE 1107 | O | Complete | No Constraint | 2023-08-22 | 2023-09-27 | 2023-09-20 | -6 | 3. Non-timely worked |  |  | 37.371159000 | -121.774358000 | 2 | [5 empty] | Unit completed late by vendor.
-1057089653 | VMS | Distribution | M | Priority 2 (P2) | Chinese Elm | ZRC to 11 | DASJ1077286 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082191101 | MABURY 1101 | O | Complete | No Constraint | 2023-02-17 | 2023-03-23 | 2023-03-20 | -4 | 3. Non-timely worked |  |  | 37.339209930 | -121.874857870 | [6 empty] | Unit Constrained due to Storm Access.
-1057102527 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC to 11 | DASJ1077265 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082191104 | MABURY 1104 | O | Complete | No Constraint | 2023-02-17 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.355043060 | -121.869027310 | [6 empty] | Unit Constrained due to Storm Access.
-1057068049 | VMS | Distribution | M | Priority 2 (P2) | Bottlebrush | ZRC to 11 | DASJ1077283 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082311101 | ALMADEN 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-23 | 2023-03-20 | -4 | 3. Non-timely worked |  |  | 37.281070840 | -121.902604990 | [6 empty] | Unit Constrained due to Storm Access.
-1057068821 | VMS | Distribution | M | Priority 2 (P2) | Fruit Tree | ZRC to 11 | DASJ1077283 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082311101 | ALMADEN 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-23 | 2023-03-20 | -4 | 3. Non-timely worked |  |  | 37.280687640 | -121.902215340 | [6 empty] | Unit Constrained due to Storm Access.
-1057072786 | VMS | Distribution | M | Priority 2 (P2) | Cottonwood, Fremont | ZRC to 11 | DASJ1077283 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082311101 | ALMADEN 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-22 | 2023-03-20 | -3 | 3. Non-timely worked |  |  | 37.283263250 | -121.904184890 | [6 empty] | Unit Constrained due to Storm Access.
-1057072787 | VMS | Distribution | M | Priority 2 (P2) | Chinese Elm | ZRC to 11 | DASJ1077282 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082191104 | MABURY 1104 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.339801960 | -121.873474210 | [6 empty] | Unit Constrained due to Storm Access.
-1057073580 | VMS | Distribution | M | Priority 2 (P2) | Privet | ZRC to 11 | DASJ1077283 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082311101 | ALMADEN 1101 | O | Complete | No Constraint | 2023-02-20 | 2023-03-21 | 2023-03-20 | -2 | 3. Non-timely worked |  |  | 37.268234710 | -121.893382040 | [6 empty] | Unit Constrained due to Storm Access.
-1057048437 | VMS | Distribution | M | Priority 2 (P2) | Weeping Willow | ZRC to 11 | DASJ1077283 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082311101 | ALMADEN 1101 | O | Complete | No Constraint | 2023-02-21 | 2023-03-22 | 2023-03-21 | -2 | 3. Non-timely worked |  |  | 37.281823130 | -121.903089200 | [6 empty] | Unit Constrained due to Storm Access.
-1056801587 | VMS | Distribution | M | Priority 2 (P2) | Plum | ZRC to 11 | DASJ1077350 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082311110 | ALMADEN 1110 | O | Complete | No Constraint | 2023-03-07 | 2023-09-08 | 2023-04-04 | -114 | 3. Non-timely worked |  |  | 37.248410470 | -121.902025350 | [6 empty] | Unit completed late by vendor.
-1056458663 | VMS | Distribution | M | Priority 2 (P2) | Podocarpus | ZRC to 11 | DASJ1077428 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083432103 | HICKS 2103 | O | Complete | No Constraint | 2023-03-28 | 2023-04-27 | 2023-04-25 | -3 | 3. Non-timely worked |  |  | 37.220486700 | -121.873950210 | [6 empty] | Unit Constrained due to Storm Access.
-1056447815 | VMS | Distribution | M | Priority 2 (P2) | Vine | ZRC to 11 | DASJ1077469 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082832110 | MILPITAS 2110 | O | Complete | No Constraint | 2023-03-30 | 2023-04-28 | 2023-04-27 | -2 | 3. Non-timely worked |  |  | 37.409773880 | -121.876511160 | [6 empty] | Unit Constrained due to Storm Access.
-1056449366 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DASJ1077465 | RD1 | 1 | Central Coast | SJ | LOS GATOS | SC | 0083431115 | HICKS 1115 | O | Complete | No Constraint | 2023-03-30 | 2023-04-28 | 2023-04-27 | -2 | 3. Non-timely worked |  |  | 37.241931870 | -121.929865030 | [6 empty] | Unit Constrained due to Storm Access.
-1056449432 | VMS | Distribution | M | Priority 2 (P2) | Loquat | ZRC to 11 | DASJ1077469 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082832110 | MILPITAS 2110 | O | Complete | No Constraint | 2023-03-30 | 2023-04-28 | 2023-04-27 | -2 | 3. Non-timely worked |  |  | 37.413237850 | -121.867415590 | [6 empty] | Unit Constrained due to Storm Access.
-1056449544 | VMS | Distribution | M | Priority 2 (P2) | Magnolia | ZRC to 11 | DASJ1077469 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082832110 | MILPITAS 2110 | O | Complete | No Constraint | 2023-03-30 | 2023-04-28 | 2023-04-27 | -2 | 3. Non-timely worked |  |  | 37.413141340 | -121.867548850 | [6 empty] | Unit Constrained due to Storm Access.
-1056365370 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DASJ1077676 | RD1 | 1 | Central Coast | SJ | NEW ALMADEN | SC | 0083432101 | HICKS 2101 | O | Complete | No Constraint | 2023-04-17 | 2023-05-16 | 2023-05-15 | -2 | 3. Non-timely worked |  |  | 37.176759610 | -121.821875100 | 2 | [5 empty] | Unit Constrained due to Storm Access.
-1056383065 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC to 11 | DASJ1077676 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083432101 | HICKS 2101 | O | Complete | No Constraint | 2023-04-17 | 2023-05-16 | 2023-05-15 | -2 | 3. Non-timely worked |  |  | 37.193077420 | -121.821179010 | [6 empty] | Unit Constrained due to Storm Access.
-1056383569 | VMS | Distribution | M | Priority 2 (P2) | Red Ironbark | ZRC to 11 | DASJ1077633 | RD1 | 1 | Central Coast | SJ | MILPITAS | SC | 0088012101 | DIXON LANDING 2101 | O | Complete | No Constraint | 2023-04-17 | 2023-05-16 | 2023-05-15 | -2 | 3. Non-timely worked |  |  | 37.456909450 | -121.908290310 | [6 empty] | Unit Constrained due to Storm Access.
-1056383570 | VMS | Distribution | M | Priority 2 (P2) | Red Ironbark | ZRC to 11 | DASJ1077633 | RD1 | 1 | Central Coast | SJ | MILPITAS | SC | 0088012101 | DIXON LANDING 2101 | O | Complete | No Constraint | 2023-04-17 | 2023-05-16 | 2023-05-15 | -2 | 3. Non-timely worked |  |  | 37.456892040 | -121.908266640 | [6 empty] | Unit Constrained due to Storm Access.
-1056383571 | VMS | Distribution | M | Priority 2 (P2) | Red Ironbark | ZRC to 11 | DASJ1077633 | RD1 | 1 | Central Coast | SJ | MILPITAS | SC | 0088012101 | DIXON LANDING 2101 | O | Complete | No Constraint | 2023-04-17 | 2023-05-16 | 2023-05-15 | -2 | 3. Non-timely worked |  |  | 37.456916740 | -121.908284510 | [6 empty] | Unit Constrained due to Storm Access.
-1056386529 | VMS | Distribution | M | Priority 2 (P2) | Deodara Cedar | ZRC to 11 | DASJ1077631 | RD1 | 1 | Central Coast | SJ | GILROY | SC | 0083182107 | LLAGAS 2107 | O | Complete | No Constraint | 2023-04-17 | 2023-05-16 | 2023-05-15 | -2 | 3. Non-timely worked |  |  | 37.040974360 | -121.532823180 | [6 empty] | Unit Constrained due to Storm Access.
-1056261758 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DASJ1077772 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082952106 | EDENVALE 2106 | O | Complete | No Constraint | 2023-05-15 | 2023-06-14 | 2023-06-13 | -2 | 3. Non-timely worked |  |  | 37.243399870 | -121.841927410 | [6 empty] | Unit completed late by vendor.
-1056255036 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DASJ1077780 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083432103 | HICKS 2103 | O | Complete | No Constraint | 2023-05-16 | 2023-07-11 | 2023-06-14 | -20 | 3. Non-timely worked |  |  | 37.229487310 | -121.905109760 | [6 empty] | Unit completed late by vendor.
-1056255429 | VMS | Distribution | M | Priority 2 (P2) | Palm-Fan | ZRC to 11 | DASJ1077773 | RD1 | 1 | Central Coast | SJ | LOS GATOS | SC | 0083431116 | HICKS 1116 | O | Complete | No Constraint | 2023-05-16 | 2023-06-15 | 2023-06-14 | -2 | 3. Non-timely worked |  |  | 37.221602830 | -121.940866220 | 2 | [5 empty] | Unit completed late by vendor.
-1056250695 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DASJ1077770 | RD1 | 1 | Central Coast | SJ | MORGAN HILL | SC | 0083242111 | MORGAN HILL 2111 | O | Complete | No Constraint | 2023-05-18 | 2023-06-20 | 2023-06-16 | -3 | 3. Non-timely worked |  |  | 37.134742630 | -121.734440260 | 2 | [5 empty] | Unit Constrained due to System Hardening field verification.
-1056250696 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | DASJ1077770 | RD1 | 1 | Central Coast | SJ | MORGAN HILL | SC | 0083242111 | MORGAN HILL 2111 | O | Complete | No Constraint | 2023-05-18 | 2023-06-20 | 2023-06-16 | -3 | 3. Non-timely worked |  |  | 37.134727720 | -121.734410280 | 2 | [5 empty] | Vendor Billing error.
-1056233049 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | DASJ1077831 | RD1 | 1 | Central Coast | SJ | MORGAN HILL | SC | 0083242105 | MORGAN HILL 2105 | O | Complete | No Constraint | 2023-05-26 | 2023-06-28 | 2023-06-27 | -2 | 3. Non-timely worked |  |  | 37.059765620 | -121.676930610 | 3 | [5 empty] | Unit completed late by vendor.
-1056229555 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC to 11 | DASJ1077839 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-05-31 | 2023-07-06 | 2023-06-29 | -6 | 3. Non-timely worked |  |  | 37.342579350 | -121.930893870 | [6 empty] | Unit completed late by vendor.
-1056227192 | VMS | Distribution | M | Priority 2 (P2) | Ailanthus | ZRC to 11 | DASJ1077851 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082012103 | EVERGREEN 2103 | O | Complete | No Constraint | 2023-06-01 | 2023-07-06 | 2023-06-30 | -5 | 3. Non-timely worked |  |  | 37.285774030 | -121.827589730 | [6 empty] | Unit completed late by vendor.
-1056227252 | VMS | Distribution | M | Priority 2 (P2) | Maple | ZRC to 11 | DASJ1077852 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-01 | 2023-07-06 | 2023-06-30 | -5 | 3. Non-timely worked |  |  | 37.331608670 | -121.932096740 | [6 empty] | Unit completed late by vendor.
-1056227371 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC to 11 | DASJ1077857 | RD1 | 1 | Central Coast | SJ | GILROY | SC | 0083182103 | LLAGAS 2103 | O | Complete | No Constraint | 2023-06-01 | 2023-07-06 | 2023-06-30 | -5 | 3. Non-timely worked |  |  | 37.047923510 | -121.582882400 | [6 empty] | Unit completed late by vendor.
-1056221639 | VMS | Distribution | M | Priority 2 (P2) | Canary Island Pine | ZRC to 11 | DASJ1077867 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082831108 | MILPITAS 1108 | O | Complete | No Constraint | 2023-06-05 | 2023-07-13 | 2023-07-05 | -7 | 3. Non-timely worked |  |  | 37.412692710 | -121.847308680 | [6 empty] | Unit completed late by vendor.
-1056220061 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DASJ1077866 | RD1 | 1 | Central Coast | SJ | GILROY | SC | 0083182103 | LLAGAS 2103 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.037084380 | -121.619391660 | 2 | [5 empty] | Unit completed late by vendor.
-1056220548 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335378380 | -121.932610870 | [6 empty] | Unit completed late by vendor.
-1056220549 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-18 | 2023-07-06 | -9 | 3. Non-timely worked |  |  | 37.335394350 | -121.932585770 | [6 empty] | Unit completed late by vendor.
-1056220550 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335358010 | -121.932577200 | [6 empty] | Unit completed late by vendor.
-1056220551 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335359650 | -121.932592390 | [6 empty] | Unit completed late by vendor.
-1056220552 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335367540 | -121.932616940 | [6 empty] | Unit completed late by vendor.
-1056220553 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335374490 | -121.932620800 | [6 empty] | Unit completed late by vendor.
-1056220554 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335383070 | -121.932587710 | [6 empty] | Unit completed late by vendor.
-1056220555 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335372180 | -121.932627450 | [6 empty] | Unit completed late by vendor.
-1056220556 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335368400 | -121.932568270 | [6 empty] | Unit completed late by vendor.
-1056220639 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.335383020 | -121.932557330 | [6 empty] | Unit completed late by vendor.
-1056220757 | VMS | Distribution | M | Priority 2 (P2) | Unknown | ZRC to 11 | DASJ1077884 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082952106 | EDENVALE 2106 | O | Complete | No Constraint | 2023-06-06 | 2023-07-12 | 2023-07-06 | -5 | 3. Non-timely worked |  |  | 37.248602110 | -121.841883930 | [6 empty] | Unit completed late by vendor.
-1056216986 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DASJ1077888 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082832112 | MILPITAS 2112 | O | Complete | No Constraint | 2023-06-07 | 2023-07-13 | 2023-07-07 | -5 | 3. Non-timely worked |  |  | 37.408220290 | -121.889007980 | [6 empty] | Unit completed late by vendor.
-1056217821 | VMS | Distribution | M | Priority 2 (P2) | Evergreen Ash | ZRC to 11 | DASJ1077883 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082311111 | ALMADEN 1111 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.264770410 | -121.887542930 | [6 empty] | Unit completed late by vendor.
-1056217823 | VMS | Distribution | M | Priority 2 (P2) | Evergreen Ash | ZRC to 11 | DASJ1077883 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082311111 | ALMADEN 1111 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.264754580 | -121.887541030 | [6 empty] | Unit completed late by vendor.
-1056217891 | VMS | Distribution | M | Priority 2 (P2) | Fruit Tree | ZRC to 11 | DASJ1077876 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-06-07 | 2023-07-14 | 2023-07-07 | -6 | 3. Non-timely worked |  |  | 37.333647070 | -121.934797430 | [6 empty] | Unit completed late by vendor.
-1056218311 | VMS | Distribution | M | Priority 2 (P2) | Ginkgo | ZRC to 11 | DASJ1077886 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082831109 | MILPITAS 1109 | O | Complete | No Constraint | 2023-06-07 | 2023-07-11 | 2023-07-07 | -3 | 3. Non-timely worked |  |  | 37.417655910 | -121.867044610 | [6 empty] | Unit completed late by vendor.
-1056218313 | VMS | Distribution | M | Priority 2 (P2) | Ash | ZRC to 11 | DASJ1077887 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082832110 | MILPITAS 2110 | O | Complete | No Constraint | 2023-06-07 | 2023-07-14 | 2023-07-07 | -6 | 3. Non-timely worked |  |  | 37.409831930 | -121.873048620 | [6 empty] | Unit completed late by vendor.
-1056218459 | VMS | Distribution | M | Priority 2 (P2) | Ash | ZRC to 11 | DASJ1077887 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082832110 | MILPITAS 2110 | O | Complete | No Constraint | 2023-06-07 | 2023-07-10 | 2023-07-07 | -2 | 3. Non-timely worked |  |  | 37.410937820 | -121.872996250 | [6 empty] | Unit completed late by vendor.
-1056218612 | VMS | Distribution | M | Priority 2 (P2) | Palm-Queen | ZRC to 11 | DASJ1077887 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082832110 | MILPITAS 2110 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.399878690 | -121.851148310 | [6 empty] | Unit completed late by vendor.
-1056219375 | VMS | Distribution | M | Priority 2 (P2) | Blackwood Acacia | ZRC to 11 | DASJ1077885 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082831108 | MILPITAS 1108 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.411859970 | -121.878912330 | [6 empty] | Unit completed late by vendor.
-1056219378 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077877 | RD1 | 1 | Central Coast | SJ | GILROY | SC | 0083182103 | LLAGAS 2103 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.051870570 | -121.611461080 | [6 empty] | Unit completed late by vendor.
-1056219441 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077877 | RD1 | 1 | Central Coast | SJ | GILROY | SC | 0083182103 | LLAGAS 2103 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.051867080 | -121.611492020 | [6 empty] | Unit completed late by vendor.
-1056219452 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DASJ1077877 | RD1 | 1 | Central Coast | SJ | GILROY | SC | 0083182103 | LLAGAS 2103 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.052232190 | -121.611645360 | [6 empty] | Unit completed late by vendor.
-1056219461 | VMS | Distribution | M | Priority 2 (P2) | Palm-Queen | ZRC to 11 | DASJ1077891 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082952106 | EDENVALE 2106 | O | Complete | No Constraint | 2023-06-07 | 2023-07-12 | 2023-07-07 | -4 | 3. Non-timely worked |  |  | 37.247441060 | -121.849010640 | [6 empty] | Unit completed late by vendor.
-1056199420 | VMS | Distribution | M | Priority 2 (P2) | Red Ironbark | ZRC to 11 | DASJ1077886 | RD1 | 1 | Central Coast | SJ | MILPITAS | SC | 0082831109 | MILPITAS 1109 | O | Complete | No Constraint | 2023-06-08 | 2023-07-11 | 2023-07-10 | -2 | 3. Non-timely worked |  |  | 37.448681960 | -121.847164240 | [6 empty] | Unit completed late by vendor.
-1056199421 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZRC to 11 | DASJ1077886 | RD1 | 1 | Central Coast | SJ | MILPITAS | SC | 0082831109 | MILPITAS 1109 | O | Complete | No Constraint | 2023-06-08 | 2023-07-11 | 2023-07-10 | -2 | 3. Non-timely worked |  |  | 37.447738770 | -121.850101310 | [6 empty] | Unit completed late by vendor.
-1056199647 | VMS | Distribution | M | Priority 2 (P2) | Locust, Black | ZRC to 11 | DASJ1077887 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082832110 | MILPITAS 2110 | O | Complete | No Constraint | 2023-06-08 | 2023-07-11 | 2023-07-10 | -2 | 3. Non-timely worked |  |  | 37.411693330 | -121.866844930 | [6 empty] | Unit completed late by vendor.
-1056199813 | VMS | Distribution | M | Priority 2 (P2) | Mulberry | ZRC to 11 | DASJ1077905 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082952113 | EDENVALE 2113 | O | Complete | No Constraint | 2023-06-08 | 2023-07-15 | 2023-07-10 | -5 | 3. Non-timely worked |  |  | 37.245465940 | -121.834763710 | [6 empty] | Unit completed late by vendor.
-1056200248 | VMS | Distribution | M | Priority 2 (P2) | Italian Cypress | ZRC to 11 | DASJ1077885 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082831108 | MILPITAS 1108 | O | Complete | No Constraint | 2023-06-08 | 2023-07-11 | 2023-07-10 | -2 | 3. Non-timely worked |  |  | 37.414843900 | -121.864860580 | [6 empty] | Unit completed late by vendor.
-1056200263 | VMS | Distribution | M | Priority 2 (P2) | Chinese Elm | ZRC to 11 | DASJ1077885 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082831108 | MILPITAS 1108 | O | Complete | No Constraint | 2023-06-08 | 2023-07-15 | 2023-07-10 | -5 | 3. Non-timely worked |  |  | 37.414783650 | -121.865118850 | [6 empty] | Unit completed late by vendor.
-1056034354 | VMS | Distribution | M | Priority 2 (P2) | Pepper Tree | ZRC to 11 | DASJ1078517 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083531107 | MC KEE 1107 | O | Complete | No Constraint | 2023-09-18 | 2023-10-17 | 2023-10-16 | -2 | 3. Non-timely worked |  |  | 37.375481620 | -121.815276830 | [6 empty] | Unit completed late by vendor.
-1056017916 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | DASJ1078626 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083701101 | STONE 1101 | O | Complete | No Constraint | 2023-10-04 | 2023-11-03 | 2023-11-01 | -3 | 3. Non-timely worked |  |  | 37.296364110 | -121.907461040 | [6 empty] | Unit completed late by vendor.
-1056003457 | VMS | Distribution | M | Priority 2 (P2) | Palm-Queen | ZRC to 11 | DASJ1078719 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082251112 | SAN JOSE SUB A 1112 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.314248340 | -121.909153390 | [6 empty] | Unit completed late by vendor.
-1055999682 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | DASJ1078755 | RD1 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083431111 | HICKS 1111 | O | Complete | No Constraint | 2023-10-18 | 2023-11-21 | 2023-11-16 | -4 | 3. Non-timely worked |  |  | 37.274042120 | -121.908181540 | [6 empty] | Unit completed late by vendor.
-1057221636 | VMS | Distribution | M | Priority 2 (P2) | Fig | ZRC to 11 | DASJ1077274 | RD2 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083871101 | FMC 1101 | O | Complete | No Constraint | 2023-02-15 | 2023-03-17 | 2023-03-16 | -2 | 3. Non-timely worked |  |  | 37.334131740 | -121.934079230 | [6 empty] | Unit Constrained due to Storm Access.
-1056199549 | VMS | Distribution | M | Priority 2 (P2) | Italian Stone Pine | ZRC 12+ | DASJ1077892 | RD2 | 1 | Central Coast | SJ | MILPITAS | SC | 0088012102 | DIXON LANDING 2102 | O | Complete | No Constraint | 2023-06-08 | 2023-07-11 | 2023-07-10 | -2 | 3. Non-timely worked |  |  | 37.437799910 | -121.914865750 | [6 empty] | Unit completed late by vendor.
-1056072366 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC 12+ | DASJ1078360 | RD2 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083531107 | MC KEE 1107 | O | Complete | No Constraint | 2023-08-22 | 2023-09-27 | 2023-09-20 | -6 | 3. Non-timely worked |  |  | 37.370888860 | -121.774728320 | 2 | [5 empty] | Unit completed late by vendor.
-1056061508 | VMS | Distribution | M | Priority 2 (P2) | Pepper Tree | ZRC 12+ | DASJ1078421 | RD2 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083531107 | MC KEE 1107 | O | Complete | No Constraint | 2023-08-29 | 2023-09-28 | 2023-09-27 | -2 | 3. Non-timely worked |  |  | 37.377845110 | -121.806329710 | [6 empty] | Unit completed late by vendor.
-1056033722 | VMS | Distribution | M | Priority 2 (P2) | Red Oak, Northern | ZRC 12+ | DASJ1078517 | RD2 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083531107 | MC KEE 1107 | O | Complete | No Constraint | 2023-09-19 | 2023-10-19 | 2023-10-17 | -3 | 3. Non-timely worked |  |  | 37.388346730 | -121.814372720 | [6 empty] | Unit completed late by vendor.
-1056017803 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | DASJ1078626 | RD2 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083701101 | STONE 1101 | O | Complete | No Constraint | 2023-10-04 | 2023-11-02 | 2023-11-01 | -2 | 3. Non-timely worked |  |  | 37.295414980 | -121.907394650 | [6 empty] | Unit completed late by vendor.
-1056003507 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | RC to 11.9 | DASJ1078719 | RD2 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082251112 | SAN JOSE SUB A 1112 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.310754000 | -121.909197000 | [6 empty] | Unit completed late by vendor.
-1056003539 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC 12+ | DASJ1078719 | RD2 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082251112 | SAN JOSE SUB A 1112 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.310642530 | -121.910191400 | [6 empty] | Unit completed late by vendor.
-1056003567 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC 12+ | DASJ1078719 | RD2 | 1 | Central Coast | SJ | SAN JOSE | SC | 0082251112 | SAN JOSE SUB A 1112 | O | Complete | No Constraint | 2023-10-13 | 2023-11-14 | 2023-11-13 | -2 | 3. Non-timely worked |  |  | 37.310633240 | -121.911022820 | [6 empty] | Unit completed late by vendor.
-1056733127 | VMS | Distribution | M | Priority 2 (P2) | Palm-Queen | ZRC to 11 | DASJ1077364 | TO | 1 | Central Coast | SJ | SAN JOSE | SC | 0083701110 | STONE 1110 | O | Complete | No Constraint | 2023-03-08 | 2023-04-12 | 2023-04-05 | -6 | 3. Non-timely worked |  |  | 37.335732040 | -122.022789500 | [6 empty] | Unit Constrained due to Storm Access.
-1056244692 | VMS | Distribution | M | Priority 2 (P2) | Palm-Queen | ZRC to 11 | DASJ1077819 | U01 | 1 | Central Coast | SJ | SAN JOSE | SC | 0083701101 | STONE 1101 | O | Complete | No Constraint | 2023-05-22 | 2023-06-27 | 2023-06-21 | -5 | 3. Non-timely worked |  |  | 37.299381520 | -121.884576060 | [6 empty] | Unit completed late by vendor.

## Central Valley
iTreeRecsID | Source | Circuit type | sAcctType | PRIORITY | Tree_Type | TRIM_TYPE | sWorkReq | ActualTrimCode | Tree_Qty | Region | Division | sCity | sCountyCode | scircuit | CIRCUIT | sNotification | Completion status - field | Constraint? | dtInspDate | dtWorkDate | Due date per compliance | Business Days Between Work Date and Compliance Date | Timeliness status | Location_Lat | Location_Long | Tree_Lat | Tree_Long | iHFTDTier | iRefusalID | sDocNumber | REFUSAL_TYPE | sRefusalStatus | dtResolved | Reason for Completion after Compliance Due Date
-1056060490 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZMAJOR R1 | X6FR1027019 | MA1 | 1 | Central Valley | FR | SQUAW VALLE | FR | 0254601103 | SAND CREEK 1103 | O | Complete | Constraint_ITS_past | 2023-08-30 | 2023-10-05 | 2023-09-28 | -6 | 3. Non-timely worked |  |  | 36.700602080 | -119.098309190 | 2 | 612393 | HNT830133849 | Hazard Notification | NEW |  | Additional constraint due to access issues.
-1056028721 | VMS | Distribution | M | Priority 2 (P2) | Palm-Queen | ZMAJOR R2 | X6FR1027244 | MA2 | 1 | Central Valley | FR | FRESNO | FR | 0252052105 | ASHLAN AVENUE 2105 | O | Complete | Constraint_ITS_past | 2023-09-22 | 2023-12-06 | 2023-10-20 | -34 | 3. Non-timely worked |  |  | 36.819958880 | -119.819782450 |  | 614360 | HNT922140146 | Hazard Notification | NEW |  | Additional constraint due to access issues.
-1056060491 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZMAJOR R3 | X6FR1027019 | MA3 | 1 | Central Valley | FR | SQUAW VALLE | FR | 0254601103 | SAND CREEK 1103 | O | Complete | Constraint_ITS_past | 2023-08-30 | 2023-10-05 | 2023-09-28 | -6 | 3. Non-timely worked |  |  | 36.700611940 | -119.098315650 | 2 | 612392 | HNT830133820 | Hazard Notification | NEW |  | Additional constraint due to access issues.
-1056159572 | VMS | Distribution | M | Priority 2 (P2) | Palm-Date | ZRC 12+ | X6FR1026397 | NWK | 1 | Central Valley | FR | FRESNO | FR | 0254251108 | MALAGA 1108 | O | Complete | Constraint_ITS_past | 2023-06-29 | 2023-08-09 | 2023-07-28 | -9 | 3. Non-timely worked |  |  | 36.676236790 | -119.799952350 |  | 605444 | HNT629160811 | Hazard Notification | NEW |  | Customer Cut Tree - No Longer in Scope
-1056159573 | VMS | Distribution | M | Priority 2 (P2) | Palm-Date | ZRC 12+ | X6FR1026397 | NWK | 1 | Central Valley | FR | FRESNO | FR | 0254251108 | MALAGA 1108 | O | Complete | Constraint_ITS_past | 2023-06-29 | 2023-08-09 | 2023-07-28 | -9 | 3. Non-timely worked |  |  | 36.676324510 | -119.799954800 |  | 605443 | HNT629160727 | Hazard Notification | NEW |  | Customer Cut Tree - No Longer in Scope
-1056089529 | VMS | Distribution | M | Priority 2 (P2) | Ginkgo | ZRC 12+ | X6FR1026816 | U02 | 1 | Central Valley | FR | FRESNO | FR | 0252701114 | KEARNEY 1114 | O | Complete | Constraint_ITS_past | 2023-08-07 | 2023-10-06 | 2023-09-05 | -24 | 3. Non-timely worked |  |  | 36.756396280 | -119.866371870 |  | 609161 | HNT807142802 | Hazard Notification | NEW |  | Additional constraint due to access issues.
-1056170723 | VMS | Distribution | M | Priority 2 (P2) | Pine | ZRC 12+ | X6FR1026326 | RD2 | 1 | Central Valley | FR | CLOVIS | FR | 0254151102 | AUBERRY 1102 | O | Complete | No Constraint | 2023-06-21 | 2023-11-14 | 2023-07-20 | -84 | 3. Non-timely worked |  |  | 37.018763460 | -119.580955820 | 2 | 604775 | HNT622085952 | Hazard Notification | NEW |  | Additional constraint due to access issues.
-1056170724 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC 12+ | X6FR1026326 | RD2 | 1 | Central Valley | FR | CLOVIS | FR | 0254151102 | AUBERRY 1102 | O | Complete | No Constraint | 2023-06-21 | 2023-11-14 | 2023-07-20 | -84 | 3. Non-timely worked |  |  | 37.018772000 | -119.580984000 | 2 | 604773 | HNT622085849 | Hazard Notification | NEW |  | Additional constraint due to access issues.
-1056092737 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZRC to 11 | JAST1041637 | RD1 | 1 | Central Valley | ST | MOKELUMNE H | CA | 0163201102 | WEST POINT 1102 | O | Complete | No Constraint | 2023-06-29 | 2023-08-04 | 2023-07-28 | -6 | 3. Non-timely worked |  |  | 38.276174090 | -120.544787340 | 2 | [5 empty] | Unit completed late by vendor.
-1056098120 | VMS | Distribution | M | Priority 2 (P2) | Cork Oak | ZRC 12+ | DMST1037695 | RD2 | 1 | Central Valley | ST | STOCKTON | SJ | 0163301105 | HAMMER 1105 | O | Complete | No Constraint | 2023-07-31 | 2023-09-11 | 2023-08-28 | -11 | 3. Non-timely worked |  |  | 38.017081000 | -121.338830000 | [6 empty] | Additional constraint due to customer refusal issues.
-1057468838 | VMS | Distribution | M | Priority 2 (P2) | Cedar | ZRC 12+ | YOYO1270274 | RD2 | 1 | Central Valley | YO | MARIPOSA | MR | 025445210C | MARIPOSA 2101-C | O | Complete | No Constraint | 2023-02-02 | 2023-03-15 | 2023-03-03 | -9 | 3. Non-timely worked |  |  | 37.502810000 | -119.813103000 | 3 | [5 empty] | Vendor Billing Error

## North Coast
iTreeRecsID | Source | Circuit type | sAcctType | PRIORITY | Tree_Type | TRIM_TYPE | sWorkReq | ActualTrimCode | Tree_Qty | Region | Division | sCity | sCountyCode | scircuit | CIRCUIT | sNotification | Completion status - field | Constraint? | dtInspDate | dtWorkDate | Due date per compliance | Business Days Between Work Date and Compliance Date | Timeliness status | Location_Lat | Location_Long | Tree_Lat | Tree_Long | iHFTDTier | iRefusalID | sDocNumber | REFUSAL_TYPE | sRefusalStatus | dtResolved | Reason for Completion after Compliance Due Date
-1056155561 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | NPNB1023705 | RD2 | 1 | North Coast South | NB | NAPA | NA | 0043291104 | PUEBLO 1104 | O | Complete | Constraint_ITS_past | 2023-06-30 | 2023-11-17 | 2023-10-03 | -34 | 3. Non-timely worked |  |  | 38.352910000 | -122.283682000 |  | 608171 | RFT728133705 | Refusal | CLOSE | 2023-07-27 | Additional constraint added on 9/5/23 and released 10/20/23.
-1056271349 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC 12+ | LCNC1003098 | RD2 | 1 | North Coast | NC | UPPER LAKE | LK | 0042871101 | UPPER LAKE 1101 | O | Complete | Constraint_ITS_past | 2023-05-09 | 2023-08-31 | 2023-07-03 | -44 | 3. Non-timely worked |  |  | 39.197630930 | -122.975887520 | 2 | 539252 | RFT517145004 | Refusal | CLOSE | 2023-06-02 | Additional constraint due to access issue.
-1057668840 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | TopDirecti | LCNC1002237 | U02 | 1 | North Coast | NC | WITTER SPRI | LK | 0042871101 | UPPER LAKE 1101 | O | Complete | Constraint_ITS_past | 2023-01-25 | 2023-07-14 | 2023-07-03 | -10 | 3. Non-timely worked |  |  | 39.199032000 | -122.978132000 | 2 | 539252 | RFT517145004 | Refusal | CLOSE | 2023-06-02 | Additional constraint due to access issue.
-1057669098 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | TopDirecti | LCNC1002237 | U02 | 1 | North Coast | NC | UPPER LAKE | LK | 0042871101 | UPPER LAKE 1101 | O | Complete | Constraint_ITS_past | 2023-01-25 | 2023-07-14 | 2023-07-03 | -10 | 3. Non-timely worked |  |  | 39.197573000 | -122.975973000 | 2 | 539252 | RFT517145004 | Refusal | CLOSE | 2023-06-02 | Additional constraint due to access issue.
-1057030146 | VMS | Distribution | M | Priority 2 (P2) | Willow | ZR CLEAR | UCNC1005616 | BP1 | 1 | North Coast | NC | FORT BRAGG | ME | 0042761101 | FORT BRAGG STA A 1101 | O | Complete | No Constraint | 2023-02-21 | 2023-03-22 | 2023-03-21 | -2 | 3. Non-timely worked |  |  | 39.525504930 | -123.730416390 | 2 | [5 empty] | Additional constraint due to access issue.
-1056028299 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC 12+ | SRNC1032617 | RD2 | 1 | North Coast | NC | SANTA ROSA | SN | 0043182103 | BELLEVUE 2103 | O | Complete | No Constraint | 2023-09-23 | 2023-10-23 | 2023-10-20 | -2 | 3. Non-timely worked |  |  | 38.375779580 | -122.695536890 | [6 empty] | Additional constraint due to access issue.
-1056028300 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | SRNC1032617 | RD2 | 1 | North Coast | NC | SANTA ROSA | SN | 0043182103 | BELLEVUE 2103 | O | Complete | No Constraint | 2023-09-23 | 2023-10-23 | 2023-10-20 | -2 | 3. Non-timely worked |  |  | 38.382304870 | -122.685011600 | [6 empty] | Additional constraint due to access issue.
-1056228658 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC 12+ | NPNB1023580 | RD2 | 1 | North Coast South | NB | ST HELENA | NA | 0043432103 | SILVERADO 2103 | O | Complete | Constraint_ITS_past | 2023-05-31 | 2023-09-05 | 2023-08-29 | -6 | 3. Non-timely worked |  |  | 38.509507300 | -122.390355190 | 3 | 605259 | RFT628151109 | Refusal | CLOSE | 2023-08-01 | Additional constraint due to access issue.
-1056228659 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC 12+ | NPNB1023580 | RD2 | 1 | North Coast South | NB | ST HELENA | NA | 0043432103 | SILVERADO 2103 | O | Complete | Constraint_ITS_past | 2023-05-31 | 2023-09-05 | 2023-08-29 | -6 | 3. Non-timely worked |  |  | 38.509512250 | -122.390364910 | 3 | 605259 | RFT628151109 | Refusal | CLOSE | 2023-08-01 | Additional constraint due to access issue.
-1056228660 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC 12+ | NPNB1023580 | RD2 | 1 | North Coast South | NB | ST HELENA | NA | 0043432103 | SILVERADO 2103 | O | Complete | Constraint_ITS_past | 2023-05-31 | 2023-09-05 | 2023-08-29 | -6 | 3. Non-timely worked |  |  | 38.509488000 | -122.390353000 | 3 | 605259 | RFT628151109 | Refusal | CLOSE | 2023-08-01 | Additional constraint due to access issue.
-1057199509 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | UCNC1005659 | RD2 | 1 | North Coast | NC | GUALALA | ME | 0042841112 | GUALALA 1112 | O | Complete | Constraint_ITS_past | 2023-02-15 | 2023-04-03 | 2023-03-17 | -12 | 3. Non-timely worked |  |  | 38.802263000 | -123.562413000 | 2 | 583405 | RPT216122404 | Riparian | CLOSE | 2023-02-16 | Additional constraint due to coastal comission.
-1056162680 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZMAJOR R1 | SRNC1031958 | MA1 | 1 | North Coast | NC | HEALDSBURG | SN | 0042751113 | FITCH MOUNTAIN 1113 | O | Complete | Constraint_ITS_past | 2023-06-27 | 2023-08-15 | 2023-07-27 | -14 | 3. Non-timely worked |  |  | 38.576810030 | -122.966681600 | 3 | 560391 | RFT920072000 | Refusal | CLOSE | 2023-06-28 | Additional constraint due to customer refusal.
-1057786448 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | SRNC1029145 | RD2 | 1 | North Coast | NC | PENNGROVE | SN | 0043471101 | PENNGROVE 1101 | O | Complete | No Constraint | 2023-01-20 | 2023-02-20 | 2023-02-17 | -2 | 3. Non-timely worked |  |  | 38.297705900 | -122.675595540 | [6 empty] | Additional constraint due to customer refusal.
-1056115729 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC 12+ | SRNC1031690 | RD2 | 1 | North Coast | NC | SONOMA | SN | 0043071102 | DUNBAR 1102 | O | Complete | No Constraint | 2023-07-17 | 2023-08-15 | 2023-08-14 | -2 | 3. Non-timely worked |  |  | 38.331997280 | -122.526945490 | 2 | [5 empty] | Additional constraint due to customer refusal.
-1056115730 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | SRNC1031690 | RD2 | 1 | North Coast | NC | SONOMA | SN | 0043071102 | DUNBAR 1102 | O | Complete | No Constraint | 2023-07-17 | 2023-08-15 | 2023-08-14 | -2 | 3. Non-timely worked |  |  | 38.331937060 | -122.527008550 | 2 | [5 empty] | Additional constraint due to customer refusal.
-1056115731 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZRC 12+ | SRNC1031690 | RD2 | 1 | North Coast | NC | SONOMA | SN | 0043071102 | DUNBAR 1102 | O | Complete | No Constraint | 2023-07-17 | 2023-08-15 | 2023-08-14 | -2 | 3. Non-timely worked |  |  | 38.331921000 | -122.526975540 | 2 | [5 empty] | Additional constraint due to customer refusal.
-1056481027 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZRC 12+ | NPNB1023340 | RD2 | 1 | North Coast South | NB | NAPA | NA | 0043292103 | PUEBLO 2103 | O | Complete | Constraint_ITS_past | 2023-03-23 | 2023-06-20 | 2023-05-02 | -36 | 3. Non-timely worked |  |  | 38.326452120 | -122.400285620 | 2 | 567414 | RFT027145454 | Refusal | CLOSE | 2023-04-04 | Additional constraint due to customer refusal.
-1056481028 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | NPNB1023340 | RD2 | 1 | North Coast South | NB | NAPA | NA | 0043292103 | PUEBLO 2103 | O | Complete | Constraint_ITS_past | 2023-03-23 | 2023-06-20 | 2023-05-02 | -36 | 3. Non-timely worked |  |  | 38.326692300 | -122.400352740 | 2 | 567414 | RFT027145454 | Refusal | CLOSE | 2023-04-04 | Additional constraint due to customer refusal.
-1056077685 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZMAJOR R2 | NPNB1023911 | MA2 | 1 | North Coast South | NB | CALISTOGA | NA | 0042711101 | CALISTOGA 1101 | O | Complete | No Constraint | 2023-08-16 | 2023-11-28 | 2023-09-14 | -54 | 3. Non-timely worked |  |  | 38.570778810 | -122.591271780 | 3 | [5 empty] | Additional constraint due to customer refusal.
-1056223661 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZRC 12+ | MANB1031191 | RD2 | 1 | North Coast South | NB | NICASIO | MN | 0043021101 | WOODACRE 1101 | O | Complete | No Constraint | 2023-06-05 | 2023-07-06 | 2023-07-05 | -2 | 3. Non-timely worked |  |  | 38.051362460 | -122.661871360 | 3 | [5 empty] | Additional constraint due to customer refusal.
-1056116421 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZRC 12+ | MANB1032034 | RD2 | 1 | North Coast South | NB | POINT REYES | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-07-17 | 2024-03-05 | 2023-08-14 | -147 | 3. Non-timely worked |  |  | 38.068422060 | -122.539755260 | [6 empty] | Additional constraint due to park permits.
-1056070429 | VMS | Distribution | M | Priority 2 (P2) | Alder | ZRC 12+ | MANB1031560 | RD2 | 1 | North Coast South | NB | INVERNESS | MN | 0042291101 | OLEMA 1101 | O | Complete | No Constraint | 2023-08-23 | 2023-10-06 | 2023-09-21 | -12 | 3. Non-timely worked |  |  | 38.109311410 | -122.894411090 | 2 | [5 empty] | Additional constraint due to park permits.
-1056070430 | VMS | Distribution | M | Priority 2 (P2) | Alder | ZRC 12+ | MANB1031560 | RD2 | 1 | North Coast South | NB | INVERNESS | MN | 0042291101 | OLEMA 1101 | O | Complete | No Constraint | 2023-08-23 | 2023-10-06 | 2023-09-21 | -12 | 3. Non-timely worked |  |  | 38.109317130 | -122.894387860 | 2 | [5 empty] | Additional constraint due to park permits.
-1056070431 | VMS | Distribution | M | Priority 2 (P2) | Alder | ZRC 12+ | MANB1031560 | RD2 | 1 | North Coast South | NB | INVERNESS | MN | 0042291101 | OLEMA 1101 | O | Complete | No Constraint | 2023-08-23 | 2023-10-06 | 2023-09-21 | -12 | 3. Non-timely worked |  |  | 38.109356900 | -122.894299920 | 2 | [5 empty] | Additional constraint due to park permits.
-1055983105 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | RC to 11.9 | MANB1032366 | U01 | 1 | North Coast South | NB | STINSON BEA | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-06 | 2024-06-26 | 2023-12-07 | -145 | 3. Non-timely worked |  |  | 37.890721000 | -122.620307000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055982945 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-06 | 2024-06-26 | 2023-12-07 | -145 | 3. Non-timely worked |  |  | 37.890712000 | -122.617842000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055982955 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-06 | 2024-06-26 | 2023-12-07 | -145 | 3. Non-timely worked |  |  | 37.890766000 | -122.618060000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055982970 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-06 | 2024-06-26 | 2023-12-07 | -145 | 3. Non-timely worked |  |  | 37.890737000 | -122.618095000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055983151 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-06 | 2024-06-27 | 2023-12-07 | -146 | 3. Non-timely worked |  |  | 37.891327000 | -122.622692000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055975520 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | MILL VALLEY | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-21 | 2024-06-25 | 2023-12-21 | -134 | 3. Non-timely worked |  |  | 37.895171000 | -122.594257000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055975555 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | MILL VALLEY | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-21 | 2024-06-25 | 2023-12-21 | -134 | 3. Non-timely worked |  |  | 37.895077000 | -122.594369000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055975564 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | MILL VALLEY | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-21 | 2024-06-25 | 2023-12-21 | -134 | 3. Non-timely worked |  |  | 37.895097000 | -122.594397000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055969912 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | RC 12 PLUS | MANB1032062 | U02 | 1 | North Coast South | NB | SAUSALITO | MN | 0042491102 | SAUSALITO 1102 | O | Complete | No Constraint | 2023-12-01 | 2024-03-04 | 2024-01-02 | -45 | 3. Non-timely worked |  |  | 37.850757000 | -122.491064000 | 2 | [5 empty] | Additional constraint due to park permits.
-1055969005 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032262 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042291101 | OLEMA 1101 | O | Complete | No Constraint | 2023-12-04 | 2024-05-09 | 2024-01-03 | -92 | 3. Non-timely worked |  |  | 37.908641000 | -122.653150000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055968493 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | RC 12 PLUS | MANB1032262 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042291101 | OLEMA 1101 | O | Complete | No Constraint | 2023-12-05 | 2024-05-08 | 2024-01-04 | -90 | 3. Non-timely worked |  |  | 37.909477000 | -122.649324000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055968506 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | RC 12 PLUS | MANB1032262 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042291101 | OLEMA 1101 | O | Complete | No Constraint | 2023-12-05 | 2024-05-13 | 2024-01-04 | -93 | 3. Non-timely worked |  |  | 37.909407000 | -122.649319000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055966024 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | MILL VALLEY | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-12-07 | 2024-06-24 | 2024-01-08 | -121 | 3. Non-timely worked |  |  | 37.895896000 | -122.591421000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055965270 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | MUIR BEACH | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-12-08 | 2024-06-24 | 2024-01-09 | -120 | 3. Non-timely worked |  |  | 37.895304000 | -122.588559000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055965274 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | MUIR BEACH | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-12-08 | 2024-06-24 | 2024-01-09 | -120 | 3. Non-timely worked |  |  | 37.895232000 | -122.588567000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055965355 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-12-08 | 2024-06-27 | 2024-01-09 | -123 | 3. Non-timely worked |  |  | 37.910632000 | -122.645949000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055961135 | VMS | Distribution | M | Priority 2 (P2) | Canyon Live Oak | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | MILL VALLEY | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-12-13 | 2024-06-24 | 2024-01-12 | -117 | 3. Non-timely worked |  |  | 37.892807000 | -122.583007000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055960408 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | RC 12 PLUS | MANB1032366 | U02 | 1 | North Coast South | NB | MILL VALLEY | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-12-14 | 2024-06-24 | 2024-01-16 | -115 | 3. Non-timely worked |  |  | 37.892546000 | -122.582467000 | 3 | [5 empty] | Additional constraint due to park permits.
-1055976039 | VMS | Distribution | M | Priority 2 (P2) | Monterey Pine | ZRC 12+ | MANB1032264 | RD2 | 1 | North Coast South | NB | SAUSALITO | MN | 0042491102 | SAUSALITO 1102 | O | Complete | No Constraint | 2023-11-17 | 2024-05-09 | 2023-12-19 | -103 | 3. Non-timely worked |  |  | 37.822384160 | -122.529897990 | 2 | [5 empty] | Additional constraint due to quarantine.
-1055979053 | VMS | Distribution | M | Priority 2 (P2) | Monterey Cypress | RC 12 PLUS | MANB1032058 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-14 | 2024-03-04 | 2023-12-14 | -58 | 3. Non-timely worked |  |  | 37.898961000 | -122.635454000 | 3 | [5 empty] | Additional constraint due to quarantine.
-1055979096 | VMS | Distribution | M | Priority 2 (P2) | Monterey Cypress | RC 12 PLUS | MANB1032058 | U02 | 1 | North Coast South | NB | STINSON BEA | MN | 0042261101 | BOLINAS 1101 | O | Complete | No Constraint | 2023-11-14 | 2024-03-04 | 2023-12-14 | -58 | 3. Non-timely worked |  |  | 37.898769000 | -122.635797000 | 3 | [5 empty] | Additional constraint due to quarantine.
-1056251700 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | SRNC1030811 | RD1 | 1 | North Coast | NC | SONOMA | SN | 0043071103 | DUNBAR 1103 | O | Complete | Constraint_ITS_past | 2023-05-17 | 2023-09-15 | 2023-09-08 | -6 | 3. Non-timely worked |  |  | 38.322517000 | -122.495667000 |  | 601328 | RFT523080309 | Refusal | CLOSE | 2023-08-10 | Additional constraint in system.
-1057403266 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | SRNC1029185 | RD2 | 1 | North Coast | NC | CLOVERDALE | SN | 0042821102 | CLOVERDALE 1102 | O | Complete | Constraint_ITS_past | 2023-02-07 | 2023-05-24 | 2023-05-09 | -12 | 3. Non-timely worked |  |  | 38.774323320 | -123.001080520 |  | 586402 | NST306104101 | Nest Review | RSLVD | 2023-03-22 | Additional constraint of work due to nesting season.
-1056079422 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZRC 12+ | SRNC1032061 | RD2 | 1 | North Coast | NC | JENNER | SN | 0042851121 | FORT ROSS 1121 | O | Complete | No Constraint | 2023-08-15 | 2023-09-14 | 2023-09-13 | -2 | 3. Non-timely worked |  |  | 38.546293420 | -123.294120880 | 2 | [5 empty] | Compliant Tree work completed 9/08/2023 - work request provided on early report. Data entry error.
-1056228984 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZPRUNE R1 | MANB1032034 | MN1 | 1 | North Coast South | NB | BOLINAS | MN | 0042261101 | BOLINAS 1101 | O | Complete | Constraint_ITS_past | 2023-05-31 | 2024-04-25 | 2023-11-27 | -109 | 3. Non-timely worked |  |  | 37.988761670 | -122.740410480 | 3 | 602121 | ECD601113035 | Archeology | CLOSE | 2023-10-25 | Constraints were resolved prematurely.
-1056070517 | VMS | Distribution | M | Priority 2 (P2) | Monterey Pine | ZPRUNE R4 | SRNC1032166 | NW | 1 | North Coast | NC | SEBASTOPOL | SN | 0042091101 | MIRABEL 1101 | O | Complete | No Constraint | 2023-08-23 | 2023-09-22 | 2023-09-21 | -2 | 3. Non-timely worked |  |  | 38.453876760 | -122.900212750 | 2 | [5 empty] | Data entry error.
-1056251698 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | SRNC1030811 | NWK | 1 | North Coast | NC | SONOMA | SN | 0043071103 | DUNBAR 1103 | O | Complete | Constraint_ITS_past | 2023-05-17 | 2023-09-28 | 2023-09-08 | -15 | 3. Non-timely worked |  |  | 38.321858000 | -122.495190000 |  | 601328 | RFT523080309 | Refusal | CLOSE | 2023-08-10 | ITS resolved 9/18/23; Work release date was set at 9/18/23; Work completed on date of release date. Data entry error.
-1056251699 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | SRNC1030811 | NWK | 1 | North Coast | NC | SONOMA | SN | 0043071103 | DUNBAR 1103 | O | Complete | Constraint_ITS_past | 2023-05-17 | 2023-09-28 | 2023-09-08 | -15 | 3. Non-timely worked |  |  | 38.322272000 | -122.495344000 |  | 601328 | RFT523080309 | Refusal | CLOSE | 2023-08-10 | ITS resolved 9/18/23; Work release date was set at 9/18/23; Work completed on date of release date. Data entry error.
-1056249665 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | SRNC1031066 | RD2 | 1 | North Coast | NC | PETALUMA | SN | 0042631109 | PETALUMA C 1109 | O | Complete | Constraint_ITS_past | 2023-05-18 | 2023-08-02 | 2023-06-20 | -32 | 3. Non-timely worked |  |  | 38.215275640 | -122.626840530 | 2 | 601038 | RFT519073917 | Refusal | CLOSE | 2023-05-19 | Refusal tree work flipped prematurely to resolved before released work was in tree crew hands; NTW approval set to resolution date; improper resolved date set
-1056086614 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | SRNC1032014 | RD2 | 1 | North Coast | NC | HEALDSBURG | SN | 0042751113 | FITCH MOUNTAIN 1113 | O | Complete | No Constraint | 2023-08-09 | 2023-09-14 | 2023-09-07 | -6 | 3. Non-timely worked |  |  | 38.520673590 | -122.884694840 | 2 | [5 empty] | Refusal-No ITS Ticket - Resolved Refusal Location - Record Flipped to okay prematurely
-1056093717 | VMS | Distribution | M | Priority 2 (P2) | Willow | ZRC 12+ | HBNC1033147 | NWK | 1 | North Coast | NC | ALDERPOINT | HU | 0192321121 | FORT SEWARD 1121 | O | Complete | Constraint_ITS_past | 2023-08-02 | 2023-10-16 | 2023-09-22 | -17 | 3. Non-timely worked |  |  | 40.173670350 | -123.606706610 | 2 | 564124 | RFT013163315 | LCE - Resolved | CLOSE | 2023-08-24 | Tree found completed on 8/23. Data entry error.
-1056239369 | VMS | Distribution | M | Priority 2 (P2) | Madrone | ZMAJOR R2 | HBNC1032581 | NWK | 1 | North Coast | NC | GARBERVILLE | HU | 0192221101 | GARBERVILLE 1101 | O | Complete | Constraint_ITS_past | 2023-05-24 | 2024-05-08 | 2023-10-09 | -153 | 3. Non-timely worked |  |  | 40.035522280 | -123.791159190 | 2 | 603484 | RFT620074701 | Refusal | CLOSE | 2023-07-21 | Tree was completed on HBNC1033931 on 4/15/24. Data entry error.
-1056167219 | VMS | Distribution | M | Priority 2 (P2) | Bigleaf Maple | ZRC 12+ | SRNC1031394 | RD2 | 1 | North Coast | NC | GLEN ELLEN | SN | 0043071102 | DUNBAR 1102 | O | Complete | No Constraint | 2023-06-23 | 2023-07-25 | 2023-07-24 | -2 | 3. Non-timely worked |  |  | 38.383346920 | -122.559793300 | 2 | [5 empty] | Tree work completed on 7/24/2023. Invoicing altered date on 7/25/2023—worked timely. - Vendor billing error.
-1057454651 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | ZMAJOR R1 | XBNC1003551 | MA1 | 1 | North Coast | NC | WILLOW CREE | HU | 0192171103 | WILLOW CREEK 1103 | O | Complete | Constraint_ITS_past | 2023-02-03 | 2023-06-01 | 2023-05-30 | -3 | 3. Non-timely worked |  |  | 40.903396680 | -123.610817720 | 2 | 585492 | OTT228105357 | Other | CLOSE | 2023-05-01 | Unit completed late by vendor.
-1056017593 | VMS | Distribution | M | Priority 2 (P2) | Bamboo | ZR PRUNE | SRNC1032738 | BP1 | 1 | North Coast | NC | SANTA ROSA | SN | 0042151104 | SANTA ROSA A 1104 | O | Complete | No Constraint | 2023-10-04 | 2023-11-07 | 2023-11-01 | -5 | 3. Non-timely worked |  |  | 38.471862660 | -122.684146000 | 3 | [5 empty] | Unit completed late by vendor.
-1056053826 | VMS | Distribution | M | Priority 2 (P2) | Locust, Black | ZR CLEAR | HBNC1033333 | BPG | 1 | North Coast | NC | REDWAY | HU | 0192221102 | GARBERVILLE 1102 | O | Complete | No Constraint | 2023-09-01 | 2023-10-04 | 2023-10-02 | -3 | 3. Non-timely worked |  |  | 40.124575210 | -123.834009590 | 2 | [5 empty] | Unit completed late by vendor.
-1055975376 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZR CLEAR | SRNC1033081 | BPG | 1 | North Coast | NC | CAZADERO | SN | 0042851121 | FORT ROSS 1121 | O | Complete | No Constraint | 2023-11-20 | 2023-12-21 | 2023-12-20 | -2 | 3. Non-timely worked |  |  | 38.582170290 | -123.242983970 | 2 | [5 empty] | Unit completed late by vendor.
-1056010940 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R1 | HBNC1033481 | MA1 | 1 | North Coast | NC | KNEELAND | HU | 0192021122 | ARCATA 1122 | O | Complete | No Constraint | 2023-10-09 | 2023-11-08 | 2023-11-06 | -3 | 3. Non-timely worked |  |  | 40.791224380 | -124.057222480 | [6 empty] | Unit completed late by vendor.
-1056009793 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R2 | HBNC1033477 | MA2 | 1 | North Coast | NC | ARCATA | HU | 0192391101 | JANES CREEK 1101 | O | Complete | No Constraint | 2023-10-10 | 2023-11-08 | 2023-11-07 | -2 | 3. Non-timely worked |  |  | 40.908570310 | -124.045293530 | [6 empty] | Unit completed late by vendor.
-1056149674 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZMAJOR R3 | SRNC1031556 | MA3 | 1 | North Coast | NC | GLEN ELLEN | SN | 0043071103 | DUNBAR 1103 | O | Complete | No Constraint | 2023-06-22 | 2023-07-24 | 2023-07-21 | -2 | 3. Non-timely worked |  |  | 38.372123850 | -122.521864080 | 2 | [5 empty] | Unit completed late by vendor.
-1056023179 | VMS | Distribution | M | Priority 2 (P2) | Cottonwood, Black | ZPRUNE R2 | UKNC1040694 | MN2 | 1 | North Coast | NC | HOPLAND | ME | 0042251101 | HOPLAND 1101 | O | Complete | No Constraint | 2023-09-29 | 2023-10-28 | 2023-10-27 | -1 | 3. Non-timely worked |  |  | 38.989128450 | -123.058991520 | 2 | [5 empty] | Unit completed late by vendor.
-1057701871 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | SRNC1029155 | RD2 | 1 | North Coast | NC | SANTA ROSA | SN | 0043321103 | RINCON 1103 | O | Complete | No Constraint | 2023-01-23 | 2023-02-22 | 2023-02-21 | -2 | 3. Non-timely worked |  |  | 38.507407680 | -122.641124920 | 3 | [5 empty] | Unit completed late by vendor.
-1056381407 | VMS | Distribution | M | Priority 2 (P2) | Tan Oak | ZRC 12+ | HBNC1032342 | RD2 | 1 | North Coast | NC | WHITETHORN | HU | 0192221102 | GARBERVILLE 1102 | O | Complete | No Constraint | 2023-04-17 | 2023-05-18 | 2023-05-15 | -4 | 3. Non-timely worked |  |  | 40.104251120 | -123.908489290 | 2 | [5 empty] | Unit completed late by vendor.
-1056229543 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | SRNC1031064 | RD2 | 1 | North Coast | NC | OCCIDENTAL | SN | 0042811111 | MONTE RIO 1111 | O | Complete | No Constraint | 2023-05-31 | 2023-06-30 | 2023-06-29 | -2 | 3. Non-timely worked |  |  | 38.469244070 | -123.029455450 | 3 | [5 empty] | Unit completed late by vendor.
-1056218020 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | ZRC to 11 | SRNC1031582 | RD2 | 1 | North Coast | NC | BODEGA BAY | SN | 0042271105 | COTATI 1105 | O | Complete | No Constraint | 2023-06-07 | 2023-07-11 | 2023-07-07 | -3 | 3. Non-timely worked | [10 empty] | Unit completed late by vendor.
-1056166738 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | HBNC1032981 | RD2 | 1 | North Coast | NC | LEGGETT | ME | 0192221101 | GARBERVILLE 1101 | O | Complete | No Constraint | 2023-06-23 | 2023-10-19 | 2023-07-24 | -64 | 3. Non-timely worked |  |  | 39.856614000 | -123.719042000 | 2 | [5 empty] | Unit completed late by vendor.
-1056062813 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | SRNC1032228 | RD2 | 1 | North Coast | NC | FORESTVILLE | SN | 0042091102 | MIRABEL 1102 | O | Complete | No Constraint | 2023-08-28 | 2023-09-27 | 2023-09-26 | -2 | 3. Non-timely worked |  |  | 38.498878710 | -122.913060310 | 3 | [5 empty] | Unit completed late by vendor.
-1056052034 | VMS | Distribution | M | Priority 2 (P2) | Birch | ZRC 12+ | SRNC1032682 | RD2 | 1 | North Coast | NC | SEBASTOPOL | SN | 0042571101 | MOLINO 1101 | O | Complete | No Constraint | 2023-09-05 | 2023-10-04 | 2023-10-03 | -2 | 3. Non-timely worked |  |  | 38.349253700 | -122.824615260 | [6 empty] | Unit completed late by vendor.
-1056041555 | VMS | Distribution | M | Priority 2 (P2) | Ash | ZRC 12+ | UKNC1040661 | RD2 | 1 | North Coast | NC | COVELO | ME | 0043061101 | COVELO 1101 | O | Complete | No Constraint | 2023-09-13 | 2023-10-12 | 2023-10-11 | -2 | 3. Non-timely worked |  |  | 39.746643890 | -123.234001450 | [6 empty] | Unit completed late by vendor.
-1056041558 | VMS | Distribution | M | Priority 2 (P2) | Ash | ZRC 12+ | UKNC1040661 | RD2 | 1 | North Coast | NC | COVELO | ME | 0043061101 | COVELO 1101 | O | Complete | No Constraint | 2023-09-13 | 2023-10-12 | 2023-10-11 | -2 | 3. Non-timely worked |  |  | 39.746668580 | -123.233988890 | [6 empty] | Unit completed late by vendor.
-1056027257 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC 12+ | SRNC1032623 | RD2 | 1 | North Coast | NC | HEALDSBURG | SN | 0042751113 | FITCH MOUNTAIN 1113 | O | Complete | No Constraint | 2023-09-25 | 2023-12-01 | 2023-10-23 | -30 | 3. Non-timely worked |  |  | 38.603038030 | -122.892428130 | 2 | [5 empty] | Unit completed late by vendor.
-1056016467 | VMS | Distribution | M | Priority 2 (P2) | Liq Ambar (Sw Gum) | ZRC 12+ | SRNC1032761 | RD2 | 1 | North Coast | NC | SANTA ROSA | SN | 004HW01201 | Hwy 12 (Sonoma) | O | Complete | No Constraint | 2023-10-04 | 2023-12-14 | 2023-11-01 | -32 | 3. Non-timely worked |  |  | 38.447799360 | -122.688359870 | [6 empty] | Unit completed late by vendor.
-1056056246 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R2 | HBNC1033319 | MA2 | 1 | North Coast | NC | BENBOW | HU | 0192221101 | GARBERVILLE 1101 | O | Complete | No Constraint | 2023-08-30 | 2023-09-29 | 2023-09-28 | -2 | 3. Non-timely worked |  |  | 40.067016340 | -123.762241560 | [6 empty] | Unit was noted to be constrained due to access restriction, unit cleared and worked next day per non timely sheet
-1056177995 | VMS | Distribution | M | Priority 2 (P2) | Bay, Calif. | ZMAJOR R3 | HBNC1032783 | MA3 | 1 | North Coast | NC | PIERCY | ME | 0192221101 | GARBERVILLE 1101 | O | Complete | No Constraint | 2023-06-16 | 2024-04-04 | 2023-07-18 | -188 | 3. Non-timely worked |  |  | 39.932540800 | -123.761957440 | 2 | [5 empty] | Vendor billing error.
-1056177994 | VMS | Distribution | M | Priority 2 (P2) | Canyon Live Oak | ZRC to 11 | HBNC1032783 | RD1 | 1 | North Coast | NC | PIERCY | ME | 0192221101 | GARBERVILLE 1101 | O | Complete | No Constraint | 2023-06-16 | 2024-04-25 | 2023-07-18 | -203 | 3. Non-timely worked |  |  | 39.933152670 | -123.762588150 | 2 | [5 empty] | Vendor billing error.
-1056250360 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC 12+ | SRNC1030829 | RD2 | 1 | North Coast | NC | SANTA ROSA | SN | 0043321104 | RINCON 1104 | O | Complete | No Constraint | 2023-05-18 | 2023-06-20 | 2023-06-16 | -3 | 3. Non-timely worked |  |  | 38.456372810 | -122.682630170 | 3 | [5 empty] | Vendor billing error.
-1056162564 | VMS | Distribution | M | Priority 2 (P2) | Eucalyptus | P1RC 12+ | SRNC1031423 | U02 | 1 | North Coast | NC | PENNGROVE | MN | 0042271102 | COTATI 1102 | O | Complete | No Constraint | 2023-06-27 | 2023-07-31 | 2023-07-26 | -4 | 3. Non-timely worked |  |  | 38.304213000 | -122.896972000 | [6 empty] | Vendor billing error.
-1056102650 | VMS | Distribution | M | Priority 2 (P2) | Coast Live Oak | ZRC to 11 | NPNB1023839 | NWK | 1 | North Coast South | NB | ANGWIN | NA | 0043432104 | SILVERADO 2104 | O | Complete | Constraint_ITS_past | 2023-07-26 | 2023-11-16 | 2023-09-21 | -41 | 3. Non-timely worked |  |  | 38.556415010 | -122.455228630 | 3 | 609798 | RFT815152208 | Refusal | CLOSE | 2023-08-23 | Vendor billing error.
-1056105183 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | NPNB1023877 | NWK | 1 | North Coast South | NB | Unincorpora | SN | 0042711101 | CALISTOGA 1101 | O | Complete | Constraint_ITS_past | 2023-07-25 | 2024-02-16 | 2023-12-14 | -47 | 3. Non-timely worked |  |  | 38.606858770 | -122.652716710 | 3 | 610336 | RFT818090737 | Refusal | CLOSE | 2023-11-14 | Vendor billing error.
-1056074250 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | ZMAJOR R4 | NPNB1023916 | NWK | 1 | North Coast South | NB | CALISTOGA | NA | 0042711101 | CALISTOGA 1101 | O | Complete | Constraint_ITS_past | 2023-08-21 | 2024-05-14 | 2024-02-13 | -66 | 3. Non-timely worked |  |  | 38.572133560 | -122.598704100 | 3 | 613503 | RFT913092353 | Refusal | CLOSE | 2023-12-18 | Vendor billing error.
-1056088757 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZPRUNE R4 | NPNB1023877 | MN4 | 1 | North Coast South | NB | CALISTOGA | NA | 0042711101 | CALISTOGA 1101 | O | Complete | Constraint_ITS_past | 2023-08-08 | 2023-10-02 | 2023-09-15 | -12 | 3. Non-timely worked |  |  | 38.588483080 | -122.547088850 | 3 | 610027 | RFT816155922 | Refusal | CLOSE | 2023-08-17 | Vendor data entry error.

## North Valley
iTreeRecsID | Source | Circuit type | sAcctType | PRIORITY | Tree_Type | TRIM_TYPE | sWorkReq | ActualTrimCode | Tree_Qty | Region | Division | sCity | sCountyCode | scircuit | CIRCUIT | sNotification | Completion status - field | Constraint? | dtInspDate | dtWorkDate | Due date per compliance | Business Days Between Work Date and Compliance Date | Timeliness status | Location_Lat | Location_Long | Tree_Lat | Tree_Long | iHFTDTier | iRefusalID | sDocNumber | REFUSAL_TYPE | sRefusalStatus | dtResolved | Reason for Completion after Compliance Due Date
-1056103954 | VMS | Distribution | M | Priority 2 (P2) | Black Walnut | ZRC 12+ | CHNV1049528 | RD2 | 1 | North Valley | NV | CHICO | BU | 0102971111 | SYCAMORE CREEK 1111 | O | Complete | No Constraint | 2023-07-25 | 2023-08-23 | 2023-08-22 | -2 | 3. Non-timely worked |  |  | 39.837454860 | -121.844475240 | 2 | [5 empty] | Additional constraint due to access issue.
-1056010429 | VMS | Distribution | M | Priority 2 (P2) | Pecan | ZMAJOR R1 | CHNV1050183 | MA1 | 1 | North Valley | NV | CHICO | BU | 0102971105 | SYCAMORE CREEK 1105 | O | Complete | No Constraint | 2023-10-09 | 2023-11-07 | 2023-11-06 | -2 | 3. Non-timely worked |  |  | 39.755981090 | -121.821454670 | [6 empty] | Additional constraint due to access issue.
-1056074669 | VMS | Distribution | M | Priority 2 (P2) | Red Oak, Northern | ZMAJOR R3 | CHNV1049707 | MA3 | 1 | North Valley | NV | CHICO | BU | 0102041102 | NOTRE DAME 1102 | O | Complete | No Constraint | 2023-08-18 | 2023-09-19 | 2023-09-18 | -2 | 3. Non-timely worked |  |  | 39.742262900 | -121.820981840 | [6 empty] | Additional constraint due to line kill.
-1056172817 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R1 | SHNV1036429 | MA1 | 1 | North Valley | NV | KESWICK | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-10 | 2023-07-19 | -17 | 3. Non-timely worked |  |  | 40.618378750 | -122.663829020 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175847 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R1 | SHNV1036429 | MA1 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-10 | 2023-07-19 | -17 | 3. Non-timely worked |  |  | 40.611158660 | -122.657873640 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056176412 | VMS | Distribution | M | Priority 2 (P2) | Sugar Pine | ZMAJOR R1 | SHNV1036429 | MA1 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-10 | 2023-07-19 | -17 | 3. Non-timely worked |  |  | 40.608323760 | -122.654372300 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175510 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-10 | 2023-07-19 | -17 | 3. Non-timely worked |  |  | 40.615067360 | -122.661064450 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175795 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.611347870 | -122.657750920 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175802 | VMS | Distribution | M | Priority 2 (P2) | White Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.611268470 | -122.657680700 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175838 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-10 | 2023-07-19 | -17 | 3. Non-timely worked |  |  | 40.611189930 | -122.657817740 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175872 | VMS | Distribution | M | Priority 2 (P2) | White Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.611050070 | -122.657866470 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175874 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-10 | 2023-07-19 | -17 | 3. Non-timely worked |  |  | 40.611132020 | -122.657743790 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175878 | VMS | Distribution | M | Priority 2 (P2) | White Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.611027530 | -122.657881980 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175885 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-10 | 2023-07-19 | -17 | 3. Non-timely worked |  |  | 40.611128640 | -122.657682840 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175903 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMAJOR R2 | SHNV1036429 | MA2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.611064080 | -122.657715690 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175801 | VMS | Distribution | M | Priority 2 (P2) | White Fir | ZMAJOR R3 | SHNV1036429 | MA3 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-10 | 2023-07-19 | -17 | 3. Non-timely worked |  |  | 40.611302290 | -122.657748750 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056175844 | VMS | Distribution | M | Priority 2 (P2) | White Fir | ZMAJOR R3 | SHNV1036429 | MA3 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.611089080 | -122.657981110 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056176445 | VMS | Distribution | M | Priority 2 (P2) | Red Fir | ZMAJOR R3 | SHNV1036429 | MA3 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.607617020 | -122.654344190 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056174265 | VMS | Distribution | M | Priority 2 (P2) | Ponderosa Pine | ZMAJOR R2 | SHNV1036429 | NWK | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.614464520 | -122.660787250 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056225006 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | ZRC to 11 | SHNV1036430 | RD1 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-02 | 2023-08-10 | 2023-07-03 | -29 | 3. Non-timely worked |  |  | 40.608919620 | -122.527223150 | 3 | [5 empty] | Additional constraint due to National Park permit.
-1056220389 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZRC 12+ | SHNV1036430 | RD2 | 1 | North Valley | NV | WHISKEYTOWN | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-06 | 2023-08-10 | 2023-07-06 | -26 | 3. Non-timely worked |  |  | 40.613749410 | -122.522048030 | 3 | [5 empty] | Additional constraint due to National Park permit.
-1056172804 | VMS | Distribution | M | Priority 2 (P2) | Canyon Live Oak | ZRC 12+ | SHNV1036429 | RD2 | 1 | North Valley | NV | KESWICK | SH | 0103761102 | Whiskeytown NP | O | Complete | No Constraint | 2023-06-20 | 2023-08-08 | 2023-07-19 | -15 | 3. Non-timely worked |  |  | 40.621744040 | -122.669062420 | 2 | [5 empty] | Additional constraint due to National Park permit.
-1056074823 | VMS | Distribution | M | Priority 2 (P2) | Pecan | ZRC 12+ | CHNV1049709 | RD2 | 1 | North Valley | NV | CHICO | BU | 0102971109 | SYCAMORE CREEK 1109 | O | Complete | No Constraint | 2023-08-18 | 2023-09-19 | 2023-09-18 | -2 | 3. Non-timely worked |  |  | 39.757609730 | -121.802256100 | [6 empty] | Additional constraint due to traffic control.
-1056074885 | VMS | Distribution | M | Priority 2 (P2) | Pistache | ZRC 12+ | CHNV1049709 | RD2 | 1 | North Valley | NV | CHICO | BU | 0102971109 | SYCAMORE CREEK 1109 | O | Complete | No Constraint | 2023-08-18 | 2023-09-19 | 2023-09-18 | -2 | 3. Non-timely worked |  |  | 39.751455830 | -121.803535590 | [6 empty] | Additional constraint due to traffic control.
-1056052620 | VMS | Distribution | M | Priority 2 (P2) | English Walnut | ZRC 12+ | CHNV1049859 | NWK | 1 | North Valley | NV | CHICO | BU | 010OR00003 | SUMMER ORCHARDS | O | Complete | No Constraint | 2023-09-05 | 2023-10-31 | 2023-10-03 | -21 | 3. Non-timely worked |  |  | 39.722802340 | -121.921128740 | [6 empty] | Additional constraint due to weather delay.
-1056052640 | VMS | Distribution | M | Priority 2 (P2) | Walnut | ZRC 12+ | CHNV1049859 | NWK | 1 | North Valley | NV | CHICO | BU | 010OR00003 | SUMMER ORCHARDS | O | Complete | No Constraint | 2023-09-05 | 2023-10-31 | 2023-10-26 | -4 | 3. Non-timely worked |  |  | 39.724047140 | -121.920985140 | [6 empty] | Additional constraint due to weather delay.
-1056114953 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | SHNV1036157 | RD1 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-17 | 2023-08-15 | -3 | 3. Non-timely worked |  |  | 40.545605060 | -122.310875240 | 2 | [5 empty] | Unit completed late by tree crew vendor.
-1056115130 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC to 11 | SHNV1036156 | RD1 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-17 | 2023-08-15 | -3 | 3. Non-timely worked |  |  | 40.494460100 | -122.319178160 | [6 empty] | Unit completed late by tree crew vendor.
-1056097613 | VMS | Distribution | M | Priority 2 (P2) | Palm-Date | ZRC to 11 | SHNV1036364 | RD1 | 1 | North Valley | NV | RED BLUFF | TE | 0103541105 | RED BLUFF 1105 | O | Complete | No Constraint | 2023-07-31 | 2023-09-25 | 2023-08-28 | -21 | 3. Non-timely worked |  |  | 40.180531180 | -122.236781080 | [6 empty] | Unit completed late by tree crew vendor.
-1056114954 | VMS | Distribution | M | Priority 2 (P2) | Gray Pine | ZRC 12+ | SHNV1036157 | RD2 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-17 | 2023-08-15 | -3 | 3. Non-timely worked |  |  | 40.534797220 | -122.329383650 | 2 | [5 empty] | Unit completed late by tree crew vendor.
-1056114955 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | SHNV1036157 | RD2 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-17 | 2023-08-15 | -3 | 3. Non-timely worked |  |  | 40.534722780 | -122.330774240 | [6 empty] | Unit completed late by tree crew vendor.
-1056114956 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | SHNV1036157 | RD2 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-17 | 2023-08-15 | -3 | 3. Non-timely worked |  |  | 40.534812110 | -122.329082830 | 2 | [5 empty] | Unit completed late by tree crew vendor.
-1056114957 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | SHNV1036157 | RD2 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-16 | 2023-08-15 | -2 | 3. Non-timely worked |  |  | 40.534810790 | -122.325822240 | 2 | [5 empty] | Unit completed late by tree crew vendor.
-1056114958 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC 12+ | SHNV1036157 | RD2 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-16 | 2023-08-15 | -2 | 3. Non-timely worked |  |  | 40.534822610 | -122.318633870 | 2 | [5 empty] | Unit completed late by tree crew vendor.
-1056114959 | VMS | Distribution | M | Priority 2 (P2) | Interior Live Oak | ZRC 12+ | SHNV1036157 | RD2 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-16 | 2023-08-15 | -2 | 3. Non-timely worked |  |  | 40.534698470 | -122.307277560 | 2 | [5 empty] | Unit completed late by tree crew vendor.
-1056114960 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZRC 12+ | SHNV1036157 | RD2 | 1 | North Valley | NV | REDDING | SH | 0103441103 | JESSUP 1103 | O | Complete | No Constraint | 2023-07-18 | 2023-08-16 | 2023-08-15 | -2 | 3. Non-timely worked |  |  | 40.534683110 | -122.306708670 | 2 | [5 empty] | Unit completed late by tree crew vendor.

## Sierra
iTreeRecsID | Source | Circuit type | sAcctType | PRIORITY | Tree_Type | TRIM_TYPE | sWorkReq | ActualTrimCode | Tree_Qty | Region | Division | sCity | sCountyCode | scircuit | CIRCUIT | sNotification | Completion status - field | Constraint? | dtInspDate | dtWorkDate | Due date per compliance | Business Days Between Work Date and Compliance Date | Timeliness status | Location_Lat | Location_Long | Tree_Lat | Tree_Long | iHFTDTier | iRefusalID | sDocNumber | REFUSAL_TYPE | sRefusalStatus | dtResolved | Reason for Completion after Compliance Due Date
-1056391485 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC 12+ | CSSA1012234 | RD2 | 1 | Sierra | SA | MARYSVILLE | YU | 010321110B | HONCUT 1102-B | O | Complete | Constraint_ITS_past | 2023-04-13 | 2023-05-31 | 2023-05-24 | -6 | 3. Non-timely worked |  |  | 39.298661980 | -121.457864640 |  | 594685 | RFT420091514 | Refusal | CLOSE | 2023-04-26 | Constraint closed early.
-1056027312 | VMS | Distribution | M | Priority 2 (P2) | English Walnut | ZRC to 11 | SASA1100010 | RD1 | 1 | Sierra | SA | DIXON | SO | 0062061104 | DIXON 1104 | O | Complete | No Constraint | 2023-09-25 | 2023-11-01 | 2023-10-23 | -8 | 3. Non-timely worked |  |  | 38.424969010 | -121.844423870 | [6 empty] | Additional constraint due to soil condition.
-1056027337 | VMS | Distribution | M | Priority 2 (P2) | English Walnut | ZRC to 11 | SASA1100010 | RD1 | 1 | Sierra | SA | DIXON | SO | 0062061104 | DIXON 1104 | O | Complete | No Constraint | 2023-09-25 | 2023-11-01 | 2023-10-23 | -8 | 3. Non-timely worked |  |  | 38.424980660 | -121.844231010 | [6 empty] | Additional constraint due to soil condition.
-1056027347 | VMS | Distribution | M | Priority 2 (P2) | English Walnut | ZRC to 11 | SASA1100010 | RD1 | 1 | Sierra | SA | DIXON | SO | 0062061104 | DIXON 1104 | O | Complete | No Constraint | 2023-09-25 | 2023-11-01 | 2023-10-23 | -8 | 3. Non-timely worked |  |  | 38.424926070 | -121.844112540 | [6 empty] | Additional constraint due to soil condition.
-1057869767 | VMS | Distribution | M | Priority 2 (P2) | English Walnut | ZRC 12+ | CSSA1011640 | RD2 | 1 | Sierra | SA | MARYSVILLE | YU | 015OR1008 | Colgate Orchards Ph2 | O | Complete | No Constraint | 2023-01-17 | 2023-02-15 | 2023-02-14 | -2 | 3. Non-timely worked |  |  | 39.289274240 | -121.579376220 | [6 empty] | Additional constraint due to soil condition.
-1056132788 | VMS | Distribution | M | Priority 2 (P2) | Cedar | ZRC 12+ | SASA1099714 | RD2 | 1 | Sierra | SA | WINTERS | YO | 0063681102 | PUTAH CREEK 1102 | O | Complete | No Constraint | 2023-05-08 | 2023-07-14 | 2023-06-06 | -29 | 3. Non-timely worked |  |  | 38.521946570 | -121.969145830 | [6 empty] | Vendor completed late.
-1055999925 | VMS | Distribution | M | Priority 2 (P2) | Citrus | ZRC 12+ | SASA1100161 | RD2 | 1 | Sierra | SA | WEST SACRAM | YO | 0063131110 | WEST SACRAMENTO 1110 | O | Complete | No Constraint | 2023-10-17 | 2024-03-14 | 2023-11-15 | -87 | 3. Non-timely worked |  |  | 38.588962100 | -121.561143030 | [6 empty] | Vendor completed late.
-1056156671 | VMS | Distribution | M | Priority 2 (P2) | Lodgepole Pine | ZMAJOR R2 | SISI1204110 | MA2 | 1 | Sierra | SI | SODA SPRING | NE | 0152591101 | SUMMIT 1101 | O | Complete | Constraint_ITS_past | 2023-06-30 | 2023-10-18 | 2023-09-20 | -21 | 3. Non-timely worked |  |  | 39.325081820 | -120.385355080 | 2 | 608570 | RFT731161756 | Refusal | CLOSE | 2023-08-22 | Refusal, TW released 10/18, case close 10/19
-1056154132 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | ZMAJOR R5 | SISI1204030 | MA5 | 1 | Sierra | SI | GRASS VALLE | NE | 015248110M | BRUNSWICK 1105-M | O | Complete | Constraint_ITS_past | 2023-07-05 | 2023-08-23 | 2023-08-14 | -8 | 3. Non-timely worked |  |  | 39.232175000 | -121.023281000 | 3 | 605830 | DBM706074456 | Debris Management | RSLVD | 2023-07-17 | Location required wood haul, traffic control, multiple days and two different size bucket trucks to complete. All of the constraints were not logged in the ststem of record.
-1057645938 | VMS | Distribution | M | Priority 2 (P2) | Ponderosa Pine | ZMAJOR R3 | SISI1200499 | NWK | 1 | Sierra | SI | AUBURN | PC | 0152241101 | HALSEY 1101 | O | Complete | Constraint_ITS_past | 2023-01-26 | 2023-12-01 | 2023-06-16 | -121 | 3. Non-timely worked |  |  | 38.977977690 | -121.050071500 | 2 | 586471 | RFT306141151 | Refusal | CLOSE | 2023-05-18 | duplicate NW, Refusal, TW on 7/6/23. Vendor completed late.
-1056254062 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | ZRC to 11 | SISI1202848 | NWK | 1 | Sierra | SI | GRASS VALLE | NE | 015269110B | HIGGINS 1109-B | O | Complete | Constraint_ITS_past | 2023-05-17 | 2023-07-24 | 2023-06-21 | -24 | 3. Non-timely worked |  |  | 39.101631650 | -121.093248840 | 2 | 570355 | RFT115133400 | Access | CLOSE | 2023-05-22 | Additional constraint was Released and Closed on 7/20/23, tree work completed on XNSI1008527, tree #3, SISI1202848 was closed as No Work on 7/24/23
-1056231129 | VMS | Distribution | M | Priority 2 (P2) | Willow | ZMAJOR R1 | SISI1204123 | NWK | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-05-30 | 2023-09-14 | 2023-08-04 | -30 | 3. Non-timely worked |  |  | 38.809461000 | -121.163788000 | 2 | 601966 | RPT531081411 | Riparian | CLOSE | 2023-05-31 | data entry cleanup, tree was no worked.
-1056345712 | VMS | Distribution | M | Priority 2 (P2) | Cottonwood, Fremont | ZR CLEAR | SISI1203618 | NWK | 1 | Sierra | SI | AUBURN | PC | 0152271102 | WISE 1102 | O | Complete | Constraint_ITS_past | 2023-04-24 | 2023-09-01 | 2023-08-18 | -11 | 3. Non-timely worked |  |  | 38.891297000 | -121.118576000 | 2 | 595332 | RPT424122836 | Riparian | CLOSE | 2023-04-26 | data entry cleanup, tree was no worked.
-1056106736 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | NWK | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804212800 | -121.157133280 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | data entry cleanup, tree was no worked.
-1056106753 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | NWK | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804321270 | -121.157116750 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | data entry cleanup, tree was no worked.
-1055977466 | VMS | Distribution | M | Priority 2 (P2) | Ponderosa Pine | ZMAJOR R3 | SISI1206426 | NWK | 1 | Sierra | SI | NEVADA CITY | NE | 015247110B | COLUMBIA HILL 1101-B | O | Complete | Constraint_ITS_past | 2023-11-16 | 2023-12-26 | 2023-12-22 | -3 | 3. Non-timely worked |  |  | 39.367754000 | -121.071056000 | 3 | 619552 | CLR122092307 | Clearance Request | CLOSE | 2023-11-22 | data entry cleanup, tree was no worked.
-1056044944 | VMS | Distribution | M | Priority 2 (P2) | Valley Oak | ZMAJOR R5 | SISI1205555 | NWK | 1 | Sierra | SI | PENRYN | PC | 0152561103 | PENRYN 1103 | O | Complete | Constraint_ITS_past | 2023-09-11 | 2024-05-15 | 2024-04-24 | -16 | 3. Non-timely worked |  |  | 38.857761000 | -121.174502000 |  | 615907 | ACC009091111 | Access Issue | CLOSE | 2024-03-27 | data entry cleanup, tree was no worked.
-1057864701 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZRC to 11 | SISI1200353 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152581104 | DELMAR 1104 | O | Complete | Constraint_ITS_past | 2023-01-17 | 2023-08-14 | 2023-08-11 | -2 | 3. Non-timely worked |  |  | 38.806527460 | -121.193516140 |  | 583232 | RFT215143817 | Refusal | CLOSE | 2023-04-12 | Additional constraint due to customer refusal.
-1056106706 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804172510 | -121.157130920 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106768 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804381180 | -121.157118440 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106793 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804430170 | -121.157129620 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106853 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804452150 | -121.157112280 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106880 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804458420 | -121.157098690 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106889 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804465580 | -121.157136720 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106896 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804473510 | -121.157133070 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106928 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804698000 | -121.157071410 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106941 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804518860 | -121.157094940 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106948 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804735330 | -121.157100880 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106961 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804895430 | -121.157065950 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056106974 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804853270 | -121.157054250 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056107011 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804928250 | -121.157073230 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056107037 | VMS | Distribution | M | Priority 2 (P2) | Redwood, Coast | ZRC to 11 | SISI1204541 | RD1 | 1 | Sierra | SI | LOOMIS | PC | 0152561104 | PENRYN 1104 | O | Complete | Constraint_ITS_past | 2023-07-24 | 2023-11-02 | 2023-09-01 | -45 | 3. Non-timely worked |  |  | 38.804888410 | -121.157039970 |  | 607636 | RFT724135609 | Refusal | CLOSE | 2023-08-04 | Additional constraint due to customer refusal.
-1056102217 | VMS | Distribution | M | Priority 2 (P2) | Locust, Black | ZRC 12+ | SISI1204567 | RD2 | 1 | Sierra | SI | FOREST | SI | 015210110C | ALLEGHANY 1101-C | O | Complete | Constraint_ITS_past | 2023-07-26 | 2024-04-18 | 2023-09-20 | -152 | 3. Non-timely worked |  |  | 39.489864000 | -120.852513000 | 3 | 607868 | QRT726131843 | Quarantine | CLOSE | 2023-08-22 | Additional constraint due to USFS permit approval.
-1056102218 | VMS | Distribution | M | Priority 2 (P2) | Locust, Black | ZRC 12+ | SISI1204567 | RD2 | 1 | Sierra | SI | FOREST | SI | 015210110C | ALLEGHANY 1101-C | O | Complete | Constraint_ITS_past | 2023-07-26 | 2024-04-18 | 2023-09-20 | -152 | 3. Non-timely worked |  |  | 39.489873000 | -120.852489000 | 3 | 607867 | QRT726131809 | Quarantine | CLOSE | 2023-08-22 | Additional constraint due to USFS permit approval.
-1056073750 | VMS | Distribution | M | Priority 2 (P2) | Black Walnut | ZRC 12+ | SISI1205109 | RD2 | 1 | Sierra | SI | Unincorpora | SI | 0152201102 | PIKE CITY 1102 | O | Complete | Constraint_ITS_past | 2023-08-21 | 2024-04-03 | 2023-09-20 | -141 | 3. Non-timely worked |  |  | 39.518939000 | -120.991254000 | 3 | 610576 | QRT821161734 | Quarantine | CLOSE | 2023-08-22 | Additional constraint due to USFS permit approval.
-1056073751 | VMS | Distribution | M | Priority 2 (P2) | Honey Locust | ZRC 12+ | SISI1205109 | RD2 | 1 | Sierra | SI |  | SI | 0152201102 | PIKE CITY 1102 | O | Complete | Constraint_ITS_past | 2023-08-21 | 2024-04-03 | 2023-09-20 | -141 | 3. Non-timely worked |  |  | 39.519326000 | -120.992028000 | 3 | 610574 | QRT821161608 | Quarantine | CLOSE | 2023-08-22 | Additional constraint due to USFS permit approval.
-1056034939 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZFELL R1 | SISI1205655 | MN1 | 1 | Sierra | SI | FORESTHILL | PC | 0152181102 | FORESTHILL 1102 | O | Complete | No Constraint | 2023-09-18 | 2023-12-15 | 2023-10-16 | -45 | 3. Non-timely worked |  |  | 39.020333550 | -120.844404710 | 3 | [5 empty] | Additional constraint due to customer refusal.
-1056034915 | VMS | Distribution | M | Priority 2 (P2) | Cedar | ZFELL R2 | SISI1205655 | MN2 | 1 | Sierra | SI | FORESTHILL | PC | 0152181102 | FORESTHILL 1102 | O | Complete | No Constraint | 2023-09-18 | 2023-12-15 | 2023-10-16 | -45 | 3. Non-timely worked |  |  | 39.020312490 | -120.844434780 | 3 | [5 empty] | Additional constraint due to customer refusal.
-1056253532 | VMS | Distribution | M | Priority 2 (P2) | Black Oak | ZPRUNE R3 | SISI1203181 | MN3 | 1 | Sierra | SI | MEADOW VIST | PC | 0152241101 | HALSEY 1101 | O | Complete | No Constraint | 2023-05-17 | 2023-08-14 | 2023-06-15 | -43 | 3. Non-timely worked |  |  | 39.001094910 | -121.053017880 | 2 | [5 empty] | Additional constraint due to customer and access issues.
-1056223741 | VMS | Distribution | M | Priority 2 (P2) | Ponderosa Pine | ZMAJOR R3 | SISI1203504 | NWK | 1 | Sierra | SI | NEVADA CITY | NE | 015248110M | BRUNSWICK 1105-M | O | Complete | No Constraint | 2023-06-05 | 2023-07-10 | 2023-07-05 | -4 | 3. Non-timely worked |  |  | 39.280624800 | -120.966160600 | 3 | [5 empty] | Additional constraint due to line clearance.
-1056167991 | VMS | Distribution | M | Priority 2 (P2) | Ponderosa Pine | ZMAJOR R1 | SISI1203798 | NWK | 1 | Sierra | SI | NEVADA CITY | NE | 0152481103 | BRUNSWICK 1103 | O | Complete | No Constraint | 2023-06-22 | 2024-07-24 | 2023-07-21 | -264 | 3. Non-timely worked |  |  | 39.278162350 | -120.995052460 | 3 | [5 empty] | Additional constraint due to customer refusal.
-1056167992 | VMS | Distribution | M | Priority 2 (P2) | Ponderosa Pine | ZMAJOR R1 | SISI1203798 | NWK | 1 | Sierra | SI | NEVADA CITY | NE | 0152481103 | BRUNSWICK 1103 | O | Complete | No Constraint | 2023-06-22 | 2024-07-24 | 2023-07-21 | -264 | 3. Non-timely worked |  |  | 39.278199000 | -120.994994070 | 3 | [5 empty] | Additional constraint due to customer refusal.
-1056167993 | VMS | Distribution | M | Priority 2 (P2) | Ponderosa Pine | ZMAJOR R1 | SISI1203798 | NWK | 1 | Sierra | SI | NEVADA CITY | NE | 0152481103 | BRUNSWICK 1103 | O | Complete | No Constraint | 2023-06-22 | 2024-07-24 | 2023-07-21 | -264 | 3. Non-timely worked |  |  | 39.278277380 | -120.995002960 | 3 | [5 empty] | Additional constraint due to customer refusal.
-1055969480 | VMS | Distribution | M | Priority 2 (P2) | Maple | ZRC 12+ | SISI1206580 | NWK | 1 | Sierra | SI | GRASS VALLE | NE | 0152481107 | BRUNSWICK 1107 | O | Complete | No Constraint | 2023-12-04 | 2024-08-12 | 2024-01-03 | -159 | 3. Non-timely worked |  |  | 39.210355170 | -121.057980790 | 2 | [5 empty] | data entry cleanup, tree was no worked.
-1056132869 | VMS | Distribution | M | Priority 2 (P2) | Ponderosa Pine | ZMAJOR R2 | SISI1204253 | RD1 | 1 | Sierra | SI | GRASS VALLE | NE | 015248110S | BRUNSWICK 1106-S | O | Complete | No Constraint | 2023-07-13 | 2023-08-11 | 2023-08-10 | -2 | 3. Non-timely worked |  |  | 39.146845110 | -121.041817340 | [6 empty] | P2 was completed on 20th business day. Entered in system day after. Data entry delay.
-1056254241 | VMS | Distribution | M | Priority 2 (P2) | Blue Oak | ZRC 12+ | SISI1202908 | RD2 | 1 | Sierra | SI | SOMERSET | ED | 0153662102 | APPLE HILL 2102-Seq 1 | O | Complete | No Constraint | 2023-05-16 | 2023-12-27 | 2023-06-14 | -141 | 3. Non-timely worked |  |  | 38.568614390 | -120.682102510 | 2 | [5 empty] | Data entry error. Tree Work Date was accidentally overridden during invoicing backlog catch-up to 12-27-23, vendor is unable to make changes.
-1056191122 | VMS | Distribution | M | Priority 2 (P2) | Maple | ZRC 12+ | SISI1203671 | RD2 | 1 | Sierra | SI | PENN VALLEY | NE | 015313210A | NARROWS 2101-A | O | Complete | No Constraint | 2023-06-13 | 2023-09-13 | 2023-07-13 | -45 | 3. Non-timely worked |  |  | 39.201967770 | -121.241822140 | 2 | [5 empty] | Additional constraint due to customer refusal.
-1056191123 | VMS | Distribution | M | Priority 2 (P2) | Maple | ZRC 12+ | SISI1203671 | RD2 | 1 | Sierra | SI | PENN VALLEY | NE | 015313210A | NARROWS 2101-A | O | Complete | No Constraint | 2023-06-13 | 2023-09-13 | 2023-07-13 | -45 | 3. Non-timely worked |  |  | 39.201524520 | -121.241494580 | 2 | [5 empty] | Additional constraint due to customer refusal.
-1056191124 | VMS | Distribution | M | Priority 2 (P2) | Sycamore | ZRC 12+ | SISI1203671 | RD2 | 1 | Sierra | SI | PENN VALLEY | NE | 015313210A | NARROWS 2101-A | O | Complete | No Constraint | 2023-06-13 | 2023-09-13 | 2023-07-13 | -45 | 3. Non-timely worked |  |  | 39.201604350 | -121.241244790 | 2 | [5 empty] | Additional constraint due to customer refusal.
-1056040157 | VMS | Distribution | M | Priority 2 (P2) | Live Oak | ZRC 12+ | SISI1205663 | RD2 | 1 | Sierra | SI | COLFAX | PC | 0152431102 | SHADY GLEN 1102 | O | Complete | No Constraint | 2023-09-14 | 2023-10-31 | 2023-10-12 | -14 | 3. Non-timely worked |  |  | 39.125045880 | -120.927354680 | 3 | [5 empty] | Additional constraint due to construction.
-1056222000 | VMS | Distribution | M | Priority 2 (P2) | Douglas Fir | ZMOV to 20 | SISI1203505 | UOA | 1 | Sierra | SI | GRASS VALLE | NE | 015248110S | BRUNSWICK 1106-S | O | Complete | No Constraint | 2023-06-05 | 2023-07-07 | 2023-07-05 | -3 | 3. Non-timely worked |  |  | 39.165637980 | -120.966053000 | 2 | [5 empty] | Additional constraint due to access issue.