## 2023-2024-2025
Project ID | Project Name | Energization | Total Circuit Segment Miles | Total Constructed Miles | Total Miles Undergrounded | Overhead Removed | Covered Conductor Installed | Other Mitigations | Justification for Alternate Mitigation | Other Mitigations Miles | Total Un-Mitigated Circuit-Miles on Circuit Segment | Subprojects | Underground Subprojects | Covered Conductor Subprojects | Secondary Lines | Service Lines
ESH C1030 4 SUG-1 | CIR 1030 4 South Kiavo (1.73mi) - Services Only - COMPLETE | 2023-01-20 | 1.73 | 1.73 | 1.73 | 9.44 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C1030 4 SUG | CIR 1030 4 South Kiavo (8.42mi) | 2023-01-20 | 8.42 | 8.42 | 8.42 | 9.44 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0SL1 A SUG-1 | CIR SL1 A - Wings Oak Height (0.39mi) - Servcies Only - COMPLETE | 2023-01-27 | 0.39 | 0.39 | 0.39 | 0.35 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0075 DUG 2 SUG-1 | CIR 75 DUG 2 Lyons Valley Rd (0.01mi) - Services Only - COMPLETE | 2023-02-15 | 0.01 | 0.01 | 0.01 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0972 DUG A SUG-1 | CIR 972 DUG A - Ashley Rd (1.72mi) - Services Only - COMPLETE | 2023-02-15 | 1.72 | 1.72 | 1.72 | 2.27 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0972 DUG B SUG-1 | CIR 972 DUG B - Ashley Rd (1.23mi) - Services Only - COMPLETE | 2023-03-02 | 1.23 | 1.23 | 1.23 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0441 DUG B SUG | CIR 441 SUG Getaway (0.2mi) | 2023-07-14 | 0.2 | 0.2 | 0.2 | 4.72 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0221 A SUG-1 | CIR 221 A - Wings Manzanita (0.94mi) - Services Only - COMPLETE | 2023-07-19 | 0.94 | 0.94 | 0.94 | 0.4 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0221 A SUG | CIR 221 A - Wings Manzanita (1.62mi) | 2023-07-19 | 1.62 | 1.62 | 1.62 | 0.4 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0221 D SUG | CIR 221 D (0.30mi) | 2023-09-20 | 0.3 | 0.3 | 0.3 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0221 DUG 3 SUG | CIR 221 DUG 3 - Mainline (6.07mi) - CNF - COMPLETE | 2023-09-21 | 6.07 | 6.07 | 6.07 | 0.02 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 A SUG | CIR 222 A (0.14mi) | 2023-09-21 | 0.14 | 0.14 | 0.14 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0OK1 B SUG | CIR OK1 B - Wings (6.02mi) | 2023-10-11 | 6.02 | 6.02 | 6.02 | 4.97 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 X SUG | CIR 222 X (2.87mi) | 2023-10-12 | 2.87 | 2.87 | 2.87 | 0.99 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0OK1 A SUG | CIR OK1 A - Wings (8.44mi) | 2023-10-25 | 8.44 | 8.44 | 8.44 | 2.94 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0221 B2 SUG | CIR 221 B2 - Wings (1.19mi) | 2023-11-06 | 1.19 | 1.19 | 1.19 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0445 C SUG | CIR 445 C (2.07mi) | 2023-11-30 | 2.07 | 2.07 | 2.07 | 1.57 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 B SUG | CIR 445 B (2.63mi) | 2023-12-01 | 2.63 | 2.63 | 2.63 | 1.47 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0073 A SUG | CIR 73 A (2.66mi) | 2023-12-07 | 2.66 | 2.66 | 2.66 | 0.71 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 DD SUG | CIR 222 DD (2.42mi) | 2023-12-12 | 2.47 | 2.47 | 2.47 | 1.11 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 EE SUG | CIR 222 EE (2.94mi) | 2023-12-13 | 2.94 | 2.94 | 2.94 | 1.795 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 E SUG | CIR 222 E (2.68mi) | 2023-12-20 | 2.95 | 2.95 | 2.95 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 V SUG | CIR 222 V (1.04mi) | 2023-12-21 | 1.04 | 1.04 | 1.04 | 1.01 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 C SUG | CIR 222 C (3.54mi) | 2023-12-22 | 3.56 | 3.56 | 3.56 | 1.71 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 A SUG | CIR 445 A (1.52mi) | 2023-12-22 | 1.52 | 1.52 | 1.52 | 0.9 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 O SUG | CIR 445 O - 2023 (0.97mi) | 2023-12-22 | 0.97 | 0.97 | 0.97 | 0.9 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0358 DUG 2 SUG | CIR 358 DUG 2 - CalTrans Crossing & Willows Rd (2.32mi) | 2023-12-27 | 2.32 | 2.32 | 2.32 | 1.03 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0222 BB SUG | CIR 222 BB - Mainline (1.14mi) | 2023-12-29 | 1.14 | 1.14 | 1.14 | 1.31 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 H SUG | CIR 222 H - 2023 (2.78mi) | 2023-12-29 | 2.78 | 2.78 | 2.78 | 0.649 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 L SUG | CIR 222 L (1.59mi) | 2023-12-29 | 1.59 | 1.59 | 1.59 | 1.204 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 N SUG | CIR 222 N - 2023 (0.75mi) | 2023-12-29 | 0.75 | 0.75 | 0.75 | 0.64 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 W SUG | CIR 222 W - Mainline (3.05mi) | 2023-12-29 | 3.05 | 3.05 | 3.05 | 1.886 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 F SUG | CIR 445 F - 2023 (1.38mi) | 2023-12-29 | 1.38 | 1.38 | 1.38 | 3.14 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0972 C SUG | CIR 972 C - 2023 (6.08mi) | 2023-12-29 | 6.08 | 6.08 | 6.08 | 2.31 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 BB SUG-1 | CIR 222 BB - Services (0.19mi) | 2024-01-02 | 0.19 | 0.19 | 0.19 | 1.31 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 W SUG-1 | CIR 222 W - Services (0.24mi) | 2024-01-11 | 0.24 | 0.24 | 0.24 | 1.886 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 CC SUG | CIR 222 CC (2.04mi) | 2024-01-19 | 2.04 | 2.04 | 2.04 | 0.7 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 N SUG-1 | CIR 222 N - 2024 (0.60mi) | 2024-01-19 | 0.6 | 0.6 | 0.6 | 0.64 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C1458 1B SUG | CIR 1458 1B - Quick Win W. Victoria Rd (0.53mi) | 2024-02-09 | 0.53 | 0.53 | 0.53 | 0.17 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 O SUG-1 | CIR 445 O - 2024 (0.44mi) | 2024-02-29 | 0.44 | 0.44 | 0.44 | 0.9 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 H SUG-1 | CIR 222 H - 2024 (0.66mi) | 2024-07-11 | 3.2 | 3.2 | 3.2 | 0.649 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 Z SUG | CIR 222 Z (4.79mi) | 2024-07-17 | 4.79 | 4.79 | 4.79 | 2.41 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 F SUG-1 | CIR 445 F - 2024 (6.08mi) | 2024-07-31 | 6.2 | 6.2 | 6.2 | 3.14 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 I SUG | CIR 0222 I (1.21mi) | 2024-08-16 | 1.25 | 1.25 | 1.25 | 1.053 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 K2 SUG | CIR 0220 K2 (0.26mi) | 2024-08-22 | 3.08 | 3.08 | 3.08 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0222 Y SUG | CIR 0222 Y (3.84mi) | 2024-09-04 | 3.84 | 3.84 | 3.84 | 2.46 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0972 C SUG-1 | CIR 972 C - 2024 (0.67mi) | 2024-09-06 | 0.67 | 0.67 | 0.67 | 2.31 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 L SUG | CIR 0220 L (2.43mi) | 2024-09-10 | 2.43 | 2.43 | 2.43 | 1.3 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0221 DUG 3 SUG-1 | CIR 221 DUG 3 - Services (0.04mi) - CNF | 2024-09-10 | 0.04 | 0.04 | 0.04 | 0.02 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 A2 SUG | CIR 0445 A2 (0.84mi) | 2024-09-11 | 0.84 | 0.84 | 0.84 | 1.86 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0073 G SUG | CIR 0073 G (1.86mi) | 2024-09-12 | 1.74 | 1.74 | 1.74 | 1.12 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 F SUG | CIR 0222 F (2.69) | 2024-09-19 | 2.24 | 2.24 | 2.24 | 1.2 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 J SUG | CIR 0220 J (3.39mi) | 2024-09-25 | 3.24 | 3.24 | 3.24 | 2.26 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 D SUG | CIR 0445 D (3.88mi) | 2024-09-27 | 5.79 | 5.79 | 5.79 | 4.64 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 Q SUG | CIR 0220 Q (1.16mi) | 2024-10-01 | 1.38 | 1.38 | 1.38 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0222 U SUG | CIR 0222 U (3.71mi) | 2024-10-01 | 3.71 | 3.71 | 3.71 | 3.04 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 B SUG | CIR 0220 B - (3.47mi) | 2024-10-07 | 4.22 | 4.22 | 4.22 | 0.23 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0073 C SUG | CIR 0073 C (4.04mi) | 2024-10-09 | 4.04 | 4.04 | 4.04 | 2.02 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 G SUG | CIR 0222 G (4.85mi) | 2024-10-10 | 4.85 | 4.85 | 4.85 | 3.2 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0073 E SUG | CIR 0073 E (2.49mi) | 2024-10-14 | 3.81 | 3.81 | 3.81 | 2.08 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 N SUG | CIR 0445 N (1.89mi) | 2024-10-24 | 1.89 | 1.89 | 1.89 | 1.73 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0972 C3 SUG | CIR 972 C3 (0.11mi) | 2024-10-28 | 0.11 | 0.11 | 0.11 | 0 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 D SUG | CIR 0222 D (3.23mi) | 2024-10-31 | 3.4 | 3.4 | 3.4 | 6.3 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0909 A SUG | CIR 0909 A (2.53mi) | 2024-11-01 | 2.55 | 2.55 | 2.55 | 0 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0445 F2 SUG | CIR 0445 F2 (0.30mi) | 2024-11-08 | 0.3 | 0.3 | 0.3 | 0.3 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0972 D SUG | CIR 0972 D - (0.47mi) | 2024-11-08 | 0.47 | 0.47 | 0.47 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | No
ESH C0SL1 C SUG | CIR CSL1 C - Wings (5.74mi) | 2024-12-03 | 5.74 | 5.74 | 5.74 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0SL1 B SUG | CIR CSL1 B - Wings (7.45mi) | 2024-12-10 | 7.45 | 7.45 | 7.45 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 B SUG | CIR 0222 B (3.80mi) | 2025-01-02 | 4.69 | 4.69 | 4.69 | 4.08 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 J2 SUG | CIR 0220 J2 (3.39mi) | 2025-01-09 | 0.15 | 0.15 | 0.15 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 U SUG | CIR 0220 U (2.68mi) | 2025-01-14 | 2.68 | 2.68 | 2.68 | 2.3 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 GG SUG | CIR 0222 GG (0.02mi) | 2025-01-31 | 0.02 | 0.02 | 0.02 | 0.02 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0210 N SUG | CIR 0210 N (3.60mi) | 2025-02-18 | 3.6 | 3.6 | 3.6 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 G SUG | CIR 0445 G (4.12mi) | 2025-02-18 | 4.12 | 4.12 | 4.12 | 3.51 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0210 G SUG | CIR 0210 G (2.70mi) | 2025-02-20 | 2.7 | 2.7 | 2.7 | N/A | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 E2 SUG | CIR 0222 E2 (0.25mi) | 2025-02-24 | 0.25 | 0.25 | 0.25 | 0 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 K SUG | CIR 0222 K (3.18mi) | 2025-02-24 | 3.24 | 3.24 | 3.24 | 2.78 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0073 D SUG | CIR 0073 D (6.13mi) | 2025-03-04 | 6.13 | 6.13 | 6.13 | 2.78 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 M SUG | CIR 0220 M (2.16mi) | 2025-03-04 | 2.19 | 2.19 | 2.19 | 0.59 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 J SUG | CIR 0222 J (2.11mi) | 2025-03-06 | 2 | 2 | 2 | 1.4 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0217 A SUG | CIR 0217 A (3.30mi) | 2025-03-07 | 3.3 | 3.3 | 3.3 | 0 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0972 E2 SUG | CIR 0972 E2 - (1.23mi) | 2025-03-10 | 1.23 | 1.23 | 1.23 | 0.036 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 B2 SUG | CIR 0220 B2 (0.75mi) | 2025-03-19 | 0.75 | 0.75 | 0.75 | 0.6 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 Q SUG | CIR 0222 Q (1.68mi) | 2025-03-19 | 1.68 | 1.68 | 1.68 | 2.25 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 T SUG | CIR 0222 T (1.73mi) | 2025-03-19 | 1.73 | 1.73 | 1.73 | 2.26 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 FF SUG | CIR 0222 FF (4.18mi) | 2025-04-15 | 4.31 | 4.31 | 4.31 | 2.68 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 N SUG | CIR 0220 N (3.50mi) | 2025-04-17 | 3.5 | 3.5 | 3.5 | 1.12 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0217 B SUG | CIR 0217 B (3.70mi) | 2025-04-29 | 3.7 | 3.7 | 3.7 | 4.02 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0221 C SUG | CIR 0221 C - Wings (7.78mi) | 2025-04-29 | 7.78 | 7.78 | 7.78 | 8.568 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0210 C SUG | CIR 0210 C (0.50mi) | 2025-05-05 | 0.43 | 0.43 | 0.43 | 0.19 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0210 F SUG | CIR 0210 F (3.20mi) | 2025-05-12 | 3.2 | 3.2 | 3.2 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 S SUG | CIR 0220 S (4.20mi) | 2025-05-14 | 1.5 | 1.5 | 1.5 | 2.81 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0314 A SUG | CIR 0314 A RFS Only (0.00mi) | 2025-05-19 | 0 | 0 | 0 | 0.49 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0442 B SUG | CIR 0442 B (3.45mi) | 2025-05-19 | 3.45 | 3.45 | 3.45 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0442 A SUG | CIR 0442 A (3.25mi) | 2025-05-21 | 3.25 | 3.25 | 3.25 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0221 E SUG | CIR 0221 E (0.50mi) | 2025-05-30 | 0.5 | 0.5 | 0.5 | 0.95 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 W SUG | CIR 0220 W (2.04mi) | 2025-06-03 | 2.04 | 2.04 | 2.04 | 15.4 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 S2 SUG | CIR 0220 S2 (4.20mi) | 2025-06-05 | 2.2 | 2.2 | 2.2 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C1030 1B SUG | CIR 1030 1B (3.47mi) - BIA | 2025-06-10 | 3.47 | 3.47 | 3.47 | 3.51 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0442 DUG SUG | CIR 0442 DUG (6.2mi) - CNF | 2025-06-12 | 8.47 | 8.47 | 8.47 | 1.3 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C1215 D SUG | CIR 1215 D (1.40mi) | 2025-06-16 | 1.4 | 1.4 | 1.4 | 1.4 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0212 A SUG | CIR 0212 A (0.30mi) | 2025-06-23 | 0.3 | 0.3 | 0.3 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0221 B SUG | CIR 0221 B - Wings (5.00mi) | 2025-06-24 | 5.95 | 5.95 | 5.95 | 2 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0441 DUG A SUG | CIR 0441 DUG A (6.12mi) - CNF | 2025-07-09 | 6.32 | 6.32 | 6.32 | 4.4 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 H SUG | CIR 0211 H (1.70mi) | 2025-07-29 | 1.7 | 1.7 | 1.7 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 G SUG | CIR 0211 G (2.10mi) | 2025-07-30 | 2.1 | 2.1 | 2.1 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0078 C SUG | CIR 0078 C (0.40mi) | 2025-07-31 | 0.4 | 0.4 | 0.4 | 0 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0210 E SUG | CIR 0210 E (3.20mi) | 2025-08-05 | 3.2 | 3.2 | 3.2 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 E SUG | CIR 0211 E (4.30mi) | 2025-08-05 | 4.3 | 4.3 | 4.3 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0212 F SUG | CIR 0212 F (0.40mi) | 2025-08-05 | 0.4 | 0.4 | 0.4 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0078 B SUG | CIR 0078 B (0.40mi) | 2025-08-07 | 0.4 | 0.4 | 0.4 | 0.45 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0078 D SUG | CIR 0078 D (0.30mi) | 2025-08-13 | 0.3 | 0.3 | 0.3 | 0.79 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0078 A SUG | CIR 0078 A (0.50mi) | 2025-08-20 | 0.5 | 0.5 | 0.5 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 D SUG | CIR 0211 D (4.40mi) | 2025-08-20 | 4.4 | 4.4 | 4.4 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 B SUG | CIR 0211 B (4.40mi) | 2025-08-21 | 4.4 | 4.4 | 4.4 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 I SUG | CIR 0211 I (2.80mi) | 2025-08-21 | 2.8 | 2.8 | 2.8 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 A SUG | CIR 0211 A (5.00mi) | 2025-08-25 | 5 | 5 | 5 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0212 D SUG | CIR 0212 D (1.80mi) | 2025-08-25 | 1.8 | 1.8 | 1.8 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C1215 C SUG | CIR 1215 C (0.50mi) | 2025-08-25 | 0.5 | 0.5 | 0.5 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 J SUG | CIR 0211 J (2.10mi) | 2025-08-26 | 2.1 | 2.1 | 2.1 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0075 A SUG | CIR 0075 A (0.2mi) | 2025-08-29 | 0.2 | 0.2 | 0.2 | 5.2 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0210 B SUG | CIR 0210 B (1.60mi) | 2025-09-24 | 1.6 | 1.6 | 1.6 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0441 E SUG | CIR 0441 E (0.77mi) | 2025-09-30 | 0.77 | 0.77 | 0.77 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0211 F SUG | CIR 0211 F (2.30mi) | 2025-10-23 | 2.3 | 2.3 | 2.3 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0909 B SUG | CIR 0909 B (0.55mi) - BIA | 2025-10-30 | 2.46 | 2.46 | 2.46 | 2.94 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 Q SUG | CIR 0971 Q (0.50mi) | 2025-11-03 | 0.5 | 0.5 | 0.5 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0212 B SUG | CIR 0212 B (2.70mi) | 2025-11-05 | 2.7 | 2.7 | 2.7 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0358 C SUG | CIR 0358 C (1.20mi) | 2025-11-05 | 1.2 | 1.2 | 1.2 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 D SUG | CIR 0971 D (1.40mi) | 2025-11-11 | 1.4 | 1.4 | 1.4 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 M SUG | CIR 0971 M (1.30mi) | 2025-11-12 | 1.3 | 1.3 | 1.3 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 C SUG | CIR 0971 C (1.60mi) | 2025-11-17 | 1.6 | 1.6 | 1.6 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0222 AA SUG | CIR 0222 AA (4.35mi) | 2025-11-18 | 4.35 | 4.35 | 4.35 | 2.53 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 E SUG | CIR 0971 E (1.40mi) | 2025-11-18 | 1.4 | 1.4 | 1.4 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 R SUG | CIR 0971 R (1.30mi) | 2025-11-18 | 1.3 | 1.3 | 1.3 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0231 A SUG | CIR 0231 A (1.01mi) | 2025-11-19 | 1.01 | 1.01 | 1.01 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 U SUG | CIR 0971 U (1.00mi) | 2025-11-24 | 1 | 1 | 1 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 K SUG | CIR 0220 K (0.77mi) - BIA | 2025-12-02 | 1.03 | 1.03 | 1.03 | 0.75 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 A2 SUG | CIR 0971 A2 (0.00mi) - Substation | 2025-12-04 | 0 | 0 | 0 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0445 P SUG | CIR 0445 P (1.35mi) - BIA | 2025-12-08 | 1.23 | 1.23 | 1.23 | 1.33 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0358 B SUG | CIR 0358 B (1.90mi) | 2025-12-09 | 1.9 | 1.9 | 1.9 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0971 B SUG | CIR 0971 B (1.60mi) | 2025-12-17 | 1.6 | 1.6 | 1.6 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0210 D SUG | CIR 0210 D (2.20mi) | 2025-12-18 | 2.2 | 2.2 | 2.2 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0524 C SUG | CIR 0524 C (1.53mi) | 2025-12-18 | 1.53 | 1.53 | 1.53 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0220 P SUG | CIR 0220 P (1.33mi) - BIA | 2025-12-19 | 2.38 | 2.38 | 2.38 | 1.97 | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
ESH C0524 B SUG | CIR 0524 B (2.45mi) | 2025-12-22 | 2.45 | 2.45 | 2.45 | TBD | No | No | N/A | No | No | N/A | N/A | N/A | Yes | Yes
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Projects with Blank or N/A provide mitigation resulting in removal of OH facilities when combined with another projects, and the removal is accounted for on the other project. Projects with TBD indicate that design has not advanced to the point where the exact location and total mileage of removal is determined.