## Primary
[7 empty] | See Note (A) below for select definitions of "Justifications for Alternative Mitigation" |  | See notes in Data Response |  |  |  |  | See Notes in Data Response | See Notes in Data Response
Primary CPZ | Total Circuit Segment Miles | Total Constructed Miles | Total Miles Undergrounded | Overhead Removed | Covered Conductor or Installed | Other Mitigations | Justification for Alternate Mitigation | Other Mitigations Miles | Total Un-Mitigated Circuit-Miles on Circuit Segment | Subprojects | Underground Subprojects | Covered Conductor Subprojects | Other Mitigation Subprojects | Secondary Lines | Service Lines | EPSS
KESWICK 11011586 | 7.4325 | 8.8322 | 5.5123 | 6.9447 | 3.2864 |  | Cost Effective alternative to UG - Hybrid | 0.033523 |  | 6 | 3 | 4 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
POTTER VALLEY P H 110576498 | 14.8417 | 0.94148 | 0.37178 | 0.94167 | 0.5697 |  | Cost effective alternative to UG – Hybrid, Other - Wires Down | 0 |  | 2 | 1 | 1 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
STANISLAUS 17021804 | 8.3786 | 1.785 | 0.053977 | 1.9341 | 1.6826 | Removal | Cost effective alternative to UG – Hybrid , Portion of [Total Constructed Miles] is pure Removal | 0.048485 |  | 1 | 1 | 1 | 1 | No | No | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SILVERADO 210478268 | 11.4487 | 17.2885 | 17.047 |  | 0.24148 |  | UG Infeasible, Cost effective alternative to UG – Hybrid | 0 |  | 10 | 9 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VACAVILLE 11046542 | 14.4352 | 17.6184 | 6.6049 |  | 9.9498 | Removal | Cost effective alternative to UG – Hybrid | 1.0636 |  | 13 | 6 | 10 | 4 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
EL DORADO PH 210119752 | 38.3799 | 41.5536 | 7.7146 |  | 33.839 |  | Cost effective alternative to UG – Hybrid | 0 |  | 20 | 5 | 20 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MOUNTAIN QUARRIES 2101CB | 24.6691 | 25.375 | 2.9714 |  | 22.4036 |  | Cost effective alternative to UG – Hybrid | 0 |  | 21 | 5 | 18 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VOLTA 1101CB | 8.2129 | 10.9547 | 2.7663 | 12.5494 | 7.7985 |  | Cost effective alternative to UG – Hybrid | 0.38996 |  | 14 | 6 | 11 | 2 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SHINGLE SPRINGS 210935598 | 11.3577 | 13.4282 | 5.0311 |  | 8.3972 |  | Cost effective alternative to UG – Hybrid | 0 |  | 5 | 1 | 5 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
AUBERRY 1101R2578 | 44.5246 | 45.5525 | 1.0919 |  | 44.439 | Removal | Cost Effective alternative to UG - Hybrid | 0.021591 |  | 22 | 4 | 20 | 1 | Yes |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WILDWOOD 11011454 | 7.7772 | 7.7314 | 0.19792 | 7.9098 | 7.5335 |  | Cost effective alternative to UG – Hybrid | 0 |  | 5 | 1 | 4 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WOODSIDE 11018974 | 13.104 | 2.6419 | 1.6436 |  | 0.9983 |  | Cost effective alternative to UG – Hybrid, Other - Wires Down | 0 |  | 3 | 2 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
HIGHLANDS 1102628 | 14.7136 | 21.065 | 6.3525 |  | 13.3208 | Removal-Remote Grid LEIP | Cost effective alternative to UG – Remote Grid/Removal | 1.3917 |  | 13 | 3 | 9 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MIDDLETOWN 1101548 | 28.3423 | 32.3659 | 18.5866 |  | 12.7399 | Removal-Remote Grid | Cost effective alternative to UG – Remote Grid/Removal | 1.0394 |  | 35 | 16 | 20 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
AUBERRY 1101CB | 17.8966 | 17.3216 | 0.14148 |  | 17.1231 | Removal | Portion of [Total Constructed Miles] is pure Removal, Cost effective alternative to UG – Hybrid | 0.057008 |  | 8 | 1 | 8 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MIDDLETOWN 110148212 | 10.6295 | 13.76 | 4.2845 |  | 9.4756 |  | Cost effective alternative to UG – Hybrid | 0 |  | 14 | 3 | 12 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLAYTON 221296224 | 7.6836 | 8.5939 | 2.5614 |  | 5.7826 | Removal | GRC Decision required Hybrid Consideration | 0.25 |  | 5 | 3 | 3 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PINE GROVE 11021222 | 17.0491 | 11.4673 | 0.098106 | 14.7737 | 11.3692 |  | Cost effective alternative to UG – Hybrid | 0 |  | 8 | 1 | 8 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
EL DORADO PH 2101CB | 7.2823 | 14.3712 | 6.2 |  | 8.1712 |  | Cost Effective alternative to UG - Hybrid | 0 |  | 10 | 4 | 6 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BANGOR 1101CB | 21.0291 | 1.6758 | 1.3922 | 1.1911 | 0.28352 |  | UG Infeasible | 0 |  | 1 | 1 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
KANAKA 1101CB | 40.8159 | 13.415 | 5.1208 |  | 8.185 | Removal | Other - FRRB | 0.10909 |  | 30 | 7 | 22 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
STANISLAUS 1701CB | 36.4691 | 37.2648 | 5.2758 |  | 31.9491 | Removal | UG Infeasible | 0.039962 |  | 21 | 6 | 18 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLAYTON 2215184604 | 10.2363 | 1.9153 | 1.875 | 1.7898 | 0.040341 |  | UG Infeasible | 0 |  | 1 | 1 | 1 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SILVERADO 2105658898 | 16.8969 | 18.4988 | 13.33 |  | 5.1688 |  | GRC Decision required Hybrid Consideration | 0 |  | 12 | 8 | 4 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
STANISLAUS 1702CB | 8.0185 | 10.0165 | 5.8235 |  | 3.5843 | Removal-Remote Grid LEIP | UG Infeasible | 0.60871 |  | 6 | 3 | 5 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MARIPOSA 210135244 | 16.3928 | 19.5472 | 5.6633 |  | 12.9241 | Removal-Remote Grid | Cost effective alternative to UG – Hybrid | 0.95985 |  | 8 | 2 | 5 | 2 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
UPPER LAKE 11011276 | 12.7022 | 15.0216 | 6.6555 |  | 8.3661 |  | Cost effective alternative to UG – Hybrid | 0 |  | 14 | 6 | 12 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG BEND 11021972 | 20.6351 | 22.153 | 22.1436 |  | 0.0094697 |  | All UG | 0 |  | 20 | 20 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MARTELL 1101CB | 13.1286 | 1.5177 | 1.3877 |  | 0.13 |  | Cost effective alternative to UG – Hybrid | 0 |  | 4 | 2 | 1 | 0 | Yes |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG MEADOWS 21012248 | 9.2087 | 13.1803 | 12.5455 |  | 0.54015 | Removal | Other - FRRB, UG Infeasible, Portion of [Total Constructed Miles] is pure Removal | 0.094697 |  | 10 | 6 | 2 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
DESCHUTES 11041370 | 21.76 | 11.7924 | 0.30227 | 12.9652 | 11.2746 | Removal | Cost effective alternative to UG – Hybrid | 0.21553 |  | 6 | 2 | 4 | 2 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG MEADOWS 21012260 | 21.673 | 6.5017 | 5.2945 |  | 0.53788 | Removal | Other - FRRB, Portion of [Total Constructed Miles] is pure Removal | 0.66932 |  | 22 | 12 | 2 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MIDDLETOWN 1102302610 | 5.425 | 5.4138 | 2.1521 |  | 3.2617 |  | Cost effective alternative to UG – Hybrid | 0 |  | 7 | 3 | 7 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MIDDLETOWN 1103830 | 38.0893 | 21.782 | 10.9286 | 20.6979 | 10.8534 |  | Cost effective alternative to UG – Hybrid | 0 |  | 19 | 8 | 11 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
TIDEWATER 210614072 | 3.6351 | 4.0472 | 2.8125 |  | 1.2347 |  | Cost effective alternative to UG – Hybrid | 0 |  | 3 | 2 | 2 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
GRAYS FLAT 0401CB | 10.5908 | 3.2108 | 1.4616 |  | 1.7492 |  | Cost Effective alternative to UG - Hybrid | 0 |  | 2 | 1 | 1 | 0 | No | No | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
KIRKER 2104442850 | 5.6919 | 5.1621 | 1.7894 |  | 3.3727 |  | Cost effective alternative to UG – Hybrid | 0 |  | 2 | 1 | 2 | 0 | Yes |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VOLTA 11011596 | 21.1057 | 4.2648 | 0.74186 | 5.5352 | 3.4009 | Removal | Cost effective alternative to UG – Hybrid | 0.12197 |  | 6 | 2 | 6 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BUCKS CREEK 1102CB | 29.4282 | 34.0089 | 31.1324 |  | 2.8765 |  | GRC Decision required Hybrid Consideration, Other - FRRB | 0 |  | 18 | 16 | 3 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
OREGON TRAIL 110335002 | 56.7319 | 66.5998 | 22.6996 |  | 43.9002 |  | Cost effective alternative to UG – Hybrid | 0 |  | 41 | 10 | 35 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MARIPOSA 2102440236 | 4.2347 | 4.7945 | 0.17614 | 5.3879 | 4.6184 |  | Cost effective alternative to UG – Hybrid | 0 |  | 4 | 2 | 4 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
HALF MOON BAY 11036012 | 9.5597 | 1.7587 | 1.7208 |  | 0.037879 |  | Other - FRRB | 0 |  | 2 | 2 | 1 | 0 | Yes |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
FROGTOWN 1702CB | 4.6818 | 0.4947 | 0.4947 | 2.5184 | 0 |  | Cost effective alternative to UG – Hybrid | 0 |  | 1 | 1 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VOLTA 110153118 | 8.5995 | 9.4688 | 0.77121 | 9.8049 | 8.6975 |  | Cost effective alternative to UG – Hybrid | 0 |  | 8 | 2 | 8 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
GANSNER 11012424 | 18.3753 | 3.9807 | 3.8784 | 0.55663 | 0.10227 |  | UG Infeasible | 0 |  | 2 | 2 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
HALF MOON BAY 110369412 | 21.0648 | 5.2678 | 5.2678 | 5.6864 | 0 |  | All UG | 0 |  | 2 | 2 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CRESCENT MILLS 21012056 | 6.4599 | 2.054 | 0.82008 |  | 1.2339 |  | Other - FRRB | 0 |  | 6 | 1 | 2 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
HARTLEY 1101698 | 10.612 | 8.4362 | 0.29773 |  | 8.1384 |  | Cost effective alternative to UG – Hybrid | 0 |  | 6 | 1 | 5 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
POTTER VALLEY P H 110537476 | 8.7707 | 1.2873 | 0.63125 |  | 0.65606 |  | Cost effective alternative to UG – Hybrid | 0 |  | 3 | 1 | 3 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
DUNBAR 1101CB | 17.0365 | 2.4557 | 2.4557 |  | 0 |  | All UG | 0 |  | 3 | 3 | 0 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
POTTER VALLEY P H 11051904 | 39.7518 | 31.8642 | 3.1239 |  | 28.7403 |  | Cost effective alternative to UG – Hybrid | 0 |  | 29 | 5 | 24 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MOUNTAIN QUARRIES 21011350 | 21.6832 | 22.9239 | 4.1892 |  | 18.7347 |  | Cost effective alternative to UG – Hybrid | 0 |  | 22 | 6 | 18 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PLACERVILLE 21067522 | 67.2991 | 2.2197 | 1.5197 |  | 0 | Removal | All UG | 0.7 |  | 4 | 3 | 0 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SPANISH CREEK 4401CB | 7.7587 | 5.9625 | 3.2328 |  | 0 |  | Other - FRRB | 2.7297 |  | 3 | 2 | 0 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WYANDOTTE 11031974 | 19.2335 | 20.9256 | 20.9256 |  | 0 |  | All UG, Other - FRRB | 0 |  | 40 | 40 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WILLOW CREEK 11032936 | 32.6023 | 9.6314 | 9.5453 |  | 0.086174 |  | UG Infeasible, Other - FRRB | 0 |  | 11 | 8 | 1 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BUCKS CREEK 1101CB | 4.7732 | 3.958 | 3.9034 |  | 0.054545 |  | Other - FRRB | 0 |  | 5 | 3 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG MEADOWS 21012476 | 8.5645 | 1.4964 | 1.3364 |  | 0.16004 |  | Other - FRRB, All UG - based on 3 PMs in the RAW Output tab | 0 |  | 3 | 2 | 1 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG MEADOWS 21012586 | 10.9901 | 0.46155 | 0.11932 |  | 0.34223 |  | Other - FRRB | 0 |  | 3 | 1 | 1 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SHADY GLEN 11012768 | 8.0771 | 8.5078 | 5.3364 |  | 2.6415 | Removal | Portion of [Total Constructed Miles] is pure Removal, Cost effective alternative to UG – Hybrid | 0.52992 |  | 10 | 7 | 4 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WYANDOTTE 11031976 | 13.1675 | 25.8545 | 25.6705 |  | 0.1178 | Removal | Other - FRRB | 0.066288 |  | 30 | 24 | 1 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
DUNBAR 1101416 | 3.167 | 1.3411 | 1.3411 |  | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SHADY GLEN 110132726 | 12.2854 | 14.9176 | 11.8945 |  | 2.9491 | Removal | GRC Decision required Hybrid Consideration, Other - FRRB | 0.074053 |  | 12 | 11 | 5 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SHADY GLEN 110248894 | 11.4113 | 12.9877 | 10.9966 |  | 1.8891 | Removal | Portion of [Total Constructed Miles] is pure Removal, GRC Decision required Hybrid Consideration, Other - FRRB | 0.10208 |  | 12 | 10 | 3 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BUCKS CREEK 1103CB | 2.1773 | 2.0424 | 0.59848 |  | 1.4439 |  | Other - FRRB | 0 |  | 2 | 1 | 2 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ANDERSON 11031600 | 10.7217 | 3.8811 | 0.80095 |  | 2.9801 | Removal | Cost effective alternative to UG – Hybrid | 0.1 |  | 5 | 2 | 3 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLARK ROAD 1102CB | 1.5131 | 1.2869 | 1.2869 | 1.0555 | 0 |  | All UG | 0 |  | 2 | 2 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLARK ROAD 110281296 | 15.6018 | 8.1547 | 8.1311 | 7.6258 | 0 | Removal | Portion of [Total Constructed Miles] is pure Removal, All UG | 0.023674 |  | 4 | 4 | 0 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLARK ROAD 11022094 | 3.3703 | 4.2208 | 4.2208 | 2.1021 | 0 |  | All UG | 0 |  | 3 | 3 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLARK ROAD 11022070 | 9.2742 | 6.2737 | 5.4782 |  | 0 | Removal-Remote Grid LEIP | Cost effective alternative to UG – Remote Grid/Removal | 0.79545 |  | 4 | 3 | 0 | 1 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLARK ROAD 110247006 | 4.4768 | 5.7553 | 5.7553 | 5.2892 | 0 |  | All UG | 0 |  | 2 | 2 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ANDERSON 1103226050 | 14.9792 | 2.935 | 2.935 | 2.5879 | 0 |  | All UG | 0 |  | 2 | 2 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CORNING 110253184 | 31.88 | 37.7117 | 25.5074 |  | 0.064583 | Removal-Remote Grid | UG Infeasible | 12.1398 |  | 15 | 10 | 1 | 5 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CORNING 1102915324 | 3.3709 | 4.5259 | 4.5259 | 3.9125 | 0 |  | UG Infeasible | 0 |  | 3 | 3 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
COTTONWOOD 1102544790 | 17.0951 | 13.8962 | 13.8962 |  | 0 |  | All UG | 0 |  | 4 | 4 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CURTIS 1701CB | 12.0919 | 3.1371 | 3.1371 |  | 0 |  | All UG | 0 |  | 4 | 4 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ELK CREEK 11012002 | 29.5396 | 19.2555 | 16.2426 |  | 0.81288 | Removal-Remote Grid | Cost effective alternative to UG – Remote Grid/Removal | 2.2 |  | 8 | 7 | 1 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ELK CREEK 110193504 | 2.4653 | 1.6619 | 0.51913 |  | 1.1428 |  | Cost effective alternative to UG – Hybrid | 0 |  | 2 | 1 | 2 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
JESSUP 1103348657 | 2.3619 | 3.1708 | 1.686 |  | 1.4848 |  | Cost effective alternative to UG – Hybrid | 0 |  | 4 | 2 | 2 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
REDBUD 1101454 | 5.5288 | 10.8112 | 10.8112 | 7.4394 | 0 |  | All UG | 0 |  | 3 | 3 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
REDBUD 1101708166 | 20.6836 | 13.0002 | 11.5504 |  | 1.4498 |  | Cost effective alternative to UG – Hybrid | 0 |  | 10 | 10 | 2 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
TEJON 11022455 | 6.3046 | 9.1028 | 9.1028 |  | 0 |  | All UG | 0 |  | 3 | 3 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
COTTONWOOD 11029026 | 24.4492 | 22.7977 | 22.3379 |  | 0.39697 | Removal | Portion of [Total Constructed Miles] is pure Removal, Dependency Constraint | 0.062879 |  | 7 | 7 | 2 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
REDBUD 1101323962 | 28.5898 | 25.0542 | 20.2163 |  | 0.68996 | Removal | Cost effective alternative to UG – Hybrid | 4.1479 |  | 11 | 9 | 1 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
JESSUP 11021550 | 22.0963 | 25.9755 | 24.0121 |  | 1.9634 |  | GRC Decision required Hybrid Consideration | 0 |  | 13 | 12 | 2 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG BASIN 110110720 | 4.5212 | 0.19413 | 0.1803 |  | 0.013826 |  | Cost effective alternative to UG – Hybrid, Other - FRRB | 0 |  | 1 | 1 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG BASIN 11022253 | 0.64585 | 0.78466 | 0.74318 |  | 0.041477 |  | UG Infeasible, Other - FRRB | 0 |  | 2 | 2 | 1 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
LINCOLN 11042070 | 28.8441 | 4.2509 | 4.2509 | 4.2011 | 0 |  | Cost effective alternative to UG – Hybrid | 0 |  | 2 | 2 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VACAVILLE 11088762 | 20.3292 | 7.9837 | 7.9837 |  | 0 |  | Dependency Constraint | 0 |  | 6 | 6 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VACAVILLE 110838316 | 22.811 | 12.8513 | 12.8513 |  | 0 |  | All UG | 0 |  | 9 | 9 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VACAVILLE 1111CB | 11.837 | 7.8642 | 7.8642 |  | 0 |  | UG Infeasible | 0 |  | 4 | 4 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
JAMESON 110265516 | 11.2485 | 11.7864 | 11.7186 |  | 0.067803 |  | Dependency Constraint | 0 |  | 10 | 9 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
HORSESHOE 110150140 | 6.2697 | 3.3313 | 1.6835 | 2.4509 | 1.6477 |  | Cost effective alternative to UG – Hybrid | 0 |  | 3 | 2 | 2 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
LINCOLN 1104275986 | 0.59634 | 6.9331 | 3.6258 |  | 2.4473 | Removal | Cost effective alternative to UG – Hybrid | 0.86004 |  | 3 | 2 | 2 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
LINCOLN 1104685276 | 21.7153 | 3.5163 | 2.8366 |  | 0 | Removal | Portion of [Total Constructed Miles] is pure Removal, Cost effective alternative to UG – Hybrid | 0.67973 |  | 2 | 2 | 0 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
JAMESON 1105466348 | 30.1496 | 16.8025 | 15.7869 | 16.0002 | 1.0155 |  | Dependency Constraint | 0 |  | 10 | 10 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
JAMESON 1105371694 | 4.034 | 0.28826 | 0.28826 | 0.24394 | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
JAMESON 1105913400 | 1.0937 | 1.5386 | 1.5386 | 0.76458 | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PANORAMA 1101CB | 16.8654 | 1.6341 | 1.6341 | 0.87216 | 0 |  | All UG | 0 |  | 2 | 2 | 0 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
FLINT 1101750 | 9.2159 | 5.39 | 4.6273 |  | 0.76269 |  | Dependency Constraint | 0 |  | 5 | 3 | 2 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
FLINT 1101958726 | 0.9988 | 0.1322 | 0.1322 | 0.18466 | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WYANDOTTE 1110980944 | 16.2764 | 11.7025 | 10.9795 |  | 0.4053 | Removal | Cost effective alternative to UG – Hybrid | 0.31761 |  | 8 | 7 | 1 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
LINCOLN 110451756 | 34.6465 | 2.2848 | 0.20777 | 1.6602 | 2.0771 |  | Cost effective alternative to UG – Hybrid | 0 |  | 1 | 1 | 1 | 0 | No | No
BELL 11082202 | 32.9026 | 27.6686 | 12.3025 |  | 15.3661 |  | Cost effective alternative to UG – Hybrid | 0 |  | 18 | 8 | 12 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG BASIN 110212758 | 5.8761 | 0.13617 | 0.13617 |  | 0 |  | All UG, Other - FRRB | 0 |  | 1 | 1 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VACAVILLE 111113652 | 4.2785 | 4.9008 | 4.9008 |  | 0 |  | UG Infeasible | 0 |  | 2 | 2 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
JAMESON 11059472 | 7.2592 | 1.465 | 0.48902 | 1.5472 | 0.97595 |  | Cost effective alternative to UG – Hybrid | 0 |  | 2 | 2 | 1 | 0 | No | No | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG BASIN 11025066 | 6.8255 | 7.6352 | 7.0939 |  | 0.54129 |  | Other - FRRB | 0 |  | 5 | 4 | 1 | 0 |  | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG BASIN 110296986 | 5.7292 | 0.14489 | 0.14489 |  | 0 |  | All UG, Other - FRRB | 0 |  | 1 | 1 | 0 | 0 | No | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BONNIE NOOK 1101CB | 14.4437 | 23.5297 | 23.5297 |  | 0 |  | UG Infeasible | 0 |  | 7 | 7 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
FORESTHILL 110150486 | 11.6351 | 17.8684 | 17.8684 |  | 0 |  | UG Infeasible | 0 |  | 6 | 6 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MARIPOSA 21019400 | 62.3092 | 21.6991 | 21.5812 |  | 0 | Removal | Portion of [Total Constructed Miles] is pure Removal, Other - FRRB | 0.1178 |  | 17 | 14 | 0 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MARIPOSA 210110240 | 19.8722 | 21.9718 | 8.4619 |  | 13.5098 |  | GRC Decision required Hybrid Consideration | 0 |  | 9 | 4 | 5 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MARIPOSA 210110170 | 16.1371 | 0.98144 | 0.98144 |  | 0 |  | All UG | 0 |  | 2 | 2 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
STANISLAUS 17021888 | 18.9786 | 6.2951 | 6.2951 |  | 0 |  | All UG | 0 |  | 4 | 4 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
FORESTHILL 110137238 | 11.5935 | 2.4714 | 1.928 |  | 0 |  | Cost effective alternative to UG – Remote Grid/Removal | 0.54337 |  | 4 | 1 | 0 | 3 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BRUNSWICK 110651486 | 56.752 | 0.10549 | 0.10549 | 0.30568 | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 | No | No | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PLACERVILLE 21061104 | 49.2341 | 1.0307 | 1.0307 | 0.04072 | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ANTLER 11011520 | 8.9409 | 11.236 | 8.859 |  | 0 | Removal-Remote Grid | Cost effective alternative to UG – Remote Grid/Removal | 2.377 |  | 5 | 4 | 0 | 1 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PINE GROVE 1101CB | 4.2753 | 6.7223 | 6.6359 |  | 0.086364 |  | UG Infeasible | 0 |  | 3 | 3 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PINE GROVE 110213438 | 16.5261 | 5.7727 | 5.5822 |  | 0.19053 |  | UG infeasible | 0 |  | 2 | 2 | 1 | 0 | Yes | Yes | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ALLEGHANY 1101VR816 | 4.0965 | 5.7032 | 4.4055 |  | 1.2977 |  | GRC Decision required Hybrid Consideration | 0 |  | 8 | 7 | 7 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ALLEGHANY 1102CB | 17.7807 | 34.355 | 34.355 |  | 0 |  | Cost effective alternative to UG – Remote Grid/Removal | 1.7045e-05 |  | 14 | 13 | 0 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ANTLER 11011384 | 9.0375 | 14.698 | 14.698 |  | 0 |  | All UG | 0 |  | 4 | 4 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ANTLER 11011612 | 7.9154 | 11.7627 | 7.0237 |  | 4.739 |  | GRC Decision required Hybrid Consideration | 0 |  | 10 | 7 | 6 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ANTLER 1101CB | 1.5904 | 1.0801 | 0.42008 |  | 0.66004 |  | GRC Decision required Hybrid Consideration | 0 |  | 1 | 1 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
APPLE HILL 1104CB | 4.0817 | 5.5 | 5.39 |  | 0.11 |  | UG Infeasible | 0 |  | 2 | 2 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
APPLE HILL 21026552 | 12.1088 | 16.3214 | 16.2116 |  | 0.10985 |  | UG Infeasible | 0 |  | 5 | 5 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
APPLE HILL 21027502 | 22.8336 | 34.9559 | 34.9559 |  | 0 |  | UG Infeasible | 0 |  | 10 | 10 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
APPLE HILL 210289934 | 5.4274 | 5.3799 | 0.93996 |  | 4.44 |  | GRC Decision required Hybrid Consideration | 0 |  | 2 | 2 | 2 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
AUBERRY 1101R2839 | 12.5464 | 0.0875 | 0.083333 |  | 0.0041667 |  | Cost Effective alternative to UG - Hybrid | 0 |  | 1 | 1 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BEAR VALLEY 210576694 | 4.5851 | 5.15 | 2.14 |  | 2.95 | Removal | Portion of [Total Constructed Miles] is pure Removal | 0.060038 |  | 2 | 2 | 2 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
BIG BEND 1101180398 | 5.3451 | 3.22 | 0.7 |  | 2.27 |  | GRC Decision required Hybrid Consideration | 0.25 |  | 3 | 3 | 2 | 1
CALISTOGA 1101122350 | 13.4533 | 13.2581 | 5.0621 |  | 7.858 | Removal | GRC Decision required Hybrid Consideration | 0.33807 |  | 16 | 7 | 11 | 2 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CALISTOGA 110143924 | 9.3913 | 8.6841 | 2.964 |  | 5.7201 |  | GRC Decision required Hybrid Consideration | 0 |  | 6 | 3 | 4 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CALISTOGA 1102131531 | 4.8416 | 5.0801 | 1.7098 |  | 3.3703 |  | Cost effective alternative to UG – Hybrid | 0 |  | 5 | 2 | 4 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLAYTON 2212614950 | 1.4029 | 0.66989 | 0.65 |  | 0.019886 |  | UG Infeasible | 0 |  | 1 | 1 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CLAYTON 2212681608 | 26.818 | 27.1996 | 0.043939 |  | 26.9657 |  | GRC Decision required Hybrid Consideration | 0.18996 |  | 11 | 1 | 11 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
COLUMBIA HILL 110190730 | 8.3716 | 8.7188 | 2.9295 |  | 5.7892 |  | GRC Decision required Hybrid Consideration | 0 |  | 7 | 5 | 7 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CURTIS 170356972 | 8.2034 | 8.5341 | 0.24508 |  | 8.289 |  | Cost Effective alternative to UG - Hybrid | 0 |  | 5 | 1 | 5 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
CURTIS 17039240 | 10.8962 | 16.7799 | 16.7699 |  | 0.010038 |  | UG Infeasible | 0 |  | 9 | 9 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
DRUM 1101CB | 2.1646 | 2.09 | 0.27992 |  | 1.81 |  | GRC Decision required Hybrid Consideration | 0 |  | 2 | 1 | 2 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ECHO SUMMIT 1101481660 | 1.1404 | 0.94148 | 0.21989 |  | 0.72159 |  | Other - FRRB | 0 |  | 4 | 1 | 3 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
DUNBAR 1103534 | 17.1371 | 1.3818 | 1.3818 |  | 0 |  | All UG | 0 |  | 2 | 2 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ELECTRA 11017104 | 12.074 | 16.1377 | 16.1377 |  | 0 |  | All UG | 0 |  | 4 | 4 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ELECTRA 1101L1697 | 5.7665 | 6.54 | 5.66 |  | 0.87992 |  | UG Infeasible | 0 |  | 3 | 3 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ELK CREEK 11012032 | 9.3496 | 9.4299 | 0.48996 |  | 8.94 |  | GRC Decision required Hybrid Consideration | 0 |  | 2 | 1 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
INDIAN FLAT 1104CB | 15.817 | 15.9294 | 3.0598 |  | 12.7496 | Removal | Cost Effective alternative to UG - Hybrid | 0.11989 |  | 10 | 3 | 7 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
FORESTHILL 11022106 | 27.8705 | 36.3008 | 27.9 |  | 7.65 | Removal-Remote Grid | Portion of [Total Constructed Miles] is pure Removal, GRC Decision required Hybrid Consideration | 0.75076 |  | 16 | 15 | 5 | 2 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
GIRVAN 11029012 | 15.5575 | 15.0799 | 0.33996 |  | 14.34 | Removal | GRC Decision required Hybrid Consideration | 0.4 |  | 6 | 1 | 6 | 3 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ORO FINO 1102CB | 2.157 | 3.164 | 3.137 |  | 0.027 |  | UG Infeasible | 0 |  | 3 | 3 | 2 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PLACERVILLE 210611132 | 42.7004 | 56.1935 | 27.2548 |  | 28.8186 | Removal | GRC Decision required Hybrid Consideration | 0.12008 |  | 28 | 23 | 23 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
STANISLAUS 17011812 | 19.2034 | 25.9956 | 25.9928 |  | 0.0028409 |  | All UG | 0 |  | 10 | 10 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SILVERADO 2104515946 | 16.2604 | 17.6571 | 13.98 |  | 3.6771 |  | GRC Decision required Hybrid Consideration | 0 |  | 8 | 5 | 3 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WEST POINT 11021341 | 9.7908 | 10.5994 | 10.4295 |  | 0.16989 |  | UG Infeasible | 0 |  | 6 | 6 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
KESWICK 11011588 | 8.7083 | 12.4479 | 2.06 |  | 3.25 | Removal-Remote Grid | GRC Decision required Hybrid Consideration | 7.1379 |  | 5 | 2 | 2 | 3 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
NOTRE DAME 11042028 | 10.8392 | 14.1899 | 12.875 |  | 1.3149 |  | GRC Decision required Hybrid Consideration | 0 |  | 8 | 7 | 2 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
KESWICK 110148480 | 10.5204 | 10.5297 | 0.27992 |  | 10.2498 |  | GRC Decision required Hybrid Consideration | 0 |  | 3 | 1 | 3 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
KESWICK 11019712 | 18.5915 | 19.8705 | 6.0902 |  | 13.3203 | Removal | Portion of [Total Constructed Miles] is pure Removal, GRC Decision required Hybrid Consideration | 0.46004 |  | 10 | 5 | 8 | 4 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PLACERVILLE 2106935216 | 20.7464 | 33.0955 | 33.0756 |  | 0.019886 |  | UG Infeasible | 0 |  | 14 | 14 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
OAKHURST 110310140 | 16.6046 | 19.5741 | 7.4972 |  | 12.0769 |  | GRC Decision required Hybrid Consideration | 0 |  | 13 | 11 | 12 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WILDWOOD 110198896 | 5.0272 | 6.3699 | 4.66 |  | 1.6299 | Removal | Portion of [Total Constructed Miles] is pure Removal, GRC Decision required Hybrid Consideration | 0.079924 |  | 4 | 4 | 3 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WEST POINT 110277204 | 7.4433 | 8.15 | 3.46 |  | 4.64 | Removal | GRC Decision required Hybrid Consideration | 0.05 |  | 3 | 1 | 3 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MIDDLETOWN 11011314 | 0.92536 | 1.05 | 1.05 |  | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MIDDLETOWN 1101171414 | 3.5119 | 2.4299 | 2.4299 |  | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MIWUK 170236888 | 0.61464 | 0.43996 | 0.42992 |  | 0.010038 |  | UG Infeasible | 0 |  | 1 | 1 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
Middletown 1101433160 |  | 1.39 | 1.39 |  | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
MOUNTAIN QUARRIES 210135466 | 7.2944 | 6.86 | 0.33996 |  | 6.5201 |  | GRC Decision required Hybrid Consideration | 0 |  | 3 | 2 | 3 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PLACERVILLE 111219712 | 12.9786 | 14.0303 | 5.9002 |  | 8.1301 |  | GRC Decision required Hybrid Consideration | 0 |  | 14 | 8 | 11 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PIT NO 3 2101CB | 4.5495 | 5.757 | 5.7061 |  | 0.050947 |  | All UG | 0 |  | 3 | 3 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PIT NO 5 1101CB | 0.744 | 0.93409 | 0.67405 |  | 0.26004 |  | GRC Decision required Hybrid Consideration | 0 |  | 1 | 1 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
OREGON TRAIL 11021584 | 13.1714 | 14.3301 | 7.0301 |  | 7.26 | Removal | GRC Decision required Hybrid Consideration | 0.039962 |  | 10 | 5 | 5 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
ORO FINO 110276008 | 16.1491 | 20.19 | 20.19 |  | 0 |  | All UG | 0 |  | 10 | 10 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SHADY GLEN 11022232 | 19.7286 | 27.6939 | 27.1439 |  | 0.55 |  | UG Infeasible | 0 |  | 18 | 17 | 1 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
TIGER CREEK 0201CB | 0.23574 | 4.3384 | 4.3384 |  | 0 |  | UG Infeasible | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PIKE CITY 11011720 | 5.8943 | 7.52 | 7.52 |  | 0 |  | All UG | 0 |  | 2 | 2 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PIKE CITY 1101CB | 19.67 | 28.1799 | 28.1799 |  | 0 |  | UG Infeasible | 0 |  | 16 | 7 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SILVERADO 2104646776 | 3.5161 | 2.235 | 2.235 |  | 0 |  | UG Infeasible | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
PINE GROVE 11013166 | 12.1497 | 2.456 | 2.456 |  | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SYCAMORE CREEK 11112268 | 21.6869 | 28.2697 | 27.7897 |  | 0 | Removal-Remote Grid | Cost effective alternative to UG – Remote Grid/Removal, All UG | 0.48 |  | 10 | 9 | 0 | 1 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SILVERADO 2104632 | 18.385 | 28.1292 | 28.1292 |  | 0 |  | UG Infeasible | 0 |  | 11 | 11 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
POINT MORETTI 110112122 | 8.833 | 1.1119 | 1.1119 |  | 0 |  | All UG, Other - FRRB | 0 |  | 2 | 2 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WEST POINT 11014706 | 11.4709 | 15.307 | 15.307 |  | 0 |  | All UG | 0 |  | 7 | 7 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
SILVERADO 2104708 | 4.9167 | 4.8312 | 4.8312 |  | 0 |  | UG Infeasible | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
STANISLAUS 170237278 | 6.7927 | 10.65 | 10.65 |  | 0 |  | All UG | 0 |  | 5 | 5 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
STANISLAUS 17026028 | 8.3079 | 9.28 | 9.28 |  | 0 |  | All UG | 0 |  | 3 | 3 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
TEJON 11023751 | 9.2397 | 8.5934 | 8.5934 |  | 0 |  | All UG | 0 |  | 4 | 4 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
TEJON 1102732836 | 15.5796 | 9.4362 | 9.4362 |  | 0 |  | All UG | 0 |  | 4 | 4 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
VACAVILLE 110847860 | 3.8733 | 0.44508 | 0.44508 |  | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WEST POINT 1101CB | 4.7928 | 5.2598 | 5.2598 |  | 0 |  | UG Infeasible | 0 |  | 2 | 2 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
WEST POINT 11024788 | 72.2384 | 3.26 | 3.26 |  | 0 |  | All UG | 0 |  | 1 | 1 | 0 | 0 |  |  | Already installed in the HFTD/HFRA. Will be enabled during the year based on our weather and fire modeling
Note (A):
GRC Decision required Hybrid Consideration – These are projects that were rescoped to Hybrid following the 2023 GRC decision to fulfill the risk reduction and cost target while staying under the authorized mileage caps for OH and UG.
Cost Effective Alternative to UG – Remote Grid/Removal – These are projects where Remote Grid, LEIP, or Removal was selected as a solution.
Cost Effective Alternative to UG – Hybrid – These are projects that were scoped as Hybrid using the decision tree prior to the inception of the UG program. These projects were scoped Hybrid from the perspective of, “why not OH?” Hybrid was chosen due to Vegetation Fall-in and Ingress/Egress.
UG Infeasible – These are locations where Overhead was used due to construction constraints.
Dependency Constraint – These are locations where an environmental, cultural, or permitting constraint shifted a project to hybrid. Examples include: CALTRANS ROW where it is access controlled and an alternative route did not exist, if the project is going through a cultural area and UG is not allowed, or a significant contamination (i.e., asbestos) that UG was not advisable.
Other - FRBB - Emerging work in response to a fire where existing lines were destroyed but the customer meter and property was not damaged.
Other - Wires Down - Program targeted specific overhead conductor that represented a potential safety and reliability hazard.