## 2024 Expense Summary
Expense 2024 WMP Forecast vs Actual Overview
Financials are shown in $ Thousands
Target / Target-Quarterly / Objective | 2023-2025 WMP Category | 2023-2025 WMP Section # | 2023-2025 WMP Section Name | Utility Initiative Tracking ID | 2023-2025 WMP Initiative Name | 2024 Planned Budget (as reported in the WMP in 1,000s) | 2024 Actual Expenditure (in 1,000s) | Variance | Met Threshold for Variance Explanation (greater than 10%) | Detailed explanation of the reason for the discrepancy
Objective | Grid Design, Operations and Maintenance | 8.1.9.1 | Asset Inspections | AI-01 | Retainment of Inspectors and Internal Workforce Development | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.1 | Ground Detailed Inspections | AI-02 | Detailed Inspection Transmission – Ground | 7238.95 | 6737.4315 | -501.5185 | No
Objective | Grid Design, Operations and Maintenance | 8.1.3.2.7 | Pilot Inspections | AI-03 | Develop Distribution Aerial Inspections program | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.2 | Aerial Detailed Inspections | AI-04 | Detailed Inspection Transmission – Aerial | 17102.52 | 16704.9647 | -397.5553 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.3 | Climbing Detailed Inspections | AI-05 | Detailed Inspection Transmission – Climbing | 1213.61 | 1686.3238 | 472.7138 | Yes | Target met; Inspection charges misallocated to HFTD order numbers rather than NHFTD order numbers on reinspection’s due to InspectApp glitch in March/April.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.4 | Infrared Inspections | AI-06 | Perform transmission infrared inspections | 1327.97 | 1185.9227 | -142.0473 | Yes | Target met; 2024 BFV WMP EOY favorability was driven by the shift from renting hardware equipment in the prior year (2023) to purchasing and owning equipment in current year (2024), resulting in lower overall costs. Additionally, the planning team improved operational efficiency by strategically positioning crews in areas where circuit loading was optimal and scheduling work around favorable weather conditions (e.g., avoiding fog and high winds). These efforts reduced the number of helicopter flight days and total crew time required on the program.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.2.1 | Detailed Ground Inspections | AI-07 | Detailed Ground Inspections - Distribution | 28951.44 | 23989.7307 | -4961.7093 | Yes | Aerial Distribution saw favorability thru efficiency gains throughout year due to improvement of overall processes related to inspector skillset and data collection methods. Overhead Line Inspections saw favorability due to new and improved checklist and using internal inspectors.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-08 | Supplemental Inspections - Substation Distribution | 2649.37 | 2378.1567 | -271.2133 | Yes | Favorability primarily due to efficiency in ground, Infrared, and Aerial inspections due to process improvement.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-09 | Supplemental Inspections - Substation Transmission | 2647.18 | 2143.7528 | -503.4272 | Yes | Favorability primarily due to efficiency in ground, Infrared, and Aerial inspections due to process improvement.
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 1016.6667 | 2246.0843 | 1229.4176 | Yes | Target met; At the end of 2024, System Inspection identified that costs to perform PG drone inspections were incorrectly charged to Substation orders in 2023. Actual inspection costs exceeded forecasted costs due to aerial drone inspections which were previously incorrectly charged to substation orders being correctly charged to Power Gen during the 2024 inspection season. Additionally, contract resources were used to perform ground inspections because internal resources were not available resulting in an increased cost.
Objective | Grid Design, Operations and Maintenance | 8.1.5 | Asset Management and Inspection Enterprise System(s) | AI-11 | Filling Asset Inventory Data Gaps | 0 | 0 | 0 | No
Objective | Community Outreach and Engagement | 8.5.2 | Public Outreach and Education Awareness Program | CO-01 | Community Engagement - Meetings | 0 | 0 | 0 | No
Target (Quarterly) | Community Outreach and Engagement | 8.5.4 | Public Outreach and Education Awareness Program | CO-02 | Community Engagement - Surveys | 0 | 0 | 0 | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.3 | Public Outreach and Education Awareness Program | CO-04 | Community Engagement - Outreach to HFRA Infrastructure Customers | 0 | 0 | 0 | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.5 | Public Outreach and Education Awareness Program | CO-05 | Community Engagement - Outage Preparedness Campaign | 0 | 0 | 0 | No
Objective | Emergency Preparedness | 8.4.2.3.1 | Drills, Simulations, and Tabletop Exercises | EP-01 | Complete PSPS and Wildfire Tabletop and Functional Exercises | 0 | 0 | 0 | No
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-02 | Maintain All Hazards planning and preparedness program | 0 | 0 | 0 | No
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-04 | Expand All Hazards planning to include additional threats and scenarios | 0 | 0 | 0 | No
Target | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-07 | Common Operating Picture Technology | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-08 | Threats and Hazards Identification and Risk Assessment (THIRA) updates | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-09 | County Execute Briefings | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-01 | System Hardening - Distribution | 0 | 0 | 0 | No
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-02 | Evaluate Covered Conductor Effectiveness | 0 | 0 | 0 | No
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-03 | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.2 | Undergrounding of electric lines and/or equipment | GH-04 | 10K Undergrounding | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-05 | System Hardening - Transmission | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-06 | System Hardening - Transmission Shunt Splices | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.8.1 | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Distribution Protective Devices | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.10.4 | Surge Arrestors | GH-08 | Surge Arrestor - Removals | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.10.3 | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Distribution Line Motor Switch Operator (MSO) - Replacements | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.10.5 | Non-Exempt Expulsion Fuses | GH-10 | Non-Exempt Expulsion Fuse - Removal | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.6.1 | Quality Assurance (QA) | GM-01 | Asset Inspections - Quality Assurance | 5449.49 | 8052.3543 | 2602.8643 | Yes | Target met; Unfavorability increase primarily due to 2023 accounting for the new QASI program did not include all costs related to sampling, dispatch, data collection and reporting, which was resolved in 2024 accounting.
Target | Grid Design, Operations and Maintenance | 8.1.7.1 | Open Work Orders - Transmission | GM-02 | HFTD-HFRA Open Tag Reduction - Transmission | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.8.1 | Downed Conductor Detection (DCD) Devices | GM-06 | EPSS - Down Conductor Detection (DCD) | 0 | 0 | 0 | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.8.1.1 | Protective Equipment and Device Settings | GM-07 | Updates on EPSS Reliability Study | 0 | 0 | 0 | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-08 | Eliminate HFTD/HFRA distribution backlog | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.6.2 | Quality Control (QC) | GM-09 | Asset Inspection – Quality Control | 29737.5 | 31434.0121 | 1696.5121 | No
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-01 | Evaluate enhancements for the PSPS Transmission guidance | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions | 0 | 0 | 0 | No
Target | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | 12614.26 | 12635.1328 | 20.8728 | No
Target | Public Safety Power Shutoff | 9.1.5 | Performance Metrics Identified by the Electrical Corporation | PS-07 | Reduce PSPS impacts by ~55k customer events (3.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-08 | Evaluate emerging technologies to reduce PSPS customer impact | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-09 | Reduce PSPS impacts via Undergrounding | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-10 | Continue sharing PSPS lessons learned | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-11 | Pilot using drones for PSPS restoration | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-01 | Artificial Intelligence (AI) in Wildfire Cameras | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.1 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures | SA-02 | Line Sensor - Installations | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-03 | EFD and DFA Reporting | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-04 | FPI and IPW Modeling - Revision Evaluation | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | 3278.38 | 2138.1233 | -1140.2567 | Yes | Target met; Favorability primarily due to internal labor for IT supporting the AWS migration and development for meteorology. The main increase was driven by development of the PSPS dashboard in weathermap, which was not originally forecast.
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-06 | Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-07 | Monitor and evaluate the Cameras AI system’s performance | 0 | 0 | 0 | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-08 | Evaluate the Cameras AI system functionalities and technologies | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-09 | EFD and DFA Reporting | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-10 | Distribution Fault Anticipation (DFA) Installations | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-11 | Early Fault Detection (EFD) Installations | 0 | 0 | 0 | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-12 | Evaluate the use and effectiveness of real-time monitoring tools | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission NERC and Non-NERC | VM-01 | LiDAR Data Collection - Transmission | 6633.96 | 6999.6853 | 365.7253 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.3.1 | Pole Clearing | VM-02 | Pole Clearing Program | 71303 | 68512.3599 | -2790.6401 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-03 | Focused Tree Inspection (FTI) | 76549.762 | 61915.1189 | -14634.6431 | Yes | Favorability primarily the result of decreased units completed due to a rebalance of work, that was based upon a risk-informed assessment of available tree work. Funding/ work was reallocated from Focused Tree Inspection (FTI) to prioritize work in areas that held higher risk in the marked tree inventory and reduced the overall carryover.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.4 | Tree Removal | VM-04 | Tree Removal Inventory (TRI) | 26772.394 | 26655.5329 | -116.8611 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-05 | Defensible Space Inspections - Distribution Substation | 2500.02 | 2389.9469 | -110.0731 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-06 | Defensible Space Inspections - Transmission Substation | 1282.5 | 1048.9549 | -233.5451 | Yes | Target met; Primary underspend driver for VM-06 (AMG) - while the team met the annual WMP commitments completing inspections and mitigation work at 55 sites, the remaining budget was planned for additional defensible space improvements however those opportunities did not occur.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 1916.6667 | 1558.4732 | -358.1934 | Yes | Target met; Favorability driven by better weather and enviromental conditions.
Target | Vegetation Management and Inspection | 8.2.5 | Quality Assurance and Quality Control | VM-08 | Vegetation Management – Quality Assurance | 14709.56 | 13104.145 | -1605.415 | Yes | Target met; Program met targeted metrics while incurring cost below forecast. Favorable cost variance was primarily driven by increased workforce efficiency, resulting in higher productivity, as well as cost sharing opportunities with Electric Operations that reduced overall program expenditures.
Objective | Vegetation Management and Inspection | 8.2.6 | Open Work Orders | VM-09 | Constraint Resolution Procedural Guideline | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2 | Vegetation Management Inspections | VM-10 | Inspection in HFTD and HFRA supporting key vegetation management initiatives | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-11 | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.1 | VM Transmission and Distribution Inspections | VM-12 | Evaluate emerging technologies | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission – Ground | VM-13 | Routine Ground - Transmission | 25666.62 | 26433.8979 | 767.2779 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.2 | Transmission Second Patrol | VM-14 | Transmission Second Patrol | 1192.27 | 3695.207 | 2502.937 | Yes | Target met; Unfavorability primarily due to unplanned costs of inspections and data collection using LiDAR. Actual expenditure represents the cost of PG&E completing the VM-14 target.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.3 | Integrated Vegetation Management | VM-15 | Integrated Vegetation Management - Transmission | 14576.81 | 9164.3906 | -5412.4194 | Yes | Achieved the VM-15 inspections target while completing a lower volume of IVM tree work compared to original plan
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.1 | Distribution Routine Patrol | VM-16 | Distribution Routine Patrol | 843832.4654 | 890506.9995 | 46674.5341 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.2 | Distribution Second Patrol | VM-17 | Distribution Second Patrol | 159324.34 | 135186.1157 | -24138.2243 | Yes | Target met; Favorability primarily resulted from reduction in average unit cost due to change in mix of work types in identified work, and reduction in late Q4 work completed due to adverse weather conditions, compared to budget forecast.
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.3 | VM for Operational Mitigations | VM-18 | VM for Operational Mitigations (VMOM) | 15086.456 | 8418.8837 | -6667.5723 | Yes | Favorability primarily the result of decreased units completed due to a rebalance of work based upon a risk-informed assessment of available tree work. Funding/ work was reallocated from VM for Operational Mitigations (VMOM) to prioritize work in areas that held higher risk in the marked tree inventory and reduced the overall carryover.
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | 27000 | 29511.717 | 2511.717 | No
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-20 | Record Keeping Enhancement (VMOM, TRI) | 0 | 0 | 0 | No
Objective | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-21 | FTI Record Keeping Enhancement | 0 | 1310.936 | 1310.936 | Yes | Target met; Costs were incurred to enhance digital recordkeeping. VM-21 was not budgeted separately, instead it was part of the larger Technology budget.
Target | Vegetation Management and Inspection | 8.2.5.2 | Quality Control | VM-22 | Vegetation Management - Quality Control | 42453.09 | 40138.5005 | -2314.5895 | No
Total

## 2024 Capital Summary
Capital 2024 WMP Forecast vs Actual Overview
Financials are shown in $ Thousands
Target / Target-Quarterly / Objective | 2023-2025 WMP Category | 2023-2025 WMP Section # | 2023-2025 WMP Section Name | Utility Initiative Tracking ID | 2023-2025 WMP Initiative Name | 2024 Planned Budget (as reported in the WMP in 1,000s) | 2024 Actual Expenditure (in 1,000s) | Variance | Met Threshold for Variance Explanation (greater than 10%) | Detailed explanation of the reason for the discrepancy
Objective | Grid Design, Operations and Maintenance | 8.1.9.1 | Asset Inspections | AI-01 | Retainment of Inspectors and Internal Workforce Development | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.1 | Ground Detailed Inspections | AI-02 | Detailed Inspection Transmission – Ground | 0 | 0 | 0 | No
Objective | Grid Design, Operations and Maintenance | 8.1.3.2.7 | Pilot Inspections | AI-03 | Develop Distribution Aerial Inspections program | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.2 | Aerial Detailed Inspections | AI-04 | Detailed Inspection Transmission – Aerial | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.3 | Climbing Detailed Inspections | AI-05 | Detailed Inspection Transmission – Climbing | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.4 | Infrared Inspections | AI-06 | Perform transmission infrared inspections | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.2.1 | Detailed Ground Inspections | AI-07 | Detailed Ground Inspections - Distribution | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-08 | Supplemental Inspections - Substation Distribution | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-09 | Supplemental Inspections - Substation Transmission | 0 | 0 | 0 | No
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 0 | 0 | 0 | No
Objective | Grid Design, Operations and Maintenance | 8.1.5 | Asset Management and Inspection Enterprise System(s) | AI-11 | Filling Asset Inventory Data Gaps | 0 | 0 | 0 | No
Objective | Community Outreach and Engagement | 8.5.2 | Public Outreach and Education Awareness Program | CO-01 | Community Engagement - Meetings | 0 | 0 | 0 | No
Target (Quarterly) | Community Outreach and Engagement | 8.5.4 | Public Outreach and Education Awareness Program | CO-02 | Community Engagement - Surveys | 0 | 0 | 0 | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.3 | Public Outreach and Education Awareness Program | CO-04 | Community Engagement - Outreach to HFRA Infrastructure Customers | 0 | 0 | 0 | No
Objective (10 Year) | Community Outreach and Engagement | 8.5.5 | Public Outreach and Education Awareness Program | CO-05 | Community Engagement - Outage Preparedness Campaign | 0 | 0 | 0 | No
Objective | Emergency Preparedness | 8.4.2.3.1 | Drills, Simulations, and Tabletop Exercises | EP-01 | Complete PSPS and Wildfire Tabletop and Functional Exercises | 0 | 0 | 0 | No
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-02 | Maintain All Hazards planning and preparedness program | 0 | 0 | 0 | No
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-04 | Expand All Hazards planning to include additional threats and scenarios | 0 | 0 | 0 | No
Target | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-07 | Common Operating Picture Technology | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-08 | Threats and Hazards Identification and Risk Assessment (THIRA) updates | 0 | 0 | 0 | No
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-09 | County Execute Briefings | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-01 | System Hardening - Distribution | 97014.003 | 134731.6045 | 37717.6015 | Yes | Unfavorability due to increased volume of overhead miles completed 108 miles compared to the original plan of 70 miles. *The GH-01 target includes both overhead and underground miles. To prevent double counting costs, the expenditures related to underground work are shown in GH-04.
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-02 | Evaluate Covered Conductor Effectiveness | 0 | 0 | 0 | No
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-03 | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.2 | Undergrounding of electric lines and/or equipment | GH-04 | 10K Undergrounding | 960417.8646 | 1003608.7735 | 43190.9089 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-05 | System Hardening - Transmission | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-06 | System Hardening - Transmission Shunt Splices | 4900 | 2842.1287 | -2057.8713 | Yes | Target met; Favorability primarily due to reduced costs by collaboratively identifying efficiencies working with tag crews and leveraging existing clearances.
Target | Grid Design, Operations and Maintenance | 8.1.2.8.1 | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Distribution Protective Devices | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.2.10.4 | Surge Arrestors | GH-08 | Surge Arrestor - Removals | 5799.78 | 7529.0286 | 1729.2486 | Yes | Target met; Unfavorability primarily due to higher unit cost in North Valley and Central Valley (project locations required higher travel time and higher contractor costs) and higher cost of Quality as we implemented an enhanced QA process.
Target | Grid Design, Operations and Maintenance | 8.1.2.10.3 | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Distribution Line Motor Switch Operator (MSO) - Replacements | 5835.035 | 2940.0433 | -2894.9917 | Yes | Target met; Favorability was primarily due to original plan including MSO legacy work that was not a part of the WMP commitment and was ultimately deferred. There were also some scope changes from replacement to removal only, which resulted in lower cost due to not replacing with SCADA enable devices.
Target | Grid Design, Operations and Maintenance | 8.1.2.10.5 | Non-Exempt Expulsion Fuses | GH-10 | Non-Exempt Expulsion Fuse - Removal | 19800 | 16932.2832 | -2867.7168 | Yes | Target met; Favorability primarily due to lower unit cost because work was now being completed internal labor compared to the past which was primarily contractors executing work.
Target | Grid Design, Operations and Maintenance | 8.1.6.1 | Quality Assurance (QA) | GM-01 | Asset Inspections - Quality Assurance | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.7.1 | Open Work Orders - Transmission | GM-02 | HFTD-HFRA Open Tag Reduction - Transmission | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.8.1 | Downed Conductor Detection (DCD) Devices | GM-06 | EPSS - Down Conductor Detection (DCD) | 31257.1 | 30522.8181 | -734.2819 | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.8.1.1 | Protective Equipment and Device Settings | GM-07 | Updates on EPSS Reliability Study | 0 | 0 | 0 | No
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-08 | Eliminate HFTD/HFRA distribution backlog | 0 | 0 | 0 | No
Target | Grid Design, Operations and Maintenance | 8.1.6.2 | Quality Control (QC) | GM-09 | Asset Inspection – Quality Control | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-01 | Evaluate enhancements for the PSPS Transmission guidance | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions | 0 | 0 | 0 | No
Target | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | 0 | 0 | 0 | No
Target | Public Safety Power Shutoff | 9.1.5 | Performance Metrics Identified by the Electrical Corporation | PS-07 | Reduce PSPS impacts by ~55k customer events (3.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-08 | Evaluate emerging technologies to reduce PSPS customer impact | 0 | 0 | 0 | No
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-09 | Reduce PSPS impacts via Undergrounding | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-10 | Continue sharing PSPS lessons learned | 0 | 0 | 0 | No
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-11 | Pilot using drones for PSPS restoration | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-01 | Artificial Intelligence (AI) in Wildfire Cameras | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.1 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures | SA-02 | Line Sensor - Installations | 2463.04 | 2055.0294 | -408.0106 | Yes | Target met; Favorability primarily due to removing Non-WMP circuits from scope. Reduced Circuits from 54 units to 45 units due to the program being overplanned in the beginning of the year.
Objective | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-03 | EFD and DFA Reporting | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-04 | FPI and IPW Modeling - Revision Evaluation | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | 1852.19 | 2609.1909 | 757.0009 | Yes | Unfavorability primarily due to internal labor for IT supporting the Amazon Web Services (AWS) migration and development for meteorology. The main increase was driven by development of the PSPS dashboard in weathermap, which was not originally forecast.
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-06 | Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-07 | Monitor and evaluate the Cameras AI system’s performance | 0 | 0 | 0 | No
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-08 | Evaluate the Cameras AI system functionalities and technologies | 0 | 0 | 0 | No
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-09 | EFD and DFA Reporting | 0 | 0 | 0 | No
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-10 | Distribution Fault Anticipation (DFA) Installations | 2999.88 | 1909.0268 | -1090.8532 | Yes | Target met; Favorability primarily due to deferral of Engineering work, as there were 7 readiness projects for 2025 that did not get started (planned to be started in 2024).
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-11 | Early Fault Detection (EFD) Installations | 6999.99 | 3019.8272 | -3980.1628 | Yes | Target met; Favorability primarily due to work deferral with resource and schedule issues (2025 readiness work was not able to be started in 2024) and lower unit cost.
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-12 | Evaluate the use and effectiveness of real-time monitoring tools | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission NERC and Non-NERC | VM-01 | LiDAR Data Collection - Transmission | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.3.1 | Pole Clearing | VM-02 | Pole Clearing Program | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-03 | Focused Tree Inspection (FTI) | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.4 | Tree Removal | VM-04 | Tree Removal Inventory (TRI) | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-05 | Defensible Space Inspections - Distribution Substation | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-06 | Defensible Space Inspections - Transmission Substation | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 0 | 0 | 0 | No
Target | Vegetation Management and Inspection | 8.2.5 | Quality Assurance and Quality Control | VM-08 | Vegetation Management – Quality Assurance | 0 | 0 | 0 | No
Objective | Vegetation Management and Inspection | 8.2.6 | Open Work Orders | VM-09 | Constraint Resolution Procedural Guideline | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2 | Vegetation Management Inspections | VM-10 | Inspection in HFTD and HFRA supporting key vegetation management initiatives | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-11 | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | 0 | 0 | 0 | No
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.1 | VM Transmission and Distribution Inspections | VM-12 | Evaluate emerging technologies | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission – Ground | VM-13 | Routine Ground - Transmission | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.2 | Transmission Second Patrol | VM-14 | Transmission Second Patrol | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.3 | Integrated Vegetation Management | VM-15 | Integrated Vegetation Management - Transmission | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.1 | Distribution Routine Patrol | VM-16 | Distribution Routine Patrol | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.2 | Distribution Second Patrol | VM-17 | Distribution Second Patrol | 0 | 0 | 0 | No
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.3 | VM for Operational Mitigations | VM-18 | VM for Operational Mitigations (VMOM) | 0 | 0 | 0 | No
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | 0 | 0 | 0 | No
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-20 | Record Keeping Enhancement (VMOM, TRI) | 0 | 0 | 0 | No
Objective | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-21 | FTI Record Keeping Enhancement | 0 | 0 | 0 | No
Target | Vegetation Management and Inspection | 8.2.5.2 | Quality Control | VM-22 | Vegetation Management - Quality Control | 0 | 0 | 0 | No
Total

## Template (hidden)
[5 empty] | OPEX HFTD | #VALUE! | #VALUE!
[5 empty] | CAPEX HFTD | #VALUE! | #VALUE!
2023-2025 WMP Forecast vs Actual Overview
| Financials are shown in $ Thousands |  |  |  |  | #VALUE!
Target / Target-Quarterly / Objective | 2023-2025 WMP Category | 2023-2025 WMP Section # | 2023-2025 WMP Section Name | Utility Initiative Tracking ID | 2023-2025 WMP Initiatve Name | 2023 Planned Budget (as reported in the WMP Errata in 1,000s) | 2023 Actual Expenditure HFTD (in 1,000s) | Variance | . | Threshold for change (greater than 10%) | .. | Detailed explanation of the reason for the discrepancy
Objective | Community Outreach and Engagement | 8.5.2 | Public Outreach and Education Awareness Program | CO-01 | Community Engagement - Meetings | 14931.7992 | 11326.7317 | -3605.0675 | Yes | meet
Target (Quarterly) | Community Outreach and Engagement | 8.5.4 | Public Outreach and Education Awareness Program | CO-02 | Community Engagement - Surveys | 11834.5776 | 11580.847 | -253.7306 | Yes | not met
Objective (10 Year) | Community Outreach and Engagement | 8.5.3 | Public Outreach and Education Awareness Program | CO-04 | Community Engagement - Outreach to HFRA Infrastructure Customers | 23346.5806 | 9547.3863 | -13799.1943 | Yes | meet
Objective (10 Year) | Community Outreach and Engagement | 8.5.5 | Public Outreach and Education Awareness Program | CO-05 | Community Engagement - Outage Preparedness Campaign | 3496.1115 | 3404.964 | -91.1475 | Yes | not met
Objective | Emergency Preparedness | 8.4.2.3.1 | Drills, Simulations, and Tabletop Exercises | EP-01 | Complete PSPS and Wildfire Tabletop and Functional Exercises | 8700 | 7493.0565 | -1206.9435 | Yes | meet
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-02 | Maintain All Hazards planning and preparedness program | 4119 | 10850.7744 | 6731.7744 | Yes | meet
Objective | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-04 | Expand All Hazards planning to include additional threats and scenarios | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-07 | Common Operating Picture Technology | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-08 | Threats and Hazards Identification and Risk Assessment (THIRA) updates | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Emergency Preparedness | 8.4.3.1 | Emergency Planning | EP-09 | County Execute Briefings | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Grid Design, Operations and Maintenance | 8.1.9.1 | Asset Inspections | AI-01 | Retainment of Inspectors and Internal Workforce Development | PCC Costs | PCC Costs |  | No (PCC Costs)
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.1 | Ground Detailed Inspections | AI-02 | Detailed Inspection Transmission – Ground | 10177.4132 | 9168.7073 | -1008.7059 | Yes | not met
Objective | Grid Design, Operations and Maintenance | 8.1.3.2.7 | Pilot Inspections | AI-03 | Develop Distribution Aerial Inspections program | 2297.8178 | 3382.2149 | 1084.397 | Yes (1:1) | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.2 | Aerial Detailed Inspections | AI-04 | Detailed Inspection Transmission – Aerial | 16913.4639 | 16894.164 | -19.2999 | Yes | not met
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.3 | Climbing Detailed Inspections | AI-05 | Detailed Inspection Transmission – Climbing | 1438 | 4532.0562 | 3094.0562 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.1.4 | Infrared Inspections | AI-06 | Perform transmission infrared inspections | 1100 | 2908.9432 | 1808.9432 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.2.1 | Detailed Ground Inspections | AI-07 | Detailed Ground Inspections - Distribution | 23422.894 | 31626.4497 | 8203.5557 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-08 | Supplemental Inspections - Substation Distribution | 2826.0332 | 1083.5342 | -1742.499 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-09 | Supplemental Inspections - Substation Transmission | 2596.8896 | 1605.8621 | -991.0275 | Yes | meet
Target (Quarterly) | Grid Design, Operations and Maintenance | 8.1.3.3.1 | Asset Inspection Program - Substation | AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | 1181.6663 | 7.3612 | -1174.3051 | Yes | meet
Objective | Grid Design, Operations and Maintenance | 8.1.5 | Asset Management and Inspection Enterprise System(s) | AI-11 | Filling Asset Inventory Data Gaps | 0 | 0 | 0 | Yes
Target | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-01 | System Hardening - Distribution | 67504.2203 | 125029 | 57524.7797 | Yes | meet
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-02 | Evaluate Covered Conductor Effectiveness | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Grid Design, Operations and Maintenance | 8.1.2.1 | Covered conductor installation | GH-03 | Evaluate and Implement Covered Conductor Effectiveness Impact on Inspections and Maintenance Standards | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Grid Design, Operations and Maintenance | 8.1.2.2 | Undergrounding of electric lines and/or equipment | GH-04 | 10K Undergrounding | 1233980.7283 | 1128010 | -105970.7283 | Yes | not met
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-05 | System Hardening - Transmission | 14134.1732 | 17282 | 3147.8268 | Yes | meet
Target | Grid Design, Operations and Maintenance | 8.1.2.5.1 | Traditional overhead hardening - Transmission | GH-06 | System Hardening - Transmission Shunt Splices | 5000 | 2673 | -2327 | Yes | meet
Target | Grid Design, Operations and Maintenance | 8.1.2.8.1 | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Distribution Protective Devices | 12679.2 | 12151.24 | -527.96 | Yes (49A work) | not met
Target | Grid Design, Operations and Maintenance | 8.1.2.10.4 | Surge Arrestors | GH-08 | Surge Arrestor - Removals | 3796.5281 | 5190 | 1393.4719 | Yes (2AR work) | meet | -10222.2785
Target | Grid Design, Operations and Maintenance | 8.1.2.10.3 | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Distribution Line Motor Switch Operator (MSO) - Replacements | 3169.8 | 1809.29 | -1360.51 | Yes | meet | -10222.2785
Target | Grid Design, Operations and Maintenance | 8.1.2.10.5 | Non-Exempt Expulsion Fuses | GH-10 | Non-Exempt Expulsion Fuse - Removal | 27962.0933 | 18258 | -9704.0933 | Yes | meet | -10222.2785
Target | Grid Design, Operations and Maintenance | 8.1.6.1 | Quality Assurance (QA) | GM-01 | Asset Inspections - Quality Assurance | 1873.5091 | 4847 | 2973.4909 | Yes | meet | 16914.605
Target | Grid Design, Operations and Maintenance | 8.1.7.1 | Open Work Orders - Transmission | GM-02 | HFTD-HFRA Open Tag Reduction - Transmission | 1442.7149 | 1538.7305 | 96.0157 | Yes | not met | 211.6761
Target | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | 1737.8944 | 1853.5548 | 115.6605 | Yes | not met | 211.6761
Target | Grid Design, Operations and Maintenance | 8.1.2.10.1 | Downed Conductor Detection (DCD) Devices | GM-06 | EPSS - Down Conductor Detection (DCD) | 41301.1159 | 35571 | -5730.1159 | Yes | meet
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.8.1.1 | Protective Equipment and Device Settings | GM-07 | Updates on EPSS Reliability Study | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Grid Design, Operations and Maintenance | 8.1.7.2 | Open Work Orders - Distribution | GM-08 | Eliminate HFTD/HFRA distribution backlog | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Grid Design, Operations and Maintenance | 8.1.6.2 | Quality Control (QC) | GM-09 | Asset Inspection – Quality Control | 8783.8859 | 22725 | 13941.1141 | Yes | meet | 16914.605
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-01 | Evaluate enhancements for the PSPS Transmission guidance | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Public Safety Power Shutoff | 9.2.1 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-02 | Evaluate incorporation of approved IPW enhancements into the PSPS Distribution guidance | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-05 | Evaluate the transition of the Portable Battery Program to permanent battery solutions | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Public Safety Power Shutoff | 8.5.3 | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | 10800 | 10610.0236 | -189.9764 | Yes | not met
Target | Public Safety Power Shutoff | 9.1.5 | Performance Metrics Identified by the Electrical Corporation | PS-07 | Reduce PSPS impacts by ~55k customer events (3.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-08 | Evaluate emerging technologies to reduce PSPS customer impact | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-09 | Reduce PSPS impacts via Undergrounding | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-10 | Continue sharing PSPS lessons learned | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Public Safety Power Shutoff | 9.1.2 | Risk Thresholds (e.g., WS, FPI, etc.) and Decision Making Process That Determine the Need for a PSPS | PS-11 | Pilot using drones for PSPS restoration | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-01 | Artificial Intelligence (AI) in Wildfire Cameras | 6412.6448 | 6153.0575 | -259.5874 | Yes | not met
Target | Situational Awareness and Forecasting | 8.3.3.1 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures | SA-02 | Line Sensor - Installations | 7798.5822 | 3008 | -4790.5822 | Yes | meet
Objective | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-03 | EFD and DFA Reporting | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-04 | FPI and IPW Modeling - Revision Evaluation | 1976.0114 | 1880.6446 | -95.3668 | Yes | not met
Objective | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-05 | Evaluate FPI and IPW Modeling enhancements in 2023 - 2025 | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.6.3 | Planned Improvements | SA-06 | Evaluate FPI and IPW Modeling enhancements in 2026 - 2032 | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-07 | Monitor and evaluate the Cameras AI system’s performance | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-08 | Evaluate the Cameras AI system functionalities and technologies | PCC Costs | PCC Costs |  | No (PCC Costs)
Objective | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-09 | EFD and DFA Reporting | PCC Costs | PCC Costs |  | No (PCC Costs)
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-10 | Distribution Fault Anticipation (DFA) Installations | 999.92 | 180 | -819.92 | Yes | meet
Target | Situational Awareness and Forecasting | 8.3.3.3 | Grid Monitoring Systems, Planned Improvements | SA-11 | Early Fault Detection (EFD) Installations | 999.6568 | 644 | -355.6568 | Yes | meet | -6453.0511
Objective (10 Year) | Situational Awareness and Forecasting | 8.3.2.3 | Planned Improvements | SA-12 | Evaluate the use and effectiveness of real-time monitoring tools | PCC Costs | PCC Costs |  | No (PCC Costs)
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission NERC and Non-NERC | VM-01 | LiDAR Data Collection - Transmission | 10163 | 8575.303 | -1587.697 | Yes | meet |  | Asking LOB Dana Edwards for Split from VM-01
Target (Quarterly) | Vegetation Management and Inspection | 8.2.3.1 | Pole Clearing | VM-02 | Pole Clearing Program | 17049.5 | 16818.3226 | -231.1774 | Yes | not met
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-03 | Focused Tree Inspection (FTI) | 0 | 0 | 0 | Yes
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.4 | Tree Removal | VM-04 | Tree Removal Inventory (TRI) | 160356.7372 | 64936.3512 | -95420.386 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-05 | Defensible Space Inspections - Distribution Substation | 2521.7317 | 3374.6762 | 852.9445 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-06 | Defensible Space Inspections - Transmission Substation | 407.602 | 695 | 287.398 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.3.1 | Substation Defensible Space | VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 1906.6667 | 1321.5244 | -585.1423 | Yes | meet
Target | Vegetation Management and Inspection | 8.2.5 | Quality Assurance and Quality Control | VM-08 | Vegetation Management – Quality Assurance | Reached out to LOB for allocation from VM-22 | Reached out to LOB for allocation from VM-22 |  | Yes
Objective | Vegetation Management and Inspection | 8.2.6 | Open Work Orders | VM-09 | Constraint Resolution Procedural Guideline | 0 | 0 | 0 | Yes
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2 | Vegetation Management Inspections | VM-10 | Inspection in HFTD and HFRA supporting key vegetation management initiatives | Reached out to LOB for info | Reached out to LOB for info |  | Yes |  |  | Reached out to LOB Nicole de la Torre for info
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-11 | Enhance and refine Focus Tree Inspection – Areas of Concern (AOC) | Reached out to LOB for info | Reached out to LOB for info |  | Yes |  |  | Reached out to LOB Nicole de la Torre for info
Objective (10 Year) | Vegetation Management and Inspection | 8.2.2.1 | VM Transmission and Distribution Inspections | VM-12 | Evaluate emerging technologies | Reached out to LOB for info | Reached out to LOB for info |  | Yes |  |  | Reached out to LOB Nicole de la Torre for info
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.1 | Routine Transmission – Ground | VM-13 | Routine Ground - Transmission | 21727 | 23798.349 | 2071.349 | Yes | not met |  | Asking LOB Dana Edwards for Split from VM-01
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.2 | Transmission Second Patrol | VM-14 | Transmission Second Patrol | 1000 | 4210.26 | 3210.26 | Yes | meet |  | Asking LOB Dana Edwards for Split from VM-01
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.1.3 | Integrated Vegetation Management | VM-15 | Integrated Vegetation Management - Transmission | 12679 | 963.908 | -11715.092 | Yes | meet |  | Asking LOB Dana Edwards for Split from VM-01
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.1 | Distribution Routine Patrol | VM-16 | Distribution Routine Patrol | 354500 | 235600 | -118900 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.2 | Distribution Second Patrol | VM-17 | Distribution Second Patrol | 87200 | 71300 | -15900 | Yes | meet
Target (Quarterly) | Vegetation Management and Inspection | 8.2.2.2.3 | VM for Operational Mitigations | VM-18 | VM for Operational Mitigations (VMOM) | See Note | See Note |  | Yes |  |  | Initiative 8.2.2.2 for 2023 included only Routine and Second Patrol. VMOM and all the other transitional programs were embedded within Fall-In Mitigation (8.2.3.4).
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-19 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | 18000 | 35300.1363 | 17300.1363 | Yes | meet |  | Since modifications related to VM-19 thru VM-21 were part of a revision process that occurred the second half of 2023, the definitions of spend or tracking mechanisms were not modified accordingly. This focus has really been specific to the start of this year. All that said, for VM-19 & VM-20, there was a minimal amount of time and effort in completing the ask so any costs would be immaterial and already embedded within what has been reported.
Objective | Vegetation Management and Inspection | 8.2.4 | VM Enterprise System | VM-20 | Record Keeping Enhancement (VMOM, TRI) | See Note | See Note |  | Yes |  |  | Since modifications related to VM-19 thru VM-21 were part of a revision process that occurred the second half of 2023, the definitions of spend or tracking mechanisms were not modified accordingly. This focus has really been specific to the start of this year. All that said, for VM-19 & VM-20, there was a minimal amount of time and effort in completing the ask so any costs would be immaterial and already embedded within what has been reported.
Objective | Vegetation Management and Inspection | 8.2.2.2.5 | Focused Tree Inspections | VM-21 | FTI Record Keeping Enhancement | See Note | See Note |  | Yes |  |  | Since modifications related to VM-19 thru VM-21 were part of a revision process that occurred the second half of 2023, the definitions of spend or tracking mechanisms were not modified accordingly. This focus has really been specific to the start of this year. All that said, for VM-19 & VM-20, there was a minimal amount of time and effort in completing the ask so any costs would be immaterial and already embedded within what has been reported.
Target | Vegetation Management and Inspection | 8.2.5.2 | Quality Control | VM-22 | Vegetation Management - Quality Control | 11029.6955 | 34362.5828 | 23332.8873 | Yes | meet
Total | [5 empty] | 2279275.8588 | 2026083.0072 | -253192.8515 |  |  |  | 11
[6 empty] | #VALUE! | #VALUE!
[5 empty] | Total | 2279275.8588 | 2026083.0072 | -253192.8515
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Free text variance explanation where difference between the actual expenditure and planned budget is more than 10% (no dollar threshold)
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OPEX Only
Note on G42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAPEX only
Note on I43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both CAPEX & OPEX
Note on G55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both CAPEX & OPEX Totals
Note on I55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both CAPEX & OPEX
Note on G56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAPEX Only