## Cover Sheet Tables 1-15
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines, Appendix D
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | Liberty Utilities
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2024
Reporting Period quarter |  | Q1 |  | Q1 | 2023
Date Modified |  | 2024-07-25 |  | Q2 | 2024
|  |  |  | Q3 | 2025
Q4

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitiativeObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmailAH:AHAP6AI:AOAE:AOAP6AI:AOAD:AOAP6AI:AOAC:AOAP6AI:AOY:U:AO | Comment
Liberty | 2024-05-01 | Project |  |  | Covered conductor installation |  |  | Grid Design, Operations, and Maintenance | 8.1 | Covered conductor installation |  | 8.1.2.1 | WMP-GDOM-GH-01 |  | 144 |  |  | Circuit Miles | 5.61 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Undergrounding of electric lines and/or equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | WMP-GDOM-GH-02 |  | 149 |  |  | Circuit Miles | 1.25 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Distribution pole replacements and reinforcements |  |  | Grid Design, Operations, and Maintenance | 8.1 | Distribution pole replacements and reinforcements |  | 8.1.2.3 | WMP-GDOM-GH-03 |  | 150 |  |  | Poles | 400 |  |  |  |  | 26 | [8 empty] | In progress
Liberty | 2024-05-01 |  |  |  | Transmission pole/tower replacements and reinforcements |  |  | Grid Design, Operations, and Maintenance | 8.1 | Transmission pole/tower replacements and reinforcements |  | 8.1.2.4 | WMP-GDOM-GH-04 |  | 151 |  |  | - | - |  |  |  |  | - | [8 empty] | -
Liberty | 2024-07-25 | Project |  |  | Traditional overhead hardening |  |  | Grid Design, Operations, and Maintenance | 8.1 | Traditional overhead hardening |  | 8.1.2.5 | WMP-GDOM-GH-05 |  | 151 |  |  | Circuit Miles | 3.5 |  |  |  |  | 3.5 | [8 empty] | In progress | [7 empty] | Revised per the July 1, 2024 Energy Safety Decision on Liberty's 2024 Change Order Request
Liberty | 2024-05-01 | Pilot |  |  | Emerging grid hardening technology installations and pilot progress |  |  | Grid Design, Operations, and Maintenance | 8.1 | Emerging grid hardening technology installations and pilot progress |  | 8.1.2.6 | WMP-GDOM-GH-06 |  | 152 |  |  | - | 1 |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Microgrids |  |  | Grid Design, Operations, and Maintenance | 8.1 | Microgrids |  | 8.1.2.7 | WMP-GDOM-GH-07 |  | 154 |  |  | Microgrids | 1 |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Installation of system automation equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Installation of system automation equipment |  | 8.1.2.8 | WMP-GDOM-GH-08 |  | 155 |  |  | Automatic Reclosers | 8 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Line removal (in HFTD) |  |  | Grid Design, Operations, and Maintenance | 8.1 | Line removal (in HFTD) |  | 8.1.2.9 | WMP-GDOM-GH-09 |  | 156 |  |  | Circuit Miles | 1.1 |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 |  |  |  | Other grid topology improvements to minimize risk of ignitions |  |  | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | WMP-GDOM-GH-10 |  | 156 |  |  | - | - |  |  |  |  | - | [8 empty] | -
Liberty | 2024-05-01 |  |  |  | Other grid topology improvements to mitigate or reduce PSPS events |  |  | Grid Design, Operations, and Maintenance | 8.1 | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | WMP-GDOM-GH-11 |  | 157 |  |  | - | - |  |  |  |  | - | [8 empty] | -
Liberty | 2024-05-01 |  |  |  | Other technologies and systems not listed above: |  |  | Grid Design, Operations, and Maintenance | 8.1 | Other technologies and systems not listed above: |  | 8.1.2.12 | WMP-GDOM-GH-12 |  | 157 |  |  | - | - |  |  |  |  | - | [8 empty] | -
Liberty | 2024-05-01 | Project |  |  | Tree attachment removals |  |  | Grid Design, Operations, and Maintenance | 8.1 | Tree attachment removals |  | 8.1.2.12 | WMP-GDOM-GH-12a |  | 157 |  |  | Tree Attachments | 60 |  |  |  |  | 2 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Expulsion fuse replacement |  |  | Grid Design, Operations, and Maintenance | 8.1 | Expulsion fuse replacement |  | 8.1.2.12 | WMP-GDOM-GH-12b |  | 157 |  |  | Expulsion Fuses | 500 |  |  |  |  | 8 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Animal guards |  |  | Grid Design, Operations, and Maintenance | 8.1 | Animal guards |  | 8.1.2.12 | WMP-GDOM-GH-12c |  | 157 |  |  | Animal Guards | 2 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | CalFIRE exempt hardware |  |  | Grid Design, Operations, and Maintenance | 8.1 | CalFIRE exempt hardware |  | 8.1.2.12 | WMP-GDOM-GH-12d |  | 157 |  |  | CalFIRE Exempt Hardware | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Open wire/grey wire |  |  | Grid Design, Operations, and Maintenance | 8.1 | Open wire/grey wire |  | 8.1.2.12 | WMP-GDOM-GH-12e |  | 157 |  |  | Circuit Miles | 5.096 |  |  |  |  | 0.41 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Substation Equipment Replacement |  |  | Grid Design, Operations, and Maintenance | 8.1 | Substation Equipment Replacement |  | 8.1.2.12 | WMP-GDOM-GH-12f |  | 157 |  |  | Substations | 1 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Detailed inspections of distribution electric lines and equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Detailed inspections of distribution electric lines and equipment |  | 8.1.3.1 | WMP-GDOM-AI-01 |  | 164 |  |  | Circuit Miles | 264.2 |  |  |  |  | 102.2 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Intrusive pole inspections |  |  | Grid Design, Operations, and Maintenance | 8.1 | Intrusive pole inspections |  | 8.1.3.2 | WMP-GDOM-AI-02 |  | 164 |  |  | Poles | 2302 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Patrol inspections of distribution electric lines and equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Patrol inspections of distribution electric lines and equipment |  | 8.1.3.3 | WMP-GDOM-AI-03 |  | 165 |  |  | Circuit Miles | 589 |  |  |  |  | 394 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Other discretionary inspections of distribution electric lines and equipment |  |  | Grid Design, Operations, and Maintenance | 8.1 | Other discretionary inspections of distribution electric lines and equipment |  | 8.1.3.4 | WMP-GDOM-AI-04 |  | 165 |  |  | Circuit Miles | 1 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Quality assurance / quality control of inspections |  |  | Grid Design, Operations, and Maintenance | 8.1 | Quality assurance / quality control of inspections |  | 8.1.3.5 | WMP-GDOM-AI-05 |  | 166 |  |  | % of Detailed Inspections | 2% |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Substation inspections |  |  | Grid Design, Operations, and Maintenance | 8.1 | Substation inspections |  | 8.1.3.6 | WMP-GDOM-AI-06 |  | 166 |  |  | Substations | 42 |  |  |  |  | 20 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Equipment maintenance and repair |  |  | Grid Design, Operations, and Maintenance | 8.1 | Equipment maintenance and repair |  | 8.1.4 | WMP-GDOM-MR-01 |  | 166 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-07-25 | Project |  |  | Equipment settings to reduce wildfire risk |  |  | Grid Design, Operations, and Maintenance | 8.1 | Equipment settings to reduce wildfire risk |  | 8.1.8.1 | WMP-GDOM-GO-01 |  | 174 |  |  | # of circuits with SRP | 15 |  |  |  |  | 0 | [8 empty] | In progress | [7 empty] | Revised per the July 1, 2024 Energy Safety Decision on Liberty's 2024 Change Order Request
Liberty | 2024-05-01 | Program |  |  | Grid response procedures and notifications |  |  | Grid Design, Operations, and Maintenance | 8.1 | Grid response procedures and notifications |  | 8.1.8.2 | WMP-GDOM-GO-02 |  | 176 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Personnel work procedures and training in conditions of elevated fire risk |  |  | Grid Design, Operations, and Maintenance | 8.1 | Personnel work procedures and training in conditions of elevated fire risk |  | 8.1.8.3 | WMP-GDOM-GO-03 |  | 177 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Automatic recloser operations |  |  | Grid Design, Operations, and Maintenance | 8.1 | Automatic recloser operations |  | 8.1.8.1 | WMP-GDOM-GO-04 |  | 174 |  |  | - | - |  |  |  |  | - | [8 empty] | -
Liberty | 2024-05-01 | Project |  |  | Asset Management and Inspection Enterprise System |  |  | Grid Design, Operations, and Maintenance | 8.1 | Asset Management and Inspection Enterprise System |  | 8.1.5 | WMP-GDOM-GO-05 |  | 169 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Vegetation Management Inspection Program - Detailed |  |  | Vegetation Management & Inspections | 8.2 | Vegetation Management Inspection Program - Detailed |  | 8.2.2.1 | WMP-VM-INSP-01 |  | 193 |  |  | Line Miles | 220 |  |  |  |  | 80.2 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Vegetation Management Inspection Program - Patrol |  |  | Vegetation Management & Inspections | 8.2 | Vegetation Management Inspection Program - Patrol |  | 8.2.2.2 | WMP-VM-INSP-02 |  | 193 |  |  | Line Miles | - |  |  |  |  | 57 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Vegetation Management Inspection Program - LiDar |  |  | Vegetation Management & Inspections | 8.2 | Vegetation Management Inspection Program - LiDar |  | 8.2.2.3 | WMP-VM-INSP-03 |  | 193 |  |  | Line Miles | 700 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Pole Clearing |  |  | Vegetation Management & Inspections | 8.2 | Pole Clearing |  | 8.2.3.1 | WMP-VM-VFM-01 |  | 205 |  |  | Subject Poles | 4960 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Wood and Slash Management |  |  | Vegetation Management & Inspections | 8.2 | Wood and Slash Management |  | 8.2.3.2 | WMP-VM-VFM-02 |  | 205 |  |  | Acres | 280 |  |  |  |  | 13.5 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Substation Defensible Space |  |  | Vegetation Management & Inspections | 8.2 | Substation Defensible Space |  | 8.2.3.5 | WMP-VM-VFM-03 |  | 213 |  |  | Substation Treatments | - |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Fire-Resilient Right-of-Ways |  |  | Vegetation Management & Inspections | 8.2 | Fire-Resilient Right-of-Ways |  | 8.2.3.7 | WMP-VM-VFM-04 |  | 214 |  |  | Line Miles | - |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Clearance |  |  | Vegetation Management & Inspections | 8.2 | Clearance |  | 8.2.3.3 | WMP-VM-VFM-05 |  | 207 |  |  | Line Miles | - |  |  |  |  | 208.2 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Fall-In Mitigation |  |  | Vegetation Management & Inspections | 8.2 | Fall-In Mitigation |  | 8.2.3.4 | WMP-VM-VFM-06 |  | 209 |  |  | Line Miles | 220 |  |  |  |  | 31.2 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | High-Risk Species |  |  | Vegetation Management & Inspections | 8.2 | High-Risk Species |  | 8.2.3.6 | WMP-VM-VFM-07 |  | 214 |  |  | - | - |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Emergency Response Vegetation Management |  |  | Vegetation Management & Inspections | 8.2 | Emergency Response Vegetation Management |  | 8.2.3.8 | WMP-VM-VFM-08 |  | 215 |  |  | - | - |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Vegetation Management Enterprise System |  |  | Vegetation Management & Inspections | 8.2 | Vegetation Management Enterprise System |  | 8.2.4 | WMP-VM-ESG-01 |  | 217 |  |  | - | - |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Quality Assurance and Quality Control |  |  | Vegetation Management & Inspections | 8.2 | Quality Assurance and Quality Control |  | 8.2.5 | WMP-VM-QAQC-01 |  | 222 |  |  | Line Miles | 229 |  |  |  |  | 56.9 | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Environmental monitoring systems |  |  | Situational Awareness & Forecasting | 8.3 | Environmental monitoring systems |  | 8.3.2 | WMP-SA-01 |  | 242 |  |  | Weather Stations | 0 |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Grid monitoring systems |  |  | Situational Awareness & Forecasting | 8.3 | Grid monitoring systems |  | 8.3.3 | WMP-SA-02 |  | 246 |  |  | Circuits with Fault Indicators | 10 |  |  |  |  | 0 | [8 empty] | In progress
Liberty | 2024-05-01 | Pilot |  |  | Fire detection and alarm systems |  |  | Situational Awareness & Forecasting | 8.3 | Fire detection and alarm systems |  | 8.3.4 | WMP-SA-03 |  | 249 |  |  | DFA Units | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Weather forecasting |  |  | Situational Awareness & Forecasting | 8.3 | Weather forecasting |  | 8.3.5 | WMP-SA-04 |  | 253 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Fire Potential Index |  |  | Situational Awareness & Forecasting | 8.3 | Fire Potential Index |  | 8.3.6 | WMP-SA-05 |  | 258 |  |  | - | - |  |  |  |  | - | [8 empty] | Completed
Liberty | 2024-05-01 | Project |  |  | Ignition likelihood calculation |  |  | Situational Awareness & Forecasting | 6.2 | Ignition likelihood calculation |  | 6.2.2.1 | WMP-SA-06 |  | 73 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Project |  |  | Ignition consequence calculation |  |  | Situational Awareness & Forecasting | 6.2 | Ignition consequence calculation |  | 6.2.2.2 | WMP-SA-07 |  | 75 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Wildfire and PSPS emergency preparedness plan |  |  | Emergency Preparedness | 8.4 | Wildfire and PSPS emergency preparedness plan |  | 8.4.2 | WMP-EP-01 |  | 268 |  |  | - | - |  |  |  |  | - | [8 empty] | Completed
Liberty | 2024-05-01 | Program |  |  | Collaboration and coordination with public safety partners |  |  | Emergency Preparedness | 8.4 | Collaboration and coordination with public safety partners |  | 8.4.3 | WMP-EP-02 |  | 287 |  |  | - | - |  |  |  |  | - |  |  |  | Continued engagement with local stakeholders and PSPs to prepare for and respond to fire-related event; Meet with Community Advisory Boards | Engaged with stakeholders through participation in 11 community councils and working group meetings |  |  |  | In progress
Liberty | 2024-05-01 | Program |  |  | Public notification and communication strategy |  |  | Emergency Preparedness | 8.4 | Public notification and communication strategy |  | 8.4.4 | WMP-EP-03 |  | 305 |  |  | - | - |  |  |  |  | - |  |  |  | - | - |  |  |  | Completed
Liberty | 2024-05-01 | Program |  |  | Preparedness and planning for service restoration |  |  | Emergency Preparedness | 8.4 | Preparedness and planning for service restoration |  | 8.4.5 | WMP-EP-04 |  | 314 |  |  | - | - |  |  |  |  | - |  |  |  | - | - |  |  |  | Completed
Liberty | 2024-05-01 | Program |  |  | Customer support in wildfire and PSPS emergencies |  |  | Emergency Preparedness | 8.4 | Customer support in wildfire and PSPS emergencies |  | 8.4.6 | WMP-EP-05 |  | 319 |  |  | - | - |  |  |  |  | - |  |  |  | Conduct annual Incident Command training for all identified IC members. Hold Tabletop (1) and Functional (1) PSPS Exercises. Continue to implement Liberty’s AFN Plan. Continue maintenance of emergency response plans. Update plans and procedures based on feedback and lessons learned from stakeholders and After Action Reports (AARs). | PSPS exercise planning meetings took place on 4/4/2024 and 4/25/2024. Liberty's 2024 PSPS tabletop exercise is scheduled for 5/23/2024, and its functional exercise is scheduled for 6/27/2024. |  |  |  | In progress
Liberty | 2024-05-01 |  |  |  | Learning after wildfire and PSPS events |  |  | Emergency Preparedness | 8.4 | Learning after wildfire and PSPS events |  |  | WMP-EP-06 |  | - |  |  | - | - |  |  |  |  | - |  |  |  | - | - |  |  |  | In progress
Liberty | 2024-05-01 | Program |  |  | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management |  |  | Community Outreach and Engagement | 8.5 | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management |  | 8.5.2 | WMP-CO-01 |  | 329 |  |  | - | - |  |  |  |  | - |  |  |  | Continue to survey customers, CBOs, community partners, and stakeholders to gauge awareness of Liberty assistance programs and of customer needs. Strengthen and expand AFN CBO partnerships. | 8 in-person events, 8 Virtual events, and 16 rounds of emails, website posts, and social media posts focused on PSPS education and wildfire awareness, AFN outreach and CBO collaboration. 4 sets of direct mail & bill inserts and sets of print and digital ads focused on customer and stakeholder outreach |  |  |  | In progress
Liberty | 2024-05-01 |  |  |  | Public engagement in WMP decision-making process |  |  | Community Outreach and Engagement | 8.5 | Public engagement in WMP decision-making process |  |  | WMP-CO-02 |  | - |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Engagement with AFN populations, local governments, and tribal communities |  |  | Community Outreach and Engagement | 8.5 | Engagement with AFN populations, local governments, and tribal communities |  | 8.5.3 | WMP-CO-03 |  | 335 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 | Program |  |  | Collaboration on local wildfire mitigation and planning |  |  | Community Outreach and Engagement | 8.5 | Collaboration on local wildfire mitigation and planning |  | 8.5.4 | WMP-CO-04 |  | 337 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Liberty | 2024-05-01 |  |  |  | Best practice sharing with other electrical corporations |  |  | Community Outreach and Engagement | 8.5 | Best practice sharing with other electrical corporations |  | 8.5.5 | WMP-CO-05 |  | 341 |  |  | - | - |  |  |  |  | - | [8 empty] | In progress
Note on C2: Author: Select cells for dropdown list.

## Table 2
| Utility | Liberty Utilities | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-05-01 | HWW = High wind warning
RFW = Red flag warning
[10 empty] | Actuals | Projected
| Table 2: Performance Metrics | [8 empty] | Q1
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 95 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 1 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 5 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | 15 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 15 |  |  |  | Number of events
|  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | 1 |  |  |  | Number of events
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 98 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 1 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 8 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 16 |  |  |  | Number of events
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 26 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 1 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 5 |  |  |  | Number of events
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 1.5 | 1.5 | 1.5 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0.25 | 0.25 | 0.25 | Number of events
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 768 |  |  |  | hours
|  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 1728 |  |  |  | hours
|  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 1668 |  |  |  | hours
|  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 3168 |  |  |  | hours
|  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 1416 |  |  |  | hours
|  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 1857 |  |  |  | hours
|  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 1248 |  |  |  | hours
|  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 1248 |  |  |  | hours
|  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 16272 |  |  |  | hours
|  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 30984 |  |  |  | hours
|  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 30264 |  |  |  | hours
|  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 30977 |  |  |  | hours
|  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 24216 |  |  |  | hours
|  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 30696 |  |  |  | hours
|  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 30624 |  |  |  | hours
|  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 30835 |  |  |  | hours
|  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 17640 |  |  |  | hours
|  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 17640 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 30528 |  |  |  | hours
|  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 31826 |  |  |  | hours
|  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 29544 |  |  |  | hours
|  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 31337 |  |  |  | hours
|  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 30696 |  |  |  | hours
|  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 30696 |  |  |  | hours
|  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 30672 |  |  |  | hours
|  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 30672 |  |  |  | hours
|  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 1691 | 4881 | 4881 | 4881 | Number of orders
|  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 11 |  |  |  | Number of orders
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 9772 | 8500 | 6700 | 5960 | Number of orders
|  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 658 | 107.75 | 25 | 25 | Number of orders
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Hours
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of fatalities
|  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of injuries
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | 1000
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of structures
|  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of structures
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Acres
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 21 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 2614 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 393.5 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 73.18 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 15 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 136 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 4 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 538 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 809 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 17.34 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 44 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 4 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 74 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 1 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 549 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 11.69 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 27 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 140 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 127 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 100 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 15 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 15 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 3 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 3 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 12 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 2 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 7 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
x | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 938 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 80 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 8 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 93 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 3 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other | 31 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 4 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 10 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | 1 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | 0 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection.
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Percentage of customers notified of evacuation

## Table 3
Utility | Liberty Utilities
Table No. | 3
Date Modified
[5 empty] | Actual | Projected
Table 3: List and description of additional metrics |  |  |  |  | Q1
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning

## Table 4
Utility | Liberty Utilities
Table No. | 4
Date Modified | 2024-05-01
Table 4: Weather patterns |  |  | Q1
Metric type | # | Metric name | 2024 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 0 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 0 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 428 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 0 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 31 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 428 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 0 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 31 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 0 | Fire potential index overhead circuit mile days, see above for definition
| 4.c. | Fire potential index circuit mile days - non-HFTD | 0 | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed)

## Table 5
| Utility | Liberty Utilities | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-05-01
[8 empty] | Actual number of risk events | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q1
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.0 | 3rd party contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.0 | Other contact from object | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.2 | Other contact from object | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.0 | Other contact from object | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.2 | Other contact from object | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.0 | Unknown | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 6 | 29 | 29 | 29 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 4 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 4 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 1 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 3 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 5 | 6 | 6 | 6 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 26 | 92 | 92 | 92 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 1 | 11 | 11 | 11 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 10 | 26 | 26 | 26 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 3 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 4 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 1 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 3 | 15 | 15 | 15 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 2 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 1 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 1 | 8 | 8 | 8 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 3 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 2 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 10 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 61 | 81 | 81 | 81 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 5 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 | Yes | 0 | 8 | 8 | 8 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 13 | 13 | 13 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 4 | 76 | 76 | 76 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | 3 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 | Yes |  |  |  |  | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 | Yes |  |  |  |  | # risk events (excluding ignitions)

## Table 6
| Utility | Liberty Utilities | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-05-01
[7 empty] | Actual number of ignitions | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q1
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 0 | 0.66667 | 0.66667 | 0.66667 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0.33333 | 0.33333 | 0.33333 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions

## Table 7
| Utility | Liberty Utilities
| Table No. | 7
| Date Modified | 2024-05-01
[7 empty] | Actual | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q1
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 4.6 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 1.04 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 12.57 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 5.38 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 52.16 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 15.95 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 305.15 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 17.89 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 577.63 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 162.1 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 112.41 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 72.13 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0.03 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 108.03 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 15.63 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 1.46 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0.39 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0.1 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0.16 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | - |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | - |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 1.57 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0.18 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 5.69 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 20.68 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | - |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0.29 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | - |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0.03 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 2.32 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Circuit miles
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 21.73 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 1.05 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 3.36 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 1.52 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 8.7 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 1.85 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 103.07 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 11.64 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 294.38 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 76.64 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 34.44 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 10.4 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | - |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 8.76 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 1.46 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | - |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | - |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | - |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | - |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | - |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | - |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0.06 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | - |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 1.09 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0.15 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | - |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | - |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | - |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | - |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | - |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Circuit miles
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 16 |  |  |  | Number of critical facilities
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | - |  |  |  | Number of critical facilities
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 13 |  |  |  | Number of critical facilities
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 2 |  |  |  | Number of critical facilities
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 74 |  |  |  | Number of critical facilities
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 13 |  |  |  | Number of critical facilities
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 347 |  |  |  | Number of critical facilities
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 54 |  |  |  | Number of critical facilities
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 260 |  |  |  | Number of critical facilities
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 58 |  |  |  | Number of critical facilities
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 50 |  |  |  | Number of critical facilities
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 25 |  |  |  | Number of critical facilities
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | - |  |  |  | Number of critical facilities
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Number of critical facilities
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 60 |  |  |  | Number of critical facilities
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 3 |  |  |  | Number of critical facilities
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Number of critical facilities
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Number of critical facilities
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 1011 |  |  |  | Number of residential customers
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 17 |  |  |  | Number of residential customers
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 372 |  |  |  | Number of residential customers
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 19 |  |  |  | Number of residential customers
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 1509 |  |  |  | Number of residential customers
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 39 |  |  |  | Number of residential customers
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 14420 |  |  |  | Number of residential customers
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 39 |  |  |  | Number of residential customers
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 20107 |  |  |  | Number of residential customers
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 1059 |  |  |  | Number of residential customers
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 1783 |  |  |  | Number of residential customers
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 217 |  |  |  | Number of residential customers
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 1 |  |  |  | Number of residential customers
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Number of residential customers
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 2817 |  |  |  | Number of residential customers
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 145 |  |  |  | Number of residential customers
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Number of residential customers
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Number of residential customers
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | 110 |  |  |  | Number of commercial customers
|  | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 13 |  |  |  | Number of commercial customers
|  | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | 79 |  |  |  | Number of commercial customers
|  | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 98 |  |  |  | Number of commercial customers
|  | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 242 |  |  |  | Number of commercial customers
|  | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 93 |  |  |  | Number of commercial customers
|  | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 2042 |  |  |  | Number of commercial customers
|  | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 267 |  |  |  | Number of commercial customers
|  | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 1628 |  |  |  | Number of commercial customers
|  | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 364 |  |  |  | Number of commercial customers
|  | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 162 |  |  |  | Number of commercial customers
|  | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 94 |  |  |  | Number of commercial customers
|  | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | - |  |  |  | Number of commercial customers
|  | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Number of commercial customers
|  | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 55 |  |  |  | Number of commercial customers
|  | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 6 |  |  |  | Number of commercial customers
|  | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Number of commercial customers
|  | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Number of commercial customers
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | 164 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 6 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | 80 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 12 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 610 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 24 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 3674 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 8 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 2947 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 176 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 532 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 77 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | - |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 475 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 27 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Number of customers belonging to access and functional needs populations
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | - |  |  |  | Number of substations
|  | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | - |  |  |  | Number of substations
|  | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | - |  |  |  | Number of substations
|  | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | - |  |  |  | Number of substations
|  | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 1 |  |  |  | Number of substations
|  | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 1 |  |  |  | Number of substations
|  | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 2 |  |  |  | Number of substations
|  | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | - |  |  |  | Number of substations
|  | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 4 |  |  |  | Number of substations
|  | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 1 |  |  |  | Number of substations
|  | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 1 |  |  |  | Number of substations
|  | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 1 |  |  |  | Number of substations
|  | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | - |  |  |  | Number of substations
|  | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | - |  |  |  | Number of substations
|  | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 1 |  |  |  | Number of substations
|  | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | - |  |  |  | Number of substations
|  | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | - |  |  |  | Number of substations
|  | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | - |  |  |  | Number of substations
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 |  |  |  | Number of weather stations
|  | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 1 |  |  |  | Number of weather stations
|  | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 3 |  |  |  | Number of weather stations
|  | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 2 |  |  |  | Number of weather stations
|  | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 8 |  |  |  | Number of weather stations
|  | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 11 |  |  |  | Number of weather stations
|  | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 5 |  |  |  | Number of weather stations
|  | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 7 |  |  |  | Number of weather stations
|  | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Number of weather stations
|  | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 1 |  |  |  | Number of weather stations
|  | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of weather stations
|  | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of weather stations

## Table 8
| Utility | Liberty Utilities |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2024-05-01 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q1
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0.01 | - | - | - | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 0.01 | - | - | - | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 0.01 | - | - | - | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0.01 | - | - | - | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | -0.08 | - | - | - | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | -0.04 | - | - | - | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | -0.21 | - | -0.39 | - | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | - | -0.02 | - | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | -1.12 | -2.88 | - | - | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | -0.09 | -0.01 | - | - | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | -0.04 | - | - | - | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 0.01 | - | - | - | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0.01 | - | - | - | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | -0.01 | - | - | - | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0.01 | - | - | - | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0.02 | - | - | - | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | -0.01 | - | - | - | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0.01 | - | - | - | Circuit miles
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | -0.03 | - | 0.39 | - | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0.12 | - | 0.02 | - | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | -0.35 | 2.88 | - | - | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | -0.2 | 0.01 | - | - | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 | - | - | - | Number of substations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Number of substations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | - | - | - | Number of substations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Number of substations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | - | - | - | Number of substations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | - | - | - | Number of substations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | - | - | - | Number of substations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | - | - | - | Number of substations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Number of substations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Number of substations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Number of substations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Number of substations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Number of substations
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 | - | - | - | Number of weather stations
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | - | - | - | Number of weather stations
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Number of weather stations
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | - | - | - | Number of weather stations
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | - | - | - | Number of weather stations
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | - | - | - | Number of weather stations
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Number of weather stations
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Number of weather stations
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Number of weather stations
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Number of weather stations

## Table 9
| Utility | Liberty Utilities
| Table No. | 9
| Date Modified | 2024-05-01
[7 empty] | Actual | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q1
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | - | 0.36 | - | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 0 | 2.58 | 5.09 | 2.21 | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 0 | 0.03 | 0.09 | 1.81 | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 0.18 | 1.45 | 3.04 | - | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 3.45 | 6.27 | 0.26 | - | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Circuit miles
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI |  | 1 | - | - | Number of substations
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Number of substations
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | - | - | - | Number of substations
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Number of substations
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 1 | - | - | Number of substations
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | - | - | - | Number of substations
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 2 | - | - | Number of substations
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | - | - | - | Number of substations
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Number of substations
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | - | - | Number of substations
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Number of substations
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Number of substations
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Number of substations
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Number of substations
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 | - | - | - | Number of weather stations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | - | - | - | Number of weather stations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | - | - | - | Number of weather stations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | - | - | - | Number of weather stations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | - | - | - | Number of weather stations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | - | - | - | Number of weather stations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | - | - | - | Number of weather stations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | - | - | - | Number of weather stations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | - | - | - | Number of weather stations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | - | - | - | Number of weather stations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | - | - | - | Number of weather stations

## Table 10
Utility | Liberty Utilities |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2024-05-01 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q1
Metric type | # | Wind Warning Status | Metric name | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW only | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW & RFW | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | All (regardless of RFW/HWW status) | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.b. | RFW only | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW only | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW & RFW | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | All (regardless of RFW/HWW status) | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
| 1.c. | RFW only | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW only | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW & RFW | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
|  | All (regardless of RFW/HWW status) | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
| 1.d. | RFW only | Frequency of fast-trip events (total) | 0 |  |  |  | Number of events
|  | HWW only | Frequency of fast-trip events (total) | 0 |  |  |  | Number of events
|  | HWW & RFW | Frequency of fast-trip events (total) | 0 |  |  |  | Number of events
|  | None | Frequency of fast-trip events (total) | 0 |  |  |  | Number of events
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | 0 |  |  |  | Circuit mile days
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | 0 |  |  |  | Circuit mile days
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | 0 |  |  |  | Circuit mile days
|  | None | Circuit mile days with fast-trip settings enabled (total) | 0 |  |  |  | Circuit mile days
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | 12322.58 |  |  |  | Total customer hours of planned outages per year
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | 149977.55 |  |  |  | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip |  |  |  |  | Total customer hours of outages due to fast-trip per year
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | 181.82 |  |  |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | 181.82 |  |  |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | 0.9312 |  |  |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | 0.9312 |  |  |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | 0 |  |  |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | 0 | 0 | 0 | 0 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
4. Community outreach of PSPS metrics | 4.b. | N/A | # of medical baseline customers impacted by PSPS | 0 |  |  |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
4. Community outreach of PSPS metrics | 4.c. | N/A | # of customers notified prior to initiation of PSPS event | 0 |  |  |  | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | 0 |  |  |  | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | 0 |  |  |  | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | 0 |  |  |  | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | 0 |  |  |  | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | 0 |  |  |  | Number of customers
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | 0 |  |  |  | =1.c. / RFW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | 0 |  |  |  | =1.c. / HWW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | 0 |  |  |  | =1.c. / FPI OH circuit mile days in time period
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | 0 |  |  |  | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | 0 |  |  |  | Number of risk events

## Table 11
Utility | Liberty Utilities | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2024-07-25 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actuals |  |  |  | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2024 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Grid Design, Operations, and Maintenance | Covered conductor installation | WMP-GDOM-GH-01 | Other contact with object | Equipment failure | 2019 | 2021 WMP | NA | In compliance | NA | NA | [5 empty] | 3284.76 | 3284.76 |  |  | 8627.427 | 8627.427 |  |  | 7640.2 | 7640.2
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | WMP-GDOM-GH-02 | Other contact with object | Equipment failure |  | 2020 WMP | NA | Exceeds | NA | NA | [5 empty] | 7692.65 | 7692.65 |  |  | 8482.68 | 8482.68 |  |  | 9100 | 9100
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | WMP-GDOM-GH-03 | Equipment failure |  | 2011 | 2021 WMP | NA | In compliance | GO 165 | NA | [5 empty] | 10970.194 | 10970.194 |  |  | 7413 | 7413 |  |  | 5000 | 5000
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | WMP-GDOM-GH-04
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP-GDOM-GH-05 | [13 empty] | 4961.889 | 4961.889 |  |  | 3500 | 3500 |  |  | 2500 | 2500
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilot progress | WMP-GDOM-GH-06 | [13 empty] | 150 | 150 |  |  | 3050 | 3050
Grid Design, Operations, and Maintenance | Microgrids | WMP-GDOM-GH-07 | PSPS - for sectionalization, etc. | Resiliency | 2020 | 2021 WMP | NA | In compliance | R20A | NA | [9 empty] | 1500 | 1500 |  |  | 1000 | 1000
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP-GDOM-GH-08 | PSPS - for sectionalization, etc. |  | 2011 | 2021 WMP | NA | Exceeds | NA | NA | [5 empty] | 1200 | 1200 |  |  | 1200 | 1200 |  |  | 1200 | 1200
Grid Design, Operations, and Maintenance | Line removal (in HFTD) | WMP-GDOM-GH-09 | [17 empty] | 500 | 500
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP-GDOM-GH-10
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP-GDOM-GH-11 | PSPS - for sectionalization, etc. |  | 2020 | 2021 WMP | NA | In compliance | R20A | NA
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above: | WMP-GDOM-GH-12
Grid Design, Operations, and Maintenance | Tree attachment removals | WMP-GDOM-GH-12a | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA | [5 empty] | 701.112 | 701.112 |  |  | 720.392 | 720.392 |  |  | 1101.673 | 1101.673
Grid Design, Operations, and Maintenance | Expulsion fuse replacement | WMP-GDOM-GH-12b | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA | [13 empty] | 2000 | 2000
Grid Design, Operations, and Maintenance | Animal guards / Avian Protection | WMP-GDOM-GH-12c | Equipment failure | Animal contact | 2020 | 2021 WMP | NA | NA | NA | NA | [5 empty] | 40 | 40 |  |  | 100 | 100
Grid Design, Operations, and Maintenance | CalFIRE exempt hardware | WMP-GDOM-GH-12d | Equipment failure | Contact with vegetation | 2020 | 2021 WMP | NA | NA | NA | NA
Grid Design, Operations, and Maintenance | Open wire/grey wire | WMP-GDOM-GH-12e | Equipment failure |  | 2021 | 2021 WMP | NA | NA | NA | NA | [5 empty] | 1000 | 1000 |  |  | 2000 | 2000 |  |  | 3000 | 3000
Grid Design, Operations, and Maintenance | Substation Equipment Replacement | WMP-GDOM-GH-12f | Equipment failure |  |  |  | NA | NA | NA | NA | [13 empty] | 607.584 | 607.584
Grid Design, Operations, and Maintenance | Detailed inspections of distribution electric lines and equipment | WMP-GDOM-AI-01 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO128; GO165 | NA | [7 empty] | 20 | 20 |  |  | 125 | 125 |  |  | 500 | 500
Grid Design, Operations, and Maintenance | Intrusive pole inspections | WMP-GDOM-AI-02 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO165 | NA | [15 empty] | 175 | 175
Grid Design, Operations, and Maintenance | Patrol inspections of distribution electric lines and equipment | WMP-GDOM-AI-03 | Equipment failure | Other contact with object | 2011 | 2019 GRC | NA | In Compliance | GO95; GO165 | NA | [7 empty] | 15 | 15 |  |  | 15 | 15 |  |  | 150 | 150
Grid Design, Operations, and Maintenance | Other discretionary inspections of distribution electric lines and equipment | WMP-GDOM-AI-04 | Equipment failure | Other contact with object | 2020 | 2021 WMP | NA | Exceeds | GO95; GO128; GO165 | NA | [7 empty] | 1000 | 1000 |  |  | 1000 | 1000 |  |  | 150 | 150
Grid Design, Operations, and Maintenance | Quality assurance / quality control of inspections | WMP-GDOM-AI-05 | Equipment failure | Other contact with object | 2021 | NA | NA | In Compliance | GO95; GO128; GO165 | NA | [7 empty] | 10 | 10 |  |  | 10 | 10 |  |  | 30 | 30
Grid Design, Operations, and Maintenance | Substation inspections | WMP-GDOM-AI-06 | Equipment failure | Other contact with object | 2016 | 2019 GRC | NA | In Compliance | GO174 | NA | [7 empty] | 10 | 10 |  |  | 10 | 10 |  |  | 45 | 45
Grid Design, Operations, and Maintenance | Equipment maintenance and repair | WMP-GDOM-MR-01 | Equipment failure |  |  | 2019 GRC | NA | NA | NA | NA | [7 empty] | 500 | 500 |  |  | 500 | 500 |  |  | 500 | 500
Grid Design, Operations, and Maintenance | Equipment settings to reduce wildfire risk | WMP-GDOM-GO-01 | PSPS - for sectionalization, etc. |  | 2021 | NA | NA | NA | NA | NA | [5 empty] | 150 | 150 |  |  | 800 | 800 |  |  | 500 | 500
Grid Design, Operations, and Maintenance | Grid response procedures and notifications | WMP-GDOM-GO-02 | PSPS - for sectionalization, etc. |  | 2021 | NA | NA | In compliance | CPUC D.21-06-034 | NA
Grid Design, Operations, and Maintenance | Personnel work procedures and training in conditions of elevated fire risk | WMP-GDOM-GO-03 | Equipment failure | Other contact with object | 2019 | 2021 WMP | WMPMA | In compliance | NA | NA | [7 empty] | 283.8938 | 283.8938 |  |  | 298.0884 | 298.0884 |  |  | 312.9929 | 312.9929
Grid Design, Operations, and Maintenance | Automatic recloser operations | WMP-GDOM-GO-04 | Contact with vegetation | Equipment failure | 2011 | NA | WMPMA | In compliance | NA | NA
Grid Design, Operations, and Maintenance | Asset Management and Inspection Enterprise System | WMP-GDOM-GO-05
Vegetation Management & Inspections | Vegetation Management Inspection Program - Detailed | WMP-VM-INSP-01 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 789.82 | 789.82 |  |  | 813.5146 | 813.5146 |  |  | 837.92 | 837.92
Vegetation Management & Inspections | Vegetation Management Inspection Program - Patrol | WMP-VM-INSP-02 | Contact with vegetation |  | 2018 | 2019 GRC | NA | NA | NA | NA | [7 empty] | 250 | 250 |  |  | 257.5 | 257.5 |  |  | 265.225 | 265.225
Vegetation Management & Inspections | Vegetation Management Inspection Program - LiDAR | WMP-VM-INSP-03 | Contact with vegetation |  | 2020 | NA | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 700 | 700 |  |  | 721 | 721 |  |  | 742.63 | 742.63
Vegetation Management & Inspections | Pole Clearing | WMP-VM-VFM-01 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 480 | 480 |  |  | 494.4 | 494.4 |  |  | 509.232 | 509.232
Vegetation Management & Inspections | Wood and Slash Management | WMP-VM-VFM-02 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | PRC 4291; PRC 4292 | NA | [7 empty] | 1500 | 1500 |  |  | 1545 | 1545 |  |  | 1591.35 | 1591.35
Vegetation Management & Inspections | Substation Defensible Space | WMP-VM-VFM-03 | [15 empty] | 20 | 20 |  |  | 20.6 | 20.6 |  |  | 21.218 | 21.218
Vegetation Management & Inspections | Fire-Resilient Right-of-Ways | WMP-VM-VFM-04 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 255 | 255 |  |  | 262.65 | 262.65 |  |  | 270.5295 | 270.5295
Vegetation Management & Inspections | Clearance | WMP-VM-VFM-05 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 886.9 | 886.9 |  |  | 913.507 | 913.507 |  |  | 940.9122 | 940.9122
Vegetation Management & Inspections | Fall-In Mitigation | WMP-VM-VFM-06 | Contact with vegetation |  | 2018 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [7 empty] | 7750 | 7750 |  |  | 7982.5 | 7982.5 |  |  | 8221.975 | 8221.975
Vegetation Management & Inspections | High-Risk Species | WMP-VM-VFM-07 | Contact with vegetation |  | 2011 | 2019 GRC | NA | Exceeds | GO 95 Rule 35; PRC 4293 | NA | [15 empty] | 0 | 0
Vegetation Management & Inspections | Emergency Response Vegetation Management | WMP-VM-VFM-08 | Contact with vegetation |  | 2021 | NA | NA | NA | NA | NA | [15 empty] | 0 | 0
Vegetation Management & Inspections | Vegetation Management Enterprise System | WMP-VM-ESG-01 | [15 empty] | 406.005 | 406.005 |  |  | 418.1852 | 418.1852 |  |  | 430.7307 | 430.7307
Vegetation Management & Inspections | Quality Assurance and Quality Control | WMP-VM-QAQC-01 | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | NA | NA | NA | [7 empty] | 500 | 500 |  |  | 515 | 515 |  |  | 530.45 | 530.45
Vegetation Management & Inspections | Vegetation Management - Discretionary Inspections | N/A | Contact with vegetation |  | 2020 | 2021 WMP | WMPMA | Exceeds | GO 95 Rule 35; PRC 4293 | NA
Situational Awareness & Forecasting | Environmental monitoring systems | WMP-SA-01 | PSPS - for sectionalization, etc. |  | 2019 | 2021 WMP | WFMMA | Exceeds | NA | NA | [15 empty] | 50 | 50
Situational Awareness & Forecasting | Grid monitoring systems | WMP-SA-02 | Equipment failure |  | 2020 | 2021 WMP | WFMMA | NA | NA | NA | [5 empty] | 150 | 150 |  |  | 150 | 150 |  |  | 300 | 300
Situational Awareness & Forecasting | Fire detection and alarm systems | WMP-SA-03 | Equipment failure |  | 2022 | NA | NA | NA | NA | NA
Situational Awareness & Forecasting | Weather forecasting | WMP-SA-04
Situational Awareness & Forecasting | Fire Potential Index | WMP-SA-05 | PSPS - for sectionalization, etc. |  | 2020 | 2021 WMP | WFMMA | Exceeds | NA | NA
Situational Awareness & Forecasting | Ignition likelihood calculation | WMP-SA-06 | Contact with vegetation | Equipment failure | 2020 | 2021 WMP | WMPMA | NA | NA | NA | [7 empty] | 1154.34 | 1154.34 |  |  | 683.807 | 683.807 |  |  | 806 | 806
Situational Awareness & Forecasting | Ignition consequence calculation | WMP-SA-07 | Contact with vegetation | Equipment failure | 2020 | 2021 WMP | WMPMA | NA | NA | NA
Emergency Preparedness | Wildfire and PSPS emergency preparedness plan | WMP-EP-01 |  |  | 2011 | GO 166 | NA | In compliance | GO 166 | NA | [13 empty] | 35 | 35
Emergency Preparedness | Collaboration and coordination with public safety partners | WMP-EP-02 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Emergency Preparedness | Public notification and communication strategy | WMP-EP-03 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Emergency Preparedness | Preparedness and planning for service restoration | WMP-EP-04 | PSPS - for sectionalization, etc. | Equipment failure | 2011 | GO 166 | NA | In compliance | GO 166 | NA | [7 empty] | 1369.2709 | 1369.2709 |  |  | 1437.7345 | 1437.7345 |  |  | 1509.6212 | 1509.6212
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | WMP-EP-05 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA | [7 empty] | 100 | 100 |  |  | 105 | 105 |  |  | 110 | 110
Emergency Preparedness | Learning after wildfire and PSPS events | WMP-EP-06 |  |  | 2011 | GO 166 | NA | In compliance | GO 166 | NA
Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | WMP-CO-01 |  |  | 2019 | 2021 WMP | WMPMA | Exceeds | P.U. Code § 451 | NA | [7 empty] | 90 | 90 |  |  | 90 | 90 |  |  | 90 | 90
Community Outreach and Engagement | Public engagement in WMP decision-making process | WMP-CO-02
Community Outreach and Engagement | Engagement with AFN populations, local governments, and tribal communities | WMP-CO-03 |  |  | 2011 | 2021 WMP | WMPMA | In compliance | NA | NA
Community Outreach and Engagement | Collaboration on local wildfire mitigation and planning | WMP-CO-04 |  |  |  | 2021 WMP | NA | NA | NA | NA
Community Outreach and Engagement | Best practice sharing with other electrical corporations | WMP-CO-05

## Table 12
Utility | Liberty Utilities | Notes:
Table No. | 12
Date Modified | 2024-07-25
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | Method of Verification | Comments
Grid Design, Operations, and Maintenance | Covered conductor installation | WMP-GDOM-GH-01 | Quantitative | Circuit Miles | 0 | 0 | 5.72 |  |  | 5.61 |  |  | 2.68
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | WMP-GDOM-GH-02 | Quantitative | Circuit Miles | 0 | 0.12 | 1.37 |  |  | 1.25 |  |  | 1.25
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | WMP-GDOM-GH-03 | Quantitative | Poles | 0 | 125 | 200 |  |  | 400 |  |  | 400
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | WMP-GDOM-GH-04 |  | - | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Traditional overhead hardening | WMP-GDOM-GH-05 | Quantitative | Circuit Miles | 0 | 2 | 4 |  |  | 3.5 |  |  | 2 |  | Revised per the July 1, 2024 Energy Safety Decision on Liberty's 2024 Change Order Request
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilot progress | WMP-GDOM-GH-06 |  | - | - | - | - |  |  | 1 |  |  | -
Grid Design, Operations, and Maintenance | Microgrids | WMP-GDOM-GH-07 | Quantitative | Microgrids | - | - | - |  |  | 1 |  |  | TBD
Grid Design, Operations, and Maintenance | Installation of system automation equipment | WMP-GDOM-GH-08 | Quantitative | Automatic Reclosers | 0 | 4 | 8 |  |  | 8 |  |  | 4
Grid Design, Operations, and Maintenance | Line removal (in HFTD) | WMP-GDOM-GH-09 | Quantitative | Circuit Miles | - | - | - |  |  | 1.1 |  |  | TBD
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | WMP-GDOM-GH-10 |  | - | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | WMP-GDOM-GH-11 |  | - | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above: | WMP-GDOM-GH-12 |  | - | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Tree attachment removals | WMP-GDOM-GH-12a | Quantitative | Tree Attachments | 15 | 30 | 60 |  |  | 60 |  |  | 60
Grid Design, Operations, and Maintenance | Expulsion fuse replacement | WMP-GDOM-GH-12b | Quantitative | Expulsion Fuses | - | - | 3800 |  |  | 500 |  |  | TBD
Grid Design, Operations, and Maintenance | Animal guards | WMP-GDOM-GH-12c | Quantitative | Animal Guards | 1 | 3 | 4 |  |  | 2 |  |  | 0
Grid Design, Operations, and Maintenance | CalFIRE exempt hardware | WMP-GDOM-GH-12d | Quantitative | CalFIRE Exempt Hardware | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Open wire/grey wire | WMP-GDOM-GH-12e | Quantitative | Circuit Miles | 0 | 0 | 2.548 |  |  | 5.096 |  |  | 5.2362
Grid Design, Operations, and Maintenance | Substation Equipment Replacement | WMP-GDOM-GH-12f | Quantitative | TBD | - | - | TBD |  |  | 1 |  |  | TBD
Grid Design, Operations, and Maintenance | Detailed inspections of distribution electric lines and equipment | WMP-GDOM-AI-01 | Quantitative | Circuit Miles | 0 | 0 | 40.3 |  |  | 264.2 |  |  | 260.9
Grid Design, Operations, and Maintenance | Intrusive pole inspections | WMP-GDOM-AI-02 | Quantitative | Poles | 0 | 1500 | 2867 |  |  | 2302 |  |  | 2411
Grid Design, Operations, and Maintenance | Patrol inspections of distribution electric lines and equipment | WMP-GDOM-AI-03 | Quantitative | Circuit Miles | 0 | 701.5 | 701.5 |  |  | 589 |  |  | 540.9
Grid Design, Operations, and Maintenance | Other discretionary inspections of distribution electric lines and equipment | WMP-GDOM-AI-04 | Quantitative | Circuit Miles | - | - | TBD |  |  | 1 |  |  | TBD
Grid Design, Operations, and Maintenance | Quality assurance / quality control of inspections | WMP-GDOM-AI-05 | Quantitative | % of Detailed Inspections | 0 | 0 | 0.01 |  |  | 0.02 |  |  | 0.03
Grid Design, Operations, and Maintenance | Substation inspections | WMP-GDOM-AI-06 | Quantitative | Substations | 24 | 38 | 42 |  |  | 42 |  |  | 42
Grid Design, Operations, and Maintenance | Equipment maintenance and repair | WMP-GDOM-MR-01 |  | - | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Equipment settings to reduce wildfire risk | WMP-GDOM-GO-01 | Quantitative | # of circuits with SRP | - | - | - |  |  | 15 |  |  | - |  | Revised per the July 1, 2024 Energy Safety Decision on Liberty's 2024 Change Order Request
Grid Design, Operations, and Maintenance | Grid response procedures and notifications | WMP-GDOM-GO-02 |  | - | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Personnel work procedures and training in conditions of elevated fire risk | WMP-GDOM-GO-03 |  | - | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Automatic recloser operations | WMP-GDOM-GO-04 |  | - | - | - | - |  |  | - |  |  | -
Grid Design, Operations, and Maintenance | Asset Management and Inspection Enterprise System | WMP-GDOM-GO-05 |  | - | - | - | - |  |  | - |  |  | -
Vegetation Management & Inspections | Vegetation Management Inspection Program - Detailed | WMP-VM-INSP-01 | Quantitative | Line Miles | 88 | 151 | 220 |  |  | 220 |  |  | 220
Vegetation Management & Inspections | Vegetation Management Inspection Program - Patrol | WMP-VM-INSP-02 | Quantitative | Line Miles | - | - | - |  |  | - |  |  | -
Vegetation Management & Inspections | Vegetation Management Inspection Program - LiDar | WMP-VM-INSP-03 | Quantitative | Line Miles | 0 | 700 | 700 |  |  | 700 |  |  | 700
Vegetation Management & Inspections | Pole Clearing | WMP-VM-VFM-01 | Quantitative | Line Miles | 900 | 4060 | 4900 |  |  | 4960 |  |  | 4960
Vegetation Management & Inspections | Wood and Slash Management | WMP-VM-VFM-02 | Quantitative | Acres | 93 | 93 | 280 |  |  | 280 |  |  | 280
Vegetation Management & Inspections | Substation Defensible Space | WMP-VM-VFM-03 |  | - | 0 | 0 | 12 |  |  | - |  |  | -
Vegetation Management & Inspections | Fire-Resilient Right-of-Ways | WMP-VM-VFM-04 | Quantitative | Line Miles | - | - | - |  |  | - |  |  | -
Vegetation Management & Inspections | Clearance | WMP-VM-VFM-05 | Quantitative | Line Miles | - | - | 670.8 |  |  | - |  |  | -
Vegetation Management & Inspections | Fall-In Mitigation | WMP-VM-VFM-06 | Quantitative | Line Miles | 70 | 150 | 220 |  |  | 220 |  |  | 220
Vegetation Management & Inspections | High-Risk Species | WMP-VM-VFM-07 |  | - | - | - | - |  |  | - |  |  | -
Vegetation Management & Inspections | Emergency Response Vegetation Management | WMP-VM-VFM-08 |  | - | - | - | - |  |  | - |  |  | -
Vegetation Management & Inspections | Vegetation Management Enterprise System | WMP-VM-ESG-01 |  | - | - | - | - |  |  | - |  |  | -
Vegetation Management & Inspections | Quality Assurance and Quality Control | WMP-VM-QAQC-01 | Quantitative | Line Miles | 114 | 171 | 229 |  |  | 229 |  |  | 229
Situational Awareness & Forecasting | Environmental monitoring systems | WMP-SA-01 | Quantitative | Weather Stations | - | - | 5 |  |  | 0 |  |  | 0
Situational Awareness & Forecasting | Grid monitoring systems | WMP-SA-02 | Quantitative | Fault Indicators | 3 | 6 | 10 |  |  | 10 |  |  | 10
Situational Awareness & Forecasting | Fire detection and alarm systems | WMP-SA-03 | Quantitative | DFA Units | - | - | - |  |  | - |  |  | TBD
Situational Awareness & Forecasting | Weather forecasting | WMP-SA-04 |  | - | - | - | - |  |  | - |  |  | -
Situational Awareness & Forecasting | Fire Potential Index | WMP-SA-05 | Qualitative | - | - | - | - |  |  | - |  |  | -
Situational Awareness & Forecasting | Ignition likelihood calculation | WMP-SA-06 | Qualitative | - | - | - | - |  |  | - |  |  | -
Situational Awareness & Forecasting | Ignition consequence calculation | WMP-SA-07 | Qualitative | - | - | - | - |  |  | - |  |  | -
Emergency Preparedness | Wildfire and PSPS emergency preparedness plan | WMP-EP-01 |  | - | - | - | - |  |  | - |  |  | -
Emergency Preparedness | Collaboration and coordination with public safety partners | WMP-EP-02 | Qualitative | - | TBD | TBD | Continued engagement with local stakeholders and PSPs to prepare for and respond to fire-related event; Meet with Community Advisory Boards |  |  | Continued engagement with local stakeholders and PSPs to prepare for and respond to fire-related event; Meet with Community Advisory Boards |  |  | Continued engagement with local stakeholders and PSPs to prepare for and respond to fire-related event; Meet with Community Advisory Boards
Emergency Preparedness | Public notification and communication strategy | WMP-EP-03 |  | - | - | - | - |  |  | - |  |  | -
Emergency Preparedness | Preparedness and planning for service restoration | WMP-EP-04 |  | - | - | - | - |  |  | - |  |  | -
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | WMP-EP-05 | Qualitative | - | TBD | TBD | Conduct Incident Command Training for all identified IC members and hold a Virtual PSPS Tabletop exercise; Continued implementation of Liberty’s 2022 AFN Plan; Continued maintenance of emergency response plans; Enhanced documentation and use of lessons learned to update plans. |  |  | Conduct annual Incident Command training for all identified IC members. Hold Tabletop (1) and Functional (1) PSPS Exercises. Continue to implement Liberty’s AFN Plan. Continue maintenance of emergency response plans. Update plans and procedures based on feedback and lessons learned from stakeholders and After Action Reports (AARs). |  |  | Conduct annual Incident Command training for all identified IC members. Hold Tabletop (1) and Functional (1) PSPS Exercises. Continue to implement Liberty’s AFN Plan. Continue maintenance of emergency response plans. Update plans and procedures based on feedback and lessons learned from stakeholders and After Action Reports (AARs).
Emergency Preparedness | Learning after wildfire and PSPS events | WMP-EP-03 |  | - | - | - | - |  |  | - |  |  | -
Community Outreach and Engagement | Public outreach and education awareness for wildfires, PSPS, outages from protective equipment and device settings, and vegetation management | WMP-CO-01 | Qualitative | - | TBD | TBD | Continue to survey customers, CBOs, community partners and stakeholders to understand wildfire and PSPS awareness and the needs of customers. Strengthen and expand AFN CBO partnerships. Identify emerging channels and technologies to better communicate with customers, community and stakeholders. |  |  | Continue to survey customers, CBOs, community partners, and stakeholders to gauge awareness of Liberty assistance programs and of customer needs. Strengthen and expand AFN CBO partnerships. |  |  | Continue to survey customers, CBOs, community partners, and stakeholders to gauge awareness of Liberty assistance programs and of customer needs. Strengthen and expand AFN CBO partnerships.
Community Outreach and Engagement | Public engagement in WMP decision-making process | WMP-CO-02 |  | - | - | - | - |  |  | - | - |  | -
Community Outreach and Engagement | Engagement with AFN populations, local governments, and tribal communities | WMP-CO-03 |  | - | - | - | - |  |  | - | - |  | -
Community Outreach and Engagement | Collaboration on local wildfire mitigation and planning | WMP-CO-04 |  | - | - | - | - |  |  | - | - |  | -
Community Outreach and Engagement | Best practice sharing with other electrical corporations | WMP-CO-05 |  | - | - | - | - |  |  | - | - |  | -

## Table 13
Utility | Liberty Utilities |  | Note: Provide a listing (as rows) of all work orders / notifications for corrective work on electric circuits that were open as of the end of the quarter.
Table No. | 13
Date Modified | 2024-05-01
Table 13: Open work orders / notifications
a. Work order number | b. Equipment Type | c. HFTD Tier | d. Line type | e. Date the work order was originally opened | f. Due date of the original work order | g. GO 95 rule 18 priority level of the original work order | h. Optional utility-specific repair priority | i. Date(s) the work order was reinspected or modified (if applicable) | j. Due date of the work order after it was reinspected or modified (if applicable) | k. Priority of the work order after it was reinspected or modified (if applicable) | l. Reason for reinspection (if applicable)
292463f0-3564-44c6-b80e-e93a7f92c6d9 | Pole | 2 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
fdb36ba8-1cfd-4924-9f09-2f9608aa69e7 | Pole | 0 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
3927be7f-8d6e-4dc7-8f71-111aeeccc576 | Pole | 0 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
e76ebf8f-3586-4459-8d0f-228a4e8df366 | Pole | 2 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
2bdf6cc7-69b1-485c-a41c-c499970e5057 | Pole | 2 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
5b7425b9-ec1f-44d6-a434-05e152179e04 | Pole | 2 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
7ac2458b-dcd1-43ec-b7c1-765ca94bcc1f | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
ad581a73-2d0d-41d7-8959-ef7f1a492d27 | Pole | 0 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
2e8ed29e-70dd-478f-bbe1-0f83f0759243 | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
bef140bd-fdc4-490e-bc97-4f941805f85c | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
5e76905f-23f0-4589-bbef-245daa4456ca | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
945fce7b-cfdd-40aa-aae1-0d47c3d51ee0 | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
40826a16-c983-4de8-bf86-8393f80b3dbe | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
8f9f5d56-9ebe-4b36-a937-e9e6c457f2d6 | Pole | 0 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
2de03aeb-b4e2-4640-b222-b5ad07cb304e | Pole | 2 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
9dab363d-ac1d-4ead-8508-3e1782d60067 | Pole | 2 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
b64ec123-b0fb-486b-922d-9c278e5bd81f | Pole | 0 | Distribution | 2024-03-28 | 2025-03-28 | Level 2
11259963-4939-4c72-8c16-e0833ec09076 | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
31c6bd7f-b1f3-4074-bea0-40f036cdb7ed | Pole | 2 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
f188f8a3-49d1-44fe-a043-7986326854fc | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
978d82d2-2b18-4983-956f-269bb879bdf2 | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
2519e6c2-4c77-492f-868d-3750d96795a1 | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
ed867b02-2786-4227-8336-47efa669032b | Pole | 2 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
05e5225f-da35-4ba2-bf98-15117c8072c6 | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
dfce73af-efd0-45dc-b099-86867272f1fc | Pole | 0 | Distribution | 2024-03-28 | 2029-03-27 | Level 3
796b3ee9-2ec8-47e9-9a11-db6563133211 | Pole | 3 | Distribution | 2024-03-27 | 2029-03-26 | Level 3
e439a1c3-6831-4458-8628-0038d0931332 | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
eaa09e16-2807-47e5-b21d-46aa16df96d8 | Pole | 2 | Distribution | 2024-03-27 | 2029-03-26 | Level 3
35c8633a-c446-4c40-8153-99e855e157fe | Pole | 2 | Distribution | 2024-03-27 | 2029-03-26 | Level 3
29a83280-7a12-4e45-ac8a-36b7a3e13990 | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
00383671-6b9f-4226-957e-2db7041ba9da | Pole | 2 | Distribution | 2024-03-27 | 2029-03-26 | Level 3
00383671-6b9f-4226-957e-2db7041ba9da | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
b32d724c-7de0-4811-86f7-6ab560e2bead | Pole | 3 | Distribution | 2024-03-27 | 2024-09-23 | Level 2
37f8d06a-f6b3-4f79-8b3a-e34fede2d630 | Pole | 2 | Distribution | 2024-03-27 | 2029-03-26 | Level 3
bed1685e-07a1-4ce5-a021-a2bed7f78dce | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
da91d30f-bd5f-46cd-be7c-c1a73e068c68 | Pole | 3 | Distribution | 2024-03-27 | 2029-03-26 | Level 3
c17d7576-5215-4b14-9884-76d6c3463c7a | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
7423636d-f839-436c-a767-47ea8f7ff6d7 | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
31c1a07e-3d99-4380-9be4-693f76709411 | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
2cff183c-63e5-4ab1-a15e-171f436d852f | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
0caf431c-0b97-427e-865b-1fc50e16cdcd | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
8a63c227-9d4d-4c5f-9ce8-8bfa8b9fa199 | Pole | 2 | Distribution | 2024-03-27 | 2025-03-27 | Level 2
d7dbb161-42c6-4c30-b716-9ec7b545a6c5 | Pole | 3 | Distribution | 2024-03-27 | 2024-09-23 | Level 2
407ebd9c-27d7-45a6-8b9a-e94d66953172 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
547ae631-d4aa-4eb1-9c62-8b0c99827d59 | Pole | 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2
5aff294e-23de-4a7c-a2a7-9e7cbd0ecaea | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
5aff294e-23de-4a7c-a2a7-9e7cbd0ecaea | Pole | 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2
5a897c18-9e93-43ab-9faa-1c2a139d9c51 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
5a897c18-9e93-43ab-9faa-1c2a139d9c51 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
b25361b5-5591-42c6-be07-534bc588a041 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
ba200718-345c-4a5d-ae57-05f298aa9a5a | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
cf694910-e60c-4330-821f-363d803793d0 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
d26758b8-a7f9-460c-b201-631234262042 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
7ae52af0-668c-4ad3-abfb-e6d1057d3c75 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
9606b5b1-db0c-44bf-a47b-46e1d94b7425 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
5e966840-cb47-4bac-87d6-53c1b6ca6c97 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
5ee3017b-ccbd-45f1-b2ee-1ce290e00175 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
43eefb5d-6dd3-4b20-a7f6-f3d394da8cb8 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
4ee9864b-586a-466f-bde8-ac7bed6e047f | Pole | 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2
c86a65e8-2708-4619-87ef-e406f467a518 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
07ab0bae-d662-4131-903d-4106893cb647 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
816acdb6-4723-4dfa-bb46-715f03378a43 | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
11013ab1-1c84-4285-a2ab-eafc6c032df1 | Pole | 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2
b43d0163-d0c0-4972-a52a-e3829f915d6b | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
9c5d1905-b4c0-4d6a-b080-87b7eeb9d03f | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
9c5d1905-b4c0-4d6a-b080-87b7eeb9d03f | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
ef5f3d2c-86d5-4cea-a599-e9a8c84374ea | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
c4d9a72f-e7e9-4791-9425-1ddbb14084d3 | Pole | 2 | Distribution | 2024-03-26 | 2025-03-26 | Level 2
439f4f1a-ef34-4020-9d57-1cf73bc0bc7b | Pole | 2 | Distribution | 2024-03-26 | 2029-03-25 | Level 3
ffdfce8d-25ee-4cd0-b253-ba08d6508dd4 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
6c0fb2cd-ef45-4d1e-bec5-9da2390c28a0 | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
9fd31c4c-560c-41c6-ae08-89f309938ffe | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
b3b06fc2-0ab1-4730-9545-a5a18e97def1 | Pole | 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
b3b06fc2-0ab1-4730-9545-a5a18e97def1 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
9f1fd254-cc24-4cfd-887d-c6f20dba28f1 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
06972e8f-7dc5-438f-b33f-35510119a835 | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
92103ab7-e307-4022-8f61-883051ee656c | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
eaa030f6-82ae-44fe-a346-8f8c57244f55 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
9ff16f76-ca58-4874-a1dd-44f3a4e7be8e | Pole | 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
69a27824-6010-4fb9-8d90-ff28a46393f8 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
f541c835-4fb7-4925-8f12-b548445e8377 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
28c0b09b-59eb-4bf1-904e-055ebdafa2d2 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
919465ea-efea-4261-9f5a-4f91cb3e8cf3 | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
c3f1302f-9faa-447d-abb8-87d37ec135fe | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
cc69dd27-a5d6-4458-b1d2-ebc40172c0c6 | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
cde1acd5-0220-4630-a455-50123ab05f68 | Pole | 0 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
9d89ec99-aec4-4fe4-8896-c77e9d458afd | Pole | 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
b2c71ee3-47c1-42ee-b70f-dfde24749466 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
869b1d91-0739-46e0-bb69-f2076ffdbefd | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
a14cf560-3e1d-4248-9940-b618c5d6a77d | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
d13be912-32cb-4a9c-81f4-490a1ffc7eea | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
77eb305c-4873-4f16-b29d-fe37a64b7d69 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
77eb305c-4873-4f16-b29d-fe37a64b7d69 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
d7b9bb58-ceb3-401f-8b78-9e24b0393fd2 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
d6eb1b6a-d6c5-4a46-a983-a18f24192be8 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
e0cdc8b5-1572-44ef-8f90-4d117dccea12 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
cb26b583-44ae-49e2-a4b9-48bfd23f473a | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
cb26b583-44ae-49e2-a4b9-48bfd23f473a | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
e803c6a8-09ff-4b35-98fe-050245e92993 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
fd2c66a1-d430-461a-8d13-eaf41471acf8 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
bef47df3-f3df-43ad-9c0a-3b342fe827bd | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
590ddffb-adeb-481f-b538-b8df68ed1c33 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
5ccaf539-35bf-4b3f-88cb-62c6bbc92c34 | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
8a422453-d2f4-488d-b154-a639544d04d8 | Pole | 0 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
8a422453-d2f4-488d-b154-a639544d04d8 | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
3819d7e1-adc6-4475-8860-7bee70b023c5 | Pole | 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
51498ecf-5d11-4aec-845b-47c4475ba00f | Pole | 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
3d8cbdb6-dd42-4689-9599-f28f29adf4a2 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
3506e123-6807-40ff-84fd-040a2f3b8510 | Pole | 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
2f8cf4cc-d5d6-4052-b31c-47b8001e58b7 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
54963d4b-5d80-4d7d-a999-7ebc87cfd053 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
2504a978-48a9-456a-919e-c0050e2a0edf | Pole | 0 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
20105d19-eb20-480d-886b-605c7dff2ec7 | Pole | 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
0f5be94a-869a-45e8-9f34-78c77392cafa | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
9d7cbc5a-d907-4533-81cb-a020d18481b5 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
9d7cbc5a-d907-4533-81cb-a020d18481b5 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
9d7cbc5a-d907-4533-81cb-a020d18481b5 | Pole | 2 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
a54bb8c0-58f3-4b3e-b5be-c32ff35d4ad9 | Pole | 2 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
8e46cf52-1148-4af0-a30e-d13f81904e12 | Pole | 0 | Distribution | 2024-03-25 | 2025-03-25 | Level 2
8e46cf52-1148-4af0-a30e-d13f81904e12 | Pole | 0 | Distribution | 2024-03-25 | 2029-03-24 | Level 3
79bcaeb5-e20e-4355-a087-f82c42be58f8 | Pole | 2 | Distribution | 2024-03-22 | 2029-03-21 | Level 3
79bcaeb5-e20e-4355-a087-f82c42be58f8 | Pole | 2 | Distribution | 2024-03-22 | 2029-03-21 | Level 3
1c001f81-d803-4ad0-b36e-045ad791e3fa | Pole | 2 | Distribution | 2024-03-21 | 2025-03-21 | Level 2
1316151e-84c4-4d0d-8160-99bfb51cd5b8 | Pole | 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
990e530b-5437-4484-8b98-5ac1573b7936 | Pole | 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
e8293a8d-d8e5-46e6-be90-6bfaa5b58a78 | Pole | 2 | Distribution | 2024-03-21 | 2025-03-21 | Level 2
631c9364-656b-4c61-bf6c-3c1a85474ac6 | Pole | 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
faaa79b8-0533-40a1-b55e-5be9f1dee2c9 | Pole | 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
faaa79b8-0533-40a1-b55e-5be9f1dee2c9 | Pole | 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
79f1f185-1912-4a34-97bf-101042f3bb5f | Pole | 3 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
1e3cc382-36a1-4613-b60a-50a7bb85b90e | Pole | 3 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
af7e4402-b388-402e-b157-b35c66f2bb71 | Pole | 3 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
df3b2441-2766-48b7-885a-6341d6f1abd7 | Pole | 2 | Distribution | 2024-03-21 | 2025-03-21 | Level 2
420a3ed6-10c5-42ce-8c27-937277b31c80 | Pole | 3 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
08fdeefc-3c51-4607-add6-b2bc5f4a3b57 | Pole | 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
bb2057e2-f77e-4948-8b02-28844880f609 | Pole | 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
076f89b7-7432-4a4f-8808-17afc7a7570a | Pole | 2 | Distribution | 2024-03-21 | 2029-03-20 | Level 3
b5d14093-ebf1-4cff-b101-44d2a73456e1 | Pole | 2 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
b5d14093-ebf1-4cff-b101-44d2a73456e1 | Pole | 2 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
e58a30e9-909f-44a0-bf5e-b9398bec5e48 | Pole | 2 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
6a609678-360a-46cb-aa60-69113b2fe438 | Pole | 3 | Distribution | 2024-03-20 | 2024-09-16 | Level 2
68417c58-a39e-4051-8501-d79e33d7780b | Pole | 3 | Distribution | 2024-03-20 | 2024-09-16 | Level 2
b4b67759-1d9f-4321-adf1-65d6c4ae7dd7 | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
ea60cde8-d125-4770-999a-8ffeae81d5ea | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
7da6611b-5f78-4d37-9ee3-b63fb2907b8c | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
8c2c95a4-495b-4654-a1f8-daadfce3acd9 | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
8c2c95a4-495b-4654-a1f8-daadfce3acd9 | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
d8d2ea06-dc7d-4035-bc32-fcafe4c02823 | Pole | 2 | Distribution | 2024-03-20 | 2025-03-20 | Level 2
eaa1e22d-0165-4e10-8bf3-0b8245078c89 | Pole | 2 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
4cdbca96-ad2f-4657-9032-934c15f6630a | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
c84575cd-88ab-45ef-89c9-894ee69be3af | Pole | 2 | Distribution | 2024-03-20 | 2025-03-20 | Level 2
8632bd2d-9c7b-46ff-a6e7-d917e66c9ec7 | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
146d351e-3bda-47cb-830b-02287d5d866e | Pole | 3 | Distribution | 2024-03-20 | 2024-09-16 | Level 2
3ea67142-1251-4cc4-be86-a7e50de4cd1f | Pole | 3 | Distribution | 2024-03-20 | 2024-09-16 | Level 2
289a4eae-7afd-492c-9f1a-9e499742915c | Pole | 2 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
3451a003-6206-4a9f-9dff-c759f2c7fe2d | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
3451a003-6206-4a9f-9dff-c759f2c7fe2d | Pole | 3 | Distribution | 2024-03-20 | 2029-03-19 | Level 3
da906808-76ba-40aa-b70f-67e019ba1ac1 | Pole | 3 | Distribution | 2024-03-19 | 2024-09-15 | Level 2
6e50c875-9419-4579-add9-ba3ebe1ae4d2 | Pole | 2 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
c57d5fea-de12-45a8-8e05-537cbd7b8fd8 | Pole | 2 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
d855a00c-67fe-41f5-941b-dc9f6be92d53 | Pole | 2 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
d855a00c-67fe-41f5-941b-dc9f6be92d53 | Pole | 2 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
ebd63b03-7449-47c0-aec5-4d368a623ebb | Pole | 2 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
64a1ec8d-cf45-4cfa-bd2f-b3cdd5917235 | Pole | 2 | Distribution | 2024-03-19 | 2025-03-19 | Level 2
eee3bbd4-d86e-4db1-8644-2b827a3928ab | Pole | 2 | Distribution | 2024-03-19 | 2025-03-19 | Level 2
a519db11-e81a-45cf-af0b-bab3dcb1ffeb | Pole | 2 | Distribution | 2024-03-19 | 2025-03-19 | Level 2
4bfa1811-23e1-4284-b196-a0ca271a1b0b | Pole | 3 | Distribution | 2024-03-19 | 2024-09-15 | Level 2
b6d2dfca-3a6f-4b1c-a771-b50169bd69a9 | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
305b8992-2005-452e-b1db-9ed04ceb5db8 | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
dfa7f028-d0ca-4935-9fc8-f556ee2a27d3 | Pole | 3 | Distribution | 2024-03-19 | 2024-09-15 | Level 2
67489272-1b60-4ac5-a721-376143f74f1c | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
32c5164a-278b-4de6-8ba0-eec735574189 | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
b2dd8775-c2f9-4726-b647-0063d4c56bff | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
702b2947-1088-4f89-bd39-acd62d6487c6 | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
c83aae4f-10b7-4577-af12-0ba0fb800e53 | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
243cb938-76c9-44f9-9cbf-7e1ead4fde96 | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
e6971c08-e9f9-4a31-8782-60b7197bfdc4 | Pole | 3 | Distribution | 2024-03-19 | 2029-03-18 | Level 3
ec67a7ca-4c76-4298-a25d-7f99ec5d8a7b | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
ec67a7ca-4c76-4298-a25d-7f99ec5d8a7b | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
f122bac3-91b2-438c-90c5-0fa22576dc1a | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
8eee6817-0611-4b74-961f-34f112221542 | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
5c8ea43e-1226-434b-957f-b7e33e5cbeae | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
5c8ea43e-1226-434b-957f-b7e33e5cbeae | Pole | 3 | Distribution | 2024-03-18 | 2024-09-14 | Level 2
a72b7085-d1b3-4cb0-b320-fa94f7465873 | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
8bb31abe-4802-4954-a9cd-b629c0f2551e | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
c2758a88-d998-4034-81e1-7431db73e4a5 | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
8a269a15-9eb7-4bca-aafa-8ee2d6195d9a | Pole | 3 | Distribution | 2024-03-18 | 2024-09-14 | Level 2
626b915e-dfb8-48a9-b6f8-ab3835b17a73 | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
f78302cb-5512-45cd-83e9-95850ed24e25 | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
27581ac7-bc3a-480d-91bc-cf62737763f2 | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
070727c5-b0a5-41cd-b1a4-45ee4133c433 | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
7b34fda0-cc12-4ed0-839b-bad462289374 | Pole | 2 | Distribution | 2024-03-18 | 2025-03-18 | Level 2
04bc14fb-04e4-4ad9-97c0-6d7bdbe07148 | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
c849bfb6-9dbe-403e-ac4d-be6136d21bdc | Pole | 2 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
bbdc9774-ef09-4d73-8cc2-4fd51572d96f | Pole | 2 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
c646074f-f8b2-4fcd-9cb9-e32a6afe863d | Pole | 2 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
448d965f-ab74-47be-b5f3-a9fbe1a1c69a | Pole | 3 | Distribution | 2024-03-18 | 2029-03-17 | Level 3
04f4d012-143b-4395-b60e-0b6101d9ddf7 | Pole | 0 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
5b89e1cb-e006-4282-90a3-d8e8f38cd91f | Pole | 0 | Distribution | 2024-03-15 | 2025-03-15 | Level 2
5b89e1cb-e006-4282-90a3-d8e8f38cd91f | Pole | 0 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
81719855-bfbd-4fd9-80aa-f6c8649d370f | Pole | 0 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
ca77a8d2-4b9b-4281-908e-971acba65537 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
ca77a8d2-4b9b-4281-908e-971acba65537 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
0cbb7e81-4142-48af-adbf-9d0d38b63be8 | Pole | 0 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
acd45106-2e48-4941-b30d-bfcdb1e20110 | Pole | 0 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
81d8ef28-5319-47f3-b868-b5ab8ee21e52 | Pole | 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2
94db60c7-d3ec-4d7a-8119-1cb5f2ffdf67 | Pole | 0 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
6c9da36f-4613-433a-aa97-f76e50dd0c8f | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
6c9da36f-4613-433a-aa97-f76e50dd0c8f | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
5c520009-053d-44b0-bc48-0e24d1162b6a | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
a5b5bdd7-d799-4468-87bd-df8fd8f99927 | Pole | 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2
873bec57-a3bc-486d-808b-953304dec26e | Pole | 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2
451ebfa4-b2f7-4b16-9476-0000c5a41fb8 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
7d542951-a673-4186-91b2-23165a23f1c8 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
46dc1da9-b06a-438b-b1c3-a80929ff6012 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
85a994ee-218a-4a63-9a51-21ec1db3c9b5 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
8d3e495b-2259-4360-8d30-97cc224149bd | Pole | 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2
618d4b71-2d4f-4a66-9c36-bb4f93a37b7c | Pole | 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2
920c15f2-82fb-489f-94c2-486e824018a0 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
9233c06b-4391-4e5e-a127-2572d957f4c2 | Pole | 2 | Distribution | 2024-03-15 | 2025-03-15 | Level 2
b09fa20e-a7d1-47af-86d4-66d53310a772 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
75388b7f-b275-4da5-b320-be52785547ea | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
07c5e084-c33a-4f97-ae20-b4598b9a6f8a | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
bae9418f-3727-40ca-b232-930da6564434 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
3c341758-4271-4fed-9811-10f503ad4d11 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
e14ca43b-d7b3-45fc-acc2-b90f84b76dd3 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
a99f53ce-11be-44f8-a145-6ddb818d2bfa | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
2f42eab6-9e41-4f1a-a470-7f1b41763b94 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
2f42eab6-9e41-4f1a-a470-7f1b41763b94 | Pole | 2 | Distribution | 2024-03-15 | 2029-03-14 | Level 3
dc67055a-8a8e-441d-9179-75ace6d6ffbd | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
9fdb74f3-2188-45be-8390-a72772fea765 | Pole | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
8c3a3394-2ea3-4911-873e-fe6330489d85 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
8c3a3394-2ea3-4911-873e-fe6330489d85 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
6c28ca20-e409-4a24-9e9a-5d008eb8b314 | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
07826595-9403-4ece-9e3b-7855a13373b3 | Pole | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
22678b77-17b5-4732-b06e-8845a2540d0c | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
22678b77-17b5-4732-b06e-8845a2540d0c | Pole | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
5a1a39d9-25c2-4213-a30d-2cad209cac55 | Pole | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
ff24349d-0e12-460b-9e42-f9aacb19313d | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
ff24349d-0e12-460b-9e42-f9aacb19313d | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
1690a91a-1b12-4eed-9fff-59c7c7c29be8 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
3978e8d7-c54f-4d45-9eb4-4a6b900c0d9c | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
ef217907-84cf-44e7-bd59-3c3115bf0af4 | Pole | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
1ed64d66-c515-4d90-ad15-073e481ac805 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
2ddde2ee-e860-4c50-b43a-d50bba6c0984 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
b3a1883d-cd23-4b3e-a2dc-8081c9029cdf | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
671af8fe-d837-45f0-bc3e-775cef03a077 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
671af8fe-d837-45f0-bc3e-775cef03a077 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
6196a326-3a43-475e-b3b4-b80a53e4b204 | Pole | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
4d307b47-2f22-41c1-a5ee-18926fc63cb8 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
4b0613c9-20d2-4ca5-b945-4d1947066b3f | UG Transformer | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
2c0a844e-c1d7-4c28-9e3b-15d94c887cde | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
e598baa4-6661-45a7-a608-fa8b16f14b67 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
b4ec6d68-155e-4b9a-8f6a-cea5b3145ed3 | Pole | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
7a1b3cf5-4e25-47de-9d09-f4051dcb2b1b | Pole | 0 | Distribution | 2024-03-14 | 2025-03-14 | Level 2
2b30b5af-88d3-474d-9d99-ea87c7fd5b80 | Pole | 0 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
5ac29d35-bca8-439d-bd5e-82e0eac7d52d | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
c3e6c25f-5b5d-4019-8d41-92b6fd0f72b7 | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
1194cd94-854f-4741-864c-13a5f87a0c49 | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
db48b62c-3404-4918-ba2f-6a739a8a4389 | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
eb16d4de-7039-42b8-ac70-41f6c6eae00b | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
ebf9a957-efe1-459d-aba9-18f29655ea44 | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
b4b02ead-0bf7-4cc7-93ea-170deff55522 | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
8531c9a7-ea4c-4e3c-b993-7bedd7b9d6ad | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
6ed27881-c137-4db9-b0e3-0a8af010bc86 | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
3ff94987-c892-403a-8c64-a75419e5c691 | Pole | 2 | Distribution | 2024-03-14 | 2029-03-13 | Level 3
caea4356-53f5-49dc-ac5f-3d968436a089 | Pole | 0 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
f85c7d00-0b40-4291-bfe3-8fbb4ba7626c | Pole | 0 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
178b972f-f163-4382-822f-7648fdb5be01 | Pole | 0 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
9835b7f9-09f6-402b-b537-c08396dfb26f | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
06a0712e-c3c3-44fa-979b-ee9c216455b0 | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
387d203a-d61e-4bc4-82ed-07ee986fa1b4 | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
99ef8eec-dba4-4b02-b684-2eabfcfa08e8 | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
a48286ed-b7e2-4c1d-a13b-f95ca5129fc9 | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
c9a4b06b-def7-49ed-9dfd-28f9e822eefd | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
b0f4c606-feb9-4204-976f-353fa9b80b10 | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
255350d9-1de3-4c4b-9a49-5a4a04371a0f | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
255350d9-1de3-4c4b-9a49-5a4a04371a0f | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
edc2f829-3290-4e13-91dc-01e6692bd68e | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
edc2f829-3290-4e13-91dc-01e6692bd68e | Pole | 2 | Distribution | 2024-03-13 | 2025-03-13 | Level 2
c8478854-55af-45ab-82aa-1599ae1af628 | Pole | 0 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
613d0b2c-9d20-4454-8f55-e08ac74e678b | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
656716a8-8f6b-4b4e-bcf0-0f55444d67e7 | Pole | 2 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
41d547ee-cd96-42dc-b2b9-2b0b9397d5b5 | Pole | 2 | Distribution | 2024-03-13 | 2025-03-13 | Level 2
77c129c6-ea88-45a3-8944-bacae0ac6454 | Pole | 2 | Distribution | 2024-03-13 | 2025-03-13 | Level 2
6d32cb47-eb6e-47f3-97d8-d2311a2cade3 | Pole | 0 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
e39191f7-e3df-4114-8897-c9ef1353a158 | Pole | 0 | Distribution | 2024-03-13 | 2029-03-12 | Level 3
070549e9-574c-487a-b5eb-e10e5c38a2fa | Pole | 2 | Distribution | 2024-03-13 | 2025-03-13 | Level 2
2546d8df-9301-483a-8eae-96eb9a7ead1e | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
1026ccb6-e261-4d40-8855-9aad823c976d | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
6b79f5c2-2753-4f15-b91d-d8c43cc5c7bf | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
ec09a040-7563-4c1e-a0ec-b466cd3f1fd0 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
2917fb9b-2a0c-4806-91af-80f91bbd428b | Pole | 0 | Distribution | 2024-03-12 | 2025-03-12 | Level 2
2917fb9b-2a0c-4806-91af-80f91bbd428b | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
3978e39f-1a26-44b9-803f-31c0a0c49c74 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
8c7d26fa-a1fe-4958-941d-1bc3d9e2bb5b | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
2e0f87d9-dbe7-4e52-b336-22347ffbbc71 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
35b541e8-8d98-45bb-963d-10f7886f47b8 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
fa33f759-6cdb-4317-a552-37d604cdc7d7 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
5d2d4d98-907c-4264-bc6b-005b041d9a42 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
e57b0b1d-7d5a-4966-9049-32c53588aafe | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
4ed21ab4-189c-4d1d-94ef-572b2cdacc08 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
ccda2710-2a00-49ff-bf5a-e105cd05cbeb | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
ccda2710-2a00-49ff-bf5a-e105cd05cbeb | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
ccda2710-2a00-49ff-bf5a-e105cd05cbeb | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
0b2e686d-0fd3-4a6f-a5f5-b02cf0071a0b | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
0b2e686d-0fd3-4a6f-a5f5-b02cf0071a0b | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
b32c4b9d-6c77-437f-bb92-f19c179eea5b | Pole | 0 | Distribution | 2024-03-12 | 2025-03-12 | Level 2
b32c4b9d-6c77-437f-bb92-f19c179eea5b | Pole | 0 | Distribution | 2024-03-12 | 2025-03-12 | Level 2
ffddb409-8048-4b2b-b41e-9f3c92347993 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
a73d20bc-97fc-41b2-80cc-0362c19a6d5f | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
316d846b-8315-4a12-b976-dc3712ea5fc0 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
5c077e6d-0f17-45d5-991b-c4d774de9d19 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
e8482be5-6670-466e-9809-b935e5888c77 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
00392c16-ca27-463b-bf1a-88b96f37144d | Pole | 2 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
fabab53c-38af-4b7b-a6a5-4f33abfa487f | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
a0988bac-30ca-4eea-946a-8f6b78920a43 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
8ee6371f-c940-48a3-ba62-2f23e4e82837 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
ee2a6001-5a21-45f5-b666-1188492ceb88 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
28292332-8020-4055-883c-6bb760a99056 | Pole | 0 | Distribution | 2024-03-12 | 2029-03-11 | Level 3
8ae604ba-27d2-4783-9b24-ee1af86e3ae0 | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
9c4822fb-9c7f-467f-9795-7a31bd92248c | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
97de8504-fd39-4c3f-bc14-b1b54df9c7cd | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
eab986d1-72dc-4425-885a-bbc36b208b77 | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
9ad377f1-3d50-4082-aff0-76ef2ebf94a7 | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
1b9c2306-3784-4477-852a-1b6d30bff078 | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
1b9c2306-3784-4477-852a-1b6d30bff078 | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
71a10a31-9234-48cf-8ea7-4cf857c1ac3c | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
71a10a31-9234-48cf-8ea7-4cf857c1ac3c | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
3037f421-e216-4aa3-b5d6-eb4b1ff737c1 | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
17c53b93-1598-41ad-be80-359cce421345 | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
db08b317-00f1-4690-bd87-629337143826 | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
0480007d-e095-4ed5-9879-84c2706e326d | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
eb885587-3a94-466a-a978-85a1da0ae610 | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
eb885587-3a94-466a-a978-85a1da0ae610 | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
c4f200d3-2bca-4dc6-9620-11031254c290 | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
f00129f7-0d53-47e1-8263-05891b037e6f | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
5de2faa2-a35c-4404-bf1a-db08b2abe8a4 | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
76a8b0fd-711c-4413-900e-ded0074ed862 | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
8c4cd3fa-e0fa-45b9-860a-a84df24b8b62 | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
ca861d4b-b6b8-4a9a-b610-3a7803d3330e | Pole | 0 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
bce8886b-c009-48aa-b9b4-84d94681378c | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
bce8886b-c009-48aa-b9b4-84d94681378c | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
9ea965dc-3d90-4cd4-86e4-597e0c741dea | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
9ea965dc-3d90-4cd4-86e4-597e0c741dea | Pole | 2 | Distribution | 2024-03-11 | 2029-03-10 | Level 3
642f244c-ca45-42a6-90ef-1ddba4cd710e | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
938a08c6-62b8-475f-b3a1-a28a7ba33f0e | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
897852af-4e90-49bb-bf3c-04d4540922e0 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
fff205d9-fdcb-4707-a88a-787160f597a0 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
e611c240-8cb6-4aa4-af92-ace763211a6e | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
95da875f-e165-42d4-9683-08b14e1fc408 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
f6d01e62-8c71-4064-8175-46007b0cf106 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
28d7798a-d457-4c43-9bdf-53441cdefd6f | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
8908495c-734e-411d-a27b-a4c4b44bd2e1 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
a3dc23c7-095b-4ea9-b2a4-e9f7df5d5cfd | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
89a63500-cfad-4594-b14a-4fada7008b24 | Pole | 0 | Distribution | 2024-03-08 | 2025-03-08 | Level 2
09e3c6c5-731c-4ef1-a0e7-83332ec8d02b | Pole | 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
b6f62fc1-a241-4f31-80ac-73c3a743d804 | Pole | 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
e7e54f41-e05e-4ad3-977a-6f135e79943a | Pole | 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
73e21503-88be-4696-af29-77d892f36557 | Pole | 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
b5324420-a776-467a-beea-8ccb212a3cc9 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
19466a1e-8d24-46a8-85ea-7f26968a1394 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
33cb1985-b383-4819-baed-02e03535b9f9 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
d126760b-03ec-45c6-bdbe-91b9827656b6 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
6174cfca-1d17-4565-b940-3ed1242e364d | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
063fe1f0-7d4c-4600-ac04-0b30649fdfea | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
60634f10-915b-412f-86f1-ffe80636cafa | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
2c32b5ac-75a7-4144-9a27-fe13d7cdace6 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
68d63cef-fd32-4dd8-a306-8189a5042194 | Pole | 0 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
8dc80301-dfaf-4110-8d68-74a3ddc3a6af | Pole | 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
8dc80301-dfaf-4110-8d68-74a3ddc3a6af | Pole | 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
a6ace773-a1af-4353-a1e9-50bbf91fbbc3 | Pole | 2 | Distribution | 2024-03-08 | 2029-03-07 | Level 3
08bbf9cd-1247-420a-89af-0d99eb3ad7c9 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
57733c2a-4230-4ebb-b7d5-92f105645d65 | Pole | 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
aaf9319c-d9d8-4712-98d5-9b3d513c0f07 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
c216ebf4-35cb-4029-9ceb-cfb93f3e5820 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
c216ebf4-35cb-4029-9ceb-cfb93f3e5820 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
dd5a0d59-1230-4420-b5bc-96515de5e0d7 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
dd5a0d59-1230-4420-b5bc-96515de5e0d7 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
ccb5b19f-0ac1-465b-b92c-334ef353cd26 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
ccb5b19f-0ac1-465b-b92c-334ef353cd26 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
e824c26f-0cd8-453c-aafe-e82f59fd0b7b | Pole | 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
a43a068e-eece-4418-801d-e4b92e8ccf9c | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
31c1b442-e018-46d0-a150-77a22a89a9e8 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
31c1b442-e018-46d0-a150-77a22a89a9e8 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
2618349d-f5f8-42a1-aa90-f445c584cf17 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
3b768b55-ccb3-428a-a74f-85c044236ebe | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
0cafef72-5301-41b1-ba25-b0c7bd91ee71 | Pole | 0 | Distribution | 2024-03-07 | 2025-03-07 | Level 2
0cafef72-5301-41b1-ba25-b0c7bd91ee71 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
49202a77-d54b-4c11-8a4e-651887284760 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
1ac901da-b9e1-4271-92c6-b08e544ca96a | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
d1a228bf-b1e9-4ab4-affc-11e8307ff20d | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
c37e24ea-3eb2-4a36-be5d-8419aa5a8daf | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
b6e52144-8fe7-4c87-ae45-ce83f12869ae | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
3b61d076-b890-4b34-94c8-a7c3a0f5d16f | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
03aa88e9-5e8b-4a21-b0f8-9dc679130e24 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
03aa88e9-5e8b-4a21-b0f8-9dc679130e24 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
03aa88e9-5e8b-4a21-b0f8-9dc679130e24 | Pole | 3 | Distribution | 2024-03-07 | 2024-09-03 | Level 2
9073b083-b6fa-41bc-9456-3f28ad7fb70d | Pole | 0 | Distribution | 2024-03-07 | 2025-03-07 | Level 2
9073b083-b6fa-41bc-9456-3f28ad7fb70d | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
d1d7fa17-fb61-4d4e-86fd-6fc1be7cec68 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
0ee1aa4f-b3d8-492d-b074-5bcf66825a2d | Pole | 0 | Distribution | 2024-03-07 | 2025-03-07 | Level 2
0f3e98f1-4d14-4ce9-946f-6ef1db4cfffc | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
6b5bd890-11d5-41a7-a686-8e0925ebdbc0 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
6b5bd890-11d5-41a7-a686-8e0925ebdbc0 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
994e11d7-094e-461a-9c2e-aa877bfb1867 | Pole | 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
6f13c984-8130-46ab-a83e-a7de34113603 | Pole | 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
5ce8fec7-603e-4157-a4e9-6af7d26ab1ee | Pole | 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
f0f5323d-3f93-4102-947f-ce44f2ab3755 | Pole | 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
699c50ec-809e-476c-b2ae-f7b75e6134e3 | Pole | 2 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
f08b0df9-d27d-4c7c-a473-3fef6ab95f92 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
c2b0676a-62ea-4a5e-aa2b-03964cf50415 | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
5603c595-bfa1-44b6-8706-a85444ed5f3b | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
79ba45b8-7bc8-4680-84f0-d3038ff5fe1e | Pole | 0 | Distribution | 2024-03-07 | 2029-03-06 | Level 3
c4b929af-26a0-4633-99d0-5a066ce990e2 | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
fd7c6e7c-8432-447d-985f-3578bb5e1334 | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
fd7c6e7c-8432-447d-985f-3578bb5e1334 | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
f3fd51bb-b3ff-4e03-912e-467599dd6b78 | Pole | 2 | Distribution | 2024-03-06 | 2025-03-06 | Level 2
0ea61359-570d-4ae7-b1ae-17008eeefa83 | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
466efe1c-b899-4be3-98ac-19b69b87d983 | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
91929722-7fe8-4ba6-b99d-30a9b68b97c4 | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
0c58baa4-a3f4-4d8a-aa9f-d31c4608ba8b | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
ecb6141c-4e89-4a42-a996-3cd7cf806d46 | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
6f0336b9-9cd9-4d8e-b582-38a4f4f86c26 | Pole | 0 | Distribution | 2024-03-06 | 2025-03-06 | Level 2
aa477842-7087-4932-9ef7-f58d33aa14ae | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
24334ed0-dff4-4f32-aedc-5bb4497d199a | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
2afb875c-9db0-4f88-af79-81b6501cc9c0 | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
95c71cb9-4ef5-474b-8a4c-8197c67794ad | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
ed493cbb-15e5-45da-966a-7d9126f155cd | Pole | 0 | Distribution | 2024-03-06 | 2029-03-05 | Level 3
c0fe2780-0b51-4db3-93ec-2555a5b0319b | Pole | 2 | Distribution | 2024-03-05 | 2029-03-04 | Level 3
72311e7e-0cd0-40b7-84fe-a9358e811f86 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
f687f434-b62f-4ecf-a2ec-88f7f21a2d00 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
c31bb5e9-66ad-484c-b6aa-59ff126b2066 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
af46c94a-7ba4-43f5-b403-e48ce2229dc2 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
cc3d4551-a292-4149-bceb-8fda9a142625 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
12755552-d927-491f-afce-2da810b382ba | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
69a4effb-f976-4aca-968f-82aa05104a1d | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
d6ec854d-96d6-4d4e-be39-92f5799d120d | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
4567186f-b1a9-4d69-818f-845b3a76e104 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
1bd4c9ef-eccf-4384-85ec-4cccd4003092 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
3a20ee58-57b3-474c-9d78-7d6668ff1a0b | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
148565cf-6988-42f5-8003-478d292c8159 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
35b123cf-441d-4084-8f01-46e82a4f73f7 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
078837ed-0297-4bfa-8ccb-b9cb5f9cab4e | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
7e940654-7e96-4e59-b50d-a3dfcaed60fe | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
0dc316a5-2e37-48d0-9b06-648f0afeccd9 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
9200b1f1-0fae-45aa-86f8-9f278a05e9d9 | Pole | 2 | Distribution | 2024-03-01 | 2025-03-01 | Level 2
08186b3b-154a-43c0-b189-d122f412d1c7 | Pole | 2 | Distribution | 2024-02-29 | 2025-02-28 | Level 2
380fa61b-d30a-4c68-b4ea-e65dfb919c74 | Pole | 2 | Distribution | 2024-02-29 | 2029-02-27 | Level 3
8be7f492-7ed2-4fa0-94c2-37e23b136ac5 | Pole | 3 | Distribution | 2024-02-28 | 2029-02-26 | Level 3
c7efe317-ec09-4cf1-8df1-eba14aef8c92 | Pole | 3 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
28a9801a-d4da-4439-9520-19d221c562a7 | Pole | 3 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
6a6e079d-e6a0-4930-905c-36c93484a951 | Pole | 3 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
c3599b9e-fddb-4889-b625-6fca66eefeaa | Pole | 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
c3599b9e-fddb-4889-b625-6fca66eefeaa | Pole | 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
b48530e5-bd30-47fb-8473-b4075f37b772 | Pole | 3 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
1e328980-efe2-4bb7-81dd-e64b5d47146d | Pole | 2 | Distribution | 2024-02-27 | 2029-02-25 | Level 3
10858027-00bc-4639-b757-07920fb02e12 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
71fd52ed-7590-4532-bc76-bf16980569c1 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
fd0e945b-5db7-47c6-acda-d035267da9c9 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
fd0e945b-5db7-47c6-acda-d035267da9c9 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
fd0e945b-5db7-47c6-acda-d035267da9c9 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
fea8f128-5102-4b99-88bd-57b57a48f76a | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
fea8f128-5102-4b99-88bd-57b57a48f76a | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
de39883f-bf09-4af8-809e-88a0a146e0d4 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
350c6116-143e-4e60-a485-22ab28b5b51a | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
350c6116-143e-4e60-a485-22ab28b5b51a | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
786b9e06-9a83-43f3-8be4-23a7c62277fe | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
599d888d-e1d2-447a-8a26-34df6bd7d61d | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
275de8a0-d3ee-4bc3-a5c7-36442e2b9e82 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
34e2601a-0fff-483d-9835-48c52e0e1617 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
34e2601a-0fff-483d-9835-48c52e0e1617 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
c21b4f59-4955-4024-858a-62e688f28464 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
03beb2a7-911d-4b32-9abe-b5644ed36cde | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
03beb2a7-911d-4b32-9abe-b5644ed36cde | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
98a9a795-181c-44c0-9b94-2f554fb0957a | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
d70048ad-942a-474e-85a4-02ec5487ad99 | Pole | 2 | Distribution | 2024-02-26 | 2029-02-24 | Level 3
c81b55e5-a404-4a68-aa81-004f0caf0567 | Pole | 2 | Distribution | 2024-02-23 | 2029-02-21 | Level 3
c81b55e5-a404-4a68-aa81-004f0caf0567 | Pole | 2 | Distribution | 2024-02-23 | 2025-02-22 | Level 2
c81b55e5-a404-4a68-aa81-004f0caf0567 | Pole | 2 | Distribution | 2024-02-23 | 2029-02-21 | Level 3
e5dd39f0-1f07-4bc7-ac1b-e7f6e40ead8a | Pole | 3 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
db25654b-255e-4109-8eca-61413e73ea63 | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
e52abb1a-510c-45b8-92f4-80b6888bfee8 | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
e52abb1a-510c-45b8-92f4-80b6888bfee8 | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
f38f4de5-ace3-4fc1-a27a-6f8fd359bd33 | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
283a161d-9cc6-4609-be73-b6fd3eb8582d | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
fd9ee573-0d76-4a21-a490-62141b62ca8e | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
d065b46d-3120-44e8-8538-5984d1bf32f3 | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
73381375-3274-48c7-8137-56e216796f2b | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
b89a9de6-5f59-42c1-83ae-942a4da3b604 | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
ef0d7626-593c-4c4e-a005-4b0bcf7eb222 | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
6e53b0de-81c3-459c-b852-3e73a2c3914b | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
6e53b0de-81c3-459c-b852-3e73a2c3914b | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
6e53b0de-81c3-459c-b852-3e73a2c3914b | Pole | 2 | Distribution | 2024-02-22 | 2029-02-20 | Level 3
f2327610-d2e8-45bb-a9ac-614116be7dc4 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
7a4b7b36-eda9-4ec0-8b17-a18640a7c56f | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
ebaa98df-153e-47f4-864b-f96dac8c06a1 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
a741eb04-0b61-497c-ac36-7ee3bf644317 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
ad29ab38-c95d-48a3-bfa1-98d707c7cb56 | Pole | 2 | Distribution | 2024-02-21 | 2025-02-20 | Level 2
ad29ab38-c95d-48a3-bfa1-98d707c7cb56 | Pole | 2 | Distribution | 2024-02-21 | 2025-02-20 | Level 2
636795ba-90f8-4e20-ad7f-22889f5b6873 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
79211d2e-cfc3-4c60-a5d4-a56b3b51a66b | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
0857b78f-6f5e-45b7-9123-40061e20957b | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
501b58fa-3085-48a4-ac38-da570208bb5a | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
501b58fa-3085-48a4-ac38-da570208bb5a | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
501b58fa-3085-48a4-ac38-da570208bb5a | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
1d89281d-b44e-4820-819d-5dca1f5752c3 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
5f4df282-8de1-4cbe-b2a8-c3155750720c | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
b2f7b8ea-77c0-4abf-a2d6-7d4bc4a5753f | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
1305dbb2-1ad1-4d78-8c02-0e1fad51ec31 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
1305dbb2-1ad1-4d78-8c02-0e1fad51ec31 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
c0f6c0a4-9b29-4aff-be8b-48f6644b58af | Pole | 3 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
d9e26cf9-21a0-4f53-80dd-303a4f101037 | Pole | 3 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
ef4b15d5-cf62-44be-ac0f-cb1706e4c7a9 | Pole | 3 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
ef4b15d5-cf62-44be-ac0f-cb1706e4c7a9 | Pole | 3 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
e9dea076-9c89-4896-9bee-e385ecdda189 | Pole | 3 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
cd52c32c-2530-4859-83d8-4816e9be4f81 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
dcf503eb-c154-428e-af27-018054c4210a | Pole | 3 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
dcf503eb-c154-428e-af27-018054c4210a | Pole | 3 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
259c9db2-7921-4b51-93e7-b6c1312b0a85 | Pole | 3 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
16605c0b-8ebd-4751-9d83-36f23f36af91 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
076444f5-7fdf-4d74-89de-4b328f514659 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
076444f5-7fdf-4d74-89de-4b328f514659 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
1e92dcea-508e-4253-995c-db939f302bf1 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
1e92dcea-508e-4253-995c-db939f302bf1 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
eb0dbb3d-47b0-444f-8a7c-6b925c808b30 | Pole | 2 | Distribution | 2024-02-21 | 2025-02-20 | Level 2
eb0dbb3d-47b0-444f-8a7c-6b925c808b30 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
eb0dbb3d-47b0-444f-8a7c-6b925c808b30 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
62c7429a-6560-4289-bbb7-bf47f5a0d95f | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
62c7429a-6560-4289-bbb7-bf47f5a0d95f | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
bd841551-b843-40e1-9eb1-ea2c04c313b4 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
dea8cea6-5423-44b6-af12-97ef2c692e16 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
2f0e0c0b-fab2-459f-8b64-2846b1b0d241 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
2f0e0c0b-fab2-459f-8b64-2846b1b0d241 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
2f0e0c0b-fab2-459f-8b64-2846b1b0d241 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
28d7826f-4e42-4f15-aaac-53133db07be7 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
3c37ed16-cae0-4509-9503-4ab15e4304b0 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
d3cdb83a-0c6e-4bd5-9774-cb38b1504821 | Pole | 2 | Distribution | 2024-02-21 | 2024-02-23 | Level 1
5eb4ffee-7858-4da9-b13f-32a38787ee81 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
4c52a986-91d5-42ed-840a-e2a45299e2ba | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
b505b0ea-26e7-448e-8aaa-e4e4e527cf4b | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
fd3efeb9-b00e-47f1-bc32-5b236c612f1c | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
54133d9c-a936-4451-9b08-81c2d5ee5479 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
188dc025-7873-45d5-b698-8d33e5a6bc89 | Riser | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
32d7219a-ad37-4c16-9417-154bd9405b7e | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
64d55888-b88e-4d17-bd44-99bf9aa76a80 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
64d55888-b88e-4d17-bd44-99bf9aa76a80 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
64d55888-b88e-4d17-bd44-99bf9aa76a80 | Pole | 2 | Distribution | 2024-02-21 | 2029-02-19 | Level 3
b6c91c8d-ee3f-4c4f-9bbc-29a3759b01e2 | Pole | 2 | Distribution | 2024-02-16 | 2029-02-14 | Level 3
3118b7d2-5add-4642-b2b1-29b959ceb849 | Pole | 2 | Distribution | 2024-02-16 | 2029-02-14 | Level 3
194839d4-de7f-4f6c-8c8b-bc82c26efbb4 | Pole | 2 | Distribution | 2024-02-15 | 2029-02-13 | Level 3
1b9f3133-da71-4f86-8059-7e709fa520d9 | Pole | 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2
1b9f3133-da71-4f86-8059-7e709fa520d9 | Pole | 2 | Distribution | 2024-02-15 | 2029-02-13 | Level 3
1b9f3133-da71-4f86-8059-7e709fa520d9 | Pole | 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2
1b9f3133-da71-4f86-8059-7e709fa520d9 | Pole | 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2
845b72a1-26fb-4819-9500-4085861146f7 | Pole | 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2
845b72a1-26fb-4819-9500-4085861146f7 | Pole | 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2
845b72a1-26fb-4819-9500-4085861146f7 | Pole | 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2
845b72a1-26fb-4819-9500-4085861146f7 | Pole | 2 | Distribution | 2024-02-15 | 2025-02-14 | Level 2
775fb11a-3fda-492e-a4d5-7d9f87078058 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
95b93442-9eca-4ff0-b73c-0d3286d659ee | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
f68aacd1-1eb6-43eb-930c-f18c146ab1df | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
eec5f2f7-fc1c-4011-884d-e32a1db72c54 | Pole | 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2
a0254dad-ff8a-4a9e-9f18-a4d42850d45a | Pole | 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2
a0254dad-ff8a-4a9e-9f18-a4d42850d45a | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
3035188a-3e25-484d-af79-3d19185e2b6a | Pole | 3 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
ea89ee70-90ee-458d-a291-c72e6e29441c | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
b1d2ef54-7139-4685-8163-accee856723a | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
b1d2ef54-7139-4685-8163-accee856723a | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
1ed8852d-d909-407c-9222-f51332a8e99a | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
1ed8852d-d909-407c-9222-f51332a8e99a | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
1ed8852d-d909-407c-9222-f51332a8e99a | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
1ed8852d-d909-407c-9222-f51332a8e99a | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
2b7ba891-f3a3-453a-8b70-9edce9e8db97 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
2b7ba891-f3a3-453a-8b70-9edce9e8db97 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
2b7ba891-f3a3-453a-8b70-9edce9e8db97 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
bcfa7aa0-29c4-464b-9312-ac8df9f2bc28 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
7df3e4b7-a8b1-438e-b011-0a9efc8f9d40 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
298df510-33f2-46e0-8d22-c368d5c4776b | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
fea2fd5f-f621-49b7-bbe4-3e7b0686358a | Pole | 3 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
92a8e7c9-d186-4e55-b9f6-318472d9ca09 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
92a8e7c9-d186-4e55-b9f6-318472d9ca09 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
664ab5e5-34d5-428d-b9c9-548078ef2d3c | Pole | 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2
664ab5e5-34d5-428d-b9c9-548078ef2d3c | Pole | 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2
49d354a9-72b5-4cdf-b87c-49813a8422a2 | Pole | 3 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
20533ec5-10a8-43d3-9a1d-129b0785e8ee | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
3f547d7f-c752-4412-8bc0-76c15d53d6e4 | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
41457c93-b098-44c5-afa0-5139a62775bb | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
e84261f5-f41b-4454-b502-cafb95749f2d | Pole | 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2
ed6d4460-e20f-487e-9b8f-46ab9dc2caed | Pole | 2 | Distribution | 2024-02-14 | 2029-02-12 | Level 3
11405a2f-41ac-4e7f-987a-45667f405214 | Pole | 2 | Distribution | 2024-02-14 | 2025-02-13 | Level 2
ce62a33d-01e9-471d-8966-9f2d4504d2c6 | Pole | 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2
ce62a33d-01e9-471d-8966-9f2d4504d2c6 | Pole | 3 | Distribution | 2024-02-13 | 2029-02-11 | Level 3
ce62a33d-01e9-471d-8966-9f2d4504d2c6 | Pole | 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2
ce62a33d-01e9-471d-8966-9f2d4504d2c6 | Pole | 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2
beaeb331-4794-4c6b-afb2-3de498581578 | Pole | 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2
176f00d7-d95a-4c7a-afc9-ee8c719e9d94 | Pole | 2 | Distribution | 2024-02-13 | 2029-02-11 | Level 3
d61892bd-fe08-4de5-a8b6-756647743d51 | Pole | 2 | Distribution | 2024-02-13 | 2025-02-12 | Level 2
d61892bd-fe08-4de5-a8b6-756647743d51 | Pole | 2 | Distribution | 2024-02-13 | 2025-02-12 | Level 2
d61892bd-fe08-4de5-a8b6-756647743d51 | Pole | 2 | Distribution | 2024-02-13 | 2025-02-12 | Level 2
d61892bd-fe08-4de5-a8b6-756647743d51 | Pole | 2 | Distribution | 2024-02-13 | 2029-02-11 | Level 3
a8ccc48d-709a-481f-8461-f6fc56ccf4fd | Pole | 3 | Distribution | 2024-02-13 | 2029-02-11 | Level 3
a8ccc48d-709a-481f-8461-f6fc56ccf4fd | Pole | 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2
7d68a3b9-c9e2-43db-a39d-c988564809d4 | Pole | 2 | Distribution | 2024-02-13 | 2025-02-12 | Level 2
e4ed1a34-9d6e-4fd4-bfe5-9fc78a15d05f | Pole | 2 | Distribution | 2024-02-13 | 2025-02-12 | Level 2
f35e4648-aef7-4cc9-88f0-e9eade8a1858 | Pole | 3 | Distribution | 2024-02-13 | 2024-08-11 | Level 2
f241ef45-461b-4a35-bd67-ef692afe5555 | Pole | 3 | Distribution | 2024-02-13 | 2029-02-11 | Level 3
8247efed-3828-49fa-8eac-7aef3d24a5fd | Pole | 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2
5bde5c22-0ebe-4658-b7bc-f536803f6a03 | Pole | 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2
d861f6ee-166f-4c08-aeb0-8c4d72a55ca3 | Pole | 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2
2534eefb-099d-4a51-a84a-be2dfe1a792c | Pole | 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2
4625aea7-8dba-4237-9316-bc1f3328ce92 | Pole | 2 | Distribution | 2024-01-16 | 2025-01-15 | Level 2
fae02613-d589-4e8c-a3d6-29c241bfcad1 | Pole | 2 | Distribution | 2024-01-12 | 2025-01-11 | Level 2
d62e6a75-c027-43cf-8050-942c0ec6b8dc | Pole | 2 | Distribution | 2024-01-11 | 2029-01-09 | Level 3
c791edf1-18b5-4988-8e6e-e0d23f99770a | Pole | 2 | Distribution | 2024-01-11 | 2029-01-09 | Level 3
a3880147-5dc7-40f5-84c9-34ef098e1e47 | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
2da1ae28-2f23-4571-9820-32b5a63c0c2b | Pole | 0 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
a5befc16-47c5-47ca-ab71-944f89a76aad | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
8756a12a-4283-45bf-b1f4-5b4cde181873 | Pole | 2 | Distribution | 2024-01-10 | 2029-01-08 | Level 3
32f36530-b6bf-4f75-9882-d9f09a6929c6 | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
2bed610e-e932-4c0b-935f-c229000750d7 | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
a928e29d-a51b-4873-b69f-a3904174f356 | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
27fb9d55-dc74-47ae-a07d-2465bc122ad6 | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
3e30d935-8fe5-4e2a-b4d8-7f2085915154 | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
a26490e1-c6be-4596-9b66-14fbc88ab3f5 | Pole | 2 | Distribution | 2024-01-10 | 2029-01-08 | Level 3
8b5ce0a3-54d0-4021-b461-2ad99d409e6d | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
4ee2e521-4749-4c88-9f7f-d3b0fc3f4a1c | Pole | 2 | Distribution | 2024-01-10 | 2024-01-12 | Level 1
ad0de065-8cf6-4cb1-9660-b3b917665ddc | Pole | 2 | Distribution | 2024-01-10 | 2025-01-09 | Level 2
8a2bc592-feb1-4115-a54b-37208522d155 | Pole |  | Distribution | 2023-12-21 | 2028-12-19 | Level 3
1c02d811-0872-4269-9df3-741dca98edb5 | Pole |  | Distribution | 2023-12-21 | 2024-12-20 | Level 2
84611a73-f50d-47ac-a2c4-4c59368aff1e | Pole |  | Distribution | 2023-12-21 | 2024-12-20 | Level 2
c422d3c3-8743-4ec1-8e9a-307d896352eb | Pole |  | Distribution | 2023-12-21 | 2024-12-20 | Level 2
44494ca6-0c34-4c1f-94fe-09b23d040d7a | Pole |  | Distribution | 2023-12-21 | 2024-12-20 | Level 2
bdca8d03-4baa-4ae8-b0dd-34a747f1ef63 | Pole |  | Distribution | 2023-12-21 | 2024-12-20 | Level 2
6a1056b6-7305-4e70-be08-26787064493c | Pole |  | Distribution | 2023-12-21 | 2024-12-20 | Level 2
8ce98fc7-1ab9-44f7-a5ae-ea185e90f154 | Pole |  | Distribution | 2023-12-21 | 2024-12-20 | Level 2
bcacf0bb-e722-4436-bb29-27cf4e90e43b | Pole |  | Distribution | 2023-12-21 | 2024-12-20 | Level 2
7f362a64-449f-4d6b-b913-cfd55b773b3d | Pole |  | Distribution | 2023-12-20 | 2023-12-22 | Level 1
0b050c6b-3321-4550-b545-ad0798795044 | Pole |  | Distribution | 2023-12-06 | 2023-12-08 | Level 1
aac7007e-dcad-4a73-8e94-9a8b5485b683 | Pole |  | Distribution | 2023-12-06 | 2028-12-04 | Level 3
671703ec-debb-4cb2-aa90-53dba2de032a | Pole |  | Distribution | 2023-11-29 | 2024-11-28 | Level 2
2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3
2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
2fab22df-f859-4475-940d-4c45dab5f3bf | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3
760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
760ac6f1-0649-4c3b-aad4-31ea10535f27 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
8c88d310-3666-42b8-958a-60e712547a25 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
8c88d310-3666-42b8-958a-60e712547a25 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
8c88d310-3666-42b8-958a-60e712547a25 | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
8c88d310-3666-42b8-958a-60e712547a25 | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3
f977c13d-1b5e-4a1b-bc1e-a8696300c618 | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3
e7ad16db-7eb9-4506-af8c-d4cdd950697e | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3
15c83ebc-94ba-4f4b-88f7-50f451ff2dca | Pole | 2 | Distribution | 2023-10-17 | 2028-10-15 | Level 3
859eb4ab-bd5b-4954-96f4-76aef8b1990c | Pole | 2 | Distribution | 2023-10-17 | 2024-10-16 | Level 2
e532f368-125e-499a-b6fa-abb72ec66f2d | UG Transformer | 2 | Distribution | 2023-10-16 | 2028-10-14 | Level 3
9686b69f-fe7d-46a5-bc05-effa7b4791cf | UG Transformer | 2 | Distribution | 2023-10-16 | 2024-10-15 | Level 2
9686b69f-fe7d-46a5-bc05-effa7b4791cf | UG Transformer | 2 | Distribution | 2023-10-16 | 2028-10-14 | Level 3
be4be738-c74c-43c7-9491-4da142e1c2d5 | Pole | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3
be4be738-c74c-43c7-9491-4da142e1c2d5 | Pole | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3
50a11142-f99e-4a9b-884f-2a088221c9d4 | UG Transformer | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3
ae9bc4da-b916-4258-952e-8a9000986684 | Pole | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3
ae909aec-b467-4283-94a5-a037d6e84479 | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2
50a11142-f99e-4a9b-884f-2a088221c9d4 | UG Transformer | 2 | Distribution | 2023-10-13 | 2028-10-11 | Level 3
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2
f08a1c39-c006-4e72-abb2-015de7e0e8ef | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2
a7d573e9-2a48-4bb2-b378-e5290a7f9a40 | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2
2da4b3a5-6afc-42c2-9eb3-fdb0620d0cd2 | Pole | 2 | Distribution | 2023-10-13 | 2024-10-12 | Level 2
f941ba6b-a553-40c4-9c7f-bed3fa9860cf | UG Transformer | 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3
e40d9236-f6c0-4ad0-9875-9aa53573e7b7 | UG Transformer | 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3
3e7c9e46-6945-4a6a-b6b8-87aacbac709b | UG Transformer | 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3
7524fd8e-bb2e-48bc-9393-910728de7545 | UG Transformer | 2 | Distribution | 2023-10-12 | 2028-10-10 | Level 3
f38d1b8e-ca13-40da-b5bf-e10b96a49c77 | Pole | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3
f38d1b8e-ca13-40da-b5bf-e10b96a49c77 | Pole | 2 | Distribution | 2023-10-05 | 2024-10-04 | Level 2
b9da561a-be1f-4b06-9b72-41d54cf2060d | Pole | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3
9b67dfee-4368-47cc-b862-6ea82e09b621 | UG Transformer | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3
9b67dfee-4368-47cc-b862-6ea82e09b621 | UG Transformer | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3
ed94cc9b-ad66-4cbb-9bc9-2557f329cdd7 | UG Transformer | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3
ed94cc9b-ad66-4cbb-9bc9-2557f329cdd7 | UG Transformer | 2 | Distribution | 2023-10-05 | 2028-10-03 | Level 3
4298ab5f-2240-400d-b9f9-c93090400e23 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2
73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2
73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | 2 | Distribution | 2023-10-04 | 2028-10-02 | Level 3
73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2
73d0a1b3-d946-40f3-8911-68f3e82fb879 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2
01f1ae25-1fce-49eb-b04b-e5563c344c43 | Pole | 2 | Distribution | 2023-10-04 | 2024-10-03 | Level 2
af3dbaf5-db9f-4fa2-a3ed-4492bd352c94 | Switch | 2 | Distribution | 2023-10-03 | 2024-10-02 | Level 2
0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
0f71aed6-bfaa-4316-bb33-832cf384f5c3 | UG Transformer | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2
af631e78-0929-4686-9a6b-6190295ebaf6 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
af631e78-0929-4686-9a6b-6190295ebaf6 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
06a9c6ff-20c6-4e52-ae0b-d1dc51eeab04 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
65e0dc54-a129-47ad-8900-878ef9a2673f | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
65e0dc54-a129-47ad-8900-878ef9a2673f | UG Transformer | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2
2792b831-c0ae-4289-829a-1cff99e1ee30 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
2792b831-c0ae-4289-829a-1cff99e1ee30 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
49fa9a73-c609-4c81-ac09-04d2031aa554 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
48070ade-2503-4d1c-8c35-0d8de2eb81b7 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
48070ade-2503-4d1c-8c35-0d8de2eb81b7 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
1081d5d3-15b3-4cb2-b489-94416ac1a91c | UG Transformer | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2
ce1111e2-8fac-4ba8-88a7-65568b7cb270 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
cc8d5550-a21c-41f5-ac6f-c72f38125443 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
721f0bad-bdc0-4009-b93c-0da5657c30d5 | Switch | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
721f0bad-bdc0-4009-b93c-0da5657c30d5 | Switch | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2
da05f32c-ca4e-4a28-93d2-c3d362dde5a9 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
12493a3a-71c6-4597-ab06-bc306445855b | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
9da09cb6-02b1-4a88-8ff9-5a27491d333e | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
b9f088c5-f33a-4df0-a65b-3ea2bc138839 | UG Transformer | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2
635cc53a-4aa4-44a1-9cde-e27e3770b3d6 | UG Transformer | 2 | Distribution | 2023-10-02 | 2028-09-30 | Level 3
288ac579-f6b2-4403-bbbd-b79504d89df8 | Switch | 2 | Distribution | 2023-10-02 | 2024-10-01 | Level 2
d2febd0a-0747-4f4a-9421-eb17077d2a0a | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
9f969ff6-a0c5-4b20-be78-045a5e279531 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
479fe971-dd07-4db5-9b7d-41c8c4bcbb76 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
479fe971-dd07-4db5-9b7d-41c8c4bcbb76 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
479fe971-dd07-4db5-9b7d-41c8c4bcbb76 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
924d244c-ad54-45ba-8d18-fbb9bcab7d6f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
924d244c-ad54-45ba-8d18-fbb9bcab7d6f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
9f969ff6-a0c5-4b20-be78-045a5e279531 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
9f969ff6-a0c5-4b20-be78-045a5e279531 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
9f969ff6-a0c5-4b20-be78-045a5e279531 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
a9de1709-e999-4e83-bc0a-df157bd8b344 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
a9de1709-e999-4e83-bc0a-df157bd8b344 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
c28261fa-ee8d-460b-b3b8-df13b799d57c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
c28261fa-ee8d-460b-b3b8-df13b799d57c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
934872c2-62f5-4f7a-baf2-650a2b6b3524 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
934872c2-62f5-4f7a-baf2-650a2b6b3524 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
934872c2-62f5-4f7a-baf2-650a2b6b3524 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
076a13fc-43a3-44af-bfaf-a0857f212781 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
076a13fc-43a3-44af-bfaf-a0857f212781 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
076a13fc-43a3-44af-bfaf-a0857f212781 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
076a13fc-43a3-44af-bfaf-a0857f212781 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
fcbb726b-86cb-4953-b87d-17a403085c2f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
fcbb726b-86cb-4953-b87d-17a403085c2f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
fcbb726b-86cb-4953-b87d-17a403085c2f | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
f6641e66-79ca-4573-b56d-a6560043c1e9 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f6641e66-79ca-4573-b56d-a6560043c1e9 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f6641e66-79ca-4573-b56d-a6560043c1e9 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f6641e66-79ca-4573-b56d-a6560043c1e9 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
924d244c-ad54-45ba-8d18-fbb9bcab7d6f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
924d244c-ad54-45ba-8d18-fbb9bcab7d6f | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
44b8da88-1a2b-4d06-8274-6c05fc9b61ea | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
44b8da88-1a2b-4d06-8274-6c05fc9b61ea | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
44b8da88-1a2b-4d06-8274-6c05fc9b61ea | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
44b8da88-1a2b-4d06-8274-6c05fc9b61ea | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
bf590aa0-a752-4941-b813-c89467ba4baa | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f55fff51-3b3d-4dc4-a4f5-556c5ea2b3bc | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
ca4d0fdd-4da8-4684-a8b9-a6348c94fa83 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
e9e49e1b-02c4-434c-b6c6-d4044824a19c | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
bef63843-2ac4-40d1-b728-39db7cf5e273 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
2b03bd47-b7a0-4e06-9f78-7aad37331951 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
2b03bd47-b7a0-4e06-9f78-7aad37331951 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
2b03bd47-b7a0-4e06-9f78-7aad37331951 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
2b03bd47-b7a0-4e06-9f78-7aad37331951 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
73bc6ea5-d236-43e1-a839-f9165107cb0c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
73bc6ea5-d236-43e1-a839-f9165107cb0c | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
f7dc9064-5ee5-4ca7-8204-9974d4279645 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
f7dc9064-5ee5-4ca7-8204-9974d4279645 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
e3fc905f-6ada-4f76-9a48-7cdaefa40d10 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
e3fc905f-6ada-4f76-9a48-7cdaefa40d10 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
e3fc905f-6ada-4f76-9a48-7cdaefa40d10 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
e3fc905f-6ada-4f76-9a48-7cdaefa40d10 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
0dbcbabc-72d2-4af7-8ba2-c96e1fb9da13 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
a9de1709-e999-4e83-bc0a-df157bd8b344 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
0dbcbabc-72d2-4af7-8ba2-c96e1fb9da13 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
0dbcbabc-72d2-4af7-8ba2-c96e1fb9da13 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2028-09-27 | Level 3
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
a0c655b0-118b-4887-9e8f-a09cc7dac16d | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
d2febd0a-0747-4f4a-9421-eb17077d2a0a | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
d2febd0a-0747-4f4a-9421-eb17077d2a0a | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
d2febd0a-0747-4f4a-9421-eb17077d2a0a | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
80776df3-5760-400c-9a84-13a7446f4e31 | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
0a6fdbbf-57dc-4bfa-813c-73e8c9ae22cd | Pole | 2 | Distribution | 2023-09-29 | 2024-09-28 | Level 2
3f76948d-08f8-4ecd-a084-d88560053acc | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
28b2c850-2182-47ff-8508-2bae4904181c | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2
c2a78614-0a87-40a5-801b-120e11e0b2c6 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2
c2a78614-0a87-40a5-801b-120e11e0b2c6 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2
451a8d6e-75fe-4e3c-a750-adb3a9f84d86 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
451a8d6e-75fe-4e3c-a750-adb3a9f84d86 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
3e326912-ac6a-4eaa-b012-d6d799777bd5 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2
956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
956322ed-693a-4bb9-bcbe-487f03805ca9 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
454ceea3-c978-4c25-bd41-d6dba6c19948 | Pole | 2 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
c2a78614-0a87-40a5-801b-120e11e0b2c6 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2
c2a78614-0a87-40a5-801b-120e11e0b2c6 | Pole | 2 | Distribution | 2023-09-25 | 2024-09-24 | Level 2
9ca5e4b5-5013-4c2f-9e35-9e998e0da0f1 | Pole | 0 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
be91dead-a04f-4479-8398-32f972af61cf | Pole | 0 | Distribution | 2023-09-25 | 2028-09-23 | Level 3
1c878b6f-c6bf-41d6-93bb-0eab61c70797 | Pole | 2 | Distribution | 2023-09-09 | 2028-09-07 | Level 3
81b94aa9-cd3e-418c-85d6-3285fb6db3c1 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2
81b94aa9-cd3e-418c-85d6-3285fb6db3c1 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2
81b94aa9-cd3e-418c-85d6-3285fb6db3c1 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2
8ed218e7-d598-4c1b-9df7-b2428423e115 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2
8ed218e7-d598-4c1b-9df7-b2428423e115 | Pole | 2 | Distribution | 2023-09-09 | 2024-09-08 | Level 2
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2024-08-30 | Level 2
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2028-08-29 | Level 3
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2024-08-30 | Level 2
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2024-08-30 | Level 2
e1617b9f-e750-406d-b7b1-65e478a4eb35 | Pole | 2 | Distribution | 2023-08-31 | 2024-08-30 | Level 2
9fbe3716-89f7-470e-83ab-e7d6314272b3 | UG Transformer | 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3
2693dc3e-af8b-4bd7-867e-45e1c3c67bcb | UG Transformer | 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3
2693dc3e-af8b-4bd7-867e-45e1c3c67bcb | UG Transformer | 2 | Distribution | 2023-08-26 | 2028-08-24 | Level 3
c2a30b56-94ba-41ac-870b-2e2d90302857 | Pole | 2 | Distribution | 2023-08-25 | 2028-08-23 | Level 3
a0078f0f-ceda-4456-9c0a-f744f7a00be5 | Pole | 2 | Distribution | 2023-08-25 | 2024-08-24 | Level 2
c2a30b56-94ba-41ac-870b-2e2d90302857 | Pole | 2 | Distribution | 2023-08-25 | 2024-08-24 | Level 2
ae387d68-5ba9-4ed3-b38c-45548ab67474 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3
ae387d68-5ba9-4ed3-b38c-45548ab67474 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3
450c2c55-7a7d-4fb8-bc95-3a7ec2fe20ac | UG Transformer | 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2
c4d9e107-dfed-4445-baa4-4059dfa7169b | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3
c4d9e107-dfed-4445-baa4-4059dfa7169b | UG Transformer | 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2
967ae741-4d1a-44db-afc7-09ef9c374019 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3
967ae741-4d1a-44db-afc7-09ef9c374019 | UG Transformer | 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2
7558a656-f808-4736-b44a-666d0a6cc3d6 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3
7558a656-f808-4736-b44a-666d0a6cc3d6 | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3
73ec8ebb-cf59-4ee3-bcc7-ed63994907d0 | UG Transformer | 2 | Distribution | 2023-08-24 | 2024-08-23 | Level 2
450c2c55-7a7d-4fb8-bc95-3a7ec2fe20ac | UG Transformer | 2 | Distribution | 2023-08-24 | 2028-08-22 | Level 3
e0f03e02-e426-44f6-b5f7-8817feb70c65 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
5183bf2a-f940-4956-9189-e7ebc55d13d6 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
3527813a-a393-4926-a21d-3f48666ded19 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
052d70c3-0dd1-477b-816f-398ad52e2139 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
27992f4d-4d86-4b0c-9617-6f79476238e3 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
a909370a-782c-4066-af7f-cfa579d5ba85 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
4e022486-b6e0-4213-9f55-ecb5ab221f55 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
67e41575-96fe-497d-b435-7995e89f775d | Pole | 3 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
3c98da15-44e3-41ae-b017-2c519209b370 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
b18c1b61-daa4-4535-856e-c45919e8cd3a | Pole | 3 | Distribution | 2023-08-23 | 2024-02-19 | Level 2
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
69f53c3c-0aad-4458-94ab-5e7e0eaea428 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
19c2175d-2f27-4451-814f-43f4f026845c | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
19c2175d-2f27-4451-814f-43f4f026845c | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
7919200a-7112-4a35-b12a-0d9494d95094 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
7919200a-7112-4a35-b12a-0d9494d95094 | Pole | 2 | Distribution | 2023-08-23 | 2024-08-22 | Level 2
a7150367-c843-44e0-b95e-ac182f9d7c85 | Pole | 3 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
e1963b4b-b01c-4f34-8ba4-8d299acd4ce3 | Pole | 3 | Distribution | 2023-08-23 | 2024-02-19 | Level 2
378d6b5b-47a4-437b-9ff8-249935065b0c | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
c5376880-6048-4e10-947d-59f22e59a67c | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
4ae0a9da-9ecb-48e4-a553-8b68d38c57f5 | Pole | 2 | Distribution | 2023-08-23 | 2028-08-21 | Level 3
5c223a31-d36f-4881-82a6-fe3ced9f3622 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
4b67c191-306b-4682-b7c8-5f538566f82e | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
cb9dd658-63b7-421c-b26f-7c3dd33b4280 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
1d97789e-38ac-4121-baf3-7b091231b6b1 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
1d97789e-38ac-4121-baf3-7b091231b6b1 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
4b67c191-306b-4682-b7c8-5f538566f82e | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
ab926a43-ca86-4277-92e0-3d020c7ef43c | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
1f01ba0a-da2a-4971-aeb1-ada765205f84 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
bcf43e93-ebb3-4c85-b585-823195ae952b | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
f1f0595e-0a49-4c17-98c9-c8c5db110fa1 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
eddd4f53-4663-46b7-9fe6-72ab8be16f36 | UG Transformer | 2 | Distribution | 2023-08-22 | 2024-08-21 | Level 2
abee0617-1a2f-4b78-bf34-fbbda211f50a | UG Transformer | 2 | Distribution | 2023-08-22 | 2028-08-20 | Level 3
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
73e409f3-fa03-4f5f-a1e5-ebb0a3a91790 | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
a6565349-b1ac-48c1-b8c8-031fbcb41239 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
a6565349-b1ac-48c1-b8c8-031fbcb41239 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
674aefc2-2390-4ed3-a25c-78b5b0d6c719 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
cb29fbc4-d545-4512-bec6-05266cb4f477 | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
cb29fbc4-d545-4512-bec6-05266cb4f477 | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
cb29fbc4-d545-4512-bec6-05266cb4f477 | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
ef93f18a-691d-4d20-a12e-d48025270f00 | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
0acb74fa-7883-4a85-b9a3-f513fea01aff | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
0acb74fa-7883-4a85-b9a3-f513fea01aff | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
2a4934cd-e59b-4db0-98c6-a99181eebd7d | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
97c3c1d6-4931-45d7-ae00-f2f00e1230a4 | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
97c3c1d6-4931-45d7-ae00-f2f00e1230a4 | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
243eb73c-1079-4460-b014-11010f14499d | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
1b903c86-ae6f-463c-b711-8a33598e8f0f | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
1b903c86-ae6f-463c-b711-8a33598e8f0f | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
243eb73c-1079-4460-b014-11010f14499d | UG Transformer | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
1b903c86-ae6f-463c-b711-8a33598e8f0f | Pole | 0 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
1b903c86-ae6f-463c-b711-8a33598e8f0f | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
241092c0-de49-41b2-ba3b-22298028dbc2 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
0acb74fa-7883-4a85-b9a3-f513fea01aff | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2028-08-15 | Level 3
3547413e-91f8-46e9-89d7-62a78d3c4701 | Pole | 2 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3dfe3964-b15a-4a31-b454-d7adf6158eee | Pole | 0 | Distribution | 2023-08-17 | 2024-08-16 | Level 2
3572f41a-64d5-40dd-9945-95f16d8538fd | UG Transformer | 2 | Distribution | 2023-08-16 | 2024-08-15 | Level 2
035b289e-8b69-420a-897b-580b94e3a585 | Regulator | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
b43a8611-d1a5-4101-8cec-3edd7f69d696 | UG Transformer | 2 | Distribution | 2023-08-16 | 2024-08-15 | Level 2
58fc35cb-6f1e-4dbb-9786-70e9d7ca44a4 | Switch | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
b52016fc-3acb-4e82-aa9d-96145b447b64 | Switch | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
fd043d17-f221-4afc-9ae2-eb78936e6e24 | Switch | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
be95c557-170f-4528-b577-6b0ac7125401 | Regulator | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
4bcfeaa3-a764-4a04-b3af-0a8d7fc7abc3 | Regulator | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
3572f41a-64d5-40dd-9945-95f16d8538fd | UG Transformer | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
d22ee777-ac34-4da4-b5e4-5e2f8178894b | UG Transformer | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
d22ee777-ac34-4da4-b5e4-5e2f8178894b | UG Transformer | 2 | Distribution | 2023-08-16 | 2028-08-14 | Level 3
dae95481-ead8-4a05-b671-d263130d6fec | Pole | 0 | Distribution | 2023-08-15 | 2024-08-14 | Level 2
dae95481-ead8-4a05-b671-d263130d6fec | Pole | 0 | Distribution | 2023-08-15 | 2028-08-13 | Level 3
c374ec53-facb-48a6-9610-a660e7cb5af6 | Pole | 0 | Distribution | 2023-08-15 | 2028-08-13 | Level 3
70442009-34a9-4cbf-b9d3-e9d99e77da76 | UG Transformer | 2 | Distribution | 2023-08-15 | 2028-08-13 | Level 3
2051e2e1-8ae2-4dc5-8c39-aeca041a3b22 | Pole | 2 | Distribution | 2023-08-15 | 2024-08-14 | Level 2
d3fb262c-bcf5-400c-ad9a-ad7f3cd07310 | Pole | 2 | Distribution | 2023-08-15 | 2024-08-14 | Level 2
7003eb97-7f50-4bad-9bff-4f9eb93ec3c9 | Pole | 2 | Distribution | 2023-08-15 | 2024-08-14 | Level 2
d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2
d71ef5f4-8dd2-42ff-872d-374c6a58ed0c | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
d2aa4357-e6cb-49e9-8eda-18bc94d1aeaa | Pole | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
d2aa4357-e6cb-49e9-8eda-18bc94d1aeaa | Pole | 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2
ebc37288-97d0-4831-bf37-2bd2db97971a | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
ebc37288-97d0-4831-bf37-2bd2db97971a | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
85041ef2-c7b8-4a1c-8eb9-f44d77321aaf | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
74ccbbf1-373a-4547-9d92-8db63838cf50 | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
880fb73d-b44a-4791-9c41-3ef1915f5d9a | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
1d81d75f-7f6b-494e-8104-fa638a5436f1 | UG Transformer | 2 | Distribution | 2023-08-14 | 2024-08-13 | Level 2
4ddf43cc-990a-4c97-9677-bb8dea4f69bc | UG Transformer | 2 | Distribution | 2023-08-14 | 2028-08-12 | Level 3
72619d12-57c1-4cfd-858d-d6429a087f47 | Pole | 2 | Distribution | 2023-08-12 | 2024-08-11 | Level 2
72619d12-57c1-4cfd-858d-d6429a087f47 | Pole | 2 | Distribution | 2023-08-12 | 2024-08-11 | Level 2
72619d12-57c1-4cfd-858d-d6429a087f47 | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3
dce7f710-19f1-46a5-93d7-ca8fce00a2c4 | Pole | 2 | Distribution | 2023-08-12 | 2024-08-11 | Level 2
dce7f710-19f1-46a5-93d7-ca8fce00a2c4 | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3
0f4a8e90-636e-4fae-9205-20df91f47aa2 | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3
1a9baa8a-4da2-46be-b5f9-8319d9775b63 | Pole | 2 | Distribution | 2023-08-12 | 2024-08-11 | Level 2
1a9baa8a-4da2-46be-b5f9-8319d9775b63 | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3
1e6ec8fc-b023-476e-9371-4052357e670e | Pole | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3
74f2946d-e8e1-4874-a36f-b2eb8b6e8efa | UG Transformer | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3
af44782d-e74a-4eb5-b8c7-a9d5a0a793eb | UG Transformer | 2 | Distribution | 2023-08-12 | 2028-08-10 | Level 3
32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | 0 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | 0 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
8555842f-337a-4c33-bf06-c60d6315ab95 | Pole | 0 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
32c83549-6e48-4748-bc9f-be374873b04c | UG Transformer | 0 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
0b2edd57-e419-4eeb-ad72-8c1b26ee7304 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
d8734d5c-5be0-4675-8733-c8211ac8ae97 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
ca5b3a34-133b-4062-ab26-c2695a6a7af5 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
ca5b3a34-133b-4062-ab26-c2695a6a7af5 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
577fb3b6-ae0f-4dc3-b71d-18a1b8a0e27a | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
db4777bf-e97f-425f-8bef-b4bba2f36e29 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
fbf22393-af38-4629-9fab-fbb52ab7e6f5 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
fbf22393-af38-4629-9fab-fbb52ab7e6f5 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
791f0da6-307c-4228-b721-3ee92d30b220 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
791f0da6-307c-4228-b721-3ee92d30b220 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | 2 | Distribution | 2023-08-11 | 2024-08-10 | Level 2
a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
a17f537d-e825-4492-9a41-0d1fec36fe33 | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
db82a00c-8503-4cb5-9ccc-66e0785dc73b | Pole | 2 | Distribution | 2023-08-11 | 2028-08-09 | Level 3
33312161-3410-46df-84e9-d1dd54121209 | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
9d2b8689-6f67-47d8-836e-22d1ab556f65 | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
093fa2a8-d25c-4951-9f25-66114e85a606 | Pole | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2
093fa2a8-d25c-4951-9f25-66114e85a606 | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
161f5bb3-c408-4270-bdf1-bf56d9c4c13d | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2
3bae045f-37d0-4825-b326-16dea303f216 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
a79307d7-546e-4597-a553-3f902306e604 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
314ac0bd-372e-4280-9274-9b5ca92c9c61 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
314ac0bd-372e-4280-9274-9b5ca92c9c61 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
0ceb50c6-05d1-42b3-906e-64786005e8a1 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
95ae16f9-0c3f-4f76-9844-46551ff52b15 | UG Transformer | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
3467600c-882b-4022-91be-fca076f96adf | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
87fbfaeb-7e6a-4a78-a7f1-1fc13357485a | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
87fbfaeb-7e6a-4a78-a7f1-1fc13357485a | Pole | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2
4b0aea41-8804-4fb4-8a8a-08d0274b2831 | UG Transformer | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2
bb03438a-f3cf-4993-94dd-d0657497b523 | Pole | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2
bb03438a-f3cf-4993-94dd-d0657497b523 | Pole | 2 | Distribution | 2023-08-10 | 2028-08-08 | Level 3
cdb667a1-1ad6-4674-b6f1-603bb9edd36b | Pole | 2 | Distribution | 2023-08-10 | 2024-08-09 | Level 2
8f0d7149-73bc-4b2f-99a6-0318bfdb78cc | Pole | 2 | Distribution | 2023-08-09 | 2024-08-08 | Level 2
8f0d7149-73bc-4b2f-99a6-0318bfdb78cc | Pole | 2 | Distribution | 2023-08-09 | 2024-08-08 | Level 2
7e885feb-4419-487c-91bb-27338a56f9a5 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
7e885feb-4419-487c-91bb-27338a56f9a5 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
fe5bfd0b-16da-41b5-987e-49529d383f01 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
da6c581b-31d0-40ba-9637-f04d7aff0249 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
82437ccc-2689-4506-ad18-0157147e699c | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
749cb7b6-ff3f-4210-972f-9933fde66bc7 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
b805ba8c-daf1-49e1-bdd8-1e25a7d47bde | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
b805ba8c-daf1-49e1-bdd8-1e25a7d47bde | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
ee55da44-c3eb-4e14-8912-39dbdee235c7 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
ee55da44-c3eb-4e14-8912-39dbdee235c7 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
0b64d76e-2543-4a3a-8a17-825bfe157b67 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
b218a9e9-8a18-45c5-b10c-462d491586f3 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
b218a9e9-8a18-45c5-b10c-462d491586f3 | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
e74cded5-9d7d-4bd5-8faa-f679f828d05a | UG Transformer | 2 | Distribution | 2023-08-09 | 2028-08-07 | Level 3
1babbb9c-0c0f-4bd8-82d9-b572619de616 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
2ba08818-e9bf-422d-aaa7-ab5a3bab4546 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
2ba08818-e9bf-422d-aaa7-ab5a3bab4546 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
e17fde17-4dd0-4c45-bcc3-702827eff6ac | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
e17fde17-4dd0-4c45-bcc3-702827eff6ac | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
88252c7e-6d45-470a-b69c-26eb176c7432 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
88252c7e-6d45-470a-b69c-26eb176c7432 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
59699ea0-8488-4955-9d2b-fdab627fef4a | Switch | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
5d68e8d9-9a66-4b4b-844c-8223382e3a42 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
e4ff76a1-858f-401c-9a22-d3cff50d08b7 | Switch | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
53bd6099-69d1-483e-a6cf-7b951353ec9e | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
7429ccf5-9ca6-43d7-b891-0fe7e19f2253 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
7870c4d6-8685-47ab-bd95-6728d82ca87a | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
91f4fd99-78af-4227-b5b7-031d0e4affd6 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
90021dbd-8aca-4229-b8cc-b270799a24e3 | UG Transformer | 2 | Distribution | 2023-08-08 | 2028-08-06 | Level 3
10ae7c58-8fa2-4cd7-a833-ef3d619c4ec5 | Pole | 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3
10ae7c58-8fa2-4cd7-a833-ef3d619c4ec5 | Pole | 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3
73a6df4e-5dbd-4be3-922f-33dbee3e7c57 | Pole | 2 | Distribution | 2023-08-07 | 2028-08-05 | Level 3
09c1127f-65e4-48d6-bfa4-de86496d3774 | Pole | 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3
bc6b4799-6f59-4023-9b1e-c65c956a92d1 | Pole | 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3
bc6b4799-6f59-4023-9b1e-c65c956a92d1 | Pole | 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3
bc6b4799-6f59-4023-9b1e-c65c956a92d1 | Pole | 2 | Distribution | 2023-08-05 | 2024-08-04 | Level 2
f99b957b-a5aa-4bbc-945b-b19030d27d28 | UG Transformer | 0 | Distribution | 2023-08-05 | 2028-08-03 | Level 3
c4448545-1165-4d71-a048-f6684059948c | UG Transformer | 2 | Distribution | 2023-08-05 | 2024-08-04 | Level 2
5f7a055b-0b79-4eb7-ad9d-fcbc99612a1d | Pole | 2 | Distribution | 2023-08-05 | 2028-08-03 | Level 3
56a68e5b-2c48-43e3-a8da-16edf14cceb6 | UG Transformer | 2 | Distribution | 2023-08-03 | 2028-08-01 | Level 3
082bc590-82be-4263-a6ad-85ad8d9c7188 | UG Transformer | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3
082bc590-82be-4263-a6ad-85ad8d9c7188 | UG Transformer | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3
25af01c1-9801-496b-90e4-e65b797d48ee | Pole | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3
25af01c1-9801-496b-90e4-e65b797d48ee | Pole | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3
eb774b59-de36-441d-93d4-8c091737890c | Padmount-Ã¡Transformer | 2 | Distribution | 2023-08-02 | 2028-07-31 | Level 3
2793fa60-d2b9-4cca-a62e-dc50a1e0ad2e | Padmount-Ã¡Transformer | 2 | Distribution | 2023-07-31 | 2028-07-29 | Level 3
7e5a12fe-6157-4700-9c6a-a1f982c4cd01 | Riser | 2 | Distribution | 2023-07-31 | 2024-07-30 | Level 2
9766ac52-a5e1-4943-a0e2-ff337b47fe92 | Riser | 2 | Distribution | 2023-07-29 | 2024-07-28 | Level 2
eb2872bd-5e84-4c7f-aa02-d14288984733 | Riser | 2 | Distribution | 2023-07-29 | 2024-07-28 | Level 2
ba4bcd27-6cd3-4d1a-9b6f-d7f0bf6bd8f5 | Riser | 2 | Distribution | 2023-07-29 | 2024-07-28 | Level 2
c5dab43e-e49f-4c2e-842b-d4428b4e5bfb | UG Transformer | 2 | Distribution | 2023-07-27 | 2028-07-25 | Level 3
69c8ea18-805f-443f-a05c-f403b2bddf72 | UG Transformer | 2 | Distribution | 2023-07-27 | 2028-07-25 | Level 3
1f8396a4-2003-411e-8a92-26ae4922a60e | UG Transformer | 2 | Distribution | 2023-07-26 | 2024-07-25 | Level 2
534a7df3-9755-460a-bd78-d6a7c7e31ac8 | Riser | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
c78ce37a-934b-40ec-822a-442348cf622e | Switching Cabinet | 3 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
4bf70ddf-7dc4-48ef-9ba0-61358f8feb4a | UG Transformer | 3 | Distribution | 2023-07-26 | 2024-01-22 | Level 2
32dbcdef-7633-4ce8-81f1-b695548afc69 | UG Transformer | 3 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
b8e1015c-ec15-447a-8948-7c0dfb644321 | UG Transformer | 3 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
b8e1015c-ec15-447a-8948-7c0dfb644321 | UG Transformer | 3 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
1a962da0-3d35-42ac-8569-eeb9469d0149 | UG Transformer | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
1a962da0-3d35-42ac-8569-eeb9469d0149 | UG Transformer | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
fe13df30-50b6-4649-86a1-fda96e1ec7fb | UG Transformer | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
fe13df30-50b6-4649-86a1-fda96e1ec7fb | UG Transformer | 2 | Distribution | 2023-07-26 | 2028-07-24 | Level 3
b7fc6ee5-d271-4f61-9b80-a83955dfa9a2 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
52d38d9c-097e-4a94-a033-d1f94cfd012c | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
52d38d9c-097e-4a94-a033-d1f94cfd012c | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
ac491658-8fa0-4a9e-adf9-9204f4d81b63 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
ac491658-8fa0-4a9e-adf9-9204f4d81b63 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
ac491658-8fa0-4a9e-adf9-9204f4d81b63 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
ac126868-4db8-486b-a976-8ff9827e43ae | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
ac126868-4db8-486b-a976-8ff9827e43ae | UG Transformer | 2 | Distribution | 2023-07-25 | 2024-07-24 | Level 2
d2948cc4-7a18-4455-aaca-c89025d24c6c | Riser | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
06e0e8ca-9fab-4761-b25a-8f17c53680f3 | UG Transformer | 2 | Distribution | 2023-07-25 | 2028-07-23 | Level 3
9fc88b18-a7dd-423e-a8b5-f331c46c2738 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
9fc88b18-a7dd-423e-a8b5-f331c46c2738 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
4f84e8df-fafa-434e-b488-fc1cb576a412 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
eea04e77-bdf2-4014-a362-d1d8bb2f9418 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
3d3adacd-688a-4df5-b1fb-da3131f3fd42 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
49fa3206-a8f8-4703-af50-f52ed1e2b01f | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
6392ab05-c86a-4c7e-a224-e9bb2e7194be | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
be791687-cdc1-4658-b03d-a6c2a57f58b7 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
8fd92af6-248e-4579-929b-85cd9a4aa35d | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
7ea2b5fb-d5b3-4f37-a7aa-25bb90e463e2 | Padmount-Ã¡Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
0957426b-5825-479b-8eb4-48d557b19cb1 | UG Transformer | 2 | Distribution | 2023-07-24 | 2028-07-22 | Level 3
e86f5750-ed06-4c7d-9b9a-dad1241d619b | Riser | 2 | Distribution | 2023-07-21 | 2024-07-20 | Level 2
20a4021c-2811-4f05-8bae-fcd2f02904dc | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3
807c49d3-5103-4302-9100-54b87760830c | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3
cd233071-41f0-40e7-a0e5-ab62daf614c8 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3
cd233071-41f0-40e7-a0e5-ab62daf614c8 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3
cd233071-41f0-40e7-a0e5-ab62daf614c8 | UG Transformer | 2 | Distribution | 2023-07-21 | 2024-07-20 | Level 2
ec332fc4-3c2f-49a9-8f6d-4269a1bb4e80 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3
ec332fc4-3c2f-49a9-8f6d-4269a1bb4e80 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3
12cf6afd-b2b3-4523-b9d9-30c2cf69fe96 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3
12cf6afd-b2b3-4523-b9d9-30c2cf69fe96 | UG Transformer | 2 | Distribution | 2023-07-21 | 2024-07-20 | Level 2
6e0da2e1-9b1c-4a9f-92f8-e84506b0b335 | UG Transformer | 2 | Distribution | 2023-07-21 | 2028-07-19 | Level 3
dedf249a-df86-437f-ab15-0b2d1705c2a0 | Riser | 2 | Distribution | 2023-07-20 | 2024-07-19 | Level 2
aa7b0f85-ba75-4e55-a668-3b9ba30a4f27 | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3
aa7b0f85-ba75-4e55-a668-3b9ba30a4f27 | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3
c1b41946-c03d-4cf7-922b-f3adcf0d1ced | Padmount-Ã¡Switch | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3
d66e16c4-daee-48a8-9539-32338ac7466d | Padmount-Ã¡Switch | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3
f936467a-7f58-423f-9d76-84a938f0ba2b | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3
c1a60222-69e6-4192-ad9b-b9a5be9e0e17 | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3
3529b85b-517f-4c36-bb1c-a88e40812eac | UG Transformer | 2 | Distribution | 2023-07-20 | 2028-07-18 | Level 3
3529b85b-517f-4c36-bb1c-a88e40812eac | UG Transformer | 2 | Distribution | 2023-07-20 | 2024-07-19 | Level 2
f8d87a04-5437-425a-8720-382ac942775d | Riser | 2 | Distribution | 2023-07-20 | 2024-07-19 | Level 2
c1a60222-69e6-4192-ad9b-b9a5be9e0e17 | UG Transformer | 2 | Distribution | 2023-07-20 | 2024-07-19 | Level 2
1fd12b33-96fe-40b3-85db-446e9d72a90e | UG Transformer | 2 | Distribution | 2023-07-19 | 2028-07-17 | Level 3
c973809d-74b5-423d-8a25-b9bbbe791132 | UG Transformer | 2 | Distribution | 2023-07-19 | 2028-07-17 | Level 3
e8e89b46-c1e1-471b-85f0-33577bbeb545 | UG Transformer | 2 | Distribution | 2023-07-19 | 2028-07-17 | Level 3
31f5541c-22c8-404c-93d9-a662bff55a1d | Riser | 2 | Distribution | 2023-07-19 | 2024-07-18 | Level 2
3d6dbb31-8604-452d-b2e3-1b6bd637b6a1 | Switching Cabinet | 2 | Distribution | 2023-07-19 | 2028-07-17 | Level 3
1d34d315-42aa-43b7-a014-4aa83f43af95 | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
ad807f78-cbbe-4aa7-a7f8-747c187a67b1 | Switching Cabinet | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
e4feea66-539f-4245-9d01-4d7b9be00901 | Riser | 2 | Distribution | 2023-07-18 | 2024-07-17 | Level 2
627e58cd-03dc-4e9c-925e-fd668f6cc9a3 | Riser | 2 | Distribution | 2023-07-18 | 2024-07-17 | Level 2
2c316183-eace-4469-83ab-85a12d1ab753 | Riser | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
7214ace2-32fe-4112-a57e-7f1fe19f47d1 | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
7214ace2-32fe-4112-a57e-7f1fe19f47d1 | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
8e2cf5a9-101d-4ea8-8207-50635ababdad | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
51d1e3f2-d006-408b-9167-4d097d26075a | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
51d1e3f2-d006-408b-9167-4d097d26075a | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
51d1e3f2-d006-408b-9167-4d097d26075a | UG Transformer | 2 | Distribution | 2023-07-18 | 2028-07-16 | Level 3
9ab08fa6-7b4a-4319-8792-308a58d71c3f | Switching Cabinet | 2 | Distribution | 2023-07-18 | 2024-07-17 | Level 2
972f633f-c5f5-4a3c-98f5-bddccfc70b78 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
9604b66a-ae4e-4b52-9103-37f5b6c0390a | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
3389aa92-7c0f-4bee-b8ac-5d7ba8061414 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
3389aa92-7c0f-4bee-b8ac-5d7ba8061414 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
3389aa92-7c0f-4bee-b8ac-5d7ba8061414 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
8a0f8531-f1a4-4ce5-a2a0-a1f6ab790a2f | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2
8a0f8531-f1a4-4ce5-a2a0-a1f6ab790a2f | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
e934856c-58f8-482d-8f8f-97144cbc370b | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
268cfe86-f63f-4cf7-aca5-357f8945c226 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
972f633f-c5f5-4a3c-98f5-bddccfc70b78 | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2
73845d1f-ddbc-46a0-9325-66af1de7b48a | Switching Cabinet | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
ad2c6c22-877f-4693-aa0b-eb2cfff72198 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
093ab44a-17ae-43eb-997f-67d392b6576c | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2
5e99a115-3f96-4694-b016-c281dcb6436e | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2
8bcfb4ef-395f-4d90-9b3a-c221ccdbbff4 | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
219ceacf-f780-4fd1-903b-38c2e374f00b | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
219ceacf-f780-4fd1-903b-38c2e374f00b | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
219ceacf-f780-4fd1-903b-38c2e374f00b | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
aed033f3-153d-49b5-8d9f-503834a9debc | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
aed033f3-153d-49b5-8d9f-503834a9debc | UG Transformer | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
aed033f3-153d-49b5-8d9f-503834a9debc | UG Transformer | 2 | Distribution | 2023-07-17 | 2024-07-16 | Level 2
88814f6a-9294-450b-96bd-41730e945177 | Riser | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
724c48c7-c51c-41cb-9dca-4a04d0b4d542 | Riser | 2 | Distribution | 2023-07-17 | 2028-07-15 | Level 3
49e76f4f-94c2-4687-a241-f676e1e212c0 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
586f02f5-ff26-4433-af0f-dde23d881e89 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
99fda636-ba57-4e8a-a0c4-4c801372308d | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
741884fb-4f44-403c-8d1f-2111bd8b1da3 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
9eea07db-e999-47a0-8a2d-882ff50c2868 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
6547ae66-7e11-4cda-a804-86ff73e218c6 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
c47234eb-2fda-409d-938f-f171af1ad631 | Switching Cabinet | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
202d9c0e-0b64-4c97-964a-78f21bdd10ce | Switching Cabinet | 2 | Distribution | 2023-07-15 | 2024-07-14 | Level 2
202d9c0e-0b64-4c97-964a-78f21bdd10ce | Switching Cabinet | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
202d9c0e-0b64-4c97-964a-78f21bdd10ce | Switching Cabinet | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
7091a91c-08a5-4dad-9dc3-de9245cbb564 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
f93241a4-bba7-43a7-98ef-0d516c5b5a65 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
783fc654-ee70-4334-8dd8-e6b243596d96 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
ff5341bc-f564-4027-a1ec-503460e6c2c0 | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
8e9c7771-8214-4ad2-bbf6-6bf6a7e6862f | UG Transformer | 2 | Distribution | 2023-07-15 | 2028-07-13 | Level 3
cb32f91b-1357-4e4b-9dc2-a5348573ca9a | UG Transformer | 2 | Distribution | 2023-07-14 | 2028-07-12 | Level 3
b8af1c74-626a-4653-a483-ec2ed7d90e05 | UG Transformer | 2 | Distribution | 2023-07-14 | 2028-07-12 | Level 3
ed706fac-ffe0-4170-9fef-99cd75253f95 | UG Transformer | 2 | Distribution | 2023-07-14 | 2028-07-12 | Level 3
931d1d42-61d8-4e44-b88b-f03273d11b9f | UG Transformer | 2 | Distribution | 2023-07-14 | 2024-07-13 | Level 2
931d1d42-61d8-4e44-b88b-f03273d11b9f | UG Transformer | 2 | Distribution | 2023-07-14 | 2028-07-12 | Level 3
585a69ca-d858-47d5-8c94-6c38c83069ad | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
585a69ca-d858-47d5-8c94-6c38c83069ad | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
585a69ca-d858-47d5-8c94-6c38c83069ad | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
e9f8a133-11ee-4f2f-8187-e90800aebd23 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
39ffeded-cccb-4954-8099-6270888eaf1c | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
0fecf000-b905-492c-8c7f-93c0eb7171c0 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
9b8ad226-de05-4471-b981-4dd6824b69d1 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
c2da7da1-9e0c-4ce7-883c-012b453ca938 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
c2da7da1-9e0c-4ce7-883c-012b453ca938 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
49ad5418-61de-4a93-a82e-7f6274004658 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
2b23f413-82a2-48a1-b9b1-c21f40468144 | UG Transformer | 2 | Distribution | 2023-07-13 | 2028-07-11 | Level 3
fe307e8c-3986-4382-9dc2-fec8910c9c1b | UG Transformer | 2 | Distribution | 2023-07-12 | 2028-07-10 | Level 3
ae4770c7-053c-4a59-b015-a477ed1e6242 | UG Transformer | 2 | Distribution | 2023-07-12 | 2028-07-10 | Level 3
090e5d36-cbf9-400f-8e50-34018635d87e | Switching Cabinet | 2 | Distribution | 2023-07-11 | 2028-07-09 | Level 3
090e5d36-cbf9-400f-8e50-34018635d87e | Switching Cabinet | 2 | Distribution | 2023-07-11 | 2028-07-09 | Level 3
b00e2bbe-f01f-4ee4-8a40-646f84116fcd | UG Transformer | 2 | Distribution | 2023-07-11 | 2028-07-09 | Level 3
7922db2e-c76c-48bf-a145-26f598dd418e | Pole | 2 | Distribution | 2023-06-21 | 2028-06-19 | Level 3
4352dc51-da21-420f-809f-1b5548caeb30 | Pole | 2 | Transmission | 2023-06-20 | 2028-06-18 | Level 3
42227fd2-373a-4a01-9e11-4764b061fbd7 | Pole | 2 | Transmission | 2023-06-20 | 2028-06-18 | Level 3
e4f3f827-471e-4a2a-b982-7f06b303bd95 | Pole | 2 | Transmission | 2023-06-20 | 2024-06-19 | Level 2
e847e428-2001-4594-9788-ac74c41f48c7 | Pole | 2 | Transmission | 2023-06-20 | 2028-06-18 | Level 3
e4be9cba-f2f3-466d-9af2-0b2bc4723c45 | Pole | 2 | Transmission | 2023-06-20 | 2028-06-18 | Level 3
6683fc71-8b48-4287-b7c9-05b6e14e884c | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3
1d870439-b07c-4d3b-bd87-e32e995d0f1d | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3
603c4036-e86a-4ab3-8508-2af5613496a9 | UG Transformer | 2 | Distribution | 2022-12-20 | 2027-12-19 | Level 3
0e390fe4-c150-4bb1-bd86-8ee5d6a963ca | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3
e4d54697-90b4-4c0f-8054-564699302bad | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3
89926fbb-cae6-49c3-b81a-361100e2f151 | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3
adef5ec6-94cb-4749-aa95-9a009b4f90c3 | UG Transformer | 2 | Distribution | 2022-12-06 | 2027-12-05 | Level 3
d689b31a-dfb8-45a3-84d8-941810274be7 | Pole | 2 | Transmission | 2022-11-23 | 2027-11-22 | Level 3
889d3755-0ce9-4849-a53f-a410f3d60766 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
2439f181-39ee-431e-89e9-0e27b0b4fb44 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
dd30c485-f732-48af-a419-c23e6af5be23 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
4384139a-8914-4f69-898a-dcfc983d3606 | Pole | 2 | Distribution | 2022-11-22 | 2027-11-21 | Level 3
58942f1a-5036-44b2-91b6-f30a3ef7760f | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
3c855010-4141-4bd1-8816-7c7dd8e3e396 | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
5bdf31cc-12ba-40bd-945b-df6d16365a4b | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
575f5753-2477-4b9b-a2e1-a7602258edfc | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
bfde1b03-fd7c-428a-9801-45647e7f245d | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
986ff4b7-5132-4b0d-9221-aff00fb9ed4e | Pole | 2 | Distribution | 2022-11-21 | 2027-11-20 | Level 3
af1cb5e4-d7c6-4250-ad1e-b0c8ba097f58 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
9871f144-207f-445a-83d2-e70b618e35f5 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
05424644-e141-48c3-b836-1e04f775c299 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
279b39fa-e1c9-4903-9c28-68043690652d | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
390e4d13-65ab-4011-90f0-4c9bfc1dbbe1 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
7d8dd5db-5b95-4953-9214-71f4ea07b834 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
f5f7f618-595e-458b-9551-fc38426e872c | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
fa9a583e-e74f-4d93-9403-9463f183dc81 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
5a590a03-3348-42c7-a656-21ac9d10ae10 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
8029cc16-eaec-49cf-af10-4ec84ae103f1 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2023-08-25 | Level 2
6b1ae1a4-428b-4dba-97f2-a493b71f6c90 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
1183d39d-1dc9-4c4b-ad48-da44f6057a64 | Padmount Transformer | 2 | Distribution | 2022-08-25 | 2027-08-24 | Level 3
cfbef4e5-cbf9-40f4-9444-585ce549423a | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2
3e4c6145-134c-4104-a579-0b4309f9c94f | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
41375cd6-eebc-43fd-b564-7cfbd63d5278 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
93e03673-6637-4894-913c-77f87a7eace4 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
a28d12ef-69ed-41df-a1e7-c79e0bfaf05e | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
cc0a0498-0e59-4468-a87b-d5e286323e83 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2
e41871fe-103e-4997-94fd-40c37951a733 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
493f2e0d-d24c-493d-8e8f-1dc94a068fd1 | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
64e39d77-1867-4417-8e0c-e715fc4f932c | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2023-08-23 | Level 2
a767130c-dba3-4952-917f-3ecbef23df55 | Padmount Switch | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
87a165b5-ae73-4c59-bc68-0ac3fc94b44e | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
b9023123-e78a-4574-8077-001d9a4529ba | Padmount Transformer | 2 | Distribution | 2022-08-23 | 2027-08-22 | Level 3
7aec2cde-0c8b-4373-ae05-963e468e25d8 | Padmount Transformer | 2 | Distribution | 2022-08-20 | 2023-08-20 | Level 2
f07da56a-f3cc-43de-9464-849917314445 | Padmount Transformer | 2 | Distribution | 2022-08-18 | 2027-08-17 | Level 3
535c7cf6-0fe5-4998-b175-8c659de3f0e2 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
a71ef824-c2bc-4acd-9d39-bf5326eac1e6 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2
68ff7442-50c4-42c1-957b-7353b5141e73 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2
0184cb9e-1316-4350-8fdc-49ad401c0bc9 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
24468157-72e7-4e81-9a97-9131fea2a8aa | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
d627965b-18e3-46f3-80c8-a090d628dd4d | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
60c7352e-e2ca-41e4-b777-9c66b20e6f58 | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
024331a3-be90-425c-973c-6606c5e02e06 | Padmount Switch | 2 | Distribution | 2022-08-17 | 2027-08-16 | Level 3
73b33a60-718e-45e1-be66-7665d45bbb94 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2
22eb09b5-181a-41b7-878e-b93311d44e98 | Padmount Transformer | 2 | Distribution | 2022-08-17 | 2023-08-17 | Level 2
9455b029-8445-47d2-ae09-d8435a7339a0 | Padmount Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3
e8094d4f-dc0b-479d-a747-5b551348ddd3 | Subsurface Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3
055d4a8a-a9f3-4084-98f4-33839fc50091 | Subsurface transformer in cabinet | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3
090d0960-c0bf-4243-a70d-952b018015c5 | Padmount Transformer | 2 | Distribution | 2022-08-15 | 2027-08-14 | Level 3
97469f90-6197-4c07-b313-b1e18fa4a873 | Padmount Transformer | 2 | Distribution | 2022-08-11 | 2027-08-10 | Level 3
b0d7d791-1408-4a03-997f-e76303f83691 | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
551d7049-3680-4d3c-b86a-8ab3c0b39a03 | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
c61c9708-851f-4d07-b5e6-9688d560081a | Padmount Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
c12d6384-f464-4de5-95c3-64bddecf4c59 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
f60c47f7-4dc0-485d-bd3e-bcf1fdf28e54 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
d5636e90-0e1a-44fd-8e2a-62427b08c5d7 | Padmount Transformer | 3 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
8932cfee-afd9-4c3a-a74a-1356c81f1554 | Subsurface Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
f181aca2-9243-4210-b20b-f296f4d959a0 | Subsurface Transformer | 2 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
d5601299-ce56-48d1-a84b-0f66eca70bab | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
0be8bcc9-67f5-4258-b3dd-a5ae8079bebc | Subsurface Transformer | 0 | Distribution | 2022-08-01 | 2027-07-31 | Level 3
b9a781ed-4ea7-4ce4-a8a3-f1a04afad7b8 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
a6715506-e507-48ed-887e-83fadb3014a5 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2023-07-30 | Level 2
ce38b17f-da91-472c-9395-7d1e3d7722cc | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2023-07-30 | Level 2
69a96925-cc06-440c-9b2f-475fc55218d0 | Padmount Transformer | 0 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
34676611-518b-4fea-ac97-e8d8543a0ac5 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
f4343387-4bdd-4505-b3cf-a4b09f7a2010 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
2e744b36-b962-4744-8d66-c2e62ba5bb58 | Junction Enclosure | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
c5e97d32-4cde-4060-9ba5-6b9dc2766f89 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
b50f0096-968c-48bf-9e26-a52003b046d3 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2023-07-30 | Level 2
db1089c1-261e-4831-81da-48dfce9f5005 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
7410d3df-1fed-4cea-80d6-315c4022df64 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
8e4a5f9f-6632-4d4f-a9f5-1d80070e9d15 | Padmount Transformer | 2 | Distribution | 2022-07-30 | 2027-07-29 | Level 3
250c9c34-9c2e-45bd-af09-ab33a48ca98c | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2023-07-29 | Level 2
ea9c69b8-d525-414d-8a95-f15e5cc68fc7 | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
6cb5f3c7-bd45-459b-b014-f082c2b0ebb4 | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
65d3714c-1df3-4741-b98b-07d6a384ccbe | Padmount Transformer | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
e5687798-66d1-40cd-91a7-d3da0ce5a4b4 | Riser | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
861b19f4-6d5c-4e9c-9ba3-2c6ccad098db | Riser | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
b0268673-e6c0-4cb0-ab9a-6609cf887d27 | Pole | 2 | Distribution | 2022-07-29 | 2027-07-28 | Level 3
9e7ecdf4-4653-42ac-ad6d-850829b6f1d6 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
5ac12c6f-3ad7-463e-9239-feeed233a5f6 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2023-07-27 | Level 2
0a06ac16-598c-424e-b4eb-233e72e13620 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
6afb2566-bd9a-4ff9-8468-a7468a5268d8 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
a9397d43-0dcd-4c29-a948-40b7010d35e0 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
f55618a6-1f62-48fe-8bf2-1115e5f41d21 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
341d56ad-4a32-4bb0-b9a9-8d3614f11eb2 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
a8abaf8e-5bc4-4ba0-85c2-e9a5c7efdfae | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
0b437a6f-992c-4b63-a4a0-8f63bd61e472 | Padmount Transformer | 2 | Distribution | 2022-07-27 | 2027-07-26 | Level 3
1a27a9cf-dc7f-4bc3-b2e6-fbfe68a30b2c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
675e58bb-28dc-4e04-867a-1bd8b7207473 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2
d87e3694-0fc7-48a5-8c45-b29c3679e33c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
69642a7e-84c4-4db3-90da-e2d9b776a952 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
5a5bb1a4-1131-4fc2-8a5f-abb07ab05718 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
77793559-5287-440e-8def-2d3f2ed3bd11 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
d2a27a69-d475-4feb-8400-300c992ea1d1 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
4f595da1-4354-4fb8-acba-fd9314f20b0c | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2
8dd3673d-4c38-4812-9032-9c7028bf5216 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2023-07-26 | Level 2
95d79daf-b3b6-46a7-95cf-761c5a74859a | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
31813f44-b57a-4296-85b6-fd66ae276c82 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
0b50282c-7fd6-49fa-8b00-1f1305cab7f0 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3 |  | 0:00 | 0:00
884194fe-1dee-4abe-9f39-1f907d53ada5 | Padmount Transformer | 2 | Distribution | 2022-07-26 | 2027-07-25 | Level 3
31332b21-931a-44b4-956e-6993ef7ed5b5 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
4886971a-3471-44ca-a661-16449a1380a4 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
f503f765-03d2-4afe-8fb4-2de7d0fdb1d3 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
9075fa42-4c3d-487f-a422-210cffd4125d | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
294e7f47-d95b-497c-864a-d7d66db88130 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
956f4069-31b0-428d-8177-b463da41c82e | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
5321383c-e6de-4fff-a775-611f046675fa | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
a911aff4-9c38-4ffe-965d-b093eb1a13f2 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
0362e6ab-ce17-47fe-956a-9f771f25f8c8 | Padmount Transformer | 2 | Distribution | 2022-07-25 | 2027-07-24 | Level 3
d00f29c3-9cf1-469f-ac39-107417483492 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
30dcd263-f462-417a-85ba-1ed216a3cb18 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
8afed30d-af2a-41f4-82e2-096f0182e553 | Padmount Transformer | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
be65b7a9-0606-4a77-bc91-6909cacb4fe5 | Junction Enclosure | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
e29ddcdd-dcdc-466d-86d7-4baed185d2d4 | Junction Enclosure | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
fdefdf95-fead-4925-b734-d1d13d0ac4ce | Padmount Transformer | 3 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
8778d3f4-313d-43a3-9601-be10799c26f9 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
2e3b666d-5a2a-4ebd-8ef5-c40eb21d0101 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
cdd81f99-0c1e-4117-bd49-8cc919fafbd3 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
830b5119-e30f-421b-985d-cacfda17d10b | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
ba8c44eb-52e6-42b9-a08e-023e286df4d2 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
6972277e-1219-4402-98b1-47968c05a7e4 | Padmount Transformer | 0 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
1ce135df-0492-4f05-a54f-9bfd206d79cb | Padmount Switch | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
e3b24731-f94d-4b5e-8a1b-25cf57a7e5f1 | Padmount Switch | 2 | Distribution | 2022-07-23 | 2027-07-22 | Level 3
915c9f2e-77c3-4454-b5d4-0816e8586cdf | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
91853f5b-ebfa-4c2d-802c-6777e74acc44 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
87bf2d25-51f5-4eda-a819-3e4bc1b3e078 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
1921a16a-9eb2-4a74-bd75-b59ed792a8d0 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
f020a51a-b5df-4f16-a610-6fc66e8217e3 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
b4c00fa9-e2d6-467d-9da7-1477bf4ad733 | Junction Enclosure | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
09b6a4c9-9d9a-4658-a262-ffae9d6a71f0 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
9d1360b0-d78b-4956-b9a7-c3cff338b71e | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
7d1c1ce3-6f82-499d-9d0e-ac6a13a28378 | Padmount Transformer | 2 | Distribution | 2022-07-22 | 2027-07-21 | Level 3
ffc6ab46-5799-4009-924b-309c0bf5c4b0 | Padmount Transformer | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3
916aae83-4ce8-466a-b377-bd1a2df74ada | Padmount Transformer | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3
5621a3df-f5c6-4921-9d74-96aaac526093 | Riser | 2 | Distribution | 2022-07-21 | 2027-07-20 | Level 3
0e1bf72d-2512-4448-ae30-bb458d249f82 | Padmount Transformer | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3
3cbd90aa-9655-4e4f-a4ec-802bedc5e9d5 | Riser | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3
c97c87ec-f115-42a9-9eb6-7efcdc14342c | Padmount Transformer | 2 | Distribution | 2022-07-20 | 2027-07-19 | Level 3
5e15942c-10a5-499d-bc5e-5cf00d088373 | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
11deba5f-8923-4b68-b64f-fc0c83247e94 | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
4d85fbd3-0ecd-4729-be4a-8415b59a261a | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
ed9c0452-40c1-4795-88a2-77612647cc3f | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
503b2711-da55-4704-9f2a-7c2d6d4d528f | Padmount Transformer | 2 | Distribution | 2022-07-19 | 2027-07-18 | Level 3
cd408b5f-a09a-485f-8f27-e6803a712d42 | Padmount Transformer | 0 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
39732bce-4537-47fc-a2a1-2444145d59fd | Padmount Transformer | 0 | Distribution | 2022-07-16 | 2023-07-16 | Level 2
0dcdac62-15c1-4b4d-8bb5-ae602fbde396 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2023-07-16 | Level 2
615eb800-1974-438d-b5e5-b83e4e8b78d6 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
436bff65-1e42-4cdf-b38d-9154e6ca75eb | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
9123d66e-a97f-433c-ab1d-0232923dacb8 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
ba98a25d-f5f8-492a-abb7-8c54732f1ef8 | Padmount Transformer | 2 | Distribution | 2022-07-16 | 2027-07-15 | Level 3
dc142e9c-5516-485e-8870-39690eb540fd | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3
179aeb7c-a58f-4c01-94bf-2733a6069c87 | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3
d6efa84d-31c2-4031-b7cb-6913f263534e | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3
14d3fbec-cdea-436a-b506-902b9b425279 | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2
0eaa605b-90e2-4dbc-aa23-f842abb4441a | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2
1e5b4693-4012-4541-94cf-5a10b67cf02c | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2023-07-15 | Level 2
572a067d-dbe9-492e-9d01-d8016fec4e2f | Padmount Transformer | 2 | Distribution | 2022-07-15 | 2027-07-14 | Level 3
b36e2ca2-b169-4493-9b73-e845e21fd800 | Padmount Switch | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
49c0182d-a1f1-46de-9431-6770c058615d | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
68a02437-a256-419e-a9d3-f894f99ad010 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
2c46a6b7-8e04-4748-afbe-a3cda8019211 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
365bee8d-1b6a-42a1-b2fc-77d25bdadf62 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
93f622d5-9481-4454-9711-a95cc62475c9 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
7043c738-d041-43cf-9b14-2807c0406316 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
b548237b-9408-400b-b565-8a28bf3d6739 | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
df73377f-8e16-4be6-a8e8-a831c9668a3f | Padmount Transformer | 2 | Distribution | 2022-07-14 | 2027-07-13 | Level 3
f5bef563-93a4-4e5c-8152-864e6dd8f6b1 | Junction Enclosure | 2 | Distribution | 2022-07-13 | 2027-07-12 | Level 3
32a90151-c9ff-402a-8e34-3d86e01a9052 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2
60d3794a-6e91-440e-b84e-7ed56015b922 | Padmount Transformer | 2 | Distribution | 2022-07-13 | 2023-07-13 | Level 2
92530485-8c67-4892-827b-293d16760fab | Riser | 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3
d661365c-f23a-4424-b3a5-1608c055c038 | Padmount Transformer | 2 | Distribution | 2022-07-09 | 2027-07-08 | Level 3
b79fbdf9-cd7d-4c21-b4da-2da62d78492e | Pole | 2 | Distribution | 2022-07-08 | 2027-07-07 | Level 3
543bdd87-6ad5-4467-a96b-1817cdf1685c | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
cad96719-c1ad-4544-ba90-3d96d7c9daa5 | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
9027305d-5ca5-4d5a-9787-94edef7f4c3d | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
7b81f885-698b-40f4-bf70-872bdb3a84c2 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2
0eaec015-d283-49a0-b937-bbdabba47018 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2023-07-07 | Level 2
866d4f8a-f536-4f2c-a15e-2fe3d47e28fe | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
35c0a14f-e71e-4039-93ba-c1c0a0e077a3 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
af4a2120-e8a6-444a-8cf2-9f9173acc042 | Padmount Transformer | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
39df8bba-e3ec-4586-a4f4-e88ea4e81a39 | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
7f1ff962-6326-4560-80e9-9bdc6059841a | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
68e1d5e5-eff0-424a-9140-d7a6c56d949c | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
96f35bd5-2d54-4ad3-887f-2982b4691c8c | Padmount Switch | 2 | Distribution | 2022-07-07 | 2027-07-06 | Level 3
8f1cfaa6-fa5c-4bcd-8cac-67fb4803ad76 | Padmount Transformer | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
737883d5-c881-49dd-a4ba-11d018923726 | Junction Enclosure | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
c51783c2-eb7f-43dc-9154-9e496a6f7e5a | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
a748300e-ff2d-42dc-89a4-eb1d9a4dbf57 | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
705da63e-2ba7-43f7-acd8-8bbb9dc75726 | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
9c1dd4ec-db04-49ac-8b38-729c84ad393f | Pole | 2 | Distribution | 2022-07-02 | 2027-07-01 | Level 3
51d31739-f023-4f0a-af6b-356f3f09467a | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3
9b5f2d37-ff25-4842-8de1-153bd7b26a75 | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3
6a10e78d-e849-4d53-96ac-903f9d740ad9 | Padmount Transformer | 2 | Distribution | 2022-07-01 | 2027-06-30 | Level 3
7142821b-0126-4800-b5ed-30fe0d80526b | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
ddf4c389-923c-467c-96b0-d0c119361cc2 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
ecad7c32-ba3f-452a-b4fc-8b8a34a72cfc | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
932cef69-6251-41a0-9c2b-d4e9c18b70b3 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
3c6e3906-5dbc-47c0-ab98-7c06e5d5b54d | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
4211b33e-172d-45bd-9697-8a989f875f1e | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
68d4db95-826e-4a41-99d6-adbacc591d9f | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
dc8b62e1-29cd-4951-9234-3c9c888e7a7b | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
a24192c7-d0e0-4b59-a80e-4c1dfa603c19 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2023-06-30 | Level 2
b6a202cc-e85c-4595-9e38-5237c44102d4 | Padmount Transformer | 2 | Distribution | 2022-06-30 | 2027-06-29 | Level 3
8b167cad-ced3-48d0-970e-6006b5a91556 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
cb46753c-69b2-4b62-bfa8-fd6e22d45485 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
0687ca96-0d7d-499a-b133-6232b6a7a83a | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
5f0f0f98-d7a8-4f7b-8e1c-9eed7eab2f85 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
5ee63644-9e79-4756-a201-1bf59accbe53 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
d0248b90-8bf6-4a68-bff8-0331537d2212 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
3e50c77f-a7f2-4955-b0d0-5278041b75a2 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
3660f9c8-118f-4a67-a131-8be4912ccb05 | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
e6196d01-9922-43cd-81e6-ed765dfbaead | Padmount Transformer | 2 | Distribution | 2022-06-29 | 2027-06-28 | Level 3
a045f6a4-5a5f-4005-a009-1d3e74085d87 | Riser | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
65a9971a-6362-4e5d-9cb4-3eaf1725e19f | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
46b5491d-a643-4ea0-9d7c-d7a875934113 | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
652d85cd-7dca-4650-b09d-38be7c3593fa | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
039b0d1b-f16b-44e8-9c30-bef197d876ce | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
a7f44a4f-90ab-4f83-a5b9-d16942e0f474 | Padmount Switch | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
a56054d6-e431-4b38-8102-c6340cd0a187 | Junction Enclosure | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
3aa680e5-bc9e-4303-8983-379d6a5bcc86 | Padmount Transformer | 2 | Distribution | 2022-06-28 | 2027-06-27 | Level 3
57132dbf-b2ac-4061-a0c9-85a59e17da31 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
c7091109-e6cb-4bd3-aeda-bc71f46805d1 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
1cdd61bb-40cc-4898-a072-83625893d433 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
945759fd-7e64-461e-9003-579624b1b8a6 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
97333fea-8d0f-4cd7-b461-c7801cd23c3c | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
8bb83fdc-cf25-4ed3-a1b4-aaec1d4d16a1 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
250fb58a-d59f-4e30-acdf-da04a8325175 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
158284ec-87b6-44ff-8d88-744610aef02c | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
2e7582e2-17ba-40c1-b3f8-8230194c5720 | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
417ba8ba-aff3-4c3c-a6ca-712c8d56501d | Padmount Transformer | 2 | Distribution | 2022-06-27 | 2027-06-26 | Level 3
9ab7f456-a2d7-4bac-b9d6-a22a4ae06fce | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
0276fbd3-4b6d-4a0a-9b7d-f0d6a7d9d58a | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
e88d3cef-d974-4f40-b969-eaed7156703a | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
3ca1e1bb-6d6c-497f-9632-0c7bb1721885 | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
ed42748d-cde4-4cea-8306-63913d379ec9 | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
8eaa42d2-3c2a-43d8-868e-1c4607bea3cc | Junction Enclosure | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
328f773a-3bbb-48cf-acf6-11c9c4514842 | Padmount Transformer | 2 | Distribution | 2022-06-25 | 2027-06-24 | Level 3
3a916cab-3fa2-4352-8551-d7e195085c80 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
5bb253fb-2aba-44f5-b468-489eeeaba216 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2023-06-24 | Level 2
c8a68e42-6db8-45f8-a73c-3b63e6a8d181 | Junction Enclosure | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
983332d7-a2d7-4f4e-87fa-337b7aca6c24 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
b8daf1f6-1c7a-49ea-9f87-a5455520c5e2 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
2876af88-cb1a-4ae9-a211-7396568f0ce7 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
c9e6a4a4-6892-431c-9c6e-9bff7f782e69 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
70c03c5e-c0eb-43b5-9304-5b4b58c14e51 | Padmount Transformer | 2 | Distribution | 2022-06-24 | 2027-06-23 | Level 3
6b7360dd-d7ca-478d-a8f4-621faa5f32aa | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
7dea3583-8a76-4701-bbff-0d76c1d40381 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
fc00b21c-94d0-41e1-b78f-2da60c9f1c66 | Padmount Switch | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
9fe80817-b76a-41b7-b99a-6e5982e7301c | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2023-06-23 | Level 2
9e31fbe7-495e-410e-be28-838fb43b055a | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
d13ec6ad-2fdf-41da-b0ea-8b8bcb119603 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
b507717d-4fef-4b44-9fbf-7080fd933f3c | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
da61a454-3b12-4842-b23f-f8ce9a5d9375 | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
f2144e7c-b2f0-4a5b-b261-25ea32aa872d | Other (Describe) | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
6c9aca1e-de70-4304-802d-23aac78d08b3 | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
f3a74b06-ca89-44fc-9aa2-970b8f01b5ab | Other (Describe) | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
646e47e1-596b-4c18-9e99-e3b019554b14 | Subsurface Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
873c3160-dc6f-4c6d-9cd5-907452cd4bab | Padmount Transformer | 2 | Distribution | 2022-06-23 | 2027-06-22 | Level 3
0506b8a3-464f-4898-b97d-fbd1adc9cbef | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
3b34f210-1300-4f76-97de-97cf73055ebe | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
99d66450-6366-41fd-9cbd-ec5fc98f170e | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
cd54d625-24a3-4554-831c-b03562412bb2 | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
c62a6fd3-3d2a-4738-83c5-9c116ff7d314 | Padmount Transformer | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
1f3e2d0b-4465-4596-8775-db561b7ecb54 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
a6ea84c3-f617-4943-93b4-b20a57622cff | Pole | 0 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
f57249bb-e0c6-4e31-b952-966facf30c04 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
86d0243f-c291-40c5-ac7b-cb1dbe150bfd | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
0f552bba-6a98-4f3f-bf4c-e1e6b54a2889 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
5ff51a71-1123-4167-a8f1-9b8cdb1bc2e2 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
b5ecf54b-8f71-492e-b9ef-5fd482eaddc5 | Pole | 2 | Distribution | 2022-06-22 | 2027-06-21 | Level 3
97f58b5d-8cef-4551-8b35-298f73685ad1 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
b020aae7-2559-49d6-b69a-568c73d95411 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
73e61b9b-9c57-4cd1-b8a6-d973bd599f77 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
ecdaaf67-2f25-48e0-b1f1-17c861eee95e | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
c32741fe-cfac-41e6-8903-51d452f4222c | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
afbcdd41-9670-439b-9ffe-df89054667ae | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
6341d88c-4143-454a-8a88-a2c71eb74b70 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
2625c5b4-fb0e-4ad3-93fd-09e3dde8fc73 | Padmount Switch | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
83cb1b94-fe53-4233-ba65-b57df4a5f29c | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
2a6fc61d-ec28-49a9-a828-ac07c755ebe4 | Padmount Transformer | 2 | Distribution | 2022-06-21 | 2027-06-20 | Level 3
4434c782-74d5-4f2c-a82c-96bddec5c6cf | Padmount Transformer | 2 | Distribution | 2022-06-20 | 2023-06-20 | Level 2
de95aa96-8b3f-478f-ac18-01663b7bb0a6 | Padmount Transformer | 2 | Distribution | 2022-06-20 | 2027-06-19 | Level 3
8e7c11bc-ab30-4a6a-bc20-03597152f93e | Padmount Switch | 2 | Distribution | 2022-06-20 | 2027-06-19 | Level 3
d9bf59df-21ac-4e4c-94d3-f737205c5a93 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
b9158da8-200b-408a-b0b3-fb24709ef9fd | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
7e212068-3acf-47f4-9214-d7170a58f009 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
d7c209e0-3cd6-45ce-a082-cb48abee240d | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
ed9fe677-fa14-4fc9-a972-79aa488a92e3 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
a13d0258-61f1-43b1-9228-dce5c58695ec | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
5c779567-9f7b-4a49-bbb5-e3a9b15ce3aa | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
9797b6a0-a6ce-484d-99ef-e7b1277772e3 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
a183ea84-4574-42c4-83cf-160c72450850 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
cfa424be-1ade-43fa-b75e-5577b89676e5 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
c8b69eb6-aec6-48c1-9b49-bc58621544f4 | Junction Enclosure | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
af878fdd-e739-454c-b83c-0d3c8a3da074 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
32741ceb-896d-452b-96ba-e07359dffa68 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
03e35072-a4be-4ccc-913d-6eb56020644d | Padmount Switch | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
9da46770-0fda-41c3-87c3-2dac72b9aedd | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
edf775bc-9d7b-4a7c-b533-cec7cc2aeb91 | Padmount Transformer | 2 | Distribution | 2022-06-18 | 2027-06-17 | Level 3
a85af020-f1a8-4bb7-9b25-7d6ab1800b87 | Padmount Switch | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
5130edae-bd79-4ba5-bb9a-0a3700ed4e69 | Padmount Switch | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
5a47bdef-e192-447a-908c-febf0d336eca | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
94ead8eb-5256-4eec-9e73-cc55975f3aac | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
4bcae9be-09ad-4b8e-9d80-4edc59cfa6a4 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
3bab858e-5e11-40a5-8a19-325a0fe605b9 | Padmount Transformer | 0 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
d3c9cbf5-7f45-454c-b4b9-305dcb465d91 | Padmount Transformer | 0 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
b9dcc4c2-d986-4466-a298-b71daad4aed2 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
b4c67ffb-8e1b-4316-a2cb-13655371deb1 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
9fa3fb16-783e-439f-a137-d189d85edde6 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
1e0436ed-acd5-4707-9e0d-4b9caf87169b | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
c29af4d0-15bc-4a57-af8c-9349b7329734 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
9fefda5a-c474-4c3b-b008-51ecf675b89b | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
1cd58a7a-4a44-41f2-b43c-71405fb4fe55 | Padmount Transformer | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
c19fde90-5337-4ab8-b411-2b6c4af6ba3a | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
8a69389e-42e4-4bf2-8fc6-3e0a7062ef4a | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
df52a1a8-0c31-44bf-8e75-6d7b9568ab17 | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
e28a3cf3-c43f-442b-afcf-caff845f3b3e | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
daed959a-4d21-4774-b0e0-a6f3204eda5c | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
850c4a3c-16db-41c0-bd1c-7e4235e41cde | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
1f0ae53d-ed03-4fae-bad7-fed38ae00e9f | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
e4856038-cb1a-451c-8a7b-c4ca6595cdcb | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
8469ab74-35be-445a-ac3d-969d7431d8f4 | Pole | 2 | Distribution | 2022-06-17 | 2027-06-16 | Level 3
c4c35c38-bb84-4a25-a2ba-8ae5cdb4c7e0 | Pole | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2
1b437797-e7da-4b7f-9f33-a2353b7a05cd | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
ef2b6b89-31e4-41f2-b08d-62fe967cd958 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
3be1b787-56a8-460f-a934-283c82edd225 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
18e8883c-5871-4d53-8b54-f822ff9b0bca | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
ac0a7736-89d2-4830-aca9-990ecbaee780 | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
1cf96f06-cc51-48f4-af3b-69bb6b81b81d | Pole | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
bf32fec6-968c-4837-af4d-610d3f242349 | Padmount Switch | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
6ee10a26-a07e-405a-a205-dda0961b8089 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
cd1d59a7-4fc4-4b0d-86dc-4f87bcede5d4 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
3326eae9-8915-41ed-8c3a-ef82f50c8e29 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2
2ab9ebb6-a13e-455e-9d5d-eee2f3fc5415 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
c968c4f0-659f-4de5-a1e6-f4e6889ab438 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
13f53e72-f481-40ec-bc62-9184799269dc | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2
e3c72cee-d094-433c-8f7d-e7b6adda54d7 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
36e9404f-b39d-459a-87b2-8a4451fc4f9d | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2023-06-16 | Level 2
0376c3be-b3c8-495b-957c-8b33413a41d1 | Padmount Transformer | 2 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
98989c5f-65de-46e5-80dd-aa56cb001af5 | Padmount Transformer | 0 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
298880e0-5326-4328-ab84-29d25d0c3509 | Padmount Transformer | 0 | Distribution | 2022-06-16 | 2027-06-15 | Level 3
2d41216f-eb07-4d47-8ac4-d361b2cc6657 | Padmount Transformer | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3
d5883e28-c8b9-4cfc-a5e6-3a6d407fd18c | Padmount Transformer | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3
b7137f0b-e07e-4d6f-b28c-527d4970a1ed | Pole | 2 | Distribution | 2022-06-15 | 2027-06-14 | Level 3
41c771ad-a229-48d4-b6ce-833512e9406d | Pole | 2 | Distribution | 2022-06-15 | 2023-06-15 | Level 2
6caa5d57-2859-42c4-b6a8-4aff7aea2a62 | Pole | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
4cffdebe-6b28-4f95-8684-2ba580ee4cf0 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
4da1583a-09df-461d-98df-c52e9eef8c32 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2023-06-14 | Level 2
8da15489-0c79-49d8-a2b5-d9657f001e25 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
01d772fd-37b6-4c2b-ba60-74b5953dc58e | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
31bd0687-5047-4776-aeec-5a0e59630cc2 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
62f41e21-fd72-44c0-9e40-428dc67e40d7 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
0ede8458-fe64-4fe8-aa1f-1001484e6c23 | Padmount Transformer | 0 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
4b047ca6-1b7e-4d8c-b79b-27fd2880956a | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
2356a8df-bed8-4722-a538-a0e13afdd20f | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
9d931224-1b1d-4b0c-a10c-3146752be6b3 | Padmount Transformer | 2 | Distribution | 2022-06-14 | 2027-06-13 | Level 3
f7b87618-6ab5-4a0c-9cd2-257dc9c646ce | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
d60e7213-0abf-4d68-a77e-c670919e64de | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
3f72c3c4-b139-4746-83be-66219e91b11c | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
53dec5b3-faa7-4bfc-a0c6-48c5cc985149 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
efcc95b5-2126-42ab-8708-b9881e78c60e | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
b7809b28-bd3d-4e4f-85a8-8d71e13df508 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
55ff8a66-62f9-4125-90f7-3fd21f8c442c | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
32e267c8-84fa-43f5-ae4a-81246921927b | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
1285fe7a-41ca-4da2-bcc7-e9f28b4f25ee | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
a57bfe1b-c179-46d0-b10e-ff93c631c020 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
45c74e7f-6f85-4b30-888b-4b7260c34cf6 | Pole | 2 | Distribution | 2022-06-13 | 2023-06-13 | Level 2
bad390b3-c903-4be0-93e4-942920b6bb8d | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
43afcc3c-dc6b-40d9-b76d-b32e9627b339 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
3c2024f3-3bfd-4964-985b-a8a6e4811a87 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
d1753f35-63fa-464c-b705-daf1cf8ac8bf | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
49e7d3c1-4baa-481f-8b7a-99b53ecf6011 | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
7d98426a-1568-40cf-99fb-d528cc8a41cf | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
b142c4c5-82cc-4937-a8e4-2befc07d782c | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
a9b0bcdb-a1bf-4a10-a4ea-dd20a4ac0b5a | Pole | 2 | Distribution | 2022-06-13 | 2027-06-12 | Level 3
190563a1-0644-4d08-b1e4-23489e44ff24 | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2
65afe448-4e5d-4267-aead-b056db2139d3 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
f6162a34-a159-4591-bdd0-9495d27962b4 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
e63ee37c-9e77-4b4c-a390-1fe9daf492f7 | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2
34575d69-e68f-4379-9637-d26f15c8b743 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
2a57d8cb-f0cc-4d12-be65-ad767a431439 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
6b6cdbbe-fcf8-460c-9a52-178b96039102 | Pole | 2 | Distribution | 2022-06-11 | 2027-06-10 | Level 3
ce749701-3e23-4323-9ee0-3daeba73ca6d | Pole | 2 | Distribution | 2022-06-11 | 2023-06-11 | Level 2
74c5dd60-f8d2-40d8-b606-4ac2f7096b0b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
7a096404-c6db-401b-9c0e-6d69e51f83fc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
804502ca-24d1-400f-a84d-0e9a9eb097cc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
408ead9d-8c47-452b-86ea-166c4a7d60fd | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
3873a587-5e53-49e7-9d4a-2f9f5a677351 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
91da5b98-7af5-4a4f-ab56-6f8195f33720 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
3f9e0f34-cd83-4ba3-a1d2-bffcbd1108e2 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
e3eedb98-60df-4408-b15c-d986e8827147 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
0f30e4bf-789f-44d9-a930-8727944076c1 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
5b615b9c-ac4c-4d44-85a0-e409bb969a3c | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
8dfae59c-eed3-4df2-8281-c14d0df52f36 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
699324da-bb0d-4487-a086-e86d128a785b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
24c63960-2949-42cf-903e-ff759109994b | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
dd57316a-83fc-4d6f-81a2-dbc163e2924b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
c7e8802c-d27b-4b94-baa7-e10f88157697 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
ab02603e-840a-43a7-9f4c-325968540c93 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
f41478ee-683b-478b-b430-6641d9c61b4b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
261cabce-af69-41d1-a513-b03e51fed527 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
fc47e68d-ad6c-4e62-b3f2-e4668ed6ca13 | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
d1a0409e-8058-4121-bcdd-874595064e6b | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
b1a7d64c-7a21-4cee-819f-df93dc2eedd5 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
db6af8c7-5e20-4e33-b1d9-7cd021bf3786 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
73ca89fe-85b5-4b96-9621-8e91e4a65ca9 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
5d124e0b-77b2-48e7-9313-3f3db4224a4c | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
5775a1e6-05d1-44b5-a543-7e4b7318f052 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
39c1dac9-e06a-4b8c-bd8a-4c93aeac0196 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
1170992b-ed45-41ac-93a7-032a54eb0ebb | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
19cab8c8-0dfa-4322-8b4a-05320eb6f9fa | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
1de2c696-a2b7-4b7a-ac6e-39f87a4dc1e5 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
d03823a5-9742-4526-a977-5a7534b82a18 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
b2f9c999-a4e5-4b34-aa30-10c7ac927129 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
8d0e55ff-e064-484e-8b42-b5e0c78a2695 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
55c92808-b9d6-41c7-ace1-392949910923 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
f0166268-2464-4c2c-9702-7aa32f362b69 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
a62bae72-306b-4eae-832a-2129fad5a76f | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
3314c839-49fd-4c84-94f0-ff403a2bdffc | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
1c1504b5-446d-4ff1-82eb-28faf23d02af | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
c21ec53c-ef54-444b-b8ce-623927a779a0 | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
fc9d603a-221f-4c0e-aec3-1aa90c798efe | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
efd3f90f-9739-4c81-a469-48521dbe643d | Pole | 2 | Distribution | 2022-06-10 | 2027-06-09 | Level 3
00b3fd56-db6c-41ff-a851-5eff8b2cacdb | Pole | 2 | Distribution | 2022-06-10 | 2023-06-10 | Level 2
1cea45da-bc2d-42ed-abcd-f25cd56c82a3 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
35ed2a18-82a2-4ab2-b79d-171d24206f13 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
6dbbf8fc-a6db-4565-8976-7174e4606826 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
7b09cb7c-f6dc-4ba3-8aae-e83bf299e90d | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
de614919-df7d-490e-b6aa-3ba696d31a37 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
9f62e665-54f0-4c44-b33b-53c80657a277 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
a16e4a84-84a7-4f5d-9c1b-f86cf42893fb | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
bc7929a8-81eb-4f38-b040-4aab7bf60376 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
c2a855e3-f912-47da-a981-c5cb431607b0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
1bddce8b-51af-493f-8ff2-fac9ee93b34e | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
a9cd4a66-b9b7-42ce-bc51-c7ced036d76f | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
efab264e-d833-4984-8b68-4cffa4b0faa3 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
8823bcf2-5a8b-4e38-a025-12a11cfb0f69 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
f2c2ad53-04ce-4783-a4d9-951e48be4994 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
80e726dd-8693-4556-94ee-30918a08623d | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
9afc7767-cc86-497c-bb2e-b61316415c7b | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
b5f6ae45-7962-4d58-b38a-06dcc5a2cd15 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
7e618191-a9e9-40e3-b7e0-2f90d7ee8142 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
d3d5c8c5-5f12-4ef5-aa51-97ea57ecbb41 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
910c4810-263c-4616-93a4-af5bb4c194d5 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
5b15de2f-4970-41de-8235-aaaa4a3b6961 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
6734fe9d-87f6-4247-99ea-7163f41dc9a2 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
5182dca2-ef61-4303-b834-52684d6930ee | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
3b53f5a8-10b0-4db1-a667-40d33a431ed7 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
356cd0ba-d898-4e07-907c-f35f19af5018 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
eec0317c-6a48-4eec-9716-7ce75e49df66 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
a34c196a-47ca-4983-bfaa-c8821936e298 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
7498583a-fd8a-499d-98db-67d2943192e0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
d21f36af-a788-41a6-a2f7-406f2ccf412a | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
8b8256dd-84d7-48a0-8da3-6a035abf43e0 | Pole | 2 | Distribution | 2022-06-09 | 2027-06-08 | Level 3
249927ef-e0df-4e3d-8205-354d55f3fba0 | Pole | 2 | Distribution | 2022-06-09 | 2023-06-09 | Level 2
e2606b07-1c58-4746-9c85-884dac2ff3e3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
06b47d1d-c5fd-4fe8-b82d-dbd38ea8e0e2 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
b90cadbc-a988-42b6-b032-ee25c611af61 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
44ce2fcd-932b-443e-bd84-2dea92269b13 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
6aa2eeac-a9a8-49ad-8e90-7c088d354d00 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
6efafb16-b4b2-4eca-88a2-06a14c1ea4fa | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
59e80f05-3557-4c90-bcea-bc10df1be715 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
bb7ae4ec-850a-4889-be7b-c7769b3cc726 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
9f5f4036-0b0c-4ae0-b953-e198ca5a87df | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
6e8efdb5-9225-4f0b-bdab-a9e86d23f028 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
a093f7d3-98b4-45cd-9f44-5994f9f7e574 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
72e2909f-3a6c-4947-ad12-a6e0a22ea95f | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
bf041ecd-6b91-41f1-b71b-aceba9ac6631 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
5f5b4618-7268-428c-b0b8-09d42b89103d | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
a91b776b-9d8b-4edc-9a12-b7c48ed066f6 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
d206aedf-c741-47e4-8256-a93cd5b71298 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
d0672f7a-c10b-4a24-be37-c98d5566b47c | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
c7ea0d7b-8c7e-420b-abe5-83e7ab9e7429 | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
7a1111ea-8917-4aad-bf78-02a3f7e22a8c | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
94e06f01-586d-4916-93b3-4858ba59a27d | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
8d8aa830-4e11-4ac9-a531-f31c1b7f7f8e | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
ee259df9-03fc-4a09-9126-d0b360ffb060 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
d8f0eaf7-a89c-447d-9b9a-ff7ffb3bdb28 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
eec22a6c-64ac-407a-8e2d-9a47c73998c5 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
fc4b04ed-221c-4b43-8109-d0ec8d1e23eb | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
776ba426-b852-4b74-ad93-8b094a7a7bf7 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
a3a973dc-676b-49d3-9567-b008c3465bdf | Pole | 2 | Distribution | 2022-06-08 | 2027-06-07 | Level 3
547df3a8-d8cf-402b-87f7-886f2b88ebd8 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
3ff53d29-9563-4f26-a93f-3de4ac86d9c3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
19ec18cf-589b-4159-87e0-a0ce16964c5d | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
00b8c0a6-c1a8-4e54-8c60-19669f2de0f3 | Pole | 2 | Distribution | 2022-06-08 | 2023-06-08 | Level 2
16736fa8-722d-4f1b-92db-821095e5fd60 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
3894c5ad-c5ea-4bae-8275-5b100046b365 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
992ded53-33dd-4611-af76-9f92d103cf7d | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
ca74a331-e4cc-4f8e-ad42-8574c45660dc | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
e1b9709a-344d-4b43-857c-0d6c316f2268 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
7360a078-0a86-439d-a7c0-196dbda5fecc | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
bf012361-830d-45ef-a59e-602e4e18d229 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
2ae64c44-e90e-4ed1-81d0-6959f5fe1b3b | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
6e80bc61-8c7a-44ad-88b3-c3641cebfe45 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
fa02ba18-7868-4f64-87fd-aeb01f8e6926 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
dcac5f3e-4407-470e-be13-c09cf9a31e21 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
67afd26c-d3f6-4ce3-a851-501a1a857693 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
4d25a906-c4e2-4089-ab3d-4449c0fdc7b8 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
f94afe8d-cb88-42db-b43b-d702af3a8d7f | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
d4ae4378-3070-4ca1-9009-183da73c76e0 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
639521ae-05f0-4abd-b6c5-82b96a55caa1 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
a706e177-cd63-4ef9-984c-e27242f5da03 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
8131c11a-f9e8-488e-82f9-892003027963 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
955f7bad-e0de-4d11-966e-c08488217d6b | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
030516a7-37e7-476b-af86-799f23d757ba | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
0d1f616f-770b-420e-986d-f1fc7bd3a990 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
dc248d8d-c700-4bc9-a3ba-d55f7e2fc200 | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
59369ff7-ec57-45e1-8bf9-c0577d184f35 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
590cf76c-a89a-4e81-b739-d18a1642ac34 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
b97a498c-5c5f-48ec-8343-cfd2184200d6 | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
b3382cfd-c86f-403d-bc3e-889a8fa63c5d | Pole | 2 | Distribution | 2022-06-07 | 2027-06-06 | Level 3
d5daeaf8-1647-460c-9095-ec2bd3fd7fdd | Pole | 2 | Distribution | 2022-06-07 | 2023-06-07 | Level 2
00c6c0df-7ba4-46e4-9ca0-f596c6566e99 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
b53ba4da-4c50-41d4-83cb-4664dd6fe869 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
610a11c5-d848-4ba5-a3e9-4b9f049202c2 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
10e75c0d-ef4b-4388-b340-0c723134601e | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
5e665a4a-1cfd-4b7c-b3c9-79ac17054773 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
7b4e4f45-4042-4bda-a3eb-93ddffa49b70 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
c043bef2-8c25-4843-a6d7-4c57315b35ac | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
2d8f792a-2f8c-4947-b3e3-dda69c820c66 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
d4d0f64b-1b9a-466c-bab8-f5c5130ebc3f | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
e99a5261-5b6c-451c-ad50-e048655028ee | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
1c1a3677-ba9b-49d0-a429-8e1417474d26 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
ad4bc031-31af-4954-a81a-dbadd5261944 | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2
6721eba9-26ee-4363-9e7d-f2baf93dfed9 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
fd680597-8140-4f9e-afb9-d33fb48688eb | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
39c9cae9-f732-4d6e-9ce3-4fb4e0ad0de8 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
6ff2103e-9b57-43e2-a8e2-6a016c8de0cb | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
033e80b5-8fdd-4101-826b-1b3dbb4c5003 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
d34c369e-0670-458f-9779-ec2eee716336 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
d8a5981c-99a8-4882-bc7b-fe15da7e877c | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
94a0c8c5-2903-4047-bbea-5334412cd953 | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2
89243e80-21b9-4c81-abb0-ac874c6aef31 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
e2af2c61-872f-43dd-ae6c-a1ffa0134aff | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
46b3736e-d55a-4b84-86f5-89b1306ae357 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
0ed4cc9e-383b-4403-83f3-140be6a2aec1 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
16957b7f-f983-4d49-889d-1c2c9b4c3e2a | Pole | 2 | Distribution | 2022-06-06 | 2023-06-06 | Level 2
811c29aa-d1ab-4bc5-b0de-4dc6d53e7404 | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
eb6dc44a-b988-418a-a0ff-22d1cd79acdd | Pole | 2 | Distribution | 2022-06-06 | 2027-06-05 | Level 3
0200fbf5-5e71-4d27-9bf2-1b0f89bf8a16 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
43501e18-0e84-4ad2-ab2d-2a2b9e7df184 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
d6cd3eed-b6b8-4874-8349-92039cf7d9db | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
a1e8170d-d7f9-4c71-ac3f-8e22425c7ecc | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
5c7abca4-93ab-415f-aae6-894390258a8b | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
5a115124-8908-49a9-94a8-4fde1c0b83ff | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
2b633708-0cef-4527-a8d4-9119b075dfd0 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
0f3b29de-43a4-4019-a79d-eb0d26a27127 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
c3b3a404-477c-439a-9ce5-65cd6e2437b8 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
be5ece9f-9866-4eac-9334-2a0111a72dbd | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
fb367aff-2091-4b6b-b6dd-4b5368d95621 | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
8347da64-97a9-4a07-816e-f71c74c97c51 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
d05e7b2e-80a6-4535-a5de-94064cea95bc | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
bdfc1123-ca3e-424f-a172-c484daa01e15 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
1091024c-4583-41af-ac5f-c8132f98a92d | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
04d90c31-c6cf-40db-a291-c14c7c0d019b | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
79df62d4-4dd2-4508-ba7f-6016607cdb70 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
2628c265-f38d-47c8-91f4-c3b899afc407 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
f0366e2f-3c13-4419-b8da-b0cb60dce6a2 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
a462f44b-488e-45ff-a864-6352b6f8ee8e | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
2a83371c-6805-483e-b8fa-115e4efd9845 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
b18384f7-d98d-4851-a203-1dd41237edff | Pole | 2 | Distribution | 2022-06-04 | 2023-06-04 | Level 2
a7e4c324-e7d0-49ed-a931-d2e0f25d95a1 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
c2b386f3-ff5b-4dd6-8cfe-eaba46a5655f | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
498bbc1e-87ed-402f-acaa-1e43184e88ef | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
89b7b56c-6ee6-4ea6-aa4f-c62b9e0b616c | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
6024e71a-260b-4ac9-96dc-e8be5c7a322d | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
17a22e5b-8b3d-4a7b-b9ef-36576707d486 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
75346032-5ffd-467a-a9dc-26765ebe63f9 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
6f69bad8-f7b3-456c-8901-297866b3168a | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
ef5123cb-d246-4d14-ba64-fff8b68cf143 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
e4207e32-3e57-4e46-aff9-bef016f2e1e3 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
6164a3fd-2e5d-4854-a49c-e1ba315485f8 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
5dbb384d-5ed2-4e9d-8243-c29615898e04 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
143bbcb1-4bff-4433-84e3-d094e278d229 | Pole | 2 | Distribution | 2022-06-04 | 2027-06-03 | Level 3
43d4a2d2-071a-46c9-bb90-b2749196bc9f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
cd4a6116-442b-4d49-b794-8b71fd6785b8 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
1105f55c-a02b-4f8c-a1ab-ec093302f416 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
8b6b3e00-ee3e-48e7-a445-fce9cc685653 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
90fee683-d963-4d0e-9327-346e9f41b287 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
28ff136d-8274-48a8-83ba-c3f34a0bf1e1 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
8eb7d97e-fabf-429c-ac5f-4a8efc01a614 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
85bd66b4-9b62-4760-8d76-49d1113c42fd | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
1dcc91c3-6439-4a25-b616-c0c3163c8238 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
a9408bc8-7d43-408e-8ce0-21b554a0fa6f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
641c7bd6-7e31-4005-b8e0-0e00bc1a38b5 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
ba4ef147-96b6-4d55-9e4b-4fe01bf5a68f | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
0004ef32-55de-4796-a5d2-ef0815b5b4d5 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
365ad973-8dea-4f3d-b539-c451969f6133 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
c72b6fa5-65cf-4ee6-b860-e9bbdd92d250 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
a57bea5f-2613-4fad-926a-bd76af3440e8 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
cc09cfdc-7ce1-4808-852a-f933e92f2e84 | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
a24df196-8d97-4a12-92e6-f5a8922fc6a0 | Pole | 2 | Distribution | 2022-06-03 | 2027-06-02 | Level 3
44d3930f-fed5-4551-95da-28560ea80bed | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
568897e5-692f-4a67-9af5-1ba24d26a6bf | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
0257d981-50de-4016-92df-0a9a2290e96e | Pole | 2 | Distribution | 2022-06-03 | 2023-06-03 | Level 2
ba834cde-e3df-43f5-96d1-33b9be818e80 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
c2f00bf4-d74b-4975-bed9-12f53f52f774 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
ab349ebf-3f7b-4b3e-802a-1025bc172f19 | Pole | 2 | Distribution | 2022-06-02 | 2027-06-01 | Level 3
a0e91ea1-20e1-4eed-b5c3-5408145d40c5 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
344540d6-aa77-49c6-87b8-ee89545406f9 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
d9b309e3-a9ca-443d-925f-931b8c31be80 | Pole | 2 | Distribution | 2022-06-02 | 2023-06-02 | Level 2
544ea706-289a-48f0-8384-c72a8b6ab557 | Pole | 2 | Distribution | 2022-06-02 | 2027-06-01 | Level 3
9b5c75b5-ec13-4479-a57a-3d5eca35c05d | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
a75dc238-4b55-4230-80b5-c570377e8fb5 | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
25b2e274-6aaa-450a-aa2a-c3ceaf205b75 | Pole | 2 | Distribution | 2022-06-01 | 2027-05-31 | Level 3
9955d68a-5c5f-4d3f-ab30-f6c18feb4e1e | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3
7493ed1a-00af-4355-a092-383cf7c0d111 | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3
77332381-4f14-4eb1-b441-72c8b5b8e7b9 | Pole | 2 | Distribution | 2022-05-31 | 2027-05-30 | Level 3
96efef68-d2ff-4ca3-a2fc-f0e3aeb407aa | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
877836b3-dd74-4bf5-9c6b-ff661710bbe3 | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
80b85f3a-9117-41d0-9c76-d1e70b8f289f | Pole | 2 | Distribution | 2022-05-31 | 2023-05-31 | Level 2
35209a0e-9b48-4506-87da-501a290bdbaf | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
e0c988d9-a902-49c3-9c95-34d6067e3fda | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
a2473792-ef56-427d-a95d-423999bf95c1 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
f449ab15-e9ff-45fd-bfae-cfcf326b07d7 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
63365578-58ff-46e9-8336-cf747e38cde3 | Pole | 2 | Distribution | 2022-05-27 | 2027-05-26 | Level 3
ac07bd03-ce8a-44be-bd89-d24904f5f391 | Pole | 2 | Distribution | 2022-05-27 | 2023-05-27 | Level 2
22b4cbd1-3d67-415c-a47a-50cbd2b022e6 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3
e526279b-ed7c-40eb-8099-3746fcdfec96 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3
7d2f1c1f-932e-488b-9765-49ad27882812 | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3
3e92f47a-65e1-4e13-b072-7b1cb5e090e7 | Pole | 2 | Distribution | 2022-05-26 | 2023-05-26 | Level 2
1dc314d0-11c2-4f43-aa8a-a4131e7c003f | Pole | 2 | Distribution | 2022-05-26 | 2027-05-25 | Level 3
59455992-9461-48e4-97ec-f5f9c665ccc5 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
de4f3f45-d0d4-4ba2-a3c6-bf3836c2d426 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
66115500-4bf0-4d9f-bc1c-b7d06e4bce20 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
5072ce8d-9834-4add-a63d-e52acb103917 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
f160d08f-6a1e-46d9-ac66-d902a79b9ed2 | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
d7aff897-46aa-4afe-b1d1-dfa8685cb22d | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
22299901-0f59-4707-81b9-769ec8f650aa | Pole | 2 | Distribution | 2022-05-25 | 2027-05-24 | Level 3
ceea8410-f62f-416a-a7c4-b23e273cf619 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
b5ab0eaa-c29c-4281-b77a-93d8b0114f33 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
9f99edc3-6bdf-40cf-910f-5f84dacab975 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
88fb5747-16b1-4f56-b066-ccb7fab27f4e | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
732c27b2-45de-4ed2-89e5-6e48a2bcfe04 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
0df625a4-db4e-4cee-a6cb-d4dadfd77d3a | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
3c50456e-25b7-4a83-b669-353187ff64f4 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
ebb27f0e-7932-483f-81b3-afdc68154065 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
fd340584-8b88-483b-bf90-26d3f8827736 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
60183bb6-6bcf-472c-8413-081fd6aac91d | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
f4e22ffe-6b08-4517-85c6-75ca91aee3e9 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
5d553ff7-ee75-4cde-9563-0da84159e678 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
13b0b3ca-53ee-43b9-923e-5b6356603705 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
8aeb2d85-050e-477e-af90-c4ebaf7c42c2 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
76f37124-91df-4cbe-8964-13cf992f56b1 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
961f2713-774c-471c-8f08-c3b9cf972127 | Pole | 2 | Distribution | 2022-05-24 | 2023-05-24 | Level 2
d5bb20d8-2408-45e9-b957-d2f5e1eba677 | Pole | 2 | Distribution | 2022-05-24 | 2027-05-23 | Level 3
9155a036-ddce-4153-a0d0-44c851a12fca | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
5a41558a-d04e-4c48-b213-1a82a99d62b8 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
6e368a25-af71-4924-bcbf-00c3c50baef5 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
17b25550-373d-4c9d-bbcd-882f32c45001 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
dc7877b6-a9b0-4fe9-8240-9ef7cc1dbfc9 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
d3043195-c9c8-4020-b207-be73e2db89cc | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
efc9b24c-0113-4f8d-8387-17679624b0db | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
3c50df41-b1cd-4c2b-97be-80611e16cbaa | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
71a4bc93-ed2c-485f-9823-2345f2cea45e | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
abe60f95-1731-414e-b847-a507c4ea0969 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
2f152e79-307e-41cf-a830-5f5389eec106 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
3a855c2b-1857-42c8-8850-c51d01e2f481 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
2e353a9f-445b-4240-8dbd-3236eb6e8d23 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
47c58d6f-9aee-45f0-ae9f-05b326bb32d6 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
46fa1606-63bc-41e6-9f34-efad31c5f0b9 | Pole | 2 | Distribution | 2022-05-23 | 2027-05-22 | Level 3
ac237f28-9555-4f50-b984-7528333fadbb | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
7459bda8-3abb-466e-b42f-3268ac203cb3 | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
055dc2a9-be82-49c3-afb8-88fb39888a0c | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
ae24e9d1-bdec-41a3-a8c2-89f32bbc48b5 | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
09a260c3-77a5-4772-a258-5a1a5b66ea3a | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
449b87c6-5e53-40d2-8166-0665f7a1d879 | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
9c0e2499-44d6-4e31-aff9-74f207158bdb | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
010e0020-c8cd-48fa-a80b-834f2967770e | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
82ea73e2-0efa-45ac-a8f9-98bf59bf105e | Pole | 2 | Distribution | 2022-05-20 | 2023-05-20 | Level 2
314e7b35-7ea7-4eae-9c90-e028ea06a985 | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
4ad9da18-917b-4291-8884-271f04675abf | Pole | 2 | Distribution | 2022-05-20 | 2027-05-19 | Level 3
ec196a38-98dd-4e08-8eea-7c971650741f | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
304f1e88-33f1-48e3-ba34-7bbe004eb742 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
49e8d807-fce8-43c9-bceb-02bf5ed9d1f0 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
db876965-5197-403b-aefe-95aad0258ce1 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
4e7fa2fa-8c1f-4f5f-bee2-8b6dbe927515 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
93a335ca-82cf-4835-a281-331b5e83b781 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
52f93104-8448-4fef-ae59-88653391c9d6 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
3e4d08e2-1296-4bc4-b3bf-81756346a887 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
ade811e7-b55a-406e-bd85-e3cd30edb095 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
ea5785b1-bf8a-4b71-89f4-3af532006b39 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
7d8414b7-ff9a-4d69-8992-df55ac0cbc62 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
c8e5f9a6-ce7e-48f2-80b5-a5e0ba803450 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
50d35370-528c-423c-bd11-8da4b094cd89 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
9c438d86-726c-4e65-a203-d2bcac9d287f | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
50abee65-818f-40b3-8141-6948c17c2d94 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
6f2df028-03e9-4e56-b18a-2c4bfb112639 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
5220555d-530b-45d6-b4bd-ee50b223879a | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
5c21b966-f6db-41a9-bf62-b3d9d2f34c3a | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
8460ce50-0b37-4933-ad25-95050f88c719 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
536d83ea-f364-426f-93a5-0a620ea9406e | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
571f0020-9591-4622-9474-2b8e91dfba03 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
d542c0d8-df17-4f29-9ec2-fc934ca050d7 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
123a9e06-62e8-4afd-ab56-247195019dbf | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
7b89fcb4-3cd3-43fa-9592-c47b1ca957e4 | Pole | 2 | Distribution | 2022-05-19 | 2023-05-19 | Level 2
3491b4d5-1c53-4b90-9947-3be1e233dfaa | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
f3b1c574-0fc6-4e8b-898f-170248306465 | Pole | 2 | Distribution | 2022-05-19 | 2027-05-18 | Level 3
de823bc0-8d63-4926-a57d-7854fc53a55b | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
6b877e8d-8acc-4e10-b718-5eb75c248112 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
104950d2-0272-416f-8686-84215cf155b0 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
0d80419b-bf9f-4184-b4ae-4b27ae58c222 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
aa65076f-4933-4807-b073-434bc9591816 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
a1ea593c-b185-4196-b046-595f5ba05e97 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
c311b3f2-bf1e-4e29-b177-17934cda0ece | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
d0283dad-cc53-4d92-a7fe-42be13e315ea | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
a43c9627-0d8d-43a5-bfc4-4cd8414b681c | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
74266696-695b-4964-b1dd-a2b63713e3c1 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
f8190310-fae6-4b2a-b517-ab1f4388407f | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
35d43c75-e3ef-41a7-b070-4c6eac7d844b | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
32333d13-64fa-47a1-9e56-dca8e3eef442 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
f89edeb2-c46a-49f4-8055-92bf361b8f29 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
0ad3329d-1306-423e-90dd-7b311f7760cd | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
4147ebb7-d785-437d-94f1-c63e15439295 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
662e0bfc-3131-4f47-8230-40fbc4fed84e | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
b3ac1287-4de5-49ba-a161-efe7e47413b8 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
c267a96e-9a05-4bd3-96de-095097d5e278 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
0707aaf2-c0ae-469f-88b0-3cb3981aa796 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
5ce1a4c8-5c74-4e61-8b60-a253f34df4b9 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
a26810fc-68ac-457e-8ea7-9abaccd6588a | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
5903c963-16cb-4a0f-8e38-f800c9e244e8 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
175f420f-e847-4184-9998-fd23d168f48e | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
6bbf3f82-28f2-426e-9b71-1d50074026ce | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
0486a58f-bdb6-45b7-ba7d-28240ba67d45 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
82a7526d-7a2f-4475-a870-68c09b9c835b | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
c830a559-ab82-4815-92d3-c2386f52acad | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
e915edc4-9537-4dbc-9a78-47734a6ab98e | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
90b4f5e9-41c8-48c4-9322-70be8a13ca5a | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
3b773101-870e-4a08-ae20-b02ab96a33c6 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
0640b799-8f6a-4f11-8d18-dabb435fe145 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
2edafc4e-a5e2-4c3b-a0df-6a25975ca7b0 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
46fa30e2-97c6-4a32-840b-7b3e9f31d2d8 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
6b04fb6a-31df-48d0-9fc0-334cd1a12725 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
92424739-e331-4e40-a749-7a329c235006 | Pole | 2 | Distribution | 2022-05-18 | 2023-05-18 | Level 2
8732133a-438e-4ded-ad8b-cec9ba855769 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
1864c947-254f-430d-811c-db73e773ef64 | Pole | 2 | Distribution | 2022-05-18 | 2027-05-17 | Level 3
cf4b55c9-5aba-43ca-b132-d30426043996 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
2b8bd0da-72b9-4866-a727-2242c6f6e6e6 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
8b93c3a2-edd4-44c4-bae6-07877af99f1e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
078072b0-71f3-49ad-bbfe-bf824f9b3cbf | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
62a80d46-8938-4e92-90dc-5cf6e3998b80 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
c162c34b-39f3-4869-af08-224f7af9fee9 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
f589bd31-b3c8-4344-ae97-b49df98d8913 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
97df6be5-a6ed-4314-abb9-e8e2e1270fa0 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
a6ce0b2e-ac23-4aaf-a34b-558ac239c1f7 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
876a7730-77be-4090-bc98-50db532e4141 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
1070bec3-2966-4e39-8354-b72b3d08757f | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
8346f35e-f234-47aa-9434-a2116b44bb26 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
6e168b59-7a0b-4bba-a899-81f7a92ad7f6 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
f016d9cd-42e8-402d-9607-a374b1a1eacb | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
219e7cd2-12ca-4b13-a8b7-8621badafdeb | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
714a5bcf-804b-4038-a5d5-352eb694ab5e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
488caa30-ed3c-4f9b-9b11-c1e178d6b86e | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
76feba2b-2651-4f98-8bb7-bd8a7faa8b1f | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
f2d4e6dc-2309-449c-b1a2-c556636c8fa4 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
4b62cb6e-b2d5-4723-ab9d-a64436a57b43 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
c4055f7e-19e9-401c-8d65-1c7cfca7f892 | Pole | 2 | Distribution | 2022-05-17 | 2027-05-16 | Level 3
0f070b41-15c3-4d82-b992-9d73209fa178 | Pole | 2 | Distribution | 2022-05-17 | 2023-05-17 | Level 2
5a6e5bd4-88bd-441a-a0ce-17c749ae2ce3 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
1159c80e-4c3b-45d0-bba4-21f8f8f4d773 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
6d6c1649-9610-420f-a93d-da286d9a99bc | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
9557e282-8f9d-4a1c-9f17-3c7931ec364d | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
22589855-1772-4d68-85af-91b3e958f9df | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
237dad7d-48a8-460e-8c48-89b67321a2aa | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
e2c3e5e5-b4db-4e9b-b384-c3a5d7977276 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
519b67dd-89ac-4b6f-94f8-6e3f24d8e250 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
ccf999ef-e5d5-4a6d-9874-66232e53efb9 | Pole | 2 | Distribution | 2022-05-16 | 2027-05-15 | Level 3
06da5821-f246-4f7d-9c6f-752a68a848f1 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
db5f8dc4-33e8-41e9-bb0f-0ad577f75c62 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
d773336f-c1b1-4778-94e1-b32fa1bd9a10 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
396e1662-d2d0-4286-95fc-d376b2e62559 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
d4ce3d9c-87c4-4ca5-8d17-dc551a99da55 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
1ef8c973-b823-4a2f-a5d2-e06b849c4a90 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
47c89d3f-4265-4127-bae6-7ac6891e3a39 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
9d666eb6-1b72-4bbd-ad54-88d2094f5c34 | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
9ed03e98-53ca-46a7-9617-77e5ed9ffb1f | Pole | 2 | Distribution | 2022-05-14 | 2027-05-13 | Level 3
0680f341-6c1f-4e59-baf0-e1d4c69a21ae | Pole | 2 | Distribution | 2022-05-13 | 2023-05-13 | Level 2
85ee3e80-4f20-42f4-a67d-38af9b9511d8 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
4f2a3573-f2d9-4ff3-b2a5-afe6de78150a | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
e84f7c0b-e5e0-41ac-891a-c728f3990d34 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
fa40f187-c389-41f5-9127-aa22ca5bfa94 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
afaad66e-9a9a-4bf5-afc2-7ee64c669dbb | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
d833749e-0c56-48ca-a0fb-7beff27afedc | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
f60dc076-11b1-4df4-b652-af532aea360c | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
637599e0-ec51-4add-9d1a-42663680cb5b | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
b3bf5bcd-09cb-418d-9e4b-aa111694b225 | Pole | 2 | Distribution | 2022-05-13 | 2027-05-12 | Level 3
f724d32f-943c-4cdc-9711-87ce46c7939b | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2
d5aae43c-3c1e-4043-88d8-def61824f9db | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2
8fd1d9c4-bf77-49e7-9abf-b1012c4672fb | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3
0204041b-1a77-41c7-9247-42c3b34be7aa | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2
256b66b1-2ddb-43cb-ad76-83810c9f160e | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3
194dc582-a29f-4dbc-a317-91b32acef012 | Pole | 2 | Distribution | 2022-05-12 | 2027-05-11 | Level 3
38683f2a-5adb-440c-a1c2-81f1288d9be0 | Pole | 2 | Distribution | 2022-05-12 | 2023-05-12 | Level 2
78d3cfd8-53ce-4ff8-bf20-fe77d7eae1e8 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
33b79351-792d-4d2d-835b-6d7d670c416d | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
220a05b6-c830-4ef5-a6da-fa4170b7b94f | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
972e7dbc-c100-486b-8177-670cb2803156 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
32c6b6d6-cb5f-407c-878d-0985e5c5acc0 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
e9ae9ee6-2fc5-4b44-9733-cd5cfb8bb0d9 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
7dc01b1c-02f4-4d88-ac33-1e5c9abc506b | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
be154a97-5b53-4013-9a8e-4b8643bf52bf | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
505e633f-bce3-47aa-85fc-1234122e8ba7 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
13100467-81e8-4d66-aa0b-f423075276be | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
9ed43638-b9d3-47f7-8d2b-087c225373ad | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
294674d8-d9f4-4e88-8461-86d97e46f4bb | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
3d9dac08-5e73-428a-9723-b3bcc0600b01 | Pole | 2 | Distribution | 2022-05-11 | 2023-05-11 | Level 2
6629aca7-8fd5-4d3e-a714-eee9437ad511 | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
49fb5ba0-64c5-4e38-b0f5-2a8c899d902f | Pole | 2 | Distribution | 2022-05-11 | 2027-05-10 | Level 3
dd6e61f7-a06b-466b-997a-a0a8649f4e58 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
f4506190-281a-465d-9d46-fd99a42d869f | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
ec391e67-c3be-43a3-aec4-a087563f7ff6 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
30ac2746-26bb-46c5-87c6-acf4c25fb429 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
b6dded03-7c16-42f9-a8b5-82641a92bef8 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
73c34230-7354-4775-8ee6-23a6e3fa1583 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
108d34d8-4517-448c-be2a-1186078e302d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
547a0952-2197-4b32-9bbb-36d7249a625e | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
4c453254-238b-4546-802a-dc8ebee7a6c9 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
edc9c05c-0227-461b-8f01-842471a3381d | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
61bcc74d-e717-4103-883b-297b3173ed70 | Pole | 2 | Distribution | 2022-05-10 | 2023-05-10 | Level 2
0678f8a2-b3eb-4de3-8787-e17649350717 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
a3b2fc8a-8493-41d0-b4d3-8e0d75d04f29 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
99456af3-f563-4a5f-b6ae-8832e8654d17 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
e517c7dc-17cf-4c9b-8014-32d596d7b441 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
6ae0df42-bf1c-4842-83d3-fcb69c7acece | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
cf9c32c9-ead5-430c-a5b3-d98b54e04c52 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
3fec7da1-48ae-4ce1-883c-83dd0f972d9a | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
ab67e711-e865-4782-bd62-2d367eb475cb | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
2c011b87-f707-4c13-b9dc-4bfc441020af | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
41947854-6932-4f22-b900-f1f6a97a7688 | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
7e35ce2a-9bd4-47f5-8e97-f4fedfda30ab | Pole | 2 | Distribution | 2022-05-10 | 2027-05-09 | Level 3
63057f2e-0863-47c1-8d75-4a0eebe620af | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
1ccc9596-f125-47b2-ab94-951452106206 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
e22f244a-0041-4546-b830-e561007ff366 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
56b1a033-198d-4bc1-a07f-0eb32b0ed58b | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
9ea2fde5-4db6-4f90-a51b-174fcdb5e656 | Pole | 2 | Distribution | 2022-05-09 | 2023-05-09 | Level 2
f5781dcd-e01d-40c4-b100-2d9f63e273a9 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
f70d9920-31e0-487a-81d1-9d74e638dfb4 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
900da43b-04a7-45ae-81d1-de5f0af9f3b6 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
ee2fd42a-3d23-4a9a-a0aa-58202834ac50 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
a5003db8-217d-4336-9f3f-db97e213fea6 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
a42f0493-0684-486d-8333-e2289e0c3161 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
bf0aa8b5-a941-4939-a381-93910f7fc02e | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
90783e95-7e39-4992-b4f8-71b3128a9482 | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
dabed6aa-f8f0-4745-9501-28e7e84dcf8f | Pole | 2 | Distribution | 2022-05-09 | 2027-05-08 | Level 3
026d47dc-553a-4ff9-a20f-23e44e64751b | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
b605ea32-f156-4465-8b97-a49162316d92 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
fe002313-099b-4a80-ac35-3a3fc9088b7c | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
5a5a41fb-162a-435d-937e-1b032e906c4c | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
0b1e0fe6-1291-41a8-9a1d-861417c02db4 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
ad25fa49-2bb6-4179-8eda-e9ac9f8493ff | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
2737454e-4260-49eb-8111-875df1cb3b21 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
7f8d2fde-1755-4d97-91f0-eeb4f092bf32 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
8b29ee0d-724e-40bb-ba29-ac0ebe8559a9 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
93ada3f8-e853-4787-a2ed-f0b7870cd766 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
866b2edb-b250-4424-96b6-c3b86a0976b8 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
b0e440c5-168e-4668-8c38-693f00bd2aa7 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
352cd739-a6b4-4fb3-8e36-c3e93f22bb63 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
810f9668-2368-4863-98eb-093f7cf724fa | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
fe2e481d-f037-4f69-82f4-c7a5c959308c | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
8a5a4df7-ccbc-4fe1-a564-d7c289f777c1 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
3ae6c5d3-c414-424d-a062-5333682d7029 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
b5f26494-e562-47e3-a3bc-d18e02851bef | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
e7e3c85a-f8db-45d5-8aec-09f48a3bb715 | Pole | 2 | Distribution | 2022-05-06 | 2023-05-06 | Level 2
4392d768-0901-4ca6-9d77-2ed47f7efb4b | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
f446b843-8afd-416b-821b-2148b5ec5c88 | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
f13f49c2-aba6-4985-9435-eb679b8dad4a | Pole | 2 | Distribution | 2022-05-06 | 2027-05-05 | Level 3
df73a8da-26a1-42cf-98f3-2ee96cc3c1e9 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
838dce41-ca2d-4d97-a272-98ca91f47122 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
500167d1-0ff0-4bba-bea2-7a5a742042af | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
8c54cc1f-12be-43df-becf-bc441ce52540 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
ec320cce-d1a4-414b-957f-415718a43756 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
723a343f-4e51-4bf7-a265-9242d90af7b1 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
5a163363-d9be-49d5-81cb-72b428b16110 | Pole | 2 | Distribution | 2022-05-05 | 2023-05-05 | Level 2
13336123-cfb2-4bd8-81e7-16fbb24084fa | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
0d3a0903-4db9-4957-9ba4-337edfac3076 | Pole | 2 | Distribution | 2022-05-05 | 2027-05-04 | Level 3
26e12f30-e2cf-4a51-ae6e-051856c267e4 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
92155074-1e9f-4f27-933a-53155c709102 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
a153e5b7-67ad-4956-af3f-21da2c6992aa | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
0f3a120b-7446-4255-8ec7-6c7f193af38e | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
ad92c3c1-1c63-48c8-8684-e93fb0e004a2 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
2dcec391-80df-4f4f-ad23-090ea3738b4f | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2
bf380df4-2c23-4518-80c6-9a6a4fb159d6 | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2
48c01278-af28-44e5-a26b-dd1d010abdf0 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
7814f53c-c373-417c-a2d2-629c3ac77954 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
eddc312f-48a3-4918-837c-2a59bb177e38 | Pole | 2 | Distribution | 2022-05-04 | 2023-05-04 | Level 2
2d0208ab-1bdd-4532-a626-e644f08d8c7e | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
34f2c261-e464-4c56-be2f-3610ddae6394 | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
b97f01d5-fa57-44cb-815b-daac957d9caf | Pole | 2 | Distribution | 2022-05-04 | 2027-05-03 | Level 3
076d4ef7-a837-4601-946a-029bef5e14ba | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
77182ab3-77f5-498f-beb5-85cc3deb90e0 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
bd894413-e933-4360-912d-a32f8fea01d7 | Pole | 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2
6c05f3e6-37bf-4168-b966-e1438fc2d73a | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
eacb7d9c-4cba-425d-bed3-504356e99776 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
d7eb3ac1-6b18-4425-9cdd-373363321ecb | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
d8032f20-9dea-48b3-914d-27c54b7f6925 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
e52e8fe8-90d7-45f9-b80f-3df0403efeb3 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
228d2cb7-d7a6-4a36-a73a-283efe271485 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
89cf2416-36ec-48b1-bb4c-9052cb4369fd | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
8a7b2d40-9237-4655-a519-21efd6f22c7d | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
61173988-c7b1-48ad-b17a-2d1497dceaa6 | Pole | 2 | Distribution | 2022-05-03 | 2023-05-03 | Level 2
48518f1d-2595-40b5-8924-6b742fdcb17d | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
a203d871-6590-4aec-8e96-ef991e36f81c | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
0c6f7350-a4ea-45fa-ab22-370ebbee41e7 | Pole | 2 | Distribution | 2022-05-03 | 2027-05-02 | Level 3
318c7b46-e673-4d1c-b4cd-7f033c31d376 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
0c8e7d8e-9899-4ba7-9984-e99feba3ad6f | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
68ebfe06-637e-4f88-896d-96645b530d1b | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
a505d7a8-f7cd-4f25-a549-362868951d27 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
ca695a36-c0f7-49e5-92eb-87e275d4e714 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
6b025a29-d9b0-45eb-8b6a-ceb7dc88b186 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
4e8d5dc1-856f-4046-805e-8a954648c489 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
df68ef83-7e79-4448-be29-50a71572d360 | Pole | 2 | Distribution | 2022-05-02 | 2023-05-02 | Level 2
7c473661-9e38-41b1-abcc-a26a97e1d21d | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
e2095962-bdf5-4afe-8797-0233055b99e8 | Pole | 2 | Distribution | 2022-05-02 | 2027-05-01 | Level 3
5e027456-795e-4b81-a8d0-86d8c146ea5a | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
33a55016-349e-41fc-a0c6-e49767add75e | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
341b548c-ae42-4302-9ae5-3897ce9f0680 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
d6ab7c48-9bab-4fbe-9b4d-9d860a9c2e0c | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
24146a7b-51ee-4e81-931f-e2fd66909a79 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
a4fe59d9-672f-4c29-a3e8-738250b92127 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
246b2e48-94f1-4411-8a1c-d06c04444f16 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
594dd444-ca51-40d6-81a4-94385fd0dacf | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
1536684a-211c-40db-9af6-4199a916d950 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
1761b84e-f0c6-4206-ae56-3e9464a42f90 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
72db2865-e80d-4dad-898b-f9c98b309b2f | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
e1bc60cd-916d-4277-a384-2de9ebc1cd81 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
7aa47c82-9e5f-4760-8cf5-15e50e48708e | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
da380639-a5b4-4d9d-a9c1-5cf6b88927ce | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
9349ea89-26e4-455b-9bd8-3d9f11f2317e | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
5bcb458e-9e6d-408c-a2be-98e3b88b0ec9 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
bff92b25-2566-489f-a195-93767608bd67 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
8fa52884-10f0-4eb6-86ee-aa719caf9619 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
5f92a481-35f9-4857-b3f2-eb108755e8fc | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
e203f001-da55-4f5c-8a55-2da7a8b35868 | Pole | 2 | Distribution | 2022-04-29 | 2023-04-29 | Level 2
e6494aea-47fa-482d-8648-15ab5747b169 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
3d8bd53d-c6b2-49ae-b822-850928f81956 | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
0234498d-ad8e-4b40-8afe-c0b403f2ac8b | Pole | 2 | Distribution | 2022-04-29 | 2027-04-28 | Level 3
3405dcee-99a7-426f-8fd8-bed4543525e9 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
b6ecde73-ce19-4b8e-8f61-e46186057791 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
fb9b2ead-06e9-4098-bbdf-db0fc5061f8c | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
42d32473-1f99-4f39-af4c-34f7cbca946c | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
0dda6f65-eb19-40b6-b945-4fd6ca182da7 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
4898f1f9-ca92-4abd-a39a-56c31bca5fcd | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
3f2d58af-39fd-41f0-bc76-431a4b0f6fce | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
2617f26d-02ce-4ab6-8fd0-91eff4d3c449 | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
d2d1e4dd-0faa-42c7-a490-9f331f9fd649 | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
7a7993fc-5cfe-4c56-8496-d721b321e80c | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
77e090c7-9e60-4cf1-a15d-ea403e60a9fd | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
17a215a7-a6cb-425c-9e29-130efbaf6fe5 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
27e3db0d-9a6e-4c92-bdcb-60af8abe9e3d | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
fd946841-35c6-41e7-a1f7-55e477a766da | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
929101b3-b50a-4d44-84be-00e737994858 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
16a39b9b-e032-4f6a-a032-aa2a246c387c | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
3aa036e9-1a77-4653-aa81-42b481a56beb | Pole | 2 | Distribution | 2022-04-28 | 2023-04-28 | Level 2
198dbe61-54ae-406a-ac56-24a2c8805765 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
ec81eb58-86e6-4ebf-a94e-aa7e70ab80c8 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
fdb9518d-3c84-4bbc-b469-0f43993ffffd | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
f0d50760-95a9-4cc3-a86f-8c427405f517 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
a40b1cfd-b0af-4f5a-a559-507feb57f89a | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
5e5568b1-4fd2-4063-89bf-358efa693e7f | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
82f7a0e2-0728-42d9-a38c-f0b89ecbc160 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
89271cb7-de87-400b-b17a-4c0701d14603 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
e1c833bf-37ca-4e04-8d08-70a7ebee73b6 | Pole | 2 | Distribution | 2022-04-28 | 2027-04-27 | Level 3
8250d725-cc01-43cc-8f23-3254f0e72d0e | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
8301bf99-a3a6-4415-82a0-5ad16bd85f1e | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
8b9d1e14-ace4-4f85-aba7-b989505dd28c | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
b5ca188e-f899-4b0a-96de-c11d5246f427 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
a985b574-9cde-45f0-8a41-e914321f1b1c | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
cb5945f0-9be0-45d6-8bfe-5bd12f4dd4af | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
26768c99-8868-4ec8-b111-d76c648afdfb | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
3636c18b-c058-4485-8039-e34bec8cba11 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
212cb912-e24e-4343-bd3e-bfc6145ffcb9 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
0a0bacef-9fc4-499e-8558-647fd2c0be1f | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
564a106d-0ae7-4e5d-aa4c-e1fb43ea2901 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
690e78ee-29c2-46a3-81d1-af6c4c5f1c79 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
22bf9b5c-b001-4d92-902c-43c4733d2574 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
d366d640-46a0-4f93-9247-7c19cb93fcbf | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
6ebf55f6-3536-4e8f-8754-927eaad90ecc | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
b6937104-4532-4756-93bf-b225d7135eb6 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
b5780f2f-838e-4fdf-8b5d-df06ce8e5484 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
8eb424bf-e1e1-463f-9772-2cca597d3be0 | Pole | 2 | Distribution | 2022-04-27 | 2023-04-27 | Level 2
54f86c39-892e-46d8-941c-f9ade22d4870 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
1fd43ccd-e5e4-4e3e-87df-4397fee6dc37 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
0318d11f-2f87-450a-b603-43d888a89f72 | Pole | 2 | Distribution | 2022-04-27 | 2027-04-26 | Level 3
40f404f7-dc72-4dc7-8d67-686cfe847e3c | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
d60e3007-fc96-476a-9381-ad3643717c56 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
0367aa0d-f46a-432e-959b-d3859b0a17bb | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
038f91bd-8454-46a2-ae8a-e4908d660e69 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
9d29eb7a-6ea7-44e4-8ed6-023beb64f8d9 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
069ed871-507e-4c1e-846d-c92cc464c1c1 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
f4a4f0d8-bb92-4f64-b3e3-79cd6479c452 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
7bfc2379-96f5-4571-8714-afb7ee873d07 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
07d834e7-8f2b-49bc-87d1-27a6fd4dc5a4 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
cd37d0b4-ddbf-4d47-b6ad-43d58fdfce36 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
41b66920-69dd-48f1-b4b4-98ddbc999562 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
ae7f8db5-b9c1-414b-91ed-49c90a051ce9 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
fb283363-5592-4be7-9764-10b624714f82 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
758e15ff-a633-4495-b376-8b9a44799092 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
663f2b28-a649-46ef-ae1f-4bf5ae717110 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
07bfed0e-c746-4c8f-917a-4248316c2af2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
01d92645-4777-4f1d-b242-0334b457dfb2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
53a37f78-8993-4739-af06-b616d3ae3e77 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
72b0d48b-eb88-4c83-9be2-ae4576358aea | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
6a43f961-bb20-4849-907f-14538694b5e4 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
589ef09d-4c69-46b4-bd8e-274ab38f46bb | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
50bec5c4-71e5-4185-bf79-5361312f15b8 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
834a7a1e-47f1-41e2-b4e1-40aacdb85f78 | Pole | 2 | Distribution | 2022-04-26 | 2023-04-26 | Level 2
8ea913ab-45b6-42fb-afbe-cf977650b049 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
5a417363-4ed5-4d92-8015-12be423cd2d2 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
52f857ac-6d0f-4ba0-8e97-19cc8588bb8d | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
61e83759-0271-443d-abff-525b6fd7e48c | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
17de24c2-dfd4-4fd5-98c5-57ccb2182bb5 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
0833051c-b789-492d-9806-12e8358f4344 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
beb398ae-2ae3-4eca-9999-c9c5570f9792 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
b2606c75-08ed-491d-87b4-5d9f1cbfcce7 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
85bcb33d-0c35-4fa8-be16-8f4a22edd160 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
ef23f2bd-81ca-4be9-8160-d13efa8306c7 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
e4499eb4-909f-47c5-bc44-525058e7f990 | Pole | 2 | Distribution | 2022-04-26 | 2027-04-25 | Level 3
51b1eadd-a6ed-4bb3-be36-c36e88e52843 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
2f243988-2fa6-48d8-abe0-8492a97c81c5 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
5d1cdcf7-cf77-4d35-ae7c-f4eabca8e997 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
3dbebf98-ac14-4bee-9c02-e676adaf0872 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
0abf462f-4a89-4ad1-93a1-5c809be35dfa | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
a7685d84-109d-4a27-b5ca-1deecf092af3 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
16a33b52-5c49-4a86-91c8-2c426afc256a | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
77b6f8ca-e4a6-4ef8-8e44-f9036fe953a1 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
b54999a0-3cfd-4075-95d7-bc9c75a9d4f2 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
d3e0b15a-ce35-4a71-811f-da58dc85a696 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
710d83bb-840c-4a36-86a3-5a843c89ee4d | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
c65a0758-fb70-4012-8743-352dfe10f458 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
c6a44c2d-b649-4509-ac88-16dff9f42731 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
eab6a9b3-f84e-46ef-9457-61187b254332 | Pole | 3 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
2406f9f3-e6fe-47e2-ae4a-d7416dd2b1c4 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
a008d37d-0cbd-4ee2-97f5-2d20d394eafb | Pole | 2 | Distribution | 2022-04-25 | 2023-04-25 | Level 2
ef4075bd-e271-46ab-8913-3db49c6b78fb | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
31905159-7ab1-429b-8efc-06ae07dee55d | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
7df8c0c0-5b6a-4bd5-80e8-b7f7a98175c1 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
04a9d646-9efd-4061-a678-7db7600e449a | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
8015a689-bd64-48c2-a191-5a0f687408d8 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
8bea342d-0196-48de-9f71-45cb08c431d5 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
9639183e-8204-41fb-88ed-13a524577e27 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
502368bb-6d99-4105-bda3-8490f7be749e | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
777597b1-ae99-42ef-8558-8ba002ddc946 | Pole | 2 | Distribution | 2022-04-25 | 2027-04-24 | Level 3
54c6c5c7-af47-4c91-92b2-813046992f50 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
0cdaa5f0-aa98-4c2f-a7d5-d704aec50ed6 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2
044cc782-1ed1-4432-9585-6b85bb948fbf | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
39247234-a6cf-497a-8401-46673d79b298 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
23bd6e0d-7625-4a8e-a9f1-8b199e2a657c | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2
c48b42c7-d669-4c37-98ad-fe93558dfe71 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
2a27cfc0-721c-433a-9041-b5969624522f | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
29b603ab-ec6d-44a9-8b96-6b949b6492d5 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
e79d5f6f-bec2-4403-b983-9f2af8015a75 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
645df035-6d32-4acc-9e66-2e458f1374a3 | Pole | 2 | Distribution | 2022-04-22 | 2023-04-22 | Level 2
a551285b-18dd-46b8-9be5-6324e3b5fb18 | Pole | 2 | Distribution | 2022-04-22 | 2027-04-21 | Level 3
1f30e40c-e8d0-4759-b5d3-68467e64ea48 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
d5ec9669-37ab-439f-917f-9370f770d13a | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
a5ef761c-4fdf-43a0-95e4-cacbc7df56e4 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
ee281a7a-954e-4279-8d5f-e3d4cdd508b5 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
58bfd453-3669-4847-8464-c3906ea0539b | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
b41acc02-a3cb-4116-bbe4-ed092a439a81 | Pole | 2 | Distribution | 2022-04-21 | 2023-04-21 | Level 2
21cc9ccd-84a4-4e94-b033-832ca5e79404 | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
af2931f1-1663-45ca-9442-79950f592897 | Pole | 2 | Distribution | 2022-04-21 | 2023-04-21 | Level 2
6dd093d7-4d98-417b-8966-989557e8e47a | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
515f9e6a-b336-470c-a130-22c684af9fab | Pole | 2 | Distribution | 2022-04-21 | 2027-04-20 | Level 3
9772a723-2f64-42e1-8cc0-5f1f82b1178e | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
f1b338dd-4222-4fb4-917c-e7faec94a149 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
e7870a9e-d735-4842-a675-f0b52c9d1bc8 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
97873176-0c76-4b9b-9c10-0f7645ee7bfb | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
bc9af2ee-8b89-4018-b278-d05b9f6c55db | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
273ba082-00f7-4349-a975-b4e9df59307e | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
a73c2a3c-debb-483e-b3a2-a01985a052e9 | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2
e0dc8417-b16e-4bff-b3d4-49214f604e2f | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
db9b0309-2e8b-42ab-86d3-196ba68add20 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
79a0ecdf-3fd3-4e45-8e16-323b372112cc | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2
4e1d73d7-3d14-4f6a-9218-bfd869079ee8 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
9eb99346-4d3a-471c-aa00-1effa3959605 | Pole | 2 | Distribution | 2022-04-20 | 2023-04-20 | Level 2
78d1ccd9-3911-4bd2-9c00-40f31eb4a38a | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
3abac912-64b6-4103-aabb-354e2cb0dae2 | Pole | 2 | Distribution | 2022-04-20 | 2027-04-19 | Level 3
d091772c-f9c9-4cef-894a-56c98ff09b58 | Pole | 2 | Distribution | 2022-04-19 | 2023-04-19 | Level 2
e05502a5-09c8-4f79-996c-f04ee625a61f | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
180dddd5-3a08-4127-80af-d0a2337d7d6e | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
ab279528-8f1a-4ad8-b7c8-fea9d47704e1 | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
6cba7a52-ab89-45a4-94ad-9102f1a5e49e | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
56868fd5-9ff0-4f89-82d4-7be7a56e6942 | Pole | 2 | Distribution | 2022-04-19 | 2027-04-18 | Level 3
56cf1067-2051-4971-8821-6c9641dd1a41 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
98a38247-b04c-4ac1-a41a-1562fd198823 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
4d7fbda5-e43c-46a5-b778-4afc68793f4f | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
b332e4f1-6cde-41b0-86f4-7d0b268d74ce | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
84533a32-7b4d-4dc8-ae99-e970c426cddc | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
52403095-c006-4df4-bda1-0ef42303f754 | Pole | 2 | Distribution | 2022-04-18 | 2023-04-18 | Level 2
254b66a1-7352-4c51-9f61-8cac67d87333 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
0bd4c211-2fa0-4ffc-a3a3-bcded4f6b868 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
e327c1cb-1cd4-4877-b74e-782d514eb4b8 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
1b308e41-8eef-4f01-8695-2f778faf43f6 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
9406777b-4441-440a-9a39-08327bd49676 | Pole | 2 | Distribution | 2022-04-18 | 2027-04-17 | Level 3
7de8a9a8-846b-4e38-96e9-a4952b78d819 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
7cb83437-f6e7-4e3b-9150-24b9dff21a2f | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
5f9f2e8d-c191-46df-bda3-118d3523d4a2 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
22b5057e-3d76-4c55-8b83-048e78ea29a6 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
98219143-1471-4aaa-a415-ba60d1b34d14 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
3b25ab8d-845a-4f13-823a-e24707d3e252 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
b0578be8-ff41-49f0-ba78-8b5266a06dee | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
8739f452-dbb5-4f7e-9b92-be33290ec8c0 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
34188dce-9593-4da6-a8d3-a23c78bdd2e5 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
c117febe-713a-4a78-9ee8-5730bd8cd8ac | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
eaf92ed2-82d7-4d73-926f-43b6498137f3 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
a696cbf6-2311-4295-bb81-6ca5690ad502 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
eccfd6d8-acf6-4758-a83c-65180e565fb4 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
3519c253-e12f-425c-9bd3-f0f540b08283 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
46fa10f8-a381-4ff6-bf27-65ad50a860fc | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
b08889ee-cab6-4d1f-9820-0cbb0b6c1890 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
4daae178-c498-4952-973e-9e2ca33f41f5 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
0cb11de0-c940-4107-85a0-a362719d60c1 | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
d670ffb7-afd5-4a68-983c-14c8a5e8e42f | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
d118a864-2860-4ba7-ba06-8da6829be47f | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
a1d4f08a-129a-452f-9c9a-9d8b7e8e747c | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
58b1dc1a-2f93-45e5-a588-25d0000094be | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
53e22257-d863-45aa-be5a-4b9ffeb2db7c | Pole | 2 | Distribution | 2022-04-15 | 2023-04-15 | Level 2
63639052-7d8a-4148-ba18-da2636ec976a | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
5149607e-d663-4d92-aeea-0b0e5e11edc0 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
e51699d1-2083-41bf-969d-ab7f570dc789 | Pole | 2 | Distribution | 2022-04-15 | 2027-04-14 | Level 3
37ced4df-2357-4c0d-b9bd-ac2b485fd4df | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
2e3e75b5-cb8e-44b1-8231-10e37d7be6c1 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
6caa2c64-cc49-40f9-9e73-38d20bafa34f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
46d1fafb-47ef-4b24-be4d-2d611d53b42f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
95aadd0c-83fe-45a7-a906-9627397d36a0 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
95ade939-2538-4008-a08a-a823d6d34b66 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
74d9f9d2-5c33-48fc-98f1-f7de4db96d26 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
a7978a0b-a636-40ac-a42b-2b214aee9077 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
543fd334-c0c7-4361-9569-153ef40dce9d | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
5d7d532b-9cac-49b0-85b7-43685b3ce849 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
b8a3c1c3-60dc-49ee-8451-c633fa64a3a4 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
407180b4-8080-4c0f-a1c5-5c48ee428a7f | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
43605e97-3ece-477a-b27e-5858505b3b50 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
38bfc3a2-e04e-48d1-86cc-97d661b1b849 | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
2303c569-23d0-4e2b-b11b-dc1230aac3f1 | Pole | 2 | Distribution | 2022-04-14 | 2023-04-14 | Level 2
1b946904-148b-4bdf-bc48-70d5ea50b3db | Pole | 2 | Distribution | 2022-04-14 | 2027-04-13 | Level 3
69c465b0-603c-49e9-9907-7b1bf9244dbb | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
e3342162-d6f8-46bc-b0ba-219d23c2d252 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
a05159f4-3bdb-4c11-a05d-1e6c4436e9f4 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
04033804-b4c3-4d80-830b-a7a95b8a0527 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
a1423266-f9b5-4b7d-8b63-98d7000c94dd | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
c5fc0e98-f616-40d7-b78e-acd718d8ce1d | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
85c234cd-3fb1-428f-9e56-78e3f210c822 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
6cc8fef2-8517-4e54-a02f-d6c447c29159 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
8c5cb3bc-b7b1-47b7-9657-3e2f254bdcfe | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
9b7fa005-09f1-4e72-8f0e-2bb4c688d2a6 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
0255c325-77ac-4d86-bd16-8bfcf45f9eef | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
91263e8a-96e5-4cef-a764-64a1dc400f17 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
ec7f82f8-4b5e-4598-9456-79c5cdfb747d | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
f435a7b8-06f2-4b6b-9fdf-8eb65f08c292 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
fc2c159a-ae49-4cb9-8688-dfea83f773a7 | Pole | 2 | Distribution | 2022-04-13 | 2027-04-12 | Level 3
15a8510e-5caf-4f94-9c84-c23352144894 | Pole | 2 | Distribution | 2022-04-13 | 2023-04-13 | Level 2
802ae38c-43be-4b1e-80ae-be0a03e89114 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
fcfb005b-5af5-44af-99dc-1f9859caa707 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
969808e2-e63f-4c96-8cad-34e50ca2ecc0 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
4771aac8-e424-4297-a657-bb9d8165da26 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
51d941da-1ea2-4b06-b1cf-ec2c7b918d12 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
344dcb0b-06e1-412a-91e2-0174a804f168 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
089da26f-0a22-4ca1-a226-62a94e2cc3a9 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
c3e0a445-ba3d-4db1-a5b6-2b7f678cdbf5 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
539206c6-785c-4360-a057-97571eb7e5e3 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
9441e91c-7b1d-4fae-8a31-5204036dc095 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
fee81b88-0170-40b1-ac9a-c7c944a7aa14 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
a0e8e8b4-792d-481e-aff5-af88c1ab75b6 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
0f60ef12-9527-408a-a304-d1cd7f4d30b2 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
67c6b4e4-4d9c-456d-9889-c87907659f09 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
0a66d65a-3fa9-421a-a1f7-65d9dac49469 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
497d4a24-b574-49c4-b47b-d04eb2b34f0c | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
926910b6-22b4-4d03-8804-2453d9bf325e | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
c335708a-9c1c-4f52-bf0a-372951cf6e28 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
ccbbf5d6-424a-4913-b12b-3ce684553850 | Pole | 2 | Distribution | 2022-04-12 | 2027-04-11 | Level 3
ccb378ae-b837-4738-8914-9a5503502d4a | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
a6a4386c-e04c-4192-ac0f-464059095588 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
54b8461e-4806-4f58-bfa3-70ed626e1606 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
1544ccbe-fbcc-477a-b0e7-85f33f0a08cb | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
25ff992f-3184-4b34-9463-ea896bb6ce19 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
cc00849c-8eb3-40fd-a6e7-ed38b13486ba | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
fb2d214e-b91d-435f-9f3b-e2b0845207e1 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
ac825b42-2f9f-494f-8b6d-f2c0fbd2529e | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
b4b229c7-0dd0-4a81-ae1b-3a1b4db8ba28 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
5da1ffe8-e13c-4e1b-8d84-4f24e9a59222 | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
7f9f2bf2-b36a-4093-8a23-d04f9dc0d04d | Pole | 2 | Distribution | 2022-04-11 | 2027-04-10 | Level 3
50b30623-87c5-49eb-826b-7fe81ce79572 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
4d2b8ecc-c3f7-41b2-8868-bda740cad8a8 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
752f7f4e-4f9c-4523-9d70-effcd4b9fae5 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
dbde7c58-9f55-429b-8dd8-d36bb2fe4f06 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
1c918c01-a2cc-4e59-8a5d-7d05f9392d6a | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
f3c25928-8609-4651-a68b-3a65dcf43984 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
cb3882a6-06d2-41ea-bad7-9ba7027598e6 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
31144e21-548e-437a-96b7-e0e1a0ca98f3 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
893d438e-38da-4a1c-8277-df8c921f331a | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
a9077e38-0a8a-4f05-bb09-d2e748847190 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
6a56aa29-5d24-4179-ab69-2d8a5118ae4e | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
92ebab34-88d2-4e0e-af9f-1a54dee52310 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
b18ac578-5674-49dd-a472-13aa899aedef | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
ae8a5b56-5f09-49c5-879f-39a52004dce2 | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
5f704f5b-9674-49fc-a084-041814e9145b | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
7458865c-ccb2-4f54-82a2-011af5d3522b | Pole | 2 | Distribution | 2022-04-08 | 2027-04-07 | Level 3
759dd31a-a29e-47a2-acbf-3117e4dd7a3e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
453e5e4a-a4bf-4062-9c16-7154c57a7647 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
7f7458a2-d63f-4f1f-af4b-ead310ce806b | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2
ba31ea8c-07c5-4600-a7e5-0892d7adaa56 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
9dd4116d-078b-42f9-9b94-92ccf7f1ebd0 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
ce61d46f-6e7f-4e8a-96ca-f5e12021aa28 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
93df7ac3-a101-49e7-a9a0-081db111c960 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
ab44f8dc-89e3-4176-850f-793b3f19f46d | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2
110e256e-ed09-42c0-977b-6ab387d4d360 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
989d3a22-55d6-4d04-be3e-072a0db3b5ab | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
41ed7441-2394-478d-8c32-528aa9839a6a | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
06fbe163-02ab-4510-b071-ab68098ccbf1 | Pole | 2 | Distribution | 2022-04-07 | 2023-04-07 | Level 2
f073a40d-ec75-4bb8-bc0c-bd0bbf1fd031 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
f0a38a97-52b0-471b-ac55-f62e15c3613e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
47ab9d43-bf03-4de6-9615-c79cd8e6f57e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
c3a29af3-8df4-4143-8864-b06a10d0f73e | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
bd59abc6-3dd7-4d8f-9199-94f9be846fb5 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
3312cced-0c43-47c9-9268-33658a56b4ba | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
5c4e7dde-77b3-4613-a6e6-7e362b1c0e91 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
7f5d4317-8e59-4210-8d36-86f829a70cf2 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
ec0e8d41-e7c9-428d-9be6-c293c45c8aa2 | Pole | 2 | Distribution | 2022-04-07 | 2027-04-06 | Level 3
0dba6e19-acb0-4b5d-bff5-f55abb94f985 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
b456e1ce-be9f-47fa-b2f9-6637c376e266 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
406e13b0-2310-4f0e-93c3-465097c609c8 | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
04f67fff-4a65-4373-bdf0-ff776df5fe0f | Pole | 2 | Distribution | 2022-04-06 | 2027-04-05 | Level 3
5e98754d-8e65-4817-b4ee-f93d0f3b5073 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
1357eced-8afd-4479-b82c-152944c3f572 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3
a39dd90a-6368-42a5-8bdf-ff9f0348990f | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3
51fcd251-20d2-4d11-8ff0-5e3c30eaad34 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3
ef7fea55-987a-43d3-9f22-203f7c6236a6 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3
fad86c80-6615-4b44-8b56-5f6200dcffc0 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3
9644509f-ddb0-408c-aea3-d01dbd944b83 | Pole | 2 | Transmission | 2022-04-05 | 2023-04-05 | Level 2
c41d3b73-5ace-40ad-8145-f8563c8d2a53 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3
c4998d00-7245-4eeb-bb67-208def1546f7 | Pole | 2 | Transmission | 2022-04-05 | 2027-04-04 | Level 3
17110f8b-c3ee-4ff3-a026-e51494e1cf8c | Pole | 2 | Transmission | 2022-04-05 | 2023-04-05 | Level 2
c8d0333c-1ab8-4836-9766-032e21e4742d | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
4b8543b4-81d4-43a2-b8c9-a9d1ba053787 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
0ca8a859-b5cb-4f82-b0c5-f891d553eb89 | Pole | 2 | Distribution | 2022-04-05 | 2027-04-04 | Level 3
6490187f-9bae-4210-ace4-826a81fc03b8 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
e707e466-721c-4732-9532-a9f6cc279846 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
65aea2c3-65de-49ea-8c7b-da0da71d7c4c | Pole | 2 | Transmission | 2022-04-04 | 2027-04-03 | Level 3
6ddc633d-747c-438e-9737-1ba3a0a6dc06 | Pole | 2 | Transmission | 2022-04-04 | 2027-04-03 | Level 3
d34f4cf2-e8c8-456a-8526-104005306e15 | Pole | 2 | Transmission | 2022-04-04 | 2023-04-04 | Level 2
c51b68ce-3e6a-43db-9fe1-9ef47b103ca9 | Pole | 2 | Transmission | 2022-04-04 | 2023-04-04 | Level 2
588474a6-25a5-4a6b-b3e4-08a6f6898b19 | Pole | 2 | Transmission | 2022-04-04 | 2023-04-04 | Level 2
42416bc3-b0fb-42c1-9961-e231d17186db | Pole | 2 | Transmission | 2022-04-04 | 2027-04-03 | Level 3
891c7007-934c-4802-926b-c92f036b54f8 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
a514a183-210e-4d3d-9669-be29f8443e5a | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
3e4167d9-5472-4774-854a-6b53e05d62a5 | Pole | 2 | Distribution | 2022-04-04 | 2023-04-04 | Level 2
536882ae-ee2d-4682-a30f-02f7efdd9622 | Pole | 2 | Distribution | 2022-04-04 | 2027-04-03 | Level 3
6753f49f-78be-43e9-b0e1-7ad99d995a72 | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
771a1a54-c679-4232-8d62-bfebeeeba78c | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
66a36bd6-ddf1-4343-8ded-318b84afcc04 | Pole | 2 | Transmission | 2022-04-01 | 2023-04-01 | Level 2
11951544-ac09-410e-9b67-787b49f3dfd5 | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
b749afa2-f60d-4b16-a6ab-c8c92391fb2b | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
9d54261b-583d-4de6-9a34-5a3bc96ee7c8 | Pole | 2 | Transmission | 2022-04-01 | 2023-04-01 | Level 2
c1d3a587-eb86-4aff-8eee-3859a1a8b293 | Pole | 2 | Transmission | 2022-04-01 | 2023-04-01 | Level 2
9ddd52ad-27a2-4940-b3bc-9183c21d6be5 | Pole | 2 | Transmission | 2022-04-01 | 2023-04-01 | Level 2
60b388e9-9190-4be4-844d-0f31aed95a7e | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
70490651-8848-40de-b6b8-6db69485859e | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
88a46452-182b-40e8-a311-561508acf7cc | Pole | 2 | Transmission | 2022-04-01 | 2027-03-31 | Level 3
3490a2ae-cf9d-443c-a876-3945b1a2ddd8 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
ce7d0427-8658-41c9-9497-c0adce5ac409 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
9517ff8b-70eb-4a79-9c2c-13f5d37f6027 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
d0ca56b8-d416-4434-ae5c-41f9b51005c2 | Pole | 2 | Distribution | 2022-04-01 | 2023-04-01 | Level 2
aeb3f051-68ce-4d17-b99c-3a30c040d614 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
b419a52d-bd16-45fa-92d9-24da7540126b | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
77a734b1-f825-4a0d-bfde-f8fef4f64205 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
57298da4-085e-4a72-9192-b84b02d621eb | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
3fbedee7-5a99-4aee-9a4e-471dc904f736 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
e8803a8d-62e6-4fea-8538-962bde8504f9 | Pole | 2 | Distribution | 2022-04-01 | 2027-03-31 | Level 3
011ec3be-637c-4c53-8455-19bd724131e2 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
db67ef23-5606-4962-88af-aa13d23541ee | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
54ccdac7-65e7-46aa-8772-7ac31e642101 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
3427a04e-af38-44c7-9dc0-03f25aea0c47 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
0d818849-b462-47b1-b64b-09034da53661 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
a6325903-5690-4566-a643-a95167b5973d | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
88780bf0-6e73-41fe-9dff-845115867a46 | Pole | 2 | Distribution | 2022-03-31 | 2027-03-30 | Level 3
7ce90122-c092-4e49-bccb-85440ed0b30d | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
c8bdab78-0c5b-4209-871e-e9ea2e4e3118 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
ca4720c8-5ed2-4db6-a280-b55370cf589a | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
78e82791-ec49-4494-9f03-0e875b4e68b1 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
94b9925d-0c4c-4917-8b7a-3b98ee27b73d | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
fc83b659-098c-4bb4-81a2-adb559ab8f89 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
6d1b0110-1392-456a-94f9-dcf6ff4171bf | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
4fab5f0d-3051-44dc-85a5-b019491ad3cc | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
c4d29819-fed4-45ff-b7a7-ca68887233e9 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
f3007a7b-d884-4d87-9f70-33666733bf30 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
8b443ca0-7851-4a81-8ab8-8d63a71b476a | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
449a3fd9-6a15-4edb-adef-37eecac70186 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
3bb02784-7dc2-4e8c-a3c6-e36fd5d31219 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
b1aa0da5-f4a9-437c-90d0-ca0a246abe10 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
a9bfb66b-f162-4b34-98b5-7dda4204c231 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
fb204016-655a-44a1-9307-fb449a10c57e | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
4c41728c-b3e3-48a1-9d54-839cac4e7513 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
cd68c314-02ea-47f3-a18d-6f8eebcd2459 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
0433e635-6459-45c2-a96f-dcb378c21e73 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
2526366c-7d72-463d-b87a-572826383f6c | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
f18805e4-d2db-40f3-8e7f-36fa9d0231fd | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
80ae8e82-c16f-4a96-9269-1ae027ba6cb8 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
31a70705-7cad-4c98-ad1b-346a1a5fa69c | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
8d4f6243-4f8c-42be-a198-dcbd678ae2c5 | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
8d54dcdf-1a6c-49db-afda-98e99130de1d | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
6c6ce9cf-af7a-4b5e-9a32-872c136f8d6e | Pole | 2 | Transmission | 2022-03-31 | 2023-03-31 | Level 2
53c60202-2fc4-4d0f-8eb0-64fad0838449 | Pole | 2 | Transmission | 2022-03-31 | 2027-03-30 | Level 3
467f7c03-befd-4a18-ba8f-0168f99f851d | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3
09f1c01d-3812-4691-a333-c4f67703de98 | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3
80b7baf0-df49-479c-b1be-683135d89104 | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3
84b52372-589a-4d67-b45d-6df73a7fe2dd | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3
40129d3b-7c9a-4e64-8341-5b5bac0bfe11 | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3
371f7c92-04ec-4d25-9929-44772f4a543d | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3
2a75247d-d462-4a28-92d0-6ee95d5eab4f | Pole | 2 | Transmission | 2022-03-30 | 2027-03-29 | Level 3
77da13f2-e51e-4343-84a8-8a2bbd21f480 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
f3b5b8b5-252a-4bfc-9474-f51b9a84c246 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
c54573f5-0856-4cf8-88f2-d2c71b3747b9 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
158ff743-f443-4039-8f3b-147887272a04 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
a285c7f0-7141-4cab-b006-5ce892882fef | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
3ebe0cbb-27eb-41e0-b609-e6202b6571b0 | Pole | 2 | Distribution | 2022-03-30 | 2027-03-29 | Level 3
3680f66d-8301-4e4c-8077-ed8fe78e3c7d | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
4cf2f11f-0be7-4345-811d-b4c6af47fae1 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
054d5142-3c61-417b-93ed-a94b7bdfd801 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
db47ef52-d8ab-4a74-8543-6e9adc9515b8 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
b9cd256a-feb4-4d90-826d-9822a74540a3 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
f09b139c-1fd8-44b1-b6f8-f3886641beaf | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
dae60379-6f06-412c-b840-9ea6044082c9 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
69ee62c8-ae3c-4c3f-9e09-4154c499eb66 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
a4eca477-882c-4782-8ea4-8de3006f2571 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
f8100800-b33b-45ea-932e-630f87eb3779 | Pole | 2 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
3e4d9860-54bc-4284-b86d-482d1087a4cf | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
b697c0d1-222d-449d-a7bc-49617e4acdc7 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
91361795-60df-4b1a-9321-0cfc53bf378c | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
0dbf0317-a7a8-4698-a4ca-3971775080b0 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
bed53dd8-e7b2-4f94-a8fc-2fd562ab41b2 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
41241f71-55e4-488a-b5a8-6343683eef57 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
99d7243f-5c8e-4660-a75e-fac5c6b459bd | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
56dcb4a9-f149-4118-94a7-fb0ae769b8bb | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
82ee6174-3cb0-4c52-afa9-ebd956c2e838 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
2ef54a15-4c10-49e5-b567-5e59d0700826 | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
f60e8afb-b15b-42ea-bbd2-a02f3193f59b | Pole | 3 | Distribution | 2022-03-29 | 2022-09-25 | Level 2
843ea2ba-a32b-45e7-b2d4-f9055a18cb86 | Pole | 3 | Distribution | 2022-03-29 | 2027-03-28 | Level 3
a9e1c32c-16e2-4bf6-870f-594a27c27380 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
576433c1-00d5-4142-ab60-574f73f8b481 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
088d6e8b-8dfc-4af1-8424-a7b20328ee6b | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
f1eab8ff-b0b7-42cd-a2df-61ca5e145a62 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
eb64b061-18b7-4d35-8d61-aa1c863c4a85 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
30ebaf39-0ece-440a-9dda-b9718906fa0c | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
2f7fe449-2991-4db1-9ed4-233caefc8f61 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
3eba6a40-cc51-4e45-9881-f709b53de4cb | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
7113c053-0d5e-4b37-ac1a-e0d5289233dd | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
ee0688f6-7625-4b66-8f99-be251eb47300 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
f9d49df4-00fb-497f-bfbf-417c02838a38 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
4c7c8abc-f686-40b3-bd47-59270d8226ca | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
f1796a26-08d3-4992-8b1d-64e4efe52a50 | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
1a93eb3f-f827-489c-a224-2a114bfcc464 | Pole | 2 | Transmission | 2022-03-28 | 2023-03-28 | Level 2
b2efeb4d-1763-4ae4-b9dc-f8deff9b794a | Pole | 2 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
be47bb45-9307-4fe5-a58d-b5404dcd5477 | Pole | 3 | Distribution | 2022-03-28 | 2022-09-24 | Level 2
4e889c56-a03f-4a27-b96d-b61e7750e2e0 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
5a74840a-f070-47be-b881-55be4791cae5 | Pole | 3 | Distribution | 2022-03-28 | 2022-09-24 | Level 2
7e9a6086-1a1e-4600-b621-64b022f371b6 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
ad30b0b4-deb0-4522-8234-f90c5af20818 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
9caefccc-45ee-4908-b9b4-6bb22162fda4 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
0a09f7b4-a52b-4f94-ad95-54c10d0e50f1 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
8ee6f7c2-e248-4b75-813a-f29ff833a560 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
33765a7c-2407-42da-af75-23c078fcc578 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
200ff739-41c9-4c5c-b5a6-d450709308b9 | Pole | 3 | Distribution | 2022-03-28 | 2027-03-27 | Level 3
6699147a-6673-431d-830b-225a8877bb19 | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3
b4884129-3fd9-4d6f-b444-1c305127ca1f | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3
69aaa11c-e5c6-419c-9c55-729a62cd0f23 | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3
11243b97-53ab-4744-a034-24451762a977 | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3
513fd5a0-de8c-41da-9d72-1424d6b94193 | Pole | 2 | Transmission | 2022-03-25 | 2027-03-24 | Level 3
bc74636c-5151-4683-b755-1a6d7a31847b | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
6aadc235-7fa4-4d37-aa2e-1fb1c9f33c10 | Pole | 2 | Distribution | 2022-03-25 | 2027-03-24 | Level 3
635f9fa8-3766-4c4c-9dbb-8ccf5eb329b5 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
0a7892d0-e1cc-49fb-88f8-147c3111999c | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
38b8cda4-4c09-4873-abd9-113c145665bb | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
53373121-98de-448e-8c85-35b9576a6869 | Pole | 2 | Distribution | 2022-03-24 | 2027-03-23 | Level 3
a2fb0a9c-6906-4fb9-900a-4fac4be7bb0a | Pole | 2 | Transmission | 2022-03-24 | 2027-03-23 | Level 3
02f1711d-c3ca-4a27-9542-6712e192c178 | Pole | 2 | Transmission | 2022-03-24 | 2027-03-23 | Level 3
16c7a8ca-d294-4077-8444-0473df29aca3 | Pole | 2 | Transmission | 2022-03-24 | 2027-03-23 | Level 3
56166386-a26e-44c9-a6eb-d4262ef2a8d7 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
67b5eb10-2680-4429-9b60-994e45a85302 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
5ca58bf3-0258-484b-bdc3-30ad06f4fdb7 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
7e043f09-b91b-4d40-8029-d46cb83e6b84 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
6dd3bb92-e7e5-4228-93a7-002478038549 | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
447ed10d-58ee-48d8-89a5-867fb454245c | Pole | 2 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
7b5dee18-6d15-4e99-a3ae-8dfdabc965c4 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
c1baf5f6-97fa-4434-977c-b1e1136be72b | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
4acbd570-1d2d-4ffc-8438-a62d218c4ac4 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
dddb4116-46de-4952-a2c4-738668f1ea8a | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
8e20a9d7-45fe-468e-9f69-e23d7ce2e508 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
f89b896e-07a6-488f-96a5-543230fac341 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
a6bfd5ee-865a-4814-9e0e-1df0e7600bf9 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
23774c31-0797-47d4-b0e9-8bdd8bd27e94 | Pole | 3 | Distribution | 2022-03-23 | 2027-03-22 | Level 3
560db93d-3c89-4f60-a167-677f58802def | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
3ff87b0b-e34b-457f-be4a-8695265fc19c | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
140aa5fb-4683-4775-a87d-35ca405d2236 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
1aac4d42-464b-4da0-b231-20b6f6a06b97 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
ea9b8a76-f067-45f2-b25c-685d63c98253 | Pole | 3 | Distribution | 2022-03-23 | 2022-09-19 | Level 2
30a5ebd3-baba-41ee-926c-6ac341664752 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
373bf0b7-ba44-4850-b54c-41ea75be2660 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
af4e0761-fae5-457c-b4f1-9ec961b0f9ad | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
828b8419-e97d-445f-a054-db36bc5cfdbe | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
6b4ae72c-2ea7-4e35-8810-0ffaf2bb1ea1 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
e3db88c7-f89c-4738-8cdb-81fe55a72999 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
1763ee4b-8321-454e-8bfc-b13cc1e079b6 | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
9f148b51-c9aa-4630-bb30-0c5c88046c5e | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
48dd83f8-80a8-4950-aeee-27004f83fddb | Pole | 2 | Distribution | 2022-03-22 | 2027-03-21 | Level 3
9743601d-a563-49a9-b989-53394adbcef1 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
811602ef-6022-41d4-99e1-d86307e3e657 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
e56b0a19-d77c-434c-90c1-636d57a1142c | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
42e3d468-2f5f-40f2-951f-286f35f35b1c | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
81a9eefa-5d2e-4fc6-b919-d84d93a2f74c | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
cba3d22f-5dcf-41c5-a4b8-2e838459ff38 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
bc49c0ff-57c7-471f-92da-29a03735adc2 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
d5ea176f-2f85-43dd-850b-9a70d0726a03 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
5600602a-e0b6-402b-9576-b8c528e3a1fb | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
ca843b56-99c9-4151-9145-7bd4b7645870 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
68d65041-18be-47ff-a2d8-0f37eb7854f0 | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
5360e95d-af7a-49ef-8025-dfea3146d5ce | Pole | 2 | Distribution | 2022-03-21 | 2023-03-21 | Level 2
a4681f11-8df9-4cab-9864-b15c560da8b8 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
3b57e49f-aed7-4e4a-88e2-06675e5e4418 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
9932d08c-9950-4b33-a9ee-87efe222a449 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
c4f945aa-aab0-4a0f-bc6f-4f279b5f19a3 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
38ca824a-2abc-4ad6-975f-4110e77e4fd9 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
84ef54bc-3380-4333-a157-497a39da266e | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
79096de5-208d-4f60-a25b-925873503991 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
af7de0d1-50fd-4fcd-a12a-e7c4a4a54ad7 | Pole | 2 | Distribution | 2022-03-21 | 2027-03-20 | Level 3
2956fbb8-2b4d-4f3d-8950-2386873a3c59 | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
ba8d0a27-5b02-48eb-9c07-b4b7aec6d00e | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
95e725ab-d539-4898-959c-e9efb0a6c79b | Pole | 0 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
5ea6f806-94d2-45f8-afee-bfc21a9cbf00 | Pole | 0 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
42b8af2d-2292-4e20-84f6-bd12843b48a1 | Pole | 2 | Distribution | 2022-03-18 | 2027-03-17 | Level 3
1c6a1ff4-0a94-49aa-8583-8f3abe9d7f26 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
482bc288-e8b7-4f39-88be-0a7740247e14 | Pole | 2 | Distribution | 2022-03-15 | 2027-03-14 | Level 3
974c6e73-1861-4b99-90e5-856952a7e3bd | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
058b3238-f344-4a1c-bcec-4b27eb6f203c | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
7c24e023-b231-4b8f-91c5-0ec59d66f256 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
0478cc94-0f0e-48fb-9852-d500dc8bcf42 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
5c3a802c-4785-4db0-94c5-f154d611ed32 | Pole | 2 | Distribution | 2022-03-15 | 2027-03-14 | Level 3
8d79dd12-3bf3-4cf4-ba22-431cffa0d543 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
2ef72a3e-2478-4340-bbcc-a488360d832c | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
6aeebeca-82a7-4a2d-b9bb-6abc2d989058 | Pole | 2 | Distribution | 2022-03-15 | 2023-03-15 | Level 2
e59ccf2e-acb0-4adf-a134-86a8d15c4b63 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
d45e9353-79be-4969-9c66-566d481027a5 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
ecffc587-cbd4-4a44-b6bd-d80c02e982a7 | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
f5b65d56-f626-44d4-8be2-369d271c7370 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
ff1e9233-01b3-495b-a602-4c463825dc1c | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
bb7567a0-885b-4452-86d5-374a14e2e18e | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
94ace622-8c1a-4609-8a33-472cd42734ce | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
17d3c5ae-1a61-499b-85db-e0afebfb141a | Pole | 2 | Distribution | 2022-03-14 | 2023-03-14 | Level 2
4603d0bb-e271-4150-ac04-2241b42f860f | Pole | 0 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
5a6ed601-50b4-406f-923c-17ec889eb8d1 | Pole | 0 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
e0259b07-0c21-497c-b08a-7ed5e2506f97 | Pole | 2 | Distribution | 2022-03-14 | 2027-03-13 | Level 3
5bd81093-f232-47fd-af7e-68e5c0bf90d3 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
5960d81e-af50-48d2-809b-ae69fa14be13 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
4ffc6e7e-0a2e-467f-9c1d-9cf72424c2b4 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
eee6c825-8770-4f13-9298-273ba7da5e09 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
033d17e9-55ab-4c53-818a-49b90ddc6cd6 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
b5c03242-7eaa-49c0-ae4e-6d9717f62e71 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
f13d4655-f3b0-47bb-82d5-09c840a3b9a3 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
279d1e14-2627-43da-8c7e-af99443f339f | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
3715d1fb-91fd-423d-afab-7c8bcae80623 | Pole | 0 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
c22e7131-2579-48a3-ab97-aeb489c57316 | Pole | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
141c7577-c329-4591-a877-0a7d83bbdeca | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
bb356c05-3af4-4b7b-bf4d-0d0ac2b45127 | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2023-03-11 | Level 2
eb530aad-7b18-4fac-b711-865eb071c1b3 | Padmount Transformer | 2 | Distribution | 2022-03-11 | 2027-03-10 | Level 3
1d33503c-9bc0-47e7-be14-b1b53691a757 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
7d05c622-4a5e-4882-a671-a9fd262946b0 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
1a7643da-9618-40e6-946a-8c2c2d56714b | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
d113c1ba-623b-49e3-94e8-7bb9c3f45b3f | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
2372015e-64c0-44b8-82b4-73056cdde97f | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
a9b2b03a-df52-4c65-9dfb-9318ccfb7f88 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
c20c1f1f-7462-4211-b5fe-e4148c16ef12 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
676714d5-68aa-4c9c-976e-ef813cfdd699 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
a7b864e5-96ad-4fcb-8fe0-2a97a37e631c | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
70ddc3ca-18fc-4e3d-bd71-0c7c693f97e4 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
e7def9e7-d7af-4c6e-ad1d-d26eb717d698 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
025c4b62-5b4b-41ee-9419-e27acc7063a6 | Pole | 2 | Distribution | 2022-03-10 | 2027-03-09 | Level 3
16798d74-022e-4437-b25f-649b59081b37 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
44633787-88e7-4af9-8ec1-e9972e059db8 | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
c6234b52-1401-4d86-a5bf-0b4e08381ece | Pole | 2 | Distribution | 2022-03-10 | 2023-03-10 | Level 2
1df7f79b-a981-42fb-9ac5-455e1dd4b0b0 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
af0375a9-c7d2-4a90-8acc-34d85a7f13a4 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
b4476d03-25d1-4434-8c0c-a7902095b7d2 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
23537b86-62b8-4250-b35d-034eaa1c1141 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
e3246536-3dcf-44ef-86b3-5c19328aaaac | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
605e7139-bc15-4384-80a0-e9de124b5015 | Pole | 2 | Distribution | 2022-03-09 | 2027-03-08 | Level 3
52b3bb82-a148-4fe7-9809-3d3e3af5559a | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
846e663b-edf0-44f5-a7c8-537674ae3985 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
a9167ffc-b364-4904-a8f5-90858cd97fe3 | Pole | 2 | Distribution | 2022-03-08 | 2023-03-08 | Level 2
061c8eba-3bb4-4ae2-b7f1-8549334a02f6 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
68836db5-75d8-4aad-a2be-cdcb197bb3e2 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
b11d56e4-ee07-4482-bac6-a5e36516ec30 | Pole | 2 | Distribution | 2022-03-08 | 2023-03-08 | Level 2
ed0f6aea-7165-4fff-88d8-f9867587887d | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
f835e242-4b66-4e7c-aca2-3697a3f0e3a4 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
3f0c9acf-3bdb-4b70-b93b-c4aa35120ab6 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
f789fc99-b2a4-4bb9-bac7-c403caed68ae | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
e6c1721f-beb8-44ec-b219-19a1059a8b6d | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
2f2523e0-7813-45e4-8a58-ef81b4ccec88 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
8c01093e-fe1e-4abd-af6a-3558a3e369c8 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
96fda099-61e5-4a65-854a-88b07f5157d5 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
17c4164c-08cf-44c6-8260-4c22c1d562a8 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
a97070f0-5eb5-4298-9b6c-ebac96bd5688 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
c35d1544-aa74-4417-8cdc-e81f255d8238 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
464b835f-a798-4131-8016-4c214f0e213c | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
c7fca155-0652-4ee4-aafd-7503a09ce007 | Pole | 2 | Distribution | 2022-03-08 | 2027-03-07 | Level 3
5e0722d8-69a2-407c-a314-57a8661cffea | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
f0e1f223-0124-4ccf-bb14-f3bb9f41e348 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
6e286861-2fe2-450a-8b00-e5f6fe613bf6 | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3
0e8625a3-c494-412e-836c-1be5916e8639 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
2372f5c2-cc0a-49e6-ab1c-2dd7fcfc068f | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
9de101a5-29f0-4ef5-8b1d-7282e3de919a | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3
26765015-9d89-4141-800e-c39046580bad | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3
dba0de0b-e910-4ad9-b9e6-2f78914fc9ae | Pole | 2 | Transmission | 2022-03-07 | 2023-03-07 | Level 2
c00c60ce-8573-4a4d-ba19-025391d89fbe | Pole | 2 | Transmission | 2022-03-07 | 2027-03-06 | Level 3
61ca8aa9-9f93-4772-b94a-3ed5add449ce | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
8eddc616-56e7-495f-bb7d-c5fe14e9b934 | Pole | 2 | Distribution | 2022-03-07 | 2027-03-06 | Level 3
e0b22470-e823-4b0a-94e5-b34563b87d3a | Pole | 2 | Transmission | 2022-03-06 | 2023-03-06 | Level 2
fac6a3a0-75c0-4c0e-ad42-252501c6f847 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
99fc7cda-66cb-4d16-9062-7493c69c22ed | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
9e2e4c11-0309-44e4-895a-2def76648e70 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
47dd40eb-38a8-4772-aa88-a283ddcf0597 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
4b093598-5e42-4a39-9233-e1fa149ee236 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
7ed130d7-1186-4547-9330-9eaeda9697ad | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
194af122-7ba8-452d-92b4-2e945ff7b1bb | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
131a2118-e6cd-4620-b5f6-97f79bd425d6 | Pole | 2 | Transmission | 2022-03-06 | 2027-03-05 | Level 3
ec42faca-dcdb-498a-8bf6-a60434c3b19a | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
96708bff-8bc3-4550-a2fb-20e3b30d5e52 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
35b4d4d0-2fc3-436e-96ad-81964433385a | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
025e007c-06ce-4b46-bbc8-5cabb0bd4861 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
d500bc58-e23c-45c1-accd-4d30e52bc300 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
5c8cd669-43da-4290-bf9e-f9ac7d21bee8 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
c182d3be-fafd-4868-9269-acef9b47712b | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
bf515492-9cd1-4193-90d2-9bf157917115 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
890ce002-3f41-4eb1-b37d-b6be1048d91b | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
353766f1-44e7-4178-94c1-8ac40f110f3c | Pole | 2 | Distribution | 2022-03-04 | 2023-03-04 | Level 2
45db216a-e14e-45c7-a114-8075f729ddad | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
6d4e04e6-91fd-44ad-922e-62012c0d31a8 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
24d2edde-aeb0-4236-bc19-ba4362ad2f40 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
7e19f252-101e-4b08-b6e8-824cb7ed7eb6 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
819a3168-cac9-4bcd-a941-a3954609b813 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
2e409d41-287c-43f3-ac53-499d40a97fef | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
0f662efc-3ac0-4aa7-8a02-0ccfc133df98 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
c06e8002-8e70-4553-8c1b-822d3e181b18 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
43a65242-1c7c-4286-9d19-7d97648a390f | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
7e3b28cd-1d10-47c2-84e4-8c62190a6099 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
eff1c26a-66c2-4481-9297-519c502653d5 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
928bbc33-bdbe-438e-99a4-bea302d0435d | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
9117be77-b5a9-4744-ac55-c52b5de5f09e | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
2024979d-c021-487a-a2fa-a2e6d07a09c6 | Pole | 2 | Distribution | 2022-03-04 | 2027-03-03 | Level 3
2ded8066-d4b4-40f2-bd54-ddb7872365cd | Pole | 2 | Distribution | 2022-03-04 | 2023-03-04 | Level 2
33f59594-0c27-45ee-b5ab-3493515073f6 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
06206f9d-eda9-4c5c-96ed-3f59c4327e0d | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
9d132614-0aa3-494d-aac5-3e3d460483ed | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
dbd1372c-c638-40b0-a3db-cd5693d7c804 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
620954ff-355a-49c5-ab33-e6a060c052cd | Pole | 2 | Transmission | 2022-03-03 | 2027-03-02 | Level 3
7c1d2fd2-d98e-46eb-81a6-748860f7b50d | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
b413799e-05fd-45c5-802e-338b566158e2 | Pole | 2 | Transmission | 2022-03-03 | 2027-03-02 | Level 3
aba0429d-c04c-49af-99a8-cea2d2e7aff6 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
4ac35a51-82d1-4533-9529-2c6634d7ceb8 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
1da73f04-c984-40a2-b8e6-9f9366d0df20 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
758290f2-01dd-4589-b57a-e87f0f5f5633 | Pole | 2 | Distribution | 2022-03-03 | 2027-03-02 | Level 3
3df0bec5-a624-49bb-bd69-1c3c07bc2706 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
dfcf8a9d-eb91-4253-8590-a160c4caadd0 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
fa6c7baa-32de-4b98-ab22-a0e03ab650da | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
75ecbeb3-bf64-4fa9-ae16-d7357816e3e0 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
d1b72a86-f7be-4903-9054-deb205701c4f | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
2faa0286-4d2d-4802-a602-1c0e8b995b19 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
3659639d-9882-44da-bdbf-68aa293c1ee7 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
724d5e19-ee2c-46e8-b91e-82c5961309eb | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
3ef96de5-6e55-455d-9012-0c5a3bc12f1c | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
f88c8f7c-92a9-43f3-bb9f-b123e322da59 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
122a807f-c7ec-4aed-928e-6b3d4f503e18 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
14b43334-4892-43f3-a1a6-aa38552380b5 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
1c2f1ab1-2d58-4c48-bb42-ecbfefa48e04 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
118db6f3-3972-4377-b6ff-70f0658a1503 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
b8834e72-d29b-4778-b42f-e2b80f7f191a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
c7863bf5-26e3-4ffb-8f1b-71b33ed22fc6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
8d118ee1-dd6c-495d-b2cd-52df3a96953a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
e7f4af8e-02c8-44ad-a67e-14d3f4c94fbe | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
18e5b3be-284d-4902-a1ee-d6bb5ce2f183 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
0748d31d-9a0e-4785-9110-e2548baf68bf | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
2f111a29-6b32-457a-9820-681f39c0f7d4 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
6c215b98-b1b7-497e-8a66-3970d8a5494a | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
43ffd650-ff5c-466c-b1d9-bd4eae98c628 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
89657559-0bcb-4d5f-b8e3-84122ca68424 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
27c9ae21-8533-4ae8-9740-3318625968de | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
b6260d5a-1901-4166-a6c1-b260bbeb57b6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
bac01e77-1f47-4cf2-8f25-54a526864b6e | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
fcc1597a-45de-4181-b63d-34996c6ce1ff | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
fd775da9-8175-45c0-8c64-c18753d96dbf | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
474acbbf-1f6b-40c5-ab4b-c83d0bf93411 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
72bb551f-6b47-4005-adea-85a9e259208e | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
8146167e-d080-4c28-8fe0-198b6e8a9165 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
7adc2332-94ef-496d-a96a-f6ec2947f265 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
7d018483-bba2-4200-9adc-8c381cc929e3 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
51708ac0-d11e-4bd3-8f62-d39b0431acc9 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
b2336ecc-a1d2-43f8-b9b6-427b9730dd83 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
680f696a-d323-4268-9363-35638b749d85 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
468e7a72-aac9-4875-b6c6-7ca17a809add | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
b772229f-97fe-48d9-b003-e5f11e0eb8dd | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
cba75e47-6f96-4558-9d85-e6d55a79ff4a | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
af8dfd74-8f2c-4b62-9813-3fcb014ba1e9 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
a36c39a2-d592-40bf-bb22-32899f3d83ba | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
19f71cb1-dbcd-4170-8ae6-25e7ed818a99 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
000345bd-beab-4323-b047-7f58ba23bfbe | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
8a979b76-6ec7-41fc-8585-4eefc8cf724d | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
5e33c42e-4c59-401e-9915-88db56c0ed59 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
33061a2a-6d36-4520-96b4-52f28f78dce1 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
0e86a72c-b6bf-4b5b-8af1-ae60b9358040 | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
70944a0d-756d-494f-b125-25dabe12863d | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
8bb2c126-9068-4690-ab94-4f64edd7f3ec | Pole | 2 | Distribution | 2022-03-02 | 2027-03-01 | Level 3
fff10f7c-ed25-49bc-96de-64b2a069d9d6 | Pole | 2 | Transmission | 2022-03-02 | 2027-03-01 | Level 3
54c80c86-bda6-4faa-b364-0de74817354f | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
9eb1cdb7-024f-4897-ba8d-65150cefb10c | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
86d91ef0-bb98-44e9-941b-17e6c4447ff3 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
859fd0c2-8fa4-4bf2-9659-587b4e5732ba | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
0ae7b352-2068-4074-8fab-d548e5c6c68b | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
3bbcdad2-e1dc-4fef-810a-019ee6ab95b1 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
d73636b1-e8b1-4abb-ba62-27cbdf69c45b | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
1dcabb81-1f56-4fea-bca5-f7f19f9bf01f | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
7ca3e4fb-fb83-489d-98aa-772562220747 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
72c4c84c-87b0-455e-851d-825e40159edb | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
2ceee83f-745a-4463-ab2d-78d3abdec0a1 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
62bce5c0-f588-45f9-8106-4ba0db955ef6 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
9c4203c1-b39b-4541-b373-fa82aaacf2bd | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
68b18736-b7b4-4bca-8d46-59248f476a1c | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
dc5d2b55-535a-4145-9186-3c2a0aa11515 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
2c55fe27-4cd1-4e2a-ae51-18a99ba78830 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
964f3cce-fe69-45c0-8bf0-5f65bfa42529 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
d68284bd-a701-4957-a1b3-f3cb139f7a64 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
950a67c5-1730-4be5-b8f7-2437a7ad8fb3 | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
0d16fe95-8650-4231-a428-68409e9a8f3a | Pole | 2 | Distribution | 2022-03-01 | 2027-02-28 | Level 3
4aa52295-2248-4da6-b326-9dd4b4f35a9b | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
122eb7be-1c77-4245-a809-e09c54b2adfa | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2
1aca49f4-c0cc-4aef-a70e-09b25742eab9 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
fe559a22-c1bd-4951-804f-41f2a2e465dd | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
727405c8-18bb-47d6-b2d6-6f98a423c685 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
2fa0521b-e61b-416a-8f2f-3c0c17fe21fc | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
e0db64da-2c9d-4cdc-b766-f48469b85041 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
1e45b898-c7f2-435e-8349-fc7809bc9f55 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
cb9757c8-d8a8-4991-8515-a062a28b9290 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
abc16615-7808-45bd-8c70-2b5542d2bcc1 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
a40c9abe-5c76-4fd4-a070-8f009638f197 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
d117c99e-354c-49ac-b4d8-105333acd364 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
2b9f9207-d3aa-442d-b07f-39d280f770b2 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
fc784963-eeb2-4201-822b-6048a528620f | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
ea17fc89-d740-4a5a-8096-ede5873481dc | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
4a28b787-6012-416f-8b40-7721bc6fcedf | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
25f2e63b-c85c-4234-9ffc-04de760a6776 | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2
24618b52-1670-4e55-a09c-e2d1fb43c8cd | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
0986680f-8214-4c22-94b3-8c32954200cb | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
6d074cf4-a17a-4fe5-bfe0-6de6cb56cce8 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
f31d21e5-944e-48ac-bcee-c29074c92159 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
16d48e85-5980-4fb0-80e5-af92cd8c0c12 | Pole | 2 | Distribution | 2022-02-28 | 2023-02-28 | Level 2
e55eebf1-bf37-4a9a-bd12-b1932e810128 | Pole | 2 | Distribution | 2022-02-28 | 2027-02-27 | Level 3
9231d6f7-6fa9-45e8-aec7-b40fecdc7368 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
83f5d058-7808-425a-b206-12cfdbffbee9 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
cbee412b-ea08-4e2e-8dd3-d840df3f1c60 | Pole | 0 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
42f85533-e863-4a93-87e7-99415f5e27e5 | Pole | 0 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
a265bb57-349a-40eb-9932-c92587748cde | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
766c83e0-a3aa-4e77-b637-e8ecaf1b61ed | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
35e5c18b-0dec-4bfc-bf48-1f60948ebfaa | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
c455f87c-68f4-4a74-8c62-9f34c883b9ab | Pole | 0 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
0b6fa2a9-15c2-4fb5-a732-95b67d772a09 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
a6107ee3-4637-4ff1-89f5-6e474a425c0a | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
62489f1b-d54a-41e2-a264-b7bafe0d0157 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
abecd5f2-eb6e-415a-9c75-aba7decef107 | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
528d45cb-0f42-4079-b4b8-49fa9b7b5315 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
b44346f8-e0ac-49ec-b4b8-4b41fbd05c58 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
4de6ce0f-cb74-44fa-be5c-062afe46e7be | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
e13607fb-4ea9-4e5a-914b-bb659cba38c7 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
6c09af98-be98-4462-881f-f1d78def1e5c | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
0d772885-a904-4855-a0e0-707a9fa963aa | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
fd91963e-a2cc-43a3-a68b-18168ae3086a | Pole | 2 | Distribution | 2022-02-26 | 2023-02-26 | Level 2
16402208-3df6-430e-8b4e-ee80422b2254 | Pole | 2 | Distribution | 2022-02-26 | 2027-02-25 | Level 3
2b6404e0-300e-4568-b19d-daeb5f1312ff | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
fac502ae-f6d8-4080-92ee-301b5930cafb | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
19e6c6d5-3a10-431c-bd3b-6269206237cd | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
007adb36-353c-4d60-9351-f01847004a89 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
fcde8853-3f14-4a30-91b9-6e7d7e542ef6 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
193082a7-e68b-4ce4-8a3b-9b364ebc950c | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
d3b213f5-43c0-4075-84c3-bd43f7297c41 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
356e602a-f24f-4c41-b98a-1b0be6e758a3 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
9e1f1fbd-075e-437b-96ed-f2611da9d845 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
ab3c6590-a4df-42c2-8121-9cf7647b2562 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
81eaa342-3487-479a-ba94-4d620a038329 | Pole | 2 | Distribution | 2022-02-25 | 2023-02-25 | Level 2
e3aff06e-22a7-4b19-9110-190114a77c6d | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
2bf7b5bb-b699-4a78-a386-b22cc4a00aa8 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
1e4290a2-bf89-4ca7-b567-b0f90682ac45 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
e7b213d0-3779-4907-b2d9-3f148b7206f4 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
87acbce1-183e-469f-89bb-f3aafed8179e | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
809af1d9-399a-47c9-8fb6-8efba13a0af5 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
7c10a9ac-4ea9-498f-b730-4b1065e51329 | Pole | 2 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
aaecfa6c-cfa5-43f6-8b5c-d38d2a748b99 | Pole | 0 | Distribution | 2022-02-25 | 2023-02-25 | Level 2
02287107-b5c9-47ad-a076-6b4080f37575 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
bb82f9b8-e802-473f-8a06-6d61c026f351 | Pole | 0 | Distribution | 2022-02-25 | 2027-02-24 | Level 3
5f74188c-7d0f-4654-903f-dd07b1ff2938 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
653e1c9d-7ae1-4705-8755-43c539383418 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
4707987d-5239-43ec-a193-afa0d31cd8d0 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
eae58e54-52f9-4ea4-995c-125da0f0f215 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
c19e6e65-7d10-4a44-a241-18982b285b54 | Pole | 2 | Transmission | 2022-02-24 | 2023-02-24 | Level 2
c8847889-53be-40b1-af9d-59ce98bc74ea | Pole | 2 | Transmission | 2022-02-24 | 2023-02-24 | Level 2
d5f16ab2-8a29-40b1-85ed-73ee67224e08 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
592a28d7-5d44-4ec4-9df9-d4a543d9502b | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
ea66c5b7-9c80-4ad8-8e4f-c788116c06bd | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
6ba47bd8-a400-42ee-b779-bb1cc7941ed6 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
bbef76b2-3d90-4a6b-b2a4-4a9c7b9a4934 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
f1e8c6c2-4de8-412c-aa2b-e4963cdf9c0c | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
16d8cd56-e13d-4341-9277-3a576765b208 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
d5049150-9b22-48c4-a7a7-a8b1ec4eb6b7 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
de35ac6e-74d0-42c4-bbe0-ce163b65e1c7 | Pole | 0 | Distribution | 2022-02-24 | 2023-02-24 | Level 2
ee11176b-3a19-4089-8484-06d7561fa353 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
617233fe-4179-44f6-8e64-2079d1e94090 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
e7f729ce-ace2-4cd7-b676-9d4d161b25bd | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
4f6414e8-2baf-48f5-b9d8-7b32a0de8f13 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
a8b4ab2a-eb29-4e16-9782-63034f4d0465 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
0c1fa858-08cd-4b10-b081-f06df53fe855 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
8be489ac-8429-4a28-87ab-64885de3e9df | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
a0dd75d0-b4df-4f0f-b125-6856ded774d3 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
41d6a7ff-eb55-4d3b-adc1-f1ad1336eb34 | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3
0d0ce0e9-ab78-4daf-89f7-b341bd58b579 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
fa420291-7268-418d-a286-ffc4591be4a5 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
7c3e3bb4-6a83-4dad-b9f8-7f3ed34fde94 | Pole | 2 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
eb996fe9-c479-441a-9a73-d88a38ca7f49 | Pole | 0 | Distribution | 2022-02-24 | 2023-02-24 | Level 2
688af7c8-9566-4874-b32b-950521a06c76 | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
50ec66bd-cf4a-43bd-86e2-f06446bbfb0e | Pole | 0 | Distribution | 2022-02-24 | 2027-02-23 | Level 3
ff36785d-4895-4b39-bcfd-64f13737584a | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3
2241ac4b-d0c8-4428-b8d5-dcc663a03eca | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3
d089bd9c-b2d7-4026-9d59-f64fc9a6ec5a | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3
8020fb5f-2f00-4302-af7a-fef6bc43c26a | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3
e7a4df91-179a-4d39-b3ea-90d33d5661a7 | Pole | 2 | Transmission | 2022-02-24 | 2027-02-23 | Level 3
f785a383-b8c7-4949-92c5-a96f19b711ea | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
7f527968-df73-49cc-9f05-cee645222c12 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
372548d8-5d80-4e58-8835-e36b0f7f89e0 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
8214c438-9985-4466-ae83-4df0a16e2e41 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
78875fd4-13a8-495b-85ed-64b32539bffa | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
8ea93489-bcfe-4f13-b958-deafc56beff1 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
3caf99d2-0abb-439c-9769-a4ff298a68f5 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
531a22fa-866b-4e53-ad53-89fd92e25d63 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
4b6d1296-b85e-48e6-a916-2b30cb4661b6 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
0140a406-6179-42b2-b2a0-71b36891e433 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
8623e559-0d0a-4e71-a711-b09f3f779f4f | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
efbcf980-3eb9-4358-b4b4-fab2c7cbd84a | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
630fd4ac-7b24-4af2-8518-c56c321a5816 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
b9628861-bc4b-4148-b1fd-949f998b1025 | Pole | 0 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
124dea7d-f27f-4eaf-b349-c1c7a50111de | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
f43ef478-f816-4534-807e-30a5f1e2b999 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
5afd6502-8f0f-4a16-bf57-2f2f56ceb31e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
4909c102-847e-4b1b-b3b8-96117b2f076e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
0379701f-b44e-43d0-9341-899221cc2669 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
1c5378ec-3677-4013-b0b2-c329fd782dec | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
36069986-be44-4faa-8aa2-6eda045b2330 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
be02f36a-9b3d-4e56-b48c-c3225cb948d4 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
20450006-f432-4668-b702-b8e36c5bfddd | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
f064449a-ebf4-4c12-8b30-c523861c16b0 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
cac1df23-bf75-4e0c-b092-534cadd6ed8e | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
7b4ed4b5-987c-4178-8126-47e8fc35ae06 | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
bd5384c7-4bd1-4745-97a1-ac54117d1068 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
f4b7252d-7706-4bb6-9124-504b40c9892b | Pole | 0 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
ffe7051f-b693-481e-85a8-15ddc753f00a | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
6173cb7a-c893-47af-a28a-4a74f1e27324 | Pole | 2 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
7494c47b-292c-48e2-88e2-df9f87ce0379 | Pole | 2 | Distribution | 2022-02-23 | 2023-02-23 | Level 2
5a4c2575-d784-4717-a5b9-5b04aecb63fb | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
07c28662-ceac-4cd0-90ce-8232d672aabc | Pole | 2 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
c187a387-0679-4feb-ba14-1b09635120f3 | Pole | 0 | Distribution | 2022-02-23 | 2027-02-22 | Level 3
ba12ac90-f81c-4d8d-9070-2cff1aceae74 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
0cd63da1-526d-4da0-ac70-547f15f64ce0 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
88843017-9c65-45d8-93d1-b860d32ae628 | Pole | 2 | Distribution | 2022-02-22 | 2023-02-22 | Level 2
c6096db7-aa5a-4245-a2c2-a96b032299cf | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
6b61782c-fec9-4fae-bcdb-f8a67d3504f8 | Pole | 2 | Distribution | 2022-02-22 | 2027-02-21 | Level 3
02e2ef56-f561-4295-acac-ac41e9847395 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
e729f543-36a5-413d-b31c-4375990c69fc | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
4b4c7bc1-cefd-4e62-be59-d42b422ceb0b | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
935fcf7b-57f0-4309-b78f-19e5b8f9afb3 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
e234c2b7-5a0f-487f-a649-9d28f00d1a91 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
3987970c-c1ce-46c6-b15e-53928aa69149 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
37fa9bba-bcbd-412a-95af-4e2d9e84c822 | Pole | 2 | Distribution | 2022-02-21 | 2023-02-21 | Level 2
39633e0d-56ab-497f-8238-3a8df6bf0422 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
27bf932c-cdd0-42fa-bae3-ffae46450035 | Pole | 0 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
1d7adb21-0340-4c49-bdee-7f24895a2ca2 | Pole | 0 | Distribution | 2022-02-21 | 2023-02-21 | Level 2
dd434e8d-f495-42ae-8a3c-fbc483fa85a6 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
77826756-5e17-4d26-b134-e37ade697d3d | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
89f49812-93ae-46ff-962f-b7b67ea85506 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
c8f056ac-db16-40d8-8fa4-89a632372d17 | Pole | 2 | Distribution | 2022-02-21 | 2027-02-20 | Level 3
d6f3c386-d7a5-4808-b5dd-fd681b500b73 | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3
bc29ee4b-f7a0-4828-968d-3e0639b738ec | Pole | 2 | Transmission | 2022-02-19 | 2023-02-19 | Level 2
10e876c6-2a1b-4a9c-bf84-44016aeb1892 | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3
5187767b-3cdd-4cdb-8f9f-10e4aa4480da | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3
bbfbd9e5-2a43-4cf9-8d63-384354e6193b | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3
859ba831-d0d3-4c11-84f3-8617d3494973 | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3
ff865cf6-cf44-45b0-861c-7d275610101b | Pole | 2 | Transmission | 2022-02-19 | 2023-02-19 | Level 2
264b5ab0-413d-448c-8116-10d1869718da | Pole | 2 | Transmission | 2022-02-19 | 2027-02-18 | Level 3
78061a04-4fec-4305-93a4-7cfd7a4b02ae | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
f271782d-5511-4e1d-bdf3-28767b2d367d | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
9ebdfd81-25dc-409d-8f99-287299a905da | Pole | 2 | Distribution | 2022-02-18 | 2027-02-17 | Level 3
fb9048f9-5624-4264-9d5b-e8011ad6c8c7 | Pole | 2 | Transmission | 2022-02-18 | 2023-02-18 | Level 2
54f4a338-1b7a-4e1f-a3df-9f70fe166300 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
10f20064-542b-4830-af34-68bb174c67d5 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
8bd616ac-809a-4ef6-8ae4-aebb96ae6c54 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
66d67cb7-0a5e-4f49-92b2-dfcc25c0c996 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
877f8b4c-dc66-4311-908d-bbcea4e4d9be | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
7ae8bcc0-ff28-43ad-821f-34df53e64856 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
65a309c1-cf6b-4bed-bcae-32cb6208d3b2 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
6a4a1c51-02a6-4b74-b82f-3fcac6619351 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
5bebe5ff-2c01-4b56-a77f-80dcc59928a2 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
ac5e64b7-acb8-4a6c-bb1e-19af91331589 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
be5507f0-60d3-47e0-9691-1b65485e38c7 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
76bc5507-d5b8-4391-b358-fd12cb4faa44 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
67d30b97-97b0-4a62-84cd-7797cbc7b27a | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
20ebfdd9-851a-4144-ba77-0625426e7d2f | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
e3510e28-1307-4d46-9454-ec5d1a1ec04c | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
244f07ff-8cae-43b4-9289-1cc2efb2b7c4 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
5ce7533d-3ee9-41e1-b22f-ae9f635c88b4 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
d969d457-fe53-4ba4-b9e9-b87c641c08a8 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
9d0b1f07-aeca-4179-9c61-d5c19e29d82e | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
ffd4779b-c0d9-4725-9b42-351f37b59c47 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
552f0a00-eef7-4833-8a3a-4c29ddbf7b79 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
f063a576-c2b0-4457-b0f0-97e0cb588a4e | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
e9c86fb0-6313-4803-b85e-72184bea0efe | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
4e389dee-70ea-4356-81fb-848fef83676e | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
a4b3aed5-09f3-42d6-9182-f9fe12c38c47 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
0f36032e-a34f-4754-91dc-47ff2a73a780 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
d8e7a254-8a3a-4de6-be80-3ae534416fe2 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
96ee963a-a3aa-4fe7-8aba-3a3c507240dd | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
b5061134-142f-4342-8014-0a2d767e3bbc | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
c46eeda5-e1b1-4d5b-b74f-77cffee8366d | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
283a6378-1bd6-4d04-9e97-f397374239cb | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
96ac7bc1-1d28-4af4-8a56-4082430c47f2 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
ce444bd1-7843-4a24-97ce-db8d482edaf0 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
5e59230f-37cd-4b9b-9a74-00da4dfc6c55 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
37bc1523-6a11-4ff1-86d9-7279f88c8d46 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
10ed8733-af37-4da6-92c8-9fd2f663e4d9 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
f3cd9c1f-4c46-439e-8a76-2812b3465187 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
b574719a-7966-4dfb-b4f3-c52cc84fb70f | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
d422ad98-a166-4f00-b5c3-d0ffb783b6ff | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
1b3ce024-4b1d-422d-a0c3-3f9b51d9ee13 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
4fcae5b4-076c-4606-90eb-7451fcc61311 | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
a1244c25-99ee-4524-b910-82767ebe789e | Pole | 2 | Transmission | 2022-02-18 | 2027-02-17 | Level 3
9b33a883-46e6-4e44-a5fb-cb23af6f1daf | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
ae116213-af5f-42cc-b484-d2d33bee6dee | Pole | 2 | Transmission | 2022-02-17 | 2023-02-17 | Level 2
20304509-bc34-492b-a313-18c2622fefdb | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
b0f2f717-f4ab-499f-8053-20af695ded7c | Pole | 2 | Transmission | 2022-02-17 | 2023-02-17 | Level 2
b0b78394-d538-4c74-bd45-fa3c8b5519d8 | Pole | 2 | Transmission | 2022-02-17 | 2023-02-17 | Level 2
2dafe234-c350-4a22-b05a-4618d50078c3 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
7f8b7030-ef5a-4aa9-a69b-48627e76fb78 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
9d022b08-baf9-4dc3-851c-5f875c872ae3 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
eeda8052-0c8c-45c1-b98f-525241ff9abd | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
5c4f95d1-d523-425e-9963-647e5a53c5fe | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
0ed6137f-68ab-468e-9627-772310bca331 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
701d94bc-9812-47e0-8ac8-132e8531acae | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
70d32056-7851-4462-aa51-fa56955ad38a | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
8621246a-ca6c-4f4d-9c76-f902012c90a3 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
077c66c6-f44d-4523-b9e8-69a3c7cfa7b9 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
708ce6c9-1517-4ddc-a7be-264312b1ac38 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
74866de0-16c5-4b62-9d23-2b95b0ad037a | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
400aa66b-215c-4181-95ec-7b0e831f1bf7 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
9f3d9b3b-c7c8-4231-b897-17f0e3dcb676 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
c0382428-dc2b-4b99-8042-c74090e94096 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
9443dcbc-54a3-49f4-bd68-6a4199c6044e | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
f9e503a2-28d1-4614-9105-80b064f10829 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
0d0bbe7f-c4fc-4976-9fab-e6f5da0c688c | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
9dbdf0c5-a323-4342-af6d-5dad03f7cd5b | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
d73ac0c0-0bce-472f-b676-a3d01dae965d | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
271138f7-5681-485c-a4ad-f1121977cc3a | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
724923f7-f34c-451b-9e8c-fe74dd568deb | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
ea1fb652-0fd8-429d-80d0-084ea93c2976 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
99e20059-b9cc-4a3a-9f4b-b2912bf19144 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
9785ba76-1aba-41f1-864d-849a201fd1e3 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
49cc4cbe-ae3a-4e43-9dc4-6547476d1c7c | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
0b995957-56d6-443c-8bca-8201f2e469d0 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
c759a3a6-d3ce-4df8-9543-3c2a63ed597b | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
5865ac4e-a73c-4af6-ad1b-2855f0e051fd | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
8d8d136e-295f-4bd5-a39e-370d80b33820 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
47ce586a-09a3-4662-99a2-8fff6187df98 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
44fe6654-06be-439c-887c-70312b9f1c44 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
4cffcaa4-5daf-41a9-8b4c-2a7062fe2ea1 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
c1b5acd2-946f-4d5f-a591-52b40de913ff | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
22d303dd-6f3f-4495-869f-f550c3c1c990 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
c65a2464-72d2-4e03-b050-aa50e1bec388 | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
ba1957ca-b71b-44d6-928c-e08a6c85191c | Pole | 2 | Distribution | 2022-02-17 | 2027-02-16 | Level 3
2ec9f44d-2040-42a7-a15d-e49edf39d141 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
691e566d-b98f-4afc-8531-bb44156b2843 | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
efbee5aa-3981-42f1-92b4-a6e75952b7bf | Pole | 2 | Transmission | 2022-02-17 | 2027-02-16 | Level 3
b94ff1b6-54e0-4804-a8bd-29e125163ec3 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
3a89e89a-dd36-4b9e-a5ca-d48f3ac4ef29 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
d890ee9a-0f14-4296-9bcb-cac84e5cb56a | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
761e0631-9e18-4c18-b91d-11607bb6c248 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
38853420-36b3-4547-8e53-0b4f46fe2305 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
553f2862-4976-4606-b812-4a351c550645 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
6bffbf8f-5193-4989-9d4d-868158074cb2 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
f7deaf33-5ee4-4c6b-a334-ec6c4138a5e6 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
a69f610f-2ce0-453c-bf6e-188cddc9421c | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2
4e8d9aa4-a7e1-4e57-b12d-d3da98fc7707 | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2
248d43da-8321-4808-a946-7cabdb32c13b | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
e3f6bb7e-bd0b-4d80-950a-097a99a868bb | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
7e07d202-73f1-4563-a420-00fb3f5d7ffa | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
947bc1d4-4b8f-4b81-a2f2-63d56c37edbe | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
7931be79-59c6-4093-8bf0-f35fff6cfba1 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
02796879-2d8e-48f0-8d61-19999923fd7b | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
b22ee7ef-2188-4ff5-b4b3-c54bea5237be | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
3f6dd675-87dc-4253-ab19-28b711bb2c96 | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2
87462660-e568-41cb-b54b-9a9c864adca1 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
438f01c7-4e93-4fed-899b-db83aa2f520b | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
55899d15-7725-4a37-b2ac-a02ae705d0ee | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
7da9e69c-245a-42ae-af6b-417204b8571d | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2
18bd9e4c-5b55-47fb-801d-d163bfd77b96 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
3c6b65c4-c447-44ba-8b8d-39cb1b955f06 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
487ad8dc-134c-47ab-9b38-4b7772b7d179 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
69f3fdb5-fc6c-4016-a37a-1c5b3981f9e1 | Pole | 2 | Transmission | 2022-02-16 | 2023-02-16 | Level 2
65be6773-48df-42d0-8a6c-69c015e3152d | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
c062b670-c241-4a35-b934-06669267a140 | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
a78cc53e-7923-4c2b-bb1e-6cf59d8a332e | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
039d6d2a-b43d-49d4-9bb3-875ca5452b3d | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
ee4f3c52-702f-462c-8a6a-505e7d518d4b | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
e090602f-3ae0-4894-8b91-6c55cfcc870d | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
f80faefa-f6a3-4b7d-a0da-2c08a49e03df | Pole | 2 | Transmission | 2022-02-16 | 2027-02-15 | Level 3
da83ef42-52ad-42b2-b8c1-ec12b7d3294e | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
df0e6db0-e95b-47ff-8728-3bae6646c39b | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
45ecfcbc-2389-4242-a5ce-de7064b1d746 | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
383aa520-ca8f-4e32-9b16-df1d4a27ed0d | Pole | 2 | Distribution | 2022-02-16 | 2027-02-15 | Level 3
74624c63-4d4d-485d-821d-65a1725e9c91 | Pole | 2 | Distribution | 2022-02-14 | 2027-02-13 | Level 3
b8daa9ae-7ca3-4e7b-b9d5-7b92c08e954c | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
3bfdd5a6-e333-4da7-a375-20004b5d6fc7 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
0b4dbea0-9aa1-4c2d-98af-0e14ef947e5b | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
5aff8b59-a6c4-4e8a-b3c1-87ab7457b5aa | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
90b0a8f3-97ea-48a5-b83b-b41ce2aba6e0 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
94d69d5e-b9c9-43e8-b57c-6b5f4214c313 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
29680063-05b2-4883-ae3e-bd1e250dd46c | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
36f334c7-a190-4f99-b45d-1e740329be2d | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
a44c9641-1ef0-4d78-a32a-2fe5306a978e | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
52bf416b-bc47-43d0-8ad9-ac88cbe69068 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
d9e040c1-b18f-4b27-a4a8-b2008765546b | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
17407ecf-d6ae-4333-a45f-c72e0dd2f76f | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
35475c42-c6bb-4c3b-8f31-ecc9fafb1fc2 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
1cf59be6-c5e4-4755-aefd-924f11e06867 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
01f2f755-36c3-4cd8-85cb-6c5d1280b754 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
daeaf391-654d-4291-aa01-3ff6de002d49 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
d6b20f75-a2c2-431e-86ff-7afeed876eb2 | Pole | 2 | Transmission | 2022-02-14 | 2027-02-13 | Level 3
9bfca67a-0300-4dbe-b484-7e9513d71de2 | Pole | 2 | Transmission | 2022-02-14 | 2023-02-14 | Level 2
86064895-eec6-4003-b4bf-25c639008185 | Pole | 2 | Transmission | 2022-02-11 | 2023-02-11 | Level 2
a778c250-eeeb-44bb-81b9-94f18cf50bc8 | Pole | 2 | Distribution | 2022-02-11 | 2027-02-10 | Level 3
7975eba6-4ada-453f-9f75-5f0e06d525a9 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
5f3dff51-319e-46b0-98b6-e3656b60e743 | Pole | 2 | Transmission | 2022-02-11 | 2023-02-11 | Level 2
9eadc902-960d-462b-ae6a-85a890a2b9ed | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
48cde3d7-c26e-4fee-b6f5-36d1b31c6894 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
a91bcfcf-9eed-4f03-bb0b-5e5807b9a478 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
2203535d-0869-461c-ab49-ed472ad0a845 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
1048a037-c19e-4410-a822-f54a33a094e2 | Pole | 2 | Transmission | 2022-02-11 | 2023-02-11 | Level 2
f98781ca-7f80-4d10-9921-e9f3e33dfecf | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
5b5d578b-5cc4-49f1-909c-43d1aa697d7e | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
9a7e0f58-d901-472f-9d39-46d84a1deb44 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
27271a79-83ee-4590-bc95-201c162d2d62 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
0ed4b466-e953-4ed0-a059-eec179a89ccd | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
f93c7ddc-36bf-4e1f-aab6-bcc9ca37f7b9 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
6eafa25b-0379-4a53-a155-a00da1809bdf | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
0096ef7a-d300-41bb-894d-8731d7d42a20 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
8fdd7ca0-48ee-48e5-8706-1e05f3dc29a1 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
90dbe23a-5b6a-4fe4-847e-069aa09a1b87 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
7fd32072-5cc8-40b7-87e8-a7b5b9a3db60 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
854a7074-a592-4f1a-8b28-994790628182 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
5027ec82-9617-45c1-b457-2c865828a8a4 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
3255b111-9ee4-4ea9-9911-131e79871f89 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
e8ea4709-8a1f-41fc-bd5e-022f9f4e755b | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
85cf0826-67ef-469b-953f-fff1489e8e07 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
7889ba89-05dd-4b28-98b5-2c780633160b | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
640e56e0-8c5b-421e-ae26-999b8e6b038d | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
98797cd6-beba-4dd1-a582-96adbd90c85a | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
ef0f6d13-2f30-42cf-a839-16c3b8bd0f84 | Pole | 2 | Transmission | 2022-02-11 | 2027-02-10 | Level 3
e1bc3482-f8dd-45b3-9c5c-02021907d297 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
ea3ffd3d-76d1-472b-962c-05a5f788a14a | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
347a3df6-003d-4e15-a10e-c538cc3aa9c2 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
92273650-5c8c-4b31-80fb-371286773c33 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
7ca72158-fca3-4608-963a-606b7090802f | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
84f38b4c-878d-4aab-8e63-f0fca525ea00 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
98e997d0-bb60-416e-9d8d-00e00d072fc6 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
336ffc13-c07a-4ce2-908b-b94223b4b313 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
f8b26909-0c63-4bb4-a557-61764d582af3 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
afc2c3c2-8cc4-4f9a-bf8b-acf9f7e7afec | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
8577e9c9-d067-43e7-b353-dabea63707cd | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
373081f1-43f4-43b3-9ac0-ac3005b9bc1c | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
ef2c5216-f05c-4c86-aa97-c358aa5d4da3 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
fd25aefc-5092-45e8-8b3f-41191c2b6338 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
641c09cd-7df8-49c1-89fd-0c28e7ab180e | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
4ba7a9c4-396a-4e83-b196-597dc613f730 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
4e714cfe-6bfc-47c4-9d1d-9c79c9631560 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
b5369aa0-9d84-4889-8a25-ba2d224cabd7 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
72180a74-92d1-4ee8-af48-47fe23503a02 | Pole | 2 | Transmission | 2022-02-10 | 2027-02-09 | Level 3
f4ed4a8c-c4a4-4a20-979c-921a00c4a32f | Pole | 2 | Transmission | 2022-02-10 | 2023-02-10 | Level 2 |  | 0:00 | 0:00 |  | Insulator broken on 7200 center phase
e28837f0-09b3-4e71-a818-70bd5fb9c6fd | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
e491c326-4ddc-480c-af9e-5cf024b89dd5 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
f5e435d2-8dcb-4ab3-8d2b-874bf6cfbc58 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
685c2e3b-7e3a-4f84-afcb-a540db1bd42b | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
e94c659b-4d85-4b88-9972-6d2f0fc95a7b | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
0d19c7ec-c428-45af-9d00-249b7b29c16e | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
9e1bba3a-8133-4bcd-90e4-4a1ad40a0f54 | Pole | 2 | Distribution | 2022-02-09 | 2027-02-08 | Level 3
aee47510-2510-4c8a-866a-dfc1851e7622 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
7838ca3b-97d3-41ed-864e-90337de4d2cb | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
b164fc35-2500-44d9-9ece-ebfeb6b00cdf | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
409e354b-5e35-4b21-9f26-c5349fcaf695 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
3377288b-7821-4177-8bf7-5452691c702b | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
1418d789-7bc6-4a55-93a4-632676a3455d | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
3a211bc7-0824-48e7-ab31-826154608772 | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
bbb0feb7-c394-4e1f-b724-67b7a5aa828d | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
8b77616c-e838-4a9d-9d19-43e258cce374 | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
8ebbf735-2967-43ce-a524-164f20cfb254 | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
ad3fb623-0e83-4c5e-9c25-c81f37faa957 | Pole | 0 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
3ecc3630-65b8-4cfa-b026-5aea84a78cc9 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
dc0dde83-37dc-46dc-abf8-e909708acf89 | Pole | 2 | Transmission | 2022-02-09 | 2023-02-09 | Level 2
65d2bf68-d300-4cd4-b5b8-897247934d06 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
b4aff6f8-b0f6-4950-a3c5-64249790acc4 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
b82ee00e-e10b-462c-b893-fd1c6cf6c836 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
04d57a4f-0ec3-42b6-914f-a3469fd5f3a2 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
f9deba75-bfe9-44f9-8b9b-6a996ee65564 | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
4c4a84be-2c92-4176-b64c-03051d78995d | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
e62a2953-aa96-437a-adc0-6eca5113006a | Pole | 2 | Transmission | 2022-02-09 | 2023-02-09 | Level 2
9c8a0198-fe64-4ece-a649-80e87f783fdd | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
11b9b340-0f94-43dd-b4e7-f59a375faf5e | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
f5f3a27d-0f28-41e2-b904-041b5222c77f | Pole | 2 | Transmission | 2022-02-09 | 2027-02-08 | Level 3
27a4e67d-0b6f-45b8-bda6-d421370b0101 | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
0d4d8486-686b-4e59-9502-cf8d8dec856d | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
b5aa8e4f-995f-4832-8c9d-a0f0382225c0 | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
7b48c7b5-e511-40cf-9c07-908d5a0fcc4f | Pole | 2 | Transmission | 2022-02-08 | 2023-02-08 | Level 2
361ad578-c9d1-44d6-83fd-a6171688612e | Pole | 2 | Transmission | 2022-02-08 | 2023-02-08 | Level 2
a5cdc95e-52b2-4bbf-a91a-46e8ac3e68eb | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
24567a0a-842b-4466-8e30-ec5914884b87 | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
c897e307-c5e7-4f21-b76c-66ebb1c7c7b0 | Pole | 2 | Transmission | 2022-02-08 | 2023-02-08 | Level 2
b1d99005-1e7a-4463-9842-bcd00c91afeb | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
8fd2d194-0cc3-4236-b131-692a3f7afe6e | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
262258f9-4b4a-4482-ab78-5c5d251ff5d4 | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
2f8b7c0e-9f64-40b0-9e06-c2e61b46ab5f | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
7867d964-1f89-4b8c-9e83-e87cc761370e | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
aab229c0-4d78-4d7d-ae92-e8778adf11b9 | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
3a508812-be8d-4175-855e-66a8a93c1e9f | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
c5a11c96-f73a-4aa4-a8e8-9b0f66fc6d10 | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
6e920e41-7726-4669-b859-7885e6e5d4ff | Pole | 0 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
6541e1ef-582c-4724-abc1-27c4a5ff6ff1 | Pole | 2 | Transmission | 2022-02-08 | 2027-02-07 | Level 3
74d3db50-2958-4ea3-aae7-6ec687c6f7f3 | Pole | 0 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
93088519-5600-44c8-b679-2de6d10b40fb | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
4fee4d82-ce54-4497-92cd-bef5e1a98bcd | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
40731215-a42f-447e-8e09-2a70e393c3f5 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
48876cbb-c205-4317-900c-8b1b899ffb53 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
9d4aeb38-6c02-4d0d-9d96-ecf2b02be560 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
c8b0d519-5ed0-4d04-ad75-c9644ff6b414 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
024a504a-a708-47ea-a6e1-6aea8430b429 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
2ba86207-016f-4a6c-8374-f575e54bc4d0 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
5e8d7c1c-19a9-4c15-bd56-e3877901be45 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
26733d3c-41e1-4939-b0c9-974e9b7aed94 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
fdb754c7-0348-4e32-8e09-bf70bf37e73c | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
47d9ac1c-3101-444c-a723-f6b156677068 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
c8948eb2-ee8e-4a7a-b39d-4d0fb33f4b2b | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
bd2ecedf-a2b4-4298-b714-ea376549d553 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
45d8b59e-b40d-437d-9a7c-2b9b922f4f0e | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
6fe1e808-51f9-4bbb-b36b-38c49894d5df | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
ba6e7d0f-d2c6-4b19-a729-2cf4fa5b6aba | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
96ed71cd-d30a-4844-86b5-88e009d4f810 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
c60090d2-1d60-416a-a60d-d31e4a6797b9 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
689a9694-35c7-4e5d-8fd6-76093054c955 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
94c1c1f8-c648-4047-ab7b-42658c6e8c22 | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
829bc174-98ef-4def-b02c-c28427280eb9 | Pole | 2 | Transmission | 2022-02-07 | 2023-02-07 | Level 2
e755036b-b4b9-46e2-9efe-88413bcaceed | Pole | 2 | Transmission | 2022-02-07 | 2027-02-06 | Level 3
e491bab9-5918-49d5-910a-d85306c65fe7 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
50eec48a-d4d0-451b-8f8d-7bf69be83d88 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
ca052ec3-6474-4b71-9760-46f14f99c04b | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
3cd8779a-dd4f-4a80-bd0f-da912a22a440 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
2ef13931-0df6-425f-baae-b99d67aa692b | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
9b504635-8529-47ad-987c-e9c222dfaf87 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
0f5d4677-fbd6-4d80-881f-e1aced3e76ba | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
59814633-5d78-46c3-98a6-d6a793ea0993 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
73c23c0f-66aa-4389-a9e0-3c4e21a9372d | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
7ae3c14f-2dbc-4e6d-bd76-be4e2ded08fb | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
3246d659-6d77-4831-90b6-cea9af7d79c8 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
5a44b1f9-daf3-47d2-9906-da650f080764 | Pole | 2 | Transmission | 2022-02-05 | 2027-02-04 | Level 3
4caed8d0-3562-4ccf-8268-1666563489a4 | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3
5557cf6e-722e-449a-b1c9-9d5b57bf62ed | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3
863da285-edbf-4295-b8c2-fe56458d6273 | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3
6f851d3c-aed8-43cb-83c7-ed251a712fb0 | Pole | 2 | Transmission | 2022-02-04 | 2027-02-03 | Level 3
f00f17de-b84b-4d40-bccf-c6688a380e85 | Pole | 2 | Transmission | 2022-02-04 | 2023-02-04 | Level 2
d91d5763-eb98-45d2-b25d-14175af96863 | Pole | 2 | Transmission | 2022-02-04 | 2023-02-04 | Level 2
db955333-1b48-44ff-a86f-eb29f060cb2d | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3
eb0ee75f-54e1-4190-bbfc-c675345a4506 | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3
3b411f7d-7f84-4058-aeeb-38aeb8b9ae3e | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3
ccfc32d6-007e-4975-aaf2-5b54592213bd | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3
2ae45b42-6bdc-45a4-8c14-68dc424b9375 | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3
aaffcd1b-a947-42c5-b502-27c72cdab91b | Pole | 2 | Transmission | 2022-02-03 | 2023-02-03 | Level 2
1b830366-a6c7-4b26-ae93-86da0e17ae57 | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3
0a5f34bb-89c6-4d6f-88e6-975684f2b44d | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3
8e8cc5cf-35da-4c8b-8bba-06cfc398c5a3 | Pole | 2 | Transmission | 2022-02-03 | 2027-02-02 | Level 3
eef9f8e3-0d94-48c5-8767-e524d5a51daf | Pole | 2 | Transmission | 2022-02-02 | 2027-02-01 | Level 3
0616218b-bb19-4d87-99e1-0e825bcd16ea | Pole | 2 | Transmission | 2022-02-02 | 2027-02-01 | Level 3
7a202396-2fa4-4d61-aba4-2c26ca013098 | Pole | 2 | Transmission | 2022-02-02 | 2027-02-01 | Level 3
e044ce00-f559-4a8f-b3ce-01599b55f35d | Pole | 2 | Transmission | 2022-02-02 | 2023-02-02 | Level 2
e0a1751c-bdfa-4331-8979-9128fd95f145 | Pole | 2 | Transmission | 2022-02-02 | 2023-02-02 | Level 2
8e910bc3-7b15-4540-9482-fe25885e484c | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3
bb6f0d85-ecd7-4884-a166-b09df0130823 | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3
673b2574-95cf-4487-b75a-9bd29aeba34f | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3
cd06f12c-7067-4332-93c2-1bf2de1e0fac | Pole | 0 | Transmission | 2022-02-01 | 2023-02-01 | Level 2
b5a819ee-8a32-44bd-9ab3-4557bc103c3d | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3
f9f147e9-2310-4fd9-8566-3b168ad678f2 | Pole | 0 | Transmission | 2022-02-01 | 2027-01-31 | Level 3
40ed4c65-72dc-40e1-bb31-024a4eaeb42f | Pole | 2 | Transmission | 2022-02-01 | 2027-01-31 | Level 3
1804e337-8682-4fa3-90af-ab5a106c71e5 | Pole | 0 | Transmission | 2022-02-01 | 2023-02-01 | Level 2
c683f763-e432-4ba1-9825-fd7bf223df28 | Pole | 2 | Transmission | 2022-02-01 | 2023-02-01 | Level 2
b66c6340-5f3a-4341-ac49-6bfce30c3977 | Pole | 2 | Transmission | 2022-02-01 | 2023-02-01 | Level 2
47a98e2f-f112-4294-9698-44510b7ddfe7 | Pole | 2 | Transmission | 2022-02-01 | 2023-02-01 | Level 2
74d3df68-d906-4449-be83-d39385d41faf | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
4683e080-f392-4e3b-95c2-a95e274ac53a | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
ec0ae177-610f-40dd-8840-854efb5ca0fc | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
79258e62-ee91-4690-9408-c165c6761acc | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
a945fddb-f3c3-44de-a109-e0d56866c621 | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2
ee8b96bf-0235-4a6d-b410-3adc36b03f94 | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
d53e934e-5450-43ab-981c-1a4c39321b26 | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
697dd3f0-21f1-48f0-bf87-f8c7b3d3a00a | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2
c4e018ac-38c8-4b21-a021-3434ef36aed7 | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2
fee644bf-d820-47ff-84ef-ed0a8f4c90fe | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
e7f8b7f3-8c67-4c62-a2d3-25de36bddacb | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2
45272cd3-3f95-4a7b-bae8-62c8842024cf | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
5cfd89ec-b5bf-4403-a62b-7de5a991b46e | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
b2ae0f31-3cfd-41dc-9a14-e0695e2c3162 | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
79500704-6812-4c62-823b-ede8492e679d | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
453370c9-9491-4498-89a4-34d078f014b2 | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
14a55c3d-7228-478b-9c15-e17f4b3f3dcc | Pole | 2 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
3863d8ff-96e3-4363-8e01-44bd64f1e23d | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2
0f04e37b-11c4-4417-839e-18c95bb58812 | Pole | 0 | Transmission | 2022-01-31 | 2027-01-30 | Level 3
89554432-36cf-4421-a905-75d794760a16 | Pole | 2 | Transmission | 2022-01-31 | 2023-01-31 | Level 2
3e5aa20b-287f-4e65-8d89-20f2b57510ef | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
bf41e8c1-f20b-4868-bd31-488ffc926480 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
64de3135-7326-462c-b984-7f93c432fe62 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
19034374-606f-44f0-bbca-bbc9c8e6c6d5 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
80b3a676-69ca-4447-8044-503c203f9f54 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
38ea6374-a530-4a97-8051-02e116fa36d8 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
30e9314b-3fc7-4ef3-8a8f-8672f6471c83 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
32ecb370-1fe2-4223-9aa3-b3b344016ad4 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
240dd5b0-bf4b-4d2b-9958-dd0349c52e71 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
6dd8d446-3ba3-4675-81d8-13aadcafe105 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
7b161d3f-c818-4639-a2bb-a97f1b8dc49e | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
310df571-c1f2-4150-b7d9-9590cc000ce0 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
9db076d1-85ab-4f7b-8fe6-cebe9e9e4372 | Pole | 2 | Transmission | 2022-01-28 | 2027-01-27 | Level 3
93ee02b8-6f36-4c48-a150-07ca5b99df53 | Padmount Transformer | 2 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
bfbc3d9d-99ea-4edd-91aa-d26abf3aec1e | Padmount Transformer | 0 | Distribution | 2022-01-28 | 2027-01-27 | Level 3
c2494965-76d3-4f24-9c76-06d620e419d3 | Padmount Transformer | 2 | Distribution | 2022-01-28 | 2023-01-28 | Level 2
191884e9-eb33-4f6f-bf76-653a77eeefa4 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
36db653b-49fa-4fff-a66e-f48cda801d8c | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
6e1d1192-67d8-43df-8937-bd582eeac2d0 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
5957e772-71c6-475b-a7b0-6c0c4f54115e | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
b816cc8d-e397-44c2-b931-b1693beffc76 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
c55ae154-c776-4d22-8c01-d3618e007b92 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
55163faa-a6bf-4846-a22a-43f45272dba0 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
854ae423-8952-4f95-b779-391c374b506b | Pole | 0 | Transmission | 2022-01-27 | 2023-01-27 | Level 2
8d86757a-3c9b-42af-adc7-06796d9d7a29 | Pole | 0 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
159e1a8c-1def-4adf-85dc-753639c85d4e | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
af3c60aa-0c35-43c4-b18b-54a6a678f88d | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
4170f2d8-a3b3-4fd9-892d-02c99aeff2c0 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
78e1a696-704a-4c47-bcee-1338dd0737c4 | Pole | 0 | Transmission | 2022-01-27 | 2023-01-27 | Level 2
8c70cf5e-777d-4e6a-a0e3-216ed425c4a3 | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
8bfd5005-be1f-41ac-8a4e-f257533a2c7e | Pole | 2 | Transmission | 2022-01-27 | 2023-01-27 | Level 2
043fae98-ccc9-44de-a7c0-fa93e21c647c | Pole | 2 | Transmission | 2022-01-27 | 2027-01-26 | Level 3
6eed2db0-a166-431d-8bd6-c30d56d18c7c | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
468f2fdd-e8ea-4ee5-8a89-d9111ae6c9ea | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
28a651f7-bf68-40a7-a7d4-87e2666f933b | Pole | 2 | Transmission | 2022-01-26 | 2023-01-26 | Level 2
b07a6841-ec72-4547-80db-57b6fb1ba967 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
8bf623ee-ebef-4f63-a753-3af34c5f53f2 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
de0312a9-32dd-4e37-b7ea-5450062d4b14 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
99eb7146-2303-4774-b479-2df14edf0fea | Pole | 0 | Transmission | 2022-01-26 | 2023-01-26 | Level 2
71859952-679d-4912-8265-60faa7e2ef99 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
228af172-de20-4126-8c9b-17f1104625e8 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
3b13e89d-65a8-4270-8810-28f708bfc6ea | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
ed1f4cfe-c268-4216-abc5-e013378d3fef | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
2de29661-84fd-42b7-9355-fdb668ede5d7 | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
5f2162e3-67aa-44a3-9117-68f66bec77ca | Pole | 2 | Transmission | 2022-01-26 | 2027-01-25 | Level 3
dd4c6a5b-6280-461a-9307-7810ce4d656a | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
89cff108-88f9-4315-9b45-e516a53c9b5f | Pole | 0 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
4d986c89-524b-49a6-9c18-2c77865ba0b1 | Pole | 0 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
08977244-361d-49a6-a11d-b7ea84885b95 | Pole | 0 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
1aa56628-a981-4cc2-9c27-8f81f0b0010e | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
900092a9-0d82-4ba2-8e68-2a871ec76873 | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
ffdb08e1-3cda-4d70-b378-a29db53c941b | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
7a8cc998-e2c9-46f8-acc3-c1ce1ebd65ce | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
79f94430-f7dd-4e43-b791-ac44b00b66bf | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
b646a044-212a-4883-b835-05df3135e9be | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
099b610b-3d59-4b76-957e-d75e3f85534a | Pole | 0 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
222bee85-4956-4636-87b3-8d20690dc12e | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
ede85024-0ed1-4881-a165-cae441895ca2 | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
8dd8777f-cf04-4be3-b637-99cdbbccd3a6 | Pole | 2 | Transmission | 2022-01-25 | 2027-01-24 | Level 3
8f54a0c1-d79e-4053-adb3-8dbe11fabb40 | Pole | 2 | Transmission | 2022-01-25 | 2023-01-25 | Level 2
fc498a09-326d-4d63-9f85-0e58a10d54c1 | Pole | 2 | Transmission | 2022-01-24 | 2023-01-24 | Level 2
32eac4d9-d7a9-4d84-afbd-d62f0f2bc1fa | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3
b65d9914-75b7-42d7-87c2-3a1b5618bdb9 | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3
df04d907-f050-4e06-9ae5-67856b74cbd9 | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3
d26fd316-98a4-484a-b296-4ab7bd2d1fd5 | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3
2b5846ce-5add-4fb6-b30e-110f0be2516c | Pole | 2 | Transmission | 2022-01-24 | 2027-01-23 | Level 3
1aaa5c1f-bcb6-4cce-9787-100a211eb9e5 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
07721d5a-ad9b-47f9-8819-d39cf45b9d5c | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
472eb80e-191d-40fd-ade0-ae3e51c4e6d1 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
d267c7e5-4ceb-4199-97f7-bf2048740895 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
da6dacc1-4a6a-4394-957c-924cb73056d8 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
103f1ea9-8a8e-42f9-a2b3-3525f31e499a | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2023-01-21 | Level 2
1f99e0f4-136f-406a-8262-107ae1a80f08 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3
6cc1fc5a-97c5-4a06-a0a6-da51d2293a39 | Padmount Transformer | 0 | Distribution | 2022-01-21 | 2027-01-20 | Level 3 |  | 0:00 | 0:00 |  | Has zip ties holding elbows on. Need bails for future (non emergency)
dfd24fd6-91b4-4bb8-8839-a82c1dc935e2 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
d266625c-43c3-4c3c-94e3-23d778ea75a3 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
01bebe7d-d676-4e4d-878b-d83a0d6dc154 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
00baae16-87f8-4ef0-a371-677f6b3fc9d0 | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
4734d0db-d69d-442d-9329-a72bd49e6426 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
0dbd06bf-73c9-47f4-b82c-fd93a575e3a5 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
c6690925-fa90-43e6-ba6d-049b1e0e9c3f | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
dbc3e3b3-ae05-4c5a-9963-18c961f030ea | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
4bf630e0-88f5-4909-bdc3-531419564305 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
f2a2a997-eeb8-4c09-877b-e9fdcb6035c0 | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
2db31abf-c0c9-4fa2-9a85-9c046769046a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
c5d55497-e65c-4f7d-ab84-8e9cdf4e869a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
7c8bfe0b-609c-4ba6-a3c1-85b5d2ef29ba | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
1afa07df-5652-4731-a553-837aea85f6ef | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
7ecacf7e-521e-45bf-bb42-2b4274086fde | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
31a84e3a-8718-4206-8d68-4eb3f1824895 | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2023-01-20 | Level 2
aea6ccf9-6fad-4278-87f5-ba0510d99b5f | Padmount Transformer | 2 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
29bce270-d482-4724-924d-613e6e3fb41a | Padmount Transformer | 0 | Distribution | 2022-01-20 | 2027-01-19 | Level 3
b9d0b771-b60d-40b9-bdb6-3f6e28f4a8d0 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
0277508f-0c50-4703-9be7-9125d4268361 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
1e9a1327-0c87-46d3-bf4e-f7d4a57910f0 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
bf15e60a-78ab-448d-b152-b3a0481513e7 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
7362db7c-3418-46b1-b363-050ebc6befd6 | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
86c714dc-ffa8-4b1a-848f-e5d8b0e30c5e | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
3cf79ed8-740f-4afc-abb6-af5a8d24cf81 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
85876347-5fe2-4ec0-a549-8c3ebe25f0a8 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
ebbebcd8-d748-458d-b72b-0b3cb3a8a81d | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
433df26e-b9fe-46b3-ac84-8f2d3d679ced | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
ed1651d5-b910-41dc-a308-9c61a77f537e | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
e0d50655-43ff-40fb-bb34-dd1edbc37ac3 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
1f24d5d0-8418-47f1-897d-4683b8869b3c | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
4a12f514-e185-4ea2-9ffc-50bb9db60e56 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
6a00524e-e4bb-48f7-ab2c-8930f7cddceb | Padmount Switch | 2 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
08d547e8-a5c2-473a-a6be-84f511b6d5fb | Padmount Transformer | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
f3182b1d-31f0-4c76-97f6-63e1d518d9ec | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
d9cf66c2-337d-4eb0-b597-6165a1a0e021 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
1eb15c5c-161b-4a25-b21c-3dba971c1f6f | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
a5eee544-b786-4e61-a196-4bd701207d97 | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
dfcfdca6-6336-43ba-b883-e93be03864cf | Padmount Transformer | 0 | Distribution | 2022-01-19 | 2023-01-19 | Level 2
1104ef60-88ca-43c9-bdf6-97494ad8fda6 | Padmount Switch | 2 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
00ae7a6e-21ce-43f3-8e6a-e9c5360de7fd | Padmount Switch | 0 | Distribution | 2022-01-19 | 2027-01-18 | Level 3
4006d224-a3cd-41e1-bbf4-2f8e33663527 | Junction Enclosure | 2 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
b043c885-86d2-4708-a4a8-d4c523c38710 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
9815eb27-a84d-4d74-90f4-48b89dbd5194 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
2d440729-aaad-4cbe-b9cf-29f1a2671023 | Padmount Transformer | 2 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
9b2b4f00-bf87-450b-b218-4bd61980c528 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
259e0f78-ef03-4bec-b5d0-52870c54dd63 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
6fdfe8d9-f1d1-4987-afa5-100642f24f8f | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
2f431f96-ba99-48fb-b4ed-144018357c85 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
98880d10-31ab-4fd3-bd11-918b54d50281 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
edc285b9-13e1-4d0b-b27b-8ac71239b037 | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
ceae8a3c-ebaa-48c5-96eb-3820c7acfeca | Padmount Transformer | 0 | Distribution | 2022-01-18 | 2027-01-17 | Level 3
c32b12be-062f-4209-acce-3b56afc9ff2c | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3
2d968f2b-c0c2-48ac-a981-41d4c4c06d4d | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3
9bb99be4-599e-48de-a5a8-3adeb285894e | Junction Enclosure | 2 | Distribution | 2021-12-21 | 2026-12-20 | Level 3
eba29318-c221-4eaf-b989-0ba7d80e26ab | Padmount Transformer | 2 | Distribution | 2021-12-21 | 2022-12-21 | Level 2
7f028d2a-90c8-44d1-b2c5-70c6d9c66a4e | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
5ee1b427-c329-4379-8db0-a2052d7642cc | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
3d3a05a7-c603-4c90-bad2-0dcebecd2e53 | Junction Enclosure | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
11f778af-d1c3-469f-a294-ebb58f0efb19 | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
de7edbd5-f702-4c28-a3ca-d686c7e9311a | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2022-12-20 | Level 2
43ab3ef7-b7d2-45a5-8fda-42eb651834c2 | Padmount Transformer | 2 | Distribution | 2021-12-20 | 2026-12-19 | Level 3
e70af0a7-2aa0-41cf-8c43-6486ee763173 | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3
25ff2b77-ef21-4496-b38e-9a8111541a44 | Padmount Switch | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3
9ae2ab3f-b422-4680-8c42-2921922e1c1f | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3
a719487e-a750-441b-b85f-04a822e554bd | Padmount Transformer | 2 | Distribution | 2021-12-13 | 2026-12-12 | Level 3
14d6eb9f-89f0-4b12-9036-a3f7b388f9fa | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
e3a29ce1-e303-4930-a89d-e0a322d3acc9 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
cb869d06-bdaf-4ba4-a091-e77f580294ec | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
80aa210b-37b6-4f13-a74e-2710845afc9e | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2
2c97498b-cd6e-4150-b31d-c40916a8e36e | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2
243d7ee1-f943-4ef4-ba74-67b07dabec33 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2
26b0dcfa-de42-40df-9903-179e832b48d8 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2022-12-10 | Level 2
caba6f74-2b89-45f8-a32c-90a52d5d8b28 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
0eb637ab-60cf-4b3b-b8ae-840ddb8b5cf1 | Padmount Transformer | 2 | Distribution | 2021-12-10 | 2026-12-09 | Level 3
3fc33f72-480f-4986-b4d7-245969deafb7 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
c589af83-02ef-467f-aeee-7d217f1e8f13 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
5094ee40-d750-4e30-acc0-72c09561e678 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
6f081616-2a6d-4b22-9142-b6696dcea656 | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
dc0f5871-0131-4f09-9527-17d704e73a1e | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
36be12e2-15f6-4ae7-8887-2f6823f3012c | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
ca4cb178-f6a7-4484-816e-59b7c67fe56a | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
f17ccf5b-a1c4-4a0a-9532-3522a4767fcc | Padmount Transformer | 2 | Distribution | 2021-12-09 | 2026-12-08 | Level 3
c28aee0a-ceff-4572-bc48-2e5cb0a84e83 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
89dc8e3e-bbc0-46d8-93ef-8e076dbceb41 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
78f4a10a-4ad7-403d-85aa-6e1c501f5833 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
f79316fc-f799-462c-aa1b-9da0ca30754a | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
858ac9f1-67ea-4d93-b090-1448d44e0922 | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
134b6581-1656-426b-8159-10bae2b929db | Padmount Transformer | 2 | Distribution | 2021-12-08 | 2026-12-07 | Level 3
9e52e1e2-97ec-4ddd-94f0-6eecd1d46ef0 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
d1bc89fd-6369-4743-97c7-3ec1c295fc98 | Junction Enclosure | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
a628d59a-f18b-4ad5-a2de-7b8ef81e545b | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
28ae7b8f-a7fb-44e9-9bdf-bbe9ed769bf2 | Junction Enclosure | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
59dc15a0-980c-47bd-b5be-6d0074d4c738 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2022-12-01 | Level 2
3d4bdd58-28cb-4bc1-8ab5-24a2b45ebda5 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
da876f43-5eca-4b84-b449-92617ba3821e | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
3431efa3-da78-4ad6-a734-9f8b13f762d9 | Padmount Transformer | 2 | Distribution | 2021-12-01 | 2026-11-30 | Level 3
00fb24bf-98fe-4101-8238-883b65fe9137 | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3
f8f2dd25-e607-49f7-bc2a-a2d8ae51067e | Padmount Switch | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3
855a23c1-8179-4082-8ca9-d7faeca7a793 | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3
7e1a7735-c75b-45e0-b5f7-42de67dcb4ad | Padmount Transformer | 2 | Distribution | 2021-11-30 | 2026-11-29 | Level 3
8edfd2d7-e57e-4fe8-90ee-604aa24ac4a4 | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3
c4ece5b2-7e7c-44d0-9cea-67796624633b | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3
ff964d7f-6d24-449c-b315-071cc9b78f34 | Padmount Transformer | 2 | Distribution | 2021-11-29 | 2026-11-28 | Level 3
cc1f8089-8663-4abf-afb9-cb4b43c68fdb | Junction Enclosure | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
0b1f391b-32c2-4f14-92ab-711db48a41b7 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
4e8ef4c2-2c5e-4f71-bcfa-4845bc57d7da | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
97a720ee-e51b-46e1-88ab-58b6bfd08bc3 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
1b253976-9c2d-4270-a34f-813ab66503a0 | Padmount Transformer | 2 | Distribution | 2021-11-24 | 2026-11-23 | Level 3
4da60e94-641b-423a-9dad-5c5c95c6de2f | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3
b36ebc00-f57f-414f-afef-b60fdadd8779 | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3
f2859908-b0c1-49df-921c-ce5a60d0cbad | Padmount Transformer | 2 | Distribution | 2021-11-23 | 2026-11-22 | Level 3
cc61fa4b-8928-4590-a4d1-bd72247967e8 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
36c17e5c-1cc8-421a-a50c-f67bb2d7ec7b | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
4435fc26-76b4-4a0e-a46c-8dcbfbc84136 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
6b3a6260-7875-48dc-a1fd-33bbbb986312 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
e5295df6-40db-4f53-89ce-ac6e73646e07 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
c370e1cd-6580-40e7-91f9-db0eeca2b9ae | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
8d4a8de5-304f-4643-a28a-05dc0f673e86 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
8d2fe2d9-43de-4491-a056-9a97584d3eb4 | Padmount Transformer | 2 | Distribution | 2021-11-22 | 2026-11-21 | Level 3
a12c31c3-9ac8-4131-b5ea-77233fe0b020 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
a040db75-035a-43d4-bec6-c13c38f64046 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
e20eaa67-1091-4ce1-b285-a0e3f1931e75 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
f8615808-3fd3-40bc-9370-4ea665f9e3f3 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
69a59481-aed4-4173-9712-9f08c91585fe | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
304d7afb-bbed-456e-9ae8-f48dcb2304a2 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
95ede16f-c88d-46c4-b310-16cf8354ec48 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
241ab08b-d97b-42a8-a97e-99c77a7d6f79 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2022-11-19 | Level 2
c4928fcc-5509-493e-9b9a-2742942b5c46 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
9b024ff7-2807-44b3-9991-494a15a76622 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2022-11-19 | Level 2
f48ff40f-4ce2-4846-b1ed-ac068f6235e2 | Padmount Transformer | 2 | Distribution | 2021-11-19 | 2026-11-18 | Level 3
c7b2ac54-938e-4cf5-a26d-cd52ae3b1b42 | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3
d9340227-da6e-4f44-bacb-51dceb365b6e | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3
6618f0f8-ebb0-4295-a4c0-6bfc3488c21e | Padmount Transformer | 2 | Distribution | 2021-11-18 | 2026-11-17 | Level 3
d00c121c-2471-4af9-8c17-3a79b2777da5 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
21bc4f74-b34f-45f6-b29e-a2dd5aecd76e | Padmount Switch | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
c094b4dd-1902-47ff-a385-e48c5e994a19 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
cb1e5547-d2dd-4b55-8a09-be2dc3b60a6a | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
70c962d7-6162-4a7f-94d4-ad9df67d6c07 | Padmount Transformer | 2 | Distribution | 2021-11-17 | 2026-11-16 | Level 3
8edd9b0d-26e7-48a1-b66e-fac80750d58b | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
b822fca3-fd4c-47ea-9ddc-9167b560ad51 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
48698bf5-585c-4c57-b8de-ec5aa34a7970 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
154ab2c1-ae69-4121-a8de-166eaa9b3a14 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
70058380-feae-409b-b1e3-47d2ad9e6e77 | Padmount Transformer | 2 | Distribution | 2021-11-16 | 2026-11-15 | Level 3
c556ac8e-a705-4d00-9b78-97b085f2af0f | Padmount Transformer | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3
51ec8f6b-3653-493e-962e-330279c4d004 | Junction Enclosure | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3
9f80bca3-d103-477c-9ec5-a389993ccd73 | Padmount Transformer | 2 | Distribution | 2021-11-15 | 2026-11-14 | Level 3
4abace26-9b92-462c-a909-ec21b40f503a | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
6ff67d57-ab95-4cbc-883b-367c9e4cfc15 | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
6098b3a4-42c1-45d9-a318-c394bae91b4f | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
06e4862b-57b0-4ee6-9c99-899fc65af24b | Padmount Switch | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
3ca8fda8-fcab-4e9c-8950-7876261c927f | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
e361cf1e-7e14-4baf-a0b8-3b432485a2cd | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
161128f5-5beb-464e-b4ed-b0cfb4d63550 | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
2c1a70d9-e6ae-4d34-a193-e6787d5cd9d8 | Padmount Transformer | 2 | Distribution | 2021-11-12 | 2026-11-11 | Level 3
51788ff7-bb37-4122-a2d6-7e4d6b7e172c | Padmount Transformer | 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2
a8ea1ae8-5656-4ce1-8b6f-08c89190871f | Padmount Transformer | 2 | Distribution | 2021-11-10 | 2022-11-10 | Level 2
99265580-7cd9-4c07-b772-80aea4f639d1 | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3
95541ad0-168f-41ca-bcb2-d0b547cfbacc | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3
d56b7971-beb4-49a9-8dfc-cc670246da33 | Padmount Transformer | 2 | Distribution | 2021-11-08 | 2026-11-07 | Level 3
56359f14-9ac2-4f85-9075-d22b8ecaab76 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
97e9c61d-d22e-4545-9191-e249545e43e4 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
f3353016-ac9f-4637-a0bc-487684cb63de | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
d664a045-7015-4ed1-b912-f92646a4c65b | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
9a921048-7e6f-4db6-9494-62177420aec9 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
b19740c6-82b3-4456-bc27-4dbc429cd91e | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
25f7629f-7d89-48d8-8852-a15c4657cc3f | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
fd2d7187-2411-42ed-81b8-58a4d3d71abb | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
319c29e1-03ea-4d14-8610-01d22d6f36a5 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
fd37a7ff-ec5c-49d6-b940-190d7817b22f | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
bd07ebc9-d428-4687-95c6-9e045b4fadb3 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
c2889f05-4510-4bf6-ab9b-3a4b66be74a3 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
00dc6f15-9045-4a19-93be-ce9de0c68255 | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
719dbd3b-d751-45e9-87ab-af0d9109e15b | Padmount Switch | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
90c8650f-41e4-41aa-822c-fcf8ee06143a | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
d9d5b7f0-c1a6-493e-b2c6-e022dec25fd8 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
d33e239c-4582-4f45-bf1c-f22a3f9c29b5 | Padmount Transformer | 2 | Distribution | 2021-11-07 | 2026-11-06 | Level 3
f36d7db6-0938-472d-b286-e7d76932d14d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
f9784fb5-d97f-44e6-aea9-2072689fe04d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
3fd61d92-6f63-4b37-ba9a-b1b09c5ce596 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
27c06025-52ce-4196-b682-3a241787ae85 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
e974d547-3d45-4077-a1ef-ecea5dcef47d | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
bba9a32a-bb17-416c-aa4a-9af80ebfac5f | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
bed65d66-1f64-4025-9500-e2f2ba549cc3 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
9affb1e5-9dbb-418c-920a-daeb0018f39e | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
69241977-9715-4fec-ad36-d67f66b5f906 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
6c3a4663-78f2-4816-81b3-95a91e27fb16 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
b5057e47-e617-43af-a3cf-91b4802b90e5 | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
74c0b6b5-b8d2-40a1-85f9-4c74c64bbdd4 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
1875650d-24c7-4293-8782-8c6e3824b99f | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
2792c957-ee85-4f28-bab0-56c2e206c72b | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
f6c9f6e3-df6c-4084-8b5e-a695bebdf92a | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
66e0e874-4e13-4d2f-a3ec-f2e723fc496e | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
2dd09a9c-c660-4e43-8e11-029d8ae9e48b | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
18fcb6ea-fd22-445b-b0b4-e1c64f157c4d | Padmount Switch | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
9f401988-789d-4f66-80a9-765293f412af | Padmount Switch | 2 | Distribution | 2021-11-06 | 2022-11-06 | Level 2
b9004984-ec78-4876-8754-7a73adee4943 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2021-11-08 | Level 1
7ad44b3b-d63c-4695-a1ef-4f86f9eadee0 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
46d022c9-680e-4e20-8f99-55002d0e7284 | Padmount Switch | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
577437d5-0a47-4e9c-a242-6670b40b3cfc | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
cb93ed30-9033-443e-93f2-3bb708c9b8ea | Padmount Transformer | 2 | Distribution | 2021-11-06 | 2026-11-05 | Level 3
73b7c453-abd5-4af7-9ffc-7b8156c492be | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
8a7c0559-9c60-453e-9fc8-7530b67dce88 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
a0ea73a0-5f94-49b8-a85c-31731e089641 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
fd0b4574-5ba1-4562-b59f-68fb630ea61c | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
341f0cc8-8c7f-4c87-8032-1f3a48f11e10 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
2dd3e7a8-fdf4-4d1e-8536-f017c5ceb505 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
c0f1ca20-bbdf-4aa0-b0c9-1cb02cf1ed0a | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
e23e8807-3a89-4db3-8790-9130562e7746 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
a5386803-b15c-4a6f-bf05-638df8393114 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
1f9260c7-52f3-4899-bb23-d50f0f10e731 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
fe41d1c6-0e56-47e9-a73c-3040e69b2502 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
c5b9339d-41e8-44b3-80bc-90d403e4634c | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
a75e9ea7-3731-4bac-b931-04e78db08cf7 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
e51f68ea-cec8-4452-a21a-c62a1982412f | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
e2bb6d47-6f79-4d3c-ab96-0820c511eb40 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
f889f99b-8348-4eae-9e52-0725d6ac6b52 | Padmount Switch | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
4c547298-e4bd-485b-917b-51011cfbd4a1 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
c3a8e1af-bae3-4e0b-a94a-a90a8b1f5883 | Padmount Transformer | 2 | Distribution | 2021-11-05 | 2026-11-04 | Level 3
bebc84c7-06b8-40db-bbe1-f514f12a8092 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
fb3f036c-8876-42ba-ba67-aed8dbd22c2f | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
a0667eed-d8c1-4c75-b815-1d3ec28802f6 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
70b2142d-8af5-4574-91a6-0d128404f305 | Regulator | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
3f89810f-aec4-4c11-9464-bba99e81c671 | REGULATOR | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
f7fb82af-30e1-4070-aced-8e7e8b00fabd | Regulator | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
64d0c6e2-4180-4485-b091-665f21f54a1d | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
4cf051ed-03c2-4b86-93ad-d36824c5d1b7 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
23cfefa2-b7ac-4d1d-a846-ea7217718faa | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
0889c0ab-af53-4b52-966b-c7966de6c95e | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
93d7140b-c38d-4544-8943-d6f10f81c0d1 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
2764ddfa-0b63-4c37-8cc2-a6629c2dd847 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
2aac781f-1042-4840-8cf2-cece4975881b | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
ebfa4c12-246b-49b1-9f0f-3763bc8403ec | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
2c2b9acc-bc63-4d8c-a8eb-5612c880af46 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
f7a05631-3d06-42f7-886d-22c6ce62d088 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
3034fb3c-80d5-46f5-b837-b356ff07d96a | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
627e2ed8-2b7b-4ad5-9592-b2b9b1da2e03 | Padmount Transformer | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
663be561-e47d-4a4a-a947-9a6ed3226a13 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
62520226-2d13-44b5-98c4-39e513502843 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
706064f3-6b86-46b4-a599-35b72f63b403 | Padmount Switch | 2 | Distribution | 2021-11-04 | 2026-11-03 | Level 3
49820070-79e5-40a8-bf91-1519dd8ce439 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
08424585-7ba5-4cff-b92e-801dd5235785 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
202306af-3d29-4b76-9fc9-c92977c5c6fc | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
a01c768e-377a-42fd-9b04-e254799656e7 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
bc562ff2-9873-4067-beb1-2f2520203035 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
7d7a2c81-2e1f-444f-b157-e14dfcb1a344 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
a226c54b-8224-45f2-a698-f0c54751d210 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
ea54d99a-af5a-4ee7-b2af-fb88850a308c | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
a16e8f1a-4a74-44d7-aac1-cd8b0e3e9a9f | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
0d9ba3c0-2cbc-4ac0-888c-67a632acd0e0 | Padmount Switch | 2 | Distribution | 2021-11-02 | 2022-11-02 | Level 2
b355d795-79e3-442c-8cf8-b69dfafbe192 | Padmount Switch | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
2a17d956-d1d9-4688-8a05-e6366d70043f | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
34c4977c-6c47-4c0a-98a3-d647a63042a9 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
0fbb8efd-795b-47a9-844a-41c33711be26 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
2bcfa3c7-e207-4b2a-9fdb-162a328ebb25 | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
40754894-3c03-4575-bdae-b16e8eda3e1d | Padmount Transformer | 2 | Distribution | 2021-11-02 | 2026-11-01 | Level 3
dda5488c-0c0e-422f-bdb9-d392e60854ca | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
687bf21f-b12c-48bf-9870-c8de1c197818 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
a06a1ad2-9562-4b09-8f02-4a154d17f877 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
d6b82dd1-a08b-4b83-82a5-d2bd032df7d2 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
69d7491f-b958-4eb5-9cd1-5435458de94c | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
f752fed6-7947-407b-aaf2-bdd3a0357ef5 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
860516a4-f107-40dc-8538-e90fa6a756de | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
df7688d4-8313-4168-b7bf-a87b95666571 | Padmount Transformer | 0 | Distribution | 2021-11-01 | 2022-11-01 | Level 2
6f28b315-0e58-4612-ad5a-2a3853b04416 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
222913d1-64b2-4570-b54a-c92d197894b9 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
8eb42b9e-511f-4868-89ae-9d12db9fe120 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
cc851e0e-8d95-479b-a5a9-3d77768ae1be | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
1f47a02a-b72a-4272-8e35-70c46eca8481 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2
3759326a-470d-4c7d-8311-25a0e44e0f4e | Million riser with bridge switches | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
667e43bc-507a-4413-8557-353f4a4898d3 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2022-11-01 | Level 2
aeeb16c4-7b48-4227-8f43-0d4eee62ea2c | Other (Describe) | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
aaf28071-aeea-4c96-99df-6eab44cc2337 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
9f691f93-53a5-43e5-b44b-baf83c2ef448 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
c8cc97f7-4d0f-448c-aebc-cebb7276f32b | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
b50b99a7-fb00-4311-a1d9-a3f89d7864d6 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3 |  | 0:00 | 0:00
8a336278-04fd-44fa-9ed4-c5d71dde4123 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
e03311d5-420b-422e-a9ab-3d0fc1e77fda | Million dip pole with bridge switches | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
30e9ec4f-8a1b-4d9e-8532-c854b4e6b4bd | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
576f7b80-f2d2-4731-be05-70a5d29b13e9 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
2194b38e-ecc9-42e7-ba81-98882a6802c5 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
263d957b-b8ec-4459-99d4-708c8f4cb8e5 | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
899bc20c-4cb4-4be1-bf60-bc086ba5793b | Padmount Transformer | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
6f123e8a-3cb2-41b9-aa62-e23a93ef5b19 | Padmount Switch | 2 | Distribution | 2021-11-01 | 2026-10-31 | Level 3
289c8014-190f-47e9-ac2d-755d631fc1a4 | Padmount Switch | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
cae5cd38-c6c4-455d-8ecf-babbbe45d76b | Padmount Switch | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
b95c5c5b-4dfb-4aa2-8956-8bcabdd6a8b5 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
1662a1cd-5ceb-49b1-93fc-a780bc658dbf | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
6c746ba8-da7e-4ad8-8790-70a1250c36d4 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
ddcb61f1-817e-4f30-a5eb-1399cdeb7f15 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
516d4ecf-2e7f-47ec-8b9e-cb0e6172279a | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
def94314-7bf1-4d50-a301-c1377311a40a | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
60e1dc24-1694-476a-8035-f63d08c7a5de | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2022-10-29 | Level 2
d3de8ebe-423f-4820-9355-20ab83160314 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
ea278f9c-df96-4c88-90ab-79fd5f703f23 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
d9bd5f86-2789-47d1-95f2-8ef4e7546ecd | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
705954ad-496e-4cc0-b6c7-10e0d1e5534f | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
3a9e766f-4355-48a6-a98c-26413c184e08 | Padmount Transformer | 2 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
c76a61c9-f3f7-47dd-9a91-409abc408bb0 | Padmount Transformer | 3 | Distribution | 2021-10-29 | 2026-10-28 | Level 3
70475f39-c271-4181-b6c6-8f85749d583b | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2
69c5f10d-8eff-470f-aedd-ab4db63e9967 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2
2daa0614-4553-43b3-9a31-051a0e16b041 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2
b9ea6852-7497-44da-8f8b-d77c1b943033 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2
791e201f-de2a-4d61-9a7c-8117d626cef5 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
67eacf97-c032-4b3d-a1bd-be19fb824b78 | Subsurface Transformer | 2 | Distribution | 2021-10-28 | 2022-10-28 | Level 2
a9cbf5a1-fb57-4c92-8e76-664dcb70e241 | Padmount Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
a9ae1d94-323b-4985-b0a8-208d43683390 | Padmount Transformer | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
7cfdedad-72e3-449c-8de1-0af0106c75e2 | Padmount Switch | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
b8c207f0-341f-45b2-a5dc-2f565c61c815 | Padmount Switch | 2 | Distribution | 2021-10-28 | 2026-10-27 | Level 3
5ea41cff-1efb-4996-827b-ec22ec35b5ec | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
a28afb3c-6a47-4909-8bcb-d96e2a66fba6 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
2a653d8b-0cb8-4cc2-a9d0-0b7e137608ce | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
d2b24d0b-51f5-4e33-ab76-5c8916cda60f | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
731c9e68-6eaf-4025-83ec-c99eea7335fe | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
173bbc1f-e2dd-49a0-9434-f4ff8d4befc5 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
09525167-8322-4e8a-88b5-ad0c01ed99a7 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
8dc31024-acc9-43c3-be5a-581331739be3 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
6dd0c98a-e008-4d06-96b7-10ccc7cd1f82 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
37aa2543-c5a9-4355-94de-15de40e25801 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
fecd6ad9-8d2a-45fc-9d21-1e135817ab51 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
d0335cd1-ed87-4caf-b00a-b8edbb0f7ce5 | Subsurface Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
6df7862d-1a18-4493-8d17-5070bbd3807a | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
4edde5ec-f06a-4d0d-a9e3-2ad0a2a16f9f | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
d186e017-9afb-4ddb-8520-c7cbcdf14db2 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
b557800e-b205-4891-92b2-d173ce3c1667 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
b97cc0c4-568a-4b1b-83cb-681dffc0ccc6 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
1226f38f-6372-4b38-8ebf-db2acc652f06 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
257cace0-d5f5-4006-9363-9058a66e4ceb | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
f3f04387-269e-4300-8002-5ab516fc4df7 | Padmount Switch | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
9d9bcdd6-28f2-43a1-a9ed-07e9161713d6 | Padmount Transformer | 2 | Distribution | 2021-10-27 | 2026-10-26 | Level 3
0223c440-79de-4cc1-b6f3-3b99fbb4e611 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2022-10-26 | Level 2
896c3455-6340-4bea-ba2c-3a2ebd063f10 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3
698e8fb3-e5b1-42f4-95fc-055bb01c1e24 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3
9593a78c-fcaa-4dfd-be17-45943eb14fb0 | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3
f833ecdf-bd46-4695-82f5-8a499459153b | Padmount Transformer | 2 | Distribution | 2021-10-26 | 2026-10-25 | Level 3
c03ddda7-3e08-4c55-b886-6f6d4d377ee5 | Padmount Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
64125ed6-bf79-4bd5-b24b-cfae85f50f67 | Vault/Box | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
26ee2dea-6b75-4afe-8159-a40882cf5d0b | Vault/Box | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
2f502134-ee12-46db-b322-bd84040b8394 | Subsurface Transformer | 0 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
f9c08220-3b95-456c-8660-2b98d8ac2897 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
ec44ca4f-a2ad-4dd4-83b0-03f3766314aa | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
6f28aa38-21b4-4d1c-8e29-1f09c4daf840 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
59dcf11c-5afa-4e0f-b760-1f9f74e4ee29 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
7da367c6-0a7d-4273-975f-8fd3299f27b3 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
948a5d2d-164b-4e9b-85a9-87574ea00e73 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
f3243f21-b472-48aa-b895-5759dc0954e3 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
067e54ae-6f41-4593-8219-f4b6caefbc14 | Subsurface Transformer | 2 | Distribution | 2021-10-22 | 2026-10-21 | Level 3
168468f5-1a76-4702-a32c-68e40c8d4997 | Padmount Transformer | 2 | Distribution | 2021-10-22 | 2022-10-22 | Level 2
f6f76c88-b3ea-48e9-9aba-271fdbdd66b4 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
b7b8c16d-993d-44d6-85ca-5786b2d08d54 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
59c289e0-f8e6-4231-94cf-a84fb953f7d4 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
3510d1f5-b55c-4026-a699-48009589fd8c | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
e144c5c7-892b-4b33-94db-1c202faaefee | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
5419f188-597b-4f87-ac2a-f85ca3a0088e | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
3a9dcaf6-0d0f-4631-849c-6da5b3fd2ad4 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
e6ec1743-2d0c-4896-92ab-9b58d88d6b77 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
4ae352cf-3849-433b-850d-bf137ac3614f | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
16d604cb-d4b6-4555-97a7-f540f28222e2 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
178690c6-20b4-4625-b0d2-ad7bb32b23f3 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
69b5b637-59f6-482d-944e-2f451b5b0397 | Subsurface Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
7ed4bb36-60ba-423d-995c-cea3c157ab56 | Subsurface Transformer | 0 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
75ea10ca-c63c-4e90-8a6b-97d7fb348fab | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
282a7f03-51f0-4639-b6a4-fb5f21735e46 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
34d38710-c291-423f-bc5a-053b2f4338a4 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
3607a411-9506-4dd9-bde5-6d417a28f4a0 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
dfbf6508-3bc0-42d2-8ae7-1bcdab2f7041 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
e9026147-f9d7-44a6-910e-71e0489624aa | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
208033da-57b1-4f97-8a6d-4f91d396e108 | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
042e8926-2c53-44bd-b440-5088822e1078 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
813bcc20-84da-4843-b1fc-2a810be994ec | Vault/Box | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
a09553e3-7e4a-480e-837a-0161a44610c7 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
e3a8ee9e-1e0f-4bfe-b2e3-4587330ca0d2 | Padmount Transformer | 2 | Distribution | 2021-10-21 | 2026-10-20 | Level 3
700098f9-95c1-4d46-bb5b-a0441f4ab144 | Subsurface Transformer | 2 | Distribution | 2021-10-20 | 2026-10-19 | Level 3
0f48869a-73cd-4dd0-a399-20e4da546ec1 | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3
18e79d39-bc5c-4ba1-96d7-51eac8aff3d4 | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3
c8f7c641-dc69-428d-aa03-7d10624ad54d | Subsurface Transformer | 0 | Distribution | 2021-10-20 | 2026-10-19 | Level 3
3c09ec68-ea4f-405a-a972-25afcdd34695 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
c7590ca7-0f57-463e-8661-044b781c6280 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
38b45260-c054-41ff-b95a-4f5841ef6436 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
af7fac7a-e34e-4471-94e0-851510639e15 | Subsurface Transformer | 0 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
c3e666c3-5df2-4e96-b060-6774d1cd4019 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
5193025a-5b67-4cc4-8604-8e93fc8e2d81 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
ecb03a07-2432-4e2c-a9f8-30195c936947 | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2026-10-18 | Level 3
9ad01a60-27ea-4f2d-9b84-f99bc5076aca | Subsurface Transformer | 2 | Distribution | 2021-10-19 | 2022-10-19 | Level 2
c124d0af-8ed4-47b6-a135-dcf5e92c1360 | Pole | 2 | Distribution | 2021-07-09 | 2026-07-08 | Level 3
34e3cfc8-e4d8-4bb8-8f9b-d73583d99c8d | Pole | 2 | Distribution | 2021-07-09 | 2026-07-08 | Level 3
fcf297d2-10a7-4bb0-977e-a28aa527aa50 | Pole | 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3
4a4474af-1995-41b4-9d01-f9405889bb78 | Pole | 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3
14219f68-abc9-47d6-9c31-f787b6450796 | Pole | 2 | Distribution | 2021-07-08 | 2026-07-07 | Level 3
1c3d0e1c-ba90-461d-b685-dce35d0cef47 | Pole | 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3
af972b85-ef7e-4fab-b62d-63e311958fa5 | Pole | 2 | Distribution | 2021-07-07 | 2026-07-06 | Level 3
14ee7c33-3957-46b1-8042-10df52c595c2 | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3
0e4e6094-7cc0-4cd4-8c93-c623e394cfd3 | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3
5b7c59f5-2241-4d5a-a61f-44619dc28cea | Pole | 2 | Distribution | 2021-07-06 | 2026-07-05 | Level 3
2d0d5ff1-e53c-49b7-91a6-fa1a7d1a07cd | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3
88170c15-148b-49b1-9483-32f69fb49d71 | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3
7618aadf-07d7-4222-a267-f7f7d9285122 | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3
fc642943-4c43-4530-9e1c-3507c790d03b | Pole | 2 | Distribution | 2021-06-24 | 2026-06-23 | Level 3
cb078fce-4181-4170-97d2-3d28a6c8a8ef | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3
5ea583c9-58b8-4b65-84c7-4592c200aa38 | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3
8c12109f-5e1c-4929-83ef-0326996a47d5 | Pole | 2 | Distribution | 2021-06-22 | 2026-06-21 | Level 3
839e7ee8-7c40-4c80-9f50-87d0160630ea | Pole | 2 | Transmission | 2021-06-22 | 2026-06-21 | Level 3
2ed40ae8-7ecb-4bc3-af77-9ab8c0527856 | Pole | 2 | Distribution | 2021-06-21 | 2022-06-21 | Level 2
05fa339a-1700-4f68-87e0-aab5efa1b46f | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
ba196846-799d-4408-ad22-d2bbc1452d0a | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
e6df7adf-b39b-4a70-a115-5e85cea4503d | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
d779e54a-a832-447f-b43e-c84d7b64f4aa | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
c5a76494-d8de-4329-b5fc-812a5fd7d9dc | Pole | 2 | Distribution | 2021-06-16 | 2026-06-15 | Level 3
63975c28-5e39-4be5-9e5a-366944612499 | Pole | 2 | Distribution | 2021-06-14 | 2026-06-13 | Level 3
8c3a30b8-c7e5-4e1f-b099-b21d51181055 | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3
8fdc8965-49d7-4753-bc91-051ed7b7cd59 | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3
cc953013-ddf2-4b47-b420-359eb93f1ffc | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3
126788a7-aa86-4ec6-95a8-5380489b1b7c | Pole | 2 | Distribution | 2021-06-04 | 2026-06-03 | Level 3
18a40d05-90fd-445f-819c-db748d984211 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3
5ab2c315-aff3-4fc1-af2b-b6ebd77be984 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3
d92a770c-1c52-415f-b5f0-faca8fc6011f | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3
7c56fffb-b9fe-4224-9fbf-f1c6a93c2bb8 | Pole | 2 | Distribution | 2021-06-03 | 2026-06-02 | Level 3
c2c4fba6-8be8-4156-9ceb-38c84210ac45 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3
b36ffc38-4d5e-4250-a769-c9e388fec444 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3
37056221-fe6c-4de8-b617-a94feca8a471 | Pole | 2 | Distribution | 2021-05-06 | 2026-05-05 | Level 3
296bef50-d0da-4c12-b265-17e221248a61 | Pole | 2 | Distribution | 2021-05-05 | 2026-05-04 | Level 3
fb47b541-12d0-41ad-a428-5f7fc375958b | Pole | 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3
7ebd0501-4c69-46c3-a9b3-fc7c3005632f | Pole | 2 | Distribution | 2021-05-04 | 2026-05-03 | Level 3
c06e0d38-1814-494a-b657-b2e5dfaf63db | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3
2921d876-d683-4510-ae5b-fbab0913a353 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3
0f52bc9a-dedb-480d-9a2f-8be6e92238d4 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3
01367fc4-8fc5-47d1-9109-edf3e1a5e4e4 | Pole | 2 | Distribution | 2021-05-03 | 2026-05-02 | Level 3
bf71822f-1fe7-4f1c-beb4-3cd0f71b0a31 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
ba3c37c4-5184-4bab-8106-de6da6799464 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
a829abaf-bbb8-4fe5-9c0e-f80fe4af51b6 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
94a68f8e-9954-4fea-a59d-acb8a0b712fb | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
8e6b4499-3622-4999-a502-77eb608cd385 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
bb7d72a0-99f9-4841-b25c-90e8fd0e33f2 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
b2b532f3-0553-447e-a66d-3b730849b277 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
a91e7fd3-36a4-4083-857a-ad2a76aad36f | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
46c6109a-3376-435a-85fb-202def1b4017 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
5129bbb2-6cf7-4d34-aa5a-3b3795c0b3ce | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
0061582a-773f-43b5-8863-245bc0d08fa2 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
18b08b8c-1201-4f08-a90c-d91cab8251f1 | Pole | 2 | Distribution | 2021-04-30 | 2026-04-29 | Level 3
18df15b7-dbcb-4eca-84d1-2be331080052 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
3ffb3f8e-f0c3-4551-907e-66e478986f1a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
2a07577f-b3f4-4ce8-ae72-5d1ad47185d9 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
22f64a95-b562-44aa-9537-65f936ce9654 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
af57562b-db22-48aa-9b36-d89583ac5f7e | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
bec5e9e1-c8c5-46a8-96b7-ca73a130722b | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
7809daac-a066-4b4c-80a6-50fef4685c4f | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
fb58cdeb-97b8-478c-9abd-e449ac77695a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
e7bafe57-13cd-45e5-aba3-70bc50025290 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
e30160df-4c83-49c6-9980-367734f7c1fe | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
f5292a05-5d6f-4fd4-b118-08a7fc08a5ac | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
0c88dec1-27d0-44a2-9cac-edc4127bf2d1 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
1e9d1d0a-bb27-469e-b595-5ff300ff273a | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
35ce2f0d-a464-4c34-b1e8-086b90711db3 | Pole | 2 | Distribution | 2021-04-29 | 2026-04-28 | Level 3
3a34d26c-1b83-488e-b0db-cf3fcdcec3bf | Pole | 2 | Distribution | 2021-04-28 | 2026-04-27 | Level 3
e7620f4c-5dde-4833-9dc3-0f86ba11b22d | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
a73fee10-0e9d-47ba-937a-3f9687900e87 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
8cf29a3a-1bcb-45d2-80e1-b792ad8fc960 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
be3a6610-8ad3-4ae2-9c39-2372d418b8eb | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
21cf93c0-8456-4c78-8f2f-da402b654f02 | Pole | 2 | Distribution | 2021-01-07 | 2026-01-06 | Level 3
1132b68c-088b-41ba-a207-4b380e802cbd | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
330852cd-9aae-48df-943e-96a15c57a544 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
638d596e-8576-4ba0-876d-6c5e126ca05b | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
6bbfbf2e-0990-432c-9763-3453ed37c7ed | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
a21b8b30-d55d-471e-9127-7b6faed0a8f8 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
31e90cb5-ce05-431d-92da-dce023a6746f | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
9deeeaf6-b96b-42bb-ad8d-0556629dcd01 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
d0de9407-1752-4628-a809-8de834351d41 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
d01164f6-447f-4225-b969-e271db983325 | Pole | 2 | Distribution | 2020-12-18 | 2025-12-17 | Level 3
e01786a2-1cbf-4fe9-a8a6-882b6f59dba2 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
dcd9d11c-fca7-4ebc-b570-4d34ef118141 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
42beeeb4-6d9f-45a3-8787-c8088dbace9d | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
3d7daa0b-97c7-4848-b2f3-7c1161854d38 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
1dfba368-0f8b-4bc7-9ea6-13bef4ed3455 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
059cd3f8-3f05-4f08-8ac0-2007b0349c85 | Pole | 2 | Distribution | 2020-12-17 | 2025-12-16 | Level 3
d311405d-07ff-4d02-a01a-9aeafdd5e2ee | Pole | 2 | Transmission | 2020-12-16 | 2025-12-15 | Level 3
ce355eb1-8741-4b1e-aa45-4559704fbef4 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
cd5019ab-cb16-4734-bbdd-2b9627301993 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
f05649f1-0061-4aa5-a97f-37b282cfe320 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
a6f42990-a933-4e30-93da-5bbe8b784519 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
a757e3f2-eeab-4dd3-b4d1-975da11a09a9 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
c8213d31-66e3-4e5e-9621-c7d7695d96e2 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
51ed5513-539c-43e4-978d-a60c01ada391 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
05abd4a0-3ad4-4c26-9ab6-96c44e02f66d | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
6f2768e7-417e-436d-a182-1bede09d23b1 | Pole | 2 | Distribution | 2020-12-14 | 2025-12-13 | Level 3
6cdb0dd6-58bb-4a1b-879e-c8c92d1f03b9 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
74da15fb-1dd5-4e5a-b57b-6230b4e7212b | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
41c301ca-f8da-4262-a899-f0e928c5c567 | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3
4006a461-8e7b-436a-9f94-3b80ffb7368d | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
3fa3edb9-0223-4c2f-bf5c-93a4d1912192 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
36c24442-95a7-46d7-b483-e43348955130 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
37e13b96-c9a0-4a56-b9cd-ca210701994d | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3
10a46bdc-ff45-4cfb-b382-d32b53018fa3 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
52a264de-d18c-4886-b22e-9e9bdbb46bf3 | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3
a2870148-6a38-491c-a2b3-c69849e44dfd | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3
c67c4188-1292-440e-bd6a-91d3a40eeeb1 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
af45b8e6-2d8b-420a-ac23-d86959b0f453 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
89706162-b9c4-4b79-b1b8-3a5769d6ca25 | Pole | 2 | Transmission | 2020-12-11 | 2025-12-10 | Level 3
8203fb0f-5e11-48ba-959b-050786096a80 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
d2a06795-a4b5-4e0e-99e1-f6ba8276f609 | Pole | 2 | Distribution | 2020-12-11 | 2025-12-10 | Level 3
857011e7-17e7-4989-b5f7-d8855b094072 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
8a7c6375-a2f8-47f1-b34e-fbf98195de7d | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
9e1c0331-0913-481a-b7f0-c3e55090b069 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
70d06477-1cdf-4e60-a521-7aaa6ae06aa6 | Pole | 2 | Transmission | 2020-11-03 | 2021-11-03 | Level 2 |  | 0:00 | 0:00 |  | Arm rolled
fc508bcb-835e-47fb-98fd-b217a0253225 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
fd7a2ddb-6dbe-478a-bfbe-09e4977c6baa | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
13e66b18-4646-4c68-ba09-2ecfbeea5295 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
18b83043-c444-4081-92e3-17f2e0fcc1ce | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
16c4fbfc-1b2d-4e48-9411-33aa38fd24fe | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
30188ccc-6c02-42a6-9593-d4bfab541819 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
242938d9-ea14-48f9-a871-4b0fe2c56ce1 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
3f0821eb-0661-41e1-beb0-ab8f2328c4b3 | Pole | 2 | Distribution | 2020-11-03 | 2021-11-03 | Level 2
73c7aa1d-f3d3-4858-b5a4-7a30e63398cf | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
6fa3379f-28d8-47f3-9075-5dcee0021350 | Pole | 2 | Distribution | 2020-11-03 | 2025-11-02 | Level 3
5aa1f991-42e3-49f9-a448-314cacfe0558 | Pole | 2 | Transmission | 2020-11-03 | 2025-11-02 | Level 3
72f060b6-aee7-4276-97e9-17a602834e7d | Pole | 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
4cbd9b67-e042-4eb6-acad-60eebb0ff06d | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
2ac66b2f-e929-4ae6-a6ae-2fcdb3a43704 | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
7f2ff55a-d4b4-467c-8390-8cde4f3d9ad9 | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
b58728be-315c-4702-b333-4650a1252bd1 | Pole | 2 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
fa93d64e-e449-40b9-a04c-47c9e3a5d44a | Pole | 0 | Distribution | 2020-11-02 | 2025-11-01 | Level 3
fa3a6a3f-da62-49f4-8cb0-b8cffda0ee3e | Pole | 0 | Distribution | 2020-11-02 | 2021-11-02 | Level 2
68b79d80-623b-415a-bb8f-e39003edfc9e | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
97da06a5-91c6-4200-99a3-80429c15eb49 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
2d05026f-d6f7-424e-be09-0a53a38b5fbe | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
95ddb1f1-d32d-4242-8aa4-4fe7898c177e | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
6328891d-e2d5-47e8-9fce-5ad49d6939a9 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
4a22d034-af5a-484a-80d0-d56cab2fc52a | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
045821c8-1666-49a5-a4bf-e757974e75ae | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
31efd5c0-35aa-432b-ba18-725735bb42af | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
35da62bb-89f0-4555-8c23-d6e82a91cd79 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
3b8c4552-f17b-417f-8b5e-b5134f299bd7 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
7451306b-464f-451e-a308-b8a879e2f521 | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
0fd03e2b-6cfc-4c28-82b7-04dafb7755fb | Pole | 2 | Distribution | 2020-10-31 | 2025-10-30 | Level 3
259f747d-cab9-450d-a73c-bc97decc887f | Pole | 2 | Distribution | 2020-10-31 | 2021-10-31 | Level 2
0202af24-c134-487b-93f8-d56b5b5dff89 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
23921928-dd79-4922-828e-4525249c2020 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
576da134-1eab-4915-905d-2ee96edcd332 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
0e8605ca-cf6e-4082-9e78-dc3b6ed24db3 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
8b3644d2-6861-496a-8cc9-c17c552e9baf | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
5c28d58c-64ff-457b-a3af-be2a874f5acc | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
f4685233-5388-4328-8e88-53d5e2f87c01 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
7d8c80a0-cf74-4ab2-8108-1fbd84f60766 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
c66cebb7-58b5-460b-86ad-1da8d1f743c7 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
23624916-6017-4757-8054-d2a71d0d1e7d | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
0f469cfe-371a-4e0f-b808-0eaae1d8f827 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
b75ad0ca-e0a0-469f-b3d5-f729f419cee1 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
7d75c011-f9e8-460f-b2dd-782b7ab47cb7 | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
ab75932b-2c78-43d1-902b-3cbf6c81e4a7 | Pole | 0 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
bc5e5133-99a4-4e44-b7c4-6223673422eb | Pole | 2 | Distribution | 2020-10-24 | 2025-10-23 | Level 3
e36a2c59-9285-4e5b-9b41-916363ade87f | Pole | 0 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
0c05e7be-3d32-4e62-bfb2-a81a1d2c3991 | Pole | 0 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
a78d19da-acfd-4a33-b7c6-dc81e657c7c4 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
2db263e1-28d3-4ecb-8bd7-780d6408c6d2 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
de3247ce-f59a-4b1d-ac4f-2b9c288080fc | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
66805d0e-a7e2-41a7-af28-4c5dcf500c10 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
f43e52f3-c885-4794-b45a-fdb4db053711 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
76d9e0bb-037c-431c-b168-cf278af9d51f | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
52b71227-2f78-4064-9510-0a1d4214a2c1 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
fc630e9c-6c65-4728-95c6-a6625fb3a494 | Pole | 2 | Distribution | 2020-10-17 | 2025-10-16 | Level 3
05c645a9-cd34-4c5f-b0bb-a00358e1f839 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
08fe1380-7898-442a-8092-0642125d5e61 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
08112856-2b9d-4f15-a1c0-8b39d1bb64ee | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
70a02f91-77e8-416b-90c8-37f28f13f796 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
783d18df-429c-42cf-bfda-60aa13b6455a | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
6a01a572-5309-4914-93d6-db110c29b828 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
3bf898ac-e17e-4a42-a0de-6dd4c2b373f2 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
3f357e24-71d9-4c8c-a25b-09b8b09f7499 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
409a1c2b-44ab-4c49-a6dc-08e5305f3b50 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
464a53fb-0379-4377-a9ba-2124d4b51c1c | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
36ec1802-a5b0-4fcc-a0cc-e7ac3781cf33 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
24b66aa1-e886-4701-bd93-f52c2188c94e | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
ff3ce20a-11c1-493c-9066-67568265e51c | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
8ed7a970-5ab6-47e2-bce3-59bf35b8c592 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
937bceaa-08e0-47a3-9008-73ec1e532314 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
d48e861f-26bf-48ee-a4b5-e77f74542ca6 | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
ce44f22d-89fb-452c-b5e3-4cdae58eb01a | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
d15114f8-3dfd-4ad3-bcdf-d93f58ab86ca | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
c4794c18-ff10-4f09-8903-663680283b1c | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
aff9bcb2-33fc-4acd-8893-e768bb1398dc | Pole | 0 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
8bea36d5-da4e-42a0-8afc-4ff8dd8dd1f0 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
b240550f-360f-47c9-bcfa-7c6639d619e4 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
9111d2f5-b08b-410b-8aa2-fbf3068e7107 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
a6e72fd3-7687-4b37-88fd-607cf2eb3de2 | Pole | 2 | Distribution | 2020-10-04 | 2025-10-03 | Level 3
8dcef529-717f-4101-afb2-09d6a7cfcb27 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
8a6fdd68-4c2e-4d42-9a43-1f56bde74c66 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
b4467d20-79ec-4adf-a2b9-7766baa4b143 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
ac42d891-175e-4b53-824b-afdc9ba92ff7 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
aad5284f-cf48-4794-a4da-2592de82e896 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
aa8e7ff1-c981-49e2-97eb-4e2577832c45 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
be28be52-f91f-4fea-b065-be3ae65a7ba3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
cd19da15-d082-4204-9b1d-35b3a4d24fc6 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
c8b7d356-301c-43dd-aa43-95ef651f88d6 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
f8316d8a-d2de-4fed-82cc-31ced95672a1 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
eef020f1-e468-4325-a884-d2586f2c1dc3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
279f3360-6ee1-4438-9260-b6dea217540b | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
2ba2bcfc-60e3-455a-bdd3-3051b79fd991 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
2f5c0bb0-1200-406e-a1cb-3bcef4c7a133 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
480c2983-675a-41c6-8f4d-7a6e449464a2 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
49d3a1ce-fb6b-4e95-b78a-cabeda51a5f0 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
3bb8cfcf-1147-47a1-bb53-747e552dcbca | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
3a5b00d9-84c5-408a-b2d2-176951d3dee3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
6752692a-257c-4fb8-8c24-82ec0b574362 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
70823a40-febe-4108-8ad9-70d057ce54d9 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
78122c3c-e98d-4114-8391-152c3079ccea | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
71446ff4-9909-4f67-b0d9-d8865feba4a9 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
59accfff-a725-4fe4-873e-d1b51220c0fa | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
4fbe3f1c-1637-4f9d-8445-4b54b34c90db | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
5c6ab85f-c7d6-488f-bbf0-fa2a7d6aa742 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
0822043e-147c-4566-9214-9ab66abbbe1f | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
171dae0b-a1e1-4c1c-9930-83cbf65851a3 | Pole | 2 | Distribution | 2020-10-03 | 2025-10-02 | Level 3
18b49776-fd89-48e8-8c0b-6d1fdc129e18 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
089f6d02-0269-470b-bf54-6f4f55bd4c69 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
0f09dd73-6162-4d90-b6e5-e5379e8855dd | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
a7cc73c5-eecd-452d-a877-cedbcd85a55d | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2
6102cc02-baf7-4511-a4e8-285ac03b9361 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
5cb8d148-fe45-4f79-a200-d18f987aa9da | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
62f13b10-e755-4c35-b337-ef6026af9916 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
54516942-f08c-433f-9f28-5c853b4f85d9 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
74f4da9b-1906-4ee1-b31d-42ac1bb04bf4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
421dd21d-9307-4272-8c7c-d3e1f73b7d52 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
2bec4f63-d4ec-4992-af66-98c7d088240e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
ef5b64ba-f200-43da-8d7b-cfb8d4d0d8d2 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
f18689de-38b8-4474-a6c5-3f927b0e0cff | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
f44551c7-83ae-4559-8f67-ea8339cc5246 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
c29e85c3-a3bf-477e-8dac-224c4cb3445a | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
a036e711-0315-4a54-bac3-9b0a629c5e16 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
69a415e2-f048-4f07-a80e-7730dba5bc34 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
30e72115-8f73-424d-8ecc-79214094cae4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
df2a27f9-0f81-4a41-9b07-ab59748877ca | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
c4744b04-54c0-4252-8746-e113b5ec3142 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
09028e99-5d02-4bed-96a5-90b246972158 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
ea722252-db7e-404e-a49a-3cd4e1da035d | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
d554ed87-db18-43b8-9ac1-02d309f18a41 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
db981d8d-c628-4b01-85db-00da6c133ed1 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
d991737a-6733-4501-8099-57a932b0cfbc | Pole | 0 | Distribution | 2020-09-26 | 2021-09-26 | Level 2
c599ca11-c9cc-4b3b-9b0e-3ec7b84ea11e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
121c6538-9c22-44d6-8b38-635f4ee35bbe | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
9ef6f2d4-befd-4d2f-bc4e-315154660a62 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
991e79e1-42d0-461c-ab21-cbff43d1e652 | Pole | 2 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
919e5b7a-6e5c-4fce-abbc-8338266a90f4 | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
de629e6e-b40b-43d5-9a7a-1f02c116e82e | Pole | 0 | Distribution | 2020-09-26 | 2025-09-25 | Level 3
ffa34a39-ef1f-4524-a636-595b49248c0f | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
8bbaf5b8-eed4-473c-a4c2-9c4a38c62059 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
855e5ef6-5b9f-4cbc-a685-611445b321bb | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
7ee6f158-f093-45e7-897c-28564e0592ce | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
b2d8ee65-83c9-41f0-998a-316d649842bf | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
bb10f092-94a3-4482-84bc-724b83061830 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
adf493ae-9310-4bee-8bc3-6c1ad88258ba | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
97c109dc-80ed-4efc-ae8f-a930752a2d2c | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
da2ad61b-7116-4fe9-bf8d-16631e499f5d | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
ec92a2d0-7117-4ea8-88c3-58125ed00aee | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
e8198807-4624-4b13-b2c9-18813a90ea6f | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
f312b6d3-ca7a-49d4-bc2d-b0972f9bd4a5 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
f8e5a2e5-27dc-41eb-81e0-ed47b9664c2b | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
3048addc-d28a-48b6-991a-5eadd5fd03b7 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
453ac828-a001-4bc5-992b-d2e535489cfd | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
583a377f-3d93-472c-84c0-1727816b6837 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
63b2eaf6-1c5f-4c86-9fb1-9a2007e4565d | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
63e3eaf1-827b-4499-853f-a9ec0b84e3c8 | Pole | 0 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
5e6bbac8-4251-4cf8-878f-4938327be4b0 | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
12b3c0a0-1434-4a0d-9f64-f79b23cad13b | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
234b87d0-7609-4032-856c-432078f2e060 | Pole | 2 | Distribution | 2020-09-25 | 2025-09-24 | Level 3
1d4d29e3-ca10-4501-8219-0ce24e712dae | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
09d68a3f-e4ac-4b24-b4c6-b224611c70f8 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
0113187d-969a-487c-8333-f82ec1ab6ae9 | Pole | 2 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
71ee2e78-4e14-4a2c-9dfb-96c1442394f5 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
704185da-3454-4160-989e-9fd85c65cac9 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
6f2509b5-adf1-4d7d-b0c2-135b63ff7362 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
45718d8b-01e1-4314-8080-fe3183110c39 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
4b87c4eb-d3d3-4a08-a3f3-001395047364 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
396105ff-5c6f-4ff2-b723-4c0aa1a2be6b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
2959c08b-2d61-4dd4-b84a-c430ced94c0e | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
fbea8a5c-92f2-4a5d-a3d7-97eaaa819d7b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
f56bacf5-2d6b-44c5-a39a-7da8d192985e | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
d84483d6-f80e-41b4-be8b-d718c0956194 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
dc170a4d-fb8b-42fd-9283-5f9b4fe35c83 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
d6e906d6-5694-4e6c-9401-5ff6bd6bda82 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
ab23d578-c5c6-4120-bb19-f10d6db7071a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
b2569ea7-8267-40f5-bca5-841c9c6ddb77 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
b415ca9a-f0eb-4100-b34e-163e1f51c9c9 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
8ed4feb7-2f41-40d8-9025-568fb267ac03 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
963ea595-4ef4-4972-8113-5d0fe3facd00 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
a68f1ce3-f612-4e9b-adca-504d667a1a3d | Pole | 2 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
4470a632-25d9-4396-a577-3a6886bf6ff0 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
408da581-b792-48ab-a4f3-51d0de8a106b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
494375ba-3253-4c92-b4ce-4f13bfa61d7a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
26c29f7a-590f-44ca-8869-c2c4b7b333e5 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
0904baa1-e4c8-4efd-bab8-68769a47e986 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
11b6d47c-3ee6-4cda-8a23-64c1336cacf3 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
1d280027-04f6-47e4-80ac-48afe986e84f | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
1832dc12-5ef5-49b7-a70f-a4e2725c6458 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
cb5a1e7f-bd7f-4f71-a2bd-c0f2d2b84c54 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
f86916e6-3703-48d9-93fe-f3aa0b357368 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
f03bc64f-e118-4f33-9bc8-1d5c5ae7eb65 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
edc52a12-a097-4c4f-8b40-d08bbf974a6b | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
97b4e740-f17f-48db-ba20-487b5984f0a6 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
7b2ef357-f3a4-483f-8008-1cd84f5b3a0a | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
863ee853-cd25-431c-8853-a1cd779a38d8 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
a7317bc6-9766-4721-9b7f-28780f5efcb7 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
a67a9c0a-fb0b-4c9f-ba60-057dfbe2e558 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
ada8989f-4023-4937-bc58-09c6f4260e01 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
b957c8dc-03aa-4a21-9c89-65b3c3948462 | Pole | 0 | Distribution | 2020-09-24 | 2025-09-23 | Level 3
88bf9e5b-712f-45d1-a757-18de6e8a9333 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
7b879260-8240-42ff-a819-d8237f735781 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
75ac842b-131f-41aa-ac05-362e5fcb22e6 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
9bde3b8e-b7a3-4337-82fe-645cfb8fdd7d | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
8eac32a1-3e4f-448a-8c52-9391a0b96aa7 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
90f9aff7-b2ef-404b-9b07-99a10d537107 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
fcca4c0c-971f-4d03-a6af-d299317a3ba2 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
cac0e953-93eb-4e2b-b842-b7beb4e7fe30 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
c9b77d53-1992-4902-b026-1fa5f36365c1 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
d3e2c850-037d-4970-8e4e-2b76531ce32c | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
d466c7a7-3f54-423c-82f3-e7e454879774 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
05dad096-127c-4b2d-b6eb-d4d799332779 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
2a6febca-9650-4a16-b64c-981622ad12b3 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
286b3b1e-002b-4299-9b00-12b89fae14ed | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
26985cbf-f6df-47d7-bd12-5a9ced24f730 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
48c688de-4ac3-44e0-8eae-2028eaed4c5f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
69a6b781-5323-4678-8dce-296e4b8990a7 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
6a208164-8b29-4834-ba67-66f354dc6b2f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
50ecd8b8-a11e-46d1-969c-127156a96abe | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
899b4e46-63ff-4e11-8240-3528774fa842 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
b336bae1-4de4-42f8-8342-a75ac26107bd | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
9cd04e7c-24b0-4d52-b0da-4de823c37a05 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
f1dfba25-bb98-4aaa-bafa-22ab77ddf652 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
310c89e6-3d96-4994-9742-19fd1f80d49d | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
40540f1a-ba90-415b-b62d-db6f03f4bcce | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
725fcadf-d587-4187-8419-613508848c3e | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
6008c623-14f8-411f-baba-30f99e57e83f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
1dae268c-2c82-4f9d-b775-e99d9d9981df | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
183f7684-fa6d-4cee-bbfe-0815333cf09f | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
19e3ca7b-42df-445f-ad31-1cd727a30780 | Pole | 0 | Distribution | 2020-09-23 | 2025-09-22 | Level 3
0372d406-43ea-4d8b-916e-baa6b619a8d9 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
6e91be45-74f8-4cee-a80d-b729442d818f | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
f4622cbb-471d-4d00-9b02-87afe135a3e3 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
6d15505f-1c03-4442-87c5-e139ca184132 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
315893bc-8bf0-4169-9044-290fd14510ce | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
16cb6f18-110e-47bf-bb21-2b49c863a980 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
0b1fc06e-bb35-4fa0-94a6-407136e6821d | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
d9b8e866-edc7-4fcf-8651-68ded02b80f2 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
83c76b50-c5e2-4c44-bc14-26eae6d45f25 | Pole | 0 | Distribution | 2020-09-22 | 2025-09-21 | Level 3
c00852cf-094a-4399-8968-2ff75599306a | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
c34be656-3015-4e8a-b974-b59edbd8ce1e | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
ab061379-8e68-42ff-89e2-09a998aab300 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
d2e96ea3-ab61-40ac-acdd-a06e0b5a4be5 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
09e2028b-dd39-45e8-bb14-beeb43dba495 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
b00122b0-d174-4c6a-96ff-347b2d312b57 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
967b71e5-a348-4d23-b76c-7ff17325523b | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
c1a0303f-de68-4cca-b4fe-a1950f6f6cb8 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
8baf0207-8837-4fb0-8337-ef289fd5eba4 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
6d8a5646-6a38-4ee9-b4d8-ffce1f8eeabf | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
5c7bb953-d9c2-49e9-b1ea-ede13ebc527e | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
62b08ee9-a921-4a59-b178-59b0f9970b6f | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
2bd3bd95-1be1-4b54-a30b-5d48625870a4 | Pole | 2 | Distribution | 2020-09-21 | 2025-09-20 | Level 3
2c99cbf7-7d26-411c-8af6-23b9e1158ebd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
3453d0d2-a655-49fb-9ad8-1810b75432ea | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
387cc8e2-2d3d-49f9-8841-99d9abb071d9 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
46101885-50f2-45f8-b1e7-a692a1a9b0f8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
64760a9a-780e-4e14-a944-fc8fb47f47b7 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
545fd7fd-e788-4d67-8c3c-2ef4dce14e1f | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
693a1f56-5104-42de-a179-77cfc44456fd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
71e617a2-e939-4499-85f5-9e7210963caf | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
1117d1f1-fe70-409c-83e0-ec926de681d3 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
14532269-d714-4010-bbcd-652cd9ae26d6 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
1ea289ed-b6a2-4f3e-88f4-b140ea1499fe | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
22b8e8d0-a4de-462f-a08f-6e54f5c46c1f | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
82174148-0a5f-4b46-9191-5bb750438556 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3 |  | 0:00 | 0:00 |  | Pole needs replacement, rotten pole top
a24eb6f6-4d2e-4703-9556-06a97fa67214 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
c41c3d44-552f-4c17-970e-39011f68caba | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
54c8cf7f-92b9-4e44-b7e8-f70dd7ccce8b | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
ab03f6ad-35b0-4485-8bf0-efd1aca3b486 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
aa8edd9c-7ee6-4212-9687-9bd38fabceea | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
1cefd6ff-8a39-4ba8-8f0d-813c43084c99 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
b932e7be-4127-4738-b0a8-d3d1f11b1af2 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
73a70c41-d838-428c-b6b9-538bbf7b931c | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
4ba63b2f-5b79-4c38-8a14-fc6435dce7bd | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
b9f92c26-c72f-4180-ad0a-89742a7969e8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
15e24b26-d177-4193-94ee-ad0e83155867 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
5a114bab-ad6e-40c0-a4ea-80e597da421e | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
0e740a7b-7d29-43cf-a0cc-eaa21602b720 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
c2c9d79b-7d35-4742-939b-0373d22e0fc9 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
e04b4164-2aba-44a5-ae76-1a7a99b0ca8e | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
e15d998b-37fe-4e12-9cd7-70b3452e2117 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
e09a7e9d-ac55-4c4e-a5bd-0e14245c4336 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
de17cbb0-da00-46f3-9f93-90d2d5c86ed8 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
d8a60def-06c9-4b60-8bc7-28f66a835e5d | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
d17f322d-79ca-484e-92d4-de702ba0fdc6 | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
fc9763da-5feb-4619-8e0a-5bbef2f0a77c | Pole | 2 | Distribution | 2020-09-20 | 2025-09-19 | Level 3
cd3c3e79-6e00-455a-b805-7faa5e05d82e | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
d4740d9c-b482-466c-b338-3e22518f4a89 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
d3609e1b-52f4-4f31-8fbe-b3ffbeb041c8 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
d0552240-ad2d-41aa-99f2-ebc66d5e9463 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
dce02cab-2f64-464c-8787-ca752d541d8d | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
e39e9540-d75b-42a3-8022-d79d6285dc98 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
b0e14802-6165-4f88-8981-1bf04ed23404 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
7f413600-9fea-49c3-b532-925067d40b87 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
a7fccfc1-f161-452b-a740-090fe2e0d5c5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
d3a05c5c-8937-4030-a809-4a34d80200e4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
75d1fc85-7755-4b72-bb93-b309d8ea3930 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
870336d2-780c-4d45-8f3a-9417175fa2c0 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
4e298a92-46c3-49d7-97ce-f85b1c05dc29 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
1b238d06-2938-44e0-a1f9-ae909ee178ff | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
ebd4b750-cf76-43b6-a3eb-4b31c0f8a773 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
131e8968-d1fa-4c1c-b968-a7793e30c812 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
5f49e29a-51f0-45cc-9982-fb7d9fd98c68 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
4eda5d1e-d599-4a7a-a3ec-b02133a038d4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
ec5dc4ac-6a07-41b9-b61e-dad2c5c9e780 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
5eddef51-62f3-4b95-92f4-fd582d3511d4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
381d8814-d3a6-49ac-9848-8e76e63b0524 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
3a3ac121-d4d6-4b9a-bc67-e354d823fd1d | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
f349b4b2-af6f-4d17-b93c-013a76e9ac07 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
f22e9fb5-b5d8-443c-ae18-be0d32f6fef7 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
e20d97f5-d335-4f0f-a319-b09e13407e07 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
93082e1b-e7e9-4ce1-89a3-2a9b1944771c | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
eb8b3260-d6a5-4952-8cca-4c2a71e0f260 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
fb46d411-5cc4-4e79-804f-728d4650d58b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
aaab666b-c2d6-4b26-ad9e-771fcb5536bb | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
af3e8268-2e81-48be-8ea7-bb83170a2faf | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
c1555915-83f2-4cd7-a767-425ab9a0e932 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
bdae4cf3-59c7-4b0d-b646-d87e3150b3b8 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
8c37726f-b365-498a-9805-ea90dee7df35 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
c3696ce8-4cc0-44db-a49a-6d1d31802eb4 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
c811748c-f3ed-4bca-8035-d2a263064ae5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
7b282242-ebcf-4dfa-891a-b3538d922efc | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
7f718100-8722-49bc-a879-4a95d7106ba5 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
1d549433-8f37-42e9-9f9d-1ba386aa5086 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
144964b2-28c4-4443-abdb-1fd432bc0ed2 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
16e75a48-71d7-446b-be1f-c011067d8713 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
02478bd8-57a8-4d1a-b6d8-c31b522adab2 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
18f6926d-bf28-4073-82ca-dcf1e0a03969 | Pole | 2 | Distribution | 2020-09-19 | 2021-09-19 | Level 2
ba24abe6-05db-42c8-ac89-e73092c60d76 | Pole | 2 | Distribution | 2020-09-19 | 2021-09-19 | Level 2
064f086c-54e6-4007-944b-398f79d3713b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
0d230900-2629-4e0b-8ef3-951fd826b2d1 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
0c0994aa-3444-494a-a211-fca5f27b60a9 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
72407f6f-3629-41ce-a150-e1fccc9ee5cf | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
725f8b5f-df3b-4b22-8c10-0a7eba33af26 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
280e46b9-6bb1-4010-9091-ffb217b83c58 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
67a26434-ecb7-41db-a708-04f4a2e0154f | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
71349818-7580-455a-91d0-048fd826e4c0 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
53f96c07-8016-463d-b808-94c49787328b | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
5f641f14-f3dc-4074-8cfc-f0a209295355 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
38081f83-c28e-4b24-ac25-3d45d8cbd2ae | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
2c7e8da3-493a-4221-a267-1f7825506d8a | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3 |  | 0:00 | 0:00 |  | Pole needs replacement
282e9eb5-ae62-4c61-81e0-8b54c6631b9e | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
26964d70-51c6-4e86-a41c-f71119ecbe04 | Pole | 2 | Distribution | 2020-09-19 | 2025-09-18 | Level 3
38c95a71-08e4-4b9e-81ec-db4c6fb63593 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
20cb28f7-61d3-4784-a45b-710a7678a36f | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
4be75378-5f4a-459e-b458-0f1d1bbc600a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
45eb5350-c97a-4f5a-a3b5-9ad2ab5dcd8b | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
4612ac93-3159-4bbc-aa74-44e409c85742 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
3fd0bfd6-afa6-41b5-9c84-60dc6a75914d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
42a95ff2-89a0-4cd9-9e15-e1938b7eded3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
5c9472de-c4ea-409b-8b56-c7cefb2b086d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
63167f0c-f143-4fb9-a8f2-a780200c68ba | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
51dc9f81-f4da-4c03-a1b4-289c80803f41 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
5a135d5e-5a13-4681-b7d7-0c68a78c303b | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
563682f3-9b98-4d5c-8687-5e85323f1ea3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
55b091e8-0373-4266-ae34-a990caf18c71 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
788f5ea1-9623-487a-9665-fd79e78b3c75 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
0f6d8585-c96b-4b2a-8505-2ae85c885aed | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
0169efcb-2ed4-46a6-938c-9355f405f29a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
02dd2efa-4a82-40e8-b0dc-a9bac672145c | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
161a6279-0e70-4b64-84c2-ae4db8cde788 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
1a22c63e-20cf-4e46-b500-b518ba555114 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
1481e906-fc04-42e5-950f-5c1bdd2515f1 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
eb13cd7a-4931-4ad0-8ff2-8fc8ba005ec0 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
84740b3a-385b-4615-b2fd-0b49f99c79c9 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
8a22207f-5436-46b6-9d74-fcfa85b29d56 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
87a69f7b-e368-4bb8-a01b-bb63429d8fff | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
a4c4ca2a-cc13-4985-91b1-0f395446db77 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
a29d1750-c86c-418f-a254-44d62cd85908 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
a7a0b342-c6ed-4b27-8685-0438b78c4833 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
a87a505c-9c20-4cdf-8222-b72d9dcf5755 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
963c12c9-7b0f-467d-9c58-cbf6e88b5f04 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
97c6bb25-ce15-4cff-b3f1-b485ea909282 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
af40d29d-b24f-444d-a48c-12bf5593a315 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
b01c07ed-d120-4b35-97ed-2bb63026fc1a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
ad0a2c1c-4861-4356-97f4-cb11c9d6134a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
aa2380d3-8eba-403f-b0c1-3f45abe71f18 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3 |  | 0:00 | 0:00 |  | Need to install split bolt at top of pole, pole ID installed 04/16/21
9c0f69e4-5fc0-4a37-88c0-52f7e74af755 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
abc60e15-37a6-47f9-8211-e278b3351738 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
b0d549f3-b255-42b5-a79e-09a0f619f941 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
f25dc6da-ad0f-4012-9e9d-617087ec7230 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
d5385b7e-bf12-4cfd-944c-8ccc97c81c38 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
bbcb524b-b380-4a3d-922d-3975149be33f | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
f3b94888-8879-4bf2-8d5a-f37987967b66 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
c62b4dd9-4343-4492-83c1-667c5b157d80 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
eb4eb104-f56c-4363-98a0-528a4b632402 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
f3ede1de-0f44-4b95-8563-c50ffb570473 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
b3b74663-4b02-4240-9a7e-879cbff5357d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
ce972377-fbf7-4a68-86b4-1ce8cd23b1b1 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
e98f4df7-9ef2-402b-9bb1-ca2eea3e3701 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
e5dc5cbb-8b70-4326-826e-a23fb01cba97 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
dc24ed84-4be8-492f-95c4-c286e84eba22 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
db8dda95-89d8-4d44-9c22-577164cd8c0d | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
d507778b-7f2b-43ac-a5ba-548a999bb32a | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
d76a10eb-13f4-4cfb-9a22-6aaa31a618a3 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
faa36a05-6d01-427b-9b99-8c640ca26358 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
e465f5d5-0d4e-45e7-8b49-d11c88f1c759 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
7f1e6e8f-b861-45e8-b507-f2f42b9aeac0 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
0af720ed-a0ee-422b-8ee4-5b43c9d33bc7 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
b762f9ee-8b1f-493d-93ba-a5b1a423e7f7 | Pole | 2 | Distribution | 2020-09-18 | 2025-09-17 | Level 3
d66fe9e6-429e-4b7f-a14c-50d763735cbc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
c500eb9a-3614-42cb-a1e6-1f63f4815c4d | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
4a93adc1-e7f3-4f81-9808-16b9b62a52ca | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
552207e6-75b8-457e-bd52-b416f5780f45 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
408f30e8-6d9e-4f0d-88f6-f11a9f89dbc6 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
f56d600a-0a69-4468-aa43-2511b6ecd3fa | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
f65c39d7-b294-41d6-8e96-30413e9716bc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
c6a77b7f-e804-4183-8913-475ea4635186 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
bfe9da00-69bc-4548-8219-ad57ae7eba4c | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
9bd6ea73-c0f0-4846-9bdd-7f9c326bc4da | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
a349cab4-f321-487f-ae80-4e56731d67ab | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
8db86714-7cd0-45a4-8838-b01231ed8491 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
84826027-e0e4-4e4e-86dd-e09c269dfb50 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
07f7bef7-e317-4cae-a372-0bb3492bed6a | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
79d02709-cf05-4575-a30f-190b4f420571 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
72c8b212-8d5b-4925-b63f-88ab55c0a1bc | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
518b01b3-f0d1-412c-8fe8-597620965eb0 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
4998c980-b7fb-497c-a656-e76fe594a783 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
260619ef-6aad-4159-a461-1062dbb9ed12 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
2a73b142-fce7-459b-b03c-3cc306567b45 | Pole | 2 | Distribution | 2020-09-17 | 2025-09-16 | Level 3
25d3161f-6f1c-453b-be04-853f01ed7245 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
37b978b8-efa6-4d26-95e7-f322863fdacc | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
2faa00f9-2964-4f78-bdfe-0de414ea9a6a | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
3e69c394-2d6a-49f9-bf43-05ee6b6ffd72 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
591f3239-7835-4764-8b38-ddc7ed924b35 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
582ff41a-00ee-4ba6-90a3-f21790ab6d84 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
6fd0ea63-d3ed-4f83-aad4-f6ae44c01438 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
00e53c6d-3ff6-452f-bf1c-fd95b05f1d8b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
06c91f96-2882-44df-a127-d9d7edb056e3 | Pole | 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2
16f16a53-c628-498c-add5-2cde6af5614f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
1920283a-ab84-4304-ba1c-b2b7e81a407b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
81df3ead-c173-42c8-92ae-29a5cd1a91f6 | Pole | 2 | Distribution | 2020-09-16 | 2021-09-16 | Level 2 |  | 0:00 | 0:00 |  | Pole cracked all the way up, already stubbed
908b1516-b4d2-4365-8a8c-d8fe544c1598 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
9128dc83-f3a8-4507-9eff-afd05f5e9abb | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
a1367e0f-1f7a-455b-9696-278ddb5bab36 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
970ed103-bd33-4f27-b406-6f87814c3a7f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
911c6faf-0b65-47ec-b1bd-9a34161166c1 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
92dd6c1f-e942-41c8-ac60-b0b426f174ba | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
bd6e233c-0f91-4150-9600-9b03016c7374 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
aac668a0-e890-48b8-a57e-20028e3bc185 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
afe872f4-e448-4231-ab4d-b3fd5ba0f220 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
f79fa4df-f779-49ee-8bc9-0b1948b9a3a9 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
ef08833b-4fa6-4df6-bfb0-10e45e6a8bfb | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
e2719427-d0b9-4433-b28e-d9237ed649ad | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
a1e65cd2-52d2-4e57-8400-2591b1046bac | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
72fd69f9-5bd4-428e-90b4-a7b4b42f0630 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
6e3025f3-316c-4dd5-9a86-76dd587a1607 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
e6e6e4b0-56dc-4017-9280-a0cfa7a65284 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
7c1075e7-6c0c-43c7-a567-eebe29dc10fd | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
ccfe3f15-bc48-48cb-8bfb-f355f95bd249 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
cc216c78-a960-45ec-b0a8-7f4ae515c58b | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
b63d98e9-25ac-4df6-91ba-2a5e0883425f | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
ffcf7ca7-62a9-4256-a8b9-f71301012fff | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
d572c4ee-6734-4c64-9c51-c990f525caf2 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
b7785d70-15a8-4224-961e-d2173cb94f85 | Pole | 2 | Distribution | 2020-09-16 | 2025-09-15 | Level 3
b886b911-20b3-4066-92e3-e8cc20675f44 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
c1720bef-4566-4d2f-8a1f-91269baad7f3 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8eb5ff86-91b6-440c-89ec-7c4dbdb06fcb | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d7dbcda5-3b07-4167-a103-e2395c77a380 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
ec7d63bf-2694-48cb-b862-a7141a854db5 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
90624ba7-6762-4402-9406-0b3d8e20251c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8ae19aae-0071-4595-81dc-43884931423a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
862f2dd9-360a-4444-8aef-b2870a42807f | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d13f7b66-b894-4757-8c5d-087da3ad415c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d138fc4d-6fd1-49d0-8f13-6968a31b9586 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
ce59f6cf-4f6b-403e-8916-8d871077ed7d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d1796ca6-f922-452d-890c-5dcf6bca29a6 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d737cfbc-e4cf-40aa-be91-063577e7f4a1 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d32c1bfb-84a2-43ff-a577-b81e9940f5c0 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d4a22035-e959-4264-9207-3c09be3820f9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
9df6dcd8-3dcc-4589-8ab5-7c5e81e01996 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
d8ecff38-59cd-442a-84a1-36f2be89cb4d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
664e2e7a-b144-464d-af7c-d1132438b573 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
df909596-d684-4343-b007-72b96d93e505 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8122da08-bc53-4fd5-a516-05fbf08d7e43 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
9cb6165e-f9d4-4165-a703-cfd2b5194f41 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
b5028673-0f01-4209-88bc-77c2e275cb10 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
e561d49f-34b7-4e88-ac3d-bb9024d46f51 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8d92b1e6-efd4-4596-a0b8-518b9710e5e0 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
e506a92a-c8cc-485e-81e8-79a8a9c1cc32 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
3cb5e2a6-a19a-455c-bb52-4f0aecf94ff8 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
69790a6f-42f7-41ea-86dd-965fae409c41 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
78972a0d-4932-4116-bc8b-092d55069718 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
43a896f4-c675-4bf8-9b67-dd69d08d987a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
f1b8fcf7-c299-4f9b-84f1-75bf884592bd | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
f15f43c3-5a0c-4503-a204-6a5612dd845b | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
f7141845-a515-4116-a3de-da48789f83c9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
f7cbe413-6fd2-43c6-8a6f-d6e1ea7b3266 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
bcb375d3-66d5-4288-9aa7-41776c6ca9e7 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
bdc962b1-fa7f-4ca7-bfe5-8d6774347587 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
8f90750d-0075-43ee-8c62-dccc27d04d6c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
89686f07-b95c-4cd6-91fc-00d97765fa55 | Pole | 2 | Distribution | 2020-09-15 | 2021-09-15 | Level 2
802c6196-7321-4988-a5a4-70c294cc4944 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
7eaa1565-1ad5-40dc-ab59-a8217d453bef | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
1a6ba33c-00cf-49b9-9043-41b91d4bc8e8 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
14b98f8f-0c48-45db-8853-4a7482454431 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
107ba6d0-e1b6-4f10-9919-f37f2e208575 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
10c9ccd2-308e-485c-a558-0008371562a9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
067e4ac0-886f-4ac1-af54-32a63eab9b42 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
07fca404-4dc4-44f7-a404-09d8523b587c | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
7606eb99-8600-4603-aaac-200e22ef804d | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
756ee04b-8cc6-402d-a244-88780a075a63 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
599ccb56-6f87-46da-9250-b2c7aaa4ba8f | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
65e3b1da-37ee-4ec3-9bd3-4bc859c5a9b5 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
5e644c34-f461-4598-a822-2f8d4f2319b9 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
498bdfc7-bad8-46cf-a701-ea01bdf5a587 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
477ae48d-10f0-4d68-98ab-8fa0bb030f8a | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
43d17037-cffa-4d8b-9374-3b091af9a85e | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
3075c30e-85cc-4db1-8118-945536b7b927 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
27be5e51-b051-440d-af43-b3cb806b36c1 | Pole | 2 | Distribution | 2020-09-15 | 2025-09-14 | Level 3
289c49f7-0840-4bc0-a318-af0365dbc828 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
2e8b6799-1d7f-4dbc-90c5-e1a2916a9c67 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
2ccd4649-4bd2-4208-ab69-7024a37c3a7e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
30ea35ba-82a2-4395-b5ca-23767c9f4cff | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
2f940277-22be-42a7-8834-28da9b620be7 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
37b626c9-790c-4620-8ff6-503f9536079e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
4a08e08d-85bb-4562-88c5-937f0c2a8ae0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3a7a4299-3220-414f-859f-6d963ab6b87c | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
43e21dca-aab9-4819-81c9-33bbda26f39e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
6e743dcd-99a5-4a3c-8223-2ee7bd1c376e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
72783e60-b2da-468a-b64f-240f165d90a8 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
714d193b-5ad9-44a9-9ec8-1bd95146278f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
679c7247-166d-4cda-8f68-754f0b779935 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
666fb3ed-e20d-40f0-8b03-913de4682d4d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
6b5a8c21-5912-495d-a809-0cdd73a5ade3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
10054db1-627f-4676-9177-bcb9cd077701 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
00eaccc4-4087-4125-ba38-91a7ed63a24b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
142f4922-2844-4143-931a-25157e0c6c99 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
236987f1-51e5-4077-aa3f-567e317677f4 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
239ac3a8-1ac8-483a-ab08-bc48b883da89 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
21c27a95-45c8-4ae3-8cba-8a5ce930180c | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
78fc88c5-a130-4294-8c06-631a641c9794 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
7f98a276-aaef-4e4e-8020-a5a6b515e965 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
7c387807-4864-49b9-9be7-eaf0a5c3dc11 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
79ff81be-c137-4ef6-b8fa-88490cc87c68 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
818f8593-eea8-4d65-95e4-707b548ab5e2 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
83a8c1c4-e015-4089-865e-e4daacbcaf66 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
96ea5888-fbb6-424b-a049-5adf718be119 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
9b827a8d-2e06-4358-9460-25ffbb47fa92 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
984de1fa-faed-4291-919b-7e77f6b01246 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
983f8ae9-03e1-49a3-b856-45d5f93c6135 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
9f774194-b8d7-4a48-9767-09e3fdfafa1a | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
46a0c114-b7d3-4a0a-a855-772da5c09609 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a094e5f0-2dda-46f4-87b9-68b3aea4666e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
9f883c68-681e-4422-a6b7-139e5c86449d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a51abbcd-cb0f-49ec-9cd1-db12da4b3f32 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
be8b262a-684c-4e47-9bdd-f065634ae952 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
be90295b-349a-4878-98bf-33a2a2d7ec67 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
c67d3a4d-f21e-4d7b-a899-bc6aad27a9be | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
c55a605a-ed89-47a6-b36d-2c75c05fac98 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
ba4c3707-710f-40c8-b5f4-9bdab567945e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
f86a644c-9338-40d8-92d2-a1f3b75e6a8f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
e827226c-a359-471e-b274-de887a36c47e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3268f684-b4c0-4caa-bb35-a6f7a291a021 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
1ae76144-8199-475a-a238-9c5c36d35793 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
2ec02df7-19f7-410b-bfd0-9af776299377 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
1f01ee3c-8b7e-4501-9d96-6e8a76ee9633 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
e6cacc72-dfbb-40c1-a08e-472b82fe849e | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
fa0f8be2-9eb2-4510-b8d1-8f2f636f6167 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
c55a2456-6b93-4050-911b-48f71a4c3e8d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a574af9f-d02a-4e64-8ea5-08e12ccdde3b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
eadc47fb-a021-4234-a4e4-6b277b3a7e2f | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
e159490b-60f8-42ca-badb-3f026dd704ee | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
daef9cc9-1a31-4b38-b101-652e946f8b70 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d3753484-90c2-40c6-aa44-3ca624190873 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
fe7a4988-1ccb-464e-814c-a7a524d0fb56 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
ec50b6a9-9fe4-45f2-a5bc-45b6b71b6477 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d8d3ef4d-b13a-4c14-bf38-864feed58533 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
dc21539b-4d1f-4990-8084-407e0b5d592b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
df9bfc8b-c32a-4240-b8de-64a94b1edba1 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
e4fd0d7f-e763-44ab-9e26-9fc35bf3a22b | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d2a9aa10-7714-47f7-8cfc-652b51da1d80 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d722d7ca-d9bb-422a-a8f2-6ae5321c69c3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d02ad81d-c36c-4f03-8446-63f38b87a1a0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3db4a227-beba-4a17-bdd9-e48ca6425e88 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3d9319f3-88c4-422c-901b-4cd2e2dbc9c0 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3f26fa99-0f48-494c-885e-9a95a886e0c8 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
3ed28385-0648-4977-87a6-65a7d7a1fe66 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
1c669c99-126c-4efc-862f-91480eea31c5 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
201a9dc9-63b6-45e9-ae6c-9534f67456b3 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
9234af58-456c-49d4-ad61-d21a411a6694 | Pole | 2 | Distribution | 2020-09-14 | 2021-09-14 | Level 2
16404d5d-b241-4eac-8015-cc30df8852bf | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
746d3295-42cc-44e6-9475-a5b550153674 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
fdb3aa6e-3ea3-44f6-b303-5f01c602ff79 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
fc43f010-3bfd-4a9f-88cf-e50d24db8908 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
d0e4dcb4-f883-4a7b-b998-7e882a986b74 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
cdec7f9b-9445-4227-b217-c1691deef7fb | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
8aed9894-cd25-4c07-a7db-76de1b4ae368 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a81f8630-108e-4a47-ade7-080ef714b268 | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
a3493de1-a56d-4952-8ae9-b8383a85242d | Pole | 2 | Distribution | 2020-09-14 | 2025-09-13 | Level 3
b4beaee6-2627-423f-90de-1e1e9d57a0d7 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
bb76c009-be7a-4bba-a483-da41b3743b91 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9155ac75-ca35-4712-b5ab-146830acb411 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9a02260b-2a44-40ce-a817-7a4384261c63 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9990b478-c4e4-4ecd-849e-ebe907e73454 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
cab342d0-2bef-4463-8368-1aa5d5ccb4df | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
cdfba419-7c3e-49db-8f2d-88f8b2238cd0 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d208860b-fc78-4c95-8ccc-2a8d4178954e | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d49a18d4-bfd1-4509-9a62-daf135a843ad | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d3df4e29-eb1b-4e76-8f19-8744e29f940f | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e3e35637-ec93-4ea9-a3ce-851c60d10b8c | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e8505b70-dcf4-4dd6-922c-2ccaa4bb6d79 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e9c96776-7433-41eb-a7a3-4f5fab9fef0a | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
ff3c09cd-251d-4306-a517-6d9082c544b3 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
ef23e86c-4acf-463e-a10e-e3f74c580c3d | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
f924a1a0-15ac-423a-a941-724e10b92eb0 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
fb3e4972-d35d-4610-a425-83779eaf94aa | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
fcd9b46c-3491-4c49-b1c3-aeec9f576b91 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
fc88c135-f63c-4ca6-94f4-d22989f0e019 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
4055c402-0c8b-4bcf-a47a-21cd851fbd60 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e27a9e6a-264e-4d80-bb44-f0f3e4ec453c | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
b5e91be1-bd32-47e1-841a-32dd2ce308aa | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3 |  | 0:00 | 0:00 |  | Arms are not in need of repair at this time.
1691c318-562f-43d3-b54f-4030205c64ff | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
1ac7413e-69d1-4edb-9091-6cc19eef7c55 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
0f07545b-e55f-4d04-82fe-3cda2c6ae59b | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
06755211-ab07-441e-9981-3b4edef33865 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
0712ed3c-753c-4061-b5f8-2836f1c77cef | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
06604983-fa04-4aaf-be86-ef07b43fc7b0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9254e558-b0bc-4f80-a46a-d487b061c3a0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
66e156d8-e695-4d11-816e-f899d950c393 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d08c887b-7e80-4488-979f-3e6014235aa6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
cdf0ecfb-1a7f-414b-9639-22d8cb3167db | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
cf10adcf-7179-41eb-985c-19f1af5d42bc | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
dc297714-4f0f-42c9-9348-412898baadcd | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
d8f1a664-5636-4020-995b-4479eb02dc7c | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
db063571-bea5-4468-bce5-2f3c382a3158 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
da72b4fd-0ad9-4747-a5b4-6911d648762b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
b47a14d1-105d-4c69-8952-a08f3262052a | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
e78bc320-9752-4aa7-9564-47813cd6fb87 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
15cf07a7-56d7-497b-bab4-84660d8b852a | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
edad180d-af49-4d38-9971-4391a9ce1299 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
baf4cd56-dff3-49f1-9400-138a09cb5fb5 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
b0de87ba-e3b0-4f4f-8d06-76a3d8c60f6b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
aeff464c-7fee-443d-9091-78b67a79b8c0 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
aadae53c-71d4-4b7f-a582-a31bbd79c427 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
c8f462f4-91d6-45eb-9a2d-153a801bf53b | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
be1a67ff-9ee5-424e-9c65-032689bdcca4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
9f9043e8-b8c5-48e3-bf62-6239c569e427 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
872a3935-9cd2-44bd-b21c-5d4738959eb4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
8b542ee7-b9d3-44f3-ad3b-f5eeda3cc86b | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
21654e92-310e-4a09-b165-ee32b6bf795d | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
1ca7a044-c332-463d-a98c-6b36b1fc90b6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
163e8a9e-3a5a-43f6-9d4e-1ccfba73aacd | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
0c319c12-23a2-45d7-be58-283f2dcb12f4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
06b0d8f4-a9d1-49fa-91bc-74efe51457ae | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
6774d447-f696-4a90-8325-f3ce1be506ab | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
6f00bbce-6bac-49c7-8616-27d9b0703203 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
6c4a54ba-d370-4451-9756-d9a3f5a7c0f3 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
7220c249-f551-4bf2-ab9f-fe4038e72af9 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
734c6e77-d2eb-4181-a3f6-35dac2b83043 | Pole | 0 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
7553da92-b5a5-4e3a-8e40-acb6726eda82 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
61f41eca-2114-4dcf-8232-a3559f12b6ae | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
3f4d3ec9-2c51-4acb-bb84-d4e115e1ff84 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
4b06414f-8076-4c60-a1a2-e8805922d95e | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
4e939279-f832-489f-948a-41ca884bc7e4 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
4d1cf6c4-cdb6-417d-9dbe-b90a5efeb6d6 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
38946370-0838-4111-be8b-cf241ddf1c33 | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
25f5c736-d551-4930-8e41-51a1cda4fbfa | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
257aedf9-3c0e-46f8-beda-b1beddbaacbd | Pole | 2 | Distribution | 2020-09-12 | 2025-09-11 | Level 3
38d52519-20ab-4359-8758-f701609e7a82 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
2fedb42e-f08d-41c7-bff4-b6cc6791b7ec | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
32320a52-aabf-4be4-be8f-7ca01287a010 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
39ffb9a0-9517-488b-bbb5-9261d40114ae | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
632a2553-610b-48e4-8022-8a1d554914f1 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
50a00ead-c7a9-4a04-92ed-ac72fd7b4b30 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
66efadb2-d4e5-403d-8927-29a942926aad | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
69b36e18-d30e-444c-9569-d89ae132554c | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
0bc962f4-7e68-4ead-a677-b7910bf77c62 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
0cebb518-40d5-402a-8f70-0778e1139389 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
0dfc1b39-c2b9-49e3-a640-e18a4609bba6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
05de68df-cb14-47e4-b564-32e1008d89b9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
046fcf7f-3e1e-4a86-9129-9ff828622dac | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
17c1b3ed-698c-446e-b6a8-b17b92eaf191 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
17c155f4-c258-40b0-a588-41e830848475 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
136576f3-067c-4c70-bc58-c3ed1d828cee | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
1ee99fdc-4900-48ac-93c9-1998500ae93d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8e2d50e2-fe17-496c-ab82-7e0cfc9925d7 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
9020629a-ccf4-4a82-a5f7-87fd81f23d2d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
88530dd5-6868-4f87-81dc-fd0022eea835 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8601578b-c58f-46e3-a0ca-0398c6bd2fa5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
a6bb3f46-0dee-4029-b1e1-915f491d80b3 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
a87b6f9c-b48b-4f20-8c6a-d5d56bc572f6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
9d979115-e9fd-4210-b01f-9dae17b6aef6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
bcb3a97f-456f-4489-8141-276490866959 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
bbedcc58-d59e-40b4-b5e8-e690f94981ff | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c211d9c7-f71c-4c80-8ec6-a6c53286dd0d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
7a2f9074-de47-48b2-a9c5-a81414e10b19 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
abb8cd0e-9b02-4d20-93ff-7d95cb1af307 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ad0dc710-e286-4ca2-b190-7c54279903e9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ac70b546-3509-47d4-a30d-da199e16d0eb | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ac2c3a92-5048-4329-8111-746b82aac626 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ae8fccf5-3142-4a3c-bb42-11af8844d968 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
1fc849dd-2451-41a6-abdb-fb1049b05b14 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ba9b8ffe-4c61-482d-a9ad-d2f19342f84e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
f51985c8-cb0e-4b2e-9da5-308ffa27e25a | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
d153fc80-566f-4787-b331-8f300c39f0bc | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
f8459cd4-a447-461a-9738-f47a8fc3b581 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
227076e0-3522-4396-a1fc-fd3126607bd9 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
312028b5-da46-43de-b246-beaa87f8a2a2 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
201df0c3-44ad-4f03-b2a7-6fd703227a4b | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8ae3071a-7787-452d-8866-325ddd8b4d2b | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
2036f882-4de9-4ad1-ab93-cff7634e5d35 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
53b83bc1-c945-4103-810f-e103e07c8880 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
0ae4385d-8987-4a51-89d9-220c22a9d2cf | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8b23e39c-cc65-451e-9eea-f2d1baebedba | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c01d86e4-cd0e-473f-ba4b-7ad4812a5047 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
eaabc698-88c3-4daa-9155-d77e053d1d86 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ead94f8c-f29f-4fb0-840e-10878e1ecd49 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c0331e2c-fbf5-4cd3-b147-618faa155e33 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
ee54049b-aeba-4f2a-9c13-67ecaf4a25bf | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
994f5a5c-4f3f-4179-8c5c-7bda58b75483 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
d8b2a13f-b851-4dbe-b751-090c379670b5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
94b9512c-28e8-4d4b-85f1-f86a654b30e7 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
dd7186c9-f289-460e-9a8c-04af99402f0e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c976e090-d0b9-4e22-b331-d72dd6d7e01f | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
d62b3434-70fe-47da-a47a-1a462d9826a4 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
246e587c-ee06-4d07-9bb8-17e62a8b9e48 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
07069fb2-5304-4444-99d6-5b165010b9cd | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
00be9e54-14e0-40b4-963f-783681085ee5 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
dda6dcdb-915a-44b6-b01f-b4335150818d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
dbc0d419-3c41-4821-849e-7c0247f230e6 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c9c01a04-41b6-46ba-b733-675fdca5698e | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
98a5d338-02aa-435a-be64-3b77bcfdf4eb | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
b777cdb4-363f-42a4-828b-28109ffa5bef | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
c20fba24-b1c0-4eee-b816-d239cf852423 | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
9ca62d32-b106-408b-860a-11bbfaf6a79d | Pole | 2 | Distribution | 2020-09-11 | 2025-09-10 | Level 3
8bbaea22-21c4-4ad2-b7c1-c4df7f28f134 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
bba20c57-5a90-4bc9-85ac-9f1c5d3e7f1e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
5a2f144b-7621-42a0-8ea2-574ab12133cd | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
d6bb383a-d6c5-4757-ac41-cefb820d7c56 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
d5fd6047-4915-45f6-b2d5-9636c87fe220 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
d7674af9-0fc9-429f-8564-bab04a1bd0ba | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
cb2a11f2-d208-4ee7-8dc6-dafde46aface | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
cf928c1e-e5fb-45d2-adb9-787f81497bb6 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
dffcc6e1-3005-4831-86a9-1b5d07ece2c6 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
e30174c1-5673-4617-8c30-481419c386ea | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
e19acc34-e06c-406b-b384-c461968b757f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
ef093c28-1799-456b-afde-e8118635aeba | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
e52524d3-0a65-42fd-a7c0-f408d6232394 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
8c52d151-6226-48f9-be80-b4d18df7b4f1 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
d0cfdcf9-12d6-45d8-9dbb-79f957841f13 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
26a5a473-a5f6-4562-b8c4-1f35128adf8c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
4010651b-9a16-4090-8425-5a10fab00e12 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
864c79c2-b840-436b-b20d-132d0d4c14b9 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
1dcb4be3-30cb-4828-9ae5-14b8ce742746 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
3b2f696c-1736-4687-b6f2-4192915f631c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
e8df1698-f47e-42c7-9331-be67c8b7ef86 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
f881a56e-ac93-4cc4-97a4-3d2cf6f933e7 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
0c3dbf29-5c48-4190-9f13-246d14cb1e4d | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
ef2f3830-8bdc-473b-bc6c-5d5e3c0a2257 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
b3787423-b15e-42a0-8144-eed040a1464a | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
b4b7ef74-f0f1-4e35-8f7f-25f368e188b2 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
c3f88970-c8ac-4350-9225-a98bb8ba1c5f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
71f40119-bc71-4064-8e99-7f18a6a2484c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
445468da-5be3-436a-9ef1-8a8b34522f3e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
06094732-0d28-41d2-af3a-7302be409143 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
96d21b30-8e4d-4aef-b099-2cf7ddac941c | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
a8916749-cc5f-479c-8804-e50c7dcc4268 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
2dd013d8-8f60-46a8-a298-a040d821d64d | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
82f158c8-a3a2-47f3-a057-1cf7cc7f5983 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
10c84829-41c9-4047-9d4a-16636a3128b5 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
19e12a14-1a05-45af-b0e6-954e28c9ea70 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
0f2ebcad-ecab-4290-bb06-750f1bd97f51 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
08cc3064-e8d3-4142-a001-61100fa7252e | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
69c6a510-4a23-4767-b433-56414a4a8f55 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
70903d03-db04-46f8-b114-b595047587b8 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
6f71e2c7-ce89-40f6-bd18-e67d501c6dec | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
71d5542e-7e9c-42cb-826e-3db4bfa9bfdd | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
3eba58dd-57a9-44cd-b792-ea6d6ec2a51f | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
3ddd2f2c-3e80-400d-b3b1-dd632ace2c40 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
407bf218-0e81-4691-abed-136d398a3e35 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
435fc398-26bf-4571-9a80-f68662556def | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
24a52811-eb26-48a2-8e7f-238867955863 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
28e65c12-9e2e-474a-be83-454ac367bf56 | Pole | 2 | Distribution | 2020-09-10 | 2025-09-09 | Level 3
24e4529f-9728-4a4d-9714-8f81c6853de3 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
385a498a-f6ca-459a-9057-e294cf77139b | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
353bc8c9-147e-41e8-851b-d03064a5c56e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3d386e16-9cf7-4545-a597-58fcfca2fcdb | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3af34345-9d0e-48cd-a463-4f774261f162 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3b971442-07c6-49ee-a7a9-a9f1e1349e29 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
77196ef7-113b-49a4-a25c-5c97513578df | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
79818e87-1936-4878-8dae-4019320e079a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
5a2c25df-c168-43f8-a9dd-bc41d7455e19 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
58841f2d-54fe-4296-a20c-cbe15fcd1b56 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
54b5d292-9787-4c8a-bace-241cfa6831b7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
11ec67f5-9c1e-45a5-9686-2e5d750bf4bd | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
10b04f77-b488-47e9-b35c-4b311c07eff7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
879fb521-a0f6-4a66-815b-12940472578f | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
aefee700-0616-40c7-8795-c0b7a625f74e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
7c187c63-4ac1-40e4-bfe0-2f31ba9ba143 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
a494f653-fba6-4b1b-bffa-568c25c45f58 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
96ec0dd6-0c31-4ace-8a66-8d06853c2d85 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
9325734d-7db3-47aa-a039-385bd47c9ecc | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
9bced209-5a6a-414b-821e-fc1df9483d55 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
99f8a735-991d-4534-a5e2-bf46e44e9bdc | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
bb4f430d-0792-4719-939e-2f40c5dc0d94 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
c85d5613-8f6e-4bc6-87e5-a1c7252f5bd6 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
c351f124-b84c-4420-bf5f-1e11a6ee13f7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b14978a1-ae9d-4b9a-871c-22de517726e2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b88b9f25-860e-4866-9055-904312608291 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
ad86ba97-47ad-40a9-a66b-401cf8a70f89 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
ad4610f3-cdc8-48bb-b50d-f1036c8ace75 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
fbb628c3-0e1a-4128-937d-d315aae2ebd0 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3789f0d9-5a8a-4ce8-9e9b-c0218362de42 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
19fba032-bcc1-45cf-b87f-eb4ba2c174e7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
1c655b60-d492-40cb-9257-6c92d764b412 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
6d30dc64-a57f-4fa5-a18c-87172319c6fb | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
8735d8b5-3937-4730-94aa-e7f489ce9e84 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
e48c593f-e666-448e-9885-7b5160303671 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
f1c8bf7d-aad6-463c-9df5-6e7a7efe2ec7 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b723812c-70f2-44a0-9c8b-e9c4dc0cd642 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b6678cd0-091e-4dab-8177-3772efc3cd9a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
7bedcf8c-be74-4f77-a8b9-8050fe29473e | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
e1c723df-5942-452e-a8e4-5441e4ee90fa | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
dda1f78f-6c90-4366-abb5-ab36e6526399 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
d9337983-775a-4461-beb0-697ac09c5a05 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
b50780e8-0311-4a48-b639-02a7f817676c | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
d2b7160e-789f-4a4a-a680-001b77ca3dcc | Pole | 2 | Distribution | 2020-09-09 | 2021-09-09 | Level 2
66a86bde-102e-4e0f-9ee0-0de3d662e805 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
73270fdb-d3b1-44f9-ac89-01721fc49d3a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
476fec00-2b69-4167-a662-f4f309809ea9 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
2bad7dd0-0984-4602-9ffb-7fbecbb194dd | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
0b3484ec-82c1-4898-b34b-c221ee045f70 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
15f5a249-a566-43ff-bac3-d50aaa28aaa2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
3a05872e-ab72-4941-b98f-0ab8e17e087a | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
71e6de20-9815-48c1-ba65-939bb5bc05e2 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
fcc9ee67-7cba-471b-ab96-8d89f84a73f8 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
bfc4e19a-ec42-4224-9b83-9793801b6ce0 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
cdc01b4d-b15b-4e32-8681-7eb967089f58 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
ca5b430b-720c-45a8-87b8-72a944b0ec2c | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
dc2bcdc5-f3e3-42c0-9847-b44bf745bde1 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
007fdac0-cb4e-4e37-90d9-3a3349f9ebd5 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
07f6d1d4-a745-4314-bc68-39428f89bd87 | Pole | 2 | Distribution | 2020-09-09 | 2025-09-08 | Level 3
fa9f6063-133d-495c-8d5b-dfe8a4f89622 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
8f042e4a-6974-41d1-a522-8237c4793bac | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
78f5ca16-6f8b-4ae5-96dd-843cb92aac15 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
a566bea4-f8cc-4c9d-ad0e-52f458024ac6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
6fbe44da-810e-43c3-ba9c-19560823a653 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
7a4ace39-6521-4a1d-8c08-40f0a0d9918e | Pole | 2 | Transmission | 2020-09-08 | 2021-09-08 | Level 2 |  | 0:00 | 0:00 |  | Kingpin bent sideways on the angle
19a5b9fc-749c-40a4-948e-101072e56771 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2c94f8e6-2da7-4ece-8f84-b8bfd465d47b | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2b4a46c4-f79c-41df-8856-36bf667578d5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
41e953e2-fc58-41c8-83a4-045ef44bab7e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
55a7ecde-57c4-4e64-91f9-102c42ac961e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
4d07c03b-e33f-4224-b4cb-43d894302b47 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
d6ca7524-6261-4ced-aa07-dbd39ab49a16 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
d3085b44-6db7-4998-8f42-e7aa173344a5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
d3ebeb17-7ded-45c1-9864-239f5465c1d6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
d041f2d5-d22d-47e2-be2a-89c5239369f1 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
dcae8831-43fb-4edc-8eef-f44370eef726 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
eda784c0-6fe5-44e1-835e-f3a702b2e559 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
f535d0c9-2c43-4f48-802c-066fbe4676d0 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
f44fb34b-0e6e-4c9e-afc8-13c2ef973133 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
f35668be-83fa-4190-9161-8da3e5ede8fd | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
abf0df36-36dd-4d10-a1be-dbe52a03f3d4 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
aad3c9ec-80ee-4d6b-ba65-99a040d897b6 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
a92fdd03-e53f-4461-98d2-fda5083039e7 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
bb854659-af6f-4a5e-ae8d-775c1b200a91 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
92955c0d-8f91-44ab-84f5-dd61971d297c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
7c48afce-1b06-475b-a8d0-0698b0715c84 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2ea550ad-8ef0-49cb-9761-fdc48d5bfb8e | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
806a044a-1e7e-4440-b9cf-3c946f102d01 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
8102d5dc-0f2b-4c0b-a698-e9ad86f47ad8 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
8fc0ecc6-5811-4fc1-8b13-4d4bc637f719 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2abf4712-2189-4708-8a18-51848df4112a | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
54c59ffb-9223-4b48-983d-2196acdc90fa | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
66120f86-56c2-4bfd-9430-bc20357231c1 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
636a27a1-b387-4d00-9ad3-5a1228759afc | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
76e896a7-6e8d-4b5d-91b2-b0fe5140136c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
73490d40-4936-4a87-b5f1-77ab16ee65e2 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
69cc017a-5d89-464d-ac5b-4ec33c1ddbed | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
393d7c17-7e53-4b80-90c7-9e855dff80bf | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
4db87775-266c-4b75-9591-9079baa6d8a5 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
48d3ec55-feeb-49d7-9a30-1a37c2e95bd2 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
42ae9b87-a6c6-43fc-9952-ce84e5559e6d | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
375ab800-c410-4131-b9c9-8fc3fabafa40 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
2fbda864-7b21-40d3-8a25-6992afe2fb9c | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
240b50d4-c7eb-4bc0-a676-8a16bf2ea521 | Pole | 2 | Distribution | 2020-09-08 | 2025-09-07 | Level 3
30a71c3c-efbe-4569-b745-24354b8b0729 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
37c14969-153a-41f0-8be2-4137adf34384 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
498947c7-4d35-4419-a553-7c1c34293f97 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
687591f2-36b9-44a0-b23a-77303cb79d5a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
76df2894-b548-44f2-9b3d-1fbf65014e5a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
609169e2-a165-4a27-a080-e51de78251fe | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
5105c557-1c73-4f7c-8c66-56a22fc92eff | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
4f86c94d-dae8-4a0e-99e6-081c8391feb0 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
0a1bbb28-fed4-4e68-bdd1-b7513814c362 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
0ced76c3-4d7b-48ae-abfb-1ad255951dc9 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
10d96d76-610a-4198-bd15-e2982b8464ce | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
14ebf574-7f8e-41a2-b968-8e8da245e45b | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
1fbfdcd5-613e-4f50-93ff-9f88a90018a1 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
01e07b73-c11b-4788-8934-0a883d539e0a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
37d49d91-f96b-4f10-acac-42a82cf76338 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
8ffd1c2e-9442-4098-83dd-25f3c734fb28 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
85d298f7-98ca-4fe4-a82e-b09b78e42448 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
83d11714-ab4d-4cd7-9c7d-2366b418a7c1 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
a24763e9-8525-411a-acf0-4a28c82220fe | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
7d1ad1bc-454c-47bd-8999-752f376c7faa | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
afc68393-d89a-4a9a-8ea2-1c63fe8eb06a | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
b43d9cde-796b-4e6b-be6c-6e05343becec | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
b3869d9e-d9b9-4cc2-99ca-6bca4151a640 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
b84f5f6d-b861-4f42-817d-693d2c26e82f | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
f5edade8-b947-4c0f-afd4-9b2cf4c1aea7 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
f8b161fc-0e9a-404c-99b2-ed5fd018c308 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
c9c479a8-4418-43bb-84d0-e2eeb10e8ae5 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
9e72ff63-ec9f-4430-ac3a-16f5b9ec1b94 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
be284cae-e84a-48bd-ba5e-fcac4c0a0d67 | Pole | 2 | Distribution | 2020-09-05 | 2021-09-05 | Level 2 |  | 0:00 | 0:00 |  | Pole is marked rotten and top of pile is rotted as well, need job # to replace pole entirely.
53863e53-64a0-4226-8642-34cb2169d364 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
41b49b5f-9621-4809-b095-7288ac22ff6b | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
d9884afb-8c3d-4684-9791-ea8c23cfb7c4 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
da7071ca-cacd-47eb-aa47-c6cfc507a48d | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
406a7372-3a54-4637-9f03-7a745b469b3c | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
2747e8ad-0167-406d-92b3-b10059bfa622 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
00b12d0f-273b-46f5-af10-0d8c19cfa9c2 | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
96a41b9c-09d4-4427-850d-d1f0d48f9c1e | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
aff8bc86-68e0-453b-a5f9-93840bda7eca | Pole | 2 | Distribution | 2020-09-05 | 2025-09-04 | Level 3
9dee83c4-429e-40f7-afee-7b5469bf8317 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f0c4d872-f970-4941-9bde-bfaad45c7af0 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f0c532bd-1a74-4597-bbd4-60907b480179 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
de8f1549-549d-4ca4-9f93-b3e94ec87361 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
ea88181f-b8ad-4a90-bde5-69b975ab296b | Pole | 2 | Distribution | 2020-09-04 | 2021-09-04 | Level 2
986ce322-8b30-40f7-baf3-b98e99bef4e6 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
5e9d3dbe-83e3-4031-a451-f7607487bed4 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
8846969b-ab27-4cd8-944c-a20f37ce3b6b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
ce733115-7d3e-4afa-955b-4bcd0e10fa76 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
7622ffd3-0e55-435f-ad87-4c5fa95f9905 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
5333c5f7-dc2a-42c8-b0a1-7d51a85b4330 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
111d99d2-0abf-436c-9c59-b28c6e0a8a34 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2b100b8e-37cd-41bc-a6e7-cf7b2c630ca6 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
1fc88df2-c68c-4200-9db2-f4a7e98e3de3 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2fe5873d-68a3-4a36-85bc-6166cd9f3480 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
4da17a15-1c32-40b8-8b6b-34c8a83edf07 | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
59d8f02f-daa6-4005-aa82-b5201b40101a | Pole | 0 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
6625a1b7-4aa3-4839-9560-d1b4c2c798de | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
62a2a326-04f4-477f-a4b4-ffae717d4338 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
c9bd42c0-1988-446f-9dd8-dc4800b40448 | Pole | 2 | Distribution | 2020-09-04 | 2021-09-04 | Level 2 |  | 0:00 | 0:00 |  | Broken tie wire. #2 acsr with aluminum tie.
552a5ca1-8004-4832-bc93-a8dc4572480d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
7b9dd334-23b4-4f0c-96ac-37f6f9effd9e | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
a38335c1-5bf0-47c0-a335-611b5acc4e48 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
326f9c67-dd0e-46fa-ba69-df3b0521600e | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
1b5e87cb-9e6b-4225-8725-582dcad776fd | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
e3eeaac4-5add-475a-98a1-cc17c032dce4 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
d30ec098-6943-4e28-a1c7-ae2fd67c8381 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
d74ab664-8fba-4068-8250-1a339149868a | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
d62827ec-7323-4015-b7f9-29a92c85428c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
98653a36-9249-4f40-9ecf-adb4654c618b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
e78aa2d6-ce03-4b5b-b20a-f8f7d4038f87 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f01c0809-a76e-4e7b-b101-445d0b805549 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f6d4d2e6-cebb-421d-ab71-3ce4021bb699 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
f136769b-cb1a-4cba-bfa3-e0d7d74cbf41 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
b17dbbaf-b321-4a53-943b-d6cff3d0037b | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
b8d9b0b0-c808-4ef5-a886-1a1e8c452c27 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
b988b884-c0b8-488e-a11d-19bad8120d7f | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
3761f46a-35b8-49b6-946f-63528659eee5 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
bde5e2d0-5723-4d0e-a62a-a654bbc4d037 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
58af91a2-9173-4891-bd46-f22d3af4f8d1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
c78149bb-e550-4284-b0d1-b445fe292b27 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
a616811b-b3e8-4c0c-bbdf-e485917b6187 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
ffe83f37-d44b-4b5a-ba2c-6f193843c5d1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
20f1b388-4757-4b77-b8c8-a89e117761af | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
23322787-dee5-4e83-bd8c-ba5a35a7ac0a | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
1bc6be04-5cd4-4a10-acc7-94b09b27699c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
188e4e64-b8d5-4ad4-94e8-efddc3801ea8 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
04e3e2fe-194f-48af-8dc1-3622f6a40b74 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
0aebd7e9-f056-40be-816d-5961c129c4b2 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
0144a31f-f308-4520-82e2-885c76ec70ed | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
599e071f-b927-4f9d-a839-7d6bb427e94c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
6118d409-b573-4433-b074-ebcc40146fca | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
43d35486-ca0a-4731-8b39-0acfae6744fe | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
7379d2af-e4b6-40ef-afd2-556b87769b0d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
675beea7-8022-43c6-83d3-c552ef04193d | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
3ec8c3f4-9955-4c1a-a33f-5e730b7f9da1 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
3c73a0b7-ab99-4927-a417-92474c552f09 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2ed8418c-495c-425a-8157-267f7a16bc3c | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
29d29366-b49a-4217-b14a-58f8a04f7ffe | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2c1d4635-8652-438d-8ee3-69b9d4796bb9 | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2b3d117e-70cf-4eba-a855-96bb895608fd | Pole | 2 | Distribution | 2020-09-04 | 2025-09-03 | Level 3
2cff5f4a-2437-4440-9ade-5592907f087b | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
28dec882-be69-4b0d-898c-8226bb188e21 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
32c5e4a5-9ff1-4583-a848-61b592b3c704 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
377d6ab5-d931-40c4-8a2b-b77469799d8e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
40457e96-3d71-43b6-9645-28c65b9a7d93 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
42de51ae-2f3c-481e-843b-6fe39b4edeb4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
47cd5c0a-9d2d-4e6c-b0ed-15931ffac538 | Pole | 2 | Distribution | 2020-09-03 | 2021-09-03 | Level 2
4b2730b9-1661-448f-b5ef-138721f0df29 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
4c61cb8b-fca6-41ea-8191-b67c7bbda8cd | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
4e2c152d-48f5-4274-8564-e2160cfdce48 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
40042331-70b4-47a7-ba96-d5ac8a91216e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
6f696f76-7ff9-49a4-accc-9ad1bd8059cf | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
74752e6e-b206-42ea-ae09-3f41d38f0439 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
64bd2ecd-5c2e-4a77-bb4a-e308e3b590fa | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
50c2db88-5df4-472a-b1f1-5447b0163033 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
51213f38-9a94-4183-8c0e-ab1e8587dcd0 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
026eed93-a63f-487e-9762-9514fc61aa88 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
0e866a93-bfa2-4330-b155-ca7e6d295290 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1876de59-37d2-4888-a040-c80203093175 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1821f34d-3e92-44ab-8a9f-fc76e4363942 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1abc30e8-fd13-4041-b0f5-89406ac22b0f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
1d4d8048-9041-4d02-b767-246583ccdbf2 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
241a3ae9-d3a7-4a77-b10e-4c012f6b3bf1 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
25841d4e-d5a0-47ba-9d1e-1cb9133e32e7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
9001bb70-723a-4903-8848-888a2fb5af4f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7d3ed886-79d0-4e0e-94e1-92456a8147bd | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7dcd709c-7a36-4b59-b760-9554231998ad | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
88952e0b-115c-4252-a2b8-1977d941ce9a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
91ac1360-78a2-4775-babc-ed1ea48cc12a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c779e182-c441-4de8-b6fd-b3b81fb0d70a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
78e81f6d-1bd1-406b-8548-412d7e2c353a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
3e25d63d-4117-4aa8-b091-7970e8178931 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
8dee2d31-6e16-439c-9afe-8fc9332d6d7f | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
b11e74be-b298-4cf1-9fff-8a32eabcf047 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ab5a839b-d9d1-49bc-957b-1556dbecfd4d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
2bd4b273-a600-4a5e-a6c4-9b6135c11bf7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
aba9bf91-affb-4196-b128-8faab3ce837b | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f0ca0045-f786-4618-8664-3cecb1df301c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ee5fe661-3c6b-4707-8e5f-ff0886e60c5d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f599e0ca-c8e7-4ee0-99cd-6ff51b213105 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f870d706-5d5b-42cf-a78e-5df2c6358e5d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
f449fc2a-d4bf-44d0-b996-c5b4efa1801e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
e7d139ee-40c5-4715-991f-976c48c684ae | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
93a67e1c-d8ba-4426-99b8-d3c37aa5dab6 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
8e9cb34d-8f3f-4f5e-b0e5-09ea686f46d5 | Pole | 2 | Distribution | 2020-09-03 | 2021-09-03 | Level 2
d0fc5976-1529-416e-84c7-0ea6f9ebec77 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ce6c2722-65f2-46b1-9a96-fd416b16eb61 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c937511b-a453-4fd9-a638-daa60d69aea4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
e8d5fc16-ccc6-46cf-aa4a-bfcbfc2ec23e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
e07f3cef-361e-4278-ba0f-5648cc6ddbf8 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
793ee3f0-4ba2-4fff-84ea-78591fdea2e9 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
59bcd9f1-8d47-432f-b030-1c50ccd6a341 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
32917b75-fa84-46c6-936f-b257d8ae43c5 | Pole | 0 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
42af15cf-e466-4908-8db0-71e72dc1590c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
45bc74f6-1240-4d96-ae1a-817faddc4129 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ccdf8de7-fa66-4912-b143-98fa6b727181 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
22192ba3-1c1f-46a5-a6df-d5f7e038f414 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
5c39527f-40d5-4b47-a41a-52aaed79e30d | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
8ff1bc52-0726-4352-b0b3-d831262c3a6c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
53d6e92f-b9b2-4d22-afa4-89d7fbc87490 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
a6ecf43c-7e1b-4d0a-875f-bc0a168ce775 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
5908cb06-5cae-47f4-9330-4d66a5cb09ca | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
a99bd2e8-35cb-42b5-8c3f-9ba750389135 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
fd115b23-38fe-43a7-9098-0892debe1571 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ffd402e8-8849-4e5f-ada2-4667ae6e3c07 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
ff161ed3-af56-4e06-93be-d635fe5f7b0c | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
feb31db9-739c-4246-b217-67c4d3479010 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
e716486c-85a7-48b1-a136-0e43efa7958a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c331422e-23c9-4e96-a6db-d4b80e116488 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
c997713d-0e5f-405d-b451-ab03b96270ed | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
cdf75ea9-fd3c-4178-a016-f0b75dfec632 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
eed2b923-49b4-4d34-b30c-8878b699ca62 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
a3997a6a-46ee-4788-8cfe-540f41f7fe94 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
bee7f411-d34b-4f10-9e31-44f694ebd1f7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7c1c83b4-0e4c-4f4a-824e-428a7ceeca4a | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
7c827a66-cdd9-4045-baa7-0c07096e7aa4 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
859e89c7-bc68-41dd-8bdd-17ed9bb5e533 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
8c0d2acd-fd47-410f-985b-9fff62dee6c7 | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
0f67fafc-bf6b-4578-9e13-e91edd72022e | Pole | 2 | Distribution | 2020-09-03 | 2025-09-02 | Level 3
8d2ed11a-e266-4d3a-b968-e4de2b10703c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c31566fe-07e5-4295-a95f-065b8ef2b747 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
a3b368e6-6baf-4913-8684-ba72e72c0c53 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
fea02365-3dec-4a27-bd4b-c94340890528 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
e26e8bb6-3661-4c63-bbaa-6c3cc6984930 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
795baf10-946f-482d-882b-8d48c7250918 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
9bb3c732-38c9-49c2-be62-6fd71f3fa4dc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
fe38089c-aa00-4512-9842-39a293bd7ed4 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
ecf7f048-e36a-477d-9aac-f03e39882b50 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
94e72f92-4961-4903-8097-99fda1b6b0c5 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
66c9877b-0b55-417d-b957-59ce26913e30 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
81f66b9f-bf0d-4df8-bb58-58316f9aabbc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
60bb171b-0d91-49cc-91a5-41d3778a5441 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
441c0487-52f2-4b01-a27f-1087429efb6c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
4afbf1a3-7284-4b92-ba5e-a590ac715f10 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
59c77c7f-d073-49a5-a5ef-b67f91b08aa0 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
5ecc8eaf-db7f-4dc3-9bd5-31dea1878395 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
15ac1b4b-aa67-43f5-8c09-912543d2ab64 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
02d04093-143b-4f68-a648-2ca57cd362d6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
1f10ed99-3f21-4bec-a67b-d0361a453726 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
19ce6161-2a94-41b7-bb83-fd8e507e286f | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
59e8d255-b4aa-4c17-bc15-739a56cc2794 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
6ad850d4-7b6a-42d4-be9b-d2f23f4be085 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
6d0a4f46-f766-4226-9cc6-5065b4a1fed6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
d09ba523-b3db-4310-8479-7eaeac594469 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
e5cd6b9e-331f-4cca-bc9b-a937b82f7a76 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
d8b1a01b-6d84-4a14-8417-27129ac077d7 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
ca0f3982-9948-4978-9c5a-68da3c4388cb | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
d359d0dc-37a4-471b-90e1-86dee87e79b7 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
d60536e3-4ae3-443f-b159-a8b533d22979 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
fa77a539-6489-4abd-8d45-4ce110d069cd | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
ef867c46-ca44-4738-8ff0-51be94d3b248 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
f53bf024-7ef8-4afd-b1ea-ca5b6f2f625e | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
ac2b75a3-7f9b-4b1b-a188-2420a6ef26bc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
b25c2317-b76c-4b2e-baf9-08196d89a979 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
b7c0ceb6-811d-440e-a34f-7c8a0c8015fc | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c877b346-ab51-4811-b848-e518db1f365c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c28ed16a-ec4c-48ba-b13b-cf0520b4de16 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
c25d9c3f-7191-425b-9ed9-a40a4fd5a201 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
9030198a-d4bb-47d9-b44f-05b835798f83 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
9099b8aa-6e93-4498-855a-05d35d914d04 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
8ee5b509-ba9c-4fe8-a9d7-59d9ec9fe80a | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
8673e38d-6d6e-4d40-ae6b-a1517c53f50d | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
85b45d95-927e-42e9-96bc-32ab87026aaf | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
84ad98db-b50f-45c8-93db-1d5014266fc6 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
93a9fd03-49b9-45fb-bdd6-33a86d0cee24 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
94a56a3b-fec0-4a42-9056-10ed26262c8d | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
943348fb-3449-45c9-8ee4-f0a88d9d7e66 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
96f21226-74b2-49fb-a8e6-04ab98866d82 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
a8d0f2a6-b09d-45b0-ab51-c2415c6b6e32 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
20d00224-fc97-456b-8e5e-3375e1bb6cb8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
1da421fc-c7c8-4de7-934e-869945778fd8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
1b2750ce-dd1d-4157-a1c1-82c9ce5902d2 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
0ceb36db-0fb4-40e5-899b-d8555958f19a | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
028bba8c-b1f4-4b64-8dd5-f2a76f3d706c | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
63bd84d5-f025-4cee-84e9-6378fbbeee27 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
6f32cb28-8681-4ff8-bcfc-30e14ef7d7d2 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
6983ef13-e457-4102-a978-20114d4f1878 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
450cf542-041d-4199-b502-74cf55cac66b | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
4ca9d859-fd9c-4ea1-b0d3-9bb871a98fa4 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
4bb75326-d7e4-4591-a838-240a5ebdf11b | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
43accaba-0103-4976-b84f-ade8668a9958 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
4289eb5e-9202-465a-8a64-a5835eec2231 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
3671a876-f064-4e36-b861-d75f1c2349f8 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
30f30b1e-da12-4b28-8673-597916f0fd55 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
30c82d42-2490-493b-9298-38f340310fc0 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
2aca75ac-e5b2-48cf-9918-ef81c8b6eff1 | Pole | 2 | Distribution | 2020-09-02 | 2025-09-01 | Level 3
2bf0adde-0e08-46de-92c7-a3163bfdf5c7 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
28a1450d-3823-4925-b769-f2abc45ac855 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
2540eb6a-ee4c-4927-8ce8-d8c47140014d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
38689df5-ed3a-4972-a768-a30870e2458c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
42a4c11f-be39-4720-b107-e78c23c73ac5 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
3f02a38a-f265-4bd5-a1e9-7d3f31b1a410 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
3cdebe1b-383c-4a18-a748-1482c78bd7a9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
4e54a16d-e9b3-4353-87fc-f120013a38e6 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
67abe691-35fb-4d6c-8251-a4930192d069 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7386fbb0-4cea-49e4-b493-95e94bd119ae | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
64ebcbf4-2e78-4dbe-ab72-a7fb5da8dc1d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
4f81ed6c-143f-43d5-a56e-cf9d22866d8f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
02cf0692-0c5c-404d-9e77-c8c59dcd1e26 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
42c4b99c-903b-4f0f-9189-d34173c9d46d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
bb64e499-75bd-4afb-9122-afbbc0e62239 | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
ecb93fbf-51c2-4fb4-96f5-d630752a56b2 | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
0748dd77-f736-4127-a1c7-4597a86d5c5e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
1f430726-98d0-43d5-9ba1-978a9a60c34c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
1d7ffae3-6ebf-4158-8c4f-b85f03cf581d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
1febe576-cd49-4c54-b733-cb53e2826dcf | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
f8a9b4aa-8c29-4e54-a583-cb68d849f0b0 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
a2e6fce6-c524-49e7-8e77-99f166a04b38 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
9593c5bb-8859-4d0a-b89d-579a93190b97 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
81148ac1-dd0f-4a8f-bae2-86d37b95eaa1 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7eb2c6b3-f8fd-4cef-b728-e04c7a10f61e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
6675f7fe-66e1-42d8-802d-e07e9fc5c7c8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
6598de81-29fb-444c-a292-7c462f6fa622 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
296dbc28-e97b-4fc6-88de-0830c0c866e8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
58f9fbe3-6e1a-493f-9c09-980197e63350 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
48d37046-a22f-4285-85ba-ea171c29b02f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
29a1421b-d404-427e-b99b-61dfc91c3c56 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
fbaea623-918b-491c-aa89-4f5454ee1360 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
99e5ce0d-a2e3-4967-99cf-486898fd6ac9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
f33666c9-d97d-45a1-b05f-29f40affb989 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
f0bab855-33d6-4d15-8d7c-142df5e52731 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
efb84d4b-64f5-4ed6-b6c9-e8aec7df8cc1 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
ed1ec319-8364-47e6-8a79-91132087eb31 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
d7103d61-3aab-4e98-a1ee-68f52282bc2e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
8c39bf06-f0a8-416b-88d7-b06f29272800 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
cd1fb2f9-721f-4594-8fcb-c92d7cada6e7 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7fdaca81-d2c1-42b6-a2f8-1482fa2809ae | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
9f76e8b3-6fb6-4bfa-be87-b983fb0d6ea2 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dd3f4ef2-aba8-4c98-91dd-e82cd8521feb | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dc7568cd-6059-4b39-af9c-748517347e14 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
d55162ba-c472-433c-adf7-518ef7186212 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e0997e6c-cca2-497b-b835-90d92aed5f6b | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
d09b8b6f-2ab8-43da-a8a9-e91774f6655e | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0452c33f-6125-4ed5-bec4-ed3b8a65b199 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dbf77031-3d77-41f6-a0ca-6594a216e747 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0b1a28ad-51a6-4e5c-8c05-7e1a04f884d9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0cd2f3fd-3c6c-4520-b5c6-70effe16c1bb | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
09d10548-d343-4feb-89b5-aeef8494d6dc | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
69de7782-3e45-422b-aa80-0f036d3c6633 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
71425b1d-dc09-43c6-a239-b2fde62f8e57 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
4ff2e1e9-3ff3-4dce-b435-7265a02b8a59 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
241fa420-b339-4a73-a778-7cecbd4cf154 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
300d4d28-de23-460e-ab98-c7a5345ee175 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
2d4c6ff4-4348-4546-b247-18a591d570e4 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
45c9ec24-b788-4594-9024-ee3ca5fa0444 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
40ca0c67-2eb0-4821-bdbb-9dad7fe6c6f9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
338c0afb-45ac-4e4c-9c9d-632970961463 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
094e8042-ad7c-4b45-9ac0-92f60ebb085b | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
13cb38af-c27c-4246-9024-ed6375b925f5 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0542e537-4b5a-417d-86e0-3039c14a5dd4 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
1f9fdb01-6ff5-4190-aafa-f6015a30eeda | Pole | 2 | Distribution | 2020-09-01 | 2021-09-01 | Level 2
108ac909-658d-45db-819e-1807f2aa0960 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
01eeb00e-9c7b-49d2-838f-9582360f1c3a | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
04b2b7c6-09cd-43bf-af84-e69f59035c1f | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e617cb04-b05d-4fa8-9b41-296590d76e99 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dac227bb-8a69-492f-9c47-70b24a146074 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dabdb48b-6ef7-4f76-b4d3-d417ea1282ab | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
d95fe712-ff6a-4a25-98f9-d8a8ac6e40c8 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e9753b4c-a67c-4829-8629-674a2fe942d9 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dd154be7-6396-47d6-ad5c-5b17a52e2012 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
fdcaeee7-fdfe-4fde-815e-8382fd31821d | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
00ea67b3-d014-4f72-8a56-1eec72dac360 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
b144cc85-6181-43d6-a3ba-9b8935c5ded5 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
c493cdc8-1f5b-4e88-b75e-42d613be479c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
be42a931-e725-48f5-870e-908d52782b4c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
9021155c-d406-4db8-9a3e-68dc02c56483 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
9cb83f2e-272e-434d-a99a-c2725ef521df | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
87be9d3b-5bc6-458b-9500-006d9bfab959 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
820202a5-1469-4bbd-a65d-4040b42e812b | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7e0a3f3e-3101-4967-9843-29656b0658d3 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7b419c2d-34a4-4423-87c6-d6d937673b43 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
7c1a5ce5-a610-49f6-afa4-05ca3188b95c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
79c89fec-cf61-4fe4-a3fe-e23ccd0222df | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
ce36b1da-8f29-4946-8802-e0958bedf189 | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
ce06f667-11fc-4299-8e9a-46d1a986fb8c | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
ce4b319a-5f73-48bb-8291-6378792d4f2c | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
cf0a15a1-73cc-4921-9e7e-bebccb0c4a6a | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
eb6920ce-79a4-466f-ae37-87fc5dbb44de | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e2ceb37a-cef6-4cad-8c6b-1496e1b1215f | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
dd62f31f-5529-4d25-aaa0-fe3c17fdabd9 | Pole | 0 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
0fd6c225-61a9-407e-bfc3-dafb7ba9ca3a | Pole | 2 | Distribution | 2020-09-01 | 2025-08-31 | Level 3
e11f3af3-6270-40e1-bfc4-d178f510132b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
d137aa0a-c075-4b91-842e-14ebb0dfe363 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
ecb2de1f-4edb-4d7a-9801-0deab7f37c3a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
ecee9244-d93f-497b-877a-e525f2ae0b8d | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f35cedbd-3d77-4094-b5e2-80ea631e78c0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
74f0ad61-dd7d-4a59-a5ed-51eaa371fefc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
84e1196b-0153-4b13-ad7f-e99e0b0852ef | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
95e3c09a-7baa-4037-a878-f9fd4f94af2a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
8a669dc2-aa45-4129-b35f-92d3a2dca667 | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b4617974-1982-47cb-8672-13a5f005fece | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b86717c7-beb6-495e-92aa-2cb90869310c | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b944276b-e247-456a-a95e-32db3f079b08 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b86fa922-6699-4783-8d9f-4e50e54009c1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
9e05c523-b7f4-46cd-a687-d0d682684298 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
062c2f04-7f46-48d0-99f1-44d9c6fb5188 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
bd47fbd7-abee-459c-a648-481f979d985a | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
fb61b037-8890-471e-acac-f042c5b9adb7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
929bed08-2f14-4b60-be02-700ab3355c60 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
875d130f-b150-4cf3-88bd-41320835ac86 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
3c500bac-f68e-4ec3-9062-5161bca625fd | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
71a2b5e6-6936-4a9f-b326-994511fafe69 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
2afb1480-243c-4bba-8e57-61d0019984e2 | Pole | 0 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
27c24d24-0b53-4fe0-a923-e7df32ce2b7f | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
51f67e93-04e1-4a0d-a2c7-8d664519d290 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
0d31ab71-ff97-4a68-a3e6-8278fe133e62 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
5d09086a-2e2f-4ebd-9091-de50065ea0f7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
6c63fcfd-6d66-4f0f-8097-da502f1d6929 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
6118cef0-2623-4972-b1f9-434eec962a7d | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
160d63fe-1595-4fe3-8ea4-be158c40c27c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
15eae9f4-1d60-4e82-a6c4-1e4f64ac0b42 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
c80d6530-165e-43df-a89e-0a8b2a734fc6 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e199d637-2e3f-41c4-abb3-3b385ba62c47 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e684fce7-e87f-4a47-9a9a-f646ae16aff9 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e4e3e716-8050-4205-a8ac-fae2c4107156 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
dc7688e3-764c-4518-97e3-803a2ff79980 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b5cd0e67-c0bf-4698-b3e2-625165f658d1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
b1c745f4-5083-4796-a1c4-c7b641705168 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
a7a377b5-f6ce-4f4f-ace4-b8cee00359b3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
dbeea258-a912-4ec6-aca1-384355ded232 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
89147cdd-15cc-41fe-abb1-3bb43f3ef51c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
cef986ba-2381-45dd-887c-dc7ba4435a13 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
800ada78-e40b-4af1-aedc-505aa75a5968 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
83325ef1-434c-4d60-909f-267d766f7403 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
7e116651-da1b-4b64-ada3-06458605b742 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
d539be7b-0e66-4011-9555-2d4dd5573359 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
d64855d8-8843-4cfd-b0a1-cc0e45b9d810 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f9664bae-2d45-46dd-93da-eff1e1a80b84 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f60a4b47-fab6-46a0-afc9-178ac64f8a1b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
e90d2002-95ce-4f5d-aadf-70b08778a2f3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
eae5ecf3-20c4-4bce-a8a2-fda3576491e0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f694ce95-f22d-4b53-958e-52cef46b9c83 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
f1a4d153-fb12-40a2-bfea-e50f6abe6ebc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
9d5b6d10-6ac0-452c-956b-dcb6b88867c3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
bf438a78-0353-4109-a0a6-8f4a49f4ace2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
bc12987d-59d7-49b1-b536-b51bc23cd288 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
357c69d8-cdc5-4058-8a23-d3e5e5cb98dc | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
c4f224b7-c0a6-41d3-b214-37ad5049330c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
52c93669-db64-4b56-9272-c6159f297f96 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
7c479afd-a0a4-48fe-aa0b-a59f482471c2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
79bfb517-adda-4dd6-a8ea-a2dc07e85f55 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
c6c67015-c860-4b6b-8bb9-91902f2bce86 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
80f63447-0533-4ada-b654-b9631e0347a3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
77897dde-06a4-466f-b792-15fd3254a2ce | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
84755190-9622-402c-9776-541b9d281016 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
87dac9fe-851d-4e22-b737-28b58fc487d1 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
886b88ee-a8e3-47fa-bd29-d00df34e9069 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
8b8ab350-37c2-49ea-9121-51d78a21db27 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
97307ef0-0ad2-42b2-bf8c-6571261d36ba | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
940b0d13-1312-4f18-8427-e8fc56481ec4 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
a7bda126-e3f2-43f5-a0cd-8d540dd75049 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
a53ad0a7-b18d-487b-aa0a-70a5023394d0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
020fd888-a02e-4dff-ac8f-888762d08506 | Pole | 2 | Distribution | 2020-08-31 | 2021-08-31 | Level 2
8d1225ab-0eab-4a8c-8e27-db536b3a1003 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
d2c99502-e285-4806-8cbe-815a720a4a89 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
1d16959b-37ce-405f-b3f9-32c129e77915 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
240db039-f27b-4a44-a5ca-8968d2e4e581 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
239ef321-6ebd-424e-b8bd-2461094f5392 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
17b46e6f-b804-46e7-aef0-5c7533f8824b | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
0b1116ba-d827-4249-94ac-d4119160e231 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
046dd7f6-f250-44ae-a93a-c471a0003ae3 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
0488d860-8e13-4301-b664-3755ac68f5e0 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
02c0e15c-b416-4dbe-ada3-1e7c60fea209 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
5419ed02-11a9-4ccc-88ca-ce8eb98e509f | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
59988cdd-c539-4a9e-a9ef-4c5d7aa4cd7e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
741d6642-5be6-4219-9783-4948204d0833 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
6c336089-7169-456e-80f1-c7736ca75aaf | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
43db67da-deff-41c6-aa3c-b1bbeb12a316 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
3fa3b635-1bb3-4829-9667-3cc4b4066e8e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
40df8c8d-034a-4fec-98bb-ef97da437b93 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
35c243a7-6cba-424c-bea9-943d130d74e2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
3576262b-4b01-4543-93a0-522ea5aba78e | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
3404e748-dec9-457d-895c-d21ecdd77e54 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
23c853f9-00c4-4b86-88e6-55f55127cdf7 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
25a748a8-a1d0-41c1-9722-b3f50ac2e647 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
2a3f068c-197a-411b-9db5-a959dcb804e2 | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
2d44d5c1-c15e-4408-8ab3-7dff52602d7c | Pole | 2 | Distribution | 2020-08-31 | 2025-08-30 | Level 3
2ea31130-dd9f-4633-9ff7-7d21c0b76b64 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
252e052c-f447-4585-9f27-ff6d6e2339a9 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
32802c40-6d99-4836-97d3-4270f76e3dcd | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4e07c79a-398e-4ad5-8164-9cb68a487c5a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4bae78ef-a3d8-46db-bb32-f8f1961b1542 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
6db70c71-2f1c-42df-9183-6f6b6a7b5ad4 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
77106a3a-903b-46e9-8791-ba85e33dd47c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
78b1e580-37f0-45c5-8508-2ad06b9476e0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
79acb193-3355-46bb-a41a-75f656adf4be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
59e77797-a3ac-4efb-96dc-4a1615400290 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4fc7c861-6692-452b-bdac-1640d3f59d94 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
649360f8-d65b-41a9-8b14-0a26a83052ce | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
02154b5c-5733-475e-875d-70f6576fcc8a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
1370bfcb-0f40-4109-8523-e6b71d9eaf99 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
20725891-8460-4ad7-a407-514b072b7795 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
1ba90aeb-83d7-4dcc-9ae2-e54b5da8e025 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
1e1a7f7e-aa1e-4263-8194-6dc8993e25ea | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
1f8a62ae-5655-4024-a415-325d13602523 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
93cbebe4-2038-4374-85d8-a9f38f38e7d1 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
91763030-325d-489f-9d19-412d9ea90357 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
9d1ac5b8-87b4-406f-a331-4cd47be1fc6d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
9101ec35-8ae9-49e9-a4c8-d57fe2f99a7d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
910b841d-ca3d-4e94-954a-7e3f4f32f836 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
8a99b69e-6246-427e-a390-c9e44aa20e85 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
87dc14f8-f0dc-4deb-8f7c-7a1ed269e219 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
849dad03-256e-433d-ab1f-793ad7b63aea | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
67f7b467-dfff-4428-8f4c-12d22df72a95 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
7c5cd56b-b536-4a10-8795-cec4fd40226f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
419d5566-43b2-4339-89d4-abf786f432ec | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
be6d0c99-898b-4327-bea2-ee9854cd983f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
5842ce0d-a641-48c7-a73a-11fece367d83 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
c0549cc1-32df-4aef-a0bb-82dfbb4f44f0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
aac16faa-286d-4438-8e85-59a574f86a0a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
afc49c8d-c96e-4371-8b01-2c61cdcb337a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
285a40f3-9da7-469e-96f2-f1a8c89f426f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
24af0108-e145-4fb7-ae99-f5a40dc152bc | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b92c4ebf-d938-4441-bd02-d24cee72bf1b | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b2473eb6-80f6-4e44-b4a7-664a0a0ab89e | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
f4af0ee8-60cb-4f1c-972e-f51c4ea9db87 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
f9ba4a13-894c-46ec-adf1-ec131be8da44 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
fe7277c5-c631-4eb9-9e36-a71d6000790b | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
8a94738b-4706-4581-805a-d7508ddaa86f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
e8d4726b-6658-4616-a51d-631eb3ac122d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
eaf2b7bf-d29b-4912-8ea4-494fe2d13d3f | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
96ad6dd8-e019-43a9-bdd9-349c15e2dd6a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
958d6208-957b-4c19-b64f-1366d39e83be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
9116c256-c4dc-4cf8-ba9b-d39dc25ff7af | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
cf15e6fe-975f-49d7-a55b-8f729d5208f3 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
cfd2919a-372d-45b0-b103-c425fc173eb0 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
d1b7adea-2503-4dfb-948b-d562f3d4aa82 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
d0656d07-e935-452a-8214-2fc076b0b432 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
a2b9158a-980c-4bb0-bed4-691466c63a15 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
a67244a2-99dc-4ed5-bfd8-c1bd2ef2f6be | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
a5ba7098-af8f-446f-b6f0-0db9c2190e0d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b3dda626-3f26-46bf-8441-4e20fab6bd0c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b95794e2-4d0a-4b81-87f2-13831c057df5 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
e4869d67-af42-40af-ad79-30f3e004cc56 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
d2122a85-6c29-4e2b-93c5-142f68cb2fcb | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
e233563f-1b50-420b-aefc-810d6cf91930 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
a1646d65-ab36-4087-96cd-b05087cc6f8d | Pole | 2 | Distribution | 2020-08-29 | 2021-08-29 | Level 2
78a8d2c6-8337-4397-a4d7-27042f54ba92 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
58a291b9-e925-40e9-aaa0-43ff0d862112 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
4c8d0cc6-f680-4d10-8de1-135fa285b48c | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
37dfb10c-98b5-41cb-a7ea-6080dbad0b7a | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
27bb5e92-20b5-4e52-a586-94f1912beaf9 | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
b91daa42-5b8a-4937-96cc-214d1d91d12d | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
c7426c0c-2f36-4540-a879-9365a174d7af | Pole | 2 | Distribution | 2020-08-29 | 2025-08-28 | Level 3
a55a437f-4d29-4531-b24b-bd172c4305b0 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
fe027072-d689-4cfd-925f-0d0b57ea48ad | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
e7e9076b-b97a-453a-a794-298d157389f7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d0198959-7a5a-4d2d-b716-47f229529bc9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
ba683b89-189c-42bd-bd55-a771492b0d0f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
c1a1f810-a23e-4212-ba94-9a7e1ae2f4ce | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
9210f170-5482-459a-b767-1ed0f6447dc8 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
89e8ed6a-1056-43c4-8822-efc4a2923a3b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2d39bc14-75dc-4ac0-b4a1-31d46948b1e7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
a889cad6-3f97-4eda-bf6d-489040f1c037 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
018c1ed2-a704-4cac-975c-6c447cde1844 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
717b07e8-4e05-43d4-9ac9-9f2d47ce7ad5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
fa549dd8-c467-4879-8f5c-6745fc543021 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2c43fd7f-0a5d-47f9-84f0-42f5cee1653c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
658d77a9-52c3-49d5-8fd1-cd4cd55db7a9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
098295a0-3194-4d6e-b0f0-00f6d410de41 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
0cdfff1f-d7b9-4da5-bf24-eb3fa7e9d5be | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
c8760a75-1537-4b14-8d24-784498b6d1b5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
c849c4d0-58e2-4291-a6a0-05e92d59f9b4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d252b023-84a9-475e-9b35-54887aa00539 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
e18ae2aa-2441-4dc4-a3ee-a42230fb04cd | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
dd1c355e-7928-45bf-8379-044e6fff89fb | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
e0bfa77e-b701-4216-b869-46b70a824265 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d3bfec49-5350-4530-a016-216aa13e0c1c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d4479c95-ddd1-435a-af96-aa47f6900c49 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d2b6c5f2-2e68-4538-8baf-8fb8a6507517 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d2dbf5ad-abbe-47ab-8703-243a822bd2dc | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
d330751e-8cdf-4091-aeea-e690002ea98b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
97478a66-a5e0-4e67-9956-d0a2c9cb25d7 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
989a3ae9-4376-4bed-ad43-7e95ed17d559 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
91489629-77af-472b-a704-e811758dfeaa | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
fadeeb00-f555-4535-ac21-5644dcfd06ec | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
f36fb126-0344-4d6a-b8d5-a972a9b898df | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
e7e1fc8d-b959-406b-a0f0-8bf09bc89ca6 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
fa290195-eb15-409d-86f3-43149eafba13 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
f04a10be-6ca2-4c17-97e0-23be546faade | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
efbb6374-935e-406f-93b4-f98e80901107 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
b0add2fe-8626-4508-9f61-558fc344dff0 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
b33ac467-9a25-4186-95fb-718498acf0ba | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
b8e566e1-4e8e-46ae-ae92-94221113717f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
b868d7b2-751f-4da4-8bb6-66dd65202301 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
1ecf6d8f-35cd-44ba-bfad-8f8bc8a2908c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
1bbc9d4e-5f98-4d3c-a8d5-ae1b6736e67f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
22f3cd7b-18f9-4273-bc58-592d3a172d7c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
22aaad18-0f1d-4be8-9fd3-43ccae48d198 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
aed0bfb8-4a5b-4b4b-9365-cd52214b81f3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
ac39aed1-7f6c-4a55-ba5c-84a88ac1e179 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
bc4bb32c-1e90-43b8-aadc-fe71bdd162a4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
c74f1c9e-e8c1-48de-a8db-a70736d33a9e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
65119417-d2bb-4d72-8255-643fed97dfd8 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
6792ca8b-be41-45e6-baeb-d8e89f109549 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
8629dd4f-bb13-4e13-aa38-72edc96ee2d4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
7e69918a-900c-4839-badc-f389b42b74b3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
80f1c292-d8ad-44ab-b8aa-3e5c19bb6bf5 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
7b8df639-6602-432c-8f3c-6ad8449e5a7e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
8828ad41-f56d-4175-967d-c391f39a0996 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
86abc42d-2766-419c-bdcd-c171faad51ae | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
9f492354-d461-4fab-8ce3-2d27b07c4077 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
9514ed02-f5f8-4ab3-a42b-792a3664635b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
a512b0a5-726e-4e41-9291-da8874724915 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
22d21458-98a9-46fc-885b-bfc1aadfcbee | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
19650172-b43b-4681-9819-4b227a0fe108 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
0ae6c236-98da-4c1f-ad53-e30ae104f337 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
649596bb-7442-4225-baad-cdeee3342fac | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
656a3474-e118-402c-b4b4-a1b934d97c14 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
5b0306e9-c656-4f5a-b553-5add00bc9e9b | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
58ee8569-2d99-4124-9bd4-32301f5e328f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
57b80639-bada-4ac9-9f99-646a5209da48 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
54ca7898-fb64-4326-a881-659240d53e8f | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
7462d635-af71-40fe-aafb-2428c71b078c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
4c000ed9-825b-4e61-a788-a78f17f43b8d | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
47676695-7d3f-428b-a6ca-23950b1f09b4 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
45ad98a6-b982-40ce-91ee-b5baef752587 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
3efbc659-b90f-4e1f-a4e8-354c5950515e | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
38e60757-40cc-4b7b-8ffe-b3134ca026e9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
3c1fe5cb-0cf2-4624-8b3f-c3d20a5bceea | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2
3b77507c-1f0b-43b5-8020-024453af8ba2 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2f83882d-da96-4a9e-b5c6-a1306ac8134c | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2faabb7c-eebb-4d7a-984f-167b91a13785 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
36be8bf8-b35e-4b96-9bbe-47086a979a54 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
3857a653-55e7-46c1-b39c-29a8c9df7b72 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
383b00ed-fd9c-431a-9a50-7fd5a9e59e09 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2e00d42c-a0ee-4987-968f-6eee4215b4b9 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
2cd4964f-54f9-4a2f-9030-a92d08681453 | Pole | 2 | Distribution | 2020-08-28 | 2021-08-28 | Level 2
2c0d3320-e06e-415f-82bf-950b82787cb3 | Pole | 2 | Distribution | 2020-08-28 | 2025-08-27 | Level 3
732e56f6-c64f-4310-8ff0-24b8e597fe0b | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
60747b85-18e5-4fcd-b6d1-a79930b5345e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
129abf4c-d429-4522-8b80-7014ad9394b2 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
226fe9dd-8318-4d44-9bed-6367747b2001 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
87d519ef-56fe-4c58-880a-a699047ad4a7 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
8d38071c-b43f-43af-87f4-67878ec71e22 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
c4c48f43-911d-4df8-a64c-9892edfffc89 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
7a5bdbfc-3f90-40a5-a7d0-611c441cb00f | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
b4544187-8b3f-46aa-bd11-bab0baceabe4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
bc67f35e-201a-4351-8a95-e26e4f36b615 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
301f12b0-12e2-45e3-b254-9346adb5bc2d | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
45a927ba-06e5-48c3-bfe5-e5d8cee38537 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
13dbe904-9f5b-4758-b16d-5607247b3960 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
1bb41ec6-65f0-458c-aa6c-7f2aa4551f7f | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
f34a9b28-5cd7-4a7d-88a2-d13c138c5076 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
007413c7-508c-4a71-ba33-6b12a56b51c3 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
d3ba9d5f-cfce-406b-ac3d-3bb283103ce4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
d2e236e2-77f9-4e2d-9a21-0cfd1c4340c7 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
c72c9726-c8c3-45ca-87ec-e9a5835b60c9 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
c84207f2-f38f-455c-8c9a-8eff55723067 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
dc22ddff-c170-46e0-a217-a0569d0bd5b8 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
db55c75d-cac3-40c6-bb17-bcd6cb16d793 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
9ab77f4d-12b0-45f3-9c01-b927f0ed0d58 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
0e35b734-55aa-4a24-9a4e-5c948587a09b | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
856ec955-a16c-48a4-a9a2-aacd3beb4c2a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
50756823-7823-4f55-b0b8-5a8033ab8e38 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
09f2f087-cf5b-4d0c-8bc1-97e6d8fb4080 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
4b7f6609-6852-4b9f-8105-eb749f349cca | Pole | 2 | Distribution | 2020-08-27 | 2021-08-27 | Level 2
5f51c0e1-2ca6-4cc5-aa74-65e76ad5affd | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
6ec94a68-fbd2-4c0c-99e6-7ccce0c7e657 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
848106d3-1601-4cfe-8e4c-8abdd31b94a5 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
45946db1-b2e0-4a65-a817-35d3f6213f5a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
9a1b273e-9121-4994-a3dd-1eb8e9b6701e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
1defc274-243b-4a96-978f-78ceade39019 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
091bb153-f365-4d07-8c27-ae892724630c | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
f2e81ad8-0d9e-4049-b150-976ad17adbc4 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
a3e1f557-fefa-4874-979f-a2a78f9ff93a | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
cd2d3d8e-f489-4a64-8cda-22b1590e7e68 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
032ad3ab-2b61-4217-a907-57e46d336d85 | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
1798505f-54cb-4398-86cb-08a8a90d930e | Pole | 2 | Distribution | 2020-08-27 | 2025-08-26 | Level 3
e939a423-0475-4cbe-8888-8c9647736f19 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
b637846d-8322-420a-8540-53ee8aa180cf | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
071c7c18-3be8-44d7-a6b2-964c51c68a3e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
baa7346d-0ea7-48a0-aba1-dfe196417946 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
f9f29c55-d913-48c6-8637-d5c1f49368e6 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
fd1904d9-72be-4cfb-8870-5c97cc031ef5 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
ef411a7f-9675-4d79-99ba-fc84c5628345 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
45bfebba-bb22-422f-bea3-3ad3a143a596 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
446d81be-8cbb-404e-bc7f-b56e9aed4f2b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
27a13a0c-95ee-4d45-85af-f2a41fead3b4 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
91886048-4ca0-4d03-a1e9-2dc2a82e1b66 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
0f297c49-8f54-42c2-92c7-47c82d023893 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d02aa2b8-aaef-45b2-9443-64365ae13e13 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d8deaadd-34d8-4a0b-9a29-d18a32500fdb | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
de085876-38a6-4ead-9c01-6002befaa8e9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
cfed5938-97e1-446d-84f4-b9a5f27ba7ce | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d18053e7-499f-4a62-ace9-81888de0cdc6 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d2a1168d-3186-4da5-92d9-d7938ed6ed71 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d355a7f6-c74d-457f-92ef-524cf8b9f733 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
9a88eaf9-1343-4e00-bdad-d69bb6dff177 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
d10d1ae8-fed7-4b57-95ad-26e705e8bd9d | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
cf7c8f33-bdf1-4785-b5ef-eaa8042e9a1e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
82ebaf66-a15e-427e-bc90-709990efd9ff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
cac7c7cd-34d8-424b-b54f-eb4a431fe292 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
e72751a5-9167-47aa-ba5a-edc24c3df84f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
e6826095-e636-45b1-b778-9b4bb7f769a8 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
ec6c28d2-8fa2-40ef-aaee-fef93f43df06 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3 |  | 0:00 | 0:00 |  | Pole shows rot, has blown arrestor, needs stirups.
7f6da5e2-be12-42fd-a778-f115bd52f6f3 | Pole | 2 | Distribution | 2020-08-26 | 2021-08-26 | Level 2
efa13b06-e773-4d0e-a26e-3891dac2cbf8 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
f481de80-e9f0-4f28-9963-f82822e1d28e | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
f5b1afa2-64a6-4e5b-a9af-358a8543650c | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
f543e580-9cd5-4e30-b2ea-2181ce187df9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
ae9fbdc6-7ac2-4ca2-afe6-da00053e77bc | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
aa6d6ad3-b879-4e51-87c8-9aa7134b5902 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
a99ec8cb-7f02-4209-bc41-4ce76aef82ca | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
bf2218e3-0c44-4382-9254-b0622e8b71ff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
4f3a3287-3c04-4963-b179-080fd499da54 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3f8dc028-e635-48af-85cd-f543515bf917 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
c72fb72e-9b56-4a1c-b1d1-ca179a14dc4a | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
c60d00a5-e438-45e0-b550-aaad016bcaeb | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
c573c9ae-8745-4fc8-ac84-5c3f9aa7abff | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
c3d61466-d21f-4e92-9d0d-26b77aba4abe | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
5bc13482-3f2b-477d-983d-3dab41bc0945 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
86707e61-9fb6-4489-8c3f-5b1ace96c221 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
a4f7f48f-db2c-42c9-9cdf-d1df945e981b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
a6794192-54d4-42fd-823c-b47efdb794bd | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
93401b71-f7c5-4f02-9b22-8cbc2ce288ab | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
973b227a-22f7-471c-b5e4-7b3ba06c0238 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
22e4f44b-a759-490c-b839-445240cebcc1 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
1d7c21e1-e5c1-4a80-a34c-e2da39a18e4f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
1dd0bae7-34c0-40d7-a0b3-535102a03610 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
1d14d146-58de-4807-b155-55bf84040336 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
00d60a2f-06a0-42cc-b9a1-1f60d02c75ce | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
01cb9da3-0b8f-432c-9307-4a7db2c733fe | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
5ff4555d-16d5-442b-b2cf-2e107f2a3d0a | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
5ca9f5f0-d72d-473e-ac11-a09b29592f8b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
5380d8b2-64cb-4e84-a136-2220df73533b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
52fbbcf5-e938-464e-8da5-69fa5c9914bc | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
52c02616-77d7-4ad9-9bc4-b384471c32e9 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
77770603-c699-451e-9cd2-c89bee6fe724 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
6a72f514-d73d-4f44-ad7d-4cc89870b633 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
6bd4377d-42dc-458e-8566-837751f2e86c | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
26c1af08-e315-465c-ac33-01d1d34b3e5f | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
29c2b704-f16f-4878-9132-7232a1bf211b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3397b717-6a1d-468f-a1f7-92d0ce515f6b | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3225f821-7503-4c43-a498-7a49db9521ca | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
33b0fef5-ade0-4330-a97a-740ba45b9e72 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3a2d51a7-dfde-4c6f-bf0d-3fa928e81646 | Pole | 2 | Distribution | 2020-08-26 | 2025-08-25 | Level 3
3c007cde-26f1-428e-bc0b-f0653aa957db | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3ec8fbff-93a8-4042-8e0e-69bdb5d8cc91 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3db2b8ec-f03f-4428-8c6c-29036754afe0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
471a5d38-e10d-4c5f-865e-c9911ce99d4b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
4639c896-33ba-4496-8a7f-7f79b405920a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
4bfebac9-2560-4f0c-a90e-91c671b8048e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
31890bb4-24f5-4e2a-acb1-1a0b516b8fca | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3787a36b-b6c8-4ad2-bbd1-957fb132a548 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
356c03e0-a104-4da7-8cc6-0bac1ac8e8d4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
369067ac-d08b-43a7-a9de-afebe9bd2606 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
290650ee-3e72-48ee-9fc6-a0c054289240 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
28b41204-6e2a-48ac-a8cd-775283fda1ba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
2b5a7faf-e1b4-497a-83f7-5b9788bef450 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
2c8ed2ac-b841-49a0-811e-814adf031065 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6d8b2cf5-7dfd-466e-840a-4ce363c319a0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6fba6b99-d8ef-499f-82b0-bd7e50630f65 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
767d3999-9b67-49b7-846f-b276f2ed11bb | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
53479864-ed55-4c5c-9aa8-5d6d490e13fa | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
508c141b-125d-4ba6-8992-7ad79f3ae5a6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
51634ef9-6b28-4308-a0ae-e33bf474a973 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5775b823-3452-45e4-9aac-6665444284ba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
591890f5-503c-4d4f-89e7-57bbf4109907 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5b36e71b-745e-459d-b7a9-3f095b896ce4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5c7eb72a-e97b-4b09-aabf-984b8fc9b0ed | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5ef33cea-2239-4aea-9dc3-0f0e36e42d49 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5ec95d73-3fa9-4f7e-b013-15dc90e532b7 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5eb99e4b-7408-4098-a89e-4f6e2401656f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
64d293f7-bc29-49bf-b88f-087ab25c52d8 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
63af1910-deea-4bc6-85da-9a84b0d40ecc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
611acafe-5c5d-4f1f-bdac-b6df3554ad75 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
05735387-2b6f-47f4-aa1b-ed79fed23364 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
04240fbe-8615-4a27-9b7d-38f9c513796e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
091ac45c-1b4b-45e4-a73e-5e1b04c88ce6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0689b605-fecd-4319-be07-2bdf5d64ae8d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0642d086-0be9-426b-b9ac-9a801b57a878 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
08208c8b-bc39-4294-af3e-51e6ea1fb3bf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0d52d201-79dd-40e7-a479-9a4d412d3fe3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0d80d7dc-eb08-4e31-8596-91016621b234 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1cfb9c8c-e949-4acc-b0d6-4a339c712a6d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1a437a76-6ca1-443f-a2e7-344b91852719 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
21d5df52-4e67-445d-ac9c-725275a44f0e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1201c7d1-dad6-456a-976c-22e94956bdf3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
18e5d7d2-a28e-4db8-89fa-5d50abd3457a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
158fc6d4-50af-45fe-b5f8-bc7132288d17 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
976892ad-4b3a-4468-943b-f56b5bb6d73c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
91e29412-5c62-48a1-abad-8ec5da3020d4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9e15aaf0-92f3-46e6-b145-a670d9c44397 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9acc4129-1b85-4117-b0cf-508654e0bfb5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
97e49778-1eee-4438-81ae-7040ea1f2905 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
974d755e-6c14-40a8-ac35-7f210a4b2b62 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9a7a7b73-82a9-49fe-ae6b-2f2ca24d9437 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9979df8c-c3f8-4472-97a8-231e91ff0e6a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a6b117d3-dd97-4fec-8095-8c70969cffda | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9fae1d3d-4f03-44b4-8af0-6f867fb9a838 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a7a57a60-4bb4-4295-955d-80307362806e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a0c62f60-bb66-4ba2-9d29-60ded7e52771 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
79edce01-d09b-4375-bf3e-f7596c38ed13 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8189db7b-78fc-49c1-822e-edc1d7fc8aac | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8376508e-1e64-4bf8-a050-2603dce0999d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
7cd7f51b-ae5a-43a0-bb83-dec7c55b1665 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8dced52f-467e-4903-b7b7-0dc9c8f286c7 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8e1d1a36-483e-4ccc-967d-8fab40e487f5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8f46bb38-599f-400c-ac58-15d64dcc60b0 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
881aac50-c5ec-4d3b-880e-5d45778a6ba4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
8ae398fe-aa12-461e-b480-6aa1975fd365 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
c2d5ac84-42e3-44ff-831a-07e366207228 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
c4928fa6-2792-4b9b-a09a-517dcd2d6ec4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6e70763a-c65d-428c-846d-f43e4c0bd236 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
73cc2647-e5df-4549-b79d-1c4c63f0d7e3 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
7c02d2f9-1c8f-4cb2-81ce-70833d3c0d23 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
7bfa8f18-4b4d-4e46-b2a9-9704e3009c4a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
bb270697-4253-4626-92da-a3daf117455e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3205ee93-d368-4642-91e6-c88ee4d6ca54 | Pole | 2 | Distribution | 2020-08-25 | 2021-08-25 | Level 2
35a966f3-027e-4a5d-bd6e-49dfbd6d8232 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
c00bbb7b-7e1e-4b98-9f01-f0c187deb66e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5330c84f-9b80-495c-b861-aaf8ac0fb7c6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
c0bd06ff-25d5-4232-ac6c-646d5c7a30f6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a9fcd34b-63d1-4e67-a632-bde997c30517 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a94e18ce-e4a2-43e7-b4c4-f086c045997f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a9468f7c-0233-4c00-ad49-6b3c0d72f9a2 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a8b870fe-fe2c-4a73-8b64-1d177e7f9bf4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9fcd68a0-7631-456c-9a09-053129464caf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ae0e8e50-910d-472e-9c14-ed5c90828881 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ab3fe644-3280-4509-a0cd-1ce9fe622fa5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
af5a584c-12ce-4b47-8f8d-32dd295a4b8d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
1cbbe529-3a0c-4c33-9565-d00c119d1b4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f58c4eee-d8ec-4250-96e3-17cc55ae72f5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f99159a9-291e-4c1a-9c09-802b0256a515 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
fbd31e49-2636-4be7-a69f-cb34531cf26d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d5dc456b-2d99-46ed-82bc-fd0788a1edff | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f2a0a66a-d58a-42dc-b1c4-a0981c57e4a1 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ef024a55-ce9d-4dd0-bb79-3fa86937f5a4 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f02875d6-5cad-4e73-b6ae-5148e25ee977 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f045205c-8ebb-4859-baee-63ab05173ec9 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e769cda8-1713-42cb-8820-35f39edf7782 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ea35d793-e5cd-4dc2-a152-599e7c234d9b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e84ff4e1-767a-48c3-bce3-e7ae339c907a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e7ffc440-e131-4120-a669-f5981d147d4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ed826ba9-0ab5-49e7-8845-63cc5f73c967 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
cf89e813-f253-4bab-8379-7659167d2626 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
86b1e3cf-37a4-4aa5-b67b-090768153103 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d1af7df4-4c9c-4288-a5ad-7bd9e91bad88 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
cd197258-db6c-4f2a-a989-758162450ca9 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d7d0c8bc-56a1-4ced-90a6-cfa8b42e83bc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d2c000c7-e232-490a-bf7d-939c6e93f729 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
9028919b-c486-4a59-8250-909e35736c4c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d480a95b-8835-4a16-8963-49cb101fb3a1 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e6503596-9981-41ce-9bd2-2b398f47161a | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e5d333d2-d180-4deb-9e61-69d19076863f | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
e1eb8ed2-847e-4b3e-8bae-a61b99063acf | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
b22f93bd-b5e6-41f8-91d1-d0f974aed8dd | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
f3ccbce3-9af8-43f2-b636-c929063fb658 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
898a9cae-21a5-4dfb-a943-0b88b56bd2ef | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
2f68e0fd-edf7-409d-a930-564e5e540938 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
96a224d1-7736-4cb7-bb4a-762385ab3a89 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
3a1eb240-3e97-4ea1-9eda-66939614ab67 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
5ff5527d-4d84-4af6-a6f9-28f25451bd7c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
924b6453-1ba2-4430-9b56-ee7133ea44e2 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
fe2a45e3-0af5-4a9a-b946-826f08320464 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
0832fd9f-32ff-4381-9159-a4301b83620e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
a0c8acef-2327-4529-a12c-0c556ee890d6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
b1a97f1c-ffda-4c76-9ffd-0b2b7bf246c5 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
ffe3cc2a-5f07-4aa9-a1be-7a193e39762c | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6bac055d-196b-4d53-8f2e-cf18665e5ba6 | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
72c073f8-70af-4d8f-8e05-1f186a8bf22e | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
b97a270e-f6cd-4842-8213-9cfac3080aba | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
045d07b0-95a0-42dc-a023-d0d23a813c5b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
69a7761f-4081-4dfe-b411-874b7a3f925d | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
6d1665d6-c454-4ddd-81f1-aefd3a96579b | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
d849511a-d182-4d41-b0e4-3dcf052a76bc | Pole | 2 | Distribution | 2020-08-25 | 2025-08-24 | Level 3
cc0e2af0-179c-49f2-9df0-54ac69d1af88 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d4751484-6b66-46bb-a175-1e5165e64c05 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e2ddcbad-e02d-41f6-896a-2ccece9bbd56 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
9417c7c2-27a3-4444-929d-99550aee1a7a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
8bf43cfb-1590-4a26-8d4d-d33057e1545e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
7d4eb686-fda6-43e4-945b-326a3b89e5be | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d39287cc-a79e-4099-932f-c76fbac2db39 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b4a4247f-7853-43ff-bdf5-b9ee9e8be258 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
a510717f-51cf-4a30-b879-a62b0bd6ef6b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1e030840-5d4e-4de4-a1fb-22270c81a486 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
eaa75bc6-f620-4fb9-9d8e-eada2a070958 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ffe7de67-0575-40da-ae6a-dbd636c5a3b9 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d505db20-efbd-4d35-aafb-f5a08947d83b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b70951ed-fb8f-4576-ba69-5605aa6bf76a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
30e20acc-170c-4051-a7f2-9b9c3cfe3ed5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
6459fb92-ba38-4e6a-9457-5d82fc8dca52 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
5c33c5eb-fed5-4029-b3b5-61a78f2d647d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
715570d0-7fee-454d-af52-64d6692fb73c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e26e8dc8-b761-4c38-85a8-272adcf8f5c3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
6635d941-e229-4b81-bbe0-ab452de061f8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2c2653c5-5a40-4b2e-bd53-100e06ad2691 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2bad306e-f2bb-4655-9e60-3200b56187e8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0ed56227-999a-4b37-af68-fdc8b0ea4438 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2
26b159dd-11e2-4cfc-874e-442d8894933e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0533f8d9-f359-4131-ad25-7aafad4fb232 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
07bcb6db-ebf1-451e-b2b0-cbac7c0752fd | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
9cb92896-3a35-4ec1-abd6-a0d3a2353e61 | Pole | 2 | Transmission | 2020-08-24 | 2025-08-23 | Level 3 |  | 0:00 | 0:00 |  | Bent stack
cde96f37-e445-4374-ba98-c3b43593b3a7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0dfa2a0d-43aa-4e39-ac2f-a6e18bf117a3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
8bc662ce-450f-4725-8101-d0acc4878a3a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b24ac6c8-e066-45ff-b166-d6ff54da78f8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2157e450-8c93-4cf2-91f6-d09d301af560 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
afb61237-75a8-487c-a036-783048f8dcc6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1c69312c-875f-4482-9837-cb21ef73029f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
f34f2a8f-96c7-4570-9d8e-2de9f097cca7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
255fc0f2-f0f1-4434-893f-38c5529608b8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
5f3870d1-710b-4bc3-a3f9-672b0bdbd90c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
78e55c04-9191-4af6-9b78-29a17131859c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
07159db7-db1b-4b8f-82d8-27cea174a573 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
efa95dfa-f8de-40bf-a995-227fe933aba5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0a34fe5f-7f51-4afd-8527-9dbf5b62a98d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
8d90996b-d904-47c1-a474-ddf27517edf7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
3bc9967a-d0aa-4488-a474-f51e867c36e5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2bf9a9cf-0f27-45b9-b079-82b5fc528394 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
feb7c63c-674a-4f50-bf0b-b62233d13bd4 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0f9baf43-159e-4d43-b950-dfda2d8b8b7a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b399f829-020a-4886-9382-685feb32e14b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ddf3ecab-d5c3-4b29-92f2-91b766903775 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
de0a915b-ead8-4c51-abbd-81b09d336567 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d9bf2872-c676-4c0e-9f77-33f997728f81 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
a45f56a7-54f0-4832-a465-50e732eb111f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e0deefa4-7549-4abd-b562-43394f0bc88c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
9db055d7-2483-45fb-b97c-470efc2fc826 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e41dde77-3a78-4ad0-a169-2815a08ec305 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
d34d85d1-ce18-4be3-8290-f469ee2d5f4f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ce47a680-b0b4-4448-825a-92bd03b2acd6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ccd99c5b-9b21-40f6-837f-4c788ec7d461 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
e8c7318b-28de-406c-9fa9-6a5bdb753794 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
eac3aa17-2c63-4359-91cc-5152023cdc1f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
fd829f2b-ce2b-4922-97bd-589472d85208 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
edfef705-72de-46be-b3f4-850b9d95c468 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
f3cce9bc-b5f8-479f-be7a-07dd22f5c398 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
f3dcbfd8-0e2e-420c-847d-81f844cffd16 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1531b749-4268-450b-9d0f-fff2cce2c90c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b85d380c-57cf-4c64-9aad-1b995413088a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b351a7f2-224d-4cd4-aca5-22122e479ac6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b76bfd6a-40e2-4079-a87e-b850886417ae | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
b1b4e4d7-b056-4319-9efa-242c22516399 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ac887a93-6032-495d-9319-29a17c154294 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
ad6bf67b-b398-49fd-8fd7-97736345f7b3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
aa45a9d2-4e27-4911-9157-4dd9ddad9397 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
c0b3e5af-87c0-40da-8175-68dfe2b2cf8a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
37811f8c-b4fd-4615-86f7-c7938a590e7f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4002d2ce-9bf0-4bf4-8688-f5857beca803 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
bc4f3a85-7192-43eb-9f56-26bc260cb3e8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
c750e280-511c-43f3-8729-73715423dd5c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
c71cbab4-722b-4b47-a86b-33136ea63b77 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
c646a5b5-fc57-4f5d-be09-9db12d1cc650 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
88308dbb-4ab0-46f3-bc5b-b11f0dbe02a1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
86d73140-d9c2-40dd-a974-9f80754c880d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
8746834e-548b-4ea1-8698-f62cdda2d08c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
7d43d86e-07fb-4fa3-ae2f-bd32605b066a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
7c2634b8-6da8-4192-8f1d-fbadfd13b428 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
7f7e2670-8d9b-4e1c-85d4-d16716bffc07 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2
83e35432-4064-4aae-afda-55c42783f64a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
82f87c6f-e524-4581-919d-c438606b880f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
73d5aba5-3d28-4a5f-bc47-6e9decaafcbd | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
a8c68e71-550f-4dd0-b3f4-8a768fe8728a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
a6f82906-da08-45ee-85f4-7cae9d535516 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
9c910675-6a06-492e-9ea8-b2026b6232ba | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
961222b1-4a34-4c6b-b4bf-b38aa160118d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
95ee95a7-d907-4b38-a868-7d3c30aaa927 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
15cea97c-174c-4a49-a4a7-d4af04b3b229 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
17c89b67-9c69-43d1-851a-cdbd04caad12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
194783d2-4339-4b29-aa4a-c5c6350ff681 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1c8199c6-504a-4cd7-824c-9589720bfa24 | Pole | 2 | Distribution | 2020-08-24 | 2021-08-24 | Level 2
1a86563e-f6fa-4bb1-bb29-907fe461d184 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
10e52de0-8ad8-47fd-ad88-4cc811f53231 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
20494439-07b4-4765-bb9b-9a10b9919d39 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
23c8095e-175c-424a-b73e-fa1e25bcb57a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
1a6bc9eb-b33f-4881-9b83-bd83882dc9d6 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0c576fa3-328a-4596-b4a3-93a10eecf676 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0f277fe5-d973-4160-9ef4-936e0bf5473f | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0f8278c0-5d4c-46ea-8eeb-0dcaae21c278 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
03959e41-5712-45e9-8064-9d0cd087740a | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
0509118a-5be4-4204-895d-5d9ca101510e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
65cffca3-84ca-47bf-b564-d75dac5cdc08 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
653e39c2-86c5-420a-93bd-823a9b33cd47 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
5bc97d7f-e75e-464b-966c-8eaa206a0d12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
50389f54-5bdc-4015-8318-a3b44dd125a9 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
53d78c6e-5722-4446-9f01-09481e51ff20 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
77517874-dd3b-46ab-af63-71f1e66afa06 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
737e8da1-2771-41f6-9524-ef0d3f6d00fe | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
74229587-c37a-4884-ad39-1b24a79243d3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
73bd8e10-363d-4ae8-96c2-68505d266d8c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
71d11db3-e944-414c-bfaa-ce24d212da3e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
6db749a1-1a5d-4c39-a1bd-7a12f61de856 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
6b2bbb73-3f82-4f9c-a0e8-927f38bcc7dc | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2c780323-ea7c-4568-a9a7-ff4d04d74b05 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2d72985e-be3c-4906-8b4a-289b9060b7bb | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2ad9e6bb-cd42-4107-b85d-713c55e549a1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
2a0d97f3-0303-4f8c-a13f-de23903c8c12 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
29e8f289-377c-4710-9e73-25e90601395b | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
21d20f80-bd9d-4cf1-912d-28a5e25118d3 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
25a10e5e-b5b6-459b-a7e0-d85acf4759b7 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
322d579e-b470-434b-9fb9-617cebcf406e | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4a4f11ce-fc5b-49e3-8e5c-9e6c3a4944f1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4bb4eb82-e238-4578-bb15-809d0e3feec5 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
46f1eecb-5681-420e-b167-9567e773d5c8 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
3bcb8731-93b6-4792-8428-c5206e100620 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
41002bd6-f76f-4d7e-a8ef-911facb83c85 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4083875d-9460-4504-89c3-7fe0e4b6405c | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
422d8a55-b179-4a29-ac5d-69f8235f292d | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
43a07d3d-b42f-44ec-bae9-02b23d36b2d1 | Pole | 2 | Distribution | 2020-08-24 | 2025-08-23 | Level 3
4857f2bb-d3cf-4fd2-808a-8f0e3a6c27ff | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
455f6c3d-6030-40e9-91e3-05c0ee958885 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
43f9115b-9101-40f2-b41a-9f811941ddec | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
455bf8ee-ce56-4cd4-afbc-b1fff98db057 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
4a2b7159-6a1c-4f46-b9e3-35f3cb7ea8fb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
4bd97999-6744-437d-a5d4-c513db99e08a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
36ae1088-f3a9-4747-9692-adb8d2bebbe7 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
25dde5d3-9c0e-4a3a-bb29-c29926f5cc49 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
291ff5a2-1c7d-4228-b267-69eca0d406df | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
2a2c61a2-e97b-45ed-8a12-51f2093f176b | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
2fd3bf45-f566-4dc8-bbd2-6241c11a7da4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
6fed99d9-a3a0-4e88-ba36-a623728d58cf | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
714cace7-bdee-4b10-a429-dbf01f0d8817 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
798006f7-b816-421d-a0e1-2119e0cc3dda | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
52c5b391-9858-4285-a4a9-b8dee6260a2a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
5047d9df-483e-463d-8cff-9352daba5a91 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
574110f9-6a32-4710-a86c-8915792b1042 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
55aa453d-d19a-44da-98b8-ae57d0a16e5f | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
5fcab607-b49a-44b8-a4d6-2e826096f695 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
03a54ad9-5348-4f0a-a037-bac73be6983f | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
fb35cad8-18b7-4afa-95fe-70cfb50e7f54 | Pole | 2 | Distribution | 2020-08-22 | 2021-08-22 | Level 2
1beb9eed-ba0f-4dda-9d47-f2dee27912a5 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
13c979b0-53df-42ea-b29a-161e807952fb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
138b0dad-0a7f-4e38-b381-4be4ee9a2f49 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
95344de2-059e-44da-87fe-eff7f0340c40 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
993bc072-b69d-4438-9527-14e3430aff12 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3 |  | 0:00 | 0:00 |  | Pole top is fine. O abnormalities in pole top
a09e5d65-3ee8-438f-a62d-1b04fd7abca0 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
a26ae3f6-57d8-4769-ba5a-d115a73f924c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
9f85ee01-9a5b-40f6-ab78-a3341136817a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
a4062a4d-8e86-4645-a051-5fc867a0e355 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
83ca67f8-eb62-4096-819e-6dd136034245 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8a735ec5-2713-47c2-91f0-271596c41001 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8f0be831-2257-4c68-899f-c8901df70abe | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8df58217-fabd-4d04-994e-a0b3d66b49cb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8ce2769d-c402-41bc-a24f-6d47b4a2d5c4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
8b3703a8-8b2a-4429-99e5-3ff8c9ff6d37 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
c2cbda82-13e6-4bbd-9b75-c594b88cfac8 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
c8f0f0b4-6bfd-40eb-b187-3e6bd285d61c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
af4c6123-df01-4cc8-9fdb-593b7b3e4e65 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
b1b3fce1-6e7e-41a6-b32a-45ae0b6a2b65 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
fa9c2cd1-dd55-4c6f-a638-084f2a81fe81 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
f9655750-ee7a-44a0-8f04-80135fcdcf77 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
f9fd398b-bc2c-458f-981e-80f73a36c463 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e9254aff-9023-4222-8427-0642bb90b0f8 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ec3dcdd7-9c3f-41f4-97a2-a325d4153c1c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
cd0f189c-5904-4f67-9b8f-c99be5fa5130 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
caf10615-6298-43a4-83e3-6b71b9675914 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
cb7df45d-150d-4d00-a026-402a1e1107bc | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
c9ce0c68-3e3c-400f-8a61-f541e4c13666 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
d3d58892-96e0-47a0-841c-47234b991750 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ce3f6533-b1db-4ecb-9b0b-109b863824b3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
d188cb32-1117-4adb-a63f-afe3184569d2 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e53b9ff8-377c-4624-8d57-fa8ae40e9fae | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e0474074-20a1-4fb9-b3af-d7641d8cdcad | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
e1b3ae38-18c4-491c-8fdd-e6c120a8b73c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
de3aba20-9ef5-40fe-a095-ac3e0dfa3f52 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
dadb22c0-33eb-4413-97e1-11d2f1da3d99 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
93e1ea25-ed79-4b46-9119-1df8a838654a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
38b0a9f4-2f81-4691-9e88-0f0f66e84a2c | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
9b6379f0-956a-4034-91c9-6ba5f91802f3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
fe7a8dd8-8790-45a2-b39e-812edd1361eb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
7dffac05-9b4b-41f5-bcc5-71667cd534e7 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
7205845a-d190-4a6e-b656-f2d75b1c0ce1 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
b6d072b7-22fb-42f6-97f0-6d10a2d1a6cb | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ed1c1b49-16bd-451b-9582-827f27784724 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
2ea60b47-c3cb-4980-86b1-a7d86aef722a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
1d911a6c-d51f-4dae-958e-1f864a1b066a | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ebc7b5a6-e101-4da7-b444-003b4cf170f3 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
c2284def-ce66-405d-96a6-e4b8f0699bcf | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
b6a87fb3-e863-43df-bbe3-65a8b7323bd0 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
ffe96216-db00-4a09-840d-c79543dffda4 | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
b6bb7f89-b211-415a-83b5-89fca471306e | Pole | 2 | Distribution | 2020-08-22 | 2025-08-21 | Level 3
f27d39e6-a57e-442d-bdb2-98c165f32a0e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
c7bbf099-b30e-4738-b921-90db42b3aa68 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
26359e5c-65fb-4759-b965-3ea13715fdf1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
fcf8168d-30e0-42ab-adb2-36e4655389f1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ff4ddf1d-a766-48e0-9172-3a52af9f0191 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
290bfdc5-072e-46f9-8c7c-2ae3816280ca | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
1f4cdf85-591a-4ffc-ba96-bd0cf71a06fb | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
708b9374-1d03-487e-9584-ffc790998eb3 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
4d33210b-47ca-4af3-912c-4b60024ea558 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2911651e-0244-4029-9114-11c08591aafa | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
16a43eae-fc46-4dca-bdfa-371eb00bda01 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
1b164444-d1c5-437a-90b4-67936087b88d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
94149a5b-8f4a-4555-8f20-a0e5104bd592 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
8ddd82c4-023f-4354-96e9-10b74739127e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
82fc94cc-c2af-4a25-bf7a-7f044b54971b | Pole | 2 | Distribution | 2020-08-21 | 2021-08-21 | Level 2 |  | 0:00 | 0:00 |  | Pole top has a 2GÃ‡Ã– split down the center and cracked. Change to level 2
ac4dd433-43cf-46b9-b6b6-568aeaa7c929 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ac165c9b-15a1-49e8-965f-1769af3fd06e | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b046d6b5-9f41-4f25-a3bd-d4b59c7628af | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b02a0c2d-4dc9-4cf3-b256-40d1ff9ef270 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b4bd537e-8cb4-4d68-9778-a2fdddf7aad5 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d4a7cb65-7f1c-4982-8440-273be46d92ba | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d8f09f6b-032a-4324-8d1b-23324449e63f | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d6c67903-58a8-4beb-8c54-31632b0ba073 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
dd7db983-9c8b-466e-9335-6082c40a9b30 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d32d0d18-c709-426c-b914-db34bd194039 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ff711c0b-540c-4490-8846-4c33771bf483 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
dfde9fdb-3f97-4c82-b1b2-c879ab736ccf | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
dd1a9414-6087-40f5-bfcd-a04017f99b0d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
e0db0126-a525-4fba-b218-0e4187c4e56a | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
e41a0e8d-d0b9-48f0-a74c-4433a5b2fe7c | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d424608e-b920-4abd-8677-75990a249ece | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d377aaf3-701d-4eff-ade6-67ccf33aab48 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b536a166-6092-4f29-9fd5-2143c80ce1e8 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
d065a93c-2b76-4ddb-a651-a0c8b1fec846 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
ec57f022-d105-4971-a0a2-a20855e356ba | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
edb3418c-512f-46d7-8443-d9a508cc7672 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
e9d88dc0-89c1-4ea9-93c6-5ecbad6c72a9 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
e9e09793-9636-4526-a13b-cb424e4e6672 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
eff1f07a-da92-4609-adfd-ff1fd725c85d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b3a1ef30-ccbd-486b-9c9a-92e252dc3985 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
b83e0265-85be-4f55-badd-a27c37b6edf2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a9428bfe-0632-43bb-b908-445120f3e936 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
c72408f7-cd4b-4530-a85f-8d9f97ef8ef0 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
c615d57c-94a5-409e-845f-f88c848eef43 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
bbed361c-7952-4b23-a0f6-1f576c0fbcf2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
8b195a16-3acf-4455-b579-1d75f8cac2bf | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
7bc4e703-2ef2-41ef-9c46-7c85d08bd49b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a4b560e6-1d75-40cb-a115-e7764c2bf7e1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a1f9bab8-3242-403f-8cf9-5a87f6f5b867 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a243caf2-ed7b-4888-a349-634bd5d851c9 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
a0fc2ac0-9e91-43d1-b7a4-6889bfaf3f09 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2b35dfb7-d39d-48bd-b6b8-b278f1df137b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
95dc0d80-5869-468f-b4aa-b34c8819e8fb | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
120a58a8-b0c3-41d3-bb84-da1f25905a69 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
19b5d6be-7b33-440b-bfae-1db15d626e24 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
18e3e729-8144-43cb-a98b-e6b18d99a77b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
17a99d36-eed9-40ad-9aa3-ec8d689230d7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
181416d8-5923-4b0c-8cf5-091451d27d45 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
1c0d7534-e690-4c0f-8e81-210c9bcee5c8 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2404b8fe-084e-46d3-bb1d-b3f5a56f3794 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
206dcf61-946e-4705-80f0-0bee6cfc2253 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2256753b-572f-461e-87d3-1fbfae08fe5b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
65ee9b37-0b7f-44c4-8af2-d2b13933f0f7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
648f480a-ca28-4729-b215-58ce1b046b25 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
5749e759-008b-420d-a6d0-a185be758918 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
578bccc9-a71a-48e9-ba9b-019c616783d4 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
503edd13-1405-4654-a70d-285465a4416c | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
724b8804-5e98-40e5-bfce-24e62c9b9745 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
7254d6e7-1cbc-47ee-965f-dfc73cb7012b | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
7464383b-60bf-474d-aa59-bac45025e8b1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
74a9ec57-97db-4ead-8bac-a45b658a4724 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
7046a946-aa1c-4421-8be2-7dd426be470d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
70170b6c-6ae3-4efc-9e25-bcfa526b0102 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
69a730e0-23fe-49be-991d-2d0509a6f407 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
6788174a-cc61-4c97-ba38-c500cf43cfd3 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2acb6da7-16de-41b2-9381-8595a4426468 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
296e128c-6c61-446e-ad5b-afd9fea966f2 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
381e8af2-1000-4949-9235-6040da3568ef | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
38b3744c-8a90-4ebe-87f6-f8014a1f0e82 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
2e56e6ed-6bf7-47b7-a989-fd412931f776 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
460515e4-f6fc-4904-bab4-ee97dea0cd9d | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
423b9eaa-1d6e-4bcb-b984-8aa9c584c967 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
3f9a6f37-595a-4641-af67-8a8e3faba5d1 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
3f0bd24e-ceb5-4c24-a68e-c51b13344ab7 | Pole | 2 | Distribution | 2020-08-21 | 2025-08-20 | Level 3
434e1e55-a04f-4756-a7c0-817ad9f97aa9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
3ecf158b-3797-493d-81d5-fd83ff9946dc | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
30f1e271-0964-40fa-a120-75f53679680e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
36ef9d67-8998-401c-99db-330696393cd6 | Pole | 2 | Distribution | 2020-08-20 | 2021-08-20 | Level 2 |  | 0:00 | 0:00 |  | Will not meet clearance issue
721d35a2-de0f-427b-b61f-7f643b0aa11f | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
4fd93608-f794-4726-98ec-6ebae4779bda | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
4f27343e-ad92-457e-aac7-df14b975fe9e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
20701f49-a4ca-499e-a442-2596fd6990fc | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
1cfea449-468e-44f3-b0f7-b7ad4ff6b767 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
11423224-828e-4e7b-a7b4-e6a7f4f3c75b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
046ce6c8-929e-41ad-9d43-7239d315b280 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
02c955f1-c0ea-43fc-b9df-a55734a8a077 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
0caca01c-db4d-483d-981f-f6230422b8d3 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
080420c0-d108-4057-976b-0baf9dd9aeae | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
04929957-94a1-43c6-94b2-8be6b2b3a8cb | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
0784caf9-122e-43c8-8c37-be7a23f9a8c1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
96a498b7-c844-4958-bb33-ff0cd3a453e1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
a72476b1-1614-4a7f-a97a-c9dece18d7f1 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
848f5619-1dc7-4ae0-8906-23ed199b5d6c | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
886216f1-afd0-4ead-aea1-e3c173754212 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
c129ca7d-ed0c-4254-b9c5-641333619ca9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
b648586b-3fc7-45f8-acda-058f3a15894a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
9ef66c75-aebe-4eb1-a36b-4093959608e2 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
b199ce3f-8cd9-45cb-b9c0-53378891b31f | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
d7e811b2-3721-4feb-8b2f-48d8f27ba946 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
98e69d14-a840-4608-a01a-e405bad3fe08 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
e7a8049b-d174-4b61-891a-9918452f9b24 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
e760087c-bb48-4c00-807c-29427a41bb11 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
4f406a31-3d44-4b89-a8f6-8409844660f9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
ccd478d1-b4a5-4c0d-bfaa-7a1a1e03360b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
d3c62967-cdf2-4341-8c88-536b7a30af00 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
b56321e8-08a1-4803-b2cb-5b0812b55ade | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
e4d07fa4-9cfe-4bf1-b285-49503dfb244a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
defbe8fc-f958-412a-81a4-402a0bd1ef2b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
d9cfb9d4-94f0-4570-b691-1d71d00d4460 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
d8d9b280-4a8d-4609-a737-dab6528bc1a4 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
f442b77e-cb66-422e-a8ea-e0596c67fe0d | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
ccdbe39e-5ed6-4209-ad84-c42c01c0e7d9 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
c7c2562b-fae5-4fe0-b7bc-89253ca5dd1b | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
85cb32f2-1c77-4b97-a761-57b880250339 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
c900045f-f318-49ab-a830-a32f27695c96 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
ddbff38c-084d-414c-be5c-478240ed2285 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
6b70e287-fac6-479f-ac15-3776e01d5080 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
6d0a4a2f-a8ae-46d7-b318-eaca4913fdc5 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
1d83f641-e17e-4a91-8a61-e8bdfd5a64f6 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
20037d15-fed1-4a24-b0fc-6db8a39955be | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
49ad1175-8d66-4c68-8b57-22fad176056d | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
080bdac0-5181-43a2-bd24-ccb91e925547 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
5c4017fb-fb9f-4167-8ffa-ff9fa7db18f7 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
31b4b520-499d-4290-beaf-7175e7afe03e | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
a2c94345-e9a4-4cb8-8844-a62af37f2111 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
5d030dcd-6912-485a-8ca6-26e1afd3f51a | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
9dbc7287-6aa6-4a14-a5a1-7a16aef3d578 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
7bde8c50-9400-4f08-89c3-a50632f44772 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
5a6a2a72-367a-4962-800b-11cdcc428e29 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
5a5b48ef-833f-433c-8525-bbb26d81e678 | Pole | 2 | Distribution | 2020-08-20 | 2025-08-19 | Level 3
7a138981-8606-4d31-a4d4-a8c6a97c102c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
9e8598f9-4271-4af8-8da0-1b32cbc19519 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
a15867d6-bc7a-4471-93a7-6b786534f678 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
8873423d-378a-4af6-8175-12a054520c81 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
df5462c4-331b-426f-a4e3-8d572bd288e7 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
d47facfb-c829-4102-9d60-886dbb6f4db6 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
2ff4b31f-402d-4b9a-847f-a93209956482 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
5baf3b98-ea75-4c18-807c-ca39ebbce0e6 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
01edf49b-3de4-47ab-982d-47a4243edbcc | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
0fce14c2-b555-4cb2-85c5-4778229405c9 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
29ef90b9-2ea8-4d25-81c1-b69b50a2a0f5 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
6089591b-f976-451d-964d-673d2418874e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
46ee302a-de1d-48f4-9c81-235337c7ce5a | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4369a697-45f6-4f7b-9df9-f4f7b462c5a1 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
44650334-5131-4870-9b56-a54802ed159f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b64f6e58-abcc-4bf5-bddb-1644a64c1fdb | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
fd24a9a4-ef63-4840-bf6f-6a64480f8e27 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b5e5a689-b304-48b7-95c4-8966b0c2c421 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
40564c82-c3c5-42f5-b53c-f0cf24544ff2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
60ccd8e9-edda-4b5c-b244-68f461cdf38d | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
73fc4211-e067-4eb0-b436-3fb0d00b87c5 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
72663578-72f0-4579-a218-40d4ffbcb42c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
66466e1b-525a-4fef-91c5-975c99eb4cfb | Pole | 0 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
09808cdd-b7ef-42fc-a490-904b7dd1a99c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
01c4f200-327a-482e-9420-a4b74a4a5075 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
86cff8e1-2989-4640-887d-a7ebab1535d7 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
93e27638-5729-44b6-b534-6dd6a741a88c | Pole | 0 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
f273512b-7a48-4b91-8957-7ec60a965b61 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
f4949f60-25a4-412f-87fd-b0a786be3b29 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
fe2f857e-3972-40cd-b6d3-f614903a91a2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b138b43e-3a72-4d7e-9bec-fe0735ea3a7d | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
d6f421a1-cce8-461d-84cb-3ba32bf766ea | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
e2b7dd9a-1898-4c4d-9607-98687ba39676 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
e6698b4a-c239-4dea-95ed-1e676c83091f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
d23e8e37-7c92-4ce9-a670-4da00fff9de4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
d7f8e1eb-e163-4890-ac62-6a7fe6dd5a02 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
ef678ddb-5991-483e-ad56-c631c85f8f82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
f188fab2-03c6-44bf-bd2a-9054c657b3bf | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b2316b78-20b9-437b-81e0-045b39f6d125 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b45f0373-1ad9-4cfc-9278-7dd1ef3fc6ec | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
b9188a3e-207c-4189-ae54-2358ce7e1e40 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
175f1662-ec38-44ef-a219-48a74210c46f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
af802fac-1402-41e8-83f8-cc888a43f354 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
be93ec67-49c5-4db6-8fa6-0246a9f2b08a | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
bcf8b45a-8487-4bc7-a8e0-d7b363680fdd | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
c749493f-04f9-4087-a555-ddafafe7fbb2 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
c68bf7be-9539-4f76-9a6c-7efed0a94a35 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
8aa38f18-e81d-45fa-a12d-856edbb8a495 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
911e85b5-ab1a-4e89-9ef3-c3e6760fd084 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
83ecbd07-9907-4007-b566-21b3b11a86d4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
7c01e3ad-66b4-41b2-b0de-539308e0a955 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
7dd2857a-bc0c-412f-8aa5-d3dab831e510 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
a74eadf3-e41b-41f7-89d8-5deab2996789 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
a8b5fe50-2c39-4c8a-b16f-793e6f10556a | Pole | 2 | Distribution | 2020-08-19 | 2021-08-19 | Level 2
a4c41253-5265-412b-8590-07f4f07df7d4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
9bb9420d-a7db-4ba1-8e1a-90986940145e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
0f0aee21-1d63-490f-aa79-ab3c2850a307 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
1095a1f7-41d8-41b3-9c4e-9a910624b565 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
13b15da0-a934-482c-8aea-a35a358d0040 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
50790657-e212-43b6-b0eb-0dfa19a1ef78 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
517133dc-441f-41ae-ae6b-f6d1c433af9b | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
5709ba8f-816b-43cc-a89f-343c48fb2433 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
59c8fc01-639e-4a13-8721-b44943e46e04 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
6373f150-fffd-49c8-9097-937ea25a8796 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
5c5719c5-37ef-4b2f-b782-42795374cb57 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
5cd5616c-6f7b-4efe-bc95-970d3669ce69 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
760f5dc9-240b-4373-9fd2-bd08f08ffbac | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
6a47356a-c822-4bdd-8074-be17c440c57e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
6ce62036-f92c-4482-9a4e-7534971edc88 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
38ae9491-c1c2-4fe1-9970-b14b5754915e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
327120d5-ab67-4602-b121-4b63dbea0812 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
33cd40fd-68d5-49e7-b28e-e770d27a3c00 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
25c7c50e-099c-48f9-985a-8d9503285c1f | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
2663d61e-a9ea-4e55-9800-dc9d5647d33c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
2d30ac7f-4f81-4118-9d5a-3ad711d7ea80 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
3d5fbd3d-7774-4969-89ec-0980349482fe | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
3aac25cd-18d4-42f6-8c11-945552fadc82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
39cfc813-49dd-4991-91f4-e8cbf7365957 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
462f680c-8c4d-4283-a9cb-c051c3deec25 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
470755a4-efdf-4ab5-858e-073bf26e177c | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4546ef99-0c98-4b26-947d-dccdf90e223e | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
44c3317f-eef0-4f98-be55-2fb244b082bd | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
443da5f5-40ff-4a48-9f8a-327cd6c62f82 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4b5f1c21-5255-482f-bda5-62bd6be6a9b4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4a42eff8-044f-4311-bf8f-00f6465692a4 | Pole | 2 | Distribution | 2020-08-19 | 2025-08-18 | Level 3
4c2d2957-4fd0-4dbd-ac63-7e0dea3a1e58 | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3
451033b0-1758-4568-969d-3e6279118a92 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
453f9748-a296-48d3-bc0c-75f3653f60dc | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3bdcc904-3039-4424-9d36-549b44cb56a5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3b562847-952f-4668-8d90-f27aa9d9b91f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3d2f3246-cf5b-46b0-b0df-359820ccc940 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3e8e3315-076c-4172-b85c-a110b3fe42f6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
2ae4a931-d30c-4f3f-89da-a031b868cc2a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
26219c65-5417-4716-a7ff-8be83d87fc8b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
2699c35c-8f25-4595-8b5a-24986bdef181 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
325673a1-1d31-4513-bb68-1edff9a97ef5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
38a44b26-7dce-4e61-aa8f-6e11d11e11f8 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3548192a-ce1e-4a38-8955-52f57a6f4b0a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
6eb674d0-4723-45cf-808c-a6510fce7c67 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
723a389d-ac75-41d5-b5d8-4f27cc245836 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
71be8d32-9e4f-4ba8-9a75-0a15e922a5ef | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3
5c93a722-7f9b-4af5-9dd5-92d18edd7c26 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
5d3b9254-7f11-4f5f-8862-a67c30ecaf43 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
55031869-6936-4e29-9700-a254e3170282 | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3
5339741f-0c7a-4201-a3b2-18e80f377f46 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
1485262f-ca19-4be9-a707-c50541d554a7 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
10ff2d43-ca85-472d-b3f9-89a9e90f8ed5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
184d0a28-a8bd-4c03-8f99-a834837b6407 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
1c5a017b-5683-4c5a-a9dc-c9a8bc2a8c84 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
224c7fa6-2ef0-482d-86c0-b5ffd950b6d5 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0e057503-38a7-46ae-aa73-161e8e7ef00b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0ac890f6-d830-4aba-afe8-e8cb2f2cbe2a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0789bcda-fabb-40fd-b0e1-8c4a342cc89a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
0874076c-938d-4888-9586-ba6f7d508656 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
037f4bb6-ff16-42da-b708-14e877054505 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3c71a6af-e6ec-43af-9769-781499060547 | Pole | 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2
9d8c5c96-3dec-452b-8fd7-06d7412a2ce2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9cf01289-ab07-4f46-a4cb-49479fd9534e | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
a4e88dda-84b1-4171-a033-afebea131e5a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
a214e533-0789-4696-b2a9-2ece6e343bb2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
94cab6d5-9e34-4e37-8330-ababbf11eafd | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
a877e69f-5cc3-42a3-b5b0-a702e90b470c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
811b999d-c62d-44de-8362-ac538008ba82 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
88c2707f-b121-4dfe-ba0d-789fdc2ad72e | Pole | 0 | Distribution | 2020-08-18 | 2021-08-18 | Level 2
876d703e-467b-4f13-8bf1-09bcf9af4b0c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
c5106f44-b5b7-4ebf-af75-cfdf2e5db260 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
afeb76ca-aa75-4cdb-8b3a-b8808df05d7c | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ab444256-8dc6-43fb-8978-e839456af26a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ab54b250-806c-4168-9e03-52650d47f7fe | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3
b98ff61c-6834-46f1-8b40-a043d0ed0251 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
eee074ca-3b9a-4ef0-bace-a361bcb9bafb | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
b3f06a93-8ca7-4681-bde3-fdd11bf86898 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
f9379adc-61d5-4744-975e-09ec8614da3a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
fc031a9f-3809-4d57-9c2c-fb6c3df2012c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
f651612d-e0f7-4ad3-b916-652e318ff48a | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ddac9ace-d50c-4064-a84a-cae86ceb6a90 | Pole | 2 | Transmission | 2020-08-18 | 2021-08-18 | Level 2
d3372f1c-4378-4ab0-b729-13c787dc499f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
cc8ff79a-1a27-4cba-a419-a08822ad3c63 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
cab6999d-b6b5-48bd-8d28-dd7cfd260ea6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
c96067ff-f30a-44be-8894-ae47b1c897cb | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
807f6987-52b6-44eb-a6ae-a1bbc3705f0d | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
e43255f8-b40a-4e16-a338-755868481c97 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
7c185836-647b-4458-a807-7d73341df16d | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
e02bb811-23f5-4894-93dd-95d83d0c2e11 | Pole | 2 | Distribution | 2020-08-18 | 2021-08-18 | Level 2
dbc9e480-1418-493e-8314-302d2f3b7778 | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3
ee2b3e8f-93ef-47df-99fc-a7b002203614 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
fe9d2d69-7444-4b6f-b96e-185ea21440b3 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
c9295586-d953-48be-b98c-d4c5aa968576 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
db5738d8-5ac3-4429-9c39-386354d2b0c6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
dbef4d57-e519-4a39-bbac-b0006b42557e | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
8c36461c-d479-4f66-8004-085b96e9e8f9 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
92c8b363-e6f3-479f-b643-2fab4f152750 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
88dc3f26-449d-4b7a-a4d6-7cb485ff3f5f | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
b5c34493-c737-4286-b045-6d7fd8db6f70 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
afc78ec9-a571-452b-ba2f-e79af29f8ed4 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9f3147e5-5128-4243-84df-eaccad993da6 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
8dc2f7d5-a641-445d-954e-03cfddbc812b | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
1ca66a6a-b843-45b7-8176-ddd870e21726 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9918e2d6-29a7-4611-8937-99fd60659765 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
ab4369bc-bf7b-4d8c-adc1-b875d68c72c2 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
18c35cdd-0462-4221-b7c8-aa3c5f36de69 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
14e9bde6-b391-4cef-b64f-54fc50ac9ae0 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
b70a66b1-d15a-456f-aed5-d477aeca7050 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
6945c72c-9976-4651-906e-5bee6e6fa0b7 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
5b66073f-3706-4bf2-ac6d-8c79ccb83394 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
5455ee15-0018-4cd2-a5d9-13c1d34dd292 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
4e1a04cf-15f9-410d-85f2-6aecb95a8daf | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
50e8adf4-2e8c-4ffa-85f9-fb1e5b90b288 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
50aee005-d410-4074-841d-9dd018e4d149 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3e1a716d-83c3-41d9-842b-7f83dabd3755 | Pole | 0 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
2f55ab03-6f57-4749-8aa2-98d5b1b65d85 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
2ca83bdb-bd87-4fe0-acb7-bf91f62b1ac6 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
fe49a6bf-4d67-4632-b08d-43d24b4066b8 | Pole | 2 | Transmission | 2020-08-18 | 2025-08-17 | Level 3
b707e4ea-b55f-4b59-9a73-22f5f85fb903 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
3bafffc9-76f5-46ee-a490-d1d6aa2dbcdd | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
fe5ade2b-d90f-4d54-aa14-feb27297b4bc | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
21c1ee9c-aa5b-4755-b5a2-549878cc4158 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
9c430c21-d296-450c-85c6-7a156c9579ed | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
99a23be1-a46e-4f88-a1f7-5923c07a7385 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
7fc858fb-3310-453c-baf7-a569db6ebc6c | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
6188d1ff-0ee3-40da-ad4f-5d1365767bc8 | Pole | 2 | Distribution | 2020-08-18 | 2025-08-17 | Level 3
c870e2d3-6d0c-4a62-a313-96eac2328b7c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
2569924e-25dd-4879-8a83-33ccb91bae84 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
62a5cb90-d3b1-413b-be86-8b8d736caa62 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 0:00 | 0:00 |  | Pole top split
1cbc349e-79b0-47be-a206-08701acd7cbe | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d13ddcea-d37e-4bdc-8e15-bdd0df4b7f7c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 0:00 | 0:00 |  | Split top, loose braces
9d310ff6-a880-4d39-806b-4b1436070d18 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
b9e9e230-6219-4fa4-8658-65c23f0e48f4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
4bff3a0c-b7d4-4331-98d9-79d737515a9c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3 |  | 0:00 | 0:00 |  | Hotline clamp stirrups and HV sign, addressed. Pole needs replaced.
89184d9c-8092-4880-8664-008afdf3310e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
2f8b5669-282b-4c29-902d-dfce109c59be | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
56667e94-ec85-4255-96f4-c0de81248b9a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
51bfe483-4817-42c8-acbf-272e6b90525f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
7f4f1a4a-e575-404b-9e28-e92223e83328 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
16943990-539d-42c8-a9bd-3f047fc6e42e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
3660f45a-20f7-4ce3-8114-0875951c52a3 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
a5edbeca-083b-47da-9a1c-4da37cef2b88 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
39b9e663-9ced-4562-b1f5-1c480aa6437c | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
272bf117-5927-4e5b-b382-2d6ac69e0760 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
aa78fa36-7666-4e67-986d-4320d1e1367a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
53a5f6f2-079b-42f1-996e-4219f6bbdad2 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
52de37d7-ab7f-4b7c-a2de-48c6320659a1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
debf420f-9b73-46ea-b497-ece854a4cf1c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
9c9043f2-2844-4085-b533-1fc2c13d8251 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e4be35d7-263d-42df-9492-8650436f5c1f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
cbb6c1e3-b9e3-4d73-b866-0d23ff8da89f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e1202c72-2e24-46e8-953d-f9f4ba387f33 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
cf20e5ab-7994-491d-8c48-f71752e2f9da | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
ced65230-8ce3-435d-b3cd-049e512f70f1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d29561a7-8405-4a5e-b5b0-b3878fd954d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d794126c-74ad-4908-8120-3f7f9e5ddc95 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d7c21f9f-9c8c-4152-8c10-516a78c9d365 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e753e589-d39b-4991-86b0-3828f5360e5f | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
e6fd3be4-9c85-4051-a8d0-4eafb561c95a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
f5f39dc4-94a1-49da-a567-f006b67ac6d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
f959cab9-f391-4340-b0cd-0d11d74b9c1e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
f1ce3b9f-2443-4abb-a2a3-7c38ba45c3de | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
b45fece8-d42d-467b-a9bf-e4345b362c31 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
b4031d0a-bf36-4ad6-85ac-bdd9db8d462b | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
ab4083ac-8340-4d40-a7f1-f0e60e08b1bd | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
7c78dff6-e125-4a0a-982d-a006e9900bce | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
af718e4e-7ae4-4c6d-9257-92113c342ee9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
af6d4ddf-7a25-4c52-b979-d7f12bec1ce1 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
674722df-ed2e-4c30-9007-ec44c3488dbe | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
c4ffec8e-09cb-4b96-9de1-e0052129e00e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
a64ba217-551f-4721-8ee5-0aba3c66d87d | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
84ebc02e-44a8-4f14-b714-69c304893e6a | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
a1fb95c3-ca88-473f-a284-331bfaa60309 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
a28035f5-b9fc-4552-a383-28122d72a803 | Pole | 2 | Transmission | 2020-08-17 | 2025-08-16 | Level 3
9ccd0455-f1dc-4168-9bd6-d878bf39bfec | Pole | 2 | Transmission | 2020-08-17 | 2025-08-16 | Level 3
9a79125a-0329-4a6f-b019-f9aaf71bc318 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
9605d1d6-55c8-44ad-b1ac-612445ea4b72 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
015c2480-1383-4725-8533-0ab38fea2293 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
08ff3a2a-40ad-498f-b462-f6eb83c963f2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
08c5f11b-ad44-4173-b76c-b2af354dd03a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
228db20d-9b6d-4847-9d06-ce75dcc32870 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
1e4367f4-2c9d-42d0-844a-303194872c6c | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
161875ca-cdbd-4985-acce-7cbd1bb65e03 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
d9772245-ef52-40b1-ac10-7eb5f1fd87b9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
117a341d-5365-441c-84c7-940a097f0c4e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
831c2938-fd76-45f8-a96c-d200701cf205 | Pole | 2 | Distribution | 2020-08-17 | 2021-08-17 | Level 2
576ee34f-d0ae-480e-a976-b8a92aaa4971 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
55ba0fec-d19e-4fcd-888a-c18a6a2dacd6 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
58a009cc-6878-4e63-8c78-b7de977c6cb2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
64246506-5d8d-4682-8ec3-846c5c787df9 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
744d1497-f8e6-444e-ab2d-f2d73c919b1d | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
7a19c449-2489-4962-81d0-a9af56ddac00 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
6de3bd9c-aecb-4059-a602-2de95260446a | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
6c2c97c0-5e55-4339-8638-93b95ed5fb96 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
32c57763-aefe-415f-bf04-69341fe31c28 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
307d8277-ef02-442b-8ab6-fd169e6ca394 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
251a0bb4-83f3-4b78-b4a1-ff8bbb9bd5d2 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
28146eac-d943-411f-8889-deb211631540 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
2c114db1-886f-437c-b12c-1fb65ec0526e | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
42dac4db-8e0d-437c-bd90-a7b328ae40d4 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
411ed8e8-44b6-4879-84ce-aba8c2921428 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
45864e66-f483-4cc7-b32b-c96d77bdbc94 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
48030b4f-b861-452c-9a92-4d2ac63cb503 | Pole | 2 | Distribution | 2020-08-17 | 2025-08-16 | Level 3
490506b0-59ae-4dfe-bfd9-035280b95623 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
31b80abc-d615-4816-9e40-40405a6bb6b5 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
2fd3d56b-fe1f-4ded-bcb2-2cc3d2d4b39e | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
3617d431-76a1-4fb2-90d6-8ccca747ba20 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
37c174c5-ddc5-4789-ae06-578e8fc9b9ac | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 0:00 | 0:00 |  | Pole rotten needs replace
6db03cfe-d3c9-4a60-bf9a-6a3a06467bad | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
7a92742c-4d5a-4c14-99a0-425bdefdef94 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
7562d2cf-2ae6-40f3-b2e3-b6bd5d1d3eb5 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
651987c7-7b3d-4845-8225-0d3f6e7545c2 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
5a78c1b9-2070-470d-bdde-e2224132a44f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
54d9c368-af37-4469-96f2-0939976416d8 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
4e5266dc-8573-4028-8b70-07e5a49a2076 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
4f06e832-849d-449d-90b5-0407f1d96e58 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 0:00 | 0:00 |  | Pole top split is not an issue.
1f8b0832-4db5-4553-87ff-77ad4bba8b8b | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
0211e8f8-b6ff-4830-876a-48b93cbd08b3 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
05800e39-c7d1-4b5b-a76e-c1c836d516bf | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
95f95bff-3d70-4da6-81ed-04f0d659589d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
917ce863-0fe6-4434-9de4-9a2c0da7560d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
a00f4933-b1dd-490e-bbc0-55da1ce2c64a | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
a1508a0e-8f74-4b2a-a416-b04d2dc3bc78 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
a5866153-51df-47a2-93bf-3e873729c1f4 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
87c9e503-e571-4bac-8aa7-fcd7e8bf852f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
864418c7-5d3b-4f8f-abc0-4368cf03e0ad | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
89ce9c8d-6786-49e6-9aa1-7f340250f257 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
8157bf08-64f7-4a4b-bfbf-6327d5b1c540 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
c0089e0e-773a-4bf5-812b-46dcb14260a0 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
325e224d-b5ed-4082-bebf-a6a9123295ba | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
ad650805-040b-4934-bb05-b83e22cbb3cf | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
b348bcf3-f28f-47ac-89b4-e3176fb40321 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
9fcde381-bc44-4000-8ba4-81d05f6e1a21 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
b12ca565-c372-42cb-877d-59db9e82567c | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
e6f40188-8ccd-42dc-b207-172408ca5641 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
eaff128f-0a14-40a6-9208-ffa70e24cf01 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
ebdd8ec2-c8f5-4449-913a-6a4716585bb9 | Pole | 2 | Distribution | 2020-08-15 | 2021-08-15 | Level 2
d85f947c-4a9c-4601-bd86-bdc3f739bc44 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
d3aa8a2b-a2e0-45f2-b265-3e250c51223c | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
b5041df4-aa6b-4bc2-8fe5-3481ed039ffa | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
da66590b-acbb-458e-bbf7-1a6ea54ae44d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
dc6c0124-508c-4376-9344-e45e9a81c989 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
5a4bd463-45dd-4f9b-8430-6ab6cc5d383f | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
91488720-29f3-45dd-b103-f3532d961515 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
84dfda52-8222-4551-b993-ea82dc159805 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
236604c4-9294-4cb2-b998-4538b47637bb | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
3b5d666d-34e6-4f28-a604-061ce9813249 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
d3a0fe46-3ed2-431b-9a21-512f8fafd5dc | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
fd668582-c75b-4e92-85c9-31d0f5ff75f7 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
388da06a-d796-4401-b0c4-f0cd0f4f2d88 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
46eeaf0e-dc62-4353-b605-a110e7b7fd8d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
a755a4c7-4357-441c-9e36-528414d4e700 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 0:00 | 0:00 |  | Pole stubbed and cracked. Needs his-strips
e5a0be90-e1c2-4b80-bb6e-442635ce73d0 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
4836bf34-9269-4123-913f-a0d04f2507c3 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 0:00 | 0:00 |  | Pole needs replaced. Com equipment attached. Transformer is leaking.
d9696caa-4404-4b8b-a194-cfa39ac5ca60 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 0:00 | 0:00 |  | Pole stubbed and cracked.
fdede023-b3e1-457a-af88-47fa1f6bc977 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
c327e379-d2a0-4dc2-ab9e-39d5cf7772d6 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3 |  | 0:00 | 0:00 |  | Pole rotten, needs replace
989286d1-8539-4f15-98cc-8c47ef735132 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
b8078155-979e-4aba-bb46-95049ffb048d | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
f4e36da8-0b4c-41b7-ac66-aa197514d18a | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
1152a63a-2a0e-4a25-a0eb-47f97a651d89 | Pole | 2 | Distribution | 2020-08-15 | 2025-08-14 | Level 3
00319bbe-a52c-476e-b92f-8d67cdf9d297 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
c9243a75-de5f-4a88-a89c-a2bb48669383 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
7a87e7a4-aed1-4461-9030-04ec47814c10 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b8b81add-0d53-499d-804c-a9aac3129e4d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
fe4ee3a0-bb3f-4d86-9fab-f2a147fadab5 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
fd48d4f7-bbed-4371-8804-6bf3397382e4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
916dda97-dded-4eaa-ab95-6abd17098b08 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
5997646b-b80e-44c2-9263-36338731aa4a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
637bed12-26e7-4561-8741-64f2eb372892 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
eedee0d2-7dfb-4736-9154-5cb4b357e8f9 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | 0:00 | 0:00 |  | Prep for repairs
36ad5913-8cd7-42c7-828e-773a1888feda | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b22e7a3e-f920-4e74-83e7-699d76adb9d7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
60df7a83-e2b7-41de-899a-89af255ae74d | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2 |  | 0:00 | 0:00 |  | Pole cracked from ground towards pole top
5c5bcf67-be2a-4afd-a874-d7038f1d4ae7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
81845573-b07d-441a-ac12-90653a46c47b | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4a8a7b63-cd99-40de-a477-f7d6bb21a378 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b3577643-12b2-4928-93db-ea4baf3358dd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
acc70cb6-b822-4522-bd21-77a603905cf1 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2
6b02b67e-2e4d-4745-b5b9-311f0e5e1df2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
09cbf493-2005-4a68-b940-e61155dfb64c | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b12f5e9c-ac18-4f59-a37d-23c4f73437f2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
dfcfe4cb-a756-4869-8793-ed9f52bef5a4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
dbc64b55-54d2-467c-b22d-bedfa8d9bbdb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
d9265647-f7e7-4826-9bba-6aa620dbb0b4 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
df364ea1-a48a-451f-9d09-93d13c19b9c5 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
b510c45f-c689-4756-a5f0-85bcdfb9fd50 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
cb687a34-fc7f-4367-909a-801ba3a2f0db | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
d29b1171-3281-4930-a1bc-d58cd937c498 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
d87f2178-c65a-4df4-a850-af77b89e9907 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
d8a0f4e8-e9e9-4120-9f5e-72e19a1e6697 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
f441916c-100f-45ef-8be8-ae11692e3706 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
f87581c4-6579-4365-ac11-9e767761d3bb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
f5f1b57f-b77f-41b2-8658-ef6b33321f46 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
f5d233e0-974b-4eb2-b89c-97752c3ecdd8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
af0f6cf6-8a59-4e8f-9a6d-f31231274621 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
9bf5754d-a001-4fde-be2c-31e52e3d5eac | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
a8e69d42-444a-414c-b6b7-5ecd7bcdcbc8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
c5992e72-d5f6-457b-a13e-0a23aae26ae6 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
813f1274-0381-4685-8794-0c66d8792b4f | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
81b1a7bc-60f5-476e-a969-4cf9c68186ab | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
84fad399-0aff-4cf7-8f39-292466aa5455 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
7de91a19-9b7c-4271-8135-01f57ebd2ffd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
7d1fde50-8e5f-40dd-a9df-d7f1231b335a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
8b4649c4-c71d-460d-9116-d412ea6f609c | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
9c9e4b93-3de4-4b0e-aa47-8de5833f9240 | Pole | 2 | Distribution | 2020-08-14 | 2021-08-14 | Level 2
51d6d732-0f90-4609-b7db-509332696458 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
9b71307c-dfdb-4711-ab2b-e8a20fda2dfd | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
050067e0-6d79-4f65-bdb4-63af528f4cde | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
0c6e0603-2876-40b3-8edb-02adc4b6a0d7 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
1e6d628a-6c56-445f-910e-ddd39aad3653 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
12212548-c09c-4714-bbeb-3bb6160da972 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
535619d8-01bd-4ca8-bbbf-c2d65559bef2 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
595085a2-838d-4df9-9371-e890f10e5b05 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
61f32093-3370-4fe6-a39f-bf511de8c9c8 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
71ed9e41-996b-43c0-a0da-87e5e5794a7f | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
6b233bca-6b80-4348-b1f8-c6c3b262269d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
6ad4a601-476d-4bd6-b3ea-8bfb599b5d1d | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
38195f22-dff8-432d-a9aa-aa4f964d8417 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
2b2c9ece-414e-4010-bda5-1b1853947f6a | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
2ec6b880-ab4c-4c7d-bab9-acef35d11f55 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
2d3df91d-46fa-4f41-b735-532d21dd4620 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
2d9c2da4-f42d-4073-a244-09d973798eb6 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4a1eb129-0dfa-43e3-a3a5-660a31b01deb | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4bd83973-63e5-45ed-b637-947215fed7ad | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4718a946-4fa3-4680-9206-dd33e8b2362b | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4482735b-d051-420c-b600-760171a56049 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
43c865df-3edd-4779-8ab9-a6d019d91180 | Pole | 2 | Distribution | 2020-08-14 | 2025-08-13 | Level 3
4e8bef8e-2743-4080-afae-86c519fd1614 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
3f29dd34-b394-40bc-a23c-fd0822e757c6 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
3a1f98c4-1404-4e8a-939c-242c6c19fb4f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 0:00 | 0:00 |  | Hard angle and pulling pole over.
2a17f094-ddf9-42ab-8c8b-bbbc100136bf | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
259f17ef-ae74-4b75-a494-b74bd2b14169 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
3832ffc3-0b2e-4f35-99a9-07c81315971c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
35eabd22-f0ba-48a0-82b9-d5c0824ba6bd | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
2fd1858b-a392-4140-8238-e41b1c936db7 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
2f10f4fd-3dfb-4327-a5f5-8a5937e213cb | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
2ffbb6ff-c91d-47b7-b5b5-7e2fe0033357 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
6bc203fc-a5bc-4c9e-8d48-49fa7686d540 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
6891b239-c848-45c5-a415-81309ed07811 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
6742c3d7-5014-4e77-89f7-f4dd00e36b2e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
697169ed-7b13-465a-b903-3ccc0b399a61 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
701fb98a-9bcd-4ebf-8292-7ce080a7d127 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
70f916c6-9efa-433b-971d-73c8f98228de | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
77377869-009b-45f5-9a6f-9ff1fb1b9245 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
792e710a-4a81-4ac8-a018-451aa41700f9 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
61d768d2-4b69-489a-aee2-8bb8c4011422 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
65e9d501-aef8-489d-872b-ff59bcab4d54 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
66def900-7600-469b-9faa-a900856c8057 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
5d67f1eb-e5cc-4c50-8fed-144807184d44 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
5d1173d0-097f-4ccd-82b1-ee73f52109ee | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
60e3173a-965b-4318-9238-e3b7f0b93670 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
5d2a72e3-8216-4bca-8ec0-14fe4a0eeb29 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
583ae9ad-9adf-4156-8917-af0092ae617b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
15300369-90f5-4123-8f9e-a01ff2fe25c7 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
51f4b82e-c7d9-469f-82d6-abd100f15a7b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
16055c60-98fa-4f7a-a5de-94d6ea4d85ab | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
1651e3d4-1dc0-4225-92f1-72f11ec1776b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
1bdc4cdb-ebb6-4fc1-a07b-4f54862572b3 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
21abeddc-f80c-4a61-bfe5-8534997917af | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
0bd215ab-5e21-48cc-8770-8902b6d57ad9 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
0cb84489-4dea-4c60-b1e6-bbda3cdb677b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
0987eb82-2978-44d0-b7dd-206f5e9d4d47 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
affad873-f0f4-43db-8a53-198fd472fe7f | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 0:00 | 0:00 |  | Dead tree near line
391ef15f-25e3-4ab0-a834-d5bdc7b4ba78 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 0:00 | 0:00 |  | Distro and trans x-Arms needs replaced ASAP, someone has came by and changed out the fuses to fault tamers.
9af49be3-c04f-4d03-8e26-0ce756b8d94f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
99e54a94-e9c5-4199-8644-420be1579690 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
978d0485-3a87-47ef-89f2-4b917128c02a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
a054ba27-f49d-4d8c-9b15-37b8990d174e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
a42a1a2d-6bc7-4f90-ae84-278747f82a67 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
85bc66bf-7687-4391-8bae-dfe9591a32bf | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
822f6a92-8e50-405d-a46b-85d0e9042c7c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
c49e23c9-b579-4bed-9a7a-30f0ddddd831 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
bd3a9134-f914-4056-aee1-43c622513394 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
c07be6dd-70fd-46e8-b60d-b1efe6c8aace | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
a9eeaef3-a442-4961-8028-a646554e990b | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
abf02d38-2319-469d-8797-bbc3891146c6 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
fa21e8b1-a328-4e21-a4ad-8745a8356b5e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
fb59c5da-9d0a-4da4-bf22-de2ebc621d54 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 0:00 | 0:00 |  | Service is attached by wedge-bail on both sides wedge-bail is on service but no risk to public or reliability Considered idol hardware
f478c9d4-800d-41d5-a4b9-d609414a4d2c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
e91a6999-153c-4f2a-a9ff-d77fcf7a87fb | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
ec7930f0-7f62-42ab-94a8-67802bfa1f5d | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
eedbf0fc-8bef-4e17-a50b-77e1bf3cf520 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
d3884099-007a-441f-9aed-cb2f0325a23e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3 |  | 0:00 | 0:00 |  | Crew changed out x-arm to 8GÃ‡Ã– fiberglass, pulled up slack on guy. still needs HV sign.
cb9ee7ef-be23-4461-982c-460181a3741c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
cd4f05de-8abe-446a-afdd-4ded7fc6f609 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
cb3e3a32-9690-4b29-afb7-4eb7d3009591 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
c2704209-38af-4944-9cb7-c02752a67019 | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
835fa24a-4fea-4055-ae6e-c1e69ed2cb69 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
e426e70c-83f0-4d97-b9d5-a489163aa24c | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
9636fd8d-8d86-4506-a690-0bf7744b2b66 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
084c6fbf-b655-4c63-9ec0-848f235c8a5f | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2 |  | 0:00 | 0:00 |  | Chance Glass Broken
2d0ff6d1-73bb-44f9-bdc0-35a427a5eeb8 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
d69c52d7-283c-4a45-b673-0af2dbdc1454 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
ab71b13d-5f8f-46e3-bc54-e128437b681b | Pole | 2 | Distribution | 2020-08-13 | 2021-08-13 | Level 2
0b68a451-7788-4a8e-b2f6-22963332269a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
912b9fe7-67df-43ea-a42d-aac7b52cf35d | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
933f8ec1-0cbe-4407-b4dc-31448210676a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
cc490623-3855-4887-8da3-a719f481840e | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
61cbd3d2-64a2-4fa5-b64d-11106447c187 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
98017901-7984-43a0-93fa-36d3fb9df275 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
a8ef3ff7-fe49-4a2f-a780-4a1e09c6a143 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
b7088299-9c9a-4b05-8572-02b81c71cba0 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
fc2a9cc0-b145-4d7e-82b2-581f5e3dae9f | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
bdc915b2-a1db-4ec7-8168-55c97915d24a | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
8f5f0054-1f46-4772-83f9-8dd4799107fe | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
d355c38d-c720-455a-88a2-474753e17391 | Pole | 2 | Distribution | 2020-08-13 | 2025-08-12 | Level 3
d554d4b8-0a2b-438d-b512-c819333654d7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d00bc188-d698-433c-9534-1cb37aeb1b34 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
dcaa42ba-9515-4d6e-aee3-4c0aa0546ef3 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e59f7617-02c2-4c0e-9eb7-bc597227bba0 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
ea472a04-0ce6-437c-85ff-7bf44bc30848 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e69ace64-164d-45b6-8455-2ec519773e4d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e65968f5-7e18-49b0-b78f-24e86351a72b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e75e0ef3-2fb6-49ef-9d05-22ac64fa2702 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
faa99ad4-c658-4666-b88c-3afb5c8f8d3a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
91a5c92f-e227-4365-8b07-fe02f190015f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7d4202ad-95e5-4a71-93f1-310e925e4c79 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7a3541b1-889e-4a6d-b340-564b584c4e06 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
b968f4da-c5e9-44ce-ad50-349b008e5504 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
9f5365f7-b542-4a6f-a2ff-ed82ae082bdc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
aba25529-66af-4f4b-a588-37db8b05b647 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
aacf146a-42a3-4109-ac98-33d80b5e8f82 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
b195fce0-5199-4a1b-8bd2-05bc2a915fae | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
acd58bd4-fd0f-4884-8143-6e2288e4e7b1 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
fd30dacd-455a-4da7-9961-07ba7fea4e6f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3c75e3bc-a35f-43ea-8937-7c1cf618d08f | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
dd42ac7a-70eb-4ae6-a220-401ffe8e2add | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
df53b8c1-aca3-43e2-bcbc-1f46e621a914 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
97191a49-590d-4e3e-bd8c-2aec9ca6b0ef | Pole | 2 | Transmission | 2020-08-12 | 2021-08-12 | Level 2 |  | 0:00 | 0:00 |  | King pin bent significantly
66ed57dd-4f41-48a5-9515-c46c6bd8832a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
6e4eca6f-784a-422c-827f-2f2c48f752ee | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
6c87e8ba-2deb-4a68-82af-9846a0c87df2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
5644e16a-bcab-4ca2-970c-151153bb536a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
5e4d35b4-9d47-45b9-ba0a-5cb3ebfc7c83 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
4f526001-1185-4acd-a3e3-60ddce305dde | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
488a93a6-640b-4d58-8782-45cc2e8fe4b8 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3110ea1c-5bd1-457f-b99a-15d5e39200e2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
2e5352df-3597-40e3-8c21-229edced4bfe | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
2a755204-0c03-44e8-b0bc-d6f4c4883d86 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1ef6a2c4-325d-4852-ab96-9204729e35d3 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1d900489-246c-49ae-aca1-fd1c881bfff7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1d4c5e9d-6f2c-401c-8741-1b03d4455716 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
22ccc302-5f2c-4519-9e35-c569fdd1b59d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1fd5a071-4782-40fb-8103-2383846142bd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d888170b-00e9-44fa-96d9-e5e4d9ac1296 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
cdd62acb-4b9d-41e6-bf85-3409a1cf0683 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
aaa4e655-a1e2-4c75-8b2f-e43d1bcf638b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
591e4568-81ee-4b27-9730-20c49031e646 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
0563280c-a8f1-4a91-bfb3-3d31002c2dab | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
5c4ccbe4-8c31-40a8-8222-7620c29065eb | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
e0948f39-4546-4dae-935a-73b449e2d3b4 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d8efe912-1f0c-4e76-b582-024667a4f7b2 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d8afc4d0-96cb-4f8e-ad46-f144fecaa543 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
ddcb61a9-cd8e-4026-8f84-a3cdbba63208 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d392dcdd-700f-4565-8e05-732f57e64dbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d49c7247-c0fd-420c-b685-e841c29f4220 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d49a8cad-d360-44bf-9505-9e71c449e7ce | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
d8069c6a-1394-4a06-9af3-e65bf837d125 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
ef6f1ff6-311e-4627-8108-c055103a940d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
e75afbaa-988a-49b7-829f-34e66362cd25 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
8fdcb8f4-6664-48f7-9d21-67c6ddd6a9cf | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
b40af3fe-918c-40a1-9123-9487ba1808d9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
fafad9e8-5ed6-4569-a6a7-b0b7d0b0e9bc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
bae6aecc-9e41-4aa6-aba9-98c01139ff1a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
aaa89b44-3a31-44b1-a766-aae067cb74fd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
9c716cea-353d-40a1-9ec5-ce5f191c4d3c | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
808e5343-03b2-45e7-ace0-ebda45409701 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
c1c5b4bc-0617-460c-95d1-9245d5e3789f | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7bdba4b8-b2a7-4a04-8aef-fee4078b2f93 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7ce6f6f2-b5bc-4694-a166-ab17b07afcce | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
898a41ed-20be-4ec5-963c-69f04a1378fc | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
86a77624-595f-4d0b-b720-3c0289cb3762 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
a6c6a5ce-055d-4ed0-b594-1d0bbb9b4b27 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
a6c10575-5828-49e3-983c-f0bd5fb7300b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
956e35e2-7a53-47ca-b7e6-c7367d8da01d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
0475b47e-4b35-4548-946e-126a6d8530a7 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
01c4f125-4a07-4d39-ba73-b36005081ed9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
02ceb0c5-9c55-4bae-8743-1f002290c8af | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
0b5564e3-e707-4425-8b96-2efcfaf76433 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
0abff65f-ffc5-4a5a-922b-7e0487ac1cbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
062a10d4-0ad1-4b24-ae97-4ce6acd9b06b | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
20dfe33b-ccce-41bf-9f60-a04f09221578 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1aff95be-7f01-45d1-96e4-8a282c990974 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1c8a0104-57fa-4757-87ff-7204c7128ea5 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1dc17a5b-5fa2-48e9-9c93-0d5a9cda3c70 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
1dbd14da-8dd6-4c21-ad69-ee62d193e122 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
15c6a04e-c5cd-46e3-ac51-8511bf45ef03 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
166214a8-63d0-45c2-99f6-7b7c768e04ff | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
102a4ac4-9bc5-4da9-bd67-297582af2a91 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
713c4c87-4b62-407d-9568-1936fdd36062 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
520ca10b-7b06-4c05-95ad-83a3aa260a73 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3 |  | 0:00 | 0:00 |  | Needs guy guard and aluminum bells changed out.
4fc70023-0783-468a-9f20-b2d4849c3046 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
54973d07-a59a-4eee-abfb-74bd97e1d9e8 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
58667738-cd0b-4e77-9c30-56d15717d138 | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2 |  | 0:00 | 0:00 |  | Dozen or so wood pecker holes. Some a quarter to half way into pole
5f3e222c-84fa-4206-b606-9477a0ae6c92 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
7848c8f4-db12-42d8-b69b-34670cbd891e | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
73d94ea0-b88f-407b-b54e-0e7fc593475a | Pole | 2 | Distribution | 2020-08-12 | 2021-08-12 | Level 2
6e2e0070-4cba-4bdf-a681-a775a6d47d16 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
6db4ce95-3ecc-40ff-a7a4-e1d38fe36392 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
68a810e2-8dde-4b7f-8d92-0ba1ddb37f2a | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
687a2a25-df42-4f4c-adbd-e537759e5154 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
69807d73-1c22-4d6f-9b92-bfab57e31c06 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
34bd7f36-21ef-4a46-b460-399432e0849d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
348d0cd8-bdcf-4350-8b50-9b17e6015d4d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
31b3ec69-01a1-4773-8def-094fddf0113d | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3198ca17-2857-4eca-83f3-f4d990bd6e69 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
290a2e00-67ef-4e7e-bcfb-5a58f387f714 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
29c70cb0-66fe-42e2-9fcc-80bfe9e35963 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3b22f3e7-f573-4537-97d6-bfae8209b083 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
391b6155-61f4-4c87-ac4a-913739009a25 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
3d45753b-7543-46eb-9e97-59c724149314 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
41019575-aed0-4603-8227-02f21ca13391 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
495c9d31-b037-4d23-8d6a-62b7ea696bbd | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
485dd898-327e-4d73-92b2-fd071ccb2c13 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
46b74e23-c1ed-4b1a-b2df-3d019ec001b9 | Pole | 2 | Distribution | 2020-08-12 | 2025-08-11 | Level 3
4d3f9d2f-da3f-4bc8-a847-525eb2f0a355 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
40343078-60d8-4c22-9592-1ce3ebfdc203 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3f1730e1-8fb6-486b-a06a-9b385a6780ab | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3f246742-297e-4197-82a4-038d21972036 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3e95def7-3fb4-4148-9e8c-7a41a080dd95 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
2b4afd08-e386-4417-bb5d-c42a9906f8d1 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
2a525730-764c-4233-9035-62bfe76f68e8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
35566c08-5d3d-419d-ae6a-90c12d56a86b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
38c48d19-ff5b-49d0-a69b-dff760465eee | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
6013c15f-bb99-46e9-850e-4647a71c14d9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
6e09334c-2ea1-43b5-b31e-fa4c10074ecd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
755a998c-b2d6-4607-95b0-74e78b5aa1b6 | Pole | 3 | Transmission | 2020-08-11 | 2025-08-10 | Level 3
61908aa3-9b59-448a-ad92-021315eeff23 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
5d72eebf-dc35-4ce8-b155-2f023a7b789b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
6205d9a2-2469-4b3f-ad52-042161682d67 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
56679041-8d59-4dd7-9c4f-1669ae7b6f5b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
547d5850-1bcc-49bc-8e15-cdad790e3961 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
4fb66361-1bdd-4b4d-9e00-35ba4094317a | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
11237a51-1789-4e9b-ad4c-25c91e699457 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
1d7bcd56-23be-4e6f-ba43-f6409db8d3e6 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
232fd5a5-85e0-4d13-94f2-75c6d28c6e6b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0cf155d7-27fd-41b9-a1d0-4dc060be6bcc | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0efd3256-decd-4030-83b8-2dd08fa277ff | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
02bfd782-dcfb-44df-97e3-4b624b0f7a90 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
04e9ae6e-89fa-47da-9029-fc298ddc7393 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
9fd32fd6-56e5-4971-994e-530e138bb4f9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a84dbf8c-f31f-45e6-acaa-f8ae05bc7432 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a0e56827-87e1-4427-8715-2aa99ce2c9db | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a1e4527f-4e9c-4311-a375-48b43d1f8c1b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a19ce921-79fa-4de1-85ff-e32b3808c4a7 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
8df984a7-7a56-44d7-8f17-ed20bf4f9967 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
7e78ff96-e4a6-4d70-8a63-15580687498a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
812c6d77-3d5e-4b4d-ab74-f87db9607451 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
83749815-9cbb-457e-b748-09983f982346 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
8550e1e9-b102-430e-a668-9e236f44565a | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
84c01308-3a30-4c7d-b891-4cf7978f9c0c | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
2bc3fc72-e7bd-4e7d-973e-20f8c7648c08 | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
ae907f3d-6a31-4c90-a77e-fd41d05d0cae | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ade3a6c4-99d2-43fb-aaa2-bf5a74f6ca22 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
a96bb538-7baf-4806-b79c-8d254e55a3c9 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0033dc4f-c9fa-4faa-b3c9-08c64394c60b | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2 |  | 0:00 | 0:00 |  | Stub Pole & clearance issues. Veg issues have been addressed.
b87c0910-ac42-4c1a-b720-74a05842bab5 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b15487ce-fe4e-4241-bf58-50ac4c3ac7dd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
f7411306-3cc2-4a63-b444-a90ae1eb35aa | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ed0b9dbe-db40-496c-9601-e52c55514115 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
e70c8f33-d22f-4bdd-9795-ad89a080f7a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
e6bddca9-9ae9-49e5-a5e8-843636da981f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
70d208eb-40bf-4003-8def-f3973169e86c | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
d814d3cf-5a3d-4819-8709-c06ff4799632 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
986a7178-cadc-40e4-bd35-0db93472953f | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3 |  | 0:00 | 0:00 |  | Changed to level 3 pole does not need to be changed out, need to replace down guy, tighten hardware and replace 69kv jumper field phase.
d2dfd70f-c13d-411a-9bf2-a3f7200ee5ce | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
dd9aa1ef-64e2-4d00-9bd1-22c57afaed0d | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
e02a8c5a-c207-45ec-a9c9-c7e3ce25b97d | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
dc4b7b1d-a604-4354-a5a4-0b84f1d6976b | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
e1c755d9-3507-4bc9-9dba-b9d636ab4f0d | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
985c20df-ae78-4612-bec9-4d1d89a69440 | Pole | 3 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
075f2da0-2cc9-4c78-b741-83d30a00646a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
00b9fd77-89d5-44dc-af68-b394b3bcb59b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
01b43a7d-067d-4130-a078-809aba570e62 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
0b877b59-c620-4def-8f73-d418140aff7f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
19ce6b24-5e85-426b-957d-23b4a8ec34b9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
157bb57b-6160-4ad3-b33d-938a04cc3141 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
7d9da2b0-9b08-4441-9e66-d9b9e22ddc40 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
294a28b1-8042-4318-bd27-cf9f2bcaf2cf | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
35372b90-34f2-4d79-8fd5-85440191235b | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
31cab056-13dc-4efb-b5fe-0979fd87e6a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
381e4d13-0ee9-4bff-ae65-af96b01cf12a | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3e5fa1fa-12cb-446c-8a5a-9b65206fe7b8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
3d7f74df-c904-4d91-85d4-2f337bd32aed | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
46a075e5-4d51-44de-89d0-65f1654a7678 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
4b1f6b6f-ceda-41e0-813d-5e106b5832ec | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
51cbfc7e-9349-43ec-aa40-691a27a897ed | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
5f1d12d6-a743-4ce5-8562-e716b8f12997 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
5401313d-1f35-42fa-bf29-105eab38d294 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
526ffd37-262c-4205-9eea-e5be282e2d83 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
682866e8-88a9-4cf2-9f01-3b3028168d22 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
73109797-ac64-46e8-ae0c-b908f41072dd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
6596c158-2bc3-4dca-9797-cd51ea69f4cd | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
5514772e-9065-4f53-9551-f1974eeb9a11 | Pole | 3 | Transmission | 2020-08-11 | 2021-02-07 | Level 2 |  | 0:00 | 0:00 |  | Pole dose have woodpecker holes at I would make it level 3 ,640 line
b705139c-25e8-4a75-a7bc-e7ff0e38e1bf | Pole | 2 | Distribution | 2020-08-11 | 2021-08-11 | Level 2
7b745c87-d2a8-4fad-a21b-817edefb5bb5 | Pole | 3 | Distribution | 2020-08-11 | 2021-02-07 | Level 2
fee37963-6c31-4923-8cee-f839e20d3903 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b5e5cf86-bd42-4ab7-a9e6-1e2656725532 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ad886d2a-3bc3-4716-bab3-2b88cab9809f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b366bd8e-ee08-48da-bd35-a2a7925a62fc | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
bafada88-8846-44d8-b260-8137cb4e898e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ba748093-3ea4-4e04-b742-6b0e777143eb | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b79fc751-e5f4-45dd-a9bb-49f2d37aeca1 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
b845ee1f-9879-4778-ba4f-da52c528f605 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
75118536-2cbc-4dbc-8668-24172c2a4751 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
76f1e667-e5b8-4001-828c-253512d3ef32 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
75390c82-54f8-492e-b7d2-6dd9b53043d7 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
7db52768-7e70-4580-894d-084f51a8c2a9 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
7dd32696-157b-4907-a075-93889b3aea74 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
837f2a58-5707-4160-b3d6-2645bc20efc8 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
90e578ca-ed6b-4d1c-a108-c3fd9b5f3619 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
8c33ff4a-24e7-4011-aec1-cb27983fe88f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
97431d8c-ede0-4f6b-a296-038a5bda8bbe | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
93950de4-201a-408f-8a6e-7c6acd39e430 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
9c785737-6de2-42fa-8b37-9e8c94180b33 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
fc8b3e11-3958-4591-9b02-41beba8fbdc7 | Pole | 2 | Transmission | 2020-08-11 | 2025-08-10 | Level 3
f6dd73bd-431b-493a-91ac-0c2f940d93eb | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
f8700744-ccdb-4253-850a-bd057f73c9d0 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ebbb8f7c-7c78-4345-add0-74535e2cc0d6 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
ee54b362-5fa9-4de7-a0c0-0ae338c7f04f | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
006bfd1d-bc17-44d5-8738-a5c00bbb089e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
dbd4b02f-f6ee-4eca-94bd-477026884420 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
db79698b-1db4-463b-a26e-5d6c05e9bf9e | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
c7ed9cd8-0fa1-4edc-ba92-0117dd529295 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
cafd9538-2f84-4115-be4b-f05d84559eac | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
c4127e7d-8eba-4059-8dc3-0b3cb3f78b99 | Pole | 2 | Distribution | 2020-08-11 | 2025-08-10 | Level 3
c91acdcc-896f-492b-9147-0a505aabbc5e | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
d3185ad4-06db-4160-9f73-f5063a92d089 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
e6ae605c-f65c-4bc4-be0e-99a0a263fac7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
fe5f647f-afac-43d3-8dec-1dd946271f67 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ec4891e0-82c4-49f5-aa0e-af537bf7ead4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
fa0a4eca-a786-442d-9a28-446dceefd54e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
9a818497-6161-49c5-bc29-7d07af6968d1 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
96a0cfa9-903b-4fde-ac99-3d4afe2a256f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8032e7d3-27aa-4e0d-8b05-623edea9d822 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
7ec4a4b0-2347-4191-8718-65a3f7f16ec0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
7c36f091-643d-436f-ac02-72472b8b16c9 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
bb32c5ff-216b-47e6-bff6-8db03de960f0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
b2fe75f5-eb18-4b84-a7c3-77c92168e1d3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ae2785c1-8b25-4425-9245-e228b8cb5357 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
af30944a-91df-4d34-ad3e-786e177bc4ae | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
a69946de-8393-4559-91e1-7863b21258f2 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
ff42a9a2-01e6-4fba-8c9f-fad3174eef84 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
fd413ece-688f-4af9-ae39-b329fc71feb0 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
6e9211bb-2b2f-41b9-9fc7-c9f9dce4317e | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
5c82b238-5f98-458a-956a-9c3545cdd839 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
31a10354-8cb5-44db-b3d0-1cc82f2b5971 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
40ab11a5-779a-4454-aa04-8b481458511f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ee0e9526-dce6-43af-ac23-0935a028973c | Pole | 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2
fc0a968b-6754-48e5-8fab-990a67545535 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
f66910c8-8ab7-4037-a14a-6107b39e388f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
13fdc2a0-0af6-4114-bb88-2223c46c8f56 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
e4f1c3fa-1186-4d4a-a968-74da57d744a6 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
dc25532d-7634-433d-8268-bf0e8b64da12 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
dfc0a50a-757e-4245-bb9e-0712f29de56b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
d9b33f7e-82d5-4cab-a5eb-f3792a4ce0c8 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
da757bf2-cf77-47a3-a2d6-96416db0d4b5 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
d32fa763-e735-4d5b-96bd-a0d8304609cb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
d48df17a-3d47-4e88-90de-b5f0cb1627b4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
d8287010-cae8-488e-898a-5ef93e2a83a0 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
cf3a9cd7-70de-4e90-8a99-349651712814 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
d2617a62-240b-406a-87ae-305d1ed393e3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
e7dc4542-65f8-4fe9-8032-7318a6a81059 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
e6f5ce70-efaf-4778-a0b0-27c2d8711c09 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
838fb907-b3a0-406a-9072-1e399d78eefa | Pole | 2 | Transmission | 2020-08-10 | 2021-08-10 | Level 2
f1e5a4f5-4127-40a9-8a93-8b5e32abeef3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
ef6f0b72-be91-498e-9930-1eb6026ddc8a | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ef27f034-6f79-4de5-819f-c68ba9cf9bc2 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
b839500b-6047-4905-b9c6-df7d9e1e532e | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
b8e46f50-140e-4116-b0e1-461c915c0ed5 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
ba95fe97-7d4e-4fad-994a-e9e6716550fb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
73c4a8cc-c28a-4133-adf5-f637528fc4eb | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
be7608e9-79b7-43e4-942a-a7736ce6c78c | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
c20929f2-2453-4652-8b67-1cdd3e4547f6 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
c51ee81f-4cec-4651-921d-e4603b37b1ea | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
83f69566-1b33-43b7-b18d-921305b57c0b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
829ea974-07c2-455f-a205-271d72e99bf7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
7dd5160d-be73-4133-bd97-b755def7547d | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8cf50f29-a20f-47c2-8a96-fb48aeb7f68f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8efbfe7e-51f5-4ae3-9891-e1721e725657 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
8acfa16a-29ac-4bd7-9d9d-df7c3965c57f | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
9b86b828-25d3-42bc-864c-15a3a1fbaf41 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
058a6018-0adf-441f-98d4-700424598959 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
03c319fb-8baf-4b34-ae6b-4062f03464e3 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
0da049a3-ad51-409b-979f-08da6c2f9e03 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
0cc66d0d-b590-46b6-a33d-70d8b2e6bcc3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
0846c154-c3fb-429a-b0ef-0c4a15a265d9 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
21be9825-f584-494f-b1ec-5e777ea1caef | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
1c041453-c3ee-40da-a0d9-f6120ab35595 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
144fe3d9-06cc-42d6-aa6e-ef1285809bd7 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
0ebcbba0-01ea-4b94-9d1e-f66ed002f129 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
2d25792b-ba3e-46ce-a419-53ae60fc0ed2 | Pole | 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2
50c1ca9e-2ef3-473d-995a-e1906b0e2f6b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
55cf549a-ff24-44a4-ab8d-c49bc1d902c4 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
544b6797-3133-4f1a-adf3-de312306f3bf | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
5084c38a-7ff3-4f68-a164-b1135835b633 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
57db1d8a-50fc-42c9-8105-39ddaaf25e48 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
71f62ba5-20b9-413c-a158-b43c912507a3 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
6d34c4f4-418e-443a-8e05-fd1208133649 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
6840d229-2c61-4b56-b767-50d2a9ba57be | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
676acd28-4dda-4019-a5d0-1f18a3771d98 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
38217f5a-fd7d-4faf-994c-8b3a0c86ba9d | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
312564e7-7af6-4612-9d9a-200747f7c84e | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
3314f109-ef76-4222-87a0-ce35dbc9cd85 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3 |  | 0:00 | 0:00 |  | Vibration dampeners gone
344e7ce4-34cc-48a0-b396-4ebdda41cd7a | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
2f378d56-0883-4d52-8602-1f73fcaa44de | Pole | 2 | Distribution | 2020-08-10 | 2021-08-10 | Level 2
2996ddf8-389e-43d2-99f9-c3234e9a1cf9 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
27fbeef5-7241-4a5c-a0d7-947c2298347b | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
25a1499d-73b7-4d37-823e-5ba4571711a2 | Pole | 2 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
3e1644dd-fa31-4155-830c-28a9db266c12 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
3f18ce0d-a86d-4518-a486-a74fe1d4c001 | Pole | 2 | Distribution | 2020-08-10 | 2025-08-09 | Level 3
4305e7cb-770c-4e32-a2ef-f981ea180cc7 | Pole | 3 | Transmission | 2020-08-10 | 2025-08-09 | Level 3
48c67562-3f9e-42fc-925c-e91777125ac4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
24d8636d-d2ad-448c-b203-cb55973ef767 | Pole | 2 | Transmission | 2020-08-08 | 2025-08-07 | Level 3
262790ad-73d1-4107-acda-5f78efff53c9 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
381a9021-335e-4d31-8753-f4b5b3c3c402 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
3795a344-c14e-4004-a738-a09aa39db785 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
376d17c0-bcc5-4a4f-a959-401440a0937c | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
354e0b99-e20d-412f-bead-bee2b7ef7cb0 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
67347856-db2e-4591-b79c-37ce9016f4f8 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
6d34b0ea-e4e8-4d78-a276-f3dd283ef829 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
6cd0a2e7-a269-4fda-aab6-0c9f54b5bdb0 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
71ef0733-318a-4aaf-b2e2-ce5df17c64b7 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
76c48ad8-f71f-45a0-8c55-e86007388f7f | Pole | 3 | Transmission | 2020-08-08 | 2021-02-04 | Level 2 |  |  |  |  | 111 line to be re-inspected June 2021
76631a4f-4d31-4b6c-9853-09a5d1af81eb | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
79aac699-d5fc-4aff-91b7-77075ead77d1 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
556ef512-1961-49f4-a841-f5032e796ebb | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
52bea135-6342-49c4-b224-96a154c6fdec | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
4e768e82-a505-4442-b95d-0c69977ebcee | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
6333adf6-3f33-44ba-bd44-0f5a0a6e1f85 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
66711678-afd0-4a1e-829d-75dcdc438fa3 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
5df46407-b24d-4bd0-9a6b-52d6364d25b4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
114f1cc8-b4a5-434c-bcbe-d05606eb152f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
12451f30-7775-46bf-90e4-e5679e5678cb | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0b168aec-76d1-48ec-9d86-6777d1afb3a6 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0a163401-b722-4f99-a8ce-fd38fa842878 | Pole | 3 | Distribution | 2020-08-08 | 2021-02-04 | Level 2
09dfe4ef-a759-4b86-9016-2c895c06a713 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
09d38a63-2124-4bfe-a326-4a89b64d92a4 | Pole | 3 | Transmission | 2020-08-08 | 2025-08-07 | Level 3
0b8ce194-b19c-4595-b2c8-95e5cc7a7415 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0f39039f-7552-41e2-9292-8a858bb32cf4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
980f09f8-9921-4048-825f-99afcb5d9c7c | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
9c137735-85a6-4d22-8473-2aaac15d119f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
9557d04e-7e05-4905-8839-90a6778671f2 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
9154720c-f78e-4969-a4da-a2d63af6b8c1 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
88b05b64-e38e-4f30-9ab5-ea3da6b979bd | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
7e6acdf8-2059-41d4-bbbb-c8c0490b7a6c | Pole | 3 | Transmission | 2020-08-08 | 2025-08-07 | Level 3
7f48c2cd-6592-4f00-85ba-093f316fc9dc | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
c846bcea-9f1c-4acf-8d31-f9c28e55a50e | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
c160f3e8-6e96-4131-b409-7fcb66cc2237 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
c0651488-7b56-43f9-bd19-f8c1df98af19 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
bbe6edfa-e325-47e1-843e-fa758a3a32cf | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
a9873b68-eac2-4780-9b11-3d2a7967842d | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b9ba4abf-b5a5-4766-a983-f6b105826f9f | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b94ed509-ec1f-4dc3-898b-b4b12f1f9dc4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b25d2d8c-4dca-40ac-a79f-7090a5638a54 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b4208164-897b-4fa0-81a8-16ecd0ff19ab | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
f9dba5a7-7aa4-4822-b00a-f896dd24f44e | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
9570cb38-1dc7-4630-815a-840d66c6d2fe | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e9228c32-2489-481b-af57-491a11847902 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e8ed8f4f-b11b-4888-85c7-64f818e6754f | Pole | 2 | Transmission | 2020-08-08 | 2025-08-07 | Level 3
e8ad5662-8c0f-4209-9a0a-7bf58ce843a4 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d2146ed7-947c-4121-b85b-d983dfd9fd55 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
cddb1b7b-d8a0-4f05-82ac-70f66e4095f4 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
cc602c02-c923-4901-b516-a3ca9a30498e | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d6b027b0-79c8-4973-907a-080eb0c68013 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d293ce12-3567-4dcf-9817-528cc753b2d9 | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d94fe4fa-22a2-421b-b8ac-bce559f0ee3e | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
de5ac015-6037-4fa5-8802-cf5c951b6b4d | Pole | 3 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e5fee9dc-b689-44d6-9157-f130b868ce51 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e484adaa-c8d7-43d5-acb9-f93f4adc6695 | Pole | 2 | Distribution | 2020-08-08 | 2021-08-08 | Level 2
0d04d559-6add-494f-b154-163ddd155afc | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0a62a4fc-08a0-4811-aad9-1b0d73fd17c4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
0771a3fd-b22b-488a-bfea-ccb93d9025bc | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
f31620c4-3cc4-450d-bbfd-a5ff3870e74a | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
4615da5e-caff-4528-92a2-3c84b03b294c | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
49c141bd-86fd-4d37-94f5-2ee2479ab9fe | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
384030ba-2fd3-40ce-8218-262c10ff1bb9 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
61146b59-2f58-4c33-83ac-a6892b4a75c4 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
d2a9964d-2593-4591-8db1-5b95c98e4c8d | Pole | 3 | Transmission | 2020-08-08 | 2021-02-04 | Level 2 |  |  |  |  | 111 line to be re-inspected June 2021
1bebb68c-d6cc-4638-8dd7-e0af5c46e470 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
bb500cd1-4278-4b62-97f5-fd714f0c1778 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
af21bcd9-e913-49a9-9d60-d91e0175062a | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
7f2afca6-7bd3-4b31-9e5b-91991cb25e05 | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
96b8c7ca-f31a-484d-8570-396c38d818aa | Pole | 0 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
8ed209a0-9924-4d32-a293-fd2c452feef2 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
b5b7eaa5-a391-49e3-9b2c-d01e9e86f1d0 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
e262779a-7db1-4491-a6d8-086e748f6081 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
ce1fdb9c-d8ae-4185-ab97-3a3c61f60f32 | Pole | 2 | Distribution | 2020-08-08 | 2025-08-07 | Level 3
da86f739-68db-471b-878c-c43d5c67e176 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
93b164b3-f9ef-4b13-9734-422b08aef464 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
b7f500bc-cff1-4176-9ce7-330219743bec | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
f4cedd95-44a0-4ce2-b023-410875eb848f | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
0033f633-775a-42a1-8d8b-5a5f681d458e | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
898fb4e4-2a41-4d44-97e9-9e41d64bf08c | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
949cf6f0-584d-44ab-8202-79dd1f5cfcdf | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
7969d91b-d734-4237-8c96-a44b4be48c1e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
77910078-a650-4efe-ad18-4bf4d053be01 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
22fe7f11-5d91-4941-8645-a81f949cfe9c | Pole | 3 | Transmission | 2020-08-07 | 2021-02-03 | Level 2 |  |  |  |  | 111 line to be re-inspected June 2021
fd99e5b5-7ebc-4baa-a229-2e91211a0a60 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
ff686600-44d8-454b-bb77-c03308af28e2 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
64725eca-f689-41d0-8925-050fe44435e8 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
6a1a7c52-a491-41e1-b2bf-4bd62b7abb37 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
4f2b7a14-8989-4ae0-b19f-4f5c97080968 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
58ceca54-a69b-4265-beae-10bcdb14967c | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
43990ec4-c3e9-4fee-bbba-626312ca730d | Pole | 2 | Distribution | 2020-08-07 | 2021-08-07 | Level 2
0988a21c-1ae9-433e-8a3c-48e39d169683 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
1a1496b2-c0c0-4a27-a30a-8ee41d4092a9 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
e4c4d3cb-c410-460c-aee3-947a3c96d051 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
e38ade05-f812-4b3b-8351-e27efda55cc4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
e3284f93-d64e-44ac-80b5-38be06ad72bd | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
db98aabd-62dc-4bfe-beb9-e58c9734a5f0 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
db9e3513-c175-4a57-a482-e5e8f6282133 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
d42b0df8-9bf9-46ab-88ec-457838d09f9d | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
d8513130-8605-4eb3-b92a-821d21c1614f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
d799e9ac-d124-4713-9a7c-c0d589d378d4 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
cd6ee233-a8ff-4a4a-8880-bb43e9bad7a7 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
cae9bbb5-e019-46dc-b780-31c6d71512f7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
e95092dd-5f86-4f4d-9b14-e2faa64316d5 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
ecbdd67b-529e-44b6-bbfb-e05edbc80dd1 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
987f479b-8039-440a-b286-fcac2b2a7a09 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
93aa8a56-96f7-480f-b605-68aff92bfc92 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2 |  | 0:00 | 0:00 |  | Vibration dampener missing
9eb4d24c-e04c-4494-9b2e-c86ee8d2deb2 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
b5be4d08-7f9b-4d72-b2c3-6f875059f1b4 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
0223d736-bf71-4c13-8be7-40cfd5051cd4 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
988ca0e3-1467-49c8-b36d-bef4c9ab222b | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
f34e57ca-c632-4e55-b81e-9175f53c5a45 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
ba80bbf8-ce69-412b-95e2-ca531209a50e | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
95d5b573-c3eb-44d5-b1dd-50aa9de901de | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 0:00 | 0:00 |  | Hardware needs tightening
abcc1f25-862a-4655-8237-5f54c8adf17a | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
ae7b9670-b59f-4cfb-9c42-5b0ae48ffede | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
acdde7ec-7dd9-4c89-915f-5a09470831b7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
af96a897-1d36-4bd5-9434-6a28ba0fbb74 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
bfeddf90-70b1-4f83-9fc6-e297d3df690a | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
c56830f5-4972-4233-9d88-2812d201d127 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
c28b6284-6d21-4baf-906a-af4bd038798f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
7d838af6-e97d-44a2-8ff7-7dd12a0c243c | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
83c0920f-a3ea-488d-a74b-4bb14a3444c0 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3 |  | 0:00 | 0:00 |  | Tighten hardware HV Sign needs changed out; need new upset bolt. Non GO stirups & bird guard
7637161e-21ee-44a7-80b6-f7b4d37eed11 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
89b76d8a-6f80-4695-98ca-de37aac708e8 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
8f11bc46-f3c2-4be1-9811-d23156f8ef5e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
900b2a71-16cb-4cff-ab05-b775bf0fad3a | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
952397e1-3130-49a7-8084-6dfaeb0da75e | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
95307ad0-66fa-47d0-8150-7beb6e60c230 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
96a1e0a9-c7aa-4293-bfe2-348cfbe5850b | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
9bce5e35-3fd9-4dca-80f3-c1ad98b231cd | Pole | 0 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
9cc4f567-2d93-4b55-8d49-86cda292dcb4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
a0c744c0-8453-427b-934a-0d27604ea11a | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
a603589d-404a-4163-a1de-9309aabe10e0 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
0ba60eab-d404-495f-aa44-cf6d1fc14b99 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
0d4077f1-04db-495f-b1ff-97570487daac | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
094f0ba7-79b7-4d9d-9cd1-8a4d310e5650 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
02246cbe-3a83-455a-b774-5911ef51b30f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
1029d0ee-ccb1-4168-aa4b-cdc166633f86 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
144134f3-759d-481f-a7ef-602c3cc8b989 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
15570870-31e7-40fc-bb11-b47a8031a01f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
1b6c5f96-1900-4cdd-ac81-f61ac23a20e4 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
21aeb734-edba-4b2e-91b5-d718b296cd1b | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
c7347d5b-8e51-455f-a754-0aae2c6da479 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
62054625-3946-455b-98ee-8afbab0f20d7 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
670f770c-2367-49c9-aa26-3134c8f0a2cf | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
631b9428-9efd-466b-833e-f73802a748a6 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
6384113b-954c-4046-8962-86b2f630d0f6 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
504d0ab9-e61e-4108-a817-4721caba8e2f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
5391c9a3-4564-420c-9504-23637ecc6973 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
53ec9e31-08e1-43eb-b958-60ece6e6e657 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
54d6b2fd-d106-46b8-9913-881257d831fa | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
57357c9c-4260-46d6-91e6-ee618d65e684 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
79e9deca-358b-457a-b0de-968b6ee90b06 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
79a520d2-0a98-4212-8254-fc4f8bf73b94 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
78c5593a-2ba5-436b-93ff-b66dda796582 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
75aa3e2d-133f-424c-8700-c1a9216172c9 | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
7633d2c6-12c4-4f55-a8f2-63aa8d59b96e | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
78338716-93a0-4bb6-8fbe-dcfaf66d0376 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
71b3b1c8-2433-43c1-84d3-721ddea6c241 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
6d2c645d-b53e-4655-bad5-5d56d72b64ef | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
7091401a-2cf8-44ff-91ef-8e5651c58f78 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
2e7a1a36-0959-4f56-9a54-b103d5b34f6f | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
2b7e82c2-5850-4e5e-8b28-00093f17b058 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
2cdefd32-ab80-4864-8b80-80dc20b3d859 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
4bcd46ac-01d5-4b3a-875f-5d09d6a9f691 | Pole | 2 | Transmission | 2020-08-07 | 2025-08-06 | Level 3
441c15d8-87bb-4617-9b9e-834d29b1a0d9 | Pole | 3 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
3dfe287f-2078-422a-b56c-8ea1e47efac4 | Pole | 2 | Distribution | 2020-08-07 | 2025-08-06 | Level 3
3e958964-2e7d-457b-97b3-590fed72085c | Pole | 2 | Transmission | 2020-08-07 | 2021-08-07 | Level 2
3b142276-1b53-4ab6-b782-dcee543537f0 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
431d602f-04cd-40aa-9cd6-0a867182e4ed | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
4e1f38f0-b338-438a-9ceb-cf48f0d62f02 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2c67edb4-a078-4b7c-87b2-a7c8d7c17bfa | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2ed522c4-2c00-4c45-be3d-477a6e35e73e | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2ac5f31b-18a1-430f-b01f-244b6f330998 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2bb14fb0-8ed5-42b7-a13d-0dac281e73b5 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
27c7108d-946a-4542-a3fa-44291b8fc6e5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
273dd98e-be57-48fa-960f-23575d9ace86 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
21493901-e1ad-4891-bd75-8aef6c61586b | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
34a41090-2455-4a09-9d58-0018a6e1436e | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
336992f0-33d9-472b-a198-9a7f70d73ea6 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
749ce49c-ce96-4cf7-8548-9ceb7c928c31 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
7b1a224c-d871-447b-b280-e65de7e8b020 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
79b2a4dd-6511-42d1-868f-5322cd1d6370 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
797ecf81-1a20-469a-bfa5-2aec7609fbec | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
51b846b8-f1e6-461a-81d9-06bd4346b6fd | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
50d2d93c-64c0-448c-a8f6-a90585d6f9d2 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
4f7c55ca-9bcc-4851-89e9-be2df314aa65 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
66492662-7246-4545-9615-9486a83bd365 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
5eff9fa5-ae71-4c6b-b9a1-24d8d5ef5f03 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
5cd7e909-36a5-4dbf-87c6-5a96c28a285d | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
2167a372-0b16-489d-a25c-813e2199c73e | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
21277841-1680-42dd-860b-7e81da34e133 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
23702c38-4150-40ce-aff3-5a032fee91cb | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
22b04be1-4ccb-449f-9929-b94d8b5bc871 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
1fbb3618-1ef4-42ba-8d11-45589f9cb6fd | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
1be441be-fd15-424a-b32e-08f638bdfdbd | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
1cb4e5d9-7f76-4ae3-b4bb-492ee919388c | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
152f7142-95eb-443d-bf16-4adb53721e55 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
04614e75-11ae-419d-a151-f8962ee01168 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
0798a37c-6e73-43be-a6af-9d527de937ce | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
0aae8441-c6b5-4752-99d7-5319d558b075 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
a5c7bef8-b9b7-4317-9206-20d6fc73fd21 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
a8a66c1f-1872-407f-a13e-3074a1c2e581 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
6780215e-6d92-4338-8380-50603cd9effb | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
99a04e76-b79c-4bca-a78b-469ba67619b0 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
90bf984b-2b8e-4ca4-98fb-561c49819037 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
93e5284d-7508-4b1a-a31c-3a63489558cc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
8fa28f4b-faa9-425a-bb4f-3d10fbc02d78 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
89562b8d-c9f5-4dbc-9ab1-b3c708b740ba | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
8b27b12a-e1d8-4b29-843d-143c552a6787 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 0:00 | 0:00 |  | Needs high-voltage sign stirrups and copper hot taps / Changing to level III
8b23763b-e982-41fe-8d50-ea375b106be3 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
86b60daf-887b-4caf-ab67-e30d06efd9de | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
339260b7-56da-481b-812b-b5060715ecc9 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
822112db-b37f-4904-8c6d-e54ee88b8d62 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
7d14871a-915c-42a5-8bd5-5a395461f090 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
7e0bf980-d8bc-4529-adbc-996b7aa5aa93 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
8038b02f-2539-485a-8f60-1cb29129256a | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
c1717a43-c82f-428d-93d4-cccfc5f33e77 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
c3a00615-bd6f-480f-9a1b-ef9d536e0c56 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
7b16aab1-5b31-4e76-994f-81f0155f3c40 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
bf2ed20a-b677-454d-af48-a3a8b4f1ad2c | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
c0a18295-55fe-4762-b589-76d5d83b3d82 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
bd51a076-16fd-452a-b2fc-fd5437ed8bc1 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
b092926a-4f95-4926-b0a6-8000ffc7f819 | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
9c60ff2c-058b-4549-bada-efba859c7ffc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
b81a658e-396a-48b4-b9aa-35564ff30269 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
f1f65302-a38c-4800-bcda-ebbbf44788be | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
d4883218-9e77-450a-a09c-ae2529abe71c | Pole | 3 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
ed28f450-96cf-4737-93ad-f9cdbf23fd67 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
ede784ad-c97d-4b07-ada1-e9e942370bd8 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
eb488266-1193-40a7-887f-6f4ff76d29e5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
d035dba8-17b6-49c1-8bd7-914b4f6e1bcc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
d7997488-3ea8-4478-a492-b2b88e69131e | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
d6ebea98-2c75-4b76-88ba-e756ba58f37a | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
d9dc8d8c-cb3b-4dc7-a651-b46e88169341 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
e12f340d-b8e5-4437-a0dc-552558de9ebc | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
e21d1c4b-40bc-4e24-a1ec-ce545d9874a9 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
c5262d63-f7a7-4b6e-b548-009234183927 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
b20ef1aa-a86a-455b-b280-8532554c1277 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
8c673f87-a295-4fc9-b77d-9201603ef82a | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
53c19b41-c407-4d31-ac65-922b982df8c5 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
5baf9f7e-b80a-433a-a64d-d24ef462aedd | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
306a8452-4d4c-43e2-9429-343854a70dd1 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
fdc0f9b1-3315-40be-980b-beafe5bd0791 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
8f591d33-5cb6-4257-825f-d8fae9d60b0c | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3 |  | 0:00 | 0:00 |  | Needs hardware tightedned
94a0f837-7a7f-4e5b-a606-433ae1e2d179 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
b797b66f-0f10-4012-91b0-216ae24bad62 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
bed3caaa-573f-450d-943a-ea560626a283 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
b86c43a0-ff8c-4e98-afea-44fd7fe37b3d | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
a0c24945-a699-48c2-af2a-07715f737b44 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
f21b2d06-6edd-433c-98dd-c78c9d99d776 | Pole | 2 | Distribution | 2020-08-06 | 2025-08-05 | Level 3
b7c5e067-fcd8-419b-8a8c-58f1ece0cdc5 | Pole | 2 | Transmission | 2020-08-06 | 2025-08-05 | Level 3
948a7c6d-6da5-423f-b48d-7dd5785c6052 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
940ce92b-4bd0-4000-808a-814be67cbaf1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
c8917a6e-7690-4fd9-bf9b-6a5ad105f978 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d7cfd504-78f0-4148-8f07-a8bfc885fccd | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e8163cfe-dc38-44d4-9150-284e9a83f924 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ea8243de-0f7d-4e75-af5e-521bdb3f2b0a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e98947ef-2596-4287-af6c-fca455145239 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
9d7ecb32-74e6-4b45-877d-45f01c9bb3c4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
bd906c22-52c1-4e53-855d-048666ebf3aa | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
c6bda757-da5c-416e-a0d2-5f8b88c234e7 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
94b0cee8-ecfd-40fa-a49e-c72042900252 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
7511b759-3986-49b9-8a46-92fc3f4daaf9 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
85591d6f-5225-401a-8421-1aa41d5e44e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ff5a0709-52a6-403f-bfea-580d05329914 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0ee9daa5-cd0a-433e-a41b-ab2f09e097d1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0ab08512-65f3-404f-b99f-6f4110b1907d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0a6911e5-3ecb-499d-8519-23f292e2ee2a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1e6c7d78-b821-4305-bb63-665abbb459d2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2dce39a7-222e-4aea-8163-92d5c7de4644 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
460f2025-530b-4c60-b4f4-22343d8eea7c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2afe0aa0-29a4-4492-98e2-ba8d35e7c57d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2a886aa9-6ebd-4fe0-953c-ec90f93aa0a0 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2235dfe3-7c8c-47b5-9bb3-bd5398c06db6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
36719411-5eb0-44cf-93bb-5f2a3381bae1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
59ccace7-f6fb-4def-b050-181734132481 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
6ab39443-84d3-4b43-9d17-9347d1511f5e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
70ec3213-18de-483f-93b3-f521470d788c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
662a1fa6-a019-4578-86e2-e4d9e82bb285 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
b1990580-29f9-4f5b-9f4e-aecc429e9a05 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
bf979a9a-e453-4e87-bd38-930a475e62d4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
bb1c0598-e0b7-469c-8e05-a5127d1d028a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
3de89cfa-4381-46d0-8356-6444256d0c60 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
65605fe1-44cf-4653-857f-bfc088019f8c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ea560e12-6bbe-4a21-8697-6ed8c3bd69d6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d523fe1f-f25b-4c80-abe0-90ef889f6d17 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e00e6ee7-915b-4846-bd3d-d3467e3f9a97 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2732e135-2118-40df-a459-a1351ff942e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
16e854ad-3e9c-4559-8c18-4138240fd24e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0989dc6e-ae07-4eda-8b9a-7947360344b6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
049e3cdb-38a5-461d-8e69-7a855821562f | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
00784bfc-aa4e-401d-8cb3-5ea57aa86b66 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e4425c75-4c89-4ba2-a83a-726fd5ceb60a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
b5bec8e3-8013-448c-9cd6-fd0017f81029 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d7444693-fb4b-4bb8-8487-2c240599d7b2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d6ae9d52-065b-40fc-aba4-fea0f364199d | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
d285b588-71ca-4067-9f56-d9d53cdebf18 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ce9f8d44-26bb-4841-a8c8-d43966759fdd | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2 |  | 0:00 | 0:00 |  | All hardware sucking thru pole, rotten, needs to be replaced not topped.
ce5de478-9be1-413f-bd57-290980287b40 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
cc10387c-8083-4a11-8741-08174f7ce52e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e731d4cd-5abd-43fa-9d39-0f3fe21fb5e8 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
e7b3191f-e0aa-4b2f-a962-db5e98e91018 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
00ec779c-eb12-48d4-804f-c13cb846c68c | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
f1caca33-bc9b-4326-ac62-14e643a2208a | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
ba4a9d4c-d19a-46bc-bba9-bbaa89a36618 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
a8db26bb-c05f-47e0-a589-2bf2a05276c7 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
bf65479c-d7fc-4dab-be80-f42c588c48eb | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
7d381d25-7b50-49ba-921c-dcd194958e55 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
7bec93b9-3acf-43fe-af3d-4bd326ff1cca | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
8a927bb1-878b-42bc-b8c5-fbabdb4834e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
8b2830f1-2494-4494-9581-97041f0d8d82 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
8b399519-6373-4863-9ab5-b17050739f97 | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2
9a48666b-5954-4e17-8e2e-13c0c2af7ecd | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
9dbf5f10-0543-4aca-b696-74a03a69a732 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
9cffeb8c-cdb5-48de-ba82-41b5b3f2024e | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
a8a8ccb3-3444-4e3a-8b6a-ab99a23e81fe | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
a5aa7bb1-6234-42d3-b7df-147264f95079 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0af5cae6-5c55-43b8-bfe7-0e8e127c9cc2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0d1aeec7-c8ae-4d0e-890e-e418534f6367 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
0b449792-eb3a-46c6-8f30-d04c1a4275a9 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
01a1e930-8bfd-462a-9ff8-28c5ca3bcbd3 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
14765d57-5199-4faf-8067-754407c46ec8 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
177ac5a9-cd72-4674-93be-03e0b26071a2 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1e3cc06f-87cf-48f5-ba76-37fbf86dd601 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1e399946-4e29-446a-ada9-87a6f56a4436 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1f55b1f0-e131-4dd8-a30f-9e0638fa8636 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1c49a69d-3c87-437d-99ae-9913f423aa6b | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2257e7dc-45b9-4f4b-917e-fe1db5251496 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
1e47fb8a-633b-4db9-abfe-01d127932c0b | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
21814b91-fdf5-42f5-bd64-63d8de4714e5 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
20355b09-f97b-49df-8aaa-181965450382 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
5f76f859-8d4c-41e6-af95-a34a107a73ac | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
5fc9948a-a322-402b-8a36-c511e264de74 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
5303fd3b-93bf-449e-a899-b0cbc43a43d4 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
5934d853-9693-4572-9eee-2f39c7cba159 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
6b7bc8f4-f818-4114-accc-0ba4383e9104 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 0:00 | 0:00 |  | No threat to service reliability moving to level III
656cd643-361c-4c01-8138-e727a53db9ff | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 0:00 | 0:00 |  | No immediate hazard to service or reliability moving to level 3
66e88ea4-2b44-4628-96fd-37f36ace2cf6 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
287a91da-c557-46ac-975b-684d2d417462 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 0:00 | 0:00 |  | No issue with service laying on the ground at pole did see service still in tree cut on both sides looks like itGÃ‡Ã–s for temp power when contractor gets panel set moving to level 3 8601 hwy 89 (Amanda lane)
28e94845-96fb-4387-a992-0d43789dbb43 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
28c6732b-7ce4-46c0-ae01-07714309cf4f | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
2a9cb56e-db86-4e1d-82fc-a3e544af255f | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
4d168164-34f7-4d5b-a4e6-42ca58b013fa | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
4a99594b-e709-4232-85ed-f2f830356b6a | Pole | 2 | Distribution | 2020-08-05 | 2021-08-05 | Level 2 |  | 0:00 | 0:00 |  | Pole needs to be replaced
459f694b-8792-4467-ac68-cf8f98030fd1 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
3fbcfa36-5e57-4280-9b0c-b3eceb5e1303 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
3bc8d9bc-10f2-4183-acf3-fdbeb7fbaeef | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3 |  | 0:00 | 0:00 |  | No immediate threat to reliability of service changing to level 3
3d951ac9-4003-49c1-9d35-9ba373c41067 | Pole | 2 | Distribution | 2020-08-05 | 2025-08-04 | Level 3
39a94e2e-9455-437d-8111-959907cc1919 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
3fc797ee-0868-4a15-aea4-103adc2ad54d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
410d9361-8f75-40a8-a42e-46e8861c02bd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
456d3608-9550-4e96-9efc-3472a392ebd5 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
4593022f-da59-4d37-a1ba-2c861ea2c86c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
2a208ec8-3785-4200-81cf-7b99c6bd636d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
2ded5301-cdcd-4744-9dcb-b1ac19c707f2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
27db1a60-7eb3-41b3-bc90-36839b815a66 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
364233ba-48a9-4630-8bab-77ddb66c71e4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
385ac7fe-3ee9-489e-a3ec-c6ebc4b09bde | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
384e7e46-9b7c-428e-a620-258d6f42a838 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
37441fdc-6a2b-4f0c-925a-fc14cdd0fe2d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
2f5ffcfd-0698-465c-a3bf-2fe14e4ecde7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
2fc6b427-fc8d-4480-91dd-6e814be52699 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
33b09294-571f-4543-81f8-de4eef4a698d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
338cbd3a-4c85-405e-8b8f-bf4e678d6d11 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
69bf8ad4-c344-4782-8606-a006492712e4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6a2604ac-328b-4e68-8fe4-e3cf9ae985f3 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6c399e4b-69e0-4410-80c5-7bd3109a4bd6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6fe5b755-9c35-4afa-99d3-7390003f0382 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
79005cb1-9a4d-4559-8664-97238b311bd0 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
77a87cf6-9909-46bb-83ff-d596eeeb422b | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
77435444-98e3-4c7e-a8e5-dcf56a5fb792 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
76697788-29fe-40a6-9345-64aeec456774 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
70509ffb-06f1-4f99-bc1b-924bd4a2fe25 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
71fcd5da-68f3-43ce-a2fa-85b365d8e59f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
726137b2-25fa-4d46-8530-4701ba8a5542 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
59935878-a084-456d-9ecf-4bbf76be0387 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
55e5a746-db68-460f-95f4-5e49528826fa | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5eb88ab9-b27b-425c-917e-f94463d97d77 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5f56bb5f-9cd6-4fb1-8a3c-a04c976b34dd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 0:00 | 0:00 |  | Climber needs a high voltage assign and guy guard
5b3d9ee6-6933-403d-8222-47592c421b9c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6642fc8c-3637-4f3d-938c-3bb2c92e70d7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
1c1ad66d-52b3-4521-b5d0-1e86a18117d3 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
155a9102-ce41-4525-96bb-4e9e218116d8 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
150a290a-fa44-431d-831a-0d45c6536cb9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
12bd148b-ddbc-4f02-bc02-35d66aa798a6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
1130cbaf-ca1f-4143-82fa-dc54f3c73e93 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
01e17ebc-bdf4-4a1c-9a4e-a4053a4b0a4c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 0:00 | 0:00 |  | Pole split and has stub that needs changed out
016de47e-ac16-4ae9-974c-85cb069a0068 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
0c666485-386c-4b59-900d-1efda3b4f1ce | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
0aa31781-2582-4845-962c-8cdd2631662d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
092f20eb-d98b-4121-b115-56890e9c3a25 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
fa71151c-810d-415f-86d0-54c733efcefc | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
a77ff628-6127-4bd8-9b4d-1b05e7540605 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
9f62e863-7b9e-40f4-97d6-570ef8aef2a0 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
997021d0-b955-4107-a0c3-ad96636ad6f1 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
92f3df32-83ba-489b-a899-0f29afe5c95e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
96e53035-709a-4439-9434-a986590e2dfa | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
84d5b6e1-0965-4885-97ba-8b26177dac88 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
8d733888-c52a-406a-8a05-c3876ea94763 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
8ffe057a-b4e6-44b6-b085-6e94ba1eea1c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
863f4b77-9867-48bf-8863-d416d79d74d2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  | 0:00 | 0:00 |  | Changing to level three conductor that is not taped up is D energized once span to deadens pole
7a26ca39-760d-4032-a468-1f38ffcdb0bd | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
7dd236f7-5255-403e-b2c6-60efeb44f5b6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c21cf2fd-9ee5-4721-a0bc-2c3906d80d5e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
bb6494c2-3cd1-4286-a88e-552f7da99374 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c6e2e9e6-3af1-4670-b774-95928ffc94b7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c94e826c-39a1-4559-8070-57d317f0c003 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c368069e-ab63-42e3-9d2d-acb03d404d1a | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
9e7c5562-1003-4660-8343-df5753778e7e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
909d9418-0f50-4293-945d-e0318b0175d9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ab285fb4-6940-4489-ad35-103d1972c094 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
b114f1d0-0e21-4b9c-9155-d245a0563289 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
f18fa482-e68f-4d93-9c77-59365cc3c7bc | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
efb05e35-63c0-4d65-a961-5cf07756494f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
f515ffe5-fa3b-44c4-a54e-a214003da4b9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e7ed035e-3882-4647-9f92-34f5b1b39e10 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e89d5933-a6c8-4c35-a3a6-c8dae02a3c41 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ee40f41c-e415-4389-ad21-dd368a8dd9d2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c9acc18f-bd41-4539-b9ef-d3b4e3be4363 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ceb57227-dd31-4ad7-9090-151b25e4f856 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
cf0bdde3-9846-4959-bc29-f3d3957bdb01 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
d18a9d65-36a9-4723-9bbe-2626220b0667 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
d21e9052-05af-4895-912a-4b87437d2abb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
d39a0d31-2b91-4f10-b5f8-90195a5ccb8c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
d8c02533-cde1-4616-bcc4-764edfca56f2 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
db5e2e0c-f22d-482a-9ed5-eac4f6e1e987 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
df8ab364-0589-4645-809a-dcf2aef9d528 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
dec26b87-b825-4210-aea5-ac46932ea715 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e00d3961-74a0-4de0-b612-b3287720a3eb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e3f816c8-d3ba-4b80-a92d-a318ec5a8d58 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
dfbb6664-0216-49d1-802f-55a86a33ee09 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3 |  |  |  |  | No longer trees in primary. Moved to level three after re-inspection.
e619b660-f1ea-4678-9fff-5c45931b6a7f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e22be44a-1efa-4075-abfa-d0a2efa4b2d6 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e13cdb5b-f8c6-4f15-8949-1f3f68280fa5 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
0e3ea69b-4419-4f6b-8cd0-36be8afde6a9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
63cad37a-749f-4094-aba0-47481db4c772 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6aad7281-c469-44b7-8bf0-c61d80443e2e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
68ede30f-4e51-4571-bfb7-3425113c7667 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
88338fbc-b0c9-46b8-9e36-fd0e0105b74d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
c3c3981e-fbda-4e9d-9400-801dce639daf | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
cf4df3f3-b5b8-465d-8dda-d02feb2c1058 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ec0e4c9e-7796-4b2f-904e-b8ae1c8560f7 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
b3c8123c-8fa1-4a3b-a81a-dc33d7ecb83e | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
6a035814-8aac-432d-b0a9-3ae643effc8f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ab7400f7-bf2e-4b36-bd8c-4dc8f433a08f | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
82ba9dd8-8c34-48c7-93ff-3dff212e01eb | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
9fe0a798-e1cd-402f-91bb-d4ab9718fc7c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
685a536c-c659-47fc-a9a1-413ab21c5d38 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5ed22696-98cf-4d9b-91a0-7c4a728af6e9 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
59638746-062d-43d1-b52a-7a41723fe40c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
5909e2c8-2bc2-4b0e-b24d-fe8bbaaa0213 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
3b77ffb5-ce56-453b-bf22-8cba81c67564 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
291692dd-fa0a-45b1-ab1d-7817cea70e53 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
b73c7276-6cb9-4da3-a489-87c3dcce1f37 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
fc20c68f-8a02-4d1c-8816-196bec0ebb3d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
932cc9ac-8528-4217-9936-e44a3bd76fa4 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
7dc95049-cce7-4bab-b1a8-a879afffc607 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
bfd55422-aa1d-4c08-ae75-a4efd9a7f51d | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
e4c08b8f-339d-4eab-8ec3-9f9833d47261 | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ca15506c-e4b0-4ba2-bf8e-4ab83ab4c38b | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
eeb1defd-1415-4b79-9af7-ce79922ae44c | Pole | 2 | Distribution | 2020-08-04 | 2025-08-03 | Level 3
ffbfb881-ae1b-4ba2-9e3b-c7d6cc7d423f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ce7c1fb0-7d96-4c48-899d-b02d32e8521b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
db43b801-97eb-41eb-bf09-85908d5d355d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
a2391e1c-451c-4256-9bff-b39d388eb895 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
aa50cf13-be7c-4403-a954-0631041ae19a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
85d49349-3372-4df2-81b7-cddd8249a552 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
81891eb4-0285-4b00-b3dd-11e17543c1c2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
fe634fba-7186-4898-a13b-626e52f7418d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ff13701b-d8ed-40b1-a94b-400d0e2efe4a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1e930df5-fef5-48bc-b718-c7c50f6d4e5b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ebf595ee-2fc5-44e1-87d2-ab94f7c0ff64 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
018e380a-947c-4810-9bbd-0c50e0e4f599 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
130d4e00-1d0b-45db-8b0e-496b631714d4 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3f92e769-2ca6-4559-9cec-124d6c66410a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
5a597158-95ef-4c9b-8142-400bd172e179 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
52ab1469-0867-4595-9493-2eb36542a309 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
488f9a81-77b7-4613-80da-f523e1254c92 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
5dfd2579-bc42-435b-b102-9aec8fe0f2c0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
a4e2e557-f66f-40d3-8ef6-0967856bb59d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
93ef954f-75a8-4751-bc2b-8ee73be93e61 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
974ed518-130e-49a4-b47a-95d2b85901a5 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
c907274e-1b71-46b4-b27c-fca780cbcbb0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
d25628c9-a142-46d4-a40f-4dfa083cc8d2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
6ea8b47c-7563-4659-850d-d0342618be7f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3d4d78dd-42d1-4d3b-a50b-46859f1376a8 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3c6943ff-27fa-40b1-9c6e-a014d71fa691 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2cb6e554-25b3-4ec2-948b-5e678c0acf70 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
38311ffc-3747-40c7-a198-201a7674bd44 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2638f325-4898-471f-b39d-64d934e31970 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
224410c4-a0b1-40cb-bc33-1e20cd2ec6e7 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
fcbf3fd4-b0cd-4760-b7f9-b2af1c0f0ccd | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f4133813-d90d-4b8d-af40-55e5ea892bd0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f10b59f1-d25e-477f-b843-5f13747e4fc0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1107750b-4798-4e6f-bfe0-10f4c75a568f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
df4fc912-ba3a-4c9e-a1db-761b3e0d19bf | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
dfeafac8-b4fb-45b8-8136-032b2c9e23aa | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e67594c6-80fc-4e14-9192-5021f583407e | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e356b4a7-a764-4a4a-b250-ad8182334898 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
dc133c13-1dd4-4d88-a78b-aa847c1dc480 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
8304f19b-186a-46f6-bffe-b3a05bafd516 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
9498c9ab-e901-42e2-9b13-41bd1e0eb7ab | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
d7990b3b-b7fd-46e0-a899-26bce4bf9687 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
d0bf7dad-6410-408c-adb1-cda2ef9b8bfe | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
d05e2b24-da5d-448a-ba90-0babb4cddf0f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
caf4fd7d-271b-46d1-9397-e04d18e3f5b6 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
cc0bd53b-fa69-46de-ae60-616818616496 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e9dba797-a711-46e3-9e8a-6e53b7504b84 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
ea4358c6-86c1-436e-954e-e4d293d61fd9 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
e6a0f759-b684-40ca-9085-19665bd4fc0d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f2bede69-3eb9-477e-872a-f8621fd8fad8 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f0364de3-38b6-4579-a31a-87e341e14ae3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f1335eb3-1fbd-4245-b8e8-692cb8406e6f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
f78438a9-eb3d-4086-8839-40c985cbdb99 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
fb907482-ebcc-45e9-bdb7-7bb4c7325669 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
b1436b1c-8bcf-4a80-a466-9863da5a9aad | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
baec7f17-1d8d-4600-b986-4b813ce2beaa | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
aa8b3c73-cb52-4308-9434-cc1cf2addde7 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
c8542491-e865-43e0-9a4f-67535513bdcb | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
c80d64e7-80f9-4c8c-97fe-d4a93e6ca127 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
c7f4c31a-bf49-42dd-a7eb-d8f3099fcc8b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
39a2f2d5-d782-434a-b82d-340e528ee5ac | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
bc0f2cc9-1474-4950-ac8b-6e6913b5e679 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
bfe436a5-a729-4ecb-8e2c-51e71db67b09 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
7bb558df-bd0a-4d42-ad2d-0eadf733395d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
85db1d0e-fa0f-481a-97e2-412e55aad0f3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
87068f74-60ad-4336-86a6-860dd8b55f42 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
885217dd-8276-4bae-ac68-0ccee650d88b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
8bdaf38b-c989-4c03-b4e1-936772e85375 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
8b84ea1c-8793-48bd-9f46-3ce4aaf26963 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
8b81e8ce-de14-4e50-8b91-daee4836eae3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
940a2b00-fccb-4f4c-8a56-2bc8c598dba0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
9980b6f7-5641-47fe-8c2a-9baf7c4d7f63 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
9b17161f-8c3f-4418-a8ca-bea4ef08e78a | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
9daaf1e5-89a2-4959-bf88-1dcf9a80ac27 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
a0e042cb-4458-4e5a-888d-46f2868fd6e2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
09f6d240-905a-461b-8bf8-d77ed594f31d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0c2a266b-6b1c-44e1-8939-d6e9d4526f41 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0b6c1320-fd8e-4acc-a649-1460e84bde4f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0dfe9e62-034e-4e88-8e99-f9eb51cc13d1 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
0ffc3f4c-b098-4c17-b57f-1cea71085925 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
136f9d67-de17-43ab-ac44-412b12d45e4b | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
15d39de6-8a7c-492e-b609-485393d48f25 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
19d04e4a-0d37-47c3-b5fb-11be61ced039 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1a5b203e-0bc2-4383-8309-bd1906cdf55f | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1e6fb41e-5421-4e77-b774-9513d2dfeab2 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
1fa5b571-4852-4f94-9695-7aacccd59534 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
5caae9f5-c314-4bad-bebd-5abad13f0a0d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
4cfbd08c-11bd-4d9f-8869-8c7cca6cc794 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
55501b28-ef41-46c4-bece-bf35aee83548 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
57bf5e4d-f016-4d6b-a6c7-0940cc00c167 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
72209d37-2179-4077-98cd-c290167c1b57 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
721a006f-09c1-4752-a4e1-493d95098d0c | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
709f3b95-8e3e-4bd0-9839-59f72ed8ba65 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
67d2c9ff-bd9b-426f-93c4-ff16e405c140 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
6b661b0a-36a7-442c-b66d-3181bb9e6580 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2f266d5f-de7a-407f-b136-73d3655c7278 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
304c4817-9e28-4f87-9f16-135ade81fdfe | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2ebd9721-acaf-4a78-a137-6c52114f1ea1 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
36a22349-8c00-4aae-b1ab-13480c1db606 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2df2ef07-ab06-4722-9193-34e78bf1b7f4 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
2325bf99-6f22-4c88-b432-566d72d80ad5 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
489df34d-717f-4ac2-a712-1770661dddbf | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
4dfae9a6-30e1-471a-8045-b9a99c196d8d | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
4b8a30f6-302c-4b76-8519-c472c4d7f8d3 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
4126f051-f83a-495b-b0e8-0badba462f0e | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3c532d41-4e11-4ff7-a6f0-fa5fa2755ad0 | Pole | 2 | Distribution | 2020-08-03 | 2025-08-02 | Level 3
3ec305a7-aaae-4075-9af0-f3363bf414be | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
3edb2e98-a5ea-4b36-b962-97e7297549c9 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
5ea04825-81db-43de-b679-1a8403c36582 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
188852bf-7e31-4b74-a4c4-ab573fc2c8da | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
4dcd2a82-68dc-4042-814d-a94ea8fdbefa | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
9d28af65-1aae-4c86-b959-1da10c160023 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
8e4e0149-8380-45bf-8b88-c4e89585699f | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
c4fccad2-0f9a-46a5-bf54-406f1f4bf58e | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
e8f9bdf8-b321-43d3-9de9-d98143e3eed3 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
d6d4af7e-2867-4f1b-b381-d8e649626bd8 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
1cceb03c-0abd-464c-a263-ba99d2f8f8a9 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
455d47fb-d0fe-488d-ad1f-66270ae21528 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
73070146-f2d2-4e7b-8283-23b2f9780d9e | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
4a77bfff-337e-457c-a8d5-db6a23d03727 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
001795d8-d8d7-47e5-ae00-a0f0a750b103 | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
60d25ec9-0428-4b06-8fda-a2c588cbb12f | Pole | 2 | Distribution | 2020-08-01 | 2025-07-31 | Level 3
dc6844a5-dee1-4014-8e5e-f838a2050c65 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9a38cb32-db3f-4718-ad8c-14d0301a8464 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
b5c61d2b-7aa4-4f81-962c-04c1a5322f9a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
4ce1d739-0e10-4e61-ac8f-80b2d063391a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
96abef3b-ec1f-47fb-a988-f7c29c394695 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
171cf388-e301-40cd-a45e-645246fa6494 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
3252dd4f-fc85-43fd-ac07-54e0bd73cec6 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
7fd72772-4251-4e41-9ab5-4b8eb355eb4c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
889bff9f-a31d-4850-b111-451f0e2ddf96 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
78d4a2b9-8bad-41af-9a78-08ea968e0b3b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9b6e34f3-c54b-4c12-a78f-46301bceee21 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9bc6a260-8b08-4388-b606-cf0be95967fe | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
b9459af1-e01c-4ac5-97d4-f9c730bae24c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
ccd2c51e-0b96-404f-a200-df16ef8e251d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
d4ad8854-dd45-42e2-99b2-4372fd81d10f | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
cb455cfb-e71c-49d4-bc3a-8e03a989c126 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
952f498e-07e1-4040-be46-13afc3f2a7b6 | Pole | 2 | Distribution | 2020-07-31 | 2021-07-31 | Level 2 |  | 0:00 | 0:00 |  | Refer to change out pole due to stub. If pole topped would have standard clearance issue with comm cable.
e2f77868-b496-4e70-b56e-3abff794696e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
ef021309-ef28-42e4-a38b-f52b39a3be3d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
f5adcc77-8cea-4953-9be8-42183961fb0d | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
99ab8b9e-c923-4ce0-b46c-8e9890dd9355 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
c05c5e37-46f8-4884-a4a1-02e55cf07d01 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
bbeaad8d-7068-47d4-9943-344369aaef27 | Pole | 2 | Distribution | 2020-07-31 | 2021-07-31 | Level 2 |  | 0:00 | 0:00 |  | Refer to change out pole due to stub. If pole topped would have standard clearance issue with comm cable.
87452c8a-2cb3-4d27-985e-79f8b0281f06 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
7cb9636b-fd28-489e-a13d-ea0273d0ab8e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
7c13e852-312a-461c-bb1c-43edb052e81c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9e904ef8-ca92-4a6b-aceb-99903fd38385 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
9e1cc321-18c6-4c0f-a7da-55392c1ab5d9 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
97d57daf-34d2-408b-9d7d-b7854ea01e12 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
a10efa60-7aaf-4d57-bd5d-3d98a3643c33 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
a2c570fa-56be-4b0f-8341-14a6346dc187 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
a32e8679-ade5-4414-b7b0-ea711c924fbf | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
1a100b9e-1185-41a1-bd2a-bdd3cb22140a | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
1622dcb3-4770-4139-932a-926a8334e95c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
126fd123-11a6-4211-91a8-e3a25ad0a677 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
224341ad-2cc7-4fe5-9e3b-d64159e5c262 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
1cc64aac-3612-4b75-95dc-1f3a7e674aa3 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
0f600af8-e21d-4f48-a075-eaf85ac02ec8 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
0a3582ac-30be-4318-a20e-b370c5b950b2 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
5d02d0ed-383c-4006-95bc-02c4de96f23c | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
635888d4-19f9-4422-9cd3-40159f92eaf4 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
5a441163-533b-45b0-9f6e-8b68f9d988dc | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
56640363-305b-4796-8fe4-b6a3a4edb1e0 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
696f6861-cb91-4370-af66-0d7ed5758dd7 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
3f9ca84c-ed45-4a74-a1c2-30b1d847890f | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
4e5ddaff-d9ee-4aa7-b198-e914156e3f9b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
4992da7c-5d6b-406e-a560-46267d3355e9 | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
2c6a54aa-4837-43d0-9123-b98373e88c1e | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
37fc1b02-059d-4954-8823-2897756d437b | Pole | 2 | Distribution | 2020-07-31 | 2025-07-30 | Level 3
2ed490fb-80c8-4625-83f6-0ac3618de835 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
467e2744-01dc-45b1-8cc4-09a5ed171bee | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
4190bffe-e431-4f1a-93e0-295ae2cdeff5 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
67506e5e-7bd8-48ae-9efd-84cdd7f284d8 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
74dfafd9-7fcb-418b-92f8-65c3e4a9cba6 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
56b5d1c3-0811-4df6-96f4-ea94411eec24 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
621f490a-019b-4906-8a66-c9c8709137df | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
5fbd73d2-389e-49dd-b3de-9d8ead41b493 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
06b847b3-fec7-403a-aef5-743294ba574f | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
0b82095c-23db-4106-a52b-1aa08b274c02 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
23b43a59-3d7f-41db-b121-1a6079b10cca | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
163fd724-f184-4fa5-ad4c-87c14616ceac | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
8d8d8458-3a22-45b1-ae86-bbc984a36f85 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
b41fba4f-3a53-41bc-ab37-26ab8e59a45a | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
d53bbb7b-4ef8-4252-a579-5e39eef82efe | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
848051fa-fb95-415f-a8df-1d4f439fdf51 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
3bd02773-faf8-4a90-b71b-61909c00069f | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
f21d7579-0fe1-4539-885f-fd8e9a067410 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
fb45652f-bb6a-4972-a4f3-0fc3aa63669b | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
d99a9ea9-dfb4-4e10-a395-fb86f8ebb618 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
dfd7a173-f86e-4b4e-b5c4-febea764c9bd | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
dc85d9e8-fcc4-4350-a14c-db8f1d853ca3 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
23e58721-722f-4dd5-a1e6-a5ba53f2d8a9 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
4db217ec-acb2-4333-a444-fe91a09a2c29 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
39ab9892-5a96-47ee-9591-cce751d9ebce | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
56c25b00-1b97-4e8b-a119-6b2885c2aa25 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
23d5be88-bb3b-429f-b665-1038cac42329 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
2c28b806-2e23-414a-b770-db946a9555ed | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
98a3f311-9d56-4693-8e97-bcd26455e683 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
ab225ffb-46ce-4cd2-b5da-7efe58fbbb8c | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
8f07b11d-0467-4b2b-8b88-bd2251c54a23 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
adea6fd4-30e3-4863-ad07-8a0e3b1c559d | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
8a95f0dc-3de1-4647-a7be-e65e6605ffe9 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
7df02f3d-fc07-4472-b9d0-d330e9b786c6 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
eb960ef1-6022-44c4-ac45-76ee623e3e26 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
e9f00fcb-48a4-4941-86ee-f9967f4b118d | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
e84d9cfe-88b5-4eaa-8b9b-25ccca25c024 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
dbe3d212-618f-48d1-b1c0-40858e895c62 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
cff6b214-5ccd-4972-9dce-2ed3393d64d8 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
c703fc86-af30-48f2-a543-02218fd1832e | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
b9b73726-0207-4b26-bc56-4ebdea9c8379 | Pole | 2 | Distribution | 2020-07-30 | 2025-07-29 | Level 3
e4cbb4b7-6344-44d1-9040-8190f557bddc | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
fe276f13-e176-4342-a789-6f96623eb761 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
693709ed-c576-4234-af7c-41068ab22b0d | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
3111d693-dfda-4ec7-9f2d-e2a45e58f8ee | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
fdb40fdd-130a-4d12-8cac-410e008a66d2 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
b9ed212d-c65b-4da8-95a6-f9e331b51600 | Pole | 2 | Distribution | 2020-07-29 | 2021-07-29 | Level 2 |  | 0:00 | 0:00 |  | Pole definitely needs changed out
bbdf13b0-7cf4-448f-a4bf-3b5f07b0172c | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
e433fabb-6d6e-4786-85be-7151856ba7fa | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
a586fa3a-5e0d-49a8-9f9e-a9b8e9cce037 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
dfc9c00f-4892-46db-a67b-6729c6027b55 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
d78ca063-ac73-4aa5-a0fb-978b23f7d073 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
cc63cf0b-6844-4d5e-b954-53d1f8ef0e80 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
d0bb76fd-5dca-481c-8b9e-8678aeaeaa8d | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
edce0504-399c-4c3b-a2cb-8ed6ab0ba374 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
e8d4af19-f666-4eff-a174-877bac0e1fa7 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
eb6df2a8-0e23-4afa-8d55-a632337336c0 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
c0abcb83-c54c-4502-ae34-f8a6b4272d59 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
c876d12c-2b23-46b0-884c-a1de489372c4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
9ee2413c-d189-4b77-8edf-7431864abfa5 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
9784cba4-c0ce-4787-bdad-482aff9567a9 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
7c69f66a-76c3-44f1-8297-8179bf540365 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
8a064dec-25f2-40c4-bb8a-f4d4250bb05a | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
8dfc44b1-bf2e-4274-8197-6af57753517b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
f22dd979-5340-48fd-abca-7d9ba7801da3 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
a631df52-39fc-4fea-8d46-4cf22257a836 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
36bcfa88-b9b0-49a5-826c-93a8fdee5f59 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
1f916061-aaf9-4807-abe7-7d6191f0de6c | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
a6c86b8c-da3b-49ac-8efe-d12df7df666b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
248f7ed7-2e31-466d-9fc7-0b5c8af7eae9 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
193e3815-f98e-4087-ab8c-a98e2ec355ff | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
1f2c40fe-c02e-43cc-87c4-5bea377fa0d2 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
1b308029-a7a1-48cd-962d-4c49080299c3 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
0ab79c47-1aee-490d-9cfa-74ce0f6d2067 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
5f4d106f-440f-41ca-95d2-b76e20e7514b | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
5b37d8a4-3fd3-401b-8a92-ee6324dc52c4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
74285a22-5e06-46e1-a1c1-63eb5b833fc0 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
7007ce8e-ee20-4f47-baa1-9e7661759f97 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
6d58c532-f052-416a-951e-232b73d5ea98 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
4a9f5b49-79d2-4fbc-8854-78931865ba37 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
49b1aab9-da8c-4e05-a481-43e6c6b751ba | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
3495b74b-f180-441f-8bc1-0e87be8ef2e4 | Pole | 2 | Distribution | 2020-07-29 | 2025-07-28 | Level 3
48ff97ee-f096-40e2-80c6-79ad6e0f1010 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
62d91f4e-7d90-4de3-93ea-cbb2d4086e17 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
57b9bdcc-ad8c-48d2-acdb-13697751ba2b | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
88bac969-6de0-4066-84fa-f923d58dd592 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
9339479d-15e6-4b4e-a74c-63d32f9742f4 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
c26ed660-6679-4137-85dd-d702ec2bc333 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
cf3366d4-2f94-4442-8694-a54ed5dbd9b1 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
b791c4ff-1208-4a4e-ac5d-02706af92bf8 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
e0aea6cb-3892-41a2-a92c-c10ae6d50647 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
0549899d-67b7-4e22-a7b4-70f665d21b6f | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
5cbc8dfb-85d1-4533-bad3-75ba5e67bd63 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
ae5168cc-9f3e-4869-9dc2-a275595d773c | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
aacebaa4-e2c7-4490-b0d2-6ad7bba36c17 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
b6a2eebc-b732-4904-b7b3-2a91b74435e8 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
e0e41d57-2316-4497-be09-37f8403ddfd4 | Pole | 2 | Distribution | 2020-07-28 | 2025-07-27 | Level 3
4498c0e0-4771-4f08-b24c-c2bf5b087968 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
6509f087-f157-4b0a-afeb-61a7bad2ae19 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
5626322e-0487-4f57-9373-d0ad1ad1c27d | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
f1f3a918-1ca1-4190-bd29-f4633a548a9e | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
26cc9f27-6d88-4c56-84a3-79d74c0f16ea | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
d0f14781-16ae-4395-acb6-bdc59bc37df6 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
377ea0e0-3b5a-49c2-bc35-e62fc260b8f9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
90449a01-0b54-412d-a266-58b3fb1c403a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
24ede8d3-94c6-4693-9295-63130864f5a5 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
d85e5374-c715-4a59-8e9a-21ece63cf463 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
c5bdc97f-e027-4039-8ec8-d3421ea340e3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
b9516bdd-c9e5-4ec2-9ea7-ca8c8b7cc0bf | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e81cd987-ec11-40d2-acf4-67599cf5c5b9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
c1708261-48fa-4aca-b30b-a327cc7ae9c5 | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
9ad72806-0e0a-4d42-8d2a-0bad5c92f8ba | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
d1de505c-6b60-4c06-a3e8-5ec1da9cb29b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
bbb71932-fefe-47b1-83d0-5b92e63c3c98 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
859602a5-0c5b-4ba9-9856-0375b091dbb4 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
7221de15-46e0-4765-b4ba-4f00db901a85 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
240f5504-42f5-45bb-85e1-f8371f776cc0 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
0aafad34-42ac-476e-ac8c-54c862e16cbb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
a63ebe2d-d7a5-42cf-9f66-e6d45152d6e1 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ce51b1b2-4597-4f79-a22f-87a947b51394 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e07056a8-fe97-4a0c-aa40-5667a7f90580 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e4a6e208-a721-4c91-af40-5065b5850b8b | Pole | 2 | Distribution | 2020-07-27 | 2021-07-27 | Level 2
e3f47c04-c64c-47fe-aac7-7d357fe1a0e0 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
97ef9a56-58d6-47f0-b54e-5adba61d01dc | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
d6f48278-49b5-4c0d-9acd-d7d9bb6413c3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
cd0f9b49-edcd-44f5-af7e-082c4fc8b828 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
81180f46-e739-4a22-8676-936e05f70a26 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
caca63a5-c510-4cef-9de8-ddfdc645f616 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ca8196b6-beb6-4c75-82ba-61cc33c78fdb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
c984bb3d-c177-4894-8d44-24d6feab679a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ea2ee312-b599-48aa-a510-2375b951488a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
ee2bad73-8101-4480-a5ff-1ec3567132c5 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e75ffa6a-b9bf-45aa-a6ff-f1535dcc73cf | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
e77d9ce5-76b2-4e8b-9f0c-1a425b5961c7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
f97e627e-7e39-4f41-98c0-61ba9b377a09 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
c5eade21-f3b4-41d7-9e41-90b2f6e046d2 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
52a7be7e-b1fb-42b4-8801-a7f34327bde7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
4a5579b2-7175-4948-9702-016a4d552df3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
5040948d-cecf-4677-a2de-3f9eaab147b9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
bc9ed3f5-d2a1-416d-9e0a-1c7738dd7c37 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
a9bf8b0b-9cef-44d2-b61f-b2ac60b9320b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
bac3de06-73bc-4427-bcb3-f9a181b0042c | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
1f983b94-d24d-45d5-b246-da45b6367fc7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
a2e84a4a-54a6-4ab1-ba9e-f94b68ebe30a | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
a0c77977-a560-4a76-a444-7c7316b0995b | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
88c264f9-e4a0-4a5b-b8df-4720c9ed66b4 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
8dc0c9db-6268-4b04-9b72-8c795e33b2d7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
802a7fd7-ed36-446c-83ed-e631c056bce6 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
8534da5d-a8dc-4b42-8119-d0bd06e2f0e9 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
536eeab0-bf6a-443b-ac5a-22f2b888f0f7 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
3e253b70-8ed3-4288-84b6-d241933fd525 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
325fdf71-c816-44db-85ea-3843ce618bcc | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
256c610f-a22d-47da-88eb-212cc5eb9987 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
16071641-3702-4977-bf43-a54664ef80cb | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
04fb1bc2-11a2-4207-8216-58d6856f9f21 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
410758f3-b72c-439b-af9e-fb1771285d7f | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
6052ce87-bd3f-4ead-9833-c40e5fcbd947 | Pole | 3 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
19ce54f8-126f-41d6-bce6-55edc5d1add3 | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
16079d29-deaf-425a-be8a-2245f5bf19af | Pole | 2 | Distribution | 2020-07-27 | 2025-07-26 | Level 3
1cbce5f6-c8c5-4558-95e1-588168863eb9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
24498ce0-e1fc-4109-808b-1d4071da1e88 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
2414fa95-46c4-4c84-a207-61d4018eb31d | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
40d16bb1-c5fd-4485-80db-25436f30aeaf | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
48fe73ee-9948-4386-a7e2-2420b1d71f42 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
46053864-22bb-47cd-9772-65731f1be5c7 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
5d4892a3-546d-426d-bd2b-27b4016a7b7b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
6af7a202-7a76-47b2-843d-d3405b8def54 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
79cea3dc-6837-4cbf-a132-5dc114de007f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
a0ff8995-3177-47a1-8e4a-a49e3eb61fa0 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
9e72f818-3d7c-4d12-b55b-1ad6f5f80ba3 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
a4ddd710-4d7e-460e-afd7-ba537d5f0c12 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
a58ffd25-d7a5-473c-9c53-133b954cd1b9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
2fce35c2-08fd-4336-97f7-70d8457934b3 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
bc0d92df-f8e9-4213-a4b8-651c5f98d9bd | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
faa804ab-0c23-4062-bbc9-394aa6f74b7d | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
653b50fa-bec5-4939-885d-46121f5cdcd9 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
a2d42460-8559-47cc-b617-62c7bfb82140 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
ef11487d-6f1a-4269-91ce-e2205c6a2e7f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
5be44354-cfce-4926-af84-11da50b211fa | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
894bcc58-a829-418f-acd8-2ab8d55438f4 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
95f90b1a-5519-4198-b78a-83e85d26ae7b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
d8506054-6f8b-4ade-b5e7-b3f2679603fc | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
b3708441-83ea-4bdf-b5bd-350e20511b75 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
da0f11d5-e2ac-47ae-9d6b-8cec2b0e68c0 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
d5af6537-e686-40ca-a17d-e24a9b91a5e5 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
cf986275-b8c9-4115-a8ba-1246522517b1 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
bfb2b51f-0065-480f-b240-6d6d417138ef | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
8ac96b96-71e9-47bf-952d-0212e8762f58 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
8a06853d-dcc7-4258-917d-37d0cccd6351 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
31463294-66e3-4dfc-ad24-6c43d7ac1a8b | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
76e58a45-cb14-4453-92fd-dffae4d9172f | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
9dd7c588-3bf2-45de-ac05-4010301dd772 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
9ba9c733-6653-46a6-a735-ea2c9baade51 | Pole | 2 | Distribution | 2020-07-25 | 2025-07-24 | Level 3
fdbfcc1b-3376-4b23-a829-1caa3373725d | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
3d28c191-d444-4a96-9e89-299617c57217 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
3d1aaf44-3d1a-4792-a657-a853978901a2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e6f77305-c823-4467-90b6-6c054a208c3c | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e0f896da-cf58-4b2c-a52e-6720c90a28d1 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
19baf206-5c26-4d6b-bbe5-8a2c704aa694 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
aed073ee-3047-4e68-9716-9053c86c2125 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
aa64dc5b-aeee-4deb-9619-1f354a3e7fb3 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1c12eec7-5ebf-424c-83a8-fd5f478a608a | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
802b8fc1-c6a7-4869-be3f-eadcd1ae393b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e4a0c59a-b115-466a-9505-8ce23b616aa1 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
a61eea3e-4d56-494b-b7ce-f440da7f71a4 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
ad3d56a0-1031-4e6c-b671-fa7f41777979 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
ecb5faf9-6e0b-4b35-b555-a75dcebae774 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
62241ba0-b7e0-4af8-84bc-f9ce14c3a198 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | 0:00 | 0:00 |  | Need pole replacement
e677af6b-a06c-40ee-94c3-7b25e6f97f7f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e369c0ab-7a00-4cb0-84e4-a8040b994409 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
c0778902-b75b-4846-8def-337b8b43e207 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
e0ba35fe-cb16-42cb-b192-aa5612a1b339 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
d545220d-91d9-4cba-81b2-77722478e04f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
d25e5082-eece-4711-a22b-cfc8ba2f7553 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
68275e3c-66f1-49c2-bb85-4f36cee8c165 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f6c3a41e-6d34-434a-8bfd-644f9b1fa854 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
eb6cb0cd-04db-4cfa-afde-6d40409cb012 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
0b47ebd7-c425-421d-86b4-5d53573a560f | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
b405f9e1-4769-4bcc-b9a1-0728c496b813 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
fa0fd212-d8f8-4ad9-856d-5c08c4395da2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f91fee5e-7ef2-4260-8d16-bf1434bfc7d5 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f86cdc8b-1efb-440b-9f4c-e27753315103 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
f57b86e8-a119-4adf-9f83-408cde6cfcc2 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
38687e2a-2c98-48e6-a05b-8ad2ab78fc64 | Pole | 3 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
89d6031e-8edf-49f6-91ee-9422099803c0 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
708a52bb-062e-4997-98ef-022033b3c3bb | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1ac5ab46-f1b7-4aa0-8f25-f12dec34e942 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
b2aaaf91-eb36-4830-acec-b1c004751f78 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
115994ac-439f-44cb-9ab8-f0de01013b7e | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
867074a8-218a-4ae1-8e29-d22832ed1860 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
7661cf2e-3116-4f35-976e-9a6cea7a067b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3 |  | 0:00 | 0:00 |  | Needs pole replaced
6df356bf-63eb-4276-9bd9-0dd80497962b | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
5d8387f4-0713-46a7-ac75-d1df6ab20258 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
52e8104a-6e84-4f5b-87a5-fdb12a133772 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
59909e58-1b08-4e5e-a859-5afc39079d77 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
4a2b5025-4710-4276-a145-569f0cddbdb9 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
435c05e2-3a99-45b1-a41d-0c3b4b9cd321 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1d9c3aeb-79e0-4723-afcd-85eed64ca037 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
1d0983f2-c338-4fbe-bf9f-27907390bd05 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
20f4af41-75d2-460d-a866-7a0db49de817 | Pole | 2 | Distribution | 2020-07-24 | 2025-07-23 | Level 3
27404532-3408-48ad-9a47-7a7cfcece515 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4a39d4a5-6c73-4261-b391-da50cf40d701 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
60cd121f-d795-4c5f-917a-24e91332c073 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
00ce0865-0dd5-4d91-aa90-01561d97be37 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
085c2c25-5898-4f0a-bc5f-9385d146de45 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
21565dca-9bcc-48c2-b026-e547c5d98e44 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
1b06439d-9ad4-4df0-a7ba-1fc62015f25f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
47fafa8c-cb3d-4110-9eb8-d8ecc0b3cf26 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
d54a66e7-fb70-4ed9-bf6b-732d8ce29998 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4398aa7d-1a63-4f83-924a-a414910ad33f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
25d9e6ee-5ea9-48ce-9fc5-e447f997294b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
37198e6e-e7ec-4d4d-af04-1ab1359c4c2c | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
54cebd87-2719-4443-a224-8b692043b06f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
7040eaef-d496-4f0b-8448-a8adad58fa11 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
7acfc8db-4e08-45de-986e-ac95fde0dc49 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
78ce8d24-c839-4120-9cd0-b7a964b374b9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
885704c2-940f-4d6c-834d-76a9dad1fc16 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
841db771-85ce-40f5-8c95-498545060e61 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
a71d4161-dc15-4cbd-8cf2-1ca301cd624f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
9c8222f1-a13b-4444-9c30-e8e4d6adc330 | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
b4d30087-ca3b-48d1-aeb1-e6960034c54c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
5972564a-69b3-47ab-8170-913e61e0276c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 0:00 | 0:00
bd13d8ad-9fae-40d2-b038-92498ae8218a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
0d8ee1c4-f016-48f5-be8e-32869cd24322 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
f28dc49c-cc67-4dfc-b9b6-f6662dd41d18 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
05a3f811-7a19-4417-a272-2f63df0e7920 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
3021d73c-a8be-44f2-b25a-46b72896598e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
8f09317d-dd5e-4588-a0db-2f9f2a0fef78 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 0:00 | 0:00
9b6a594c-0c09-43cb-b4e3-b62302ba649e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
f4719c35-e1e5-40f0-ae0d-44e4d223b884 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
e0776c6d-73f9-46e2-8f4b-28cf2d1d77a6 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
944e1cd3-f96f-4d26-999e-1fd2623aff73 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
fb95a9e8-1af2-4c28-871b-9d0e00e3142a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
ee7ac0e6-b9c2-4193-b7b9-aa9910a7fcb8 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
d1f04ea7-6d73-410d-86ec-e34a73e428f7 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
c92ae763-7071-404f-9f90-fc83c0fd6867 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 0:00 | 0:00 |  | Pole old and cracked, however no pole change needed at this time.
d7ffe809-1b0a-46e2-ad0d-6ab7239e3f48 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
354d9ceb-7af8-425e-881d-9e6dab935a0f | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
e3fd1a61-8c49-4ba8-9074-d018b8c85d2c | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
df78451d-0c2f-4b78-98bf-6bd6865c03b4 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
419942b2-93f7-4f7b-93de-bbb8b9b2ee18 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
bd407c35-55c8-4b8e-8678-1f5bfcae0a03 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
8f577979-a23c-4d3e-88ac-c169a0d7597b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
d398e978-0e99-487c-9605-e8fbd109843b | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4478bc29-cce3-4387-a2cd-c32a3e1f3acf | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
363e3f99-74c0-4428-b074-bdba35b4b9b9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
2c0100ac-11c8-437d-bdf9-717f38ec384a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
4d7435e7-f3b7-439e-bca6-5981e48ce258 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
53e74fcf-a45b-4b18-847f-098712d8972a | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
92c622fe-9ed7-4249-9005-3899c4084d2e | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
863aa4f2-b747-4f64-ae9b-8879f0fabd8b | Pole | 0 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
04475d42-57e2-4981-941e-2b3de281b128 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
1ed3847d-f7fc-4074-89f9-7a6b653869e1 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
1ad2d8df-a69e-473a-935e-3aaea16136ae | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
6ce6c076-5091-4dd0-83fb-b93cbd937e95 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3 |  | 0:00 | 0:00 |  | Replace pole unsafe to climb ,bad place for pole shape corner
5cb2ac38-d26c-404c-a8c9-f0d77e0c3be9 | Pole | 2 | Distribution | 2020-07-23 | 2025-07-22 | Level 3
c678b42d-01f6-468f-b181-ced58d55b8ea | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
9d2cf61f-5a50-41c4-98b6-e174e1d019d6 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
9f1eafbe-ed7b-4906-acc1-7b1076608be3 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
190b03f7-b251-4993-8382-15af1568e858 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
1a799a6a-5541-4ab2-82b8-3e5ed80819eb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
155762f0-4785-463c-8856-95f0551ef22d | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
0786dad8-bca3-499d-bc57-785b98ae8d2f | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
69208e43-3a14-48d5-99bf-1d3b0ae68c14 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
690883b7-c36b-470e-b002-9e20cb13309c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
0de55f19-e2f8-44be-9f62-df9912c0d1d7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
598c74c6-8ea9-4d3a-a02f-b83d41f8dc50 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
d53a06b9-9c2d-4e7c-a637-ec8a8f9a59a9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
da133657-de75-4ac4-9604-1690dbe4c606 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
da0e6c72-9e2d-4933-ba8e-ada24d403f75 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
e24506d0-e73f-4c09-a7b0-33b74c5bcb57 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f77c1508-8f47-4721-9e1b-92e915f963cf | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8ad250f5-f519-40c0-b058-4b8fcbbba1b7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8dab747a-3709-498d-bcf7-506777190769 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
d85f85ff-5cbe-43a2-9ec1-20846a6e0d00 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
7914e5df-8243-4f12-874d-6f2b9c738878 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
b7942559-3236-4f98-9a47-f6db44a637d7 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
b2bdc967-b469-467d-8186-02b7f0ae0029 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
a08fb303-85d7-49de-8aec-e0829ad05dd3 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
e00c735c-a286-43a1-a31a-00fb36379f4e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
c042e979-570b-4978-b783-689160cf81cb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f13e9beb-6897-4157-9214-e0c672b568cc | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
ce47d1ae-af91-4ebd-b247-ca19071bbcbe | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
ce40b536-e69b-4029-b28a-c833c18157fe | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
cac63fa1-8a82-491d-92f8-e1330f14a5f9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f05dcb78-2778-4503-ac04-9177a07287ff | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
1963cb4c-b18a-4ebd-b74d-0182939b6df9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
1d9584ef-ebf1-4864-b4f3-5789b70bf57a | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f45cfb59-ba99-4a2b-b1c3-cd66d4fb930b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
11120c99-a2ad-475d-8dbe-b54e7075998c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
c9c8db20-aab1-48da-b1c7-1bd83eefbc2d | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
b9463073-4e7b-4e41-8295-c1a0a13f00b5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
24b987f4-5597-40e5-af46-782b541fa24b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
26e77652-6876-4728-a567-0a7925d3e879 | Pole | 2 | Distribution | 2020-07-22 | 2021-07-22 | Level 2 |  | 0:00 | 0:00 |  | Pole is rotted and cracked. Pole carries mainline for 3100
84d37068-9341-44d8-964b-07ad838c664b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8004e28c-2a38-460b-8e21-887038ef0251 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
8b65fdf4-59bb-416e-9ee8-be0b341c8b5e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
780fb113-4ded-4ce8-b6c9-bfba421c0616 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
73b3a429-219d-4dd1-bf1d-10fce518c971 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
50b568f2-695a-466a-b98d-2997535f785c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
61fad609-a547-4a6c-a6ad-bc8ce0eae09e | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
66646f9d-524b-424c-a5f8-4cb771e41843 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
35802a8c-3856-4a9d-8eb8-03a9413009fb | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
2e17ac99-11ae-45b8-a9f1-273d58ef5eb9 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 0:00 | 0:00 |  | Base of pole missing big chunks has been hit by plow. Pole top rotten. Pole needs replaced
3c39e64d-f70e-4e1f-8251-021fe85f1fd1 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
098c164f-7e9d-4633-a5b4-88153739b5a5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
3d7ba87d-8b13-4e08-bbcf-24c034797c1c | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
e0cc2876-9cd0-4a8f-bb2f-c03d14cd63c5 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
9b2847ed-2921-4ad7-bf63-9dd326765631 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
a22d6ed9-e6ca-4e29-9171-6c0caceeef9a | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
04febacc-9966-4a43-87eb-69a86f1e24f0 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
f9e9047c-b34a-4ed8-b73c-daf01b292062 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
60a9223b-21ef-455b-aa5b-5b6ff35fb81b | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
16f4b1cf-f0f6-4e81-94a2-2595d9f7dd64 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3
132456e1-0066-4fe2-b241-25a488e5a680 | Pole | 2 | Distribution | 2020-07-22 | 2025-07-21 | Level 3 |  | 0:00 | 0:00
8e34fb4f-63b5-4512-be3b-bfc452499ee4 | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
e7cac274-98c8-44c9-b6bb-9feb6ff071ee | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
275c3a42-3c2e-4a82-83df-8f8cc7b3f614 | Pole | 3 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
07620583-adf3-43cc-9a91-f6834a0b0554 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
fe617fe5-7c30-41f8-a77a-16bf41ce9204 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
12b57d87-721d-4b2b-96dc-aeb535649d5d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
e5392381-9f70-43d8-ad9e-a1c9298bee5f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
362d7092-0399-4d99-861e-03d354a068ca | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
1258e9e6-143b-4ff1-913e-86cccc0089e4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
36dbf361-c960-4a34-931c-5a8f2374766d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
38358e00-bd4e-4880-8a0d-c4b02e134be4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
3253b362-4bba-4929-beb9-1c2410e24140 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
64b88181-53d1-4653-8691-2faf0d2e5b99 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
72f98bc5-e352-4f42-9d9d-edc4089c6c16 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
6ed0ac91-9311-4139-9280-68f3823b8899 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 0:00 | 0:00 |  | Base of pole sounds hollow
8bb19de2-7608-47d3-8038-6e63998f79e4 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
85c68410-ff3a-440c-bbcd-b64ef788ce01 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
92d9ce94-74b2-4d6c-829e-41e7e46e7d08 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
9cd705f6-8d6d-48f8-ab56-7a7bde2acd07 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
a4c7d7a8-396c-4809-93e8-77154a7a0f9d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
a349e40b-0ddc-49ac-9e78-72a187d965bb | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
ba08c030-cefb-4d9b-bfbe-5a994ecf831e | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
b6d853d6-f71e-430c-b623-547e88375d43 | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
aca471ff-7d2e-4d82-9042-afea6052942d | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
c5865cee-90a0-4085-8cc1-13936170ee9e | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 0:00 | 0:00 |  | down graded to level 3
c21f4584-7d63-4012-a386-39d322e656ae | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
bda08f9b-eeb1-4fd5-88a8-3a0bd64601f9 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
f7dc410d-8814-4910-bc35-62597dfda333 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
b5e13980-29b8-45e8-88e8-41f8d337ae76 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
f68f4919-e060-40fa-80b9-832faaaaf89b | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
f387ad30-1bd0-459f-8e75-32c891644940 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
f4aa5d71-2f63-4e72-b1d3-933e25c3c387 | Pole | 0 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
52abae4d-633f-4648-80e4-f87a66fdfcde | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
6ff3febb-d5f9-4fea-af9d-121db7f0cd8f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
da7599b7-749c-4b43-8474-2c4e8a0c3bad | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 0:00 | 0:00 |  | Pole has cracks but not bad enough to fail the pole. DoesnGÃ‡Ã–t need to be replaced
ced979d4-fa4d-4d59-96bc-57639d2353f8 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
9409c75d-7c30-49b3-8146-fad952b09d54 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
d5108369-35a7-4d36-bb0d-80259427fbd2 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
dc0837f1-e8bc-4868-aa00-9d32837d377c | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
c70b88aa-de9c-46e8-86f6-c4b633986114 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
694ccc4e-d5b4-4526-9b6a-2ea31f8cf2b2 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
fbc61eb1-b8c0-41c0-a335-9fbd4d1b5658 | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3
8e0aab8d-ca63-42c8-9d7c-981a9fcf5c4f | Pole | 2 | Distribution | 2020-07-21 | 2025-07-20 | Level 3 |  | 0:00 | 0:00 |  | down graded to level 3
ab2da9cb-b40a-47b1-a72e-ef95d3c05cb7 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
3a5f7a23-7bc9-450a-a5f6-d8537cec5340 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
ff6992f4-747b-44c9-af52-294742064d1c | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
611090df-9c8a-41d2-ae6f-82029f640a35 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
30b87931-03c0-4850-b683-2f30d7609a4f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
35fe3b8a-8969-4d06-8b13-bd1f63a3781f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
2a28e0ca-8af6-4972-a0e6-028beafc7f84 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
7229fb24-2a3b-4ec6-a7ae-292bb838bea2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
4b217c92-9fd5-4cf8-b6c7-3a1606ff6dd1 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
c4551ab1-5a6f-4b02-9abf-7e1a8258ca49 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
efdede95-9920-4017-b8bb-5a86b3615374 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
2ca30f9c-44c2-4b1f-819b-f0331d5f1d5e | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
9612ab60-195d-4464-87fa-f77f2c8ff299 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
e3976782-8580-4c31-9870-32e8c144e65b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
9564ef0a-02a7-4c72-9c69-ed3d50f1ac4b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d6528172-7ee0-4858-971b-2e0d6f19aaf2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d1de1219-f68c-4ccc-9255-498c2c1832cd | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d0aecece-4e54-491c-a62a-125922771b26 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
85db31c4-72df-4cf5-ad74-8cb2c82e946b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
b2f48594-f25a-46be-b4d9-2d3e50b21e20 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
73a73861-daa7-4c3f-a14c-58fbfb56a8b4 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
9e52205a-a613-47de-a1e7-5457af2c7402 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
e6d06425-ead1-475f-bf9e-f3d3c7e5c790 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
fa420072-be74-4196-9c4b-2558018eb189 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
5ad2e8a0-37a4-49aa-aecc-3e80de2e686f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
290bf067-f873-4001-aa45-bc06dee2ade8 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
dbc765fd-5adf-420e-b00d-1544dbfcc9e2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
f8648ac4-9c88-441c-8e95-0dc27c7723d6 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d2bc092e-634e-4ca0-be39-d42640e3999c | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
c5dd986e-495d-48f7-be1c-a78e0835a290 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
bb13b521-2d96-473c-aec9-7d21f83b770d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
a86888b6-6692-4aca-9343-84360627b78e | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
9cb15299-16b9-4f1b-90bf-330239be398b | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
69fd2fe0-51d9-4fbe-ba2c-ba81f969327f | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
7931707b-99c7-4120-8ed0-e097149de49d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
626ebcdd-4704-4010-a8f2-076f04d2b05a | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
596c30ac-3828-40db-a384-247fc8298fca | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
4305418b-d31a-4981-875c-5c025b4e9657 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
46936969-c8fb-4c15-b6e8-470a48a7e18d | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
cc3eaf5b-8fe8-402d-876e-746bf55e7f85 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
06ae4613-be32-4a1e-b034-6e1b01532978 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
196bc163-a8b6-4590-b677-4f85b86ff3a6 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
816cb613-0007-4008-b5cf-dbd15e40c22c | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
6b3c1700-406a-4410-9d58-bf50e1e2e85a | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
6c92aeeb-ea13-475d-b2dd-56b4dcceff1e | Pole | 2 | Distribution | 2020-07-20 | 2021-07-20 | Level 2 |  | 0:00 | 0:00 |  | Pole need to replaced bad shape move pole off owners driveway
e1aba768-76bb-4c00-8353-56688c2b1df2 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
06e02a1a-8240-44e0-a277-b80eac4c6ff4 | Pole | 2 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
85b474a4-0499-48ba-ab38-ffcfd2a4dfe2 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
28ddd9e1-2095-4504-a177-83922d788c04 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
17ed0436-cc43-45c9-bc37-3459a1b590b4 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
d0986280-a573-44b3-a36f-e142da9b98a6 | Pole | 3 | Distribution | 2020-07-20 | 2025-07-19 | Level 3
2804356c-9fe4-4a49-bc1f-17583af14fef | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 0:00 | 0:00 |  | Pole top rotten needs to be replaced
19268f5c-dfbf-437c-b14d-e8ca4d8d5a2b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
2311241d-3d0d-459b-ba7b-c8de086d8219 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
c4c63535-fa10-4603-9374-be4065b1f623 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
efbb483a-158f-49bb-85bf-29a970c0febe | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
4787aa03-530b-4213-beba-bafc340fa18e | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
30866adf-2311-4c6c-9ce0-050f651409cc | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
8a484f29-fff7-4857-9089-2654b7eba806 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
8509fa78-d222-4e74-aa72-1846f285b24d | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
81f2ec27-6401-4940-8c63-63105b64f621 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 0:00 | 0:00
ac043725-2f27-47fa-99d9-f1ca294dfdf1 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
a92bbaf3-b018-434b-9c0c-3a57327715d9 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
a962400c-fd23-4609-a5a7-4ae59a61c4e1 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
f4593b9f-06de-4c7b-afd0-6b9df836ec22 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
c451203f-0202-4240-af51-175eba5a674b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 0:00 | 0:00 |  | Still needs changed
b21923de-223f-49b6-8122-51a19ce0791f | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
d8a8f95a-5387-4e46-b565-124a697f9272 | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
a3e0fae0-27bc-4339-b082-c43b5de9e03f | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
d00805be-e237-4d7d-b3a4-b11fe00f07ba | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
b816f01f-cdb6-47bb-af95-1d24dfa3e796 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
fb2ccd4c-2017-44d2-87e7-ae25026ec653 | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
f464f476-f015-4750-b8d9-a98dd5b6c26f | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
5161549c-315a-4bd9-8be8-667f5aed786b | Pole | 2 | Distribution | 2020-07-19 | 2025-07-18 | Level 3 |  | 0:00 | 0:00
6417255d-899b-4456-b3c6-fa37231f5386 | Pole | 3 | Distribution | 2020-07-19 | 2025-07-18 | Level 3
6a2e5370-0f7a-4fe7-9e57-b33c403d3ef3 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
87aa3d4c-0fb2-4fba-9072-6727f95cc351 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
84c1ff77-3191-471a-a3a8-57f29fd2a95f | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
bc093c8c-ecf9-4a3a-9bf3-b45cd6bea5c5 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
9c401bfb-2322-4c76-833a-fa11e6204837 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
11908b5f-0fde-4dba-bfd3-92ed8e4a3545 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
e7ef003c-d2f5-4286-b943-78fb99c2f935 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
e7c16dd1-9c91-4812-972f-7c1bcb5708e5 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
f6e09d6b-a53a-4261-a4a3-d46456c8e254 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
60bcc842-a224-43e2-9dd6-e1ce849175b7 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
8e116f2c-86dc-495b-b264-eb6b074fd4c0 | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
55f7fcbc-abba-4161-878b-35b0ebefbbdf | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
6bc63adf-03d4-4b31-a0a9-bb5f638750bc | Pole | 2 | Distribution | 2020-07-18 | 2025-07-17 | Level 3
6f2802bb-c03f-460c-8737-2d1e1d2e70f5 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
6f8b5209-cdcb-4711-8a9e-7d62f74c6144 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
59c11797-c686-4198-98a8-360f1a092c54 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
5ca68509-e990-44c1-bf0a-09ff47d10245 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
344583d1-f707-4ff7-b50c-db6c291a323e | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
3f538d4a-ec5a-469d-9ef0-fa0a6260a2f9 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
12b002c6-86c3-46e5-ae29-fb22f34d2f94 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
1c3e7cff-0c2a-47b4-8f03-7556f7ca60bb | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
b71347e2-5250-4981-bbcb-38ae685dc42d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
93609343-806f-4598-b67f-1eaa9784a017 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
4815b3e9-76d4-40cd-b715-ab9e63a62be4 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
167b91ed-1f3c-4519-95de-ee4a519c2963 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
b95397ff-1bff-4008-b171-68cb2bd58e68 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
4dff9202-a97c-48da-9870-9744cbe7b268 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | 0:00 | 0:00 |  | Pole leaning hard towards building. Triplex can be grabbed from stairs of the building Needs to be 35ft pole
f833f559-06cd-4272-821e-21572ce4406e | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
f9220b3c-33c9-4657-b286-389740b83b9b | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
0dc9c97f-7a17-4bad-a8e8-5f452181e982 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
9737481e-398a-4ed9-9e07-0416dd74317b | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
62db877e-3f07-4980-b74b-2bcb506a199d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
47575fa9-54ad-429b-9d93-235cc2d8c578 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2 |  | 0:00 | 0:00 |  | Unsafe to climb leaning badly
aa630e89-aa2c-4391-84f1-97c61e7d3d82 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
abf4326a-1ccd-4eea-9968-3990dfe656ac | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
96dee2f0-7179-49de-bb4c-d9be812d50f3 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
92b50663-df2b-4ade-83f9-e6e8e754ec97 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
24783cfb-5044-4bff-9a6b-281582e9c1e4 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
ec65114b-27f6-4e39-b7f9-03bb08b23d8f | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
bad4e9da-5b75-43a8-95aa-b2c82050c272 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
db932bb5-8bb9-4d90-80b3-855174819c6a | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
e1754114-6a89-46c9-a307-b47eab8306f4 | Pole | 3 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
d752e5ab-64bf-4cd9-8e3a-fd4624510d79 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3 |  | 0:00 | 0:00 |  | Pole in good condition just natural cracks doesnGÃ‡Ã–t need replaced
93b03910-1519-4d79-bcd9-a5a6578a8a12 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
ff8c77ad-a4b7-4cca-a85b-0e341bde2859 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
01f717d1-7308-41ee-86a4-940501af91f9 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
241ba7fa-c720-4591-986c-d3b18dc938f9 | Pole | 2 | Distribution | 2020-07-17 | 2021-07-17 | Level 2
a05a06e1-9d4f-44f8-a4da-d7975a901ec0 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
70a0627f-ab7c-453f-8fcb-484b435c3452 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
0f5a4247-7f07-4c99-9ba4-4813ae448809 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
926a72c5-58d0-4523-938a-7eb5f1b78a8d | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
7c4db3d1-1106-4899-a4eb-5377de5241e0 | Pole | 2 | Distribution | 2020-07-17 | 2025-07-16 | Level 3
c06d3336-ea87-4d00-b924-c66bdc5c197e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
cf8753c5-d61c-4d35-a7f8-ff6b4ece8324 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
e5a1c66f-16f4-4644-aac5-fc2f6a0f0fdf | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
ec8f1c88-ca51-4c18-b26b-b985a8ea9e09 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
1f114070-f894-42c6-8b01-a5d4632aaccb | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
80207ad2-8e9a-4226-8076-c0529428f921 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
61c93b86-24f7-46ea-be52-b2a36942afef | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
0334c31c-299a-4b5f-b805-f2326f4f7220 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
a6cbd979-8acd-40b8-b26d-154669f8795c | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
5d4c9934-081a-4483-a6d5-7c2c0b2bae25 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
4d3fe422-2c5f-47c1-99db-8aa5c1f0d789 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
3a9dc097-e4f2-4859-9c9a-8814593ccb8a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
d0bb3155-c65b-4a5a-a2e3-62b8af6e2f9e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
d3d24e91-b9a0-4161-b809-bb708c53b175 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
8b402724-3a2e-4d75-9544-a537ed05743e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
74f5eac6-b938-47de-9331-74315f348238 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
0b04a3e1-67d8-4e0c-a93e-fc5f43765948 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
1b40114b-b171-432d-876f-01a4c20913ab | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
18c3fff6-a0bd-4099-9727-456d63de6e14 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
ce2a0f74-0a4f-403a-b434-cf8b74ffa268 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
b7eac2fd-45fd-4e75-9b14-086353456a7b | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
efe1b942-82e5-408f-bfb3-a4852dbe45e3 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
2928656e-8f23-47e3-82d7-bc5f867d6533 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
4ca456d0-8d09-4503-abcf-671eee9c3bfc | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
4567128c-ff18-472d-89d4-92d0d7721df0 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
77bff4ba-7e52-4065-8efe-3139cd48cb3e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
a6d4657f-4e1e-4fe7-96d8-619b5959aa0a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
482d19a2-4a63-4692-b1ea-b97df1d84a20 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
168eceb0-93c6-45dc-b560-0396c5ff2b6f | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
0237034f-f68f-4caa-b5b5-1b3d4449a72e | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
6ba35320-b539-45dd-8812-51f43f0c4703 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
74629c3c-9de9-42ef-9865-9e1e4cbccb7d | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
15fdde60-0a4f-42b8-b934-489d6e8121af | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
a9f50b8c-543b-4c11-85bb-f384c1f33024 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
78f38334-8eb0-4a05-954e-34bf4f9c2d5b | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
fc87c65f-3146-4f17-beaa-5f90a8cffd09 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
3d872ec7-743e-44ab-93f6-d71036cff90a | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
5e1d043f-b4ad-427b-beff-aa7026b36ff7 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
6504e2ae-260e-4814-af61-51052ed75d76 | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
55a2bbd2-728d-4e0c-8dc0-1de2f7ff7e6c | Pole | 2 | Distribution | 2020-07-16 | 2025-07-15 | Level 3
5c9af004-5123-43b5-8fd4-e18472a598d3 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
3a12d4cf-64f5-4eb4-8288-b822bc786964 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
3a460b97-8a06-48f0-ac28-901d3920a027 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
3d87b62e-86b6-4e3f-a187-ee47eb6046e5 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
4a3d8b56-c88a-40fd-a4fb-0d1fc8fef922 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | 0:00 | 0:00 |  | Missing pole #
c2fe30d7-b47a-49f7-b525-52124b92718e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
863d578d-efb3-46da-b376-6cfa0fd284af | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
6bcc5a1d-2d2d-4637-b413-681f433cd6b2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
056e4ce3-5902-4996-a68d-6f7306ec5bd6 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
a6fe9675-0109-4adc-b758-352813f7f606 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
64f88342-f190-42eb-9149-603605a5a436 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
c1ef1f28-9135-4034-9d09-063294a5483b | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
2ecd2313-5ce0-4fb1-8d43-7a55265fb8f4 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
57afcd7d-acd1-4dbd-b108-a8362e2028b2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
bab58fd8-ab16-4c02-8259-c05aca64b1a1 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
ae59537b-6c67-470f-91f7-87587e9c8065 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
f9df9a55-39c9-4d6c-bd88-503f1d4b58c2 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
fdd79a73-2537-4e9c-a915-7d156c10b1da | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
99cb0f3b-95e7-4fa7-a3ef-f7c9eb39d343 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
e023329f-8498-4245-93b0-afa35662413a | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
e6db48f8-888b-4340-b755-d814f47fa8f5 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
f6201cc8-5008-4a14-a9f2-9dce3da63b33 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3 |  | 0:00 | 0:00 |  | Repaired high sign
859f4d1c-a87f-4bee-be47-aa2788edf1a8 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
806381ee-a00c-47aa-8268-1f1026f06f87 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
d59c5e89-d456-4dbf-856f-95f32b046148 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
9011ec9a-91ef-45cb-9b94-350e82bee796 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
18577d8c-2af4-4625-97c8-c80a2b7bf16f | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
6adefe5e-cae0-4f41-9fb3-9adb0c64eced | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
591c2e28-1e91-49c3-b8bc-b46ccecb7668 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
1f4b6be9-8e76-47f0-9b37-1893b79a5061 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
f1d7c57e-9957-423e-bee7-de69da3877bd | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
3f56cc60-3519-486a-80ea-feda0f55f465 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
5b2459c9-0c84-490f-98be-a72b3270cd73 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
4f789622-6ee9-4c56-b18f-207894de2d0c | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
21913b3f-17c6-4042-b66d-43882c9c7356 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
38da69a1-062c-406d-92d1-a4bac2960717 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
25c8ab34-c4d1-4906-a0bc-7c28476aa6c8 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
66bdfca1-8808-4a2c-a7ba-5b2832c5b813 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
6d511096-17b0-4c19-b602-da8243c37e94 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
88255f82-12a8-4308-88c5-d7b40ccc7629 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
aba16b00-80bd-4bf6-92de-81f429fd6ca3 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
003a1b8e-3dd1-4fd5-b7e1-9d1aad092aca | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
b358ef18-8ea2-4482-a3ca-cdcea0fd882e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
b257a734-e34b-4568-aee1-4d762fbe0c91 | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
96ec2302-57bf-43c6-a0e3-2637aa48559e | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
940a890a-48db-4f3f-943f-e12b46eb80ee | Pole | 2 | Distribution | 2020-07-15 | 2025-07-14 | Level 3
9c57eafa-c083-4bb7-a16d-a4c1a67f3ed5 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
b7be3051-26f3-4e9a-8ccb-2fa19c685529 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
39b54d10-77d6-42d1-84e3-a7e0975182d3 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3 |  | 0:00 | 0:00
a9c25284-649c-44e3-90a6-eaae94b995e4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
f6c6ac34-65f3-49f7-9e10-7b7fcba18f2b | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
b6ba2138-f206-4422-9413-18969e71f6cc | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
2045bdbe-cfce-4c5b-a2e4-d6c5e6a15783 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
3102b1bc-61ea-43df-b1ee-d56aabdcaad4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
35e8f7a6-252b-4da9-8882-c6b0a97da0b8 | Pole | 0 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
5cf8556c-efac-4258-b13a-d3c8290edd88 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
6c51d5cd-e64d-4d3e-a967-e5f3d2209bfb | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
d0765955-c15c-47ac-807e-d6b9b3402339 | Pole | 0 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
e369b04e-76dd-42fc-adf6-4973cd112cbf | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
dea1d9ad-92bf-4f30-9cd5-add90bf97b9f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
d39c399e-753b-437b-9d0e-d3dc6be72dfd | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
f32a3838-ac6f-4d72-b52e-0d27cb592ee6 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
ea5e7a63-0ef1-4bfd-ba9f-02db6bfc5e19 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
afdf6967-245c-4d1d-b770-6592348bf19d | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
ab3c81f6-75d3-4b0c-9229-3fd4528ef3de | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
bd1dcf2c-1154-4361-9706-667c0f14e630 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
c880847e-38b9-4790-9b1d-d71d6c16cc5f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
c78c1a41-acd4-4896-b17c-e13250784c85 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
a03bbac5-6bfc-438c-b8c2-31c0c054bed2 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
95971189-7f86-45ac-8418-103c47255113 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
956c84f9-db01-4958-a608-fe93cb8dfdba | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
9afb25a7-8e56-4334-911d-d028ee55accf | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
03db0ec4-4589-4769-b418-ab0ad6033bfd | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
443e5d5e-531d-42b0-8d74-f81076661a30 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
0b2408bb-c402-4e00-b0e3-1e87406bedc1 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
0951fe77-6d9d-435d-8a92-a65818b547ac | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
1e238023-4bb0-4b50-b19d-b866493a9284 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
cf3a3473-814f-4f90-b63e-61d09e46ab87 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
4418ad78-a931-4a91-81b6-5edf804a7ad7 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
3a663fab-ccab-43b3-9855-436f204b5456 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
41b6bbbe-86fd-4427-82e1-3ee795c0b829 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
278b1280-99c0-4d0d-b5a0-20d34567cc9f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
5b3e361a-4d62-498c-bc8c-56c9572b50e6 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
5de3af97-792e-4441-9d67-ed157497ce0f | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
6f16aa83-0e34-496a-b063-5d5de5da5dd4 | Pole | 2 | Distribution | 2020-07-14 | 2025-07-13 | Level 3
61726dab-05cf-4d18-a83c-63985a3a274f | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
25ac6250-68ad-4763-bf9b-560bf3fc0fe0 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
c348571e-90f1-4b22-84ca-21f5a0de7980 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
6de9c915-8e96-4ca8-a40c-8c1e4ae75b86 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bdf395ad-2726-4c91-b341-2023c4ddafa7 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
975dd9b4-3e59-45f3-896e-f2caee795652 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
1be2113f-541a-4e01-ac94-5a027d03f037 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
218753f8-caa7-484b-a94f-0529f31e3cbc | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
0f9bce5d-8ce8-4055-8a8d-6d20c3d800fb | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
06cc3d5d-da4f-4a70-b401-3333bdf816b9 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
4af32f74-290c-4e46-bfc7-38f1d2506652 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bc6aea75-f002-4862-9b31-a57090c5114a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
a7647d6e-bd39-456a-8992-4e46ef6ad01c | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
81c50eca-4bb0-49a7-9aff-c40b70a659f5 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
c931e7b2-c5c8-4423-9a35-3da57752328c | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
c63a44b0-0588-4c9b-adaf-b97da5b8f899 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bfe33634-60fd-429b-bc08-9962ff00094a | Pole | 0 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
ab7e51a4-7b28-4a86-9bcc-c2907a0371fc | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
bad09e72-aaf4-45ef-bea1-5c1458b3e263 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
b0fb093e-b5aa-4bcf-b75a-1856e6b6ff28 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
ad1b880b-50eb-4073-8e89-34c2f78a37c6 | Pole | 2 | Distribution | 2020-07-13 | 2021-07-13 | Level 2
85e50f89-6285-492b-aa29-10b3640a6c70 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
076acbaa-b9cb-4d2a-9226-fee4160a29a3 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
cef367a7-b2c9-4ad5-8f80-121802ecda91 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
60d7a4b0-309c-4959-97a8-c8f8eee53299 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
aebbad7c-8d73-4286-bab2-fe126e229fa2 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
6b255edd-ed25-4211-a360-fd29bb6523a9 | Pole | 3 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
e2a9d5d3-bbcc-4546-851d-9bc70f285421 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
2d8c8f16-a95a-4956-ba3e-6f8fedc6772a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
f668d65b-a29d-400b-b075-24f26c06c982 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
fc9db498-54ea-4e27-8b4f-20df72a77a84 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
fc7b7975-62c7-4fe9-b9ff-dd6296f2f82a | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
8e8b354f-a8c1-4f66-be8d-84a0f54eacec | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
8a9cb10a-a529-483f-bb27-5ba21e1b394e | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
a383d047-e090-4873-99a5-63f9e264dbfd | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
aa09c30e-0565-46e3-aa35-6aaadf6c5a36 | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
ba1f1c0c-10cd-4dc2-bf79-f952bb78cc2b | Pole | 2 | Distribution | 2020-07-13 | 2025-07-12 | Level 3
e0940932-bb69-4de1-8219-5c8516485cc9 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
e4defeb2-fd3c-462d-be4f-e1e992aa0946 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
2e684ee6-cb95-4c8e-87f9-6d9ae3c5f8ba | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
cbaa88d1-e54f-4660-8061-3ef6e179edca | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
cd1090b9-c0f3-47a0-9d79-3f4123ffa402 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
957def5e-9283-4ab8-92eb-474b7d9ae653 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
217869cb-f684-418c-9654-6378bf3dbddd | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
b0ceec1e-d446-42bc-96f1-b6eadaf6378e | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
9a69eced-85c0-4013-98bf-0c1090de5121 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
02ab1997-8c82-4fb2-b9a9-5a60b1cacb34 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
1d92fff8-9a0e-4add-a7b8-4a3d8cbef31c | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
a73d38f1-8039-4ec7-9abd-0697fd19651d | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
2f06ca57-5ba2-437e-a1a7-843137e805ca | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
62d22d83-e2c3-4cf6-bf1a-714d8711b0e8 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
63c5c14f-7b73-4783-9033-a0d6afd485c7 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
56873713-bee0-42aa-bdd0-67301e8755f6 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
115df9f9-1924-4a29-863e-6f73d130edfc | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
68dbe3cf-51a5-4a8b-a69b-1470441af42f | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
75253ccb-161f-4d9e-9845-9208899056a5 | Pole | 2 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
749c4458-f0ef-4a06-a7fc-a81f415b9e72 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
74ad17b2-94fa-484a-a23e-10219704ab89 | Pole | 0 | Distribution | 2020-07-11 | 2025-07-10 | Level 3
029131b4-0785-4c56-a449-d29a9f038cc0 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
6fc92763-275d-4223-b5f8-d6dc1fdf00af | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
65d126ec-8de4-4cdb-82a3-2256b95e3272 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
bbd149d4-15a8-47c6-b462-40fa38bfd062 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
2340128f-e9f6-484f-a290-75a46f458ec5 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
284aba57-8f5a-406e-a1c2-8a5249514420 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
389e10e8-a939-4438-9e46-f5911de6b854 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
a0abe18e-3705-47df-bf18-b480954c0e2d | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
a1f9a0a2-e669-4fb4-a817-a2d105e65044 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
a1cce40d-56c2-42eb-8d3b-3f2bab0ef617 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7c8dc814-d882-4c81-8df4-372dd3c350ef | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7a933010-5609-4515-ab08-3a982ae744df | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
72aca320-85d9-4a46-85a9-4b5ead644d56 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ec82d171-f80f-4c41-9fd5-3e15894b2942 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
4bf086a1-ed82-4503-a500-ce8d481176a2 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
f193becc-25b2-4289-a18a-17e6aaa3eff7 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
fb871fe2-feb6-4397-a61b-be3cd4ff418b | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ae881877-ae5b-4df7-be28-3b08c4886ce6 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
94670d55-bb6c-4b2b-90a9-60cfa5b4fa0f | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7f6c9254-b686-4c48-9886-03ae426df60b | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ffeeca76-70f8-491f-add1-5b6698252e01 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ce0a14a5-f0d3-4ee5-899b-d6b48a1e7b67 | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
c98f5eb4-afcd-4b07-919d-5ea45dfd8fd4 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
c1d52933-9662-4b22-b58f-10bd7053c57d | Pole | 2 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
b3a1be52-e478-45c8-be12-5601f631de34 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
ac4820ca-6f3e-40ae-9e17-a637c7718ee8 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
af3fb385-e147-4899-804c-024c8a1f6832 | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7fe208ac-aca7-476f-851c-423b6eb09d2d | Pole | 0 | Distribution | 2020-07-10 | 2025-07-09 | Level 3
7a46c49a-876f-4b95-aee0-75419a7da8ac | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
8d792b1d-3fb7-471a-aecd-0f6ad0190807 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
a4208c9c-14f8-4057-965c-0432a4afeb94 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
28de7189-4749-474b-8420-97a96eeee4ce | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
98bd97d3-30cd-4b4c-83ea-9e5169b023d8 | Pole | 3 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
f797c6d5-623f-420d-bae9-530502569f82 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
d73736c1-9f8d-4655-bb72-509b6cffc1d3 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
ce1e99ef-c521-4194-84ca-b41443e71a7f | Pole | 3 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
db4bed87-98e1-43fb-ad7e-b9b884c25fdf | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
5cfaead7-7dd5-4c16-80b7-58955c44706e | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
acb4af6f-8d13-4347-bafd-acd60cb4fdc7 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
7c24b7b7-0d82-4161-82a3-74e7313ea976 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
96f06149-da11-4570-b19d-7c92371687fb | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
1f590e13-c214-437c-af18-0313d881a3e2 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
102b8a1c-fbcb-4a53-8060-49b706605ef7 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
210ab97b-c5cc-4324-b224-dabf31dcb559 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
b7f99e6e-1beb-4fa2-b4c8-4538d26fc979 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
efc89a8c-3e4f-4a97-9981-3e749ef5f250 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
0b8a8bcb-4c87-4690-9a2a-ecab003e418b | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
67997b7c-f999-4a66-aec3-97263f7d05c8 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
4448cb1a-4cb9-4159-9d03-9ec494115634 | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
4a8b18bf-13ce-45e8-ae56-e7419af93bca | Pole | 2 | Distribution | 2020-07-09 | 2025-07-08 | Level 3
44402463-686c-49d2-9db5-3750d3c03ac9 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
78a22abb-4ec5-4736-bb66-0014495f0c32 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
72028981-a4fb-4d92-a513-50d4248076cc | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
62a85437-6942-408c-af20-a47ff7985bbf | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
5df62bd9-4ad4-489f-8427-5134de5a3b66 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
625479c4-9bc4-483c-b3c6-675a7c5ccb60 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
5a48fcd4-4e98-48cf-8686-f49a80c17e5a | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
039dab48-7ab6-424e-bd35-878ccccbc01c | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
0f9b104a-fbf8-45a5-a750-c150da9b58fb | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
84ce554d-2b99-4049-9e09-0a4b8d13d550 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
07b47977-02ab-41a6-bab0-a2f5302dccdc | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
88599f80-4282-4c60-8dfd-b74de6ab0141 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
8d3a2d38-10d6-4d82-94fc-69287e8fcd1b | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
3b33b767-d154-4729-a074-794e34aae61e | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
23a0855f-120f-4e32-9afe-f66bd242b4fe | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
183e1851-4f1d-4fad-98ca-65a576de818f | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
932a79dd-1490-416c-bc1f-322b3541d400 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
a4515193-5a42-4a24-a5d7-6e865d9c9121 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
a724e85e-8c36-400d-8c46-6676d5332f1c | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
a510252a-8b76-4c18-8595-89194a2d5827 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
3d8e0bc9-362f-42f9-8b65-801458a5fa23 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
8658dc2e-4f45-40d4-a6b7-77ab6cb67a16 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
aab536c2-e237-4961-a3d7-12a9b2a3c86b | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
d0b24701-9db7-483f-ae69-1e34cff4bf30 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
6aacb92f-84a4-4e71-b7a6-41208188f31f | Pole | 3 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
367eb169-e2da-450c-b405-e9da58bd38e3 | Pole | 3 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
01a565ce-279b-4893-804d-ecfdd68e35d9 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
be819848-1845-41fe-abda-9795370756e3 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
b7e626c7-1448-4dd2-8ed3-7465dca1f582 | Pole | 2 | Distribution | 2020-07-08 | 2025-07-07 | Level 3
cac04a0c-751b-485f-bb86-bec8b74ced2a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
d8189565-6f54-47a3-96af-37d0e0c8cb1e | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
0998404c-c5a6-40a5-8f52-f3557ce6b9c6 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
638f8a87-2f23-4abb-8016-c16a2d31875c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
d6e6c551-ff75-49d6-bb4b-53adc8f0ee9d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
f5680546-7a1d-479a-bf7e-ee89a155881c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
afdec874-724a-41f5-9749-aa4cbbeca2c0 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
d051843b-0edf-417b-a57c-babceefbdd8a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
a9ab6ab7-ee25-471c-abc0-3cd04d547907 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
2fbaf27d-5e82-405f-a1ba-850e6bbe4949 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
57c7666d-c431-497a-b51d-a1c9ecacf456 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
5c3f7a04-ad4c-4dd7-aaf3-c2d0d86848da | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
490d302b-80fa-4c9c-9c35-2c8584ef34bf | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
8c2019d3-49f8-4e34-8a5e-43d8f50cf9a5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
8cd19431-121a-4233-9960-dbb3ce26f551 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
75c12d75-f7ab-4d3f-956a-5e83cc171ea6 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
6650820a-acf2-4374-b578-87596ef5a20f | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
6590c18c-c624-4014-9a69-6fde521c7d20 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
c5affcf9-f7d4-4d53-8365-4554100de38d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
f900cbb5-a9a3-491d-950d-c438424e3497 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
0d59c623-85e0-4a88-81f5-75c003a6efa1 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
fb0fd933-8f31-4395-b381-7f9cfd812add | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
5995cc07-d3c3-42d2-9493-28fc9097cf98 | Pole | 2 | Distribution | 2020-07-07 | 2021-07-07 | Level 2
9beab15a-3606-4b07-adde-a707ae3600d3 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
9b649708-b3de-4368-b345-a4f4571ff944 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
ad8cd10f-c662-4538-81bb-56e8bafc3da2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
bb43f43b-84fe-433d-aef7-325e4f26608a | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
c3eedc2d-ce18-4912-a4ed-56c23a29bbe7 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
c3adf9c8-7e1e-4719-a2fd-2a452800f245 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
be79c0fa-1065-4be5-ab0d-09bbf3bcfad4 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
7a755d73-b3aa-4eef-a717-16664cbf4b66 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
96d8d3f2-57a8-4a90-a89b-5e198f305d84 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
162252b0-ea0e-4964-ae08-628bc0d93fd2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
20b61a44-5209-4ce0-b705-5067d2780bfc | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
09789e8b-a0a4-451b-ae99-4fdc82a78836 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
2e08d494-cec7-4cfd-a681-33309fe959d2 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b983ea63-2431-4771-a381-96a53ce83e86 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b4a13217-5857-4480-997a-a7fa3a142f31 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b8b29138-2ce1-4ce6-b1df-d2c4cdf4b0e8 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
40e4332a-0b32-4532-8018-db31e8239325 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
509f1361-6031-43b4-923d-ff8b75fa87ba | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
945791ae-ff42-4bd2-acd0-a9f043292e06 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
db9f0799-2bb9-4f61-a4f8-901221e66b31 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
88d655b9-11c2-469d-aa38-a877bf790a8d | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3c0eb500-e11c-493a-9f08-4bb1c84b3562 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
b50dfc88-e6d6-4861-9730-67feea529433 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
9e17c0a4-319d-48e9-b786-6d85ce7282a5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
86d5d62e-0cea-4f00-af76-15aca8c6052e | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
eeb3e4f7-db32-4187-8127-fba22c230109 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3785822e-c4e1-454e-8414-9b5bdace0334 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3e12d27f-881f-4efd-8707-42bc669ba974 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
3099c0f9-3ace-4cae-8478-f4ddd8ff247c | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
350fd8f0-f559-4afe-80d0-8716e19defa5 | Pole | 2 | Distribution | 2020-07-07 | 2025-07-06 | Level 3
97cf3a0a-27aa-4ce5-8970-9818295f806f | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
885ee9b8-7720-4690-803b-fedda2eb4135 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
62e557c2-ef6e-41d1-bbec-eb0e9f0b96a2 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
728285a9-0039-4f09-bd8f-b5e3baf66d8b | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
21e0c81b-36e8-40d2-b1d0-d8e616cb36d9 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
562335b2-7a72-4bf2-b31b-490945698c89 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3 |  | 0:00 | 0:00
05d73453-5a32-4012-a77c-de379b54be8b | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
b8d9cb64-ffee-48fc-8bd7-394178ff9187 | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
ad0de100-52a0-45b0-b4c6-ce8968ad0963 | Pole | 3 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
ed21d40c-e8e1-477a-b8cd-17538399044e | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
79c8bb23-b503-455c-80f0-98d18656e233 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
bd165113-6276-483e-957b-211cda272fec | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
bc0f4971-62e5-453d-8419-1feea26b57a0 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
a3b24d15-6bad-461d-809b-8b4e55389976 | Pole | 2 | Distribution | 2020-07-06 | 2025-07-05 | Level 3
ad16868b-a539-40a0-bcb9-c25cfaf67c8f | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
b08acdce-6f5f-4e3d-be94-8f2d8f58a957 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
bc724c11-dfb5-48cd-90d4-c5cfa93d6928 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
77b39cd6-fc8a-4702-bd83-e4daa89d1493 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
9c0abb0b-a348-4999-9343-0b6686df6525 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
db584575-0efa-46d9-9fa4-9fd064a1999c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
dd386778-2810-43ef-960c-3afcd4f7e669 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | 0:00 | 0:00 |  | Blown fuse on cat bank
e0d700c0-2d91-47bf-89cc-fddd6f43f41e | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
dd0eee9d-91e3-4089-a583-8bcdca49f43f | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
fff4b774-407a-49dc-985f-1654642809e6 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
9bd3f677-d4d9-4d76-94b1-7d2a1574364a | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
6059279f-5a46-4e2d-904e-1e86690766ba | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
663ec697-531d-4437-86ed-8608796a2b73 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
60f56ba1-b348-4043-ada4-3678fb08c8d0 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
6337d787-14a8-4e05-9eb8-0988212e4c8d | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
71cb4785-14a8-49ab-af12-e89cd1d9676e | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
4ff1158b-4d31-4e2b-b2ad-77a685b556c1 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
56a1c32c-4e86-4583-abeb-af61764d2424 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
1b88f05f-27e8-4cc2-b6fb-c46d46c4d736 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
92764730-a935-47cf-8c26-20852a5a66cb | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3 |  | 0:00 | 0:00 |  | Replace put at top of list
23ca360d-b7c9-4408-b14e-abbd08fd7549 | Pole | 0 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
28f0a912-fa6c-4218-8c24-77bcdb8f5265 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
e94082b3-e375-46da-9330-b270df7ad367 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
c162ec37-2c3d-4639-a0c3-5353b1b667ad | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
bb5a472b-ab23-401e-8866-6039d3babc30 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
a00d5fea-e2a4-42d6-b24a-bd0321b04678 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
04eaeadf-3804-4277-9e99-99e0e161763c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
4cf14ed9-5d22-4c5d-a9ec-4e0a75642859 | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
78b06658-fec5-4708-b8e9-7834dfda691c | Pole | 2 | Distribution | 2020-07-04 | 2025-07-03 | Level 3
7047572e-f938-4c47-85ee-7322ab3e06a9 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
24008e5f-3f22-499b-839f-240dc1400bb1 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
476233b1-e400-4667-a56a-b7280ac65ff8 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
156216d1-767d-4048-b862-a87db522f3ab | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
0e83fa6f-3f1b-4a2f-99a5-3e56c06de4d6 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
0cdcfefa-585e-4411-8005-f3ba4439e79b | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
9314ebea-407c-452d-97ed-5a114b37a1cb | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
bc20f272-e776-4b4c-bfb2-93717e684dc5 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
ed52b673-d866-41f9-89bb-847012e7230c | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
e4766b0d-b291-440e-8fdf-2addc537b6f4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
5ac9bf74-6775-4596-b6d1-ece0b5ce2f87 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
50043214-c47a-4379-96dd-ad23350081ce | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
52ebe1db-c269-4f7a-8371-f92894b3dd9f | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
7023fec6-cd05-40e2-9c67-1cd2548a17e9 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
0a720879-1a68-4922-8d53-4eb8cdb25b0a | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
ccf0ec6c-9f33-4d08-a33d-e4ee9ae9e966 | Pole | 3 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
4f67f863-89b3-4091-9c94-a6cf88fef633 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
f8d52daa-332b-4eeb-8507-862ab852c93d | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
f4cb338e-d902-4a52-bd88-9a84c6f21ff4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
d750fa3b-40ca-464b-8b9d-8768d5fc19d7 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3 |  | 0:00 | 0:00 |  | Al blown replace
c7f95d63-a6ff-40ca-8a07-c9ccdeeb32ed | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
ef91043d-64ed-4241-90f7-eb7a661ad63f | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
7c68b51a-688a-4057-b5b4-ffdcbfe6deb8 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
87c437d6-7418-4019-8f61-abd750ff5749 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
b444c3a0-9813-40c5-9758-a964b10e1a79 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
a6d53c28-5e67-4a6d-9ccb-dfa957ae13d4 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
aaf4fa1b-7adb-4a32-9234-1e7ff0d4c097 | Pole | 2 | Distribution | 2020-07-03 | 2025-07-02 | Level 3
d9d8b4be-d8eb-456c-802c-f3f3fdce077c | Pole | 2 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
06cea37c-a8ea-4c08-8951-532495f3a242 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
e5719e0d-066c-4f55-a501-295b111763c5 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
b73c318c-c739-45dc-95a4-efc087d84edb | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
3df0d63c-ef17-4ac3-9e30-2aa2a228b9b1 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
21ed4afa-bad8-4973-9bff-ed07b02e4c17 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
809e6db5-a91e-4d4b-ab4b-076127e93aad | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
2c0ac079-7793-43a0-a9bd-77394058e1d8 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
491889b6-8361-46c7-a2dc-b64ada3a139c | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
6ddd0ecc-ba20-43c9-8d2d-b6c6e5b05203 | Pole | 3 | Distribution | 2020-07-02 | 2025-07-01 | Level 3
4ba583d3-8d0b-43d6-80e1-8345f3e1192c | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
29e0707c-f938-46ce-8de7-b2d115555323 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
359c62bb-0d12-43b0-817c-067e390a1563 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
681edcbb-e8c2-4781-97b8-a2fb9828edbd | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
dc8303f0-d0a3-429a-9640-eafcec41f31b | Pole | 3 | Distribution | 2020-07-01 | 2020-12-28 | Level 2 |  | 0:00 | 0:00 |  | Went to change out high signs and when pole was being climbed the top of the pole wobbles, top of pole is rotten and full of wood pecker holes. Unsafe to climb pole needs to be changed out.
83b4395d-0dbb-4ee9-9587-fb6a0b0c70f1 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
e5406709-d765-4f8d-a5aa-478fb8a5ab2e | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
7ec94654-ca3f-410e-9ac5-13236eaa97d3 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
bab110b8-bd28-4fe1-baa5-0777ef860235 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
b1fe51d8-68e2-4ac2-863e-f9a5efb7affc | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
af23feef-c4b6-4a8f-ad12-492cf6b94286 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
a9621bf2-8437-4ea5-910f-6db8fd57ef01 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
2a71a7c7-6c6e-4648-aedb-cdf565a1464a | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
47064fc4-cf1e-4e77-8e4d-66d79537a47d | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
ba110dea-13aa-459d-bb0e-2fd554c8eeb4 | Pole | 2 | Distribution | 2020-07-01 | 2021-07-01 | Level 2 |  | 0:00 | 0:00 |  | repaired cracked line arm, pole needs replaced.
4e92bd42-3149-4c89-8703-ceab0a955c16 | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
1380528d-05e1-44be-8659-b6c2ac92ebad | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
b3e8d100-9c01-4fca-9e47-25f0395d137b | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
2da97822-8553-414d-b81a-e68123316f96 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
41d5985d-c9d5-4adf-84ce-432a63725292 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
41269246-0aba-4fd3-8c17-8f3e1ccace21 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
d1d8edb0-1c90-4077-9a6d-4f43b53508e1 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
95df34f4-d327-40a4-87e5-72d2c9787603 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
8c17a871-df9c-4003-a610-f7d914dacca0 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
7ea1828b-8371-4ca1-9615-7b1a6ba4325e | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
ab3fa375-8bfc-49c2-87a1-3197fb2f69f7 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
96952dc0-5280-4fb2-b099-f802f86ad70a | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
9e8f5b3f-ed38-4423-8365-150d27ce4372 | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
6e8aa700-b83b-4699-93b9-ba4444c935ec | Pole | 3 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
78247f7a-0352-44d0-8c6a-1c6698d9514c | Pole | 2 | Distribution | 2020-07-01 | 2025-06-30 | Level 3
a3f0da5f-84a0-4fc2-a292-4250e81f7aab | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
26456949-a6fb-4af8-a1ce-169b430c9b9d | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
47963164-c2d7-4ad3-93c2-8b2ea740310e | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
4706b5f9-4362-4f9e-a161-72fda9ad1a0d | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cb573dd7-8f3e-4b6e-bedd-30c65e707dd9 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
8c09ced1-900b-40fb-9b43-5153732e8573 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
197fb920-d9b8-4af6-8d44-359d8f30a0f2 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
1ed6e8bc-7d30-46f3-934e-e8870c76e87b | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
fba4dd40-87ff-4f89-a805-697d00e74e47 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
a7d342db-42cf-4886-ad47-460c07bd2e22 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
d4ccab76-7a51-49e2-bda4-48d9181e111e | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
17999798-87f1-4f99-b1ed-db74f51fb5b0 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
52d25e4d-c469-4fec-8fe1-80762dc82227 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
713a99d7-169c-4c4c-ae37-fa558a197479 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cf7186fb-1763-44a6-9ee6-988cc6ae9297 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
f9d98c21-da5a-481d-9141-b5b3e241c58f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
c481f239-aaff-40f7-8c5c-6095135ede3e | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
8fc5ec2a-52e9-4619-af19-55dd0653257d | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cf2407c0-3a11-479d-9dd8-e9c11ecf9df7 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
b514cd60-bb09-45c3-8ff1-588f8b6d8191 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
d566079e-d3f5-4e65-b35a-e17117275520 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
9935d440-1b9e-4127-8ddc-832fcf6930a3 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
b569d043-9aa1-47ae-a254-853040276277 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
bea4a1a8-d14b-4ac1-9c7c-6610cd1db4a5 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
415f4615-39a8-4bec-b443-0e8ac73c1bfb | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
c2a14c40-f9af-4f1f-a412-0f929e414227 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
c2e1e764-0581-4996-8e98-cf83d256f982 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
672dc76e-dc2d-4424-89fb-d5a6de907be7 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
63f09cb1-6076-48af-9870-5bd5ea1b07ff | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
b10a44e0-31e3-4afb-a6e7-be0e9156b789 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
1b117939-4685-40c1-b61a-cd9204e4d92a | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
9dd71ebf-c328-45f5-b058-277917ca4169 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
e6c5804a-585e-4dbc-94d8-71c18cbaea2f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
cdbe3ec8-7811-4481-aa48-bf62569eb7a8 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
6adfa1cb-43a6-45dc-9c0e-9721bd8447d1 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
2a8bfdc5-d62d-4526-b19c-c02b5f546988 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
c36cb937-9237-4e3a-ad29-fe2dfe0cf2c8 | Pole | 3 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
1a8aec85-62d6-49c5-a333-dfd5cad287d3 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
f73768b7-aef2-4297-a9b1-ac19bc9dcefc | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0d50f5e0-6b86-42ff-a529-0b77f181e8ac | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0f0c18fa-ed86-4758-89c0-d19a7d095d38 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0398fe52-2ba3-40f5-baaf-591472bce0de | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0399be6e-35f2-410b-9925-5c644135282f | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
5c4fc335-c8bd-47df-9d9a-25372f9f5c98 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3 |  | 0:00 | 0:00 |  | High sign in wrong location, missing vis strips, missing molding
1128dbda-f585-46b5-8643-76ac2cf0d407 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
3886ddc4-978e-4636-a374-20e7f080066b | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
3140b80e-652b-4b93-b08a-302508803a00 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
24363318-3afe-4cd7-a5b0-a1b36ae7ffcb | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
74bac55c-1eb6-47d5-83c4-0b00cda2400c | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
57e36233-b8f8-4085-984e-111b358905d7 | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
5311c8c5-d4d3-4f79-ab1f-481dcf41bd9c | Pole | 2 | Distribution | 2020-06-30 | 2025-06-29 | Level 3
0508e5c9-9634-4fb2-bd93-42beef939288 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
2878ce35-c745-4643-aca3-e5e1e41e46de | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
2e6afe47-8b4d-4b91-b05d-ea09faae6ebe | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
44962482-c053-4446-9e43-8ff3c0b98109 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
442ce52a-3ccf-4667-8b12-ab57d047ee6f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
61c10519-e229-4b28-91ca-2a5beac6bfc4 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
504c40b7-cd0d-4f19-b30d-2e869850c6c7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
17204ebb-ada2-4803-b50a-cb89600c83b1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
1425b2a4-e013-49a2-9817-2556d9be8c71 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
f136a2cb-4126-4ff4-97e9-be365ddb5961 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
f569e62f-b536-4656-93c3-4a049b03836a | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
e8f7ddfa-2f6f-4dd8-9724-073800ecbd1f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
6ce013c0-8231-4929-b0ca-ad121c5b5cb2 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
b464cdf1-9d79-4cd5-b151-6d6debdba853 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a691948e-9a3e-4464-abc1-edf2a248e796 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a75c6235-372d-4ef5-acd8-9402b38bc7d8 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
2107f36e-a842-424b-b58b-a6556228af91 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
94f93e8f-bfc5-4d7f-8645-6d4d3784b6f7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a6d73656-12e9-4681-abe8-0ad1733ddda0 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a46fa2d5-4ad8-4f18-964a-f6c47856ce0a | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
80169dad-3e79-49fa-8733-3ba1a0554c11 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
8bbf06fc-02e3-463e-8ee8-a298bd105e3a | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a92e6097-1c91-4ce6-b54d-1f3f65a8e68b | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
3a67bf18-b460-4590-8631-4f4296711e77 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
e366110a-a17d-4d19-b020-4ac22956f496 | Pole | 0 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
c7f42114-e5f2-4636-9471-f99a17b12e6d | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
408f776d-c353-41d9-a29d-d729cfaa03d1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
e1fdfed8-d81a-4ac2-850c-4c8748bb721c | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
dddaf571-a30b-48dd-9bfc-345a72ac7d1f | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
ecd71f45-465a-4c15-b45c-ab328900bdd2 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
4816836e-d108-4928-95ff-bd9d22bd442b | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
fac8e6d2-6fd7-4a4d-8eb7-cecbaea24ab7 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
a411ab9b-0f0d-4435-b35a-a75bffb7548e | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
1e1e89d4-14b7-4fc7-8322-8afd029686a1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
21a861eb-0df7-466a-ae53-7c35c80d8164 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
ae900de9-ff22-4fd3-9141-a073c1bceaf0 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
dec80bf3-ee49-4446-a0e4-a62785713791 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
6b714a30-3bd4-4a5b-beb7-4aa4e85b633c | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
667dd612-ac84-42d9-b97f-8c04b6c2e2b1 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
6ee4fa0d-2562-4aae-9f07-00203a52bb61 | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
621f1f70-d18a-4baf-a929-88724179afcc | Pole | 2 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
05a5439e-d149-4511-b22d-6b3ceb7a1086 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
14e377a1-e093-4ce3-ab63-bcf42dd61975 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
f7d6a012-fd71-4055-b6ab-7f5de486e797 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
b0cdb9cb-4328-4681-80f3-6fd185bb8a64 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
42b739f2-26ee-484c-ba18-02685a5eb480 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
715c593d-701e-4002-8281-cbd554deba35 | Pole | 3 | Distribution | 2020-06-29 | 2025-06-28 | Level 3
edfcb782-ead5-43fa-968d-e0c59fdcdfd9 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
e35752c3-be1f-40d4-ab58-98b3e3af8ba5 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
187a3b78-cd7f-46b2-af5a-3b67deb63aba | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
884975fc-2cb4-486f-8832-f749224689fe | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
68415d3f-52bc-4364-9332-12143462bcd2 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
02ef93b2-f9e4-4147-88b8-94e6bca6ce8d | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
9a1d3ded-fe52-4a59-a37d-6f97683426bf | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
c3faa75c-5ee7-4d1d-900d-926287bef9c0 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
f28f6101-8cd5-4d7d-b260-cd6aa9b2bfe5 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
b0acd8a7-018b-4433-981a-0bdcfba8283c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
603d293b-69d3-42a2-bd67-cc8b06f420c9 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
556905b2-b911-4435-bcc2-364dc56bf95f | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
8d0fbcf8-a48d-437a-b2ae-1620829e3d9b | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
3969bf77-0256-4c83-b6a1-e5b79a9885ae | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
3b821410-34b9-408e-ac3c-e0fe85a9607a | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
f3cba543-55e0-40d2-b7dc-ae28bf2faa3c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
b69a0afe-0601-468f-929f-e6dc571b3be7 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
9bff3554-1abf-414c-9afc-0783bab946f0 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
e242ea4e-dd01-494d-9d35-b9cd1c397f61 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
ce9c74b8-5406-4376-b450-30224704c272 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
a0b71633-ddd2-46c1-a6e8-e9a4b830df0c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
94d58262-0436-4c54-9bad-7125a07b2dc6 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
85ef6292-47ab-47cc-b945-fc2cdb60db9e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
8806c422-b2ce-46dd-94ac-80ab4e19fd4e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
e7c7ceef-6e7f-4598-a673-b144b1c37c20 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
2b6fa4f7-0190-4d83-a802-6722a2886a76 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
37a47cf5-337d-4417-83c7-9b9e7b2d5d0a | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
43802c10-c840-42c0-8b9b-9cf9137bb581 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
3d588a01-bbcb-494a-a689-113ef6616ad2 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
72bc0fba-0e18-4f06-9b8f-91ba2213beab | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
642a93f6-411a-4897-8772-5eda69304c2e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
5c5638f9-db42-40c4-9f7d-edf5ea0bf692 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
5333a12c-2e6e-4519-8b85-1a1564e03492 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
54efb175-1c61-4a82-a4b4-5b5558d8709e | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
e442d116-3c58-4eee-a889-3832325663cd | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
107e3cb4-987e-4158-a158-c35f49ea3595 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
1284b4d1-d833-429e-b933-a357e900a647 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
06d73a8e-c88d-430b-952e-c4e7c2adce99 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
f751f785-c464-4c2f-8814-5594c759f51c | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
0eea7117-0804-4eb3-8dcb-7b4b51b1bd60 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
09986968-41e9-4962-b795-6364930f9a48 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
147fb4d5-07ca-48c7-a541-91de53d4cd38 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
3ca0b151-623f-4e70-8f50-4250096f3517 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
4148eb72-d1f1-448e-a4ee-f37ed6088bbc | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
433a0535-2570-4e23-80d4-12c2fc438f06 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
36de26e1-3f94-41d5-9cda-19889db7dc32 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
72696d1f-1fda-4026-9d7b-0d38893f9287 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
78b36adc-1733-4dfa-87a7-4a106a55ca90 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
6eabcfea-503c-49ff-b0fb-37889e91c08d | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
712d8bff-7077-48ef-8ed5-a30cc9ce6fd3 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
69d727d2-eedc-4298-9e8f-d3d62cd4e230 | Pole | 2 | Distribution | 2020-06-27 | 2025-06-26 | Level 3
6f49de98-44b8-42bd-9d32-cb230f76f77f | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
3616faf2-70ac-49be-9038-f43a55d4a132 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
44f132df-06a2-4366-997f-abe300570334 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
45b9385a-ff0d-46c3-a387-e629de452425 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
4761d2bd-df55-40bc-8b3f-685d08c65b50 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
4a1ba934-7f4d-45fa-ae17-00b0aab98e7d | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
153a8b97-1037-42e1-a826-3e07d0398f0a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
037f1e9c-2fa5-4b2f-89d7-94b71533a86e | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
676309f5-4399-462d-bbe5-56f3eba2a109 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
fc4b0c68-1e8f-4ab5-9f5f-7f0481f8e37f | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
fec1f6e4-ecf1-4d58-9992-7e4ec1c7ae43 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
ec8a747f-f7d6-4143-a01e-2d4a6d7712d8 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
10929716-ffdb-4809-8965-18dca0f94032 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
410c85d8-c60b-4a47-8a2f-f518a34aa65a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
c431e01f-357d-4c27-9fb7-8c411e9087f7 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
7d6d4e47-cfcd-4bf2-8b92-3dfde0dd8885 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
85951483-a278-464f-9fa7-0b3ba767d66c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
3f81c4c5-4e27-44c0-b0f3-8133c8a04c53 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
aac4a932-fc7f-4c4e-9b8c-08537c9388be | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
afb77e87-6c87-467c-845c-6729d5c06cdb | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
ad7985d4-cd46-4f6e-84ab-61f86cc488a9 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
b957b650-276d-451b-8bdd-699c7dfba05c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
e4951624-5c90-4133-a059-7ccd435c250a | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
be2c8d00-3ede-4f6c-9f34-fcc520ce8885 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
f43b4113-1e8b-4972-b255-6e7de666817c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
14635e22-68db-492e-9390-bbb0b42f63eb | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
9ef8814d-191b-438b-bfcf-85d36dce3c7c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
74b35813-f04c-42a6-a9e4-786970a9f75c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
7ab4984f-0e02-429a-a669-a28fbacb10a1 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
5d8e0cb4-a54a-4b14-9d5a-06f07a5076d0 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
bb7900e9-22fd-4f03-9f50-549f3dac6d84 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
010dea4b-5723-4c4e-b547-0f071701cd6c | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
28228cbc-9c8c-4a42-acaa-8b5e532176bd | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
fe200f70-1456-453e-a343-aab9690db571 | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
f71a341e-40c2-40dc-adcf-f7dda7623a1e | Pole | 2 | Distribution | 2020-06-26 | 2025-06-25 | Level 3
17cc363b-bb3a-48fe-a6f7-ab19fc71200e | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3
121083f7-cab6-402e-a038-b8b0d40729ed | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3
aa4a4f89-550c-434b-a987-2d285f6f57a5 | Pole | 2 | Distribution | 2020-06-25 | 2025-06-24 | Level 3
9e07b871-8577-4097-9c72-79efca0bd079 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
b04c6fff-951c-4d53-ae63-a00d2ba076c9 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
c192c0d3-89c1-4ada-8475-774403aec93f | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
a3c0c5f7-c4e0-4669-90b5-4b324db82ee0 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
e057a47f-8dab-445c-b650-91f8f5296eaf | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
d3efbae6-5a18-46b2-a87b-c0cc3b2dd8b4 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
51c12225-f0a7-4bde-bdcf-9be7fb3184b5 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
1fffa40f-168c-4c5a-96f3-7ace5c433a87 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
6117b049-b1b7-4db0-97de-9b4d446a95d0 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
adc3f614-a6b0-4668-a12c-dc6f6c16d47c | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
bab2724b-f600-43ce-b63e-3c69af96fc57 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
bac569a7-20e2-45a5-832f-7e6665904430 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
e13a886f-4473-4389-829f-b8786a4c08ef | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
7d031917-c268-45e9-99ce-9c1c631ae30e | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
90edf98c-3ea8-4aec-952d-32387489bb11 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
a76bcf26-87cb-4275-955b-582f6152e6ae | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
2b43afe4-ffc3-4b43-9ccf-dba75c65bcdb | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
2ed05423-321b-4ad3-a8b2-caa4c423738b | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
5cf7502e-b68f-4b18-be04-b0f14b66f219 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
61f3292b-6d38-4605-8fdb-f272c6b85b37 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
4da846b7-2d95-4710-8a88-0e60645e55b8 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
02fee0a8-e4c7-4832-8bf3-8bc953161c59 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
bbbbacdd-82ac-4f75-a7e8-a7f6b3973088 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
d5253ffb-2d0f-4d58-8ade-62e43808e029 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
5fa3078a-7dc4-40d3-9faf-a585269cf9da | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
271dbae6-d155-4640-a474-23b6db1d9ab7 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
2cba7531-2b01-4ad6-a51b-c13d65176e13 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
104366a6-69a6-4bc2-b570-c221d630521f | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
1f727005-d03d-4c80-b788-8b9f61afd3c2 | Pole | 2 | Distribution | 2020-06-24 | 2025-06-23 | Level 3
b0aceb20-1ff8-4fe3-bb30-314f7b6d3db9 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
02e58939-3c4d-4c0c-8aa6-205e085404ab | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
06afd339-c8d3-43f6-8464-7542998c4fc6 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
77125cdd-8bad-464d-a039-daff3efda020 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
bf323f11-80d1-48ec-bb42-5e28d0779737 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
dd64b478-1578-4906-9424-a6f78b7ecd71 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
d8a89991-219d-49a6-9a63-6febcf5a043d | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
4b532bdf-88a2-4bb9-818c-d9127e2df87f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
49b74be3-0168-4d1e-952c-4450c7981ef9 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
4c864429-e355-4b71-afdd-21c5ebec5d02 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
371f0990-793a-4128-bb68-65be4fe67121 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
26339124-825e-40ec-915a-fffa7052bdac | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
71af0cbc-2934-4f81-97af-86d4407feb7e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
716caf31-a3a5-4db2-bcef-9d175a8c12e4 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
52987523-dfe3-4bb6-aedc-c09e5df517e2 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
56455d3f-cae2-4fdd-914e-46f91b0be54f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
a4ff24a2-2757-43c8-ab0d-f9472decfbd1 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
79396c85-28dc-41b7-97c0-10fd468e20ae | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
1ac8b35a-f9cf-42f0-b562-9980c4ba079d | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | 0:00 | 0:00 |  | Multiple woodpecker holes
7b858153-914b-421c-98bf-79e93c373e0a | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
9155ce3e-0816-434b-ac6d-bf79d1a9c117 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
999a6497-c49c-46f1-bbf2-d6ec19793e4c | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
917abdc6-e03f-44b2-a578-8c6b474ddd46 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
8c3df28b-caed-4749-a636-9b10cd12e431 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
002fe135-38ea-4cf3-a441-6a06ae4fa972 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
e3088ea0-f521-4bef-87fb-39cdc23e2bc5 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
e4429fe8-ede8-472f-b03e-00757d01375e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
ab1ef444-5aae-475a-b7cb-e0eb421901f6 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
d0228653-c7f8-4087-b513-ff1b4c937371 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
b1c14276-328a-486e-a4e7-6a67621b65a9 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
7cba5a89-d7bf-4934-8bea-36aac7c87da1 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
a929ad9d-d48e-44dc-a3b2-bf54d8d7b99f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
49191429-dff4-4d4f-a0d5-763c6a9305a3 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
44b178ae-c3ba-4f53-b211-e946903f463a | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3 |  | 0:00 | 0:00 |  | Pole top ok, arm needs attention
f7147810-e152-4c85-b25d-d97e83ffd02e | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
8090ad40-5ccd-4208-9f0b-120434b674db | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
2bc59a40-d6a5-45fe-aad7-ccce00411051 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
507edeba-5cb4-49ae-876f-e4b19d86d29f | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
2e2ecc4b-9379-4450-879f-feea210b48e6 | Pole | 3 | Distribution | 2020-06-23 | 2020-12-20 | Level 2 |  | 0:00 | 0:00 |  | Pole is hollow at base. Sec lift pole
c2866058-dd9a-42d4-8f90-cfc688e0cd46 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
c4a45a4c-57ae-4334-a2c7-311ae6cfcf82 | Pole | 2 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
7b899d9f-eec2-4024-9b71-2ece1dcb79b3 | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
87d3f39c-c1f2-4dce-834e-341f0bec52da | Pole | 3 | Distribution | 2020-06-23 | 2025-06-22 | Level 3
874e2e05-029c-447c-b6fe-9f4b8c57c95f | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
8c5882e1-dac8-4d1d-b0c5-192a405036bd | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
98ffcd3a-418b-4b1a-b964-c67028f62714 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
c3f2cbd6-ac4b-4ef0-aded-0cb7172a17e8 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
c1db789b-2672-45e7-8b51-6223e1e69bee | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
6ecd1eca-1fce-45b2-abda-82b5e17cea38 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
bfe55a0f-3a28-441a-bdc5-d2e672bd5494 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
aaf091ac-d100-4aa7-9d32-ce8d06ff1d19 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
ab11dd14-a0e5-4887-86ac-2c345dadd443 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
04bebec8-8a5a-499e-839d-5f3635adebc3 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
19ae9250-ec80-4d6a-bc85-28213d7eca13 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
a7cec7a9-9054-4fb7-8450-8b2d6283c877 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
b0a7f69a-37e8-4f80-94bb-32d35df8528d | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
d3b88be7-2c4d-4dcd-8965-8961cb73e174 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
e80a4238-bee0-42f3-b4e2-a34b34278291 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
e7b77432-b78e-476f-9b9c-3c0c11045415 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
edf83bfa-6151-4eac-b63e-33abc518b217 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
d2682e02-7aba-4199-998e-69243c831842 | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
54d42a26-1e38-4522-b8d8-fee85db89470 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
70339f64-6fd3-423f-91c0-197b9122e000 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
4cab09c3-8c60-4b58-b7ca-15f48cd94d07 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
4b8791d8-ceb1-4a03-903e-a072c1a957fb | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
3e82aae9-a5ca-4755-bda8-016105f231ba | Pole | 2 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
5570b5d7-33d6-4d2f-b389-06ed8022b1c3 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
61b6aff5-e6f3-4937-9cba-acb41beffd60 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
698d282f-292d-4df2-bf40-834e8800b482 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
29956b7f-ec0f-43f6-8fe9-f97990686847 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
d291f631-a08c-459c-8d52-c03a33b9a713 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
c2e783e7-5a64-4ff9-9540-94a8c883fe33 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
b88edc8f-0dc6-4266-9baa-254862dcfb32 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
7e608a48-b485-4d0f-be98-265f06fec672 | Pole | 0 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
10a25420-c12b-4fab-8fe0-7785fc4f162e | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
e8218af6-7717-4d4a-a6b2-b1ba075e47b4 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
f1834de7-8c0f-4f89-925b-8aa0436bc679 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
0b7c5dae-9b47-4f96-a4d2-7b64a75f7eb7 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
b49ba89a-e2f3-43d4-a762-1b64c9673c63 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
10994a1c-e862-499d-99aa-5c0d1d1a5721 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
1483d12b-e665-4576-aa1b-b010a6f21d74 | Pole | 3 | Distribution | 2020-06-22 | 2025-06-21 | Level 3
12abae04-4c2a-4f18-84ed-89e038e285e9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
039d7ab9-5c89-4a2b-9302-08d477fabea0 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
05856d6f-64e6-4102-9c88-f6809c0e9015 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ee4aa1a6-ecbc-4a80-9018-bc7d3c2faf98 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
1a28444f-0187-4d71-b066-4d637bf88df9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
17ff1c88-8438-4a22-a3bb-f81a46a9b9e9 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
21dd1f4e-acec-4c91-bb6c-541016106b53 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
5591e8ed-22be-45d7-96ec-1d89c99e28f2 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
caad1ad2-21a1-4f6f-a931-7007a1c44fd2 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ca6b90d4-2d4c-4056-ba6b-17f5b42947a4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
485fccae-0846-4c6b-bcbd-841bee744d31 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
089d1e32-36b3-4a4b-94ad-04ca87094bfa | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
44a3ef4b-98db-44d4-8a4a-eb043aa2ce8f | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
0c1b9592-e898-4a7a-aa77-b2582f94fa04 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
79b23a67-d2e3-4ca3-9516-d9a10f2b7a40 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
6a3cc61f-514f-4585-809a-ef0783b4978d | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
671568b6-3d67-4abd-b075-b73a46ae9be1 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
5a3b9384-33f6-4c84-bc81-9de47f7f43f8 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
d0673a44-eec4-4dbb-a44e-98fd9f20a746 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
deea4bc9-9ef1-45e2-8793-8c515cfc3031 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
de4b462d-ce0a-4f59-8d16-a1cab842d645 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
e5ed5acf-f90e-4443-b65b-49640baf5228 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
bcf04c9f-c76e-4d6f-90b2-5c88e4449b1a | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
e030bb8a-cd30-475f-8e01-f23227c4d985 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
98724d3d-0e04-4127-a63d-89ced6dff3ad | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ef92b9c6-19de-4e27-83ee-12d8e99d778d | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
ad226c8a-0447-4453-ac74-ecc11dc58ac4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
2476a927-6cc2-419c-a714-ac75e5e74f41 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
34bd9831-dd25-45ae-9a5a-8505b1a230bd | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
f1bae1e0-c81d-47c7-9a49-b853bbaa8ea7 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
a925c989-d261-4fdb-b7a5-7d5faa313422 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
aed855f3-a0f4-441a-bd87-f53090f00454 | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
b88f5c63-1dd2-42be-8e24-594eb0d77642 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
45060af8-637b-4b2d-b4f0-f8054ae16143 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
912e00e4-d44f-4eba-a324-3c6cf9f58ab4 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
9b003c92-caee-4c4d-b18a-16533f830aa5 | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
8f887f03-f5a7-40b3-9eb8-89626a5bee4a | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
7dc399fc-6b05-4983-9192-bb113b582d0d | Pole | 0 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
8361087a-9c3e-4fa0-aeff-af3355203f1b | Pole | 3 | Distribution | 2020-06-20 | 2025-06-19 | Level 3
8dd92974-28ab-4178-b432-222e3bf66269 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
a4738ee0-32a1-46b0-92e3-8d9bfe6cf5ad | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
a416bccc-e385-43bd-901f-6ef2f22a7f6f | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
945e5153-e460-4407-a38e-134b5a338b22 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9b54d2b3-f79e-4b3e-93bf-4e02f4c577de | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
c11f75fd-d5cc-4832-a573-24d7abe136c0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
c8445fe5-6159-4042-82e0-d30b275daf4c | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
b3978a2d-c517-41ee-b407-11a585bf96eb | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
1f5076f0-909c-41b7-a5fc-b526edcd0171 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
f42dd436-4f49-43e4-846d-f473d1497df0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
14b1b9bb-6399-4855-b711-9434da84ef08 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
11155b4e-d8a1-41de-80d1-721a10a46e01 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
0c384509-d31d-4f33-bc00-eee02296eb58 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9eb03c0d-d84d-4c47-ba5b-4dd9e449f92e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9a3c901c-ec77-4714-9858-197191b3277e | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
f6a88c60-ba9a-468d-b550-240f277ba0f5 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
11307c9a-348a-4634-a842-17b2bc617e8e | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
eb15c717-e93e-47a6-9367-9daa1ace59e0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
cd6e785c-855d-4582-b955-f6b5517e27fa | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
bacbba9d-24cc-47d8-be54-5e0f4ac4db19 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
adb95c06-6aa5-467b-9fd4-e4ccad54ab5f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
ec7ab5d0-11c9-40f0-bfa0-ad5e59c02b6a | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
e5b1e486-53bb-4adf-918f-e0864c6da55b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
db3a2ec9-db5d-4664-990e-acee3e624953 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9dcda6d2-9adf-4968-bf8f-98defc9706d6 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d2b0813d-d7c9-41ee-9100-aaeab7ef8491 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d70e2f5c-58de-4fdc-9c81-09adebd5a8c6 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d5fac83e-6961-43be-b824-6c76f4005b4b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d691ca28-27b1-4ec1-bc1c-a711cd2c027b | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
efc2d95c-e966-46b4-8cad-b1a9a0327fd3 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
8938d985-fd76-4bdb-b2ce-7203c56ca3e7 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
0e5b9d25-4fb1-42fb-8e8c-1cede50f1535 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9763e357-b051-4e7d-93d5-fd7dafd2e2a0 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9b52c8f2-ad8f-4689-bb38-ff05775d6ca3 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
2f43e28c-aea0-4720-9649-7d20005f0a30 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3 |  | 0:00 | 0:00 |  | Anchor has been installed and new guy wire as well
5397419f-3760-4435-9aa1-7259d14586ba | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
62b1cda1-254c-4bc1-bf8d-ca12df9f39d2 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
5cc87c91-672f-46a4-8132-e2abbb4528de | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
03114452-4eee-4113-aa19-a7899349f90b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
2dc10e8c-43ce-4889-9c0b-9571509d83c1 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
265debab-6d68-4896-b119-01dc4f5fd30b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
0ac0c8e2-e5dd-4d65-a629-28048831e00e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
c39e7137-89e4-489f-8d12-a9473229ac32 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
e77bdbf4-a4f2-48ac-a141-9522595cccc2 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
a20cec94-5e73-4bb6-8753-d9fbe4874595 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
7b093877-434e-4afe-82a3-0634ff7c2009 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
173567e0-cb2f-48ba-b379-95c413e4bbc5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
eaf8744e-cc6a-4f13-8c3d-ea4a88b0e40b | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
b13797b8-66e9-4e91-b80d-3084fd7ff124 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
9d3b6db5-f354-40d4-9b6f-15e2178b313b | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
d0b98047-b4f2-4bd7-a235-ece05abb368d | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
daf5c354-220f-4576-8c48-8d406f16f5a6 | Pole | 0 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
67f6543b-74f4-481b-aa6a-437c2813189f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
6a0101cc-b040-4785-a94d-6dfead3e4d35 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
432b48f7-9e15-4c09-ac0e-d4f774afe696 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
4c853d16-73b0-4d07-99e1-fef395e67089 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
4e6090fa-a289-4b6b-a426-e57eb3a47ad8 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
2ca32e57-453d-4d14-aa06-2e98922bee0f | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
32087715-86ce-45bd-b5c2-aaa2532014c5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
1d53278b-4333-40b2-a690-baf75dcbc5d5 | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
3f0aede7-2193-439a-ab5e-275d34e83af7 | Pole | 2 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
239a01e1-ba2f-4513-9604-c58cca19516e | Pole | 3 | Distribution | 2020-06-19 | 2025-06-18 | Level 3
20bf6001-78af-4a0d-afc5-40110335257f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
2186f6d4-80f9-457d-a4ec-b0ecad324911 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3fbb4c23-222c-4754-83f9-c06024bc26e4 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
0e4fff38-eca0-4ea6-9047-e7949160e310 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
0b01c3f8-5563-4fa9-be0d-ef8cee63ab86 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3360d1c9-02e2-4969-8c84-88e8fb2a69c7 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
ceefe8f8-5fe1-48c9-8ba9-14f0a6acf560 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
96848c03-cd9f-4f8b-b9c7-da7510cf6f0d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
df600a4d-b67d-4b6e-a6b8-ad77c019379f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
00cd6034-90ae-4c92-ab96-ec4797187743 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
0ba37e80-2aaf-4a13-877f-5ef357f58c41 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
1f86e085-6bc6-4058-b916-bd7d81948fdc | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
1fedba06-3edc-4961-9265-f421931c2425 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
024f1dfa-f5cf-47b7-8c39-bacda515e7ad | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
02db2998-be85-4cd7-b008-30ed1fc15005 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
b7751c2c-6be5-43db-88c6-ec1edde17080 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
9af747f0-dcc9-42fc-b9ad-6bbd91be0427 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
dc7f9438-4285-4007-bb4b-c52e6a345abd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d1d7bcd7-6e85-4bcb-80e4-babf3c4eb51f | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
5e9e06b6-0807-4bf8-b61c-616fcf2b1ced | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
6da1e94a-4500-43a6-b1ea-99040f7fa44a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
35247a14-7218-4971-8115-f2fbaeae2580 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4639ab5e-ff57-4d4b-b238-41d347b528fd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3ec938b7-fb1e-4d77-bd02-c1c6d191c956 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
43c1b9f4-605d-43c2-af51-403c220536f7 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3923537c-b2dc-42a5-ab41-2b6683866076 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3d5f3b0e-76e3-49a3-9ea3-45a25874adb3 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
f3400bd4-188d-4c92-982b-132bd4f1e955 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
f86f93b7-c168-4c85-ae7e-8f251e43242a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
fdc52b0c-8fd5-403a-ae54-5986169802de | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
3b41cf8b-8918-4512-bc2f-e96e4d9975d1 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
471cafaf-ed83-4570-a7a7-a483791da6f5 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4a40846c-d6f3-4ba9-a0d4-4f6c1783bcee | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
295e741b-0444-42cc-b9d4-a278db89ba1e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
6ddf18bd-5522-4b4e-a0a5-fc21bcd2a77a | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
733c4f3d-8676-404b-9d13-00014b5fcc47 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
6187ee35-27d0-408c-b25f-685c6f4cff86 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
5ea0e2a3-f49f-4d72-a98d-ba8f1bb89e60 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
52257f2f-699b-42ac-85bc-a8c0cba0ab37 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
24f11f4a-c7ce-4fd8-90e2-61a5ce2cf505 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
496409a8-957d-48ed-b939-11e31b43278e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4d08eb59-41a9-4271-b73b-fa021f7cf60b | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
4a76a857-e0db-427b-b038-1bebfdd1c073 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
111e8b90-16cb-4a16-be1c-5a78cd98bb84 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
1a5cab52-5491-4ecc-ada6-38ac1ecf5a75 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
14eab584-ca74-449b-8b28-95e18ace810f | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
016bd0b4-ab54-4578-bebd-54201027436c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
6759a367-0d01-47af-9fe9-ccfedd1ec6fc | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
92db5668-0323-4947-8344-ef1cace2864d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
be89cbed-f794-4a3e-928f-9f1dc484a109 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
bffd744b-6f18-4239-bec0-0c1c39ab9b3c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d587e5bf-ee41-4e4f-8f09-5fa7de5fc5e4 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
c7100f98-1b10-456e-a32e-364fff9b2ae0 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d7ec684e-5593-49b5-87cc-962d05b13cdc | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
b58c4337-fe71-470a-bf88-a860c1441de3 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d1ddf84c-9ac3-4f8e-baec-29fb1c328e59 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
d92edfbd-2989-499d-8710-3ef92315e503 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
f63ec69d-6c6e-4b3b-8db0-5fb57453e9fd | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
b1046a26-9670-4553-84d7-0244821568b2 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
ae79c957-85d8-4126-93bb-48cfe524ac0e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
ac1e9bb3-2479-4d4f-a516-ace320ba0248 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
c66e7fc9-3e30-44dc-9748-f365d63aa59d | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
bc082cc7-9d27-44f0-a03f-af80323e9115 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
973242ce-6831-40b2-afb2-2ddfaea2e86c | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
a1995b28-ab54-4271-8c21-865137b1185e | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
a06f9b29-5bfc-4782-bfba-eeaf2b9cb502 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
a870008a-7a56-4e4b-9081-62c247b984f8 | Pole | 2 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
8a813efc-1f90-4ddb-81f4-a94aae52ce28 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
7f4c1647-2eb1-4ff3-bf35-658ac45ba797 | Pole | 0 | Distribution | 2020-06-18 | 2025-06-17 | Level 3
a7951fc7-f848-4f22-afc9-2a6ffc3a4ed9 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
bc73a106-27f2-453e-8017-c9de226194a0 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
c014fa42-d1d4-48b9-898e-0b1885ce8878 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | 0:00 | 0:00 |  | Arm ok, no tracking.
ba8e8ee3-723b-4739-b039-eb771634110a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
f64acb2e-c98f-4038-98ae-5752f7650b31 | Pole | 2 | Distribution | 2020-06-17 | 2021-06-17 | Level 2 |  | 0:00 | 0:00 |  | Secondary pole is broke off and needs replaced the tree is holing the pole up now. Not sure if itGÃ‡Ã–s our pole or customers pole.
dcd2ac25-9eaf-44a8-9117-cd8540ec101d | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
dce68f65-4f23-4363-93a6-d36f8c80fe9e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
ce653643-a75e-47e3-a4f3-44fa8b82ea95 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
ccafc5d3-4780-48a7-92f0-4e3b77312a66 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
bd5f70f0-e7b1-43c4-959e-1ca538087e52 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
882db907-2e16-4705-8b13-fef0cd1d9fdd | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
5543403c-cd01-4d57-bd23-d62d524d4e03 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
602c59c6-4284-466d-b49c-287b8b50a721 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
3f660050-96ea-4eff-a87c-21b42e2a2770 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
e009a6fd-a426-4242-b8b3-4aefdbf018c4 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
c1599ab9-7266-41da-8c23-e9beadb09126 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
bb98d7fa-2c72-4172-97b0-cb9abe553aae | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
b7516126-c0ef-4d18-97e2-f4347694221a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
72a5e09d-451f-43de-a3c9-142a2221e2ca | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
74385126-e8ff-4b62-9239-6fab093db6de | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3 |  | 0:00 | 0:00
7252cb95-08ad-4ba8-9f0c-93deaf06e8dd | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
75c6c19c-23e0-4a2f-9093-fbfd6b2c82aa | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
76ca1961-26bd-4a53-8ddb-679109929708 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
6f0f98f0-b3ad-4932-88db-869aad680f2c | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
67abe50f-763d-4505-90a1-5c21df6f0b00 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
2854f145-7758-4242-932b-40d9bf7c1f98 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
363aa800-8034-4a9a-9647-4da1b7e8321d | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
460366f8-75fb-4dfa-a44f-52869b92191e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
3a7a2532-caae-4be5-bef2-3e7c196b622e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
3b7a4f42-efa3-4191-85e2-047e738de316 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
ebe854e2-10ca-4c69-bde3-d31f5894addc | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
47620d6b-5844-42aa-a240-480623dd2a10 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
2d92a3ea-bd47-495a-943d-00aa49140d26 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
274cbf33-8770-4627-9dcf-95c261373c7a | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
69eb1326-21b2-4ed7-bd5a-3950afb0a371 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
dafffccc-49ae-4098-b8ea-97f3d339b228 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
cd740d2f-4fb6-4d72-b109-b5af9413fc0f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
a93d94ef-5c3e-4e55-9aef-0d5cfd6f060f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
80b89359-e257-4176-a191-fa0fde99f6d1 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
8f5a474e-b911-40b8-9956-1a73928a83f0 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
042cd7f9-01c1-4c97-b3a3-2de190df6602 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
58eeeba5-cc3a-4625-94e0-dac6000e66bb | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
61e28d29-fb4b-4bd5-a644-a4445d70d0d9 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
23ac153c-a11e-4cc0-a74d-5ae3f4dc6f2e | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
121b0a16-9f60-4cd0-81ec-de8f90975d6f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
13b2b12c-4694-494b-bf0f-4949db7aa4c8 | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
1849050b-a2be-4d37-9671-dbc35474c58f | Pole | 2 | Distribution | 2020-06-17 | 2025-06-16 | Level 3
23e03bcd-46a3-4169-9aa2-ebb46e3b7988 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
12588efb-58d3-4dd5-9415-3e45ef959629 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
ddb274d6-023c-45b8-a868-5e452090d704 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
a57bde98-bd3e-4ed3-9b2c-c132720e5b05 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
a4b24059-d2ca-4db9-b7d9-7792cbaa8415 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
c2d60c9c-3ccc-437d-a313-29344358e42f | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
dd961bcb-c36c-40c4-b2ad-c672534e5f52 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
71a92032-cc44-4019-b3ef-03a16dea9727 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
62958aed-5be4-4e80-941b-315f2de15eaf | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
4b3d8b42-ec61-493a-b497-8c246586e6a2 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
25fe7bf1-8a6a-4df0-ae24-fe9a006c4127 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
42de0a8e-f463-431c-84f9-74b432827e48 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
43e8f4a9-00cb-4995-8799-b07472ced851 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
4d38c9a2-e0ea-4e68-9983-3ec0d32dc3d7 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
2fac2070-83e2-49dd-8375-65f1ac739517 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
5385694c-b7ea-4e2a-9856-aba709463f69 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
b74d8cd0-e943-4604-9678-6af45864fcc8 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
be827ee8-6726-4ac3-958b-ea21d218938f | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
905504d0-9e30-43ce-910f-372bafa149cf | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
85725ea5-5553-4e30-b74c-27b04540523e | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
7a751178-337b-4718-93d3-cfbec13ef339 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
4d75f31c-dc00-4a8f-b2e3-77f5e1ebe810 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
c3e77797-3f5d-4bfb-bc9b-1d6ee05b3d7b | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
14e4d08b-32e9-464c-859c-206557919546 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
95958bba-fc1b-4c56-b82f-7dd30736e687 | Pole | 2 | Distribution | 2020-06-16 | 2025-06-15 | Level 3
8550362b-1f26-4be8-a3d1-8fd8e75a871d | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
1ec593a7-4f68-4903-982a-0c8ee6dd9ec9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
2ace12f2-9784-4ffa-8c4f-597075c9c8c4 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
fb5e081a-0154-47c7-aa31-2ee4aa6ab4e9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
98c62ce5-fdd6-462f-a119-8b62387e241e | Pole | 0 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
e6893d0f-e805-4d12-b81a-ff3230f48099 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
d28d08da-8a9a-4a83-a251-2fed91f2436b | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
6f1a0b58-bf7f-4f9a-85ab-998425147884 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
d7fe47f9-c662-486c-b60f-3a561ddb9737 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
aca4ece7-5ace-402e-8cf7-2154b11186d9 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
942e4bd1-9fd6-4fa4-a47c-4765099b899b | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
4c6750d6-1d06-4e02-b6aa-74a6a405019f | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
dbdc1909-681e-4867-b01b-fd2e312c7738 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
bee7bcdc-d2fd-4b28-8ef9-945f5765540d | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
11658340-a951-426c-bc97-aef0d57266b3 | Pole | 2 | Distribution | 2020-06-15 | 2025-06-14 | Level 3
293b9178-b9e4-44f5-b557-6d233a3de302 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
59e4e5f6-18f7-43d0-bcef-b155802e98d4 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
d1811666-9286-46a2-8061-20744598e308 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
d8bf584c-7a8c-4d25-9d4b-b3fcfb3efc43 | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
ed8b752a-a673-4962-9c22-df4d82be806a | Pole | 2 | Distribution | 2020-06-12 | 2025-06-11 | Level 3
f290599e-7bc1-45ef-bd7d-03007011e779 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
cfe2ccd5-422a-400c-80a6-92875bfed708 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
9760bf70-9b7d-497f-a4e2-edb0753d230c | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
8129d2e4-8709-4d35-902c-93ce87740e5f | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
927a0a7d-7c51-4d82-ab78-e8b632ffdb82 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
a5feccf3-cfe4-4bb1-87d9-a168e6ed80cb | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
ecf79453-46aa-4172-affe-23f89b20b9ae | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
60f5e1d4-bfca-41b6-81ef-6112ec31ac01 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
6e3e8a50-794f-4210-a1a0-24c7b4feee32 | Pole | 2 | Distribution | 2020-06-11 | 2025-06-10 | Level 3
6ff21d50-881a-42b6-adca-1c6b573e7570 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
73a96c50-d579-4516-ae91-fd5d8950e3bf | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
2a69ee6f-0001-4da2-9451-0e86a2c1baed | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
2b78c450-4ae6-4a52-9a7c-7d1b460a800f | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
2b167978-5f9b-43b3-a44e-888e986516f8 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
33894339-aea8-4535-b979-2ad380646a01 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
4116cfc5-4215-41c5-a6e1-850c32a5ec54 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
004cc409-6767-4f47-922e-70a181b3111c | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
0f8d7fb0-459f-4606-bc8c-edf30432c8db | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
0599d14a-ff5f-46fc-9842-8026c3dbe721 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
d43ec500-5f73-4518-97f2-675408b934cf | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
ff453540-dd5c-44b9-818e-e76993a5ef01 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
e646d019-6aa8-4487-b200-28079532c5d0 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
8b2796f9-8091-4815-9bbb-cb765a2d2a1e | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
b9ab27a1-b4d9-4f4b-a303-ccebc36945a5 | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
f9813daf-7509-41ee-ad7b-fb9cc7afba5c | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
f8834862-2132-4dd2-9862-6ec011e234dd | Pole | 2 | Distribution | 2020-06-10 | 2025-06-09 | Level 3
f7b05064-67bb-4860-869c-92da0fa42fa5 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
f1ea5576-3363-4244-a989-f809b777f346 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
f4574e02-cfa4-4fb5-9a52-a395ce2863ba | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
730291ff-fd0a-441c-9355-56f0fb97999d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
eb139688-455f-48c3-8684-e56a0b600a8d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
db09e8a7-ce2e-48cd-802b-2335114cc856 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
db67f771-1c69-4fca-9857-1a02fd97d909 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
e496fda0-9d29-4a84-a5dc-b0fcdb06f835 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
b0eda230-26c5-48ba-8929-1e469db1553a | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
b48b4c59-2c96-4eba-ad86-6662e445bf50 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
bb220be7-8f0a-4ccf-9383-1666ad64e609 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
c81d314e-f947-4c1d-b4c8-94f8c78c991b | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
c6217fcb-1654-4cd0-9b63-a60d0c7f99c6 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
999a9a37-e93e-47a5-8e78-d100204d1dd7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
7c540a44-82f0-4e33-9597-c00f12d6dfd9 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
7c800ae2-0c50-4f6c-ae14-8930671bbd65 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
06e4038d-c548-4310-bda4-3813c1460585 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
080401cf-608d-4320-839f-236e9050f19e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
0967767a-ae26-42da-9af2-f828eb3a33bd | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
02dfe44e-70a4-4ac4-b452-a6b19d4da52d | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
1422c26c-bef3-402d-a3ba-17bf458470e3 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
170789aa-88d3-4501-a556-8f74a5aa40c7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
176e05d5-c420-41e1-997e-23940a2c0cbf | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
215ff7e3-c507-4041-97f6-a9a277dde2e0 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
1b5681ae-7351-4d77-a623-900390def3ec | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
1b1d833e-4a57-45b0-aa3f-2137df008f6b | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
6291db56-a064-4aba-b92a-7e2156cba41e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
3bab1843-2b41-460b-9e88-f2f1633828d3 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
46fc78ec-48c7-4000-8109-e6769d8a5386 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
34d88b01-6c39-4059-b5a7-699ae79b9d5e | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
37841d19-9db8-4e23-bd88-3535b4ba739f | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
2548c863-b045-48c7-a426-a4ad9bea30b5 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
76bd49f3-4101-45b5-8642-dd7bfd90ce0c | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
76b4f43e-9720-4b57-a917-3b9b58aef381 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
6fb8be98-3328-4c21-9de9-58c62dce53ba | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
6bc56f87-9b1c-4f86-9eb8-845b4e5c62ed | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
685e4d35-f687-4d42-807f-d1daa6e999a8 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
671f2925-2aae-4aee-a177-a5a1661638af | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
60214aef-2742-4cc5-a78f-0603ebd8e13f | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
5484733b-c97d-4873-8d9a-0fde7043f4f7 | Pole | 2 | Distribution | 2020-06-09 | 2025-06-08 | Level 3
545b9cde-99d3-4a44-847f-cb4f2ebcbbb0 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
5f3d33ee-c093-4c0e-9141-38e119b7f936 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
2d72eb9e-2c3e-47e3-b598-f967379303fd | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
385011b6-e124-4200-b979-a6cceaaafe20 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
21b47173-9eff-45c7-8b94-863a9f119792 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
7e1e834e-550a-4d34-b758-89eb071558ee | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
9ab0e5fc-be17-4b27-9b13-b6c5cf6ff9ff | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
d03c6be3-6cb5-495e-aa2d-1443451c09ad | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
e8c321d7-ef6c-4c75-84b8-e4f6a20240bc | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
f331ed81-87b3-4963-8bfe-c33ee6f51ca2 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
9a604bf3-419a-4dae-ad3f-96161468c058 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
ff2f1fc6-ffc0-4dce-913d-9b952a34a384 | Pole | 2 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
acbf3bf0-9be1-4635-a9b1-1824ddb72572 | Pole | 0 | Distribution | 2020-06-08 | 2025-06-07 | Level 3
c93df8b3-40aa-4669-9f40-067e31dbba44 | Pole | 2 | Distribution | 2020-06-05 | 2025-06-04 | Level 3
02344e6d-83e7-49f8-9d84-ff2e35b3a6f6 | Pole | 2 | Distribution | 2020-06-05 | 2025-06-04 | Level 3
d6bddd38-89b0-4ba6-803d-d1ff74c6db1e | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
aeb3343c-5028-4b3e-8073-ecc29fcc4678 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
837e4b18-02ab-4739-b434-a15c44b6a8b6 | Pole | 0 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
6c2b1a47-994b-43a9-834d-e072e7f77577 | Pole | 2 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
04b45561-b615-4f05-ad50-ffd9e7fe8e8c | Pole | 0 | Distribution | 2020-06-04 | 2025-06-03 | Level 3
001b28b1-a788-460d-9767-d6b7fc992dcd | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
166595b4-e30c-477e-b2e0-ce3e384aa416 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
15251438-a773-41c6-9771-cb1f1f28e3fa | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
7452e2cc-3fd5-424f-a42b-11b56c9b9090 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
52af7a26-e7f2-4236-ad4d-f94de591db22 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
3d1d9cda-042a-442d-9321-3904889025b4 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
20a13a3a-095b-4343-8521-b05a83bc4990 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
8e845c8f-03fa-4c64-9a47-101b9a8ffb8e | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
be1398a6-2afa-4363-95b5-a5b27b182f3a | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
b3ccb286-e26d-4f97-891a-f4375a0745e5 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
000d6554-53fd-4fd2-ba83-2102f1df719c | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
8ad3f694-741a-45d0-b6d4-0618fbf19756 | Pole | 2 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
a16662dc-7d00-4b29-9f5b-c7b468958946 | Pole | 0 | Distribution | 2020-06-03 | 2025-06-02 | Level 3
7c0d85a2-2b45-46f2-bc55-51b7281eb017 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
cb32183b-ed20-4f04-a034-b443de2422b4 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
a8896dd5-c2e7-4923-a9ec-4a27f7b43588 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
93c1acd1-18a8-4137-bfa4-aab9046cb191 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
30ce9bcd-9edb-4a38-9332-0219dbb0439c | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
4c4e9433-fa75-46d5-9b3c-3adf8300c6f3 | Pole | 0 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
6c3241ef-ccde-484c-a350-c79f6e612ad5 | Pole | 2 | Distribution | 2020-06-02 | 2025-06-01 | Level 3
783733ec-4a1c-4608-bd56-3a0ff25bad90 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
1ca119eb-337d-43b3-a385-476e595df367 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
0f9cb270-fb35-4788-a9c1-a46ff9aa712c | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
250e00df-d4d4-4c89-ae53-a9ca3157d619 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
0b7d1737-4577-426b-b129-c5b15b3b7d4a | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
2b540719-fc7e-4b37-8568-85fdd48fb504 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
a3b6a4b2-7c65-4c80-a09b-ccba8dc652a3 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
e97574c7-efd1-44a2-9684-b3d4c8ab40d8 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
adcdfe91-858d-436f-a41b-b179a0922201 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
8ace8f23-17a2-4fbf-b272-d6ffe3a13601 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
212a8d75-764e-40bd-a7d5-384f98ffba3c | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
9e4a87ee-5f08-4575-9378-715c9f8a12b0 | Pole | 2 | Distribution | 2020-06-01 | 2025-05-31 | Level 3
b0475d8e-21db-46ff-be02-44d63d9d98d8 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
e891a2cf-274f-4f82-a8d3-ce36bb376abe | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
e80b276d-e60f-4816-848b-9b3fa22c5c92 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
58b9b3cc-6110-4661-b21d-e7aae29f8c3b | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
ebfa42cb-ce02-4436-b12c-81348cdb782a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
5a3f69c9-cd0b-4b2b-8547-e2c9c7154cea | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
3f117007-e7bb-4065-bf39-9358ce376e3a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
2fdf2a14-0af0-4f35-b5e7-3d906b5de7f2 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
6a481b6e-6597-42e2-b26f-388d05b0b6e7 | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
04d42b15-f7c7-4887-be1d-39eedb6b041a | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
2b0c58f3-f9be-4447-884c-1d88c8333df8 | Pole | 0 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
eb8ea6ed-a522-4ff3-af56-edcfc06879da | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
584a2ad4-6616-4e53-a150-fd7da3df079b | Pole | 2 | Distribution | 2020-05-30 | 2025-05-29 | Level 3
47fdb50e-08bc-49b1-b030-a1708b0d993b | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
c8ea586a-a2a0-4d25-bba7-ece86ef09e19 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
0612c414-af3a-4c55-b1b3-de65e27559bd | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
3843097c-090b-45cf-a84a-0eccbae83213 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
c9aa8721-2594-478d-90ea-a3cc79e75ae9 | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
d3024389-ab7e-438f-ba4d-933ef69e9d0a | Pole | 2 | Distribution | 2020-05-29 | 2025-05-28 | Level 3
ddee5057-698f-42a7-8cdd-1adbdd72fa29 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
bf8b8222-f331-4ea8-93e6-3249da62d084 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
8847256b-025d-455f-ba07-099b871ddf47 | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
9535265a-04ca-4a09-b71c-f2a6b1ee6336 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
fd8b8786-faf8-47f5-8792-5e667966c606 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
61f6ddf2-94e6-40d1-84b4-630fc2a19a8c | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
9aa22f0c-03de-4aed-ab61-8d005899e06e | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
e9877be7-d0ff-4236-98c2-f0c2372624a6 | Pole | 0 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
131875ae-3128-4e84-bf4c-efdfc56713a3 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
71491fe0-7d6f-4e83-8af1-d79095464810 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
6b27f451-f0dc-4269-a840-d75e5b34b566 | Pole | 2 | Distribution | 2020-05-28 | 2025-05-27 | Level 3
6ff2debe-4365-4913-b15d-b63f5e6797ca | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
13059a39-a6e8-4090-8e3a-1d1f8f576a48 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
0fbf518d-e1cc-4d8f-b1d2-535960d40d3a | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
0da8d208-acf7-4b4c-bc30-263e5c53ab80 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
80c21f99-d4ff-4301-b9bb-69b8b7163da5 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
9b911c71-95b7-4d18-8dc8-898ef9a00069 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
784cee99-1e90-4161-94d0-e2550919cd1d | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
77e1e2db-23fe-4104-809f-0849d7aaef1e | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
5db4f4b7-e454-40fc-ba11-227f09e3a1ec | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
29810324-acc4-45f7-91dd-d3cecc49279c | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
91a28a7c-fe2d-4986-ab86-f27417a7a491 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
a557eb2f-2b17-484a-a235-cbba6576dbe2 | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
a6b9607d-2138-4d2c-81b3-f460bd0ba83a | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
8d2d86b3-ef49-4e9c-a762-b433a843cf81 | Pole | 2 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
d1362e5f-f700-4fcb-8614-62d0092f867a | Pole | 0 | Distribution | 2020-05-27 | 2025-05-26 | Level 3
8509e229-981f-4b69-86f6-cf19b8bedcc8 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
cbca5b3a-458c-4101-99b8-524b13c48d8b | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
e2625e98-ad3b-4ba3-a1e2-85ed0a6db25c | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
f45f5cde-ec6e-475e-b0b0-7b7e550c8551 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
7d69b8a9-2c7a-47eb-aab8-3da6c2a5d175 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
a51d1920-1706-4103-b220-fff42644f53c | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
959bc14d-9d18-40d9-b530-7fea3b3dae7e | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
bf6fa54a-f59d-4cf0-8da1-8d7988b0e429 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
b445c7a9-27df-44f3-904a-da661b95d27e | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
aaf293f6-f244-4e31-b52e-b5820a9527b2 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
aa2afc70-11b3-4453-a8ba-c475c13f3373 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
c374e464-70a4-4a0d-a325-d0bc55efab34 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
bf9d2f32-faab-43b3-84a2-b18dbb39e559 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
ae4833bf-1fda-4e03-8994-6900c6f63ad6 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
8619fd70-b12c-41ef-8b54-7dcf5c4788c9 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
15b027a4-45d1-48fa-a6f7-ee9afae5fe13 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
d9656d1c-f0d1-4115-a01a-b249ab231187 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
e7856048-dfee-476e-bc51-87785f15041c | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
58b0355e-0c9c-46a7-a0bd-e9275f924c24 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
3fb5d623-1e1c-4717-8fa7-72dca553dae2 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
b7efc259-ca0c-4158-8d1d-19e19039dfbe | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
bfcdc883-a456-40da-bb63-bd1e9d510d9f | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
d5971376-5bdf-4766-ba58-2a2e23e648c5 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
ec1fb059-cd11-4d13-84bc-31a81ee2ddb6 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
f20ae222-1d51-481c-a752-8ca01c452f23 | Pole | 0 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
8ee9b02e-7d14-4992-9708-1dd748ddb05d | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
22d87353-89d0-40aa-87a2-209c6e49f722 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
56019431-6ed3-487d-8338-e116d210dbd2 | Pole | 2 | Distribution | 2020-05-26 | 2025-05-25 | Level 3
639d7211-e341-4be8-97df-820cc41c815c | Pole | 0 | Distribution | 2020-05-23 | 2025-05-22 | Level 3
3cf44692-62de-4a0b-bb8a-6e27d4f83e6e | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
227572b7-f111-42a7-83e6-19a059229dc7 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
0575f101-4702-4ca8-9bfd-27590b7be815 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
042ab82f-0c8d-489b-a416-94c06e104e4b | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
84322372-bb4c-4a89-b66c-df6c180fa8bf | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
c02852c9-0704-4665-94ed-3ab62e39d823 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
8863c212-da34-4eee-a1d1-2bf7ae2c1d60 | Pole | 2 | Distribution | 2020-05-22 | 2025-05-21 | Level 3
eb4e1951-4361-47fb-b521-d3f33255ed47 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
ce42fda2-e39f-43b8-ad09-b7da29f3b2f0 | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
6c4fc33d-43eb-459d-8745-433d7e9736ea | Pole | 2 | Distribution | 2020-05-21 | 2025-05-20 | Level 3
d7c3ff93-6fc9-4627-9bff-10a3b5f86ca5 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
e6545e42-4c3e-460f-a0ec-9f8dac1385e7 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
afcd25ed-80f3-4710-9d92-a76f02827438 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
732b30cf-9323-4987-a1fd-018c45039dd9 | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
e09cc3cd-02f6-4596-b535-28b222f50d30 | Pole | 0 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
d398af7e-ecfb-4696-b860-fe7984364c7c | Pole | 2 | Distribution | 2020-05-20 | 2025-05-19 | Level 3
9480f630-f5fd-4e8f-80b9-fa41724cb2af | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
891678a7-8fce-4958-b836-933d5d8cfc67 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
fe96cde6-e725-465f-964c-1a786efce1ed | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
5f8d96f8-5dde-4237-822c-ddfa88d1853f | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
8b60f815-127a-4b58-8173-31d5f69776ef | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
92303dab-032d-492d-a17c-65cb6a12ed5f | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
b05a5515-a2e6-4cf2-bbe3-2d377331ee8a | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
6cd22fb0-050b-4df8-ac7f-d45c3520d2bb | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
64bc557d-69ee-411d-80b9-965c38e24d50 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
560f12e2-fa49-4cac-96bf-f27c1762b310 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
44a5ef5a-0990-4c87-8642-ac9f22725b38 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
24219567-b721-4569-9039-9d8da67cdb26 | Pole | 2 | Distribution | 2020-05-19 | 2025-05-18 | Level 3
452d3435-5fd0-43f6-9bab-dd0972a41569 | Pole | 0 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
53a03697-8ccd-4acc-aca5-ddbb1ab86fc2 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
6b8f67ff-67ff-4dbf-b318-3b5688c09ea6 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
e012bca1-98dd-4843-b9c6-248c74cdcfed | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
89fa3ebf-b907-4136-8ebb-eb32238cb44a | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
8354e197-8683-48b2-b1ca-30d0da015944 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
fb639ec5-b61f-44e2-bdba-796b5490571b | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
fb4048fc-2030-47e2-b626-8570022422de | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
5f1d6604-7895-434c-8d0b-5f750f554b44 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
8fba3f55-a097-4e38-a568-12695c576fe7 | Pole | 2 | Distribution | 2020-05-18 | 2025-05-17 | Level 3
e3a70d1f-79be-4932-a296-a55f84df0ed3 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
eb175d0a-80d9-48bf-a4c0-6a515e2f7e61 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
8a75bdaf-ca8a-4f49-9fc6-5dc687f0d0e6 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
aeb55969-9193-4974-a095-a94c53e77055 | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
692dd435-25cc-4076-b5e5-4a927b917dff | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
444c6720-5675-4c55-b791-401109d52add | Pole | 0 | Distribution | 2020-05-16 | 2025-05-15 | Level 3
06e9d14b-d287-4818-b8d3-3397c8e89060 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
ad010ba3-457c-4624-a5a3-b173a5995b91 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
ec18621e-b025-4de9-af07-db20384faab7 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3 |  | 0:00 | 0:00 |  | Pole good and intact, missing above itwms
d80e0c4b-16c5-4d4b-9fdf-6db86c2d1426 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
8f3369c2-dba0-44b0-afe3-7a77978017b7 | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
91549a1d-4b9f-485f-9953-ddfddcbe51ad | Pole | 2 | Distribution | 2020-05-15 | 2025-05-14 | Level 3
c7a86051-62f5-47b9-bbde-77adf7c75979 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
7b4e004e-5e0e-4cee-a456-09ab935df573 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
a7b9ac68-544e-49f3-8ea2-a6f522cf73b6 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 0:00 | 0:00 |  | High Voltage sign installed. Crew to change out insulator
05b6dca4-4d19-46c6-8462-bc0fdecc75d1 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
1b1a4e68-8650-4314-9b30-d2810dbbae26 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 0:00 | 0:00 |  | X-Arm needs lowered with pole top topped and new split bolt installed.
e13149d4-fde4-4285-a12b-dfca8e9e9096 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3 |  | 0:00 | 0:00 |  | Need guy guard changed out and new HV Sign
1f23bf72-744c-40e8-a47f-d60ff72e09ad | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
92827999-fa1f-4e4c-93d2-b93e5453f065 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
d46971f5-bd54-4962-bedd-af1b7e5cdfa4 | Pole | 2 | Distribution | 2020-05-14 | 2025-05-13 | Level 3
2797543e-f9e1-4cfc-8b11-8cc8ab73fd56 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
3d23236f-de9d-48e0-90be-22227b8b5c34 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
04ec7d19-0ad4-441b-84ba-190c4c7faefe | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
04ec83aa-2194-457b-bcc0-14614f6dac2a | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
462d1add-2cfb-4921-aa82-cb92b5cae146 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
354b21eb-6cc7-4319-b900-271bbd3866f8 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
326caf54-c51c-4d5a-bb0c-46bd95233ff2 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
32b1bfd8-4d3b-43c8-a65a-baed2746be8d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
7869b44d-4be5-4876-b651-4bb059d61a39 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
a5c833b2-094d-4951-a7fe-e4ec3b9e005d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
9ca3a0ff-6b2d-4cbd-83dd-c7fdad2b6bd6 | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
b91850f9-27f5-4632-b7de-7a4bc61adb7d | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3 |  | 0:00 | 0:00 |  | Need HV sign and to inspect neutral Hendrix top to be melted
b49fc804-557e-41c2-9ec2-03a0204a3e6b | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
e0eed9ca-a8e0-413b-97e5-dca44df97395 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
f209ccbf-5469-483b-9a5e-3c813f456fbc | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
9be6cfb4-6006-4c13-99c5-971d5f1c31e2 | Pole | 2 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
a61c9711-dd4e-48cb-92f3-4fbae07448ff | Pole | 0 | Distribution | 2020-05-13 | 2025-05-12 | Level 3
8bac5bc3-a5ac-4c48-af13-76fa21690590 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
8d80af29-cee7-42db-b2ed-17324163acf6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
77161aa9-b9c7-4a74-8dfe-7809c72fd552 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
73849316-6ee3-49ff-a442-56599d17825c | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
aa1af4eb-7b46-4d45-92a1-2693d1bbe70b | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
64936060-0067-482a-822b-2d137dcb1867 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
fd5d8217-62d8-452c-963d-8dc312761640 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
ccc09d29-fee6-4267-bc86-cece4a79f36a | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
bc290678-eed0-4999-ac82-496fd9598186 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
e6cc5012-fa93-4dc8-a9b9-ef98a63d4db5 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
e32fed23-ed08-47b2-bd4a-75d6d27c7068 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
d56cdd82-11ee-437f-8158-c22ca24cbd91 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
b326dc47-51ae-4702-95e8-84a9f1607487 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
c7c316c7-69a0-44c9-a178-34d0c93ce210 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
91d48b43-a333-435f-b2f3-a99d328df695 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
a71864ea-0516-44f6-b339-6f40e46af0ea | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
8f82629c-9eaf-4e4d-a648-31e6ef66e984 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
8ed2adb7-dfb9-4581-8d9a-012d27f92d36 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
753180d6-ec1f-4684-a1af-50050a72cb3d | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
4fd236c0-7fe1-4b44-9d65-344d7c936ba6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
379b5736-0e77-4891-9545-3cc3a20739a2 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
2d7bffda-1adb-4972-9742-569fc916e561 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
4a358beb-6d90-4744-9e31-a1b6a212ecea | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
3b4cfe3b-401a-4956-b4ab-9b80bcf1c13e | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
1b6164e0-69ec-4d84-8a13-49f4469860d7 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
afa326d3-bc78-48ed-8322-394624533157 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
1e442a4c-6904-47b8-adf6-0df1ad10b047 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
0e13fb79-1f4a-42cc-a4f2-f95ff17d35b6 | Pole | 2 | Distribution | 2020-05-12 | 2025-05-11 | Level 3
5845bf12-b2f5-49a8-9991-b61e94c174ad | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
69e3eadc-54cf-4204-b5cd-28aef412dde8 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
7f961c1a-6c7c-4797-9760-4dc9a329062c | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
d3fa00ee-bb8d-4159-bce4-c69e392a3504 | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
cb8665d2-7ee5-4682-bf3b-15a5c505b0cc | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
a8a670f6-3efb-47a8-afb8-07313639c21e | Pole | 2 | Distribution | 2020-05-11 | 2025-05-10 | Level 3
9b064557-13ca-4b78-964c-fc661059d18d | Pole | 0 | Distribution | 2020-05-09 | 2025-05-08 | Level 3
b5cab04c-9fd3-4a11-8662-3a8de9c45116 | Pole | 0 | Distribution | 2020-05-09 | 2025-05-08 | Level 3
33559564-5257-4c65-bc57-d6b2e7cd39ce | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
9ce10e49-3c4b-4e7c-8f46-4df48a42d12f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
f9b1c9c3-bb3b-486f-96f4-19b930b9e6a0 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
b28ef08d-df94-4e58-b883-314161d25093 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
974f76a9-a150-495f-b6b7-a5563defb33e | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
8b861111-56a7-4d6f-af31-978d2a1a8be2 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
fb4a757e-148f-4087-8683-6b0a354f583c | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
ce8f30f3-6da7-4ce4-b5b6-cb174cab6f5f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
c90447eb-aa47-4c74-9fc0-66bd65536d3c | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
c3c94409-f784-410a-9679-b141c109d0ae | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
3103430c-6289-47f9-9763-f83bbd411174 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
8696c674-f9d8-421b-8a2d-5532d8e1fefa | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
25ae29be-4599-42e4-8d3e-5068934c3a24 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
cd115a8a-b0af-48de-a7ee-55af3c97f726 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
cab9b05e-dc1d-4803-9b71-dccfb5f12d23 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
d8fb5c1a-36b4-45f0-8fee-7b23c51089f7 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
caa57011-9cf4-4fe6-9971-a5d394aa7353 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
ab5603f9-761a-46d9-9507-6f0026706245 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
e439c010-30d2-4f2c-9e2c-df2c4bccf5d6 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
eeb87e1a-a320-4c65-9b95-42224a8c1486 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
854a7c06-8c13-4385-bab0-1dc63c5de6f4 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
86e0983a-7b3a-4457-a319-a061265aae09 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
a5bdce12-8234-4147-aa95-76aff7277f20 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
a3941a41-fcd9-4bc5-9366-143afd5a4766 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
924873f7-8324-4c88-87d0-56ae1b541427 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
93e262df-8418-460e-a1f5-6c19ea22a16b | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
743266c2-5a3e-43b6-9eaa-3a7e2d84499a | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
6d5824ba-7dd7-4361-b612-39ecf4c43161 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
7b7ad3bc-6ee8-4da3-8ba1-39bcaee2ff33 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
494b5a07-b74d-4cb9-97fd-d9f6a8e6074d | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
b82124c1-708a-4f0a-bb54-392ece6e05ad | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
b8585375-ab22-48cf-aa87-aaeab22f316f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
1b185877-7b36-4480-bc86-c5c202de6492 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
51c0f373-154d-4214-9405-a977744dbb0f | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
63ae0f58-192a-4e45-beac-a4c45b78f7ca | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
8c045216-06d7-4459-9b52-cc43d3176fc9 | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
1b356147-041a-4f4c-8746-d356fe3f94bd | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
bdf9e004-1570-4586-9707-e5b4b61449aa | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
86fb0fa0-ced6-4c72-99d7-af0e126b4bec | Pole | 2 | Distribution | 2020-05-08 | 2025-05-07 | Level 3
adcd22a3-3967-4abe-9342-fd24d10b4b5c | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
3c7a1e4f-e996-47e0-8dc5-4cab9bfda021 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
0a472885-8ce2-4131-92ed-98c0b602e0e7 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
0f734ede-ab67-4b08-ac4b-238ea8069931 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
12b3159a-273a-43a8-bb97-fac8654984a7 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
b94a7a26-6cdd-4cd7-97af-900b7adcaffa | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
62d9f053-507e-4d52-8f8d-296812263303 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
5c216429-df09-4067-9dd8-3ecfbc8a321d | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
4cf81b5d-9aa1-4a6f-9e7f-1f3635736e13 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
6b4ac851-152a-4cd7-b22e-bdeb42d6910c | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
43b2ff6f-676f-4578-9be1-a4784f1e40b9 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
4878e6c2-ac6b-4129-a566-11ca4cd42eff | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
77a6c29a-7286-4357-88c5-e88abb2fffdb | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
bc2de546-577d-4c70-bcbd-3982b2ae1516 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
9a5a27bb-174f-479d-ab21-c2071e6ab5f3 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
99c63bba-56e9-4a1c-9a93-311f7a2be91d | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
a1d31faf-ccfb-4ab6-b7b7-a6e3659bb1bc | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
84c1808f-ed0a-4640-b834-0fd864939323 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
7fe7c6ff-a2bb-4618-b592-1a04ab96f255 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
e76b04a0-1549-4437-a020-cac09ec3f737 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
f3d542ff-86e3-46b3-9317-60df2c91ccdd | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
d3f9e964-f3a2-47ba-b8d1-8617b4394edc | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
dba44d10-376d-4f82-a49d-c1bdaea8caf5 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
be037e3a-a305-4193-ab92-b35574ffef49 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
d753be93-1ec5-44b8-b922-75e5c7dbe0b6 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
0b593546-fb59-452b-8f51-bda6849fa20b | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
087a548c-b2ca-4812-996c-539d0ac2951f | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
d28b39ac-900f-42ba-b1ea-60c1fe512d62 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
c71fa9af-fd28-49b7-8daa-c5b3185298c6 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
fd267ec2-1b23-4346-b8a5-9d866f5be262 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
f2aa4ac3-5776-4e77-83d7-1c60a9c655b9 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
ad432d86-1a01-48aa-9f8e-3ed66ed6f288 | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
acdaa6df-cd0a-446d-9025-0c999c961c0d | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
b676793a-7515-465e-8bc1-88ff76a3773a | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
bc6a8e15-dfcc-43ce-b08a-b48e58c5b56a | Pole | 2 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
29ae7109-7c6c-4ab1-876f-7873be1d9ee9 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
5fade760-903f-4870-b54a-460a26bf56a7 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
ed23497d-b31e-4081-a1e5-23088818abce | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
f6f5f18c-4a61-4141-870b-38e2e95651d6 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
e359ac23-0467-452b-931a-34255c5fdd06 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
db01bd40-1567-4592-8c13-37a694287334 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
cc49f07d-2d41-4da9-ad81-e654ff424a96 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
bc768dc7-bbf2-4ca1-9233-d56341a7cd7f | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
b2c785e2-a23c-41a9-830d-fee4069d5e90 | Pole | 0 | Distribution | 2020-05-07 | 2025-05-06 | Level 3
b7d572c3-f401-4c97-b557-e4960e9f13c7 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
9727fe7d-767b-4390-a517-c0c5d42d918c | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
94606a0d-c0db-48a7-96db-7bbebc17da4e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
e97989c3-0227-425b-b15d-4280c14cb383 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
f9c7b66b-de01-470b-a6b0-539f32715790 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
b38179b8-df64-45fc-b9af-4cb462bbb102 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
1fe5f67a-d7cd-4576-8c80-907b24a887d2 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
1a8c4fcc-6520-4df7-9c6d-5f5eca9b4f19 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
fe3576e4-0013-4cc1-ac7f-382ffa9892b6 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
cb721eb4-3536-4225-a2a7-c99249a8a59e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
d988cf77-27da-49f0-b8f3-acaa4ab7f216 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
e0f3279e-e97d-4e6a-9bf9-d79700f70a45 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
eea829a2-e560-48c4-8d8b-32f40074ac26 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
fb899cf2-302a-4494-90aa-492ce0cc10c5 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
f614e3d2-f5a2-45e7-9d2b-e3c6db5d6e94 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
ed3eb46d-2e0a-46ea-89ea-f0d599033206 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
e9b6ec95-b731-479c-897a-f7d556dd0740 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
874bfd68-e89f-4621-a4ac-d8d59b2200f8 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
a2d850d9-f0fd-4552-936b-94f695fe6863 | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
7f7f356f-1707-4f47-bfc6-749ab2a3c90f | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
74588346-5a86-4929-bbba-e2b44332404a | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
18b77001-1728-4d75-ba2b-c916a2f57d0c | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
4b0b0d75-3f5d-4893-81d7-65b13c29a2ea | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
2418d01c-9971-40dd-b125-c30a27636ba5 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
2fac3e3e-54b6-4494-94e6-dc128cfe3764 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
6efa98bd-2c4d-46e9-bb45-897e5fd2772e | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
17728c14-68ab-46f6-9495-8176955dffbc | Pole | 0 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
1064b926-749a-4270-be28-9f405174c5d8 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
235a2e58-1007-42c9-ac95-a928de663551 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
7bd01956-df26-458d-b9a3-278c53710e97 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
65456cc0-25b1-4dab-9ee1-298f7c3c12bd | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
820e8a3c-6065-48e7-a24b-5c4ad6a3c509 | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
f6cb001a-9f44-424f-97ca-3827f23aa9de | Pole | 2 | Distribution | 2020-05-06 | 2025-05-05 | Level 3
1ba0d940-bd62-472e-920b-b86b0616188c | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
6c4ca4c1-4ba3-49a8-b9ae-4cefeecbf104 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
6919f6a0-3538-481e-9dfd-2950dec89825 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
650ad662-ef52-40b4-80c0-34220680f3e0 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
46fd5cd0-e01c-4422-95fa-729a9b59c745 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3 |  | 0:00 | 0:00 |  | Need to remove thimble bolt
b4175150-c61a-4755-8afe-19749612f1b6 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
be273a27-9dc7-49aa-aad0-8e2d917f8d3d | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
a11ff7ab-6c0c-4b67-9dc7-1832bd85d5b8 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
8c7b0d52-f92f-406c-ac3a-2fc49d3b9a29 | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
e6483c6a-5b35-4605-83cb-047fa5b5dd2d | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
82536ea8-9d81-4e03-9db3-b8f8b7071001 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
08b20688-f7a4-4a51-a737-20485ef672eb | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
016f8834-03ee-4296-bd93-bab2873a2ac0 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
4cd2fd2d-7805-4640-9f59-b3de4e2bc24a | Pole | 2 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
608c69d6-a5df-426b-b1f6-08687a993aa1 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
6eae9dde-cce3-4f19-8c5b-d070f21b9e57 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
4e59c8e6-ed46-45f6-ae8f-f05927fce800 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
463ddb6a-0edc-445d-b4c7-4f4a9085aec4 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
428b1e74-9274-44ef-b7d0-12775d24fa8d | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
ede2f44a-5ef7-4a40-8348-2aec92768940 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
81459025-1b79-476f-adc7-af20e9d8c7f9 | Pole | 0 | Distribution | 2020-05-05 | 2025-05-04 | Level 3
8f515682-dd02-4e89-bf77-494cf254e3a3 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
bae7fb8f-229e-41b3-8fc6-aa9fe3416dee | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
c069f8a0-a04d-458f-8563-97a792681d37 | Pole | 2 | Distribution | 2020-05-04 | 2021-05-04 | Level 2
eb254225-642b-455c-965b-6b1b80619fd4 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
3dce80fd-6022-4f55-a4da-911a2b56475d | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
46580a1d-244b-4ee5-8c52-7aac3429ca87 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
3a473451-21c9-4248-9874-445e3a453a20 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
0ac8c25e-5b2d-4874-83cd-b21898375815 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
d4641a33-7d4c-4016-be19-80a2a185d123 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a7960325-9bc8-4dc9-84ba-44d10be9929f | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
11c3ec88-c92b-4b75-8c48-e16a5ef250de | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
837204a4-0758-4fd1-85da-326293832aae | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
ca9ce774-70d4-46dd-89e2-352d84fd9c0e | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
e60892f0-eea6-4860-bba2-816c5df82afa | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
ff17b4b5-af21-4aea-88f1-59479d8b8c34 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
f57052c8-6f90-454c-9868-f4c49bc18d23 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a1985791-bec5-475e-ace0-f2c81d22227b | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a3693937-3182-46ec-8110-dd9917ca1cc5 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
a41c06be-6e87-40e1-a6eb-23e988908819 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
bb4cff05-4607-4c67-b0ff-28be0df77de7 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
576ee34c-4d43-4718-b9ec-0b9a586205c8 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
5dc8dcbd-7e28-47cb-a413-682c7b17d8c1 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
9ebe9fb2-4c28-4c29-be37-4f6d213f1649 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
37c9345a-298b-4db9-936b-4f3678d68780 | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
3f9489a6-3a02-4738-9db1-fa247d4ac3fb | Pole | 0 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
54a954dc-4fa3-4bbc-9a0d-254206958f78 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
58e646eb-e8a4-4c0e-8c6f-b6c31c791770 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
2042c71d-3113-48b1-910d-3a5598d405f3 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
1478225c-52a6-4954-87c1-e1bfb2507b9a | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
17d25510-a18d-4cd2-a779-0f43ee01bf88 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
0f76feaa-1666-42df-b7bb-d36a97fed275 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
0ba5aa72-29e9-4786-9d89-e3bf6d83b5f2 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
084175f2-7bd3-40aa-96d2-b8366849f297 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
d9683e52-99cc-442b-b18e-dedba6870a25 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
94cb8661-cd32-4726-a160-a3963fe2ada5 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
6cb8822c-adea-4d81-aaa8-4ad0207d5e1c | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
5dd658a5-7315-445e-8e33-a68d54a67628 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
2d21897f-fcec-4149-b276-f3cb466dbb27 | Pole | 2 | Distribution | 2020-05-04 | 2025-05-03 | Level 3
1ab641ac-174c-4edd-9ccb-23e3e8922632 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
aad29f10-8a17-4176-b81f-8f3132b93043 | Pole | 0 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
c5b926bf-86fe-44a2-8625-7488281a4644 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
8b08687e-5a25-47c0-9739-cf881f303a81 | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
d934a254-bca8-4aee-bb4c-769dc670e1fd | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
b6f9b765-443c-49b0-a3e9-393b024e99af | Pole | 2 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
99488eec-fbde-4a5c-bc28-a0f48dcf60ef | Pole | 0 | Distribution | 2020-05-02 | 2025-05-01 | Level 3
513b111c-abdd-4e56-9431-bda8b50ed367 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
1d548ab6-014a-4ffb-b7ce-e383eac221e4 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
8e2c75f9-0cc2-4c3b-aec3-11e79c446ec0 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
7e1b6587-91ed-40ae-8493-245f60b3df1c | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
8680a7bc-3b07-4c69-838d-929539cc1b92 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
f99f9a2e-8115-44d5-9ed5-d9e8dc00feb5 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
e0be06f9-e0c3-4c95-9268-cc3d71afcaf4 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
c165a378-e034-47c4-a56c-a8793eac1a90 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
db182d75-dbba-4957-adf0-58c264fc654b | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
d9f903f5-d11f-4dca-a9e0-63cb69f961fb | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
90799aa6-b524-498d-a18f-795c5aa77db0 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
d5720fbf-c827-4d09-9abe-8ee9fcbeeaf9 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
147cf57c-8f56-4434-b71d-f9bb704f4172 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3 |  | 0:00 | 0:00 |  | Service to night guard light has been abandoned. Light not in use at this time.
143cb5b9-da5a-4e87-a81a-cbe730b6d4fa | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
0c68c2b7-45e9-4333-aa11-72e744a70032 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
bbb934ec-fe27-4061-ba82-6b77deebab01 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
2228cfd3-67ea-4ffe-ad9e-5f3a135245b7 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
57d32883-1cc5-479f-b42a-e3dcf3cd5f06 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
52d63da3-dd2d-428f-b1b3-a1c31d503460 | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
3c182798-e4eb-44fa-91f1-443892bc1d1e | Pole | 2 | Distribution | 2020-05-01 | 2025-04-30 | Level 3
430f64f7-a95e-4e5a-8aec-2352fde5a289 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
5be6da19-ee26-4bd5-ba31-722099741d01 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
5b043478-833c-49a2-be8a-e0c76ff83b7b | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
67c19923-31a3-4cdc-a311-9a2b71708c74 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
6bf162b6-cbd1-40c0-b617-b4cda4bddf27 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
6ad6aa60-8d22-4530-b319-499b4d2d77f7 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
7155a2df-d460-427e-8609-99c4e0340b1c | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
30c90825-1c2d-4664-a008-e7a370d3e8b4 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
0e74556c-089a-4d47-bba2-be11f351b6b0 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
13381093-4e8b-4428-87d7-f02868751e23 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
d4e7342a-ab96-4da6-b6ed-a462f7ac45d1 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
20e3a89e-fcac-406e-b0a0-daeec355ce16 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
a23b456a-f53d-46d6-9e66-600e6da1e621 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
ab516081-6c3a-4456-ab89-7faee59e4a20 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
c1136a3a-4945-4892-b3d2-0d15e5fb6b24 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
c79ef9ab-12b8-4505-b97b-d7b8e6264fcb | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
30dbb492-2a83-4816-be14-3e8a88609e48 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
91a1d565-acdd-421d-bf4d-96abb48027b0 | Pole | 2 | Distribution | 2020-04-30 | 2025-04-29 | Level 3
92a0b3d8-e180-4d0b-9528-42d1e72823cb | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
7eb651e8-6f7d-4e6a-abfa-1348b20eae85 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
53b8cadc-146d-402b-935f-e9e4be740132 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
a7552d2f-c6c4-47a3-82be-fa035cc237c4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
d5cf375d-7ca2-470d-a1ad-6c35294240e4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
1fb22a72-3638-412d-8b1d-7e382dbe9a28 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
837080ef-05b3-4ad7-a623-e84c4ceee013 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e55c30c6-d89a-48f4-b58e-81f9225c325f | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
c54e1d26-1669-439a-94a3-c85444c46491 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
c77635b3-e156-48d4-9908-34bc7f1d966c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
bf701bbb-1174-4420-96a9-9f16db9bbc16 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
9d2004b4-40db-4e87-822a-a2851681477a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
b13ab5fa-4cbb-4511-8bdb-6dc7afe376fe | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
b1cdd578-fb2d-4458-9b88-2349c7ed84e7 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
9a6b2120-3d3f-4281-aa73-9881e38340e9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
30a775ed-e367-48a6-ab67-49d03fe62ae9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
7bbeda37-855e-4278-a5f7-15d0f8e2ff1b | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
7cc032f3-dfd4-4616-ba8e-78652c921b5c | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
83add555-73b2-4af8-b989-23ad42284190 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
eccc256e-e031-4584-a793-5a2cc85592dd | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
f8531135-6865-4a21-8838-5e5df384c415 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e6511318-6b17-42df-bb6c-2af709525f8a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e5ef72ba-a80a-49e6-8809-5298f6f42351 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
e50d8b8c-b58e-4a77-a4dc-618468c9d4dd | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
1f5e92bb-7e8c-4628-93f0-4678b01822fb | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
20d7ad77-0388-405d-8b5a-2047e3da4021 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
dab140af-faa1-4f0c-83c8-3ef77cafb1f9 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
4fcfe9b5-fe35-4105-bc41-d71a14ce63aa | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
58fdb083-cfe6-4863-a8e0-88360b46afc0 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
46e1c6a3-9e32-4d82-bf99-baf27da9ddb4 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
4273e01d-0147-43fe-9b71-7bacce3b1b42 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
41be9fe7-698c-4043-8c26-d6ef61797c6a | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
443f664b-94f3-4d72-a10e-3a2e41625171 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
27e7ed88-e29b-442d-9c11-4cddbcb21692 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
28f857f3-5c8a-4801-b154-fa774e3decf5 | Pole | 2 | Distribution | 2020-04-29 | 2025-04-28 | Level 3
2e895b5c-d700-4386-9ff1-635f4b0e2494 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
62c3fda6-08bc-45e5-8acf-64d416454ffa | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c33c1b73-5222-437f-9258-b4814fc9cab9 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
1569a903-0015-46c3-b11d-f88e6b9b0587 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
0d056eb0-3bf1-4fa6-b47c-01880a10fb9f | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
08da7db0-5556-45c8-bbaa-9e6b1c70a52d | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
47eff5b4-e383-417d-87c8-2ae90b78daf6 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c886beca-9c20-4a89-b578-8a6e93e503a8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
83160693-5a95-4aa8-93c1-fcf36d4afa60 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3 |  | 0:00 | 0:00
c9fb3f22-fb50-45b5-a1f6-7341c660bdfa | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
ce2f3699-c7f4-4fcc-ac90-d21d2f3d8861 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
fc186ee5-1475-4748-ba65-5b858cce0ce2 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
f67f8181-c62e-4d90-89b3-65fd89d4c45e | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
ea53d1ec-7868-4080-8364-2ca69227cc1d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
87965bb3-6c6d-4ccc-bb48-fa2a349c8484 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
89e32e9e-34d5-46ad-93f5-5c81514796f7 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
a331fcfa-a745-4e38-9ff8-696690322020 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
a589524d-986f-4ccc-8eb2-221838a26ba8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
b1a2b2dd-776c-484f-a18e-0c1c8aee0c98 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
aa752864-76a1-4ecd-82ce-20979837f59d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
abdccf8b-0d55-4fce-a61e-5237525935d1 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
aac3b5d7-4eec-4939-8f72-97303baa8232 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
af3ba445-3fc1-4727-8471-2d77b11eb2d3 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
bbe541da-1c00-450b-b3ef-39beee439c05 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c44b7643-4161-40df-b44e-54de45c0f367 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
2110b418-c40c-44c4-87f5-1019f222072b | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
fea01f17-a03d-4af4-a45b-7a4782fb1f10 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
4069606d-04ed-497e-a25e-884ebd7bfbe5 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
15171492-6852-4719-a1aa-18c406ae8fd8 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
c8dd21e1-80c7-4423-b8b6-bce86b47a8f1 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
bee7947b-f1ff-43ce-8cee-9063fc018f83 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
f9bff972-e071-44b8-b006-3aa7695e8c1d | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
520771fc-2c29-42a4-a70e-0145754135a3 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
9321a826-8036-451a-aef9-c8dd8b9ea4a4 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
adcd4bef-d719-4c53-a2a7-642f425852f6 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
003532a5-f874-4897-86e2-01d263236200 | Pole | 2 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
db916691-1634-4971-b061-0f57059d73b5 | Pole | 0 | Distribution | 2020-04-28 | 2025-04-27 | Level 3
896e8a26-5c9f-42d7-820f-060d929235d3 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
0cb86daa-8b95-44c7-8511-eed3b1ff75df | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
358dbb48-3405-48d7-a534-aa2998c50fb5 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
15e04300-3efe-4048-b1f4-8dd65b10999b | Pole | 0 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
fdf225e1-57bd-4723-bd69-b9442cedb160 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
b5ef5c4f-9165-496a-bd80-f8f3312b493b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
e09d463f-2b2d-4cde-83c3-31f82e066b68 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
a58e9d74-fc1a-4044-9f60-0dc239b4422b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
9e5fab15-37da-415f-8f67-0d4e209faaf1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
96d95561-583f-49d0-bdc1-6f4b9b60c165 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
893968a9-f7d2-4c0f-b312-20e4d5d4a1a1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
8781a40d-2fa2-4ca4-9073-7d05247afe3b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
86ad855b-a238-408a-91c7-0cfa0f2641ee | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
85e97c2c-4a72-448a-9f6c-05ac725c2882 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
ebc04b78-716d-4f65-abc8-f6a8510b86e1 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
193ecc48-f145-46f7-afb6-d7323365fdf9 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
e6f5fedc-e6bc-4424-ae7b-690392737d38 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
f947711f-32df-4c92-b4d0-ddb1d2ee18b9 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
f346c9e4-0241-454f-8168-f46c74cae8c3 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
d3bd90b5-ec10-49a6-a840-1dae9da3dfe0 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
d25291aa-f01a-4bf2-aff3-b3d8388fab22 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
d7a5be38-5c2e-4e16-98df-e31ad6467bed | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
e5408b23-06a0-4889-9cfe-1459aa63425d | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
0b20744c-7ce5-46c0-8662-d6ced55ce383 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
1513cbde-9513-4a2d-b368-c118048e6255 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
18471bd1-4e36-469d-9510-377de789fdb6 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
19f52d03-65ae-47fb-968b-8a6af7f6974b | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
20b078f5-16e1-41e6-82d1-906a27abb805 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
1906ceb7-2181-43ea-bb68-72b0f275c8b5 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
1add986b-aa20-4c3d-868d-fa81f86c3876 | Pole | 0 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
052d2dca-85a3-441f-bd7b-1c872bed5b31 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
14e64303-7777-4f98-a2cd-11d4d0b78db0 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
62140000-74be-412f-a13c-323014773a5f | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
64630b3c-53f9-497f-8e2c-459d02c7ab55 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
58be6e1d-4c82-4459-9369-350933d98e5a | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
78bd680e-0b2c-47b1-b275-f41547a0c3a2 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
305760d3-ae78-40be-9883-9813964cc033 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
35231c4f-2d82-4ed9-8941-f3d334697e52 | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
47a7d44b-9b90-4b65-b4e5-f893dd2f2e8d | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
4d87377c-721b-4d68-8e25-42c016158f1c | Pole | 2 | Distribution | 2020-04-27 | 2025-04-26 | Level 3
32b9b9a1-4096-4b4d-9b79-0b77845dc752 | Pole | 2 | Distribution | 2020-04-25 | 2025-04-24 | Level 3
468f77b4-aeba-4c1f-b80e-465c1d3e4e2e | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
4362f727-1e3b-45d8-ac26-34f497563152 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
5b2dcaa5-ce5c-4b28-87e8-91db4577ff84 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
63a27cc3-61be-4796-8fc1-cd5e2f7cdaf1 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
636a0edc-2a68-457d-8ac5-0132755ff629 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
56e6d26e-f56b-488f-aebe-ae32f72cae50 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
70b70a5e-143e-4355-bff6-e4a5ca6bdf77 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
ce14771e-9686-4d33-90ce-30fdb3b084d6 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
031e5e33-430b-4ee5-b3f1-ff553e8ef611 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
dc429a9a-de94-4609-aa9d-e399944f899b | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
d6ccb6ed-5d8e-43c3-9369-95f01c2d5fa0 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
cdc89234-0185-4242-942f-12f4bb17161d | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
7df47d11-625b-4dd1-82b9-69cc53395b36 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
f438a777-b494-4635-a6c7-209a0a40d197 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
8c6222be-80ae-4c20-8175-fd6e02588f74 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
8b339ae1-63b2-42b9-879f-1369b547f46d | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
b535aa4b-763e-4e94-996e-2e4b218884e8 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
af059ab7-70f8-42ed-8863-864a800daac7 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
b3aa5ff1-2e11-4fcd-8bd5-d3b365476aef | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
4dbec616-d185-4342-ae3c-bda82bd2db1f | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
22263dcf-3c6a-415b-b628-cb3020a24d21 | Pole | 2 | Distribution | 2020-04-24 | 2025-04-23 | Level 3
4fb90ed1-9a09-427d-9f06-4ad972bf6ec2 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
2d616e43-f43a-4608-97bd-40131d8fe579 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
34febe28-5276-477f-8cba-9171b96fee69 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
0aaf83fd-8545-4826-85d0-71e05450a684 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
30e3df49-05d2-40e3-8337-67a1f890dcd9 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
cc0880ad-3986-41af-8002-c42769af9bfb | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
65ea9b8e-ebd7-468f-8e2b-a1e84a2bddb6 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
c38ab4c8-f8ff-4694-a012-43c8cad96184 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
3c571e2b-540d-4e9a-b23c-941815925a0c | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
8f0fb592-05a5-453c-9458-79743e63281e | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
90cf3f03-79ed-4b75-87d0-18f727d55766 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
83df61ef-a37e-4127-bc92-40be66c53d09 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
7c3f9750-2aa0-4eab-8269-bcf940f3d658 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
79fcdf9c-1b78-47bf-a59f-09843066c16d | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
fc00541f-050e-4859-bd85-2d37d2dd7880 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
f7496b4d-e984-4905-8964-65b60f15eb6c | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
cf1a3e34-e802-443d-bcae-87a5fa9c495c | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
eaabc6a5-7887-4001-b7ab-b68af62b6af0 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
c9b78ab8-6064-4095-a9f9-c124c6865c5f | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
e393b4f1-6870-4767-8bfc-6fa2017dab2d | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
0e895f7d-aa31-4248-a239-54b5ba0bf69f | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
1b171de5-2db1-416a-891c-4f7fba14fa64 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
17be4394-07a7-4e09-bbd5-b7757f645743 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
1728d1d8-5718-477e-ac21-40d1f50dd7c5 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
14a8e0e7-64a6-4d57-b6fc-60fbb6db1198 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
1189e360-cf6c-441a-b1b2-7181b6b3f818 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
6d7638a1-cfe7-4341-aa28-62b098dbf121 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
594207b9-1c2b-4223-aa8a-373fb19e1cc5 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
5ff8551b-994d-4812-9976-1197f80619ff | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
78705628-d02c-48cc-aa99-f45ce803a379 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
76c823e1-20c7-476c-ad3f-082f1f2f5312 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
693ad4fb-5e89-4305-8f19-febad96819e4 | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
6770e7a6-9df6-491d-bb4a-6c73ed51106a | Pole | 2 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
3a9c8c7f-7d31-4f66-a114-a8335401f4f9 | Pole | 0 | Distribution | 2020-04-23 | 2025-04-22 | Level 3
3c61f6bb-f2f4-41c5-b74b-1c9757a85d76 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
41373813-f3a1-40f3-8b6a-51620bcb51ad | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
67e7d1c0-4255-450b-ae74-720a1c6d3ee9 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
6ca4fe7b-0bbf-4585-aace-3726f01d34d7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
78e905ec-0006-490c-94eb-bd55dc617a0a | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
593da27a-be52-430e-864c-4f96bbfa6500 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
1315b189-4810-4252-9e96-1832f27bfc2d | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
0b975f68-e109-4084-a542-6936e358ba21 | Pole | 0 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
09d5ec18-7ed2-44ae-898e-43cd5a2e90c7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
e02c0192-81e3-4a0f-b8c3-8d4066e6fc48 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
cd44ea95-389d-42d4-9258-541932298835 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
ce8baa4c-bdf0-4539-b3f4-ea531d8c0858 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
c83c26f0-2b58-4a77-88dc-7cbb227e131a | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
d2f2e459-deb6-469a-bfb6-688ad81186a7 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
e86dc3ef-e925-45c9-ab5d-40a022a01820 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
79a5ff48-4ab8-49ed-8b27-179c5a018434 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
f7c3560e-1e28-4228-9b91-b32216ee6422 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
7d90a458-b5d8-4e50-b1e1-e8902f317992 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
930af33b-56d4-411c-8946-dadb7fca5b96 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
9ed46254-7134-419e-adf7-387fe6096557 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
9b520188-af2f-4ba4-b57d-9d3191ca4711 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
bab31805-c363-4d70-abb9-663a5ee51044 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
aeae9bb5-9123-4117-af70-cb9341ba2f26 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
d78e72e2-1767-4299-a45b-1f2caff5907b | Pole | 0 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
8df3e928-0f3d-47cf-af43-1ec84f821bdd | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
fea88618-8b64-4a43-8887-09db6fceb5d6 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
ffcbe9f2-5a40-4740-9ead-27f63142b2f8 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
968ca7e4-8732-4a66-827e-a1f034d16d78 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
414e240c-64ac-4243-adfa-6f3e5b2033ff | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
9b690f08-76b7-4fae-bd57-13d2474b0ae1 | Pole | 2 | Distribution | 2020-04-22 | 2025-04-21 | Level 3
491763eb-a112-4dc5-b552-a84fe7eddf9a | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | 0:00 | 0:00 |  | Dead end pole
44a42916-abdf-4565-acb7-c47e84e88d4a | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
2f95c48e-3d8b-426a-adc2-ea226366f938 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
1680450c-0582-432b-aeac-a5827ee1a94f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
a73f63e2-0bdf-4362-84b7-f2aebcb3eef7 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
58b929de-5247-448b-a68c-fe41b5e3b24d | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
e87f2462-9024-4202-bef6-a8216a7b316b | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
fe1b98fa-0479-4aa7-bde5-fcd6b95614b0 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
9fc0ffa7-335e-433e-8a95-79934889322c | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
9f5194d7-7ef2-45ce-8f61-268b60afca3f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
f2cba526-375e-4a99-aaa9-432169446cea | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
d3b55c3b-f849-460a-b00c-d876394ffe3f | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
d191e4b2-3e69-416d-b7e4-1701b534e01b | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
b4272723-6a32-4de2-b80a-58127ad84b42 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
d8f5c361-8ec4-4580-806f-0696447b723b | Pole | 0 | Distribution | 2020-04-21 | 2025-04-20 | Level 3 |  | 0:00 | 0:00 |  | DDE
1a5094ac-da30-40d9-b916-ccd79e47d854 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
1ddd7e6c-aa1e-4851-8111-dd3d765503b8 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
6b301545-6b00-4341-a430-7dfeabac34b4 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
e2ca8f63-ca7c-4267-a107-589ca5e1b013 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
1038cf65-c946-40b7-a2f4-77e5ec3305d7 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
747b45b6-2e59-4d73-8b7a-17455a66a67e | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
2dc6ab5f-32b8-4a7e-a16e-04a265f731c0 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
33a69be3-0d81-4e88-98c0-f23783f398cc | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
3664cd3f-59ba-4d71-98e3-a13c02708d03 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
2c7d5038-f946-42fd-b48d-7f28c4bc4498 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
2a7d5cd6-c887-4f4a-80fe-2f789e1a9ef6 | Pole | 2 | Distribution | 2020-04-21 | 2025-04-20 | Level 3
29d73382-fd62-4c61-bb6a-f17dc156c53e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
2958caf4-a91a-46ab-a32e-a78524fe6015 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
745b7f2e-ec59-44fc-b136-f0642b600204 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
7a15f696-2919-4fc7-802a-00a25ea0b941 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
767496c9-70bd-4f0d-8a26-ad435ffe667f | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
56521823-2149-49ac-9d56-dc1d9cd34dfc | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
10dff315-fec7-4327-88c1-332a4ed87c1e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
1bb9f3bf-0ec3-44e6-bd52-5de556f2f7a8 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
c4079f18-1e1a-40df-b140-3adcbf8a3cd4 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
affbb68e-abfd-4cd0-8311-847b0474a597 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
a9a3b0e2-7266-428f-b4b5-5a18d8cae88b | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
7777d14f-f6da-4385-a437-e56f8241a554 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
51eb688a-6040-43ca-8f5c-9e1d0f152402 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
2395bd13-6049-4d62-9371-f6a71ae5eb56 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
0a76f961-1187-4364-b614-f4136c4e5c62 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
011fdb3d-c951-4a32-9f79-0bf6e20719ef | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
d9d62337-45f1-4842-9e75-2828497afee0 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
e0fc6f4d-910b-401a-b303-6fc49c380c85 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
cd18cfd1-b975-435c-b97a-26df11cddb7e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
d7c82787-3415-4296-a1f7-c6ea3d73180f | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
fc442c7a-2fbf-4697-baa0-40f4428d2ef4 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
ee90950b-48af-46a6-9428-8f169b5d5c8e | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
190bc995-7a47-4d8b-8bc0-c7ef82381248 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
ea8b7c5f-6bd5-40a7-a81b-6d4995b974c6 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
e987f4f9-db2e-4b0e-bc85-dfc9d1490c04 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
92f0442e-a417-4958-9667-8c877e5d7921 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
85bb94f8-a5c3-466e-a765-7d91b7ab68cd | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
bdb06a02-45e9-4a9c-9f9a-6f2d6b471542 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
c23594dd-16aa-43a8-afbc-c6cbccc8a83a | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
561f8a7d-1085-49eb-9450-fdb1299f0f4a | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
3e00bbd3-243b-4eb1-a313-4e12640a95ca | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
85ea555a-b7ce-488b-96df-24a243705569 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
acbf2db0-d5ea-4df1-b4cb-78d4950758df | Pole | 0 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
cd271600-5414-4423-ac95-425a27d58550 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
cfdf8038-78e4-4b94-a381-140a991fb875 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
ef289629-0095-4247-90a8-e676f74b8c35 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
f6f1cf70-f8c3-4f98-849a-ebac0797fd16 | Pole | 2 | Distribution | 2020-04-20 | 2025-04-19 | Level 3
bccc86f7-f67a-40bf-b089-cef29c9c942e | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
65fe869f-1899-4d68-99de-af301e37f52a | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
0a3b271b-1ae3-4423-92cb-0a6551313004 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
53ad3a5b-5149-4e22-9eb1-6a7efbc43ee6 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
6a64ce17-1a36-4066-939f-33ddd4490f32 | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
45c8f5a8-5244-496e-a503-1d2fee48c9ac | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
4c23040e-31e4-45c2-8037-3a0726091cbc | Pole | 2 | Distribution | 2020-04-18 | 2025-04-17 | Level 3
424f1ca0-d53d-4289-a3fb-94a762bf16ad | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
5009dcc9-f8c7-4b1b-8499-04d3947f2d23 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
6445f9f7-a93f-4d69-ba02-057c304c9d93 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
51b29948-21e5-4747-a454-690d9129d040 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
f726b5d5-5780-4ec3-964c-9b9c75395b64 | Pole | 2 | Distribution | 2020-04-17 | 2021-04-17 | Level 2 |  | 0:00 | 0:00 |  | Pole needs to be changed out due to pole being deteriorated and stubbed.
0179ca7d-c005-4946-8475-d588b6401759 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
012e6b14-40f9-40ee-8b0b-129121bbe713 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
0768ebec-fc3b-4135-aa8b-7f5b7db41a6d | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
a9275406-a444-4867-b8be-c680679fb079 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
d2f771b4-1fd1-416c-930e-35eab0a3cbe0 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
ed429bd8-3666-413b-a956-b6a4abd3c957 | Pole | 0 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
f39a5c5a-a70d-4e74-9e85-b442019dd0e7 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
07ad58b3-fc44-4081-9527-611ef3bbea00 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3 |  | 0:00 | 0:00 |  | Pole needs replaced will not meet clearances if topped
58912729-0b81-45ae-8534-5733ae947555 | Pole | 2 | Distribution | 2020-04-17 | 2025-04-16 | Level 3
64a178e6-fa47-4970-b56e-0b49b0d1028e | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
07977cbc-9149-40e5-8bb6-4c9c151303db | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
fdcfeaab-dcdf-45be-9d3c-8ef2add63147 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
8cbf0acb-8fcb-4e4d-8525-68799c14afa4 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
d50e5640-b3e5-4ab4-8fdf-7302c89dfb3e | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 0:00 | 0:00 |  | Needs above condition
d0383438-6416-47a5-8811-fa20f6aa4877 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
ed3fe5c1-1ee2-4792-a1cf-e667c191531a | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
a902c5a5-04f6-467d-b67f-015295133382 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
babbf408-caae-4fbb-9ba5-3609e58c43ec | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
b2841180-667a-400c-b6b2-363f2826e918 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
bfe8b61c-6d2a-41cb-a337-8c60da0ca7ac | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
c1a92c54-9344-4296-94dc-9a4ee053aa85 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
c8eae61e-9f20-4bb2-b691-160e78626c9a | Pole | 0 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 0:00 | 0:00 |  | XFMR DECAL
c681123b-4b20-473d-bb7c-f7aabb18cf6f | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
7cb55b62-90bc-4884-95a2-717037cc85b3 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
8f93aa1f-caa1-4ad6-b861-67acb766ebea | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
92609d42-3a00-42d8-900a-c6f62ad88f9c | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
0b9c0fe9-444f-4135-aeef-d0a9972b32bb | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
02691da4-35fb-4a11-8ab3-ec566dc61c4b | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
1412eba2-827a-4857-94b1-f2d0421d01c4 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
151f16cc-ca70-468f-b6fd-75d085ef2813 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
1bdc8b4b-2b00-4962-90d6-94803586f065 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
3bd638bd-0190-4cb0-a3f1-7de71610b198 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
675eeff6-eabf-408b-b4ed-e399c3acd6ec | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
704f4cf0-4c90-444c-a9f8-fa3349b3dc48 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
7730be94-43b7-45fe-9656-3466337cfb17 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3 |  | 0:00 | 0:00 |  | Change to level 3. Distribution should be reframed due to heavy angle.
392be24c-9cc5-4951-81fb-c037186123e8 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
38f7296d-4930-49e1-9510-3637bf8e0be5 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
4203a1f1-8128-4901-a86e-57a0bf730038 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
457c586b-b7c7-4316-997b-efa9afe8c124 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
29507e3e-4130-4f9a-979a-fd16a2e7b536 | Pole | 2 | Distribution | 2020-04-16 | 2025-04-15 | Level 3
3a463e14-a140-4649-930a-e01b509326a5 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
4183c821-6f73-42eb-975a-c452917f9789 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
701c1854-9b5d-4972-bca6-55e4a6ad409a | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
651f1799-2533-4911-ade8-9ce983af9bf2 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
52395920-5878-4b42-b049-a1aad481cfee | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
56e11b57-691a-4697-b525-2cc9925c9d0b | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
22073d1f-54d1-4363-9d87-5f5e4bb7bc4a | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | 0:00 | 0:00 |  | Pole area is submerged in water
21f6294c-a614-43cb-853c-c50f5feb2c30 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
1afb34f5-1250-4ae9-908e-30b3de598bc4 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
0883ebcb-778e-44b3-b8b4-6c1767d019ef | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
9e962665-bc94-4dd2-9062-556c722c2b2c | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
efbc38ed-2ccd-4eb4-ba72-58c241ef9ce0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
f403f7f3-2caa-4773-bc8e-bb19cbcf21fa | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
c9c4fa62-81b0-4bdb-a049-43ab274bcbc1 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
ad618fb7-6e8e-4ed1-bcf1-d07152b9feb1 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
a17b8d85-c010-434f-b6ff-a6ee5981aab0 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
c3f13bc3-e395-4f25-ba97-44eb49f3e65e | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
ba9b80e0-fd27-4a50-b92b-8b9fc34dad35 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
bcb0f141-d8b6-4ed2-a4ab-d0ef12527dd5 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
d74dbdce-fd34-4113-9f24-df16414b3790 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
08c02c81-3d3e-4674-8fac-2048684dea52 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
09e9fa0f-ac47-4a92-8f47-a4bcebc5db54 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
0ea06e49-19a9-4e6e-9453-2efc22b69a8c | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3 |  | 0:00 | 0:00 |  | Loose down guy, needs to be brought to tension
047f3f3e-6600-42a1-8dda-fca0b5418a66 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
04b22eaa-9f6a-4001-b5dc-dc2d078007bf | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
6400e8f5-4426-4f53-96de-d236cbb046e4 | Pole | 0 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
3f8e7a84-5a1c-4b8c-be93-c7602a4dc1d0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
3d8f4f08-f0e6-4a49-8880-c43fa308a8e0 | Pole | 2 | Distribution | 2020-04-15 | 2025-04-14 | Level 3
27f273a9-f0c9-40a4-b1f5-7e56beb88eda | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
186ec59a-27b4-4a1f-8ee5-e2dcbc4a1842 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
e04d5835-06c4-4f71-a0bc-6ba9b71ed739 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
e2ea30de-0167-4acf-824d-93858c3813b0 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
e4959f03-aef9-4718-a6c3-cc1e1ab788a8 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
f612475f-7fa3-4094-8d19-1f42cc4f7a5a | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
c8131cc2-3a08-42bf-b7d8-1708276012ea | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
0285bc85-5e14-4320-9904-1823aa2376a3 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
621cd443-057c-44a9-986d-8f806b7066ef | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
14e549d8-7961-4a7b-9094-1f8e3fcfe401 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
77b1ed33-c2ab-4598-91cb-4058d358df04 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
93655288-925f-4af3-9414-7c432241a9b6 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
be24cfc1-08ac-4c05-9d6f-9ef610d15aab | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
0afe3999-0f69-4626-a966-c0ceaa8b79c7 | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
0df54f4d-f917-4074-80a7-4da7e13d0a8e | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
fd1f5200-6859-4d8e-bea4-ed4554ecbb5a | Pole | 2 | Distribution | 2020-04-14 | 2025-04-13 | Level 3
062e61ae-866b-4c65-a751-787bd12ba3bd | Pole | 2 | Distribution | 2020-04-13 | 2025-04-12 | Level 3
ab7d95b8-417a-4a70-840f-e6c409a19c16 | Pole | 2 | Distribution | 2020-04-13 | 2025-04-12 | Level 3
0b83e500-030d-4ded-a4db-62533d2ece14 | Pole | 2 | Distribution | 2020-04-13 | 2021-04-13 | Level 2 |  | 0:00 | 0:00 |  | Needs changed out
6ef80bad-a949-4aaa-93a4-ce252d210ff9 | Pole | 2 | Distribution | 2020-04-10 | 2025-04-09 | Level 3

## Table 14
Utility | Liberty Utilities
Table No. | 14
Date Modified
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Non-HFTD Distribution
HFTD 2 Distribution
HFTD 3 Distribution
Non-HFTD Transmission
HFTD 2 Transmission
HFTD 3 Transmission

## Table 15
Utility | Liberty Utilities
Table No. | 15
Date Modified | 2023-05-01
Table 15: Top Risk Circuit Scores
*EC to add all other risk categories to right of last required category.
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
TPZ1261 |  | Primary | 83.9991 |  |  | 0.0023407 | 0.0022756 | 6.5057e-05
MULLER1296 |  | Primary | 78.188 |  |  | 0.00037423 | 0.00032853 | 4.5698e-05
MEY3400 |  | Primary | 143.647 |  |  | 0.00032986 | 0.00011523 | 0.00021463
TAH7300 |  | Primary | 190.8235 |  |  | 0.00027109 | 6.7424e-05 | 0.00020367
GLS7400 |  | Primary | 79.0224 |  |  | 0.00020004 | 0.00017586 | 2.417e-05
MEY3300 |  | Primary | 162.5108 |  |  | 0.00018587 | 8.1725e-05 | 0.00010415
STL3101 |  | Primary | 59.3724 |  |  | 0.00015508 | 1.2751e-05 | 0.00014233
POR31 |  | Primary | 31.9075 |  |  | 0.00014488 | 0.00014488 | 0
SQV8200 |  | Primary | 27.9706 |  |  | 8.5557e-05 | 8.393e-05 | 1.6267e-06
SQV7201 |  | Primary | 36.7944 |  |  | 8.1156e-05 | 5.9518e-05 | 2.1638e-05
608 |  | Primary | 17.3219 |  |  | 7.8716e-05 | 7.8715e-05 | 1.3e-09
MEY3200 |  | Primary | 116.2371 |  |  | 7.3462e-05 | 1.6879e-05 | 5.6583e-05
MEY3100 |  | Primary | 64.7987 |  |  | 7.2541e-05 | 1.6319e-05 | 5.6223e-05
STL3501 |  | Primary | 60.6142 |  |  | 6.3584e-05 | 3.0216e-06 | 6.0562e-05
TAH7100 |  | Primary | 59.2746 |  |  | 6.2619e-05 | 1.4548e-05 | 4.8071e-05
MEY3500 |  | Primary | 114.952 |  |  | 5.4543e-05 | 2.6597e-05 | 2.7946e-05
CAL204 |  | Primary | 7.0932 |  |  | 5.331e-05 | 5.331e-05 | 0
POR32 |  | Primary | 55.1117 |  |  | 5.0969e-05 | 5.0969e-05 | 0
TRK7204 |  | Primary | 8.9823 |  |  | 4.0907e-05 | 4.0907e-05 | 0
SRB51 |  | Primary | 14.3662 |  |  | 3.4184e-05 | 3.4184e-05 | 0