## Cover Sheet Tables 1-15
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines, Appendix D
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | BVES
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2024
Reporting Period quarter |  | Q2 |  | Q1 | 2023
Date Modified |  | 2024-08-01 |  | Q2 | 2024
|  |  |  | Q3 | 2025
Q4

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitiativeObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
BV | 2023-05-01 | Program |  |  | Public outreach and education awareness program | Development and deployment of public outreach and education awareness program(s) for wildfires; outages due to wildfires, PSPS events, and protective equipment and device settings; service restoration before, during, and after the incidents and vegetation management. | Development and deployment of public outreach and education awareness program(s) for wildfires; outages due to wildfires, PSPS events, and protective equipment and device settings; service restoration before, during, and after the incidents and vegetation management. | Community Outreach and Engagement | 8.5.2 | Public outreach and education awareness program |  | 8.5.2 | COE_1 | BV_Community Outreach and Engagement_Public outreach and education awareness program_COE_1_ | TBD | PSPS Vulnerability | No | Number of Public Outreach and Education Events | 360 | 90 | 180 | 270 | 360 | 244 | 496 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Engagement with access and functional needs populations | Actions taken understand, evaluate, design, and implement wildfire and PSPS risk mitigation strategies, policies, and procedures specific to access and functional needs customers. | Actions taken understand, evaluate, design, and implement wildfire and PSPS risk mitigation strategies, policies, and procedures specific to access and functional needs customers. | Community Outreach and Engagement | 8.5.3 | Engagement with access and functional needs populations |  | 8.5.3 | COE_2 | BV_Community Outreach and Engagement_Engagement with access and functional needs populations_COE_2_ | TBD | PSPS Vulnerability | No | AFN Customer Needs Verifications | 12 | 3 | 6 | 9 | 12 | 6 | 12 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Collaboration on local wildfire mitigation planning | Development and integration of plans, programs, and/or policies for collaborating with communities on local wildfire mitigation planning, such as wildfire safety elements in general plans, community wildfire protection plans, and local multi-hazard mitigation plans. | Development and integration of plans, programs, and/or policies for collaborating with communities on local wildfire mitigation planning, such as wildfire safety elements in general plans, community wildfire protection plans, and local multi-hazard mitigation plans. | Community Outreach and Engagement | 8.5.4 | Collaboration on local wildfire mitigation planning |  | 8.5.4 | COE_3 | BV_Community Outreach and Engagement_Collaboration on local wildfire mitigation planning_COE_3_ | TBD | Wildfire Hazard | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Engage with Local Support (Fire Department & Forestry Service) on project statuses and other items | Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Best practice sharing with other utilities | Development and integration of an electrical corporation’s policy for sharing best practices and collaborating with other electrical corporations on technical and programmatic aspects of its WMP program. | Development and integration of an electrical corporation’s policy for sharing best practices and collaborating with other electrical corporations on technical and programmatic aspects of its WMP program. | Community Outreach and Engagement | 8.5.5 | Best practice sharing with other utilities |  | 8.5.5 | COE_4 | BV_Community Outreach and Engagement_Best practice sharing with other utilities_COE_4_ | TBD | Wildfire Hazard | No | Working Groups, Conferences | 15 | 4 | 8 | 12 | 15 | 23 | 56 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Emergency preparedness plan | Development and integration of wildfire- and PSPS-specific emergency strategies, practices, policies, and procedures into the electrical corporation’s overall emergency plan based on the minimum standards described in GO 166. | Development and integration of wildfire- and PSPS-specific emergency strategies, practices, policies, and procedures into the electrical corporation’s overall emergency plan based on the minimum standards described in GO 166. | Emergency Preparedness | 8.4.2 | Emergency preparedness plan |  | 8.4.2 | EP_1 | BV_Emergency Preparedness_Emergency preparedness plan_EP_1_ | TBD | Wildfire Vulnerability | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Evaluate Emergency Plan | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | External collaboration and coordination | Actions taken to coordinate wildfire and PSPS emergency preparedness with relevant public safety partners including the state, cities, counties, and tribes. | Actions taken to coordinate wildfire and PSPS emergency preparedness with relevant public safety partners including the state, cities, counties, and tribes. | Emergency Preparedness | 8.4.3 | External collaboration and coordination |  | 8.4.3 | EP_2 | BV_Emergency Preparedness_External collaboration and coordination_EP_2_ | TBD | Wildfire Vulnerability | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Meetings with Community Partners and Mutual Aid Groups | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Public emergency communication strategy | Development and integration of a comprehensive communication strategy to inform essential customers and other stakeholder groups of wildfires, outages due to wildfires, and PSPS and service restoration, as required by Public Utilities Code section 768.6. | Development and integration of a comprehensive communication strategy to inform essential customers and other stakeholder groups of wildfires, outages due to wildfires, and PSPS and service restoration, as required by Public Utilities Code section 768.6. | Emergency Preparedness | 8.4.4 | Public emergency communication strategy |  | 8.4.4 | EP_3 | BV_Emergency Preparedness_Public emergency communication strategy_EP_3_ | TBD | Wildfire Vulnerability | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Preparedness and planning for service restoration | Development and integration of the electrical corporation’s plan to restore service after an outage due to a wildfire or PSPS event. | Development and integration of the electrical corporation’s plan to restore service after an outage due to a wildfire or PSPS event. | Emergency Preparedness | 8.4.5 | Preparedness and planning for service restoration |  | 8.4.5 | EP_4 | BV_Emergency Preparedness_Preparedness and planning for service restoration_EP_4_ | TBD | Wildfire Vulnerability | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Opoerations Group | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Customer support in wildfire and PSPS emergencies | Development and deployment of programs, systems, and protocols to support residential and non- residential customers in wildfire emergencies and PSPS events. | Development and deployment of programs, systems, and protocols to support residential and non- residential customers in wildfire emergencies and PSPS events. | Emergency Preparedness | 8.4.6 | Customer support in wildfire and PSPS emergencies |  | 8.4.6 | EP_5 | BV_Emergency Preparedness_Customer support in wildfire and PSPS emergencies_EP_5_ | TBD | Wildfire Vulnerability | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Covered Conductor Replacement Project | BVES plans to cover all overhead bare sub-transmission lines (34.5 kV) in the High Fire-Threat District (HFTD) Tiers 2 and 3 covering approximately 4.3 circuit miles per year. This action will result in the entire 34.5 kV system in the HFTD being underground or covered; thereby, reducing the risk of sub-transmission lines contacting vegetation or other debris and causing an ignition to near zero. BVES also plans to cover all overhead bare distribution lines (4 kV) in the High Fire-Threat District (HFTD) Tiers 2 and 3 over a 20-year period. The focus of the first 10 years of the project are the highest risk areas and will result in covering approximately 8.6 circuit miles per year. This action will eventually result in the entire 4 kV system in the HFTD being underground or covered; thereby, reducing the risk of distribution lines contacting vegetation or other debris and causing an ignition to near zero. | Installation of covered or insulated conductors to replace standard bare or unprotected conductors (defined in accordance with GO 95 as supply conductors, including but not limited to lead wires, not enclosed in a grounded metal pole or not covered by: a “suitable protective covering” (in accordance with Rule 22.8), grounded metal conduit, or grounded metal sheath or shield). In accordance with GO 95, conductor is defined as a material suitable for: (1) carrying electric current, usually in the form of a wire, cable or bus bar, or (2) transmitting light in the case of fiber optics; insulated conductors as those which are surrounded by an insulating material (in accordance with Rule 21.6), the dielectric strength of which is sufficient to withstand the maximum difference of potential at normal operating voltages of the circuit without breakdown or puncture; and suitable protective covering as a covering of wood or other non-conductive material having the electrical insulating efficiency (12kV/in. dry) and impact strength (20ft.-lbs) of 1.5 inches of redwood or other material meeting the requirements of Rule 22.8-A, 22.8-B, 22.8-C or 22.8-D. | Grid Design, Operations, and Maintenance | 8.1.2.1 | Covered conductor installation |  | 8.1.2.1 | GD_1 | BV_Grid Design, Operations, and Maintenance_Covered conductor installation_GD_1_44927 | TBD | Contact from vegetation ignition likelihood | No | Circuit Miles of Line Replaced | 12.9 | 0 | 2.5 | 7 | 12.9 | 1.34 | 7.18 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | Bear Valley Solar Energy Project | BVES proposes an Energy Storage (seperate project) and Solar Generating Facility Project that are designed to reduce the likelihood and consequences of disruptive events and provide many of the benefits outlined the Grid Resilience and Innovation Partnerships (GRIP) program. The proposed projects enhance safety, reliability and quality of service. The projects are designed to significantly mitigate the potential of ignitions by removing the need to expand sub-transmission supply lines to Bear Valley’s service area, which may cause wildfires with catastrophic loss of life and enormous loss of property. These projects significantly reduce the need for Public Safety Power Shut-off (PSPS) and the impact of Southern California Edison (SCE) initiating a PSPS event affecting the supply lines to Bear Valley. BVES proposes to construct the Bear Valley Solar Energy Project (BVSEP), 5 MW alternating current single-axis tracker solar generation facility, to be constructed on a 21-acre site within the BVES service territory. This system will directly feed the distribution system benefiting all customers. One of the purposes of the solar energy project is to minimize the impact of the loss of all SCE energy imports to the BVES service area due to a SCE-directed PSPS of the SCE supply lines to BVES. BVES energy imports from SCE are subject to PSPS and while these lines may be required to be de-energized by SCE, the BVES service area may not require PSPS. This project will be submitted to the CPUC and the County of San Bernardino in 2023. If the proposed project is approved it will allow BVES to internally supply energy to most of its customers by utilizing its existing peaking power plant (8.4 MW), along with the BVSEP and the energy storage battery to minimize the effects of any PSPS event. | Development and deployment of microgrids that may reduce the risk of ignition, risk from PSPS, and wildfire consequence. “Microgrid” is defined by Public Utilities Code section 8370(d). | Grid Design, Operations, and Maintenance | 8.1.2.7 | Microgrids |  | 8.1.2.7 | GD_10 | BV_Grid Design, Operations, and Maintenance_Microgrids_GD_10_45292 | TBD | PSPS Exposure Potential | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Preform Necessary Project Action | N/A | N/A | N/A | N/A | Program Not Started in 2023 | N/A
BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | Energy Storage Project | BVES proposes an Energy Storage and Solar Generating Facility Project (seperate project) that are designed to reduce the likelihood and consequences of disruptive events and provide many of the benefits outlined the Grid Resilience and Innovation Partnerships (GRIP) program. The proposed projects enhance safety, reliability and quality of service. The projects are designed to significantly mitigate the potential of ignitions by removing the need to expand sub-transmission supply lines to Bear Valley’s service area, which may cause wildfires with catastrophic loss of life and enormous loss of property. These projects significantly reduce the need for Public Safety Power Shut-off (PSPS) and the impact of Southern California Edison (SCE) initiating a PSPS event affecting the supply lines to Bear Valley. BVES proposes to construct an energy storage project of approximately 5 MW/20 MWh (four-hour) Lithium-Ion NMC utility-grade battery located in the BVES maintenance yard. This project will complement the Bear Valley Solar Energy Project (BVSEP), 5 MW alternating current single-axis tracker solar generation facility, to be constructed on a 21-acre site within the BVES service territory. This system will directly feed the distribution system benefiting all customers. One of the purposes of the storage project is to minimize the impact of the loss of all SCE energy imports to the BVES service area due to a SCE-directed PSPS of the SCE supply lines to BVES. BVES energy imports from SCE are subject to PSPS and while these lines may be required to be de-energized by SCE, the BVES service area may not require PSPS. The project will be submitted to the CPUC and the County of San Bernardino in 2023. If the project is approved it will allow BVES to internally supply energy to most of its customers by utilizing its existing peaking power plant (8.4 MW), along with the BVSEP and the energy storage battery to minimize the effects of any PSPS event. | Development and deployment of microgrids that may reduce the risk of ignition, risk from PSPS, and wildfire consequence. “Microgrid” is defined by Public Utilities Code section 8370(d). | Grid Design, Operations, and Maintenance | 8.1.2.7 | Microgrids |  | 8.1.2.7 | GD_11 | BV_Grid Design, Operations, and Maintenance_Microgrids_GD_11_45292 | TBD | PSPS Exposure Potential | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Preform Necessary Project Action | N/A | N/A | N/A | N/A | Program Not Started in 2023 | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Substation Automation | The project aims to connect 9 substations to Bear Valley’s SCADA network in order to allow remote real-time monitoring, reporting, and documenting key substation parameters over 3 years. The project involves the following elements: installing SCADA enabled control equipment, enhancing telemetry, and creating the capability to collect and modify settings remotely. This project will establish a robust and secure IP communications network across the distribution system to fully enable monitoring and control of critical equipment at the substations throughout the distribution system. Critical switches at substations will be automated and connected to SCADA in a phased approach. Connectivity to SCADA will be via the BVES service area fiber optic network. Additionally, sensors will be placed throughout the substations to continuously monitor volt-ampere reactive (VAR) performance and power quality. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | 8.1.2.8 | Installation of system automation equipment |  | 8.1.2.8 | GD_12 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_12_44927 | TBD | Equipment ignition likelihood | No | Number of Substations Automated and Connected to SCADA | 3 | 0 | 1 | 2 | 3 | 0 | 1 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Switch and Field Device Automation | This project aims to automate and connect to Bear Valley’s SCADA network 28 sub-transmission (34 kV) switches and distribution switches over the next 4 years (2023 to 2026) in order to allow remote real-time monitoring, reporting, and documenting key 16 switch parameters and enable remote operation of the switches. The project involves the following elements: installing SCADA enabled control equipment, enhancing telemetry, and creating the capability to collect and modify settings remotely. This project will establish a robust and secure IP communications network across the sub-transmission and distribution systems to fully enable monitoring and control of critical switches throughout the sub-transmission and distribution systems. Critical switches in the system will be automated and connected to SCADA in a phased approach. Connectivity to SCADA will be via the BVES service area fiber optic network and in some cases via radio/cellular data transfer equipment. This project will mitigate and/or reduce PSPS events in terms of geographic scope and number of customers affected not covered by another initiative. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | 8.1.2.8 | Installation of system automation equipment |  | 8.1.2.8 | GD_13 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_13_44927 | TBD | Equipment ignition likelihood | No | Number of Field Switches Automated and Connected to SCADA | 10 | 0 | 5 | 10 | 10 | 0 | 2 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Capacitor Bank Upgrade Project | The Capacitor Bank Upgrade Project aims to replace 24 aging capacitor banks from 2023 – 2026 with updated SCADA enabled capacitor banks. 23 of the capacitor banks are overhead type and 1 is underground pad mounted type. The existing capacitor banks are manually operated units, are nearing the end of their useful life (all greater than 40 years old), and are showing the telltale signs of near-term failure both in electronic performance and structurally, which may lead to the potential for fire and explosion hazards (catastrophic failure). The project will study the locations to ensure that they are optimal for providing the necessary voltage support and control in the distribution system such that customers receive the proper voltage at their connecting points. The capacitors will be replaced with 450KVAR 3Phase units that are fully capable of being connected to SCADA for remote control and monitoring. Connectivity to SCADA will be via radio/cellular data transfer equipment and the BVES service area fiber optic network. This will allow Bear Valley to control voltage by placing or removing the capacitor banks from service as needed without having to send a crew to manually operate the capacitor banks. Additionally, the capacitor banks will be continuously monitored to ensure the banks do not overheat or have excessive voltage which may lead to catastrophic failure. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | 8.1.2.8 | Installation of system automation equipment |  | 8.1.2.8 | GD_14 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_14_44927 | TBD | Equipment ignition likelihood | No | Number of Capacitor Banks Replaced and Connected to SCADA | 6 | 0 | 1 | 6 | 6 | 0 | 1 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Fuse TripSaver Automation | This project aims to connect and automate 160 Fuse TripSaver®’s to Bear Valley’s SCADA network over 4 years. A Fuse TripSaver is a device used in lieu of fuse cutouts on laterals, feeders, or circuit sections. The TripSaver improves system reliability by eliminating the permanent outages caused when lateral fuses respond to temporary faults. When the device is in “automatic” mode, the device keeps the power on and avoids truck rolls since power is restored automatically for transient faults similar to the way a re-closer would restore power. During high fire threat weather, the TripSavers are placed in “manual”; such that when a fault is detected, the device drops out and requires crew response similar to conventional fuses. Unlike a conventional fuse, there is no expulsion of metal slag that could cause an ignition. The advantage of the TripSaver is that in addition to having an “automatic re-close” or “manual” one shot mode of operation, it is programmable with various selectable protection curves (time vs. current curves) and it will behave like a conventional fuse. The setting may be optimized for reliability during a storm or ignition prevention during high fire threat weather. By connecting the TripSavers to the SCADA network, they can be monitored and operators would be alerted when a TripSaver actuates on fault. This provides prompt notification of a potential fault and ignition as well as localizing information; thereby, vastly improving response times. Additionally, by connecting the TripSavers to the SCADA network, they can be remotely programmed allowing the utility to rapidly optimize the TripSavers for fire prevention during high fire threat weather. Currently, Bear Valley crews must drive to each TripSaver and change their program operation, which takes several days. Therefore, Bear Valley operates the TripSavers in “manual” one-shot mode from April to November/December depending on the weather outlook. This project will establish a robust and secure IP communications network across the sub-transmission and distribution systems to fully enable monitoring of the TripSavers. Connectivity to SCADA will be via the BVES service area fiber optic network and via radio/cellular data transfer equipment. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | 8.1.2.8 | Installation of system automation equipment |  | 8.1.2.8 | GD_15 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_15_44927 | TBD | Equipment ignition likelihood | No | Number of Fuse TripSavers Automated and Connected to SCADA | 50 | 0 | 16 | 41 | 50 | 0 | 11 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2024-01-01 | Server Room | The Server Room Project is designed to expand, upgrade, and improve security and reliability of the current computer server room capabilities. In the past four years, Bear Valley has installed a fiber network in the BVES service area, began automating substations and certain field devices, installed a server-based circuit metering system, migrated the Bear Valley Power Plant control system to Bear Valley’s current SCADA software application, and fully developed a GIS database with asset and inspection applications that fully support data schema requirements directed by the Office of Energy Infrastructure Safety (OEIS). Looking ahead, it is clear that Bear Valley will need to continue to significantly expand the automation of substations and field devices, eventually install Advanced Metering Infrastructure (AMI), and grow the GIS database and associated applications. The current server room is becoming inadequate and will eventually not be able to support the ever-growing information technology (IT) systems. The Server Room is currently 10 feet by 4.9 feet (47.5 square feet). This project will enlarge it to 10 feet by 9 feet (180 square feet) and install a properly rated and redundant environmental control system to ensure system safety and reliability. According to North American Electric Reliability Corporation (NERC) standards and best practices for industrial control systems, the SCADA system is required to operate independently from the other server racks. This requirement necessitates the enlargement of the current Server Room. This upgrade also allows for future expansion on the server racks. This project includes the design and installation of the servers for the SCADA system. The Server Room Project is a component of the significant grid automation efforts taken to date and being planned, which will enable Bear Valley to provide safer, more reliable, more resilient, and higher quality service to its customers and the communities it serves. In order to achieve Bear Valley’s grid automation goals, it is essential to install a robust and secure server room for the Internet Protocol (IP) network and SCADA system. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | 8.1.2.8 | Installation of system automation equipment |  | 8.1.2.8 | GD_16 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_16_44927 | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Project Milestones for Server Insillation | Quarterly Target Met | Quarterly Target Met | Quarterly Target Met | Yearly Target Met | Ongoing | N/A
BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | Distribution Management Center | The Distribution Management Center Project is intended to establish a control room to interface with the applications designed to monitor and control the entire sub-transmission and distribution network efficiently and reliably. Improving the safety, reliability, resiliency and quality of service in terms of mitigating ignitions, preventing wildfires, reducing outages, minimizing outage time, maintaining acceptable frequency and voltage levels are the key deliverables of the Distribution Management Center. The project specifically establishes a small two operator control room located adjacent to Bear Valley’s Emergency Operations Center equipped with the following capabilities: (1) Monitor and operate the SCADA system; (2) Monitor the Outage Management System; (3) Monitor Bear Valley’s network of weather stations; (4) Access the Customer Information System (CIS) as needed; (5) Monitor Geographical Information System (GIS) applications as applicable; (6) Monitor security systems installed to provide physical security; (7) Update the Interactive Voice Response System (IVRS), TextPower system, and Bear Valley’s website and social media; (8) Communicate with Management, Field Operations crews, key stakeholders, and customers; and (9) When installed, monitor and operate the AMI system. In the past four years, Bear Valley has installed a fiber network in the BVES service area, began automating substations and certain field devices, installed a server-based circuit metering system, migrated the Bear Valley Power Plant control system to Bear Valley’s current SCADA software application, and fully developed a GIS database with asset and inspection applications that fully support data schema requirements directed by the Office of Energy Infrastructure Safety (OEIS). Looking ahead, it is clear that Bear Valley will need to continue to significantly expand the automation substations and field devices, eventually install AMI, and grow the GIS database and associated applications. Therefore, establishing a control room to access, process, and act upon the information provided by these information technology (IT) systems is an important component necessary to truly reap their benefit. Bear Valley currently does not have a single control room to provide the situational awareness in one location that these systems offer. Currently, staff access these applications at specific controlled locations as in the case of SCADA and through various other devices such as desktop computers, workbooks and other mobile devices. | Installation of electric equipment that increases the ability of the electrical corporation to automate system operation and monitoring, including equipment that can be adjusted remotely such as automatic reclosers (switching devices designed to detect and interrupt momentary faults that can reclose automatically and detect if a fault remains, remaining open if so). | Grid Design, Operations, and Maintenance | 8.1.2.8 | Installation of system automation equipment |  | 8.1.2.8 | GD_17 | BV_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GD_17_45292 | TBD | Wildfire Exposure Potential | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Project Milestones for Distribution Management Center | N/A | N/A | N/A | N/A | Program Not Started in 2023 | N/A
BV | 2023-05-01 |  |  |  | Line removals (in HFTD) | BVES does not have any line removel projects planned. | Removal of overhead lines to minimize the risk of ignition due to the design, location, or configuration of electric equipment in HFTDs. | Grid Design, Operations, and Maintenance | 8.1.2.9 | Line removals (in HFTD) |  | 8.1.2.9 | GD_18 | BV_Grid Design, Operations, and Maintenance_Line removals (in HFTD)_GD_18_ | TBD | NA | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Tree Attachment Removal Project | This project is dedicated to the removal of existing distribution line tree attachments in BVES’s distribution system and it includes costs for replacing tree attachments with poles as necessary to safely and reliably route distribution lines and service lines to customers. BVES has been proactively removing tree attachments, which will improve system reliability and safety and reduce potential fire hazards. Since 2018 when this initiative started, BVES removed 642 tree attachments and has 565 tree attachments remaining in the system. | Actions taken to minimize the risk of ignition due to the design, location, or configuration of electric equipment in HFTDs not covered by another initiative. | Grid Design, Operations, and Maintenance | 8.1.2.10 | Other grid topology improvements to minimize risk of ignitions |  | 8.1.2.10 | GD_19 | BV_Grid Design, Operations, and Maintenance_Other grid topology improvements to minimize risk of ignitions_GD_19_44927 | TBD | Contact from vegetation ignition likelihood | No | Number of Tree Attachments Removed | 100 | 0 | 30 | 50 | 100 | 51 | 84 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2024-01-01 | Radford Line Replacement Project | BVES plans to replace bare wire with a high-performance covered conductor on the Radford 34kV sub-transmission line. This line was selected specifically since it has the highest risk of wildfires (High Fire Threat District Tier 3). The line is located in a densely vegetated area that is difficult to patrol, so BVES believes that replacing the line completely will provide the greatest protection. | Installation of covered or insulated conductors to replace standard bare or unprotected conductors (defined in accordance with GO 95 as supply conductors, including but not limited to lead wires, not enclosed in a grounded metal pole or not covered by: a “suitable protective covering” (in accordance with Rule 22.8), grounded metal conduit, or grounded metal sheath or shield). In accordance with GO 95, conductor is defined as a material suitable for: (1) carrying electric current, usually in the form of a wire, cable or bus bar, or (2) transmitting light in the case of fiber optics; insulated conductors as those which are surrounded by an insulating material (in accordance with Rule 21.6), the dielectric strength of which is sufficient to withstand the maximum difference of potential at normal operating voltages of the circuit without breakdown or puncture; and suitable protective covering as a covering of wood or other non-conductive material having the electrical insulating efficiency (12kV/in. dry) and impact strength (20ft.-lbs) of 1.5 inches of redwood or other material meeting the requirements of Rule 22.8-A, 22.8-B, 22.8-C or 22.8-D. | Grid Design, Operations, and Maintenance | 8.1.2.1 | Covered conductor installation |  | 8.1.2.1 | GD_2 | BV_Grid Design, Operations, and Maintenance_Covered conductor installation_GD_2_44927 | TBD | Contact from vegetation ignition likelihood | No | Circuit Miles of Line Replaced | 2.7 | 0 | 0 | 1 | 2.7 | 0 | 0.75 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 |  |  |  | Other grid topology improvements to mitigate or reduce PSPS events | The objectives of this initiative are achieved through BVES's installation of system automation equipment initiatives. | Actions taken to mitigate or reduce PSPS events in terms of geographic scope and number of customers affected not covered by another initiative. | Grid Design, Operations, and Maintenance | 8.1.2.11 | Other grid topology improvements to mitigate or reduce PSPS events |  | 8.1.2.11 | GD_20 | BV_Grid Design, Operations, and Maintenance_Other grid topology improvements to mitigate or reduce PSPS events_GD_20_ | TBD | NA | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | BVPP Phase 4 Upgrade Project | The BVPP Reliability Upgrades Project is aimed at reducing the impacts of power outages from proactive de-energization and preserving essential services by improving the reliability of the BVPP. The project includes installing updated engine controls on all seven natural gas engines to a current controls system that will allow efficient start/stop functions, consolidated controls, and synchronization monitoring. Also, the project replaces the Detonation Sensing Module (DSM) Controls on all engines with a detonation controller (DetCon) system that will allow for visual DSM monitoring. DSM modules will also be wired to prevent any fire hazards or failure. Lastly, the project is scheduled to replace the governor speed control systems on all engines with a ProActTM engine speed control system and an EX Gen excitation control system. This upgraded system will be used to fine tune emissions, allow monitoring on the engine control unit, and eliminate all mechanical linkage. The proposed upgrade package is designed to provide improved performance through modifications which translate into better response, lower emissions, reduced downtime, maintenance costs savings, and single source control over the engine and emissions system performance. | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design, Operations, and Maintenance | 8.1.2.12 | Other technologies and systems not listed above |  | 8.1.2.12 | GD_21 | BV_Grid Design, Operations, and Maintenance_Other technologies and systems not listed above_GD_21_45292 | TBD | PSPS Exposure Potential | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Project Milesstones for Propane Engine Upgrades | N/A | N/A | N/A | N/A | Program Not Started in 2023 | N/A
BV | 2023-05-01 | Project | 2024-01-01 | 2025-01-01 | Partial Safety and Technical Upgrades to Maltby Substation | This project replaces overhead regulators with pad mounted regulators, installs pad mounted IntelliRupter switches, converts substation to be fully underground and updates substation controls. The substation is located in one of the more densely populated residential areas of Big Bear City on the East end of the BVES service area. This two 3.75 MVA transformer substation converts 34.5 kV sub-transmission to two 4.160 kV distribution circuits (Paradise and Erwin Lake circuits). These circuits also provide power to small businesses in the area. These circuits are located in high wind areas. The IntelliRupter switches will significantly (1) Improve the ability of the circuits to be rapidly de-energized when fault conditions are detected. (2) The IntelliRupter when in automatic mode will test at approximately 10% power when a fault is detected, thereby significantly reducing the possibility of causing an ignition. The equipment will be SCADA enabled with remote monitoring and operation capability. The regulators and switches at Maltby Substation are aged and approaching their maximum useful life which makes the equipment more prone to failure and requires costly heightened monitoring and maintenance. Maintaining compliance with GO-174 standards has also been very difficult and costly. As substation equipment further ages, catastrophic failure of the equipment is more likely. Such a failure could potentially cause an ignition event that could lead to a wildfire. Maltby Substation was partially upgraded in 2012 resulting in the feeds on both the sub-transmission and distribution sides being undergrounded and the transformers being pad mounted. The re-closers and regulators are of the overhead design. This project would complete the conversion of the substation to be completely underground with pad mounted equipment. At the completion of the project there would be no exposed bare wire or bus work. The Maltby Substation is heavily loaded making voltage regulation an important issue. The aging regulators are struggling to maintain proper voltage and will need to be replaced. There are safety concerns with the exposed wiring configuration at the substation. These concerns are reduced through increased worker protections, including additional personal protective equipment, additional protective covers, increased safety processes and enhanced safety reviews and briefing prior to entering the substation. These enhanced safety precautions are costly but are necessary to reduce the potential safety exposure to workers and the public. The heightened but costly safety measures are not acceptable as a long-term solution to the safety concerns that exist at the substation. | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design, Operations, and Maintenance | 8.1.2.12 | Other technologies and systems not listed above |  | 8.1.2.12 | GD_22 | BV_Grid Design, Operations, and Maintenance_Other technologies and systems not listed above_GD_22_45292 | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Project Milesstones for Maltby Substation | N/A | N/A | N/A | N/A | Program Not Started in 2023 | N/A
BV | 2023-05-01 | Project | 2025-01-01 | 2026-01-01 | Safety and Technical Upgrades to Lake Substation | The existing Lake Substation is to be converted from an overhead-type to an underground pad-mounted design. This single 2.0 MVA transformer substation converts 34.5 kV sub-transmission to one 4.160 kV distribution circuit (Pump House circuit). The project will improve the safety, reliability and efficiency of the substation by eliminating a wiring configuration that is a potential safety issue, and replacing all aged substation equipment with more efficient and enclosed pad mount transformers, voltage regulators, circuit re-closers, and bus work. The transformation capability would be increased to 5 MVA to accommodate load growth and allow the Pump House circuit to pick up other circuits’ loads for maintenance considerations and during faulted conditions, to improve system reliability and resiliency. The equipment will be SCADA enabled with remote monitoring and operation capability. Advanced metering will be installed to provide real-time, high-quality circuit load data as well as reliability data. The transformer in the Lake Substation is approaching its maximum useful life. In the event of a major transformer failure at the Lake Substation, Bear Valley would not be able to restore the substation until a new or refurbished transformer is procured and delivered, which at a minimum would take a week but more likely several weeks due to supply chain issues and the logistics of trucking such a transformer up the mountain roads to Big Bear Lake. The substation equipment is over 33 years old, which makes the equipment more prone to failure and requiring costly, heightened monitoring and maintenance. Maintaining compliance with GO-174 standards has been very difficult and costly. As substation equipment further ages, catastrophic failure of the equipment is more likely. Such a failure could potentially cause an ignition event that could lead to a wildfire. Replacing the substation would also permit BVES to improve and strengthen the existing oil spill prevention systems. This should avoid increases in the ongoing maintenance costs of complying with the San Bernardino County Fire Department and the Environmental Protection Agency’s requirements regarding oil spill prevention and countermeasures. The substation is located less than 1,000 ft. from Big Bear Lake and therefore, a catastrophic failure of oil-filled equipment (transformer, regulator, and circuit breaker) may pose a threat of contaminating the lake. The Lake Substation is heavily loaded. Circuit loads are often at a high load condition, which makes the likelihood of a circuit trip very likely due to even small current spikes. Circuit trips reduce reliability of service. Additionally, due to load limitations, combining other circuits with circuits originating from this substation is not feasible except during the summer months when load is reduced. Being so heavily loaded reduces overall service reliability in the event of unplanned outages. It also increases maintenance costs because it limits the flexibility of planned maintenance activities. There are safety concerns with the exposed wiring configuration at the substation. These concerns are reduced through increased worker protections, including additional personal protective equipment, additional protective covers, increased safety processes and enhanced safety reviews and briefing prior to entering the substation. These enhanced safety precautions are costly but are necessary to reduce the potential safety exposure to workers and the public. The heightened but costly safety measures are not acceptable as a long-term solution to the safety concerns that exist at the station. | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design, Operations, and Maintenance | 8.1.2.12 | Other technologies and systems not listed above |  | 8.1.2.12 | GD_23 | BV_Grid Design, Operations, and Maintenance_Other technologies and systems not listed above_GD_23_45658 | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Project Milesstones for Lake Substation | N/A | N/A | N/A | N/A | Program Not Started in 2023 | N/A
BV | 2023-05-01 | Project | 2025-01-01 | 2026-01-01 | Partial Safety and Technical Upgrades to Village Substation | This project replaces overhead enclosed regulators with pad mounted regulators, installs pad mounted IntelliRupter switches, and updates substation controls. The substation is located in one of the more densely populated commercial and residential areas of Big Bear Lake. This 2 3.75 MVA transformer substation converts 34.5 kV sub-transmission to three 4.160 kV distribution circuits (Boulder, Harnish, and Lagonita circuits). These circuits also provide power to critical infrastructure and small businesses in the area. The reliability and safety of this substation is crucial to providing reliable and safe service to a substantial portion of BVES’s customers. Two of the distribution circuits traverse high wind and high vegetation areas. The IntelliRupter switches will significantly improve the ability of the circuits to be rapidly de-energized when fault conditions are detected. The IntelliRupter when in automatic mode will test at approximately 10% power when a fault is detected, thereby significantly reducing the possibility of causing an ignition. The equipment will be SCADA enabled with remote monitoring and operation capability. The regulators and switches at Village Substation are over 23 years old and approaching their maximum useful life, which makes the equipment more prone to failure and requires costly, heightened monitoring and maintenance. Maintaining compliance with GO-174 standards has been very difficult and costly. As substation equipment further ages, catastrophic failure of the equipment is more likely. Such a failure could potentially cause an ignition event that could lead to a wildfire. Village Substation was partially upgraded in 2012 resulting in the feeds on both the sub-transmission and distribution sides being underground and the transformers being pad mounted. The re-closers and regulators are of the overhead design. This project would complete the conversion of the substation to be completely underground with pad mounted equipment. At the completion of the project there would be no exposed bare wire or bus work. The Village Substation is heavily loaded making voltage regulation an important issue. The aging regulators are struggling to maintain proper voltage and will need to be replaced. There are safety concerns with the exposed wiring configuration at the substation. These concerns are reduced through increased worker protections, including additional personal protective equipment, additional protective covers, increased safety processes and enhanced safety reviews and briefing prior to entering the substation. These enhanced safety precautions are costly but are necessary to reduce the potential safety exposure to workers and the public. The heightened but costly safety measures are not acceptable as a long-term solution to the safety concerns that exist at the station. | Other grid design and system hardening actions which the electrical corporation takes to reduce its ignition and PSPS risk not otherwise covered by other initiatives in this section. | Grid Design, Operations, and Maintenance | 8.1.2.12 | Other technologies and systems not listed above |  | 8.1.2.12 | GD_24 | BV_Grid Design, Operations, and Maintenance_Other technologies and systems not listed above_GD_24_45658 | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Project Milesstones for Village Substation | N/A | N/A | N/A | N/A | Program Not Started in 2023 | N/A
BV | 2023-05-01 | Program |  |  | Detailed Inspections | In accordance with GO 165, careful visual inspections of overhead electric distribution lines and equipment where individual pieces of equipment and structures are carefully examined, visually and through use of routine diagnostic test, as appropriate, and (if practical and if useful information can be so gathered) opened, and the condition of each rated and recorded. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | 8.1.3.1 | Asset inspections |  | 8.1.3.1 | GD_25 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_25_ | TBD | Equipment ignition likelihood | No | Circuit Miles Inspected | 51 | 9 | 21 | 40 | 51 | 10 | 31.85 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Patrol Inspections | In accordance with GO 165, simple visual inspections of overhead electric distribution lines and equipment that is designed to identify obvious structural problems and hazards. Patrol inspections may be carried out in the course of other company business. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | 8.1.3.1 | Asset inspections |  | 8.1.3.1 | GD_26 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_26_ | TBD | Equipment ignition likelihood | No | Circuit Miles Inspected | 205 | 51 | 102 | 153 | 205 | 58 | 105.79 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Program |  |  | UAV Thermography | Inspections of overhead electric distribution lines, equipment, and right-of-way using infrared (heat-sensing) technology and cameras that can identify "hot spots", or conditions that indicate deterioration or potential equipment failures, of electrical equipment. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | 8.1.3.1 | Asset inspections |  | 8.1.3.1 | GD_27 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_27_ | TBD | Equipment ignition likelihood | No | Circuit Miles Inspected | 205 | 0 | 0 | 205 | 205 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Program |  |  | UAV HD Photography/Videography | Inspections of overhead electric distribution lines, equipment, and right-of-way using high definition (HD) photography and video cameras that can identify conditions that indicate deterioration or potential equipment failures, of electrical equipment. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | 8.1.3.1 | Asset inspections |  | 8.1.3.1 | GD_28 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_28_ | TBD | Equipment ignition likelihood | No | Circuit Miles Inspected | 205 | 0 | 0 | 205.2 | 205.2 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Program |  |  | LiDAR Inspection | Inspections of overhead electric distribution lines, equipment, and right-of-way using LiDAR (Light Detection and Ranging, a remote sensing method that uses light in the form of a pulsed laser to measure variable distances). | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | 8.1.3.1 | Asset inspections |  | 8.1.3.1 | GD_29 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_29_ | TBD | Equipment ignition likelihood | No | Circuit Miles Inspected | 205 | 0 | 0 | 205 | 205 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Minor Undergrounding Upgrades Projects | Actions taken to convert overhead electric lines and/or equipment to underground electric lines and/or equipment (i.e., located underground and in accordance with GO 128). | Actions taken to convert overhead electric lines and/or equipment to underground electric lines and/or equipment (i.e., located underground and in accordance with GO 128). | Grid Design, Operations, and Maintenance | 8.1.2.2 | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | GD_3 | BV_Grid Design, Operations, and Maintenance_Undergrounding of electric lines and/or equipment_GD_3_44927 | TBD | Contact from vegetation ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Initaite Underground Projects as needed | No Projects Proposed or Initatied in Quarter |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | 3rd Party Ground Patrol | In accordance with GO 165, simple visual inspections of overhead electric distribution lines and equipment that is designed to identify obvious structural problems and hazards. Patrol inspections may be carried out in the course of other company business. This inspection is performed by an independent 3rd Party. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | 8.1.3.1 | Asset inspections |  | 8.1.3.1 | GD_30 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_30_ | TBD | Equipment ignition likelihood | No | Circuit Miles Inspected | 205 | 0 | 0 | 205 | 205 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Program |  |  | Intrussive Pole Inspections | In accordance with GO 165, intrusive inspections involve movement of soil, taking samples for analysis, and/or using more sophisticated diagnostic tools beyond visual inspections or instrument reading. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | 8.1.3.1 | Asset inspections |  | 8.1.3.1 | GD_31 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_31_ | TBD | Equipment ignition likelihood | No | Number of Poles Intrusively Inspected | 850 | 0 | 0 | 850 | 850 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Substation inspections | In accordance with GO 174, inspection of substations performed by qualified persons and according to the frequency established by the utility, including record-keeping. | Inspections of overhead electric distribution lines, equipment, and right-of-way. | Grid Design, Operations, and Maintenance | 8.1.3.1 | Asset inspections |  | 8.1.3.1 | GD_32 | BV_Grid Design, Operations, and Maintenance_Asset inspections_GD_32_ | TBD | Equipment ignition likelihood | No | Number of Substations Inspected | 144 | 36 | 72 | 108 | 144 | 39 | 78 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Equipment maintenance and repair | Remediation, adjustments, or installations of new equipment to improve or replace existing connector equipment, such as hotline clamps. | Remediation, adjustments, or installations of new equipment to improve or replace existing connector equipment, such as hotline clamps. | Grid Design, Operations, and Maintenance | 8.1.4 | Equipment maintenance and repair |  | 8.1.4 | GD_33 | BV_Grid Design, Operations, and Maintenance_Equipment maintenance and repair_GD_33_ | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | As Needed Maintenance | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Asset management and inspection enterprise system(s) | Operation of and support for centralized asset management and inspection enterprise system(s) updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | Operation of and support for centralized asset management and inspection enterprise system(s) updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | Grid Design, Operations, and Maintenance | 8.1.5 | Asset management and inspection enterprise system(s) |  | 8.1.5 | GD_34 | BV_Grid Design, Operations, and Maintenance_Asset management and inspection enterprise system(s)_GD_34_ | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program Not Started in 2024 | N/A
BV | 2023-05-01 | Program |  |  | Asset Quality assurance / quality control | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | Grid Design, Operations, and Maintenance | 8.1.6 | Quality assurance / quality control |  | 8.1.6 | GD_35 | BV_Grid Design, Operations, and Maintenance_Quality assurance / quality control_GD_35_ | TBD | Equipment ignition likelihood | No | Number of Asset QCs on WMP Work | 20 | 5 | 10 | 15 | 20 | 5 | 10 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Asset Open work orders | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe asset management activities. | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe asset management activities. | Grid Design, Operations, and Maintenance | 8.1.7 | Open work orders |  | 8.1.7 | GD_36 | BV_Grid Design, Operations, and Maintenance_Open work orders_GD_36_ | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No descrep exceeding GO95 resolution timeframes | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Equipment Settings to Reduce Wildfire Risk | The electrical corporation’s procedures for adjusting the sensitivity of grid elements to reduce wildfire risk. | The electrical corporation’s procedures for adjusting the sensitivity of grid elements to reduce wildfire risk. | Grid Design, Operations, and Maintenance | 8.1.8.1 | Equipment Settings to Reduce Wildfire Risk |  | 8.1.8.1 | GD_37 | BV_Grid Design, Operations, and Maintenance_Equipment Settings to Reduce Wildfire Risk_GD_37_ | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Evaluate System Settings | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Grid Response Procedures and Notifications | The electrical corporation’s procedures it uses to respond to faults, ignitions, or other issues detected on its grid that may result in a wildfire. | The electrical corporation’s procedures it uses to respond to faults, ignitions, or other issues detected on its grid that may result in a wildfire. | Grid Design, Operations, and Maintenance | 8.1.8.2 | Grid Response Procedures and Notifications |  | 8.1.8.2 | GD_38 | BV_Grid Design, Operations, and Maintenance_Grid Response Procedures and Notifications_GD_38_ | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Update Procedure Annually | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | Work activity guidelines that designate what type of work can be performed during operating conditions of different levels of wildfire risk. Training for personnel on these guidelines and the procedures they prescribe, from normal operating procedures to increased mitigation measures to constraints on work performed. | Work activity guidelines that designate what type of work can be performed during operating conditions of different levels of wildfire risk. Training for personnel on these guidelines and the procedures they prescribe, from normal operating procedures to increased mitigation measures to constraints on work performed. | Grid Design, Operations, and Maintenance | 8.1.8.3 | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk |  | 8.1.8.3 | GD_39 | BV_Grid Design, Operations, and Maintenance_Personnel Work Procedures and Training in Conditions of Elevated Fire Risk_GD_39_ | TBD | Wildfire Spread | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Update Procedure Annually. Verification of Trainging Annual | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2025-01-01 | Covered Conductor Replacement Project | In conducting the Covered Conductor Preplacement Project, existing poles are assessed (3-D stress loading, GO-95 discrepancies, intrussive testing) and are remediated or replaced to ensure they are able to support covered conductor. | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. | Grid Design, Operations, and Maintenance | 8.1.2.3 | Distribution pole replacements and reinforcements |  | 8.1.2.3 | GD_4 | BV_Grid Design, Operations, and Maintenance_Distribution pole replacements and reinforcements_GD_4_44927 | TBD | Equipment ignition likelihood | No | Number of Poles Replaced | 200 | 0 | 50 | 100 | 200 | 56 | 166 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Asset Workforce Planning | Programs to ensure that the electrical corporation has qualified asset personnel and to ensure that both employees and contractors tasked with asset management responsibilities are adequately trained to perform relevant work. | Programs to ensure that the electrical corporation has qualified asset personnel and to ensure that both employees and contractors tasked with asset management responsibilities are adequately trained to perform relevant work. | Grid Design, Operations, and Maintenance | 8.1.9 | Workforce Planning |  | 8.1.9 | GD_40 | BV_Grid Design, Operations, and Maintenance_Workforce Planning_GD_40_ | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Verify Approraite Staffing Levels for Wildfire Related Activities | Staffing Level Verifed |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2024-01-01 | Radford Line Replacement Project | Radford Line Replacement Project replaces fire resistant (ductile iron) poles because it is located in an area designated as High Fire Threat District Tier 3 (“extreme fire risk”) by the CPUC. BVES believes that this approach will provide the greatest protection and significantly enhance public safety. | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. | Grid Design, Operations, and Maintenance | 8.1.2.3 | Distribution pole replacements and reinforcements |  | 8.1.2.3 | GD_5 | BV_Grid Design, Operations, and Maintenance_Distribution pole replacements and reinforcements_GD_5_44927 | TBD | Equipment ignition likelihood | No | Number of Poles Replaced | 70 | 0 | 0 | 20 | 70 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Evacuation Route Hardening Project | This project aims to build upon the work that Bear Valley previously accomplished in the area of hardening evacuation routes. In 2021 and 2022, Bear Valley completed the hardening of primary evacuation routes to its service area. This project is aimed at hardening electrical assets along secondary roads that lead to the primary evacuation routes. The hardening of BVES electrical assets (poles, wires, equipment) along the evacuation routes and secondary roads that lead to primary evacuation routes is important to ensure they do not fail during a wildfire, which would limit mobility along the evacuation routes required to safely perform an evacuation. Lessons learned from past wildfires and most notably the Camp Fire indicate hardening of utility assets along evacuation routes is critical to public safety for the following reasons: (1) To allow the safe evacuation of the public in the event of a wildfire; and (2) To allow the mobility for First Responders to move assets in and out of the wildfire areas to allow them to actively fight the wildfire, save lives, protect property, and minimize environmental damage. BVES plans to install wire wrap mesh on 500 wood poles per year in selected high-risk areas along secondary roads leading to the primary evacuation routes from 2023 to 2026. | Remediation, adjustments, or installations of new equipment to improve or replace existing distribution poles (i.e., those supporting lines under 65kV), including with equipment such as composite poles manufactured with materials reduce ignition probability by increasing pole lifespan and resilience against failure from object contact and other events. | Grid Design, Operations, and Maintenance | 8.1.2.3 | Distribution pole replacements and reinforcements |  | 8.1.2.3 | GD_6 | BV_Grid Design, Operations, and Maintenance_Distribution pole replacements and reinforcements_GD_6_44927 | TBD | Wildfire Vulnerability | No | Number of Poles that had Wire Mesh Installed on them. | 500 | 250 | 300 | 400 | 500 | 600 | 991 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 |  |  |  | NA | BVES does not own or operate any transmission lines. | Remediation, adjustments, or installations of new equipment to improve or replace existing transmission towers (e.g., structures such as lattice steel towers or tubular steel poles that support lines at or above 65kV). | Grid Design, Operations, and Maintenance | 8.1.2.4 | Transmission pole/tower replacements and reinforcements |  | 8.1.2.4 | GD_7 | BV_Grid Design, Operations, and Maintenance_Transmission pole/tower replacements and reinforcements_GD_7_ | TBD | NA | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BV | 2023-05-01 | Program |  |  | Traditional overhead hardening | Maintenance, repair, and replacement of capacitors, circuit breakers, cross-arms, transformers, fuses, and connectors (e.g., hot line clamps) with the intention of minimizing the risk of ignition. | Maintenance, repair, and replacement of capacitors, circuit breakers, cross-arms, transformers, fuses, and connectors (e.g., hot line clamps) with the intention of minimizing the risk of ignition. | Grid Design, Operations, and Maintenance | 8.1.2.5 | Traditional overhead hardening |  | 8.1.2.5 | GD_8 | BV_Grid Design, Operations, and Maintenance_Traditional overhead hardening_GD_8_ | TBD | Equipment ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | As Needed Maintenance | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 |  |  |  | Emerging grid hardening technology installations and pilots | BVES does not have any pilot projects or programs for novel grid hardening technology. BVES is following what other larger electric utilties are doing regarding grid hardening technology as well as participating in industry conferences and trade shows to keep current on any emerging grid hardening technologies. BVES will certainly pilot any promising grid hardening technologies that would work well in BVES's service area and system. | Development, deployment, and piloting of novel grid hardening technology. | Grid Design, Operations, and Maintenance | 8.1.2.6 | Emerging grid hardening technology installations and pilots |  | 8.1.2.6 | GD_9 | BV_Grid Design, Operations, and Maintenance_Emerging grid hardening technology installations and pilots_GD_9_ | TBD | NA | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program Not Started in 2024 | N/A
BV | 2023-05-01 | Program |  |  | Technosylva Contractor. Program implemented and ongoing. | Development and use of tools and processes to assess the risk of wildfire and PSPS across an electrical corporation’s service territory. | Development and use of tools and processes to assess the risk of wildfire and PSPS across an electrical corporation’s service territory. | Risk Methodology and Assessment | 6 | Risk Methodology and Assessment |  | 6 | RMA_1 | BV_Risk Methodology and Assessment_Risk Methodology and Assessment_RMA_1_ | TBD | Wildfire Hazard | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Maintain real time risk mapping | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Advanced weather monitoring and weather stations | Project installs and maintains 20 weather stations. | Development and deployment of systems which measure environmental characteristics, such as fuel moisture, air temperature, and velocity. | Situational Awareness and Forecasting | 8.3.2 | Environmental monitoring systems |  | 8.3.2 | SAF_1 | BV_Situational Awareness and Forecasting_Environmental monitoring systems_SAF_1_44927 | TBD | PSPS likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Maintain Established Weatherstations | Maintenance Needs Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2024-01-01 | Install Fault Indicators | The project aims to install an additional 129 fault indicators (FIs) at 43 locations in Bear Valley’s sub-transmission and distribution system. FIs are devices installed on overhead power lines in electric power distribution systems to detect and indicate the occurrence of faults. They are installed at specific distances along a circuit and at major branch lines so that when a fault occurs, the fault zone (where the fault occurred) is minimized, thereby reducing time to locate and identify the fault and, therefore, restore service to affected customers. FIs provide a visual indicator on which side of the FI the fault occurred. Therefore, responding crews look for the portion of the circuit in which the FIs have “sandwiched” the fault. Some FIs, in addition to providing a visual indicator, have the capability to be connected to the Supervisory Control and Data Acquisition (SCADA) network which allows remote identification of the fault zone. This further reduces response time in localizing a fault since the crews would be directed to roll their truck directly to the fault zone rather than the faulted circuit. This project will install the SCADA capable FI devices. This project will establish a robust and secure IP communications network across the sub-transmission and distribution systems to fully enable monitoring of the FIs. Connectivity to SCADA will be via the BVES service area fiber optic network and via radio/cellular data transfer equipment. FIs allow crews to locate and arrive at the fault location significantly faster and are more likely to identify a faulted situation and ignition with greater opportunity to reduce the risks of a wildfire. | Development and deployment of systems that checks the operational conditions of electrical facilities and equipment and detects such things as faults, failures, and recloser operations. | Situational Awareness and Forecasting | 8.3.3 | Grid monitoring systems |  | 8.3.3 | SAF_2 | BV_Situational Awareness and Forecasting_Grid monitoring systems_SAF_2_44927 | TBD | Equipment ignition likelihood | No | Number of Fis installed. | 30 | 0 | 15 | 30 | 30 | 0 | 9 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Project | 2023-01-01 | 2026-01-01 | Online Diagnostic System | Project installs continuous monitor sensors to provide usable grid insight information that is measured, reported, and documented. Analytics enable the ability to identify and correct current and future irregularities before a problem arises. This will enhance safety, reliability, cost control, and customer satisfaction. Designed to pinpoint irregularities, which may be due to degrading/imminent hardware failures, as well as identify objects such as vegetation contacting the lines. Enables BVES to rapidly inspect potential problems before they develop into an ignition source. | Development and deployment of systems that checks the operational conditions of electrical facilities and equipment and detects such things as faults, failures, and recloser operations. | Situational Awareness and Forecasting | 8.3.3 | Grid monitoring systems |  | 8.3.3 | SAF_3 | BV_Situational Awareness and Forecasting_Grid monitoring systems_SAF_3_44927 | TBD | Equipment ignition likelihood | No | Number of circuits installed on per year. | 1 | 0 | 0 | 1 | 1 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | HD ALERTWildfire Cameras | Project installs 15 HD ALERTWildfire Cameras to provide complete coverage of the BVES Service Area. | Development and deployment of systems which discover or identify the presence or existence of an ignition, such as cameras. | Situational Awareness and Forecasting | 8.3.4 | Ignition detection systems |  | 8.3.4 | SAF_4 | BV_Situational Awareness and Forecasting_Ignition detection systems_SAF_4_ | TBD | Wildfire Spread | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Complete | N/A
BV | 2023-05-01 | Program |  |  | Weather forecasting | Program leverages Technosylva’s software capabilities and solutions, which have been implemented across California in other electric utilities, to provide: (1) On-demand, real time wildfire behavior modeling, predictive spread conditions, and derivation of potential impacts analysis; (2)Ability to conduct simulations on-demand, to reflect changing conditions or local data observations, including proactive “what if” scenarios; and (3) Weather and wildfire risk forecasting for BVES’s assets and the service territory using daily weather prediction integration to support PSPS activation calls and response operations. Also, program engages an expert weather consultant to provide BVES specific weather forecasts at least weekly and more frequently during fire threat weather conditions. This information, along with the information gained from Technosylva fire threat analysis applications allows BVES to evalaute weather impacts on electric lines and equipment and the potential for ignitions and wildfire. | Development methodology for forecast of weather conditions relevant to electrical corporation operations, forecasting weather conditions and conducting analysis to incorporate into utility decision- making, learning and updates to reduce false positives and false negatives of forecast PSPS conditions. | Situational Awareness and Forecasting | 8.3.5 | Weather forecasting |  | 8.3.5 | SAF_5 | BV_Situational Awareness and Forecasting_Weather forecasting_SAF_5_ | TBD | PSPS likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Monitoring and Maintenance | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Fire potential index | Calculation and application of a landscape scale index used as a proxy for assessing real-time risk of a wildfire under current and forecasted weather conditions. | Calculation and application of a landscape scale index used as a proxy for assessing real-time risk of a wildfire under current and forecasted weather conditions. | Situational Awareness and Forecasting | 8.3.6 | Fire potential index |  | 8.3.6 | SAF_6 | BV_Situational Awareness and Forecasting_Fire potential index_SAF_6_ | TBD | PSPS likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Monitoring and Maintenance | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Project |  |  | GreenGrid iSIU | The iSIU System is a camera-based inspection and monitoring device. The device consists of a camera, optical sensors, communication module, processor and power module in one integrated unit. The devices have been strategically placed on poles on the Boulder and North Shore Circuits and allow for autonomous monitoring of the power line infrastructures and advise the remote maintenance, inspections, or operations crews on potentially hazardous events automatically, thus saving operational cost and reducing risks to humans and the environment. | Continuous circuit monitoring | Situational Awareness and Forecasting | 8.3.6 | Grid monitoring systems |  | 8.3.3 | SAF_7 | BV_Situational Awareness and Forecasting_Grid monitoring systems_SAF_7_ | TBD | PSPS likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Monitoring and Maintenance | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Environmental compliance and permitting | Development and implementation of process and procedures to ensure compliance with applicable environmental laws, regulations, and permitting related to the implementation of the WMP. | Development and implementation of process and procedures to ensure compliance with applicable environmental laws, regulations, and permitting related to the implementation of the WMP. | Overview of the Service Territory | 5.4.5 | Environmental compliance and permitting |  | 5.4.5 | ST_1 | BV_Overview of the Service Territory_Environmental compliance and permitting_ST_1_ | TBD | Wildfire Hazard | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Annual Review and Update | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Detailed Inspections | Careful visual inspections and maintenance of vegetation around the distribution right-of-way, where individual trees are carefully examined, visually, and the condition of each rated and recorded. Describe the frequency of inspection and maintenance programs. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | 8.2.2.1 | Vegetation inspections |  | 8.2.2.1 | VM_1 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_1_ | TBD | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected | 51 | 9 | 21 | 40 | 51 | 10 | 31.85 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Fall-in mitigation | Actions taken to identify and remove or otherwise remediate trees that pose a high risk of failure or fracture that could potentially strike electrical equipment. | Actions taken to identify and remove or otherwise remediate trees that pose a high risk of failure or fracture that could potentially strike electrical equipment. | Vegetation Management and Inspection | 8.2.3.4 | Fall-in mitigation |  | 8.2.3.4 | VM_10 | BV_Vegetation Management and Inspection_Fall-in mitigation_VM_10_ | TBD | Contact from vegetation ignition likelihood | No | Number of trees remediated or removed to prevent fall-in | 88 | 22 | 44 | 66 | 88 | 23 | 63 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Substation defensible space | Actions taken to reduce ignition probability and wildfire consequence due to contact with substation equipment. | Actions taken to reduce ignition probability and wildfire consequence due to contact with substation equipment. | Vegetation Management and Inspection | 8.2.3.5 | Substation defensible space |  | 8.2.3.5 | VM_11 | BV_Vegetation Management and Inspection_Substation defensible space_VM_11_ | TBD | Contact from vegetation ignition likelihood | No | Substations inspected and cleared | 13 | 0 | 8 | 13 | 13 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | High-risk species | Actions taken to reduce the ignition probability and wildfire consequence attributable to high-risk species of vegetation. | Actions taken to reduce the ignition probability and wildfire consequence attributable to high- risk species of vegetation. | Vegetation Management and Inspection | 8.2.3.6 | High-risk species |  | 8.2.3.6 | VM_12 | BV_Vegetation Management and Inspection_High-risk species_VM_12_ | TBD | Contact from vegetation ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | As needed remediation of high-risk species | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Fire-resilient rights-of-way | Actions taken to promote vegetation communities that are sustainable, fire-resilient, and compatible with the use of the land as an electrical corporation right-of-way. | Actions taken to promote vegetation communities that are sustainable, fire-resilient, and compatible with the use of the land as an electrical corporation right-of-way. | Vegetation Management and Inspection | 8.2.3.7 | Fire-resilient rights-of-way |  | 8.2.3.7 | VM_13 | BV_Vegetation Management and Inspection_Fire-resilient rights-of-way_VM_13_ | TBD | Wildfire Spread | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Program Not Started in 2024 | N/A
BV | 2023-05-01 | Program |  |  | Emergency response vegetation management | Planning and execution of vegetation activities in response to emergency situations including weather conditions that indicate an elevated fire threat and post-wildfire service restoration. | Planning and execution of vegetation activities in response to emergency situations including weather conditions that indicate an elevated fire threat and post-wildfire service restoration. | Vegetation Management and Inspection | 8.2.3.8 | Emergency response vegetation management |  | 8.2.3.8 | VM_14 | BV_Vegetation Management and Inspection_Emergency response vegetation management_VM_14_ | TBD | Contact from vegetation ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Update Procedure | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Vegetation management enterprise system | Operation of and support for centralized vegetation management and inspection enterprise system(s) updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | Operation of and support for centralized vegetation management and inspection enterprise system(s) updated based upon inspection results and activities such as hardening, maintenance, and remedial work. | Vegetation Management and Inspection | 8.2.4 | Vegetation management enterprise system |  | 8.2.4 | VM_15 | BV_Vegetation Management and Inspection_Vegetation management enterprise system_VM_15_ | TBD | Contact from vegetation ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Update Procedure | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Vegetation Management Quality assurance / quality control | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | Establishment and function of audit process to manage and confirm work completed by employees or contractors, including packaging QA/QC information for input to decision-making and related integrated workforce management processes. | Vegetation Management and Inspection | 8.2.5 | Quality assurance / quality control |  | 8.2.5 | VM_16 | BV_Vegetation Management and Inspection_Quality assurance / quality control_VM_16_ | TBD | Contact from vegetation ignition likelihood | No | Number of Vegetation Management Audits | 5 | 2 | 3 | 4 | 5 | 2 | 3 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Vegetation Management Open work orders | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe vegetation management activities. | Actions taken to manage the electrical corporation’s open work orders resulting from inspections that prescribe vegetation management activities. | Vegetation Management and Inspection | 8.2.6 | Open work orders |  | 8.2.6 | VM_17 | BV_Vegetation Management and Inspection_Open work orders_VM_17_ | TBD | Contact from vegetation ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Compliance with Corrective action Timeframe | Quarterly Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Vegetation Management Workforce planning | Programs to ensure that the electrical corporation has qualified vegetation management personnel and to ensure that both employees and contractors tasked with vegetation management responsibilities are adequately trained to perform relevant work. | Programs to ensure that the electrical corporation has qualified vegetation management personnel and to ensure that both employees and contractors tasked with vegetation management responsibilities are adequately trained to perform relevant work. | Vegetation Management and Inspection | 8.2.7 | Workforce planning |  | 8.2.7 | VM_18 | BV_Vegetation Management and Inspection_Workforce planning_VM_18_ | TBD | Contact from vegetation ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Verification Current Staffing Level (Internal & Contractors) Meets Need | Needs Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Project |  |  | AiDash | AiDash software uses satellite imagining providing a rapid assessment of BVES’s service territory and insight into whether vegetation should be assessed or moved up in priority for upcoming patrol, detailed, or third-party ground inspections. The AiDash assessment allows BVES to gain a comprehensive understanding of its service territory at a glance. AiDash also provides a complementary review of BVES’s vegetation management program. | The AiDash assessment allows BVES to gain a comprehensive understanding of its service territory at a glance. AiDash also provides a complementary review of BVES’s vegetation management program. | Vegetation Management and Inspection | 8.2.2.7 | Vegetation inspections |  | 8.2.2.1 | VM_19 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_19_ | TBD | Contact from vegetation ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Once annual review of vegetation management program planning vs AiDash outout vegetation management action | Target Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Patrol Inspections | Visual inspections of vegetation along rights-of- way that is designed to identify obvious hazards. Patrol inspections may be carried out in the course of other company business. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | 8.2.2.1 | Vegetation inspections |  | 8.2.2.1 | VM_2 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_2_ | TBD | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected | 205 | 52 | 105 | 158 | 205 | 58 | 105.79 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Program |  |  | UAV HD Photography/Videography | Inspections of right-of-way using aerial (UAV) HD photography and vido cameras. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | 8.2.2.1 | Vegetation inspections |  | 8.2.2.1 | VM_3 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_3_ | TBD | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected | 205 | 0 | 0 | 205 | 205 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Program |  |  | LiDAR Inspection | Inspections of right-of-way using LiDAR. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | 8.2.2.1 | Vegetation inspections |  | 8.2.2.1 | VM_4 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_4_ | TBD | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected | 205 | 0 | 0 | 205 | 205 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Program |  |  | 3rd Party Ground Patrol | Visual inspections of vegetation along rights-of- way that is designed to identify obvious hazards. Patrol inspections may be carried out in the course of other company business. This inspection is performed by an independent 3rd Party. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | 8.2.2.1 | Vegetation inspections |  | 8.2.2.1 | VM_5 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_5_ | TBD | Contact from vegetation ignition likelihood | No | Circuit Miles Inspected | 205 | 0 | 0 | 205 | 205 | 0 | 0 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | Project is not delayed but, adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
BV | 2023-05-01 | Program |  |  | Substation inspections | Inspection of vegetation surrounding substations, performed by qualified persons and according to the frequency established by the utility, including record-keeping. | Inspections of vegetation around and adjacent to electrical facilities and equipment that may be hazardous by growing, blowing, or falling into electrical facilities or equipment. | Vegetation Management and Inspection | 8.2.2.1 | Vegetation inspections |  | 8.2.2.1 | VM_6 | BV_Vegetation Management and Inspection_Vegetation inspections_VM_6_ | TBD | Contact from vegetation ignition likelihood | No | Number of Substations Inspected | 144 | 36 | 72 | 108 | 144 | 39 | 78 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Pole clearing | Plan and execution of vegetation removal around poles per Public Resources Code section 4292 and outside the requirements of Public Resources Code section 4292 (e.g., pole clearing performed outside of the State Responsibility Area). | Plan and execution of vegetation removal around poles per Public Resources Code section 4292 and outside the requirements of Public Resources Code section 4292 (e.g., pole clearing performed outside of the State Responsibility Area). | Vegetation Management and Inspection | 8.2.3.1 | Pole clearing |  | 8.2.3.1 | VM_7 | BV_Vegetation Management and Inspection_Pole clearing_VM_7_ | TBD | Contact from vegetation ignition likelihood | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review and Update Procedure | Needs Met |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Wood and slash management | Actions taken to manage all downed wood and “slash” generated from vegetation management activities. | Actions taken to manage all downed wood and “slash” generated from vegetation management activities. | Vegetation Management and Inspection | 8.2.3.2 | Wood and slash management |  | 8.2.3.2 | VM_8 | BV_Vegetation Management and Inspection_Wood and slash management_VM_8_ | TBD | Wildfire Spread | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Contractor Adhered to Waste Removal | Contractor Met Requirements |  |  |  | Ongoing | N/A
BV | 2023-05-01 | Program |  |  | Clearance | Actions taken after inspection to ensure that vegetation does not encroach upon electrical equipment and facilities, such as tree trimming. | Actions taken after inspection to ensure that vegetation does not encroach upon electrical equipment and facilities, such as tree trimming. | Vegetation Management and Inspection | 8.2.3.3 | Clearance |  | 8.2.3.3 | VM_9 | BV_Vegetation Management and Inspection_Clearance_VM_9_ | TBD | Contact from vegetation ignition likelihood | No | Circuit Miles Cleared | 72 | 18 | 36 | 54 | 72 | 18.254 | 37.06 |  |  | N/A | N/A | N/A | N/A | N/A | Ongoing | N/A
Note on C2: Author: Select cells for dropdown list.

## Table 2
| Utility | BVES | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-08-01 | HWW = High wind warning
RFW = Red flag warning
[10 empty] | Actuals | Projected
| Table 2: Performance Metrics | [8 empty] | Q2
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 5 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
|  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events |  | Not Applicable
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 2 | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 3 | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of events | BVES does not adjust settings based on season or condition. BVES operates at all times on the optimal fire prevention settings based on coordination study. | Not Applicable
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A |  |  |  |  | hours | BVES is working to determine the capability of tracking said metric. There is no definitive date for when this data will be available. | Not Applicable
|  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A |  |  |  |  | hours | BVES is working to determine the capability of tracking said metric. There is no definitive date for when this data will be available. | Not Applicable
|  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A |  |  |  |  | hours | BVES is working to determine the capability of tracking said metric. There is no definitive date for when this data will be available. | Not Applicable
|  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A |  |  |  |  | hours | BVES is working to determine the capability of tracking said metric. There is no definitive date for when this data will be available. | Not Applicable
|  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 |  |  |  | hours
|  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
|  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not Applicable
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of orders
|  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of orders
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of orders
|  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of orders
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Hours | BVES is working to determine the capability of tracking said metric. There is no definitive date for when this data will be available. | Not Applicable
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of fatalities
|  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of injuries
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 1000 |  | Not Applicable
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Number of structures |  | Not Applicable
|  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Number of structures |  | Not Applicable
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Acres |  | Not Applicable
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of ignitions |  | Not Applicable
|  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of ignitions |  | Not Applicable
|  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of ignitions |  | Not Applicable
|  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A |  |  |  |  | Number of ignitions |  | Not Applicable
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 47.79 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 21.85 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | BVES Inspections are done based off of line mile not on an asset basis | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | BVES Inspections are done based off of line mile not on an asset basis | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | BVES Inspections are done based off of line mile not on an asset basis | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | BVES Inspections are done based off of line mile not on an asset basis | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | BVES Inspections are done based off of line mile not on an asset basis | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | BVES Inspections are done based off of line mile not on an asset basis | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | BVES Inspections are done based off of line mile not on an asset basis | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | BVES Inspections are done based off of line mile not on an asset basis | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of findings from these asset inspections |  | Not Applicable
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of asset inspection findings which have been fixed |  | Not Applicable
x | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not tracked before 2022
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not tracked before 2022
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 8 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not tracked before 2021
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not tracked before 2021
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not tracked before 2021
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not tracked before 2021
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Percentage of customers notified of evacuation | BVES has not had a utility ignited wildfire | Not Applicable

## Table 3
Utility | BVES
Table No. | 3
Date Modified | 2024-08-01
[5 empty] | Actual | Projected
Table 3: List and description of additional metrics |  |  |  |  | Q2
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
Number of poles assessed | Count of poles assessed | Identify # of inspected poles to reduce the number of pole failures & possibility of fire | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 50 | 260 | 260 | 260 | Count of poles assessed
Number of poles that failed assessment (wind loading, age, deterioraton, unfixable GO-95 violation) | Count of poles that fail assessment | Identify proper pole replacement periodicty, lifespan, etc. and reduce possibility of fire | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 43 | 50% of Assessed | 50% of Assessed | 50% of Assessed | Count of poles that fail assessment
Number of poles replaced as a result of failed assessments | Count of poles replaced | Demonstrates progress of fire resilience efforts | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 110 | 200 | 200 | 200 | Count of poles replaced
Number of poles remediated as a result of failed assessments | Count of poles remediated as a result of failed assessment | Demonstrates progress of fire resilience efforts | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 11 | 100 | 100 | 100 | Count of poles remediated as a result of failed assessment
Number of Tree Attachments Removed | Count of tree attachments removed | Demonstrates progress toward goal of zero tree attachment and reduce possibility of fire | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 33 | 100 | 100 | 100 | Count of tree attachments removed
Number of new poles installed as a result of Tree Attachments Removed | Count of poles installed to replace wiring attachment from prior tree attachment | Demonstrates progress in reducing direct vegetation contact risk and installing more resilient poles in place of the prior attachment. | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 19 | 50 | 50 | 50 | Count of poles installed to replace wiring attachment from prior tree attachment
Length of Covered Bare Wire (Circuit Miles) | Miles of covered bare wire | Demonstrates progress in covering bare wire | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 5.84 | 12.9 | 12.9 | 12.9 | Miles of covered bare wire
Percent of 34.5 kV System that is Overhead Bare Wire | Percent of 34.5 kV System that is Overhead Bare Wire | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 36.7% | 38.5% | 35% | 32% | Percent of 34.5 kV System that is Overhead Bare Wire
Percent of 34.5 kV System that is Underground | Percent of 34.5 kV System that is underground | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 3% | 3% | 3% | 3% | Percent of 34.5 kV System that is underground
Percent of 34.5 kV System that is Covered Wire | Percent of 34.5 kV System that is covered wire | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 60.2% | 58.5% | 62% | 65% | Percent of 34.5 kV System that is underground
Percent of 4 kV System that is Overhead Bare Wire | Percent of 4 kV System that is overhead | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 60.7% | 62.4% | 60.4% | 58.4% | Percent of 34.5 kV System that is overhead
Percent of 4 kV System that is Underground | Percent of 4 kV System that is underground | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 22.6% | 22.6% | 22.6% | 22.6% | Percent of 4 kV System that is underground
Percent of 4 kV System that is Covered Wire | Percent of 4 kV System that is covered wire | Inventory | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 16.6% | 15% | 17% | 19% | Percent of 34.5 kV System that is underground
Number of Tree Attachments Remaining in System | Count of tree attachments | Demonstrates progress toward goal of zero tree attachment and reduce possibility of fire | Assess overall system hardening | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 365 | 464 | 364 | 264 | Count of tree attachments
Number of Trees Trimmed | Count of trees trimmed as part of veg mgmt work | Inventory and identify trends | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 1730 |  |  |  | Count of trees trimmed as part of veg mgmt work |  | BVES does not currently project the number of tree's trimmed a year
Number of Trees Removed | Count of trees removed as part of veg mgmt work | Inventory and identify trends | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 40 |  |  |  | Count of trees removed as part of veg mgmt work |  | BVES does not currently project the number of tree's removed a year
Circuit Miles Trimmed | Number of Circuit Miles with VM trimming | Account for circuit miles that receive tree trimming activities per quarter | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 18.81 | 72 | 72 | 72 | Number of Circuit Miles with VM trimming
VM QCs | Number of VM QCs performed | Include metrics for the number of quality checks performed on vegtation management activities | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 77 | 72 | 72 | 72 | Number of VM QCs performed
Number of Substations Inspected | Number of Substations Inspected | Accounting record for number of substations inspected quarterly | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 39 | 144 | 144 | 144 | Number of Substations Inspected
Number of Poles Intrusively Inspected | Number of Poles Intrusively Inspected | Inventory and identify performance trends | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 0 | 850 | 850 | 850 | Number of Poles Intrusively Inspected
Number of Poles Failing Instrusive Inspection | Number of Poles Failing Intrusively Inspection | Inventory and identify trends | Determine if plan is on schedule | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 0 | 30 | 25 | 20 | Number of Poles Failing Intrusively Inspection
Number of Customer Service Calls about Tree Trimming | Number of Customer Service Calls about Tree Trimming | Inventory and identify trends | Monitor changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 66 | 100 | 100 | 100 | Number of Customer Service Calls about Tree Trimming
Number of Customer Engagements in Community Outreach for PSPS and WMP | Count of Engagements | Record of outreach performed each quarter related to WMP activities or PSPS preparedness | Monitor customer and community outreach activities | No third-party validation necessary | 252 | 360 | 360 | 360 | Number of outreach performed
SAIDI due to PSPS | SAIDI Reliability Performance impacts due to PSPS | Identify impacts to SAIDI performance from PSPS events | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 0 | 0 | 0 | 0 | SAIDI Reliability Performance impacts due to PSPS | BVES has not initiated any PSPS activation to date.
Number of NFDRS “Very Dry” and “Dry” Days | Count of NFDRS "very dry" and "dry" days | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 0 |  |  |  | Count of NFDRS "very dry" and "dry" days |  | BVES does not currently project weatehr related metrics
Number of PSPS Events | Count of PSPS events | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 0 | 0 | 0 | 0 | Count of PSPS events
Maximum recorded sustained winds Recorded | Highest recorded sutained wind speed recorded | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 34 |  |  |  | Highest recorded sutained wind speed recorded |  | BVES does not currently project weatehr related metrics
Maximum recorded wind gusts Recorded | Highest recorded sutained wind gust recorded | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Contracted 3rd party analysts or academic researchers could review open as well as closed work orders, BVES GIS databases, staff interviews, as well as spot-checking select items for confirmation of status. | 60 |  |  |  | Highest recorded sutained wind gust recorded |  | BVES does not currently project weatehr related metrics
Frequency of sustained high winds (number of days sustained wind > 50 mph) | Count of sustained high wind days recorded | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Data obtained from BVES owned weather stations | 0 |  |  |  | Count of sustained high wind days recorded |  | BVES does not currently project weatehr related metrics
Frequency of high wind gusts (number of days wind gusts > 50 mph) recorded | Count of days with high wind gusts recorded | Inventory and identify trends | Monitor the need for PSPS events over time as an indicator of changing climatic and weather patterns | Data obtained from BVES owned weather stations | 2 |  |  |  | Count of days with high wind gusts recorded |  | BVES does not currently project weatehr related metrics

## Table 4
Utility | BVES
Table No. | 4
Date Modified | 2024-08-01
Table 4: Weather patterns |  |  | Q2
Metric type | # | Metric name | 2024 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 0 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 0 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 0 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD |  | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 0 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD |  | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 0 | Fire potential index overhead circuit mile days, see above for definition
| 4.c. | Fire potential index circuit mile days - non-HFTD |  | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed)

## Table 5
| Utility | BVES | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-08-01
[8 empty] | Actual number of risk events | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q2
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | YES | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.e.d.0 | 3rd party contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.0 | 3rd party contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.f.d.0 | Other contact from object | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.f.d.2 | Other contact from object | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.0 | Other contact from object | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.f.t.2 | Other contact from object | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.g.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.g.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.g.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | YES | 0 | 8 | 8 | 8 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | YES | 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 | YES | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | YES | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | YES | 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 | YES | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | YES | 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 | YES | 0 | 1 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 | YES | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 | YES | 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 | YES | 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrester | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrester | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 | YES | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 | YES | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 | YES | 0 | 1 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | YES | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 1 | 2 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 | YES | 1 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 | [5 empty] | # risk events (excluding ignitions) |  | Not Applicable

## Table 6
| Utility | BVES | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-08-01
[7 empty] | Actual number of ignitions | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q2
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | YES | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | YES | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | [5 empty] | # ignitions |  | Not Applicable
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | [5 empty] | # ignitions |  | Not Applicable
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | [5 empty] | # ignitions |  | Not Applicable

## Table 7
| Utility | BVES
| Table No. | 7
| Date Modified | 2024-08-01
[7 empty] | Actual | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q2
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 453.07 | 457.28 | 457.28 | 457.28 | Circuit miles | Adjusted to reflect total overhead circuit miles (primary & secondary) based off of updated guidance
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 122.06 | 117.6 | 117.6 | 117.6 | Circuit miles | Adjusted to reflect total overhead circuit miles (primary & secondary) based off of updated guidance
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 1.64 | 1.64 | 1.64 | 1.64 | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 103.72 | 106.28 | 106.28 | 106.28 | Circuit miles | Adjusted to reflect total overhead circuit miles (primary & secondary) based off of updated guidance
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 36.7 | 34.06 | 34.06 | 34.06 | Circuit miles | Adjusted to reflect total overhead circuit miles (primary & secondary) based off of updated guidance
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 12 | 12 | 12 | 12 | Number of critical facilities
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of critical facilities
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 2 | 2 | 2 | 2 | Number of critical facilities
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of critical facilities
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of critical facilities
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of critical facilities
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of critical facilities
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of critical facilities
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of critical facilities |  | Not Applicable
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 17829 |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of residential customers
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 5465 |  |  |  | Number of residential customers
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of residential customers
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of residential customers
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of residential customers
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of residential customers
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of residential customers
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of residential customers |  | Not Applicable
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of residential customers |  | Not Applicable
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 1176 |  |  |  | Number of commercial customers
|  | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of commercial customers
|  | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 312 |  |  |  | Number of commercial customers
|  | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of commercial customers
|  | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of commercial customers
|  | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of commercial customers
|  | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Number of commercial customers
|  | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of commercial customers
|  | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
|  | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of commercial customers |  | Not Applicable
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 412 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of customers belonging to access and functional needs populations
|  | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 121 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of customers belonging to access and functional needs populations
|  | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of customers belonging to access and functional needs populations
|  | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of customers belonging to access and functional needs populations
|  | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of customers belonging to access and functional needs populations
|  | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of customers belonging to access and functional needs populations
|  | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
|  | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of customers belonging to access and functional needs populations |  | Not Applicable
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 8 | 8 | 8 | 8 | Number of substations
|  | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 5 | 5 | 5 | 5 | Number of substations
|  | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Number of substations
|  | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 9 | 9 | 9 | 9 | Number of weather stations
|  | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 9 | 9 | 9 | 9 | Number of weather stations
|  | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 2 | 2 | 2 | 2 | Number of weather stations
|  | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable

## Table 8
| Utility | BVES |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2024-08-01 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q2
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable

## Table 9
| Utility | BVES
| Table No. | 9
| Date Modified | 2024-08-01
[7 empty] | Actual | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q2
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0.23 | 12.9 | 12.9 | 12.9 | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 5.61 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | Not Applicable
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | Not Applicable
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of substations |  | Not Applicable
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of substations |  | Not Applicable
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | Not Applicable
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | Not Applicable

## Table 10
Utility | BVES |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2024-08-01 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q2
Metric type | # | Wind Warning Status | Metric name | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW only | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW & RFW | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | All (regardless of RFW/HWW status) | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.b. | RFW only | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW only | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW & RFW | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | All (regardless of RFW/HWW status) | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
| 1.c. | RFW only | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW only | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW & RFW | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
|  | All (regardless of RFW/HWW status) | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
| 1.d. | RFW only | Frequency of fast-trip events (total) | 0 | 0 | 0 | 0 | Number of events | The numbers found in this row represent unplanned outages in which a TripSaver was actuated. BVES does not adjust its TripSaver curve but instead adjusts the number of shots based off the season
|  | HWW only | Frequency of fast-trip events (total) | 0 | 0 | 0 | 0 | Number of events | The numbers found in this row represent unplanned outages in which a TripSaver was actuated. BVES does not adjust its TripSaver curve but instead adjusts the number of shots based off the season
|  | HWW & RFW | Frequency of fast-trip events (total) | 0 | 0 | 0 | 0 | Number of events | The numbers found in this row represent unplanned outages in which a TripSaver was actuated. BVES does not adjust its TripSaver curve but instead adjusts the number of shots based off the season
|  | None | Frequency of fast-trip events (total) | 0 | 0 | 0 | 0 | Number of events | The numbers found in this row represent unplanned outages in which a TripSaver was actuated. BVES does not adjust its TripSaver curve but instead adjusts the number of shots based off the season
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | 0 | 0 | 0 | 0 | Circuit mile days | BVES does not adjust its TripSaver curves but instead adjusts the number of shots based off the season
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | 0 | 0 | 0 | 0 | Circuit mile days | BVES does not adjust its TripSaver curves but instead adjusts the number of shots based off the season
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | 0 | 0 | 0 | 0 | Circuit mile days | BVES does not adjust its TripSaver curves but instead adjusts the number of shots based off the season
|  | None | Circuit mile days with fast-trip settings enabled (total) | 0 | 0 | 0 | 0 | Circuit mile days | BVES does not adjust its TripSaver curves but instead adjusts the number of shots based off the season
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | 0 | 5544.4 | 5544.4 | 5544.4 | Total customer hours of planned outages per year
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | 1750.9833 | 304677.4167 | 304677.4167 | 304677.4167 | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | 0 | 0 | 0 | 0 | Total customer hours of outages due to fast-trip per year | The numbers found in this row represent unplanned outages in which a TripSaver was actuated. BVES does not adjust its TripSaver curve but instead adjusts the number of shots based off the season
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | 4.3 | 677.7006 | 677.7006 | 677.7006 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | 4.3 | 677.7006 | 677.7006 | 677.7006 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | 0.19429 | 10.1812 | 10.1812 | 10.1812 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | 0.19429 | 10.1812 | 10.1812 | 10.1812 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | 0 | 0 | 0 | 0 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | 0 | 0 | 0 | 0 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
4. Community outreach of PSPS metrics | 4.b. | N/A | # of medical baseline customers impacted by PSPS | 0 | 0 | 0 | 0 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
4. Community outreach of PSPS metrics | 4.c. | N/A | # of customers notified prior to initiation of PSPS event | 0 | 0 | 0 | 0 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | 0 | 0 | 0 | 0 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | 0 | 0 | 0 | 0 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | 0 | 0 | 0 | 0 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | 0 | 0 | 0 | 0 | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | 0 | 0 | 0 | 0 | Number of customers
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | 0 | 0 | 0 | 0 | =1.c. / RFW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | 0 | 0 | 0 | 0 | =1.c. / HWW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | 0 | 0 | 0 | 0 | =1.c. / FPI OH circuit mile days in time period
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | 0 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | 0 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | 0 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | 0 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | 0 | 0 | 0 | 0 | Number of risk events

## Table 11
Utility | BVES | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2024-08-01 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actuals |  |  |  | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2024 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Community Outreach and Engagement | Public outreach and education awareness program | COE_1 | PSPS Vulnerability | N/A | 2019 | NA | WMPMA | In Compliance | GO 166 | NA | [5 empty] | 0 | 0 | 90 | 90 | 0 | 0 | 92.7 | 92.7 | 0 | 0 | 95.481 | 95.481
Community Outreach and Engagement | Engagement with access and functional needs populations | COE_2 | PSPS Vulnerability | N/A | 2020 | NA | WMPMA | In Compliance | GO 166 | NA | [5 empty] | 0 | 0 | 30 | 30 | 0 | 0 | 30.9 | 30.9 | 0 | 0 | 31.827 | 31.827
Community Outreach and Engagement | Collaboration on local wildfire mitigation planning | COE_3 | Wildfire Hazard | Wildfire Spread | 2019 | NA | NA | In Compliance | GO 166 | NA | [5 empty] | 0 | 0 | 22.631 | 22.631 | 0 | 0 | 23.31 | 23.31 | 0 | 0 | 24.009 | 24.009
Community Outreach and Engagement | Best practice sharing with other utilities | COE_4 | Wildfire Hazard | Wildfire Hazard | 2019 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 14.796 | 14.796 | 0 | 0 | 15.24 | 15.24 | 0 | 0 | 15.697 | 15.697
Emergency Preparedness | Emergency preparedness plan | EP_1 | Wildfire Vulnerability | Wildfire Hazard | 2018 | D. 19-08-027 | NA | In Compliance | GO 166 | NA | [5 empty] | 0 | 0 | 4.685 | 4.685 | 0 | 0 | 4.826 | 4.826 | 0 | 0 | 4.971 | 4.971
Emergency Preparedness | External collaboration and coordination | EP_2 | Wildfire Vulnerability | Wildfire Hazard | 2019 | NA | WMPMA | In Compliance | GO 166 | NA | [5 empty] | 0 | 0 | 21.398 | 21.398 | 0 | 0 | 22.04 | 22.04 | 0 | 0 | 22.701 | 22.701
Emergency Preparedness | Public emergency communication strategy | EP_3 | Wildfire Vulnerability | Wildfire Hazard | 2019 | NA | WMPMA | In Compliance | GO 166 | NA | [5 empty] | 0 | 0 | 4.192 | 4.192 | 0 | 0 | 4.318 | 4.318 | 0 | 0 | 4.448 | 4.448
Emergency Preparedness | Preparedness and planning for service restoration | EP_4 | Wildfire Vulnerability | Wildfire Hazard | 2019 | NA | CEMA, if applicable | In Compliance | GO 166 | NA | [5 empty] | 0 | 0 | 5.672 | 5.672 | 0 | 0 | 5.842 | 5.842 | 0 | 0 | 6.017 | 6.017
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | EP_5 | Wildfire Vulnerability | Wildfire Hazard | 2019 | NA | WMPMA | In Compliance | R. 18-12-005 | NA | [5 empty] | 0 | 0 | 3.452 | 3.452 | 0 | 0 | 3.556 | 3.556 | 0 | 0 | 3.663 | 3.663
Grid Design, Operations, and Maintenance | Covered conductor installation | GD_1 | Contact from vegetation ignition likelihood | Wildfire Vulnerability | 2019 | NA | WMPMA | NA | NA | NA | [5 empty] | 4785.701 | 4785.701 | 0 | 0 | 4737.29 | 4737.29 | 0 | 0 | 4655.694 | 4655.694 | 0 | 0
Grid Design, Operations, and Maintenance | Covered conductor installation | GD_2 | Contact from vegetation ignition likelihood | Wildfire Vulnerability | 2019 | NA | WMPMA | NA | NA | NA | [5 empty] | 4340.243 | 4340.243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | GD_19 | Contact from vegetation ignition likelihood | Equipment ignition likelihood | NA | NA | NA | NA | NA | NA | [5 empty] | 605.612 | 605.612 | 0 | 0 | 607.223 | 607.223 | 0 | 0 | 592.681 | 592.681 | 0 | 0
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | GD_20 | N/A | N/A | NA | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GD_21 | PSPS Exposure Potential | PSPS Vulnerability | NA | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 561.55 | 561.55 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GD_22 | PSPS Exposure Potential | PSPS Vulnerability | NA | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 1777.479 | 1777.479 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GD_23 | PSPS Exposure Potential | PSPS Vulnerability | NA | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065.781 | 2065.781 | 0 | 0
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GD_24 | PSPS Exposure Potential | PSPS Vulnerability | NA | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144.054 | 1144.054 | 0 | 0
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | GD_3 | Contact from vegetation ignition likelihood | Equipment ignition likelihood | NA | NA | NA | In Compliance | NA | NA | [5 empty] | 200 | 200 | 0 | 0 | 303.68 | 303.68 | 0 | 0 | 301.226 | 301.226 | 0 | 0
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | GD_4 | Wildfire Vulnerability | Wildfire hazard | 2018 | D. 19-08-027 | NA | In Compliance | GO 95 | NA | [5 empty] | 2051.015 | 2051.015 | 0 | 0 | 2030.267 | 2030.267 | 0 | 0 | 2789.368 | 2789.368 | 0 | 0
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | GD_5 | Wildfire Vulnerability | Wildfire hazard | 2018 | D. 19-08-027 | NA | In Compliance | GO 95 | NA | [5 empty] | 1860.104 | 1860.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | GD_6 | Wildfire Vulnerability | Wildfire hazard | 2018 | D. 19-08-027 | NA | In Compliance | GO 95 | NA | [5 empty] | 816.243 | 816.243 | 0 | 0 | 807.986 | 807.986 | 0 | 0 | 794.07 | 794.07 | 0 | 0
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | GD_7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | BVES does not have any Transmission Lines in their System | [16 empty] | Not Applicable
Grid Design, Operations, and Maintenance | Traditional overhead hardening | GD_8 | Equipment ignition likelihood | Contact by object ignition | 2019 | N/A | N/A | N/A | N/A | NA | [5 empty] | 500 | 500 | 0 | 0 | 809.814 | 809.814 | 0 | 0 | 803.269 | 803.269 | 0 | 0
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots | GD_9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Microgrids | GD_10 | PSPS Exposure Potential | PSPS Vulnerability | N/A | N/A | N/A | N/A | N/A | NA | [5 empty] | 0 | 0 | 0 | 0 | 13578.409 | 13578.409 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Microgrids | GD_11 | PSPS Exposure Potential | PSPS Vulnerability | N/A | N/A | N/A | N/A | N/A | NA | [5 empty] | 0 | 0 | 0 | 0 | 10342.009 | 10342.009 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_12 | Equipment ignition likelihood | Contact by object ignition | 2019 | D. 19-08-027 | NA | In Compliance | NA | NA | [5 empty] | 654.139 | 654.139 | 0 | 0 | 655.88 | 655.88 | 0 | 0 | 640.172 | 640.172 | 0 | 0
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_13 | Equipment ignition likelihood | Contact by object ignition | 2019 | D. 19-08-027 | NA | In Compliance | NA | NA | [5 empty] | 711.05 | 711.05 | 0 | 0 | 673.608 | 673.608 | 0 | 0 | 640.172 | 640.172 | 0 | 0
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_14 | Equipment ignition likelihood | Contact by object ignition | 2019 | D. 19-08-027 | NA | In Compliance | NA | NA | [5 empty] | 345.024 | 345.024 | 0 | 0 | 319.11 | 319.11 | 0 | 0 | 311.468 | 311.468 | 0 | 0
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_15 | Equipment ignition likelihood | Contact by object ignition | 2019 | D. 19-08-027 | NA | In Compliance | NA | NA | [5 empty] | 197.645 | 197.645 | 0 | 0 | 136.879 | 136.879 | 0 | 0 | 133.601 | 133.601 | 0 | 0
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_16 | Equipment ignition likelihood | Contact by object ignition | 2019 | D. 19-08-027 | NA | In Compliance | NA | NA | [5 empty] | 126.7 | 126.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_17 | Equipment ignition likelihood | Contact by object ignition | 2019 | D. 19-08-027 | NA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 37.407 | 37.407 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Line removals (in HFTD) | GD_18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A | [16 empty] | BVES has not nor does it have plans to remove line miles. Its whole service territory is HFTD.
Grid Design, Operations, and Maintenance | Asset inpsections | GD_25 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 13.5 | 13.5 | 0 | 0 | 13.905 | 13.905 | 0 | 0 | 14.322 | 14.322
Grid Design, Operations, and Maintenance | Asset inpsections | GD_26 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 31.5 | 31.5 | 0 | 0 | 32.445 | 32.445 | 0 | 0 | 33.418 | 33.418
Grid Design, Operations, and Maintenance | Asset inpsections | GD_27 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 56.295 | 56.295 | 0 | 0 | 53.651 | 53.651 | 0 | 0 | 54.036 | 54.036
Grid Design, Operations, and Maintenance | Asset inpsections | GD_28 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 56.295 | 56.295 | 0 | 0 | 53.651 | 53.651 | 0 | 0 | 54.036 | 54.036
Grid Design, Operations, and Maintenance | Asset inpsections | GD_29 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 57.873 | 57.873 | 0 | 0 | 55.154 | 55.154 | 0 | 0 | 55.55 | 55.55
Grid Design, Operations, and Maintenance | Asset inpsections | GD_30 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 46.707 | 46.707 | 0 | 0 | 44.513 | 44.513 | 0 | 0 | 44.832 | 44.832
Grid Design, Operations, and Maintenance | Asset inpsections | GD_31 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 18.54 | 18.54 | 0 | 0 | 19.096 | 19.096 | 0 | 0 | 19.669 | 19.669
Grid Design, Operations, and Maintenance | Asset inpsections | GD_32 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 275 | 275 | 0 | 0 | 283.25 | 283.25 | 0 | 0 | 291.748 | 291.748
Grid Design, Operations, and Maintenance | Equipment inspections, maintenance, and repair | GD_33 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 1041.919 | 1041.919 | 0 | 0 | 1073.177 | 1073.177 | 0 | 0 | 1105.372 | 1105.372
Grid Design, Operations, and Maintenance | Asset managmenet and inspection enterprise system(s) | GD-34 | Equipment ignition likelihood | Contact by object ignition | 2022 | NA | WMPMA | In Compliance | GO-165 | NA | [5 empty] | 0 | 0 | 56 | 56 | 0 | 0 | 57.68 | 57.68 | 0 | 0 | 59.41 | 59.41
Grid Design, Operations, and Maintenance | Quality assurance / quality control | GD_35 | Equipment ignition likelihood | Contact by object ignition | 2020 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 19.728 | 19.728 | 0 | 0 | 20.32 | 20.32 | 0 | 0 | 20.93 | 20.93
Grid Design, Operations, and Maintenance | Open work orders | GD_36 | Equipment ignition likelihood | Contact by object ignition | 2023 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 17.262 | 17.262 | 0 | 0 | 17.78 | 17.78 | 0 | 0 | 18.314 | 18.314
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk (Grid Ops) | GD_37 | Equipment ignition likelihood | Contact by object ignition | NA | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 4.932 | 4.932 | 0 | 0 | 5.08 | 5.08 | 0 | 0 | 5.232 | 5.232
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications (Grid Ops) | GD_38 | Equipment ignition likelihood | Contact by object ignition | 2019 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 8.631 | 8.631 | 0 | 0 | 8.89 | 8.89 | 0 | 0 | 9.517 | 9.517
Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk (Grid Ops) | GD_39 | Wildfire Spread | Wildfire vulnerability | 2029 | NA | NA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 3.699 | 3.699 | 0 | 0 | 3.81 | 3.81 | 0 | 0 | 3.924 | 3.924
Grid Design, Operations, and Maintenance | Workforce Planning | GD_40 | Equipment ignition likelihood | Contact by object ignition | 2023 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 6.165 | 6.165 | 0 | 0 | 6.35 | 6.35 | 0 | 0 | 6.541 | 6.541
Overview of the Service Territory | Environmental compliance and permitting | ST_1 | Wildfire Hazard | Wildfire Vulnerability | 2023 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 24.66 | 24.66 | 0 | 0 | 25.4 | 25.4 | 0 | 0 | 26.162 | 26.162
Risk Methodology and Assessment | Risk Methodology and Assessment | RMA_1 | Wildfire Hazard | Wildfire Vulnerability | 2021 | NA | WMPMA | NA | NA | NA | [5 empty] | 0 | 0 | 64.409 | 64.409 | 0 | 0 | 61.383 | 61.383 | 0 | 0 | 61.824 | 61.824
Situational Awareness and Forecasting | Environmental monitoring systems | SAF_1 | PSPS likelihood | PSPS Exposure Potential | 2019 | NA | WMPMA | In Compliance | GO 95 | NA | [5 empty] | 0 | 0 | 7.101 | 7.101 | 0 | 0 | 7.314 | 7.314 | 0 | 0 | 7.533 | 7.533
Situational Awareness and Forecasting | Grid monitoring systems | SAF_2 | Equipment ignition likelihood | Wildfire Hazard | 2022 | NA | WMPMA | Exceeding Compliance | GO 95 | NA | [5 empty] | 360.121 | 360.121 | 0 | 0 | 77.251 | 77.251 | 0 | 0 | 75.92 | 75.92 | 0 | 0
Situational Awareness and Forecasting | Ignition detection systems | SAF_4 | Wildfire Spread | Wildfire Exposure Potential | NA | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Complete and Fully Operational
Situational Awareness and Forecasting | Weather forecasting | SAF_5 | PSPS likelihood | PSPS Exposure Potential | 2018 | NA | WMPMA | Exceeding Compliance | ESRB-8 | NA | [5 empty] | 0 | 0 | 51.277 | 51.277 | 0 | 0 | 48.867 | 48.867 | 0 | 0 | 49.219 | 49.219
Situational Awareness and Forecasting | Fire potential index | SAF_6 | PSPS likelihood | PSPS Exposure Potential | 2023 | N/A | WMPMA | N/A | GO 166 Standard 1.E | NA | [5 empty] | 0 | 0 | 38.645 | 38.645 | 0 | 0 | 36.83 | 36.83 | 0 | 0 | 37.094 | 37.094
Situational Awareness and Forecasting | Grid monitoring systems | SAF_7 | PSPS likelihood | PSPS Exposure Potential | 2023 | N/A | WMPMA | N/A | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 130 | 130 | 0 | 0 | 10 | 10 | 0 | 0
Vegetation Management and Inspection | Vegetation Inspections | VM_1 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | D.19-08-027 | NA | Exceeding Compliance | GO-95 | [6 empty] | 0 | 0 | 13.5 | 13.5 | 0 | 0 | 13.905 | 13.905 | 0 | 0 | 14.322 | 14.322
Vegetation Management and Inspection | Vegetation Inspections | VM_2 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | D.19-08-027 | NA | Exceeding Compliance | GO-95 | [6 empty] | 0 | 0 | 31.5 | 31.5 | 0 | 0 | 32.445 | 32.445 | 0 | 0 | 33.418 | 33.418
Vegetation Management and Inspection | Vegetation Inspections | VM_3 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | D.19-08-027 | NA | Exceeding Compliance | GO-95 | [6 empty] | 0 | 0 | 58.001 | 58.001 | 0 | 0 | 55.277 | 55.277 | 0 | 0 | 55.673 | 55.673
Vegetation Management and Inspection | Vegetation Inspections | VM_4 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | D.19-08-027 | NA | Exceeding Compliance | GO-95 | [6 empty] | 0 | 0 | 57.873 | 57.873 | 0 | 0 | 55.154 | 55.154 | 0 | 0 | 55.55 | 55.55
Vegetation Management and Inspection | Vegetation Inspections | VM_5 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | D.19-08-027 | NA | Exceeding Compliance | GO-95 | [6 empty] | 0 | 0 | 46.707 | 46.707 | 0 | 0 | 44.513 | 44.513 | 0 | 0 | 44.832 | 44.832
Vegetation Management and Inspection | Vegetation Inspections | VM_6 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | D.19-08-027 | NA | Exceeding Compliance | GO-95 | [6 empty] | 0 | 0 | 4.25 | 4.25 | 0 | 0 | 4.378 | 4.378 | 0 | 0 | 4.509 | 4.509
Vegetation Management and Inspection | Pole clearing | VM_7 | Contact from vegetation ignition likelihood | Wildfire Hazard | N/A | N/A | NA | N/A | N/A | N/A | N/A | [16 empty] | Not Applicable
Vegetation Management and Inspection | Wood and slash management | VM_8 | Wildfire Spread | Wildfire Hazard | 2018 | NA | FHPMA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 417.312 | 417.312 | 0 | 0 | 418.749 | 418.749 | 0 | 0 | 423.386 | 423.386
Vegetation Management and Inspection | Clearance | VM_9 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | NA | FHPMA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 1761.687 | 1761.687 | 0 | 0 | 1766.513 | 1766.513 | 0 | 0 | 1786.607 | 1786.607
Vegetation Management and Inspection | Fall-in mitigation | VM_10 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | NA | FHPMA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 282.875 | 282.875 | 0 | 0 | 283.973 | 283.973 | 0 | 0 | 287.064 | 287.064
Vegetation Management and Inspection | Substation defensible space | VM_11 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | D.19-08-027 | NA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 15 | 15 | 0 | 0 | 15.45 | 15.45 | 0 | 0 | 15.914 | 15.914
Vegetation Management and Inspection | High-risk species | VM_12 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | NA | FHPMA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 282.875 | 282.875 | 0 | 0 | 283.973 | 283.973 | 0 | 0 | 287.064 | 287.064
Vegetation Management and Inspection | Fire-resillient right-of-ways | VM_13 | Wildfire Spread | Wildfire Hazard | 2023 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 14 | 14 | 0 | 0 | 14.42 | 14.42 | 0 | 0 | 14.583 | 14.583
Vegetation Management and Inspection | Emergency response vegetation management | VM_14 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2019 | NA | NA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 24.604 | 24.604 | 0 | 0 | 25.342 | 25.342 | 0 | 0 | 26.102 | 26.102
Vegetation Management and Inspection | Vegetation management enterprise system | VM_15 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2021 | NA | NA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 21 | 21 | 0 | 0 | 21.63 | 21.63 | 0 | 0 | 22.279 | 22.279
Vegetation Management and Inspection | Quality assurance / quality control | VM_16 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2018 | NA | NA | In Compliance | NA | NA | [5 empty] | 0 | 0 | 46.059 | 46.059 | 0 | 0 | 47.44 | 47.44 | 0 | 0 | 48.863 | 48.863
Vegetation Management and Inspection | Open work orders | VM_17 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2023 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 31.262 | 31.262 | 0 | 0 | 32.2 | 32.2 | 0 | 0 | 33.166 | 33.166
Vegetation Management and Inspection | Workforce Planning | VM_18 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2023 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 6.165 | 6.165 | 0 | 0 | 6.35 | 6.35 | 0 | 0 | 6.541 | 6.541
Vegetation Management and Inspection | Vegetation Inspections | VM_19 | Contact from vegetation ignition likelihood | Wildfire Hazard | 2024 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 40 | 40 | 0 | 0
Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development | WMSD_1 | Wildfire Hazard | Wildfire Vulnerability | 2023 | NA | NA | NA | NA | NA | [5 empty] | 0 | 0 | 29.592 | 29.592 | 0 | 0 | 30.48 | 30.48 | 0 | 0 | 31.395 | 31.395

## Table 12
Utility | BVES | Notes:
Table No. | 12
Date Modified | 2024-08-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | Method of Verification | Comments
Overview of the Service Territory | Environmental compliance and permitting | ST_1 | Qualitative | Annual Review and Update | Continued Review Process | Continued Review Process | Annual Review and Update | Continued Review Process | Continued Review Process | Annual Review and Update | Continued Review Process | Annual Review and Update | Annual Review and Update | Version History
Risk Methodology and Assessment | Risk Methodology and Assessment | RMA_1 | Qualitative | Maintain real time risk mapping | Maintain real time risk mapping | Maintain real time risk mapping | Maintain real time risk mapping | Maintain real time risk mapping | Maintain real time risk mapping | Maintain real time risk mapping | Maintain real time risk mapping | Maintain real time risk mapping | Maintain real time risk mapping | Version History
Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development | WMSD_1 | Qualitative | Develop and Issue WMP | Review WMP Comments | Update WMP | Finalize and Issue WMP | Review WMP Comments | Update WMP | Finalize and Issue WMP | Update WMP | Finalize and Issue WMP | Finalize and Issue WMP | Version History
Grid Design, Operations, and Maintenance | Covered conductor installation | GD_1 | Quantitative | Circuit Miles of Line Replaced | 2.5 | 8.9 | 12.9 | 2.5 | 8.9 | 12.9 | 1 | 3 | 5.1 | Quantitative
Grid Design, Operations, and Maintenance | Covered conductor installation | GD_2 | Quantitative | Circuit Miles of Line Replaced | 0 | 0 | 0 | 0 | 0 | 2.7 | 0 | 0 | 0 | Quantitative | BVES has updated the targets to reflect the change to the project timeline due to USFS permitting issue. BVES has continued to update EnergySafety regarding this issue and made EnergySafety aware that the permit has been signed.
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | GD_3 | Qualitative | Initaite Underground Projects as needed (% of Budget) | 20% | 60% | 100% | 20% | 60% | 100% | 20% | 60% | 100% | Budget Review
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | GD_4 | Quantitative | Number of Poles Replaced | 80 | 140 | 200 | 80 | 140 | 200 | 80 | 100 | 100 | Quantitative
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | GD_5 | Quantitative | Number of Poles Replaced | 0 | 0 | 0 | 10 | 40 | 70 | 0 | 0 | 0 | Quantitative | BVES has updated the targets to reflect the change to the project timeline due to USFS permitting issue. BVES has continued to update EnergySafety regarding this issue and made EnergySafety aware that the permit has been signed.
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | GD_6 | Quantitative | Number of Poles that had Wire Mesh Installed on them. | 300 | 400 | 500 | 300 | 400 | 500 | 300 | 400 | 500 | Quantitative
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | GD_7 |  | N/A | [10 empty] | BVES does not own or operate any transmission lines.
Grid Design, Operations, and Maintenance | Traditional overhead hardening | GD_8 | Qualitative | As Needed Maintenance (% of Budget) | 50% | 75% | 100% | 50% | 75% | 100% | 50% | 75% | 100% | Budget Review
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots | GD_9 |  | N/A | [10 empty] | BVES does not have any pilot projects or programs for novel grid hardening technology. BVES is following what other larger electric utilties are doing regarding grid hardening technology as well as participating in industry conferences and trade shows to keep current on any emerging grid hardening technologies. BVES will certainly pilot any promising grid hardening technologies that would work well in BVES's service area and system.
Grid Design, Operations, and Maintenance | Microgrids | GD_10 | Qualitative | Preform Necessary Project Action | No Action | No Action | No Action | Prepare Application | Prepare Application | File Application | No Action | No Action | No Action | Project Timeline and Budget
Grid Design, Operations, and Maintenance | Microgrids | GD_11 | Qualitative | Preform Necessary Project Action | No Action | No Action | No Action | Prepare Application & Permitting Paperwork | Prepare Application & Permitting Paperwork | File Application & Obtain Permit | No Action | No Action | No Action | Project Timeline and Budget
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_12 | Quantitative | Number of Substations Automated and Connected ot SCADA | 0 | 2 | 3 | 0 | 2 | 3 | 0 | 2 | 3 | Quantitative
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_13 | Quantitative | Number of Field Switches Automated and Connected to SCADA | 0 | 6 | 13 | 5 | 8 | 10 | 0 | 8 | 11 | Quantitative
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_14 | Quantitative | Number of Capacitor Banks Replaced and Connected to SCADA | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | Quantitative
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_15 | Quantitative | Number of Fuse TripSavers Automated and Connected to SCADA | 0 | 6 | 10 | 30 | 40 | 50 | 30 | 40 | 50 | Quantitative
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_16 | Qualitative | Project Milestones for Server Insillation | 16% Project Completion | 24% | 32% | 48% | 56% | 64% | 72% | 80% | 100% Project Completion | Project Timeline and Budget
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GD_17 | Qualitative | Project Milestones for Distribution Management Center | No Action | No Action | No Action | 25% Project Completion | 35% Project Completion | 50% Project Completion | 65% Project Completion | 80% Project Completion | 100% Project Completion | Project Timeline and Budget
Grid Design, Operations, and Maintenance | Line removals (in HFTD) | GD_18 |  | N/A | [10 empty] | BVES does not have any line removel projects planned.
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | GD_19 | Quantitative | Number of Tree Attachments Removed | 0 | 50 | 100 | 0 | 50 | 100 | 0 | 50 | 100 | Quantitative
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events | GD_20 |  | N/A | [10 empty] | The objectives of this initiative are achieved through BVES's installation of system automation equipment initiatives.
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GD_21 | Qualitative | Project Milesstones for Propane Engine Upgrades | 16% Project Completion | 24% | 32% | 48% | 56% | 64% | 72% | 80% | 100% Project Completion | Project Timeline and Budget
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GD_22 | Qualitative | Project Milesstones for Maltby Substation | 16% Project Completion | 24% | 32% | 48% | 56% | 64% | 72% | 80% | 100% Project Completion | Project Timeline and Budget
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GD_23 | Qualitative | Project Milesstones for Lake Substation | 0% Project Completion | 0% | 0% | 16% | 24% | 32% | 48% | 56% | 64% Project Completion | Project Timeline and Budget
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above | GD_24 | Qualitative | Project Milesstones for Village Substation | 0% Project Completion | 0% | 0% | 0% | 0% | 0% | 16% | 24% | 32% Project Completion | Project Timeline and Budget
Grid Design, Operations, and Maintenance | Asset inspections | GD_25 | Quantitative | Circuit Miles Inspected | 88 | 88 | 134.5 | 0 | 40 | 51.35 | 0 | 20 | 53 | Quantitative
Grid Design, Operations, and Maintenance | Asset inspections | GD_26 | Quantitative | Circuit Miles Inspected | 105 | 158 | 205 | 105 | 158 | 205 | 102 | 153 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Grid Design, Operations, and Maintenance | Asset inspections | GD_27 | Quantitative | Circuit Miles Inspected | 0 | 205 | 205 | 0 | 205 | 205 | 0 | 205 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Grid Design, Operations, and Maintenance | Asset inspections | GD_28 | Quantitative | Circuit Miles Inspected | 0 | 205 | 205 | 0 | 205 | 205 | 0 | 205 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Grid Design, Operations, and Maintenance | Asset inspections | GD_29 | Quantitative | Circuit Miles Inspected | 0 | 205 | 205 | 0 | 205 | 205 | 0 | 205 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Grid Design, Operations, and Maintenance | Asset inspections | GD_30 | Quantitative | Circuit Miles Inspected | 0 | 205 | 205 | 0 | 205 | 205 | 0 | 205 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Grid Design, Operations, and Maintenance | Asset inspections | GD_31 | Quantitative | Number of Poles Intrusively Inspected | 0 | 850 | 850 | 0 | 300 | 850 | 0 | 300 | 850 | Quantitative
Grid Design, Operations, and Maintenance | Asset inspections | GD_32 | Quantitative | Number of Substations Inspected | 72 | 108 | 144 | 72 | 108 | 144 | 72 | 108 | 144 | Quantitative
Grid Design, Operations, and Maintenance | Equipment maintenance and repair | GD_33 | Qualitative | As Needed Maintenance (% of Budget) | 50% | 75% | 100% | 50% | 75% | 100% | 50% | 75% | 100% | Budget Review
Grid Design, Operations, and Maintenance | Asset management and inspection enterprise system(s) | GD_34 | Qualitative | Maintainance of Asset Management System | 50% | 75% | 100% | 50% | 75% | 100% | 50% | 75% | 100% | Budget Review
Grid Design, Operations, and Maintenance | Quality assurance / quality control | GD_35 | Quantitative | Number of Asset QCs on WMP Work | 10 | 15 | 20 | 10 | 15 | 20 | 10 | 15 | 20 | Quantitative
Grid Design, Operations, and Maintenance | Open work orders | GD_36 | Qualitative | No descrep exceeding GO95 resolution timeframes | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | WO Log
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk | GD_37 | Qualitative | Review and Evaluate System Settings | Review and Evaluate System Settings | Review and Evaluate System Settings | Review and Evaluate System Settings | Review and Evaluate System Settings | Review and Evaluate System Settings | Review and Evaluate System Settings | Review and Evaluate System Settings | Review and Evaluate System Settings | Review and Evaluate System Settings | Meeting Minutes
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications | GD_38 | Qualitative | Review and Update Procedure Annually | Review and Update Procedure | Review and Update Procedure | Finalize Review | Review and Update Procedure | Review and Update Procedure | Finalize Review | Review and Update Procedure | Review and Update Procedure | Finalize Review | Version History
Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk | GD_39 | Qualitative | Review and Update Procedure Annually. Verification of Trainging Annual | Review and Update Procedure | Review and Update Procedure | Finalize Review | Review and Update Procedure | Review and Update Procedure | Finalize Review | Review and Update Procedure | Review and Update Procedure | Finalize Review | Version History
Grid Design, Operations, and Maintenance | Workforce Planning | GD_40 | Qualitative | Verify Approraite Staffing Levels for Wildfire Related Activities | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Meeting Minutes
Vegetation Management and Inspection | Vegetation inspections | VM_1 | Quantitative | Circuit Miles Inspected | 88 | 88 | 134.5 | 0 | 40 | 51.35 | 0 | 20 | 53 | Quantitative
Vegetation Management and Inspection | Vegetation inspections | VM_2 | Quantitative | Circuit Miles Inspected | 105 | 158 | 205 | 105 | 158 | 205 | 102 | 153 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Vegetation Management and Inspection | Vegetation inspections | VM_3 | Quantitative | Circuit Miles Inspected | 0 | 205 | 205 | 0 | 205 | 205 | 0 | 205 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Vegetation Management and Inspection | Vegetation inspections | VM_4 | Quantitative | Circuit Miles Inspected | 0 | 205 | 205 | 0 | 205 | 205 | 0 | 205 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Vegetation Management and Inspection | Vegetation inspections | VM_5 | Quantitative | Circuit Miles Inspected | 0 | 205 | 205 | 0 | 205 | 205 | 0 | 205 | 205 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Vegetation Management and Inspection | Vegetation inspections | VM_6 | Quantitative | Number of Substations Inspected | 72 | 108 | 144 | 72 | 108 | 144 | 72 | 108 | 144 | Quantitative | Adjusted annual target to reflect new total primary overhead circuit miles following GIS layers updates
Vegetation Management and Inspection | Pole clearing | VM_7 |  | N/A | [10 empty] | Plan and execution of vegetation removal around poles per Public Resources Code section 4292 and outside the requirements of Public Resources Code section 4292 (e.g., pole clearing performed outside of the State Responsibility Area).
Vegetation Management and Inspection | Wood and slash management | VM_8 | Qualitative | Contractor Adhered to Waste Removal | Waste Removal Requirements Met | Waste Removal Requirements Met | Waste Removal Requirements Met | Waste Removal Requirements Met | Waste Removal Requirements Met | Waste Removal Requirements Met | Waste Removal Requirements Met | Waste Removal Requirements Met | Waste Removal Requirements Met | Contract Status
Vegetation Management and Inspection | Clearance | VM_9 | Quantitative | Circuit Miles Cleared | 36 | 54 | 72 | 36 | 54 | 72 | 36 | 54 | 72 | Quantitative
Vegetation Management and Inspection | Fall-in mitigation | VM_10 | Quantitative | Number of trees remediated or removed to prevent fall-in | 44 | 66 | 88 | 44 | 66 | 88 | 44 | 66 | 88 | Quantitative
Vegetation Management and Inspection | Substation defensible space | VM_11 | Quantitative | Substations inspected and cleared | 8 | 13 | 13 | 8 | 13 | 13 | 8 | 13 | 13 | Quantitative
Vegetation Management and Inspection | High-risk species | VM_12 | Qualitative | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | Version History
Vegetation Management and Inspection | Fire-resilient rights-of-way | VM_13 | Qualitative | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | WMP Plan Review and Vegetation Discussion with Experts | Version History
Vegetation Management and Inspection | Emergency response vegetation management | VM_14 | Qualitative | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Verification of Readiness and Review of Plan | Version History
Vegetation Management and Inspection | Vegetation management enterprise system | VM_15 | Qualitative | Ongoing Monitoring and Maintenance | 50% | 75% | 100% | 50% | 75% | 100% | 50% | 75% | 100% | Budget Review
Vegetation Management and Inspection | Quality assurance / quality control | VM_16 | Quantitative | Number of Vegetation Management Audits | 36 | 54 | 72 | 36 | 54 | 72 | 36 | 54 | 72 | Quantitative
Vegetation Management and Inspection | Open work orders | VM_17 | Qualitative | No descrep exceeding GO95 resolution timeframes | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | All WO resolved within GO 95 Timeframe | WO Log
Vegetation Management and Inspection | Workforce planning | VM_18 | Qualitative | Verify Approraite Staffing Levels for Wildfire Related Activities | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Staffing Level Verifed | Meeting Minutes
Vegetation Management and Inspection | AiDash | VM_19 | Qualitative | Verification of Plan Quality and accuracy | N/A | N/A | N/A | Program Validated | Program Validated | Program Validated | Program Validated | Program Validated | Program Validated | Review Meeting
Situational Awareness and Forecasting | Environmental monitoring systems | SAF_1 | Qualitative | Ongoing Monitoring and Maintenance | 50% | 75% | 100% | 50% | 75% | 100% | 50% | 75% | 100% | Budget Review
Situational Awareness and Forecasting | Grid monitoring systems | SAF_2 | Quantitative | Number of FIS installed. | 10 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | Quantitative
Situational Awareness and Forecasting | Grid monitoring systems | SAF_3 | Quantitative | Number of circuits installed on per year. | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | Quantitative
Situational Awareness and Forecasting | Ignition detection systems | SAF_4 |  | N/A | [10 empty] | All 15 HD ALERTWildfire cameras were installed. Project is full operational.
Situational Awareness and Forecasting | Weather forecasting | SAF_5 | Qualitative | Ongoing Monitoring and Maintenance | 50% | 75% | 100% | 50% | 75% | 100% | 50% | 75% | 100% | Budget Review
Situational Awareness and Forecasting | Fire potential index | SAF_6 | Qualitative | Ongoing Monitoring and Maintenance | 50% | 75% | 100% | 50% | 75% | 100% | 50% | 75% | 100% | Budget Review
Situational Awareness and Forecasting | GreenGrid iSIU | SAF_7 | Qualitative | Ongoing Monitoring and Maintenance | N/A | N/A | N/A | System Review and Additional Node Discussion | System Review and Additional Node Discussion | System Review and Additional Node Discussion | System Review and Additional Node Discussion | System Review and Additional Node Discussion | System Review and Additional Node Discussion | Meeting minutes
Emergency Preparedness | Emergency preparedness plan | EP_1 | Qualitative | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Review and Evaluate Emergency Plan | Annual Review Meeting
Emergency Preparedness | External collaboration and coordination | EP_2 | Qualitative | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Meetings with Community Partners and Mutual Aid Groups | Records of Meetings with Community Parterns and Mutual Aid Groups
Emergency Preparedness | Public emergency communication strategy | EP_3 | Qualitative | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review and Evaluate Emergency Program // Review and Evaluate Communcations Strategy | Review Meetings
Emergency Preparedness | Preparedness and planning for service restoration | EP_4 | Qualitative | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Review and Evaluare Emergency Plan // Update Service Restoration Plan with Operations Group | Annual Revise Service Restoration Plan
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | EP_5 | Qualitative | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Review and Evaluare PSPS Program // Yearly Review and Evaluate PSPS Program | Annual Review Meeting
Community Outreach and Engagement | Public outreach and education awareness program | COE_1 | Quantitative | Number of Public Outreach and Education Events | 180 | 270 | 360 | 180 | 270 | 360 | 180 | 270 | 360 | Quantitative
Community Outreach and Engagement | Engagement with access and functional needs populations | COE_2 | Qualitative | AFN customer needs verifications | 6 | 9 | 12 | 6 | 9 | 12 | 6 | 9 | 12 | Quantitative
Community Outreach and Engagement | Collaboration on local wildfire mitigation planning | COE_3 | Qualitative | Develop Program | 50% | 75% | 100% | Review and Maintain Program | Review and Maintain Program | Review and Maintain Program | Review and Maintain Program | Review and Maintain Program | Review and Maintain Program | Version History
Community Outreach and Engagement | Best practice sharing with other utilities | COE_4 | Quantitative | Work Groups, Conferences | 8 | 12 | 15 | 8 | 12 | 15 | 8 | 12 | 15 | Quantitative

## Table 13
Utility | BVES |  | Note: Provide a listing (as rows) of all work orders / notifications for corrective work on electric circuits that were open as of the end of the quarter.
Table No. | 13
Date Modified | 2024-08-01
Table 13: Open work orders / notifications
a. Work order number | b. Equipment Type | c. HFTD Tier | d. Line type | e. Date the work order was originally opened | f. Due date of the original work order | g. GO 95 rule 18 priority level of the original work order | h. Optional utility-specific repair priority | i. Date(s) the work order was reinspected or modified (if applicable) | j. Due date of the work order after it was reinspected or modified (if applicable) | k. Priority of the work order after it was reinspected or modified (if applicable) | l. Reason for reinspection (if applicable)
T4835BV_20240614091250 | crossarm | HFTD Tier 2 | Distribution | 2024-06-14 | 2029-06-14 | 3

## Table 14
Utility | BVES
Table No. | 14
Date Modified | 2024-08-01
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Non-HFTD Distribution | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HFTD 2 Distribution | 48359.2667 | 30 | 33.5294 | 30 | 30 | 30 | 30 | 38.8235 | 33.5294 | 65.2941 | 49.4118 | 49.4118 | 49.4118 | 45.8824 | 45.8824 | 45.8824
HFTD 3 Distribution | 31214.88 | 60 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 90 | 90 | 90 | 30 | 90 | 30
Non-HFTD Transmission | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HFTD 2 Transmission | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HFTD 3 Transmission | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Table 15
Utility | BVES
Table No. | 15
Date Modified | 2024-08-01
Table 15: Top Risk Circuit Scores
*EC to add all other risk categories to right of last required category.
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Radford | Circuit | Ditribution | 2.84 | Both >1% and Top 5% | 3 | 31214.88 | 60 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 90 | 90 | 90 | 30 | 90 | 30
Shay | Circuit | Ditribution | 17.56 | <1% contribution | 2 | 190.38 | 30 | 60 | 30 | 30 | 30 | 30 | 30 | 60 | 90 | 90 | 90 | 90 | 90 | 90 | 90
Baldwin | Circuit | Ditribution | 9.44 | Both >1% and Top 5% | 2 | 6321.91 | 30 | 60 | 30 | 30 | 30 | 30 | 90 | 60 | 90 | 90 | 90 | 90 | 90 | 90 | 90
Boulder | Circuit | Ditribution | 19.48 | <1% contribution | 2 | 700.22 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 30 | 60 | 30
North Shore (Fawnskin) | Circuit | Ditribution | 23.92 | Both >1% and Top 5% | 2 | 6603.54 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 90 | 90 | 90 | 30 | 60 | 30
Pioneer (Palomino) | Circuit | Ditribution | 19.34 | >1% contribution | 2 | 2447.08 | 30 | 30 | 30 | 30 | 30 | 30 | 90 | 30 | 90 | 30 | 30 | 30 | 30 | 30 | 30
Clubview | Circuit | Ditribution | 10.45 | >1% contribution | 2 | 2642.98 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 90 | 90 | 90 | 30 | 60 | 30
Goldmine | Circuit | Ditribution | 18.46 | Both >1% and Top 5% | 2 | 4534.8 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 30 | 60 | 30
Paradise | Circuit | Ditribution | 11.85 | >1% contribution | 2 | 1139.63 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 30 | 30 | 30
Sunset | Circuit | Ditribution | 11.17 | >1% contribution | 2 | 2001.92 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 30 | 30 | 30
Sunrise (Maple) | Circuit | Ditribution | 11.65 | >1% contribution | 2 | 1538.99 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 60 | 60 | 60 | 30 | 30 | 30
Holcomb (Bear City) | Circuit | Ditribution | 14.1 | Both >1% and Top 5% | 2 | 4717.87 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 90 | 90 | 90 | 90 | 30 | 30 | 30
Georgia | Circuit | Ditribution | 9.86 | >1% contribution | 2 | 1380.19 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 30 | 30 | 30
Eagle | Circuit | Ditribution | 8.91 | >1% contribution | 2 | 1510.19 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 60 | 30 | 60
Garstin | Circuit | Ditribution | 8.91 | >1% contribution | 2 | 1166.4 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 90 | 30 | 90
Lagonita | Circuit | Ditribution | 8.89 | >1% contribution | 2 | 1531.14 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 30 | 60 | 30
Interlaken | Circuit | Ditribution | 10 | >1% contribution | 2 | 1128.55 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 60 | 30 | 60
Castle Glen (Division) | Circuit | Ditribution | 10.61 | >1% contribution | 2 | 1481.82 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 60
Harnish (Village) | Circuit | Ditribution | 2.55 | >1% contribution | 2 | 794.06 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 30 | 30 | 30
Country Club | Circuit | Ditribution | 4.12 | <1% contribution | 2 | 639.54 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 30 | 30 | 30 | 30 | 30 | 30