## Cover Sheet Tables 1-15
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines, Appendix D
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | PacifiCorp
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2024
Reporting Period quarter |  | Q3 |  | Q1 | 2023
Date Modified |  | 2024-11-01 |  | Q2 | 2024
|  |  |  | Q3 | 2025
Q4

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitiativeObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
PacifiCorp | 2024-11-01 | Program |  |  | Transmission Patrol inspections | Transmission Patrol Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Transmission Patrol inspections |  | 8.1.3.1 | AI-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Patrol inspections_AI-01_2024 | 165 | TBD | Yes | Inspection Count | 12034 | 613 | 5329 | 9735 | 12263 | 475 | 11377 | 11377 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Brian Pagel
PacifiCorp | 2024-11-01 | Program |  |  | Distribution Patrol Inspections | Distribution Patrol Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Distribution Patrol Inspections |  | 8.1.3.1 | AI-02 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Patrol Inspections_AI-02_2024 | 165 | TBD | Yes | Inspection Count | 46276 | 2421 | 12260 | 33957 | 48423 | 9330 | 32687 | 45556 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Brian Pagel
PacifiCorp | 2024-11-01 | Program |  |  | Transmission Detail Inspections | Transmission Detail Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Transmission Detail Inspections |  | 8.1.3.2 | AI-03 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Detail Inspections_AI-03_2024 | 166 | TBD | Yes | Inspection Count | 1631 | 49 | 272 | 1087 | 1631 | 0 | 0 | 167 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Brian Pagel
PacifiCorp | 2024-11-01 | Program |  |  | Distribution Detail Inspections | Distribution Detail Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Distribution Detail Inspections |  | 8.1.3.2 | AI-04 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Detail Inspections_AI-04_2024 | 166 | TBD | Yes | Inspection Count | 8672 | 2170 | 3258 | 5427 | 8680 | 2986 | 5964 | 7959 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Brian Pagel
PacifiCorp | 2024-11-01 | Program |  |  | Transmission Intrusive Pole Inspections | Transmission Intrusive Pole Inspections - Transmission and Distribution Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Transmission Intrusive Pole Inspections |  | 8.1.3.3 | AI-05 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Intrusive Pole Inspections_AI-05_2024 | 168 | TBD | Yes | Inspection Count | 783 | 0 | 0 | 470 | 783 | 247 | 780 | 780 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Brian Pagel
PacifiCorp | 2024-11-01 | Program |  |  | Distribution Intrusive Pole Inspections | Distribution Intrusive Pole Inspections - Transmission and Distribution Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Distribution Intrusive Pole Inspections |  | 8.1.3.3 | AI-06 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Intrusive Pole Inspections_AI-06_2024 | 168 | TBD | Yes | Inspection Count | 2523 | 0 | 0 | 1516 | 2527 | 324 | 1746 | 2251 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Brian Pagel
PacifiCorp | 2024-11-01 | Program |  |  | Enhanced (Infrared) Inspections in Transmission Lines | Enhanced (Infrared) Inspections in Transmission Lines. Tracking of line miles. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Enhanced (Infrared) Inspections in Transmission Lines |  | 8.1.3.6 | AI-07 | PacifiCorp_Grid Design, Operations, and Maintenance_Enhanced (Infrared) Inspections in Transmission Lines_AI-07_2024 | 172 | TBD | Yes | Line miles | 700 | 100 | 100 | 700 | 700 | 100 | 560 | 700 |  | N/A | N/A | N/A | N/A | N/A | Completed | [5 empty] | Michael Thames
PacifiCorp | 2024-11-01 | Pilot |  |  | Enhanced (Infrared) Inspections in Distribution Lines | Enhanced (Infrared) Inspections in Distribution Lines. Tracking of line miles. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Enhanced (Infrared) Inspections in Distribution Lines |  | 8.1.3.5 | AI-08 | PacifiCorp_Grid Design, Operations, and Maintenance_Enhanced (Infrared) Inspections in Distribution Lines_AI-08_2024 | 171 | TBD | Yes | Line miles | 810 | 0 | 0 | 810 | 810 | 0 | 185 | 810 |  | N/A | N/A | N/A | N/A | N/A | Completed | [5 empty] | Michael Thames
PacifiCorp | 2024-11-01 | Program |  |  | Substation Inspections | Substation Inspections. Tracking of units. Cost tracked on Table 11. |  | Grid Design, Operations, and Maintenance | 8.1 | Substation Inspections |  | 8.1.3.4 | AI-11 | PacifiCorp_Grid Design, Operations, and Maintenance_Substation Inspections_AI-11_2024 | 169 | TBD | Yes | Inspection Count | 451 | 166 | 223 | 388 | 445 | 166 | 222 | 387 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Mindy Curnes
PacifiCorp | 2024-11-01 | Program |  |  | QA/QC of Asset Inspections | QA/QC of Asset Inspections |  | Grid Design, Operations, and Maintenance | 8.1 | Quality Assurance and Quality Control |  | 8.1.6 | AI-12 | PacifiCorp_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control_AI-12_2024 | 178 | TBD | Yes | Inspection Count | 0 | 68 | 272 | 476 | 681 | 115 | 528 | 720 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Brian Pagel
PacifiCorp | 2024-11-01 | Program |  |  | Partner with public safety partners in communities throughout California regarding wildfire safety and preparedness and PSPS. | Public Outreach and Education Awareness Program | Partner with public safety partners in communities throughout California regarding wildfire safety and preparedness and PSPS. | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | CO-01 | PacifiCorp_Community Outreach and Engagement_Public Outreach and Education Awareness Program_CO-01_2024 | 324 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | >55% of sample survey aware of wildfire safety communications | >55% of sample survey aware of wildfire safety communications | >55% of sample survey aware of wildfire safety communications | >55% of sample survey aware of wildfire safety communications |  | Completed | [5 empty] | Babak Asgharian
PacifiCorp | 2024-11-01 | Program |  |  | External collaboration and coordination | To enhance awareness of PSPS plan and understanding of roles and responsibilities. | To enhance awareness of PSPS plan and understanding of roles and responsibilities. | Emergency Preparedness | 8.4 | External Collaboration and Coordination |  | 8.4.2.3 | EP-02 | PacifiCorp_Emergency Preparedness_External Collaboration and Coordination_EP-02_2024 | 285 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Conduct 1: Functional exercise, tabletop exercise, workshop, and preparedness fair/ CRC demo. | N/A | Preparedness fair conducted May 1, 2024.Tabletop exercise, workshop, and community resource center demonstration completed May 22, 2024. Functional exercise completed June 25, 2024. | N/A | N/A | Completed | [5 empty] | Nora Yotsov/Traci Schultz
PacifiCorp | 2024-11-01 | Project |  | 2023-12-31 | Public Safety Partner Portal | Develop a web-based portal for Public Safety Partners with critical facility/ infrastructure data for use during PSPS events | Develop a web-based application that hosts key information from PacifiCorp's IT systems about customers identified as critical facilities or infrastructure for use by public safety partners during PSPS events. | Emergency Preparedness | 8.4 | Messaging |  | 8.4.4.2 | EP-03 | PacifiCorp_Emergency Preparedness_Messaging_EP-03_2024 | 307 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | [5 empty] | Amanda
PacifiCorp | 2024-11-01 | Program |  |  | Line Rebuild | Line Rebuild program - Covered Conductor installation. Includes undergrounding. Tracking of line miles. Cost tracked on Table 11. | Address the potential that incidental object contact will result in a fault event | Grid Design, Operations, and Maintenance | 8.1 | Line Rebuild - Covered conductor installation |  | 8.1.2.1 | GH-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Line Rebuild - Covered conductor installation_GH-01_2024 | 156 | TBD | Yes | Line miles | 80 | 17.6 | 45 | 65 | 80 | 17.6 | 48 | 67 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Kevin Schiedler/Hillary
PacifiCorp | 2024-11-01 | Program |  |  | Targeted Pole Replacement | Distribution Pole Replacement. Tracking of units. Cost tracked on Table 11 under Line Rebuild program | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | Grid Design, Operations, and Maintenance | 8.1 | Distribution Pole Replacement |  | 8.1.2.3 | GH-02 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Pole Replacement_GH-02_2024 | 159 | TBD | Yes | Poles | 1600 | 396 | 800 | 1200 | 1600 | 430 | 683 | 799 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Kevin Schiedler/Hillary
PacifiCorp | 2024-11-01 | Program |  |  | Transmission Pole Replacement | Transmission Pole Replacement Tracking of units. Cost tracked on Table 11 under Line Rebuild program | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | Grid Design, Operations, and Maintenance | 8.1 | Transmission Pole Replacement |  | 8.1.2.4 | GH-03 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Pole Replacement_GH-03_2024 | 159 | TBD | Yes | Poles | 160 | 34 | 80 | 120 | 160 | 0 | 13 | 97 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Kevin Schiedler/Hillary
PacifiCorp | 2024-11-01 | Program |  |  | Relay/Recloser/CB Replacements / Upgrade | Relay/Recloser/CB Replacements / Upgrade. Tracking of units. Cost tracked on Table 11. | Enhances fault detection capabilities, reduce fault isolation time, improve fault location and record availability, and speed up restoration efforts | Grid Design, Operations, and Maintenance | 8.1 | Installation of system automation equipment |  | 8.1.2.8 | GH-04 | PacifiCorp_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GH-04_2024 | 160 | TBD | Yes | Devices | 20 | 2 | 10 | 18 | 20 | 2 | 2 | 6 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Kevin Schiedler/Hillary
PacifiCorp | 2024-11-01 | Project |  | 2024-12-31 | Expulsion fuse replacement | Tracking of units. Cost tracked on Table 11. | Install new and CAL FIRE-approved non expulsion fuses including power fuses and current limiting fuses to replace existing expulsion fuse equipment | Grid Design, Operations, and Maintenance | 8.1 | Expulsion fuse replacement |  | 8.1.2.12 | GH-05 | PacifiCorp_Grid Design, Operations, and Maintenance_Expulsion fuse replacement_GH-05_2024 | 161 | TBD | Yes | Fuse locations | 500 | 364 | 700 | 1000 | 1000 | 364 | 811 | 2270 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Kevin Schiedler/Hillary
PacifiCorp | 2024-11-01 | Program |  |  | Weather Station Maintenance | Annual maintenance and calibration of weather station fleet | Ensure each weather station is operational and reporting correct and accurate data. | Grid Design, Operations, and Maintenance | 8.1 | Equipment Maintenance and Repair |  | 8.1.4 | MA-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Equipment Maintenance and Repair_SA-01_2024 | 174 | N/A | Yes | Unit | 0 | 0 | 50 | 108 | 108 | 0 | 107 | 108 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Michael Thames
PacifiCorp | 2024-11-01 | Program |  |  | Risk modeling using FireSight (WRRM) | Risk and Risk Components Calculation. Cost tracked on Table 11. | Identify the specific assets associated with the risk, the areas of risk, and the consequence of an ignition or wildfire in that area | Risk Methodology and Assessment | 6 | Risk and Risk Components Calculation | Annual FireSight (WRRM) Planning Model Updates | 6.2.2 | RA-01 | PacifiCorp_Risk Methodology and Assessment_Risk and Risk Components Calculation_RA-01_2024 | 86 | TBD | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Updated wildfire risk at circuit level | Ignition (Wildfire) risk now calculated at the circuit level. | N/A | N/A | N/A | Completed | [5 empty] | Kevin Benson
PacifiCorp | 2024-11-01 | Program |  |  | Public Safety Power Shutoff (PSPS) Risk Assessment Solution | Public Safety Power Shutoff (PSPS) Risk Assessment Solution | Implement capability to calculate PSPS risks and risk components | Risk Methodology and Assessment | 6 | Risk and Risk Components Calculation |  | 6.1.1 | RA-01 | PacifiCorp_Risk Methodology and Assessment_Risk and Risk Components Calculation_RA-01_2024 | 66 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Updated PSPS risk at circuit level | Model development progressing and anticipate updated PSPS risk in 2024. | N/A | Continued development of internal PSPS probability and consequence. |  | In Progress | [5 empty] | Kevin Benson
PacifiCorp | 2024-11-01 | Program |  |  | Risk map refresh | Proposed Updates to the HFTD. Cost tracked on Table 11. | Continue evaluating the HFRA and update its boundaries on a regular cycle | Risk Methodology and Assessment | 6 | Top Risk Areas within the HFRA | FHCA Refresh | 6.4.1 | RA-02 | PacifiCorp_Risk Methodology and Assessment_Top Risk Areas within the HFRA_RA-02_2024 | 100 | TBD | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Updated approved FHCA | FHCA approved and updated. | N/A | N/A | N/A | Completed | [5 empty] | Kevin Benson
PacifiCorp | 2024-11-01 | Program |  |  | Risk Spend Efficiency (RSE) Modeling Implementation | Risk Spend Efficiency (RSE) Modeling Implementation | Provide risk spend efficiency calculations for proposed mitigations | Risk Methodology and Assessment | 6 | Other Key Metrics | Risk Spend Efficiency (RSE) Model Refresh | 6.4.3 | RA-03 | PacifiCorp_Risk Evaluation_Mitigation Selection Process_RA-01_2024 | 104 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Effectiveness measures for select mitigations. | Work shifted to Q2 2024 to prioritize wildfire risk and PSPS risk modeling efforts. | Initiated discovery and benchmarking for effectiveness of undergrounding and convered conductor. | Began development of internal effectiveness modeling for undergrounding. |  | In Progress | [5 empty] | Kevin Benson
PacifiCorp | 2024-11-01 | Program |  |  | Installation of weather stations | Tracking of units. Cost tracked on Table 11. |  | Situational Awareness and Forecasting | 8.3 | Environmental monitoring systems |  | 8.3.2 | SA-01 | PacifiCorp_Situational Awareness and Forecasting_Environmental monitoring systems_SA-01_2024 | 236 | TBD | Yes | Unit | 8 | 0 | 2 | 8 | 8 | 0 | 5 | 10 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Kevin Schiedler/Hillary
PacifiCorp | 2024-11-01 | Project | 2023-01-01 | 2024-12-31 | Wildfire Detection Network | Install up to 8 advanced wildfire detection cameras | Install 8 high-definition, pan/ tilt/ zoom wildfire detection cameras to fill in the "gaps" in the existing camera network within Pacific Power's California service territory | Situational Awareness and Forecasting | 8.3 | Ignition Detection Systems |  | 8.3.4.1 | SA-04 | PacifiCorp_Situational Awareness and Forecasting_Ignition Detection Systems_SA-04_2024 | 242 | N/A | No | Unit | 6 | 0 | 0 | 0 | 6 | 0 | 2 | 5 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Babak Asgharian
PacifiCorp | 2024-11-01 | Project |  | 2026-12-31 | Advanced Forecasting and Situational Awareness | Implement improvements to weather forecasting systems | * Improve integration of weather data into PacifiCorp's systems * Full integration of 30-year historic weather data analysis into operational and planning processes * Develop detailed technical requirements for multi-member WRF ensemble implementation. * Continue optimization and improvement of machine learning (ML) models' access to 30-year historic weather data analysis. | Situational Awareness and Forecasting | 8.3 | Weather Forecasting |  | 8.3.5.3 | SA-05 | PacifiCorp_Situational Awareness and Forecasting_Weather Forecasting_N/A_2024 | 262 | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | * Extend historic 30-year weather data reanalysis through 2023. * Build Machine Learning (ML) gridded grassland NDVI product. * Develop detailed technical requirements for multi-member WRF ensemble implementation. | N/A | * Extend historic 30-year weather data reanalysis through 2023. | N/A |  | In Progress | [5 empty] | Stephanie Beall
PacifiCorp | 2024-11-01 | Program |  |  | Detailed Inspection – Distribution | Detailed inspections for vegetation clearances around distribution electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks. | Vegetation Management | 8.2 | Detailed Inspection – Distribution |  | 8.2.2.1 | VM-01 | PacifiCorp_Vegetation Management_Detailed Inspection – Distribution_VM-01_2024 | 210 | N/A | Yes | Line miles | 874 | 275 | 484 | 750 | 875 | 453.25 | 507 | 669 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Josh Hooley
PacifiCorp | 2024-11-01 | Program |  |  | Detailed Inspection - Transmission | Detailed inspections for vegetation clearances around transmission electric lines. | To eliminate vegetation-related reliability (cascading outages), safety, and wildfire ignition risks. | Vegetation Management | 8.2 | Detailed Inspection - Transmission |  | 8.2.2.2 | VM-02 | PacifiCorp_Vegetation Management_Detailed Inspection - Transmission_VM-02_2024 | 213 | N/A | Yes | Line miles | 602 | 172 | 498 | 599 | 599 | 238.34 | 287 | 563 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Josh Hooley
PacifiCorp | 2024-11-01 | Program |  |  | Patrol Inspection - Distribution | Patrol (ground) inspections for vegetation clearances around distribution electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks by addressing vegetation conditions that require corrective action prior to the next scheduled work. | Vegetation Management | 8.2 | Patrol Inspection - Distribution |  | 8.2.3.3 | VM-03 | PacifiCorp_Vegetation Management_Patrol Inspection - Distribution_VM-03_2024 | 222 | N/A | Yes | Line miles | 865 | 462 | 877 | 1037 | 1037 | 1173 | 973 | 1037 |  | N/A | N/A | N/A | N/A | N/A | Completed | [5 empty] | Josh Hooley
PacifiCorp | 2024-11-01 | Program |  |  | Patrol Inspection - Transmission | Patrol (ground) inspections for vegetation clearances around transmission electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks by addressing vegetation conditions that require corrective action while maintaining compliance with applicable Public Resource Codes, NERC requirements, and as described in the Vegetation SOP | Vegetation Management | 8.2 | Patrol Inspection - Transmission |  | 8.2.2.4 | VM-04 | PacifiCorp_Vegetation Management_Patrol Inspection - Transmission_VM-04_2024 | 217 | N/A | Yes | Line miles | 99 | 32.83 | 119 | 119 | 119 | 32.83 | 99 | 119 |  | N/A | N/A | N/A | N/A | N/A | Completed | [5 empty] | Josh Hooley
PacifiCorp | 2024-11-01 | Program |  |  | Pole Clearing | Pole clearing beyond PRC 4292 | Pole clearing is designed to reduce the risk of fire ignition if sparks are emitted from electrical equipment. | Vegetation Management | 8.2 | Fuels management – Pole clearing beyond PRC 4292 |  | 8.2.3.1.2 | VM-05 | PacifiCorp_Vegetation Management_Fuels management – Pole clearing beyond PRC 4292_VM-05_2024 | 221 | N/A | No | Poles | 3126 | 1412 | 2200 | 2900 | 3192 | 1412 | 2425 | 2922 |  | N/A | N/A | N/A | N/A | N/A | In Progress | [5 empty] | Josh Hooley
PacifiCorp | 2024-11-01 | Program |  |  | Quality Assurance and Quality Control | Patrol post-audits on distribution electric lines | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications. | Vegetation Management | 8.2 | QA/QC - Post-Audits Distribution (Patrol) |  | 8.2.5 | VM-11 | PacifiCorp_Vegetation Management_QAQC - Post-Audits Distribution (Patrol)_VM-11_2024 | 227 | N/A | Yes | Line miles | 865 | 188.6 | 550 | 850 | 1037 | 188.6 | 317 | 1037 |  | N/A | N/A | N/A | N/A | N/A | Completed | [5 empty] | Josh Hooley
PacifiCorp | 2024-11-01 | Program |  |  | Quality Assurance and Quality Control | Patrol post-audits on transmission electric lines | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications. | Vegetation Management | 8.2 | QA/QC - Post-Audits Transmission (Patrol) |  | 8.2.5 | VM-11 | PacifiCorp_Vegetation Management_QAQC - Post-Audits Transmission (Patrol)_VM-11_2024 | 227 | N/A | Yes | Line miles | 99 | 24 | 50 | 119 | 119 | 24 | 100 | 119 |  | N/A | N/A | N/A | N/A | N/A | Completed | [5 empty] | Josh Hooley
Note on C2: Author: Select cells for dropdown list.

## Table 2
| Utility | PacifiCorp | Notes:
| Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-11-01 | HWW = High wind warning
RFW = Red flag warning
[10 empty] | Actuals | Projected
| Table 2: Performance Metrics | [8 empty] | Q3
| Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | 1 |  |  |  | Number of events
| 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1 |  |  |  | Number of events
|  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | 4 |  |  |  | Number of events
| 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 238 |  |  |  | Number of events
| 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 9 |  |  |  | Number of events
| 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 2 | 2 | 2 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 2 | 2 | 2 | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of events
|  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 13 | 13 | 13 | Number of events
| 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
|  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A |  |  |  |  | hours |  | Not able to provide at this time. PacifiCorp does not currently have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data. PacifiCorp will further review its data and coordinate as needed with its software vendor to identify a reasonable approach for conducting this analysis.
| 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 384 |  |  |  | hours
|  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 782.4 |  |  |  | hours
|  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 216 |  |  |  | hours
|  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 336 |  |  |  | hours
|  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 168 |  |  |  | hours
|  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 816 |  |  |  | hours
|  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | NA |  |  |  | hours
|  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | NA |  |  |  | hours
|  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 0 |  |  |  | hours
|  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 477.6 |  |  |  | hours
| 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 17424 |  |  |  | hours
|  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 22204.8 |  |  |  | hours
|  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 17736 |  |  |  | hours
|  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 21312 |  |  |  | hours
|  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 19152 |  |  |  | hours
|  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 21384 |  |  |  | hours
|  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 7752 |  |  |  | hours
|  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 53016 |  |  |  | hours
|  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 6912 |  |  |  | hours
|  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 48124.8 |  |  |  | hours
|  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 28344 |  |  |  | hours
|  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 58272 |  |  |  | hours
| 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 61812 |  |  |  | hours
|  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 146670 |  |  |  | hours
|  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 65064 |  |  |  | hours
|  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 153354 |  |  |  | hours
|  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 21192 |  |  |  | hours
|  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 108720 |  |  |  | hours
|  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 35088 |  |  |  | hours
|  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 156912 |  |  |  | hours
|  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 55020 |  |  |  | hours
|  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 94105.2 |  |  |  | hours
|  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 102888 |  |  |  | hours
|  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 112368 |  |  |  | hours
| 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Number of orders |  | Not able to provide at this time. PacifiCorp does not currently issue vegetation management work at the task by task level with specific "work orders", but rather at the circuit level. That being said, PacifiCorp does identify vegetation management activities at the work location level within its mobile data management software. PacifiCorp is currently reviewing its data to identify a process to more accurately identify work locations that may be "open"/unresolved considering limitations and other variables within its mobile data management software. PacifiCorp does not assign completion date requirements at the work location level.
|  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Number of orders |  | Not able to provide at this time. PacifiCorp does not currently issue vegetation management work at the task by task level with specific "work orders", but rather at the circuit level. That being said, PacifiCorp does identify vegetation management activities at the work location level within its mobile data management software. PacifiCorp is currently reviewing its data to identify a process to more accurately identify work locations that may be "open"/unresolved considering limitations and other variables within its mobile data management software. PacifiCorp does not assign completion date requirements at the work location level.
| 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 11856 |  |  |  | Number of orders
|  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 212 |  |  |  | Number of orders
| 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A | 1.14 |  |  |  | Hours
| 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of fatalities
|  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of injuries
| 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | 1000
| 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of structures
|  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 |  |  |  | Number of structures
| 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | 0.25 |  |  |  | Acres
| 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 |  |  |  | Number of ignitions
|  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | 2 |  |  |  | Number of ignitions
x | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 6257 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 650 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 6621 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 45 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 290.0182 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 31.1065 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 279.4828 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 1.8392 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 3 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 4 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 151 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 19 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 147 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 3 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 1903 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 1531 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 430 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 88 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 38.6953 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 11 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 221 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 255 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 3 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 4709 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 319 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 5 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 58 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 203.6424 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 14.953 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 6.1881 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 2.7066 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 4 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 58 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 8 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 66 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 2 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 34 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 1 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 1.902 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0.063078 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 10 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 1 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0.2221 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0.12687 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 1 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 123 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 25.1374 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of circuit miles inspected by the utility
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of findings from these asset inspections
| 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of findings from these asset inspections
x | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 13 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 475 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 7 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 422 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 4 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 23 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 302 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 6 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 405 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 25 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 2 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 512 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 9 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 399 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 4 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 1 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 25 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 26 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 3 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 5 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 7 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 56 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 39 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR | 0 |  |  |  | # of asset inspection findings which have been fixed
| 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 0 |  |  |  | # of asset inspection findings which have been fixed
x | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 1500 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 379 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 40 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 143 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | 1556 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 33 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other | 0 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other".
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program.
| 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | 41 |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2024.
x | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Percentage of customers notified of evacuation |  | PacifiCorp does not have authority to order evacuations. This is a local jurisdiction Incident Command authority. Local jurisdictions use their own alert and warning system to execute evacuation orders.

## Table 3
Utility | PacifiCorp
Table No. | 3
Date Modified | 2024-11-01
[5 empty] | Actual | Projected
Table 3: List and description of additional metrics |  |  |  |  | Q3
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
PC3a | Events Recorded with Fire Reference: Not Fire Season |  | Data source is outage reporting system in which outage makes reference to fire in comment or outage cause | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | 0 | 2 | 2 | 2
PC3b | Events Recorded with Fire Reference: Fire Season |  | Data source is outage reporting system in which outage makes reference to fire in comment or outage cause | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | 1 | 0 | 0 | 0
PC4a | Events Recorded with Fire Reference: damage fire, equipment fire, pole fire: Not Fire Season |  | Subset of PC3 where record makes reference to utility equipment or key components | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | 0 | 1 | 1 | 1
PC4b | Events Recorded with Fire Reference: damage fire, equipment fire, pole fire: Fire Season |  | Subset of PC3 where record makes reference to utility equipment or key components | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | 1 | 0 | 0 | 0
PC5 | Wire down risks |  | Data source is outage reporting system in which cause code or comments would result in downed conductor during fire season | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | 5 | 6 | 6 | 6
PC6 | Wire down trend |  | Reduction in quantity of wire down events, year over year, during the designated fire season period | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | 1 | 4 | 4 | 4

## Table 4
Utility | PacifiCorp
Table No. | 4
Date Modified | 2024-11-01
Table 4: Weather patterns |  |  | Q3
Metric type | # | Metric name | 2024 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 824 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 54 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 1385 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 0 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 0 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 0 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 824 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 54 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 1385 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 59575.55 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 3191.56 | Fire potential index overhead circuit mile days, see above for definition
| 4.c. | Fire potential index circuit mile days - non-HFTD | 118105.66 | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed) |  |  |  | Not applicable

## Table 5
| Utility | PacifiCorp | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-11-01
[8 empty] | Actual number of risk events | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q3
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | 2 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.0 | 3rd party contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.0 | Other contact from object | Distribution | Non-HFTD | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.2 | Other contact from object | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.0 | Other contact from object | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.2 | Other contact from object | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 1 | 29 | 29 | 29 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD | Yes | 0 | 10 | 10 | 10 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 33 | 43 | 43 | 43 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 2 | 12 | 12 | 12 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | 4 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 12 | 12 | 12 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 8 | 134 | 134 | 134 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 6 | 52 | 52 | 52 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 8 | 73 | 73 | 73 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 0 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 17 | 136 | 136 | 136 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 2 | 7 | 7 | 7 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 2 | 13 | 13 | 13 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 1 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 9 | 39 | 39 | 39 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD | Yes | 6 | 24 | 24 | 24 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 5 | 5 | 5 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 1 | 2 | 2 | 2 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 17 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 2 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 69 | 116 | 116 | 116 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 16 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 4 | 4 | 4 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD | Yes | 32 | 136 | 136 | 136 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | 8 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions)

## Table 6
| Utility | PacifiCorp | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2024-11-01
[7 empty] | Actual number of ignitions | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q3
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 0 | 2 | 2 | 2 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # ignitions
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions

## Table 7
| Utility | PacifiCorp
| Table No. | 7
| Date Modified | 2024-11-01
[7 empty] | Actual | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q3
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 23.42 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 23.37 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 389.94 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 319.66 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 165.64 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 778.74 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 4.59 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0.03 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 323.37 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 91.36 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 206.85 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 145.19 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 34.67 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 5.54 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 1.11 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 1.75 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 66.67 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 97.43 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 23.01 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 196.09 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0.7 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 81.3 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 67.93 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 57.64 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 111.82 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 15.42 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 7.84 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 17.92 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 11.58 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 79.49 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 46.24 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 23.6 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 56.81 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 1.45 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0.01 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 223.97 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 28.33 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 63.74 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 30.42 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 51.07 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 3.47 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 127 |  |  |  | Number of critical facilities
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 82 |  |  |  | Number of critical facilities
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 210 |  |  |  | Number of critical facilities
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 159 |  |  |  | Number of critical facilities
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 157 |  |  |  | Number of critical facilities
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 171 |  |  |  | Number of critical facilities
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 5 |  |  |  | Number of critical facilities
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of critical facilities
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 294 |  |  |  | Number of critical facilities
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 59 |  |  |  | Number of critical facilities
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 105 |  |  |  | Number of critical facilities
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 48 |  |  |  | Number of critical facilities
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of critical facilities
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of critical facilities
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 37 |  |  |  | Number of critical facilities
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 9 |  |  |  | Number of critical facilities
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of critical facilities
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of critical facilities
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 2979 |  |  |  | Number of residential customers
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 2537 |  |  |  | Number of residential customers
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 7769 |  |  |  | Number of residential customers
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 2632 |  |  |  | Number of residential customers
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 2427 |  |  |  | Number of residential customers
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 2416 |  |  |  | Number of residential customers
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 138 |  |  |  | Number of residential customers
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of residential customers
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 10703 |  |  |  | Number of residential customers
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 554 |  |  |  | Number of residential customers
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 3219 |  |  |  | Number of residential customers
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 598 |  |  |  | Number of residential customers
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of residential customers
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of residential customers
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 930 |  |  |  | Number of residential customers
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 68 |  |  |  | Number of residential customers
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of residential customers
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of residential customers
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | 357 |  |  |  | Number of commercial customers
|  | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 541 |  |  |  | Number of commercial customers
|  | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | 1343 |  |  |  | Number of commercial customers
|  | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 973 |  |  |  | Number of commercial customers
|  | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 563 |  |  |  | Number of commercial customers
|  | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 983 |  |  |  | Number of commercial customers
|  | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 30 |  |  |  | Number of commercial customers
|  | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 1 |  |  |  | Number of commercial customers
|  | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 1969 |  |  |  | Number of commercial customers
|  | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 316 |  |  |  | Number of commercial customers
|  | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 608 |  |  |  | Number of commercial customers
|  | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 240 |  |  |  | Number of commercial customers
|  | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of commercial customers
|  | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of commercial customers
|  | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 128 |  |  |  | Number of commercial customers
|  | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 61 |  |  |  | Number of commercial customers
|  | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of commercial customers
|  | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of commercial customers
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | 152 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 159 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | 394 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 100 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 83 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 109 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 5 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 415 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 17 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 145 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 15 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 13 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 1 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of customers belonging to access and functional needs populations
|  | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of customers belonging to access and functional needs populations
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  |  | Number of substations
|  | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Number of substations
|  | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | 5 |  |  |  | Number of substations
|  | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 1 |  |  |  | Number of substations
|  | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Number of substations
|  | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Number of substations
|  | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of substations
|  | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 1 |  |  |  | Number of substations
|  | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 5 |  |  |  | Number of substations
|  | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Number of substations
|  | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 1 |  |  |  | Number of substations
|  | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of substations
|  | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of substations
|  | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 1 |  |  |  | Number of substations
|  | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of substations
|  | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of substations
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | 9 |  |  |  | Number of weather stations
|  | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 10 |  |  |  | Number of weather stations
|  | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 4 |  |  |  | Number of weather stations
|  | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 18 |  |  |  | Number of weather stations
|  | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 17 |  |  |  | Number of weather stations
|  | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 8 |  |  |  | Number of weather stations
|  | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 14 |  |  |  | Number of weather stations
|  | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 22 |  |  |  | Number of weather stations
|  | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 3 |  |  |  | Number of weather stations
|  | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 3 |  |  |  | Number of weather stations
|  | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of weather stations
|  | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of weather stations

## Table 8
| Utility | PacifiCorp |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2024-11-01 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q3
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0.07 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 0.05 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | -0.09 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0.03 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0.09 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | -0.15 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 0.05 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | -0.06 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 0.05 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | -0.03 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | -0.01 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | -1.83 |  |  |  | Circuit miles
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0.08 |  |  |  | Circuit miles
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | -0.05 |  |  |  | Circuit miles
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | -0.14 |  |  |  | Circuit miles
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0.13 |  |  |  | Circuit miles
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0.17 |  |  |  | Circuit miles
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0.01 |  |  |  | Circuit miles
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0.01 |  |  |  | Circuit miles
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 0.9 |  |  |  | Circuit miles
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 0.25 |  |  |  | Circuit miles
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 0.02 |  |  |  | Circuit miles
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 0.01 |  |  |  | Circuit miles
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 0.1 |  |  |  | Circuit miles
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  |  | Number of substations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Number of substations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 |  |  |  | Number of substations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Number of substations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Number of substations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of substations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Number of substations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | -2 |  |  |  | Number of substations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Number of substations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of substations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of substations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Number of substations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of substations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of substations
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 |  |  |  | Number of weather stations
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Number of weather stations
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 1 |  |  |  | Number of weather stations
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 1 |  |  |  | Number of weather stations
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Number of weather stations
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 3 |  |  |  | Number of weather stations
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Number of weather stations
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of weather stations
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of weather stations

## Table 9
| Utility | PacifiCorp
| Table No. | 9
| Date Modified | 2024-11-01
[7 empty] | Actual | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q3
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 26.72 |  |  |  | Circuit miles
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 1.69 |  |  |  | Circuit miles
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 2.9 |  |  |  | Circuit miles
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 0.11 |  |  |  | Circuit miles
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 3.96 |  |  |  | Circuit miles
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 0.49 |  |  |  | Circuit miles
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 1 |  |  |  | Circuit miles
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Circuit miles
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Circuit miles
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  |  | Number of substations
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 1 |  |  |  | Number of substations
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | 4 |  |  |  | Number of substations
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 4 |  |  |  | Number of substations
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 8 |  |  |  | Number of substations
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Number of substations
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of substations
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Number of substations
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 1 |  |  |  | Number of substations
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 |  |  |  | Number of substations
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of substations
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of substations
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Number of substations
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Number of substations
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of substations
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of substations
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 |  |  |  | Number of weather stations
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 1 |  |  |  | Number of weather stations
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 |  |  |  | Number of weather stations
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 3 |  |  |  | Number of weather stations
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 1 |  |  |  | Number of weather stations
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 4 |  |  |  | Number of weather stations
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 |  |  |  | Number of weather stations
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 |  |  |  | Number of weather stations
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 |  |  |  | Number of weather stations
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 |  |  |  | Number of weather stations
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 |  |  |  | Number of weather stations

## Table 10
Utility | PacifiCorp |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2024-11-01 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q3
Metric type | # | Wind Warning Status | Metric name | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW only | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | HWW & RFW | Frequency of PSPS events (total) | 0 | 2 | 2 | 2 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
|  | All (regardless of RFW/HWW status) | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| 1.b. | RFW only | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW only | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | HWW & RFW | Scope of PSPS events (total) | 0 | 20 | 20 | 20 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
|  | All (regardless of RFW/HWW status) | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
| 1.c. | RFW only | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW only | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
|  | HWW & RFW | Duration of PSPS events (total) | 0 | 200 | 200 | 200 | Customer hours per year
|  | All (regardless of RFW/HWW status) | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year
| 1.d. | RFW only | Frequency of fast-trip events (total) | 33 | 15 | 15 | 15 | Number of events
|  | HWW only | Frequency of fast-trip events (total) | 0 | 2 | 2 | 2 | Number of events
|  | HWW & RFW | Frequency of fast-trip events (total) | 0 | 2 | 2 | 2 | Number of events
|  | None | Frequency of fast-trip events (total) | 223 | 70 | 70 | 70 | Number of events
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | 23941 | 44000 | 44000 | 44000 | Circuit mile days
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | 0 | 6200 | 6200 | 6200 | Circuit mile days
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | 0 | 6200 | 6200 | 6200 | Circuit mile days
|  | None | Circuit mile days with fast-trip settings enabled (total) | 203220 | 200000 | 200000 | 200000 | Circuit mile days
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | 0 | 52344.8753 | 52344.8753 | 52344.8753 | Total customer hours of planned outages per year
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | 0 | 99071.3833 | 99071.3833 | 99071.3833 | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | 0 | 0 | 0 | 0 | Total customer hours of outages due to fast-trip per year
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | 0 | 157.0899 | 157.0899 | 157.0899 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | 0 | 150.5899 | 150.5899 | 150.5899 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | 0 | 0.58237 | 0.58237 | 0.58237 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | 0 | 0.56987 | 0.56987 | 0.56987 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served)
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | 0 | 0 | 0 | 0 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | 0 | 0 | 0 | 0 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
4. Community outreach of PSPS metrics | 4.b. | N/A | # of medical baseline customers impacted by PSPS | 0 | 0 | 0 | 0 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer)
4. Community outreach of PSPS metrics | 4.c. | N/A | # of customers notified prior to initiation of PSPS event | 0 | 0 | 0 | 0 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | 0 | 0 | 0 | 0 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | 0 | 0 | 0 | 0 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | 0 | 0 | 0 | 0 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | 0 | 0 | 0 | 0 | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | 0 | 0 | 0 | 0 | Number of customers
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | 0 | 0 | 0 | 0 | =1.c. / RFW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | 0 | 0 | 0 | 0 | =1.c. / HWW OH circuit mile days in time period
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | 0 | 0 | 0 | 0 | =1.c. / FPI OH circuit mile days in time period
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | 0 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | 0 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | 0 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | 0 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | 0 | 0 | 0 | 0 | Number of risk events

## Table 11
Utility | PacifiCorp | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2024-11-01 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actuals |  |  |  | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2024 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Grid Design, Operations, and Maintenance | Transmission Patrol inspections | AI-01 | Equipment failure | N/A | 2019 |  | N/A | [10 empty] | 93 |  |  |  | 93 |  |  |  | 93 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Distribution Patrol Inspections | AI-02 | Equipment failure | N/A | 2019 |  | N/A | [10 empty] | 308 |  |  |  | 308 |  |  |  | 308 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Transmission Detail Inspections | AI-03 | Equipment failure | N/A | 2019 |  | N/A | [10 empty] | 137 |  |  |  | 137 |  |  |  | 137 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Distribution Detail Inspections | AI-04 | Equipment failure | N/A | 2019 |  | N/A | [10 empty] | 203 |  |  |  | 203 |  |  |  | 203 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Transmission Intrusive Pole Inspections | AI-05 | [15 empty] | 171 |  |  |  | 171 |  |  |  | 171 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Distribution Intrusive Pole Inspections | AI-06 | Equipment failure | N/A | 2019 |  | N/A | [10 empty] | 90 |  |  |  | 90 |  |  |  | 90 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Enhanced IR Inspections in transmission lines | AI-07 | Equipment failure | N/A | 2019 | 2023 GRC | N/A | [10 empty] | 90 |  |  |  | 90 |  |  |  | 90 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Enhanced IR Inspections in distribution lines | AI-08 | Equipment failure | N/A | 2022 |  | N/A | [10 empty] | 125 |  |  |  | 130 | [5 empty] | 2025 projected spend is to be determined depending on work done in 2024. Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Substation Inspections | AI-11 | Equipment failure | N/A | 2019 |  | N/A | [10 empty] | 179 |  |  |  | 179 |  |  |  | 179 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Quality assurance / quality control | AI-12 | Equipment failure | N/A | 2019 | 2023 GRC | N/A | [10 empty] | 36 |  |  |  | 36 |  |  |  | 36 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Community Outreach and Engagement | Public outreach and education awareness program | CO-01 | PSPS - for sectionalization, etc. |  | 2020 | 2023 GRC | NA | [10 empty] | 90 |  |  |  | 90 |  |  |  | 90 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Community Outreach and Engagement | Engagement with access and functional needs populations | CO-02 | [25 empty] | Spend for this initiative is included in CO-01
Community Outreach and Engagement | Collaboration on local wildfire mitigation planning | CO-03 | [25 empty] | Spend for this initiative is included in CO-01
Community Outreach and Engagement | Best practice sharing with other utilities | CO-04 | [25 empty] | Spend for this initiative is included in CO-01
Emergency Preparedness | Emergency preparedness plan | EP-01 | [15 empty] | 50 |  |  |  | 50 |  |  |  | 50 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Emergency Preparedness | External collaboration and coordination | EP-02 |  |  |  | NA | NA | [10 empty] | 30 |  |  |  | 30 |  |  |  | 30 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Emergency Preparedness | Public emergency communication strategy | EP-03 | PSPS - for sectionalization, etc. | N/A |  | N/A | N/A | [8 empty] | 106 |  | 4 | [9 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Emergency Preparedness | Customer support in wildfire and PSPS emergencies | EP-05 | N/A | N/A | 2021 | 2023 GRC | NA | [10 empty] | 150 | [9 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Line Rebuild - Covered conductor installation | GH-01 | Contact with vegetation | Wire-to-wire contact |  | 2023 GRC | NA | [8 empty] | 83000 | 83000 | 313 | 313 | 62000 | 62000 | 313 | 313 | 62000 | 62000 | 313 | 313
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements | GH-02 | Contact with vegetation |  | 2019 | 2023 GRC | NA | In Compliance | GO 95; GO 165 | [18 empty] | Spend for this initiative is included in GH-01
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements | GH-03 | [25 empty] | Spend for this initiative is included in GH-01
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GH-04 | Equipment failure | Wire-to-wire contact |  | 2023 GRC | NA | [8 empty] | 10000 |  |  |  | 5000 |  |  |  | 2500 |  |  |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Expulsion Fuse Replacement | GH-05 | Contact with vegetation |  |  | 2023 GRC | NA | [8 empty] | 10000 |  |  |  | 1000 | [7 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk (Grid Ops): EFR and Fault Indicators | GO-01 | Contact with vegetation | N/A | 2019 | 2023 GRC | N/A | [8 empty] | 150 |  | 50 | [9 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications (Grid Ops): Patrols | GO-02 | PSPS - for sectionalization, etc. | N/A |  | 2023 GRC | NA | [10 empty] | 600 |  |  |  | 600 |  |  |  | 600 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Situational Awareness and Forecasting | Maintenance: Weather Station | MA-01 | [15 empty] | 245 |  |  |  | 285 |  |  |  | 325 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
PSPS | Protocols on PSPS | PS-01 | PSPS - for sectionalization, etc. | N/A |  | 2023 GRC | NA | [10 empty] | 850 |  |  |  | 800 |  |  |  | 750
Risk Methodology and Assessment | Risk and Risk Component Calculation | RA-01 | [15 empty] | 130 |  |  |  | 130 |  |  |  | 130 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Risk Methodology and Assessment | Top Risk Areas within the HFRA | RA-02 | [15 empty] | 45 | [9 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Risk Methodology and Assessment | Other Key Metrics | RA-03 | [15 empty] | 50 |  |  |  | 40 |  |  |  | 40
Risk Methodology and Assessment | Enterprise System for Risk Assessment | RA-04 | Equipment failure | N/A | 2019 | 2023 GRC | N/A | [8 empty] | 99 |  | 5 |  | 149 |  | 8 |  | 104 |  | 8 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Situational Awareness and Forecasting | Environmental monitoring systems | SA-01 | Other contact with object | Equipment failure | 2019 | 2023 GRC | N/A | [8 empty] | 240 |  |  |  | 160 |  |  |  | 120 |  |  |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Situational Awareness and Forecasting | Grid monitoring systems | SA-02 | Other contact with object | Equipment failure | 2019 | 2023 GRC | N/A | [10 empty] | 39 |  |  |  | 39 | [5 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Situational Awareness and Forecasting | Smoke and Air Quality Sensors | SA-03 | [13 empty] | 64 |  | 6 |  | 13 |  | 2 | [5 empty] | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Situational Awareness and Forecasting | Wildfire Detection Cameras | SA-04 | [13 empty] | 320 |  |  |  | 985 |  | 80 |  |  |  | 80 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Situational Awareness and Forecasting | Weather Forecasting | SA-05 | [13 empty] | 26 |  | 94 |  | 12 |  | 103 |  | 12 |  | 103 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Situational Awareness and Forecasting | Fire potential index | SA-06 | Contact with vegetation | N/A |  | 2023 GRC | N/A | [8 empty] | 2 |  | 96 |  | 1 |  | 96 |  | 1 |  | 96 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Vegetation Management and Inspection | Vegetation Inspections: Detailed Inspection – Distribution | VM-01 | Contact with vegetation | N/A | 2019 | 2023 GRC | NA | [10 empty] | 280 |  |  |  | 294 |  |  |  | 278 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Vegetation Management and Inspection | Vegetation Inspections: Detailed Inspection - Transmission | VM-02 | Contact with vegetation |  | 2019 | 2023 GRC | NA | [10 empty] | 70 |  |  |  | 157 |  |  |  | 72 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Vegetation Management and Inspection | Vegetation Inspections: Patrol Inspection - Distribution | VM-03 | Contact with vegetation | N/A |  | 2023 GRC | NA | [10 empty] | 375 | 375 |  |  | 316 | 316 |  |  | 336 | 336 | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Vegetation Management and Inspection | Vegetation Inspections: Patrol Inspection - Transmission | VM-04 | Contact with vegetation | N/A |  | 2023 GRC | NA | [10 empty] | 120 | 120 |  |  | 20 | 20 |  |  | 120 | 120 | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Vegetation Management and Inspection | Pole clearing | VM-05 | [15 empty] | 374 |  |  |  | 374 |  |  |  | 374 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Vegetation Management and Inspection | Clearance - Distribution | VM-06 | Contact with vegetation | N/A | 2019 | 2023 GRC | NA | [10 empty] | 15915 |  |  |  | 15087 |  |  |  | 15241 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Vegetation Management and Inspection | Clearance - Transmission | VM-07 | Contact with vegetation | N/A | 2019 | 2023 GRC | NA | [10 empty] | 1405 |  |  |  | 1904 |  |  |  | 1416 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Vegetation Management and Inspection | Fall-in mitigation | VM-08 | [15 empty] | 500 | 500 |  |  | 30 | 30 |  |  | 20 | 20
Vegetation Management and Inspection | Quality assurance / quality control | VM-11 | [15 empty] | 135 |  |  |  | 135 |  |  |  | 135 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development | WP-01 | N/A | N/A | 2020 | 2023 GRC | NA | [10 empty] | 500 |  |  |  | 520 |  |  |  | 544 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.
Wildfire Mitigation Strategy Development | Identifying and Evaluating Mitigation Initiatives | WP-02 | N/A | N/A | 2021 |  | NA | [10 empty] | 100 |  |  |  | 100 |  |  |  | 100 |  | Spend in 2023-2025 is not deferred for work done in the HFTD and amounts will only be provided for territory spend.

## Table 12
Utility | PacifiCorp | Notes:
Table No. | 12
Date Modified | 2024-11-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | Method of Verification | Comments
Grid Design, Operations, and Maintenance | Transmission Patrol inspections | AI-01 | Quantitative | Inspection Counts | 5726 | 9343 | 11754 | N/A | N/A | 12034 | N/A | N/A | 12030 | Quantitative
Grid Design, Operations, and Maintenance | Distribution Patrol Inspections | AI-02 | Quantitative | Inspection Counts | 14430 | 36056 | 50474 | N/A | N/A | 46276 | N/A | N/A | 50485 | Quantitative
Grid Design, Operations, and Maintenance | Transmission Detail Inspections | AI-03 | Quantitative | Inspection Counts | 453 | 1810 | 2715 | N/A | N/A | 1631 | N/A | N/A | 540 | Quantitative
Grid Design, Operations, and Maintenance | Distribution Detail Inspections | AI-04 | Quantitative | Inspection Counts | 3259 | 6501 | 8662 | N/A | N/A | 8672 | N/A | N/A | 10135 | Quantitative
Grid Design, Operations, and Maintenance | Transmission Intrusive Pole Inspections | AI-05 | Quantitative | Inspection Counts | 0 | 561 | 935 | N/A | N/A | 783 | N/A | N/A | 960 | Quantitative
Grid Design, Operations, and Maintenance | Distribution Intrusive Pole Inspections | AI-06 | Quantitative | Inspection Counts | 298 | 1561 | 2404 | N/A | N/A | 2523 | N/A | N/A | 3173 | Quantitative
Grid Design, Operations, and Maintenance | Enhanced (Infrared) Inspections in Transmission Lines | AI-07 | Quantitative | Line miles | 125 | 131 | 701 | N/A | N/A | 700 | N/A | N/A | 700 | Quantitative
Grid Design, Operations, and Maintenance | Enhanced (Infrared) Inspections in Distribution Lines | AI-08 | Quantitative | Line miles | 0 | 814 | 814 | N/A | N/A | 810 | N/A | N/A | TBD | Quantitative
Grid Design, Operations, and Maintenance | Substation Inspections | AI-11 | Quantitative | Inspection Counts | 225 | 393 | 451 | N/A | N/A | 451 | N/A | N/A | 451 | Quantitative
Grid Design, Operations, and Maintenance | QA/QC (Asset Inspections) | AI-12 | Quantitative | Inspection Counts | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Quantitative
Community Outreach and Engagement | Public Outreach and Education Awareness Program | CO-01 | Qualitative | N/A | Complete annual pre-fire season wildfire awareness survey | N/A | Complete annual post-fire season wildfire awareness survey | N/A | N/A | >55% of wildfire safety and preparedness survey participants are aware of wildfire safety communications | N/A | N/A | >60% of wildfire safety and preparedness survey participants are aware of wildfire safety communications | Survey results
Emergency Preparedness | External Collaboration and Coordination | EP-02 | Qualitative | N/A | Conduct: 1 Tabletop Exercise (TTX) | N/A | Conduct: 1 Tabletop Exercise (TTX) 1 Functional Exercise (FE) 1 workshop | N/A | N/A | Conduct: 1 Tabletop Exercise (TTX) 1 Functional Exercise (FE) 1 workshop | N/A | N/A | Conduct: 1 Tabletop Exercise (TTX) 1 Functional Exercise (FE) 1 workshop | After Action Report and Improvement Plan (AAR/IP); Workshop presentation materials
Grid Design, Operations, and Maintenance | Line Rebuild - Covered conductor installation | GH-01 | Quantitative | Line miles | 44 | 104 | 130 | N/A | N/A | 80 | N/A | N/A | 120 | Quantitative
Grid Design, Operations, and Maintenance | Distribution Pole Replacement | GH-02 | Quantitative | Poles | 880 | 2040 | 2600 | N/A | N/A | 1600 | N/A | N/A | 2400 | Quantitative
Grid Design, Operations, and Maintenance | Transmission Pole Replacement | GH-03 | Quantitative | Poles | 75 | 150 | 260 | N/A | N/A | 160 | N/A | N/A | 240 | Quantitative
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GH-04 | Quantitative | Devices | 22 | 36 | 40 | N/A | N/A | 20 | N/A | N/A | 10 | Quantitative
Grid Design, Operations, and Maintenance | Expulsion fuse replacement | GH-05 | Quantitative | Fuse locations | 1800 | 4100 | 5000 | N/A | N/A | 500 | N/A | N/A | 500 | Quantitative
Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair | MA-01 | Quantitative | Unit | 60 | 93 | 93 | N/A | N/A | 108 | N/A | N/A | 116 | Quantitative
Situational Awareness and Forecasting | Environmental monitoring systems | SA-01 | Quantitative | Unit | 8 | 11 | 12 | N/A | N/A | 8 | N/A | N/A | 5 | Quantitative
Situational Awareness and Forecasting | Distribution Fault Anticipation (DFA) Sensor Pilot | SA-02 | Quantitative | Unit | 2 | 2 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | Number of units installed
Situational Awareness and Forecasting | Smoke and Air Quality Sensors | SA-03 | Quantitative | Unit | 20 | 20 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | Number of units installed
Situational Awareness and Forecasting | Ignition Detection Systems | SA-04 | Quantitative | Unit | 0 | 0 | 2 | N/A | N/A | 6 | N/A | N/A | 0 | Number of units installed
Vegetation Management | Detailed Inspection – Distribution | VM-01 | Quantitative | Line miles | 450 | 700 | 829 | N/A | N/A | 874 | N/A | N/A | 826 | Inspection records, billing, project closeout documentation, and field verification
Vegetation Management | Detailed Inspection - Transmission | VM-02 | Quantitative | Line miles | 158 | 211 | 264 | N/A | N/A | 602 | N/A | N/A | 270 | Inspection records, billing, project closeout documentation, and field verification
Vegetation Management | Patrol Inspection - Distribution | VM-03 | Quantitative | Line miles | 820 | 1027 | 1027 | N/A | N/A | 865 | N/A | N/A | 922 | Inspection records, billing, project closeout documentation, and field verification
Vegetation Management | Patrol Inspection - Transmission | VM-04 | Quantitative | Line miles | 296 | 329 | 329 | N/A | N/A | 99 | N/A | N/A | 329 | Inspection records, billing, project closeout documentation, and field verification
Vegetation Management | Fuels management – Pole clearing beyond PRC 4292 | VM-05 | Quantitative | Poles | N/A | N/A | 3126 | N/A | N/A | 3126 | N/A | N/A | 3126 | annual post work audit by internal staff
Vegetation Management | QAQC - Post-Audits Distribution (Patrol) | VM-11 | Quantitative | Line miles | 635 | 1027 | 1027 | N/A | N/A | 865 | N/A | N/A | 922 | Mileage documentation and tracking
Vegetation Management | QAQC - Post-Audits Transmission (Patrol) | VM-11 | Quantitative | Line miles | 175 | 329 | 329 | N/A | N/A | 99 | N/A | N/A | 329 | Mileage documentation and tracking

## Table 13
Utility | PacifiCorp |  | Note: Provide a listing (as rows) of all work orders / notifications for corrective work on electric circuits that were open as of the end of the quarter.
Table No. | 13
Date Modified | 2024-11-01
Table 13: Open work orders / notifications
a. Work order number | b. Equipment Type | c. HFTD Tier | d. Line type | e. Date the work order was originally opened | f. Due date of the original work order | g. GO 95 rule 18 priority level of the original work order | h. Optional utility-specific repair priority | i. Date(s) the work order was reinspected or modified (if applicable) | j. Due date of the work order after it was reinspected or modified (if applicable) | k. Priority of the work order after it was reinspected or modified (if applicable) | l. Reason for reinspection (if applicable)
33213714-99660-DETAIL-01_11_2023-SVCENTCO-1^06240004.0099004 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
766221624-61090-DETAIL-01_11_2023-GO95MLD-1^06240004.0099005 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
254029874-56855-ADMIN-12_01_2023-POLEREPL-1^06240004.0099040 | POLE | CA-TIER-2 | Distribution | 2023-12-01 | 2024-12-01 | 2
713276544-82760-DETAIL-01_11_2023-GO95MLD-1^06240004.0099042 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
554572814-50560-AUDIT-02_07_2023-SVCROAD-1^06240004.0099045 | OTHER | CA-TIER-2 | Distribution | 2023-02-07 | 2026-02-07 | 2
715466268-64043-DETAIL-01_11_2023-SVCENTCO-1^06240004.0099100 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
558618254-86860-DETAIL-01_11_2023-GO95TCH-1^06240004.0099141 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
459698874-93460-DETAIL-01_10_2023-SVCENTCO-1^06240004.0099201 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
459698874-93460-DETAIL-01_10_2023-SVCROAD-1^06240004.0099201 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
698511403-89960-DETAIL-01_11_2023-GO95MLD-1^06240004.0099241 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
392161634-12190-DETAIL-05_08_2023-GUYHINS-1^06240004.0100007 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
566637345-70240-DETAIL-05_08_2023-SVCROAD-1^06240004.0100012 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
122398574-92740-DETAIL-05_08_2023-GO95MLD-1^06240004.0100101 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
338128505-93140-DETAIL-05_08_2023-GUYHINS-1^06240004.0102003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
338128505-93140-DETAIL-05_08_2023-GUYHINS-2^06240004.0102003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
256268675-72040-DETAIL-05_08_2023-RISEGRD-1^06240004.0103001 | OTHER | CA-TIER-2 | Distribution | 2023-05-08 | 2026-05-08 | 2
780845423-45680-DETAIL-04_17_2023-GUYHINS-1^06240004.0160802 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
503050223-22680-DETAIL-04_17_2023-GO95HV-1^06240004.0160803 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
135071564-43564-DETAIL-04_17_2023-GO95MLD-1^06240004.0160900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
605035639-96770-DETAIL-03_23_2023-SVCDEFLC-1^06240004.0161401 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
786122268-81570-DETAIL-03_23_2023-SVCDEFLC-1^06240004.0161402 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
786122268-81570-DETAIL-03_23_2023-SVCDEFLC-2^06240004.0161402 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
650855233-13880-DETAIL-03_27_2023-GO95BLTC-1^06240004.0162501 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
60988283-27980-DETAIL-03_21_2023-GO95MLD-1^06240004.0162502 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
827050653-70653-DETAIL-03_27_2023-GO95BLTC-1^06240004.0162503 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
833084323-27180-DETAIL-03_21_2023-GO95TCH-1^06240004.0162601 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
833084323-27180-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0162601 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
710094148-40350-DETAIL-03_21_2023-GO95MLD-1^06240004.0162603 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
710094148-40350-DETAIL-03_21_2023-GUYHINS-1^06240004.0162603 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
767709178-87650-DETAIL-03_21_2023-GO95CL10-1^06240004.0162642 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
767709178-87650-DETAIL-03_21_2023-GO95HV-1^06240004.0162642 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
326423368-35650-DETAIL-03_21_2023-GO95HV-1^06240004.0162643 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
326423368-35650-DETAIL-03_21_2023-GUYHINS-1^06240004.0162643 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
895612633-80280-DETAIL-03_21_2023-GO95MLD-1^06240004.0162700 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
244463208-57240-DETAIL-03_21_2023-ABNDEQPM-1^06240004.0162703 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
244463208-57240-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0162703 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
501551528-1340-DETAIL-03_21_2023-GUYNOINS-1^06240004.0162705 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
587253983-66380-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0163500 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
138006878-74840-DETAIL-03_27_2023-GO95TCH-1^06240004.0163501 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
364175297-46240-DETAIL-03_27_2023-GO95HV-1^06240004.0163502 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
364175297-46240-DETAIL-03_27_2023-GO95MLD-1^06240004.0163502 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
651565833-2880-DETAIL-03_23_2023-GO95MLD-1^06240004.0163504 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
636383136-44410-DETAIL-03_27_2023-GO95MLD-1^06240004.0163505 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
359676701-87680-DETAIL-03_21_2023-GO95HV-1^06240004.0163600 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
567809923-86480-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0163601 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
66355563-54980-DETAIL-03_21_2023-GO95MLD-1^06240004.0163602 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
66355563-54980-DETAIL-03_21_2023-GO95TCH-1^06240004.0163602 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
398506286-9210-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0163603 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
279401196-17310-DETAIL-03_21_2023-GO95HV-1^06240004.0163605 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
279401196-17310-DETAIL-03_21_2023-GO95MLD-1^06240004.0163605 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
279401196-17310-DETAIL-03_21_2023-GUYHINS-1^06240004.0163605 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
279401196-17310-DETAIL-03_21_2023-GUYHINS-2^06240004.0163605 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
990074506-98310-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0163607 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
611816-2410-DETAIL-03_27_2023-GO95MLD-1^06240004.0163608 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
688622223-55780-DETAIL-03_27_2023-GO95MLD-1^06240004.0163611 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
5705003-24480-DETAIL-03_21_2023-GO95MLD-1^06240004.0163702 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
378286658-36350-DETAIL-03_21_2023-GO95MLD-1^06240004.0163703 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
897252593-49380-DETAIL-03_21_2023-GO95MLD-1^06240004.0163705 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
873228383-34380-DETAIL-04_19_2023-GO95MLD-1^06240004.0163800 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
560341048-7550-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0163941 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
49601419-17670-DETAIL-04_19_2023-GO95MLD-1^06240004.0164401 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
34066709-95670-DETAIL-04_19_2023-GO95MLD-1^06240004.0164403 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
943946698-37570-DETAIL-04_19_2023-GO95HV-1^06240004.0164405 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
943946698-37570-DETAIL-04_19_2023-GO95HV-2^06240004.0164405 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
247337193-30080-DETAIL-04_19_2023-GO95MLD-1^06240004.0164500 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
171905963-1380-DETAIL-04_19_2023-GO95HV-1^06240004.0164503 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
239845283-34680-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0164506 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
18413323-6480-DETAIL-03_23_2023-GO95HV-1^06240004.0164600 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2028-03-23 | 3
18413323-6480-DETAIL-03_23_2023-GO95MLD-1^06240004.0164600 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2026-03-23 | 2
683437243-52280-DETAIL-03_27_2023-GO95MLD-1^06240004.0164603 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
237495403-88680-DETAIL-03_28_2023-GUYHINS-1^06240004.0164604 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
8281781-36680-DETAIL-03_27_2023-GUYNOINS-1^06240004.0164605 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
391615878-49840-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0164607 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
966628763-41980-DETAIL-03_27_2023-GO95CL10-1^06240004.0164608 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2028-03-27 | 3
966628763-41980-DETAIL-03_27_2023-GO95MLD-1^06240004.0164608 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
782675398-24750-DETAIL-03_29_2023-GO95MLD-1^06240004.0164740 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
708882413-73180-DETAIL-04_19_2023-GO95MLD-1^06240004.0164800 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
952795588-25550-DETAIL-03_29_2023-POLESTEP-1^06240004.0164844 | POLE | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
385177378-1550-DETAIL-04_19_2023-GO95MLD-1^06240004.0164846 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
385177378-1550-DETAIL-04_19_2023-GUYHINS-1^06240004.0164846 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
745358513-34180-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0164900 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
680039673-73380-DETAIL-04_19_2023-GO95MLD-1^06240004.0165401 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
680039673-73380-DETAIL-04_19_2023-RISEGRD-1^06240004.0165401 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
506063273-61380-DETAIL-04_19_2023-GO95MLD-1^06240004.0165403 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
228127509-71570-DETAIL-03_28_2023-ABNDEQPM-1^06240004.0165501 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
245959370-82970-DETAIL-03_28_2023-GO95MLD-1^06240004.0165503 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
603032780-77270-DETAIL-04_19_2023-GO95MLD-1^06240004.0165506 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
801882231-89180-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0165540 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
987259911-56970-DETAIL-04_17_2023-GO95MLD-1^06240004.0165641 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
622785331-95080-DETAIL-04_17_2023-GO95BLTC-1^06240004.0165643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
622785331-95080-DETAIL-04_17_2023-GO95CL10-1^06240004.0165643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
622785331-95080-DETAIL-04_17_2023-GO95HV-1^06240004.0165643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
862460663-10380-DETAIL-03_29_2023-SVCDEFLC-1^06240004.0165701 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
639928567-73670-DETAIL-03_28_2023-GO95MLD-1^06240004.0165800 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
459384087-14670-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0165802 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
335068058-25970-DETAIL-04_12_2023-GO95MLD-1^06240004.0165804 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
335068058-25970-DETAIL-04_12_2023-GO95TCH-1^06240004.0165804 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
335068058-25970-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0165804 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
335068058-25970-DETAIL-04_12_2023-SVCWIND-1^06240004.0165804 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
706177888-67570-DETAIL-04_17_2023-GUYHINS-1^06240004.0165805 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
857023568-4450-DETAIL-03_28_2023-GO95MLD-1^06240004.0165840 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
857023568-4450-DETAIL-03_28_2023-SVCWIND-1^06240004.0165840 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
270644919-16270-DETAIL-03_29_2023-GO95MLD-1^06240004.0165841 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
270644919-16270-DETAIL-03_29_2023-GO95TCH-1^06240004.0165841 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
270644919-16270-DETAIL-03_29_2023-POLESTEP-1^06240004.0165841 | POLE | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
694430629-49070-DETAIL-04_12_2023-GO95MLD-1^06240004.0165900 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
745680919-57070-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0165901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
573660998-59070-DETAIL-04_12_2023-GO95MLD-1^06240004.0165902 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
463618668-53870-DETAIL-04_12_2023-GO95MLD-1^06240004.0165906 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
636490870-79570-DETAIL-03_27_2023-GO95TCH-1^06240004.0166000 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
860010230-57870-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166100 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
79123001-50970-DETAIL-03_22_2023-GO95MLD-1^06240004.0166101 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
79123001-50970-DETAIL-03_22_2023-SVCRUBLG-1^06240004.0166101 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
636548079-40570-DETAIL-03_22_2023-GO95HV-1^06240004.0166102 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
86165630-27870-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166103 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
591558790-79270-DETAIL-03_22_2023-GO95MLD-1^06240004.0166104 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
591558790-79270-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166104 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
591558790-79270-DETAIL-03_22_2023-SVCDEFLC-2^06240004.0166104 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
957553731-45080-DETAIL-03_22_2023-GO95TCH-1^06240004.0166105 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
957553731-45080-DETAIL-03_22_2023-SVCENTCO-1^06240004.0166105 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
35983081-79380-DETAIL-03_22_2023-GO95TCH-1^06240004.0166140 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
664194000-42370-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166202 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
279709423-46680-DETAIL-03_22_2023-GO95MLD-1^06240004.0166203 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
279709423-46680-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166203 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
875049161-84261-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166208 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
112292551-35180-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0166301 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
112292551-35180-DETAIL-03_21_2023-SVCDEFLC-2^06240004.0166301 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
92945831-8080-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0166303 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
949792741-12180-DETAIL-03_21_2023-SVCROOF-1^06240004.0166304 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
949792741-12180-DETAIL-03_21_2023-SVCWIND-1^06240004.0166304 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
3583480-7270-DETAIL-03_21_2023-GO95TCH-1^06240004.0166305 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
3583480-7270-DETAIL-03_21_2023-GUYHINS-1^06240004.0166305 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
3583480-7270-DETAIL-03_21_2023-SVCROAD-1^06240004.0166305 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
3583480-7270-ENHANCED-08_08_2024-IRSPOTOH-1^06240004.0166305 | OTHER | CA-TIER-2 | Distribution | 2024-08-08 | 2025-08-08 | 2
536428272-83302-DETAIL-03_22_2023-GO95HV-1^06240004.0166306 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
536428272-83302-DETAIL-03_22_2023-GO95MLD-1^06240004.0166306 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
455550172-20880-DETAIL-03_22_2023-GO95MLD-1^06240004.0166310 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
501080272-66880-DETAIL-03_28_2023-GO95MLD-1^06240004.0166400 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
884870580-42670-DETAIL-04_12_2023-GO95MLD-1^06240004.0166402 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
884870580-42670-DETAIL-04_12_2023-SVCENTCO-1^06240004.0166402 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
406857680-19770-DETAIL-04_12_2023-GO95HV-1^06240004.0166500 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
854512820-86870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166502 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
480388800-93070-DETAIL-04_12_2023-GUYHINS-1^06240004.0166503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
480388800-93070-DETAIL-04_12_2023-GUYHINS-2^06240004.0166503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
577396250-32870-DETAIL-04_12_2023-GO95STUB-1^06240004.0166504 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
71652830-93170-DETAIL-04_12_2023-GO95MLD-1^06240004.0166507 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
349021370-54870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166508 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
467960938-26343-DETAIL-04_12_2023-SVCROOF-1^06240004.0166509 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
938362990-99270-DETAIL-04_12_2023-GO95BLTC-1^06240004.0166511 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
53447961-52980-DETAIL-04_17_2023-GO95MLD-1^06240004.0166540 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
64472204-71259-DETAIL-04_12_2023-GO95HV-1^06240004.0166601 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
64472204-71259-DETAIL-04_12_2023-SVCENTCO-1^06240004.0166601 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
259645324-66324-DETAIL-04_12_2023-GO95HV-1^06240004.0166610 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
398102401-53401-DETAIL-04_17_2023-GO95MLD-1^06240004.0166611 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
29261841-49280-DETAIL-04_17_2023-GO95MLD-1^06240004.0166641 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
29261841-49280-DETAIL-04_17_2023-GUYHINS-1^06240004.0166641 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
401781783-6550-DETAIL-04_17_2023-RISEGRD-1^06240004.0166642 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
401781783-6550-DETAIL-04_17_2023-SVCROAD-1^06240004.0166642 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
786104514-22799-DETAIL-04_17_2023-GO95MLD-1^06240004.0166643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
786104514-22799-DETAIL-04_17_2023-SVCWIND-1^06240004.0166643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
786104514-22799-DETAIL-04_17_2023-SVCWIND-2^06240004.0166643 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
452556801-40399-DETAIL-04_17_2023-GO95MLD-1^06240004.0166644 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
452556801-40399-DETAIL-04_17_2023-RISEGRD-1^06240004.0166644 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
100743301-96080-DETAIL-04_17_2023-GO95MLD-1^06240004.0166645 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
288969418-94670-DETAIL-04_17_2023-GO95MLD-1^06240004.0166700 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
777300119-20465-DETAIL-04_12_2023-GO95MLD-1^06240004.0166701 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
62426070-74270-DETAIL-04_12_2023-GO95MLD-1^06240004.0166703 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
164918120-40870-DETAIL-04_12_2023-GO95BLTC-1^06240004.0166704 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
164918120-40870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166704 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
445323300-46870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166705 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
445323300-46870-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0166705 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
925054519-20470-DETAIL-03_29_2023-GO95MLD-1^06240004.0166841 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
683344569-42370-DETAIL-03_29_2023-GO95MLD-1^06240004.0166842 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
40626528-59870-DETAIL-03_29_2023-GO95MLD-1^06240004.0166900 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
318312388-59770-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0166901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
318312388-59770-DETAIL-04_12_2023-SVCDEFLC-2^06240004.0166901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
318312388-59770-DETAIL-04_12_2023-SVCENTCO-1^06240004.0166901 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
33796397-64670-DETAIL-04_12_2023-GO95HV-1^06240004.0166902 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
33796397-64670-DETAIL-04_12_2023-GO95MLD-1^06240004.0166902 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
251764928-54170-DETAIL-03_28_2023-GO95MLD-1^06240004.0166905 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
251764928-54170-DETAIL-03_28_2023-GO95TCH-1^06240004.0166905 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
580976323-97323-DETAIL-03_27_2023-ENCHRW-1^06240004.0167030 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
386901350-50570-DETAIL-03_27_2023-GUYNOINS-1^06240004.0167040 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
640218151-29180-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167041 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
627715401-52970-DETAIL-03_22_2023-GO95MLD-1^06240004.0167101 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
627715401-52970-DETAIL-03_22_2023-GO95TCH-1^06240004.0167101 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
935643511-11180-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167103 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
521844420-11470-DETAIL-03_27_2023-GO95MLD-1^06240004.0167104 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
528405420-52470-DETAIL-03_27_2023-GO95MLD-1^06240004.0167105 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
670358610-69370-DETAIL-03_27_2023-GO95MLD-1^06240004.0167107 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
986931581-86380-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167141 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
951220914-3760-DETAIL-03_22_2023-GO95HV-1^06240004.0167143 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
278932831-54080-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0167200 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
278932831-54080-DETAIL-03_22_2023-SVCDEFLC-2^06240004.0167200 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
278932831-54080-DETAIL-03_22_2023-SVCWIND-1^06240004.0167200 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
395095243-1780-DETAIL-03_22_2023-SVCWIND-1^06240004.0167202 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
516792832-82880-DETAIL-03_22_2023-GO95MLD-1^06240004.0167204 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
577993399-1570-DETAIL-04_11_2023-GO95MLD-1^06240004.0167207 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
598165850-99870-DETAIL-03_22_2023-GO95MLD-1^06240004.0167208 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
598165850-99870-DETAIL-03_22_2023-GUYHINS-1^06240004.0167208 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
102877192-21880-DETAIL-03_27_2023-GO95MLD-1^06240004.0167209 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
102877192-21880-DETAIL-03_27_2023-SVCWIND-1^06240004.0167209 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
858338512-75780-DETAIL-03_22_2023-GO95MLD-1^06240004.0167240 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
452855181-40780-DETAIL-03_22_2023-GO95MLD-1^06240004.0167242 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
774502352-96780-DETAIL-03_27_2023-GO95TCH-1^06240004.0167245 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
774502352-96780-DETAIL-03_27_2023-SVCWIND-1^06240004.0167245 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
358281493-580-DETAIL-03_21_2023-GO95MLD-1^06240004.0167301 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
853910491-22080-DETAIL-04_11_2023-GO95MLD-1^06240004.0167302 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
693368121-99970-DETAIL-03_22_2023-GO95MLD-1^06240004.0167306 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
693368121-99970-DETAIL-03_22_2023-GO95TCH-1^06240004.0167306 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
469810059-59470-DETAIL-03_21_2023-GO95MLD-1^06240004.0167308 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
338918142-86780-DETAIL-03_22_2023-SVCWIND-1^06240004.0167341 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
850452241-94680-DETAIL-03_21_2023-GO95MLD-1^06240004.0167342 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
657507920-92170-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0167400 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
404766230-80870-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0167401 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
404766230-80870-DETAIL-04_12_2023-SVCDEFLC-2^06240004.0167401 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
955803518-25670-DETAIL-04_11_2023-GO95HV-1^06240004.0167402 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2028-04-11 | 3
955803518-25670-DETAIL-04_11_2023-GO95MLD-1^06240004.0167402 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
281159569-85470-DETAIL-04_11_2023-GO95MLD-1^06240004.0167403 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
868928573-33480-DETAIL-04_11_2023-GO95MLD-1^06240004.0167406 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
868928573-33480-DETAIL-04_11_2023-SVCENTCO-1^06240004.0167406 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
653043290-47670-DETAIL-03_29_2023-GO95HV-1^06240004.0167407 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2028-03-29 | 3
687984290-19670-DETAIL-03_21_2023-GO95HV-1^06240004.0167411 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2028-03-21 | 3
687984290-19670-DETAIL-03_21_2023-GO95MLD-1^06240004.0167411 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
406980263-10680-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0167413 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
406980263-10680-DETAIL-03_21_2023-SVCRUBLG-1^06240004.0167413 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
516954791-21780-DETAIL-03_21_2023-GO95MLD-1^06240004.0167415 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
516954791-21780-DETAIL-03_21_2023-GO95TCH-1^06240004.0167415 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
516954791-21780-DETAIL-03_21_2023-SVCDEFLC-1^06240004.0167415 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
42362859-58470-DETAIL-03_21_2023-GO95MLD-1^06240004.0167416 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
42362859-58470-DETAIL-03_21_2023-GO95TCH-1^06240004.0167416 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
277492210-11170-DETAIL-03_21_2023-GO95MLD-1^06240004.0167417 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
277492210-11170-DETAIL-03_21_2023-GO95TCH-1^06240004.0167417 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
637043361-8280-DETAIL-03_21_2023-GO95TCH-1^06240004.0167441 | OTHER | CA-TIER-2 | Distribution | 2023-03-21 | 2026-03-21 | 2
558953990-69770-DETAIL-04_12_2023-SVCROOF-1^06240004.0167501 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
133947108-20670-DETAIL-04_11_2023-GO95MLD-1^06240004.0167502 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
133947108-20670-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0167502 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
101966518-87870-DETAIL-04_11_2023-GO95MLD-1^06240004.0167503 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
745869738-85170-DETAIL-04_11_2023-GO95MLD-1^06240004.0167504 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
745869738-85170-DETAIL-04_11_2023-GUYHINS-1^06240004.0167504 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
745869738-85170-ENHANCED-08_13_2024-IRSPOTOH-1^06240004.0167504 | OTHER | CA-TIER-2 | Distribution | 2024-08-13 | 2025-08-13 | 2
61996389-34370-DETAIL-03_28_2023-GO95HV-1^06240004.0167541 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
176215011-36780-DETAIL-04_17_2023-SVCWIND-1^06240004.0167543 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
176215011-36780-DETAIL-04_17_2023-SVCWIND-2^06240004.0167543 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
734638989-67170-DETAIL-04_11_2023-GO95TCH-1^06240004.0167548 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
350294799-58170-DETAIL-03_28_2023-RISECLMB-1^06240004.0167549 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
788703292-24292-DETAIL-04_19_2023-GO95MLD-1^06240004.0167550 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
788703292-24292-DETAIL-04_19_2023-RISEGRD-1^06240004.0167550 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
912219292-10392-DETAIL-04_17_2023-GO95MLD-1^06240004.0167551 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
891190580-14670-DETAIL-04_12_2023-GO95MLD-1^06240004.0167700 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
337237760-3870-DETAIL-04_12_2023-SVCWIND-1^06240004.0167701 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
30748950-270-DETAIL-04_12_2023-GO95MLD-1^06240004.0167702 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
181798893-993-DETAIL-04_12_2023-GO95MLD-1^06240004.0167703 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
181798893-993-DETAIL-04_12_2023-RISEGRD-1^06240004.0167703 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
372540369-65170-DETAIL-03_28_2023-GO95HV-1^06240004.0167800 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
657392968-41570-DETAIL-03_28_2023-GO95MLD-1^06240004.0167802 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
406204828-10770-DETAIL-03_28_2023-GO95MLD-1^06240004.0167804 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
56243918-93670-DETAIL-04_12_2023-GO95HV-1^06240004.0167900 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
56243918-93670-DETAIL-04_12_2023-GO95HV-2^06240004.0167900 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
56243918-93670-DETAIL-04_12_2023-GO95TCH-1^06240004.0167900 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
153792948-43970-DETAIL-03_28_2023-GO95MLD-1^06240004.0167901 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
790235282-1880-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168000 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
790235282-1880-DETAIL-04_10_2023-SVCDEFLC-2^06240004.0168000 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
196210244-97170-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0168046 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
349405651-55380-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168142 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
961384991-64780-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0168144 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
941558360-3870-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168304 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
481973979-37570-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168305 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
545172148-81270-ADMIN-05_28_2024-POLEREPL-1^06240004.0168507 | POLE | CA-TIER-2 | Distribution | 2024-05-28 | 2025-05-28 | 2
653037698-70770-DETAIL-04_11_2023-SVCWIND-1^06240004.0168509 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
336857039-71470-ADMIN-12_05_2023-POLEREPL-1^06240004.0168541 | POLE | CA-TIER-2 | Distribution | 2023-12-05 | 2024-12-05 | 2
980450708-81670-DETAIL-03_28_2023-GO95MLD-1^06240004.0168902 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
566153022-26780-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0169042 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
566153022-26780-DETAIL-04_10_2023-SVCDEFLC-2^06240004.0169042 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
241282521-79580-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0169044 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
526880731-61680-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0169045 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
526880731-61680-DETAIL-04_10_2023-SVCDEFLC-2^06240004.0169045 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
86565588-6799-DETAIL-03_22_2023-SVCWIND-1^06240004.0169142 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
913258219-12570-ENHANCED-08_08_2024-IRSPOTOH-1^06240004.0169203 | OTHER | CA-TIER-2 | Distribution | 2024-08-08 | 2025-08-08 | 2
691429680-54870-DETAIL-04_11_2023-GO95CLSV-1^06240004.0169302 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
648151361-87680-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0169402 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
360691820-76870-AUDIT-05_22_2023-SVCDEFLC-1^06240004.0169403 | OTHER | CA-TIER-2 | Distribution | 2023-05-22 | 2026-05-22 | 2
419291821-86180-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0169404 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
244774768-22570-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0169500 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
989651188-85070-DETAIL-03_28_2023-GO95MLD-1^06240004.0169502 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
343252448-96670-DETAIL-04_12_2023-SVCDEFLC-1^06240004.0169503 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
343252448-96670-ADMIN-05_07_2024-POLEREPL-1^06240004.0169503 | POLE | CA-TIER-2 | Distribution | 2024-05-07 | 2025-05-07 | 2
918712298-37070-DETAIL-03_28_2023-GO95MLD-1^06240004.0169504 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
602295238-46670-DETAIL-03_28_2023-GO95MLD-1^06240004.0169506 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
602295238-46670-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0169506 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
835770848-48670-DETAIL-03_28_2023-GO95TCH-1^06240004.0169507 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
835770848-48670-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0169507 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
835770848-48670-DETAIL-03_28_2023-SVCENTCO-1^06240004.0169507 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
508246828-55670-DETAIL-03_28_2023-GO95MLD-1^06240004.0169509 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
508246828-55670-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0169509 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
113600818-55770-DETAIL-04_12_2023-ABNDEQPM-1^06240004.0169510 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2028-04-12 | 3
343990278-48770-DETAIL-04_11_2023-RISEGRD-1^06240004.0169511 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
753653689-84370-DETAIL-03_28_2023-GO95MLD-1^06240004.0169540 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
753653689-84370-DETAIL-03_28_2023-GO95TCH-1^06240004.0169540 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
145701299-56370-DETAIL-03_28_2023-GUYNOINS-1^06240004.0169543 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
145701299-56370-DETAIL-03_28_2023-GUYNOINS-2^06240004.0169543 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
77522768-41070-DETAIL-04_12_2023-SVCWIND-1^06240004.0169600 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
398134749-75470-DETAIL-03_28_2023-GO95MLD-1^06240004.0169640 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
764157138-74470-DETAIL-03_28_2023-GO95MLD-1^06240004.0169700 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
864951588-91569-DETAIL-03_28_2023-GO95HV-1^06240004.0169800 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
864951588-91569-DETAIL-03_28_2023-GO95MLD-1^06240004.0169800 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
329220608-33170-DETAIL-03_28_2023-GO95HV-1^06240004.0169900 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2028-03-28 | 3
329220608-33170-DETAIL-03_28_2023-GO95MLD-1^06240004.0169900 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
776399661-9730-DETAIL-04_19_2023-SVCWIND-1^06240004.0171900 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
353174591-80530-DETAIL-04_19_2023-GO95MLD-1^06240004.0171902 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
918774504-55903-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0171941 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
359454613-12590-DETAIL-04_20_2023-SVCDEFLC-1^06240004.0172500 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2026-04-20 | 2
915879023-26230-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0172942 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
98432090-33030-DETAIL-04_17_2023-GO95HV-1^06240004.0175504 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
5465273-56390-DETAIL-03_23_2023-ABNDEQPM-1^06240004.0176401 | OTHER | CA-TIER-2 | Distribution | 2023-03-23 | 2028-03-23 | 3
188529451-52230-DETAIL-04_20_2023-GO95HV-1^06240004.0176501 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
355280151-71230-DETAIL-04_17_2023-GO95MLD-1^06240004.0176502 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
370630851-21230-DETAIL-04_17_2023-GO95HV-1^06240004.0176503 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
329537631-67130-DETAIL-04_17_2023-GO95MLD-1^06240004.0176601 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
500768921-85130-DETAIL-04_17_2023-ABNDEQPM-1^06240004.0176701 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
500768921-85130-DETAIL-04_17_2023-GO95HV-1^06240004.0176701 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
500768921-85130-DETAIL-04_17_2023-GO95MLD-1^06240004.0176701 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
90946875-39875-DETAIL-04_17_2023-GO95BLTC-1^06240004.0176803 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
218483550-46830-DETAIL-04_17_2023-GO95MLD-1^06240004.0176804 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
657765011-79030-DETAIL-04_17_2023-GO95MLD-1^06240004.0176900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
657765011-79030-DETAIL-04_17_2023-SVCDEFLC-1^06240004.0176900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
252873131-60430-DETAIL-04_17_2023-SVCDEFLC-1^06240004.0176902 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
459658880-69930-DETAIL-04_19_2023-GO95BLTC-1^06240004.0177701 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
459658880-69930-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0177701 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
459918801-96030-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0177702 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
466443101-63330-DETAIL-04_19_2023-GO95MLD-1^06240004.0177804 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2028-04-19 | 3
283110220-62630-DETAIL-04_17_2023-SVCDEFLC-1^06240004.0177940 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
874852711-45330-DETAIL-04_17_2023-GO95HV-1^06240004.0178900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
874852711-45330-DETAIL-04_17_2023-GO95MLD-1^06240004.0178900 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
744849581-75730-DETAIL-01_25_2023-SVCDEFLC-1^06240004.0186800 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
265631291-95730-DETAIL-01_25_2023-SVCDEFLC-1^06240004.0186900 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2026-01-25 | 2
393525851-11730-DETAIL-01_23_2023-SVCDEFLC-1^06240004.0189700 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
811134628-94043-ADMIN-09_19_2022-GUYHINS-1^06240004.0214541 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-09-19 | 2025-09-19 | 2
657407392-87080-DETAIL-01_25_2023-GO95TCH-1^06240005.0015000 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2026-01-25 | 2
657407392-87080-DETAIL-01_25_2023-SVCDEFLC-1^06240005.0015000 | OTHER | CA-TIER-3 | Distribution | 2023-01-25 | 2026-01-25 | 2
277313613-49080-DETAIL-01_25_2023-GO95MLD-1^06240005.0016101 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
229078143-12180-DETAIL-01_25_2023-RISECLMB-1^06240005.0016201 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
229078143-12180-DETAIL-01_25_2023-RISEGRD-1^06240005.0016201 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
49172771-61963-DETAIL-01_25_2023-GO95MLD-1^06240005.0128900 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
49172771-61963-DETAIL-01_25_2023-SVCDEFLC-1^06240005.0128900 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
28667661-82263-DETAIL-01_25_2023-SVCDEFLC-1^06240005.0128902 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
95960671-73263-DETAIL-01_24_2023-SVCDEFLC-1^06240005.0129900 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
649486253-25341-DETAIL-02_08_2022-GO95MLD-1^06241004.0182303 | OTHER | CA-TIER-3 | Distribution | 2022-02-08 | 2025-02-08 | 2
799487483-81490-DETAIL-06_27_2024-SVCDEFLC-1^06241004.0313100 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
426363924-53590-DETAIL-06_27_2024-GO95CL10-1^06241004.0313200 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
702750559-57559-DETAIL-04_25_2023-SVCROAD-1^06241004.0313240 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
870747123-8690-DETAIL-06_27_2024-GO95CL10-1^06241004.0314001 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
870747123-8690-DETAIL-06_27_2024-SVCWIND-1^06241004.0314001 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
953335973-83390-DETAIL-06_27_2024-GO95CL10-1^06241004.0314002 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
64448663-64290-DETAIL-06_27_2024-GO95CL10-1^06241004.0314003 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
149940304-46490-DETAIL-04_25_2023-GO95TCH-1^06241004.0314100 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
134023553-21090-DETAIL-04_25_2023-GO95MLD-1^06241004.0314101 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
907037805-37241-DETAIL-05_09_2022-SVCROOF-1^06241005.0011707 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
31501234-22721-DETAIL-05_10_2022-GO95MLD-1^06241005.0012404 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
377793804-18631-DETAIL-05_09_2022-GUYHINS-1^06241005.0013506 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
860596378-64798-DETAIL-05_10_2022-GUYHINS-1^06241005.0013620 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
860596378-64798-DETAIL-05_10_2022-SVCWIND-1^06241005.0013620 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
611126065-52341-DETAIL-05_03_2022-SVCWIND-1^06241005.0013642 | OTHER | CA-TIER-2 | Distribution | 2022-05-03 | 2025-05-03 | 2
904344566-18271-DETAIL-05_09_2022-SVCRUBLG-1^06241005.0014500 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
748194031-66331-ENHANCED-08_02_2024-IRSPOTOH-1^06241005.0024101 | OTHER | CA-TIER-2 | Distribution | 2024-08-02 | 2025-08-02 | 2
504020846-62868-DETAIL-05_12_2022-GUYHINS-1^06241005.0025602 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
914521398-16652-DETAIL-05_18_2022-ABNDEQPM-1^06241005.0026001 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
914521398-16652-DETAIL-05_18_2022-GO95HV-1^06241005.0026001 | OTHER | CA-TIER-2 | Distribution | 2022-05-18 | 2027-05-18 | 3
297954124-36932-DETAIL-05_18_2022-GUYHINS-1^06241005.0027013 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
163537137-77400-DETAIL-05_18_2022-GUYHINS-1^06241005.0028003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
44458140-68852-DETAIL-05_18_2022-POLESTEP-1^06241005.0028242 | POLE | CA-TIER-2 | Distribution | 2022-05-18 | 2025-05-18 | 2
818338265-23332-DETAIL-05_16_2022-GUYHINS-1^06241005.0028405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
244106715-86032-DETAIL-05_16_2022-GUYHINS-1^06241005.0028406 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
82466240-57601-DETAIL-06_02_2022-GO95HV-1^06241005.0030701 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2027-06-02 | 3
518508479-42391-DETAIL-06_01_2022-GO95HV-1^06241005.0031700 | OTHER | CA-TIER-2 | Distribution | 2022-06-01 | 2027-06-01 | 3
956455860-51901-DETAIL-06_02_2022-GO95MLD-1^06241005.0031701 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
330998460-18801-DETAIL-06_02_2022-GO95MLD-1^06241005.0031703 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
277081250-57701-DETAIL-06_02_2022-GO95MLD-1^06241005.0031704 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
794690014-79241-DETAIL-06_02_2022-GO95MLD-1^06241005.0037900 | OTHER | CA-TIER-2 | Distribution | 2022-06-02 | 2025-06-02 | 2
987169941-99711-DETAIL-06_07_2022-GO95MLD-1^06241005.0109700 | OTHER | CA-TIER-2 | Distribution | 2022-06-07 | 2025-06-07 | 2
474822851-81011-DETAIL-06_07_2022-GO95MLD-1^06241005.0109701 | OTHER | CA-TIER-2 | Distribution | 2022-06-07 | 2025-06-07 | 2
435249654-66471-DETAIL-01_27_2022-GO95BLTC-1^06241005.0114600 | OTHER | CA-TIER-2 | Distribution | 2022-01-27 | 2027-01-27 | 3
273082443-87514-DETAIL-01_13_2022-GO95MLD-1^06241005.0115605 | OTHER | CA-TIER-2 | Distribution | 2022-01-13 | 2025-01-13 | 2
587210352-87684-DETAIL-01_27_2022-GUYHINS-1^06241005.0117611 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
587210352-87684-DETAIL-01_27_2022-GUYHINS-2^06241005.0117611 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
587210352-87684-DETAIL-01_27_2022-GUYHINS-3^06241005.0117611 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
587210352-87684-DETAIL-01_27_2022-GUYHINS-4^06241005.0117611 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-01-27 | 2025-01-27 | 2
699996784-52212-DETAIL-01_26_2022-GO95MLD-1^06241005.0118301 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
396122130-60432-DETAIL-01_26_2022-GO95MLD-1^06241005.0118505 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
715779130-97232-DETAIL-01_26_2022-GO95MLD-1^06241005.0118507 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
703889731-22332-DETAIL-01_26_2022-GO95MLD-1^06241005.0118603 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
956167380-80532-DETAIL-01_26_2022-GO95MLD-1^06241005.0118604 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
818032532-9463-DETAIL-01_26_2022-GO95MLD-1^06241005.0118606 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2027-01-26 | 3
877003933-32302-DETAIL-01_26_2022-GO95MLD-1^06241005.0119402 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
469233321-27452-DETAIL-01_26_2022-GO95MLD-1^06241005.0119403 | OTHER | CA-TIER-2 | Distribution | 2022-01-26 | 2025-01-26 | 2
451071137-74742-DETAIL-01_20_2022-GO95MLD-1^06241005.0121101 | OTHER | CA-TIER-2 | Distribution | 2022-01-20 | 2025-01-20 | 2
468592623-65649-DETAIL-05_05_2022-GO95MLD-1^06241005.0130704 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
142994032-7931-DETAIL-05_11_2022-GO95MLD-1^06241005.0130800 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
877624782-49831-DETAIL-05_05_2022-GO95BLTC-1^06241005.0131505 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2027-05-05 | 3
936447263-62151-DETAIL-05_11_2022-GO95MLD-1^06241005.0131903 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
275032983-8951-DETAIL-05_11_2022-GO95MLD-1^06241005.0132803 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
914656193-22741-DETAIL-05_11_2022-GO95MLD-1^06241005.0132804 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
576054553-26051-DETAIL-05_11_2022-GO95MLD-1^06241005.0133901 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
605768356-34371-DETAIL-05_11_2022-GO95MLD-1^06241005.0149500 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
253920786-48471-DETAIL-05_11_2022-GO95GUYP-1^06241005.0149501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
253920786-48471-DETAIL-05_11_2022-GO95GUYP-2^06241005.0149501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
57042733-57030-AUDIT-06_08_2023-GO95CL10-1^06241005.0250003 | OTHER | CA-TIER-2 | Distribution | 2023-06-08 | 2028-06-08 | 3
21575423-42420-DETAIL-05_02_2023-GUYNOINS-1^06241005.0250004 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
21575423-42420-DETAIL-05_02_2023-GUYNOINS-2^06241005.0250004 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
794397604-19730-DETAIL-05_02_2023-GO95MLD-1^06241005.0252041 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
794397604-19730-DETAIL-05_02_2023-GUYHINS-1^06241005.0252041 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
523970224-91930-DETAIL-05_03_2023-GO95MLD-1^06241005.0252140 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
523970224-91930-DETAIL-05_03_2023-RISEGRD-1^06241005.0252140 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
231588113-83030-DETAIL-05_03_2023-GO95MLD-1^06241005.0253703 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
702913303-41030-DETAIL-05_03_2023-GO95MLD-1^06241005.0254200 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
17292064-48130-DETAIL-05_03_2023-GO95MLD-1^06241005.0254203 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
282485493-11030-DETAIL-05_03_2023-GO95CLSV-1^06241005.0254204 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
282485493-11030-DETAIL-05_03_2023-GO95MLD-1^06241005.0254204 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
344316764-43630-DETAIL-05_03_2023-GO95MLD-1^06241005.0254301 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
406591645-29830-DETAIL-04_27_2023-GO95MLD-1^06241005.0254641 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
406591645-29830-DETAIL-04_27_2023-GRDRODHI-1^06241005.0254641 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
202124574-49130-DETAIL-04_27_2023-GO95MLD-1^06241005.0254800 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
321965736-78301-DETAIL-04_27_2023-GO95MLD-1^06241005.0255500 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
479923836-56401-DETAIL-05_04_2023-GO95MLD-1^06241005.0255601 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2028-05-04 | 3
531208836-83501-DETAIL-05_04_2023-GO95MLD-1^06241005.0255602 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2028-05-04 | 3
52894544-76030-DETAIL-04_27_2023-GO95MLD-1^06241005.0255803 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
402238984-50730-DETAIL-04_27_2023-GO95MLD-1^06241005.0255902 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2028-04-27 | 3
47537374-89630-DETAIL-04_27_2023-GO95HV-1^06241005.0255903 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2028-04-27 | 3
684186079-7079-DETAIL-04_27_2023-GO95HV-1^06241005.0255904 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2028-04-27 | 3
303507738-69050-DETAIL-04_27_2023-GO95MLD-1^06241005.0255940 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
614961934-18930-DETAIL-04_27_2023-GO95MLD-1^06241005.0256441 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
122094546-76511-DETAIL-04_27_2023-GO95MLD-1^06241005.0256601 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
32021036-9511-DETAIL-04_27_2023-GO95MLD-1^06241005.0256702 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
686511814-16430-DETAIL-04_27_2023-GO95MLD-1^06241005.0256900 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
267685397-37397-DETAIL-04_27_2023-GO95MLD-1^06241005.0257300 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
23113424-74930-DETAIL-04_27_2023-GRDRODHI-1^06241005.0257440 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
539121224-31530-DETAIL-04_27_2023-GO95MLD-1^06241005.0257900 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
286116949-1320-DETAIL-01_26_2023-GO95MLD-1^06241005.0260206 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2028-01-26 | 3
483513959-37510-DETAIL-01_26_2023-GO95MLD-1^06241005.0262200 | OTHER | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
483513959-37510-DETAIL-01_26_2023-SVCDEFLC-1^06241005.0262200 | OTHER | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
961932539-13610-DETAIL-01_26_2023-GO95MLD-1^06241005.0262203 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2026-01-26 | 2
420340389-33010-DETAIL-01_26_2023-GO95BLTC-1^06241005.0262204 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2028-01-26 | 3
420340389-33010-DETAIL-01_26_2023-GO95MLD-1^06241005.0262204 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2026-01-26 | 2
420340389-33010-DETAIL-01_26_2023-SVCDEFLC-1^06241005.0262204 | OTHER | CA-TIER-3 | Distribution | 2023-01-26 | 2026-01-26 | 2
506962677-68645-DETAIL-01_26_2023-SVCDEFLC-1^06241005.0267100 | OTHER | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
835992679-63420-DETAIL-01_25_2023-GO95MLD-1^06241005.0268101 | OTHER | CA-TIER-2 | Distribution | 2023-01-25 | 2026-01-25 | 2
922603123-95120-DETAIL-05_02_2023-GO95TCH-1^06241005.0360801 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
6133884-15330-DETAIL-05_02_2023-GO95MLD-1^06241005.0360903 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
152515944-64630-DETAIL-05_02_2023-GO95MLD-1^06241005.0360904 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
359966244-82630-DETAIL-05_02_2023-GO95MLD-1^06241005.0361900 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
303831764-33630-DETAIL-05_02_2023-GO95MLD-1^06241005.0361901 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
469823933-82420-DETAIL-05_02_2023-GO95MLD-1^06241005.0362902 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
992814976-56976-DETAIL-05_04_2023-GO95TCH-1^06241005.0363300 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
501095384-3330-DETAIL-05_04_2023-GO95BLTC-1^06241005.0363400 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2028-05-04 | 3
114756876-39369-DETAIL-05_04_2023-GO95MLD-1^06241005.0363402 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
161598624-42530-DETAIL-05_02_2023-GO95MLD-1^06241005.0363501 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
893385083-98520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363502 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
537729214-93130-DETAIL-05_02_2023-GO95BLTC-1^06241005.0363600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2028-05-02 | 3
537729214-93130-DETAIL-05_02_2023-GO95MLD-1^06241005.0363600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
537729214-93130-AUDIT-07_10_2023-SVCDEFLC-1^06241005.0363600 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
793752773-4520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363601 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
637996134-38130-DETAIL-05_02_2023-GO95TCH-1^06241005.0363700 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
578374114-2230-DETAIL-05_02_2023-GO95MLD-1^06241005.0363702 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2028-05-02 | 3
776957053-52520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363703 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
776957053-52520-DETAIL-05_02_2023-SVCROAD-1^06241005.0363703 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
378086253-41520-DETAIL-05_02_2023-GO95MLD-1^06241005.0363704 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
692024624-930-DETAIL-05_01_2023-GO95MLD-1^06241005.0364301 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
812756223-35030-DETAIL-05_01_2023-GO95MLD-1^06241005.0364302 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
437277904-36430-DETAIL-05_04_2023-GO95MLD-1^06241005.0364304 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
327544204-60430-DETAIL-05_04_2023-GO95MLD-1^06241005.0364400 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
218532503-71030-DETAIL-05_01_2023-GO95MLD-1^06241005.0364401 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
88310614-19430-DETAIL-05_04_2023-GO95MLD-1^06241005.0364402 | OTHER | CA-TIER-2 | Distribution | 2023-05-04 | 2026-05-04 | 2
952184736-70040-DETAIL-05_02_2023-GO95MLD-1^06241005.0364600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2028-05-02 | 3
876579416-68640-DETAIL-05_03_2023-GO95MLD-1^06241005.0364802 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
993511306-57540-DETAIL-05_03_2023-GO95HV-1^06241005.0364803 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
501531093-9220-DETAIL-05_03_2023-GRDRODHI-1^06241005.0364900 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
292002324-32530-DETAIL-05_01_2023-GO95MLD-1^06241005.0365101 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
292002324-32530-DETAIL-05_01_2023-GO95TCH-1^06241005.0365101 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
247158994-33430-DETAIL-05_01_2023-GO95MLD-1^06241005.0365200 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
247158994-33430-DETAIL-05_01_2023-SVCDEFLC-1^06241005.0365200 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
454982033-6030-DETAIL-05_01_2023-GO95MLD-1^06241005.0365201 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
165039523-45030-DETAIL-05_01_2023-GO95MLD-1^06241005.0365205 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
682230194-92330-DETAIL-05_01_2023-GO95MLD-1^06241005.0365206 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
411946116-56640-DETAIL-05_01_2023-SVCROAD-1^06241005.0365300 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
379809694-73130-DETAIL-05_02_2023-RISEGRD-1^06241005.0365601 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
277838964-88030-DETAIL-05_02_2023-GO95MLD-1^06241005.0365602 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
257353545-32830-DETAIL-05_03_2023-GO95HV-1^06241005.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
423073314-80230-DETAIL-05_03_2023-GO95MLD-1^06241005.0365803 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
423073314-80230-DETAIL-05_03_2023-GO95TCH-1^06241005.0365803 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
636098506-22640-DETAIL-05_03_2023-GO95MLD-1^06241005.0365804 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
523673804-18130-DETAIL-05_03_2023-GO95MLD-1^06241005.0365901 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
166918643-78030-DETAIL-05_01_2023-GO95MLD-1^06241005.0366100 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
531343554-63130-DETAIL-05_01_2023-GO95MLD-1^06241005.0366102 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
531343554-63130-DETAIL-05_01_2023-GUYHINS-1^06241005.0366102 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
27765924-36930-DETAIL-05_01_2023-GO95MLD-1^06241005.0366200 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
27765924-36930-DETAIL-05_01_2023-SVCDEFLC-1^06241005.0366200 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
746396674-41130-DETAIL-05_02_2023-GO95HV-1^06241005.0366600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2028-05-02 | 3
746396674-41130-DETAIL-05_02_2023-GO95MLD-1^06241005.0366600 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
535398883-87030-DETAIL-05_02_2023-GO95MLD-1^06241005.0366603 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
487892513-58530-DETAIL-05_02_2023-GO95MLD-1^06241005.0366604 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
184540064-58030-DETAIL-05_02_2023-GO95MLD-1^06241005.0366700 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
687446524-75130-DETAIL-05_03_2023-GO95MLD-1^06241005.0367900 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
108864345-93730-DETAIL-05_03_2023-SVCENTCO-1^06241005.0367901 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
446518284-47330-DETAIL-05_03_2023-SVCDEFLC-1^06241005.0367902 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
49197711-34099-ADMIN-06_18_2024-POLEREPL-1^06241009.0031500 | POLE | CA-NON-TIER | Distribution | 2024-06-18 | 2027-06-18 | 2
361415634-5399-ADMIN-07_18_2023-POLEREPL-1^06241009.0220501 | POLE | CA-NON-TIER | Distribution | 2023-07-18 | 2026-07-18 | 2
181955823-36519-ADMIN-08_02_2023-POLEREPL-1^06241009.0224300 | POLE | CA-NON-TIER | Distribution | 2023-08-02 | 2026-08-02 | 2
133571063-70151-DTLSB-07_25_2022-ABNDEQPM-1^06242005.0159000 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2027-07-25 | 3
685475843-97843-DTLSB-08_02_2022-GO95MLD-1^06242005.0176300 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
710454894-23251-DTLSB-08_02_2022-GO95MLD-1^06242005.0177101 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
859185703-34541-ENHANCED-07_31_2024-COPLLEAN-1^06242005.0228000 | POLE | CA-TIER-2 | Distribution | 2024-07-31 | 2025-07-31 | 2
713258650-63571-ADMIN-12_04_2023-POLEREPL-1^06242005.0267300 | POLE | CA-TIER-2 | Distribution | 2023-12-04 | 2024-12-04 | 2
829847215-61714-DETAIL-05_23_2022-SVCRUBLG-1^06242005.0368641 | OTHER | CA-TIER-2 | Distribution | 2022-05-23 | 2025-05-23 | 2
528662539-63289-DETAIL-02_09_2021-GO95MLD-1^06242009.0044100 | OTHER | FHCA | Distribution | 2021-02-09 | 2024-02-09 | 2
649560825-78589-ADMIN-07_18_2024-POLEREPL-1^06242009.0059201 | POLE | CA-TIER-2 | Distribution | 2024-07-18 | 2025-07-18 | 2
369923174-51399-DETAIL-02_05_2021-SVCWIND-1^06242009.0120501 | OTHER | FHCA | Distribution | 2021-02-05 | 2024-02-05 | 2
140041974-91119-DETAIL-02_17_2021-SVCENTCO-1^06242009.0207500 | OTHER | CA-TIER-2 | Distribution | 2021-02-17 | 2024-02-17 | 2
829266640-31669-ADMIN-07_24_2023-POLEREPL-1^06242009.0246902 | POLE | CA-NON-TIER | Distribution | 2023-07-24 | 2026-07-24 | 2
654452740-73079-ADMIN-07_24_2023-POLEREPL-1^06242009.0246903 | POLE | CA-NON-TIER | Distribution | 2023-07-24 | 2026-07-24 | 2
435576823-70589-DETAIL-08_12_2021-GO95CLSV-1^06242009.0276202 | OTHER | FHCA | Distribution | 2021-08-12 | 2024-08-12 | 2
904854149-83029-DETAIL-08_03_2021-SVCROAD-1^06242009.0280108 | OTHER | FHCA | Distribution | 2021-08-03 | 2024-08-03 | 2
448063308-49129-DETAIL-08_03_2021-ENCHRW-1^06242009.0281202 | OTHER | FHCA | Distribution | 2021-08-03 | 2024-08-03 | 2
714798569-5599-ADMIN-06_19_2024-GO95MLD-1^06242009.0284104 | OTHER | FHCA | Distribution | 2024-06-19 | 2027-06-19 | 2
629229878-96512-DTLSB-08_29_2022-GO95HV-1^06243004.0035300 | OTHER | FHCA | Distribution | 2022-08-29 | 2027-08-29 | 3
861269088-33612-DTLSB-08_29_2022-GO95HV-1^06243004.0037300 | OTHER | FHCA | Distribution | 2022-08-29 | 2027-08-29 | 3
507857318-47769-DTLSB-08_29_2022-GO95MLD-1^06243004.0049000 | OTHER | FHCA | Distribution | 2022-08-29 | 2025-08-29 | 2
507857318-47769-DTLSB-08_29_2022-GO95TCH-1^06243004.0049000 | OTHER | FHCA | Distribution | 2022-08-29 | 2025-08-29 | 2
263733251-79389-DTLSB-09_07_2022-GO95MLD-1^06243004.0060400 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2025-09-07 | 2
854804219-45219-DTLSB-09_07_2022-GO95HV-1^06243004.0060502 | OTHER | CA-TIER-2 | Distribution | 2022-09-07 | 2027-09-07 | 3
344520961-8379-DTLSB-09_22_2022-GO95TCH-1^06243004.0063400 | OTHER | CA-TIER-2 | Distribution | 2022-09-22 | 2025-09-22 | 2
337812981-57942-DTLSB-09_06_2022-GO95MLD-1^06243004.0065240 | OTHER | CA-TIER-2 | Distribution | 2022-09-06 | 2025-09-06 | 2
383383902-81269-DTLSB-10_03_2022-GO95MLD-1^06243004.0074301 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2025-10-03 | 2
465553662-23552-DTLSB-08_10_2022-ABNDEQPM-1^06243004.0075301 | OTHER | CA-TIER-2 | Distribution | 2022-08-10 | 2027-08-10 | 3
633744813-30499-DTLSB-09_28_2022-GO95HV-1^06243004.0085000 | OTHER | FHCA | Distribution | 2022-09-28 | 2027-09-28 | 3
812681805-62569-DTLSB-09_01_2022-GO95MLD-1^06243004.0087140 | OTHER | FHCA | Distribution | 2022-09-01 | 2025-09-01 | 2
571500238-11989-DTLSB-09_27_2022-GO95MLD-1^06243004.0094901 | OTHER | FHCA | Distribution | 2022-09-27 | 2025-09-27 | 2
533523728-53889-DTLSB-09_01_2022-GO95MLD-1^06243004.0095900 | OTHER | FHCA | Distribution | 2022-09-01 | 2025-09-01 | 2
115404717-93329-DTLSB-08_30_2022-GO95MLD-1^06243004.0097900 | OTHER | FHCA | Distribution | 2022-08-30 | 2025-08-30 | 2
418191487-35599-DTLSB-08_29_2022-GO95MLD-1^06243004.0100200 | OTHER | FHCA | Distribution | 2022-08-29 | 2025-08-29 | 2
418191487-35599-DTLSB-08_29_2022-GO95TCH-1^06243004.0100200 | OTHER | FHCA | Distribution | 2022-08-29 | 2025-08-29 | 2
795620607-50429-DTLSB-08_29_2022-GO95MLD-1^06243004.0101402 | OTHER | FHCA | Distribution | 2022-08-29 | 2025-08-29 | 2
369733027-71429-DTLSB-08_24_2022-GO95HV-1^06243004.0103200 | OTHER | FHCA | Distribution | 2022-08-24 | 2027-08-24 | 3
595728487-51329-DTLSB-08_24_2022-GO95MLD-1^06243004.0105200 | OTHER | FHCA | Distribution | 2022-08-24 | 2025-08-24 | 2
578917767-82429-DTLSB-08_24_2022-GUYNOINS-1^06243004.0106002 | ANCHOR/GUY | FHCA | Distribution | 2022-08-24 | 2025-08-24 | 2
578917767-82429-DTLSB-08_24_2022-GUYNOINS-2^06243004.0106002 | ANCHOR/GUY | FHCA | Distribution | 2022-08-24 | 2025-08-24 | 2
237485459-51269-DTLSB-09_01_2022-GO95MLD-1^06243004.0172000 | OTHER | FHCA | Distribution | 2022-09-01 | 2025-09-01 | 2
61498398-69398-DTLSB-08_10_2022-GO95MLD-1^06243004.0177040 | OTHER | FHCA | Distribution | 2022-08-10 | 2025-08-10 | 2
454782229-19479-DTLSB-08_01_2022-GO95MLD-1^06243004.0177401 | OTHER | FHCA | Distribution | 2022-08-01 | 2025-08-01 | 2
325638479-11389-DTLSB-08_08_2022-ABNDEQPM-1^06243004.0177902 | OTHER | FHCA | Distribution | 2022-08-08 | 2027-08-08 | 3
375451355-62669-DTLSB-08_11_2022-GO95MLD-1^06243004.0179400 | OTHER | FHCA | Distribution | 2022-08-11 | 2025-08-11 | 2
854913338-44669-ENHANCED-07_31_2024-IRSPOTOH-1^06243004.0192200 | OTHER | CA-TIER-2 | Distribution | 2024-07-31 | 2025-07-31 | 2
596996889-64089-DTLSB-08_04_2022-GO95MLD-1^06243004.0212201 | OTHER | FHCA | Distribution | 2022-08-04 | 2025-08-04 | 2
596996889-64089-DTLSB-08_04_2022-GRDRODHI-1^06243004.0212201 | OTHER | FHCA | Distribution | 2022-08-04 | 2025-08-04 | 2
596996889-64089-DTLSB-08_04_2022-GRDRODHI-2^06243004.0212201 | OTHER | FHCA | Distribution | 2022-08-04 | 2025-08-04 | 2
838711869-36339-DTLSB-08_23_2022-GO95MLD-1^06243004.0234200 | OTHER | FHCA | Distribution | 2022-08-23 | 2025-08-23 | 2
397580970-75339-DTLSB-09_01_2022-GO95MLD-1^06243004.0234500 | OTHER | FHCA | Distribution | 2022-09-01 | 2025-09-01 | 2
176387070-48989-DTLSB-09_01_2022-GO95MLD-1^06243004.0234501 | OTHER | FHCA | Distribution | 2022-09-01 | 2025-09-01 | 2
892688239-54339-DTLSB-08_23_2022-ABNDEQPM-1^06243004.0236200 | OTHER | FHCA | Distribution | 2022-08-23 | 2027-08-23 | 3
819212540-50439-DTLSB-08_22_2022-ABNDEQPM-1^06243004.0240900 | OTHER | FHCA | Distribution | 2022-08-22 | 2027-08-22 | 3
579673401-1489-DTLSB-08_25_2022-GO95MLD-1^06243004.0280500 | OTHER | FHCA | Distribution | 2022-08-25 | 2025-08-25 | 2
191762349-98539-DTLSB-08_04_2022-GO95HV-1^06243004.0286904 | OTHER | FHCA | Distribution | 2022-08-04 | 2027-08-04 | 3
374407090-7489-DTLSB-08_10_2022-GO95MLD-1^06243004.0287900 | OTHER | FHCA | Distribution | 2022-08-10 | 2025-08-10 | 2
193032444-6199-DTLSB-09_19_2022-GO95HV-1^06243005.0014200 | OTHER | CA-TIER-2 | Distribution | 2022-09-19 | 2027-09-19 | 3
193032444-6199-DTLSB-09_19_2022-GO95MLD-1^06243005.0014200 | OTHER | CA-TIER-2 | Distribution | 2022-09-19 | 2025-09-19 | 2
472511933-13639-DTLSB-09_20_2022-GO95MLD-1^06243005.0016902 | OTHER | FHCA | Distribution | 2022-09-20 | 2025-09-20 | 2
409643375-34375-DTLSB-10_03_2022-GO95HV-1^06243005.0023300 | OTHER | FHCA | Distribution | 2022-10-03 | 2027-10-03 | 3
670336375-17375-DTLSB-10_03_2022-GO95HV-1^06243005.0023301 | OTHER | FHCA | Distribution | 2022-10-03 | 2027-10-03 | 3
806044284-76679-DTLSB-09_08_2022-ABNDEQPM-1^06243005.0038300 | OTHER | FHCA | Distribution | 2022-09-08 | 2027-09-08 | 3
806044284-76679-DTLSB-09_08_2022-GO95MLD-1^06243005.0038300 | OTHER | FHCA | Distribution | 2022-09-08 | 2025-09-08 | 2
351915375-3399-DTLSB-09_08_2022-GO95MLD-1^06243005.0039100 | OTHER | FHCA | Distribution | 2022-09-08 | 2025-09-08 | 2
228878871-39969-DTLSB-09_29_2022-ABNDEQPM-1^06243005.0077401 | OTHER | FHCA | Distribution | 2022-09-29 | 2027-09-29 | 3
64985488-14139-DTLSB-09_29_2022-GUYNOINS-1^06243005.0089203 | ANCHOR/GUY | FHCA | Distribution | 2022-09-29 | 2025-09-29 | 2
108957958-5139-DTLSB-09_29_2022-GO95HV-1^06243005.0089300 | OTHER | FHCA | Distribution | 2022-09-29 | 2027-09-29 | 3
531041253-98639-DTLSB-09_19_2022-GO95HV-1^06243005.0113900 | OTHER | FHCA | Distribution | 2022-09-19 | 2027-09-19 | 3
531041253-98639-DTLSB-09_19_2022-GO95MLD-1^06243005.0113900 | OTHER | FHCA | Distribution | 2022-09-19 | 2025-09-19 | 2
451972713-50469-DTLSB-09_21_2022-GO95MLD-1^06243005.0118900 | OTHER | FHCA | Distribution | 2022-09-21 | 2025-09-21 | 2
752579970-41070-DTLSB-10_03_2022-GO95MLD-1^06243005.0121820 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2025-10-03 | 2
304964676-16676-DTLSB-10_03_2022-GO95HV-1^06243005.0121900 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2027-10-03 | 3
304964676-16676-DTLSB-10_03_2022-GO95MLD-1^06243005.0121900 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2025-10-03 | 2
304964676-16676-DTLSB-10_03_2022-GO95TCH-1^06243005.0121900 | OTHER | CA-TIER-2 | Distribution | 2022-10-03 | 2025-10-03 | 2
462021129-18989-DTLSB-06_29_2022-GO95HV-1^06243005.0130000 | OTHER | FHCA | Distribution | 2022-06-29 | 2027-06-29 | 3
462021129-18989-DTLSB-06_29_2022-GO95MLD-1^06243005.0130000 | OTHER | FHCA | Distribution | 2022-06-29 | 2025-06-29 | 2
586320079-82389-DTLSB-06_29_2022-GO95HV-1^06243005.0130500 | OTHER | CA-TIER-2 | Distribution | 2022-06-29 | 2027-06-29 | 3
217870199-41779-DTLSB-06_29_2022-GO95MLD-1^06243005.0131001 | OTHER | FHCA | Distribution | 2022-06-29 | 2025-06-29 | 2
641149919-65439-DTLSB-06_29_2022-GO95MLD-1^06243005.0131200 | OTHER | FHCA | Distribution | 2022-06-29 | 2025-06-29 | 2
930285146-16146-DTLTRT-06_29_2022-GO95HV-1^06243005.0132001 | OTHER | FHCA | Distribution | 2022-06-29 | 2027-06-29 | 3
345255449-33799-DTLSB-06_29_2022-GO95MLD-1^06243005.0133300 | OTHER | CA-TIER-2 | Distribution | 2022-06-29 | 2025-06-29 | 2
464658558-51539-DTLSB-06_30_2022-GO95MLD-1^06243005.0140901 | OTHER | FHCA | Distribution | 2022-06-30 | 2025-06-30 | 2
205782409-60539-DTLSB-06_30_2022-GO95MLD-1^06243005.0142700 | OTHER | FHCA | Distribution | 2022-06-30 | 2025-06-30 | 2
375114119-2439-DTLSB-06_29_2022-GO95HV-1^06243005.0240901 | OTHER | FHCA | Distribution | 2022-06-29 | 2027-06-29 | 3
744690451-22539-DTLSB-07_19_2022-GO95MLD-1^06243005.0249000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
744690451-22539-DTLSB-07_19_2022-GRDRODHI-1^06243005.0249000 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2025-07-19 | 2
575147072-81639-DTLSB-07_18_2022-GO95MLD-1^06243005.0257300 | OTHER | CA-TIER-2 | Distribution | 2022-07-18 | 2025-07-18 | 2
531032413-70339-ADMIN-06_17_2024-XARMSPCR-1^06243007.0011400 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
712417963-4362-ADMIN-06_17_2024-XARMSPCR-2^06243007.0019740 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
712417963-4362-ADMIN-08_08_2024-POLEREPL-1^06243007.0019740 | POLE | CA-TIER-2 | Distribution | 2024-08-08 | 2025-08-08 | 2
462726413-69429-DTLSB-09_06_2023-GO95HV-1^06243007.0171100 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
292945813-80979-DTLSB-09_06_2023-ABNDEQPM-1^06243007.0171101 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
292945813-80979-AUDIT-10_09_2023-GO95BLTC-1^06243007.0171101 | OTHER | CA-TIER-2 | Distribution | 2023-10-09 | 2028-10-09 | 3
609890837-42837-DTLSB-08_25_2023-GO95MLD-1^06243007.0180900 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2026-08-25 | 2
812246763-96429-DTLSB-09_06_2023-GO95HV-1^06243007.0185601 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
298938073-67429-DTLSB-09_06_2023-GO95HV-1^06243007.0186600 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
673531983-97429-DTLSB-09_06_2023-GO95HV-1^06243007.0187500 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
247755083-73109-DTLSB-09_06_2023-GO95MLD-1^06243007.0188501 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
637849342-19479-DTLSB-09_06_2023-GRDRODHI-1^06243007.0202302 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
637849342-19479-DTLSB-09_06_2023-GRDRODHI-2^06243007.0202302 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
776582433-81529-DTLSB-09_06_2023-GO95HV-1^06243007.0202501 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
553457833-62109-DTLSB-09_06_2023-ABNDEQPM-1^06243007.0202700 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2028-09-06 | 3
196002303-84589-DTLSB-09_06_2023-GO95MLD-1^06243007.0203000 | OTHER | CA-TIER-2 | Distribution | 2023-09-06 | 2026-09-06 | 2
98016213-36529-DTLSB-08_31_2023-GO95HV-1^06243007.0293301 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
505191313-6529-DTLSB-08_31_2023-GO95HV-1^06243007.0293401 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
380888403-35529-DTLSB-08_31_2023-GO95HV-1^06243007.0293601 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
625795093-50789-DTLSB-08_31_2023-GO95MLD-1^06243007.0293700 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2026-08-31 | 2
242896923-11189-DTLSB-08_31_2023-ABNDEQPM-1^06243007.0294200 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
19738813-10629-DTLSB-08_31_2023-GO95HV-1^06243007.0320101 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
96949313-92499-DTLSB-08_31_2023-GO95MLD-1^06243007.0320200 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2026-08-31 | 2
901594903-59529-DTLSB-08_31_2023-GO95HV-1^06243007.0320400 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
287263093-68079-DTLSB-08_31_2023-GO95MLD-1^06243007.0320401 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2026-08-31 | 2
208212583-19529-DTLSB-08_31_2023-GO95HV-1^06243007.0320601 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
799533733-50729-DTLSB-09_07_2023-GO95HV-1^06243008.0023001 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
691558036-69036-DTLSB-08_31_2023-GO95HV-1^06243008.0025700 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
149401664-35389-DTLSB-08_31_2023-GO95MLD-1^06243008.0025801 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
849763493-75629-DTLSB-08_31_2023-GO95MLD-1^06243008.0025802 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
509517293-91729-DTLSB-08_31_2023-GO95HV-1^06243008.0025900 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
958132114-8629-DTLSB-09_07_2023-GO95MLD-1^06243008.0026000 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2026-09-07 | 2
24923753-87629-DTLSB-09_07_2023-GO95HV-1^06243008.0026100 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
112481173-37629-DTLSB-09_07_2023-GO95HV-1^06243008.0026200 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
237720273-96629-DTLSB-09_07_2023-GO95HV-1^06243008.0026301 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
306231916-3916-DTLSB-08_31_2023-GO95HV-1^06243008.0026600 | OTHER | CA-TIER-2 | Distribution | 2023-08-31 | 2028-08-31 | 3
947231752-68009-DETAIL-07_12_2023-GO95MLD-1^06243008.0054700 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
362044152-99431-DETAIL-07_12_2023-GO95MLD-1^06243008.0054800 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
38224431-14489-DTLSB-09_05_2023-GO95MLD-1^06243008.0089101 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
701655981-91631-DTLSB-09_05_2023-GUYNOINS-1^06243008.0092500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
166870591-36729-DTLSB-09_05_2023-ENCHRW-1^06243008.0092502 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
293738011-62829-DTLSB-09_05_2023-ABNDEQPM-1^06243008.0093300 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
293738011-62829-DTLSB-09_05_2023-GO95MLD-1^06243008.0093300 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
34231511-32989-DTLSB-09_05_2023-GO95MLD-1^06243008.0094200 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
297788991-50369-DTLSB-09_05_2023-GO95HV-1^06243008.0095601 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
689106101-5669-DTLSB-09_05_2023-GO95MLD-1^06243008.0096600 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
689106101-5669-DTLSB-09_05_2023-SVCDEFLC-1^06243008.0096600 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
50560451-17729-DTLSB-09_28_2023-GO95HV-1^06243008.0097600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
50560451-17729-DTLSB-09_28_2023-GO95MLD-1^06243008.0097600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2026-09-28 | 2
122419691-78729-DTLSB-09_28_2023-GO95MLD-1^06243008.0101600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2026-09-28 | 2
57709191-78999-DTLSB-09_28_2023-GO95MLD-1^06243008.0102501 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2026-09-28 | 2
400388271-79729-DTLSB-09_28_2023-GO95HV-1^06243008.0103600 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
499192181-80829-DTLSB-09_28_2023-GO95HV-1^06243008.0107700 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
600655631-41829-DTLSB-09_07_2023-GO95HV-1^06243008.0109800 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
897105781-11829-DTLSB-09_28_2023-GO95HV-1^06243008.0110801 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
391094623-99629-DTLSB-09_28_2023-GO95HV-1^06243008.0112900 | OTHER | CA-TIER-2 | Distribution | 2023-09-28 | 2028-09-28 | 3
455056534-98629-DTLSB-09_07_2023-GO95HV-1^06243008.0118800 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
231170844-94629-DTLSB-09_07_2023-GO95HV-1^06243008.0120600 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
314760344-31629-DTLSB-09_07_2023-ABNDEQPM-1^06243008.0121601 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
10876383-92629-DTLSB-09_07_2023-GO95MLD-1^06243008.0124202 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2026-09-07 | 2
331728904-54629-DTLSB-09_07_2023-GO95HV-1^06243008.0128000 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
658525023-1029-DTLSB-08_25_2023-GO95HV-1^06243008.0133401 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
969667163-60029-DTLSB-08_25_2023-GO95HV-1^06243008.0133403 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
640222533-54029-DTLSB-08_25_2023-GO95HV-1^06243008.0137700 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
527347643-94429-DTLSB-09_07_2023-GO95HV-1^06243008.0139900 | OTHER | CA-TIER-2 | Distribution | 2023-09-07 | 2028-09-07 | 3
144945522-94131-DTLSB-09_05_2023-GO95HV-1^06243008.0161900 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
608509722-67601-DTLSB-09_05_2023-GO95HV-1^06243008.0161901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
608509722-67601-DTLSB-09_05_2023-GO95MLD-1^06243008.0161901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
695674832-67761-DTLSB-09_05_2023-GO95HV-1^06243008.0162801 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
291730032-83021-DTLSB-09_05_2023-GO95HV-1^06243008.0162901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
409603842-90713-DTLSB-09_05_2023-GO95MLD-1^06243008.0163901 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
940980012-94789-DTLSB-08_24_2023-GO95MLD-1^06243008.0171700 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
940980012-94789-DTLSB-08_24_2023-GRDRODHI-1^06243008.0171700 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
428116512-89829-DTLSB-08_24_2023-GUYNOINS-1^06243008.0172701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
428116512-89829-DTLSB-08_24_2023-GUYNOINS-2^06243008.0172701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-24 | 2026-08-24 | 2
67531412-98241-DTLSB-08_30_2023-SVCDEFLC-1^06243008.0173100 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
929033032-29589-DTLSB-08_24_2023-GO95MLD-1^06243008.0174901 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2028-08-24 | 3
850662392-8599-DTLSB-08_25_2023-GO95BLTC-1^06243008.0175500 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
763169762-64929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176100 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
613690852-34929-DTLSB-08_30_2023-GO95HV-1^06243008.0176201 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2028-08-30 | 3
613690852-34929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176201 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
208267552-73929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176300 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
934448852-51929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176400 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
250361152-41929-AUDIT-10_09_2023-GO95HV-1^06243008.0176500 | OTHER | CA-TIER-2 | Distribution | 2023-10-09 | 2028-10-09 | 3
80086013-20209-DTLSB-09_05_2023-GO95MLD-1^06243008.0178500 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
463019842-209-DTLSB-08_30_2023-GO95MLD-1^06243008.0179701 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2028-08-30 | 3
447034132-21389-ADMIN-07_10_2024-POLEREPL-1^06243008.0180200 | POLE | CA-TIER-2 | Distribution | 2024-07-10 | 2025-07-10 | 2
188959232-65829-ADMIN-07_10_2024-POLEREPL-1^06243008.0180201 | POLE | CA-TIER-2 | Distribution | 2024-07-10 | 2025-07-10 | 2
894864382-47829-ADMIN-07_15_2024-POLEREPL-1^06243008.0185400 | POLE | CA-TIER-2 | Distribution | 2024-07-15 | 2025-07-15 | 2
487940592-68829-DTLSB-08_24_2023-GO95HV-1^06243008.0186501 | OTHER | CA-TIER-2 | Distribution | 2023-08-24 | 2028-08-24 | 3
859332073-34073-DTLSB-08_30_2023-GO95HV-1^06243008.0205700 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2028-08-30 | 3
284887372-78679-DTLSB-08_30_2023-SVCWIND-1^06243008.0205800 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
484414072-45929-DTLSB-08_30_2023-GO95MLD-1^06243008.0206900 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
917198162-44989-DTLSB-08_30_2023-GO95MLD-1^06243008.0207900 | OTHER | CA-TIER-2 | Distribution | 2023-08-30 | 2026-08-30 | 2
675098153-50029-DTLSB-09_05_2023-GO95HV-1^06243008.0235000 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
292465543-1079-DTLSB-09_05_2023-GO95MLD-1^06243008.0235100 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
782952593-50799-DTLSB-08_25_2023-GO95MLD-1^06243008.0240800 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2026-08-25 | 2
901054953-74341-DTLSB-09_05_2023-GO95MLD-1^06243008.0240900 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
961041983-23029-DTLSB-08_25_2023-GO95MLD-1^06243008.0241800 | OTHER | CA-TIER-2 | Distribution | 2023-08-25 | 2028-08-25 | 3
973457393-86699-DTLSB-09_08_2023-GO95MLD-1^06243008.0262800 | OTHER | CA-TIER-2 | Distribution | 2023-09-08 | 2028-09-08 | 3
730281003-16889-DTLSB-09_05_2023-GO95MLD-1^06243008.0263800 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2028-09-05 | 3
773570893-16799-DTLSB-09_08_2023-GO95MLD-1^06243008.0263801 | OTHER | CA-TIER-2 | Distribution | 2023-09-08 | 2028-09-08 | 3
496426809-30621-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0010500 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
496426809-30621-DETAIL-06_01_2023-SVCDEFLC-2^06243009.0010500 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
604071069-42821-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0010504 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
23210659-44189-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0010601 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
689133729-72521-DETAIL-06_01_2023-GO95HV-1^06243009.0010602 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
689133729-72521-DETAIL-06_01_2023-GO95MLD-1^06243009.0010602 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2028-06-01 | 3
794171419-53021-DETAIL-01_04_2024-POLEREPL-1^06243009.0010603 | POLE | CA-TIER-2 | Distribution | 2024-01-04 | 2025-01-04 | 2
902253138-5211-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0010702 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
902253138-5211-DETAIL-05_30_2023-SVCDEFLC-2^06243009.0010702 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
455756128-67711-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0010703 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
709961459-21821-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0010802 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
709961459-21821-DETAIL-05_30_2023-SVCDEFLC-2^06243009.0010802 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
30113649-98721-DETAIL-06_01_2023-GO95MLD-1^06243009.0011502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
30113649-98721-DETAIL-06_01_2023-SVCDEFLC-1^06243009.0011502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
169204228-57929-DETAIL-05_30_2023-GO95HV-1^06243009.0011801 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
733182339-29221-DETAIL-06_01_2023-GO95MLD-1^06243009.0012502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
542548528-2108-AUDIT-08_29_2023-ABNDEQPM-1^06243009.0020002 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2026-08-29 | 2
565389029-80189-DETAIL-06_14_2023-GO95MLD-1^06243009.0022000 | OTHER | FHCA | Distribution | 2023-06-14 | 2026-06-14 | 2
219642799-50129-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0024401 | OTHER | FHCA | Distribution | 2023-06-05 | 2026-06-05 | 2
312253409-79029-DETAIL-06_05_2023-GO95STUB-1^06243009.0024404 | OTHER | FHCA | Distribution | 2023-06-05 | 2026-06-05 | 2
89093901-57229-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0025103 | OTHER | FHCA | Distribution | 2023-06-02 | 2026-06-02 | 2
793862539-4241-DETAIL-06_02_2023-GO95MLD-1^06243009.0025106 | OTHER | CA-TIER-2 | Distribution | 2023-06-02 | 2028-06-02 | 3
399920369-45299-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0025406 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
755709239-229-DETAIL-06_05_2023-GO95HV-1^06243009.0025412 | OTHER | FHCA | Distribution | 2023-06-05 | 2028-06-05 | 3
761413981-5229-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026203 | OTHER | FHCA | Distribution | 2023-06-02 | 2026-06-02 | 2
721516589-64229-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026303 | OTHER | FHCA | Distribution | 2023-06-02 | 2026-06-02 | 2
391688749-48521-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0026400 | OTHER | FHCA | Distribution | 2023-06-05 | 2026-06-05 | 2
177554359-18879-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0026402 | OTHER | FHCA | Distribution | 2023-06-05 | 2026-06-05 | 2
128219699-61229-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026403 | OTHER | FHCA | Distribution | 2023-06-02 | 2026-06-02 | 2
541598909-19129-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026404 | OTHER | FHCA | Distribution | 2023-06-02 | 2026-06-02 | 2
187815611-76611-DETAIL-06_02_2023-SVCDEFLC-1^06243009.0026420 | OTHER | FHCA | Distribution | 2023-06-02 | 2026-06-02 | 2
753082402-23541-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0026501 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
687954540-18871-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0026502 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
22008250-55489-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0026504 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
468195199-8099-ENHANCED-07_09_2024-IRSPOTOH-1^06243009.0027311 | OTHER | CA-TIER-2 | Distribution | 2024-07-09 | 2025-07-09 | 2
605265471-32229-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0027404 | OTHER | FHCA | Distribution | 2023-06-05 | 2026-06-05 | 2
235075256-22579-DETAIL-06_05_2023-SVCWIND-1^06243009.0027405 | OTHER | FHCA | Distribution | 2023-06-05 | 2026-06-05 | 2
665318666-17589-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0027411 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
665318666-17589-DETAIL-06_05_2023-SVCDEFLC-2^06243009.0027411 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
871355048-95129-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0027412 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
511782271-32301-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0027500 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
108878380-44461-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0027501 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
876566711-37231-DETAIL-05_31_2023-GO95MLD-1^06243009.0027606 | OTHER | FHCA | Distribution | 2023-05-31 | 2028-05-31 | 3
876566711-37231-DETAIL-05_31_2023-GUYHINS-1^06243009.0027606 | ANCHOR/GUY | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
876566711-37231-DETAIL-05_31_2023-SVCROAD-1^06243009.0027606 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
208848291-98929-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0027607 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
411749400-16161-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0027610 | OTHER | FHCA | Distribution | 2023-05-31 | 2026-05-31 | 2
932526561-82531-DETAIL-05_30_2023-GRDRODHI-1^06243009.0027900 | OTHER | FHCA | Distribution | 2023-05-30 | 2026-05-30 | 2
673747869-75129-ADMIN-04_05_2024-POLEREPL-1^06243009.0028302 | POLE | CA-TIER-2 | Distribution | 2024-04-05 | 2025-04-05 | 2
990468598-7129-DETAIL-06_01_2023-GRDRODHI-1^06243009.0028411 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
990468598-7129-DETAIL-06_01_2023-GRDRODHI-2^06243009.0028411 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
990468598-7129-DETAIL-06_01_2023-GUYHINS-1^06243009.0028411 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
413642519-98399-DETAIL-06_05_2023-SVCDEFLC-1^06243009.0028418 | OTHER | CA-TIER-2 | Distribution | 2023-06-05 | 2026-06-05 | 2
647962280-78929-DETAIL-05_31_2023-SVCDEFLC-1^06243009.0028506 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
759873120-97929-DETAIL-05_30_2023-GO95HV-1^06243009.0028602 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
481834381-26731-DETAIL-05_31_2023-GO95HV-1^06243009.0028605 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2028-05-31 | 3
481834381-26731-DETAIL-05_31_2023-GO95MLD-1^06243009.0028605 | OTHER | CA-TIER-2 | Distribution | 2023-05-31 | 2026-05-31 | 2
644600661-36611-DETAIL-06_01_2023-SVCWIND-1^06243009.0029502 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
315176475-88475-DETAIL-06_01_2023-GO95MLD-1^06243009.0029505 | OTHER | CA-TIER-2 | Distribution | 2023-06-01 | 2026-06-01 | 2
368127760-8929-ADMIN-08_26_2024-POLEREPL-1^06243009.0029601 | POLE | CA-TIER-2 | Distribution | 2024-08-26 | 2025-08-26 | 2
989774611-16201-DETAIL-05_30_2023-GO95MLD-1^06243009.0029702 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
989774611-16201-DETAIL-05_30_2023-SVCRUBLG-1^06243009.0029702 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
272177150-97761-DETAIL-05_30_2023-SVCDEFLC-1^06243009.0029706 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
272177150-97761-DETAIL-05_30_2023-SVCDEFLC-2^06243009.0029706 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
953119961-62811-DETAIL-05_30_2023-ENCHRW-1^06243009.0029904 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
890239043-81489-DETAIL-06_27_2023-GO95HV-1^06243009.0032800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
890239043-81489-DETAIL-06_27_2023-GO95MLD-1^06243009.0032800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
890239043-81489-DETAIL-06_27_2023-GRDRODHI-1^06243009.0032800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
890239043-81489-DETAIL-06_27_2023-GRDRODHI-2^06243009.0032800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
216910583-77561-DETAIL-06_13_2023-GO95MLD-1^06243009.0037601 | OTHER | FHCA | Distribution | 2023-06-13 | 2026-06-13 | 2
405609403-32099-DETAIL-06_13_2023-GO95MLD-1^06243009.0038500 | OTHER | FHCA | Distribution | 2023-06-13 | 2026-06-13 | 2
405609403-32099-DETAIL-06_13_2023-GRDRODHI-1^06243009.0038500 | OTHER | FHCA | Distribution | 2023-06-13 | 2026-06-13 | 2
405609403-32099-DETAIL-06_13_2023-GRDRODHI-2^06243009.0038500 | OTHER | FHCA | Distribution | 2023-06-13 | 2026-06-13 | 2
542930083-2429-DETAIL-06_15_2023-GO95MLD-1^06243009.0039000 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2026-06-15 | 2
110240203-77329-DETAIL-06_13_2023-GO95MLD-1^06243009.0039500 | OTHER | FHCA | Distribution | 2023-06-13 | 2028-06-13 | 3
115838693-97329-DETAIL-06_13_2023-GO95MLD-1^06243009.0039501 | OTHER | FHCA | Distribution | 2023-06-13 | 2026-06-13 | 2
323502703-96329-DETAIL-06_27_2023-GO95MLD-1^06243009.0041800 | OTHER | FHCA | Distribution | 2023-06-27 | 2026-06-27 | 2
323502703-96329-DETAIL-06_27_2023-GRDRODHI-1^06243009.0041800 | OTHER | FHCA | Distribution | 2023-06-27 | 2026-06-27 | 2
157884363-41429-DETAIL-06_27_2023-SVCDEFLC-1^06243009.0047900 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
157884363-41429-DETAIL-06_27_2023-SVCDEFLC-2^06243009.0047900 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
157884363-41429-DETAIL-06_27_2023-SVCWIND-1^06243009.0047900 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
412582163-42479-DETAIL-06_27_2023-GO95MLD-1^06243009.0047901 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
968845314-56699-DTLSB-07_25_2023-GO95MLD-1^06243009.0052501 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
139977174-49429-DTLSB-07_25_2023-SVCDEFLC-1^06243009.0053002 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
139977174-49429-DTLSB-07_25_2023-SVCDEFLC-2^06243009.0053002 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
942161473-29429-DTLSB-07_25_2023-GO95MLD-1^06243009.0053004 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
519010384-68989-ADMIN-08_02_2024-POLEREPL-1^06243009.0053501 | POLE | CA-TIER-2 | Distribution | 2024-08-02 | 2025-08-02 | 2
709132974-58479-DTLSB-07_25_2023-GO95MLD-1^06243009.0053502 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
633571963-48429-DTLSB-07_25_2023-GO95MLD-1^06243009.0054300 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
338714504-58081-DTLSB-07_25_2023-ENCHRW-1^06243009.0054400 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
108038263-87429-DTLSB-07_25_2023-GO95MLD-1^06243009.0054401 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
319984853-93189-DTLSB-07_25_2023-ENCHRW-1^06243009.0054403 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
319984853-93189-DTLSB-07_25_2023-GO95MLD-1^06243009.0054403 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
319984853-93189-ADMIN-06_27_2024-GO95BLTC-1^06243009.0054403 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
304675743-68799-DTLSB-07_26_2023-GO95HV-1^06243009.0054600 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
304675743-68799-DTLSB-07_26_2023-SVCDEFLC-1^06243009.0054600 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
305458264-75429-DTLSB-07_26_2023-GO95HV-1^06243009.0054701 | OTHER | FHCA | Distribution | 2023-07-26 | 2028-07-26 | 3
388019633-61189-DTLSB-07_26_2023-GO95MLD-1^06243009.0055000 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
388019633-61189-DTLSB-07_26_2023-GRDRODHI-1^06243009.0055000 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
388019633-61189-DTLSB-07_26_2023-GRDRODHI-2^06243009.0055000 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
533835374-39479-DTLSB-07_25_2023-GO95MLD-1^06243009.0055500 | OTHER | FHCA | Distribution | 2023-07-25 | 2026-07-25 | 2
723424174-60879-DTLSB-07_26_2023-GO95MLD-1^06243009.0055702 | OTHER | FHCA | Distribution | 2023-07-26 | 2026-07-26 | 2
428786964-27789-DTLSB-07_26_2023-GO95HV-1^06243009.0055703 | OTHER | FHCA | Distribution | 2023-07-26 | 2028-07-26 | 3
428786964-27789-DTLSB-07_26_2023-GO95MLD-1^06243009.0055703 | OTHER | FHCA | Distribution | 2023-07-26 | 2026-07-26 | 2
452680324-95429-DTLSB-07_26_2023-GO95HV-1^06243009.0055902 | OTHER | FHCA | Distribution | 2023-07-26 | 2028-07-26 | 3
379832404-66779-DTLSB-07_26_2023-GO95MLD-1^06243009.0056000 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
329563494-92589-DTLSB-07_25_2023-GO95MLD-1^06243009.0056400 | OTHER | FHCA | Distribution | 2023-07-25 | 2026-07-25 | 2
120356244-39581-DTLSB-07_25_2023-GO95MLD-1^06243009.0056403 | OTHER | FHCA | Distribution | 2023-07-25 | 2026-07-25 | 2
154700374-5981-DTLSB-07_25_2023-GO95MLD-1^06243009.0056600 | OTHER | FHCA | Distribution | 2023-07-25 | 2026-07-25 | 2
154700374-5981-DTLSB-07_25_2023-GRDRODHI-1^06243009.0056600 | OTHER | FHCA | Distribution | 2023-07-25 | 2026-07-25 | 2
154700374-5981-DTLSB-07_25_2023-GRDRODHI-2^06243009.0056600 | OTHER | FHCA | Distribution | 2023-07-25 | 2026-07-25 | 2
154700374-5981-DTLSB-07_25_2023-SVCENTCO-1^06243009.0056600 | OTHER | FHCA | Distribution | 2023-07-25 | 2026-07-25 | 2
786415514-76429-DTLSB-07_26_2023-GO95HV-1^06243009.0058900 | OTHER | FHCA | Distribution | 2023-07-26 | 2028-07-26 | 3
415917893-21289-DTLSB-07_26_2023-GO95MLD-1^06243009.0059900 | OTHER | FHCA | Distribution | 2023-07-26 | 2026-07-26 | 2
824930404-56889-DTLSB-07_26_2023-GO95HV-1^06243009.0059901 | OTHER | FHCA | Distribution | 2023-07-26 | 2028-07-26 | 3
824930404-56889-DTLSB-07_26_2023-GO95MLD-1^06243009.0059901 | OTHER | FHCA | Distribution | 2023-07-26 | 2026-07-26 | 2
386201483-74499-ADMIN-08_02_2024-POLEREPL-1^06243009.0078000 | POLE | CA-TIER-2 | Distribution | 2024-08-02 | 2025-08-02 | 2
733162913-98529-DTLSB-08_01_2023-GO95STUB-1^06243009.0078001 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
471345453-18529-DTLSB-07_31_2023-GO95MLD-1^06243009.0080000 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
825829993-63529-DTLSB-07_31_2023-GO95MLD-1^06243009.0080100 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
665503903-33529-DTLSB-07_31_2023-GO95MLD-1^06243009.0081201 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
930257763-42529-DTLSB-07_31_2023-GO95HV-1^06243009.0081301 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
688784703-82529-DTLSB-07_31_2023-GO95MLD-1^06243009.0081302 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
722211503-7789-DTLSB-07_31_2023-GO95HV-1^06243009.0082500 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
722211503-7789-AUDIT-09_21_2023-GO95MLD-1^06243009.0082500 | OTHER | CA-TIER-2 | Distribution | 2023-09-21 | 2026-09-21 | 2
539899084-79181-DTLSB-07_26_2023-GO95MLD-1^06243009.0082600 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
539899084-79181-AUDIT-10_09_2023-RISEBKSP-1^06243009.0082600 | OTHER | CA-TIER-2 | Distribution | 2023-10-09 | 2026-10-09 | 2
561958383-51529-DTLSB-07_26_2023-GO95MLD-1^06243009.0082603 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
245585973-5161-DTLSB-07_26_2023-GO95HV-1^06243009.0082900 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
633773403-66529-DTLSB-07_31_2023-GO95HV-1^06243009.0084100 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
268484203-76529-DTLSB-07_31_2023-GO95STUB-1^06243009.0085100 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
491923554-88471-DTLSB-07_31_2023-GO95MLD-1^06243009.0085200 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
486633364-60589-DTLSB-07_31_2023-GO95MLD-1^06243009.0085301 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
649259564-96529-DTLSB-07_31_2023-GO95MLD-1^06243009.0086200 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
96510544-85879-ADMIN-04_24_2024-POLEREPL-1^06243009.0087400 | POLE | CA-TIER-2 | Distribution | 2024-04-24 | 2025-04-24 | 2
63481083-74529-DTLSB-07_31_2023-GO95MLD-1^06243009.0087500 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
220291173-91799-DTLSB-07_31_2023-GO95MLD-1^06243009.0087600 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
293166084-11181-DTLSB-07_31_2023-GO95MLD-1^06243009.0087602 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2028-07-31 | 3
238991563-84529-DTLSB-07_26_2023-GO95MLD-1^06243009.0087800 | OTHER | FHCA | Distribution | 2023-07-26 | 2026-07-26 | 2
800256663-35529-DTLSB-07_26_2023-GO95HV-1^06243009.0087902 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
800256663-35529-DTLSB-07_26_2023-GO95MLD-1^06243009.0087902 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
840262876-78869-DTLSB-08_16_2023-GO95MLD-1^06243009.0104201 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2028-08-16 | 3
826504133-36979-DTLSB-08_16_2023-GO95MLD-1^06243009.0105000 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2028-08-16 | 3
348171913-24429-ADMIN-08_28_2024-POLEREPL-1^06243009.0105100 | POLE | CA-TIER-2 | Distribution | 2024-08-28 | 2025-08-28 | 2
679439893-92429-DTLSB-08_23_2023-GO95HV-1^06243009.0109400 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
679439893-92429-DTLSB-08_23_2023-GO95MLD-1^06243009.0109400 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
231592603-33429-DTLSB-08_23_2023-GO95MLD-1^06243009.0109402 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
445134286-3779-DTLSB-08_29_2023-GO95HV-1^06243009.0110300 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
681693796-35796-DTLSB-08_23_2023-GO95HV-1^06243009.0110340 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
303478696-40796-DTLSB-08_29_2023-GO95HV-1^06243009.0110341 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
533297316-7121-DTLSB-08_29_2023-GO95MLD-1^06243009.0114800 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
951490270-82633-DTLSB-08_29_2023-GO95TCH-1^06243009.0117400 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
828366986-78189-DTLSB-08_29_2023-GO95TCH-1^06243009.0117401 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
828366986-78189-DTLSB-08_29_2023-SVCDEFLC-1^06243009.0117401 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
828366986-78189-DTLSB-08_29_2023-SVCDEFLC-2^06243009.0117401 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
632342276-89189-DTLSB-08_29_2023-GO95MLD-1^06243009.0118400 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
961015216-10389-DTLSB-08_24_2023-GO95MLD-1^06243009.0118600 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
328776236-17279-DTLSB-08_24_2023-GO95MLD-1^06243009.0118601 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
545587866-3089-DTLSB-08_24_2023-CLRTOUCH-1^06243009.0118603 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
545587866-3089-DTLSB-08_24_2023-GO95MLD-1^06243009.0118603 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
317356906-58229-DTLSB-08_29_2023-GO95MLD-1^06243009.0119401 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
667551236-40329-DTLSB-08_24_2023-GO95MLD-1^06243009.0119500 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
506209626-94689-DTLSB-08_24_2023-GO95MLD-1^06243009.0119502 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
870207646-28229-DTLSB-08_24_2023-GO95MLD-1^06243009.0119503 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
870207646-28229-DTLSB-08_24_2023-SVCDEFLC-1^06243009.0119503 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
121722166-49229-DTLSB-08_24_2023-SVCDEFLC-1^06243009.0119602 | OTHER | CA-NON-TIER | Distribution | 2023-08-24 | 2026-08-24 | 2
654704466-82329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120100 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
806503823-55329-DTLSB-08_29_2023-GO95BLTC-1^06243009.0120101 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
806503823-55329-DTLSB-08_29_2023-GO95HV-1^06243009.0120101 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2028-08-29 | 3
806503823-55329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120101 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
485419896-8599-DTLSB-08_29_2023-GO95MLD-1^06243009.0120302 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
441242436-21329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120400 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
838302813-95329-DTLSB-08_29_2023-GO95MLD-1^06243009.0121001 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
478822603-76299-DTLSB-08_29_2023-GO95MLD-1^06243009.0121102 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
253004103-15329-DTLSB-08_29_2023-GO95MLD-1^06243009.0121201 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
161689143-49379-DTLSB-08_29_2023-GO95MLD-1^06243009.0121300 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
917126223-23329-AUDIT-10_10_2023-GO95BLTC-1^06243009.0121400 | OTHER | CA-NON-TIER | Distribution | 2023-10-10 | 2028-10-10 | 3
137157923-43329-ADMIN-07_11_2024-POLEREPL-1^06243009.0122302 | POLE | CA-NON-TIER | Distribution | 2024-07-11 | 2027-07-11 | 2
514582783-23769-DTLSB-08_29_2023-GO95MLD-1^06243009.0123401 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2026-08-29 | 2
604326763-94329-DTLSB-08_29_2023-GO95MLD-1^06243009.0123503 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2028-08-29 | 3
319769243-679-DTLSB-08_29_2023-GO95MLD-1^06243009.0123504 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2028-08-29 | 3
94384963-879-ADMIN-07_11_2024-POLEREPL-1^06243009.0124600 | POLE | CA-TIER-2 | Distribution | 2024-07-11 | 2025-07-11 | 2
428992363-20189-ADMIN-07_11_2024-POLEREPL-1^06243009.0125601 | POLE | CA-TIER-2 | Distribution | 2024-07-11 | 2025-07-11 | 2
29301959-85289-DTLSB-08_29_2023-GO95STUB-1^06243009.0130900 | OTHER | CA-NON-TIER | Distribution | 2023-08-29 | 2026-08-29 | 2
29301959-85289-ADMIN-07_11_2024-POLEREPL-1^06243009.0130900 | POLE | CA-NON-TIER | Distribution | 2024-07-11 | 2027-07-11 | 2
706118169-19029-DTLSB-08_17_2023-GO95MLD-1^06243009.0131002 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
706118169-19029-DTLSB-08_17_2023-SVCDEFLC-1^06243009.0131002 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
50515680-80399-DTLSB-08_17_2023-GO95MLD-1^06243009.0131003 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
300344880-79029-DTLSB-08_17_2023-GO95HV-1^06243009.0131200 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
300344880-79029-DTLSB-08_17_2023-GO95MLD-1^06243009.0131200 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
678147265-98265-DTLSB-08_17_2023-GO95MLD-1^06243009.0131201 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
371132991-26689-DTLSB-08_17_2023-GO95MLD-1^06243009.0131300 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
25090050-1129-DTLSB-08_17_2023-GUYNOINS-1^06243009.0131502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
25090050-1129-DTLSB-08_17_2023-GUYNOINS-2^06243009.0131502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
73603850-60129-DTLSB-08_17_2023-GO95MLD-1^06243009.0131503 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
768628189-80129-DTLSB-08_17_2023-GO95MLD-1^06243009.0131600 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
766508810-1309-DTLSB-08_17_2023-GO95MLD-1^06243009.0131602 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
442719271-59269-AUDIT-10_09_2023-GO95HV-1^06243009.0131800 | OTHER | CA-NON-TIER | Distribution | 2023-10-09 | 2028-10-09 | 3
990407171-17882-DTLSB-08_17_2023-GO95HV-1^06243009.0131801 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
281640789-51309-DTLSB-08_17_2023-GO95HV-1^06243009.0132501 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
281640789-51309-DTLSB-08_17_2023-GO95MLD-1^06243009.0132501 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
704993151-30582-DTLSB-08_23_2023-GO95MLD-1^06243009.0133000 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
803295009-96942-DTLSB-08_23_2023-GO95HV-1^06243009.0133001 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2028-08-23 | 3
85408179-68929-DTLSB-08_17_2023-GO95HV-1^06243009.0134500 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
626203519-19929-ADMIN-07_10_2024-POLEREPL-1^06243009.0136400 | POLE | CA-TIER-2 | Distribution | 2024-07-10 | 2025-07-10 | 2
573143809-72209-DTLSB-08_17_2023-GO95HV-1^06243009.0136401 | OTHER | CA-TIER-2 | Distribution | 2023-08-17 | 2028-08-17 | 3
573143809-72209-DTLSB-08_17_2023-GO95MLD-1^06243009.0136401 | OTHER | CA-TIER-2 | Distribution | 2023-08-17 | 2028-08-17 | 3
476126851-29-ADMIN-07_10_2024-POLEREPL-1^06243009.0137001 | POLE | CA-NON-TIER | Distribution | 2024-07-10 | 2027-07-10 | 2
234633941-1029-ADMIN-07_10_2024-POLEREPL-1^06243009.0137400 | POLE | CA-TIER-2 | Distribution | 2024-07-10 | 2025-07-10 | 2
546196431-11029-ADMIN-07_11_2024-POLEREPL-1^06243009.0137401 | POLE | CA-TIER-2 | Distribution | 2024-07-11 | 2025-07-11 | 2
184338839-79929-ADMIN-07_10_2024-POLEREPL-1^06243009.0138401 | POLE | CA-TIER-2 | Distribution | 2024-07-10 | 2025-07-10 | 2
296102961-80679-DTLSB-08_08_2023-GO95MLD-1^06243009.0140601 | OTHER | CA-NON-TIER | Distribution | 2023-08-08 | 2026-08-08 | 2
99310291-94229-DTLSB-08_08_2023-GO95MLD-1^06243009.0140701 | OTHER | CA-NON-TIER | Distribution | 2023-08-08 | 2026-08-08 | 2
687064149-75149-DTLSB-08_10_2023-GO95MLD-1^06243009.0141001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
852377489-61178-DTLSB-08_10_2023-GO95MLD-1^06243009.0150000 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
18883718-19829-DTLSB-08_09_2023-GO95MLD-1^06243009.0150302 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
592797918-39829-DTLSB-08_09_2023-GO95MLD-1^06243009.0150303 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
623601309-26978-DTLSB-08_10_2023-GO95MLD-1^06243009.0152001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
251241409-30778-DTLSB-08_10_2023-GO95MLD-1^06243009.0153000 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
514725318-36722-ADMIN-06_19_2024-POLEREPL-1^06243009.0153501 | POLE | CA-TIER-2 | Distribution | 2024-06-19 | 2025-06-19 | 2
825000020-78574-ADMIN-06_19_2024-POLEREPL-1^06243009.0153700 | POLE | CA-TIER-2 | Distribution | 2024-06-19 | 2025-06-19 | 2
939680509-75578-DTLSB-08_10_2023-GO95MLD-1^06243009.0154001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
748764928-20929-DTLSB-08_16_2023-GO95MLD-1^06243009.0154300 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
415763728-70989-DTLSB-08_16_2023-ABNDEQPM-1^06243009.0154400 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2028-08-16 | 3
415763728-70989-DTLSB-08_16_2023-GO95HV-1^06243009.0154400 | OTHER | CA-NON-TIER | Distribution | 2023-08-16 | 2028-08-16 | 3
765055228-60929-DTLSB-08_08_2023-GUYNOINS-1^06243009.0154500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
765055228-60929-DTLSB-08_08_2023-GUYNOINS-2^06243009.0154500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
974313798-6929-DTLSB-08_16_2023-GO95MLD-1^06243009.0154601 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
974313798-6929-DTLSB-08_16_2023-GRDRODHI-1^06243009.0154601 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
382467928-16929-DTLSB-08_08_2023-SVCROAD-1^06243009.0155600 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
334261918-93779-ADMIN-08_26_2024-POLEREPL-1^06243009.0155601 | POLE | CA-TIER-2 | Distribution | 2024-08-26 | 2025-08-26 | 2
67238698-46929-DTLSB-08_16_2023-GO95MLD-1^06243009.0155901 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
994410138-6829-DTLSB-08_10_2023-GO95MLD-1^06243009.0156001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
831303158-53929-DTLSB-08_03_2023-GO95MLD-1^06243009.0156401 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2028-08-03 | 3
536486078-12889-DTLSB-08_03_2023-GO95MLD-1^06243009.0156500 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
536486078-12889-DTLSB-08_03_2023-SVCROAD-1^06243009.0156500 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
388998217-94369-ADMIN-08_26_2024-POLEREPL-1^06243009.0156700 | POLE | CA-TIER-2 | Distribution | 2024-08-26 | 2025-08-26 | 2
530917278-31929-DTLSB-08_03_2023-GO95HV-1^06243009.0157400 | OTHER | CA-NON-TIER | Distribution | 2023-08-03 | 2028-08-03 | 3
530917278-31929-DTLSB-08_03_2023-INSULDMG-1^06243009.0157400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
340740238-94189-DTLSB-08_10_2023-GO95MLD-1^06243009.0158001 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
39042838-92699-DTLSB-08_23_2023-GO95MLD-1^06243009.0158900 | OTHER | CA-TIER-2 | Distribution | 2023-08-23 | 2026-08-23 | 2
39042838-92699-DTLSB-08_23_2023-GUYHINS-1^06243009.0158900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-23 | 2026-08-23 | 2
254676048-12929-DTLSB-08_23_2023-GO95MLD-1^06243009.0158901 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
721209088-72929-DTLSB-08_08_2023-GO95MLD-1^06243009.0159502 | OTHER | CA-NON-TIER | Distribution | 2023-08-08 | 2028-08-08 | 3
582367027-99829-DTLSB-08_16_2023-GUYNOINS-1^06243009.0169000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
582367027-99829-DTLSB-08_16_2023-GUYNOINS-2^06243009.0169000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-16 | 2026-08-16 | 2
421420004-72479-DTLSB-08_01_2023-GO95MLD-1^06243009.0172900 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
637984824-87589-DTLSB-07_25_2023-GO95MLD-1^06243009.0172901 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
606090414-22729-DTLSB-08_01_2023-GO95HV-1^06243009.0173602 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
370671044-53099-DTLSB-07_27_2023-SVCDEFLC-1^06243009.0187402 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
739287754-7729-DTLSB-08_01_2023-SVCDEFLC-1^06243009.0187701 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
325461964-37729-DTLSB-07_31_2023-GO95MLD-1^06243009.0188600 | OTHER | CA-TIER-2 | Distribution | 2023-07-31 | 2026-07-31 | 2
696128584-46729-DTLSB-08_01_2023-GO95MLD-1^06243009.0188701 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
408101594-65729-DTLSB-08_01_2023-GO95MLD-1^06243009.0189803 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
972160814-65629-DTLSB-08_09_2023-GO95MLD-1^06243009.0190500 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
502743516-34516-DTLSB-08_09_2023-GO95MLD-1^06243009.0190701 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
110229804-37629-DTLSB-08_09_2023-GO95MLD-1^06243009.0193300 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
142594694-35629-DTLSB-08_09_2023-GO95MLD-1^06243009.0194200 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
967554324-5629-DTLSB-08_09_2023-GO95MLD-1^06243009.0196100 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
773831134-50629-DTLSB-08_07_2023-GO95MLD-1^06243009.0196201 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
959117324-40629-DTLSB-08_07_2023-GO95HV-1^06243009.0196202 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
410298734-60629-DTLSB-08_07_2023-GO95MLD-1^06243009.0196401 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
811824334-41629-DTLSB-08_07_2023-GO95HV-1^06243009.0196501 | OTHER | FHCA | Distribution | 2023-08-07 | 2028-08-07 | 3
59987334-81629-DTLSB-08_02_2023-GO95HV-1^06243009.0196601 | OTHER | FHCA | Distribution | 2023-08-02 | 2028-08-02 | 3
59987334-81629-DTLSB-08_02_2023-GO95MLD-1^06243009.0196601 | OTHER | FHCA | Distribution | 2023-08-02 | 2026-08-02 | 2
983378754-10629-DTLSB-08_07_2023-GO95MLD-1^06243009.0197001 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
132507637-63479-DTLTRT-08_21_2023-SVCDEFLC-1^06243009.0213400 | OTHER | CA-TIER-2 | Distribution | 2023-08-21 | 2026-08-21 | 2
863647187-20989-DTLSB-08_17_2023-GO95BLTC-1^06243009.0214301 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
863647187-20989-DTLSB-08_17_2023-GO95MLD-1^06243009.0214301 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
653540667-91099-DTLSB-08_17_2023-GO95HV-1^06243009.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2028-08-17 | 3
653540667-91099-DTLSB-08_17_2023-SVCDEFLC-1^06243009.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-08-17 | 2026-08-17 | 2
140474407-53829-DTLSB-08_21_2023-GUYNOINS-1^06243009.0216000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
908615169-58169-DTLSB-08_21_2023-GO95MLD-1^06243009.0216005 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
537247597-81109-DTLSB-08_21_2023-GO95MLD-1^06243009.0219000 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
537247597-81109-DTLSB-08_21_2023-GUYHINS-1^06243009.0219000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
644138927-20829-DTLSB-08_21_2023-GO95HV-1^06243009.0219200 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
644138927-20829-DTLSB-08_21_2023-INSULDMG-1^06243009.0219200 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
105017367-8829-ADMIN-06_30_2022-POLEREPL-1^06243009.0219802 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
105017367-8829-DTLSB-08_21_2023-XARMBRAC-1^06243009.0219802 | CROSSARM | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
812981187-25822-ADMIN-06_30_2022-POLEREPL-1^06243009.0219803 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
812981187-25822-DTLSB-08_21_2023-GO95HV-1^06243009.0219803 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
154476807-20679-DTLSB-08_21_2023-GO95HV-1^06243009.0219804 | OTHER | CA-TIER-2 | Distribution | 2023-08-21 | 2028-08-21 | 3
262677457-28829-ADMIN-08_26_2024-POLEREPL-1^06243009.0219805 | POLE | CA-TIER-2 | Distribution | 2024-08-26 | 2025-08-26 | 2
568176985-92768-ADMIN-06_30_2022-POLEREPL-1^06243009.0220700 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
568176985-92768-DTLSB-08_21_2023-GO95HV-1^06243009.0220700 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
700707307-87829-DTLSB-08_21_2023-GO95MLD-1^06243009.0220800 | OTHER | CA-NON-TIER | Distribution | 2023-08-21 | 2028-08-21 | 3
449555437-83322-DTLSB-08_21_2023-GUYHINS-1^06243009.0222200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-21 | 2026-08-21 | 2
343666524-77524-DTLSB-08_10_2023-GO95MLD-1^06243009.0225700 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
343666524-77524-DTLSB-08_10_2023-GUYHINS-1^06243009.0225700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
320129424-40524-DTLSB-08_10_2023-GO95HV-1^06243009.0226700 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2028-08-10 | 3
898312217-78222-DTLSB-08_10_2023-GO95MLD-1^06243009.0227800 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
771237369-9369-DTLSB-08_23_2023-GO95CLSV-1^06243009.0231600 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
771237369-9369-DTLSB-08_23_2023-SVCDEFLC-1^06243009.0231600 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
771237369-9369-DTLSB-08_23_2023-SVCWIND-1^06243009.0231600 | OTHER | CA-NON-TIER | Distribution | 2023-08-23 | 2026-08-23 | 2
751569350-61229-DTLSB-08_03_2023-INSULDMG-1^06243009.0232301 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-03 | 2026-08-03 | 2
729336706-92488-DTLSB-08_14_2023-GO95HV-1^06243009.0236700 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
607558391-30491-DTLSB-08_14_2023-GO95HV-1^06243009.0236902 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
851057811-19482-DTLSB-08_14_2023-GO95MLD-1^06243009.0238400 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
851057811-19482-DTLSB-08_14_2023-GUYHINS-1^06243009.0238400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
216575606-6668-DTLSB-08_14_2023-GO95HV-1^06243009.0241800 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
216575606-6668-ADMIN-07_11_2024-POLEREPL-1^06243009.0241800 | POLE | CA-NON-TIER | Distribution | 2024-07-11 | 2027-07-11 | 2
518907831-85789-DTLSB-08_14_2023-GO95MLD-1^06243009.0242300 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
508063619-16029-AUDIT-10_09_2023-GO95HV-1^06243009.0242700 | OTHER | CA-NON-TIER | Distribution | 2023-10-09 | 2028-10-09 | 3
304739299-27029-DTLSB-08_14_2023-GO95HV-1^06243009.0242900 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
766141229-36679-DTLSB-08_15_2023-GO95MLD-1^06243009.0243601 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
298361119-63029-DTLSB-08_14_2023-GO95HV-1^06243009.0244101 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
296192290-57199-DTLSB-08_14_2023-GO95MLD-1^06243009.0244405 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
651650419-86042-DTLSB-08_14_2023-GRDRODHI-1^06243009.0244900 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
872456400-71029-DTLSB-08_14_2023-INSULDMG-1^06243009.0245300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
872456400-71029-DTLSB-08_14_2023-INSULDMG-2^06243009.0245300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
964799700-51029-DTLSB-08_14_2023-INSULDMG-1^06243009.0245301 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
20750621-70889-DTLSB-08_15_2023-GO95BLTC-1^06243009.0245500 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2028-08-15 | 3
20750621-70889-DTLSB-08_15_2023-GO95MLD-1^06243009.0245500 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
235914551-54789-DTLSB-08_14_2023-GO95MLD-1^06243009.0246000 | OTHER | CA-TIER-2 | Distribution | 2023-08-14 | 2028-08-14 | 3
121475103-37103-DTLSB-08_14_2023-GO95MLD-1^06243009.0246002 | OTHER | CA-TIER-2 | Distribution | 2023-08-14 | 2028-08-14 | 3
823344649-57989-DTLSB-08_14_2023-GO95HV-1^06243009.0246101 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2028-08-14 | 3
126905179-82029-DTLSB-08_14_2023-GO95MLD-1^06243009.0246103 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
257235591-51282-DTLSB-08_14_2023-GO95MLD-1^06243009.0246104 | OTHER | CA-NON-TIER | Distribution | 2023-08-14 | 2026-08-14 | 2
582852706-4298-DTLSB-08_16_2023-GUYHINS-1^06243009.0246200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-08-16 | 2026-08-16 | 2
118144135-14302-DTLSB-08_15_2023-SVCDEFLC-1^06243009.0261001 | OTHER | FHCA | Distribution | 2023-08-15 | 2026-08-15 | 2
797988988-17342-DTLSB-08_15_2023-SVCDEFLC-1^06243009.0261003 | OTHER | FHCA | Distribution | 2023-08-15 | 2026-08-15 | 2
797988988-17342-DTLSB-08_15_2023-SVCDEFLC-2^06243009.0261003 | OTHER | FHCA | Distribution | 2023-08-15 | 2026-08-15 | 2
904583715-98429-DTLSB-08_15_2023-SVCDEFLC-1^06243009.0262700 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
545039676-59879-DTLSB-08_15_2023-GO95MLD-1^06243009.0263800 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2028-08-15 | 3
545039676-59879-DTLSB-08_15_2023-SVCDEFLC-1^06243009.0263800 | OTHER | CA-NON-TIER | Distribution | 2023-08-15 | 2026-08-15 | 2
787563348-42899-DTLSB-08_15_2023-GO95MLD-1^06243009.0267001 | OTHER | FHCA | Distribution | 2023-08-15 | 2026-08-15 | 2
791784713-90489-DTLSB-08_10_2023-GO95MLD-1^06243009.0276100 | OTHER | CA-NON-TIER | Distribution | 2023-08-10 | 2026-08-10 | 2
676376611-9529-DTLSB-08_16_2023-GUYNOINS-1^06243009.0281801 | ANCHOR/GUY | FHCA | Distribution | 2023-08-16 | 2026-08-16 | 2
605147931-629-DTLSB-08_07_2023-GO95HV-1^06243009.0281804 | OTHER | FHCA | Distribution | 2023-08-07 | 2028-08-07 | 3
807229931-49529-DTLSB-08_07_2023-GO95STUB-1^06243009.0281805 | OTHER | FHCA | Distribution | 2023-08-07 | 2026-08-07 | 2
552135201-79529-DTLSB-08_16_2023-GO95MLD-1^06243009.0281900 | OTHER | FHCA | Distribution | 2023-08-16 | 2026-08-16 | 2
654706843-78189-DTLSB-08_16_2023-GO95MLD-1^06243009.0283200 | OTHER | FHCA | Distribution | 2023-08-16 | 2026-08-16 | 2
504294483-32452-DTLSB-08_16_2023-SVCDEFLC-1^06243009.0283600 | OTHER | FHCA | Distribution | 2023-08-16 | 2026-08-16 | 2
362854203-15589-DTLSB-08_16_2023-GO95HV-1^06243009.0283601 | OTHER | FHCA | Distribution | 2023-08-16 | 2028-08-16 | 3
320830463-2199-DTLSB-08_16_2023-RISEGRD-1^06243009.0284200 | OTHER | FHCA | Distribution | 2023-08-16 | 2026-08-16 | 2
707214863-3979-DTLSB-08_21_2023-GO95HV-1^06243009.0286901 | OTHER | FHCA | Distribution | 2023-08-21 | 2028-08-21 | 3
707214863-3979-DTLSB-08_21_2023-GO95MLD-1^06243009.0286901 | OTHER | FHCA | Distribution | 2023-08-21 | 2026-08-21 | 2
682273511-90129-DTLSB-07_19_2023-GO95MLD-1^06243010.0020000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
456607790-55532-DTLSB-07_19_2023-GO95MLD-1^06243010.0020100 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
456607790-55532-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0020100 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
519464102-24888-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0020203 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
217129180-89899-DTLSB-07_19_2023-GO95HV-1^06243010.0020300 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
217129180-89899-DTLSB-07_19_2023-GO95MLD-1^06243010.0020300 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
217129180-89899-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0020300 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
475167819-69029-DTLSB-07_18_2023-GO95HV-1^06243010.0020401 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
991326421-83342-DTLSB-07_20_2023-GO95HV-1^06243010.0021200 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
172027480-75332-DTLSB-07_19_2023-GO95MLD-1^06243010.0021201 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
178665150-34732-DTLSB-07_19_2023-GO95MLD-1^06243010.0021202 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
70207160-34232-DTLSB-07_19_2023-GO95MLD-1^06243010.0021203 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
524098910-70189-DTLSB-07_19_2023-SVCENTCO-1^06243010.0021400 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
918940650-41129-DTLSB-07_19_2023-GO95MLD-1^06243010.0021402 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
155955429-14479-DTLSB-07_18_2023-GO95MLD-1^06243010.0021404 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
827785830-50129-DTLSB-07_24_2023-GO95HV-1^06243010.0021701 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
577843500-46832-DTLSB-07_19_2023-GO95HV-1^06243010.0022201 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
577843500-46832-DTLSB-07_19_2023-GO95MLD-1^06243010.0022201 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
636422470-11132-DTLSB-07_19_2023-GO95MLD-1^06243010.0022202 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
836410950-2232-DTLSB-07_19_2023-RISEGRD-1^06243010.0022300 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
355834540-51232-DTLSB-07_19_2023-GO95MLD-1^06243010.0022301 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
727673811-59352-DTLSB-07_24_2023-GO95MLD-1^06243010.0023300 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
882821149-20129-DTLSB-07_20_2023-GO95MLD-1^06243010.0023401 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
882821149-20129-DTLSB-07_20_2023-GO95MLD-2^06243010.0023401 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
882821149-20129-DTLSB-07_20_2023-GRDRODHI-1^06243010.0023401 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
791629699-76899-DTLSB-07_24_2023-GO95MLD-1^06243010.0024301 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
641662159-39029-DTLSB-07_24_2023-GO95HV-1^06243010.0024402 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
975529269-7579-DTLSB-07_24_2023-GO95MLD-1^06243010.0024403 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
688597758-98758-DTLSB-07_24_2023-GO95HV-1^06243010.0025700 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
870190770-47199-DTLSB-07_25_2023-GO95BLTC-1^06243010.0026200 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
870190770-47199-DTLSB-07_25_2023-GO95HV-1^06243010.0026200 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
870190770-47199-DTLSB-07_25_2023-GO95MLD-1^06243010.0026200 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
994504990-79789-DTLSB-07_20_2023-GO95MLD-1^06243010.0026402 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
831611340-8879-DTLSB-07_17_2023-GO95MLD-1^06243010.0028101 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
539838210-762-DTLSB-07_19_2023-GO95MLD-1^06243010.0034000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
539838210-762-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0034000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
998084819-38029-ADMIN-07_24_2024-POLEREPL-1^06243010.0034501 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
566575019-57042-DTLSB-07_18_2023-GO95HV-1^06243010.0035501 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
430291109-51042-DTLSB-07_18_2023-GO95HV-1^06243010.0037500 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
407513280-5762-DTLSB-07_18_2023-GO95HV-1^06243010.0037602 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
407513280-5762-DTLSB-07_18_2023-GO95MLD-1^06243010.0037602 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
566666751-10582-DTLSB-07_18_2023-GO95MLD-1^06243010.0037801 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
885366720-31762-DTLSB-07_18_2023-GO95MLD-1^06243010.0037901 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
448758859-55342-DTLSB-07_19_2023-GO95HV-1^06243010.0038000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
448758859-55342-DTLSB-07_19_2023-GO95MLD-1^06243010.0038000 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
520905170-31662-DTLSB-07_18_2023-GO95MLD-1^06243010.0038303 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
520905170-31662-DTLSB-07_18_2023-SVCRUBLG-1^06243010.0038303 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
520905170-31662-DTLSB-07_18_2023-SVCWIND-1^06243010.0038303 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
480408789-65742-ADMIN-07_24_2024-POLEREPL-1^06243010.0038401 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
365841010-29172-DTLSB-07_20_2023-SVCDEFLC-1^06243010.0038700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
782959069-7029-ADMIN-07_16_2024-POLEREPL-1^06243010.0039001 | POLE | CA-TIER-2 | Distribution | 2024-07-16 | 2025-07-16 | 2
449557370-25162-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0039101 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
748972621-72682-DTLSB-07_19_2023-GO95MLD-1^06243010.0039102 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
391307811-15582-DTLSB-07_19_2023-GO95HV-1^06243010.0039103 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
402091769-15642-DTLSB-07_19_2023-GO95MLD-1^06243010.0039104 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
560729139-37029-DTLSB-07_19_2023-GO95MLD-1^06243010.0039204 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
449721381-94982-DTLSB-07_19_2023-GO95MLD-1^06243010.0039205 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
879548049-28942-DTLSB-07_19_2023-GO95CL10-1^06243010.0039206 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
879548049-28942-DTLSB-07_19_2023-GO95MLD-1^06243010.0039206 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
297895210-54662-DTLSB-07_18_2023-GO95MLD-1^06243010.0039300 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
301425500-95462-DTLSB-07_18_2023-GO95MLD-1^06243010.0039301 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
583323230-66762-DTLSB-07_19_2023-GO95TCH-1^06243010.0039302 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
675615400-11362-DTLSB-07_18_2023-GO95MLD-1^06243010.0039304 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
175214289-77029-DTLSB-07_18_2023-GO95HV-1^06243010.0039305 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
252923239-58742-DTLSB-07_18_2023-GO95MLD-1^06243010.0039500 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
252923239-58742-DTLSB-07_18_2023-SVCDEFLC-1^06243010.0039500 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
518936440-31162-DTLSB-07_18_2023-SVCDEFLC-1^06243010.0039502 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
984102540-23262-DTLSB-07_18_2023-GO95HV-1^06243010.0039601 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
708278750-91362-DTLSB-07_18_2023-GO95HV-1^06243010.0039701 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
156471560-76362-DTLSB-07_18_2023-GO95HV-1^06243010.0039800 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
144964360-68362-DTLSB-07_18_2023-GO95HV-1^06243010.0039801 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
144964360-68362-DTLSB-07_18_2023-GO95MLD-1^06243010.0039801 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
197328589-56642-DTLSB-07_19_2023-GO95HV-1^06243010.0104900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
197328589-56642-DTLSB-07_19_2023-GO95MLD-1^06243010.0104900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
170301679-85679-DTLSB-07_19_2023-ABNDEQPM-1^06243010.0105900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
170301679-85679-DTLSB-07_19_2023-GO95MLD-1^06243010.0105900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
170301679-85679-DTLSB-07_19_2023-GRDRODHI-1^06243010.0105900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
170301679-85679-DTLSB-07_19_2023-SVCDEFLC-1^06243010.0105900 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2026-07-19 | 2
571040769-6029-DTLSB-07_19_2023-GO95HV-1^06243010.0105901 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
478079166-81266-DTLSB-07_25_2023-GO95MLD-1^06243010.0109300 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
241017049-65852-DTLSB-07_25_2023-GO95HV-1^06243010.0110201 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
277897014-13114-DTLSB-07_25_2023-GO95MLD-1^06243010.0110202 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
924297259-87029-DTLSB-07_27_2023-GO95HV-1^06243010.0110401 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
571073619-31252-DTLSB-07_24_2023-GO95MLD-1^06243010.0110600 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
318521070-42972-DTLSB-07_24_2023-GO95MLD-1^06243010.0110700 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
382153090-30589-DTLSB-07_24_2023-GO95MLD-1^06243010.0110801 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
494506980-93672-DTLSB-07_24_2023-SVCDEFLC-1^06243010.0110802 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
494506980-93672-DTLSB-07_24_2023-SVCROAD-1^06243010.0110802 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
12274430-64272-DTLSB-07_24_2023-GO95MLD-1^06243010.0110803 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
12274430-64272-DTLSB-07_24_2023-SVCDEFLC-1^06243010.0110803 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
844380330-62372-DTLSB-07_24_2023-GO95MLD-1^06243010.0110900 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
876349840-87872-DTLSB-07_24_2023-GO95MLD-1^06243010.0110902 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
180166050-1472-DTLSB-07_19_2023-GO95HV-1^06243010.0110907 | OTHER | CA-TIER-2 | Distribution | 2023-07-19 | 2028-07-19 | 3
968447150-13472-DTLSB-07_27_2023-GO95MLD-1^06243010.0111500 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2028-07-27 | 3
792789590-5572-DTLSB-07_24_2023-GO95MLD-1^06243010.0111800 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
942283570-30572-DTLSB-07_24_2023-SVCDEFLC-1^06243010.0111801 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
39663970-94499-DTLSB-07_24_2023-GO95MLD-1^06243010.0112801 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
845116230-4272-DTLSB-07_24_2023-GO95HV-1^06243010.0112901 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2028-07-24 | 3
845116230-4272-DTLSB-07_24_2023-GO95MLD-1^06243010.0112901 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
150263753-84890-DTLSB-07_17_2023-GO95MLD-1^06243010.0116500 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
297886740-56172-DTLSB-07_25_2023-ABNDEQPM-1^06243010.0116800 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
297886740-56172-DTLSB-07_25_2023-GO95HV-1^06243010.0116800 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2028-07-25 | 3
297886740-56172-DTLSB-07_25_2023-GO95MLD-1^06243010.0116800 | OTHER | CA-TIER-2 | Distribution | 2023-07-25 | 2026-07-25 | 2
813776320-96962-DTLSB-07_17_2023-GO95MLD-1^06243010.0117700 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
21184000-96172-DTLSB-07_17_2023-GO95HV-1^06243010.0117801 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
878960530-34299-DTLSB-07_17_2023-SVCRUBLG-1^06243010.0117802 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
930788530-47772-DTLSB-07_17_2023-GO95HV-1^06243010.0118200 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
930788530-47772-DTLSB-07_17_2023-GO95MLD-1^06243010.0118200 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
985717690-61962-DTLSB-07_17_2023-ABNDEQPM-1^06243010.0118201 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
985717690-61962-DTLSB-07_17_2023-GO95MLD-1^06243010.0118201 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
198934520-36472-DTLSB-07_17_2023-GO95MLD-1^06243010.0118900 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
242152070-63029-DTLSB-07_17_2023-GO95MLD-1^06243010.0119002 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
385948279-29952-DTLSB-07_17_2023-GO95HV-1^06243010.0119100 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
715162950-11862-DTLSB-07_26_2023-GO95HV-1^06243010.0119400 | OTHER | CA-TIER-2 | Distribution | 2023-07-26 | 2028-07-26 | 3
181576308-17702-DTLSB-08_07_2023-GO95MLD-1^06243010.0130000 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
80182955-19289-DTLSB-08_02_2023-GO95HV-1^06243010.0130400 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
265493708-31329-DTLSB-08_07_2023-GO95MLD-1^06243010.0131000 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
493814308-78702-DTLSB-08_07_2023-ABNDEQPM-1^06243010.0131001 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
493814308-78702-DTLSB-08_07_2023-GO95MLD-1^06243010.0131001 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
121266595-3329-DTLSB-08_07_2023-GO95MLD-1^06243010.0131101 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
695510355-52668-ADMIN-07_17_2024-POLEREPL-1^06243010.0131105 | POLE | CA-TIER-2 | Distribution | 2024-07-17 | 2025-07-17 | 2
160447788-86679-DTLSB-08_02_2023-GO95HV-1^06243010.0131201 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
432949183-40283-DTLSB-08_02_2023-SVCROAD-1^06243010.0131205 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
432949183-40283-DTLSB-08_02_2023-SVCROAD-2^06243010.0131205 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
114234958-44329-ADMIN-04_08_2024-POLEREPL-1^06243010.0131400 | POLE | CA-TIER-2 | Distribution | 2024-04-08 | 2025-04-08 | 2
571463845-8799-DTLSB-08_02_2023-GO95MLD-1^06243010.0131402 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
509688837-25289-DTLSB-08_02_2023-GO95HV-1^06243010.0131404 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
509688837-25289-DTLSB-08_02_2023-GO95MLD-1^06243010.0131404 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
54761075-71329-DTLSB-08_02_2023-GO95TCH-1^06243010.0132100 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
433181375-54189-DTLSB-08_02_2023-GO95MLD-1^06243010.0132101 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
433181375-54189-DTLSB-08_02_2023-GUYHINS-1^06243010.0132101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
433181375-54189-DTLSB-08_02_2023-SVCDEFLC-1^06243010.0132101 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
433181375-54189-DTLSB-08_02_2023-SVCROAD-1^06243010.0132101 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
156119585-42329-DTLSB-08_02_2023-SVCDEFLC-1^06243010.0132102 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
434147539-20639-DTLSB-08_02_2023-GO95TCH-1^06243010.0132143 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
41833835-1329-DTLSB-08_02_2023-GO95MLD-1^06243010.0132300 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
622618915-80329-DTLSB-08_02_2023-GO95HV-1^06243010.0132303 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
882247005-329-DTLSB-08_02_2023-GO95MLD-1^06243010.0134100 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
882247005-329-DTLSB-08_02_2023-GRDRODHI-1^06243010.0134100 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2026-08-02 | 2
549780174-8229-DTLSB-08_16_2023-GO95HV-1^06243010.0134200 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2028-08-16 | 3
429009674-39229-DTLSB-08_16_2023-GO95HV-1^06243010.0134201 | OTHER | CA-TIER-2 | Distribution | 2023-08-16 | 2028-08-16 | 3
429355164-96229-DTLSB-08_09_2023-GO95HV-1^06243010.0135000 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
87232764-37229-DTLSB-08_09_2023-GO95MLD-1^06243010.0135001 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
62629174-57229-DTLSB-08_02_2023-GO95MLD-1^06243010.0135002 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
350112414-10432-DTLSB-07_20_2023-GO95MLD-1^06243010.0141600 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
858649314-78332-DTLSB-07_24_2023-GO95MLD-1^06243010.0141700 | OTHER | CA-TIER-2 | Distribution | 2023-07-24 | 2026-07-24 | 2
803016314-42812-DTLSB-07_20_2023-SVCDEFLC-1^06243010.0142600 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
443767393-59393-DTLSB-07_20_2023-GO95HV-1^06243010.0142703 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
909822683-33683-DTLSB-07_20_2023-GO95MLD-1^06243010.0143702 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
72444574-82179-DTLSB-07_20_2023-SVCDEFLC-1^06243010.0144400 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
912607583-29583-DTLSB-07_20_2023-GO95HV-1^06243010.0144701 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
307034483-35980-DTLSB-07_20_2023-GO95MLD-1^06243010.0145700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
842538383-79383-DTLSB-07_20_2023-GO95HV-1^06243010.0146700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
842538383-79383-DTLSB-07_20_2023-GO95MLD-1^06243010.0146700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
94657653-98653-DTLSB-07_20_2023-GO95MLD-1^06243010.0146702 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
555580653-61653-DTLSB-07_20_2023-GO95HV-1^06243010.0147700 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
333727553-38553-DTLSB-07_20_2023-GO95MLD-1^06243010.0147701 | OTHER | CA-TIER-2 | Distribution | 2023-07-20 | 2028-07-20 | 3
278427243-50343-DTLSB-07_17_2023-GO95MLD-1^06243010.0148600 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
37705664-61229-DTLSB-07_20_2023-GUYNOINS-1^06243010.0148700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
37705664-61229-DTLSB-07_20_2023-GUYNOINS-2^06243010.0148700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-20 | 2026-07-20 | 2
976494801-35241-DTLSB-07_17_2023-GO95MLD-1^06243010.0148702 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
170309454-70229-DTLSB-07_17_2023-GUYNOINS-1^06243010.0148703 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
170309454-70229-DTLSB-07_17_2023-GUYNOINS-2^06243010.0148703 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
943620124-91229-DTLSB-07_17_2023-GO95MLD-1^06243010.0148801 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
247121484-12229-DTLSB-07_17_2023-GUYNOINS-1^06243010.0148803 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
247121484-12229-DTLSB-07_17_2023-GUYNOINS-2^06243010.0148803 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
85796774-52229-DTLSB-07_17_2023-GO95HV-1^06243010.0148804 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
80932284-22229-DTLSB-07_17_2023-GO95HV-1^06243010.0148900 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2028-07-17 | 3
457345184-55289-DTLSB-07_17_2023-RISEGRD-1^06243010.0149400 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
435319434-18689-ADMIN-07_16_2024-POLEREPL-1^06243010.0149401 | POLE | CA-TIER-2 | Distribution | 2024-07-16 | 2025-07-16 | 2
867019594-82229-DTLSB-07_17_2023-GO95MLD-1^06243010.0149900 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
558244884-42229-DTLSB-07_17_2023-GO95MLD-1^06243010.0149901 | OTHER | CA-TIER-2 | Distribution | 2023-07-17 | 2026-07-17 | 2
114966953-44292-DTLSB-08_02_2023-GO95HV-1^06243010.0156200 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
218103913-48792-DTLSB-07_27_2023-GO95MLD-1^06243010.0156701 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
691291343-10292-ADMIN-04_28_2024-POLEREPL-1^06243010.0157201 | POLE | CA-TIER-2 | Distribution | 2024-04-28 | 2025-04-28 | 2
143740433-99992-DTLSB-08_02_2023-GO95HV-1^06243010.0157202 | OTHER | CA-TIER-2 | Distribution | 2023-08-02 | 2028-08-02 | 3
721074303-62792-DTLSB-08_01_2023-GO95MLD-1^06243010.0158301 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
721074303-62792-DTLSB-08_01_2023-SVCDEFLC-1^06243010.0158301 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
296514583-45692-DTLSB-08_01_2023-GO95MLD-1^06243010.0158400 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
412935661-60582-DTLSB-08_01_2023-GO95MLD-1^06243010.0159601 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
673384983-78799-DTLSB-08_01_2023-GO95MLD-1^06243010.0159700 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
52445811-74082-DTLSB-07_26_2023-GUYNOINS-1^06243010.0159702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
52445811-74082-DTLSB-07_26_2023-GUYNOINS-2^06243010.0159702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-07-26 | 2026-07-26 | 2
460032913-66731-AUDIT-09_05_2023-GO95TCH-1^06243010.0159800 | OTHER | CA-TIER-2 | Distribution | 2023-09-05 | 2026-09-05 | 2
496662753-32292-DTLSB-07_27_2023-GO95MLD-1^06243010.0159900 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
496662753-32292-DTLSB-07_27_2023-RISEGRD-1^06243010.0159900 | OTHER | CA-TIER-2 | Distribution | 2023-07-27 | 2026-07-27 | 2
406332894-49129-DTLSB-08_08_2023-GO95TCH-1^06243010.0230000 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
552389314-29129-DTLSB-08_08_2023-GO95HV-1^06243010.0230001 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
614676314-58129-DTLSB-08_08_2023-GO95HV-1^06243010.0231102 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
403650464-96129-DTLSB-08_08_2023-GUYNOINS-1^06243010.0237400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
403650464-96129-DTLSB-08_08_2023-GUYNOINS-2^06243010.0237400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
196614404-37689-DTLSB-08_07_2023-GO95MLD-1^06243010.0239400 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2028-08-07 | 3
196614404-37689-DTLSB-08_07_2023-SVCDEFLC-1^06243010.0239400 | OTHER | CA-TIER-2 | Distribution | 2023-08-07 | 2026-08-07 | 2
663947534-12129-DTLSB-08_09_2023-GO95HV-1^06243010.0248700 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
225402434-55412-DTLSB-08_09_2023-GO95HV-1^06243010.0248701 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2028-08-09 | 3
225402434-55412-DTLSB-08_09_2023-GO95MLD-1^06243010.0248701 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
406850134-73029-DTLSB-08_09_2023-GO95MLD-1^06243010.0249600 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
449817929-19929-DTLSB-08_09_2023-GO95MLD-1^06243010.0249702 | OTHER | CA-TIER-2 | Distribution | 2023-08-09 | 2026-08-09 | 2
4453850-7089-DTLSB-08_08_2023-GO95MLD-1^06243010.0260400 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
159980588-95642-DTLSB-08_08_2023-GO95HV-1^06243010.0264900 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2028-08-08 | 3
358408595-42629-ADMIN-07_17_2024-POLEREPL-1^06243010.0279501 | POLE | CA-TIER-2 | Distribution | 2024-07-17 | 2025-07-17 | 2
952642415-14629-ADMIN-07_17_2024-POLEREPL-1^06243010.0279702 | POLE | CA-TIER-2 | Distribution | 2024-07-17 | 2025-07-17 | 2
731887296-49296-DTLSB-08_08_2023-GO95MLD-1^06243010.0279703 | OTHER | CA-TIER-2 | Distribution | 2023-08-08 | 2026-08-08 | 2
714219339-90439-DETAIL-07_18_2024-GO95HV-1^06244004.0042800 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
627240069-45199-DETAIL-07_18_2024-GRDRODHI-1^06244004.0043700 | OTHER | FHCA | Distribution | 2024-07-18 | 2027-07-18 | 2
969007341-56439-DETAIL-07_10_2024-GO95HV-1^06244004.0051400 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
966611171-39199-DETAIL-07_18_2024-GO95MLD-1^06244004.0052500 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
465614001-80979-DETAIL-07_18_2024-GUYHINS-1^06244004.0055300 | ANCHOR/GUY | FHCA | Distribution | 2024-07-18 | 2027-07-18 | 2
817793281-19439-DETAIL-07_18_2024-GO95HV-1^06244004.0056000 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
331807011-78439-DETAIL-07_18_2024-GO95HV-1^06244004.0056201 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
530793531-34439-DETAIL-07_18_2024-GO95HV-1^06244004.0056600 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
872508531-14439-DETAIL-07_18_2024-GO95HV-1^06244004.0057600 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
290729961-43439-DETAIL-07_18_2024-GO95HV-1^06244004.0058700 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
592604671-78199-DETAIL-04_04_2024-GO95HV-1^06244004.0066400 | OTHER | FHCA | Distribution | 2024-04-04 | 2029-04-04 | 3
592604671-78199-DETAIL-04_04_2024-GO95MLD-1^06244004.0066400 | OTHER | FHCA | Distribution | 2024-04-04 | 2027-04-04 | 2
592604671-78199-DETAIL-04_04_2024-GRDRODHI-1^06244004.0066400 | OTHER | FHCA | Distribution | 2024-04-04 | 2027-04-04 | 2
609089151-13599-DETAIL-03_20_2024-GO95HV-1^06244004.0066401 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
609089151-13599-DETAIL-03_20_2024-GO95MLD-1^06244004.0066401 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
609089151-13599-DETAIL-03_20_2024-SVCWIND-1^06244004.0066401 | OTHER | FHCA | Distribution | 2024-03-20 | 2027-03-20 | 2
233994071-47439-DETAIL-03_20_2024-GO95HV-1^06244004.0067400 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
281284591-85199-DETAIL-03_20_2024-RISEGRD-1^06244004.0068401 | OTHER | FHCA | Distribution | 2024-03-20 | 2027-03-20 | 2
107007374-6679-DETAIL-03_20_2024-GO95MLD-1^06244004.0069500 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
504593381-61539-DETAIL-07_18_2024-XARMSPCR-1^06244004.0086301 | CROSSARM | FHCA | Distribution | 2024-07-18 | 2027-07-18 | 2
555678041-80539-DETAIL-07_18_2024-GO95HV-1^06244004.0086600 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
98419331-20539-DETAIL-07_18_2024-GO95HV-1^06244004.0086700 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
100480722-42099-DETAIL-07_18_2024-SVCDEFLC-1^06244004.0176900 | OTHER | FHCA | Distribution | 2024-07-18 | 2027-07-18 | 2
422599025-94279-DETAIL-07_09_2024-GO95MLD-1^06244004.0182300 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
396880365-84639-DETAIL-07_09_2024-ABNDEQPM-1^06244004.0183100 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
897113085-30639-DETAIL-07_10_2024-GO95HV-1^06244004.0190000 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
897113085-30639-DETAIL-07_10_2024-GO95MLD-1^06244004.0190000 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
692123456-9819-DETAIL-07_24_2024-GO95HV-1^06244004.0190401 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
692123456-9819-DETAIL-07_24_2024-GRDRODHI-1^06244004.0190401 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
692123456-9819-DETAIL-07_24_2024-GRDRODHI-2^06244004.0190401 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
515995411-45939-DETAIL-07_10_2024-GO95HV-1^06244004.0190702 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
308439259-18679-DETAIL-07_10_2024-GO95MLD-1^06244004.0190803 | OTHER | FHCA | Distribution | 2024-07-10 | 2027-07-10 | 2
71697536-3199-DETAIL-07_10_2024-GO95MLD-1^06244004.0191800 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
201679119-25579-DETAIL-07_24_2024-GO95MLD-1^06244004.0192600 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
252035785-52639-DETAIL-07_09_2024-GO95HV-1^06244004.0192602 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
899982306-31639-DETAIL-07_09_2024-SVCDEFLC-1^06244004.0193502 | OTHER | FHCA | Distribution | 2024-07-09 | 2027-07-09 | 2
987284446-79699-DETAIL-07_31_2024-GO95MLD-1^06244004.0193601 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
660539005-9539-DETAIL-07_10_2024-GO95BLTC-1^06244004.0194000 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
660539005-9539-DETAIL-07_10_2024-GO95MLD-1^06244004.0194000 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
895474226-76879-DETAIL-07_31_2024-ABNDEQPM-1^06244004.0194500 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
443179836-8969-DETAIL-07_31_2024-GO95CL10-1^06244004.0194601 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
443179836-8969-DETAIL-07_31_2024-GO95MLD-1^06244004.0194601 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
257564505-48539-DETAIL-07_10_2024-GO95MLD-1^06244004.0196000 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
335074135-16539-DETAIL-07_10_2024-GO95HV-1^06244004.0203200 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
274945976-94539-DETAIL-07_10_2024-GO95HV-1^06244004.0205340 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
709149576-18639-DETAIL-07_10_2024-SVCENTCO-1^06244004.0215500 | OTHER | CA-TIER-2 | Distribution | 2024-07-10 | 2027-07-10 | 2
945850566-67989-DETAIL-07_10_2024-GO95MLD-1^06244004.0215501 | OTHER | CA-TIER-2 | Distribution | 2024-07-10 | 2029-07-10 | 3
437396776-41089-DETAIL-07_10_2024-GO95MLD-1^06244004.0216500 | OTHER | CA-TIER-2 | Distribution | 2024-07-10 | 2027-07-10 | 2
598360844-23099-DETAIL-07_08_2024-GO95MLD-1^06244005.0010301 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
512957254-72679-DETAIL-07_08_2024-GUYNOINS-1^06244005.0013501 | ANCHOR/GUY | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
512957254-72679-DETAIL-07_08_2024-GUYNOINS-2^06244005.0013501 | ANCHOR/GUY | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
554794587-59298-DETAIL-07_08_2024-GO95HV-1^06244005.0013502 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
554794587-59298-DETAIL-07_08_2024-GO95MLD-1^06244005.0013502 | OTHER | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
399987487-79487-DETAIL-07_05_2024-GO95HV-1^06244005.0013602 | OTHER | FHCA | Distribution | 2024-07-05 | 2029-07-05 | 3
566574893-20839-DETAIL-07_08_2024-GO95HV-1^06244005.0015500 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
940567703-40839-DETAIL-07_08_2024-GUYLOINS-1^06244005.0016401 | ANCHOR/GUY | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
48488513-51839-DETAIL-07_08_2024-GO95HV-1^06244005.0017402 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
430487223-31839-DETAIL-07_05_2024-GO95HV-1^06244005.0018400 | OTHER | FHCA | Distribution | 2024-07-05 | 2029-07-05 | 3
79204473-21679-DETAIL-07_18_2024-COPLLEAN-1^06244005.0019201 | POLE | FHCA | Distribution | 2024-07-18 | 2027-07-18 | 2
106310808-43058-DETAIL-07_05_2024-GO95MLD-1^06244005.0019402 | OTHER | FHCA | Distribution | 2024-07-05 | 2027-07-05 | 2
672459743-96499-DETAIL-08_05_2024-GO95HV-1^06244005.0025100 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
193502073-6139-DETAIL-08_05_2024-ENCHRW-1^06244005.0028101 | OTHER | FHCA | Distribution | 2024-08-05 | 2027-08-05 | 2
193502073-6139-DETAIL-08_05_2024-GO95HV-1^06244005.0028101 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
611708793-94739-DETAIL-08_05_2024-GO95HV-1^06244005.0029001 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
239286604-18099-DETAIL-08_05_2024-GO95MLD-1^06244005.0029002 | OTHER | FHCA | Distribution | 2024-08-05 | 2027-08-05 | 2
482712803-38579-DETAIL-08_05_2024-GO95HV-1^06244005.0029200 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
707323053-65739-DETAIL-08_05_2024-GO95HV-1^06244005.0029202 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
15837344-57099-DETAIL-08_05_2024-ABNDEQPM-1^06244005.0031500 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
15837344-57099-DETAIL-08_05_2024-GO95HV-1^06244005.0031500 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
635697314-44839-DETAIL-08_05_2024-GO95HV-1^06244005.0031900 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
529580294-97269-DETAIL-08_05_2024-SVCENTCO-1^06244005.0119900 | OTHER | FHCA | Distribution | 2024-08-05 | 2027-08-05 | 2
188169463-89639-DETAIL-07_08_2024-GO95HV-1^06244005.0125000 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
572837473-13799-DETAIL-07_08_2024-GRDRODHI-1^06244005.0125001 | OTHER | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
238527964-60739-DETAIL-07_08_2024-XARMSPCR-1^06244005.0125301 | CROSSARM | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
857270754-3579-AUDIT-08_12_2024-GRDRODHI-1^06244005.0125400 | OTHER | FHCA | Distribution | 2024-08-12 | 2027-08-12 | 2
392690674-23674-DETAIL-07_05_2024-SVCDEFLC-1^06244005.0125600 | OTHER | FHCA | Distribution | 2024-07-05 | 2027-07-05 | 2
55605134-53739-DETAIL-07_08_2024-SVCDEFLC-1^06244005.0125900 | OTHER | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
188740214-95979-DETAIL-07_10_2024-GO95MLD-1^06244005.0126100 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
203827704-94269-DETAIL-07_10_2024-RISEGRD-1^06244005.0126101 | OTHER | FHCA | Distribution | 2024-07-10 | 2027-07-10 | 2
919490183-43279-DETAIL-07_18_2024-GO95HV-1^06244005.0129900 | OTHER | FHCA | Distribution | 2024-07-18 | 2029-07-18 | 3
418132681-57399-DETAIL-07_24_2024-GO95MLD-1^06244005.0131300 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
418132681-57399-DETAIL-07_24_2024-SVCDEFLC-1^06244005.0131300 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
700892211-88512-DETAIL-07_24_2024-GO95HV-1^06244005.0131440 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
795667081-26069-DETAIL-07_24_2024-GUYHINS-1^06244005.0132401 | ANCHOR/GUY | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
507782990-39579-DETAIL-07_24_2024-ABNDEQPM-1^06244005.0133104 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
819410230-80230-DETAIL-07_24_2024-GO95MLD-1^06244005.0133301 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
777626230-67230-DETAIL-07_24_2024-GO95MLD-1^06244005.0133304 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
955963479-78039-DETAIL-07_08_2024-GO95HV-1^06244005.0135801 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
249765269-68039-DETAIL-07_08_2024-GO95HV-1^06244005.0135900 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
229980559-40889-DETAIL-07_24_2024-ABNDEQPM-1^06244005.0136200 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
229980559-40889-DETAIL-07_24_2024-GO95MLD-1^06244005.0136200 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
506617200-64889-DETAIL-07_08_2024-GO95MLD-1^06244005.0136700 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
545302681-18039-DETAIL-07_08_2024-GO95MLD-1^06244005.0136800 | OTHER | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
992405181-73679-DETAIL-07_08_2024-GO95MLD-1^06244005.0136801 | OTHER | FHCA | Distribution | 2024-07-08 | 2027-07-08 | 2
84155189-29879-DETAIL-07_08_2024-GO95HV-1^06244005.0136802 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
931665989-49189-DETAIL-07_08_2024-GO95HV-1^06244005.0137700 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
426697709-96039-DETAIL-07_08_2024-GO95HV-1^06244005.0138600 | OTHER | FHCA | Distribution | 2024-07-08 | 2029-07-08 | 3
176336751-14899-DETAIL-07_09_2024-GO95HV-1^06244005.0139201 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
869760041-64899-DETAIL-07_09_2024-GO95MLD-1^06244005.0139300 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
869760041-64899-DETAIL-07_09_2024-GRDRODHI-1^06244005.0139300 | OTHER | FHCA | Distribution | 2024-07-09 | 2027-07-09 | 2
873465395-10189-DETAIL-07_09_2024-GO95MLD-1^06244005.0139400 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
155727431-44899-DETAIL-07_09_2024-GO95MLD-1^06244005.0139401 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
161170068-15239-DETAIL-03_20_2024-GO95MLD-1^06244005.0140042 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
624346758-84379-DETAIL-03_25_2024-GO95MLD-1^06244005.0140043 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
325210046-66489-DETAIL-03_25_2024-GO95MLD-1^06244005.0140300 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
578295936-95239-DETAIL-04_01_2024-GUYLOINS-1^06244005.0140401 | ANCHOR/GUY | FHCA | Distribution | 2024-04-01 | 2027-04-01 | 2
348322238-73239-DETAIL-03_20_2024-GO95BLTC-1^06244005.0141040 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
348322238-73239-DETAIL-03_20_2024-GO95HV-1^06244005.0141040 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
524982078-64239-DETAIL-03_20_2024-GO95MLD-1^06244005.0141041 | OTHER | FHCA | Distribution | 2024-03-20 | 2027-03-20 | 2
925395678-6239-DETAIL-03_25_2024-GO95MLD-1^06244005.0141400 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
48124436-90239-DETAIL-03_25_2024-GO95MLD-1^06244005.0141401 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
637924538-48379-DETAIL-03_25_2024-GO95MLD-1^06244005.0141440 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
486618418-24469-DETAIL-03_20_2024-GO95HV-1^06244005.0142001 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
150931676-2489-DETAIL-03_20_2024-SVCENTCO-1^06244005.0142100 | OTHER | FHCA | Distribution | 2024-03-20 | 2027-03-20 | 2
281019208-42239-DETAIL-03_20_2024-GO95MLD-1^06244005.0142302 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
259646826-89189-DETAIL-03_25_2024-GO95MLD-1^06244005.0142406 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
696604086-61239-AUDIT-04_30_2024-GO95MLD-1^06244005.0143300 | OTHER | FHCA | Distribution | 2024-04-30 | 2027-04-30 | 2
508808588-3992-DETAIL-03_20_2024-GO95MLD-1^06244005.0144404 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
607609766-27789-DETAIL-03_20_2024-GO95MLD-1^06244005.0144406 | OTHER | FHCA | Distribution | 2024-03-20 | 2027-03-20 | 2
607609766-27789-DETAIL-03_20_2024-GRDRODHI-1^06244005.0144406 | OTHER | FHCA | Distribution | 2024-03-20 | 2027-03-20 | 2
607609766-27789-DETAIL-03_20_2024-GRDRODHI-2^06244005.0144406 | OTHER | FHCA | Distribution | 2024-03-20 | 2027-03-20 | 2
748907306-22139-DETAIL-03_25_2024-GO95MLD-1^06244005.0145001 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
748907306-22139-DETAIL-03_25_2024-SVCDEFLC-1^06244005.0145001 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
487686766-45889-DETAIL-03_25_2024-SVCDEFLC-1^06244005.0145104 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
244879818-71092-DETAIL-03_25_2024-GO95MLD-1^06244005.0145300 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
768127676-17979-DETAIL-03_25_2024-GO95HV-1^06244005.0145301 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
533327158-83989-DETAIL-03_25_2024-GO95MLD-1^06244005.0145302 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
726796286-48139-DETAIL-03_20_2024-GUYNOINS-1^06244005.0145401 | ANCHOR/GUY | FHCA | Distribution | 2024-03-20 | 2027-03-20 | 2
634119676-90782-DETAIL-03_20_2024-GO95HV-1^06244005.0145402 | OTHER | FHCA | Distribution | 2024-03-20 | 2029-03-20 | 3
287034526-3899-DETAIL-03_25_2024-GO95MLD-1^06244005.0146101 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
287034526-3899-DETAIL-03_25_2024-SVCDEFLC-1^06244005.0146101 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
799336916-30139-DETAIL-03_25_2024-GRDRODHI-1^06244005.0146102 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
42960498-64139-DETAIL-03_25_2024-GO95MLD-1^06244005.0146241 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
716107138-35139-DETAIL-03_25_2024-GO95MLD-1^06244005.0146300 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
102999388-54139-DETAIL-03_25_2024-GO95MLD-1^06244005.0146301 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
174164738-99638-DETAIL-03_25_2024-SVCDEFLC-1^06244005.0146400 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
363203193-54964-DETAIL-03_25_2024-GO95MLD-1^06244005.0146403 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
291757228-1869-DETAIL-03_26_2024-GO95HV-1^06244005.0147000 | OTHER | FHCA | Distribution | 2024-03-26 | 2029-03-26 | 3
585622848-2189-DETAIL-03_25_2024-GO95MLD-1^06244005.0147140 | OTHER | FHCA | Distribution | 2024-03-25 | 2029-03-25 | 3
577806918-85689-DETAIL-03_25_2024-GO95MLD-1^06244005.0147240 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
577806918-85689-DETAIL-03_25_2024-GRDRODHI-1^06244005.0147240 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
649083706-86099-DETAIL-03_25_2024-GO95MLD-1^06244005.0148401 | OTHER | FHCA | Distribution | 2024-03-25 | 2027-03-25 | 2
580730068-95699-DETAIL-03_26_2024-GO95MLD-1^06244005.0149001 | OTHER | FHCA | Distribution | 2024-03-26 | 2027-03-26 | 2
455774338-28489-DETAIL-04_01_2024-SVCENTBK-1^06244005.0149300 | OTHER | FHCA | Distribution | 2024-04-01 | 2027-04-01 | 2
480846998-36139-DETAIL-04_04_2024-SVCDEFLC-1^06244005.0149402 | OTHER | FHCA | Distribution | 2024-04-04 | 2027-04-04 | 2
194006934-65979-DETAIL-07_11_2024-RISEBKSP-1^06244005.0217500 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
731693804-70939-DETAIL-07_11_2024-GO95MLD-1^06244005.0218800 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
144054704-77839-DETAIL-07_11_2024-GO95HV-1^06244005.0219200 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
195846614-62779-DETAIL-07_11_2024-GO95HV-1^06244005.0219401 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
372041738-32738-DETAIL-07_11_2024-GO95MLD-1^06244005.0219601 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
306465054-40899-DETAIL-07_11_2024-GO95MLD-1^06244005.0219803 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
631088314-18679-DETAIL-07_11_2024-SVCDEFLC-1^06244005.0220200 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
259008313-59313-DETAIL-07_11_2024-GO95MLD-1^06244005.0220401 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
910364574-9839-DETAIL-07_11_2024-GO95MLD-1^06244005.0221802 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
614297415-76309-DETAIL-07_11_2024-GUYHINS-1^06244005.0221900 | ANCHOR/GUY | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
305058294-59989-DETAIL-07_09_2024-GO95MLD-1^06244005.0224000 | OTHER | FHCA | Distribution | 2024-07-09 | 2027-07-09 | 2
479116644-21789-DETAIL-07_17_2024-CUTOUTAR-3^06244005.0227104 | LIGHTNING ARRESTER | FHCA | Distribution | 2024-07-17 | 2027-07-17 | 2
759463964-27389-DETAIL-07_24_2024-GO95MLD-1^06244005.0227700 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
286595125-69669-DETAIL-07_24_2024-GO95MLD-1^06244005.0228601 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
292649034-14279-DETAIL-07_24_2024-SVCDEFLC-1^06244005.0228604 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
327390984-51962-DETAIL-07_24_2024-GO95MLD-1^06244005.0229601 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
350669135-33872-DETAIL-07_17_2024-GO95HV-1^06244005.0229640 | OTHER | FHCA | Distribution | 2024-07-17 | 2029-07-17 | 3
684007844-66464-DETAIL-06_24_2024-GO95MLD-1^06244005.0230000 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
403467809-30789-DETAIL-06_24_2024-GO95MLD-1^06244005.0230001 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
403467809-30789-DETAIL-06_24_2024-GRDRODHI-1^06244005.0230001 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
318511531-73751-DETAIL-06_24_2024-GO95HV-1^06244005.0230103 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
477866860-17589-DETAIL-06_24_2024-GO95MLD-1^06244005.0230300 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
657787963-15539-DETAIL-07_03_2024-GO95MLD-1^06244005.0230401 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
657787963-15539-DETAIL-07_03_2024-SVCDEFLC-1^06244005.0230401 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
185598473-5539-DETAIL-07_03_2024-GO95MLD-1^06244005.0230402 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
501333150-12289-DETAIL-07_03_2024-GO95MLD-1^06244005.0230500 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
703600011-6539-DETAIL-07_03_2024-GO95MLD-1^06244005.0230603 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
821829974-69379-DETAIL-07_03_2024-GO95MLD-1^06244005.0230841 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
821829974-69379-DETAIL-07_03_2024-GRDRODHI-1^06244005.0230841 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
821829974-69379-DETAIL-07_03_2024-GRDRODHI-2^06244005.0230841 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
902343143-19539-DETAIL-07_03_2024-GO95MLD-1^06244005.0230900 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
902343143-19539-DETAIL-07_03_2024-SVCDEFLC-1^06244005.0230900 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
657880561-98099-DETAIL-06_24_2024-GO95HV-1^06244005.0231101 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
553727951-43539-DETAIL-06_24_2024-GO95HV-1^06244005.0231102 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
339535250-69439-DETAIL-06_24_2024-GO95MLD-1^06244005.0231301 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
850018081-9439-DETAIL-07_02_2024-GO95MLD-1^06244005.0231600 | OTHER | FHCA | Distribution | 2024-07-02 | 2029-07-02 | 3
509758203-67539-DETAIL-07_02_2024-GO95MLD-1^06244005.0231700 | OTHER | FHCA | Distribution | 2024-07-02 | 2029-07-02 | 3
753507011-82899-DETAIL-07_02_2024-GO95MLD-1^06244005.0231704 | OTHER | FHCA | Distribution | 2024-07-02 | 2027-07-02 | 2
753507011-82899-DETAIL-07_02_2024-GO95TCH-1^06244005.0231704 | OTHER | FHCA | Distribution | 2024-07-02 | 2027-07-02 | 2
895491413-58189-DETAIL-07_03_2024-GO95HV-1^06244005.0231900 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
90122503-80539-DETAIL-06_24_2024-GO95MLD-1^06244005.0232200 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
602755541-40539-DETAIL-06_24_2024-GO95HV-1^06244005.0232202 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
982697453-89439-DETAIL-06_26_2024-GO95MLD-1^06244005.0232300 | OTHER | FHCA | Distribution | 2024-06-26 | 2029-06-26 | 3
86855811-99439-DETAIL-06_26_2024-GO95MLD-1^06244005.0232301 | OTHER | FHCA | Distribution | 2024-06-26 | 2029-06-26 | 3
94355955-58439-DETAIL-06_26_2024-GO95MLD-1^06244005.0232542 | OTHER | FHCA | Distribution | 2024-06-26 | 2029-06-26 | 3
210191290-53290-DETAIL-06_26_2024-GO95HV-1^06244005.0232610 | OTHER | FHCA | Distribution | 2024-06-26 | 2029-06-26 | 3
210191290-53290-DETAIL-06_26_2024-GO95MLD-1^06244005.0232610 | OTHER | FHCA | Distribution | 2024-06-26 | 2029-06-26 | 3
210191290-53290-DETAIL-06_26_2024-GUYHINS-1^06244005.0232610 | ANCHOR/GUY | FHCA | Distribution | 2024-06-26 | 2027-06-26 | 2
883198053-72599-DETAIL-07_05_2024-SVCDEFLC-1^06244005.0232800 | OTHER | FHCA | Distribution | 2024-07-05 | 2027-07-05 | 2
540008974-73339-DETAIL-06_24_2024-GO95MLD-1^06244005.0233040 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
659415073-35989-DETAIL-06_24_2024-GO95MLD-1^06244005.0233100 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
688299490-12590-DETAIL-06_24_2024-SVCDEFLC-1^06244005.0233200 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
736035053-5339-DETAIL-06_24_2024-GO95MLD-1^06244005.0233300 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
736035053-5339-DETAIL-06_24_2024-SVCDEFLC-1^06244005.0233300 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
736035053-5339-DETAIL-06_24_2024-SVCDEFLC-2^06244005.0233300 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
23655164-22599-DETAIL-06_24_2024-GO95MLD-1^06244005.0233341 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
958536141-32639-DETAIL-06_26_2024-GUYNOINS-1^06244005.0233704 | ANCHOR/GUY | FHCA | Distribution | 2024-06-26 | 2027-06-26 | 2
561011633-2639-DETAIL-07_03_2024-GO95MLD-1^06244005.0233800 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
195440011-24599-DETAIL-07_03_2024-GO95MLD-1^06244005.0233901 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
180111444-43339-DETAIL-06_24_2024-GO95BLTC-1^06244005.0234040 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
180111444-43339-DETAIL-06_24_2024-GO95MLD-1^06244005.0234040 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
780551433-71299-DETAIL-06_24_2024-GO95HV-1^06244005.0234201 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
283743131-94289-DETAIL-06_25_2024-GO95MLD-1^06244005.0234400 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
977891505-85805-DETAIL-07_03_2024-GO95MLD-1^06244005.0234541 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
690064371-9889-DETAIL-07_03_2024-GO95HV-1^06244005.0234601 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
138016491-78402-DETAIL-07_03_2024-GO95HV-1^06244005.0234603 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
844917181-66089-DETAIL-07_03_2024-CUTOUTAR-1^06244005.0234703 | LIGHTNING ARRESTER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
526314881-5881-DETAIL-06_26_2024-GO95MLD-1^06244005.0234840 | OTHER | FHCA | Distribution | 2024-06-26 | 2027-06-26 | 2
994932021-26589-DETAIL-07_03_2024-GO95MLD-1^06244005.0234903 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
994932021-26589-DETAIL-07_03_2024-SVCDEFLC-1^06244005.0234903 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
950403993-44993-DETAIL-06_24_2024-GO95HV-1^06244005.0235200 | OTHER | FHCA | Distribution | 2024-06-24 | 2029-06-24 | 3
950403993-44993-DETAIL-06_24_2024-GO95MLD-1^06244005.0235200 | OTHER | FHCA | Distribution | 2024-06-24 | 2027-06-24 | 2
599418563-19339-DETAIL-06_25_2024-GO95MLD-1^06244005.0235600 | OTHER | FHCA | Distribution | 2024-06-25 | 2029-06-25 | 3
939637863-88339-DETAIL-06_25_2024-GO95HV-1^06244005.0235603 | OTHER | FHCA | Distribution | 2024-06-25 | 2029-06-25 | 3
762555473-29339-DETAIL-06_25_2024-GO95MLD-1^06244005.0235701 | OTHER | FHCA | Distribution | 2024-06-25 | 2029-06-25 | 3
670661664-34439-DETAIL-07_03_2024-GO95MLD-1^06244005.0235841 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
384923354-92479-DETAIL-07_03_2024-GO95MLD-1^06244005.0235842 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
384923354-92479-DETAIL-07_03_2024-GRDRODHI-1^06244005.0235842 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
384923354-92479-DETAIL-07_03_2024-GRDRODHI-2^06244005.0235842 | OTHER | FHCA | Distribution | 2024-07-03 | 2027-07-03 | 2
773508891-92339-DETAIL-06_25_2024-GO95HV-1^06244005.0236001 | OTHER | FHCA | Distribution | 2024-06-25 | 2029-06-25 | 3
773508891-92339-DETAIL-06_25_2024-GO95MLD-1^06244005.0236001 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
814330843-41099-DETAIL-06_25_2024-GO95MLD-1^06244005.0236600 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
959186661-45989-DETAIL-07_03_2024-GO95HV-1^06244005.0236900 | OTHER | FHCA | Distribution | 2024-07-03 | 2029-07-03 | 3
246153901-32089-DETAIL-06_25_2024-GO95MLD-1^06244005.0237000 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
246153901-32089-DETAIL-06_25_2024-GRDRODHI-1^06244005.0237000 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
952921883-58239-DETAIL-06_25_2024-GO95MLD-1^06244005.0237301 | OTHER | FHCA | Distribution | 2024-06-25 | 2029-06-25 | 3
952921883-58239-DETAIL-06_25_2024-SVCDEFLC-1^06244005.0237301 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
6115159-56989-DETAIL-06_25_2024-GO95MLD-1^06244005.0237305 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
111215430-99339-DETAIL-06_20_2024-GO95HV-1^06244005.0237705 | OTHER | FHCA | Distribution | 2024-06-20 | 2029-06-20 | 3
623354981-30339-DETAIL-06_25_2024-GO95HV-1^06244005.0238400 | OTHER | FHCA | Distribution | 2024-06-25 | 2029-06-25 | 3
83084111-65602-DETAIL-06_25_2024-GO95HV-1^06244005.0238401 | OTHER | FHCA | Distribution | 2024-06-25 | 2029-06-25 | 3
308203423-59339-DETAIL-06_20_2024-SVCDEFLC-1^06244005.0238600 | OTHER | FHCA | Distribution | 2024-06-20 | 2027-06-20 | 2
25115883-18699-DETAIL-06_25_2024-SVCENTCO-1^06244005.0239000 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
100017283-16512-DETAIL-06_25_2024-SVCDEFLC-1^06244005.0239100 | OTHER | FHCA | Distribution | 2024-06-25 | 2027-06-25 | 2
119861313-43312-DETAIL-06_20_2024-GO95MLD-1^06244005.0239400 | OTHER | FHCA | Distribution | 2024-06-20 | 2027-06-20 | 2
724404193-59239-DETAIL-06_20_2024-GO95HV-1^06244005.0239402 | OTHER | FHCA | Distribution | 2024-06-20 | 2029-06-20 | 3
774640561-89009-DETAIL-06_12_2024-GO95MLD-1^06244005.0241100 | OTHER | FHCA | Distribution | 2024-06-12 | 2027-06-12 | 2
774640561-89009-DETAIL-06_12_2024-GRDRODHI-1^06244005.0241100 | OTHER | FHCA | Distribution | 2024-06-12 | 2027-06-12 | 2
774640561-89009-DETAIL-06_12_2024-GRDRODHI-2^06244005.0241100 | OTHER | FHCA | Distribution | 2024-06-12 | 2027-06-12 | 2
775880721-77939-DETAIL-06_12_2024-GO95MLD-1^06244005.0242100 | OTHER | FHCA | Distribution | 2024-06-12 | 2027-06-12 | 2
698668040-60039-DETAIL-06_12_2024-GO95MLD-1^06244005.0243701 | OTHER | FHCA | Distribution | 2024-06-12 | 2027-06-12 | 2
698668040-60039-AUDIT-07_01_2024-RISEGRD-1^06244005.0243701 | OTHER | FHCA | Distribution | 2024-07-01 | 2027-07-01 | 2
342739996-40096-DETAIL-06_12_2024-GO95HV-1^06244005.0247800 | OTHER | FHCA | Distribution | 2024-06-12 | 2029-06-12 | 3
785046981-37939-DETAIL-06_12_2024-GO95MLD-1^06244005.0248940 | OTHER | FHCA | Distribution | 2024-06-12 | 2029-06-12 | 3
785046981-37939-DETAIL-06_12_2024-GO95MLD-2^06244005.0248940 | OTHER | FHCA | Distribution | 2024-06-12 | 2029-06-12 | 3
869072013-30889-DETAIL-07_24_2024-GO95HV-1^06244005.0250000 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
470074563-71409-DETAIL-07_15_2024-GO95MLD-1^06244005.0250400 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
931120321-1321-DETAIL-07_15_2024-GO95HV-1^06244005.0250500 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
423962321-3321-DETAIL-07_15_2024-GO95BLTC-1^06244005.0250501 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
437288913-44899-DETAIL-07_24_2024-GO95BLTC-1^06244005.0251001 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
437288913-44899-DETAIL-07_24_2024-GO95MLD-1^06244005.0251001 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
437288913-44899-DETAIL-07_24_2024-SVCDEFLC-1^06244005.0251001 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
632236123-34699-DETAIL-07_24_2024-GO95MLD-1^06244005.0251002 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
199007304-3822-DETAIL-07_15_2024-GO95HV-1^06244005.0251200 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
354973414-64669-DETAIL-07_15_2024-GO95MLD-1^06244005.0252300 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
659614385-35385-DETAIL-07_15_2024-GO95MLD-1^06244005.0253300 | OTHER | FHCA | Distribution | 2024-07-15 | 2027-07-15 | 2
887369603-37822-ADMIN-07_15_2024-ABNDEQPM-1^06244005.0254700 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
226682573-32039-DETAIL-07_15_2024-GO95HV-1^06244005.0254702 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
735223493-55669-DETAIL-07_15_2024-GO95HV-1^06244005.0255500 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
611266373-56269-DETAIL-07_15_2024-GO95MLD-1^06244005.0256000 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
743825824-80109-DETAIL-07_15_2024-GO95MLD-1^06244005.0256800 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
587096473-62899-DETAIL-07_11_2024-GO95HV-1^06244005.0260001 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
587096473-62899-DETAIL-07_11_2024-GO95MLD-1^06244005.0260001 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
341247693-71839-DETAIL-07_11_2024-GO95HV-1^06244005.0260200 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
45864493-67089-DETAIL-07_11_2024-GO95HV-1^06244005.0260202 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
425270833-91839-DETAIL-07_11_2024-GO95MLD-1^06244005.0260301 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
78139103-76479-DETAIL-07_11_2024-GO95MLD-1^06244005.0260403 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
959257213-73839-DETAIL-07_11_2024-GO95HV-1^06244005.0260500 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
764548983-24099-DETAIL-07_11_2024-GO95HV-1^06244005.0260700 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
764548983-24099-DETAIL-07_11_2024-GO95MLD-1^06244005.0260700 | OTHER | FHCA | Distribution | 2024-07-11 | 2027-07-11 | 2
887327363-4322-DETAIL-07_09_2024-SVCROAD-1^06244005.0260902 | OTHER | FHCA | Distribution | 2024-07-09 | 2027-07-09 | 2
610655163-54599-DETAIL-07_17_2024-GO95MLD-1^06244005.0262901 | OTHER | FHCA | Distribution | 2024-07-17 | 2027-07-17 | 2
525658313-52979-DETAIL-07_11_2024-GO95HV-1^06244005.0263400 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
965513964-29939-DETAIL-07_15_2024-GO95MLD-1^06244005.0264940 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
545670064-66689-DETAIL-07_15_2024-GO95MLD-1^06244005.0264941 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
889994054-1739-DETAIL-07_24_2024-GO95MLD-1^06244005.0268140 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
536903703-38922-DETAIL-07_15_2024-ENCHRW-1^06244005.0269201 | OTHER | FHCA | Distribution | 2024-07-15 | 2027-07-15 | 2
832312553-48522-DETAIL-07_15_2024-GO95MLD-1^06244005.0269202 | OTHER | FHCA | Distribution | 2024-07-15 | 2029-07-15 | 3
320635933-22899-DETAIL-07_10_2024-GO95MLD-1^06244005.0271900 | OTHER | FHCA | Distribution | 2024-07-10 | 2027-07-10 | 2
890228423-29499-DETAIL-07_10_2024-GO95MLD-1^06244005.0271902 | OTHER | FHCA | Distribution | 2024-07-10 | 2027-07-10 | 2
292361406-51098-DETAIL-07_10_2024-GO95HV-1^06244005.0273900 | OTHER | FHCA | Distribution | 2024-07-10 | 2029-07-10 | 3
183134593-49239-DETAIL-07_09_2024-GO95HV-1^06244005.0273901 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
453175653-43139-DETAIL-07_16_2024-GO95MLD-1^06244005.0274002 | OTHER | FHCA | Distribution | 2024-07-16 | 2027-07-16 | 2
453175653-43139-DETAIL-07_16_2024-SVCENTCO-1^06244005.0274002 | OTHER | FHCA | Distribution | 2024-07-16 | 2027-07-16 | 2
446740964-29462-DETAIL-07_16_2024-GUYHINS-1^06244005.0274100 | ANCHOR/GUY | FHCA | Distribution | 2024-07-16 | 2027-07-16 | 2
489857570-89261-DETAIL-07_16_2024-GO95HV-1^06244005.0275202 | OTHER | FHCA | Distribution | 2024-07-16 | 2029-07-16 | 3
248423074-23139-DETAIL-07_16_2024-GO95HV-1^06244005.0275203 | OTHER | FHCA | Distribution | 2024-07-16 | 2029-07-16 | 3
245667494-70189-DETAIL-07_16_2024-GO95TCH-1^06244005.0275301 | OTHER | FHCA | Distribution | 2024-07-16 | 2027-07-16 | 2
245667494-70189-DETAIL-07_16_2024-GUYHINS-1^06244005.0275301 | ANCHOR/GUY | FHCA | Distribution | 2024-07-16 | 2027-07-16 | 2
243463184-62989-DETAIL-07_16_2024-GO95MLD-1^06244005.0275302 | OTHER | FHCA | Distribution | 2024-07-16 | 2029-07-16 | 3
901549923-50339-DETAIL-07_09_2024-GO95HV-1^06244005.0276900 | OTHER | FHCA | Distribution | 2024-07-09 | 2029-07-09 | 3
434886154-40489-DETAIL-07_17_2024-RISEGRD-1^06244005.0277000 | OTHER | FHCA | Distribution | 2024-07-17 | 2027-07-17 | 2
434886154-40489-DETAIL-07_17_2024-RISEGRD-2^06244005.0277000 | OTHER | FHCA | Distribution | 2024-07-17 | 2027-07-17 | 2
603332934-40139-DETAIL-07_17_2024-GO95MLD-1^06244005.0277002 | OTHER | FHCA | Distribution | 2024-07-17 | 2029-07-17 | 3
432975929-61339-DETAIL-07_11_2024-GO95MLD-1^06244005.0279401 | OTHER | FHCA | Distribution | 2024-07-11 | 2029-07-11 | 3
189533783-16239-DETAIL-07_17_2024-GO95HV-1^06244005.0281100 | OTHER | FHCA | Distribution | 2024-07-17 | 2029-07-17 | 3
536962883-26239-DETAIL-07_17_2024-GO95HV-1^06244005.0281101 | OTHER | FHCA | Distribution | 2024-07-17 | 2029-07-17 | 3
195803524-78189-DETAIL-07_17_2024-GO95MLD-1^06244005.0282101 | OTHER | FHCA | Distribution | 2024-07-17 | 2027-07-17 | 2
731465714-55239-DETAIL-07_17_2024-GO95HV-1^06244005.0282103 | OTHER | FHCA | Distribution | 2024-07-17 | 2029-07-17 | 3
731465714-55239-DETAIL-07_17_2024-GO95MLD-1^06244005.0282103 | OTHER | FHCA | Distribution | 2024-07-17 | 2029-07-17 | 3
706762883-63239-DETAIL-07_17_2024-GO95HV-1^06244005.0282300 | OTHER | FHCA | Distribution | 2024-07-17 | 2029-07-17 | 3
150503843-43489-AUDIT-08_27_2024-ABNDEQPM-1^06244005.0283305 | OTHER | FHCA | Distribution | 2024-08-27 | 2029-08-27 | 3
661237183-31239-DETAIL-07_17_2024-GO95HV-1^06244005.0284201 | OTHER | FHCA | Distribution | 2024-07-17 | 2029-07-17 | 3
661237183-31239-DETAIL-07_17_2024-GO95MLD-1^06244005.0284201 | OTHER | FHCA | Distribution | 2024-07-17 | 2027-07-17 | 2
822647014-24799-DETAIL-07_17_2024-GO95MLD-1^06244005.0284500 | OTHER | FHCA | Distribution | 2024-07-17 | 2027-07-17 | 2
727353023-57239-AUDIT-08_27_2024-GO95MLD-1^06244005.0288900 | OTHER | FHCA | Distribution | 2024-08-27 | 2029-08-27 | 3
562100713-97239-DETAIL-07_10_2024-ENCHRW-1^06244005.0289900 | OTHER | FHCA | Distribution | 2024-07-10 | 2027-07-10 | 2
562100713-97239-DETAIL-07_10_2024-GO95MLD-1^06244005.0289900 | OTHER | FHCA | Distribution | 2024-07-10 | 2027-07-10 | 2
653800393-34979-DETAIL-07_31_2024-GO95MLD-1^06244005.0292740 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
803418863-4339-DETAIL-08_05_2024-GO95HV-1^06244005.0323001 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
892629604-11199-DETAIL-08_05_2024-GO95MLD-1^06244005.0324701 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
72967373-13339-DETAIL-08_05_2024-GO95HV-1^06244005.0325200 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
964367613-66339-DETAIL-08_05_2024-GO95HV-1^06244005.0325601 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
367701083-68339-DETAIL-08_06_2024-GO95HV-1^06244005.0329900 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
356639328-48339-DETAIL-08_06_2024-GO95HV-1^06244005.0329901 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
124573260-48769-DETAIL-07_31_2024-GO95BLTC-1^06244005.0333900 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
124573260-48769-DETAIL-07_31_2024-GO95HV-1^06244005.0333900 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
472355173-88799-DETAIL-07_31_2024-GRDRODHI-1^06244005.0337903 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
318655413-10239-DETAIL-07_31_2024-GO95HV-1^06244005.0337904 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
135513444-20079-DETAIL-07_31_2024-GO95MLD-1^06244005.0338900 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
574229713-28399-DETAIL-07_31_2024-GO95MLD-1^06244005.0339901 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
520386313-88479-DETAIL-07_31_2024-GO95MLD-1^06244005.0339902 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
277186903-86299-DETAIL-07_31_2024-GO95HV-1^06244005.0340901 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
277186903-86299-DETAIL-07_31_2024-GO95MLD-1^06244005.0340901 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
277186903-86299-DETAIL-07_31_2024-SVCENTCO-1^06244005.0340901 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
524380824-34162-DETAIL-07_31_2024-GO95MLD-1^06244005.0340940 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
548619593-84779-DETAIL-07_31_2024-GO95MLD-1^06244005.0341900 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
94170193-8139-DETAIL-07_31_2024-GO95HV-1^06244005.0342901 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
688303993-63139-DETAIL-07_31_2024-GO95MLD-1^06244005.0343900 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
822320650-62650-DETAIL-07_30_2024-GO95MLD-1^06244005.0344901 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
837431313-9039-DETAIL-07_30_2024-GO95HV-1^06244005.0345801 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
922220703-80139-DETAIL-07_31_2024-GUYHINS-1^06244005.0346902 | ANCHOR/GUY | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
511605823-93089-DETAIL-07_31_2024-GO95MLD-1^06244005.0346903 | OTHER | FHCA | Distribution | 2024-07-31 | 2027-07-31 | 2
702410804-66469-DETAIL-07_25_2024-ABNDEQPM-1^06244005.0347001 | OTHER | FHCA | Distribution | 2024-07-25 | 2029-07-25 | 3
542698743-48039-DETAIL-07_25_2024-GO95HV-1^06244005.0347901 | OTHER | FHCA | Distribution | 2024-07-25 | 2029-07-25 | 3
562211969-44099-DETAIL-07_25_2024-ABNDEQPM-1^06244005.0349200 | OTHER | FHCA | Distribution | 2024-07-25 | 2029-07-25 | 3
646571054-69189-DETAIL-07_25_2024-SVCDEFLC-1^06244005.0349301 | OTHER | FHCA | Distribution | 2024-07-25 | 2027-07-25 | 2
97119213-83589-DETAIL-07_30_2024-GO95MLD-1^06244005.0349601 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
795303409-69599-DETAIL-07_30_2024-SVCDEFLC-1^06244005.0349602 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
606420406-47879-DETAIL-07_25_2024-GRDRODHI-1^06244005.0350601 | OTHER | FHCA | Distribution | 2024-07-25 | 2027-07-25 | 2
699915666-6879-DETAIL-07_25_2024-SVCDEFLC-1^06244005.0350801 | OTHER | FHCA | Distribution | 2024-07-25 | 2027-07-25 | 2
658523276-59989-DETAIL-07_25_2024-GO95MLD-1^06244005.0350802 | OTHER | FHCA | Distribution | 2024-07-25 | 2029-07-25 | 3
658523276-59989-DETAIL-07_25_2024-GRDRODHI-1^06244005.0350802 | OTHER | FHCA | Distribution | 2024-07-25 | 2027-07-25 | 2
187910528-66289-DETAIL-07_30_2024-GO95MLD-1^06244005.0352201 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
649377678-3739-DETAIL-07_30_2024-GO95HV-1^06244005.0353101 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
69336988-61739-DETAIL-07_30_2024-GO95MLD-1^06244005.0354100 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
388192450-51328-DETAIL-07_30_2024-GO95MLD-1^06244005.0354301 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
275729128-26039-DETAIL-07_30_2024-GUYHINS-1^06244005.0354700 | ANCHOR/GUY | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
315515856-94039-DETAIL-07_25_2024-GO95HV-1^06244005.0354903 | OTHER | FHCA | Distribution | 2024-07-25 | 2029-07-25 | 3
616602506-25699-DETAIL-07_25_2024-SVCDEFLC-1^06244005.0354904 | OTHER | FHCA | Distribution | 2024-07-25 | 2027-07-25 | 2
810408178-96899-DETAIL-07_30_2024-GO95HV-1^06244005.0355100 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
349835968-90899-DETAIL-07_30_2024-GO95HV-1^06244005.0355202 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
349835968-90899-DETAIL-07_30_2024-GO95MLD-1^06244005.0355202 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
136902208-84389-DETAIL-07_30_2024-GRDRODHI-1^06244005.0355400 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
136902208-84389-DETAIL-07_30_2024-GRDRODHI-2^06244005.0355400 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
785155288-72039-DETAIL-07_30_2024-GO95MLD-1^06244005.0355401 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
785155288-72039-DETAIL-07_30_2024-GRDRODHI-1^06244005.0355401 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
785155288-72039-DETAIL-07_30_2024-GRDRODHI-2^06244005.0355401 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
944068876-48679-DETAIL-07_30_2024-SVCDEFLC-1^06244005.0355900 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
211298099-37639-DETAIL-07_30_2024-GUYHINS-1^06244005.0357400 | ANCHOR/GUY | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
14502329-6639-DETAIL-07_30_2024-GO95HV-1^06244005.0358400 | OTHER | FHCA | Distribution | 2024-07-30 | 2029-07-30 | 3
844961469-95639-DETAIL-07_30_2024-GO95MLD-1^06244005.0359200 | OTHER | FHCA | Distribution | 2024-07-30 | 2027-07-30 | 2
106169559-54889-DETAIL-07_24_2024-GO95MLD-1^06244005.0359500 | OTHER | FHCA | Distribution | 2024-07-24 | 2029-07-24 | 3
553457769-289-DETAIL-07_24_2024-GO95MLD-1^06244005.0359801 | OTHER | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
115856443-8479-DETAIL-08_06_2024-GUYHINS-1^06244005.0364200 | ANCHOR/GUY | FHCA | Distribution | 2024-08-06 | 2027-08-06 | 2
76900723-4639-DETAIL-08_06_2024-INSULDMG-1^06244005.0365000 | INSULATOR AND BUSHING | FHCA | Distribution | 2024-08-06 | 2027-08-06 | 2
875034205-38439-DETAIL-06_07_2023-GO95HV-1^06244006.0010600 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
567119115-97489-DETAIL-06_07_2023-ABNDEQPM-1^06244006.0010601 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
567119115-97489-DETAIL-06_07_2023-GO95HV-1^06244006.0010601 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
567119115-97489-DETAIL-06_07_2023-GO95MLD-1^06244006.0010601 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2026-06-07 | 2
116362695-88439-DETAIL-06_07_2023-GO95HV-1^06244006.0011700 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
123021895-59439-DETAIL-06_07_2023-GO95HV-1^06244006.0012800 | OTHER | CA-NON-TIER | Distribution | 2023-06-07 | 2028-06-07 | 3
969217135-13989-DETAIL-06_07_2023-GO95MLD-1^06244006.0025800 | OTHER | FHCA | Distribution | 2023-06-07 | 2028-06-07 | 3
752453159-63692-ADMIN-07_18_2024-POLETOP-1^06244006.0198140 | POLE | CA-TIER-2 | Distribution | 2024-07-18 | 2025-07-18 | 2
282112213-24249-ADMIN-09_05_2024-POLETOP-1^06244006.0257901 | POLE | FHCA | Distribution | 2024-09-05 | 2027-09-05 | 2
885020909-96852-ADMIN-06_17_2024-XARMSPCR-1^06244006.0308441 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
405242679-89952-ADMIN-07_23_2024-POLEREPL-1^06244006.0315741 | POLE | CA-TIER-2 | Distribution | 2024-07-23 | 2025-07-23 | 2
881745589-47989-ENHANCED-06_17_2024-IRSPOTOH-1^06244007.0037402 | OTHER | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
951497093-8879-DETAIL-06_13_2024-GO95MLD-1^06244007.0041000 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
12535583-97689-DETAIL-06_13_2024-GO95MLD-1^06244007.0041002 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
424597133-10249-DETAIL-06_13_2024-GO95MLD-1^06244007.0041100 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
217615393-41249-DETAIL-06_13_2024-GO95MLD-1^06244007.0042400 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
962793173-81989-DETAIL-06_13_2024-GO95MLD-1^06244007.0043400 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
31928363-8149-DETAIL-06_13_2024-GO95HV-1^06244007.0044201 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
134556833-58789-DETAIL-06_13_2024-GO95MLD-1^06244007.0045200 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
53069834-38149-DETAIL-06_13_2024-GO95MLD-1^06244007.0045302 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
760299513-80199-DETAIL-06_13_2024-GO95HV-1^06244007.0045400 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
760299513-80199-DETAIL-06_13_2024-GO95MLD-1^06244007.0045400 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
894066504-4799-DETAIL-06_13_2024-GO95MLD-1^06244007.0045500 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
361753504-17149-DETAIL-06_13_2024-RISEGRD-1^06244007.0045501 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
709110043-38479-DETAIL-06_13_2024-GO95MLD-1^06244007.0046409 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
355590733-84733-DETAIL-06_13_2024-SVCROAD-1^06244007.0046500 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
181895024-55579-DETAIL-06_13_2024-GO95MLD-1^06244007.0046501 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
181895024-55579-DETAIL-06_13_2024-GUYHINS-1^06244007.0046501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
92886804-35149-DETAIL-06_13_2024-GO95MLD-1^06244007.0047400 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
483367903-14999-DETAIL-06_19_2024-GO95BLTC-1^06244007.0047402 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
600300584-34149-ADMIN-06_24_2024-POLEREPL-1^06244007.0047503 | POLE | CA-TIER-2 | Distribution | 2024-06-24 | 2025-06-24 | 2
600300584-34149-ADMIN-06_27_2024-GUYSLACK-1^06244007.0047503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-27 | 2025-06-27 | 2
600300584-34149-ADMIN-06_27_2024-XARMSPCR-1^06244007.0047503 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-27 | 2025-06-27 | 2
662482155-33155-DETAIL-06_13_2024-GO95MLD-1^06244007.0047504 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2027-06-13 | 2
789428851-61979-DETAIL-06_19_2024-GRDRODHI-1^06244007.0081300 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2027-06-19 | 2
521914780-95079-DETAIL-06_19_2024-GO95MLD-1^06244007.0081302 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2027-06-19 | 2
521914780-95079-DETAIL-06_19_2024-GUYHINS-1^06244007.0081302 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-19 | 2027-06-19 | 2
521914780-95079-DETAIL-06_19_2024-SVCWIND-1^06244007.0081302 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2027-06-19 | 2
892363530-4449-DETAIL-06_13_2024-POLETOP-1^06244007.0087601 | POLE | CA-TIER-2 | Distribution | 2024-06-13 | 2025-06-13 | 2
58788620-18899-DETAIL-06_13_2024-GO95MLD-1^06244007.0088702 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
32684610-22399-DETAIL-06_13_2024-POLETOP-1^06244007.0089801 | POLE | CA-TIER-2 | Distribution | 2024-06-13 | 2025-06-13 | 2
438924310-94452-DETAIL-06_13_2024-GO95MLD-1^06244007.0089802 | OTHER | CA-TIER-2 | Distribution | 2024-06-13 | 2029-06-13 | 3
624598134-82522-DETAIL-07_12_2023-GO95MLD-1^06244008.0228100 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
75410344-65599-DETAIL-07_12_2023-GO95MLD-1^06244008.0228200 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
982669814-13332-DETAIL-07_12_2023-RISEGRD-1^06244008.0229000 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
153432064-24789-DETAIL-07_12_2023-GO95HV-1^06244008.0271300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
153432064-24789-DETAIL-07_12_2023-GO95MLD-1^06244008.0271300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
153432064-24789-DETAIL-07_12_2023-SVCDEFLC-1^06244008.0271300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
108056934-22122-DETAIL-07_13_2023-GO95MLD-1^06244008.0271600 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
276580202-28010-DETAIL-07_13_2023-GO95HV-1^06244008.0272202 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
309761399-43399-DETAIL-07_12_2023-ENCHRW-1^06244008.0274400 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
76433054-26129-DETAIL-07_12_2023-GO95MLD-1^06244008.0274501 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
746805014-58722-DETAIL-07_12_2023-GO95MLD-1^06244008.0276701 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
746805014-58722-DETAIL-07_12_2023-SVCDEFLC-1^06244008.0276701 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
881536115-31932-DETAIL-07_12_2023-GO95MLD-1^06244008.0276702 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
695613514-47129-AUDIT-08_29_2023-GO95HV-1^06244008.0277700 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2028-08-29 | 3
919646164-97129-DETAIL-07_12_2023-GO95TCH-1^06244008.0279700 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
52167894-63129-DETAIL-07_11_2023-SVCDEFLC-1^06244008.0281004 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
141595274-27532-DETAIL-07_13_2023-GO95MLD-1^06244008.0281100 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
141595274-27532-DETAIL-07_13_2023-RISEGRD-1^06244008.0281100 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
626656134-45032-DETAIL-07_11_2023-GO95MLD-1^06244008.0285100 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
760034954-42622-DETAIL-07_11_2023-GO95HV-1^06244008.0285103 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
272726594-61669-DETAIL-07_12_2023-GO95MLD-1^06244008.0286100 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
35136124-35129-DETAIL-07_12_2023-GO95HV-1^06244008.0289300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
35136124-35129-DETAIL-07_12_2023-GO95MLD-1^06244008.0289300 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
488474276-56972-DETAIL-07_10_2023-GO95HV-1^06244008.0290200 | OTHER | FHCA | Distribution | 2023-07-10 | 2028-07-10 | 3
488474276-56972-DETAIL-07_10_2023-GO95MLD-1^06244008.0290200 | OTHER | FHCA | Distribution | 2023-07-10 | 2028-07-10 | 3
589235276-55972-DETAIL-07_10_2023-GO95HV-1^06244008.0290201 | OTHER | FHCA | Distribution | 2023-07-10 | 2028-07-10 | 3
730405726-61672-DETAIL-07_11_2023-GO95MLD-1^06244008.0291000 | OTHER | FHCA | Distribution | 2023-07-11 | 2026-07-11 | 2
118042495-90069-DETAIL-07_11_2023-GO95HV-1^06244008.0291001 | OTHER | FHCA | Distribution | 2023-07-11 | 2028-07-11 | 3
118042495-90069-DETAIL-07_11_2023-GO95MLD-1^06244008.0291001 | OTHER | FHCA | Distribution | 2023-07-11 | 2028-07-11 | 3
887188586-47972-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0291401 | OTHER | FHCA | Distribution | 2023-07-11 | 2028-07-11 | 3
912352071-60213-DETAIL-07_11_2023-GO95MLD-1^06244008.0292000 | OTHER | FHCA | Distribution | 2023-07-11 | 2026-07-11 | 2
455765871-79669-DETAIL-07_11_2023-GO95MLD-1^06244008.0292001 | OTHER | FHCA | Distribution | 2023-07-11 | 2026-07-11 | 2
639493656-46772-DETAIL-07_11_2023-GO95MLD-1^06244008.0293000 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2026-07-11 | 2
508383371-39202-DETAIL-07_10_2023-GO95MLD-1^06244008.0302001 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
508383371-39202-AUDIT-08_29_2023-GO95TCH-1^06244008.0302001 | OTHER | FHCA | Distribution | 2023-08-29 | 2026-08-29 | 2
812463028-14028-DETAIL-07_10_2023-GO95HV-1^06244008.0304001 | OTHER | FHCA | Distribution | 2023-07-10 | 2028-07-10 | 3
812463028-14028-DETAIL-07_10_2023-GO95MLD-1^06244008.0304001 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
812463028-14028-DETAIL-07_10_2023-GO95TCH-1^06244008.0304001 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
595593091-63502-DETAIL-07_10_2023-SVCDEFLC-1^06244008.0305100 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
965669201-41389-DETAIL-07_10_2023-GO95MLD-1^06244008.0306200 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
965669201-41389-DETAIL-07_10_2023-GO95TCH-1^06244008.0306200 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
495919641-72102-DETAIL-07_10_2023-GO95MLD-1^06244008.0306202 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
495919641-72102-DETAIL-07_10_2023-GUYNOINS-1^06244008.0306202 | ANCHOR/GUY | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
495919641-72102-DETAIL-07_10_2023-GUYNOINS-2^06244008.0306202 | ANCHOR/GUY | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
557935071-1402-DETAIL-07_10_2023-GO95MLD-1^06244008.0307201 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
543071811-10479-DETAIL-07_10_2023-GO95MLD-1^06244008.0307202 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
97369351-10848-DETAIL-07_10_2023-GO95MLD-1^06244008.0307204 | OTHER | FHCA | Distribution | 2023-07-10 | 2026-07-10 | 2
670634851-39102-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0308000 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
222074421-89602-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0309000 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
767072231-25702-DETAIL-07_11_2023-GO95MLD-1^06244008.0309001 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
823070401-48502-DETAIL-07_11_2023-GO95MLD-1^06244008.0309002 | OTHER | CA-TIER-2 | Distribution | 2023-07-11 | 2028-07-11 | 3
612201177-14669-DETAIL-07_18_2023-SVCDEFLC-1^06244008.0310200 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
451122436-47982-DETAIL-07_18_2023-GO95MLD-1^06244008.0310300 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
451122436-47982-DETAIL-07_18_2023-GO95TCH-1^06244008.0310300 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2026-07-18 | 2
451122436-47982-DETAIL-01_04_2024-POLEREPL-1^06244008.0310300 | POLE | CA-TIER-2 | Distribution | 2024-01-04 | 2025-01-04 | 2
679260385-56385-DETAIL-06_28_2023-GO95MLD-1^06244008.0310901 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
692130406-40272-DETAIL-07_05_2023-GO95HV-1^06244008.0311900 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
692130406-40272-DETAIL-07_05_2023-GO95MLD-1^06244008.0311900 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
909240896-40582-DETAIL-06_28_2023-GO95MLD-1^06244008.0312800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
978171386-55482-DETAIL-06_28_2023-GO95HV-1^06244008.0312801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
978171386-55482-DETAIL-06_28_2023-GO95MLD-1^06244008.0312801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
425978186-13782-DETAIL-07_18_2023-GO95HV-1^06244008.0314500 | OTHER | CA-TIER-2 | Distribution | 2023-07-18 | 2028-07-18 | 3
628468697-37692-DETAIL-07_05_2023-GO95MLD-1^06244008.0316840 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
222497627-44692-DETAIL-07_05_2023-GO95MLD-1^06244008.0317840 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
610015081-29129-DETAIL-07_05_2023-GUYNOINS-1^06244008.0320700 | ANCHOR/GUY | FHCA | Distribution | 2023-07-05 | 2026-07-05 | 2
610015081-29129-DETAIL-07_05_2023-GUYNOINS-2^06244008.0320700 | ANCHOR/GUY | FHCA | Distribution | 2023-07-05 | 2026-07-05 | 2
778006186-81182-DETAIL-07_11_2023-GO95MLD-1^06244008.0320800 | OTHER | FHCA | Distribution | 2023-07-11 | 2028-07-11 | 3
105210781-95342-DETAIL-07_13_2023-GO95MLD-1^06244008.0320801 | OTHER | FHCA | Distribution | 2023-07-13 | 2026-07-13 | 2
105210781-95342-DETAIL-07_13_2023-SVCDEFLC-1^06244008.0320801 | OTHER | FHCA | Distribution | 2023-07-13 | 2026-07-13 | 2
365235786-50182-DETAIL-07_11_2023-GO95HV-1^06244008.0321900 | OTHER | FHCA | Distribution | 2023-07-11 | 2028-07-11 | 3
690819066-79282-DETAIL-07_11_2023-GO95MLD-1^06244008.0321901 | OTHER | FHCA | Distribution | 2023-07-11 | 2026-07-11 | 2
534744246-98982-DETAIL-07_05_2023-ABNDEQPM-1^06244008.0322700 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
534744246-98982-DETAIL-07_05_2023-GO95HV-1^06244008.0322700 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
114495718-49692-DETAIL-07_05_2023-GO95HV-1^06244008.0322740 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
285683546-11489-DETAIL-07_11_2023-GO95MLD-1^06244008.0322901 | OTHER | FHCA | Distribution | 2023-07-11 | 2028-07-11 | 3
180278108-98692-DETAIL-07_05_2023-GO95HV-1^06244008.0323740 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
341679651-51232-ADMIN-07_19_2024-POLEREPL-1^06244008.0324700 | POLE | CA-TIER-2 | Distribution | 2024-07-19 | 2025-07-19 | 2
508584841-14032-DETAIL-01_04_2024-POLEREPL-1^06244008.0324701 | POLE | CA-TIER-2 | Distribution | 2024-01-04 | 2025-01-04 | 2
68002941-31632-ADMIN-09_03_2024-POLEREPL-1^06244008.0325701 | POLE | CA-TIER-2 | Distribution | 2024-09-03 | 2025-09-03 | 2
631215991-84213-DETAIL-07_06_2023-GO95MLD-1^06244008.0325800 | OTHER | FHCA | Distribution | 2023-07-06 | 2028-07-06 | 3
806831391-33213-DETAIL-07_06_2023-GO95MLD-1^06244008.0325903 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2026-07-06 | 2
966738836-78129-DETAIL-07_06_2023-GO95MLD-1^06244008.0326700 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
353341967-26692-DETAIL-07_06_2023-GO95CL10-1^06244008.0326740 | OTHER | FHCA | Distribution | 2023-07-06 | 2028-07-06 | 3
353341967-26692-DETAIL-07_06_2023-GO95MLD-1^06244008.0326740 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
651114995-96172-DETAIL-07_07_2023-GO95MLD-1^06244008.0327500 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
257931995-25172-DETAIL-07_13_2023-GO95MLD-1^06244008.0327501 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
789554573-36640-ADMIN-07_24_2024-POLEREPL-1^06244008.0328300 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
844367566-27772-DETAIL-07_13_2023-GO95MLD-1^06244008.0328700 | OTHER | FHCA | Distribution | 2023-07-13 | 2026-07-13 | 2
237641808-18692-DETAIL-07_13_2023-GO95HV-1^06244008.0328740 | OTHER | FHCA | Distribution | 2023-07-13 | 2028-07-13 | 3
237641808-18692-DETAIL-07_13_2023-GO95MLD-1^06244008.0328740 | OTHER | FHCA | Distribution | 2023-07-13 | 2026-07-13 | 2
871757931-28931-ADMIN-07_24_2024-POLEREPL-1^06244008.0329301 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
624519626-65582-DETAIL-07_06_2023-GO95MLD-1^06244008.0329603 | OTHER | FHCA | Distribution | 2023-07-06 | 2028-07-06 | 3
750351146-40672-DETAIL-07_07_2023-GO95HV-1^06244008.0329800 | OTHER | FHCA | Distribution | 2023-07-07 | 2028-07-07 | 3
86518011-77632-DETAIL-07_07_2023-GRDRODHI-1^06244008.0329801 | OTHER | FHCA | Distribution | 2023-07-07 | 2026-07-07 | 2
495877901-78599-DETAIL-07_06_2023-GO95MLD-1^06244008.0329901 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
495877901-78599-DETAIL-07_06_2023-GRDRODHI-1^06244008.0329901 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
943169156-28129-DETAIL-07_06_2023-GO95MLD-1^06244008.0329902 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2028-07-06 | 3
20913590-4532-DETAIL-07_06_2023-GO95MLD-1^06244008.0329903 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2026-07-06 | 2
20913590-4532-DETAIL-07_06_2023-SVCROAD-1^06244008.0329903 | OTHER | CA-TIER-2 | Distribution | 2023-07-06 | 2026-07-06 | 2
733126964-80722-DETAIL-07_07_2023-GO95TCH-1^06244008.0330200 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
42780084-86922-DETAIL-07_07_2023-SVCDEFLC-1^06244008.0330300 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
313849664-49822-DETAIL-07_07_2023-GO95HV-1^06244008.0330401 | OTHER | FHCA | Distribution | 2023-07-07 | 2028-07-07 | 3
258099104-35962-DETAIL-07_07_2023-GO95HV-1^06244008.0330501 | OTHER | FHCA | Distribution | 2023-07-07 | 2028-07-07 | 3
258099104-35962-DETAIL-07_07_2023-GO95MLD-1^06244008.0330501 | OTHER | FHCA | Distribution | 2023-07-07 | 2026-07-07 | 2
555633876-18876-DETAIL-07_07_2023-GO95MLD-1^06244008.0330700 | OTHER | FHCA | Distribution | 2023-07-07 | 2026-07-07 | 2
583003084-87732-DETAIL-07_07_2023-GO95MLD-1^06244008.0330800 | OTHER | FHCA | Distribution | 2023-07-07 | 2028-07-07 | 3
351639544-56522-DETAIL-07_06_2023-GO95MLD-1^06244008.0330900 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
999391625-37232-DETAIL-07_07_2023-GO95TCH-1^06244008.0331700 | OTHER | FHCA | Distribution | 2023-07-07 | 2026-07-07 | 2
977974534-54222-DETAIL-07_11_2023-GO95MLD-1^06244008.0332800 | OTHER | FHCA | Distribution | 2023-07-11 | 2026-07-11 | 2
388526124-74922-DETAIL-07_11_2023-GO95HV-1^06244008.0332801 | OTHER | FHCA | Distribution | 2023-07-11 | 2028-07-11 | 3
838216285-38788-DETAIL-07_11_2023-GO95MLD-1^06244008.0333901 | OTHER | FHCA | Distribution | 2023-07-11 | 2026-07-11 | 2
838216285-38788-DETAIL-07_11_2023-SVCENTBK-1^06244008.0333901 | OTHER | FHCA | Distribution | 2023-07-11 | 2026-07-11 | 2
640311655-37132-DETAIL-07_12_2023-GO95MLD-1^06244008.0334200 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2028-07-12 | 3
584644045-17132-DETAIL-07_12_2023-GO95MLD-1^06244008.0335200 | OTHER | CA-TIER-2 | Distribution | 2023-07-12 | 2026-07-12 | 2
568229725-84132-DETAIL-07_07_2023-GO95MLD-1^06244008.0335401 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
683845615-18329-DETAIL-07_07_2023-GO95MLD-1^06244008.0335700 | OTHER | FHCA | Distribution | 2023-07-07 | 2026-07-07 | 2
937461265-87032-DETAIL-07_07_2023-GO95MLD-1^06244008.0336100 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
590352165-21129-DETAIL-07_07_2023-GO95MLD-1^06244008.0337100 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
278219754-23722-DETAIL-07_13_2023-GO95HV-1^06244008.0337700 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
892973804-22622-DETAIL-07_13_2023-GO95MLD-1^06244008.0337901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
34280515-80129-DETAIL-07_07_2023-GO95MLD-1^06244008.0338200 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
34280515-80129-DETAIL-07_07_2023-GRDRODHI-1^06244008.0338200 | OTHER | CA-TIER-2 | Distribution | 2023-07-07 | 2026-07-07 | 2
499125714-61632-ADMIN-07_19_2024-POLEREPL-1^06244008.0338700 | POLE | CA-TIER-2 | Distribution | 2024-07-19 | 2025-07-19 | 2
225223835-2699-DETAIL-07_13_2023-GO95MLD-1^06244008.0339900 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
802957764-95922-DETAIL-07_13_2023-GO95HV-1^06244008.0339902 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
728076505-2129-DETAIL-07_13_2023-GO95MLD-1^06244008.0343900 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
516876002-79498-DETAIL-07_13_2023-GO95HV-1^06244008.0343903 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
472222994-30032-DETAIL-07_13_2023-GO95MLD-1^06244008.0344800 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
755772204-50332-DETAIL-07_13_2023-GO95HV-1^06244008.0344801 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
425448705-70832-DETAIL-07_13_2023-GO95MLD-1^06244008.0344900 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
425448705-70832-DETAIL-07_13_2023-SVCENTCO-1^06244008.0344900 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
425448705-70832-ADMIN-07_19_2024-POLEREPL-1^06244008.0344900 | POLE | CA-TIER-2 | Distribution | 2024-07-19 | 2025-07-19 | 2
213748305-28732-DETAIL-07_13_2023-GO95HV-1^06244008.0344901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
213748305-28732-DETAIL-07_13_2023-GO95MLD-1^06244008.0344901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2028-07-13 | 3
213748305-28732-DETAIL-01_04_2024-POLEREPL-1^06244008.0344901 | POLE | CA-TIER-2 | Distribution | 2024-01-04 | 2025-01-04 | 2
312159038-10138-DETAIL-07_05_2023-GO95MLD-1^06244009.0019100 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
239426138-56138-DETAIL-06_28_2023-GO95MLD-1^06244009.0113301 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
940909138-69138-DETAIL-06_28_2023-GO95MLD-1^06244009.0114501 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
54014171-45582-DETAIL-07_05_2023-GO95MLD-1^06244009.0124300 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
131740002-33392-DETAIL-07_05_2023-SVCDEFLC-1^06244009.0124301 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
791374251-78382-DETAIL-07_05_2023-SVCDEFLC-1^06244009.0126301 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
175863751-73482-DETAIL-07_05_2023-GO95HV-1^06244009.0127301 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
649308171-33599-DETAIL-07_05_2023-GO95HV-1^06244009.0128400 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
716180789-10912-DETAIL-07_03_2023-GO95HV-1^06244009.0130001 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
167937019-512-DETAIL-07_05_2023-GO95MLD-1^06244009.0131401 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
889466642-11288-DETAIL-07_05_2023-GO95MLD-1^06244009.0132000 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
88173739-90312-DETAIL-07_05_2023-GO95MLD-1^06244009.0132300 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
836158199-1712-DETAIL-07_05_2023-GO95MLD-1^06244009.0132700 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
871784029-7912-DETAIL-07_05_2023-SVCDEFLC-1^06244009.0133200 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2026-07-05 | 2
759619338-438-DETAIL-06_28_2023-GO95HV-1^06244009.0143501 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
257070138-61138-DETAIL-06_28_2023-GO95MLD-1^06244009.0143800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
736127392-24492-DETAIL-06_26_2023-SVCDEFLC-1^06244009.0195001 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
416401303-83692-DETAIL-06_21_2023-GO95TCH-1^06244009.0198370 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
527472951-13423-DETAIL-06_13_2023-GO95HV-1^06244009.0225401 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
598172682-52069-DETAIL-06_28_2023-GO95HV-1^06244009.0228800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
779114409-49812-DETAIL-06_29_2023-GO95MLD-1^06244009.0240300 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
895327779-73112-DETAIL-06_29_2023-GO95MLD-1^06244009.0241000 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
474617379-66712-DETAIL-07_05_2023-GO95MLD-1^06244009.0241900 | OTHER | CA-TIER-2 | Distribution | 2023-07-05 | 2028-07-05 | 3
69050909-65229-DETAIL-06_29_2023-GO95HV-1^06244009.0243201 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
267773109-26212-DETAIL-07_03_2023-GO95MLD-1^06244009.0243500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
983097969-77489-AUDIT-08_29_2023-GO95MLD-1^06244009.0244100 | OTHER | CA-TIER-2 | Distribution | 2023-08-29 | 2028-08-29 | 3
847706689-77112-DETAIL-07_03_2023-GO95BLTC-1^06244009.0244303 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
434782779-34112-DETAIL-06_29_2023-GO95MLD-1^06244009.0244305 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
774572549-61512-DETAIL-07_03_2023-GO95HV-1^06244009.0245400 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
901770549-61599-DETAIL-07_03_2023-GO95MLD-1^06244009.0245500 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
901830048-37112-DETAIL-07_03_2023-GO95MLD-1^06244009.0251800 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2026-07-03 | 2
176823648-59212-DETAIL-06_28_2023-GO95HV-1^06244009.0252301 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
350399438-45212-DETAIL-01_04_2024-POLEREPL-1^06244009.0252402 | POLE | CA-TIER-2 | Distribution | 2024-01-04 | 2025-01-04 | 2
381793248-58202-DETAIL-07_03_2023-GO95MLD-1^06244009.0252700 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
860713768-7312-DETAIL-06_28_2023-GO95MLD-1^06244009.0253200 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
810844148-7712-DETAIL-06_28_2023-GO95MLD-1^06244009.0254000 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
680386708-39602-DETAIL-06_29_2023-GO95HV-1^06244009.0254202 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
737052178-10212-DETAIL-06_29_2023-GO95HV-1^06244009.0254700 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
454831298-84718-DETAIL-06_29_2023-GO95HV-1^06244009.0254800 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
454831298-84718-DETAIL-06_29_2023-GO95MLD-1^06244009.0254800 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
51001388-45412-DETAIL-06_29_2023-GUYHINS-1^06244009.0254801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
199542698-8299-DETAIL-06_28_2023-GO95MLD-1^06244009.0255001 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
763196498-45612-DETAIL-06_29_2023-GO95MLD-1^06244009.0255700 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
763196498-45612-DETAIL-06_29_2023-RISEGRD-1^06244009.0255700 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
1240588-62612-DETAIL-06_29_2023-GO95HV-1^06244009.0255701 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
711175058-25479-DETAIL-06_28_2023-GO95MLD-1^06244009.0256000 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
656695328-55012-DETAIL-06_29_2023-GO95MLD-1^06244009.0257701 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
656695328-55012-DETAIL-06_29_2023-RISEBKSP-1^06244009.0257701 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
827177529-19369-DETAIL-07_03_2023-GO95HV-1^06244009.0269401 | OTHER | CA-TIER-2 | Distribution | 2023-07-03 | 2028-07-03 | 3
636812517-76369-DETAIL-06_21_2023-GO95MLD-1^06244009.0270000 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
730260690-2922-DETAIL-06_27_2023-GO95BLTC-1^06244009.0270200 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
730260690-2922-DETAIL-06_27_2023-GO95MLD-1^06244009.0270200 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
589147957-30057-DETAIL-06_27_2023-GO95BLTC-1^06244009.0270201 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
589147957-30057-DETAIL-06_27_2023-GO95MLD-1^06244009.0270201 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
331772590-32-DETAIL-06_27_2023-GO95CL10-1^06244009.0271800 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
432036220-84132-DETAIL-06_27_2023-ABNDEQPM-1^06244009.0272000 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2028-06-27 | 3
859781710-54032-DETAIL-06_27_2023-SVCDEFLC-1^06244009.0273100 | OTHER | CA-TIER-2 | Distribution | 2023-06-27 | 2026-06-27 | 2
618271961-42632-DETAIL-06_21_2023-GO95MLD-1^06244009.0282001 | OTHER | FHCA | Distribution | 2023-06-21 | 2026-06-21 | 2
697351551-80432-AUDIT-08_01_2023-GO95HV-1^06244009.0282100 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
45079451-64329-DETAIL-06_21_2023-GO95HV-1^06244009.0282101 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2028-06-21 | 3
244067051-12232-DETAIL-06_21_2023-GO95HV-1^06244009.0282200 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2028-06-21 | 3
244067051-12232-DETAIL-06_21_2023-GO95MLD-1^06244009.0282200 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
244067051-12232-DETAIL-06_21_2023-SVCENTBK-1^06244009.0282200 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2026-06-21 | 2
497712370-9232-DETAIL-06_21_2023-GO95HV-1^06244009.0282202 | OTHER | CA-TIER-2 | Distribution | 2023-06-21 | 2028-06-21 | 3
360216001-22632-DETAIL-06_15_2023-GO95MLD-1^06244009.0285000 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
586296690-55822-DETAIL-06_27_2023-GO95MLD-1^06244009.0285002 | OTHER | FHCA | Distribution | 2023-06-27 | 2026-06-27 | 2
586296690-55822-DETAIL-06_27_2023-SVCDEFLC-1^06244009.0285002 | OTHER | FHCA | Distribution | 2023-06-27 | 2026-06-27 | 2
586296690-55822-DETAIL-06_27_2023-SVCWIND-1^06244009.0285002 | OTHER | FHCA | Distribution | 2023-06-27 | 2026-06-27 | 2
286774821-22132-DETAIL-06_27_2023-GO95HV-1^06244009.0286100 | OTHER | FHCA | Distribution | 2023-06-27 | 2028-06-27 | 3
883334417-35369-AUDIT-08_22_2023-GO95MLD-1^06244009.0287000 | OTHER | FHCA | Distribution | 2023-08-22 | 2026-08-22 | 2
292322721-25329-DETAIL-06_27_2023-GO95MLD-1^06244009.0287200 | OTHER | FHCA | Distribution | 2023-06-27 | 2026-06-27 | 2
615963911-85199-DETAIL-06_27_2023-GO95MLD-1^06244009.0289200 | OTHER | FHCA | Distribution | 2023-06-27 | 2026-06-27 | 2
560824531-72852-DETAIL-06_15_2023-GO95MLD-1^06244009.0290700 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
560824531-72852-AUDIT-08_01_2023-GO95HV-1^06244009.0290700 | OTHER | FHCA | Distribution | 2023-08-01 | 2028-08-01 | 3
610527431-1852-DETAIL-06_15_2023-GO95MLD-1^06244009.0290701 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
410347021-29752-DETAIL-06_15_2023-GO95MLD-1^06244009.0291700 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
799577194-68194-DETAIL-06_15_2023-GO95MLD-1^06244009.0291702 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
466702917-85369-DETAIL-06_08_2023-GO95MLD-1^06244009.0292602 | OTHER | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
123921641-84852-DETAIL-06_08_2023-GO95HV-1^06244009.0292701 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
177842911-83452-DETAIL-06_08_2023-GO95MLD-1^06244009.0293600 | OTHER | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
702031901-7252-DETAIL-06_08_2023-GO95HV-1^06244009.0294502 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
923769141-57329-DETAIL-06_08_2023-GO95MLD-1^06244009.0296103 | OTHER | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
901844191-77942-DETAIL-06_08_2023-GO95HV-1^06244009.0296400 | OTHER | CA-TIER-2 | Distribution | 2023-06-08 | 2028-06-08 | 3
103372951-90942-DETAIL-06_08_2023-GO95MLD-1^06244009.0297300 | OTHER | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
63670551-29329-DETAIL-06_08_2023-GO95HV-1^06244009.0297301 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
297838564-82048-DETAIL-06_08_2023-GO95MLD-1^06244009.0297400 | OTHER | CA-TIER-2 | Distribution | 2023-06-08 | 2026-06-08 | 2
297838564-82048-DETAIL-06_08_2023-GUYHINS-1^06244009.0297400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-08 | 2026-06-08 | 2
471103521-85299-DETAIL-06_08_2023-GO95HV-1^06244009.0299000 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
756190423-9329-DETAIL-06_26_2023-GO95HV-1^06244009.0300300 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
450821592-20152-DETAIL-06_26_2023-GO95HV-1^06244009.0300600 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
472253533-55452-DETAIL-06_26_2023-SVCENTCO-1^06244009.0301600 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
30501703-41152-DETAIL-06_26_2023-GO95HV-1^06244009.0301700 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
335238003-62152-DETAIL-06_26_2023-GO95MLD-1^06244009.0302802 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
335238003-62152-DETAIL-06_26_2023-GRDRODHI-1^06244009.0302802 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
265659933-61452-DETAIL-06_26_2023-GO95MLD-1^06244009.0303100 | OTHER | FHCA | Distribution | 2023-06-26 | 2028-06-26 | 3
265659933-61452-DETAIL-06_26_2023-GO95TCH-1^06244009.0303100 | OTHER | FHCA | Distribution | 2023-06-26 | 2026-06-26 | 2
370734323-35652-DETAIL-06_26_2023-GO95HV-1^06244009.0303802 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
923727713-7152-DETAIL-06_26_2023-GO95MLD-1^06244009.0303903 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2026-06-26 | 2
481241813-97552-DETAIL-01_04_2024-POLEREPL-1^06244009.0304903 | POLE | CA-TIER-2 | Distribution | 2024-01-04 | 2025-01-04 | 2
186298823-48152-DETAIL-06_26_2023-GO95HV-1^06244009.0304905 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
186298823-48152-DETAIL-06_26_2023-GO95MLD-1^06244009.0304905 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
567723523-18499-DETAIL-01_04_2024-POLEREPL-1^06244009.0305901 | POLE | CA-TIER-2 | Distribution | 2024-01-04 | 2025-01-04 | 2
1230992-799-DETAIL-06_15_2023-GO95MLD-1^06244009.0307600 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
189786243-55329-DETAIL-06_15_2023-GO95HV-1^06244009.0307601 | OTHER | FHCA | Distribution | 2023-06-15 | 2028-06-15 | 3
692277033-41252-DETAIL-06_21_2023-GO95MLD-1^06244009.0307902 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
670811913-22352-ADMIN-07_24_2024-POLEREPL-1^06244009.0308800 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
18050723-88752-DETAIL-06_21_2023-GO95HV-1^06244009.0309400 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
18050723-88752-DETAIL-06_21_2023-GO95TCH-1^06244009.0309400 | OTHER | FHCA | Distribution | 2023-06-21 | 2026-06-21 | 2
28455423-51852-DETAIL-06_21_2023-ABNDEQPM-1^06244009.0309500 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
28455423-51852-DETAIL-06_21_2023-GO95MLD-1^06244009.0309500 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
786626503-57452-DETAIL-06_21_2023-GO95MLD-1^06244009.0309501 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
282266573-58352-DETAIL-06_21_2023-GO95HV-1^06244009.0309601 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
282266573-58352-DETAIL-06_21_2023-RISEGRD-1^06244009.0309601 | OTHER | FHCA | Distribution | 2023-06-21 | 2026-06-21 | 2
970359393-62252-DETAIL-06_15_2023-RISEGRD-1^06244009.0309701 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
384385303-21352-DETAIL-06_15_2023-GO95MLD-1^06244009.0309801 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2028-06-15 | 3
384385303-21352-DETAIL-06_15_2023-RISEGRD-1^06244009.0309801 | OTHER | CA-TIER-2 | Distribution | 2023-06-15 | 2026-06-15 | 2
274589131-19099-DETAIL-06_26_2023-GO95MLD-1^06244009.0310601 | OTHER | FHCA | Distribution | 2023-06-26 | 2028-06-26 | 3
380633311-50252-DETAIL-06_26_2023-GO95HV-1^06244009.0310602 | OTHER | FHCA | Distribution | 2023-06-26 | 2028-06-26 | 3
533487581-2052-DETAIL-06_26_2023-GO95BLTC-1^06244009.0310701 | OTHER | FHCA | Distribution | 2023-06-26 | 2028-06-26 | 3
533487581-2052-DETAIL-06_26_2023-GO95MLD-1^06244009.0310701 | OTHER | FHCA | Distribution | 2023-06-26 | 2026-06-26 | 2
30902771-18952-DETAIL-06_26_2023-GO95HV-1^06244009.0310900 | OTHER | FHCA | Distribution | 2023-06-26 | 2028-06-26 | 3
347899611-50652-DETAIL-06_29_2023-GO95MLD-1^06244009.0325101 | OTHER | FHCA | Distribution | 2023-06-29 | 2026-06-29 | 2
342776961-3061-DETAIL-06_26_2023-GO95HV-1^06244009.0325601 | OTHER | CA-TIER-2 | Distribution | 2023-06-26 | 2028-06-26 | 3
690163522-76599-DETAIL-06_08_2023-ABNDEQPM-1^06244009.0325700 | OTHER | CA-TIER-2 | Distribution | 2023-06-08 | 2028-06-08 | 3
54422801-43552-DETAIL-06_29_2023-GO95MLD-1^06244009.0326300 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2026-06-29 | 2
683861591-82352-DETAIL-06_29_2023-GO95HV-1^06244009.0326301 | OTHER | CA-TIER-2 | Distribution | 2023-06-29 | 2028-06-29 | 3
845910564-25488-DETAIL-06_08_2023-GO95HV-1^06244009.0326600 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
897525301-66279-DETAIL-06_08_2023-GO95MLD-1^06244009.0327501 | OTHER | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
6088862-32952-DETAIL-06_08_2023-GO95HV-1^06244009.0327801 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
352334061-96852-DETAIL-06_08_2023-GO95HV-1^06244009.0327802 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
752597161-43052-DETAIL-06_08_2023-GUYHINS-1^06244009.0328401 | ANCHOR/GUY | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
191263351-74852-DETAIL-06_08_2023-GO95MLD-1^06244009.0328900 | OTHER | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
572439170-21332-DETAIL-06_15_2023-GO95HV-1^06244009.0335103 | OTHER | FHCA | Distribution | 2023-06-15 | 2028-06-15 | 3
878902940-65532-DETAIL-06_15_2023-GO95HV-1^06244009.0335301 | OTHER | FHCA | Distribution | 2023-06-15 | 2028-06-15 | 3
670617930-8232-DETAIL-06_15_2023-GO95MLD-1^06244009.0335500 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
6691020-68922-DETAIL-06_08_2023-GO95HV-1^06244009.0335601 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
28158110-14329-DETAIL-06_08_2023-GO95HV-1^06244009.0335700 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
938176180-27332-DETAIL-06_15_2023-GO95MLD-1^06244009.0336100 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
907153980-49432-DETAIL-06_15_2023-GO95HV-1^06244009.0336102 | OTHER | FHCA | Distribution | 2023-06-15 | 2028-06-15 | 3
658517410-57932-DETAIL-06_08_2023-GO95HV-1^06244009.0336601 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
14885820-53322-DETAIL-06_08_2023-GO95MLD-1^06244009.0336602 | OTHER | FHCA | Distribution | 2023-06-08 | 2028-06-08 | 3
722162310-42522-DETAIL-06_08_2023-GO95MLD-1^06244009.0336800 | OTHER | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
866194000-69122-DETAIL-06_08_2023-GO95MLD-1^06244009.0336900 | OTHER | FHCA | Distribution | 2023-06-08 | 2026-06-08 | 2
299547710-20232-DETAIL-06_21_2023-GO95HV-1^06244009.0336901 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
446987080-60532-DETAIL-06_15_2023-GO95HV-1^06244009.0337100 | OTHER | FHCA | Distribution | 2023-06-15 | 2028-06-15 | 3
446987080-60532-DETAIL-06_15_2023-GO95MLD-1^06244009.0337100 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
762185258-12358-DETAIL-06_21_2023-GO95MLD-1^06244009.0337502 | OTHER | FHCA | Distribution | 2023-06-21 | 2026-06-21 | 2
609186758-81858-DETAIL-06_21_2023-GO95HV-1^06244009.0337600 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
651281210-15199-DETAIL-06_21_2023-GO95MLD-1^06244009.0337701 | OTHER | FHCA | Distribution | 2023-06-21 | 2026-06-21 | 2
843594020-42232-DETAIL-06_21_2023-GO95HV-1^06244009.0337900 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
843594020-42232-DETAIL-06_21_2023-GO95MLD-1^06244009.0337900 | OTHER | FHCA | Distribution | 2023-06-21 | 2028-06-21 | 3
38150590-77632-DETAIL-06_15_2023-GO95HV-1^06244009.0338101 | OTHER | FHCA | Distribution | 2023-06-15 | 2028-06-15 | 3
930275890-98632-DETAIL-06_15_2023-GO95MLD-1^06244009.0339100 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
19856788-86840-DETAIL-06_27_2023-GO95TCH-1^06244009.0346700 | OTHER | FHCA | Distribution | 2023-06-27 | 2026-06-27 | 2
462452928-35612-DETAIL-07_15_2022-UNIGRDSG-1^06244009.0355300 | OTHER | CA-TIER-2 | Distribution | 2022-07-15 | 2025-07-15 | 2
462452928-35612-DETAIL-06_20_2023-GO95MLD-1^06244009.0355300 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
796593118-96512-DETAIL-06_20_2023-SVCENTCO-1^06244009.0356001 | OTHER | FHCA | Distribution | 2023-06-20 | 2026-06-20 | 2
806223619-83912-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0360002 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
816477089-45612-ADMIN-06_27_2024-ABNDEQPM-2^06244009.0360003 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
734387299-12712-DETAIL-06_12_2023-GO95MLD-1^06244009.0360102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
734387299-12712-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0360102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
91468349-73312-DETAIL-06_12_2023-GO95MLD-1^06244009.0360103 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
609171629-24999-DETAIL-06_12_2023-GO95HV-1^06244009.0361102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
609171629-24999-DETAIL-06_12_2023-GO95MLD-1^06244009.0361102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
609171629-24999-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361102 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
236637590-30722-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361104 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
514520942-75479-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361203 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
226215619-52329-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361205 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
616467809-71912-DETAIL-06_12_2023-GO95MLD-1^06244009.0361206 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
616467809-71912-ADMIN-07_19_2024-POLEREPL-1^06244009.0361206 | POLE | FHCA | Distribution | 2024-07-19 | 2027-07-19 | 2
911504089-74122-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0361207 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
21081389-84112-DETAIL-06_20_2023-GO95MLD-1^06244009.0361401 | OTHER | FHCA | Distribution | 2023-06-20 | 2026-06-20 | 2
857751159-21612-DETAIL-06_20_2023-GO95MLD-1^06244009.0361402 | OTHER | FHCA | Distribution | 2023-06-20 | 2028-06-20 | 3
294727479-79522-DETAIL-06_28_2023-GO95HV-1^06244009.0362000 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
492284659-25422-DETAIL-06_28_2023-GO95MLD-1^06244009.0362101 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
731019299-20499-DETAIL-06_12_2023-GO95MLD-1^06244009.0362200 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
879852709-30912-DETAIL-06_12_2023-GO95MLD-1^06244009.0362301 | OTHER | FHCA | Distribution | 2023-06-12 | 2028-06-12 | 3
879852709-30912-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0362301 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
645175499-57222-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0362303 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
11411119-76212-DETAIL-06_12_2023-GO95MLD-1^06244009.0362304 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
839071879-13112-DETAIL-06_12_2023-GO95MLD-1^06244009.0362306 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
375390840-45669-DETAIL-06_20_2023-GO95HV-1^06244009.0362308 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
386712940-33122-DETAIL-06_20_2023-SVCDEFLC-1^06244009.0362320 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
386712940-33122-DETAIL-06_20_2023-SVCDEFLC-2^06244009.0362320 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
849401149-20412-DETAIL-06_12_2023-GO95MLD-1^06244009.0362400 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
6963318-16512-DETAIL-06_20_2023-GO95MLD-1^06244009.0362500 | OTHER | FHCA | Distribution | 2023-06-20 | 2026-06-20 | 2
767481110-41329-DETAIL-06_28_2023-GO95MLD-1^06244009.0363000 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
129171379-28622-DETAIL-06_28_2023-GO95MLD-1^06244009.0363001 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
852487800-51329-ADMIN-08_26_2024-POLEREPL-1^06244009.0363100 | POLE | CA-TIER-2 | Distribution | 2024-08-26 | 2025-08-26 | 2
991741559-47512-DETAIL-06_28_2023-GO95MLD-1^06244009.0363301 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
991741559-47512-DETAIL-06_28_2023-GUYHINS-1^06244009.0363301 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
691436830-64669-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0363302 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
857785630-84669-DETAIL-06_12_2023-GO95HV-1^06244009.0363400 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
461395779-30022-DETAIL-06_12_2023-GO95MLD-1^06244009.0363501 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
461395779-30022-DETAIL-06_12_2023-GUYHINS-1^06244009.0363501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
461395779-30022-DETAIL-06_12_2023-GUYHINS-2^06244009.0363501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
260254518-11612-DETAIL-06_12_2023-GUYHINS-1^06244009.0363600 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
260254518-11612-DETAIL-06_12_2023-GUYHINS-2^06244009.0363600 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
261480528-26612-DETAIL-06_12_2023-GUYHINS-1^06244009.0363700 | ANCHOR/GUY | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
261480528-26612-DETAIL-06_12_2023-GUYHINS-2^06244009.0363700 | ANCHOR/GUY | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
426769629-70579-DETAIL-06_28_2023-GO95HV-1^06244009.0364300 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
426769629-70579-DETAIL-06_28_2023-SVCDEFLC-1^06244009.0364300 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
434104478-85799-DETAIL-06_12_2023-GO95MLD-1^06244009.0365501 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
434104478-85799-DETAIL-06_12_2023-GUYHINS-1^06244009.0365501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
191962149-32869-DETAIL-06_12_2023-GO95MLD-1^06244009.0365502 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
191962149-32869-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0365502 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2026-06-12 | 2
503786588-73212-DETAIL-06_12_2023-GO95HV-1^06244009.0365600 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
503786588-73212-DETAIL-06_12_2023-GO95MLD-1^06244009.0365600 | OTHER | CA-TIER-2 | Distribution | 2023-06-12 | 2028-06-12 | 3
468840921-94921-DETAIL-06_28_2023-GO95TCH-1^06244009.0365800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
505861158-78229-DETAIL-06_28_2023-GO95MLD-1^06244009.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
505861158-78229-DETAIL-06_28_2023-GRDRODHI-1^06244009.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
505861158-78229-DETAIL-06_28_2023-SVCDEFLC-1^06244009.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
505861158-78229-DETAIL-06_28_2023-SVCDEFLC-2^06244009.0365801 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2026-06-28 | 2
620990588-68229-AUDIT-07_13_2023-GO95MLD-1^06244009.0365901 | OTHER | CA-TIER-2 | Distribution | 2023-07-13 | 2026-07-13 | 2
997026778-1902-ADMIN-08_28_2024-POLEREPL-1^06244009.0366702 | POLE | CA-TIER-2 | Distribution | 2024-08-28 | 2025-08-28 | 2
903121578-18229-DETAIL-06_28_2023-GO95HV-1^06244009.0367700 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
146344788-49229-DETAIL-06_28_2023-GO95HV-1^06244009.0368800 | OTHER | CA-TIER-2 | Distribution | 2023-06-28 | 2028-06-28 | 3
870935323-62852-DETAIL-06_13_2023-GO95MLD-1^06244010.0220400 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
603456293-14252-DETAIL-06_13_2023-GO95MLD-1^06244010.0221400 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
176110793-85252-DETAIL-06_13_2023-GO95MLD-1^06244010.0223501 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
361195853-4752-DETAIL-06_13_2023-GO95MLD-1^06244010.0225501 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
361195853-4752-DETAIL-06_13_2023-SVCDEFLC-1^06244010.0225501 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
720977643-10552-DETAIL-06_13_2023-GO95HV-1^06244010.0227301 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
304102723-26352-DETAIL-06_13_2023-GO95HV-1^06244010.0228300 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
674139351-36742-AUDIT-08_01_2023-GO95HV-1^06244010.0243002 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2028-08-01 | 3
674139351-36742-AUDIT-08_01_2023-SVCROAD-1^06244010.0243002 | OTHER | CA-TIER-2 | Distribution | 2023-08-01 | 2026-08-01 | 2
623534871-8442-DETAIL-06_19_2023-GO95MLD-1^06244010.0243200 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
946496141-75799-DETAIL-06_19_2023-GO95HV-1^06244010.0244000 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
946496141-75799-DETAIL-06_19_2023-GUYHINS-1^06244010.0244000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
946496141-75799-DETAIL-06_19_2023-SVCROAD-1^06244010.0244000 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
478546981-67742-DETAIL-06_19_2023-GO95MLD-1^06244010.0244300 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
943092151-22429-DETAIL-06_19_2023-ABNDEQPM-1^06244010.0244400 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
1449191-97942-DETAIL-06_19_2023-GO95MLD-1^06244010.0244402 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
959920701-91252-DETAIL-06_19_2023-GO95MLD-1^06244010.0244600 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
811148862-23952-DETAIL-06_19_2023-GO95MLD-1^06244010.0250100 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
397515533-34952-DETAIL-06_20_2023-GO95MLD-1^06244010.0250101 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
72982593-36252-DETAIL-06_20_2023-GO95MLD-1^06244010.0250103 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
163081912-56979-DETAIL-06_19_2023-GO95HV-1^06244010.0250202 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
67529802-2902-DETAIL-06_19_2023-GO95MLD-1^06244010.0250401 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
301956163-90352-DETAIL-06_19_2023-GO95MLD-1^06244010.0250501 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
307309202-80052-DETAIL-06_19_2023-GUYNOINS-1^06244010.0250503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
307309202-80052-DETAIL-06_19_2023-GUYNOINS-2^06244010.0250503 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
655616822-1652-DETAIL-06_19_2023-GO95HV-1^06244010.0251200 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
998024302-37429-DETAIL-06_19_2023-GO95HV-1^06244010.0251601 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
480821863-1852-DETAIL-06_20_2023-GO95HV-1^06244010.0252301 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
175033612-73052-DETAIL-06_19_2023-GO95MLD-1^06244010.0252700 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
463861912-34052-DETAIL-06_19_2023-GO95HV-1^06244010.0252801 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2028-06-19 | 3
984063453-29252-DETAIL-06_20_2023-GO95HV-1^06244010.0253300 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
44840773-75852-DETAIL-06_20_2023-GO95MLD-1^06244010.0253500 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
976415583-59052-DETAIL-06_20_2023-GO95MLD-1^06244010.0253501 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
976415583-59052-DETAIL-06_20_2023-RISEGRD-1^06244010.0253501 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
766372343-91252-ADMIN-07_24_2024-POLEREPL-1^06244010.0254300 | POLE | FHCA | Distribution | 2024-07-24 | 2027-07-24 | 2
429411032-85852-DETAIL-06_20_2023-GO95MLD-1^06244010.0255300 | OTHER | FHCA | Distribution | 2023-06-20 | 2026-06-20 | 2
459933132-30999-DETAIL-06_20_2023-GO95HV-1^06244010.0255301 | OTHER | FHCA | Distribution | 2023-06-20 | 2028-06-20 | 3
142076553-20352-AUDIT-08_22_2023-GO95MLD-1^06244010.0255302 | OTHER | FHCA | Distribution | 2023-08-22 | 2026-08-22 | 2
926497555-19555-DETAIL-06_20_2023-SVCDEFLC-1^06244010.0256300 | OTHER | FHCA | Distribution | 2023-06-20 | 2026-06-20 | 2
659900103-72652-DETAIL-06_20_2023-GO95MLD-1^06244010.0256402 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
660641333-83952-DETAIL-06_20_2023-GO95MLD-1^06244010.0256500 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
660641333-83952-DETAIL-06_20_2023-SVCDEFLC-1^06244010.0256500 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
266062413-38429-ADMIN-07_24_2024-POLEREPL-1^06244010.0256501 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
140264555-55555-DETAIL-06_20_2023-GO95MLD-1^06244010.0257500 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
73151122-92852-DETAIL-06_20_2023-SVCDEFLC-1^06244010.0258501 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
73151122-92852-DETAIL-06_20_2023-SVCDEFLC-2^06244010.0258501 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
518651793-86252-DETAIL-06_20_2023-SVCDEFLC-1^06244010.0258504 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
225879843-58429-DETAIL-06_26_2023-GRDRODHI-1^06244010.0259100 | OTHER | FHCA | Distribution | 2023-06-26 | 2026-06-26 | 2
225879843-58429-DETAIL-06_26_2023-GRDRODHI-2^06244010.0259100 | OTHER | FHCA | Distribution | 2023-06-26 | 2026-06-26 | 2
265220555-71555-DETAIL-06_20_2023-GO95HV-1^06244010.0259600 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2028-06-20 | 3
32290682-33752-DETAIL-06_20_2023-GO95MLD-1^06244010.0259601 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
782561202-51252-DETAIL-06_19_2023-GO95MLD-1^06244010.0261400 | OTHER | FHCA | Distribution | 2023-06-19 | 2026-06-19 | 2
286929331-87429-DETAIL-06_19_2023-GO95MLD-1^06244010.0263500 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
890408721-65399-DETAIL-06_19_2023-GO95MLD-1^06244010.0264501 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
890408721-65399-DETAIL-06_19_2023-GRDRODHI-1^06244010.0264501 | OTHER | CA-TIER-2 | Distribution | 2023-06-19 | 2026-06-19 | 2
881744113-65262-DETAIL-06_15_2023-GO95HV-1^06244010.0269001 | OTHER | FHCA | Distribution | 2023-06-15 | 2028-06-15 | 3
449693991-41452-ADMIN-07_24_2024-POLEREPL-1^06244010.0269200 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
308654791-80452-DETAIL-06_20_2023-GO95MLD-1^06244010.0269201 | OTHER | CA-TIER-2 | Distribution | 2023-06-20 | 2026-06-20 | 2
421866783-76853-DETAIL-06_07_2023-GO95MLD-1^06244010.0270801 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
558447123-11553-DETAIL-06_07_2023-GO95MLD-1^06244010.0271700 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
536846863-73853-DETAIL-06_07_2023-GO95MLD-1^06244010.0271802 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
536846863-73853-DETAIL-06_07_2023-GUYLOINS-1^06244010.0271802 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
248520383-86653-DETAIL-06_13_2023-GO95HV-1^06244010.0272700 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
248520383-86653-DETAIL-06_13_2023-GO95MLD-1^06244010.0272700 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
453536151-40529-DETAIL-06_07_2023-GO95HV-1^06244010.0273700 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
714864643-1529-DETAIL-06_07_2023-GO95TCH-1^06244010.0273800 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
419210151-70529-DETAIL-06_07_2023-GO95HV-1^06244010.0273803 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
838878443-6289-DETAIL-06_07_2023-GO95MLD-1^06244010.0275401 | OTHER | FHCA | Distribution | 2023-06-07 | 2028-06-07 | 3
872820653-19199-DETAIL-06_07_2023-GO95MLD-1^06244010.0275500 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
388511333-58779-DETAIL-06_07_2023-GO95MLD-1^06244010.0275502 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
933636913-42753-DETAIL-06_07_2023-GO95MLD-1^06244010.0275600 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
933636913-42753-DETAIL-06_07_2023-SVCROAD-1^06244010.0275600 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
330672073-45653-DETAIL-06_07_2023-GO95HV-1^06244010.0275602 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
913699143-33353-DETAIL-06_07_2023-GO95MLD-1^06244010.0275703 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
913699143-33353-DETAIL-06_07_2023-SVCDEFLC-1^06244010.0275703 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
913699143-33353-DETAIL-06_07_2023-SVCWIND-1^06244010.0275703 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2026-06-07 | 2
759143570-68668-DETAIL-06_07_2023-GO95HV-1^06244010.0276601 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
150072533-98429-DETAIL-06_07_2023-GO95MLD-1^06244010.0276801 | OTHER | CA-TIER-2 | Distribution | 2023-06-07 | 2028-06-07 | 3
644677243-51529-DETAIL-06_13_2023-GO95MLD-1^06244010.0285801 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2026-06-13 | 2
505417489-89892-DETAIL-06_13_2023-GO95HV-1^06244010.0287900 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
137899349-13792-DETAIL-06_14_2023-GO95HV-1^06244010.0288301 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
303116739-91792-DETAIL-06_14_2023-GO95HV-1^06244010.0288400 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
723669786-26378-DETAIL-06_14_2023-GO95HV-1^06244010.0288500 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
290712989-16892-DETAIL-06_13_2023-GO95HV-1^06244010.0288900 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
857189169-78792-DETAIL-06_13_2023-GO95HV-1^06244010.0288901 | OTHER | CA-TIER-2 | Distribution | 2023-06-13 | 2028-06-13 | 3
57223439-89692-DETAIL-06_14_2023-GO95HV-1^06244010.0289500 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
205847095-17172-DETAIL-06_06_2023-GO95MLD-1^06244010.0340501 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
826374446-61672-DETAIL-06_06_2023-GO95MLD-1^06244010.0342300 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
328631036-32529-DETAIL-06_06_2023-RISEBKSP-1^06244010.0342302 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
406204735-39872-DETAIL-06_06_2023-GO95MLD-1^06244010.0342401 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
142798126-66372-DETAIL-06_06_2023-GO95HV-1^06244010.0342403 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
575782825-20872-DETAIL-06_06_2023-GO95HV-1^06244010.0342500 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
327325305-90672-DETAIL-06_06_2023-GO95HV-1^06244010.0344501 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
74605926-56472-DETAIL-05_30_2023-GO95MLD-1^06244010.0344900 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
74605926-56472-DETAIL-05_30_2023-GUYHINS-1^06244010.0344900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
988122404-49962-DETAIL-05_30_2023-GO95HV-1^06244010.0344901 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
983077804-48962-DETAIL-05_30_2023-GO95HV-1^06244010.0344902 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
724558445-82529-DETAIL-06_06_2023-ENCHRW-1^06244010.0345300 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
583898036-65282-DETAIL-06_06_2023-GO95MLD-1^06244010.0345400 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
134005385-55172-DETAIL-05_30_2023-GO95MLD-1^06244010.0345401 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2026-05-30 | 2
963511904-81499-ADMIN-07_24_2024-POLEREPL-1^06244010.0346000 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
109817374-60572-DETAIL-06_06_2023-GO95MLD-1^06244010.0346300 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
435441514-17072-DETAIL-06_06_2023-GO95MLD-1^06244010.0346302 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
876017114-12529-DETAIL-06_14_2023-GO95CL10-1^06244010.0347103 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
307669586-84189-DETAIL-06_06_2023-GO95HV-1^06244010.0347200 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
307669586-84189-DETAIL-06_06_2023-GO95MLD-1^06244010.0347200 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2028-06-06 | 3
849038385-49072-DETAIL-06_06_2023-GUYLOINS-1^06244010.0347400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
62097004-43529-DETAIL-05_30_2023-GO95HV-1^06244010.0347500 | OTHER | CA-TIER-2 | Distribution | 2023-05-30 | 2028-05-30 | 3
119454256-75772-DETAIL-06_06_2023-GO95MLD-1^06244010.0347600 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
652987636-24469-DETAIL-06_14_2023-SVCENTCO-1^06244010.0348100 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
826791055-88872-DETAIL-06_14_2023-GO95MLD-1^06244010.0348104 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
389623066-85282-DETAIL-06_14_2023-GO95MLD-1^06244010.0349300 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
389623066-85282-DETAIL-06_14_2023-RISEBKSP-1^06244010.0349300 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
411334556-56082-DETAIL-06_14_2023-GO95MLD-1^06244010.0349302 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
712683445-83529-DETAIL-06_06_2023-GO95MLD-1^06244010.0349600 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
180019824-75162-DETAIL-06_06_2023-GO95MLD-1^06244010.0349602 | OTHER | CA-TIER-2 | Distribution | 2023-06-06 | 2026-06-06 | 2
941648752-2352-DETAIL-06_14_2023-GO95MLD-1^06244010.0352101 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
69750852-22352-DETAIL-06_14_2023-GO95MLD-1^06244010.0352200 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
69750852-22352-DETAIL-06_14_2023-SVCDEFLC-1^06244010.0352200 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
4024403-5675-DETAIL-06_14_2023-GO95MLD-1^06244010.0352201 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2028-06-14 | 3
382667320-40420-DETAIL-06_14_2023-SVCDEFLC-1^06244010.0352220 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
533511811-49279-DETAIL-06_14_2023-GO95MLD-1^06244010.0352600 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
471233961-2052-DETAIL-06_14_2023-SVCDEFLC-1^06244010.0352700 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
854097459-13056-DETAIL-06_14_2023-GO95MLD-1^06244010.0354700 | OTHER | CA-TIER-2 | Distribution | 2023-06-14 | 2026-06-14 | 2
876854921-83252-DETAIL-06_15_2023-GO95MLD-1^06244010.0356701 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
876854921-83252-DETAIL-06_15_2023-GRDRODHI-1^06244010.0356701 | OTHER | FHCA | Distribution | 2023-06-15 | 2026-06-15 | 2
496855594-44109-DETAIL-10_19_2022-GO95MLD-1^06244011.0010500 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
395931734-24079-DETAIL-07_31_2024-GO95HV-1^06245004.0060801 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
395931734-24079-DETAIL-07_31_2024-GO95MLD-1^06245004.0060801 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
592926424-96469-DETAIL-07_31_2024-GO95HV-1^06245004.0073701 | OTHER | FHCA | Distribution | 2024-07-31 | 2029-07-31 | 3
658069916-81589-DETAIL-08_20_2024-GO95HV-1^06245004.0190900 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
624842326-11049-DETAIL-08_20_2024-GO95HV-1^06245004.0191900 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
650262236-59949-DETAIL-08_20_2024-GO95HV-1^06245004.0194900 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
129868836-78949-DETAIL-08_20_2024-GO95HV-1^06245004.0196901 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
124986856-66949-DETAIL-08_20_2024-GO95HV-1^06245004.0200900 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
697172866-26949-DETAIL-08_20_2024-GO95MLD-1^06245004.0200902 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
188010475-98049-DETAIL-08_19_2024-GO95MLD-1^06245004.0290500 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
188010475-98049-DETAIL-08_19_2024-GRDRODHI-1^06245004.0290500 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
188010475-98049-DETAIL-08_19_2024-SVCDEFLC-1^06245004.0290500 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
99387975-87479-DETAIL-08_19_2024-GO95MLD-1^06245004.0290502 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
104994035-62149-DETAIL-07_05_2024-GO95HV-1^06245004.0300600 | OTHER | FHCA | Distribution | 2024-07-05 | 2029-07-05 | 3
297827285-87469-DETAIL-07_05_2024-SVCENTCO-1^06245004.0308401 | OTHER | FHCA | Distribution | 2024-07-05 | 2027-07-05 | 2
337370964-4669-DETAIL-08_05_2024-GO95HV-1^06245004.0327702 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
337370964-4669-DETAIL-08_05_2024-GO95MLD-1^06245004.0327702 | OTHER | FHCA | Distribution | 2024-08-05 | 2029-08-05 | 3
67456915-96049-DETAIL-08_06_2024-INSULDMG-1^06245004.0328500 | INSULATOR AND BUSHING | FHCA | Distribution | 2024-08-06 | 2027-08-06 | 2
67456915-96049-ADMIN-09_11_2024-XARMSPCR-1^06245004.0328500 | CROSSARM | FHCA | Distribution | 2024-09-11 | 2027-09-11 | 2
514154325-77049-DETAIL-08_06_2024-POLETOP-1^06245004.0328600 | POLE | FHCA | Distribution | 2024-08-06 | 2027-08-06 | 2
441941135-65199-DETAIL-08_06_2024-GO95MLD-1^06245004.0328700 | OTHER | FHCA | Distribution | 2024-08-06 | 2027-08-06 | 2
441941135-65199-DETAIL-08_06_2024-GO95STUB-1^06245004.0328700 | OTHER | FHCA | Distribution | 2024-08-06 | 2027-08-06 | 2
990002805-85049-DETAIL-08_06_2024-GO95HV-1^06245004.0329301 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
979439505-36049-DETAIL-08_06_2024-GO95HV-1^06245004.0329401 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
230986196-5049-DETAIL-08_06_2024-GO95HV-1^06245004.0330200 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
17593175-65049-DETAIL-08_06_2024-INSULDMG-1^06245004.0330300 | INSULATOR AND BUSHING | FHCA | Distribution | 2024-08-06 | 2027-08-06 | 2
823341056-63049-DETAIL-08_06_2024-GO95HV-1^06245004.0331000 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
857068386-44049-DETAIL-08_06_2024-INSULDMG-1^06245004.0331100 | INSULATOR AND BUSHING | FHCA | Distribution | 2024-08-06 | 2027-08-06 | 2
348516356-3049-DETAIL-08_06_2024-GO95HV-1^06245004.0332001 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
810198066-12049-DETAIL-08_06_2024-GO95HV-1^06245004.0334100 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
150196066-32049-DETAIL-08_06_2024-GO95HV-1^06245004.0334101 | OTHER | FHCA | Distribution | 2024-08-06 | 2029-08-06 | 3
878741439-95259-DETAIL-05_06_2024-GO95MLD-1^06245005.0045901 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
640910249-91989-DETAIL-05_06_2024-GO95MLD-1^06245005.0047900 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2029-05-06 | 3
795994328-27249-DETAIL-03_14_2024-GO95MLD-1^06245005.0060302 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
459508758-11349-DETAIL-03_14_2024-GO95HV-1^06245005.0061500 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
459508758-11349-DETAIL-03_14_2024-GO95MLD-1^06245005.0061500 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
783873378-5099-DETAIL-03_18_2024-GO95MLD-1^06245005.0061600 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
783873378-5099-AUDIT-04_05_2024-INSULDMG-1^06245005.0061600 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-05 | 2027-04-05 | 2
783873378-5099-AUDIT-04_05_2024-XARMSPCR-1^06245005.0061600 | CROSSARM | CA-NON-TIER | Distribution | 2024-04-05 | 2027-04-05 | 2
783873378-5099-ADMIN-07_19_2024-POLETOP-1^06245005.0061600 | POLE | CA-NON-TIER | Distribution | 2024-07-19 | 2027-07-19 | 2
658305599-76249-DETAIL-03_14_2024-GO95MLD-1^06245005.0061601 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
996176489-96249-DETAIL-03_14_2024-GO95HV-1^06245005.0061602 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
123869089-80349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061603 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
123869089-80349-DETAIL-03_18_2024-GUYNOINS-1^06245005.0061603 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
747264989-29099-DETAIL-03_18_2024-GO95MLD-1^06245005.0061604 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
447599478-60349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061701 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
447599478-60349-DETAIL-03_18_2024-GUYNOINS-1^06245005.0061701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
181145459-19583-DETAIL-03_14_2024-GO95HV-1^06245005.0061740 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
980113588-349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061800 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
911586298-40349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061900 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
243630588-20349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061901 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
937149279-5089-DETAIL-03_14_2024-GO95MLD-1^06245005.0062400 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
591142099-19249-DETAIL-03_14_2024-GO95MLD-1^06245005.0062502 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
909309589-53789-DETAIL-03_14_2024-GO95MLD-1^06245005.0062503 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
840801299-49249-DETAIL-03_14_2024-GO95MLD-1^06245005.0062601 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
840801299-49249-DETAIL-03_14_2024-SVCWIND-1^06245005.0062601 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
457383959-99583-DETAIL-03_14_2024-SVCNEUT-1^06245005.0062740 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
805506159-46249-DETAIL-06_22_2023-GO95MLD-1^06245005.0071000 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
805506159-46249-DETAIL-06_22_2023-GO95MLD-2^06245005.0071000 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
422274004-12203-DETAIL-06_22_2023-GO95MLD-1^06245005.0075000 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
479005139-52779-DETAIL-06_22_2023-GO95MLD-1^06245005.0075002 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
659737829-14249-DETAIL-06_22_2023-GO95MLD-1^06245005.0076000 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
898220409-38589-DETAIL-06_22_2023-GO95MLD-1^06245005.0076001 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
345326929-93249-DETAIL-06_22_2023-GO95MLD-1^06245005.0077000 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
45360289-35889-DETAIL-06_22_2023-GO95MLD-1^06245005.0077201 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
839038679-56179-DETAIL-06_22_2023-GO95MLD-1^06245005.0077203 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
839038679-56179-DETAIL-06_22_2023-SVCROAD-1^06245005.0077203 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
62188799-10249-DETAIL-06_22_2023-GO95MLD-1^06245005.0078201 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
821328479-80249-DETAIL-06_22_2023-GO95MLD-1^06245005.0078204 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
503779259-23249-DETAIL-06_22_2023-GO95MLD-1^06245005.0078205 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
503779259-23249-DETAIL-06_22_2023-SVCROAD-1^06245005.0078205 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
944318449-48183-DETAIL-06_22_2023-GO95MLD-1^06245005.0078206 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
944318449-48183-DETAIL-06_22_2023-SVCROAD-1^06245005.0078206 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
35273869-30299-DETAIL-06_22_2023-GO95MLD-1^06245005.0079000 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
413785798-81249-DETAIL-06_22_2023-GO95HV-1^06245005.0079004 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
78148259-80683-DETAIL-06_22_2023-GO95MLD-1^06245005.0079042 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
721403039-41249-DETAIL-06_22_2023-GO95MLD-1^06245005.0079100 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
581532139-27383-DETAIL-06_22_2023-GO95MLD-1^06245005.0079140 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
438553149-77383-DETAIL-06_22_2023-GO95MLD-1^06245005.0079241 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
6685529-39149-DETAIL-06_22_2023-GO95MLD-1^06245005.0079500 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
6734559-58583-DETAIL-06_22_2023-GO95MLD-1^06245005.0079540 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
722269959-58149-DETAIL-06_22_2023-GO95HV-1^06245005.0079601 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
781877669-26289-AUDIT-07_05_2023-GUYLOINS-1^06245005.0079700 | ANCHOR/GUY | FHCA | Distribution | 2023-07-05 | 2026-07-05 | 2
948308609-34199-DETAIL-05_04_2023-GO95MLD-1^06245005.0080202 | OTHER | FHCA | Distribution | 2023-05-04 | 2026-05-04 | 2
948308609-34199-DETAIL-05_04_2023-GRDRODHI-1^06245005.0080202 | OTHER | FHCA | Distribution | 2023-05-04 | 2026-05-04 | 2
948308609-34199-DETAIL-05_04_2023-GRDRODHI-2^06245005.0080202 | OTHER | FHCA | Distribution | 2023-05-04 | 2026-05-04 | 2
818718869-9149-DETAIL-05_25_2023-GO95MLD-1^06245005.0080700 | OTHER | FHCA | Distribution | 2023-05-25 | 2028-05-25 | 3
818718869-9149-DETAIL-05_25_2023-SVCROAD-1^06245005.0080700 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
3385649-16149-DETAIL-05_04_2023-GO95HV-1^06245005.0085201 | OTHER | FHCA | Distribution | 2023-05-04 | 2028-05-04 | 3
371333379-16079-DETAIL-05_04_2023-GO95HV-1^06245005.0088300 | OTHER | FHCA | Distribution | 2023-05-04 | 2028-05-04 | 3
371333379-16079-DETAIL-05_04_2023-GO95MLD-1^06245005.0088300 | OTHER | FHCA | Distribution | 2023-05-04 | 2028-05-04 | 3
466091993-84469-DETAIL-08_20_2024-GO95HV-1^06245005.0137101 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
365000745-86549-DETAIL-05_18_2023-GO95HV-1^06245005.0159201 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
56795755-57549-DETAIL-05_18_2023-GO95HV-1^06245005.0159300 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
879873555-77549-DETAIL-05_18_2023-GO95MLD-1^06245005.0159400 | OTHER | FHCA | Distribution | 2023-05-18 | 2026-05-18 | 2
101917668-27349-DETAIL-05_25_2023-GO95MLD-1^06245005.0170001 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
673781968-78349-DETAIL-05_23_2023-GO95HV-1^06245005.0170201 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
193251078-74889-DETAIL-05_25_2023-GO95MLD-1^06245005.0170401 | OTHER | FHCA | Distribution | 2023-05-25 | 2028-05-25 | 3
193251078-74889-DETAIL-05_25_2023-SVCROAD-1^06245005.0170401 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
659431598-94679-DETAIL-05_23_2023-GO95MLD-1^06245005.0170700 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
336913068-17569-DETAIL-05_23_2023-GO95HV-1^06245005.0170800 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
778257188-16989-DETAIL-05_23_2023-SVCROAD-1^06245005.0170901 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
155815418-60679-DETAIL-05_24_2023-GO95MLD-1^06245005.0181000 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
79604328-17783-DETAIL-05_23_2023-GO95HV-1^06245005.0181940 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
131838258-22689-DETAIL-05_23_2023-GO95MLD-1^06245005.0183801 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
131838258-22689-DETAIL-05_23_2023-GRDRODHI-1^06245005.0183801 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
763992468-17449-DETAIL-05_23_2023-GO95MLD-1^06245005.0185900 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
763992468-17449-DETAIL-05_23_2023-SVCROAD-1^06245005.0185900 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
386614598-46449-DETAIL-05_23_2023-SVCROAD-1^06245005.0185901 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
178429208-76449-DETAIL-05_23_2023-GUYNOINS-1^06245005.0186900 | ANCHOR/GUY | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
178429208-76449-DETAIL-05_23_2023-GUYNOINS-2^06245005.0186900 | ANCHOR/GUY | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
274799128-6449-DETAIL-05_23_2023-SVCROAD-1^06245005.0187900 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
733517602-93569-DETAIL-05_25_2023-GO95MLD-1^06245005.0189401 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
136619438-84449-DETAIL-05_23_2023-GO95MLD-1^06245005.0189500 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
597441738-43579-DETAIL-05_23_2023-GO95MLD-1^06245005.0189501 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
320810338-91099-DETAIL-05_23_2023-GO95MLD-1^06245005.0189503 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
804750258-14079-DETAIL-05_23_2023-GO95MLD-1^06245005.0189702 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
438093688-57269-DETAIL-05_23_2023-GO95MLD-1^06245005.0189801 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
34134778-27269-DETAIL-05_23_2023-GO95HV-1^06245005.0189802 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
34134778-27269-DETAIL-05_23_2023-GO95MLD-1^06245005.0189802 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
167108962-12669-DETAIL-05_23_2023-GO95HV-1^06245005.0189804 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
878239588-92383-DETAIL-05_23_2023-GO95HV-1^06245005.0189900 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
878239588-92383-DETAIL-05_23_2023-GO95MLD-1^06245005.0189900 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
26648948-3449-DETAIL-05_23_2023-GO95MLD-1^06245005.0189902 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
901783608-53449-DETAIL-05_23_2023-SVCENTCO-1^06245005.0189904 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
322415238-59449-DETAIL-05_24_2023-GO95MLD-1^06245005.0192101 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
515585988-25269-DETAIL-05_24_2023-GO95MLD-1^06245005.0192102 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
537873898-15269-DETAIL-05_24_2023-GO95HV-1^06245005.0192300 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
915794908-2349-DETAIL-05_22_2023-GO95MLD-1^06245005.0197000 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
425868538-69779-DETAIL-05_25_2023-GO95HV-1^06245005.0199401 | OTHER | FHCA | Distribution | 2023-05-25 | 2028-05-25 | 3
425868538-69779-DETAIL-05_25_2023-GRDRODHI-1^06245005.0199401 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
425868538-69779-DETAIL-05_25_2023-GRDRODHI-2^06245005.0199401 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
493472538-65349-DETAIL-05_25_2023-GO95MLD-1^06245005.0199402 | OTHER | FHCA | Distribution | 2023-05-25 | 2028-05-25 | 3
493472538-65349-DETAIL-05_25_2023-SVCENTCO-1^06245005.0199402 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
435687148-26089-DETAIL-05_25_2023-GO95MLD-1^06245005.0199800 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
872900628-41449-DETAIL-05_25_2023-ENCHRW-1^06245005.0200400 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
715783638-34349-DETAIL-05_25_2023-GO95MLD-1^06245005.0200401 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
352231828-95199-DETAIL-05_25_2023-GO95MLD-1^06245005.0200403 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
630771748-76979-DETAIL-05_25_2023-GO95MLD-1^06245005.0200700 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
899676258-36349-DETAIL-05_25_2023-GO95HV-1^06245005.0200800 | OTHER | FHCA | Distribution | 2023-05-25 | 2028-05-25 | 3
61671338-31149-DETAIL-05_18_2023-GO95MLD-1^06245005.0214001 | OTHER | CA-NON-TIER | Distribution | 2023-05-18 | 2026-05-18 | 2
403043048-20149-DETAIL-05_18_2023-GO95HV-1^06245005.0215001 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
403043048-20149-DETAIL-05_18_2023-GO95MLD-1^06245005.0215001 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
953130258-29049-DETAIL-05_18_2023-GO95MLD-1^06245005.0217000 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
237085058-68049-DETAIL-05_18_2023-GO95MLD-1^06245005.0218001 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
46920068-57049-DETAIL-05_18_2023-GO95MLD-1^06245005.0219002 | OTHER | FHCA | Distribution | 2023-05-18 | 2026-05-18 | 2
214238578-46049-DETAIL-05_18_2023-GO95HV-1^06245005.0222000 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
793804178-56889-DETAIL-05_18_2023-GO95MLD-1^06245005.0223000 | OTHER | FHCA | Distribution | 2023-05-18 | 2026-05-18 | 2
302981778-30279-DETAIL-05_18_2023-GO95MLD-1^06245005.0223001 | OTHER | FHCA | Distribution | 2023-05-18 | 2026-05-18 | 2
287691338-62598-DETAIL-05_18_2023-GO95HV-1^06245005.0225001 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
429700998-94049-DETAIL-05_11_2023-GO95MLD-1^06245005.0226000 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
751739898-2899-DETAIL-05_18_2023-GO95MLD-1^06245005.0226001 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
108076108-84049-DETAIL-05_11_2023-GO95MLD-1^06245005.0227000 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
358397965-17599-DETAIL-05_24_2023-GO95MLD-1^06245005.0228000 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
358397965-17599-DETAIL-05_24_2023-GUYHINS-1^06245005.0228000 | ANCHOR/GUY | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
358397965-17599-DETAIL-05_24_2023-SVCNEUT-1^06245005.0228000 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
953398765-60549-DETAIL-05_24_2023-GUYNOINS-1^06245005.0228001 | ANCHOR/GUY | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
28263118-3049-DETAIL-05_11_2023-GUYNOINS-1^06245005.0228002 | ANCHOR/GUY | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
128744008-80599-DETAIL-05_11_2023-GO95MLD-1^06245005.0228003 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
128744008-80599-DETAIL-05_11_2023-SVCROAD-1^06245005.0228003 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
55481955-30549-DETAIL-05_24_2023-GO95MLD-1^06245005.0229001 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
573702275-80549-DETAIL-05_11_2023-GO95HV-1^06245005.0229101 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
611272795-51549-DETAIL-05_11_2023-GO95HV-1^06245005.0229200 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
664228395-31549-DETAIL-05_11_2023-GO95HV-1^06245005.0229201 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
383699895-81549-DETAIL-05_18_2023-GO95HV-1^06245005.0229301 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
774411105-42549-DETAIL-05_18_2023-GO95HV-1^06245005.0229400 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
486145705-12549-DETAIL-05_18_2023-GO95HV-1^06245005.0229401 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
314615115-93549-DETAIL-05_18_2023-GO95HV-1^06245005.0229500 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
309002115-55549-DETAIL-05_18_2023-GO95HV-1^06245005.0229700 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
477934929-53749-DETAIL-05_11_2023-GO95HV-1^06245005.0230002 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
239654569-51749-DETAIL-05_11_2023-GO95HV-1^06245005.0233000 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
679874089-69649-DETAIL-05_11_2023-GO95MLD-1^06245005.0234000 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
247809424-96698-DETAIL-05_11_2023-GO95MLD-1^06245005.0234001 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
299190713-70649-DETAIL-05_11_2023-GO95MLD-1^06245005.0235000 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
299190713-70649-DETAIL-05_11_2023-SVCENTCO-1^06245005.0235000 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
299190713-70649-DETAIL-05_11_2023-SVCENTCO-2^06245005.0235000 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
662120189-29649-DETAIL-05_11_2023-GO95HV-1^06245005.0235003 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
923428259-9999-DETAIL-05_11_2023-GO95MLD-1^06245005.0238001 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
554891524-82524-DETAIL-08_19_2024-SVCDEFLC-1^06245005.0248201 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
616802259-93649-DETAIL-08_19_2024-GO95HV-1^06245005.0250000 | OTHER | FHCA | Distribution | 2024-08-19 | 2029-08-19 | 3
616802259-93649-DETAIL-08_19_2024-GO95MLD-1^06245005.0250000 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
616802259-93649-DETAIL-08_19_2024-GRDRODHI-1^06245005.0250000 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
516420189-43649-DETAIL-08_20_2024-GO95HV-1^06245005.0250100 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
345755299-92649-DETAIL-08_20_2024-GO95HV-1^06245005.0251201 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
304895899-42649-DETAIL-08_20_2024-GO95HV-1^06245005.0251300 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
427949119-49389-DETAIL-08_20_2024-GO95MLD-1^06245005.0251500 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
427949119-49389-DETAIL-08_20_2024-SVCDEFLC-1^06245005.0251500 | OTHER | FHCA | Distribution | 2024-08-20 | 2027-08-20 | 2
353773709-84109-DETAIL-08_20_2024-GO95MLD-1^06245005.0252400 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
153606109-2649-DETAIL-08_20_2024-SVCDEFLC-1^06245005.0252401 | OTHER | FHCA | Distribution | 2024-08-20 | 2027-08-20 | 2
155378750-71649-DETAIL-08_20_2024-SVCWIND-1^06245005.0252402 | OTHER | FHCA | Distribution | 2024-08-20 | 2027-08-20 | 2
117817019-41649-DETAIL-08_19_2024-GO95HV-1^06245005.0258601 | OTHER | FHCA | Distribution | 2024-08-19 | 2029-08-19 | 3
609502419-90649-DETAIL-08_19_2024-GO95HV-1^06245005.0259600 | OTHER | FHCA | Distribution | 2024-08-19 | 2029-08-19 | 3
195118319-16749-DETAIL-05_22_2023-GO95MLD-1^06245005.0261000 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
195118319-16749-DETAIL-05_22_2023-SVCROAD-1^06245005.0261000 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
462671570-66953-DETAIL-05_22_2023-GO95HV-1^06245005.0262040 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
145988860-36749-DETAIL-05_22_2023-SVCROAD-1^06245005.0263000 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
973422849-55749-DETAIL-05_11_2023-GO95HV-1^06245005.0264000 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
902902149-94109-AUDIT-06_22_2023-GO95HV-1^06245005.0264002 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
978117009-56749-DETAIL-05_22_2023-GUYNOINS-1^06245005.0264003 | ANCHOR/GUY | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
978117009-56749-DETAIL-05_22_2023-GUYNOINS-2^06245005.0264003 | ANCHOR/GUY | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
978117009-56749-DETAIL-05_22_2023-GUYNOINS-3^06245005.0264003 | ANCHOR/GUY | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
609468699-34289-DETAIL-05_22_2023-GO95HV-1^06245005.0264004 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
609468699-34289-DETAIL-05_22_2023-GO95MLD-1^06245005.0264004 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
466108639-74749-DETAIL-05_11_2023-GO95HV-1^06245005.0264201 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
318448550-46279-DETAIL-05_11_2023-GO95MLD-1^06245005.0264300 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
391800845-70845-DETAIL-05_11_2023-GO95MLD-1^06245005.0264500 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
655202409-95649-DETAIL-05_22_2023-GO95MLD-1^06245005.0265000 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
655202409-95649-DETAIL-05_22_2023-SVCWIND-1^06245005.0265000 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
204084229-36649-DETAIL-05_22_2023-GO95MLD-1^06245005.0265001 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
521053460-7649-DETAIL-05_11_2023-GO95MLD-1^06245005.0265300 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
68136649-75649-DETAIL-05_22_2023-SVCWIND-1^06245005.0266000 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
310131970-17953-DETAIL-05_22_2023-SVCDEFLC-1^06245005.0266040 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
59033839-28649-DETAIL-05_11_2023-GUYNOINS-1^06245005.0266900 | ANCHOR/GUY | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
59033839-28649-DETAIL-05_11_2023-GUYNOINS-2^06245005.0266900 | ANCHOR/GUY | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
39030379-55769-DETAIL-05_22_2023-GO95MLD-1^06245005.0272100 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
887587678-89789-DETAIL-05_22_2023-GO95MLD-1^06245005.0274102 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
12876338-82748-DETAIL-05_22_2023-GO95MLD-1^06245005.0276200 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
12876338-82748-DETAIL-05_22_2023-GUYHINS-1^06245005.0276200 | ANCHOR/GUY | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
157497858-9279-DETAIL-05_11_2023-GO95MLD-1^06245005.0276900 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
673491258-57399-DETAIL-05_22_2023-GO95BLTC-1^06245005.0279900 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
673491258-57399-DETAIL-05_22_2023-GO95MLD-1^06245005.0279900 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
806203788-51889-DETAIL-05_22_2023-GO95MLD-1^06245005.0280401 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
806203788-51889-DETAIL-05_22_2023-GRDRODHI-1^06245005.0280401 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
806203788-51889-DETAIL-05_22_2023-GRDRODHI-2^06245005.0280401 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
903379538-32149-DETAIL-05_18_2023-GO95HV-1^06245005.0283901 | OTHER | FHCA | Distribution | 2023-05-18 | 2028-05-18 | 3
995537368-88599-DETAIL-05_18_2023-GO95MLD-1^06245005.0284900 | OTHER | FHCA | Distribution | 2023-05-18 | 2026-05-18 | 2
912693934-41169-DETAIL-05_24_2023-GUYNOINS-1^06245005.0290801 | ANCHOR/GUY | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
864771134-31169-DETAIL-05_24_2023-GO95MLD-1^06245005.0290802 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
338995824-25173-DETAIL-05_24_2023-GO95MLD-1^06245005.0290841 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
522140424-89149-AUDIT-07_05_2023-GO95MLD-1^06245005.0290901 | OTHER | FHCA | Distribution | 2023-07-05 | 2026-07-05 | 2
374329524-23173-DETAIL-05_24_2023-GO95MLD-1^06245005.0290940 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
930994614-29149-DETAIL-05_24_2023-GO95MLD-1^06245005.0291801 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
697988534-36173-DETAIL-05_24_2023-GO95HV-1^06245005.0292841 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
697988534-36173-DETAIL-05_24_2023-GO95MLD-1^06245005.0292841 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
540208234-59173-DETAIL-05_24_2023-GO95MLD-1^06245005.0293841 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
711843105-57105-DETAIL-05_24_2023-GO95TCH-1^06245005.0294800 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
428291644-51199-DETAIL-05_24_2023-GO95HV-1^06245005.0294840 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
428291644-51199-DETAIL-05_24_2023-GO95MLD-1^06245005.0294840 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
428291644-51199-DETAIL-05_24_2023-SVCROAD-1^06245005.0294840 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
795124444-64273-DETAIL-05_24_2023-GO95TCH-1^06245005.0294841 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
241966444-53273-DETAIL-05_24_2023-GO95HV-1^06245005.0294842 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
241966444-53273-DETAIL-05_24_2023-GO95MLD-1^06245005.0294842 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
240089654-7273-DETAIL-05_24_2023-GO95HV-1^06245005.0295840 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
608943844-96273-DETAIL-05_24_2023-GO95MLD-1^06245005.0295841 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
4691764-58149-DETAIL-05_24_2023-GO95HV-1^06245005.0295900 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
606541654-51373-DETAIL-05_24_2023-GO95HV-1^06245005.0296841 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
513773194-1089-DETAIL-05_24_2023-GO95HV-1^06245005.0296900 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
513773194-1089-DETAIL-05_24_2023-GO95MLD-1^06245005.0296900 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
748008254-73373-DETAIL-05_24_2023-GO95MLD-1^06245005.0297840 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
447259454-53373-DETAIL-05_24_2023-GO95HV-1^06245005.0297841 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
39133234-35773-DETAIL-05_24_2023-GRDRODHI-1^06245005.0298500 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
282073864-6373-DETAIL-05_24_2023-GO95CL10-1^06245005.0298841 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
282073864-6373-DETAIL-05_24_2023-GO95MLD-1^06245005.0298841 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
402350164-14373-DETAIL-05_24_2023-GO95MLD-1^06245005.0298842 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
289447329-7353-DETAIL-05_22_2023-GO95HV-1^06245005.0299240 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
731858729-64153-DETAIL-05_22_2023-GO95HV-1^06245005.0299241 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
862372528-93679-DETAIL-05_22_2023-GO95MLD-1^06245005.0299300 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
75165509-2753-DETAIL-05_22_2023-GO95MLD-1^06245005.0299340 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
357404448-14149-DETAIL-05_18_2023-GO95MLD-1^06245005.0299502 | OTHER | FHCA | Distribution | 2023-05-18 | 2026-05-18 | 2
297281818-23149-DETAIL-05_18_2023-GO95MLD-1^06245005.0299601 | OTHER | FHCA | Distribution | 2023-05-18 | 2026-05-18 | 2
988226838-82149-DETAIL-05_18_2023-GO95MLD-1^06245005.0299700 | OTHER | FHCA | Distribution | 2023-05-18 | 2026-05-18 | 2
371117164-47373-DETAIL-05_24_2023-GO95MLD-1^06245005.0299841 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
775376664-16373-DETAIL-05_24_2023-GO95MLD-1^06245005.0299843 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
744077464-84973-DETAIL-07_06_2023-GO95MLD-1^06245005.0300941 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
955662794-61073-DETAIL-07_06_2023-GO95MLD-1^06245005.0303940 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
779941694-81073-AUDIT-07_13_2023-GO95HV-1^06245005.0304941 | OTHER | FHCA | Distribution | 2023-07-13 | 2028-07-13 | 3
793659794-73073-DETAIL-07_06_2023-GO95HV-1^06245005.0305942 | OTHER | FHCA | Distribution | 2023-07-06 | 2028-07-06 | 3
460208914-40249-DETAIL-07_06_2023-GO95MLD-1^06245005.0307900 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
7267814-28073-DETAIL-07_06_2023-GO95MLD-1^06245005.0307940 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
863707714-31173-DETAIL-07_06_2023-GO95MLD-1^06245005.0308940 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
147447004-21169-DETAIL-07_06_2023-GUYNOINS-1^06245005.0309900 | ANCHOR/GUY | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
147447004-21169-DETAIL-07_06_2023-GUYNOINS-2^06245005.0309900 | ANCHOR/GUY | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
887796944-30249-DETAIL-07_06_2023-GO95MLD-1^06245005.0309901 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
330475934-55149-DETAIL-05_22_2023-GO95MLD-1^06245005.0329200 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
61044444-75149-DETAIL-05_22_2023-GO95MLD-1^06245005.0329201 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
511640854-95149-DETAIL-05_22_2023-GO95HV-1^06245005.0329203 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
221161954-98799-DETAIL-05_22_2023-GO95MLD-1^06245005.0329300 | OTHER | FHCA | Distribution | 2023-05-22 | 2026-05-22 | 2
98011564-26149-DETAIL-05_22_2023-GO95HV-1^06245005.0329400 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
124944464-56149-DETAIL-05_22_2023-GO95MLD-1^06245005.0329401 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
186910079-1653-DETAIL-05_22_2023-GO95HV-1^06245005.0337941 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
503255798-90449-DETAIL-05_22_2023-GO95HV-1^06245005.0339904 | OTHER | FHCA | Distribution | 2023-05-22 | 2028-05-22 | 3
817424278-20099-DETAIL-08_14_2024-ABNDEQPM-1^06245005.0341000 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
325416168-13949-DETAIL-08_14_2024-GO95HV-1^06245005.0342000 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
775720468-34599-DETAIL-08_14_2024-GO95MLD-1^06245005.0344001 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
740795698-27949-DETAIL-08_14_2024-GO95HV-1^06245005.0344700 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
437006698-8789-DETAIL-08_14_2024-GO95MLD-1^06245005.0344801 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
916078788-67949-DETAIL-08_14_2024-GO95HV-1^06245005.0344900 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
608451860-97789-DETAIL-08_13_2024-SVCROAD-1^06245005.0353900 | OTHER | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
283729129-19299-DETAIL-08_13_2024-GO95MLD-1^06245005.0354900 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
186557300-68749-DETAIL-08_13_2024-GO95HV-1^06245005.0359600 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
788669501-92579-DETAIL-08_13_2024-GO95HV-1^06245005.0360501 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
788669501-92579-DETAIL-08_13_2024-SVCROAD-1^06245005.0360501 | OTHER | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
867882943-86109-DETAIL-08_14_2024-GO95MLD-1^06245005.0360503 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
867882943-86109-DETAIL-08_14_2024-GUYHINS-1^06245005.0360503 | ANCHOR/GUY | FHCA | Distribution | 2024-08-14 | 2027-08-14 | 2
762645201-19849-DETAIL-08_13_2024-GO95HV-1^06245005.0360506 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
134747980-51949-DETAIL-08_13_2024-GO95HV-1^06245005.0360700 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
484028070-65199-DETAIL-08_14_2024-ABNDEQPM-1^06245005.0360901 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
150681733-75849-DETAIL-08_13_2024-SVCDEFLC-1^06245005.0361101 | OTHER | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
672559733-94849-DETAIL-08_13_2024-GO95MLD-1^06245005.0361102 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
619746411-57849-DETAIL-08_13_2024-GO95HV-1^06245005.0361303 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
313375015-17015-DETAIL-08_13_2024-GO95HV-1^06245005.0361304 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
256608023-99849-DETAIL-08_13_2024-GO95MLD-1^06245005.0361500 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
465966115-97115-DETAIL-08_13_2024-GO95MLD-1^06245005.0362302 | OTHER | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
465966115-97115-DETAIL-08_13_2024-GRDRODHI-1^06245005.0362302 | OTHER | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
221718938-52619-DETAIL-08_13_2024-GUYNOINS-1^06245005.0363301 | ANCHOR/GUY | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
238608215-9215-DETAIL-08_13_2024-GO95MLD-1^06245005.0364300 | OTHER | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
238608215-9215-DETAIL-08_13_2024-GRDRODHI-1^06245005.0364300 | OTHER | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
571678080-31849-DETAIL-08_13_2024-GO95HV-1^06245005.0364303 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
609431760-44089-DETAIL-08_13_2024-GO95MLD-1^06245005.0367400 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
609431760-44089-DETAIL-08_13_2024-GUYHINS-1^06245005.0367400 | ANCHOR/GUY | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
101051463-98879-DETAIL-08_13_2024-GO95MLD-1^06245005.0367401 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
101051463-98879-DETAIL-08_13_2024-GRDRODHI-1^06245005.0367401 | OTHER | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
375387460-69749-AUDIT-09_03_2024-GUYNOINS-1^06245005.0367402 | ANCHOR/GUY | FHCA | Distribution | 2024-09-03 | 2027-09-03 | 2
714441900-9749-DETAIL-08_13_2024-GO95MLD-1^06245005.0368300 | OTHER | FHCA | Distribution | 2024-08-13 | 2029-08-13 | 3
893683283-89749-DETAIL-08_13_2024-GUYLOINS-1^06245005.0368400 | ANCHOR/GUY | FHCA | Distribution | 2024-08-13 | 2027-08-13 | 2
729674629-53499-DETAIL-03_18_2024-GO95MLD-1^06245006.0010703 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
128109878-23699-DETAIL-03_18_2024-GO95MLD-1^06245006.0010901 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
75746568-12349-DETAIL-03_21_2024-GO95MLD-1^06245006.0014000 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
441061738-41699-DETAIL-03_21_2024-GO95MLD-1^06245006.0015000 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
709519558-47982-DETAIL-03_21_2024-SVCDEFLC-1^06245006.0015002 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
1794568-71349-DETAIL-03_14_2024-GO95HV-1^06245006.0015004 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
1794568-71349-DETAIL-03_14_2024-GO95MLD-1^06245006.0015004 | OTHER | FHCA | Distribution | 2024-03-14 | 2027-03-14 | 2
1794568-71349-DETAIL-03_14_2024-GUYNOINS-1^06245006.0015004 | ANCHOR/GUY | FHCA | Distribution | 2024-03-14 | 2027-03-14 | 2
110709778-72899-DETAIL-03_21_2024-GO95HV-1^06245006.0016000 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
311169830-21930-DETAIL-03_14_2024-GO95MLD-1^06245006.0017000 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
572084718-88249-DETAIL-03_14_2024-CLMBTRE-1^06245006.0018001 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
572084718-88249-DETAIL-03_14_2024-GO95MLD-1^06245006.0018001 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
292255415-19772-DETAIL-03_14_2024-GO95MLD-1^06245006.0018100 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
930690925-30349-DETAIL-03_14_2024-GO95MLD-1^06245006.0019101 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
298197625-50349-DETAIL-03_14_2024-GO95MLD-1^06245006.0019200 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
502847218-42449-DETAIL-06_03_2024-SVCROAD-1^06245006.0024000 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2027-06-03 | 2
403594739-76199-DETAIL-06_03_2024-GO95HV-1^06245006.0028700 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
563079219-17349-DETAIL-06_03_2024-GO95HV-1^06245006.0028701 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
856916389-38199-ADMIN-06_03_2024-ABNDEQPM-1^06245006.0029500 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
205691839-83589-DETAIL-06_03_2024-GO95MLD-1^06245006.0029701 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
147729206-13572-DETAIL-06_05_2024-GO95HV-1^06245006.0032040 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
313270816-14572-DETAIL-06_06_2024-GO95MLD-1^06245006.0032140 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
313270816-14572-DETAIL-06_06_2024-SVCENTCO-1^06245006.0032140 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
111097536-27569-DETAIL-06_06_2024-GO95MLD-1^06245006.0035400 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
373560836-77569-DETAIL-06_06_2024-GO95MLD-1^06245006.0036501 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
558336996-97569-DETAIL-06_06_2024-GO95MLD-1^06245006.0036601 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
513494716-1789-DETAIL-06_04_2024-GO95HV-1^06245006.0037000 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
439238588-88588-DETAIL-06_06_2024-ABNDEQPM-1^06245006.0038800 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
439238588-88588-AUDIT-08_06_2024-GO95MLD-1^06245006.0038800 | OTHER | CA-NON-TIER | Distribution | 2024-08-06 | 2029-08-06 | 3
422832427-88099-DTLSB-07_22_2024-GO95MLD-1^06245006.0060000 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2027-07-22 | 2
422832427-88099-DTLSB-07_22_2024-SVCDEFLC-1^06245006.0060000 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2027-07-22 | 2
584782377-67503-DTLSB-07_22_2024-GO95MLD-1^06245006.0060240 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2027-07-22 | 2
686342457-3309-DTLSB-07_22_2024-GO95MLD-1^06245006.0063200 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2027-07-22 | 2
184205097-27103-AUDIT-08_27_2024-GO95MLD-1^06245006.0063541 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
839338838-84203-DTLSB-07_22_2024-GO95MLD-1^06245006.0063940 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2027-07-22 | 2
992496787-12609-DTLSB-09_05_2024-GO95MLD-1^06245006.0072901 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
161384347-28099-DTLSB-09_04_2024-SVCENTCO-1^06245006.0072902 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
55033287-61609-DTLSB-09_04_2024-GO95MLD-1^06245006.0072903 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
748320707-82609-DTLSB-09_05_2024-GRDRODHI-1^06245006.0073800 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
748320707-82609-DTLSB-09_05_2024-GRDRODHI-2^06245006.0073800 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
748320707-82609-DTLSB-09_05_2024-GRDRODHI-3^06245006.0073800 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
680947297-32609-DTLSB-09_05_2024-GO95HV-1^06245006.0073801 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
45362327-13609-DTLSB-09_05_2024-GO95MLD-1^06245006.0074700 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
781769086-31186-DTLSB-09_05_2024-GO95HV-1^06245006.0076500 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
781769086-31186-DTLSB-09_05_2024-GO95MLD-1^06245006.0076500 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
961238097-20199-DTLSB-09_05_2024-CLRTOUCH-1^06245006.0077500 | CONDUCTOR | CA-TIER-2 | Distribution | 2024-09-05 | 2025-09-05 | 2
961238097-20199-DTLSB-09_05_2024-GO95HV-1^06245006.0077500 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
961238097-20199-DTLSB-09_05_2024-GO95MLD-1^06245006.0077500 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
893053737-56979-DETAIL-07_02_2024-GO95MLD-1^06245006.0088801 | OTHER | CA-NON-TIER | Distribution | 2024-07-02 | 2027-07-02 | 2
893053737-56979-DETAIL-07_02_2024-SVCWIND-1^06245006.0088801 | OTHER | CA-NON-TIER | Distribution | 2024-07-02 | 2027-07-02 | 2
248254716-18472-DETAIL-08_08_2024-INSULDMG-1^06245006.0090640 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-08-08 | 2027-08-08 | 2
545720346-84572-DETAIL-08_08_2024-GRDRODHI-1^06245006.0091140 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2027-08-08 | 2
85994036-91572-DETAIL-08_08_2024-INSULDMG-1^06245006.0091340 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-08-08 | 2027-08-08 | 2
464075136-31572-DETAIL-08_08_2024-GO95HV-1^06245006.0091341 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
534479826-70572-DETAIL-08_08_2024-GO95HV-1^06245006.0091440 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
975582916-9472-DETAIL-08_08_2024-INSULDMG-1^06245006.0091541 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-08-08 | 2027-08-08 | 2
982574356-56572-DETAIL-08_08_2024-GO95HV-1^06245006.0092141 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
982574356-56572-DETAIL-08_08_2024-GO95MLD-1^06245006.0092141 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
600990896-61549-DETAIL-08_21_2024-SVCENTCO-1^06245006.0092200 | OTHER | CA-NON-TIER | Distribution | 2024-08-21 | 2027-08-21 | 2
789806476-46609-DETAIL-08_08_2024-GO95MLD-1^06245006.0092701 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
184654766-39572-DETAIL-08_08_2024-GO95HV-1^06245006.0093140 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
307462266-96609-DETAIL-08_08_2024-GO95MLD-1^06245006.0093801 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
137519586-13789-DETAIL-08_08_2024-GO95MLD-1^06245006.0094201 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2027-08-08 | 2
389111266-62179-DETAIL-08_08_2024-GO95MLD-1^06245006.0094800 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2027-08-08 | 2
754341896-5479-DETAIL-08_21_2024-GO95MLD-1^06245006.0095100 | OTHER | CA-NON-TIER | Distribution | 2024-08-21 | 2027-08-21 | 2
887749876-48209-DETAIL-08_08_2024-GO95HV-1^06245006.0095140 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
195650256-77199-DETAIL-08_21_2024-GO95MLD-1^06245006.0095900 | OTHER | CA-NON-TIER | Distribution | 2024-08-21 | 2029-08-21 | 3
195650256-77199-DETAIL-08_21_2024-SVCSVC-1^06245006.0095900 | OTHER | CA-NON-TIER | Distribution | 2024-08-21 | 2027-08-21 | 2
97408796-73672-DETAIL-08_08_2024-GO95MLD-1^06245006.0097140 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
634625896-3672-DETAIL-08_08_2024-GO95HV-1^06245006.0097141 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
335250706-93689-DETAIL-08_08_2024-GRDRODHI-1^06245006.0099140 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2027-08-08 | 2
782306706-15672-DETAIL-08_08_2024-GO95HV-1^06245006.0099141 | OTHER | CA-NON-TIER | Distribution | 2024-08-08 | 2029-08-08 | 3
818665516-85209-DETAIL-08_08_2024-GUYNOINS-1^06245006.0099940 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-08-08 | 2027-08-08 | 2
822357730-25649-DETAIL-08_12_2024-GO95HV-1^06245006.0101401 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
935250260-52799-DETAIL-08_12_2024-GO95MLD-1^06245006.0102400 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
563907868-92369-DETAIL-08_12_2024-GO95MLD-1^06245006.0102403 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
500984359-88183-DETAIL-08_01_2024-GO95MLD-1^06245006.0104002 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
277125960-80789-DETAIL-08_12_2024-GO95MLD-1^06245006.0104901 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
220204820-18549-DETAIL-08_12_2024-GO95MLD-1^06245006.0104902 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
887980298-3689-DETAIL-08_12_2024-GO95MLD-1^06245006.0105001 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
806537670-24549-DETAIL-08_01_2024-GO95HV-1^06245006.0105100 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
608103940-93549-DETAIL-08_01_2024-GO95MLD-1^06245006.0105103 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
656257470-4549-DETAIL-08_06_2024-GO95HV-1^06245006.0105201 | OTHER | CA-NON-TIER | Distribution | 2024-08-06 | 2029-08-06 | 3
656257470-4549-DETAIL-08_06_2024-GO95MLD-1^06245006.0105201 | OTHER | CA-NON-TIER | Distribution | 2024-08-06 | 2029-08-06 | 3
853690780-74549-DETAIL-08_06_2024-GO95MLD-1^06245006.0105301 | OTHER | CA-NON-TIER | Distribution | 2024-08-06 | 2027-08-06 | 2
687395580-25549-DETAIL-08_12_2024-GO95HV-1^06245006.0105402 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
687395580-25549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105402 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2027-08-12 | 2
465495050-55549-DETAIL-08_12_2024-CLMBTRE-1^06245006.0105501 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2027-08-12 | 2
465495050-55549-DETAIL-08_12_2024-GO95HV-1^06245006.0105501 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
27312190-95549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105503 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
842883900-66549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105601 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
138775110-7549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105701 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2027-08-12 | 2
956308610-67549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105800 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2027-08-12 | 2
994226480-33889-DETAIL-08_06_2024-SVCDEFLC-1^06245006.0106101 | OTHER | CA-NON-TIER | Distribution | 2024-08-06 | 2027-08-06 | 2
758913500-78549-DETAIL-08_21_2024-GO95MLD-1^06245006.0108901 | OTHER | CA-NON-TIER | Distribution | 2024-08-21 | 2027-08-21 | 2
15046990-18309-DETAIL-08_21_2024-GO95HV-1^06245006.0109903 | OTHER | CA-NON-TIER | Distribution | 2024-08-21 | 2029-08-21 | 3
15046990-18309-DETAIL-08_21_2024-GO95MLD-1^06245006.0109903 | OTHER | CA-NON-TIER | Distribution | 2024-08-21 | 2029-08-21 | 3
919992698-28449-DETAIL-08_01_2024-GO95HV-1^06245006.0111001 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
454119326-66449-DETAIL-07_29_2024-CONDCOIL-1^06245006.0111700 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
979906526-60089-DETAIL-08_01_2024-INSULDMG-1^06245006.0111800 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
573307416-46449-DETAIL-08_01_2024-INSULDMG-1^06245006.0111801 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
351774945-74449-DETAIL-07_29_2024-GO95MLD-1^06245006.0111902 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
490261355-84449-DETAIL-07_29_2024-GO95HV-1^06245006.0111903 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
319875806-25449-DETAIL-07_29_2024-GO95HV-1^06245006.0111904 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
565478008-97449-DETAIL-08_01_2024-GO95HV-1^06245006.0112001 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
407048235-4449-DETAIL-07_29_2024-GO95HV-1^06245006.0113900 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
818788945-24449-DETAIL-07_29_2024-GO95MLD-1^06245006.0113901 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
641251335-92449-DETAIL-07_22_2024-GO95MLD-1^06245006.0114901 | OTHER | CA-NON-TIER | Distribution | 2024-07-22 | 2029-07-22 | 3
712609835-73449-DETAIL-07_29_2024-GO95HV-1^06245006.0114902 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
451436898-45269-DETAIL-07_29_2024-GO95MLD-1^06245006.0115401 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
474359606-9449-DETAIL-07_29_2024-GO95HV-1^06245006.0115500 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
701449608-44979-DETAIL-07_29_2024-GO95HV-1^06245006.0115501 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
559707106-58449-DETAIL-07_29_2024-GO95MLD-1^06245006.0115502 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
559707106-58449-DETAIL-07_29_2024-GUYHINS-1^06245006.0115502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
633752495-18449-DETAIL-07_22_2024-GO95MLD-1^06245006.0115503 | OTHER | CA-NON-TIER | Distribution | 2024-07-22 | 2029-07-22 | 3
348701085-87449-DETAIL-07_22_2024-GO95HV-1^06245006.0115601 | OTHER | CA-NON-TIER | Distribution | 2024-07-22 | 2029-07-22 | 3
328149738-34569-DETAIL-07_29_2024-SVCDEFLC-1^06245006.0115800 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
130391525-33899-DETAIL-07_29_2024-SVCDEFLC-1^06245006.0115900 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
197842728-52449-DETAIL-07_29_2024-GO95MLD-1^06245006.0115902 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
197842728-52449-DETAIL-07_29_2024-GO95TCH-1^06245006.0115902 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
845638115-61449-DETAIL-07_29_2024-GO95HV-1^06245006.0116900 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
46673015-21449-DETAIL-07_29_2024-GO95MLD-1^06245006.0117900 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
597490205-49989-DETAIL-07_29_2024-CONDFRAY-1^06245006.0118900 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
514653269-23913-DETAIL-03_11_2024-GO95MLD-1^06245006.0120040 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
9525169-913-DETAIL-03_11_2024-GO95HV-1^06245006.0120041 | OTHER | FHCA | Distribution | 2024-03-11 | 2029-03-11 | 3
779128438-14349-DETAIL-03_14_2024-ENCHRW-1^06245006.0120900 | OTHER | FHCA | Distribution | 2024-03-14 | 2027-03-14 | 2
897067295-63349-DETAIL-03_14_2024-GO95MLD-1^06245006.0120901 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
268433438-93438-DETAIL-03_11_2024-GO95HV-1^06245006.0121001 | OTHER | FHCA | Distribution | 2024-03-11 | 2029-03-11 | 3
849214516-21249-DETAIL-03_11_2024-GO95MLD-1^06245006.0121101 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
321263826-71249-DETAIL-03_11_2024-GO95MLD-1^06245006.0121200 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
281795936-72249-DETAIL-03_11_2024-GO95MLD-1^06245006.0122300 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
746304146-13249-DETAIL-03_11_2024-GO95MLD-1^06245006.0123400 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
853248946-63249-DETAIL-03_11_2024-GO95MLD-1^06245006.0123500 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
89028965-52349-DETAIL-03_14_2024-GO95HV-1^06245006.0123900 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
424203856-75249-DETAIL-03_11_2024-GO95MLD-1^06245006.0124501 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
878717655-51349-DETAIL-03_14_2024-GO95HV-1^06245006.0124900 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
878717655-51349-DETAIL-03_14_2024-GO95MLD-1^06245006.0124900 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
21669166-16249-DETAIL-03_11_2024-GO95HV-1^06245006.0125600 | OTHER | FHCA | Distribution | 2024-03-11 | 2029-03-11 | 3
21669166-16249-DETAIL-03_11_2024-GO95MLD-1^06245006.0125600 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
989802245-11349-DETAIL-03_14_2024-GO95HV-1^06245006.0125900 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
811964866-889-DETAIL-03_14_2024-GO95MLD-1^06245006.0126602 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
529696256-83249-DETAIL-03_14_2024-SVCDEFLC-1^06245006.0126604 | OTHER | FHCA | Distribution | 2024-03-14 | 2027-03-14 | 2
699927935-55872-DETAIL-03_14_2024-GO95MLD-1^06245006.0126901 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
868907936-44972-DETAIL-03_18_2024-SVCDEFLC-1^06245006.0127602 | OTHER | FHCA | Distribution | 2024-03-18 | 2027-03-18 | 2
706855726-93989-DETAIL-03_18_2024-GO95MLD-1^06245006.0127604 | OTHER | FHCA | Distribution | 2024-03-18 | 2027-03-18 | 2
728155336-54249-DETAIL-03_18_2024-SVCDEFLC-1^06245006.0127700 | OTHER | FHCA | Distribution | 2024-03-18 | 2027-03-18 | 2
843346816-84249-DETAIL-03_14_2024-GO95HV-1^06245006.0127701 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
734433216-8179-DETAIL-03_18_2024-GO95MLD-1^06245006.0127702 | OTHER | FHCA | Distribution | 2024-03-18 | 2027-03-18 | 2
703110496-87249-DETAIL-03_18_2024-GO95MLD-1^06245006.0127900 | OTHER | FHCA | Distribution | 2024-03-18 | 2027-03-18 | 2
139817135-1349-DETAIL-03_14_2024-GO95HV-1^06245006.0127902 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
842904418-65279-DETAIL-03_14_2024-GO95MLD-1^06245006.0127904 | OTHER | FHCA | Distribution | 2024-03-14 | 2029-03-14 | 3
842904418-65279-DETAIL-03_14_2024-GUYHINS-1^06245006.0127904 | ANCHOR/GUY | FHCA | Distribution | 2024-03-14 | 2027-03-14 | 2
323795488-54982-DETAIL-03_11_2024-GO95HV-1^06245006.0127941 | OTHER | FHCA | Distribution | 2024-03-11 | 2029-03-11 | 3
323795488-54982-DETAIL-03_11_2024-GO95MLD-1^06245006.0127941 | OTHER | FHCA | Distribution | 2024-03-11 | 2027-03-11 | 2
776746876-47249-DETAIL-03_18_2024-GO95HV-1^06245006.0128804 | OTHER | FHCA | Distribution | 2024-03-18 | 2029-03-18 | 3
776746876-47249-DETAIL-03_18_2024-GO95MLD-1^06245006.0128804 | OTHER | FHCA | Distribution | 2024-03-18 | 2027-03-18 | 2
232534459-67813-DETAIL-05_04_2023-GO95MLD-1^06245006.0130940 | OTHER | CA-NON-TIER | Distribution | 2023-05-04 | 2028-05-04 | 3
788919728-55349-DETAIL-05_04_2023-GO95HV-1^06245006.0135701 | OTHER | FHCA | Distribution | 2023-05-04 | 2028-05-04 | 3
424422808-16349-DETAIL-05_04_2023-GO95HV-1^06245006.0135800 | OTHER | FHCA | Distribution | 2023-05-04 | 2028-05-04 | 3
949841108-10299-DETAIL-05_04_2023-GO95MLD-1^06245006.0135900 | OTHER | FHCA | Distribution | 2023-05-04 | 2026-05-04 | 2
905280079-53013-DETAIL-05_04_2023-GO95HV-1^06245006.0135940 | OTHER | FHCA | Distribution | 2023-05-04 | 2028-05-04 | 3
171116778-12379-DETAIL-05_04_2023-GO95MLD-1^06245006.0136500 | OTHER | FHCA | Distribution | 2023-05-04 | 2026-05-04 | 2
393419778-81899-DETAIL-05_04_2023-GO95MLD-1^06245006.0136600 | OTHER | FHCA | Distribution | 2023-05-04 | 2026-05-04 | 2
226394964-72064-DETAIL-05_04_2023-GO95MLD-1^06245006.0136940 | OTHER | FHCA | Distribution | 2023-05-04 | 2026-05-04 | 2
414207688-4969-DETAIL-05_11_2023-GO95HV-1^06245006.0139001 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
414207688-4969-AUDIT-07_13_2023-GO95BLTC-1^06245006.0139001 | OTHER | FHCA | Distribution | 2023-07-13 | 2028-07-13 | 3
682831193-11343-DETAIL-05_04_2023-GO95MLD-1^06245006.0139940 | OTHER | FHCA | Distribution | 2023-05-04 | 2028-05-04 | 3
664661458-32289-DETAIL-08_12_2024-GUYHINS-1^06245006.0140200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-08-12 | 2027-08-12 | 2
361811708-3849-DETAIL-08_12_2024-INSULDMG-1^06245006.0140401 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-08-12 | 2027-08-12 | 2
990047329-20399-DETAIL-08_01_2024-GO95HV-1^06245006.0140900 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
990047329-20399-DETAIL-08_01_2024-GUYHINS-1^06245006.0140900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
764022569-74713-DETAIL-07_23_2024-ABNDEQPM-1^06245006.0141001 | OTHER | FHCA | Distribution | 2024-07-23 | 2029-07-23 | 3
793534019-18169-DETAIL-07_23_2024-GO95MLD-1^06245006.0141002 | OTHER | FHCA | Distribution | 2024-07-23 | 2027-07-23 | 2
792363429-51913-DETAIL-07_23_2024-GO95MLD-1^06245006.0142041 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2027-07-23 | 2
959873208-78799-DETAIL-07_23_2024-GO95MLD-1^06245006.0143000 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2027-07-23 | 2
959873208-78799-DETAIL-07_23_2024-GRDRODHI-1^06245006.0143000 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2027-07-23 | 2
26905518-63449-DETAIL-07_23_2024-SVCDEFLC-1^06245006.0143001 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2027-07-23 | 2
996229348-43449-DETAIL-07_23_2024-SVCENTCO-1^06245006.0143100 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2027-07-23 | 2
850305789-85813-AUDIT-09_03_2024-CONDFRAY-1^06245006.0143140 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-09-03 | 2027-09-03 | 2
850305789-85813-AUDIT-09_03_2024-CONDFRAY-2^06245006.0143140 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-09-03 | 2027-09-03 | 2
850305789-85813-AUDIT-09_03_2024-INSULDMG-1^06245006.0143140 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-09-03 | 2027-09-03 | 2
482941889-17813-DETAIL-07_23_2024-GO95MLD-1^06245006.0144241 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2029-07-23 | 3
786104779-62013-DETAIL-07_23_2024-GO95HV-1^06245006.0144442 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2029-07-23 | 3
609229889-29013-DETAIL-07_23_2024-GO95HV-1^06245006.0144540 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2029-07-23 | 3
904800769-37913-DETAIL-07_23_2024-ABNDEQPM-1^06245006.0145341 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2029-07-23 | 3
137492579-84013-DETAIL-07_23_2024-GO95MLD-1^06245006.0145342 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2029-07-23 | 3
310944999-81113-DETAIL-07_23_2024-GO95MLD-1^06245006.0146441 | OTHER | CA-NON-TIER | Distribution | 2024-07-23 | 2027-07-23 | 2
310944999-81113-DETAIL-07_23_2024-INSULDMG-1^06245006.0146441 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-07-23 | 2027-07-23 | 2
310944999-81113-DETAIL-07_23_2024-INSULDMG-2^06245006.0146441 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-07-23 | 2027-07-23 | 2
592108809-50213-DETAIL-07_29_2024-GO95HV-1^06245006.0147540 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
592108809-50213-DETAIL-07_29_2024-GO95MLD-1^06245006.0147540 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
950595619-33213-DETAIL-07_29_2024-GO95MLD-1^06245006.0147640 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
720822409-9789-DETAIL-07_29_2024-GO95MLD-1^06245006.0148401 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
613995319-74213-DETAIL-07_29_2024-GO95MLD-1^06245006.0148641 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
415662249-30313-AUDIT-09_03_2024-CONDFRAY-1^06245006.0148740 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-09-03 | 2027-09-03 | 2
909922129-46213-DETAIL-07_29_2024-GO95MLD-1^06245006.0148741 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
909922129-46213-DETAIL-07_29_2024-GRDRODHI-1^06245006.0148741 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
909922129-46213-DETAIL-07_29_2024-INSULDMG-1^06245006.0148741 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-07-29 | 2027-07-29 | 2
140119638-36989-DETAIL-07_29_2024-GO95MLD-1^06245006.0149701 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
523526449-93713-DETAIL-07_29_2024-GO95MLD-1^06245006.0149841 | OTHER | CA-NON-TIER | Distribution | 2024-07-29 | 2029-07-29 | 3
331179158-2179-DETAIL-08_01_2024-GO95MLD-1^06245006.0151400 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
510959010-90110-DETAIL-08_01_2024-GO95HV-1^06245006.0152900 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
587290538-66689-DETAIL-08_01_2024-SVCROAD-1^06245006.0153400 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
216121388-53299-DETAIL-08_01_2024-GO95MLD-1^06245006.0154701 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
51851028-8899-DETAIL-08_06_2024-GO95MLD-1^06245006.0155002 | OTHER | CA-NON-TIER | Distribution | 2024-08-06 | 2029-08-06 | 3
348203059-59183-DETAIL-08_06_2024-GO95MLD-1^06245006.0155100 | OTHER | CA-NON-TIER | Distribution | 2024-08-06 | 2029-08-06 | 3
409303138-25999-DETAIL-08_01_2024-GO95MLD-1^06245006.0155103 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
296112238-74849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155104 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
762895438-5999-DETAIL-08_01_2024-SVCROAD-1^06245006.0155201 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
791774398-59749-DETAIL-08_12_2024-XARMSPCR-1^06245006.0155301 | CROSSARM | CA-NON-TIER | Distribution | 2024-08-12 | 2027-08-12 | 2
209468358-25849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155302 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
706719718-67849-DETAIL-08_01_2024-GO95HV-1^06245006.0155401 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
706719718-67849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155401 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
685440078-55999-DETAIL-08_01_2024-GO95MLD-1^06245006.0155502 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
470284088-97849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155601 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
555150588-69849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155700 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
424346098-99849-DETAIL-08_01_2024-GO95HV-1^06245006.0155800 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2029-08-01 | 3
628549398-30949-DETAIL-08_01_2024-GO95MLD-1^06245006.0155801 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
453827998-40949-DETAIL-08_01_2024-GO95MLD-1^06245006.0155900 | OTHER | CA-NON-TIER | Distribution | 2024-08-01 | 2027-08-01 | 2
848225498-91849-DETAIL-08_12_2024-GO95HV-1^06245006.0159300 | OTHER | CA-NON-TIER | Distribution | 2024-08-12 | 2029-08-12 | 3
630260598-94299-ADMIN-07_01_2024-ABNDEQPM-1^06245006.0180000 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
630260598-94299-DTLSB-07_01_2024-GO95HV-1^06245006.0180000 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
630260598-94299-DTLSB-07_01_2024-GO95MLD-1^06245006.0180000 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2027-07-01 | 2
302386598-31269-DTLSB-07_01_2024-GO95HV-1^06245006.0180001 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
302386598-31269-DTLSB-07_01_2024-GO95MLD-1^06245006.0180001 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
243465698-24299-DTLSB-07_01_2024-GO95MLD-1^06245006.0180003 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
468328708-96579-DTLSB-07_01_2024-GO95MLD-1^06245006.0181002 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2027-07-01 | 2
886144718-6299-DTLSB-07_02_2024-GO95MLD-1^06245006.0182001 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2027-07-02 | 2
982591528-27299-DTLSB-07_02_2024-INSULDMG-1^06245006.0183000 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-07-02 | 2025-07-02 | 2
982591528-27299-DTLSB-07_02_2024-RISEGRD-1^06245006.0183000 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2027-07-02 | 2
477084618-7299-DTLSB-07_02_2024-GO95MLD-1^06245006.0183100 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2029-07-02 | 3
421110088-90749-DTLSB-07_02_2024-GO95MLD-1^06245006.0183101 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2027-07-02 | 2
683828248-67299-DTLSB-07_02_2024-GUYNOINS-1^06245006.0184101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-07-02 | 2027-07-02 | 2
832429398-70489-DTLSB-07_02_2024-GO95HV-1^06245006.0184600 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2029-07-02 | 3
614757009-56669-DTLSB-07_02_2024-GO95HV-1^06245006.0184700 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2029-07-02 | 3
342302408-78299-DTLSB-07_02_2024-CUTOUTAR-2^06245006.0185101 | LIGHTNING ARRESTER | CA-TIER-2 | Distribution | 2024-07-02 | 2025-07-02 | 2
342302408-78299-DTLSB-07_02_2024-GO95MLD-1^06245006.0185101 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2027-07-02 | 2
342302408-78299-DTLSB-07_02_2024-GO95MLD-2^06245006.0185101 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2027-07-02 | 2
854663658-99299-DTLSB-07_02_2024-GO95MLD-1^06245006.0185200 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2029-07-02 | 3
643554628-12399-DTLSB-07_02_2024-GO95HV-1^06245006.0185601 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2029-07-02 | 3
980051188-14499-DTLSB-07_02_2024-GO95HV-1^06245006.0186201 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2029-07-02 | 3
980051188-14499-DTLSB-07_02_2024-GO95MLD-1^06245006.0186201 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2027-07-02 | 2
996801898-70399-DTLSB-07_02_2024-GO95HV-1^06245006.0186301 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2029-07-02 | 3
468441008-76089-DTLSB-07_02_2024-GO95HV-1^06245006.0186401 | OTHER | CA-TIER-2 | Distribution | 2024-07-02 | 2029-07-02 | 3
152275368-25399-DTLSB-07_02_2024-GO95MLD-1^06245006.0187200 | OTHER | FHCA | Distribution | 2024-07-02 | 2027-07-02 | 2
605896388-93399-DTLSB-07_02_2024-GO95HV-1^06245006.0188500 | OTHER | FHCA | Distribution | 2024-07-02 | 2029-07-02 | 3
466158954-38749-DETAIL-05_08_2023-GO95MLD-1^06245006.0213601 | OTHER | FHCA | Distribution | 2023-05-08 | 2026-05-08 | 2
634143415-8473-DETAIL-05_08_2023-GO95MLD-1^06245006.0215040 | OTHER | FHCA | Distribution | 2023-05-08 | 2026-05-08 | 2
584861015-37473-DETAIL-05_08_2023-GO95HV-1^06245006.0215140 | OTHER | FHCA | Distribution | 2023-05-08 | 2028-05-08 | 3
584861015-37473-DETAIL-05_08_2023-GO95MLD-1^06245006.0215140 | OTHER | FHCA | Distribution | 2023-05-08 | 2026-05-08 | 2
584861015-37473-AUDIT-07_25_2023-RISECLMB-1^06245006.0215140 | OTHER | FHCA | Distribution | 2023-07-25 | 2026-07-25 | 2
751409105-53473-DETAIL-05_11_2023-GO95HV-1^06245006.0216040 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
751409105-53473-DETAIL-05_11_2023-GO95MLD-1^06245006.0216040 | OTHER | FHCA | Distribution | 2023-05-11 | 2026-05-11 | 2
678011425-78473-DETAIL-05_11_2023-GO95HV-1^06245006.0216041 | OTHER | FHCA | Distribution | 2023-05-11 | 2028-05-11 | 3
798921216-46149-DETAIL-04_05_2023-GUYHINS-1^06245006.0220000 | ANCHOR/GUY | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
309441999-40289-DETAIL-04_04_2023-GO95MLD-1^06245006.0220100 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
309441999-40289-DETAIL-04_04_2023-SVCNEUT-1^06245006.0220100 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
373944299-54149-DETAIL-04_04_2023-GO95MLD-1^06245006.0220204 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
884674538-37538-DETAIL-04_04_2023-GO95MLD-1^06245006.0221300 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
686784991-93993-DETAIL-04_03_2023-SVCROAD-1^06245006.0222000 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
659080761-25049-DETAIL-04_04_2023-SVCROAD-1^06245006.0222002 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
79644090-97889-DETAIL-04_04_2023-GO95MLD-1^06245006.0222004 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
978741810-28699-DETAIL-04_03_2023-GO95MLD-1^06245006.0222101 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
978741810-28699-DETAIL-04_03_2023-GUYHINS-1^06245006.0222101 | ANCHOR/GUY | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
978741810-28699-DETAIL-04_03_2023-GUYHINS-2^06245006.0222101 | ANCHOR/GUY | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
678016910-42049-DETAIL-04_03_2023-GO95MLD-1^06245006.0222104 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
34150691-41599-DETAIL-04_03_2023-GO95MLD-1^06245006.0222105 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
975903079-62613-DETAIL-04_03_2023-ABNDEQPM-1^06245006.0222140 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
555312789-85379-DETAIL-04_04_2023-GO95MLD-1^06245006.0222141 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
555312789-85379-DETAIL-04_04_2023-GO95TCH-1^06245006.0222141 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
999047208-78013-DETAIL-04_03_2023-GO95HV-1^06245006.0222143 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
711980799-913-DETAIL-04_03_2023-GO95MLD-1^06245006.0222144 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
711980799-913-DETAIL-04_03_2023-SVCENTCO-1^06245006.0222144 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
17821501-28049-DETAIL-04_04_2023-SVCDEFLC-1^06245006.0222202 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
384108609-60613-DETAIL-04_04_2023-GUYHINS-1^06245006.0222243 | ANCHOR/GUY | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
273682099-16513-DETAIL-04_04_2023-GRDRODHI-1^06245006.0222244 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
626635981-31149-DETAIL-04_04_2023-GO95MLD-1^06245006.0222300 | OTHER | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
139598001-70149-DETAIL-04_04_2023-GO95MLD-1^06245006.0222400 | OTHER | FHCA | Distribution | 2023-04-04 | 2028-04-04 | 3
139598001-70149-DETAIL-04_04_2023-GUYLOINS-1^06245006.0222400 | ANCHOR/GUY | FHCA | Distribution | 2023-04-04 | 2026-04-04 | 2
328059771-1149-DETAIL-04_04_2023-GO95HV-1^06245006.0222401 | OTHER | FHCA | Distribution | 2023-04-04 | 2028-04-04 | 3
607035940-78593-DETAIL-04_03_2023-GO95MLD-1^06245006.0223001 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
835940449-79913-DETAIL-04_03_2023-GO95MLD-1^06245006.0223041 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
282385369-91313-DETAIL-04_03_2023-GO95HV-1^06245006.0223042 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
363401959-50313-DETAIL-04_03_2023-GO95MLD-1^06245006.0223043 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
373792966-25966-DETAIL-04_03_2023-GO95MLD-1^06245006.0223045 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
790273793-6303-DETAIL-04_03_2023-GO95MLD-1^06245006.0223046 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
790273793-6303-AUDIT-05_04_2023-GO95HV-1^06245006.0223046 | OTHER | FHCA | Distribution | 2023-05-04 | 2028-05-04 | 3
461433980-93323-DETAIL-04_05_2023-GO95MLD-1^06245006.0223047 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
705252699-17613-DETAIL-04_03_2023-GO95MLD-1^06245006.0223140 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
119731959-78513-DETAIL-04_03_2023-GO95HV-1^06245006.0223141 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
119731959-78513-DETAIL-04_03_2023-GO95TCH-1^06245006.0223141 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
119731959-78513-DETAIL-04_03_2023-GUYHINS-1^06245006.0223141 | ANCHOR/GUY | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
119731959-78513-DETAIL-04_03_2023-GUYHINS-2^06245006.0223141 | ANCHOR/GUY | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
123053179-28413-DETAIL-04_03_2023-GO95HV-1^06245006.0223142 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
965567459-45413-DETAIL-04_03_2023-GUYHINS-1^06245006.0223143 | ANCHOR/GUY | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
678474569-86413-DETAIL-04_03_2023-GUYHINS-1^06245006.0223144 | ANCHOR/GUY | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
678474569-86413-AUDIT-06_12_2023-SVCENTCO-1^06245006.0223144 | OTHER | FHCA | Distribution | 2023-06-12 | 2026-06-12 | 2
466480420-33049-DETAIL-04_03_2023-GO95TCH-1^06245006.0223200 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
266408589-63513-DETAIL-04_03_2023-GO95MLD-1^06245006.0223241 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
597863379-40513-DETAIL-04_03_2023-GO95MLD-1^06245006.0223242 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
553170638-94228-DETAIL-04_13_2023-GO95MLD-1^06245006.0223400 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
553170638-94228-DETAIL-04_13_2023-GRDRODHI-1^06245006.0223400 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
718785988-77949-DETAIL-04_13_2023-ENCHRW-1^06245006.0223800 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
337862978-24999-DETAIL-04_13_2023-GO95TCH-1^06245006.0223801 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
506450511-39293-DETAIL-04_05_2023-GO95MLD-1^06245006.0224000 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
185009460-55199-DETAIL-04_03_2023-GO95MLD-1^06245006.0224002 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
296070141-56693-DETAIL-04_03_2023-SVCWIND-1^06245006.0224100 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
305662060-32379-DETAIL-04_03_2023-GO95MLD-1^06245006.0224101 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
670342880-71093-DETAIL-04_03_2023-GO95HV-1^06245006.0224102 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
670342880-71093-DETAIL-04_03_2023-GO95MLD-1^06245006.0224102 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
873281880-71049-DETAIL-04_03_2023-GO95MLD-1^06245006.0224103 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
673855570-71799-DETAIL-04_03_2023-GO95MLD-1^06245006.0224104 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
78299861-50569-DETAIL-04_03_2023-GO95HV-1^06245006.0224200 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
992085140-65309-DETAIL-04_03_2023-GO95MLD-1^06245006.0224203 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
757270250-31799-DETAIL-04_06_2023-GO95MLD-1^06245006.0224300 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
757270250-31799-DETAIL-04_06_2023-SVCENTCO-1^06245006.0224300 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
992184221-69049-DETAIL-04_13_2023-GO95MLD-1^06245006.0224400 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
615690711-2979-DETAIL-04_13_2023-GO95TCH-1^06245006.0224401 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
727212698-32789-DETAIL-04_13_2023-GO95HV-1^06245006.0224900 | OTHER | FHCA | Distribution | 2023-04-13 | 2028-04-13 | 3
837186865-98865-DETAIL-04_05_2023-GO95MLD-1^06245006.0225001 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
675578281-58553-DETAIL-04_05_2023-GO95HV-1^06245006.0225040 | OTHER | FHCA | Distribution | 2023-04-05 | 2028-04-05 | 3
675578281-58553-DETAIL-04_05_2023-GO95TCH-1^06245006.0225040 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
675578281-58553-DETAIL-04_05_2023-SVCWIND-1^06245006.0225040 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
240640030-82249-DETAIL-04_06_2023-GO95HV-1^06245006.0225401 | OTHER | FHCA | Distribution | 2023-04-06 | 2028-04-06 | 3
944759608-49-DETAIL-04_13_2023-GO95MLD-1^06245006.0225503 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
862312818-15949-DETAIL-04_06_2023-GO95MLD-1^06245006.0225504 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
88703018-23783-DETAIL-04_13_2023-GO95MLD-1^06245006.0225540 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
890944418-9949-DETAIL-04_06_2023-GO95HV-1^06245006.0225602 | OTHER | FHCA | Distribution | 2023-04-06 | 2028-04-06 | 3
890944418-9949-DETAIL-04_06_2023-GO95MLD-1^06245006.0225602 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
127756308-59949-DETAIL-04_06_2023-GO95MLD-1^06245006.0225603 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
970381158-38999-DETAIL-04_13_2023-GO95MLD-1^06245006.0225900 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
895712648-46949-DETAIL-04_13_2023-GO95MLD-1^06245006.0225901 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
814379928-27499-DETAIL-04_06_2023-GO95HV-1^06245006.0225905 | OTHER | FHCA | Distribution | 2023-04-06 | 2028-04-06 | 3
814379928-27499-DETAIL-04_06_2023-GO95MLD-1^06245006.0225905 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
593500979-98149-DETAIL-04_05_2023-SVCRUBLG-1^06245006.0226000 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
593500979-98149-DETAIL-04_05_2023-SVCWIND-1^06245006.0226000 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
206564949-85089-DETAIL-04_05_2023-GO95MLD-1^06245006.0226003 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
89006345-27345-DETAIL-04_05_2023-GO95MLD-1^06245006.0226007 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
5136791-20653-DETAIL-04_05_2023-GO95TCH-1^06245006.0226040 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
410915829-90343-DETAIL-04_05_2023-GO95MLD-1^06245006.0226100 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
999092901-90653-DETAIL-04_05_2023-GUYHINS-1^06245006.0226140 | ANCHOR/GUY | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
661358761-32053-DETAIL-04_05_2023-GO95MLD-1^06245006.0226141 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
288282601-32653-DETAIL-04_05_2023-GO95MLD-1^06245006.0226142 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
284223011-73653-DETAIL-04_05_2023-SVCROAD-1^06245006.0226143 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
438181621-5653-DETAIL-04_05_2023-GO95MLD-1^06245006.0226144 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
811146621-75653-DETAIL-04_05_2023-GO95MLD-1^06245006.0226240 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
811146621-75653-DETAIL-04_05_2023-SVCENTCO-1^06245006.0226240 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
58930148-74949-DETAIL-04_06_2023-GO95MLD-1^06245006.0226500 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
592236159-78149-DETAIL-05_16_2023-GO95HV-1^06245006.0227001 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
592236159-78149-DETAIL-05_16_2023-GO95MLD-1^06245006.0227001 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
929161001-59149-DETAIL-04_05_2023-SVCENTCO-1^06245006.0227240 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
801409051-39149-DETAIL-04_05_2023-GO95MLD-1^06245006.0227241 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
94376963-83679-DETAIL-04_05_2023-GO95MLD-1^06245006.0227301 | OTHER | FHCA | Distribution | 2023-04-05 | 2028-04-05 | 3
167399871-59889-DETAIL-04_05_2023-GO95MLD-1^06245006.0227302 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
214182219-7099-DETAIL-04_05_2023-GO95MLD-1^06245006.0227304 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
183576209-71249-DETAIL-04_05_2023-GUYNOINS-1^06245006.0227305 | ANCHOR/GUY | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
183576209-71249-DETAIL-04_05_2023-GUYNOINS-2^06245006.0227305 | ANCHOR/GUY | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
475997081-52789-DETAIL-04_13_2023-GO95MLD-1^06245006.0227306 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
135997880-86179-DETAIL-04_13_2023-GO95CL10-1^06245006.0227401 | OTHER | FHCA | Distribution | 2023-04-13 | 2028-04-13 | 3
135997880-86179-DETAIL-04_13_2023-GO95MLD-1^06245006.0227401 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
337341710-12249-DETAIL-04_13_2023-GO95HV-1^06245006.0227402 | OTHER | FHCA | Distribution | 2023-04-13 | 2028-04-13 | 3
665954129-5943-DETAIL-04_06_2023-GO95MLD-1^06245006.0227403 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
194473391-61499-DETAIL-04_13_2023-GO95TCH-1^06245006.0228001 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
783232209-54073-DETAIL-04_13_2023-GO95MLD-1^06245006.0228002 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
404591850-58149-DETAIL-04_13_2023-GO95MLD-1^06245006.0228003 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
253039689-40789-DETAIL-04_13_2023-GO95MLD-1^06245006.0228004 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
253039689-40789-DETAIL-04_13_2023-SVCROAD-1^06245006.0228004 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
253039689-40789-DETAIL-04_13_2023-SVCROAD-2^06245006.0228004 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
761952779-97149-DETAIL-04_13_2023-GO95MLD-1^06245006.0228005 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
631935791-77149-DETAIL-04_13_2023-GO95MLD-1^06245006.0228006 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
886752719-81579-DETAIL-04_05_2023-GO95MLD-1^06245006.0228302 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
68052340-31249-DETAIL-04_13_2023-GO95MLD-1^06245006.0228401 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
38837879-18889-DETAIL-04_13_2023-GO95MLD-1^06245006.0228404 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
10778088-32983-DETAIL-04_13_2023-GO95MLD-1^06245006.0228541 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
41263240-31579-DETAIL-04_13_2023-GO95MLD-1^06245006.0229000 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
626847999-13489-DETAIL-04_13_2023-GO95MLD-1^06245006.0229001 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
964322041-57599-DETAIL-04_13_2023-GO95HV-1^06245006.0229002 | OTHER | FHCA | Distribution | 2023-04-13 | 2028-04-13 | 3
964322041-57599-DETAIL-04_13_2023-GO95MLD-1^06245006.0229002 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
478043771-85899-DETAIL-04_13_2023-GO95MLD-1^06245006.0229004 | OTHER | FHCA | Distribution | 2023-04-13 | 2028-04-13 | 3
359740233-2233-DETAIL-04_05_2023-GO95HV-1^06245006.0229100 | OTHER | FHCA | Distribution | 2023-04-05 | 2028-04-05 | 3
359740233-2233-DETAIL-04_05_2023-GO95MLD-1^06245006.0229100 | OTHER | FHCA | Distribution | 2023-04-05 | 2026-04-05 | 2
964620121-86489-DETAIL-04_05_2023-ABNDEQPM-1^06245006.0229201 | OTHER | FHCA | Distribution | 2023-04-05 | 2028-04-05 | 3
386025971-11249-DETAIL-04_13_2023-GO95MLD-1^06245006.0229300 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
491466248-4949-DETAIL-04_13_2023-GO95MLD-1^06245006.0229600 | OTHER | FHCA | Distribution | 2023-04-13 | 2028-04-13 | 3
719732908-21783-DETAIL-04_13_2023-GO95MLD-1^06245006.0229640 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
614141708-10783-DETAIL-04_13_2023-GO95MLD-1^06245006.0229641 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
903939218-32783-DETAIL-04_13_2023-GO95MLD-1^06245006.0229740 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
655524118-31089-DETAIL-07_03_2023-GO95BLTC-1^06245006.0230100 | OTHER | FHCA | Distribution | 2023-07-03 | 2028-07-03 | 3
655524118-31089-DETAIL-07_03_2023-GO95TCH-1^06245006.0230100 | OTHER | FHCA | Distribution | 2023-07-03 | 2026-07-03 | 2
133428108-10589-DETAIL-07_03_2023-GO95BLTC-1^06245006.0230200 | OTHER | FHCA | Distribution | 2023-07-03 | 2028-07-03 | 3
133428108-10589-DETAIL-07_03_2023-GO95MLD-1^06245006.0230200 | OTHER | FHCA | Distribution | 2023-07-03 | 2026-07-03 | 2
133428108-10589-DETAIL-07_03_2023-GO95MLD-2^06245006.0230200 | OTHER | FHCA | Distribution | 2023-07-03 | 2026-07-03 | 2
457408313-2343-DETAIL-06_22_2023-GO95HV-1^06245006.0230740 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
23212028-42179-DETAIL-06_22_2023-GO95MLD-1^06245006.0230800 | OTHER | FHCA | Distribution | 2023-06-22 | 2028-06-22 | 3
984387023-41399-DETAIL-07_03_2023-GO95MLD-1^06245006.0230801 | OTHER | FHCA | Distribution | 2023-07-03 | 2028-07-03 | 3
342225499-76449-DETAIL-07_03_2023-GO95MLD-1^06245006.0230900 | OTHER | FHCA | Distribution | 2023-07-03 | 2026-07-03 | 2
400777438-72289-DETAIL-07_07_2023-GO95MLD-1^06245006.0230901 | OTHER | FHCA | Distribution | 2023-07-07 | 2026-07-07 | 2
419773248-82079-DETAIL-07_03_2023-GO95MLD-1^06245006.0231101 | OTHER | FHCA | Distribution | 2023-07-03 | 2026-07-03 | 2
854863928-26449-DETAIL-06_22_2023-GO95MLD-1^06245006.0231800 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
771069329-27813-DETAIL-06_22_2023-GO95MLD-1^06245006.0231840 | OTHER | FHCA | Distribution | 2023-06-22 | 2026-06-22 | 2
70319659-42789-DETAIL-07_06_2023-GO95MLD-1^06245006.0231902 | OTHER | FHCA | Distribution | 2023-07-06 | 2026-07-06 | 2
759369038-43349-DETAIL-07_03_2023-GO95HV-1^06245006.0232000 | OTHER | FHCA | Distribution | 2023-07-03 | 2028-07-03 | 3
702536518-60379-DETAIL-07_07_2023-GO95TCH-1^06245006.0232902 | OTHER | FHCA | Distribution | 2023-07-07 | 2026-07-07 | 2
732499508-42349-DETAIL-04_18_2023-GO95TCH-1^06245006.0240000 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
630004259-79349-DETAIL-05_16_2023-GO95MLD-1^06245006.0240900 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
276445278-61689-DETAIL-04_18_2023-GO95HV-1^06245006.0242000 | OTHER | FHCA | Distribution | 2023-04-18 | 2028-04-18 | 3
276445278-61689-DETAIL-04_18_2023-GO95MLD-1^06245006.0242000 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
284418818-89569-DETAIL-04_06_2023-GO95MLD-1^06245006.0244400 | OTHER | FHCA | Distribution | 2023-04-06 | 2028-04-06 | 3
643726038-349-DETAIL-04_06_2023-GO95HV-1^06245006.0245101 | OTHER | FHCA | Distribution | 2023-04-06 | 2028-04-06 | 3
747680558-70349-DETAIL-04_18_2023-GO95MLD-1^06245006.0246000 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
535710388-25099-DETAIL-04_18_2023-GO95MLD-1^06245006.0246001 | OTHER | FHCA | Distribution | 2023-04-18 | 2028-04-18 | 3
581114819-70913-DETAIL-04_18_2023-GO95MLD-1^06245006.0247040 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
788097358-53249-DETAIL-04_06_2023-GO95MLD-1^06245006.0249000 | OTHER | FHCA | Distribution | 2023-04-06 | 2028-04-06 | 3
284829268-64249-DETAIL-04_06_2023-GO95HV-1^06245006.0249100 | OTHER | FHCA | Distribution | 2023-04-06 | 2028-04-06 | 3
74689009-69299-DETAIL-04_06_2023-GO95MLD-1^06245006.0249700 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
949519900-77923-DETAIL-04_18_2023-GO95MLD-1^06245006.0250941 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
877372099-74923-DETAIL-04_18_2023-GO95MLD-1^06245006.0250942 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
152988819-25413-DETAIL-04_18_2023-GO95MLD-1^06245006.0251900 | OTHER | FHCA | Distribution | 2023-04-18 | 2028-04-18 | 3
522318789-94549-DETAIL-04_18_2023-GO95MLD-1^06245006.0251901 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
318989529-44549-DETAIL-04_18_2023-GO95MLD-1^06245006.0252900 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
386221319-24549-DETAIL-04_18_2023-GO95MLD-1^06245006.0253900 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
610552439-10179-DETAIL-04_18_2023-GO95MLD-1^06245006.0254900 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
343100330-77423-DETAIL-04_06_2023-GO95MLD-1^06245006.0255940 | OTHER | FHCA | Distribution | 2023-04-06 | 2026-04-06 | 2
141682120-84423-DETAIL-04_18_2023-GO95MLD-1^06245006.0255942 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
541016140-93623-DETAIL-04_18_2023-GO95MLD-1^06245006.0256940 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
595894330-62523-DETAIL-04_18_2023-GO95HV-1^06245006.0256941 | OTHER | FHCA | Distribution | 2023-04-18 | 2028-04-18 | 3
350607350-9723-DETAIL-04_18_2023-GO95MLD-1^06245006.0258940 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
942133444-93549-DETAIL-04_18_2023-GO95MLD-1^06245006.0259900 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
459253750-32823-DETAIL-04_18_2023-GO95MLD-1^06245006.0259942 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
459253750-32823-DETAIL-04_18_2023-GO95MLD-2^06245006.0259942 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
122896590-16379-DETAIL-04_13_2023-GO95MLD-1^06245006.0260800 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
104203221-96023-DETAIL-04_20_2023-GO95MLD-1^06245006.0260840 | OTHER | FHCA | Distribution | 2023-04-20 | 2026-04-20 | 2
596767001-3023-DETAIL-04_13_2023-GO95MLD-1^06245006.0260841 | OTHER | FHCA | Distribution | 2023-04-13 | 2026-04-13 | 2
867626850-87189-DETAIL-04_18_2023-GO95MLD-1^06245006.0260900 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
969247591-11789-DETAIL-04_20_2023-GO95CL10-1^06245006.0261841 | OTHER | FHCA | Distribution | 2023-04-20 | 2028-04-20 | 3
969247591-11789-DETAIL-04_20_2023-RISEGRD-1^06245006.0261841 | OTHER | FHCA | Distribution | 2023-04-20 | 2026-04-20 | 2
400255331-80123-DETAIL-04_20_2023-GO95MLD-1^06245006.0261842 | OTHER | FHCA | Distribution | 2023-04-20 | 2026-04-20 | 2
400255331-80123-DETAIL-04_20_2023-GO95MLD-2^06245006.0261842 | OTHER | FHCA | Distribution | 2023-04-20 | 2026-04-20 | 2
116950010-89549-DETAIL-04_18_2023-GO95MLD-1^06245006.0261902 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
373556700-49549-DETAIL-04_18_2023-SVCWIND-1^06245006.0263801 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
93753411-15733-DETAIL-04_18_2023-GO95MLD-1^06245006.0263840 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
551772530-40649-DETAIL-04_18_2023-GO95HV-1^06245006.0264801 | OTHER | FHCA | Distribution | 2023-04-18 | 2028-04-18 | 3
119341410-8499-DETAIL-04_18_2023-GO95MLD-1^06245006.0264802 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
122577521-62833-DETAIL-04_18_2023-GO95HV-1^06245006.0264840 | OTHER | FHCA | Distribution | 2023-04-18 | 2028-04-18 | 3
335407120-19549-DETAIL-04_18_2023-GO95MLD-1^06245006.0264900 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
359094070-36999-DETAIL-04_03_2023-GO95MLD-1^06245006.0265200 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
27604520-6549-DETAIL-04_03_2023-GO95MLD-1^06245006.0265201 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
627649510-75999-DETAIL-04_03_2023-GO95MLD-1^06245006.0265300 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
627649510-75999-DETAIL-04_03_2023-GO95TCH-1^06245006.0265300 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
832940680-56549-DETAIL-04_03_2023-GO95HV-1^06245006.0265401 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
832940680-56549-DETAIL-04_03_2023-GO95MLD-1^06245006.0265401 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
587617360-58549-DETAIL-05_16_2023-GO95MLD-1^06245006.0265701 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
47803001-92649-DETAIL-04_18_2023-GRDRODHI-1^06245006.0265901 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
439040700-9549-DETAIL-04_18_2023-GO95MLD-1^06245006.0265902 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
841187512-39512-DETAIL-04_18_2023-GO95MLD-1^06245006.0265904 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
427900041-59823-DETAIL-04_18_2023-GO95MLD-1^06245006.0266941 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
426545130-27549-DETAIL-04_03_2023-GO95MLD-1^06245006.0267400 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
177543851-38923-DETAIL-04_18_2023-GO95HV-1^06245006.0267940 | OTHER | FHCA | Distribution | 2023-04-18 | 2028-04-18 | 3
987878851-83923-DETAIL-04_18_2023-GO95MLD-1^06245006.0267941 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
30300681-77549-DETAIL-04_18_2023-GO95MLD-1^06245006.0268940 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
432045151-13033-DETAIL-04_18_2023-GO95HV-1^06245006.0268942 | OTHER | FHCA | Distribution | 2023-04-18 | 2028-04-18 | 3
432045151-13033-DETAIL-04_18_2023-GO95MLD-1^06245006.0268942 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
209303691-51233-DETAIL-04_18_2023-GO95MLD-1^06245006.0269940 | OTHER | FHCA | Distribution | 2023-04-18 | 2026-04-18 | 2
593406123-12949-DETAIL-05_09_2023-SVCROAD-1^06245006.0270800 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
651687380-37779-DETAIL-05_10_2023-ABNDEQPM-1^06245006.0271201 | OTHER | FHCA | Distribution | 2023-05-10 | 2028-05-10 | 3
574157055-96199-DETAIL-05_10_2023-GO95MLD-1^06245006.0271642 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
574157055-96199-DETAIL-05_10_2023-SVCROAD-1^06245006.0271642 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
311980014-62343-DETAIL-05_09_2023-SVCROAD-1^06245006.0271701 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
777432754-1179-DETAIL-05_10_2023-SVCROAD-1^06245006.0272801 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
759233633-86849-DETAIL-05_10_2023-GO95HV-1^06245006.0272802 | OTHER | FHCA | Distribution | 2023-05-10 | 2028-05-10 | 3
759233633-86849-DETAIL-05_10_2023-GUYHINS-1^06245006.0272802 | ANCHOR/GUY | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
397238080-55049-DETAIL-05_09_2023-GO95MLD-1^06245006.0272903 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
903898778-86113-DETAIL-05_09_2023-GO95MLD-1^06245006.0272942 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
3344464-58879-DETAIL-05_25_2023-GO95MLD-1^06245006.0273401 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
646674764-83849-DETAIL-05_25_2023-GO95MLD-1^06245006.0273500 | OTHER | FHCA | Distribution | 2023-05-25 | 2026-05-25 | 2
161194464-14849-DETAIL-05_10_2023-GO95MLD-1^06245006.0273600 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
257592384-34849-DETAIL-05_10_2023-GO95MLD-1^06245006.0273602 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
579896264-97889-DETAIL-05_10_2023-GO95MLD-1^06245006.0273603 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
515623263-2699-DETAIL-05_10_2023-GO95MLD-1^06245006.0273703 | OTHER | FHCA | Distribution | 2023-05-10 | 2028-05-10 | 3
650036371-43469-DETAIL-05_10_2023-GO95MLD-1^06245006.0273707 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
69043753-69833-DETAIL-05_10_2023-GO95HV-1^06245006.0273802 | OTHER | FHCA | Distribution | 2023-05-10 | 2028-05-10 | 3
69043753-69833-DETAIL-05_10_2023-SVCENTCO-1^06245006.0273802 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
486407503-18849-DETAIL-05_09_2023-GO95MLD-1^06245006.0273803 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
797475714-97849-DETAIL-05_10_2023-GO95HV-1^06245006.0273804 | OTHER | FHCA | Distribution | 2023-05-10 | 2028-05-10 | 3
485281893-13543-DETAIL-05_09_2023-GO95MLD-1^06245006.0273805 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
626654934-75343-DETAIL-05_10_2023-GO95MLD-1^06245006.0273902 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
287474521-30049-DETAIL-05_10_2023-RISEGRD-1^06245006.0273903 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
840588105-453-DETAIL-05_09_2023-GO95MLD-1^06245006.0273940 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
814527454-27753-DETAIL-05_09_2023-GO95MLD-1^06245006.0273942 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
814527454-27753-DETAIL-05_09_2023-GUYHINS-1^06245006.0273942 | ANCHOR/GUY | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
340730739-8913-DETAIL-05_09_2023-GO95BLTC-1^06245006.0273943 | OTHER | FHCA | Distribution | 2023-05-09 | 2028-05-09 | 3
340730739-8913-DETAIL-05_09_2023-GO95MLD-1^06245006.0273943 | OTHER | FHCA | Distribution | 2023-05-09 | 2026-05-09 | 2
722366584-27253-DETAIL-05_10_2023-GO95HV-1^06245006.0273944 | OTHER | FHCA | Distribution | 2023-05-10 | 2028-05-10 | 3
107221334-10799-DETAIL-05_10_2023-GO95MLD-1^06245006.0274600 | OTHER | FHCA | Distribution | 2023-05-10 | 2028-05-10 | 3
885747025-59553-DETAIL-05_15_2023-GUYHINS-1^06245006.0274743 | ANCHOR/GUY | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
885747025-59553-DETAIL-05_15_2023-SVCENTCO-1^06245006.0274743 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
885747025-59553-DETAIL-05_15_2023-SVCROOF-1^06245006.0274743 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
700019344-54753-DETAIL-05_15_2023-GO95MLD-1^06245006.0274745 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
334533964-3953-DETAIL-05_15_2023-GO95MLD-1^06245006.0274840 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
522506364-47953-DETAIL-05_15_2023-GO95HV-1^06245006.0274843 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
558988644-69653-DETAIL-05_10_2023-GO95MLD-1^06245006.0274845 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
561851904-8389-DETAIL-05_10_2023-GO95MLD-1^06245006.0274902 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
561851904-8389-DETAIL-05_10_2023-GO95TCH-1^06245006.0274902 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
983753416-8223-DETAIL-05_10_2023-GO95MLD-1^06245006.0274940 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
850336404-98653-DETAIL-05_10_2023-GUYHINS-1^06245006.0274941 | ANCHOR/GUY | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
111461425-3653-DETAIL-05_10_2023-GO95MLD-1^06245006.0274942 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
111461425-3653-DETAIL-05_10_2023-GO95TCH-1^06245006.0274942 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
718682844-43849-DETAIL-05_23_2023-GO95MLD-1^06245006.0275401 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
150743394-62073-DETAIL-05_23_2023-GO95HV-1^06245006.0275440 | OTHER | FHCA | Distribution | 2023-05-23 | 2028-05-23 | 3
150743394-62073-DETAIL-05_23_2023-GO95MLD-1^06245006.0275440 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
713435710-51653-DETAIL-05_23_2023-GO95MLD-1^06245006.0275441 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
55141553-10749-DETAIL-05_17_2023-GO95MLD-1^06245006.0275500 | OTHER | FHCA | Distribution | 2023-05-17 | 2026-05-17 | 2
202317364-2388-DETAIL-05_23_2023-GO95MLD-1^06245006.0275502 | OTHER | FHCA | Distribution | 2023-05-23 | 2026-05-23 | 2
380586847-70947-DETAIL-05_15_2023-GO95MLD-1^06245006.0275702 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
112425744-30389-DETAIL-05_15_2023-GO95HV-1^06245006.0275800 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
828445793-47789-DETAIL-05_15_2023-GO95MLD-1^06245006.0275803 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
246462624-949-DETAIL-05_15_2023-GO95MLD-1^06245006.0275804 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
389892125-65125-DETAIL-05_10_2023-GO95HV-1^06245006.0275810 | OTHER | FHCA | Distribution | 2023-05-10 | 2028-05-10 | 3
38721204-25073-DETAIL-05_15_2023-GO95HV-1^06245006.0275841 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
38721204-25073-DETAIL-05_15_2023-GO95MLD-1^06245006.0275841 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
329052724-15279-DETAIL-05_15_2023-GO95MLD-1^06245006.0275842 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
344007173-81849-DETAIL-05_15_2023-GO95MLD-1^06245006.0275901 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
534212663-32849-DETAIL-05_15_2023-GO95MLD-1^06245006.0275903 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
162366189-74569-DETAIL-05_15_2023-GO95MLD-1^06245006.0275906 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
162366189-74569-DETAIL-05_15_2023-GO95TCH-1^06245006.0275906 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
271764984-96873-DETAIL-05_15_2023-GO95HV-1^06245006.0275940 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
831289383-53903-DETAIL-05_10_2023-GO95MLD-1^06245006.0275942 | OTHER | FHCA | Distribution | 2023-05-10 | 2026-05-10 | 2
196563909-15649-DETAIL-05_17_2023-GO95BLTC-1^06245006.0276101 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
196563909-15649-DETAIL-05_17_2023-GO95HV-1^06245006.0276101 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
467822744-80749-DETAIL-05_17_2023-GO95MLD-1^06245006.0276400 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
467822744-80749-DETAIL-05_17_2023-RISEGRD-1^06245006.0276400 | OTHER | FHCA | Distribution | 2023-05-17 | 2026-05-17 | 2
844977463-90749-DETAIL-05_17_2023-GO95MLD-1^06245006.0276403 | OTHER | FHCA | Distribution | 2023-05-17 | 2026-05-17 | 2
961867714-39379-DETAIL-05_17_2023-GO95MLD-1^06245006.0276440 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
522543503-22373-DETAIL-05_15_2023-GO95MLD-1^06245006.0276700 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
764320484-58749-DETAIL-05_15_2023-GO95MLD-1^06245006.0276800 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
262698893-8749-DETAIL-05_15_2023-GO95MLD-1^06245006.0276801 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
429111663-94489-DETAIL-05_15_2023-GO95MLD-1^06245006.0276805 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
423942783-89749-DETAIL-05_15_2023-GO95MLD-1^06245006.0276806 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
281752673-88749-DETAIL-05_15_2023-GO95MLD-1^06245006.0276900 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
641634503-30849-DETAIL-05_15_2023-GO95MLD-1^06245006.0276902 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
730203803-22999-DETAIL-05_15_2023-GO95HV-1^06245006.0276903 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
271525659-46059-DETAIL-05_15_2023-GO95MLD-1^06245006.0276905 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
453948534-56773-DETAIL-05_15_2023-GO95MLD-1^06245006.0276940 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
453948534-56773-DETAIL-05_15_2023-GO95TCH-1^06245006.0276940 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
727096834-79873-DETAIL-05_15_2023-GUYHINS-1^06245006.0276944 | ANCHOR/GUY | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
547732114-31173-DETAIL-05_15_2023-GUYNOINS-1^06245006.0276946 | ANCHOR/GUY | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
900312714-99073-DETAIL-05_15_2023-GO95MLD-1^06245006.0276947 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
811058681-58319-DETAIL-05_16_2023-GO95HV-1^06245006.0277200 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
811058681-58319-DETAIL-05_16_2023-GO95MLD-1^06245006.0277200 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
264479098-93898-DETAIL-05_16_2023-GO95MLD-1^06245006.0277300 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
859660369-48649-DETAIL-05_16_2023-GO95MLD-1^06245006.0277400 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
818447449-75649-DETAIL-05_16_2023-GO95HV-1^06245006.0277401 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
79309604-32704-DETAIL-05_16_2023-ABNDEQPM-1^06245006.0277402 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
633200344-51749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277500 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
308713443-61749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277600 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
5244383-22749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277700 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
489483793-7799-DETAIL-05_16_2023-GO95MLD-1^06245006.0277804 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
860605723-66749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277805 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
5189643-17749-DETAIL-05_16_2023-GO95MLD-1^06245006.0277900 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
90119013-65089-DETAIL-05_15_2023-GO95MLD-1^06245006.0277901 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
90119013-65089-DETAIL-05_15_2023-GRDRODHI-1^06245006.0277901 | OTHER | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
90119013-65089-DETAIL-05_15_2023-GUYHINS-1^06245006.0277901 | ANCHOR/GUY | FHCA | Distribution | 2023-05-15 | 2026-05-15 | 2
432269133-6963-DETAIL-05_15_2023-ABNDEQPM-1^06245006.0277903 | OTHER | FHCA | Distribution | 2023-05-15 | 2028-05-15 | 3
194305073-2289-DETAIL-05_16_2023-GO95MLD-1^06245006.0278601 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
367207434-13749-DETAIL-05_16_2023-SVCROAD-1^06245006.0278703 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
560038234-43749-DETAIL-05_16_2023-GO95TCH-1^06245006.0278704 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
379703238-54238-DETAIL-05_16_2023-SVCROAD-1^06245006.0278705 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
531932124-67299-DETAIL-05_16_2023-GO95MLD-1^06245006.0278706 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
531932124-67299-DETAIL-05_16_2023-GO95TCH-1^06245006.0278706 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
518063064-13973-DETAIL-05_16_2023-RISEGRD-1^06245006.0278843 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
400212714-58689-DETAIL-05_16_2023-GO95MLD-1^06245006.0278904 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
309563393-71479-DETAIL-05_16_2023-GO95HV-1^06245006.0278905 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
309563393-71479-DETAIL-05_16_2023-GO95MLD-1^06245006.0278905 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
683177143-90479-DETAIL-05_16_2023-GO95MLD-1^06245006.0278906 | OTHER | FHCA | Distribution | 2023-05-16 | 2026-05-16 | 2
276225483-93749-DETAIL-05_16_2023-GO95HV-1^06245006.0279801 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
777694373-82873-DETAIL-05_16_2023-GO95HV-1^06245006.0279901 | OTHER | FHCA | Distribution | 2023-05-16 | 2028-05-16 | 3
835547384-38384-DTLSB-08_22_2024-GO95CL10-1^06245006.0320500 | OTHER | CA-TIER-2 | Distribution | 2024-08-22 | 2029-08-22 | 3
835547384-38384-DTLSB-08_22_2024-GO95HV-1^06245006.0320500 | OTHER | CA-TIER-2 | Distribution | 2024-08-22 | 2029-08-22 | 3
502753798-14989-DTLSB-08_22_2024-GO95MLD-1^06245006.0322701 | OTHER | FHCA | Distribution | 2024-08-22 | 2027-08-22 | 2
969804307-12999-DTLSB-08_22_2024-GO95MLD-1^06245006.0323200 | OTHER | CA-TIER-2 | Distribution | 2024-08-22 | 2027-08-22 | 2
644183438-71999-DTLSB-08_22_2024-RISEBKSP-1^06245006.0323201 | OTHER | CA-TIER-2 | Distribution | 2024-08-22 | 2027-08-22 | 2
194842606-92999-DTLSB-08_22_2024-GO95HV-1^06245006.0324000 | OTHER | FHCA | Distribution | 2024-08-22 | 2029-08-22 | 3
330742347-72999-DTLSB-08_22_2024-GO95MLD-1^06245006.0324100 | OTHER | FHCA | Distribution | 2024-08-22 | 2029-08-22 | 3
347535107-56389-DTLSB-08_22_2024-GO95MLD-1^06245006.0324401 | OTHER | FHCA | Distribution | 2024-08-22 | 2027-08-22 | 2
495129637-40999-DTLSB-08_22_2024-GUYNOINS-1^06245006.0325200 | ANCHOR/GUY | FHCA | Distribution | 2024-08-22 | 2027-08-22 | 2
150511328-39899-DTLSB-08_22_2024-GO95MLD-1^06245006.0325400 | OTHER | FHCA | Distribution | 2024-08-22 | 2027-08-22 | 2
223948248-64999-DTLSB-08_22_2024-ENCHRW-1^06245006.0326600 | OTHER | FHCA | Distribution | 2024-08-22 | 2027-08-22 | 2
223948248-64999-DTLSB-08_22_2024-GO95MLD-1^06245006.0326600 | OTHER | FHCA | Distribution | 2024-08-22 | 2027-08-22 | 2
999616348-18899-DTLSB-08_22_2024-GO95HV-1^06245006.0326601 | OTHER | FHCA | Distribution | 2024-08-22 | 2029-08-22 | 3
530302587-90599-DTLSB-08_22_2024-GO95MLD-1^06245006.0326602 | OTHER | FHCA | Distribution | 2024-08-22 | 2029-08-22 | 3
739905728-94999-DTLSB-08_22_2024-GO95HV-1^06245006.0327740 | OTHER | FHCA | Distribution | 2024-08-22 | 2029-08-22 | 3
739905728-94999-DTLSB-08_22_2024-GO95MLD-1^06245006.0327740 | OTHER | FHCA | Distribution | 2024-08-22 | 2027-08-22 | 2
76510718-65199-DTLSB-08_22_2024-GO95MLD-1^06245006.0328600 | OTHER | FHCA | Distribution | 2024-08-22 | 2029-08-22 | 3
76510718-65199-DTLSB-08_22_2024-GRDRODHI-1^06245006.0328600 | OTHER | FHCA | Distribution | 2024-08-22 | 2027-08-22 | 2
721378197-59179-DETAIL-08_21_2024-GO95HV-1^06245006.0331001 | OTHER | FHCA | Distribution | 2024-08-21 | 2029-08-21 | 3
721184490-6049-DETAIL-05_17_2023-GO95HV-1^06245006.0345700 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
646220000-56049-DETAIL-05_17_2023-GO95HV-1^06245006.0345800 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
279773191-31523-DETAIL-05_17_2023-GO95MLD-1^06245006.0346400 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
188247440-41589-DETAIL-05_17_2023-GO95MLD-1^06245006.0346401 | OTHER | FHCA | Distribution | 2023-05-17 | 2026-05-17 | 2
336756060-85049-DETAIL-05_17_2023-GO95HV-1^06245006.0346700 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
785301770-64049-DETAIL-05_17_2023-GO95HV-1^06245006.0347801 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
393412650-94049-DETAIL-05_17_2023-GO95HV-1^06245006.0347802 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
276415080-13049-DETAIL-05_17_2023-GO95HV-1^06245006.0349600 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
389168390-63049-DETAIL-05_17_2023-GO95HV-1^06245006.0349700 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
988911149-70549-DETAIL-05_17_2023-GO95HV-1^06245006.0350200 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
602696309-80549-DETAIL-05_17_2023-GO95HV-1^06245006.0350300 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
128985309-85599-DETAIL-05_17_2023-GO95MLD-1^06245006.0350400 | OTHER | FHCA | Distribution | 2023-05-17 | 2026-05-17 | 2
151544303-77303-DETAIL-05_24_2023-GO95HV-1^06245006.0352200 | OTHER | FHCA | Distribution | 2023-05-24 | 2028-05-24 | 3
146303403-64403-DETAIL-05_24_2023-GO95MLD-1^06245006.0352201 | OTHER | FHCA | Distribution | 2023-05-24 | 2026-05-24 | 2
654896879-7789-DETAIL-05_17_2023-GO95MLD-1^06245006.0352500 | OTHER | FHCA | Distribution | 2023-05-17 | 2026-05-17 | 2
438696559-62549-DETAIL-05_17_2023-GO95HV-1^06245006.0352600 | OTHER | FHCA | Distribution | 2023-05-17 | 2028-05-17 | 3
830563629-79439-DETAIL-05_09_2023-GO95HV-1^06245006.0362300 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
283586019-39889-DETAIL-05_09_2023-GO95MLD-1^06245006.0362400 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2026-05-09 | 2
715982739-49449-DETAIL-05_09_2023-GO95HV-1^06245006.0363101 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
671105829-10549-DETAIL-05_09_2023-GO95HV-1^06245006.0363300 | OTHER | CA-NON-TIER | Distribution | 2023-05-09 | 2028-05-09 | 3
209060959-42679-DTLSB-08_27_2024-GO95MLD-1^06245007.0012001 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
209060959-42679-DTLSB-08_27_2024-GRDRODHI-1^06245007.0012001 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
209060959-42679-DTLSB-08_27_2024-GRDRODHI-2^06245007.0012001 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
606814379-36409-DTLSB-08_27_2024-GO95MLD-1^06245007.0012100 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
904624980-17409-DTLSB-09_03_2024-GO95HV-1^06245007.0013100 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
224589889-76409-DTLSB-09_03_2024-GO95HV-1^06245007.0013101 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
322916980-909-DTLSB-09_03_2024-GO95MLD-1^06245007.0014001 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
947823489-40909-DTLSB-09_03_2024-GO95MLD-1^06245007.0014101 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
812850580-80909-DTLSB-08_27_2024-GO95HV-1^06245007.0014102 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
884684080-87389-DTLSB-09_03_2024-GO95MLD-1^06245007.0014103 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
154659370-38179-DTLSB-09_03_2024-GO95MLD-1^06245007.0014200 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
340567449-42509-DTLSB-09_03_2024-GO95MLD-1^06245007.0014300 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
588392839-3509-DTLSB-09_03_2024-GO95HV-1^06245007.0014302 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
588392839-3509-DTLSB-09_03_2024-GO95MLD-1^06245007.0014302 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
670965590-75409-DTLSB-09_03_2024-GO95HV-1^06245007.0015001 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
185699610-52599-DTLSB-09_03_2024-GO95MLD-1^06245007.0015103 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
404851570-98409-DTLSB-09_05_2024-CLMBTRE-1^06245007.0015200 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2025-09-05 | 2
850096560-11579-DTLSB-09_05_2024-GO95MLD-1^06245007.0015201 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
377590359-71509-DTLSB-09_03_2024-GO95MLD-1^06245007.0015400 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
602327569-61509-DTLSB-09_04_2024-GO95HV-1^06245007.0015500 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
602327569-61509-DTLSB-09_04_2024-GO95MLD-1^06245007.0015500 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
12930260-94579-DTLSB-09_03_2024-GO95MLD-1^06245007.0016201 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
909188009-19409-DTLSB-09_03_2024-GO95MLD-1^06245007.0016300 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
88546279-69409-DTLSB-09_04_2024-GO95HV-1^06245007.0016500 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
464110479-89409-DTLSB-09_04_2024-GO95MLD-1^06245007.0016502 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
472007899-94509-DETAIL-09_04_2024-GO95MLD-1^06245007.0016602 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
825028489-45509-DTLSB-09_04_2024-GO95MLD-1^06245007.0016604 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
379722419-99589-DTLSB-09_04_2024-GO95MLD-1^06245007.0016700 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
973261800-77509-DTLSB-09_03_2024-GO95HV-1^06245007.0017000 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
973261800-77509-DTLSB-09_03_2024-GO95MLD-1^06245007.0017000 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
973261800-77509-DTLSB-09_03_2024-GRDRODHI-1^06245007.0017000 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
947883730-56499-DTLSB-09_03_2024-GO95MLD-1^06245007.0018000 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
952664879-19489-DTLSB-09_03_2024-GO95MLD-1^06245007.0018100 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
952664879-19489-DTLSB-09_03_2024-SVCENTCO-1^06245007.0018100 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
977022009-19679-DTLSB-09_03_2024-GO95MLD-1^06245007.0018400 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
977022009-19679-DTLSB-09_03_2024-GRDRODHI-1^06245007.0018400 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
759016850-41509-DTLSB-09_04_2024-GO95MLD-1^06245007.0018405 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
197371201-91201-DTLTRT-09_04_2024-SVCDEFLC-1^06245007.0018430 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
74599240-78509-DTLSB-09_03_2024-GO95HV-1^06245007.0019001 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
74599240-78509-DTLSB-09_03_2024-GO95MLD-1^06245007.0019001 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
172344840-10779-DTLSB-09_04_2024-GO95MLD-1^06245007.0019102 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
172344840-10779-DTLSB-09_04_2024-GRDRODHI-1^06245007.0019102 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
831354920-98509-DTLSB-09_03_2024-GO95HV-1^06245007.0019302 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
505615350-56769-DTLSB-09_04_2024-GO95MLD-1^06245007.0019400 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
505615350-56769-DTLSB-09_04_2024-SVCDEFLC-1^06245007.0019400 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
921445689-16809-DTLSB-09_05_2024-GO95HV-1^06245007.0030100 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
430435399-96809-DTLSB-09_05_2024-GRDRODHI-1^06245007.0030200 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
454355079-39289-DTLSB-09_05_2024-GO95MLD-1^06245007.0031102 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
542772249-31389-DTLSB-09_05_2024-GO95MLD-1^06245007.0033000 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
5011500-83809-DTLSB-09_05_2024-GO95HV-1^06245007.0033001 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
797486159-73809-DTLSB-09_05_2024-GUYNOINS-1^06245007.0034000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
390045739-92809-DTLSB-09_05_2024-GO95HV-1^06245007.0034002 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
390045739-92809-DTLSB-09_05_2024-GO95MLD-1^06245007.0034002 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
342984230-67809-DTLSB-09_05_2024-GO95MLD-1^06245007.0049100 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
979157090-3389-DTLSB-07_22_2024-GO95MLD-1^06245007.0106800 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2029-07-22 | 3
479447529-99289-DTLSB-07_22_2024-GO95MLD-1^06245007.0106902 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2029-07-22 | 3
197754440-58709-DTLSB-07_23_2024-GO95MLD-1^06245007.0107200 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2027-07-23 | 2
362151290-2389-DTLSB-07_23_2024-GO95MLD-1^06245007.0107201 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2027-07-23 | 2
275830760-76089-DTLSB-07_23_2024-GO95MLD-1^06245007.0107401 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2029-07-23 | 3
866681050-65789-DTLSB-07_23_2024-RISEGRD-1^06245007.0107403 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2027-07-23 | 2
370094860-809-DTLSB-07_23_2024-GO95HV-1^06245007.0107500 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2029-07-23 | 3
370094860-809-DTLSB-07_23_2024-GO95MLD-1^06245007.0107500 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2027-07-23 | 2
986800880-64489-DTLSB-07_22_2024-GO95MLD-1^06245007.0107802 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2029-07-22 | 3
61995393-38709-DTLSB-07_23_2024-GO95HV-1^06245007.0108200 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2029-07-23 | 3
259294950-7709-DTLSB-07_23_2024-GO95HV-1^06245007.0109201 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2029-07-23 | 3
112654200-50389-DTLSB-07_23_2024-GO95MLD-1^06245007.0109300 | OTHER | CA-TIER-2 | Distribution | 2024-07-23 | 2027-07-23 | 2
699678539-60809-DTLSB-07_22_2024-GO95HV-1^06245007.0109700 | OTHER | CA-TIER-2 | Distribution | 2024-07-22 | 2029-07-22 | 3
116882231-56709-DTLSB-08_26_2024-GO95HV-1^06245007.0110100 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
621494312-55709-DTLSB-08_26_2024-GO95HV-1^06245007.0111101 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
243057091-18269-DTLSB-08_26_2024-GO95MLD-1^06245007.0111201 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
243057091-18269-DTLSB-08_26_2024-SVCDEFLC-1^06245007.0111201 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
373587281-15709-DTLSB-08_26_2024-GO95HV-1^06245007.0112100 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
411338982-9289-DTLSB-08_26_2024-GO95HV-1^06245007.0112200 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
411338982-9289-DTLSB-08_26_2024-GO95MLD-1^06245007.0112200 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
956059752-65289-DTLSB-08_26_2024-GO95HV-1^06245007.0112401 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
828394861-33709-DTLSB-08_26_2024-GO95HV-1^06245007.0112700 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
860415841-35109-DTLSB-08_28_2024-GO95MLD-1^06245007.0113000 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
501998121-54709-DTLSB-08_28_2024-GO95MLD-1^06245007.0113002 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
855347622-32989-DTLSB-08_26_2024-GO95TCH-1^06245007.0113101 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
217342982-75633-DTLSB-08_26_2024-SVCENTCO-1^06245007.0113300 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
998309371-2289-DTLSB-08_26_2024-GO95MLD-1^06245007.0113301 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
624128642-52389-DTLSB-08_26_2024-GO95MLD-1^06245007.0113400 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
538653892-24579-DTLSB-08_26_2024-GO95HV-1^06245007.0113401 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
538653892-24579-DTLSB-08_26_2024-GO95MLD-1^06245007.0113401 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
538653892-24579-DTLSB-08_26_2024-GO95TCH-1^06245007.0113401 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
965885072-98109-DTLSB-08_26_2024-GO95MLD-1^06245007.0113402 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
738523171-71289-DTLSB-08_26_2024-GO95MLD-1^06245007.0113403 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
555721811-16289-DTLSB-08_26_2024-GO95MLD-1^06245007.0113501 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
555721811-16289-DTLSB-08_26_2024-GUYNOINS-1^06245007.0113501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
911220411-68599-DTLSB-08_27_2024-GO95HV-1^06245007.0113900 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
69327981-72389-DTLSB-08_26_2024-GO95HV-1^06245007.0114100 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
721783681-96109-DTLSB-08_26_2024-GO95HV-1^06245007.0114204 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
844902261-48109-DTLSB-08_26_2024-GO95MLD-1^06245007.0114301 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
383066232-77109-DTLSB-08_26_2024-GO95HV-1^06245007.0114302 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
383066232-77109-DTLSB-08_26_2024-GO95MLD-1^06245007.0114302 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
681404232-97109-DTLSB-08_26_2024-GO95MLD-1^06245007.0114303 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
750522051-86689-DTLSB-08_26_2024-GO95HV-1^06245007.0114304 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2029-08-26 | 3
935062541-57109-DTLSB-08_26_2024-GO95MLD-1^06245007.0114305 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
600034721-60709-DTLSB-08_27_2024-SVCDEFLC-1^06245007.0114801 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
244968651-94779-DTLSB-08_27_2024-GRDRODHI-1^06245007.0114802 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
178871641-90709-DTLSB-08_27_2024-GO95HV-1^06245007.0114803 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
239595922-16109-DTLSB-08_26_2024-GO95MLD-1^06245007.0115200 | OTHER | CA-TIER-2 | Distribution | 2024-08-26 | 2027-08-26 | 2
72590211-84589-DTLSB-09_04_2024-GO95HV-1^06245007.0115301 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
185451271-39499-DTLSB-08_27_2024-GO95BLTC-1^06245007.0115501 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
185451271-39499-DTLSB-08_27_2024-GO95HV-1^06245007.0115501 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
185451271-39499-DTLSB-08_27_2024-GO95MLD-1^06245007.0115501 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
782130241-84189-DTLSB-08_27_2024-GO95MLD-1^06245007.0115900 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
782130241-84189-DTLSB-08_27_2024-GRDRODHI-1^06245007.0115900 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
461259343-85669-DTLSB-08_27_2024-SVCENTCO-1^06245007.0116400 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
328025421-21209-DTLSB-08_28_2024-GO95HV-1^06245007.0116402 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
381114881-7389-DTLSB-08_28_2024-GRDRODHI-1^06245007.0116700 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
636032631-83149-DTLSB-08_27_2024-GO95HV-1^06245007.0116801 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
636032631-83149-DTLSB-08_27_2024-GO95MLD-1^06245007.0116801 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
169288501-89679-DTLSB-08_27_2024-GRDRODHI-1^06245007.0116901 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
121862741-3209-DTLSB-08_27_2024-POLETOP-1^06245007.0117500 | POLE | CA-TIER-2 | Distribution | 2024-08-27 | 2025-08-27 | 2
121862741-3209-DTLSB-08_27_2024-SVCDEFLC-1^06245007.0117500 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
724356631-8479-DTLSB-08_27_2024-GO95MLD-1^06245007.0117501 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
15481791-64169-DTLSB-08_28_2024-GO95HV-1^06245007.0117502 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
148142351-7489-DTLSB-08_27_2024-GO95MLD-1^06245007.0118600 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
286839271-17679-DTLSB-08_27_2024-GO95MLD-1^06245007.0118701 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
12945151-9479-DTLSB-08_27_2024-GUYHINS-1^06245007.0118900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
12945151-9479-DTLSB-08_27_2024-GUYHINS-2^06245007.0118900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
496721361-78479-DTLSB-08_27_2024-GO95MLD-1^06245007.0119702 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
496721361-78479-DTLSB-08_27_2024-POLETOP-1^06245007.0119702 | POLE | CA-TIER-2 | Distribution | 2024-08-27 | 2025-08-27 | 2
325525401-68099-DTLSB-08_27_2024-GUYHINS-1^06245007.0119703 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
873580251-99579-DTLSB-08_27_2024-GO95MLD-1^06245007.0119800 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2027-08-27 | 2
873580251-99579-DTLSB-08_27_2024-POLETOP-1^06245007.0119800 | POLE | CA-TIER-2 | Distribution | 2024-08-27 | 2025-08-27 | 2
849479561-49609-DTLSB-08_27_2024-GO95MLD-1^06245007.0120700 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
70184829-9809-DTLSB-08_27_2024-GO95MLD-1^06245007.0120800 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
598507249-91199-DTLSB-08_27_2024-GO95HV-1^06245007.0121900 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
598507249-91199-DTLSB-08_27_2024-GO95MLD-1^06245007.0121900 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
150651549-95409-DTLSB-08_27_2024-GO95MLD-1^06245007.0122900 | OTHER | CA-TIER-2 | Distribution | 2024-08-27 | 2029-08-27 | 3
999328889-22489-DTLSB-09_03_2024-GO95MLD-1^06245007.0123900 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
999328889-22489-DTLSB-09_03_2024-GUYHINS-1^06245007.0123900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
41634216-39208-DTLSB-09_03_2024-GO95MLD-1^06245007.0124900 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
41634216-39208-DTLSB-09_03_2024-GRDRODHI-1^06245007.0124900 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
41634216-39208-DTLSB-09_03_2024-GRDRODHI-2^06245007.0124900 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
41634216-39208-DTLSB-09_03_2024-SVCNEUT-1^06245007.0124900 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2027-09-03 | 2
762114475-33109-DTLSB-08_28_2024-GO95HV-1^06245007.0140002 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
762114475-33109-DTLSB-08_28_2024-GO95MLD-1^06245007.0140002 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
54236794-37289-DTLSB-08_28_2024-GO95HV-1^06245007.0140202 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
54236794-37289-DTLSB-08_28_2024-GO95MLD-1^06245007.0140202 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
54236794-37289-DTLSB-08_28_2024-GO95TCH-1^06245007.0140202 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
785916435-54009-DTLSB-08_28_2024-GO95HV-1^06245007.0140402 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
76631846-6009-DTLSB-09_04_2024-GO95MLD-1^06245007.0140601 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
67578335-23679-DTLSB-09_04_2024-GO95MLD-1^06245007.0141401 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
837802665-33009-DTLSB-08_28_2024-GO95MLD-1^06245007.0141500 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
253522895-40989-DTLSB-08_28_2024-GO95HV-1^06245007.0141501 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
253522895-40989-DTLSB-08_28_2024-GO95MLD-1^06245007.0141501 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
253522895-40989-DTLSB-08_28_2024-SVCDEFLC-1^06245007.0141501 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
243714775-84289-DTLSB-08_28_2024-ANCHIDLE-1^06245007.0141505 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
243714775-84289-DTLSB-08_28_2024-GO95HV-1^06245007.0141505 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
243714775-84289-DTLSB-08_28_2024-GO95MLD-1^06245007.0141505 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
46216496-99193-DTLSB-09_04_2024-GO95BLTC-1^06245007.0141540 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
360051845-65009-DTLSB-08_28_2024-SVCDEFLC-1^06245007.0141600 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
108872765-24289-DTLSB-08_28_2024-GO95MLD-1^06245007.0141601 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
612043225-73389-DETAIL-08_28_2024-GO95HV-1^06245007.0141602 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
612152125-46009-DTLSB-08_28_2024-GO95HV-1^06245007.0141700 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
182960736-17009-DTLSB-09_04_2024-GO95MLD-1^06245007.0141900 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
445413636-68289-DTLSB-09_04_2024-GO95MLD-1^06245007.0141902 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
886245726-38889-DTLSB-09_04_2024-SVCENTCO-1^06245007.0142401 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
108323635-25189-DTLSB-08_28_2024-GO95HV-1^06245007.0142700 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
516957555-96289-DTLSB-08_28_2024-SVCDEFLC-1^06245007.0142802 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
813797845-1389-DTLSB-09_04_2024-GO95MLD-1^06245007.0142902 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2027-09-04 | 2
400786795-42109-DTLSB-08_28_2024-GO95HV-1^06245007.0143300 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
52805483-39009-DTLSB-09_03_2024-GO95MLD-1^06245007.0143900 | OTHER | CA-TIER-2 | Distribution | 2024-09-03 | 2029-09-03 | 3
301292951-77389-DTLSB-08_28_2024-GO95MLD-1^06245007.0158001 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
32714771-31189-DTLSB-08_28_2024-GO95MLD-1^06245007.0158300 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2027-08-28 | 2
717607802-71269-DTLSB-08_28_2024-GO95HV-1^06245007.0158500 | OTHER | CA-TIER-2 | Distribution | 2024-08-28 | 2029-08-28 | 3
305949071-11009-DTLSB-08_28_2024-GO95MLD-1^06245007.0159100 | OTHER | FHCA | Distribution | 2024-08-28 | 2029-08-28 | 3
305949071-11009-DTLSB-08_28_2024-GRDRODHI-1^06245007.0159100 | OTHER | FHCA | Distribution | 2024-08-28 | 2027-08-28 | 2
305949071-11009-DTLSB-08_28_2024-GRDRODHI-2^06245007.0159100 | OTHER | FHCA | Distribution | 2024-08-28 | 2027-08-28 | 2
841060381-48589-DTLSB-09_04_2024-GO95HV-1^06245007.0159900 | OTHER | CA-TIER-2 | Distribution | 2024-09-04 | 2029-09-04 | 3
556996560-77149-DETAIL-07_01_2024-GO95MLD-1^06245007.0190101 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2027-07-01 | 2
556996560-77149-DETAIL-07_01_2024-GRDRODHI-1^06245007.0190101 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2027-07-01 | 2
556996560-77149-DETAIL-07_01_2024-GRDRODHI-2^06245007.0190101 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2027-07-01 | 2
924167940-74423-DETAIL-07_01_2024-SVCRUBLG-1^06245007.0192002 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2027-07-01 | 2
924167940-74423-DETAIL-07_01_2024-SVCWIND-1^06245007.0192002 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2027-07-01 | 2
565788719-1389-ADMIN-06_30_2022-POLEREPL-1^06245007.0218700 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
835868169-8249-ADMIN-06_30_2022-POLEREPL-1^06245007.0218701 | POLE | CA-NON-TIER | Distribution | 2022-06-30 | 2025-06-30 | 2
11305301-23363-DTLSB-04_29_2024-SVCDEFLC-1^06245007.0220440 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
32374291-21363-DTLSB-04_29_2024-GO95MLD-1^06245007.0220441 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
879712041-13463-DTLSB-04_17_2024-GO95HV-1^06245007.0220442 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
128500340-65163-DTLSB-04_11_2024-GO95HV-1^06245007.0220446 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
631562778-83143-DTLSB-04_29_2024-GO95MLD-1^06245007.0220540 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
631562778-83143-DTLSB-04_29_2024-SVCENTCO-1^06245007.0220540 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
363960656-78623-DTLSB-04_17_2024-GO95MLD-1^06245007.0220542 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
363960656-78623-DTLSB-04_17_2024-SVCDEFLC-1^06245007.0220542 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
324103645-91549-DTLSB-05_01_2024-GO95MLD-1^06245007.0220601 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
324103645-91549-DTLSB-05_01_2024-SVCENTCO-1^06245007.0220601 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
324103645-91549-DTLSB-05_01_2024-SVCROAD-1^06245007.0220601 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
340832455-32549-DTLSB-05_01_2024-SVCDEFLC-1^06245007.0220602 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
97708906-46823-DTLSB-04_30_2024-GO95HV-1^06245007.0220641 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2029-04-30 | 3
189676306-71623-DTLSB-04_30_2024-GO95MLD-1^06245007.0220642 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
861437228-98543-DTLSB-05_06_2024-COPLLEAN-1^06245007.0220740 | POLE | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
861437228-98543-DTLSB-05_06_2024-GO95MLD-1^06245007.0220740 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
861437228-98543-DTLSB-05_06_2024-SVCENTCO-1^06245007.0220740 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
370298528-68543-DTLSB-04_30_2024-GO95MLD-1^06245007.0220741 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
816693176-38723-DTLSB-04_30_2024-GO95TCH-1^06245007.0220743 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
305060766-71723-DTLSB-04_30_2024-GO95MLD-1^06245007.0220744 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
930839338-94243-DTLSB-04_30_2024-GO95STUB-1^06245007.0220840 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
670638028-33243-DTLSB-04_30_2024-GO95MLD-1^06245007.0220841 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
798421518-1243-DTLSB-04_30_2024-SVCWIND-1^06245007.0220843 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
242234638-76243-DTLSB-04_30_2024-GO95MLD-1^06245007.0220940 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
426310278-12043-DTLSB-04_30_2024-GO95MLD-1^06245007.0220941 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
426310278-12043-DTLSB-04_30_2024-GO95STUB-1^06245007.0220941 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
886776329-52899-DTLSB-04_10_2024-SVCENTCO-1^06245007.0221001 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
878689067-30769-DTLSB-04_11_2024-SVCWIND-1^06245007.0221101 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
201028840-77649-DTLSB-04_09_2024-GO95MLD-1^06245007.0221300 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
63078741-81463-DTLSB-04_09_2024-GO95MLD-1^06245007.0221341 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
297096151-68763-DTLSB-04_09_2024-GO95MLD-1^06245007.0221342 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
822779671-23263-DTLSB-04_29_2024-GO95MLD-1^06245007.0221443 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
721809451-81263-DTLSB-04_29_2024-RISEGRD-1^06245007.0221444 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
345970944-95023-DTLSB-04_30_2024-SVCROAD-1^06245007.0221500 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
668510756-3323-DTLSB-04_29_2024-GO95MLD-1^06245007.0221540 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
688990096-51123-DTLSB-04_29_2024-SVCENTCO-1^06245007.0221541 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
224788996-70123-DTLSB-04_29_2024-GO95BLTC-1^06245007.0221542 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2029-04-29 | 3
307143286-69023-DTLSB-04_29_2024-GO95MLD-1^06245007.0221543 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
824139275-87423-DTLSB-05_01_2024-GO95MLD-1^06245007.0221600 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
331362366-2423-DTLSB-04_29_2024-GO95MLD-1^06245007.0221641 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
331362366-2423-DTLSB-04_29_2024-GUYHINS-1^06245007.0221641 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
471066426-64223-DTLSB-04_29_2024-GO95TCH-1^06245007.0221642 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
139700216-91223-DTLSB-04_29_2024-GO95MLD-1^06245007.0221643 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
395051806-89123-DTLSB-04_29_2024-GO95MLD-1^06245007.0221644 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
555339846-73123-DTLSB-04_29_2024-GO95MLD-1^06245007.0221646 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
332039485-88123-DTLSB-05_06_2024-GO95MLD-1^06245007.0221701 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2029-05-06 | 3
183578248-8243-DTLSB-05_01_2024-CLMBTRE-1^06245007.0221740 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
130844516-23623-DTLSB-04_30_2024-SVCDEFLC-1^06245007.0221742 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
425550398-87043-DTLSB-05_06_2024-GO95CL10-1^06245007.0221743 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2029-05-06 | 3
828263588-5043-DTLSB-05_06_2024-GO95MLD-1^06245007.0221744 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
232335988-93043-DTLSB-05_06_2024-GO95MLD-1^06245007.0221745 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
264645548-12343-DTLSB-04_30_2024-GO95MLD-1^06245007.0221841 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2029-04-30 | 3
264645548-12343-DTLSB-04_30_2024-SVCWIND-1^06245007.0221841 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
931111408-19143-DTLSB-04_30_2024-GO95MLD-1^06245007.0221843 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
341703798-43543-DTLSB-04_30_2024-GO95MLD-1^06245007.0221846 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
239996178-50043-DTLSB-04_30_2024-GO95HV-1^06245007.0221940 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
436067878-45743-DTLSB-04_30_2024-GO95MLD-1^06245007.0221941 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
885392458-76443-DTLSB-04_30_2024-SVCDEFLC-1^06245007.0221942 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
311055760-31069-DTLSB-04_16_2024-CLMBTRE-1^06245007.0222002 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
748263039-61599-DTLSB-04_10_2024-POLETOP-1^06245007.0222005 | POLE | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
626333329-38549-DTLSB-04_10_2024-SVCWIND-1^06245007.0222007 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
988172589-44969-DTLSB-04_10_2024-SVCROAD-1^06245007.0222009 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
959399600-11649-DTLSB-04_11_2024-SVCDEFLC-1^06245007.0222200 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
65205700-56649-DTLSB-04_11_2024-GO95MLD-1^06245007.0222206 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
540777060-48263-DTLSB-04_17_2024-GO95MLD-1^06245007.0222444 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
679943950-46263-DTLSB-04_17_2024-GO95HV-1^06245007.0222445 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
309971040-24163-DTLSB-04_17_2024-GO95MLD-1^06245007.0222446 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
309971040-24163-DTLSB-04_17_2024-SVCWIND-1^06245007.0222446 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
596142846-47923-DTLSB-05_02_2024-GO95MLD-1^06245007.0222540 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
552098426-60623-DTLSB-05_02_2024-GUYNOINS-1^06245007.0222541 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
552098426-60623-DTLSB-05_02_2024-GUYNOINS-2^06245007.0222541 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
884209116-7523-DTLSB-05_02_2024-GO95MLD-1^06245007.0222544 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
788308306-54823-DTLSB-04_23_2024-GO95MLD-1^06245007.0222643 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
39025196-13823-DTLSB-04_23_2024-GO95MLD-1^06245007.0222644 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
815439156-50023-DTLSB-04_29_2024-GO95TCH-1^06245007.0222647 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
320602345-61549-DTLSB-04_30_2024-GO95HV-1^06245007.0222700 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2029-04-30 | 3
789737235-11549-DTLSB-04_30_2024-SVCDEFLC-1^06245007.0222701 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
472316525-1549-DTLSB-05_06_2024-GO95MLD-1^06245007.0222702 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2029-05-06 | 3
423566976-79423-DTLSB-05_02_2024-GO95MLD-1^06245007.0222741 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
210931676-58423-DTLSB-04_23_2024-GO95MLD-1^06245007.0222742 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
120875958-54743-AUDIT-06_20_2024-SVCWIND-1^06245007.0222840 | OTHER | CA-NON-TIER | Distribution | 2024-06-20 | 2027-06-20 | 2
874075848-19643-DTLSB-04_30_2024-GO95HV-1^06245007.0222842 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
641747488-41543-DTLSB-04_30_2024-SVCDEFLC-1^06245007.0222843 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
436095978-98443-DTLSB-04_30_2024-GO95MLD-1^06245007.0222844 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
436095978-98443-DTLSB-04_30_2024-GRDRODHI-1^06245007.0222844 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
793157638-13643-DTLSB-05_02_2024-GO95MLD-1^06245007.0222846 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
640919448-83643-DTLSB-04_30_2024-GO95MLD-1^06245007.0222847 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
640919448-83643-DTLSB-04_30_2024-SVCWIND-1^06245007.0222847 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
931637268-27443-DTLSB-04_30_2024-GO95MLD-1^06245007.0222849 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
188165718-71243-DTLSB-04_30_2024-GO95MLD-1^06245007.0222850 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
631976838-38243-DTLSB-04_30_2024-GO95MLD-1^06245007.0222942 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
404232111-92363-DTLSB-04_10_2024-SVCROAD-1^06245007.0223042 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
489028868-99549-DTLSB-04_11_2024-SVCWIND-1^06245007.0223200 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
104530148-67989-DTLSB-04_15_2024-SVCDEFLC-1^06245007.0223203 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
104530148-67989-DTLSB-04_15_2024-SVCWIND-1^06245007.0223203 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
145214130-72649-DTLSB-04_09_2024-SVCWIND-1^06245007.0223300 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
723567621-30763-DTLSB-04_09_2024-SVCDEFLC-1^06245007.0223342 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
674064181-75963-DTLSB-04_17_2024-GO95CLSV-1^06245007.0223344 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
674064181-75963-DTLSB-04_17_2024-SVCROAD-1^06245007.0223344 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
674064181-75963-DTLSB-04_17_2024-SVCWIND-1^06245007.0223344 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
570017570-20749-DTLSB-04_17_2024-GO95MLD-1^06245007.0223402 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
275771819-88649-DTLSB-04_17_2024-GO95MLD-1^06245007.0223403 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
688982649-28299-DTLSB-04_17_2024-GO95MLD-1^06245007.0223404 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
399036364-56364-DTLTRT-04_17_2024-SVCWIND-1^06245007.0223406 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
831050599-66653-DTLSB-04_17_2024-SVCWIND-1^06245007.0223440 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
268500136-95623-DTLSB-04_23_2024-GO95MLD-1^06245007.0223443 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
308898841-31463-DTLSB-04_17_2024-GO95HV-1^06245007.0223444 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
97957386-21823-DTLSB-04_23_2024-GO95MLD-1^06245007.0223540 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
897376306-77123-DTLSB-04_23_2024-GO95MLD-1^06245007.0223542 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
897376306-77123-DTLSB-04_23_2024-SVCENTCO-1^06245007.0223542 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
897376306-77123-DTLSB-04_23_2024-SVCENTCO-2^06245007.0223542 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
638756726-73623-DTLSB-04_23_2024-GO95HV-1^06245007.0223547 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
638756726-73623-DTLSB-04_23_2024-GO95MLD-1^06245007.0223547 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
34619535-49449-DTLSB-04_24_2024-GO95MLD-1^06245007.0223600 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
734987074-74299-DTLSB-04_23_2024-GO95MLD-1^06245007.0223601 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
558377586-49423-DTLSB-04_24_2024-GO95HV-1^06245007.0223641 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
558377586-49423-DTLSB-04_24_2024-GO95MLD-1^06245007.0223641 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
742723876-64323-DTLSB-04_24_2024-GRDRODHI-1^06245007.0223642 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
946822584-16009-DTLSB-04_23_2024-GO95MLD-1^06245007.0223700 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
551427674-46569-DTLSB-04_23_2024-GO95BLTC-1^06245007.0223701 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
551427674-46569-DTLSB-04_23_2024-GO95MLD-1^06245007.0223701 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
421443124-59499-DTLSB-04_23_2024-GO95MLD-1^06245007.0223702 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
212220714-36009-DTLSB-04_23_2024-GO95MLD-1^06245007.0223703 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
212220714-36009-DTLSB-04_23_2024-SVCENTCO-1^06245007.0223703 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
615757184-50549-DTLSB-04_23_2024-GO95MLD-1^06245007.0223706 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
731319694-84009-DTLSB-04_24_2024-GO95HV-1^06245007.0223800 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
620928074-64009-DTLSB-04_24_2024-GO95HV-1^06245007.0223802 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
495424004-88909-DTLSB-04_23_2024-GO95MLD-1^06245007.0223803 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
329026394-45599-DTLSB-04_23_2024-GO95MLD-1^06245007.0223804 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
572148684-61079-DTLSB-04_23_2024-GO95MLD-1^06245007.0223805 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
785959958-93943-DTLSB-04_23_2024-GO95HV-1^06245007.0223941 | OTHER | CA-TIER-2 | Distribution | 2024-04-23 | 2029-04-23 | 3
400633839-53549-DTLSB-04_10_2024-SVCWIND-1^06245007.0224003 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
222261839-52549-DTLSB-04_10_2024-SVCDEFLC-1^06245007.0224004 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
976002189-31399-DTLSB-04_10_2024-CLMBTRE-1^06245007.0224005 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
465220879-15549-DTLSB-04_10_2024-GO95MLD-1^06245007.0224008 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
465220879-15549-DTLSB-04_10_2024-XARMSPCR-1^06245007.0224008 | CROSSARM | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
465220879-15549-ADMIN-07_19_2024-POLETOP-1^06245007.0224008 | POLE | CA-NON-TIER | Distribution | 2024-07-19 | 2027-07-19 | 2
390712141-61069-DTLSB-04_10_2024-GUYNOINS-1^06245007.0224041 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
841163809-41899-DTLSB-04_15_2024-GO95CLSV-1^06245007.0224103 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
533416511-96363-DTLSB-04_15_2024-SVCWIND-1^06245007.0224140 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
319472111-95363-DTLSB-04_15_2024-SVCDEFLC-1^06245007.0224141 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
512772009-3649-DTLSB-04_15_2024-SVCWIND-1^06245007.0224202 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
544521778-29299-DTLSB-04_15_2024-SVCDEFLC-1^06245007.0224204 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
544521778-29299-DTLSB-04_15_2024-SVCROAD-1^06245007.0224204 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
249161564-74564-DTLSB-04_11_2024-SVCWIND-1^06245007.0224207 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
344584591-38563-DTLSB-04_16_2024-SVCWIND-1^06245007.0224342 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
954442070-28969-DTLSB-04_17_2024-SVCRUBLG-1^06245007.0224346 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
41315481-76563-DTLSB-04_17_2024-SVCDEFLC-1^06245007.0224349 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
878216799-59649-DTLSB-04_17_2024-GO95MLD-1^06245007.0224400 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
181025559-75399-DTLSB-04_17_2024-GO95MLD-1^06245007.0224402 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
181025559-75399-DTLSB-04_17_2024-SVCWIND-1^06245007.0224402 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
13995679-79649-DTLSB-04_23_2024-GO95MLD-1^06245007.0224406 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
538404289-22579-DTLSB-04_22_2024-SVCENTCO-1^06245007.0224407 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
645763401-94363-DTLSB-04_23_2024-GO95MLD-1^06245007.0224440 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
354293934-56449-DTLSB-04_17_2024-GO95MLD-1^06245007.0224501 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
354293934-56449-DTLSB-04_17_2024-POLETOP-1^06245007.0224501 | POLE | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
54736245-39623-DTLSB-05_02_2024-GO95MLD-1^06245007.0224502 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
157039844-95399-DTLSB-05_02_2024-SVCDEFLC-1^06245007.0224504 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
669923104-54799-DTLSB-04_17_2024-GO95MLD-1^06245007.0224505 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
52553165-7449-DTLSB-04_17_2024-GO95MLD-1^06245007.0224507 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
562249546-32123-DTLSB-04_17_2024-GO95MLD-1^06245007.0224508 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
864955668-47943-DTLSB-04_23_2024-GO95MLD-1^06245007.0224540 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
634411260-32260-DTLSB-04_24_2024-GUYNOINS-1^06245007.0224600 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
496669835-87449-DTLSB-04_24_2024-GO95MLD-1^06245007.0224605 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
976344954-99999-DTLSB-04_24_2024-GO95MLD-1^06245007.0224607 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
373136274-78449-DTLSB-04_23_2024-GUYHINS-1^06245007.0224702 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
373136274-78449-DTLSB-04_23_2024-SVCDEFLC-1^06245007.0224702 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
120882964-19449-DTLSB-04_23_2024-GO95MLD-1^06245007.0224703 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
994406414-69909-DTLSB-04_23_2024-POLETOP-1^06245007.0224704 | POLE | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
585442554-47009-ADMIN-09_20_2024-POLEREPL-1^06245007.0224706 | POLE | CA-NON-TIER | Distribution | 2024-09-20 | 2027-09-20 | 2
735526024-10549-DTLSB-04_24_2024-GO95MLD-1^06245007.0224708 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
120029134-30009-DTLSB-04_23_2024-GO95MLD-1^06245007.0224801 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
120029134-30009-DTLSB-04_23_2024-SVCDEFLC-1^06245007.0224801 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
120029134-30009-DTLSB-04_23_2024-SVCENTCO-1^06245007.0224801 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
841733634-41499-DTLSB-04_23_2024-GO95MLD-1^06245007.0224802 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
841733634-41499-DTLSB-04_23_2024-GRDRODHI-1^06245007.0224802 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
841733634-41499-DTLSB-04_23_2024-SVCENTCO-1^06245007.0224802 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
152443534-89909-DTLSB-04_23_2024-SVCENTCO-1^06245007.0224803 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
769047634-36589-DTLSB-04_24_2024-GRDRODHI-1^06245007.0224806 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
1995095-31189-DTLSB-04_24_2024-GO95MLD-1^06245007.0224810 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
842870754-62123-DTLSB-04_24_2024-GO95MLD-1^06245007.0224900 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
27928670-10949-AUDIT-05_22_2024-SVCENTCO-1^06245007.0225000 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2027-05-22 | 2
547151535-81535-DTLSB-04_10_2024-SVCWIND-1^06245007.0225009 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
714399266-87999-DTLSB-04_22_2024-SVCWIND-1^06245007.0225101 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
264066710-60949-DTLSB-04_29_2024-SVCWIND-1^06245007.0225105 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
264066710-60949-DTLSB-04_29_2024-SVCWIND-2^06245007.0225105 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
947538696-90949-DETAIL-04_15_2024-SVCROAD-1^06245007.0225106 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
826177106-49889-DTLSB-04_15_2024-SVCWIND-1^06245007.0225107 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
838352296-81999-DTLSB-04_15_2024-SVCDEFLC-1^06245007.0225108 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
353093026-44899-DTLSB-04_15_2024-SVCWIND-1^06245007.0225109 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
803186950-32949-DTLSB-04_22_2024-SVCROOF-1^06245007.0225200 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
803186950-32949-DTLSB-04_22_2024-SVCROOF-2^06245007.0225200 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
649301489-75753-DTLSB-05_01_2024-SECVINE-1^06245007.0225241 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
649301489-75753-DTLSB-05_01_2024-SVCWIND-1^06245007.0225241 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
907234131-61763-DTLSB-04_22_2024-SVCWIND-1^06245007.0225242 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
979345701-66663-DTLSB-04_22_2024-GO95MLD-1^06245007.0225243 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
800668449-51353-DTLSB-04_17_2024-SVCWIND-1^06245007.0225341 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
367945929-99953-DTLSB-04_17_2024-POLETOP-1^06245007.0225342 | POLE | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
367945929-99953-DTLSB-04_17_2024-SVCWIND-1^06245007.0225342 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
901689719-66953-DTLSB-04_16_2024-SVCWIND-1^06245007.0225343 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
707968500-89500-DTLSB-04_16_2024-SVCDEFLC-1^06245007.0225348 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
766276768-13849-DTLSB-04_22_2024-GO95MLD-1^06245007.0225401 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
766276768-13849-DTLSB-04_22_2024-SVCENTCO-1^06245007.0225401 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
502505799-4153-DTLSB-04_22_2024-SVCROOF-1^06245007.0225441 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
502505799-4153-DTLSB-04_22_2024-SVCWIND-1^06245007.0225441 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
555543521-11449-DTLSB-04_24_2024-GO95HV-1^06245007.0225502 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
695347701-22449-DTLSB-04_24_2024-GO95MLD-1^06245007.0225602 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
695347701-22449-DTLSB-04_24_2024-SVCROAD-1^06245007.0225602 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
93355921-71449-DETAIL-04_24_2024-SVCROAD-1^06245007.0225604 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
93355921-71449-DETAIL-04_24_2024-SVCROAD-2^06245007.0225604 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
9251171-2009-DTLSB-04_23_2024-GO95MLD-1^06245007.0225703 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
9251171-2009-DTLSB-04_23_2024-SVCENTCO-1^06245007.0225703 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
305786361-59909-DTLSB-04_24_2024-SVCDEFLC-1^06245007.0225803 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
186273956-11223-DTLSB-04_10_2024-GO95TCH-1^06245007.0226008 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
390911834-19849-DTLSB-04_10_2024-SVCWIND-1^06245007.0226009 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
80843276-57689-DTLSB-04_10_2024-GO95HV-1^06245007.0226011 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
703449206-18999-DTLSB-04_15_2024-SVCWIND-1^06245007.0226100 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
61617286-40949-DTLSB-04_15_2024-CLMBTRE-1^06245007.0226101 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
61617286-40949-DTLSB-04_15_2024-SVCWIND-1^06245007.0226101 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
215801273-85273-DTLSB-04_22_2024-SVCENTCO-1^06245007.0226111 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
429503430-89089-DTLSB-04_22_2024-SVCWIND-1^06245007.0226204 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
522815991-43663-DETAIL-04_22_2024-SVCWIND-1^06245007.0226247 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
522815991-43663-DETAIL-04_22_2024-SVCWIND-2^06245007.0226247 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
530862668-97749-DTLSB-04_16_2024-SVCENTCO-1^06245007.0226300 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
898679659-24353-DTLSB-04_22_2024-SVCENTCO-1^06245007.0226344 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
849849599-92953-DETAIL-04_16_2024-SVCWIND-1^06245007.0226345 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
831316289-35753-DTLSB-04_16_2024-SVCWIND-1^06245007.0226346 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
523163538-81849-DTLSB-04_29_2024-SVCROAD-1^06245007.0226401 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
229942078-1849-DTLSB-04_22_2024-SVCENTCO-1^06245007.0226404 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
65006818-79749-DTLSB-04_29_2024-CLRTOUCH-1^06245007.0226407 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
907785199-82453-DTLSB-04_29_2024-GO95MLD-1^06245007.0226442 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
12129489-79353-DTLSB-04_22_2024-GO95MLD-1^06245007.0226443 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
642078779-13753-DTLSB-04_29_2024-GO95MLD-1^06245007.0226444 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2029-04-29 | 3
642078779-13753-DTLSB-04_29_2024-RISEGRD-1^06245007.0226444 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
267904529-85553-DTLSB-04_29_2024-CLRTOUCH-1^06245007.0226445 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
267904529-85553-DTLSB-04_29_2024-GO95MLD-1^06245007.0226445 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2029-04-29 | 3
9757039-69553-DTLSB-04_29_2024-GO95MLD-1^06245007.0226446 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
9757039-69553-DTLSB-04_29_2024-GO95TCH-1^06245007.0226446 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
533576029-66753-DTLSB-04_29_2024-GO95MLD-1^06245007.0226447 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
533576029-66753-AUDIT-05_22_2024-SVCRUBLG-1^06245007.0226447 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2027-05-22 | 2
579723011-25399-DTLSB-04_24_2024-GO95MLD-1^06245007.0226500 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
341939804-41813-DTLSB-04_29_2024-CLMBTRE-1^06245007.0226542 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
341939804-41813-DTLSB-04_29_2024-SVCWIND-1^06245007.0226542 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
489976341-20693-DETAIL-04_24_2024-GO95TCH-1^06245007.0226601 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
788056361-75279-DTLSB-04_23_2024-GO95MLD-1^06245007.0226700 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
788056361-75279-DTLSB-04_23_2024-GRDRODHI-1^06245007.0226700 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
788056361-75279-DTLSB-04_23_2024-GRDRODHI-2^06245007.0226700 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
384859004-11009-DTLSB-04_23_2024-GO95MLD-1^06245007.0226740 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
384859004-11009-DTLSB-04_23_2024-GRDRODHI-1^06245007.0226740 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
384859004-11009-AUDIT-06_20_2024-CLMBHAZ-1^06245007.0226740 | OTHER | CA-NON-TIER | Distribution | 2024-06-20 | 2027-06-20 | 2
341063761-29909-DTLSB-05_06_2024-GO95HV-1^06245007.0226800 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2029-05-06 | 3
341063761-29909-DTLSB-05_06_2024-GO95TCH-1^06245007.0226800 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
341063761-29909-AUDIT-06_20_2024-SVCENTCO-1^06245007.0226800 | OTHER | CA-NON-TIER | Distribution | 2024-06-20 | 2027-06-20 | 2
316094551-78909-DTLSB-05_02_2024-GUYNOINS-1^06245007.0226802 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
316094551-78909-DTLSB-05_02_2024-GUYNOINS-2^06245007.0226802 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
236555096-75849-DTLSB-04_15_2024-SVCWIND-1^06245007.0227004 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
826490441-68949-DTLSB-04_09_2024-SVCENTCO-1^06245007.0227014 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
208941056-47849-DTLSB-04_15_2024-SVCDEFLC-1^06245007.0227100 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
1607226-90589-DTLSB-04_15_2024-GO95MLD-1^06245007.0227105 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
1607226-90589-DTLSB-04_15_2024-SVCENTCO-1^06245007.0227105 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
314363016-27289-DTLSB-04_22_2024-SVCWIND-1^06245007.0227202 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
890520130-97849-DTLSB-04_22_2024-ENCHRW-1^06245007.0227204 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
651253985-93985-DTLSB-04_16_2024-SVCWIND-1^06245007.0227207 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
680865646-90973-DTLSB-04_22_2024-SVCWIND-1^06245007.0227246 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
680865646-90973-DTLSB-04_22_2024-SVCWIND-2^06245007.0227246 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
396505398-38749-DTLSB-05_01_2024-SVCDEFLC-1^06245007.0227307 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
711073298-85999-DTLTRT-04_16_2024-SVCENTCO-1^06245007.0227312 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
29677616-11223-DTLSB-05_01_2024-SVCWIND-1^06245007.0227341 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
100313159-10953-DTLSB-04_16_2024-GO95MLD-1^06245007.0227346 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
100313159-10953-DTLSB-04_16_2024-GRDRODHI-1^06245007.0227346 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
745356149-26853-DTLSB-04_16_2024-CLMBTRE-1^06245007.0227347 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
745356149-26853-DTLSB-04_16_2024-GO95HV-1^06245007.0227347 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
926795326-63749-DTLSB-05_01_2024-SVCDEFLC-1^06245007.0227400 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
613017754-4113-DTLSB-05_01_2024-GO95MLD-1^06245007.0227440 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
129570679-41653-DTLSB-05_06_2024-GO95MLD-1^06245007.0227444 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
129570679-41653-DTLSB-05_06_2024-GRDRODHI-1^06245007.0227444 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
129570679-41653-DTLSB-05_06_2024-GRDRODHI-2^06245007.0227444 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
697390941-55999-DTLSB-05_01_2024-GO95MLD-1^06245007.0227500 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
193950251-28349-DTLSB-04_29_2024-GO95TCH-1^06245007.0227501 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
193950251-28349-DTLSB-04_29_2024-SVCDEFLC-1^06245007.0227501 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
881169904-92813-DTLSB-04_29_2024-CLMBTRE-1^06245007.0227542 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
276423933-14113-DTLSB-04_24_2024-GO95MLD-1^06245007.0227544 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
142931423-52513-DTLSB-04_24_2024-SVCDEFLC-1^06245007.0227545 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
142931423-52513-DTLSB-04_24_2024-SVCWIND-1^06245007.0227545 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
316765703-19313-DTLSB-04_25_2024-GUYNOINS-1^06245007.0227548 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
316765703-19313-DTLSB-04_25_2024-GUYNOINS-2^06245007.0227548 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
471979003-98313-DTLSB-04_25_2024-GUYHINS-1^06245007.0227549 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
390280083-16313-DTLSB-04_25_2024-SVCWIND-1^06245007.0227550 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
9262543-18113-DTLSB-05_01_2024-GO95MLD-1^06245007.0227640 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
9262543-18113-DTLSB-05_01_2024-SVCWIND-1^06245007.0227640 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
9262543-18113-DTLSB-05_01_2024-SVCWIND-2^06245007.0227640 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
806426433-76113-DTLSB-05_01_2024-SVCWIND-1^06245007.0227641 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
402774660-55669-DTLSB-05_02_2024-SVCDEFLC-1^06245007.0227901 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2027-05-02 | 2
313891386-56949-DTLSB-04_09_2024-SVCROAD-1^06245007.0228003 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
313891386-56949-DTLSB-04_09_2024-SVCRUBLG-1^06245007.0228003 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
833203443-62069-DTLSB-04_09_2024-SVCDEFLC-1^06245007.0228005 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
833203443-62069-DTLSB-04_09_2024-SVCDEFLC-2^06245007.0228005 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
833203443-62069-DTLSB-04_09_2024-SVCWIND-1^06245007.0228005 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
634847673-98949-DTLSB-04_09_2024-SVCDEFLC-1^06245007.0228009 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
111140866-24749-DTLSB-04_25_2024-GO95CLSV-1^06245007.0228300 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
111140866-24749-DTLSB-04_25_2024-SVCWIND-1^06245007.0228300 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
983843795-74749-DTLSB-04_25_2024-POLETOP-1^06245007.0228307 | POLE | CA-TIER-2 | Distribution | 2024-04-25 | 2025-04-25 | 2
14765082-79082-DTLSB-04_25_2024-GO95MLD-1^06245007.0228341 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
218000746-10323-DTLSB-05_01_2024-SVCWIND-1^06245007.0228441 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2027-05-01 | 2
77674750-94750-DTLTRT-04_25_2024-SVCWIND-1^06245007.0228502 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
447873574-51313-DTLSB-04_25_2024-GO95MLD-1^06245007.0228541 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
374422733-5913-DTLSB-05_02_2024-GO95MLD-1^06245007.0228543 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2027-05-02 | 2
374422733-5913-DTLSB-05_02_2024-SVCWIND-1^06245007.0228543 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2027-05-02 | 2
106967033-33913-DTLSB-05_01_2024-GO95MLD-1^06245007.0228544 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
36408264-99213-DTLSB-04_25_2024-GO95MLD-1^06245007.0228545 | OTHER | CA-TIER-2 | Distribution | 2024-04-25 | 2027-04-25 | 2
36408264-99213-DTLSB-04_25_2024-SVCRUBLG-1^06245007.0228545 | OTHER | CA-TIER-2 | Distribution | 2024-04-25 | 2027-04-25 | 2
934699873-5313-DTLSB-04_25_2024-SVCWIND-1^06245007.0228547 | OTHER | CA-TIER-2 | Distribution | 2024-04-25 | 2027-04-25 | 2
945300383-77349-DTLSB-05_01_2024-GO95MLD-1^06245007.0228601 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2029-05-01 | 3
33559771-17349-DTLSB-05_01_2024-SVCROOF-1^06245007.0228602 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
651321313-70913-DTLSB-05_01_2024-GO95MLD-1^06245007.0228641 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
198909553-33713-DTLSB-05_01_2024-GO95HV-1^06245007.0228643 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2029-05-01 | 3
71447243-36913-DTLSB-05_01_2024-GO95HV-1^06245007.0228645 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2029-05-01 | 3
71447243-36913-DTLSB-05_01_2024-GO95MLD-1^06245007.0228645 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
584250393-41013-DTLSB-05_02_2024-GO95HV-1^06245007.0228740 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2029-05-02 | 3
531771324-29813-DTLSB-05_02_2024-GO95HV-1^06245007.0228741 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2029-05-02 | 3
531771324-29813-AUDIT-05_22_2024-GO95TCH-1^06245007.0228741 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2027-05-22 | 2
531771324-29813-AUDIT-05_22_2024-RISEGRD-1^06245007.0228741 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2027-05-22 | 2
274389373-83913-DTLSB-05_01_2024-SVCROAD-1^06245007.0228746 | OTHER | CA-NON-TIER | Distribution | 2024-05-01 | 2027-05-01 | 2
232410653-37909-DTLSB-05_02_2024-ENCHRW-1^06245007.0228800 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
414028793-19793-DTLSB-05_02_2024-GO95MLD-1^06245007.0228904 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2027-05-02 | 2
21225893-75893-DTLSB-05_02_2024-GO95HV-1^06245007.0228906 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2029-05-02 | 3
21225893-75893-DTLSB-05_02_2024-GO95MLD-1^06245007.0228906 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2027-05-02 | 2
441741956-27323-DTLSB-04_25_2024-GO95MLD-1^06245007.0229342 | OTHER | CA-TIER-2 | Distribution | 2024-04-25 | 2027-04-25 | 2
264512435-15749-DTLSB-04_25_2024-GO95MLD-1^06245007.0229400 | OTHER | CA-TIER-2 | Distribution | 2024-04-25 | 2027-04-25 | 2
283096306-95749-DTLSB-05_06_2024-GO95HV-1^06245007.0229406 | OTHER | CA-TIER-2 | Distribution | 2024-05-06 | 2029-05-06 | 3
375568993-36169-DTLSB-04_25_2024-SVCWIND-1^06245007.0229501 | OTHER | CA-TIER-2 | Distribution | 2024-04-25 | 2027-04-25 | 2
2188463-32313-DTLSB-04_25_2024-POLETOP-1^06245007.0229541 | POLE | CA-TIER-2 | Distribution | 2024-04-25 | 2025-04-25 | 2
639235709-85709-DTLSB-04_25_2024-POLETOP-1^06245007.0229544 | POLE | CA-TIER-2 | Distribution | 2024-04-25 | 2025-04-25 | 2
36511183-68913-DTLSB-05_02_2024-GO95HV-1^06245007.0229742 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2029-05-02 | 3
312955883-45913-DTLSB-05_02_2024-GO95MLD-1^06245007.0229743 | OTHER | CA-NON-TIER | Distribution | 2024-05-02 | 2027-05-02 | 2
240029984-73909-DTLSB-05_02_2024-GO95HV-1^06245007.0229843 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2029-05-02 | 3
240029984-73909-DTLSB-05_02_2024-GO95MLD-1^06245007.0229843 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2027-05-02 | 2
515129484-30713-DTLSB-05_02_2024-GO95MLD-1^06245007.0229941 | OTHER | CA-TIER-2 | Distribution | 2024-05-02 | 2027-05-02 | 2
19061936-19899-DTLSB-09_30_2024-GO95BLTC-1^06245007.0230001 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
19061936-19899-DTLSB-09_30_2024-GO95MLD-1^06245007.0230001 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
677046676-67579-DTLSB-09_30_2024-GO95MLD-1^06245007.0230003 | OTHER | FHCA | Distribution | 2024-09-30 | 2027-09-30 | 2
849704460-31909-DTLSB-09_30_2024-GO95HV-1^06245007.0230040 | OTHER | FHCA | Distribution | 2024-09-30 | 2029-09-30 | 3
494241970-12159-DTLSB-09_30_2024-RISEGRD-1^06245007.0230140 | OTHER | FHCA | Distribution | 2024-09-30 | 2027-09-30 | 2
739407870-32159-DTLSB-09_30_2024-GO95MLD-1^06245007.0230141 | OTHER | FHCA | Distribution | 2024-09-30 | 2029-09-30 | 3
31791870-23909-DTLSB-09_30_2024-GO95HV-1^06245007.0230241 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
789760096-13159-DTLSB-09_30_2024-GO95MLD-1^06245007.0231303 | OTHER | FHCA | Distribution | 2024-09-30 | 2027-09-30 | 2
269740180-4389-DTLSB-09_30_2024-GO95HV-1^06245007.0231341 | OTHER | FHCA | Distribution | 2024-09-30 | 2029-09-30 | 3
794999050-95313-DTLSB-09_30_2024-GO95MLD-1^06245007.0231441 | OTHER | FHCA | Distribution | 2024-09-30 | 2027-09-30 | 2
650066223-77059-DTLSB-09_30_2024-GO95MLD-1^06245007.0231500 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
198698893-7059-DTLSB-09_30_2024-GO95BLTC-1^06245007.0231501 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
198698893-7059-DTLSB-09_30_2024-GO95MLD-1^06245007.0231501 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
198698893-7059-DTLSB-09_30_2024-RISEBKSP-1^06245007.0231501 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
159507504-97059-DTLSB-09_30_2024-GO95MLD-1^06245007.0231540 | OTHER | FHCA | Distribution | 2024-09-30 | 2027-09-30 | 2
519585894-67059-DTLSB-09_30_2024-CLMBTRE-1^06245007.0231541 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2025-09-30 | 2
193461366-10789-DTLSB-09_30_2024-CLRTOUCH-1^06245007.0232300 | CONDUCTOR | CA-TIER-2 | Distribution | 2024-09-30 | 2025-09-30 | 2
193461366-10789-DTLSB-09_30_2024-GO95BLTC-1^06245007.0232300 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
576428090-6159-DTLSB-09_30_2024-GO95MLD-1^06245007.0232401 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
923302716-42793-DTLSB-09_30_2024-GO95MLD-1^06245007.0232404 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
710805596-45159-DTLSB-09_30_2024-GO95MLD-1^06245007.0232405 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
928940790-52569-DTLSB-09_30_2024-SVCROOF-1^06245007.0232408 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
193745256-43159-DTLSB-09_30_2024-GO95MLD-1^06245007.0232412 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
193745256-43159-DTLSB-09_30_2024-RISEGRD-1^06245007.0232412 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
477534173-76059-DTLSB-09_30_2024-GO95MLD-1^06245007.0232501 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
158731353-96059-DTLSB-09_30_2024-GO95BLTC-1^06245007.0232502 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
158731353-96059-DTLSB-09_30_2024-GO95MLD-1^06245007.0232502 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
262346916-15159-DTLSB-09_30_2024-GUYNOINS-1^06245007.0233400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
526038943-98179-DTLSB-09_30_2024-GO95HV-1^06245007.0233401 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
526038943-98179-DTLSB-09_30_2024-GO95MLD-1^06245007.0233401 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
526038943-98179-DTLSB-09_30_2024-GO95TCH-1^06245007.0233401 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
599928083-56059-DTLSB-09_30_2024-GO95BLTC-1^06245007.0234502 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
599928083-56059-DTLSB-09_30_2024-GO95HV-1^06245007.0234502 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2029-09-30 | 3
599928083-56059-DTLSB-09_30_2024-GO95MLD-1^06245007.0234502 | OTHER | CA-TIER-2 | Distribution | 2024-09-30 | 2027-09-30 | 2
243982085-48399-DTLSB-09_05_2024-GO95HV-1^06245007.0235601 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
243982085-48399-DTLSB-09_05_2024-XARMSPCR-1^06245007.0235601 | CROSSARM | CA-TIER-2 | Distribution | 2024-09-05 | 2025-09-05 | 2
864050186-57399-DTLSB-09_05_2024-GO95HV-1^06245007.0236601 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
375144486-87879-DTLSB-09_05_2024-GO95HV-1^06245007.0236603 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
535141276-27399-DTLSB-09_05_2024-GO95HV-1^06245007.0237600 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
346480606-6399-DTLSB-09_05_2024-GO95MLD-1^06245007.0238701 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2029-09-05 | 3
734353541-51851-DETAIL-03_04_2024-GO95HV-1^06245007.0271100 | OTHER | CA-TIER-2 | Distribution | 2024-03-04 | 2029-03-04 | 3
734353541-51851-DETAIL-03_04_2024-GO95MLD-1^06245007.0271100 | OTHER | CA-TIER-2 | Distribution | 2024-03-04 | 2027-03-04 | 2
712324245-65703-DETAIL-03_06_2024-SVCROAD-1^06245007.0271900 | OTHER | CA-TIER-2 | Distribution | 2024-03-06 | 2027-03-06 | 2
578517315-88233-DETAIL-03_04_2024-SVCDEFLC-1^06245007.0272000 | OTHER | CA-TIER-2 | Distribution | 2024-03-04 | 2027-03-04 | 2
578517315-88233-DETAIL-03_04_2024-SVCDEFLC-2^06245007.0272000 | OTHER | CA-TIER-2 | Distribution | 2024-03-04 | 2027-03-04 | 2
717680436-26659-DETAIL-03_06_2024-SVCROAD-1^06245007.0272701 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
844657365-60759-DETAIL-03_06_2024-SVCENTCO-1^06245007.0272902 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
664246425-20759-DETAIL-03_06_2024-GO95MLD-1^06245007.0272904 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
664246425-20759-DETAIL-03_06_2024-POLETOP-1^06245007.0272904 | POLE | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
345539445-59699-DETAIL-03_06_2024-SVCDEFLC-1^06245007.0272906 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
251268125-31759-DETAIL-03_04_2024-GO95MLD-1^06245007.0273000 | OTHER | CA-TIER-2 | Distribution | 2024-03-04 | 2027-03-04 | 2
196405846-65499-DETAIL-03_06_2024-SVCDEFLC-1^06245007.0273901 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
196405846-65499-DETAIL-03_06_2024-SVCWIND-1^06245007.0273901 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
196405846-65499-DETAIL-03_06_2024-SVCWIND-2^06245007.0273901 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
375343966-59659-DETAIL-03_12_2024-ENCHRW-1^06245007.0273902 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
314235234-25518-DETAIL-03_04_2024-SVCROAD-1^06245007.0274301 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
468995853-72189-DETAIL-03_04_2024-GO95MLD-1^06245007.0274307 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
27205405-38233-DETAIL-03_04_2024-GO95MLD-1^06245007.0274308 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
27205405-38233-DETAIL-03_04_2024-RISEBKSP-1^06245007.0274308 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
466059204-64973-DETAIL-03_04_2024-SVCROAD-1^06245007.0274342 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
466059204-64973-DETAIL-03_04_2024-SVCROAD-2^06245007.0274342 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
65402834-24173-DETAIL-03_04_2024-SVCDEFLC-1^06245007.0274441 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
888777788-18788-DETAIL-03_04_2024-GO95MLD-1^06245007.0274445 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
60207915-32373-DETAIL-03_04_2024-GO95MLD-1^06245007.0274500 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
898157306-78459-DETAIL-03_06_2024-CLMBTRE-1^06245007.0274502 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
898157306-78459-DETAIL-03_06_2024-GO95MLD-1^06245007.0274502 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
996950125-49459-DETAIL-03_06_2024-GO95MLD-1^06245007.0274503 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
649011256-43659-DETAIL-03_12_2024-CLMBTRE-1^06245007.0274504 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
668205636-85109-DETAIL-03_04_2024-GO95MLD-1^06245007.0275100 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
454156215-5859-DETAIL-03_04_2024-SVCROAD-1^06245007.0275101 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
510791105-60013-DETAIL-03_04_2024-GO95MLD-1^06245007.0275102 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
760161055-98469-DETAIL-03_04_2024-GO95MLD-1^06245007.0275104 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
328748465-87859-DETAIL-03_04_2024-GO95MLD-1^06245007.0275200 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
449291875-64689-DETAIL-03_04_2024-GO95MLD-1^06245007.0275201 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
372855534-699-DETAIL-03_05_2024-SVCROAD-1^06245007.0275302 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
502105859-9513-DETAIL-03_05_2024-SVCDEFLC-1^06245007.0275343 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
754477949-67513-DETAIL-03_05_2024-GUYHINS-1^06245007.0275344 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
70457899-34713-DETAIL-03_04_2024-GO95HV-1^06245007.0275353 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2029-03-04 | 3
70457899-34713-DETAIL-03_04_2024-GO95MLD-1^06245007.0275353 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
70457899-34713-DETAIL-03_04_2024-SVCDEFLC-1^06245007.0275353 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
70457899-34713-DETAIL-03_04_2024-SVCDEFLC-2^06245007.0275353 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
306358285-19703-DETAIL-03_05_2024-SVCROAD-1^06245007.0275401 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
3956503-77589-DETAIL-03_06_2024-SVCWIND-1^06245007.0275403 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
741242301-5401-DETAIL-03_12_2024-GO95MLD-1^06245007.0275405 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
837314993-15379-DETAIL-03_04_2024-GO95MLD-1^06245007.0275442 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
52639388-28459-DETAIL-03_06_2024-GO95MLD-1^06245007.0275443 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
52639388-28459-DETAIL-03_06_2024-GRDRODHI-1^06245007.0275443 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
860489616-5099-DETAIL-03_06_2024-GO95MLD-1^06245007.0275505 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
876628774-33489-DETAIL-03_12_2024-GO95MLD-1^06245007.0275509 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2029-03-12 | 3
896816426-2999-DETAIL-03_06_2024-GO95MLD-1^06245007.0275510 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
896816426-2999-DETAIL-03_06_2024-GUYHINS-1^06245007.0275510 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
886393756-70089-DETAIL-03_06_2024-GO95MLD-1^06245007.0275511 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
794799955-11699-DETAIL-03_06_2024-GO95HV-1^06245007.0275512 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
794799955-11699-DETAIL-03_06_2024-GO95MLD-1^06245007.0275512 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
482929745-40559-DETAIL-03_12_2024-GO95MLD-1^06245007.0275608 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
615160264-58979-DETAIL-03_07_2024-GO95TCH-1^06245007.0275609 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
773201034-92689-DETAIL-03_07_2024-GO95CL10-1^06245007.0275611 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2029-03-07 | 3
773201034-92689-DETAIL-03_07_2024-GO95MLD-1^06245007.0275611 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
986755474-20689-DETAIL-03_07_2024-GO95HV-1^06245007.0275614 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2029-03-07 | 3
986755474-20689-DETAIL-03_07_2024-GO95MLD-1^06245007.0275614 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
781799965-15559-DETAIL-03_07_2024-GO95MLD-1^06245007.0275615 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
71129764-89699-DETAIL-03_12_2024-GO95MLD-1^06245007.0275705 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
410245454-32899-AUDIT-03_21_2024-POLETOP-1^06245007.0275707 | POLE | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
410245454-32899-ADMIN-04_05_2024-ABNDEQPM-1^06245007.0275707 | OTHER | CA-NON-TIER | Distribution | 2024-04-05 | 2029-04-05 | 3
74472138-38983-DETAIL-03_07_2024-GO95MLD-1^06245007.0275741 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
160558238-21483-DETAIL-03_07_2024-GO95MLD-1^06245007.0275743 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
702933978-53383-DETAIL-03_07_2024-GUYHINS-1^06245007.0275840 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
702933978-53383-DETAIL-03_07_2024-GUYHINS-2^06245007.0275840 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
702933978-53383-ADMIN-03_07_2024-POLEREPL-1^06245007.0275840 | POLE | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
702933978-53383-DETAIL-03_07_2024-XARMSPCR-1^06245007.0275840 | CROSSARM | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
902705698-64383-DETAIL-03_07_2024-GO95MLD-1^06245007.0275841 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
902705698-64383-DETAIL-03_07_2024-SVCWIND-1^06245007.0275841 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
902705698-64383-DETAIL-03_07_2024-XARMSPCR-1^06245007.0275841 | CROSSARM | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
728225418-26383-DETAIL-03_07_2024-SVCWIND-1^06245007.0275842 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
231472224-90799-DETAIL-03_05_2024-GO95MLD-1^06245007.0276100 | OTHER | CA-TIER-2 | Distribution | 2024-03-05 | 2027-03-05 | 2
641689166-7859-DETAIL-03_05_2024-GO95MLD-1^06245007.0276204 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
131588473-60379-DETAIL-03_05_2024-GO95MLD-1^06245007.0276300 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
337346833-23103-DETAIL-03_05_2024-GO95MLD-1^06245007.0276303 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
337346833-23103-AUDIT-03_21_2024-GO95HV-1^06245007.0276303 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
180454293-33003-DETAIL-03_05_2024-SVCENTCO-1^06245007.0276304 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
384609449-93413-DETAIL-03_05_2024-GO95CLSV-1^06245007.0276340 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
223637275-66703-DETAIL-03_05_2024-SVCROAD-1^06245007.0276400 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
229260473-50989-DETAIL-03_05_2024-GO95MLD-1^06245007.0276401 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
822751564-39859-DETAIL-03_05_2024-GO95MLD-1^06245007.0276407 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
890881661-78581-DETAIL-03_05_2024-GO95MLD-1^06245007.0276410 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
890881661-78581-DETAIL-03_05_2024-RISEGRD-1^06245007.0276410 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
236851079-92713-DETAIL-03_05_2024-SVCWIND-1^06245007.0276441 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
200968505-75459-DETAIL-03_06_2024-SVCROAD-1^06245007.0276503 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
75491936-76183-DETAIL-03_12_2024-GO95HV-1^06245007.0276805 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2029-03-12 | 3
959565656-51899-DETAIL-03_12_2024-GO95MLD-1^06245007.0276807 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
586412073-39189-DETAIL-03_05_2024-GO95MLD-1^06245007.0277300 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
586412073-39189-DETAIL-03_05_2024-GUYHINS-1^06245007.0277300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
320128196-2459-DETAIL-03_07_2024-SVCDEFLC-1^06245007.0277804 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
569340543-32459-DETAIL-03_12_2024-SVCWIND-1^06245007.0277811 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
569340543-32459-DETAIL-03_12_2024-SVCWIND-2^06245007.0277811 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
317027734-58999-DETAIL-03_12_2024-SVCDEFLC-1^06245007.0277812 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
206053716-63459-DETAIL-03_12_2024-SVCDEFLC-1^06245007.0277903 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
293836406-54069-DETAIL-03_12_2024-SVCDEFLC-1^06245007.0277907 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
701429676-91279-DETAIL-03_05_2024-GO95HV-1^06245007.0278101 | OTHER | CA-TIER-2 | Distribution | 2024-03-05 | 2029-03-05 | 3
701429676-91279-DETAIL-03_05_2024-GO95MLD-1^06245007.0278101 | OTHER | CA-TIER-2 | Distribution | 2024-03-05 | 2027-03-05 | 2
907482474-49759-DETAIL-03_05_2024-GO95HV-1^06245007.0278102 | OTHER | CA-TIER-2 | Distribution | 2024-03-05 | 2029-03-05 | 3
49145914-92459-DETAIL-03_07_2024-SVCROAD-1^06245007.0278900 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
50335333-31589-DETAIL-03_12_2024-SVCDEFLC-1^06245007.0278905 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
50335333-31589-DETAIL-03_12_2024-SVCDEFLC-2^06245007.0278905 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
50335333-31589-DETAIL-03_12_2024-SVCDEFLC-3^06245007.0278905 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
660242093-39479-DETAIL-03_05_2024-GO95HV-1^06245007.0279100 | OTHER | CA-TIER-2 | Distribution | 2024-03-05 | 2029-03-05 | 3
160586490-46959-DETAIL-03_21_2024-GO95MLD-1^06245007.0280000 | OTHER | CA-TIER-2 | Distribution | 2024-03-21 | 2027-03-21 | 2
894394110-57959-DETAIL-03_21_2024-GO95HV-1^06245007.0280200 | OTHER | CA-TIER-2 | Distribution | 2024-03-21 | 2029-03-21 | 3
940126010-27959-DETAIL-03_21_2024-GO95HV-1^06245007.0280202 | OTHER | CA-TIER-2 | Distribution | 2024-03-21 | 2029-03-21 | 3
593079770-97959-DETAIL-03_21_2024-GO95MLD-1^06245007.0280300 | OTHER | CA-TIER-2 | Distribution | 2024-03-21 | 2027-03-21 | 2
593079770-97959-DETAIL-03_21_2024-POLETOP-1^06245007.0280300 | POLE | CA-TIER-2 | Distribution | 2024-03-21 | 2025-03-21 | 2
286520911-57569-DETAIL-03_21_2024-GO95MLD-1^06245007.0280301 | OTHER | CA-TIER-2 | Distribution | 2024-03-21 | 2029-03-21 | 3
401664401-26169-DETAIL-03_13_2024-GO95MLD-1^06245007.0280401 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
941511391-59099-DETAIL-03_13_2024-GO95MLD-1^06245007.0280501 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
47357620-82789-DETAIL-03_13_2024-GO95HV-1^06245007.0282200 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
483654200-47169-DETAIL-03_13_2024-GO95HV-1^06245007.0282201 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
483654200-47169-DETAIL-03_13_2024-GO95MLD-1^06245007.0282201 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
158025770-2199-DETAIL-03_13_2024-GO95MLD-1^06245007.0282202 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
215620680-30499-DETAIL-03_13_2024-GO95BLTC-1^06245007.0282300 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
215620680-30499-DETAIL-03_13_2024-GO95HV-1^06245007.0282300 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
215620680-30499-DETAIL-03_13_2024-GO95MLD-1^06245007.0282300 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
38010911-71973-DETAIL-03_13_2024-GO95HV-1^06245007.0282341 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
658496571-49893-DETAIL-03_13_2024-GO95HV-1^06245007.0282440 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
1207771-50993-DETAIL-03_13_2024-GO95MLD-1^06245007.0282441 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
549963560-44189-DETAIL-03_13_2024-GO95MLD-1^06245007.0283204 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
739095961-85959-DETAIL-03_13_2024-GO95MLD-1^06245007.0283400 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
324197070-3959-DETAIL-03_13_2024-GO95MLD-1^06245007.0284100 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
335699260-52959-DETAIL-03_13_2024-GO95MLD-1^06245007.0284101 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
207063760-63959-DETAIL-03_13_2024-GO95MLD-1^06245007.0284200 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
909561701-14959-DETAIL-03_13_2024-GO95MLD-1^06245007.0284300 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
575080390-36858-DETAIL-03_13_2024-GO95MLD-1^06245007.0284301 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
845503301-63489-DETAIL-03_13_2024-GO95MLD-1^06245007.0284400 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
481930869-71959-DETAIL-03_13_2024-GO95MLD-1^06245007.0285000 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
535291370-41959-DETAIL-03_13_2024-GO95MLD-1^06245007.0285002 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
535291370-41959-DETAIL-03_13_2024-GO95TCH-1^06245007.0285002 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
327917640-12959-DETAIL-03_13_2024-SVCDEFLC-1^06245007.0285100 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
639777950-54789-DETAIL-03_13_2024-GO95MLD-1^06245007.0285101 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
370074350-90399-DETAIL-03_13_2024-GO95MLD-1^06245007.0285102 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
495083390-5390-DETAIL-03_13_2024-GO95HV-1^06245007.0285400 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2029-03-13 | 3
495083390-5390-DETAIL-03_13_2024-GO95MLD-1^06245007.0285400 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
462186423-21169-DETAIL-03_12_2024-POLETOP-1^06245007.0285900 | POLE | CA-TIER-2 | Distribution | 2024-03-12 | 2025-03-12 | 2
257527040-80959-DETAIL-03_13_2024-SVCDEFLC-1^06245007.0286000 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
554403240-56299-DETAIL-03_13_2024-GO95MLD-1^06245007.0286004 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
175004191-74489-DETAIL-03_13_2024-SVCNEUT-1^06245007.0286100 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
477240541-35379-DETAIL-03_13_2024-GRDRODHI-1^06245007.0286103 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
853140310-93169-DETAIL-03_13_2024-GO95MLD-1^06245007.0287001 | OTHER | CA-TIER-2 | Distribution | 2024-03-13 | 2027-03-13 | 2
263556613-50169-DETAIL-03_12_2024-POLETOP-1^06245007.0287901 | POLE | CA-TIER-2 | Distribution | 2024-03-12 | 2025-03-12 | 2
208413050-12169-DETAIL-03_12_2024-ENCHRW-1^06245007.0288901 | OTHER | CA-TIER-2 | Distribution | 2024-03-12 | 2027-03-12 | 2
205042880-71169-DETAIL-03_12_2024-SVCDEFLC-1^06245007.0289900 | OTHER | CA-TIER-2 | Distribution | 2024-03-12 | 2027-03-12 | 2
458521423-51209-DETAIL-06_18_2024-SVCDEFLC-1^06245007.0290500 | OTHER | CA-TIER-2 | Distribution | 2024-06-18 | 2027-06-18 | 2
436755503-15359-DETAIL-06_18_2024-SVCDEFLC-1^06245007.0290502 | OTHER | CA-TIER-2 | Distribution | 2024-06-18 | 2027-06-18 | 2
894520283-38899-DETAIL-06_18_2024-SVCENTCO-1^06245007.0291300 | OTHER | CA-TIER-2 | Distribution | 2024-06-18 | 2027-06-18 | 2
645247633-70589-DETAIL-06_18_2024-SVCDEFLC-1^06245007.0297201 | OTHER | CA-TIER-2 | Distribution | 2024-06-18 | 2027-06-18 | 2
246413203-39789-DETAIL-06_18_2024-SVCDEFLC-1^06245007.0298202 | OTHER | CA-TIER-2 | Distribution | 2024-06-18 | 2027-06-18 | 2
334662651-88889-DETAIL-07_16_2024-SVCWIND-1^06245007.0309402 | OTHER | CA-TIER-2 | Distribution | 2024-07-16 | 2027-07-16 | 2
147635651-62569-DETAIL-07_01_2024-GO95HV-1^06245007.0311700 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
147635651-62569-DETAIL-07_01_2024-GO95MLD-1^06245007.0311700 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
555423741-42569-DETAIL-07_01_2024-GO95MLD-1^06245007.0311701 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
262616421-12569-DETAIL-07_01_2024-GO95MLD-1^06245007.0312702 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
642330211-61569-DETAIL-07_01_2024-GO95MLD-1^06245007.0313801 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
642330211-61569-AUDIT-07_24_2024-GO95HV-1^06245007.0313801 | OTHER | CA-TIER-2 | Distribution | 2024-07-24 | 2029-07-24 | 3
270146401-31569-DETAIL-07_01_2024-GO95HV-1^06245007.0313802 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
931983290-26789-DETAIL-07_01_2024-GO95MLD-1^06245007.0313901 | OTHER | CA-TIER-2 | Distribution | 2024-07-01 | 2029-07-01 | 3
819809403-21059-DETAIL-06_19_2024-GO95HV-1^06245007.0336000 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
150067553-11059-DETAIL-06_19_2024-GO95HV-1^06245007.0336001 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
826523653-70059-DETAIL-06_19_2024-GO95MLD-1^06245007.0337000 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
466132083-99959-DETAIL-06_19_2024-GO95HV-1^06245007.0338000 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
466132083-99959-DETAIL-06_19_2024-GRDRODHI-1^06245007.0338000 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2027-06-19 | 2
304549569-49828-DETAIL-06_19_2024-GO95HV-1^06245007.0338100 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
304549569-49828-DETAIL-06_19_2024-GO95MLD-1^06245007.0338100 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2027-06-19 | 2
343905073-3169-DETAIL-06_18_2024-GO95MLD-1^06245007.0338900 | OTHER | CA-TIER-2 | Distribution | 2024-06-18 | 2027-06-18 | 2
220881899-67899-DETAIL-06_19_2024-GO95HV-1^06245007.0339001 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
220881899-67899-DETAIL-06_19_2024-GO95MLD-1^06245007.0339001 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
855809193-30059-DETAIL-06_19_2024-GO95MLD-1^06245007.0339100 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
855809193-30059-DETAIL-06_19_2024-POLETOP-1^06245007.0339100 | POLE | CA-TIER-2 | Distribution | 2024-06-19 | 2025-06-19 | 2
721607283-71059-DETAIL-06_18_2024-GO95HV-1^06245007.0339900 | OTHER | CA-TIER-2 | Distribution | 2024-06-18 | 2029-06-18 | 3
484617093-7069-DETAIL-06_19_2024-SVCWIND-1^06245007.0340900 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2027-06-19 | 2
15689554-39159-DETAIL-06_19_2024-GO95HV-1^06245007.0341000 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
15689554-39159-DETAIL-06_19_2024-GO95MLD-1^06245007.0341000 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2027-06-19 | 2
398055633-9159-DETAIL-06_19_2024-GO95HV-1^06245007.0341001 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
209853813-47079-DETAIL-06_11_2024-GO95MLD-1^06245007.0341700 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2029-06-11 | 3
547619723-71999-DETAIL-06_11_2024-SVCWIND-1^06245007.0341701 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
278483573-53169-DETAIL-06_19_2024-CONDCOIL-1^06245007.0341801 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2025-06-19 | 2
278483573-53169-DETAIL-06_19_2024-GO95BLTC-1^06245007.0341801 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
537830350-70350-ADMIN-06_19_2024-ABNDEQPM-1^06245007.0341802 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
723866043-43499-DETAIL-06_19_2024-GO95HV-1^06245007.0341900 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
723866043-43499-DETAIL-06_19_2024-SVCENTCO-1^06245007.0341900 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2027-06-19 | 2
793266123-46089-DETAIL-06_19_2024-GO95MLD-1^06245007.0342000 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
363979492-18159-DETAIL-06_19_2024-GO95MLD-1^06245007.0342102 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
650055723-38899-DETAIL-06_11_2024-GUYHINS-1^06245007.0342601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
465774803-50379-DETAIL-06_11_2024-GO95HV-1^06245007.0342603 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2029-06-11 | 3
465774803-50379-DETAIL-06_11_2024-GO95MLD-1^06245007.0342603 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
465774803-50379-DETAIL-06_11_2024-GO95TCH-1^06245007.0342603 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
185920703-87979-DETAIL-06_11_2024-CLRTOUCH-1^06245007.0343600 | CONDUCTOR | CA-TIER-2 | Distribution | 2024-06-11 | 2025-06-11 | 2
185920703-87979-DETAIL-06_11_2024-GO95HV-1^06245007.0343600 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2029-06-11 | 3
185920703-87979-DETAIL-06_11_2024-GO95MLD-1^06245007.0343600 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
276381735-11759-DETAIL-06_19_2024-GO95MLD-1^06245007.0343901 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
550108633-44259-DETAIL-06_11_2024-SVCDEFLC-1^06245007.0344100 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
981349543-69169-DETAIL-06_11_2024-GO95HV-1^06245007.0344540 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2029-06-11 | 3
552525458-45458-DETAIL-06_11_2024-GO95TCH-1^06245007.0344801 | OTHER | CA-NON-TIER | Distribution | 2024-06-11 | 2027-06-11 | 2
894245383-53259-DETAIL-06_10_2024-GO95MLD-1^06245007.0345001 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
773127393-43259-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0345003 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
479322483-92259-DETAIL-06_10_2024-GO95HV-1^06245007.0345004 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
479322483-92259-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0345004 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
67566603-93259-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0345100 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
803321823-64259-DETAIL-06_11_2024-SVCDEFLC-1^06245007.0345102 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
831688253-35689-DETAIL-06_11_2024-GUYLOINS-1^06245007.0345103 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
533580403-38079-DETAIL-06_11_2024-GRDRODHI-1^06245007.0345104 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
533580403-38079-DETAIL-06_11_2024-GRDRODHI-2^06245007.0345104 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
533580403-38079-DETAIL-06_11_2024-SVCDEFLC-1^06245007.0345104 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
580620223-94259-DETAIL-06_11_2024-SVCDEFLC-1^06245007.0345240 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
569491599-9579-DETAIL-06_11_2024-GO95BLTC-1^06245007.0345341 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2029-06-11 | 3
293798143-61179-DETAIL-06_11_2024-CLMBHAZ-1^06245007.0345500 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
293798143-61179-DETAIL-06_11_2024-GO95MLD-1^06245007.0345500 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
442898525-83059-DETAIL-06_11_2024-GO95HV-1^06245007.0345640 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2029-06-11 | 3
80556841-67841-DETAIL-06_11_2024-GO95HV-1^06245007.0345700 | OTHER | CA-NON-TIER | Distribution | 2024-06-11 | 2029-06-11 | 3
80556841-67841-DETAIL-06_11_2024-GO95MLD-1^06245007.0345700 | OTHER | CA-NON-TIER | Distribution | 2024-06-11 | 2029-06-11 | 3
910672595-25489-DETAIL-06_11_2024-GO95HV-1^06245007.0345701 | OTHER | CA-NON-TIER | Distribution | 2024-06-11 | 2029-06-11 | 3
463218185-99079-DETAIL-06_11_2024-GO95MLD-1^06245007.0345702 | OTHER | CA-NON-TIER | Distribution | 2024-06-11 | 2027-06-11 | 2
29073475-41289-DETAIL-06_11_2024-GO95HV-1^06245007.0345800 | OTHER | CA-NON-TIER | Distribution | 2024-06-11 | 2029-06-11 | 3
717049943-88089-DETAIL-06_10_2024-GO95MLD-1^06245007.0346003 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
870584673-73579-DETAIL-06_10_2024-GO95HV-1^06245007.0346005 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
870584673-73579-DETAIL-06_10_2024-GO95MLD-1^06245007.0346005 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
616008823-83779-DETAIL-06_10_2024-GO95MLD-1^06245007.0346007 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
622646624-42299-DETAIL-06_10_2024-CLRTOUCH-1^06245007.0346008 | CONDUCTOR | CA-TIER-2 | Distribution | 2024-06-10 | 2025-06-10 | 2
19771463-74099-DETAIL-06_11_2024-GO95MLD-1^06245007.0346400 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2029-06-11 | 3
227486073-70389-DETAIL-06_11_2024-GO95MLD-1^06245007.0346401 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
64002984-89-DETAIL-06_11_2024-GUYHINS-1^06245007.0346501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
928986915-27933-DETAIL-06_10_2024-ENCHRW-1^06245007.0346702 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
928986915-27933-DETAIL-06_10_2024-RISEGRD-1^06245007.0346702 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
740836885-85489-DETAIL-06_10_2024-RISEGRD-1^06245007.0346740 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
689324414-34889-DETAIL-06_10_2024-GO95HV-1^06245007.0347001 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
747697533-80259-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0347002 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
549067103-92589-DETAIL-06_10_2024-GO95MLD-1^06245007.0347004 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
281550453-97889-DETAIL-06_10_2024-GO95HV-1^06245007.0347006 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
728443155-7733-DETAIL-06_10_2024-GO95HV-1^06245007.0347640 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
728443155-7733-DETAIL-06_10_2024-SVCNEUT-1^06245007.0347640 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
718129664-13489-DETAIL-06_11_2024-GO95MLD-1^06245007.0347800 | OTHER | CA-TIER-2 | Distribution | 2024-06-11 | 2027-06-11 | 2
295008263-2589-DETAIL-06_10_2024-GO95MLD-1^06245007.0348000 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
931986373-60799-DETAIL-06_10_2024-GO95MLD-1^06245007.0348003 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
332003981-59869-DETAIL-06_10_2024-GO95HV-1^06245007.0349000 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
310845771-969-DETAIL-06_10_2024-GO95MLD-1^06245007.0349001 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
997390604-47789-DETAIL-06_10_2024-GO95MLD-1^06245007.0349004 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
86895993-99159-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0349005 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
210791331-96599-DETAIL-06_10_2024-GRDRODHI-1^06245007.0349006 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
210791331-96599-DETAIL-06_10_2024-SVCROAD-1^06245007.0349006 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
758325581-83669-DETAIL-06_10_2024-GO95HV-1^06245007.0349100 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
758325581-83669-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0349100 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
64695074-3059-DETAIL-06_10_2024-GO95HV-1^06245007.0349600 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
695136384-13499-DETAIL-06_10_2024-GO95HV-1^06245007.0349601 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
695136384-13499-DETAIL-06_10_2024-GO95MLD-1^06245007.0349601 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
695136384-13499-DETAIL-06_10_2024-GRDRODHI-1^06245007.0349601 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
695136384-13499-DETAIL-06_10_2024-GRDRODHI-2^06245007.0349601 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
215816024-72059-DETAIL-06_10_2024-GO95HV-1^06245007.0349602 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
91662835-32059-DETAIL-06_10_2024-GO95MLD-1^06245007.0349603 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2027-06-10 | 2
219952734-1089-DETAIL-06_10_2024-GO95HV-1^06245007.0349604 | OTHER | CA-TIER-2 | Distribution | 2024-06-10 | 2029-06-10 | 3
216334474-10999-ADMIN-06_19_2024-GO95HV-1^06245007.0357604 | OTHER | CA-TIER-2 | Distribution | 2024-06-19 | 2029-06-19 | 3
581185955-69499-DETAIL-08_07_2024-GO95MLD-1^06245008.0215600 | OTHER | CA-TIER-2 | Distribution | 2024-08-07 | 2029-08-07 | 3
581185955-69499-DETAIL-08_07_2024-GO95TCH-1^06245008.0215600 | OTHER | CA-TIER-2 | Distribution | 2024-08-07 | 2027-08-07 | 2
809422045-38479-DETAIL-08_07_2024-GO95MLD-1^06245008.0215701 | OTHER | CA-TIER-2 | Distribution | 2024-08-07 | 2029-08-07 | 3
699647625-67529-DETAIL-08_07_2024-GO95HV-1^06245008.0228400 | OTHER | CA-TIER-2 | Distribution | 2024-08-07 | 2029-08-07 | 3
766612065-71072-DETAIL-08_07_2024-XARMBRAC-1^06245008.0229102 | CROSSARM | CA-TIER-2 | Distribution | 2024-08-07 | 2025-08-07 | 2
139589885-65529-DETAIL-08_07_2024-GO95HV-1^06245008.0229200 | OTHER | CA-TIER-2 | Distribution | 2024-08-07 | 2029-08-07 | 3
139589885-65529-DETAIL-08_07_2024-INSULDMG-1^06245008.0229200 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-08-07 | 2025-08-07 | 2
3892105-95529-DETAIL-08_07_2024-GO95HV-1^06245008.0229301 | OTHER | CA-TIER-2 | Distribution | 2024-08-07 | 2029-08-07 | 3
843056735-37529-DETAIL-08_07_2024-SVCENTCO-1^06245008.0229402 | OTHER | CA-TIER-2 | Distribution | 2024-08-07 | 2027-08-07 | 2
738875915-74629-DETAIL-08_07_2024-INSULDMG-1^06245008.0229404 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-08-07 | 2025-08-07 | 2
592216310-57310-DETAIL-08_07_2024-ABNDEQPM-1^06245008.0229500 | OTHER | CA-TIER-2 | Distribution | 2024-08-07 | 2029-08-07 | 3
592216310-57310-DETAIL-08_07_2024-GUYLOINS-1^06245008.0229500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-08-07 | 2027-08-07 | 2
395674795-75629-DETAIL-08_21_2024-SVCROAD-1^06245008.0245100 | OTHER | CA-TIER-2 | Distribution | 2024-08-21 | 2027-08-21 | 2
204776836-55629-DETAIL-08_21_2024-GRDRODHI-1^06245008.0246100 | OTHER | CA-TIER-2 | Distribution | 2024-08-21 | 2027-08-21 | 2
204776836-55629-DETAIL-08_21_2024-GRDRODHI-2^06245008.0246100 | OTHER | CA-TIER-2 | Distribution | 2024-08-21 | 2027-08-21 | 2
987879526-45629-DETAIL-08_21_2024-GO95HV-1^06245008.0246101 | OTHER | CA-TIER-2 | Distribution | 2024-08-21 | 2029-08-21 | 3
70872675-25629-DETAIL-08_21_2024-GO95HV-1^06245008.0249103 | OTHER | CA-TIER-2 | Distribution | 2024-08-21 | 2029-08-21 | 3
525142196-16629-DETAIL-07_16_2024-GO95MLD-1^06245008.0260701 | OTHER | CA-TIER-2 | Distribution | 2024-07-16 | 2029-07-16 | 3
838147676-96629-DETAIL-08_07_2024-XARMSPCR-1^06245008.0279800 | CROSSARM | CA-TIER-2 | Distribution | 2024-08-07 | 2025-08-07 | 2
916130411-14599-DETAIL-10_06_2022-GO95MLD-1^06245010.0153000 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
174534501-70309-DETAIL-10_25_2022-GO95HV-1^06245010.0158000 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
184653341-58209-DETAIL-10_25_2022-GO95HV-1^06245010.0159100 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
252571638-45878-DETAIL-10_06_2022-GO95TCH-1^06245010.0213700 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
291691121-14879-DETAIL-10_06_2022-ABNDEQPM-1^06245010.0213701 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
783840671-99209-DETAIL-10_06_2022-GO95MLD-1^06245010.0213800 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
456414951-20309-DETAIL-10_06_2022-GO95MLD-1^06245010.0213900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
456414951-20309-DETAIL-10_06_2022-SVCWIND-1^06245010.0213900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
494984341-15299-DETAIL-10_06_2022-GO95HV-1^06245010.0218900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
494984341-15299-DETAIL-10_06_2022-GO95MLD-1^06245010.0218900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
494984341-15299-DETAIL-10_06_2022-GO95TCH-1^06245010.0218900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
506020961-18399-DETAIL-10_06_2022-GO95MLD-1^06245010.0220900 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
992363661-18209-DETAIL-10_06_2022-GO95HV-1^06245010.0220901 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
998391571-78579-DETAIL-10_06_2022-GO95HV-1^06245010.0220902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2027-10-06 | 3
998391571-78579-DETAIL-10_06_2022-GO95MLD-1^06245010.0220902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
998391571-78579-DETAIL-10_06_2022-GRDRODHI-1^06245010.0220902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
998391571-78579-DETAIL-10_06_2022-GRDRODHI-2^06245010.0220902 | OTHER | CA-TIER-2 | Distribution | 2022-10-06 | 2025-10-06 | 2
117562383-27309-DETAIL-10_19_2022-GO95MLD-1^06245010.0298801 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2025-10-19 | 2
650961043-20289-DETAIL-10_25_2022-ABNDEQPM-1^06245010.0317301 | OTHER | CA-TIER-2 | Distribution | 2022-10-25 | 2027-10-25 | 3
165125733-26309-DETAIL-10_25_2022-GUYNOINS-1^06245010.0322801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-25 | 2025-10-25 | 2
165125733-26309-DETAIL-10_25_2022-GUYNOINS-2^06245010.0322801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-25 | 2025-10-25 | 2
546524553-68983-DETAIL-08_20_2024-GO95HV-1^06246004.0185141 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
80710983-78679-DETAIL-08_20_2024-GO95HV-1^06246004.0185240 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
303219073-4483-DETAIL-08_20_2024-GO95HV-1^06246004.0185241 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
174520843-50289-DETAIL-08_15_2024-GO95MLD-1^06246004.0200900 | OTHER | FHCA | Distribution | 2024-08-15 | 2027-08-15 | 2
174520843-50289-DETAIL-08_15_2024-SVCDEFLC-1^06246004.0200900 | OTHER | FHCA | Distribution | 2024-08-15 | 2027-08-15 | 2
593931746-22659-DETAIL-08_14_2024-GO95MLD-1^06246004.0311200 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
448211775-99559-DETAIL-08_19_2024-POLETOP-1^06246004.0315400 | POLE | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
96905795-9559-DETAIL-08_19_2024-GO95HV-1^06246004.0317400 | OTHER | FHCA | Distribution | 2024-08-19 | 2029-08-19 | 3
935588076-82299-DETAIL-08_19_2024-GO95MLD-1^06246004.0321501 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
935588076-82299-AUDIT-09_03_2024-ABNDEQPM-1^06246004.0321501 | OTHER | FHCA | Distribution | 2024-09-03 | 2029-09-03 | 3
910328546-30289-DETAIL-08_19_2024-GO95MLD-1^06246004.0322700 | OTHER | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
733473706-91199-DETAIL-08_20_2024-GO95MLD-1^06246004.0325800 | OTHER | FHCA | Distribution | 2024-08-20 | 2027-08-20 | 2
733473706-91199-DETAIL-08_20_2024-GO95TCH-1^06246004.0325800 | OTHER | FHCA | Distribution | 2024-08-20 | 2027-08-20 | 2
872130416-35559-DETAIL-08_20_2024-GO95HV-1^06246004.0326801 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
816085936-94559-DETAIL-08_19_2024-GUYNOINS-1^06246004.0326900 | ANCHOR/GUY | FHCA | Distribution | 2024-08-19 | 2027-08-19 | 2
772194336-91699-DETAIL-08_19_2024-GO95MLD-1^06246004.0328800 | OTHER | FHCA | Distribution | 2024-08-19 | 2029-08-19 | 3
342681837-3938-DETAIL-04_03_2024-GO95HV-1^06246005.0030500 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
342681837-3938-DETAIL-04_03_2024-GO95MLD-1^06246005.0030500 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
575114919-10273-DETAIL-04_01_2024-GO95HV-1^06246005.0038901 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
308531929-54273-DETAIL-04_01_2024-GO95MLD-1^06246005.0039801 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
558941819-79243-DETAIL-03_26_2024-GO95MLD-1^06246005.0040602 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
558941819-79243-DETAIL-03_26_2024-GO95TCH-1^06246005.0040602 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
865358809-67589-ADMIN-04_02_2024-ABNDEQPM-1^06246005.0042501 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
603857339-89569-DETAIL-03_26_2024-GO95HV-1^06246005.0042700 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
483552068-11999-DETAIL-04_02_2024-GO95MLD-1^06246005.0043600 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
132008859-36659-DETAIL-03_28_2024-GO95HV-1^06246005.0043701 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
821605349-77659-DETAIL-03_28_2024-GO95HV-1^06246005.0043702 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
898358359-46659-DETAIL-03_28_2024-GO95HV-1^06246005.0044700 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
986821869-18279-DETAIL-03_28_2024-GO95MLD-1^06246005.0044701 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
582969169-66659-DETAIL-03_28_2024-GO95HV-1^06246005.0045700 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
689885579-14659-DETAIL-03_28_2024-GO95HV-1^06246005.0045701 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
162862909-7479-DETAIL-04_02_2024-GO95HV-1^06246005.0047801 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
162862909-7479-DETAIL-04_02_2024-GO95MLD-1^06246005.0047801 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
162862909-7479-DETAIL-04_02_2024-GRDRODHI-1^06246005.0047801 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
511290619-25659-DETAIL-04_02_2024-GO95MLD-1^06246005.0048901 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
129608238-90338-DETAIL-03_26_2024-SVCROAD-1^06246005.0050401 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
129608238-90338-DETAIL-03_26_2024-SVCROAD-2^06246005.0050401 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
61829080-81143-DETAIL-03_26_2024-SVCENTBK-1^06246005.0050500 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
860240199-17879-DETAIL-03_26_2024-GO95MLD-1^06246005.0051300 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
860240199-17879-DETAIL-03_26_2024-GRDRODHI-1^06246005.0051300 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
860240199-17879-DETAIL-03_26_2024-SVCWIND-1^06246005.0051300 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
870145359-75759-DETAIL-03_26_2024-GO95MLD-1^06246005.0052400 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
828376659-16759-DETAIL-03_26_2024-GO95HV-1^06246005.0052401 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
380593799-12769-DETAIL-03_26_2024-GO95MLD-1^06246005.0053300 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
364195069-4759-DETAIL-03_26_2024-GO95HV-1^06246005.0053400 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
851879889-4043-DETAIL-03_26_2024-GO95HV-1^06246005.0053401 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
851879889-4043-DETAIL-03_26_2024-GO95MLD-1^06246005.0053401 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
256950929-25759-DETAIL-03_26_2024-GO95MLD-1^06246005.0054501 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
386329049-42759-DETAIL-04_02_2024-GO95HV-1^06246005.0055300 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
466794099-43759-DETAIL-03_26_2024-GO95HV-1^06246005.0055500 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
183644749-25379-DETAIL-04_08_2024-GO95MLD-1^06246005.0056300 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
237854589-84759-DETAIL-03_26_2024-GO95MLD-1^06246005.0056500 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
513036299-64759-DETAIL-03_26_2024-GO95MLD-1^06246005.0056502 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
38332909-20759-DETAIL-03_26_2024-GO95MLD-1^06246005.0058601 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
38332909-20759-DETAIL-03_26_2024-GRDRODHI-1^06246005.0058601 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
162022219-10289-DETAIL-03_26_2024-GRDRODHI-1^06246005.0059601 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
162022219-10289-DETAIL-03_26_2024-GRDRODHI-2^06246005.0059601 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
971726590-52859-DETAIL-03_21_2024-GO95MLD-1^06246005.0060100 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
788736180-32559-DETAIL-03_21_2024-GO95MLD-1^06246005.0060200 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
20857160-15689-DETAIL-03_21_2024-GO95MLD-1^06246005.0060300 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
20857160-15689-DETAIL-03_21_2024-GRDRODHI-1^06246005.0060300 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
60707560-72559-DETAIL-03_21_2024-GO95MLD-1^06246005.0060301 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
770388560-13559-DETAIL-03_21_2024-GO95MLD-1^06246005.0060400 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
210310500-3743-DETAIL-03_21_2024-GO95MLD-1^06246005.0061200 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
163773880-53243-DETAIL-03_21_2024-GO95MLD-1^06246005.0061401 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
946712270-2859-DETAIL-03_21_2024-GO95MLD-1^06246005.0063400 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
849923960-71859-DETAIL-03_21_2024-GO95HV-1^06246005.0063401 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
165557250-16143-DETAIL-03_21_2024-GO95MLD-1^06246005.0063402 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
718255480-50789-DETAIL-03_21_2024-GO95MLD-1^06246005.0063500 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
540206200-47759-DETAIL-03_21_2024-GO95MLD-1^06246005.0066000 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
636515310-93499-DETAIL-03_21_2024-GO95MLD-1^06246005.0067000 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
622006350-61369-DETAIL-03_21_2024-GO95HV-1^06246005.0067100 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
68312250-81369-DETAIL-03_21_2024-GO95MLD-1^06246005.0067101 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
512248220-36759-DETAIL-03_21_2024-GO95HV-1^06246005.0067102 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
593029280-59759-DETAIL-03_27_2024-GO95HV-1^06246005.0069101 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
898937770-29759-DETAIL-03_27_2024-GO95HV-1^06246005.0069200 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
683387150-38759-DETAIL-03_27_2024-GO95HV-1^06246005.0069202 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
531090416-62416-DETAIL-04_08_2024-GO95HV-1^06246005.0071101 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
225451198-77859-DETAIL-04_08_2024-GRDRODHI-1^06246005.0071200 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
160757908-97859-DETAIL-04_08_2024-GO95HV-1^06246005.0072301 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
495093818-38859-DETAIL-04_08_2024-GO95MLD-1^06246005.0072400 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
770700608-46859-DETAIL-03_21_2024-GO95MLD-1^06246005.0073002 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
285964518-48859-DETAIL-04_04_2024-GO95MLD-1^06246005.0073402 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
294288658-94859-DETAIL-03_18_2024-GO95MLD-1^06246005.0074300 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
581877748-5859-DETAIL-04_03_2024-GO95HV-1^06246005.0074301 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
94077648-25859-DETAIL-04_03_2024-GO95HV-1^06246005.0074400 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
94077648-25859-DETAIL-04_03_2024-GO95MLD-1^06246005.0074400 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
740198504-70604-DETAIL-03_18_2024-GO95MLD-1^06246005.0076100 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
41622163-58279-DETAIL-03_18_2024-GO95MLD-1^06246005.0076101 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
495057918-2499-DETAIL-03_18_2024-GO95HV-1^06246005.0076200 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
495057918-2499-DETAIL-03_18_2024-GO95MLD-1^06246005.0076200 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
262101528-33379-DETAIL-04_08_2024-GO95HV-1^06246005.0076600 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
705924098-4859-DETAIL-03_18_2024-COPLLEAN-1^06246005.0077200 | POLE | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
303040208-3859-DETAIL-03_18_2024-GO95MLD-1^06246005.0079200 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
520201549-45549-DETAIL-03_18_2024-GO95MLD-1^06246005.0079300 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
686599204-4959-DETAIL-03_18_2024-GO95MLD-1^06246005.0081201 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
677198524-14959-DETAIL-03_18_2024-INSULDMG-1^06246005.0082201 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
855833034-21959-DETAIL-03_18_2024-GRDBROKE-1^06246005.0088001 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
142798613-27059-DETAIL-05_29_2024-GO95HV-1^06246005.0098101 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
181330823-599-ADMIN-05_29_2024-ABNDEQPM-1^06246005.0098200 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
181330823-599-DETAIL-05_29_2024-GO95MLD-1^06246005.0098200 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
213256213-56059-DETAIL-05_29_2024-GO95HV-1^06246005.0099000 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
88268203-46059-DETAIL-05_29_2024-GO95MLD-1^06246005.0099002 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
359003098-38838-DETAIL-08_15_2024-COPLLEAN-1^06246005.0125000 | POLE | FHCA | Distribution | 2024-08-15 | 2027-08-15 | 2
46739223-75743-DETAIL-08_15_2024-GO95HV-1^06246005.0125100 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
46739223-75743-DETAIL-08_15_2024-GO95MLD-1^06246005.0125100 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
772033154-63159-DETAIL-08_15_2024-GO95MLD-1^06246005.0130101 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
263896115-47535-DETAIL-08_15_2024-XARMSPCR-1^06246005.0134102 | CROSSARM | FHCA | Distribution | 2024-08-15 | 2027-08-15 | 2
263896115-47535-DETAIL-08_15_2024-XARMSPCR-2^06246005.0134102 | CROSSARM | FHCA | Distribution | 2024-08-15 | 2027-08-15 | 2
843137844-2379-DETAIL-08_15_2024-GO95MLD-1^06246005.0135101 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
58250664-87679-DETAIL-08_15_2024-GO95HV-1^06246005.0135102 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
466781204-59824-DETAIL-08_15_2024-GO95HV-1^06246005.0135300 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
997680079-55699-DETAIL-08_15_2024-GO95HV-1^06246005.0135900 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
209026170-17990-DETAIL-08_15_2024-GO95HV-1^06246005.0135901 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
920908134-21303-DETAIL-08_15_2024-GO95HV-1^06246005.0138041 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
872181114-48169-DETAIL-08_15_2024-GO95HV-1^06246005.0144100 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
707036044-75289-DETAIL-08_15_2024-GO95HV-1^06246005.0144101 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
707036044-75289-DETAIL-08_15_2024-GO95MLD-1^06246005.0144101 | OTHER | FHCA | Distribution | 2024-08-15 | 2027-08-15 | 2
949717274-31779-DETAIL-08_15_2024-GO95HV-1^06246005.0147200 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
949717274-31779-DETAIL-08_15_2024-GO95MLD-1^06246005.0147200 | OTHER | FHCA | Distribution | 2024-08-15 | 2027-08-15 | 2
360779864-84159-DETAIL-08_15_2024-GO95HV-1^06246005.0148101 | OTHER | FHCA | Distribution | 2024-08-15 | 2029-08-15 | 3
732066273-65803-DETAIL-05_30_2024-INSULDMG-1^06246005.0150000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-05-30 | 2027-05-30 | 2
529762043-24703-DETAIL-05_30_2024-GO95HV-1^06246005.0150100 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
347810173-39999-DETAIL-05_30_2024-GO95HV-1^06246005.0150101 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
667944603-75059-DETAIL-05_29_2024-GO95HV-1^06246005.0150800 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
924475863-6059-DETAIL-05_30_2024-GO95MLD-1^06246005.0150900 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2027-05-30 | 2
274459923-91103-DETAIL-05_30_2024-GO95HV-1^06246005.0169000 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
932343232-25959-DETAIL-05_29_2024-GO95HV-1^06246005.0178000 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
932343232-25959-DETAIL-05_29_2024-GO95MLD-1^06246005.0178000 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
985983183-45959-DETAIL-05_29_2024-GO95MLD-1^06246005.0178100 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
336169422-14299-DETAIL-05_29_2024-SVCENTCO-1^06246005.0178101 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2027-05-29 | 2
635514212-55959-DETAIL-05_29_2024-GO95HV-1^06246005.0178102 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
635514212-55959-DETAIL-05_29_2024-GO95MLD-1^06246005.0178102 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2027-05-29 | 2
591863983-36893-DETAIL-05_29_2024-GO95HV-1^06246005.0178201 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
591863983-36893-DETAIL-05_29_2024-GO95MLD-1^06246005.0178201 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
402252432-5959-DETAIL-05_29_2024-GO95MLD-1^06246005.0179000 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
402252432-5959-DETAIL-05_29_2024-GRDRODHI-1^06246005.0179000 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2027-05-29 | 2
251123192-74959-DETAIL-05_29_2024-GRDRODHI-1^06246005.0209900 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2027-05-29 | 2
623567493-51703-DETAIL-05_29_2024-GO95MLD-1^06246005.0210900 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
623567493-51703-DETAIL-05_29_2024-GRDRODHI-1^06246005.0210900 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2027-05-29 | 2
183643693-60159-DETAIL-06_04_2024-GO95HV-1^06246005.0212500 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
183643693-60159-DETAIL-06_04_2024-GO95MLD-1^06246005.0212500 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
337998833-20159-DETAIL-05_29_2024-GO95MLD-1^06246005.0213700 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
240511583-279-ADMIN-05_30_2024-ABNDEQPM-1^06246005.0219400 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
240511583-279-DETAIL-05_30_2024-GO95MLD-1^06246005.0219400 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2027-05-30 | 2
692952303-33059-DETAIL-05_29_2024-GO95HV-1^06246005.0219700 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
131915026-83909-DETAIL-05_29_2024-GO95HV-1^06246005.0219702 | OTHER | CA-NON-TIER | Distribution | 2024-05-29 | 2029-05-29 | 3
359621293-903-DETAIL-05_30_2024-GO95HV-1^06246005.0219800 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
542301073-31409-ADMIN-05_30_2024-ABNDEQPM-1^06246005.0219900 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
323590333-12059-DETAIL-05_30_2024-GO95HV-1^06246005.0220401 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
358064525-75525-DETAIL-05_30_2024-GO95MLD-1^06246005.0220600 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
994552463-50059-DETAIL-05_30_2024-GO95HV-1^06246005.0222100 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
377931193-5379-DETAIL-08_20_2024-GO95MLD-1^06246005.0243100 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
377931193-5379-DETAIL-08_20_2024-SVCDEFLC-1^06246005.0243100 | OTHER | FHCA | Distribution | 2024-08-20 | 2027-08-20 | 2
294531883-77479-DETAIL-08_20_2024-COPLLEAN-1^06246005.0244101 | POLE | FHCA | Distribution | 2024-08-20 | 2027-08-20 | 2
945098473-47479-DETAIL-08_20_2024-GO95HV-1^06246005.0245100 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
952795917-18755-DETAIL-08_14_2024-GO95MLD-1^06246005.0253742 | OTHER | FHCA | Distribution | 2024-08-14 | 2027-08-14 | 2
523183484-39679-DETAIL-08_14_2024-GO95HV-1^06246005.0254800 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
523183484-39679-DETAIL-08_14_2024-GO95MLD-1^06246005.0254800 | OTHER | FHCA | Distribution | 2024-08-14 | 2027-08-14 | 2
332138344-16899-DETAIL-08_14_2024-GO95MLD-1^06246005.0256800 | OTHER | FHCA | Distribution | 2024-08-14 | 2029-08-14 | 3
459397314-96159-DETAIL-08_21_2024-GO95MLD-1^06246005.0269541 | OTHER | FHCA | Distribution | 2024-08-21 | 2027-08-21 | 2
459397314-96159-DETAIL-08_21_2024-GRDRODHI-1^06246005.0269541 | OTHER | FHCA | Distribution | 2024-08-21 | 2027-08-21 | 2
459397314-96159-DETAIL-08_21_2024-GRDRODHI-2^06246005.0269541 | OTHER | FHCA | Distribution | 2024-08-21 | 2027-08-21 | 2
967932234-61479-DETAIL-08_21_2024-GO95MLD-1^06246005.0269741 | OTHER | FHCA | Distribution | 2024-08-21 | 2027-08-21 | 2
959754644-41779-DETAIL-08_21_2024-GO95MLD-1^06246005.0269840 | OTHER | FHCA | Distribution | 2024-08-21 | 2027-08-21 | 2
959754644-41779-DETAIL-08_21_2024-GRDRODHI-1^06246005.0269840 | OTHER | FHCA | Distribution | 2024-08-21 | 2027-08-21 | 2
976663968-34359-DETAIL-05_30_2024-GO95HV-1^06246005.0272800 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
833087429-56713-DETAIL-05_30_2024-GO95MLD-1^06246005.0272902 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
774847159-59159-DETAIL-05_30_2024-GO95HV-1^06246005.0273001 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
914849439-42359-DETAIL-05_30_2024-GO95MLD-1^06246005.0273100 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
444984389-54359-DETAIL-05_30_2024-GO95HV-1^06246005.0273600 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
374543195-6195-DETAIL-06_03_2024-GO95HV-1^06246005.0305000 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
775279478-22879-DETAIL-06_03_2024-CLMBHAZ-1^06246005.0305002 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2027-06-03 | 2
42356514-54759-DETAIL-06_04_2024-GO95BLTC-1^06246005.0310300 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
42356514-54759-DETAIL-06_04_2024-GO95MLD-1^06246005.0310300 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2027-06-04 | 2
383836604-94759-DETAIL-06_04_2024-GO95HV-1^06246005.0310401 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
383836604-94759-DETAIL-06_04_2024-INSULDMG-1^06246005.0310401 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-06-04 | 2027-06-04 | 2
600357898-49459-DETAIL-05_31_2024-GO95HV-1^06246005.0312500 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
486435188-87459-DETAIL-06_03_2024-GO95MLD-1^06246005.0313000 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2027-06-03 | 2
801841698-18459-DETAIL-06_03_2024-GUYHINS-1^06246005.0314101 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-06-03 | 2027-06-03 | 2
225703628-86459-DETAIL-06_03_2024-GO95MLD-1^06246005.0314301 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
3466738-16459-DETAIL-06_03_2024-GO95MLD-1^06246005.0314400 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
294341288-17479-DETAIL-06_03_2024-GO95HV-1^06246005.0314501 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
345809148-75459-DETAIL-06_03_2024-GO95HV-1^06246005.0315502 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
291814458-83459-DETAIL-06_03_2024-GO95MLD-1^06246005.0315701 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
277168568-24459-DETAIL-06_03_2024-GO95MLD-1^06246005.0315800 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
275649178-64459-DETAIL-06_03_2024-GO95MLD-1^06246005.0315900 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
407029498-38789-DETAIL-06_03_2024-GO95MLD-1^06246005.0317901 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
642632338-16599-DETAIL-06_04_2024-GO95MLD-1^06246005.0318701 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
742616408-52459-DETAIL-06_03_2024-GO95MLD-1^06246005.0319902 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
856889528-49359-DETAIL-05_31_2024-GO95MLD-1^06246005.0320502 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
474129808-59359-DETAIL-06_04_2024-GO95MLD-1^06246005.0320503 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
214129268-58359-DETAIL-05_31_2024-GO95MLD-1^06246005.0321501 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
208635068-97359-DETAIL-05_31_2024-GO95MLD-1^06246005.0322501 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
208635068-97359-AUDIT-07_17_2024-GRDRODHI-1^06246005.0322501 | OTHER | CA-NON-TIER | Distribution | 2024-07-17 | 2027-07-17 | 2
115402278-47359-DETAIL-05_31_2024-GO95MLD-1^06246005.0323501 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
358925288-83689-DETAIL-05_31_2024-GO95HV-1^06246005.0324400 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
351493088-56359-DETAIL-05_31_2024-GO95MLD-1^06246005.0325401 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
300275988-95359-DETAIL-05_31_2024-GO95MLD-1^06246005.0326401 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
429233698-75359-DETAIL-05_31_2024-GO95MLD-1^06246005.0327401 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
167688608-35359-DETAIL-05_31_2024-GO95MLD-1^06246005.0328401 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
967430708-94359-DETAIL-05_31_2024-GO95MLD-1^06246005.0329401 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
666033949-30359-DETAIL-05_31_2024-GO95MLD-1^06246005.0330400 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
317666859-7259-DETAIL-05_31_2024-GO95HV-1^06246005.0332400 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
481480959-11359-DETAIL-05_31_2024-GO95MLD-1^06246005.0332401 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
535573809-90613-DETAIL-05_31_2024-GO95HV-1^06246005.0333103 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
951845509-72289-DETAIL-05_31_2024-GO95MLD-1^06246005.0333201 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2027-05-31 | 2
225227709-93489-DETAIL-05_31_2024-GO95HV-1^06246005.0333300 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
938202599-98589-DETAIL-05_31_2024-GO95MLD-1^06246005.0333301 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2027-05-31 | 2
996016669-27259-DETAIL-05_31_2024-GO95HV-1^06246005.0333402 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
996016669-27259-DETAIL-05_31_2024-GO95MLD-1^06246005.0333402 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
927957519-58259-DETAIL-05_31_2024-GO95HV-1^06246005.0334400 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
927957519-58259-DETAIL-05_31_2024-GO95MLD-1^06246005.0334400 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2027-05-31 | 2
725804319-87259-DETAIL-05_31_2024-GUYNOINS-1^06246005.0334402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-31 | 2027-05-31 | 2
881307419-31359-DETAIL-05_31_2024-GO95HV-1^06246005.0334501 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
975084229-23199-DETAIL-05_31_2024-GO95MLD-1^06246005.0334800 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
928802369-49259-DETAIL-05_31_2024-GO95MLD-1^06246005.0336400 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2027-05-31 | 2
726858099-94259-DETAIL-06_04_2024-GO95MLD-1^06246005.0337101 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2027-06-04 | 2
591324389-24259-DETAIL-06_04_2024-GO95HV-1^06246005.0337202 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
628533259-34279-DETAIL-05_31_2024-GRDRODHI-1^06246005.0337404 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2027-05-31 | 2
628533259-34279-DETAIL-05_31_2024-GRDRODHI-2^06246005.0337404 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2027-05-31 | 2
622415749-12259-DETAIL-05_31_2024-GO95HV-1^06246005.0338400 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
622415749-12259-DETAIL-05_31_2024-GO95MLD-1^06246005.0338400 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2027-05-31 | 2
538393649-42259-DETAIL-05_31_2024-GO95HV-1^06246005.0338401 | OTHER | CA-NON-TIER | Distribution | 2024-05-31 | 2029-05-31 | 3
502760489-65389-AUDIT-07_01_2024-GO95MLD-1^06246005.0339300 | OTHER | CA-NON-TIER | Distribution | 2024-07-01 | 2027-07-01 | 2
12393639-91259-DETAIL-05_30_2024-GO95MLD-1^06246005.0339400 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2027-05-30 | 2
513237039-1259-DETAIL-05_30_2024-GO95MLD-1^06246005.0340403 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2027-05-30 | 2
907578119-259-DETAIL-05_30_2024-GO95HV-1^06246005.0341600 | OTHER | CA-NON-TIER | Distribution | 2024-05-30 | 2029-05-30 | 3
54637114-62779-DETAIL-08_20_2024-GO95HV-1^06246005.0366901 | OTHER | FHCA | Distribution | 2024-08-20 | 2029-08-20 | 3
93992050-96559-DETAIL-07_05_2023-POLEREPL-1^06246006.0011500 | POLE | CA-NON-TIER | Distribution | 2023-07-05 | 2026-07-05 | 2
45762611-76373-DETAIL-06_13_2023-POLEREPL-1^06246006.0013501 | POLE | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
678982400-45659-DETAIL-06_17_2024-GO95MLD-1^06246006.0131300 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
895855431-18579-DETAIL-06_17_2024-GO95HV-1^06246006.0131401 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
396325440-56440-DETAIL-06_17_2024-GO95HV-1^06246006.0131500 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
182813110-25659-DETAIL-06_17_2024-GO95HV-1^06246006.0132301 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
909607020-5659-DETAIL-06_17_2024-GO95MLD-1^06246006.0132400 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
909607020-5659-DETAIL-06_17_2024-GRDRODHI-1^06246006.0132400 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2027-06-17 | 2
833729130-84659-DETAIL-06_19_2024-GO95MLD-1^06246006.0133400 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
892315090-32423-DETAIL-06_19_2024-GO95MLD-1^06246006.0136800 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
270970770-59323-DETAIL-06_19_2024-GO95MLD-1^06246006.0136801 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
638744260-11713-DETAIL-06_19_2024-GO95MLD-1^06246006.0137701 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
113083671-78523-DETAIL-06_19_2024-GO95MLD-1^06246006.0138501 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
323020201-9423-DETAIL-06_19_2024-GO95MLD-1^06246006.0138900 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
570064611-60523-DETAIL-06_19_2024-GO95MLD-1^06246006.0139900 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
375840321-22523-DETAIL-06_19_2024-GO95HV-1^06246006.0139901 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
375840321-22523-DETAIL-06_19_2024-GO95MLD-1^06246006.0139901 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
191991731-23799-DETAIL-06_20_2024-SVCENTCO-1^06246006.0233000 | OTHER | CA-NON-TIER | Distribution | 2024-06-20 | 2027-06-20 | 2
804174961-95961-DETAIL-06_20_2024-GUYNOINS-1^06246006.0233001 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-06-20 | 2027-06-20 | 2
558161071-31171-DETAIL-06_17_2024-GO95MLD-1^06246006.0238600 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
276068771-27659-DETAIL-06_17_2024-GO95MLD-1^06246006.0239000 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
472216851-78659-DETAIL-06_17_2024-GO95HV-1^06246006.0239100 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
472216851-78659-DETAIL-06_17_2024-GO95MLD-1^06246006.0239100 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
395330571-60759-AUDIT-07_17_2024-GO95STUB-1^06246006.0239400 | OTHER | CA-NON-TIER | Distribution | 2024-07-17 | 2027-07-17 | 2
64842301-90759-DETAIL-06_17_2024-GO95MLD-1^06246006.0239501 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
950795141-63759-DETAIL-06_17_2024-GO95BLTC-1^06246006.0239900 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
950795141-63759-DETAIL-06_17_2024-GO95MLD-1^06246006.0239900 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
950795141-63759-DETAIL-06_17_2024-GUYHINS-1^06246006.0239900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-06-17 | 2027-06-17 | 2
701912671-86023-DETAIL-06_17_2024-GO95BLTC-1^06246006.0239901 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
701912671-86023-DETAIL-06_17_2024-GO95MLD-1^06246006.0239901 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
59970351-95389-DETAIL-06_17_2024-GO95MLD-1^06246006.0241101 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2027-06-17 | 2
609692421-63299-DETAIL-06_17_2024-GO95MLD-1^06246006.0241202 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2027-06-17 | 2
995362251-89399-DETAIL-06_17_2024-GO95MLD-1^06246006.0241600 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
965372371-25879-DETAIL-06_17_2024-GO95MLD-1^06246006.0242801 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
593574341-32889-ADMIN-06_17_2024-ABNDEQPM-1^06246006.0242900 | OTHER | CA-NON-TIER | Distribution | 2024-06-17 | 2029-06-17 | 3
877162284-29759-DETAIL-06_05_2024-GO95MLD-1^06246006.0251900 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
166452194-68759-DETAIL-06_05_2024-GO95MLD-1^06246006.0251902 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
730751464-27479-DETAIL-06_05_2024-ABNDEQPM-1^06246006.0256800 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
730751464-27479-DETAIL-06_05_2024-GO95MLD-1^06246006.0256800 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
481345154-26759-DETAIL-06_05_2024-GO95MLD-1^06246006.0257800 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
300226044-10599-DETAIL-06_05_2024-GO95MLD-1^06246006.0257801 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
405472470-76199-DETAIL-06_19_2024-GO95MLD-1^06246006.0263300 | OTHER | CA-NON-TIER | Distribution | 2024-06-19 | 2029-06-19 | 3
807107471-95589-DETAIL-06_06_2024-GO95MLD-1^06246006.0264000 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
840649539-12569-DETAIL-06_05_2024-GO95MLD-1^06246006.0264200 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
91726251-18169-DETAIL-06_05_2024-GO95MLD-1^06246006.0264800 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
91726251-18169-DETAIL-06_05_2024-GRDRODHI-1^06246006.0264800 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
145178571-20859-DETAIL-06_06_2024-GO95HV-1^06246006.0265000 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
145178571-20859-DETAIL-06_06_2024-GO95MLD-1^06246006.0265000 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
287041391-1859-DETAIL-06_06_2024-GO95MLD-1^06246006.0265201 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
176666080-21859-DETAIL-06_05_2024-GO95MLD-1^06246006.0265202 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
176666080-21859-DETAIL-06_05_2024-GUYLOINS-1^06246006.0265202 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
176666080-21859-DETAIL-06_05_2024-INSULDMG-1^06246006.0265202 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
586765671-60959-DETAIL-06_05_2024-GO95HV-1^06246006.0265600 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
71545691-71859-DETAIL-06_05_2024-GO95HV-1^06246006.0266200 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
316305611-33859-DETAIL-06_05_2024-GO95MLD-1^06246006.0266301 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
723271001-13859-DETAIL-06_05_2024-GO95MLD-1^06246006.0266302 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
723271001-13859-DETAIL-06_05_2024-GO95STUB-1^06246006.0266302 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
291152221-22079-DETAIL-06_05_2024-GO95MLD-1^06246006.0266400 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
521449401-62859-DETAIL-06_05_2024-GO95MLD-1^06246006.0267200 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
27105073-98438-DETAIL-06_05_2024-GO95MLD-1^06246006.0267201 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
666748501-79189-DETAIL-06_05_2024-GO95MLD-1^06246006.0267202 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
364048031-73859-DETAIL-06_05_2024-GO95HV-1^06246006.0267401 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
25261131-73979-DETAIL-06_05_2024-GO95MLD-1^06246006.0267503 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
11231041-68859-DETAIL-06_05_2024-GO95HV-1^06246006.0267600 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
11231041-68859-DETAIL-06_05_2024-GO95MLD-1^06246006.0267600 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
11231041-68859-DETAIL-06_05_2024-RISEGRD-1^06246006.0267600 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
413091351-19859-DETAIL-06_05_2024-GO95MLD-1^06246006.0268602 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
529057151-38859-DETAIL-06_05_2024-GO95BLTC-1^06246006.0269600 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2029-06-05 | 3
968442791-99859-DETAIL-06_05_2024-GO95STUB-1^06246006.0269901 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
174678033-85623-DTLSB-09_05_2024-GO95MLD-1^06246006.0314040 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
266064923-30623-DTLSB-09_05_2024-GO95MLD-1^06246006.0314041 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
291287763-77409-DTLSB-09_05_2024-GO95MLD-1^06246006.0314141 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
183190493-48409-DTLSB-09_05_2024-RISEGRD-1^06246006.0314240 | OTHER | CA-TIER-2 | Distribution | 2024-09-05 | 2027-09-05 | 2
657831831-71831-DETAIL-06_06_2024-GO95HV-1^06246006.0349300 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
713665373-63959-DETAIL-06_06_2024-GO95MLD-1^06246006.0350000 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
404673183-80789-DETAIL-06_06_2024-GO95MLD-1^06246006.0350102 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
109957634-13869-DETAIL-06_06_2024-ABNDEQPM-1^06246006.0350300 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
109957634-13869-DETAIL-06_06_2024-GO95MLD-1^06246006.0350300 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
329502013-73689-DETAIL-06_06_2024-GO95MLD-1^06246006.0351301 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
136222193-74959-DETAIL-06_06_2024-GO95MLD-1^06246006.0351303 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
914562013-94959-DETAIL-06_06_2024-GO95MLD-1^06246006.0351401 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
654249023-35959-DETAIL-06_06_2024-GO95MLD-1^06246006.0351500 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2029-06-06 | 3
491136923-55959-DETAIL-06_06_2024-GO95MLD-1^06246006.0352500 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
362789733-65959-AUDIT-08_06_2024-GO95MLD-1^06246006.0352604 | OTHER | CA-NON-TIER | Distribution | 2024-08-06 | 2029-08-06 | 3
373654043-95959-DETAIL-06_06_2024-GO95MLD-1^06246006.0352700 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
741838540-97758-DETAIL-06_06_2024-GO95MLD-1^06246006.0353702 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
741838540-97758-DETAIL-06_06_2024-GRDRODHI-1^06246006.0353702 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
661890663-7959-DETAIL-06_06_2024-GO95MLD-1^06246006.0353800 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
716191674-56333-DETAIL-06_06_2024-GO95MLD-1^06246006.0354900 | OTHER | CA-NON-TIER | Distribution | 2024-06-06 | 2027-06-06 | 2
32654989-30449-DETAIL-06_03_2024-GO95HV-1^06246006.0359000 | OTHER | CA-NON-TIER | Distribution | 2024-06-03 | 2029-06-03 | 3
729309296-899-DETAIL-06_04_2024-GO95MLD-1^06246006.0362002 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2027-06-04 | 2
729309296-899-AUDIT-07_17_2024-CONDFRAY-1^06246006.0362002 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-07-17 | 2027-07-17 | 2
133056299-54209-DETAIL-06_04_2024-GO95HV-1^06246006.0362100 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
755478326-90209-DETAIL-06_04_2024-GO95HV-1^06246006.0366001 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
33190526-29389-DETAIL-06_04_2024-CLRTOUCH-1^06246006.0366002 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-06-04 | 2027-06-04 | 2
33190526-29389-DETAIL-06_04_2024-GO95MLD-1^06246006.0366002 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2027-06-04 | 2
87788416-60899-DETAIL-06_04_2024-GO95HV-1^06246006.0367001 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
87788416-60899-DETAIL-06_04_2024-GO95MLD-1^06246006.0367001 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2027-06-04 | 2
981348634-55759-DETAIL-06_04_2024-GO95HV-1^06246006.0368100 | OTHER | CA-NON-TIER | Distribution | 2024-06-04 | 2029-06-04 | 3
805247108-31289-DETAIL-11_09_2022-GO95MLD-1^06246007.0063400 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
853433210-44269-DETAIL-11_07_2022-GO95TCH-1^06246008.0016300 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
940636816-75509-DETAIL-11_02_2022-GO95HV-1^06246008.0024401 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
211012830-17479-DETAIL-11_09_2022-SVCROAD-1^06246008.0026601 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
619578236-52499-DETAIL-11_09_2022-GO95MLD-1^06246008.0026603 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
619578236-52499-ADMIN-06_17_2024-XARMSPCR-1^06246008.0026603 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
699650500-40669-DETAIL-11_09_2022-GO95MLD-1^06246008.0027600 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
699650500-40669-DETAIL-11_09_2022-GO95MLD-2^06246008.0027600 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
222720730-42989-DETAIL-11_07_2022-GO95MLD-1^06246008.0028701 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
516463770-32509-DETAIL-11_07_2022-SVCENTBK-1^06246008.0028901 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
461471540-61799-DETAIL-11_08_2022-GO95HV-1^06246008.0041400 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
107766890-3869-DETAIL-11_09_2022-ABNDEQPM-1^06246008.0043200 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
107766890-3869-DETAIL-11_09_2022-GO95HV-1^06246008.0043200 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
854080680-70609-DETAIL-11_08_2022-GO95HV-1^06246008.0043300 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
552392870-38009-DETAIL-11_08_2022-GO95MLD-1^06246008.0043301 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
631141880-33499-DETAIL-11_10_2022-GO95MLD-1^06246008.0044301 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
129241780-2609-DETAIL-11_09_2022-ABNDEQPM-1^06246008.0045300 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
96464880-32609-DETAIL-11_09_2022-GO95MLD-1^06246008.0046200 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
868498800-68399-DETAIL-11_09_2022-GO95MLD-1^06246008.0046202 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
849522041-86709-DETAIL-11_02_2022-SVCENTCO-1^06246008.0050700 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
473398640-84899-DETAIL-11_02_2022-GO95MLD-1^06246008.0050702 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
473398640-84899-DETAIL-11_02_2022-GO95TCH-1^06246008.0050702 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
889288240-709-DETAIL-10_27_2022-GO95HV-1^06246008.0050704 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
413378011-6709-DETAIL-11_02_2022-GO95MLD-1^06246008.0051500 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
413378011-6709-DETAIL-11_02_2022-GO95TCH-1^06246008.0051500 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
19152801-29489-DETAIL-11_02_2022-GO95MLD-1^06246008.0051501 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
971877811-26709-DETAIL-11_02_2022-SVCENTCO-1^06246008.0051601 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
534002121-66709-DETAIL-11_02_2022-GO95MLD-1^06246008.0051603 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
534002121-66709-DETAIL-11_02_2022-GO95TCH-1^06246008.0051603 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
654443831-83079-ADMIN-06_17_2024-XARMSPCR-1^06246008.0051701 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
382695370-99-DETAIL-11_02_2022-GO95HV-1^06246008.0052601 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
382695370-99-DETAIL-11_02_2022-GO95MLD-1^06246008.0052601 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
783723731-45709-DETAIL-11_02_2022-GO95MLD-1^06246008.0053500 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2025-11-02 | 2
447779990-41709-DETAIL-11_02_2022-GO95HV-1^06246008.0054501 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
846467890-31709-DETAIL-11_02_2022-GO95HV-1^06246008.0054502 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
361260351-25709-DETAIL-11_08_2022-GO95TCH-1^06246008.0056400 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
989357771-44709-DETAIL-11_08_2022-GO95MLD-1^06246008.0057400 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
338857411-52709-DETAIL-11_08_2022-GO95MLD-1^06246008.0057501 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
338857411-52709-DETAIL-11_08_2022-GRDRODHI-1^06246008.0057501 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
775485121-46799-DETAIL-11_08_2022-GO95HV-1^06246008.0057502 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
775485121-46799-DETAIL-11_08_2022-GO95MLD-1^06246008.0057502 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
775485121-46799-ADMIN-06_17_2024-XARMSPCR-1^06246008.0057502 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
897346541-71099-DETAIL-11_10_2022-GO95HV-1^06246008.0058300 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
344180031-24709-DETAIL-11_07_2022-ABNDEQPM-1^06246008.0059400 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
216658201-96389-DETAIL-10_26_2022-GO95HV-1^06246008.0061101 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
216658201-96389-ADMIN-06_17_2024-XARMSPCR-1^06246008.0061101 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
184692811-31999-DETAIL-10_26_2022-ABNDEQPM-1^06246008.0062101 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
781613001-7809-DETAIL-10_26_2022-GO95HV-1^06246008.0062103 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
904443921-69709-ADMIN-06_17_2024-XARMSPCR-1^06246008.0062200 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
617154201-54809-DETAIL-11_10_2022-ABNDEQPM-1^06246008.0063001 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
564565971-18699-DETAIL-11_07_2022-ABNDEQPM-1^06246008.0063003 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
977177691-36809-DETAIL-10_26_2022-ABNDEQPM-1^06246008.0063101 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
950523361-13299-ADMIN-11_30_2023-POLEREPL-1^06246008.0063202 | POLE | CA-TIER-2 | Distribution | 2023-11-30 | 2024-11-30 | 2
756912531-97989-DETAIL-10_26_2022-GO95MLD-1^06246008.0063300 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
756912531-97989-DETAIL-10_26_2022-SVCENTBK-1^06246008.0063300 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
926123471-93809-ENHANCED-06_25_2024-IRSPOTOH-1^06246008.0065100 | OTHER | CA-TIER-2 | Distribution | 2024-06-25 | 2025-06-25 | 2
758472371-65999-DETAIL-10_27_2022-GO95TCH-1^06246008.0065101 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
758472371-65999-DETAIL-10_27_2022-SVCENTCO-1^06246008.0065101 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
630513901-21499-DETAIL-11_08_2022-GO95MLD-1^06246008.0066600 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
529724168-75168-ADMIN-06_17_2024-XARMSPCR-1^06246008.0066601 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
748220191-15279-DETAIL-11_08_2022-GO95MLD-1^06246008.0066700 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
167651161-62809-DETAIL-11_08_2022-GO95MLD-1^06246008.0067700 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
283299811-53089-DETAIL-10_27_2022-GO95HV-1^06246008.0067702 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
283299811-53089-DETAIL-10_27_2022-GO95MLD-1^06246008.0067702 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
492721431-97709-DETAIL-10_27_2022-GO95HV-1^06246008.0069800 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
694771131-18709-DETAIL-10_27_2022-GO95HV-1^06246008.0069801 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
143581960-45609-DETAIL-11_02_2022-GO95HV-1^06246008.0101800 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
482014120-87609-DETAIL-11_02_2022-GO95HV-1^06246008.0105701 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
393559920-8609-DETAIL-11_02_2022-GO95HV-1^06246008.0106700 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
585095830-68609-DETAIL-11_02_2022-GO95HV-1^06246008.0107700 | OTHER | CA-TIER-2 | Distribution | 2022-11-02 | 2027-11-02 | 3
588361350-79609-DETAIL-11_09_2022-GO95MLD-1^06246008.0108700 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
588361350-79609-DETAIL-11_09_2022-SVCWIND-1^06246008.0108700 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2025-11-09 | 2
957534818-42309-DETAIL-11_01_2022-GO95HV-1^06246009.0073100 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2027-11-01 | 3
774297318-24589-DETAIL-11_01_2022-GO95MLD-1^06246009.0076200 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
787848628-72189-DETAIL-10_18_2022-GO95HV-1^06246009.0078100 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
787848628-72189-DETAIL-10_18_2022-GO95MLD-1^06246009.0078100 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
737785158-24879-ENHANCED-07_05_2024-IRSPOTOH-1^06246009.0086302 | OTHER | CA-TIER-2 | Distribution | 2024-07-05 | 2025-07-05 | 2
368326158-94379-DETAIL-10_31_2022-GUYHINS-1^06246009.0091700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-31 | 2025-10-31 | 2
368326158-94379-DETAIL-10_31_2022-GUYHINS-2^06246009.0091700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-31 | 2025-10-31 | 2
658797162-60262-DETAIL-10_31_2022-GO95HV-1^06246009.0091702 | OTHER | CA-TIER-2 | Distribution | 2022-10-31 | 2027-10-31 | 3
958732578-35379-DETAIL-10_31_2022-GO95HV-1^06246009.0097500 | OTHER | CA-TIER-2 | Distribution | 2022-10-31 | 2027-10-31 | 3
340109625-70089-DETAIL-11_08_2022-GO95MLD-1^06246009.0099300 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
332644474-38379-DETAIL-11_08_2022-GO95TCH-1^06246009.0103400 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
232401405-75209-DETAIL-11_08_2022-ABNDEQPM-1^06246009.0104300 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2027-11-08 | 3
364826514-38699-DETAIL-11_08_2022-SVCROAD-1^06246009.0105300 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
909544838-42209-ADMIN-07_18_2024-GO95STUB-1^06246009.0105500 | OTHER | CA-TIER-2 | Distribution | 2024-07-18 | 2027-07-18 | 2
781907248-12209-DETAIL-11_03_2022-GO95HV-1^06246009.0105600 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
644289398-25869-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0109300 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
171511634-60299-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110200 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
920496848-67569-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110201 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
461516944-46069-DETAIL-11_03_2022-GO95HV-1^06246009.0110300 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
113276144-66069-DETAIL-11_03_2022-GO95HV-1^06246009.0110301 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
810909063-49379-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110500 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
802641353-29379-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110501 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
75094963-79379-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0110600 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
589020933-30909-DETAIL-11_03_2022-GO95HV-1^06246009.0111202 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
59408473-68379-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0111600 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
659045923-54779-DETAIL-11_03_2022-ABNDEQPM-1^06246009.0112100 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
934915793-71909-DETAIL-10_27_2022-GO95HV-1^06246009.0113000 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
688106583-51479-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0114600 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
163321293-67279-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0114700 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
635722793-97379-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0115700 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
793847304-43079-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0115701 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
513292314-32909-DETAIL-11_01_2022-SVCENTCO-1^06246009.0118200 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
277671913-84909-DETAIL-11_01_2022-GO95MLD-1^06246009.0120200 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
56559323-31799-ADMIN-11_30_2023-POLEREPL-1^06246009.0121102 | POLE | CA-TIER-2 | Distribution | 2023-11-30 | 2024-11-30 | 2
926603603-75909-DETAIL-11_01_2022-ABNDEQPM-1^06246009.0121201 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2027-11-01 | 3
787782013-49299-DETAIL-11_01_2022-GO95MLD-1^06246009.0121202 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
830326323-80009-DETAIL-10_26_2022-GO95HV-1^06246009.0124201 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
830326323-80009-ADMIN-06_17_2024-XARMSPCR-1^06246009.0124201 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
340456853-42009-DETAIL-10_26_2022-GO95HV-1^06246009.0125501 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
803909363-21009-DETAIL-10_26_2022-GO95HV-1^06246009.0126601 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
958552043-69989-DETAIL-10_26_2022-GO95MLD-1^06246009.0127702 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
595727273-72099-DETAIL-10_26_2022-GO95HV-1^06246009.0127703 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
723978073-56009-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128701 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
30438443-69799-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128702 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
976827393-45009-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128802 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2027-10-26 | 3
34489383-48599-DETAIL-10_26_2022-GO95MLD-1^06246009.0128806 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
130429903-52579-DETAIL-10_26_2022-GO95MLD-1^06246009.0129903 | OTHER | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
130429903-52579-ADMIN-07_18_2024-GO95STUB-1^06246009.0129903 | OTHER | CA-TIER-2 | Distribution | 2024-07-18 | 2027-07-18 | 2
646913703-64009-ADMIN-06_17_2024-XARMSPCR-1^06246009.0129904 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
437389803-47909-DETAIL-11_03_2022-GUYHINS-1^06246009.0130900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
917092589-24779-DETAIL-11_03_2022-GUYHINS-1^06246009.0130907 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
917092589-24779-DETAIL-11_03_2022-GUYHINS-2^06246009.0130907 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
766428879-46409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0131000 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
209176979-66409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0131001 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
132899163-23479-DETAIL-11_07_2022-GO95MLD-1^06246009.0131900 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
693707679-17409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0132100 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
602667589-57409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0132200 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
483411570-77509-DETAIL-11_01_2022-GO95CL10-1^06246009.0132700 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2027-11-01 | 3
483411570-77509-DETAIL-11_01_2022-GO95MLD-1^06246009.0132700 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
934993719-88389-DETAIL-10_20_2022-ABNDEQPM-1^06246009.0133200 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2027-10-20 | 3
337724219-21509-DETAIL-10_20_2022-ANCHIDLE-1^06246009.0133400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
594886559-85779-DETAIL-10_20_2022-GO95HV-1^06246009.0133401 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2027-10-20 | 3
870646109-41509-DETAIL-10_20_2022-ANCHIDLE-1^06246009.0133402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
734381080-47509-ADMIN-11_30_2023-POLEREPL-1^06246009.0133701 | POLE | CA-TIER-2 | Distribution | 2023-11-30 | 2024-11-30 | 2
720592670-20899-DETAIL-11_01_2022-GO95MLD-1^06246009.0133702 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2025-11-01 | 2
720592670-20899-ADMIN-06_17_2024-XARMSPCR-1^06246009.0133702 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
720592670-20899-ADMIN-07_17_2024-POLEREPL-1^06246009.0133702 | POLE | CA-TIER-2 | Distribution | 2024-07-17 | 2025-07-17 | 2
347817019-40079-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0134600 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
398365629-66509-DETAIL-10_20_2022-GO95MLD-1^06246009.0135402 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
340511519-27509-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0135600 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
188539549-3699-DETAIL-10_20_2022-GO95MLD-1^06246009.0136300 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
118179601-30701-DETAIL-10_20_2022-GO95MLD-1^06246009.0136400 | OTHER | CA-TIER-2 | Distribution | 2022-10-20 | 2025-10-20 | 2
756475459-36179-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0136600 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
298450023-30009-ADMIN-06_17_2024-XARMSPCR-1^06246009.0136900 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
810173260-76260-DETAIL-10_26_2022-GUYHINS-1^06246009.0136902 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-10-26 | 2025-10-26 | 2
683401280-73169-DETAIL-11_07_2022-ABNDEQPM-1^06246009.0138100 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
629105569-61489-DETAIL-11_07_2022-GO95MLD-1^06246009.0138101 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2025-11-07 | 2
723130269-72509-DETAIL-11_03_2022-GO95HV-1^06246009.0149900 | OTHER | CA-TIER-2 | Distribution | 2022-11-03 | 2027-11-03 | 3
723130269-72509-DETAIL-11_03_2022-GUYHINS-1^06246009.0149900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
723130269-72509-DETAIL-11_03_2022-GUYHINS-2^06246009.0149900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-11-03 | 2025-11-03 | 2
279785639-72499-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0236101 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
20499039-91279-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0237201 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
114362219-23409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0239500 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
434593019-32499-DETAIL-10_27_2022-GO95HV-1^06246009.0239501 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
434593019-32499-DETAIL-10_27_2022-GO95MLD-1^06246009.0239501 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
876067529-82699-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0241700 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
345396349-5409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0241802 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
442496309-16409-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0241900 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
547578809-39389-DETAIL-10_27_2022-GO95HV-1^06246009.0243500 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2027-10-27 | 3
547578809-39389-DETAIL-10_27_2022-GO95MLD-1^06246009.0243500 | OTHER | CA-TIER-2 | Distribution | 2022-10-27 | 2025-10-27 | 2
385097431-5709-DETAIL-10_05_2022-SVCWIND-1^06246010.0055200 | OTHER | CA-TIER-2 | Distribution | 2022-10-05 | 2025-10-05 | 2
947795033-35019-AUDIT-12_06_2022-GO95MLD-1^06246010.0130000 | OTHER | CA-TIER-2 | Distribution | 2022-12-06 | 2025-12-06 | 2
983396123-94019-DETAIL-10_18_2022-GO95MLD-1^06246010.0130002 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
588097681-97119-DETAIL-11_01_2022-GO95HV-1^06246010.0133800 | OTHER | CA-TIER-2 | Distribution | 2022-11-01 | 2027-11-01 | 3
118616248-56248-DETAIL-10_17_2022-GO95TCH-1^06246010.0143101 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
408199970-41099-DETAIL-10_17_2022-GO95CL10-1^06246010.0144102 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
256984821-30909-DETAIL-10_17_2022-GO95TCH-1^06246010.0154100 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
908605391-80909-DETAIL-11_08_2022-SVCENTCO-1^06246010.0154200 | OTHER | CA-TIER-2 | Distribution | 2022-11-08 | 2025-11-08 | 2
456794401-34909-DETAIL-10_04_2022-GO95MLD-1^06246010.0156301 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2025-10-04 | 2
436439281-16809-DETAIL-10_04_2022-ABNDEQPM-1^06246010.0169600 | OTHER | CA-TIER-2 | Distribution | 2022-10-04 | 2027-10-04 | 3
429259250-72809-DETAIL-10_18_2022-GO95HV-1^06246010.0215000 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
599492640-64679-DETAIL-10_17_2022-GO95MLD-1^06246010.0217000 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
580736710-94809-AUDIT-12_06_2022-GO95MLD-1^06246010.0217200 | OTHER | CA-TIER-2 | Distribution | 2022-12-06 | 2025-12-06 | 2
402513510-42289-DETAIL-10_17_2022-GO95HV-1^06246010.0217201 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
402513510-42289-DETAIL-10_17_2022-GO95MLD-1^06246010.0217201 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
402513510-42289-DETAIL-10_17_2022-GO95MLD-2^06246010.0217201 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
402513510-42289-DETAIL-10_17_2022-GO95TCH-1^06246010.0217201 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
328684240-21809-DETAIL-10_17_2022-GO95HV-1^06246010.0217203 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
150435430-90879-DETAIL-10_17_2022-GO95MLD-1^06246010.0217204 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
718578991-57669-DETAIL-10_17_2022-GO95HV-1^06246010.0218000 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2027-10-17 | 3
293954780-90809-DETAIL-10_17_2022-GO95MLD-1^06246010.0218300 | OTHER | CA-TIER-2 | Distribution | 2022-10-17 | 2025-10-17 | 2
984170191-55019-DETAIL-10_18_2022-GO95TCH-1^06246010.0240901 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
921696670-50099-DETAIL-10_18_2022-GO95BLTC-1^06246010.0241901 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
788195170-12999-DETAIL-10_18_2022-GO95BLTC-1^06246010.0241902 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
835968861-76219-DETAIL-10_18_2022-GO95HV-1^06246010.0283500 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
355149471-25219-DETAIL-10_18_2022-GO95HV-1^06246010.0284800 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
67148471-96219-DETAIL-10_18_2022-GO95HV-1^06246010.0284801 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
929771371-94219-DETAIL-10_18_2022-GO95HV-1^06246010.0284901 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2027-10-18 | 3
948544664-64909-DETAIL-10_19_2022-GO95HV-1^06246010.0329501 | OTHER | CA-TIER-2 | Distribution | 2022-10-19 | 2027-10-19 | 3
44697491-29219-DETAIL-10_18_2022-GO95MLD-1^06246010.0331900 | OTHER | CA-TIER-2 | Distribution | 2022-10-18 | 2025-10-18 | 2
201785008-95969-DTLSB-09_03_2020-ENCHRW-1^06246011.0366240 | OTHER | CA-TIER-2 | Distribution | 2020-09-03 | 2023-09-03 | 2
695039384-71432-ENHANCED-07_03_2024-IRSPOTOH-1^06246012.0133501 | OTHER | CA-TIER-2 | Distribution | 2024-07-03 | 2025-07-03 | 2
728701114-57922-ADMIN-06_27_2024-GUYSLACK-1^06246012.0143800 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-27 | 2025-06-27 | 2
379803015-28533-ADMIN-08_17_2022-POLEREPL-1^06247004.0076540 | POLE | CA-NON-TIER | Distribution | 2022-08-17 | 2025-08-17 | 2
376130549-69359-ADMIN-07_26_2022-POLEREPL-1^06247005.0057300 | POLE | CA-NON-TIER | Distribution | 2022-07-26 | 2025-07-26 | 2
751812150-99559-ADMIN-07_22_2022-POLEREPL-1^06247005.0205401 | POLE | CA-NON-TIER | Distribution | 2022-07-22 | 2025-07-22 | 2
382777939-2173-DETAIL-06_29_2023-POLEREPL-1^06247005.0209800 | POLE | CA-NON-TIER | Distribution | 2023-06-29 | 2026-06-29 | 2
663172973-3189-DETAIL-06_30_2023-POLEREPL-1^06247005.0214702 | POLE | CA-NON-TIER | Distribution | 2023-06-30 | 2026-06-30 | 2
260901058-56959-ADMIN-08_17_2022-POLEREPL-1^06247005.0266400 | POLE | CA-NON-TIER | Distribution | 2022-08-17 | 2025-08-17 | 2
525950083-71779-DETAIL-04_04_2024-SVCWIND-1^06247005.0280300 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
786834635-20969-DETAIL-04_03_2024-GO95MLD-1^06247005.0282801 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
450750228-42259-DETAIL-04_03_2024-GO95MLD-1^06247005.0283800 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
390711218-23599-DETAIL-04_03_2024-GO95MLD-1^06247005.0283900 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
692491658-22289-DETAIL-04_08_2024-GO95MLD-1^06247005.0285002 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
743909828-73179-ADMIN-04_04_2024-ABNDEQPM-1^06247005.0285100 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
743909828-73179-DETAIL-04_04_2024-GO95MLD-1^06247005.0285100 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
197815428-55499-DETAIL-04_04_2024-GO95HV-1^06247005.0285101 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
35825228-5159-DETAIL-04_08_2024-GO95MLD-1^06247005.0286100 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
307085998-64789-DETAIL-03_22_2024-GO95MLD-1^06247005.0286500 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2027-03-22 | 2
210285428-9059-DETAIL-03_22_2024-GO95MLD-1^06247005.0287101 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2027-03-22 | 2
269336908-3159-DETAIL-03_22_2024-GO95HV-1^06247005.0287301 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
269336908-3159-AUDIT-05_09_2024-GRDRODHI-1^06247005.0287301 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2027-05-09 | 2
30317738-62159-DETAIL-03_22_2024-SVCWIND-1^06247005.0287402 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2027-03-22 | 2
565696818-95799-DETAIL-03_22_2024-GO95MLD-1^06247005.0287403 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
773001908-10159-DETAIL-03_22_2024-GO95MLD-1^06247005.0289400 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
903099703-58459-DETAIL-04_04_2024-GO95MLD-1^06247005.0291001 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
290160663-9459-DETAIL-04_04_2024-GO95MLD-1^06247005.0292001 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
742401213-57279-DETAIL-04_04_2024-GO95MLD-1^06247005.0293200 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
273024913-35559-DETAIL-04_04_2024-GO95HV-1^06247005.0297200 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
745299133-95559-DETAIL-04_04_2024-GO95HV-1^06247005.0297300 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
917134013-63559-DETAIL-04_04_2024-GO95HV-1^06247005.0298200 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
636713553-84559-DETAIL-04_04_2024-GO95HV-1^06247005.0298401 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
153238270-59270-DETAIL-04_03_2024-GO95HV-1^06247005.0298700 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
647725733-36279-DETAIL-04_03_2024-GO95MLD-1^06247005.0298800 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
540974423-17559-DETAIL-04_03_2024-GO95HV-1^06247005.0298801 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
518988543-58559-DETAIL-04_03_2024-GO95MLD-1^06247005.0298902 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
153916893-10489-DETAIL-04_03_2024-GO95MLD-1^06247005.0298903 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
215964370-95370-DETAIL-04_03_2024-GO95HV-1^06247005.0299700 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
16617370-77370-DETAIL-04_03_2024-GO95HV-1^06247005.0299701 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
609298304-38189-ADMIN-07_07_2023-POLEREPL-1^06247005.0300502 | POLE | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
291257374-43659-ADMIN-07_07_2023-POLEREPL-1^06247005.0302500 | POLE | CA-NON-TIER | Distribution | 2023-07-07 | 2026-07-07 | 2
631375286-28959-DETAIL-03_27_2024-GO95MLD-1^06247005.0320700 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
709008796-38959-DETAIL-03_27_2024-GO95MLD-1^06247005.0320800 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
688851347-43959-DETAIL-04_08_2024-GO95HV-1^06247005.0321200 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
193663547-93959-DETAIL-04_08_2024-GO95HV-1^06247005.0321300 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
470259067-72959-DETAIL-04_08_2024-GO95BLTC-1^06247005.0322103 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
617480657-23959-DETAIL-04_08_2024-GO95HV-1^06247005.0322200 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
617480657-23959-DETAIL-04_08_2024-GO95MLD-1^06247005.0322200 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
197453756-55756-DETAIL-04_08_2024-GO95MLD-1^06247005.0322502 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
484652666-66959-DETAIL-03_27_2024-GO95HV-1^06247005.0322600 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
281961310-15269-DETAIL-04_08_2024-GO95HV-1^06247005.0323601 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
831078317-21859-DETAIL-03_27_2024-GO95MLD-1^06247005.0324301 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
487801246-36889-DETAIL-03_27_2024-GO95HV-1^06247005.0324500 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
344113746-13859-DETAIL-03_27_2024-GO95HV-1^06247005.0324501 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
344113746-13859-DETAIL-03_27_2024-GO95MLD-1^06247005.0324501 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2027-03-27 | 2
841592936-82859-DETAIL-03_27_2024-GO95HV-1^06247005.0324502 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
975337796-77859-DETAIL-03_28_2024-GO95MLD-1^06247005.0326501 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
653917916-9759-DETAIL-03_27_2024-GO95HV-1^06247005.0327201 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
576976196-54859-DETAIL-03_28_2024-GRDRODHI-1^06247005.0327500 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
40163476-35859-DETAIL-03_28_2024-GO95HV-1^06247005.0327602 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
250926936-47759-DETAIL-03_27_2024-GO95HV-1^06247005.0329100 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
250926936-47759-DETAIL-03_27_2024-GO95MLD-1^06247005.0329100 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
303087156-99663-DETAIL-03_28_2024-GO95MLD-1^06247005.0331500 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
940248246-78663-DETAIL-03_28_2024-GO95HV-1^06247005.0331502 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
940248246-78663-DETAIL-03_28_2024-GO95MLD-1^06247005.0331502 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
871527276-58563-DETAIL-03_28_2024-GO95MLD-1^06247005.0331503 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
993329426-70679-DETAIL-03_26_2024-GO95MLD-1^06247005.0332000 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
444413776-68259-DETAIL-03_28_2024-GO95MLD-1^06247005.0332900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
546055566-8259-DETAIL-03_28_2024-GO95MLD-1^06247005.0332902 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
251462206-20359-DETAIL-03_28_2024-GO95HV-1^06247005.0333700 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
273121196-53269-DETAIL-03_27_2024-GO95MLD-1^06247005.0336600 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
156541789-52789-AUDIT-04_30_2024-GO95MLD-1^06247005.0336602 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2029-04-30 | 3
649883146-38663-DETAIL-04_03_2024-GO95MLD-1^06247005.0336900 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
280962581-5188-DETAIL-03_27_2024-GO95MLD-1^06247005.0337601 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2027-03-27 | 2
280962581-5188-DETAIL-03_27_2024-GRDRODHI-1^06247005.0337601 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2027-03-27 | 2
653806995-29995-DETAIL-03_22_2024-GO95HV-1^06247005.0338300 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
653806995-29995-DETAIL-03_22_2024-INSULDMG-1^06247005.0338300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-22 | 2027-03-22 | 2
269102753-17798-DETAIL-03_22_2024-GO95MLD-1^06247005.0338400 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
269102753-17798-AUDIT-05_09_2024-GO95BLTC-1^06247005.0338400 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
654583095-5095-DETAIL-03_22_2024-GO95MLD-1^06247005.0338401 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
630453195-36195-DETAIL-03_22_2024-GO95HV-1^06247005.0338500 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
630453195-36195-DETAIL-03_22_2024-GO95MLD-1^06247005.0338500 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
195232366-51189-DETAIL-04_03_2024-GO95TCH-1^06247005.0338800 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
76024216-83259-DETAIL-04_02_2024-GO95MLD-1^06247005.0339000 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
850114906-17109-DETAIL-03_22_2024-GO95MLD-1^06247005.0339201 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
811881406-5259-DETAIL-03_22_2024-GO95MLD-1^06247005.0339202 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
811881406-5259-AUDIT-04_30_2024-GO95TCH-1^06247005.0339202 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
590655366-36359-DETAIL-03_22_2024-GRDRODHI-1^06247005.0339203 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2027-03-22 | 2
142007546-93979-DETAIL-04_03_2024-GO95MLD-1^06247005.0339700 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
155363247-13768-DETAIL-04_03_2024-GO95MLD-1^06247005.0339901 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
151692912-34912-DETAIL-04_02_2024-GO95MLD-1^06247005.0340001 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
397062812-15812-DETAIL-04_02_2024-GO95MLD-1^06247005.0340101 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
847063351-84351-DETAIL-03_22_2024-GO95HV-1^06247005.0340141 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2029-03-22 | 3
847063351-84351-DETAIL-03_22_2024-GO95MLD-1^06247005.0340141 | OTHER | CA-NON-TIER | Distribution | 2024-03-22 | 2027-03-22 | 2
717732226-56359-DETAIL-03_28_2024-GO95MLD-1^06247005.0340200 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
394063236-95359-DETAIL-03_28_2024-GO95MLD-1^06247005.0341202 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
586601846-11919-DETAIL-03_28_2024-GO95MLD-1^06247005.0341400 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
201182175-10063-DETAIL-03_28_2024-RISEBKSP-1^06247005.0341440 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
670026895-83599-ADMIN-04_01_2024-ABNDEQPM-1^06247005.0341800 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
670026895-83599-DETAIL-04_01_2024-GO95HV-1^06247005.0341800 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
670026895-83599-DETAIL-04_01_2024-GO95MLD-1^06247005.0341800 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
707535516-14459-DETAIL-04_01_2024-GO95MLD-1^06247005.0342500 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
944873315-53189-DETAIL-04_01_2024-GO95MLD-1^06247005.0342501 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
740874256-58359-DETAIL-04_01_2024-GO95HV-1^06247005.0342503 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
511171685-56459-DETAIL-04_01_2024-GO95HV-1^06247005.0342700 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
590217156-46899-DETAIL-04_02_2024-GO95MLD-1^06247005.0343300 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
109540225-39359-DETAIL-04_01_2024-GO95MLD-1^06247005.0344501 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
716923226-98089-DETAIL-04_01_2024-SVCWIND-1^06247005.0345100 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
906762845-12459-DETAIL-04_01_2024-GO95MLD-1^06247005.0346740 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
204526335-459-DETAIL-04_01_2024-COPLLEAN-1^06247005.0346741 | POLE | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
290263306-88899-DETAIL-04_03_2024-GO95MLD-1^06247005.0346801 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
288858885-70359-DETAIL-04_01_2024-GO95HV-1^06247005.0347102 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
357446655-81459-DETAIL-04_01_2024-GO95MLD-1^06247005.0348840 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
985275366-22959-DETAIL-04_02_2024-GO95MLD-1^06247005.0351800 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
538839548-41959-DETAIL-04_08_2024-GO95BLTC-1^06247005.0352400 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
481680938-21959-DETAIL-04_08_2024-GO95HV-1^06247005.0352401 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
247690238-70959-DETAIL-04_08_2024-GO95MLD-1^06247005.0352501 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
977235676-66479-AUDIT-04_30_2024-GRDRODHI-1^06247005.0352800 | OTHER | CA-NON-TIER | Distribution | 2024-04-30 | 2027-04-30 | 2
379228496-59859-DETAIL-04_02_2024-GO95MLD-1^06247005.0354800 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
428451926-33189-DETAIL-04_02_2024-GO95HV-1^06247005.0355800 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
428451926-33189-DETAIL-04_02_2024-GO95MLD-1^06247005.0355800 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
802939785-8309-ADMIN-08_09_2023-POLEREPL-2^06247006.0267300 | POLE | CA-NON-TIER | Distribution | 2023-08-09 | 2026-08-09 | 2
197418956-33309-ADMIN-08_09_2023-POLEREPL-2^06247006.0267403 | POLE | CA-NON-TIER | Distribution | 2023-08-09 | 2026-08-09 | 2
17659031-66368-ADMIN-08_09_2023-POLEREPL-2^06247006.0267501 | POLE | CA-NON-TIER | Distribution | 2023-08-09 | 2026-08-09 | 2
32899585-35309-ADMIN-08_09_2023-POLEREPL-2^06247006.0268302 | POLE | CA-NON-TIER | Distribution | 2023-08-09 | 2026-08-09 | 2
240098270-4370-DETAIL-06_13_2023-POLEREPL-2^06247006.0361602 | POLE | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
129585809-16809-DETAIL-06_13_2023-POLEREPL-1^06247006.0362101 | POLE | CA-NON-TIER | Distribution | 2023-06-13 | 2026-06-13 | 2
966177945-70319-DETAIL-10_24_2022-GO95HV-1^06247008.0191000 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
917960866-38319-DETAIL-10_24_2022-GO95HV-1^06247008.0301900 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
439864466-18319-DETAIL-10_24_2022-GO95HV-1^06247008.0301901 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
909973055-91319-DETAIL-10_24_2022-GO95HV-1^06247008.0303400 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
300352575-87319-DETAIL-10_24_2022-GO95HV-1^06247008.0304100 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
613192606-90379-DETAIL-10_24_2022-GO95HV-1^06247008.0314903 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
231779806-5319-DETAIL-10_24_2022-GO95MLD-1^06247008.0315200 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
339910316-2989-DETAIL-10_24_2022-GO95HV-1^06247008.0315201 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
339910316-2989-DETAIL-10_24_2022-GO95MLD-1^06247008.0315201 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
745608796-5889-DETAIL-10_24_2022-GO95HV-1^06247008.0315300 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
745608796-5889-DETAIL-10_24_2022-GO95MLD-1^06247008.0315300 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
658413705-43879-DETAIL-10_24_2022-GO95MLD-1^06247008.0315302 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
658413705-43879-DETAIL-10_24_2022-SVCENTCO-1^06247008.0315302 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
531814186-71319-DETAIL-10_24_2022-GO95HV-1^06247008.0315303 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
379474805-39379-DETAIL-10_24_2022-GO95MLD-1^06247008.0315305 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
958986135-83199-DETAIL-10_24_2022-GO95MLD-1^06247008.0315500 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
569934095-95319-DETAIL-10_24_2022-GO95HV-1^06247008.0316000 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
739075750-73979-DETAIL-11_07_2022-GO95HV-1^06247008.0361000 | OTHER | CA-TIER-2 | Distribution | 2022-11-07 | 2027-11-07 | 3
928899896-9979-DETAIL-10_24_2022-GO95MLD-1^06247009.0247500 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2025-10-24 | 2
640297076-99319-DETAIL-10_24_2022-GO95HV-1^06247009.0248300 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
58406226-70419-DETAIL-10_24_2022-GO95HV-1^06247009.0249301 | OTHER | CA-TIER-2 | Distribution | 2022-10-24 | 2027-10-24 | 3
787524490-77643-ADMIN-05_30_2024-XARMSPCR-1^06248003.0338940 | CROSSARM | CA-TIER-2 | Distribution | 2024-05-30 | 2025-05-30 | 2
825336645-16179-ADMIN-06_17_2024-XARMSPCR-1^06248004.0285100 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
549467885-559-ADMIN-06_17_2024-XARMSPCR-1^06248004.0287101 | CROSSARM | CA-TIER-2 | Distribution | 2024-06-17 | 2025-06-17 | 2
50997411-40823-ADMIN-07_24_2024-POLEREPL-1^06248004.0349341 | POLE | CA-TIER-2 | Distribution | 2024-07-24 | 2025-07-24 | 2
666638739-99473-ADMIN-04_27_2023-POLEREPL-1^06248007.0132001 | POLE | CA-NON-TIER | Distribution | 2023-04-27 | 2026-04-27 | 2
903589821-7273-ADMIN-04_27_2023-POLEREPL-1^06248007.0223102 | POLE | CA-NON-TIER | Distribution | 2023-04-27 | 2026-04-27 | 2
752516993-31093-ADMIN-04_27_2023-POLEREPL-1^06248007.0243301 | POLE | CA-NON-TIER | Distribution | 2023-04-27 | 2026-04-27 | 2
210173509-37473-ADMIN-04_26_2023-POLEREPL-1^06248007.0244900 | POLE | CA-NON-TIER | Distribution | 2023-04-26 | 2026-04-26 | 2
693629611-38299-DETAIL-07_11_2022-GUYHINS-1^07116007.0010500 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
735977388-48388-DETAIL-07_11_2022-GO95MLD-1^07116007.0010600 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
747930561-4419-DETAIL-07_11_2022-GO95MLD-1^07116007.0012500 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
814108803-89803-DETAIL-07_11_2022-GO95HV-1^07116007.0014500 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
276840281-54419-DETAIL-07_11_2022-GO95MLD-1^07116007.0014600 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
948611943-49479-DETAIL-07_11_2022-GO95MLD-1^07116007.0016200 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
905630983-87419-DETAIL-07_11_2022-GO95HV-1^07116007.0016401 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
743153391-30719-DETAIL-07_11_2022-ABNDEQPM-1^07116007.0016501 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
743153391-30719-DETAIL-07_11_2022-GO95HV-1^07116007.0016501 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
747513-49419-DETAIL-07_11_2022-GO95HV-1^07116007.0017101 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
786473203-60519-DETAIL-07_11_2022-GUYHINS-1^07116007.0017300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
786473203-60519-DETAIL-07_11_2022-GUYHINS-2^07116007.0017300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
617962303-19079-DETAIL-07_11_2022-GO95HV-1^07116007.0019302 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
617962303-19079-DETAIL-07_11_2022-GO95MLD-1^07116007.0019302 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
617962303-19079-DETAIL-07_11_2022-GRDRODHI-1^07116007.0019302 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
681656632-50409-DETAIL-07_11_2022-GO95TCH-1^07116007.0019403 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
292254033-26419-DETAIL-07_11_2022-GO95MLD-1^07116007.0019500 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
169680468-21099-DETAIL-06_20_2022-GO95MLD-1^07116007.0020101 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
263709373-52819-DETAIL-06_20_2022-GO95MLD-1^07116007.0020102 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
217125168-8689-DETAIL-06_20_2022-GO95TCH-1^07116007.0020200 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
181876578-96699-DETAIL-06_20_2022-GO95MLD-1^07116007.0020201 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
181876578-96699-DETAIL-06_20_2022-SVCRUBLG-1^07116007.0020201 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
781707404-2719-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0020400 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
302773324-51719-DETAIL-06_21_2022-GO95MLD-1^07116007.0020502 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
468023294-80719-DETAIL-06_21_2022-GO95MLD-1^07116007.0020601 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
426786058-86799-DETAIL-06_20_2022-GO95BLTC-1^07116007.0021002 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2027-06-20 | 3
426786058-86799-DETAIL-06_20_2022-GUYHINS-1^07116007.0021002 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
747283408-23819-DETAIL-06_15_2022-GUYHINS-1^07116007.0021007 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
747283408-23819-DETAIL-06_15_2022-GUYHINS-2^07116007.0021007 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
730905588-98499-DETAIL-06_20_2022-GUYHINS-1^07116007.0021100 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
992360487-62819-DETAIL-06_20_2022-GO95MLD-1^07116007.0021101 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2027-06-20 | 3
85272843-90819-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0021405 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
80119334-72719-DETAIL-06_21_2022-GO95TCH-1^07116007.0021501 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
492984804-18730-DETAIL-06_21_2022-GO95MLD-1^07116007.0021601 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
96524324-5719-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0021602 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
725767477-9289-DETAIL-06_15_2022-GUYHINS-1^07116007.0022003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
16975018-36819-DETAIL-06_20_2022-GO95MLD-1^07116007.0022200 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
858708953-56819-DETAIL-06_21_2022-GO95MLD-1^07116007.0022301 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
860782353-20819-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0022401 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
316487373-819-DETAIL-06_21_2022-GO95MLD-1^07116007.0022402 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
252549924-54719-DETAIL-06_21_2022-ENCHRW-1^07116007.0022500 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
252549924-54719-DETAIL-06_21_2022-GO95MLD-1^07116007.0022500 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
656107514-14719-DETAIL-06_21_2022-RISEBKSP-1^07116007.0022504 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
176118604-76730-DETAIL-06_21_2022-GO95MLD-1^07116007.0022505 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2025-06-21 | 2
230018423-33789-DETAIL-06_20_2022-GUYHINS-1^07116007.0023003 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
315315193-39819-DETAIL-06_20_2022-GO95MLD-1^07116007.0023102 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
394785203-47819-DETAIL-06_21_2022-GO95HV-1^07116007.0023303 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
209680538-86819-DETAIL-06_21_2022-GO95HV-1^07116007.0023401 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
782756214-36719-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0023601 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
250192598-31089-DETAIL-06_13_2022-GO95MLD-1^07116007.0024100 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
250192598-31089-DETAIL-06_13_2022-GUYHINS-1^07116007.0024100 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
397364924-58719-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0024900 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
887430243-89519-DETAIL-06_13_2022-GUYNOINS-1^07116007.0025002 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
406221113-22089-DETAIL-06_13_2022-GUYHINS-1^07116007.0025005 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
586832694-67519-DETAIL-06_15_2022-GO95HV-1^07116007.0026300 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
267401193-73320-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0026900 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
162458693-69220-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0026901 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
702199403-97379-DETAIL-06_15_2022-GO95BLTC-1^07116007.0027401 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
702199403-97379-DETAIL-06_15_2022-GO95MLD-1^07116007.0027401 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
702199403-97379-DETAIL-06_15_2022-GRDRODHI-1^07116007.0027401 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
990329933-7519-DETAIL-06_15_2022-GO95MLD-1^07116007.0028300 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
761022953-51519-DETAIL-06_15_2022-GO95MLD-1^07116007.0028401 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
356862443-31189-DETAIL-06_13_2022-GO95MLD-1^07116007.0028404 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
852044973-54499-DETAIL-06_15_2022-GO95HV-1^07116007.0028500 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
898433773-6779-DETAIL-06_13_2022-GO95MLD-1^07116007.0029000 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
531381153-79079-DETAIL-06_13_2022-GO95HV-1^07116007.0029002 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
395061543-72499-DETAIL-06_13_2022-GO95MLD-1^07116007.0029101 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
395061543-72499-DETAIL-06_13_2022-GRDRODHI-1^07116007.0029101 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
368253713-19689-DETAIL-06_13_2022-GO95TCH-1^07116007.0029400 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
368253713-19689-DETAIL-06_13_2022-GUYHINS-1^07116007.0029400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
113302233-26519-DETAIL-06_13_2022-GO95MLD-1^07116007.0029401 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
632155043-71519-DETAIL-06_22_2022-GO95MLD-1^07116007.0029502 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
206892463-58179-DETAIL-06_15_2022-GO95BLTC-1^07116007.0029503 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
206892463-58179-DETAIL-06_15_2022-GO95MLD-1^07116007.0029503 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
736714748-20989-DETAIL-06_20_2022-GUYHINS-1^07116007.0038400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
736714748-20989-DETAIL-06_20_2022-GUYHINS-2^07116007.0038400 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
59181148-14679-DETAIL-06_20_2022-GO95MLD-1^07116007.0038401 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
59181148-14679-DETAIL-06_20_2022-GUYHINS-1^07116007.0038401 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
25172008-9689-DETAIL-06_20_2022-GUYHINS-1^07116007.0039101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
553606328-6179-DETAIL-06_20_2022-GUYHINS-1^07116007.0039204 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
553606328-6179-DETAIL-06_20_2022-GUYHINS-2^07116007.0039204 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
454772428-74599-DETAIL-06_20_2022-GO95MLD-1^07116007.0039205 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
416936208-34219-DETAIL-06_21_2022-ABNDEQPM-1^07116007.0039800 | OTHER | CA-TIER-2 | Distribution | 2022-06-21 | 2027-06-21 | 3
149129987-72099-DETAIL-06_23_2022-ABNDEQPM-1^07116007.0102100 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
149129987-72099-DETAIL-06_23_2022-GO95HV-1^07116007.0102100 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
149129987-72099-DETAIL-06_23_2022-GO95MLD-1^07116007.0102100 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2025-06-23 | 2
229797067-78219-DETAIL-06_23_2022-GO95HV-1^07116007.0103000 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
660777447-48219-DETAIL-06_23_2022-GO95HV-1^07116007.0103001 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
461510757-19219-DETAIL-06_23_2022-ABNDEQPM-1^07116007.0103101 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
664376557-90270-DETAIL-06_23_2022-GO95HV-1^07116007.0103103 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
7974427-34899-DETAIL-06_22_2022-ABNDEQPM-1^07116007.0103200 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
277117017-87209-DETAIL-06_23_2022-ABNDEQPM-1^07116007.0103201 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
565477327-30319-DETAIL-06_23_2022-GO95MLD-1^07116007.0103300 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2025-06-23 | 2
128294337-99219-DETAIL-06_22_2022-GO95HV-1^07116007.0104201 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
669960737-699-DETAIL-06_22_2022-GO95MLD-1^07116007.0104400 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
932695758-97379-DETAIL-06_22_2022-GO95BLTC-1^07116007.0105102 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
64606358-5319-DETAIL-06_22_2022-GO95HV-1^07116007.0105103 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
387448088-84319-DETAIL-06_22_2022-GO95MLD-1^07116007.0106200 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
267108077-93799-DETAIL-06_22_2022-ABNDEQPM-1^07116007.0108201 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2027-06-22 | 3
800249238-71370-DETAIL-06_22_2022-SVCROAD-1^07116007.0108240 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
998928287-82319-DETAIL-07_06_2022-GO95MLD-1^07116007.0108305 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
659729987-91099-DETAIL-07_06_2022-GO95TCH-1^07116007.0108306 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
875748978-14319-DETAIL-06_28_2022-GO95MLD-1^07116007.0109208 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
605535967-48319-DETAIL-06_28_2022-GO95MLD-1^07116007.0109209 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
53949207-1219-DETAIL-06_28_2022-GO95MLD-1^07116007.0110201 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
630371367-22200-DETAIL-06_22_2022-SVCROAD-1^07116007.0110203 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
500489526-61088-DETAIL-06_22_2022-SVCROAD-1^07116007.0110304 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
115031427-87119-DETAIL-06_28_2022-SVCROAD-1^07116007.0110305 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
699717637-17119-DETAIL-06_28_2022-GO95MLD-1^07116007.0110306 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
627005426-66368-DETAIL-06_22_2022-GO95MLD-1^07116007.0110308 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
645966678-73119-DETAIL-06_28_2022-GO95MLD-1^07116007.0110400 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
995467827-86199-DETAIL-06_28_2022-GO95MLD-1^07116007.0110402 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
995467827-86199-DETAIL-06_28_2022-GUYHINS-1^07116007.0110402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
499016747-58119-DETAIL-06_22_2022-GUYHINS-1^07116007.0110403 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
382319037-19119-DETAIL-06_22_2022-GO95MLD-1^07116007.0111300 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
656517867-10589-DETAIL-06_22_2022-GO95MLD-1^07116007.0111302 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
656517867-10589-DETAIL-06_22_2022-GO95TCH-1^07116007.0111302 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
595720357-12099-DETAIL-06_22_2022-GO95MLD-1^07116007.0111305 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
296703777-59119-DETAIL-06_22_2022-GO95MLD-1^07116007.0111401 | OTHER | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
296703777-59119-DETAIL-06_22_2022-GUYHINS-1^07116007.0111401 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
949521709-71699-DETAIL-06_22_2022-GUYHINS-1^07116007.0111406 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-22 | 2025-06-22 | 2
998635078-67019-DETAIL-06_28_2022-GO95MLD-1^07116007.0111507 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
490818864-42379-DETAIL-06_20_2022-GUYHINS-1^07116007.0111801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
415193608-46919-DETAIL-06_20_2022-SVCENTCO-1^07116007.0111901 | OTHER | CA-TIER-2 | Distribution | 2022-06-20 | 2025-06-20 | 2
673623758-65499-DETAIL-06_15_2022-GUYHINS-1^07116007.0111905 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
441936257-22879-DETAIL-06_14_2022-GO95MLD-1^07116007.0112300 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
606146598-96019-DETAIL-06_15_2022-GO95MLD-1^07116007.0112506 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
284005148-47479-DETAIL-06_15_2022-GO95MLD-1^07116007.0112507 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
432394158-78979-DETAIL-06_15_2022-GO95BLTC-1^07116007.0112705 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2027-06-15 | 3
432394158-78979-DETAIL-06_15_2022-GUYHINS-1^07116007.0112705 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
897653919-16389-DETAIL-06_15_2022-GO95MLD-1^07116007.0112804 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
862266899-10019-DETAIL-06_15_2022-GUYHINS-1^07116007.0112805 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
862266899-10019-DETAIL-06_15_2022-GUYHINS-2^07116007.0112805 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
208108758-33099-DETAIL-06_15_2022-GO95MLD-1^07116007.0112807 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
521868119-64689-DETAIL-06_15_2022-GO95MLD-1^07116007.0112808 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
913757288-13799-DETAIL-06_15_2022-GO95TCH-1^07116007.0112903 | OTHER | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
913757288-13799-DETAIL-06_15_2022-GUYHINS-1^07116007.0112903 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-15 | 2025-06-15 | 2
48132797-42219-DETAIL-06_14_2022-SVCROAD-1^07116007.0113301 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
454363627-34199-DETAIL-06_14_2022-GUYHINS-1^07116007.0113402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
624655976-43686-DETAIL-06_14_2022-GO95TCH-1^07116007.0113421 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
233390089-43119-DETAIL-06_16_2022-GO95MLD-1^07116007.0113512 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
233390089-43119-DETAIL-06_16_2022-SVCROAD-1^07116007.0113512 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
233390089-43119-DETAIL-06_16_2022-SVCROAD-2^07116007.0113512 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
783342029-20119-DETAIL-06_16_2022-SVCROAD-1^07116007.0113603 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
790234399-74019-DETAIL-06_14_2022-GO95MLD-1^07116007.0113609 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
844394659-34019-DETAIL-06_14_2022-GO95TCH-1^07116007.0113702 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
844394659-34019-DETAIL-06_14_2022-SVCWIND-1^07116007.0113702 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
593305869-72119-DETAIL-06_13_2022-SVCROAD-1^07116007.0114508 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
266705109-119-DETAIL-06_16_2022-SVCWIND-1^07116007.0114600 | OTHER | CA-TIER-2 | Distribution | 2022-06-16 | 2025-06-16 | 2
79657038-64489-DETAIL-06_13_2022-GUYHINS-1^07116007.0114812 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-13 | 2025-06-13 | 2
261897548-5919-DETAIL-06_08_2022-GO95MLD-1^07116007.0114902 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
660111161-47699-DETAIL-06_14_2022-ABNDEQPM-1^07116007.0115300 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2027-06-14 | 3
660111161-47699-DETAIL-06_14_2022-GO95MLD-1^07116007.0115300 | OTHER | CA-TIER-2 | Distribution | 2022-06-14 | 2025-06-14 | 2
733121484-94619-DETAIL-06_08_2022-GUYNOINS-1^07116007.0115707 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
101114404-62619-DETAIL-06_08_2022-GO95MLD-1^07116007.0115802 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
10776604-14619-DETAIL-06_08_2022-GO95MLD-1^07116007.0115806 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
10776604-14619-DETAIL-06_08_2022-GUYHINS-1^07116007.0115806 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
620923184-99789-DETAIL-06_08_2022-GUYHINS-1^07116007.0116701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
620923184-99789-DETAIL-06_08_2022-SVCROAD-1^07116007.0116701 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
620923184-99789-DETAIL-06_08_2022-SVCROAD-2^07116007.0116701 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
615856614-82619-DETAIL-06_08_2022-GO95TCH-1^07116007.0116802 | OTHER | CA-TIER-2 | Distribution | 2022-06-08 | 2025-06-08 | 2
974641734-8199-DETAIL-06_13_2022-ABNDEQPM-1^07116007.0116900 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
848991734-33499-DETAIL-06_13_2022-ABNDEQPM-1^07116007.0117900 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
905672634-36619-DETAIL-06_13_2022-ABNDEQPM-1^07116007.0117901 | OTHER | CA-TIER-2 | Distribution | 2022-06-13 | 2027-06-13 | 3
637237221-4899-DETAIL-07_06_2022-GO95MLD-1^07116007.0140400 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
637237221-4899-DETAIL-07_06_2022-GRDRODHI-1^07116007.0140400 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
228459229-90619-DETAIL-07_06_2022-GO95HV-1^07116007.0140501 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
126760959-41619-DETAIL-07_06_2022-GO95HV-1^07116007.0141400 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
443134139-29399-DETAIL-07_06_2022-GO95MLD-1^07116007.0141402 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
496455339-97199-DETAIL-07_06_2022-GO95MLD-1^07116007.0141602 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
150237179-32619-DETAIL-07_06_2022-ENCHRW-1^07116007.0142300 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
715984949-42619-DETAIL-07_06_2022-GO95MLD-1^07116007.0142302 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
715984949-42619-DETAIL-07_06_2022-GRDRODHI-1^07116007.0142302 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
992098969-12619-DETAIL-07_06_2022-GO95TCH-1^07116007.0142402 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
108045679-51619-DETAIL-07_06_2022-GO95MLD-1^07116007.0142403 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
108045679-51619-DETAIL-07_06_2022-GO95TCH-1^07116007.0142403 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
565238208-92889-DETAIL-06_23_2022-GO95MLD-1^07116007.0152401 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2025-06-23 | 2
975451008-84419-DETAIL-06_23_2022-GO95HV-1^07116007.0152503 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
842035118-48089-DETAIL-06_23_2022-ABNDEQPM-1^07116007.0153500 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2027-06-23 | 3
776728461-39208-DETAIL-06_23_2022-GO95MLD-1^07116007.0153700 | OTHER | CA-TIER-2 | Distribution | 2022-06-23 | 2025-06-23 | 2
236226708-81589-DETAIL-06_28_2022-GO95MLD-1^07116007.0155400 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
339808198-73789-DETAIL-06_28_2022-GO95MLD-1^07116007.0155402 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
160101878-82789-DETAIL-06_28_2022-GO95MLD-1^07116007.0155404 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
473440088-71419-DETAIL-06_28_2022-GUYHINS-1^07116007.0155405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
473440088-71419-DETAIL-06_28_2022-GUYHINS-2^07116007.0155405 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
917956228-30489-DETAIL-06_28_2022-GO95MLD-1^07116007.0155406 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
331919428-91419-DETAIL-06_28_2022-GO95TCH-1^07116007.0155407 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
187948673-25519-DETAIL-06_27_2022-GO95MLD-1^07116007.0155500 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
224184963-57099-DETAIL-06_27_2022-GO95MLD-1^07116007.0155501 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
224184963-57099-DETAIL-06_27_2022-GRDRODHI-1^07116007.0155501 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
944506283-65519-DETAIL-06_27_2022-GO95MLD-1^07116007.0155502 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
569786153-78419-DETAIL-06_27_2022-GO95MLD-1^07116007.0155506 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
898787533-93689-DETAIL-06_27_2022-GO95HV-1^07116007.0155507 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
898787533-93689-DETAIL-06_27_2022-GO95MLD-1^07116007.0155507 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
743423881-45519-DETAIL-06_27_2022-GO95HV-1^07116007.0155509 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
959158794-20894-DETAIL-06_27_2022-SVCENTCO-1^07116007.0155511 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
460721844-48419-DETAIL-06_27_2022-GO95MLD-1^07116007.0155601 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
460721844-48419-AUDIT-07_25_2022-GO95HV-1^07116007.0155601 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2027-07-25 | 3
367737963-29248-DETAIL-06_27_2022-ABNDEQPM-1^07116007.0155640 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
548740873-94989-DETAIL-06_27_2022-GO95MLD-1^07116007.0155701 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
963297433-38599-DETAIL-06_27_2022-GO95HV-1^07116007.0155802 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
963297433-38599-DETAIL-06_27_2022-GO95MLD-1^07116007.0155802 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
281660693-59419-DETAIL-06_27_2022-GO95TCH-1^07116007.0156501 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
796032341-79419-DETAIL-06_27_2022-GO95HV-1^07116007.0156502 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
850742823-10519-DETAIL-06_27_2022-GO95MLD-1^07116007.0156504 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
637538083-30399-DETAIL-06_27_2022-GO95HV-1^07116007.0156602 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
637538083-30399-DETAIL-06_27_2022-GO95MLD-1^07116007.0156602 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
118664243-37599-DETAIL-06_27_2022-GO95MLD-1^07116007.0156700 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
937723093-99689-DETAIL-06_27_2022-GO95MLD-1^07116007.0156703 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
759030394-55179-DETAIL-06_27_2022-GO95MLD-1^07116007.0156901 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
991677671-19310-DETAIL-06_27_2022-ABNDEQPM-1^07116007.0156904 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
474479468-36419-DETAIL-06_28_2022-GO95MLD-1^07116007.0157400 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
763029558-95419-DETAIL-06_28_2022-GO95MLD-1^07116007.0157401 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
29961994-33994-DETAIL-06_28_2022-ENCHRW-1^07116007.0157404 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
215447704-76419-DETAIL-06_27_2022-GO95MLD-1^07116007.0157500 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
752315764-70519-DETAIL-06_27_2022-GO95MLD-1^07116007.0157502 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
595093764-73469-DETAIL-06_27_2022-GO95HV-1^07116007.0157504 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
866162751-40519-DETAIL-06_27_2022-GO95HV-1^07116007.0157506 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2027-06-27 | 3
866174643-10099-DETAIL-06_27_2022-GO95MLD-1^07116007.0157902 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
143844904-86589-DETAIL-06_28_2022-GO95MLD-1^07116007.0158500 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
143844904-86589-DETAIL-06_28_2022-SVCROAD-1^07116007.0158500 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
124309223-96419-DETAIL-06_27_2022-GO95MLD-1^07116007.0158501 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
526859278-56419-DETAIL-06_27_2022-GO95MLD-1^07116007.0159401 | OTHER | CA-TIER-2 | Distribution | 2022-06-27 | 2025-06-27 | 2
809500114-87419-DETAIL-06_28_2022-GO95MLD-1^07116007.0159500 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
809500114-87419-DETAIL-06_28_2022-SVCROOF-1^07116007.0159500 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
526263764-7419-DETAIL-06_28_2022-GO95MLD-1^07116007.0159501 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2027-06-28 | 3
605808686-48579-DETAIL-07_06_2022-GO95HV-1^07116007.0166201 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
605808686-48579-DETAIL-07_06_2022-GO95MLD-1^07116007.0166201 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
343441356-95519-DETAIL-07_06_2022-GO95HV-1^07116007.0166202 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
196342536-37399-DETAIL-07_06_2022-GO95MLD-1^07116007.0167101 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
798788756-77399-DETAIL-07_06_2022-GO95MLD-1^07116007.0167200 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
809156286-10379-DETAIL-07_06_2022-GO95HV-1^07116007.0168000 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
700130086-17519-DETAIL-07_06_2022-GO95MLD-1^07116007.0168001 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
147364196-27519-DETAIL-07_06_2022-GO95HV-1^07116007.0168101 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
950790806-67519-DETAIL-07_06_2022-GO95HV-1^07116007.0169201 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
319854728-30640-DETAIL-07_06_2022-GO95MLD-1^07116007.0219602 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
900082558-71540-DETAIL-07_06_2022-GO95MLD-1^07116007.0219900 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2025-07-06 | 2
714810865-23468-DETAIL-07_11_2022-GO95MLD-1^07116008.0060000 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
640013513-80409-DETAIL-07_11_2022-GO95MLD-1^07116008.0060101 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
576151923-86419-DETAIL-07_11_2022-GO95HV-1^07116008.0060200 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
611456779-88619-DETAIL-07_11_2022-GO95MLD-1^07116008.0070700 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
538689629-68619-DETAIL-07_11_2022-GO95HV-1^07116008.0070701 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
546346209-979-DETAIL-07_11_2022-GO95MLD-1^07116008.0071500 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2025-07-11 | 2
377207599-9619-DETAIL-07_11_2022-GO95HV-1^07116008.0071501 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
905623039-30399-DETAIL-07_11_2022-GO95HV-1^07116008.0071503 | OTHER | CA-TIER-2 | Distribution | 2022-07-11 | 2027-07-11 | 3
529814031-30089-DETAIL-07_12_2022-GO95HV-1^07117007.0053000 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
529814031-30089-DETAIL-07_12_2022-GO95MLD-1^07117007.0053000 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2025-07-12 | 2
982735801-57619-DETAIL-07_12_2022-GO95MLD-1^07117007.0054000 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2025-07-12 | 2
343961490-67619-DETAIL-07_12_2022-ABNDEQPM-1^07117007.0054100 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
343961490-67619-DETAIL-07_12_2022-SVCROAD-1^07117007.0054100 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2025-07-12 | 2
8399550-45340-DETAIL-07_12_2022-ABNDEQPM-1^07117007.0076301 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
638796141-82050-DETAIL-07_08_2022-GO95HV-1^07117007.0089840 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
903700500-45269-DETAIL-07_08_2022-GO95MLD-1^07117007.0090600 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2025-07-08 | 2
903700500-45269-DETAIL-07_08_2022-GRDRODHI-1^07117007.0090600 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2025-07-08 | 2
299828640-6619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0091600 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
430817230-46619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0091601 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
151810390-19189-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0091603 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
28731960-62619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0092802 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
46812480-64779-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0093900 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
743154620-74619-DETAIL-07_08_2022-ABNDEQPM-1^07117007.0094100 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2027-07-08 | 3
883749319-45819-DETAIL-07_12_2022-GO95HV-1^07117007.0133400 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
131212339-66819-DETAIL-07_12_2022-GO95MLD-1^07117007.0136101 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2025-07-12 | 2
589464321-25719-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150000 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
624282581-5719-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150100 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
624282581-5719-DETAIL-07_05_2022-GO95MLD-1^07117007.0150100 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2025-07-05 | 2
941327511-59250-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150101 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
968271021-24719-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150102 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
723974501-94719-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0150103 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
495672171-56719-DETAIL-07_07_2022-GO95HV-1^07117007.0152002 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
934227441-71699-DETAIL-07_07_2022-GO95HV-1^07117007.0152100 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
387393431-49719-DETAIL-07_07_2022-GO95HV-1^07117007.0168600 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
991715824-10819-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0169101 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
613459301-97050-DETAIL-07_07_2022-GO95MLD-1^07117007.0169600 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
782999081-37389-DETAIL-07_07_2022-GO95MLD-1^07117007.0169604 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2025-07-07 | 2
908001381-31050-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0169701 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
669622861-8719-DETAIL-07_08_2022-GO95MLD-1^07117007.0169803 | OTHER | CA-TIER-2 | Distribution | 2022-07-08 | 2025-07-08 | 2
110416563-63663-DETAIL-07_07_2022-GO95HV-1^07117007.0225930 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
166417101-47599-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0226200 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
48138651-29689-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0226701 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
176262991-73819-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0227200 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
391351061-4819-DETAIL-05_25_2023-GO95HV-1^07117007.0227202 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2028-05-25 | 3
636285441-52819-DETAIL-05_25_2023-RISEGRD-1^07117007.0227400 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2026-05-25 | 2
906152341-22819-DETAIL-07_05_2022-GO95MLD-1^07117007.0227500 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2025-07-05 | 2
228954591-92099-DETAIL-05_25_2023-GO95HV-1^07117007.0227600 | OTHER | CA-TIER-2 | Distribution | 2023-05-25 | 2028-05-25 | 3
38544281-38169-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0227601 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
59606891-24819-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0228100 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
287860761-64819-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0229000 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
273996941-94819-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0229102 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
338588340-59819-DETAIL-07_05_2022-GO95MLD-1^07117007.0260001 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2025-07-05 | 2
338588340-59819-DETAIL-07_05_2022-GRDRODHI-1^07117007.0260001 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2025-07-05 | 2
220903740-44880-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0260700 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
303100430-96819-DETAIL-07_07_2022-SVCWIND-1^07117007.0260901 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2025-07-07 | 2
187651250-97819-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0261301 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
386405701-71919-DETAIL-07_07_2022-GO95HV-1^07117007.0278901 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
500046711-61669-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0279000 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
396173378-44378-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0279001 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
95698331-92919-DETAIL-07_06_2022-ABNDEQPM-1^07117007.0279703 | OTHER | CA-TIER-2 | Distribution | 2022-07-06 | 2027-07-06 | 3
993078951-31919-DETAIL-07_07_2022-ABNDEQPM-1^07117007.0279903 | OTHER | CA-TIER-2 | Distribution | 2022-07-07 | 2027-07-07 | 3
869331358-52358-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0349000 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
869331358-52358-DETAIL-07_05_2022-GO95HV-1^07117007.0349000 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
390290824-15919-DETAIL-07_05_2022-GO95HV-1^07117007.0349001 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
184389645-65920-DETAIL-07_05_2022-GO95HV-1^07117007.0349701 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
268395645-59903-DETAIL-07_05_2022-GO95HV-1^07117007.0349702 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
982750645-36803-DETAIL-07_05_2022-GO95HV-1^07117007.0349703 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
77115130-70919-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0350400 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
742761760-27340-DETAIL-07_05_2022-GO95HV-1^07117007.0350501 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
742240650-2340-DETAIL-07_05_2022-ABNDEQPM-1^07117007.0350701 | OTHER | CA-TIER-2 | Distribution | 2022-07-05 | 2027-07-05 | 3
835046079-66919-DETAIL-07_12_2022-GO95HV-1^07118006.0258001 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
74641669-86919-DETAIL-07_12_2022-GO95HV-1^07118006.0258002 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
772200295-32669-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0322300 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
157872195-2669-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0322301 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
164813559-29919-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0322303 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
906853395-78352-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0323400 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
674419395-41941-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0324400 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
438875495-72669-DETAIL-07_12_2022-ABNDEQPM-1^07118007.0324501 | OTHER | CA-TIER-2 | Distribution | 2022-07-12 | 2027-07-12 | 3
818281441-469-DTLTRT-10_24_2022-GO95MLD-1^668001/00 1/024 | OTHER | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
818281441-469-DTLTRT-10_24_2022-GUYHINS-1^668001/00 1/024 | ANCHOR/GUY | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
959870934-58499-DTLTRT-11_15_2022-GO95HV-1^668001/00 1/043 | OTHER | CA-TIER-2 | Transmission | 2022-11-15 | 2027-11-15 | 3
358076479-51669-DTLTRT-11_15_2022-GO95HV-1^668001/00 1/048 | OTHER | CA-TIER-2 | Transmission | 2022-11-15 | 2027-11-15 | 3
85218943-51689-DTLTRT-11_07_2022-GO95HV-1^668001/00 10/030 | OTHER | FHCA | Transmission | 2022-11-07 | 2027-11-07 | 3
153471741-38690-DTLTRT-10_24_2022-GO95HV-1^668001/00 11/023 | OTHER | FHCA | Transmission | 2022-10-24 | 2027-10-24 | 3
566490951-94369-DTLTRT-10_24_2022-GO95MLD-1^668001/00 11/024 | OTHER | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
538645071-62369-DTLTRT-10_24_2022-GO95MLD-1^668001/00 12/024 | OTHER | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
538364670-42329-DTLTRT-10_26_2022-GO95HV-1^668001/00 12/028 | OTHER | FHCA | Transmission | 2022-10-26 | 2027-10-26 | 3
621562851-61131-DETAIL-12_22_2022-GO95MLD-1^668001/00 13/023 | OTHER | FHCA | Transmission | 2022-12-22 | 2025-12-22 | 2
320857180-20209-DTLTRT-10_26_2022-GO95MLD-1^668001/00 13/028 | OTHER | FHCA | Transmission | 2022-10-26 | 2025-10-26 | 2
970746179-15299-DTLTRT-11_10_2022-GO95HV-1^668001/00 13/038 | OTHER | CA-TIER-2 | Transmission | 2022-11-10 | 2027-11-10 | 3
306527538-60263-DETAIL-10_25_2022-GO95HV-1^668001/00 13/046 | OTHER | CA-TIER-2 | Transmission | 2022-10-25 | 2027-10-25 | 3
866338354-89999-DTLTRT-10_27_2022-GUYNOINS-1^668001/00 13A/031 | ANCHOR/GUY | FHCA | Transmission | 2022-10-27 | 2025-10-27 | 2
866338354-89999-DTLTRT-10_27_2022-GUYNOINS-2^668001/00 13A/031 | ANCHOR/GUY | FHCA | Transmission | 2022-10-27 | 2025-10-27 | 2
866338354-89999-DTLTRT-10_27_2022-GUYNOINS-3^668001/00 13A/031 | ANCHOR/GUY | FHCA | Transmission | 2022-10-27 | 2025-10-27 | 2
452390701-73999-DTLTRT-11_07_2022-GO95MLD-1^668001/00 14/029 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
393401173-85469-DTLTRT-11_07_2022-GO95BLTC-1^668001/00 14/030 | OTHER | FHCA | Transmission | 2022-11-07 | 2027-11-07 | 3
393401173-85469-DTLTRT-11_07_2022-GO95MLD-1^668001/00 14/030 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
193754063-96399-DTLTRT-11_14_2022-GO95HV-1^668001/00 14/041 | OTHER | CA-TIER-2 | Transmission | 2022-11-14 | 2027-11-14 | 3
446534746-46746-DTLTRT-11_17_2022-GO95MLD-1^668001/00 14/046 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
266873219-71473-DTLTRT-11_17_2022-GO95HV-1^668001/00 14A/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
263548429-42473-DTLTRT-11_17_2022-GO95HV-1^668001/00 15/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
704942093-73309-DTLTRT-11_07_2022-GO95HV-1^668001/00 17/030 | OTHER | FHCA | Transmission | 2022-11-07 | 2027-11-07 | 3
723775003-24309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 18/030 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
604131985-82985-DTLTRT-11_07_2022-GO95MLD-1^668001/00 18/031 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
136829511-53880-DTLTRT-10_24_2022-GO95HV-1^668001/00 19/023 | OTHER | FHCA | Transmission | 2022-10-24 | 2027-10-24 | 3
653682981-52209-DTLTRT-10_26_2022-GO95MLD-1^668001/00 19/028 | OTHER | FHCA | Transmission | 2022-10-26 | 2025-10-26 | 2
981161603-64309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 19/030 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
392163998-80599-DETAIL-11_15_2022-GUYHINS-1^668001/00 19/045 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-15 | 2025-11-15 | 2
392163998-80599-DETAIL-11_15_2022-GUYNOINS-1^668001/00 19/045 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-15 | 2025-11-15 | 2
191697019-91573-DTLTRT-11_17_2022-GO95HV-1^668001/00 19/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
837092141-31222-DETAIL-12_19_2022-GO95HV-1^668001/00 2/024 | OTHER | FHCA | Transmission | 2022-12-19 | 2027-12-19 | 3
371124223-75309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 2/031 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
958988999-27673-DTLTRT-11_15_2022-GO95HV-1^668001/00 2/048 | OTHER | CA-TIER-2 | Transmission | 2022-11-15 | 2027-11-15 | 3
494050629-43573-DTLTRT-11_17_2022-GO95HV-1^668001/00 20/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
578684449-46573-DTLTRT-11_17_2022-GO95HV-1^668001/00 20A/047 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
983037808-86563-DTLTRT-11_17_2022-GO95HV-1^668001/00 22/045 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
502045270-97369-DTLTRT-10_24_2022-GO95BLTC-1^668001/00 24/022 | OTHER | FHCA | Transmission | 2022-10-24 | 2027-10-24 | 3
502045270-97369-DTLTRT-10_24_2022-GO95HV-1^668001/00 24/022 | OTHER | FHCA | Transmission | 2022-10-24 | 2027-10-24 | 3
502045270-97369-DTLTRT-10_24_2022-GO95MLD-1^668001/00 24/022 | OTHER | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
502045270-97369-DTLTRT-10_24_2022-GUYHINS-2^668001/00 24/022 | ANCHOR/GUY | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
502045270-97369-DTLTRT-10_24_2022-GUYHINS-3^668001/00 24/022 | ANCHOR/GUY | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
502045270-97369-DTLTRT-10_24_2022-GUYHINS-4^668001/00 24/022 | ANCHOR/GUY | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
502045270-97369-DETAIL-12_19_2022-GUYHINS-1^668001/00 24/022 | ANCHOR/GUY | FHCA | Transmission | 2022-12-19 | 2025-12-19 | 2
502045270-97369-DETAIL-12_19_2022-GUYHINS-2^668001/00 24/022 | ANCHOR/GUY | FHCA | Transmission | 2022-12-19 | 2025-12-19 | 2
502045270-97369-DETAIL-12_19_2022-GUYHINS-3^668001/00 24/022 | ANCHOR/GUY | FHCA | Transmission | 2022-12-19 | 2025-12-19 | 2
716419200-78469-DETAIL-12_19_2022-ANCHIDLE-1^668001/00 25/022 | ANCHOR/GUY | FHCA | Transmission | 2022-12-19 | 2025-12-19 | 2
716419200-78469-DETAIL-12_19_2022-GRDRODHI-1^668001/00 25/022 | OTHER | FHCA | Transmission | 2022-12-19 | 2025-12-19 | 2
794604550-59679-DTLTRT-10_24_2022-GO95HV-1^668001/00 3/023 | OTHER | FHCA | Transmission | 2022-10-24 | 2027-10-24 | 3
385701375-71375-DTLTRT-11_17_2022-GUYHINS-1^668001/00 3X/049 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
385701375-71375-DTLTRT-11_17_2022-GUYHINS-2^668001/00 3X/049 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
385701375-71375-DTLTRT-11_17_2022-GUYHINS-3^668001/00 3X/049 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
385701375-71375-DTLTRT-11_17_2022-GUYHINS-4^668001/00 3X/049 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
108106870-10779-DTLTRT-10_24_2022-GO95HV-1^668001/00 4/023 | OTHER | FHCA | Transmission | 2022-10-24 | 2027-10-24 | 3
179008721-44209-DTLTRT-10_27_2022-GO95MLD-1^668001/00 4/029 | OTHER | FHCA | Transmission | 2022-10-27 | 2025-10-27 | 2
726059743-56309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 4/031 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
612593103-85009-DTLTRT-11_07_2022-GO95MLD-1^668001/00 5/030 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
31872591-10609-DTLTRT-11_07_2022-GO95BLTC-1^668001/00 5/032 | OTHER | FHCA | Transmission | 2022-11-07 | 2027-11-07 | 3
31872591-10609-DTLTRT-11_07_2022-GO95HV-1^668001/00 5/032 | OTHER | FHCA | Transmission | 2022-11-07 | 2027-11-07 | 3
31872591-10609-DTLTRT-11_07_2022-GO95MLD-1^668001/00 5/032 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
762850524-5679-DTLTRT-11_14_2022-GO95HV-1^668001/00 5/042 | OTHER | CA-TIER-2 | Transmission | 2022-11-14 | 2027-11-14 | 3
641740458-40163-DTLTRT-11_17_2022-GO95HV-1^668001/00 5/046 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
87665190-38369-DETAIL-10_24_2022-ANCHIDLE-1^668001/00 6/023 | ANCHOR/GUY | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
802240241-79899-DTLTRT-10_27_2022-GO95MLD-1^668001/00 6/029 | OTHER | FHCA | Transmission | 2022-10-27 | 2025-10-27 | 2
789834401-4662-DTLTRT-10_24_2022-GO95MLD-1^668001/00 7/023 | OTHER | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
876843441-10999-DTLTRT-10_27_2022-GO95MLD-1^668001/00 7/029 | OTHER | FHCA | Transmission | 2022-10-27 | 2025-10-27 | 2
585249973-70883-DTLTRT-11_07_2022-GO95MLD-1^668001/00 7/031 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
238217911-20970-DTLTRT-10_24_2022-GUYHINS-1^668001/00 8/023 | ANCHOR/GUY | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
238217911-20970-DTLTRT-10_24_2022-GUYHINS-2^668001/00 8/023 | ANCHOR/GUY | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
238217911-20970-DTLTRT-10_24_2022-GUYHINS-3^668001/00 8/023 | ANCHOR/GUY | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
238217911-20970-DETAIL-12_20_2022-GO95HV-1^668001/00 8/023 | OTHER | FHCA | Transmission | 2022-12-20 | 2027-12-20 | 3
763756231-67991-DTLTRT-10_24_2022-GO95MLD-1^668001/00 9/024 | OTHER | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
443796761-1999-DTLTRT-11_07_2022-GO95MLD-1^668001/00 9/029 | OTHER | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
493535233-67009-DTLTRT-11_07_2022-GO95HV-1^668001/00 9/030 | OTHER | FHCA | Transmission | 2022-11-07 | 2027-11-07 | 3
481961610-76273-DTLTRT-11_17_2022-GO95HV-1^668001/00 9A/048 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
551606264-83983-DTLTRT-11_17_2022-GO95MLD-1^668001/06 1/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
704658345-78345-DETAIL-11_17_2022-GO95HV-1^668001/06 1X2/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
284314564-6983-DTLTRT-11_17_2022-GO95HV-1^668001/06 2/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-17 | 2027-11-17 | 3
560541204-68083-DTLTRT-11_17_2022-GUYHINS-1^668001/06 7/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-17 | 2025-11-17 | 2
741603209-36469-DETAIL-02_15_2023-GO95BLTC-1^668002/00 10/014 | OTHER | FHCA | Transmission | 2023-02-15 | 2028-02-15 | 3
774700925-76950-DRONE_HY-09_16_2023-UGEQRUST-1^668002/00 10/058 | TRANSFORMER | CA-TIER-2 | Transmission | 2023-09-16 | 2028-09-16 | 3
665080454-65969-DETAIL-03_08_2023-GO95HV-1^668002/00 11/034 | OTHER | CA-TIER-2 | Transmission | 2023-03-08 | 2028-03-08 | 3
411175129-82179-DRONE_HY-09_13_2023-GO95HV-1^668002/00 11/077 | OTHER | CA-TIER-2 | Transmission | 2023-09-13 | 2028-09-13 | 3
507691148-28469-DRONE_HY-09_14_2023-GO95HV-1^668002/00 12/012 | OTHER | FHCA | Transmission | 2023-09-14 | 2028-09-14 | 3
528229139-70069-DRONE_HY-09_14_2023-GO95HV-1^668002/00 12/041 | OTHER | CA-TIER-2 | Transmission | 2023-09-14 | 2028-09-14 | 3
747506958-85423-DRONE_HY-09_14_2023-GO95HV-1^668002/00 13/012 | OTHER | FHCA | Transmission | 2023-09-14 | 2028-09-14 | 3
503703429-18769-DRONE_HY-09_14_2023-GO95HV-1^668002/00 13/014 | OTHER | FHCA | Transmission | 2023-09-14 | 2028-09-14 | 3
118321139-58769-DETAIL-02_15_2023-GO95HV-1^668002/00 15/014 | OTHER | FHCA | Transmission | 2023-02-15 | 2028-02-15 | 3
79489183-74969-DETAIL-02_08_2023-GO95HV-1^668002/00 15/018 | OTHER | FHCA | Transmission | 2023-02-08 | 2028-02-08 | 3
639235893-98769-DRONE_HY-09_20_2023-GO95HV-1^668002/00 15/063 | OTHER | FHCA | Transmission | 2023-09-20 | 2028-09-20 | 3
525312651-47369-DETAIL-03_09_2023-GO95HV-1^668002/00 16/004 | OTHER | FHCA | Transmission | 2023-03-09 | 2028-03-09 | 3
91220239-78769-DETAIL-02_15_2023-GO95HV-1^668002/00 16/014 | OTHER | FHCA | Transmission | 2023-02-15 | 2028-02-15 | 3
967390479-23269-DRONE_HY-09_21_2023-GO95HV-1^668002/00 16/066 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
211939961-87369-DETAIL-03_09_2023-GO95HV-1^668002/00 17/004 | OTHER | FHCA | Transmission | 2023-03-09 | 2028-03-09 | 3
247828349-29769-DETAIL-02_15_2023-GO95HV-1^668002/00 17/014 | OTHER | FHCA | Transmission | 2023-02-15 | 2028-02-15 | 3
133076909-52869-DRONE_HY-09_14_2023-GO95HV-1^668002/00 17/015 | OTHER | FHCA | Transmission | 2023-09-14 | 2028-09-14 | 3
154317471-83469-DRONE_HY-09_20_2023-GO95HV-1^668002/00 17/070 | OTHER | CA-TIER-2 | Transmission | 2023-09-20 | 2028-09-20 | 3
55885559-98769-DETAIL-02_15_2023-GO95HV-1^668002/00 18/014 | OTHER | FHCA | Transmission | 2023-02-15 | 2028-02-15 | 3
487609958-32569-DRONE_HY-09_14_2023-GO95HV-1^668002/00 18/048 | OTHER | CA-TIER-2 | Transmission | 2023-09-14 | 2028-09-14 | 3
166030043-37940-DRONE_HY-09_14_2023-GO95HV-1^668002/00 19/055 | OTHER | CA-TIER-3 | Transmission | 2023-09-14 | 2028-09-14 | 3
586334494-44269-DETAIL-05_26_2022-GO95HV-1^668002/00 2/001 | OTHER | FHCA | Transmission | 2022-05-26 | 2027-05-26 | 3
321913391-83179-DETAIL-05_09_2022-GO95HV-1^668002/00 20/050 | OTHER | CA-TIER-2 | Transmission | 2022-05-09 | 2027-05-09 | 3
519869996-29279-DRONE_HY-09_23_2023-ABNDEQPM-1^668002/00 25/059 | OTHER | CA-TIER-2 | Transmission | 2023-09-23 | 2028-09-23 | 3
206576059-24479-DRONE_HY-09_13_2023-GO95HV-1^668002/00 3/078 | OTHER | CA-TIER-2 | Transmission | 2023-09-13 | 2028-09-13 | 3
504335064-14969-DETAIL-03_08_2023-GO95HV-1^668002/00 4/034 | OTHER | CA-TIER-2 | Transmission | 2023-03-08 | 2028-03-08 | 3
531297279-44869-DRONE_HY-09_14_2023-GO95HV-1^668002/00 5/016 | OTHER | FHCA | Transmission | 2023-09-14 | 2028-09-14 | 3
814187078-12169-DETAIL-03_09_2023-GO95HV-1^668002/00 5/023 | OTHER | FHCA | Transmission | 2023-03-09 | 2028-03-09 | 3
191432041-38869-DRONE_HY-09_03_2023-GO95HV-1^668002/00 6/017 | OTHER | FHCA | Transmission | 2023-09-03 | 2028-09-03 | 3
159542153-61069-DETAIL-03_08_2023-GO95BLTC-1^668002/00 6/032 | OTHER | CA-TIER-2 | Transmission | 2023-03-08 | 2026-03-08 | 2
496480979-47769-DETAIL-02_15_2023-GRDRODHI-1^668002/00 9/014 | OTHER | FHCA | Transmission | 2023-02-15 | 2028-02-15 | 3
351639731-40369-DRONE_HY-09_16_2023-GO95HV-1^668002/00 9/061 | OTHER | CA-TIER-2 | Transmission | 2023-09-16 | 2028-09-16 | 3
958231879-16330-DETAIL-05_03_2023-GUYNOINS-1^668002/01 11/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-05-03 | 2026-05-03 | 2
237045863-11470-DETAIL-01_31_2023-GO95HV-1^668002/07 16/001 | OTHER | CA-TIER-2 | Transmission | 2023-01-31 | 2028-01-31 | 3
734226600-26070-DTLTRT-11_16_2022-GO95HV-1^668003/00 10X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-2^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-3^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-4^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-5^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
734226600-26070-DTLTRT-11_16_2022-GUYNOINS-6^668003/00 10X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
821395310-47070-DTLTRT-11_16_2022-GO95HV-1^668003/00 11X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
551094510-39070-DTLTRT-11_16_2022-GO95HV-1^668003/00 12X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
53985910-70170-DTLTRT-11_16_2022-GO95HV-1^668003/00 13X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
415594390-80370-DTLTRT-11_16_2022-GO95HV-1^668003/00 14X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
246900900-91370-DTLTRT-11_16_2022-GO95HV-1^668003/00 15X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
398579100-37370-DTLTRT-11_16_2022-GO95HV-1^668003/00 17X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
416873980-44679-DTLTRT-11_16_2022-GO95MLD-1^668003/00 2X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
313275390-31340-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 3X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
681183470-670-DTLTRT-11_16_2022-GO95HV-1^668003/00 3X/002 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
849646190-37970-DTLTRT-11_16_2022-GO95HV-1^668003/00 4X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
589421180-91340-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 4X/002 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
946257990-98040-DTLTRT-11_16_2022-GO95HV-1^668003/00 5X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
946257990-98040-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 5X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
946257990-98040-DTLTRT-11_16_2022-GUYNOINS-2^668003/00 5X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
222354480-93670-DTLTRT-11_16_2022-GO95HV-1^668003/00 5X/002 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
909400590-32070-DTLTRT-11_16_2022-GO95HV-1^668003/00 6X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
878242880-84670-DTLTRT-11_16_2022-GO95HV-1^668003/00 6X/002 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
440264480-55670-DTLTRT-11_16_2022-GO95HV-1^668003/00 7X/002 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
318923400-34070-DTLTRT-11_16_2022-GO95HV-1^668003/00 8X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
318923400-34070-DTLTRT-11_16_2022-GUYNOINS-1^668003/00 8X/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2022-11-16 | 2025-11-16 | 2
107921900-15070-DTLTRT-11_16_2022-GO95HV-1^668003/00 9X/001 | OTHER | CA-TIER-2 | Transmission | 2022-11-16 | 2027-11-16 | 3
14568933-86280-DTLTRT-09_25_2023-GO95HV-1^668010/00 1/004 | OTHER | FHCA | Transmission | 2023-09-25 | 2028-09-25 | 3
575737673-52879-DTLTRT-09_27_2023-GO95HV-1^668010/00 1/006 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
605354734-60180-DTLTRT-09_27_2023-GO95MLD-1^668010/00 1/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
308345061-61030-DTLTRT-10_30_2023-GO95HV-1^668010/00 1/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
308345061-61030-DTLTRT-10_30_2023-GUYLOINS-1^668010/00 1/014 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-30 | 2026-10-30 | 2
975611084-95979-DTLTRT-10_30_2023-GO95HV-1^668010/00 1/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
60980975-24190-DTLTRT-10_31_2023-GO95HV-1^668010/00 1/017 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
849774085-21479-DTLTRT-11_01_2023-GO95HV-1^668010/00 1/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
926219268-9479-DTLTRT-11_02_2023-GO95HV-1^668010/00 1/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
138340549-35900-DTLTRT-10_26_2023-GUYLOINS-1^668010/00 1/023 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
138340549-35900-DTLTRT-10_26_2023-GUYLOINS-2^668010/00 1/023 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
138340549-35900-DTLTRT-10_26_2023-GUYLOINS-3^668010/00 1/023 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
399901221-61769-DTLTRT-10_05_2023-GO95MLD-1^668010/00 1/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
399901221-61769-DTLTRT-10_05_2023-SVCROAD-1^668010/00 1/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
173537351-36579-DTLTRT-10_05_2023-GO95HV-1^668010/00 1/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
394634371-66579-DTLTRT-10_04_2023-GO95HV-1^668010/00 1/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2028-10-04 | 3
394634371-66579-DTLTRT-10_04_2023-GO95MLD-1^668010/00 1/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
599842902-58340-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 1/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
31737743-7540-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
558464254-8040-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
531002633-85940-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/035 | OTHER | FHCA | Transmission | 2023-10-02 | 2028-10-02 | 3
415034995-56360-DTLTRT-10_09_2023-GO95HV-1^668010/00 1/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
415034995-56360-DTLTRT-10_09_2023-GUYHINS-1^668010/00 1/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
419608113-48369-DTLTRT-10_11_2023-GO95MLD-1^668010/00 1/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
477594402-61321-DTLTRT-10_16_2023-GO95HV-1^668010/00 10/002 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
318662544-58469-DTLTRT-09_25_2023-GO95MLD-1^668010/00 10/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2026-09-25 | 2
318662544-58469-DTLTRT-09_25_2023-GO95TCH-1^668010/00 10/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2026-09-25 | 2
74647123-44570-DTLTRT-09_26_2023-GO95HV-1^668010/00 10/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
230439944-61780-DTLTRT-09_27_2023-GO95MLD-1^668010/00 10/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
297880096-95890-DTLTRT-10_18_2023-GO95HV-1^668010/00 10/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
541149306-79700-DTLTRT-11_01_2023-GO95HV-1^668010/00 10/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
494152419-68979-DTLTRT-10_26_2023-GO95HV-1^668010/00 10/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
91726933-35779-DTLTRT-10_19_2023-GO95HV-1^668010/00 10/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
91726933-35779-DTLTRT-10_19_2023-GO95MLD-1^668010/00 10/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2026-10-19 | 2
582254773-17640-DTLTRT-10_04_2023-GO95HV-1^668010/00 10/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
582254773-17640-DTLTRT-10_04_2023-GO95MLD-1^668010/00 10/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
582254773-17640-DTLTRT-10_04_2023-INSULDMG-1^668010/00 10/029 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
297936813-5140-DTLTRT-10_03_2023-GO95MLD-1^668010/00 10/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
297936813-5140-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 10/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
506499844-53540-DTLTRT-10_02_2023-GO95HV-1^668010/00 10/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
506499844-53540-DTLTRT-10_02_2023-GO95MLD-1^668010/00 10/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
716846955-20650-DTLTRT-10_10_2023-GO95MLD-1^668010/00 10/037 | OTHER | FHCA | Transmission | 2023-10-10 | 2028-10-10 | 3
688514466-80269-DTLTRT-10_09_2023-GO95HV-1^668010/00 10/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
937784506-80460-DTLTRT-10_12_2023-GO95HV-1^668010/00 10/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
937784506-80460-DTLTRT-10_12_2023-GO95MLD-1^668010/00 10/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
62310008-76069-DTLTRT-10_11_2023-GO95MLD-1^668010/00 10/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
142040518-5169-DTLTRT-10_23_2023-GO95HV-1^668010/00 10/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
142040518-5169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 10/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
796551319-93479-DTLTRT-11_01_2023-GUYNOINS-1^668010/00 10A/018 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-01 | 2026-11-01 | 2
181128184-32240-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 10A/035 | ANCHOR/GUY | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
181128184-32240-DTLTRT-10_04_2023-GUYNOINS-2^668010/00 10A/035 | ANCHOR/GUY | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
700104508-27820-DTLTRT-10_17_2023-GUYNOINS-1^668010/00 10XB/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
700104508-27820-DTLTRT-10_17_2023-GUYNOINS-2^668010/00 10XB/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
700104508-27820-DTLTRT-10_17_2023-GUYNOINS-3^668010/00 10XB/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
216091161-29470-DTLTRT-10_16_2023-GO95HV-1^668010/00 11/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
766339812-44469-DTLTRT-10_16_2023-GO95MLD-1^668010/00 11/002 | OTHER | FHCA | Transmission | 2023-10-16 | 2026-10-16 | 2
680819384-24180-DTLTRT-09_26_2023-GO95HV-1^668010/00 11/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
660711464-30880-DTLTRT-09_27_2023-GO95HV-1^668010/00 11/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
660711464-30880-DTLTRT-09_27_2023-GO95MLD-1^668010/00 11/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
665832106-41990-DTLTRT-10_18_2023-GO95HV-1^668010/00 11/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
348953118-32630-DTLTRT-10_18_2023-GO95HV-1^668010/00 11/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
995571705-90890-DTLTRT-10_31_2023-GO95HV-1^668010/00 11/017 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
614874848-24679-DTLTRT-11_02_2023-GO95CL10-1^668010/00 11/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
614874848-24679-DTLTRT-11_02_2023-GO95MLD-1^668010/00 11/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
614874848-24679-DTLTRT-11_02_2023-GO95TCH-1^668010/00 11/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
893496869-91579-DTLTRT-10_26_2023-GO95BLTC-1^668010/00 11/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
893496869-91579-DTLTRT-10_26_2023-GO95MLD-1^668010/00 11/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
647873680-64579-DTLTRT-11_03_2023-GO95HV-1^668010/00 11/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
32610481-85130-DTLTRT-10_05_2023-GO95MLD-1^668010/00 11/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
32610481-85130-DTLTRT-10_05_2023-GUYHINS-1^668010/00 11/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
449832883-46579-AUDIT-11_10_2023-INSULDMG-1^668010/00 11/029 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-11-10 | 2026-11-10 | 2
736793804-4340-DTLTRT-10_04_2023-GO95HV-1^668010/00 11/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2028-10-04 | 3
736793804-4340-DTLTRT-10_04_2023-GO95MLD-1^668010/00 11/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
736793804-4340-DTLTRT-10_04_2023-GUYHINS-1^668010/00 11/035 | ANCHOR/GUY | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
736793804-4340-DTLTRT-10_04_2023-GUYHINS-2^668010/00 11/035 | ANCHOR/GUY | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
98501075-4779-DTLTRT-10_10_2023-GO95MLD-1^668010/00 11/037 | OTHER | FHCA | Transmission | 2023-10-10 | 2026-10-10 | 2
98501075-4779-AUDIT-11_10_2023-GO95HV-1^668010/00 11/037 | OTHER | FHCA | Transmission | 2023-11-10 | 2028-11-10 | 3
232544276-50269-DTLTRT-10_09_2023-ABNDEQPM-1^668010/00 11/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
232544276-50269-DTLTRT-10_09_2023-GO95HV-1^668010/00 11/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
232544276-50269-DTLTRT-10_09_2023-GO95MLD-1^668010/00 11/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
120302116-46460-DTLTRT-10_12_2023-GO95HV-1^668010/00 11/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
580632406-89069-DTLTRT-10_12_2023-GO95BLTC-1^668010/00 11/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
580632406-89069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 11/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
580632406-89069-DTLTRT-10_12_2023-GRDRODHI-1^668010/00 11/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
580632406-89069-DTLTRT-10_12_2023-GRDRODHI-2^668010/00 11/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
426230963-92340-DTLTRT-10_19_2023-GUYNOINS-1^668010/00 11A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
426230963-92340-DTLTRT-10_19_2023-GUYNOINS-2^668010/00 11A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
426230963-92340-DTLTRT-10_19_2023-GUYNOINS-3^668010/00 11A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
426230963-92340-DTLTRT-10_19_2023-GUYNOINS-4^668010/00 11A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
619782632-42540-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 11A/031 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
619782632-42540-DTLTRT-10_03_2023-GUYNOINS-2^668010/00 11A/031 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
676724434-28440-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 11A/035 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
975935786-33590-DTLTRT-10_16_2023-GO95HV-1^668010/00 11X/008 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
486288671-69470-DTLTRT-10_16_2023-GO95HV-1^668010/00 12/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
795171614-81469-DTLTRT-09_26_2023-ANCHIDLE-1^668010/00 12/004 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
795171614-81469-DTLTRT-09_26_2023-GO95MLD-1^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
795171614-81469-DTLTRT-09_26_2023-GRDRODHI-1^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
795171614-81469-DTLTRT-09_26_2023-GRDRODHI-2^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
795171614-81469-DTLTRT-09_26_2023-GRDRODHI-3^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
795171614-81469-DTLTRT-09_26_2023-SVCROAD-1^668010/00 12/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
530417643-48379-DTLTRT-09_26_2023-GO95HV-1^668010/00 12/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
771930464-46880-DTLTRT-09_27_2023-GO95MLD-1^668010/00 12/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
624513615-27890-AUDIT-11_10_2023-GO95HV-1^668010/00 12/017 | OTHER | CA-TIER-2 | Transmission | 2023-11-10 | 2028-11-10 | 3
876866739-88979-DTLTRT-10_26_2023-GO95HV-1^668010/00 12/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
448783463-29779-DTLTRT-10_19_2023-GO95MLD-1^668010/00 12/024 | OTHER | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
789259021-75330-DTLTRT-10_05_2023-GUYHINS-1^668010/00 12/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
140955893-42740-DTLTRT-10_04_2023-GO95HV-1^668010/00 12/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2028-10-04 | 3
140955893-42740-DTLTRT-10_04_2023-GO95MLD-1^668010/00 12/029 | OTHER | CA-NON-TIER | Transmission | 2023-10-04 | 2026-10-04 | 2
817917591-47579-DTLTRT-10_03_2023-GUYHINS-1^668010/00 12/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
17909742-72540-DTLTRT-10_03_2023-GO95HV-1^668010/00 12/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
161210264-55740-DTLTRT-10_02_2023-GO95MLD-1^668010/00 12/034 | OTHER | FHCA | Transmission | 2023-10-02 | 2026-10-02 | 2
865845684-51569-DTLTRT-10_10_2023-RISEBKSP-1^668010/00 12/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
865845684-51569-DTLTRT-10_10_2023-RISEGRD-1^668010/00 12/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
752733326-2769-DTLTRT-10_12_2023-GO95HV-1^668010/00 12/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
752733326-2769-DTLTRT-10_12_2023-GO95MLD-1^668010/00 12/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
454372218-36069-DTLTRT-10_11_2023-GO95HV-1^668010/00 12/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
454372218-36069-DTLTRT-10_11_2023-GO95MLD-1^668010/00 12/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
36287608-43169-DTLTRT-10_10_2023-GUYNOINS-1^668010/00 12/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
375097031-17330-DTLTRT-10_05_2023-GUYHINS-1^668010/00 12A/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
375097031-17330-DTLTRT-10_05_2023-GUYNOINS-1^668010/00 12A/028 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
250547013-90113-DTLTRT-10_10_2023-GUYNOINS-1^668010/00 12A/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
250547013-90113-DTLTRT-10_10_2023-GUYNOINS-2^668010/00 12A/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
250547013-90113-DTLTRT-10_10_2023-GUYNOINS-3^668010/00 12A/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
250547013-90113-DTLTRT-10_10_2023-GUYNOINS-4^668010/00 12A/044 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
274472706-76790-DTLTRT-10_17_2023-GUYHINS-1^668010/00 12X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
977593628-56920-DTLTRT-10_17_2023-GO95MLD-1^668010/00 12X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
284928581-79470-DTLTRT-10_16_2023-GO95HV-1^668010/00 13/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
603038734-86379-DTLTRT-09_26_2023-GO95MLD-1^668010/00 13/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
603038734-86379-DTLTRT-09_26_2023-GUYHINS-1^668010/00 13/004 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
587377753-73670-DTLTRT-09_26_2023-GO95HV-1^668010/00 13/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
587377753-73670-DTLTRT-09_26_2023-GO95STUB-1^668010/00 13/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
501555801-18330-DTLTRT-10_30_2023-GO95HV-1^668010/00 13/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
600730915-37979-DTLTRT-10_31_2023-GO95BLTC-1^668010/00 13/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
600730915-37979-DTLTRT-10_31_2023-GO95HV-1^668010/00 13/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
893010450-4930-DTLTRT-11_03_2023-GO95HV-1^668010/00 13/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
990666832-67579-DTLTRT-10_03_2023-GO95HV-1^668010/00 13/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
775253052-45540-DTLTRT-10_03_2023-GO95HV-1^668010/00 13/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
183880633-73240-DTLTRT-10_05_2023-GO95MLD-1^668010/00 13/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
183880633-73240-DTLTRT-10_05_2023-GRDRODHI-1^668010/00 13/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
635791764-25740-DTLTRT-10_04_2023-GO95HV-1^668010/00 13/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2028-10-04 | 3
232319566-68060-DTLTRT-10_09_2023-GO95MLD-1^668010/00 13/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
232319566-68060-DTLTRT-10_09_2023-GUYHINS-1^668010/00 13/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
232319566-68060-DTLTRT-10_09_2023-GUYHINS-2^668010/00 13/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
232319566-68060-DTLTRT-10_09_2023-GUYHINS-3^668010/00 13/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
232319566-68060-DTLTRT-10_09_2023-GUYHINS-4^668010/00 13/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
277401545-85269-DTLTRT-10_10_2023-GO95HV-1^668010/00 13/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
277401545-85269-DTLTRT-10_10_2023-INSULDMG-1^668010/00 13/040 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
883793136-44560-DTLTRT-10_12_2023-GO95HV-1^668010/00 13/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
932367616-29069-DTLTRT-10_23_2023-GO95HV-1^668010/00 13/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
454472038-51030-DETAIL-10_17_2023-GUYHINS-1^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-2^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-3^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-4^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-5^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
454472038-51030-DETAIL-10_17_2023-GUYHINS-6^668010/00 13X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
906086291-62570-DTLTRT-10_16_2023-GO95HV-1^668010/00 14/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
119221653-39470-DTLTRT-09_26_2023-GO95MLD-1^668010/00 14/003 | OTHER | FHCA | Transmission | 2023-09-26 | 2026-09-26 | 2
702188384-98980-DTLTRT-09_27_2023-GO95MLD-1^668010/00 14/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
965491739-46130-DETAIL-10_26_2023-GUYHINS-1^668010/00 14/021 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
965491739-46130-DETAIL-10_26_2023-GUYHINS-2^668010/00 14/021 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
965491739-46130-DETAIL-10_26_2023-GUYHINS-3^668010/00 14/021 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
55123269-29979-DTLTRT-10_26_2023-GO95HV-1^668010/00 14/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
627139451-85530-DTLTRT-10_05_2023-GO95HV-1^668010/00 14/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
378546542-57769-DTLTRT-10_03_2023-GO95HV-1^668010/00 14/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
588874984-87840-DTLTRT-10_02_2023-GO95HV-1^668010/00 14/034 | OTHER | FHCA | Transmission | 2023-10-02 | 2028-10-02 | 3
588874984-87840-DTLTRT-10_02_2023-GO95MLD-1^668010/00 14/034 | OTHER | FHCA | Transmission | 2023-10-02 | 2028-10-02 | 3
713446664-81350-DTLTRT-11_03_2023-GO95HV-1^668010/00 14/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
859604145-59869-DTLTRT-10_10_2023-GO95HV-1^668010/00 14/037 | OTHER | FHCA | Transmission | 2023-10-10 | 2028-10-10 | 3
608576506-89169-DTLTRT-10_09_2023-GO95CL10-1^668010/00 14/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
608576506-89169-DTLTRT-10_09_2023-GO95MLD-1^668010/00 14/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
508668155-75269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 14/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
610112246-68560-DTLTRT-10_12_2023-GO95HV-1^668010/00 14/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
573251026-9069-DTLTRT-10_23_2023-GO95MLD-1^668010/00 14/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
325555928-94169-DTLTRT-10_11_2023-GO95HV-1^668010/00 14/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
325555928-94169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 14/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
66051028-28169-DTLTRT-10_10_2023-GO95HV-1^668010/00 14/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
342732473-73669-DTLTRT-10_16_2023-GO95HV-1^668010/00 15/002 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
360667163-89469-DTLTRT-09_26_2023-GO95MLD-1^668010/00 15/003 | OTHER | FHCA | Transmission | 2023-09-26 | 2026-09-26 | 2
618874754-67780-DTLTRT-09_26_2023-GO95HV-1^668010/00 15/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
274361883-82680-DTLTRT-09_27_2023-GO95HV-1^668010/00 15/006 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
274361883-82680-DTLTRT-09_27_2023-GUYNOINS-1^668010/00 15/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
274361883-82680-DTLTRT-09_27_2023-GUYNOINS-2^668010/00 15/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
274361883-82680-DTLTRT-09_27_2023-GUYNOINS-3^668010/00 15/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
153089721-43430-DTLTRT-10_30_2023-GO95HV-1^668010/00 15/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
621503174-13080-DTLTRT-10_31_2023-GO95HV-1^668010/00 15/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
128392835-87990-DTLTRT-10_31_2023-GO95HV-1^668010/00 15/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
704376146-34200-DTLTRT-11_01_2023-GO95HV-1^668010/00 15/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
253736939-53579-DTLTRT-10_19_2023-GO95MLD-1^668010/00 15/025 | OTHER | FHCA | Transmission | 2023-10-19 | 2026-10-19 | 2
612740571-84579-DTLTRT-10_05_2023-GO95HV-1^668010/00 15/027 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
42656361-19530-DTLTRT-10_05_2023-GO95HV-1^668010/00 15/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
42656361-19530-DTLTRT-10_05_2023-GO95MLD-1^668010/00 15/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
48774962-96340-DTLTRT-10_03_2023-GO95MLD-1^668010/00 15/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
4965955-10160-DTLTRT-10_09_2023-GO95HV-1^668010/00 15/037 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
337351086-79869-DTLTRT-10_09_2023-GO95MLD-1^668010/00 15/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
193102326-54779-DTLTRT-10_09_2023-GO95MLD-1^668010/00 15/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
193102326-54779-DTLTRT-10_09_2023-UBPBCTGD-1^668010/00 15/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
62650565-47669-DTLTRT-10_10_2023-GO95HV-1^668010/00 15/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
103416856-47069-DTLTRT-10_12_2023-GO95HV-1^668010/00 15/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
103416856-47069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 15/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
813837536-88069-DTLTRT-10_23_2023-GO95HV-1^668010/00 15/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
348689838-97169-DTLTRT-10_10_2023-GO95HV-1^668010/00 15/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
998279446-26260-DTLTRT-10_23_2023-GUYNOINS-1^668010/00 15A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
998279446-26260-DTLTRT-10_23_2023-GUYNOINS-2^668010/00 15A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
998279446-26260-DTLTRT-10_23_2023-GUYNOINS-3^668010/00 15A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
810428131-67570-DTLTRT-10_16_2023-GO95BLTC-1^668010/00 15X/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
810428131-67570-DTLTRT-10_16_2023-GO95MLD-1^668010/00 15X/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2026-10-16 | 2
65393783-62870-DTLTRT-09_26_2023-GO95MLD-1^668010/00 16/003 | OTHER | FHCA | Transmission | 2023-09-26 | 2026-09-26 | 2
261923164-26880-DTLTRT-09_26_2023-GO95HV-1^668010/00 16/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
920473993-5780-DTLTRT-09_27_2023-GO95HV-1^668010/00 16/006 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
203380454-88169-DTLTRT-10_17_2023-GO95MLD-1^668010/00 16/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
252453848-37730-DTLTRT-10_18_2023-GO95HV-1^668010/00 16/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
471774794-20280-DTLTRT-10_31_2023-GO95HV-1^668010/00 16/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
405358446-40390-DTLTRT-11_01_2023-GO95HV-1^668010/00 16/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
582999556-87200-DTLTRT-11_01_2023-GO95HV-1^668010/00 16/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
444050909-48530-DTLTRT-10_26_2023-GO95MLD-1^668010/00 16/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
444050909-48530-DTLTRT-10_26_2023-RISEGRD-1^668010/00 16/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
486265249-15879-DTLTRT-10_19_2023-GO95HV-1^668010/00 16/025 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
248587889-30430-DTLTRT-11_03_2023-GO95HV-1^668010/00 16/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
248587889-30430-DTLTRT-11_03_2023-UBPBXARM-1^668010/00 16/026 | CROSSARM | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
192566181-54030-DTLTRT-10_05_2023-GO95MLD-1^668010/00 16/027 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
808168371-65579-DTLTRT-10_05_2023-GO95HV-1^668010/00 16/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
413002572-47340-DTLTRT-10_03_2023-GO95HV-1^668010/00 16/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
429722294-73769-DTLTRT-11_03_2023-GO95HV-1^668010/00 16/036 | OTHER | FHCA | Transmission | 2023-11-03 | 2028-11-03 | 3
429722294-73769-DTLTRT-11_03_2023-GO95MLD-1^668010/00 16/036 | OTHER | FHCA | Transmission | 2023-11-03 | 2026-11-03 | 2
336121706-75160-DTLTRT-10_09_2023-GO95MLD-1^668010/00 16/038 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
550518575-62269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 16/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
891682866-18069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 16/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
766992346-58069-DTLTRT-10_25_2023-GO95MLD-1^668010/00 16/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2026-10-25 | 2
813480148-44169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 16/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
585217838-67169-DTLTRT-10_10_2023-GO95HV-1^668010/00 16/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
585217838-67169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 16/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
246779621-89670-DTLTRT-10_16_2023-GO95HV-1^668010/00 16X/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
925143064-580-DTLTRT-09_27_2023-GO95MLD-1^668010/00 16X/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-1^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-2^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-3^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-4^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-5^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
742865886-64890-DTLTRT-10_17_2023-GUYHINS-6^668010/00 16X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
214019768-47179-DTLTRT-10_17_2023-GO95HV-1^668010/00 16X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2028-10-17 | 3
214019768-47179-DTLTRT-10_17_2023-GO95STUB-1^668010/00 16X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
632937093-4970-DTLTRT-09_26_2023-GO95HV-1^668010/00 17/003 | OTHER | FHCA | Transmission | 2023-09-26 | 2028-09-26 | 3
265282474-55469-DTLTRT-09_26_2023-GO95MLD-1^668010/00 17/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
755437474-77580-DTLTRT-10_17_2023-GO95MLD-1^668010/00 17/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
814503346-81300-ADMIN-06_19_2024-POLEREPL-1^668010/00 17/010 | POLE | CA-TIER-2 | Transmission | 2024-06-19 | 2025-06-19 | 2
980844258-79730-DTLTRT-10_18_2023-GO95HV-1^668010/00 17/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
858119666-46300-DTLTRT-11_01_2023-GO95HV-1^668010/00 17/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
780547289-51900-DTLTRT-10_26_2023-GO95HV-1^668010/00 17/021 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
400279999-9869-DTLTRT-11_03_2023-GO95MLD-1^668010/00 17/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
788854981-25030-DTLTRT-10_05_2023-GO95HV-1^668010/00 17/027 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
636745389-11239-AUDIT-11_20_2023-GO95HV-1^668010/00 17/028 | OTHER | CA-TIER-2 | Transmission | 2023-11-20 | 2028-11-20 | 3
960517582-57340-DTLTRT-10_03_2023-GO95HV-1^668010/00 17/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
960517582-57340-DTLTRT-10_03_2023-GO95MLD-1^668010/00 17/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
484367544-12940-DTLTRT-10_02_2023-GRDRODHI-1^668010/00 17/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
834290834-50140-DTLTRT-10_02_2023-GO95BLTC-1^668010/00 17/034 | OTHER | FHCA | Transmission | 2023-10-02 | 2028-10-02 | 3
317150685-28260-DTLTRT-10_09_2023-GO95HV-1^668010/00 17/037 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
317150685-28260-DTLTRT-10_09_2023-GO95MLD-1^668010/00 17/037 | OTHER | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
180978656-65069-DTLTRT-10_23_2023-GO95HV-1^668010/00 17/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
709710348-37169-DTLTRT-10_10_2023-GO95HV-1^668010/00 17/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
356532509-5530-DTLTRT-11_03_2023-GO95MLD-1^668010/00 17A/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
924628801-97670-DTLTRT-10_16_2023-GO95HV-1^668010/00 17X/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
924628801-97670-DTLTRT-10_16_2023-GO95MLD-1^668010/00 17X/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2026-10-16 | 2
65793078-21430-DTLTRT-10_30_2023-GO95HV-1^668010/00 17X/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-30 | 2028-10-30 | 3
623734781-6779-DTLTRT-10_16_2023-GO95HV-1^668010/00 18/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
50506503-17779-DTLTRT-09_27_2023-GO95HV-1^668010/00 18/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
300480741-74979-DTLTRT-10_30_2023-GO95HV-1^668010/00 18/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
926664576-30400-DTLTRT-11_02_2023-GO95HV-1^668010/00 18/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
953151503-32840-DTLTRT-10_19_2023-GO95HV-1^668010/00 18/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
809811779-55879-DTLTRT-10_19_2023-ABNDEQPM-1^668010/00 18/025 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
21900619-5469-DTLTRT-11_03_2023-GO95MLD-1^668010/00 18/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
21900619-5469-DTLTRT-11_03_2023-UBPBCTGD-1^668010/00 18/026 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
922908111-28030-DTLTRT-10_05_2023-GO95MLD-1^668010/00 18/027 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
875045411-15930-DTLTRT-10_05_2023-GO95HV-1^668010/00 18/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
751995102-87340-DTLTRT-10_03_2023-GO95HV-1^668010/00 18/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
240665133-82540-DTLTRT-10_02_2023-GO95MLD-1^668010/00 18/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
415467954-66469-DTLTRT-10_02_2023-GO95MLD-1^668010/00 18/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
273322676-35069-DTLTRT-10_23_2023-GO95HV-1^668010/00 18/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
273322676-35069-DTLTRT-10_23_2023-GO95MLD-1^668010/00 18/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
273322676-35069-DTLTRT-10_23_2023-GUYHINS-1^668010/00 18/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
376242584-10820-DTLTRT-11_01_2023-GUYNOINS-1^668010/00 18A/017 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-01 | 2026-11-01 | 2
425119286-11060-DTLTRT-10_23_2023-GUYNOINS-1^668010/00 18A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
425119286-11060-DTLTRT-10_23_2023-GUYNOINS-2^668010/00 18A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
425119286-11060-DTLTRT-10_23_2023-GUYNOINS-3^668010/00 18A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
425119286-11060-DTLTRT-10_23_2023-GUYNOINS-4^668010/00 18A/042 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
250632834-56980-DTLTRT-09_27_2023-GO95MLD-1^668010/00 18X/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
586551626-27000-DTLTRT-10_17_2023-ABNDEQPM-1^668010/00 18X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
68044301-74769-DTLTRT-09_25_2023-GO95BLTC-1^668010/00 19/001 | OTHER | FHCA | Transmission | 2023-09-25 | 2028-09-25 | 3
68044301-74769-DTLTRT-09_25_2023-GO95MLD-1^668010/00 19/001 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-GUYHINS-1^668010/00 19/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-GUYHINS-2^668010/00 19/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-GUYHINS-3^668010/00 19/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-GUYHINS-4^668010/00 19/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
68044301-74769-DTLTRT-09_25_2023-SVCROAD-1^668010/00 19/001 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
480770414-2180-DTLTRT-09_26_2023-GO95HV-1^668010/00 19/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
415606353-37779-DTLTRT-09_27_2023-GO95HV-1^668010/00 19/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
410479685-80479-DTLTRT-11_01_2023-GO95HV-1^668010/00 19/017 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
598205686-62321-DTLTRT-11_01_2023-GO95HV-1^668010/00 19/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
565629076-24400-DTLTRT-11_02_2023-GO95HV-1^668010/00 19/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
222136384-15540-DTLTRT-10_04_2023-GO95HV-1^668010/00 19/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2028-10-04 | 3
63664801-29080-DTLTRT-09_27_2023-GO95MLD-1^668010/00 19X/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
361667406-60460-DTLTRT-10_09_2023-GUYNOINS-1^668010/00 1A/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
667571355-4090-DTLTRT-09_26_2023-GUYHINS-1^668010/00 1X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
667571355-4090-DTLTRT-09_26_2023-GUYHINS-2^668010/00 1X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
667571355-4090-DTLTRT-09_26_2023-GUYHINS-3^668010/00 1X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
180370408-37720-DTLTRT-10_17_2023-GO95HV-1^668010/00 1X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
180370408-37720-DTLTRT-10_17_2023-GO95MLD-1^668010/00 1X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
564695422-869-DTLTRT-09_26_2023-GO95MLD-1^668010/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
564695422-869-DTLTRT-09_26_2023-GO95STUB-1^668010/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
288600585-17190-DTLTRT-10_31_2023-GO95HV-1^668010/00 2/017 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
425969995-41479-DTLTRT-11_01_2023-GO95HV-1^668010/00 2/018 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
425982859-85830-DTLTRT-10_26_2023-GO95HV-1^668010/00 2/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
800854549-17630-DTLTRT-10_19_2023-GO95MLD-1^668010/00 2/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2026-10-19 | 2
656973429-26469-DTLTRT-10_19_2023-GO95HV-1^668010/00 2/026 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
658617539-92469-DTLTRT-11_03_2023-GO95HV-1^668010/00 2/027 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
63515461-58140-DTLTRT-10_05_2023-GO95HV-1^668010/00 2/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
63515461-58140-DTLTRT-10_05_2023-GO95MLD-1^668010/00 2/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
918090032-68340-DTLTRT-10_03_2023-GO95HV-1^668010/00 2/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
108459372-78579-DTLTRT-10_03_2023-GO95MLD-1^668010/00 2/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
530394763-13640-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
826206264-50140-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
826206264-50140-DTLTRT-10_02_2023-GRDRODHI-1^668010/00 2/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
158523173-6040-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/035 | OTHER | FHCA | Transmission | 2023-10-02 | 2028-10-02 | 3
158523173-6040-DTLTRT-10_02_2023-GO95MLD-1^668010/00 2/035 | OTHER | FHCA | Transmission | 2023-10-02 | 2026-10-02 | 2
880540605-72150-DTLTRT-11_03_2023-GO95HV-1^668010/00 2/037 | OTHER | FHCA | Transmission | 2023-11-03 | 2028-11-03 | 3
836783816-66460-DTLTRT-10_09_2023-GO95HV-1^668010/00 2/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
836783816-66460-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
836783816-66460-DTLTRT-10_09_2023-GUYHINS-1^668010/00 2/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
727934726-82260-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
727934726-82260-DTLTRT-10_09_2023-GUYHINS-1^668010/00 2/039 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
727934726-82260-DTLTRT-10_09_2023-GUYHINS-2^668010/00 2/039 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
659421095-91269-DTLTRT-10_10_2023-GO95HV-1^668010/00 2/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
659421095-91269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 2/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
659421095-91269-DTLTRT-10_10_2023-INSULDMG-1^668010/00 2/041 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
612218986-57069-DTLTRT-10_12_2023-GO95HV-1^668010/00 2/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
612218986-57069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 2/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
735109948-14169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 2/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
113029358-86169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 2/045 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
617226473-85179-DTLTRT-09_27_2023-GUYHINS-1^668010/00 20/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
617226473-85179-DTLTRT-09_27_2023-GUYHINS-2^668010/00 20/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
617226473-85179-DTLTRT-09_27_2023-GUYHINS-3^668010/00 20/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
153297724-96980-DTLTRT-09_27_2023-GUYNOINS-1^668010/00 20/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
153297724-96980-DTLTRT-09_27_2023-GUYNOINS-2^668010/00 20/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
153297724-96980-DTLTRT-09_27_2023-GUYNOINS-3^668010/00 20/006 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
200313884-99569-DTLTRT-10_17_2023-GO95HV-1^668010/00 20/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2028-10-17 | 3
200313884-99569-DTLTRT-10_17_2023-GO95MLD-1^668010/00 20/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
186054094-81640-DTLTRT-10_04_2023-GO95HV-1^668010/00 20/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2028-10-04 | 3
186054094-81640-DTLTRT-10_04_2023-GO95MLD-1^668010/00 20/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
321130656-4300-DTLTRT-10_24_2023-GUYHINS-1^668010/00 20X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
321130656-4300-DTLTRT-10_24_2023-GUYHINS-2^668010/00 20X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
321130656-4300-DTLTRT-10_24_2023-GUYHINS-3^668010/00 20X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
180077786-58869-DTLTRT-10_18_2023-GO95MLD-1^668010/00 21/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2026-10-18 | 2
180077786-58869-DTLTRT-10_18_2023-GRDRODHI-1^668010/00 21/010 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2026-10-18 | 2
903964079-73979-DTLTRT-10_30_2023-GO95HV-1^668010/00 21/013 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
416852571-38730-DTLTRT-10_30_2023-GO95HV-1^668010/00 21/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-30 | 2028-10-30 | 3
753125456-67979-DTLTRT-11_02_2023-GO95HV-1^668010/00 21/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
753125456-67979-DTLTRT-11_02_2023-GO95MLD-1^668010/00 21/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
753125456-67979-DTLTRT-11_02_2023-GRDRODHI-1^668010/00 21/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
603641516-8800-DTLTRT-10_17_2023-GO95HV-1^668010/00 21X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
27189926-4000-DTLTRT-10_17_2023-GO95HV-1^668010/00 22X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
27189926-4000-DTLTRT-10_17_2023-GUYHINS-1^668010/00 22X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
27189926-4000-DTLTRT-10_17_2023-GUYHINS-2^668010/00 22X/008 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
417966664-18780-DTLTRT-10_17_2023-GO95MLD-1^668010/00 23/007 | OTHER | CA-NON-TIER | Transmission | 2023-10-17 | 2026-10-17 | 2
466280629-57569-DTLTRT-10_25_2023-GO95BLTC-1^668010/00 23/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
466280629-57569-DTLTRT-10_25_2023-GO95MLD-1^668010/00 23/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2026-10-25 | 2
727116676-22400-DTLTRT-10_17_2023-GO95HV-1^668010/00 24X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
287040149-96130-DTLTRT-10_18_2023-GO95HV-1^668010/00 26/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
66370126-61560-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2A/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
909771188-78020-DTLTRT-10_17_2023-GO95MLD-1^668010/00 2X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
729339242-46170-DTLTRT-09_26_2023-GO95HV-1^668010/00 3/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
608718254-63980-DTLTRT-09_27_2023-GO95HV-1^668010/00 3/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
946303495-59190-DTLTRT-10_24_2023-GO95MLD-1^668010/00 3/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
477910389-12430-ADMIN-06_19_2024-POLEREPL-1^668010/00 3/012 | POLE | CA-TIER-2 | Transmission | 2024-06-19 | 2025-06-19 | 2
115282156-47300-DTLTRT-11_01_2023-GO95HV-1^668010/00 3/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
188645803-34179-DTLTRT-11_02_2023-GO95HV-1^668010/00 3/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
56170249-45630-DTLTRT-11_03_2023-GO95HV-1^668010/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
4049971-52240-DTLTRT-10_05_2023-GO95HV-1^668010/00 3/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
693679632-88340-DTLTRT-10_03_2023-GO95HV-1^668010/00 3/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
211927193-9579-DTLTRT-10_02_2023-GO95MLD-1^668010/00 3/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
405634836-93560-DTLTRT-10_09_2023-GO95HV-1^668010/00 3/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
405634836-93560-DTLTRT-10_09_2023-GO95MLD-1^668010/00 3/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
405634836-93560-DTLTRT-10_09_2023-GUYHINS-1^668010/00 3/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
888304764-24269-DTLTRT-10_11_2023-GO95MLD-1^668010/00 3/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
556894515-61269-DTLTRT-10_10_2023-GO95HV-1^668010/00 3/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
379660306-21169-DTLTRT-10_12_2023-GO95HV-1^668010/00 3/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2028-10-12 | 3
49277688-56169-DTLTRT-10_10_2023-GUYHINS-1^668010/00 3/045 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
868687563-50480-DTLTRT-09_25_2023-GUYNOINS-1^668010/00 3A/004 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
602709846-76560-DTLTRT-10_09_2023-GUYNOINS-1^668010/00 3A/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
602709846-76560-DTLTRT-10_09_2023-GUYNOINS-2^668010/00 3A/038 | ANCHOR/GUY | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
193263105-71290-DTLTRT-10_16_2023-GO95HV-1^668010/00 3X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
193263105-71290-DTLTRT-10_16_2023-GO95MLD-1^668010/00 3X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2026-10-16 | 2
193263105-71290-DTLTRT-10_16_2023-RISEGRD-1^668010/00 3X/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2026-10-16 | 2
452286508-62120-DTLTRT-10_17_2023-GO95HV-1^668010/00 3X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
685345601-4469-DTLTRT-09_25_2023-GUYHINS-1^668010/00 4/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
685345601-4469-DTLTRT-09_25_2023-GUYHINS-2^668010/00 4/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
685345601-4469-DTLTRT-09_25_2023-GUYHINS-3^668010/00 4/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
124521753-67270-DTLTRT-09_26_2023-GO95HV-1^668010/00 4/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
126277464-71080-DTLTRT-09_27_2023-GO95MLD-1^668010/00 4/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
426097037-95720-DTLTRT-10_24_2023-GO95HV-1^668010/00 4/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
196028399-93430-DTLTRT-10_18_2023-GO95HV-1^668010/00 4/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
122641518-24120-DTLTRT-11_02_2023-GO95HV-1^668010/00 4/020 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
411134088-85430-DTLTRT-11_02_2023-GO95HV-1^668010/00 4/021 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
669753789-6930-DTLTRT-10_26_2023-GO95HV-1^668010/00 4/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
669753789-6930-DTLTRT-10_26_2023-GO95MLD-1^668010/00 4/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
669753789-6930-DTLTRT-10_26_2023-RISEGRD-1^668010/00 4/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2026-10-26 | 2
928199969-42730-DTLTRT-10_19_2023-GO95HV-1^668010/00 4/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
99537359-79630-DTLTRT-11_03_2023-GO95HV-1^668010/00 4/027 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2028-11-03 | 3
99537359-79630-DTLTRT-11_03_2023-GO95MLD-1^668010/00 4/027 | OTHER | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
945459481-37240-DTLTRT-10_05_2023-GO95HV-1^668010/00 4/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
945459481-37240-DTLTRT-10_05_2023-GO95MLD-1^668010/00 4/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
106479642-39340-DTLTRT-10_03_2023-GO95HV-1^668010/00 4/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
59036723-89840-AUDIT-11_16_2023-GO95CN-1^668010/00 4/032 | OTHER | CA-TIER-2 | Transmission | 2023-11-16 | 2026-11-16 | 2
388615603-84569-DTLTRT-10_02_2023-GO95BLTC-1^668010/00 4/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
388615603-84569-DTLTRT-10_02_2023-GO95HV-1^668010/00 4/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
388615603-84569-DTLTRT-10_02_2023-RISEGRD-1^668010/00 4/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
494481684-20240-DTLTRT-10_02_2023-GO95HV-1^668010/00 4/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
642130396-72360-DTLTRT-10_09_2023-GO95HV-1^668010/00 4/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
642130396-72360-DTLTRT-10_09_2023-GO95MLD-1^668010/00 4/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
162109935-31269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 4/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
250644526-42169-DTLTRT-10_23_2023-GO95HV-1^668010/00 4/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
250644526-42169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 4/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
2550968-83169-DTLTRT-10_11_2023-GO95HV-1^668010/00 4/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
2550968-83169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 4/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
120980001-51970-DTLTRT-09_25_2023-GUYNOINS-1^668010/00 4A/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
120980001-51970-DTLTRT-09_25_2023-GUYNOINS-2^668010/00 4A/001 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
320642394-17150-DTLTRT-10_04_2023-GO95MLD-1^668010/00 4A/036 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
320642394-17150-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 4A/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
320642394-17150-DTLTRT-10_04_2023-GUYNOINS-2^668010/00 4A/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
320642394-17150-DTLTRT-10_04_2023-GUYNOINS-3^668010/00 4A/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
405037321-27469-DTLTRT-09_25_2023-GO95MLD-1^668010/00 5/001 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
405037321-27469-DTLTRT-09_25_2023-GRDRODHI-1^668010/00 5/001 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
405037321-27469-DTLTRT-09_25_2023-GRDRODHI-2^668010/00 5/001 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
405037321-27469-DTLTRT-09_25_2023-GRDRODHI-3^668010/00 5/001 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
405037321-27469-DTLTRT-09_25_2023-GRDRODHI-4^668010/00 5/001 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
572941493-22209-DTLTRT-09_25_2023-GO95HV-1^668010/00 5/003 | OTHER | FHCA | Transmission | 2023-09-25 | 2028-09-25 | 3
572941493-22209-DTLTRT-09_25_2023-GUYHINS-1^668010/00 5/003 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
572941493-22209-DTLTRT-09_25_2023-GUYHINS-2^668010/00 5/003 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
572941493-22209-DTLTRT-09_25_2023-GUYHINS-3^668010/00 5/003 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
630378283-98869-DTLTRT-09_25_2023-ANCHIDLE-1^668010/00 5/004 | ANCHOR/GUY | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
630378283-98869-DTLTRT-09_25_2023-GO95MLD-1^668010/00 5/004 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
630378283-98869-DTLTRT-09_25_2023-GO95TCH-1^668010/00 5/004 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
512100119-4030-DTLTRT-10_25_2023-GO95HV-1^668010/00 5/013 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
762624894-93090-DTLTRT-10_31_2023-GO95HV-1^668010/00 5/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
309191928-56800-DTLTRT-11_02_2023-GUYHINS-1^668010/00 5/020 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
309191928-56800-DTLTRT-11_02_2023-GUYHINS-2^668010/00 5/020 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
309191928-56800-DTLTRT-11_02_2023-GUYHINS-3^668010/00 5/020 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
473294059-13730-DTLTRT-10_26_2023-GO95HV-1^668010/00 5/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
620509399-1579-DTLTRT-10_26_2023-GO95MLD-1^668010/00 5/023 | OTHER | FHCA | Transmission | 2023-10-26 | 2026-10-26 | 2
889136179-32579-DTLTRT-10_19_2023-GO95HV-1^668010/00 5/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
981374259-99769-DTLTRT-10_19_2023-GO95HV-1^668010/00 5/026 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
981374259-99769-DTLTRT-10_19_2023-GO95MLD-1^668010/00 5/026 | OTHER | FHCA | Transmission | 2023-10-19 | 2026-10-19 | 2
876629679-54579-DTLTRT-11_02_2023-GO95MLD-1^668010/00 5/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
784289501-18730-DTLTRT-10_04_2023-GO95HV-1^668010/00 5/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2028-10-04 | 3
784289501-18730-DTLTRT-10_04_2023-GO95MLD-1^668010/00 5/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
478742443-54879-DTLTRT-10_03_2023-GO95MLD-1^668010/00 5/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
478742443-54879-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 5/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
21313983-29579-DTLTRT-10_02_2023-GO95HV-1^668010/00 5/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
170451253-29669-DTLTRT-10_04_2023-GO95BLTC-1^668010/00 5/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2028-10-04 | 3
170451253-29669-DTLTRT-10_04_2023-GO95MLD-1^668010/00 5/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
190819614-1450-DTLTRT-11_03_2023-GO95HV-1^668010/00 5/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
393995066-63660-DTLTRT-10_09_2023-GO95HV-1^668010/00 5/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
393995066-63660-DTLTRT-10_09_2023-GO95MLD-1^668010/00 5/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
458520984-14269-DTLTRT-10_11_2023-GO95HV-1^668010/00 5/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
458520984-14269-DTLTRT-10_11_2023-GO95MLD-1^668010/00 5/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
743671136-22169-DTLTRT-10_23_2023-GO95HV-1^668010/00 5/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
805075068-16169-DTLTRT-10_11_2023-GO95HV-1^668010/00 5/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
106456795-26590-DTLTRT-09_27_2023-RISEGRD-1^668010/00 5X/008 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
438039618-35120-DTLTRT-10_17_2023-GUYHINS-1^668010/00 5X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
438039618-35120-DTLTRT-10_17_2023-GUYHINS-2^668010/00 5X/009 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-17 | 2026-10-17 | 2
562888512-37750-DTLTRT-09_25_2023-GO95HV-1^668010/00 6/002 | OTHER | FHCA | Transmission | 2023-09-25 | 2028-09-25 | 3
562888512-37750-DTLTRT-09_25_2023-GO95MLD-1^668010/00 6/002 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
562888512-37750-DTLTRT-09_25_2023-GRDRODHI-1^668010/00 6/002 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
332794423-50970-DTLTRT-09_25_2023-GO95HV-1^668010/00 6/003 | OTHER | FHCA | Transmission | 2023-09-25 | 2028-09-25 | 3
271437193-15569-DTLTRT-09_26_2023-GO95HV-1^668010/00 6/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
271437193-15569-DTLTRT-09_26_2023-GO95MLD-1^668010/00 6/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2026-09-26 | 2
422398605-18079-DTLTRT-10_24_2023-GO95MLD-1^668010/00 6/008 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2026-10-24 | 2
784749416-31990-DTLTRT-11_01_2023-GO95MLD-1^668010/00 6/010 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2026-11-01 | 2
144252176-31500-DTLTRT-11_01_2023-GO95HV-1^668010/00 6/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
343757879-44830-DTLTRT-10_26_2023-GO95HV-1^668010/00 6/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
21572199-830-DTLTRT-10_19_2023-GO95HV-1^668010/00 6/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
210848343-52540-DTLTRT-10_05_2023-GO95MLD-1^668010/00 6/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
264249911-14930-DTLTRT-10_03_2023-GO95HV-1^668010/00 6/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
779773513-49579-DTLTRT-10_02_2023-GO95HV-1^668010/00 6/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
779773513-49579-DTLTRT-10_02_2023-GO95MLD-1^668010/00 6/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
79694563-75440-DTLTRT-10_04_2023-GO95HV-1^668010/00 6/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2028-10-04 | 3
79694563-75440-DTLTRT-10_04_2023-GO95MLD-1^668010/00 6/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
694413976-57179-DTLTRT-10_09_2023-GO95HV-1^668010/00 6/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2028-10-09 | 3
577210816-29360-DTLTRT-10_09_2023-GO95HV-1^668010/00 6/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
441753055-25269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 6/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
441753055-25269-DTLTRT-10_10_2023-GUYHINS-1^668010/00 6/041 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
376473136-80169-DTLTRT-10_12_2023-GO95MLD-1^668010/00 6/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
680424536-91169-DTLTRT-10_23_2023-GO95HV-1^668010/00 6/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
680424536-91169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 6/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
543919678-95169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 6/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
543919678-95169-DTLTRT-10_11_2023-GRDRODHI-1^668010/00 6/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
385597165-63160-DTLTRT-11_03_2023-GUYNOINS-1^668010/00 6A/041 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-11-03 | 2026-11-03 | 2
196963848-44220-DTLTRT-10_17_2023-GO95HV-1^668010/00 6X/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
351253541-17270-AUDIT-11_10_2023-GO95HV-1^668010/00 7/001 | OTHER | FHCA | Transmission | 2023-11-10 | 2028-11-10 | 3
8616422-26379-DTLTRT-09_25_2023-GO95MLD-1^668010/00 7/002 | OTHER | FHCA | Transmission | 2023-09-25 | 2026-09-25 | 2
422741214-47280-DTLTRT-09_27_2023-GO95MLD-1^668010/00 7/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
626741686-8500-DTLTRT-11_01_2023-GO95HV-1^668010/00 7/019 | OTHER | CA-TIER-2 | Transmission | 2023-11-01 | 2028-11-01 | 3
16219169-52330-DTLTRT-11_02_2023-GO95HV-1^668010/00 7/025 | OTHER | FHCA | Transmission | 2023-11-02 | 2028-11-02 | 3
601415679-63930-DTLTRT-10_19_2023-GO95MLD-1^668010/00 7/026 | OTHER | FHCA | Transmission | 2023-10-19 | 2026-10-19 | 2
24238730-61830-DTLTRT-11_03_2023-GO95HV-1^668010/00 7/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
160219841-77530-DTLTRT-10_05_2023-GO95HV-1^668010/00 7/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2028-10-05 | 3
160219841-77530-DTLTRT-10_05_2023-GO95MLD-1^668010/00 7/028 | OTHER | CA-TIER-2 | Transmission | 2023-10-05 | 2026-10-05 | 2
488321221-37579-DTLTRT-10_03_2023-GUYHINS-1^668010/00 7/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
511657662-90440-DTLTRT-10_03_2023-GO95HV-1^668010/00 7/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
511657662-90440-DTLTRT-10_03_2023-GO95MLD-1^668010/00 7/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
291173-63040-DTLTRT-10_03_2023-GO95HV-1^668010/00 7/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
291173-63040-DTLTRT-10_03_2023-GO95MLD-1^668010/00 7/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
90730026-10460-DTLTRT-10_09_2023-GO95MLD-1^668010/00 7/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
701638575-94269-DTLTRT-10_10_2023-GUYHINS-1^668010/00 7/041 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
546150346-71169-DTLTRT-10_23_2023-GO95HV-1^668010/00 7/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
955420331-6040-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 7A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
955420331-6040-DTLTRT-10_03_2023-GUYNOINS-2^668010/00 7A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
989712101-470-DTLTRT-10_16_2023-GO95HV-1^668010/00 8/001 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
745205933-91321-DTLTRT-09_26_2023-GO95HV-1^668010/00 8/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
307611124-11480-DTLTRT-09_27_2023-GO95MLD-1^668010/00 8/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
663013867-87620-DTLTRT-10_24_2023-GO95HV-1^668010/00 8/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
625419245-21390-DTLTRT-10_31_2023-GO95HV-1^668010/00 8/017 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
846583268-49800-DETAIL-11_02_2023-GUYHINS-1^668010/00 8/020 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-02 | 2026-11-02 | 2
494220799-28979-DTLTRT-10_26_2023-GO95HV-1^668010/00 8/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
650234950-71830-DTLTRT-11_03_2023-GO95HV-1^668010/00 8/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
650234950-71830-DTLTRT-11_03_2023-GO95MLD-1^668010/00 8/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
650234950-71830-DTLTRT-11_03_2023-GRDRODHI-1^668010/00 8/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
367169863-59540-DTLTRT-10_04_2023-GO95HV-1^668010/00 8/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2028-10-04 | 3
367169863-59540-DTLTRT-10_04_2023-GO95MLD-1^668010/00 8/029 | OTHER | CA-TIER-2 | Transmission | 2023-10-04 | 2026-10-04 | 2
746638341-97040-DTLTRT-10_03_2023-GO95HV-1^668010/00 8/030 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
746638341-97040-DTLTRT-10_03_2023-GUYHINS-1^668010/00 8/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
578475572-87579-DTLTRT-10_03_2023-GO95HV-1^668010/00 8/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-03 | 2028-10-03 | 3
883116734-80679-DTLTRT-10_02_2023-SVCROAD-1^668010/00 8/034 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2026-10-02 | 2
883116734-80679-ADMIN-07_12_2024-POLEREPL-1^668010/00 8/034 | POLE | CA-TIER-2 | Transmission | 2024-07-12 | 2025-07-12 | 2
281130504-59269-DTLTRT-10_04_2023-GO95HV-1^668010/00 8/035 | OTHER | FHCA | Transmission | 2023-10-04 | 2028-10-04 | 3
982169336-65460-DTLTRT-10_09_2023-GO95HV-1^668010/00 8/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
706197814-3269-ADMIN-10_11_2023-GO95MLD-1^668010/00 8/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
732020895-74269-DTLTRT-10_10_2023-GO95HV-1^668010/00 8/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2028-10-10 | 3
732020895-74269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 8/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
785883256-30169-DTLTRT-10_12_2023-GO95MLD-1^668010/00 8/042 | OTHER | CA-NON-TIER | Transmission | 2023-10-12 | 2026-10-12 | 2
944538756-51169-DTLTRT-10_11_2023-GO95HV-1^668010/00 8/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
944538756-51169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 8/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
944538756-51169-DTLTRT-10_11_2023-GUYHINS-1^668010/00 8/043 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
943118403-22140-DTLTRT-10_19_2023-GO95HV-1^668010/00 8A/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2028-10-19 | 3
943118403-22140-DTLTRT-10_19_2023-GO95MLD-1^668010/00 8A/024 | OTHER | FHCA | Transmission | 2023-10-19 | 2026-10-19 | 2
776719151-60140-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 8A/030 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-03 | 2026-10-03 | 2
368861862-29769-DTLTRT-10_16_2023-GO95HV-1^668010/00 9/002 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
930679463-67421-DTLTRT-09_26_2023-GO95MLD-1^668010/00 9/003 | OTHER | FHCA | Transmission | 2023-09-26 | 2026-09-26 | 2
229547814-18880-DTLTRT-09_25_2023-GO95HV-1^668010/00 9/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2028-09-25 | 3
229547814-18880-DTLTRT-09_25_2023-GO95MLD-1^668010/00 9/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2026-09-25 | 2
124332333-76280-DTLTRT-09_27_2023-GO95HV-1^668010/00 9/006 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2028-09-27 | 3
342560234-42580-DTLTRT-09_27_2023-GO95MLD-1^668010/00 9/007 | OTHER | CA-TIER-2 | Transmission | 2023-09-27 | 2026-09-27 | 2
125096477-44879-DTLTRT-10_24_2023-GO95HV-1^668010/00 9/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-24 | 2028-10-24 | 3
460738598-98430-DTLTRT-10_18_2023-GO95HV-1^668010/00 9/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
460738598-98430-DTLTRT-10_18_2023-GO95MLD-1^668010/00 9/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2026-10-18 | 2
150653365-98790-DTLTRT-10_31_2023-GO95HV-1^668010/00 9/016 | OTHER | CA-TIER-2 | Transmission | 2023-10-31 | 2028-10-31 | 3
369253856-33479-DTLTRT-11_01_2023-GUYHINS-1^668010/00 9/018 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-01 | 2026-11-01 | 2
604489309-15030-DTLTRT-10_26_2023-GO95HV-1^668010/00 9/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
673825139-10230-DTLTRT-11_02_2023-GO95HV-1^668010/00 9/023 | OTHER | CA-TIER-2 | Transmission | 2023-11-02 | 2028-11-02 | 3
427078643-94340-DTLTRT-10_02_2023-GO95HV-1^668010/00 9/033 | OTHER | CA-TIER-2 | Transmission | 2023-10-02 | 2028-10-02 | 3
170577034-10940-DTLTRT-10_04_2023-GUYHINS-1^668010/00 9/035 | ANCHOR/GUY | FHCA | Transmission | 2023-10-04 | 2026-10-04 | 2
105023984-46850-DETAIL-11_03_2023-GUYHINS-1^668010/00 9/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
105023984-46850-DETAIL-11_03_2023-GUYHINS-2^668010/00 9/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
105023984-46850-DETAIL-11_03_2023-GUYHINS-3^668010/00 9/036 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-11-03 | 2026-11-03 | 2
309340196-1860-DTLTRT-10_09_2023-GO95MLD-1^668010/00 9/038 | OTHER | FHCA | Transmission | 2023-10-09 | 2026-10-09 | 2
607730256-11269-DTLTRT-10_09_2023-GO95HV-1^668010/00 9/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2028-10-09 | 3
607730256-11269-DTLTRT-10_09_2023-GO95MLD-1^668010/00 9/039 | OTHER | CA-NON-TIER | Transmission | 2023-10-09 | 2026-10-09 | 2
49478444-96150-DTLTRT-10_11_2023-GO95HV-1^668010/00 9/040 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
49478444-96150-DTLTRT-10_11_2023-GUYHINS-1^668010/00 9/040 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-11 | 2026-10-11 | 2
54203595-44269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 9/041 | OTHER | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-1^668010/00 9/041 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-2^668010/00 9/041 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-3^668010/00 9/041 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2023-10-10 | 2026-10-10 | 2
658178398-7069-DTLTRT-10_11_2023-GO95HV-1^668010/00 9/043 | OTHER | CA-NON-TIER | Transmission | 2023-10-11 | 2028-10-11 | 3
978055818-25169-DTLTRT-10_23_2023-GO95HV-1^668010/00 9/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2028-10-23 | 3
978055818-25169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 9/044 | OTHER | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
978055818-25169-DTLTRT-10_23_2023-UBPBXARM-1^668010/00 9/044 | CROSSARM | CA-NON-TIER | Transmission | 2023-10-23 | 2026-10-23 | 2
838686523-47140-DTLTRT-10_19_2023-GUYNOINS-1^668010/00 9A/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-10-19 | 2026-10-19 | 2
868454798-63114-DETAIL-05_26_2022-GO95HV-1^668018/00 11/003 | OTHER | CA-TIER-2 | Transmission | 2022-05-26 | 2027-05-26 | 3
868454798-67594-DETAIL-05_26_2022-GO95HV-1^668018/00 11/003 | OTHER | CA-TIER-2 | Transmission | 2022-05-26 | 2027-05-26 | 3
881115190-29669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 1/012 | OTHER | CA-TIER-2 | Transmission | 2023-10-11 | 2028-10-11 | 3
260380185-90869-ADMIN-09_20_2024-XARMSPCR-1^668033/00 1/041 | CROSSARM | CA-TIER-2 | Transmission | 2024-09-20 | 2025-09-20 | 2
224883036-3131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
224883036-33131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
224883036-5960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
378850066-24880-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
378850066-29060-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
378850066-53880-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
156252576-83540-DRONE_HY-10_25_2023-GO95HV-1^668033/00 10/001 | OTHER | CA-TIER-2 | Transmission | 2023-10-25 | 2028-10-25 | 3
524825426-92279-DRONE_HY-09_26_2023-GO95HV-1^668033/00 10/002 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
524825426-92279-DRONE_HY-10_16_2023-GO95HV-1^668033/00 10/002 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
813037370-38669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 10/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-11 | 2028-10-11 | 3
296134458-34279-DRONE_HY-09_28_2023-GO95HV-1^668033/00 11/004 | OTHER | CA-TIER-2 | Transmission | 2023-09-28 | 2028-09-28 | 3
964343990-98669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 12/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-11 | 2028-10-11 | 3
581161579-17430-DRONE_HY-11_03_2023-GO95HV-1^668033/00 12/028 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
876113328-31428-DRONE_HY-10_16_2023-GO95HV-1^668033/00 13/003 | OTHER | FHCA | Transmission | 2023-10-16 | 2028-10-16 | 3
855452743-91272-DRONE_HY-09_28_2023-GO95HV-1^668033/00 13X1/004 | OTHER | FHCA | Transmission | 2023-09-28 | 2028-09-28 | 3
59934178-36869-DRONE_HY-09_29_2023-GO95HV-1^668033/00 14/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-29 | 2028-09-29 | 3
90384273-83649-DRONE_HY-10_17_2023-GO95HV-1^668033/00 14/037 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
474687708-67760-DRONE_HY-10_18_2023-GO95HV-1^668033/00 15/004 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
575191478-40070-DRONE_HY-09_28_2023-GO95HV-1^668033/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-28 | 2028-09-28 | 3
681354739-15379-DRONE_HY-10_16_2023-GO95HV-1^668033/00 2/009 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
947024173-32049-DRONE_HY-11_07_2023-GO95HV-1^668033/00 2/036 | OTHER | CA-TIER-2 | Transmission | 2023-11-07 | 2028-11-07 | 3
115043395-47570-ADMIN-09_20_2024-CUTOUTAR-1^668033/00 2/040 | LIGHTNING ARRESTER | CA-TIER-2 | Transmission | 2024-09-20 | 2025-09-20 | 2
541618446-22331-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
541618446-72331-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
541618446-77960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
16689319-91415-DRONE_HY-11_03_2023-GO95HV-1^668033/00 2X/027 | OTHER | CA-TIER-2 | Transmission | 2023-11-03 | 2028-11-03 | 3
222965188-5279-DRONE_HY-09_29_2023-GO95HV-1^668033/00 3/005 | OTHER | CA-TIER-2 | Transmission | 2023-09-29 | 2028-09-29 | 3
532543651-20569-DRONE_HY-10_13_2023-GO95HV-1^668033/00 3/015 | OTHER | CA-TIER-2 | Transmission | 2023-10-13 | 2028-10-13 | 3
421127660-35930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 3/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
344856405-18570-DRONE_HY-10_18_2023-ABNDEQPM-1^668033/00 3/042 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
679514901-65569-DRONE_HY-10_06_2023-GO95HV-1^668033/00 4/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-06 | 2028-10-06 | 3
679514901-75570-DRONE_HY-10_06_2023-GO95HV-1^668033/00 4/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-06 | 2028-10-06 | 3
621985754-2980-DRONE_HY-10_18_2023-GO95HV-1^668033/00 4/022 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
689443434-26280-DRONE_HY-10_18_2023-GO95HV-1^668033/00 4/023 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
606249279-93330-DRONE_HY-11_13_2023-GO95HV-1^668033/00 4/030 | OTHER | CA-TIER-2 | Transmission | 2023-11-13 | 2028-11-13 | 3
863978670-27930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 4/031 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
626571-56730-DRONE_HY-10_26_2023-GO95HV-1^668033/00 4/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
520611664-29040-DRONE_HY-10_27_2023-GO95HV-1^668033/00 4/037 | OTHER | CA-TIER-2 | Transmission | 2023-10-27 | 2028-10-27 | 3
785734006-34931-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
785734006-63931-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
785734006-91860-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
149372389-769-ADMIN-08_02_2024-POLEREPL-1^668033/00 5/010 | POLE | CA-TIER-2 | Transmission | 2024-08-02 | 2025-08-02 | 2
726458001-35569-DRONE_HY-10_06_2023-GO95HV-1^668033/00 5/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-06 | 2028-10-06 | 3
726458001-35570-DRONE_HY-10_06_2023-GO95HV-1^668033/00 5/014 | OTHER | CA-TIER-2 | Transmission | 2023-10-06 | 2028-10-06 | 3
612491893-2369-DRONE_HY-11_15_2023-GO95HV-1^668033/00 5/035 | OTHER | CA-TIER-2 | Transmission | 2023-11-15 | 2028-11-15 | 3
266529476-10909-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/044 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
266529476-68131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/044 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
516804006-32231-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
516804006-53860-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
550542026-82080-DRONE_HY-11_10_2023-GO95HV-1^668033/00 5/048 | OTHER | CA-TIER-2 | Transmission | 2023-11-10 | 2028-11-10 | 3
550542026-83080-DRONE_HY-11_10_2023-GO95HV-1^668033/00 5/048 | OTHER | CA-TIER-2 | Transmission | 2023-11-10 | 2028-11-10 | 3
546491123-34005-DRONE_HY-09_27_2023-GO95HV-1^668033/00 5X1/003 | OTHER | FHCA | Transmission | 2023-09-27 | 2028-09-27 | 3
150347940-64669-DRONE_HY-10_18_2023-GO95HV-1^668033/00 6/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
150347940-64670-DRONE_HY-10_18_2023-GO95HV-1^668033/00 6/011 | OTHER | CA-TIER-2 | Transmission | 2023-10-18 | 2028-10-18 | 3
56941126-43531-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
56941126-91960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
56941126-93531-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
640983933-66161-DRONE_HY-09_26_2023-GO95HV-1^668033/00 7X1/002 | OTHER | FHCA | Transmission | 2023-09-26 | 2028-09-26 | 3
907647633-21692-DRONE_HY-09_27_2023-GO95HV-1^668033/00 7X1/003 | OTHER | FHCA | Transmission | 2023-09-27 | 2028-09-27 | 3
110359745-22869-DRONE_HY-10_17_2023-GO95HV-1^668033/00 8/040 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
963322925-57350-ADMIN-09_20_2024-XARMSPCR-1^668033/00 8/041 | CROSSARM | CA-TIER-2 | Transmission | 2024-09-20 | 2025-09-20 | 2
942001116-52279-DRONE_HY-09_26_2023-GO95HV-1^668033/00 9/002 | OTHER | CA-TIER-2 | Transmission | 2023-09-26 | 2028-09-26 | 3
688257588-77260-DRONE_HY-10_16_2023-GO95HV-1^668033/00 9/003 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
281183823-2970-DRONE_HY-10_10_2023-GO95HV-1^668033/00 9/018 | OTHER | CA-TIER-2 | Transmission | 2023-10-10 | 2028-10-10 | 3
299499755-81869-DRONE_HY-10_17_2023-GO95HV-1^668033/00 9/040 | OTHER | CA-TIER-2 | Transmission | 2023-10-17 | 2028-10-17 | 3
734349136-49920-DRONE_HY-10_12_2023-GO95HV-1^668033/00 9/043 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
734349136-92560-DRONE_HY-10_12_2023-GO95HV-1^668033/00 9/043 | OTHER | CA-TIER-2 | Transmission | 2023-10-12 | 2028-10-12 | 3
476848521-28930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 9A/032 | OTHER | CA-TIER-2 | Transmission | 2023-10-26 | 2028-10-26 | 3
944345905-21950-DRONE_HY-10_16_2023-GO95HV-1^668033/01 17/003 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
20828535-50-DRONE_HY-10_16_2023-GO95HV-1^668033/01 19/003 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
818513284-90150-DRONE_HY-10_16_2023-GO95HV-1^668033/01 20/002 | OTHER | CA-TIER-2 | Transmission | 2023-10-16 | 2028-10-16 | 3
197639346-31269-ENHANCED-06_30_2024-IRSPOTOH-1^668047/00 11/031 | OTHER | CA-TIER-2 | Transmission | 2024-06-30 | 2025-06-30 | 2
197639346-31270-ENHANCED-06_30_2024-IRSPOTOH-1^668047/00 11/031 | OTHER | CA-TIER-2 | Transmission | 2024-06-30 | 2025-06-30 | 2
821595223-34560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/004 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
821595223-4560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/004 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
821595223-90500-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/004 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
632792504-89560-DTLTRT-04_08_2024-GO95HV-1^668062/00 1/006 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
632792504-89560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
632792504-93753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
704235763-653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 2/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-09 | 2027-04-09 | 2
712638323-61753-DTLTRT-04_08_2024-GO95HV-1^668062/00 2/004 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
712638323-74560-DTLTRT-04_08_2024-GO95HV-1^668062/00 2/004 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
712638323-61753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/004 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
353298674-47560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
353298674-77560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
438162054-57680-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/007 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
438162054-76680-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/007 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
438162054-86753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/007 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
910421873-50653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 3/001 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-09 | 2027-04-09 | 2
670648283-18653-DTLTRT-04_09_2024-GO95HV-1^668062/00 3/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-09 | 2029-04-09 | 3
670648283-3560-DTLTRT-04_09_2024-GO95HV-1^668062/00 3/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-09 | 2029-04-09 | 3
670648283-72560-DTLTRT-04_09_2024-GO95HV-1^668062/00 3/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-09 | 2029-04-09 | 3
670648283-3560-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 3/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-09 | 2027-04-09 | 2
670648283-72560-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 3/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-09 | 2027-04-09 | 2
350115474-38560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 3/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
350115474-43753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 3/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
350115474-8560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 3/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
829047883-33560-DTLTRT-04_09_2024-GO95HV-1^668062/00 4/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-09 | 2029-04-09 | 3
829047883-63560-DTLTRT-04_09_2024-GO95HV-1^668062/00 4/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-09 | 2029-04-09 | 3
829047883-78653-DTLTRT-04_09_2024-GO95HV-1^668062/00 4/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-09 | 2029-04-09 | 3
829047883-33560-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 4/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-09 | 2027-04-09 | 2
829047883-63560-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 4/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-09 | 2027-04-09 | 2
829047883-78653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 4/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-09 | 2027-04-09 | 2
931890384-73753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 4/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
931890384-78560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 4/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
931890384-9560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 4/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
649534924-1660-DTLTRT-04_08_2024-GO95HV-1^668062/00 4/006 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
75916933-75560-DTLTRT-04_08_2024-POLETOP-1^668062/00 5/004 | POLE | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
980669484-39560-DETAIL-04_08_2024-ANCHIDLE-1^668062/00 5/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
980669484-39560-DETAIL-04_08_2024-GO95HV-1^668062/00 5/005 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
980669484-93753-DETAIL-04_08_2024-GO95HV-1^668062/00 5/005 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
660006134-6753-DTLTRT-04_08_2024-GO95HV-1^668062/00 5/006 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
660006134-73660-DTLTRT-04_08_2024-GO95HV-1^668062/00 5/006 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
660006134-73660-DTLTRT-04_08_2024-INSULBRK-1^668062/00 5/006 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
104264293-51653-DTLTRT-04_09_2024-GO95HV-1^668062/00 6/001 | OTHER | CA-TIER-2 | Transmission | 2024-04-09 | 2029-04-09 | 3
322109934-13660-DTLTRT-04_08_2024-GO95HV-1^668062/00 6/006 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
322109934-26753-DTLTRT-04_08_2024-GO95HV-1^668062/00 6/006 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
322109934-13660-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 6/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
322109934-26753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 6/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-08 | 2027-04-08 | 2
574554803-71653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 7/001 | ANCHOR/GUY | FHCA | Transmission | 2024-04-09 | 2027-04-09 | 2
593773553-75653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 7/002 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-09 | 2027-04-09 | 2
629128444-72660-DTLTRT-04_08_2024-GO95HV-1^668062/00 7/006 | OTHER | CA-NON-TIER | Transmission | 2024-04-08 | 2029-04-08 | 3
720777351-4391-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-10 | 2029-04-10 | 3
720777351-5391-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-10 | 2029-04-10 | 3
720777351-65180-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | CA-NON-TIER | Transmission | 2024-04-10 | 2029-04-10 | 3
720777351-4391-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 1/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-10 | 2027-04-10 | 2
720777351-5391-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 1/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-10 | 2027-04-10 | 2
720777351-65180-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 1/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-10 | 2027-04-10 | 2
743523991-53791-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/004 | OTHER | CA-NON-TIER | Transmission | 2024-04-10 | 2029-04-10 | 3
988215071-36891-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
988215071-49469-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
988215071-5891-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
396695053-13811-DTLTRT-04_16_2024-GO95HV-1^668067/00 1/013 | OTHER | CA-NON-TIER | Transmission | 2024-04-16 | 2029-04-16 | 3
566629774-13329-DTLTRT-04_16_2024-XARMSPCR-1^668067/00 1/016 | CROSSARM | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
566629774-13329-ADMIN-07_16_2024-POLEREPL-1^668067/00 1/016 | POLE | CA-NON-TIER | Transmission | 2024-07-16 | 2027-07-16 | 2
283021148-42171-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 1/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-04 | 2027-04-04 | 2
283021148-57520-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 1/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-04 | 2027-04-04 | 2
283021148-81171-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 1/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-04 | 2027-04-04 | 2
639775018-83969-DTLTRT-04_04_2024-GO95HV-1^668067/00 11/024 | OTHER | CA-TIER-2 | Transmission | 2024-04-04 | 2029-04-04 | 3
639775018-83969-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 11/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-04 | 2027-04-04 | 2
990943138-42969-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 14/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-04 | 2027-04-04 | 2
924504871-30691-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 2/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
924504871-88070-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 2/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
389408658-969-DTLTRT-04_04_2024-RISEBKSP-1^668067/00 2/024 | OTHER | CA-TIER-2 | Transmission | 2024-04-04 | 2027-04-04 | 2
802112441-45202-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
802112441-94070-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
573510881-59070-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
573510881-90302-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
318203293-86402-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 3/010 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
318203293-97170-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 3/010 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
523290363-12502-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 3/011 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
523290363-33502-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 3/011 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
73256324-49980-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 3/014 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
73256324-53211-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 3/014 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
73256324-83211-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 3/014 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
315614896-53002-DTLTRT-04_18_2024-GO95HV-1^668067/00 3/021 | OTHER | FHCA | Transmission | 2024-04-18 | 2029-04-18 | 3
315614896-54002-DTLTRT-04_18_2024-GO95HV-1^668067/00 3/021 | OTHER | FHCA | Transmission | 2024-04-18 | 2029-04-18 | 3
315614896-75700-DTLTRT-04_18_2024-GO95HV-1^668067/00 3/021 | OTHER | FHCA | Transmission | 2024-04-18 | 2029-04-18 | 3
315614896-53002-DTLTRT-04_18_2024-GUYNOINS-1^668067/00 3/021 | ANCHOR/GUY | FHCA | Transmission | 2024-04-18 | 2027-04-18 | 2
315614896-54002-DTLTRT-04_18_2024-GUYNOINS-1^668067/00 3/021 | ANCHOR/GUY | FHCA | Transmission | 2024-04-18 | 2027-04-18 | 2
315614896-75700-DTLTRT-04_18_2024-GUYNOINS-1^668067/00 3/021 | ANCHOR/GUY | FHCA | Transmission | 2024-04-18 | 2027-04-18 | 2
539520571-24702-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | FHCA | Transmission | 2024-04-10 | 2027-04-10 | 2
539520571-28469-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | FHCA | Transmission | 2024-04-10 | 2027-04-10 | 2
539520571-55702-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | FHCA | Transmission | 2024-04-10 | 2027-04-10 | 2
370520451-16180-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
370520451-28802-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
370520451-29802-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
562513891-30170-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
562513891-34902-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/006 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
494255073-43770-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 4/011 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
494255073-90202-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 4/011 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
678741316-62890-DTLTRT-04_18_2024-GO95HV-1^668067/00 4/020 | OTHER | CA-NON-TIER | Transmission | 2024-04-18 | 2029-04-18 | 3
639638878-43671-AUDIT-04_30_2024-XARMSPCR-1^668067/00 4/023 | CROSSARM | CA-TIER-2 | Transmission | 2024-04-30 | 2025-04-30 | 2
824327932-78602-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 5/007 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
824327932-89469-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 5/007 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
824327932-99602-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 5/007 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-11 | 2027-04-11 | 2
182363134-18611-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 5/014 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
182363134-49080-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 5/014 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
136546375-34490-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 5/019 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
136546375-64302-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 5/019 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
53902316-31990-DTLTRT-04_18_2024-GO95HV-1^668067/00 5/020 | OTHER | CA-NON-TIER | Transmission | 2024-04-18 | 2029-04-18 | 3
53902316-62402-DTLTRT-04_18_2024-GO95HV-1^668067/00 5/020 | OTHER | CA-NON-TIER | Transmission | 2024-04-18 | 2029-04-18 | 3
796419088-70969-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 5/024 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-04 | 2027-04-04 | 2
692962815-6645-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 6/001 | ANCHOR/GUY | FHCA | Transmission | 2024-04-10 | 2027-04-10 | 2
623713673-20569-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 6/008 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
623713673-24402-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 6/008 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
623713673-65402-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 6/008 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-15 | 2027-04-15 | 2
571262304-37780-DTLTRT-04_16_2024-GO95HV-1^668067/00 6/013 | OTHER | CA-NON-TIER | Transmission | 2024-04-16 | 2029-04-16 | 3
571262304-66811-DTLTRT-04_16_2024-GO95HV-1^668067/00 6/013 | OTHER | CA-NON-TIER | Transmission | 2024-04-16 | 2029-04-16 | 3
571262304-7811-DTLTRT-04_16_2024-GO95HV-1^668067/00 6/013 | OTHER | CA-NON-TIER | Transmission | 2024-04-16 | 2029-04-16 | 3
571262304-37780-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 6/013 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
571262304-66811-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 6/013 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
571262304-7811-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 6/013 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
59543395-50101-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 6/017 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
469891345-67101-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 6/018 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
147723876-13490-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 6/019 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
147723876-29502-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 6/019 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
643474088-35969-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 6/025 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2024-04-04 | 2027-04-04 | 2
710566093-20970-DTLTRT-04_16_2024-GO95HV-1^668067/00 7/011 | OTHER | CA-NON-TIER | Transmission | 2024-04-16 | 2029-04-16 | 3
710566093-44702-DTLTRT-04_16_2024-GO95HV-1^668067/00 7/011 | OTHER | CA-NON-TIER | Transmission | 2024-04-16 | 2029-04-16 | 3
710566093-20970-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 7/011 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
710566093-44702-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 7/011 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-16 | 2027-04-16 | 2
656405165-190-DTLTRT-04_17_2024-GO95HV-1^668067/00 7/016 | OTHER | CA-NON-TIER | Transmission | 2024-04-17 | 2029-04-17 | 3
656405165-2111-DTLTRT-04_17_2024-GO95HV-1^668067/00 7/016 | OTHER | CA-NON-TIER | Transmission | 2024-04-17 | 2029-04-17 | 3
656405165-62111-DTLTRT-04_17_2024-GO95HV-1^668067/00 7/016 | OTHER | CA-NON-TIER | Transmission | 2024-04-17 | 2029-04-17 | 3
656405165-190-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 7/016 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
656405165-2111-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 7/016 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
656405165-62111-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 7/016 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2024-04-17 | 2027-04-17 | 2
731787626-38090-DTLTRT-04_18_2024-GO95HV-1^668067/00 7/020 | OTHER | CA-NON-TIER | Transmission | 2024-04-18 | 2029-04-18 | 3
731787626-52802-DTLTRT-04_18_2024-GO95HV-1^668067/00 7/020 | OTHER | CA-NON-TIER | Transmission | 2024-04-18 | 2029-04-18 | 3
900053265-41301-DTLTRT-04_17_2024-GO95HV-1^668067/00 8/016 | OTHER | CA-NON-TIER | Transmission | 2024-04-17 | 2029-04-17 | 3
795742660-50660-DTLTRT-10_26_2022-GO95MLD-1^668075/00 1/028 | OTHER | FHCA | Transmission | 2022-10-26 | 2025-10-26 | 2
744624199-67699-DTLTRT-10_25_2022-GO95HV-1^668075/00 10/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
861430700-25600-DTLTRT-10_26_2022-GUYNOINS-1^668075/00 10A/028 | ANCHOR/GUY | FHCA | Transmission | 2022-10-26 | 2025-10-26 | 2
87604999-35399-DTLTRT-10_25_2022-GO95HV-1^668075/00 11/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
87604999-35399-DTLTRT-10_25_2022-GO95MLD-1^668075/00 11/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2025-10-25 | 2
87609620-46120-DTLTRT-11_16_2022-GO95HV-1^668075/00 11/026 | OTHER | FHCA | Transmission | 2022-11-16 | 2027-11-16 | 3
748792720-99120-DTLTRT-10_26_2022-GO95MLD-1^668075/00 11/027 | OTHER | FHCA | Transmission | 2022-10-26 | 2025-10-26 | 2
915656899-42609-DTLTRT-10_25_2022-GO95HV-1^668075/00 12/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
53105629-78329-DTLTRT-10_25_2022-GO95HV-1^668075/00 13/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
747865140-87540-DTLTRT-10_26_2022-GO95MLD-1^668075/00 14/027 | OTHER | FHCA | Transmission | 2022-10-26 | 2025-10-26 | 2
505398239-86639-DTLTRT-10_25_2022-GO95MLD-1^668075/00 15/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2025-10-25 | 2
232400513-91023-DTLTRT-10_24_2022-GO95HV-1^668075/00 16/024 | OTHER | FHCA | Transmission | 2022-10-24 | 2027-10-24 | 3
807892099-15399-DTLTRT-10_24_2022-GO95HV-1^668075/00 17/024 | OTHER | FHCA | Transmission | 2022-10-24 | 2027-10-24 | 3
807892099-15399-DTLTRT-10_24_2022-GO95MLD-1^668075/00 17/024 | OTHER | FHCA | Transmission | 2022-10-24 | 2025-10-24 | 2
973216199-14099-DTLTRT-10_25_2022-GO95MLD-1^668075/00 17/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2025-10-25 | 2
471250249-22749-DTLTRT-10_25_2022-GO95HV-1^668075/00 18/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
368245249-60749-DTLTRT-10_25_2022-GO95MLD-1^668075/00 19/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2025-10-25 | 2
368245249-60749-DETAIL-12_20_2022-GO95TCH-1^668075/00 19/025 | OTHER | FHCA | Transmission | 2022-12-20 | 2025-12-20 | 2
866155159-82259-DETAIL-12_22_2022-GUYNOINS-1^668075/00 19A/025 | ANCHOR/GUY | FHCA | Transmission | 2022-12-22 | 2025-12-22 | 2
74403029-59529-DTLTRT-10_25_2022-GO95HV-1^668075/00 2/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
253197140-66540-DTLTRT-11_16_2022-GO95HV-1^668075/00 2/027 | OTHER | FHCA | Transmission | 2022-11-16 | 2027-11-16 | 3
846567029-97629-DTLTRT-10_25_2022-GO95HV-1^668075/00 3/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
846567029-97629-DTLTRT-10_25_2022-GO95MLD-1^668075/00 3/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2025-10-25 | 2
846567029-97629-DETAIL-12_21_2022-GO95BLTC-1^668075/00 3/025 | OTHER | FHCA | Transmission | 2022-12-21 | 2027-12-21 | 3
259703669-72069-DTLTRT-10_25_2022-GO95HV-1^668075/00 3/026 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
119719140-49540-DTLTRT-11_16_2022-GO95MLD-1^668075/00 3/027 | OTHER | FHCA | Transmission | 2022-11-16 | 2025-11-16 | 2
108545959-73859-DTLTRT-10_25_2022-GO95HV-1^668075/00 4/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
482513970-82470-DTLTRT-10_26_2022-GO95MLD-1^668075/00 4/028 | OTHER | FHCA | Transmission | 2022-10-26 | 2025-10-26 | 2
965660099-6699-DTLTRT-10_25_2022-GO95MLD-1^668075/00 5/026 | OTHER | FHCA | Transmission | 2022-10-25 | 2025-10-25 | 2
145214479-82079-DTLTRT-10_25_2022-GO95HV-1^668075/00 7/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2027-10-25 | 3
145214479-82079-DTLTRT-10_25_2022-GO95MLD-1^668075/00 7/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2025-10-25 | 2
145214479-82079-DTLTRT-10_25_2022-GRDRODHI-1^668075/00 7/025 | OTHER | FHCA | Transmission | 2022-10-25 | 2025-10-25 | 2
307829090-69090-DTLTRT-11_16_2022-GO95MLD-1^668075/00 7/027 | OTHER | FHCA | Transmission | 2022-11-16 | 2025-11-16 | 2
156512980-17780-DETAIL-12_22_2022-GO95HV-1^668075/00 7/028 | OTHER | FHCA | Transmission | 2022-12-22 | 2027-12-22 | 3
839259300-23800-DTLTRT-10_26_2022-GO95HV-1^668075/00 8/027 | OTHER | FHCA | Transmission | 2022-10-26 | 2027-10-26 | 3
649455610-69010-DTLTRT-11_16_2022-GO95HV-1^668075/00 9/026 | OTHER | FHCA | Transmission | 2022-11-16 | 2027-11-16 | 3
649455610-69010-DTLTRT-11_16_2022-GO95MLD-1^668075/00 9/026 | OTHER | FHCA | Transmission | 2022-11-16 | 2025-11-16 | 2
321721166-90029-DETAIL-07_01_2020-GO95MLD-1^06142012.0014101 | OTHER | FHCA | Distribution | 2020-07-01 | 2023-07-01 | 2
918391279-36902-ADMIN-06_30_2020-POLEDERP-1^06142012.0106400 | POLE | FHCA | Distribution | 2020-06-30 | 2023-06-30 | 2
726224121-27229-DETAIL-06_29_2020-SVCROAD-1^06142012.0118504 | OTHER | FHCA | Distribution | 2020-06-29 | 2023-06-29 | 2
816790411-71529-DETAIL-05_08_2024-ABNDEQPM-1^06142012.0120003 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
347776651-74929-DETAIL-05_08_2024-GO95HV-1^06142012.0120004 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
959348831-25929-DETAIL-05_08_2024-GO95BLTC-1^06142012.0120005 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
959348831-25929-DETAIL-05_08_2024-GO95MLD-1^06142012.0120005 | OTHER | FHCA | Distribution | 2024-05-08 | 2027-05-08 | 2
223764784-26329-DETAIL-05_08_2024-GO95HV-1^06142012.0120006 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
778258499-20129-DETAIL-05_08_2024-GO95HV-1^06142012.0120010 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
778258499-20129-DETAIL-05_08_2024-GO95MLD-1^06142012.0120010 | OTHER | FHCA | Distribution | 2024-05-08 | 2027-05-08 | 2
194110384-41329-DETAIL-05_09_2024-SVCRUBLG-1^06142012.0120508 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
85557931-99931-DETAIL-05_09_2024-GO95MLD-1^06142012.0120509 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
85557931-99931-DETAIL-05_09_2024-RISESTRP-1^06142012.0120509 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
172875525-5929-ADMIN-08_01_2024-POLEREPL-1^06142012.0120600 | POLE | FHCA | Distribution | 2024-08-01 | 2027-08-01 | 2
247492573-35129-DETAIL-05_09_2024-GO95MLD-1^06142012.0120601 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
786217613-9429-DETAIL-05_09_2024-GO95MLD-1^06142012.0120602 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
571341503-1529-DETAIL-05_09_2024-GO95HV-1^06142012.0120603 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
571341503-1529-DETAIL-05_09_2024-GO95MLD-1^06142012.0120603 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
58380913-17929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120604 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
58380913-17929-DETAIL-05_09_2024-SVCENTCO-1^06142012.0120604 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
859803333-53792-DETAIL-05_16_2024-GO95MLD-1^06142012.0120700 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
566575073-16929-DETAIL-05_09_2024-SVCDEFLC-1^06142012.0121603 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
658945193-64201-DETAIL-05_16_2024-GO95MLD-1^06142012.0121701 | OTHER | FHCA | Distribution | 2024-05-16 | 2029-05-16 | 3
657707193-12601-DETAIL-05_16_2024-GO95HV-1^06142012.0121703 | OTHER | FHCA | Distribution | 2024-05-16 | 2029-05-16 | 3
657707193-12601-DETAIL-05_16_2024-GO95MLD-1^06142012.0121703 | OTHER | FHCA | Distribution | 2024-05-16 | 2029-05-16 | 3
976533783-68629-DETAIL-05_16_2024-GO95MLD-1^06142012.0121706 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
976533783-68629-DETAIL-05_16_2024-SVCDEFLC-1^06142012.0121706 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
203832845-97529-DETAIL-05_16_2024-GO95MLD-1^06142012.0121800 | OTHER | FHCA | Distribution | 2024-05-16 | 2029-05-16 | 3
818508565-43829-DETAIL-05_16_2024-GO95MLD-1^06142012.0121900 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
158552050-27800-DETAIL-05_06_2024-GO95HV-1^06142012.0122000 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
872944579-13129-DETAIL-05_06_2024-GO95MLD-1^06142012.0122001 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
541116418-77418-DETAIL-04_17_2019-SVCROOF-1^06142012.0122002 | OTHER | FHCA | Distribution | 2019-04-17 | 2024-03-17 | 2
22641701-16829-DETAIL-05_14_2024-GO95MLD-1^06142012.0122404 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
674155571-56829-DETAIL-05_14_2024-SVCENTCO-1^06142012.0122406 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
801451891-72829-DETAIL-05_13_2024-GO95MLD-1^06142012.0122407 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
922310760-23829-DETAIL-05_14_2024-GO95MLD-1^06142012.0122409 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
922310760-23829-DETAIL-05_14_2024-SVCROAD-1^06142012.0122409 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
116144389-74729-DETAIL-05_14_2024-GO95MLD-1^06142012.0122410 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
623278346-25129-DETAIL-05_13_2024-CLRTOUCH-1^06142012.0122412 | CONDUCTOR | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
398662253-90429-DETAIL-05_14_2024-GO95BLTC-1^06142012.0122503 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
917854253-14729-DETAIL-05_14_2024-GO95MLD-1^06142012.0122504 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
706788304-38729-DETAIL-05_01_2024-GO95MLD-1^06142012.0122506 | OTHER | FHCA | Distribution | 2024-05-01 | 2027-05-01 | 2
904356643-41929-DETAIL-05_14_2024-GO95MLD-1^06142012.0122601 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
903161323-72729-DETAIL-05_14_2024-GO95MLD-1^06142012.0122604 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
16122131-40989-DETAIL-05_06_2024-GO95MLD-1^06142012.0123008 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
187692211-8211-DETAIL-05_06_2024-GUYNOINS-1^06142012.0123012 | ANCHOR/GUY | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
187692211-8211-DETAIL-05_06_2024-GUYNOINS-2^06142012.0123012 | ANCHOR/GUY | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
963748195-57029-DETAIL-05_06_2024-CLRTOPOL-1^06142012.0123100 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
963748195-57029-DETAIL-05_06_2024-SVCENTCO-1^06142012.0123100 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
727862161-66029-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0123103 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
727862161-66029-DETAIL-05_06_2024-SVCENTCO-1^06142012.0123103 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
111815981-71929-DETAIL-05_07_2024-GO95MLD-1^06142012.0123108 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
866332691-44029-DETAIL-05_07_2024-GO95MLD-1^06142012.0123109 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
337345641-92029-DETAIL-05_07_2024-GO95HV-1^06142012.0123112 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
493229761-91029-DETAIL-05_06_2024-GO95MLD-1^06142012.0123114 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
699515935-10411-DETAIL-05_15_2024-GO95MLD-1^06142012.0123703 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
699515935-10411-DETAIL-05_15_2024-GRDRODHI-1^06142012.0123703 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
475272653-3629-DETAIL-05_15_2024-GO95HV-1^06142012.0123900 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
745604553-62629-DETAIL-05_15_2024-GO95HV-1^06142012.0123901 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
487638511-16461-DETAIL-05_06_2024-CLRTOUCH-1^06142012.0124000 | CONDUCTOR | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
487638511-16461-DETAIL-05_06_2024-GO95MLD-1^06142012.0124000 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
487638511-16461-DETAIL-05_06_2024-SVCENTCO-1^06142012.0124000 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
168004821-66910-DETAIL-05_06_2024-GO95HV-1^06142012.0124001 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
168004821-66910-DETAIL-05_06_2024-GO95MLD-1^06142012.0124001 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
692205961-62691-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0124002 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
56859920-54960-DETAIL-05_06_2024-GUYHINS-1^06142012.0124003 | ANCHOR/GUY | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
370227409-30020-DETAIL-05_13_2024-GO95MLD-1^06142012.0124305 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
370227409-30020-DETAIL-05_13_2024-SVCDEFLC-1^06142012.0124305 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
370227409-30020-DETAIL-05_13_2024-SVCENTCO-1^06142012.0124305 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
278730819-88420-DETAIL-05_13_2024-GO95CLMP-1^06142012.0124306 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
278730819-88420-DETAIL-05_13_2024-GO95HV-1^06142012.0124306 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
278730819-88420-DETAIL-05_13_2024-SVCENTCO-1^06142012.0124306 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
891697062-49892-DETAIL-05_13_2024-GO95MLD-1^06142012.0124400 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
71381682-1200-DETAIL-05_13_2024-GO95HV-1^06142012.0124402 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
71381682-1200-DETAIL-05_13_2024-SVCRUBLG-1^06142012.0124402 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
387456382-26240-DETAIL-05_13_2024-GO95HV-1^06142012.0124404 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
387456382-26240-DETAIL-05_13_2024-SVCDEFLC-1^06142012.0124404 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
963353788-85353-DETAIL-05_14_2024-GO95MLD-1^06142012.0124406 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
903140488-44442-DETAIL-05_02_2024-GO95MLD-1^06142012.0125108 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
760806408-52181-DETAIL-05_02_2024-GO95MLD-1^06142012.0125109 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
442794278-8901-DETAIL-05_02_2024-GO95HV-1^06142012.0125111 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
727464179-88291-DETAIL-04_18_2019-SVCROAD-1^06142012.0125202 | OTHER | FHCA | Distribution | 2019-04-18 | 2024-03-18 | 2
727464179-88291-DETAIL-05_02_2024-GO95MLD-1^06142012.0125202 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
863560492-36702-DETAIL-05_15_2024-GO95HV-1^06142012.0125701 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
534020652-81821-DETAIL-05_15_2024-SVCDEFLC-1^06142012.0125800 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
336332792-30629-DETAIL-05_15_2024-GO95HV-1^06142012.0125805 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
390160032-84139-DETAIL-05_15_2024-GO95MLD-1^06142012.0125806 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
264875522-40329-DETAIL-05_15_2024-GO95HV-1^06142012.0125900 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
733059612-1629-DETAIL-05_15_2024-GO95HV-1^06142012.0125903 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
733059612-1629-DETAIL-05_15_2024-GO95MLD-1^06142012.0125903 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
378316543-66129-DETAIL-04_12_2022-GO95MLD-1^06142012.0130606 | OTHER | FHCA | Distribution | 2022-04-12 | 2027-04-12 | 3
378316543-66129-DETAIL-04_12_2022-SVCENTCO-1^06142012.0130606 | OTHER | FHCA | Distribution | 2022-04-12 | 2025-04-12 | 2
378316543-66129-DETAIL-04_12_2022-SVCENTCO-2^06142012.0130606 | OTHER | FHCA | Distribution | 2022-04-12 | 2025-04-12 | 2
378316543-66129-DETAIL-04_12_2022-SVCWIND-1^06142012.0130606 | OTHER | FHCA | Distribution | 2022-04-12 | 2025-04-12 | 2
930762403-53729-DETAIL-03_06_2017-SVCWIND-1^06142012.0130611 | OTHER | FHCA | Distribution | 2017-03-06 | 2022-02-06 | 2
415284634-73129-DETAIL-03_16_2017-SVCWIND-1^06142012.0130614 | OTHER | FHCA | Distribution | 2017-03-16 | 2022-02-16 | 2
57768820-11929-DETAIL-04_11_2022-CLMBHAZ-1^06142012.0130708 | OTHER | FHCA | Distribution | 2022-04-11 | 2025-04-11 | 2
132922781-24429-DETAIL-04_11_2022-GO95BLTC-1^06142012.0130800 | OTHER | FHCA | Distribution | 2022-04-11 | 2027-04-11 | 3
132922781-24429-DETAIL-04_11_2022-GO95MLD-1^06142012.0130800 | OTHER | FHCA | Distribution | 2022-04-11 | 2025-04-11 | 2
362291083-53029-DETAIL-04_11_2022-POLETOP-1^06142012.0130907 | POLE | FHCA | Distribution | 2022-04-11 | 2025-04-11 | 2
799986794-99682-DETAIL-04_12_2022-GO95MLD-1^06142012.0131302 | OTHER | FHCA | Distribution | 2022-04-12 | 2025-04-12 | 2
445444204-36301-DETAIL-04_12_2022-ABNDEQPM-1^06142012.0131304 | OTHER | FHCA | Distribution | 2022-04-12 | 2027-04-12 | 3
779988084-15632-DETAIL-04_12_2022-GO95MLD-1^06142012.0131405 | OTHER | FHCA | Distribution | 2022-04-12 | 2025-04-12 | 2
352846883-62129-DETAIL-04_12_2022-GO95MLD-1^06142012.0131505 | OTHER | FHCA | Distribution | 2022-04-12 | 2025-04-12 | 2
385210623-43229-DETAIL-04_12_2022-GO95MLD-1^06142012.0131508 | OTHER | FHCA | Distribution | 2022-04-12 | 2025-04-12 | 2
850341785-24829-DETAIL-04_13_2022-GO95MLD-1^06142012.0131607 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
850341785-24829-DETAIL-04_13_2022-GRDRODHI-1^06142012.0131607 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
716115674-56829-DETAIL-04_19_2022-GRDRODHI-1^06142012.0131804 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
465090434-41829-DETAIL-04_19_2022-GO95MLD-1^06142012.0131805 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
465090434-41829-DETAIL-04_19_2022-SVCROAD-1^06142012.0131805 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
465090434-41829-DETAIL-04_19_2022-SVCWIND-1^06142012.0131805 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
465090434-41829-DETAIL-04_19_2022-SVCWIND-2^06142012.0131805 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
862390155-2729-DETAIL-04_19_2022-GO95MLD-1^06142012.0131809 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
862390155-2729-DETAIL-04_19_2022-GO95TCH-1^06142012.0131809 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
118618281-90829-DETAIL-04_19_2022-POLETOP-1^06142012.0131814 | POLE | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
440017730-84329-DETAIL-04_19_2022-GUYHINS-1^06142012.0132816 | ANCHOR/GUY | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
928491721-93129-DETAIL-04_19_2022-GO95HV-1^06142012.0132901 | OTHER | FHCA | Distribution | 2022-04-19 | 2027-04-19 | 3
928491721-93129-DETAIL-04_19_2022-GUYHINS-1^06142012.0132901 | ANCHOR/GUY | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
166314665-83429-DETAIL-04_19_2022-GO95MLD-1^06142012.0132902 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
166314665-83429-DETAIL-04_19_2022-GO95TCH-1^06142012.0132902 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
166314665-83429-DETAIL-04_19_2022-SVCRUBLG-1^06142012.0132902 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
616622914-27129-DETAIL-04_19_2022-GO95HV-1^06142012.0132906 | OTHER | FHCA | Distribution | 2022-04-19 | 2027-04-19 | 3
616622914-27129-DETAIL-04_19_2022-GO95MLD-1^06142012.0132906 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
25270683-52429-DETAIL-04_19_2022-GO95HV-1^06142012.0132907 | OTHER | FHCA | Distribution | 2022-04-19 | 2027-04-19 | 3
25270683-52429-DETAIL-04_19_2022-GO95MLD-1^06142012.0132907 | OTHER | FHCA | Distribution | 2022-04-19 | 2027-04-19 | 3
24039591-80870-DETAIL-04_19_2022-POLETOP-1^06142012.0134903 | POLE | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
298428773-36040-DETAIL-04_21_2022-GO95HV-1^06142012.0135000 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
871044243-7722-DETAIL-04_14_2022-ANCHIDLE-1^06142012.0135401 | ANCHOR/GUY | FHCA | Distribution | 2022-04-14 | 2025-04-14 | 2
862592163-16302-DETAIL-04_14_2022-GO95CL10-1^06142012.0135502 | OTHER | FHCA | Distribution | 2022-04-14 | 2027-04-14 | 3
339240023-86780-DETAIL-04_14_2022-GO95MLD-1^06142012.0135503 | OTHER | FHCA | Distribution | 2022-04-14 | 2025-04-14 | 2
339240023-86780-DETAIL-04_14_2022-SVCROAD-1^06142012.0135503 | OTHER | FHCA | Distribution | 2022-04-14 | 2025-04-14 | 2
797096253-53929-DETAIL-04_14_2022-GO95HV-1^06142012.0136501 | OTHER | FHCA | Distribution | 2022-04-14 | 2027-04-14 | 3
827870093-75682-DETAIL-04_14_2022-GO95HV-1^06142012.0136502 | OTHER | FHCA | Distribution | 2022-04-14 | 2027-04-14 | 3
766256424-11139-DETAIL-11_05_2021-GO95HV-1^06142012.0144200 | OTHER | FHCA | Distribution | 2021-11-05 | 2026-11-05 | 3
472933454-53841-DETAIL-11_08_2021-SVCROAD-1^06142012.0145801 | OTHER | FHCA | Distribution | 2021-11-08 | 2024-11-08 | 2
925702949-35229-DETAIL-11_10_2021-SVCROAD-1^06142012.0146504 | OTHER | FHCA | Distribution | 2021-11-10 | 2024-11-10 | 2
421695248-7970-DETAIL-11_03_2021-GO95TCH-1^06142012.0146700 | OTHER | FHCA | Distribution | 2021-11-03 | 2024-11-03 | 2
220126504-56529-DETAIL-11_08_2021-SVCRUBLG-1^06142012.0146702 | OTHER | FHCA | Distribution | 2021-11-08 | 2024-11-08 | 2
423329150-74928-DETAIL-11_03_2021-GO95TCH-1^06142012.0146808 | OTHER | FHCA | Distribution | 2021-11-03 | 2024-11-03 | 2
671830178-44929-ADMIN-08_09_2024-POLEREPL-1^06142012.0147503 | POLE | FHCA | Distribution | 2024-08-09 | 2027-08-09 | 2
227880459-55929-ADMIN-08_02_2024-POLEREPL-1^06142012.0147507 | POLE | FHCA | Distribution | 2024-08-02 | 2027-08-02 | 2
59128218-93929-DETAIL-11_03_2021-GO95TCH-1^06142012.0147907 | OTHER | FHCA | Distribution | 2021-11-03 | 2024-11-03 | 2
222314411-56411-DETAIL-04_30_2024-GO95HV-1^06142015.0027900 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
688029411-1511-DETAIL-04_30_2024-GO95HV-1^06142015.0027901 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
749168511-1611-DETAIL-04_30_2024-GO95HV-1^06142015.0028901 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
923726611-58611-DETAIL-04_30_2024-GO95HV-1^06142015.0028902 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
587121711-23711-DETAIL-04_30_2024-GO95HV-1^06142015.0029900 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
795280811-86849-DETAIL-04_30_2024-GO95HV-1^06142015.0030901 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
559622041-93041-DETAIL-04_30_2024-GO95HV-1^06142015.0033900 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
554440141-72141-DETAIL-04_30_2024-GO95HV-1^06142015.0034900 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
317449141-11241-DTLSB-04_16_2014-GUYNOINS-1^06142015.0034902 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2014-04-16 | 2019-03-16 | 2
325351211-92211-DETAIL-03_23_2023-GO95MLD-1^06142016.0051105 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
88547311-9311-DETAIL-03_27_2023-GO95TCH-1^06142016.0051201 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
88547311-9311-DETAIL-03_27_2023-GUYHINS-1^06142016.0051201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
789179331-80431-DETAIL-03_27_2023-GO95MLD-1^06142016.0052003 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
161372531-8834-DETAIL-03_27_2023-GO95MLD-1^06142016.0052100 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
161372531-8834-DETAIL-03_27_2023-GRDRODHI-1^06142016.0052100 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
498179531-90631-DETAIL-03_27_2023-GO95HV-1^06142016.0052102 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
333239961-71061-DETAIL-03_27_2023-GO95HV-1^06142016.0052202 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
333239961-71061-DETAIL-03_27_2023-GO95MLD-1^06142016.0052202 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
796643081-95081-DETAIL-03_27_2023-GUYHINS-1^06142016.0052300 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
887170281-42281-DETAIL-03_27_2023-GO95HV-1^06142016.0052400 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
288510381-11381-DETAIL-03_27_2023-GO95HV-1^06142016.0052500 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
768439801-77644-DETAIL-03_30_2023-COPLLEAN-1^06142016.0055102 | POLE | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
768439801-77644-DETAIL-03_30_2023-GO95MLD-1^06142016.0055102 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
232845901-57901-DETAIL-03_30_2023-GUYHINS-1^06142016.0055103 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
593370241-23241-DETAIL-03_30_2023-GO95HV-1^06142016.0055201 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
660983302-18302-DETAIL-03_30_2023-GO95HV-1^06142016.0056001 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
994836983-3083-DETAIL-03_30_2023-GO95HV-1^06142016.0058001 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
350741283-27283-DETAIL-03_30_2023-GO95HV-1^06142016.0059000 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
165520683-44683-DETAIL-03_30_2023-GO95MLD-1^06142016.0059004 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
530109683-22783-DETAIL-03_30_2023-ENCHRW-1^06142016.0059005 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
530109683-22783-DETAIL-03_30_2023-ENCHRW-2^06142016.0059005 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
112627883-42983-DETAIL-03_30_2023-GO95HV-1^06142016.0059100 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
224475323-69323-DETAIL-04_30_2024-GO95HV-1^06142016.0060101 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
268617713-80813-DETAIL-04_29_2024-GRDRODHI-1^06142016.0079700 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
268617713-80813-DETAIL-04_29_2024-SVCROAD-1^06142016.0079700 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
430222243-74243-DETAIL-04_29_2024-GO95MLD-1^06142016.0079701 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
320686243-48243-DETAIL-04_29_2024-GRDRODHI-1^06142016.0079703 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
892099243-81343-DETAIL-04_29_2024-GO95MLD-1^06142016.0079704 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
450171963-49963-DETAIL-04_29_2024-GO95MLD-1^06142016.0079801 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
450171963-49963-DETAIL-04_29_2024-GRDRODHI-1^06142016.0079801 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
450171963-49963-AUDIT-05_30_2024-GO95HV-1^06142016.0079801 | OTHER | CA-TIER-2 | Distribution | 2024-05-30 | 2029-05-30 | 3
416106063-80163-DETAIL-04_29_2024-GO95BLTC-1^06142016.0079802 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
448881263-93263-DETAIL-04_29_2024-SVCROAD-1^06142016.0079901 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
499876263-19263-DETAIL-04_29_2024-GO95MLD-1^06142016.0079902 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
499876263-19263-DETAIL-04_29_2024-GRDRODHI-1^06142016.0079902 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
811287614-20714-DETAIL-03_27_2023-GO95MLD-1^06142016.0082901 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
560580491-5191-DETAIL-03_27_2023-ABNDEQPM-1^06142016.0082903 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
560580491-5191-DETAIL-03_27_2023-GO95MLD-1^06142016.0082903 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
826205234-27234-DETAIL-03_29_2023-GUYHINS-1^06142016.0083400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
852825596-61562-DETAIL-03_29_2023-GO95MLD-1^06142016.0083500 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
912199254-32354-DETAIL-03_28_2023-GO95HV-1^06142016.0083801 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
472421554-14554-DETAIL-03_28_2023-GO95MLD-1^06142016.0083805 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
686933654-94654-DETAIL-03_28_2023-GO95MLD-1^06142016.0083807 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
106095974-8084-DETAIL-03_29_2023-GO95MLD-1^06142016.0084400 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
408012504-92473-DETAIL-03_29_2023-SVCROAD-1^06142016.0084602 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
15851624-24624-DETAIL-03_28_2023-GO95MLD-1^06142016.0084701 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
851191724-44724-DETAIL-03_28_2023-GO95MLD-1^06142016.0084704 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
724521634-24634-DETAIL-03_29_2023-CLRTOUCH-1^06142016.0085601 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
37987634-33675-DETAIL-03_29_2023-GO95TCH-1^06142016.0085602 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
910548734-58153-ADMIN-04_21_2023-GO95TCH-1^06142016.0085701 | OTHER | CA-NON-TIER | Distribution | 2023-04-21 | 2026-04-21 | 2
553854954-65094-DETAIL-03_30_2023-GUYNOINS-1^06142016.0085805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
255471524-84524-DETAIL-04_25_2024-GO95HV-1^06142016.0160201 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
886881624-33624-DETAIL-04_25_2024-GO95HV-1^06142016.0160800 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
744855624-17624-DETAIL-04_25_2024-GO95HV-1^06142016.0160900 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
655217724-68724-DETAIL-04_25_2024-CUTOUTAR-1^06142016.0161800 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
655217724-68724-DETAIL-04_25_2024-GO95HV-1^06142016.0161800 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
655217724-68724-DETAIL-04_25_2024-GO95MLD-1^06142016.0161800 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
655217724-68724-DETAIL-04_25_2024-GRDRODHI-1^06142016.0161800 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
655217724-68724-DETAIL-04_25_2024-GUYHINS-1^06142016.0161800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
932863114-46114-DETAIL-04_25_2024-GO95HV-1^06142016.0177900 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
258140214-22214-DETAIL-04_25_2024-GO95HV-1^06142016.0177901 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
702729234-91334-DETAIL-04_25_2024-GO95HV-1^06142016.0179201 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
58371444-66444-DETAIL-04_25_2024-GO95HV-1^06142016.0179901 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
249141454-2429-DETAIL-04_26_2022-GO95MLD-1^06143012.0237000 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
883931294-97629-DETAIL-04_26_2022-GO95HV-1^06143012.0238000 | OTHER | FHCA | Distribution | 2022-04-26 | 2027-04-26 | 3
744707784-7629-DETAIL-04_26_2022-GO95MLD-1^06143012.0239000 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
744707784-7629-DETAIL-04_26_2022-GUYSLACK-1^06143012.0239000 | ANCHOR/GUY | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
926342090-18329-ADMIN-10_24_2022-CUTOUTAR-1^06143012.0240801 | LIGHTNING ARRESTER | FHCA | Distribution | 2022-10-24 | 2025-10-24 | 2
522408421-93629-DETAIL-04_27_2022-GO95HV-1^06143012.0241000 | OTHER | FHCA | Distribution | 2022-04-27 | 2027-04-27 | 3
479348011-88529-DETAIL-04_27_2022-GO95HV-1^06143012.0241001 | OTHER | FHCA | Distribution | 2022-04-27 | 2027-04-27 | 3
135593701-53629-DETAIL-04_27_2022-GRDRODHI-1^06143012.0241100 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
792615791-72629-DETAIL-04_27_2022-GO95MLD-1^06143012.0241200 | OTHER | FHCA | Distribution | 2022-04-27 | 2027-04-27 | 3
814144219-12529-DETAIL-04_27_2022-GO95MLD-1^06143012.0242300 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
717938211-31429-DETAIL-05_02_2022-SVCNEUT-1^06143012.0244000 | OTHER | FHCA | Distribution | 2022-05-02 | 2025-05-02 | 2
282555460-68629-DETAIL-05_02_2022-SVCROAD-1^06143012.0245800 | OTHER | FHCA | Distribution | 2022-05-02 | 2025-05-02 | 2
959492898-83629-DETAIL-04_28_2022-GO95HV-1^06143012.0246401 | OTHER | FHCA | Distribution | 2022-04-28 | 2027-04-28 | 3
854274429-65329-DETAIL-04_28_2022-GO95MLD-1^06143012.0247400 | OTHER | FHCA | Distribution | 2022-04-28 | 2025-04-28 | 2
450430869-88329-DETAIL-04_28_2022-GO95MLD-1^06143012.0248403 | OTHER | FHCA | Distribution | 2022-04-28 | 2025-04-28 | 2
177369944-27529-DETAIL-04_27_2022-GO95MLD-1^06143012.0251901 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
30810703-95329-DETAIL-04_25_2022-GO95MLD-1^06143012.0252700 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
287305174-48529-DETAIL-04_25_2022-GO95HV-1^06143012.0253201 | OTHER | FHCA | Distribution | 2022-04-25 | 2027-04-25 | 3
222667223-10629-DETAIL-04_27_2022-GO95MLD-1^06143012.0254901 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
949907743-20529-DETAIL-04_25_2022-GUYHINS-1^06143012.0255203 | ANCHOR/GUY | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
673174673-35529-DETAIL-04_25_2022-GO95HV-1^06143012.0255300 | OTHER | FHCA | Distribution | 2022-04-25 | 2027-04-25 | 3
673174673-35529-DETAIL-04_25_2022-GO95MLD-1^06143012.0255300 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
627848253-55429-DETAIL-04_27_2022-GO95MLD-1^06143012.0255701 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
331848364-24129-DETAIL-05_02_2022-GO95MLD-1^06143012.0255800 | OTHER | FHCA | Distribution | 2022-05-02 | 2025-05-02 | 2
98534414-99129-DETAIL-04_28_2022-GO95MLD-1^06143012.0255802 | OTHER | FHCA | Distribution | 2022-04-28 | 2027-04-28 | 3
249770414-96229-DETAIL-04_25_2022-GO95MLD-1^06143012.0256202 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
707063223-1829-DETAIL-04_25_2022-GO95MLD-1^06143012.0365900 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
707063223-1829-DETAIL-04_25_2022-GRDRODHI-1^06143012.0365900 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
864096713-70829-DETAIL-04_25_2022-GO95MLD-1^06143012.0365901 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
132028934-36229-DETAIL-04_20_2022-GO95MLD-1^06143012.0366003 | OTHER | FHCA | Distribution | 2022-04-20 | 2025-04-20 | 2
823695444-81229-DETAIL-04_20_2022-SVCROAD-1^06143012.0369003 | OTHER | FHCA | Distribution | 2022-04-20 | 2025-04-20 | 2
79501724-3029-DETAIL-05_04_2022-GO95MLD-1^06143013.0190400 | OTHER | FHCA | Distribution | 2022-05-04 | 2025-05-04 | 2
312875624-72029-DETAIL-05_04_2022-SVCNEUT-1^06143013.0190401 | OTHER | FHCA | Distribution | 2022-05-04 | 2025-05-04 | 2
600831394-39629-DETAIL-05_04_2022-GO95MLD-1^06143013.0190501 | OTHER | FHCA | Distribution | 2022-05-04 | 2025-05-04 | 2
636724253-5651-DETAIL-04_03_2023-GO95HV-1^06143014.0176201 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
828859205-35892-DETAIL-04_03_2023-GO95HV-1^06143014.0181300 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
938933383-61992-DETAIL-04_03_2023-GO95HV-1^06143014.0181301 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
383325463-57329-DETAIL-04_03_2023-GO95TCH-1^06143014.0213700 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2026-04-03 | 2
523461793-74801-DETAIL-04_03_2023-ABNDEQPM-1^06143014.0213901 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
815438613-27742-DETAIL-04_04_2023-ABNDEQPM-1^06143014.0217900 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
815438613-27742-DETAIL-04_04_2023-GO95MLD-1^06143014.0217900 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2026-04-04 | 2
530356083-93811-DETAIL-04_04_2023-SVCENTCO-1^06143014.0219702 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2026-04-04 | 2
746216573-25841-DETAIL-04_04_2023-GO95HV-1^06143014.0224701 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
937417383-22492-DETAIL-04_04_2023-GO95HV-1^06143014.0225800 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
737170953-78621-DETAIL-04_06_2023-GO95MLD-1^06143014.0230500 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
400089773-63434-DETAIL-05_01_2024-GO95HV-1^06143015.0338601 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
400089773-63434-DETAIL-05_01_2024-GUYLOINS-1^06143015.0338601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-05-01 | 2027-05-01 | 2
400089773-63434-DETAIL-05_01_2024-INSULDMG-1^06143015.0338601 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-05-01 | 2024-06-01 | 1
529436244-35534-DETAIL-05_01_2024-GO95HV-1^06143015.0339602 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
161580874-88034-DETAIL-05_01_2024-SVCDEFLC-1^06143015.0339901 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2027-05-01 | 2
994501454-67534-DETAIL-05_01_2024-GO95HV-1^06143015.0341500 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
279268954-49534-DETAIL-05_01_2024-GO95HV-1^06143015.0342400 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
290941014-30934-DETAIL-05_01_2024-GO95HV-1^06143015.0347100 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
27346814-80934-DETAIL-05_01_2024-GO95HV-1^06143015.0348001 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
719646384-40484-DETAIL-03_28_2023-GO95HV-1^06143016.0322101 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
684804121-84119-ADMIN-05_24_2021-INSULDMG-1^668005/00 10/083 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
59347615-44619-DETAIL-08_11_2019-POLEDERP-1^668005/00 10/096 | POLE | FHCA | Transmission | 2019-08-11 | 2022-08-11 | 2
659406248-64719-DTLTRT-08_18_2022-GO95MLD-1^668005/00 10/098 | OTHER | FHCA | Transmission | 2022-08-18 | 2025-08-18 | 2
659406248-64719-DTLTRT-08_18_2022-GRDRODHI-1^668005/00 10/098 | OTHER | FHCA | Transmission | 2022-08-18 | 2025-08-18 | 2
845417682-71369-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 10A/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
588082218-27519-DETAIL-08_01_2022-GO95HV-1^668005/00 11/072 | OTHER | CA-NON-TIER | Transmission | 2022-08-01 | 2027-08-01 | 3
184719579-25819-ADMIN-05_24_2021-INSULDMG-1^668005/00 11/077 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
262546251-11119-ADMIN-08_05_2020-POLEDERP-1^668005/00 11/082 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
391808933-4519-ADMIN-05_20_2021-POLETOP-1^668005/00 14/093 | POLE | FHCA | Transmission | 2021-05-20 | 2024-05-20 | 2
391808933-4519-DTLTRT-08_17_2022-UBPBXARM-1^668005/00 14/093 | CROSSARM | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
506152954-87519-ADMIN-11_18_2022-POLEDERP-1^668005/00 14/094 | POLE | FHCA | Transmission | 2022-11-18 | 2025-11-18 | 2
254759124-41619-DTLTRT-08_17_2022-GO95HV-1^668005/00 14/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2027-08-17 | 3
248144023-15419-ADMIN-06_15_2021-INSULDMG-1^668005/00 15/091 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
248144023-15419-DTLTRT-08_16_2022-GO95HV-1^668005/00 15/091 | OTHER | FHCA | Transmission | 2022-08-16 | 2027-08-16 | 3
248144023-15419-DTLTRT-08_16_2022-GO95MLD-1^668005/00 15/091 | OTHER | FHCA | Transmission | 2022-08-16 | 2025-08-16 | 2
248144023-15419-DTLTRT-08_16_2022-GRDRODHI-1^668005/00 15/091 | OTHER | FHCA | Transmission | 2022-08-16 | 2025-08-16 | 2
561581869-89919-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 2/079 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-03 | 2025-08-03 | 2
793797551-67219-ADMIN-12_31_2018-POLEREPL-1^668005/00 2/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
99559872-61319-ADMIN-12_31_2018-POLEREPL-1^668005/00 2/088 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
33473365-82619-DTLTRT-08_17_2022-GO95HV-1^668005/00 2/096 | OTHER | FHCA | Transmission | 2022-08-17 | 2027-08-17 | 3
508676516-77619-ADMIN-07_27_2021-INSULDMG-1^668005/00 2/097 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
427015438-5969-DETAIL-06_28_2022-GO95MLD-1^668005/00 3/026 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
19138340-7269-ADMIN-08_05_2020-POLEDERP-1^668005/00 3/051 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
18901286-79669-ADMIN-05_24_2021-INSULDMG-1^668005/00 3/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
775078606-40769-ADMIN-05_24_2021-INSULDMG-1^668005/00 4/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
587682099-47819-ADMIN-06_24_2021-INSULDMG-1^668005/00 4/078 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-24 | 2024-06-24 | 2
293723679-30019-ADMIN-05_24_2021-INSULDMG-1^668005/00 4/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
7883440-3019-ADMIN-05_24_2021-INSULDMG-1^668005/00 4/080 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
806127861-86019-ADMIN-07_27_2021-INSULDMG-1^668005/00 4/081 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
574770541-5219-DETAIL-08_15_2022-GO95HV-1^668005/00 4/086 | OTHER | CA-NON-TIER | Transmission | 2022-08-15 | 2027-08-15 | 3
782174153-56419-DTLTRT-08_16_2022-POLETOP-1^668005/00 4/092 | POLE | FHCA | Transmission | 2022-08-16 | 2025-08-16 | 2
16979116-21769-ADMIN-05_24_2021-INSULDMG-1^668005/00 6/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
719570266-17419-ADMIN-07_29_2024-POLEDERP-1^668005/00 6/069 | POLE | CA-NON-TIER | Transmission | 2024-07-29 | 2027-07-29 | 2
889472999-60019-ADMIN-06_15_2021-INSULDMG-1^668005/00 6/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
279641631-10119-DTLTRT-08_04_2022-GO95HV-1^668005/00 6/082 | OTHER | CA-NON-TIER | Transmission | 2022-08-04 | 2027-08-04 | 3
317226001-77119-ADMIN-08_05_2020-POLEDERP-1^668005/00 6/084 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
317226001-77119-DTLTRT-08_04_2022-GUYHINS-1^668005/00 6/084 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-04 | 2025-08-04 | 2
707259392-43319-ADMIN-06_15_2021-INSULDMG-1^668005/00 6/088 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
624826183-7419-DTLTRT-08_16_2022-POLETOP-1^668005/00 6/092 | POLE | CA-NON-TIER | Transmission | 2022-08-16 | 2025-08-16 | 2
282887671-95219-ADMIN-06_15_2021-INSULDMG-1^668005/00 7/086 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
521231512-69219-ADMIN-06_15_2021-INSULDMG-1^668005/00 7/087 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
521231512-69219-DTLTRT-08_15_2022-GO95HV-1^668005/00 7/087 | OTHER | CA-NON-TIER | Transmission | 2022-08-15 | 2027-08-15 | 3
683677398-90498-DETAIL-08_17_2022-GO95MLD-1^668005/00 7/094 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
676703974-10619-DTLTRT-08_17_2022-GO95MLD-1^668005/00 7/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
676703974-10619-DTLTRT-08_17_2022-UBPBCTGD-1^668005/00 7/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
612042055-71919-ADMIN-07_27_2021-INSULDMG-1^668005/00 7/096 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
612042055-71919-DTLTRT-08_17_2022-GO95HV-1^668005/00 7/096 | OTHER | FHCA | Transmission | 2022-08-17 | 2027-08-17 | 3
182791969-12969-DETAIL-08_02_2022-GO95HV-1^668005/00 7X/077 | OTHER | CA-NON-TIER | Transmission | 2022-08-02 | 2027-08-02 | 3
392890933-419-DTLTRT-08_16_2022-GO95HV-1^668005/00 9/090 | OTHER | CA-NON-TIER | Transmission | 2022-08-16 | 2027-08-16 | 3
16708513-8419-DTLTRT-08_16_2022-POLETOP-1^668005/00 9/092 | POLE | CA-NON-TIER | Transmission | 2022-08-16 | 2025-08-16 | 2
416147894-50619-DETAIL-08_17_2022-GO95HV-1^668005/00 9/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2027-08-17 | 3
416147894-50619-DETAIL-08_17_2022-GO95MLD-1^668005/00 9/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
416147894-50619-AUDIT-08_29_2022-GO95BLTC-1^668005/00 9/095 | OTHER | FHCA | Transmission | 2022-08-29 | 2025-08-29 | 2
620579949-16769-ADMIN-06_15_2021-POLEDERP-1^668005/03 10/004 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
597666959-46769-ADMIN-06_15_2021-POLEDERP-1^668005/03 11/004 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
257187213-46019-ADMIN-11_10_2020-POLEDERP-1^668036/00 10/055 | POLE | FHCA | Transmission | 2020-11-10 | 2023-11-10 | 2
926458488-88119-ADMIN-08_10_2021-XARMSPCR-1^668036/00 11/020 | CROSSARM | FHCA | Transmission | 2021-08-10 | 2024-08-10 | 2
751904989-7419-ADMIN-11_21_2022-POLEDERP-1^668036/00 12/045 | POLE | CA-TIER-2 | Transmission | 2022-11-21 | 2023-11-21 | 2
751904989-7419-ADMIN-11_21_2022-POLEDERP-2^668036/00 12/045 | POLE | CA-TIER-2 | Transmission | 2022-11-21 | 2023-11-21 | 2
682465129-52419-DETAIL-11_14_2023-INSULBRK-1^668036/00 14/044 | INSULATOR AND BUSHING | FHCA | Transmission | 2023-11-14 | 2026-11-14 | 2
5672018-40819-DETAIL-11_14_2023-INSULBRK-1^668036/00 17/050 | INSULATOR AND BUSHING | CA-TIER-2 | Transmission | 2023-11-14 | 2024-11-14 | 2
997723871-43649-DETAIL-02_28_2024-SVCENTCO-1^07113001.0031300 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
214507171-23649-DETAIL-02_28_2024-GUYHINS-1^07113001.0031303 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
791930641-37139-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0032100 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
773749771-81359-DETAIL-02_28_2024-SVCENTCO-1^07113001.0032301 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
854871461-30649-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0033100 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
320785503-68649-DETAIL-03_16_2023-GO95HV-1^07113001.0040403 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
112964341-62159-DETAIL-03_16_2023-ENCHRW-1^07113001.0040502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
112964341-62159-DETAIL-03_16_2023-SVCENTCO-1^07113001.0040502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
815207180-77149-DETAIL-03_16_2023-GO95MLD-1^07113001.0042500 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
836720470-15649-DETAIL-03_16_2023-GO95HV-1^07113001.0042501 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
836720470-15649-DETAIL-03_16_2023-GO95MLD-1^07113001.0042501 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
836720470-15649-DETAIL-03_16_2023-SVCROAD-1^07113001.0042501 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
329356333-73749-DETAIL-03_21_2023-GO95BLTC-1^07113001.0056600 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
997862064-51149-DETAIL-03_21_2023-ABNDEQPM-1^07113001.0057500 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
997862064-51149-DETAIL-03_21_2023-GO95HV-1^07113001.0057500 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
184699403-92749-DETAIL-03_21_2023-GO95MLD-1^07113001.0057503 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
151609833-20239-DETAIL-03_21_2023-GO95HV-1^07113001.0058501 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
151609833-20239-DETAIL-03_21_2023-GUYHINS-1^07113001.0058501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
488732093-51749-DETAIL-03_21_2023-GO95MLD-1^07113001.0058504 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
488732093-51749-DETAIL-03_21_2023-GUYHINS-1^07113001.0058504 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
612842733-92733-DETAIL-03_21_2023-GO95TCH-1^07113001.0058601 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
612842733-92733-DETAIL-03_21_2023-GUYHINS-1^07113001.0058601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
149165073-60749-DETAIL-03_21_2023-GO95MLD-1^07113001.0059400 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
901582313-749-DETAIL-03_16_2023-ABNDEQPM-1^07113001.0059502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
307226831-28339-DETAIL-02_29_2024-GO95MLD-1^07113001.0105600 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
328258788-85888-DETAIL-02_29_2024-GO95HV-1^07113001.0106302 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
887478488-45588-DETAIL-02_29_2024-GUYHINS-1^07113001.0106304 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
67527803-40139-DETAIL-02_29_2024-GO95HV-1^07113001.0106401 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
67527803-40139-DETAIL-02_29_2024-GO95MLD-1^07113001.0106401 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
337516513-67839-DETAIL-02_29_2024-GO95HV-1^07113001.0106402 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
117366371-52239-DETAIL-02_29_2024-GO95CL10-1^07113001.0106500 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
117366371-52239-DETAIL-02_29_2024-GO95HV-1^07113001.0106500 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
117366371-52239-DETAIL-02_29_2024-GO95MLD-1^07113001.0106500 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
62600083-35749-DETAIL-02_29_2024-GO95HV-1^07113001.0107001 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
180485763-61339-DETAIL-02_29_2024-GO95MLD-1^07113001.0107004 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
66506840-72359-DETAIL-02_29_2024-GO95MLD-1^07113001.0107100 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
670974361-20539-DETAIL-02_26_2024-GO95HV-1^07113001.0138302 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
616416651-25149-DETAIL-02_26_2024-GO95HV-1^07113001.0138306 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
616416651-25149-DETAIL-02_26_2024-GO95MLD-1^07113001.0138306 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
290267951-88049-DETAIL-02_26_2024-GO95MLD-1^07113001.0138307 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
814597151-71249-DETAIL-02_26_2024-GO95MLD-1^07113001.0138308 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
127744741-34239-DETAIL-02_21_2024-SVCROAD-1^07113001.0138309 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
16079080-39839-DETAIL-02_26_2024-GO95MLD-1^07113001.0138401 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
992805560-48539-DETAIL-02_26_2024-GO95MLD-1^07113001.0138402 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
992805560-48539-DETAIL-02_26_2024-SVCENTCO-1^07113001.0138402 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
992805560-48539-DETAIL-03_26_2024-GUYHINS-1^07113001.0138402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
992805560-48539-DETAIL-03_26_2024-SVCROAD-1^07113001.0138402 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
701983181-40149-DETAIL-02_26_2024-GO95HV-1^07113001.0138403 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
384843302-89359-DETAIL-02_21_2024-GO95HV-1^07113001.0144101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
384843302-89359-DETAIL-02_21_2024-RISEGRD-1^07113001.0144101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
957998302-94159-DETAIL-02_21_2024-GO95MLD-1^07113001.0144201 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
712679131-43249-DETAIL-02_21_2024-GO95MLD-1^07113001.0145101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
945118515-65113-DETAIL-02_21_2024-GO95CL10-1^07113001.0145200 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
222729661-93549-DETAIL-02_28_2024-GO95HV-1^07113001.0145701 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
343937712-91459-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0146000 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
343937712-91459-DETAIL-02_21_2024-SVCENTCO-1^07113001.0146000 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
119096861-43849-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0146001 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
212965171-49049-DETAIL-02_21_2024-GO95MLD-1^07113001.0146100 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
212965171-49049-DETAIL-02_21_2024-GRDRODHI-1^07113001.0146100 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
514348221-44091-DETAIL-02_21_2024-GO95MLD-1^07113001.0146101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
521970284-30049-ADMIN-03_18_2024-POLEDERP-1^07113001.0175500 | POLE | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
961298565-36949-DETAIL-02_26_2024-GO95MLD-1^07113001.0211401 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
961298565-36949-DETAIL-02_26_2024-SVCDEFLC-1^07113001.0211401 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
84455355-35049-DETAIL-02_26_2024-CUTOUTAR-1^07113001.0211403 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
84455355-35049-DETAIL-02_26_2024-CUTOUTAR-3^07113001.0211403 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
84455355-35049-DETAIL-02_26_2024-CUTOUTAR-4^07113001.0211403 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
420864735-17049-DETAIL-02_26_2024-SVCENTCO-1^07113001.0211500 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
620196125-55949-DETAIL-02_26_2024-GO95HV-1^07113001.0213400 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
620196125-55949-DETAIL-02_26_2024-GO95MLD-1^07113001.0213400 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
260933126-89249-DETAIL-02_27_2024-GO95TCH-1^07113002.0071100 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
373053625-46625-DETAIL-02_27_2024-GO95MLD-1^07113002.0071101 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
373053625-46625-DETAIL-02_27_2024-GRDRODHI-1^07113002.0071101 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
195720123-17959-DETAIL-02_20_2024-SVCENTCO-1^07113002.0181009 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
199370021-19639-DETAIL-02_21_2024-GO95MLD-1^07113002.0181101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
199370021-19639-DETAIL-02_21_2024-RISEBKSP-1^07113002.0181101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
431426942-21749-DETAIL-02_21_2024-GO95MLD-1^07113002.0181103 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
855908693-58249-DETAIL-02_20_2024-GO95HV-1^07113002.0181105 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
340630532-73049-DETAIL-02_20_2024-GO95MLD-1^07113002.0181106 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
448526701-82349-DETAIL-02_20_2024-GO95HV-1^07113002.0181109 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
448526701-82349-DETAIL-02_20_2024-GO95MLD-1^07113002.0181109 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
448526701-82349-DETAIL-02_20_2024-SVCDEFLC-1^07113002.0181109 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
911057563-38139-DETAIL-02_27_2024-GO95MLD-1^07113002.0181400 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
724282053-62049-DETAIL-02_27_2024-GO95MLD-1^07113002.0181402 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
760513813-69459-DETAIL-02_20_2024-GO95MLD-1^07113002.0182000 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
468051635-65539-DETAIL-02_27_2024-SVCENTCO-1^07113002.0183601 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
986062155-88349-DETAIL-02_27_2024-GO95MLD-1^07113002.0183703 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
484744975-43139-DETAIL-02_27_2024-GO95BLTC-1^07113002.0183704 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
484744975-43139-DETAIL-02_27_2024-GO95MLD-1^07113002.0183704 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
835565905-74349-DETAIL-02_27_2024-GO95HV-1^07113002.0183705 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2029-02-27 | 3
689148630-23559-DETAIL-02_19_2024-ENCHRW-1^07113002.0184001 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
560275999-57149-DETAIL-02_19_2024-GO95MLD-1^07113002.0184003 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
559179980-73349-DETAIL-02_19_2024-GO95MLD-1^07113002.0184101 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
559179980-73349-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0184101 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
253375880-64149-DETAIL-02_27_2024-SVCENTCO-1^07113002.0184102 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
886204799-74439-DETAIL-02_27_2024-GO95MLD-1^07113002.0184103 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
886204799-74439-DETAIL-02_27_2024-GRDRODHI-1^07113002.0184103 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
894508023-51559-DETAIL-02_20_2024-GO95MLD-1^07113002.0193901 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
79023173-83339-DETAIL-03_16_2023-GO95CL10-1^07114001.0205002 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
79023173-83339-DETAIL-03_16_2023-GO95HV-1^07114001.0205002 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
88577043-28649-DETAIL-03_16_2023-GUYHINS-1^07114001.0206000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
425749113-2259-DETAIL-03_20_2023-GO95TCH-1^07114001.0206001 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
480543533-27249-DETAIL-03_16_2023-GO95HV-1^07114001.0206003 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
487099943-38749-DETAIL-03_20_2023-GO95MLD-1^07114001.0206200 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
441659173-66249-DETAIL-03_20_2023-GO95HV-1^07114001.0206202 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
441659173-66249-DETAIL-03_20_2023-GO95MLD-1^07114001.0206202 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
86369793-60549-DETAIL-03_16_2023-GO95MLD-1^07114001.0208002 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
292566233-53339-DETAIL-03_14_2023-GO95HV-1^07114001.0275300 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
88859944-53044-DETAIL-03_14_2023-GUYHINS-1^07114001.0275400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
868530053-52249-DETAIL-03_14_2023-GO95HV-1^07114001.0276503 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
589498553-7639-DETAIL-03_14_2023-GO95MLD-1^07114001.0276504 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
108862643-61849-DETAIL-03_14_2023-GO95HV-1^07114001.0276505 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
368644463-54739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276506 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
532385693-15739-DETAIL-03_14_2023-GO95HV-1^07114001.0276600 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
532385693-15739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276600 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
169960563-349-DETAIL-03_14_2023-GO95MLD-1^07114001.0277501 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
198857413-20049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277502 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
894419123-49949-DETAIL-03_14_2023-CLRTOUCH-1^07114001.0277503 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
822486023-50049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277504 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
206702963-71049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277600 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
363564723-90049-DETAIL-03_14_2023-GO95HV-1^07114001.0277602 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
179295604-36649-DETAIL-03_16_2023-GO95MLD-1^07114001.0282402 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
713306043-44949-DETAIL-03_16_2023-GO95MLD-1^07114001.0282403 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
837571408-72408-DETAIL-03_16_2023-ABNDEQPM-1^07114001.0282604 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
4642574-99259-DETAIL-03_16_2023-GO95HV-1^07114001.0282640 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
506249154-80149-DETAIL-03_16_2023-GO95MLD-1^07114001.0283304 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
277786744-81149-DETAIL-03_16_2023-ABNDEQPM-1^07114001.0283305 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
434662124-23539-DETAIL-03_20_2023-GO95MLD-1^07114001.0283307 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
356717214-12149-DETAIL-03_16_2023-GO95HV-1^07114001.0283308 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
356717214-12149-DETAIL-03_16_2023-GO95MLD-1^07114001.0283308 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
356717214-12149-DETAIL-03_16_2023-GUYHINS-1^07114001.0283308 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
454528524-24549-DETAIL-03_20_2023-GO95HV-1^07114001.0283402 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
454528524-24549-DETAIL-03_20_2023-GO95MLD-1^07114001.0283402 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
455857225-69749-DETAIL-03_15_2023-GUYNOINS-1^07114001.0326201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
513733185-48749-DETAIL-03_15_2023-GO95HV-1^07114001.0327000 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
165347305-84449-DETAIL-03_15_2023-GO95MLD-1^07114001.0328001 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
130421324-97449-DETAIL-03_15_2023-GO95MLD-1^07114001.0335900 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
130421324-97449-DETAIL-03_15_2023-SVCENTCO-1^07114001.0335900 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
296176934-65049-DETAIL-03_15_2023-CLRTOUCH-1^07114001.0336900 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
324983414-17849-DETAIL-03_15_2023-GO95TCH-1^07114001.0338500 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
850691204-5139-AUDIT-03_22_2023-GO95HV-1^07114001.0338501 | OTHER | CA-NON-TIER | Distribution | 2023-03-22 | 2028-03-22 | 3
105178184-98849-DETAIL-03_15_2023-GO95HV-1^07114001.0339404 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
8523504-18849-DETAIL-03_15_2023-GO95HV-1^07114001.0339500 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
8523504-18849-DETAIL-03_15_2023-GO95MLD-1^07114001.0339500 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
933778517-3739-DETAIL-03_15_2023-GUYHINS-1^07114001.0340800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
419236908-89459-DETAIL-05_16_2022-GO95MLD-1^07116001.0059200 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
80552008-559-DETAIL-05_16_2022-GO95MLD-1^07116001.0059300 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
80552008-559-DETAIL-05_16_2022-POLETOP-1^07116001.0059300 | POLE | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
165995738-7459-DETAIL-05_10_2022-SVCRUBLG-1^07116001.0059302 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
334590248-28459-DETAIL-05_10_2022-GO95TCH-1^07116001.0059340 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
381276728-17728-DETAIL-05_10_2022-GO95TCH-1^07116001.0059342 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
376564181-56249-DETAIL-05_16_2022-GO95MLD-1^07116001.0090801 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
376564181-56249-DETAIL-05_16_2022-SVCNEUT-1^07116001.0090801 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
635358990-15359-DETAIL-05_16_2022-ABNDEQPM-1^07116001.0090900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
635358990-15359-DETAIL-05_16_2022-GO95TCH-1^07116001.0090900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
635358990-15359-DETAIL-05_16_2022-GUYSLACK-1^07116001.0090900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
971116123-17159-DETAIL-05_16_2022-GO95MLD-1^07116001.0090902 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
833596979-34559-DETAIL-05_10_2022-GO95CL10-1^07116001.0091400 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
833596979-34559-DETAIL-05_10_2022-GO95MLD-1^07116001.0091400 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
80643456-25012-DETAIL-05_10_2022-GO95HV-1^07116001.0091401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
730114300-21449-DETAIL-04_28_2022-GO95MLD-1^07116001.0093301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
730114300-21449-DETAIL-04_28_2022-GO95TCH-1^07116001.0093301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
730114300-21449-DETAIL-04_28_2022-SVCNEUT-1^07116001.0093301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
695534121-18943-DETAIL-05_12_2022-GO95CL10-1^07116001.0093700 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
695534121-18943-DETAIL-05_12_2022-GO95MLD-1^07116001.0093700 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
695534121-18943-DETAIL-05_12_2022-SVCNEUT-1^07116001.0093700 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
751786131-40331-DETAIL-05_12_2022-GO95TCH-1^07116001.0093800 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
223592381-4481-DETAIL-05_10_2022-GO95MLD-1^07116001.0093801 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
740926443-96608-DETAIL-04_28_2022-GO95MLD-1^07116001.0094401 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
409291071-86559-DETAIL-04_28_2022-GO95MLD-1^07116001.0094402 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
409291071-86559-DETAIL-04_28_2022-GO95TCH-1^07116001.0094402 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
984181048-13048-DETAIL-05_10_2022-GO95MLD-1^07116001.0094700 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
611870848-33848-DETAIL-05_12_2022-GO95HV-1^07116001.0094800 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2027-05-12 | 3
611870848-33848-DETAIL-05_12_2022-GO95MLD-1^07116001.0094800 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
18885208-56208-DETAIL-05_10_2022-GO95HV-1^07116001.0094901 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2027-05-10 | 3
315901943-16198-DETAIL-05_09_2022-GO95MLD-1^07116001.0096207 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
315901943-16198-DETAIL-05_09_2022-SVCROAD-1^07116001.0096207 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
734857843-51468-DETAIL-05_09_2022-GO95MLD-1^07116001.0096300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
734857843-51468-DETAIL-05_09_2022-SVCROAD-1^07116001.0096300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
126883506-31878-DETAIL-05_09_2022-GO95MLD-1^07116001.0096301 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
539603843-36058-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096302 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
864265743-51459-DETAIL-04_28_2022-GO95HV-1^07116001.0096304 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
864265743-51459-DETAIL-04_28_2022-GO95MLD-1^07116001.0096304 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
872480471-9949-DETAIL-05_09_2022-GO95TCH-1^07116001.0097200 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
308716221-45659-DETAIL-05_09_2022-GO95HV-1^07116001.0097300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
308716221-45659-DETAIL-05_09_2022-GO95MLD-1^07116001.0097300 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
447676106-40318-DETAIL-05_09_2022-GO95MLD-1^07116001.0098104 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
299736571-91339-DETAIL-05_09_2022-GO95MLD-1^07116001.0098201 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
646120280-75759-DETAIL-05_02_2022-GO95TCH-1^07116001.0168903 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
561053634-3551-DETAIL-07_10_2023-GO95HV-1^07117001.0246040 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2028-07-10 | 3
561053634-3551-DETAIL-07_10_2023-GO95MLD-1^07117001.0246040 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
198454184-830-DETAIL-07_10_2023-GO95CL10-1^07117001.0246102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2028-07-10 | 3
198454184-830-DETAIL-07_10_2023-GO95TCH-1^07117001.0246102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
198454184-830-DETAIL-07_10_2023-SVCNEUT-1^07117001.0246102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
290790174-2530-DETAIL-07_10_2023-GO95MLD-1^07117001.0246103 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
108732244-12649-DETAIL-07_10_2023-GO95MLD-1^07117001.0247002 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
922762764-67922-DETAIL-07_10_2023-GO95MLD-1^07117001.0247101 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
447153654-57401-DETAIL-07_10_2023-GO95MLD-1^07117001.0247102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
447153654-57401-DETAIL-07_10_2023-GO95TCH-1^07117001.0247102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
145929694-69759-DETAIL-05_17_2022-GO95HV-1^07117001.0319403 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2027-05-17 | 3
145929694-69759-DETAIL-05_17_2022-GO95MLD-1^07117001.0319403 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
408639764-74249-DETAIL-05_17_2022-GO95MLD-1^07117001.0319404 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
722138114-70249-DETAIL-05_11_2022-GO95MLD-1^07117001.0320404 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
996638334-46259-DETAIL-05_17_2022-ABNDEQPM-1^07117001.0320500 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2027-05-17 | 3
996638334-46259-DETAIL-05_17_2022-GO95TCH-1^07117001.0320500 | OTHER | CA-TIER-2 | Distribution | 2022-05-17 | 2025-05-17 | 2
499339703-9149-DETAIL-05_11_2022-GO95HV-1^07117001.0321401 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
416974133-39259-DETAIL-05_11_2022-GO95MLD-1^07117001.0326001 | OTHER | CA-NON-TIER | Distribution | 2022-05-11 | 2025-05-11 | 2
632915828-67259-DETAIL-03_08_2023-GO95HV-1^07117002.0193200 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
632915828-67259-DETAIL-03_08_2023-GO95MLD-1^07117002.0193200 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
357617035-74533-DETAIL-03_01_2023-GO95MLD-1^07117002.0197206 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
357617035-74533-DETAIL-03_01_2023-SVCNEUT-1^07117002.0197206 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
926416705-21733-ADMIN-11_16_2023-POLEREPL-1^07117002.0197241 | POLE | CA-TIER-2 | Distribution | 2023-11-16 | 2024-11-16 | 2
895347715-62833-DETAIL-03_01_2023-GO95MLD-1^07117002.0197300 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
895347715-62833-DETAIL-03_01_2023-RISESTRP-1^07117002.0197300 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
647060875-60059-DETAIL-03_01_2023-GO95MLD-1^07117002.0197301 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
213072049-40059-DETAIL-03_01_2023-GO95MLD-1^07117002.0197303 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
213072049-40059-DETAIL-03_01_2023-GO95TCH-1^07117002.0197303 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
136285215-42833-DETAIL-03_08_2023-GO95MLD-1^07117002.0198000 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
136285215-42833-DETAIL-03_08_2023-GO95TCH-1^07117002.0198000 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
747716725-92433-DETAIL-03_02_2023-GO95MLD-1^07117002.0198200 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
877089521-15673-DETAIL-03_02_2023-GO95MLD-1^07117002.0202200 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
970224274-30374-DETAIL-03_02_2023-GO95MLD-1^07117002.0202300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
883143271-53473-DETAIL-03_02_2023-GO95MLD-1^07117002.0202304 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
902648611-38473-DETAIL-03_09_2023-GO95MLD-1^07117002.0203207 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
322350681-31173-DETAIL-03_02_2023-GO95CL10-1^07117002.0203300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
322350681-31173-DETAIL-03_02_2023-GO95MLD-1^07117002.0203300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
304370581-56259-DETAIL-03_02_2023-GO95CL10-1^07117002.0203301 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
304370581-56259-DETAIL-03_02_2023-GO95MLD-1^07117002.0203301 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
426436061-92773-DETAIL-03_06_2023-ENCHRW-1^07117002.0204200 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
621144343-72831-DETAIL-03_02_2023-GO95HV-1^07117002.0204203 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
583430443-6059-DETAIL-03_06_2023-GO95MLD-1^07117002.0204204 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2028-03-06 | 3
738547461-58939-DETAIL-03_02_2023-GO95MLD-1^07117002.0204300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
448681668-16549-DETAIL-03_09_2023-GRDRODHI-1^07117002.0207242 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
425781908-64143-DETAIL-03_06_2023-GO95MLD-1^07117002.0207301 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
789754329-56973-DETAIL-03_08_2023-GO95BLTC-1^07117002.0207501 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
789754329-56973-DETAIL-03_08_2023-GUYHINS-1^07117002.0207501 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
217644519-85973-DETAIL-03_08_2023-GO95MLD-1^07117002.0207600 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
679755679-33173-DETAIL-03_08_2023-GO95HV-1^07117002.0207601 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
679755679-33173-DETAIL-03_08_2023-GO95MLD-1^07117002.0207601 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
679755679-33173-DETAIL-03_08_2023-GUYHINS-1^07117002.0207601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
703212619-99039-DETAIL-03_08_2023-GO95MLD-1^07117002.0207602 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
703212619-99039-DETAIL-03_08_2023-SVCNEUT-1^07117002.0207602 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
973861359-59073-DETAIL-03_07_2023-GO95MLD-1^07117002.0207802 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
973861359-59073-DETAIL-03_07_2023-GO95TCH-1^07117002.0207802 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
698817181-55620-DETAIL-03_07_2023-SVCENTCO-1^07117002.0210501 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
734980971-90620-DETAIL-03_07_2023-GO95MLD-1^07117002.0210600 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
515793731-53743-DETAIL-03_07_2023-GO95MLD-1^07117002.0210700 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
490214021-25320-DETAIL-03_08_2023-GRDRODHI-1^07117002.0211101 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
520050671-52620-DETAIL-03_08_2023-GO95MLD-1^07117002.0211102 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
897080301-6720-DETAIL-03_08_2023-GO95MLD-1^07117002.0211104 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
897080301-6720-DETAIL-03_08_2023-SVCNEUT-1^07117002.0211104 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
274668501-23720-DETAIL-03_08_2023-GO95MLD-1^07117002.0211200 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
642869331-92920-DETAIL-03_07_2023-GO95MLD-1^07117002.0211201 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
423746651-49420-DETAIL-03_07_2023-GRDRODHI-1^07117002.0211300 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
648813343-55018-DETAIL-03_08_2023-GO95MLD-1^07117002.0212002 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
648813343-55018-DETAIL-03_08_2023-GO95TCH-1^07117002.0212002 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
64858865-13663-DETAIL-04_24_2023-GO95MLD-1^07117003.0024101 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
127965075-11763-DETAIL-04_24_2023-GO95HV-1^07117003.0025100 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
808836875-98663-DETAIL-04_24_2023-GO95HV-1^07117003.0025101 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
808836875-98663-DETAIL-04_24_2023-GO95MLD-1^07117003.0025101 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
614323785-25459-DETAIL-04_24_2023-GO95MLD-1^07117003.0027300 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
311428785-55459-DETAIL-04_24_2023-GO95HV-1^07117003.0027401 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
311428785-55459-DETAIL-04_24_2023-GO95MLD-1^07117003.0027401 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
76168385-6459-DETAIL-04_24_2023-GO95MLD-1^07117003.0028500 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
465628368-26459-DETAIL-04_24_2023-GO95MLD-1^07117003.0029700 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
536760575-28663-DETAIL-04_24_2023-GO95MLD-1^07117003.0082400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
536760575-28663-DETAIL-04_24_2023-GO95TCH-1^07117003.0082400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
241598765-49765-DETAIL-04_24_2023-GO95MLD-1^07117003.0082401 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
360032933-46313-DETAIL-02_28_2024-GRDBROKE-1^07215001.0025200 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
763272733-7503-DETAIL-02_28_2024-GO95HV-1^07215001.0025500 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
953053115-20733-DETAIL-02_28_2024-GO95MLD-1^07215001.0025900 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
749805351-33351-ADMIN-06_19_2024-POLEDERP-1^07216001.0020903 | POLE | CA-NON-TIER | Distribution | 2024-06-19 | 2027-06-19 | 2
547525541-10939-DTLSB-04_07_2022-GO95HV-1^07216001.0033108 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
547525541-10939-DTLSB-04_07_2022-GO95MLD-1^07216001.0033108 | OTHER | CA-NON-TIER | Distribution | 2022-04-07 | 2027-04-07 | 3
547525541-10939-ADMIN-07_01_2024-POLEDERP-1^07216001.0033108 | POLE | CA-NON-TIER | Distribution | 2024-07-01 | 2027-07-01 | 2
825490209-91482-ADMIN-04_07_2023-DISTHDWR-1^07216001.0093204 | CONNECTION DEVICE | CA-NON-TIER | Distribution | 2023-04-07 | 2026-04-07 | 2
323781251-6970-ADMIN-10_23_2023-POLEDERP-1^07216001.0101502 | POLE | CA-NON-TIER | Distribution | 2023-10-23 | 2026-10-23 | 2
798102931-89859-ADMIN-10_23_2023-POLEDERP-1^07216001.0104301 | POLE | CA-NON-TIER | Distribution | 2023-10-23 | 2026-10-23 | 2
42777973-35259-ADMIN-09_18_2024-POLEDERP-1^07216001.0186300 | POLE | CA-NON-TIER | Distribution | 2024-09-18 | 2024-12-17 | 1
927266724-59759-DTLSB-02_13_2024-GO95HV-1^07216001.0186400 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
927266724-59759-DTLSB-02_13_2024-GO95MLD-1^07216001.0186400 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
167019395-60759-DTLSB-02_14_2024-GO95CL10-1^07216001.0187000 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
167019395-60759-DTLSB-02_14_2024-GO95HV-1^07216001.0187000 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
167019395-60759-DTLSB-02_14_2024-GO95MLD-1^07216001.0187000 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
976304913-40339-DTLSB-02_13_2024-GO95MLD-1^07216001.0187001 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
960727683-49949-DTLSB-02_13_2024-GO95MLD-1^07216001.0187002 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
561860473-68659-DTLSB-02_13_2024-GO95MLD-1^07216001.0187100 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
835450348-97049-DTLSB-02_13_2024-GO95MLD-1^07216001.0187102 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
835450348-97049-DTLSB-02_13_2024-SVCROAD-1^07216001.0187102 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
835450348-97049-AUDIT-03_07_2024-GO95HV-1^07216001.0187102 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2029-03-07 | 3
281994298-74359-DTLSB-02_15_2024-GO95MLD-1^07216001.0190800 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
603963619-42759-DTLSB-02_05_2024-GO95HV-1^07216001.0190900 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2029-02-05 | 3
603963619-42759-DTLSB-02_05_2024-GO95MLD-1^07216001.0190900 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
149373461-62028-DTLSB-02_05_2024-CLMBTRE-1^07216001.0190901 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
149373461-62028-DTLSB-02_05_2024-GO95MLD-1^07216001.0190901 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
149373461-62028-DTLSB-02_05_2024-GRDRODHI-1^07216001.0190901 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
149373461-62028-DTLSB-02_05_2024-GRDRODHI-2^07216001.0190901 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
924946629-34359-DTLSB-02_05_2024-SVCDEFLC-1^07216001.0190902 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
225078549-1759-DTLSB-02_05_2024-GO95HV-1^07216001.0190940 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2029-02-05 | 3
513501988-33359-DTLSB-02_15_2024-GO95MLD-1^07216001.0191600 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
671878178-24359-DTLSB-02_15_2024-GO95HV-1^07216001.0191601 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
503422719-31939-DTLSB-02_15_2024-GO95MLD-1^07216001.0191800 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
797069888-73259-DTLSB-02_08_2024-SVCDEFLC-1^07216001.0197101 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
116811934-67449-DTLSB-02_08_2024-GO95MLD-1^07216001.0197103 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
248581834-76139-DTLSB-02_08_2024-GO95MLD-1^07216001.0197141 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2029-02-08 | 3
983409784-19449-DTLSB-02_08_2024-GO95MLD-1^07216001.0198002 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
983409784-19449-DTLSB-02_08_2024-GRDRODHI-1^07216001.0198002 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
890968648-28428-DTLSB-02_08_2024-GO95MLD-1^07216001.0198004 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
222465394-44549-DTLSB-02_08_2024-SVCROAD-1^07216001.0198100 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
96151026-40563-DTLSB-02_08_2024-GO95MLD-1^07216001.0198101 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
302094694-59449-DTLSB-02_08_2024-GO95HV-1^07216001.0198105 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2029-02-08 | 3
838822124-44939-DTLSB-02_08_2024-GUYHINS-1^07216001.0198201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
244721766-80939-DTLSB-02_08_2024-CLMBTRE-1^07216001.0198203 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
393091148-81840-DTLSB-02_14_2024-SVCENTCO-1^07216001.0198240 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
102067443-80759-DTLSB-02_14_2024-GO95MLD-1^07216001.0198903 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
195219034-54959-DTLSB-02_13_2024-GO95HV-1^07216001.0198904 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
195219034-54959-DTLSB-02_13_2024-GO95MLD-1^07216001.0198904 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
989235551-17551-DTLSB-02_14_2024-GO95MLD-1^07216001.0198920 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
908881874-5939-DTLSB-02_07_2024-GO95CL10-1^07216001.0199001 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2029-02-07 | 3
908881874-5939-AUDIT-02_27_2024-GO95MLD-1^07216001.0199001 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
452392564-21349-DTLSB-02_07_2024-GO95MLD-1^07216001.0199002 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
781405174-21549-DTLSB-02_07_2024-GO95HV-1^07216001.0199100 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2029-02-07 | 3
972195474-19849-DTLSB-02_07_2024-GO95MLD-1^07216001.0199101 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
646499344-38839-DTLSB-02_07_2024-GO95MLD-1^07216001.0199102 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2029-02-07 | 3
702396634-13149-DTLSB-02_07_2024-GO95MLD-1^07216001.0199103 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
702396634-13149-DTLSB-02_07_2024-SVCENTCO-1^07216001.0199103 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
76659464-44239-DTLSB-02_07_2024-GO95TCH-1^07216001.0199307 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
102159314-35549-DTLSB-02_07_2024-GUYNOINS-1^07216001.0199309 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
806099764-88039-DTLSB-02_07_2024-SVCENTBK-1^07216001.0199310 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
244608974-87539-DTLSB-02_07_2024-SVCENTCO-1^07216001.0199400 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
118551294-67649-DTLSB-02_07_2024-SVCDEFLC-1^07216001.0199402 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
912987684-5549-DTLSB-02_07_2024-GUYHINS-1^07216001.0199403 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
979332764-20203-DTLSB-02_07_2024-GO95MLD-1^07216001.0199405 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
160407028-14549-DTLSB-02_07_2024-GO95MLD-1^07216001.0199406 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2029-02-07 | 3
160407028-14549-DTLSB-02_07_2024-SVCENTCO-1^07216001.0199406 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
160407028-14549-DTLSB-02_07_2024-SVCENTCO-2^07216001.0199406 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
638703644-53644-DTLSB-02_07_2024-SVCENTCO-1^07216001.0199408 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
359777726-71449-DTLSB-02_13_2024-GO95HV-1^07216001.0199701 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
432056949-10049-DETAIL-02_19_2024-CLRTOUCH-1^07216001.0260302 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
115101351-53059-DTLSB-02_20_2024-GO95MLD-1^07216001.0260306 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
653704330-34739-DTLSB-02_20_2024-GO95MLD-1^07216001.0260308 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
879419221-80059-DTLSB-02_20_2024-GO95MLD-1^07216001.0260309 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
802999629-68349-DTLSB-02_20_2024-GO95MLD-1^07216001.0260340 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
422242131-6949-DTLSB-02_20_2024-GO95MLD-1^07216001.0260400 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
318847281-94559-DTLSB-02_20_2024-GO95MLD-1^07216001.0260401 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
73109728-24849-DTLSB-02_20_2024-GO95TCH-1^07216001.0260502 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
55956259-84749-DTLSB-02_20_2024-SVCENTCO-1^07216001.0260503 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
55956259-84749-DTLSB-02_20_2024-SVCENTCO-2^07216001.0260503 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
946597859-94749-DTLSB-02_20_2024-GO95MLD-1^07216001.0260504 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
2232698-83849-DTLSB-02_20_2024-GO95MLD-1^07216001.0260506 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
986800988-82539-DTLSB-02_28_2024-GO95TCH-1^07216001.0260903 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
986800988-82539-DTLSB-02_28_2024-SVCENTBK-1^07216001.0260903 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
798254478-70539-DTLSB-02_27_2024-GO95HV-1^07216001.0260904 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
798254478-70539-DTLSB-02_27_2024-GO95MLD-1^07216001.0260904 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
798254478-70539-DTLSB-02_27_2024-GUYHINS-1^07216001.0260904 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
129216988-42849-DTLSB-02_28_2024-GO95MLD-1^07216001.0260905 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
675217289-8449-DTLSB-02_28_2024-GO95MLD-1^07216001.0260906 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
196473578-91849-DTLSB-02_27_2024-GO95MLD-1^07216001.0260908 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
196473578-91849-DTLSB-02_27_2024-GO95TCH-1^07216001.0260908 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
814516068-78749-DTLSB-02_26_2024-GO95MLD-1^07216001.0260909 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
515592158-19449-DTLSB-02_26_2024-GO95MLD-1^07216001.0260910 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
373577588-12688-DTLSB-02_28_2024-CLMBTRE-1^07216001.0260912 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
808313579-75949-DTLSB-02_19_2024-GO95HV-1^07216001.0261206 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2029-02-19 | 3
831014640-6149-DTLSB-02_19_2024-GO95MLD-1^07216001.0261300 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
698533430-58339-DTLSB-02_19_2024-SVCROAD-1^07216001.0261303 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
930922700-18349-DTLSB-02_20_2024-GO95HV-1^07216001.0261304 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
930922700-18349-DTLSB-02_20_2024-GO95MLD-1^07216001.0261304 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
260016890-63739-DTLSB-02_20_2024-GO95CLSV-1^07216001.0261307 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
260016890-63739-DTLSB-02_20_2024-SVCDEFLC-1^07216001.0261307 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
260016890-63739-DTLSB-02_20_2024-SVCWIND-1^07216001.0261307 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
921316711-20559-DETAIL-02_20_2024-GO95MLD-1^07216001.0261309 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
843191949-74949-DTLSB-02_19_2024-SVCROAD-1^07216001.0261310 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
81946208-55849-DTLSB-02_21_2024-GO95HV-1^07216001.0261400 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
81946208-55849-DTLSB-02_21_2024-GO95MLD-1^07216001.0261400 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
200227850-81740-DTLSB-02_16_2024-GO95MLD-1^07216001.0262100 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
171892471-4559-DTLSB-02_16_2024-ABNDEQPM-1^07216001.0262101 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
142370520-52559-DTLSB-02_19_2024-SVCWIND-1^07216001.0262102 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
274746750-60749-DTLSB-02_19_2024-GO95TCH-1^07216001.0262103 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
349930450-23890-DTLSB-02_16_2024-GO95MLD-1^07216001.0262105 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
349930450-23890-DTLSB-02_16_2024-SVCROAD-1^07216001.0262105 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
944678571-39959-DTLSB-02_16_2024-SVCENTCO-1^07216001.0262106 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
28290161-76159-DTLSB-02_16_2024-GO95MLD-1^07216001.0262108 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
737492780-48149-DTLSB-02_16_2024-GO95MLD-1^07216001.0262200 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
99160080-38949-DTLSB-02_16_2024-GO95HV-1^07216001.0262201 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
99160080-38949-DTLSB-02_16_2024-GO95MLD-1^07216001.0262201 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
584361860-83949-DTLSB-02_16_2024-GO95MLD-1^07216001.0262202 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
594062198-59339-DTLSB-02_22_2024-GO95MLD-1^07216001.0262902 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
913840302-72659-DTLSB-02_22_2024-SVCDEFLC-1^07216001.0262903 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
135246418-32658-DTLSB-02_15_2024-GO95HV-1^07216001.0263000 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
135246418-32658-DTLSB-02_15_2024-GO95MLD-1^07216001.0263000 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
519642461-72849-DTLSB-02_15_2024-GO95MLD-1^07216001.0263001 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
158036360-32949-DTLSB-02_16_2024-GO95MLD-1^07216001.0263100 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
77077040-41249-DTLSB-02_16_2024-GO95MLD-1^07216001.0263101 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
909582380-84949-DTLSB-02_16_2024-GO95MLD-1^07216001.0263102 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
356576830-12839-DTLSB-02_16_2024-SVCDEFLC-1^07216001.0263201 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
356576830-12839-DTLSB-02_16_2024-SVCENTCO-1^07216001.0263201 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
356576830-12839-DTLSB-02_16_2024-SVCENTCO-2^07216001.0263201 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
532953750-36749-DTLSB-02_16_2024-GO95HV-1^07216001.0263202 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
179905773-14720-DTLSB-02_19_2024-GO95CL10-1^07216001.0264206 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2029-02-19 | 3
179905773-14720-DTLSB-02_19_2024-SVCROAD-1^07216001.0264206 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
179905773-14720-DTLSB-02_19_2024-SVCROAD-2^07216001.0264206 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
229935828-9828-DTLSB-02_19_2024-GO95TCH-1^07216001.0264207 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
229935828-9828-DTLSB-02_19_2024-SVCENTBK-1^07216001.0264207 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
305758070-74139-DTLSB-02_15_2024-GO95MLD-1^07216001.0264301 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
444321159-17949-DTLSB-02_15_2024-GO95MLD-1^07216001.0264302 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
882410783-62783-DTLSB-02_15_2024-GO95MLD-1^07216001.0264305 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
903554579-94449-DTLSB-02_21_2024-CLMBTRE-1^07216001.0264500 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
903554579-94449-DTLSB-02_21_2024-GO95MLD-1^07216001.0264500 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
799592365-89082-DTLSB-02_19_2024-GO95MLD-1^07216001.0264501 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
907159768-1439-DTLSB-02_19_2024-GO95HV-1^07216001.0264800 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2029-02-19 | 3
604911673-55449-DTLSB-02_28_2024-SVCENTCO-2^07216001.0272700 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
196294883-84659-DTLSB-02_28_2024-CLMBTRE-1^07216001.0272702 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
807159533-92139-DTLSB-02_27_2024-SVCDEFLC-1^07216001.0272706 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
964772313-239-DTLSB-02_28_2024-GO95HV-1^07216001.0273701 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
242586393-59049-DTLSB-02_28_2024-GO95CL10-1^07216001.0273702 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
242586393-59049-DTLSB-02_28_2024-GO95HV-1^07216001.0273702 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
242586393-59049-DTLSB-02_28_2024-GO95MLD-1^07216001.0273702 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
788326686-68686-DTLSB-02_28_2024-GO95TCH-1^07216001.0273801 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
788326686-68686-DTLSB-02_28_2024-SVCDEFLC-1^07216001.0273801 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
788326686-68686-DTLSB-02_28_2024-SVCDEFLC-2^07216001.0273801 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
781998247-95210-DTLSB-02_28_2024-GO95MLD-1^07216001.0273802 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
607941247-37246-DTLSB-02_27_2024-GO95MLD-1^07216001.0273805 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
897082444-58149-DTLSB-02_26_2024-SVCROAD-1^07216001.0277806 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
180437034-78149-DTLSB-02_26_2024-GO95MLD-1^07216001.0277807 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
691427064-60439-DTLSB-02_26_2024-SVCENTCO-1^07216001.0277901 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
16452998-69521-DTLSB-02_26_2024-SVCDEFLC-1^07216001.0277903 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
73088473-87549-DTLSB-02_26_2024-CLMBTRE-1^07216001.0277907 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
73088473-87549-DTLSB-02_26_2024-GO95HV-1^07216001.0277907 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
73088473-87549-DTLSB-02_26_2024-SVCROAD-1^07216001.0277907 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
92059004-83449-DTLSB-02_26_2024-GO95MLD-1^07216001.0277908 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
752281574-89649-DTLSB-02_26_2024-GO95HV-1^07216001.0277909 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
640357578-28578-DTLSB-02_26_2024-SVCWIND-1^07216001.0277910 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
521592954-85528-DTLSB-02_27_2024-GO95MLD-1^07216001.0278600 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
727217873-80939-DTLSB-02_27_2024-GO95MLD-1^07216001.0278702 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
883600687-86418-DTLSB-02_22_2023-RISEGRD-1^07216001.0280704 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
397733413-24413-DTLSB-02_21_2023-SVCROAD-1^07216001.0280730 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
973929126-88483-DETAIL-02_21_2023-SVCWIND-1^07216001.0280770 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
189436485-8049-DTLSB-02_21_2023-GO95MLD-1^07216001.0281602 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
189436485-8049-DTLSB-02_21_2023-SVCENTCO-1^07216001.0281602 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
478108386-5439-DTLSB-02_21_2023-GO95MLD-1^07216001.0281604 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
676429458-75461-DTLSB-02_21_2023-SVCENTBK-1^07216001.0281640 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
676429458-75461-DTLSB-02_21_2023-SVCWIND-1^07216001.0281640 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
219486106-88339-DTLSB-02_21_2023-GO95MLD-1^07216001.0281701 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
42210456-15540-DTLSB-02_21_2023-CLMBTRE-1^07216001.0281704 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
42210456-15540-DTLSB-02_21_2023-GO95MLD-1^07216001.0281704 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
303930566-65749-DTLSB-02_21_2023-GO95MLD-1^07216001.0281800 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
964498435-54933-DTLSB-02_22_2023-GO95TCH-1^07216001.0287804 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
365479595-81439-DTLSB-02_22_2023-GO95MLD-1^07216001.0287805 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
3262142-92142-DETAIL-02_22_2023-GO95TCH-1^07216001.0287806 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
788226370-97370-DTLSB-02_22_2023-GO95MLD-1^07216001.0288601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
788226370-97370-DTLSB-02_22_2023-SVCENTCO-1^07216001.0288601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
580233085-84649-DTLSB-02_22_2023-GO95MLD-1^07216001.0288700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
549280546-77549-DTLSB-02_22_2023-GO95MLD-1^07216001.0288702 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
882908585-54939-DTLSB-02_22_2023-GO95MLD-1^07216001.0289102 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
901166670-69098-DTLSB-02_22_2023-GO95HV-1^07216001.0289601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
715538570-10670-DTLSB-02_22_2023-GO95MLD-1^07216001.0289604 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
74397256-37643-DTLSB-02_22_2023-GO95MLD-1^07216001.0289700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
743978495-77849-DETAIL-03_15_2023-SVCENTBK-1^07216001.0290501 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
306982009-50859-DETAIL-03_13_2023-SVCENTBK-1^07216001.0290740 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
931883049-98759-DETAIL-03_01_2023-SVCENTCO-1^07216001.0290743 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
265340104-22849-DETAIL-03_13_2023-SVCWIND-1^07216001.0290800 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
487839993-8049-DETAIL-03_13_2023-GO95MLD-1^07216001.0290801 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
812843183-94649-DETAIL-03_13_2023-GO95MLD-1^07216001.0290802 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
192489763-49139-DETAIL-03_15_2023-GO95MLD-1^07216001.0290804 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
930444453-52939-DETAIL-03_13_2023-GO95MLD-1^07216001.0290805 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
845084755-18939-DETAIL-03_02_2023-GO95MLD-1^07216001.0290902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
845084755-18939-DETAIL-03_02_2023-GO95MLD-2^07216001.0290902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
83265633-88249-DETAIL-03_15_2023-GO95MLD-1^07216001.0291500 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
83265633-88249-DETAIL-03_15_2023-GUYHINS-1^07216001.0291500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
150328463-3049-DETAIL-03_15_2023-GUYHINS-1^07216001.0291501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
321491353-77759-DETAIL-03_02_2023-GO95HV-1^07216001.0291708 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
239740469-37459-DETAIL-03_01_2023-SVCWIND-1^07216001.0291740 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
907066233-56649-DETAIL-03_13_2023-GO95MLD-1^07216001.0291800 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
17211054-18549-DETAIL-03_01_2023-SVCNEUT-1^07216001.0291801 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
885032364-55839-DETAIL-03_01_2023-GO95CL10-1^07216001.0291802 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
885032364-55839-DETAIL-03_01_2023-GO95MLD-1^07216001.0291802 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
885032364-55839-DETAIL-03_01_2023-GO95TCH-1^07216001.0291802 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
505698263-23239-DETAIL-03_02_2023-GO95MLD-1^07216001.0291803 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
628960783-67049-DETAIL-03_01_2023-GO95MLD-1^07216001.0291804 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
628960783-67049-DETAIL-03_01_2023-SVCWIND-1^07216001.0291804 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
252371009-86009-DETAIL-03_01_2023-SVCWIND-1^07216001.0291820 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
484229379-87459-DETAIL-03_01_2023-GO95MLD-1^07216001.0291840 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
51453459-50559-DETAIL-03_01_2023-SVCWIND-1^07216001.0292541 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
51453459-50559-DETAIL-03_01_2023-SVCWIND-2^07216001.0292541 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
139682759-21859-DETAIL-03_13_2023-SVCENTCO-1^07216001.0292544 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
226594413-6649-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0292600 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
226594413-6649-DETAIL-03_01_2023-GO95MLD-1^07216001.0292600 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
865940103-93649-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0292601 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
351381593-14239-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0292602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
351381593-14239-DETAIL-03_01_2023-GO95MLD-1^07216001.0292602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
351381593-14239-DETAIL-03_01_2023-GO95TCH-1^07216001.0292602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
505764733-29649-DETAIL-03_01_2023-GO95MLD-1^07216001.0292603 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
505764733-29649-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292603 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
935872817-78349-DETAIL-03_13_2023-GUYHINS-1^07216001.0293403 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
93727479-94759-DETAIL-03_02_2023-GO95MLD-1^07216001.0293408 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
597473373-82839-DETAIL-03_13_2023-GO95TCH-1^07216001.0293410 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
707112858-45641-DETAIL-03_13_2023-GO95TCH-1^07216001.0293440 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
433673003-67349-DETAIL-03_01_2023-GO95HV-1^07216001.0293501 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
509750759-6149-DETAIL-03_01_2023-GO95MLD-1^07216001.0293502 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
509750759-6149-DETAIL-03_01_2023-GRDRODHI-1^07216001.0293502 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
509750759-6149-DETAIL-03_01_2023-SVCWIND-1^07216001.0293502 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
678652613-97349-DETAIL-03_01_2023-GO95HV-1^07216001.0293503 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
678652613-97349-DETAIL-03_01_2023-GO95MLD-1^07216001.0293503 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
160332993-68739-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
160332993-68739-DETAIL-03_01_2023-GO95CL10-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
541867836-72649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
541867836-72649-DETAIL-03_02_2023-SVCENTBK-1^07216001.0293903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
541867836-72649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
565660026-78649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293904 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
565660026-78649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293904 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
250005856-71749-DETAIL-03_02_2023-GO95MLD-1^07216001.0293907 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
480153809-88849-DETAIL-03_02_2023-GO95MLD-1^07216001.0293909 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
480153809-88849-DETAIL-03_02_2023-SVCWIND-1^07216001.0293909 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
701244619-20649-DETAIL-03_02_2023-GO95HV-1^07216001.0293911 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
701244619-20649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293911 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
716208487-75249-DETAIL-03_08_2023-GO95MLD-1^07216001.0294200 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
716208487-75249-DETAIL-03_08_2023-SVCWIND-1^07216001.0294200 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
630204439-98249-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0294506 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
630204439-98249-DETAIL-03_07_2023-GO95CL10-1^07216001.0294506 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
111515229-96839-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0294508 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
111515229-96839-DETAIL-03_07_2023-GO95CL10-1^07216001.0294508 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
111515229-96839-DETAIL-03_07_2023-GO95MLD-1^07216001.0294508 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
461995235-51939-DETAIL-03_07_2023-GUYHINS-1^07216001.0294509 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
890583928-68203-DETAIL-03_07_2023-GO95MLD-1^07216001.0294544 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
813959629-84249-DETAIL-03_09_2023-GO95HV-1^07216001.0294601 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
813959629-84249-DETAIL-03_09_2023-GO95MLD-1^07216001.0294601 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
813959629-84249-DETAIL-03_09_2023-GUYHINS-1^07216001.0294601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
131361125-39249-DETAIL-03_09_2023-GO95MLD-1^07216001.0294602 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
131361125-39249-DETAIL-03_09_2023-GO95TCH-1^07216001.0294602 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
398176809-5139-DETAIL-03_02_2023-CLRTOPOL-1^07216001.0294902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
398176809-5139-DETAIL-03_02_2023-GO95MLD-1^07216001.0294902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
826802979-24359-DETAIL-03_02_2023-GO95HV-1^07216001.0294903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
826802979-24359-DETAIL-03_02_2023-GO95MLD-1^07216001.0294903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
544063754-83028-DETAIL-03_08_2023-GO95MLD-1^07216001.0295300 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
544063754-83028-DETAIL-03_08_2023-GO95TCH-1^07216001.0295300 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
743413358-97088-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0295301 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
592368258-89258-DETAIL-03_08_2023-GO95HV-1^07216001.0295302 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
592368258-89258-DETAIL-03_08_2023-GO95MLD-1^07216001.0295302 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
592368258-89258-DETAIL-03_08_2023-SVCNEUT-1^07216001.0295302 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
994355854-4258-DETAIL-03_08_2023-GO95MLD-1^07216001.0295304 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
994355854-4258-DETAIL-03_08_2023-SVCNEUT-1^07216001.0295304 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
440289785-90139-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295502 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
207141163-24958-DETAIL-03_08_2023-GO95CLSV-1^07216001.0295504 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
207141163-24958-DETAIL-03_08_2023-GO95HV-1^07216001.0295504 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
207141163-24958-DETAIL-03_08_2023-GO95MLD-1^07216001.0295504 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
497402440-5559-DETAIL-03_08_2023-GO95CL10-1^07216001.0295506 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
497402440-5559-DETAIL-03_08_2023-GO95MLD-1^07216001.0295506 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
497402440-5559-DETAIL-03_08_2023-GUYHINS-1^07216001.0295506 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
12192063-84578-DETAIL-03_08_2023-SVCRUBLG-1^07216001.0295507 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
713016385-46761-DETAIL-03_09_2023-GO95TCH-1^07216001.0295508 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
713016385-46761-DETAIL-03_09_2023-GUYHINS-1^07216001.0295508 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
713016385-46761-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295508 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
638399404-41551-DETAIL-03_09_2023-SVCENTBK-1^07216001.0295540 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
158772585-84139-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0295901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
158772585-84139-DETAIL-03_06_2023-GO95MLD-1^07216001.0295901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
158772585-84139-DETAIL-03_06_2023-SVCNEUT-1^07216001.0295901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
158772585-84139-DETAIL-03_06_2023-SVCWIND-1^07216001.0295901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
626915355-14249-DETAIL-03_02_2023-CLRTOPOL-1^07216001.0295902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
626915355-14249-DETAIL-03_02_2023-GO95MLD-1^07216001.0295902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
626915355-14249-DETAIL-03_02_2023-SVCWIND-1^07216001.0295902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
653558906-14939-DETAIL-03_06_2023-GO95CL10-1^07216001.0295904 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
393084837-65948-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0295905 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
965349645-72359-DETAIL-03_02_2023-GO95MLD-1^07216001.0295906 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
965349645-72359-DETAIL-03_02_2023-SVCNEUT-1^07216001.0295906 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
84607045-92359-DETAIL-03_02_2023-GO95MLD-1^07216001.0295907 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
675766486-16768-DETAIL-03_08_2023-GUYHINS-1^07216001.0296409 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
298312576-24649-DETAIL-03_08_2023-GO95HV-1^07216001.0296410 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
298312576-24649-DETAIL-03_08_2023-GO95MLD-1^07216001.0296410 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
609887708-90466-DETAIL-03_08_2023-SVCROAD-1^07216001.0296542 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
910483224-57472-DETAIL-03_08_2023-GO95TCH-1^07216001.0296543 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
766354296-18149-DETAIL-03_06_2023-GO95MLD-1^07216001.0296603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
766354296-18149-DETAIL-03_06_2023-RISEBKSP-1^07216001.0296603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
890910364-1349-DETAIL-03_08_2023-GO95MLD-1^07216001.0296605 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
632901770-5639-DETAIL-03_06_2023-GO95HV-1^07216001.0296606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
632901770-5639-DETAIL-03_06_2023-GO95TCH-1^07216001.0296606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
632901770-5639-DETAIL-03_06_2023-GUYHINS-1^07216001.0296606 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
632901770-5639-DETAIL-03_06_2023-SVCWIND-1^07216001.0296606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
761019800-84349-DETAIL-02_23_2023-SVCWIND-1^07216001.0296904 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
224343440-41160-DETAIL-02_23_2023-SVCENTCO-1^07216001.0296905 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
212848316-30350-DETAIL-02_23_2023-GO95TCH-1^07216001.0296906 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
212848316-30350-DETAIL-02_23_2023-SVCENTCO-1^07216001.0296906 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
212848316-30350-DETAIL-02_23_2023-SVCENTCO-2^07216001.0296906 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
664174124-22921-DETAIL-02_23_2023-SVCENTCO-1^07216001.0296941 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
354220187-459-DETAIL-03_07_2023-GO95MLD-1^07216001.0297300 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
772381685-19359-DETAIL-03_07_2023-GO95HV-1^07216001.0297301 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
772381685-19359-DETAIL-03_07_2023-GO95MLD-1^07216001.0297301 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
591758745-36639-DETAIL-03_07_2023-GO95HV-1^07216001.0297302 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
991914475-18359-DETAIL-03_07_2023-GO95HV-1^07216001.0297401 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
386205655-89649-DETAIL-03_07_2023-GO95BLTC-1^07216001.0297402 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
494037606-87149-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0297606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
494037606-87149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297606 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
494037606-87149-DETAIL-03_06_2023-GUYHINS-1^07216001.0297606 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
764841216-77139-DETAIL-02_28_2023-GO95MLD-1^07216001.0297700 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
764841216-77139-DETAIL-02_28_2023-GUYHINS-1^07216001.0297700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
57694116-91249-DETAIL-02_28_2023-GO95MLD-1^07216001.0297701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
57694116-91249-DETAIL-02_28_2023-GUYHINS-1^07216001.0297701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
57694116-91249-DETAIL-02_28_2023-SVCWIND-1^07216001.0297701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
505584631-40849-DETAIL-03_06_2023-GO95MLD-1^07216001.0297702 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
505584631-40849-DETAIL-03_06_2023-SVCWIND-1^07216001.0297702 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
315541538-94839-DETAIL-03_06_2023-GO95MLD-1^07216001.0297704 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
315541538-94839-DETAIL-03_06_2023-GO95TCH-1^07216001.0297704 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
733090030-48049-DETAIL-02_27_2023-GO95MLD-1^07216001.0297905 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
654495276-86891-DETAIL-02_27_2023-GO95MLD-1^07216001.0297906 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
910099054-35393-DETAIL-02_23_2023-GO95MLD-1^07216001.0297907 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
641003518-83950-DETAIL-02_27_2023-GO95TCH-1^07216001.0297944 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
670967418-85250-DETAIL-02_23_2023-SVCENTCO-1^07216001.0297945 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
510319248-39248-DETAIL-02_27_2023-CLRTOPOL-1^07216001.0297970 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
926556165-26842-DETAIL-03_06_2023-GO95HV-1^07216001.0298402 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
168899665-87359-DETAIL-03_06_2023-GO95MLD-1^07216001.0298404 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
761047358-48358-DETAIL-03_07_2023-GO95HV-1^07216001.0298405 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
761047358-48358-DETAIL-03_07_2023-GO95MLD-1^07216001.0298405 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
761047358-48358-DETAIL-03_07_2023-GO95TCH-1^07216001.0298405 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
63419495-48359-DETAIL-03_07_2023-GO95HV-1^07216001.0298406 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
521870399-69901-DETAIL-02_28_2023-RISEGRD-1^07216001.0298608 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
455553348-76238-DETAIL-03_02_2023-GO95TCH-1^07216001.0298640 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
455553348-76238-DETAIL-03_02_2023-SVCENTCO-1^07216001.0298640 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
455553348-76238-DETAIL-03_02_2023-SVCRUBLG-1^07216001.0298640 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
455553348-76238-DETAIL-03_02_2023-SVCWIND-1^07216001.0298640 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
834743018-96612-DETAIL-03_02_2023-GO95MLD-1^07216001.0298643 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
105847528-54668-DETAIL-02_28_2023-GO95TCH-1^07216001.0298644 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
774843918-33039-DETAIL-02_28_2023-GO95TCH-1^07216001.0298701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
222807139-8549-DETAIL-02_28_2023-GO95MLD-1^07216001.0298702 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
584105401-16591-DETAIL-03_01_2023-GO95HV-1^07216001.0298704 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
584105401-16591-DETAIL-03_01_2023-GO95MLD-1^07216001.0298704 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
179145246-68049-DETAIL-02_28_2023-SVCENTCO-1^07216001.0298705 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
790317128-32219-DETAIL-02_28_2023-GO95TCH-1^07216001.0298840 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
688965238-80399-DETAIL-02_27_2023-GO95TCH-1^07216001.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
688965238-80399-DETAIL-02_27_2023-SVCENTCO-1^07216001.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
688965238-80399-DETAIL-02_27_2023-SVCENTCO-2^07216001.0298841 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
867402406-34406-DETAIL-02_23_2023-GO95HV-1^07216001.0298901 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
887194521-83282-DETAIL-02_23_2023-GO95MLD-1^07216001.0298903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
887194521-83282-DETAIL-02_23_2023-GO95TCH-1^07216001.0298903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
887194521-83282-DETAIL-02_23_2023-SVCENTCO-1^07216001.0298903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
512653095-84691-DETAIL-02_23_2023-GO95MLD-1^07216001.0298904 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
890878505-51349-DETAIL-02_23_2023-ABNDEQPM-1^07216001.0298906 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
252445866-98649-DETAIL-02_23_2023-GO95MLD-1^07216001.0298907 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
252445866-98649-DETAIL-02_23_2023-SVCROAD-1^07216001.0298907 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
559582561-85139-DETAIL-02_28_2023-GO95MLD-1^07216001.0299702 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
87526959-14949-DETAIL-02_28_2023-GO95TCH-1^07216001.0299703 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
790641349-32139-DETAIL-02_28_2023-GO95MLD-1^07216001.0299704 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
771795238-94349-DETAIL-02_23_2023-ABNDEQPM-1^07216001.0299705 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
202652778-6838-DETAIL-02_23_2023-GO95MLD-1^07216001.0299707 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
851544651-40349-DETAIL-02_23_2023-GO95MLD-1^07216001.0299708 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
697969085-78949-DETAIL-02_23_2023-GO95MLD-1^07216001.0299710 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
649476326-25349-DETAIL-02_28_2023-GO95TCH-1^07216001.0299711 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
649476326-25349-DETAIL-02_28_2023-GUYHINS-1^07216001.0299711 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
321965929-33459-DETAIL-02_28_2023-GO95TCH-1^07216001.0299740 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
321965929-33459-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299740 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
406523055-91549-DETAIL-02_28_2023-GO95MLD-1^07216001.0299801 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
534111173-54639-DTLSB-02_06_2024-GO95MLD-1^07216001.0308803 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
62593964-93039-DTLSB-02_08_2024-GO95MLD-1^07216001.0308900 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
647311134-85839-DTLSB-02_08_2024-GO95MLD-1^07216001.0308903 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
876210014-67039-DTLSB-02_08_2024-GO95MLD-1^07216001.0308904 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
876210014-67039-DTLSB-02_08_2024-SVCWIND-1^07216001.0308904 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
119628424-10259-DTLSB-02_08_2024-GO95MLD-1^07216001.0308905 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
443596434-49549-DTLSB-02_08_2024-GO95HV-1^07216001.0308907 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2029-02-08 | 3
659070054-87339-DTLSB-02_06_2024-GO95MLD-1^07216001.0308908 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
11436834-74934-DTLSB-02_08_2024-GO95MLD-1^07216001.0308909 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
696100661-69818-DTLSB-02_06_2024-CUTOUTAR-1^07216001.0309700 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
696100661-69818-DTLSB-02_06_2024-GO95HV-1^07216001.0309700 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2029-02-06 | 3
696100661-69818-DTLSB-02_06_2024-GO95TCH-1^07216001.0309700 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
292861349-73349-DTLSB-02_06_2024-GO95MLD-1^07216001.0309917 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
156657181-83959-DTLSB-02_06_2024-SVCENTCO-1^07216001.0309942 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
749760413-8759-DETAIL-02_28_2024-GO95MLD-1^07216001.0342901 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
66066636-28249-DETAIL-02_22_2024-GO95MLD-1^07216001.0344803 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
218013749-21649-DETAIL-02_22_2024-SVCENTBK-1^07216001.0345800 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
554943579-74759-DETAIL-02_22_2024-GO95HV-1^07216001.0346702 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
554943579-74759-DETAIL-02_22_2024-GO95MLD-1^07216001.0346702 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
647878589-97649-DETAIL-02_22_2024-GUYHINS-1^07216001.0347701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
390455099-17649-DETAIL-02_22_2024-GO95MLD-1^07216001.0348700 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
355376929-56649-DETAIL-02_22_2024-GO95MLD-1^07216001.0348702 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
962318919-95649-DETAIL-02_22_2024-GO95MLD-1^07216001.0349701 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
323628881-58881-DETAIL-02_22_2024-GUYHINS-1^07216001.0349702 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
374873739-63159-DETAIL-05_03_2022-GO95CL10-1^07217001.0247402 | OTHER | FHCA | Distribution | 2022-05-03 | 2027-05-03 | 3
374873739-63159-DETAIL-05_03_2022-GO95HV-1^07217001.0247402 | OTHER | FHCA | Distribution | 2022-05-03 | 2027-05-03 | 3
374873739-63159-DETAIL-05_03_2022-GO95MLD-1^07217001.0247402 | OTHER | FHCA | Distribution | 2022-05-03 | 2025-05-03 | 2
374873739-63159-DETAIL-05_03_2022-GUYHINS-1^07217001.0247402 | ANCHOR/GUY | FHCA | Distribution | 2022-05-03 | 2025-05-03 | 2
465586139-70631-ADMIN-07_12_2024-POLEDERP-1^668038/00 1/068 | POLE | FHCA | Transmission | 2024-07-12 | 2027-07-12 | 2
26122899-79732-DETAIL-11_01_2023-POLEREPL-1^668044/00 1/055 | POLE | CA-TIER-2 | Transmission | 2023-11-01 | 2024-11-01 | 2
26122899-87670-DETAIL-11_01_2023-POLEREPL-1^668044/00 1/055 | POLE | CA-TIER-2 | Transmission | 2023-11-01 | 2024-11-01 | 2
820924590-45242-ADMIN-07_16_2024-POLEREPL-1^668044/00 4/060 | POLE | CA-TIER-2 | Transmission | 2024-07-16 | 2025-07-16 | 2
820924590-46162-ADMIN-07_16_2024-POLEREPL-1^668044/00 4/060 | POLE | CA-TIER-2 | Transmission | 2024-07-16 | 2025-07-16 | 2
986212448-66513-DRONE_HY-10_26_2023-GO95HV-1^668087/00 17/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-26 | 2028-10-26 | 3
371846371-70720-DRONE_HY-10_25_2023-GO95HV-1^668087/00 17/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
757637858-85971-DRONE_HY-10_25_2023-GO95HV-1^668087/00 18/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
659266668-97301-DRONE_HY-10_25_2023-GO95HV-1^668087/00 19/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
367309631-63439-DRONE_HY-10_25_2023-GO95HV-1^668087/00 2/001 | OTHER | FHCA | Transmission | 2023-10-25 | 2028-10-25 | 3
148334728-23690-DRONE_HY-10_25_2023-GO95HV-1^668087/00 2/004 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
749429711-19739-DRONE_HY-10_25_2023-GO95HV-1^668087/00 2/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
630937391-71439-DRONE_HY-10_25_2023-GO95HV-1^668087/00 2/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
299845716-42839-DRONE_HY-10_25_2023-GO95HV-1^668087/00 2/011 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
387143158-26339-DRONE_HY-10_25_2023-GO95HV-1^668087/00 3/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
389394908-3540-DRONE_HY-10_25_2023-GO95HV-1^668087/00 3/003 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
276533431-39739-DRONE_HY-10_25_2023-GO95HV-1^668087/00 3/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
199144894-65259-DETAIL-03_20_2023-ABNDEQPM-1^07118004.0020501 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2028-03-20 | 3
419225473-39659-ADMIN-04_30_2024-POLEREPL-1^668004/02 2/007 | POLE | CA-NON-TIER | Transmission | 2024-04-30 | 2027-04-30 | 2
237364878-89960-DTLTRT-09_30_2020-GO95HV-1^668018/00 1/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
842842629-44300-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/005 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
842842629-63300-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/005 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
230540189-94870-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
558777618-31860-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
558777618-31860-ADMIN-08_27_2024-POLEREPL-1^668018/00 10/002 | POLE | CA-TIER-2 | Transmission | 2024-08-27 | 2025-08-27 | 2
23011868-58882-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
23011868-63400-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
23011868-72400-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
40070728-12760-DTLTRT-09_30_2020-GO95HV-1^668018/00 8/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
272573908-97760-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
272573908-97760-ADMIN-08_27_2024-POLEREPL-1^668018/00 9/002 | POLE | CA-TIER-2 | Transmission | 2024-08-27 | 2025-08-27 | 2
378571548-97620-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
675253539-25500-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
675253539-55500-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
923386709-51679-DETAIL-09_29_2020-GO95HV-1^668018/00 9/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
514120778-560-DRONE_HY-07_15_2024-CONDLOOS-1^668014/00 6/054 | CONDUCTOR | CA-TIER-3 | Transmission | 2024-07-15 | 2024-08-15 | 1
981159691-3230-DETAIL-09_24_2024-GRDSHDBK-1^668014/00 8/027 | OTHER | CA-TIER-2 | Transmission | 2024-09-24 | 2027-09-24 | 2
26691084-24269-DRONE_HY-09_21_2023-GO95HV-1^668002/00 1/001 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
779315401-41469-DETAIL-02_23_2023-GO95HV-1^668002/00 10/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
433449734-53030-DETAIL-04_13_2023-GUYNOINS-1^668002/00 9A/058 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2023-04-13 | 2026-04-13 | 2
847046054-43250-DRONE_HY-09_20_2023-GO95HV-1^668002/00 9C/058 | OTHER | CA-TIER-2 | Transmission | 2023-09-20 | 2028-09-20 | 3
56490293-95859-DETAIL-01_31_2023-GRDRODHI-1^668002/07 17/002 | OTHER | CA-TIER-2 | Transmission | 2023-01-31 | 2026-01-31 | 2
235890784-64770-DETAIL-04_17_2024-GO95MLD-1^06144001.0012300 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
561403034-35061-DETAIL-04_18_2024-GO95HV-1^06144001.0013900 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
375498814-15320-DETAIL-04_17_2024-GO95MLD-1^06144001.0122301 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
686070294-67171-DETAIL-04_17_2024-GO95HV-1^06144001.0122700 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
720404804-38071-DETAIL-04_17_2024-GO95HV-1^06144001.0130900 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
618347221-4431-DTLSB-03_29_2022-GO95HV-1^06144006.0099900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
659536911-86901-DTLSB-03_29_2022-GO95HV-1^06144006.0100900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
42911721-67740-DTLSB-03_29_2022-GO95HV-1^06144006.0100901 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
173400443-74610-DTLSB-03_24_2022-XARMSPCR-1^06144006.0153201 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-24 | 2025-03-24 | 2
173400443-74610-ADMIN-01_29_2024-POLEREPL-1^06144006.0153201 | POLE | CA-NON-TIER | Distribution | 2024-01-29 | 2024-04-28 | 1
654669896-64191-DTLSB-03_29_2022-GO95MLD-1^06144006.0165002 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
906244163-50679-DTLSB-03_30_2022-CONDFRAY-1^06144006.0192601 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
485899803-93351-DTLSB-03_30_2022-ABNDEQPM-1^06144006.0194900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
995903053-17343-DTLSB-03_30_2022-XARMSPCR-1^06144006.0198900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
302505053-2540-DTLSB-03_30_2022-GO95HV-1^06144006.0201900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
250827333-75980-DTLSB-03_28_2022-POLETOP-1^06144006.0224700 | POLE | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
220709613-34360-DTLSB-03_28_2022-GO95HV-1^06144006.0225701 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
220709613-34360-DTLSB-03_28_2022-POLETOP-1^06144006.0225701 | POLE | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
376850686-26120-DETAIL-01_25_2017-POLETOP-1^06144006.0230500 | POLE | CA-NON-TIER | Distribution | 2017-01-25 | 2021-12-25 | 2
122896003-58579-DTLSB-03_31_2022-GO95HV-1^06144006.0298700 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
122896003-58579-DTLSB-03_31_2022-GO95MLD-1^06144006.0298700 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
184560238-69920-DETAIL-04_17_2024-GO95MLD-1^06145001.0013400 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
961315348-71053-DETAIL-04_17_2024-INSULDMG-1^06145001.0014400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
761315458-4981-DETAIL-04_17_2024-GO95MLD-1^06145001.0015400 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
307308468-84550-DETAIL-04_17_2024-GO95HV-1^06145001.0018500 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
286115498-33820-DETAIL-04_16_2024-GO95HV-1^06145001.0019300 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
286115498-33820-DETAIL-04_16_2024-GO95MLD-1^06145001.0019300 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
40084598-67930-DETAIL-04_16_2024-GO95MLD-1^06145001.0019400 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
11463478-25489-DETAIL-04_17_2024-GO95HV-1^06145001.0019500 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
290129188-27130-DETAIL-04_17_2024-GO95MLD-1^06145001.0019501 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
628713188-23989-DETAIL-04_17_2024-GO95MLD-1^06145001.0019502 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
908255348-47762-ADMIN-04_23_2024-ABNDEQPM-1^06145001.0022170-A | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
637590628-56251-DETAIL-04_23_2024-GO95HV-1^06145001.0023000 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
304363336-76450-DETAIL-04_24_2024-SVCDEFLC-1^06145001.0030100 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
612759735-64821-DETAIL-04_24_2024-GO95HV-1^06145001.0031000 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
612759735-64821-DETAIL-04_24_2024-GO95MLD-1^06145001.0031000 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
248337195-87580-DETAIL-04_24_2024-SVCDEFLC-1^06145001.0031101 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
20116995-26040-DETAIL-04_24_2024-GO95MLD-1^06145001.0031200 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
292690405-67430-DETAIL-04_24_2024-GO95HV-1^06145001.0031201 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
292690405-67430-DETAIL-04_24_2024-SVCDEFLC-1^06145001.0031201 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
292690405-67430-DETAIL-04_24_2024-SVCDEFLC-2^06145001.0031201 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
858461645-76582-DETAIL-04_23_2024-GO95MLD-1^06145001.0033100 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
958962355-37543-DETAIL-04_23_2024-GO95MLD-1^06145001.0034101 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
548932335-3741-DETAIL-04_23_2024-GO95HV-1^06145001.0035102 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
548932335-3741-DETAIL-04_23_2024-GO95MLD-1^06145001.0035102 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
632141229-35741-DETAIL-04_24_2024-GO95MLD-1^06145001.0053300 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
52956049-5450-DETAIL-04_24_2024-GO95MLD-1^06145001.0054200 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
613750749-63421-DETAIL-04_24_2024-GRDRODHI-1^06145001.0055100 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
613750749-63421-DETAIL-04_24_2024-INSULDMG-1^06145001.0055100 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
45436659-38340-ADMIN-04_24_2024-ABNDEQPM-1^06145001.0057000 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
709459579-78251-DETAIL-04_24_2024-GO95MLD-1^06145001.0060700 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
490662889-14861-DETAIL-04_24_2024-GO95HV-1^06145001.0061600 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
165779899-67710-DETAIL-04_24_2024-GO95HV-1^06145001.0062500 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
573571189-51071-DETAIL-04_24_2024-GO95HV-1^06145001.0062501 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
573571189-51071-DETAIL-04_24_2024-GO95MLD-1^06145001.0062501 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
98142629-76389-DETAIL-04_24_2024-GO95MLD-1^06145001.0089900 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
665463979-8121-DETAIL-04_24_2024-GO95MLD-1^06145001.0089901 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
885666638-6372-DETAIL-04_16_2024-GO95MLD-1^06145001.0129803 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
605301941-44121-DETAIL-04_18_2024-GO95MLD-1^06145001.0130300 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
860425241-95779-DETAIL-04_18_2024-GO95MLD-1^06145001.0130301 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
860425241-95779-DETAIL-04_18_2024-GRDRODHI-1^06145001.0130301 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2027-04-18 | 2
198712671-99930-DETAIL-04_15_2024-GO95MLD-1^06145001.0136100 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
922002681-68822-DETAIL-04_15_2024-GO95MLD-1^06145001.0136200 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
656181281-24301-DETAIL-04_15_2024-GO95MLD-1^06145001.0139000 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
188576781-39830-DETAIL-04_15_2024-GO95HV-1^06145001.0139100 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
188576781-39830-DETAIL-04_15_2024-GO95MLD-1^06145001.0139100 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
949871181-50123-DETAIL-04_15_2024-GO95MLD-1^06145001.0139101 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
362545771-47710-DETAIL-04_15_2024-GO95MLD-1^06145001.0139200 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
384988771-76530-DETAIL-04_15_2024-GO95MLD-1^06145001.0139300 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
602088751-57711-DETAIL-04_15_2024-GO95MLD-1^06145001.0249901 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
644668491-57761-DETAIL-04_15_2024-GO95HV-1^06145001.0249903 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
644668491-57761-DETAIL-04_15_2024-GO95MLD-1^06145001.0249903 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
486681426-49751-DETAIL-04_18_2024-XARMSPCR-1^06145001.0250100 | CROSSARM | CA-NON-TIER | Distribution | 2024-04-18 | 2027-04-18 | 2
675894996-53051-DETAIL-04_18_2024-GO95HV-1^06145001.0268800 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
126595696-88970-DETAIL-04_18_2024-GO95MLD-1^06145001.0268900 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
560131516-86851-DETAIL-04_18_2024-GO95HV-1^06145001.0269300 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
10122476-94469-DETAIL-04_18_2024-GO95HV-1^06145001.0362500 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
123391146-11460-DETAIL-04_18_2024-GO95HV-1^06145001.0362901 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
822233286-89272-DETAIL-04_18_2024-GO95HV-1^06145001.0363200 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
165429452-81610-DETAIL-02_08_2023-GO95BLTC-1^06145002.0047800 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
165429452-81610-DETAIL-02_08_2023-GO95MLD-1^06145002.0047800 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
149136181-1090-DETAIL-04_16_2024-INSULDMG-1^06145002.0182801 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
266423381-37400-DETAIL-04_16_2024-GO95HV-1^06145002.0183800 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
863995081-70202-DETAIL-04_16_2024-GO95MLD-1^06145002.0183801 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
598389191-37701-DETAIL-04_16_2024-GO95HV-1^06145002.0184803 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
598389191-37701-DETAIL-04_16_2024-GO95MLD-1^06145002.0184803 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
714103801-12861-DETAIL-04_16_2024-GO95MLD-1^06145002.0185900 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
272430601-9410-DETAIL-04_16_2024-GO95HV-1^06145002.0186900 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
272430601-9410-DETAIL-04_16_2024-INSULDMG-1^06145002.0186900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-16 | 2027-04-16 | 2
266100601-32200-DETAIL-04_16_2024-GO95MLD-1^06145002.0187900 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
645991833-64679-DTLSB-03_31_2022-GO95HV-1^06145006.0223501 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
528873533-96979-DTLSB-03_31_2022-ENCHRW-1^06145006.0223502 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2025-03-31 | 2
287190261-98779-DETAIL-02_01_2023-GO95MLD-1^06146002.0081100 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
831290101-20492-DETAIL-01_31_2023-GO95MLD-1^06146002.0153500 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
959516781-69479-DETAIL-01_31_2023-GO95MLD-1^06146002.0153700 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
574997491-89479-DETAIL-01_31_2023-GO95CL10-1^06146002.0153701 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
574997491-89479-DETAIL-01_31_2023-GO95MLD-1^06146002.0153701 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
498374562-99071-DETAIL-02_08_2023-GO95HV-1^06146002.0272100 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
419336542-67570-DETAIL-02_08_2023-GO95HV-1^06146002.0274700 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
345562542-26690-DETAIL-02_08_2023-GO95HV-1^06146002.0274800 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
742110332-70731-DETAIL-02_08_2023-GO95MLD-1^06146002.0274901 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
360636412-88500-DETAIL-02_08_2023-GO95HV-1^06146002.0276901 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
351741922-76790-DETAIL-02_08_2023-GO95CL10-1^06146002.0277900 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
614241522-26621-DETAIL-02_08_2023-GO95MLD-1^06146002.0334300 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
124546103-82070-DETAIL-02_09_2023-GO95MLD-1^06146004.0078000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
890656013-15392-DETAIL-02_09_2023-GO95MLD-1^06146004.0078001 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
81118993-95710-DETAIL-02_09_2023-GO95MLD-1^06146004.0078100 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
632841503-69351-DETAIL-02_09_2023-GO95MLD-1^06146004.0078101 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
86296023-32220-DETAIL-02_08_2023-GO95MLD-1^06146004.0079000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
143018823-78880-DETAIL-02_08_2023-GO95MLD-1^06146004.0080000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
878389523-83952-DETAIL-02_08_2023-GO95MLD-1^06146004.0080001 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
79525823-2710-DETAIL-02_08_2023-GO95MLD-1^06146004.0081000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
944017423-72613-DETAIL-02_08_2023-GO95MLD-1^06146004.0081001 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
481388533-17051-DETAIL-02_08_2023-GO95MLD-1^06146004.0082000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
48878833-48450-DETAIL-02_09_2023-GO95MLD-1^06146004.0083000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
565774733-30661-DETAIL-02_08_2023-GO95MLD-1^06146004.0083001 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
276052544-97510-DETAIL-02_09_2023-GO95MLD-1^06146004.0166900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
674763343-11641-DETAIL-02_09_2023-INSULDMG-1^06146004.0176300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
294064463-79230-DETAIL-02_09_2023-GO95MLD-1^06146004.0177200 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
294064463-79230-ADMIN-03_06_2023-GO95TCH-1^06146004.0177200 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
42003100-42579-DETAIL-02_16_2022-ABNDEQPM-1^06146005.0025000 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2027-02-16 | 3
42003100-42579-DETAIL-02_16_2022-GO95MLD-1^06146005.0025000 | OTHER | CA-NON-TIER | Distribution | 2022-02-16 | 2025-02-16 | 2
719426244-21809-DETAIL-02_14_2022-GO95HV-1^06146005.0035100 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
18209749-33279-DETAIL-02_14_2022-ABNDEQPM-1^06146005.0035500 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
149692583-9609-DETAIL-02_14_2022-GO95HV-1^06146005.0036601 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
280249568-69568-DETAIL-02_22_2022-INSULDMG-1^06146005.0165600 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
774464535-78189-DETAIL-02_22_2022-GO95MLD-1^06146005.0170400 | OTHER | CA-NON-TIER | Distribution | 2022-02-22 | 2025-02-22 | 2
702831754-36321-DETAIL-02_21_2022-GO95HV-1^06146005.0170501 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
531926554-55221-DETAIL-02_21_2022-GO95HV-1^06146005.0171600 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
549625195-5541-DETAIL-02_28_2022-GO95MLD-1^06146005.0176101 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2025-02-28 | 2
737231465-70721-DETAIL-02_23_2022-GO95MLD-1^06146005.0200500 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
130950635-47079-DETAIL-02_23_2022-GO95MLD-1^06146005.0202701 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
524427016-69016-DETAIL-02_23_2022-GO95TCH-1^06146005.0203701 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
742649665-7731-DETAIL-02_21_2022-GO95HV-1^06146005.0203800 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
368017295-39310-DTLSB-03_17_2022-GO95HV-1^06146005.0240901 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
800198651-24292-DTLSB-03_23_2022-GO95HV-1^06146005.0242000 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
498920231-60671-DTLSB-03_23_2022-CONDFRAY-1^06146005.0242100 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
498920231-60671-DTLSB-03_23_2022-GO95HV-1^06146005.0242100 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
575319014-11271-DTLSB-03_22_2022-ABNDEQPM-1^06146005.0242901 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2027-03-22 | 3
926178395-28542-DTLSB-03_23_2022-GO95HV-1^06146005.0243201 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
911818733-14882-DTLSB-03_22_2022-GO95MLD-1^06146005.0243900 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
260830764-89500-DETAIL-02_23_2022-GO95MLD-1^06146005.0281500 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
242637154-15680-DETAIL-02_23_2022-GO95HV-1^06146005.0281501 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
714504861-11461-DETAIL-03_07_2022-GO95MLD-1^06146006.0074501 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
285871371-83620-DETAIL-03_02_2022-GO95HV-1^06146006.0075300 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
610196810-80321-DETAIL-03_02_2022-GO95HV-1^06146006.0075504 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
78577290-42010-DETAIL-03_07_2022-GO95HV-1^06146006.0075600 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
326641600-41370-DETAIL-03_07_2022-GO95HV-1^06146006.0075601 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
182423270-91820-DETAIL-03_07_2022-GO95HV-1^06146006.0075700 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
283285740-21409-DETAIL-03_02_2022-GO95HV-1^06146006.0076201 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
658882761-40001-DETAIL-03_02_2022-GO95MLD-1^06146006.0076300 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
658882761-40001-DETAIL-03_02_2022-GRDRODHI-1^06146006.0076300 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
760753708-87081-ADMIN-01_11_2022-POLEDERP-1^06147001.0106501 | POLE | CA-NON-TIER | Distribution | 2022-01-11 | 2025-01-11 | 2
717651370-98771-DETAIL-08_31_2020-GO95BLTC-1^06147001.0106801 | OTHER | CA-NON-TIER | Distribution | 2020-08-31 | 2025-08-31 | 3
818483753-69452-DETAIL-09_10_2020-SVCROAD-1^06147001.0188600 | OTHER | CA-NON-TIER | Distribution | 2020-09-10 | 2023-09-10 | 2
440374834-34090-AUDIT-09_24_2020-GUYSLACK-1^06147001.0309500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2020-09-24 | 2023-09-24 | 2
850064195-24652-DETAIL-02_07_2023-GO95HV-1^06147002.0047300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
526594585-10411-DETAIL-02_07_2023-GO95HV-1^06147002.0047400 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
143465485-15080-DETAIL-02_07_2023-GO95HV-1^06147002.0047401 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
276684455-19010-DETAIL-02_07_2023-GO95HV-1^06147002.0047900 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
174234146-67210-DETAIL-02_06_2023-GO95MLD-1^06147002.0070000 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
957829458-59858-DETAIL-01_31_2023-GO95MLD-1^06147002.0349500 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
898677329-19122-DETAIL-01_25_2023-ABNDEQPM-1^06147003.0023901 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
898677329-19122-DETAIL-01_25_2023-GO95MLD-1^06147003.0023901 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
763119849-31891-DETAIL-01_25_2023-INSULDMG-1^06147003.0025400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
259103359-84890-DETAIL-01_25_2023-GO95HV-1^06147003.0025600 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
631305459-34241-DETAIL-01_25_2023-GO95HV-1^06147003.0025801 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
250975969-58090-DETAIL-01_25_2023-GO95HV-1^06147003.0025901 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
627560629-37741-DETAIL-01_25_2023-GO95MLD-1^06147003.0027500 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
664993709-7621-DETAIL-01_25_2023-GO95MLD-1^06147003.0027501 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
623091941-2201-ADMIN-03_06_2023-GO95HV-1^06147003.0112000 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
513060900-28900-DETAIL-01_24_2023-GO95TCH-1^06147003.0129501 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
633491479-50151-DETAIL-01_24_2023-GO95CL10-1^06147003.0129600 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
392683550-49440-DETAIL-01_24_2023-GO95MLD-1^06147003.0249800 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
551260300-94141-DETAIL-01_24_2023-GO95HV-1^06147003.0249900 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
551260300-94141-DETAIL-01_24_2023-GO95MLD-1^06147003.0249900 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
548486190-51541-DETAIL-01_24_2023-GO95MLD-1^06147003.0249901 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
599951468-21211-DETAIL-01_30_2023-GO95HV-1^06147003.0302800 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
749205549-34209-DETAIL-03_04_2024-INSULDMG-2^06147004.0010202 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
523318908-52209-AUDIT-03_21_2024-GO95MLD-1^06147004.0010300 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
523318908-52209-AUDIT-03_21_2024-GRDRODHI-1^06147004.0010300 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
781547649-26979-AUDIT-03_14_2024-GO95MLD-1^06147004.0010302 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
222769869-76209-DETAIL-03_04_2024-GO95HV-1^06147004.0010303 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2029-03-04 | 3
222769869-76209-DETAIL-03_04_2024-GO95MLD-1^06147004.0010303 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2029-03-04 | 3
913484918-13209-DETAIL-03_04_2024-GO95HV-1^06147004.0010500 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2029-03-04 | 3
408090799-77109-DETAIL-03_06_2024-GO95HV-1^06147004.0017400 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
696359466-698-DETAIL-03_06_2024-GO95MLD-1^06147004.0017500 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
943405444-74574-DETAIL-03_07_2024-GO95MLD-1^06147004.0017600 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
60841209-30079-DETAIL-03_04_2024-GO95MLD-1^06147004.0018200 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
174822274-70974-DETAIL-03_07_2024-GO95HV-1^06147004.0019500 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2029-03-07 | 3
163592470-40409-DETAIL-03_11_2024-SVCDEFLC-1^06147004.0020200 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
184244190-77409-DETAIL-03_05_2024-GO95MLD-1^06147004.0020202 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
427295820-78079-DETAIL-03_05_2024-CONDFRAY-1^06147004.0020203 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
427295820-78079-DETAIL-03_05_2024-GO95MLD-1^06147004.0020203 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
821556990-36409-DETAIL-03_05_2024-CONDFRAY-1^06147004.0020300 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
481012290-73389-DETAIL-03_05_2024-GO95HV-1^06147004.0020301 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
815098910-74309-DETAIL-03_05_2024-CONDFRAY-1^06147004.0022000 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
747026481-72079-DETAIL-03_12_2024-GRDRODHI-1^06147004.0032700 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
456954831-86809-DETAIL-03_11_2024-CONDFRAY-1^06147004.0037600 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
456954831-86809-DETAIL-03_11_2024-CONDFRAY-2^06147004.0037600 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
456954831-86809-DETAIL-03_11_2024-CONDFRAY-3^06147004.0037600 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
647469431-87779-DETAIL-03_11_2024-GO95HV-1^06147004.0038600 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
460028231-56809-DETAIL-03_11_2024-GO95HV-1^06147004.0038601 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
142902731-26809-DETAIL-03_11_2024-GO95HV-1^06147004.0039600 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
15566401-95809-DETAIL-03_11_2024-GO95MLD-1^06147004.0039602 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
388221771-33679-DETAIL-03_11_2024-GO95MLD-1^06147004.0039702 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
990620161-36579-DETAIL-03_11_2024-GO95MLD-1^06147004.0047801 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
990620161-36579-DETAIL-03_11_2024-GRDRODHI-1^06147004.0047801 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
669192391-59809-DETAIL-03_11_2024-GO95HV-1^06147004.0049800 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
23610841-17579-DETAIL-03_13_2024-CLRTOUCH-1^06147004.0072100 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
23610841-17579-DETAIL-03_13_2024-GUYHINS-1^06147004.0072100 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
381870421-28730-DETAIL-03_13_2024-GO95HV-1^06147004.0084000 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2029-03-13 | 3
225208341-70660-DETAIL-03_13_2024-GO95MLD-1^06147004.0085004 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
627619941-48741-DETAIL-03_13_2024-GO95HV-1^06147004.0085100 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2029-03-13 | 3
520498651-42701-DETAIL-03_13_2024-GO95MLD-1^06147004.0085101 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
779894521-39779-AUDIT-03_27_2024-GO95MLD-1^06147004.0085900 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
87267211-91820-DETAIL-03_12_2024-CONDFRAY-1^06147004.0085901 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
64101309-55309-DETAIL-03_21_2024-CONDFRAY-1^06147004.0113900 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
904699350-97579-DETAIL-03_21_2024-GO95HV-1^06147004.0116800 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
904699350-97579-DETAIL-03_21_2024-GO95MLD-1^06147004.0116800 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
752791560-42309-DETAIL-03_21_2024-GO95MLD-1^06147004.0117800 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
274156982-53610-DETAIL-03_14_2024-GO95HV-1^06147004.0325600 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
984218582-1213-DETAIL-03_14_2024-GO95HV-1^06147004.0325601 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
39852152-78099-DETAIL-01_29_2019-GO95MLD-1^06147004.0350401 | OTHER | CA-NON-TIER | Distribution | 2019-01-29 | 2023-12-29 | 2
39852152-78099-DETAIL-01_29_2019-GRDRODHI-1^06147004.0350401 | OTHER | CA-NON-TIER | Distribution | 2019-01-29 | 2023-12-29 | 2
39852152-78099-DETAIL-03_14_2024-GUYHINS-1^06147004.0350401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
39852152-78099-DETAIL-03_14_2024-INSULDMG-1^06147004.0350401 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
951839052-19099-DETAIL-01_29_2019-GO95MLD-1^06147004.0350500 | OTHER | CA-NON-TIER | Distribution | 2019-01-29 | 2023-12-29 | 2
951839052-19099-DETAIL-03_14_2024-GRDRODHI-1^06147004.0350500 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
224353252-59099-DETAIL-03_14_2024-GO95MLD-1^06147004.0350501 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
224353252-59099-DETAIL-03_14_2024-GRDRODHI-1^06147004.0350501 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2027-03-14 | 2
657515869-35501-DETAIL-04_02_2024-GRDRODHI-1^06147005.0096200 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
511734559-69999-DETAIL-04_01_2024-EQUIPOIL-1^06147005.0097700 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
511734559-69999-DETAIL-04_01_2024-GO95MLD-1^06147005.0097700 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
511734559-69999-DETAIL-04_01_2024-GRDRODHI-1^06147005.0097700 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
544590039-95999-DETAIL-04_01_2024-GO95MLD-1^06147005.0097900 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
291390119-30609-DETAIL-04_02_2024-GO95HV-1^06147005.0102001 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
386638939-24279-DETAIL-04_02_2024-GO95MLD-1^06147005.0102201 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
386638939-24279-DETAIL-04_02_2024-GO95TCH-1^06147005.0102201 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
286081058-36099-DETAIL-04_01_2024-ABNDEQPM-1^06147005.0102701 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
421883899-49279-DETAIL-04_01_2024-CLRTOUCH-1^06147005.0107201 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
421883899-49279-DETAIL-04_01_2024-GO95TCH-1^06147005.0107201 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
923478989-84199-DETAIL-04_01_2024-GUYHINS-1^06147005.0107700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
162880858-34079-DETAIL-03_28_2024-GO95MLD-1^06147005.0122201 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
786508956-92479-DETAIL-03_28_2024-GO95MLD-1^06147005.0122500 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
786508956-92479-DETAIL-03_28_2024-GUYHINS-1^06147005.0122500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
402920936-39379-DETAIL-04_01_2024-CLRTOUCH-1^06147005.0124500 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
402920936-39379-DETAIL-04_01_2024-GO95MLD-1^06147005.0124500 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
402920936-39379-DETAIL-04_01_2024-GO95TCH-1^06147005.0124500 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
402920936-39379-DETAIL-04_01_2024-GRDRODHI-1^06147005.0124500 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
402920936-39379-DETAIL-04_01_2024-GUYHINS-1^06147005.0124500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
762263476-21399-DETAIL-04_01_2024-GO95MLD-1^06147005.0124900 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
497809195-86909-DETAIL-04_01_2024-GO95MLD-1^06147005.0126800 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
449010095-65909-DETAIL-04_01_2024-GO95HV-1^06147005.0126900 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
362274175-69019-DETAIL-04_01_2024-GO95HV-1^06147005.0127501 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
60082426-59879-DETAIL-03_25_2024-GO95MLD-1^06147005.0134901 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
425641596-63679-DETAIL-04_04_2024-GO95HV-1^06147005.0139001 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
16261656-30879-DETAIL-03_25_2024-GO95HV-1^06147005.0139901 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
16261656-30879-DETAIL-03_25_2024-GO95MLD-1^06147005.0139901 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
811452666-899-DETAIL-03_25_2024-GO95CL10-1^06147005.0141901 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
811452666-899-DETAIL-03_25_2024-GO95MLD-1^06147005.0141901 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
749332196-44079-DETAIL-04_03_2024-GO95MLD-1^06147005.0142003 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
749332196-44079-DETAIL-04_03_2024-GUYHINS-1^06147005.0142003 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
953389205-21579-ADMIN-04_03_2024-ABNDEQPM-1^06147005.0142006 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
953389205-21579-DETAIL-04_03_2024-GO95MLD-1^06147005.0142006 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
662451136-44579-DETAIL-04_03_2024-CLRTOUCH-1^06147005.0142200 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
662451136-44579-DETAIL-04_03_2024-GO95MLD-1^06147005.0142200 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
183643758-98879-DETAIL-04_03_2024-CLRTOUCH-1^06147005.0157200 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
183643758-98879-DETAIL-04_03_2024-GO95MLD-1^06147005.0157200 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
183643758-98879-DETAIL-04_03_2024-GRDRODHI-1^06147005.0157200 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
183643758-98879-DETAIL-04_03_2024-SVCENTCO-1^06147005.0157200 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
761758338-29799-DETAIL-03_28_2024-GO95MLD-1^06147005.0157900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
947311928-68909-DETAIL-03_28_2024-GO95MLD-1^06147005.0157905 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
812649907-38309-DETAIL-04_10_2024-GO95HV-1^06147005.0160201 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
812649907-38309-DETAIL-04_10_2024-INSULDMG-1^06147005.0160201 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
372802988-14720-DETAIL-04_02_2024-GO95HV-1^06147005.0161900 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
372802988-14720-DETAIL-04_02_2024-GO95MLD-1^06147005.0161900 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
372802988-14720-DETAIL-04_02_2024-SVCROAD-1^06147005.0161900 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
930545478-33262-DETAIL-04_02_2024-GO95HV-1^06147005.0162700 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
508459694-5999-DETAIL-03_11_2024-COPLLEAN-1^06147005.0173001 | POLE | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
350283313-72899-DETAIL-03_11_2024-GO95HV-1^06147005.0173700 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
350283313-72899-DETAIL-03_11_2024-GO95MLD-1^06147005.0173700 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
713279603-32899-DETAIL-03_11_2024-GO95HV-1^06147005.0174702 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
694437860-97860-DETAIL-03_05_2024-GO95HV-1^06147005.0174902 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
264588263-74309-DETAIL-03_05_2024-GO95HV-1^06147005.0176900 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
544229683-97799-ADMIN-03_11_2024-GO95TCH-1^06147005.0177300 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
403295814-73799-DETAIL-03_06_2024-GO95MLD-1^06147005.0177701 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
142995104-74799-DETAIL-03_06_2024-GO95HV-1^06147005.0177800 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
953828783-9699-DETAIL-03_05_2024-GO95HV-1^06147005.0177900 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
953828783-9699-DETAIL-03_05_2024-GO95MLD-1^06147005.0177900 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
580734283-15799-DETAIL-03_11_2024-GO95HV-1^06147005.0178400 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
986121508-4779-DETAIL-04_09_2024-GO95MLD-1^06147005.0212003 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
670493038-69309-DETAIL-04_10_2024-CLRTOUCH-1^06147005.0212703 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
670493038-69309-DETAIL-04_10_2024-GO95MLD-1^06147005.0212703 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
752319628-29999-DETAIL-04_10_2024-GO95HV-1^06147005.0212900 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
731785947-60409-DETAIL-04_10_2024-GO95MLD-1^06147005.0212902 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
731785947-60409-DETAIL-04_10_2024-GRDRODHI-1^06147005.0212902 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
152025947-44099-DETAIL-04_09_2024-INSULDMG-1^06147005.0213001 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
501706659-91409-DETAIL-04_10_2024-GO95MLD-1^06147005.0213900 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
716235608-31409-DETAIL-04_10_2024-GO95MLD-1^06147005.0214900 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
716235608-31409-DETAIL-04_10_2024-GRDRODHI-1^06147005.0214900 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
532783999-41009-DETAIL-04_10_2024-GO95HV-1^06147005.0214901 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
882818027-83309-DETAIL-04_09_2024-INSULDMG-1^06147005.0215000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
933076134-10334-DETAIL-04_09_2024-GO95MLD-1^06147005.0219520 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
498050742-38099-DTLSB-02_27_2019-ENCHRW-1^06147005.0220302 | OTHER | CA-NON-TIER | Distribution | 2019-02-27 | 2024-01-27 | 2
498050742-38099-DETAIL-04_09_2024-SVCDEFLC-1^06147005.0220302 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
160282782-90079-DETAIL-04_08_2024-GO95BLTC-1^06147005.0220400 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
160282782-90079-DETAIL-04_08_2024-GO95MLD-1^06147005.0220400 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
160282782-90079-DETAIL-04_08_2024-SVCDEFLC-1^06147005.0220400 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
126581272-46319-ADMIN-05_28_2024-POLEREPL-1^06147005.0220403 | POLE | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
948550112-8319-DETAIL-04_08_2024-GO95MLD-1^06147005.0220600 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
707409902-679-DETAIL-04_08_2024-GO95MLD-1^06147005.0222400 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
707409902-679-DETAIL-04_08_2024-GUYHINS-1^06147005.0222400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
643594929-37479-DETAIL-04_03_2024-CLRTOUCH-1^06147005.0222700 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
88979726-52079-DETAIL-04_04_2024-GO95MLD-1^06147005.0238102 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
88979726-52079-DETAIL-04_04_2024-GUYHINS-1^06147005.0238102 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
511175416-74979-DETAIL-04_04_2024-GO95MLD-1^06147005.0238201 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
257635582-57582-DETAIL-04_04_2024-GO95MLD-1^06147005.0240201 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
823483583-54583-DETAIL-04_04_2024-GO95MLD-1^06147005.0240400 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
823483583-54583-DETAIL-04_04_2024-SVCROAD-1^06147005.0240400 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
984577616-18520-DETAIL-04_04_2024-GO95MLD-1^06147005.0242901 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
984577616-18520-DETAIL-04_04_2024-GUYHINS-1^06147005.0242901 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
581527490-82700-DETAIL-04_04_2024-GO95MLD-1^06147005.0243000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
875991492-34492-DETAIL-04_04_2024-GO95MLD-1^06147005.0243100 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
913966506-66779-DETAIL-04_08_2024-GO95HV-1^06147005.0245100 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
913966506-66779-DETAIL-04_08_2024-GO95MLD-1^06147005.0245100 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
42231334-85379-DETAIL-02_02_2022-SVCENTCO-1^06147005.0266202 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
103303629-27409-DETAIL-02_01_2022-SVCWIND-1^06147005.0267304 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
536290808-76379-DETAIL-02_02_2022-ABNDEQPM-1^06147005.0268101 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
536290808-76379-DETAIL-02_02_2022-GO95MLD-1^06147005.0268101 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
411384238-1509-DETAIL-02_02_2022-SVCWIND-1^06147005.0268202 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
536929718-79409-ADMIN-01_23_2024-POLEREPL-1^06147005.0268301 | POLE | CA-NON-TIER | Distribution | 2024-01-23 | 2027-01-23 | 2
801323423-16379-DETAIL-02_03_2022-GO95MLD-1^06147005.0270900 | OTHER | CA-NON-TIER | Distribution | 2022-02-03 | 2025-02-03 | 2
701374737-35737-DETAIL-02_09_2022-ABNDEQPM-1^06147005.0279702 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
983151760-8903-DETAIL-03_02_2022-GO95HV-1^06147006.0321301 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2027-03-02 | 3
912278029-39389-ADMIN-05_20_2024-COPLLEAN-1^06148001.0253200 | POLE | CA-NON-TIER | Distribution | 2024-05-20 | 2027-05-20 | 2
775308970-80179-DTLSB-06_23_2020-UNIGRDSG-1^06148001.0341600 | OTHER | CA-NON-TIER | Distribution | 2020-06-23 | 2023-06-23 | 2
887886829-81689-DETAIL-01_30_2023-INSULDMG-1^06148002.0131400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
538110869-97589-DETAIL-01_30_2023-GO95MLD-1^06148002.0149400 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
429957449-47589-DETAIL-01_30_2023-GO95HV-1^06148002.0149402 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
508834588-32781-DETAIL-02_06_2023-GO95MLD-1^06148002.0285301 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
750456103-98261-DETAIL-02_06_2023-GUYSLACK-1^06148002.0286100 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
525615703-36611-DETAIL-02_06_2023-INSULDMG-1^06148002.0286101 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
126148308-6870-DETAIL-02_02_2023-GO95HV-1^06148002.0287001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
577721398-17881-DETAIL-02_02_2023-GO95HV-1^06148002.0287100 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
620126644-86644-DETAIL-01_09_2023-GO95MLD-1^06148003.0144201 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
860832561-15689-DETAIL-01_09_2023-GO95TCH-1^06148003.0149100 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
329335790-96789-DETAIL-01_09_2023-GO95HV-1^06148003.0153000 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
329335790-96789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153000 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
817672890-27789-DETAIL-01_09_2023-GO95HV-1^06148003.0153001 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
817672890-27789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153001 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
311847980-26789-DETAIL-01_09_2023-GO95HV-1^06148003.0153100 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
311847980-26789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153100 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
872179020-53889-DETAIL-01_09_2023-GO95HV-1^06148003.0153300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
984073630-93889-DETAIL-01_09_2023-GO95HV-1^06148003.0153301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
525122080-85789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154100 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
434001670-55789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
457278699-589-DETAIL-01_26_2023-GO95MLD-1^06148003.0209400 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
901429295-70395-DETAIL-01_30_2023-GO95MLD-1^06148003.0223400 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
662574410-60889-DETAIL-01_30_2023-GO95MLD-1^06148003.0223500 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
75922980-65599-DETAIL-01_30_2023-GO95TCH-1^06148003.0223501 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
142026310-99789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223600 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
565868210-30889-DETAIL-01_30_2023-GO95MLD-1^06148003.0223601 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
8305000-9789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223700 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
702887300-49789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223701 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
948105200-58789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223800 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
797174590-77789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223900 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
379793100-28789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223901 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
116242721-22579-DETAIL-01_24_2023-GO95MLD-1^06148003.0240000 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
959789779-63653-DETAIL-01_24_2023-GO95HV-1^06148003.0265501 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
864769069-76589-DETAIL-01_30_2023-GO95MLD-1^06148003.0295400 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
720628359-12379-DETAIL-01_30_2023-GO95BLTC-1^06148003.0295401 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
720628359-12379-DETAIL-01_30_2023-GO95MLD-1^06148003.0295401 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
505151649-7679-DETAIL-01_30_2023-ABNDEQPM-1^06148003.0295402 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
505151649-7679-DETAIL-01_30_2023-GO95BLTC-1^06148003.0295402 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
822753719-54379-DETAIL-01_30_2023-GO95BLTC-1^06148003.0295501 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
822753719-54379-DETAIL-01_30_2023-GO95MLD-1^06148003.0295501 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
919750699-25589-DETAIL-01_30_2023-CONDFRAY-1^06148003.0295601 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
437624993-41790-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355003 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
865219459-92412-DETAIL-01_25_2023-GO95HV-1^06148003.0355400 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
649401669-25281-DETAIL-01_25_2023-GO95HV-1^06148003.0355500 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2028-01-25 | 3
237817143-92779-AUDIT-02_17_2023-GUYHINS-1^06148004.0157301 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-17 | 2026-02-17 | 2
800000764-23579-DETAIL-01_16_2023-GO95MLD-1^06148004.0160300 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
52188434-41479-DETAIL-01_16_2023-GO95MLD-2^06148004.0160302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
52188434-41479-AUDIT-02_16_2023-ABNDEQPM-1^06148004.0160302 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
872098266-80366-DETAIL-01_16_2023-GO95BLTC-1^06148004.0160303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
872098266-80366-DETAIL-01_16_2023-GO95MLD-1^06148004.0160303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
205514366-16366-DETAIL-01_16_2023-GO95HV-1^06148004.0160304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
205514366-16366-DETAIL-01_16_2023-GO95MLD-1^06148004.0160304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
295615477-96477-DETAIL-01_16_2023-GO95MLD-1^06148004.0160305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
295615477-96477-ADMIN-03_10_2023-GO95CL10-1^06148004.0160305 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
572952227-24227-DETAIL-01_16_2023-GO95MLD-1^06148004.0161304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
680192377-64377-DETAIL-01_16_2023-GO95MLD-1^06148004.0161305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
662777284-43579-DETAIL-01_16_2023-GO95TCH-1^06148004.0164304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
478779220-60879-ADMIN-01_16_2023-GO95HV-1^06148004.0164308 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
478779220-60879-DETAIL-01_16_2023-GO95MLD-1^06148004.0164308 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
478779220-60879-DETAIL-01_16_2023-GO95MLD-2^06148004.0164308 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
53154578-35578-DETAIL-01_16_2023-GO95MLD-1^06148004.0165301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
53154578-35578-DETAIL-01_16_2023-GO95TCH-1^06148004.0165301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
932847578-58578-DETAIL-01_16_2023-GO95MLD-1^06148004.0165302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
751740215-73779-DETAIL-01_16_2023-GO95MLD-1^06148004.0165304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
751740215-73779-DETAIL-01_16_2023-RISEBKSP-1^06148004.0165304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
310145405-74879-DETAIL-01_16_2023-GO95BLTC-1^06148004.0165305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
310145405-74879-DETAIL-01_16_2023-GO95MLD-1^06148004.0165305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
310145405-74879-DETAIL-01_16_2023-SVCROAD-1^06148004.0165305 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
48048851-32989-DETAIL-01_17_2023-GO95HV-1^06148004.0175302 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
977740661-56989-DETAIL-01_16_2023-INSULDMG-1^06148004.0176300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
930704435-2009-DETAIL-01_16_2023-GO95HV-1^06148004.0177100 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
529958635-13009-DETAIL-01_16_2023-COPLLEAN-1^06148004.0177300 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
86357154-49909-DETAIL-01_16_2023-INSULDMG-1^06148004.0177301 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
298799715-88909-DETAIL-01_16_2023-COPLLEAN-1^06148004.0179300 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
298799715-88909-DETAIL-01_16_2023-GO95MLD-1^06148004.0179300 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
113965564-73479-DETAIL-01_16_2023-SVCROAD-1^06148004.0179301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
993326006-57689-DETAIL-01_10_2023-GO95MLD-1^06148004.0180201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
94262081-379-DETAIL-01_24_2023-GO95MLD-1^06148004.0182000 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
420814456-98279-DETAIL-01_24_2023-GO95HV-1^06148004.0182002 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
420814456-98279-DETAIL-01_24_2023-GO95MLD-1^06148004.0182002 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
685097671-95989-DETAIL-01_10_2023-GO95TCH-1^06148004.0186201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
685097671-95989-DETAIL-01_10_2023-GRDRODHI-1^06148004.0186201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
519764185-84479-DETAIL-01_10_2023-GO95MLD-1^06148004.0187200 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
519764185-84479-ADMIN-03_10_2023-GO95CL10-1^06148004.0187200 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
16724645-58889-DETAIL-01_10_2023-GO95MLD-1^06148004.0187203 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
345261786-26379-DETAIL-01_10_2023-GO95MLD-1^06148004.0187204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
345261786-26379-DETAIL-01_10_2023-GO95MLD-2^06148004.0187204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
704567781-40881-DETAIL-01_10_2023-GO95MLD-1^06148004.0187206 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
704567781-40881-DETAIL-01_10_2023-GO95MLD-2^06148004.0187206 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
395076619-31719-DETAIL-01_10_2023-GO95MLD-1^06148004.0189204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
439508719-64819-DETAIL-01_10_2023-GO95MLD-1^06148004.0189205 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
180456054-43089-DETAIL-01_23_2023-GO95MLD-1^06148004.0191501 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
443601764-42089-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192502 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
443601764-42089-DETAIL-01_23_2023-GO95HV-1^06148004.0192502 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
403845295-89-DETAIL-01_23_2023-GO95MLD-1^06148004.0192700 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
287185054-79989-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192701 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
500625636-38989-DETAIL-01_23_2023-GO95MLD-1^06148004.0192900 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
390516191-55179-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192903 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
390516191-55179-DETAIL-01_23_2023-GO95BLTC-1^06148004.0192903 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
626270154-69589-DETAIL-01_23_2023-GO95CL10-1^06148004.0193002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
626270154-69589-DETAIL-01_23_2023-GO95MLD-1^06148004.0193002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
626270154-69589-DETAIL-01_23_2023-GRDRODHI-1^06148004.0193002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
568363054-39689-DETAIL-01_23_2023-GO95MLD-1^06148004.0193003 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
480886004-62979-DETAIL-01_23_2023-GO95MLD-1^06148004.0193200 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
653137285-56579-DETAIL-01_19_2023-GO95MLD-2^06148004.0204200 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
653137285-56579-DETAIL-01_19_2023-GO95TCH-1^06148004.0204200 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
879162174-67879-DETAIL-01_19_2023-GO95BLTC-1^06148004.0204601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
879162174-67879-DETAIL-01_19_2023-GO95MLD-1^06148004.0204601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
24249945-63679-DETAIL-01_19_2023-GO95MLD-1^06148004.0204602 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
417652965-55109-DETAIL-01_19_2023-GO95MLD-1^06148004.0204603 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
417652965-55109-DETAIL-01_19_2023-GO95MLD-2^06148004.0204603 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
566554395-66079-DETAIL-01_18_2023-GO95BLTC-1^06148004.0205000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
149617545-50779-DETAIL-01_18_2023-GO95HV-1^06148004.0207000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
149617545-50779-DETAIL-01_18_2023-XARMBRAC-1^06148004.0207000 | CROSSARM | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
616782635-19109-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
112370225-17079-DETAIL-01_18_2023-GO95HV-1^06148004.0207100 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
763712606-95379-DETAIL-01_19_2023-GO95BLTC-1^06148004.0209400 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
66981733-50309-DETAIL-01_18_2023-CONDFRAY-1^06148004.0210001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
66981733-50309-DETAIL-01_18_2023-CONDFRAY-2^06148004.0210001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
66981733-50309-DETAIL-01_18_2023-CONDFRAY-3^06148004.0210001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
984194113-89079-DETAIL-01_19_2023-GO95MLD-1^06148004.0210500 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
984194113-89079-DETAIL-01_19_2023-GO95MLD-2^06148004.0210500 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
736809193-17309-DETAIL-01_19_2023-CONDFRAY-1^06148004.0210602 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
433070803-42779-AUDIT-02_16_2023-ABNDEQPM-1^06148004.0210800 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
191266144-28144-DETAIL-01_19_2023-GO95HV-1^06148004.0210801 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
938281254-92254-DETAIL-01_19_2023-GO95MLD-1^06148004.0210901 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
938281254-92254-DETAIL-01_19_2023-GO95MLD-2^06148004.0210901 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
19704063-71779-DETAIL-01_18_2023-GO95MLD-1^06148004.0211000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
554531004-54209-ADMIN-01_19_2023-ENCHRW-1^06148004.0216601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
372725224-96179-DETAIL-01_19_2023-GO95MLD-1^06148004.0216701 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
372725224-96179-ADMIN-04_24_2024-GO95CLSV-1^06148004.0216701 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2024-05-24 | 1
225471651-21389-DETAIL-01_18_2023-GO95MLD-1^06148004.0219000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
225471651-21389-DETAIL-01_18_2023-GO95MLD-2^06148004.0219000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
758896411-48109-ADMIN-01_17_2023-ENCHRW-1^06148004.0219500 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
758896411-48109-DETAIL-01_17_2023-SVCENTCO-1^06148004.0219500 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
758896411-48109-AUDIT-02_16_2023-GO95CLSV-1^06148004.0219500 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
910943803-99279-DETAIL-01_18_2023-GO95CL10-1^06148004.0220300 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
405058381-9579-DETAIL-01_18_2023-GO95MLD-1^06148004.0220301 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
405058381-9579-DETAIL-01_18_2023-GO95TCH-1^06148004.0220301 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
319285034-9579-DETAIL-01_17_2023-GO95MLD-1^06148004.0222700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
319285034-9579-DETAIL-01_17_2023-GO95MLD-2^06148004.0222700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
22550001-92209-DETAIL-01_17_2023-GO95HV-1^06148004.0222702 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
22550001-92209-DETAIL-01_17_2023-GO95MLD-1^06148004.0222702 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
246751583-81079-DETAIL-01_17_2023-GO95BLTC-1^06148004.0222704 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
246751583-81079-DETAIL-01_17_2023-GO95TCH-1^06148004.0222704 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
246751583-81079-DETAIL-01_17_2023-SVCROAD-1^06148004.0222704 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
673859151-62209-DETAIL-01_17_2023-GO95HV-1^06148004.0222705 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
251547031-4609-DETAIL-01_18_2023-GO95MLD-1^06148004.0223001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
251547031-4609-DETAIL-01_18_2023-GO95MLD-2^06148004.0223001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
723797451-53609-DETAIL-01_17_2023-COPLLEAN-1^06148004.0223003 | POLE | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
723797451-53609-DETAIL-01_17_2023-GO95HV-1^06148004.0223003 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
460608821-54879-DTLSB-11_01_2021-GO95BLTC-1^06148004.0242605 | OTHER | CA-NON-TIER | Distribution | 2021-11-01 | 2026-11-01 | 3
460608821-54879-DTLSB-11_01_2021-GO95HV-1^06148004.0242605 | OTHER | CA-NON-TIER | Distribution | 2021-11-01 | 2026-11-01 | 3
182382903-99720-ADMIN-03_07_2023-POLEDERP-1^06148004.0291500 | POLE | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
327941333-74679-DTLSB-11_11_2021-CUTOUTAR-1^06148004.0303402 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2021-11-11 | 2024-11-11 | 2
490469561-75419-DTLSB-11_08_2021-SVCENTBK-1^06148004.0310103 | OTHER | CA-NON-TIER | Distribution | 2021-11-08 | 2024-11-08 | 2
947984720-52609-ADMIN-03_07_2023-POLEDERP-1^06148004.0337600 | POLE | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
295572123-83809-DETAIL-08_25_2021-SVCWIND-1^06148004.0353206 | OTHER | CA-NON-TIER | Distribution | 2021-08-25 | 2024-08-25 | 2
777133633-22709-DETAIL-08_30_2021-SVCWIND-1^06148004.0354410 | OTHER | CA-NON-TIER | Distribution | 2021-08-30 | 2024-08-30 | 2
104792999-6509-DETAIL-10_28_2021-ENCHRW-2^06148005.0255100 | OTHER | CA-NON-TIER | Distribution | 2021-10-28 | 2024-10-28 | 2
686446436-81699-DETAIL-10_12_2021-ENCHRW-1^06148005.0322903 | OTHER | CA-NON-TIER | Distribution | 2021-10-12 | 2024-10-12 | 2
601786588-35979-ADMIN-06_13_2024-CUTOUTAR-1^06148005.0330902 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-06-13 | 2027-06-13 | 2
428048231-66999-DETAIL-03_16_2022-POLETOP-1^06148006.0308100 | POLE | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
644014623-99461-DTLSB-05_22_2024-GO95MLD-1^06243001.0030300 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
750233223-70851-DTLSB-05_22_2024-GO95MLD-1^06243001.0030301 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
156795723-59290-DTLSB-05_22_2024-GO95MLD-1^06243001.0030400 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
219184323-47550-DTLSB-05_22_2024-GO95HV-1^06243001.0031200 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
665231133-75489-DTLSB-05_22_2024-GO95MLD-1^06243001.0032000 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
528767493-90411-DTLSB-05_22_2024-GO95MLD-1^06243001.0047901 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
342045892-2380-DTLSB-05_22_2024-GO95MLD-1^06243001.0111200 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
93311703-46830-DTLSB-05_22_2024-GO95MLD-1^06243001.0112100 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
604741103-40711-DTLSB-05_22_2024-GO95MLD-1^06243001.0113100 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
139653703-6280-DTLSB-05_22_2024-GO95MLD-1^06243001.0114100 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
304361503-66450-DTLSB-05_22_2024-GO95MLD-1^06243001.0114101 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
850283213-28152-DTLSB-05_22_2024-GO95MLD-1^06243001.0115000 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
22348533-6050-DTLSB-05_23_2024-GRDBROKE-1^06243001.0116001 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2027-05-23 | 2
489599633-18061-DETAIL-05_23_2024-GO95HV-1^06243001.0117000 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
527854933-76411-DTLSB-05_23_2024-GO95HV-1^06243001.0117001 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
116471243-42260-DTLTRT-05_23_2024-GO95HV-1^06243001.0119000 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
837155353-7222-DETAIL-05_23_2024-GO95HV-1^06243001.0120000 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
588823053-889-DETAIL-05_23_2024-GO95HV-1^06243001.0120001 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
965344733-18563-DTLSB-05_28_2024-GUYNOINS-1^06243001.0126400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
275073043-2110-DTLSB-05_28_2024-GO95HV-1^06243001.0127402 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
275073043-2110-DTLSB-05_28_2024-GO95MLD-1^06243001.0127402 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
995500313-53843-DTLSB-05_23_2024-GO95HV-1^06243001.0130700 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
995500313-53843-DTLSB-05_23_2024-GO95MLD-1^06243001.0130700 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
402760513-38650-DETAIL-05_23_2024-GO95HV-1^06243001.0130800 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
863766603-8002-DTLSB-05_23_2024-GO95HV-1^06243001.0130900 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
9112693-57649-DTLSB-05_23_2024-GO95MLD-1^06243001.0134901 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
110862983-27350-DTLSB-05_23_2024-GO95HV-1^06243001.0135900 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
110862983-27350-DTLSB-05_23_2024-GO95MLD-1^06243001.0135900 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
90526543-8120-DTLSB-05_23_2024-GO95MLD-1^06243001.0149001 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
400029743-66050-DTLSB-05_23_2024-GO95MLD-1^06243001.0149100 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
794528495-19972-DTLSB-05_08_2024-GO95HV-1^06244001.0032700 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
794528495-19972-DTLSB-05_08_2024-GO95MLD-1^06244001.0032700 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
600404885-48411-DTLSB-05_08_2024-GO95MLD-1^06244001.0032800 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
697672195-25211-DTLSB-05_08_2024-GO95HV-1^06244001.0033600 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
190057605-6630-DTLSB-05_08_2024-GO95MLD-1^06244001.0034300 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
274297105-76710-DTLSB-05_08_2024-GO95HV-1^06244001.0034401 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
237068915-15470-DTLSB-05_08_2024-GO95MLD-1^06244001.0035100 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
967922515-273-DTLSB-05_08_2024-GO95HV-1^06244001.0035200 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
625528115-25141-DTLSB-05_08_2024-GO95MLD-1^06244001.0035201 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
358396225-40100-DTLSB-05_08_2024-GO95MLD-1^06244001.0106900 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
366376745-65310-DTLSB-05_08_2024-GO95MLD-1^06244001.0107500 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
82307245-36710-DTLSB-05_08_2024-GO95HV-1^06244001.0107600 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
530802486-63486-DTLSB-05_13_2024-RISEGRD-1^06244001.0154300 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2027-05-13 | 2
676902468-98951-DTLSB-05_13_2024-GO95MLD-1^06244001.0155100 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
253622068-94690-DTLSB-05_13_2024-GO95HV-1^06244001.0155201 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
253622068-94690-DTLSB-05_13_2024-GO95MLD-1^06244001.0155201 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
784125048-27142-DTLSB-05_15_2024-XARMSPCR-1^06244001.0157600 | CROSSARM | CA-NON-TIER | Distribution | 2024-05-15 | 2024-06-15 | 1
613496385-26321-DTLSB-05_15_2024-GO95HV-1^06244001.0190100 | OTHER | CA-NON-TIER | Distribution | 2024-05-15 | 2029-05-15 | 3
146500895-69480-DTLSB-05_14_2024-GO95MLD-1^06244001.0201000 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
570782785-72571-DTLSB-05_14_2024-GO95MLD-1^06244001.0202000 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
524180865-90411-DTLSB-05_14_2024-GO95MLD-1^06244001.0203200 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
977000995-77893-ADMIN-05_13_2024-ABNDEQPM-1^06244001.0207300 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
365216818-56610-DTLSB-05_13_2024-GUYHINS-1^06244001.0215401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-13 | 2027-05-13 | 2
586350946-70691-DTLSB-05_14_2024-GO95MLD-1^06244001.0299101 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
633098716-80951-DTLSB-05_22_2024-GO95MLD-1^06244001.0331800 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
871562816-89532-DTLSB-05_14_2024-GO95MLD-1^06244001.0331900 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
386593226-46730-DTLSB-05_22_2024-GO95HV-1^06244001.0332800 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
83554526-27520-DTLSB-05_22_2024-GO95MLD-1^06244001.0333700 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
267804386-84010-DTLSB-05_22_2024-GO95MLD-1^06244001.0336200 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
814591096-10642-DTLSB-05_22_2024-GO95MLD-1^06244001.0337000 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
814591096-10642-DTLSB-05_22_2024-INSULDMG-1^06244001.0337000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-05-22 | 2027-05-22 | 2
154218387-38387-DTLSB-05_21_2024-GO95HV-1^06244002.0140200 | OTHER | CA-NON-TIER | Distribution | 2024-05-21 | 2029-05-21 | 3
104918207-88207-DTLSB-05_21_2024-GO95HV-1^06244002.0142501 | OTHER | CA-NON-TIER | Distribution | 2024-05-21 | 2029-05-21 | 3
311200307-40307-DTLSB-05_21_2024-GO95HV-1^06244002.0143600 | OTHER | CA-NON-TIER | Distribution | 2024-05-21 | 2029-05-21 | 3
311200307-40307-AUDIT-06_05_2024-GO95TCH-1^06244002.0143600 | OTHER | CA-NON-TIER | Distribution | 2024-06-05 | 2027-06-05 | 2
498820483-43471-DETAIL-04_24_2024-GO95HV-1^06245001.0019300 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
647222283-19771-DETAIL-04_24_2024-GO95MLD-1^06245001.0019400 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
647222283-19771-DETAIL-04_24_2024-GRDRODHI-1^06245001.0019400 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
2152854-62399-DETAIL-03_20_2024-CUTOUTAR-2^06245001.0051000 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-03-20 | 2027-03-20 | 2
2152854-62399-DETAIL-03_20_2024-GO95BLTC-1^06245001.0051000 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
2152854-62399-DETAIL-03_20_2024-GUYHINS-1^06245001.0051000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-20 | 2027-03-20 | 2
2152854-62399-DETAIL-03_20_2024-SVCENTCO-1^06245001.0051000 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2027-03-20 | 2
235441354-96370-DETAIL-03_20_2024-GO95MLD-1^06245001.0051001 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
445133444-41001-DETAIL-03_20_2024-GO95BLTC-1^06245001.0051101 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
445133444-41001-DETAIL-03_20_2024-GO95MLD-1^06245001.0051101 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
454407124-67911-DETAIL-03_20_2024-GO95MLD-1^06245001.0051301 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
454407124-67911-AUDIT-06_24_2024-GRDRODHI-1^06245001.0051301 | OTHER | CA-NON-TIER | Distribution | 2024-06-24 | 2027-06-24 | 2
944863725-94813-DTLSB-05_07_2024-GO95MLD-1^06245001.0297301 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
541809935-83831-DTLSB-05_08_2024-GO95MLD-1^06245001.0298200 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
382249335-77030-DTLSB-05_08_2024-GO95MLD-1^06245001.0298201 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
919346845-3112-DTLSB-05_08_2024-GO95HV-1^06245001.0299100 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
919346845-3112-DTLSB-05_08_2024-GO95MLD-1^06245001.0299100 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
559930545-40851-DTLSB-05_08_2024-GO95MLD-1^06245001.0299101 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
667837835-42031-DTLSB-05_07_2024-GO95HV-1^06245001.0302800 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
415873325-89170-DTLSB-05_07_2024-GO95HV-1^06245001.0302900 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
415873325-89170-DTLSB-05_07_2024-GRDRODHI-1^06245001.0302900 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2027-05-07 | 2
272974055-39610-DTLSB-05_07_2024-GO95MLD-1^06245001.0303400 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
121092155-57960-DTLSB-05_07_2024-GO95MLD-1^06245001.0303401 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
341066074-9780-DTLSB-05_08_2024-GO95MLD-1^06245001.0331900 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
279441518-95920-DETAIL-03_19_2024-GO95MLD-1^06245002.0014601 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
518650487-76701-DETAIL-03_19_2024-SVCENTCO-1^06245002.0014801 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
271230798-70710-DETAIL-03_19_2024-GRDRODHI-1^06245002.0014803 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
942581718-84003-DETAIL-03_19_2024-CONDCOIL-1^06245002.0015600 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
188788978-44030-DETAIL-03_20_2024-GO95MLD-1^06245002.0017000 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
188788978-44030-DETAIL-03_20_2024-GRDRODHI-1^06245002.0017000 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2027-03-20 | 2
670037368-90831-DETAIL-03_20_2024-GO95HV-1^06245002.0017300 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
23845958-92670-DETAIL-03_20_2024-GO95HV-1^06245002.0017500 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
265768818-28000-DETAIL-03_20_2024-GO95HV-1^06245002.0017700 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
265768818-28000-DETAIL-03_20_2024-GO95MLD-1^06245002.0017700 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
601182208-30011-DETAIL-03_20_2024-GO95MLD-1^06245002.0017900 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
966035438-3099-DETAIL-03_19_2024-GO95HV-1^06245002.0020000 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
842263439-77632-DETAIL-03_18_2024-INSULDMG-1^06245002.0041900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
107924529-11540-DETAIL-03_18_2024-GO95MLD-1^06245002.0052501 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
602036319-46711-DETAIL-03_19_2024-GO95MLD-1^06245002.0053501 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
442237319-68899-DETAIL-03_19_2024-GO95MLD-1^06245002.0053600 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
96458819-45630-DETAIL-03_19_2024-GO95MLD-1^06245002.0054600 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
97705309-3430-DETAIL-03_19_2024-GO95MLD-1^06245002.0055600 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
71630099-6300-DETAIL-03_18_2024-GO95HV-1^06245002.0057800 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
681151799-4361-DETAIL-03_18_2024-GO95HV-1^06245002.0057900 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
750715069-20789-DETAIL-03_18_2024-GO95HV-1^06245002.0059900 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
773147299-31612-DETAIL-04_11_2024-GO95MLD-1^06245002.0100100 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
400574089-4350-DETAIL-04_11_2024-GO95MLD-1^06245002.0100101 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
688593179-32389-AUDIT-05_07_2024-GO95MLD-1^06245002.0101101 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
467710609-58131-DETAIL-04_11_2024-GO95MLD-1^06245002.0107500 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
758845799-78299-DETAIL-04_11_2024-GO95MLD-1^06245002.0109500 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
823153619-31072-DETAIL-04_11_2024-GO95HV-1^06245002.0109502 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
823153619-31072-DETAIL-04_11_2024-GO95MLD-1^06245002.0109502 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
385099209-15630-DETAIL-04_11_2024-GO95HV-1^06245002.0109503 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
601415848-66011-DETAIL-04_10_2024-GO95HV-1^06245002.0112500 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
233125098-17170-DETAIL-04_10_2024-GO95MLD-1^06245002.0113001 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
520899688-16001-DETAIL-04_10_2024-GO95MLD-1^06245002.0113100 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
894207038-41202-DETAIL-04_10_2024-GO95MLD-1^06245002.0113300 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
855959858-75272-DETAIL-04_10_2024-GO95MLD-1^06245002.0113402 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
117158438-8560-DETAIL-04_10_2024-GO95MLD-1^06245002.0113500 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
117158438-8560-DETAIL-04_10_2024-GRDRODHI-1^06245002.0113500 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
982818989-94803-DTLSB-05_07_2024-GO95MLD-1^06245002.0136601 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
798661209-58582-DTLSB-05_07_2024-GO95MLD-1^06245002.0137000 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
663854499-76421-DTLSB-05_07_2024-INSULDMG-1^06245002.0137300 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-05-07 | 2027-05-07 | 2
126901099-91770-DTLSB-05_07_2024-GO95MLD-1^06245002.0137401 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
39914451-82830-DTLSB-05_07_2024-GRDRODHI-1^06245002.0138100 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2027-05-07 | 2
866837531-38212-DETAIL-04_11_2024-GO95MLD-1^06245002.0140200 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
594099941-72101-DETAIL-04_11_2024-GO95MLD-1^06245002.0140202 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
624029279-4241-DETAIL-04_10_2024-GO95HV-1^06245002.0140901 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
449730821-39111-DETAIL-04_11_2024-GO95MLD-1^06245002.0141201 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
133411369-68970-DETAIL-04_10_2024-GO95MLD-1^06245002.0141900 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
269399381-77710-DETAIL-04_11_2024-GO95MLD-1^06245002.0143100 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
590333271-60591-DETAIL-04_11_2024-GO95MLD-1^06245002.0143300 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
722307888-94881-ADMIN-01_25_2022-POLETOP-1^06246001.0335700 | POLE | CA-NON-TIER | Distribution | 2022-01-25 | 2025-01-25 | 2
367315178-72910-DTLSB-02_02_2023-SVCSVC-1^06247001.0010200 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
137445278-48180-DTLSB-02_02_2023-GRDRODHI-1^06247001.0010202 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
137445278-48180-DTLSB-02_02_2023-GRDRODHI-2^06247001.0010202 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
374166758-49420-DTLSB-02_02_2023-GO95MLD-1^06247001.0010500 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
374166758-49420-DTLSB-02_02_2023-GRDRODHI-1^06247001.0010500 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
686340488-50181-DTLSB-02_01_2023-GO95HV-1^06247001.0010901 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
686340488-50181-DTLSB-02_01_2023-INSULDMG-1^06247001.0010901 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
299755578-8740-DTLSB-02_01_2023-GO95HV-1^06247001.0011900 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
28272258-64670-DTLSB-02_02_2023-GO95MLD-1^06247001.0013000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
885075738-53372-DTLSB-02_02_2023-GO95MLD-1^06247001.0014301 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
544319248-22431-DTLSB-01_26_2023-GO95HV-1^06247001.0015901 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
681668681-74961-DETAIL-02_13_2023-GO95MLD-1^06247002.0018100 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
722969591-88689-DETAIL-02_22_2023-GO95HV-1^06247002.0030001 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
682946623-34171-DETAIL-02_22_2023-GO95HV-1^06247002.0030601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
682946623-34171-DETAIL-02_22_2023-GO95MLD-1^06247002.0030601 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
941332443-69503-DETAIL-02_22_2023-GO95HV-1^06247002.0031800 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
338210453-91180-DETAIL-02_22_2023-GO95HV-1^06247002.0031801 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
83674553-15620-DETAIL-02_22_2023-GO95HV-1^06247002.0031900 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
319039283-37560-DETAIL-02_22_2023-GO95MLD-1^06247002.0032100 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
319039283-37560-DETAIL-02_22_2023-GRDRODHI-1^06247002.0032100 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
589343493-81791-DETAIL-02_22_2023-GO95MLD-1^06247002.0032700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
589343493-81791-DETAIL-02_22_2023-GRDRODHI-1^06247002.0032700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
96062272-28430-DETAIL-02_21_2023-CONDFRAY-1^06247002.0045401 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
397457943-29650-AUDIT-02_21_2023-GUYLOINS-1^06247002.0160000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
188287853-96630-DETAIL-02_16_2023-GO95HV-1^06247002.0161000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
489396583-97861-DETAIL-02_16_2023-GO95BLTC-1^06247002.0161102 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
489396583-97861-DETAIL-02_16_2023-GO95MLD-1^06247002.0161102 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
645557273-20761-DETAIL-02_16_2023-GO95BLTC-1^06247002.0161103 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
645557273-20761-DETAIL-02_16_2023-GO95MLD-1^06247002.0161103 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
645557273-20761-DETAIL-02_16_2023-GRDRODHI-1^06247002.0161103 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
481352833-26051-DETAIL-02_16_2023-GO95HV-1^06247002.0163000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
535104064-51289-DETAIL-02_16_2023-GO95MLD-1^06247002.0164002 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
780948823-69132-DETAIL-02_16_2023-ABNDEQPM-1^06247002.0165400 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
780948823-69132-DETAIL-02_16_2023-ABNDEQPM-2^06247002.0165400 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
780948823-69132-DETAIL-02_16_2023-SVCROAD-1^06247002.0165400 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
296035314-95730-DETAIL-02_15_2023-GO95MLD-1^06247002.0236701 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
935700424-89679-DETAIL-02_15_2023-GO95TCH-1^06247002.0237600 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
57463444-53460-DETAIL-02_16_2023-GO95HV-1^06247002.0238500 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
583777824-25491-DETAIL-02_14_2023-GO95HV-1^06247002.0240501 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
799856344-69482-DETAIL-02_14_2023-CLRTOUCH-1^06247002.0242801 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
799856344-69482-DETAIL-02_14_2023-GO95MLD-1^06247002.0242801 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
799856344-69482-AUDIT-02_21_2023-GRDRODHI-1^06247002.0242801 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
476887254-36579-DETAIL-02_14_2023-GO95MLD-1^06247002.0242900 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
22826160-4089-DETAIL-02_16_2023-GO95MLD-1^06247002.0278901 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
145779966-55280-DETAIL-02_20_2023-GO95HV-1^06247002.0296101 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
962105838-37753-DETAIL-02_20_2023-GRDRODHI-1^06247002.0296600 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
501223218-30271-DETAIL-02_20_2023-GO95MLD-1^06247002.0297400 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
122211924-3660-DTLSB-02_07_2023-GO95MLD-1^06248001.0158200 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
185015744-43220-DTLSB-02_07_2023-SVCENTCO-1^06248001.0158300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
814247675-90342-DTLSB-02_08_2023-GO95MLD-1^06248001.0163401 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
309266265-45950-DTLSB-02_08_2023-GO95HV-1^06248001.0164401 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
973806655-74483-DTLSB-02_08_2023-GO95MLD-1^06248001.0166400 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
905081371-22252-DTLSB-02_16_2023-GO95MLD-1^06248001.0197000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
336388562-28080-DTLSB-02_16_2023-GO95MLD-1^06248001.0203701 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
675857112-40051-DTLSB-02_16_2023-GO95HV-1^06248001.0209001 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
636767432-289-DTLSB-02_16_2023-GO95MLD-1^06248001.0209201 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
636767432-289-DTLSB-02_16_2023-GO95TCH-1^06248001.0209201 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
864209735-73379-DTLSB-02_16_2023-GO95MLD-1^06248001.0210100 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
190613978-6830-DTLSB-02_08_2023-GO95HV-1^06248001.0227901 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
194217664-58730-DTLSB-02_06_2023-GO95MLD-1^06248001.0257201 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
200054934-86640-DTLSB-01_30_2023-GO95MLD-1^06248001.0257500 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
101960373-88189-DTLSB-02_06_2023-GO95MLD-1^06248001.0257800 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
722239533-34879-DTLSB-01_30_2023-GO95HV-1^06248001.0258000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
264197834-25100-DTLSB-01_30_2023-GO95HV-1^06248001.0258500 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
571526063-48189-DTLSB-02_06_2023-GO95HV-1^06248001.0258701 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
719277843-42079-DTLSB-01_30_2023-GO95HV-1^06248001.0259002 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
719277843-42079-DTLSB-01_30_2023-GO95MLD-1^06248001.0259002 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
719277843-42079-DTLSB-01_30_2023-GO95TCH-1^06248001.0259002 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
274870243-93879-DTLSB-01_30_2023-GO95HV-1^06248001.0259003 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
274870243-93879-DTLSB-01_30_2023-GO95MLD-1^06248001.0259003 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
419662504-82770-DTLSB-01_30_2023-GO95MLD-1^06248001.0259100 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
797539473-19882-DETAIL-02_05_2018-ENCHRW-1^06248001.0276600 | OTHER | CA-NON-TIER | Distribution | 2018-02-05 | 2023-01-05 | 2
797539473-19882-DTLSB-02_09_2023-GO95MLD-1^06248001.0276600 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
386409084-50630-DTLSB-02_13_2023-GO95MLD-1^06248001.0276740 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
338390502-60380-DTLSB-02_13_2023-GO95HV-1^06248001.0277001 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
224497643-78160-AUDIT-03_08_2023-GO95MLD-1^06248001.0277302 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
493170804-63661-DTLSB-02_09_2023-GO95HV-1^06248001.0277600 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
768512714-60602-AUDIT-04_28_2023-GO95MLD-1^06248001.0277601 | OTHER | CA-NON-TIER | Distribution | 2023-04-28 | 2026-04-28 | 2
403052633-73950-DTLSB-02_13_2023-GO95MLD-1^06248001.0278201 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
480745162-87551-DTLSB-02_13_2023-GO95MLD-1^06248001.0278301 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
422711052-14570-DTLSB-02_13_2023-GO95MLD-1^06248001.0278304 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
783147474-54842-DTLSB-02_13_2023-GO95HV-1^06248001.0278740 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
210128191-37850-DTLSB-02_15_2023-GO95HV-1^06248001.0308203 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
150492401-64990-DTLSB-02_15_2023-GO95MLD-1^06248001.0308300 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
917522801-24502-DTLSB-02_15_2023-GO95HV-1^06248001.0309400 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
206921011-73240-DTLSB-02_15_2023-GO95MLD-1^06248001.0309500 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
729268611-6901-DTLSB-02_15_2023-GO95HV-1^06248001.0309600 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
109366811-42450-DTLSB-02_15_2023-GO95HV-1^06248001.0309700 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
984287021-73213-DTLSB-02_15_2023-GO95HV-1^06248001.0309800 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
684843353-30171-DTLSB-02_16_2023-GO95MLD-1^06248001.0334900 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
56438543-48560-DTLSB-02_16_2023-ABNDEQPM-1^06248001.0334901 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
56438543-48560-DTLSB-02_16_2023-GO95MLD-1^06248001.0334901 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
612893513-15921-DTLSB-02_14_2023-GO95MLD-1^06248001.0339401 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
243445383-92180-DTLSB-02_14_2023-GO95HV-1^06248001.0339702 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
750262276-22851-DTLSB-01_31_2023-GUYHINS-1^06248001.0367807 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
750262276-22851-AUDIT-02_07_2023-GO95MLD-1^06248001.0367807 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
42508626-84540-DTLSB-01_31_2023-GO95HV-1^06248001.0367809 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
42508626-84540-DTLSB-01_31_2023-GUYHINS-1^06248001.0367809 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
984670736-68813-DTLSB-01_31_2023-GO95MLD-1^06248001.0367901 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
947315956-99523-DTLSB-01_30_2023-GO95MLD-1^06248001.0367903 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
9014886-56549-DTLSB-01_31_2023-GO95MLD-1^06248001.0367904 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
9014886-56549-DTLSB-01_31_2023-SVCENTCO-1^06248001.0367904 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
296314126-61930-DTLSB-01_31_2023-GO95HV-1^06248001.0367905 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
296314126-61930-DTLSB-01_31_2023-GO95MLD-1^06248001.0367905 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
351948696-76890-DTLSB-01_31_2023-GO95MLD-1^06248001.0367906 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
880828156-76662-DTLSB-01_31_2023-GO95MLD-1^06248001.0367908 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
685897466-20171-DTLSB-01_31_2023-GO95MLD-1^06248001.0369704 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
685897466-20171-DTLSB-01_31_2023-GO95TCH-1^06248001.0369704 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
171455186-28510-DTLSB-01_31_2023-GO95MLD-1^06248001.0369706 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
570851006-92671-DTLSB-02_01_2023-ABNDEQPM-1^06248001.0369709 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
712095378-91851-DTLSB-01_30_2023-GO95HV-1^06248001.0369710 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
712095378-91851-DTLSB-01_30_2023-GO95MLD-1^06248001.0369710 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
876925476-7752-DTLSB-01_30_2023-GO95MLD-1^06248001.0369711 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
876925476-7752-DTLSB-01_30_2023-SVCWIND-1^06248001.0369711 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
751354976-31161-DTLSB-01_30_2023-GO95MLD-1^06248001.0369712 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
543014506-19631-DTLSB-01_30_2023-GO95MLD-1^06248001.0369800 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
209684996-86550-DTLSB-01_30_2023-GO95MLD-1^06248001.0369801 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
942074336-25103-DTLSB-01_30_2023-GO95MLD-1^06248001.0369802 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
785277398-13959-DTLTRT-06_30_2022-ABNDEQPM-1^668005/00 10/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
521644820-5269-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 10/034 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
523657688-80369-DTLTRT-07_05_2022-GO95HV-1^668005/00 10/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
555923951-46469-DTLTRT-07_20_2022-GO95HV-1^668005/00 10/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
213774098-82069-DTLTRT-06_30_2022-GO95MLD-1^668005/00 11/031 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
76329608-29769-ADMIN-12_21_2022-GUYHINS-1^668005/00 11/032 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
115306559-68169-ADMIN-12_21_2022-GO95HV-1^668005/00 11/033 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2027-12-21 | 3
253329148-45159-ADMIN-08_05_2020-ABNDEQPM-1^668005/00 11/036 | OTHER | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
234989578-7469-DTLTRT-07_06_2022-GO95HV-1^668005/00 11/037 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
965850161-66469-DTLTRT-07_20_2022-GO95HV-1^668005/00 11/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
450087538-68069-DTLTRT-06_30_2022-GO95MLD-1^668005/00 3/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
43656915-52269-DTLTRT-07_05_2022-GO95HV-1^668005/00 3/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
966001668-56369-DTLTRT-07_06_2022-GO95MLD-1^668005/00 3/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
782567918-83469-DTLTRT-07_06_2022-GO95HV-1^668005/00 3/037 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
782567918-83469-DTLTRT-07_06_2022-GO95MLD-1^668005/00 3/037 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
438056618-32769-DTLTRT-07_07_2022-UBPBXARM-1^668005/00 3/041 | CROSSARM | CA-NON-TIER | Transmission | 2022-07-07 | 2025-07-07 | 2
597167674-68469-DTLTRT-07_20_2022-GO95HV-1^668005/00 3/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
455743818-68969-DTLTRT-06_30_2022-GO95MLD-1^668005/00 4/031 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
263829048-29069-DTLTRT-06_30_2022-GO95HV-1^668005/00 4/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
437364738-18269-DTLTRT-07_05_2022-GO95HV-1^668005/00 4/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
846356618-15959-DTLTRT-07_06_2022-GO95MLD-1^668005/00 7/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
846356618-15959-DTLTRT-07_06_2022-GRDRODHI-1^668005/00 7/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
335920711-25469-DTLTRT-07_20_2022-GO95HV-1^668005/00 7/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
335920711-25469-DTLTRT-07_20_2022-GO95MLD-1^668005/00 7/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2025-07-20 | 2
136337600-76159-DTLTRT-07_05_2022-GO95HV-1^668005/00 8/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
136337600-76159-DTLTRT-07_05_2022-GO95MLD-1^668005/00 8/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
834339328-58369-DTLTRT-07_06_2022-GO95HV-1^668005/00 8/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
619307588-32959-DTLTRT-06_30_2022-GO95MLD-1^668005/00 9/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
619307588-32959-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 9/032 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
164101020-54269-DTLTRT-07_05_2022-GO95HV-1^668005/00 9/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
511000839-75769-ADMIN-02_07_2022-POLEDERP-1^668005/03 9/004 | POLE | CA-NON-TIER | Transmission | 2022-02-07 | 2025-02-07 | 2
511000839-75769-DTLTRT-10_10_2022-GO95HV-1^668005/03 9/004 | OTHER | CA-NON-TIER | Transmission | 2022-10-10 | 2027-10-10 | 3
601809733-82869-DTLTRT-06_07_2021-GO95HV-1^668041/00 1/012 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
79025024-64234-DTLTRT-06_08_2021-GO95HV-1^668041/00 1/014 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
239426058-53069-DTLTRT-06_10_2021-GO95HV-1^668041/00 1/015 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
719327068-16159-DTLTRT-06_09_2021-INSULBRK-1^668041/00 1/017 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
719327068-16159-DTLTRT-06_09_2021-UBPBCTGD-1^668041/00 1/017 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
719327068-16159-DTLTRT-06_09_2021-UNIGRDSG-1^668041/00 1/017 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
28177719-74169-DTLTRT-06_10_2021-GO95HV-1^668041/00 1/018 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
558214470-16221-DTLTRT-06_15_2021-CLRTOUCH-1^668041/00 1/022 | CONDUCTOR | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
188461738-82069-DTLTRT-06_10_2021-ANCHIDLE-1^668041/00 16/014 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-10 | 2024-06-10 | 2
15979660-74369-DTLTRT-06_15_2021-GO95HV-1^668041/00 16/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
646739609-41969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 17/017 | POLE | CA-NON-TIER | Transmission | 2021-02-24 | 2024-02-24 | 2
509183170-15369-DTLTRT-06_15_2021-GO95HV-1^668041/00 17/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
20965819-71969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 18/017 | POLE | CA-NON-TIER | Transmission | 2021-02-24 | 2024-02-24 | 2
585509378-39069-DTLTRT-06_09_2021-ANCHIDLE-1^668041/00 2/016 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
585509378-39069-DTLTRT-06_09_2021-GO95HV-1^668041/00 2/016 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
767639029-32969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 2/018 | POLE | CA-NON-TIER | Transmission | 2021-02-24 | 2024-02-24 | 2
350441839-9169-DTLTRT-06_14_2021-GO95HV-1^668041/00 2/020 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
486945200-76369-DTLTRT-06_15_2021-GO95HV-1^668041/00 20/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
889134000-17369-DTLTRT-06_15_2021-GO95HV-1^668041/00 21/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
760158388-19869-ADMIN-04_13_2021-COPLLEAN-1^668041/00 5/017 | POLE | CA-NON-TIER | Transmission | 2021-04-13 | 2024-04-13 | 2
214249139-65169-DTLTRT-06_10_2021-GO95HV-1^668041/00 5/018 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
382193809-2269-DTLTRT-06_14_2021-GO95HV-1^668041/00 5/021 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
396064621-9881-DTLTRT-06_15_2021-GO95HV-1^668041/00 5/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
325731043-19870-ADMIN-02_17_2022-INSULDMG-1^668041/00 5/027 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-17 | 2025-02-17 | 2
557184444-43951-DTLTRT-06_21_2021-GO95HV-1^668041/00 5/028 | OTHER | CA-NON-TIER | Transmission | 2021-06-21 | 2026-06-21 | 3
557184444-43951-ADMIN-02_01_2022-POLEDERP-1^668041/00 5/028 | POLE | CA-NON-TIER | Transmission | 2022-02-01 | 2025-02-01 | 2
449795833-84669-DTLTRT-06_23_2021-GO95MLD-1^668041/00 5/032 | OTHER | CA-NON-TIER | Transmission | 2021-06-23 | 2024-06-23 | 2
449795833-84669-DTLTRT-06_23_2021-UBPBXARM-1^668041/00 5/032 | CROSSARM | CA-NON-TIER | Transmission | 2021-06-23 | 2024-06-23 | 2
690692741-72369-DTLTRT-06_02_2021-GO95HV-1^668041/00 6/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
361974233-92669-DTLTRT-06_04_2021-GO95HV-1^668041/00 8/009 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
714032839-43669-DTLTRT-06_09_2021-GO95HV-1^668041/00 8/014 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
225587959-85169-DTLTRT-06_10_2021-GO95HV-1^668041/00 8/018 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
271330629-16069-DTLTRT-06_14_2021-GO95HV-1^668041/00 8/021 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
313130691-7469-DTLTRT-06_03_2021-GO95HV-1^668041/00 9/007 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
335700332-35569-DTLTRT-06_04_2021-GO95HV-1^668041/00 9/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
436258503-70769-DTLTRT-06_08_2021-GO95HV-1^668041/00 9/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
626175053-28769-DTLTRT-06_07_2021-GO95HV-1^668041/00 9/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
307332918-53869-DTLTRT-06_09_2021-GO95HV-1^668041/00 9/015 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
589201708-16869-DTLTRT-06_09_2021-GO95HV-1^668041/00 9/016 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
918451009-83069-DTLTRT-06_14_2021-ANCHIDLE-1^668041/00 9/020 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-14 | 2024-06-14 | 2
918451009-83069-DTLTRT-06_14_2021-GO95HV-1^668041/00 9/020 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
609895596-50280-ADMIN-09_19_2022-GO95MLD-1^06239004.0245905 | OTHER | CA-TIER-2 | Distribution | 2022-09-19 | 2027-09-19 | 3
184515631-5801-DETAIL-01_25_2022-SVCWIND-1^06239004.0255141 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
781920921-62011-DETAIL-01_19_2022-SVCWIND-1^06239004.0255242 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
755580684-23360-DETAIL-01_19_2022-GO95MLD-1^06239004.0255301 | OTHER | CA-TIER-2 | Distribution | 2022-01-19 | 2025-01-19 | 2
73472308-98290-AUDIT-06_28_2022-GO95MLD-1^06239004.0255340 | OTHER | CA-TIER-2 | Distribution | 2022-06-28 | 2025-06-28 | 2
171071001-59201-DETAIL-01_12_2022-SVCRUBLG-1^06239004.0255443 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
596883106-24261-DETAIL-11_15_2022-GO95MLD-1^06239004.0365600 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
648574205-86941-DETAIL-11_14_2022-SVCWIND-1^06239004.0365701 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
358093516-99871-DETAIL-11_14_2022-SVCWIND-1^06239004.0365842 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
580267526-1371-DETAIL-11_14_2022-SVCWIND-2^06239004.0365940 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
88713355-76451-DETAIL-11_15_2022-GO95MLD-1^06239004.0366601 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
379275255-38361-DETAIL-11_15_2022-GO95MLD-1^06239004.0366604 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
252055586-42861-DETAIL-11_15_2022-GO95MLD-1^06239004.0366802 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
675650958-98340-ADMIN-06_18_2024-POLEREPL-1^06240003.0076102 | POLE | CA-TIER-2 | Distribution | 2024-06-18 | 2025-06-18 | 2
946060668-80440-ADMIN-09_23_2024-XARMSPCR-1^06240003.0077201 | CROSSARM | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
155019378-38440-ADMIN-09_23_2024-GO95MLD-1^06240003.0078300 | OTHER | CA-TIER-2 | Distribution | 2024-09-23 | 2027-09-23 | 2
395015888-24540-ADMIN-09_23_2024-GO95MLD-2^06240003.0078400 | OTHER | CA-TIER-2 | Distribution | 2024-09-23 | 2027-09-23 | 2
446555988-20940-ADMIN-09_23_2024-GO95MLD-1^06240003.0078401 | OTHER | CA-TIER-2 | Distribution | 2024-09-23 | 2027-09-23 | 2
611623298-18940-ADMIN-09_23_2024-GO95MLD-1^06240003.0079500 | OTHER | CA-TIER-2 | Distribution | 2024-09-23 | 2027-09-23 | 2
112743488-83940-ADMIN-09_23_2024-INSULDMG-1^06240003.0079501 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
898298008-17050-ADMIN-09_23_2024-XARMSPCR-1^06240003.0080601 | CROSSARM | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
973909138-350-ADMIN-06_18_2024-POLEREPL-1^06240003.0081700 | POLE | CA-TIER-2 | Distribution | 2024-06-18 | 2025-06-18 | 2
289982187-53970-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061203 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
839266937-41970-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
938744023-94230-DETAIL-06_27_2024-GO95CL10-1^06240004.0061601 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
545984213-31230-DETAIL-06_27_2024-GO95CL10-1^06240004.0061602 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
632074653-19830-DETAIL-04_27_2023-GO95MLD-1^06240004.0061702 | OTHER | CA-TIER-2 | Distribution | 2023-04-27 | 2026-04-27 | 2
964126619-270-DETAIL-04_24_2023-GO95MLD-1^06240004.0062200 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
413533213-3630-DETAIL-06_27_2024-GO95CL10-1^06240004.0062702 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
300458783-85530-DETAIL-04_25_2023-GO95MLD-1^06240004.0062704 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
300458783-85530-DETAIL-04_25_2023-GO95TCH-1^06240004.0062704 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
804839993-47430-DETAIL-06_27_2024-GO95CL10-1^06240004.0062705 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
836603229-50770-DETAIL-04_26_2023-SVCENTCO-1^06240004.0063100 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
731790413-27130-DETAIL-04_24_2023-GO95BLTC-1^06240004.0065400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
731790413-27130-DETAIL-04_24_2023-GO95MLD-1^06240004.0065400 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
740595353-53090-DETAIL-06_27_2024-GO95CL10-1^06240004.0065900 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
316804743-54279-DETAIL-06_27_2024-GO95TCH-1^06240004.0065901 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
510977353-19330-DETAIL-06_27_2024-CLRTOUCH-1^06240004.0065905 | CONDUCTOR | CA-TIER-2 | Distribution | 2024-06-27 | 2025-06-27 | 2
510977353-19330-DETAIL-06_27_2024-SVCDEFLC-1^06240004.0065905 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
565555763-58330-DETAIL-06_27_2024-GO95CL10-1^06240004.0066001 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
565555763-58330-DETAIL-06_27_2024-SVCDEFLC-1^06240004.0066001 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
938539443-11330-DETAIL-04_26_2023-GO95MLD-1^06240004.0066003 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
73200753-74330-DETAIL-06_27_2024-GO95HV-1^06240004.0066005 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
239338578-94678-DETAIL-04_26_2023-GO95MLD-1^06240004.0067002 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
403207076-10176-DETAIL-04_26_2023-SVCDEFLC-1^06240004.0067004 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
637478461-43433-DETAIL-01_24_2023-GO95HV-1^06240004.0079501 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2028-01-24 | 3
86246675-76770-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079502 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
305253141-60433-DETAIL-01_24_2023-GO95MLD-1^06240004.0079503 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
711833951-2433-DETAIL-01_24_2023-POLESTEP-1^06240004.0079504 | POLE | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
849528521-40333-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079505 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
758847233-18243-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079600 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
480943823-75243-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079700 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
497672561-6433-DETAIL-01_24_2023-ABNDEQPM-1^06240004.0079702 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
927487811-27233-DETAIL-01_24_2023-GO95MLD-1^06240004.0079740 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
200269423-37243-DETAIL-01_24_2023-SVCROAD-1^06240004.0079800 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
780833015-69270-DETAIL-01_24_2023-GO95MLD-1^06240004.0079801 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
311394818-48970-DETAIL-01_23_2023-GO95MLD-1^06240004.0081202 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
311394818-48970-DETAIL-01_23_2023-GO95TCH-1^06240004.0081202 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
433057508-10170-DETAIL-01_24_2023-ABNDEQPM-1^06240004.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
433057508-10170-DETAIL-01_24_2023-GO95BLTC-1^06240004.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
433057508-10170-DETAIL-01_24_2023-GO95HV-1^06240004.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
433057508-10170-DETAIL-01_24_2023-GO95MLD-1^06240004.0081300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
796110406-73840-DETAIL-01_19_2023-GO95MLD-1^06240004.0081302 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
620919626-58740-DETAIL-01_19_2023-GO95MLD-1^06240004.0081440 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
252286748-79930-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081500 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
9658378-96920-DETAIL-01_19_2023-GO95MLD-1^06240004.0081641 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
9658378-96920-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081641 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
354381038-79830-DETAIL-01_19_2023-GO95MLD-1^06240004.0081700 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
354381038-79830-DETAIL-01_19_2023-RISEGRD-1^06240004.0081700 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
274967218-17830-DETAIL-01_19_2023-GO95TCH-1^06240004.0081701 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
274967218-17830-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081701 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
274967218-17830-DETAIL-01_19_2023-SVCDEFLC-2^06240004.0081701 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
507026169-80430-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081800 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
813471508-87270-DETAIL-01_17_2023-GO95MLD-1^06240004.0082201 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
778608288-17070-DETAIL-01_17_2023-GO95MLD-1^06240004.0082202 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
778608288-17070-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0082202 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
778608288-17070-DETAIL-01_17_2023-SVCDEFLC-2^06240004.0082202 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
774008336-86569-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0082203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
774008336-86569-DETAIL-01_17_2023-SVCDEFLC-2^06240004.0082203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
496255146-40940-DETAIL-01_17_2023-GO95TCH-1^06240004.0082204 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
496255146-40940-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0082204 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
251044808-50170-DETAIL-01_19_2023-GO95TCH-1^06240004.0082401 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
251044808-50170-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0082401 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
688128728-38830-DETAIL-01_19_2023-GO95HV-1^06240004.0082506 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2028-01-19 | 3
688128728-38830-DETAIL-01_19_2023-GO95MLD-1^06240004.0082506 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
688128728-38830-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0082506 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
367335318-16830-DETAIL-01_19_2023-GO95MLD-1^06240004.0082601 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
769433398-91970-DETAIL-01_23_2023-GO95MLD-1^06240004.0083000 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
188781926-6640-DETAIL-01_17_2023-GO95MLD-1^06240004.0083041 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
927187968-15070-DETAIL-01_17_2023-GO95MLD-1^06240004.0083101 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
500495266-80840-DETAIL-01_17_2023-GO95MLD-1^06240004.0083140 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
558945956-63940-DETAIL-01_17_2023-GO95MLD-1^06240004.0083201 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
235374876-54940-DETAIL-01_17_2023-GO95HV-1^06240004.0083203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
235374876-54940-DETAIL-01_17_2023-GO95MLD-1^06240004.0083203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
235374876-54940-DETAIL-01_17_2023-GUYHINS-1^06240004.0083203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
235374876-54940-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0083203 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
386041398-76570-DETAIL-01_17_2023-GO95MLD-1^06240004.0083303 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
657875816-87540-DETAIL-01_17_2023-GO95TCH-1^06240004.0083340 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
657875816-87540-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0083340 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
676698158-62130-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0083500 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
149138968-3130-DETAIL-01_19_2023-GO95TCH-1^06240004.0083501 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
53557939-95330-DETAIL-01_19_2023-GO95MLD-1^06240004.0083503 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
397234089-30330-DETAIL-01_19_2023-GO95MLD-1^06240004.0083600 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
697735889-53430-DETAIL-01_18_2023-SVCDEFLC-1^06240004.0083702 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
868284834-79003-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0084042 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
125387048-78070-DETAIL-01_17_2023-GO95MLD-1^06240004.0084302 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
525091215-70489-DETAIL-01_18_2023-GO95MLD-1^06240004.0084600 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
333016308-88030-DETAIL-01_18_2023-SVCDEFLC-1^06240004.0084601 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
956958429-74330-DETAIL-01_18_2023-GO95MLD-1^06240004.0084702 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
457815289-74810-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085041 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
932180009-6220-DETAIL-01_17_2023-GO95MLD-1^06240004.0085042 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
734150340-4630-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085044 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
980427192-50470-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085101 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
228960382-85370-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085102 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
959133402-37370-DETAIL-01_17_2023-GO95MLD-1^06240004.0085302 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
959133402-37370-DETAIL-01_17_2023-GUYHINS-1^06240004.0085302 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
931107092-96370-DETAIL-01_17_2023-GO95MLD-1^06240004.0085303 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
931107092-96370-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085303 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
124211572-55370-DETAIL-01_18_2023-SVCDEFLC-1^06240004.0085304 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
145199605-45530-DETAIL-01_17_2023-GO95TCH-1^06240004.0085341 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
145199605-45530-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0085341 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
205049311-17030-DETAIL-01_18_2023-GO95CL10-1^06240004.0085400 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2028-01-18 | 3
695928692-89370-DETAIL-01_18_2023-GO95MLD-1^06240004.0085401 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
227352128-97330-DETAIL-01_18_2023-GO95MLD-1^06240004.0085602 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
535443198-31730-DETAIL-01_18_2023-GO95HV-1^06240004.0085603 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2028-01-18 | 3
429070508-73330-DETAIL-01_18_2023-GO95MLD-1^06240004.0085606 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
19099405-1530-DETAIL-01_17_2023-GO95HV-1^06240004.0086141 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
19099405-1530-DETAIL-01_17_2023-GO95MLD-1^06240004.0086141 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
892468185-73530-DETAIL-01_18_2023-GO95MLD-1^06240004.0086240 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
892468185-73530-DETAIL-01_18_2023-SVCDEFLC-1^06240004.0086240 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
763930275-33530-DETAIL-01_17_2023-GO95HV-1^06240004.0086241 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2028-01-17 | 3
763930275-33530-DETAIL-01_17_2023-GO95MLD-1^06240004.0086241 | OTHER | CA-TIER-2 | Distribution | 2023-01-17 | 2026-01-17 | 2
516642426-28470-DETAIL-01_24_2022-GO95MLD-1^06239004.0257205 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
529054051-79401-DETAIL-01_25_2022-GO95MLD-1^06239004.0257442 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
954510988-80988-DETAIL-01_25_2022-SVCROAD-1^06239004.0258009 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
506235205-5270-DETAIL-01_25_2022-GO95MLD-1^06239004.0258301 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
713329821-44101-DETAIL-01_25_2022-GO95MLD-1^06239004.0258441 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
293309732-20832-DETAIL-11_09_2022-ABNDEQPM-1^06239004.0362407 | OTHER | CA-TIER-2 | Distribution | 2022-11-09 | 2027-11-09 | 3
474432336-31661-DETAIL-11_16_2022-GO95MLD-1^06239004.0365501 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
600794156-21661-DETAIL-11_15_2022-GO95MLD-1^06239004.0366804 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
600794156-21661-DETAIL-11_15_2022-SVCWIND-1^06239004.0366804 | OTHER | CA-TIER-2 | Distribution | 2022-11-15 | 2025-11-15 | 2
40222666-88861-DETAIL-11_14_2022-SVCWIND-1^06239004.0366903 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
595804886-10571-ADMIN-06_21_2024-POLEREPL-1^06239004.0367841 | POLE | CA-TIER-2 | Distribution | 2024-06-21 | 2025-06-21 | 2
883723306-55971-DETAIL-11_16_2022-GO95MLD-1^06239004.0367842 | OTHER | CA-TIER-2 | Distribution | 2022-11-16 | 2025-11-16 | 2
65505056-69171-DETAIL-11_14_2022-GO95MLD-1^06239004.0367944 | OTHER | CA-TIER-2 | Distribution | 2022-11-14 | 2025-11-14 | 2
537538278-39450-ADMIN-09_23_2024-INSULDMG-1^06240003.0052000 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
774613268-42450-ADMIN-09_23_2024-INSULDMG-1^06240003.0052002 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
574100988-23550-ADMIN-09_23_2024-INSULDMG-1^06240003.0053201 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
516098128-67650-ADMIN-09_23_2024-INSULDMG-1^06240003.0055500 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
243039228-14750-ADMIN-09_23_2024-ANCPUCO-1^06240003.0056600 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
542110438-95750-ADMIN-09_23_2024-POLEREPL-1^06240003.0056700 | POLE | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
910700438-96750-ADMIN-09_23_2024-ANCPUCO-1^06240003.0057701 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
289882848-62850-ADMIN-09_23_2024-UBBRACE-1^06240003.0058800 | CROSSARM | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
441422648-48950-ADMIN-09_23_2024-COPLLEAN-1^06240003.0058900 | POLE | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
139848858-72050-ADMIN-09_23_2024-ANCPUCO-1^06240003.0059900 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
561036958-67350-ADMIN-09_23_2024-XARMSPCR-1^06240003.0081801 | CROSSARM | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
856067846-13080-DETAIL-04_26_2023-GO95CL10-1^06240004.0050004 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
856067846-13080-DETAIL-04_26_2023-GO95MLD-1^06240004.0050004 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
975048126-41480-DETAIL-05_01_2023-GO95MLD-1^06240004.0050100 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
693602216-94980-DETAIL-05_01_2023-GO95MLD-1^06240004.0050140 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
693602216-94980-DETAIL-05_01_2023-GRDRODHI-1^06240004.0050140 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
572198636-28980-DETAIL-05_01_2023-SVCDEFLC-1^06240004.0050141 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
936510216-32980-DETAIL-05_01_2023-GO95MLD-1^06240004.0050142 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
299265658-5850-DETAIL-04_26_2023-GO95MLD-1^06240004.0050144 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
896026976-29080-DETAIL-04_26_2023-SVCDEFLC-1^06240004.0051000 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
353483896-44280-DETAIL-04_26_2023-GO95MLD-1^06240004.0051001 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
666803259-86510-DETAIL-05_01_2023-GO95HV-1^06240004.0051440 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2028-05-01 | 3
146901476-62680-DETAIL-05_01_2023-GO95MLD-1^06240004.0052300 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
489751986-41780-DETAIL-05_01_2023-GO95MLD-1^06240004.0052301 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
654179707-64970-DETAIL-04_26_2023-GO95MLD-1^06240004.0060100 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
912521697-54970-DETAIL-04_26_2023-GO95MLD-1^06240004.0060101 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
912521697-54970-DETAIL-04_26_2023-SVCROAD-1^06240004.0060101 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
607382919-48670-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0060401 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
397275904-87904-DETAIL-04_24_2023-GO95MLD-1^06240004.0061002 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
514186515-20569-DETAIL-04_24_2023-GO95HV-1^06240004.0061100 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
260512225-12275-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061102 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
492251139-22370-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061106 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
19071749-82370-DETAIL-04_26_2023-GO95MLD-1^06240004.0063101 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
823278728-33170-DETAIL-06_27_2024-SVCDEFLC-1^06240004.0063103 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
173903839-90370-DETAIL-04_26_2023-ABNDEQPM-1^06240004.0063200 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2028-04-26 | 3
262862697-39970-DETAIL-06_27_2024-SVCROAD-1^06240004.0063202 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
262862697-39970-DETAIL-06_27_2024-SVCROAD-2^06240004.0063202 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
480089259-27370-DETAIL-06_27_2024-GO95TCH-1^06240004.0063206 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
904239093-36430-DETAIL-06_27_2024-GO95CL10-1^06240004.0063700 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
677281368-31270-DETAIL-06_27_2024-GUYHINS-1^06240004.0064103 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
677281368-31270-DETAIL-06_27_2024-GUYHINS-2^06240004.0064103 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
872466569-80470-DETAIL-04_26_2023-GO95MLD-1^06240004.0064200 | OTHER | CA-TIER-2 | Distribution | 2023-04-26 | 2026-04-26 | 2
686978587-88970-DETAIL-06_27_2024-GO95CL10-1^06240004.0064202 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
355015239-44770-DETAIL-06_27_2024-GO95CL10-1^06240004.0064203 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
20030163-31430-DETAIL-05_01_2023-GO95MLD-1^06240004.0064541 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
544342143-94330-DETAIL-05_01_2023-GO95MLD-1^06240004.0064601 | OTHER | CA-TIER-2 | Distribution | 2023-05-01 | 2026-05-01 | 2
358966183-96930-DETAIL-04_25_2023-GO95MLD-1^06240004.0064700 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
358966183-96930-DETAIL-04_25_2023-SVCDEFLC-1^06240004.0064700 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
967263773-84930-DETAIL-06_27_2024-GO95CL10-1^06240004.0064701 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
643151903-92130-DETAIL-06_27_2024-GO95CL10-1^06240004.0064801 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2029-06-27 | 3
292285509-97419-DETAIL-04_25_2023-GO95MLD-1^06240004.0064803 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2028-04-25 | 3
292285509-97419-DETAIL-04_25_2023-SVCROAD-1^06240004.0064803 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
991229733-35730-DETAIL-04_25_2023-GO95MLD-1^06240004.0064804 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
991229733-35730-DETAIL-04_25_2023-RISECLMB-1^06240004.0064804 | OTHER | CA-TIER-2 | Distribution | 2023-04-25 | 2026-04-25 | 2
56852113-9590-DETAIL-06_27_2024-SVCDEFLC-1^06240004.0064901 | OTHER | CA-TIER-2 | Distribution | 2024-06-27 | 2027-06-27 | 2
509773733-29230-DETAIL-06_26_2024-SVCNEUT-1^06240004.0065103 | OTHER | CA-TIER-2 | Distribution | 2024-06-26 | 2027-06-26 | 2
838498341-6469-DTLTRT-07_20_2022-GO95HV-1^668005/00 9/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
64094449-3869-ADMIN-06_15_2021-POLEDERP-1^668005/03 10/005 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
573487674-81598-ADMIN-06_15_2021-POLEDERP-1^668005/03 16/005 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
573487674-81598-DTLTRT-10_10_2022-GO95HV-1^668005/03 16/005 | OTHER | CA-NON-TIER | Transmission | 2022-10-10 | 2027-10-10 | 3
768286448-86069-ADMIN-06_15_2021-POLEDERP-1^668005/03 18/002 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
768286448-86069-DTLTRT-10_11_2022-GO95HV-1^668005/03 18/002 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
793578783-83898-ADMIN-06_15_2021-POLEDERP-1^668005/03 18/003 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
854360988-66669-DTLTRT-10_11_2022-GO95HV-1^668005/03 3/003 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
74234608-37669-DTLTRT-10_11_2022-GO95HV-1^668005/03 4/003 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
74234608-37669-DTLTRT-10_11_2022-GO95MLD-1^668005/03 4/003 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2025-10-11 | 2
638418219-63769-ADMIN-02_07_2022-POLEDERP-1^668005/03 5/004 | POLE | CA-NON-TIER | Transmission | 2022-02-07 | 2025-02-07 | 2
58139215-71869-ADMIN-05_15_2021-POLEDERP-1^668005/03 7/005 | POLE | CA-NON-TIER | Transmission | 2021-05-15 | 2024-05-15 | 2
58139215-71869-DTLTRT-10_10_2022-GO95HV-1^668005/03 7/005 | OTHER | CA-NON-TIER | Transmission | 2022-10-10 | 2027-10-10 | 3
247872599-25769-ADMIN-02_07_2022-POLEDERP-1^668005/03 8/004 | POLE | CA-NON-TIER | Transmission | 2022-02-07 | 2025-02-07 | 2
343230929-12869-ADMIN-06_15_2021-POLEDERP-1^668005/03 8/005 | POLE | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
343230929-12869-DTLTRT-10_10_2022-GO95HV-1^668005/03 8/005 | OTHER | CA-NON-TIER | Transmission | 2022-10-10 | 2027-10-10 | 3
966639568-63259-DTLTRT-10_11_2022-GO95HV-1^668005/03 9/003 | OTHER | CA-NON-TIER | Transmission | 2022-10-11 | 2027-10-11 | 3
164367003-70060-DETAIL-01_12_2023-GO95HV-1^06240004.0072341 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2028-01-12 | 3
164367003-70060-DETAIL-01_12_2023-GO95MLD-1^06240004.0072341 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
136214573-62960-DETAIL-01_12_2023-GO95MLD-1^06240004.0072343 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
406397463-71860-DETAIL-01_12_2023-GO95MLD-1^06240004.0073340 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
457101853-67760-DETAIL-01_12_2023-GO95HV-1^06240004.0073342 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2028-01-12 | 3
758558494-21360-DETAIL-01_12_2023-GO95MLD-1^06240004.0074300 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
957702004-8360-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0076300 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
625148304-26360-DETAIL-01_12_2023-GO95MLD-1^06240004.0076301 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
700016313-72660-DETAIL-01_12_2023-GO95MLD-1^06240004.0076340 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
455465513-49560-DETAIL-01_12_2023-SVCROAD-1^06240004.0076341 | OTHER | CA-TIER-3 | Distribution | 2023-01-12 | 2026-01-12 | 2
18734461-74533-DETAIL-01_24_2023-GO95MLD-1^06240004.0077941 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
574467261-42533-DETAIL-01_24_2023-GO95MLD-1^06240004.0077942 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
558214470-16221-DTLTRT-06_15_2021-GO95HV-1^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
558214470-16221-DTLTRT-06_15_2021-GO95MLD-1^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
558214470-16221-DTLTRT-06_15_2021-GO95MLD-2^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
558214470-16221-DTLTRT-06_15_2021-GRDRODHI-1^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
558214470-16221-DTLTRT-06_15_2021-GRDRODHI-2^668041/00 1/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
702056718-10969-DTLTRT-06_09_2021-COPLLEAN-1^668041/00 10/017 | POLE | CA-NON-TIER | Transmission | 2021-06-09 | 2024-06-09 | 2
407780811-95369-DTLTRT-06_02_2021-GO95HV-1^668041/00 11/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
131148121-36369-DTLTRT-06_02_2021-GO95HV-1^668041/00 12/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
758352138-27069-ADMIN-01_31_2023-POLEDERP-1^668041/00 12/015 | POLE | CA-NON-TIER | Transmission | 2023-01-31 | 2026-01-31 | 2
673344589-60069-DTLTRT-06_14_2021-GO95HV-1^668041/00 12/019 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
490899301-13469-DTLTRT-06_16_2021-GUYNOINS-1^668041/00 12/023 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-16 | 2024-06-16 | 2
490899301-13469-DTLTRT-06_16_2021-GUYNOINS-2^668041/00 12/023 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-16 | 2024-06-16 | 2
672390424-37841-ADMIN-02_26_2021-COPLLEAN-1^668041/00 12/028 | POLE | CA-NON-TIER | Transmission | 2021-02-26 | 2024-02-26 | 2
700216310-42269-DTLTRT-06_02_2021-GO95HV-1^668041/00 13/003 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
403724939-21269-DTLTRT-06_14_2021-GO95HV-1^668041/00 13/020 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
664626469-41269-DTLTRT-06_14_2021-GO95HV-1^668041/00 14/020 | OTHER | CA-NON-TIER | Transmission | 2021-06-14 | 2026-06-14 | 3
62308650-14369-DTLTRT-06_15_2021-GO95HV-1^668041/00 15/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
263980893-70369-DTLTRT-06_23_2021-COPLLEAN-1^668041/00 15/032 | POLE | CA-NON-TIER | Transmission | 2021-06-23 | 2024-06-23 | 2
854603392-19933-DETAIL-01_24_2023-GO95TCH-1^06240004.0078500 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
928336936-71480-DETAIL-01_24_2023-GO95MLD-1^06240004.0078600 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
385252943-58243-DETAIL-01_24_2023-GO95HV-1^06240004.0078601 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2028-01-24 | 3
716568165-90770-DETAIL-01_24_2023-GO95MLD-1^06240004.0078800 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
733529874-50160-DETAIL-01_24_2023-GO95MLD-1^06240004.0079300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
733529874-50160-DETAIL-01_24_2023-SVCDEFLC-1^06240004.0079300 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
695524444-96060-DETAIL-01_24_2023-GO95MLD-1^06240004.0079401 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
695524444-96060-DETAIL-01_24_2023-GRDRODHI-1^06240004.0079401 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
695524444-96060-DETAIL-01_24_2023-GRDRODHI-2^06240004.0079401 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
715020308-97660-DETAIL-01_24_2023-GO95BLTC-1^06240004.0079405 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
715020308-97660-DETAIL-01_24_2023-GO95MLD-1^06240004.0079405 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
994076064-38960-DETAIL-01_24_2023-GO95MLD-1^06240004.0079406 | OTHER | CA-TIER-3 | Distribution | 2023-01-24 | 2026-01-24 | 2
583902501-28369-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/006 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
36328941-64469-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/007 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
272157782-3569-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
553642103-20669-DTLTRT-06_04_2021-GO95HV-1^668041/00 3/009 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
221349033-38669-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
347686913-94769-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
50345243-93869-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/012 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
240178078-94869-DTLTRT-06_10_2021-GO95HV-1^668041/00 3/016 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
35153213-54259-DTLTRT-06_17_2021-GO95HV-1^668041/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2021-06-17 | 2026-06-17 | 3
35153213-54259-DTLTRT-06_17_2021-GO95MLD-1^668041/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2021-06-17 | 2024-06-17 | 2
35153213-54259-DTLTRT-06_17_2021-SVCROAD-1^668041/00 3/027 | OTHER | CA-NON-TIER | Transmission | 2021-06-17 | 2024-06-17 | 2
770328001-91369-DTLTRT-06_02_2021-GO95HV-1^668041/00 4/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
470877513-75769-DTLTRT-06_07_2021-GO95HV-1^668041/00 4/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
327581721-18681-ADMIN-03_03_2021-UBBRACE-1^668041/00 4/022 | CROSSARM | CA-NON-TIER | Transmission | 2021-03-03 | 2024-03-03 | 2
856429770-66269-DTLTRT-06_02_2021-GO95HV-1^668041/00 5/004 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
363765761-35469-DTLTRT-06_03_2021-GO95HV-1^668041/00 5/007 | OTHER | CA-NON-TIER | Transmission | 2021-06-03 | 2026-06-03 | 3
438432192-93569-DTLTRT-06_04_2021-GO95HV-1^668041/00 5/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
39784913-21669-DTLTRT-06_04_2021-GO95HV-1^668041/00 5/009 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
680106823-46769-DTLTRT-06_07_2021-GO95HV-1^668041/00 5/011 | OTHER | CA-NON-TIER | Transmission | 2021-06-07 | 2026-06-07 | 3
749648829-60769-DTLTRT-06_08_2021-GO95HV-1^668041/00 5/014 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
567325788-169-DTLTRT-06_10_2021-ANCHIDLE-1^668041/00 5/016 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2021-06-10 | 2024-06-10 | 2
567325788-169-DTLTRT-06_10_2021-GO95HV-1^668041/00 5/016 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
305093502-34569-DTLTRT-06_04_2021-GO95HV-1^668041/00 6/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
184279808-46069-DTLTRT-06_10_2021-GO95HV-1^668041/00 6/015 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
446507549-13969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 6/018 | POLE | CA-NON-TIER | Transmission | 2021-02-24 | 2024-02-24 | 2
703166581-56281-ADMIN-02_18_2022-INSULDMG-1^668041/00 6/022 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-18 | 2025-02-18 | 2
257059733-25490-ADMIN-02_26_2021-INSULDMG-1^668041/00 6/026 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-02-26 | 2024-02-26 | 2
891309443-48392-ADMIN-02_17_2022-INSULDMG-1^668041/00 6/027 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-17 | 2025-02-17 | 2
449197054-98601-DTLTRT-06_21_2021-GO95HV-1^668041/00 6/028 | OTHER | CA-NON-TIER | Transmission | 2021-06-21 | 2026-06-21 | 3
449197054-98601-ADMIN-02_01_2022-POLEDERP-1^668041/00 6/028 | POLE | CA-NON-TIER | Transmission | 2022-02-01 | 2025-02-01 | 2
71828990-67269-DTLTRT-06_02_2021-GO95HV-1^668041/00 7/004 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
776349483-89669-DTLTRT-06_08_2021-GO95HV-1^668041/00 7/010 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
890862438-3688-DTLTRT-06_08_2021-GO95HV-1^668041/00 7/013 | OTHER | CA-NON-TIER | Transmission | 2021-06-08 | 2026-06-08 | 3
598893539-58569-DTLTRT-06_09_2021-GO95HV-1^668041/00 7/014 | OTHER | CA-NON-TIER | Transmission | 2021-06-09 | 2026-06-09 | 3
610116518-72869-DTLTRT-06_10_2021-GO95HV-1^668041/00 7/015 | OTHER | CA-NON-TIER | Transmission | 2021-06-10 | 2026-06-10 | 3
639581401-84161-DTLTRT-06_15_2021-GO95HV-1^668041/00 7/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
211573643-96259-ADMIN-02_26_2021-INSULDMG-1^668041/00 7/026 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-02-26 | 2024-02-26 | 2
15244453-63889-ADMIN-02_17_2022-INSULDMG-1^668041/00 7/027 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-17 | 2025-02-17 | 2
784898612-62742-DTLTRT-06_22_2021-LIGHT-1^668041/00 7/030 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2021-06-22 | 2024-06-22 | 2
799259371-4369-DTLTRT-06_02_2021-GO95HV-1^668041/00 8/005 | OTHER | CA-NON-TIER | Transmission | 2021-06-02 | 2026-06-02 | 3
47127222-94569-DTLTRT-06_04_2021-GO95HV-1^668041/00 8/008 | OTHER | CA-NON-TIER | Transmission | 2021-06-04 | 2026-06-04 | 3
632701831-17199-DTLSB-02_14_2023-INSULDMG-1^06248001.0339801 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
558335602-42651-DTLSB-02_20_2023-GO95MLD-1^06248001.0340900 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
558335602-42651-DTLSB-02_20_2023-GO95TCH-1^06248001.0340900 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
60260503-14270-DTLSB-02_14_2023-GO95HV-1^06248001.0341700 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
673089523-72941-DTLTRT-02_14_2023-GO95BLTC-1^06248001.0342701 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
13967892-87892-DTLTRT-02_14_2023-GO95BLTC-1^06248001.0342702 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
532204242-78421-DTLSB-02_20_2023-GO95HV-1^06248001.0345800 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
532204242-78421-DTLSB-02_20_2023-GO95MLD-1^06248001.0345800 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
357410003-75400-DTLSB-02_14_2023-GO95MLD-1^06248001.0346901 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
561998340-44761-DTLSB-02_14_2023-GO95MLD-1^06248001.0347600 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
561998340-44761-AUDIT-02_22_2023-GO95HV-1^06248001.0347600 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
348806223-83190-DTLSB-02_14_2023-GO95MLD-1^06248001.0347601 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
189948443-62630-DTLSB-02_14_2023-CLRTOUCH-1^06248001.0349501 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
189948443-62630-DTLSB-02_14_2023-GO95MLD-1^06248001.0349501 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
526929034-65811-DTLSB-02_06_2023-GO95MLD-1^06248001.0353800 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
166184735-92910-DTLSB-02_02_2023-GO95MLD-1^06248001.0360900 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
166184735-92910-DTLSB-02_02_2023-SVCENTBK-1^06248001.0360900 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
166184735-92910-DTLSB-02_02_2023-SVCROAD-1^06248001.0360900 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
554934385-95551-DTLSB-02_02_2023-ENCHRW-1^06248001.0360901 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
854567000-95100-DTLSB-01_30_2023-GUYLOINS-1^06248001.0366900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
288594316-7489-DTLSB-01_31_2023-GO95MLD-1^06248001.0367800 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
165647376-52710-DTLSB-01_31_2023-GO95HV-1^06248001.0367801 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
156865376-1390-DTLSB-01_31_2023-GO95MLD-1^06248001.0367804 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
215972096-36950-DTLSB-01_31_2023-SVCENTCO-1^06248001.0367805 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
211330805-38270-DETAIL-01_24_2023-GO95MLD-1^06240004.0079804 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
631638878-18920-DETAIL-01_19_2023-GO95MLD-1^06240004.0079840 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
339192096-42280-DETAIL-01_24_2023-GO95MLD-1^06240004.0079901 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
7474213-69933-DETAIL-01_24_2023-GO95MLD-1^06240004.0079902 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
200687838-93170-DETAIL-01_23_2023-GO95MLD-1^06240004.0080002 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
363001009-16530-DETAIL-01_23_2023-SVCDEFLC-1^06240004.0080003 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
213428878-26170-DETAIL-01_23_2023-GO95MLD-1^06240004.0080100 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
568539596-2840-DETAIL-01_26_2023-GUYHINS-1^06240004.0080200 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
163413999-75530-DETAIL-01_26_2023-GUYHINS-1^06240004.0080201 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-26 | 2026-01-26 | 2
266546388-29170-DETAIL-01_23_2023-SVCROAD-1^06240004.0080204 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
199250528-14370-DETAIL-01_23_2023-GO95MLD-1^06240004.0080206 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
199250528-14370-DETAIL-01_23_2023-POLESTEP-1^06240004.0080206 | POLE | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
751701365-8261-DTLSB-02_01_2023-GO95MLD-1^06248001.0368000 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
734220465-47979-DTLSB-02_01_2023-GO95MLD-1^06248001.0368001 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
315357875-82560-DTLSB-02_01_2023-GO95BLTC-1^06248001.0368101 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
315357875-82560-DTLSB-02_01_2023-GO95HV-1^06248001.0368101 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
315357875-82560-DTLSB-02_01_2023-GO95MLD-1^06248001.0368101 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
116096985-42060-DTLSB-02_02_2023-GO95MLD-1^06248001.0368102 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
419830485-33870-DTLSB-02_02_2023-SVCENTCO-1^06248001.0368104 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
210449505-27050-DTLSB-02_01_2023-ENCHRW-1^06248001.0368301 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
963916995-20263-DTLSB-02_01_2023-GO95MLD-1^06248001.0368302 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
791182866-74662-DTLSB-02_01_2023-GO95MLD-1^06248001.0368701 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
532146226-67979-DTLSB-01_31_2023-GO95MLD-1^06248001.0368803 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
488157116-45861-DTLSB-01_31_2023-GUYHINS-1^06248001.0368808 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
778294276-38232-DTLSB-02_01_2023-SVCROAD-1^06248001.0368904 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
460839856-51956-DTLSB-01_30_2023-GO95MLD-1^06248001.0368906 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
907479025-34162-DTLSB-02_01_2023-GO95HV-1^06248001.0369201 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
174578905-23410-DTLSB-02_01_2023-ABNDEQPM-1^06248001.0369300 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
885889655-60172-DTLSB-02_01_2023-GO95MLD-1^06248001.0369304 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
185153626-89220-DTLSB-01_31_2023-GO95MLD-1^06248001.0369500 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
293124226-30379-DTLSB-02_01_2023-GO95MLD-1^06248001.0369600 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
293124226-30379-DTLSB-02_01_2023-GRDBROKE-1^06248001.0369600 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
305491966-16450-DTLSB-02_01_2023-GO95MLD-1^06248001.0369601 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
737958266-34221-DTLSB-02_01_2023-GO95TCH-1^06248001.0369603 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
676034716-75579-DTLSB-01_31_2023-GO95MLD-1^06248001.0369701 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
685897466-20171-DTLSB-01_31_2023-GO95HV-1^06248001.0369704 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2028-01-31 | 3
317961201-76161-DTLTRT-06_15_2021-GO95HV-1^668041/00 9/022 | OTHER | CA-NON-TIER | Transmission | 2021-06-15 | 2026-06-15 | 3
108971580-39355-ADMIN-04_05_2021-INSULBRK-1^668041/00 9/029 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-04-05 | 2024-04-05 | 2
108971580-39355-ADMIN-02_01_2022-INSULDMG-2^668041/00 9/029 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-02-01 | 2025-02-01 | 2
525113935-43919-ADMIN-09_14_2023-POLEREPL-1^668078/00 2/002 | POLE | CA-NON-TIER | Transmission | 2023-09-14 | 2026-09-14 | 2
716800977-28370-DTLSB-04_27_2021-ENCHRW-1^06236005.0113900 | OTHER | CA-TIER-2 | Distribution | 2021-04-27 | 2024-04-27 | 2
373467235-30310-DETAIL-11_10_2022-GO95HV-1^06238004.0222502 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2027-11-10 | 3
299017425-58210-DETAIL-11_10_2022-SVCWIND-1^06238004.0223601 | OTHER | CA-TIER-2 | Distribution | 2022-11-10 | 2025-11-10 | 2
637334801-85250-DETAIL-11_17_2022-SVCROAD-1^06238004.0272801 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
97110436-82279-DTLSB-01_31_2023-GO95TCH-1^06248001.0369803 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
177299296-69920-DTLSB-02_01_2023-GO95MLD-1^06248001.0369806 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
300518706-26140-DTLSB-02_01_2023-GO95MLD-1^06248001.0369807 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
263566413-30423-AUDIT-03_07_2023-GUYNOINS-1^06248001.0369820 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
772921416-60512-DTLSB-01_30_2023-GO95BLTC-1^06248001.0369900 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
792917956-40672-DTLSB-01_30_2023-ABNDEQPM-1^06248001.0369901 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
104333746-81379-DTLSB-02_01_2023-GO95HV-1^06248001.0369903 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
104333746-81379-DTLSB-02_01_2023-GO95TCH-1^06248001.0369903 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
600522756-98511-DTLSB-02_01_2023-GO95MLD-1^06248001.0369906 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
966902071-91173-DTLSB-02_15_2023-GO95MLD-1^06248002.0340401 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
134184641-29370-DTLSB-02_15_2023-GO95MLD-1^06248002.0349500 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
177999036-45459-ADMIN-09_26_2022-UBPBXARM-1^668004/00 1/025 | CROSSARM | CA-NON-TIER | Transmission | 2022-09-26 | 2025-09-26 | 2
125204743-5598-ADMIN-07_24_2020-POLEDERP-1^668004/00 4/025 | POLE | CA-NON-TIER | Transmission | 2020-07-24 | 2023-07-24 | 2
715148266-52759-ADMIN-03_31_2022-INSULDMG-1^668004/00 6/017 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-03-31 | 2025-03-31 | 2
945076758-76969-DTLTRT-06_30_2022-GO95HV-1^668005/00 1/031 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
652021908-17269-DTLTRT-07_05_2022-GO95BLTC-1^668005/00 1/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
652021908-17269-DTLTRT-07_05_2022-GO95HV-1^668005/00 1/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
652021908-17269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 1/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
76571108-13469-DTLTRT-07_06_2022-GO95HV-1^668005/00 1/037 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
729363448-80569-DTLTRT-07_06_2022-GO95MLD-1^668005/00 1/038 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2025-07-06 | 2
841253960-3069-AUDIT-08_29_2022-GO95HV-1^668005/00 1/047 | OTHER | CA-NON-TIER | Transmission | 2022-08-29 | 2027-08-29 | 3
26088180-15169-DTLTRT-07_18_2022-GO95HV-1^668005/00 1/049 | OTHER | CA-NON-TIER | Transmission | 2022-07-18 | 2027-07-18 | 3
862652364-8469-DTLTRT-07_20_2022-GO95HV-1^668005/00 1/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
637334801-85250-DETAIL-11_17_2022-SVCROAD-2^06238004.0272801 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
857574491-54650-DETAIL-11_17_2022-SVCROAD-1^06238004.0274800 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
857574491-54650-ADMIN-08_29_2024-POLEREPL-1^06238004.0274800 | POLE | CA-TIER-2 | Distribution | 2024-08-29 | 2025-08-29 | 2
153399971-54150-DETAIL-11_17_2022-SVCDECK-1^06238004.0274801 | OTHER | CA-TIER-2 | Distribution | 2022-11-17 | 2025-11-17 | 2
506129224-990-ADMIN-05_26_2023-POLEREPL-2^06239002.0063605 | POLE | CA-NON-TIER | Distribution | 2023-05-26 | 2026-05-26 | 2
601822316-7910-ADMIN-06_18_2024-POLEREPL-1^06239003.0015900 | POLE | CA-NON-TIER | Distribution | 2024-06-18 | 2027-06-18 | 2
848010196-31180-DETAIL-03_30_2021-ENCHRW-1^06239004.0244800 | OTHER | CA-TIER-2 | Distribution | 2021-03-30 | 2024-03-30 | 2
818495418-69769-DTLTRT-06_30_2022-GO95MLD-1^668005/00 12/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
846877540-41159-DTLTRT-07_05_2022-GO95MLD-1^668005/00 12/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
846877540-41159-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 12/034 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
239570371-37469-DTLTRT-07_20_2022-GO95HV-1^668005/00 12/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
867576958-78859-DTLTRT-06_30_2022-GO95MLD-1^668005/00 13/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
964146508-92369-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 13/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
589250919-77691-ADMIN-12_21_2022-GUYSLACK-1^668005/00 13A/028 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
639221478-869-DTLTRT-06_30_2022-GO95MLD-1^668005/00 14/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
280523978-2169-DTLTRT-06_30_2022-GO95MLD-1^668005/00 15/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
231392499-40269-DTLTRT-07_05_2022-GO95HV-1^668005/00 15/033 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
231392499-40269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 15/033 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
85379488-49520-DTLTRT-06_28_2022-GO95MLD-1^668005/00 16/027 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
398159588-62169-DTLTRT-06_30_2022-GO95HV-1^668005/00 16/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
908430639-80269-DTLTRT-07_05_2022-GO95HV-1^668005/00 16/033 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
341532538-48069-DETAIL-06_30_2022-GO95HV-1^668005/00 2/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
448704470-43069-DTLTRT-07_15_2022-GO95HV-1^668005/00 2/047 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
763514979-81269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 20/033 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
646164629-83959-DTLTRT-06_30_2022-GO95BLTC-1^668005/00 21/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
646164629-83959-DTLTRT-06_30_2022-GO95HV-1^668005/00 21/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2027-06-30 | 3
646164629-83959-DTLTRT-06_30_2022-GO95MLD-1^668005/00 21/032 | OTHER | CA-NON-TIER | Transmission | 2022-06-30 | 2025-06-30 | 2
762441152-68391-DETAIL-02_13_2023-GO95HV-1^06247002.0118701 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
297002231-15979-DETAIL-02_13_2023-GO95MLD-1^06247002.0125500 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
297002231-15979-DETAIL-02_13_2023-GRDRODHI-1^06247002.0125500 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
833541936-61302-DETAIL-02_13_2023-GO95MLD-1^06247002.0134401 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
597354686-23001-DETAIL-02_13_2023-GO95HV-1^06247002.0134601 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
597354686-23001-DETAIL-02_13_2023-GO95MLD-1^06247002.0134601 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
559734276-54651-DETAIL-02_15_2023-GO95HV-1^06247002.0142900 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
852437684-35062-DETAIL-02_15_2023-GO95HV-1^06247002.0144301 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
604335794-68211-DETAIL-02_15_2023-CLRTOUCH-1^06247002.0144500 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
150056226-45790-DETAIL-02_15_2023-GO95HV-1^06247002.0144501 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
201642826-59440-DETAIL-02_15_2023-GO95MLD-1^06247002.0144700 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
44062536-81540-DETAIL-02_15_2023-GO95HV-1^06247002.0144800 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
989995904-32433-DETAIL-02_16_2023-GO95HV-1^06247002.0165601 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
649855824-52881-DETAIL-02_16_2023-GO95HV-1^06247002.0165800 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
787817203-18952-DETAIL-02_16_2023-GO95HV-1^06247002.0166000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
987134303-67123-DETAIL-02_16_2023-GO95MLD-1^06247002.0166001 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
668410813-48631-DETAIL-02_16_2023-GO95MLD-1^06247002.0166101 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
641528053-58461-DETAIL-02_20_2023-GUYNOINS-1^06247002.0207000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
273844573-24410-DETAIL-02_20_2023-GO95MLD-1^06247002.0207400 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
859384893-66779-DETAIL-02_20_2023-GO95MLD-1^06247002.0207500 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
957119713-143-DETAIL-02_14_2023-GO95HV-1^06247002.0214700 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
701743954-53779-DETAIL-02_16_2023-GO95MLD-1^06247002.0217900 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
123692104-63560-DETAIL-02_15_2023-CONDFRAY-1^06247002.0232600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
123692104-63560-DETAIL-02_15_2023-CONDFRAY-2^06247002.0232600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
123692104-63560-DETAIL-02_15_2023-CONDFRAY-3^06247002.0232600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
123692104-63560-DETAIL-02_15_2023-CONDFRAY-4^06247002.0232600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
123692104-63560-DETAIL-02_15_2023-GO95MLD-1^06247002.0232600 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
524959446-32311-DETAIL-02_15_2023-GO95MLD-1^06247002.0232700 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
927633057-63057-DETAIL-02_15_2023-GO95CL10-1^06247002.0232702 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
927633057-63057-DETAIL-02_15_2023-GO95MLD-1^06247002.0232702 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
346460464-87290-DETAIL-02_15_2023-SVCROAD-1^06247002.0233500 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
462662284-66721-DETAIL-02_15_2023-GO95HV-1^06247002.0235601 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
717784094-99871-DETAIL-02_15_2023-GO95TCH-1^06247002.0235703 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
649524694-49681-DETAIL-02_15_2023-GO95MLD-1^06247002.0235704 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
463303796-88031-DETAIL-02_15_2023-GO95MLD-1^06247002.0235801 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
657093144-29001-DETAIL-02_15_2023-GO95HV-1^06247002.0236500 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
117889248-67370-DETAIL-01_23_2023-SVCROAD-1^06240004.0080207 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
121056589-65530-DETAIL-01_24_2023-GO95HV-1^06240004.0080302 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2028-01-24 | 3
121056589-65530-DETAIL-01_24_2023-GO95MLD-1^06240004.0080302 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
450539936-10840-DETAIL-01_19_2023-GO95MLD-1^06240004.0080440 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
450539936-10840-DETAIL-01_19_2023-RISECLMB-1^06240004.0080440 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
627531698-93920-DETAIL-01_19_2023-GO95MLD-1^06240004.0080500 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
627531698-93920-DETAIL-01_19_2023-GO95STUB-1^06240004.0080500 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
751728588-76130-DETAIL-01_24_2023-GO95MLD-1^06240004.0080700 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
749522669-54230-DETAIL-01_19_2023-GO95HV-1^06240004.0080802 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2028-01-19 | 3
305874438-60130-DETAIL-01_19_2023-GO95MLD-1^06240004.0080900 | OTHER | CA-TIER-2 | Distribution | 2023-01-19 | 2026-01-19 | 2
286190518-90370-DETAIL-01_23_2023-GO95MLD-1^06240004.0081200 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
286190518-90370-DETAIL-01_23_2023-POLESTEP-1^06240004.0081200 | POLE | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
287804836-48720-DETAIL-02_20_2023-GO95MLD-1^06247002.0297402 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
287804836-48720-DETAIL-02_20_2023-GUYHINS-1^06247002.0297402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
381703226-20730-DETAIL-02_20_2023-CONDFRAY-1^06247002.0297502 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
381703226-20730-DETAIL-02_20_2023-GO95HV-1^06247002.0297502 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
185916916-45620-DETAIL-02_20_2023-GO95HV-1^06247002.0297600 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
736569028-78721-DETAIL-02_20_2023-GO95HV-1^06247002.0297701 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
581447188-72281-DETAIL-02_20_2023-GO95MLD-1^06247002.0297900 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
450845986-35111-DETAIL-02_21_2023-GO95HV-1^06247002.0299700 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
994798358-58143-DETAIL-02_20_2023-GO95MLD-1^06247002.0325700 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
330935748-39770-DETAIL-02_20_2023-ABNDEQPM-1^06247002.0326800 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
884040023-57299-DTLSB-02_07_2023-SVCROAD-1^06248001.0154303 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
877692883-37299-DTLSB-02_07_2023-GO95MLD-1^06248001.0154304 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
304643713-76650-DTLSB-02_08_2023-GO95MLD-1^06248001.0155203 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
121716393-25360-DTLSB-02_07_2023-GO95HV-1^06248001.0155300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
541128684-96679-DTLSB-02_07_2023-GO95HV-1^06248001.0156101 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
250282783-56199-DTLSB-02_07_2023-GO95MLD-1^06248001.0156201 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
663576673-41289-DTLSB-02_08_2023-GO95MLD-1^06248001.0157000 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
820196514-58762-DTLSB-02_07_2023-ABNDEQPM-1^06248001.0157201 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
820196514-58762-DTLSB-02_07_2023-GO95MLD-1^06248001.0157201 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
437693294-89790-DTLSB-02_07_2023-GO95HV-1^06248001.0157202 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
504079304-981-DTLSB-02_07_2023-GO95HV-1^06248001.0157203 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
793161404-66679-DTLSB-02_07_2023-GO95BLTC-1^06248001.0158100 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
793161404-66679-DTLSB-02_07_2023-GO95TCH-1^06248001.0158100 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2026-02-07 | 2
314744494-51060-DTLSB-02_07_2023-GO95HV-1^06248001.0158102 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
437364738-18269-AUDIT-08_02_2022-GUYNOINS-1^668005/00 4/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-02 | 2025-08-02 | 2
437364738-18269-AUDIT-08_02_2022-GUYSLACK-1^668005/00 4/035 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-02 | 2025-08-02 | 2
417526801-67271-DETAIL-07_06_2022-GO95HV-1^668005/00 4/038 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
417526801-67271-AUDIT-08_02_2022-SVCROAD-1^668005/00 4/038 | OTHER | CA-NON-TIER | Transmission | 2022-08-02 | 2025-08-02 | 2
417526801-67271-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 4/038 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
928015420-14069-DTLTRT-07_15_2022-GO95HV-1^668005/00 4/047 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
56437859-13269-DTLTRT-07_05_2022-GO95HV-1^668005/00 5/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
895162648-48269-DTLTRT-07_05_2022-GO95HV-1^668005/00 5/035 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
408785888-87369-DTLTRT-07_06_2022-GO95HV-1^668005/00 5/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
36089801-20911-ADMIN-07_04_2022-POLEDERP-1^668005/00 5/038 | POLE | CA-NON-TIER | Transmission | 2022-07-04 | 2025-07-04 | 2
937811298-11992-DTLSB-02_08_2023-GO95MLD-1^06248001.0227902 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
152483734-59099-DTLSB-02_09_2023-GO95MLD-1^06248001.0228501 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
469130392-70392-DTLSB-02_14_2023-GO95MLD-1^06248001.0228503 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
248467292-8292-DTLSB-02_09_2023-GUYNOINS-1^06248001.0228600 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
133284898-83970-DTLSB-02_08_2023-GRDRODHI-1^06248001.0228900 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
44337409-4809-DTLSB-02_13_2023-GO95HV-1^06248001.0229140 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
44337409-4809-DTLSB-02_13_2023-GO95MLD-1^06248001.0229140 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
784329078-42942-DTLSB-02_09_2023-GO95HV-1^06248001.0229401 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
559505688-43451-DTLSB-02_09_2023-GO95HV-1^06248001.0229501 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
943291898-58803-DTLSB-02_14_2023-GO95MLD-1^06248001.0229600 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
577332808-31681-DTLSB-02_08_2023-GO95MLD-1^06248001.0229701 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
77851893-4700-DTLSB-02_06_2023-GO95MLD-1^06248001.0243100 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
543753983-79279-DTLSB-02_02_2023-GO95MLD-1^06248001.0250000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
707755803-50499-DTLSB-02_02_2023-GO95MLD-1^06248001.0254001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
958107903-95379-DTLSB-01_30_2023-GO95MLD-1^06248001.0255004 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
25683014-45679-DTLSB-01_30_2023-GO95MLD-1^06248001.0256000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
533223013-74879-AUDIT-02_07_2023-GO95HV-1^06248001.0256002 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
657226673-44101-DTLSB-02_06_2023-GO95HV-1^06248001.0256900 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
504118524-95789-DTLSB-01_30_2023-GO95HV-1^06248001.0257000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
772926554-71512-DTLSB-02_06_2023-GO95HV-1^06248001.0257001 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
804803754-80702-DTLSB-01_30_2023-GO95HV-1^06248001.0257002 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
548697413-81479-DTLSB-01_30_2023-GO95MLD-1^06248001.0257004 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
564946764-21061-DTLSB-02_06_2023-GO95MLD-1^06248001.0257200 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
194217664-58730-DTLSB-02_06_2023-GO95HV-1^06248001.0257201 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
36089801-20911-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 5/038 | OTHER | CA-NON-TIER | Transmission | 2022-12-21 | 2025-12-21 | 2
101004320-64069-DETAIL-07_15_2022-GO95HV-1^668005/00 5/047 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
13599681-64469-DTLTRT-07_20_2022-GO95MLD-1^668005/00 5/054 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2025-07-20 | 2
824673794-29469-DTLTRT-07_20_2022-GO95HV-1^668005/00 5/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
257440269-83269-DTLTRT-07_05_2022-GO95HV-1^668005/00 6/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2027-07-05 | 3
257440269-83269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 6/034 | OTHER | CA-NON-TIER | Transmission | 2022-07-05 | 2025-07-05 | 2
829007598-8369-DETAIL-07_06_2022-GO95HV-1^668005/00 6/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
427584130-5069-DTLTRT-07_15_2022-GO95HV-1^668005/00 6/047 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
599146991-84469-AUDIT-08_29_2022-GO95HV-1^668005/00 6/054 | OTHER | CA-NON-TIER | Transmission | 2022-08-29 | 2027-08-29 | 3
895067204-59469-DTLTRT-07_20_2022-GO95HV-1^668005/00 6/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
846356618-15959-DTLTRT-07_06_2022-GO95HV-1^668005/00 7/036 | OTHER | CA-NON-TIER | Transmission | 2022-07-06 | 2027-07-06 | 3
109765628-39650-DETAIL-03_19_2024-GO95MLD-1^06245002.0021000 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
966369138-52663-DETAIL-03_19_2024-SVCNEUT-1^06245002.0022001 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
671978608-92341-DETAIL-03_19_2024-GRDRODHI-1^06245002.0023001 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
671978608-92341-DETAIL-03_19_2024-SVCENTCO-1^06245002.0023001 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
656572008-93801-DETAIL-03_19_2024-GO95MLD-1^06245002.0026000 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
772480098-50812-DETAIL-03_19_2024-GO95MLD-1^06245002.0026001 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
549506588-91541-DETAIL-03_19_2024-GO95MLD-1^06245002.0028000 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
408573888-1779-DETAIL-03_19_2024-GO95CL10-1^06245002.0029001 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
408573888-1779-DETAIL-03_19_2024-GO95MLD-1^06245002.0029001 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
398844888-55150-DETAIL-03_18_2024-XARMSPCR-1^06245002.0033900 | CROSSARM | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
450330288-66611-ADMIN-07_31_2023-POLEDMRS-1^06245002.0033901 | POLE | CA-NON-TIER | Distribution | 2023-07-31 | 2026-07-31 | 2
664811359-33779-DETAIL-03_18_2024-GO95TCH-1^06245002.0035000 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
664811359-33779-DETAIL-03_18_2024-SVCENTCO-1^06245002.0035000 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
82126539-21610-DETAIL-03_18_2024-GO95HV-1^06245002.0035001 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
815772678-5142-DETAIL-03_18_2024-GO95MLD-1^06245002.0035900 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
567060168-5561-DETAIL-03_18_2024-GO95HV-1^06245002.0036900 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
906562258-79952-DETAIL-03_18_2024-GO95MLD-1^06245002.0037901 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
906562258-79952-AUDIT-04_02_2024-SVCROAD-1^06245002.0037901 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
680441279-4361-DETAIL-03_18_2024-CUTOUTAR-3^06245002.0038300 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
99465879-86440-DETAIL-03_19_2024-GO95MLD-1^06245002.0039000 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
240613489-20380-DETAIL-03_19_2024-GO95MLD-1^06245002.0039001 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
240613489-20380-DETAIL-03_19_2024-GUYHINS-1^06245002.0039001 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
999199218-89889-DETAIL-03_18_2024-GO95HV-1^06245002.0039701 | OTHER | CA-NON-TIER | Distribution | 2024-03-18 | 2029-03-18 | 3
994929249-75343-DETAIL-03_18_2024-XARMSPCR-1^06245002.0040901 | CROSSARM | CA-NON-TIER | Distribution | 2024-03-18 | 2027-03-18 | 2
419662504-82770-DTLSB-01_30_2023-SVCROAD-1^06248001.0259100 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
330047104-32470-DTLSB-01_30_2023-CONDCOIL-1^06248001.0259101 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
937593714-77714-DTLSB-01_30_2023-GO95TCH-1^06248001.0259201 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
53205924-22750-DTLSB-02_06_2023-GO95HV-1^06248001.0259203 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
242872093-45780-DTLSB-01_30_2023-GO95MLD-1^06248001.0259400 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
110715124-60350-DTLSB-01_30_2023-GO95HV-1^06248001.0259501 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
552799451-79941-DTLSB-02_06_2023-GO95MLD-1^06248001.0259600 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
921044660-6660-DTLSB-02_08_2023-GO95HV-1^06248001.0260001 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
320304394-79160-DTLSB-02_09_2023-GO95MLD-1^06248001.0260900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
876752553-5779-DTLSB-02_06_2023-GO95MLD-1^06248001.0262000 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
876752553-5779-DTLSB-02_06_2023-GO95TCH-1^06248001.0262000 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
73519679-79500-DETAIL-04_11_2024-GO95MLD-1^06245002.0101102 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
535947369-19979-DETAIL-04_11_2024-GO95HV-1^06245002.0102100 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
535947369-19979-DETAIL-04_11_2024-GO95MLD-1^06245002.0102100 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
328708159-39570-DETAIL-04_11_2024-GO95MLD-1^06245002.0102101 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
350242259-8990-DETAIL-04_11_2024-GO95HV-1^06245002.0102102 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
350242259-8990-DETAIL-04_11_2024-GO95MLD-1^06245002.0102102 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
390965729-20640-DETAIL-04_11_2024-GO95HV-1^06245002.0102200 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
390965729-20640-DETAIL-04_11_2024-GO95MLD-1^06245002.0102200 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
441561129-85990-ADMIN-04_11_2024-CUTOUTAR-1^06245002.0102201 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
151529509-87590-DETAIL-04_11_2024-GO95HV-1^06245002.0102301 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
151529509-87590-DETAIL-04_11_2024-GO95MLD-1^06245002.0102301 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
234283449-67870-DETAIL-04_11_2024-GO95MLD-1^06245002.0102302 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
484049049-89951-DETAIL-04_11_2024-GUYNOINS-1^06245002.0102303 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
357272109-64300-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0103300 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
402916699-74850-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0104300 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
112090099-17050-DETAIL-04_11_2024-GO95HV-1^06245002.0104301 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
770043789-33512-DETAIL-04_11_2024-GO95HV-1^06245002.0105300 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
770043789-33512-DETAIL-04_11_2024-GO95MLD-1^06245002.0105300 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
568831989-42271-DETAIL-04_11_2024-GO95MLD-1^06245002.0105301 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
518448879-61701-DETAIL-04_11_2024-GO95HV-1^06245002.0105400 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
485683589-83151-DETAIL-04_11_2024-GO95MLD-1^06245002.0105401 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
151896809-26790-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0106501 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
151896809-26790-DETAIL-04_11_2024-INSULDMG-1^06245002.0106501 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
544313963-17879-DTLSB-02_02_2023-GO95HV-1^06248001.0266000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
621105063-76879-DTLSB-02_02_2023-GO95HV-1^06248001.0267000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
591750684-39301-DTLSB-02_02_2023-GO95HV-1^06248001.0267002 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
923432973-58779-DTLSB-02_02_2023-GO95MLD-1^06248001.0268000 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
606261473-96279-DTLSB-02_02_2023-GO95MLD-1^06248001.0268001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
75837083-17079-DTLSB-02_02_2023-ABNDEQPM-1^06248001.0269001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
75837083-17079-DTLSB-02_02_2023-GO95MLD-1^06248001.0269001 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
300680503-11240-DTLSB-02_13_2023-GO95MLD-1^06248001.0272901 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
881681581-3562-DTLSB-02_14_2023-GO95MLD-1^06248001.0275001 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
605334373-45121-DTLSB-02_20_2023-GO95MLD-1^06248001.0275002 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
777735391-19879-DTLSB-02_13_2023-GO95HV-1^06248001.0276000 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
969555653-42773-DTLSB-02_13_2023-GO95TCH-1^06248001.0276400 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
39947428-85830-DETAIL-04_10_2024-GO95MLD-1^06245002.0114200 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
202456628-96940-DETAIL-04_10_2024-GO95MLD-1^06245002.0114201 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
3520728-17509-DETAIL-04_10_2024-GO95MLD-1^06245002.0115200 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
355792818-2779-DETAIL-04_10_2024-CUTOUTAR-1^06245002.0119201 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-04-10 | 2027-04-10 | 2
233880618-5570-DETAIL-03_20_2024-GO95MLD-1^06245002.0120200 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
832904508-92702-DETAIL-03_20_2024-GO95MLD-1^06245002.0121200 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
102391108-75040-DETAIL-03_20_2024-GO95HV-1^06245002.0121201 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
838615597-57722-DETAIL-03_20_2024-GO95MLD-1^06245002.0122200 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
799021797-63182-DETAIL-03_20_2024-GO95HV-1^06245002.0123200 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
401049467-74650-DETAIL-03_19_2024-GO95CL10-1^06245002.0123800 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
401049467-74650-DETAIL-03_19_2024-GO95MLD-1^06245002.0123800 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
57526197-49460-DETAIL-03_20_2024-GO95HV-1^06245002.0124202 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
57526197-49460-DETAIL-03_20_2024-GO95MLD-1^06245002.0124202 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
62359968-80889-ADMIN-03_20_2024-GO95STUB-1^06245002.0124301 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2027-03-20 | 2
899329168-79922-DETAIL-03_20_2024-GO95HV-1^06245002.0124400 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
939014868-76192-DETAIL-03_19_2024-GO95MLD-1^06245002.0124501 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
224364558-91160-AUDIT-04_02_2024-GO95MLD-1^06245002.0124701 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
957416748-72243-DETAIL-03_19_2024-GO95MLD-1^06245002.0124900 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
868783588-87122-DETAIL-03_20_2024-GUYHINS-1^06245002.0127700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-20 | 2027-03-20 | 2
704715988-80631-DETAIL-03_20_2024-GRDRODHI-1^06245002.0127801 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2027-03-20 | 2
704715988-80631-AUDIT-04_15_2024-GO95BLTC-1^06245002.0127801 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
710607098-97051-DETAIL-03_20_2024-CONDFRAY-1^06245002.0128700 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-20 | 2027-03-20 | 2
744631479-81889-DTLSB-05_07_2024-GO95MLD-1^06245002.0134900 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
222224679-32889-DTLSB-05_07_2024-GO95MLD-1^06245002.0135800 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
231441074-52260-DETAIL-01_12_2022-GO95MLD-1^06239004.0255546 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
231441074-52260-DETAIL-01_12_2022-SVCENTCO-1^06239004.0255546 | OTHER | CA-TIER-2 | Distribution | 2022-01-12 | 2025-01-12 | 2
777668416-97480-ADMIN-09_11_2024-GO95CL10-1^06239004.0256546 | OTHER | CA-TIER-2 | Distribution | 2024-09-11 | 2027-09-11 | 2
676279125-83770-DETAIL-01_17_2022-GO95MLD-1^06239004.0256602 | OTHER | CA-TIER-2 | Distribution | 2022-01-17 | 2025-01-17 | 2
52499796-8080-DETAIL-01_24_2022-GO95MLD-1^06239004.0256647 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
993285001-5501-DETAIL-01_25_2022-SVCROOF-1^06239004.0257040 | OTHER | CA-TIER-2 | Distribution | 2022-01-25 | 2025-01-25 | 2
121338399-48790-DETAIL-01_24_2022-GO95MLD-1^06239004.0257101 | OTHER | CA-TIER-2 | Distribution | 2022-01-24 | 2025-01-24 | 2
976084861-16893-DETAIL-04_11_2024-GO95HV-1^06245002.0143500 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
452358351-67211-DETAIL-04_11_2024-GO95MLD-1^06245002.0143501 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
374697299-72720-DETAIL-04_11_2024-GO95MLD-1^06245002.0143700 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
587759789-9591-DETAIL-04_11_2024-GO95MLD-1^06245002.0143800 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
793837091-18472-DETAIL-04_11_2024-GO95MLD-1^06245002.0144100 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
793837091-18472-DETAIL-04_11_2024-INSULDMG-1^06245002.0144100 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
287509681-720-DETAIL-04_11_2024-GO95MLD-1^06245002.0144101 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
50100411-73450-DETAIL-04_11_2024-GO95MLD-1^06245002.0145100 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
50100411-73450-DETAIL-04_11_2024-GRDRODHI-1^06245002.0145100 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
196351111-18730-DETAIL-04_11_2024-GO95MLD-1^06245002.0145101 | OTHER | CA-NON-TIER | Distribution | 2024-04-11 | 2029-04-11 | 3
143124519-2980-DTLSB-05_07_2024-CONDFRAY-1^06245002.0248700 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-05-07 | 2027-05-07 | 2
143124519-2980-DTLSB-05_07_2024-GO95MLD-1^06245002.0248700 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
264629019-37400-DTLSB-05_07_2024-GO95MLD-1^06245002.0248800 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
442817059-19901-DTLSB-05_07_2024-GO95MLD-1^06245002.0249601 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
639708929-8351-DTLSB-05_07_2024-GO95MLD-1^06245002.0249701 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
377993204-57579-DETAIL-08_12_2020-GO95TCH-1^06246001.0130900 | OTHER | CA-NON-TIER | Distribution | 2020-08-12 | 2023-08-12 | 2
616371134-11989-DETAIL-07_15_2020-GO95HV-1^06246001.0172600 | OTHER | CA-NON-TIER | Distribution | 2020-07-15 | 2025-07-15 | 3
381882136-68730-ADMIN-07_14_2020-ENCHRW-1^06246001.0176403 | OTHER | CA-NON-TIER | Distribution | 2020-07-14 | 2023-07-14 | 2
596166660-80001-ADMIN-08_13_2020-GUYSLACK-1^06246001.0301900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2020-08-13 | 2023-08-13 | 2
147346581-96989-ADMIN-04_11_2024-XARMSPCR-1^06246001.0314401 | CROSSARM | CA-NON-TIER | Distribution | 2024-04-11 | 2027-04-11 | 2
912419378-75082-ADMIN-01_25_2022-POLETOP-1^06246001.0334601 | POLE | CA-NON-TIER | Distribution | 2022-01-25 | 2025-01-25 | 2
82307245-36710-DTLSB-05_08_2024-GO95MLD-1^06244001.0107600 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
368713435-36910-DTLSB-05_08_2024-GO95HV-1^06244001.0107700 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
296840695-57130-DTLSB-05_09_2024-GO95MLD-1^06244001.0107800 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
289859095-3030-DTLSB-05_13_2024-GO95MLD-1^06244001.0108101 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
198652875-59830-DTLSB-05_08_2024-GO95HV-1^06244001.0108300 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
664405645-81121-DTLSB-05_08_2024-GO95MLD-1^06244001.0108400 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
400814145-42550-DTLSB-05_08_2024-GO95HV-1^06244001.0108500 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
400814145-42550-DTLSB-05_08_2024-GO95MLD-1^06244001.0108500 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
960178805-5053-DTLSB-05_09_2024-GO95MLD-1^06244001.0108901 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
384495985-23330-DTLSB-05_13_2024-GO95MLD-1^06244001.0109200 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
34897685-6230-DTLSB-05_13_2024-GO95MLD-1^06244001.0109300 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
950799784-28923-DTLSB-05_09_2024-GO95HV-1^06244001.0110900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
950799784-28923-DTLSB-05_09_2024-GO95MLD-1^06244001.0110900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
195621294-7330-DTLSB-05_09_2024-GO95MLD-1^06244001.0110901 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
840542594-12622-DTLSB-05_09_2024-GO95MLD-1^06244001.0111900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
541388094-21531-DTLSB-05_09_2024-GO95MLD-1^06244001.0112900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
810167404-36032-DTLSB-05_09_2024-GO95MLD-1^06244001.0112901 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
214853204-3450-DTLSB-05_09_2024-GO95MLD-1^06244001.0113900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
333368014-53080-DTLSB-05_09_2024-GO95MLD-1^06244001.0114900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
807201144-26012-DTLSB-05_09_2024-GO95MLD-1^06244001.0118900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
69426244-99890-DTLSB-05_09_2024-GO95HV-1^06244001.0119900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
69426244-99890-DTLSB-05_09_2024-GO95MLD-1^06244001.0119900 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
70402048-93779-DTLSB-05_13_2024-SVCENTCO-1^06244001.0153100 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2027-05-13 | 2
338027386-38386-DTLSB-05_13_2024-GO95MLD-1^06244001.0154203 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
357487201-56500-DTLSB-02_13_2023-GO95MLD-1^06248001.0279000 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
77191680-26880-DTLSB-02_09_2023-GO95MLD-1^06248001.0279220 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
321626152-47460-DTLSB-02_13_2023-GO95MLD-1^06248001.0279301 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
605546004-51221-DTLSB-02_09_2023-GO95HV-1^06248001.0279601 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
268715604-71410-DTLSB-02_09_2023-GO95HV-1^06248001.0279602 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
269879964-30010-DTLSB-02_09_2023-ABNDEQPM-1^06248001.0279742 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
269879964-30010-DTLSB-02_09_2023-ANCHIDLE-1^06248001.0279742 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
269879964-30010-DTLSB-02_09_2023-GO95HV-1^06248001.0279742 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
175227004-9004-DTLSB-02_13_2023-GO95MLD-1^06248001.0279743 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
58105331-56241-AUDIT-02_22_2023-GO95HV-1^06248001.0279921 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
339822634-64080-DTLSB-02_20_2023-GO95MLD-1^06248001.0284601 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
897897801-34199-DTLSB-02_20_2023-GO95HV-1^06248001.0286600 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
269069608-20610-DTLSB-05_09_2024-GUYNOINS-1^06244001.0215402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-09 | 2027-05-09 | 2
269069608-20610-DTLSB-05_09_2024-GUYNOINS-2^06244001.0215402 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-05-09 | 2027-05-09 | 2
559366068-68351-DTLSB-05_13_2024-GO95HV-1^06244001.0215403 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
365024048-38410-DTLSB-05_09_2024-GO95MLD-1^06244001.0217403 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
381874628-38730-DTLSB-05_14_2024-GO95HV-1^06244001.0218401 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
381874628-38730-DTLSB-05_14_2024-GO95MLD-1^06244001.0218401 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
71799918-95400-DTLSB-05_14_2024-GO95MLD-1^06244001.0218403 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2027-05-14 | 2
868125718-66722-DTLSB-05_14_2024-GO95MLD-1^06244001.0220400 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2027-05-14 | 2
940075708-15692-DTLSB-05_14_2024-GO95MLD-1^06244001.0221400 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2027-05-14 | 2
866414498-53212-DTLSB-05_09_2024-GO95MLD-1^06244001.0223400 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2027-05-09 | 2
927089198-25242-DTLSB-05_09_2024-GO95MLD-1^06244001.0224501 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2027-05-09 | 2
478034988-33141-DTLSB-05_13_2024-GO95MLD-1^06244001.0225600 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
958583516-76843-DTLSB-05_14_2024-GO95MLD-1^06244001.0280000 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
35446816-75530-DTLSB-05_14_2024-GO95MLD-1^06244001.0280001 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
74550006-81300-DTLSB-05_14_2024-GO95MLD-1^06244001.0293900 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
12331306-52169-DTLSB-05_14_2024-GO95MLD-1^06244001.0293901 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
106922616-90040-DTLSB-05_14_2024-GO95MLD-1^06244001.0294700 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
509059616-65881-DTLSB-05_14_2024-GO95MLD-1^06244001.0294800 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
811120016-80332-DTLSB-05_14_2024-GO95MLD-1^06244001.0294801 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
382654526-67230-DTLSB-05_14_2024-GO95MLD-1^06244001.0295700 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
948895446-50723-DTLSB-05_14_2024-GO95MLD-1^06244001.0298200 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
464418946-91931-DTLSB-05_14_2024-GO95MLD-1^06244001.0298201 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
496393146-35171-DTLSB-05_14_2024-GO95MLD-1^06244001.0298300 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
659283456-90501-DTLSB-05_14_2024-GO95MLD-1^06244001.0299100 | OTHER | CA-NON-TIER | Distribution | 2024-05-14 | 2029-05-14 | 3
754495348-66461-DTLSB-01_26_2023-GO95MLD-1^06247001.0016900 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
920187338-91312-DTLSB-01_26_2023-GUYSLACK-1^06247001.0017905 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
749830708-44351-DTLSB-02_06_2023-GO95MLD-1^06247001.0019201 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
749830708-44351-DTLSB-02_06_2023-GO95TCH-1^06247001.0019201 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
809697678-69822-DETAIL-02_05_2018-ENCHRW-1^06247001.0019902 | OTHER | CA-NON-TIER | Distribution | 2018-02-05 | 2023-01-05 | 2
583151688-34191-DETAIL-02_23_2023-GO95HV-1^06247001.0089300 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
331526308-92079-DETAIL-02_23_2023-GO95CL10-1^06247001.0089500 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
331526308-92079-DETAIL-02_23_2023-GO95MLD-1^06247001.0089500 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
873757416-37389-DTLSB-02_02_2023-GO95MLD-1^06247001.0120501 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
76798206-11100-DTLSB-02_02_2023-GO95MLD-1^06247001.0121600 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
174603221-879-DTLSB-02_09_2023-GO95MLD-1^06247001.0129000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
480939321-60421-DTLSB-02_09_2023-GO95MLD-1^06247001.0129002 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
726598258-89291-DTLSB-05_16_2024-GO95HV-1^06244002.0201400 | OTHER | CA-NON-TIER | Distribution | 2024-05-16 | 2029-05-16 | 3
119327838-40160-DTLSB-05_16_2024-GO95HV-1^06244002.0204500 | OTHER | CA-NON-TIER | Distribution | 2024-05-16 | 2029-05-16 | 3
752454018-27261-DTLSB-05_16_2024-GO95HV-1^06244002.0208500 | OTHER | CA-NON-TIER | Distribution | 2024-05-16 | 2029-05-16 | 3
397831568-60850-DTLSB-05_15_2024-GO95HV-1^06244002.0215700 | OTHER | CA-NON-TIER | Distribution | 2024-05-15 | 2029-05-15 | 3
828198558-62392-DTLSB-05_15_2024-GO95HV-1^06244002.0217701 | OTHER | CA-NON-TIER | Distribution | 2024-05-15 | 2029-05-15 | 3
455218428-73711-DTLSB-05_15_2024-GO95HV-1^06244002.0226600 | OTHER | CA-NON-TIER | Distribution | 2024-05-15 | 2029-05-15 | 3
591952157-82157-DTLSB-05_21_2024-GO95HV-1^06244002.0232800 | OTHER | CA-NON-TIER | Distribution | 2024-05-21 | 2029-05-21 | 3
721535088-47781-DTLSB-05_15_2024-GO95MLD-1^06244002.0234500 | OTHER | CA-NON-TIER | Distribution | 2024-05-15 | 2029-05-15 | 3
767368828-89602-DTLSB-05_21_2024-GO95HV-1^06244002.0243301 | OTHER | CA-NON-TIER | Distribution | 2024-05-21 | 2029-05-21 | 3
911681599-4182-DTLSB-05_20_2024-GO95HV-1^06244003.0227000 | OTHER | CA-NON-TIER | Distribution | 2024-05-20 | 2029-05-20 | 3
702983609-90521-DTLSB-05_16_2024-GO95HV-1^06244003.0247000 | OTHER | CA-NON-TIER | Distribution | 2024-05-16 | 2029-05-16 | 3
935309799-95482-DTLSB-05_16_2024-GO95HV-1^06244003.0249200 | OTHER | CA-NON-TIER | Distribution | 2024-05-16 | 2029-05-16 | 3
955714319-70343-DTLSB-05_20_2024-GO95HV-1^06244003.0270800 | OTHER | CA-NON-TIER | Distribution | 2024-05-20 | 2029-05-20 | 3
802364829-61092-DTLSB-05_28_2024-GO95HV-1^06244003.0284601 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
941501509-49003-DTLSB-05_28_2024-GO95BLTC-1^06244003.0285600 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
941501509-49003-DTLSB-05_28_2024-GO95MLD-1^06244003.0285600 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
814550509-25442-DTLSB-05_28_2024-GO95MLD-1^06244003.0285601 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
364771469-84310-DTLSB-05_20_2024-GO95HV-1^06244003.0287600 | OTHER | CA-NON-TIER | Distribution | 2024-05-20 | 2029-05-20 | 3
542392959-5331-DTLSB-05_20_2024-GO95BLTC-1^06244003.0287700 | OTHER | CA-NON-TIER | Distribution | 2024-05-20 | 2029-05-20 | 3
791564673-33262-DETAIL-04_24_2024-GO95MLD-1^06245001.0017500 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
791564673-33262-DETAIL-04_24_2024-GRDRODHI-1^06245001.0017500 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
793467963-19972-DETAIL-04_24_2024-GO95MLD-1^06245001.0017501 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
793467963-19972-DETAIL-04_24_2024-GRDRODHI-1^06245001.0017501 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
812894973-77142-DETAIL-04_24_2024-GO95MLD-1^06245001.0018400 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
124162859-17760-DETAIL-02_23_2023-GO95HV-1^06247001.0179700 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
646248769-45061-DETAIL-02_23_2023-GO95HV-1^06247001.0179900 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
733717019-95179-DETAIL-02_22_2023-GO95HV-1^06247001.0194000 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
530976289-66521-DETAIL-02_23_2023-GO95HV-1^06247001.0209200 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
696919919-60101-DETAIL-02_23_2023-GO95HV-1^06247001.0209500 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
605354029-6121-DETAIL-09_11_2020-CONDFRAY-1^06247001.0239501 | CONDUCTOR | CA-NON-TIER | Distribution | 2020-09-11 | 2023-09-11 | 2
269116449-3779-DETAIL-09_11_2020-CONDFRAY-1^06247001.0245402 | CONDUCTOR | CA-NON-TIER | Distribution | 2020-09-11 | 2023-09-11 | 2
896112821-63912-DETAIL-02_27_2023-GO95HV-1^06247001.0299000 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
853358831-68062-DETAIL-02_23_2023-GO95HV-1^06247001.0299400 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
30708261-300-ADMIN-07_17_2023-CONDFRAY-1^06247001.0349500 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-07-17 | 2026-07-17 | 2
681668681-74961-DETAIL-02_13_2023-CLRTOUCH-1^06247002.0018100 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-13 | 2026-02-13 | 2
848001814-38742-DETAIL-03_20_2024-GO95MLD-1^06245001.0051401 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
835575784-37812-DETAIL-03_20_2024-GO95MLD-1^06245001.0052101 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
913935694-83782-DETAIL-03_20_2024-GO95HV-1^06245001.0054100 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
844967944-56242-DETAIL-03_20_2024-GO95MLD-1^06245001.0063501 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
258437554-32290-DETAIL-03_20_2024-GO95HV-1^06245001.0070600 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
799327074-86782-DETAIL-03_20_2024-GO95MLD-1^06245001.0071600 | OTHER | CA-NON-TIER | Distribution | 2024-03-20 | 2029-03-20 | 3
531492854-27821-DTLSB-05_07_2024-GO95MLD-1^06245001.0190400 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
738911534-40521-DTLSB-05_07_2024-GO95MLD-1^06245001.0190502 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
118872924-99860-DTLSB-05_07_2024-GO95HV-1^06245001.0191300 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
118872924-99860-DTLSB-05_07_2024-GO95MLD-1^06245001.0191300 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
983626914-22513-DTLSB-05_07_2024-GO95MLD-1^06245001.0191301 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
576906184-26481-DTLSB-05_07_2024-GO95MLD-1^06245001.0191400 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
21951534-16750-DTLSB-05_07_2024-GO95MLD-1^06245001.0191501 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
135379154-49970-DTLSB-05_07_2024-GO95MLD-1^06245001.0192001 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
471443034-38441-DTLSB-05_07_2024-GO95MLD-1^06245001.0192100 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
821111934-34262-DTLSB-05_07_2024-GO95MLD-1^06245001.0192200 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
958980875-8543-DTLSB-05_07_2024-GO95MLD-1^06245001.0291201 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
248408075-99580-DTLSB-05_13_2024-GO95MLD-1^06245001.0292200 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
248408075-99580-DTLSB-05_13_2024-GO95MLD-2^06245001.0292200 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
810658605-93432-DTLSB-05_13_2024-GO95MLD-1^06245001.0294200 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
757110105-97571-DTLSB-05_13_2024-GO95MLD-1^06245001.0294300 | OTHER | CA-NON-TIER | Distribution | 2024-05-13 | 2029-05-13 | 3
712387715-18551-DTLSB-05_07_2024-GO95MLD-1^06245001.0295301 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
250627125-35880-DTLSB-05_07_2024-GO95MLD-1^06245001.0296300 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
760032325-66381-DTLSB-05_07_2024-GO95MLD-1^06245001.0297300 | OTHER | CA-NON-TIER | Distribution | 2024-05-07 | 2029-05-07 | 3
971142383-71209-DETAIL-01_17_2023-GO95HV-1^06148004.0220801 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
344302683-10209-DETAIL-01_17_2023-GO95MLD-1^06148004.0220900 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
344302683-10209-DETAIL-01_17_2023-GRDBROKE-1^06148004.0220900 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
182719803-41379-DETAIL-01_17_2023-GO95MLD-1^06148004.0220901 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
310282351-14450-DETAIL-01_18_2023-GO95MLD-1^06148004.0221001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
310282351-14450-DETAIL-01_18_2023-GO95MLD-2^06148004.0221001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
310282351-14450-DETAIL-01_18_2023-GO95TCH-1^06148004.0221001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
938754064-17609-DETAIL-01_18_2023-GO95HV-1^06148004.0221004 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
854546984-25089-DETAIL-01_18_2023-GO95MLD-1^06148004.0221200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
854546984-25089-DETAIL-01_18_2023-GO95MLD-2^06148004.0221200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
854546984-25089-DETAIL-01_18_2023-GO95TCH-1^06148004.0221200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
65211113-32209-DETAIL-01_17_2023-GO95MLD-1^06148004.0221700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
564330844-19179-DETAIL-01_17_2023-GO95MLD-1^06148004.0223500 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
564330844-19179-DETAIL-01_17_2023-GO95MLD-2^06148004.0223500 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
286029511-81979-DETAIL-01_17_2023-GO95MLD-1^06148004.0225001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
286029511-81979-DETAIL-01_17_2023-SVCROAD-1^06148004.0225001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-GO95MLD-1^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-GO95MLD-2^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-GO95TCH-1^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-GRDRODHI-1^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
1249911-18309-DETAIL-01_17_2023-SVCROAD-1^06148004.0227001 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
501618523-63209-DETAIL-01_17_2023-GO95HV-1^06148004.0227100 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
554945733-3679-DETAIL-01_17_2023-GO95MLD-1^06148004.0227101 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
554945733-3679-DETAIL-01_17_2023-GO95MLD-2^06148004.0227101 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
113402533-53309-DETAIL-01_17_2023-GUYSLACK-1^06148004.0227700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
750468333-93309-DETAIL-01_17_2023-GO95HV-1^06148004.0227800 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
880717653-93679-DETAIL-01_17_2023-COPLLEAN-1^06148004.0227801 | POLE | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
880717653-93679-DETAIL-01_17_2023-GO95MLD-1^06148004.0227801 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
880717653-93679-DETAIL-01_17_2023-GO95MLD-2^06148004.0227801 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
880717653-93679-DETAIL-01_17_2023-GO95TCH-1^06148004.0227801 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
960361113-96309-DETAIL-01_17_2023-GO95HV-1^06148004.0228700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
353184241-45499-DETAIL-01_17_2023-COPLLEAN-1^06148004.0229200 | POLE | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
415655503-47309-DETAIL-01_17_2023-GO95BLTC-1^06148004.0229700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
415655503-47309-DETAIL-01_17_2023-GO95MLD-1^06148004.0229700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
415655503-47309-DETAIL-01_17_2023-GO95MLD-2^06148004.0229700 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
618067151-17331-DTLSB-02_20_2023-GO95MLD-1^06248001.0287400 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
38579092-46830-DTLSB-02_16_2023-GO95MLD-1^06248001.0288000 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
276564771-72199-DTLSB-02_20_2023-GO95HV-1^06248001.0288400 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
771130981-40212-DTLSB-02_20_2023-GO95MLD-1^06248001.0288403 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2026-02-20 | 2
45292561-51979-DTLSB-02_20_2023-GO95HV-1^06248001.0289200 | OTHER | CA-NON-TIER | Distribution | 2023-02-20 | 2028-02-20 | 3
655462616-74616-DTLSB-02_16_2023-GO95MLD-1^06248001.0299002 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
268072153-39079-DTLSB-02_16_2023-GO95MLD-1^06248001.0299200 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
116472971-1189-DTLSB-02_16_2023-GO95HV-1^06248001.0299300 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
870541841-18679-DTLSB-02_16_2023-GO95TCH-1^06248001.0299600 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2026-02-16 | 2
419986666-27666-DTLSB-02_15_2023-GO95MLD-1^06248001.0305001 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2026-02-15 | 2
729970666-71666-DTLSB-02_15_2023-GO95HV-1^06248001.0307101 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
208374521-21050-DTLSB-02_15_2023-GO95MLD-1^06248001.0308200 | OTHER | CA-NON-TIER | Distribution | 2023-02-15 | 2028-02-15 | 3
274511410-70079-ADMIN-02_22_2023-POLEDERP-1^06148004.0354501 | POLE | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
469656106-52336-DETAIL-09_27_2021-SVCROOF-1^06148004.0355204 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
777955324-82143-DETAIL-09_27_2021-GO95MLD-1^06148004.0355415 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
42651956-18716-DETAIL-09_09_2021-SVCROAD-1^06148004.0356000 | OTHER | CA-NON-TIER | Distribution | 2021-09-09 | 2024-09-09 | 2
659910746-62206-DETAIL-09_28_2021-SVCWIND-1^06148004.0356006 | OTHER | CA-NON-TIER | Distribution | 2021-09-28 | 2024-09-28 | 2
343565206-21366-DETAIL-09_27_2021-GO95MLD-1^06148004.0356202 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
846960094-38686-DETAIL-09_27_2021-GO95CL10-1^06148004.0356209 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2026-09-27 | 3
780633844-20253-DETAIL-09_27_2021-SVCROAD-1^06148004.0356300 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
910279616-76786-DETAIL-09_27_2021-SVCROAD-1^06148004.0356301 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
910279616-76786-DETAIL-09_27_2021-SVCROAD-2^06148004.0356301 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
759834034-92743-DETAIL-09_27_2021-SVCWIND-1^06148004.0356307 | OTHER | CA-NON-TIER | Distribution | 2021-09-27 | 2024-09-27 | 2
792393905-2489-DETAIL-10_28_2021-ENCHRW-1^06148005.0146103 | OTHER | CA-NON-TIER | Distribution | 2021-10-28 | 2024-10-28 | 2
618646698-79589-DETAIL-10_28_2021-ENCHRW-1^06148005.0254700 | OTHER | CA-NON-TIER | Distribution | 2021-10-28 | 2024-10-28 | 2
104792999-6509-DETAIL-10_28_2021-ENCHRW-1^06148005.0255100 | OTHER | CA-NON-TIER | Distribution | 2021-10-28 | 2024-10-28 | 2
841359944-25622-DTLSB-05_08_2024-GO95MLD-1^06245001.0331901 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
841359944-25622-DTLSB-05_08_2024-GRDRODHI-1^06245001.0331901 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2027-05-08 | 2
514678714-39391-DTLSB-05_08_2024-GO95MLD-1^06245001.0332800 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
913056914-95782-DTLSB-05_08_2024-GO95MLD-1^06245001.0332801 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
293579924-58030-DTLSB-05_08_2024-GO95MLD-1^06245001.0333700 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
69129214-64190-DTLSB-05_08_2024-GO95MLD-1^06245001.0333701 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
69129214-64190-DTLSB-05_08_2024-GRDRODHI-1^06245001.0333701 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2027-05-08 | 2
449028924-72601-DTLSB-05_08_2024-GO95MLD-1^06245001.0334500 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
828150224-99292-DTLSB-05_08_2024-GO95MLD-1^06245001.0334600 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
386838534-54930-DTLSB-05_08_2024-GO95MLD-1^06245001.0335400 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
770101324-75512-DTLSB-05_08_2024-GO95MLD-1^06245001.0335500 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
145970734-81380-DTLSB-05_08_2024-GO95MLD-1^06245001.0336300 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
995248013-40643-DTLSB-05_22_2024-GO95MLD-1^06243001.0048700 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
303421003-25050-DTLSB-05_22_2024-GO95MLD-1^06243001.0048800 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
902118443-88942-DTLSB-05_22_2024-GO95HV-1^06243001.0102800 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
902118443-88942-DTLSB-05_22_2024-GO95MLD-1^06243001.0102800 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
47115443-88440-DTLSB-05_22_2024-GO95MLD-1^06243001.0102900 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
261697643-32800-DTLSB-05_22_2024-GO95HV-1^06243001.0102901 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
29855853-44500-DETAIL-05_22_2024-GO95HV-1^06243001.0103600 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
46390553-65940-DTLTRT-05_22_2024-GO95HV-1^06243001.0103700 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
46390553-65940-DTLTRT-05_22_2024-GO95MLD-1^06243001.0103700 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
391822453-72140-DTLSB-05_22_2024-GO95MLD-1^06243001.0103701 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
260684483-4500-DTLSB-05_22_2024-GO95MLD-1^06243001.0104400 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
687382463-67281-DTLSB-05_22_2024-RISEGRD-1^06243001.0104500 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2027-05-22 | 2
543030253-10731-DTLSB-05_22_2024-GO95HV-1^06243001.0104501 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
543030253-10731-DTLSB-05_22_2024-GO95MLD-1^06243001.0104501 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
157303483-39200-DTLSB-05_22_2024-GO95MLD-1^06243001.0105400 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
636244883-23351-DTLSB-05_22_2024-GO95MLD-1^06243001.0105401 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
585998983-23391-DTLSB-05_22_2024-GO95HV-1^06243001.0106400 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
585998983-23391-DTLSB-05_22_2024-GO95MLD-1^06243001.0106400 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
635120493-35251-DTLSB-05_22_2024-GO95MLD-1^06243001.0108300 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
188076003-28530-DETAIL-05_22_2024-GO95HV-1^06243001.0109300 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
951832592-39133-DTLSB-05_22_2024-GO95MLD-1^06243001.0110200 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
577533082-4781-DTLSB-05_22_2024-COPLLEAN-1^06243001.0110201 | POLE | CA-NON-TIER | Distribution | 2024-05-22 | 2027-05-22 | 2
577533082-4781-DTLSB-05_22_2024-GO95HV-1^06243001.0110201 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
577533082-4781-DTLSB-05_22_2024-GO95MLD-1^06243001.0110201 | OTHER | CA-NON-TIER | Distribution | 2024-05-22 | 2029-05-22 | 3
432147944-31880-DTLSB-05_08_2024-GO95MLD-1^06245001.0337200 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
641004834-66061-DTLSB-05_08_2024-GO95MLD-1^06245001.0337300 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
323214944-35570-DTLSB-05_08_2024-GO95MLD-1^06245001.0338100 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
929394144-37652-DTLSB-05_08_2024-GO95MLD-1^06245001.0338200 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
305128244-68150-DTLSB-05_08_2024-GO95HV-1^06245001.0339100 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
305128244-68150-DTLSB-05_08_2024-GO95MLD-1^06245001.0339100 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
126073373-43870-DTLSB-05_08_2024-GO95MLD-1^06245001.0340000 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
279280454-80920-DTLSB-05_08_2024-GO95MLD-1^06245001.0340001 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
580145378-1981-DETAIL-03_19_2024-INSULDMG-1^06245002.0012000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
799949168-38682-DETAIL-03_19_2024-GO95MLD-1^06245002.0013000 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
799949168-38682-DETAIL-03_19_2024-GRDRODHI-1^06245002.0013000 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2027-03-19 | 2
107450928-13240-DETAIL-03_19_2024-GO95HV-1^06245002.0014500 | OTHER | CA-NON-TIER | Distribution | 2024-03-19 | 2029-03-19 | 3
777276726-72479-DETAIL-01_24_2023-COPLLEAN-1^06148004.0182101 | POLE | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
777276726-72479-DETAIL-01_24_2023-GO95CL10-1^06148004.0182101 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
777276726-72479-DETAIL-01_24_2023-GO95MLD-1^06148004.0182101 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
889432605-38279-DETAIL-01_24_2023-GO95MLD-1^06148004.0182103 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
911087461-86879-DETAIL-01_24_2023-ABNDEQPM-1^06148004.0182200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
911087461-86879-DETAIL-01_24_2023-GO95MLD-1^06148004.0182200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
911087461-86879-DETAIL-01_24_2023-GO95TCH-1^06148004.0182200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
406432384-7989-DETAIL-01_24_2023-CONDFRAY-1^06148004.0182201 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
203607075-64889-DETAIL-01_10_2023-GO95HV-1^06148004.0182202 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2028-01-10 | 3
721781521-18379-DETAIL-01_24_2023-GO95HV-1^06148004.0182203 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
721781521-18379-DETAIL-01_24_2023-GO95MLD-1^06148004.0182203 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
699172542-96989-DETAIL-01_10_2023-GO95MLD-1^06148004.0182206 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
246769105-26889-DETAIL-01_10_2023-GO95MLD-1^06148004.0183201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
246769105-26889-DETAIL-01_10_2023-GO95TCH-1^06148004.0183201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
246769105-26889-DETAIL-01_10_2023-SVCSVC-1^06148004.0183201 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
246769105-26889-ADMIN-03_10_2023-GO95CL10-1^06148004.0183201 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
455444505-86079-ADMIN-01_10_2023-ENCHRW-1^06148004.0183203 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
455444505-86079-DETAIL-01_10_2023-GO95MLD-1^06148004.0183203 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
455444505-86079-ADMIN-03_10_2023-GO95CL10-1^06148004.0183203 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
70749994-76889-DETAIL-01_10_2023-GO95MLD-1^06148004.0183204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
521679055-47889-DETAIL-01_10_2023-EQUIPOIL-1^06148004.0184203 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
521679055-47889-AUDIT-02_06_2023-GO95MLD-1^06148004.0184203 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
215173555-81579-DETAIL-01_10_2023-GO95MLD-1^06148004.0184204 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
822696061-61879-DETAIL-01_10_2023-GO95MLD-1^06148004.0184205 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
963281853-45153-DTLSB-05_23_2024-GO95HV-1^06243001.0121000 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
963281853-45153-DTLSB-05_23_2024-GO95MLD-1^06243001.0121000 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
963281853-45153-DTLSB-05_23_2024-GRDRODHI-1^06243001.0121000 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2027-05-23 | 2
698998563-86511-DETAIL-05_23_2024-GO95HV-1^06243001.0122000 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
922394063-86222-DTLSB-05_23_2024-GO95MLD-1^06243001.0123000 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
786046193-5952-DTLSB-05_23_2024-GO95HV-1^06243001.0125001 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
786046193-5952-DTLSB-05_23_2024-GO95MLD-1^06243001.0125001 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2027-05-23 | 2
153900793-77890-DTLSB-05_28_2024-GO95MLD-1^06243001.0125003 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
726854203-1491-DTLSB-05_28_2024-GO95MLD-1^06243001.0125004 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
618460303-56079-DTLSB-05_28_2024-GO95HV-1^06243001.0125100 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
618460303-56079-DTLSB-05_28_2024-GO95MLD-1^06243001.0125100 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
586747503-23891-DTLSB-05_28_2024-GO95MLD-1^06243001.0125102 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
958070056-47779-DETAIL-01_24_2023-GO95MLD-1^06148004.0191900 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
426985984-88689-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
426985984-88689-DETAIL-01_23_2023-GO95MLD-1^06148004.0192002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
598769744-15189-DETAIL-01_23_2023-GO95MLD-1^06148004.0192003 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
598769744-15189-DETAIL-01_23_2023-GO95TCH-1^06148004.0192003 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
598769744-15189-DETAIL-01_23_2023-SVCENTCO-1^06148004.0192003 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
321533495-93189-DETAIL-01_23_2023-GO95TCH-1^06148004.0192100 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
589087435-48779-DETAIL-01_23_2023-GO95MLD-1^06148004.0192101 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
398308494-34189-DETAIL-01_23_2023-GO95HV-1^06148004.0192102 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
690849516-53379-DETAIL-01_23_2023-GO95MLD-1^06148004.0192104 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
690849516-53379-DETAIL-01_23_2023-SVCROAD-1^06148004.0192104 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
307092451-81189-DETAIL-01_23_2023-GO95CL10-1^06148004.0192201 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
307092451-81189-DETAIL-01_23_2023-GO95MLD-1^06148004.0192201 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
229582911-30789-DETAIL-01_23_2023-GO95HV-1^06148004.0192300 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
229582911-30789-DETAIL-01_23_2023-GO95MLD-1^06148004.0192300 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
185489324-27379-ADMIN-03_10_2023-GO95CL10-1^06148004.0192401 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
9996305-30189-DETAIL-01_23_2023-GO95MLD-1^06148004.0192404 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
2514386-77179-DETAIL-01_23_2023-ABNDEQPM-1^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
2514386-77179-DETAIL-01_23_2023-GO95HV-1^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
2514386-77179-DETAIL-01_23_2023-GO95MLD-1^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
2514386-77179-DETAIL-01_23_2023-GRDRODHI-1^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
2514386-77179-DETAIL-01_23_2023-GRDRODHI-2^06148004.0192405 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
971719134-61089-DETAIL-01_23_2023-GO95MLD-1^06148004.0192500 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
32540934-2089-DETAIL-01_23_2023-GO95MLD-1^06148004.0192501 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
620333573-49179-DTLSB-05_28_2024-GO95HV-1^06243001.0125103 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
824030043-79979-DTLSB-05_28_2024-GO95MLD-1^06243001.0125202 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
363530533-310-DTLSB-05_28_2024-GO95MLD-1^06243001.0125203 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
714183353-28861-DTLSB-05_28_2024-GO95MLD-1^06243001.0125300 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
714183353-28861-DTLSB-05_28_2024-SVCENTCO-1^06243001.0125300 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
260403783-10279-DTLSB-05_28_2024-GO95HV-1^06243001.0126103 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
468210583-77431-DTLSB-05_28_2024-GO95MLD-1^06243001.0126200 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
510117793-35791-DTLSB-05_28_2024-GO95MLD-1^06243001.0126201 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
811950613-98332-DTLSB-05_28_2024-SVCROAD-1^06243001.0126301 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
889155403-78182-DTLSB-05_28_2024-GO95MLD-1^06243001.0126302 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2027-05-28 | 2
581159003-20081-DTLSB-05_28_2024-GO95HV-1^06243001.0126303 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
581159003-20081-DTLSB-05_28_2024-GO95MLD-1^06243001.0126303 | OTHER | CA-NON-TIER | Distribution | 2024-05-28 | 2029-05-28 | 3
256266141-23189-DETAIL-01_23_2023-GO95HV-1^06148004.0193202 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
331697604-40540-DETAIL-01_23_2023-GO95MLD-1^06148004.0193700 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
762469876-12976-DETAIL-01_23_2023-GO95MLD-1^06148004.0193701 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
762469876-12976-DETAIL-01_23_2023-GO95TCH-1^06148004.0193701 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
535532334-57689-DETAIL-01_23_2023-GO95MLD-1^06148004.0196000 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
468054034-17689-DETAIL-01_23_2023-GO95MLD-1^06148004.0196002 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
43261524-76689-DETAIL-01_23_2023-GO95HV-1^06148004.0197001 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
43261524-76689-DETAIL-01_23_2023-GO95MLD-1^06148004.0197001 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
779052414-16689-DETAIL-01_23_2023-GO95MLD-1^06148004.0199000 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
567072805-90109-DETAIL-01_19_2023-GO95MLD-1^06148004.0199601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
567072805-90109-DETAIL-01_19_2023-GO95MLD-2^06148004.0199601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
567072805-90109-DETAIL-01_19_2023-SVCROAD-1^06148004.0199601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
707808905-98009-DETAIL-01_19_2023-GO95HV-1^06148004.0199701 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
645638125-68179-DETAIL-01_19_2023-ABNDEQPM-1^06148004.0199801 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
453083105-96109-DETAIL-01_23_2023-CONDFRAY-1^06148004.0200001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
554324204-44279-DETAIL-01_19_2023-GO95HV-1^06148004.0200004 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
954916105-78109-DETAIL-01_23_2023-GO95HV-1^06148004.0200100 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2028-01-23 | 3
260773315-36879-DETAIL-01_23_2023-GO95MLD-1^06148004.0200200 | OTHER | CA-NON-TIER | Distribution | 2023-01-23 | 2026-01-23 | 2
189044191-18779-DETAIL-01_19_2023-GO95MLD-1^06148004.0200600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
189044191-18779-ADMIN-03_10_2023-GO95CL10-1^06148004.0200600 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
21223755-48179-DETAIL-01_18_2023-GO95HV-1^06148004.0204000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
21223755-48179-DETAIL-01_18_2023-GO95MLD-1^06148004.0204000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
653137285-56579-DETAIL-01_19_2023-GO95HV-1^06148004.0204200 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
653137285-56579-DETAIL-01_19_2023-GO95MLD-1^06148004.0204200 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
799018963-96389-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049200 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
799018963-96389-DETAIL-02_22_2023-GO95MLD-1^06247002.0049200 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
480338063-14251-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049201 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
402402953-11550-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049300 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
105621922-62240-DETAIL-02_21_2023-GO95HV-1^06247002.0095000 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
611472932-35221-DETAIL-02_21_2023-CONDFRAY-1^06247002.0095400 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
998335421-5299-DETAIL-02_21_2023-GO95MLD-1^06247002.0095500 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
933973412-71972-DETAIL-02_21_2023-GO95MLD-1^06247002.0096000 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
942542822-30803-DETAIL-02_21_2023-GO95HV-1^06247002.0096002 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
80496892-31779-DETAIL-02_14_2023-GO95MLD-1^06247002.0112900 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2026-02-14 | 2
577034102-51581-ADMIN-02_14_2023-GO95HV-1^06247002.0113101 | OTHER | CA-NON-TIER | Distribution | 2023-02-14 | 2028-02-14 | 3
149619052-13390-DETAIL-02_13_2023-GO95HV-1^06247002.0117700 | OTHER | CA-NON-TIER | Distribution | 2023-02-13 | 2028-02-13 | 3
112370225-17079-DETAIL-01_18_2023-INSULDMG-1^06148004.0207100 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
977348665-69109-ADMIN-01_18_2023-ENCHRW-1^06148004.0207201 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
436529965-89109-DETAIL-01_18_2023-GO95MLD-1^06148004.0207301 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
720766155-36789-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207400 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
720766155-36789-DETAIL-01_18_2023-COPLLEAN-1^06148004.0207400 | POLE | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
720766155-36789-DETAIL-01_18_2023-GO95MLD-1^06148004.0207400 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
815023224-38279-DETAIL-01_18_2023-GO95HV-1^06148004.0207500 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
815023224-38279-DETAIL-01_18_2023-GO95MLD-1^06148004.0207500 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
815023224-38279-DETAIL-01_18_2023-GO95MLD-2^06148004.0207500 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
872484884-58789-DETAIL-01_19_2023-INSULDMG-1^06148004.0207601 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
984444755-90009-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
984444755-90009-DETAIL-01_18_2023-CONDFRAY-2^06148004.0207700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
984444755-90009-DETAIL-01_18_2023-CONDFRAY-3^06148004.0207700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
220278255-65579-DETAIL-01_18_2023-COPLLEAN-1^06148004.0207701 | POLE | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
220278255-65579-DETAIL-01_18_2023-GO95BLTC-1^06148004.0207701 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
220278255-65579-DETAIL-01_18_2023-GO95HV-1^06148004.0207701 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
220278255-65579-DETAIL-01_18_2023-GO95MLD-1^06148004.0207701 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
220278255-65579-DETAIL-01_18_2023-GO95MLD-2^06148004.0207701 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
277165745-9-DETAIL-01_18_2023-GO95MLD-1^06148004.0207800 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
489594245-40009-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207900 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
489594245-40009-DETAIL-01_18_2023-GO95HV-1^06148004.0207900 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
489594245-40009-DETAIL-01_18_2023-GO95MLD-1^06148004.0207900 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
955473781-2779-AUDIT-02_16_2023-ABNDEQPM-1^06148004.0207901 | OTHER | CA-NON-TIER | Distribution | 2023-02-16 | 2028-02-16 | 3
394165985-58109-DETAIL-01_18_2023-GO95HV-1^06148004.0208001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
502853450-94789-DETAIL-01_09_2023-GO95HV-1^06148003.0154300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
502853450-94789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
314511040-44789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
686266160-35789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154302 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
302898230-4789-DETAIL-01_09_2023-GO95MLD-1^06148003.0155300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
418621520-43789-DETAIL-01_09_2023-GO95HV-1^06148003.0156300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
418621520-43789-DETAIL-01_09_2023-GO95MLD-1^06148003.0156300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
259701530-73789-DETAIL-01_09_2023-GO95MLD-1^06148003.0156301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
570033820-13789-DETAIL-01_09_2023-GO95MLD-1^06148003.0157300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
804559110-32789-DETAIL-01_09_2023-GO95MLD-1^06148003.0158300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
867283120-92789-DETAIL-01_09_2023-GO95MLD-1^06148003.0158301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
688239680-91789-DETAIL-01_09_2023-GO95MLD-1^06148003.0159300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
58616859-94489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0174000 | POLE | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
447250159-53489-DETAIL-01_26_2023-CONDFRAY-1^06148003.0174100 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
14715359-54489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0174101 | POLE | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
700939649-3489-DETAIL-01_26_2023-GO95HV-1^06148003.0174200 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
989006429-35323-DETAIL-01_26_2023-GO95MLD-1^06148003.0204602 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
575026769-85489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0204800 | POLE | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
575026769-85489-DETAIL-01_26_2023-GO95MLD-1^06148003.0204800 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
131203977-46977-DETAIL-01_26_2023-GO95MLD-1^06148003.0204901 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
252476849-53589-DETAIL-01_30_2023-GO95HV-1^06148003.0205000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
357228539-23589-DETAIL-01_30_2023-GO95HV-1^06148003.0205101 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2028-01-30 | 3
333726789-87899-DETAIL-01_26_2023-GO95TCH-1^06148003.0206401 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
357318943-16300-DTLSB-05_23_2024-GO95MLD-1^06243001.0149101 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
834067243-69789-DTLSB-05_23_2024-GO95HV-1^06243001.0149200 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
834067243-69789-DTLSB-05_23_2024-GO95MLD-1^06243001.0149200 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
574616043-99771-DTLSB-05_23_2024-GO95MLD-1^06243001.0149301 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
738162623-96421-DETAIL-05_23_2024-GO95HV-1^06243001.0149501 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
993345773-87243-ADMIN-05_23_2024-ABNDEQPM-1^06243001.0149600 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
192219363-8630-DTLSB-05_23_2024-GO95MLD-1^06243001.0149601 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
195876823-57430-DTLSB-05_23_2024-GO95MLD-1^06243001.0149602 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
735949748-80848-DTLSB-05_23_2024-GO95MLD-1^06243001.0149603 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
926340013-77642-DTLSB-05_23_2024-GO95MLD-1^06243001.0149700 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
238889903-779-DTLSB-05_23_2024-GO95MLD-1^06243001.0238800 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
260139313-3590-DTLSB-05_23_2024-GO95HV-1^06243001.0238801 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
583123811-29089-DETAIL-01_24_2023-CONDFRAY-1^06148003.0240100 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
583123811-29089-DETAIL-01_24_2023-GO95HV-1^06148003.0240100 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
642791511-98089-DETAIL-01_24_2023-GO95MLD-1^06148003.0240200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
642791511-98089-DETAIL-01_24_2023-GRDRODHI-1^06148003.0240200 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
404410731-8089-DETAIL-01_24_2023-CONDFRAY-1^06148003.0241301 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
292623311-55089-DETAIL-01_24_2023-GO95MLD-1^06148003.0243400 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
292623311-55089-DETAIL-01_24_2023-GRDRODHI-1^06148003.0243400 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
391250611-91611-DETAIL-01_24_2023-GO95MLD-1^06148003.0248401 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
638904651-74089-DETAIL-01_24_2023-GO95MLD-1^06148003.0248501 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
48516217-54644-DETAIL-01_24_2023-ABNDEQPM-1^06148003.0249400 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
859197585-11989-DETAIL-01_24_2023-GO95MLD-1^06148003.0249402 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
225050031-99579-DETAIL-01_24_2023-GO95MLD-1^06148003.0249501 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
619480261-9289-DETAIL-01_24_2023-GO95MLD-1^06148003.0249502 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
433478259-99279-DETAIL-01_24_2023-GO95HV-1^06148003.0257601 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
433478259-99279-DETAIL-01_24_2023-GO95MLD-1^06148003.0257601 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
452583749-23289-DETAIL-01_24_2023-GO95HV-1^06148003.0257700 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
517498699-48701-DETAIL-01_24_2023-GO95HV-1^06148003.0259000 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
490145909-28461-DETAIL-01_25_2023-GO95MLD-1^06148003.0265001 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
514012539-88891-DETAIL-01_24_2023-INSULDMG-1^06148003.0265400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
514012539-88891-DETAIL-01_24_2023-INSULDMG-2^06148003.0265400 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
96192260-20579-DETAIL-01_24_2023-GO95HV-1^06148003.0265500 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
96192260-20579-DETAIL-01_24_2023-GO95MLD-1^06148003.0265500 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
96192260-20579-DETAIL-01_24_2023-GRDRODHI-1^06148003.0265500 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
773469183-46279-DETAIL-01_18_2023-GO95MLD-1^06148004.0212001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
338665213-56579-DETAIL-01_19_2023-GO95MLD-1^06148004.0212601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
338665213-56579-DETAIL-01_19_2023-SVCROAD-1^06148004.0212601 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
187360763-54309-DETAIL-01_18_2023-GO95HV-1^06148004.0213000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
729610831-74309-DETAIL-01_18_2023-GO95HV-1^06148004.0214001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
109420054-88779-DETAIL-01_19_2023-GO95MLD-1^06148004.0214600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
109420054-88779-AUDIT-02_06_2023-GUYHINS-1^06148004.0214600 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
664838463-35309-DETAIL-01_18_2023-GO95MLD-1^06148004.0215001 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-CONDFRAY-1^06148004.0215002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-CONDFRAY-2^06148004.0215002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-CONDFRAY-3^06148004.0215002 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-GO95MLD-1^06148004.0215002 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
649401669-25281-DETAIL-01_25_2023-INSULDMG-1^06148003.0355500 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
941019959-1203-DETAIL-01_25_2023-GRDRODHI-1^06148003.0355501 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
941019959-1203-AUDIT-02_06_2023-GO95HV-1^06148003.0355501 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
941019959-1203-AUDIT-02_06_2023-GRDRODHI-1^06148003.0355501 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
458069169-27221-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355600 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
574979079-4071-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
574979079-4071-DETAIL-01_25_2023-COPLLEAN-1^06148003.0355700 | POLE | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
422878189-54670-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355903 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
815329460-46542-DETAIL-01_25_2023-GO95MLD-1^06148003.0356900 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
815329460-46542-DETAIL-01_25_2023-GO95TCH-1^06148003.0356900 | OTHER | CA-NON-TIER | Distribution | 2023-01-25 | 2026-01-25 | 2
920301819-29612-DETAIL-01_24_2023-GO95HV-1^06148003.0368901 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2028-01-24 | 3
920301819-29612-DETAIL-01_24_2023-GO95MLD-1^06148003.0368901 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
906223471-35279-DETAIL-01_11_2023-SVCROAD-1^06148004.0133200 | OTHER | CA-NON-TIER | Distribution | 2023-01-11 | 2026-01-11 | 2
887057583-6679-DETAIL-01_11_2023-SVCROAD-1^06148004.0137200 | OTHER | CA-NON-TIER | Distribution | 2023-01-11 | 2026-01-11 | 2
887057583-6679-AUDIT-01_18_2023-SVCROAD-1^06148004.0137200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
489475360-72889-AUDIT-01_18_2023-GO95HV-1^06148004.0139000 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
22347603-9279-DETAIL-01_11_2023-SVCROAD-1^06148004.0139200 | OTHER | CA-NON-TIER | Distribution | 2023-01-11 | 2026-01-11 | 2
620195621-17479-ADMIN-01_12_2023-ENCHRW-1^06148004.0140200 | OTHER | CA-NON-TIER | Distribution | 2023-01-12 | 2026-01-12 | 2
629846721-85089-ADMIN-01_12_2023-ENCHRW-1^06148004.0142200 | OTHER | CA-NON-TIER | Distribution | 2023-01-12 | 2026-01-12 | 2
635651741-78989-ADMIN-03_10_2023-GO95CL10-1^06148004.0148200 | OTHER | CA-NON-TIER | Distribution | 2023-03-10 | 2028-03-10 | 3
813767351-58989-AUDIT-01_18_2023-SVCROAD-1^06148004.0149200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
374096973-69109-DETAIL-01_16_2023-GO95HV-1^06148004.0150000 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
881550413-30279-DETAIL-01_18_2023-GO95MLD-2^06148004.0215002 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
881550413-30279-DETAIL-01_18_2023-GO95TCH-1^06148004.0215002 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
981280733-16309-DETAIL-01_18_2023-CONDFRAY-1^06148004.0215101 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
981280733-16309-DETAIL-01_18_2023-GO95HV-1^06148004.0215101 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2028-01-18 | 3
72454614-79779-DETAIL-01_18_2023-GO95MLD-1^06148004.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
72454614-79779-DETAIL-01_18_2023-GO95MLD-2^06148004.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
72454614-79779-DETAIL-01_18_2023-GO95TCH-1^06148004.0215200 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
72454614-79779-DETAIL-01_18_2023-GUYHINS-1^06148004.0215200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
322603701-14701-DETAIL-01_18_2023-GO95TCH-1^06148004.0215201 | OTHER | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
383003071-51079-DETAIL-01_19_2023-GO95HV-1^06148004.0215600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2028-01-19 | 3
383003071-51079-DETAIL-01_19_2023-GO95MLD-1^06148004.0215600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
383003071-51079-DETAIL-01_19_2023-GO95TCH-1^06148004.0215600 | OTHER | CA-NON-TIER | Distribution | 2023-01-19 | 2026-01-19 | 2
389385127-87127-DETAIL-01_16_2023-GO95MLD-1^06148004.0162300 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
72765124-41379-DETAIL-01_16_2023-GO95MLD-1^06148004.0162302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
72765124-41379-DETAIL-01_16_2023-GO95TCH-1^06148004.0162302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
876075484-75909-DETAIL-01_16_2023-GO95HV-1^06148004.0163200 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
876075484-75909-DETAIL-01_16_2023-GUYSLACK-1^06148004.0163200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
483198524-55909-DETAIL-01_16_2023-GO95TCH-1^06148004.0163302 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
387241904-81279-DETAIL-01_16_2023-GO95MLD-1^06148004.0163303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
387241904-81279-DETAIL-01_16_2023-GO95MLD-2^06148004.0163303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
797710824-3579-DETAIL-01_16_2023-GO95MLD-1^06148004.0163304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
246289704-63909-DETAIL-01_16_2023-GO95HV-1^06148004.0164100 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
246289704-63909-DETAIL-01_16_2023-GO95MLD-1^06148004.0164100 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
246289704-63909-DETAIL-01_16_2023-GO95MLD-2^06148004.0164100 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
299242151-28451-DETAIL-01_16_2023-GO95BLTC-1^06148004.0164120 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
299242151-28451-DETAIL-01_16_2023-GO95MLD-1^06148004.0164120 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
299242151-28451-DETAIL-01_16_2023-GO95MLD-2^06148004.0164120 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
949933615-66909-DETAIL-01_16_2023-GO95MLD-1^06148004.0164140 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
949933615-66909-DETAIL-01_16_2023-GO95TCH-1^06148004.0164140 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
471956314-86909-DETAIL-01_16_2023-GO95MLD-1^06148004.0164200 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
471956314-86909-DETAIL-01_16_2023-GUYHINS-1^06148004.0164200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
754291754-95589-DETAIL-01_16_2023-GO95MLD-1^06148004.0164203 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
692654924-82909-DETAIL-01_16_2023-GO95MLD-1^06148004.0164301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
157384174-72689-DETAIL-01_16_2023-GO95HV-1^06148004.0164303 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
662777284-43579-DETAIL-01_16_2023-GO95HV-1^06148004.0164304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
662777284-43579-DETAIL-01_16_2023-GO95MLD-1^06148004.0164304 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
336600334-10999-DETAIL-03_21_2024-GO95MLD-1^06147005.0209500 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
336600334-10999-DETAIL-03_21_2024-GRDRODHI-1^06147005.0209500 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
356680064-39899-DETAIL-03_21_2024-GO95HV-1^06147005.0209501 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
614993384-59899-DETAIL-03_21_2024-GO95HV-1^06147005.0209502 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
316227074-99899-DETAIL-03_21_2024-GO95BLTC-1^06147005.0209503 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
316227074-99899-DETAIL-03_21_2024-GUYHINS-1^06147005.0209503 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
414816413-78899-DETAIL-03_21_2024-GO95MLD-1^06147005.0209801 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
175094029-62309-DETAIL-04_09_2024-GO95MLD-1^06147005.0210000 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
175094029-62309-DETAIL-04_09_2024-GUYHINS-1^06147005.0210000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
110076167-74279-DETAIL-04_09_2024-GO95MLD-1^06147005.0211001 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
985571308-84979-DETAIL-04_09_2024-CLRTOUCH-1^06147005.0212001 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
985571308-84979-DETAIL-04_09_2024-GO95MLD-1^06147005.0212001 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
742775818-22009-DETAIL-04_09_2024-GO95TCH-1^06147005.0215800 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
416333438-12009-DETAIL-04_09_2024-GO95BLTC-1^06147005.0215802 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
416333438-12009-DETAIL-04_09_2024-SVCROAD-1^06147005.0215802 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
1909404-57904-DETAIL-04_09_2024-CLRTOUCH-1^06147005.0215820 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
642196628-43009-DETAIL-04_09_2024-GO95MLD-1^06147005.0216701 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
642196628-43009-DETAIL-04_09_2024-GRDRODHI-1^06147005.0216701 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
22360477-6099-DETAIL-04_09_2024-GO95HV-1^06147005.0217002 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
712109807-37579-DETAIL-04_09_2024-GO95MLD-1^06147005.0217003 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
712109807-37579-DETAIL-04_09_2024-GO95STUB-1^06147005.0217003 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
296664389-8479-AUDIT-04_19_2024-GO95TCH-1^06147005.0217004 | OTHER | CA-NON-TIER | Distribution | 2024-04-19 | 2027-04-19 | 2
973144739-75209-DETAIL-04_09_2024-GO95HV-1^06147005.0217100 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
597290949-73579-DETAIL-04_09_2024-GO95MLD-1^06147005.0217200 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
790836359-71409-DETAIL-04_09_2024-CUTOUTAR-1^06147005.0217601 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
790836359-71409-DETAIL-04_09_2024-GO95HV-1^06147005.0217601 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
790836359-71409-DETAIL-04_09_2024-GUYHINS-1^06147005.0217601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
18991749-21409-AUDIT-04_19_2024-GO95MLD-1^06147005.0217602 | OTHER | CA-NON-TIER | Distribution | 2024-04-19 | 2029-04-19 | 3
596660548-62409-DETAIL-04_09_2024-GO95MLD-1^06147005.0217701 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
596660548-62409-DETAIL-04_09_2024-INSULDMG-1^06147005.0217701 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
275890732-6009-DETAIL-04_09_2024-COPLLEAN-1^06147005.0218601 | POLE | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
275890732-6009-DETAIL-04_09_2024-GO95HV-1^06147005.0218601 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
275890732-6009-DETAIL-04_09_2024-GO95MLD-1^06147005.0218601 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
275890732-6009-DETAIL-04_09_2024-GRDRODHI-1^06147005.0218601 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
396941732-44009-DETAIL-04_09_2024-GO95MLD-1^06147005.0218602 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
64566842-74009-DETAIL-04_09_2024-GO95MLD-1^06147005.0219503 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
260139313-3590-DTLSB-05_23_2024-GO95MLD-1^06243001.0238801 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
381125463-76230-DTLSB-05_23_2024-GO95MLD-1^06243001.0238901 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
616325033-83831-DTLSB-05_23_2024-GO95MLD-1^06243001.0239500 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
828677623-13292-DTLSB-05_23_2024-GO95MLD-1^06243001.0239601 | OTHER | CA-NON-TIER | Distribution | 2024-05-23 | 2029-05-23 | 3
31795514-29500-DTLSB-05_06_2024-GO95MLD-1^06243003.0096400 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
335026794-25180-DTLSB-05_06_2024-GO95HV-1^06243003.0096403 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2029-05-06 | 3
335026794-25180-DTLSB-05_06_2024-GO95MLD-1^06243003.0096403 | OTHER | CA-NON-TIER | Distribution | 2024-05-06 | 2027-05-06 | 2
849157174-98289-DTLSB-05_09_2024-INSULDMG-1^06244001.0010200 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-05-09 | 2027-05-09 | 2
771172124-93212-DTLSB-05_09_2024-GO95MLD-1^06244001.0025000 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
856757034-65872-DTLSB-05_09_2024-GO95MLD-1^06244001.0026000 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
8434834-98079-DTLSB-05_09_2024-GO95MLD-1^06244001.0026002 | OTHER | CA-NON-TIER | Distribution | 2024-05-09 | 2029-05-09 | 3
773995185-69622-DTLSB-05_08_2024-GO95MLD-1^06244001.0031800 | OTHER | CA-NON-TIER | Distribution | 2024-05-08 | 2029-05-08 | 3
643594929-37479-DETAIL-04_03_2024-GO95MLD-1^06147005.0222700 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
591254360-5360-DETAIL-04_08_2024-GO95MLD-1^06147005.0223200 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
591254360-5360-DETAIL-04_08_2024-SVCENTCO-1^06147005.0223200 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
908696598-85679-DETAIL-04_08_2024-GO95MLD-1^06147005.0227003 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
10623879-5679-DETAIL-04_08_2024-GO95MLD-1^06147005.0227401 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
884213868-42479-DETAIL-04_03_2024-GO95MLD-1^06147005.0227800 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
167475529-97779-DETAIL-04_08_2024-GO95MLD-1^06147005.0229501 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
167475529-97779-DETAIL-04_08_2024-GUYHINS-1^06147005.0229501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
299321503-28938-DETAIL-04_03_2024-GO95MLD-1^06147005.0229900 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
366695496-94079-DETAIL-04_08_2024-GO95MLD-1^06147005.0232001 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
121178396-56179-DETAIL-04_08_2024-GO95MLD-1^06147005.0232003 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
121178396-56179-DETAIL-04_08_2024-GRDRODHI-1^06147005.0232003 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
433011066-83479-DETAIL-04_03_2024-GO95MLD-1^06147005.0232700 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
433011066-83479-DETAIL-04_03_2024-SVCENTCO-1^06147005.0232700 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
772532556-11409-DETAIL-04_03_2024-INSULDMG-1^06147005.0232801 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
790027586-4179-DETAIL-04_08_2024-GO95MLD-1^06147005.0234003 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
935527576-84309-DETAIL-04_08_2024-GO95MLD-1^06147005.0234005 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
935527576-84309-DETAIL-04_08_2024-GUYHINS-1^06147005.0234005 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
709299426-43979-DETAIL-04_08_2024-GO95MLD-1^06147005.0236200 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
218902816-48409-DETAIL-04_08_2024-CONDFRAY-1^06147005.0237201 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
389587386-87179-DETAIL-04_03_2024-GO95MLD-1^06147005.0237700 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
389587386-87179-DETAIL-04_03_2024-GUYHINS-1^06147005.0237700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
597699816-23509-DETAIL-04_04_2024-GO95HV-1^06147005.0238101 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
88979726-52079-ADMIN-04_04_2024-ABNDEQPM-1^06147005.0238102 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
414178835-12779-DETAIL-01_16_2023-GO95MLD-1^06148004.0165306 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
414178835-12779-DETAIL-01_16_2023-SVCROAD-1^06148004.0165306 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
414178835-12779-DETAIL-01_16_2023-SVCROAD-2^06148004.0165306 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
414338345-88345-DETAIL-01_16_2023-GO95MLD-1^06148004.0165307 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
87574840-25840-DETAIL-01_16_2023-GO95TCH-1^06148004.0166200 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
545648575-61909-DETAIL-01_16_2023-POLETOP-1^06148004.0166305 | POLE | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
364450605-19809-DETAIL-01_16_2023-GO95HV-1^06148004.0167301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2028-01-16 | 3
364450605-19809-DETAIL-01_16_2023-GO95MLD-1^06148004.0167301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
364450605-19809-DETAIL-01_16_2023-GO95TCH-1^06148004.0167301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
364450605-19809-DETAIL-01_16_2023-GRDRODHI-1^06148004.0167301 | OTHER | CA-NON-TIER | Distribution | 2023-01-16 | 2026-01-16 | 2
811910845-89379-DETAIL-01_10_2023-GO95BLTC-1^06148004.0170300 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2028-01-10 | 3
913966506-66779-DETAIL-04_08_2024-SVCENTCO-1^06147005.0245100 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
64993376-15779-ADMIN-04_08_2024-ABNDEQPM-1^06147005.0245400 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
64993376-15779-DETAIL-04_08_2024-CUTOUTAR-1^06147005.0245400 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-04-08 | 2027-04-08 | 2
64993376-15779-DETAIL-04_08_2024-GO95MLD-1^06147005.0245400 | OTHER | CA-NON-TIER | Distribution | 2024-04-08 | 2029-04-08 | 3
763058768-68479-DETAIL-04_09_2024-GO95MLD-1^06147005.0254600 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
763058768-68479-DETAIL-04_09_2024-GUYHINS-1^06147005.0254600 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
959300613-60613-DETAIL-04_09_2024-CONDFRAY-1^06147005.0254704 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
959300613-60613-DETAIL-04_09_2024-CONDFRAY-2^06147005.0254704 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
959300613-60613-DETAIL-04_09_2024-GO95HV-1^06147005.0254704 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
959300613-60613-DETAIL-04_09_2024-GO95MLD-1^06147005.0254704 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
608035931-88621-DETAIL-04_09_2024-GO95MLD-1^06147005.0255000 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2029-04-09 | 3
608035931-88621-DETAIL-04_09_2024-GO95TCH-1^06147005.0255000 | OTHER | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
608035931-88621-DETAIL-04_09_2024-GUYHINS-1^06147005.0255000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
608035931-88621-DETAIL-04_09_2024-INSULDMG-1^06147005.0255000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-09 | 2027-04-09 | 2
130582510-72379-DETAIL-02_02_2022-ABNDEQPM-1^06147005.0260503 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
439582539-86609-DETAIL-02_02_2022-ABNDEQPM-1^06147005.0261500 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2027-02-02 | 3
439582539-86609-DETAIL-02_02_2022-GO95MLD-1^06147005.0261500 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
600506049-71309-ADMIN-01_23_2024-POLEREPL-1^06147005.0261702 | POLE | CA-NON-TIER | Distribution | 2024-01-23 | 2027-01-23 | 2
188384368-29079-DETAIL-02_01_2022-SVCWIND-1^06147005.0265405 | OTHER | CA-NON-TIER | Distribution | 2022-02-01 | 2025-02-01 | 2
997358828-67409-DETAIL-02_02_2022-SVCENTCO-1^06147005.0266201 | OTHER | CA-NON-TIER | Distribution | 2022-02-02 | 2025-02-02 | 2
612493551-65879-DETAIL-01_10_2023-GO95HV-1^06148004.0170301 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2028-01-10 | 3
612493551-65879-DETAIL-01_10_2023-GO95MLD-1^06148004.0170301 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
612493551-65879-DETAIL-01_10_2023-GRDRODHI-1^06148004.0170301 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
443259831-8279-DETAIL-01_17_2023-GO95BLTC-1^06148004.0174302 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
443259831-8279-DETAIL-01_17_2023-GO95MLD-1^06148004.0174302 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
604570584-52584-DETAIL-01_17_2023-GO95MLD-1^06148004.0174303 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
265220486-14379-DETAIL-01_17_2023-GO95HV-1^06148004.0175000 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
265220486-14379-DETAIL-01_17_2023-GO95MLD-1^06148004.0175000 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
265220486-14379-DETAIL-01_17_2023-GO95MLD-2^06148004.0175000 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
22382176-83989-DETAIL-01_17_2023-CONDFRAY-1^06148004.0175001 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
275013566-23989-DETAIL-01_17_2023-GO95HV-1^06148004.0175200 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
315371766-72989-DETAIL-01_17_2023-GO95HV-1^06148004.0175300 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
224353252-59099-AUDIT-04_18_2024-GO95HV-1^06147004.0350501 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
578914702-98999-DETAIL-03_21_2024-COPLLEAN-1^06147004.0366400 | POLE | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
578914702-98999-DETAIL-03_21_2024-GO95HV-1^06147004.0366400 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
870775965-65699-DETAIL-10_14_2021-RISEBKSP-1^06147005.0010900 | OTHER | CA-NON-TIER | Distribution | 2021-10-14 | 2024-10-14 | 2
916931256-68199-DETAIL-10_13_2021-SVCROAD-1^06147005.0022003 | OTHER | CA-NON-TIER | Distribution | 2021-10-13 | 2024-10-13 | 2
923035571-49281-DETAIL-10_07_2021-SVCWIND-1^06147005.0043900 | OTHER | CA-NON-TIER | Distribution | 2021-10-07 | 2024-10-07 | 2
569721919-23099-DETAIL-09_29_2021-SVCROAD-1^06147005.0047200 | OTHER | CA-NON-TIER | Distribution | 2021-09-29 | 2024-09-29 | 2
854913524-57009-DETAIL-04_01_2024-GO95HV-1^06147005.0090600 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
608905824-26009-DETAIL-04_01_2024-GO95HV-1^06147005.0090900 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
510514978-56499-DETAIL-04_01_2024-GO95MLD-1^06147005.0090901 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
942193888-82403-DETAIL-04_02_2024-GO95MLD-1^06147005.0092200 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
942193888-82403-DETAIL-04_02_2024-GO95TCH-1^06147005.0092200 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
942193888-82403-DETAIL-04_02_2024-GRDRODHI-1^06147005.0092200 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
4251518-92909-DETAIL-04_02_2024-GO95HV-1^06147005.0092300 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
241663028-72080-DETAIL-04_02_2024-GO95HV-1^06147005.0092401 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
82289979-55599-DETAIL-04_01_2024-GUYHINS-1^06147005.0093700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
836601679-15599-DETAIL-04_01_2024-GO95HV-1^06147005.0093800 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
708743408-86409-DETAIL-04_01_2024-GO95MLD-1^06147005.0094900 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
564116759-82261-DETAIL-04_02_2024-GO95HV-1^06147005.0096000 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
657515869-35501-DETAIL-04_02_2024-GO95TCH-1^06147005.0096200 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
701374737-35737-DETAIL-02_09_2022-GO95HV-1^06147005.0279702 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2027-02-09 | 3
701374737-35737-DETAIL-02_09_2022-GO95MLD-1^06147005.0279702 | OTHER | CA-NON-TIER | Distribution | 2022-02-09 | 2025-02-09 | 2
221463046-8199-DETAIL-02_15_2022-GO95HV-1^06147005.0330200 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
221463046-8199-DETAIL-02_15_2022-GO95MLD-1^06147005.0330200 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
221463046-8199-DETAIL-02_15_2022-INSULDMG-1^06147005.0330200 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
707777554-48009-DETAIL-02_15_2022-GO95MLD-1^06147005.0330201 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
707777554-48009-DETAIL-02_15_2022-GO95TCH-1^06147005.0330201 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
346556284-37009-DETAIL-02_15_2022-INSULDMG-1^06147005.0333201 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
202187914-95009-DETAIL-02_15_2022-GO95HV-1^06147005.0334102 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2027-02-15 | 3
983375579-73199-DETAIL-04_01_2024-GO95HV-1^06147005.0107902 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
927064488-26199-DETAIL-04_01_2024-SVCDEFLC-1^06147005.0108900 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
841378506-21019-DETAIL-03_28_2024-GO95HV-1^06147005.0112001 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
841378506-21019-DETAIL-03_28_2024-INSULDMG-1^06147005.0112001 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
210543017-35017-ADMIN-03_25_2024-GO95TCH-1^06147005.0112002 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2027-03-25 | 2
226055616-89909-DETAIL-03_28_2024-GO95HV-1^06147005.0112100 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
720848916-75379-DETAIL-03_28_2024-GO95HV-1^06147005.0112201 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
720848916-75379-DETAIL-03_28_2024-GO95TCH-1^06147005.0112201 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
259633676-29199-DETAIL-04_01_2024-SVCROAD-1^06147005.0112900 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
657193093-3299-DETAIL-04_01_2024-SVCROAD-1^06147005.0113900 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
421450226-70299-DETAIL-04_01_2024-GO95TCH-1^06147005.0113901 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
937460088-81709-DETAIL-03_28_2024-GO95HV-1^06147005.0117100 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
64951538-60679-DETAIL-03_28_2024-GO95MLD-1^06147005.0117200 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
64951538-60679-DETAIL-03_28_2024-GO95TCH-1^06147005.0117200 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
783453496-86299-DETAIL-04_01_2024-CLRTOUCH-1^06147005.0117800 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
783453496-86299-DETAIL-04_01_2024-GO95HV-1^06147005.0117800 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
783453496-86299-DETAIL-04_01_2024-GO95TCH-1^06147005.0117800 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
679391395-7379-DETAIL-03_28_2024-GO95HV-1^06147005.0118500 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
679391395-7379-DETAIL-03_28_2024-GO95MLD-1^06147005.0118500 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
493181985-5219-DETAIL-03_25_2024-GO95TCH-1^06147005.0120000 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2027-03-25 | 2
76612248-86219-DETAIL-03_28_2024-GO95MLD-1^06147005.0122000 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
113170997-71997-DETAIL-03_28_2024-GO95HV-1^06147005.0122002 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
113170997-71997-DETAIL-03_28_2024-GO95MLD-1^06147005.0122002 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
162880858-34079-DETAIL-03_28_2024-GO95HV-1^06147005.0122201 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
428672334-96009-DETAIL-02_15_2022-GO95MLD-1^06147005.0334300 | OTHER | CA-NON-TIER | Distribution | 2022-02-15 | 2025-02-15 | 2
122174542-66509-DETAIL-02_14_2022-GO95HV-1^06147005.0350601 | OTHER | CA-NON-TIER | Distribution | 2022-02-14 | 2027-02-14 | 3
463181600-88509-DETAIL-02_10_2022-GO95HV-1^06147005.0350603 | OTHER | CA-NON-TIER | Distribution | 2022-02-10 | 2027-02-10 | 3
417349378-38079-DETAIL-03_09_2022-ABNDEQPM-1^06147006.0181203 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
564786249-89779-DETAIL-02_28_2022-ABNDEQPM-1^06147006.0300000 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
709957261-49851-DETAIL-03_07_2022-GO95HV-1^06147006.0316101 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
709957261-49851-DETAIL-03_07_2022-GO95MLD-1^06147006.0316101 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
796719671-16282-DETAIL-03_07_2022-GO95MLD-1^06147006.0316200 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
89054385-30879-DETAIL-04_01_2024-GO95MLD-1^06147005.0127601 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
89054385-30879-DETAIL-04_01_2024-GRDRODHI-1^06147005.0127601 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
284363316-98579-DETAIL-04_01_2024-CUTOUTAR-1^06147005.0128700 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-04-01 | 2027-04-01 | 2
284363316-98579-DETAIL-04_01_2024-GO95MLD-1^06147005.0128700 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
554880706-37909-DETAIL-04_01_2024-GO95HV-1^06147005.0128701 | OTHER | CA-NON-TIER | Distribution | 2024-04-01 | 2029-04-01 | 3
112302246-15979-DETAIL-04_04_2024-GO95MLD-1^06147005.0130000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
894002490-84219-DETAIL-03_25_2024-GO95MLD-1^06147005.0130900 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2027-03-25 | 2
853281376-39079-DETAIL-04_04_2024-GO95MLD-1^06147005.0132000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
853281376-39079-DETAIL-04_04_2024-GO95TCH-1^06147005.0132000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
853281376-39079-DETAIL-04_04_2024-GRDBROKE-1^06147005.0132000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
853281376-39079-DETAIL-04_04_2024-SVCROAD-1^06147005.0132000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
464880036-60419-DETAIL-04_02_2024-GO95HV-1^06147005.0132001 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
293228936-30419-DETAIL-04_04_2024-INSULDMG-1^06147005.0132002 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
151554826-92579-DETAIL-04_04_2024-GO95MLD-1^06147005.0132003 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
151554826-92579-DETAIL-04_04_2024-GRDRODHI-1^06147005.0132003 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
151554826-92579-DETAIL-04_04_2024-SVCDEFLC-1^06147005.0132003 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
590830936-11419-DETAIL-04_02_2024-GO95HV-1^06147005.0132101 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
906521046-10179-DETAIL-04_02_2024-GO95TCH-1^06147005.0132200 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
600801406-53379-DETAIL-03_28_2024-GO95HV-1^06147005.0132700 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
600801406-53379-DETAIL-03_28_2024-GO95MLD-1^06147005.0132700 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
52110716-17219-DETAIL-03_25_2024-GO95HV-1^06147005.0133900 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
135530566-46479-DETAIL-03_25_2024-GO95MLD-1^06147005.0134700 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2027-03-25 | 2
965050416-77219-DETAIL-03_25_2024-GO95HV-1^06147005.0134900 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
27956181-71799-DETAIL-01_18_2023-GUYSLACK-1^06148004.0220400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-18 | 2026-01-18 | 2
623198271-22379-DETAIL-01_17_2023-GO95MLD-1^06148004.0220501 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
425267583-30209-DETAIL-01_17_2023-GO95MLD-1^06148004.0220601 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
12948131-50209-DETAIL-01_17_2023-GO95HV-1^06148004.0220602 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
12948131-50209-DETAIL-01_17_2023-GO95MLD-1^06148004.0220602 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
358491331-73079-DETAIL-01_17_2023-GO95CL10-1^06148004.0220701 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
358491331-73079-DETAIL-01_17_2023-GO95MLD-1^06148004.0220701 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
358491331-73079-DETAIL-01_17_2023-GO95TCH-1^06148004.0220701 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
593232111-87679-DETAIL-01_17_2023-GO95MLD-1^06148004.0220702 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
593232111-87679-DETAIL-01_17_2023-SVCROAD-1^06148004.0220702 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2026-01-17 | 2
876130821-41209-DETAIL-01_17_2023-GO95HV-1^06148004.0220800 | OTHER | CA-NON-TIER | Distribution | 2023-01-17 | 2028-01-17 | 3
983055616-58579-DETAIL-03_28_2024-GO95HV-1^06147005.0142700 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
983055616-58579-DETAIL-03_28_2024-GUYHINS-1^06147005.0142700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
738974070-81019-AUDIT-04_10_2024-GO95MLD-1^06147005.0143900 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
134803976-13019-DETAIL-03_25_2024-GO95HV-1^06147005.0144900 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
601102276-99079-DETAIL-03_25_2024-GO95MLD-1^06147005.0145900 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2027-03-25 | 2
337934225-11879-DETAIL-04_04_2024-CLRTOUCH-1^06147005.0147000 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
337934225-11879-DETAIL-04_04_2024-GO95MLD-1^06147005.0147000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
440857035-80579-DETAIL-04_04_2024-GO95MLD-1^06147005.0147003 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
547629276-42409-DETAIL-04_02_2024-GO95MLD-1^06147005.0147200 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
377810636-33709-DETAIL-03_28_2024-GO95TCH-1^06147005.0147700 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
547869936-7079-DETAIL-03_28_2024-GO95HV-1^06147005.0147701 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
14267670-77179-AUDIT-04_18_2024-GO95MLD-1^06147005.0147902 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2027-04-18 | 2
564086935-99199-DETAIL-04_04_2024-GO95MLD-1^06147005.0148000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2029-04-04 | 3
564086935-99199-DETAIL-04_04_2024-SVCROAD-1^06147005.0148000 | OTHER | CA-NON-TIER | Distribution | 2024-04-04 | 2027-04-04 | 2
139003006-26980-DETAIL-03_25_2024-GO95HV-1^06147005.0149902 | OTHER | CA-NON-TIER | Distribution | 2024-03-25 | 2029-03-25 | 3
312578218-78509-DETAIL-03_28_2024-GO95HV-1^06147005.0150900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
312578218-78509-DETAIL-03_28_2024-GO95MLD-1^06147005.0150900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
654363628-7799-DETAIL-03_28_2024-GO95MLD-1^06147005.0151900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
754041397-85479-DETAIL-04_03_2024-GO95MLD-1^06147005.0152002 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
981090928-21609-DETAIL-04_02_2024-GO95HV-1^06147005.0152902 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
625485088-16279-DETAIL-04_02_2024-GO95MLD-1^06147005.0153900 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
839142117-94079-DETAIL-04_03_2024-SVCROAD-1^06147005.0154001 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2027-04-03 | 2
943391628-88799-DETAIL-03_28_2024-GO95MLD-1^06147005.0156900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
319843248-57309-DETAIL-04_03_2024-GO95HV-1^06147005.0157004 | OTHER | CA-NON-TIER | Distribution | 2024-04-03 | 2029-04-03 | 3
633491479-50151-DETAIL-01_24_2023-GO95MLD-1^06147003.0129600 | OTHER | CA-NON-TIER | Distribution | 2023-01-24 | 2026-01-24 | 2
709793930-92551-DETAIL-01_26_2023-ABNDEQPM-1^06147003.0141100 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
709793930-92551-DETAIL-01_26_2023-GO95MLD-1^06147003.0141100 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
709793930-92551-DETAIL-01_26_2023-GO95MLD-2^06147003.0141100 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
334641180-28780-DETAIL-01_26_2023-CONDFRAY-1^06147003.0142100 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
548894450-91741-DETAIL-01_26_2023-GO95CL10-1^06147003.0142101 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
724350120-73191-DETAIL-01_26_2023-GUYSLACK-1^06147003.0142401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
735674140-13711-DETAIL-01_26_2023-GO95HV-1^06147003.0142502 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
54647700-69160-DETAIL-01_26_2023-GO95HV-1^06147003.0142504 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
197406300-73230-DETAIL-01_26_2023-GO95HV-1^06147003.0142600 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
549453100-83441-DETAIL-01_26_2023-GO95HV-1^06147003.0142601 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
934189650-71172-DETAIL-01_26_2023-ABNDEQPM-1^06147003.0143500 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
934189650-71172-DETAIL-01_26_2023-GRDRODHI-1^06147003.0143500 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
987352486-83486-DETAIL-01_26_2023-GO95MLD-1^06147003.0167901 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
987352486-83486-DETAIL-01_26_2023-GO95TCH-1^06147003.0167901 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
489952386-23386-DETAIL-01_26_2023-GO95HV-1^06147003.0168900 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
144923488-86780-DETAIL-01_30_2023-GO95MLD-1^06147003.0191000 | OTHER | CA-NON-TIER | Distribution | 2023-01-30 | 2026-01-30 | 2
214953930-5450-DETAIL-01_26_2023-GO95BLTC-1^06147003.0234500 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
214953930-5450-DETAIL-01_26_2023-GO95MLD-1^06147003.0234500 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
65878920-84180-DETAIL-01_26_2023-GO95CL10-1^06147003.0234600 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
65878920-84180-DETAIL-01_26_2023-GO95MLD-1^06147003.0234600 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2026-01-26 | 2
176947210-54720-DETAIL-01_26_2023-GO95HV-1^06147003.0234601 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
856816210-35182-DETAIL-01_26_2023-GO95HV-1^06147003.0235701 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
950454000-79623-DETAIL-01_26_2023-GO95HV-1^06147003.0235900 | OTHER | CA-NON-TIER | Distribution | 2023-01-26 | 2028-01-26 | 3
600505803-68511-DETAIL-02_02_2023-GO95HV-1^06148002.0337200 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
488387883-23161-DETAIL-02_02_2023-GO95HV-1^06148002.0337402 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
443594023-88501-DETAIL-02_02_2023-INSULDMG-1^06148002.0337601 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
152893203-67290-DETAIL-02_02_2023-GO95HV-1^06148002.0337700 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
77883994-55700-DETAIL-02_02_2023-XARMBRAC-1^06148002.0337901 | CROSSARM | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
642514763-81361-DETAIL-02_06_2023-GO95HV-1^06148002.0338001 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
391816441-65279-DETAIL-01_10_2023-GO95MLD-1^06148003.0139100 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
391816441-65279-DETAIL-01_10_2023-GO95MLD-2^06148003.0139100 | OTHER | CA-NON-TIER | Distribution | 2023-01-10 | 2026-01-10 | 2
771181821-85689-DTLSB-03_12_2018-ENCHRW-1^06148003.0139101 | OTHER | CA-NON-TIER | Distribution | 2018-03-12 | 2023-02-12 | 2
66905481-21789-DETAIL-01_09_2023-GO95MLD-1^06148003.0140301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
73225391-13079-DETAIL-01_09_2023-GO95HV-1^06148003.0140302 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
73225391-13079-DETAIL-01_09_2023-GO95MLD-1^06148003.0140302 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
858106579-36209-DETAIL-03_04_2024-GO95HV-1^06147004.0011200 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2029-03-04 | 3
493423119-7479-DETAIL-03_04_2024-GO95MLD-1^06147004.0011203 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
849368529-98109-DETAIL-03_06_2024-GO95HV-1^06147004.0011300 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
71526139-87209-DETAIL-03_04_2024-LIGHT-1^06147004.0011301 | CONNECTION DEVICE | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
841633039-49579-DETAIL-03_06_2024-GO95MLD-1^06147004.0011500 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
841633039-49579-DETAIL-03_06_2024-GO95TCH-1^06147004.0011500 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
970621159-41159-DETAIL-03_06_2024-GUYHINS-1^06147004.0011701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
267520049-15209-DETAIL-03_04_2024-RISEBKSP-1^06147004.0012301 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
83916059-35379-DETAIL-03_04_2024-GO95HV-1^06147004.0012901 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2029-03-04 | 3
615458223-39223-DETAIL-03_11_2024-GO95HV-1^06147004.0013901 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
615458223-39223-DETAIL-03_11_2024-GO95MLD-1^06147004.0013901 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
563620089-25299-DETAIL-03_11_2024-GO95MLD-1^06147004.0014900 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
554308039-74299-DETAIL-02_06_2019-SVCROAD-1^06147004.0014902 | OTHER | CA-NON-TIER | Distribution | 2019-02-06 | 2024-01-06 | 2
554308039-74299-DETAIL-03_11_2024-GO95HV-1^06147004.0014902 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
554308039-74299-DETAIL-03_11_2024-GO95MLD-1^06147004.0014902 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
345302649-56299-DETAIL-03_11_2024-GO95MLD-1^06147004.0014903 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
345302649-56299-DETAIL-03_11_2024-GO95TCH-1^06147004.0014903 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
184760860-22860-DETAIL-03_11_2024-GO95MLD-1^06147004.0014904 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
146463551-34551-DETAIL-03_04_2024-GO95MLD-1^06147004.0015202 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
228455369-24679-DETAIL-03_06_2024-GO95MLD-1^06147004.0017002 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
407499849-96109-DETAIL-03_04_2024-CONDFRAY-1^06147004.0017202 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
786592339-66109-ADMIN-03_04_2024-GO95TCH-1^06147004.0017300 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
786592339-66109-DETAIL-03_04_2024-SVCDEFLC-1^06147004.0017300 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
124963399-78389-DETAIL-03_06_2024-GO95HV-1^06147004.0017302 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
930545478-33262-ADMIN-07_10_2024-COPLLEAN-1^06147005.0162700 | POLE | CA-NON-TIER | Distribution | 2024-07-10 | 2027-07-10 | 2
206229578-42840-DETAIL-04_02_2024-GO95HV-1^06147005.0162800 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
987106977-86123-DETAIL-04_02_2024-GO95MLD-1^06147005.0162904 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
840017467-38999-DETAIL-04_10_2024-GO95HV-1^06147005.0163001 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
256080288-12990-DETAIL-04_02_2024-GO95MLD-1^06147005.0163900 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
256080288-12990-DETAIL-04_02_2024-SVCROAD-1^06147005.0163900 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
921011968-20009-DETAIL-04_10_2024-GO95MLD-1^06147005.0164001 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
926249477-2789-DETAIL-03_28_2024-GO95HV-1^06147005.0165900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
926249477-2789-DETAIL-03_28_2024-SVCROAD-1^06147005.0165900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
926249477-2789-AUDIT-04_10_2024-GO95MLD-1^06147005.0165900 | OTHER | CA-NON-TIER | Distribution | 2024-04-10 | 2029-04-10 | 3
634423478-13751-DETAIL-03_28_2024-SVCENTCO-1^06147005.0165901 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
223138010-6309-DETAIL-03_05_2024-GO95HV-1^06147004.0022003 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
447937261-93409-DETAIL-03_05_2024-GO95HV-1^06147004.0022300 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
382991271-26479-DETAIL-03_05_2024-GO95MLD-1^06147004.0022500 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
382991271-26479-DETAIL-03_05_2024-GUYHINS-1^06147004.0022500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
704254371-70279-DETAIL-03_04_2024-GO95MLD-1^06147004.0025200 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2029-03-04 | 3
13512760-74409-DETAIL-03_04_2024-XARMSPCR-1^06147004.0025201 | CROSSARM | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
511838870-33389-DETAIL-03_05_2024-GO95HV-1^06147004.0025400 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
363645500-78379-DETAIL-03_05_2024-CONDFRAY-1^06147004.0025900 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
363645500-78379-DETAIL-03_05_2024-GO95HV-1^06147004.0025900 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
510992750-11409-DETAIL-03_04_2024-GO95MLD-1^06147004.0027202 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
510992750-11409-DETAIL-03_04_2024-GO95TCH-1^06147004.0027202 | OTHER | CA-NON-TIER | Distribution | 2024-03-04 | 2027-03-04 | 2
290775021-5379-DETAIL-03_06_2024-GO95MLD-1^06147004.0027500 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
261435351-1779-DETAIL-03_06_2024-GO95MLD-1^06147004.0027501 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
235647630-2279-DETAIL-03_11_2024-GO95MLD-1^06147004.0027901 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
235647630-2279-DETAIL-03_11_2024-GO95TCH-1^06147004.0027901 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
364432770-19009-DETAIL-03_11_2024-GO95MLD-1^06147004.0028900 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
318292291-4989-DETAIL-03_11_2024-CLRTOUCH-1^06147004.0028902 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
318292291-4989-DETAIL-03_11_2024-GO95MLD-1^06147004.0028902 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
444715360-78009-DETAIL-03_11_2024-ENCHRW-1^06147004.0028903 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
296113901-28009-DETAIL-03_11_2024-GO95HV-1^06147004.0028904 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
296113901-28009-ADMIN-03_11_2024-GO95TCH-1^06147004.0028904 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
919057950-49009-DETAIL-03_11_2024-GO95MLD-1^06147004.0028905 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
981072861-37809-DETAIL-03_11_2024-GO95HV-1^06147004.0031801 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
747026481-72079-DETAIL-03_12_2024-GO95MLD-1^06147004.0032700 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
827636678-61582-DETAIL-03_28_2024-GO95MLD-1^06147005.0165902 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
827636678-61582-DETAIL-03_28_2024-INSULDMG-1^06147005.0165902 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
634100318-20651-DETAIL-04_02_2024-GO95HV-1^06147005.0166500 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
323542918-4870-DTLSB-02_18_2019-SVCDRIVE-1^06147005.0166502 | OTHER | CA-NON-TIER | Distribution | 2019-02-18 | 2024-01-18 | 2
323542918-4870-DETAIL-04_02_2024-GO95MLD-1^06147005.0166502 | OTHER | CA-NON-TIER | Distribution | 2024-04-02 | 2029-04-02 | 3
323542918-4870-DETAIL-04_02_2024-GUYHINS-1^06147005.0166502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-02 | 2027-04-02 | 2
580546697-26181-DETAIL-03_28_2024-GO95HV-1^06147005.0167900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
20301608-89140-DETAIL-03_28_2024-GO95MLD-1^06147005.0169900 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2027-03-28 | 2
40020358-31930-DETAIL-03_28_2024-GO95MLD-1^06147005.0169901 | OTHER | CA-NON-TIER | Distribution | 2024-03-28 | 2029-03-28 | 3
982044254-46309-DETAIL-03_06_2024-GO95MLD-1^06147005.0172800 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
644959524-67699-DETAIL-03_06_2024-GO95HV-1^06147005.0172902 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
529236294-57999-DETAIL-03_11_2024-GO95HV-1^06147005.0173000 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
822717841-77479-DETAIL-03_11_2024-GO95MLD-1^06147004.0049801 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
822717841-77479-DETAIL-03_11_2024-GRDRODHI-1^06147004.0049801 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
822717841-77479-DETAIL-03_11_2024-GRDRODHI-2^06147004.0049801 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2027-03-11 | 2
247765231-30579-DETAIL-03_12_2024-CLRTOUCH-1^06147004.0055200 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
247765231-30579-DETAIL-03_12_2024-GO95TCH-1^06147004.0055200 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
247765231-30579-DETAIL-03_12_2024-GUYHINS-1^06147004.0055200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
573217861-87879-DETAIL-03_12_2024-GO95MLD-1^06147004.0056801 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
706024681-21009-DETAIL-03_12_2024-INSULDMG-1^06147004.0056802 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
771029871-64912-ADMIN-03_27_2024-ABNDEQPM-1^06147004.0056902 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
301721291-92009-DETAIL-03_12_2024-CONDFRAY-1^06147004.0058800 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
706304711-16931-DETAIL-03_12_2024-GO95MLD-1^06147004.0059700 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
314527761-6860-DETAIL-03_12_2024-GO95HV-1^06147004.0059701 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2029-03-12 | 3
74787051-97400-DETAIL-03_12_2024-GO95HV-1^06147004.0061900 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2029-03-12 | 3
74787051-97400-DETAIL-03_12_2024-GO95MLD-1^06147004.0061900 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
506381461-87781-DETAIL-03_12_2024-SVCENTBK-1^06147004.0062900 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
506381461-87781-DETAIL-03_12_2024-SVCENTCO-1^06147004.0062900 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
935782651-97082-DETAIL-03_13_2024-GO95MLD-1^06147004.0070001 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
915613571-98192-AUDIT-04_15_2024-SVCROAD-1^06147004.0070100 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
233513731-81470-DETAIL-03_13_2024-GO95MLD-1^06147004.0070200 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
761592502-65381-DETAIL-03_13_2024-GO95MLD-1^06147004.0070201 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
969210691-76073-AUDIT-04_15_2024-SVCROAD-1^06147004.0070202 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
75231032-23679-DETAIL-03_12_2024-GO95MLD-1^06147004.0070701 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
75231032-23679-AUDIT-03_27_2024-SVCROAD-2^06147004.0070701 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2027-03-27 | 2
75231032-23679-AUDIT-04_15_2024-GRDRODHI-1^06147004.0070701 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
923764724-52532-DETAIL-02_09_2023-GO95MLD-1^06146004.0160900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
164830414-54210-DETAIL-02_09_2023-GO95MLD-1^06146004.0160901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
234920824-85170-DETAIL-02_09_2023-GO95MLD-1^06146004.0161900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
526515324-61311-DETAIL-02_09_2023-GO95HV-1^06146004.0161901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
526515324-61311-DETAIL-02_09_2023-GO95MLD-1^06146004.0161901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
344626024-72090-DETAIL-02_09_2023-GO95HV-1^06146004.0162900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
344626024-72090-DETAIL-02_09_2023-GO95MLD-1^06146004.0162900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
599653034-25911-DETAIL-02_09_2023-GO95MLD-1^06146004.0163901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
779473434-62032-DETAIL-02_09_2023-GO95MLD-1^06146004.0164900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
461605734-15521-DETAIL-02_09_2023-GO95MLD-1^06146004.0165900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
461605734-15521-DETAIL-02_09_2023-GRDRODHI-1^06146004.0165900 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
187644544-17330-DETAIL-02_09_2023-GO95MLD-1^06146004.0165901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
188668458-14009-DETAIL-02_23_2022-GO95HV-1^06146005.0046901 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
237377073-89209-DETAIL-02_23_2022-GO95HV-1^06146005.0098700 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
89984728-22909-DETAIL-02_28_2022-GO95HV-1^06146005.0106701 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
973342638-11909-DETAIL-02_28_2022-GO95HV-1^06146005.0107601 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
54952068-63909-DETAIL-02_28_2022-GO95HV-1^06146005.0108401 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
177342000-20020-DETAIL-03_03_2022-ABNDEQPM-1^06146005.0122000 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2027-03-03 | 3
177342000-20020-DETAIL-03_03_2022-GO95MLD-1^06146005.0122000 | OTHER | CA-NON-TIER | Distribution | 2022-03-03 | 2025-03-03 | 2
747092139-23139-DTLTRT-03_22_2022-GUYNOINS-1^06146005.0133004 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
226909423-76879-DTLSB-03_23_2022-CONDFRAY-1^06146005.0137100 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-03-23 | 2025-03-23 | 2
22220644-67950-DTLSB-03_22_2022-SVCROAD-1^06146005.0137202 | OTHER | CA-NON-TIER | Distribution | 2022-03-22 | 2025-03-22 | 2
326198103-67070-DTLSB-03_23_2022-ABNDEQPM-1^06146005.0137300 | OTHER | CA-NON-TIER | Distribution | 2022-03-23 | 2027-03-23 | 3
337645475-83319-DTLSB-03_21_2022-INSULDMG-1^06146005.0141901 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-21 | 2025-03-21 | 2
13866733-78679-DETAIL-04_14_2022-GO95HV-1^06146005.0153000 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
212371043-28050-DETAIL-04_14_2022-GO95HV-1^06146005.0153100 | OTHER | CA-NON-TIER | Distribution | 2022-04-14 | 2027-04-14 | 3
119717064-48289-DETAIL-02_24_2022-SVCROAD-1^06146005.0160100 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
807894671-59689-DETAIL-01_09_2023-GO95MLD-1^06148003.0141200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
807894671-59689-DETAIL-01_09_2023-GO95MLD-2^06148003.0141200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
867375851-97379-DETAIL-01_09_2023-GO95BLTC-1^06148003.0141300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2028-01-09 | 3
867375851-97379-DETAIL-01_09_2023-GO95TCH-1^06148003.0141300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
96516561-19689-DETAIL-01_09_2023-GO95MLD-1^06148003.0141301 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
885582501-80789-DETAIL-01_09_2023-GO95TCH-1^06148003.0142300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
143266651-61579-DETAIL-01_09_2023-GO95MLD-1^06148003.0143200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
143266651-61579-DETAIL-01_09_2023-GRDRODHI-1^06148003.0143200 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
428730061-77079-DETAIL-01_09_2023-GO95MLD-1^06148003.0143201 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
428730061-77079-DETAIL-01_09_2023-GRDRODHI-1^06148003.0143201 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
428730061-77079-DETAIL-01_09_2023-SVCCOMMD-1^06148003.0143201 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
665961991-10789-DETAIL-01_09_2023-GO95TCH-1^06148003.0143300 | OTHER | CA-NON-TIER | Distribution | 2023-01-09 | 2026-01-09 | 2
742649665-7731-DETAIL-02_21_2022-INSULDMG-1^06146005.0203800 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
420520065-99379-DETAIL-02_23_2022-GO95HV-1^06146005.0203801 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
420520065-99379-DETAIL-02_23_2022-GO95MLD-1^06146005.0203801 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2027-02-23 | 3
420520065-99379-DETAIL-02_23_2022-GRDRODHI-1^06146005.0203801 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
916684384-69302-DETAIL-02_21_2022-ANCHIDLE-1^06146005.0205601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
166110484-77810-AUDIT-04_04_2022-CUTOUTAR-1^06146005.0206700 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-04-04 | 2025-04-04 | 2
755744785-8071-DETAIL-02_21_2022-GO95HV-1^06146005.0207000 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
801858574-60892-DETAIL-02_28_2022-GO95HV-1^06146005.0207700 | OTHER | CA-NON-TIER | Distribution | 2022-02-28 | 2027-02-28 | 3
165330313-81510-DETAIL-02_24_2022-ABNDEQPM-1^06146005.0217700 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
191499973-46330-DTLSB-03_16_2022-GO95MLD-1^06146005.0221900 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
191499973-46330-DTLSB-03_16_2022-GRDRODHI-1^06146005.0221900 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
557442973-35151-DTLSB-03_16_2022-GUYSLACK-1^06146005.0221901 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-16 | 2025-03-16 | 2
116128464-35060-DTLSB-03_16_2022-ABNDEQPM-1^06146005.0222401 | OTHER | CA-NON-TIER | Distribution | 2022-03-16 | 2027-03-16 | 3
424659703-80779-DTLSB-03_17_2022-GO95BLTC-1^06146005.0222701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
424659703-80779-DTLSB-03_17_2022-GO95MLD-1^06146005.0222701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
424659703-80779-DTLSB-03_17_2022-GO95STUB-1^06146005.0222701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
424659703-80779-DTLSB-03_17_2022-GUYHINS-1^06146005.0222701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-17 | 2025-03-17 | 2
964711105-24363-DTLSB-03_17_2022-GO95HV-1^06146005.0240701 | OTHER | CA-NON-TIER | Distribution | 2022-03-17 | 2027-03-17 | 3
752791560-42309-DETAIL-03_21_2024-SVCENTCO-1^06147004.0117800 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
222545960-2309-DETAIL-03_21_2024-GO95HV-1^06147004.0118800 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
693562970-21279-DETAIL-03_21_2024-GO95MLD-1^06147004.0119700 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
693562970-21279-DETAIL-03_21_2024-GO95TCH-1^06147004.0119700 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
405837960-61309-DETAIL-03_21_2024-GO95HV-1^06147004.0119701 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
745431831-86279-DETAIL-03_06_2024-GO95MLD-1^06147004.0127800 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
745431831-86279-DETAIL-03_06_2024-GO95TCH-1^06147004.0127800 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
481425531-89499-DETAIL-03_07_2024-GUYNOINS-1^06147004.0129200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
776387069-57699-DETAIL-03_06_2024-GO95HV-1^06147004.0139301 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
597072959-75699-DETAIL-03_06_2024-GO95TCH-1^06147004.0139400 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
782711340-64742-DETAIL-03_13_2024-GO95HV-1^06147004.0180101 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2029-03-13 | 3
622855420-16331-DETAIL-03_13_2024-GO95MLD-1^06147004.0180700 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
948139574-79723-DETAIL-02_23_2022-GO95MLD-1^06146005.0285502 | OTHER | CA-NON-TIER | Distribution | 2022-02-23 | 2025-02-23 | 2
127917034-73999-DETAIL-02_24_2022-GO95HV-1^06146005.0289600 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
127917034-73999-DETAIL-02_24_2022-GO95MLD-1^06146005.0289600 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2025-02-24 | 2
528532224-7211-DETAIL-02_24_2022-GO95HV-1^06146005.0289602 | OTHER | CA-NON-TIER | Distribution | 2022-02-24 | 2027-02-24 | 3
665832024-71021-DETAIL-02_21_2022-GO95MLD-1^06146005.0297800 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
345586034-96690-DETAIL-02_21_2022-GRDRODHI-1^06146005.0297801 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
345586034-96690-DETAIL-02_21_2022-GRDRODHI-2^06146005.0297801 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
916139894-91792-DETAIL-02_21_2022-GO95HV-1^06146005.0297900 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2027-02-21 | 3
834242819-46919-DETAIL-02_21_2022-GO95MLD-1^06146005.0297901 | OTHER | CA-NON-TIER | Distribution | 2022-02-21 | 2025-02-21 | 2
256404770-80190-DETAIL-03_01_2022-SVCROAD-1^06146006.0052603 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
677159881-32251-DETAIL-03_01_2022-GO95MLD-1^06146006.0053401 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
677159881-32251-DETAIL-03_01_2022-GO95TCH-1^06146006.0053401 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
867678891-1222-DETAIL-03_07_2022-GO95MLD-1^06146006.0065400 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
339335331-24880-DETAIL-03_07_2022-GO95HV-1^06146006.0065502 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
813046020-26242-DETAIL-03_07_2022-ABNDEQPM-1^06146006.0066700 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
642107491-96961-DETAIL-03_08_2022-CUTOUTAR-1^06146006.0070902 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
714504861-11461-DETAIL-03_07_2022-GO95HV-1^06146006.0074501 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
761911310-8981-DETAIL-03_13_2024-GO95MLD-1^06147004.0180800 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
923455680-132-AUDIT-03_27_2024-GO95MLD-1^06147004.0180900 | OTHER | CA-NON-TIER | Distribution | 2024-03-27 | 2029-03-27 | 3
920411060-23122-DETAIL-03_13_2024-GO95HV-1^06147004.0180901 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2029-03-13 | 3
192837860-28930-DETAIL-03_13_2024-GUYHINS-1^06147004.0190400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
835571650-7812-DETAIL-03_13_2024-GO95MLD-1^06147004.0190500 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
837547890-39422-DETAIL-03_13_2024-GO95MLD-1^06147004.0190900 | OTHER | CA-NON-TIER | Distribution | 2024-03-13 | 2027-03-13 | 2
410699930-43899-DETAIL-03_07_2024-GO95MLD-1^06147004.0230501 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
410699930-43899-DETAIL-03_07_2024-GRDRODHI-1^06147004.0230501 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
757210700-77799-DETAIL-03_07_2024-INSULDMG-1^06147004.0238500 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-03-07 | 2027-03-07 | 2
373904599-99699-DETAIL-03_06_2024-GO95HV-1^06147004.0249601 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
995770913-46243-DETAIL-03_14_2024-GO95HV-1^06147004.0300901 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
923294513-25532-DETAIL-03_14_2024-GO95HV-1^06147004.0301700 | OTHER | CA-NON-TIER | Distribution | 2024-03-14 | 2029-03-14 | 3
135510969-26080-DETAIL-04_24_2024-GO95MLD-1^06145001.0089902 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
135510969-26080-DETAIL-04_24_2024-GRDRODHI-1^06145001.0089902 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
135510969-26080-DETAIL-04_24_2024-XARMSPCR-1^06145001.0089902 | CROSSARM | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
431742565-28480-DETAIL-04_24_2024-GO95HV-1^06145001.0090900 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
431742565-28480-DETAIL-04_24_2024-GO95MLD-1^06145001.0090900 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
419641825-42770-DETAIL-04_24_2024-GO95HV-1^06145001.0090901 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
410682629-11860-DETAIL-04_23_2024-GO95TCH-1^06145001.0112901 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
128882438-770-DETAIL-04_23_2024-GO95MLD-1^06145001.0113900 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
314182108-70579-DETAIL-04_22_2024-SVCROAD-1^06145001.0119100 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
802938998-94502-DETAIL-04_22_2024-GO95HV-1^06145001.0119101 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
111372398-92650-DETAIL-04_22_2024-GO95MLD-1^06145001.0119400 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
537713588-12621-DETAIL-04_22_2024-GO95HV-1^06145001.0119401 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
710486388-12651-DETAIL-04_22_2024-GO95MLD-1^06145001.0119601 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
743977178-78741-DETAIL-04_22_2024-GO95HV-1^06145001.0119801 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
435276478-82290-DETAIL-04_22_2024-GO95MLD-1^06145001.0119900 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
511804098-82891-DETAIL-04_16_2024-GO95MLD-1^06145001.0129000 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
140522598-41389-DETAIL-04_16_2024-GO95MLD-1^06145001.0129100 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
385934198-48330-DETAIL-04_16_2024-GO95MLD-1^06145001.0129200 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
172423198-66010-DETAIL-04_16_2024-GO95MLD-1^06145001.0129201 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
96863588-62030-DETAIL-04_16_2024-GO95MLD-1^06145001.0129300 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
544934648-13131-DETAIL-04_16_2024-GO95MLD-1^06145001.0129501 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
303308378-86940-DETAIL-04_16_2024-GO95MLD-1^06145001.0129503 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
394807678-7840-DETAIL-04_16_2024-GO95MLD-1^06145001.0129504 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
669613768-27431-DETAIL-04_16_2024-GO95MLD-1^06145001.0129700 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
786855541-80852-DETAIL-03_08_2022-CUTOUTAR-1^06146006.0076502 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2022-03-08 | 2025-03-08 | 2
221476260-6860-DETAIL-03_07_2022-GO95HV-1^06146006.0076801 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2027-03-07 | 3
107674680-15340-DETAIL-03_07_2022-ENCHRW-1^06146006.0076905 | OTHER | CA-NON-TIER | Distribution | 2022-03-07 | 2025-03-07 | 2
667362414-11514-DETAIL-03_01_2022-GO95BLTC-1^06146006.0092600 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2027-03-01 | 3
667362414-11514-DETAIL-03_01_2022-GO95MLD-1^06146006.0092600 | OTHER | CA-NON-TIER | Distribution | 2022-03-01 | 2025-03-01 | 2
664225708-54921-DETAIL-03_02_2022-GO95MLD-1^06146006.0186900 | OTHER | CA-NON-TIER | Distribution | 2022-03-02 | 2025-03-02 | 2
66133888-88380-DETAIL-03_08_2022-ABNDEQPM-1^06146006.0214402 | OTHER | CA-NON-TIER | Distribution | 2022-03-08 | 2027-03-08 | 3
833444519-46202-DETAIL-03_09_2022-GO95HV-1^06146006.0283701 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
675873371-61051-DETAIL-04_15_2024-GO95MLD-1^06145001.0139301 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
75136561-13700-DETAIL-04_15_2024-GO95MLD-1^06145001.0139501 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
2326751-23599-DETAIL-04_15_2024-GO95MLD-1^06145001.0139600 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
207519251-40640-DETAIL-04_15_2024-GO95MLD-1^06145001.0139601 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
691778951-71191-DETAIL-04_16_2024-GO95MLD-1^06145001.0139700 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
969712141-34973-DETAIL-04_16_2024-GO95MLD-1^06145001.0139800 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
167228241-21410-DETAIL-04_16_2024-GO95MLD-1^06145001.0139900 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
670522131-19231-DETAIL-04_16_2024-GO95MLD-1^06145001.0139901 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
933998095-779-DETAIL-04_18_2024-SVCENTCO-1^06145001.0144700 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2027-04-18 | 2
413228504-36360-DETAIL-04_18_2024-GO95MLD-1^06145001.0146701 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
943958774-60613-DETAIL-04_18_2024-GO95MLD-1^06145001.0148700 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
292179521-54230-DETAIL-04_18_2024-GO95MLD-1^06145001.0149401 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
895772611-28212-DETAIL-04_18_2024-GO95MLD-1^06145001.0149700 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
895772611-28212-DETAIL-04_18_2024-GO95TCH-1^06145001.0149700 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2027-04-18 | 2
891853374-5779-DETAIL-04_22_2024-GO95MLD-1^06145001.0149703 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
891853374-5779-DETAIL-04_22_2024-GRDRODHI-1^06145001.0149703 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
474350001-49641-DETAIL-04_22_2024-GO95MLD-1^06145001.0149900 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
43894121-2440-DETAIL-04_18_2024-GO95HV-1^06145001.0239400 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
345124901-38390-DETAIL-04_18_2024-GO95HV-1^06145001.0239901 | OTHER | CA-NON-TIER | Distribution | 2024-04-18 | 2029-04-18 | 3
393064171-11840-DETAIL-04_15_2024-GO95MLD-1^06145001.0246900 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
702584696-94696-DETAIL-04_15_2024-SVCENTCO-1^06145001.0246902 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
253909161-63890-DETAIL-04_15_2024-GO95MLD-1^06145001.0247900 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
66781791-26780-DETAIL-04_15_2024-GO95MLD-1^06145001.0249800 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
325415581-51770-DETAIL-04_15_2024-GO95MLD-1^06145001.0249801 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
833444519-46202-DETAIL-03_09_2022-GO95MLD-1^06146006.0283701 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
833444519-46202-DETAIL-03_09_2022-GUYHINS-1^06146006.0283701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
186409839-74820-DETAIL-03_09_2022-INSULDMG-1^06146006.0283801 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
950873389-1033-DETAIL-03_09_2022-GO95HV-1^06146006.0299700 | OTHER | CA-NON-TIER | Distribution | 2022-03-09 | 2027-03-09 | 3
950873389-1033-DETAIL-03_09_2022-GUYSLACK-1^06146006.0299700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-09 | 2025-03-09 | 2
648128480-20171-DETAIL-03_19_2015-SVCWIND-2^06147001.0060800 | OTHER | CA-NON-TIER | Distribution | 2015-03-19 | 2020-02-19 | 2
318366660-67260-ADMIN-01_11_2022-POLEDERP-1^06147001.0105400 | POLE | CA-NON-TIER | Distribution | 2022-01-11 | 2025-01-11 | 2
270478708-96210-ADMIN-01_11_2022-POLEDERP-1^06147001.0106500 | POLE | CA-NON-TIER | Distribution | 2022-01-11 | 2025-01-11 | 2
368031352-79310-DETAIL-02_08_2023-GO95HV-1^06145002.0047801 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2028-02-08 | 3
302470231-31540-DETAIL-04_15_2024-GO95MLD-1^06145002.0050600 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
958159521-91443-DETAIL-04_15_2024-GO95MLD-1^06145002.0052701 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
700157791-68311-DETAIL-04_16_2024-GO95MLD-1^06145002.0061002 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
540244221-16431-DETAIL-04_15_2024-GO95MLD-1^06145002.0061501 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
69433721-11990-DETAIL-04_15_2024-GO95MLD-1^06145002.0062500 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
159843421-91600-DETAIL-04_15_2024-GO95MLD-1^06145002.0062501 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
19065631-66640-DETAIL-04_15_2024-GO95MLD-1^06145002.0064600 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
618513231-28431-DETAIL-04_15_2024-GO95HV-1^06145002.0064601 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
618513231-28431-DETAIL-04_15_2024-GO95MLD-1^06145002.0064601 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
500936573-54673-DETAIL-04_15_2024-GO95MLD-1^06145002.0065602 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
500936573-54673-AUDIT-06_24_2024-ABNDEQPM-1^06145002.0065602 | OTHER | CA-NON-TIER | Distribution | 2024-06-24 | 2029-06-24 | 3
832761608-98702-DETAIL-04_23_2024-GO95HV-1^06145001.0028300 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
832761608-98702-DETAIL-04_23_2024-GO95MLD-1^06145001.0028300 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
758119568-62071-DETAIL-04_22_2024-GO95HV-1^06145001.0029000 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
758119568-62071-DETAIL-04_22_2024-GO95MLD-1^06145001.0029000 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
919610779-98712-DETAIL-04_22_2024-GO95MLD-1^06145001.0029302 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
140141658-74480-DETAIL-04_22_2024-GO95HV-1^06145001.0029304 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
261556308-44700-DETAIL-04_22_2024-GO95MLD-1^06145001.0029400 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
10233018-23669-DETAIL-04_22_2024-GO95MLD-1^06145001.0029501 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
80871128-28610-DETAIL-04_22_2024-GO95MLD-1^06145001.0029600 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
80871128-28610-DETAIL-04_22_2024-GRDRODHI-1^06145001.0029600 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
168682828-5210-DETAIL-04_22_2024-GO95HV-1^06145001.0029700 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
168682828-5210-DETAIL-04_22_2024-GO95MLD-1^06145001.0029700 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
266656341-9500-DETAIL-04_15_2024-GO95MLD-1^06145002.0066601 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
514906151-66491-DETAIL-04_15_2024-GO95MLD-1^06145002.0066900 | OTHER | CA-NON-TIER | Distribution | 2024-04-15 | 2029-04-15 | 3
184921131-50220-DETAIL-04_15_2024-GUYNOINS-1^06145002.0068700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-15 | 2027-04-15 | 2
559335161-18351-DETAIL-04_16_2024-GO95HV-1^06145002.0073500 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
943881671-82879-DETAIL-04_16_2024-GO95MLD-1^06145002.0075500 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
984081981-73813-DETAIL-04_16_2024-GO95HV-1^06145002.0078001 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
984081981-73813-DETAIL-04_16_2024-GO95MLD-1^06145002.0078001 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
789155371-26062-DETAIL-04_16_2024-GO95MLD-1^06145002.0180800 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
267040571-81700-DETAIL-04_16_2024-GO95HV-1^06145002.0181800 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
267040571-81700-DETAIL-04_16_2024-GO95MLD-1^06145002.0181800 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
590803871-57991-DETAIL-04_16_2024-GO95MLD-1^06145002.0182800 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
149136181-1090-DETAIL-04_16_2024-GO95MLD-1^06145002.0182801 | OTHER | CA-NON-TIER | Distribution | 2024-04-16 | 2029-04-16 | 3
580734283-15799-DETAIL-03_11_2024-GO95MLD-1^06147005.0178400 | OTHER | CA-NON-TIER | Distribution | 2024-03-11 | 2029-03-11 | 3
695005242-19209-DETAIL-03_05_2024-GO95MLD-1^06147005.0179100 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2027-03-05 | 2
840689613-15899-DETAIL-03_05_2024-GO95HV-1^06147005.0179201 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
111361260-2260-DETAIL-03_05_2024-GO95HV-1^06147005.0179401 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
154144233-21309-DETAIL-03_05_2024-GO95HV-1^06147005.0179602 | OTHER | CA-NON-TIER | Distribution | 2024-03-05 | 2029-03-05 | 3
741994823-93799-DETAIL-03_06_2024-GO95MLD-1^06147005.0179902 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2029-03-06 | 3
341449944-30699-DETAIL-03_21_2024-GO95HV-1^06147005.0184800 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
316351124-58599-ADMIN-03_21_2024-ABNDEQPM-1^06147005.0186600 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
316351124-58599-ADMIN-03_21_2024-CUTOUTAR-1^06147005.0186600 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
316351124-58599-DETAIL-03_21_2024-GO95MLD-1^06147005.0186600 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
415776454-31999-DETAIL-03_21_2024-GO95HV-1^06147005.0206700 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
415776454-31999-DETAIL-03_21_2024-GO95MLD-1^06147005.0206700 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
701805633-6979-DTLSB-03_31_2022-GO95MLD-1^06145006.0224500 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
862456369-10902-DETAIL-04_22_2024-GO95MLD-1^06146001.0359000 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
863743769-36002-DETAIL-04_22_2024-GO95HV-1^06146001.0359100 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
41444069-18830-DETAIL-04_22_2024-GO95MLD-1^06146001.0359101 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
818700959-47652-DETAIL-04_22_2024-GO95MLD-1^06146001.0360000 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
218028469-43050-DETAIL-04_22_2024-GO95MLD-1^06146001.0360001 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
368961379-77010-DETAIL-04_22_2024-GO95HV-1^06146001.0360200 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
368961379-77010-DETAIL-04_22_2024-GRDRODHI-1^06146001.0360200 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
360954055-97700-DETAIL-04_22_2024-GO95HV-1^06146001.0361001 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
360954055-97700-DETAIL-04_22_2024-GO95MLD-1^06146001.0361001 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
316208379-19860-DETAIL-04_22_2024-GO95MLD-1^06146001.0362001 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
192286799-79630-DETAIL-04_22_2024-INSULDMG-1^06146001.0364000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
864521598-12079-DRONE_HY-09_22_2023-GO95HV-1^668002/00 2/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-22 | 2028-09-22 | 3
823874069-80379-DRONE_HY-09_16_2023-GO95HV-1^668002/00 20/060 | OTHER | CA-TIER-2 | Transmission | 2023-09-16 | 2028-09-16 | 3
159863568-36079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 21/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
754234178-56079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 22/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
671267829-31130-DRONE_HY-09_25_2023-GO95HV-1^668002/00 5/060 | OTHER | CA-TIER-2 | Transmission | 2023-09-25 | 2028-09-25 | 3
114448991-70469-DETAIL-02_23_2023-GO95HV-1^668002/00 7/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
899823993-98469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 8/007 | CROSSARM | CA-NON-TIER | Transmission | 2023-09-12 | 2026-09-12 | 2
229239593-90069-DRONE_HY-09_14_2023-GO95HV-1^668002/00 8/020 | OTHER | FHCA | Transmission | 2023-09-14 | 2028-09-14 | 3
272561601-90469-DETAIL-02_23_2023-GO95HV-1^668002/00 8/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
148899671-44469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 9/006 | CROSSARM | CA-NON-TIER | Transmission | 2023-09-12 | 2028-09-12 | 3
148899671-44469-DRONE_HY-09_13_2023-EARMSPCR-1^668002/00 9/006 | OTHER | CA-NON-TIER | Transmission | 2023-09-13 | 2028-09-13 | 3
3345101-11469-DETAIL-02_23_2023-GO95HV-1^668002/00 9/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
53772211-1360-DTLSB-03_29_2022-GO95HV-1^06144006.0101900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
598992401-67311-DTLSB-03_29_2022-GO95MLD-1^06144006.0102900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
572781111-20271-DTLSB-03_29_2022-GO95HV-1^06144006.0105400 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
572781111-20271-DTLSB-03_29_2022-POLETOP-1^06144006.0105400 | POLE | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
528048551-29611-DTLSB-03_29_2022-GO95HV-1^06144006.0105900 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
563657981-67861-DTLSB-03_29_2022-GO95HV-1^06144006.0105901 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
889363851-32582-DTLSB-03_29_2022-GO95HV-1^06144006.0106901 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
220183391-42616-DTLSB-03_29_2022-GO95HV-1^06144006.0107902 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
220183391-42616-DTLSB-03_29_2022-INSULDMG-1^06144006.0107902 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
540585861-7731-ADMIN-02_09_2024-POLEREPL-1^06144006.0109901 | POLE | CA-NON-TIER | Distribution | 2024-02-09 | 2027-02-09 | 2
388254953-40740-DTLSB-03_28_2022-GO95HV-1^06144006.0153100 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
388254953-40740-ADMIN-02_09_2024-POLEREPL-1^06144006.0153100 | POLE | CA-NON-TIER | Distribution | 2024-02-09 | 2027-02-09 | 2
374998653-18920-DTLSB-03_28_2022-POLETOP-1^06144006.0153101 | POLE | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
374998653-18920-DTLSB-03_28_2022-XARMSPCR-1^06144006.0153101 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
173400443-74610-DTLSB-03_24_2022-GO95HV-1^06144006.0153201 | OTHER | CA-NON-TIER | Distribution | 2022-03-24 | 2027-03-24 | 3
989354109-45133-ADMIN-04_22_2024-ABNDEQPM-1^06146001.0365101 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
989354109-45133-DETAIL-04_22_2024-GO95MLD-1^06146001.0365101 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
621914244-15244-DETAIL-04_22_2024-GRDRODHI-1^06146001.0365203 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
750466244-76244-DETAIL-04_22_2024-GRDRODHI-1^06146001.0365204 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
157818539-62500-DETAIL-04_22_2024-GO95HV-1^06146001.0365301 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
355794939-81400-DETAIL-04_22_2024-GO95HV-1^06146001.0365400 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2029-04-22 | 3
391446341-35840-DETAIL-01_31_2023-GO95MLD-1^06146002.0035900 | OTHER | CA-NON-TIER | Distribution | 2023-01-31 | 2026-01-31 | 2
199260071-9240-DETAIL-02_01_2023-GO95HV-1^06146002.0062300 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
99062791-40240-DETAIL-02_01_2023-GO95HV-1^06146002.0072900 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
463720221-51431-DETAIL-02_01_2023-GO95HV-1^06146002.0074500 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
650109321-51981-DETAIL-02_01_2023-GO95MLD-1^06146002.0074600 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
599587531-13911-DETAIL-02_01_2023-GO95HV-1^06146002.0075301 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
451953852-95911-DTLSB-03_30_2022-GO95HV-1^06144006.0203900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
558574643-96751-DTLSB-03_30_2022-GO95HV-1^06144006.0205901 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
558574643-96751-DTLSB-03_30_2022-INSULDMG-1^06144006.0205901 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-30 | 2025-03-30 | 2
928531932-90152-DTLTRT-03_30_2022-GO95HV-1^06144006.0206900 | OTHER | CA-NON-TIER | Distribution | 2022-03-30 | 2027-03-30 | 3
310299003-44450-DTLSB-03_31_2022-GO95HV-1^06144006.0209000 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
339471823-87880-DTLSB-03_31_2022-GO95HV-1^06144006.0210000 | OTHER | CA-NON-TIER | Distribution | 2022-03-31 | 2027-03-31 | 3
981553763-81703-DTLSB-03_29_2022-GO95HV-1^06144006.0210401 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
39132663-9230-DTLSB-03_29_2022-GO95HV-1^06144006.0210500 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
930684673-8562-DTLSB-03_29_2022-GO95HV-1^06144006.0210600 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
93463683-2930-DTLSB-03_29_2022-GO95HV-1^06144006.0210700 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
289192173-24630-DTLSB-03_29_2022-XARMSPCR-1^06144006.0211900 | CROSSARM | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
350071523-29890-DTLSB-03_28_2022-POLETOP-1^06144006.0216900 | POLE | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
983151223-8903-DTLSB-03_28_2022-INSULDMG-1^06144006.0217900 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
380397813-17830-ADMIN-10_27_2023-POLEREPL-1^06144006.0218900 | POLE | CA-NON-TIER | Distribution | 2023-10-27 | 2026-10-27 | 2
71394683-51200-DTLSB-03_28_2022-GO95HV-1^06144006.0220901 | OTHER | CA-NON-TIER | Distribution | 2022-03-28 | 2027-03-28 | 3
71394683-51200-DTLSB-03_28_2022-GUYLOINS-1^06144006.0220901 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-03-28 | 2025-03-28 | 2
174234146-67210-DETAIL-02_06_2023-GO95TCH-1^06147002.0070000 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
45349666-55340-DETAIL-02_06_2023-GO95MLD-1^06147002.0070001 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
572933085-16271-DETAIL-02_07_2023-GO95HV-1^06147002.0094100 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
415386575-44960-DETAIL-02_07_2023-GO95HV-1^06147002.0095100 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
493223865-85661-DETAIL-02_07_2023-GO95HV-1^06147002.0096300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
129531055-74070-DETAIL-02_07_2023-GO95HV-1^06147002.0097300 | OTHER | CA-NON-TIER | Distribution | 2023-02-07 | 2028-02-07 | 3
312364171-8771-DETAIL-02_06_2023-GO95BLTC-1^06147002.0162100 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
768508151-1561-DETAIL-02_06_2023-GO95BLTC-1^06147002.0162101 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
378480644-63644-DETAIL-02_06_2023-GO95CL10-1^06147002.0162102 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
378480644-63644-DETAIL-02_06_2023-GO95MLD-1^06147002.0162102 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
8948796-20689-DETAIL-02_02_2023-GO95CL10-1^06147002.0172800 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
8948796-20689-DETAIL-02_02_2023-GO95MLD-1^06147002.0172800 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2026-02-02 | 2
208155693-42579-DTLSB-03_29_2022-GO95HV-1^06144006.0298701 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2027-03-29 | 3
208155693-42579-DTLSB-03_29_2022-GO95MLD-1^06144006.0298701 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
208155693-42579-DTLSB-03_29_2022-RISEGRD-1^06144006.0298701 | OTHER | CA-NON-TIER | Distribution | 2022-03-29 | 2025-03-29 | 2
208155693-42579-ADMIN-06_30_2023-POLEDERP-1^06144006.0298701 | POLE | CA-NON-TIER | Distribution | 2023-06-30 | 2026-06-30 | 2
717223581-59379-ADMIN-10_27_2022-POLEREPL-1^06144007.0313500 | POLE | CA-NON-TIER | Distribution | 2022-10-27 | 2025-10-27 | 2
745409608-78141-DETAIL-04_17_2024-GO95MLD-1^06145001.0010301 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
334765480-6480-DETAIL-04_22_2024-SVCDEFLC-1^06145001.0010500 | OTHER | CA-NON-TIER | Distribution | 2024-04-22 | 2027-04-22 | 2
184961918-31220-DETAIL-04_17_2024-GUYHINS-1^06145001.0011301 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-17 | 2027-04-17 | 2
892983992-31002-DETAIL-04_17_2024-GO95MLD-1^06145001.0012401 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
184560238-69920-DETAIL-04_17_2024-GO95HV-1^06145001.0013400 | OTHER | CA-NON-TIER | Distribution | 2024-04-17 | 2029-04-17 | 3
955586122-90243-DETAIL-02_08_2023-GO95MLD-1^06146002.0335301 | OTHER | CA-NON-TIER | Distribution | 2023-02-08 | 2026-02-08 | 2
516319123-60299-DETAIL-03_21_2024-GO95BLTC-1^06146004.0014400 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
516319123-60299-DETAIL-03_21_2024-GO95MLD-1^06146004.0014400 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2029-03-21 | 3
516319123-60299-DETAIL-03_21_2024-GRDRODHI-1^06146004.0014400 | OTHER | CA-NON-TIER | Distribution | 2024-03-21 | 2027-03-21 | 2
985911973-26913-DETAIL-02_09_2023-GO95MLD-1^06146004.0065100 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
401974173-24250-DETAIL-02_09_2023-GO95MLD-1^06146004.0065101 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
704395573-89631-DETAIL-02_09_2023-GO95MLD-1^06146004.0065201 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
164660373-8110-DETAIL-02_09_2023-GO95MLD-1^06146004.0065300 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
575924853-45671-DETAIL-02_09_2023-GO95MLD-1^06146004.0065400 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
514769363-31491-DETAIL-02_09_2023-GO95MLD-1^06146004.0065401 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
34438183-96930-DETAIL-02_09_2023-GO95MLD-1^06146004.0066000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
200633763-78840-DETAIL-02_09_2023-GO95MLD-1^06146004.0066700 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
637590628-56251-DETAIL-04_23_2024-GO95MLD-1^06145001.0023000 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
637590628-56251-DETAIL-04_23_2024-INSULDMG-1^06145001.0023000 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
923569928-58332-DETAIL-04_23_2024-GO95MLD-1^06145001.0023100 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
24911518-34770-DETAIL-04_23_2024-GO95MLD-1^06145001.0023101 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
883027069-55172-DETAIL-04_23_2024-GRDRODHI-1^06145001.0023204 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
392358568-14340-ADMIN-04_23_2024-ABNDEQPM-1^06145001.0023205 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
392358568-14340-DETAIL-04_23_2024-GO95HV-1^06145001.0023205 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
555093478-67651-DETAIL-04_23_2024-GO95MLD-1^06145001.0025201 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
914343688-17592-DETAIL-04_23_2024-GO95BLTC-1^06145001.0026304 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
914343688-17592-DETAIL-04_23_2024-GO95MLD-1^06145001.0026304 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
233636159-35470-DETAIL-04_23_2024-GO95MLD-1^06145001.0026600 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
233636159-35470-DETAIL-04_23_2024-GRDRODHI-1^06145001.0026600 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
418259079-95949-DETAIL-02_22_2024-SVCDEFLC-1^07216001.0352000 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
153840069-10759-DETAIL-02_22_2024-GO95HV-1^07216001.0352100 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
531456039-52759-DETAIL-02_22_2024-GO95MLD-1^07216001.0353300 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
308889539-99339-DETAIL-02_22_2024-GO95HV-1^07216001.0354302 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
308889539-99339-DETAIL-02_22_2024-GO95MLD-1^07216001.0354302 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
653594855-80359-DTLSB-02_14_2024-GO95MLD-1^07216002.0139200 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
681439044-79249-DTLSB-02_05_2024-GO95MLD-1^07216002.0248902 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
858042824-68259-DTLSB-02_05_2024-CLMBTRE-1^07216002.0249900 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
858042824-68259-DTLSB-02_05_2024-GO95HV-1^07216002.0249900 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2029-02-05 | 3
909674534-80159-DTLSB-02_05_2024-GO95HV-1^07216002.0249903 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2029-02-05 | 3
909674534-80159-DTLSB-02_05_2024-GO95MLD-1^07216002.0249903 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
909674534-80159-DTLSB-02_05_2024-GUYNOINS-1^07216002.0249903 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
292429438-59559-ADMIN-10_25_2023-EARMSPCR-1^07217001.0024401 | OTHER | CA-NON-TIER | Distribution | 2023-10-25 | 2026-10-25 | 2
21564181-76059-DETAIL-05_05_2022-COPLLEAN-1^07217001.0120500 | POLE | CA-NON-TIER | Distribution | 2022-05-05 | 2025-05-05 | 2
678148400-30733-ADMIN-11_08_2023-POLETOP-1^07217001.0151500 | POLE | CA-NON-TIER | Distribution | 2023-11-08 | 2026-11-08 | 2
706817522-10720-ADMIN-01_31_2024-SVCDEFLC-1^07217001.0156700 | OTHER | CA-NON-TIER | Distribution | 2024-01-31 | 2027-01-31 | 2
675722828-82828-ADMIN-12_29_2022-POLEREPL-1^07217001.0227040 | POLE | CA-NON-TIER | Distribution | 2022-12-29 | 2025-12-29 | 2
374873739-63159-DETAIL-05_03_2022-ANCPUCO-1^07217001.0247402 | ANCHOR/GUY | FHCA | Distribution | 2022-05-03 | 2025-05-03 | 2
757121563-38571-DETAIL-02_09_2023-GO95MLD-1^06146004.0066701 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
92130843-47030-DETAIL-02_09_2023-GO95MLD-1^06146004.0066800 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
343335043-31390-DETAIL-02_09_2023-GO95MLD-1^06146004.0067901 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
10128383-35469-DETAIL-02_09_2023-GO95HV-1^06146004.0076600 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
10128383-35469-DETAIL-02_09_2023-GO95MLD-1^06146004.0076600 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
529074763-63711-DETAIL-02_09_2023-GO95MLD-1^06146004.0076800 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
746174593-61841-DETAIL-02_09_2023-GO95MLD-1^06146004.0077200 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
353707103-100-DETAIL-02_09_2023-GO95MLD-1^06146004.0077300 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
744016303-71841-DETAIL-02_09_2023-GO95MLD-1^06146004.0077301 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
629655493-29241-DETAIL-02_09_2023-GO95MLD-1^06146004.0077400 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
153838793-6890-DETAIL-02_09_2023-GO95MLD-1^06146004.0077500 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
77524493-59500-DETAIL-02_09_2023-GO95MLD-1^06146004.0077601 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
374873739-63159-DETAIL-05_03_2022-GUYLOINS-1^07217001.0247402 | ANCHOR/GUY | FHCA | Distribution | 2022-05-03 | 2025-05-03 | 2
374873739-63159-DETAIL-05_03_2022-GUYNOINS-1^07217001.0247402 | ANCHOR/GUY | FHCA | Distribution | 2022-05-03 | 2025-05-03 | 2
374873739-63159-ADMIN-04_24_2024-POLEDERP-1^07217001.0247402 | POLE | FHCA | Distribution | 2024-04-24 | 2024-07-23 | 1
834370198-3823-ADMIN-06_24_2024-POLEDERP-1^07217001.0273801 | POLE | CA-NON-TIER | Distribution | 2024-06-24 | 2027-06-24 | 2
372753991-65991-ADMIN-08_04_2023-POLEREPL-1^07218001.0219500 | POLE | CA-NON-TIER | Distribution | 2023-08-04 | 2026-08-04 | 2
651479536-22109-DETAIL-02_02_2023-GO95HV-1^06147002.0175901 | OTHER | CA-NON-TIER | Distribution | 2023-02-02 | 2028-02-02 | 3
144879586-85079-DETAIL-02_06_2023-GO95MLD-1^06147002.0200200 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
54767466-44289-DETAIL-02_06_2023-GO95MLD-1^06147002.0200600 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
679530496-24361-DETAIL-02_06_2023-ABNDEQPM-1^06147002.0302200 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2028-02-06 | 3
679530496-24361-DETAIL-02_06_2023-GO95MLD-1^06147002.0302200 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
977293595-83393-DETAIL-02_01_2023-GO95MLD-1^06147002.0310000 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
644589296-55761-DETAIL-02_01_2023-XARMBRAC-1^06147002.0310500 | CROSSARM | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
821758906-87162-DETAIL-02_06_2023-GO95MLD-1^06147002.0318900 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
864535566-42902-DETAIL-02_06_2023-GO95MLD-1^06147002.0318901 | OTHER | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
765850756-21002-DETAIL-02_01_2023-GO95MLD-1^06147002.0319100 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2026-02-01 | 2
574269526-59571-DETAIL-02_01_2023-GO95HV-1^06147002.0319500 | OTHER | CA-NON-TIER | Distribution | 2023-02-01 | 2028-02-01 | 3
447349306-47501-DETAIL-02_06_2023-GUYSLACK-1^06147002.0319900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-06 | 2026-02-06 | 2
315211701-93342-DTLTRT-03_26_2024-POLEDERP-1^668044/00 5/060 | POLE | CA-TIER-2 | Transmission | 2024-03-26 | 2025-03-26 | 2
507808541-38081-DTLTRT-03_26_2024-POLEDERP-1^668044/00 6/061 | POLE | CA-TIER-2 | Transmission | 2024-03-26 | 2025-03-26 | 2
446464202-83039-ADMIN-09_03_2024-POLEDERP-1^668086/00 12/011 | POLE | CA-NON-TIER | Transmission | 2024-09-03 | 2027-09-03 | 2
486822711-53851-DRONE_HY-10_25_2023-GO95HV-1^668087/00 1/001 | OTHER | FHCA | Transmission | 2023-10-25 | 2028-10-25 | 3
165473418-72610-DRONE_HY-10_25_2023-GO95HV-1^668087/00 1/004 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
981634581-39803-DRONE_HY-10_25_2023-GO95HV-1^668087/00 1/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
304857745-50339-DRONE_HY-10_25_2023-GO95HV-1^668087/00 1/010 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
353690296-79000-DRONE_HY-10_25_2023-GO95HV-1^668087/00 1/011 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
438054198-32290-DRONE_HY-10_25_2023-GO95HV-1^668087/00 11/003 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
311771875-14450-DRONE_HY-10_25_2023-GO95HV-1^668087/00 11/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
565412845-87361-DETAIL-04_23_2024-GO95MLD-1^06145001.0035200 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
804243826-82202-DETAIL-04_23_2024-GO95HV-1^06145001.0035301 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
325978155-30070-DETAIL-04_23_2024-GO95MLD-1^06145001.0035302 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
979064536-42693-DETAIL-04_23_2024-GO95MLD-1^06145001.0035501 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
979064536-42693-DETAIL-04_23_2024-GRDRODHI-1^06145001.0035501 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
948433165-13223-DETAIL-04_23_2024-GO95MLD-1^06145001.0037100 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
82633895-29910-DETAIL-04_23_2024-GUYLOINS-1^06145001.0037200 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
700080326-64311-DETAIL-04_23_2024-SVCNEUT-1^06145001.0038200 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2027-04-23 | 2
109878802-7750-DETAIL-04_23_2024-GO95HV-1^06145001.0039200 | OTHER | CA-NON-TIER | Distribution | 2024-04-23 | 2029-04-23 | 3
597542535-55101-DETAIL-04_24_2024-GO95MLD-1^06145001.0042002 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
530417675-35811-DETAIL-04_24_2024-GO95HV-1^06145001.0043000 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
174317415-42310-DETAIL-04_24_2024-GO95HV-1^06145001.0043002 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
654854780-10139-ADMIN-04_21_2023-POLEREPL-1^668087/00 3/025 | POLE | CA-NON-TIER | Transmission | 2023-04-21 | 2026-04-21 | 2
582076058-44981-DRONE_HY-10_25_2023-GO95HV-1^668087/00 4/004 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
467925981-79739-DRONE_HY-10_25_2023-GO95HV-1^668087/00 4/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
415850221-19170-DRONE_HY-10_25_2023-GO95HV-1^668087/00 4/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
269886948-40010-DRONE_HY-10_25_2023-GO95HV-1^668087/00 5/003 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
319391489-67660-DRONE_HY-10_25_2023-GO95HV-1^668087/00 5/006 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
32922131-58420-DRONE_HY-10_25_2023-GO95HV-1^668087/00 5/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
5107135-52339-DRONE_HY-10_25_2023-GO95HV-1^668087/00 5/010 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
519996375-79401-DRONE_HY-10_25_2023-GUYSLACK-1^668087/00 5X/002 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-25 | 2026-10-25 | 2
14065267-7789-DRONE_HY-10_25_2023-GO95HV-1^668087/00 6/001 | OTHER | FHCA | Transmission | 2023-10-25 | 2028-10-25 | 3
253933341-48239-DRONE_HY-10_25_2023-GO95HV-1^668087/00 6/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
782839857-24942-DRONE_HY-10_25_2023-GO95HV-1^668087/00 7/001 | OTHER | FHCA | Transmission | 2023-10-25 | 2028-10-25 | 3
31333578-22439-DRONE_HY-10_25_2023-GUYSLACK-1^668087/00 7/003 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2023-10-25 | 2026-10-25 | 2
618406171-88239-DRONE_HY-10_25_2023-GO95HV-1^668087/00 7/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
480741445-67551-DRONE_HY-10_25_2023-GO95HV-1^668087/00 7/010 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
285760762-23208-DRONE_HY-10_25_2023-XARMSPCR-1^668087/00 7A/002 | CROSSARM | CA-NON-TIER | Transmission | 2023-10-25 | 2026-10-25 | 2
262503418-47200-DRONE_HY-10_25_2023-GO95HV-1^668087/00 8/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
957176979-32143-DRONE_HY-10_25_2023-GO95HV-1^668087/00 8/005 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
212529081-61839-DRONE_HY-10_25_2023-GO95HV-1^668087/00 8/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
524544865-12339-DRONE_HY-10_25_2023-GO95HV-1^668087/00 8/010 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
989459749-40849-ADMIN-08_14_2023-POLEREPL-1^668087/01 3/001 | POLE | CA-NON-TIER | Transmission | 2023-08-14 | 2026-08-14 | 2
79732681-85259-DETAIL-03_20_2023-ABNDEQPM-1^07118004.0020500 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2028-03-20 | 3
174317415-42310-DETAIL-04_24_2024-GO95MLD-1^06145001.0043002 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
174317415-42310-DETAIL-04_24_2024-GRDRODHI-1^06145001.0043002 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2027-04-24 | 2
528097795-30711-DETAIL-04_24_2024-GO95MLD-1^06145001.0044001 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
993865485-27943-DETAIL-04_24_2024-GO95MLD-1^06145001.0044101 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
864150405-49502-DETAIL-04_24_2024-GO95HV-1^06145001.0045000 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
424966115-62080-DETAIL-04_24_2024-GO95MLD-1^06145001.0047000 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
108062705-56640-DETAIL-04_24_2024-GO95HV-1^06145001.0047001 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
755696815-25071-DETAIL-04_24_2024-GO95HV-1^06145001.0048000 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
755696815-25071-DETAIL-04_24_2024-GO95MLD-1^06145001.0048000 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
695280809-21701-DETAIL-04_24_2024-GO95MLD-1^06145001.0051300 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
305224989-61250-DETAIL-04_24_2024-GO95HV-1^06145001.0052300 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
343737919-5590-DETAIL-04_24_2024-GO95MLD-1^06145001.0052301 | OTHER | CA-NON-TIER | Distribution | 2024-04-24 | 2029-04-24 | 3
918041336-14502-DRONE_HY-10_25_2023-GO95HV-1^668087/00 11/011 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
646826521-80839-DRONE_HY-10_25_2023-GO95HV-1^668087/00 12/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
154946346-77490-DRONE_HY-10_25_2023-GO95HV-1^668087/00 12/011 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
469661567-1439-DRONE_HY-10_25_2023-GO95HV-1^668087/00 13/001 | OTHER | FHCA | Transmission | 2023-10-25 | 2028-10-25 | 3
879179508-60752-DRONE_HY-10_25_2023-GO95HV-1^668087/00 13/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
422059105-89239-DRONE_HY-10_25_2023-GO95HV-1^668087/00 13/009 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
955278655-28733-DRONE_HY-10_25_2023-GO95HV-1^668087/00 13/010 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
962408341-41839-DRONE_HY-10_25_2023-GO95HV-1^668087/00 14/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
245128428-61980-DRONE_HY-10_25_2023-GO95HV-1^668087/00 15/002 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
347022598-23590-DRONE_HY-10_25_2023-GO95HV-1^668087/00 16/003 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
629244169-52739-DRONE_HY-10_25_2023-XARMSPCR-1^668087/00 16/005 | CROSSARM | CA-NON-TIER | Transmission | 2023-10-25 | 2026-10-25 | 2
202232561-24840-DRONE_HY-10_25_2023-GO95HV-1^668087/00 16/008 | OTHER | CA-NON-TIER | Transmission | 2023-10-25 | 2028-10-25 | 3
635304390-62249-DETAIL-02_27_2023-GO95MLD-1^07216001.0297807 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
635304390-62249-DETAIL-02_27_2023-SVCWIND-1^07216001.0297807 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
255867706-60339-DETAIL-02_27_2023-GO95MLD-1^07216001.0297808 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
255867706-60339-DETAIL-02_27_2023-SVCWIND-1^07216001.0297808 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
774038556-59049-DETAIL-02_27_2023-GO95HV-1^07216001.0297809 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
164164217-56217-DETAIL-02_27_2023-GO95MLD-1^07216001.0297810 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
313810864-63249-DETAIL-02_27_2023-GO95MLD-1^07216001.0297811 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
313810864-63249-DETAIL-02_27_2023-SVCNEUT-1^07216001.0297811 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
563998896-22839-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0297901 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
563998896-22839-DETAIL-02_23_2023-GO95CL10-1^07216001.0297901 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
291484906-4849-DETAIL-02_23_2023-GO95CL10-1^07216001.0297903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
291484906-4849-DETAIL-02_23_2023-SVCENTCO-1^07216001.0297903 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
63419495-48359-DETAIL-03_07_2023-GO95MLD-1^07216001.0298406 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
218771099-44450-DETAIL-02_28_2023-GO95MLD-1^07216001.0298501 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
833539094-21194-DETAIL-02_28_2023-GO95HV-1^07216001.0298504 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
833539094-21194-DETAIL-02_28_2023-GO95MLD-1^07216001.0298504 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
858379979-34349-DETAIL-02_28_2023-GO95HV-1^07216001.0298505 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
858379979-34349-DETAIL-02_28_2023-GO95MLD-1^07216001.0298505 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
188605489-96239-DETAIL-02_28_2023-GO95MLD-1^07216001.0298506 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
188605489-96239-DETAIL-02_28_2023-SVCENTCO-1^07216001.0298506 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
828675069-17449-DETAIL-02_28_2023-GO95MLD-1^07216001.0298508 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
390942439-73349-DETAIL-03_06_2023-GO95MLD-1^07216001.0298509 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
145462279-47249-DETAIL-03_02_2023-GO95TCH-1^07216001.0298600 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
804627468-20168-DETAIL-02_28_2023-GO95MLD-1^07216001.0298601 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
804627468-20168-DETAIL-02_28_2023-GUYHINS-1^07216001.0298601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
746701568-12568-DETAIL-02_28_2023-GO95MLD-1^07216001.0298603 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
746701568-12568-DETAIL-02_28_2023-GUYHINS-1^07216001.0298603 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
746701568-12568-DETAIL-02_28_2023-GUYHINS-2^07216001.0298603 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
450306309-19939-DETAIL-02_28_2023-GO95MLD-1^07216001.0298604 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
812279609-89049-DETAIL-02_28_2023-CLRTOUCH-1^07216001.0298605 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
812279609-89049-DETAIL-02_28_2023-GO95MLD-1^07216001.0298605 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
785350468-22468-DETAIL-02_28_2023-CLRTOUCH-1^07216001.0298606 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
785350468-22468-DETAIL-02_28_2023-GO95MLD-1^07216001.0298606 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
785350468-22468-DETAIL-02_28_2023-GUYHINS-1^07216001.0298606 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
569075719-38249-DETAIL-02_28_2023-GO95HV-1^07216001.0298607 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
569075719-38249-DETAIL-02_28_2023-GO95MLD-1^07216001.0298607 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
486856056-96650-DTLTRT-10_01_2020-GO95HV-1^668018/00 11/001 | OTHER | CA-TIER-2 | Transmission | 2020-10-01 | 2025-10-01 | 3
725004818-91860-DTLTRT-09_30_2020-GO95HV-1^668018/00 11/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
725004818-91860-ADMIN-08_27_2024-POLEREPL-1^668018/00 11/002 | POLE | CA-TIER-2 | Transmission | 2024-08-27 | 2025-08-27 | 2
946379528-23860-DTLTRT-09_30_2020-GO95HV-1^668018/00 12/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
946379528-23860-ADMIN-08_28_2024-POLEREPL-1^668018/00 12/002 | POLE | CA-TIER-2 | Transmission | 2024-08-28 | 2025-08-28 | 2
36843439-61679-DETAIL-09_29_2020-GO95HV-1^668018/00 12/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
609110749-37770-DETAIL-09_29_2020-GO95HV-1^668018/00 13/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
905731499-32970-DTLTRT-09_29_2020-GO95HV-1^668018/00 16/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
125987169-62870-DTLTRT-09_29_2020-GO95HV-1^668018/00 16/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
107576178-54609-DTLTRT-09_30_2020-GO95HV-1^668018/00 2/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
192941739-1000-DTLTRT-09_29_2020-ANCHIDLE-1^668018/00 2/005 | ANCHOR/GUY | CA-TIER-2 | Transmission | 2020-09-29 | 2023-09-29 | 2
510533138-74138-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0298707 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
510533138-74138-DETAIL-02_28_2023-SVCWIND-1^07216001.0298707 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
222615328-65558-DETAIL-02_28_2023-SVCWIND-1^07216001.0298740 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
449399538-79639-DETAIL-02_28_2023-GO95TCH-1^07216001.0298742 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
242070466-78049-DETAIL-02_28_2023-GO95MLD-1^07216001.0298800 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
242070466-78049-DETAIL-02_28_2023-GO95TCH-1^07216001.0298800 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
944363512-93389-DETAIL-02_27_2023-GO95HV-1^07216001.0298801 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
944363512-93389-DETAIL-02_27_2023-GO95MLD-1^07216001.0298801 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
452971556-32459-DETAIL-02_27_2023-CLRTOPOL-1^07216001.0298802 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
452971556-32459-DETAIL-02_27_2023-GO95MLD-1^07216001.0298802 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
881270005-76849-DETAIL-02_27_2023-SVCENTCO-1^07216001.0298804 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
226046686-49639-DETAIL-02_27_2023-GO95MLD-1^07216001.0298805 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
226046686-49639-DETAIL-02_27_2023-GUYHINS-1^07216001.0298805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
226046686-49639-DETAIL-02_27_2023-GUYHINS-2^07216001.0298805 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
226046686-49639-DETAIL-02_27_2023-SVCWIND-1^07216001.0298805 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
809597945-18039-DETAIL-02_27_2023-GO95MLD-1^07216001.0298806 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
809597945-18039-DETAIL-02_27_2023-SVCWIND-1^07216001.0298806 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
564826093-47038-DETAIL-02_23_2023-CLRTOUCH-1^07216001.0298808 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
564826093-47038-DETAIL-02_23_2023-GO95MLD-1^07216001.0298808 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
471183193-55193-DETAIL-02_23_2023-GO95MLD-1^07216001.0298809 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
437151346-55349-DETAIL-02_23_2023-GO95MLD-1^07216001.0298810 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
437151346-55349-DETAIL-02_23_2023-GO95TCH-1^07216001.0298810 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
131514982-15982-DETAIL-02_27_2023-GO95TCH-1^07216001.0298811 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
192941739-1000-DTLTRT-09_29_2020-GO95HV-1^668018/00 2/005 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
968216199-14000-DETAIL-09_29_2020-GO95HV-1^668018/00 2/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
968216199-72879-DETAIL-09_29_2020-GO95HV-1^668018/00 2/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
632580298-66390-DTLTRT-09_30_2020-GO95HV-1^668018/00 3/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
875477510-68870-DTLTRT-09_29_2020-GO95HV-1^668018/00 4/007 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
250146279-35520-DTLTRT-09_30_2020-GO95HV-1^668018/00 5/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
250146279-74520-DTLTRT-09_30_2020-GO95HV-1^668018/00 5/004 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
346078518-43170-DTLTRT-09_30_2020-GO95HV-1^668018/00 6/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
233481279-95670-DETAIL-09_29_2020-GO95HV-1^668018/00 6/006 | OTHER | CA-TIER-2 | Transmission | 2020-09-29 | 2025-09-29 | 3
364780888-28870-DTLTRT-09_30_2020-GO95HV-1^668018/00 7/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
944267718-4170-DTLTRT-09_30_2020-GO95HV-1^668018/00 7/003 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
260352998-76760-DTLTRT-09_30_2020-GO95HV-1^668018/00 8/002 | OTHER | CA-TIER-2 | Transmission | 2020-09-30 | 2025-09-30 | 3
349608800-24690-DETAIL-02_23_2023-GO95MLD-1^07216001.0298909 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
349608800-24690-DETAIL-02_23_2023-SVCNEUT-1^07216001.0298909 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
349608800-24690-AUDIT-03_06_2023-SVCRUBLG-1^07216001.0298909 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
303650029-10449-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299400 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
303650029-10449-DETAIL-02_28_2023-GO95HV-1^07216001.0299400 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
303650029-10449-DETAIL-02_28_2023-GO95MLD-1^07216001.0299400 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
396489119-56849-DETAIL-02_28_2023-GO95MLD-1^07216001.0299500 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
553652259-31239-DETAIL-02_28_2023-GO95HV-1^07216001.0299600 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
553652259-31239-DETAIL-02_28_2023-GO95MLD-1^07216001.0299600 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
553652259-31239-DETAIL-02_28_2023-GO95TCH-1^07216001.0299600 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
822334889-90639-DETAIL-02_28_2023-GO95MLD-1^07216001.0299601 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
822334889-90639-DETAIL-02_28_2023-GO95MLD-2^07216001.0299601 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
751216829-25039-DETAIL-02_28_2023-GO95HV-1^07216001.0299602 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
751216829-25039-DETAIL-02_28_2023-GO95MLD-1^07216001.0299602 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
439709434-40534-DETAIL-02_23_2023-GO95MLD-1^07216001.0299604 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
660057518-37049-DETAIL-02_28_2023-GO95HV-1^07216001.0299605 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
660057518-37049-DETAIL-02_28_2023-GO95MLD-1^07216001.0299605 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
660057518-37049-DETAIL-02_28_2023-SVCNEUT-1^07216001.0299605 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
464391899-87649-DETAIL-02_28_2023-GO95MLD-1^07216001.0299607 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
656174001-53301-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299700 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
928729426-60849-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
928729426-60849-DETAIL-02_28_2023-GO95MLD-1^07216001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
928729426-60849-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
559582561-85139-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299702 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
267304143-78800-DETAIL-02_09_2023-GO95MLD-1^06146004.0084000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
824982243-68282-DETAIL-02_09_2023-GO95MLD-1^06146004.0085000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
424907943-50080-DETAIL-02_09_2023-GO95MLD-1^06146004.0085002 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
424907943-50080-DETAIL-02_09_2023-INSULDMG-1^06146004.0085002 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
718231143-62471-DETAIL-02_09_2023-GO95MLD-1^06146004.0086000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
718231143-62471-DETAIL-02_09_2023-GO95MLD-2^06146004.0086000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
344253653-20990-DETAIL-02_09_2023-GO95MLD-1^06146004.0087000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
275728353-63410-DETAIL-02_09_2023-GO95MLD-1^06146004.0088000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
56185653-6360-DETAIL-02_09_2023-GO95MLD-1^06146004.0089000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
498488633-89171-DETAIL-02_09_2023-GO95CL10-1^06146004.0101000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2028-02-09 | 3
498488633-89171-DETAIL-02_09_2023-GO95MLD-1^06146004.0101000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
498488633-89171-DETAIL-02_09_2023-GO95TCH-1^06146004.0101000 | OTHER | CA-NON-TIER | Distribution | 2023-02-09 | 2026-02-09 | 2
454627277-78277-DETAIL-03_08_2023-GO95MLD-1^07216001.0295305 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
454627277-78277-DETAIL-03_08_2023-GUYSLACK-1^07216001.0295305 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
352793095-70559-DETAIL-03_09_2023-GO95MLD-1^07216001.0295306 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
578096337-46559-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295307 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
69561148-94110-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295343 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
668605455-82449-DETAIL-03_13_2023-GO95MLD-1^07216001.0295400 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
144614035-52239-DETAIL-03_13_2023-SVCENTCO-1^07216001.0295401 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
144614035-52239-DETAIL-03_13_2023-SVCWIND-1^07216001.0295401 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
920719815-60939-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0295402 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
146744478-94478-DETAIL-03_07_2023-GO95CL10-1^07216001.0295403 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
146744478-94478-DETAIL-03_07_2023-SVCWIND-1^07216001.0295403 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
504479365-22449-DETAIL-03_09_2023-GO95MLD-1^07216001.0295404 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
504479365-22449-DETAIL-03_09_2023-SVCWIND-1^07216001.0295404 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
611751080-21559-DETAIL-03_09_2023-GO95MLD-1^07216001.0295405 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
205818365-72749-DETAIL-03_09_2023-GO95HV-1^07216001.0295406 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
205818365-72749-DETAIL-03_09_2023-GO95MLD-1^07216001.0295406 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
205818365-72749-DETAIL-03_09_2023-SVCENTBK-1^07216001.0295406 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
939948028-74731-DETAIL-03_09_2023-SVCENTBK-1^07216001.0295440 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
638530575-7039-DETAIL-03_09_2023-GO95HV-1^07216001.0295500 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
638530575-7039-DETAIL-03_09_2023-GO95MLD-1^07216001.0295500 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
638530575-7039-DETAIL-03_09_2023-GUYHINS-1^07216001.0295500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
703546070-9249-DETAIL-03_09_2023-GUYHINS-1^07216001.0295501 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
703546070-9249-DETAIL-03_09_2023-SVCWIND-1^07216001.0295501 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
440289785-90139-DETAIL-03_09_2023-GUYHINS-1^07216001.0295502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
991808058-6668-DETAIL-02_28_2023-GO95MLD-1^07216001.0299802 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
991808058-6668-DETAIL-02_28_2023-GRDRODHI-1^07216001.0299802 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
641272135-90349-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299803 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
641272135-90349-DETAIL-02_28_2023-GO95HV-1^07216001.0299803 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
641272135-90349-DETAIL-02_28_2023-GO95MLD-1^07216001.0299803 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
641272135-90349-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299803 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
485607465-60349-DETAIL-02_28_2023-GO95HV-1^07216001.0299804 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2028-02-28 | 3
481620293-51293-DETAIL-02_23_2023-GO95MLD-1^07216001.0299807 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
732782415-74415-DETAIL-02_28_2023-GO95MLD-1^07216001.0299808 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
425750624-20939-DTLSB-02_08_2024-GO95MLD-1^07216001.0306901 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
985909784-37839-DTLSB-02_08_2024-GO95HV-1^07216001.0307800 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2029-02-08 | 3
985909784-37839-DTLSB-02_08_2024-GO95MLD-1^07216001.0307800 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
548484453-76939-DETAIL-03_08_2023-GO95MLD-1^07216001.0295600 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
411432436-89739-AUDIT-03_06_2023-GUYHINS-1^07216001.0295601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
411432436-89739-DETAIL-03_08_2023-GO95TCH-1^07216001.0295601 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
2155446-37249-DETAIL-03_08_2023-GO95TCH-1^07216001.0295605 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
720372751-65559-DETAIL-02_27_2023-GO95MLD-1^07216001.0295606 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
562419431-34531-DETAIL-02_27_2023-SVCROAD-1^07216001.0295640 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
268186317-29317-DETAIL-02_27_2023-GO95MLD-1^07216001.0295701 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
268186317-29317-DETAIL-02_27_2023-GO95TCH-1^07216001.0295701 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
268186317-29317-DETAIL-02_27_2023-SVCWIND-1^07216001.0295701 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
175245981-53749-DETAIL-02_27_2023-GO95MLD-1^07216001.0295702 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
649282233-14639-DETAIL-02_27_2023-GO95MLD-1^07216001.0295703 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
649282233-14639-DETAIL-02_27_2023-GO95MLD-2^07216001.0295703 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
450303289-64289-DETAIL-02_23_2023-GO95MLD-1^07216001.0295705 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
732125390-30311-DETAIL-02_23_2023-GO95HV-1^07216001.0295706 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2028-02-23 | 3
732125390-30311-DETAIL-02_23_2023-GO95MLD-1^07216001.0295706 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
732125390-30311-DETAIL-02_23_2023-GRDRODHI-1^07216001.0295706 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
56634246-11760-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0295707 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
56634246-11760-DETAIL-02_23_2023-GO95MLD-1^07216001.0295707 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
406879366-60449-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0295708 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
406879366-60449-DETAIL-02_23_2023-GO95MLD-1^07216001.0295708 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
282785936-44359-DETAIL-02_23_2023-GO95MLD-1^07216001.0295801 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
333923871-96249-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0295802 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
333923871-96249-DETAIL-03_06_2023-GO95MLD-1^07216001.0295802 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
468220828-79943-DETAIL-03_06_2023-SVCENTBK-1^07216001.0295840 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
878390184-67859-DTLSB-02_06_2024-GO95MLD-1^07216001.0307801 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
878390184-67859-DTLSB-02_06_2024-GUYLOINS-1^07216001.0307801 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
851147414-89939-DTLSB-02_06_2024-SVCNEUT-1^07216001.0307900 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
163842025-47859-DTLSB-02_06_2024-SVCENTBK-1^07216001.0307902 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
356936294-20139-DTLSB-02_06_2024-GO95MLD-1^07216001.0307903 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
909406561-66248-DTLSB-02_08_2024-SVCWIND-1^07216001.0307905 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
362580034-15749-DTLSB-02_08_2024-GO95MLD-1^07216001.0307907 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
118894064-21849-DTLSB-02_06_2024-SVCDEFLC-1^07216001.0308700 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
592233254-73839-DTLSB-02_06_2024-GO95MLD-1^07216001.0308801 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
592233254-73839-DTLSB-02_06_2024-GRDRODHI-1^07216001.0308801 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
435225684-93749-DTLSB-02_06_2024-GO95MLD-1^07216001.0308802 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
435225684-93749-DTLSB-02_06_2024-SVCDEFLC-1^07216001.0308802 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
292361035-13139-DETAIL-03_02_2023-GO95MLD-1^07216001.0295908 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
292361035-13139-DETAIL-03_02_2023-GUYHINS-1^07216001.0295908 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
801933528-30124-DETAIL-03_06_2023-SVCENTBK-1^07216001.0295941 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
601422425-96011-DETAIL-03_07_2023-GO95MLD-1^07216001.0296100 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
246782895-50459-DETAIL-03_07_2023-GO95HV-1^07216001.0296300 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
364320095-5239-DETAIL-03_07_2023-GO95MLD-1^07216001.0296301 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
388208695-90459-DETAIL-03_07_2023-GO95MLD-1^07216001.0296302 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
796460515-3639-DETAIL-03_07_2023-GO95MLD-1^07216001.0296303 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
830387435-5539-DETAIL-03_08_2023-GO95MLD-1^07216001.0296304 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
830387435-5539-DETAIL-03_08_2023-GO95TCH-1^07216001.0296304 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
738938015-53449-DETAIL-03_08_2023-GO95MLD-1^07216001.0296305 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
438065885-82549-DETAIL-03_08_2023-SVCNEUT-1^07216001.0296400 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
438065885-82549-DETAIL-03_08_2023-SVCWIND-1^07216001.0296400 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
552412425-58839-DETAIL-03_08_2023-GO95MLD-1^07216001.0296401 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
552412425-58839-DETAIL-03_08_2023-SVCNEUT-1^07216001.0296401 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
884619735-17939-DETAIL-03_08_2023-GO95MLD-1^07216001.0296402 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
698588078-14749-DETAIL-03_09_2023-GO95MLD-1^07216001.0296403 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
698588078-14749-DETAIL-03_09_2023-GO95TCH-1^07216001.0296403 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
103334665-63139-DETAIL-03_09_2023-GO95MLD-1^07216001.0296404 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
465286455-15649-DETAIL-03_09_2023-GO95MLD-1^07216001.0296405 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
31224770-85649-DETAIL-03_08_2023-GO95MLD-1^07216001.0296407 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
875232135-13449-DETAIL-03_08_2023-GO95MLD-1^07216001.0296408 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
875232135-13449-DETAIL-03_08_2023-GUYLOINS-1^07216001.0296408 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
675766486-16768-DETAIL-03_08_2023-GO95MLD-1^07216001.0296409 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
881946201-18369-DRONE_HY-09_21_2023-GO95HV-1^668002/00 10/069 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
396876381-5469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 11/006 | CROSSARM | CA-NON-TIER | Transmission | 2023-09-12 | 2028-09-12 | 3
396876381-5469-DRONE_HY-09_13_2023-EARMSPCR-1^668002/00 11/006 | OTHER | CA-NON-TIER | Transmission | 2023-09-13 | 2028-09-13 | 3
910207911-91469-DETAIL-02_23_2023-GO95HV-1^668002/00 12/030 | OTHER | CA-TIER-2 | Transmission | 2023-02-23 | 2028-02-23 | 3
945072849-96069-DRONE_HY-09_14_2023-GO95HV-1^668002/00 14/042 | OTHER | CA-TIER-2 | Transmission | 2023-09-14 | 2028-09-14 | 3
274323368-64079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 14/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
879822212-16469-DRONE_HY-09_12_2023-POLETOP-1^668002/00 15/006 | POLE | CA-NON-TIER | Transmission | 2023-09-12 | 2028-09-12 | 3
580752329-12669-DRONE_HY-09_14_2023-GO95HV-1^668002/00 15/039 | OTHER | CA-TIER-2 | Transmission | 2023-09-14 | 2028-09-14 | 3
563779128-35079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 17/075 | OTHER | CA-TIER-2 | Transmission | 2023-09-21 | 2028-09-21 | 3
964754271-97369-DETAIL-03_09_2023-GO95HV-1^668002/00 18/004 | OTHER | FHCA | Transmission | 2023-03-09 | 2028-03-09 | 3
793208429-61630-DRONE_HY-09_13_2023-GO95HV-1^668002/00 18/060 | OTHER | CA-TIER-2 | Transmission | 2023-09-13 | 2028-09-13 | 3
100751181-58369-DETAIL-03_09_2023-GO95HV-1^668002/00 19/004 | OTHER | FHCA | Transmission | 2023-03-09 | 2028-03-09 | 3
124997486-42270-DETAIL-02_27_2023-GO95MLD-1^07216001.0296700 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
782596386-5359-DETAIL-02_27_2023-GO95HV-1^07216001.0296702 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
782596386-5359-DETAIL-02_27_2023-SVCWIND-1^07216001.0296702 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
86462896-249-DETAIL-03_06_2023-GO95MLD-1^07216001.0296705 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
82750425-71239-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0296706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
82750425-71239-DETAIL-03_06_2023-SVCENTCO-1^07216001.0296706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
423706611-55670-DETAIL-02_27_2023-GO95MLD-1^07216001.0296708 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
423706611-55670-DETAIL-02_27_2023-RISESTRP-1^07216001.0296708 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
423706611-55670-DETAIL-02_27_2023-RISESTRP-2^07216001.0296708 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
53271526-82249-DETAIL-02_27_2023-GO95HV-1^07216001.0296800 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
53271526-82249-DETAIL-02_27_2023-GO95MLD-1^07216001.0296800 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
141355326-89239-DETAIL-03_06_2023-GO95HV-1^07216001.0296801 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
141355326-89239-DETAIL-03_06_2023-GO95MLD-1^07216001.0296801 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
692201718-73718-DETAIL-03_06_2023-GO95CL10-1^07216001.0296803 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
692201718-73718-DETAIL-03_06_2023-GO95MLD-1^07216001.0296803 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
692201718-73718-DETAIL-03_06_2023-SVCENTCO-1^07216001.0296803 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
162767036-85100-DETAIL-02_23_2023-GO95MLD-1^07216001.0296805 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
820043616-79662-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0296807 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
820043616-79662-DETAIL-03_06_2023-GO95MLD-1^07216001.0296807 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
406757318-95753-DETAIL-02_27_2023-GO95TCH-1^07216001.0296843 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
406757318-95753-DETAIL-02_27_2023-SVCENTBK-1^07216001.0296843 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
273647412-89412-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0296901 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
761019800-84349-DETAIL-02_23_2023-GO95MLD-1^07216001.0296904 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
761019800-84349-DETAIL-02_23_2023-SVCENTCO-1^07216001.0296904 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
484229379-87459-DETAIL-03_01_2023-SVCWIND-1^07216001.0291840 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
484229379-87459-DETAIL-03_01_2023-SVCWIND-2^07216001.0291840 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
591445659-90759-DETAIL-03_02_2023-CLRTOPOL-1^07216001.0291902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
591445659-90759-DETAIL-03_02_2023-GO95MLD-1^07216001.0291902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
555749845-99459-DETAIL-03_02_2023-GO95HV-1^07216001.0291903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
342290269-99659-DETAIL-03_02_2023-ABNDEQPM-1^07216001.0291940 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
829746499-13059-DETAIL-03_02_2023-SVCENTCO-1^07216001.0291941 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
715582969-18459-DETAIL-03_02_2023-SVCENTCO-1^07216001.0291943 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
599107797-30639-DETAIL-03_02_2023-GO95MLD-1^07216001.0292401 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
599107797-30639-DETAIL-03_02_2023-SVCROAD-1^07216001.0292401 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
599107797-30639-AUDIT-03_06_2023-SVCENTBK-1^07216001.0292401 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
662284669-27349-DETAIL-03_01_2023-GO95MLD-1^07216001.0292500 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
270609723-11939-DETAIL-03_13_2023-GO95MLD-1^07216001.0292502 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
699465723-24839-DETAIL-03_02_2023-GO95MLD-1^07216001.0292503 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
699465723-24839-DETAIL-03_02_2023-SVCROAD-1^07216001.0292503 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
357169143-65049-DETAIL-03_01_2023-GO95MLD-1^07216001.0292505 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
284597003-44049-DETAIL-03_02_2023-GO95MLD-1^07216001.0292506 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
284597003-44049-DETAIL-03_02_2023-GUYHINS-1^07216001.0292506 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
816900893-41649-DETAIL-03_02_2023-GO95HV-1^07216001.0292507 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
816900893-41649-DETAIL-03_02_2023-GO95MLD-1^07216001.0292507 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
800860489-2049-DETAIL-03_01_2023-SVCROAD-1^07216001.0292540 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
51453459-50559-DETAIL-03_01_2023-GO95MLD-1^07216001.0292541 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
51453459-50559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292541 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
801475824-58959-DTLSB-02_06_2024-GO95MLD-1^07216001.0309702 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2029-02-06 | 3
819360553-19049-DTLSB-02_06_2024-CLMBTRE-1^07216001.0309800 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
819360553-19049-DTLSB-02_06_2024-GO95HV-1^07216001.0309800 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2029-02-06 | 3
276882404-6359-DTLSB-02_06_2024-GO95MLD-1^07216001.0309802 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
852726204-2939-DTLSB-02_06_2024-SVCROAD-1^07216001.0309803 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
503337144-68549-DTLSB-02_06_2024-GO95MLD-1^07216001.0309805 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
88321874-16639-DTLSB-02_06_2024-GO95MLD-1^07216001.0309806 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
979345288-78959-DTLSB-02_06_2024-SVCDEFLC-1^07216001.0309840 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
979345288-78959-DTLSB-02_06_2024-SVCDEFLC-2^07216001.0309840 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
37371054-18139-DTLSB-02_06_2024-GO95MLD-1^07216001.0309901 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
644638464-49239-DTLSB-02_06_2024-GO95MLD-1^07216001.0309902 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
197159694-89549-DTLSB-02_06_2024-SVCDEFLC-1^07216001.0309903 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
510778048-46359-DETAIL-03_01_2023-GO95MLD-1^07216001.0292604 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
200002559-90559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292640 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
200002559-90559-DETAIL-03_01_2023-SVCWIND-1^07216001.0292640 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
200002559-90559-DETAIL-03_01_2023-SVCWIND-2^07216001.0292640 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
801273259-11559-DETAIL-03_01_2023-GO95MLD-1^07216001.0292641 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
801273259-11559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292641 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
188936383-40749-DETAIL-03_01_2023-GO95MLD-1^07216001.0292700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
895155936-29549-DETAIL-03_01_2023-GO95MLD-1^07216001.0292701 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
895155936-29549-DETAIL-03_01_2023-GO95TCH-1^07216001.0292701 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
502410062-52149-DETAIL-03_02_2023-GO95MLD-1^07216001.0292900 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
975698599-76939-DETAIL-03_02_2023-GO95MLD-1^07216001.0292901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
678938429-82239-DETAIL-03_02_2023-GO95TCH-1^07216001.0292902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
810475677-1849-DETAIL-03_09_2023-GO95CL10-1^07216001.0293302 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
810475677-1849-DETAIL-03_09_2023-GO95MLD-1^07216001.0293302 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
810475677-1849-DETAIL-03_09_2023-GO95TCH-1^07216001.0293302 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
874203348-49886-DETAIL-03_09_2023-SVCENTBK-1^07216001.0293340 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
395389808-69776-DETAIL-03_09_2023-GO95TCH-1^07216001.0293341 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
706506007-70839-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0293402 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
706506007-70839-DETAIL-03_13_2023-GO95CL10-1^07216001.0293402 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
706506007-70839-DETAIL-03_13_2023-SVCENTBK-1^07216001.0293402 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
706506007-70839-DETAIL-03_13_2023-SVCWIND-1^07216001.0293402 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
935872817-78349-DETAIL-03_13_2023-GO95MLD-1^07216001.0293403 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
386205655-89649-DETAIL-03_07_2023-GO95MLD-1^07216001.0297402 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
872726375-56149-DETAIL-03_07_2023-GO95MLD-1^07216001.0297403 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
814724120-8742-DETAIL-03_07_2023-GO95MLD-1^07216001.0297405 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
138474528-24139-DETAIL-03_06_2023-GO95HV-1^07216001.0297500 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
138474528-24139-DETAIL-03_06_2023-GO95MLD-1^07216001.0297500 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
138474528-24139-DETAIL-03_06_2023-GUYHINS-1^07216001.0297500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
138474528-24139-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297500 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
471971079-67539-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0297502 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
471971079-67539-DETAIL-03_06_2023-GO95MLD-1^07216001.0297502 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
537994925-36249-DETAIL-03_08_2023-GO95MLD-1^07216001.0297504 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
537994925-36249-DETAIL-03_08_2023-GUYHINS-1^07216001.0297504 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
675507665-40139-DETAIL-03_07_2023-GO95MLD-1^07216001.0297505 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
160332993-68739-DETAIL-03_01_2023-GO95HV-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
160332993-68739-DETAIL-03_01_2023-GO95MLD-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
160332993-68739-DETAIL-03_01_2023-SVCNEUT-1^07216001.0293506 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
551244563-21639-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0293601 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
551244563-21639-DETAIL-03_01_2023-GO95HV-1^07216001.0293601 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
914782523-90239-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0293602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
914782523-90239-DETAIL-03_01_2023-GO95MLD-1^07216001.0293602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
914782523-90239-DETAIL-03_01_2023-GO95TCH-1^07216001.0293602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
914782523-90239-DETAIL-03_01_2023-SVCNEUT-1^07216001.0293602 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
15531018-92189-DETAIL-03_09_2023-GO95MLD-1^07216001.0293603 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
75851489-57439-DETAIL-03_09_2023-GO95MLD-1^07216001.0293605 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
75851489-57439-DETAIL-03_09_2023-GO95TCH-1^07216001.0293605 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
611018789-67249-DETAIL-03_09_2023-GO95MLD-1^07216001.0293606 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
807489399-96049-DETAIL-03_09_2023-GO95MLD-1^07216001.0293607 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
80758849-12610-DETAIL-03_09_2023-SVCWIND-1^07216001.0293608 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
70023123-37390-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0293609 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
70023123-37390-DETAIL-03_07_2023-GO95MLD-1^07216001.0293609 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2028-03-07 | 3
12462686-28649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293900 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
12462686-28649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293900 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
63546876-72349-DETAIL-03_02_2023-GO95MLD-1^07216001.0293901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
63546876-72349-DETAIL-03_02_2023-GO95MLD-2^07216001.0293901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
63546876-72349-DETAIL-03_02_2023-SVCWIND-1^07216001.0293901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
787058179-64279-DETAIL-03_02_2023-GO95MLD-1^07216001.0293902 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
541867836-72649-DETAIL-03_02_2023-GO95CL10-1^07216001.0293903 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2028-03-02 | 3
794452101-63101-DETAIL-03_08_2023-GUYHINS-1^07216001.0297506 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
883317001-48001-DETAIL-03_08_2023-GO95HV-1^07216001.0297509 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2028-03-08 | 3
883317001-48001-DETAIL-03_08_2023-GO95MLD-1^07216001.0297509 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
886121016-48149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297510 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
63949358-96849-DETAIL-03_08_2023-GO95MLD-1^07216001.0297600 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
63949358-96849-AUDIT-03_21_2023-GO95HV-1^07216001.0297600 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
356074455-97149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297601 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
698164489-68249-DETAIL-03_06_2023-GO95MLD-1^07216001.0297603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
698164489-68249-DETAIL-03_06_2023-GO95TCH-1^07216001.0297603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
698164489-68249-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297603 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
980779261-68149-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297604 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
597879960-31939-DETAIL-03_06_2023-GO95MLD-1^07216001.0297605 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
539831647-57249-DETAIL-03_08_2023-GO95MLD-1^07216001.0294201 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
662315177-26811-DETAIL-03_08_2023-GO95MLD-1^07216001.0294303 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
662315177-26811-DETAIL-03_08_2023-SVCENTBK-1^07216001.0294303 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
202077547-749-DETAIL-03_09_2023-GO95HV-1^07216001.0294306 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
554669518-68666-DETAIL-03_08_2023-SVCWIND-1^07216001.0294340 | OTHER | CA-NON-TIER | Distribution | 2023-03-08 | 2026-03-08 | 2
372732887-58339-DETAIL-03_13_2023-GO95MLD-1^07216001.0294400 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
372732887-58339-DETAIL-03_13_2023-GUYHINS-1^07216001.0294400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
324207217-97559-DETAIL-03_09_2023-CLRTOPOL-1^07216001.0294401 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
324207217-97559-DETAIL-03_09_2023-GO95MLD-1^07216001.0294401 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
324207217-97559-DETAIL-03_09_2023-SVCWIND-1^07216001.0294401 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
308664377-77559-DETAIL-03_09_2023-SVCWIND-1^07216001.0294402 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
939573607-98349-DETAIL-03_13_2023-GO95HV-1^07216001.0294405 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
637905216-47139-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0294407 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
637905216-47139-DETAIL-03_13_2023-GO95CL10-1^07216001.0294407 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
637905216-47139-DETAIL-03_13_2023-SVCENTBK-1^07216001.0294407 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
476678336-72559-DETAIL-03_07_2023-GO95MLD-1^07216001.0294410 | OTHER | CA-NON-TIER | Distribution | 2023-03-07 | 2026-03-07 | 2
118322428-36495-DETAIL-03_09_2023-SVCENTCO-1^07216001.0294441 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
925451495-31839-DETAIL-03_09_2023-CLRTOPOL-1^07216001.0294501 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
925451495-31839-DETAIL-03_09_2023-GO95MLD-1^07216001.0294501 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
747810789-35451-DETAIL-03_09_2023-GUYHINS-1^07216001.0294502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
747810789-35451-DETAIL-03_09_2023-SVCENTBK-1^07216001.0294502 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
775564069-98622-DETAIL-03_09_2023-GO95MLD-1^07216001.0294503 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2028-03-09 | 3
647889535-88971-DETAIL-03_09_2023-GO95MLD-1^07216001.0294504 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
647889535-88971-DETAIL-03_09_2023-GUYHINS-1^07216001.0294504 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
802647303-19759-DTLSB-02_16_2024-GUYNOINS-1^07216001.0270000 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
936653873-98759-DTLSB-02_22_2024-GUYNOINS-1^07216001.0270040 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
407085843-914-DTLSB-02_28_2024-SVCWIND-1^07216001.0270600 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
852946475-93649-DTLSB-02_27_2024-SVCNEUT-1^07216001.0270700 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
337868393-48759-DTLSB-02_16_2024-GO95HV-1^07216001.0271000 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
603232893-62739-DTLSB-02_16_2024-GO95MLD-1^07216001.0271001 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
546067353-88639-DTLSB-02_28_2024-GO95MLD-1^07216001.0271600 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
251498157-54218-DTLSB-02_27_2024-GO95HV-1^07216001.0271700 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
251498157-54218-DTLSB-02_27_2024-GO95MLD-1^07216001.0271700 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
129445793-20939-DTLSB-02_16_2024-GO95MLD-1^07216001.0272000 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
604911673-55449-DTLSB-02_28_2024-GO95HV-1^07216001.0272700 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
604911673-55449-DTLSB-02_28_2024-SVCENTCO-1^07216001.0272700 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
604766513-30449-DTLSB-02_27_2024-GO95TCH-1^07216001.0273806 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
772132347-3347-DTLSB-02_28_2024-GO95MLD-1^07216001.0273807 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
348230547-23547-DTLSB-02_27_2024-GO95HV-1^07216001.0273808 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
348230547-23547-DTLSB-02_27_2024-GO95MLD-1^07216001.0273808 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
826562884-47249-DTLSB-02_28_2024-SVCROAD-1^07216001.0275901 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
594427014-63459-DTLSB-02_26_2024-ENCHRW-1^07216001.0276702 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
648322224-69649-DTLSB-02_26_2024-GO95MLD-1^07216001.0276800 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
648322224-69649-DTLSB-02_26_2024-SVCROAD-1^07216001.0276800 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
347990824-85449-DTLSB-02_26_2024-GO95MLD-1^07216001.0276901 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
508807554-22549-DTLSB-02_27_2024-SVCROAD-1^07216001.0276902 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
730640764-20549-DTLSB-02_26_2024-GO95CL10-1^07216001.0277601 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
730640764-20549-DTLSB-02_26_2024-GO95MLD-1^07216001.0277601 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
304123214-80303-DTLSB-02_26_2024-GO95MLD-1^07216001.0277605 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
304123214-80303-DTLSB-02_26_2024-GUYHINS-1^07216001.0277605 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
796207814-82459-DTLSB-02_26_2024-GO95MLD-1^07216001.0277703 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
888734104-66739-DTLSB-02_26_2024-GO95MLD-1^07216001.0277704 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
888734104-66739-DTLSB-02_26_2024-GRDRODHI-1^07216001.0277704 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
680596104-12749-DTLSB-02_26_2024-GO95MLD-1^07216001.0277705 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
66836594-13459-DTLSB-02_27_2024-SVCROAD-1^07216001.0277706 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
650725578-7578-DTLSB-02_26_2024-GO95TCH-1^07216001.0277707 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
275413484-66439-DTLSB-02_26_2024-GO95MLD-1^07216001.0277800 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
320684984-36449-DTLSB-02_26_2024-CLMBTRE-1^07216001.0277801 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
320684984-36449-DTLSB-02_26_2024-GO95MLD-1^07216001.0277801 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
881847504-20549-AUDIT-03_07_2024-GO95HV-1^07216001.0277804 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2029-03-07 | 3
312820844-90059-DTLSB-02_08_2024-SVCROAD-1^07216001.0309904 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
53572998-63998-DTLSB-02_08_2024-GO95HV-1^07216001.0309905 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2029-02-08 | 3
53572998-63998-DTLSB-02_08_2024-GO95MLD-1^07216001.0309905 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
395444626-30649-DTLSB-02_08_2024-GO95MLD-1^07216001.0309906 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
340246864-93280-DTLTRT-02_06_2024-GUYHINS-1^07216001.0309907 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
340246864-93280-DTLTRT-02_06_2024-SVCNEUT-1^07216001.0309907 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
716134764-79839-DTLSB-02_06_2024-GUYHINS-1^07216001.0309911 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
582374244-26349-DTLSB-02_06_2024-GO95MLD-1^07216001.0309914 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
582374244-26349-DTLSB-02_06_2024-SVCENTCO-1^07216001.0309914 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
48696194-70649-DTLSB-02_06_2024-SVCENTCO-1^07216001.0309915 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
537236814-14839-DTLSB-02_06_2024-GO95MLD-1^07216001.0309916 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
537236814-14839-DTLSB-02_06_2024-GRDRODHI-1^07216001.0309916 | OTHER | CA-NON-TIER | Distribution | 2024-02-06 | 2027-02-06 | 2
281969204-92749-DTLSB-02_27_2024-SVCENTCO-1^07216001.0278706 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
292656673-9749-DTLSB-02_27_2024-GO95MLD-1^07216001.0278802 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
855700508-87723-DTLSB-02_27_2024-GO95MLD-1^07216001.0278804 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
547704533-72749-DTLSB-02_27_2024-GO95HV-1^07216001.0278805 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
499366313-52159-DTLSB-02_27_2024-GO95MLD-1^07216001.0278806 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
702609033-51459-DTLSB-02_28_2024-GUYLOINS-1^07216001.0278903 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
432238114-14749-DTLSB-02_27_2024-GO95MLD-1^07216001.0278905 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
835658360-88360-DTLSB-02_16_2024-GO95MLD-1^07216001.0279100 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
190139404-28459-DTLSB-02_28_2024-SVCDEFLC-1^07216001.0279800 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
190139404-28459-DTLSB-02_28_2024-SVCENTCO-1^07216001.0279800 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
82082624-6459-DTLSB-02_27_2024-GO95HV-1^07216001.0279902 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
209529155-32859-DTLSB-02_21_2023-GUYHINS-1^07216001.0280502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
53694636-82859-DTLSB-02_21_2023-GO95MLD-1^07216001.0280503 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
544427465-26039-DTLSB-02_21_2023-GO95HV-1^07216001.0280600 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
544427465-26039-DTLSB-02_21_2023-GO95MLD-1^07216001.0280600 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
300634255-16339-DTLSB-02_21_2023-GO95HV-1^07216001.0280601 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
246516346-85249-DTLSB-02_21_2023-GO95MLD-1^07216001.0280603 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
856954855-6249-DTLSB-02_21_2023-GO95MLD-1^07216001.0280604 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
21280906-79249-DTLSB-02_21_2023-GO95HV-1^07216001.0280605 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
21280906-79249-DTLSB-02_21_2023-GO95MLD-1^07216001.0280605 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
573024956-52049-DTLSB-02_22_2023-GO95MLD-1^07216001.0280700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
481430235-65249-DTLSB-02_22_2023-GO95HV-1^07216001.0280701 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
883600687-86418-DTLSB-02_22_2023-GO95HV-1^07216001.0280704 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
883600687-86418-DTLSB-02_22_2023-GO95MLD-1^07216001.0280704 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
131361125-39249-DETAIL-03_09_2023-SVCNEUT-1^07216001.0294602 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
634524499-85349-DETAIL-02_27_2023-GO95HV-1^07216001.0294603 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
634524499-85349-DETAIL-02_27_2023-SVCENTCO-1^07216001.0294603 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
426980219-40580-DETAIL-02_27_2023-GO95MLD-1^07216001.0294605 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
426980219-40580-DETAIL-02_27_2023-GO95TCH-1^07216001.0294605 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
496787666-47371-DETAIL-03_09_2023-GO95MLD-1^07216001.0294606 | OTHER | CA-NON-TIER | Distribution | 2023-03-09 | 2026-03-09 | 2
608502393-26349-DETAIL-02_23_2023-GO95MLD-1^07216001.0294607 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
571537865-79271-DETAIL-02_23_2023-GO95MLD-1^07216001.0294608 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
827185679-83559-DETAIL-02_27_2023-GO95MLD-1^07216001.0294609 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
879364178-77093-DETAIL-02_23_2023-GO95TCH-1^07216001.0294643 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
879364178-77093-DETAIL-02_23_2023-SVCENTCO-1^07216001.0294643 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
104630956-86649-DETAIL-02_23_2023-GO95MLD-1^07216001.0294704 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
521982786-52001-DTLSB-02_21_2023-GO95MLD-1^07216001.0281801 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
833034181-35149-DTLSB-02_21_2023-GO95CL10-1^07216001.0281900 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
635504726-64451-DTLSB-02_21_2023-GO95MLD-1^07216001.0281901 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
420727196-17370-DTLSB-02_21_2023-GO95HV-1^07216001.0283500 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2028-02-21 | 3
420727196-17370-DTLSB-02_21_2023-GO95MLD-1^07216001.0283500 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
165188796-60259-DTLSB-02_21_2023-GO95MLD-1^07216001.0283502 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
200327046-37740-DTLSB-02_21_2023-GO95MLD-1^07216001.0283503 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
539283776-16531-DTLSB-02_21_2023-GO95MLD-1^07216001.0283504 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
372895766-96720-DTLSB-02_21_2023-GO95MLD-1^07216001.0284503 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
989590966-75733-DTLSB-02_21_2023-GO95MLD-1^07216001.0284504 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
236666070-60508-DTLSB-02_22_2023-GO95MLD-1^07216001.0285503 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
214220470-51470-DTLSB-02_22_2023-GO95MLD-1^07216001.0285507 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
35873208-71308-DTLSB-02_22_2023-GO95MLD-1^07216001.0285602 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
91511155-81649-DTLSB-02_22_2023-ABNDEQPM-1^07216001.0287604 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2028-02-22 | 3
44138736-25049-DTLSB-02_22_2023-GO95MLD-1^07216001.0287700 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
965392366-32649-DTLSB-02_21_2023-SVCENTCO-1^07216001.0287701 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
282546916-25539-DTLSB-02_21_2023-GO95TCH-1^07216001.0287703 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
70516396-26539-DTLSB-02_21_2023-CLRTOUCH-1^07216001.0287704 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
70516396-26539-DTLSB-02_21_2023-GO95TCH-1^07216001.0287704 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
417456025-34539-DTLSB-02_21_2023-SVCENTCO-1^07216001.0287707 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
999654415-52833-DTLSB-02_21_2023-GO95TCH-1^07216001.0287708 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
999654415-52833-DTLSB-02_21_2023-SVCROAD-1^07216001.0287708 | OTHER | CA-NON-TIER | Distribution | 2023-02-21 | 2026-02-21 | 2
876463416-51443-ADMIN-02_08_2024-CUTOUTAR-1^07216001.0287801 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
964498435-54933-DTLSB-02_22_2023-GO95MLD-1^07216001.0287804 | OTHER | CA-NON-TIER | Distribution | 2023-02-22 | 2026-02-22 | 2
104630956-86649-DETAIL-02_23_2023-GO95TCH-1^07216001.0294704 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
3224355-71839-DETAIL-02_23_2023-GO95MLD-1^07216001.0294705 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
3224355-71839-DETAIL-02_23_2023-SVCENTCO-1^07216001.0294705 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
428785395-1449-DETAIL-02_23_2023-GO95MLD-1^07216001.0294706 | OTHER | CA-NON-TIER | Distribution | 2023-02-23 | 2026-02-23 | 2
9356745-43349-DETAIL-02_27_2023-GO95HV-1^07216001.0294707 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
9356745-43349-DETAIL-02_27_2023-GO95MLD-1^07216001.0294707 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
558855475-83349-DETAIL-02_27_2023-GO95MLD-1^07216001.0294708 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
826047485-15349-DETAIL-02_27_2023-ABNDEQPM-1^07216001.0294740 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
826047485-15349-DETAIL-02_27_2023-GO95TCH-1^07216001.0294740 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
826047485-15349-DETAIL-02_27_2023-RISEGRD-1^07216001.0294740 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
371302479-17859-DETAIL-03_02_2023-GO95MLD-1^07216001.0294900 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
965243889-52349-DETAIL-03_02_2023-GO95MLD-1^07216001.0294901 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
2232698-83849-DTLSB-02_20_2024-SVCENTCO-1^07216001.0260506 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
2232698-83849-DTLSB-02_20_2024-SVCENTCO-2^07216001.0260506 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
402425224-74459-DTLSB-02_21_2024-SVCENTBK-1^07216001.0260600 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
489784918-94349-DTLSB-02_21_2024-GO95MLD-1^07216001.0260701 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
161916118-34349-DTLSB-02_21_2024-CLMBTRE-1^07216001.0260702 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
161916118-34349-DTLSB-02_21_2024-SVCROAD-1^07216001.0260702 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
376482104-6749-DTLSB-02_21_2024-SVCENTCO-1^07216001.0260703 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
376482104-6749-DTLSB-02_21_2024-SVCROAD-1^07216001.0260703 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
505519414-65749-DTLSB-02_21_2024-SVCROAD-1^07216001.0260704 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
245952409-57839-DTLSB-02_21_2024-GO95CL10-1^07216001.0260800 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
245952409-57839-DTLSB-02_21_2024-SVCDEFLC-1^07216001.0260800 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
245952409-57839-DTLSB-02_21_2024-SVCENTCO-1^07216001.0260800 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
206829789-16459-DTLSB-02_21_2024-GO95MLD-1^07216001.0260802 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
543815098-73849-DTLSB-02_21_2024-GO95MLD-1^07216001.0260803 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
859769869-38859-DTLSB-02_21_2024-GO95CL10-1^07216001.0260804 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
859769869-38859-DTLSB-02_21_2024-GO95MLD-1^07216001.0260804 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
684321939-17459-DTLSB-02_21_2024-CLRTOPOL-1^07216001.0260808 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
98381838-47649-DTLSB-02_21_2024-GO95MLD-1^07216001.0260809 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
849419301-30401-DTLSB-02_21_2024-GO95CL10-1^07216001.0260810 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
849419301-30401-DTLSB-02_21_2024-GO95MLD-1^07216001.0260810 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
408342979-21059-DTLSB-02_28_2024-GO95MLD-1^07216001.0260900 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
71508108-52849-DTLSB-02_28_2024-GO95HV-1^07216001.0260901 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
71508108-52849-DTLSB-02_28_2024-GO95MLD-1^07216001.0260901 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
986800988-82539-DTLSB-02_28_2024-GO95CLSV-1^07216001.0260903 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
296338233-84339-DETAIL-03_15_2023-CLRTOPOL-1^07216001.0290600 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
296338233-84339-DETAIL-03_15_2023-GO95MLD-1^07216001.0290600 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
296338233-84339-DETAIL-03_15_2023-SVCENTCO-1^07216001.0290600 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
285927345-76639-DETAIL-03_13_2023-GO95MLD-1^07216001.0290601 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
285815705-6049-DETAIL-03_15_2023-GO95MLD-1^07216001.0290602 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
285815705-6049-DETAIL-03_15_2023-SVCENTBK-1^07216001.0290602 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
75202485-95239-DETAIL-03_15_2023-GO95CL10-1^07216001.0290604 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
622696893-67939-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0290605 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
622696893-67939-DETAIL-03_13_2023-CLRTOPOL-2^07216001.0290605 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
622696893-67939-DETAIL-03_13_2023-GO95BLTC-1^07216001.0290605 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
23949206-87158-DETAIL-03_13_2023-GO95MLD-1^07216001.0290606 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
23949206-87158-DETAIL-03_13_2023-SVCWIND-1^07216001.0290606 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
373577588-12688-DTLSB-02_28_2024-SVCDEFLC-1^07216001.0260912 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
482467499-89649-DTLSB-02_15_2024-GO95HV-1^07216001.0261001 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
482467499-89649-DTLSB-02_15_2024-GO95MLD-1^07216001.0261001 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
500511361-96859-DTLSB-02_15_2024-SVCENTCO-1^07216001.0261002 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
500511361-96859-DTLSB-02_15_2024-SVCENTCO-2^07216001.0261002 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
402918689-30949-DTLSB-02_15_2024-GO95MLD-1^07216001.0261004 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
676763801-74559-DTLSB-02_16_2024-SVCDEFLC-1^07216001.0261006 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
676763801-74559-DTLSB-02_16_2024-SVCENTCO-1^07216001.0261006 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
863197739-15249-DTLSB-02_19_2024-GO95MLD-1^07216001.0261007 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
3334900-50949-DTLSB-02_16_2024-GO95HV-1^07216001.0261009 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
3334900-50949-DTLSB-02_16_2024-GO95MLD-1^07216001.0261009 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
406175349-56839-DTLSB-02_16_2024-GO95HV-1^07216001.0261010 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
406175349-56839-DTLSB-02_16_2024-GO95MLD-1^07216001.0261010 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
499205789-62949-DTLSB-02_16_2024-GO95MLD-1^07216001.0261100 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
792555829-94349-DTLSB-02_16_2024-GO95MLD-1^07216001.0261102 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
792555829-94349-AUDIT-02_27_2024-SVCNEUT-1^07216001.0261102 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
572566159-88449-DTLSB-02_16_2024-GO95MLD-1^07216001.0261103 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
483974410-71639-DTLSB-02_16_2024-GO95MLD-1^07216001.0261104 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
463143439-43349-DTLSB-02_16_2024-GO95CL10-1^07216001.0261105 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
463143439-43349-DTLSB-02_16_2024-SVCENTCO-1^07216001.0261105 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
959516571-50059-DTLSB-02_16_2024-GO95MLD-1^07216001.0261200 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
452906420-4049-DTLSB-02_19_2024-GO95MLD-1^07216001.0261203 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
215246020-78249-DTLSB-02_19_2024-GO95MLD-1^07216001.0261204 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
226764849-97349-DTLSB-02_20_2024-GO95MLD-1^07216001.0261205 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
106236199-99759-DETAIL-03_13_2023-SVCENTCO-1^07216001.0290640 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
535308475-2139-DETAIL-03_13_2023-GO95MLD-1^07216001.0290700 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
535308475-2139-DETAIL-03_13_2023-GUYHINS-1^07216001.0290700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
535308475-2139-DETAIL-03_13_2023-SVCWIND-1^07216001.0290700 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
682272074-28849-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0290701 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
682272074-28849-DETAIL-03_13_2023-SVCNEUT-1^07216001.0290701 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
900298124-72049-DETAIL-03_13_2023-SVCWIND-1^07216001.0290702 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
842699644-53639-DETAIL-03_01_2023-GO95MLD-1^07216001.0290704 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
27951343-55639-DETAIL-03_01_2023-GO95CL10-1^07216001.0290705 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
27951343-55639-DETAIL-03_01_2023-GO95MLD-1^07216001.0290705 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
701607514-4539-DETAIL-03_13_2023-GO95HV-1^07216001.0290707 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2028-03-13 | 3
701607514-4539-DETAIL-03_13_2023-GUYHINS-1^07216001.0290707 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
58060108-8739-DTLSB-02_20_2024-GO95MLD-1^07216001.0261501 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
838887059-48049-DTLSB-02_21_2024-GO95MLD-1^07216001.0261503 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
574793949-78049-DTLSB-02_21_2024-GO95MLD-1^07216001.0261505 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
805236558-35849-DTLSB-02_20_2024-GO95CL10-1^07216001.0261508 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
805236558-35849-DTLSB-02_20_2024-SVCWIND-1^07216001.0261508 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
490286938-44849-DTLSB-02_20_2024-GO95MLD-1^07216001.0261510 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
285134429-94849-DTLSB-02_20_2024-SVCDEFLC-1^07216001.0261601 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
750046509-43849-DTLSB-02_21_2024-CLMBTRE-1^07216001.0261700 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
224833219-76459-DTLSB-02_21_2024-GO95MLD-1^07216001.0261800 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
243598429-81149-DTLSB-02_26_2024-GO95HV-1^07216001.0261900 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
923690579-9839-DTLSB-02_16_2024-GO95HV-1^07216001.0262000 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
835371221-51059-DTLSB-02_16_2024-GO95MLD-1^07216001.0262001 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
2373269-39549-DTLSB-02_16_2024-GO95MLD-1^07216001.0262002 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
2373269-39549-DTLSB-02_16_2024-GO95TCH-1^07216001.0262002 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
2373269-39549-DTLSB-02_16_2024-SVCENTCO-1^07216001.0262002 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
2373269-39549-DTLSB-02_16_2024-SVCENTCO-2^07216001.0262002 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
664415821-57739-DTLSB-02_16_2024-GO95TCH-1^07216001.0262003 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
664415821-57739-DTLSB-02_16_2024-SVCENTBK-1^07216001.0262003 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
664415821-57739-DTLSB-02_16_2024-SVCENTCO-1^07216001.0262003 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
664415821-57739-DTLSB-02_16_2024-SVCROAD-1^07216001.0262003 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
590984270-2739-DTLSB-02_15_2024-GO95HV-1^07216001.0262004 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
590984270-2739-DTLSB-02_15_2024-GO95MLD-1^07216001.0262004 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
979732139-43049-DTLSB-02_15_2024-SVCENTCO-1^07216001.0262006 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
922597919-14559-DTLSB-02_16_2024-GO95MLD-1^07216001.0262007 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
811680946-59149-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0297705 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
136125046-65149-DETAIL-03_06_2023-GO95HV-1^07216001.0297706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2028-03-06 | 3
136125046-65149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
136125046-65149-DETAIL-03_06_2023-GRDRODHI-1^07216001.0297706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
136125046-65149-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297706 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
885449980-40849-DETAIL-03_06_2023-GO95MLD-1^07216001.0297708 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
951661438-91008-DETAIL-03_06_2023-SVCWIND-1^07216001.0297741 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
36910528-80468-DETAIL-03_06_2023-SVCWIND-1^07216001.0297742 | OTHER | CA-NON-TIER | Distribution | 2023-03-06 | 2026-03-06 | 2
924391436-16939-DETAIL-02_27_2023-GO95HV-1^07216001.0297800 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2028-02-27 | 3
924391436-16939-DETAIL-02_27_2023-GO95MLD-1^07216001.0297800 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
488315705-32249-DETAIL-02_28_2023-GO95MLD-1^07216001.0297804 | OTHER | CA-NON-TIER | Distribution | 2023-02-28 | 2026-02-28 | 2
276444661-12459-DETAIL-02_27_2023-GO95MLD-1^07216001.0297806 | OTHER | CA-NON-TIER | Distribution | 2023-02-27 | 2026-02-27 | 2
638136990-25949-DTLTRT-02_19_2024-SVCENTCO-1^07216001.0262204 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
558910729-59949-DTLSB-02_19_2024-SVCDEFLC-1^07216001.0262205 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
995750481-56059-DTLSB-02_19_2024-GO95MLD-1^07216001.0262206 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
214214420-87749-DTLSB-02_20_2024-GO95MLD-1^07216001.0262300 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
208592519-95349-DTLSB-02_20_2024-SVCROAD-1^07216001.0262301 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
648115869-59639-DTLSB-02_19_2024-GO95MLD-1^07216001.0262302 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
648115869-59639-DTLSB-02_19_2024-SVCDEFLC-1^07216001.0262302 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
648115869-59639-DTLSB-02_19_2024-SVCENTCO-1^07216001.0262302 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
648115869-59639-DTLSB-02_19_2024-SVCENTCO-2^07216001.0262302 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
584717251-11059-DTLSB-02_20_2024-GO95MLD-1^07216001.0262306 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
584717251-11059-DTLSB-02_20_2024-GO95TCH-1^07216001.0262306 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
381287700-44939-DTLSB-02_20_2024-SVCROAD-1^07216001.0262307 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
282054478-26849-DTLSB-02_21_2024-GUYLOINS-1^07216001.0262400 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
262272348-77849-DTLSB-02_21_2024-GO95MLD-1^07216001.0262503 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
138393338-46849-DTLSB-02_21_2024-COPLLEAN-1^07216001.0262505 | POLE | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
603456828-42839-DTLSB-02_21_2024-GO95MLD-1^07216001.0262506 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
985485258-98849-DTLSB-02_21_2024-GO95HV-1^07216001.0262600 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
341926478-92539-DTLSB-02_21_2024-GO95HV-1^07216001.0262700 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
341926478-92539-DTLSB-02_21_2024-GO95MLD-1^07216001.0262700 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
792974819-40349-DTLSB-02_26_2024-GO95HV-1^07216001.0262800 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
857335437-25368-DTLSB-02_26_2024-GO95MLD-1^07216001.0262801 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
809807299-89749-DTLSB-02_26_2024-GO95HV-1^07216001.0262901 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
809807299-89749-DTLSB-02_26_2024-GO95MLD-1^07216001.0262901 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
594062198-59339-DTLSB-02_22_2024-GO95HV-1^07216001.0262902 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
916899648-50939-DTLSB-02_13_2024-GO95MLD-1^07216001.0187103 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
685265388-74010-DTLSB-02_13_2024-SVCDEFLC-1^07216001.0187200 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
685265388-74010-DTLSB-02_13_2024-SVCENTCO-1^07216001.0187200 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
910263933-49559-DTLSB-02_13_2024-GUYHINS-1^07216001.0187203 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
833579195-91295-DTLSB-02_13_2024-GO95MLD-1^07216001.0187204 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
106108858-159-DETAIL-02_13_2024-GO95HV-1^07216001.0187400 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
82855024-84959-DTLSB-02_13_2024-GO95MLD-1^07216001.0187401 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
82855024-84959-DTLSB-02_13_2024-SVCNEUT-1^07216001.0187401 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
996420858-9759-DTLSB-02_13_2024-GO95MLD-1^07216001.0187402 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
459749658-39759-DTLSB-02_13_2024-GO95MLD-1^07216001.0187403 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
742022303-18059-DTLSB-02_14_2024-GO95MLD-1^07216001.0188000 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
35274483-48559-DTLSB-02_13_2024-GO95TCH-1^07216001.0188100 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
217720963-79559-DTLSB-02_13_2024-GO95TCH-1^07216001.0188200 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
135945763-41339-DTLSB-02_13_2024-GO95HV-1^07216001.0188201 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
135945763-41339-DTLSB-02_13_2024-GO95MLD-1^07216001.0188201 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
135945763-41339-AUDIT-03_07_2024-ABNDEQPM-1^07216001.0188201 | OTHER | CA-NON-TIER | Distribution | 2024-03-07 | 2029-03-07 | 3
385370183-10659-DTLSB-02_13_2024-GO95MLD-1^07216001.0188202 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
226163443-28639-DTLSB-02_13_2024-GO95MLD-1^07216001.0188203 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
226163443-28639-DTLSB-02_13_2024-SVCROAD-1^07216001.0188203 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
294181563-79559-DTLSB-02_21_2024-GO95MLD-1^07216001.0189000 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
979853923-47059-DTLSB-02_14_2024-GO95CL10-1^07216001.0189002 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
979853923-47059-DTLSB-02_14_2024-GO95MLD-1^07216001.0189002 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
344433398-41039-DTLSB-02_15_2024-GO95MLD-1^07216001.0190700 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
132385588-13359-DTLSB-02_15_2024-GO95MLD-1^07216001.0190701 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
150328463-3049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291501 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
962610363-23049-DETAIL-03_15_2023-GO95MLD-1^07216001.0291502 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
962610363-23049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291502 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
199421635-19039-DETAIL-03_15_2023-GO95MLD-1^07216001.0291503 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
188472925-2939-DETAIL-03_15_2023-GO95MLD-1^07216001.0291504 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
575644525-83549-DETAIL-03_15_2023-GO95MLD-1^07216001.0291505 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
623081405-3939-DETAIL-03_15_2023-GO95MLD-1^07216001.0291506 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
459960559-1859-DETAIL-03_13_2023-SVCENTCO-1^07216001.0291540 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
253350183-59649-DETAIL-03_02_2023-GO95MLD-1^07216001.0291601 | OTHER | CA-NON-TIER | Distribution | 2023-03-02 | 2026-03-02 | 2
558577353-63049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291603 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
879541943-24049-DETAIL-03_15_2023-GO95MLD-1^07216001.0291605 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
664123753-3859-DETAIL-03_15_2023-CLRTOPOL-1^07216001.0291606 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
441402419-25939-DTLSB-02_15_2024-GO95MLD-1^07216001.0191801 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
56688489-2759-DTLSB-02_05_2024-GO95MLD-1^07216001.0191940 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
60897149-39049-DTLSB-02_05_2024-GO95MLD-1^07216001.0191941 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
60897149-39049-DTLSB-02_05_2024-SVCROAD-1^07216001.0191941 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
337714979-31759-DTLSB-02_05_2024-GO95HV-1^07216001.0192940 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2029-02-05 | 3
337714979-31759-DTLSB-02_05_2024-GO95MLD-1^07216001.0192940 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
323416279-61759-DTLSB-02_05_2024-GO95HV-1^07216001.0192941 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2029-02-05 | 3
383050459-87959-DTLSB-02_05_2024-GO95MLD-1^07216001.0194940 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
878587248-72259-DTLSB-02_08_2024-SVCROAD-1^07216001.0196001 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
24258814-47449-DTLSB-02_08_2024-SVCDEFLC-1^07216001.0196101 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
959407448-61949-AUDIT-02_27_2024-GO95HV-1^07216001.0196103 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
959407448-61949-AUDIT-02_27_2024-GO95MLD-1^07216001.0196103 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
413652963-60159-DTLSB-02_15_2024-GO95MLD-1^07216001.0196900 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
244361847-70059-DTLSB-02_08_2024-GO95MLD-1^07216001.0197000 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
487928014-66039-DETAIL-02_08_2024-SVCDEFLC-1^07216001.0197001 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
487928014-66039-DETAIL-02_08_2024-SVCDEFLC-2^07216001.0197001 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
487928014-66039-DETAIL-02_08_2024-SVCENTBK-1^07216001.0197001 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
487928014-66039-DETAIL-02_08_2024-SVCROAD-1^07216001.0197001 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
75696794-9939-DTLSB-02_08_2024-GO95CL10-1^07216001.0197002 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2029-02-08 | 3
75696794-9939-AUDIT-02_27_2024-GO95MLD-1^07216001.0197002 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
831651084-16839-DTLSB-02_08_2024-SVCWIND-1^07216001.0197003 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
396272208-13259-DTLSB-02_08_2024-SVCENTCO-1^07216001.0197004 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
981371504-50059-DTLSB-02_08_2024-SVCENTBK-1^07216001.0197040 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
329460071-15270-DTLSB-02_08_2024-SVCROAD-1^07216001.0197100 | OTHER | CA-NON-TIER | Distribution | 2024-02-08 | 2027-02-08 | 2
532953750-36749-DTLSB-02_16_2024-GO95MLD-1^07216001.0263202 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2029-02-16 | 3
300798910-8339-DTLSB-02_19_2024-SVCDEFLC-1^07216001.0263204 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
300798910-8339-DTLSB-02_19_2024-SVCENTCO-1^07216001.0263204 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
324488230-51559-DTLSB-02_20_2024-GO95MLD-1^07216001.0263300 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
769345340-28749-DTLSB-02_20_2024-GO95MLD-1^07216001.0263301 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
465698637-40788-DTLSB-02_15_2024-GO95MLD-1^07216001.0263303 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
431851220-80249-DTLSB-02_20_2024-GO95MLD-1^07216001.0263306 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
893071810-92939-DTLSB-02_20_2024-GO95TCH-1^07216001.0263308 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
893071810-92939-DTLSB-02_20_2024-SVCDEFLC-1^07216001.0263308 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
531193649-83249-DTLSB-02_21_2024-GO95MLD-1^07216001.0263600 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
811724138-38549-DTLSB-02_22_2024-GO95MLD-1^07216001.0263902 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
95620718-13949-DTLSB-02_22_2024-CLMBTRE-1^07216001.0263904 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
750409824-58049-DTLSB-02_14_2024-GO95MLD-1^07216001.0198300 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
229499834-96549-DTLSB-02_14_2024-CLRTOPOL-1^07216001.0198301 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
229499834-96549-DTLSB-02_14_2024-GO95MLD-1^07216001.0198301 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
229499834-96549-DTLSB-02_14_2024-GO95TCH-1^07216001.0198301 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
751910274-88339-DTLSB-02_14_2024-GO95MLD-1^07216001.0198304 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
235510214-43839-DTLSB-02_14_2024-GO95HV-1^07216001.0198306 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
283002418-24259-DTLSB-02_14_2024-GO95MLD-1^07216001.0198307 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
283002418-24259-DTLSB-02_14_2024-SVCENTBK-1^07216001.0198307 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
102887524-15939-DTLSB-02_14_2024-GO95MLD-1^07216001.0198308 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
118949654-39-DTLSB-02_14_2024-GO95HV-1^07216001.0198310 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
781572304-6349-ADMIN-06_19_2024-POLEDERP-1^07216001.0198311 | POLE | CA-NON-TIER | Distribution | 2024-06-19 | 2027-06-19 | 2
278956098-70159-DTLSB-02_14_2024-GO95MLD-1^07216001.0198312 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
312146684-69259-DTLSB-02_14_2024-SVCDEFLC-1^07216001.0198313 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
312146684-69259-DTLSB-02_14_2024-SVCDEFLC-2^07216001.0198313 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
312146684-69259-DTLSB-02_14_2024-SVCROAD-1^07216001.0198313 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
608743014-43349-DTLSB-02_14_2024-GO95MLD-1^07216001.0198400 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
608743014-43349-DTLSB-02_14_2024-GRDRODHI-1^07216001.0198400 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
128883644-36939-DTLSB-02_14_2024-CLMBTRE-1^07216001.0198401 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
36103004-61639-DTLSB-02_14_2024-GO95MLD-1^07216001.0198403 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
987886334-42559-DTLSB-02_13_2024-GO95MLD-1^07216001.0198800 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
971564361-74268-DTLSB-02_13_2024-GO95MLD-1^07216001.0198900 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
183634753-27520-DTLSB-02_13_2024-GO95MLD-1^07216001.0198902 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
102067443-80759-DTLSB-02_14_2024-CLMBHAZ-1^07216001.0198903 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
102067443-80759-DTLSB-02_14_2024-GO95HV-1^07216001.0198903 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
95620718-13949-DTLSB-02_22_2024-GO95MLD-1^07216001.0263904 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
266651108-20849-DTLSB-02_22_2024-GO95MLD-1^07216001.0263906 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
222138429-65939-DTLSB-02_15_2024-GO95MLD-1^07216001.0264001 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
496069209-38449-DTLTRT-02_15_2024-GUYHINS-1^07216001.0264003 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
90050600-38839-DTLTRT-02_15_2024-SVCROAD-1^07216001.0264101 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
708550380-26049-DTLSB-02_15_2024-GO95HV-1^07216001.0264200 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
279211539-76049-DTLSB-02_15_2024-GO95HV-1^07216001.0264202 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
279211539-76049-DTLSB-02_15_2024-GO95MLD-1^07216001.0264202 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
279211539-76049-DTLSB-02_15_2024-SVCWIND-1^07216001.0264202 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
127561620-22559-DTLSB-02_16_2024-GO95MLD-1^07216001.0264205 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
127561620-22559-DTLSB-02_16_2024-GO95TCH-1^07216001.0264205 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
179905773-14720-DTLSB-02_19_2024-CLMBTRE-1^07216001.0264206 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
799368144-19249-DTLSB-02_07_2024-GO95TCH-1^07216001.0199104 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
799368144-19249-DTLSB-02_07_2024-GUYHINS-1^07216001.0199104 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
163021378-6259-DTLSB-02_07_2024-ENCHRW-1^07216001.0199106 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
922579224-40549-DETAIL-02_07_2024-SVCDEFLC-1^07216001.0199107 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
231431458-73458-DTLSB-02_07_2024-GO95TCH-1^07216001.0199109 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
466305094-64139-DTLSB-02_07_2024-GO95MLD-1^07216001.0199202 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
937237374-25259-DTLSB-02_07_2024-SVCRUBLG-1^07216001.0199203 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
736990354-93549-DTLSB-02_07_2024-GO95HV-1^07216001.0199204 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2029-02-07 | 3
736990354-93549-DTLSB-02_07_2024-GO95TCH-1^07216001.0199204 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
736990354-93549-DTLSB-02_07_2024-SVCDEFLC-1^07216001.0199204 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
89930094-63549-AUDIT-02_27_2024-GO95MLD-1^07216001.0199205 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
12595954-5259-DTLSB-02_07_2024-GO95TCH-1^07216001.0199209 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
239473254-57549-DTLSB-02_07_2024-GO95MLD-1^07216001.0199210 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
76481144-81939-DTLSB-02_07_2024-GO95MLD-1^07216001.0199211 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2029-02-07 | 3
757660098-86549-DTLSB-02_07_2024-GO95MLD-1^07216001.0199212 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2029-02-07 | 3
15276554-73549-DTLSB-02_07_2024-GO95TCH-1^07216001.0199240 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
349845154-10849-DTLSB-02_07_2024-GO95CLSV-1^07216001.0199300 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
349845154-10849-DTLSB-02_07_2024-GO95HV-1^07216001.0199300 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2029-02-07 | 3
349845154-10849-DTLSB-02_07_2024-SVCWIND-1^07216001.0199300 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
234447644-55149-AUDIT-02_27_2024-GO95MLD-1^07216001.0199302 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
222553394-1639-DTLSB-02_07_2024-GO95MLD-1^07216001.0199304 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
222553394-1639-DTLSB-02_07_2024-GUYHINS-1^07216001.0199304 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
623842364-36549-DTLSB-02_07_2024-SVCROAD-1^07216001.0199305 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
434079704-23839-DTLSB-02_07_2024-GO95MLD-1^07216001.0199306 | OTHER | CA-NON-TIER | Distribution | 2024-02-07 | 2027-02-07 | 2
448306141-67373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200340 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
213428831-30373-DETAIL-03_09_2023-GO95MLD-1^07117002.0201140 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
769948952-52052-DETAIL-03_02_2023-GO95HV-1^07117002.0201200 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
682879741-87973-DETAIL-03_02_2023-GO95MLD-1^07117002.0201202 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
682879741-87973-DETAIL-03_02_2023-SVCROAD-1^07117002.0201202 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
422253871-13473-DETAIL-03_02_2023-GO95MLD-1^07117002.0201303 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
564591324-2240-DETAIL-03_02_2023-GO95MLD-1^07117002.0201307 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
779516951-21473-DETAIL-03_02_2023-GO95MLD-1^07117002.0201308 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
779516951-21473-DETAIL-03_02_2023-GRDRODHI-1^07117002.0201308 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
779516951-21473-DETAIL-03_02_2023-SVCDEFLC-1^07117002.0201308 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
134762121-98473-DETAIL-03_09_2023-GUYLOINS-1^07117002.0202101 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
252373528-17443-DETAIL-03_09_2023-SVCENTCO-1^07117002.0205201 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
821256781-75473-DETAIL-03_06_2023-SVCDEFLC-1^07117002.0205205 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
821256781-75473-DETAIL-03_06_2023-SVCENTCO-1^07117002.0205205 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
400796143-72550-DETAIL-03_06_2023-GO95MLD-1^07117002.0205207 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
140102398-42143-DETAIL-03_09_2023-GO95MLD-1^07117002.0205208 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
140102398-42143-DETAIL-03_09_2023-SVCNEUT-1^07117002.0205208 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
549992088-89043-DETAIL-03_09_2023-GO95MLD-1^07117002.0205209 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
514988968-87943-DETAIL-03_09_2023-GO95MLD-1^07117002.0205210 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
465443938-7643-DETAIL-03_14_2023-GO95MLD-1^07117002.0205240 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
823181068-13543-DETAIL-03_06_2023-GO95MLD-1^07117002.0206203 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
823181068-13543-DETAIL-03_06_2023-GUYHINS-1^07117002.0206203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
464336682-93473-DETAIL-03_09_2023-GO95MLD-1^07117002.0206240 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
877805469-42173-DETAIL-03_08_2023-GO95MLD-1^07117002.0206702 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
877805469-42173-DETAIL-03_08_2023-GO95TCH-1^07117002.0206702 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
679973499-41973-DETAIL-03_08_2023-GO95HV-1^07117002.0206703 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
679973499-41973-DETAIL-03_08_2023-GO95MLD-1^07117002.0206703 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
332442599-20973-DETAIL-03_08_2023-GO95MLD-1^07117002.0206704 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
332442599-20973-DETAIL-03_08_2023-GUYHINS-1^07117002.0206704 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
145759974-32074-DETAIL-03_09_2023-GO95HV-1^07117002.0207100 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2028-03-09 | 3
145759974-32074-DETAIL-03_09_2023-GO95MLD-1^07117002.0207100 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
320769258-92743-DETAIL-03_09_2023-GUYNOINS-1^07117002.0207141 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
641334732-31880-DETAIL-03_06_2023-GO95MLD-1^07117002.0207240 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
448681668-16549-DETAIL-03_09_2023-GO95MLD-1^07117002.0207242 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
664123753-3859-DETAIL-03_15_2023-CLRTOPOL-2^07216001.0291606 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
664123753-3859-DETAIL-03_15_2023-GO95MLD-1^07216001.0291606 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
593149569-2859-DETAIL-03_13_2023-SVCENTBK-1^07216001.0291642 | OTHER | CA-NON-TIER | Distribution | 2023-03-13 | 2026-03-13 | 2
472634083-17049-DETAIL-03_01_2023-CLRTOPOL-1^07216001.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
472634083-17049-DETAIL-03_01_2023-GO95CL10-1^07216001.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
472634083-17049-DETAIL-03_01_2023-GO95HV-1^07216001.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2028-03-01 | 3
472634083-17049-DETAIL-03_01_2023-SVCENTCO-1^07216001.0291700 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
809444713-36049-DETAIL-03_01_2023-GO95MLD-1^07216001.0291702 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
575519823-45139-DETAIL-03_01_2023-GUYHINS-1^07216001.0291704 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
32509753-15049-DETAIL-03_01_2023-GO95MLD-1^07216001.0291706 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
32509753-15049-DETAIL-03_01_2023-SVCENTCO-1^07216001.0291706 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
858818363-17649-DETAIL-03_01_2023-GO95MLD-1^07216001.0291707 | OTHER | CA-NON-TIER | Distribution | 2023-03-01 | 2026-03-01 | 2
973861359-59073-DETAIL-03_07_2023-GUYHINS-1^07117002.0207802 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
890976109-63973-DETAIL-03_08_2023-GO95MLD-1^07117002.0207803 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
617481448-94243-DETAIL-03_09_2023-GO95CL10-1^07117002.0208102 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2028-03-09 | 3
617481448-94243-DETAIL-03_09_2023-GO95MLD-1^07117002.0208102 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
707103809-43809-DETAIL-03_09_2023-GO95MLD-1^07117002.0208103 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
220092558-73949-DETAIL-03_09_2023-GO95MLD-1^07117002.0208201 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
843213748-29443-DETAIL-03_06_2023-GO95HV-1^07117002.0208301 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2028-03-06 | 3
843213748-29443-DETAIL-03_06_2023-GO95MLD-1^07117002.0208301 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
318863679-68873-DETAIL-03_07_2023-GO95MLD-1^07117002.0208700 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
225308998-72143-DETAIL-03_09_2023-ENCHRW-1^07117002.0209102 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
392687578-34343-DETAIL-03_09_2023-GO95MLD-1^07117002.0209104 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
392687578-34343-DETAIL-03_09_2023-GO95TCH-1^07117002.0209104 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
713647878-77043-DETAIL-03_09_2023-GO95MLD-1^07117002.0209105 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
790122168-56943-DETAIL-03_09_2023-GO95MLD-1^07117002.0209106 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
47587978-70843-DETAIL-03_09_2023-GO95MLD-1^07117002.0209108 | OTHER | CA-TIER-2 | Distribution | 2023-03-09 | 2026-03-09 | 2
496099979-56873-DETAIL-03_07_2023-GO95MLD-1^07117002.0209701 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
886999211-10320-DETAIL-03_08_2023-GO95MLD-1^07117002.0210206 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
656590351-62520-DETAIL-03_07_2023-GO95BLTC-1^07117002.0210300 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2028-03-07 | 3
656590351-62520-DETAIL-03_07_2023-GUYHINS-1^07117002.0210300 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
444479671-78520-DETAIL-03_07_2023-GO95MLD-1^07117002.0210400 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
450243561-15520-DETAIL-03_07_2023-GO95MLD-1^07117002.0210401 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
115931461-34939-DETAIL-03_07_2023-GO95HV-1^07117002.0210403 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2028-03-07 | 3
115931461-34939-DETAIL-03_07_2023-GO95MLD-1^07117002.0210403 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
115931461-34939-DETAIL-03_07_2023-GO95TCH-1^07117002.0210403 | OTHER | CA-TIER-2 | Distribution | 2023-03-07 | 2026-03-07 | 2
359777726-71449-DTLSB-02_13_2024-GO95MLD-1^07216001.0199701 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
837604244-73559-DTLSB-02_13_2024-GO95MLD-1^07216001.0199800 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
191454138-9138-DTLSB-02_14_2024-GO95HV-1^07216001.0199900 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
191454138-9138-DTLSB-02_14_2024-GO95MLD-1^07216001.0199900 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
591589308-28259-DTLSB-02_14_2024-GO95MLD-1^07216001.0199901 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
367670523-18110-DTLSB-07_14_2022-GO95MLD-1^07216001.0210800 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
604108903-54811-ADMIN-06_24_2024-POLEDERP-1^07216001.0210801 | POLE | CA-NON-TIER | Distribution | 2024-06-24 | 2027-06-24 | 2
270142973-68010-ADMIN-10_13_2023-POLEDERP-1^07216001.0214802 | POLE | CA-NON-TIER | Distribution | 2023-10-13 | 2026-10-13 | 2
719399321-53559-DTLSB-02_15_2024-GO95MLD-1^07216001.0260000 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2029-02-15 | 3
894125789-14249-DTLSB-02_15_2024-GO95MLD-1^07216001.0260001 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
894125789-14249-DTLSB-02_15_2024-SVCRUBLG-1^07216001.0260001 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
648813343-55018-DETAIL-03_08_2023-SVCNEUT-1^07117002.0212002 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
425579493-41918-DETAIL-03_08_2023-GO95MLD-1^07117002.0212003 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
767027443-82418-DETAIL-03_08_2023-GUYHINS-1^07117002.0213000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-08 | 2026-03-08 | 2
605065249-3733-DETAIL-03_13_2023-GO95HV-1^07117002.0270501 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2028-03-13 | 3
605065249-3733-DETAIL-03_13_2023-GO95MLD-1^07117002.0270501 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2028-03-13 | 3
734775969-13833-DETAIL-03_14_2023-GO95BLTC-1^07117002.0270601 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2028-03-14 | 3
734775969-13833-DETAIL-03_14_2023-GO95MLD-1^07117002.0270601 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
734775969-13833-DETAIL-03_14_2023-GO95TCH-1^07117002.0270601 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
834542279-18833-DETAIL-03_14_2023-GO95MLD-1^07117002.0271600 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
991208238-7300-DETAIL-03_14_2023-GO95HV-1^07117002.0274700 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2028-03-14 | 3
793044638-57300-DETAIL-03_14_2023-GO95MLD-1^07117002.0275700 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
859864149-75549-DETAIL-03_14_2023-GO95MLD-1^07117002.0285900 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
729732029-26549-DETAIL-03_14_2023-GUYLOINS-1^07117002.0286801 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
704501219-6549-DETAIL-03_14_2023-GO95MLD-1^07117002.0286900 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
717784199-70333-DETAIL-03_13_2023-GO95HV-1^07117002.0289502 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2028-03-13 | 3
717784199-70333-DETAIL-03_13_2023-GO95MLD-1^07117002.0289502 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2026-03-13 | 2
386094579-79133-DETAIL-03_13_2023-GO95HV-1^07117002.0289602 | OTHER | CA-TIER-2 | Distribution | 2023-03-13 | 2028-03-13 | 3
675713995-90833-DETAIL-03_01_2023-SVCENTCO-1^07117002.0305903 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
853280068-76459-DETAIL-04_24_2023-GO95HV-1^07117003.0010700 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
104242278-96459-DETAIL-04_24_2023-GRDRODHI-1^07117003.0011700 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
433587888-81823-DETAIL-03_20_2023-GO95MLD-1^07117003.0016800 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
433587888-81823-DETAIL-03_20_2023-GRDRODHI-1^07117003.0016800 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
570972615-57363-DETAIL-04_24_2023-GO95HV-1^07117003.0020000 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
167118265-12663-DETAIL-04_24_2023-GO95HV-1^07117003.0022000 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
946578779-70949-DTLSB-02_16_2024-GO95MLD-1^07216001.0260005 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
946578779-70949-DTLSB-02_16_2024-SVCDEFLC-1^07216001.0260005 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
150290600-1949-DTLSB-02_16_2024-GO95MLD-1^07216001.0260007 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
150290600-1949-DTLSB-02_16_2024-SVCENTCO-1^07216001.0260007 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
76520389-33949-DTLSB-02_16_2024-SVCDEFLC-1^07216001.0260102 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
913189599-56849-DETAIL-02_16_2024-GUYHINS-1^07216001.0260104 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
736675268-62368-DTLSB-02_16_2024-SVCROAD-1^07216001.0260105 | OTHER | CA-NON-TIER | Distribution | 2024-02-16 | 2027-02-16 | 2
569295880-6939-DTLSB-02_19_2024-SVCDEFLC-1^07216001.0260201 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
712039879-95949-DTLSB-02_19_2024-GO95MLD-1^07216001.0260202 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
890117911-36059-DTLSB-02_19_2024-GO95MLD-1^07216001.0260205 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2029-02-19 | 3
967184669-8249-DTLSB-02_19_2024-GO95MLD-1^07216001.0260300 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
967184669-8249-DTLSB-02_19_2024-GRDRODHI-1^07216001.0260300 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
18885208-56208-DETAIL-05_10_2022-GO95MLD-1^07116001.0094901 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
355768306-17538-DETAIL-04_28_2022-GO95MLD-1^07116001.0095300 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
847241743-15338-DETAIL-04_28_2022-GO95MLD-1^07116001.0095301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
976627643-74318-DETAIL-04_28_2022-GO95MLD-1^07116001.0095401 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
976627643-74318-DETAIL-04_28_2022-GO95TCH-1^07116001.0095401 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
285997948-29948-DETAIL-05_10_2022-GO95MLD-1^07116001.0095702 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
948498906-10098-DETAIL-05_09_2022-GO95HV-1^07116001.0096101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
948498906-10098-DETAIL-05_09_2022-GO95MLD-1^07116001.0096101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
428328301-17859-DETAIL-05_09_2022-GO95TCH-1^07116001.0096200 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
668501461-39559-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096201 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
409461706-95768-ADMIN-10_24_2023-POLEREPL-1^07116001.0096202 | POLE | CA-TIER-2 | Distribution | 2023-10-24 | 2024-10-24 | 2
545238706-5798-DETAIL-05_09_2022-GO95HV-1^07116001.0096203 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
29644606-18078-DETAIL-05_09_2022-GO95MLD-1^07116001.0096206 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
29644606-18078-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096206 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
386141655-52663-DETAIL-04_24_2023-GO95HV-1^07117003.0085200 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
266070565-84663-DETAIL-04_24_2023-GO95MLD-1^07117003.0087000 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
677196265-15663-DETAIL-04_24_2023-GO95MLD-1^07117003.0088000 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
998235033-46033-DETAIL-03_14_2023-GO95MLD-1^07117003.0092002 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
386656305-24763-DETAIL-03_14_2023-GUYHINS-1^07117003.0093000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
238603515-64763-DETAIL-03_20_2023-GO95MLD-1^07117003.0093102 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
558277775-87263-DETAIL-04_24_2023-GO95HV-1^07117003.0101600 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
558277775-87263-DETAIL-04_24_2023-GO95MLD-1^07117003.0101600 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
31341935-65063-DETAIL-04_24_2023-GO95HV-1^07117003.0104700 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
509553835-28063-DETAIL-04_24_2023-GO95HV-1^07117003.0105600 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2028-04-24 | 3
646379935-7063-DETAIL-04_24_2023-GO95MLD-1^07117003.0105601 | OTHER | CA-TIER-2 | Distribution | 2023-04-24 | 2026-04-24 | 2
188644808-52223-DETAIL-03_14_2023-GO95MLD-1^07117003.0112602 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
864265743-51459-DETAIL-04_28_2022-SVCNEUT-1^07116001.0096304 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
244581331-32459-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096400 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
487176771-3249-DETAIL-05_09_2022-GO95GUYP-1^07116001.0097001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
487176771-3249-DETAIL-05_09_2022-GO95HV-1^07116001.0097001 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
487176771-3249-DETAIL-05_09_2022-GO95MLD-1^07116001.0097001 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
487176771-3249-DETAIL-05_09_2022-GUYHINS-1^07116001.0097001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
685074806-86898-DETAIL-05_09_2022-GO95HV-1^07116001.0097100 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
193880106-72106-DETAIL-05_09_2022-GO95MLD-1^07116001.0097102 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
193880106-72106-DETAIL-05_09_2022-GRDRODHI-1^07116001.0097102 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
193880106-72106-DETAIL-05_09_2022-GUYHINS-1^07116001.0097102 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
998172008-93223-DETAIL-03_14_2023-SVCENTCO-1^07117003.0112603 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
132331798-17123-DETAIL-03_14_2023-GO95MLD-1^07117003.0112604 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
132331798-17123-DETAIL-03_14_2023-GO95TCH-1^07117003.0112604 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
302752668-47023-DETAIL-03_14_2023-GO95MLD-1^07117003.0113703 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
726495948-53023-DETAIL-03_14_2023-GO95MLD-1^07117003.0113704 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
479946719-71824-DETAIL-03_14_2023-GUYHINS-1^07117003.0114800 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
479946719-71824-DETAIL-03_14_2023-SVCNEUT-1^07117003.0114800 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
643432318-48223-DETAIL-03_14_2023-GO95MLD-1^07117003.0114901 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
643432318-48223-DETAIL-03_14_2023-SVCENTCO-1^07117003.0114901 | OTHER | CA-TIER-2 | Distribution | 2023-03-14 | 2026-03-14 | 2
833381408-29823-DETAIL-03_20_2023-GO95MLD-1^07117004.0060700 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
3803328-73923-DETAIL-03_20_2023-GUYHINS-1^07117004.0061800 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
226646765-87765-DETAIL-03_20_2023-GO95MLD-1^07117004.0061830 | OTHER | CA-TIER-2 | Distribution | 2023-03-20 | 2026-03-20 | 2
585401406-92898-DETAIL-05_09_2022-GO95MLD-1^07116001.0098202 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
6395306-46788-DETAIL-05_09_2022-GO95HV-1^07116001.0099101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2027-05-09 | 3
6395306-46788-DETAIL-05_09_2022-GO95MLD-1^07116001.0099101 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
263734101-89659-DETAIL-05_09_2022-GO95MLD-1^07116001.0099102 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
682407571-46949-DETAIL-05_09_2022-GO95MLD-1^07116001.0099302 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
659504792-55901-DETAIL-05_05_2022-GO95MLD-1^07116001.0100000 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
706160382-66831-DETAIL-05_05_2022-GO95MLD-1^07116001.0100001 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
706160382-66831-DETAIL-05_05_2022-GRDRODHI-1^07116001.0100001 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
907159768-1439-DTLSB-02_19_2024-GO95MLD-1^07216001.0264800 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
286016858-76539-DTLSB-02_19_2024-GO95HV-1^07216001.0264801 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2029-02-19 | 3
286016858-76539-DTLSB-02_19_2024-GO95MLD-1^07216001.0264801 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
771236248-31849-DTLSB-02_19_2024-GO95MLD-1^07216001.0264901 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
820620798-41349-DTLSB-02_19_2024-SVCDEFLC-1^07216001.0265600 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
795896568-91949-DTLSB-02_19_2024-GO95CL10-1^07216001.0265603 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2029-02-19 | 3
795896568-91949-DTLSB-02_19_2024-GO95MLD-1^07216001.0265603 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
286237538-75149-DTLSB-02_19_2024-GO95MLD-1^07216001.0265702 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
286237538-75149-DTLSB-02_19_2024-SVCROAD-1^07216001.0265702 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
844820678-61849-DTLSB-02_19_2024-GO95CL10-1^07216001.0265800 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2029-02-19 | 3
844820678-61849-DTLSB-02_19_2024-GO95MLD-1^07216001.0265800 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
94793610-95610-DTLSB-02_19_2024-SVCDEFLC-1^07216001.0265801 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
447153654-57401-DETAIL-07_10_2023-GRDRODHI-1^07117001.0247102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
447153654-57401-DETAIL-07_10_2023-SVCENTBK-1^07117001.0247102 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
210373664-20050-DETAIL-07_10_2023-GO95MLD-1^07117001.0247104 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2026-07-10 | 2
215873624-13950-DETAIL-07_10_2023-GO95HV-1^07117001.0247300 | OTHER | CA-TIER-2 | Distribution | 2023-07-10 | 2028-07-10 | 3
956298558-53249-DETAIL-05_16_2022-GO95MLD-1^07117001.0303401 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
956298558-53249-ADMIN-09_24_2024-POLEDERP-1^07117001.0303401 | POLE | CA-TIER-2 | Distribution | 2024-09-24 | 2025-09-24 | 2
810058476-89159-DETAIL-05_05_2022-GUYLOINS-1^07117001.0308301 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
72174104-67659-DETAIL-05_16_2022-GUYHINS-1^07117001.0313700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
911940904-87659-DETAIL-05_16_2022-GO95MLD-1^07117001.0313800 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
978308124-90559-DETAIL-05_16_2022-ABNDEQPM-1^07117001.0314601 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
58804924-80959-DETAIL-05_16_2022-GO95MLD-1^07117001.0315501 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
662119534-54249-DETAIL-05_16_2022-GO95MLD-1^07117001.0316501 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
931839514-93259-DETAIL-05_16_2022-GO95TCH-1^07117001.0316800 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
188692054-67759-DETAIL-05_17_2022-GUYSLACK-1^07117001.0317500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
194739644-37759-DETAIL-05_16_2022-GO95MLD-1^07117001.0317501 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
507596974-13259-DETAIL-05_16_2022-GUYNOINS-1^07117001.0317941 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
323673490-74159-DETAIL-05_17_2022-GO95MLD-1^07117001.0319300 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
432227390-24159-DETAIL-05_17_2022-CLRTOUCH-1^07117001.0319301 | CONDUCTOR | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
432227390-24159-DETAIL-05_17_2022-GO95MLD-1^07117001.0319301 | OTHER | CA-NON-TIER | Distribution | 2022-05-17 | 2025-05-17 | 2
102616278-6253-ADMIN-03_15_2024-POLEDERP-1^07216001.0146501 | POLE | CA-NON-TIER | Distribution | 2024-03-15 | 2027-03-15 | 2
401164874-29850-ADMIN-10_13_2023-POLEDERP-1^07216001.0153705 | POLE | CA-NON-TIER | Distribution | 2023-10-13 | 2026-10-13 | 2
658280194-28059-ADMIN-10_13_2023-POLEDERP-1^07216001.0156400 | POLE | CA-NON-TIER | Distribution | 2023-10-13 | 2026-10-13 | 2
549682474-73849-ADMIN-07_15_2024-POLEDERP-1^07216001.0160801 | POLE | CA-NON-TIER | Distribution | 2024-07-15 | 2027-07-15 | 2
585995913-14391-ADMIN-06_27_2023-DISTHDWR-1^07216001.0165000 | CONNECTION DEVICE | CA-NON-TIER | Distribution | 2023-06-27 | 2026-06-27 | 2
19004572-31083-ADMIN-11_06_2023-POLEDERP-1^07216001.0176010 | POLE | CA-NON-TIER | Distribution | 2023-11-06 | 2026-11-06 | 2
778465114-77659-DTLSB-02_14_2024-GO95MLD-1^07216001.0180200 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
432934463-27659-DTLSB-02_14_2024-GO95MLD-1^07216001.0180201 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
432934463-27659-DTLSB-02_14_2024-SVCENTCO-1^07216001.0180201 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
57499168-88459-DTLSB-02_14_2024-GO95TCH-1^07216001.0180203 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2027-02-14 | 2
713742013-1859-DTLSB-02_15_2024-GO95MLD-1^07216001.0184200 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
363564723-90049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277602 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
925288993-4339-DETAIL-03_14_2023-ABNDEQPM-1^07114001.0277604 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
25509503-51049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277605 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
670449313-74449-DETAIL-03_14_2023-GO95HV-1^07114001.0277607 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
670449313-74449-DETAIL-03_14_2023-SVCROAD-1^07114001.0277607 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
204717793-42049-DETAIL-03_14_2023-GO95HV-1^07114001.0277608 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
754181803-3049-DETAIL-03_14_2023-GO95MLD-1^07114001.0277701 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
482909773-85749-DETAIL-03_14_2023-GO95MLD-1^07114001.0277800 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
118497593-63749-DETAIL-03_14_2023-GUYNOINS-1^07114001.0278900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
646933783-64049-DETAIL-03_14_2023-GO95MLD-1^07114001.0278902 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
870864943-30249-DETAIL-03_16_2023-GO95HV-1^07114001.0280700 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
915749884-21984-DETAIL-03_14_2023-GO95HV-1^07114001.0281201 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
915749884-21984-DETAIL-03_14_2023-GO95MLD-1^07114001.0281201 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
675380084-88838-DETAIL-03_14_2023-GO95MLD-1^07114001.0281202 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
916964008-15008-DETAIL-03_16_2023-GO95HV-1^07114001.0281600 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
563275008-36008-DETAIL-03_16_2023-GO95HV-1^07114001.0281602 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
563275008-36008-DETAIL-03_16_2023-SVCENTCO-1^07114001.0281602 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
242770747-47259-DETAIL-03_16_2023-GO95HV-1^07114001.0281640 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
735701683-47749-DETAIL-03_16_2023-GO95TCH-1^07114001.0281703 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
735701683-47749-DETAIL-03_16_2023-GUYHINS-1^07114001.0281703 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
164092914-83149-DETAIL-03_20_2023-GO95HV-1^07114001.0282302 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
164092914-83149-DETAIL-03_20_2023-SVCRUBLG-1^07114001.0282302 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
693435643-5149-DETAIL-03_16_2023-ENCHRW-1^07114001.0282400 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
371215134-22639-DETAIL-03_20_2023-GO95MLD-1^07114001.0282401 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
345737782-90790-DETAIL-05_02_2022-GO95MLD-1^07116001.0100101 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2025-05-02 | 2
199168482-46240-DETAIL-05_02_2022-GO95HV-1^07116001.0100102 | OTHER | CA-TIER-2 | Distribution | 2022-05-02 | 2027-05-02 | 3
125226416-62470-DETAIL-05_05_2022-GO95MLD-1^07116001.0100103 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
995855342-39539-DETAIL-05_09_2022-GO95MLD-1^07116001.0100200 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
995855342-39539-DETAIL-05_09_2022-GO95SVC-1^07116001.0100200 | OTHER | CA-TIER-2 | Distribution | 2022-05-09 | 2025-05-09 | 2
204906452-80240-DETAIL-05_05_2022-GO95MLD-1^07116001.0101000 | OTHER | CA-TIER-2 | Distribution | 2022-05-05 | 2025-05-05 | 2
64256171-12349-DETAIL-05_02_2022-GO95MLD-1^07116001.0167905 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
64256171-12349-DETAIL-05_02_2022-GUYHINS-1^07116001.0167905 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
64256171-12349-DETAIL-05_02_2022-SVCENTCO-1^07116001.0167905 | OTHER | CA-NON-TIER | Distribution | 2022-05-02 | 2025-05-02 | 2
353643394-30049-DETAIL-03_15_2023-GO95MLD-1^07114001.0284201 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
284772464-89049-DETAIL-03_15_2023-GO95HV-1^07114001.0284202 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
542275154-9049-DETAIL-03_14_2023-GO95MLD-1^07114001.0284204 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
655863244-88839-DETAIL-03_14_2023-GO95MLD-1^07114001.0284205 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
97001434-3849-DETAIL-03_14_2023-GO95MLD-1^07114001.0284206 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
356246814-16049-DETAIL-03_20_2023-GO95MLD-1^07114001.0284302 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
794359904-89549-DETAIL-03_15_2023-GO95MLD-1^07114001.0284304 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
511942124-68049-DETAIL-03_20_2023-GO95MLD-1^07114001.0284305 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
645992814-11849-DETAIL-03_20_2023-GO95HV-1^07114001.0284306 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
645992814-11849-DETAIL-03_20_2023-GO95MLD-1^07114001.0284306 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
729469404-20149-DETAIL-03_20_2023-GO95MLD-1^07114001.0284308 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
729469404-20149-DETAIL-03_20_2023-SVCWIND-1^07114001.0284308 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
306134834-33149-DETAIL-03_20_2023-GO95MLD-1^07114001.0284401 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
998037034-21139-DETAIL-03_20_2023-GO95MLD-1^07114001.0284402 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
958482644-53259-DETAIL-03_20_2023-GO95MLD-1^07114001.0285100 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
641251134-76049-DETAIL-03_20_2023-GO95HV-1^07114001.0285300 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2028-03-20 | 3
781798804-60349-DETAIL-03_20_2023-GO95MLD-1^07114001.0285402 | OTHER | CA-NON-TIER | Distribution | 2023-03-20 | 2026-03-20 | 2
610112214-42249-DETAIL-03_16_2023-GO95HV-1^07114001.0299701 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
967853093-62249-DETAIL-03_16_2023-GO95TCH-1^07114001.0299702 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
13502633-92049-DETAIL-03_16_2023-GO95MLD-1^07114001.0299801 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
726604724-82249-DETAIL-03_16_2023-SVCENTCO-1^07114001.0299802 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
544281055-86449-DETAIL-03_15_2023-GO95CL10-1^07114001.0325100 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
901226358-25259-DETAIL-03_15_2023-GO95MLD-1^07114001.0325200 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
227604895-57449-DETAIL-03_15_2023-GO95MLD-1^07114001.0326001 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
479028418-99653-DETAIL-03_08_2023-GO95HV-1^07117002.0193201 | OTHER | CA-TIER-2 | Distribution | 2023-03-08 | 2028-03-08 | 3
977863555-5133-DETAIL-03_06_2023-GO95MLD-1^07117002.0194001 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
867255255-84033-DETAIL-03_06_2023-GO95MLD-1^07117002.0195000 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2028-03-06 | 3
93184385-99733-DETAIL-03_01_2023-GO95MLD-1^07117002.0195002 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
799279195-833-DETAIL-03_01_2023-SVCENTCO-1^07117002.0195003 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
985132668-93113-DETAIL-03_01_2023-GO95MLD-1^07117002.0195100 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
793354535-92733-DETAIL-03_01_2023-GO95MLD-1^07117002.0195102 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
528908345-69933-DETAIL-03_01_2023-GO95MLD-1^07117002.0195203 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
223569139-64773-DETAIL-03_01_2023-GO95MLD-1^07117002.0195206 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
44096745-55733-DETAIL-03_01_2023-GO95MLD-1^07117002.0195207 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
44096745-55733-DETAIL-03_01_2023-GUYHINS-1^07117002.0195207 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
44096745-55733-DETAIL-03_01_2023-SVCROAD-1^07117002.0195207 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
934354827-85949-DETAIL-03_15_2023-GO95MLD-1^07114001.0340801 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
169522597-70849-DETAIL-03_15_2023-GUYHINS-1^07114001.0341100 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
602926537-73949-DETAIL-03_15_2023-GO95HV-1^07114001.0341600 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
973289557-61849-DETAIL-03_15_2023-SVCENTCO-1^07114001.0342200 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
988508837-41849-DETAIL-03_15_2023-SVCENTCO-1^07114001.0342201 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
625442707-96849-DETAIL-03_15_2023-GO95MLD-1^07114001.0342203 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
693108937-93949-DETAIL-03_15_2023-GO95HV-1^07114001.0342701 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
899895947-64949-DETAIL-03_15_2023-GO95HV-1^07114001.0342802 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
899895947-64949-DETAIL-03_15_2023-GO95MLD-1^07114001.0342802 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
206045157-22849-DETAIL-03_15_2023-GUYHINS-1^07114001.0343201 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
360305677-44849-DETAIL-03_15_2023-GO95HV-1^07114001.0346301 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2028-03-15 | 3
275387797-17349-AUDIT-04_20_2023-GO95HV-1^07114001.0347200 | OTHER | CA-TIER-2 | Distribution | 2023-04-20 | 2028-04-20 | 3
74172557-65039-DETAIL-03_15_2023-GO95CL10-1^07114001.0347201 | OTHER | CA-TIER-2 | Distribution | 2023-03-15 | 2028-03-15 | 3
913490657-75849-DETAIL-03_15_2023-GO95HV-1^07114001.0347202 | OTHER | CA-TIER-2 | Distribution | 2023-03-15 | 2028-03-15 | 3
4178087-29249-DETAIL-03_15_2023-SVCENTCO-1^07114001.0347203 | OTHER | CA-NON-TIER | Distribution | 2023-03-15 | 2026-03-15 | 2
561170835-39059-DETAIL-03_15_2023-SVCENTCO-1^07114001.0348200 | OTHER | CA-TIER-2 | Distribution | 2023-03-15 | 2026-03-15 | 2
159575610-6459-DETAIL-07_14_2022-GO95MLD-1^07116001.0040402 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
29314580-75249-DETAIL-07_14_2022-GO95MLD-1^07116001.0040505 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
274523380-67249-DETAIL-07_14_2022-SVCWIND-1^07116001.0040506 | OTHER | CA-NON-TIER | Distribution | 2022-07-14 | 2025-07-14 | 2
338762130-72359-DETAIL-07_14_2022-SVCWIND-1^07116001.0041500 | OTHER | CA-TIER-2 | Distribution | 2022-07-14 | 2025-07-14 | 2
222254818-94359-DETAIL-05_16_2022-GO95HV-1^07116001.0059000 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
192531085-79133-DETAIL-03_01_2023-GO95MLD-1^07117002.0196201 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
395532565-65733-DETAIL-03_01_2023-GO95MLD-1^07117002.0196202 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
956857275-69949-DETAIL-03_01_2023-GO95MLD-1^07117002.0196203 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
103871565-76549-DETAIL-03_01_2023-GO95MLD-1^07117002.0196204 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
773942945-7633-DETAIL-03_01_2023-GO95MLD-1^07117002.0196205 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
221961054-82060-DETAIL-03_01_2023-GO95MLD-1^07117002.0196206 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
508115445-96249-DETAIL-03_01_2023-GO95TCH-1^07117002.0196207 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
508115445-96249-DETAIL-03_01_2023-SVCROAD-1^07117002.0196207 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
13160985-84233-DETAIL-03_06_2023-SVCENTCO-1^07117002.0196300 | OTHER | CA-TIER-2 | Distribution | 2023-03-06 | 2026-03-06 | 2
503720875-17733-DETAIL-03_01_2023-GO95MLD-1^07117002.0196302 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
503720875-17733-DETAIL-03_01_2023-SVCENTCO-1^07117002.0196302 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
238597635-27533-DETAIL-03_01_2023-GO95MLD-1^07117002.0197205 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
428584218-36459-DETAIL-05_10_2022-GUYLOINS-1^07116001.0059401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
563683890-26459-DETAIL-05_10_2022-GO95MLD-1^07116001.0059402 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2027-05-10 | 3
34067098-6249-DETAIL-05_10_2022-ABNDEQPM-1^07116001.0059404 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2027-05-10 | 3
34067098-6249-DETAIL-05_10_2022-GO95MLD-1^07116001.0059404 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
34067098-6249-DETAIL-05_10_2022-GUYHINS-1^07116001.0059404 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
34067098-6249-DETAIL-05_10_2022-GUYNOINS-1^07116001.0059404 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
939888238-56859-DETAIL-05_10_2022-GO95MLD-1^07116001.0059500 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
810976490-8539-DETAIL-05_11_2022-GO95HV-1^07116001.0059601 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2027-05-11 | 3
810976490-8539-DETAIL-05_11_2022-GUYHINS-1^07116001.0059601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
323277288-5249-DETAIL-05_11_2022-GO95MLD-1^07116001.0059800 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
323277288-5249-DETAIL-05_11_2022-SVCNEUT-1^07116001.0059800 | OTHER | CA-TIER-2 | Distribution | 2022-05-11 | 2025-05-11 | 2
860415749-16349-DETAIL-04_28_2022-SVCDEFLC-1^07116001.0087603 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
826029279-25559-DETAIL-05_16_2022-GO95HV-1^07116001.0090400 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2027-05-16 | 3
569450461-93559-DETAIL-05_16_2022-GUYNOINS-1^07116001.0090401 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
103698331-92559-DETAIL-05_16_2022-GO95MLD-1^07116001.0090600 | OTHER | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
695401181-13959-DETAIL-05_16_2022-GO95HV-1^07116001.0090800 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2027-05-16 | 3
695401181-13959-DETAIL-05_16_2022-GO95MLD-1^07116001.0090800 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
695401181-13959-DETAIL-05_16_2022-GRDRODHI-1^07116001.0090800 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
427396412-22459-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0146102 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
678009902-31459-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0146103 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
404208601-74549-DETAIL-02_28_2024-GO95HV-1^07113001.0146700 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
268629071-71459-DETAIL-02_21_2024-GO95HV-1^07113001.0147101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
268629071-71459-DETAIL-02_21_2024-GO95MLD-1^07113001.0147101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
268629071-71459-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0147101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
749146491-61459-DETAIL-02_21_2024-GUYNOINS-1^07113001.0147103 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
507392402-40459-DETAIL-02_21_2024-GUYNOINS-1^07113001.0148102 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
322021711-75549-DETAIL-02_28_2024-GO95HV-1^07113001.0148800 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
960699002-26849-DETAIL-02_21_2024-GRDRODHI-1^07113001.0149100 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
704323231-16549-DETAIL-02_28_2024-GO95HV-1^07113001.0149901 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
469547205-88205-DETAIL-02_22_2024-GO95MLD-1^07113001.0154603 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
237099035-24359-DETAIL-02_22_2024-SVCENTCO-1^07113001.0156300 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
975785055-64949-DETAIL-02_22_2024-GO95HV-1^07113001.0156302 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
975785055-64949-DETAIL-02_22_2024-GUYHINS-1^07113001.0156302 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
432988055-21849-DETAIL-02_22_2024-GO95HV-1^07113001.0157200 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
912798694-52059-DETAIL-02_29_2024-GO95HV-1^07113001.0157900 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
820400585-53359-DETAIL-02_29_2024-GO95MLD-1^07113001.0157901 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
705187265-23549-DETAIL-02_21_2024-GO95MLD-1^07113001.0158001 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
13955005-20149-DETAIL-02_29_2024-GO95HV-1^07113001.0158801 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
402066675-33749-DETAIL-02_29_2024-GO95MLD-1^07113001.0159900 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
695372075-13749-DETAIL-02_29_2024-GO95MLD-1^07113001.0159902 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
39335163-61049-DETAIL-02_29_2024-GO95MLD-1^07113001.0159903 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
39335163-61049-DETAIL-02_29_2024-GO95TCH-1^07113001.0159903 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
713742013-1859-DTLSB-02_15_2024-SVCDEFLC-1^07216001.0184200 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
713742013-1859-DTLSB-02_15_2024-SVCENTCO-1^07216001.0184200 | OTHER | CA-NON-TIER | Distribution | 2024-02-15 | 2027-02-15 | 2
420755518-8259-DTLSB-02_14_2024-GO95HV-1^07216001.0184300 | OTHER | CA-NON-TIER | Distribution | 2024-02-14 | 2029-02-14 | 3
892121373-76092-DTLSB-02_05_2024-GO95HV-1^07216001.0185000 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2029-02-05 | 3
261195548-26839-DTLSB-02_05_2024-SVCDEFLC-1^07216001.0185004 | OTHER | CA-NON-TIER | Distribution | 2024-02-05 | 2027-02-05 | 2
356876938-80859-DTLSB-02_13_2024-GO95MLD-1^07216001.0185100 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
996977408-96049-DTLSB-02_13_2024-ABNDEQPM-1^07216001.0185101 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
498990123-27239-DTLSB-02_13_2024-GO95MLD-1^07216001.0185102 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
498990123-27239-DTLSB-02_13_2024-SVCROAD-1^07216001.0185102 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
786537698-45559-DTLSB-02_13_2024-GO95HV-1^07216001.0185105 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
321098473-64259-DTLSB-02_13_2024-GO95MLD-1^07216001.0186201 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2029-02-13 | 3
42777973-35259-DTLSB-02_13_2024-GO95MLD-1^07216001.0186300 | OTHER | CA-NON-TIER | Distribution | 2024-02-13 | 2027-02-13 | 2
551585525-18525-DETAIL-02_27_2024-GO95HV-1^07113002.0071102 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
96146456-99849-DETAIL-02_27_2024-GO95HV-1^07113002.0073300 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
96146456-99849-DETAIL-02_27_2024-GO95MLD-1^07113002.0073300 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
96146456-99849-DETAIL-02_27_2024-SVCRUBLG-1^07113002.0073300 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
132488233-50333-DETAIL-02_28_2024-GO95MLD-1^07113002.0073340 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
132488233-50333-DETAIL-02_28_2024-GO95TCH-1^07113002.0073340 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
78607916-549-DETAIL-02_28_2024-GO95MLD-1^07113002.0073400 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
210466236-92349-DETAIL-02_28_2024-SVCENTCO-1^07113002.0074300 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
603962126-50549-DETAIL-02_27_2024-GO95MLD-1^07113002.0076001 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
219904800-76739-DETAIL-02_20_2024-GO95MLD-1^07113002.0180100 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
8854370-72839-DETAIL-02_20_2024-GO95MLD-1^07113002.0180103 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
8854370-72839-AUDIT-03_06_2024-GO95TCH-1^07113002.0180103 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
448835992-4449-AUDIT-03_06_2024-GO95MLD-1^07113002.0180104 | OTHER | CA-NON-TIER | Distribution | 2024-03-06 | 2027-03-06 | 2
781139191-47249-DETAIL-02_21_2024-SVCENTCO-1^07113002.0180105 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
98896422-37049-DETAIL-02_21_2024-SVCDEFLC-1^07113002.0180200 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
606686036-77149-DETAIL-02_28_2024-GO95HV-1^07113002.0180500 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
606686036-77149-DETAIL-02_28_2024-GO95MLD-1^07113002.0180500 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
345952881-76349-DETAIL-02_20_2024-GO95MLD-1^07113002.0181004 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
345952881-76349-DETAIL-02_20_2024-SVCDEFLC-1^07113002.0181004 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
345952881-76349-DETAIL-02_20_2024-SVCROAD-1^07113002.0181004 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
771070582-15249-DETAIL-02_20_2024-GO95MLD-1^07113002.0181006 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
402905961-28349-DETAIL-02_20_2024-GO95MLD-1^07113002.0181008 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
402905961-28349-DETAIL-02_20_2024-GO95TCH-1^07113002.0181008 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
195720123-17959-DETAIL-02_20_2024-GO95MLD-1^07113002.0181009 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
80643456-25012-DETAIL-05_10_2022-GO95MLD-1^07116001.0091401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
63708869-12949-ADMIN-10_23_2023-POLEDERP-1^07116001.0091500 | POLE | CA-TIER-2 | Distribution | 2023-10-23 | 2024-10-23 | 2
843143401-76959-DETAIL-05_16_2022-GO95MLD-1^07116001.0091900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
843143401-76959-DETAIL-05_16_2022-GO95TCH-1^07116001.0091900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
843143401-76959-DETAIL-05_16_2022-SVCNEUT-1^07116001.0091900 | OTHER | CA-NON-TIER | Distribution | 2022-05-16 | 2025-05-16 | 2
221284461-79449-DETAIL-05_10_2022-GO95HV-1^07116001.0092401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
221284461-79449-DETAIL-05_10_2022-GO95MLD-1^07116001.0092401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
292789790-17339-DETAIL-02_20_2024-SVCENTCO-1^07113002.0182003 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
997400580-19349-DETAIL-02_20_2024-GO95BLTC-1^07113002.0182005 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
997400580-19349-DETAIL-02_20_2024-GO95MLD-1^07113002.0182005 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
335774791-16349-DETAIL-02_20_2024-GO95MLD-1^07113002.0182008 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
691230532-43449-DETAIL-02_27_2024-GO95HV-1^07113002.0182300 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
135930326-72639-DETAIL-02_27_2024-GO95HV-1^07113002.0182400 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2029-02-27 | 3
774986832-54559-DETAIL-02_27_2024-GO95HV-1^07113002.0182402 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2029-02-27 | 3
774986832-54559-DETAIL-02_27_2024-GO95MLD-1^07113002.0182402 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
774986832-54559-DETAIL-02_27_2024-GUYHINS-1^07113002.0182402 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
851101005-12449-DETAIL-02_28_2024-GO95HV-1^07113002.0182501 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
851101005-12449-DETAIL-02_28_2024-GO95MLD-1^07113002.0182501 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
851101005-12449-DETAIL-02_28_2024-SVCROAD-1^07113002.0182501 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
135169465-18349-DETAIL-02_27_2024-GO95MLD-1^07113002.0182600 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
621021815-73349-DETAIL-02_28_2024-SVCROAD-1^07113002.0182604 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
153429672-23649-DETAIL-02_20_2024-SVCENTCO-1^07113002.0183000 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
412829903-63249-DETAIL-02_20_2024-GO95HV-1^07113002.0183002 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
412829903-63249-DETAIL-02_20_2024-GO95MLD-1^07113002.0183002 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
547206549-4149-DETAIL-02_27_2024-GO95MLD-1^07113002.0183200 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
547206549-4149-DETAIL-02_27_2024-GO95TCH-1^07113002.0183200 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
547206549-4149-DETAIL-02_27_2024-GUYHINS-1^07113002.0183200 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
533183332-77949-DETAIL-02_27_2024-GO95MLD-1^07113002.0183203 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
468051635-65539-DETAIL-02_27_2024-GO95MLD-1^07113002.0183601 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
468051635-65539-DETAIL-02_27_2024-GRDRODHI-1^07113002.0183601 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
468051635-65539-DETAIL-02_27_2024-SVCDEFLC-1^07113002.0183601 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
221284461-79449-DETAIL-05_10_2022-SVCNEUT-1^07116001.0092401 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
71249331-12559-DETAIL-05_12_2022-GO95HV-1^07116001.0092800 | OTHER | CA-NON-TIER | Distribution | 2022-05-12 | 2027-05-12 | 3
71249331-12559-DETAIL-05_12_2022-GUYSLACK-1^07116001.0092800 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-12 | 2025-05-12 | 2
795069089-21759-DETAIL-05_10_2022-GO95MLD-1^07116001.0093102 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
821192669-65059-DETAIL-04_28_2022-GO95CL10-1^07116001.0093202 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
821192669-65059-DETAIL-04_28_2022-GO95TCH-1^07116001.0093202 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
821192669-65059-ADMIN-06_24_2024-POLEDERP-1^07116001.0093202 | POLE | CA-TIER-2 | Distribution | 2024-06-24 | 2025-06-24 | 2
730114300-21449-DETAIL-04_28_2022-GO95HV-1^07116001.0093301 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2027-04-28 | 3
886204799-74439-DETAIL-02_27_2024-SVCDEFLC-1^07113002.0184103 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
714140195-26349-DETAIL-02_27_2024-GO95MLD-1^07113002.0184503 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
714140195-26349-DETAIL-02_27_2024-GRDRODHI-1^07113002.0184503 | OTHER | CA-TIER-2 | Distribution | 2024-02-27 | 2027-02-27 | 2
100188046-37949-DETAIL-02_27_2024-SVCENTCO-1^07113002.0184702 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
100188046-37949-DETAIL-02_27_2024-SVCENTCO-2^07113002.0184702 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
8388169-42539-DETAIL-02_19_2024-GO95MLD-1^07113002.0185001 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
983052509-6149-DETAIL-02_19_2024-GO95MLD-1^07113002.0185002 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
328081649-9149-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0185100 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
65161629-39149-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0185103 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
65161629-39149-DETAIL-03_26_2024-GO95MLD-1^07113002.0185103 | OTHER | CA-TIER-2 | Distribution | 2024-03-26 | 2027-03-26 | 2
829956439-60849-DETAIL-02_19_2024-GO95MLD-1^07113002.0185104 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
829956439-60849-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0185104 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
829956439-60849-DETAIL-02_19_2024-SVCENTCO-1^07113002.0185104 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
294008549-69149-DETAIL-02_19_2024-GO95HV-1^07113002.0185105 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2029-02-19 | 3
294008549-69149-DETAIL-02_19_2024-GO95MLD-1^07113002.0185105 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
702929319-32639-DETAIL-02_19_2024-GO95BLTC-1^07113002.0185201 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2029-02-19 | 3
363136419-249-DETAIL-02_19_2024-SVCENTCO-1^07113002.0185202 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
263724329-9839-DETAIL-02_19_2024-GO95MLD-1^07113002.0186001 | OTHER | CA-NON-TIER | Distribution | 2024-02-19 | 2027-02-19 | 2
376316589-99449-DETAIL-02_19_2024-GO95MLD-1^07113002.0186003 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
376316589-99449-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0186003 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
376316589-99449-DETAIL-02_19_2024-SVCDEFLC-2^07113002.0186003 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
853279570-88149-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0187100 | OTHER | CA-TIER-2 | Distribution | 2024-02-19 | 2027-02-19 | 2
122204661-83249-DETAIL-02_20_2024-GO95HV-1^07113002.0193900 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
122204661-83249-DETAIL-02_20_2024-GO95TCH-1^07113002.0193900 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
159437443-25643-DETAIL-10_12_2022-GUYHINS-3^668005/08 8X7/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
159437443-25643-DETAIL-10_12_2022-GUYHINS-4^668005/08 8X7/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
520575753-22953-DETAIL-10_12_2022-GO95HV-1^668005/08 8X8/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
520575753-22953-DETAIL-10_12_2022-GUYHINS-1^668005/08 8X8/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
520575753-22953-DETAIL-10_12_2022-GUYHINS-2^668005/08 8X8/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
520575753-22953-DETAIL-10_12_2022-GUYHINS-3^668005/08 8X8/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
520575753-22953-DETAIL-10_12_2022-GUYHINS-4^668005/08 8X8/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
490156254-99719-ADMIN-04_25_2018-POLEREPL-1^668036/00 10/032 | POLE | FHCA | Transmission | 2018-04-25 | 2023-03-25 | 2
573957698-15719-DETAIL-08_14_2023-POLETOP-1^668036/00 5/050 | POLE | CA-TIER-2 | Transmission | 2023-08-14 | 2024-08-14 | 2
707777058-52819-DETAIL-11_14_2023-INSULBRK-1^668036/00 5/051 | INSULATOR AND BUSHING | FHCA | Transmission | 2023-11-14 | 2026-11-14 | 2
135787739-83919-ADMIN-10_28_2022-UBPBXARM-1^668036/00 5/053 | CROSSARM | FHCA | Transmission | 2022-10-28 | 2025-10-28 | 2
153330331-9619-DETAIL-08_11_2023-POLEREPL-1^668036/00 6/049 | POLE | CA-TIER-2 | Transmission | 2023-08-11 | 2024-08-11 | 2
262189751-69619-DETAIL-08_11_2023-POLETOP-1^668036/00 8/049 | POLE | CA-TIER-2 | Transmission | 2023-08-11 | 2024-08-11 | 2
220562058-66719-DETAIL-08_14_2023-POLETOP-1^668036/00 8/050 | POLE | CA-TIER-2 | Transmission | 2023-08-14 | 2024-08-14 | 2
843365700-71332-DTLTRT-06_06_2024-GO95HV-1^668084/00 1/001 | OTHER | FHCA | Transmission | 2024-06-06 | 2029-06-06 | 3
744571179-92332-DTLTRT-06_06_2024-GO95HV-1^668084/00 1A/001 | OTHER | FHCA | Transmission | 2024-06-06 | 2029-06-06 | 3
671544610-70341-DTLTRT-05_16_2024-GO95HV-1^668084/00 2/001 | OTHER | FHCA | Transmission | 2024-05-16 | 2029-05-16 | 3
233550391-20339-DETAIL-02_28_2024-SVCROAD-1^07113001.0030001 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
233550391-20339-DETAIL-02_28_2024-SVCWIND-1^07113001.0030001 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
856343831-29549-DETAIL-02_28_2024-GO95MLD-1^07113001.0030100 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
577535704-81649-DETAIL-02_28_2024-GO95CL10-1^07113001.0030303 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
577535704-81649-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0030303 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
136929681-42649-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0030400 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
889172731-82339-DETAIL-02_28_2024-GO95HV-1^07113001.0030402 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
889172731-82339-DETAIL-02_28_2024-GO95MLD-1^07113001.0030402 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
889172731-82339-DETAIL-02_28_2024-GRDRODHI-1^07113001.0030402 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
919740296-22296-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0030403 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
270981249-75773-DETAIL-03_02_2023-GUYNOINS-1^07117002.0198201 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
283091625-35433-DETAIL-03_02_2023-GUYHINS-1^07117002.0198203 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
171010965-7415-DETAIL-03_02_2023-GRDRODHI-1^07117002.0198204 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
846455065-45733-DETAIL-03_01_2023-GO95MLD-1^07117002.0198302 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
874885655-15733-DETAIL-03_01_2023-GO95MLD-1^07117002.0198303 | OTHER | CA-TIER-2 | Distribution | 2023-03-01 | 2026-03-01 | 2
618004741-49973-DETAIL-03_02_2023-GO95MLD-1^07117002.0200200 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
230266141-48373-DETAIL-03_02_2023-GO95HV-1^07117002.0200300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2028-03-02 | 3
230266141-48373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200300 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
976650441-9373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200302 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
649420451-61773-DETAIL-03_02_2023-GO95MLD-1^07117002.0200304 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
649420451-61773-DETAIL-03_02_2023-GO95TCH-1^07117002.0200304 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
734413803-73803-DETAIL-03_02_2023-SVCENTCO-1^07117002.0200308 | OTHER | CA-TIER-2 | Distribution | 2023-03-02 | 2026-03-02 | 2
687665710-24649-DETAIL-03_16_2023-GO95HV-1^07113001.0042504 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
838431011-55159-DETAIL-03_16_2023-GO95TCH-1^07113001.0042506 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
422029880-16649-DETAIL-03_16_2023-GO95TCH-1^07113001.0042600 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
605801380-1749-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0042601 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
605801380-1749-DETAIL-03_16_2023-GUYHINS-1^07113001.0042601 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
134526310-3649-DETAIL-03_16_2023-GO95MLD-1^07113001.0043501 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
717153908-66908-DETAIL-03_16_2023-GO95MLD-1^07113001.0043502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
507479578-82678-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0043503 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
507479578-82678-DETAIL-03_16_2023-ENCHRW-1^07113001.0043503 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
667492620-69249-DETAIL-03_16_2023-GO95MLD-1^07113001.0043505 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
240988908-39908-DETAIL-03_16_2023-GO95MLD-1^07113001.0043507 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
376448404-5159-DETAIL-03_16_2023-GO95MLD-1^07113001.0044502 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
325747100-52649-DETAIL-03_16_2023-GO95MLD-1^07113001.0044601 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
543464189-7189-DETAIL-03_16_2023-GO95CL10-1^07113001.0044906 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
543464189-7189-DETAIL-03_16_2023-GO95MLD-1^07113001.0044906 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
817988410-73449-DETAIL-03_16_2023-GO95MLD-1^07113001.0045500 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
817988410-73449-DETAIL-03_16_2023-GUYHINS-1^07113001.0045500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
650499560-45849-DETAIL-03_21_2023-GO95HV-1^07113001.0049200 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
927753733-85239-DETAIL-03_21_2023-GO95MLD-1^07113001.0055500 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
745913313-31439-DETAIL-03_21_2023-GUYHINS-1^07113001.0056500 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
729330686-83159-DETAIL-03_21_2023-ABNDEQPM-1^07113001.0056501 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2028-03-21 | 3
324817739-33749-DETAIL-03_21_2023-SVCROOF-1^07113001.0056503 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
968527623-13049-DETAIL-03_21_2023-CLRTOUCH-1^07113001.0056504 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
968527623-13049-DETAIL-03_21_2023-GO95MLD-1^07113001.0056504 | OTHER | CA-NON-TIER | Distribution | 2023-03-21 | 2026-03-21 | 2
436195543-58549-DETAIL-03_14_2023-GO95HV-1^07114001.0275401 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
436195543-58549-DETAIL-03_14_2023-GO95MLD-1^07114001.0275401 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
436195543-58549-DETAIL-03_14_2023-GUYHINS-1^07114001.0275401 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
44967753-22849-DETAIL-03_14_2023-GO95MLD-1^07114001.0275402 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
801770213-22339-DETAIL-03_14_2023-GO95MLD-1^07114001.0275403 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
801770213-22339-DETAIL-03_14_2023-GO95TCH-1^07114001.0275403 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
127389073-30539-DETAIL-03_14_2023-GO95MLD-1^07114001.0276300 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
504011173-53839-DETAIL-03_14_2023-GO95HV-1^07114001.0276301 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
504011173-53839-DETAIL-03_14_2023-GO95MLD-1^07114001.0276301 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
739267393-6649-DETAIL-03_14_2023-GO95MLD-1^07114001.0276302 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
217786823-31839-DETAIL-03_14_2023-GO95MLD-1^07114001.0276305 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
34853713-68739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276307 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
469225214-82049-DETAIL-03_16_2023-GO95HV-1^07113001.0059602 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2028-03-16 | 3
241732556-36059-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0059700 | CONDUCTOR | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
241732556-36059-DETAIL-03_16_2023-GO95MLD-1^07113001.0059700 | OTHER | CA-NON-TIER | Distribution | 2023-03-16 | 2026-03-16 | 2
749783914-86949-DETAIL-02_26_2024-SVCDEFLC-1^07113001.0085100 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
667059414-56949-DETAIL-02_26_2024-COPLLEAN-1^07113001.0085101 | POLE | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
695661694-14949-DETAIL-02_26_2024-GO95HV-1^07113001.0085401 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
450345734-36359-DETAIL-02_26_2024-CUTOUTAR-1^07113001.0085501 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
450345734-36359-DETAIL-02_26_2024-CUTOUTAR-3^07113001.0085501 | LIGHTNING ARRESTER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
351693001-89849-DETAIL-02_22_2024-GUYLOINS-1^07113001.0092701 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
450398291-49849-DETAIL-02_22_2024-GUYLOINS-1^07113001.0093700 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
448333921-5359-DETAIL-02_22_2024-GUYNOINS-1^07113001.0094600 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
591292221-88849-DETAIL-02_22_2024-GUYNOINS-1^07113001.0094602 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
568228508-39508-DETAIL-02_22_2024-GO95HV-1^07113001.0097400 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
665791531-37849-DETAIL-02_22_2024-GO95HV-1^07113001.0097500 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2029-02-22 | 3
446094741-58839-DETAIL-02_22_2024-GO95MLD-1^07113001.0099300 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
446094741-58839-DETAIL-02_22_2024-SVCROAD-1^07113001.0099300 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
205296851-69039-DETAIL-02_22_2024-GO95MLD-1^07113001.0099401 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
222728894-69539-DETAIL-02_29_2024-GO95HV-1^07113001.0101902 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
222728894-69539-DETAIL-02_29_2024-GO95MLD-1^07113001.0101902 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
222728894-69539-DETAIL-02_29_2024-SVCDEFLC-1^07113001.0101902 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
848516801-7749-DETAIL-02_22_2024-SVCDEFLC-1^07113001.0102001 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
182012412-13359-DETAIL-02_22_2024-GO95MLD-1^07113001.0103000 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
182012412-13359-DETAIL-02_22_2024-SVCDEFLC-1^07113001.0103000 | OTHER | CA-NON-TIER | Distribution | 2024-02-22 | 2027-02-22 | 2
658777181-52359-DETAIL-02_29_2024-RISEBKSP-1^07113001.0105501 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
490847043-47339-DETAIL-03_14_2023-GO95MLD-1^07114001.0276401 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
299599463-89139-DETAIL-03_14_2023-GO95MLD-1^07114001.0276402 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
441286663-18239-DETAIL-03_14_2023-GO95MLD-1^07114001.0276403 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
476905423-68949-DETAIL-03_14_2023-SVCENTCO-1^07114001.0276408 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
350520403-3239-DETAIL-03_14_2023-GO95MLD-1^07114001.0276409 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
690941203-70439-DETAIL-03_14_2023-GO95HV-1^07114001.0276410 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
690941203-70439-DETAIL-03_14_2023-GO95MLD-1^07114001.0276410 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
82668533-96739-DETAIL-03_14_2023-GO95HV-1^07114001.0276500 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
82668533-96739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276500 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
323678083-22049-DETAIL-03_14_2023-GO95HV-1^07114001.0276502 | OTHER | CA-NON-TIER | Distribution | 2023-03-14 | 2028-03-14 | 3
323678083-22049-DETAIL-03_14_2023-GUYSLACK-1^07114001.0276502 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2023-03-14 | 2026-03-14 | 2
323678083-22049-ADMIN-08_07_2024-COPLLEAN-1^07114001.0276502 | POLE | CA-NON-TIER | Distribution | 2024-08-07 | 2027-08-07 | 2
230274649-30719-ADMIN-06_24_2021-POLEDERP-1^668005/00 16/075 | POLE | CA-NON-TIER | Transmission | 2021-06-24 | 2024-06-24 | 2
712251775-26619-ADMIN-07_27_2021-INSULDMG-1^668005/00 16/096 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
6952356-58819-DETAIL-08_18_2022-GO95CL10-1^668005/00 16/097 | OTHER | FHCA | Transmission | 2022-08-18 | 2025-08-18 | 2
629769885-46619-ADMIN-06_15_2021-INSULDMG-1^668005/00 17/096 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
984474435-32619-ADMIN-07_27_2021-INSULDMG-1^668005/00 18/095 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
404293295-66619-ADMIN-06_15_2021-INSULDMG-1^668005/00 18/096 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
920488276-91719-ADMIN-07_29_2021-INSULDMG-1^668005/00 18/097 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-29 | 2024-07-29 | 2
252204106-96619-ADMIN-06_15_2021-INSULDMG-1^668005/00 19/096 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
351659886-59669-ADMIN-05_24_2021-INSULDMG-1^668005/00 2/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
17731646-8769-ADMIN-07_30_2021-INSULDMG-1^668005/00 2/062 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-30 | 2024-07-30 | 2
885396288-80619-ADMIN-10_08_2020-POLEDERP-1^668005/00 2/074 | POLE | CA-NON-TIER | Transmission | 2020-10-08 | 2023-10-08 | 2
8781459-31719-ADMIN-05_24_2021-INSULDMG-1^668005/00 2/076 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
535834089-93819-ADMIN-05_24_2021-INSULDMG-1^668005/00 2/077 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
917110323-14749-DETAIL-02_29_2024-GO95MLD-1^07113001.0107101 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
528843563-62749-DETAIL-02_29_2024-GO95MLD-1^07113001.0108000 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
870068290-34459-DETAIL-02_29_2024-GO95HV-1^07113001.0112001 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2029-02-28 | 3
146825361-33459-DETAIL-02_29_2024-GUYNOINS-1^07113001.0113002 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
146825361-33459-DETAIL-02_29_2024-GUYNOINS-2^07113001.0113002 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
145230481-19859-DETAIL-02_29_2024-SVCENTCO-1^07113001.0114000 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
909261378-39549-DETAIL-02_28_2024-GO95HV-1^07113001.0125000 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
61370858-28549-DETAIL-02_28_2024-GO95HV-1^07113001.0133900 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2029-02-28 | 3
845942228-98549-AUDIT-03_12_2024-GO95HV-1^07113001.0133901 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2029-03-12 | 3
314956630-88349-AUDIT-03_12_2024-GO95MLD-1^07113001.0136800 | OTHER | CA-NON-TIER | Distribution | 2024-03-12 | 2027-03-12 | 2
225748111-42149-DETAIL-02_20_2024-CLRTOUCH-1^07113001.0137200 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
601839621-25249-DETAIL-02_20_2024-GO95MLD-1^07113001.0137201 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
728706-38119-ADMIN-07_29_2024-POLEDERP-1^668005/00 3/063 | POLE | CA-NON-TIER | Transmission | 2024-07-29 | 2027-07-29 | 2
77149886-69419-ADMIN-07_29_2024-POLEDERP-1^668005/00 3/070 | POLE | CA-NON-TIER | Transmission | 2024-07-29 | 2027-07-29 | 2
677378269-71719-DETAIL-07_28_2022-GO95MLD-1^668005/00 3/076 | OTHER | CA-NON-TIER | Transmission | 2022-07-28 | 2025-07-28 | 2
260256969-10019-DTLTRT-08_03_2022-GO95HV-1^668005/00 3/079 | OTHER | CA-NON-TIER | Transmission | 2022-08-03 | 2027-08-03 | 3
321481731-84219-ADMIN-06_15_2021-INSULDMG-1^668005/00 3/086 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
740023151-28219-ADMIN-12_31_2018-POLEREPL-1^668005/00 3/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
374973143-26419-ADMIN-06_15_2021-INSULDMG-1^668005/00 3/092 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
64429563-88919-DETAIL-08_17_2022-GO95MLD-1^668005/00 3/094 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
847333024-29519-ADMIN-07_27_2021-INSULDMG-1^668005/00 3/095 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
847333024-29519-DTLTRT-08_17_2022-GO95HV-1^668005/00 3/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2027-08-17 | 3
91669975-27819-DTLTRT-08_17_2022-GO95MLD-1^668005/00 3/096 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
238393216-18619-ADMIN-07_27_2021-INSULDMG-1^668005/00 3/097 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
549869080-70180-DTLTRT-06_27_2022-GO95HV-1^668005/00 3A/025 | OTHER | CA-NON-TIER | Transmission | 2022-06-27 | 2027-06-27 | 3
341937059-68059-DETAIL-06_28_2022-GO95MLD-1^668005/00 3X/026 | OTHER | CA-NON-TIER | Transmission | 2022-06-28 | 2025-06-28 | 2
666175239-67239-DETAIL-08_17_2022-GO95MLD-1^668005/00 3X/094 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
617777094-98469-DTLTRT-07_20_2022-GO95HV-1^668005/00 4/055 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
839794095-36669-ADMIN-05_24_2021-INSULDMG-1^668005/00 4/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
369903281-49739-DETAIL-02_20_2024-GO95HV-1^07113001.0137300 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2029-02-20 | 3
369903281-49739-DETAIL-02_20_2024-GO95MLD-1^07113001.0137300 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
419367090-2749-DETAIL-02_26_2024-GO95HV-1^07113001.0137400 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2029-02-26 | 3
419367090-2749-DETAIL-02_26_2024-SVCENTCO-1^07113001.0137400 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
362960871-95739-DETAIL-02_20_2024-SVCENTCO-1^07113001.0138203 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
362960871-95739-DETAIL-02_20_2024-SVCENTCO-2^07113001.0138203 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
945641341-28149-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0138204 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
140852151-10559-DETAIL-02_21_2024-CLMBTRE-1^07113001.0138205 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
483051691-91149-DETAIL-02_20_2024-GO95MLD-1^07113001.0138207 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
494176860-86860-DETAIL-02_21_2024-GO95TCH-1^07113001.0138208 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
284275011-89049-DETAIL-02_26_2024-SVCENTCO-1^07113001.0138300 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
759103671-39459-DETAIL-02_26_2024-GO95MLD-1^07113001.0138301 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
943079326-48619-DETAIL-08_11_2019-POLEDERP-1^668005/00 4/097 | POLE | FHCA | Transmission | 2019-08-11 | 2022-08-11 | 2
236888910-40169-DTLTRT-07_15_2022-GO95HV-1^668005/00 5/048 | OTHER | CA-NON-TIER | Transmission | 2022-07-15 | 2027-07-15 | 3
236888910-40169-DTLTRT-07_15_2022-UBPRMSHD-1^668005/00 5/048 | CONNECTION DEVICE | CA-NON-TIER | Transmission | 2022-07-15 | 2025-07-15 | 2
646545995-86669-ADMIN-07_30_2021-INSULDMG-2^668005/00 5/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-30 | 2024-07-30 | 2
846967306-90769-ADMIN-07_30_2021-INSULDMG-1^668005/00 5/060 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-30 | 2024-07-30 | 2
943129906-25769-ADMIN-05_24_2021-INSULDMG-1^668005/00 5/061 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
579286256-36419-DETAIL-07_27_2022-GO95HV-1^668005/00 5/069 | OTHER | CA-NON-TIER | Transmission | 2022-07-27 | 2027-07-27 | 3
758640858-63519-ADMIN-12_31_2018-POLEDERP-1^668005/00 5/071 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
855689779-50019-ADMIN-06_15_2021-INSULDMG-1^668005/00 5/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
194601591-37119-ADMIN-08_05_2020-POLEDERP-1^668005/00 5/084 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
244256192-42319-ADMIN-06_15_2021-INSULDMG-1^668005/00 5/088 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
387931973-76419-ADMIN-06_15_2021-INSULDMG-1^668005/00 5/092 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
708848154-59519-ADMIN-08_11_2019-POLEDERP-1^668005/00 5/095 | POLE | FHCA | Transmission | 2019-08-11 | 2022-08-11 | 2
213760735-33619-DTLTRT-08_17_2022-GO95HV-1^668005/00 5/096 | OTHER | FHCA | Transmission | 2022-08-17 | 2027-08-17 | 3
90412435-3569-DTLTRT-07_20_2022-GO95HV-1^668005/00 6/056 | OTHER | CA-NON-TIER | Transmission | 2022-07-20 | 2027-07-20 | 3
126931225-42669-DTLTRT-07_21_2022-GUYSLACK-1^668005/00 6/058 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-07-21 | 2025-07-21 | 2
223592381-4481-DETAIL-05_10_2022-GRDRODHI-1^07116001.0093801 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
853184051-64959-DETAIL-05_12_2022-GO95MLD-1^07116001.0093803 | OTHER | CA-TIER-2 | Distribution | 2022-05-12 | 2025-05-12 | 2
237271520-32520-DETAIL-05_10_2022-GO95MLD-1^07116001.0093805 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2025-05-10 | 2
462760441-14959-DETAIL-05_10_2022-GO95MLD-1^07116001.0093900 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
462760441-14959-DETAIL-05_10_2022-GUYSLACK-1^07116001.0093900 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
462760441-14959-DETAIL-05_10_2022-SVCWIND-1^07116001.0093900 | OTHER | CA-NON-TIER | Distribution | 2022-05-10 | 2025-05-10 | 2
182901370-76349-DETAIL-05_10_2022-GO95HV-1^07116001.0094102 | OTHER | CA-TIER-2 | Distribution | 2022-05-10 | 2027-05-10 | 3
865004411-52849-DETAIL-05_16_2022-GUYHINS-1^07116001.0094201 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2022-05-16 | 2025-05-16 | 2
368084071-20649-DETAIL-04_28_2022-GO95MLD-1^07116001.0094400 | OTHER | CA-TIER-2 | Distribution | 2022-04-28 | 2025-04-28 | 2
601530954-43119-ADMIN-06_15_2021-INSULDMG-1^668005/00 6/094 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
833206964-79519-ADMIN-07_27_2021-INSULDMG-1^668005/00 6/095 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
75679945-73619-ADMIN-07_27_2021-INSULDMG-1^668005/00 6/096 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
967460597-43719-ADMIN-07_29_2021-INSULDMG-1^668005/00 6/098 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-29 | 2024-07-29 | 2
967460597-43719-DTLTRT-08_18_2022-GO95HV-1^668005/00 6/098 | OTHER | FHCA | Transmission | 2022-08-18 | 2027-08-18 | 3
88670411-8119-ADMIN-08_05_2020-POLEDERP-1^668005/00 6A/084 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
924510516-27669-ADMIN-05_24_2021-INSULDMG-1^668005/00 7/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
334783196-10419-DTLTRT-07_26_2022-INSULDMG-1^668005/00 7/067 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2022-07-26 | 2025-07-26 | 2
899890468-4519-ADMIN-12_31_2018-POLEDERP-1^668005/00 7/071 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
694379788-66519-DTLTRT-07_28_2022-GUYSLACK-1^668005/00 7/072 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-07-28 | 2025-07-28 | 2
177701189-80719-ADMIN-05_24_2021-INSULDMG-1^668005/00 7/076 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
216715300-80019-ADMIN-06_15_2021-INSULDMG-1^668005/00 7/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
843274411-4119-ADMIN-12_31_2018-POLEREPL-1^668005/00 7/083 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
871205111-58119-ADMIN-08_05_2020-POLEDERP-1^668005/00 7/084 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
800616191-62219-ADMIN-06_15_2021-INSULDMG-1^668005/00 7/085 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
450342225-65129-DETAIL-04_26_2022-GO95HV-1^06143012.0257404 | OTHER | FHCA | Distribution | 2022-04-26 | 2027-04-26 | 3
450342225-65129-DETAIL-04_26_2022-GO95MLD-1^06143012.0257404 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
69780505-37129-DETAIL-04_26_2022-RISEGRD-1^06143012.0258201 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
24290384-47429-DETAIL-04_26_2022-GO95MLD-1^06143012.0258203 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
24290384-47429-DETAIL-04_26_2022-GRDRODHI-1^06143012.0258203 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
407613294-39429-DETAIL-04_19_2022-GO95MLD-1^06143012.0360100 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
407613294-39429-DETAIL-04_19_2022-XARMSPCR-1^06143012.0360100 | CROSSARM | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
752491174-15629-DETAIL-04_20_2022-SVCENTCO-1^06143012.0364002 | OTHER | FHCA | Distribution | 2022-04-20 | 2025-04-20 | 2
370260344-86729-DETAIL-04_21_2022-GO95MLD-1^06143012.0364600 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
370260344-86729-DETAIL-04_21_2022-GRDRODHI-1^06143012.0364600 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
347436773-45729-DETAIL-04_21_2022-GO95CL10-1^06143012.0365500 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
347436773-45729-DETAIL-04_21_2022-GO95MLD-1^06143012.0365500 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
440361903-38729-DETAIL-04_21_2022-GO95MLD-1^06143012.0365702 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
440361903-38729-DETAIL-04_21_2022-GUYHINS-1^06143012.0365702 | ANCHOR/GUY | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
440361903-38729-DETAIL-04_21_2022-INSULDMG-1^06143012.0365702 | INSULATOR AND BUSHING | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
377060493-18729-DETAIL-04_21_2022-GO95MLD-1^06143012.0365802 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
913892371-32349-DETAIL-02_26_2024-GO95MLD-1^07113001.0138405 | OTHER | CA-NON-TIER | Distribution | 2024-02-26 | 2027-02-26 | 2
14590471-21149-DETAIL-02_28_2024-GO95TCH-1^07113001.0138803 | OTHER | CA-NON-TIER | Distribution | 2024-02-28 | 2027-02-28 | 2
415708831-43249-DETAIL-02_20_2024-GO95MLD-1^07113001.0139101 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
749227563-48049-DETAIL-02_21_2024-SVCENTCO-1^07113001.0139200 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
785412681-40559-DETAIL-02_20_2024-ENCHRW-1^07113001.0139201 | OTHER | CA-NON-TIER | Distribution | 2024-02-20 | 2027-02-20 | 2
518393921-10349-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0139202 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
973739811-87049-DETAIL-02_21_2024-GO95MLD-1^07113001.0139203 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
413355611-32339-DETAIL-02_21_2024-GO95MLD-1^07113001.0139205 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
328064671-8749-DETAIL-03_26_2024-GO95HV-1^07113001.0139206 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2029-03-26 | 3
328064671-8749-DETAIL-03_26_2024-GO95MLD-1^07113001.0139206 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
328064671-8749-DETAIL-03_26_2024-SVCDEFLC-1^07113001.0139206 | OTHER | CA-NON-TIER | Distribution | 2024-03-26 | 2027-03-26 | 2
55390411-47449-DETAIL-02_27_2024-GO95MLD-1^07113001.0139800 | OTHER | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
600831394-39629-DETAIL-05_04_2022-GUYHINS-1^06143013.0190501 | ANCHOR/GUY | FHCA | Distribution | 2022-05-04 | 2025-05-04 | 2
674784334-18229-DETAIL-05_04_2022-GO95MLD-1^06143013.0190602 | OTHER | FHCA | Distribution | 2022-05-04 | 2025-05-04 | 2
312768164-90829-DETAIL-05_02_2022-GO95HV-1^06143013.0192301 | OTHER | FHCA | Distribution | 2022-05-02 | 2027-05-02 | 3
20404931-35931-DETAIL-04_04_2023-GO95HV-1^06143013.0237001 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
839059494-23222-DETAIL-02_14_2018-SVCWIND-1^06143013.0238601 | OTHER | CA-TIER-2 | Distribution | 2018-02-14 | 2023-01-14 | 2
131164484-15429-DETAIL-04_04_2023-GUYHINS-1^06143013.0239001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-04 | 2026-04-04 | 2
871862474-2429-DETAIL-04_04_2023-GO95MLD-1^06143013.0241001 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2026-04-04 | 2
871862474-2429-ADMIN-04_21_2023-GO95TCH-1^06143013.0241001 | OTHER | CA-TIER-2 | Distribution | 2023-04-21 | 2026-04-21 | 2
961891363-10239-DETAIL-04_03_2023-GO95MLD-1^06143013.0333600 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
549125377-75377-DETAIL-04_03_2023-GO95HV-1^06143013.0333801 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
549125377-75377-DETAIL-04_03_2023-GO95MLD-1^06143013.0333801 | OTHER | FHCA | Distribution | 2023-04-03 | 2028-04-03 | 3
263007377-37377-DETAIL-04_03_2023-RISESTRP-1^06143013.0333802 | OTHER | FHCA | Distribution | 2023-04-03 | 2026-04-03 | 2
40770663-75829-AUDIT-04_12_2023-GO95MLD-1^06143013.0336600 | OTHER | FHCA | Distribution | 2023-04-12 | 2026-04-12 | 2
953701183-42933-DETAIL-04_04_2023-GO95HV-1^06143014.0141001 | OTHER | CA-TIER-2 | Distribution | 2023-04-04 | 2028-04-04 | 3
240426316-31280-DETAIL-04_03_2023-GO95HV-1^06143014.0146102 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
240426316-31280-DETAIL-04_03_2023-GO95MLD-1^06143014.0146102 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2026-04-03 | 2
756404523-72071-DETAIL-04_03_2023-GO95HV-1^06143014.0162200 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
28300813-6670-DETAIL-04_03_2023-GO95HV-1^06143014.0173200 | OTHER | CA-TIER-2 | Distribution | 2023-04-03 | 2028-04-03 | 3
294736160-49269-ADMIN-08_05_2020-POLEDERP-1^668005/00 8/051 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
740415916-67669-ADMIN-05_24_2021-INSULDMG-1^668005/00 8/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
650948587-21519-ADMIN-07_29_2024-POLEDERP-1^668005/00 8/070 | POLE | CA-NON-TIER | Transmission | 2024-07-29 | 2027-07-29 | 2
101950940-90019-ADMIN-06_15_2021-INSULDMG-1^668005/00 8/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-06-15 | 2024-06-15 | 2
107683022-319-ADMIN-12_31_2018-POLEREPL-1^668005/00 8/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
340260784-55719-DTLTRT-08_17_2022-GO95MLD-1^668005/00 8/094 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
392724784-92119-ADMIN-07_27_2021-INSULDMG-1^668005/00 8/095 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
313224153-18160-DETAIL-04_06_2023-GO95HV-1^06143014.0232500 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
108564033-24940-DETAIL-04_06_2023-GO95HV-1^06143014.0232701 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
492241556-52529-DETAIL-04_06_2023-GRDRODHI-1^06143014.0232800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
492241556-52529-DETAIL-04_06_2023-RISEGRD-1^06143014.0232800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
461377293-54421-DETAIL-04_06_2023-GO95MLD-1^06143014.0233800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
635670793-17751-DETAIL-04_06_2023-ABNDEQPM-1^06143014.0234700 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
937892213-34992-DETAIL-04_06_2023-GO95HV-1^06143014.0235800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
754813113-41061-ADMIN-04_21_2023-GO95TCH-1^06143014.0235802 | OTHER | CA-TIER-2 | Distribution | 2023-04-21 | 2026-04-21 | 2
401213923-20950-DETAIL-04_06_2023-GO95HV-1^06143014.0236702 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
401213923-20950-DETAIL-04_06_2023-GUYHINS-1^06143014.0236702 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
60492413-54470-DETAIL-04_06_2023-GO95MLD-1^06143014.0236800 | OTHER | CA-TIER-2 | Distribution | 2023-04-06 | 2028-04-06 | 3
960651505-29929-DETAIL-04_06_2023-GUYHINS-1^06143014.0237700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-04-06 | 2026-04-06 | 2
589954683-33291-DETAIL-04_05_2023-GO95MLD-1^06143014.0240801 | OTHER | CA-TIER-2 | Distribution | 2023-04-05 | 2026-04-05 | 2
868382711-229-DETAIL-04_05_2023-GO95BLTC-1^06143014.0241800 | OTHER | CA-TIER-2 | Distribution | 2023-04-05 | 2028-04-05 | 3
259974013-98334-DETAIL-05_01_2024-GO95HV-1^06143015.0334900 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
120511613-89334-DETAIL-05_01_2024-GO95HV-1^06143015.0335800 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
674948213-29334-DETAIL-05_01_2024-GO95HV-1^06143015.0335900 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
674948213-29334-DETAIL-05_01_2024-XARMSPCR-1^06143015.0335900 | CROSSARM | CA-TIER-2 | Distribution | 2024-05-01 | 2025-05-01 | 2
60863934-54934-DETAIL-05_01_2024-GO95MLD-1^06143015.0336700 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
60863934-54934-DETAIL-05_01_2024-GUYHINS-1^06143015.0336700 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-05-01 | 2027-05-01 | 2
569841534-98934-DETAIL-05_01_2024-GO95MLD-1^06143015.0336701 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
998889023-21434-DETAIL-05_01_2024-GO95HV-1^06143015.0336801 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
397981134-83534-DETAIL-05_01_2024-GO95HV-1^06143015.0337700 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
392724784-92119-DTLTRT-08_17_2022-GO95MLD-1^668005/00 8/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
370510318-63719-DTLTRT-08_18_2022-GO95HV-1^668005/00 8/098 | OTHER | FHCA | Transmission | 2022-08-18 | 2027-08-18 | 3
842102516-18669-ADMIN-05_24_2021-INSULDMG-1^668005/00 9/059 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
490413016-27769-ADMIN-05_24_2021-INSULDMG-1^668005/00 9/061 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
205465429-70919-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 9/078 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-03 | 2025-08-03 | 2
464531090-11019-DETAIL-12_31_2018-POLEREPL-1^668005/00 9/079 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
464531090-11019-DTLTRT-08_03_2022-POLETOP-1^668005/00 9/079 | POLE | CA-NON-TIER | Transmission | 2022-08-03 | 2025-08-03 | 2
348136981-46219-DTLTRT-08_15_2022-ANCHIDLE-1^668005/00 9/086 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-15 | 2025-08-15 | 2
761348222-20319-ADMIN-12_31_2018-POLEREPL-1^668005/00 9/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
478434335-48335-ADMIN-09_16_2021-XARMSPCR-1^06147014.0010501 | CROSSARM | FHCA | Distribution | 2021-09-16 | 2024-09-16 | 2
892532726-77769-DETAIL-07_25_2022-GO95HV-1^668005/00 1/062 | OTHER | CA-NON-TIER | Transmission | 2022-07-25 | 2027-07-25 | 3
13004688-64519-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/072 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
440679059-59919-ADMIN-07_27_2021-INSULDMG-1^668005/00 1/079 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
320165151-75019-ADMIN-07_27_2021-INSULDMG-1^668005/00 1/081 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
8645721-73219-DTLTRT-08_15_2022-GUYSLACK-1^668005/00 1/086 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-15 | 2025-08-15 | 2
974713941-87219-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/087 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
969697962-31319-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/088 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
751232583-99419-ADMIN-06_15_2021-INSULDMG-1^668005/00 1/093 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
725614684-68519-ADMIN-07_27_2021-INSULDMG-1^668005/00 1/095 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-07-27 | 2024-07-27 | 2
725614684-68519-DTLTRT-08_17_2022-GO95MLD-1^668005/00 1/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
725614684-68519-DTLTRT-08_17_2022-UBPBXARM-1^668005/00 1/095 | CROSSARM | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
978875306-37619-ADMIN-06_15_2021-INSULDMG-1^668005/00 1/097 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
373724260-75369-ADMIN-08_05_2020-POLEDERP-1^668005/00 10/052 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
623039326-47769-ADMIN-05_24_2021-INSULDMG-1^668005/00 10/061 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-05-24 | 2024-05-24 | 2
698409783-96883-DETAIL-03_23_2023-GO95MLD-1^06142016.0081904 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
682855060-5734-DETAIL-03_27_2023-CLRTOPOL-1^06142016.0082701 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
486362114-36114-DETAIL-03_27_2023-GO95MLD-1^06142016.0082803 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
646911214-38214-ADMIN-04_21_2023-GO95TCH-1^06142016.0082804 | OTHER | CA-NON-TIER | Distribution | 2023-04-21 | 2026-04-21 | 2
587856314-33414-DETAIL-03_27_2023-GO95HV-1^06142016.0082805 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
587856314-33414-DETAIL-03_27_2023-GO95MLD-1^06142016.0082805 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
587856314-33414-DETAIL-03_27_2023-GRDRODHI-1^06142016.0082805 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
587856314-33414-DETAIL-03_27_2023-SVCROAD-1^06142016.0082805 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
532251514-14514-DETAIL-03_27_2023-GO95HV-1^06142016.0082806 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
532251514-14514-DETAIL-03_27_2023-GO95MLD-1^06142016.0082806 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
369308514-50614-DETAIL-03_28_2023-GO95MLD-1^06142016.0082807 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
858553614-15614-DETAIL-03_27_2023-GO95HV-1^06142016.0082900 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
564106824-58824-DETAIL-03_29_2023-GO95HV-1^06142016.0084706 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
955890924-13924-DETAIL-03_29_2023-GO95HV-1^06142016.0084707 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
955890924-13924-DETAIL-03_29_2023-GO95MLD-1^06142016.0084707 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
797715924-17924-DETAIL-02_13_2018-SVCROAD-1^06142016.0084708 | OTHER | CA-NON-TIER | Distribution | 2018-02-13 | 2023-01-13 | 2
682349924-11024-DETAIL-03_29_2023-GO95MLD-1^06142016.0084709 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
682349924-11024-DETAIL-03_29_2023-SVCROAD-1^06142016.0084709 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
233824254-49254-DETAIL-03_28_2023-GO95TCH-1^06142016.0084804 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
742819454-94554-DETAIL-03_28_2023-GO95MLD-1^06142016.0084806 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
850950784-12884-DETAIL-02_05_2018-SVCWIND-1^06142016.0084903 | OTHER | CA-NON-TIER | Distribution | 2018-02-05 | 2023-01-05 | 2
822182984-24094-DETAIL-03_29_2023-GO95MLD-1^06142016.0084904 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
822182984-24094-DETAIL-03_29_2023-SVCROAD-1^06142016.0084904 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
46356594-49849-DETAIL-03_30_2023-GO95MLD-1^06142016.0084908 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
46356594-49849-DETAIL-03_30_2023-GO95TCH-1^06142016.0084908 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
472653794-60894-DETAIL-03_30_2023-ABNDEQPM-1^06142016.0084909 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
302532614-86614-DETAIL-03_29_2023-GO95HV-1^06142016.0085000 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
950229814-61914-DETAIL-03_29_2023-GO95MLD-1^06142016.0085002 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
115041114-83114-DETAIL-03_29_2023-GO95HV-1^06142016.0085100 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
5377114-30214-DETAIL-03_29_2023-GO95HV-1^06142016.0085101 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
5377114-30214-DETAIL-03_29_2023-INSULDMG-1^06142016.0085101 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
76823134-98134-DETAIL-03_29_2023-GO95HV-1^06142016.0085400 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2028-03-29 | 3
76823134-98134-DETAIL-03_29_2023-GO95MLD-1^06142016.0085400 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
895700534-78534-DETAIL-03_29_2023-GO95MLD-1^06142016.0085402 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
41845934-1044-DETAIL-03_29_2023-GO95MLD-1^06142016.0085501 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
226010833-22833-DETAIL-02_27_2024-GUYHINS-1^07113001.0139906 | ANCHOR/GUY | CA-NON-TIER | Distribution | 2024-02-27 | 2027-02-27 | 2
276143562-62559-DETAIL-02_29_2024-SVCENTCO-1^07113001.0140703 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
467893852-87459-DETAIL-02_29_2024-GO95MLD-1^07113001.0140801 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
467893852-87459-DETAIL-02_29_2024-SVCENTCO-1^07113001.0140801 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
2900382-26459-DETAIL-02_29_2024-SVCDEFLC-1^07113001.0140902 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
774222211-57959-DETAIL-02_21_2024-CLRTOUCH-1^07113001.0141000 | CONDUCTOR | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
866393691-27359-DETAIL-02_21_2024-GO95HV-1^07113001.0141102 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
278902702-29249-DETAIL-02_29_2024-GO95TCH-1^07113001.0142900 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
278902702-29249-DETAIL-02_29_2024-SVCDEFLC-1^07113001.0142900 | OTHER | CA-NON-TIER | Distribution | 2024-02-29 | 2027-02-28 | 2
159273761-94949-DETAIL-02_21_2024-GO95MLD-1^07113001.0143000 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
699011261-18359-DETAIL-02_21_2024-GO95HV-1^07113001.0143101 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2029-02-21 | 3
355159461-58949-DETAIL-02_21_2024-GO95MLD-1^07113001.0143201 | OTHER | CA-NON-TIER | Distribution | 2024-02-21 | 2027-02-21 | 2
910101824-22824-DETAIL-04_25_2024-GO95HV-1^06142016.0161900 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
120239824-70924-DETAIL-04_25_2024-GO95HV-1^06142016.0162200 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
203992044-84044-DETAIL-04_25_2024-GO95MLD-1^06142016.0163001 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
82785244-8244-DETAIL-04_29_2024-GO95MLD-1^06142016.0174200 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2029-04-29 | 3
552239344-1444-DETAIL-04_25_2024-SVCDEFLC-1^06142016.0174700 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
665195444-89444-DETAIL-04_25_2024-ENCHRW-1^06142016.0174800 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
411073864-16864-AUDIT-06_24_2024-GO95HV-1^06142016.0175202 | OTHER | CA-NON-TIER | Distribution | 2024-06-24 | 2029-06-24 | 3
919162964-14964-DETAIL-04_29_2024-GO95HV-1^06142016.0175300 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2029-04-29 | 3
258729064-81164-DETAIL-04_29_2024-SVCDEFLC-1^06142016.0175402 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
501094164-49164-DETAIL-04_25_2024-GO95HV-1^06142016.0175500 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
501094164-49164-DETAIL-04_25_2024-GO95MLD-1^06142016.0175500 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
856384384-67384-DETAIL-04_29_2024-GO95HV-1^06142016.0175501 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2029-04-29 | 3
152552484-95484-DETAIL-04_29_2024-GO95HV-1^06142016.0175502 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2029-04-29 | 3
234298484-2584-DETAIL-04_25_2024-GO95HV-1^06142016.0175600 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
920916584-48584-DETAIL-04_25_2024-GO95HV-1^06142016.0175601 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
518348083-17624-DETAIL-04_25_2024-GO95HV-1^06142016.0175602 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
518348083-17624-DETAIL-04_25_2024-GO95MLD-1^06142016.0175602 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
297777684-89684-DETAIL-04_25_2024-GO95HV-1^06142016.0175700 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
297777684-89684-DETAIL-04_25_2024-GO95MLD-1^06142016.0175700 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
562039784-63884-DETAIL-04_25_2024-GO95HV-1^06142016.0175800 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
955145984-17984-DETAIL-04_09_2019-SVCROAD-1^06142016.0175802 | OTHER | CA-NON-TIER | Distribution | 2019-04-09 | 2024-03-09 | 2
955145984-17984-DETAIL-04_25_2024-GO95MLD-1^06142016.0175802 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
955145984-17984-DETAIL-04_25_2024-XARMSPCR-1^06142016.0175802 | CROSSARM | CA-NON-TIER | Distribution | 2024-04-25 | 2027-04-25 | 2
775704691-50822-DETAIL-04_25_2024-GO95MLD-1^06142016.0175903 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
316473631-15119-ADMIN-07_27_2021-INSULDMG-1^668005/00 11/083 | INSULATOR AND BUSHING | CA-NON-TIER | Transmission | 2021-07-27 | 2024-07-27 | 2
22509001-47219-ADMIN-12_31_2018-POLEREPL-1^668005/00 11/086 | POLE | CA-NON-TIER | Transmission | 2018-12-31 | 2023-11-30 | 2
22509001-47219-DTLTRT-08_15_2022-POLETOP-1^668005/00 11/086 | POLE | CA-NON-TIER | Transmission | 2022-08-15 | 2025-08-15 | 2
960731252-80319-ADMIN-12_27_2018-POLEREPL-1^668005/00 11/087 | POLE | CA-NON-TIER | Transmission | 2018-12-27 | 2023-11-27 | 2
73253903-33519-ADMIN-06_15_2021-INSULDMG-1^668005/00 11/093 | INSULATOR AND BUSHING | FHCA | Transmission | 2021-06-15 | 2024-06-15 | 2
504487824-7519-ADMIN-11_18_2022-POLEDERP-1^668005/00 11/094 | POLE | FHCA | Transmission | 2022-11-18 | 2025-11-18 | 2
694839435-10919-DTLTRT-08_18_2022-GO95HV-1^668005/00 11/096 | OTHER | FHCA | Transmission | 2022-08-18 | 2027-08-18 | 3
744707784-7629-ADMIN-10_24_2022-ANCPUCO-1^06143012.0239000 | ANCHOR/GUY | FHCA | Distribution | 2022-10-24 | 2025-10-24 | 2
792910294-27629-DETAIL-04_26_2022-GO95MLD-1^06143012.0239001 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
792910294-27629-DETAIL-04_26_2022-GRDRODHI-1^06143012.0239001 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
1770654-26229-DETAIL-04_26_2022-GO95CL10-1^06143012.0239201 | OTHER | FHCA | Distribution | 2022-04-26 | 2027-04-26 | 3
1770654-26229-DETAIL-04_26_2022-GO95MLD-1^06143012.0239201 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
981364994-5229-DETAIL-04_26_2022-GO95HV-1^06143012.0239203 | OTHER | FHCA | Distribution | 2022-04-26 | 2027-04-26 | 3
981364994-5229-DETAIL-04_26_2022-GO95TCH-1^06143012.0239203 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
652454230-66629-DETAIL-04_26_2022-GO95HV-1^06143012.0240000 | OTHER | FHCA | Distribution | 2022-04-26 | 2027-04-26 | 3
466845800-16629-DETAIL-04_26_2022-GO95HV-1^06143012.0240100 | OTHER | FHCA | Distribution | 2022-04-26 | 2027-04-26 | 3
229137100-85629-DETAIL-04_26_2022-GO95MLD-1^06143012.0240101 | OTHER | FHCA | Distribution | 2022-04-26 | 2025-04-26 | 2
279215650-44629-DETAIL-04_26_2022-GO95MLD-1^06143012.0240301 | OTHER | FHCA | Distribution | 2022-04-26 | 2027-04-26 | 3
458522260-92229-DETAIL-04_27_2022-GO95MLD-1^06143012.0240701 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
926342090-18329-DETAIL-04_27_2022-CUTOUTAR-1^06143012.0240801 | LIGHTNING ARRESTER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
992882179-56819-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 12/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-03 | 2025-08-03 | 2
903423561-61119-DTLTRT-08_04_2022-GUYHINS-1^668005/00 12/082 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-04 | 2025-08-04 | 2
903423561-61119-DTLTRT-08_04_2022-GUYSLACK-1^668005/00 12/082 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-08-04 | 2025-08-04 | 2
164764341-45119-ADMIN-08_05_2020-POLEDERP-1^668005/00 12/083 | POLE | CA-NON-TIER | Transmission | 2020-08-05 | 2023-08-05 | 2
526912313-53519-DTLTRT-08_17_2022-POLETOP-1^668005/00 12/093 | POLE | FHCA | Transmission | 2022-08-17 | 2025-08-17 | 2
641058373-54419-ADMIN-11_07_2022-POLEDERP-1^668005/00 13/091 | POLE | FHCA | Transmission | 2022-11-07 | 2025-11-07 | 2
241092944-21619-DTLTRT-08_17_2022-GO95HV-1^668005/00 13/095 | OTHER | FHCA | Transmission | 2022-08-17 | 2027-08-17 | 3
1852273-79419-ENHANCED-07_21_2020-POLEDERP-1^668005/00 14/092 | POLE | FHCA | Transmission | 2020-07-21 | 2023-07-21 | 2
859720873-63392-DETAIL-04_14_2022-GO95HV-1^06142012.0136503 | OTHER | FHCA | Distribution | 2022-04-14 | 2027-04-14 | 3
80932313-99610-DETAIL-04_14_2022-GUYLOINS-1^06142012.0137400 | ANCHOR/GUY | FHCA | Distribution | 2022-04-14 | 2025-04-14 | 2
86918111-68111-DETAIL-04_21_2022-GO95HV-1^06142012.0139200 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
194947643-88929-DETAIL-04_21_2022-CLMBHAZ-1^06142012.0139300 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
194947643-88929-DETAIL-04_21_2022-GO95MLD-1^06142012.0139300 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
194947643-88929-DETAIL-04_21_2022-GUYHINS-1^06142012.0139300 | ANCHOR/GUY | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
143229269-21369-DETAIL-04_21_2022-GO95HV-1^06142012.0139302 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
599221873-33511-DETAIL-04_21_2022-GO95HV-1^06142012.0139402 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
888393003-10282-DETAIL-04_21_2022-GO95MLD-1^06142012.0139404 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
169987091-18729-DETAIL-04_27_2022-GO95MLD-1^06143012.0244005 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
112307191-20829-DETAIL-05_02_2022-GO95MLD-1^06143012.0244100 | OTHER | FHCA | Distribution | 2022-05-02 | 2025-05-02 | 2
137137698-66529-DETAIL-04_27_2022-GO95MLD-1^06143012.0244101 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
137137698-66529-DETAIL-04_27_2022-SVCNEUT-1^06143012.0244101 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
762398708-81629-DETAIL-05_02_2022-GO95MLD-1^06143012.0244202 | OTHER | FHCA | Distribution | 2022-05-02 | 2025-05-02 | 2
977081728-32629-DETAIL-04_27_2022-GO95MLD-1^06143012.0244300 | OTHER | FHCA | Distribution | 2022-04-27 | 2027-04-27 | 3
879480958-88229-DETAIL-05_02_2022-GO95MLD-1^06143012.0244302 | OTHER | FHCA | Distribution | 2022-05-02 | 2025-05-02 | 2
664227948-97229-DETAIL-03_28_2016-SVCWIND-1^06142012.0148601 | OTHER | FHCA | Distribution | 2016-03-28 | 2021-02-28 | 2
648400743-57829-DETAIL-03_28_2016-SVCWIND-1^06142012.0148701 | OTHER | FHCA | Distribution | 2016-03-28 | 2021-02-28 | 2
648400743-57829-DETAIL-11_10_2021-SVCROAD-1^06142012.0148701 | OTHER | FHCA | Distribution | 2021-11-10 | 2024-11-10 | 2
228706349-47660-DETAIL-03_14_2016-SVCWIND-1^06142012.0148908 | OTHER | FHCA | Distribution | 2016-03-14 | 2021-02-14 | 2
296060523-16129-DETAIL-03_21_2016-SVCWIND-1^06142012.0149700 | OTHER | FHCA | Distribution | 2016-03-21 | 2021-02-21 | 2
798544348-92629-DETAIL-04_27_2022-POLETOP-1^06143012.0244303 | POLE | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
902996338-62629-DETAIL-04_27_2022-GO95MLD-1^06143012.0244304 | OTHER | FHCA | Distribution | 2022-04-27 | 2027-04-27 | 3
690681250-46129-DETAIL-05_02_2022-GO95MLD-1^06143012.0244801 | OTHER | FHCA | Distribution | 2022-05-02 | 2025-05-02 | 2
952283568-72129-DETAIL-04_28_2022-GO95HV-1^06143012.0245300 | OTHER | FHCA | Distribution | 2022-04-28 | 2027-04-28 | 3
952283568-72129-DETAIL-04_28_2022-GO95MLD-1^06143012.0245300 | OTHER | FHCA | Distribution | 2022-04-28 | 2025-04-28 | 2
613707878-99429-DETAIL-04_28_2022-GO95MLD-1^06143012.0245301 | OTHER | FHCA | Distribution | 2022-04-28 | 2025-04-28 | 2
296060523-16129-DETAIL-11_08_2021-GO95CLSV-1^06142012.0149700 | OTHER | FHCA | Distribution | 2021-11-08 | 2024-11-08 | 2
290665533-50029-DETAIL-04_21_2022-GO95HV-1^06142012.0247300 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
541536333-65829-DETAIL-04_21_2022-GO95HV-1^06142012.0247301 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
541536333-65829-DETAIL-04_21_2022-GO95MLD-1^06142012.0247301 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
339653914-67129-DETAIL-11_15_2021-UNIGRDSG-1^06142013.0062201 | OTHER | FHCA | Distribution | 2021-11-15 | 2024-11-15 | 2
609441028-41721-DETAIL-11_11_2021-GO95MLD-1^06142013.0174601 | OTHER | FHCA | Distribution | 2021-11-11 | 2024-11-11 | 2
716148626-69961-DETAIL-11_15_2021-UNIGRDSG-1^06142013.0180402 | OTHER | FHCA | Distribution | 2021-11-15 | 2024-11-15 | 2
621930580-32580-DETAIL-04_30_2024-GO95HV-1^06142015.0021900 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
701915580-17580-DETAIL-04_30_2024-GO95HV-1^06142015.0022900 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
412221780-72780-DETAIL-04_30_2024-GO95HV-1^06142015.0024900 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
317449141-11241-ADMIN-01_06_2022-POLEDERP-1^06142015.0034902 | POLE | CA-TIER-2 | Distribution | 2022-01-06 | 2023-01-06 | 2
279128771-10871-ADMIN-04_19_2022-POLEDERP-1^06142015.0036902 | POLE | CA-TIER-2 | Distribution | 2022-04-19 | 2023-04-19 | 2
934862871-64871-DETAIL-04_30_2024-GO95HV-1^06142015.0037900 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
835682199-57504-DETAIL-05_01_2024-GO95HV-1^06142015.0048901 | OTHER | CA-TIER-2 | Distribution | 2024-05-01 | 2029-05-01 | 3
577534531-6531-DETAIL-04_25_2024-GO95HV-1^06142016.0040000 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
453798531-81631-DETAIL-04_25_2024-GO95HV-1^06142016.0040001 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
507892731-17731-DETAIL-04_25_2024-GO95HV-1^06142016.0041001 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
742520831-2831-DETAIL-04_25_2024-GO95MLD-1^06142016.0041002 | OTHER | CA-NON-TIER | Distribution | 2024-04-25 | 2029-04-25 | 3
858455931-76931-DETAIL-03_23_2023-GO95MLD-1^06142016.0050002 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
522967961-64364-DETAIL-03_23_2023-GO95MLD-1^06142016.0050006 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
627732161-33204-DETAIL-03_23_2023-GO95MLD-1^06142016.0050101 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
426999161-76284-DETAIL-03_27_2023-GO95BLTC-1^06142016.0050201 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
426999161-76284-DETAIL-03_27_2023-GO95MLD-1^06142016.0050201 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
372744261-16261-DETAIL-03_27_2023-ABNDEQPM-1^06142016.0050600 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
554934461-36461-DETAIL-03_23_2023-GO95MLD-1^06142016.0051001 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
712238591-42691-DETAIL-03_23_2023-GO95MLD-1^06142016.0051002 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
562003791-76791-DETAIL-03_23_2023-GO95MLD-1^06142016.0051004 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
245861860-68514-ADMIN-02_06_2018-COPLLEAN-1^06142016.0051005 | POLE | CA-NON-TIER | Distribution | 2018-02-06 | 2023-01-06 | 2
355959091-22191-DETAIL-03_23_2023-SVCROAD-1^06142016.0051100 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
476020291-16014-DETAIL-03_23_2023-GO95MLD-1^06142016.0051103 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
325351211-92211-DETAIL-03_23_2023-GO95HV-1^06142016.0051105 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2028-03-23 | 3
140309459-86769-DTLTRT-10_10_2022-POLEDERP-1^668005/03 12/004 | POLE | CA-NON-TIER | Transmission | 2022-10-10 | 2025-10-10 | 2
550968603-53903-DETAIL-10_12_2022-GO95HV-1^668005/08 8X1/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
552138813-10323-DETAIL-10_12_2022-GO95HV-1^668005/08 8X2/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
285658633-67833-DETAIL-10_12_2022-GO95HV-1^668005/08 8X3/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
24604433-49633-DETAIL-10_12_2022-GO95HV-1^668005/08 8X4/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
730281043-3243-DETAIL-10_12_2022-GO95HV-1^668005/08 8X5/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
771378443-743-DETAIL-10_12_2022-GO95HV-1^668005/08 8X6/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
159437443-25643-DETAIL-10_12_2022-GO95HV-1^668005/08 8X7/077 | OTHER | CA-NON-TIER | Transmission | 2022-10-12 | 2027-10-12 | 3
159437443-25643-DETAIL-10_12_2022-GUYHINS-1^668005/08 8X7/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
159437443-25643-DETAIL-10_12_2022-GUYHINS-2^668005/08 8X7/077 | ANCHOR/GUY | CA-NON-TIER | Transmission | 2022-10-12 | 2025-10-12 | 2
69308381-99381-DETAIL-03_27_2023-SVCENTCO-1^06142016.0052502 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
408979001-71101-DETAIL-03_27_2023-GO95HV-1^06142016.0052700 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
857782501-26501-DETAIL-03_28_2023-ABNDEQPM-1^06142016.0052901 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
857782501-26501-DETAIL-03_28_2023-GO95BLTC-1^06142016.0052901 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
857782501-26501-DETAIL-03_28_2023-GO95MLD-1^06142016.0052901 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
318334701-85801-DETAIL-03_29_2023-GO95MLD-1^06142016.0053000 | OTHER | CA-NON-TIER | Distribution | 2023-03-29 | 2026-03-29 | 2
382641121-75121-DETAIL-03_28_2023-GO95MLD-1^06142016.0053007 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
798595741-46514-DETAIL-03_28_2023-GO95MLD-1^06142016.0053300 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
798595741-46514-DETAIL-03_28_2023-GRDRODHI-1^06142016.0053300 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
708984164-86164-DETAIL-03_28_2023-GO95MLD-1^06142016.0053301 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
432779741-22841-DETAIL-03_28_2023-GO95MLD-1^06142016.0053500 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2026-03-28 | 2
25844841-66841-DETAIL-03_27_2023-GO95HV-1^06142016.0053501 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2028-03-27 | 3
306789841-51941-DETAIL-03_27_2023-GO95MLD-1^06142016.0053700 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
148588861-86094-ADMIN-04_21_2023-GO95TCH-1^06142016.0054004 | OTHER | CA-NON-TIER | Distribution | 2023-04-21 | 2026-04-21 | 2
48849061-13161-DETAIL-03_30_2023-GO95MLD-1^06142016.0054008 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
48849061-13161-DETAIL-03_30_2023-SVCENTCO-1^06142016.0054008 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
616768261-2361-DETAIL-03_30_2023-GO95TCH-1^06142016.0054010 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
393002381-29914-DETAIL-02_05_2018-SVCWIND-1^06142016.0054104 | OTHER | CA-NON-TIER | Distribution | 2018-02-05 | 2023-01-05 | 2
595017381-70684-DETAIL-03_28_2023-GO95HV-1^06142016.0054200 | OTHER | CA-NON-TIER | Distribution | 2023-03-28 | 2028-03-28 | 3
810965519-98519-DETAIL-03_30_2023-GO95MLD-1^06142016.0054300 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
810965519-98519-DETAIL-03_30_2023-GO95TCH-1^06142016.0054300 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
962168828-59828-DETAIL-03_30_2023-GO95BLTC-1^06142016.0055001 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2028-03-30 | 3
962168828-59828-DETAIL-03_30_2023-GO95MLD-1^06142016.0055001 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
787605301-47401-DETAIL-03_30_2023-GO95MLD-1^06142016.0055002 | OTHER | CA-NON-TIER | Distribution | 2023-03-30 | 2026-03-30 | 2
551393512-38241-DETAIL-05_14_2024-GO95HV-1^06142012.0124409 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
322316995-99070-DETAIL-05_15_2024-GUYHINS-1^06142012.0124500 | ANCHOR/GUY | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
83354885-30420-DETAIL-05_15_2024-GO95MLD-1^06142012.0124502 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
609732603-56921-DETAIL-05_15_2024-GO95MLD-1^06142012.0124600 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
793796405-26472-DETAIL-05_15_2024-GUYHINS-1^06142012.0124601 | ANCHOR/GUY | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
252760935-75390-DETAIL-05_15_2024-GO95BLTC-1^06142012.0124700 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
252760935-75390-DETAIL-05_15_2024-GO95HV-1^06142012.0124700 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
252760935-75390-DETAIL-05_15_2024-GO95MLD-1^06142012.0124700 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
10463013-91069-DETAIL-05_15_2024-GO95HV-1^06142012.0124701 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
375794123-79420-DETAIL-05_15_2024-GO95HV-1^06142012.0124703 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
375794123-79420-DETAIL-05_15_2024-GO95MLD-1^06142012.0124703 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
375794123-79420-DETAIL-05_15_2024-GRDRODHI-1^06142012.0124703 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
287305174-48529-DETAIL-04_25_2022-GO95MLD-1^06143012.0253201 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
142211583-88729-DETAIL-04_25_2022-GO95MLD-1^06143012.0253502 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
142211583-88729-DETAIL-04_25_2022-GO95TCH-1^06143012.0253502 | OTHER | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
257274773-3329-DETAIL-04_25_2022-POLETOP-1^06143012.0253600 | POLE | FHCA | Distribution | 2022-04-25 | 2025-04-25 | 2
683362424-16429-DETAIL-04_27_2022-GO95MLD-1^06143012.0253900 | OTHER | FHCA | Distribution | 2022-04-27 | 2027-04-27 | 3
973772673-95529-DETAIL-04_25_2022-GO95MLD-1^06143012.0254400 | OTHER | FHCA | Distribution | 2022-04-25 | 2027-04-25 | 3
175917923-7329-DETAIL-04_27_2022-GO95MLD-1^06143012.0254702 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
520468319-61701-DETAIL-05_02_2024-GO95MLD-1^06142012.0126001 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
90923898-91529-DETAIL-05_02_2024-GO95MLD-1^06142012.0126101 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
90923898-91529-DETAIL-05_02_2024-SVCENTCO-1^06142012.0126101 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
994604198-60143-DETAIL-05_02_2024-SVCDEFLC-1^06142012.0126102 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
386086229-45430-DETAIL-05_02_2024-GO95HV-1^06142012.0126104 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
341576079-31180-DETAIL-04_22_2019-SVCROAD-1^06142012.0126105 | OTHER | FHCA | Distribution | 2019-04-22 | 2024-03-22 | 2
341576079-31180-DETAIL-05_02_2024-GO95MLD-1^06142012.0126105 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
341576079-31180-DETAIL-05_02_2024-GRDRODHI-1^06142012.0126105 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
446973929-17229-DETAIL-05_02_2024-GRDRODHI-1^06142012.0126200 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
446973929-17229-DETAIL-05_02_2024-GRDRODHI-2^06142012.0126200 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
675486799-2351-DETAIL-05_02_2024-SVCDEFLC-1^06142012.0126202 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
622291423-55423-DETAIL-04_30_2024-GO95HV-1^06142016.0061100 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
285750523-5523-DETAIL-04_30_2024-GUYLOINS-1^06142016.0062000 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
499455563-69563-DETAIL-04_30_2024-GO95HV-1^06142016.0066000 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
499455563-69563-DETAIL-04_30_2024-GO95MLD-1^06142016.0066000 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2029-04-30 | 3
499455563-69563-DETAIL-04_30_2024-SVCDEFLC-1^06142016.0066000 | OTHER | CA-TIER-2 | Distribution | 2024-04-30 | 2027-04-30 | 2
747921863-92863-DETAIL-04_29_2024-GO95HV-1^06142016.0066800 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
747921863-92863-DETAIL-04_29_2024-SVCDEFLC-1^06142016.0066800 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
17992963-44405-DETAIL-04_29_2024-GO95MLD-1^06142016.0067001 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
17992963-44405-DETAIL-04_29_2024-SVCROAD-1^06142016.0067001 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
445947593-71693-DETAIL-04_29_2024-GO95MLD-1^06142016.0067902 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
445947593-71693-DETAIL-04_29_2024-GRDRODHI-1^06142016.0067902 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
682346693-49693-DETAIL-04_29_2024-GO95HV-1^06142016.0067903 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
132922781-24429-DETAIL-04_11_2022-POLETOP-1^06142012.0130800 | POLE | FHCA | Distribution | 2022-04-11 | 2025-04-11 | 2
132922781-24429-DETAIL-04_11_2022-XARMSPCR-1^06142012.0130800 | CROSSARM | FHCA | Distribution | 2022-04-11 | 2025-04-11 | 2
132922781-24429-ADMIN-10_03_2022-POLEDERP-1^06142012.0130800 | POLE | FHCA | Distribution | 2022-10-03 | 2025-10-03 | 2
221202220-52929-DETAIL-04_11_2022-GO95CL10-1^06142012.0130801 | OTHER | FHCA | Distribution | 2022-04-11 | 2025-04-11 | 2
822261591-66929-DETAIL-04_11_2022-GO95MLD-1^06142012.0130812 | OTHER | FHCA | Distribution | 2022-04-11 | 2025-04-11 | 2
822261591-66929-DETAIL-04_11_2022-GUYSLACK-1^06142012.0130812 | ANCHOR/GUY | FHCA | Distribution | 2022-04-11 | 2025-04-11 | 2
788951793-3793-DETAIL-04_29_2024-SVCROAD-1^06142016.0068000 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
130400893-51893-DETAIL-04_29_2024-GO95MLD-1^06142016.0068100 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
52980299-79129-DETAIL-04_29_2024-GO95MLD-1^06142016.0069005 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2029-04-29 | 3
52980299-79129-DETAIL-04_29_2024-GRDRODHI-1^06142016.0069005 | OTHER | CA-NON-TIER | Distribution | 2024-04-29 | 2027-04-29 | 2
276535323-27323-DETAIL-04_29_2024-ABNDEQPM-1^06142016.0069103 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
276535323-27323-DETAIL-04_29_2024-GO95MLD-1^06142016.0069103 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
276535323-27323-DETAIL-04_29_2024-GRDRODHI-1^06142016.0069103 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
171288613-72713-DETAIL-04_29_2024-SVCDEFLC-1^06142016.0078701 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
192154843-61943-DETAIL-04_29_2024-GO95MLD-1^06142016.0078800 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
974927043-30143-DETAIL-04_29_2024-GO95MLD-1^06142016.0078900 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
637093143-66143-DETAIL-04_29_2024-GO95HV-1^06142016.0078902 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
268617713-80813-DETAIL-04_29_2024-GO95MLD-1^06142016.0079700 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
392787165-73329-DETAIL-04_13_2022-ABNDEQPM-1^06142012.0131608 | OTHER | FHCA | Distribution | 2022-04-13 | 2027-04-13 | 3
682997657-13229-DETAIL-04_13_2022-GO95SVC-1^06142012.0131609 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
954575690-54829-DETAIL-04_13_2022-GO95HV-1^06142012.0131610 | OTHER | FHCA | Distribution | 2022-04-13 | 2027-04-13 | 3
954575690-54829-DETAIL-04_13_2022-GO95MLD-1^06142012.0131610 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
682291674-74229-DETAIL-04_13_2022-GO95MLD-1^06142012.0131617 | OTHER | FHCA | Distribution | 2022-04-13 | 2027-04-13 | 3
427573083-40529-DETAIL-04_13_2022-GO95MLD-1^06142012.0131619 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
123012774-5129-DETAIL-04_19_2022-GO95MLD-1^06142012.0131706 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
593948164-64129-DETAIL-04_19_2022-GUYHINS-1^06142012.0131707 | ANCHOR/GUY | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
593948164-64129-DETAIL-04_19_2022-SVCENTCO-1^06142012.0131707 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
283640303-59529-DETAIL-04_13_2022-GO95MLD-1^06142012.0131708 | OTHER | FHCA | Distribution | 2022-04-13 | 2027-04-13 | 3
517711934-74229-DETAIL-04_27_2022-GO95MLD-1^06143012.0254704 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
17814825-86329-DETAIL-04_27_2022-GO95TCH-1^06143012.0254705 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
410983203-36529-DETAIL-04_27_2022-GO95MLD-1^06143012.0254803 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
410983203-36529-DETAIL-04_27_2022-GO95MLD-2^06143012.0254803 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
77129703-96529-DETAIL-04_27_2022-GO95MLD-1^06143012.0254804 | OTHER | FHCA | Distribution | 2022-04-27 | 2025-04-27 | 2
290933274-59529-DETAIL-04_28_2022-GO95HV-1^06143012.0254900 | OTHER | FHCA | Distribution | 2022-04-28 | 2027-04-28 | 3
222667223-10629-DETAIL-04_27_2022-GO95HV-1^06143012.0254901 | OTHER | FHCA | Distribution | 2022-04-27 | 2027-04-27 | 3
883669438-95529-DETAIL-04_19_2022-GO95MLD-1^06142012.0131900 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
916097805-95129-DETAIL-04_19_2022-GO95MLD-1^06142012.0131901 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
21564734-14450-DETAIL-04_13_2022-GO95MLD-1^06142012.0132400 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
967489504-98673-DETAIL-04_13_2022-SVCROAD-1^06142012.0132401 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
165030444-29-DETAIL-04_13_2022-SVCROAD-1^06142012.0132404 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
407217334-86029-DETAIL-04_13_2022-GO95MLD-1^06142012.0132405 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
972064662-48583-DETAIL-04_13_2022-GO95MLD-1^06142012.0132601 | OTHER | FHCA | Distribution | 2022-04-13 | 2027-04-13 | 3
98134960-96630-DETAIL-03_20_2017-SVCENTCO-1^06142012.0132610 | OTHER | FHCA | Distribution | 2017-03-20 | 2022-02-20 | 2
150952841-49729-DETAIL-04_18_2022-GO95MLD-1^06142012.0132700 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
426869895-29329-DETAIL-04_13_2022-GO95MLD-1^06142012.0132711 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
332668840-58729-DETAIL-04_18_2022-SVCWIND-1^06142012.0132801 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
637152423-86051-DETAIL-04_18_2022-SVCROOF-1^06142012.0132804 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
116330241-58129-DETAIL-04_18_2022-GO95HV-1^06142012.0132808 | OTHER | FHCA | Distribution | 2022-04-18 | 2027-04-18 | 3
116330241-58129-DETAIL-04_18_2022-GO95MLD-1^06142012.0132808 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
248879780-87129-DETAIL-04_19_2022-GO95MLD-1^06142012.0132809 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
248879780-87129-DETAIL-04_19_2022-GO95TCH-1^06142012.0132809 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
688248653-78481-DETAIL-04_19_2022-GO95MLD-1^06142012.0132810 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
688248653-78481-DETAIL-04_19_2022-GUYNOINS-1^06142012.0132810 | ANCHOR/GUY | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
515003451-24329-DETAIL-04_18_2022-GO95MLD-1^06142012.0132813 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
523279913-5029-DETAIL-05_08_2024-SVCROAD-1^06142012.0120041 | OTHER | FHCA | Distribution | 2024-05-08 | 2027-05-08 | 2
728116179-60201-DETAIL-05_08_2024-GO95MLD-1^06142012.0120102 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
963166151-80853-DETAIL-05_08_2024-GO95MLD-1^06142012.0120104 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
894104475-56402-DETAIL-05_08_2024-GO95HV-1^06142012.0120105 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
167203475-30410-DETAIL-05_08_2024-GO95MLD-1^06142012.0120201 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
619895141-93029-DETAIL-05_08_2024-GO95MLD-1^06142012.0120206 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
23614859-38929-DETAIL-05_08_2024-SVCDEFLC-1^06142012.0120301 | OTHER | FHCA | Distribution | 2024-05-08 | 2027-05-08 | 2
558478671-73229-DETAIL-05_08_2024-GO95HV-1^06142012.0120302 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
558478671-73229-DETAIL-05_08_2024-GO95MLD-1^06142012.0120302 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
592190519-53229-DETAIL-05_08_2024-GO95HV-1^06142012.0120303 | OTHER | FHCA | Distribution | 2024-05-08 | 2029-05-08 | 3
352827637-99329-DETAIL-05_09_2024-SVCENTCO-1^06142012.0120310 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
736974548-6548-DETAIL-05_08_2024-GO95MLD-1^06142012.0120402 | OTHER | FHCA | Distribution | 2024-05-08 | 2027-05-08 | 2
499876263-19263-DETAIL-04_29_2024-SVCDEFLC-1^06142016.0079902 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2027-04-29 | 2
600291021-32021-DETAIL-04_29_2024-GO95MLD-1^06142016.0079904 | OTHER | CA-TIER-2 | Distribution | 2024-04-29 | 2029-04-29 | 3
600291021-32021-AUDIT-05_30_2024-GUYHINS-1^06142016.0079904 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-05-30 | 2027-05-30 | 2
67408203-6303-DETAIL-03_23_2023-GO95MLD-1^06142016.0080707 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
298439623-12723-DETAIL-03_23_2023-GO95MLD-1^06142016.0081700 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
298439623-12723-DETAIL-03_23_2023-GRDRODHI-1^06142016.0081700 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
76390823-72823-DETAIL-03_23_2023-GO95MLD-1^06142016.0081703 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
437353-70453-DETAIL-03_23_2023-GO95MLD-1^06142016.0081800 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
614493828-5828-DETAIL-03_23_2023-GO95HV-1^06142016.0081802 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2028-03-23 | 3
819388553-15443-DETAIL-03_23_2023-GO95MLD-1^06142016.0081803 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
383394753-20774-DETAIL-03_27_2023-GO95MLD-1^06142016.0081806 | OTHER | CA-NON-TIER | Distribution | 2023-03-27 | 2026-03-27 | 2
795795953-27953-DETAIL-03_23_2023-GO95MLD-1^06142016.0081901 | OTHER | CA-NON-TIER | Distribution | 2023-03-23 | 2026-03-23 | 2
981548325-71703-DETAIL-05_16_2024-SVCENTCO-1^06142012.0120701 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
904218243-89842-DETAIL-05_16_2024-GO95MLD-1^06142012.0120702 | OTHER | FHCA | Distribution | 2024-05-16 | 2029-05-16 | 3
345993955-57129-DETAIL-05_16_2024-GO95MLD-1^06142012.0120705 | OTHER | FHCA | Distribution | 2024-05-16 | 2029-05-16 | 3
276044274-57510-DETAIL-05_16_2024-SVCDEFLC-1^06142012.0120900 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
356060972-64029-DETAIL-05_08_2024-GO95MLD-1^06142012.0121005 | OTHER | FHCA | Distribution | 2024-05-08 | 2027-05-08 | 2
356060972-64029-DETAIL-05_08_2024-GO95TCH-1^06142012.0121005 | OTHER | FHCA | Distribution | 2024-05-08 | 2027-05-08 | 2
112112223-73223-DETAIL-05_08_2024-GO95MLD-1^06142012.0121007 | OTHER | FHCA | Distribution | 2024-05-08 | 2027-05-08 | 2
876900562-75752-DETAIL-05_07_2024-GO95MLD-1^06142012.0121101 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
830046259-96929-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0121102 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
830046259-96929-DETAIL-05_07_2024-SVCENTCO-1^06142012.0121102 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
953438461-51433-DETAIL-05_07_2024-GO95MLD-1^06142012.0121104 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
273650441-37210-DETAIL-05_07_2024-GO95HV-1^06142012.0121211 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
25270683-52429-DETAIL-04_19_2022-SVCWIND-1^06142012.0132907 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
539703304-57129-DETAIL-04_19_2022-GO95MLD-1^06142012.0132908 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
968764124-23473-DETAIL-04_13_2022-GO95MLD-1^06142012.0133400 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
505113600-11029-DETAIL-03_20_2017-SVCWIND-1^06142012.0133501 | OTHER | FHCA | Distribution | 2017-03-20 | 2022-02-20 | 2
624933954-24741-DETAIL-04_13_2022-ANCHIDLE-1^06142012.0133609 | ANCHOR/GUY | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
624933954-24741-DETAIL-04_13_2022-SVCROOF-1^06142012.0133609 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
486135210-70451-DETAIL-04_18_2022-GO95CLSV-1^06142012.0133700 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
486135210-70451-DETAIL-04_18_2022-SVCWIND-1^06142012.0133700 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
110515654-69150-DETAIL-04_18_2022-GO95TCH-1^06142012.0133704 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
541116418-77418-DETAIL-04_17_2019-SVCWIND-1^06142012.0122002 | OTHER | FHCA | Distribution | 2019-04-17 | 2024-03-17 | 2
574208941-82829-DETAIL-05_07_2024-GO95BLTC-1^06142012.0122003 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
574208941-82829-DETAIL-05_07_2024-GO95MLD-1^06142012.0122003 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
821580561-38129-DETAIL-05_07_2024-GO95MLD-1^06142012.0122005 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
821580561-38129-DETAIL-05_07_2024-SVCNEUT-1^06142012.0122005 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
334186101-40829-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0122100 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
943334001-34829-DETAIL-05_06_2024-GO95HV-1^06142012.0122103 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
943334001-34829-DETAIL-05_06_2024-GO95MLD-1^06142012.0122103 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
275998976-97829-DETAIL-05_07_2024-GO95MLD-1^06142012.0122104 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
117432100-10529-DETAIL-05_07_2024-GO95MLD-1^06142012.0122105 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
135267901-1829-DETAIL-05_07_2024-GO95HV-1^06142012.0122107 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
135267901-1829-DETAIL-05_07_2024-SVCENTCO-1^06142012.0122107 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
297440894-6740-DETAIL-04_18_2022-SVCWIND-1^06142012.0133705 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
660209151-41129-DETAIL-04_18_2022-GO95HV-1^06142012.0133902 | OTHER | FHCA | Distribution | 2022-04-18 | 2027-04-18 | 3
660209151-41129-DETAIL-04_18_2022-GO95MLD-1^06142012.0133902 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
302363693-37440-DETAIL-04_21_2022-GO95HV-1^06142012.0134000 | OTHER | FHCA | Distribution | 2022-04-21 | 2027-04-21 | 3
553413424-93329-DETAIL-04_21_2022-GO95MLD-1^06142012.0134002 | OTHER | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
553413424-93329-DETAIL-04_21_2022-GUYHINS-1^06142012.0134002 | ANCHOR/GUY | FHCA | Distribution | 2022-04-21 | 2025-04-21 | 2
350940014-6290-DETAIL-04_14_2022-GO95MLD-1^06142012.0134502 | OTHER | FHCA | Distribution | 2022-04-14 | 2025-04-14 | 2
524374881-10611-DETAIL-04_19_2022-GO95MLD-1^06142012.0134901 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
24039591-80870-DETAIL-04_19_2022-GO95MLD-1^06142012.0134903 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
879458664-13952-ADMIN-05_14_2024-GO95TCH-1^06142012.0122606 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
879458664-13952-DETAIL-05_14_2024-SVCDEFLC-1^06142012.0122606 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
791364045-36762-DETAIL-05_15_2024-GO95MLD-1^06142012.0122700 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
947255263-1129-DETAIL-05_14_2024-GO95HV-1^06142012.0122703 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
947255263-1129-DETAIL-05_14_2024-GO95MLD-2^06142012.0122703 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
947255263-1129-DETAIL-05_14_2024-GRDRODHI-1^06142012.0122703 | OTHER | FHCA | Distribution | 2024-05-14 | 2027-05-14 | 2
855492993-52729-DETAIL-05_14_2024-GO95MLD-1^06142012.0122704 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
89085383-44029-DETAIL-05_16_2024-GO95MLD-1^06142012.0122706 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
632823783-39629-DETAIL-05_14_2024-GO95MLD-1^06142012.0122707 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
588451453-47629-DETAIL-05_14_2024-GO95MLD-1^06142012.0122710 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
610488493-32129-DETAIL-05_14_2024-GO95HV-1^06142012.0122805 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
610488493-32129-DETAIL-05_14_2024-GO95MLD-1^06142012.0122805 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
934724932-34139-DETAIL-05_15_2024-RISEBKSP-1^06142012.0126801 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
278521662-85139-ADMIN-05_15_2024-ENCHRW-1^06142012.0126802 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
278521662-85139-DETAIL-05_15_2024-ENCHRW-1^06142012.0126802 | OTHER | FHCA | Distribution | 2024-05-15 | 2027-05-15 | 2
422423342-97929-DETAIL-05_15_2024-GO95HV-1^06142012.0126840 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
422423342-97929-DETAIL-05_15_2024-GO95MLD-1^06142012.0126840 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
547181519-85241-DETAIL-05_02_2024-GO95HV-1^06142012.0127102 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
521528359-71401-DETAIL-05_02_2024-GO95MLD-1^06142012.0127200 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
217264259-17750-DETAIL-05_02_2024-GO95HV-1^06142012.0127202 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
217264259-17750-DETAIL-05_02_2024-GO95MLD-1^06142012.0127202 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
836799029-16912-DETAIL-05_02_2024-GO95MLD-1^06142012.0128100 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
549448374-36341-DETAIL-04_12_2022-SVCROAD-1^06142012.0130400 | OTHER | FHCA | Distribution | 2022-04-12 | 2025-04-12 | 2
192391561-35829-DETAIL-05_07_2024-GO95MLD-1^06142012.0123202 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
790196506-89029-DETAIL-05_07_2024-GO95MLD-1^06142012.0123204 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
244656121-50529-DETAIL-05_07_2024-GO95HV-1^06142012.0123207 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
244656121-50529-DETAIL-05_07_2024-GO95MLD-1^06142012.0123207 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
244656121-50529-DETAIL-05_07_2024-GRDRODHI-1^06142012.0123207 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
244656121-50529-AUDIT-05_29_2024-GUYHINS-1^06142012.0123207 | ANCHOR/GUY | FHCA | Distribution | 2024-05-29 | 2027-05-29 | 2
974920931-38029-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0123208 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
575085966-83829-DETAIL-05_13_2024-GO95MLD-1^06142012.0123300 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
544420149-13829-DETAIL-05_13_2024-GO95HV-1^06142012.0123304 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
793903359-19129-DETAIL-05_13_2024-GO95MLD-1^06142012.0123305 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
793903359-19129-DETAIL-05_13_2024-SVCDEFLC-1^06142012.0123305 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
748468641-18129-DETAIL-05_13_2024-GO95HV-1^06142012.0123307 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
283640303-59529-DETAIL-04_13_2022-SVCWIND-1^06142012.0131708 | OTHER | FHCA | Distribution | 2022-04-13 | 2025-04-13 | 2
859890784-16529-DETAIL-04_14_2022-SVCWIND-1^06142012.0131709 | OTHER | FHCA | Distribution | 2022-04-14 | 2025-04-14 | 2
859890784-16529-DETAIL-04_14_2022-SVCWIND-2^06142012.0131709 | OTHER | FHCA | Distribution | 2022-04-14 | 2025-04-14 | 2
202591533-2829-DETAIL-04_19_2022-GUYHINS-1^06142012.0131712 | ANCHOR/GUY | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
202591533-2829-DETAIL-04_19_2022-GUYNOINS-1^06142012.0131712 | ANCHOR/GUY | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
240849953-92829-DETAIL-04_18_2022-GO95MLD-1^06142012.0131713 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
240849953-92829-DETAIL-04_18_2022-GRDRODHI-1^06142012.0131713 | OTHER | FHCA | Distribution | 2022-04-18 | 2025-04-18 | 2
363579850-73950-DETAIL-04_19_2022-GUYNOINS-1^06142012.0131742 | ANCHOR/GUY | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
917130613-31129-DETAIL-04_19_2022-GO95MLD-1^06142012.0131803 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
716115674-56829-DETAIL-04_19_2022-GO95MLD-1^06142012.0131804 | OTHER | FHCA | Distribution | 2022-04-19 | 2025-04-19 | 2
623279820-45631-DETAIL-05_06_2024-GO95HV-1^06142012.0124004 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
623279820-45631-DETAIL-05_06_2024-GO95MLD-1^06142012.0124004 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
263036430-65400-DETAIL-05_06_2024-SVCENTCO-1^06142012.0124005 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
233436849-2370-DETAIL-05_06_2024-GUYNOINS-1^06142012.0124006 | ANCHOR/GUY | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
699381239-44111-DETAIL-05_06_2024-SVCENTCO-1^06142012.0124007 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
298136609-79840-DETAIL-05_06_2024-GO95HV-1^06142012.0124008 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
298136609-79840-DETAIL-05_06_2024-GO95MLD-1^06142012.0124008 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
298136609-79840-DETAIL-05_06_2024-GO95STUB-1^06142012.0124008 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
180275380-97820-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0124009 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
164153420-90529-DETAIL-05_06_2024-GO95MLD-1^06142012.0124100 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
164153420-90529-DETAIL-05_06_2024-RISECLMB-1^06142012.0124100 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
256181879-76029-DETAIL-05_06_2024-GO95MLD-1^06142012.0124102 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
155870422-13370-DETAIL-01_23_2023-RISECLMB-1^06240004.0087000 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
170640212-28370-DETAIL-01_23_2023-GO95MLD-1^06240004.0087002 | OTHER | CA-TIER-2 | Distribution | 2023-01-23 | 2026-01-23 | 2
860375798-83730-DETAIL-01_12_2023-GO95TCH-1^06240004.0089501 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
609766018-16730-DETAIL-01_16_2023-SVCROAD-1^06240004.0089503 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
569392921-34921-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0089507 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
536130238-88730-DETAIL-01_12_2023-SVCROOF-1^06240004.0089600 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
250810149-33683-DETAIL-01_12_2023-GO95MLD-1^06240004.0090100 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
192243540-29783-DETAIL-01_12_2023-GO95MLD-1^06240004.0090101 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
931440929-97583-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0090102 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
931440929-97583-DETAIL-01_12_2023-SVCDEFLC-2^06240004.0090102 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
238392341-89130-DETAIL-01_12_2023-GO95MLD-1^06240004.0090501 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2028-01-12 | 3
266488948-79163-DETAIL-01_16_2023-SVCWIND-1^06240004.0090504 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
403930650-32583-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0090540 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
104865740-48483-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0090541 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
574127149-25173-DETAIL-01_12_2023-GO95MLD-1^06240004.0091000 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
574127149-25173-DETAIL-01_12_2023-RISEBKSP-1^06240004.0091000 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
232323349-23173-DETAIL-01_12_2023-RISEGRD-1^06240004.0091001 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
736510418-55150-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0091500 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
272102909-73173-DETAIL-01_16_2023-GO95MLD-1^06240004.0091502 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
272102909-73173-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0091502 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
820435704-65704-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0091503 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
86898489-4273-DETAIL-01_11_2023-GO95BLTC-1^06240004.0092203 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
86898489-4273-DETAIL-01_11_2023-GO95TCH-1^06240004.0092203 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
178877481-85830-DETAIL-01_11_2023-ABNDEQPM-1^06240004.0092204 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
332838129-34473-DETAIL-01_18_2023-GO95TCH-1^06240004.0092300 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
660273109-50473-DETAIL-01_18_2023-GO95MLD-1^06240004.0092302 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
660273109-50473-DETAIL-01_18_2023-SVCROOF-1^06240004.0092302 | OTHER | CA-TIER-2 | Distribution | 2023-01-18 | 2026-01-18 | 2
669328988-52940-DETAIL-01_16_2023-SVCWIND-1^06240004.0092500 | OTHER | CA-TIER-3 | Distribution | 2023-01-16 | 2026-01-16 | 2
110469498-80050-DETAIL-01_16_2023-GO95MLD-1^06240004.0092505 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
229769878-73840-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0092506 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
229769878-73840-DETAIL-01_16_2023-SVCDEFLC-2^06240004.0092506 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
880984038-38640-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0092540 | OTHER | CA-TIER-2 | Distribution | 2023-01-16 | 2026-01-16 | 2
587235888-89963-DETAIL-01_12_2023-GRDRODHI-1^06240004.0093200 | OTHER | CA-TIER-2 | Distribution | 2023-01-12 | 2026-01-12 | 2
680378534-260-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0095204 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
371039593-96550-DETAIL-01_09_2023-SVCDEFLC-1^06240004.0096604 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
437032753-68780-DETAIL-01_10_2023-GUYHINS-1^06240004.0097001 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
234928153-29760-DETAIL-01_10_2023-GO95HV-1^06240004.0097040 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2028-01-10 | 3
234928153-29760-DETAIL-01_10_2023-GO95MLD-1^06240004.0097040 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
234928153-29760-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0097040 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
263317043-73760-DETAIL-01_10_2023-GO95MLD-1^06240004.0097042 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
202174733-11760-DETAIL-01_10_2023-GO95MLD-1^06240004.0097140 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
202174733-11760-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0097140 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
795379913-71660-DETAIL-01_10_2023-POLESTEP-1^06240004.0097143 | POLE | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
500134968-36920-DETAIL-01_10_2023-GO95HV-1^06240004.0097200 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2028-01-10 | 3
18718316-82240-DETAIL-01_10_2023-RISEGRD-1^06240004.0097202 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
774405524-70760-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0097300 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
391588628-75450-DETAIL-01_09_2023-GO95MLD-1^06240004.0097502 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
82643198-87550-DETAIL-01_09_2023-SVCDEFLC-1^06240004.0097505 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
395451178-88150-DETAIL-01_09_2023-SVCDEFLC-1^06240004.0097701 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
244203328-77830-DETAIL-01_11_2023-GO95MLD-1^06240004.0098001 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
686710018-46830-DETAIL-01_11_2023-GO95MLD-1^06240004.0098003 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
686710018-46830-DETAIL-01_11_2023-GO95MLD-2^06240004.0098003 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
47284744-66060-DETAIL-01_11_2023-GO95TCH-1^06240004.0098005 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
47284744-66060-DETAIL-01_11_2023-SVCDEFLC-1^06240004.0098005 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
342516373-22960-DETAIL-01_11_2023-GO95HV-1^06240004.0098144 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
342516373-22960-DETAIL-01_11_2023-GO95MLD-1^06240004.0098144 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2028-01-11 | 3
757940848-60830-DETAIL-01_10_2023-GO95TCH-1^06240004.0098206 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
757940848-60830-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0098206 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
244758524-19960-DETAIL-01_11_2023-SVCDEFLC-1^06240004.0098207 | OTHER | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
842096049-57330-DETAIL-01_09_2023-GO95MLD-1^06240004.0098403 | OTHER | CA-TIER-2 | Distribution | 2023-01-09 | 2026-01-09 | 2
621314168-5130-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0099000 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
743916779-55353-DETAIL-01_10_2023-SVCDEFLC-1^06240004.0099001 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
743916779-55353-DETAIL-01_10_2023-SVCDEFLC-2^06240004.0099001 | OTHER | CA-TIER-2 | Distribution | 2023-01-10 | 2026-01-10 | 2
412781893-85380-DETAIL-01_11_2023-POLESTEP-1^06240004.0099003 | POLE | CA-TIER-2 | Distribution | 2023-01-11 | 2026-01-11 | 2
920451008-74670-DETAIL-04_17_2023-SVCDEFLC-1^06240004.0165703 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
897459310-8070-DETAIL-03_29_2023-SVCDEFLC-1^06240004.0165707 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
897459310-8070-DETAIL-03_29_2023-SVCDEFLC-2^06240004.0165707 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
705999990-38670-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0165708 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
705999990-38670-DETAIL-04_19_2023-SVCWIND-1^06240004.0165708 | OTHER | CA-TIER-2 | Distribution | 2023-04-19 | 2026-04-19 | 2
219342309-2270-DETAIL-03_29_2023-SVCWIND-1^06240004.0165740 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
219342309-2270-AUDIT-05_22_2023-SVCROAD-1^06240004.0165740 | OTHER | CA-TIER-2 | Distribution | 2023-05-22 | 2026-05-22 | 2
661292529-37270-DETAIL-03_29_2023-GO95MLD-1^06240004.0165744 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2028-03-29 | 3
290151339-78270-DETAIL-03_29_2023-GO95MLD-1^06240004.0165745 | OTHER | CA-TIER-2 | Distribution | 2023-03-29 | 2026-03-29 | 2
982487914-84999-DETAIL-04_17_2023-GO95CL10-1^06240004.0165750 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2028-04-17 | 3
982487914-84999-DETAIL-04_17_2023-GO95MLD-1^06240004.0165750 | OTHER | CA-TIER-2 | Distribution | 2023-04-17 | 2026-04-17 | 2
251764928-54170-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0166905 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
65776718-14170-DETAIL-03_28_2023-GO95MLD-1^06240004.0166906 | OTHER | CA-TIER-2 | Distribution | 2023-03-28 | 2026-03-28 | 2
64820063-82380-DETAIL-03_22_2023-GO95HV-1^06240004.0167000 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2028-03-22 | 3
64820063-82380-DETAIL-03_22_2023-GO95MLD-1^06240004.0167000 | OTHER | CA-TIER-2 | Distribution | 2023-03-22 | 2026-03-22 | 2
496435030-25470-DETAIL-03_27_2023-GO95MLD-1^06240004.0167002 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
633510681-70080-DETAIL-03_27_2023-GO95MLD-1^06240004.0167005 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
633510681-70080-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167005 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
633510681-70080-DETAIL-03_27_2023-SVCENTCO-1^06240004.0167005 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
673966860-74570-DETAIL-03_27_2023-GO95MLD-1^06240004.0167008 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
889857653-49280-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0167009 | OTHER | CA-TIER-2 | Distribution | 2023-03-27 | 2026-03-27 | 2
318008961-4980-DETAIL-04_10_2023-SVCDEFLC-1^06240004.0168307 | OTHER | CA-TIER-2 | Distribution | 2023-04-10 | 2026-04-10 | 2
411981968-5270-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0168400 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
880259410-78370-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0168406 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
617732813-60680-DETAIL-04_11_2023-GO95TCH-1^06240004.0168410 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
698978613-77580-DETAIL-04_11_2023-GO95MLD-1^06240004.0168411 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
116573013-15580-DETAIL-04_11_2023-GO95MLD-1^06240004.0168412 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
275009669-76470-DETAIL-04_11_2023-GO95MLD-1^06240004.0168414 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
698966288-89670-DETAIL-04_12_2023-SVCENTBK-1^06240004.0168501 | OTHER | CA-TIER-2 | Distribution | 2023-04-12 | 2026-04-12 | 2
328193518-46370-DETAIL-04_13_2023-SVCDEFLC-1^06240004.0168502 | OTHER | CA-TIER-2 | Distribution | 2023-04-13 | 2026-04-13 | 2
971559509-85870-DETAIL-04_11_2023-SVCWIND-1^06240004.0168505 | OTHER | CA-TIER-2 | Distribution | 2023-04-11 | 2026-04-11 | 2
308478551-43863-DETAIL-01_24_2023-GO95MLD-1^06240005.0129903 | OTHER | CA-TIER-2 | Distribution | 2023-01-24 | 2026-01-24 | 2
232342204-64579-DETAIL-09_01_2021-ENCHRW-1^06240008.0298500 | OTHER | CA-NON-TIER | Distribution | 2021-09-01 | 2024-09-01 | 2
263056064-55519-ADMIN-07_12_2023-POLEREPL-1^06240008.0298701 | POLE | CA-NON-TIER | Distribution | 2023-07-12 | 2026-07-12 | 2
383171044-90099-ADMIN-07_20_2023-POLEREPL-1^06240009.0029900 | POLE | CA-NON-TIER | Distribution | 2023-07-20 | 2026-07-20 | 2
602150345-2719-DETAIL-05_16_2024-INSULDMG-1^06240009.0127701 | INSULATOR AND BUSHING | CA-NON-TIER | Distribution | 2024-05-16 | 2027-05-16 | 2
979309036-56119-ADMIN-07_19_2023-POLEREPL-1^06240009.0134100 | POLE | CA-NON-TIER | Distribution | 2023-07-19 | 2026-07-19 | 2
738377705-23070-ADMIN-09_23_2024-INSULDMG-1^06241003.0327001 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
730677543-88380-ADMIN-09_23_2024-ANCPUCO-1^06241003.0328100 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
751690833-3180-ADMIN-09_23_2024-INSULDMG-1^06241003.0328101 | INSULATOR AND BUSHING | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
79638843-60580-ADMIN-09_23_2024-COPLLEAN-1^06241003.0329100 | POLE | CA-TIER-2 | Distribution | 2024-09-23 | 2025-09-23 | 2
207401714-78830-DETAIL-05_03_2023-GO95MLD-1^06241005.0252141 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
467795914-74830-DETAIL-05_02_2023-GO95MLD-1^06241005.0252142 | OTHER | CA-TIER-2 | Distribution | 2023-05-02 | 2026-05-02 | 2
826168879-39879-DETAIL-05_03_2023-GO95MLD-1^06241005.0252200 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
828854553-63130-DETAIL-05_03_2023-GO95HV-1^06241005.0252400 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
828854553-63130-DETAIL-05_03_2023-GO95MLD-1^06241005.0252400 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
328615103-17430-DETAIL-05_03_2023-GO95MLD-1^06241005.0252401 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
369208263-14130-DETAIL-05_03_2023-GO95MLD-1^06241005.0252502 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
848374894-71430-DETAIL-05_03_2023-GO95MLD-1^06241005.0252600 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
511755164-88230-DETAIL-05_03_2023-GUYNOINS-1^06241005.0252601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
511755164-88230-DETAIL-05_03_2023-GUYNOINS-2^06241005.0252601 | ANCHOR/GUY | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
734953334-10230-DETAIL-05_03_2023-SVCDEFLC-1^06241005.0253500 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2026-05-03 | 2
356267454-44230-DETAIL-05_03_2023-ABNDEQPM-1^06241005.0253600 | OTHER | CA-TIER-2 | Distribution | 2023-05-03 | 2028-05-03 | 3
867145189-12199-ADMIN-07_21_2023-POLEREPL-1^06241009.0365800 | POLE | CA-NON-TIER | Distribution | 2023-07-21 | 2026-07-21 | 2
909832179-27919-ADMIN-06_18_2024-POLEREPL-1^06241009.0365801 | POLE | CA-NON-TIER | Distribution | 2024-06-18 | 2027-06-18 | 2
950474609-81681-DTLSB-08_03_2022-GRDRODHI-1^06242004.0192300 | OTHER | CA-TIER-2 | Distribution | 2022-08-03 | 2025-08-03 | 2
56909367-90467-DTLSB-08_02_2022-GO95MLD-1^06242004.0193300 | OTHER | CA-TIER-2 | Distribution | 2022-08-02 | 2025-08-02 | 2
839899343-46241-DTLSB-08_25_2022-ABNDEQPM-1^06242005.0081500 | OTHER | CA-TIER-2 | Distribution | 2022-08-25 | 2027-08-25 | 3
869895219-7219-DTLSB-07_25_2022-GO95MLD-1^06242005.0139630 | OTHER | CA-TIER-2 | Distribution | 2022-07-25 | 2025-07-25 | 2
559212444-26061-DTLSB-07_19_2022-ABNDEQPM-1^06242005.0146800 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
421127934-4061-DTLSB-07_19_2022-ABNDEQPM-1^06242005.0146801 | OTHER | CA-TIER-2 | Distribution | 2022-07-19 | 2027-07-19 | 3
646161882-15229-DETAIL-05_09_2024-SVCDEFLC-1^06142012.0120405 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
417768965-2929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120409 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
372455971-36929-DETAIL-05_09_2024-GO95HV-1^06142012.0120412 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
372455971-36929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120412 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
365712236-63236-DETAIL-05_09_2024-GO95MLD-1^06142012.0120414 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
541278183-5129-DETAIL-05_09_2024-GO95MLD-1^06142012.0120500 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
541278183-5129-DETAIL-05_09_2024-SVCDEFLC-1^06142012.0120500 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
604008573-64929-DETAIL-05_09_2024-GO95HV-1^06142012.0120504 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
604008573-64929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120504 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
945304693-2929-DETAIL-05_09_2024-GO95BLTC-1^06142012.0120505 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
945304693-2929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120505 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
194110384-41329-DETAIL-05_09_2024-GO95MLD-1^06142012.0120508 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
991432582-71429-DETAIL-05_09_2024-GO95MLD-1^06142012.0121307 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
886650599-34529-DETAIL-05_09_2024-GO95MLD-1^06142012.0121308 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
833685711-68829-DETAIL-05_09_2024-GO95MLD-1^06142012.0121403 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
393214181-46629-DETAIL-05_09_2024-GO95MLD-1^06142012.0121406 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
371579082-45529-DETAIL-05_09_2024-GO95MLD-1^06142012.0121407 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
371579082-45529-DETAIL-05_09_2024-GUYNOINS-1^06142012.0121407 | ANCHOR/GUY | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
91676891-27929-DETAIL-05_09_2024-GO95MLD-1^06142012.0121409 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
91676891-27929-DETAIL-05_09_2024-SVCDEFLC-1^06142012.0121409 | OTHER | FHCA | Distribution | 2024-05-09 | 2027-05-09 | 2
784204989-68829-DETAIL-05_09_2024-GO95HV-1^06142012.0121410 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
541039473-92529-DETAIL-05_09_2024-GO95MLD-1^06142012.0121504 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
462887023-55929-AUDIT-05_29_2024-SVCDEFLC-1^06142012.0121601 | OTHER | FHCA | Distribution | 2024-05-29 | 2027-05-29 | 2
566575073-16929-DETAIL-05_09_2024-GO95MLD-1^06142012.0121603 | OTHER | FHCA | Distribution | 2024-05-09 | 2029-05-09 | 3
336309641-94429-DETAIL-05_07_2024-GUYHINS-1^06142012.0122108 | ANCHOR/GUY | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
604571885-1029-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0122110 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
173327101-9729-DETAIL-05_07_2024-GO95MLD-1^06142012.0122200 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
670370410-23529-DETAIL-05_07_2024-GO95MLD-1^06142012.0122204 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
183010701-63929-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0122205 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
183010701-63929-DETAIL-05_07_2024-SVCENTCO-1^06142012.0122205 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
775182231-12829-DETAIL-05_13_2024-GO95MLD-1^06142012.0122206 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
775182231-12829-DETAIL-05_13_2024-GRDRODHI-1^06142012.0122206 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
890431731-54192-DETAIL-05_13_2024-SVCRUBLG-1^06142012.0122300 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
590777685-32529-DETAIL-05_13_2024-GO95MLD-1^06142012.0122301 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
590777685-32529-DETAIL-05_13_2024-GRDRODHI-1^06142012.0122301 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
803106481-92829-DETAIL-05_13_2024-GO95MLD-1^06142012.0122304 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
840329963-43629-DETAIL-05_15_2024-GO95HV-1^06142012.0122900 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
977801883-44629-DETAIL-05_16_2024-GO95MLD-1^06142012.0122902 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
977801883-44629-DETAIL-05_16_2024-GRDRODHI-1^06142012.0122902 | OTHER | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
154261573-24629-DETAIL-05_15_2024-GO95HV-1^06142012.0122903 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
18172860-65040-DETAIL-05_06_2024-GO95MLD-1^06142012.0123000 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
863446189-40129-DETAIL-05_06_2024-GO95MLD-1^06142012.0123002 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
863446189-40129-DETAIL-05_06_2024-SVCENTCO-1^06142012.0123002 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
794393071-64672-DETAIL-05_06_2024-GO95HV-1^06142012.0123004 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
623405051-95831-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0123005 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
447356069-77501-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0123006 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
795771070-2872-DETAIL-05_06_2024-GO95MLD-1^06142012.0123007 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
16122131-40989-DETAIL-05_06_2024-GO95HV-1^06142012.0123008 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
748468641-18129-DETAIL-05_13_2024-GO95MLD-1^06142012.0123307 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
56350956-34829-DETAIL-05_13_2024-GO95MLD-1^06142012.0123308 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
649763581-33829-DETAIL-05_13_2024-GO95MLD-1^06142012.0123402 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
858715182-49882-DETAIL-05_13_2024-GO95MLD-1^06142012.0123404 | OTHER | FHCA | Distribution | 2024-05-13 | 2029-05-13 | 3
858715182-49882-DETAIL-05_13_2024-SVCDEFLC-1^06142012.0123404 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
999600688-45729-DETAIL-05_13_2024-GO95MLD-1^06142012.0123407 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
185159613-70829-DETAIL-05_01_2024-GO95MLD-1^06142012.0123500 | OTHER | FHCA | Distribution | 2024-05-01 | 2029-05-01 | 3
185159613-70829-DETAIL-05_01_2024-GUYHINS-1^06142012.0123500 | ANCHOR/GUY | FHCA | Distribution | 2024-05-01 | 2027-05-01 | 2
185159613-70829-DETAIL-05_01_2024-SVCNEUT-1^06142012.0123500 | OTHER | FHCA | Distribution | 2024-05-01 | 2027-05-01 | 2
995571644-98929-DETAIL-05_14_2024-GO95MLD-1^06142012.0123502 | OTHER | FHCA | Distribution | 2024-05-14 | 2029-05-14 | 3
58178385-96729-DETAIL-05_01_2024-SVCENTCO-1^06142012.0123640 | OTHER | FHCA | Distribution | 2024-05-01 | 2027-05-01 | 2
699515935-10411-DETAIL-05_15_2024-GO95HV-1^06142012.0123703 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
408239840-24429-DETAIL-05_02_2024-GO95MLD-1^06142012.0124104 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
235876800-95429-DETAIL-05_06_2024-GO95MLD-1^06142012.0124109 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
135787351-57180-DETAIL-05_06_2024-GO95MLD-1^06142012.0124110 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
45827950-42629-DETAIL-05_02_2024-GO95MLD-1^06142012.0124202 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
498916229-80129-DETAIL-05_07_2024-GO95HV-1^06142012.0124203 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
498916229-80129-DETAIL-05_07_2024-GO95MLD-1^06142012.0124203 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
930102606-15829-DETAIL-05_07_2024-GO95HV-1^06142012.0124204 | OTHER | FHCA | Distribution | 2024-05-07 | 2029-05-07 | 3
287351411-2129-DETAIL-05_07_2024-GO95MLD-1^06142012.0124205 | OTHER | FHCA | Distribution | 2024-05-07 | 2027-05-07 | 2
200235629-51740-DETAIL-05_13_2024-GUYNOINS-1^06142012.0124303 | ANCHOR/GUY | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
260534399-16400-DETAIL-05_13_2024-GO95MLD-1^06142012.0124304 | OTHER | FHCA | Distribution | 2024-05-13 | 2027-05-13 | 2
370227409-30020-ADMIN-04_01_2020-POLEDERP-1^06142012.0124305 | POLE | FHCA | Distribution | 2020-04-01 | 2023-04-01 | 2
798691455-41729-DETAIL-05_16_2024-LIGHT-1^06142012.0124803 | CONNECTION DEVICE | FHCA | Distribution | 2024-05-16 | 2027-05-16 | 2
906983053-12629-DETAIL-05_15_2024-GO95MLD-1^06142012.0124900 | OTHER | FHCA | Distribution | 2024-05-15 | 2029-05-15 | 3
125532318-72570-DETAIL-05_06_2024-GO95SVC-1^06142012.0125001 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
264555309-80029-DETAIL-05_06_2024-GO95MLD-1^06142012.0125002 | OTHER | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
391902359-55140-DETAIL-05_06_2024-XARMSPCR-1^06142012.0125003 | CROSSARM | FHCA | Distribution | 2024-05-06 | 2027-05-06 | 2
868488428-92622-DETAIL-05_06_2024-GO95MLD-1^06142012.0125005 | OTHER | FHCA | Distribution | 2024-05-06 | 2029-05-06 | 3
502559129-98481-DETAIL-05_02_2024-SVCDEFLC-1^06142012.0125007 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
945941738-42713-DETAIL-05_02_2024-GO95MLD-1^06142012.0125008 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
159276749-88200-DETAIL-05_02_2024-GO95HV-1^06142012.0125010 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3
611760299-25321-DETAIL-05_02_2024-SVCDEFLC-1^06142012.0125101 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
101827519-13740-DETAIL-05_02_2024-GO95MLD-1^06142012.0125104 | OTHER | FHCA | Distribution | 2024-05-02 | 2027-05-02 | 2
223995109-75860-DETAIL-05_02_2024-GO95MLD-1^06142012.0125106 | OTHER | FHCA | Distribution | 2024-05-02 | 2029-05-02 | 3

## Table 14
Utility | PacifiCorp
Table No. | 14
Date Modified
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Non-HFTD Distribution
HFTD 2 Distribution
HFTD 3 Distribution
Non-HFTD Transmission
HFTD 2 Transmission
HFTD 3 Transmission

## Table 15
Utility | PacifiCorp
Table No. | 15
Date Modified | 2024-11-01
Table 15: Top Risk Circuit Scores
*EC to add all other risk categories to right of last required category.
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
5G31 | Circuit | Distribution | 29.5 | Top 5% highest risk | Non-HFTD |  | 0.4
5G33 | Circuit | Distribution | 45.4 | Top 5% highest risk | Non-HFTD |  | 0.48
5G21 | Circuit | Distribution | 84 | Top 5% highest risk | HFTD Tier 2 |  | 0.31
5G83 | Circuit | Distribution | 126.5 | Top 5% highest risk | HFTD Tier 3 |  | 0.39
5G149 | Circuit | Distribution | 73.8 | Top 5% highest risk | HFTD Tier 2 |  | 0.32
5G5 | Circuit | Distribution | 26.6 | Top 5% highest risk | HFTD Tier 2 |  | 0.2
5L83 | Circuit | Distribution | 64.5 | Top 5% highest risk | Non-HFTD |  | 0.1
5G45 | Circuit | Distribution | 23.6 | Top 5% highest risk | HFTD Tier 3 |  | 0.16
5L97 | Circuit | Distribution | 18.6 | Top 5% highest risk | HFTD Tier 2 |  | 0.14
4G1 | Circuit | Distribution | 97.1 | Top 5% highest risk | HFTD Tier 2 |  | 0.59
5G151 | Circuit | Distribution | 11.8 | Top 5% highest risk | HFTD Tier 2 |  | 0.18
7G81 | Circuit | Distribution | 3.6 | Top 5% highest risk | HFTD Tier 2 |  | 0.2
7G73 | Circuit | Distribution | 2 | Top 5% highest risk | HFTD Tier 3 |  | 0.31
5L87 | Circuit | Distribution | 69.8 | Top 5% highest risk | HFTD Tier 2 |  | 0.32