## Cover Sheet Tables 1-15
| Yes | No | <-- for dropdowns
Energy Safety Data Guidelines, Appendix D
Wildifire Mitigation Data Tables Template: Tables 1 - 15
Update the below table to establish which reporting period this submission this represents.
Utility Name |  | PG&E
First year of 3-year WMP cycle |  | 2023
Reporting Period year |  | 2024
Reporting Period quarter |  | Q4 |  | Q1 | 2023
Date Modified |  | 2025-02-18 |  | Q2 | 2024
|  |  |  | Q3 | 2025
Q4

## Table 1
UtilityID | SubmissionDate | InitiativeClassification | ProjectStartDate | ProjectEndDate | UtilityInitiativeName | InitiativeDescription | InitiativeObjective | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeTrackingID | WMPInitiativeCode | WMPPageNumber | RiskTargetReduction | MidYearTarget (Yes/No) | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
PGE | 2025-02-03 | Program |  |  | Detailed Inspection Transmission – Ground | Complete detailed ground inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. | This initiative includes detailed inspections (ground) of transmission poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Ground Detailed Inspections |  | 8.1.3.1.1 | AI-02 | PGE_Grid Design, Operations and Maintenance_Ground Detailed Inspections_AI-02_2024 | 471 | Equipment ignition likelihood | Yes | # of structures | 20000 | 4000 | 12000 | 20000 | 20000 | 5357 | 21357 | 21680 | 21713 |  | Please note that we revised this annual target from "approximately 20,000" structures inspected to 21,390 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated Q1 target of 3,650 by completing 5,523 structures inspected. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 21,390 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated Q2 target of 12,000 by completing 21,383 structures inspected. This program status is 'In Progress' as we are 7 additional units to complete to meet our 2024 updated target. Please note that the Q1 completed units have been revised to 5,364 from 5,523. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 21,390 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the Q3 target of 20,000 by completing 21,702 structures inspected. This program is now "Completed' as we surpassed the updated target of 21,390 by completing 21,702 TYD. Please note that the Q2 completed units have been revised to 21,379 from 21,383. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 21,390 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. Please also note that the Q1 completed units have been revised to 5,357 from 5,364, Q2 completed units have been revised to 21,357 from 21,379, and Q3 completed units has been updated to 21,680 from 21,702. | Completed
PGE | 2025-02-03 | Program |  |  | Detailed Inspection Transmission – Aerial | Complete detailed aerial inspections on approximately 20,000 transmission structures in PG&E’s asset registry as of January 1, 2024. | This initiative includes detailed inspections (aerial) of transmission poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Aerial Detailed Inspections |  | 8.1.3.1.2 | AI-04 | PGE_Grid Design, Operations and Maintenance_Aerial Detailed Inspections_AI-04_2024 | 472 | Equipment ignition likelihood | Yes | # of structures | 20000 | 5000 | 17000 | 20000 | 20000 | 5212 | 22135 | 22763 | 22865 |  | Please note that we revised this annual target from "approximately 20,000" structures inspected to 22,274 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q1 target of 3,100 by completing 5,253 structures inspected. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 22,274 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q2 target of 17,000 by completing 22,311 structures inspected. Please note that the Q1 units have been updated to 5201 from 5,253. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 22,274 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q3 target of 20,000 by completing 22,838 structures inspected. This program is now "Completed' as we surpassed the updated target of 22,274 by completing 22,838 TYD. Please note that the Q1 units have been updated to 5,219 from 5,201 and Q2 units have been updated to 22,208 from 22,311. | Please note that we revised this annual target from "approximately 20,000" structures inspected to 22,274 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. Please also note that the Q1 units have been updated to 5,212 from 5,219, Q2 units have been updated to 22,135 from 22,208, and Q3 units are updated to 22,763 from 22,838. | Completed
PGE | 2025-02-03 | Program |  |  | Detailed Inspection Transmission – Climbing | Complete detailed climbing inspections on approximately 1,200 transmission structures in PG&E’s asset registry as of January 1, 2024. | This initiative includes detailed inspections (climbing) of transmission poles which can reduce the potential for equipment failure which could case a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Climbing Detailed Inspections |  | 8.1.3.1.3 | AI-05 | PGE_Grid Design, Operations and Maintenance_Climbing Detailed Inspections_AI-05_2024 | 473 | Equipment ignition likelihood | Yes | # of structures | 1200 | 400 | 900 | 1200 | 1200 | 636 | 1216 | 1216 | 1216 |  | Please note that we revised this annual target from "approximately 1,200" structures inspected to 1,216 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q1 target of 280 by completing 661 structures inspected. | Please note that we revised this annual target from "approximately 1,200" structures inspected to 1,216 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q2 target of 1,150 by completing 1,216 structures inspected and completed the commitment for the year. Please note that the Q1 value has been updated to 636 from 661. | Please note that we revised this annual target from "approximately 1,200" structures inspected to 1,216 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We completed the target in Q2 by completing 1,216 structures. | Please note that we revised this annual target from "approximately 1,200" structures inspected to 1,216 structures inspected to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. | Completed
PGE | 2025-02-03 | Program |  |  | Perform transmission infrared inspections | In 2024, infrared patrols will be performed on energized transmission lines in HFTD areas resulting in infrared patrols on 4,000 miles of transmission line. | This initiative includes transmission infrared inspections which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Infrared Inspections |  | 8.1.3.1.4 | AI-06 | PGE_Grid Design, Operations and Maintenance_Infrared Inspections_AI-06_2024 | 474 | Equipment ignition likelihood | Yes | # of miles | 4000 | 1000 | 1500 | 3000 | 4000 | 1560.46 | 2652.8 | 3867 | 4339.38 |  | Please note that we revised this annual target from "approximately 4,000" circuit miles to 4,315 circuit miles to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q1 target of 600 by completing 1,363 circuit miles. | Please note that we revised this annual target from "approximately 4,000" circuit miles to 4,315 circuit miles to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q2 target of 1900 by completing 2550.19 circuit miles. Please note that the Q1 value has been updated to 1478.92 from 1,363. | Please note that we revised this annual target from "approximately 4,000" circuit miles to 4,315 circuit miles to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. We surpassed the updated Q3 target of 3,300 by completing 3,861.26 circuit miles. Please note that the Q1 value has been updated to 1,560.46 from 1,479 and Q2 value to 2,652.8 from 2,550.2. | Please note that we revised this annual target from "approximately 4,000" circuit miles to 4,315 circuit miles to align with our updated asset registry numbers for January 2024. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order, and are therefore describing this revision here. Please also note that the Q3 value has been updated to 3,867 from 3,861.3. | Completed
PGE | 2025-02-03 | Program |  |  | Detailed Ground Inspections - Distribution | Complete detailed inspections on approximately 220,016 distribution poles, which will be identified in PG&E’s asset registry as of December 27, 2022. | This initiative includes detailed inspections of distribution poles which can reduce the potential for equipment failure which could cause a potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Detailed Ground Inspections |  | 8.1.3.2.1 | AI-07 | PGE_Grid Design, Operations and Maintenance_Detailed Ground Inspections_AI-07_2024 | 481 | Equipment ignition likelihood | Yes | # of poles | 220016 | 26000 | 70000 | 150000 | 220016 | 26309 | 94233 | 175940 | 223146 |  | Please note that we revised this annual target from Change Order approved value of 220,016 poles to 220,042 poles to align with our most recent asset registry numbers. This target's Change Order request was approved, and as such we have updated the Annual Target and Quarterly projected values. | Please note that we revised this annual target from Change Order approved value of 220,016 poles to 220,042 poles to align with our most recent asset registry numbers. We have surpassed the Q2 target of 70,000 by completing 95,740 poles. Please note that Q1 value has been updated to 26,522 from 27,975. | Please note that we revised this annual target from Change Order approved value of 220,016 poles to 220,042 poles to align with our most recent asset registry numbers. We have surpassed the Q3 target of 150,000 by completing 175,940 poles. Please note that Q1 value has been updated to 26,309 from 26,522 and Q2 value to 94,233 to 95,740. | Please note that we revised this annual target from Change Order approved value of 220,016 poles to 220,042 poles to align with our most recent asset registry numbers. Please also note that, of the 223,146 inspections identified, included are 2,104 constrained inspections. | Completed
PGE | 2025-02-03 | Program |  |  | Supplemental Inspections - Substation Distribution | Complete supplemental inspections on 76 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | 8.1 | Asset Inspection Program - Substation |  | 8.1.3.3.1 | AI-08 | PGE_Grid Design, Operations and Maintenance_Asset Inspection Program - Substation_AI-08_2024 | 492 | Equipment ignition likelihood | Yes | # of Distribution Substations | 76 | 16 | 68 | 76 | 76 | 0 | 12 | 76 | 76 |  | Due to the Change Order decision rejecting the update to this target on procedural grounds, the Q1 Status has been revised to "Delayed" from "In Progress." | Please note that the Q1 progress is updated to 0 from 2. The Change Order rejection for this Target has mandated each commitment to complete supplemental Infrared (IR) and ground inspections for each substation, in addition to the aerial inspection. | Please note that the Q2 progress is updated to 12 from 14. |  | Completed
PGE | 2025-02-03 | Program |  |  | Supplemental Inspections - Substation Transmission | Complete supplemental inspections on 36 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | 8.1 | Asset Inspection Program - Substation |  | 8.1.3.3.1 | AI-09 | PGE_Grid Design, Operations and Maintenance_Asset Inspection Program - Substation_AI-09_2024 | 492 | Equipment ignition likelihood | Yes | # of Transmission Substations | 36 | 16 | 33 | 36 | 36 | 0 | 6 | 36 | 36 |  | Due to the Change Order decision rejecting the update to this target on procedural grounds, the Q1 Status has been revised to "Delayed" from "In Progress." | Please note that the Q1 target has been changed to 0 from 1. The Change Order rejection for this Target has mandated each commitment to complete supplemental Infrared (IR) and ground inspections for each substation, in addition to the aerial inspection. |  |  | Completed
PGE | 2025-02-03 | Program |  |  | Supplemental Inspections - Hydroelectric Substations and Powerhouses | Complete supplemental inspections on 46 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative provides for supplemental substation inspections to identify equipment issues and damages that may impact reliability and/or pose wildfire ignition risk. | Grid Design, Operations and Maintenance | 8.1 | Asset Inspection Program - Substation |  | 8.1.3.3.1 | AI-10 | PGE_Grid Design, Operations and Maintenance_Asset Inspection Program - Substation_AI-10_2024 | 492 | Equipment ignition likelihood | Yes | # of Hydroelectric Substations and Powerhouses | 46 | 15 | 45 | 46 | 46 | 0 | 1 | 46 | 46 |  | Due to the Change Order decision rejecting the update to this target on procedural grounds, the Q1 Status has been revised to "Delayed" from "In Progress." | Please note that the Q1 target has been changed to 0 from 1. The Change Order rejection for this Target has mandated each commitment to complete supplemental Infrared (IR) and ground inspections for each substation, in addition to the aerial inspection. | Please note that the Q2 value has been updated to 1 from 4. |  | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-09-30 | Community Engagement - Meetings | PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. | This initiative concerns customer and community events to further awareness of WMP activities. | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | CO-01 | PGE_Community Outreach and Engagement_Public Outreach and Education Awareness Program_CO-01_2024 | 885 | Wildfire vulnerability | No | [10 empty] | PG&E will hold annually a total of 22 community engagement meetings within the five regions of service that will include, but are not limited to, a mix of webinars, open houses, town halls, and/or answer centers. | In Q1 of 2024, a total of five Regional Townhalls halls and one CWSP Safety Webinar were conducted. | A total of 14 events counting toward the CO-01 WMP initiative have been completed this year be end of Q2: 13 community events in Q2 of 2024, and one event in Q1 of 2024. In Q2 of 2024, PG&E conducted five Regional Townhalls, seven CWSP Safety Webinars, and one in-person Open House in Boulder Creek. | A total of 25 events counting toward the CO-01 WMP initiative have been completed YTD; 1 event in Q1; 13 events in Q2. In Q3, PG&E conducted 5 Regional Townhalls, 4 CWSP Safety Webinars, and 2 In-Person Open Houses. This initiative is complete for 2024 | This initiative was completed in Q3. | Completed
PGE | 2025-02-03 | Program |  |  | Community Engagement - Surveys | PG&E will complete two PSPS education and outreach surveys, barring External Factors. | This initiative concerns customer and community events to further awareness of WMP activities. | Community Outreach and Engagement | 8.5 | Public Outreach and Education Awareness Program |  | 8.5.2 | CO-02 | PGE_Community Outreach and Engagement_Public Outreach and Education Awareness Program_CO-02_2024 | 885 | Wildfire vulnerability | Yes | # of surveys | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 |  | In Q1 of 2024, PG&E completed the PSPS Post-Season outreach survey, which is one of the two required surveys. |  |  | In Q4 of 2024, PG&E completed the PSPS Pre-Season outreach survey, which is the second and final survey completed for 2024. This initiative is complete for 2024. | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-11-30 | Complete PSPS and Wildfire Tabletop and Functional Exercises | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP) | This initiative will complete the PSPS and Wildfire Tabletop and Functional Exercise to assist with our response to emergency activations, including wildfires. | Emergency Preparedness Plan | 8.4 | Drills, Simulations, and Tabletop Exercises |  | 8.4.2.3.1 | EP-01 | PGE_Emergency Preparedness Plan_Drills, Simulations, and Tabletop Exercises_EP-01_2024 | 821 | PSPS likelihood | No | [10 empty] | Complete PSPS and Wildfire Tabletop and Functional Exercise annually in compliance with the guiding principles of the Homeland Security Exercise Evaluation Program (HSEEP) | This work remains on track. The Public Safety Power Shutoff Tabletop (PSPS) Exercise was conducted on March 19, 2024. The after-action report for this exercise is under development. The Wildfire Tabletop exercise will take place during the April 15-19 PSPS Full Scale Exercise (FSE), and is on track to be held as scheduled. | This work remains on track. The after-action report for The Public Safety Power Shutoff (PSPS) Tabletop Exercise is complete. The PSPS Full Scale Exercise (FSE) and the Wildfire FSE were conducted on April 15-19, 2024. The after-action report is complete. The Wildfire Tabletop exercise will take place on August 22, 2024. | This work remains on track. The Wildfire Tabletop exercise was held on August 22, 2024. The after action report is scheduled to be completed by October 22, 2024, which will complete the work for the year. | The 2024 Wildfire and PSPS Tabletop and Functional exercises are complete. The PSPS TTX was held on March 19, 2024, the PSPS Functional exercise was held on April 15 to 19, 2024. The Wildfire Tabletop was held on August 22, 2024 and the after-action report completed on October 22, 2024. | Completed
PGE | 2025-02-03 | Program |  |  | Review, and revise the CERP and 2 Wildfire Related Annexes on a yearly basis | Review and revise the CERP (internal document number EMER-3001M) on a yearly basis. | This initiative will review, and revise the CERP and 2 Wildfire Related Annexes to provide emergency response and safely and expeditiously restore service, including during wildfires. | Emergency Preparedness Plan | 8.4 | Emergency Planning |  | 8.4.3.1 | EP-06 | PGE_Emergency Preparedness Plan_Emergency Planning_EP-06_2024 | 838 | PSPS likelihood | No | Company Emergency Response Plan (CERP) and the two wildfire related annexes | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 2 | 3 |  | The Wildfire Annex update was completed on March 29, 2024. This objective is on track to be completed in 2024. | This work remains on track. CERP is in the review and revision process with an expected publication date in Q4. | This work remains on track. The Wildfire Annex was completed on March 29, 2024 and the PSPS Annex was completed on July 31, 2024. The CERP document is in the review process and anticipated to be completed in Q4. | The Wildfire Annex was completed on March 29, 2024 and the PSPS Annex was completed on July 31, 2024. The CERP document review was completed in November 2024, making this commitment complete for 2024. | Completed
PGE | 2025-02-03 | Program |  |  | System Hardening - Distribution | Complete 470 circuit miles of system hardening work which includes overhead system hardening, undergrounding, and removal of overhead lines in HFTD, HFRA, or buffer zone areas except for any mileage being undergrounded and tracked separately as part of our Butte County Rebuild and other Community Rebuild efforts, barring External Factors | This initiative will harden distribution circuit miles through overhead system hardening, undergrounding, and the removal of overhead lines to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Covered conductor installation |  | 8.1.2.1 | GH-01 | PGE_Grid Design, Operations and Maintenance_Covered conductor installation _GH-01_2024 | 397 | Equipment ignition likelihood | No | # of circuit miles | 280 | 13.4 | 58.8 | 125.8 | 280 | 17.24 | 100.25 | 212.43 | 348.28 |  | This target's Change Order request was approved, and as such we have updated the annual target and quarterly projected values. |  |  |  | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-03-29 | Evaluate Covered Conductor Effectiveness | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. | This initiative will calculate the covered conductor effective using pervious year's outage data on the lines that have covered conductors for consideration in future system hardening workplans. | Grid Design, Operations and Maintenance | 8.1 | Covered conductor installation |  | 8.1.2.1 | GH-02 | PGE_Grid Design, Operations and Maintenance_Covered conductor installation _GH-02_2024 | 397 | Equipment ignition likelihood | No | [10 empty] | Update the covered conductor recorded effectiveness calculation using 2023 and 2024 outage data on the lines that have Covered Conductors for consideration in future system hardening workplans. | We met the 2024 milestones for this objective and consider this work complete for the year. The 2023 outage data--on the lines that have covered conductors for consideration in future system hardening workplans--was downloaded and we adjusted the recorded effectiveness calculation using this data. The documented results were shared with stakeholders to gain buy-in on any adjustments proposed to the covered conductor recorded effectiveness value. | This objective was completed in Q1 | This objective was completed in Q1 | This commitment was completed in Q1. | Completed
PGE | 2025-02-03 | Program |  |  | 10K Undergrounding | Complete 250 circuit miles of undergrounding work. The 250-circuit mile target includes: (1) undergrounding taking place as part of System Hardening, (2) undergrounding taking place as part of the Butte County Rebuild program (including a small volume of previously hardened overhead lines that are being placed underground) or other Community Rebuild programs, and (3) any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas | This initiative will underground electrical facilities to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Undergrounding of electric lines and/or equipment |  | 8.1.2.2 | GH-04 | PGE_Grid Design, Operations and Maintenance_Undergrounding of electric lines and/or equipment_GH-04_2024 | 400 | Equipment ignition likelihood | No | # of circuit miles | 250 | 13 | 48 | 99 | 250 | 14.83 | 61.21 | 119.61 | 257.837 |  | This target's Change Order request was approved, and as such we have updated the Annual Target and Quarterly projected values. |  |  |  | Completed
PGE | 2025-02-03 | Program |  |  | System Hardening - Transmission Shunt Splices | Install shunt splice(s) on 22 transmission lines. | This initiative will install shunt splice(s) on transmission lines to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Traditional overhead hardening - Transmission |  | 8.1.2.5.1 | GH-06 | PGE_Grid Design, Operations and Maintenance_Traditional overhead hardening - Transmission_GH-06_2024 | 436 | Equipment ignition likelihood | No | # of Transmission Lines | 22 | 0 | 6 | 14 | 22 | 1 | 6 | 15 | 23 |  |  |  | Please note that the Q2 progress has been updated to 6 from 7. |  | Completed
PGE | 2025-02-03 | Program |  |  | Distribution Line Motor Switch Operator (MSO) - Replacements | Replace or remove the remaining MSOs from the 47 identified, as of January 26, 2023. | This initiative will replace or remove Motor Switch Operators to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Motor Switch Operator (MSO) Switch Replacement |  | 8.1.2.10.3 | GH-09 | PGE_Grid Design, Operations and Maintenance_Motor Switch Operator (MSO) Switch Replacement_GH-09_2024 | 457 | Equipment ignition likelihood | No | # of MSOs replacements | 26 | 1 | 10 | 20 | 26 | 1 | 11 | 22 | 26 |  |  | The program surpassed the YTD Target of 9 with 10 units completed Q2 YTD, with 9 units completed within Q2. In June, 3 units were completed. Please note that 1 unit (Order # 35206526) was part of the original list of WMP MSO devices, but has been completed by another program under Order # 31438232 with a CN24 Date of 8/19/2022. As a result, we will be counting this unit as a 2024 completion. In total, we will be reporting 11 MSO devices as removed or replaced as part of the original list. Please note that completed units reported are subject to change due to adjustments made to attainment as data gets reconciled. | The program surpassed the YTD Target of 20 with 21 units completed Q3 YTD, with 10 units completed within Q3. In June, 3 units were completed. Please note that 1 unit (Order # 35206526) was part of the original list of WMP MSO devices, but has been completed by another program under Order # 31438232 with a CN24 Date of 8/19/2022. As a result, we will be counting this unit as a 2024 completion. In total, we will be reporting 21 MSO devices as removed or replaced as part of the original list. Please note that completed units reported are subject to change due to adjustments made to attainment as data gets reconciled. | Please note that one unit (Order # 35206526) was part of the original list of WMP MSO devices, but has been completed by another program under Order # 31438232 with a CN24 Date of August 19, 2022. As a result, we will be counting this unit as a 2024 completion. In total, we will be reporting 26 MSO devices as removed or replaced as part of the original list. Please note that Q3 units have been updated to 22 from 21. | Completed
PGE | 2025-02-03 | Program |  |  | Non-Exempt Expulsion Fuse - Removal | Remove non-exempt expulsion fuses/ cutouts from 3,000 fuse locations identified on distribution poles. | This initiative will remove non-exempt equipment that may generate electrical arcs, sparks, or hot material during its normal operation. | Grid Design, Operations and Maintenance | 8.1 | Non-Exempt Expulsion Fuses |  | 8.1.2.10.5 | GH-10 | PGE_Grid Design, Operations and Maintenance_Non-Exempt Expulsion Fuses_GH-10_2024 | 459 | Equipment ignition likelihood | No | # of fuses | 3000 | 80 | 980 | 2440 | 3000 | 215 | 1620 | 2523 | 3106 |  |  | Please note that the Q1 progress has been updated from 166 to 203 | Please note that the Q1 progress has been updated to 209 from 203 and Q2 progress to 1,614 from 1,534. | Please note that Q1 progress has been updated to 215 from 209, Q2 progress to 1620 from 1614, and Q3 progress to 2523 from 2447. | Completed
PGE | 2025-02-03 | Program |  |  | Asset Inspections - Quality Assurance | Perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program as specified below: Transmission Ground Inspection – HFTD/HFRA (Field): 500 audit locations*; 94% pass rate Distribution Ground Inspections – HFTD/HFRA (Field): 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative audits the quality of transmission and distribution system inspections, which can help identify gaps and implement improvements for inspections. | Grid Design, Operations and Maintenance | 8.1 | Quality Assurance (QA) |  | 8.1.6.1 | GM-01 | PGE_Grid Design, Operations and Maintenance_Quality Assurance (QA)_GM-01_2024 | 523 | Equipment ignition likelihood | No | % Pass Rate Audit Locations | Transmission Inspections – HFTD/HFRA : 500 audit locations*; 94% pass rate Distribution Inspections – HFTD/HFRA : 1,500 audit locations*; 90% pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | 92% | 92% | 92% | 92% | 100% | 99.81% | 99.88% | 99.8% |  | QA System Inspection Transmission Pass Rate: Total # of Tower Passed / Total # of Locations Audited Q1 – January - March (01/01/2024 – 03/30/2024): Pass Rate -> 100% Total # of Locations Audited -> 354 Total # of Locations Passed -> 354 Total # of Locations Failed -> 0 Year to Date (01/01/24 – 03/24/24): Pass Rate -> 100% Total # of Locations Audited -> 354 Total # of Locations Passed -> 354 Total # of Locations Failed -> 0 QA System Inspection Distribution – Expected to start April 2024 Pass Rate: Total # of Locations Passed / Total # of Locations Audited Q1 – January - March (01/01/2024 – 03/30/2024): Pass Rate -> NA Total # of Locations Audited -> NA Total # of Locations Passed -> NA Total # of Locations Failed -> NA Year to Date (01/01/24 – 03/30/24): Pass Rate -> NA Total # of Locations Audited -> NA Total # of Locations Passed -> NA Total # of Locations Failed -> NA This Target's Change Order request was approved, and as such we have updated the Annual Target and Quarterly projected values. | QA System Inspection Transmission Q2: Pass Rate -> 99.93% Total # of Locations Audited -> 1456 Total # of Locations Passed -> 1455 Total # of Locations Failed -> 1 Year to Date (Q1 + Q2): Pass Rate -> 99.94% Total # of Locations Audited -> 1810 Total # of Locations Passed -> 1809 Total # of Locations Failed -> 1 Pass Rate: Total # of Locations Passed / Total # of Locations Audited QA System Inspection Distribution Q2: Pass Rate -> 99.60% Total # of Locations Audited -> 2725 Total # of Locations Passed -> 2714 Total # of Locations Failed -> 11 Year to Date (Q1 + Q2): Pass Rate -> 99.60% Total # of Locations Audited -> 2725 Total # of Locations Passed -> 2714 Total # of Locations Failed -> 11 | QA System Inspection Transmission Q3: Pass Rate -> 100% Total # of Locations Audited -> 933 Total # of Locations Passed -> 933 Total # of Locations Failed -> 0 Year to Date(Q1+Q2+Q3) Pass Rate -> 99.97% Total # of Locations Audited -> 2,981 Total # of Locations Passed -> 2,980 Total # of Locations Failed -> 1 QA System Inspection Distribution Q3 : Pass Rate -> 99.79% Total # of Locations Audited -> 2,916 Total # of Locations Passed -> 2,910 Total # of Locations Failed -> 6 Year to Date(Q1+Q2+Q3) Pass Rate -> 99.74% Total # of Locations Audited -> 6,183 Total # of Locations Passed -> 6,167 Total # of Locations Failed -> 16 | QA System Inspection Transmission Pass Rate -> 99.97% Total # of Locations Audited -> 2970 Total # of Locations Passed -> 2969 Total # of Locations Failed -> 1 QA System Inspection Distribution Pass Rate -> 99.69% Total # of Locations Audited -> 7098 Total # of Locations Passed -> 7076 Total # of Locations Failed -> 12 | Completed
PGE | 2025-02-03 | Program |  |  | Eliminate HFTD-HFRA Distribution Backlog | Close at least 25,000 additional EC notifications on top of closing an equivalent number of EC notifications created in HFRA/HFTD locations in 2024. Based on the forecasted amount of new EC notifications, we expect a total forecasted execution plan of 89,000 EC notifications for 2024. Of these EC notifications, we expect to close 46,000 distribution backlog(a) ignition risk EC notifications with the remaining balance to be from backlog or newly identified EC notifications. This work will reduce 68 percent of the wildfire risk associated with backlog ignition risk EC notifications in HFTD/HFRA locations over the 2-year period (2023 to 2024), from 151.1 risk units—as of January 1, 2023—by 102.7 risk units (68 percent). | This initiative is focused on closing out open E maintenance tags for distribution facilities in HFTD and HFRA areas. | Grid Design, Operations and Maintenance | 8.1 | Open Work Orders - Distribution |  | 8.1.7.2 | GM-03 | PGE_Grid Design, Operations and Maintenance_Open Work Orders - Distribution_GM-03_2024 | 531 | Equipment ignition likelihood | No | # of Distribution EC Tags | 64000 | 10012 | 29272 | 53432 | 64000 | 14116 | 37258 | 63711 | 96141 |  | As of Q1 2024, this work is on-track with: (1) 58% interim backlog ignition risk reduction, exceeding the interim target of 51%. Due to the lag time of closing additional distribution EC notifications counting in 2023, we can now report 53.8% of backlog ignition risk reduced in 2023 (an increase from the 52.2% we reported in our Q4 2023 QDR), with an additional 4.2% of backlog ignition risk reduced in Q1 2024, and a cumulative risk reduction of 58% towards our 68% 2024 target. (2) 7,754 distribution backlog ignition risk units completed, exceeding the interim target of 7,196 distribution backlog ignition risk unit completions. (3) 12,496 HFTD/HFRA units completed, exceeding interim target of 10,012 HFTD/HFRA unit completions. | As of Q2 2024, this work is on-track with: (1) 64.8% interim backlog ignition risk reduction, exceeding the interim target of 57.1%. Due to the lag time of closing additional distribution EC notifications counting in 2023, we can now report 53.8% of backlog ignition risk reduced in 2023 (an increase from the 52.2% we reported in our Q4 2023 QDR), with an additional 11.0% of backlog ignition risk reduced through Q2 2024, and a cumulative risk reduction of 64.8% towards our 68.0% 2024 target. (2) 22,493 distribution backlog ignition risk units completed, exceeding the interim target of 21,039 distribution backlog ignition risk unit completions. (3) 37,258 HFTD/HFRA units completed, exceeding interim target of 29,272 HFTD/HFRA unit completions. Please note that the Q1 progress has been updated from 12496 to 14116. | Q3 Progress: As of Q3 2024, this work is on-track with: (1) 71.7% interim backlog ignition risk reduction, exceeding the interim target of 64.7%. Due to the lag time of closing additional distribution EC notifications counting in 2023, we can now report 53.9% of backlog ignition risk reduced in 2023 (an increase from the 52.2% we reported in our Q4 2023 QDR), with an additional 17.8% of backlog ignition risk reduced through Q3 2024, and a cumulative risk reduction of 71.8% towards our 68.0% 2024 target. We have exceeded the 2024 year-end target for backlog ignition risk reduction percentage. (2) 38,063 distribution backlog ignition risk units closed, exceeding the interim target of 37,234 distribution backlog ignition risk unit closures. (3) 63,711 HFTD/HFRA units closed, exceeding interim target of 53,432 HFTD/HFRA unit closures. We have changed our year-end target for this metric, forecasting to close 84,000 HFTD/HFRA EC notifications, which is a change from the target at the beginning of the year of 64,000 HFTD/HFRA EC notification closures. This change is to align with the year-end forecast of HFTD/HFRA EC notification creation and maintain 25,000 more HFTD/HFRA EC closures than HFTD/HFRA EC creations. | As of Q4 2024, this work is complete with: (1) 73.4% backlog ignition risk reduction, exceeding the target of 68.0%. We have exceeded the 2024 year-end target for backlog ignition risk reduction percentage. (2) 53,526 distribution backlog ignition risk units closed, exceeding the target of 46,000 distribution backlog ignition risk unit closures. (3) 96,141 HFTD/HFRA units closed, exceeding the target of 94,456 HFTD/HFRA unit closures. The target of 94,456 unit closures for total HFTD/HFRA volume is attributed to closing out 25,000 more HFTD/HFRA tags than are created in 2024. In 2024, there were 69,456 HFTD/HFRA tags created. | Completed
PGE | 2025-02-03 | Program |  |  | EPSS - Down Conductor Detection (DCD) | Make capable for Down Conductor Detection (DCD) 400 protective device controllers or relays that protect distribution primary overhead conductor that travels through EPSS buffer areas and HFRA, barring External Factors. This count includes protection devices that due to repair status cannot receive the DCD settings, and circuit reconfiguration resulting in descoping of device. | This initiative will make capable for Down Conductor Detection (DCD) 500 protective device controllers or relays to reduce the risk of potential wildfire ignition. | Grid Design, Operations and Maintenance | 8.1 | Downed Conductor Detection (DCD) Devices |  | 8.1.2.10.1 | GM-06 | PGE_Grid Design, Operations and Maintenance_Downed Conductor Detection (DCD) Devices_GM-06_2024 | 455 | Equipment ignition likelihood | No | # of Protective Device Controllers or Relays that are DCD capable | 400 | 48 | 172 | 328 | 400 | 85 | 225 | 476 | 705 |  |  |  |  | Please note that Q2 units have been updated to 225 from 228, and the Q3 units to 476 from 484. | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-02-15 | Updates on EPSS Reliability Study | Provide annually an updated EPSS reliability impact study per ACI 22-32 | This initiative provides updates on the EPSS reliability study. | Grid Design, Operations and Maintenance | 8.1 | EPSS Settings |  | 8.1.8.1.1 | GM-07 | PGE_Grid Design, Operations and Maintenance_EPSS Settings_GM-07_2024 | 561 | Equipment ignition likelihood | No | [10 empty] | Provide annually an updated EPSS reliability impact study per ACI 22-32 | PG&E provided an updated Enhanced Powerline Safety Settings (EPSS) reliability impact study per Area for Continued Improvement (ACI) PG&E-22-32 to Energy Safety on February 15, 2024. This Objective is complete for 2024. | This objective was completed in Q1 | This objective was completed in Q1 | This commitment was completed in Q1. | Completed
PGE | 2025-02-03 | Program |  |  | Asset Inspection – Quality Control | Perform system inspection QC audits and achieve the associated quality pass rates for each asset inspection program as specified below: System Inspection Transmission – HFTD (Desktop): 15,000 audit locations*; 92 percent pass rate System Inspection Transmission – HFTD (Field): 1,300 audit locations*; 92 percent pass rate System Inspection Distribution – HFTD (Desktop): 140,000 audit locations*; 88 percent pass rate System Inspection Distribution – HFTD (Field): 30,000 audit locations*; 88 percent pass rate Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | This initiative will perform system inspection QA audits on QC completed locations and achieve the associated quality pass rates for each asset inspection program, to gain insight to improve asset inspection work on the field. | Grid Design, Operations and Maintenance | 8.1 | Quality Control (QC) |  | 8.1.6.1 | GM-09 | PGE_Grid Design, Operations and Maintenance_Quality Control (QC)_GM-09_2024 | 525 | Equipment ignition likelihood | No | % Pass Rate Audit Locations | System Inspection Transmission – HFTD: 16,300 audit locations*; 92 percent pass rate System Inspection Distribution – HFTD: 170,000 audit locations*; 88 percent pass rate *Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95 percent confidence level (CL) and 5 percent margin of error. | 90% | 90% | 90% | 90% | 93% | 99.58 | 99.8 | 99.89 |  | QC System Inspection Transmission Quarter: January – March (01/01/2024 – 03/30/2024): Pass Rate -> 100.0% Total # of Locations Audited -> 913 Total # of Locations Passed -> 913 Total # of Locations Failed -> 0 Year to Date (01/01/24 – 03/30/2024): Pass Rate -> 100.0% Total # of Locations Audited -> 913 Total # of Locations Passed -> 913 Total # of Locations Failed -> 0 QC System Inspection Distribution Quarter: January – March (01/01/2024 – 03/30/2024): Pass Rate -> 93.0% Total # of Locations Audited -> 43 Total # of Locations Passed -> 40 Total # of Locations Failed -> 3 Year to Date (01/01/24 – 03/30/2024): Pass Rate -> 93.0% Total # of Locations Audited -> 43 Total # of Locations Passed -> 40 Total # of Locations Failed -> 3 This Target's Change Order request was approved, and as such we have updated the Annual Target and Quarterly projected values. | QC System Inspection Transmission Quarter Q2: Pass Rate -> 99.96% Total # of Locations Audited -> 18321 Total # of Locations Passed -> 18314 Total # of Locations Failed -> 7 Year to Date (Q1 + Q2): Pass Rate -> 99.96% Total # of Locations Audited -> 19234 Total # of Locations Passed -> 19227 Total # of Locations Failed -> 7 QC System Inspection Distribution Quarter 2: Pass Rate -> 99.78% Total # of Locations Audited -> 62493 Total # of Locations Passed -> 62357 Total # of Locations Failed -> 136 Year to Date (Q1 + Q2): Pass Rate -> 99.78% Total # of Locations Audited -> 62536 Total # of Locations Passed -> 62397 Total # of Locations Failed -> 139 | QC System Inspection Transmission Quarter 3: Pass Rate -> 99.75% Total # of Locations Audited -> 1,989 Total # of Locations Passed -> 1,984 Total # of Locations Failed -> 5 Year to Date (Q1 - Q3): Pass Rate -> 99.95% Total # of Locations Audited -> 23,022 Total # of Locations Passed -> 23,010 Total # of Locations Failed -> 12 QC System Inspection Distribution Quarter 3: Pass Rate -> 99.83% Total # of Locations Audited -> 63,548 Total # of Locations Passed -> 63,438 Total # of Locations Failed -> 110 Year to Date (Q1 - Q3): Pass Rate -> 99.82% Total # of Locations Audited -> 139,236 Total # of Locations Passed -> 138,982 Total # of Locations Failed -> 254 | QC System Inspection Transmission Quarter 4: Pass Rate -> 99.75% Total # of Locations Audited -> 1989 Total # of Locations Passed -> 1984 Total # of Locations Failed -> 5 Year to Date (Q1 - Q4): Pass Rate -> 99.95% Total # of Locations Audited -> 23012 Total # of Locations Passed -> 23000 Total # of Locations Failed -> 12 QC System Inspection Distribution Quarter 4: Pass Rate -> 99.88% Total # of Locations Audited -> 36564 Total # of Locations Passed -> 36520 Total # of Locations Failed -> 44 Year to Date (Q1 - Q4): Pass Rate -> 99.83% Total # of Locations Audited -> 175376 Total # of Locations Passed -> 175084 Total # of Locations Failed -> 292 | Completed
PGE | 2025-02-03 | Program |  |  | Provide portable batteries to PG&E customers | Provide 4,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS | This initiative will provide new or replacement portable batteries to PG&E customers to assist them during emergency events, including wildfires. | Public Safety Power Shutoff | 8.5 | Customer Support in Wildfire and PSPS Emergencies |  | 8.5.3 | PS-06 | PGE_Public Safety Power Shutoff_Customer Support in Wildfire and PSPS Emergencies_PS-06_2024 | 892 | PSPS likelihood | No | # of batteries | 4000 | 65 | 410 | 1975 | 4000 | 681 | 1414 | 3069 | 4376 |  | PG&E has decided that it is important to our customers to continue including permanent batteries for this target, despite having this Change Order request rejected on procedural grounds. We will leverage the opportunity that Energy Safety provided to explain our deviation from the Change Order decision during the compliance process. Staying the course and providing permanent batteries is a better solution for our customers. In addition, there is no risk involved to our system or our customers by providing both portable and permanent batteries. For future QDR submissions, we will include the number of portable and number of permanent batteries we provided to customers within the comments section of this table for full transparency. | Please note the Q1 value has been updated from 682 to 678 and all the reported numbers for Q1 and Q2 are portable only. As stated in Q1 comments we are also providing the permanent batteries count. We have installed 278 permanent batteries in Q2 with a YTD count of 304 permanent batteries. These are in addition to the portable batteries installed. | Please note the Q1 value has been updated to 681 from 678, Q2 to 1,413 from 1,343 and all the reported numbers are portable only. As stated in Q1 and Q2 comments we are also providing the permanent batteries count. We have installed 350 permanent batteries in Q3 with a YTD count of 654 permanent batteries. These are in addition to the portable batteries installed. | Please note the Q2 value has been updated to 1,414 from 1,413, and the Q3 value to 3,069 from 3,062. Additionally, we installed a total of 1,051 permanent batteries in 2024. These permanent batteries are in addition to the 4,376 portable batteries installed. | Completed
PGE | 2025-02-03 | Program |  |  | PSPS Customer Impact Reduction | 18,000 customer events based on Wildfire mitigation projects including but not limited to MSO replacements and Undergrounded miles planned for 2024. | This initiative will focus on the reduction of customer events based on Wildfire mitigation projects and help improve PG&E's response to wildfires. | Public Safety Power Shutoff | 9.1 | Performance Metrics Identified by the Electrical Corporation |  | 9.1.5 | PS-07 | PGE_Public Safety Power Shutoff_Performance Metrics Identified by the Electrical Corporation_PS-07_2024 | 906 | PSPS likelihood | No | # of Customer events | 9980 | 527 | 1932 | 3932 | 9980 | 599 | 2526 | 4933 | 10529 |  | This target's Change Order request was approved, and as such we have updated the annual target and quarterly projected values. |  |  |  | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-12-31 | Pilot using drones for PSPS restoration | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. | This initiative is a pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. | Public Safety Power Shutoff | 9.1 | PSPS Restoration Pilot |  | 9.1.2 | PS-11 | PGE_Public Safety Power Shutoff_PSPS Restoration Pilot_PS-11_2024 | 906 | PSPS likelihood | No | [10 empty] | Pilot using drones for PSPS restoration and/or damage assessment to improve PSPS outage restoration time. | This work remains on track. In Q1, Unmanned Aircraft Systems (UAS) Operations documented 2023 PSPS UAS Patrols processes which include lessons learned for both PSPS exercises and live missions. Unmanned Aerial Vehicles (UAV) Patrols were determined to be especially beneficial during weather events with low visibility, as helicopters are unable to fly. UAS continues to participate and document the use of UAV during PSPS events. | This work remains on track. In Q2, Unmanned Aircraft Systems (UAS) Operations started PSPS exercises in June 2024 as part of our goal of continuing to run PSPS UAS exercises and begin documentation for 2024 findings. | This work remains on track. As of the end of Q3, Unmanned Aircraft Systems (UAS) have not been called out for any PSPS events in 2024. | PG&E has completed the objective to evaluate whether drones can be used to support PSPS restoration efforts. This involved running a pilot with the use of drones for PSPS patrol and damage assessment. The findings were presented in PG&E’s WRGSC on November 14, 2024. UAV Patrols demonstrated significant benefits, including reduced risk to personnel compared to ground patrols and minimal environmental impact compared to helicopter use. | Completed
PGE | 2025-02-03 | Program |  |  | Line Sensor - Installations | Install Line Sensor devices on 40 circuits feeding into HFTD areas or HFRA locations. | This initiative will help PG&E continuously measure current in real time and report events as they occur. | Situational Awareness and Forecasting | 8.3 | Grid Monitoring Systems, Existing Systems, Technologies, and Procedures |  | 8.3.3.1 | SA-02 | PGE_Situational Awareness and Forecasting_Grid Monitoring Systems, Existing Systems, Technologies, and Procedures_SA-02_2024 | 739 | Equipment ignition likelihood | No | # of circuits | 40 | 0 | 0 | 30 | 40 | 0 | 12 | 45 | 45 | [5 empty] | Completed
PGE | 2025-02-03 | Program |  |  | Distribution Fault Anticipation (DFA) Installations | Install 15 Distribution Fault Anticipation (DFA) sensors on circuits. One sensor will be installed per circuit at the initiating substation. | This initiative will install Distribution Fault Anticipation (DFA) sensors on circuits to allow better detection and assistance in locating faults, abnormal power flow events, and categorization of events. | Situational Awareness and Forecasting | 8.3 | Grid Monitoring Systems, Planned Improvements |  | 8.3.3.3 | SA-10 | PGE_Situational Awareness and Forecasting_Grid Monitoring Systems, Planned Improvements _SA-10_2024 | 739 | Equipment ignition likelihood | No | DFA Sensors | 15 | 0 | 0 | 5 | 15 | 1 | 9 | 12 | 17 | [5 empty] | Completed
PGE | 2025-02-03 | Program |  |  | Early Fault Detection (EFD) Installations | Install Early Fault Detection (EFD) sensors on 2 circuits. | This initiative will install Early Fault Detection (EFD) sensors on circuits to detect failing equipment early and detect vegetation encroachment. | Situational Awareness and Forecasting | 8.3 | Grid Monitoring Systems, Planned Improvements |  | 8.3.3.3 | SA-11 | PGE_Situational Awareness and Forecasting_Grid Monitoring Systems, Planned Improvements _SA-11_2024 | 739 | Equipment ignition likelihood | No | EFD circuits | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 2 | [5 empty] | Completed
PGE | 2025-02-03 | Program |  |  | LiDAR Data Collection - Transmission | Complete LiDAR inspection of the Transmission System (17,500 circuit miles) of transmission lines. The final LiDAR data will inform the Transmission ground patrols by identifying vegetation related risk. The Transmission System circuit miles include HFTD / HFRA Transmission circuit miles. | This initiative includes the collection of LiDAR data for the Transmission System which can reduce the potential for asset-caused ignitions and wildfires. | Vegetation Management and Inspection | 8.2 | Routine Transmission NERC and Non-NERC |  | 8.2.2.1.1 | VM-01 | PGE_Vegetation Management and Inspection_Routine Transmission NERC and Non-NERC_VM-01_2024 | 655 | Contact from vegetation ignition likelihood | Yes | # of circuit miles | 17500 | 12031 | 16000 | 17000 | 17500 | 13379 | 17989 | 17989 | 17989 |  | Please note that we revised this annual target from 17,500 inspection to 18,004 inspections to align with our updated asset registry numbers. This Target's Change Order request was approved, and as such we updated the quarterly target values. | Please note that we revised this annual target from 17,500 inspection to 18,004 inspections to align with our updated asset registry numbers. Please note that there is a 15-mile gap to target due to data resolution and accuracy differences inherent to ETGIS and LIDAR and that this target has now been completed. The Q1 progress has been updated from 12,090 to 13,379. | Please note that we revised this annual target from 17,500 inspection to 18,004 inspections to align with our updated asset registry numbers. Please note that there is a 15-mile gap to target due to data resolution and accuracy differences inherent to ETGIS and LIDAR and that this target was completed in Q2. | This commitment was completed in Q3. | Completed
PGE | 2025-02-03 | Program |  |  | Pole Clearing Program | 2024 pole count to be adjusted by the ending pole population in the previous year (2023) poles per Vegetation Control Standard TD-7112S will be inspected, cleared, and maintained where clearing is necessary. | This initiative performs pole clearing inspections and work (where needed) for poles in HFTD and HFRA areas where clearance is not required by PRC Section 4292. Pole clearing can reduce the potential for a wildfire ignition. | Vegetation Management and Inspection | 8.2 | Pole Clearing |  | 8.2.3.1 | VM-02 | PGE_Vegetation Management and Inspection_Pole Clearing_VM-02_2024 | 679 | Contact from vegetation ignition likelihood | Yes | # of distribution poles | 63000 | 31500 | 47250 | 63000 | 63000 | 65919 | 79578 | 79988 | 79988 |  | Please note that we revised this annual target from 63,000 structures inspected to 67,196 structures inspected to align with our ending 2023 pole inventory. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated Q1 target of 56,299 by completing 59,202 structures inspected. | Please note that we revised this annual target from 63,000 structures inspected to 67,196 structures inspected to align with our ending 2023 pole inventory. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated Q2 target of 47,250 by completing 77,682 but the program is still 'In Progress', since the program can add additional poles until end of September. Please note that the Q1 values included work completed in Q4 of 2023. | Please note that we revised this annual target from 63,000 structures inspected to 67,196 structures inspected to align with our ending 2023 pole inventory. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. We surpassed the updated target of 67,196 by completing 79,692 poles and the program is now complete. Please note that the Q1 values included work completed in Q4 of 2023. Please note that the Q1 value is updated to 63,185 from 59,202 and Q2 value to 76,365 from 77,682. | Please note that additional high risk poles, without non-exempt equipment, were added to pole clearing inventory in 2024. Please note that Q1 value has been updated to 65,919 from 63,185, Q2 to 79,578 from 76,365 and Q3 to 79,988 from 79,692. | Completed
PGE | 2025-02-03 | Program |  |  | Focused Tree Inspection Program | Within Areas of Concern (AOC) locations, complete 1,500 circuit miles of FTI inspection which includes performing a level 2 inspection on all potential strike trees | This initiative will identify the Areas of Concern (AOC) and implement guidelines to reduce the risk associated with vegetation contact that could cause a potential ignition. | Vegetation Management and Inspection | 8.2 | Focused Tree Inspections |  | 8.2.2.2.5 | VM-03 | PGE_Vegetation Management and Inspection_Focused Tree Inspections_VM-03_2024 | 673 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 1500 | 73 | 300 | 1050 | 1500 | 78 | 382.48 | 1255.47 | 1568.18 |  | This target's Change Order request was approved, and as such we updated the quarterly target values. | This initiative is on track with 386 miles inspected with 60.65 miles QC surveyed by end of Q2. PGE will complete QC survey on all the miles we inspect before end of the year. | This initiative is on track with 1255.47 miles inspected with 830.79 miles QC surveyed by end of Q3. PGE will complete QC survey on all the miles we inspect before end of the year. Please note that Q2 value has been updated to 382.48 from 386. |  | Completed
PGE | 2025-02-03 | Program |  |  | Tree Removal Inventory | Mitigate(c) 20,000 trees identified from the legacy EVM Program | This initiative will remove trees identified from the legacy EVM program to reduce the risk associated with vegetation contact causing a potential ignition. | Vegetation Management and Inspection | 8.2 | Fall-in Mitigation |  | 8.2.2.2.4 | VM-04 | PGE_Vegetation Management and Inspection_Fall-in Mitigation_VM-04_2024 | 672 | Contact from vegetation ignition likelihood | Yes | # of trees Removed | 20000 | 600 | 6200 | 14000 | 20000 | 8496 | 14633 | 18309 | 32480 |  | Please note that this target's Change Order request was rejected on procedural grounds, so we are listing the quarterly targets as they appear in our pre-Change Order/Base WMP submission. |  |  |  | Completed
PGE | 2025-02-03 | Program |  |  | Defensible Space Inspections - Distribution Substation | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 131 distribution substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around distribution substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | 8.2 | Substation Defensible Space |  | 8.2.2.3.1 | VM-05 | PGE_Vegetation Management and Inspection_Substation Defensible Space_VM-05_2024 | 675 | Wildfire exposure potential | Yes | # of Distribution Substations | 131 | 125 | 130 | 131 | 131 | 109 | 131 | 131 | 131 |  | Due to the Change Order decision rejecting the update to this target on procedural grounds, the Q1 Status has been revised to "Delayed" from "In Progress." | The program has surpassed the Q2 target of 130 by completing 131 by end of Q2 and completed the commitment for the year | This initiative was completed in Q2. | This commitment was completed in Q2. Please note that the 2024 targets for VM-05 (Distribution Substation) has been misstated as 55 instead of 131 on page 683 of our 2023-2025 WMP R7. | Completed
PGE | 2025-02-03 | Program |  |  | Defensible Space Inspections - Transmission Substation | Complete defensible space inspections in alignment with the guidelines set forth in LAND 4001P-01 at 55 transmission substations. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around transmission substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | 8.2 | Substation Defensible Space |  | 8.2.2.3.1 | VM-06 | PGE_Vegetation Management and Inspection_Substation Defensible Space_VM-06_2024 | 675 | Wildfire exposure potential | Yes | # of Transmission Substations | 55 | 37 | 55 | 55 | 55 | 48 | 54 | 54 | 54 |  | Please note that this target's Change Order request was rejected on procedural grounds, so we are listing the targets as they appear in our pre-Change Order/Base WMP submission. However, we note that we will only be able to complete inspections on 54 locations, not 55, because the ownership of the Belden PH substation was transferred to the Power Generation line of business. | All inspections for this initiative are complete. Please note that one of the 55 substations, the Belden Powerhouse, was transferred to Power Generation. This asset was, therefore, inspected as part of target VM-07. Inspections were completed for each of the remaining 54 substations as part of this initiative. Note we are listing the program as “Completed”, since we have completed all substation inspections for all active substations. | All inspections for this initiative are complete by end of Q2. Please note that one of the 55 substations, the Belden Powerhouse, was transferred to Power Generation. This asset was, therefore, inspected as part of target VM-07. Inspections were completed for each of the remaining 54 substations as part of this initiative. Note we are listing the program as “Completed”, since we have completed all substation inspections for all active substations. Please note that Q1 value has been updated to 48 from 47. | This commitment was completed in Q2. Please note that the 2024 targets for VM-06 (Transmission Substation) has been misstated as 131 instead of 55 on page 683 of our 2023-2025 WMP R7. | Completed
PGE | 2025-02-03 | Program |  |  | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | Complete defensible space inspections in alignment with the guidelines set forth in LAND 5201P-01 at 61 Hydroelectric Generation Substations and Powerhouses. Co-located Hydroelectric substations and Transmission & Distribution substations are counted separately as two distinct units. | This initiative clears defensible space areas around hydroelectric substations to minimize the potential for ignition spread outside of facilities and to provide improved structure defense capability for firefighting purposes. | Vegetation Management and Inspection | 8.2 | Substation Defensible Space |  | 8.2.2.3.1 | VM-07 | PGE_Vegetation Management and Inspection_Substation Defensible Space_VM-07_2024 | 675 | Wildfire exposure potential | Yes | # of Hydroelectric Substations and Powerhouses | 61 | 24 | 61 | 61 | 61 | 53 | 59 | 59 | 59 |  | Please note that this target's Change Order request was rejected on procedural grounds, so we are listing the targets as they appear in our pre-Change Order/Base WMP submission. However we note that we will only be able to complete inspections on 59 locations, not 61, because of the following changes (three subtractions and one addition): (1) the divestiture of Deer Creek PH and Tule River PH; (2) the ownership transfer of Hamilton Branch PH to substation distribution; (3) and the addition of Kilarc PH substation. | The inspections on 59 powerhouses are complete. The remaining two powerhouses have been divested and PG&E no longer owns them. Therefore, work on this initiative is complete. Note we are listing the program as “Completed”, since we have completed all substation inspections for all active substations. | The inspections on 59 powerhouses were complete by Q2. The remaining two powerhouses have been divested and PG&E no longer owns them. Therefore, work on this initiative is complete. Note we are listing the program as “Completed”, since we have completed all substation inspections for all active substations. | This commitment was completed in Q2. | Completed
PGE | 2025-02-03 | Program |  |  | Vegetation Management – Quality Verification | Perform vegetation management QA audits on QC completed locations and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 2,675 audit locations*; 95% pass rate Transmission VM – HFTD: 1,284 audit locations; 95% pass rate Vegetation Control Pole Clearing – HFTD: 1,926 audit locations*; 95% pass rate Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative performs Quality Assurance and Quality Verification audits and reviews of various aspects of our Vegetation Management program to identify gaps and areas of improvement. | Vegetation Management and Inspection | 8.2 | Quality Assurance and Quality Control |  | 8.2.5 | VM-08 | PGE_Vegetation Management and Inspection_Quality Assurance and Quality Control_VM-08_2024 | 693 | Contact from vegetation ignition likelihood | No | # of Audit Locations % Pass Rate | 95% | 95% | 95% | 95% | 95% | 99.8% | 99.91% | 99.9% | 99.92% |  | QA Vegetation Management Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Q1: Pass Rate -> 99.89% Location Inspected- 620 Total # of Audit Trees Inspected - 941 Total # of Audit Trees Passed -940 Total # of Audit Trees Failed -1 QA Pole Clearing Pass Rate: Total # of Poles Passed / Total # of Poles Audited Q1: Pass Rate -> 99.80% Total # of Poles Audited -> 983 Total # of Poles Passed -> 981 Total # of Poles Failed -> 2 | QA Vegetation Management Distribution: Quarter 2: Pass Rate -> 99.93% Location Inspected - 1423 Total # of Audit Trees Inspected - 5862 Total # of Audit Trees Passed - 5858 Total # of Audit Trees Failed – 4 YTD: Pass Rate -> 99.91% Location Inspected -> 2368 Total # of Audit Trees Inspected - 8931 Total # of Audit Trees Passed - 8923 Total # of Audit Trees Failed - 8 QA Vegetation Management Transmission: Quarter 2: Pass Rate -> 100% Location Inspected - 1293 Total # of Audit Trees Inspected - 2110 Total # of Audit Trees Passed - 2110 Total # of Audit Trees Failed – 0 YTD: Pass Rate -> 100.00% Location Inspected - 1295 Total # of Audit Trees Inspected - 2112 Total # of Audit Trees Passed - 2112 Total # of Audit Trees Failed – 0 QA Pole Clearing: Quarter 2: Pass Rate -> 99.79% Total # of Poles Audited - 962 Total # of Poles Passed - 960 Total # of Poles Failed – 2 YTD: Pass Rate -> 99.82% Total # of Poles Audited - 2260 Total # of Poles Passed - 2256 Total # of Poles Failed - 4 Please note the updated Q1 Values: QA Vegetation Management Distribution: Quarter 1: Pass Rate -> 99.87% Location Inspected - 945 Total # of Audit Trees Inspected - 3069 Total # of Audit Trees Passed - 3065 Total # of Audit Trees Failed - 4 QA Vegetation Management Transmission: Pass Rate -> 100% Location Inspected - 02 Total # of Audit Trees Inspected - 02 Total # of Audit Trees Passed - 02 Total # of Audit Trees Failed - 0 QA Pole Clearing: Pass Rate: Pass Rate -> 99.85% Total # of Poles Audited - 1298 Total # of Poles Passed - 1296 Total # of Poles Failed - 2 | QA Vegetation Management Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 99.95% Location Inspected - 1558 Total # of Audit Trees Inspected - 7596 Total # of Audit Trees Passed - 7592 Total # of Audit Trees Failed - 4 YTD: Pass Rate -> 99.93% Location Inspected -> 3,926 Total # of Audit Trees Inspected - 16,527 Total # of Audit Trees Passed - 16,515 Total # of Audit Trees Failed - 12 QA Vegetation Management Transmission Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 99.95% Location Inspected - 886 Total # of Audit Trees Inspected - 2,140 Total # of Audit Trees Passed - 2,139 Total # of Audit Trees Failed - 1 YTD: Pass Rate -> 99.98% Location Inspected - 2,176 Total # of Audit Trees Inspected - 4,242 Total # of Audit Trees Passed - 4,241 Total # of Audit Trees Failed - 1 QA Pole Clearing Pass Rate: Total # of Poles Passed / Total # of Poles Audited Quarter 3: Pass Rate -> 100.00% Total # of Poles Audited - 785 Total # of Poles Passed - 785 Total # of Poles Failed - 0 YTD: Pass Rate -> 99.87% Total # of Poles Audited - 3,045 Total # of Poles Passed - 3,041 Total # of Poles Failed - 4 | QA Vegetation Management Distribution Q4: Pass Rate -> 99.94% Location Inspected - 1340 Total # of Audit Trees Inspected - 6614 Total # of Audit Trees Passed - 6610 Total # of Audit Trees Failed - 4 YTD: Pass Rate -> 99.95% Location Inspected -> 4477 Total # of Audit Trees Inspected - 18513 Total # of Audit Trees Passed - 18504 Total # of Audit Trees Failed - 09 QA Vegetation Management Transmission Q4: Pass Rate -> 99.88% Location Inspected - 573 Total # of Audit Trees Inspected - 1733 Total # of Audit Trees Passed - 1731 Total # of Audit Trees Failed - 2 YTD: Pass Rate -> 99.95% Location Inspected - 2728 Total # of Audit Trees Inspected - 5949 Total # of Audit Trees Passed - 5946 Total # of Audit Trees Failed - 3 QA VC Pole Clearing Q4: Pass Rate -> 99.76% Total # of Poles Audited - 421 Total # of Poles Passed - 420 Total # of Poles Failed - 1 YTD: Pass Rate -> 99.86% Total # of Poles Audited - 3466 Total # of Poles Passed - 3461 Total # of Poles Failed - 5 | Completed
PGE | 2025-02-03 | Program |  |  | Routine Ground - Transmission | Complete Routine Transmission Ground Inspection of 17,740 circuit miles as defined by Transmissions Routine LiDAR detection point data systemwide. | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | 8.2 | Routine Transmission – Ground |  | 8.2.2.1.1 | VM-13 | PGE_Vegetation Management and Inspection_Routine Transmission – Ground_VM-13_2024 | 655 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 17740 | 2250 | 9000 | 16000 | 17740 | 7620 | 13738 | 17009 | 17954 |  | This target's Change Order request was approved, and as such we updated the quarterly target values. |  |  | Please note that the completed circuit miles include constraint miles. | Completed
PGE | 2025-02-03 | Program |  |  | Transmission Second Patrol | Complete Transmission Second Patrol Inspection of 5,625 circuit miles dependent on remote sensing (ORTHO Imagery). | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | 8.2 | Transmission Second Patrol |  | 8.2.2.1.2 | VM-14 | PGE_Vegetation Management and Inspection_Transmission Second Patrol_VM-14_2024 | 658 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 5625 | 0 | 0 | 0 | 5625 | 0 | 0 | 5197 | 5848 |  | Please note that we revised this annual target from 5,625 circuit miles to 5,697 circuit miles to align with our most recent inspection data. Given the restrictive criteria in the WMP Guidelines, we were not able to include this as part of our 2024 Change Order and are, therefore, describing this change here. The updated target for Q1 is 0 and this work remains on track as it is scheduled to begin in Q4. | Program to start in Q4. | We were able to start the program in July and were able to complete 5,197 inspections in Q3. | Please note that the completed circuit miles include constraint miles. | Completed
PGE | 2025-02-03 | Program |  |  | Integrated Vegetation Management - Transmission | Complete Integrated Vegetation Management and Fee Inspections of 6,504 acres ROW across the Transmission systemwide | This initiative will identify vegetation contact that could cause a potential ignition around Transmission equipment and aid in prescribing any needed vegetation mitigation work | Vegetation Management and Inspection | 8.2 | Integrated Vegetation Management |  | 8.2.2.1.3 | VM-15 | PGE_Vegetation Management and Inspection_Integrated Vegetation Management_VM-15_2024 | 660 | Contact from vegetation ignition likelihood | Yes | Acres | 6504 | 0 | 2590 | 5690 | 6504 | 1785.51 | 5801.63 | 7822.59 | 7907 |  |  | Q1 progress is updated from 0 to 1785.51 due to internal quality review. |  |  | Completed
PGE | 2025-02-03 | Program |  |  | Distribution Routine Patrol | Complete Distribution Routine Annual Patrol Inspection of 78,650 overhead circuit miles system wide | This initiative will identify vegetation contact that could cause a potential ignition around Distribution equipment and aid in prescribing any needed vegetation mitigation work. | Vegetation Management and Inspection | 8.2 | Distribution Routine Patrol |  | 8.2.2.2.1 | VM-16 | PGE_Vegetation Management and Inspection_Distribution Routine Patrol_VM-16_2024 | 664 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 78650 | 14459 | 31460 | 51123 | 78650 | 26126.7 | 48966.3 | 70311.32 | 78307.75 |  | This target's Change Order request was approved, and as such we updated the quarterly target values. |  |  | Please note that the target for this commitment was set using ED GIS Data, however the attainment value was based on VM system of record which is not fully aligned with ED GIS Data. We are considering this target as complete due to all inspections being met per VM system of record. | Completed
PGE | 2025-02-03 | Program |  |  | Distribution Second Patrol | Complete Distribution Second Patrol Inspection of 25,685 circuit miles in HFTD and HFRA locations. | This initiative will identify vegetation contact that could cause a potential ignition around Distribution equipment and aid in prescribing any needed vegetation mitigation work | Vegetation Management and Inspection | 8.2 | Distribution Second Patrol |  | 8.2.2.2.2 | VM-17 | PGE_Vegetation Management and Inspection_Distribution Second Patrol_VM-17_2024 | 667 | Contact from vegetation ignition likelihood | Yes | Circuit Miles | 25685 | 4841 | 10274 | 16695 | 25685 | 7952.35 | 13241 | 21296.8 | 27259.79 |  | This target's Change Order request was approved, and as such we updated the quarterly target values. |  |  |  | Completed
PGE | 2025-02-03 | Program |  |  | VM for Operational Mitigations (VMOM) | Mitigate 6,500 trees for VM for Operational Mitigations program, on EPSS capable circuits. This target will include the previous year’s carry-over work and prescriptions resulting from pro-active patrols on EPSS circuits. Future workplans will be dependent on previous year’s EPSS outage data analysis. | This initiative will mitigate trees under the VM for Operational Mitigations program, on EPSS capable circuits. | Vegetation Management and Inspection | 8.2 | Mitigations of trees on EPSS capable circuits |  | 8.2.2.2.3 | VM-18 | PGE_Vegetation Management and Inspection_Mitigations of trees on EPSS capable circuits_VM-18_2024 | 670 | Contact from vegetation ignition likelihood | Yes | Trees | 6500 | 1000 | 3000 | 5000 | 6500 | 1488.5 | 4256 | 5121 | 6937 |  | Please note that we revised the Q2 and Q3 targets for this initiative to align with our most recent inspection data. However, we did not change the annual target or the Q1 and Q4 targets for this work. |  |  |  | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-01-31 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | This initiative will enhance the One VM application for routine, and second patrol to include capability to capture factors for prescribing trees for removal. | Vegetation Management and Inspection | 8.2 | One VM Application Record Keeping Enhancement (Routine, Second Patrol) |  | 8.2.4 | VM-19 | PGE_Vegetation Management and Inspection_One VM Application Record Keeping Enhancement (Routine, Second Patrol)_VM-19_2024 | 691 | Contact from vegetation ignition likelihood | No | [10 empty] | Enhance the One VM application for Routine, and Second Patrol to include capability to capture factors for prescribing trees for removal. | The tasks scheduled for Q1: "Monitor and Track" and "Publish Bulletin TD-7102P-01-B036 and 5MM email" were both completed in January on time. The objective has been completed. | This commitment was completed in Q1. | This commitment was completed in Q1. | This commitment was completed in Q1. | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-11-15 | Record Keeping Enhancement (VMOM, TRI) | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 and Tree Removal Inventory (TRI) | This initiative will enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 and Tree Removal Inventory (TRI). | Vegetation Management and Inspection | 8.2 | VMOM and TRI Record Keeping |  | 8.2.4 | VM-20 | PGE_Vegetation Management and Inspection_VMOM and TRI Record Keeping_VM-20_2024 | 691 | Contact from vegetation ignition likelihood | No | [10 empty] | Enhance the application for the Vegetation Management for Operational Mitigations (VMOM) - VMPI2 and Tree Removal Inventory (TRI) | The tasks scheduled for Q1: "Deployment" and "Monitor and Track" were both timely completed in January. This objective remains on track for completion in 2024. Please note that, since this objective was written, the timeline of programs to be onboarded onto the One VM platform has been expedited, and by the time this objective is due, both the VMOM and TRI programs will be integrated into the One VM platform, and no longer utilizing VMPI2 or Field Maps. The One VM application already captures factors for prescribing trees for removal so the objective intent will still be met and consolidating this data in the One VM platform will improve data governance. | This work remains on track for completion in 2024. For TRI/Field Maps, the schema was approved. The next milestone for TRI/Field Maps will be rollout, which we hope to accomplish in Q3. For VMOM Additional Drop downs deployed per guidance of VASA and COA EDRS 2024-13425, this work was completed and deployed with the June 27, 2024 release. | In Q3, this initiative successfully completed the enhancements to the One VM system of record for the Vegetation Management for Operational Mitigation (VMOM) to make capability to capture factors for prescribing trees for removal. In Q3, Field Maps were enhanced to include a reason for removal field for TRI. | This commitment was completed in Q3. | Completed
PGE | 2025-02-03 | Project | 2024-01-01 | 2024-03-31 | FTI Record Keeping Enhancement | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. | This initiative will enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. | Vegetation Management and Inspection | 8.2 | Focused Tree Inspections Record Keeping |  | 8.2.2.2.5 | VM-21 | PGE_Vegetation Management and Inspection_Focused Tree Inspections Record Keeping_VM-21_2024 | 673 | Contact from vegetation ignition likelihood | No | [10 empty] | Enhance record keeping practices for the Focused Tree Inspection program (FTI) by creating records of all potential strike trees inspected using a digitized Tree Risk Assessment form. | All tasks were completed in Q1: "Sprint-4 (Dev + In-Sprint Testing), Sprint-4 Demo, Review, Retro - Code Merge to Code Merge to New Integration SB, Sprint-4 Integration Testing, Code Movement to SAFEUAT, UAT, Prod Go-Live, TRAQ Digitized Form Go-Live, Hypercare Support, One VM TRAQ Skill Permissions Job Aid. The objective has been completed. | This initiative was completed in Q1. | This initiative was completed in Q1. | This commitment was completed in Q1. | Completed
PGE | 2025-02-03 | Program |  |  | Vegetation Management - Quality Control | Perform vegetation management QC audits and achieve the associated quality pass rates for each vegetation management program as specified below: Distribution Routine VM – HFTD: 80,000 audit locations*; 88% pass rate Transmission VM – HFTD: 13,500 audit locations*; 92% pass rate Vegetation Control Pole Clearing – HFTD: 11,500 audit locations*; 88% pass rate Audit locations are subject to change and dependent on completed execution work and constraints. The number of audit locations will be identified using a statistically valid approach with a 95% confidence level (CL) and 5% margin of error. | This initiative performs Quality Control and Quality Verification audits and reviews of various aspects of our Vegetation Management program to identify gaps and areas of improvement. | Vegetation Management and Inspection | 8.2 | Quality Control |  | 8.2.5.2 | VM-22 | PGE_Vegetation Management and Inspection_Quality Control_VM-22_2024 | 698 | Contact from vegetation ignition likelihood | No | % Pass Rate (# of Audit Locations) | 88% | 88% | 88% | 88% | 88% | 97.55% | 93.46% | 94.37% | 94.92% |  | QC Routine Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Q1: Pass Rate -> 96.4% Total # of Locations Audited -> 3384 Total # of Trees Audited -> 16665 Total # of Trees Passed -> 16073 Total # of Trees Failed -> 592 QC Vegetation Management Transmission Pass Rate: Total # of Trees Passed / Total # of Trees Audited Q1: Pass Rate -> 98.7% Total # of Locations Audited -> 140 Total # of Trees Audited -> 157 Total # of Trees Passed -> 155 Total # of Trees Failed -> 2 | QC Vegetation Management Distribution: Quarter 2: Pass Rate 96.64% Location Inspected – 33,713 Total # of Audit Trees Inspected – 122,624 Total # of Audit Trees Passed – 118,499 Total # of Audit Trees Failed – 4,125 YTD: Pass Rate: 96.60% Location Inspected – 39,531 Total # of Audit Trees Inspected – 155,062 Total # of Audit Trees Passed – 149,796 Total # of Audit Trees Failed – 5,266 QC Vegetation Management Transmission: Quarter 2: Pass Rate 98.62% Location Inspected - 4,696 Total # of Audit Trees Inspected - 7,947 Total # of Audit Trees Passed - 7,837 Total # of Audit Trees Failed – 110 YTD: Pass Rate -> 98.62% Location Inspected - 4,861 Total # of Audit Trees Inspected - 8,159 Total # of Audit Trees Passed - 8,046 Total # of Audit Trees Failed – 113 QC Pole Clearing: Quarter 2: Pass Rate 81.44% Total # of Poles Audited - 6,794 Total # of Poles Passed - 5,533 Total # of Poles Failed – 1,261 YTD: Pass Rate 85.18% Total # of Poles Audited - 14,145 Total # of Poles Passed - 12,049 Total # of Poles Failed – 2,096 Please note the updated Q1 Values: QC Vegetation Management Distribution: Quarter 1: Pass Rate - 96.48% Location Inspected – 5,818 Total # of Audit Trees Inspected – 32,438 Total # of Audit Trees Passed – 31,297 Total # of Audit Trees Failed – 1,141 QC Vegetation Management Transmission: Quarter 1: Pass Rate -> 98.58% Location Inspected - 165 Total # of Audit Trees Inspected - 212 Total # of Audit Trees Passed - 209 Total # of Audit Trees Failed – 3 QC Pole Clearing: Pass Rate 88.64% Total # of Poles Audited - 7,351 Total # of Poles Passed - 6,516 Total # of Poles Failed – 835 | QC Vegetation Management Distribution Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 97.59% Location Inspected – 35,081 Total # of Audit Trees Inspected – 163,750 Total # of Audit Trees Passed – 159,806 Total # of Audit Trees Failed – 3,944 YTD: Pass Rate: 97.11% Location Inspected – 74,612 Total # of Audit Trees Inspected – 318,812 Total # of Audit Trees Passed – 309,602 Total # of Audit Trees Failed – 9,210 QC Vegetation Management Transmission Pass Rate: Total # of Trees Passed / Total # of Trees Audited Quarter 3: Pass Rate -> 99.12% Location Inspected – 6661 Total # of Audit Trees Inspected – 14,047 Total # of Audit Trees Passed – 13,923 Total # of Audit Trees Failed - 124 YTD: Pass Rate -> 98.95% Location Inspected – 11,498 Total # of Audit Trees Inspected -22,146 Total # of Audit Trees Passed – 21,913 Total # of Audit Trees Failed - 233 QC Pole Clearing Pass Rate: Total # of Poles Passed / Total # of Poles Audited Quarter 3: Pass Rate – 92.21% Total # of Poles Audited – 5107 Total # of Poles Passed – 4709 Total # of Poles Failed – 398 YTD: Pass Rate – 87.05% Total # of Poles Audited – 19,252 Total # of Poles Passed – 16,758 Total # of Poles Failed – 2,494 | QC Vegetation Management Distribution Q4: Pass Rate -> 98.68% Location Inspected – 9,888 Total # of Audit Trees Inspected – 52,617 Total # of Audit Trees Passed – 51,921 Total # of Audit Trees Failed - 696 YTD: Pass Rate -> 97.38% Spans Audited -> 80,391 Total # of Trees Audited -> 343,470 Total # of Trees Passed -> 334,479 Total # of Trees Failed -> 8,991 QC Vegetation Management Transmission Q4: Pass Rate -> 99.31% Location Inspected –4,445 Total # of Audit Trees Inspected – 10,358 Total # of Audit Trees Passed – 10,287 Total # of Audit Trees Failed - 71 YTD: Pass Rate -> 99.08% Spans Audited -> 15,897 Total # of Trees Audited -> 32,444 Total # of Trees Passed -> 32,147 Total # of Trees Failed -> 297 QC Pole Clearing Q4: Pass Rate – 98.03% Total # of Poles Audited – 2,488 Total # of Poles Passed – 2,439 Total # of Poles Failed – 49 YTD: Pass Rate -> 88.30% Total # of Poles Audited -> 21,740 Total # of Poles Passed -> 19,197 Total # of Poles Failed -> 2,543 | Completed
Note on C2: Author: Select cells for dropdown list.

## Table 2
|  | Utility | PG&E | Notes:
|  | Table No. | 2 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
|  | Date Modified | 2025-02-18 | HWW = High wind warning
RFW = Red flag warning
[11 empty] | Actuals | Projected
|  | Table 2: Performance Metrics | [8 empty] | Q4
|  | Metric type | # | Metric name | Wind Warning Status | Program Name | HFTD Tier | Line Type | Inspection Type | Inspection Method | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x |  | 1. Risk Events | 1.a. | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 42 | 122.8 | 14 | 14 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 50 | 181.2 | 218 | 218 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 13.2 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1706 | 5780.6 | 5322 | 5322 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 72 | 180.6 | 9 | 9 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 53 | 143.8 | 109 | 109 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 7.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 846 | 3604.8 | 2610 | 2610 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 224 | 744.2 | 147 | 147 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 174 | 556.2 | 1297 | 1297 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 105.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | None | N/A | Non- HFTD | N/A | N/A | N/A | 8462 | 30172.4 | 38541 | 38541 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  | 1. Risk Events | 1.b. | Number of wires down | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1 | 12.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 20 | 52.4 | 83 | 83 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0.8 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 241 | 704.6 | 484 | 484 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 14 | 17.6 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 23 | 63.4 | 36 | 36 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 160 | 584.2 | 302 | 302 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 15 | 62.2 | 3 | 3 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 63 | 85.8 | 351 | 351 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 10.4 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of wires down | None | N/A | Non- HFTD | N/A | N/A | N/A | 598 | 2759.4 | 3890 | 3890 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  | 1. Risk Events | 1.c. | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 38 | 3 | 12 | 12 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 30 | 2 | 106 | 106 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 1393 | 3742 | 4486 | 4486 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 38 | 1 | 7 | 7 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 27 | 8 | 53 | 53 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 602 | 1597 | 1917 | 1917 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 197 | 35 | 129 | 129 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 108 | 7 | 1116 | 1116 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events not caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 7787 | 30820 | 33802 | 33802 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  | 1. Risk Events | 1.d. | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 4 | 3 | 2 | 2 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 20 | 2 | 35 | 35 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 313 | 613 | 906 | 906 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 34 | 1 | 2 | 2 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 26 | 5 | 30 | 30 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 244 | 650 | 708 | 708 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 27 | 35 | 19 | 19 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 66 | 7 | 839 | 839 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events caused by contact with vegetation | None | N/A | Non- HFTD | N/A | N/A | N/A | 675 | 2324 | 4101 | 4101 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  | 1. Risk Events | 1.e. | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 18 | 17.8105 | 10 | 10 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 2 | N/A | N/A | N/A | 298 | 817.3053 | 900 | 900 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 33 | 2.9684 | 5 | 5 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | HFTD Tier 3 | N/A | N/A | N/A | 102 | 271.1158 | 314 | 314 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 48 | 16.8211 | 12 | 12 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  |  |  | Number of outage events on circuits with adjusted settings for protective devices enabled. | All (regardless of RFW/HWW status) | N/A | Non- HFTD | N/A | N/A | N/A | 401 | 1223.9789 | 1130 | 1130 | Number of events | Projected values are based on a 2 year average for 2024 and 2025.
|  | 2. Time between vegetation inspection finding and resulting trimming activity | 2.d.2.a. | Median time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 1671.5 | 1700 | 1600 | 1500 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  |  | 2.d.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Distribution | N/A | N/A | 19479 | 4750 | 4650 | 4550 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  |  | 2.d.3.a. | Median time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 2027 | 1700 | 1600 | 1500 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  |  | 2.d.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Distribution | N/A | N/A | 15273 | 4750 | 4650 | 4550 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  |  | 2.d.4.a. | Median time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 566 | 1700 | 1600 | 1500 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  |  | 2.d.4.b. | 95 percentile time | N/A |  | Non- HFTD | Distribution | N/A | N/A | 15490 | 4750 | 4650 | 4550 | hours |  | To remain consistent, we are providing data from our legacy database. Please note: The data from our new One VM database is not being provided at this time.
|  |  | 2.t.2.a. | Median time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 3109 | 2700 | 2600 | 2500 | hours |  | Transmission only includes data from the legacy database.
|  |  | 2.t.2.b. | 95 percentile time | N/A |  | HFTD Tier 2 | Transmission | N/A | N/A | 8772 | 7800 | 7700 | 7600 | hours |  | Transmission only includes data from the legacy database.
|  |  | 2.t.3.a. | Median time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 2678.5 | 2700 | 2600 | 2500 | hours |  | Transmission only includes data from the legacy database.
|  |  | 2.t.3.b. | 95 percentile time | N/A |  | HFTD Tier 3 | Transmission | N/A | N/A | 7044 | 7800 | 7700 | 7600 | hours |  | Transmission only includes data from the legacy database.
|  |  | 2.t.4.a. | Median time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 2724 | 2700 | 2600 | 2500 | hours |  | Transmission only includes data from the legacy database.
|  |  | 2.t.4.b. | 95 percentile time | N/A |  | Non- HFTD | Transmission | N/A | N/A | 7936 | 7800 | 7700 | 7600 | hours |  | Transmission only includes data from the legacy database.
|  | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 3.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 0 | 0 | 0 | 0 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 1 | 2 | 2 | 2 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 0 | 0 | 0 | 0 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 1 | 2 | 2 | 2 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 0 | 0 | 0 | 0 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 1 | 6 | 6 | 6 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 0 | 1 | 1 | 1 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 2 | 10 | 27 | 27 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 1 | 5 | 1 | 1 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 15 | 12 | 29 | 29 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 1 | 1 | 1 | 1 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 3.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 21 | 13 | 20 | 20 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 4.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 808 | 528 | 502 | 380 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 2036 | 1273 | 1209 | 420 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 868 | 550 | 180 | 180 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 2029 | 1251 | 220 | 200 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 121 | 46 | 44 | 42 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 1953 | 869 | 826 | 785 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 329 | 331 | 400 | 411 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 835 | 1003.5 | 446 | 316 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 182 | 321.75 | 374 | 417 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 860 | 855.5 | 637 | 589 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 503 | 348 | 827 | 1048 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 4.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 1533 | 1105.6667 | 1340 | 1526 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 5.d.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 917 | 1603 | 1664 | 1724 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.d.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Distribution | N/A | N/A | 2928 | 2803 | 2880 | 2958 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.d.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 1223 | 1379 | 1421 | 1462 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.d.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Distribution | N/A | N/A | 2762 | 2731 | 2804 | 2877 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.d.4.a. | Median time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 1653 | 1153 | 1095 | 1037 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.d.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Distribution | N/A | N/A | 3360 | 2772 | 2845 | 2917 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.t.2.a. | Median time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 919.5 | 1095 | 557 | 636 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.t.2.b. | 95 percentile time | N/A | N/A | HFTD Tier 2 | Transmission | N/A | N/A | 1959 | 1825 | 1470 | 1687 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.t.3.a. | Median time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 230 | 1095 | 506 | 594 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.t.3.b. | 95 percentile time | N/A | N/A | HFTD Tier 3 | Transmission | N/A | N/A | 1564 | 1825 | 1277 | 1452 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.t.4.a. | Median time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 472 | 1095 | 686 | 822 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  |  | 5.t.4.b. | 95 percentile time | N/A | N/A | Non- HFTD | Transmission | N/A | N/A | 1633 | 1825 | 1457 | 1646 | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months.
|  | 6. Vegetation management work orders | 6.a. | Number of vegetation management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 98396 | 275000 | 275000 | 275000 | Number of orders | Data is in total number of trees.​ | This data includes Legacy (Distribution and Transmission) and One VM data.
|  |  | 6.b. | Number of vegetation management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 3 | 110 | 105 | 100 | Number of orders | Data is in total number of trees and is based off P1/P2 and Second Patrol numbers. These numbers do not include constrained trees.
|  | 7. Asset management work orders | 7.a. | Number of asset management open work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 962457 | 644618 | 1000000 | 1082000 | Number of orders
|  |  | 7.b. | Number of asset management past due work orders (total) | N/A | N/A | N/A | N/A | N/A | N/A | 612396 | 282584 | 624000 | 746000 | Number of orders
|  | 8. Response Time | 8.a. | Response time to locked open circuit breaker | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Hours |  | For metric 8a, data for crew response time to a locked circuit breaker incident is only readily available for instances involving hazard conditions such as 911 or wire down calls. PG&E will continue to review the available information in its outage systems to provide this information in a future filing, although we anticipate creating a system to capture this data could take many months. Currently, any quarterly data would reflect only 911 and wire down events and is not a good representation of our overall response time.
|  | 9. Fatalities and injuries due to utility-related ignitions | 9.a. | Fatalities due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of fatalities
|  |  | 9.b. | Injuries due to utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of injuries
|  | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | 10.a. | Value of assets destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1000
|  | 11. Structures damaged or destroyed by utility-related ignitions | 11.a. | Number of structures destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of structures
|  |  | 11.b. | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of structures
|  | 12. Acreage burned by utility-ignited wildfires | 12.a. | Acreage burned by utility-ignited wildfires | N/A | N/A | N/A | N/A | N/A | N/A | 357 | 0 | 0 | 0 | Acres
|  | 13. Number of utility-related ignitions | 13.a. | Number of ignitions | RFW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | HWW only | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 2 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | None | N/A | HFTD Tier 2 | N/A | N/A | N/A | 2 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | RFW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | HWW only | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | HWW & RFW | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | None | N/A | HFTD Tier 3 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | RFW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | HWW only | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | HWW & RFW | N/A | Non- HFTD | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
|  |  |  | Number of ignitions | None | N/A | Non- HFTD | N/A | N/A | N/A | 2 | 0 | 0 | 0 | Number of ignitions | CPUC Reportable, fire size >10 acre
x |  | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 16808 | 224111 | 438012 | 438012 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
|  | 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 28454 | 0 | 147894 | 147894 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial".
|  | 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 614 | 219494 | 4712 | 4712 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 630.3 | 8660.905 | 16425 | 16425 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 1067.025 | 0 | 5546 | 5546 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 23.025 | 8482.4783 | 177 | 177 | # of circuit miles inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.c.iLevel 1 findingsHFTD Tier 2Patrol Inspectionother | 14. Grid condition findings from inspection | 14.d.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 1 | 0 | 13 | 13 | # of findings from these asset inspections | Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.c.iiLevel 1 findingsHFTD Tier 2Detailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 71 | 0 | 414 | 414 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.c.iiLevel 1 findingsHFTD Tier 2Detailed Inspectionother | 14. Grid condition findings from inspection | 14.d.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 11 | 1576.6357 | 6 | 6 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.c.iiiLevel 1 findingsHFTD Tier 2Other Inspectionother | 14. Grid condition findings from inspection | 14.d.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 488 | 2038.6667 | 2281 | 2281 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.d.iLevel 2 findingsHFTD Tier 2Patrol Inspectionother | 14. Grid condition findings from inspection | 14.d.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 3 | 0 | 206 | 206 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.d.iiLevel 2 findingsHFTD Tier 2Detailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 10355 | 0 | 19892 | 19892 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.d.iiLevel 2 findingsHFTD Tier 2Detailed Inspectionother | 14. Grid condition findings from inspection | 14.d.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 172 | 54920.2451 | 1137 | 1137 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.d.iiiLevel 2 findingsHFTD Tier 2Other Inspectionother | 14. Grid condition findings from inspection | 14.d.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 1882 | 6306 | 9656 | 9656 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.e.iLevel 3 findingsHFTD Tier 2Patrol Inspectionother | 14. Grid condition findings from inspection | 14.d.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.e.iiLevel 3 findingsHFTD Tier 2Detailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 197 | 0 | 0 | 0 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.e.iiLevel 3 findingsHFTD Tier 2Detailed Inspectionother | 14. Grid condition findings from inspection | 14.d.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 41 | 9501.3651 | 237 | 237 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.2.e.iiiLevel 3 findingsHFTD Tier 2Other Inspectionother | 14. Grid condition findings from inspection | 14.d.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 113 | 520.6667 | 1451 | 1451 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 25778 | 192913 | 200464 | 200464 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility
|  | 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 6427 | 0 | 67060 | 67060 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial".
|  | 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 323 | 9578 | 2044 | 2044 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. Detailed ground inspections in HFTD Tier 3.
|  | 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 966.675 | 7455.2395 | 7517 | 7517 | # of circuit miles inspected by the utility | Projected data is based on the delta change from 2021 to 2022 for 2023 projection. 2024 and 2025 projected data stays flat until further data is obtained to update the projected data.
|  | 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 241.0125 | 0 | 2515 | 2515 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 12.1125 | 370.1476 | 77 | 77 | # of circuit miles inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.c.iLevel 1 findingsHFTD Tier 3Patrol Inspectionother | 14. Grid condition findings from inspection | 14.d.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 1 | 0 | 6 | 6 | # of findings from these asset inspections | Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.c.iiLevel 1 findingsHFTD Tier 3Detailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 18 | 0 | 188 | 188 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.c.iiLevel 1 findingsHFTD Tier 3Detailed Inspectionother | 14. Grid condition findings from inspection | 14.d.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 3 | 40.882 | 2 | 2 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.c.iiiLevel 1 findingsHFTD Tier 3Other Inspectionother | 14. Grid condition findings from inspection | 14.d.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 306 | 1254.6667 | 1043 | 1043 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.d.iLevel 2 findingsHFTD Tier 3Patrol Inspectionother | 14. Grid condition findings from inspection | 14.d.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 3 | 0 | 94 | 94 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.d.iiLevel 2 findingsHFTD Tier 3Detailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 1883 | 0 | 9020 | 9020 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.d.iiLevel 2 findingsHFTD Tier 3Detailed Inspectionother | 14. Grid condition findings from inspection | 14.d.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 52 | 1448.6962 | 493 | 493 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.d.iiiLevel 2 findingsHFTD Tier 3Other Inspectionother | 14. Grid condition findings from inspection | 14.d.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 602 | 3344 | 4417 | 4417 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.e.iLevel 3 findingsHFTD Tier 3Patrol Inspectionother | 14. Grid condition findings from inspection | 14.d.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 0 | 0 | 0 | 0 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.e.iiLevel 3 findingsHFTD Tier 3Detailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 45 | 0 | 0 | 0 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.e.iiLevel 3 findingsHFTD Tier 3Detailed Inspectionother | 14. Grid condition findings from inspection | 14.d.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 21 | 281.7402 | 103 | 103 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.3.e.iiiLevel 3 findingsHFTD Tier 3Other Inspectionother | 14. Grid condition findings from inspection | 14.d.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 70 | 330 | 664 | 664 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 350954 | 950000 | 1301439 | 1301439 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projected data is based on the average of 2021 and 2022 patrols. 2024 and 2025 projected data stays flat until further data is obtained to update the projected data.
|  | 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 201 | 0 | 5088 | 5088 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial".
|  | 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 90609 | 314929 | 328555 | 328555 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 13160.775 | 36713.3241 | 48804 | 48804 | # of circuit miles inspected by the utility | Projected data is based on the delta change from 2021 to 2022 for 2023 projection. 2024 and 2025 projected data stays flat until further data is obtained to update the projected data.
|  | 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 7.5375 | 0 | 191 | 191 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 3397.8375 | 12170.6215 | 12321 | 12321 | # of circuit miles inspected by the utility | Projected data is based on the delta change from 2021 to 2022 for 2023 projection. 2024 and 2025 projected data stays flat until further data is obtained to update the projected data.
|  | 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.c.iLevel 1 findingsNon-HFTDPatrol Inspectionother | 14. Grid condition findings from inspection | 14.d.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 103 | 0 | 78 | 78 | # of findings from these asset inspections | Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.c.iiLevel 1 findingsNon-HFTDDetailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 40 | 0 | 15 | 15 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.c.iiLevel 1 findingsNon-HFTDDetailed Inspectionother | 14. Grid condition findings from inspection | 14.d.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 451 | 4343.0968 | 1051 | 1051 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.c.iiiLevel 1 findingsNon-HFTDOther Inspectionother | 14. Grid condition findings from inspection | 14.d.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 3520 | 11954.6667 | 10720 | 10720 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.d.iLevel 2 findingsNon-HFTDPatrol Inspectionother | 14. Grid condition findings from inspection | 14.d.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 162 | 0 | 703 | 703 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.d.iiLevel 2 findingsNon-HFTDDetailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 1188 | 0 | 907 | 907 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.d.iiLevel 2 findingsNon-HFTDDetailed Inspectionother | 14. Grid condition findings from inspection | 14.d.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 16320 | 101880.6445 | 106978 | 106978 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.d.iiiLevel 2 findingsNon-HFTDOther Inspectionother | 14. Grid condition findings from inspection | 14.d.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 2979 | 12615.6667 | 13342 | 13342 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.e.iLevel 3 findingsNon-HFTDPatrol Inspectionother | 14. Grid condition findings from inspection | 14.d.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 3 | 0 | 0 | 0 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.e.iiLevel 3 findingsNon-HFTDDetailed InspectionAerial | 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 22 | 0 | 0 | 0 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.e.iiLevel 3 findingsNon-HFTDDetailed Inspectionother | 14. Grid condition findings from inspection | 14.d.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 7379 | 19363.3623 | 23886 | 23886 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
|  | 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections.
| 14.d.4.e.iiiLevel 3 findingsNon-HFTDOther Inspectionother | 14. Grid condition findings from inspection | 14.d.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 563 | 1338.3333 | 1595 | 1595 | # of findings from these asset inspections
|  | 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 26000 | 40000 | 40000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection based on historical
|  | 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 73 | 20000 | 13000 | 15000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
|  | 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 19 | 19000 | 16000 | 18000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
|  | 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 1004.7857 | 4478.3671 | 4478.3671 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 2.7375 | 772.9121 | 1455.4693 | 1679.3877 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0.7125 | 734.2665 | 1791.3469 | 1791.3469 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 2 | 26 | 12 | 9 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.c.i | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 5 | 54 | 109 | 97 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 1 | 25 | 33 | 33 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 7 | 18 | 17 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 7 | 33 | 48 | 24 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 4 | 97 | 38 | 35 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.d.i | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 2 | 157 | 71 | 71 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 25 | 5802 | 3527 | 3463 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 9 | 2266 | 3016 | 2885 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 34 | 496 | 1353 | 1341 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 5 | 7 | 1 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.e.i | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 4 | 5 | 5 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 6 | 2340 | 2583 | 2536 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 1 | 718 | 1569 | 1503 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.2.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 10 | 89 | 525 | 337 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.a.i | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 1544 | 16000 | 22000 | 22000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection based on historical
|  | 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 17 | 4000 | 7000 | 4000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
|  | 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.a.ii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 9 | 7000 | 3000 | 4000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
|  | 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.a.iii | Number of assets inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.i | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 57.9 | 618.3297 | 2506.063 | 2506.063 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0.6375 | 154.5824 | 797.3837 | 455.6478 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.ii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0.3375 | 270.5192 | 341.7359 | 455.6478 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.b.iii | Number of circuit miles inspected | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 1 | 4 | 11 | 11 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.c.i | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 4 | 18 | 48 | 48 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 5 | 21 | 12 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.c.ii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 3 | 2 | 2 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.c.iii | Level 1 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 4 | 13 | 13 | 11 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 6 | 17 | 17 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.d.i | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 5 | 25 | 41 | 41 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 6 | 1195 | 1596 | 908 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.d.ii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 7 | 470 | 398 | 541 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.d.iii | Level 2 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 15 | 149 | 432 | 432 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 0 | 2 | 2 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.e.i | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 1 | 1 | 1 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 426 | 1451 | 826 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.e.ii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 142 | 266 | 362 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.3.e.iii | Level 3 findings | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 9 | 18 | 154 | 131 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.a.i | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 11957 | 63000 | 58000 | 58000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection based on historical
|  | 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 6587 | 25000 | 20000 | 13000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
|  | 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.a.ii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 5192 | 20000 | 22000 | 18000 | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | Projection calculated based on expected baseline frequency.
|  | 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.a.iii | Number of assets inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.i | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 448.3875 | 2434.6731 | 6902.6852 | 6902.6852 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 247.0125 | 966.1401 | 2380.2363 | 1547.1536 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.ii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 194.7 | 772.9121 | 2618.2599 | 2142.2126 | # of circuit miles inspected by the utility
|  | 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.b.iii | Number of circuit miles inspected | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other |  |  |  |  | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 2 | 39 | 74 | 27 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.c.i | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 43 | 186 | 260 | 260 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 15 | 70 | 125 | 120 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.c.ii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 18 | 34 | 81 | 23 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.c.iii | Level 1 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 50 | 203 | 172 | 152 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 9 | 274 | 83 | 71 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.d.i | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 33 | 221 | 127 | 127 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 2121 | 10111 | 6682 | 6437 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.d.ii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 614 | 4853 | 5564 | 1787 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.d.iii | Level 2 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 206 | 1223 | 1752 | 1752 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 6 | 27 | 33 | 16 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.e.i | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 1 | 88 | 43 | 43 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 2486 | 4145 | 5700 | 5490 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.e.ii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 890 | 1929 | 4972 | 1451 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
|  | 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections.
|  | 14. Grid condition findings from inspection | 14.t.4.e.iii | Level 3 findings | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 267 | 211 | 566 | 431 | # of findings from these asset inspections | 2024 projections are max of 100% of forecast based on historical and estimate units, and 75% of forecast plus 2024 Q1 actuals. 2025 projections are forecasted based on historical and estimated inspection units. Projections are approximate and actual finds will be dependent on future find rates that may differ from forecasted rates, the order that different inspection methods occur, the final number of inspections performed, and other factors.
x |  | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.a.iLevel 1 findings fixedHFTD Tier 2Patrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 1 | 7 | 7 | 7 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.a.iiLevel 1 findings fixedHFTD Tier 2Detailed InspectionAerial | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 71 | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.a.iiLevel 1 findings fixedHFTD Tier 2Detailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 12 | 96 | 96 | 96 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.a.iiiLevel 1 findings fixedHFTD Tier 2Other Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 491 | 685 | 685 | 685 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.b.iLevel 2 findings fixedHFTD Tier 2Patrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 38 | 13 | 12 | 10 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.b.iiLevel 2 findings fixedHFTD Tier 2Detailed InspectionAerial | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 2767 | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.b.iiLevel 2 findings fixedHFTD Tier 2Detailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 8707 | 3798 | 4011 | 4223 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.b.iiiLevel 2 findings fixedHFTD Tier 2Other Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 4997 | 687 | 299 | 300 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.c.iLevel 3 findings fixedHFTD Tier 2Patrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Patrol Inspection | other | 6 | 6 | 7 | 7 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.c.iiLevel 3 findings fixedHFTD Tier 2Detailed InspectionAerial | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | 41 | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.c.iiLevel 3 findings fixedHFTD Tier 2Detailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Detailed Inspection | other | 2621 | 326 | 293 | 260 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.2.c.iiiLevel 3 findings fixedHFTD Tier 2Other Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Distribution | Other Inspection | other | 1319 | 195 | 182 | 169 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.a.iLevel 1 findings fixedHFTD Tier 3Patrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 1 | 3 | 3 | 3 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.a.iiLevel 1 findings fixedHFTD Tier 3Detailed InspectionAerial | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 18 | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.a.iiLevel 1 findings fixedHFTD Tier 3Detailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 3 | 79 | 79 | 79 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.a.iiiLevel 1 findings fixedHFTD Tier 3Other Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 309 | 401 | 401 | 401 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.b.iLevel 2 findings fixedHFTD Tier 3Patrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 14 | 1 | 1 | 1 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.b.iiLevel 2 findings fixedHFTD Tier 3Detailed InspectionAerial | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 1562 | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.b.iiLevel 2 findings fixedHFTD Tier 3Detailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 3872 | 2916 | 3118 | 3319 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.b.iiiLevel 2 findings fixedHFTD Tier 3Other Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 2167 | 69 | 1 | 1 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.c.iLevel 3 findings fixedHFTD Tier 3Patrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Patrol Inspection | other | 2 | 1 | 1 | 1 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.c.iiLevel 3 findings fixedHFTD Tier 3Detailed InspectionAerial | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | 35 | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.c.iiLevel 3 findings fixedHFTD Tier 3Detailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Detailed Inspection | other | 1280 | 90 | 66 | 43 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.3.c.iiiLevel 3 findings fixedHFTD Tier 3Other Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Distribution | Other Inspection | other | 455 | 47 | 42 | 37 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.a.iLevel 1 findings fixedNon-HFTDPatrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 104 | 54 | 54 | 54 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.a.iiLevel 1 findings fixedNon-HFTDDetailed InspectionAerial | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 42 | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.a.iiLevel 1 findings fixedNon-HFTDDetailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 456 | 529 | 529 | 529 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.a.iiiLevel 1 findings fixedNon-HFTDOther Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 3526 | 3428 | 3428 | 3428 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.b.iLevel 2 findings fixedNon-HFTDPatrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 208 | 54 | 42 | 31 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.b.iiLevel 2 findings fixedNon-HFTDDetailed InspectionAerial | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial | 237 | 0 | 0 | 0 | # of asset inspection findings which have been fixed | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.b.iiLevel 2 findings fixedNon-HFTDDetailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 5712 | 4709 | 4799 | 4888 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.b.iiiLevel 2 findings fixedNon-HFTDOther Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 3826 | 1118 | 1072 | 1027 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.c.iLevel 3 findings fixedNon-HFTDPatrol Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Patrol Inspection | other | 4 | 3 | 2 | 2 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | Aerial |  | 0 | 0 | 0 | # of asset inspection findings which have been fixed |  | Drone Inspection is new and not mature enough, hence PG&E will need more data to provide the projected values for 2024 & 2025. Please note that PG&E is working on improving the process for reporting tag remediation, impacting the delivery of our data. PG&E will provide updated data shortly.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.c.iiLevel 3 findings fixedNon-HFTDDetailed Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Detailed Inspection | other | 904 | 799 | 707 | 615 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections.
| 15.b.4.c.iiiLevel 3 findings fixedNon-HFTDOther Inspectionother | 15. Grid condition fixes in response to inspection findings | 15.b.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Distribution | Other Inspection | other | 1125 | 43 | 37 | 31 | # of asset inspection findings which have been fixed | Projected Data for 2023 - 2025 is a linear average forecast from previous quarterly data.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 2 | 26 | 12 | 9 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 5 | 56 | 107 | 97 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 1 | 67 | 34 | 33 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 0 | 7 | 19 | 17 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 7 | 34 | 52 | 24 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 4 | 53 | 28 | 35 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 19 | 67 | 56 | 71 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 681 | 9644 | 4274 | 3527 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 263 | 3739 | 2317 | 3016 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 178 | 752 | 1769 | 1341 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | 0 | 3 | 4 | 3 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Patrol Inspection | other | 0 | 2 | 3 | 3 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | 143 | 557 | 2755 | 1079 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Detailed Inspection | other | 82 | 190 | 900 | 351 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.2.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 2 | Transmission | Other Inspection | other | 119 | 100 | 388 | 411 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 1 | 4 | 11 | 11 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.i | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 4 | 19 | 48 | 48 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 0 | 5 | 21 | 12 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.ii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 0 | 4 | 2 | 2 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.a.iii | Level 1 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 4 | 13 | 13 | 11 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 4 | 13 | 20 | 17 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.i | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 1 | 43 | 56 | 41 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 466 | 3794 | 1781 | 908 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.ii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 116 | 1468 | 477 | 541 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.b.iii | Level 2 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 66 | 415 | 775 | 432 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | 0 | 1 | 0 | 1 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.i | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Patrol Inspection | other | 0 | 0 | 5 | 0 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | 105 | 150 | 545 | 334 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.ii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Detailed Inspection | other | 28 | 44 | 202 | 95 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.3.c.iii | Level 3 findings fixed | N/A | N/A | HFTD Tier 3 | Transmission | Other Inspection | other | 24 | 69 | 117 | 114 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 2 | 39 | 73 | 27 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.i | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 42 | 188 | 263 | 260 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 17 | 70 | 126 | 120 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.ii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 18 | 34 | 81 | 23 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.a.iii | Level 1 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 54 | 204 | 176 | 152 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 34 | 92 | 146 | 93 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.i | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 28 | 37 | 115 | 67 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 2571 | 1751 | 4769 | 2109 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.ii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 754 | 1156 | 2740 | 1342 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.b.iii | Level 2 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 418 | 1241 | 1621 | 1115 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | Aerial | 4 | 2 | 31 | 13 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.i | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Patrol Inspection | other | 11 | 0 | 271 | 62 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | Aerial | 466 | 55 | 2244 | 708 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.ii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Detailed Inspection | other | 316 | 125 | 1365 | 621 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Drone |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | Aerial |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | LiDAR |  |  |  |  | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections.
|  | 15. Grid condition fixes in response to inspection findings | 15.t.4.c.iii | Level 3 findings fixed | N/A | N/A | Non-HFTD | Transmission | Other Inspection | other | 244 | 229 | 1140 | 565 | # of asset inspection findings which have been fixed | 2024 projections are based on 2024 tag inventory and forecasted tags with in-year required end dates. 2025 projections are estimated based on tag inventory, forecasted 2024 and 2025 finds, and 2025 preliminary budgets. Projections are approximate and actual tag completion will depend on budget, unit costs, 2024-2025 tag finds, and other factors.
x |  | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 | 483 | 0 | 0 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
|  | 16. Vegetation clearance findings from inspection | 16.d.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 56470 | 409746 | 435440 | 435440 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial | 1 | 3033 | 2765 | 2765 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
|  | 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 26272 | 21611 | 18185 | 18185 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Non-Routine | other | 3615 | 5 | 5 | 5 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | LiDAR | 0 | 0 | 0 | 0 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
|  | 16. Vegetation clearance findings from inspection | 16.d.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Distribution | Routine | other | 4698 | 17830 | 17830 | 17830 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 | 505 | 0 | 0 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
|  | 16. Vegetation clearance findings from inspection | 16.d.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 30906 | 285188 | 283000 | 283000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial | 0 | 772 | 725 | 725 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
|  | 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 23938 | 27200 | 22802 | 22802 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Non-Routine | other | 2309 | 2 | 2 | 2 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | LiDAR | 0 | 0 | 0 | 0 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
|  | 16. Vegetation clearance findings from inspection | 16.d.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Distribution | Routine | other | 4011 | 13380 | 13380 | 13380 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | 0 | 35 | 0 | 0 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
|  | 16. Vegetation clearance findings from inspection | 16.d.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Routine | other | 160109 | 717468 | 685206 | 685206 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial | 0 | 766 | 708 | 708 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection.
|  | 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 2928 | 7118 | 6015 | 6015 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Non-Routine | other | 416 | 9 | 9 | 9 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | LiDAR | 0 | 0 | 0 | 0 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Projections account for there being no current workplan for Distribution GBL.
|  | 16. Vegetation clearance findings from inspection | 16.d.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Distribution | Routine | other | 14451 | 33465 | 33465 | 33465 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | 0 | 5500000 | 5500000 | 5500000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on Project Year. For 2024, and 2025, we expect approximately 5,500,000 trees.
|  | 16. Vegetation clearance findings from inspection | 16.t.2.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 1693 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | We are unable to pull forecasted numbers by HFTD tier. We've have placed all forecasted units in Non-HFTD
|  | 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | LiDAR | 0 | 5 | 4 | 2 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on the Project Year.
|  | 16. Vegetation clearance findings from inspection | 16.t.2.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 2 | Transmission | Routine | other | 0 | 3 | 0 | 1 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | 0 | 2100000 | 2100000 | 2100000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on Project Year. For 2024, and 2025, we expect approximately 2,100,000 trees.
|  | 16. Vegetation clearance findings from inspection | 16.t.3.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 545 |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | We are unable to pull forecasted numbers by HFTD tier. We've have placed all forecasted units in NonHFTD. Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | LiDAR | 0 | 47 | 10 | 10 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on the Project Year.
|  | 16. Vegetation clearance findings from inspection | 16.t.3.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | HFTD Tier 3 | Transmission | Routine | other | 0 | 3 | 1 | 1 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | 0 | 11000000 | 11000000 | 11000000 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on Project Year. For 2024, and 2025, we expect approximately 11,000,000 trees.
|  | 16. Vegetation clearance findings from inspection | 16.t.4.a.i | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Routine | other | 2315 | 64550 | 64550 | 64550 | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | These are forecasted numbers for all HFTD tiers. We are unable to pull forecasted data by HFTD tier. Inspection Method "Other" includes ground patrols.
|  | 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.a.ii | Number of trees inspected for vegetation compliance | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other |  |  |  |  | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | LiDAR |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.b.i | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Non-Routine | other |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Drone |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | Aerial |  |  |  |  | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method
|  | 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | LiDAR | 0 | 90 | 623 | 100 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 slot for each calendar year is the total count based on the Project Year.
|  | 16. Vegetation clearance findings from inspection | 16.t.4.b.ii | Number of trees inspected where at least some vegetation was found in non-compliant condition | N/A | N/A | Non-HFTD | Transmission | Routine | other | 0 | 22 | 4 | 10 | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols.
x |  | 17. Community outreach metrics | 17.a. | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Percentage of customers notified of evacuation |  | PG&E does not issue wildfire evacuation notices to customers and does not maintain metrics on the number of customers in an evacuation zone or the number of customers notified of evacuation orders. Because of this, PG&E is unable to report on evacuation related requirements in this table. PG&E anticipates this to be a recurring challenge going forward.

## Table 3
Utility | PG&E
Table No. | 3
Date Modified | 2025-02-03
[5 empty] | Actual | Projected
Table 3: List and description of additional metrics |  |  |  |  | Q4
Metric | Definition | Purpose | Assumptions made to connect metric to purpose | Third-party validation (if any) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
Customer Hours of PSPS per RFW OH Circuit Mile Day |  |  |  |  | 8.86 | 25.1 | 24.8 | 24.5

## Table 4
Utility | PG&E
Table No. | 4
Date Modified | 2025-02-03
Table 4: Weather patterns |  |  | Q4
Metric type | # | Metric name | 2024 | Unit(s) | Comments | Blank Meaning
1. Red flag warning only overhead circuit mile days | 1.a. | Red Flag Warning Only overhead circuit mile days - HFTD tier 2 | 41831.5 | Sum of overhead circuit miles of utility grid subject to red flag warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW multiplied by the number of days those circuit miles were under said RFW. For example, if 100 overhead circuit miles were under an RFW for 1 day, and 10 of those miles were under RFW for an additional day, then the total RFW OH circuit mile days would be 110.
| 1.b. | Red Flag Warning Only overhead circuit mile days - HFTD tier 3 | 19068.64 | Red flag warning overhead circuit mile days, see above for definition
| 1.c. | Red Flag Warning Only overhead circuit mile days - non-HFTD | 115554.48 | Red flag warning overhead circuit mile days, see above for definition
2. Wind condition overhead circuit mile days | 2.a. | High Wind Warning Only overhead circuit mile days - HFTD tier 2 | 1348.48 | Sum of overhead circuit miles of utility grid subject to high wind warnings (HWW, as defined by the National Weather Service) each day within a given time period, calculated as the number of overhead circuit miles that were under an HWW multiplied by the number of days those miles were under said HWW. For example, if 100 overhead circuit miles were under an HWW for 1 day, and 10 of those miles were under HWW for an additional day, then the total HWW OH circuit mile days would be 110.
| 2.b. | High Wind Warning Only overhead circuit mile days - HFTD tier 3 | 789.65 | High wind warning overhead circuit mile days, see above for definition
| 2.c. | High Wind Warning Only overhead circuit mile days - non-HFTD | 2575.02 | High wind warning overhead circuit mile days, see above for definition
3. Wind condition and Red flag warning overhead circuit mile days | 3.a. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 2 | 43179.98 | Sum of overhead circuit miles of utility grid subject to concurrent red flag warning and a high wind warning each day within a given time period, calculated as the number of overhead circuit miles that were under an RFW and HWW multiplied by the number of days those circuit miles were under said RFW and HWW. For example, if 100 overhead circuit miles were under an RFW and HWW for 1 day, and 10 of those miles were under RFW and HWW for an additional day, then the total RFW and HWW OH circuit mile days would be 110.
| 3.b. | High Wind Warning and Red Flag Warning overhead circuit mile days - HFTD tier 3 | 19858.29 | High wind warning and red flag warning overhead circuit mile days, see above for definition
| 3.c. | High Wind Warning and Red Flag Warning overhead circuit mile days - non-HFTD | 118129.5 | High wind warning and red flag warning overhead circuit mile days, see above for definition
4. Fire potential index overhead circuit mile days | 4.a. | Fire potential index circuit mile days - HFTD tier 2 | 448428.46 | Sum of overhead circuit miles of utility grid subject to high fire potential index (FPI, as defined by the utility in its WMP) each day within a given time period, calculated as the number of overhead circuit miles that were under a high FPI multiplied by the number of days those miles were under said FPI. For example, if 100 overhead circuit miles were under a high FPI for 1 day, and 10 of those miles were under a high FPI for an additional day, then the total FPI OH circuit mile days would be 110.
| 4.b. | Fire potential index circuit mile days - HFTD tier 3 | 164639.01 | Fire potential index overhead circuit mile days, see above for definition
| 4.c. | Fire potential index circuit mile days - non-HFTD | 86731.4906 | Fire potential index overhead circuit mile days, see above for definition
5. Other | 5.a. | Other relevant weather pattern metrics tracked (add additional rows as needed)

## Table 5
| Utility | PG&E | Notes:
| Table No. | 5 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2025-02-03
[8 empty] | Actual number of risk events | Projected risk events
| Table 5: Risk event drivers | [6 empty] | Q4
x | Risk event category | Metric type | # | Risk event driver | Line Type | HFTD Tier | Are risk events tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| Wire down event | 1. Fire | 1.a.d.0 | Fire | Distribution | Non-HFTD | Yes | 0 | 66 | 38 | 38 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | 0 | 5 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | 0 | 2 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.t.0 | Fire | Transmission | Non-HFTD | No | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.t.2 | Fire | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 1. Fire | 1.a.t.3 | Fire | Transmission | HFTD Tier 3 | No | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 16 | 91 | 78 | 78 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 1 | 9 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 3 | 39 | 21 | 21 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 128 | 554 | 524 | 524 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 9 | 36 | 27 | 27 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 6 | 16 | 14 | 14 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 6 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 11 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | 12 | 65 | 132 | 132 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | 4 | 11 | 14 | 14 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | 1 | 10 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.t.0 | 3rd party contact | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.d.0 | Other contact from object | Distribution | Non-HFTD | Yes | 1 | 17 | 68 | 68 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.d.2 | Other contact from object | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.d.3 | Other contact from object | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.t.0 | Other contact from object | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.t.2 | Other contact from object | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.f.t.3 | Other contact from object | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 11 | 11 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 2. Contact from object | 2.g.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 189 | 1205 | 2187 | 2187 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 158 | 416 | 262 | 262 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 135 | 372 | 207 | 207 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 4 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 2 | 3 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 4 | 0 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 0 | 0 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 164 | 567 | 748 | 748 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 23 | 50 | 43 | 43 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 13 | 32 | 21 | 21 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 2 | 5 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 2 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.0 | Connector device | Distribution | Non-HFTD | Yes | 1 | 0 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.2 | Connector device | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.d.3 | Connector device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.0 | Connector device | Transmission | Non-HFTD | No | 0 | 2 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.2 | Connector device | Transmission | HFTD Tier 2 | No | 0 | 4 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.d.t.3 | Connector device | Transmission | HFTD Tier 3 | No | 0 | 1 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 6 | 49 | 50 | 50 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 5 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 1 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 5 | 0 | 9 | 9 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | No | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 37 | 129 | 192 | 192 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 6 | 13 | 9 | 9 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 3 | 4 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 0 | 4 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 1 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 46 | 0 | 171 | 171 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 5 | 0 | 17 | 17 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 2 | 0 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 0 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 1 | 4 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 3 | 5 | 10 | 10 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 7. Vandalism/theft | 7.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 2 | 19 | 21 | 21 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 8. Lightning | 8.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.d.0 | Unknown | Distribution | Non-HFTD | No | 32 | 0 | 36 | 36 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 48 | 0 | 10 | 10 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 25 | 0 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.t.0 | Unknown | Transmission | Non-HFTD | No | 1 | 1 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 9. Unknown | 9.a.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.d.0 | All Other | Distribution | Non-HFTD | Yes | 7 | 0 | 97 | 97 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | 2 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.t.0 | All Other | Transmission | Non-HFTD | No | 0 | 0 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.t.2 | All Other | Transmission | HFTD Tier 2 | No | 0 | 2 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Wire down event | 10. Other | 10.a.t.3 | All Other | Transmission | HFTD Tier 3 | No | 0 | 0 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
x | Unplanned Outage | 11. Dig-in | 11.a.d.0 | Dig-in | Distribution | Non-HFTD | No | 29 | 82 | 70 | 70 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | No | 1 | 6 | 10 | 10 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | No | 1 | 6 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.t.0 | Dig-in | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 11. Dig-in | 11.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.d.0 | Fire | Distribution | Non-HFTD | Yes | 18 | 546 | 310 | 310 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.d.2 | Fire | Distribution | HFTD Tier 2 | Yes | 3 | 26 | 16 | 16 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.d.3 | Fire | Distribution | HFTD Tier 3 | Yes | 1 | 10 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.t.0 | Fire | Transmission | Non-HFTD | No | 2 | 7 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.t.2 | Fire | Transmission | HFTD Tier 2 | No | 0 | 14 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 12. Fire | 12.a.t.3 | Fire | Transmission | HFTD Tier 3 | No | 0 | 7 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 532 | 1411.2 | 1638 | 1638 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 83 | 254.7 | 286 | 286 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 20 | 91.8 | 91 | 91 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 13 | 32 | 30 | 30 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 5 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 1 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 57 | 443 | 410 | 410 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 3 | 7 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 1 | 2 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 380 | 1754 | 1707 | 1707 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 37 | 95 | 133 | 133 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 22 | 45 | 62 | 62 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 11 | 54 | 59 | 59 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 2 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 5 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.d.0 | 3rd party contact | Distribution | Non-HFTD | Yes | 31 | 294 | 231 | 231 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.d.2 | 3rd party contact | Distribution | HFTD Tier 2 | Yes | 11 | 38 | 36 | 36 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.d.3 | 3rd party contact | Distribution | HFTD Tier 3 | Yes | 10 | 15 | 15 | 15 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.t.0 | 3rd party contact | Transmission | Non-HFTD | No | 4 | 0 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.t.2 | 3rd party contact | Transmission | HFTD Tier 2 | No | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.e.t.3 | 3rd party contact | Transmission | HFTD Tier 3 | No | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.d.0 | Other | Distribution | Non-HFTD | Yes | 37 | 159 | 175 | 175 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 11 | 17 | 29 | 29 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 7 | 2 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 20 | 16 | 16 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.f.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 13. Object contact | 13.g.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 766 | 2263 | 4931 | 4931 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 333 | 580 | 809 | 809 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 300 | 620 | 758 | 758 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 2 | 20 | 20 | 20 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 4 | 10 | 13 | 13 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 14. Vegetation contact | 14.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 4 | 5 | 8 | 8 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 8 | 47 | 55 | 55 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 1 | 4 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 3 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 11 | 52 | 49 | 49 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 4 | 3 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 1 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 677 | 1567 | 2213 | 2213 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 86 | 109 | 200 | 200 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 50 | 57 | 93 | 93 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 4 | 10 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 2 | 3 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 2 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 217 | 184 | 433 | 433 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 21 | 3 | 31 | 31 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 4 | 0 | 13 | 13 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 4 | 10 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 5 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 1 | 5 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 269 | 677 | 825 | 825 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 30 | 74 | 113 | 113 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 11 | 38 | 47 | 47 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 212 | 803 | 977 | 977 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 29 | 72 | 90 | 90 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 7 | 49 | 52 | 52 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.0 | Cutout | Distribution | Non-HFTD | No | 0 | 322 | 224 | 224 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.2 | Cutout | Distribution | HFTD Tier 2 | No | 0 | 47 | 30 | 30 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.d.3 | Cutout | Distribution | HFTD Tier 3 | No | 0 | 14 | 12 | 12 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.0 | Cutout | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.2 | Cutout | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.g.t.3 | Cutout | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 66 | 224 | 253 | 253 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 23 | 50 | 70 | 70 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 9 | 34 | 39 | 39 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | No | 12 | 20 | 23 | 23 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | No | 0 | 10 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | No | 0 | 10 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 25 | 110 | 112 | 112 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 8 | 20 | 20 | 20 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 2 | 14 | 13 | 13 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 8 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 494 | 947 | 1266 | 1266 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 91 | 170 | 239 | 239 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 37 | 76 | 96 | 96 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 8 | 15 | 9 | 9 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 2 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 26 | 80 | 78 | 78 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 8 | 21 | 24 | 24 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 1 | 13 | 12 | 12 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.0 | Relay | Distribution | Non-HFTD | Yes | 3 | 4 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.2 | Relay | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.d.3 | Relay | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.0 | Relay | Transmission | Non-HFTD | No | 18 | 3 | 11 | 11 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.2 | Relay | Transmission | HFTD Tier 2 | No | 0 | 2 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.l.t.3 | Relay | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 1 | 0 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.0 | Splice | Distribution | Non-HFTD | Yes | 207 | 723 | 733 | 733 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.2 | Splice | Distribution | HFTD Tier 2 | Yes | 21 | 66 | 81 | 81 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.d.3 | Splice | Distribution | HFTD Tier 3 | Yes | 7 | 26 | 27 | 27 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.0 | Splice | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.2 | Splice | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.n.t.3 | Splice | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 51 | 199 | 172 | 172 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 2 | 6 | 9 | 9 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 2 | 3 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 27 | 5 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 5 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 1 | 3 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.0 | Tap | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.2 | Tap | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.d.3 | Tap | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.0 | Tap | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.2 | Tap | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.p.t.3 | Tap | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 966 | 3888 | 3675 | 3675 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 157 | 430 | 472 | 472 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 64 | 179 | 206 | 206 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 7 | 2 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 20 | 56 | 54 | 54 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 4 | 12 | 11 | 11 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 4 | 3 | 4 | 4 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.t.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.0 | Other | Distribution | Non-HFTD | Yes | 169 | 108 | 303 | 303 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 27 | 15 | 52 | 52 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 13 | 6 | 17 | 17 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.0 | Other | Transmission | Non-HFTD | Yes | 10 | 34 | 27 | 27 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 3 | 3 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 15. Equipment / facility failure or damage | 15.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 0 | 7605.77 | 5899 | 5899 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 0 | 1363.82 | 986 | 986 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 561.63 | 458 | 458 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 16. Wire-to-wire contact | 16.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 13 | 0 | 11 | 11 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 2 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 17 | 23 | 23 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 3 | 3 | 3 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 17. Contamination | 17.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 39 | 86 | 103 | 103 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 2 | 2 | 6 | 6 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 1 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 11 | 7 | 7 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 18. Vandalism/theft | 18.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 10 | 158 | 299 | 299 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 3 | 20 | 104 | 104 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 4 | 11 | 64 | 64 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 2 | 20 | 42 | 42 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 10 | 23 | 23 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 19. Lightning | 19.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 1 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.d.0 | Government agency request | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.d.2 | Government agency request | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.d.3 | Government agency request | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.t.0 | Government agency request | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.t.2 | Government agency request | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 20. Government agency request | 20.a.t.3 | Government agency request | Transmission | HFTD Tier 3 | No | 0 | 2 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.d.0 | Customer request | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.d.2 | Customer request | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.d.3 | Customer request | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.t.0 | Customer request | Transmission | Non-HFTD | No | 12 | 20 | 24 | 24 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.t.2 | Customer request | Transmission | HFTD Tier 2 | No | 4 | 11 | 15 | 15 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 21. Customer request | 21.a.t.3 | Customer request | Transmission | HFTD Tier 3 | No | 0 | 8 | 5 | 5 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.d.0 | Emergency repairs | Distribution | Non-HFTD | Yes | 0 | 47.46 | 21 | 21 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.d.2 | Emergency repairs | Distribution | HFTD Tier 2 | Yes | 0 | 3.39 | 2 | 2 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.d.3 | Emergency repairs | Distribution | HFTD Tier 3 | Yes | 0 | 1.13 | 1 | 1 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.t.0 | Emergency repairs | Transmission | Non-HFTD | No | 4 | 165 | 206 | 206 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.t.2 | Emergency repairs | Transmission | HFTD Tier 2 | No | 6 | 50 | 53 | 53 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 22. Emergency repairs | 22.a.t.3 | Emergency repairs | Transmission | HFTD Tier 3 | No | 1 | 16 | 15 | 15 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.d.0 | Unknown | Distribution | Non-HFTD | No | 2842 | 10632.17 | 11431 | 11431 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 609 | 1328.9 | 1649 | 1649 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 330 | 541.26 | 741 | 741 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.t.0 | Unknown | Transmission | Non-HFTD | No | 64 | 90 | 150 | 150 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 18 | 26 | 87 | 87 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 23. Unknown | 23.a.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 6 | 18 | 43 | 43 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.d.0 | All Other | Distribution | Non-HFTD | Yes | 379 | 0 | 421 | 421 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.d.2 | All Other | Distribution | HFTD Tier 2 | Yes | 127 | 0 | 143 | 143 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.d.3 | All Other | Distribution | HFTD Tier 3 | Yes | 45 | 0 | 50 | 50 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.t.0 | All Other | Transmission | Non-HFTD | No | 45 | 80 | 139 | 139 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.t.2 | All Other | Transmission | HFTD Tier 2 | No | 15 | 60 | 49 | 49 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.
| Unplanned Outage | 24. Other | 24.a.t.3 | All Other | Transmission | HFTD Tier 3 | No | 3 | 14 | 23 | 23 | # risk events (excluding ignitions) | Projected values are based on a 2 year average for 2024 and 2025.

## Table 6
| Utility | PG&E | Notes:
| Table No. | 6 | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV.
| Date Modified | 2025-02-03
[7 empty] | Actual number of ignitions | Projected ignitions
| Table 6: Ignition drivers | [5 empty] | Q4
| Metric type | # | Ignition driver | Line Type | HFTD Tier | Are ignitions tracked for ignition driver? (yes / no) | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
| 1. Dig-in | 1.a.d.0 | Dig-in | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.2 | Dig-in | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.d.3 | Dig-in | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.0 | Dig-in | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.2 | Dig-in | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 1. Dig-in | 1.a.t.3 | Dig-in | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
x | 2. Contact from object | 2.a.d.0 | Animal contact | Distribution | Non-HFTD | Yes | 15 | 34 | 45 | 45 | # ignitions
| 2. Contact from object | 2.a.d.2 | Animal contact | Distribution | HFTD Tier 2 | Yes | 1 | 6.8747 | 3 | 3 | # ignitions
| 2. Contact from object | 2.a.d.3 | Animal contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.a.t.0 | Animal contact | Transmission | Non-HFTD | Yes | 1 | 3 | 3 | 3 | # ignitions
| 2. Contact from object | 2.a.t.2 | Animal contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 4 | 4 | # ignitions
| 2. Contact from object | 2.a.t.3 | Animal contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.d.0 | Balloon contact | Distribution | Non-HFTD | Yes | 2 | 20 | 15 | 15 | # ignitions
| 2. Contact from object | 2.b.d.2 | Balloon contact | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 2 | 2 | # ignitions
| 2. Contact from object | 2.b.d.3 | Balloon contact | Distribution | HFTD Tier 3 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.0 | Balloon contact | Transmission | Non-HFTD | Yes | 0 | 2 | 1 | 1 | # ignitions
| 2. Contact from object | 2.b.t.2 | Balloon contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.b.t.3 | Balloon contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.d.0 | Land vehicle contact | Distribution | Non-HFTD | Yes | 8 | 36 | 39.5 | 39.5 | # ignitions
| 2. Contact from object | 2.c.d.2 | Land vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0.9821 | 2 | 2 | # ignitions
| 2. Contact from object | 2.c.d.3 | Land vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 2. Contact from object | 2.c.t.0 | Land vehicle contact | Transmission | Non-HFTD | Yes | 0 | 6 | 3 | 3 | # ignitions
| 2. Contact from object | 2.c.t.2 | Land vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 2 | 1 | 1 | # ignitions
| 2. Contact from object | 2.c.t.3 | Land vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.0 | Aircraft vehicle contact | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.2 | Aircraft vehicle contact | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.d.3 | Aircraft vehicle contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # ignitions
| 2. Contact from object | 2.d.t.0 | Aircraft vehicle contact | Transmission | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 2. Contact from object | 2.d.t.2 | Aircraft vehicle contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.d.t.3 | Aircraft vehicle contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.0 | 3rd party facility | Distribution | Non-HFTD | Yes | 0 | 0 | 4.5 | 4.5 | # ignitions
| 2. Contact from object | 2.e.d.2 | 3rd party facility | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.d.3 | 3rd party facility | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.0 | 3rd party facility | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.2 | 3rd party facility | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.e.t.3 | 3rd party facility | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.f.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.f.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following drivers 2.g Other or 10. Unknown.
| 2. Contact from object | 2.g.d.0 | Other | Distribution | Non-HFTD | Yes | 2 | 23 | 12 | 12 | # ignitions
| 2. Contact from object | 2.g.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 4.9105 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 2. Contact from object | 2.g.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.d.0 | Vegetation contact | Distribution | Non-HFTD | Yes | 12 | 57 | 54 | 54 | # ignitions
| 3. Vegetation contact | 3.a.d.2 | Vegetation contact | Distribution | HFTD Tier 2 | Yes | 2 | 25.5346 | 18 | 18 | # ignitions
| 3. Vegetation contact | 3.a.d.3 | Vegetation contact | Distribution | HFTD Tier 3 | Yes | 5 | 16.6957 | 8 | 8 | # ignitions
| 3. Vegetation contact | 3.a.t.0 | Vegetation contact | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.2 | Vegetation contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 3. Vegetation contact | 3.a.t.3 | Vegetation contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.0 | Anchor/guy | Distribution | Non-HFTD | Yes | 0 | 2 | 1.5 | 1.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.2 | Anchor/guy | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.d.3 | Anchor/guy | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.0 | Anchor/guy | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.2 | Anchor/guy | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.a.t.3 | Anchor/guy | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.0 | Capacitor bank | Distribution | Non-HFTD | Yes | 3 | 9 | 6.5 | 6.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.2 | Capacitor bank | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.d.3 | Capacitor bank | Distribution | HFTD Tier 3 | Yes | 1 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.0 | Capacitor bank | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.2 | Capacitor bank | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.b.t.3 | Capacitor bank | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.0 | Conductor | Distribution | Non-HFTD | Yes | 7 | 43 | 37 | 37 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.2 | Conductor | Distribution | HFTD Tier 2 | Yes | 3 | 0.9821 | 5 | 5 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.d.3 | Conductor | Distribution | HFTD Tier 3 | Yes | 1 | 2.9463 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.0 | Conductor | Transmission | Non-HFTD | Yes | 0 | 1 | 1.5 | 1.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.2 | Conductor | Transmission | HFTD Tier 2 | Yes | 2 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.c.t.3 | Conductor | Transmission | HFTD Tier 3 | Yes | 0 | 1 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.0 | Connection device | Distribution | Non-HFTD | Yes | 6 | 30 | 21.5 | 21.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.2 | Connection device | Distribution | HFTD Tier 2 | Yes | 0 | 2.9463 | 3 | 3 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.d.3 | Connection device | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.0 | Connection device | Transmission | Non-HFTD | Yes | 0 | 0 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.2 | Connection device | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.d.t.3 | Connection device | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.0 | Crossarm | Distribution | Non-HFTD | Yes | 1 | 0 | 2 | 2 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.2 | Crossarm | Distribution | HFTD Tier 2 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.d.3 | Crossarm | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.0 | Crossarm | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.2 | Crossarm | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.e.t.3 | Crossarm | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.0 | Fuse | Distribution | Non-HFTD | Yes | 0 | 8 | 5.5 | 5.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.2 | Fuse | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 2 | 2 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.d.3 | Fuse | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.0 | Fuse | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.2 | Fuse | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.f.t.3 | Fuse | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.g.d.0 | Cutout | Distribution | Non-HFTD | No | 1 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.d.2 | Cutout | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.d.3 | Cutout | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.t.0 | Cutout | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.t.2 | Cutout | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.g.t.3 | Cutout | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions related to cutout failure are characterized as fuse failures in PG&E's ignitions database.
| 4. Equipment / facility failure or damage | 4.h.d.0 | Insulator and bushing | Distribution | Non-HFTD | Yes | 0 | 3 | 2.5 | 2.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.2 | Insulator and bushing | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.d.3 | Insulator and bushing | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.0 | Insulator and bushing | Transmission | Non-HFTD | Yes | 1 | 0 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.2 | Insulator and bushing | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.h.t.3 | Insulator and bushing | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.0 | Lightning arrester | Distribution | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.2 | Lightning arrester | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.d.3 | Lightning arrester | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.0 | Lightning arrester | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.2 | Lightning arrester | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.i.t.3 | Lightning arrester | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.0 | Pole | Distribution | Non-HFTD | Yes | 0 | 6 | 6 | 6 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.2 | Pole | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.d.3 | Pole | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.0 | Pole | Transmission | Non-HFTD | Yes | 1 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.2 | Pole | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.j.t.3 | Pole | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.0 | Recloser | Distribution | Non-HFTD | Yes | 0 | 0 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.2 | Recloser | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.d.3 | Recloser | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.0 | Recloser | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.2 | Recloser | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.k.t.3 | Recloser | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.0 | Relay | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.2 | Relay | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.d.3 | Relay | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.0 | Relay | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.2 | Relay | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.l.t.3 | Relay | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.0 | Sectionalizer | Distribution | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.2 | Sectionalizer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.d.3 | Sectionalizer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.0 | Sectionalizer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.2 | Sectionalizer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.m.t.3 | Sectionalizer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.n.d.0 | Splice | Distribution | Non-HFTD | No | 3 | 0 | 5 | 5 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.d.2 | Splice | Distribution | HFTD Tier 2 | No | 0 | 0 | 1 | 1 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.d.3 | Splice | Distribution | HFTD Tier 3 | No | 0 | 0 | 1 | 1 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.t.0 | Splice | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.t.2 | Splice | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.n.t.3 | Splice | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Connection Devices 4.d.d.
| 4. Equipment / facility failure or damage | 4.o.d.0 | Switch | Distribution | Non-HFTD | Yes | 0 | 8 | 5.5 | 5.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.2 | Switch | Distribution | HFTD Tier 2 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.d.3 | Switch | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.0 | Switch | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.2 | Switch | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.o.t.3 | Switch | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.0 | Tap | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.2 | Tap | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.d.3 | Tap | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.0 | Tap | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.2 | Tap | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.p.t.3 | Tap | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.0 | Tie wire | Distribution | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.2 | Tie wire | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.d.3 | Tie wire | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.0 | Tie wire | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.2 | Tie wire | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.q.t.3 | Tie wire | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.0 | Transformer | Distribution | Non-HFTD | Yes | 0 | 13 | 15 | 15 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.2 | Transformer | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.d.3 | Transformer | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.0 | Transformer | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.2 | Transformer | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.r.t.3 | Transformer | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.0 | Voltage regulator/booster | Distribution | Non-HFTD | Yes | 0 | 1 | 1 | 1 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.2 | Voltage regulator/booster | Distribution | HFTD Tier 2 | Yes | 0 | 0.9821 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.d.3 | Voltage regulator/booster | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.0 | Voltage regulator/booster | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.2 | Voltage regulator/booster | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.s.t.3 | Voltage regulator/booster | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.t.d.0 | Unknown | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.d.2 | Unknown | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.d.3 | Unknown | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.t.0 | Unknown | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.t.2 | Unknown | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.t.t.3 | Unknown | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following drivers 2.g Other or 10. Unknown.
| 4. Equipment / facility failure or damage | 4.u.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 20 | 14.5 | 14.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 4.9105 | 2 | 2 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 3.9284 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 4. Equipment / facility failure or damage | 4.u.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.0 | Wire-to-wire contact | Distribution | Non-HFTD | Yes | 5 | 7 | 5 | 5 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.2 | Wire-to-wire contact | Distribution | HFTD Tier 2 | Yes | 1 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.d.3 | Wire-to-wire contact | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.0 | Wire-to-wire contact | Transmission | Non-HFTD | Yes | 0 | 1 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.2 | Wire-to-wire contact | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 5. Wire-to-wire contact | 5.a.t.3 | Wire-to-wire contact | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.0 | Contamination | Distribution | Non-HFTD | Yes | 4 | 8 | 4 | 4 | # ignitions
| 6. Contamination | 6.a.d.2 | Contamination | Distribution | HFTD Tier 2 | Yes | 1 | 1.9642 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.d.3 | Contamination | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.0 | Contamination | Transmission | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 6. Contamination | 6.a.t.2 | Contamination | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 6. Contamination | 6.a.t.3 | Contamination | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.0 | Protective device operation | Distribution | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.2 | Protective device operation | Distribution | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.d.3 | Protective device operation | Distribution | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.0 | Protective device operation | Transmission | Non-HFTD | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.2 | Protective device operation | Transmission | HFTD Tier 2 | No | 0 | 0 | 0 | 0 | # ignitions
| 7. Protective device operation | 7.a.t.3 | Protective device operation | Transmission | HFTD Tier 3 | No | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.0 | Vandalism/theft | Distribution | Non-HFTD | Yes | 1 | 2 | 6 | 6 | # ignitions
| 8. Vandalism/theft | 8.a.d.2 | Vandalism/theft | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.d.3 | Vandalism/theft | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.0 | Vandalism/theft | Transmission | Non-HFTD | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.2 | Vandalism/theft | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 8. Vandalism/theft | 8.a.t.3 | Vandalism/theft | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.0 | Lightning | Distribution | Non-HFTD | Yes | 0 | 0 | 1.5 | 1.5 | # ignitions
| 9. Lightning | 9.a.d.2 | Lightning | Distribution | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.d.3 | Lightning | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.0 | Lightning | Transmission | Non-HFTD | Yes | 0 | 2 | 1.5 | 1.5 | # ignitions
| 9. Lightning | 9.a.t.2 | Lightning | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 9. Lightning | 9.a.t.3 | Lightning | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.0 | Unknown | Distribution | Non-HFTD | Yes | 1 | 0 | 7.5 | 7.5 | # ignitions
| 10. Unknown | 10.a.d.2 | Unknown | Distribution | HFTD Tier 2 | Yes | 1 | 0.9821 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.d.3 | Unknown | Distribution | HFTD Tier 3 | Yes | 0 | 0 | 1 | 1 | # ignitions
| 10. Unknown | 10.a.t.0 | Unknown | Transmission | Non-HFTD | Yes | 0 | 0 | 0.5 | 0.5 | # ignitions
| 10. Unknown | 10.a.t.2 | Unknown | Transmission | HFTD Tier 2 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 10. Unknown | 10.a.t.3 | Unknown | Transmission | HFTD Tier 3 | Yes | 0 | 0 | 0 | 0 | # ignitions
| 11. Other | 11.a.d.0 | Other | Distribution | Non-HFTD | Yes | 0 | 28 | 14 | 14 | # ignitions
| 11. Other | 11.a.d.2 | Other | Distribution | HFTD Tier 2 | Yes | 0 | 1.9642 | 2 | 2 | # ignitions
| 11. Other | 11.a.d.3 | Other | Distribution | HFTD Tier 3 | Yes | 0 | 0.9821 | 1 | 1 | # ignitions
| 11. Other | 11.a.t.0 | Other | Transmission | Non-HFTD | Yes | 0 | 1 | 0.5 | 0.5 | # ignitions
| 11. Other | 11.a.t.2 | Other | Transmission | HFTD Tier 2 | Yes | 0 | 1 | 1 | 1 | # ignitions
| 11. Other | 11.a.t.3 | Other | Transmission | HFTD Tier 3 | Yes | 0 | 1 | 0 | 0 | # ignitions

## Table 7
| Utility | PG&E
| Table No. | 7
| Date Modified | 2025-02-03
[7 empty] | Actual | Projected
| Table 7: State of service territory and utility equipment | [5 empty] | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 4627.6352 | 4626.8062 | 4626.8062 | 4626.8062 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 9512.4855 | 9427.7867 | 9427.7867 | 9427.7867 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 6960.9373 | 6964.8843 | 6964.2888 | 6964.2649 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 28500.2013 | 28918.0957 | 28916.5517 | 28916.5838 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 423.5603 | 417.2495 | 414.7901 | 412.4651 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 5216.0764 | 4850.496 | 4850.496 | 4850.496 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 684.6329 | 676.2417 | 672.0564 | 672.0021 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 115.2903 | 111.8676 | 110.7105 | 110.2423 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 8457.7538 | 8542.8162 | 8479.2806 | 8433.5489 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 5343.8658 | 5382.2062 | 5373.0803 | 5371.2366 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 823.2718 | 791.5735 | 788.2493 | 771.2046 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 2346.4734 | 2354.5008 | 2343.5322 | 2324.9942 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 260.6652 | 267.8224 | 265.3791 | 260.6636 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 34.1546 | 33.3088 | 31.6778 | 31.6566 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 4095.0395 | 4128.5518 | 4067.9847 | 3924.0275 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 1678.6337 | 1694.6322 | 1671.444 | 1646.7885 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 343.7146 | 329.315 | 329.0328 | 326.7596 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 341.8437 | 342.0181 | 327.0256 | 324.6457 | Circuit miles | For 2023-2025 projected data, PG&E reduced the OH Circuit Miles based on the GH-04 target UG circuit miles to be installed. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. The reduction in OH miles incorporates the estimated conversion factor of 1.25 UG installed miles for each 1.0 OH removed mile. This reduction does not consider changes to OH Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 1. Overhead circuit miles | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 574.3635 | 588.3099 | 577.5943 | 577.5943 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 1604.3793 | 1594.5712 | 1610.296 | 1610.296 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 875.423 | 882.4176 | 884.0741 | 884.0741 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 7747.3875 | 7952.5809 | 7812.6742 | 7812.6742 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 47.3271 | 45.8319 | 47.4682 | 47.4682 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 1580.6756 | 1541.0439 | 1591.7092 | 1591.7092 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 100.6399 | 99.8541 | 101.2669 | 101.2669 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 116.2407 | 119.926 | 118.0885 | 118.0885 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 851.8958 | 862.0742 | 857.3767 | 857.3767 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 2054.2698 | 2067.8761 | 2066.4436 | 2066.4436 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 67.1669 | 72.8263 | 67.1932 | 67.1932 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 958.3237 | 996.3023 | 958.4114 | 958.4114 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 35.002 | 35.0025 | 35.0025 | 35.0025 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 23.1582 | 23.1582 | 23.1582 | 23.1582 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 300.9987 | 305.6539 | 300.9962 | 300.9962 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 753.7378 | 757.9541 | 753.7425 | 753.7425 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 27.054 | 27.036 | 27.0372 | 27.0372 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 1. Overhead circuit miles | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 133.1446 | 138.4021 | 133.1418 | 133.1418 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
x | 2. Underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 6498.8749 | 6476.1865 | 6476.1865 | 6476.1865 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the GH-04 target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 12389.5336 | 12097.9196 | 12097.9196 | 12097.9196 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 2889.5433 | 2804.774 | 2805.5185 | 2805.5483 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 3543.241 | 3400.5188 | 3402.4488 | 3402.4088 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 59.8611 | 62.0248 | 65.0991 | 68.0053 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 162.7255 | 166.3555 | 166.3555 | 166.3555 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 352.7308 | 340.6206 | 345.8523 | 345.9201 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 51.3205 | 49.4138 | 50.8602 | 51.4454 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 1254.406 | 1137.3278 | 1216.7473 | 1273.912 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 535.9229 | 470.5939 | 482.0013 | 484.306 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 85.0558 | 71.1856 | 75.3408 | 96.6467 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 211.1209 | 189.4792 | 203.1899 | 226.3625 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 112.1369 | 119.9679 | 123.022 | 128.9164 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 7.2808 | 7.7861 | 9.8249 | 9.8513 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 657.6682 | 562.6023 | 638.3111 | 818.2576 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 206.7629 | 188.8152 | 217.8004 | 248.6198 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 31.3538 | 20.6153 | 20.968 | 23.8095 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 47.4201 | 33.607 | 52.3476 | 55.3226 | Circuit miles | For 2023-2025 projected data, PG&E increased the UG Circuit Miles based on the target UG circuit miles. 2023 projected data is based on the 1/3/23 GH-04 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024-2025 projected data is based on the 6/26/24 GH-04 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24.This increase does not consider changes to UG Circuit Miles resulting from work outside of WMP initiative GH-04 (e.g. new business, work requested by others, capacity projects, etc.).
| 2. Underground circuit miles | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 23.521 | 10.8746 | 23.521 | 23.521 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 100.4945 | 36.3202 | 100.4948 | 100.4948 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 10.8743 | 23.3964 | 10.8746 | 10.8746 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 36.3053 | 99.8783 | 36.3053 | 36.3053 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 1.6534 | 1.1211 | 1.6534 | 1.6534 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0.14894 | 7.8594 | 0.14894 | 0.14894 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 1.1211 | 1.6534 | 1.1211 | 1.1211 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 7.8692 | 0.14894 | 7.8692 | 7.8692 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0.58353 | 0.58353 | 0.58353 | 0.58353 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0.35051 | 0.35051 | 0.35051 | 0.35051 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 2. Underground circuit miles | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | 13127 | 15539 | 13054 | 13054 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 30667 | 37488 | 30630 | 30630 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | 6502 | 7423 | 6249 | 6249 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 8474 | 12596 | 8494 | 8494 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 231 | 241 | 202 | 202 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 679 | 796 | 635 | 635 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 988 | 1141 | 1055 | 1055 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 180 | 221 | 177 | 177 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 3018 | 3578 | 3232 | 3232 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 1434 | 1690 | 1545 | 1545 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 314 | 352 | 334 | 334 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 411 | 473 | 472 | 472 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 361 | 426 | 371 | 371 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 50 | 56 | 54 | 54 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 1675 | 1960 | 1760 | 1760 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 592 | 697 | 649 | 649 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 159 | 213 | 160 | 160 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 3. Critical facilities | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 115 | 110 | 110 | 110 | Number of critical facilities | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 1240123 | 1228424 | 1232262 | 1232262 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 2598093 | 2546192 | 2576414 | 2576414 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 411369 | 403265 | 407421 | 407421 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 321627 | 312685 | 313217 | 313217 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 10100 | 10408 | 10007 | 10007 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 12808 | 10820 | 12716 | 12716 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 69605 | 72042 | 69398 | 69398 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 3751 | 3444 | 3749 | 3749 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 190988 | 195912 | 190956 | 190956 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 32715 | 27026 | 32420 | 32420 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 16457 | 17101 | 16387 | 16387 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 10266 | 8508 | 10261 | 10261 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 27309 | 27234 | 27202 | 27202 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 1803 | 1868 | 1801 | 1801 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 104584 | 105782 | 103802 | 103802 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 11426 | 9687 | 11406 | 11406 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 9131 | 9558 | 9107 | 9107 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 4. Residential customers | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 2553 | 1602 | 2553 | 2553 | Number of residential customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.0.a.i | N/A | Non-HFTD | Urban | WUI | 98101 | 107089 | 97669 | 97669 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 307607 | 322682 | 306004 | 306004 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.0.b.i | N/A | Non-HFTD | Rural | WUI | 53802 | 60055 | 53563 | 53563 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 156200 | 165601 | 154963 | 154963 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 1822 | 1990 | 1804 | 1804 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 13390 | 12653 | 13199 | 13199 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 3258 | 3952 | 3237 | 3237 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 771 | 750 | 753 | 753 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 17969 | 19648 | 18002 | 18002 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 10870 | 10370 | 10835 | 10835 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 1682 | 1921 | 1685 | 1685 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 3366 | 3174 | 3343 | 3343 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 1296 | 1717 | 1287 | 1287 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 175 | 200 | 175 | 175 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 7875 | 8774 | 7871 | 7871 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 3346 | 3252 | 3343 | 3343 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 678 | 786 | 676 | 676 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 5. Commercial customers | 5.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 564 | 503 | 565 | 565 | Number of commercial customers | 2024 - 2025 projected value is the same as Q4 2023.
| 6. AFN customers | 6.0.a.i | N/A | Non-HFTD | Urban | WUI | 334709 | 342839 | 291150 | 291150 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 861178 | 868502 | 739323 | 739323 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.b.i | N/A | Non-HFTD | Rural | WUI | 113088 | 113761 | 98813 | 98813 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 118389 | 119491 | 99380 | 99380 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 2938 | 3083 | 2632 | 2632 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 3901 | 3324 | 3134 | 3134 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 12330 | 13473 | 11615 | 11615 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 658 | 634 | 537 | 537 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 54386 | 57174 | 47895 | 47895 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 8079 | 6113 | 5218 | 5218 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 4570 | 4747 | 4142 | 4142 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 2600 | 1995 | 1699 | 1699 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 4394 | 4563 | 3857 | 3857 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 343 | 399 | 330 | 330 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 28136 | 28288 | 24429 | 24429 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 2592 | 2002 | 1724 | 1724 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 1780 | 1906 | 1587 | 1587 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 6.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 617 | 348 | 300 | 300 | Number of customers belonging to access and functional needs populations | 2024 - 2025 projected value is the same as Q4 2023.
| 7. Substations | 7.0.a.i | N/A | Non-HFTD | Urban | WUI | 96 | 87 | 100 | 100 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 202 | 216 | 206 | 206 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.b.i | N/A | Non-HFTD | Rural | WUI | 59 | 67 | 68 | 68 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 286 | 305 | 301 | 301 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 6 | 4 | 6 | 6 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 61 | 61 | 61 | 61 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 14 | 11 | 12 | 12 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 4 | 5 | 4 | 4 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 41 | 34 | 36 | 36 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 69 | 65 | 65 | 65 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 14 | 17 | 14 | 14 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 49 | 52 | 52 | 52 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 23 | 18 | 22 | 22 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 22 | 28 | 23 | 23 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 5 | 4 | 5 | 5 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 7.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 19 | 17 | 16 | 16 | Number of substations | 2024 - 2025 projected value is the same as Q4 2023.
| 8. Weather stations | 8.0.a.i | N/A | Non-HFTD | Urban | WUI | 22 | 20 | 22 | 22 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 35 | 20 | 31 | 31 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.b.i | N/A | Non-HFTD | Rural | WUI | 73 | 61 | 72 | 72 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 187 | 150 | 178 | 178 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 8 | 10 | 8 | 8 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 70 | 53 | 63 | 63 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 9 | 9 | 9 | 9 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 7 | 7 | 7 | 7 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 189 | 182 | 188 | 188 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 381 | 355 | 369 | 369 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 34 | 33 | 34 | 34 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 240 | 221 | 232 | 232 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 9 | 7 | 8 | 8 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 5 | 5 | 5 | 5 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 106 | 115 | 107 | 107 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 158 | 138 | 152 | 152 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 15 | 12 | 15 | 15 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.
|  | 8.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 37 | 34 | 34 | 34 | Number of weather stations | 2024 - 2025 projected value is the same as Q4 2023.

## Table 8
| Utility | PG&E |  |  |  |  | Notes:
| Table No. | 8 |  |  |  |  | Transmission lines refer to all lines at or above 65kV, and distribution lines refer to all lines below 65kV. Report net additions using positive numbers and net removals and undergrounding using negative numbers for circuit miles and numbers of substations. Only report changes expected within the target year.
| Date Modified | 2025-02-03 |  |  |  |  | For example, if 20 net overhead circuit miles are planned for addition by 2023, with 15 being added by 2022 and 5 more added by 2023, then report “15” for 2022 and “5” for 2023. Do not report cumulative change across years. In this case, do not report “20” for 2023, but instead the number planned to be added for just that year, which is “5”.
[7 empty] | Actual | Projected
| Table 8: Location of utility equipment additions or removal | [5 empty] | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Planned net addition (or removal) - overhead circuit miles | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | -0.23776 | -1.7999 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | -0.93844 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | -0.34193 | -60.992 | -0.59558 | -0.055101 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | -5.2321 | -17.9376 | -1.544 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | -0.52904 | -4.1272 | -2.4594 | -2.4643 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0.8125 | -8.5642 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | -2.9478 | -7.0284 | -4.1853 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | -0.31645 | -6.6406 | -1.1571 | -0.45322 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | -20.3976 | -80.1994 | -63.5356 | -44.9203 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | -9.7825 | -28.8992 | -9.1259 | -1.7255 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | -3.4508 | -6.3142 | -3.3242 | -17.0966 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | -2.7448 | -49.5734 | -10.9686 | -18.3959 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | -1.8758 | -4.1528 | -2.4433 | -4.8538 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | -1.631 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | -24.8965 | -59.1051 | -60.567 | -144.8624 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | -6.5989 | -12.9045 | -23.1882 | -24.7178 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0.0165 | -0.074433 | -0.28221 | -2.2695 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | -3.5399 | -1.6873 | -14.9925 | -2.1856 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 1, which differs from how 2023 projected miles were previously derived. As a result, the 2024 & 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0.031632 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | -0.28055 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | -0.32237 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | -36.3699 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0.24238 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 6.9e-05 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | -0.044003 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0.017327 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
x |  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | -1e-06 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | -0.11679 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0.000344 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0.000292 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | -0.00048 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
x | 2. Planned net addition (or removal) - underground circuit miles | 2.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 8.93 | 1.7999 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 27.8463 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 13.0811 | 60.992 | 0.74447 | 0.068877 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 47.3461 | 17.9376 | 1.93 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 1.5347 | 4.1272 | 3.0742 | 3.0803 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 1.6951 | 8.5642 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 7.3043 | 7.0284 | 5.2317 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 0.38059 | 6.6406 | 1.4463 | 0.56652 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 36.6344 | 80.1994 | 79.4195 | 56.1503 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 12.2435 | 28.8992 | 11.4074 | 2.1568 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 5.702 | 6.3142 | 4.1553 | 21.3708 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 13.4952 | 49.5734 | 13.7107 | 22.9948 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 4.5866 | 4.1528 | 3.0542 | 6.0673 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 2.0388 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 38.6949 | 59.1051 | 75.7088 | 181.0781 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 9.4626 | 12.9045 | 28.9852 | 30.8973 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 1.7261 | 0.074433 | 0.35277 | 2.8369 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 13.1384 | 1.6873 | 18.7406 | 2.732 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. Projected values for 2024-2025 are based on the methodology described in Table 7 Metric Type 2, which differs from how 2023 projected miles were previously derived. As a result, the 2024 and 2025 projected values have been adjusted to compensate for the change in calculation.
|  | 2.t.0.a.i | Transmission | Non-HFTD | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.b.i | Transmission | Non-HFTD | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 2.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
| 3. Planned net addition (or removal) - Substations | 3.0.a.i | N/A | Non-HFTD | Urban | WUI | -1 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | -4 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI | -3 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | -10 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | -1 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023.
| 4. Planned net addition (or removal) - Weather stations | 4.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 1 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 1 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 4 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | -1 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 1 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.
|  | 4.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2024 is the variance between Q1 2024 and Q4 2023. PG&E's has reached its weather station goal of the installation of 1,300 by the end of 2021. For Weather Station "additional and removals for 2023 and beyond", "project prioritization and timing" have not been fully determined or mapped.

## Table 9
| Utility | PG&E
| Table No. | 9
| Date Modified | 2025-02-03
[7 empty] | Actual | Projected
| Table 9: Location of utility infrastructure upgrades | [5 empty] | Q4
| Metric type | # | Line Type | HFTD Tier | Area Type | WUI Status | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
x | 1. Number of overhead circuit miles planned for upgrade | 1.d.0.a.i | Distribution | Non-HFTD | Urban | WUI | 0 | 0 | 0 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.a.ii | Distribution | Non-HFTD | Urban | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.b.i | Distribution | Non-HFTD | Rural | WUI | 0.71818 | 0 | 0.03765 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.b.ii | Distribution | Non-HFTD | Rural | Non-WUI | 0.38769 | 0 | 0.84952 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.c.i | Distribution | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 3.2125 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.0.c.ii | Distribution | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.a.i | Distribution | HFTD Tier 2 | Urban | WUI | 6.5309 | 7.7891 | 7.0067 | 3.7356 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.a.ii | Distribution | HFTD Tier 2 | Urban | Non-WUI | 1.8006 | 4.3459 | 1.3792 | 0.7371 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.b.i | Distribution | HFTD Tier 2 | Rural | WUI | 166.5816 | 140.3187 | 132.0856 | 129.9411 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.b.ii | Distribution | HFTD Tier 2 | Rural | Non-WUI | 35.9663 | 75.8792 | 28.4566 | 54.5557 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.c.i | Distribution | HFTD Tier 2 | Highly rural | WUI | 5.6983 | 10.9162 | 4.2616 | 35.1987 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.2.c.ii | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | 23.2017 | 60.1443 | 16.8361 | 41.082 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.a.i | Distribution | HFTD Tier 3 | Urban | WUI | 0.045455 | 1.3737 | 0 | 4.3082 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.a.ii | Distribution | HFTD Tier 3 | Urban | Non-WUI | 2.8678 | 3.1656 | 2.5105 | 0 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.b.i | Distribution | HFTD Tier 3 | Rural | WUI | 48.0697 | 58.0958 | 41.7092 | 182.6442 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.b.ii | Distribution | HFTD Tier 3 | Rural | Non-WUI | 36.0081 | 35.5504 | 27.1501 | 55.426 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.c.i | Distribution | HFTD Tier 3 | Highly rural | WUI | 0.47064 | 0.29637 | 0.5286 | 2.8241 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.d.3.c.ii | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | 19.9384 | 22.1249 | 17.1887 | 6.335 | Circuit miles | 2023 projected data is based on the 1/3/23 GH-01 workplan aligned with the base WMP filing and is the same as QDR Q4 2023. 2024 projected data is based on the 6/26/24 GH-01 workplan to align with the 2024 Change Order. 2025 projected data is based on the 1/13/25 GH-01 workplan to align with the 2025 WMP Update approved on 11/19/24. Projects with miles reported in Non-HFTD areas were selected because they are within the Tier 1 Buffer Zone or PG&E’s High Fire Risk Area (HFRA).
|  | 1.t.0.a.i | Transmission | Non-HFTD | Urban | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.a.ii | Transmission | Non-HFTD | Urban | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.b.i | Transmission | Non-HFTD | Rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.b.ii | Transmission | Non-HFTD | Rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.c.i | Transmission | Non-HFTD | Highly rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.0.c.ii | Transmission | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.a.i | Transmission | HFTD Tier 2 | Urban | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.a.ii | Transmission | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.b.i | Transmission | HFTD Tier 2 | Rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.b.ii | Transmission | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.c.i | Transmission | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.2.c.ii | Transmission | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.a.i | Transmission | HFTD Tier 3 | Urban | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.a.ii | Transmission | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.b.i | Transmission | HFTD Tier 3 | Rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.b.ii | Transmission | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.c.i | Transmission | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
|  | 1.t.3.c.ii | Transmission | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Circuit miles |  | PG&E does not have an equivalent "system hardening" program for transmission conductor, but PG&E is planning to replace or remove 43 HFTD miles in 2023, and 5 HFTD miles in 2025. The preliminarily planned jobs have not been mapped in order to break the data down for this table.
x | 2. Number of substations planned for upgrades | 2.0.a.i | N/A | Non-HFTD | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI | 1 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.b.i | N/A | Non-HFTD | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI | 1 | 1 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.c.i | N/A | Non-HFTD | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.a.i | N/A | HFTD Tier 2 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.b.i | N/A | HFTD Tier 2 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.a.i | N/A | HFTD Tier 3 | Urban | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.b.i | N/A | HFTD Tier 3 | Rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
|  | 2.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI | 0 | 0 | 0 | 0 | Number of substations | PG&E is in the process of refining the substation upgrade plan for 2024 - 2025 and will provide any updates in future submissions.
| 3. Number of weather stations planned for upgrades | 3.0.a.i | N/A | Non-HFTD | Urban | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.a.ii | N/A | Non-HFTD | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.b.i | N/A | Non-HFTD | Rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.b.ii | N/A | Non-HFTD | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.c.i | N/A | Non-HFTD | Highly rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.0.c.ii | N/A | Non-HFTD | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.a.i | N/A | HFTD Tier 2 | Urban | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.a.ii | N/A | HFTD Tier 2 | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.b.i | N/A | HFTD Tier 2 | Rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.b.ii | N/A | HFTD Tier 2 | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.c.i | N/A | HFTD Tier 2 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.2.c.ii | N/A | HFTD Tier 2 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.a.i | N/A | HFTD Tier 3 | Urban | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.a.ii | N/A | HFTD Tier 3 | Urban | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.b.i | N/A | HFTD Tier 3 | Rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.b.ii | N/A | HFTD Tier 3 | Rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.c.i | N/A | HFTD Tier 3 | Highly rural | WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.
|  | 3.3.c.ii | N/A | HFTD Tier 3 | Highly rural | Non-WUI |  |  |  |  | Number of weather stations |  | PG&E plans to do some power system only upgrades which does not improve or modify the reporting capabilities on some weather stations. These projects have not been mapped as upgrades are implemented as funding is available. If we have any planned upgrades, we'll provide it in the future quarterly updates.

## Table 10
Utility | PG&E |  | Notes:
Table No. | 10 |  | "PSPS" = Public Safety Power Shutoff
Date Modified | 2025-02-03 |  | In future submissions update planned upgrade numbers with actuals
|  |  |  | Actual | Projected
Table 10: Recent use of PSPS and other PSPS metrics |  |  |  | Q4
Metric type | # | Wind Warning Status | Metric name | 2024 | 2023 | 2024 | 2025 | Unit(s) | Comments | Blank Meaning
1. Recent use of PSPS and fast-trip | 1.a. | RFW only | Frequency of PSPS events (total) | 1 | 2 | 2 | 2 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW only | Frequency of PSPS events (total) | 0 | 0 | 0 | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW & RFW | Frequency of PSPS events (total) | 2 | 1.8 | 1.8 | 1.8 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | All (regardless of RFW/HWW status) | Frequency of PSPS events (total) | 4 | 3.8 | 3.8 | 3.8 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 1.b. | RFW only | Scope of PSPS events (total) | 97 | 134.4 | 134.4 | 134.4 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW only | Scope of PSPS events (total) | 0 | 0 | 0 | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | HWW & RFW | Scope of PSPS events (total) | 198 | 324.6 | 324.6 | 324.6 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
|  | All (regardless of RFW/HWW status) | Scope of PSPS events (total) | 864 | 459 | 459 | 459 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 1.c. | RFW only | Duration of PSPS events (total) | 724595 | 2795135.801 | 2763550.7661 | 2724861.055 | Customer hours per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | HWW only | Duration of PSPS events (total) | 0 | 0 | 0 | 0 | Customer hours per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | HWW & RFW | Duration of PSPS events (total) | 752610 | 9526845.295 | 9419171.854 | 9287303.448 | Customer hours per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
|  | All (regardless of RFW/HWW status) | Duration of PSPS events (total) | 1563698 | 12321981.096 | 12182722.6201 | 12012164.503 | Customer hours per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Assumes 11 hours of non-weather outage duration, comprised of 1 hour of switching time prior to weather start and 10 hours of patrol and restoration time after weather All Clear. Total durations decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
| 1.d. | RFW only | Frequency of fast-trip events (total) | 137 | 37.6 | 36.8 | 36 | Number of events | These forecasts are based on an estimated annual decrease of 2%.
|  | HWW only | Frequency of fast-trip events (total) | 0 | 0 | 0 | 0 | Number of events | These forecasts are based on an estimated annual decrease of 2%.
|  | HWW & RFW | Frequency of fast-trip events (total) | 0 | 0 | 0 | 0 | Number of events | These forecasts are based on an estimated annual decrease of 2%.
|  | None | Frequency of fast-trip events (total) | 660 | 2312.4 | 2263.2 | 2214 | Number of events | These forecasts are based on an estimated annual decrease of 2%.
| 1.e | RFW only | Circuit mile days with fast-trip settings enabled (total) | 517007 | 0 | 0 | 0 | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; EPSS does not have enough data for a 3-year historical average
|  | HWW only | Circuit mile days with fast-trip settings enabled (total) | 0 | 0 | 0 | 0 | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; EPSS does not have enough data for a 3-year historical average
|  | HWW & RFW | Circuit mile days with fast-trip settings enabled (total) | 0 | 0 | 0 | 0 | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; EPSS does not have enough data for a 3-year historical average
|  | None | Circuit mile days with fast-trip settings enabled (total) | 1417207.23 | 0 | 0 | 0 | Circuit mile days | Meteorological technology to forecast more than 1-2 weeks into the future still does not exist; EPSS does not have enough data for a 3-year historical average
2. Customer hours of PSPS and other outages | 2.a. | N/A | Customer hours of planned outages including PSPS (total) | 2879851.2667 | 11265868.55 | 11265868.55 | 11265868.55 | Total customer hours of planned outages per year | Projected values are based on 3-year historical average.
| 2.b. | N/A | Customer hours of unplanned outages, not including PSPS or fast-trip (total) | 7374134.3833 | 33804724.6167 | 33804724.6167 | 33804724.6167 | Total customer hours of unplanned outages, not including PSPS or fast-trip, per year | Projected values are based on 3-year historical average.
| 2.c. | N/A | Customer hours of unplanned outages resulting from fast-trip | 1608125.25 | 0 | 0 | 0 | Total customer hours of outages due to fast-trip per year | Projected values are based on the average of the last 2 years.
| 2.d. | N/A | System Average Interruption Duration Index (SAIDI) (including PSPS) | 122.7 | 476.9667 | 521.7 | 521.7 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Projected values are based on the average of the last 2 years. Data is reported in minutes. Projected Values have been converted to minutes to keep dataset aligned.
| 2.e. | N/A | System Average Interruption Duration Index (SAIDI) (excluding PSPS) | 106.4 | 387.4667 | 521.25 | 521.25 | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Projected values are based on the average of the last 2 years. Data is reported in minutes. Projected values have been converted to minutes to keep dataset aligned.
| 2.f. | N/A | System Average Interruption Frequency Index (SAIFI) (including PSPS) | 0.576 | 1.7237 | 1.507 | 1.507 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Projected values are based on the average of the last 2 years.
| 2.g. | N/A | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) | 0.569 | 1.678 | 1.5065 | 1.5065 | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Projected values are based on the average of the last 2 years.
3. Critical infrastructure impacted by PSPS | 3.a. | N/A | Critical infrastructure impacted by PSPS | 48826 | 231908.4893 | 229287.7073 | 226077.6795 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year | Projected values are based on a 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
4. Community outreach of PSPS metrics | 4.a. | N/A | # of customers impacted by PSPS | 48465 | 317151.1924 | 313527.2054 | 309137.8245 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | Projected values are based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Customer counts decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
4. Community outreach of PSPS metrics | 4.b. | N/A | # of medical baseline customers impacted by PSPS | 3291 | 24586.4934 | 24307.802 | 23967.4928 | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | Projected values are based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Customer counts decrease each year 2023-2025 due to additional mitigations (MSO Device Replacements and Undergrounding) planned for implementation in each of these years.
4. Community outreach of PSPS metrics | 4.c. | N/A | # of customers notified prior to initiation of PSPS event | 72293 | 456339.1389 | 451124.695 | 444808.9492 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | Projected values are larger than the number of customers impacted (4a), because it includes additional customers who were notified but not de-energized.
4. Community outreach of PSPS metrics | 4.d. | N/A | # of medical baseline customers notified prior to initiation of PSPS event | 4514 | 35054.0358 | 34656.6933 | 34171.4996 | # of customers notified of PSPS event prior to initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer) | Projected values are larger than the number of Medical Baseline customers impacted (4b), because it includes additional customers who were notified but not de-energized.
4. Community outreach of PSPS metrics | 4.e. | N/A | # of customers notified prior to a PSPS event impacting them | 48153 | 317151.1924 | 313527.2054 | 309137.8245 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
4. Community outreach of PSPS metrics | 4.f. | N/A | # of medical baseline customers notified prior to a PSPS event impacting them | 3271 | 24586.4934 | 24307.802 | 23967.4928 | # of customers impacted customers who were notified prior to PSPS initiation (if multiple PSPS events impact the same customer, count each event in which customer was notified as a separate customer)
5. Other PSPS metrics | 5.a. | N/A | Number of PSPS events in which a notification was sent but no de-energization occurred | 0 | 1 | 1 | 1 | Number of events
| 5.b. | N/A | Average number of customers located on de-energized circuit | 1961 | 1808.485 | 1808.485 | 1808.485 | Number of customers | Projected value was calculated by summing the total active customers on de-energized circuits for all events in a given quarter, divided by the number of de-energized circuit-events in the same quarter. The list of impacted circuits is based on 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022.
| 5.c. | N/A | Customer hours of PSPS per RFW OH circuit mile day | 8.86 | 25.1326 | 24.8486 | 24.5007 | =1.c. / RFW OH circuit mile days in time period | Projected values are based on 5-year historical average.
|  | N/A | Customer hours of PSPS per HWW OH circuit mile day | 332 | 444.8505 | 439.823 | 433.6655 | =1.c. / HWW OH circuit mile days in time period | Projected values are based on 5-year historical average.
|  | N/A | Customer hours of PSPS per high FPIOH circuit mile day | 2.23 | 3.2682 | 3.2312 | 3.186 | =1.c. / FPI OH circuit mile days in time period | Projected values are based on 5-year historical average.
| 5.d. | N/A | Median time between de-energization, due to PSPS, and inspection of a circuit segment | 28 | 29 | 29 | 29 | Time between de-energization and inspection on a circuit-segment basis in hours | Projected values are calculated based on the time between the start of de-energization due to PSPS, and the start of inspection (defined as the All Clear or Weather End time). Durations are based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Circuit segments are defined based on the device used to de-energize the circuit segment, not based on further sectionalization performed during the restoration process. If a circuit segment has multiple outage start times or All Clear time, the duration for that circuit segment is calculated as the max duration among the customers on that circuit segment.
| 5.e. | N/A | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment | 44 | 46 | 46 | 46 | Time between de-energization and inspection on a circuit-segment basis in hours | Projected values are calculated based on the time between the start of de-energization due to PSPS, and the start of inspection (defined as the All Clear or Weather End time). Durations are based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. Circuit segments are defined based on the device used to de-energize the circuit segment, not based on further sectionalization performed during the restoration process. If a circuit segment has multiple outage start times or All Clear time, the duration for that circuit segment is calculated as the max duration among the customers on that circuit segment.
| 5.f. | N/A | Median time between de-energization, due to fast-trip, and inspection of a circuit segment | 0.5 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.g. | N/A | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment | 1.3 | 0 | 0 | 0 | Time between de-energization and inspection on a circuit-segment basis in hours
| 5.h. | N/A | Number of risk events occurring on a de-energized circuit | 15 | 225.0284 | 225.0284 | 225.0284 | Number of risk events | Projected risk events are based on the number of damages and hazards, as reported in post de-energization reports for past PSPS events. The list of events is based on the 5-year lookback analysis, which applies 2022 PSPS guidance and existing mitigations to the weather conditions seen in 2018-2022. For lookback events which do not align with a past PSPS event, the number of risk events is approximated using the number of sustained outages which occurred during the hypothetical lookback event scope and duration, filtered to only include the types of outages which would have resulted in a damage or hazard (as reported in post de-energization reports).

## Table 11
Utility | PG&E | Notes:
Table No. | 11 | Territory spend refers to the sum total of initiative spending across all areas, including HFTDs. HFTD spend refers to initiative spending applied to HFTDs, and is a subset of territory spend.
Date Modified | 2025-02-03 | CAPEX = Capital expenditure; OPEX = Operating expenditure.
|  | As data is submitted each reporting period, replace projections for the current reporting period with actuals. | [9 empty] | Actuals |  |  |  | Projected
The units for the spend data are thousands of dollars.
Table 11: Mitigation initiative financials | [11 empty] | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands) |  | CAPEX ($ thousands) |  | OPEX ($ thousands)
[12 empty] | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD | Territory | HFTD
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | Primary driver targeted | Secondary driver targeted | Year initiated | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Comments | 2024 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Blank Meaning
Community Outreach and Engagement | Best practice sharing with other utilities |  | N/A - Foundational |  | 2021 | PSPS OII | n/a | In compliance | Customer Care portion: PSPS OII |  |  | 0 | 0 | 2820 | 733 | 0 | 0 | 3496.1115 | 3496.1115 | 0 | 0 | 19394.0333 | 19394.0333 | 0 | 0 | 3709.0247 | 3709.0247
Community Outreach and Engagement | Collaboration on local wildfire mitigation planning |  | N/A - Foundational |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 0 | 0 | 9573.3873 | 2489.0807 | 0 | 0 | 11834.5776 | 11834.5776 | 0 | 0 | 12491.15 | 12491.15 | 0 | 0 | 12555.3034 | 12555.3034
Community Outreach and Engagement | Engagement with access and functional needs populations |  | N/A - Foundational |  | 2019 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3, GO 166 |  |  | 11170.1588 | 2904.2413 | 4657.0507 | 1210.8332 | 4062.5 | 4062.5 | 23346.5806 | 23346.5806 | 4028.6149 | 4028.6149 | 0 | 0 | 4184.375 | 4184.375 | 16012.978 | 16012.978
Community Outreach and Engagement | Public outreach and education awareness program | CO-01, CO-02, CO-04, CO-05 | N/A - Foundational |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 0 | 0 | 10433.0755 | 2712.5996 | 0 | 0 | 14931.7992 | 14931.7992 | 0 | 0 | 2149.8507 | 2149.8507 | 0 | 0 | 15841.1458 | 15841.1458
Emergency Preparedness | Customer support in wildfire and PSPS emergencies |  | All Consequences |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 2.2679 | 0.58965 | 5824.1657 | 1514.2831 | 187.5 | 187.5 | 14780.0164 | 14780.0164 | 85.8446 | 85.8446 | 9374.7469 | 9374.7469 | 198.9187 | 198.9187 | 15680.1194 | 15680.1194
Emergency Preparedness | Emergency preparedness plan | EP-01 | All Consequences |  | <2018 | 2023 GRC | n/a | In Compliance | GO 166; R.96-11-004; R.18-12-005 |  |  | 0 | 0 | 11024.5747 | 2866.3894 | 0 | 0 | 4119 | 4119 | 0 | 0 | 1980.966 | 1980.966 | 0 | 0 | 4369.8471 | 4369.8471
Emergency Preparedness | External collaboration and coordination | EP-02, EP-04, EP-06, EP-07, EP-08, EP-09 | All Consequences |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 0 | 0 | 13727.34 | 3569.1084 | 0 | 0 | 17043.1514 | 17043.1514 | 0 | 0 | 17951.9869 | 17951.9869 | 0 | 0 | 18081.0793 | 18081.0793
Emergency Preparedness | Preparedness and planning for service restoration |  | All Consequences |  | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 | refer to "Other - PSPS" section 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8700 | 8700 | 0 | 0 | 21148.596 | 21148.596 | 0 | 0 | 9229.83 | 9229.83
Emergency Preparedness | Public emergency communication strategy |  | All Consequences |  | 2018 | De-energization OIR – Phase 3 | n/a | In compliance | De-energization OIR – Phase 3 |  |  | 0 | 0 | 4007.6363 | 1041.9855 | 0 | 0 | 8109.3037 | 8109.3037 | 0 | 0 | 7124.6794 | 7124.6794 | 0 | 0 | 8603.1603 | 8603.1603
Grid Design, Operations, and Maintenance | Asset inpsections | AI-01, AI-02, AI-03, AI-04, AI-05, AI-06, AI-07, AI-08, AI-09, AI-10 | Equipment / facility failure |  | Distribution - 2016 (focused on WMP work) Transmission - 2019 (when WSIP program started in full) Substation - 2019 Wildfire Safety Plan | Distribution - 2023 GRC Transmission - TO Rate Case Substation - 2023 GRC | n/a | Distribution - In compliance with WMP and GO 165 regulations. (Missed Inspections will be tracked and reported to the CPUC) Transmission - Exceeding compliance Substation - Supplemental substation inspections are performed in addition to routine based substation inspections thus exceeding GO 174 compliance. | Distribution - GO 95; GO 165 Transmission - GO 165 IV; GO 95 Rules 18B and 31.2 Substation - GO 174 |  |  | 0 | 0 | 165196.9654 | 83970.9786 | 0 | 0 | 192119.7232 | 91921.1166 | 0 | 0 | 140669.967 | 61570.522 | 0 | 0 | 192064 | 89100.2641
Grid Design, Operations, and Maintenance | Asset managmenet and inspection enterprise system(s) | AI-11 | N/A - Foundational | N/A - Foundational | n/a | n/a | n/a | n/a | n/a | Wildfire technology costs are aggregated in financials for "Other - Wildfire" |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | Wildfire technology costs are aggregated in financials for "Other - Wildfire"
Grid Design, Operations, and Maintenance | Covered conductor installation | GH-01, GH-02, GH-03 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2018 | 2023 GRC | n/a | In Compliance | TD-9001M CH 15 “Fire Area Design Guidance” in addition to all relevant standards; All projects in HFTD/HFRA/Buffer Zones |  |  | 134200.8977 | 134200.8977 | 0 | 0 | 67504.2203 | 67504.2203 | 0 | 0 | 134201 | 134201 | 0 | 0 | 248940 | 248940 | 0 | 0
Grid Design, Operations, and Maintenance | Distribution pole replacements and reinforcements |  | Equipment / facility failure |  | <2018 | 2023 GRC | n/a | Not in compliance - due to the backlog of poles to be replaced and reinforced; but have plan to reduce backlog | GO 95 Rule 18 |  |  | 573290.7243 | 337717.1649 | 0 | 0 | 266489.6043 | 218852.845 | 5809.3098 | 0 | 433063.5536 | 251975.6874 | 0 | 0 | 930131.0725 | 853248.4118 | 6163.0968 | 0
Grid Design, Operations, and Maintenance | Emerging grid hardening technology installations and pilots |  | Equipment / facility failure |  | 2020 | 2022 WMP | n/a | not in compliance – we have non-exempt fuse equipment installed in fire areas. | Cal Fire Power Line Fire Prevention Field Guide establishes what is classified as non-exempt. TD-9100P-09 is the estimating standard for equipment in fire areas that references the above guide. |  |  | 227.9314 | 227.9314 | 730.0178 | 730.0178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Equipment inspections, maintenance, and repair |  | Equipment / facility failure |  | - Distribution < 2018 - Transmission < 2018 - Substation - Circuit Breaker Maintenance and Installation initiative was introduced in the 2020 WMP. | - Distribution and Substation: 2023 GRC - Transmission: TO Rate Case | n/a | - Distribution - Not currently in compliance. Refer to Section 8.1.7.2 and associated target in 8.1.1.X GM-10 for information regarding transmission maintenance notifications. - Transmission - Not currently in compliance. Refer to Section 8.1.7.1 and associated target in 8.1.1.2 GM-09 for information regarding transmission maintenance notifications. - Substation - In Compliance with regulations | - Distribution - GO 95 Rule 18 - Transmission - GO 95 Rule 18 - Substation – CPUC General Order 174; WECC-FAC-501 |  |  | 849496.9028 | 403898.8051 | 242486.1252 | 147739.0266 | 949901.4699 | 455039.1133 | 200297.1813 | 75645.0114 | 798766.5998 | 420176.8267 | 263401.9675 | 258525.4905 | 963794.9437 | 458020.1763 | 331254.6659 | 210742.703
Grid Design, Operations, and Maintenance | Equipment Settings to Reduce Wildfire Risk (Grid Ops) | GM-07 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC | n/a | n/a | n/a |  |  | 46533.1515 | 46533.1515 | 73225.3812 | 67272.4672 | 42108.7201 | 42108.7201 | 133428.7944 | 133428.7944 | 86716.0392 | 86716.0392 | 95319.9248 | 95319.9248 | 71879 | 71879 | 121892 | 121892
Grid Design, Operations, and Maintenance | Grid Response Procedures and Notifications (Grid Ops) |  | N/A - Foundational | N/A - Foundational | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | n/a - refer to other sections (8.1.8.1 - EPSS, 8.1.8.2 - Inspections) | Refer to 8.1.8.1 where EPSS financials are aggregated, also 8.1.8.2 Inspections |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | Refer to 8.1.8.1 where EPSS financials are aggregated, also 8.1.8.2 Inspections
Grid Design, Operations, and Maintenance | Installation of system automation equipment | GH-07 | N/A - Foundational | N/A - Foundational | 2019 | 2023 GRC | n/a | n/a | n/a |  |  | 3398.4201 | 3398.4201 | 0 | 0 | 12759.2 | 12759.2 | 0 | 0 | 6907.369 | 6907.369 | 0 | 0 | 0 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Line removals (in HFTD) |  | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution - 2019 Transmission < 2018 | Distribution - 2023 GRC Transmission - Res.SED 6 | n/a | Distribution - In Compliance Transmission - In Compliance | Distribution: De-energization and removal of OH conductor in HFTD/HFRA; Utility Procedure: TD-2459P-01 “Idle Facility Program” Transmission: GO-95 rule 31.6 |  |  | 21622.4838 | 21622.4838 | 0 | 0 | 64023.161 | 21568.0233 | 0 | 0 | 15700 | 15700 | 0 | 0 | 21238 | 21238 | 0 | 0
Grid Design, Operations, and Maintenance | Microgrids |  | Consequence - PSPS |  | 2019 - Dist. Micro, CMEP, MIP, Clean Substation 2019 - Remote Grid | - Dist. Micro, CMEP, MIP, Clean Substation: Microgrid OIR, 2020 GRC, EPIC 3 - Remote Grid: 2023 GRC | - CMEP, MIP, Clean Substation: MGMA/MGBA - Remote Grid: n/a | - Dist. Micro, CMEP, MIP, Clean Substation: In compliance - Remote Grid: in compliance with required filing (Resolution E-5132) | n/a |  |  | 3094.5316 | 2266.936 | 7017.2759 | 5324.4245 | 6060.2315 | 6060.2315 | 8338.2782 | 8338.2782 | 8629.732 | 8629.732 | 8966.0275 | 8966.0275 | 6008.213 | 6008.213 | 38299.4646 | 38299.4646
Grid Design, Operations, and Maintenance | Open work orders | GM-02, GM-03, GM-08 | Equipment / facility failure |  | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | refer to 8.1.4 | Most of the costs related to "Open Work Orders" are mapped to Maintenance section 8.1.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3180.6093 | 3180.6093 | 0 | 0 | 1489.431 | 1489.431 | 0 | 0 | 3374.3084 | 3374.3084
Grid Design, Operations, and Maintenance | Other grid topology improvements to minimize risk of ignitions | GH-08, GH-09, GH-10, GM-06 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2021 | 2023 GRC | n/a | Non-Exempt Expulsion Fuse Replacement portion - not in compliance, we have non-exempt fuse equipment installed in fire areas. | Non-Exempt Expulsion Fuse Replacement portion - Cal Fire Power Line Fire Prevention Field Guide establishes what is classified as non-exempt; TD-9100P-09 is the estimating standard for equipment in fire areas that references the above guide. |  |  | 43106.8621 | 43106.8621 | 0 | 0 | 40081.5684 | 40081.5684 | 0 | 0 | 31434.8513 | 31434.8513 | 0 | 0 | 21928.7323 | 21928.7323 | 0 | 0
Grid Design, Operations, and Maintenance | Other grid topology improvements to mitigate or reduce PSPS events |  | Consequence - PSPS |  | - Distribution - 2019 - Transmission - 2019/2020 | -Distribution - 2023 GRC - Transmission - TO Rate Case | n/a | - Distribution - In compliance per WMP commitments for replacements - Transmission - n/a | n/a |  |  | 0 | 0 | 0 | 0 | 1455.9022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1544.5667 | 0 | 0 | 0
Grid Design, Operations, and Maintenance | Other technologies and systems not listed above |  | Contact from object |  | Pertaining to Substation Animal Abatement: 2019 – Wildfire Safety Plan | Pertaining to Substation Animal Abatement: 2023 GRC | n/a | Pertaining to Substation Animal Abatement: Exceeds minimum substation maintenance and inspection requirements within GO 174 | Pertaining to Substation Animal Abatement: GO 174 |  |  | 6449.6891 | 2940.8499 | 4684.9424 | 1995.7247 | 0 | 0 | 1024.1647 | 764.1681 | 0 | 0 | 1054.8896 | 787.0931 | 0 | 0 | 1086.5363 | 810.7059
Grid Design, Operations, and Maintenance | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk (Grid Ops) |  | N/A - Foundational | N/A - Foundational | <2018 | 2022 WMP | n/a | In Compliance | 2021 California Code Public Resources Code - PRC, sections 4427, 4428, 4431 | General Operations |  | 224.028 | 58.2473 | 20667.55 | 5373.563 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | General Operations
Grid Design, Operations, and Maintenance | Quality assurance / quality control | GM-01, GM-09 | N/A - Foundational | N/A - Foundational | 2020 | 2023 GRC, 2022 WMP | n/a | In Compliance | GO 95 GO 128 GO 165 |  |  | 0 | 0 | 39486.3664 | 35690.3921 | 0 | 0 | 33808.8626 | 32977.9224 | 0 | 0 | 24119 | 24119 | 0 | 0 | 57475 | 57475
Grid Design, Operations, and Maintenance | Traditional overhead hardening | GH-05, GH-06, GH-11 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | Distribution - refer to Maintenance program in 8.1.4 Transmission before 2018 | Distribution - refer to Maintenance program in 8.1.4 Transmission - TO rate case | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution - refer to Maintenance program in 8.1.4 Transmission - n/a | Distribution costs covered in the Maintenance programs, under 8.1.4 |  | 4042.3191 | 4042.3191 | 0 | 0 | 19134.1732 | 19134.1732 | 0 | 0 | 4900.0001 | 4900.0001 | 0 | 0 | 66538 | 66538 | 0 | 0
Grid Design, Operations, and Maintenance | Transmission pole/tower replacements and reinforcements |  | Equipment / facility failure |  | <2018 | TO Rate Case | n/a | Refer to section 8.1.7.1 and associated target 8.1.1.2 GM-09 for information regarding transmission maintenance notifications. | GO 95 Rule 18 |  |  | 163814.3476 | 130677.1287 | 104042.1448 | 62655.3757 | 90847.6275 | 18447.657 | 91279.8781 | 8572.9218 | 72700 | 14762.5722 | 106659 | 10941.1162 | 96380.248 | 19571.1193 | 105326.0227 | 10804.3789
Grid Design, Operations, and Maintenance | Undergrounding of electric lines and/or equipment | GH-04 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC | n/a | In Compliance | UG Design and Construction Standards; All projects in HFTD/HFRA/Buffer Zones |  |  | 999783.17 | 978748.8232 | 0 | 0 | 1175307.5973 | 1146057.5973 | 0 | 0 | 999783 | 978749 | 0 | 0 | 1215322 | 1209322 | 0 | 0
Grid Design, Operations, and Maintenance | Workforce Planning |  | N/A - Foundational | N/A - Foundational | <2018 | 2023 GRC | n/a | n/a - support function | n/a - support function | General Operations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overview of the Service Territory | Environmental compliance and permitting |  | N/A - Foundational | N/A - Foundational | <2018 | 2023 GRC | n/a | In Compliance | n/a - governed by various state, federal, local legislation | General Operations - costs are allocated to projects across the company when mitigations happen; so costs are already embedded in various programs and MWCs/MATs |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | General Operations - costs are allocated to projects across the company when mitigations happen; so costs are already embedded in various programs and MWCs/MATs
Risk Methodology and Assessment | Risk Methodology and Assessment |  | N/A - Foundational | N/A - Foundational | 2019 | 2022 WMP | n/a | Risk models - in compliance | n/a |  |  | 8413.1728 | 2187.4249 | 0 | 0 | 10750 | 3325.6654 | 0 | 0 | 7320.602 | 2264.7324 | 0 | 0 | 11404.675 | 3528.1984 | 0 | 0
Situational Awareness and Forecasting | Environmental monitoring systems | SA-01, SA-07, SA-08, SA-12 | N/A - Foundational | N/A - Foundational | 2018 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 1939.0494 | 1939.0494 | 2579.2281 | 2579.2281 | 3286.1036 | 3286.1036 | 3126.5412 | 3126.5412 | 1494.9857 | 1494.9857 | 3528.0021 | 3528.0021 | 3486.2274 | 3486.2274 | 3316.9476 | 3316.9476
Situational Awareness and Forecasting | Fire potential index |  | N/A - Foundational | N/A - Foundational | 2015 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 0 | 0 | 109.6274 | 109.6274 | 0 | 0 | 150.4726 | 150.4726 | 0 | 0 | 172 | 172 | 0 | 0 | 159.6363 | 159.6363
Situational Awareness and Forecasting | Grid monitoring systems | SA-02, SA-03, SA-09, SA-10, SA-11 | Contact from object, Vegetation Contact, Contamination, Equipment / facility failure, Other, Unknown, Wire-to-wire contact, Vandalism / Theft, CC - Seismic Scenario |  | 2019 | 2023 GRC | n/a | n/a | GO 95 |  |  | 6918.7213 | 6918.7213 | 2091.6296 | 2091.6296 | 8398.159 | 8398.159 | 3329.768 | 3329.768 | 12462.9994 | 12462.9994 | 2288.9131 | 2288.9131 | 10394.8668 | 10394.8668 | 3532.5509 | 3532.5509
Situational Awareness and Forecasting | Ignition detection systems |  | N/A - Foundational | N/A - Foundational | 2017 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 0.00012 | 0.00012 | 23219.5947 | 11419.4232 | 0 | 0 | 15324.18 | 15324.18 | 0 | 0 | 18929.0996 | 18929.0996 | 0 | 0 | 16257.4226 | 16257.4226
Situational Awareness and Forecasting | Weather forecasting | SA-04, SA-05, SA-06 | N/A - Foundational | N/A - Foundational | 2014 | 2023 GRC | n/a | exceeding compliance with regulations | n/a |  |  | 2609.191 | 2609.191 | 2290.423 | 2290.423 | 0 | 0 | 1976.0114 | 1976.0114 | 0 | 0 | 171.996 | 171.996 | 0 | 0 | 2096.3505 | 2096.3505
Vegetation Management and Inspection | Clearance |  | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | refer to 8.2.3.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Emergency response vegetation management |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | Vegetation Management Priority Tag Procedure (TD-7102P-17); Preventing and Mitigating Fires While Performing PG&E Work (TD-1464S) |  |  | 0 | 0 | 3033.3215 | 1089.4362 | 0 | 0 | 13000 | 7577.6 | 0 | 0 | 3528 | 2056.4441 | 0 | 0 | 12072.0546 | 7036.7078
Vegetation Management and Inspection | Fall-in mitigation |  | Vegetation Contact |  | 2023 | n/a | n/a | n/a | GO 95 Rule 35; PRC 4292; PRC 4293 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 123997 | 123997 | 0 | 0 | 309050 | 306178.9561 | 0 | 0 | 72540 | 72540
Vegetation Management and Inspection | Fire-resillient right-of-ways |  | Vegetation Contact |  | <2018 | TO Rate Case | n/a | In compliance | PG&E 2016 Transmission Maintenance Agreement, approved and enforced by the California Independent System Operator (CAISO); ANSI A300 (Part 7)-2018 Integrated Vegetation Management; State, county, and city weed abatement ordinances |  |  | 0 | 0 | 9164.3933 | 4416.3211 | 0 | 0 | 15553.158 | 15553.158 | 0 | 0 | 14577 | 14577 | 0 | 0 | 12680 | 12680
Vegetation Management and Inspection | High-risk species |  | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | cost embedded in 8.2.2.1 and 8.2.2.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Open work orders | VM-09 | Vegetation Contact |  | n/a | n/a | n/a | n/a | n/a | cost embedded in 8.2.2.1 and 8.2.2.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489.431 | 1489.431 | 0 | 0 | 0 | 0
Vegetation Management and Inspection | Pole clearing | VM-02 | Vegetation Contact |  | <2018, 2021 | 2023 GRC, 2022 WMP | n/a | In compliance | PRC 4292; Vegetation Control Program Standard (TD-7112S); Vegetation Control Procedure (TD-7112P-01); Vegetation Management Utility Defensible Space Standard (TD-7109S) |  |  | 0 | 0 | 68512.3599 | 53929.184 | 0 | 0 | 31000 | 17049.5 | 0 | 0 | 28803 | 17574.7792 | 0 | 0 | 28787.2071 | 15832.4996
Vegetation Management and Inspection | Quality assurance / quality control | VM-08, VM-22 | N/A - Foundational | N/A - Foundational | <2018, 2019, 2021 | 2023 GRC, 2022 WMP | n/a | n/a | n/a |  |  | 0 | 0 | 53242.6456 | 42971.1978 | 0 | 0 | 49251 | 35187.2867 | 0 | 0 | 48654 | 48654 | 0 | 0 | 79481.4404 | 57427.5272
Vegetation Management and Inspection | Substation defensible space | VM-05, VM-06, VM-07 | Vegetation Contact |  | 2019 | 2023 GRC, 2022 WMP | n/a | In compliance | California PRC 4291; Substation Defensible Space Procedure LAND-4001P-01 |  |  | 0 | 0 | 4997.3752 | 4967.1713 | 0 | 0 | 4836.0004 | 4836.0004 | 0 | 0 | 5699.165 | 5699.165 | 0 | 0 | 3488 | 3488
Vegetation Management and Inspection | Vegetation management enterprise system | VM-12, VM-19, VM-20 | N/A - Foundational | N/A - Foundational | 2021 | 2023 GRC, 2022 WMP | n/a | n/a | n/a |  |  | 0 | 0 | 29511.717 | 7673.0464 | 0 | 0 | 38798 | 38798 | 0 | 0 | 27000 | 27000 | 0 | 0 | 16715.1525 | 16715.1525
Vegetation Management and Inspection | Wood and slash management |  | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | Best Management Practices (BMP) for Vegetation Management Activities (TD-7102P-01-JA01); Wood Management (TD-7102P-26) |  |  | 0 | 0 | 45596.1641 | 44023.0965 | 0 | 0 | 80400 | 79889.9338 | 0 | 0 | 79820.788 | 79022.5801 | 0 | 0 | 97690.7802 | 97071.0195
Vegetation Management and Inspection | Workforce Planning |  | N/A - Foundational | N/A - Foundational | n/a | n/a | n/a | n/a | n/a | cost embedded in 8.2.2.1 and 8.2.2.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wildfire Mitigation Strategy Development | Wildfire Mitigation Strategy Development |  | N/A - Foundational | All Drivers, All Consequences | n/a | n/a | n/a | n/a | n/a | cost partially in Section 6 - Risk Methodology and Assessment |  | 0 | 0 | 24023.5238 | 24023.5238 | [12 empty] | Cost partially in Section 6 - Risk Methodology and Assessment
Vegetation Management and Inspection | Vegetation Inspections - Distribution | VM-03, VM-04, VM-11, VM-16, VM-17, VM-18, VM-21 | Vegetation Contact |  | <2018 | 2023 GRC, 2022 WMP | n/a | In compliance | GO 95 Rule 35; PRC 4292; PRC 4293; Distribution Routine Patrol Procedure (TD-7102P-01); Distribution Vegetation Management Standard (DVMS) (TD-7102S); ESRB-4; GO 95 Rule 18; Vegetation Management Second Patrol Procedure (TD-7102P-23) |  |  | 0 | 0 | 1120994.9104 | 637789.385 | 0 | 0 | 795246 | 432220.4341 | 0 | 0 | 824370.7808 | 383183.3469 | 0 | 0 | 1134772 | 616754.6224
Vegetation Management and Inspection | Vegetation Inspections - Substation |  | Vegetation Contact |  | Substation - 2019 Wildfire Safety Plan | Substation - 2023 GRC | N/A | Substation – Defensible Space inspections and mitigation are performed in addition to routine and supplemental based substation inspections thus exceeding GO 174 compliance. | Substation - GO 174 |  |  | 0 | 0 | 980.8647 | 980.865 | 0 | 0 | 3356.6698 | 3356.6698 | 0 | 0 | 3457.3699 | 3457.3699 | 0 | 0 | 3561.091 | 3561.091
Vegetation Management and Inspection | Vegetation Inspections - Transmission | VM-01, VM-13, VM-14, VM-15 | Vegetation Contact |  | <2018 | TO Rate Case | n/a | In compliance | "NERC Standard FAC-003-04; GO 95 Rule 35; PRC 4292; PRC 4293; Transmission Non-Orchard Routine Patrol Procedure (TD-7103P-01)" |  |  | 0 | 0 | 35280.09 | 13691.8225 | 0 | 0 | 35443.09 | 35443.09 | 0 | 0 | 33492.839 | 33492.839 | 0 | 0 | 100319 | 100319
Other | Other - Wildfire |  | N/A - Foundational | N/A - Foundational | n/a - this section supports projects and programs | 2023 GRC for Wildfire Technology | n/a | n/a - this section are support projects and programs | n/a - this section are support projects and programs |  |  | 58512.9031 | 53129.2531 | 81675.0309 | 67748.383 | 109538.4214 | 109538.4214 | 115625.5227 | 115625.5227 | 39312.5758 | 35228.9665 | 138440.1748 | 132569.0677 | 124660.1233 | 124660.1233 | 121973.457 | 121973.457
PSPS | Other - PSPS | PS-01, PS-02, PS-05, PS-06, PS-07, PS-08, PS-09, PS-10, PS-11 | Consequence - PSPS | No other consequences reflected | 2018 – PSPS program initiated | 2023 GRC and 2022 WMCE | n/a | In compliance | R.18-12-005 |  |  | 2695.9433 | 700.9454 | 74719.8455 | 72962.7217 | 3963.1799 | 3963.1799 | 93112.0087 | 93112.0087 | 2827.2911 | 2827.2911 | 89183.3297 | 89183.3297 | 2953 | 2953 | 90070 | 90070

## Table 12
Utility | PG&E | Notes:
Table No. | 12
Date Modified | 2024-11-01
Table 12: WMP Midyear & End-of-Year Targets
Targets
[5 empty] | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year | YTD end of Q2 | YTD end of Q3 | End of year
WMPInitiativeCategory | WMPInitiativeActivity | UtilityInitiativeTrackingID | TargetType | Units | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | Method of Verification | Comments
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Ground | AI-02 | Quantitative | Transmission Structures | 18000 | 27000 | 27000 | 12000 | 20000 | 20000 | 13200 | 22000 | 22000 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Aerial | AI-04 | Quantitative | Transmission Structures | 17000 | 24000 | 24000 | 17000 | 20000 | 20000 | 13000 | 19000 | 19000 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspection Transmission – Climbing | AI-05 | Quantitative | Transmission Structures | 1200 | 1700 | 1700 | 900 | 1200 | 1200 | 900 | 1200 | 1200 | Completed work orders
Grid Design, Operations and Maintenance | Perform transmission infrared inspections | AI-06 | Quantitative | Miles | 1500 | 3000 | 4000 | 1500 | 3000 | 4000 | 1000 | 2500 | 3500 | Completed work orders
Grid Design, Operations and Maintenance | Detailed Inspections - Distribution | AI-07 | Quantitative | Distribution Poles | 30000 | 72532 | 234648 | 70000 | 150000 | 220016 | 109000 | 190000 | 244000 | Completed work orders
Grid Design, Operations and Maintenance | Supplemental Inspections - Substation Distribution | AI-08 | Quantitative | Distribution Substations | 46 | 52 | 52 | 68 | 76 | 76 | 71 | 78 | 78 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared
Grid Design, Operations and Maintenance | Supplemental Inspections - Substation Transmission | AI-09 | Quantitative | Transmission Substations | 31 | 34 | 34 | 33 | 36 | 36 | 38 | 41 | 41 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared
Grid Design, Operations and Maintenance | Supplemental Inspections - Hydroelectric Substations and Powerhouses | AI-10 | Quantitative | Hydroelectric Substations and Powerhouses | 41 | 41 | 41 | 45 | 46 | 46 | 37 | 40 | 40 | Pronto report listing out the three (3) inspection methods, ground, aerial, and infrared | Tule River sub sold to SCE
Community Outreach and Engagement | Community Engagement - Surveys | CO-02 | Quantitative | Surveys | 1 | 1 | 2 | 1 | 1 | 2 |  |  | 2 | Survey results and analyses.
Emergency Preparedness Plan | Emergency Planning | EP-06 | Quantitative | 1 CERP and 2 wildfire related annexes |  |  | 3 |  |  | 3 |  |  | 3 | 1 CERP and 2 wildfire related annexes
Grid Design, Operations and Maintenance | Covered conductor installation | GH-01 | Quantitative | Circuit Miles |  |  | 420 |  |  | 280 |  |  | 520 | Post-construction projects, use as-built job package and Fire Safe Spans Inspection report (QA report from I-Auditor). In-construction projects, use design construction drawing and Fire Safe Spans Inspection report (QA report from I-Auditor).
Grid Design, Operations and Maintenance | Undergrounding of electric lines and/or equipment | GH-04 | Quantitative | Circuit Miles |  |  | 350 |  |  | 250 |  |  | 330 | Post-construction projects, use as-built job package and Fire Safe Spans Inspection report (QA report from I-Auditor). In-construction projects, use design construction drawing and Fire Safe Spans Inspection report (QA report from I-Auditor).
Grid Design, Operations and Maintenance | Traditional overhead hardening - Transmission | GH-05 | Quantitative | Circuit Miles |  |  | 43 |  |  | 0 |  |  | 5 | As-built job package.
Grid Design, Operations and Maintenance | Traditional overhead hardening - Transmission | GH-06 | Quantitative | Transmission Lines |  |  | 20 |  |  | 22 |  |  | 25 | As-built job package
Grid Design, Operations and Maintenance | Installation of System Automation Equipment – Distribution EPSS Protective Devices | GH-07 | Quantitative | Distribution Sectionalizing Devices |  |  | 75 |  |  | N/A |  |  | N/A | Completed work orders
Grid Design, Operations and Maintenance | Other grid topology improvements to minimize risk of ignitions | GH-08 | Quantitative | Surge Arrestors |  |  | 663 |  |  | N/A |  |  | N/A | Completed work orders
Grid Design, Operations and Maintenance | Motor Switch Operator (MSO) Switch Replacement | GH-09 | Quantitative | MSOs replacements |  |  | 20 |  |  | 26 |  |  | N/A | As-built job package
Grid Design, Operations and Maintenance | Non-Exempt Expulsion Fuses | GH-10 | Quantitative | Fuses |  |  | 3000 |  |  | 3000 |  |  | 1400 | Completed work orders
Grid Design, Operations and Maintenance | System Hardening – Transmission Conductor Segment Replacement | GH-11 | Quantitative | Transmission Lines |  |  | N/A |  |  | N/A |  |  | 2 | As-built job package
Grid Design, Operations and Maintenance | Asset Inspections - Quality Assurance | GM-01 | Quantitative | Pass Rate |  |  | Transmission 90% Distribution 80% |  |  | Transmission 94% Distribution 90% |  |  | Transmission 95% Distribution 95% | Final reports and field guides for all audits.
Grid Design, Operations and Maintenance | Open Work Orders - Transmission | GM-02 | Quantitative | Transmission LC Tags |  |  | 16831 |  |  | N/A |  |  | N/A | Completed notifications
Grid Design, Operations and Maintenance | Open Work Orders - Distribution | GM-03 | Quantitative | Percent Risk Reduction |  |  | 48% |  |  | 68% |  |  | 77% | Completed notifications | Note Table 1 shows quarterly EC distribution tags.
Grid Design, Operations and Maintenance | Protective Equipment and Device Settings | GM-06 | Quantitative | Protective Device Controllers or Relays that are DCD capable |  |  | 500 |  |  | 400 |  |  | 250 | Report with the number of protective device controllers or relays that were DCD capable
Grid Design, Operations and Maintenance | Asset Inspections - Quality Control | GM-09 | Quantitative | Pass Rate |  |  | Transmission 90% Distribution 80% |  |  | Transmission 92% Distribution 88% |  |  | Transmission 95% Distribution 95% | Final reports and field guides for all audits.
Public Safety Power Shutuff | Customer Support in Wildfire and PSPS Emergencies | PS-06 | Quantitative | # of batteries |  |  | 4000 |  |  | 4000 |  |  | 3300 | Received waiver from customer. Contractor provided monthly log of deliveries with Account number.
Public Safety Power Shutuff | Performance Metrics Identified by the Electrical Corporation | PS-07 | Quantitative | # of Customer events |  |  | 15000 |  |  | 9980 |  |  | 13000 | Customer event reductions as measured by the static 5 year look back impacted by PSPS
Situational Awareness and Forecasting | Planned Improvements | SA-02 | Quantitative | Circuits |  |  | 40 |  |  | 40 |  |  | 40 | Completed job packages
Situational Awareness and Forecasting | Distribution Fault Anticipation (DFA) Installations | SA-10 | Quantitative | DFA Sensors |  |  | 5 |  |  | 15 |  |  | 15 | Report demonstrating the first communication between the sensor and the Headend software.
Situational Awareness and Forecasting | Early Fault Detection (EFD) Installations | SA-11 | Quantitative | EFD circuits |  |  | 2 |  |  | 2 |  |  | 4 | SAP report with notification completion date, circuit name, and location.
Vegetation Management and Inspection | LiDAR Routine Inspections - Transmission | VM-01 | Quantitative | Circuit Miles | 17500 | 17500 | 17500 | 16000 | 17000 | 17500 | 16000 | 17000 | 17500 | LiDAR Contractor Work Complete Attestation - (Vegetation Management Project Management Database). Data is uploaded to VMPI2 mobile device for Pre-Inspectors
Vegetation Management and Inspection | Pole Clearing Program | VM-02 | Quantitative | Distribution poles | 57750 | 77503 | 77503 | 47250 | 63000 | 63000 | 39000 | 52000 | 52000 | List of all poles in VM database as of October 1, 2022. (PCD2 App) All exceptions must be accordingly documented in the system of record
Vegetation Management and Inspection | Focused Tree Inspection (FTI) | VM-03 | Quantitative | Circuit Miles | 0 | 0 | 250 | 300 | 1050 | 1500 | 300 | 1050 | 1500 | QC Survey on all miles inspected
Vegetation Management and Inspection | Fall-in Mitigation | VM-04 | Quantitative | Trees Removed | 910 | 7310 | 15000 | 6200 | 14000 | 20000 | 5000 | 17500 | 25000 | Completed work orders
Vegetation Management and Inspection | Defensible Space Inspections - Distribution Substation | VM-05 | Quantitative | Distribution Substations | 130 | 131 | 131 | 130 | 131 | 131 | 124 | 131 | 131 | Preventative Notification numbers for each defensible space inspection
Vegetation Management and Inspection | Defensible Space Inspections - Transmission Substation | VM-06 | Quantitative | Transmission Substations | 55 | 55 | 55 | 55 | 55 | 55 | 49 | 54 | 55 | Preventative Notification numbers for each defensible space inspection | 2024 End of the year target is going to be 54. Please see Table 1 for additional details
Vegetation Management and Inspection | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | VM-07 | Quantitative | Hydroelectric Substations and Powerhouses | 61 | 61 | 61 | 61 | 61 | 61 | 48 | 59 | 61 | Preventative Notification numbers for each defensible space inspection | 2024 End of the year target is going to be 59. Please see Table 1 for additional details
Vegetation Management and Inspection | Quality Assurance / Quality Control | VM-08 | Quantitative | % Pass Rate |  |  | 95% |  |  | 95% |  |  | 95% | QV VM final reports
Vegetation Management and Inspection | Routine Ground - Transmission | VM-13 | Quantitative | Circuit Miles | 16396 | 17738 | 17740 | 9000 | 16000 | 17740 | 16396 | 17738 | 17740 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Transmission Second Patrol | VM-14 | Quantitative | Circuit Miles | 0 | 0 | 5625 | 0 | 0 | 5625 | 0 | 0 | 5625 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Integrated Vegetation Management - Transmission | VM-15 | Quantitative | Acres | 11151 | 11194 | 11194 | 2590 | 5690 | 6504 | 2500 | 5000 | 6504 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Distribution Routine Patrol | VM-16 | Quantitative | Circuit Miles | 41761 | 61806 | 79000 | 31460 | 51123 | 78650 | 31280 | 50830 | 78200 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Distribution Second Patrol | VM-17 | Quantitative | Circuit Miles | 18904 | 30952 | 43000 | 10274 | 16695 | 25685 | 10274 | 16695 | 25685 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | VM for Operational Mitigations (VMOM) | VM-18 | Quantitative | Trees | N/A | N/A | N/A | 3000 | 5000 | 6500 | 3000 | 5000 | 6500 | Report from VM database reflecting completed work.
Vegetation Management and Inspection | Vegetation Management - Quality Control | VM-22 | Quantitative | % Pass Rate |  |  | VM Distribution Routine 80% VM Transmission 88% VM Pole Clearing 80% |  |  | VM Distribution Routine 88% VM Transmission 92% VM Pole Clearing 88% |  |  | VM Distribution Routine 95% VM Transmission 95% VM Pole Clearing 95% | QC VM final reports

## Table 14
Utility | PG&E
Table No. | 14
Date Modified | 2023-03-01
Table 14: HFTD Area Risk Summary
*EC to add all other risk categories to right of last required category.
HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
Non-HFTD Distribution | 855.524 | 656.744 | 198.7799 | 284.7828 | 163.0337 | 42.0053 | 79.7438 | n/a | 4.75 | 2.3061 | n/a | n/a | n/a | 41.8484 | n/a | n/a
HFTD 2 Distribution | 24291.0179 | 22425.256 | 1865.7619 | 177.0372 | 74.7102 | 75.3981 | 26.9288 | n/a | 4.75 | 126.6698 | n/a | n/a | n/a | 392.792 | n/a | n/a
HFTD 3 Distribution | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a* | n/a*
Non-HFTD Transmission | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2
HFTD 2 Transmission | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2
HFTD 3 Transmission | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2 | Note 2
Comments for Table 14: The data presented in this table are based on the best knowledge that PG&E has as of January 31, 2023. As better data becomes available, this will be updated in the quarterly updates. Note 1: Ignition Likelihood Metric: Ignition likelihood scaled from WDRM v3 to historical CPUC reportable probabilities. Note 2: The WTRM currently does not output results in the categories defined in this table. While the WTRM is used to represent risk across PG&E's Transmission System, the WTRM is not currently calibrated with the WDRM and is not fit for use for comparison of risks across multiple domains. Note 3: PSPS Likelihood Metric: PSPS likelihood is aggregated at the number of annual PSPS events and is represented as the same value for both HFTD and non-HFTD. Note 4: PG&E's risk models does not uniquely differentiate HFTD Tier 2 vs Tier 3 in its results, as PG&E sees a wide range of risk consequence in Tier 2 and Tier3. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation. N/A*: Per note 4, PG&E has provided its data in HFTD 2 Distribution row but note that the results also include HFTD 3 Distribution. As such PG&E assesses each risk consequence at each pixel, regardless of the Tier 2 and Tier 3 designation.

## Table 15
Notes
Utility | PG&E | [11 empty] | 1) As described in Section 6.2, Burn Probability is a preliminary step in wildfire calculation, PG&E does not break this apart separately
Table No. | 15 | [11 empty] | 2) PG&E interprets this as Technosylva's Terrain Difficulty Index (TDI), but is not explicitly assigned to circuit segments in the current WDRM v4.
Date Modified | 2024-08-01 | [11 empty] | 3) PG&E interprets this as Technosylva's Risk and Associated Value Exposure (RAVE), but is not in the current WDRM v4 and PSPS.
4) ignition likelihood scaled from WDRM v4 to historical CPUC reportable probabilities
Table 15: Top Risk Circuit Scores | [12 empty] | 5) Circuit segment HFTD mileage only
*EC to add all other risk categories to right of last required category. | [12 empty] | 6) Scaled to match reported Ignition Risk, which is a calibrated WDRM v4 risk
Top- Risk Circuit/ Segment/ Span ID | Risk Granularity | Line Class | Circuit/ Segment/ Span Length (mi) | Inclusion Reason | HFTD Area | Overall Utility Risk | Ignition Risk | PSPS Risk | Ignition Likelihood | Equipment Likelihood of Ignition | Contact from Vegetation Likelihood of Ignition | Contact from Object Likelihood of Ignition | Burn Probability | PSPS Likelihood | Wildfire Consequence | Wildfire Hazard Intensity | Wildfire Exposure Potential | Wildfire Vulnerability | PSPS Consequence | PSPS Exposure Potential | Vulnerability of Community to PSPS
CLAYTON 2212681608 | Circuit Segment | Distribution | 33.2215 | Top 5% Risk | HFTD T2/T3 | 126.6481 | 125.1891 | 1.459 | 0.13611 | 0.063237 | 0.046244 | 0.026633 | n/a | 0.25 | 919.7399 | n/a | n/a | n/a | 5.8362 | n/a | n/a
BALCH NO 1 1101105414 | Circuit Segment | Distribution | 7.4477 | Top 5% Risk | HFTD T2/T3 | 123.7285 | 123.7147 | 0.013865 | 0.024374 | 0.0086115 | 0.0092063 | 0.0065563 | n/a | 0.083333 | 5075.6595 | n/a | n/a | n/a | 0.16639 | n/a | n/a
CLOVERDALE 1102672 | Circuit Segment | Distribution | 22.4533 | Top 5% Risk | HFTD T2/T3 | 107.8531 | 106.4287 | 1.4244 | 0.058839 | 0.018553 | 0.030624 | 0.0096617 | n/a | 1.1667 | 1808.8248 | n/a | n/a | n/a | 1.2209 | n/a | n/a
PLACERVILLE 21067522 | Circuit Segment | Distribution | 73.5317 | Top 5% Risk | HFTD T2/T3 | 98.3161 | 91.5169 | 6.7992 | 0.385 | 0.11568 | 0.2105 | 0.058814 | n/a | 0.58333 | 237.7084 | n/a | n/a | n/a | 11.6558 | n/a | n/a
MIDDLETOWN 1101644756 | Circuit Segment | Distribution | 15.2593 | Top 5% Risk | HFTD T2/T3 | 88.1484 | 87.9343 | 0.21407 | 0.077249 | 0.022512 | 0.045453 | 0.0092835 | n/a | 0.41667 | 1138.3262 | n/a | n/a | n/a | 0.51378 | n/a | n/a
PLACERVILLE 210611132 | Circuit Segment | Distribution | 44.4736 | Top 5% Risk | HFTD T2/T3 | 86.8938 | 84.1646 | 2.7293 | 0.18299 | 0.058076 | 0.093408 | 0.031511 | n/a | 0.58333 | 459.9283 | n/a | n/a | n/a | 4.6787 | n/a | n/a
STANISLAUS 1701CB | Circuit Segment | Distribution | 38.5242 | Top 5% Risk | HFTD T2/T3 | 85.4087 | 83.9752 | 1.4336 | 0.13461 | 0.052727 | 0.034377 | 0.04751 | n/a | 0.33333 | 623.821 | n/a | n/a | n/a | 4.3007 | n/a | n/a
ALLEGHANY 1102CB | Circuit Segment | Distribution | 18.792 | Top 5% Risk | HFTD T2/T3 | 83.3905 | 80.82 | 2.5705 | 0.079255 | 0.027332 | 0.041508 | 0.010416 | n/a | 0.91667 | 1019.7418 | n/a | n/a | n/a | 2.8042 | n/a | n/a
EL DORADO PH 210119752 | Circuit Segment | Distribution | 41.5804 | Top 5% Risk | HFTD T2/T3 | 83.0626 | 74.9057 | 8.1568 | 0.20347 | 0.062625 | 0.1064 | 0.034444 | n/a | 0.66667 | 368.1409 | n/a | n/a | n/a | 12.2353 | n/a | n/a
CALPINE 1144CB | Circuit Segment | Distribution | 26.7587 | Top 5% Risk | HFTD T2/T3 | 79.9057 | 79.6976 | 0.20809 | 0.048353 | 0.013749 | 0.016475 | 0.018129 | n/a | 1.25 | 1648.2473 | n/a | n/a | n/a | 0.16647 | n/a | n/a
MARIPOSA 210237282 | Circuit Segment | Distribution | 53.2532 | Top 5% Risk | HFTD T2/T3 | 78.126 | 78.126 | 0 | 0.20758 | 0.077918 | 0.083705 | 0.045953 | n/a | 0 | 376.3731 | n/a | n/a | n/a | 0 | n/a | n/a
CALAVERAS CEMENT 1101544800 | Circuit Segment | Distribution | 23.5406 | Top 5% Risk | HFTD T2/T3 | 77.3608 | 77.1388 | 0.22206 | 0.040149 | 0.020534 | 0.011907 | 0.0077075 | n/a | 0.16667 | 1921.3215 | n/a | n/a | n/a | 1.3323 | n/a | n/a
WEST POINT 11024788 | Circuit Segment | Distribution | 74.2727 | Top 5% Risk | HFTD T2/T3 | 76.7447 | 73.831 | 2.9137 | 0.16676 | 0.076021 | 0.062502 | 0.028239 | n/a | 0.58333 | 442.7331 | n/a | n/a | n/a | 4.9948 | n/a | n/a
COLUMBIA HILL 1101CB | Circuit Segment | Distribution | 47.9377 | Top 5% Risk | HFTD T2/T3 | 74.3016 | 68.5187 | 5.7829 | 0.16327 | 0.056241 | 0.084031 | 0.022996 | n/a | 0.83333 | 419.6701 | n/a | n/a | n/a | 6.9395 | n/a | n/a