## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | REPORTING QUARTER | QUANTITATIVE ACTUAL PROGRESS Q1 | QUANTITATIVE ACTUAL PROGRESS Q1-2 | QUANTITATIVE ACTUAL PROGRESS Q1-3 | QUANTITATIVE ACTUAL PROGRESS Q1-4 | QUALITATIVE ACTUAL PROGRESS Q1 | QUALITATIVE ACTUAL PROGRESS Q1-2 | QUALITATIVE ACTUAL PROGRESS Q1-3 | QUALITATIVE ACTUAL PROGRESS Q1-4 | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | PacifiCorp | 2025-07-07 | Program |  |  | Transmission Patrol inspections | Transmission Patrol Inspections | In accordance with GO 165, a simple visual inspection of applicable utility equipment and structures that is designed to identify obvious structural problems and hazards. | Grid Design, Operations, and Maintenance | Transmission Patrol inspections |  | 8.1.3.1 | AI-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Patrol inspections_AI-01_2024 | 165 | Equipment ignition likelihood | Yes | Inspection Count |  | 2025 | 1 | 2 | [7 empty] | In Progress
1010000001 | PacifiCorp | 2025-07-07 | Program |  |  | Distribution Patrol Inspections | Distribution Patrol Inspections | In accordance with GO 165, a simple visual inspection of applicable utility equipment and structures that is designed to identify obvious structural problems and hazards. | Grid Design, Operations, and Maintenance | Distribution Patrol Inspections |  | 8.1.3.1 | AI-02 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Patrol Inspections_AI-02_2024 | 165 | Equipment ignition likelihood | Yes | Inspection Count |  | 2025 | 1 | 16742 | [7 empty] | In Progress
1010000002 | PacifiCorp | 2025-07-07 | Program |  |  | Transmission Detail Inspections | Transmission Detail Inspections | In accordance with GO 165, an inspection where individual pieces of equipment and structures are carefully examined, visually and through use of routine diagnostic test, as appropriate, and (if practical and if useful information can be so gathered) opened, and the condition of each rated and recorded. | Grid Design, Operations, and Maintenance | Transmission Detail Inspections |  | 8.1.3.2 | AI-03 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Detail Inspections_AI-03_2024 | 166 | Equipment ignition likelihood | Yes | Inspection Count |  | 2025 | 1 | 1 | [7 empty] | In Progress
1010000003 | PacifiCorp | 2025-07-07 | Program |  |  | Distribution Detail Inspections | Distribution Detail Inspections | In accordance with GO 165, an inspection where individual pieces of equipment and structures are carefully examined, visually and through use of routine diagnostic test, as appropriate, and (if practical and if useful information can be so gathered) opened, and the condition of each rated and recorded. | Grid Design, Operations, and Maintenance | Distribution Detail Inspections |  | 8.1.3.2 | AI-04 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Detail Inspections_AI-04_2024 | 166 | Equipment ignition likelihood | Yes | Inspection Count |  | 2025 | 1 | 5497 | [7 empty] | In Progress
1010000004 | PacifiCorp | 2025-07-07 | Program |  |  | Transmission Intrusive Pole Inspections | Transmission Intrusive Pole Inspections - Transmission and Distribution | May include pole-sounding, inspection hole drilling and excavation tests, designed to identify decay, wear or woodpecker damage, assess the condition of wood poles and identify the need for any treatment, repair or replacement. | Grid Design, Operations, and Maintenance | Transmission Intrusive Pole Inspections |  | 8.1.3.3 | AI-05 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Intrusive Pole Inspections_AI-05_2024 | 168 | Equipment ignition likelihood | Yes | Inspection Count |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000005 | PacifiCorp | 2025-07-07 | Program |  |  | Distribution Intrusive Pole Inspections | Distribution Intrusive Pole Inspections - Transmission and Distribution | May include pole-sounding, inspection hole drilling and excavation tests, designed to identify decay, wear or woodpecker damage, assess the condition of wood poles and identify the need for any treatment, repair or replacement. | Grid Design, Operations, and Maintenance | Distribution Intrusive Pole Inspections |  | 8.1.3.3 | AI-06 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Intrusive Pole Inspections_AI-06_2024 | 168 | Equipment ignition likelihood | Yes | Inspection Count |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000006 | PacifiCorp | 2025-07-07 | Program |  |  | Enhanced (Infrared) Inspections in Transmission Lines | Enhanced (Infrared) Inspections in Transmission Lines | Proactive identification and prevention of equipment failures through infrared inspections during peak loading intervals. | Grid Design, Operations, and Maintenance | Enhanced (Infrared) Inspections in Transmission Lines |  | 8.1.3.6 | AI-07 | PacifiCorp_Grid Design, Operations, and Maintenance_Enhanced (Infrared) Inspections in Transmission Lines_AI-07_2024 | 172 | Equipment ignition likelihood | Yes | Line miles |  | 2025 | 1 | 124 | [7 empty] | In Progress
1010000007 | PacifiCorp | 2025-07-07 | Program |  |  | Enhanced (Infrared) Inspections in Distribution Lines | Enhanced (Infrared) Inspections in Distribution Lines | Proactive identification and prevention of equipment failures through infrared inspections during peak loading intervals. | Grid Design, Operations, and Maintenance | Enhanced (Infrared) Inspections in Distribution Lines |  | 8.1.3.5 | AI-08 | PacifiCorp_Grid Design, Operations, and Maintenance_Enhanced (Infrared) Inspections in Distribution Lines_AI-08_2024 | 171 | Equipment ignition likelihood | Yes | Line miles |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000008 | PacifiCorp | 2025-07-07 | Program |  |  | Substation Inspections | Substation Inspections | Maintain the integrity of Pacific Power’s power delivery system through a systematic program of inspections to identify and correct deficiencies before they cause an outage or create a safety hazard. | Grid Design, Operations, and Maintenance | Substation Inspections |  | 8.1.3.4 | AI-11 | PacifiCorp_Grid Design, Operations, and Maintenance_Substation Inspections_AI-11_2024 | 169 | Equipment ignition likelihood | Yes | Inspection Count |  | 2025 | 1 | 165 | [7 empty] | In Progress
1010000009 | PacifiCorp | 2025-07-07 | Program |  |  | QA/QC of Asset Inspections | QA/QC of Asset Inspections | Using a combination of process controls, software tools, company policy, and physical record checking to quickly identify inaccuracies for corrective action, evaluation, root cause analysis and system improvements. | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control |  | 8.1.6 | AI-12 | PacifiCorp_Grid Design, Operations, and Maintenance_Quality Assurance and Quality Control_AI-12_2024 | 178 | Equipment ignition likelihood | Yes | Inspection Count |  | 2025 | 1 | 250 | [7 empty] | In Progress
1010000010 | PacifiCorp | 2025-07-07 | Program |  |  | Partner with public safety partners in communities throughout California regarding wildfire safety and preparedness and PSPS. | Public Outreach and Education Awareness Program | Partner with public safety partners in communities throughout California regarding wildfire safety and preparedness and PSPS. | Community Outreach and Engagement | Public Outreach and Education Awareness Program |  | 8.5.2 | CO-01 | PacifiCorp_Community Outreach and Engagement_Public Outreach and Education Awareness Program_CO-01_2024 | 324 | PSPS vulnerability | No |  |  | 2025 | 1 |  |  |  |  | 60% or more of the sample survey are aware of wildfire safety communications | Survey was conducted in Q1 and are awaiting final results and the report to be released. |  |  | In Progress
1010000011 | PacifiCorp | 2025-07-07 | Program |  |  | External collaboration and coordination | To enhance awareness of PSPS plan and understanding of roles and responsibilities. | To enhance awareness of PSPS plan and understanding of roles and responsibilities. | Emergency Preparedness | External Collaboration and Coordination |  | 8.4.2.3 | EP-02 | PacifiCorp_Emergency Preparedness_External Collaboration and Coordination_EP-02_2024 | 285 | PSPS vulnerability | No |  |  | 2025 | 1 |  |  |  |  | 1 Functional Exercise 1 Tabletop Exercise 1 Workshop | Completed 1 workshop |  |  | In Progress
1010000012 | PacifiCorp | 2025-07-07 | Program |  |  | Line Rebuild | Line Rebuild program - Covered Conductor installation. Includes undergrounding | Address the potential that incidental object contact will result in a fault event | Grid Design, Operations, and Maintenance | Line Rebuild - Covered conductor installation |  | 8.1.2.1 | GH-01 | PacifiCorp_Grid Design, Operations, and Maintenance_Line Rebuild - Covered conductor installation_GH-01_2024 | 156 | Contact by object ignition | No | Line miles |  | 2025 | 1 | 9 | [7 empty] | In Progress
1010000013 | PacifiCorp | 2025-07-07 | Program |  |  | Targeted Pole Replacement | Distribution Pole Replacement | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | Grid Design, Operations, and Maintenance | Distribution Pole Replacement |  | 8.1.2.3 | GH-02 | PacifiCorp_Grid Design, Operations, and Maintenance_Distribution Pole Replacement_GH-02_2024 | 159 | Contact by object ignition | No | Poles |  | 2025 | 1 | 192 | [7 empty] | In Progress
1010000014 | PacifiCorp | 2025-07-07 | Program |  |  | Transmission Pole Replacement | Transmission Pole Replacement | In some cases, poles need to be replaced to accommodate the additional weight of covered conductor; replacing wooden poles with stronger nonwooden solutions such as fiberglass or steel also increases grid resiliency. | Grid Design, Operations, and Maintenance | Transmission Pole Replacement |  | 8.1.2.4 | GH-03 | PacifiCorp_Grid Design, Operations, and Maintenance_Transmission Pole Replacement_GH-03_2024 | 159 | Contact by object ignition | No | Poles |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000015 | PacifiCorp | 2025-07-07 | Program |  |  | Relay/Recloser/CB Replacements / Upgrade | Relay/Recloser/Circuit Breacker Replacements / Upgrade | Enhances fault detection capabilities, reduce fault isolation time, improve fault location and record availability, and speed up restoration efforts | Grid Design, Operations, and Maintenance | Installation of system automation equipment |  | 8.1.2.8 | GH-04 | PacifiCorp_Grid Design, Operations, and Maintenance_Installation of system automation equipment_GH-04_2024 | 160 | PSPS exposure potential | No | Devices |  | 2025 | 1 | 4 | [7 empty] | In Progress
1010000016 | PacifiCorp | 2025-07-07 | Project | 2021-01-01 | 2025-12-31 | Expulsion fuse replacement | Replacement of expulsion fuses | Install new and CAL FIRE-approved non expulsion fuses including power fuses and current limiting fuses to replace existing expulsion fuse equipment | Grid Design, Operations, and Maintenance | Expulsion fuse replacement |  | 8.1.2.12 | GH-05 | PacifiCorp_Grid Design, Operations, and Maintenance_Expulsion fuse replacement_GH-05_2024 | 161 | Equipment ignition likelihood | No | Fuse locations |  | 2025 | 1 | 110 | [7 empty] | In Progress
1010000017 | PacifiCorp | 2025-07-07 | Program |  |  | Installation of weather stations | Installation of weather stations | Expansion of the weather station network to provide reliable and accurate data to support better forecasting and to inform real time situational awareness and decision-making during adverse fire weather conditions. | Situational Awareness and Forecasting | Environmental monitoring systems |  | 8.3.2 | SA-01 | PacifiCorp_Situational Awareness and Forecasting_Environmental monitoring systems_SA-01_2024 | 236 | PSPS likelihood | No | Unit |  | 2025 | 1 | 0 | [7 empty] | Planned
1010000018 | PacifiCorp | 2025-07-07 | Program |  |  | Detailed Inspection – Distribution | Detailed inspections for vegetation clearances around distribution electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks. | Vegetation Management | Detailed Inspection – Distribution |  | 8.2.2.1 | VM-01 | PacifiCorp_Vegetation Management_Detailed Inspection – Distribution_VM-01_2024 | 210 | Contact from vegetation ignition likelihood | Yes | Line miles |  | 2025 | 1 | 271 | [7 empty] | In Progress
1010000019 | PacifiCorp | 2025-07-07 | Program |  |  | Detailed Inspection - Transmission | Detailed inspections for vegetation clearances around transmission electric lines. | To eliminate vegetation-related reliability (cascading outages), safety, and wildfire ignition risks. | Vegetation Management | Detailed Inspection - Transmission |  | 8.2.2.2 | VM-02 | PacifiCorp_Vegetation Management_Detailed Inspection - Transmission_VM-02_2024 | 213 | Contact from vegetation ignition likelihood | Yes | Line miles |  | 2025 | 1 | 140 | [7 empty] | In Progress
1010000020 | PacifiCorp | 2025-07-07 | Program |  |  | Patrol Inspection - Distribution | Patrol (ground) inspections for vegetation clearances around distribution electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks by addressing vegetation conditions that require corrective action prior to the next scheduled work. | Vegetation Management | Patrol Inspection - Distribution |  | 8.2.3.3 | VM-03 | PacifiCorp_Vegetation Management_Patrol Inspection - Distribution_VM-03_2024 | 222 | Contact from vegetation ignition likelihood | Yes | Line miles |  | 2025 | 1 | 965 | [7 empty] | In Progress
1010000021 | PacifiCorp | 2025-07-07 | Program |  |  | Patrol Inspection - Transmission | Patrol (ground) inspections for vegetation clearances around transmission electric lines. | To minimize vegetation related reliability, safety, and wildfire ignition risks by addressing vegetation conditions that require corrective action while maintaining compliance with applicable Public Resource Codes, NERC requirements, and as described in the Vegetation SOP | Vegetation Management | Patrol Inspection - Transmission |  | 8.2.2.4 | VM-04 | PacifiCorp_Vegetation Management_Patrol Inspection - Transmission_VM-04_2024 | 217 | Contact from vegetation ignition likelihood | Yes | Line miles |  | 2025 | 1 | 170 | [7 empty] | In Progress
1010000022 | PacifiCorp | 2025-07-07 | Program |  |  | Pole Clearing | Pole clearing beyond PRC 4292 | Pole clearing is designed to reduce the risk of fire ignition if sparks are emitted from electrical equipment. | Vegetation Management | Fuels management – Pole clearing beyond PRC 4292 |  | 8.2.3.1.2 | VM-05 | PacifiCorp_Vegetation Management_Fuels management – Pole clearing beyond PRC 4292_VM-05_2024 | 221 | Contact from vegetation ignition likelihood | No | Poles |  | 2025 | 1 | 1374 | [7 empty] | In Progress
1010000023 | PacifiCorp | 2025-07-07 | Program |  |  | Quality Assurance and Quality Control | Patrol post-audits on distribution electric lines | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications. | Vegetation Management | QA/QC - Post-Audits Distribution (Patrol) |  | 8.2.5 | VM-11 | PacifiCorp_Vegetation Management_QAQC - Post-Audits Distribution (Patrol)_VM-11_2024 | 227 | Contact from vegetation ignition likelihood | Yes | Line miles |  | 2025 | 1 | 173 | [7 empty] | In Progress
1010000024 | PacifiCorp | 2025-07-07 | Program |  |  | Quality Assurance and Quality Control | Patrol post-audits on transmission electric lines | Quality control actions such as audits are critical to ensure vegetation requiring work (pruning and/or removal) is properly identified and the work is subsequently conducted in accordance with vegetation program standards/specifications. | Vegetation Management | QA/QC - Post-Audits Transmission (Patrol) |  | 8.2.5 | VM-11 | PacifiCorp_Vegetation Management_QAQC - Post-Audits Transmission (Patrol)_VM-11_2024 | 227 | Contact from vegetation ignition likelihood | Yes | Line miles |  | 2025 | 1 | 71 | [7 empty] | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000001 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000002 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000003 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 20
1020000004 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000005 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000006 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000007 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 1
1020000008 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000009 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000010 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000011 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 346
1020000012 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000013 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000014 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000015 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 2
1020000016 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000017 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000018 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000019 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000020 | 1. Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000021 | 1. Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000022 | 1. Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000023 | 1. Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 17
1020000024 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000025 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000026 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000027 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 14
1020000028 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000029 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000030 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000031 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 1
1020000032 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000033 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000034 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000035 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 276
1020000036 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000037 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000038 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000039 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 6
1020000040 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000041 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000042 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000043 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000044 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000045 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000046 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000047 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 70
1020000048 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000049 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000050 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000051 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000052 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000053 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000054 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000055 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000056 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000057 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000058 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000059 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1020000060 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000061 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000062 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000063 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000064 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000065 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000066 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000067 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000068 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000069 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000070 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000071 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  | Not applicable. PacifiCorp does not have a process in place to accurately identify time elapsed from inspection to completing the work in all cases due to limitations with the mobile data management software being used and other variables associated with the data | PacifiCorp | 2025 | 1
1020000072 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000073 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000074 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000075 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000076 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000077 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000078 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000079 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000080 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000081 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000082 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000083 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Not Applicable | PacifiCorp | 2025 | 1
1020000084 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 14640
1020000085 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 34076.4
1020000086 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 15312
1020000087 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 29284.8
1020000088 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 17856
1020000089 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 30243.6
1020000090 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 11928
1020000091 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 19977.6
1020000092 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 11328
1020000093 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 21020.4
1020000094 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 11904
1020000095 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 35143.2
1020000096 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 14952
1020000097 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 147720
1020000098 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 15720
1020000099 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 145105.2
1020000100 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 18888
1020000101 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 142800
1020000102 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 12936
1020000103 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 111970.8
1020000104 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 17976
1020000105 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 145975.2
1020000106 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 11904
1020000107 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  |  | PacifiCorp | 2025 | 1 | 86296.8
1020000108 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  | PacifiCorp does not issue vegetation management work at the task by task level with specific "work orders", but rather at the circuit level. That being said, PacifiCorp does identify vegetation management activities at the work location level within its mobile data management software. PacifiCorp is currently reviewing its data to identify a process to more accurately identify work locations that may be "open"/unresolved considering limitations and other variables within its mobile data management software. PacifiCorp does not assign completion date requirements at the work location level. | PacifiCorp | 2025 | 1
1020000109 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  | PacifiCorp does not issue vegetation management work at the task by task level with specific "work orders", but rather at the circuit level. That being said, PacifiCorp does identify vegetation management activities at the work location level within its mobile data management software. PacifiCorp is currently reviewing its data to identify a process to more accurately identify work locations that may be "open"/unresolved considering limitations and other variables within its mobile data management software. PacifiCorp does not assign completion date requirements at the work location level. | PacifiCorp | 2025 | 1
1020000110 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | PacifiCorp | 2025 | 1 | 9685
1020000111 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | PacifiCorp | 2025 | 1 | 139
1020000112 | 8. Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  |  | PacifiCorp | 2025 | 1 | 5
1020000113 | 9. Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | PacifiCorp | 2025 | 1 | 0
1020000114 | 9. Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | PacifiCorp | 2025 | 1 | 0
1020000115 | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | PacifiCorp | 2025 | 1 | 0
1020000116 | 11. Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | PacifiCorp | 2025 | 1 | 0
1020000117 | 11. Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | PacifiCorp | 2025 | 1 | 0
1020000118 | 12. Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | PacifiCorp | 2025 | 1 | 0
1020000119 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000120 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000121 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000122 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000123 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000124 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000125 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000126 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000127 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000128 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000129 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000130 | 13. Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | PacifiCorp | 2025 | 1 | 0
1020000131 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000132 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000133 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000134 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 8646
1020000135 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000136 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000137 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000138 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 4288
1020000139 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000140 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000141 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000142 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 191
1020000143 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000144 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000145 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000146 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 295.7281
1020000147 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000148 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000149 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000150 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 121.131
1020000151 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000152 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000153 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000154 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 4.8559
1020000155 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000156 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000157 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000158 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000159 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000160 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000161 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000162 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000163 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000164 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000165 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000166 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000167 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000168 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000169 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000170 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000171 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000172 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000173 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000174 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 755
1020000175 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000176 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000177 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000178 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 13
1020000179 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000180 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000181 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000182 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000183 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000184 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000185 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000186 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 544
1020000187 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000188 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000189 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000190 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 3
1020000191 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000192 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000193 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000194 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 4971
1020000195 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000196 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000197 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000198 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 996
1020000199 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000200 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000201 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000202 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 59
1020000203 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000204 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000205 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000206 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 38.6061
1020000207 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000208 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000209 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000210 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 37.2682
1020000211 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000212 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000213 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000214 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 2.4201
1020000215 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000216 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000217 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000218 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000219 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000220 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000221 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000222 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000223 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000224 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000225 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000226 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000227 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000228 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000229 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000230 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000231 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000232 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000233 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000234 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 108
1020000235 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000236 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000237 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000238 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000239 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000240 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000241 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000242 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000243 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000244 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000245 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000246 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 122
1020000247 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000248 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000249 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000250 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 1
1020000251 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000252 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000253 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000254 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 3125
1020000255 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000256 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000257 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000258 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 213
1020000259 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000260 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000261 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000262 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000263 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000264 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000265 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000266 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 74.2976
1020000267 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000268 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000269 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000270 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 4.3325
1020000271 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000272 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000273 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000274 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000275 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000276 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000277 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000278 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000279 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000280 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000281 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000282 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000283 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000284 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000285 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000286 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000287 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000288 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000289 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000290 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000291 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000292 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000293 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000294 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 22
1020000295 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000296 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000297 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000298 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000299 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000300 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000301 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000302 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000303 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000304 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000305 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000306 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 35
1020000307 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000308 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000309 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000310 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000311 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000312 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000313 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000314 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 1
1020000315 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000316 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000317 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000318 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 1
1020000319 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000320 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000321 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000322 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000323 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000324 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000325 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000326 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0.064856
1020000327 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000328 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000329 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000330 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0.064856
1020000331 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000332 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000333 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000334 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000335 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000336 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000337 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000338 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000339 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000340 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000341 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000342 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000343 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000344 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000345 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000346 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000347 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000348 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000349 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000350 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000351 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000352 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000353 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000354 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000355 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000356 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 10
1020000357 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000358 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000359 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000360 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000361 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000362 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000363 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000364 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000365 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000366 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000367 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000368 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000369 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000370 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000371 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000372 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000373 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000374 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 1
1020000375 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000376 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000377 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000378 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000379 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000380 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000381 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000382 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000383 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000384 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000385 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000386 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0.014243
1020000387 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000388 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000389 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000390 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000391 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000392 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000393 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000394 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000395 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000396 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000397 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000398 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000399 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000400 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000401 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000402 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000403 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000404 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000405 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000406 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000407 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000408 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000409 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000410 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000411 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000412 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000413 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000414 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000415 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000416 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000417 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000418 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000419 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000420 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000421 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000422 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000423 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000424 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000425 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000426 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000427 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000428 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000429 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000430 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000431 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000432 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000433 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000434 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000435 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000436 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000437 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000438 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000439 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000440 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000441 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000442 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000443 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000444 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000445 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000446 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000447 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000448 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000449 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000450 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000451 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000452 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000453 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000454 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  |  | PacifiCorp | 2025 | 1 | 0
1020000455 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000456 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000457 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000458 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000459 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000460 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000461 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000462 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000463 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000464 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000465 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000466 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000467 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000468 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000469 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000470 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000471 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000472 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000473 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000474 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000475 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000476 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 10
1020000477 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000478 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000479 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000480 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000481 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000482 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000483 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000484 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000485 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000486 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000487 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000488 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000489 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000490 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PacifiCorp | 2025 | 1 | 0
1020000491 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000492 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000493 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000494 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000495 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000496 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000497 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000498 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000499 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000500 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000501 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000502 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000503 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000504 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000505 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000506 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000507 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000508 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000509 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000510 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 472
1020000511 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000512 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000513 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000514 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 6
1020000515 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000516 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000517 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000518 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000519 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000520 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000521 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000522 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 189
1020000523 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000524 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000525 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000526 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 2
1020000527 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000528 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000529 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000530 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000531 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000532 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000533 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000534 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000535 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000536 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000537 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000538 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000539 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000540 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000541 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000542 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000543 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000544 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000545 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000546 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 463
1020000547 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000548 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000549 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000550 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 7
1020000551 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000552 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000553 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000554 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000555 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000556 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000557 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000558 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 309
1020000559 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000560 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000561 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000562 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 5
1020000563 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000564 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000565 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000566 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000567 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000568 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000569 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000570 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000571 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000572 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000573 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000574 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000575 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000576 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000577 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000578 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000579 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000580 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000581 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000582 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 655
1020000583 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000584 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000585 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000586 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 3
1020000587 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000588 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000589 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000590 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000591 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000592 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000593 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000594 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 283
1020000595 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000596 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000597 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000598 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 5
1020000599 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000600 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000601 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000602 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000603 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000604 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000605 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000606 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000607 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000608 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000609 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000610 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000611 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000612 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000613 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000614 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000615 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000616 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000617 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000618 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 44
1020000619 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000620 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000621 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000622 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000623 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000624 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000625 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000626 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000627 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000628 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000629 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000630 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 47
1020000631 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000632 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000633 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000634 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 1
1020000635 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000636 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000637 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000638 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000639 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000640 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000641 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000642 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000643 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000644 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000645 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000646 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000647 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000648 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000649 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000650 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000651 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000652 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000653 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000654 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 22
1020000655 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000656 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000657 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000658 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000659 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000660 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000661 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000662 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000663 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000664 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000665 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000666 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 30
1020000667 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000668 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000669 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000670 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000671 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000672 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000673 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000674 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000675 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000676 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000677 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000678 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000679 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000680 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000681 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000682 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000683 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000684 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000685 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000686 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000687 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000688 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000689 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000690 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 31
1020000691 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000692 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000693 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000694 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000695 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000696 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000697 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000698 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000699 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000700 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000701 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000702 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 31
1020000703 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000704 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000705 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000706 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PacifiCorp | 2025 | 1 | 0
1020000707 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000708 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000709 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000710 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000711 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000712 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000713 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000714 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000715 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000716 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000717 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000718 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 507
1020000719 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000720 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000721 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000722 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 337
1020000723 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000724 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000725 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000726 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000727 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000728 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000729 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000730 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000731 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000732 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000733 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000734 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 0
1020000735 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000736 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000737 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000738 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 0
1020000739 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000740 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000741 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000742 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000743 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000744 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000745 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000746 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000747 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000748 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000749 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000750 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 733
1020000751 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000752 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000753 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000754 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 3135
1020000755 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000756 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000757 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000758 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000759 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000760 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000761 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000762 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000763 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000764 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000765 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000766 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 7
1020000767 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000768 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000769 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000770 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 16
1020000771 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000772 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000773 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000774 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000775 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000776 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000777 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000778 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000779 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000780 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000781 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000782 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 0
1020000783 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000784 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000785 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000786 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 0
1020000787 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000788 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000789 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000790 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000791 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000792 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000793 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000794 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PacifiCorp does not document the number of trees that are visually inspected for compliance with it's specifications or with state regulations. This would require significant increase in inspection resources to document information on trees not requiring vegetation management actions. This information is not planned to be collected in the foreseeable future. | PacifiCorp | 2025 | 1
1020000795 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000796 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000797 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000798 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 1
1020000799 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Drones are not used as part of the vegetation management program at this time. | PacifiCorp | 2025 | 1
1020000800 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Aerial inspections may be conducted in conjunction with facility inspections or on an as needed basis. Aerial vegetation management inspections are followed up with ground based inspections. PacifiCorp does not differentiate between inspection method. Refer to inspection method "other". | PacifiCorp | 2025 | 1
1020000801 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | LiDAR is not used as part of the vegetation management program. | PacifiCorp | 2025 | 1
1020000802 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | PacifiCorp does not document number of trees that are non-compliant with state regulations, but rather identifies trees requiring vegetation management actions consistent with PacifiCorp's specifications. Trees identified by PacifiCorp as requiring vegetation management actions are not necessarily synonymous with non-compliance with state regulations. As a surrogate to number of tree found to be non-compliant with state regulations, PacifiCorp can provide number of trees worked (prune or removal) for 2025. |  | PacifiCorp | 2025 | 1 | 4
1020000803 | 17. Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | PacifiCorp does not have authority to order evacuations. This is a local jurisdiction Incident Command authority. Local jurisdictions use their own alert and warning system to execute evacuation orders. | PacifiCorp | 2025 | 1

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | PC3a | Events Recorded with Fire Reference: Not Fire Season | Monitoring this metrics helps PacifiCorp understand the frequency of ignitions as well as the potential causes of ignition. | Data source is outage reporting system in which outage makes reference to fire in comment or outage cause | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Events |  |  | PacifiCorp | 2025 | 1 | 0
1030000001 | PC3b | Events Recorded with Fire Reference: Fire Season | Monitoring this metrics helps PacifiCorp understand the frequency of ignitions as well as the potential causes of ignition. | Data source is outage reporting system in which outage makes reference to fire in comment or outage cause | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Events |  |  | PacifiCorp | 2025 | 1 | 0
1030000002 | PC4a | Events Recorded with Fire Reference: damage fire, equipment fire, pole fire: Not Fire Season | Monitoring this metric helps supports investigation of faults that potentially have an ignition associated with equipment. | Subset of PC3 where record makes reference to utility equipment or key components | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Events |  |  | PacifiCorp | 2025 | 1 | 0
1030000003 | PC4b | Events Recorded with Fire Reference: damage fire, equipment fire, pole fire: Fire Season | Monitoring this metric supports investigations of faults that potentially have an ignition associated with equipment. | Subset of PC3 where record makes reference to utility equipment or key components | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Events |  |  | PacifiCorp | 2025 | 1 | 0
1030000004 | PC5 | Wire down risks | Monitoring helps PacifiCorp understand if hardening and asset inspection initiatives are impacting the likelihood of an wire down event. | Data source is outage reporting system in which cause code or comments would result in downed conductor during fire season | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Events |  |  | PacifiCorp | 2025 | 1 | 19
1030000005 | PC6 | Wire down trend | Monitoring helps PacifiCorp understand the trends of wire down events during fire season and if there are changes due to system hardening and asset inspection initiatives. | Reduction in quantity of wire down events, year over year, during the designated fire season period | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table. | Events |  |  | PacifiCorp | 2025 | 1 | 2

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000001 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000002 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000003 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000004 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000005 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000006 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 3243.167
1040000007 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 74.648
1040000008 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 8702.759
1040000009 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 2298.004
1040000010 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 139.601
1040000011 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 4565.294
1040000012 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000013 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000014 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000015 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000016 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000017 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000018 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000019 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000020 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000021 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000022 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1040000023 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 10
1050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 4
1050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 2
1050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 60
1050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 5
1050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 45
1050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 10
1050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 13
1050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 9
1050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 3
1050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 2
1050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 2
1050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 9
1050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 136
1050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 10
1050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 34
1050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 1
1050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | PacifiCorp | 2025 | 1 | 0

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0
1060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | PacifiCorp | 2025 | 1 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 23.49
1070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 23.37
1070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 390.08
1070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 319.67
1070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 165.68
1070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 778.75
1070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 4.59
1070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.03
1070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 322.68
1070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 90.71
1070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 206.76
1070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 145.25
1070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 34.69
1070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 5.64
1070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 1.11
1070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 1
1070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 66.62
1070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 97.34
1070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 23.01
1070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 195.98
1070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.7
1070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 81.3
1070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 67.98
1070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 57.62
1070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 111.85
1070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 15.42
1070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 7.84
1070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 18.08
1070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 11.78
1070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 79.68
1070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 46.08
1070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 23.65
1070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 56.85
1070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 1.67
1070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.01
1070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 224.47
1070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 28.36
1070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 63.62
1070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 30.39
1070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 51.23
1070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 3.5
1070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 1.11
1070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 1.75
1070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 66.62
1070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 97.34
1070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 23.01
1070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 195.98
1070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.7
1070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 81.3
1070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 67.98
1070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 57.62
1070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 111.85
1070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 15.42
1070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 7.84
1070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 128
1070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 91
1070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 212
1070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 161
1070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 155
1070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 172
1070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 5
1070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 0
1070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 297
1070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 58
1070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 105
1070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 49
1070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 0
1070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 0
1070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 37
1070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 9
1070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 0
1070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | PacifiCorp | 2025 | 1 | 0
1070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 2982
1070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 2566
1070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 7778
1070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 2638
1070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 2420
1070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 2421
1070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 139
1070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 10736
1070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 559
1070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 3215
1070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 606
1070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 931
1070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 66
1070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 358
1070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 548
1070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 1348
1070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 976
1070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 566
1070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 983
1070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 30
1070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 1
1070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 1978
1070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 318
1070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 612
1070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 244
1070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 128
1070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 62
1070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | PacifiCorp | 2025 | 1 | 0
1070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 185
1070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 187
1070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 461
1070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 129
1070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 104
1070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 125
1070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 8
1070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 0
1070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 497
1070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 23
1070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 163
1070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 18
1070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 0
1070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 0
1070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 12
1070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 1
1070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 0
1070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PacifiCorp | 2025 | 1 | 0
1070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 5
1070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 1
1070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 4
1070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 1
1070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 1
1070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 9
1070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 10
1070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 4
1070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 18
1070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 17
1070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 8
1070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 14
1070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 22
1070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 3
1070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 3
1070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.04
1080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.08
1080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.01
1080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.04
1080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.01
1080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.08
1080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.02
1080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.04
1080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.02
1080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.01
1080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.75
1080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.05
1080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.09
1080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.11
1080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.05
1080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.02
1080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.03
1080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.11
1080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.06
1080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.17
1080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.01
1080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.02
1080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.05
1080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.38
1080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.01
1080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.15
1080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | -0.03
1080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.07
1080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 1.11
1080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 1.75
1080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 66.62
1080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 97.34
1080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 23.01
1080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 195.98
1080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.7
1080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 81.3
1080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 67.98
1080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 57.62
1080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 111.85
1080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 15.42
1080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 7.84
1080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | -1
1080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | -1
1080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.09
1090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.04
1090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 9.39
1090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0.43
1090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PacifiCorp | 2025 | 1 | 0
1090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 1
1090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 2
1090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 1
1090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PacifiCorp | 2025 | 1 | 0
1090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0
1090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PacifiCorp | 2025 | 1 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000001 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000002 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000003 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000004 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PacifiCorp | 2025 | 1 | 0
1100000005 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PacifiCorp | 2025 | 1 | 0
1100000006 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PacifiCorp | 2025 | 1 | 0
1100000007 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PacifiCorp | 2025 | 1 | 0
1100000008 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000009 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000010 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000011 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000012 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000013 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000014 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000015 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000016 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1100000017 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1100000018 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1100000019 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | PacifiCorp | 2025 | 1 | 0
1100000020 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | PacifiCorp | 2025 | 1 | 918.1333
1100000021 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | PacifiCorp | 2025 | 1 | 2071.7833
1100000022 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000023 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | PacifiCorp | 2025 | 1 | 69.6437
1100000024 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | PacifiCorp | 2025 | 1 | 69.6437
1100000025 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PacifiCorp | 2025 | 1 | 0.46359
1100000026 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PacifiCorp | 2025 | 1 | 0.46359
1100000027 | 3. Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | PacifiCorp | 2025 | 1 | 0
1100000028 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PacifiCorp | 2025 | 1 | 0
1100000029 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PacifiCorp | 2025 | 1 | 0
1100000030 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PacifiCorp | 2025 | 1 | 0
1100000031 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PacifiCorp | 2025 | 1 | 0
1100000032 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PacifiCorp | 2025 | 1 | 0
1100000033 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PacifiCorp | 2025 | 1 | 0
1100000034 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | PacifiCorp | 2025 | 1 | 0
1100000035 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | PacifiCorp | 2025 | 1 | 0
1100000036 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | PacifiCorp | 2025 | 1 | 0
1100000037 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | PacifiCorp | 2025 | 1 | 0
1100000038 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | PacifiCorp | 2025 | 1 | 0
1100000039 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000040 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000041 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000042 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | PacifiCorp | 2025 | 1 | 0
1100000043 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | PacifiCorp | 2025 | 1 | 0

## Table 13
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED OR MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1130000000 | 100017283-16512-DETAIL-06_25_2024-SVCDEFLC-1^06244005.0239100 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000001 | 100313159-10953-DTLSB-04_16_2024-GRDRODHI-1^06245007.0227346 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000002 | 101004320-64069-DETAIL-07_15_2022-GO95HV-1^668005/00 5/047 | OTHER | Non-HFTD | Transmission | 2022-07-15 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000003 | 101051463-98879-DETAIL-08_13_2024-GO95MLD-1^06245005.0367401 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000004 | 101051463-98879-DETAIL-08_13_2024-GRDRODHI-1^06245005.0367401 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000005 | 10122476-94469-DETAIL-04_18_2024-GO95HV-1^06145001.0362500 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000006 | 10233018-23669-DETAIL-04_22_2024-GO95MLD-1^06145001.0029501 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000007 | 102391108-75040-DETAIL-03_20_2024-GO95HV-1^06245002.0121201 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000008 | 102877192-21880-DETAIL-02_12_2025-SVCENTBK-1^06240004.0167209 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000009 | 103303629-27409-DETAIL-02_01_2022-SVCWIND-1^06147005.0267304 | OTHER | Non-HFTD | Distribution | 2022-02-01 | 2025-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000010 | 100188046-37949-DETAIL-02_27_2024-SVCENTCO-1^07113002.0184702 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000011 | 100188046-37949-DETAIL-02_27_2024-SVCENTCO-2^07113002.0184702 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000012 | 100313159-10953-DTLSB-04_16_2024-GO95MLD-1^06245007.0227346 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000013 | 100480722-42099-DETAIL-07_18_2024-SVCDEFLC-1^06244004.0176900 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000014 | 100901531-61531-DETAIL-02_20_2025-GUYHINS-1^06240004.0212902 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-20 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000015 | 103698331-92559-DETAIL-05_16_2022-GO95MLD-1^07116001.0090600 | OTHER | HFTD Tier 2 | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000016 | 103959676-55749-DETAIL-10_10_2024-GO95CL10-1^07216001.0204109 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000017 | 103959676-55749-DETAIL-10_10_2024-GO95HV-1^07216001.0204109 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000018 | 104258932-1850-DETAIL-03_20_2025-SVCROAD-1^06239003.0018101 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000019 | 104264293-37470-DTLTRT-04_09_2024-GO95HV-1^668062/00 6/001 | OTHER | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000020 | 10120037-49-DTLSB-10_03_2024-GO95HV-1^06245006.0339800 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000021 | 101573294-17710-DETAIL-03_13_2025-GO95HV-1^06238004.0156200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000022 | 101827519-13740-DETAIL-05_02_2024-GO95MLD-1^06142012.0125104 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000023 | 101960373-88189-DTLSB-02_06_2023-GO95MLD-1^06248001.0257800 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000024 | 102159314-35549-DTLSB-02_07_2024-GUYNOINS-1^07216001.0199309 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000025 | 104264293-51653-DTLTRT-04_09_2024-GO95HV-1^668062/00 6/001 | OTHER | HFTD Tier 2 | Transmission | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000026 | 104323982-17031-DETAIL-03_03_2025-CLRTOUCH-1^06241004.0181200 | CONDUCTOR | HFTD Tier 3 | Distribution | 2025-03-03 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000027 | 104333746-81379-DTLSB-02_01_2023-GO95HV-1^06248001.0369903 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000028 | 104333746-81379-DTLSB-02_01_2023-GO95TCH-1^06248001.0369903 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000029 | 104530148-67989-DTLSB-04_15_2024-SVCWIND-1^06245007.0223203 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000030 | 104630956-86649-DETAIL-02_23_2023-GO95TCH-1^07216001.0294704 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000031 | 104918207-88207-DTLSB-05_21_2024-GO95HV-1^06244002.0142501 | OTHER | Non-HFTD | Distribution | 2024-05-21 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000032 | 104994035-62149-DETAIL-07_05_2024-GO95HV-1^06245004.0300600 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000033 | 105023984-46850-DETAIL-11_03_2023-GUYHINS-1^668010/00 9/036 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000034 | 105023984-46850-DETAIL-11_03_2023-GUYHINS-2^668010/00 9/036 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000035 | 105178184-98849-DETAIL-03_15_2023-GO95HV-1^07114001.0339404 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000036 | 105210781-95342-DETAIL-07_13_2023-GO95MLD-1^06244008.0320801 | OTHER | Non-HFTD | Distribution | 2023-07-13 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000037 | 105488238-66274-DETAIL-10_21_2024-SVCNEUT-1^07216001.0209341 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000038 | 105497898-5069-DTLTRT-06_09_2021-UBPBGYBK-1^668041/00 4/015 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000039 | 105662035-63240-DETAIL-10_25_2024-GO95HV-1^07216001.0201501 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000040 | 106095974-8084-DETAIL-03_29_2023-GO95MLD-1^06142016.0084400 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000041 | 106236199-99759-DETAIL-03_13_2023-SVCENTCO-1^07216001.0290640 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000042 | 10623879-5679-DETAIL-04_08_2024-GO95MLD-1^06147005.0227401 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000043 | 106310808-43058-DETAIL-07_05_2024-GO95MLD-1^06244005.0019402 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000044 | 106479642-39340-DTLTRT-10_03_2023-GO95HV-1^668010/00 4/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000045 | 107007374-6679-DETAIL-03_20_2024-GO95MLD-1^06244004.0069500 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000046 | 107025414-24040-DETAIL-10_16_2024-GO95MLD-1^07216001.0206701 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000047 | 10718888-91370-DETAIL-11_18_2024-BIRDDMG-1^668014/00 3/059 | POLE | HFTD Tier 2 | Transmission | 2024-11-18 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000048 | 107450928-13240-DETAIL-03_19_2024-GO95HV-1^06245002.0014500 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000049 | 107576178-54609-DTLTRT-09_30_2020-GO95HV-1^668018/00 2/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000050 | 107674680-15340-DETAIL-03_07_2022-ENCHRW-1^06146006.0076905 | OTHER | Non-HFTD | Distribution | 2022-03-07 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000051 | 107766890-3869-DETAIL-11_09_2022-ABNDEQPM-1^06246008.0043200 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000052 | 107766890-3869-DETAIL-11_09_2022-GO95HV-1^06246008.0043200 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000053 | 108062705-56640-DETAIL-04_24_2024-GO95HV-1^06145001.0047001 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000054 | 108459372-78579-DTLTRT-10_03_2023-GO95MLD-1^668010/00 2/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000055 | 108539842-50520-DETAIL-02_24_2025-GO95BLTC-1^06240004.0272041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000056 | 108539842-50520-DETAIL-02_24_2025-SVCROAD-1^06240004.0272041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000057 | 108545959-73859-DTLTRT-10_25_2022-GO95HV-1^668075/00 4/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000058 | 108618095-51149-DETAIL-10_21_2024-GO95MLD-1^07216001.0200700 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000059 | 10876383-92629-DTLSB-09_07_2023-GO95MLD-1^06243008.0124202 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000060 | 109134648-74449-DETAIL-10_10_2024-GO95CL10-1^07216001.0201210 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000061 | 109134648-74449-DETAIL-10_10_2024-GO95MLD-1^07216001.0201210 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000062 | 109366811-42450-DTLSB-02_15_2023-GO95HV-1^06248001.0309700 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000063 | 109486623-64080-DETAIL-02_11_2025-GUYHINS-1^06240004.0357000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000064 | 109878802-7750-DETAIL-04_23_2024-GO95HV-1^06145001.0039200 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000065 | 110359745-22869-DRONE_HY-10_17_2023-GO95HV-1^668033/00 8/040 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000066 | 110619611-31932-DETAIL-04_02_2025-SVCROAD-1^06241005.0117405 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000067 | 110619611-31932-DETAIL-04_02_2025-SVCRUBCM-1^06241005.0117405 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130000068 | 111347670-77080-DETAIL-02_27_2025-GUYHINS-1^06240004.0232502 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000069 | 111347670-77080-DETAIL-02_27_2025-GUYHINS-2^06240004.0232502 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000070 | 111361260-2260-DETAIL-03_05_2024-GO95HV-1^06147005.0179401 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000071 | 102616278-6253-ADMIN-03_15_2024-POLEDERP-1^07216001.0146501 | POLE | Non-HFTD | Distribution | 2024-03-15 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000072 | 102877192-21880-DETAIL-02_12_2025-GO95HV-1^06240004.0167209 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000073 | 102877192-21880-DETAIL-02_12_2025-SVCROOF-1^06240004.0167209 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000074 | 102887524-15939-DTLSB-02_14_2024-GO95MLD-1^07216001.0198308 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000075 | 102985826-15310-DETAIL-03_13_2025-GO95HV-1^06238004.0224901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000076 | 102999388-54139-DETAIL-03_25_2024-GO95MLD-1^06244005.0146301 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000077 | 103959676-55749-DETAIL-10_10_2024-GO95MLD-1^07216001.0204109 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000078 | 104242278-96459-DETAIL-04_24_2023-GRDRODHI-1^07117003.0011700 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000079 | 10463013-91069-DETAIL-05_15_2024-GO95HV-1^06142012.0124701 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000080 | 104669533-64190-DETAIL-03_04_2025-GO95TCH-1^06240004.0150540 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000081 | 104792999-6509-DETAIL-10_28_2021-ENCHRW-1^06148005.0255100 | OTHER | Non-HFTD | Distribution | 2021-10-28 | 2024-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000082 | 104792999-6509-DETAIL-10_28_2021-ENCHRW-2^06148005.0255100 | OTHER | Non-HFTD | Distribution | 2021-10-28 | 2024-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000083 | 105023984-46850-DETAIL-11_03_2023-GUYHINS-3^668010/00 9/036 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000084 | 105488238-66274-DETAIL-10_21_2024-RISEBKSP-1^07216001.0209341 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000085 | 105662035-63240-DETAIL-10_25_2024-SVCROOF-1^07216001.0201501 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000086 | 105847528-54668-DETAIL-02_28_2023-GO95TCH-1^07216001.0298644 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000087 | 105912568-26841-DETAIL-03_06_2025-GO95HV-1^06241005.0161902 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000088 | 105972403-48080-DETAIL-02_25_2025-PWRTRN-1^06240005.0019001 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000089 | 106108858-159-DETAIL-02_13_2024-GO95HV-1^07216001.0187400 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000090 | 106169559-54889-DETAIL-07_24_2024-GO95MLD-1^06244005.0359500 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000091 | 106794763-24249-DTLSB-10_07_2024-GO95STUB-1^06245007.0211300 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000092 | 106922616-90040-DTLSB-05_14_2024-GO95MLD-1^06244001.0294700 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000093 | 106967033-33913-DTLSB-05_01_2024-GO95MLD-1^06245007.0228544 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000094 | 10718888-12260-DETAIL-11_18_2024-BIRDDMG-1^668014/00 3/059 | POLE | HFTD Tier 2 | Transmission | 2024-11-18 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000095 | 107683022-319-ADMIN-12_31_2018-POLEREPL-1^668005/00 8/087 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000096 | 107736930-1483-DTLSB-10_02_2024-SVCENTCO-1^06245007.0217604 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000097 | 107924529-11540-DETAIL-03_18_2024-GO95MLD-1^06245002.0052501 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000098 | 108323635-25189-DTLSB-08_28_2024-GO95HV-1^06245007.0142700 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000099 | 108346204-51640-DETAIL-02_25_2025-BIRDDMG-1^06240004.0218802 | POLE | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000100 | 108564033-24940-DETAIL-04_06_2023-GO95HV-1^06143014.0232701 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000101 | 108872765-24289-DTLSB-08_28_2024-GO95MLD-1^06245007.0141601 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000102 | 109540225-39359-DETAIL-04_01_2024-GO95MLD-1^06247005.0344501 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000103 | 109765628-39650-DETAIL-03_19_2024-GO95MLD-1^06245002.0021000 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000104 | 109957634-13869-DETAIL-06_06_2024-ABNDEQPM-1^06246006.0350300 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000105 | 109957634-13869-DETAIL-06_06_2024-GO95MLD-1^06246006.0350300 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000106 | 110076167-74279-DETAIL-04_09_2024-GO95MLD-1^06147005.0211001 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000107 | 110229804-37629-DTLSB-08_09_2023-GO95MLD-1^06243009.0193300 | OTHER | HFTD Tier 2 | Distribution | 2023-08-09 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000108 | 110240203-77329-DETAIL-06_13_2023-GO95MLD-1^06243009.0039500 | OTHER | Non-HFTD | Distribution | 2023-06-13 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000109 | 110709778-72899-DETAIL-03_21_2024-GO95HV-1^06245006.0016000 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000110 | 110715124-60350-DTLSB-01_30_2023-GO95HV-1^06248001.0259501 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000111 | 110862983-27350-DTLSB-05_23_2024-GO95HV-1^06243001.0135900 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000112 | 110862983-27350-DTLSB-05_23_2024-GO95MLD-1^06243001.0135900 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000113 | 111097536-27569-DETAIL-06_06_2024-GO95MLD-1^06245006.0035400 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000114 | 111140866-24749-DTLSB-04_25_2024-SVCWIND-1^06245007.0228300 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000115 | 111215430-99339-DETAIL-06_20_2024-GO95HV-1^06244005.0237705 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000116 | 111372398-92650-DETAIL-04_22_2024-GO95MLD-1^06145001.0119400 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000117 | 111500074-15190-DETAIL-03_25_2025-GO95HV-1^06239003.0019516 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000118 | 111515229-96839-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0294508 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000119 | 111515229-96839-DETAIL-03_07_2023-GO95CL10-1^07216001.0294508 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000120 | 111515229-96839-DETAIL-03_07_2023-GO95MLD-1^07216001.0294508 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000121 | 11165033-87680-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0168302 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000122 | 112292551-35180-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0166301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000123 | 112292551-35180-DETAIL-02_06_2025-SVCROAD-1^06240004.0166301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000124 | 112302246-15979-DETAIL-04_04_2024-GO95MLD-1^06147005.0130000 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000125 | 112481173-37629-DTLSB-09_07_2023-GO95HV-1^06243008.0026200 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000126 | 112964341-62159-DETAIL-03_16_2023-ENCHRW-1^07113001.0040502 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000127 | 113173702-70780-DETAIL-02_12_2025-PWRTRN-1^06240004.0282901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000128 | 113626898-52939-DETAIL-10_15_2024-GO95MLD-1^07216001.0203000 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000129 | 1136980-80180-DETAIL-02_27_2025-GUYHINS-1^06240004.0233602 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000130 | 11411119-76212-DETAIL-06_12_2023-GO95MLD-1^06244009.0362304 | OTHER | Non-HFTD | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000131 | 11436834-74934-DTLSB-02_08_2024-GO95MLD-1^07216001.0308909 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000132 | 114424606-44606-DETAIL-01_29_2025-GO95HV-1^06239004.0229100 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000133 | 114448991-70469-DETAIL-02_23_2023-GO95HV-1^668002/00 7/030 | OTHER | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000134 | 114495718-49692-DETAIL-07_05_2023-GO95HV-1^06244008.0322740 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000135 | 11463478-25489-DETAIL-04_17_2024-GO95HV-1^06145001.0019500 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000136 | 115041114-83114-DETAIL-03_29_2023-GO95HV-1^06142016.0085100 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000137 | 115101351-53059-DTLSB-02_20_2024-GO95MLD-1^07216001.0260306 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000138 | 115306559-68169-ADMIN-12_21_2022-GO95HV-1^668005/00 11/033 | OTHER | Non-HFTD | Transmission | 2022-12-21 | 2027-12-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000139 | 115402278-47359-DETAIL-05_31_2024-GO95MLD-1^06246005.0323501 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000140 | 115838693-97329-DETAIL-06_13_2023-GO95MLD-1^06243009.0039501 | OTHER | Non-HFTD | Distribution | 2023-06-13 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000141 | 115856443-8479-DETAIL-08_06_2024-GUYHINS-1^06244005.0364200 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-06 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000142 | 115931461-34939-DETAIL-03_07_2023-GO95HV-1^07117002.0210403 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000143 | 115931461-34939-DETAIL-03_07_2023-GO95TCH-1^07117002.0210403 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000144 | 116167998-46550-DETAIL-03_20_2025-GO95HV-1^06239003.0016304 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000145 | 116362695-88439-DETAIL-06_07_2023-GO95HV-1^06244006.0011700 | OTHER | Non-HFTD | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000146 | 116472971-1189-DTLSB-02_16_2023-GO95HV-1^06248001.0299300 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000147 | 111815981-71929-DETAIL-05_07_2024-GO95MLD-1^06142012.0123108 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000148 | 112090099-17050-DETAIL-04_11_2024-GO95HV-1^06245002.0104301 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000149 | 112112223-73223-DETAIL-05_08_2024-GO95MLD-1^06142012.0121007 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000150 | 11231041-68859-DETAIL-06_05_2024-GO95HV-1^06246006.0267600 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000151 | 11231041-68859-DETAIL-06_05_2024-GO95MLD-1^06246006.0267600 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000152 | 11231041-68859-DETAIL-06_05_2024-RISEGRD-1^06246006.0267600 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000153 | 112627883-42983-DETAIL-03_30_2023-GO95HV-1^06142016.0059100 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000154 | 112654200-50389-DTLSB-07_23_2024-GO95MLD-1^06245007.0109300 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000155 | 112964341-62159-DETAIL-03_16_2023-SVCENTCO-1^07113001.0040502 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000156 | 113029358-86169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 2/045 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000157 | 113083671-78523-DETAIL-06_19_2024-GO95MLD-1^06246006.0138501 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000158 | 113170997-71997-DETAIL-03_28_2024-GO95HV-1^06147005.0122002 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000159 | 113170997-71997-DETAIL-03_28_2024-GO95MLD-1^06147005.0122002 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000160 | 113173702-70780-DETAIL-02_12_2025-GO95HV-1^06240004.0282901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000161 | 113397999-13759-DETAIL-10_10_2024-SVCENTBK-1^07216001.0201107 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000162 | 113626898-52939-DETAIL-10_15_2024-SVCNEUT-1^07216001.0203000 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000163 | 113844574-77750-DETAIL-10_22_2024-GUYNOINS-1^07216001.0208601 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000164 | 113844574-77750-DETAIL-10_22_2024-GUYNOINS-2^07216001.0208601 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000165 | 115282156-47300-DTLTRT-11_01_2023-GO95HV-1^668010/00 3/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000166 | 115404717-93329-DTLSB-08_30_2022-GO95MLD-1^06243004.0097900 | OTHER | Non-HFTD | Distribution | 2022-08-30 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000167 | 115931461-34939-DETAIL-03_07_2023-GO95MLD-1^07117002.0210403 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000168 | 116096985-42060-DTLSB-02_02_2023-GO95MLD-1^06248001.0368102 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000169 | 116099638-11301-DETAIL-10_25_2024-GO95TCH-1^07216001.0202440 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000170 | 116144389-74729-DETAIL-05_14_2024-GO95MLD-1^06142012.0122410 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000171 | 116167998-46550-DETAIL-03_20_2025-GRDRODHI-1^06239003.0016304 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000172 | 116471243-42260-DTLTRT-05_23_2024-GO95HV-1^06243001.0119000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000173 | 116573013-15580-DETAIL-04_11_2023-GO95MLD-1^06240004.0168412 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000174 | 116811934-67449-DTLSB-02_08_2024-GO95MLD-1^07216001.0197103 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000175 | 117158438-8560-DETAIL-04_10_2024-GO95MLD-1^06245002.0113500 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000176 | 117158438-8560-DETAIL-04_10_2024-GRDRODHI-1^06245002.0113500 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000177 | 116882231-56709-DTLSB-08_26_2024-GO95HV-1^06245007.0110100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000178 | 117366371-52239-DETAIL-02_29_2024-GO95CL10-1^07113001.0106500 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000179 | 117366371-52239-DETAIL-02_29_2024-GO95MLD-1^07113001.0106500 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000180 | 117469848-72290-DETAIL-01_28_2025-GO95HV-1^06239004.0244202 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000181 | 117826615-37940-DETAIL-02_25_2025-SVCDEFLC-1^06240004.0151501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000182 | 118042495-90069-DETAIL-07_11_2023-GO95HV-1^06244008.0291001 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000183 | 118042495-90069-DETAIL-07_11_2023-GO95MLD-1^06244008.0291001 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000184 | 118176976-32949-DETAIL-10_15_2024-ANCHIDLE-1^07216001.0204501 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000185 | 118176976-32949-DETAIL-10_15_2024-GO95HV-1^07216001.0204501 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000186 | 118176976-32949-DETAIL-10_15_2024-GO95MLD-1^07216001.0204501 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000187 | 118894064-21849-DTLSB-02_06_2024-SVCDEFLC-1^07216001.0308700 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000188 | 119096861-43849-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0146001 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000189 | 119327838-40160-DTLSB-05_16_2024-GO95HV-1^06244002.0204500 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000190 | 119719140-49540-DTLTRT-11_16_2022-GO95MLD-1^668075/00 3/027 | OTHER | Non-HFTD | Transmission | 2022-11-16 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000191 | 119861313-43312-DETAIL-06_20_2024-GO95MLD-1^06244005.0239400 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000192 | 120029134-30009-DTLSB-04_23_2024-GO95MLD-1^06245007.0224801 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000193 | 120239824-70924-DETAIL-04_25_2024-GO95HV-1^06142016.0162200 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000194 | 120356244-39581-DTLSB-07_25_2023-GO95MLD-1^06243009.0056403 | OTHER | Non-HFTD | Distribution | 2023-07-25 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000195 | 120875958-54743-AUDIT-06_20_2024-SVCWIND-1^06245007.0222840 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000196 | 120882964-19449-DTLSB-04_23_2024-GO95MLD-1^06245007.0224703 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000197 | 120965224-51960-DETAIL-10_16_2024-GO95HV-1^07216001.0206702 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000198 | 120965224-51960-DETAIL-10_16_2024-GO95MLD-1^07216001.0206702 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000199 | 120980001-51970-DTLTRT-09_25_2023-GUYNOINS-2^668010/00 4A/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-09-25 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000200 | 121178396-56179-DETAIL-04_08_2024-GRDRODHI-1^06147005.0232003 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000201 | 121716393-25360-DTLSB-02_07_2023-GO95HV-1^06248001.0155300 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000202 | 117366371-52239-DETAIL-02_29_2024-GO95HV-1^07113001.0106500 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000203 | 117432100-10529-DETAIL-05_07_2024-GO95MLD-1^06142012.0122105 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000204 | 117643863-32150-DETAIL-01_23_2025-GO95HV-1^06239004.0256806 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000205 | 117643863-32150-DETAIL-01_23_2025-GO95MLD-1^06239004.0256806 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000206 | 117643863-32150-DETAIL-01_23_2025-GO95TCH-1^06239004.0256806 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000207 | 117817019-41649-DETAIL-08_19_2024-GO95HV-1^06245005.0258601 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000208 | 117892112-53550-DETAIL-03_19_2025-SVCDEFLC-1^06238004.0027401 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000209 | 118551294-67649-DTLSB-02_07_2024-SVCDEFLC-1^07216001.0199402 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000210 | 118872924-99860-DTLSB-05_07_2024-GO95HV-1^06245001.0191300 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000211 | 118872924-99860-DTLSB-05_07_2024-GO95MLD-1^06245001.0191300 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000212 | 118949654-39-DTLSB-02_14_2024-GO95HV-1^07216001.0198310 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000213 | 119454256-75772-DETAIL-06_06_2023-GO95MLD-1^06244010.0347600 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000214 | 119628424-10259-DTLSB-02_08_2024-GO95MLD-1^07216001.0308905 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000215 | 119717064-48289-DETAIL-02_24_2022-SVCROAD-1^06146005.0160100 | OTHER | Non-HFTD | Distribution | 2022-02-24 | 2025-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000216 | 119955552-57450-DETAIL-02_06_2025-GO95MLD-1^06239004.0135201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000217 | 120029134-30009-DTLSB-04_23_2024-SVCENTCO-1^06245007.0224801 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000218 | 120511613-89334-DETAIL-05_01_2024-GO95HV-1^06143015.0335800 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000219 | 120980001-51970-DTLTRT-09_25_2023-GUYNOINS-1^668010/00 4A/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-09-25 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000220 | 121092155-57960-DTLSB-05_07_2024-GO95MLD-1^06245001.0303401 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000221 | 121178396-56179-DETAIL-04_08_2024-GO95MLD-1^06147005.0232003 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000222 | 122211924-3660-DTLSB-02_07_2023-GO95MLD-1^06248001.0158200 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000223 | 12304680-14970-AUDIT-02_26_2025-GO95BLTC-1^06240004.0165505 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000224 | 123287494-50260-DETAIL-10_25_2024-GO95MLD-1^07216001.0209801 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000225 | 12331306-52169-DTLSB-05_14_2024-GO95MLD-1^06244001.0293901 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000226 | 123692104-63560-DETAIL-02_15_2023-CONDFRAY-1^06247002.0232600 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000227 | 123692104-63560-DETAIL-02_15_2023-CONDFRAY-2^06247002.0232600 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000228 | 123692104-63560-DETAIL-02_15_2023-GO95MLD-1^06247002.0232600 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000229 | 124332333-76280-DTLTRT-09_27_2023-GO95HV-1^668010/00 9/006 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000230 | 124607216-81698-DETAIL-02_03_2025-SVCENTBK-1^06239004.0244945 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000231 | 12462686-28649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293900 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000232 | 124986856-66949-DETAIL-08_20_2024-GO95HV-1^06245004.0200900 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000233 | 125144764-26130-DETAIL-09_19_2024-SVCDEFLC-1^06241005.0366201 | OTHER | HFTD Tier 2 | Distribution | 2024-09-19 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000234 | 12595954-5259-DTLSB-02_07_2024-GO95TCH-1^07216001.0199209 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000235 | 126073373-43870-DTLSB-05_08_2024-GO95MLD-1^06245001.0340000 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000236 | 126277464-71080-DTLTRT-09_27_2023-GO95MLD-1^668010/00 4/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000237 | 126356022-50680-DETAIL-02_12_2025-GO95HV-1^06240004.0282701 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000238 | 126931225-42669-DTLTRT-07_21_2022-GUYSLACK-1^668005/00 6/058 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-07-21 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000239 | 127389073-30539-DETAIL-03_14_2023-GO95MLD-1^07114001.0276300 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000240 | 127476374-28232-AUDIT-03_04_2025-GUYHINS-1^06241005.0120104 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000241 | 127561620-22559-DTLSB-02_16_2024-GO95MLD-1^07216001.0264205 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000242 | 128109878-23699-DETAIL-03_18_2024-GO95MLD-1^06245006.0010901 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000243 | 128459689-54790-DETAIL-01_15_2025-GO95HV-1^06239004.0256102 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000244 | 12876338-82748-DETAIL-05_22_2023-GO95MLD-1^06245005.0276200 | OTHER | Non-HFTD | Distribution | 2023-05-22 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000245 | 129171379-28622-DETAIL-06_28_2023-GO95MLD-1^06244009.0363001 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000246 | 129375461-12391-ENHANCED-01_27_2025-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2025-01-27 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000247 | 121475103-37103-DTLSB-08_14_2023-GO95MLD-1^06243009.0246002 | OTHER | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000248 | 121805343-60750-DETAIL-02_04_2025-GO95MLD-1^06239004.0244950 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000249 | 122204661-83249-DETAIL-02_20_2024-GO95HV-1^07113002.0193900 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000250 | 122204661-83249-DETAIL-02_20_2024-GO95TCH-1^07113002.0193900 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000251 | 122419691-78729-DTLSB-09_28_2023-GO95MLD-1^06243008.0101600 | OTHER | HFTD Tier 2 | Distribution | 2023-09-28 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000252 | 123021895-59439-DETAIL-06_07_2023-GO95HV-1^06244006.0012800 | OTHER | Non-HFTD | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000253 | 1230992-799-DETAIL-06_15_2023-GO95MLD-1^06244009.0307600 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000254 | 123301443-79651-DETAIL-03_03_2025-GUYHINS-1^06241004.0180100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000255 | 123301443-79651-DETAIL-03_03_2025-GUYHINS-2^06241004.0180100 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000256 | 123391146-11460-DETAIL-04_18_2024-GO95HV-1^06145001.0362901 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000257 | 123692104-63560-DETAIL-02_15_2023-CONDFRAY-3^06247002.0232600 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000258 | 123692104-63560-DETAIL-02_15_2023-CONDFRAY-4^06247002.0232600 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000259 | 123869089-80349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061603 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000260 | 123869089-80349-DETAIL-03_18_2024-GUYNOINS-1^06245005.0061603 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000261 | 12393639-91259-DETAIL-05_30_2024-GO95MLD-1^06246005.0339400 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000262 | 124521753-67270-DTLTRT-09_26_2023-GO95HV-1^668010/00 4/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-26 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000263 | 124573260-48769-DETAIL-07_31_2024-GO95BLTC-1^06244005.0333900 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000264 | 124573260-48769-DETAIL-07_31_2024-GO95HV-1^06244005.0333900 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000265 | 12462686-28649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293900 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000266 | 124963399-78389-DETAIL-03_06_2024-GO95HV-1^06147004.0017302 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000267 | 125047458-70050-DETAIL-01_16_2025-SVCDEFLC-1^06240004.0096602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000268 | 125096477-44879-DTLTRT-10_24_2023-GO95HV-1^668010/00 9/009 | OTHER | HFTD Tier 2 | Transmission | 2023-10-24 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000269 | 125226416-62470-DETAIL-05_05_2022-GO95MLD-1^07116001.0100103 | OTHER | HFTD Tier 2 | Distribution | 2022-05-05 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000270 | 125532318-72570-DETAIL-05_06_2024-GO95SVC-1^06142012.0125001 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000271 | 125786632-39632-DETAIL-02_18_2025-SVCDEFLC-1^06239004.0362405 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000272 | 129445793-20939-DTLSB-02_16_2024-GO95MLD-1^07216001.0272000 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000273 | 12945151-9479-DTLSB-08_27_2024-GUYHINS-1^06245007.0118900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000274 | 12945151-9479-DTLSB-08_27_2024-GUYHINS-2^06245007.0118900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000275 | 129531055-74070-DETAIL-02_07_2023-GO95HV-1^06147002.0097300 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000276 | 129608238-90338-DETAIL-03_26_2024-SVCROAD-1^06246005.0050401 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000277 | 129664966-33649-DETAIL-10_17_2024-GO95MLD-1^07216001.0202504 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000278 | 129868836-78949-DETAIL-08_20_2024-GO95HV-1^06245004.0196901 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000279 | 13004688-64519-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/072 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000280 | 130421324-97449-DETAIL-03_15_2023-GO95MLD-1^07114001.0335900 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000281 | 130421324-97449-DETAIL-03_15_2023-SVCENTCO-1^07114001.0335900 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000282 | 130429903-52579-ADMIN-07_18_2024-GO95STUB-1^06246009.0129903 | OTHER | HFTD Tier 2 | Distribution | 2024-07-18 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000283 | 130429903-52579-DETAIL-10_26_2022-GO95MLD-1^06246009.0129903 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000284 | 131164484-15429-DETAIL-04_04_2023-GUYHINS-1^06143013.0239001 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-04-04 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000285 | 131361125-39249-DETAIL-03_09_2023-SVCNEUT-1^07216001.0294602 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000286 | 131453084-71690-DETAIL-03_11_2025-GO95HV-1^06239003.0363502 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000287 | 131496130-89470-DETAIL-02_18_2025-GO95TCH-1^06240004.0220506 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000288 | 13160985-84233-DETAIL-03_06_2023-SVCENTCO-1^07117002.0196300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000289 | 131915026-83909-DETAIL-05_29_2024-GO95HV-1^06246005.0219702 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000290 | 131986096-7139-DETAIL-10_09_2024-GO95HV-1^07216001.0204111 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000291 | 131986096-7139-DETAIL-10_09_2024-GO95MLD-1^07216001.0204111 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000292 | 132008859-36659-DETAIL-03_28_2024-GO95HV-1^06246005.0043701 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000293 | 132331798-17123-DETAIL-03_14_2023-GO95MLD-1^07117003.0112604 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000294 | 132331798-17123-DETAIL-03_14_2023-GO95TCH-1^07117003.0112604 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000295 | 132507637-63479-DTLTRT-08_21_2023-SVCDEFLC-1^06243009.0213400 | OTHER | HFTD Tier 2 | Distribution | 2023-08-21 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000296 | 132754543-16069-DTLSB-10_07_2024-GO95MLD-1^06245007.0219300 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000297 | 125786632-39632-DETAIL-02_18_2025-SVCENTCO-1^06239004.0362405 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000298 | 125987169-62870-DTLTRT-09_29_2020-GO95HV-1^668018/00 16/006 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000299 | 126148308-6870-DETAIL-02_02_2023-GO95HV-1^06148002.0287001 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000300 | 126595696-88970-DETAIL-04_18_2024-GO95MLD-1^06145001.0268900 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000301 | 126883506-31878-DETAIL-05_09_2022-GO95MLD-1^07116001.0096301 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000302 | 126901099-91770-DTLSB-05_07_2024-GO95MLD-1^06245002.0137401 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000303 | 126905179-82029-DTLSB-08_14_2023-GO95MLD-1^06243009.0246103 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000304 | 127476374-28232-AUDIT-03_04_2025-GUYHINS-2^06241005.0120104 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000305 | 127561620-22559-DTLSB-02_16_2024-GO95TCH-1^07216001.0264205 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000306 | 127744741-34239-DETAIL-02_21_2024-SVCROAD-1^07113001.0138309 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000307 | 127965075-11763-DETAIL-04_24_2023-GO95HV-1^07117003.0025100 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000308 | 128392835-87990-DTLTRT-10_31_2023-GO95HV-1^668010/00 15/016 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000309 | 128500340-65163-DTLSB-04_11_2024-GO95HV-1^06245007.0220446 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000310 | 128604798-90690-DETAIL-01_21_2025-GO95MLD-1^06239004.0256301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000311 | 12876338-82748-DETAIL-05_22_2023-GUYHINS-1^06245005.0276200 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-05-22 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000312 | 128882438-770-DETAIL-04_23_2024-GO95MLD-1^06145001.0113900 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000313 | 129216988-42849-DTLSB-02_28_2024-GO95MLD-1^07216001.0260905 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000314 | 129241780-2609-DETAIL-11_09_2022-ABNDEQPM-1^06246008.0045300 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000315 | 12930260-94579-DTLSB-09_03_2024-GO95MLD-1^06245007.0016201 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000316 | 129375461-12391-ENHANCED-01_08_2025-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2025-01-08 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000317 | 129375461-90391-ENHANCED-01_08_2025-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2025-01-08 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000318 | 129375461-90391-ENHANCED-01_27_2025-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2025-01-27 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000319 | 129375461-95770-ENHANCED-01_08_2025-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2025-01-08 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000320 | 129375461-95770-ENHANCED-01_27_2025-IRSPOTOH-1^668067/00 2/001 | OTHER | HFTD Tier 2 | Transmission | 2025-01-27 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000321 | 129608238-90338-DETAIL-03_26_2024-SVCROAD-2^06246005.0050401 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000322 | 133056299-54209-DETAIL-06_04_2024-GO95HV-1^06246006.0362100 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000323 | 133411369-68970-DETAIL-04_10_2024-GO95MLD-1^06245002.0141900 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000324 | 133847981-28150-DETAIL-03_11_2025-GRDRODHI-1^06238004.0273801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000325 | 134252546-35461-DETAIL-02_24_2025-GO95MLD-1^06239004.0366902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000326 | 134762121-98473-DETAIL-03_09_2023-GUYLOINS-1^07117002.0202101 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000327 | 134803976-13019-DETAIL-03_25_2024-GO95HV-1^06147005.0144900 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000328 | 134947168-45943-DETAIL-01_14_2025-BIRDDMG-1^06240004.0098205 | POLE | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000329 | 13512760-74409-DETAIL-03_04_2024-XARMSPCR-1^06147004.0025201 | CROSSARM | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000330 | 135169465-18349-DETAIL-02_27_2024-GO95MLD-1^07113002.0182600 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000331 | 135246418-32658-DTLSB-02_15_2024-GO95HV-1^07216001.0263000 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000332 | 135267901-1829-DETAIL-05_07_2024-GO95HV-1^06142012.0122107 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000333 | 135281146-359-DETAIL-03_28_2024-BIRDDMG-1^06247005.0333600 | POLE | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000334 | 135677450-27180-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 5A/046 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000335 | 135930326-72639-DETAIL-02_27_2024-GO95HV-1^07113002.0182400 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000336 | 13599681-64469-DTLTRT-07_20_2022-GO95MLD-1^668005/00 5/054 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000337 | 136125046-65149-DETAIL-03_06_2023-GO95HV-1^07216001.0297706 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000338 | 136125046-65149-DETAIL-03_06_2023-GRDRODHI-1^07216001.0297706 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000339 | 136125046-65149-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297706 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000340 | 136214573-62960-DETAIL-01_13_2025-GO95BLTC-1^06240004.0072343 | OTHER | HFTD Tier 3 | Distribution | 2025-01-13 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000341 | 136285215-42833-DETAIL-03_08_2023-GO95MLD-1^07117002.0198000 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000342 | 136285215-42833-DETAIL-03_08_2023-GO95TCH-1^07117002.0198000 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000343 | 136337600-76159-DTLTRT-07_05_2022-GO95MLD-1^668005/00 8/034 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000344 | 136538972-94031-DETAIL-03_03_2025-GUYHINS-1^06241004.0181102 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000345 | 136546375-34490-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 5/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000346 | 136546375-64302-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 5/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000347 | 129684470-92270-DETAIL-03_19_2025-GO95HV-1^06239002.0018601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000348 | 129891659-67739-DETAIL-10_15_2024-GO95CL10-1^07216001.0202410 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000349 | 130400893-51893-DETAIL-04_29_2024-GO95MLD-1^06142016.0068100 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000350 | 130433446-46549-DETAIL-10_21_2024-GO95HV-1^07216001.0202801 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000351 | 130745758-36740-DETAIL-03_20_2025-GO95HV-1^06239003.0019004 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000352 | 131148121-36369-DTLTRT-06_02_2021-GO95HV-1^668041/00 12/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000353 | 131361125-39249-DETAIL-03_09_2023-GO95MLD-1^07216001.0294602 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000354 | 131361125-39249-DETAIL-03_09_2023-GO95TCH-1^07216001.0294602 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000355 | 131514982-15982-DETAIL-02_27_2023-GO95TCH-1^07216001.0298811 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000356 | 131766095-45449-DETAIL-10_14_2024-GO95MLD-1^07216001.0203300 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000357 | 132045652-72350-DETAIL-03_26_2025-GO95HV-1^06239004.0139000 | OTHER | HFTD Tier 3 | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000358 | 132197649-91269-ADMIN-03_25_2025-POLEDERP-1^668002/00 11/066 | POLE | HFTD Tier 2 | Transmission | 2025-03-25 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000359 | 132385588-13359-DTLSB-02_15_2024-GO95MLD-1^07216001.0190701 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000360 | 132488233-50333-DETAIL-02_28_2024-GO95MLD-1^07113002.0073340 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000361 | 132488233-50333-DETAIL-02_28_2024-GO95TCH-1^07113002.0073340 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000362 | 132565820-33568-DETAIL-02_27_2025-GO95BLTC-1^06241005.0173601 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000363 | 132609718-3150-DETAIL-09_10_2024-SVCDEFLC-1^06240004.0092503 | OTHER | HFTD Tier 2 | Distribution | 2024-09-10 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000364 | 132899163-23479-DETAIL-11_07_2022-GO95MLD-1^06246009.0131900 | OTHER | HFTD Tier 2 | Distribution | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000365 | 133095231-64773-DETAIL-07_01_2024-BIRDDMG-1^06245007.0309601 | POLE | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000366 | 133284898-83970-DTLSB-02_08_2023-GRDRODHI-1^06248001.0228900 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000367 | 133947108-20670-DETAIL-04_11_2023-GO95MLD-1^06240004.0167502 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000368 | 134184641-29370-DTLSB-02_15_2023-GO95MLD-1^06248002.0349500 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000369 | 134267240-95170-DETAIL-03_19_2025-GO95HV-1^06239002.0014602 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000370 | 134526310-3649-DETAIL-03_16_2023-GO95MLD-1^07113001.0043501 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000371 | 136902208-84389-DETAIL-07_30_2024-GRDRODHI-2^06244005.0355400 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000372 | 137157923-43329-ADMIN-07_11_2024-POLEREPL-1^06243009.0122302 | POLE | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000373 | 137334781-16521-DETAIL-02_19_2025-BIRDDMG-1^06241005.0229901 | POLE | HFTD Tier 3 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000374 | 137445278-48180-DTLSB-02_02_2023-GRDRODHI-1^06247001.0010202 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000375 | 137445278-48180-DTLSB-02_02_2023-GRDRODHI-2^06247001.0010202 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000376 | 137492579-84013-DETAIL-07_23_2024-GO95MLD-1^06245006.0145342 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000377 | 137519586-13789-DETAIL-08_08_2024-GO95MLD-1^06245006.0094201 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000378 | 138393338-46849-DTLSB-02_21_2024-COPLLEAN-1^07216001.0262505 | POLE | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000379 | 13929545-90089-DETAIL-03_03_2025-GUYHINS-1^06241005.0131401 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000380 | 13929545-90089-DETAIL-03_03_2025-GUYHINS-2^06241005.0131401 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000381 | 139461614-10960-DETAIL-01_30_2025-GRDRODHI-1^06239004.0131040 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000382 | 13955005-20149-DETAIL-02_29_2024-GO95HV-1^07113001.0158801 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000383 | 139598001-70149-DETAIL-04_04_2023-GUYLOINS-1^06245006.0222400 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-04-04 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000384 | 139670583-73419-ADMIN-07_05_2024-GO95STUB-1^06240008.0155000 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000385 | 13967892-87892-DTLTRT-02_14_2023-GO95BLTC-1^06248001.0342702 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000386 | 139682759-21859-DETAIL-03_13_2023-SVCENTCO-1^07216001.0292544 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000387 | 139700216-91223-DTLSB-04_29_2024-GO95MLD-1^06245007.0221643 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000388 | 139817135-1349-DETAIL-03_14_2024-GO95HV-1^06245006.0127902 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000389 | 140102398-42143-DETAIL-03_09_2023-SVCNEUT-1^07117002.0205208 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000390 | 140141658-74480-DETAIL-04_22_2024-GO95HV-1^06145001.0029304 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000391 | 140309459-86769-DTLTRT-10_10_2022-POLEDERP-1^668005/03 12/004 | POLE | Non-HFTD | Transmission | 2022-10-10 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000392 | 140522598-41389-DETAIL-04_16_2024-GO95MLD-1^06145001.0129100 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000393 | 140681891-16730-DETAIL-01_24_2025-GO95CL10-1^06240004.0185900 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000394 | 140681891-16730-DETAIL-01_24_2025-SVCNEUT-1^06240004.0185900 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000395 | 140852151-10559-DETAIL-02_21_2024-CLMBTRE-1^07113001.0138205 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000396 | 141642151-93151-DETAIL-02_05_2025-GO95HV-1^06240004.0165201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000397 | 134747980-51949-DETAIL-08_13_2024-GO95HV-1^06245005.0360700 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000398 | 13502633-92049-DETAIL-03_16_2023-GO95MLD-1^07114001.0299801 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000399 | 135071564-43564-DETAIL-01_30_2025-GRDRODHI-1^06240004.0160900 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000400 | 135138335-20040-ADMIN-04_04_2025-POLEDERP-1^06240004.0218701 | POLE | HFTD Tier 2 | Distribution | 2025-04-04 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000401 | 135246418-32658-DTLSB-02_15_2024-GO95MLD-1^07216001.0263000 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000402 | 135267901-1829-DETAIL-05_07_2024-SVCENTCO-1^06142012.0122107 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000403 | 135379154-49970-DTLSB-05_07_2024-GO95MLD-1^06245001.0192001 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000404 | 135386233-59399-DTLSB-10_01_2024-GO95MLD-1^06245007.0231901 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000405 | 135510969-26080-DETAIL-04_24_2024-GO95MLD-1^06145001.0089902 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000406 | 135510969-26080-DETAIL-04_24_2024-GRDRODHI-1^06145001.0089902 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000407 | 135510969-26080-DETAIL-04_24_2024-XARMSPCR-1^06145001.0089902 | CROSSARM | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000408 | 135513444-20079-DETAIL-07_31_2024-GO95MLD-1^06244005.0338900 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000409 | 135530566-46479-DETAIL-03_25_2024-GO95MLD-1^06147005.0134700 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000410 | 135787351-57180-DETAIL-05_06_2024-GO95MLD-1^06142012.0124110 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000411 | 135787739-83919-ADMIN-10_28_2022-UBPBXARM-1^668036/00 5/053 | CROSSARM | Non-HFTD | Transmission | 2022-10-28 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000412 | 135945763-41339-AUDIT-03_07_2024-ABNDEQPM-1^07216001.0188201 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000413 | 135945763-41339-DTLSB-02_13_2024-GO95HV-1^07216001.0188201 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000414 | 135945763-41339-DTLSB-02_13_2024-GO95MLD-1^07216001.0188201 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000415 | 136125046-65149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297706 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000416 | 136222193-74959-DETAIL-06_06_2024-GO95MLD-1^06246006.0351303 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000417 | 136229869-1790-DETAIL-01_28_2025-GO95HV-1^06239004.0245100 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000418 | 136337600-76159-DTLTRT-07_05_2022-GO95HV-1^668005/00 8/034 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000419 | 136538972-94031-DETAIL-03_03_2025-GUYHINS-2^06241004.0181102 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000420 | 136829511-53880-DTLTRT-10_24_2022-GO95HV-1^668001/00 19/023 | OTHER | Non-HFTD | Transmission | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000421 | 136902208-84389-DETAIL-07_30_2024-GRDRODHI-1^06244005.0355400 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000422 | 142040518-5169-DTLTRT-10_23_2023-GO95HV-1^668010/00 10/044 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000423 | 142555954-74910-DETAIL-03_13_2025-GO95HV-1^06238004.0154000 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000424 | 142594694-35629-DTLSB-08_09_2023-GO95MLD-1^06243009.0194200 | OTHER | HFTD Tier 2 | Distribution | 2023-08-09 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000425 | 14267670-77179-AUDIT-04_18_2024-GO95MLD-1^06147005.0147902 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000426 | 142798613-27059-DETAIL-05_29_2024-GO95HV-1^06246005.0098101 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000427 | 142881971-23150-DETAIL-03_11_2025-GO95HV-1^06238004.0274804 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000428 | 142902731-26809-DETAIL-03_11_2024-GO95HV-1^06147004.0039600 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000429 | 142994032-7931-DETAIL-05_11_2022-GO95MLD-1^06241005.0130800 | OTHER | HFTD Tier 2 | Distribution | 2022-05-11 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000430 | 142995104-74799-DETAIL-03_06_2024-GO95HV-1^06147005.0177800 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000431 | 143124519-2980-DTLSB-05_07_2024-CONDFRAY-1^06245002.0248700 | CONDUCTOR | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000432 | 143581960-45609-DETAIL-11_02_2022-GO95HV-1^06246008.0101800 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000433 | 143778886-19280-DRONE_VS-11_13_2024-BIRDDMG-1^668038/00 5/053 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000434 | 144047621-13350-DETAIL-02_11_2025-GO95MLD-1^06239004.0124900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000435 | 144054704-77839-DETAIL-07_11_2024-GO95HV-1^06244005.0219200 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000436 | 144252176-31500-DTLTRT-11_01_2023-GO95HV-1^668010/00 6/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000437 | 144614035-52239-DETAIL-03_13_2023-SVCWIND-1^07216001.0295401 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000438 | 144923488-86780-DETAIL-01_30_2023-GO95MLD-1^06147003.0191000 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000439 | 145214479-82079-DTLTRT-10_25_2022-GO95HV-1^668075/00 7/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000440 | 145214479-82079-DTLTRT-10_25_2022-GO95MLD-1^668075/00 7/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000441 | 145214479-82079-DTLTRT-10_25_2022-GRDRODHI-1^668075/00 7/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000442 | 145230481-19859-DETAIL-02_29_2024-SVCENTCO-1^07113001.0114000 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000443 | 14559258-6530-DETAIL-02_27_2025-GO95MLD-1^06240003.0304401 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000444 | 145759974-32074-DETAIL-03_09_2023-GO95HV-1^07117002.0207100 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000445 | 145821208-58330-DETAIL-01_15_2025-GO95CL10-1^06240004.0096300 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000446 | 14590471-21149-DETAIL-02_28_2024-GO95TCH-1^07113001.0138803 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000447 | 136905062-61750-DETAIL-03_20_2025-GO95HV-1^06239003.0016103 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000448 | 136929681-42649-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0030400 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000449 | 137376484-45360-DETAIL-01_22_2025-SVCDEFLC-1^06239004.0255502 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000450 | 137861134-25553-DTLSB-10_01_2024-GO95HV-1^06245007.0230541 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000451 | 137899349-13792-DETAIL-06_14_2023-GO95HV-1^06244010.0288301 | OTHER | HFTD Tier 2 | Distribution | 2023-06-14 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000452 | 138016491-78402-DETAIL-07_03_2024-GO95HV-1^06244005.0234603 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000453 | 13833203-44349-DTLSB-10_02_2024-GO95HV-1^06245007.0215401 | OTHER | HFTD Tier 2 | Distribution | 2024-10-02 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000454 | 138775110-7549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105701 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000455 | 139003006-26980-DETAIL-03_25_2024-GO95HV-1^06147005.0149902 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000456 | 139461614-10960-DETAIL-01_30_2025-GO95MLD-1^06239004.0131040 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000457 | 139589885-65529-DETAIL-08_07_2024-GO95HV-1^06245008.0229200 | OTHER | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000458 | 139598001-70149-DETAIL-04_04_2023-GO95MLD-1^06245006.0222400 | OTHER | Non-HFTD | Distribution | 2023-04-04 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000459 | 139653703-6280-DTLSB-05_22_2024-GO95MLD-1^06243001.0114100 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000460 | 13995679-79649-DTLSB-04_23_2024-GO95MLD-1^06245007.0224406 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000461 | 140102398-42143-DETAIL-03_09_2023-GO95MLD-1^07117002.0205208 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000462 | 140119638-36989-DETAIL-07_29_2024-GO95MLD-1^06245006.0149701 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000463 | 140889368-95920-DETAIL-09_06_2024-SVCDEFLC-1^06240004.0081540 | OTHER | HFTD Tier 2 | Distribution | 2024-09-06 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000464 | 141498613-96250-DETAIL-02_04_2025-SVCROAD-1^06239004.0135149 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000465 | 141561426-13370-DETAIL-01_16_2025-GO95HV-1^06239004.0257603 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000466 | 142007546-93979-DETAIL-04_03_2024-GO95MLD-1^06247005.0339700 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000467 | 142026310-99789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223600 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000468 | 142040518-5169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 10/044 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000469 | 142370520-52559-DTLSB-02_19_2024-SVCWIND-1^07216001.0262102 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000470 | 142798126-66372-DETAIL-06_06_2023-GO95HV-1^06244010.0342403 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000471 | 142931423-52513-DTLSB-04_24_2024-SVCWIND-1^06245007.0227545 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000472 | 143124519-2980-DTLSB-05_07_2024-GO95MLD-1^06245002.0248700 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000473 | 145929694-69759-DETAIL-05_17_2022-GO95HV-1^07117001.0319403 | OTHER | Non-HFTD | Distribution | 2022-05-17 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000474 | 145929694-69759-DETAIL-05_17_2022-GO95MLD-1^07117001.0319403 | OTHER | Non-HFTD | Distribution | 2022-05-17 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000475 | 146303403-64403-DETAIL-05_24_2023-GO95MLD-1^06245006.0352201 | OTHER | Non-HFTD | Distribution | 2023-05-24 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000476 | 146344788-49229-DETAIL-06_28_2023-GO95HV-1^06244009.0368800 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000477 | 146463551-34551-DETAIL-03_04_2024-GO95MLD-1^06147004.0015202 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000478 | 146500895-69480-DTLSB-05_14_2024-GO95MLD-1^06244001.0201000 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000479 | 146825361-33459-DETAIL-02_29_2024-GUYNOINS-1^07113001.0113002 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000480 | 146825361-33459-DETAIL-02_29_2024-GUYNOINS-2^07113001.0113002 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000481 | 147223368-33470-DETAIL-02_26_2025-CLRTOUCH-1^06240004.0064001 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-26 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000482 | 147346581-96989-ADMIN-04_11_2024-XARMSPCR-1^06246001.0314401 | CROSSARM | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000483 | 147723876-29502-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 6/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000484 | 147729206-13572-DETAIL-06_05_2024-GO95HV-1^06245006.0032040 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000485 | 148142351-7489-DTLSB-08_27_2024-GO95MLD-1^06245007.0118600 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000486 | 148899671-44469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 9/006 | CROSSARM | Non-HFTD | Transmission | 2023-09-12 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000487 | 149165073-60749-DETAIL-03_21_2023-GO95MLD-1^07113001.0059400 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000488 | 149244089-59090-DETAIL-01_16_2025-SVCDEFLC-1^06239004.0257209 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000489 | 149372389-769-ADMIN-08_02_2024-POLEREPL-1^668033/00 5/010 | POLE | HFTD Tier 2 | Transmission | 2024-08-02 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000490 | 149373461-62028-DTLSB-02_05_2024-CLMBTRE-1^07216001.0190901 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000491 | 149373461-62028-DTLSB-02_05_2024-GRDRODHI-1^07216001.0190901 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000492 | 149401664-35389-DTLSB-08_31_2023-GO95MLD-1^06243008.0025801 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000493 | 149550143-96021-DETAIL-02_18_2025-GO95TCH-1^06239004.0363700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000494 | 149550143-96021-DETAIL-02_18_2025-SVCENTCO-1^06239004.0363700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000495 | 149940304-46490-DETAIL-04_25_2023-GO95TCH-1^06241004.0314100 | OTHER | HFTD Tier 2 | Distribution | 2023-04-25 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000496 | 150072533-98429-DETAIL-06_07_2023-GO95MLD-1^06244010.0276801 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000497 | 150196066-32049-DETAIL-08_06_2024-GO95HV-1^06245004.0334101 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000498 | 150290600-1949-DTLSB-02_16_2024-SVCENTCO-1^07216001.0260007 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000499 | 143266651-61579-DETAIL-01_09_2023-GO95MLD-1^06148003.0143200 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000500 | 143266651-61579-DETAIL-01_09_2023-GRDRODHI-1^06148003.0143200 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000501 | 143465485-15080-DETAIL-02_07_2023-GO95HV-1^06147002.0047401 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000502 | 143694-36860-DETAIL-01_16_2025-GO95HV-1^06239004.0257608 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000503 | 144879586-85079-DETAIL-02_06_2023-GO95MLD-1^06147002.0200200 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000504 | 14502329-6639-DETAIL-07_30_2024-GO95HV-1^06244005.0358400 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000505 | 145178571-20859-DETAIL-06_06_2024-GO95HV-1^06246006.0265000 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000506 | 145178571-20859-DETAIL-06_06_2024-GO95MLD-1^06246006.0265000 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000507 | 145214130-72649-DTLSB-04_09_2024-SVCWIND-1^06245007.0223300 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000508 | 145462279-47249-DETAIL-03_02_2023-GO95TCH-1^07216001.0298600 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000509 | 145759974-32074-DETAIL-03_09_2023-GO95MLD-1^07117002.0207100 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000510 | 145821208-58330-DETAIL-09_09_2024-SVCDEFLC-1^06240004.0096300 | OTHER | HFTD Tier 2 | Distribution | 2024-09-09 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000511 | 145970734-81380-DTLSB-05_08_2024-GO95MLD-1^06245001.0336300 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000512 | 146039539-40349-DTLSB-10_02_2024-BIRDDMG-1^06245007.0217802 | POLE | HFTD Tier 2 | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000513 | 146881085-43600-DETAIL-03_13_2025-GO95HV-1^06239003.0244001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000514 | 14715359-54489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0174101 | POLE | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000515 | 147723876-13490-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 6/019 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000516 | 147945450-84270-DETAIL-02_20_2025-PWRTRN-1^06240004.0211400 | OTHER | HFTD Tier 2 | Distribution | 2025-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000517 | 148078075-55149-DETAIL-10_14_2024-GO95MLD-1^07216001.0204208 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000518 | 148588861-86094-ADMIN-04_21_2023-GO95TCH-1^06142016.0054004 | OTHER | Non-HFTD | Distribution | 2023-04-21 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000519 | 150328463-3049-DETAIL-03_15_2023-GUYHINS-1^07216001.0291501 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000520 | 150347940-64669-DRONE_HY-10_18_2023-GO95HV-1^668033/00 6/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000521 | 15046990-18309-DETAIL-08_21_2024-GO95HV-1^06245006.0109903 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000522 | 150503843-43489-AUDIT-08_27_2024-ABNDEQPM-1^06244005.0283305 | OTHER | Non-HFTD | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000523 | 150511328-39899-DTLSB-08_22_2024-GO95MLD-1^06245006.0325400 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000524 | 150931676-2489-DETAIL-03_20_2024-SVCENTCO-1^06244005.0142100 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000525 | 151544303-77303-DETAIL-05_24_2023-GO95HV-1^06245006.0352200 | OTHER | Non-HFTD | Distribution | 2023-05-24 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000526 | 151554826-92579-DETAIL-04_04_2024-GO95MLD-1^06147005.0132003 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000527 | 151609833-20239-DETAIL-03_21_2023-GUYHINS-1^07113001.0058501 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000528 | 151896809-26790-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0106501 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000529 | 152154020-9901-DETAIL-01_21_2025-GO95HV-1^06239004.0255447 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000530 | 152357633-36069-DTLSB-10_07_2024-XARMSPCR-1^06245007.0219301 | CROSSARM | Non-HFTD | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000531 | 152410316-14598-DETAIL-01_31_2025-SVCDEFLC-1^06239004.0242901 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000532 | 152469535-23669-ADMIN-10_12_2022-TRNSLOOS-1^668005/00 8/058 | CONNECTION DEVICE | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000533 | 152483734-59099-DTLSB-02_09_2023-GO95MLD-1^06248001.0228501 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000534 | 152552484-95484-DETAIL-04_29_2024-GO95HV-1^06142016.0175502 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000535 | 152893203-67290-DETAIL-02_02_2023-GO95HV-1^06148002.0337700 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000536 | 152896437-58437-DETAIL-01_30_2025-GO95MLD-1^06239004.0245700 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000537 | 153089721-43430-DTLTRT-10_30_2023-GO95HV-1^668010/00 15/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-30 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000538 | 153238270-59270-DETAIL-04_03_2024-GO95HV-1^06247005.0298700 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000539 | 153297724-96980-DTLTRT-09_27_2023-GUYNOINS-1^668010/00 20/006 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000540 | 153432064-24789-DETAIL-07_12_2023-GO95MLD-1^06244008.0271300 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000541 | 153471741-38690-DTLTRT-10_24_2022-GO95HV-1^668001/00 11/023 | OTHER | Non-HFTD | Transmission | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000542 | 153792948-43970-DETAIL-02_03_2025-GO95HV-1^06240004.0167901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000543 | 153840069-10759-DETAIL-02_22_2024-GO95HV-1^07216001.0352100 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000544 | 148899671-44469-DRONE_HY-09_13_2023-EARMSPCR-1^668002/00 9/006 | OTHER | Non-HFTD | Transmission | 2023-09-13 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000545 | 149136181-1090-DETAIL-04_16_2024-GO95MLD-1^06145002.0182801 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000546 | 149244089-59090-DETAIL-01_16_2025-SVCENTCO-1^06239004.0257209 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000547 | 149373461-62028-DTLSB-02_05_2024-GO95MLD-1^07216001.0190901 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000548 | 149373461-62028-DTLSB-02_05_2024-GRDRODHI-2^07216001.0190901 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000549 | 149619052-13390-DETAIL-02_13_2023-GO95HV-1^06247002.0117700 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000550 | 150056226-45790-DETAIL-02_15_2023-GO95HV-1^06247002.0144501 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000551 | 150263753-84890-DTLSB-07_17_2023-GO95MLD-1^06243010.0116500 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000552 | 150290600-1949-DTLSB-02_16_2024-GO95MLD-1^07216001.0260007 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000553 | 150328463-3049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291501 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000554 | 150347940-64670-DRONE_HY-10_18_2023-GO95HV-1^668033/00 6/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000555 | 15046990-18309-DETAIL-08_21_2024-GO95MLD-1^06245006.0109903 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000556 | 150492401-64990-DTLSB-02_15_2023-GO95MLD-1^06248001.0308300 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000557 | 150651549-95409-DTLSB-08_27_2024-GO95MLD-1^06245007.0122900 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000558 | 150653365-98790-DTLTRT-10_31_2023-GO95HV-1^668010/00 9/016 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000559 | 150681733-75849-DETAIL-08_13_2024-SVCDEFLC-1^06245005.0361101 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000560 | 150806471-38433-DETAIL-01_14_2025-POLETOP-1^06240004.0079803 | POLE | HFTD Tier 2 | Distribution | 2025-01-14 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000561 | 151529509-87590-DETAIL-04_11_2024-GO95HV-1^06245002.0102301 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000562 | 151529509-87590-DETAIL-04_11_2024-GO95MLD-1^06245002.0102301 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000563 | 151554826-92579-DETAIL-04_04_2024-GRDRODHI-1^06147005.0132003 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000564 | 151554826-92579-DETAIL-04_04_2024-SVCDEFLC-1^06147005.0132003 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000565 | 151609833-20239-DETAIL-03_21_2023-GO95HV-1^07113001.0058501 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000566 | 151692912-34912-DETAIL-04_02_2024-GO95MLD-1^06247005.0340001 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000567 | 152275368-25399-DTLSB-07_02_2024-GO95MLD-1^06245006.0187200 | OTHER | Non-HFTD | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000568 | 152443534-89909-DTLSB-04_23_2024-SVCENTCO-1^06245007.0224803 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000569 | 153916893-10489-DETAIL-04_03_2024-BIRDDMG-1^06247005.0298903 | POLE | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000570 | 154218387-38387-DTLSB-05_21_2024-GO95HV-1^06244002.0140200 | OTHER | Non-HFTD | Distribution | 2024-05-21 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000571 | 154246805-54090-DETAIL-10_22_2024-CLRTOUCH-1^07216001.0208503 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000572 | 154286043-26240-DRONE_VS-11_13_2024-UBPBXARM-1^668010/00 11/024 | CROSSARM | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000573 | 154293967-18209-DTLSB-10_03_2024-GO95MLD-1^06245006.0337900 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000574 | 154659370-38179-DTLSB-09_03_2024-GO95MLD-1^06245007.0014200 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000575 | 154700374-5981-DTLSB-07_25_2023-GO95MLD-1^06243009.0056600 | OTHER | Non-HFTD | Distribution | 2023-07-25 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000576 | 154700374-5981-DTLSB-07_25_2023-GRDRODHI-1^06243009.0056600 | OTHER | Non-HFTD | Distribution | 2023-07-25 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000577 | 154700374-5981-DTLSB-07_25_2023-SVCENTCO-1^06243009.0056600 | OTHER | Non-HFTD | Distribution | 2023-07-25 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000578 | 15566401-95809-DETAIL-03_11_2024-GO95MLD-1^06147004.0039602 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000579 | 155727431-44899-DETAIL-07_09_2024-GO95MLD-1^06244005.0139401 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000580 | 155955429-14479-DTLSB-07_18_2023-GO95MLD-1^06243010.0021404 | OTHER | HFTD Tier 2 | Distribution | 2023-07-18 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000581 | 156252576-83540-ADMIN-03_13_2025-POLEREPL-1^668033/00 10/001 | POLE | HFTD Tier 2 | Transmission | 2025-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000582 | 156512980-17780-DETAIL-12_22_2022-GO95HV-1^668075/00 7/028 | OTHER | Non-HFTD | Transmission | 2022-12-22 | 2027-12-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000583 | 157303483-39200-DTLSB-05_22_2024-GO95MLD-1^06243001.0105400 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000584 | 158036360-32949-DTLSB-02_16_2024-GO95MLD-1^07216001.0263100 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000585 | 15837344-57099-DETAIL-08_05_2024-ABNDEQPM-1^06244005.0031500 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000586 | 158523173-6040-DTLTRT-10_02_2023-GO95MLD-1^668010/00 2/035 | OTHER | Non-HFTD | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000587 | 158552050-27800-DETAIL-05_06_2024-GO95HV-1^06142012.0122000 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000588 | 158731353-96059-DTLSB-09_30_2024-GO95MLD-1^06245007.0232502 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000589 | 159437443-25643-DETAIL-10_12_2022-GO95HV-1^668005/08 8X7/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000590 | 159437443-25643-DETAIL-10_12_2022-GUYHINS-1^668005/08 8X7/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000591 | 159437443-25643-DETAIL-10_12_2022-GUYHINS-2^668005/08 8X7/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000592 | 159491533-47030-DETAIL-03_03_2025-SVCDEFLC-1^06241005.0366101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000593 | 159516363-82850-DETAIL-01_30_2025-SVCROAD-1^06239004.0132000 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000594 | 15276554-73549-DTLSB-02_07_2024-GO95TCH-1^07216001.0199240 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000595 | 153297724-96980-DTLTRT-09_27_2023-GUYNOINS-2^668010/00 20/006 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000596 | 153297724-96980-DTLTRT-09_27_2023-GUYNOINS-3^668010/00 20/006 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000597 | 153330331-9619-DETAIL-08_11_2023-POLEREPL-1^668036/00 6/049 | POLE | HFTD Tier 2 | Transmission | 2023-08-11 | 2024-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000598 | 153429672-23649-DETAIL-02_20_2024-SVCENTCO-1^07113002.0183000 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000599 | 153432064-24789-DETAIL-07_12_2023-GO95HV-1^06244008.0271300 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000600 | 153606109-2649-DETAIL-08_20_2024-SVCDEFLC-1^06245005.0252401 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000601 | 153842101-77080-DETAIL-03_18_2025-GO95HV-1^06239001.0054700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000602 | 153900793-77890-DTLSB-05_28_2024-GO95MLD-1^06243001.0125003 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000603 | 153916893-10489-DETAIL-04_03_2024-GO95MLD-1^06247005.0298903 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000604 | 154144233-21309-DETAIL-03_05_2024-GO95HV-1^06147005.0179602 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000605 | 154261573-24629-DETAIL-05_15_2024-GO95HV-1^06142012.0122903 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000606 | 154286043-26240-ADMIN-02_19_2025-POLEREPL-1^668010/00 11/024 | POLE | HFTD Tier 2 | Transmission | 2025-02-19 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000607 | 154700374-5981-DTLSB-07_25_2023-GRDRODHI-2^06243009.0056600 | OTHER | Non-HFTD | Distribution | 2023-07-25 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000608 | 15481791-64169-DTLSB-08_28_2024-GO95HV-1^06245007.0117502 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000609 | 155363247-13768-DETAIL-04_03_2024-GO95MLD-1^06247005.0339901 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000610 | 155378750-71649-DETAIL-08_20_2024-SVCWIND-1^06245005.0252402 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000611 | 156434647-43149-DETAIL-10_09_2024-GO95MLD-1^07216001.0200203 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000612 | 156541789-52789-AUDIT-04_30_2024-GO95MLD-1^06247005.0336602 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000613 | 156657181-83959-DTLSB-02_06_2024-SVCENTCO-1^07216001.0309942 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000614 | 156795723-59290-DTLSB-05_22_2024-GO95MLD-1^06243001.0030400 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000615 | 156865376-1390-DTLSB-01_31_2023-GO95MLD-1^06248001.0367804 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000616 | 157818539-62500-DETAIL-04_22_2024-GO95HV-1^06146001.0365301 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000617 | 157884363-41429-DETAIL-06_27_2023-SVCWIND-1^06243009.0047900 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000618 | 158350299-80299-DETAIL-01_13_2025-GO95CL10-1^06240004.0079340 | OTHER | HFTD Tier 3 | Distribution | 2025-01-13 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000619 | 159575610-6459-DETAIL-07_14_2022-GO95MLD-1^07116001.0040402 | OTHER | Non-HFTD | Distribution | 2022-07-14 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000620 | 160282782-90079-DETAIL-04_08_2024-GO95BLTC-1^06147005.0220400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000621 | 160282782-90079-DETAIL-04_08_2024-SVCDEFLC-1^06147005.0220400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000622 | 160407028-14549-DTLSB-02_07_2024-SVCENTCO-1^07216001.0199406 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000623 | 160757908-97859-DETAIL-04_08_2024-GO95HV-1^06246005.0072301 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000624 | 16122131-40989-DETAIL-05_06_2024-GO95HV-1^06142012.0123008 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000625 | 161282325-73859-DETAIL-10_17_2024-GO95MLD-1^07216001.0201503 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000626 | 161282325-73859-DETAIL-10_17_2024-GO95TCH-1^07216001.0201503 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000627 | 161372531-8834-DETAIL-03_27_2023-GO95MLD-1^06142016.0052100 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000628 | 161372531-8834-DETAIL-03_27_2023-GRDRODHI-1^06142016.0052100 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000629 | 161689143-49379-DTLSB-08_29_2023-GO95MLD-1^06243009.0121300 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000630 | 162022219-10289-DETAIL-03_26_2024-GRDRODHI-1^06246005.0059601 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000631 | 16261656-30879-DETAIL-03_25_2024-GO95MLD-1^06147005.0139901 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000632 | 162651674-6660-DRONE_VS-11_13_2024-INSULBRK-1^668014/00 9/041 | INSULATOR AND BUSHING | HFTD Tier 3 | Transmission | 2024-11-13 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000633 | 162862909-7479-DETAIL-04_02_2024-GO95MLD-1^06246005.0047801 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000634 | 162862909-7479-DETAIL-04_02_2024-GRDRODHI-1^06246005.0047801 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000635 | 162880858-34079-DETAIL-03_28_2024-GO95HV-1^06147005.0122201 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000636 | 163021378-6259-DTLSB-02_07_2024-ENCHRW-1^07216001.0199106 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000637 | 163592470-40409-DETAIL-03_11_2024-SVCDEFLC-1^06147004.0020200 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000638 | 163773880-53243-DETAIL-03_21_2024-GO95MLD-1^06246005.0061401 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000639 | 163842025-47859-DTLSB-02_06_2024-SVCENTBK-1^07216001.0307902 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000640 | 16397525-64565-DETAIL-02_18_2025-SVCDEFLC-1^06240004.0220406 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000641 | 164092914-83149-DETAIL-03_20_2023-SVCRUBLG-1^07114001.0282302 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000642 | 164153420-90529-DETAIL-05_06_2024-GO95MLD-1^06142012.0124100 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000643 | 164153420-90529-DETAIL-05_06_2024-RISECLMB-1^06142012.0124100 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000644 | 15837344-57099-DETAIL-08_05_2024-GO95HV-1^06244005.0031500 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000645 | 15851624-24624-DETAIL-03_28_2023-GO95MLD-1^06142016.0084701 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000646 | 158523173-6040-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/035 | OTHER | Non-HFTD | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000647 | 158731353-96059-DTLSB-09_30_2024-GO95BLTC-1^06245007.0232502 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000648 | 159022698-95270-DETAIL-01_23_2025-GO95CL10-1^06240004.0082002 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000649 | 159022698-95270-DETAIL-09_17_2024-SVCDEFLC-1^06240004.0082002 | OTHER | HFTD Tier 2 | Distribution | 2024-09-17 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000650 | 159273761-94949-DETAIL-02_21_2024-GO95MLD-1^07113001.0143000 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000651 | 159276749-88200-DETAIL-05_02_2024-GO95HV-1^06142012.0125010 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000652 | 159437443-25643-DETAIL-10_12_2022-GUYHINS-3^668005/08 8X7/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000653 | 159437443-25643-DETAIL-10_12_2022-GUYHINS-4^668005/08 8X7/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000654 | 159507504-97059-DTLSB-09_30_2024-GO95MLD-1^06245007.0231540 | OTHER | Non-HFTD | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000655 | 159542153-61069-DETAIL-03_08_2023-GO95BLTC-1^668002/00 6/032 | OTHER | HFTD Tier 2 | Transmission | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000656 | 15979660-74369-DTLTRT-06_15_2021-GO95HV-1^668041/00 16/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000657 | 159843421-91600-DETAIL-04_15_2024-GO95MLD-1^06145002.0062501 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000658 | 159863568-36079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 21/075 | OTHER | HFTD Tier 2 | Transmission | 2023-09-21 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000659 | 160219841-77530-DTLTRT-10_05_2023-GO95HV-1^668010/00 7/028 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000660 | 160219841-77530-DTLTRT-10_05_2023-GO95MLD-1^668010/00 7/028 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000661 | 160282782-90079-DETAIL-04_08_2024-GO95MLD-1^06147005.0220400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000662 | 160407028-14549-DTLSB-02_07_2024-GO95MLD-1^07216001.0199406 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000663 | 160407028-14549-DTLSB-02_07_2024-SVCENTCO-2^07216001.0199406 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000664 | 1607226-90589-DTLSB-04_15_2024-SVCENTCO-1^06245007.0227105 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000665 | 16079080-39839-DETAIL-02_26_2024-GO95MLD-1^07113001.0138401 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000666 | 161170068-15239-DETAIL-03_20_2024-GO95MLD-1^06244005.0140042 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000667 | 161210264-55740-DTLTRT-10_02_2023-GO95MLD-1^668010/00 12/034 | OTHER | Non-HFTD | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000668 | 16122131-40989-DETAIL-05_06_2024-GO95MLD-1^06142012.0123008 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000669 | 164596005-78005-DETAIL-03_12_2025-GO95HV-1^06238004.0224002 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000670 | 16471375-53289-DETAIL-10_22_2024-GO95BLTC-1^07216001.0207901 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000671 | 16471375-53289-DETAIL-10_22_2024-GO95HV-1^07216001.0207901 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000672 | 16471375-53289-DETAIL-10_22_2024-GO95MLD-1^07216001.0207901 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000673 | 165520683-44683-DETAIL-03_30_2023-GO95MLD-1^06142016.0059004 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000674 | 165557250-16143-DETAIL-03_21_2024-GO95MLD-1^06246005.0063402 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000675 | 165995738-7459-DETAIL-05_10_2022-SVCRUBLG-1^07116001.0059302 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000676 | 166030043-37940-DRONE_HY-09_14_2023-GO95HV-1^668002/00 19/055 | OTHER | HFTD Tier 3 | Transmission | 2023-09-14 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000677 | 16617370-77370-DETAIL-04_03_2024-GO95HV-1^06247005.0299701 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000678 | 166417101-47599-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0226200 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000679 | 166870591-36729-DTLSB-09_05_2023-ENCHRW-1^06243008.0092502 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000680 | 16708513-8419-DTLTRT-08_16_2022-POLETOP-1^668005/00 9/092 | POLE | Non-HFTD | Transmission | 2022-08-16 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000681 | 167118265-12663-DETAIL-04_24_2023-GO95HV-1^07117003.0022000 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000682 | 167203475-30410-DETAIL-05_08_2024-GO95MLD-1^06142012.0120201 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000683 | 167228241-21410-DETAIL-04_16_2024-GO95MLD-1^06145001.0139900 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000684 | 167228241-21410-DETAIL-04_16_2024-POLISSUE-1^06145001.0139900 | POLE | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000685 | 16762638-38370-DETAIL-02_26_2025-GO95TCH-1^06240004.0061302 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000686 | 167651161-62809-DETAIL-11_08_2022-GO95MLD-1^06246008.0067700 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000687 | 167688608-35359-DETAIL-05_31_2024-GO95MLD-1^06246005.0328401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000688 | 168004821-66910-DETAIL-05_06_2024-GO95MLD-1^06142012.0124001 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000689 | 168464088-44390-DETAIL-01_16_2025-GO95HV-1^06239004.0256213 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000690 | 168682828-5210-DETAIL-04_22_2024-GO95HV-1^06145001.0029700 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000691 | 168682828-5210-DETAIL-04_22_2024-GO95MLD-1^06145001.0029700 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000692 | 170301679-85679-DTLSB-07_19_2023-ABNDEQPM-1^06243010.0105900 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000693 | 170301679-85679-DTLSB-07_19_2023-GRDRODHI-1^06243010.0105900 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000694 | 161384347-28099-DTLSB-09_04_2024-SVCENTCO-1^06245006.0072902 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000695 | 161580874-88034-DETAIL-05_01_2024-SVCDEFLC-1^06143015.0339901 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000696 | 161916118-34349-DTLSB-02_21_2024-SVCROAD-1^07216001.0260702 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000697 | 162022219-10289-DETAIL-03_26_2024-GRDRODHI-2^06246005.0059601 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000698 | 162172116-77159-DETAIL-10_24_2024-GO95MLD-1^07216001.0203601 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000699 | 16261656-30879-DETAIL-03_25_2024-GO95HV-1^06147005.0139901 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000700 | 16261656-30879-DETAIL-03_25_2024-POLISSUE-1^06147005.0139901 | POLE | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000701 | 162862909-7479-DETAIL-04_02_2024-GO95HV-1^06246005.0047801 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000702 | 162880858-34079-DETAIL-03_28_2024-GO95MLD-1^06147005.0122201 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000703 | 163081912-56979-DETAIL-06_19_2023-GO95HV-1^06244010.0250202 | OTHER | HFTD Tier 2 | Distribution | 2023-06-19 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000704 | 163795800-94070-DETAIL-03_19_2025-GO95HV-1^06239002.0029500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000705 | 163914854-45759-ADMIN-10_10_2024-POLEDERP-1^07216002.0247901 | POLE | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000706 | 164092914-83149-DETAIL-03_20_2023-GO95HV-1^07114001.0282302 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000707 | 164101020-54269-DTLTRT-07_05_2022-GO95HV-1^668005/00 9/034 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000708 | 16437336-35289-DETAIL-10_22_2024-CUTOUTAR-2^07216001.0207200 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000709 | 164558931-82380-DETAIL-02_24_2025-GUYHINS-1^06240004.0152641 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000710 | 164596005-78005-DETAIL-03_12_2025-CLRTOUCH-1^06238004.0224002 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-12 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000711 | 164764341-45119-ADMIN-08_05_2020-POLEDERP-1^668005/00 12/083 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000712 | 164830414-54210-DETAIL-02_09_2023-GO95MLD-1^06146004.0160901 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000713 | 164918120-40870-DETAIL-02_04_2025-GO95BLTC-1^06240004.0166704 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000714 | 165125733-26309-ADMIN-06_05_2024-GO95STUB-1^06245010.0322801 | OTHER | HFTD Tier 2 | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000715 | 165315424-10060-DETAIL-01_31_2025-SVCDEFLC-1^06239004.0242940 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000716 | 165347305-84449-DETAIL-03_15_2023-GO95MLD-1^07114001.0328001 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000717 | 165429452-81610-DETAIL-02_08_2023-GO95BLTC-1^06145002.0047800 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000718 | 165429452-81610-DETAIL-02_08_2023-GO95MLD-1^06145002.0047800 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000719 | 170451253-29669-DTLTRT-10_04_2023-GO95MLD-1^668010/00 5/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000720 | 170577034-10940-DTLTRT-10_04_2023-GUYHINS-1^668010/00 9/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000721 | 170650455-43940-DETAIL-02_18_2025-CLRTOUCH-1^06240004.0102004 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-18 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000722 | 171288613-72713-DETAIL-04_29_2024-SVCDEFLC-1^06142016.0078701 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000723 | 171455186-28510-DTLSB-01_31_2023-GO95MLD-1^06248001.0369706 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000724 | 171778860-79401-DETAIL-01_31_2025-GO95TCH-1^06239004.0136113 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000725 | 171892471-4559-DTLSB-02_16_2024-ABNDEQPM-1^07216001.0262101 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000726 | 172875525-5929-ADMIN-08_01_2024-POLEREPL-1^06142012.0120600 | POLE | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000727 | 172928788-93830-DETAIL-01_15_2025-SVCDEFLC-1^06240004.0095202 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000728 | 173208476-74870-DETAIL-01_23_2025-GO95HV-1^06239004.0256643 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000729 | 173587421-68680-DETAIL-03_06_2025-GRDRODHI-1^06240004.0340700 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000730 | 174164738-99638-DETAIL-03_25_2024-SVCDEFLC-1^06244005.0146400 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000731 | 174317415-42310-DETAIL-04_24_2024-GRDRODHI-1^06145001.0043002 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000732 | 174396931-74080-DETAIL-03_18_2025-GO95HV-1^06239001.0042702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000733 | 174578905-23410-DTLSB-02_01_2023-ABNDEQPM-1^06248001.0369300 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000734 | 174632288-34250-DETAIL-03_26_2025-SVCDEFLC-1^06239003.0018305 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000735 | 174678033-85623-DTLSB-09_05_2024-GO95MLD-1^06246006.0314040 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000736 | 174977364-83090-DETAIL-03_11_2025-GO95HV-1^06239003.0367002 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000737 | 175038610-78610-DETAIL-02_06_2025-SVCDEFLC-1^06239004.0135206 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000738 | 175094029-62309-DETAIL-04_09_2024-GO95MLD-1^06147005.0210000 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000739 | 175227004-9004-DTLSB-02_13_2023-GO95MLD-1^06248001.0279743 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000740 | 175250600-12160-DETAIL-01_21_2025-BIRDDMG-1^06239004.0256544 | POLE | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000741 | 175863751-73482-DETAIL-07_05_2023-GO95HV-1^06244009.0127301 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000742 | 176110793-85252-DETAIL-06_13_2023-GO95MLD-1^06244010.0223501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-13 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000743 | 176215011-36780-DETAIL-02_12_2025-SVCROOF-1^06240004.0167543 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000744 | 165647376-52710-DTLSB-01_31_2023-GO95HV-1^06248001.0367801 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000745 | 165779899-67710-DETAIL-04_24_2024-GO95HV-1^06145001.0062500 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000746 | 166452194-68759-DETAIL-06_05_2024-GO95MLD-1^06246006.0251902 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000747 | 16689319-91415-DRONE_HY-11_03_2023-GO95HV-1^668033/00 2X/027 | OTHER | HFTD Tier 2 | Transmission | 2023-11-03 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000748 | 167019395-60759-DTLSB-02_14_2024-GO95CL10-1^07216001.0187000 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000749 | 167019395-60759-DTLSB-02_14_2024-GO95HV-1^07216001.0187000 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000750 | 167019395-60759-DTLSB-02_14_2024-GO95MLD-1^07216001.0187000 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000751 | 167475529-97779-DETAIL-04_08_2024-GO95MLD-1^06147005.0229501 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000752 | 167475529-97779-DETAIL-04_08_2024-GUYHINS-1^06147005.0229501 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000753 | 16762638-38370-DETAIL-02_26_2025-PWRTRN-1^06240004.0061302 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000754 | 167937019-512-DETAIL-07_05_2023-GO95MLD-1^06244009.0131401 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000755 | 168004821-66910-DETAIL-05_06_2024-GO95HV-1^06142012.0124001 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000756 | 169019311-84811-DETAIL-01_15_2025-GO95HV-1^06239004.0255240 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000757 | 169019311-84811-DETAIL-01_15_2025-SVCENTCO-1^06239004.0255240 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000758 | 169288501-89679-DTLSB-08_27_2024-GRDRODHI-1^06245007.0116901 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000759 | 169522597-70849-DETAIL-03_15_2023-GUYHINS-1^07114001.0341100 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000760 | 170301679-85679-DTLSB-07_19_2023-GO95MLD-1^06243010.0105900 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000761 | 170451253-29669-DTLTRT-10_04_2023-GO95BLTC-1^668010/00 5/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000762 | 171010965-7415-DETAIL-03_02_2023-GRDRODHI-1^07117002.0198204 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000763 | 171071001-59201-DETAIL-01_21_2025-GO95HV-1^06239004.0255443 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000764 | 171071001-59201-DETAIL-01_21_2025-SVCENTBK-1^06239004.0255443 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000765 | 172027480-75332-DTLSB-07_19_2023-GO95MLD-1^06243010.0021201 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000766 | 17211054-18549-DETAIL-03_01_2023-SVCNEUT-1^07216001.0291801 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000767 | 172252992-39350-DETAIL-01_31_2025-GO95HV-1^06239004.0137204 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000768 | 172344840-10779-DTLSB-09_04_2024-GO95MLD-1^06245007.0019102 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000769 | 172344840-10779-DTLSB-09_04_2024-GRDRODHI-1^06245007.0019102 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000770 | 176666080-21859-DETAIL-06_05_2024-GO95MLD-1^06246006.0265202 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000771 | 176742552-55850-DETAIL-03_20_2025-SVCENTBK-1^06239003.0016300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000772 | 176742552-55850-DETAIL-03_20_2025-SVCROAD-1^06239003.0016300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000773 | 177299296-69920-DTLSB-02_01_2023-GO95MLD-1^06248001.0369806 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000774 | 177842911-83452-DETAIL-06_08_2023-GO95MLD-1^06244009.0293600 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000775 | 177999036-45459-ADMIN-09_26_2022-UBPBXARM-1^668004/00 1/025 | CROSSARM | Non-HFTD | Transmission | 2022-09-26 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000776 | 178061643-64309-ADMIN-06_05_2024-GO95STUB-1^06245010.0322800 | OTHER | HFTD Tier 2 | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000777 | 17909742-72540-DTLTRT-10_03_2023-GO95HV-1^668010/00 12/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000778 | 179145246-68049-DETAIL-02_28_2023-SVCENTCO-1^07216001.0298705 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000779 | 1794568-71349-DETAIL-03_14_2024-GUYNOINS-1^06245006.0015004 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000780 | 179553280-53859-DETAIL-10_14_2024-SVCENTCO-1^07216001.0200340 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000781 | 179571172-43070-DETAIL-03_18_2025-GRDRODHI-1^06238004.0125801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000782 | 179905773-14720-DTLSB-02_19_2024-SVCROAD-1^07216001.0264206 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000783 | 17992963-44405-DETAIL-04_29_2024-GO95MLD-1^06142016.0067001 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000784 | 17992963-44405-DETAIL-04_29_2024-SVCROAD-1^06142016.0067001 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000785 | 180077786-58869-DTLTRT-10_18_2023-GRDRODHI-1^668010/00 21/010 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000786 | 180111444-43339-DETAIL-06_24_2024-GO95BLTC-1^06244005.0234040 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000787 | 180278108-98692-DETAIL-07_05_2023-GO95HV-1^06244008.0323740 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000788 | 180370408-37720-DTLTRT-10_17_2023-GO95HV-1^668010/00 1X/009 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000789 | 180370408-37720-DTLTRT-10_17_2023-GO95MLD-1^668010/00 1X/009 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000790 | 180437034-78149-DTLSB-02_26_2024-GO95MLD-1^07216001.0277807 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000791 | 180454293-33003-DETAIL-03_05_2024-SVCENTCO-1^06245007.0276304 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000792 | 180485763-61339-DETAIL-02_29_2024-GO95MLD-1^07113001.0107004 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000793 | 18050723-88752-DETAIL-06_21_2023-GO95HV-1^06244009.0309400 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000794 | 18050723-88752-DETAIL-06_21_2023-GO95TCH-1^06244009.0309400 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000795 | 181032828-68730-DETAIL-02_17_2025-GO95MLD-1^06240003.0314801 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000796 | 172423198-66010-DETAIL-04_16_2024-GO95MLD-1^06145001.0129201 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000797 | 173327101-9729-DETAIL-05_07_2024-GO95MLD-1^06142012.0122200 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000798 | 173903839-90370-DETAIL-04_26_2023-ABNDEQPM-1^06240004.0063200 | OTHER | HFTD Tier 2 | Distribution | 2023-04-26 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000799 | 173977098-66479-DETAIL-02_17_2025-GO95HV-1^06240004.0276400 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000800 | 174234146-67210-DETAIL-02_06_2023-GO95MLD-1^06147002.0070000 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000801 | 174234146-67210-DETAIL-02_06_2023-GO95TCH-1^06147002.0070000 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000802 | 174317415-42310-DETAIL-04_24_2024-GO95HV-1^06145001.0043002 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000803 | 174317415-42310-DETAIL-04_24_2024-GO95MLD-1^06145001.0043002 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000804 | 174520843-50289-DETAIL-08_15_2024-GO95MLD-1^06246004.0200900 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000805 | 174603221-879-DTLSB-02_09_2023-GO95MLD-1^06247001.0129000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000806 | 174822274-70974-DETAIL-03_07_2024-GO95HV-1^06147004.0019500 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000807 | 175094029-62309-DETAIL-04_09_2024-GUYHINS-1^06147005.0210000 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000808 | 175214289-77029-DTLSB-07_18_2023-GO95HV-1^06243010.0039305 | OTHER | HFTD Tier 2 | Distribution | 2023-07-18 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000809 | 175513535-29949-DETAIL-10_25_2024-GO95MLD-1^07216001.0209700 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000810 | 175851765-82530-DETAIL-01_13_2025-SVCDEFLC-1^06240004.0086140 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000811 | 176262991-73819-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0227200 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000812 | 176336751-14899-DETAIL-07_09_2024-GO95HV-1^06244005.0139201 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000813 | 176365552-5850-DETAIL-03_20_2025-GO95HV-1^06239003.0016302 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000814 | 176387070-48989-DTLSB-09_01_2022-GO95MLD-1^06243004.0234501 | OTHER | Non-HFTD | Distribution | 2022-09-01 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000815 | 176462660-98801-DETAIL-02_24_2025-BIRDDMG-1^06241005.0153500 | POLE | HFTD Tier 3 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000816 | 176666080-21859-DETAIL-06_05_2024-GUYLOINS-1^06246006.0265202 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000817 | 17667890-59940-ADMIN-03_17_2025-POLEREPL-1^06237005.0264101 | POLE | HFTD Tier 2 | Distribution | 2025-03-17 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000818 | 17821501-28049-DETAIL-04_04_2023-SVCDEFLC-1^06245006.0222202 | OTHER | Non-HFTD | Distribution | 2023-04-04 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000819 | 178665150-34732-DTLSB-07_19_2023-GO95MLD-1^06243010.0021202 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000820 | 178871641-90709-DTLSB-08_27_2024-GO95HV-1^06245007.0114803 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000821 | 181128184-32240-DTLTRT-10_04_2023-GUYNOINS-2^668010/00 10A/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000822 | 181145459-19583-DETAIL-03_14_2024-GO95HV-1^06245005.0061740 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000823 | 181798893-993-DETAIL-04_12_2023-GO95MLD-1^06240004.0167703 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000824 | 182012412-13359-DETAIL-02_22_2024-SVCDEFLC-1^07113001.0103000 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000825 | 182363134-18611-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 5/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000826 | 182363134-47611-ENHANCED-01_08_2025-IRSPOTOH-1^668067/00 5/014 | OTHER | Non-HFTD | Transmission | 2025-01-08 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000827 | 182363134-47611-ENHANCED-01_27_2025-IRSPOTOH-1^668067/00 5/014 | OTHER | Non-HFTD | Transmission | 2025-01-27 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000828 | 182363134-49080-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 5/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000829 | 182363134-49080-ENHANCED-01_08_2025-IRSPOTOH-1^668067/00 5/014 | OTHER | Non-HFTD | Transmission | 2025-01-08 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000830 | 182608751-97243-DETAIL-10_21_2024-ABNDEQPM-1^07216001.0200742 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000831 | 182665305-32000-DETAIL-03_26_2025-SVCDEFLC-1^06239003.0019609 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000832 | 182665305-32000-DETAIL-03_26_2025-SVCROAD-1^06239003.0019609 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000833 | 182791969-12969-DETAIL-08_02_2022-GO95HV-1^668005/00 7X/077 | OTHER | Non-HFTD | Transmission | 2022-08-02 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000834 | 183010701-63929-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0122205 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000835 | 183010701-63929-DETAIL-05_07_2024-SVCENTCO-1^06142012.0122205 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000836 | 183134593-49239-DETAIL-07_09_2024-GO95HV-1^06244005.0273901 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000837 | 183190493-48409-DTLSB-09_05_2024-RISEGRD-1^06246006.0314240 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000838 | 183577563-99189-DTLSB-10_01_2024-GO95HV-1^06245007.0231700 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000839 | 183577563-99189-DTLSB-10_01_2024-GO95MLD-1^06245007.0231700 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000840 | 183634753-27520-DTLSB-02_13_2024-GO95MLD-1^07216001.0198902 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000841 | 183643693-60159-DETAIL-06_04_2024-GO95MLD-1^06246005.0212500 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000842 | 183643758-98879-DETAIL-04_03_2024-GO95MLD-1^06147005.0157200 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000843 | 183643758-98879-DETAIL-04_03_2024-GRDRODHI-1^06147005.0157200 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000844 | 183644749-25379-DETAIL-04_08_2024-GO95MLD-1^06246005.0056300 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000845 | 183880633-73240-DTLTRT-10_05_2023-GO95MLD-1^668010/00 13/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000846 | 183880633-73240-DTLTRT-10_05_2023-GRDRODHI-1^668010/00 13/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000847 | 179008721-44209-DTLTRT-10_27_2022-GO95MLD-1^668001/00 4/029 | OTHER | Non-HFTD | Transmission | 2022-10-27 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000848 | 179295604-36649-DETAIL-03_16_2023-GO95MLD-1^07114001.0282402 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000849 | 1794568-71349-DETAIL-03_14_2024-GO95HV-1^06245006.0015004 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000850 | 1794568-71349-DETAIL-03_14_2024-GO95MLD-1^06245006.0015004 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000851 | 179553280-53859-DETAIL-10_14_2024-SVCDEFLC-1^07216001.0200340 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000852 | 179905773-14720-DTLSB-02_19_2024-GO95CL10-1^07216001.0264206 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000853 | 179905773-14720-DTLSB-02_19_2024-SVCROAD-2^07216001.0264206 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000854 | 180077786-58869-DTLTRT-10_18_2023-GO95MLD-1^668010/00 21/010 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000855 | 180111444-43339-DETAIL-06_24_2024-GO95MLD-1^06244005.0234040 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000856 | 180275380-97820-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0124009 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000857 | 180854056-90770-DETAIL-03_11_2025-GO95HV-1^06238004.0334304 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000858 | 180978656-65069-DTLTRT-10_23_2023-GO95HV-1^668010/00 17/042 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000859 | 181025559-75399-DTLSB-04_17_2024-GO95MLD-1^06245007.0224402 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000860 | 181025559-75399-DTLSB-04_17_2024-SVCWIND-1^06245007.0224402 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000861 | 181128184-32240-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 10A/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000862 | 181330823-599-ADMIN-05_29_2024-ABNDEQPM-1^06246005.0098200 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000863 | 181330823-599-DETAIL-05_29_2024-GO95MLD-1^06246005.0098200 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000864 | 18172860-65040-DETAIL-05_06_2024-GO95MLD-1^06142012.0123000 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000865 | 182012412-13359-DETAIL-02_22_2024-GO95MLD-1^07113001.0103000 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000866 | 1823003-11590-DETAIL-01_29_2025-SVCROAD-1^06240004.0176404 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000867 | 184205097-27103-AUDIT-08_27_2024-GO95MLD-1^06245006.0063541 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000868 | 184279808-46069-DTLTRT-06_10_2021-GO95HV-1^668041/00 6/015 | OTHER | Non-HFTD | Transmission | 2021-06-10 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000869 | 184540064-58030-DETAIL-02_26_2025-SVCNEUT-1^06241005.0366700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000870 | 184560238-69920-DETAIL-04_17_2024-GO95MLD-1^06145001.0013400 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000871 | 184654766-39572-DETAIL-08_08_2024-GO95HV-1^06245006.0093140 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000872 | 184699403-92749-DETAIL-03_21_2023-GO95MLD-1^07113001.0057503 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000873 | 184760860-22860-DETAIL-03_11_2024-GO95MLD-1^06147004.0014904 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000874 | 185015744-43220-DTLSB-02_07_2023-SVCENTCO-1^06248001.0158300 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000875 | 185058654-49860-DETAIL-01_23_2025-GO95HV-1^06239004.0257801 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000876 | 185159613-70829-DETAIL-05_01_2024-GUYHINS-1^06142012.0123500 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000877 | 185451271-39499-DTLSB-08_27_2024-GO95BLTC-1^06245007.0115501 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000878 | 185489324-27379-ADMIN-03_10_2023-GO95CL10-1^06148004.0192401 | OTHER | Non-HFTD | Distribution | 2023-03-10 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000879 | 186298823-48152-DETAIL-06_26_2023-GO95HV-1^06244009.0304905 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000880 | 186298823-48152-DETAIL-06_26_2023-GO95MLD-1^06244009.0304905 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000881 | 18640161-5231-DETAIL-02_27_2025-GO95MLD-1^06241005.0177801 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000882 | 186557300-68749-DETAIL-08_13_2024-GO95HV-1^06245005.0359600 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000883 | 187692211-8211-DETAIL-05_06_2024-GUYNOINS-1^06142012.0123012 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000884 | 187910528-66289-DETAIL-07_30_2024-GO95MLD-1^06244005.0352201 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000885 | 188010475-98049-DETAIL-08_19_2024-GRDRODHI-1^06245004.0290500 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000886 | 188076003-28530-DETAIL-05_22_2024-GO95HV-1^06243001.0109300 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000887 | 188158326-57470-DETAIL-01_22_2025-GO95HV-1^06239004.0255549 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000888 | 188158326-57470-DETAIL-01_22_2025-RISEHDWR-1^06239004.0255549 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000889 | 188165718-71243-DTLSB-04_30_2024-GO95MLD-1^06245007.0222850 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000890 | 188576781-39830-DETAIL-04_15_2024-GO95MLD-1^06145001.0139100 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000891 | 188692054-67759-DETAIL-05_17_2022-GUYSLACK-1^07117001.0317500 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-17 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000892 | 1823003-11590-DETAIL-09_24_2024-SVCDEFLC-1^06240004.0176404 | OTHER | HFTD Tier 2 | Distribution | 2024-09-24 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000893 | 182363134-18611-ENHANCED-01_08_2025-IRSPOTOH-1^668067/00 5/014 | OTHER | Non-HFTD | Transmission | 2025-01-08 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000894 | 182363134-18611-ENHANCED-01_27_2025-IRSPOTOH-1^668067/00 5/014 | OTHER | Non-HFTD | Transmission | 2025-01-27 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000895 | 182363134-49080-ENHANCED-01_27_2025-IRSPOTOH-1^668067/00 5/014 | OTHER | Non-HFTD | Transmission | 2025-01-27 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000896 | 182813110-25659-DETAIL-06_17_2024-GO95HV-1^06246006.0132301 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000897 | 182901370-76349-DETAIL-05_10_2022-GO95HV-1^07116001.0094102 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000898 | 182960736-17009-DTLSB-09_04_2024-GO95MLD-1^06245007.0141900 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000899 | 183643693-60159-DETAIL-06_04_2024-GO95HV-1^06246005.0212500 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000900 | 183643758-98879-DETAIL-04_03_2024-CLRTOUCH-1^06147005.0157200 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000901 | 183643758-98879-DETAIL-04_03_2024-SVCENTCO-1^06147005.0157200 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000902 | 184244190-77409-DETAIL-03_05_2024-GO95MLD-1^06147004.0020202 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000903 | 184346011-97302-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 5/002 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000904 | 184560238-69920-DETAIL-04_17_2024-GO95HV-1^06145001.0013400 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000905 | 184692811-31999-ADMIN-06_05_2024-GO95STUB-1^06246008.0062101 | OTHER | HFTD Tier 2 | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000906 | 184692811-31999-DETAIL-10_26_2022-ABNDEQPM-1^06246008.0062101 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000907 | 184921131-50220-DETAIL-04_15_2024-GUYNOINS-1^06145002.0068700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000908 | 184961918-31220-DETAIL-04_17_2024-GUYHINS-1^06145001.0011301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000909 | 185153626-89220-DTLSB-01_31_2023-GO95MLD-1^06248001.0369500 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000910 | 185159613-70829-DETAIL-05_01_2024-GO95MLD-1^06142012.0123500 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000911 | 185159613-70829-DETAIL-05_01_2024-SVCNEUT-1^06142012.0123500 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000912 | 1852273-79419-ENHANCED-07_21_2020-POLEDERP-1^668005/00 14/092 | POLE | Non-HFTD | Transmission | 2020-07-21 | 2023-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000913 | 185451271-39499-DTLSB-08_27_2024-GO95HV-1^06245007.0115501 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000914 | 185451271-39499-DTLSB-08_27_2024-GO95MLD-1^06245007.0115501 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000915 | 185598473-5539-DETAIL-07_03_2024-GO95MLD-1^06244005.0230402 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000916 | 185699610-52599-DTLSB-09_03_2024-GO95MLD-1^06245007.0015103 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000917 | 18577196-94961-DETAIL-02_24_2025-GO95MLD-1^06239004.0366708 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000918 | 186054094-81640-DTLTRT-10_04_2023-GO95HV-1^668010/00 20/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000919 | 186054094-81640-DTLTRT-10_04_2023-GO95MLD-1^668010/00 20/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000920 | 187337426-47426-DETAIL-03_04_2025-GO95MLD-1^06241005.0130706 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000921 | 187644544-17330-DETAIL-02_09_2023-GO95MLD-1^06146004.0165901 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000922 | 187692211-8211-DETAIL-05_06_2024-GUYNOINS-2^06142012.0123012 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000923 | 188740214-95979-DETAIL-07_10_2024-GO95MLD-1^06244005.0126100 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000924 | 189081571-17980-DETAIL-03_19_2025-GO95HV-1^06239001.0050602 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000925 | 189533783-16239-DETAIL-07_17_2024-GO95HV-1^06244005.0281100 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000926 | 189676306-71623-DTLSB-04_30_2024-GO95MLD-1^06245007.0220642 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000927 | 19004572-31083-ADMIN-11_06_2023-POLEDERP-1^07216001.0176010 | POLE | Non-HFTD | Distribution | 2023-11-06 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000928 | 190613978-6830-DTLSB-02_08_2023-GO95HV-1^06248001.0227901 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000929 | 19061936-19899-DTLSB-09_30_2024-GO95MLD-1^06245007.0230001 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000930 | 190819614-1450-DTLTRT-11_03_2023-GO95HV-1^668010/00 5/036 | OTHER | HFTD Tier 2 | Transmission | 2023-11-03 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000931 | 191263351-74852-DETAIL-06_08_2023-GO95MLD-1^06244009.0328900 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000932 | 191266144-28144-DETAIL-01_19_2023-GO95HV-1^06148004.0210801 | OTHER | Non-HFTD | Distribution | 2023-01-19 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000933 | 191580928-3390-DETAIL-02_18_2025-GO95MLD-1^06239004.0361300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000934 | 191772140-72430-DETAIL-10_25_2024-GO95MLD-1^07216001.0209705 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000935 | 191962149-32869-DETAIL-06_12_2023-GO95MLD-1^06244009.0365502 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000936 | 192154843-61943-DETAIL-04_29_2024-GO95MLD-1^06142016.0078800 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000937 | 192243540-29783-DETAIL-01_22_2025-GO95HV-1^06240004.0090101 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000938 | 192941739-1000-DTLTRT-09_29_2020-GO95HV-1^668018/00 2/005 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000939 | 193263105-71290-DTLTRT-10_16_2023-GO95MLD-1^668010/00 3X/008 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000940 | 193502073-6139-DETAIL-08_05_2024-ENCHRW-1^06244005.0028101 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000941 | 193663547-93959-DETAIL-04_08_2024-GO95HV-1^06247005.0321300 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000942 | 193709919-90349-ADMIN-03_13_2025-POLEREPL-1^06245007.0217704 | POLE | Non-HFTD | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000943 | 193731551-77430-DETAIL-03_05_2025-GRDRODHI-1^06240004.0200701 | OTHER | HFTD Tier 3 | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000944 | 193880106-72106-DETAIL-05_09_2022-GRDRODHI-1^07116001.0097102 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000945 | 193880106-72106-DETAIL-05_09_2022-GUYHINS-1^07116001.0097102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000946 | 193950251-28349-DTLSB-04_29_2024-GO95TCH-1^06245007.0227501 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000947 | 194006934-65979-DETAIL-07_11_2024-RISEBKSP-1^06244005.0217500 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000948 | 188010475-98049-DETAIL-08_19_2024-GO95MLD-1^06245004.0290500 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000949 | 188169463-89639-DETAIL-07_08_2024-GO95HV-1^06244005.0125000 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000950 | 188384368-29079-DETAIL-02_01_2022-SVCWIND-1^06147005.0265405 | OTHER | Non-HFTD | Distribution | 2022-02-01 | 2025-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000951 | 188461738-82069-DTLTRT-06_10_2021-ANCHIDLE-1^668041/00 16/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-10 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000952 | 188529451-52230-DETAIL-02_05_2025-SVCDEFLC-1^06240004.0176501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000953 | 188576781-39830-DETAIL-04_15_2024-GO95HV-1^06145001.0139100 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000954 | 188644808-52223-DETAIL-03_14_2023-GO95MLD-1^07117003.0112602 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000955 | 188788978-44030-DETAIL-03_20_2024-GO95MLD-1^06245002.0017000 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000956 | 188788978-44030-DETAIL-03_20_2024-GRDRODHI-1^06245002.0017000 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000957 | 18885208-56208-DETAIL-05_10_2022-GO95HV-1^07116001.0094901 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000958 | 18885208-56208-DETAIL-05_10_2022-GO95MLD-1^07116001.0094901 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000959 | 189244035-51870-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 4/045 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000960 | 189786243-55329-DETAIL-06_15_2023-GO95HV-1^06244009.0307601 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000961 | 18991749-21409-AUDIT-04_19_2024-GO95MLD-1^06147005.0217602 | OTHER | Non-HFTD | Distribution | 2024-04-19 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000962 | 189948443-62630-DTLSB-02_14_2023-CLRTOUCH-1^06248001.0349501 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000963 | 189948443-62630-DTLSB-02_14_2023-GO95MLD-1^06248001.0349501 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000964 | 190057605-6630-DTLSB-05_08_2024-GO95MLD-1^06244001.0034300 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000965 | 190139404-28459-DTLSB-02_28_2024-SVCENTCO-1^07216001.0279800 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000966 | 190588949-10049-DETAIL-10_10_2024-ENCHRW-1^07216001.0205130 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000967 | 19061936-19899-DTLSB-09_30_2024-GO95BLTC-1^06245007.0230001 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000968 | 19065631-66640-DETAIL-04_15_2024-GO95MLD-1^06145002.0064600 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000969 | 190812345-79640-DETAIL-02_26_2025-GO95CL10-1^06240004.0217800 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000970 | 1909404-57904-DETAIL-04_09_2024-CLRTOUCH-1^06147005.0215820 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000971 | 19099405-1530-DETAIL-01_13_2025-SVCDEFLC-1^06240004.0086141 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000972 | 19138340-7269-ADMIN-08_05_2020-POLEDERP-1^668005/00 3/051 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000973 | 194110384-41329-DETAIL-05_09_2024-GO95MLD-1^06142012.0120508 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000974 | 194110384-41329-DETAIL-05_09_2024-SVCRUBLG-1^06142012.0120508 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000975 | 19412274-50690-DETAIL-03_26_2025-GO95HV-1^06239003.0019700 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000976 | 194217664-58730-DTLSB-02_06_2023-GO95HV-1^06248001.0257201 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000977 | 194217664-58730-DTLSB-02_06_2023-GO95MLD-1^06248001.0257201 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000978 | 195118319-16749-DETAIL-05_22_2023-SVCROAD-1^06245005.0261000 | OTHER | Non-HFTD | Distribution | 2023-05-22 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000979 | 195138310-27301-DETAIL-02_20_2025-BIRDDMG-1^06241005.0158601 | POLE | HFTD Tier 3 | Distribution | 2025-02-20 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000980 | 195219034-54959-DTLSB-02_13_2024-GO95HV-1^07216001.0198904 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000981 | 195219034-54959-DTLSB-02_13_2024-GO95MLD-1^07216001.0198904 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000982 | 195440011-24599-DETAIL-07_03_2024-GO95MLD-1^06244005.0233901 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000983 | 195621294-7330-DTLSB-05_09_2024-GO95MLD-1^06244001.0110901 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000984 | 195650256-77199-DETAIL-08_21_2024-SVCSVC-1^06245006.0095900 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000985 | 195720123-17959-DETAIL-02_20_2024-GO95MLD-1^07113002.0181009 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000986 | 195720123-17959-DETAIL-02_20_2024-SVCENTCO-1^07113002.0181009 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000987 | 195803524-78189-DETAIL-07_17_2024-GO95MLD-1^06244005.0282101 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000988 | 195876823-57430-DTLSB-05_23_2024-GO95MLD-1^06243001.0149602 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000989 | 196012404-10630-DETAIL-10_22_2024-GUYHINS-1^07216001.0208902 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000990 | 196210244-97170-DETAIL-03_27_2023-SVCDEFLC-1^06240004.0168046 | OTHER | HFTD Tier 2 | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000991 | 196306326-56470-DETAIL-01_22_2025-GO95HV-1^06239004.0257700 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000992 | 196326643-55880-DETAIL-03_10_2025-GO95HV-1^06239002.0180600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000993 | 196351111-18730-DETAIL-04_11_2024-GO95MLD-1^06245002.0145101 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000994 | 196405846-65499-DETAIL-03_06_2024-SVCWIND-2^06245007.0273901 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000995 | 196473578-91849-DTLSB-02_27_2024-GO95MLD-1^07216001.0260908 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000996 | 196473578-91849-DTLSB-02_27_2024-GO95TCH-1^07216001.0260908 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130000997 | 196563909-15649-DETAIL-05_17_2023-GO95HV-1^06245006.0276101 | OTHER | Non-HFTD | Distribution | 2023-05-17 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000998 | 191432041-38869-DRONE_HY-09_03_2023-GO95HV-1^668002/00 6/017 | OTHER | Non-HFTD | Transmission | 2023-09-03 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130000999 | 191454138-9138-DTLSB-02_14_2024-GO95HV-1^07216001.0199900 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001000 | 191454138-9138-DTLSB-02_14_2024-GO95MLD-1^07216001.0199900 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001001 | 19152801-29489-DETAIL-11_02_2022-GO95MLD-1^06246008.0051501 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001002 | 191991731-23799-DETAIL-06_20_2024-SVCENTCO-1^06246006.0233000 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001003 | 192061391-61080-DETAIL-03_19_2025-GO95HV-1^06239001.0052701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001004 | 192219363-8630-DTLSB-05_23_2024-GO95MLD-1^06243001.0149601 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001005 | 192391561-35829-DETAIL-05_07_2024-GO95MLD-1^06142012.0123202 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001006 | 192566181-54030-DTLTRT-10_05_2023-GO95MLD-1^668010/00 16/027 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001007 | 192837860-28930-DETAIL-03_13_2024-GUYHINS-1^06147004.0190400 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001008 | 193102326-54779-DTLTRT-10_09_2023-GO95MLD-1^668010/00 15/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001009 | 193102326-54779-DTLTRT-10_09_2023-UBPBCTGD-1^668010/00 15/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001010 | 193263105-71290-DTLTRT-10_16_2023-GO95HV-1^668010/00 3X/008 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001011 | 193263105-71290-DTLTRT-10_16_2023-RISEGRD-1^668010/00 3X/008 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001012 | 193502073-6139-DETAIL-08_05_2024-GO95HV-1^06244005.0028101 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001013 | 193727281-91248-DETAIL-10_08_2024-GO95HV-1^07216001.0201002 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001014 | 193745256-43159-DTLSB-09_30_2024-GO95MLD-1^06245007.0232412 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001015 | 193745256-43159-DTLSB-09_30_2024-RISEGRD-1^06245007.0232412 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001016 | 193880106-72106-DETAIL-05_09_2022-GO95MLD-1^07116001.0097102 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001017 | 19412274-50690-DETAIL-03_26_2025-SVCROAD-1^06239003.0019700 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001018 | 194601591-37119-ADMIN-08_05_2020-POLEDERP-1^668005/00 5/084 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001019 | 194739644-37759-DETAIL-05_16_2022-GO95MLD-1^07117001.0317501 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001020 | 194842606-92999-DTLSB-08_22_2024-GO95HV-1^06245006.0324000 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001021 | 195232366-51189-DETAIL-04_03_2024-GO95TCH-1^06247005.0338800 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001022 | 195650256-77199-DETAIL-08_21_2024-GO95MLD-1^06245006.0095900 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001023 | 196850373-91030-DETAIL-10_21_2024-GO95MLD-1^07216001.0209603 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001024 | 196963848-44220-DTLTRT-10_17_2023-GO95HV-1^668010/00 6X/009 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001025 | 197159694-89549-DTLSB-02_06_2024-SVCDEFLC-1^07216001.0309903 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001026 | 197371201-91201-DTLTRT-09_04_2024-SVCDEFLC-1^06245007.0018430 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001027 | 197453756-55756-DETAIL-04_08_2024-GO95MLD-1^06247005.0322502 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001028 | 197455995-57930-DETAIL-03_10_2025-SVCNEUT-1^06241005.0255941 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001029 | 197639346-31269-ENHANCED-06_30_2024-IRSPOTOH-1^668047/00 11/031 | OTHER | HFTD Tier 2 | Transmission | 2024-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001030 | 197754440-58709-DTLSB-07_23_2024-GO95MLD-1^06245007.0107200 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001031 | 197842728-52449-DETAIL-07_29_2024-GO95MLD-1^06245006.0115902 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001032 | 197842728-52449-DETAIL-07_29_2024-GO95TCH-1^06245006.0115902 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001033 | 195846614-62779-DETAIL-07_11_2024-GO95HV-1^06244005.0219401 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001034 | 196002303-84589-DTLSB-09_06_2023-GO95MLD-1^06243007.0203000 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001035 | 196012404-10630-DETAIL-10_22_2024-GO95MLD-1^07216001.0208902 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001036 | 196012404-10630-DETAIL-10_22_2024-GO95TCH-1^07216001.0208902 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001037 | 196028399-93430-DTLTRT-10_18_2023-GO95HV-1^668010/00 4/012 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001038 | 196306326-56470-DETAIL-01_22_2025-SVCDEFLC-1^06239004.0257700 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001039 | 196405846-65499-DETAIL-03_06_2024-SVCWIND-1^06245007.0273901 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001040 | 196563909-15649-DETAIL-05_17_2023-GO95BLTC-1^06245006.0276101 | OTHER | Non-HFTD | Distribution | 2023-05-17 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001041 | 19738813-10629-DTLSB-08_31_2023-GO95HV-1^06243007.0320101 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001042 | 197639346-31270-ENHANCED-06_30_2024-IRSPOTOH-1^668047/00 11/031 | OTHER | HFTD Tier 2 | Transmission | 2024-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001043 | 198329085-30549-DETAIL-10_25_2024-GUYHINS-1^07216001.0201602 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001044 | 198329085-30549-DETAIL-10_25_2024-GUYHINS-2^07216001.0201602 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001045 | 198698893-7059-DTLSB-09_30_2024-RISEBKSP-1^06245007.0231501 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001046 | 198889506-56180-DETAIL-01_23_2025-GO95HV-1^06239004.0256745 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001047 | 198909553-33713-DTLSB-05_01_2024-GO95HV-1^06245007.0228643 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001048 | 19894904-21640-ADMIN-03_31_2025-POLEDERP-1^06240004.0218702 | POLE | HFTD Tier 2 | Distribution | 2025-03-31 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001049 | 19771463-74099-DETAIL-06_11_2024-GO95MLD-1^06245007.0346400 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001050 | 197815428-55499-DETAIL-04_04_2024-GO95HV-1^06247005.0285101 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001051 | 197920210-71634-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 5/013 | POLE | Non-HFTD | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001052 | 198162248-10830-DETAIL-02_17_2025-GO95MLD-1^06240003.0314700 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001053 | 198234893-19630-DETAIL-10_25_2024-SVCENTBK-1^07216001.0208609 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001054 | 198329085-30549-DETAIL-10_25_2024-GO95HV-1^07216001.0201602 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001055 | 198401846-31846-DETAIL-03_05_2025-GO95HV-1^06241005.0131907 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001056 | 19856601-53840-ADMIN-12_23_2024-POLEREPL-1^06142012.0132507 | POLE | Non-HFTD | Distribution | 2024-12-23 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001057 | 19856788-86840-DETAIL-06_27_2023-GO95TCH-1^06244009.0346700 | OTHER | Non-HFTD | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001058 | 198652875-59830-DTLSB-05_08_2024-GO95HV-1^06244001.0108300 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001059 | 198698893-7059-DTLSB-09_30_2024-GO95BLTC-1^06245007.0231501 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001060 | 198698893-7059-DTLSB-09_30_2024-GO95MLD-1^06245007.0231501 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001061 | 198712671-99930-DETAIL-04_15_2024-GO95MLD-1^06145001.0136100 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001062 | 198894927-19739-DETAIL-10_14_2024-GO95MLD-1^07216001.0203204 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001063 | 198934520-36472-DTLSB-07_17_2023-GO95MLD-1^06243010.0118900 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001064 | 199144894-65259-DETAIL-03_20_2023-ABNDEQPM-1^07118004.0020501 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001065 | 199260071-9240-DETAIL-02_01_2023-GO95HV-1^06146002.0062300 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001066 | 199370021-19639-DETAIL-02_21_2024-GO95MLD-1^07113002.0181101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001067 | 1995095-31189-DTLSB-04_24_2024-GO95MLD-1^06245007.0224810 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001068 | 200002559-90559-DETAIL-03_01_2023-SVCWIND-1^07216001.0292640 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001069 | 200054934-86640-DTLSB-01_30_2023-GO95MLD-1^06248001.0257500 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001070 | 200333012-61450-DETAIL-01_31_2025-GO95MLD-1^06239004.0136200 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001071 | 200687838-93170-DETAIL-01_28_2025-BIRDDMG-1^06240004.0080002 | POLE | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001072 | 201028840-77649-DTLSB-04_09_2024-GO95MLD-1^06245007.0221300 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001073 | 201577117-34590-DETAIL-01_30_2025-GO95TCH-1^06239004.0245541 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001074 | 201642826-59440-DETAIL-02_15_2023-GO95MLD-1^06247002.0144700 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001075 | 199007304-3822-DETAIL-07_15_2024-GO95HV-1^06244005.0251200 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001076 | 199168482-46240-DETAIL-05_02_2022-GO95HV-1^07116001.0100102 | OTHER | HFTD Tier 2 | Distribution | 2022-05-02 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001077 | 199370021-19639-DETAIL-02_21_2024-RISEBKSP-1^07113002.0181101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001078 | 199631601-68611-DETAIL-01_15_2025-GO95HV-1^06239004.0255241 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001079 | 200002559-90559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292640 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001080 | 200002559-90559-DETAIL-03_01_2023-SVCWIND-2^07216001.0292640 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001081 | 200227850-81740-DTLSB-02_16_2024-GO95MLD-1^07216001.0262100 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001082 | 200235629-51740-DETAIL-05_13_2024-GUYNOINS-1^06142012.0124303 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001083 | 200333012-61450-DETAIL-01_31_2025-GO95HV-1^06239004.0136200 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001084 | 200955732-46780-DETAIL-02_13_2025-GO95TCH-1^06240004.0168146 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001085 | 200955732-46780-DETAIL-02_13_2025-SVCDEFLC-1^06240004.0168146 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001086 | 200968505-75459-DETAIL-03_06_2024-SVCROAD-1^06245007.0276503 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001087 | 200983095-55095-DETAIL-10_25_2024-GO95TCH-1^07216001.0209712 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001088 | 200983095-55095-DETAIL-10_25_2024-SVCDEFLC-1^07216001.0209712 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001089 | 20116995-26040-DETAIL-04_24_2024-GO95MLD-1^06145001.0031200 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001090 | 201182175-10063-DETAIL-03_28_2024-RISEBKSP-1^06247005.0341440 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001091 | 201577117-34590-DETAIL-01_30_2025-GO95HV-1^06239004.0245541 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001092 | 202456628-96940-DETAIL-04_10_2024-GO95MLD-1^06245002.0114201 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001093 | 203551918-55640-DETAIL-03_20_2025-GO95HV-1^06239003.0018003 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001094 | 203827704-94269-DETAIL-07_10_2024-RISEGRD-1^06244005.0126101 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001095 | 203832845-97529-DETAIL-05_16_2024-GO95MLD-1^06142012.0121800 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001096 | 203992044-84044-DETAIL-04_25_2024-GO95MLD-1^06142016.0163001 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001097 | 20404931-35931-DETAIL-04_04_2023-GO95HV-1^06143013.0237001 | OTHER | HFTD Tier 2 | Distribution | 2023-04-04 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001098 | 204526335-459-DETAIL-04_01_2024-COPLLEAN-1^06247005.0346741 | POLE | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001099 | 204627091-62480-DETAIL-02_12_2025-GO95HV-1^06240004.0167042 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001100 | 201679119-25579-DETAIL-07_24_2024-GO95MLD-1^06244004.0192600 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001101 | 201714994-72360-DETAIL-01_16_2025-GO95TCH-1^06239004.0256210 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001102 | 202629198-11920-AUDIT-02_18_2025-SVCNEUT-1^06240004.0080640 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001103 | 202629198-11920-DETAIL-09_06_2024-SVCDEFLC-1^06240004.0080640 | OTHER | HFTD Tier 2 | Distribution | 2024-09-06 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001104 | 20301608-89140-DETAIL-03_28_2024-GO95MLD-1^06147005.0169900 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001105 | 204776836-55629-DETAIL-08_21_2024-GRDRODHI-1^06245008.0246100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001106 | 204776836-55629-DETAIL-08_21_2024-GRDRODHI-2^06245008.0246100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001107 | 206045157-22849-DETAIL-03_15_2023-GUYHINS-1^07114001.0343201 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001108 | 206829789-16459-DTLSB-02_21_2024-GO95MLD-1^07216001.0260802 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001109 | 206921011-73240-DTLSB-02_15_2023-GO95MLD-1^06248001.0309500 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001110 | 207489153-46540-DETAIL-10_22_2024-GO95TCH-1^07216001.0208804 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001111 | 20750621-70889-DTLSB-08_15_2023-GO95MLD-1^06243009.0245500 | OTHER | Non-HFTD | Distribution | 2023-08-15 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001112 | 207862500-96740-DETAIL-03_18_2025-GO95MLD-1^06239002.0070404 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001113 | 208155693-42579-DTLSB-03_29_2022-GO95HV-1^06144006.0298701 | OTHER | Non-HFTD | Distribution | 2022-03-29 | 2027-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001114 | 208155693-42579-DTLSB-03_29_2022-GO95MLD-1^06144006.0298701 | OTHER | Non-HFTD | Distribution | 2022-03-29 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001115 | 208413050-12169-DETAIL-03_12_2024-ENCHRW-1^06245007.0288901 | OTHER | HFTD Tier 2 | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001116 | 20857160-15689-DETAIL-03_21_2024-GRDRODHI-1^06246005.0060300 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001117 | 208592519-95349-DTLSB-02_20_2024-SVCROAD-1^07216001.0262301 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001118 | 209026170-17990-DETAIL-08_15_2024-GO95HV-1^06246005.0135901 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001119 | 209060959-42679-DTLSB-08_27_2024-GRDRODHI-1^06245007.0012001 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001120 | 20913590-4532-DETAIL-07_06_2023-SVCROAD-1^06244008.0329903 | OTHER | HFTD Tier 2 | Distribution | 2023-07-06 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001121 | 204906452-80240-DETAIL-05_05_2022-GO95MLD-1^07116001.0101000 | OTHER | HFTD Tier 2 | Distribution | 2022-05-05 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001122 | 204918958-16493-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 10/002 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001123 | 205049311-17030-DETAIL-01_13_2025-SVCDEFLC-1^06240004.0085400 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001124 | 205296851-69039-DETAIL-02_22_2024-GO95MLD-1^07113001.0099401 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001125 | 205465429-70919-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 9/078 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-03 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001126 | 205691839-83589-DETAIL-06_03_2024-GO95MLD-1^06245006.0029701 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001127 | 205818365-72749-ADMIN-03_04_2025-POLEDERP-1^07216001.0295406 | POLE | Non-HFTD | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001128 | 205847095-17172-DETAIL-06_06_2023-GO95MLD-1^06244010.0340501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001129 | 206229578-42840-DETAIL-04_02_2024-GO95HV-1^06147005.0162800 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001130 | 20750621-70889-DTLSB-08_15_2023-GO95BLTC-1^06243009.0245500 | OTHER | Non-HFTD | Distribution | 2023-08-15 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001131 | 207519251-40640-DETAIL-04_15_2024-GO95MLD-1^06145001.0139601 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001132 | 207713018-11741-DETAIL-03_10_2025-GO95BLTC-1^06241005.0167700 | OTHER | HFTD Tier 3 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001133 | 208108758-33099-DETAIL-06_15_2022-GO95MLD-1^07116007.0112807 | OTHER | HFTD Tier 2 | Distribution | 2022-06-15 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001134 | 208155693-42579-ADMIN-06_30_2023-POLEDERP-1^06144006.0298701 | POLE | Non-HFTD | Distribution | 2023-06-30 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001135 | 208155693-42579-DTLSB-03_29_2022-RISEGRD-1^06144006.0298701 | OTHER | Non-HFTD | Distribution | 2022-03-29 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001136 | 208212583-19529-DTLSB-08_31_2023-GO95HV-1^06243007.0320601 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001137 | 208267552-73929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176300 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001138 | 20828535-50-DRONE_HY-10_16_2023-GO95HV-1^668033/01 19/003 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001139 | 208374521-21050-DTLSB-02_15_2023-GO95MLD-1^06248001.0308200 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001140 | 208445888-70940-DETAIL-01_21_2025-GO95TCH-1^06240004.0091602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001141 | 20857160-15689-DETAIL-03_21_2024-GO95MLD-1^06246005.0060300 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001142 | 208635068-97359-AUDIT-07_17_2024-GRDRODHI-1^06246005.0322501 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001143 | 208635068-97359-DETAIL-05_31_2024-GO95MLD-1^06246005.0322501 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001144 | 209060959-42679-DTLSB-08_27_2024-GO95MLD-1^06245007.0012001 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001145 | 209060959-42679-DTLSB-08_27_2024-GRDRODHI-2^06245007.0012001 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001146 | 20913590-4532-DETAIL-07_06_2023-GO95MLD-1^06244008.0329903 | OTHER | HFTD Tier 2 | Distribution | 2023-07-06 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001147 | 209468358-25849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155302 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001148 | 209476776-63410-DETAIL-03_12_2025-GO95HV-1^06238004.0223540 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001149 | 209684996-86550-DTLSB-01_30_2023-GO95MLD-1^06248001.0369801 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001150 | 210128191-37850-DTLSB-02_15_2023-GO95HV-1^06248001.0308203 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001151 | 210191290-53290-DETAIL-06_26_2024-GO95HV-1^06244005.0232610 | OTHER | Non-HFTD | Distribution | 2024-06-26 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001152 | 210191290-53290-DETAIL-06_26_2024-GO95MLD-1^06244005.0232610 | OTHER | Non-HFTD | Distribution | 2024-06-26 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001153 | 210191290-53290-DETAIL-06_26_2024-GUYHINS-1^06244005.0232610 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-06-26 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001154 | 210310500-3743-DETAIL-03_21_2024-GO95MLD-1^06246005.0061200 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001155 | 210449505-27050-DTLSB-02_01_2023-ENCHRW-1^06248001.0368301 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001156 | 210466236-92349-DETAIL-02_28_2024-SVCENTCO-1^07113002.0074300 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001157 | 210543017-35017-ADMIN-03_25_2024-GO95TCH-1^06147005.0112002 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001158 | 210791331-96599-DETAIL-06_10_2024-SVCROAD-1^06245007.0349006 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001159 | 211169071-24380-DETAIL-03_20_2025-GO95HV-1^06239002.0049400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001160 | 21225893-75893-DTLSB-05_02_2024-GO95MLD-1^06245007.0228906 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001161 | 212965171-49049-DETAIL-02_21_2024-GRDRODHI-1^07113001.0146100 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001162 | 213072049-40059-DETAIL-03_01_2023-GO95MLD-1^07117002.0197303 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001163 | 213256213-56059-DETAIL-05_29_2024-GO95HV-1^06246005.0099000 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001164 | 214019768-47179-DTLTRT-10_17_2023-GO95STUB-1^668010/00 16X/009 | OTHER | Non-HFTD | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001165 | 214129268-58359-DETAIL-05_31_2024-GO95MLD-1^06246005.0321501 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001166 | 214214420-87749-DTLSB-02_20_2024-GO95MLD-1^07216001.0262300 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001167 | 215246020-78249-DTLSB-02_19_2024-GO95MLD-1^07216001.0261204 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001168 | 2152854-62399-DETAIL-03_20_2024-GO95BLTC-1^06245001.0051000 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001169 | 2152854-62399-DETAIL-03_20_2024-SVCENTCO-1^06245001.0051000 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001170 | 215582834-91850-DETAIL-10_16_2024-GO95MLD-1^07216001.0205700 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001171 | 21564181-76059-DETAIL-05_05_2022-COPLLEAN-1^07217001.0120500 | POLE | Non-HFTD | Distribution | 2022-05-05 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001172 | 20965819-71969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 18/017 | POLE | Non-HFTD | Transmission | 2021-02-24 | 2024-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001173 | 209840222-99650-DETAIL-03_25_2025-GO95MLD-1^06239003.0018413 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001174 | 210173509-37473-ADMIN-04_26_2023-POLEREPL-1^06248007.0244900 | POLE | Non-HFTD | Distribution | 2023-04-26 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001175 | 210285428-9059-DETAIL-03_22_2024-GO95MLD-1^06247005.0287101 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001176 | 21081389-84112-DETAIL-06_20_2023-GO95MLD-1^06244009.0361401 | OTHER | Non-HFTD | Distribution | 2023-06-20 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001177 | 210931676-58423-DTLSB-04_23_2024-GO95MLD-1^06245007.0222742 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001178 | 211012830-17479-DETAIL-11_09_2022-SVCROAD-1^06246008.0026601 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001179 | 211298099-37639-DETAIL-07_30_2024-GUYHINS-1^06244005.0357400 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001180 | 21184000-96172-DTLSB-07_17_2023-GO95HV-1^06243010.0117801 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001181 | 212220714-36009-DTLSB-04_23_2024-GO95MLD-1^06245007.0223703 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001182 | 212220714-36009-DTLSB-04_23_2024-SVCENTCO-1^06245007.0223703 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001183 | 21225893-75893-DTLSB-05_02_2024-GO95HV-1^06245007.0228906 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001184 | 212965171-49049-DETAIL-02_21_2024-GO95MLD-1^07113001.0146100 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001185 | 213072049-40059-DETAIL-03_01_2023-GO95TCH-1^07117002.0197303 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001186 | 21313983-29579-DTLTRT-10_02_2023-GO95HV-1^668010/00 5/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001187 | 213428831-30373-DETAIL-03_09_2023-GO95MLD-1^07117002.0201140 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001188 | 213695412-31780-DETAIL-03_10_2025-GO95HV-1^06240004.0289900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001189 | 213711464-88622-ADMIN-08_05_2024-GO95STUB-1^06244008.0332900 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001190 | 213774098-82069-DTLTRT-06_30_2022-GO95MLD-1^668005/00 11/031 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001191 | 213978203-35359-DETAIL-06_18_2024-BIRDDMG-1^06245007.0290501 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001192 | 214220470-51470-DTLSB-02_22_2023-GO95MLD-1^07216001.0285507 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001193 | 214249139-65169-DTLTRT-06_10_2021-GO95HV-1^668041/00 5/018 | OTHER | Non-HFTD | Transmission | 2021-06-10 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001194 | 214507171-23649-DETAIL-02_28_2024-GUYHINS-1^07113001.0031303 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001195 | 214853204-3450-DTLSB-05_09_2024-GO95MLD-1^06244001.0113900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001196 | 2152854-62399-DETAIL-03_20_2024-CUTOUTAR-2^06245001.0051000 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001197 | 21572199-830-DTLTRT-10_19_2023-GO95HV-1^668010/00 6/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001198 | 215801273-85273-DTLSB-04_22_2024-SVCENTCO-1^06245007.0226111 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001199 | 215816024-72059-DETAIL-06_10_2024-GO95HV-1^06245007.0349602 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001200 | 215964370-95370-DETAIL-04_03_2024-GO95HV-1^06247005.0299700 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001201 | 215972096-36950-DTLSB-01_31_2023-SVCENTCO-1^06248001.0367805 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001202 | 216147923-57559-DETAIL-04_03_2024-BIRDDMG-1^06247005.0298900 | POLE | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001203 | 216334474-10999-ADMIN-06_19_2024-GO95HV-1^06245007.0357604 | OTHER | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001204 | 216575606-6668-ADMIN-07_11_2024-POLEREPL-1^06243009.0241800 | POLE | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001205 | 216575606-6668-DTLSB-08_14_2023-GO95HV-1^06243009.0241800 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001206 | 216639721-52720-DETAIL-02_17_2025-GO95HV-1^06240004.0278604 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001207 | 21669166-16249-DETAIL-03_11_2024-GO95MLD-1^06245006.0125600 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001208 | 217180965-70750-DETAIL-10_16_2024-GO95HV-1^07216001.0207802 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001209 | 217264259-17750-DETAIL-05_02_2024-GO95HV-1^06142012.0127202 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001210 | 217264259-17750-DETAIL-05_02_2024-GO95MLD-1^06142012.0127202 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001211 | 217342982-75633-DTLSB-08_26_2024-SVCENTCO-1^06245007.0113300 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001212 | 217644519-85973-DETAIL-03_08_2023-GO95MLD-1^07117002.0207600 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001213 | 217720963-79559-DTLSB-02_13_2024-GO95TCH-1^07216001.0188200 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001214 | 218000746-10323-DTLSB-05_01_2024-SVCWIND-1^06245007.0228441 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001215 | 218028469-43050-DETAIL-04_22_2024-GO95MLD-1^06146001.0360001 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001216 | 218483550-46830-DETAIL-01_29_2025-SVCDEFLC-1^06240004.0176804 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001217 | 218902816-48409-DETAIL-04_08_2024-CONDFRAY-1^06147005.0237201 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001218 | 218988814-31534-DETAIL-05_01_2024-BIRDDMG-1^06143015.0346101 | POLE | HFTD Tier 2 | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001219 | 21951534-16750-DTLSB-05_07_2024-GO95MLD-1^06245001.0191501 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001220 | 219904800-76739-DETAIL-02_20_2024-GO95MLD-1^07113002.0180100 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001221 | 220204820-18549-DETAIL-08_12_2024-GO95MLD-1^06245006.0104902 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001222 | 2152854-62399-DETAIL-03_20_2024-GUYHINS-1^06245001.0051000 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001223 | 2155446-37249-DETAIL-03_08_2023-GO95TCH-1^07216001.0295605 | OTHER | Non-HFTD | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001224 | 216091161-29470-DTLTRT-10_16_2023-GO95HV-1^668010/00 11/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001225 | 216121388-53299-DETAIL-08_01_2024-GO95MLD-1^06245006.0154701 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001226 | 216639721-52720-DETAIL-02_17_2025-GO95TCH-1^06240004.0278604 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001227 | 216639721-52720-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0278604 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001228 | 21669166-16249-DETAIL-03_11_2024-GO95HV-1^06245006.0125600 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001229 | 216910583-77561-DETAIL-06_13_2023-GO95MLD-1^06243009.0037601 | OTHER | Non-HFTD | Distribution | 2023-06-13 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001230 | 217786823-31839-DETAIL-03_14_2023-GO95MLD-1^07114001.0276305 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001231 | 217793606-30240-DETAIL-02_18_2025-GO95BLTC-1^06240004.0100010 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001232 | 218013749-21649-DETAIL-02_22_2024-SVCENTBK-1^07216001.0345800 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001233 | 21900619-5469-DTLTRT-11_03_2023-GO95MLD-1^668010/00 18/026 | OTHER | Non-HFTD | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001234 | 21900619-5469-DTLTRT-11_03_2023-UBPBCTGD-1^668010/00 18/026 | OTHER | Non-HFTD | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001235 | 219184323-47550-DTLSB-05_22_2024-GO95HV-1^06243001.0031200 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001236 | 219342309-2270-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0165740 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001237 | 219952734-1089-DETAIL-06_10_2024-GO95HV-1^06245007.0349604 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001238 | 220092558-73949-DETAIL-03_09_2023-GO95MLD-1^07117002.0208201 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001239 | 220278255-65579-DETAIL-01_18_2023-GO95BLTC-1^06148004.0207701 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001240 | 220278255-65579-DETAIL-01_18_2023-GO95HV-1^06148004.0207701 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001241 | 220278255-65579-DETAIL-01_18_2023-GO95MLD-2^06148004.0207701 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001242 | 220291173-91799-DTLSB-07_31_2023-GO95MLD-1^06243009.0087600 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001243 | 220535678-73749-ADMIN-04_04_2025-POLEDERP-1^06244007.0130801 | POLE | HFTD Tier 2 | Distribution | 2025-04-04 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001244 | 220575844-40360-DETAIL-10_16_2024-GO95MLD-1^07216001.0205800 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001245 | 220709613-34360-DTLSB-03_28_2022-POLETOP-1^06144006.0225701 | POLE | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001246 | 220881899-67899-DETAIL-06_19_2024-GO95HV-1^06245007.0339001 | OTHER | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001247 | 220278255-65579-DETAIL-01_18_2023-COPLLEAN-1^06148004.0207701 | POLE | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001248 | 220278255-65579-DETAIL-01_18_2023-GO95MLD-1^06148004.0207701 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001249 | 220562058-66719-DETAIL-08_14_2023-POLETOP-1^668036/00 8/050 | POLE | HFTD Tier 2 | Transmission | 2023-08-14 | 2024-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001250 | 220575844-40360-DETAIL-10_16_2024-SVCENTBK-1^07216001.0205800 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001251 | 220709613-34360-DTLSB-03_28_2022-GO95HV-1^06144006.0225701 | OTHER | Non-HFTD | Distribution | 2022-03-28 | 2027-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001252 | 220893333-70460-DETAIL-10_16_2024-GO95TCH-1^07216001.0206844 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001253 | 221284461-79449-DETAIL-05_10_2022-SVCNEUT-1^07116001.0092401 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001254 | 221349033-38669-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/010 | OTHER | Non-HFTD | Transmission | 2021-06-07 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001255 | 222136384-15540-DTLTRT-10_04_2023-GO95HV-1^668010/00 19/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001256 | 222138429-65939-DTLSB-02_15_2024-GO95MLD-1^07216001.0264001 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001257 | 222254818-94359-DETAIL-05_16_2022-GO95HV-1^07116001.0059000 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001258 | 222545960-2309-DETAIL-03_21_2024-GO95HV-1^06147004.0118800 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001259 | 222553394-1639-DTLSB-02_07_2024-GO95MLD-1^07216001.0199304 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001260 | 222729661-93549-DETAIL-02_28_2024-GO95HV-1^07113001.0145701 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001261 | 222769869-76209-DETAIL-03_04_2024-GO95HV-1^06147004.0010303 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001262 | 222769869-76209-DETAIL-03_04_2024-GO95MLD-1^06147004.0010303 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001263 | 223063639-79249-DTLSB-10_03_2024-GO95MLD-1^06245007.0218802 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001264 | 223138010-6309-DETAIL-03_05_2024-GO95HV-1^06147004.0022003 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001265 | 2232698-83849-DTLSB-02_20_2024-SVCENTCO-2^07216001.0260506 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001266 | 223438282-71520-DETAIL-02_17_2025-GO95HV-1^06240004.0277442 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001267 | 223438282-71520-DETAIL-02_17_2025-GO95TCH-1^06240004.0277442 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001268 | 223569139-64773-DETAIL-03_01_2023-GO95MLD-1^07117002.0195206 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001269 | 22360477-6099-DETAIL-04_09_2024-GO95HV-1^06147005.0217002 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001270 | 223637275-66703-DETAIL-03_05_2024-SVCROAD-1^06245007.0276400 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001271 | 223764784-26329-DETAIL-05_08_2024-GO95HV-1^06142012.0120006 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001272 | 220881899-67899-DETAIL-06_19_2024-GO95MLD-1^06245007.0339001 | OTHER | HFTD Tier 2 | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001273 | 220936450-3459-DETAIL-07_23_2024-BIRDDMG-1^06245007.0315902 | POLE | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001274 | 221202220-52929-DETAIL-04_11_2022-GO95CL10-1^06142012.0130801 | OTHER | Non-HFTD | Distribution | 2022-04-11 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001275 | 221284461-79449-DETAIL-05_10_2022-GO95HV-1^07116001.0092401 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001276 | 221284461-79449-DETAIL-05_10_2022-GO95MLD-1^07116001.0092401 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001277 | 221718938-52619-DETAIL-08_13_2024-GUYNOINS-1^06245005.0363301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001278 | 222074421-89602-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0309000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001279 | 22220644-67950-DTLSB-03_22_2022-SVCROAD-1^06146005.0137202 | OTHER | Non-HFTD | Distribution | 2022-03-22 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001280 | 222224679-32889-DTLSB-05_07_2024-GO95MLD-1^06245002.0135800 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001281 | 222314411-56411-DETAIL-04_30_2024-GO95HV-1^06142015.0027900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001282 | 222465394-44549-DTLSB-02_08_2024-SVCROAD-1^07216001.0198100 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001283 | 222553394-1639-DTLSB-02_07_2024-GUYHINS-1^07216001.0199304 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001284 | 222720730-42989-DETAIL-11_07_2022-GO95MLD-1^06246008.0028701 | OTHER | HFTD Tier 2 | Distribution | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001285 | 222728894-69539-DETAIL-02_29_2024-GO95HV-1^07113001.0101902 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001286 | 222728894-69539-DETAIL-02_29_2024-GO95MLD-1^07113001.0101902 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001287 | 222728894-69539-DETAIL-02_29_2024-SVCDEFLC-1^07113001.0101902 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001288 | 222807139-8549-DETAIL-02_28_2023-GO95MLD-1^07216001.0298702 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001289 | 222965188-5279-DRONE_HY-09_29_2023-GO95HV-1^668033/00 3/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-29 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001290 | 223063639-79249-ADMIN-02_19_2025-POLEREPL-1^06245007.0218802 | POLE | Non-HFTD | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001291 | 2232698-83849-DTLSB-02_20_2024-GO95MLD-1^07216001.0260506 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001292 | 2232698-83849-DTLSB-02_20_2024-SVCENTCO-1^07216001.0260506 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001293 | 22348533-6050-DTLSB-05_23_2024-GRDBROKE-1^06243001.0116001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001294 | 223592381-4481-DETAIL-05_10_2022-GO95MLD-1^07116001.0093801 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001295 | 223592381-4481-DETAIL-05_10_2022-GRDRODHI-1^07116001.0093801 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001296 | 223948248-64999-DTLSB-08_22_2024-GO95MLD-1^06245006.0326600 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001297 | 22382176-83989-DETAIL-01_17_2023-CONDFRAY-1^06148004.0175001 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001298 | 223948248-64999-DTLSB-08_22_2024-ENCHRW-1^06245006.0326600 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001299 | 223995109-75860-DETAIL-05_02_2024-GO95MLD-1^06142012.0125106 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001300 | 224353252-59099-AUDIT-04_18_2024-GO95HV-1^06147004.0350501 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001301 | 224353252-59099-DETAIL-03_14_2024-GRDRODHI-1^06147004.0350501 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001302 | 224475323-69323-DETAIL-04_30_2024-GO95HV-1^06142016.0060101 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001303 | 224589889-76409-DTLSB-09_03_2024-GO95HV-1^06245007.0013101 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001304 | 224788996-70123-DTLSB-04_29_2024-GO95BLTC-1^06245007.0221542 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001305 | 224833219-76459-DTLSB-02_21_2024-GO95MLD-1^07216001.0261800 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001306 | 224883036-3131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001307 | 224883036-33131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001308 | 224883036-5960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/046 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001309 | 224985598-80890-DETAIL-01_24_2025-GO95HV-1^06239004.0247040 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001310 | 22509001-47219-DTLTRT-08_15_2022-POLETOP-1^668005/00 11/086 | POLE | Non-HFTD | Transmission | 2022-08-15 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001311 | 225227709-93489-DETAIL-05_31_2024-GO95HV-1^06246005.0333300 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001312 | 225308998-72143-DETAIL-03_09_2023-ENCHRW-1^07117002.0209102 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001313 | 22550001-92209-DETAIL-01_17_2023-GO95HV-1^06148004.0222702 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001314 | 22550001-92209-DETAIL-01_17_2023-GO95MLD-1^06148004.0222702 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001315 | 225587959-85169-ADMIN-07_24_2020-INSULPLM-1^668041/00 8/018 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2020-07-24 | 2023-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001316 | 225748111-42149-DETAIL-02_20_2024-CLRTOUCH-1^07113001.0137200 | CONDUCTOR | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001317 | 226046686-49639-DETAIL-02_27_2023-GO95MLD-1^07216001.0298805 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001318 | 226046686-49639-DETAIL-02_27_2023-GUYHINS-2^07216001.0298805 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001319 | 226046686-49639-DETAIL-02_27_2023-SVCWIND-1^07216001.0298805 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001320 | 226163443-28639-DTLSB-02_13_2024-SVCROAD-1^07216001.0188203 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001321 | 226646765-87765-DETAIL-03_20_2023-GO95MLD-1^07117004.0061830 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001322 | 224353252-59099-DETAIL-03_14_2024-GO95MLD-1^06147004.0350501 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001323 | 224364558-91160-AUDIT-04_02_2024-GO95MLD-1^06245002.0124701 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001324 | 224497643-78160-AUDIT-03_08_2023-GO95MLD-1^06248001.0277302 | OTHER | Non-HFTD | Distribution | 2023-03-08 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001325 | 225078549-1759-DTLSB-02_05_2024-GO95HV-1^07216001.0190940 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001326 | 22509001-47219-ADMIN-12_31_2018-POLEREPL-1^668005/00 11/086 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001327 | 225208341-70660-DETAIL-03_13_2024-GO95MLD-1^06147004.0085004 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001328 | 225451198-77859-DETAIL-04_08_2024-GRDRODHI-1^06246005.0071200 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001329 | 225587959-85169-DTLTRT-06_10_2021-GO95HV-1^668041/00 8/018 | OTHER | Non-HFTD | Transmission | 2021-06-10 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001330 | 22566295-32440-DETAIL-02_24_2025-CLRTOUCH-1^06240004.0152902 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-24 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001331 | 225703628-86459-DETAIL-06_03_2024-GO95MLD-1^06246005.0314301 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001332 | 226010833-22833-DETAIL-02_27_2024-GUYHINS-1^07113001.0139906 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001333 | 226046686-49639-DETAIL-02_27_2023-GUYHINS-1^07216001.0298805 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001334 | 226055616-89909-DETAIL-03_28_2024-GO95HV-1^06147005.0112100 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001335 | 226163443-28639-DTLSB-02_13_2024-GO95MLD-1^07216001.0188203 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001336 | 22641701-16829-DETAIL-05_14_2024-GO95MLD-1^06142012.0122404 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001337 | 226682573-32039-DETAIL-07_15_2024-GO95HV-1^06244005.0254702 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001338 | 227352128-97330-DETAIL-01_13_2025-SVCDEFLC-1^06240004.0085602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001339 | 227604895-57449-DETAIL-03_15_2023-GO95MLD-1^07114001.0326001 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001340 | 228127509-71570-DETAIL-03_28_2023-ABNDEQPM-1^06240004.0165501 | OTHER | HFTD Tier 2 | Distribution | 2023-03-28 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001341 | 228455369-24679-DETAIL-03_06_2024-GO95MLD-1^06147004.0017002 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001342 | 229078143-12180-DETAIL-01_25_2023-RISECLMB-1^06240005.0016201 | OTHER | HFTD Tier 2 | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001343 | 229078143-12180-DETAIL-02_25_2025-RISEGRD-1^06240005.0016201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001344 | 229167281-38380-DETAIL-03_17_2025-GO95HV-1^06239001.0048800 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001345 | 229239593-90069-DRONE_HY-09_14_2023-GO95HV-1^668002/00 8/020 | OTHER | Non-HFTD | Transmission | 2023-09-14 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001346 | 229351513-44009-ADMIN-02_27_2025-POLEREPL-1^06246009.0129900 | POLE | HFTD Tier 2 | Distribution | 2025-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001347 | 226764849-97349-DTLSB-02_20_2024-GO95MLD-1^07216001.0261205 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001348 | 227233457-30590-DETAIL-02_03_2025-GO95HV-1^06239004.0244844 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001349 | 22750640-57711-DETAIL-02_24_2025-GO95MLD-1^06241005.0154400 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001350 | 227752135-4859-DETAIL-10_16_2024-GO95MLD-1^07216001.0200500 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001351 | 227880459-55929-ADMIN-08_02_2024-POLEREPL-1^06142012.0147507 | POLE | Non-HFTD | Distribution | 2024-08-02 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001352 | 227954811-3180-DETAIL-02_14_2025-GO95TCH-1^06240004.0168043 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001353 | 228626555-68600-DETAIL-03_27_2025-GO95HV-1^06239003.0016713 | OTHER | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001354 | 228706349-47660-DETAIL-03_14_2016-SVCWIND-1^06142012.0148908 | OTHER | Non-HFTD | Distribution | 2016-03-14 | 2019-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001355 | 228954591-92099-DETAIL-05_25_2023-GO95HV-1^07117007.0227600 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001356 | 229499834-96549-DTLSB-02_14_2024-CLRTOPOL-1^07216001.0198301 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001357 | 229499834-96549-DTLSB-02_14_2024-GO95MLD-1^07216001.0198301 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001358 | 229769878-73840-DETAIL-01_16_2023-SVCDEFLC-2^06240004.0092506 | OTHER | HFTD Tier 2 | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001359 | 229942078-1849-DTLSB-04_22_2024-SVCENTCO-1^06245007.0226404 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001360 | 23011868-63400-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001361 | 230266141-48373-DETAIL-03_02_2023-GO95HV-1^07117002.0200300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001362 | 230266141-48373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001363 | 230439944-61780-DTLTRT-09_27_2023-GO95MLD-1^668010/00 10/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001364 | 230468428-19428-DTLSB-10_07_2024-RISEGRD-1^06245007.0230900 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001365 | 230801322-26750-DETAIL-03_20_2025-GO95HV-1^06239003.0018103 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001366 | 231170844-94629-DTLSB-09_07_2023-GO95HV-1^06243008.0120600 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001367 | 231431458-73458-DTLSB-02_07_2024-GO95TCH-1^07216001.0199109 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001368 | 231779806-5319-DETAIL-10_24_2022-GO95MLD-1^06247008.0315200 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001369 | 232319566-68060-DTLTRT-10_09_2023-GO95MLD-1^668010/00 13/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001370 | 232319566-68060-DTLTRT-10_09_2023-GUYHINS-2^668010/00 13/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001371 | 232319566-68060-DTLTRT-10_09_2023-GUYHINS-3^668010/00 13/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001372 | 229357139-33370-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/065 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001373 | 229499834-96549-DTLSB-02_14_2024-GO95TCH-1^07216001.0198301 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001374 | 229582911-30789-DETAIL-01_23_2023-GO95HV-1^06148004.0192300 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001375 | 229582911-30789-DETAIL-01_23_2023-GO95MLD-1^06148004.0192300 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001376 | 229769878-73840-DETAIL-01_22_2025-SVCDEFLC-1^06240004.0092506 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001377 | 229769878-73840-DETAIL-01_22_2025-SVCDEFLC-2^06240004.0092506 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001378 | 229935828-9828-DTLSB-02_19_2024-GO95TCH-1^07216001.0264207 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001379 | 229935828-9828-DTLSB-02_19_2024-SVCENTBK-1^07216001.0264207 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001380 | 229980559-40889-DETAIL-07_24_2024-ABNDEQPM-1^06244005.0136200 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001381 | 229980559-40889-DETAIL-07_24_2024-GO95MLD-1^06244005.0136200 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001382 | 23011868-58882-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001383 | 23011868-72400-DTLTRT-09_30_2020-GO95HV-1^668018/00 10/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001384 | 230274649-30719-ADMIN-06_24_2021-POLEDERP-1^668005/00 16/075 | POLE | Non-HFTD | Transmission | 2021-06-24 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001385 | 230540189-94870-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/007 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001386 | 230986196-5049-DETAIL-08_06_2024-GO95HV-1^06245004.0330200 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001387 | 231392499-40269-DTLTRT-07_05_2022-GO95HV-1^668005/00 15/033 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001388 | 231392499-40269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 15/033 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001389 | 231472224-90799-DETAIL-03_05_2024-GO95MLD-1^06245007.0276100 | OTHER | HFTD Tier 2 | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001390 | 232319566-68060-DTLTRT-10_09_2023-GUYHINS-1^668010/00 13/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001391 | 232323349-23173-DETAIL-01_22_2025-RISEBKSP-1^06240004.0091001 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001392 | 232342204-64579-DETAIL-09_01_2021-ENCHRW-1^06240008.0298500 | OTHER | Non-HFTD | Distribution | 2021-09-01 | 2024-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001393 | 232544276-50269-DTLTRT-10_09_2023-GO95HV-1^668010/00 11/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001394 | 232845901-57901-DETAIL-03_30_2023-GUYHINS-1^06142016.0055103 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001395 | 232985663-98330-DETAIL-02_27_2025-SVCENTCO-1^06240004.0067100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001396 | 233125098-17170-DETAIL-04_10_2024-GO95MLD-1^06245002.0113001 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001397 | 233436849-2370-DETAIL-05_06_2024-GUYNOINS-1^06142012.0124006 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001398 | 232319566-68060-DTLTRT-10_09_2023-GUYHINS-4^668010/00 13/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001399 | 232323349-23173-DETAIL-01_22_2025-RISEGRD-1^06240004.0091001 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001400 | 232335988-93043-DTLSB-05_06_2024-GO95MLD-1^06245007.0221745 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001401 | 232400513-91023-DTLTRT-10_24_2022-GO95HV-1^668075/00 16/024 | OTHER | Non-HFTD | Transmission | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001402 | 232410653-37909-DTLSB-05_02_2024-ENCHRW-1^06245007.0228800 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001403 | 232544276-50269-DTLTRT-10_09_2023-ABNDEQPM-1^668010/00 11/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001404 | 232544276-50269-DTLTRT-10_09_2023-GO95MLD-1^668010/00 11/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001405 | 2326751-23599-DETAIL-04_15_2024-GO95MLD-1^06145001.0139600 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001406 | 233550391-20339-DETAIL-02_28_2024-SVCROAD-1^07113001.0030001 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001407 | 233550391-20339-DETAIL-02_28_2024-SVCWIND-1^07113001.0030001 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001408 | 233636159-35470-DETAIL-04_23_2024-GRDRODHI-1^06145001.0026600 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001409 | 233693436-40470-DETAIL-01_15_2025-GO95HV-1^06239004.0255146 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001410 | 233824254-49254-DETAIL-03_28_2023-GO95TCH-1^06142016.0084804 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001411 | 233880618-5570-DETAIL-03_20_2024-GO95MLD-1^06245002.0120200 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001412 | 234028333-74030-DRONE_VS-11_13_2024-XARMSPCR-1^668014/00 7/031 | CROSSARM | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001413 | 234196596-91049-DETAIL-10_15_2024-GO95MLD-1^07216001.0202405 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001414 | 234196596-91049-DETAIL-10_15_2024-SVCNEUT-1^07216001.0202405 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001415 | 234283449-67870-DETAIL-04_11_2024-GO95MLD-1^06245002.0102302 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001416 | 234296577-48590-DETAIL-02_03_2025-GO95HV-1^06239004.0243942 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001417 | 234298484-2584-DETAIL-04_25_2024-GO95HV-1^06142016.0175600 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001418 | 233481279-95670-DETAIL-09_29_2020-GO95HV-1^668018/00 6/006 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001419 | 233513731-81470-DETAIL-03_13_2024-GO95MLD-1^06147004.0070200 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001420 | 233540680-97080-DETAIL-02_26_2025-GO95HV-1^06240004.0217401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001421 | 233636159-35470-DETAIL-04_23_2024-GO95MLD-1^06145001.0026600 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001422 | 233994071-47439-DETAIL-03_20_2024-GO95HV-1^06244004.0067400 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001423 | 234296577-48590-DETAIL-02_03_2025-GO95MLD-1^06239004.0243942 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001424 | 234630489-86819-ADMIN-01_15_2025-POLEREPL-1^668005/00 1/078 | POLE | Non-HFTD | Transmission | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001425 | 234630489-86819-ADMIN-01_15_2025-POLTOPSW-1^668005/00 1/078 | SWITCH | Non-HFTD | Transmission | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001426 | 234691302-27980-DETAIL-02_25_2025-GO95CL10-1^06240005.0019100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001427 | 234937884-39260-DETAIL-01_22_2025-BIRDDMG-1^06239004.0255547 | POLE | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001428 | 234937884-39260-DETAIL-01_22_2025-GO95HV-1^06239004.0255547 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001429 | 235510214-43839-DTLSB-02_14_2024-GO95HV-1^07216001.0198306 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001430 | 235647630-2279-DETAIL-03_11_2024-GO95TCH-1^06147004.0027901 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001431 | 235890784-64770-DETAIL-04_17_2024-GO95MLD-1^06144001.0012300 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001432 | 235914551-54789-DTLSB-08_14_2023-GO95MLD-1^06243009.0246000 | OTHER | HFTD Tier 2 | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001433 | 23610841-17579-DETAIL-03_13_2024-CLRTOUCH-1^06147004.0072100 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001434 | 23610841-17579-DETAIL-03_13_2024-GUYHINS-1^06147004.0072100 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001435 | 23614859-38929-DETAIL-05_08_2024-SVCDEFLC-1^06142012.0120301 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001436 | 236742188-23439-DETAIL-10_17_2024-GO95MLD-1^07216001.0204500 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001437 | 236742188-23439-DETAIL-10_17_2024-SVCENTCO-1^07216001.0204500 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001438 | 236851079-92713-DETAIL-03_05_2024-SVCWIND-1^06245007.0276441 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001439 | 236888910-40169-DTLTRT-07_15_2022-GO95HV-1^668005/00 5/048 | OTHER | Non-HFTD | Transmission | 2022-07-15 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001440 | 236888910-40169-DTLTRT-07_15_2022-UBPRMSHD-1^668005/00 5/048 | CONNECTION DEVICE | Non-HFTD | Transmission | 2022-07-15 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001441 | 237099035-24359-DETAIL-02_22_2024-SVCENTCO-1^07113001.0156300 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001442 | 2373269-39549-DTLSB-02_16_2024-GO95MLD-1^07216001.0262002 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001443 | 234447644-55149-AUDIT-02_27_2024-GO95MLD-1^07216001.0199302 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001444 | 234920824-85170-DETAIL-02_09_2023-GO95MLD-1^06146004.0161900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001445 | 234989578-7469-DTLTRT-07_06_2022-GO95HV-1^668005/00 11/037 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001446 | 235255538-66750-DETAIL-03_25_2025-GO95HV-1^06239003.0019306 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001447 | 235441354-96370-DETAIL-03_20_2024-GO95MLD-1^06245001.0051001 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001448 | 235647630-2279-DETAIL-03_11_2024-GO95MLD-1^06147004.0027901 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001449 | 235806925-9370-DETAIL-03_05_2025-GO95HV-1^06240003.0184901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001450 | 235876800-95429-DETAIL-05_06_2024-GO95MLD-1^06142012.0124109 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001451 | 236511745-43039-DETAIL-10_08_2024-CLRTOUCH-1^07216001.0202107 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001452 | 236511745-43039-DETAIL-10_08_2024-GO95CL10-1^07216001.0202107 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001453 | 23655164-22599-DETAIL-06_24_2024-GO95MLD-1^06244005.0233341 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001454 | 236555096-75849-DTLSB-04_15_2024-SVCWIND-1^06245007.0227004 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001455 | 236666070-60508-DTLSB-02_22_2023-GO95MLD-1^07216001.0285503 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001456 | 236735648-94049-DETAIL-10_09_2024-GO95HV-1^07216001.0203100 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001457 | 236735648-94049-DETAIL-10_09_2024-GUYHINS-1^07216001.0203100 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001458 | 237068915-15470-DTLSB-05_08_2024-GO95MLD-1^06244001.0035100 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001459 | 237271520-32520-DETAIL-05_10_2022-GO95MLD-1^07116001.0093805 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001460 | 2373269-39549-DTLSB-02_16_2024-GO95TCH-1^07216001.0262002 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001461 | 2373269-39549-DTLSB-02_16_2024-SVCENTCO-1^07216001.0262002 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001462 | 2373269-39549-DTLSB-02_16_2024-SVCENTCO-2^07216001.0262002 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001463 | 237364878-89960-DTLTRT-09_30_2020-GO95HV-1^668018/00 1/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001464 | 237641808-18692-DETAIL-07_13_2023-GO95HV-1^06244008.0328740 | OTHER | Non-HFTD | Distribution | 2023-07-13 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001465 | 237720273-96629-DTLSB-09_07_2023-GO95HV-1^06243008.0026301 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001466 | 237854589-84759-DETAIL-03_26_2024-GO95MLD-1^06246005.0056500 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001467 | 238186934-94890-DETAIL-09_09_2024-SVCDEFLC-1^06240004.0097301 | OTHER | HFTD Tier 2 | Distribution | 2024-09-09 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001468 | 237495403-88680-DETAIL-01_30_2025-GO95MLD-1^06240004.0164604 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001469 | 237495403-88680-DETAIL-03_28_2023-GUYHINS-1^06240004.0164604 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001470 | 237641808-18692-DETAIL-07_13_2023-GO95MLD-1^06244008.0328740 | OTHER | Non-HFTD | Distribution | 2023-07-13 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001471 | 238217911-20970-DETAIL-12_20_2022-GO95HV-1^668001/00 8/023 | OTHER | Non-HFTD | Transmission | 2022-12-20 | 2027-12-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001472 | 238217911-20970-DTLTRT-10_24_2022-GUYHINS-1^668001/00 8/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001473 | 238217911-20970-DTLTRT-10_24_2022-GUYHINS-2^668001/00 8/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001474 | 238603515-64763-DETAIL-03_20_2023-GO95MLD-1^07117003.0093102 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001475 | 238905805-67339-DETAIL-10_25_2024-GO95TCH-1^07216001.0208606 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001476 | 239473254-57549-DTLSB-02_07_2024-GO95MLD-1^07216001.0199210 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001477 | 239632110-86070-DETAIL-02_13_2025-GO95BLTC-1^06240004.0169207 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001478 | 239740469-37459-DETAIL-03_01_2023-SVCWIND-1^07216001.0291740 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001479 | 239845283-34680-DETAIL-01_30_2025-GUYHINS-1^06240004.0164506 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001480 | 239996178-50043-DTLSB-04_30_2024-GO95HV-1^06245007.0221940 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001481 | 240346846-68539-AUDIT-10_28_2024-GUYHINS-1^07216001.0200306 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-28 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001482 | 240426316-31280-DETAIL-04_03_2023-GO95HV-1^06143014.0146102 | OTHER | HFTD Tier 2 | Distribution | 2023-04-03 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001483 | 240511583-279-ADMIN-05_30_2024-ABNDEQPM-1^06246005.0219400 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001484 | 240665133-82540-DTLTRT-10_02_2023-GO95MLD-1^668010/00 18/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001485 | 240966606-86606-DETAIL-01_29_2025-GO95MLD-1^06239004.0227200 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001486 | 240988908-39908-DETAIL-03_16_2023-GO95MLD-1^07113001.0043507 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001487 | 241598765-49765-DETAIL-04_24_2023-GO95MLD-1^07117003.0082401 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001488 | 241663028-72080-DETAIL-04_02_2024-GO95HV-1^06147005.0092401 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001489 | 241732556-36059-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0059700 | CONDUCTOR | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001490 | 242070466-78049-DETAIL-02_28_2023-GO95MLD-1^07216001.0298800 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001491 | 242267661-1950-DETAIL-03_24_2025-SVCDEFLC-1^06238004.0028602 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001492 | 242586393-59049-DTLSB-02_28_2024-GO95CL10-1^07216001.0273702 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001493 | 238217911-20970-DTLTRT-10_24_2022-GUYHINS-3^668001/00 8/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001494 | 23845958-92670-DETAIL-03_20_2024-GO95HV-1^06245002.0017500 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001495 | 238608215-9215-DETAIL-08_13_2024-GO95MLD-1^06245005.0364300 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001496 | 238608215-9215-DETAIL-08_13_2024-GRDRODHI-1^06245005.0364300 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001497 | 238889903-779-DTLSB-05_23_2024-GO95MLD-1^06243001.0238800 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001498 | 238991563-84529-DTLSB-07_26_2023-GO95MLD-1^06243009.0087800 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001499 | 239211065-69170-DETAIL-01_21_2025-SVCDEFLC-1^06239004.0256303 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001500 | 239286604-18099-DETAIL-08_05_2024-GO95MLD-1^06244005.0029002 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001501 | 239426058-53069-DTLTRT-06_10_2021-GO95HV-1^668041/00 1/015 | OTHER | Non-HFTD | Transmission | 2021-06-10 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001502 | 239570371-37469-DTLTRT-07_20_2022-GO95HV-1^668005/00 12/054 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001503 | 239595922-16109-DTLSB-08_26_2024-GO95MLD-1^06245007.0115200 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001504 | 239845283-34680-DETAIL-03_28_2023-SVCDEFLC-1^06240004.0164506 | OTHER | HFTD Tier 2 | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001505 | 240029984-73909-DTLSB-05_02_2024-GO95HV-1^06245007.0229843 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001506 | 240029984-73909-DTLSB-05_02_2024-GO95MLD-1^06245007.0229843 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001507 | 240082246-15670-DETAIL-01_24_2025-CLRTOUCH-1^06239004.0257840 | CONDUCTOR | HFTD Tier 3 | Distribution | 2025-01-24 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001508 | 240082246-15670-DETAIL-01_24_2025-GO95HV-1^06239004.0257840 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001509 | 240178078-94869-DTLTRT-06_10_2021-GO95HV-1^668041/00 3/016 | OTHER | Non-HFTD | Transmission | 2021-06-10 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001510 | 240346846-68539-AUDIT-11_13_2024-GO95HV-1^07216001.0200306 | OTHER | Non-HFTD | Distribution | 2024-11-13 | 2029-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001511 | 240426316-31280-DETAIL-04_03_2023-GO95MLD-1^06143014.0146102 | OTHER | HFTD Tier 2 | Distribution | 2023-04-03 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001512 | 240511583-279-DETAIL-05_30_2024-GO95MLD-1^06246005.0219400 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001513 | 240613489-20380-DETAIL-03_19_2024-GO95MLD-1^06245002.0039001 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001514 | 240613489-20380-DETAIL-03_19_2024-GUYHINS-1^06245002.0039001 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001515 | 241282521-79580-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0169044 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001516 | 241732556-36059-DETAIL-03_16_2023-GO95MLD-1^07113001.0059700 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001517 | 242070466-78049-DETAIL-02_28_2023-GO95TCH-1^07216001.0298800 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001518 | 242234638-76243-DTLSB-04_30_2024-GO95MLD-1^06245007.0220940 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001519 | 242586393-59049-DTLSB-02_28_2024-GO95HV-1^07216001.0273702 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001520 | 242586393-59049-DTLSB-02_28_2024-GO95MLD-1^07216001.0273702 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001521 | 242872093-45780-DTLSB-01_30_2023-GO95MLD-1^06248001.0259400 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001522 | 243463184-62989-DETAIL-07_16_2024-GO95MLD-1^06244005.0275302 | OTHER | Non-HFTD | Distribution | 2024-07-16 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001523 | 243598429-81149-DTLSB-02_26_2024-GO95HV-1^07216001.0261900 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001524 | 243714775-84289-DTLSB-08_28_2024-GO95HV-1^06245007.0141505 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001525 | 244067051-12232-DETAIL-06_21_2023-GO95HV-1^06244009.0282200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001526 | 244361847-70059-DTLSB-02_08_2024-GO95MLD-1^07216001.0197000 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001527 | 244446910-90170-DETAIL-03_11_2025-GO95HV-1^06238003.0016701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001528 | 244643076-52880-DETAIL-01_30_2025-CLRTOUCH-1^06239004.0244602 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001529 | 244643076-52880-DETAIL-01_30_2025-GO95HV-1^06239004.0244602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001530 | 244656121-50529-DETAIL-05_07_2024-GO95MLD-1^06142012.0123207 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001531 | 244656121-50529-DETAIL-05_07_2024-GRDRODHI-1^06142012.0123207 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001532 | 244879818-71092-DETAIL-03_25_2024-GO95MLD-1^06244005.0145300 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001533 | 244930831-45750-DETAIL-02_11_2025-GO95MLD-1^06239004.0125900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001534 | 244968651-94779-ADMIN-01_27_2025-POLEREPL-1^06245007.0114802 | POLE | HFTD Tier 2 | Distribution | 2025-01-27 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001535 | 245040461-50530-DETAIL-03_05_2025-GO95TCH-1^06240004.0203704 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001536 | 245667494-70189-DETAIL-07_16_2024-GO95TCH-1^06244005.0275301 | OTHER | Non-HFTD | Distribution | 2024-07-16 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001537 | 245667494-70189-DETAIL-07_16_2024-GUYHINS-1^06244005.0275301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-16 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001538 | 245861860-68514-ADMIN-02_06_2018-COPLLEAN-1^06142016.0051005 | POLE | Non-HFTD | Distribution | 2018-02-06 | 2021-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001539 | 245952409-57839-DTLSB-02_21_2024-GO95CL10-1^07216001.0260800 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001540 | 245952409-57839-DTLSB-02_21_2024-SVCENTCO-1^07216001.0260800 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001541 | 24604433-49633-DETAIL-10_12_2022-GO95HV-1^668005/08 8X4/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001542 | 246153901-32089-DETAIL-06_25_2024-GO95MLD-1^06244005.0237000 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001543 | 246153901-32089-DETAIL-06_25_2024-GRDRODHI-1^06244005.0237000 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001544 | 24258814-47449-DTLSB-02_08_2024-SVCDEFLC-1^07216001.0196101 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001545 | 242770747-47259-DETAIL-03_16_2023-GO95HV-1^07114001.0281640 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001546 | 242896923-11189-DTLSB-08_31_2023-ABNDEQPM-1^06243007.0294200 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001547 | 243057091-18269-DTLSB-08_26_2024-GO95MLD-1^06245007.0111201 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001548 | 243057091-18269-DTLSB-08_26_2024-SVCDEFLC-1^06245007.0111201 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001549 | 243445383-92180-DTLSB-02_14_2023-GO95HV-1^06248001.0339702 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001550 | 243465698-24299-DTLSB-07_01_2024-GO95MLD-1^06245006.0180003 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001551 | 243630588-20349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061901 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001552 | 243714775-84289-DTLSB-08_28_2024-ANCHIDLE-1^06245007.0141505 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001553 | 243714775-84289-DTLSB-08_28_2024-GO95MLD-1^06245007.0141505 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001554 | 244067051-12232-DETAIL-06_21_2023-GO95MLD-1^06244009.0282200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001555 | 244067051-12232-DETAIL-06_21_2023-SVCENTBK-1^06244009.0282200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001556 | 244463208-57240-DETAIL-01_30_2025-SVCDEFLC-1^06240004.0162703 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001557 | 244581331-32459-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096400 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001558 | 244608974-87539-DTLSB-02_07_2024-SVCENTCO-1^07216001.0199400 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001559 | 244656121-50529-AUDIT-05_29_2024-GUYHINS-1^06142012.0123207 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-29 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001560 | 244656121-50529-DETAIL-05_07_2024-GO95HV-1^06142012.0123207 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001561 | 244721766-80939-DTLSB-02_08_2024-CLMBTRE-1^07216001.0198203 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001562 | 244774768-22570-DETAIL-04_11_2023-SVCDEFLC-1^06240004.0169500 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001563 | 244968651-94779-DTLSB-08_27_2024-GRDRODHI-1^06245007.0114802 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001564 | 245692458-81690-AUDIT-04_02_2025-GRDRODHI-1^06239004.0361002 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001565 | 246413203-39789-DETAIL-06_18_2024-SVCDEFLC-1^06245007.0298202 | OTHER | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001566 | 247155698-54750-DETAIL-03_20_2025-GO95HV-1^06239003.0018004 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001567 | 247337193-30080-DETAIL-02_14_2025-GO95HV-1^06240004.0164500 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001568 | 247341155-73639-DETAIL-10_09_2024-GO95CL10-1^07216001.0204202 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001569 | 246779621-89670-DTLTRT-10_16_2023-GO95HV-1^668010/00 16X/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001570 | 247158994-33430-DETAIL-03_03_2025-GO95MLD-1^06241005.0365200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001571 | 247692784-45784-DETAIL-03_11_2025-SVCENTCO-1^06238004.0272802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001572 | 247712055-82940-DETAIL-02_24_2025-GO95TCH-1^06240004.0152601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001573 | 247712055-82940-DETAIL-02_24_2025-GUYNOINS-1^06240004.0152601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001574 | 247712055-82940-DETAIL-02_24_2025-GUYNOINS-2^06240004.0152601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001575 | 247765231-30579-DETAIL-03_12_2024-GO95TCH-1^06147004.0055200 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001576 | 248144023-15419-DTLTRT-08_16_2022-GO95MLD-1^668005/00 15/091 | OTHER | Non-HFTD | Transmission | 2022-08-16 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001577 | 248254716-18472-AUDIT-10_08_2024-GO95HV-1^06245006.0090640 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001578 | 248467292-8292-DTLSB-02_09_2023-GUYNOINS-1^06248001.0228600 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001579 | 248489091-83080-DETAIL-03_18_2025-GO95HV-1^06239001.0053700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001580 | 248581834-76139-DTLSB-02_08_2024-GO95MLD-1^07216001.0197141 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001581 | 248587889-30430-DTLTRT-11_03_2023-GO95HV-1^668010/00 16/026 | OTHER | Non-HFTD | Transmission | 2023-11-03 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001582 | 248587889-30430-DTLTRT-11_03_2023-UBPBXARM-1^668010/00 16/026 | CROSSARM | Non-HFTD | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001583 | 248722571-52770-DETAIL-02_19_2025-GO95CL10-1^06241005.0275902 | OTHER | HFTD Tier 3 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001584 | 248890641-63023-DTLTRT-10_01_2024-GUYNOINS-2^06245007.0230301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001585 | 24911518-34770-DETAIL-04_23_2024-GO95MLD-1^06145001.0023101 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001586 | 24923753-87629-DTLSB-09_07_2023-GO95HV-1^06243008.0026100 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001587 | 249462415-47059-DETAIL-10_09_2024-GO95TCH-1^07216001.0205108 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001588 | 249765269-68039-DETAIL-07_08_2024-GO95HV-1^06244005.0135900 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001589 | 250146279-74520-DTLTRT-09_30_2020-GO95HV-1^668018/00 5/004 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001590 | 250361152-41929-AUDIT-10_09_2023-GO95HV-1^06243008.0176500 | OTHER | HFTD Tier 2 | Distribution | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001591 | 250547013-90113-DTLTRT-10_10_2023-GUYNOINS-1^668010/00 12A/044 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001592 | 250547013-90113-DTLTRT-10_10_2023-GUYNOINS-2^668010/00 12A/044 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001593 | 250547013-90113-DTLTRT-10_10_2023-GUYNOINS-3^668010/00 12A/044 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001594 | 247341155-73639-DETAIL-10_09_2024-SVCROAD-1^07216001.0204202 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001595 | 247492573-35129-DETAIL-05_09_2024-GO95MLD-1^06142012.0120601 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001596 | 247690238-70959-DETAIL-04_08_2024-GO95MLD-1^06247005.0352501 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001597 | 247692784-45784-DETAIL-03_11_2025-SVCDEFLC-1^06238004.0272802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001598 | 247712055-82940-DETAIL-02_24_2025-SVCDEFLC-1^06240004.0152601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001599 | 247755083-73109-DTLSB-09_06_2023-GO95MLD-1^06243007.0188501 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001600 | 247765231-30579-DETAIL-03_12_2024-CLRTOUCH-1^06147004.0055200 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001601 | 247765231-30579-DETAIL-03_12_2024-GUYHINS-1^06147004.0055200 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001602 | 247872599-25769-ADMIN-02_07_2022-POLEDERP-1^668005/03 8/004 | POLE | Non-HFTD | Transmission | 2022-02-07 | 2025-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001603 | 248144023-15419-DTLTRT-08_16_2022-GO95HV-1^668005/00 15/091 | OTHER | Non-HFTD | Transmission | 2022-08-16 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001604 | 248144023-15419-DTLTRT-08_16_2022-GRDRODHI-1^668005/00 15/091 | OTHER | Non-HFTD | Transmission | 2022-08-16 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001605 | 248337195-87580-DETAIL-04_24_2024-SVCDEFLC-1^06145001.0031101 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001606 | 248408075-99580-DTLSB-05_13_2024-GO95MLD-1^06245001.0292200 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001607 | 248408075-99580-DTLSB-05_13_2024-GO95MLD-2^06245001.0292200 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001608 | 248423074-23139-DETAIL-07_16_2024-GO95HV-1^06244005.0275203 | OTHER | Non-HFTD | Distribution | 2024-07-16 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001609 | 248520383-86653-DETAIL-06_13_2023-GO95HV-1^06244010.0272700 | OTHER | HFTD Tier 2 | Distribution | 2023-06-13 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001610 | 248520383-86653-DETAIL-06_13_2023-GO95MLD-1^06244010.0272700 | OTHER | HFTD Tier 2 | Distribution | 2023-06-13 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001611 | 248890641-63023-DTLTRT-10_01_2024-GUYNOINS-1^06245007.0230301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001612 | 249161564-74564-DTLSB-04_11_2024-SVCWIND-1^06245007.0224207 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001613 | 250146279-35520-DTLTRT-09_30_2020-GO95HV-1^668018/00 5/004 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001614 | 250205177-41590-DETAIL-02_03_2025-GO95MLD-1^06239004.0243941 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001615 | 250282783-56199-DTLSB-02_07_2023-GO95MLD-1^06248001.0156201 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001616 | 250627125-35880-DTLSB-05_07_2024-GO95MLD-1^06245001.0296300 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001617 | 250680178-6440-DETAIL-03_12_2025-SVCENTCO-1^06238004.0223402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001618 | 25090050-1129-DTLSB-08_17_2023-GUYNOINS-1^06243009.0131502 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-08-17 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001619 | 250547013-90113-DTLTRT-10_10_2023-GUYNOINS-4^668010/00 12A/044 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001620 | 250632834-56980-DTLTRT-09_27_2023-GO95MLD-1^668010/00 18X/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001621 | 250827333-75980-DTLSB-03_28_2022-POLETOP-1^06144006.0224700 | POLE | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001622 | 250926936-47759-DETAIL-03_27_2024-GO95MLD-1^06247005.0329100 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001623 | 251123192-74959-DETAIL-05_29_2024-GRDRODHI-1^06246005.0209900 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001624 | 2514386-77179-DETAIL-01_23_2023-ABNDEQPM-1^06148004.0192405 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001625 | 2514386-77179-DETAIL-01_23_2023-GO95MLD-1^06148004.0192405 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001626 | 251498157-54218-DTLSB-02_27_2024-GO95MLD-1^07216001.0271700 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001627 | 252035785-52639-DETAIL-07_09_2024-GO95HV-1^06244004.0192602 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001628 | 252055586-42861-DETAIL-02_24_2025-GO95MLD-1^06239004.0366802 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001629 | 252373528-17443-DETAIL-03_09_2023-SVCENTCO-1^07117002.0205201 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001630 | 252760935-75390-DETAIL-05_15_2024-GO95BLTC-1^06142012.0124700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001631 | 252825715-64699-DETAIL-03_06_2025-GO95HV-1^06240004.0271100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001632 | 252825715-64699-DETAIL-03_06_2025-SVCDEFLC-1^06240004.0271100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001633 | 253086302-37302-DETAIL-01_22_2025-GO95MLD-1^06239004.0254540 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001634 | 253124706-27170-DETAIL-01_24_2025-GO95HV-1^06239004.0257942 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001635 | 253329148-45159-ADMIN-08_05_2020-ABNDEQPM-1^668005/00 11/036 | OTHER | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001636 | 253522895-40989-DTLSB-08_28_2024-GO95HV-1^06245007.0141501 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001637 | 253622068-94690-DTLSB-05_13_2024-GO95HV-1^06244001.0155201 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001638 | 254337378-32549-DETAIL-10_14_2024-GO95MLD-1^07216001.0203301 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001639 | 254431831-41630-DETAIL-01_24_2025-GO95CL10-1^06240004.0189703 | OTHER | HFTD Tier 2 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001640 | 254431831-41630-DETAIL-01_24_2025-GRDRODHI-1^06240004.0189703 | OTHER | HFTD Tier 2 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001641 | 254676048-12929-DTLSB-08_23_2023-GO95MLD-1^06243009.0158901 | OTHER | Non-HFTD | Distribution | 2023-08-23 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001642 | 2550968-83169-DTLTRT-10_11_2023-GO95HV-1^668010/00 4/044 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001643 | 255421504-67710-DETAIL-03_17_2025-GO95HV-1^06238004.0157202 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001644 | 25090050-1129-DTLSB-08_17_2023-GUYNOINS-2^06243009.0131502 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-08-17 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001645 | 250926936-47759-DETAIL-03_27_2024-GO95HV-1^06247005.0329100 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001646 | 25115883-18699-DETAIL-06_25_2024-SVCENTCO-1^06244005.0239000 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001647 | 251322758-41569-DRONE_HY-10_02_2023-BIRDWST-1^668002/00 22/036 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001648 | 251436873-38920-DETAIL-02_25_2025-SVCDEFLC-1^06241005.0250005 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001649 | 2514386-77179-DETAIL-01_23_2023-GO95HV-1^06148004.0192405 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001650 | 2514386-77179-DETAIL-01_23_2023-GRDRODHI-1^06148004.0192405 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001651 | 2514386-77179-DETAIL-01_23_2023-GRDRODHI-2^06148004.0192405 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001652 | 251462206-20359-DETAIL-03_28_2024-GO95HV-1^06247005.0333700 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001653 | 251498157-54218-DTLSB-02_27_2024-GO95HV-1^07216001.0271700 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001654 | 252371009-86009-DETAIL-03_01_2023-SVCWIND-1^07216001.0291820 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001655 | 252453848-37730-DTLTRT-10_18_2023-GO95HV-1^668010/00 16/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001656 | 25261131-73979-DETAIL-06_05_2024-GO95MLD-1^06246006.0267503 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001657 | 252760935-75390-DETAIL-05_15_2024-GO95HV-1^06142012.0124700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001658 | 252760935-75390-DETAIL-05_15_2024-GO95MLD-1^06142012.0124700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001659 | 253004103-15329-DTLSB-08_29_2023-GO95MLD-1^06243009.0121201 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001660 | 253086302-37302-DETAIL-01_22_2025-GO95HV-1^06239004.0254540 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001661 | 253197140-66540-DTLTRT-11_16_2022-GO95HV-1^668075/00 2/027 | OTHER | Non-HFTD | Transmission | 2022-11-16 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001662 | 253350183-59649-DETAIL-03_02_2023-GO95MLD-1^07216001.0291601 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001663 | 253375880-64149-DETAIL-02_27_2024-SVCENTCO-1^07113002.0184102 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001664 | 253522895-40989-DTLSB-08_28_2024-GO95MLD-1^06245007.0141501 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001665 | 253522895-40989-DTLSB-08_28_2024-SVCDEFLC-1^06245007.0141501 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001666 | 253622068-94690-DTLSB-05_13_2024-GO95MLD-1^06244001.0155201 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001667 | 253795194-75690-DETAIL-01_15_2025-BIRDDMG-1^06240004.0099301 | POLE | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001668 | 253909161-63890-DETAIL-04_15_2024-GO95MLD-1^06145001.0247900 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001669 | 255966356-43080-DETAIL-03_03_2025-GO95HV-1^06240004.0051100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001670 | 256266141-23189-DETAIL-01_23_2023-GO95HV-1^06148004.0193202 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001671 | 256404770-80190-DETAIL-03_01_2022-SVCROAD-1^06146006.0052603 | OTHER | Non-HFTD | Distribution | 2022-03-01 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001672 | 256608023-99849-DETAIL-08_13_2024-GO95MLD-1^06245005.0361500 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001673 | 257258521-90169-DETAIL-02_17_2025-BIRDDMG-1^06240004.0278603 | POLE | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001674 | 257369858-64839-DETAIL-10_14_2024-GO95CL10-1^07216001.0200300 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001675 | 257527040-80959-DETAIL-03_13_2024-SVCDEFLC-1^06245007.0286000 | OTHER | HFTD Tier 2 | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001676 | 257564505-48539-DETAIL-07_10_2024-GO95MLD-1^06244004.0196000 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001677 | 258099104-35962-DETAIL-07_07_2023-GO95HV-1^06244008.0330501 | OTHER | Non-HFTD | Distribution | 2023-07-07 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001678 | 258099104-35962-DETAIL-07_07_2023-GO95MLD-1^06244008.0330501 | OTHER | Non-HFTD | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001679 | 258140214-22214-DETAIL-04_25_2024-GO95HV-1^06142016.0177901 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001680 | 259703669-72069-DTLTRT-10_25_2022-GO95HV-1^668075/00 3/026 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001681 | 259974013-98334-DETAIL-05_01_2024-GO95HV-1^06143015.0334900 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001682 | 260016890-63739-DTLSB-02_20_2024-GO95CLSV-1^07216001.0261307 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001683 | 260139313-3590-DTLSB-05_23_2024-GO95HV-1^06243001.0238801 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001684 | 260139313-3590-DTLSB-05_23_2024-GO95MLD-1^06243001.0238801 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001685 | 260403783-10279-DTLSB-05_28_2024-GO95HV-1^06243001.0126103 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001686 | 26088180-15169-DTLTRT-07_18_2022-GO95HV-1^668005/00 1/049 | OTHER | Non-HFTD | Transmission | 2022-07-18 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001687 | 26093114-45740-DETAIL-02_19_2025-SVCROOF-1^06240004.0218603 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001688 | 260933126-89249-DETAIL-02_27_2024-GO95TCH-1^07113002.0071100 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001689 | 261195548-26839-DTLSB-02_05_2024-SVCDEFLC-1^07216001.0185004 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001690 | 254675790-76970-DETAIL-03_20_2025-GO95HV-1^06239002.0027501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001691 | 2550968-83169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 4/044 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001692 | 255471524-84524-DETAIL-04_25_2024-GO95HV-1^06142016.0160201 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001693 | 255867706-60339-DETAIL-02_27_2023-GO95MLD-1^07216001.0297808 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001694 | 255867706-60339-DETAIL-02_27_2023-SVCWIND-1^07216001.0297808 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001695 | 256181879-76029-DETAIL-05_06_2024-GO95MLD-1^06142012.0124102 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001696 | 25683014-45679-DTLSB-01_30_2023-GO95MLD-1^06248001.0256000 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001697 | 256950929-25759-DETAIL-03_26_2024-GO95MLD-1^06246005.0054501 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001698 | 257235591-51282-DTLSB-08_14_2023-GO95MLD-1^06243009.0246104 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001699 | 257440269-83269-DTLTRT-07_05_2022-GO95HV-1^668005/00 6/034 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001700 | 257440269-83269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 6/034 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001701 | 257635582-57582-DETAIL-04_04_2024-GO95MLD-1^06147005.0240201 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001702 | 258436741-78280-DETAIL-03_18_2025-GO95HV-1^06239001.0059701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001703 | 258437554-32290-DETAIL-03_20_2024-GO95HV-1^06245001.0070600 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001704 | 25844841-66841-DETAIL-03_27_2023-GO95HV-1^06142016.0053501 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001705 | 258729064-81164-DETAIL-04_29_2024-SVCDEFLC-1^06142016.0175402 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001706 | 259008313-59313-DETAIL-07_11_2024-GO95MLD-1^06244005.0220401 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001707 | 259294950-7709-DTLSB-07_23_2024-GO95HV-1^06245007.0109201 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001708 | 259646826-89189-DETAIL-03_25_2024-GO95MLD-1^06244005.0142406 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001709 | 259720412-54750-DETAIL-03_27_2025-SVCDEFLC-1^06239003.0017401 | OTHER | Non-HFTD | Distribution | 2025-03-27 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001710 | 260016890-63739-DTLSB-02_20_2024-SVCWIND-1^07216001.0261307 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001711 | 260023849-14859-AUDIT-10_28_2024-CLRTOPOL-1^07216001.0201403 | OTHER | Non-HFTD | Distribution | 2024-10-28 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001712 | 260254518-11612-DETAIL-06_12_2023-GUYHINS-1^06244009.0363600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001713 | 260254518-11612-DETAIL-06_12_2023-GUYHINS-2^06244009.0363600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001714 | 260256969-10019-DTLTRT-08_03_2022-GO95HV-1^668005/00 3/079 | OTHER | Non-HFTD | Transmission | 2022-08-03 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001715 | 260352998-76760-DTLTRT-09_30_2020-GO95HV-1^668018/00 8/002 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001716 | 260534399-16400-DETAIL-05_13_2024-GO95MLD-1^06142012.0124304 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001717 | 260659678-20330-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 7/052 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001718 | 260684483-4500-DTLSB-05_22_2024-GO95MLD-1^06243001.0104400 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001719 | 26093114-45740-DETAIL-02_19_2025-BIRDDMG-1^06240004.0218603 | POLE | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001720 | 26122899-87670-DETAIL-11_01_2023-POLEREPL-1^668044/00 1/055 | POLE | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001721 | 26122899-79732-DETAIL-11_01_2023-POLEREPL-1^668044/00 1/055 | POLE | HFTD Tier 2 | Transmission | 2023-11-01 | 2024-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001722 | 261435351-1779-DETAIL-03_06_2024-GO95MLD-1^06147004.0027501 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001723 | 261480528-26612-DETAIL-06_12_2023-GUYHINS-1^06244009.0363700 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001724 | 261480528-26612-DETAIL-06_12_2023-GUYHINS-2^06244009.0363700 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001725 | 261556308-44700-DETAIL-04_22_2024-GO95MLD-1^06145001.0029400 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001726 | 261557464-54700-DETAIL-10_22_2024-GO95MLD-1^07216001.0208611 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001727 | 261697643-32800-DTLSB-05_22_2024-GO95HV-1^06243001.0102901 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001728 | 261753550-75301-DETAIL-01_31_2025-GO95HV-1^06239004.0136207 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001729 | 261794604-94800-DETAIL-10_25_2024-ABNDEQPM-1^07216001.0209808 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001730 | 262101528-33379-DETAIL-04_08_2024-GO95HV-1^06246005.0076600 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001731 | 262503418-47200-DRONE_HY-10_25_2023-GO95HV-1^668087/00 8/002 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001732 | 262546251-11119-ADMIN-08_05_2020-POLEDERP-1^668005/00 11/082 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001733 | 262862697-39970-DETAIL-06_27_2024-SVCROAD-2^06240004.0063202 | OTHER | HFTD Tier 2 | Distribution | 2024-06-27 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001734 | 262938960-29790-DETAIL-01_15_2025-SVCDEFLC-1^06239004.0256204 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001735 | 263566413-30423-AUDIT-03_07_2023-GUYNOINS-1^06248001.0369820 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001736 | 261473783-96763-DETAIL-03_11_2025-GO95HV-1^06238004.0273802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001737 | 261473783-96763-DETAIL-03_11_2025-SVCDEFLC-1^06238004.0273802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001738 | 261794604-94800-DETAIL-10_25_2024-SVCDEFLC-1^07216001.0209808 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001739 | 262189751-69619-DETAIL-08_11_2023-POLETOP-1^668036/00 8/049 | POLE | HFTD Tier 2 | Transmission | 2023-08-11 | 2024-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001740 | 262272348-77849-DTLSB-02_21_2024-GO95MLD-1^07216001.0262503 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001741 | 26364276-32799-AUDIT-10_15_2024-GUYHINS-1^06245007.0237702 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001742 | 263724329-9839-DETAIL-02_19_2024-GO95MLD-1^07113002.0186001 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001743 | 263980893-70369-DTLTRT-06_23_2021-COPLLEAN-1^668041/00 15/032 | POLE | Non-HFTD | Transmission | 2021-06-23 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001744 | 264066710-60949-DTLSB-04_29_2024-SVCWIND-1^06245007.0225105 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001745 | 264066710-60949-DTLSB-04_29_2024-SVCWIND-2^06245007.0225105 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001746 | 264197834-25100-DTLSB-01_30_2023-GO95HV-1^06248001.0258500 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001747 | 262346916-15159-DTLSB-09_30_2024-GUYNOINS-1^06245007.0233400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001748 | 262862697-39970-DETAIL-02_27_2025-GO95TCH-1^06240004.0063202 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001749 | 262862697-39970-DETAIL-02_27_2025-SVCROAD-1^06240004.0063202 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001750 | 262862697-39970-DETAIL-06_27_2024-SVCROAD-1^06240004.0063202 | OTHER | HFTD Tier 2 | Distribution | 2024-06-27 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001751 | 263036430-65400-DETAIL-05_06_2024-SVCENTCO-1^06142012.0124005 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001752 | 263317043-73760-DETAIL-09_09_2024-SVCENTCO-1^06240004.0097042 | OTHER | HFTD Tier 2 | Distribution | 2024-09-09 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001753 | 263734101-89659-DETAIL-05_09_2022-GO95MLD-1^07116001.0099102 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001754 | 263829048-29069-DTLTRT-06_30_2022-GO95HV-1^668005/00 4/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001755 | 264588263-74309-DETAIL-03_05_2024-GO95HV-1^06147005.0176900 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001756 | 264629019-37400-DTLSB-05_07_2024-GO95MLD-1^06245002.0248800 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001757 | 264735926-63370-DETAIL-01_15_2025-GO95HV-1^06239004.0255144 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001758 | 265659933-61452-DETAIL-06_26_2023-GO95TCH-1^06244009.0303100 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001759 | 265768818-28000-DETAIL-03_20_2024-GO95HV-1^06245002.0017700 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001760 | 265768818-28000-DETAIL-03_20_2024-GO95MLD-1^06245002.0017700 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001761 | 266100601-32200-DETAIL-04_16_2024-GO95MLD-1^06145002.0187900 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001762 | 266529476-68131-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/044 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001763 | 266546388-29170-DETAIL-01_23_2025-SVCDEFLC-1^06240004.0080204 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001764 | 266651108-20849-DTLSB-02_22_2024-GO95MLD-1^07216001.0263906 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001765 | 267040571-81700-DETAIL-04_16_2024-GO95HV-1^06145002.0181800 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001766 | 267094059-83440-DETAIL-03_24_2025-GO95MLD-1^06238004.0011500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001767 | 264512435-15749-DTLSB-04_25_2024-GO95MLD-1^06245007.0229400 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001768 | 264555309-80029-DETAIL-05_06_2024-GO95MLD-1^06142012.0125002 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001769 | 264645548-12343-DTLSB-04_30_2024-GO95MLD-1^06245007.0221841 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001770 | 264645548-12343-DTLSB-04_30_2024-SVCWIND-1^06245007.0221841 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001771 | 264875522-40329-DETAIL-05_15_2024-GO95HV-1^06142012.0125900 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001772 | 265056784-35032-DETAIL-03_06_2025-GRDRODHI-1^06241005.0120600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001773 | 265220555-71555-DETAIL-06_20_2023-GO95HV-1^06244010.0259600 | OTHER | HFTD Tier 2 | Distribution | 2023-06-20 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001774 | 265614404-64560-DETAIL-01_28_2025-GO95HV-1^06239004.0258500 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001775 | 265659933-61452-DETAIL-06_26_2023-GO95MLD-1^06244009.0303100 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001776 | 266064923-30623-DTLSB-09_05_2024-GO95MLD-1^06246006.0314041 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001777 | 266070565-84663-DETAIL-04_24_2023-GO95MLD-1^07117003.0087000 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001778 | 266423381-37400-DETAIL-04_16_2024-GO95HV-1^06145002.0183800 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001779 | 266529476-10909-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/044 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001780 | 266656341-9500-DETAIL-04_15_2024-GO95MLD-1^06145002.0066601 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001781 | 26691084-24269-DRONE_HY-09_21_2023-GO95HV-1^668002/00 1/001 | OTHER | HFTD Tier 2 | Transmission | 2023-09-21 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001782 | 267040571-81700-DETAIL-04_16_2024-GO95MLD-1^06145002.0181800 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001783 | 267094059-83440-DETAIL-03_24_2025-GO95HV-1^06238004.0011500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001784 | 267680380-29483-DTLSB-10_02_2024-GO95MLD-1^06245007.0218540 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001785 | 267773109-26212-DETAIL-07_03_2023-GO95MLD-1^06244009.0243500 | OTHER | HFTD Tier 2 | Distribution | 2023-07-03 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001786 | 267804386-84010-DTLSB-05_22_2024-GO95MLD-1^06244001.0336200 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001787 | 268228026-86339-DETAIL-10_09_2024-GO95MLD-1^07216001.0200213 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001788 | 268433438-93438-DETAIL-03_11_2024-GO95HV-1^06245006.0121001 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001789 | 268484203-76529-DTLSB-07_31_2023-GO95STUB-1^06243009.0085100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001790 | 268617713-80813-DETAIL-04_29_2024-GRDRODHI-1^06142016.0079700 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001791 | 268617713-80813-DETAIL-04_29_2024-SVCROAD-1^06142016.0079700 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001792 | 268629071-71459-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0147101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001793 | 267094059-83440-DETAIL-03_24_2025-XARMSPCR-1^06238004.0011500 | CROSSARM | HFTD Tier 2 | Distribution | 2025-03-24 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001794 | 267304143-78800-DETAIL-02_09_2023-GO95MLD-1^06146004.0084000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001795 | 267520049-15209-DETAIL-03_04_2024-RISEBKSP-1^06147004.0012301 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001796 | 267637659-20010-DRONE_VS-11_13_2024-BIRDDMG-1^668038/00 4/068 | POLE | Non-HFTD | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001797 | 267676365-6251-DETAIL-02_24_2025-SVCROAD-1^06239004.0366707 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001798 | 268032451-28031-DETAIL-02_27_2025-GO95MLD-1^06241005.0177900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001799 | 268072153-39079-DTLSB-02_16_2023-GO95MLD-1^06248001.0299200 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001800 | 268500136-95623-DTLSB-04_23_2024-GO95MLD-1^06245007.0223443 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001801 | 268617713-80813-DETAIL-04_29_2024-GO95MLD-1^06142016.0079700 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001802 | 268629071-71459-DETAIL-02_21_2024-GO95HV-1^07113001.0147101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001803 | 268629071-71459-DETAIL-02_21_2024-GO95MLD-1^07113001.0147101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001804 | 26905518-63449-DETAIL-07_23_2024-SVCDEFLC-1^06245006.0143001 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001805 | 269069608-20610-DTLSB-05_09_2024-GUYNOINS-1^06244001.0215402 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001806 | 269102753-17798-AUDIT-05_09_2024-GO95BLTC-1^06247005.0338400 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001807 | 269102753-17798-DETAIL-03_22_2024-GO95MLD-1^06247005.0338400 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001808 | 269336908-3159-DETAIL-03_22_2024-GO95HV-1^06247005.0287301 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001809 | 269740180-4389-DTLSB-09_30_2024-GO95HV-1^06245007.0231341 | OTHER | Non-HFTD | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001810 | 269879964-30010-DTLSB-02_09_2023-ANCHIDLE-1^06248001.0279742 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001811 | 270068784-24499-DETAIL-02_04_2025-GO95HV-1^06240004.0165748 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001812 | 270260910-12320-DTLSB-10_03_2024-GUYNOINS-1^06245006.0339000 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001813 | 270478708-96210-ADMIN-01_11_2022-POLEDERP-1^06147001.0106500 | POLE | Non-HFTD | Distribution | 2022-01-11 | 2025-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001814 | 27105073-98438-DETAIL-06_05_2024-GO95MLD-1^06246006.0267201 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001815 | 271230798-70710-DETAIL-03_19_2024-GRDRODHI-1^06245002.0014803 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001816 | 271487939-51230-DETAIL-01_14_2025-GO95CL10-1^06240004.0083703 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001817 | 27189926-4000-DTLTRT-10_17_2023-GO95HV-1^668010/00 22X/008 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001818 | 268715604-71410-DTLSB-02_09_2023-GO95HV-1^06248001.0279602 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001819 | 269069608-20610-DTLSB-05_09_2024-GUYNOINS-2^06244001.0215402 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001820 | 269336908-3159-AUDIT-05_09_2024-GRDRODHI-1^06247005.0287301 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001821 | 269399381-77710-DETAIL-04_11_2024-GO95MLD-1^06245002.0143100 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001822 | 269879964-30010-DTLSB-02_09_2023-ABNDEQPM-1^06248001.0279742 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001823 | 269879964-30010-DTLSB-02_09_2023-GO95HV-1^06248001.0279742 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001824 | 270142973-68010-ADMIN-10_13_2023-POLEDERP-1^07216001.0214802 | POLE | Non-HFTD | Distribution | 2023-10-13 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001825 | 270970770-59323-DETAIL-06_19_2024-GO95MLD-1^06246006.0136801 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001826 | 270981249-75773-DETAIL-03_02_2023-GUYNOINS-1^07117002.0198201 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001827 | 271330629-16069-DTLTRT-06_14_2021-GO95HV-1^668041/00 8/021 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001828 | 271605593-51250-DETAIL-02_04_2025-GO95HV-1^06239004.0134143 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001829 | 271605593-51250-DETAIL-02_04_2025-GO95MLD-1^06239004.0134143 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001830 | 27189926-4000-DTLTRT-10_17_2023-GUYHINS-1^668010/00 22X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001831 | 272102909-73173-DETAIL-01_21_2025-SVCDEFLC-1^06240004.0091502 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001832 | 272167824-34460-DETAIL-02_04_2025-SVCDEFLC-1^06239004.0244952 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001833 | 272561601-90469-DETAIL-02_23_2023-GO95HV-1^668002/00 8/030 | OTHER | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001834 | 273024913-35559-DETAIL-04_04_2024-GO95HV-1^06247005.0297200 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001835 | 273082443-87514-DETAIL-03_31_2025-SVCRUBCM-1^06241005.0115605 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130001836 | 273121196-53269-DETAIL-03_27_2024-GO95MLD-1^06247005.0336600 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001837 | 27312190-95549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105503 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001838 | 273322676-35069-DTLTRT-10_23_2023-GO95HV-1^668010/00 18/042 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001839 | 274323368-64079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 14/075 | OTHER | HFTD Tier 2 | Transmission | 2023-09-21 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001840 | 274361883-82680-DTLTRT-09_27_2023-GO95HV-1^668010/00 15/006 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001841 | 274361883-82680-DTLTRT-09_27_2023-GUYNOINS-1^668010/00 15/006 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001842 | 274361883-82680-DTLTRT-09_27_2023-GUYNOINS-2^668010/00 15/006 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001843 | 274361883-82680-DTLTRT-09_27_2023-GUYNOINS-3^668010/00 15/006 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001844 | 27189926-4000-DTLTRT-10_17_2023-GUYHINS-2^668010/00 22X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001845 | 272157782-3569-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/008 | OTHER | Non-HFTD | Transmission | 2021-06-03 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001846 | 272167824-34460-AUDIT-03_13_2025-GO95TCH-1^06239004.0244952 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001847 | 272430601-9410-DETAIL-04_16_2024-GO95HV-1^06145002.0186900 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001848 | 272726594-61669-DETAIL-07_12_2023-GO95MLD-1^06244008.0286100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001849 | 272974055-39610-DTLSB-05_07_2024-GO95MLD-1^06245001.0303400 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001850 | 273322676-35069-DTLTRT-10_23_2023-GO95MLD-1^668010/00 18/042 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001851 | 273322676-35069-DTLTRT-10_23_2023-GUYHINS-1^668010/00 18/042 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001852 | 27346814-80934-DETAIL-05_01_2024-GO95HV-1^06143015.0348001 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001853 | 273650441-37210-DETAIL-05_07_2024-GO95HV-1^06142012.0121211 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001854 | 274156982-53610-DETAIL-03_14_2024-GO95HV-1^06147004.0325600 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001855 | 274297105-76710-DTLSB-05_08_2024-GO95HV-1^06244001.0034401 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001856 | 274459923-91103-DETAIL-05_30_2024-GO95HV-1^06246005.0169000 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001857 | 274523380-67249-DETAIL-07_14_2022-SVCWIND-1^07116001.0040506 | OTHER | Non-HFTD | Distribution | 2022-07-14 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001858 | 274589131-19099-DETAIL-06_26_2023-GO95MLD-1^06244009.0310601 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001859 | 274870243-93879-DTLSB-01_30_2023-GO95MLD-1^06248001.0259003 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001860 | 274967218-17830-DETAIL-01_19_2023-SVCDEFLC-2^06240004.0081701 | OTHER | HFTD Tier 2 | Distribution | 2023-01-19 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001861 | 275009669-76470-DETAIL-04_11_2023-GO95MLD-1^06240004.0168414 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001862 | 275032983-8951-DETAIL-03_05_2025-GO95MLD-1^06241005.0132803 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001863 | 275073043-2110-DTLSB-05_28_2024-GO95HV-1^06243001.0127402 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001864 | 275413484-66439-DTLSB-02_26_2024-GO95MLD-1^07216001.0277800 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001865 | 275729128-26039-DETAIL-07_30_2024-GUYHINS-1^06244005.0354700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001866 | 275771819-88649-DTLSB-04_17_2024-GO95MLD-1^06245007.0223403 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001867 | 275890732-6009-DETAIL-04_09_2024-COPLLEAN-1^06147005.0218601 | POLE | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001868 | 275890732-6009-DETAIL-04_09_2024-COVCFRAY-1^06147005.0218601 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001869 | 274389373-83913-DTLSB-05_01_2024-SVCROAD-1^06245007.0228746 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001870 | 274472706-76790-DTLTRT-10_17_2023-GUYHINS-1^668010/00 12X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001871 | 274511410-70079-ADMIN-02_22_2023-POLEDERP-1^06148004.0354501 | POLE | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001872 | 274668501-23720-DETAIL-03_08_2023-GO95MLD-1^07117002.0211200 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001873 | 274746750-60749-DTLSB-02_19_2024-GO95TCH-1^07216001.0262103 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001874 | 274870243-93879-DTLSB-01_30_2023-GO95HV-1^06248001.0259003 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001875 | 274945976-94539-DETAIL-07_10_2024-GO95HV-1^06244004.0205340 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001876 | 275073043-2110-DTLSB-05_28_2024-GO95MLD-1^06243001.0127402 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001877 | 275387797-17349-AUDIT-04_20_2023-GO95HV-1^07114001.0347200 | OTHER | HFTD Tier 2 | Distribution | 2023-04-20 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001878 | 275649178-64459-DETAIL-06_03_2024-GO95MLD-1^06246005.0315900 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001879 | 275728353-63410-DETAIL-02_09_2023-GO95MLD-1^06146004.0088000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001880 | 275830760-76089-DTLSB-07_23_2024-GO95MLD-1^06245007.0107401 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001881 | 275890732-6009-DETAIL-04_09_2024-GO95MLD-1^06147005.0218601 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001882 | 275890732-6009-DETAIL-04_09_2024-GRDRODHI-1^06147005.0218601 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001883 | 275998976-97829-DETAIL-05_07_2024-GO95MLD-1^06142012.0122104 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001884 | 276143562-62559-DETAIL-02_29_2024-SVCENTCO-1^07113001.0140703 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001885 | 276535323-27323-DETAIL-04_29_2024-GO95MLD-1^06142016.0069103 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001886 | 276535323-27323-DETAIL-04_29_2024-GRDRODHI-1^06142016.0069103 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001887 | 276684455-19010-DETAIL-02_07_2023-GO95HV-1^06147002.0047900 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001888 | 277179173-60960-DETAIL-01_15_2025-SVCDEFLC-1^06240004.0098143 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001889 | 275890732-6009-DETAIL-04_09_2024-GO95HV-1^06147005.0218601 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001890 | 276044274-57510-DETAIL-05_16_2024-SVCDEFLC-1^06142012.0120900 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001891 | 276052544-97510-DETAIL-02_09_2023-GO95MLD-1^06146004.0166900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001892 | 276068771-27659-DETAIL-06_17_2024-GO95MLD-1^06246006.0239000 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001893 | 276423933-14113-DTLSB-04_24_2024-GO95MLD-1^06245007.0227544 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001894 | 276444661-12459-DETAIL-02_27_2023-GO95MLD-1^07216001.0297806 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001895 | 276533431-39739-DRONE_HY-10_25_2023-GO95HV-1^668087/00 3/008 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001896 | 276535323-27323-DETAIL-04_29_2024-ABNDEQPM-1^06142016.0069103 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001897 | 276564771-72199-DTLSB-02_20_2023-GO95HV-1^06248001.0288400 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001898 | 276580202-28010-DETAIL-07_13_2023-GO95HV-1^06244008.0272202 | OTHER | HFTD Tier 2 | Distribution | 2023-07-13 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001899 | 276882404-6359-DTLSB-02_06_2024-GO95MLD-1^07216001.0309802 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001900 | 277081250-57701-DETAIL-06_02_2022-GO95MLD-1^06241005.0031704 | OTHER | HFTD Tier 2 | Distribution | 2022-06-02 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001901 | 277125960-80789-DETAIL-08_12_2024-GO95MLD-1^06245006.0104901 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001902 | 277168568-24459-DETAIL-06_03_2024-GO95MLD-1^06246005.0315800 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001903 | 277186903-86299-DETAIL-07_31_2024-GO95HV-1^06244005.0340901 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001904 | 277186903-86299-DETAIL-07_31_2024-GO95MLD-1^06244005.0340901 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001905 | 277506-8506-DETAIL-01_29_2025-GO95MLD-1^06239004.0233002 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001906 | 277653192-82520-DETAIL-03_06_2025-GO95HV-1^06240004.0271141 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001907 | 277653192-82520-DETAIL-03_06_2025-GRDRODHI-1^06240004.0271141 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001908 | 278219754-23722-DETAIL-07_13_2023-GO95HV-1^06244008.0337700 | OTHER | HFTD Tier 2 | Distribution | 2023-07-13 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001909 | 278902702-29249-DETAIL-02_29_2024-GO95TCH-1^07113001.0142900 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001910 | 278956098-70159-DTLSB-02_14_2024-GO95MLD-1^07216001.0198312 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001911 | 279024491-79480-DETAIL-02_14_2025-GO95TCH-1^06240004.0168045 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001912 | 279184566-85080-DETAIL-03_03_2025-GO95HV-1^06240004.0050005 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001913 | 279211539-76049-DTLSB-02_15_2024-GO95MLD-1^07216001.0264202 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001914 | 27951343-55639-DETAIL-03_01_2023-GO95CL10-1^07216001.0290705 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001915 | 279641631-10119-DTLTRT-08_04_2022-GO95HV-1^668005/00 6/082 | OTHER | Non-HFTD | Transmission | 2022-08-04 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001916 | 279709423-46680-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0166203 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001917 | 279869075-20040-DETAIL-02_18_2025-BIRDDMG-1^06240004.0103000 | POLE | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001918 | 280057231-57750-DETAIL-02_11_2025-GO95MLD-1^06239004.0124905 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001919 | 277186903-86299-DETAIL-07_31_2024-SVCENTCO-1^06244005.0340901 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001920 | 277313613-49080-DETAIL-01_25_2023-GO95MLD-1^06240005.0016101 | OTHER | HFTD Tier 2 | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001921 | 277492210-11170-DETAIL-03_21_2023-GO95MLD-1^06240004.0167417 | OTHER | HFTD Tier 2 | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001922 | 277492210-11170-DETAIL-03_21_2023-GO95TCH-1^06240004.0167417 | OTHER | HFTD Tier 2 | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001923 | 27765924-36930-DETAIL-05_01_2023-SVCDEFLC-1^06241005.0366200 | OTHER | HFTD Tier 2 | Distribution | 2023-05-01 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001924 | 277786744-81149-DETAIL-03_16_2023-ABNDEQPM-1^07114001.0283305 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001925 | 277838964-88030-DETAIL-05_02_2023-GO95MLD-1^06241005.0365602 | OTHER | HFTD Tier 2 | Distribution | 2023-05-02 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001926 | 278427243-50343-DTLSB-07_17_2023-GO95MLD-1^06243010.0148600 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001927 | 278521662-85139-ADMIN-05_15_2024-ENCHRW-1^06142012.0126802 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001928 | 278521662-85139-DETAIL-05_15_2024-ENCHRW-1^06142012.0126802 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001929 | 280523978-2169-DTLTRT-06_30_2022-GO95MLD-1^668005/00 15/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001930 | 281019208-42239-DETAIL-03_20_2024-GO95MLD-1^06244005.0142302 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001931 | 281159569-85470-DETAIL-02_12_2025-BIRDDMG-1^06240004.0167403 | POLE | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001932 | 281183823-2970-DRONE_HY-10_10_2023-GO95HV-1^668033/00 9/018 | OTHER | HFTD Tier 2 | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001933 | 28123779-51530-DETAIL-09_18_2024-SVCDEFLC-1^06240004.0079301 | OTHER | HFTD Tier 3 | Distribution | 2024-09-18 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001934 | 281284591-85199-DETAIL-03_20_2024-RISEGRD-1^06244004.0068401 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001935 | 281590352-80520-DETAIL-03_06_2025-GO95HV-1^06240004.0271142 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001936 | 281677906-16571-DETAIL-02_19_2025-GO95HV-1^06239004.0365841 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001937 | 281795936-72249-DETAIL-03_11_2024-GO95MLD-1^06245006.0122300 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001938 | 281994298-74359-DTLSB-02_15_2024-GO95MLD-1^07216001.0190800 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001939 | 283002418-24259-DTLSB-02_14_2024-GO95MLD-1^07216001.0198307 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001940 | 278730819-88420-DETAIL-05_13_2024-SVCENTCO-1^06142012.0124306 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001941 | 278902702-29249-DETAIL-02_29_2024-SVCDEFLC-1^07113001.0142900 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001942 | 278932831-54080-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0167200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001943 | 279010981-90120-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0276300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001944 | 279024491-79480-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0168045 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001945 | 28300813-6670-DETAIL-04_03_2023-GO95HV-1^06143014.0173200 | OTHER | HFTD Tier 2 | Distribution | 2023-04-03 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001946 | 283021148-57520-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 1/024 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001947 | 283021148-81171-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 1/024 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001948 | 283091625-35433-DETAIL-03_02_2023-GUYHINS-1^07117002.0198203 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001949 | 283190070-63640-DETAIL-03_18_2025-GO95TCH-1^06238004.0012700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001950 | 283299811-53089-DETAIL-10_27_2022-GO95HV-1^06246008.0067702 | OTHER | HFTD Tier 2 | Distribution | 2022-10-27 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001951 | 283299811-53089-DETAIL-10_27_2022-GO95MLD-1^06246008.0067702 | OTHER | HFTD Tier 2 | Distribution | 2022-10-27 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001952 | 283743131-94289-DETAIL-06_25_2024-GO95MLD-1^06244005.0234400 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001953 | 284533601-49201-DETAIL-01_31_2025-GO95HV-1^06239004.0135005 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001954 | 28455423-51852-DETAIL-06_21_2023-ABNDEQPM-1^06244009.0309500 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001955 | 284597003-44049-DETAIL-03_02_2023-GO95MLD-1^07216001.0292506 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001956 | 284597003-44049-DETAIL-03_02_2023-GUYHINS-1^07216001.0292506 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001957 | 284669793-2149-DETAIL-10_08_2024-GO95MLD-1^07216001.0204105 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001958 | 284772464-89049-DETAIL-03_15_2023-GO95HV-1^07114001.0284202 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001959 | 284887372-78679-DTLSB-08_30_2023-SVCWIND-1^06243008.0205800 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001960 | 284928581-79470-DTLTRT-10_16_2023-GO95HV-1^668010/00 13/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001961 | 285270254-76860-DETAIL-01_21_2025-SVCENTCO-1^06239004.0256203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001962 | 285404995-64189-DTLSB-10_07_2024-GO95MLD-1^06245007.0230401 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001963 | 285683546-11489-DETAIL-07_11_2023-GO95MLD-1^06244008.0322901 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001964 | 285750523-5523-DETAIL-04_30_2024-GUYLOINS-1^06142016.0062000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001965 | 285815705-6049-DETAIL-03_15_2023-GO95MLD-1^07216001.0290602 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001966 | 285927345-76639-DETAIL-03_13_2023-GO95MLD-1^07216001.0290601 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001967 | 285997948-29948-DETAIL-05_10_2022-GO95MLD-1^07116001.0095702 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001968 | 286016858-76539-DTLSB-02_19_2024-GO95HV-1^07216001.0264801 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001969 | 286016858-76539-DTLSB-02_19_2024-GO95MLD-1^07216001.0264801 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001970 | 279147779-13470-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 4/066 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001971 | 279211539-76049-DTLSB-02_15_2024-GO95HV-1^07216001.0264202 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001972 | 279211539-76049-DTLSB-02_15_2024-SVCWIND-1^07216001.0264202 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001973 | 279268954-49534-DETAIL-05_01_2024-GO95HV-1^06143015.0342400 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001974 | 279280454-80920-DTLSB-05_08_2024-GO95MLD-1^06245001.0340001 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001975 | 27928670-10949-AUDIT-05_22_2024-SVCENTCO-1^06245007.0225000 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001976 | 286029511-81979-DETAIL-01_17_2023-SVCROAD-1^06148004.0225001 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001977 | 286237538-75149-DTLSB-02_19_2024-SVCROAD-1^07216001.0265702 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001978 | 286774821-22132-DETAIL-06_27_2023-GO95HV-1^06244009.0286100 | OTHER | Non-HFTD | Distribution | 2023-06-27 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001979 | 286839271-17679-DTLSB-08_27_2024-GO95MLD-1^06245007.0118701 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001980 | 286929331-87429-DETAIL-06_19_2023-GO95MLD-1^06244010.0263500 | OTHER | HFTD Tier 2 | Distribution | 2023-06-19 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001981 | 279401196-17310-DETAIL-02_17_2025-GRDRODHI-1^06240004.0163605 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001982 | 279441518-95920-DETAIL-03_19_2024-GO95MLD-1^06245002.0014601 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001983 | 27951343-55639-DETAIL-03_01_2023-GO95MLD-1^07216001.0290705 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001984 | 279535340-61859-DETAIL-03_21_2024-BIRDDMG-1^06246005.0063501 | POLE | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001985 | 280692908-67540-DETAIL-03_17_2025-GO95HV-1^06238004.0142200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001986 | 280962581-5188-DETAIL-03_27_2024-GO95MLD-1^06247005.0337601 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001987 | 280962581-5188-DETAIL-03_27_2024-GRDRODHI-1^06247005.0337601 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001988 | 281130504-59269-DTLTRT-10_04_2023-GO95HV-1^668010/00 8/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001989 | 281159569-85470-DETAIL-02_12_2025-GUYHINS-1^06240004.0167403 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001990 | 281159569-85470-DETAIL-02_12_2025-GUYHINS-2^06240004.0167403 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001991 | 287034526-3899-DETAIL-03_25_2024-GO95MLD-1^06244005.0146101 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001992 | 287034526-3899-DETAIL-03_25_2024-SVCDEFLC-1^06244005.0146101 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001993 | 287185054-79989-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192701 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001994 | 287263093-68079-DTLSB-08_31_2023-GO95MLD-1^06243007.0320401 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001995 | 288185479-54859-DETAIL-10_24_2024-SVCROAD-1^07216001.0200403 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001996 | 288510381-11381-DETAIL-03_27_2023-GO95HV-1^06142016.0052500 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001997 | 288594316-7489-DTLSB-01_31_2023-GO95MLD-1^06248001.0367800 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130001998 | 288858885-70359-DETAIL-04_01_2024-GO95HV-1^06247005.0347102 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130001999 | 288932223-74223-DETAIL-02_18_2025-GO95TCH-1^06240004.0220610 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002000 | 289723613-99830-DETAIL-10_16_2024-GO95MLD-1^07216001.0208800 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002001 | 289982187-53970-DETAIL-02_26_2025-GO95TCH-1^06240004.0061203 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002002 | 2900382-26459-DETAIL-02_29_2024-SVCDEFLC-1^07113001.0140902 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002003 | 290080258-58-DETAIL-10_14_2024-SVCENTCO-1^07216001.0202240 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002004 | 290263306-88899-DETAIL-04_03_2024-GO95MLD-1^06247005.0346801 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002005 | 290267951-88049-DETAIL-02_26_2024-GO95MLD-1^07113001.0138307 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002006 | 29073475-41289-DETAIL-06_11_2024-GO95HV-1^06245007.0345800 | OTHER | Non-HFTD | Distribution | 2024-06-11 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002007 | 291173-63040-DTLTRT-10_03_2023-GO95HV-1^668010/00 7/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002008 | 291173-63040-DTLTRT-10_03_2023-GO95MLD-1^668010/00 7/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002009 | 291246674-86040-DETAIL-02_26_2025-GO95TCH-1^06240004.0218901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002010 | 291527006-71849-DETAIL-10_24_2024-GUYHINS-2^07216001.0203901 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002011 | 291730032-83021-DTLSB-09_05_2023-GO95HV-1^06243008.0162901 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002012 | 291757228-1869-DETAIL-03_26_2024-GO95HV-1^06244005.0147000 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002013 | 291811964-77030-DETAIL-01_28_2025-GO95BLTC-1^06240004.0070900 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002014 | 291814458-83459-DETAIL-06_03_2024-GO95MLD-1^06246005.0315701 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002015 | 292179521-54230-DETAIL-04_18_2024-GO95MLD-1^06145001.0149401 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002016 | 292361406-51098-DETAIL-07_10_2024-GO95HV-1^06244005.0273900 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002017 | 292566233-53339-DETAIL-03_14_2023-GO95HV-1^07114001.0275300 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002018 | 292649034-14279-DETAIL-07_24_2024-SVCDEFLC-1^06244005.0228604 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002019 | 292656673-9749-DTLSB-02_27_2024-GO95MLD-1^07216001.0278802 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002020 | 292690405-67430-DETAIL-04_24_2024-SVCDEFLC-1^06145001.0031201 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002021 | 292945813-80979-AUDIT-10_09_2023-GO95BLTC-1^06243007.0171101 | OTHER | HFTD Tier 2 | Distribution | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002022 | 281550453-97889-DETAIL-06_10_2024-GO95HV-1^06245007.0347006 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002023 | 28177719-74169-DTLTRT-06_10_2021-GO95HV-1^668041/00 1/018 | OTHER | Non-HFTD | Transmission | 2021-06-10 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002024 | 281961310-15269-DETAIL-04_08_2024-GO95HV-1^06247005.0323601 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002025 | 281969204-92749-DTLSB-02_27_2024-SVCENTCO-1^07216001.0278706 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002026 | 282054478-26849-DTLSB-02_21_2024-GUYLOINS-1^07216001.0262400 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002027 | 282266573-58352-DETAIL-06_21_2023-GO95HV-1^06244009.0309601 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002028 | 282266573-58352-DETAIL-06_21_2023-RISEGRD-1^06244009.0309601 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002029 | 282485493-11030-DETAIL-02_25_2025-SVCROAD-1^06241005.0254204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002030 | 282546916-25539-DTLSB-02_21_2023-GO95TCH-1^07216001.0287703 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002031 | 28272258-64670-DTLSB-02_02_2023-GO95MLD-1^06247001.0013000 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002032 | 292945813-80979-DTLSB-09_06_2023-ABNDEQPM-1^06243007.0171101 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002033 | 29301959-85289-ADMIN-07_11_2024-POLEREPL-1^06243009.0130900 | POLE | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002034 | 293124226-30379-DTLSB-02_01_2023-GRDBROKE-1^06248001.0369600 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002035 | 293247566-34930-DETAIL-10_10_2024-ENCHRW-1^07216001.0206004 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002036 | 293267903-28419-ADMIN-10_25_2024-POLEREPL-1^668005/00 8/092 | POLE | Non-HFTD | Transmission | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002037 | 28290161-76159-DTLSB-02_16_2024-GO95MLD-1^07216001.0262108 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002038 | 283002418-24259-DTLSB-02_14_2024-SVCENTBK-1^07216001.0198307 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002039 | 283021148-42171-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 1/024 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002040 | 283096306-95749-DTLSB-05_06_2024-GO95HV-1^06245007.0229406 | OTHER | HFTD Tier 2 | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002041 | 283729129-19299-DETAIL-08_13_2024-GO95MLD-1^06245005.0354900 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002042 | 293579924-58030-DTLSB-05_08_2024-GO95MLD-1^06245001.0333700 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002043 | 293738011-62829-DTLSB-09_05_2023-GO95MLD-1^06243008.0093300 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002044 | 294008549-69149-DETAIL-02_19_2024-GO95MLD-1^07113002.0185105 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002045 | 294064463-79230-DETAIL-02_09_2023-GO95MLD-1^06146004.0177200 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002046 | 294181563-79559-DTLSB-02_21_2024-GO95MLD-1^07216001.0189000 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002047 | 294288658-94859-DETAIL-03_18_2024-GO95MLD-1^06246005.0074300 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002048 | 294341288-17479-DETAIL-06_03_2024-GO95HV-1^06246005.0314501 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002049 | 294736160-49269-ADMIN-08_05_2020-POLEDERP-1^668005/00 8/051 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002050 | 295008263-2589-DETAIL-06_10_2024-GO95MLD-1^06245007.0348000 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002051 | 295319032-12780-DETAIL-03_10_2025-GO95HV-1^06240004.0288801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002052 | 296112238-74849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155104 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002053 | 296134458-34279-DRONE_HY-09_28_2023-GO95HV-1^668033/00 11/004 | OTHER | HFTD Tier 2 | Transmission | 2023-09-28 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002054 | 296176934-65049-DETAIL-03_15_2023-CLRTOUCH-1^07114001.0336900 | CONDUCTOR | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002055 | 296192290-57199-DTLSB-08_14_2023-GO95MLD-1^06243009.0244405 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002056 | 296314126-61930-DTLSB-01_31_2023-GO95HV-1^06248001.0367905 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002057 | 296338233-84339-DETAIL-03_15_2023-CLRTOPOL-1^07216001.0290600 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002058 | 296338233-84339-DETAIL-03_15_2023-SVCENTCO-1^07216001.0290600 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002059 | 29677616-11223-DTLSB-05_01_2024-SVCWIND-1^06245007.0227341 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002060 | 297096151-68763-DTLSB-04_09_2024-GO95MLD-1^06245007.0221342 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002061 | 297788991-50369-DTLSB-09_05_2023-GO95HV-1^06243008.0095601 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002062 | 297880096-95890-DTLTRT-10_18_2023-GO95HV-1^668010/00 10/010 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002063 | 297935598-64549-DETAIL-10_14_2024-GO95MLD-1^07216001.0202200 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002064 | 297936813-5140-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 10/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002065 | 298136609-79840-DETAIL-05_06_2024-GO95HV-1^06142012.0124008 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002066 | 298136609-79840-DETAIL-05_06_2024-GO95MLD-1^06142012.0124008 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002067 | 29855853-44500-DETAIL-05_22_2024-GO95HV-1^06243001.0103600 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002068 | 298799715-88909-DETAIL-01_16_2023-COPLLEAN-1^06148004.0179300 | POLE | Non-HFTD | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002069 | 298799715-88909-DETAIL-01_16_2023-GO95MLD-1^06148004.0179300 | OTHER | Non-HFTD | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002070 | 299190713-70649-DETAIL-05_11_2023-SVCENTCO-1^06245005.0235000 | OTHER | Non-HFTD | Distribution | 2023-05-11 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002071 | 299547710-20232-DETAIL-06_21_2023-GO95HV-1^06244009.0336901 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002072 | 299565562-58349-DETAIL-10_15_2024-GO95HV-1^07216001.0205100 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002073 | 299736571-91339-DETAIL-05_09_2022-GO95MLD-1^07116001.0098201 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002074 | 300518706-26140-DTLSB-02_01_2023-GO95MLD-1^06248001.0369807 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002075 | 300680503-11240-DTLSB-02_13_2023-GO95MLD-1^06248001.0272901 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002076 | 300798910-8339-DTLSB-02_19_2024-SVCENTCO-1^07216001.0263204 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002077 | 301292951-77389-DTLSB-08_28_2024-GO95MLD-1^06245007.0158001 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002078 | 284275011-89049-DETAIL-02_26_2024-SVCENTCO-1^07113001.0138300 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002079 | 2842796-10170-DETAIL-01_24_2025-GO95HV-1^06239004.0257941 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002080 | 284363316-98579-DETAIL-04_01_2024-CUTOUTAR-1^06147005.0128700 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002081 | 284363316-98579-DETAIL-04_01_2024-GO95MLD-1^06147005.0128700 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002082 | 284418818-89569-DETAIL-04_06_2023-GO95MLD-1^06245006.0244400 | OTHER | Non-HFTD | Distribution | 2023-04-06 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002083 | 301721291-92009-DETAIL-03_12_2024-CONDFRAY-1^06147004.0058800 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002084 | 302311046-20540-DETAIL-10_22_2024-SVCNEUT-1^07216001.0207403 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002085 | 302395464-18440-DETAIL-10_25_2024-GO95MLD-1^07216001.0209904 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002086 | 302470231-31540-DETAIL-04_15_2024-GO95MLD-1^06145002.0050600 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002087 | 302851060-79459-DETAIL-08_19_2024-BIRDDMG-1^06246004.0331900 | POLE | Non-HFTD | Distribution | 2024-08-19 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002088 | 303040208-3859-DETAIL-03_18_2024-GO95MLD-1^06246005.0079200 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002089 | 303308378-86940-DETAIL-04_16_2024-GO95MLD-1^06145001.0129503 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002090 | 303478696-40796-DTLSB-08_29_2023-GO95HV-1^06243009.0110341 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002091 | 303650029-10449-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299400 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002092 | 304102723-26352-DETAIL-06_13_2023-GO95HV-1^06244010.0228300 | OTHER | HFTD Tier 2 | Distribution | 2023-06-13 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002093 | 284504728-47675-DETAIL-10_09_2024-SVCENTBK-1^07216001.0200140 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002094 | 28455423-51852-DETAIL-06_21_2023-GO95MLD-1^06244009.0309500 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002095 | 285270254-76860-DETAIL-01_21_2025-SVCDEFLC-1^06239004.0256203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002096 | 285404995-64189-DTLSB-10_07_2024-GRDRODHI-1^06245007.0230401 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002097 | 285658633-67833-DETAIL-10_12_2022-GO95HV-1^668005/08 8X3/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002098 | 304230123-94049-DETAIL-10_10_2024-SVCNEUT-1^07216001.0207001 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002099 | 304304846-26450-DETAIL-10_22_2024-GO95HV-1^07216001.0207402 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002100 | 304361503-66450-DTLSB-05_22_2024-GO95MLD-1^06243001.0114101 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002101 | 304363336-76450-DETAIL-04_24_2024-SVCDEFLC-1^06145001.0030100 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002102 | 304643713-76650-DTLSB-02_08_2023-GO95MLD-1^06248001.0155203 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002103 | 304675743-68799-DTLSB-07_26_2023-GO95HV-1^06243009.0054600 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002104 | 304857745-50339-DRONE_HY-10_25_2023-GO95HV-1^668087/00 1/010 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002105 | 304895899-42649-DETAIL-08_20_2024-GO95HV-1^06245005.0251300 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002106 | 305060766-71723-DTLSB-04_30_2024-GO95MLD-1^06245007.0220744 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002107 | 305093502-34569-DTLTRT-06_04_2021-GO95HV-1^668041/00 6/008 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002108 | 305128244-68150-DTLSB-05_08_2024-GO95HV-1^06245001.0339100 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002109 | 305128244-68150-DTLSB-05_08_2024-GO95MLD-1^06245001.0339100 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002110 | 305458264-75429-DTLSB-07_26_2023-GO95HV-1^06243009.0054701 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002111 | 305949071-11009-DTLSB-08_28_2024-GRDRODHI-2^06245007.0159100 | OTHER | Non-HFTD | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002112 | 306134834-33149-DETAIL-03_20_2023-GO95MLD-1^07114001.0284401 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002113 | 306231916-3916-DTLSB-08_31_2023-GO95HV-1^06243008.0026600 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002114 | 306789841-51941-DETAIL-03_27_2023-GO95MLD-1^06142016.0053700 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002115 | 30708261-300-ADMIN-07_17_2023-CONDFRAY-1^06247001.0349500 | CONDUCTOR | Non-HFTD | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002116 | 307085998-64789-DETAIL-03_22_2024-GO95MLD-1^06247005.0286500 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002117 | 307226831-28339-DETAIL-02_29_2024-GO95MLD-1^07113001.0105600 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002118 | 307332918-53869-DTLTRT-06_09_2021-GO95HV-1^668041/00 9/015 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002119 | 307462266-96609-DETAIL-08_08_2024-GO95MLD-1^06245006.0093801 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002120 | 307669586-84189-DETAIL-06_06_2023-GO95HV-1^06244010.0347200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002121 | 307829090-69090-DTLTRT-11_16_2022-GO95MLD-1^668075/00 7/027 | OTHER | Non-HFTD | Transmission | 2022-11-16 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002122 | 308203423-59339-DETAIL-06_20_2024-SVCDEFLC-1^06244005.0238600 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002123 | 285815705-6049-DETAIL-03_15_2023-SVCENTBK-1^07216001.0290602 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002124 | 285964518-48859-DETAIL-04_04_2024-GO95MLD-1^06246005.0073402 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002125 | 286081058-36099-DETAIL-04_01_2024-ABNDEQPM-1^06147005.0102701 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002126 | 286115498-33820-DETAIL-04_16_2024-GO95HV-1^06145001.0019300 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002127 | 286115498-33820-DETAIL-04_16_2024-GO95MLD-1^06145001.0019300 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002128 | 308478551-43863-DETAIL-01_24_2023-GO95MLD-1^06240005.0129903 | OTHER | HFTD Tier 2 | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002129 | 308531929-54273-DETAIL-04_01_2024-GO95MLD-1^06246005.0039801 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002130 | 308889539-99339-DETAIL-02_22_2024-GO95HV-1^07216001.0354302 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002131 | 308889539-99339-DETAIL-02_22_2024-GO95MLD-1^07216001.0354302 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002132 | 308898841-31463-DTLSB-04_17_2024-GO95HV-1^06245007.0223444 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002133 | 286237538-75149-DTLSB-02_19_2024-GO95MLD-1^07216001.0265702 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002134 | 286595125-69669-DETAIL-07_24_2024-GO95MLD-1^06244005.0228601 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002135 | 286775236-60670-DETAIL-01_14_2025-GO95MLD-1^06239004.0255000 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002136 | 287040149-96130-DTLTRT-10_18_2023-GO95HV-1^668010/00 26/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002137 | 287041391-1859-DETAIL-06_06_2024-GO95MLD-1^06246006.0265201 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002138 | 308981826-73589-ADMIN-04_02_2025-POLETOP-1^06245007.0142400 | POLE | HFTD Tier 2 | Distribution | 2025-04-02 | 2026-04-30 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130002139 | 30902771-18952-DETAIL-06_26_2023-GO95HV-1^06244009.0310900 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002140 | 309191928-56800-DTLTRT-11_02_2023-GUYHINS-2^668010/00 5/020 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-02 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002141 | 309191928-56800-DTLTRT-11_02_2023-GUYHINS-3^668010/00 5/020 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-02 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002142 | 309761399-43399-DETAIL-07_12_2023-ENCHRW-1^06244008.0274400 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002143 | 309795577-18999-DTLSB-10_03_2024-GUYHINS-1^06245006.0331600 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002144 | 30984072-15950-DETAIL-03_19_2025-GO95HV-1^06238004.0027242 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002145 | 310136171-4520-DETAIL-02_17_2025-SVCROAD-1^06240004.0275401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002146 | 310145405-74879-DETAIL-01_16_2023-GO95MLD-1^06148004.0165305 | OTHER | Non-HFTD | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002147 | 310282351-14450-DETAIL-01_18_2023-GO95MLD-1^06148004.0221001 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002148 | 310282351-14450-DETAIL-01_18_2023-GO95MLD-2^06148004.0221001 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002149 | 310282351-14450-DETAIL-01_18_2023-GO95TCH-1^06148004.0221001 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002150 | 310331295-92170-DETAIL-01_21_2025-GO95HV-1^06239004.0256305 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002151 | 310766631-80980-DETAIL-02_20_2025-GO95HV-1^06240004.0296002 | OTHER | HFTD Tier 3 | Distribution | 2025-02-20 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002152 | 310944999-81113-DETAIL-07_23_2024-GO95MLD-1^06245006.0146441 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002153 | 311169830-21930-DETAIL-03_14_2024-GO95MLD-1^06245006.0017000 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002154 | 311200307-40307-AUDIT-06_05_2024-GO95TCH-1^06244002.0143600 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002155 | 311200307-40307-DTLSB-05_21_2024-GO95HV-1^06244002.0143600 | OTHER | Non-HFTD | Distribution | 2024-05-21 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002156 | 311837521-92119-ADMIN-10_04_2024-GO95STUB-1^06240008.0071500 | OTHER | Non-HFTD | Distribution | 2024-10-04 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002157 | 311847980-26789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153100 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002158 | 312146684-69259-DTLSB-02_14_2024-SVCDEFLC-1^07216001.0198313 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002159 | 312238332-99902-DTLTRT-04_11_2024-BIRDDMG-1^668067/00 4/007 | POLE | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002160 | 312253409-79029-DETAIL-06_05_2023-GO95STUB-1^06243009.0024404 | OTHER | Non-HFTD | Distribution | 2023-06-05 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002161 | 312364171-8771-DETAIL-02_06_2023-GO95BLTC-1^06147002.0162100 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002162 | 312578218-78509-DETAIL-03_28_2024-GO95HV-1^06147005.0150900 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002163 | 312820844-90059-DTLSB-02_08_2024-SVCROAD-1^07216001.0309904 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002164 | 313130691-7469-DTLTRT-06_03_2021-GO95HV-1^668041/00 9/007 | OTHER | Non-HFTD | Transmission | 2021-06-03 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002165 | 313224153-18160-DETAIL-04_06_2023-GO95HV-1^06143014.0232500 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002166 | 313270816-14572-DETAIL-06_06_2024-GO95MLD-1^06245006.0032140 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002167 | 313375015-17015-DETAIL-08_13_2024-GO95HV-1^06245005.0361304 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002168 | 287190261-98779-DETAIL-02_01_2023-GO95MLD-1^06146002.0081100 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002169 | 287287246-82549-DETAIL-10_17_2024-GO95MLD-1^07216001.0204406 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002170 | 287351411-2129-DETAIL-05_07_2024-GO95MLD-1^06142012.0124205 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002171 | 287509681-720-DETAIL-04_11_2024-GO95MLD-1^06245002.0144101 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002172 | 288600585-17190-DTLTRT-10_31_2023-GO95HV-1^668010/00 2/017 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002173 | 313427946-17869-DETAIL-02_11_2025-GO95TCH-1^06240004.0356102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002174 | 313891386-56949-DTLSB-04_09_2024-SVCRUBLG-1^06245007.0228003 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002175 | 313993237-5189-DTLSB-10_03_2024-ABNDEQPM-1^06245006.0336401 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002176 | 314527761-6860-DETAIL-03_12_2024-GO95HV-1^06147004.0059701 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002177 | 314956630-88349-AUDIT-03_12_2024-GO95MLD-1^07113001.0136800 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002178 | 289859095-3030-DTLSB-05_13_2024-GO95MLD-1^06244001.0108101 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002179 | 290129188-27130-DETAIL-04_17_2024-GO95MLD-1^06145001.0019501 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002180 | 290160663-9459-DETAIL-04_04_2024-GO95MLD-1^06247005.0292001 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002181 | 290729961-43439-DETAIL-07_18_2024-GO95HV-1^06244004.0058700 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002182 | 290775021-5379-DETAIL-03_06_2024-GO95MLD-1^06147004.0027500 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002183 | 315211701-93342-DTLTRT-03_26_2024-POLEDERP-1^668044/00 5/060 | POLE | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002184 | 315357875-82560-DTLSB-02_01_2023-GO95MLD-1^06248001.0368101 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002185 | 315515856-94039-DETAIL-07_25_2024-GO95HV-1^06244005.0354903 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002186 | 315614896-53002-DTLTRT-04_18_2024-GO95HV-1^668067/00 3/021 | OTHER | Non-HFTD | Transmission | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002187 | 315614896-53002-DTLTRT-04_18_2024-GUYNOINS-1^668067/00 3/021 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-18 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002188 | 290941014-30934-DETAIL-05_01_2024-GO95HV-1^06143015.0347100 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002189 | 291152221-22079-DETAIL-06_05_2024-GO95MLD-1^06246006.0266400 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002190 | 291246674-86040-DETAIL-02_26_2025-GUYHINS-1^06240004.0218901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002191 | 291287763-77409-DTLSB-09_05_2024-GO95MLD-1^06246006.0314141 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002192 | 291390119-30609-DETAIL-04_02_2024-GO95HV-1^06147005.0102001 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002193 | 291527006-71849-DETAIL-10_24_2024-GO95CL10-1^07216001.0203901 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002194 | 315614896-54002-DTLTRT-04_18_2024-GO95HV-1^668067/00 3/021 | OTHER | Non-HFTD | Transmission | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002195 | 315614896-54002-DTLTRT-04_18_2024-GUYNOINS-1^668067/00 3/021 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-18 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002196 | 315614896-75700-DTLTRT-04_18_2024-GUYNOINS-1^668067/00 3/021 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-18 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002197 | 316094551-78909-DTLSB-05_02_2024-GUYNOINS-2^06245007.0226802 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002198 | 316227074-99899-DETAIL-03_21_2024-GO95BLTC-1^06147005.0209503 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002199 | 316227074-99899-DETAIL-03_21_2024-GUYHINS-1^06147005.0209503 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002200 | 316351124-58599-DETAIL-03_21_2024-GO95MLD-1^06147005.0186600 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002201 | 316765703-19313-DTLSB-04_25_2024-GUYNOINS-2^06245007.0227548 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002202 | 316804743-54279-AUDIT-03_18_2025-GO95MLD-1^06240004.0065901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002203 | 316921236-78240-DETAIL-02_25_2025-CLRTOUCH-1^06240004.0151802 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-25 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002204 | 317226001-77119-ADMIN-08_05_2020-POLEDERP-1^668005/00 6/084 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002205 | 317356906-58229-DTLSB-08_29_2023-GO95MLD-1^06243009.0119401 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002206 | 31791870-23909-DTLSB-09_30_2024-GO95HV-1^06245007.0230241 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002207 | 31795514-29500-DTLSB-05_06_2024-GO95MLD-1^06243003.0096400 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002208 | 317961201-76161-DTLTRT-06_15_2021-GO95HV-1^668041/00 9/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002209 | 318008961-4980-DETAIL-02_14_2025-GO95HV-1^06240004.0168307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002210 | 318312388-59770-DETAIL-04_12_2023-SVCENTCO-1^06240004.0166901 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002211 | 318334701-85801-DETAIL-03_29_2023-GO95MLD-1^06142016.0053000 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002212 | 318511531-73751-DETAIL-06_24_2024-GO95HV-1^06244005.0230103 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002213 | 318515779-24560-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 3/061 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002214 | 318847281-94559-DTLSB-02_20_2024-GO95MLD-1^07216001.0260401 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002215 | 318863679-68873-DETAIL-03_07_2023-GO95MLD-1^07117002.0208700 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002216 | 319391489-67660-DRONE_HY-10_25_2023-GO95HV-1^668087/00 5/006 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002217 | 319420179-53790-DETAIL-01_16_2025-GO95HV-1^06239004.0256216 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002218 | 319420179-53790-DETAIL-01_16_2025-SVCENTCO-1^06239004.0256216 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002219 | 291527006-71849-DETAIL-10_24_2024-GUYHINS-1^07216001.0203901 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002220 | 291811964-77030-DETAIL-01_28_2025-GO95HV-1^06240004.0070900 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002221 | 292255415-19772-DETAIL-03_14_2024-GO95MLD-1^06245006.0018100 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002222 | 292322721-25329-DETAIL-06_27_2023-GO95MLD-1^06244009.0287200 | OTHER | Non-HFTD | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002223 | 292459690-69670-DETAIL-02_05_2025-GO95HV-1^06240004.0167100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002224 | 320129424-40524-DTLSB-08_10_2023-GO95HV-1^06243009.0226700 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002225 | 320304394-79160-DTLSB-02_09_2023-GO95MLD-1^06248001.0260900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002226 | 320602345-61549-DTLSB-04_30_2024-GO95HV-1^06245007.0222700 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002227 | 320642394-17150-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 4A/036 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002228 | 320785503-68649-DETAIL-03_16_2023-GO95HV-1^07113001.0040403 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002229 | 292465543-1079-DTLSB-09_05_2023-GO95MLD-1^06243008.0235100 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002230 | 29261841-49280-DETAIL-04_17_2023-GUYHINS-1^06240004.0166641 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-04-17 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002231 | 292690405-67430-DETAIL-04_24_2024-GO95HV-1^06145001.0031201 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002232 | 292690405-67430-DETAIL-04_24_2024-SVCDEFLC-2^06145001.0031201 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002233 | 292789790-17339-DETAIL-02_20_2024-SVCENTCO-1^07113002.0182003 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002234 | 320830463-2199-DTLSB-08_16_2023-RISEGRD-1^06243009.0284200 | OTHER | Non-HFTD | Distribution | 2023-08-16 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002235 | 320895123-4780-DETAIL-03_17_2025-GO95HV-1^06239002.0059400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002236 | 321098473-64259-DTLSB-02_13_2024-GO95MLD-1^07216001.0186201 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002237 | 321130656-4300-DTLTRT-10_24_2023-GUYHINS-3^668010/00 20X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-24 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002238 | 321263826-71249-DETAIL-03_11_2024-GO95MLD-1^06245006.0121200 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002239 | 292861349-73349-DTLSB-02_06_2024-GO95MLD-1^07216001.0309917 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002240 | 292863740-39080-DETAIL-02_10_2025-CONDCOIL-1^06239003.0072900 | OTHER | HFTD Tier 3 | Distribution | 2025-02-10 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002241 | 29301959-85289-DTLSB-08_29_2023-GO95STUB-1^06243009.0130900 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002242 | 293124226-30379-DTLSB-02_01_2023-GO95MLD-1^06248001.0369600 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002243 | 29314580-75249-DETAIL-07_14_2022-GO95MLD-1^07116001.0040505 | OTHER | Non-HFTD | Distribution | 2022-07-14 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002244 | 321533495-93189-DETAIL-01_23_2023-GO95TCH-1^06148004.0192100 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002245 | 321626152-47460-DTLSB-02_13_2023-GO95MLD-1^06248001.0279301 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002246 | 321721166-90029-DETAIL-07_01_2020-GO95MLD-1^06142012.0014101 | OTHER | Non-HFTD | Distribution | 2020-07-01 | 2023-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002247 | 321965736-78301-DETAIL-03_03_2025-GO95MLD-1^06241005.0255500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002248 | 322109934-13660-DTLTRT-04_08_2024-GO95HV-1^668062/00 6/006 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002249 | 322109934-26753-DTLTRT-04_08_2024-GO95HV-1^668062/00 6/006 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002250 | 322109934-26753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 6/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002251 | 322350681-31173-DETAIL-03_02_2023-GO95CL10-1^07117002.0203300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002252 | 322744132-43450-DETAIL-02_04_2025-PWRTRN-1^06239004.0135203 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002253 | 322916980-909-DTLSB-09_03_2024-GO95MLD-1^06245007.0014001 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002254 | 323020201-9423-DETAIL-06_19_2024-GO95MLD-1^06246006.0138900 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002255 | 323214944-35570-DTLSB-05_08_2024-GO95MLD-1^06245001.0338100 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002256 | 323416279-61759-DTLSB-02_05_2024-GO95HV-1^07216001.0192941 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002257 | 323502703-96329-DETAIL-06_27_2023-GO95MLD-1^06243009.0041800 | OTHER | Non-HFTD | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002258 | 323502703-96329-DETAIL-06_27_2023-GRDRODHI-1^06243009.0041800 | OTHER | Non-HFTD | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002259 | 323678083-22049-ADMIN-08_07_2024-COPLLEAN-1^07114001.0276502 | POLE | Non-HFTD | Distribution | 2024-08-07 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002260 | 323678083-22049-DETAIL-03_14_2023-GO95HV-1^07114001.0276502 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002261 | 323781251-6970-ADMIN-10_23_2023-POLEDERP-1^07216001.0101502 | POLE | Non-HFTD | Distribution | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002262 | 324103645-91549-DTLSB-05_01_2024-GO95MLD-1^06245007.0220601 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002263 | 324103645-91549-DTLSB-05_01_2024-SVCENTCO-1^06245007.0220601 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002264 | 324488230-51559-DTLSB-02_20_2024-GO95MLD-1^07216001.0263300 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002265 | 324818103-87941-DETAIL-03_05_2025-GO95MLD-1^06241005.0132801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002266 | 324876293-86079-DETAIL-06_18_2024-BIRDDMG-1^06245007.0290503 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002267 | 324983414-17849-DETAIL-03_15_2023-GO95TCH-1^07114001.0338500 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002268 | 325416168-13949-DETAIL-08_14_2024-GO95HV-1^06245005.0342000 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002269 | 325525401-68099-DTLSB-08_27_2024-GUYHINS-1^06245007.0119703 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002270 | 325836021-92720-DETAIL-02_17_2025-GO95HV-1^06240004.0278601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002271 | 325978155-30070-DETAIL-04_23_2024-GO95MLD-1^06145001.0035302 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002272 | 327006911-14580-DETAIL-03_20_2025-GO95HV-1^06239002.0035400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002273 | 32714771-31189-DTLSB-08_28_2024-GO95MLD-1^06245007.0158300 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002274 | 327581721-18681-ADMIN-03_03_2021-UBBRACE-1^668041/00 4/022 | CROSSARM | Non-HFTD | Transmission | 2021-03-03 | 2024-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002275 | 327917640-12959-DETAIL-03_13_2024-SVCDEFLC-1^06245007.0285100 | OTHER | HFTD Tier 2 | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002276 | 327941333-74679-DTLSB-11_11_2021-CUTOUTAR-1^06148004.0303402 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2021-11-11 | 2024-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002277 | 328708159-39570-DETAIL-04_11_2024-GO95MLD-1^06245002.0102101 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002278 | 328708159-39570-DETAIL-04_11_2024-POLISSUE-1^06245002.0102101 | POLE | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002279 | 329026394-45599-DTLSB-04_23_2024-GO95MLD-1^06245007.0223804 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002280 | 293166084-11181-DTLSB-07_31_2023-GO95MLD-1^06243009.0087602 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002281 | 293247566-34930-DETAIL-10_10_2024-GUYLOINS-1^07216001.0206004 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002282 | 293309732-20832-DETAIL-11_09_2022-ABNDEQPM-1^06239004.0362407 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002283 | 293581428-36993-DETAIL-01_14_2025-GRDRODHI-1^06240004.0081940 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002284 | 293738011-62829-DTLSB-09_05_2023-ABNDEQPM-1^06243008.0093300 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002285 | 329033596-41180-DETAIL-02_19_2025-GO95MLD-1^06239004.0363303 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002286 | 329335790-96789-DETAIL-01_09_2023-GO95HV-1^06148003.0153000 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002287 | 329502013-73689-DETAIL-06_06_2024-GO95MLD-1^06246006.0351301 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002288 | 329563494-92589-DTLSB-07_25_2023-GO95MLD-1^06243009.0056400 | OTHER | Non-HFTD | Distribution | 2023-07-25 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002289 | 330672073-45653-DETAIL-06_07_2023-GO95HV-1^06244010.0275602 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002290 | 293998955-29955-DETAIL-03_24_2025-SVCENTCO-1^06238004.0029610 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002291 | 294008549-69149-DETAIL-02_19_2024-GO95HV-1^07113002.0185105 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002292 | 294064463-79230-ADMIN-03_06_2023-GO95TCH-1^06146004.0177200 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002293 | 294727479-79522-DETAIL-06_28_2023-GO95HV-1^06244009.0362000 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002294 | 295572123-83809-DETAIL-08_25_2021-SVCWIND-1^06148004.0353206 | OTHER | Non-HFTD | Distribution | 2021-08-25 | 2024-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002295 | 330742347-72999-DTLSB-08_22_2024-GO95MLD-1^06245006.0324100 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002296 | 330998460-18801-DETAIL-06_02_2022-GO95MLD-1^06241005.0031703 | OTHER | HFTD Tier 2 | Distribution | 2022-06-02 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002297 | 331179158-2179-DETAIL-08_01_2024-GO95MLD-1^06245006.0151400 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002298 | 332138344-16899-DETAIL-08_14_2024-GO95MLD-1^06246005.0256800 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002299 | 332667408-41263-DETAIL-08_29_2024-SVCDEFLC-1^06240004.0093404 | OTHER | HFTD Tier 2 | Distribution | 2024-08-29 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002300 | 332838129-34473-DETAIL-01_18_2023-GO95TCH-1^06240004.0092300 | OTHER | HFTD Tier 2 | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002301 | 333239961-71061-DETAIL-03_27_2023-GO95HV-1^06142016.0052202 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002302 | 3334900-50949-DTLSB-02_16_2024-GO95HV-1^07216001.0261009 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002303 | 3334900-50949-DTLSB-02_16_2024-GO95MLD-1^07216001.0261009 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002304 | 334477323-90030-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 5/031 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002305 | 3345101-11469-DETAIL-02_23_2023-GO95HV-1^668002/00 9/030 | OTHER | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002306 | 334590248-28459-DETAIL-05_10_2022-GO95TCH-1^07116001.0059340 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002307 | 334641180-28780-DETAIL-01_26_2023-CONDFRAY-1^06147003.0142100 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002308 | 334765480-6480-DETAIL-04_22_2024-SVCDEFLC-1^06145001.0010500 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002309 | 335074135-16539-DETAIL-07_10_2024-GO95HV-1^06244004.0203200 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002310 | 335238003-62152-DETAIL-06_26_2023-GRDRODHI-1^06244009.0302802 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002311 | 335451629-10630-DRONE_VS-11_13_2024-UBPBXARM-1^668010/00 16/023 | CROSSARM | Non-HFTD | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002312 | 33559771-17349-DTLSB-05_01_2024-SVCROOF-1^06245007.0228602 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002313 | 335700332-35569-DTLTRT-06_04_2021-GO95HV-1^668041/00 9/008 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002314 | 335774791-16349-DETAIL-02_20_2024-GO95MLD-1^07113002.0182008 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002315 | 295615477-96477-ADMIN-03_10_2023-GO95CL10-1^06148004.0160305 | OTHER | Non-HFTD | Distribution | 2023-03-10 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002316 | 295615477-96477-DETAIL-01_16_2023-GO95MLD-1^06148004.0160305 | OTHER | Non-HFTD | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002317 | 296060523-16129-DETAIL-03_21_2016-SVCWIND-1^06142012.0149700 | OTHER | Non-HFTD | Distribution | 2016-03-21 | 2019-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002318 | 296060523-16129-DETAIL-11_08_2021-GO95CLSV-1^06142012.0149700 | OTHER | Non-HFTD | Distribution | 2021-11-08 | 2024-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002319 | 296102961-80679-DTLSB-08_08_2023-GO95MLD-1^06243009.0140601 | OTHER | Non-HFTD | Distribution | 2023-08-08 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002320 | 296113901-28009-ADMIN-03_11_2024-GO95TCH-1^06147004.0028904 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002321 | 296113901-28009-DETAIL-03_11_2024-GO95HV-1^06147004.0028904 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002322 | 296314126-61930-DTLSB-01_31_2023-GO95MLD-1^06248001.0367905 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002323 | 296338233-84339-DETAIL-03_15_2023-GO95MLD-1^07216001.0290600 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002324 | 29644606-18078-DETAIL-05_09_2022-GO95MLD-1^07116001.0096206 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002325 | 29644606-18078-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096206 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002326 | 296664389-8479-AUDIT-04_19_2024-GO95TCH-1^06147005.0217004 | OTHER | Non-HFTD | Distribution | 2024-04-19 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002327 | 296703777-59119-DETAIL-06_22_2022-GO95MLD-1^07116007.0111401 | OTHER | HFTD Tier 2 | Distribution | 2022-06-22 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002328 | 296840695-57130-DTLSB-05_09_2024-GO95MLD-1^06244001.0107800 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002329 | 297777684-89684-DETAIL-04_25_2024-GO95HV-1^06142016.0175700 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002330 | 335920711-25469-DTLTRT-07_20_2022-GO95HV-1^668005/00 7/054 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002331 | 336121706-75160-DTLTRT-10_09_2023-GO95MLD-1^668010/00 16/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002332 | 336169422-14299-DETAIL-05_29_2024-SVCENTCO-1^06246005.0178101 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002333 | 336309641-94429-DETAIL-05_07_2024-GUYHINS-1^06142012.0122108 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002334 | 336388562-28080-DTLSB-02_16_2023-GO95MLD-1^06248001.0203701 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002335 | 297777684-89684-DETAIL-04_25_2024-GO95MLD-1^06142016.0175700 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002336 | 297827285-87469-DETAIL-07_05_2024-SVCENTCO-1^06245004.0308401 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002337 | 297936813-5140-DTLTRT-10_03_2023-GO95MLD-1^668010/00 10/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002338 | 298136609-79840-DETAIL-05_06_2024-GO95STUB-1^06142012.0124008 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002339 | 298197625-50349-DETAIL-03_14_2024-GO95MLD-1^06245006.0019200 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002340 | 336600334-10999-DETAIL-03_21_2024-GO95MLD-1^06147005.0209500 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002341 | 336600334-10999-DETAIL-03_21_2024-GRDRODHI-1^06147005.0209500 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002342 | 337345641-92029-DETAIL-05_07_2024-GO95HV-1^06142012.0123112 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002343 | 337370964-4669-DETAIL-08_05_2024-GO95HV-1^06245004.0327702 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002344 | 337370964-4669-DETAIL-08_05_2024-GO95MLD-1^06245004.0327702 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002345 | 337714979-31759-DTLSB-02_05_2024-GO95HV-1^07216001.0192940 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002346 | 337812981-57942-DTLSB-09_06_2022-GO95MLD-1^06243004.0065240 | OTHER | HFTD Tier 2 | Distribution | 2022-09-06 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002347 | 337934225-11879-DETAIL-04_04_2024-CLRTOUCH-1^06147005.0147000 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002348 | 337934225-11879-DETAIL-04_04_2024-GO95MLD-1^06147005.0147000 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002349 | 337998833-20159-DETAIL-05_29_2024-GO95MLD-1^06246005.0213700 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002350 | 338027386-38386-DTLSB-05_13_2024-GO95MLD-1^06244001.0154203 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002351 | 338665213-56579-DETAIL-01_19_2023-SVCROAD-1^06148004.0212601 | OTHER | Non-HFTD | Distribution | 2023-01-19 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002352 | 338762130-72359-DETAIL-07_14_2022-SVCWIND-1^07116001.0041500 | OTHER | HFTD Tier 2 | Distribution | 2022-07-14 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002353 | 338857411-52709-DETAIL-11_08_2022-GO95MLD-1^06246008.0057501 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002354 | 339535250-69439-DETAIL-06_24_2024-GO95MLD-1^06244005.0231301 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002355 | 339910316-2989-DETAIL-10_24_2022-GO95HV-1^06247008.0315201 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002356 | 340246864-93280-DTLTRT-02_06_2024-GUYHINS-1^07216001.0309907 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002357 | 340456853-42009-DETAIL-10_26_2022-GO95HV-1^06246009.0125501 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002358 | 340511519-27509-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0135600 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002359 | 340630532-73049-DETAIL-02_20_2024-GO95MLD-1^07113002.0181106 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002360 | 34067098-6249-DETAIL-05_10_2022-ABNDEQPM-1^07116001.0059404 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002361 | 34067098-6249-DETAIL-05_10_2022-GO95MLD-1^07116001.0059404 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002362 | 34067098-6249-DETAIL-05_10_2022-GUYNOINS-1^07116001.0059404 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002363 | 340740238-94189-DTLSB-08_10_2023-GO95MLD-1^06243009.0158001 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002364 | 341063761-29909-DTLSB-05_06_2024-GO95HV-1^06245007.0226800 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002365 | 341066074-9780-DTLSB-05_08_2024-GO95MLD-1^06245001.0331900 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002366 | 298361119-63029-DTLSB-08_14_2023-GO95HV-1^06243009.0244101 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002367 | 298439623-12723-DETAIL-03_23_2023-GO95MLD-1^06142016.0081700 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002368 | 298439623-12723-DETAIL-03_23_2023-GRDRODHI-1^06142016.0081700 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002369 | 298938073-67429-DTLSB-09_06_2023-GO95HV-1^06243007.0186600 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002370 | 299017425-58210-DETAIL-03_12_2025-GO95HV-1^06238004.0223601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002371 | 299017425-58210-DETAIL-11_10_2022-SVCWIND-1^06238004.0223601 | OTHER | HFTD Tier 2 | Distribution | 2022-11-10 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002372 | 299265658-5850-DETAIL-02_27_2025-GO95HV-1^06240004.0050144 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002373 | 299321503-28938-DETAIL-04_03_2024-GO95MLD-1^06147005.0229900 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002374 | 299499755-81869-DRONE_HY-10_17_2023-GO95HV-1^668033/00 9/040 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002375 | 299565562-58349-DETAIL-10_15_2024-GO95MLD-1^07216001.0205100 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002376 | 341309853-25459-DETAIL-08_14_2024-BIRDDMG-1^06246004.0170001 | POLE | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002377 | 341449944-30699-DETAIL-03_21_2024-GO95HV-1^06147005.0184800 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002378 | 341576079-31180-DETAIL-05_02_2024-GO95MLD-1^06142012.0126105 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002379 | 341926478-92539-DTLSB-02_21_2024-GO95HV-1^07216001.0262700 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002380 | 341926478-92539-DTLSB-02_21_2024-GO95MLD-1^07216001.0262700 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002381 | 341939804-41813-DTLSB-04_29_2024-SVCWIND-1^06245007.0226542 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002382 | 299755578-8740-DTLSB-02_01_2023-GO95HV-1^06247001.0011900 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002383 | 300226044-10599-DETAIL-06_05_2024-GO95MLD-1^06246006.0257801 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002384 | 300275988-95359-DETAIL-05_31_2024-GO95MLD-1^06246005.0326401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002385 | 300344880-79029-DTLSB-08_17_2023-GO95HV-1^06243009.0131200 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002386 | 300344880-79029-DTLSB-08_17_2023-GO95MLD-1^06243009.0131200 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002387 | 342508654-64680-DETAIL-10_22_2024-GO95HV-1^07216001.0208600 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002388 | 342508654-64680-DETAIL-10_22_2024-GO95MLD-1^07216001.0208600 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002389 | 342550171-7770-DTLTRT-04_09_2024-BIRDDMG-1^668067/00 4/001 | POLE | HFTD Tier 2 | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002390 | 342560234-42580-DTLTRT-09_27_2023-GO95MLD-1^668010/00 9/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002391 | 342681837-3938-DETAIL-04_03_2024-GO95HV-1^06246005.0030500 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002392 | 342776961-3061-DETAIL-06_26_2023-GO95HV-1^06244009.0325601 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002393 | 34280515-80129-DETAIL-07_07_2023-GO95MLD-1^06244008.0338200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002394 | 343230929-12869-ADMIN-06_15_2021-POLEDERP-1^668005/03 8/005 | POLE | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002395 | 343230929-12869-DTLTRT-10_10_2022-GO95HV-1^668005/03 8/005 | OTHER | Non-HFTD | Transmission | 2022-10-10 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002396 | 343375588-87739-DETAIL-10_15_2024-SVCNEUT-1^07216001.0201409 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002397 | 343565206-21366-DETAIL-09_27_2021-GO95MLD-1^06148004.0356202 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002398 | 343666524-77524-DTLSB-08_10_2023-GO95MLD-1^06243009.0225700 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002399 | 343666524-77524-DTLSB-08_10_2023-GUYHINS-1^06243009.0225700 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002400 | 343719174-19459-DETAIL-10_10_2024-ENCHRW-1^07216001.0205008 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002401 | 343990278-48770-DETAIL-04_11_2023-RISEGRD-1^06240004.0169511 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002402 | 344113746-13859-DETAIL-03_27_2024-GO95MLD-1^06247005.0324501 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002403 | 344180031-24709-DETAIL-11_07_2022-ABNDEQPM-1^06246008.0059400 | OTHER | HFTD Tier 2 | Distribution | 2022-11-07 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002404 | 344253653-20990-DETAIL-02_09_2023-GO95MLD-1^06146004.0087000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002405 | 344562568-49050-DETAIL-01_16_2025-BIRDDMG-1^06240004.0097604 | POLE | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002406 | 344584591-38563-DTLSB-04_16_2024-SVCWIND-1^06245007.0224342 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002407 | 344626024-72090-DETAIL-02_09_2023-GO95MLD-1^06146004.0162900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002408 | 344856405-18570-DRONE_HY-10_18_2023-ABNDEQPM-1^668033/00 3/042 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002409 | 345302649-56299-DETAIL-03_11_2024-GO95TCH-1^06147004.0014903 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002410 | 345562542-26690-DETAIL-02_08_2023-GO95HV-1^06146002.0274800 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002411 | 345755299-92649-DETAIL-08_20_2024-GO95HV-1^06245005.0251201 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002412 | 300352575-87319-DETAIL-10_24_2022-GO95HV-1^06247008.0304100 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002413 | 300480741-74979-DTLTRT-10_30_2023-GO95HV-1^668010/00 18/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-30 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002414 | 300891173-42579-DRONE_VS-11_13_2024-BIRDDMG-1^668010/00 7/024 | POLE | Non-HFTD | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002415 | 301128403-16349-DETAIL-10_10_2024-CLMBTRE-1^07216001.0207002 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002416 | 30113649-98721-DETAIL-06_01_2023-GO95MLD-1^06243009.0011502 | OTHER | HFTD Tier 2 | Distribution | 2023-06-01 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002417 | 301425500-95462-DTLSB-07_18_2023-GO95MLD-1^06243010.0039301 | OTHER | HFTD Tier 2 | Distribution | 2023-07-18 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002418 | 302094694-59449-DTLSB-02_08_2024-GO95HV-1^07216001.0198105 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002419 | 302386598-31269-DTLSB-07_01_2024-GO95HV-1^06245006.0180001 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002420 | 302386598-31269-DTLSB-07_01_2024-GO95MLD-1^06245006.0180001 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002421 | 302395464-18440-DETAIL-10_25_2024-GO95HV-1^07216001.0209904 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002422 | 302532614-86614-DETAIL-03_29_2023-GO95HV-1^06142016.0085000 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002423 | 302752668-47023-DETAIL-03_14_2023-GO95MLD-1^07117003.0113703 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002424 | 303087156-99663-DETAIL-03_28_2024-GO95MLD-1^06247005.0331500 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002425 | 303116739-91792-DETAIL-06_14_2023-GO95HV-1^06244010.0288400 | OTHER | HFTD Tier 2 | Distribution | 2023-06-14 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002426 | 30317738-62159-DETAIL-03_22_2024-SVCWIND-1^06247005.0287402 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002427 | 345809148-75459-DETAIL-06_03_2024-GO95HV-1^06246005.0315502 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002428 | 345952881-76349-DETAIL-02_20_2024-SVCDEFLC-1^07113002.0181004 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002429 | 345952881-76349-DETAIL-02_20_2024-SVCROAD-1^07113002.0181004 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002430 | 345970944-95023-DTLSB-04_30_2024-SVCROAD-1^06245007.0221500 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002431 | 345993955-57129-DETAIL-05_16_2024-GO95MLD-1^06142012.0120705 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002432 | 303219073-4483-DETAIL-08_20_2024-GO95HV-1^06246004.0185241 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002433 | 303421003-25050-DTLSB-05_22_2024-GO95MLD-1^06243001.0048800 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002434 | 303650029-10449-ADMIN-03_03_2025-POLEDERP-1^07216001.0299400 | POLE | Non-HFTD | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002435 | 304123214-80303-DTLSB-02_26_2024-GO95MLD-1^07216001.0277605 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002436 | 304123214-80303-DTLSB-02_26_2024-GUYHINS-1^07216001.0277605 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002437 | 304304846-26450-DETAIL-10_22_2024-GO95MLD-1^07216001.0207402 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002438 | 346078518-43170-DTLTRT-09_30_2020-GO95HV-1^668018/00 6/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002439 | 346460464-87290-DETAIL-02_15_2023-SVCROAD-1^06247002.0233500 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002440 | 347535107-56389-DTLSB-08_22_2024-GO95MLD-1^06245006.0324401 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002441 | 347686913-94769-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/011 | OTHER | Non-HFTD | Transmission | 2021-06-07 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002442 | 347776651-74929-DETAIL-05_08_2024-GO95HV-1^06142012.0120004 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002443 | 347810173-39999-DETAIL-05_30_2024-GO95HV-1^06246005.0150101 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002444 | 347899611-50652-DETAIL-06_29_2023-GO95MLD-1^06244009.0325101 | OTHER | Non-HFTD | Distribution | 2023-06-29 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002445 | 348136981-46219-DTLTRT-08_15_2022-ANCHIDLE-1^668005/00 9/086 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-15 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002446 | 348203059-59183-DETAIL-08_06_2024-GO95MLD-1^06245006.0155100 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002447 | 348230547-23547-DTLSB-02_27_2024-GO95MLD-1^07216001.0273808 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002448 | 348516356-3049-DETAIL-08_06_2024-GO95HV-1^06245004.0332001 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002449 | 348701085-87449-DETAIL-07_22_2024-GO95HV-1^06245006.0115601 | OTHER | Non-HFTD | Distribution | 2024-07-22 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002450 | 348816811-94190-DETAIL-01_21_2025-BIRDDMG-1^06239004.0256405 | POLE | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002451 | 348953118-32630-DTLTRT-10_18_2023-GO95HV-1^668010/00 11/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002452 | 349228146-61240-DETAIL-02_26_2025-SVCDEFLC-1^06241005.0362900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002453 | 349362985-39340-DETAIL-02_19_2025-BIRDDMG-1^06240004.0219908 | POLE | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002454 | 349835968-90899-DETAIL-07_30_2024-GO95HV-1^06244005.0355202 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002455 | 349845154-10849-DTLSB-02_07_2024-GO95HV-1^07216001.0199300 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002456 | 350115474-38560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 3/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002457 | 350242259-8990-DETAIL-04_11_2024-GO95HV-1^06245002.0102102 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002458 | 350283313-72899-DETAIL-03_11_2024-GO95HV-1^06147005.0173700 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002459 | 350283313-72899-DETAIL-03_11_2024-GO95MLD-1^06147005.0173700 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002460 | 350294799-58170-DETAIL-02_12_2025-BIRDDMG-1^06240004.0167549 | POLE | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002461 | 350441839-9169-ADMIN-07_24_2020-INSULPLM-1^668041/00 2/020 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2020-07-24 | 2023-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002462 | 350669135-33872-DETAIL-07_17_2024-GO95HV-1^06244005.0229640 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002463 | 304370581-56259-DETAIL-03_02_2023-GO95CL10-1^07117002.0203301 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002464 | 304370581-56259-DETAIL-03_02_2023-GO95MLD-1^07117002.0203301 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002465 | 30438443-69799-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128702 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002466 | 304525240-31479-DETAIL-02_24_2025-GUYHINS-1^06240004.0152610 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002467 | 304739299-27029-DTLSB-08_14_2023-GO95HV-1^06243009.0242900 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002468 | 30501703-41152-DETAIL-06_26_2023-GO95HV-1^06244009.0301700 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002469 | 305058294-59989-DETAIL-07_09_2024-GO95MLD-1^06244005.0224000 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002470 | 305224989-61250-DETAIL-04_24_2024-GO95HV-1^06145001.0052300 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002471 | 305491966-16450-DTLSB-02_01_2023-GO95MLD-1^06248001.0369601 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002472 | 305758070-74139-DTLSB-02_15_2024-GO95MLD-1^07216001.0264301 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002473 | 305841463-65309-ADMIN-06_05_2024-GO95STUB-1^06245010.0323601 | OTHER | HFTD Tier 2 | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002474 | 305949071-11009-DTLSB-08_28_2024-GO95MLD-1^06245007.0159100 | OTHER | Non-HFTD | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002475 | 305949071-11009-DTLSB-08_28_2024-GRDRODHI-1^06245007.0159100 | OTHER | Non-HFTD | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002476 | 306358285-19703-DETAIL-03_05_2024-SVCROAD-1^06245007.0275401 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002477 | 306465054-40899-DETAIL-07_11_2024-GO95MLD-1^06244005.0219803 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002478 | 306982009-50859-DETAIL-03_13_2023-SVCENTBK-1^07216001.0290740 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002479 | 307034483-35980-DTLSB-07_20_2023-GO95MLD-1^06243010.0145700 | OTHER | HFTD Tier 2 | Distribution | 2023-07-20 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002480 | 307092451-81189-DETAIL-01_23_2023-GO95CL10-1^06148004.0192201 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002481 | 307092451-81189-DETAIL-01_23_2023-GO95MLD-1^06148004.0192201 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002482 | 307308468-84550-DETAIL-04_17_2024-GO95HV-1^06145001.0018500 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002483 | 30748950-270-DETAIL-04_12_2023-GO95MLD-1^06240004.0167702 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002484 | 307611124-11480-DTLTRT-09_27_2023-GO95MLD-1^668010/00 8/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002485 | 307669586-84189-DETAIL-06_06_2023-GO95MLD-1^06244010.0347200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002486 | 308299584-7759-ADMIN-03_05_2025-POLEREPL-1^06245007.0274201 | POLE | Non-HFTD | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002487 | 308345061-61030-DTLTRT-10_30_2023-GO95HV-1^668010/00 1/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-30 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002488 | 350741283-27283-DETAIL-03_30_2023-GO95HV-1^06142016.0059000 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002489 | 351253541-17270-AUDIT-11_10_2023-GO95HV-1^668010/00 7/001 | OTHER | Non-HFTD | Transmission | 2023-11-10 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002490 | 351314754-14810-DETAIL-03_18_2025-GO95HV-1^06238004.0156301 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002491 | 351493088-56359-DETAIL-05_31_2024-GO95MLD-1^06246005.0325401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002492 | 351639544-56522-DETAIL-07_06_2023-GO95MLD-1^06244008.0330900 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002493 | 351639731-40369-DRONE_HY-09_16_2023-GO95HV-1^668002/00 9/061 | OTHER | HFTD Tier 2 | Transmission | 2023-09-16 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002494 | 352334061-96852-DETAIL-06_08_2023-GO95HV-1^06244009.0327802 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002495 | 352730046-94671-DETAIL-02_19_2025-GO95HV-1^06239004.0365944 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002496 | 353341967-26692-DETAIL-07_06_2023-GO95CL10-1^06244008.0326740 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002497 | 353341967-26692-DETAIL-07_06_2023-GO95MLD-1^06244008.0326740 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002498 | 353483896-44280-DETAIL-03_04_2025-GO95HV-1^06240004.0051001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002499 | 354301894-83894-DETAIL-01_23_2025-CLRTOUCH-1^06240004.0092407 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002500 | 354301894-83894-DETAIL-01_23_2025-CLRTOUCH-2^06240004.0092407 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002501 | 354972789-42579-DETAIL-03_19_2025-GO95HV-1^06239002.0029501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002502 | 355159461-58949-DETAIL-02_21_2024-GO95MLD-1^07113001.0143201 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002503 | 355376929-56649-DETAIL-02_22_2024-GO95MLD-1^07216001.0348702 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002504 | 355590733-84733-DETAIL-06_13_2024-SVCROAD-1^06244007.0046500 | OTHER | HFTD Tier 2 | Distribution | 2024-06-13 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002505 | 355792818-2779-DETAIL-04_10_2024-CUTOUTAR-1^06245002.0119201 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002506 | 355794939-81400-DETAIL-04_22_2024-GO95HV-1^06146001.0365400 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002507 | 355810431-30431-DETAIL-02_03_2025-GO95HV-1^06240004.0169902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002508 | 355834540-51232-DTLSB-07_19_2023-GO95MLD-1^06243010.0022301 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002509 | 356576830-12839-DTLSB-02_16_2024-SVCENTCO-2^07216001.0263201 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002510 | 356639328-48339-DETAIL-08_06_2024-GO95HV-1^06244005.0329901 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002511 | 356717214-12149-DETAIL-03_16_2023-GO95HV-1^07114001.0283308 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002512 | 356936294-20139-DTLSB-02_06_2024-GO95MLD-1^07216001.0307903 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002513 | 308345061-61030-DTLTRT-10_30_2023-GUYLOINS-1^668010/00 1/014 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-30 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002514 | 308439259-18679-DETAIL-07_10_2024-GO95MLD-1^06244004.0190803 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002515 | 308531929-54273-DETAIL-04_01_2024-BIRDDMG-1^06246005.0039801 | POLE | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002516 | 308586886-65840-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 3/048 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002517 | 309191928-56800-DTLTRT-11_02_2023-GUYHINS-1^668010/00 5/020 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-02 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002518 | 309211598-90561-DETAIL-02_25_2025-GO95BLTC-1^06241005.0151701 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002519 | 309266265-45950-DTLSB-02_08_2023-GO95HV-1^06248001.0164401 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002520 | 309340196-1860-DTLTRT-10_09_2023-GO95MLD-1^668010/00 9/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002521 | 309392004-44560-DETAIL-01_14_2025-BIRDDMG-1^06240004.0098203 | POLE | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002522 | 309971040-24163-DTLSB-04_17_2024-GO95MLD-1^06245007.0222446 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002523 | 309971040-24163-DTLSB-04_17_2024-SVCWIND-1^06245007.0222446 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002524 | 310136171-4520-DETAIL-02_17_2025-GO95HV-1^06240004.0275401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002525 | 310145405-74879-DETAIL-01_16_2023-GO95BLTC-1^06148004.0165305 | OTHER | Non-HFTD | Distribution | 2023-01-16 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002526 | 311098265-59039-DETAIL-10_15_2024-GO95MLD-1^07216001.0204206 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002527 | 311428785-55459-DETAIL-04_24_2023-GO95HV-1^07117003.0027401 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002528 | 311428785-55459-DETAIL-04_24_2023-GO95MLD-1^07117003.0027401 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002529 | 311847980-26789-DETAIL-01_09_2023-GO95HV-1^06148003.0153100 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002530 | 311980014-62343-DETAIL-05_09_2023-SVCROAD-1^06245006.0271701 | OTHER | Non-HFTD | Distribution | 2023-05-09 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002531 | 312146684-69259-DTLSB-02_14_2024-SVCDEFLC-2^07216001.0198313 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002532 | 312146684-69259-DTLSB-02_14_2024-SVCROAD-1^07216001.0198313 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002533 | 312159038-10138-DETAIL-07_05_2023-GO95MLD-1^06244009.0019100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002534 | 312578218-78509-DETAIL-03_28_2024-GO95MLD-1^06147005.0150900 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002535 | 312955883-45913-DTLSB-05_02_2024-GO95MLD-1^06245007.0229743 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002536 | 313270816-14572-DETAIL-06_06_2024-SVCENTCO-1^06245006.0032140 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002537 | 31341935-65063-DETAIL-04_24_2023-GO95HV-1^07117003.0104700 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002538 | 313891386-56949-DTLSB-04_09_2024-SVCROAD-1^06245007.0228003 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002539 | 356973354-9100-DETAIL-10_21_2024-GO95CL10-1^07216001.0209706 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002540 | 357169143-65049-DETAIL-03_01_2023-GO95MLD-1^07216001.0292505 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002541 | 357237728-33370-DETAIL-01_23_2025-GO95CL10-1^06240004.0081204 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002542 | 357410003-75400-DTLSB-02_14_2023-GO95MLD-1^06248001.0346901 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002543 | 357687409-75430-DETAIL-09_10_2024-SVCENTCO-1^06240004.0097403 | OTHER | HFTD Tier 2 | Distribution | 2024-09-10 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002544 | 357771333-6083-DTLSB-10_02_2024-GUYHINS-1^06245007.0218440 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002545 | 358093516-99871-DETAIL-02_19_2025-SVCROAD-1^06239004.0365842 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002546 | 35825228-5159-DETAIL-04_08_2024-GO95MLD-1^06247005.0286100 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002547 | 358281493-580-DETAIL-02_06_2025-GO95HV-1^06240004.0167301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002548 | 358397965-17599-DETAIL-05_24_2023-GUYHINS-1^06245005.0228000 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-05-24 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002549 | 358925288-83689-DETAIL-05_31_2024-GO95HV-1^06246005.0324400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002550 | 360691820-76870-AUDIT-05_22_2023-SVCDEFLC-1^06240004.0169403 | OTHER | HFTD Tier 2 | Distribution | 2023-05-22 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002551 | 360779864-84159-DETAIL-08_15_2024-GO95HV-1^06246005.0148101 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002552 | 36089801-20911-ADMIN-07_04_2022-POLEDERP-1^668005/00 5/038 | POLE | Non-HFTD | Transmission | 2022-07-04 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002553 | 36089801-20911-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 5/038 | OTHER | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002554 | 360954055-97700-DETAIL-04_22_2024-GO95MLD-1^06146001.0361001 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002555 | 361195853-4752-DETAIL-06_13_2023-GO95MLD-1^06244010.0225501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-13 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002556 | 361415634-5399-ADMIN-07_18_2023-POLEREPL-1^06241009.0220501 | POLE | Non-HFTD | Distribution | 2023-07-18 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002557 | 362141548-86460-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 3/052 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002558 | 362151290-2389-DTLSB-07_23_2024-GO95MLD-1^06245007.0107201 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002559 | 362545771-47710-DETAIL-04_15_2024-GO95MLD-1^06145001.0139200 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002560 | 362789733-65959-AUDIT-08_06_2024-GO95MLD-1^06246006.0352604 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002561 | 362854203-15589-DTLSB-08_16_2023-GO95HV-1^06243009.0283601 | OTHER | Non-HFTD | Distribution | 2023-08-16 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002562 | 36287608-43169-DTLTRT-10_10_2023-GUYNOINS-1^668010/00 12/044 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002563 | 362960871-95739-DETAIL-02_20_2024-SVCENTCO-1^07113001.0138203 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002564 | 314182108-70579-DETAIL-04_22_2024-SVCROAD-1^06145001.0119100 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002565 | 314235234-25518-DETAIL-03_04_2024-SVCROAD-1^06245007.0274301 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002566 | 314363016-27289-DTLSB-04_22_2024-SVCWIND-1^06245007.0227202 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002567 | 314744494-51060-DTLSB-02_07_2023-GO95HV-1^06248001.0158102 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002568 | 314760344-31629-DTLSB-09_07_2023-ABNDEQPM-1^06243008.0121601 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002569 | 315357875-82560-DTLSB-02_01_2023-GO95BLTC-1^06248001.0368101 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002570 | 315357875-82560-DTLSB-02_01_2023-GO95HV-1^06248001.0368101 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002571 | 31557116-96270-DETAIL-01_24_2025-GO95HV-1^06239004.0257943 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002572 | 315614896-75700-DTLTRT-04_18_2024-GO95HV-1^668067/00 3/021 | OTHER | Non-HFTD | Transmission | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002573 | 315830923-54635-DETAIL-01_30_2025-SVCDEFLC-1^06239004.0245600 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002574 | 315901943-16198-DETAIL-05_09_2022-SVCROAD-1^07116001.0096207 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002575 | 316094551-78909-DTLSB-05_02_2024-GUYNOINS-1^06245007.0226802 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002576 | 316208379-19860-DETAIL-04_22_2024-GO95MLD-1^06146001.0362001 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002577 | 316305611-33859-DETAIL-06_05_2024-GO95MLD-1^06246006.0266301 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002578 | 316351124-58599-ADMIN-03_21_2024-ABNDEQPM-1^06147005.0186600 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002579 | 316351124-58599-ADMIN-03_21_2024-CUTOUTAR-1^06147005.0186600 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002580 | 316477396-65060-DETAIL-10_16_2024-GO95MLD-1^07216001.0207803 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002581 | 316765703-19313-DTLSB-04_25_2024-GUYNOINS-1^06245007.0227548 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002582 | 317007153-40550-DETAIL-01_23_2025-GO95HV-1^06239004.0256904 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002583 | 317007153-40550-DETAIL-01_23_2025-GO95TCH-1^06239004.0256904 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002584 | 317150685-28260-DTLTRT-10_09_2023-GO95HV-1^668010/00 17/037 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002585 | 317150685-28260-DTLTRT-10_09_2023-GO95MLD-1^668010/00 17/037 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002586 | 317226001-77119-DTLTRT-08_04_2022-GUYHINS-1^668005/00 6/084 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-04 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002587 | 31737743-7540-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002588 | 317666859-7259-DETAIL-05_31_2024-GO95HV-1^06246005.0332400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002589 | 363203193-54964-DETAIL-03_25_2024-GO95MLD-1^06244005.0146403 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002590 | 36328941-64469-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/007 | OTHER | Non-HFTD | Transmission | 2021-06-03 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002591 | 363530533-310-DTLSB-05_28_2024-GO95MLD-1^06243001.0125203 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002592 | 363645500-78379-DETAIL-03_05_2024-CONDFRAY-1^06147004.0025900 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002593 | 363685474-66474-DETAIL-02_27_2025-SVCDEFLC-1^06240004.0063208 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002594 | 363960656-78623-ADMIN-02_19_2025-POLEREPL-1^06245007.0220542 | POLE | Non-HFTD | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002595 | 364048031-73859-DETAIL-06_05_2024-GO95HV-1^06246006.0267401 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002596 | 36408264-99213-DTLSB-04_25_2024-SVCRUBLG-1^06245007.0228545 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002597 | 364195069-4759-DETAIL-03_26_2024-GO95HV-1^06246005.0053400 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002598 | 364432770-19009-DETAIL-03_11_2024-GO95MLD-1^06147004.0028900 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002599 | 364780888-28870-DTLTRT-09_30_2020-GO95HV-1^668018/00 7/002 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002600 | 365024048-38410-DTLSB-05_09_2024-GO95MLD-1^06244001.0217403 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002601 | 36511183-68913-DTLSB-05_02_2024-GO95HV-1^06245007.0229742 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002602 | 365216818-56610-DTLSB-05_13_2024-GUYHINS-1^06244001.0215401 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002603 | 365235786-50182-DETAIL-07_11_2023-GO95HV-1^06244008.0321900 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002604 | 365479595-81439-DTLSB-02_22_2023-GO95MLD-1^07216001.0287805 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002605 | 365712236-63236-DETAIL-05_09_2024-GO95MLD-1^06142012.0120414 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002606 | 365765106-59459-DETAIL-10_08_2024-GO95MLD-1^07216001.0204001 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002607 | 366513394-17359-DETAIL-10_16_2024-GO95MLD-1^07216001.0209804 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002608 | 366722447-549-DETAIL-10_24_2024-GO95MLD-1^07216001.0200400 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002609 | 367670523-18110-DTLSB-07_14_2022-GO95MLD-1^07216001.0210800 | OTHER | Non-HFTD | Distribution | 2022-07-14 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002610 | 367701083-68339-DETAIL-08_06_2024-GO95HV-1^06244005.0329900 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002611 | 367945929-99953-DTLSB-04_17_2024-POLETOP-1^06245007.0225342 | POLE | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002612 | 367945929-99953-DTLSB-04_17_2024-SVCWIND-1^06245007.0225342 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002613 | 368031352-79310-DETAIL-02_08_2023-GO95HV-1^06145002.0047801 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002614 | 368084071-20649-DETAIL-04_28_2022-GO95MLD-1^07116001.0094400 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002615 | 318008961-4980-DETAIL-02_14_2025-BIRDDMG-1^06240004.0168307 | POLE | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002616 | 318203293-86402-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 3/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002617 | 318203293-97170-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 3/010 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002618 | 318292291-4989-DETAIL-03_11_2024-CLRTOUCH-1^06147004.0028902 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002619 | 318292291-4989-DETAIL-03_11_2024-GO95MLD-1^06147004.0028902 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002620 | 318366660-67260-ADMIN-01_11_2022-POLEDERP-1^06147001.0105400 | POLE | Non-HFTD | Distribution | 2022-01-11 | 2025-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002621 | 318448550-46279-DETAIL-05_11_2023-GO95MLD-1^06245005.0264300 | OTHER | Non-HFTD | Distribution | 2023-05-11 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002622 | 318655413-10239-DETAIL-07_31_2024-GO95HV-1^06244005.0337904 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002623 | 319039283-37560-DETAIL-02_22_2023-GO95MLD-1^06247002.0032100 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002624 | 319039283-37560-DETAIL-02_22_2023-GRDRODHI-1^06247002.0032100 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002625 | 319420179-53790-DETAIL-01_16_2025-GO95MLD-1^06239004.0256216 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002626 | 319843248-57309-DETAIL-04_03_2024-GO95HV-1^06147005.0157004 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002627 | 319875806-25449-DETAIL-07_29_2024-GO95HV-1^06245006.0111904 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002628 | 320635933-22899-DETAIL-07_10_2024-GO95MLD-1^06244005.0271900 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002629 | 320642394-17150-DTLTRT-10_04_2023-GO95MLD-1^668010/00 4A/036 | OTHER | HFTD Tier 2 | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002630 | 320642394-17150-DTLTRT-10_04_2023-GUYNOINS-2^668010/00 4A/036 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002631 | 320642394-17150-DTLTRT-10_04_2023-GUYNOINS-3^668010/00 4A/036 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002632 | 320684984-36449-DTLSB-02_26_2024-GO95MLD-1^07216001.0277801 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002633 | 320686243-48243-DETAIL-04_29_2024-GRDRODHI-1^06142016.0079703 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002634 | 320769258-92743-DETAIL-03_09_2023-GUYNOINS-1^07117002.0207141 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002635 | 320857180-20209-DTLTRT-10_26_2022-GO95MLD-1^668001/00 13/028 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002636 | 321130656-4300-DTLTRT-10_24_2023-GUYHINS-1^668010/00 20X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-24 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002637 | 321130656-4300-DTLTRT-10_24_2023-GUYHINS-2^668010/00 20X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-24 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002638 | 321277036-75149-DETAIL-10_09_2024-SVCDEFLC-1^07216001.0203205 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002639 | 32142145-92740-DETAIL-02_26_2025-GO95TCH-1^06240004.0219700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002640 | 36843439-61679-DETAIL-09_29_2020-GO95HV-1^668018/00 12/006 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002641 | 368848424-26440-DETAIL-02_26_2025-SVCENTCO-1^06240004.0217901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002642 | 368861862-29769-DTLTRT-10_16_2023-GO95HV-1^668010/00 9/002 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002643 | 368961379-77010-DETAIL-04_22_2024-GO95HV-1^06146001.0360200 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002644 | 368961379-77010-DETAIL-04_22_2024-GRDRODHI-1^06146001.0360200 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002645 | 369253856-33479-DTLTRT-11_01_2023-GUYHINS-1^668010/00 9/018 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-01 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002646 | 369308514-50614-DETAIL-03_28_2023-GO95MLD-1^06142016.0082807 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002647 | 369776064-87290-DETAIL-03_18_2025-CONDCOIL-1^06239003.0252801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2026-03-31 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130002648 | 370094860-809-DTLSB-07_23_2024-GO95MLD-1^06245007.0107500 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002649 | 370520451-28802-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002650 | 370520451-29802-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002651 | 370734323-35652-DETAIL-06_26_2023-GO95HV-1^06244009.0303802 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002652 | 371360156-39670-DETAIL-01_23_2025-GO95HV-1^06239004.0256742 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002653 | 371579082-45529-DETAIL-05_09_2024-GO95MLD-1^06142012.0121407 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002654 | 372267429-33570-DETAIL-02_13_2025-SVCNEUT-1^06240004.0169201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002655 | 372455971-36929-DETAIL-05_09_2024-GO95HV-1^06142012.0120412 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002656 | 372491118-60239-DETAIL-10_14_2024-GO95MLD-1^07216001.0201208 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002657 | 372491118-60239-DETAIL-10_14_2024-SVCENTBK-1^07216001.0201208 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002658 | 372802988-14720-DETAIL-04_02_2024-GO95HV-1^06147005.0161900 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002659 | 373053625-46625-DETAIL-02_27_2024-GO95MLD-1^07113002.0071101 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002660 | 373053625-46625-DETAIL-02_27_2024-GRDRODHI-1^07113002.0071101 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002661 | 373059153-22909-DETAIL-04_03_2025-SVCENTCO-1^06241005.0028244 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002662 | 373560836-77569-DETAIL-06_06_2024-GO95MLD-1^06245006.0036501 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002663 | 373587281-15709-DTLSB-08_26_2024-GO95HV-1^06245007.0112100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002664 | 373654043-95959-DETAIL-06_06_2024-GO95MLD-1^06246006.0352700 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002665 | 321491353-77759-DETAIL-03_02_2023-GO95HV-1^07216001.0291708 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002666 | 321913391-83179-DETAIL-05_09_2022-GO95HV-1^668002/00 20/050 | OTHER | HFTD Tier 2 | Transmission | 2022-05-09 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002667 | 322021711-75549-DETAIL-02_28_2024-GO95HV-1^07113001.0148800 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002668 | 322109934-13660-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 6/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002669 | 322350681-31173-DETAIL-03_02_2023-GO95MLD-1^07117002.0203300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002670 | 322673471-44130-DETAIL-03_04_2025-GO95MLD-1^06240004.0150304 | OTHER | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002671 | 323277288-5249-DETAIL-05_11_2022-GO95MLD-1^07116001.0059800 | OTHER | HFTD Tier 2 | Distribution | 2022-05-11 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002672 | 323277288-5249-DETAIL-05_11_2022-SVCNEUT-1^07116001.0059800 | OTHER | HFTD Tier 2 | Distribution | 2022-05-11 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002673 | 323590333-12059-DETAIL-05_30_2024-GO95HV-1^06246005.0220401 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002674 | 323628881-58881-DETAIL-02_22_2024-GUYHINS-1^07216001.0349702 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002675 | 323673490-74159-DETAIL-05_17_2022-GO95MLD-1^07117001.0319300 | OTHER | Non-HFTD | Distribution | 2022-05-17 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002676 | 32374291-21363-DTLSB-04_29_2024-GO95MLD-1^06245007.0220441 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002677 | 323795488-54982-DETAIL-03_11_2024-GO95HV-1^06245006.0127941 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002678 | 323795488-54982-DETAIL-03_11_2024-GO95MLD-1^06245006.0127941 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002679 | 324103645-91549-DTLSB-05_01_2024-SVCROAD-1^06245007.0220601 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002680 | 324817739-33749-DETAIL-03_21_2023-SVCROOF-1^07113001.0056503 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002681 | 32509753-15049-DETAIL-03_01_2023-GO95MLD-1^07216001.0291706 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002682 | 32509753-15049-DETAIL-03_01_2023-SVCENTCO-1^07216001.0291706 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002683 | 325210046-66489-DETAIL-03_25_2024-GO95MLD-1^06244005.0140300 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002684 | 325301838-29279-DETAIL-03_17_2025-GO95HV-1^06238004.0144200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002685 | 325351211-92211-DETAIL-03_23_2023-GO95HV-1^06142016.0051105 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002686 | 325351211-92211-DETAIL-03_23_2023-GO95MLD-1^06142016.0051105 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002687 | 325415581-51770-DETAIL-04_15_2024-GO95MLD-1^06145001.0249801 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002688 | 325555928-94169-DTLTRT-10_11_2023-GO95HV-1^668010/00 14/043 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002689 | 325555928-94169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 14/043 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002690 | 374166758-49420-DTLSB-02_02_2023-GRDRODHI-1^06247001.0010500 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002691 | 374697299-72720-DETAIL-04_11_2024-GO95MLD-1^06245002.0143700 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002692 | 374998653-18920-DTLSB-03_28_2022-POLETOP-1^06144006.0153101 | POLE | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002693 | 375144486-87879-DTLSB-09_05_2024-GO95HV-1^06245007.0236603 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002694 | 375355381-10481-DETAIL-01_30_2025-SVCDEFLC-1^06240004.0162706 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002695 | 375390840-45669-DETAIL-06_20_2023-GO95HV-1^06244009.0362308 | OTHER | HFTD Tier 2 | Distribution | 2023-06-20 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002696 | 375498814-15320-DETAIL-04_17_2024-GO95MLD-1^06144001.0122301 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002697 | 375840321-22523-DETAIL-06_19_2024-GO95HV-1^06246006.0139901 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002698 | 376309648-2470-DETAIL-02_26_2025-GO95BLTC-1^06240004.0061402 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002699 | 376316589-99449-DETAIL-02_19_2024-GO95MLD-1^07113002.0186003 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002700 | 376316589-99449-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0186003 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002701 | 376473136-80169-DTLTRT-10_12_2023-GO95MLD-1^668010/00 6/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002702 | 376482104-6749-DTLSB-02_21_2024-SVCROAD-1^07216001.0260703 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002703 | 376553018-46190-DETAIL-01_28_2025-SVCENTCO-1^06239004.0244410 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002704 | 376887788-42059-DETAIL-02_27_2025-BIRDDMG-1^06240004.0131101 | POLE | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002705 | 37723724-62230-DETAIL-10_25_2024-SVCNEUT-1^07216001.0208706 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002706 | 377810636-33709-DETAIL-03_28_2024-GO95TCH-1^06147005.0147700 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002707 | 377931193-5379-DETAIL-08_20_2024-GO95MLD-1^06246005.0243100 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002708 | 378102533-79679-DETAIL-02_24_2025-GO95TCH-1^06240004.0154900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002709 | 378159668-44639-DETAIL-10_08_2024-CLRTOUCH-1^07216001.0202109 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002710 | 37832779-25750-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/064 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002711 | 378571548-97620-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002712 | 378850066-29060-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002713 | 378850066-53880-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002714 | 379151031-29180-DETAIL-03_18_2025-GO95HV-1^06239001.0058702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002715 | 325747100-52649-DETAIL-03_16_2023-GO95MLD-1^07113001.0044601 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002716 | 325978155-30070-DETAIL-04_23_2024-POLISSUE-1^06145001.0035302 | POLE | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002717 | 32610481-85130-DTLTRT-10_05_2023-GUYHINS-1^668010/00 11/028 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002718 | 3262142-92142-DETAIL-02_22_2023-GO95TCH-1^07216001.0287806 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002719 | 32654989-30449-DETAIL-06_03_2024-GO95HV-1^06246006.0359000 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002720 | 326594073-9380-DETAIL-02_13_2025-SVCDEFLC-1^06240004.0168200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002721 | 326633230-12459-DETAIL-07_23_2024-BIRDDMG-1^06245007.0316901 | POLE | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002722 | 327325305-90672-DETAIL-06_06_2023-GO95HV-1^06244010.0344501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002723 | 327390984-51962-DETAIL-07_24_2024-GO95MLD-1^06244005.0229601 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002724 | 327430976-2050-ADMIN-03_27_2025-POLEDERP-1^668014/00 2/048 | POLE | HFTD Tier 3 | Transmission | 2025-03-27 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002725 | 327430976-92840-ADMIN-03_27_2025-POLEDERP-1^668014/00 2/048 | POLE | HFTD Tier 3 | Transmission | 2025-03-27 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002726 | 328025421-21209-DTLSB-08_28_2024-GO95HV-1^06245007.0116402 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002727 | 328064671-8749-DETAIL-03_26_2024-GO95HV-1^07113001.0139206 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002728 | 328064671-8749-DETAIL-03_26_2024-GO95MLD-1^07113001.0139206 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002729 | 328064671-8749-DETAIL-03_26_2024-SVCDEFLC-1^07113001.0139206 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002730 | 328081649-9149-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0185100 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002731 | 328149738-34569-DETAIL-07_29_2024-SVCDEFLC-1^06245006.0115800 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002732 | 328258788-85888-DETAIL-02_29_2024-GO95HV-1^07113001.0106302 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002733 | 328527056-150-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 7/049 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002734 | 328776236-17279-DTLSB-08_24_2023-GO95MLD-1^06243009.0118601 | OTHER | Non-HFTD | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002735 | 329335790-96789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153000 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002736 | 329356333-73749-DETAIL-03_21_2023-GO95BLTC-1^07113001.0056600 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002737 | 329366836-15570-ADMIN-01_15_2025-GO95CL10-1^06239004.0256207 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002738 | 329366836-15570-DETAIL-01_15_2025-GO95HV-1^06239004.0256207 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002739 | 329460071-15270-DTLSB-02_08_2024-SVCROAD-1^07216001.0197100 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002740 | 379275255-38361-DETAIL-02_24_2025-GO95MLD-1^06239004.0366604 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002741 | 379275255-38361-DETAIL-02_24_2025-SVCDEFLC-1^06239004.0366604 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002742 | 379493881-32920-DETAIL-03_06_2025-GO95BLTC-1^06240004.0272703 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002743 | 379722419-99589-DTLSB-09_04_2024-GO95MLD-1^06245007.0016700 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002744 | 379803015-28533-ADMIN-08_17_2022-POLEREPL-1^06247004.0076540 | POLE | Non-HFTD | Distribution | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002745 | 3803328-73923-DETAIL-03_20_2023-GUYHINS-1^07117004.0061800 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002746 | 38038681-37380-DETAIL-03_20_2025-GO95HV-1^06239002.0030401 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002747 | 380888403-35529-DTLSB-08_31_2023-GO95HV-1^06243007.0293601 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002748 | 380891716-61800-DETAIL-03_26_2025-SVCDEFLC-1^06239003.0018702 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002749 | 381040557-6690-DETAIL-01_30_2025-GO95HV-1^06239004.0245505 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002750 | 381125463-76230-DTLSB-05_23_2024-GO95MLD-1^06243001.0238901 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002751 | 381276728-17728-DETAIL-05_10_2022-GO95TCH-1^07116001.0059342 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002752 | 381531652-55652-DETAIL-10_21_2024-GO95TCH-1^07216001.0209540 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002753 | 381531652-55652-DETAIL-10_21_2024-SVCENTCO-1^07216001.0209540 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002754 | 381777815-32870-DETAIL-01_24_2025-GO95HV-1^06239004.0258740 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002755 | 381874628-38730-DTLSB-05_14_2024-GO95HV-1^06244001.0218401 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002756 | 381874628-38730-DTLSB-05_14_2024-GO95MLD-1^06244001.0218401 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002757 | 381882136-68730-ADMIN-07_14_2020-ENCHRW-1^06246001.0176403 | OTHER | Non-HFTD | Distribution | 2020-07-14 | 2023-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002758 | 382369550-48170-DETAIL-03_19_2025-GO95HV-1^06239002.0014600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002759 | 382441591-32080-DETAIL-03_19_2025-GO95HV-1^06239001.0053702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002760 | 382467928-16929-DTLSB-08_08_2023-SVCROAD-1^06243009.0155600 | OTHER | HFTD Tier 2 | Distribution | 2023-08-08 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002761 | 382641121-75121-DETAIL-03_28_2023-GO95MLD-1^06142016.0053007 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002762 | 382654526-67230-DTLSB-05_14_2024-GO95MLD-1^06244001.0295700 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002763 | 382917519-50959-DETAIL-02_19_2025-GO95CL10-1^06240004.0219901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002764 | 382991271-26479-DETAIL-03_05_2024-GUYHINS-1^06147004.0022500 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002765 | 330047104-32470-DTLSB-01_30_2023-CONDCOIL-1^06248001.0259101 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002766 | 330164378-29799-DTLSB-10_03_2024-GO95MLD-1^06245007.0218602 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002767 | 330748439-75330-DETAIL-01_14_2025-GRDRODHI-1^06240004.0079904 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002768 | 331313048-93048-DETAIL-10_10_2024-SVCENTBK-1^07216001.0201270 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002769 | 331362366-2423-DTLSB-04_29_2024-GO95MLD-1^06245007.0221641 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002770 | 331362366-2423-DTLSB-04_29_2024-GUYHINS-1^06245007.0221641 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002771 | 331728904-54629-DTLSB-09_07_2023-GO95HV-1^06243008.0128000 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002772 | 331807011-78439-DETAIL-07_18_2024-GO95HV-1^06244004.0056201 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002773 | 33190526-29389-DETAIL-06_04_2024-CLRTOUCH-1^06246006.0366002 | CONDUCTOR | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002774 | 33190526-29389-DETAIL-06_04_2024-COVCFRAY-1^06246006.0366002 | CONDUCTOR | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002775 | 33190526-29389-DETAIL-06_04_2024-GO95MLD-1^06246006.0366002 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002776 | 332003981-59869-DETAIL-06_10_2024-GO95HV-1^06245007.0349000 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002777 | 332039485-88123-DTLSB-05_06_2024-GO95MLD-1^06245007.0221701 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002778 | 332442599-20973-DETAIL-03_08_2023-GO95MLD-1^07117002.0206704 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002779 | 332442599-20973-DETAIL-03_08_2023-GUYHINS-1^07117002.0206704 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002780 | 333239961-71061-DETAIL-03_27_2023-GO95MLD-1^06142016.0052202 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002781 | 333368014-53080-DTLSB-05_09_2024-GO95MLD-1^06244001.0114900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002782 | 333726789-87899-DETAIL-01_26_2023-GO95TCH-1^06148003.0206401 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002783 | 334186101-40829-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0122100 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002784 | 334662651-88889-DETAIL-07_16_2024-SVCWIND-1^06245007.0309402 | OTHER | HFTD Tier 2 | Distribution | 2024-07-16 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002785 | 335026794-25180-DTLSB-05_06_2024-GO95HV-1^06243003.0096403 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002786 | 335026794-25180-DTLSB-05_06_2024-GO95MLD-1^06243003.0096403 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002787 | 335238003-62152-DETAIL-06_26_2023-GO95MLD-1^06244009.0302802 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002788 | 335250706-93689-DETAIL-08_08_2024-GRDRODHI-1^06245006.0099140 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002789 | 335403848-1350-DETAIL-03_20_2025-GO95HV-1^06239003.0016200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002790 | 383066232-77109-DTLSB-08_26_2024-GO95MLD-1^06245007.0114302 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002791 | 383171044-90099-ADMIN-07_20_2023-POLEREPL-1^06240009.0029900 | POLE | Non-HFTD | Distribution | 2023-07-20 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002792 | 383836604-94759-DETAIL-06_04_2024-GO95HV-1^06246005.0310401 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002793 | 384495985-23330-DTLSB-05_13_2024-GO95MLD-1^06244001.0109200 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002794 | 384923354-92479-DETAIL-07_03_2024-GO95MLD-1^06244005.0235842 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002795 | 384923354-92479-DETAIL-07_03_2024-GRDRODHI-1^06244005.0235842 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002796 | 384988771-76530-DETAIL-04_15_2024-GO95MLD-1^06145001.0139300 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002797 | 385099209-15630-DETAIL-04_11_2024-GO95HV-1^06245002.0109503 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002798 | 385177378-1550-DETAIL-04_19_2023-GUYHINS-1^06240004.0164846 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-04-19 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002799 | 38579092-46830-DTLSB-02_16_2023-GO95MLD-1^06248001.0288000 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002800 | 385934198-48330-DETAIL-04_16_2024-GO95MLD-1^06145001.0129200 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002801 | 385996515-15870-DETAIL-01_16_2025-SVCDEFLC-1^06239004.0256211 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002802 | 385996515-15870-DETAIL-01_16_2025-SVCENTBK-1^06239004.0256211 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002803 | 386086229-45430-DETAIL-05_02_2024-GO95HV-1^06142012.0126104 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002804 | 386409084-50630-DTLSB-02_13_2023-GO95MLD-1^06248001.0276740 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002805 | 386838534-54930-DTLSB-05_08_2024-GO95MLD-1^06245001.0335400 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002806 | 387456382-26240-DETAIL-05_13_2024-SVCDEFLC-1^06142012.0124404 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002807 | 388019633-61189-DTLSB-07_26_2023-GO95MLD-1^06243009.0055000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002808 | 388019633-61189-DTLSB-07_26_2023-GRDRODHI-1^06243009.0055000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002809 | 388019633-61189-DTLSB-07_26_2023-GRDRODHI-2^06243009.0055000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002810 | 388221771-33679-DETAIL-03_11_2024-GO95MLD-1^06147004.0039702 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002811 | 388254953-40740-ADMIN-02_09_2024-POLEREPL-1^06144006.0153100 | POLE | Non-HFTD | Distribution | 2024-02-09 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002812 | 388511333-58779-DETAIL-06_07_2023-GO95MLD-1^06244010.0275502 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002813 | 388615603-84569-DTLTRT-10_02_2023-GO95BLTC-1^668010/00 4/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002814 | 388615603-84569-DTLTRT-10_02_2023-GO95HV-1^668010/00 4/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002815 | 335869638-78490-AUDIT-02_25_2025-SVCROAD-1^06239004.0244307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002816 | 335869638-78490-DETAIL-01_28_2025-SVCENTCO-1^06239004.0244307 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002817 | 335920711-25469-DTLTRT-07_20_2022-GO95MLD-1^668005/00 7/054 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002818 | 336300878-51790-DETAIL-01_28_2025-GO95HV-1^06239004.0246043 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002819 | 336332792-30629-DETAIL-05_15_2024-GO95HV-1^06142012.0125805 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002820 | 337217509-67509-DETAIL-01_28_2025-GUYHINS-1^06240004.0171904 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002821 | 337351086-79869-DTLTRT-10_09_2023-GO95MLD-1^668010/00 15/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002822 | 337516513-67839-DETAIL-02_29_2024-GO95HV-1^07113001.0106402 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002823 | 337714979-31759-DTLSB-02_05_2024-GO95MLD-1^07216001.0192940 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002824 | 337868393-48759-DTLSB-02_16_2024-GO95HV-1^07216001.0271000 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002825 | 338210453-91180-DETAIL-02_22_2023-GO95HV-1^06247002.0031801 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002826 | 338390502-60380-DTLSB-02_13_2023-GO95HV-1^06248001.0277001 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002827 | 33846231-55750-DETAIL-01_24_2025-GO95HV-1^06239004.0258501 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002828 | 338714504-58081-DTLSB-07_25_2023-ENCHRW-1^06243009.0054400 | OTHER | HFTD Tier 2 | Distribution | 2023-07-25 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002829 | 338857411-52709-DETAIL-11_08_2022-GRDRODHI-1^06246008.0057501 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002830 | 338918142-86780-DETAIL-03_22_2023-SVCWIND-1^06240004.0167341 | OTHER | HFTD Tier 2 | Distribution | 2023-03-22 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002831 | 339822634-64080-DTLSB-02_20_2023-GO95MLD-1^06248001.0284601 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002832 | 339910316-2989-DETAIL-10_24_2022-GO95MLD-1^06247008.0315201 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002833 | 340246864-93280-DTLTRT-02_06_2024-SVCNEUT-1^07216001.0309907 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002834 | 340260784-55719-DTLTRT-08_17_2022-GO95MLD-1^668005/00 8/094 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002835 | 340311010-12809-ADMIN-01_29_2025-POLEREPL-1^06245007.0106900 | POLE | HFTD Tier 2 | Distribution | 2025-01-29 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002836 | 340567449-42509-DTLSB-09_03_2024-GO95MLD-1^06245007.0014300 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002837 | 34067098-6249-DETAIL-05_10_2022-GUYHINS-1^07116001.0059404 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002838 | 341063761-29909-AUDIT-06_20_2024-SVCENTCO-1^06245007.0226800 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002839 | 341063761-29909-DTLSB-05_06_2024-GO95TCH-1^06245007.0226800 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002840 | 388615603-84569-DTLTRT-10_02_2023-RISEGRD-1^668010/00 4/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002841 | 3892105-95529-DETAIL-08_07_2024-GO95HV-1^06245008.0229301 | OTHER | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002842 | 390160032-84139-DETAIL-05_15_2024-GO95MLD-1^06142012.0125806 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002843 | 39030379-55769-DETAIL-05_22_2023-GO95MLD-1^06245005.0272100 | OTHER | Non-HFTD | Distribution | 2023-05-22 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002844 | 390509450-21550-DETAIL-02_24_2025-BIRDDMG-1^06240004.0150902 | POLE | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002845 | 390516191-55179-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192903 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002846 | 390911834-19849-DTLSB-04_10_2024-SVCWIND-1^06245007.0226009 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002847 | 390948740-86201-DETAIL-01_31_2025-GO95HV-1^06239004.0136217 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002848 | 390965729-20640-DETAIL-04_11_2024-GO95HV-1^06245002.0102200 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002849 | 391094623-99629-DTLSB-09_28_2023-GO95HV-1^06243008.0112900 | OTHER | HFTD Tier 2 | Distribution | 2023-09-28 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002850 | 391808933-4519-ADMIN-05_20_2021-POLETOP-1^668005/00 14/093 | POLE | Non-HFTD | Transmission | 2021-05-20 | 2024-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002851 | 391822453-72140-DTLSB-05_22_2024-GO95MLD-1^06243001.0103701 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002852 | 392687578-34343-DETAIL-03_09_2023-GO95TCH-1^07117002.0209104 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002853 | 392753088-24269-DTLSB-10_03_2024-GO95MLD-1^06245007.0218600 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002854 | 392991571-51380-DETAIL-03_20_2025-GO95HV-1^06239002.0048400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002855 | 393064171-11840-DETAIL-04_15_2024-GO95MLD-1^06145001.0246900 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002856 | 393087418-12170-DETAIL-02_26_2025-BIRDDMG-1^06240004.0062103 | POLE | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002857 | 393091148-81840-DTLSB-02_14_2024-SVCENTCO-1^07216001.0198240 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002858 | 393214181-46629-DETAIL-05_09_2024-GO95MLD-1^06142012.0121406 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002859 | 39335163-61049-DETAIL-02_29_2024-GO95MLD-1^07113001.0159903 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002860 | 39335163-61049-DETAIL-02_29_2024-GO95TCH-1^07113001.0159903 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002861 | 393430788-11249-DETAIL-10_24_2024-GO95MLD-1^07216001.0200401 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002862 | 393559920-8609-DETAIL-11_02_2022-GO95HV-1^06246008.0106700 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002863 | 393995066-63660-DTLTRT-10_09_2023-GO95MLD-1^668010/00 5/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002864 | 394063236-95359-DETAIL-03_28_2024-GO95MLD-1^06247005.0341202 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002865 | 341247693-71839-DETAIL-07_11_2024-GO95HV-1^06244005.0260200 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002866 | 341532538-48069-DETAIL-06_30_2022-GO95HV-1^668005/00 2/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002867 | 341703798-43543-DTLSB-04_30_2024-GO95MLD-1^06245007.0221846 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002868 | 341937059-68059-DETAIL-06_28_2022-GO95MLD-1^668005/00 3X/026 | OTHER | Non-HFTD | Transmission | 2022-06-28 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002869 | 341955554-87260-ADMIN-08_05_2024-GO95STUB-1^06239004.0255701 | OTHER | HFTD Tier 3 | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002870 | 341955554-87260-DETAIL-01_22_2025-GO95HV-1^06239004.0255701 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002871 | 342045892-2380-DTLSB-05_22_2024-GO95MLD-1^06243001.0111200 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002872 | 34231511-32989-DTLSB-09_05_2023-GO95MLD-1^06243008.0094200 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002873 | 342516373-22960-DETAIL-01_15_2025-SVCDEFLC-1^06240004.0098144 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002874 | 342681837-3938-DETAIL-04_03_2024-GO95MLD-1^06246005.0030500 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002875 | 342732473-73669-DTLTRT-10_16_2023-GO95HV-1^668010/00 15/002 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002876 | 342739996-40096-DETAIL-06_12_2024-GO95HV-1^06244005.0247800 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002877 | 34280515-80129-DETAIL-07_07_2023-GRDRODHI-1^06244008.0338200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002878 | 342984230-67809-DTLSB-09_05_2024-GO95MLD-1^06245007.0049100 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002879 | 343252448-96670-DETAIL-02_04_2025-SVCDEFLC-1^06240004.0169503 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002880 | 343375588-87739-DETAIL-10_15_2024-GO95MLD-1^07216001.0201409 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002881 | 343737919-5590-DETAIL-04_24_2024-GO95MLD-1^06145001.0052301 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002882 | 343937712-91459-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0146000 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002883 | 343937712-91459-DETAIL-02_21_2024-SVCENTCO-1^07113001.0146000 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002884 | 344004245-35310-DETAIL-03_13_2025-GO95HV-1^06238004.0224902 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002885 | 344113746-13859-DETAIL-03_27_2024-GO95HV-1^06247005.0324501 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002886 | 344316764-43630-DETAIL-02_25_2025-SVCDEFLC-1^06241005.0254301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002887 | 344433398-41039-DTLSB-02_15_2024-GO95MLD-1^07216001.0190700 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002888 | 344626024-72090-DETAIL-02_09_2023-GO95HV-1^06146004.0162900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002889 | 34489383-48599-DETAIL-10_26_2022-GO95MLD-1^06246009.0128806 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002890 | 394807678-7840-DETAIL-04_16_2024-GO95MLD-1^06145001.0129504 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002891 | 395051806-89123-DTLSB-04_29_2024-GO95MLD-1^06245007.0221644 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002892 | 395090414-19690-DETAIL-01_15_2025-SVCROAD-1^06240004.0099300 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002893 | 395330571-60759-AUDIT-07_17_2024-GO95STUB-1^06246006.0239400 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002894 | 395444626-30649-DTLSB-02_08_2024-GO95MLD-1^07216001.0309906 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002895 | 3956503-77589-DETAIL-03_06_2024-SVCWIND-1^06245007.0275403 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002896 | 395711273-46180-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0165402 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002897 | 395931734-24079-DETAIL-07_31_2024-GO95MLD-1^06245004.0060801 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002898 | 396272208-13259-DTLSB-02_08_2024-SVCENTCO-1^07216001.0197004 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002899 | 396325440-56440-DETAIL-06_17_2024-GO95HV-1^06246006.0131500 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002900 | 396695053-13811-DTLTRT-04_16_2024-GO95HV-1^668067/00 1/013 | OTHER | Non-HFTD | Transmission | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002901 | 396903708-17350-DETAIL-03_26_2025-GO95TCH-1^06239003.0018308 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002902 | 396941732-44009-DETAIL-04_09_2024-GO95MLD-1^06147005.0218602 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002903 | 397062812-15812-DETAIL-04_02_2024-GO95MLD-1^06247005.0340101 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002904 | 397580970-75339-DTLSB-09_01_2022-GO95MLD-1^06243004.0234500 | OTHER | Non-HFTD | Distribution | 2022-09-01 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002905 | 397831568-60850-DTLSB-05_15_2024-GO95HV-1^06244002.0215700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002906 | 398308496-64990-DETAIL-02_11_2025-GO95MLD-1^06240004.0355000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002907 | 398308496-64990-DETAIL-02_11_2025-GO95STUB-1^06240004.0355000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002908 | 39852152-78099-DETAIL-01_29_2019-GO95MLD-1^06147004.0350401 | OTHER | Non-HFTD | Distribution | 2019-01-29 | 2022-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002909 | 39852152-78099-DETAIL-01_29_2019-GRDRODHI-1^06147004.0350401 | OTHER | Non-HFTD | Distribution | 2019-01-29 | 2022-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002910 | 39852152-78099-DETAIL-03_14_2024-GUYHINS-1^06147004.0350401 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002911 | 398844888-55150-DETAIL-03_18_2024-XARMSPCR-1^06245002.0033900 | CROSSARM | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002912 | 39947428-85830-DETAIL-04_10_2024-GO95MLD-1^06245002.0114200 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002913 | 399901221-61769-DTLTRT-10_05_2023-GO95MLD-1^668010/00 1/028 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002914 | 400029743-66050-DTLSB-05_23_2024-GO95MLD-1^06243001.0149100 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002915 | 345020159-30390-DRONE_VS-11_13_2024-BIRDDMG-1^668038/00 1/065 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002916 | 345124901-38390-DETAIL-04_18_2024-GO95HV-1^06145001.0239901 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002917 | 345302649-56299-DETAIL-03_11_2024-GO95MLD-1^06147004.0014903 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002918 | 345737782-90790-DETAIL-05_02_2022-GO95MLD-1^07116001.0100101 | OTHER | HFTD Tier 2 | Distribution | 2022-05-02 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002919 | 345809261-91950-DETAIL-03_24_2025-SVCDEFLC-1^06238004.0029501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002920 | 345952881-76349-DETAIL-02_20_2024-GO95MLD-1^07113002.0181004 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002921 | 346111162-34880-DETAIL-02_12_2025-ANCHIDLE-1^06240004.0166401 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002922 | 34619535-49449-DTLSB-04_24_2024-GO95MLD-1^06245007.0223600 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002923 | 346221353-41050-DETAIL-01_23_2025-GO95MLD-1^06239004.0256802 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002924 | 346480606-6399-DTLSB-09_05_2024-GO95MLD-1^06245007.0238701 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002925 | 3466738-16459-DETAIL-06_03_2024-GO95MLD-1^06246005.0314400 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002926 | 34761884-32884-DETAIL-03_11_2025-CONDCOIL-1^06238004.0271700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002927 | 347817019-40079-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0134600 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002928 | 347990824-85449-DTLSB-02_26_2024-GO95MLD-1^07216001.0276901 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002929 | 34799743-57949-DETAIL-10_22_2024-GO95MLD-1^07216001.0208900 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002930 | 348175063-46069-DTLSB-10_01_2024-SVCROAD-1^06245007.0218205 | OTHER | Non-HFTD | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002931 | 348230547-23547-DTLSB-02_27_2024-GO95HV-1^07216001.0273808 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002932 | 348322238-73239-DETAIL-03_20_2024-GO95BLTC-1^06244005.0141040 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002933 | 348322238-73239-DETAIL-03_20_2024-GO95HV-1^06244005.0141040 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002934 | 34853713-68739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276307 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002935 | 348689838-97169-DTLTRT-10_10_2023-GO95HV-1^668010/00 15/044 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002936 | 348806223-83190-DTLSB-02_14_2023-GO95MLD-1^06248001.0347601 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002937 | 34897685-6230-DTLSB-05_13_2024-GO95MLD-1^06244001.0109300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002938 | 349608800-24690-AUDIT-03_06_2023-SVCRUBLG-1^07216001.0298909 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002939 | 349608800-24690-DETAIL-02_23_2023-GO95MLD-1^07216001.0298909 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002940 | 349608800-24690-DETAIL-02_23_2023-SVCNEUT-1^07216001.0298909 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002941 | 400089773-63434-DETAIL-05_01_2024-GO95HV-1^06143015.0338601 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002942 | 400089773-63434-DETAIL-05_01_2024-GUYLOINS-1^06143015.0338601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002943 | 40020358-31930-DETAIL-03_28_2024-GO95MLD-1^06147005.0169901 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002944 | 400388271-79729-DTLSB-09_28_2023-GO95HV-1^06243008.0103600 | OTHER | HFTD Tier 2 | Distribution | 2023-09-28 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002945 | 400479782-99349-DETAIL-10_10_2024-GUYLOINS-1^07216001.0207007 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002946 | 400574089-4350-DETAIL-04_11_2024-GO95MLD-1^06245002.0100101 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002947 | 400633839-53549-DTLSB-04_10_2024-SVCWIND-1^06245007.0224003 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002948 | 400640304-96132-DETAIL-03_06_2025-GRDRODHI-1^06241005.0120502 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002949 | 40070728-12760-ADMIN-08_14_2024-BIRDDMG-1^668018/00 8/003 | POLE | HFTD Tier 2 | Transmission | 2024-08-14 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002950 | 400796143-72550-DETAIL-03_06_2023-GO95MLD-1^07117002.0205207 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002951 | 400814145-42550-DTLSB-05_08_2024-GO95MLD-1^06244001.0108500 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002952 | 401049467-74650-DETAIL-03_19_2024-GO95MLD-1^06245002.0123800 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002953 | 401213923-20950-DETAIL-04_06_2023-GO95HV-1^06143014.0236702 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002954 | 401400844-79041-DETAIL-04_03_2025-GO95MLD-1^06241005.0089002 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002955 | 40163476-35859-DETAIL-03_28_2024-GO95HV-1^06247005.0327602 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002956 | 402066675-33749-DETAIL-02_29_2024-GO95MLD-1^07113001.0159900 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002957 | 40222666-88861-DETAIL-02_24_2025-SVCDEFLC-1^06239004.0366903 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002958 | 402252432-5959-DETAIL-05_29_2024-GO95MLD-1^06246005.0179000 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002959 | 402252432-5959-DETAIL-05_29_2024-GRDRODHI-1^06246005.0179000 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002960 | 402552674-68440-DTLTRT-10_04_2023-BIRDDMG-1^668010/00 18/035 | POLE | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002961 | 402760513-38650-DETAIL-05_23_2024-GO95HV-1^06243001.0130800 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002962 | 402905961-28349-DETAIL-02_20_2024-GO95MLD-1^07113002.0181008 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002963 | 402905961-28349-DETAIL-02_20_2024-GO95TCH-1^07113002.0181008 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002964 | 402918689-30949-DTLSB-02_15_2024-GO95MLD-1^07216001.0261004 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002965 | 402920936-39379-DETAIL-04_01_2024-CLRTOUCH-1^06147005.0124500 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002966 | 402920936-39379-DETAIL-04_01_2024-GO95MLD-1^06147005.0124500 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002967 | 349835968-90899-DETAIL-07_30_2024-GO95MLD-1^06244005.0355202 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002968 | 349845154-10849-DTLSB-02_07_2024-GO95CLSV-1^07216001.0199300 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002969 | 349845154-10849-DTLSB-02_07_2024-SVCWIND-1^07216001.0199300 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002970 | 349930450-23890-DTLSB-02_16_2024-GO95MLD-1^07216001.0262105 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002971 | 349930450-23890-DTLSB-02_16_2024-SVCROAD-1^07216001.0262105 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002972 | 350071523-29890-DTLSB-03_28_2022-POLETOP-1^06144006.0216900 | POLE | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002973 | 350115474-43753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 3/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002974 | 350115474-8560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 3/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002975 | 350242259-8990-DETAIL-04_11_2024-GO95MLD-1^06245002.0102102 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002976 | 350294799-58170-DETAIL-03_28_2023-RISECLMB-1^06240004.0167549 | OTHER | HFTD Tier 2 | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002977 | 350441839-9169-DTLTRT-06_14_2021-GO95HV-1^668041/00 2/020 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002978 | 350520403-3239-DETAIL-03_14_2023-GO95MLD-1^07114001.0276409 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002979 | 351225890-66759-DETAIL-10_21_2024-GRDRODHI-1^07216001.0201901 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002980 | 35136124-35129-DETAIL-07_12_2023-GO95HV-1^06244008.0289300 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002981 | 35136124-35129-DETAIL-07_12_2023-GO95MLD-1^06244008.0289300 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002982 | 351693001-89849-DETAIL-02_22_2024-GUYLOINS-1^07113001.0092701 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002983 | 351741922-76790-DETAIL-02_08_2023-GO95CL10-1^06146002.0277900 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002984 | 351774945-74449-DETAIL-07_29_2024-GO95MLD-1^06245006.0111902 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002985 | 351948696-76890-DTLSB-01_31_2023-GO95MLD-1^06248001.0367906 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002986 | 3520728-17509-DETAIL-04_10_2024-GO95MLD-1^06245002.0115200 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002987 | 35274483-48559-DTLSB-02_13_2024-GO95TCH-1^07216001.0188100 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002988 | 352827637-99329-DETAIL-05_09_2024-SVCENTCO-1^06142012.0120310 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002989 | 353093026-44899-DTLSB-04_15_2024-SVCWIND-1^06245007.0225109 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002990 | 353184241-45499-DETAIL-01_17_2023-COPLLEAN-1^06148004.0229200 | POLE | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002991 | 353298674-47560-DTLTRT-04_08_2024-BIRDDMG-1^668062/00 2/005 | POLE | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002992 | 402920936-39379-DETAIL-04_01_2024-GRDRODHI-1^06147005.0124500 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002993 | 403044063-44450-AUDIT-03_13_2025-GO95TCH-1^06239004.0134047 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002994 | 403074885-51070-DRONE_VS-11_13_2024-INSULBRK-1^668047/00 4/023 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002995 | 403467809-30789-DETAIL-06_24_2024-GO95MLD-1^06244005.0230001 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002996 | 403633908-66670-DETAIL-02_26_2025-CLRTOUCH-1^06240004.0061001 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-26 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130002997 | 403780456-21271-DETAIL-02_24_2025-GO95BLTC-1^06239004.0367700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002998 | 404050332-39980-DETAIL-02_25_2025-GO95BLTC-1^06240005.0017201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130002999 | 404410731-8089-DETAIL-01_24_2023-CONDFRAY-1^06148003.0241301 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003000 | 40447691-81780-DETAIL-03_19_2025-GO95HV-1^06239001.0061601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003001 | 404864485-67485-DETAIL-02_03_2025-SVCDEFLC-1^06239004.0244702 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003002 | 405037321-27469-DTLTRT-09_25_2023-GRDRODHI-4^668010/00 5/001 | OTHER | Non-HFTD | Transmission | 2023-09-25 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003003 | 405358446-40390-DTLTRT-11_01_2023-GO95HV-1^668010/00 16/018 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003004 | 405472470-76199-DETAIL-06_19_2024-GO95MLD-1^06246006.0263300 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003005 | 405609403-32099-DETAIL-06_13_2023-GO95MLD-1^06243009.0038500 | OTHER | Non-HFTD | Distribution | 2023-06-13 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003006 | 405634836-93560-DTLTRT-10_09_2023-GO95HV-1^668010/00 3/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003007 | 405634836-93560-DTLTRT-10_09_2023-GO95MLD-1^668010/00 3/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003008 | 405837960-61309-DETAIL-03_21_2024-GO95HV-1^06147004.0119701 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003009 | 406171463-92750-DETAIL-10_16_2024-SVCENTCO-1^07216001.0205842 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003010 | 406204828-10770-DETAIL-02_03_2025-GO95HV-1^06240004.0167804 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003011 | 40626528-59870-DETAIL-02_03_2025-SVCNEUT-1^06240004.0166900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003012 | 406397463-71860-DETAIL-01_13_2025-GO95CL10-1^06240004.0073340 | OTHER | HFTD Tier 3 | Distribution | 2025-01-13 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003013 | 406857680-19770-DETAIL-04_12_2023-GO95HV-1^06240004.0166500 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003014 | 406879366-60449-DETAIL-02_23_2023-GO95MLD-1^07216001.0295708 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003015 | 407029498-38789-DETAIL-06_03_2024-GO95MLD-1^06246005.0317901 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003016 | 407085843-914-DTLSB-02_28_2024-SVCWIND-1^07216001.0270600 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003017 | 407392528-21740-DETAIL-03_17_2025-GO95MLD-1^06238004.0143200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003018 | 407513280-5762-DTLSB-07_18_2023-GO95HV-1^06243010.0037602 | OTHER | HFTD Tier 2 | Distribution | 2023-07-18 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003019 | 407513280-5762-DTLSB-07_18_2023-GO95MLD-1^06243010.0037602 | OTHER | HFTD Tier 2 | Distribution | 2023-07-18 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003020 | 407780811-95369-DTLTRT-06_02_2021-GO95HV-1^668041/00 11/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003021 | 408090799-77109-DETAIL-03_06_2024-GO95HV-1^06147004.0017400 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003022 | 408342979-21059-DTLSB-02_28_2024-GO95MLD-1^07216001.0260900 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003023 | 353298674-47560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003024 | 353298674-77560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003025 | 353483896-44280-DETAIL-03_04_2025-SVCROOF-1^06240004.0051001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003026 | 353643394-30049-DETAIL-03_15_2023-GO95MLD-1^07114001.0284201 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003027 | 353659646-23839-DETAIL-10_24_2024-GO95MLD-1^07216001.0200402 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003028 | 353773709-84109-DETAIL-08_20_2024-GO95MLD-1^06245005.0252400 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003029 | 354013324-55440-DETAIL-02_26_2025-BIRDDMG-1^06240004.0219905 | POLE | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003030 | 354293934-56449-DTLSB-04_17_2024-GO95MLD-1^06245007.0224501 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003031 | 354293934-56449-DTLSB-04_17_2024-POLETOP-1^06245007.0224501 | POLE | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003032 | 35446816-75530-DTLSB-05_14_2024-GO95MLD-1^06244001.0280001 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003033 | 354973414-64669-DETAIL-07_15_2024-GO95MLD-1^06244005.0252300 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003034 | 355768306-17538-DETAIL-04_28_2022-GO95MLD-1^07116001.0095300 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003035 | 355959091-22191-DETAIL-03_23_2023-SVCROAD-1^06142016.0051100 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003036 | 356060972-64029-DETAIL-05_08_2024-GO95MLD-1^06142012.0121005 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003037 | 356060972-64029-DETAIL-05_08_2024-GO95TCH-1^06142012.0121005 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003038 | 356237892-76980-DETAIL-02_26_2025-GO95TCH-1^06240005.0019201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003039 | 356237892-76980-DETAIL-02_26_2025-SVCNEUT-1^06240005.0019201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003040 | 356246814-16049-DETAIL-03_20_2023-GO95MLD-1^07114001.0284302 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003041 | 35643020-53730-DETAIL-01_29_2025-SVCDEFLC-1^06240004.0176940 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003042 | 356576830-12839-DTLSB-02_16_2024-SVCENTCO-1^07216001.0263201 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003043 | 356638505-12542-DETAIL-03_05_2025-GO95BLTC-1^06241005.0121200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003044 | 356680064-39899-DETAIL-03_21_2024-GO95HV-1^06147005.0209501 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003045 | 356717214-12149-DETAIL-03_16_2023-GO95MLD-1^07114001.0283308 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003046 | 356717214-12149-DETAIL-03_16_2023-GUYHINS-1^07114001.0283308 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003047 | 35679206-71040-DETAIL-01_23_2025-BIRDDMG-1^06240004.0083304 | POLE | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003048 | 408449173-32519-ADMIN-10_25_2024-POLEREPL-1^668005/00 8/093 | POLE | Non-HFTD | Transmission | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003049 | 408573888-1779-DETAIL-03_19_2024-GO95CL10-1^06245002.0029001 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003050 | 408573888-1779-DETAIL-03_19_2024-GO95MLD-1^06245002.0029001 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003051 | 408785888-87369-DTLTRT-07_06_2022-GO95HV-1^668005/00 5/036 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003052 | 408822305-95659-DETAIL-10_24_2024-GO95MLD-1^07216001.0201600 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003053 | 408979001-71101-DETAIL-03_27_2023-GO95HV-1^06142016.0052700 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003054 | 409291071-86559-DETAIL-04_28_2022-GO95MLD-1^07116001.0094402 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003055 | 409291071-86559-DETAIL-04_28_2022-GO95TCH-1^07116001.0094402 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003056 | 409303138-25999-DETAIL-08_01_2024-GO95MLD-1^06245006.0155103 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003057 | 409461706-95768-ADMIN-10_24_2023-POLEREPL-1^07116001.0096202 | POLE | HFTD Tier 2 | Distribution | 2023-10-24 | 2024-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003058 | 409603842-90713-DTLSB-09_05_2023-GO95MLD-1^06243008.0163901 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003059 | 410245454-32899-AUDIT-03_21_2024-POLETOP-1^06245007.0275707 | POLE | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003060 | 410298734-60629-DTLSB-08_07_2023-GO95MLD-1^06243009.0196401 | OTHER | HFTD Tier 2 | Distribution | 2023-08-07 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003061 | 410682629-11860-DETAIL-04_23_2024-GO95TCH-1^06145001.0112901 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003062 | 41098491-18511-DETAIL-01_21_2025-GO95TCH-1^06239004.0256440 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003063 | 411073864-16864-AUDIT-06_24_2024-GO95HV-1^06142016.0175202 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003064 | 411247054-1040-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/043 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003065 | 411247054-450-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/043 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003066 | 41263240-31579-ADMIN-03_19_2025-POLEREPL-1^06245006.0229000 | POLE | Non-HFTD | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003067 | 412781893-85380-DETAIL-09_12_2024-GO95HV-1^06240004.0099003 | OTHER | HFTD Tier 2 | Distribution | 2024-09-12 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003068 | 412829903-63249-DETAIL-02_20_2024-GO95HV-1^07113002.0183002 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003069 | 356876938-80859-DTLSB-02_13_2024-GO95MLD-1^07216001.0185100 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003070 | 356973354-9100-DETAIL-10_21_2024-GO95MLD-1^07216001.0209706 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003071 | 357272109-64300-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0103300 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003072 | 357318943-16300-DTLSB-05_23_2024-GO95MLD-1^06243001.0149101 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003073 | 357446655-81459-DETAIL-04_01_2024-GO95MLD-1^06247005.0348840 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003074 | 357487201-56500-DTLSB-02_13_2023-GO95MLD-1^06248001.0279000 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003075 | 358064525-75525-DETAIL-05_30_2024-GO95MLD-1^06246005.0220600 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003076 | 358093516-99871-DETAIL-11_14_2022-SVCWIND-1^06239004.0365842 | OTHER | HFTD Tier 2 | Distribution | 2022-11-14 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003077 | 3583480-7270-DETAIL-02_06_2025-GO95TCH-1^06240004.0166305 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003078 | 3583480-7270-DETAIL-03_21_2023-SVCROAD-1^06240004.0166305 | OTHER | HFTD Tier 2 | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003079 | 358396225-40100-DTLSB-05_08_2024-GO95MLD-1^06244001.0106900 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003080 | 358397965-17599-DETAIL-05_24_2023-GO95MLD-1^06245005.0228000 | OTHER | Non-HFTD | Distribution | 2023-05-24 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003081 | 358397965-17599-DETAIL-05_24_2023-SVCNEUT-1^06245005.0228000 | OTHER | Non-HFTD | Distribution | 2023-05-24 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003082 | 35873208-71308-DTLSB-02_22_2023-GO95MLD-1^07216001.0285602 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003083 | 358966183-96930-DETAIL-03_04_2025-GO95MLD-1^06240004.0064700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003084 | 359011693-34659-ADMIN-04_01_2024-GO95STUB-1^07216001.0274900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003085 | 359145173-74150-DETAIL-02_04_2025-BIRDDMG-1^06239004.0134141 | POLE | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003086 | 359621293-903-DETAIL-05_30_2024-GO95HV-1^06246005.0219800 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003087 | 359777726-71449-DTLSB-02_13_2024-GO95HV-1^07216001.0199701 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003088 | 359777726-71449-DTLSB-02_13_2024-GO95MLD-1^07216001.0199701 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003089 | 360032933-46313-DETAIL-02_28_2024-GRDBROKE-1^07215001.0025200 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003090 | 360051845-65009-DTLSB-08_28_2024-SVCDEFLC-1^06245007.0141600 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003091 | 360216001-22632-DETAIL-06_15_2023-GO95MLD-1^06244009.0285000 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003092 | 360305677-44849-DETAIL-03_15_2023-GO95HV-1^07114001.0346301 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003093 | 360364036-39570-DETAIL-01_22_2025-GO95MLD-1^06239004.0256540 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003094 | 413228504-36360-DETAIL-04_18_2024-GO95MLD-1^06145001.0146701 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003095 | 413355611-32339-DETAIL-02_21_2024-GO95MLD-1^07113001.0139205 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003096 | 413494398-45398-DETAIL-01_23_2025-GO95TCH-1^06239004.0256402 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003097 | 413652963-60159-DTLSB-02_15_2024-GO95MLD-1^07216001.0196900 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003098 | 41444069-18830-DETAIL-04_22_2024-GO95MLD-1^06146001.0359101 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003099 | 414629081-19380-DETAIL-03_20_2025-GO95HV-1^06239002.0031402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003100 | 414816413-78899-DETAIL-03_21_2024-GO95MLD-1^06147005.0209801 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003101 | 415467954-66469-DTLTRT-10_02_2023-GO95MLD-1^668010/00 18/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003102 | 415606353-37779-DTLTRT-09_27_2023-GO95HV-1^668010/00 19/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003103 | 415662249-30313-AUDIT-09_03_2024-CONDFRAY-1^06245006.0148740 | CONDUCTOR | Non-HFTD | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003104 | 416092575-52040-DETAIL-02_24_2025-SVCDEFLC-1^06240004.0151804 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003105 | 416106063-80163-DETAIL-04_29_2024-GO95BLTC-1^06142016.0079802 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003106 | 41622163-58279-DETAIL-03_18_2024-GO95MLD-1^06246005.0076101 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003107 | 41632359-33271-DETAIL-02_24_2025-GRDRODHI-1^06241005.0152600 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003108 | 416333438-12009-DETAIL-04_09_2024-SVCROAD-1^06147005.0215802 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003109 | 41634216-39208-DTLSB-09_03_2024-GO95MLD-1^06245007.0124900 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003110 | 41634216-39208-DTLSB-09_03_2024-GRDRODHI-1^06245007.0124900 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003111 | 41634216-39208-DTLSB-09_03_2024-GRDRODHI-2^06245007.0124900 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003112 | 416852571-38730-DTLTRT-10_30_2023-GO95HV-1^668010/00 21/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-30 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003113 | 416965115-55549-ADMIN-04_07_2025-POLEDERP-1^07216001.0157702 | POLE | Non-HFTD | Distribution | 2025-04-07 | 2028-04-30 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130003114 | 416972476-13070-DETAIL-01_24_2025-GO95HV-1^06239004.0258941 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003115 | 360636412-88500-DETAIL-02_08_2023-GO95HV-1^06146002.0276901 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003116 | 360954055-97700-DETAIL-04_22_2024-GO95HV-1^06146001.0361001 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003117 | 36103004-61639-DTLSB-02_14_2024-GO95MLD-1^07216001.0198403 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003118 | 361260351-25709-DETAIL-11_08_2022-GO95TCH-1^06246008.0056400 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003119 | 361667406-60460-DTLTRT-10_09_2023-GUYNOINS-1^668010/00 1A/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003120 | 361974233-92669-DTLTRT-06_04_2021-GO95HV-1^668041/00 8/009 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003121 | 362044152-99431-DETAIL-07_12_2023-GO95MLD-1^06243008.0054800 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003122 | 362274175-69019-DETAIL-04_01_2024-GO95HV-1^06147005.0127501 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003123 | 362277916-94540-DETAIL-02_20_2025-GO95HV-1^06240004.0214600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-20 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003124 | 362291138-49340-DETAIL-03_12_2025-GO95HV-1^06238004.0223300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003125 | 362580034-15749-DTLSB-02_08_2024-GO95MLD-1^07216001.0307907 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003126 | 362960871-95739-DETAIL-02_20_2024-SVCENTCO-2^07113001.0138203 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003127 | 363001009-16530-DETAIL-01_28_2025-GO95CL10-1^06240004.0080003 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003128 | 363136419-249-DETAIL-02_19_2024-SVCENTCO-1^07113002.0185202 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003129 | 363645500-78379-DETAIL-03_05_2024-GO95HV-1^06147004.0025900 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003130 | 363765761-35469-DTLTRT-06_03_2021-GO95HV-1^668041/00 5/007 | OTHER | Non-HFTD | Transmission | 2021-06-03 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003131 | 363960656-78623-DTLSB-04_17_2024-GO95MLD-1^06245007.0220542 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003132 | 36408264-99213-DTLSB-04_25_2024-GO95MLD-1^06245007.0228545 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003133 | 364771469-84310-DTLSB-05_20_2024-GO95HV-1^06244003.0287600 | OTHER | Non-HFTD | Distribution | 2024-05-20 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003134 | 365000745-86549-DETAIL-05_18_2023-GO95HV-1^06245005.0159201 | OTHER | Non-HFTD | Distribution | 2023-05-18 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003135 | 365688657-36970-DETAIL-02_25_2025-GO95CL10-1^06240004.0061109 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003136 | 366376745-65310-DTLSB-05_08_2024-GO95MLD-1^06244001.0107500 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003137 | 366513394-17359-DETAIL-10_16_2024-CLMBTRE-1^07216001.0209804 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003138 | 366695496-94079-DETAIL-04_08_2024-GO95MLD-1^06147005.0232001 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003139 | 366722447-549-DETAIL-10_24_2024-GO95HV-1^07216001.0200400 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003140 | 416974133-39259-DETAIL-05_11_2022-GO95MLD-1^07117001.0326001 | OTHER | Non-HFTD | Distribution | 2022-05-11 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003141 | 417232443-78721-ADMIN-01_17_2025-POLEREPL-1^06241005.0040701 | POLE | HFTD Tier 2 | Distribution | 2025-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003142 | 417526801-67271-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 4/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003143 | 417526801-67271-AUDIT-08_02_2022-SVCROAD-1^668005/00 4/038 | OTHER | Non-HFTD | Transmission | 2022-08-02 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003144 | 417526801-67271-DETAIL-07_06_2022-GO95HV-1^668005/00 4/038 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003145 | 417768965-2929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120409 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003146 | 4178087-29249-DETAIL-03_15_2023-SVCENTCO-1^07114001.0347203 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003147 | 418041579-34479-DTLSB-10_02_2024-SVCENTCO-1^06245007.0217806 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003148 | 418132681-57399-DETAIL-07_24_2024-GO95MLD-1^06244005.0131300 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003149 | 418259079-95949-DETAIL-02_22_2024-SVCDEFLC-1^07216001.0352000 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003150 | 41845934-1044-DETAIL-03_29_2023-GO95MLD-1^06142016.0085501 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003151 | 418540815-76170-DETAIL-10_22_2024-GUYHINS-1^07216001.0207707 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003152 | 41886001-57250-DETAIL-03_24_2025-GRDRODHI-1^06238004.0022802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003153 | 419081827-23859-DETAIL-10_25_2024-GO95MLD-1^07216001.0201400 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003154 | 419210151-70529-DETAIL-06_07_2023-GO95HV-1^06244010.0273803 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003155 | 419225473-39659-ADMIN-04_30_2024-POLEREPL-1^668004/02 2/007 | POLE | Non-HFTD | Transmission | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003156 | 419236908-89459-DETAIL-05_16_2022-GO95MLD-1^07116001.0059200 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003157 | 41926659-90149-DETAIL-10_08_2024-DISTHDWR-1^07216001.0203006 | CONNECTION DEVICE | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003158 | 419336542-67570-DETAIL-02_08_2023-GO95HV-1^06146002.0274700 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003159 | 419367090-2749-DETAIL-02_26_2024-GO95HV-1^07113001.0137400 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003160 | 419367090-2749-DETAIL-02_26_2024-SVCENTCO-1^07113001.0137400 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003161 | 419641825-42770-DETAIL-04_24_2024-GO95HV-1^06145001.0090901 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003162 | 419662504-82770-DTLSB-01_30_2023-GO95MLD-1^06248001.0259100 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003163 | 420755518-8259-DTLSB-02_14_2024-GO95HV-1^07216001.0184300 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003164 | 420814456-98279-DETAIL-01_24_2023-GO95MLD-1^06148004.0182002 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003165 | 367315178-72910-DTLSB-02_02_2023-SVCSVC-1^06247001.0010200 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003166 | 368326158-94379-DETAIL-10_31_2022-GUYHINS-1^06246009.0091700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-10-31 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003167 | 368326158-94379-DETAIL-10_31_2022-GUYHINS-2^06246009.0091700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-10-31 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003168 | 36838305-53140-DETAIL-03_04_2025-GO95TCH-1^06240004.0150501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003169 | 368713435-36910-DTLSB-05_08_2024-GO95HV-1^06244001.0107700 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003170 | 368953627-25079-DTLSB-10_07_2024-GO95MLD-1^06245006.0333300 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003171 | 369903281-49739-DETAIL-02_20_2024-GO95HV-1^07113001.0137300 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003172 | 369903281-49739-DETAIL-02_20_2024-GO95MLD-1^07113001.0137300 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003173 | 370094860-809-DTLSB-07_23_2024-GO95HV-1^06245007.0107500 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003174 | 370298528-68543-DTLSB-04_30_2024-GO95MLD-1^06245007.0220741 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003175 | 370510318-63719-DTLTRT-08_18_2022-GO95HV-1^668005/00 8/098 | OTHER | Non-HFTD | Transmission | 2022-08-18 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003176 | 370520451-16180-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003177 | 370809073-24390-DETAIL-01_29_2025-GO95HV-1^06240004.0178303 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003178 | 371039593-96550-DETAIL-01_16_2025-SVCDEFLC-1^06240004.0096604 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003179 | 371124223-75309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 2/031 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003180 | 371132991-26689-DTLSB-08_17_2023-GO95MLD-1^06243009.0131300 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003181 | 37117746-27746-DETAIL-01_29_2025-GO95MLD-1^06239004.0234000 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003182 | 371215134-22639-DETAIL-03_20_2023-GO95MLD-1^07114001.0282401 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003183 | 371579082-45529-DETAIL-05_09_2024-GUYNOINS-1^06142012.0121407 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003184 | 37170956-40770-DETAIL-01_24_2025-GO95HV-1^06239004.0258843 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003185 | 372041738-32738-DETAIL-07_11_2024-GO95MLD-1^06244005.0219601 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003186 | 372455971-36929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120412 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003187 | 372491118-60239-DETAIL-10_14_2024-SVCNEUT-1^07216001.0201208 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003188 | 372540369-65170-DETAIL-02_03_2025-CLMBHAZ-1^06240004.0167800 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003189 | 372574119-16670-AUDIT-03_04_2025-GO95CL10-1^06240005.0019400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003190 | 420864735-17049-DETAIL-02_26_2024-SVCENTCO-1^07113001.0211500 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003191 | 421161844-3190-DETAIL-03_26_2025-GO95HV-1^06239003.0018505 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003192 | 42138396-18280-DETAIL-02_03_2025-GO95MLD-1^06239004.0244805 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003193 | 421467889-25790-DETAIL-01_28_2025-GO95HV-1^06239004.0244201 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003194 | 421467889-25790-DETAIL-01_28_2025-GO95MLD-1^06239004.0244201 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003195 | 421689588-8999-DETAIL-02_26_2025-BIRDDMG-1^06240004.0150040 | POLE | HFTD Tier 3 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003196 | 421883899-49279-DETAIL-04_01_2024-CLRTOUCH-1^06147005.0107201 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003197 | 421883899-49279-DETAIL-04_01_2024-GO95TCH-1^06147005.0107201 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003198 | 422085546-49670-DETAIL-01_22_2025-GO95HV-1^06239004.0256541 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003199 | 422242131-6949-DTLSB-02_20_2024-GO95MLD-1^07216001.0260400 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003200 | 422253871-13473-DETAIL-03_02_2023-GO95MLD-1^07117002.0201303 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003201 | 422741214-47280-DTLTRT-09_27_2023-GO95MLD-1^668010/00 7/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003202 | 422832427-88099-DTLSB-07_22_2024-SVCDEFLC-1^06245006.0060000 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003203 | 422878189-54670-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355903 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003204 | 42356514-54759-DETAIL-06_04_2024-GO95BLTC-1^06246005.0310300 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003205 | 42356514-54759-DETAIL-06_04_2024-GO95MLD-1^06246005.0310300 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003206 | 423566976-79423-DTLSB-05_02_2024-GO95MLD-1^06245007.0222741 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003207 | 423706611-55670-DETAIL-02_27_2023-RISESTRP-2^07216001.0296708 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003208 | 423746651-49420-DETAIL-03_07_2023-GRDRODHI-1^07117002.0211300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003209 | 423969432-44450-DETAIL-02_06_2025-GO95MLD-1^06239004.0137202 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003210 | 424907943-50080-DETAIL-02_09_2023-GO95MLD-1^06146004.0085002 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003211 | 425000353-65002-DTLTRT-04_15_2024-BIRDDMG-1^668067/00 4/008 | POLE | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003212 | 42508626-84540-DTLSB-01_31_2023-GUYHINS-1^06248001.0367809 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003213 | 425119286-11060-DTLTRT-10_23_2023-GUYNOINS-1^668010/00 18A/042 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003214 | 425119286-11060-DTLTRT-10_23_2023-GUYNOINS-4^668010/00 18A/042 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003215 | 372744261-16261-DETAIL-03_27_2023-ABNDEQPM-1^06142016.0050600 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003216 | 372802988-14720-DETAIL-04_02_2024-GO95MLD-1^06147005.0161900 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003217 | 372802988-14720-DETAIL-04_02_2024-SVCROAD-1^06147005.0161900 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003218 | 372855534-699-DETAIL-03_05_2024-SVCROAD-1^06245007.0275302 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003219 | 373136274-78449-DTLSB-04_23_2024-GUYHINS-1^06245007.0224702 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003220 | 373467235-30310-DETAIL-11_10_2022-GO95HV-1^06238004.0222502 | OTHER | HFTD Tier 2 | Distribution | 2022-11-10 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003221 | 373577588-12688-DTLSB-02_28_2024-SVCDEFLC-1^07216001.0260912 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003222 | 37371054-18139-DTLSB-02_06_2024-GO95MLD-1^07216001.0309901 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003223 | 373724260-75369-ADMIN-08_05_2020-POLEDERP-1^668005/00 10/052 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003224 | 373904599-99699-DETAIL-03_06_2024-GO95HV-1^06147004.0249601 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003225 | 374166758-49420-DTLSB-02_02_2023-GO95MLD-1^06247001.0010500 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003226 | 374407090-7489-DTLSB-08_10_2022-GO95MLD-1^06243004.0287900 | OTHER | Non-HFTD | Distribution | 2022-08-10 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003227 | 374422733-5913-DTLSB-05_02_2024-GO95MLD-1^06245007.0228543 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003228 | 374422733-5913-DTLSB-05_02_2024-SVCWIND-1^06245007.0228543 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003229 | 374543195-6195-DETAIL-06_03_2024-GO95HV-1^06246005.0305000 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003230 | 374998653-18920-DTLSB-03_28_2022-XARMSPCR-1^06144006.0153101 | CROSSARM | Non-HFTD | Distribution | 2022-03-28 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003231 | 375083002-21069-DETAIL-07_01_2024-BIRDDMG-1^06245007.0304400 | POLE | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003232 | 375343966-59659-DETAIL-03_12_2024-ENCHRW-1^06245007.0273902 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003233 | 375387460-69749-AUDIT-09_03_2024-GUYNOINS-1^06245005.0367402 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003234 | 375568993-36169-DTLSB-04_25_2024-SVCWIND-1^06245007.0229501 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003235 | 375794123-79420-DETAIL-05_15_2024-GO95HV-1^06142012.0124703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003236 | 375794123-79420-DETAIL-05_15_2024-GO95MLD-1^06142012.0124703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003237 | 375794123-79420-DETAIL-05_15_2024-GRDRODHI-1^06142012.0124703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003238 | 375831776-90400-DETAIL-03_12_2025-BIRDDMG-1^06239003.0241300 | POLE | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003239 | 375840321-22523-DETAIL-06_19_2024-GO95MLD-1^06246006.0139901 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003240 | 425641596-63679-DETAIL-04_04_2024-GO95HV-1^06147005.0139001 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003241 | 425750624-20939-DTLSB-02_08_2024-GO95MLD-1^07216001.0306901 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003242 | 425781908-64143-DETAIL-03_06_2023-GO95MLD-1^07117002.0207301 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003243 | 425982859-85830-DTLTRT-10_26_2023-GO95HV-1^668010/00 2/023 | OTHER | HFTD Tier 2 | Transmission | 2023-10-26 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003244 | 426097037-95720-DTLTRT-10_24_2023-GO95HV-1^668010/00 4/009 | OTHER | HFTD Tier 2 | Transmission | 2023-10-24 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003245 | 426270348-53779-DTLSB-05_13_2024-COVCFRAY-1^06244001.0153101 | CONDUCTOR | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003246 | 426310278-12043-DTLSB-04_30_2024-GO95MLD-1^06245007.0220941 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003247 | 426363924-53590-DETAIL-03_10_2025-GO95HV-1^06241004.0313200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003248 | 426436061-92773-DETAIL-03_06_2023-ENCHRW-1^07117002.0204200 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003249 | 426769629-70579-DETAIL-06_28_2023-GO95HV-1^06244009.0364300 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003250 | 426980219-40580-DETAIL-02_27_2023-GO95MLD-1^07216001.0294605 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003251 | 426980219-40580-DETAIL-02_27_2023-GO95TCH-1^07216001.0294605 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003252 | 426999161-76284-DETAIL-03_27_2023-GO95BLTC-1^06142016.0050201 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003253 | 427015438-5969-DETAIL-06_28_2022-GO95MLD-1^668005/00 3/026 | OTHER | Non-HFTD | Transmission | 2022-06-28 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003254 | 427078643-94340-DTLTRT-10_02_2023-GO95HV-1^668010/00 9/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003255 | 427130178-36440-DETAIL-03_17_2025-GO95TCH-1^06238004.0145900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003256 | 427188172-43080-DETAIL-02_25_2025-GO95HV-1^06240005.0016103 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003257 | 427295820-78079-DETAIL-03_05_2024-CONDFRAY-1^06147004.0020203 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003258 | 428116512-89829-DTLSB-08_24_2023-GUYNOINS-1^06243008.0172701 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003259 | 428584218-36459-DETAIL-05_10_2022-GUYLOINS-1^07116001.0059401 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003260 | 428786964-27789-DTLSB-07_26_2023-GO95HV-1^06243009.0055703 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003261 | 429233698-75359-DETAIL-05_31_2024-GO95MLD-1^06246005.0327401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003262 | 42960498-64139-DETAIL-03_25_2024-GO95MLD-1^06244005.0146241 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003263 | 429687761-89150-DETAIL-03_24_2025-XARMSPCR-1^06238004.0028601 | CROSSARM | HFTD Tier 2 | Distribution | 2025-03-24 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003264 | 429687761-89150-DETAIL-03_24_2025-XARMSPCR-2^06238004.0028601 | CROSSARM | HFTD Tier 2 | Distribution | 2025-03-24 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003265 | 376242584-10820-DTLTRT-11_01_2023-GUYNOINS-1^668010/00 18A/017 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-01 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003266 | 376309648-2470-DETAIL-02_26_2025-GO95HV-1^06240004.0061402 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003267 | 376316589-99449-DETAIL-02_19_2024-SVCDEFLC-2^07113002.0186003 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003268 | 376448404-5159-DETAIL-03_16_2023-GO95MLD-1^07113001.0044502 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003269 | 376482104-6749-DTLSB-02_21_2024-SVCENTCO-1^07216001.0260703 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003270 | 376553018-46190-DETAIL-01_28_2025-GO95MLD-1^06239004.0244410 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003271 | 376564181-56249-DETAIL-05_16_2022-GO95MLD-1^07116001.0090801 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003272 | 376564181-56249-DETAIL-05_16_2022-SVCNEUT-1^07116001.0090801 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003273 | 377590359-71509-DTLSB-09_03_2024-GO95MLD-1^06245007.0015400 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003274 | 377993204-57579-DETAIL-08_12_2020-GO95TCH-1^06246001.0130900 | OTHER | Non-HFTD | Distribution | 2020-08-12 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003275 | 378159668-44639-DETAIL-10_08_2024-GO95CL10-1^07216001.0202109 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003276 | 378159668-44639-DETAIL-10_08_2024-GUYNOINS-1^07216001.0202109 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003277 | 378375593-17593-DETAIL-03_11_2025-GO95HV-1^06238004.0274904 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003278 | 378480644-63644-DETAIL-02_06_2023-GO95CL10-1^06147002.0162102 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003279 | 378480644-63644-DETAIL-02_06_2023-GO95MLD-1^06147002.0162102 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003280 | 378546542-57769-DTLTRT-10_03_2023-GO95HV-1^668010/00 14/030 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003281 | 378850066-24880-DRONE_HY-10_12_2023-GO95HV-1^668033/00 1/047 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003282 | 379228496-59859-DETAIL-04_02_2024-GO95MLD-1^06247005.0354800 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003283 | 379474805-39379-DETAIL-10_24_2022-GO95MLD-1^06247008.0315305 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003284 | 379660306-21169-DTLTRT-10_12_2023-GO95HV-1^668010/00 3/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003285 | 379793100-28789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223901 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003286 | 379832404-66779-DTLSB-07_26_2023-GO95MLD-1^06243009.0056000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003287 | 37987634-33675-DETAIL-03_29_2023-GO95TCH-1^06142016.0085602 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003288 | 380397813-17830-ADMIN-10_27_2023-POLEREPL-1^06144006.0218900 | POLE | Non-HFTD | Distribution | 2023-10-27 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003289 | 380593799-12769-DETAIL-03_26_2024-GO95MLD-1^06246005.0053300 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003290 | 430123014-24940-DETAIL-02_19_2025-BIRDDMG-1^06240004.0218707 | POLE | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003291 | 430487223-31839-DETAIL-07_05_2024-GO95HV-1^06244005.0018400 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003292 | 430851376-1840-DETAIL-01_28_2025-BIRDDMG-1^06240004.0084000 | POLE | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003293 | 430988854-10653-DTLSB-10_01_2024-GO95MLD-1^06245007.0230742 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003294 | 431388547-64859-DETAIL-10_14_2024-SVCDEFLC-1^07216001.0200302 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003295 | 431426942-21749-DETAIL-02_21_2024-GO95MLD-1^07113002.0181103 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003296 | 431742565-28480-DETAIL-04_24_2024-GO95MLD-1^06145001.0090900 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003297 | 431851220-80249-DTLSB-02_20_2024-GO95MLD-1^07216001.0263306 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003298 | 432074163-34980-DETAIL-03_18_2025-ABNDEQPM-1^06239002.0070500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003299 | 432074163-34980-DETAIL-03_18_2025-GUYHINS-1^06239002.0070500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003300 | 432227390-24159-DETAIL-05_17_2022-GO95MLD-1^07117001.0319301 | OTHER | Non-HFTD | Distribution | 2022-05-17 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003301 | 432238114-14749-DTLSB-02_27_2024-GO95MLD-1^07216001.0278905 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003302 | 432934463-27659-DTLSB-02_14_2024-GO95MLD-1^07216001.0180201 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003303 | 432975929-61339-DETAIL-07_11_2024-GO95MLD-1^06244005.0279401 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003304 | 432988055-21849-DETAIL-02_22_2024-GO95HV-1^07113001.0157200 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003305 | 433011066-83479-DETAIL-04_03_2024-GO95MLD-1^06147005.0232700 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003306 | 433011066-83479-DETAIL-04_03_2024-SVCENTCO-1^06147005.0232700 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003307 | 433070803-42779-AUDIT-02_16_2023-ABNDEQPM-1^06148004.0210800 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003308 | 43318828-28828-DETAIL-10_22_2024-GO95TCH-1^07216001.0208040 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003309 | 43337213-43660-DETAIL-01_14_2025-SVCENTCO-1^06240004.0097142 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003310 | 380633311-50252-DETAIL-06_26_2023-GO95HV-1^06244009.0310602 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003311 | 381114881-7389-DTLSB-08_28_2024-GRDRODHI-1^06245007.0116700 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003312 | 381287700-44939-DTLSB-02_20_2024-SVCROAD-1^07216001.0262307 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003313 | 38150590-77632-DETAIL-06_15_2023-GO95HV-1^06244009.0338101 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003314 | 381589150-64880-DETAIL-02_10_2025-CONDCOIL-1^06239003.0071903 | OTHER | HFTD Tier 3 | Distribution | 2025-02-10 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003315 | 381703226-20730-DETAIL-02_20_2023-CONDFRAY-1^06247002.0297502 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003316 | 381703226-20730-DETAIL-02_20_2023-GO95HV-1^06247002.0297502 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003317 | 381870421-28730-DETAIL-03_13_2024-GO95HV-1^06147004.0084000 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003318 | 382193809-2269-DTLTRT-06_14_2021-GO95HV-1^668041/00 5/021 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003319 | 38224431-14489-DTLSB-09_05_2023-GO95MLD-1^06243008.0089101 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003320 | 382249335-77030-DTLSB-05_08_2024-GO95MLD-1^06245001.0298201 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003321 | 382695370-99-DETAIL-11_02_2022-GO95HV-1^06246008.0052601 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003322 | 382695370-99-DETAIL-11_02_2022-GO95MLD-1^06246008.0052601 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003323 | 382777939-2173-DETAIL-06_29_2023-POLEREPL-1^06247005.0209800 | POLE | Non-HFTD | Distribution | 2023-06-29 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003324 | 382991271-26479-DETAIL-03_05_2024-GO95MLD-1^06147004.0022500 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003325 | 383050459-87959-DTLSB-02_05_2024-GO95MLD-1^07216001.0194940 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003326 | 383066232-77109-DTLSB-08_26_2024-GO95HV-1^06245007.0114302 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003327 | 38332909-20759-DETAIL-03_26_2024-GO95MLD-1^06246005.0058601 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003328 | 38332909-20759-DETAIL-03_26_2024-GRDRODHI-1^06246005.0058601 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003329 | 383394753-20774-DETAIL-03_27_2023-GO95MLD-1^06142016.0081806 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003330 | 384659008-69973-DETAIL-02_26_2025-SVCDEFLC-1^06240004.0219740 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003331 | 384772263-99760-DETAIL-01_14_2025-GO95TCH-1^06240004.0097043 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003332 | 384843302-89359-DETAIL-02_21_2024-GO95HV-1^07113001.0144101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003333 | 384843302-89359-DETAIL-02_21_2024-RISEGRD-1^07113001.0144101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003334 | 384923354-92479-DETAIL-07_03_2024-GRDRODHI-2^06244005.0235842 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003335 | 433478259-99279-DETAIL-01_24_2023-GO95HV-1^06148003.0257601 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003336 | 433587888-81823-DETAIL-03_20_2023-GO95MLD-1^07117003.0016800 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003337 | 434001670-55789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154200 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003338 | 434079704-23839-DTLSB-02_07_2024-GO95MLD-1^07216001.0199306 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003339 | 434104478-85799-DETAIL-06_12_2023-GO95MLD-1^06244009.0365501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003340 | 434104478-85799-DETAIL-06_12_2023-GUYHINS-1^06244009.0365501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003341 | 434634181-28480-DETAIL-02_27_2025-BIRDDMG-1^06240004.0136101 | POLE | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003342 | 434886154-40489-DETAIL-07_17_2024-RISEGRD-1^06244005.0277000 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003343 | 434886154-40489-DETAIL-07_17_2024-RISEGRD-2^06244005.0277000 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003344 | 435225684-93749-DTLSB-02_06_2024-GO95MLD-1^07216001.0308802 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003345 | 435276478-82290-DETAIL-04_22_2024-GO95MLD-1^06145001.0119900 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003346 | 435429493-79550-DETAIL-01_23_2025-GUYHINS-1^06239004.0256909 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003347 | 436067878-45743-DTLSB-04_30_2024-GO95MLD-1^06245007.0221941 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003348 | 436195543-58549-DETAIL-03_14_2023-GO95HV-1^07114001.0275401 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003349 | 436986508-27508-DETAIL-03_17_2025-GO95HV-1^06238004.0111300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003350 | 437288913-44899-DETAIL-07_24_2024-SVCDEFLC-1^06244005.0251001 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003351 | 437364738-18269-DTLTRT-07_05_2022-GO95HV-1^668005/00 4/035 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003352 | 437396776-41089-DETAIL-07_10_2024-GO95MLD-1^06244004.0216500 | OTHER | HFTD Tier 2 | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003353 | 437693294-89790-DTLSB-02_07_2023-GO95HV-1^06248001.0157202 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003354 | 438039618-35120-DTLTRT-10_17_2023-GUYHINS-1^668010/00 5X/009 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003355 | 438039618-35120-DTLTRT-10_17_2023-GUYHINS-2^668010/00 5X/009 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003356 | 438056618-32769-DTLTRT-07_07_2022-UBPBXARM-1^668005/00 3/041 | CROSSARM | Non-HFTD | Transmission | 2022-07-07 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003357 | 438128746-38746-DETAIL-01_29_2025-GO95MLD-1^06239004.0233001 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003358 | 438162054-57680-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003359 | 438162054-76680-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003360 | 385146939-93570-DETAIL-02_13_2025-GO95CL10-1^06240004.0169200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003361 | 385370183-10659-DTLSB-02_13_2024-GO95MLD-1^07216001.0188202 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003362 | 385597165-63160-DTLTRT-11_03_2023-GUYNOINS-1^668010/00 6A/041 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003363 | 385701375-71375-DTLTRT-11_17_2022-GUYHINS-1^668001/00 3X/049 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2022-11-17 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003364 | 385701375-71375-DTLTRT-11_17_2022-GUYHINS-2^668001/00 3X/049 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2022-11-17 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003365 | 385948279-29952-DTLSB-07_17_2023-GO95HV-1^06243010.0119100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003366 | 385994-8032-DETAIL-03_06_2025-ANCHIDLE-1^06241005.0120503 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003367 | 385996515-15870-DETAIL-01_16_2025-SVCROAD-1^06239004.0256211 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003368 | 386041398-76570-DETAIL-01_23_2025-ANCHIDLE-1^06240004.0083303 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003369 | 386094579-79133-DETAIL-03_13_2023-GO95HV-1^07117002.0289602 | OTHER | HFTD Tier 2 | Distribution | 2023-03-13 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003370 | 386141655-52663-DETAIL-04_24_2023-GO95HV-1^07117003.0085200 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003371 | 386329049-42759-DETAIL-04_02_2024-GO95HV-1^06246005.0055300 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003372 | 386593226-46730-DTLSB-05_22_2024-GO95HV-1^06244001.0332800 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003373 | 386638939-24279-DETAIL-04_02_2024-GO95MLD-1^06147005.0102201 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003374 | 386638939-24279-DETAIL-04_02_2024-GO95TCH-1^06147005.0102201 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003375 | 386656305-24763-DETAIL-03_14_2023-GUYHINS-1^07117003.0093000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003376 | 386712940-33122-DETAIL-06_20_2023-SVCDEFLC-1^06244009.0362320 | OTHER | HFTD Tier 2 | Distribution | 2023-06-20 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003377 | 386837351-68411-DETAIL-02_18_2025-GRDRODHI-1^06239004.0362401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003378 | 387289522-22450-DETAIL-01_31_2025-GO95HV-1^06239004.0136300 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003379 | 387289522-22450-DETAIL-01_31_2025-GO95MLD-1^06239004.0136300 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003380 | 387456382-26240-DETAIL-05_13_2024-GO95HV-1^06142012.0124404 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003381 | 387785316-51908-DETAIL-02_19_2025-SVCDEFLC-1^06239004.0363200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003382 | 38792138-15170-DETAIL-01_27_2025-GO95TCH-1^06240004.0081401 | OTHER | HFTD Tier 2 | Distribution | 2025-01-27 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003383 | 388192450-51328-DETAIL-07_30_2024-GO95MLD-1^06244005.0354301 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003384 | 388254953-40740-DTLSB-03_28_2022-GO95HV-1^06144006.0153100 | OTHER | Non-HFTD | Distribution | 2022-03-28 | 2027-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003385 | 438189085-7851-DETAIL-02_24_2025-SVCROAD-1^06239004.0366701 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003386 | 438432192-93569-DTLTRT-06_04_2021-GO95HV-1^668041/00 5/008 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003387 | 439238588-88588-AUDIT-08_06_2024-GO95MLD-1^06245006.0038800 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003388 | 439238588-88588-DETAIL-06_06_2024-ABNDEQPM-1^06245006.0038800 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003389 | 439864466-18319-DETAIL-10_24_2022-GO95HV-1^06247008.0301901 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003390 | 440289785-90139-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295502 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003391 | 441286663-18239-DETAIL-03_14_2023-GO95MLD-1^07114001.0276403 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003392 | 44138736-25049-DTLSB-02_22_2023-GO95MLD-1^07216001.0287700 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003393 | 441659173-66249-DETAIL-03_20_2023-GO95MLD-1^07114001.0206202 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003394 | 441691371-23250-DETAIL-02_11_2025-GO95MLD-1^06239004.0124903 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003395 | 441941135-65199-DETAIL-08_06_2024-GO95STUB-1^06245004.0328700 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003396 | 442237319-68899-DETAIL-03_19_2024-GO95MLD-1^06245002.0053600 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003397 | 442719271-59269-AUDIT-10_09_2023-GO95HV-1^06243009.0131800 | OTHER | Non-HFTD | Distribution | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003398 | 442794278-8901-DETAIL-05_02_2024-GO95HV-1^06142012.0125111 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003399 | 442898525-83059-DETAIL-06_11_2024-GO95HV-1^06245007.0345640 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003400 | 443179836-8969-DETAIL-07_31_2024-GO95CL10-1^06244004.0194601 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003401 | 443179836-8969-DETAIL-07_31_2024-GO95MLD-1^06244004.0194601 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003402 | 443259831-8279-DETAIL-01_17_2023-GO95BLTC-1^06148004.0174302 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003403 | 443259831-8279-DETAIL-01_17_2023-GO95MLD-1^06148004.0174302 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003404 | 443601764-42089-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192502 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003405 | 443601764-42089-DETAIL-01_23_2023-GO95HV-1^06148004.0192502 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003406 | 443796761-1999-DTLTRT-11_07_2022-GO95MLD-1^668001/00 9/029 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003407 | 444715360-78009-DETAIL-03_11_2024-ENCHRW-1^06147004.0028903 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003408 | 445133444-41001-DETAIL-03_20_2024-GO95BLTC-1^06245001.0051101 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003409 | 445133444-41001-DETAIL-03_20_2024-GO95MLD-1^06245001.0051101 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003410 | 388526124-74922-DETAIL-07_11_2023-GO95HV-1^06244008.0332801 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003411 | 388956747-98919-ADMIN-01_15_2025-POLTOPSW-1^668036/00 1/036 | SWITCH | Non-HFTD | Transmission | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003412 | 389111266-62179-DETAIL-08_08_2024-GO95MLD-1^06245006.0094800 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003413 | 389408658-969-DTLTRT-04_04_2024-RISEBKSP-1^668067/00 2/024 | OTHER | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003414 | 389587386-87179-DETAIL-04_03_2024-GO95MLD-1^06147005.0237700 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003415 | 389587386-87179-DETAIL-04_03_2024-GUYHINS-1^06147005.0237700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003416 | 389770853-20490-DETAIL-03_04_2025-GO95TCH-1^06240004.0150703 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003417 | 389770853-20490-DETAIL-03_04_2025-RISEGRD-1^06240004.0150703 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003418 | 390045739-92809-DTLSB-09_05_2024-GO95HV-1^06245007.0034002 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003419 | 390045739-92809-DTLSB-09_05_2024-GO95MLD-1^06245007.0034002 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003420 | 390181227-5227-DETAIL-03_10_2025-GO95HV-1^06240004.0288802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003421 | 39025196-13823-DTLSB-04_23_2024-GO95MLD-1^06245007.0222644 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003422 | 390280083-16313-DTLSB-04_25_2024-SVCWIND-1^06245007.0227550 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003423 | 39042838-92699-DTLSB-08_23_2023-GO95MLD-1^06243009.0158900 | OTHER | HFTD Tier 2 | Distribution | 2023-08-23 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003424 | 39042838-92699-DTLSB-08_23_2023-GUYHINS-1^06243009.0158900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-08-23 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003425 | 390455099-17649-DETAIL-02_22_2024-GO95MLD-1^07216001.0348700 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003426 | 390516191-55179-DETAIL-01_23_2023-GO95BLTC-1^06148004.0192903 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003427 | 390965729-20640-DETAIL-04_11_2024-GO95MLD-1^06245002.0102200 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003428 | 391351061-4819-DETAIL-05_25_2023-GO95HV-1^07117007.0227202 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003429 | 391446341-35840-DETAIL-01_31_2023-GO95MLD-1^06146002.0035900 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003430 | 391808933-4519-DTLTRT-08_17_2022-UBPBXARM-1^668005/00 14/093 | CROSSARM | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003431 | 392161634-12190-DETAIL-02_19_2025-GUYHINS-1^06240004.0100007 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003432 | 392358568-14340-ADMIN-04_23_2024-ABNDEQPM-1^06145001.0023205 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003433 | 392358568-14340-DETAIL-04_23_2024-GO95HV-1^06145001.0023205 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003434 | 392687578-34343-DETAIL-03_09_2023-GO95MLD-1^07117002.0209104 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003435 | 445134286-3779-DTLSB-08_29_2023-GO95HV-1^06243009.0110300 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003436 | 445251424-48560-DETAIL-01_22_2025-SVCDEFLC-1^06239004.0255800 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003437 | 445376466-40070-DETAIL-01_21_2025-GO95HV-1^06239004.0255304 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003438 | 445391939-92390-DETAIL-01_16_2025-GO95TCH-1^06239004.0257208 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003439 | 445413636-68289-DTLSB-09_04_2024-GO95MLD-1^06245007.0141902 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003440 | 445947593-71693-DETAIL-04_29_2024-GRDRODHI-1^06142016.0067902 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003441 | 446094741-58839-DETAIL-02_22_2024-SVCROAD-1^07113001.0099300 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003442 | 446518284-47330-DETAIL-02_26_2025-GO95MLD-1^06241005.0367902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003443 | 446740964-29462-DETAIL-07_16_2024-GUYHINS-1^06244005.0274100 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-16 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003444 | 446987080-60532-DETAIL-06_15_2023-GO95HV-1^06244009.0337100 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003445 | 447349306-47501-DETAIL-02_06_2023-GUYSLACK-1^06147002.0319900 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003446 | 447779990-41709-DETAIL-11_02_2022-GO95HV-1^06246008.0054501 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003447 | 447937261-93409-DETAIL-03_05_2024-GO95HV-1^06147004.0022300 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003448 | 448306141-67373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200340 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003449 | 448526701-82349-DETAIL-02_20_2024-GO95HV-1^07113002.0181109 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003450 | 448526701-82349-DETAIL-02_20_2024-GO95MLD-1^07113002.0181109 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003451 | 448526701-82349-DETAIL-02_20_2024-SVCDEFLC-1^07113002.0181109 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003452 | 448681668-16549-DETAIL-03_09_2023-GRDRODHI-1^07117002.0207242 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003453 | 448783463-29779-DTLTRT-10_19_2023-GO95MLD-1^668010/00 12/024 | OTHER | HFTD Tier 2 | Transmission | 2023-10-19 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003454 | 448835992-4449-AUDIT-03_06_2024-GO95MLD-1^07113002.0180104 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003455 | 448881263-93263-DETAIL-04_29_2024-SVCROAD-1^06142016.0079901 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003456 | 449010095-65909-DETAIL-04_01_2024-GO95HV-1^06147005.0126900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003457 | 449226725-76725-DETAIL-02_17_2025-GO95TCH-1^06241005.0229102 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003458 | 44944251-60420-DETAIL-03_06_2025-PWRTRN-1^06240004.0272501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003459 | 449795833-84669-DTLTRT-06_23_2021-GO95MLD-1^668041/00 5/032 | OTHER | Non-HFTD | Transmission | 2021-06-23 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003460 | 392690674-23674-DETAIL-07_05_2024-SVCDEFLC-1^06244005.0125600 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003461 | 392724784-92119-DTLTRT-08_17_2022-GO95MLD-1^668005/00 8/095 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003462 | 392890933-419-DTLTRT-08_16_2022-GO95HV-1^668005/00 9/090 | OTHER | Non-HFTD | Transmission | 2022-08-16 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003463 | 393002381-29914-DETAIL-02_05_2018-SVCWIND-1^06142016.0054104 | OTHER | Non-HFTD | Distribution | 2018-02-05 | 2021-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003464 | 393401173-85469-DTLTRT-11_07_2022-GO95BLTC-1^668001/00 14/030 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003465 | 393401173-85469-DTLTRT-11_07_2022-GO95MLD-1^668001/00 14/030 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003466 | 393995066-63660-DTLTRT-10_09_2023-GO95HV-1^668010/00 5/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003467 | 394644188-75489-ADMIN-12_12_2024-SVCDEFLC-1^06244007.0036900 | OTHER | HFTD Tier 2 | Distribution | 2024-12-12 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003468 | 395090414-19690-DETAIL-01_15_2025-SVCENTCO-1^06240004.0099300 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003469 | 395317859-76249-DTLSB-10_03_2024-GO95STUB-1^06245007.0219702 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003470 | 395451178-88150-DETAIL-01_16_2025-SVCDEFLC-1^06240004.0097701 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003471 | 395674795-75629-DETAIL-08_21_2024-SVCROAD-1^06245008.0245100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003472 | 395931734-24079-DETAIL-07_31_2024-GO95HV-1^06245004.0060801 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003473 | 396064621-9881-DTLTRT-06_15_2021-GO95HV-1^668041/00 5/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003474 | 396876381-5469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 11/006 | CROSSARM | Non-HFTD | Transmission | 2023-09-12 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003475 | 396876381-5469-DRONE_HY-09_13_2023-EARMSPCR-1^668002/00 11/006 | OTHER | Non-HFTD | Transmission | 2023-09-13 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003476 | 396880365-84639-DETAIL-07_09_2024-ABNDEQPM-1^06244004.0183100 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003477 | 397234089-30330-DETAIL-01_23_2025-GO95CL10-1^06240004.0083600 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003478 | 39784913-21669-DTLTRT-06_04_2021-GO95HV-1^668041/00 5/009 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003479 | 397981134-83534-DETAIL-05_01_2024-GO95HV-1^06143015.0337700 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003480 | 398159588-62169-DTLTRT-06_30_2022-GO95HV-1^668005/00 16/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003481 | 398308494-34189-DETAIL-01_23_2023-GO95HV-1^06148004.0192102 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003482 | 39852152-78099-DETAIL-01_29_2019-GO95HV-1^06147004.0350401 | OTHER | Non-HFTD | Distribution | 2019-01-29 | 2024-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003483 | 398662253-90429-DETAIL-05_14_2024-GO95BLTC-1^06142012.0122503 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003484 | 39883243-34450-DETAIL-01_24_2025-SVCENTCO-1^06239004.0258701 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003485 | 450087538-68069-DTLTRT-06_30_2022-GO95MLD-1^668005/00 3/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003486 | 450171963-49963-DETAIL-04_29_2024-GO95MLD-1^06142016.0079801 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003487 | 450171963-49963-DETAIL-04_29_2024-GRDRODHI-1^06142016.0079801 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003488 | 450345734-36359-DETAIL-02_26_2024-CUTOUTAR-3^07113001.0085501 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003489 | 450398291-49849-DETAIL-02_22_2024-GUYLOINS-1^07113001.0093700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003490 | 45079451-64329-DETAIL-06_21_2023-GO95HV-1^06244009.0282101 | OTHER | HFTD Tier 2 | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003491 | 450821592-20152-DETAIL-06_26_2023-GO95HV-1^06244009.0300600 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003492 | 452286508-62120-DTLTRT-10_17_2023-GO95HV-1^668010/00 3X/009 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003493 | 452392564-21349-DTLSB-02_07_2024-GO95MLD-1^07216001.0199002 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003494 | 452556913-57839-DETAIL-10_10_2024-GO95MLD-1^07216001.0205007 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003495 | 452906420-4049-DTLSB-02_19_2024-GO95MLD-1^07216001.0261203 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003496 | 452971556-32459-DETAIL-02_27_2023-CLRTOPOL-1^07216001.0298802 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003497 | 452971556-32459-DETAIL-02_27_2023-GO95MLD-1^07216001.0298802 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003498 | 453083105-96109-DETAIL-01_23_2023-CONDFRAY-1^06148004.0200001 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003499 | 453175653-43139-DETAIL-07_16_2024-GO95MLD-1^06244005.0274002 | OTHER | Non-HFTD | Distribution | 2024-07-16 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003500 | 453175653-43139-DETAIL-07_16_2024-SVCENTCO-1^06244005.0274002 | OTHER | Non-HFTD | Distribution | 2024-07-16 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003501 | 453536151-40529-DETAIL-06_07_2023-GO95HV-1^06244010.0273700 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003502 | 453798531-81631-DETAIL-04_25_2024-GO95HV-1^06142016.0040001 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003503 | 454119326-66449-DETAIL-07_29_2024-CONDCOIL-1^06245006.0111700 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003504 | 454156215-5859-DETAIL-03_04_2024-SVCROAD-1^06245007.0275101 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003505 | 454372218-36069-DTLTRT-10_11_2023-GO95MLD-1^668010/00 12/043 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003506 | 454407124-67911-AUDIT-06_24_2024-GRDRODHI-1^06245001.0051301 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003507 | 454472038-51030-DETAIL-10_17_2023-GUYHINS-1^668010/00 13X/009 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003508 | 454472038-51030-DETAIL-10_17_2023-GUYHINS-2^668010/00 13X/009 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003509 | 454472038-51030-DETAIL-10_17_2023-GUYHINS-4^668010/00 13X/009 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003510 | 398986349-27841-DETAIL-04_03_2025-GO95MLD-1^06241005.0091001 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003511 | 399036364-56364-DTLTRT-04_17_2024-SVCWIND-1^06245007.0223406 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003512 | 39914451-82830-DTLSB-05_07_2024-GRDRODHI-1^06245002.0138100 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003513 | 399901221-61769-DTLTRT-10_05_2023-SVCROAD-1^668010/00 1/028 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003514 | 399987487-79487-DETAIL-07_05_2024-GO95HV-1^06244005.0013602 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003515 | 400479782-99349-DETAIL-10_10_2024-GO95HV-1^07216001.0207007 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003516 | 400640304-96132-DETAIL-03_06_2025-SVCDEFLC-1^06241005.0120502 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003517 | 40070728-12760-DTLTRT-09_30_2020-GO95HV-1^668018/00 8/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003518 | 400786795-42109-DTLSB-08_28_2024-GO95HV-1^06245007.0143300 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003519 | 400814145-42550-DTLSB-05_08_2024-GO95HV-1^06244001.0108500 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003520 | 40084598-67930-DETAIL-04_16_2024-GO95MLD-1^06145001.0019400 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003521 | 401049467-74650-DETAIL-03_19_2024-GO95CL10-1^06245002.0123800 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003522 | 401164874-29850-ADMIN-10_13_2023-POLEDERP-1^07216001.0153705 | POLE | Non-HFTD | Distribution | 2023-10-13 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003523 | 401213923-20950-DETAIL-04_06_2023-GUYHINS-1^06143014.0236702 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-04-06 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003524 | 402288537-32859-DETAIL-10_14_2024-GO95TCH-1^07216001.0201408 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003525 | 402402953-11550-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049300 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003526 | 402425224-74459-DTLSB-02_21_2024-SVCENTBK-1^07216001.0260600 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003527 | 402774660-55669-DTLSB-05_02_2024-SVCDEFLC-1^06245007.0227901 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003528 | 402916699-74850-ADMIN-04_11_2024-ABNDEQPM-1^06245002.0104300 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003529 | 402920936-39379-DETAIL-04_01_2024-GO95TCH-1^06147005.0124500 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003530 | 402920936-39379-DETAIL-04_01_2024-GUYHINS-1^06147005.0124500 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003531 | 403052633-73950-DTLSB-02_13_2023-GO95MLD-1^06248001.0278201 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003532 | 403295814-73799-DETAIL-03_06_2024-GO95MLD-1^06147005.0177701 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003533 | 403467809-30789-DETAIL-06_24_2024-GRDRODHI-1^06244005.0230001 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003534 | 403594739-76199-DETAIL-06_03_2024-GO95HV-1^06245006.0028700 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003535 | 454472038-51030-DETAIL-10_17_2023-GUYHINS-5^668010/00 13X/009 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003536 | 454472038-51030-DETAIL-10_17_2023-GUYHINS-6^668010/00 13X/009 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003537 | 454528524-24549-DETAIL-03_20_2023-GO95HV-1^07114001.0283402 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003538 | 454528524-24549-DETAIL-03_20_2023-GO95MLD-1^07114001.0283402 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003539 | 455218428-73711-DTLSB-05_15_2024-GO95HV-1^06244002.0226600 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003540 | 455550172-20880-DETAIL-02_06_2025-GUYNOINS-1^06240004.0166310 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003541 | 455553348-76238-DETAIL-03_02_2023-GO95TCH-1^07216001.0298640 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003542 | 455553348-76238-DETAIL-03_02_2023-SVCENTCO-1^07216001.0298640 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003543 | 455553348-76238-DETAIL-03_02_2023-SVCWIND-1^07216001.0298640 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003544 | 455743818-68969-DTLTRT-06_30_2022-GO95MLD-1^668005/00 4/031 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003545 | 455774338-28489-DETAIL-04_01_2024-SVCENTBK-1^06244005.0149300 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003546 | 45658623-12721-DETAIL-02_18_2025-GUYHINS-1^06239004.0364804 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003547 | 456607790-55532-DTLSB-07_19_2023-GO95MLD-1^06243010.0020100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003548 | 456632136-80449-DETAIL-10_10_2024-SVCROOF-1^07216001.0201204 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003549 | 456954831-86809-DETAIL-03_11_2024-CONDFRAY-2^06147004.0037600 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003550 | 457383959-99583-DETAIL-03_14_2024-SVCNEUT-1^06245005.0062740 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003551 | 457684650-36301-DETAIL-01_31_2025-GO95HV-1^06239004.0135006 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003552 | 458069169-27221-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355600 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003553 | 458520984-14269-DTLTRT-10_11_2023-GO95HV-1^668010/00 5/040 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003554 | 458521423-51209-DETAIL-06_18_2024-SVCDEFLC-1^06245007.0290500 | OTHER | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003555 | 45864493-67089-DETAIL-07_11_2024-GO95HV-1^06244005.0260202 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003556 | 458787028-34079-ADMIN-07_05_2024-GO95STUB-1^06248004.0361142 | OTHER | HFTD Tier 2 | Distribution | 2024-07-05 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003557 | 459022634-80760-DETAIL-01_23_2025-GO95BLTC-1^06239004.0257706 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003558 | 459022634-80760-DETAIL-01_23_2025-GO95HV-1^06239004.0257706 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003559 | 403724939-21269-DTLTRT-06_14_2021-GO95HV-1^668041/00 13/020 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003560 | 404208601-74549-DETAIL-02_28_2024-GO95HV-1^07113001.0146700 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003561 | 404232111-92363-DTLSB-04_10_2024-SVCROAD-1^06245007.0223042 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003562 | 404416896-89940-DETAIL-09_06_2024-SVCDEFLC-1^06240004.0080304 | OTHER | HFTD Tier 2 | Distribution | 2024-09-06 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003563 | 404673183-80789-DETAIL-06_06_2024-GO95MLD-1^06246006.0350102 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003564 | 405037321-27469-DTLTRT-09_25_2023-GO95MLD-1^668010/00 5/001 | OTHER | Non-HFTD | Transmission | 2023-09-25 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003565 | 405037321-27469-DTLTRT-09_25_2023-GRDRODHI-1^668010/00 5/001 | OTHER | Non-HFTD | Transmission | 2023-09-25 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003566 | 405037321-27469-DTLTRT-09_25_2023-GRDRODHI-2^668010/00 5/001 | OTHER | Non-HFTD | Transmission | 2023-09-25 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003567 | 405037321-27469-DTLTRT-09_25_2023-GRDRODHI-3^668010/00 5/001 | OTHER | Non-HFTD | Transmission | 2023-09-25 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003568 | 405098080-12670-DETAIL-02_13_2025-GO95BLTC-1^06240004.0169205 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003569 | 405609403-32099-DETAIL-06_13_2023-GRDRODHI-1^06243009.0038500 | OTHER | Non-HFTD | Distribution | 2023-06-13 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003570 | 405609403-32099-DETAIL-06_13_2023-GRDRODHI-2^06243009.0038500 | OTHER | Non-HFTD | Distribution | 2023-06-13 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003571 | 405634836-93560-DTLTRT-10_09_2023-GUYHINS-1^668010/00 3/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003572 | 40600130-16955-DETAIL-03_13_2025-GO95HV-1^06239003.0129100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003573 | 406175349-56839-DTLSB-02_16_2024-GO95HV-1^07216001.0261010 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003574 | 406175349-56839-DTLSB-02_16_2024-GO95MLD-1^07216001.0261010 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003575 | 406204735-39872-DETAIL-06_06_2023-GO95MLD-1^06244010.0342401 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003576 | 406432384-7989-DETAIL-01_24_2023-CONDFRAY-1^06148004.0182201 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003577 | 406523055-91549-DETAIL-02_28_2023-GO95MLD-1^07216001.0299801 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003578 | 406757318-95753-DETAIL-02_27_2023-GO95TCH-1^07216001.0296843 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003579 | 406757318-95753-DETAIL-02_27_2023-SVCENTBK-1^07216001.0296843 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003580 | 406879366-60449-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0295708 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003581 | 407048235-4449-DETAIL-07_29_2024-GO95HV-1^06245006.0113900 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003582 | 407392528-21740-DETAIL-03_17_2025-SVCENTBK-1^06238004.0143200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003583 | 407392528-21740-DETAIL-03_17_2025-SVCROAD-1^06238004.0143200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003584 | 459356248-80440-DETAIL-03_12_2025-ABNDEQPM-1^06238004.0222402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003585 | 459397314-96159-DETAIL-08_21_2024-GO95MLD-1^06246005.0269541 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003586 | 459397314-96159-DETAIL-08_21_2024-GRDRODHI-1^06246005.0269541 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003587 | 459508758-11349-DETAIL-03_14_2024-GO95HV-1^06245005.0061500 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003588 | 459508758-11349-DETAIL-03_14_2024-GO95MLD-1^06245005.0061500 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003589 | 459722274-72430-DETAIL-01_28_2025-GO95MLD-1^06240004.0086042 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003590 | 459918801-96030-DETAIL-01_29_2025-SVCROOF-1^06240004.0177702 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003591 | 460028231-56809-DETAIL-03_11_2024-GO95HV-1^06147004.0038601 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003592 | 460647462-8450-DETAIL-02_06_2025-GO95TCH-1^06239004.0137201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003593 | 460738598-98430-DTLTRT-10_18_2023-GO95HV-1^668010/00 9/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003594 | 460738598-98430-DTLTRT-10_18_2023-GO95MLD-1^668010/00 9/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003595 | 460839856-51956-DTLSB-01_30_2023-GO95MLD-1^06248001.0368906 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003596 | 461019866-68770-DETAIL-01_23_2025-GO95HV-1^06239004.0256642 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003597 | 461377293-54421-DETAIL-04_06_2023-GO95MLD-1^06143014.0233800 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003598 | 461605734-15521-DETAIL-02_09_2023-GO95MLD-1^06146004.0165900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003599 | 461605734-15521-DETAIL-02_09_2023-GRDRODHI-1^06146004.0165900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003600 | 462140580-48270-DETAIL-03_11_2025-GO95HV-1^06238002.0070901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003601 | 46216496-99193-DTLSB-09_04_2024-GO95BLTC-1^06245007.0141540 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003602 | 462452928-35612-DETAIL-06_20_2023-GO95MLD-1^06244009.0355300 | OTHER | HFTD Tier 2 | Distribution | 2023-06-20 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003603 | 462726413-69429-DTLSB-09_06_2023-GO95HV-1^06243007.0171100 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003604 | 462760441-14959-DETAIL-05_10_2022-GUYSLACK-1^07116001.0093900 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003605 | 462760441-14959-DETAIL-05_10_2022-SVCWIND-1^07116001.0093900 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003606 | 462887023-55929-AUDIT-05_29_2024-SVCDEFLC-1^06142012.0121601 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003607 | 463019842-209-DTLSB-08_30_2023-GO95MLD-1^06243008.0179701 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003608 | 463116904-12039-DETAIL-10_10_2024-SVCENTCO-1^07216001.0205202 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003609 | 407499849-96109-DETAIL-03_04_2024-CONDFRAY-1^06147004.0017202 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003610 | 407603594-5594-DETAIL-03_04_2025-SVCDEFLC-1^06240004.0065906 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003611 | 40770663-75829-AUDIT-04_12_2023-GO95MLD-1^06143013.0336600 | OTHER | Non-HFTD | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003612 | 408012504-92473-DETAIL-03_29_2023-SVCROAD-1^06142016.0084602 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003613 | 408101594-65729-DTLSB-08_01_2023-GO95MLD-1^06243009.0189803 | OTHER | HFTD Tier 2 | Distribution | 2023-08-01 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003614 | 408239840-24429-DETAIL-05_02_2024-GO95MLD-1^06142012.0124104 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003615 | 408639764-74249-DETAIL-05_17_2022-GO95MLD-1^07117001.0319404 | OTHER | Non-HFTD | Distribution | 2022-05-17 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003616 | 408731471-19669-DRONE_HY-09_15_2023-BIRDWST-1^668002/00 28/061 | OTHER | HFTD Tier 2 | Transmission | 2023-09-15 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003617 | 410245454-32899-ADMIN-04_05_2024-ABNDEQPM-1^06245007.0275707 | OTHER | Non-HFTD | Distribution | 2024-04-05 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003618 | 410347021-29752-DETAIL-06_15_2023-GO95MLD-1^06244009.0291700 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003619 | 410479685-80479-DTLTRT-11_01_2023-GO95HV-1^668010/00 19/017 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003620 | 410699930-43899-DETAIL-03_07_2024-GO95MLD-1^06147004.0230501 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003621 | 410699930-43899-DETAIL-03_07_2024-GRDRODHI-1^06147004.0230501 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003622 | 410703298-27290-DETAIL-01_24_2025-GO95HV-1^06239004.0246000 | OTHER | HFTD Tier 2 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003623 | 411044279-94449-DETAIL-10_14_2024-GO95MLD-1^07216001.0202306 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003624 | 411338982-9289-DTLSB-08_26_2024-GO95HV-1^06245007.0112200 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003625 | 411338982-9289-DTLSB-08_26_2024-GO95MLD-1^06245007.0112200 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003626 | 411384238-1509-DETAIL-02_02_2022-SVCWIND-1^06147005.0268202 | OTHER | Non-HFTD | Distribution | 2022-02-02 | 2025-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003627 | 411432436-89739-AUDIT-03_06_2023-GUYHINS-1^07216001.0295601 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003628 | 411432436-89739-DETAIL-03_08_2023-GO95TCH-1^07216001.0295601 | OTHER | Non-HFTD | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003629 | 412221780-72780-DETAIL-04_30_2024-GO95HV-1^06142015.0024900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003630 | 412582163-42479-DETAIL-06_27_2023-GO95MLD-1^06243009.0047901 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003631 | 41263240-31579-ADMIN-03_20_2025-EQUIPOIL-1^06245006.0229000 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003632 | 412829903-63249-DETAIL-02_20_2024-GO95MLD-1^07113002.0183002 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003633 | 413002572-47340-DTLTRT-10_03_2023-GO95HV-1^668010/00 16/030 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003634 | 463218185-99079-DETAIL-06_11_2024-GO95MLD-1^06245007.0345702 | OTHER | Non-HFTD | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003635 | 463303796-88031-DETAIL-02_15_2023-GO95MLD-1^06247002.0235801 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003636 | 46356594-49849-DETAIL-03_30_2023-GO95TCH-1^06142016.0084908 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003637 | 463720221-51431-DETAIL-02_01_2023-GO95HV-1^06146002.0074500 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003638 | 4642574-99259-DETAIL-03_16_2023-GO95HV-1^07114001.0282640 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003639 | 464336682-93473-DETAIL-03_09_2023-GO95MLD-1^07117002.0206240 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003640 | 464418946-91931-DTLSB-05_14_2024-GO95MLD-1^06244001.0298201 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003641 | 464531090-11019-DETAIL-12_31_2018-POLEREPL-1^668005/00 9/079 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003642 | 464738854-56954-DETAIL-01_13_2025-SVCDEFLC-1^06240004.0085220 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003643 | 464880036-60419-DETAIL-04_02_2024-GO95HV-1^06147005.0132001 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003644 | 465220879-15549-DTLSB-04_10_2024-GO95MLD-1^06245007.0224008 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003645 | 465220879-15549-DTLSB-04_10_2024-XARMSPCR-1^06245007.0224008 | CROSSARM | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003646 | 466059204-64973-DETAIL-03_04_2024-SVCROAD-2^06245007.0274342 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003647 | 466280629-57569-DTLTRT-10_25_2023-GO95MLD-1^668010/00 23/012 | OTHER | HFTD Tier 2 | Transmission | 2023-10-25 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003648 | 466702917-85369-DETAIL-06_08_2023-GO95MLD-1^06244009.0292602 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003649 | 46673015-21449-DETAIL-07_29_2024-GO95MLD-1^06245006.0117900 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003650 | 467386120-79420-DETAIL-03_06_2025-GRDRODHI-1^06240004.0272001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003651 | 467386120-79420-DETAIL-03_06_2025-SVCROOF-1^06240004.0272001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003652 | 46739223-75743-DETAIL-08_15_2024-GO95MLD-1^06246005.0125100 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003653 | 467682912-45950-DETAIL-03_25_2025-GO95HV-1^06239003.0019411 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003654 | 467710609-58131-DETAIL-04_11_2024-GO95MLD-1^06245002.0107500 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003655 | 467893852-87459-DETAIL-02_29_2024-SVCENTCO-1^07113001.0140801 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003656 | 467925981-79739-DRONE_HY-10_25_2023-GO95HV-1^668087/00 4/008 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003657 | 468051635-65539-DETAIL-02_27_2024-GO95MLD-1^07113002.0183601 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003658 | 468051635-65539-DETAIL-02_27_2024-GRDRODHI-1^07113002.0183601 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003659 | 468328708-96579-DTLSB-07_01_2024-GO95MLD-1^06245006.0181002 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003660 | 413091351-19859-DETAIL-06_05_2024-GO95MLD-1^06246006.0268602 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003661 | 413533213-3630-DETAIL-03_04_2025-PWRTRN-1^06240004.0062702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003662 | 414028793-19793-DTLSB-05_02_2024-GO95MLD-1^06245007.0228904 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003663 | 414447670-4270-DETAIL-03_19_2025-GO95HV-1^06239002.0018600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003664 | 415034995-56360-DTLTRT-10_09_2023-GO95HV-1^668010/00 1/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003665 | 415034995-56360-DTLTRT-10_09_2023-GUYHINS-1^668010/00 1/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003666 | 415284634-73129-DETAIL-03_16_2017-SVCWIND-1^06142012.0130614 | OTHER | Non-HFTD | Distribution | 2017-03-16 | 2020-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003667 | 415386575-44960-DETAIL-02_07_2023-GO95HV-1^06147002.0095100 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003668 | 415708831-43249-DETAIL-02_20_2024-GO95MLD-1^07113001.0139101 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003669 | 415776454-31999-DETAIL-03_21_2024-GO95HV-1^06147005.0206700 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003670 | 415776454-31999-DETAIL-03_21_2024-GO95MLD-1^06147005.0206700 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003671 | 415873325-89170-DTLSB-05_07_2024-GO95HV-1^06245001.0302900 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003672 | 415873325-89170-DTLSB-05_07_2024-GRDRODHI-1^06245001.0302900 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003673 | 415917893-21289-DTLSB-07_26_2023-GO95MLD-1^06243009.0059900 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003674 | 416333438-12009-DETAIL-04_09_2024-GO95BLTC-1^06147005.0215802 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003675 | 41634216-39208-DTLSB-09_03_2024-SVCNEUT-1^06245007.0124900 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003676 | 416401303-83692-DETAIL-06_21_2023-GO95TCH-1^06244009.0198370 | OTHER | HFTD Tier 2 | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003677 | 417456025-34539-DTLSB-02_21_2023-SVCENTCO-1^07216001.0287707 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003678 | 417488276-65749-DTLSB-10_07_2024-GO95MLD-1^06245007.0230400 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003679 | 418041579-34479-DTLSB-10_02_2024-GO95MLD-1^06245007.0217806 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003680 | 418132681-57399-DETAIL-07_24_2024-SVCDEFLC-1^06244005.0131300 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003681 | 418207646-63610-DETAIL-03_13_2025-GO95HV-1^06238004.0225702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003682 | 418540815-76170-DETAIL-10_22_2024-GO95MLD-1^07216001.0207707 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003683 | 419013746-23746-DETAIL-01_29_2025-GO95MLD-1^06239004.0268802 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003684 | 419608113-48369-DTLTRT-10_11_2023-GO95MLD-1^668010/00 1/044 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003685 | 419623245-8149-DETAIL-10_24_2024-CLRTOUCH-1^07216001.0202502 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003686 | 419830485-33870-DTLSB-02_02_2023-SVCENTCO-1^06248001.0368104 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003687 | 419986666-27666-DTLSB-02_15_2023-GO95MLD-1^06248001.0305001 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003688 | 420814456-98279-DETAIL-01_24_2023-GO95HV-1^06148004.0182002 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003689 | 421035715-71349-DETAIL-10_08_2024-SVCENTCO-1^07216001.0200001 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003690 | 421110088-90749-DTLSB-07_02_2024-GO95MLD-1^06245006.0183101 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003691 | 421127660-35930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 3/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-26 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003692 | 421443124-59499-DTLSB-04_23_2024-GO95MLD-1^06245007.0223702 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003693 | 421450226-70299-DETAIL-04_01_2024-GO95TCH-1^06147005.0113901 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003694 | 421488198-7540-DETAIL-03_20_2025-GO95HV-1^06239003.0018104 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003695 | 421797606-8606-DETAIL-01_29_2025-GO95MLD-1^06239004.0227300 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003696 | 421866783-76853-DETAIL-06_07_2023-GO95MLD-1^06244010.0270801 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003697 | 422085546-49670-DETAIL-01_22_2025-GO95MLD-1^06239004.0256541 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003698 | 42210456-15540-DTLSB-02_21_2023-GO95MLD-1^07216001.0281704 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003699 | 422423342-97929-DETAIL-05_15_2024-GO95HV-1^06142012.0126840 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003700 | 422423342-97929-DETAIL-05_15_2024-GO95MLD-1^06142012.0126840 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003701 | 422599025-94279-DETAIL-07_09_2024-GO95MLD-1^06244004.0182300 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003702 | 422711052-14570-DTLSB-02_13_2023-GO95MLD-1^06248001.0278304 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003703 | 422832427-88099-DTLSB-07_22_2024-GO95MLD-1^06245006.0060000 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003704 | 422962237-27590-DETAIL-01_30_2025-GO95HV-1^06239004.0245642 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003705 | 423467549-64599-DTLSB-10_02_2024-GO95MLD-1^06245007.0215600 | OTHER | HFTD Tier 2 | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003706 | 42362859-58470-DETAIL-03_21_2023-GO95TCH-1^06240004.0167416 | OTHER | HFTD Tier 2 | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003707 | 423693746-4746-DETAIL-01_29_2025-GO95MLD-1^06239004.0267801 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003708 | 423706611-55670-DETAIL-02_27_2023-RISESTRP-1^07216001.0296708 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003709 | 423962321-3321-DETAIL-07_15_2024-GO95BLTC-1^06244005.0250501 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003710 | 42410316-80989-DETAIL-02_03_2025-GO95HV-1^06239004.0244943 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003711 | 424203856-75249-DETAIL-03_11_2024-GO95MLD-1^06245006.0124501 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003712 | 424346098-99849-DETAIL-08_01_2024-GO95HV-1^06245006.0155800 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003713 | 42471294-53540-DETAIL-10_22_2024-SVCENTCO-1^07216001.0208901 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003714 | 424795646-14770-DETAIL-01_15_2025-GO95HV-1^06239004.0255246 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003715 | 42508626-84540-DTLSB-01_31_2023-GO95HV-1^06248001.0367809 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003716 | 425119286-11060-DTLTRT-10_23_2023-GUYNOINS-2^668010/00 18A/042 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003717 | 425119286-11060-DTLTRT-10_23_2023-GUYNOINS-3^668010/00 18A/042 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003718 | 4251518-92909-DETAIL-04_02_2024-GO95HV-1^06147005.0092300 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003719 | 425188887-53449-DETAIL-10_08_2024-GO95HV-1^07216001.0200109 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003720 | 425270833-91839-DETAIL-07_11_2024-GO95MLD-1^06244005.0260301 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003721 | 425550398-87043-DTLSB-05_06_2024-GO95CL10-1^06245007.0221743 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003722 | 425579493-41918-DETAIL-03_08_2023-GO95MLD-1^07117002.0212003 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003723 | 425749113-2259-DETAIL-03_20_2023-GO95TCH-1^07114001.0206001 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003724 | 425774901-18343-ADMIN-08_05_2024-GO95STUB-1^07217001.0154001 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003725 | 425969995-41479-DTLTRT-11_01_2023-GO95HV-1^668010/00 2/018 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003726 | 426310278-12043-DTLSB-04_30_2024-GO95STUB-1^06245007.0220941 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003727 | 426697709-96039-DETAIL-07_08_2024-GO95HV-1^06244005.0138600 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003728 | 426985984-88689-DETAIL-01_23_2023-CONDFRAY-1^06148004.0192002 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003729 | 426985984-88689-DETAIL-01_23_2023-GO95MLD-1^06148004.0192002 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003730 | 426999161-76284-DETAIL-03_27_2023-GO95MLD-1^06142016.0050201 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003731 | 427295820-78079-DETAIL-03_05_2024-GO95MLD-1^06147004.0020203 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003732 | 427396412-22459-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0146102 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003733 | 427584130-5069-DTLTRT-07_15_2022-GO95HV-1^668005/00 6/047 | OTHER | Non-HFTD | Transmission | 2022-07-15 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003734 | 427634606-44170-DETAIL-01_16_2025-ABNDEQPM-1^06239004.0256201 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003735 | 468592623-65649-DETAIL-05_05_2022-GO95MLD-1^06241005.0130704 | OTHER | HFTD Tier 2 | Distribution | 2022-05-05 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003736 | 469225214-82049-DETAIL-03_16_2023-GO95HV-1^07113001.0059602 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003737 | 469891345-67101-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 6/018 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003738 | 470284088-97849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155601 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003739 | 470835171-14380-DETAIL-02_14_2025-GO95BLTC-1^06240004.0168044 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003740 | 470835171-14380-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0168044 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003741 | 47115443-88440-DTLSB-05_22_2024-GO95MLD-1^06243001.0102900 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003742 | 47127222-94569-DTLTRT-06_04_2021-GO95HV-1^668041/00 8/008 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003743 | 471345453-18529-DTLSB-07_31_2023-GO95MLD-1^06243009.0080000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003744 | 471774794-20280-DTLTRT-10_31_2023-GO95HV-1^668010/00 16/015 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003745 | 471990226-60570-DETAIL-01_30_2025-GO95HV-1^06239004.0245802 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003746 | 472216851-78659-DETAIL-06_17_2024-GO95HV-1^06246006.0239100 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003747 | 472511933-13639-DTLSB-09_20_2022-GO95MLD-1^06243005.0016902 | OTHER | Non-HFTD | Distribution | 2022-09-20 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003748 | 472776843-38241-DETAIL-03_03_2025-GUYHINS-1^06241004.0182200 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003749 | 473398640-84899-DETAIL-11_02_2022-GO95MLD-1^06246008.0050702 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003750 | 473704771-73920-DETAIL-03_10_2025-SVCDEFLC-1^06240004.0270801 | OTHER | HFTD Tier 3 | Distribution | 2025-03-10 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003751 | 474129808-59359-DETAIL-06_04_2024-GO95MLD-1^06246005.0320503 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003752 | 47426518-65360-DETAIL-10_21_2024-BIRDDMG-1^668014/00 6/053 | POLE | HFTD Tier 3 | Transmission | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003753 | 474350001-49641-DETAIL-04_22_2024-GO95MLD-1^06145001.0149900 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003754 | 474359606-9449-DETAIL-07_29_2024-GO95HV-1^06245006.0115500 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003755 | 474432336-31661-DETAIL-02_19_2025-GO95MLD-1^06239004.0365501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003756 | 475734355-56200-DETAIL-03_13_2025-SVCDEFLC-1^06239003.0242101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003757 | 47587978-70843-DETAIL-03_09_2023-GO95MLD-1^07117002.0209108 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003758 | 476020291-16014-DETAIL-03_23_2023-GO95MLD-1^06142016.0051103 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003759 | 476678336-72559-DETAIL-03_07_2023-GO95MLD-1^07216001.0294410 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003760 | 476778304-37141-DETAIL-10_16_2024-SVCNEUT-1^07216001.0206703 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003761 | 427803074-40190-DETAIL-03_11_2025-GO95HV-1^06239003.0362701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003762 | 427949119-49389-DETAIL-08_20_2024-GO95MLD-1^06245005.0251500 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003763 | 428116512-89829-DTLSB-08_24_2023-GUYNOINS-2^06243008.0172701 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003764 | 428328301-17859-DETAIL-05_09_2022-GO95TCH-1^07116001.0096200 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003765 | 428451926-33189-DETAIL-04_02_2024-GO95HV-1^06247005.0355800 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003766 | 428451926-33189-DETAIL-04_02_2024-GO95MLD-1^06247005.0355800 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003767 | 428786964-27789-DTLSB-07_26_2023-GO95MLD-1^06243009.0055703 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003768 | 429009674-39229-DTLSB-08_16_2023-GO95HV-1^06243010.0134201 | OTHER | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003769 | 429355164-96229-DTLSB-08_09_2023-GO95HV-1^06243010.0135000 | OTHER | HFTD Tier 2 | Distribution | 2023-08-09 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003770 | 429503430-89089-DTLSB-04_22_2024-SVCWIND-1^06245007.0226204 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003771 | 429722294-73769-DTLTRT-11_03_2023-GO95HV-1^668010/00 16/036 | OTHER | Non-HFTD | Transmission | 2023-11-03 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003772 | 429722294-73769-DTLTRT-11_03_2023-GO95MLD-1^668010/00 16/036 | OTHER | Non-HFTD | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003773 | 430222243-74243-DETAIL-04_29_2024-GO95MLD-1^06142016.0079701 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003774 | 430432817-9870-DETAIL-02_26_2025-SVCNEUT-1^06240004.0064102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003775 | 430435399-96809-DTLSB-09_05_2024-GRDRODHI-1^06245007.0030200 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003776 | 430567674-79759-DETAIL-06_05_2024-GO95HV-1^06246006.0269900 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003777 | 430567674-79759-DETAIL-06_05_2024-GO95MLD-1^06246006.0269900 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003778 | 430567674-79759-DETAIL-06_05_2024-RISEGRD-1^06246006.0269900 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003779 | 430654364-78000-DETAIL-03_20_2025-GO95HV-1^06240003.0367009 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003780 | 431388547-64859-DETAIL-10_14_2024-SVCROOF-1^07216001.0200302 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003781 | 431742565-28480-DETAIL-04_24_2024-GO95HV-1^06145001.0090900 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003782 | 431894752-66450-DETAIL-02_06_2025-GO95MLD-1^06239004.0136209 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003783 | 432036220-84132-DETAIL-06_27_2023-ABNDEQPM-1^06244009.0272000 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003784 | 432056949-10049-DETAIL-02_19_2024-CLRTOUCH-1^07216001.0260302 | CONDUCTOR | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003785 | 432147944-31880-DTLSB-05_08_2024-GO95MLD-1^06245001.0337200 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003786 | 432227390-24159-DETAIL-05_17_2022-CLRTOUCH-1^07117001.0319301 | CONDUCTOR | Non-HFTD | Distribution | 2022-05-17 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003787 | 476848521-28930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 9A/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-26 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003788 | 477324764-16910-DETAIL-03_13_2025-GO95HV-1^06238004.0155001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003789 | 477534173-76059-DTLSB-09_30_2024-GO95MLD-1^06245007.0232501 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003790 | 477569103-45841-DETAIL-10_21_2024-ENCHRW-1^07216001.0209541 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003791 | 477594402-61321-DTLTRT-10_16_2023-GO95HV-1^668010/00 10/002 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003792 | 477829791-61731-DETAIL-02_27_2025-GO95MLD-1^06241005.0176601 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003793 | 477866860-17589-DETAIL-06_24_2024-GO95MLD-1^06244005.0230300 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003794 | 478100625-57551-DETAIL-02_19_2025-GO95HV-1^06239004.0365906 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003795 | 478742443-54879-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 5/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003796 | 478834652-24370-DETAIL-01_13_2025-SVCDEFLC-1^06240004.0085300 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003797 | 479814795-7700-DETAIL-03_13_2025-GO95MLD-1^06239003.0242801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003798 | 480388800-93070-DETAIL-04_12_2023-GUYHINS-2^06240004.0166503 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003799 | 480741445-67551-DRONE_HY-10_25_2023-GO95HV-1^668087/00 7/010 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003800 | 480939321-60421-DTLSB-02_09_2023-GO95MLD-1^06247001.0129002 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003801 | 481344535-21100-DETAIL-03_25_2025-GO95HV-1^06239003.0019506 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003802 | 481480959-11359-DETAIL-05_31_2024-GO95MLD-1^06246005.0332401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003803 | 482014120-87609-DETAIL-11_02_2022-GO95HV-1^06246008.0105701 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003804 | 482443661-71980-DETAIL-03_19_2025-GO95HV-1^06239001.0068600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003805 | 482476655-94870-DETAIL-01_22_2025-GO95BLTC-1^06239004.0254401 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003806 | 482513970-82470-DTLTRT-10_26_2022-GO95MLD-1^668075/00 4/028 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003807 | 432779741-22841-DETAIL-03_28_2023-GO95MLD-1^06142016.0053500 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003808 | 432934463-27659-DTLSB-02_14_2024-SVCENTCO-1^07216001.0180201 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003809 | 433030430-14313-DETAIL-10_01_2024-GUYHINS-1^06245007.0230440 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003810 | 433143543-67559-DETAIL-04_03_2024-BIRDDMG-1^06247005.0299900 | POLE | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003811 | 433181375-54189-DTLSB-08_02_2023-SVCROAD-1^06243010.0132101 | OTHER | HFTD Tier 2 | Distribution | 2023-08-02 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003812 | 433323321-31201-DETAIL-01_21_2025-GO95HV-1^06239004.0255441 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003813 | 43337213-43660-DETAIL-09_09_2024-SVCDEFLC-1^06240004.0097142 | OTHER | HFTD Tier 2 | Distribution | 2024-09-09 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003814 | 433449734-53030-DETAIL-04_13_2023-GUYNOINS-1^668002/00 9A/058 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-04-13 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003815 | 433478259-99279-DETAIL-01_24_2023-GO95MLD-1^06148003.0257601 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003816 | 433587888-81823-DETAIL-03_20_2023-GRDRODHI-1^07117003.0016800 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003817 | 434147539-20639-DTLSB-08_02_2023-GO95TCH-1^06243010.0132143 | OTHER | HFTD Tier 2 | Distribution | 2023-08-02 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003818 | 434186291-4580-DETAIL-02_27_2025-GO95HV-1^06240004.0137201 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003819 | 434408098-90330-DETAIL-01_22_2025-CLMBHAZ-1^06240004.0089505 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003820 | 434662124-23539-DETAIL-03_20_2023-GO95MLD-1^07114001.0283307 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003821 | 435225684-93749-DTLSB-02_06_2024-SVCDEFLC-1^07216001.0308802 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003822 | 435550228-94213-DETAIL-10_14_2024-SVCENTCO-1^07216001.0203241 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003823 | 436095978-98443-DTLSB-04_30_2024-GO95MLD-1^06245007.0222844 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003824 | 436095978-98443-DTLSB-04_30_2024-GRDRODHI-1^06245007.0222844 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003825 | 436195543-58549-DETAIL-03_14_2023-GO95MLD-1^07114001.0275401 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003826 | 436195543-58549-DETAIL-03_14_2023-GUYHINS-1^07114001.0275401 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003827 | 436258503-70769-DTLTRT-06_08_2021-GO95HV-1^668041/00 9/010 | OTHER | Non-HFTD | Transmission | 2021-06-08 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003828 | 43656915-52269-DTLTRT-07_05_2022-GO95HV-1^668005/00 3/034 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003829 | 436755503-15359-DETAIL-06_18_2024-SVCDEFLC-1^06245007.0290502 | OTHER | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003830 | 437006698-8789-DETAIL-08_14_2024-GO95MLD-1^06245005.0344801 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003831 | 437145996-22979-DETAIL-04_02_2024-BIRDDMG-1^06247005.0355701 | POLE | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003832 | 483051691-91149-DETAIL-02_20_2024-GO95MLD-1^07113001.0138207 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003833 | 48312819-8173-DETAIL-01_21_2025-SVCDEFLC-1^06240004.0092403 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003834 | 483513959-37510-DETAIL-02_20_2025-SVCROAD-1^06241005.0262200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-20 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003835 | 484229379-87459-DETAIL-03_01_2023-SVCWIND-2^07216001.0291840 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003836 | 484744975-43139-DETAIL-02_27_2024-GO95BLTC-1^07113002.0183704 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003837 | 484744975-43139-DETAIL-02_27_2024-GO95MLD-1^07113002.0183704 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003838 | 484750784-89190-DETAIL-03_27_2025-GO95HV-1^06239003.0019615 | OTHER | Non-HFTD | Distribution | 2025-03-27 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003839 | 485044246-42649-DETAIL-10_09_2024-GO95TCH-1^07216001.0202101 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003840 | 485419896-8599-DTLSB-08_29_2023-GO95MLD-1^06243009.0120302 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003841 | 485683589-83151-DETAIL-04_11_2024-GO95MLD-1^06245002.0105401 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003842 | 485712455-33455-DETAIL-03_20_2025-GO95HV-1^06239003.0019103 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003843 | 485899803-93351-DTLSB-03_30_2022-ABNDEQPM-1^06144006.0194900 | OTHER | Non-HFTD | Distribution | 2022-03-30 | 2027-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003844 | 486203933-35583-DTLSB-10_02_2024-GO95MLD-1^06245007.0218442 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003845 | 486332351-17699-DETAIL-07_01_2024-BIRDDMG-1^06245007.0308600 | POLE | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003846 | 486362114-36114-DETAIL-03_27_2023-GO95MLD-1^06142016.0082803 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003847 | 486681426-49751-DETAIL-04_18_2024-XARMSPCR-1^06145001.0250100 | CROSSARM | Non-HFTD | Distribution | 2024-04-18 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003848 | 486945200-76369-DTLTRT-06_15_2021-GO95HV-1^668041/00 20/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003849 | 48696194-70649-DTLSB-02_06_2024-SVCENTCO-1^07216001.0309915 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003850 | 487099943-38749-DETAIL-03_20_2023-GO95MLD-1^07114001.0206200 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003851 | 487102007-97038-DETAIL-03_05_2025-GO95MLD-1^06241005.0120400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003852 | 487176771-3249-DETAIL-05_09_2022-GO95GUYP-1^07116001.0097001 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003853 | 487638511-16461-DETAIL-05_06_2024-CLRTOUCH-1^06142012.0124000 | CONDUCTOR | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003854 | 487638511-16461-DETAIL-05_06_2024-GO95MLD-1^06142012.0124000 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003855 | 487638511-16461-DETAIL-05_06_2024-SVCENTCO-1^06142012.0124000 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003856 | 48774962-96340-DTLTRT-10_03_2023-GO95MLD-1^668010/00 15/030 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003857 | 437288913-44899-DETAIL-07_24_2024-GO95BLTC-1^06244005.0251001 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003858 | 437288913-44899-DETAIL-07_24_2024-GO95MLD-1^06244005.0251001 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003859 | 437353-70453-DETAIL-03_23_2023-GO95MLD-1^06142016.0081800 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003860 | 437364738-18269-AUDIT-08_02_2022-GUYNOINS-1^668005/00 4/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-02 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003861 | 437364738-18269-AUDIT-08_02_2022-GUYSLACK-1^668005/00 4/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-02 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003862 | 437624993-41790-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355003 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003863 | 437836708-24190-DETAIL-01_28_2025-SVCROAD-1^06239004.0244414 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003864 | 438162054-86753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003865 | 43894121-2440-DETAIL-04_18_2024-GO95HV-1^06145001.0239400 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003866 | 440253883-94883-DTLSB-10_01_2024-GO95MLD-1^06245007.0219303 | OTHER | Non-HFTD | Distribution | 2024-10-01 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003867 | 440289785-90139-DETAIL-03_09_2023-GUYHINS-1^07216001.0295502 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003868 | 440374834-34090-AUDIT-09_24_2020-GUYSLACK-1^06147001.0309500 | ANCHOR/GUY | Non-HFTD | Distribution | 2020-09-24 | 2023-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003869 | 440715359-60330-DRONE_HY-10_20_2023-BIRDWST-1^668033/00 5/027 | OTHER | HFTD Tier 2 | Transmission | 2023-10-20 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003870 | 440857035-80579-DETAIL-04_04_2024-GO95MLD-1^06147005.0147003 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003871 | 44096745-55733-DETAIL-03_01_2023-GUYHINS-1^07117002.0195207 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003872 | 441061738-41699-DETAIL-03_21_2024-GO95MLD-1^06245006.0015000 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003873 | 441242436-21329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120400 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003874 | 441402419-25939-DTLSB-02_15_2024-GO95MLD-1^07216001.0191801 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003875 | 441500625-34990-DETAIL-10_25_2024-GO95MLD-1^07216001.0209701 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003876 | 441561129-85990-ADMIN-04_11_2024-CUTOUTAR-1^06245002.0102201 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003877 | 441659173-66249-DETAIL-03_20_2023-GO95HV-1^07114001.0206202 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003878 | 441741956-27323-DTLSB-04_25_2024-GO95MLD-1^06245007.0229342 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003879 | 441753055-25269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 6/041 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003880 | 441753055-25269-DTLTRT-10_10_2023-GUYHINS-1^668010/00 6/041 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003881 | 441941135-65199-DETAIL-08_06_2024-GO95MLD-1^06245004.0328700 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003882 | 487801246-36889-DETAIL-03_27_2024-GO95HV-1^06247005.0324500 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003883 | 487928014-66039-DETAIL-02_08_2024-SVCDEFLC-1^07216001.0197001 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003884 | 487928014-66039-DETAIL-02_08_2024-SVCDEFLC-2^07216001.0197001 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003885 | 487940592-68829-DTLSB-08_24_2023-GO95HV-1^06243008.0186501 | OTHER | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003886 | 488321221-37579-DTLTRT-10_03_2023-GUYHINS-1^668010/00 7/030 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003887 | 488387883-23161-DETAIL-02_02_2023-GO95HV-1^06148002.0337402 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003888 | 48849061-13161-DETAIL-03_30_2023-GO95MLD-1^06142016.0054008 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003889 | 48849061-13161-DETAIL-03_30_2023-SVCENTCO-1^06142016.0054008 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003890 | 48878833-48450-DETAIL-02_09_2023-GO95MLD-1^06146004.0083000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003891 | 489028868-99549-DTLSB-04_11_2024-SVCWIND-1^06245007.0223200 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003892 | 489594245-40009-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207900 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003893 | 489599633-18061-DETAIL-05_23_2024-GO95HV-1^06243001.0117000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003894 | 489624481-3480-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0167201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003895 | 490261355-84449-DETAIL-07_29_2024-GO95HV-1^06245006.0111903 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003896 | 490286938-44849-DTLSB-02_20_2024-GO95MLD-1^07216001.0261510 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003897 | 490469561-75419-DTLSB-11_08_2021-SVCENTBK-1^06148004.0310103 | OTHER | Non-HFTD | Distribution | 2021-11-08 | 2024-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003898 | 490558594-68690-DETAIL-03_11_2025-GO95HV-1^06239003.0364400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003899 | 490662889-14861-DETAIL-04_24_2024-GO95HV-1^06145001.0061600 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003900 | 490847043-47339-DETAIL-03_14_2023-GO95MLD-1^07114001.0276401 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003901 | 490899301-13469-DTLTRT-06_16_2021-GUYNOINS-1^668041/00 12/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-16 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003902 | 490899301-13469-DTLTRT-06_16_2021-GUYNOINS-2^668041/00 12/023 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-16 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003903 | 491730549-57699-DTLSB-10_02_2024-GRDRODHI-1^06245007.0217603 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003904 | 491923554-88471-DTLSB-07_31_2023-GO95MLD-1^06243009.0085200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003905 | 491941609-74609-DETAIL-03_05_2025-GO95BLTC-1^06241005.0121201 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003906 | 492459089-9659-DETAIL-10_08_2024-SVCDEFLC-1^07216001.0201142 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003907 | 442817059-19901-DTLSB-05_07_2024-GO95MLD-1^06245002.0249601 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003908 | 442901273-28541-DETAIL-03_04_2025-ABNDEQPM-1^06241005.0130602 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003909 | 443289285-61940-DETAIL-03_04_2025-SVCROAD-1^06240004.0150541 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003910 | 44337409-4809-DTLSB-02_13_2023-GO95HV-1^06248001.0229140 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003911 | 44337409-4809-DTLSB-02_13_2023-GO95MLD-1^06248001.0229140 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003912 | 443596434-49549-DTLSB-02_08_2024-GO95HV-1^07216001.0308907 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003913 | 444299331-49020-DETAIL-03_06_2025-GO95HV-1^06240004.0273400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003914 | 444321159-17949-DTLSB-02_15_2024-GO95MLD-1^07216001.0264302 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003915 | 444413776-68259-DETAIL-03_28_2024-GO95MLD-1^06247005.0332900 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003916 | 444479671-78520-DETAIL-03_07_2023-GO95MLD-1^07117002.0210400 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003917 | 444984389-54359-DETAIL-05_30_2024-GO95HV-1^06246005.0273600 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003918 | 445323300-46870-DETAIL-04_12_2023-GO95MLD-1^06240004.0166705 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003919 | 445452261-78380-DETAIL-02_13_2025-SVCNEUT-1^06240004.0169103 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003920 | 445670743-63350-DETAIL-02_04_2025-GO95MLD-1^06239004.0134040 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003921 | 445947593-71693-DETAIL-04_29_2024-GO95MLD-1^06142016.0067902 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003922 | 446094741-58839-DETAIL-02_22_2024-GO95MLD-1^07113001.0099300 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003923 | 446507549-13969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 6/018 | POLE | Non-HFTD | Transmission | 2021-02-24 | 2024-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003924 | 446876554-91619-ADMIN-08_05_2024-GO95STUB-1^06240009.0012900 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003925 | 446973929-17229-DETAIL-05_02_2024-GRDRODHI-1^06142012.0126200 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003926 | 446973929-17229-DETAIL-05_02_2024-GRDRODHI-2^06142012.0126200 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003927 | 446987080-60532-DETAIL-06_15_2023-GO95MLD-1^06244009.0337100 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003928 | 447250159-53489-DETAIL-01_26_2023-CONDFRAY-1^06148003.0174100 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003929 | 447272931-13680-DETAIL-03_17_2025-GO95HV-1^06239001.0035902 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003930 | 447356069-77501-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0123006 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003931 | 447599478-60349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061701 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003932 | 447599478-60349-DETAIL-03_18_2024-GUYNOINS-1^06245005.0061701 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003933 | 492637204-88361-DETAIL-10_22_2024-GO95MLD-1^07216001.0208400 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003934 | 492721431-97709-DETAIL-10_27_2022-GO95HV-1^06246008.0069800 | OTHER | HFTD Tier 2 | Distribution | 2022-10-27 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003935 | 493170804-63661-DTLSB-02_09_2023-GO95HV-1^06248001.0277600 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003936 | 493223865-85661-DETAIL-02_07_2023-GO95HV-1^06147002.0096300 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003937 | 493535233-67009-DTLTRT-11_07_2022-GO95HV-1^668001/00 9/030 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003938 | 494037606-87149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297606 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003939 | 494037606-87149-DETAIL-03_06_2023-GUYHINS-1^07216001.0297606 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003940 | 494255073-43770-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 4/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003941 | 494255073-90202-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 4/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003942 | 494465451-27850-DETAIL-03_11_2025-GO95MLD-1^06238004.0271641 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003943 | 494612864-49932-DETAIL-03_06_2025-GO95MLD-1^06241005.0120106 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003944 | 494612864-49932-DETAIL-03_06_2025-GO95TCH-1^06241005.0120106 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003945 | 495057918-2499-DETAIL-03_18_2024-GO95MLD-1^06246005.0076200 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003946 | 495129637-40999-DTLSB-08_22_2024-GUYNOINS-1^06245006.0325200 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003947 | 495424004-88909-DTLSB-04_23_2024-GO95MLD-1^06245007.0223803 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003948 | 496099979-56873-DETAIL-03_07_2023-GO95MLD-1^07117002.0209701 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003949 | 496205858-43070-DETAIL-01_23_2025-BIRDDMG-1^06240004.0083200 | POLE | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003950 | 496393146-35171-DTLSB-05_14_2024-GO95MLD-1^06244001.0298300 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003951 | 496669835-87449-DTLSB-04_24_2024-GO95MLD-1^06245007.0224605 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003952 | 496721361-78479-DTLSB-08_27_2024-GO95MLD-1^06245007.0119702 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003953 | 447676106-40318-DETAIL-05_09_2022-GO95MLD-1^07116001.0098104 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003954 | 447873574-51313-DTLSB-04_25_2024-GO95MLD-1^06245007.0228541 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003955 | 448333921-5359-DETAIL-02_22_2024-GUYNOINS-1^07113001.0094600 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003956 | 448480791-19770-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 1/002 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003957 | 448681668-16549-DETAIL-03_09_2023-GO95MLD-1^07117002.0207242 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003958 | 448704470-43069-DTLTRT-07_15_2022-GO95HV-1^668005/00 2/047 | OTHER | Non-HFTD | Transmission | 2022-07-15 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003959 | 449028924-72601-DTLSB-05_08_2024-GO95MLD-1^06245001.0334500 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003960 | 449399538-79639-DETAIL-02_28_2023-GO95TCH-1^07216001.0298742 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003961 | 449555437-83322-DTLSB-08_21_2023-GUYHINS-1^06243009.0222200 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-08-21 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003962 | 44967753-22849-DETAIL-03_14_2023-GO95MLD-1^07114001.0275402 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003963 | 449730821-39111-DETAIL-04_11_2024-GO95MLD-1^06245002.0141201 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003964 | 449795833-84669-DTLTRT-06_23_2021-UBPBXARM-1^668041/00 5/032 | CROSSARM | Non-HFTD | Transmission | 2021-06-23 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003965 | 450171963-49963-AUDIT-05_30_2024-GO95HV-1^06142016.0079801 | OTHER | HFTD Tier 2 | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003966 | 450243561-15520-DETAIL-03_07_2023-GO95MLD-1^07117002.0210401 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003967 | 450303289-64289-DETAIL-02_23_2023-GO95MLD-1^07216001.0295705 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003968 | 450345734-36359-DETAIL-02_26_2024-CUTOUTAR-1^07113001.0085501 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003969 | 450845986-35111-DETAIL-02_21_2023-GO95HV-1^06247002.0299700 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003970 | 45123079-71759-DETAIL-04_02_2024-BIRDDMG-1^06246005.0055201 | POLE | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003971 | 451436898-45269-DETAIL-07_29_2024-GO95MLD-1^06245006.0115401 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003972 | 451576193-1280-DETAIL-02_11_2025-GO95MLD-1^06240004.0356001 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003973 | 452358351-67211-DETAIL-04_11_2024-GO95MLD-1^06245002.0143501 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003974 | 452390701-73999-DTLTRT-11_07_2022-GO95MLD-1^668001/00 14/029 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003975 | 452583749-23289-DETAIL-01_24_2023-GO95HV-1^06148003.0257700 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003976 | 452680324-95429-DTLSB-07_26_2023-GO95HV-1^06243009.0055902 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003977 | 452868954-56550-DTLTRT-11_03_2023-BIRDDMG-1^668010/00 7/036 | POLE | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003978 | 496721361-78479-DTLSB-08_27_2024-POLETOP-1^06245007.0119702 | POLE | HFTD Tier 2 | Distribution | 2024-08-27 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003979 | 496787666-47371-DETAIL-03_09_2023-GO95MLD-1^07216001.0294606 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003980 | 497143546-91839-DETAIL-10_08_2024-GO95MLD-1^07216001.0200110 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003981 | 497402440-5559-DETAIL-03_08_2023-GO95MLD-1^07216001.0295506 | OTHER | Non-HFTD | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003982 | 497848275-3975-DETAIL-03_19_2025-GO95HV-1^06238004.0027201 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003983 | 498050742-38099-DETAIL-04_09_2024-SVCDEFLC-1^06147005.0220302 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003984 | 498050742-38099-DTLSB-02_27_2019-ENCHRW-1^06147005.0220302 | OTHER | Non-HFTD | Distribution | 2019-02-27 | 2022-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003985 | 498115248-66550-DETAIL-03_25_2025-SVCDEFLC-1^06239003.0018416 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003986 | 498179531-90631-DETAIL-03_27_2023-GO95HV-1^06142016.0052102 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003987 | 498488633-89171-DETAIL-02_09_2023-GO95TCH-1^06146004.0101000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003988 | 498820483-43471-DETAIL-04_24_2024-GO95HV-1^06245001.0019300 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003989 | 498916229-80129-DETAIL-05_07_2024-GO95MLD-1^06142012.0124203 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003990 | 498920231-60671-DTLSB-03_23_2022-CONDFRAY-1^06146005.0242100 | CONDUCTOR | Non-HFTD | Distribution | 2022-03-23 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003991 | 498990123-27239-DTLSB-02_13_2024-GO95MLD-1^07216001.0185102 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003992 | 499219948-27240-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 1/054 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003993 | 499339703-9149-DETAIL-05_11_2022-GO95HV-1^07117001.0321401 | OTHER | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003994 | 499366313-52159-DTLSB-02_27_2024-GO95MLD-1^07216001.0278806 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003995 | 499455563-69563-DETAIL-04_30_2024-GO95HV-1^06142016.0066000 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003996 | 499455563-69563-DETAIL-04_30_2024-GO95MLD-1^06142016.0066000 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130003997 | 499455563-69563-DETAIL-04_30_2024-SVCDEFLC-1^06142016.0066000 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003998 | 500511361-96859-DTLSB-02_15_2024-SVCENTCO-1^07216001.0261002 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130003999 | 500730446-68671-DETAIL-10_22_2024-CLRTOUCH-1^07216001.0207600 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004000 | 500768921-85130-DETAIL-01_29_2025-ABNDEQPM-1^06240004.0176701 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004001 | 500936573-54673-AUDIT-06_24_2024-ABNDEQPM-1^06145002.0065602 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004002 | 50100411-73450-DETAIL-04_11_2024-GO95MLD-1^06245002.0145100 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004003 | 45292561-51979-DTLSB-02_20_2023-GO95HV-1^06248001.0289200 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004004 | 45349666-55340-DETAIL-02_06_2023-GO95MLD-1^06147002.0070001 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004005 | 45351060-1970-DETAIL-03_20_2025-GO95HV-1^06239002.0023500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004006 | 45362327-13609-DTLSB-09_05_2024-GO95MLD-1^06245006.0074700 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004007 | 453827998-40949-DETAIL-08_01_2024-GO95MLD-1^06245006.0155900 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004008 | 45405953-85760-DETAIL-09_09_2024-SVCDEFLC-1^06240004.0097041 | OTHER | HFTD Tier 2 | Distribution | 2024-09-09 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004009 | 454355079-39289-DTLSB-09_05_2024-GO95MLD-1^06245007.0031102 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004010 | 45436659-38340-ADMIN-04_24_2024-ABNDEQPM-1^06145001.0057000 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004011 | 454372218-36069-DTLTRT-10_11_2023-GO95HV-1^668010/00 12/043 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004012 | 454407124-67911-DETAIL-03_20_2024-GO95MLD-1^06245001.0051301 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004013 | 454472038-51030-DETAIL-10_17_2023-GUYHINS-3^668010/00 13X/009 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-17 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004014 | 455056534-98629-DTLSB-09_07_2023-GO95HV-1^06243008.0118800 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004015 | 455102741-87670-DETAIL-02_19_2025-GO95MLD-1^06241005.0277900 | OTHER | HFTD Tier 3 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004016 | 455553348-76238-DETAIL-03_02_2023-SVCRUBLG-1^07216001.0298640 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004017 | 455857225-69749-DETAIL-03_15_2023-GUYNOINS-1^07114001.0326201 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004018 | 456136905-6659-DETAIL-10_24_2024-GUYHINS-1^07216001.0201703 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004019 | 456136905-6659-DETAIL-10_24_2024-GUYHINS-2^07216001.0201703 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004020 | 456261106-91106-DETAIL-01_29_2025-GO95MLD-1^06239004.0252601 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004021 | 456632136-80449-DETAIL-10_10_2024-GO95CL10-1^07216001.0201204 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004022 | 456954831-86809-DETAIL-03_11_2024-CONDFRAY-1^06147004.0037600 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004023 | 456954831-86809-DETAIL-03_11_2024-CONDFRAY-3^06147004.0037600 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004024 | 457278699-589-DETAIL-01_26_2023-GO95MLD-1^06148003.0209400 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004025 | 458028856-56359-DETAIL-10_24_2024-GUYLOINS-1^07216001.0204504 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004026 | 45827950-42629-DETAIL-05_02_2024-GO95MLD-1^06142012.0124202 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004027 | 458520984-14269-DTLTRT-10_11_2023-GO95MLD-1^668010/00 5/040 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004028 | 50100411-73450-DETAIL-04_11_2024-GRDRODHI-1^06245002.0145100 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004029 | 501094164-49164-DETAIL-04_25_2024-GO95HV-1^06142016.0175500 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004030 | 501094164-49164-DETAIL-04_25_2024-GO95MLD-1^06142016.0175500 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004031 | 5011500-83809-DTLSB-09_05_2024-GO95HV-1^06245007.0033001 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004032 | 501333150-12289-DETAIL-07_03_2024-GO95MLD-1^06244005.0230500 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004033 | 501551528-1340-DETAIL-01_30_2025-GUYHINS-1^06240004.0162705 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004034 | 501959531-9180-DETAIL-02_13_2025-SVCROAD-1^06240004.0168041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004035 | 502658221-62280-DETAIL-02_27_2025-GUYHINS-1^06240004.0236800 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004036 | 502753798-14989-DTLSB-08_22_2024-GO95MLD-1^06245006.0322701 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004037 | 503050223-22680-DETAIL-04_17_2023-GO95HV-1^06240004.0160803 | OTHER | HFTD Tier 2 | Distribution | 2023-04-17 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004038 | 50345243-93869-DTLTRT-06_07_2021-GO95HV-1^668041/00 3/012 | OTHER | Non-HFTD | Transmission | 2021-06-07 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004039 | 504011173-53839-DETAIL-03_14_2023-GO95HV-1^07114001.0276301 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004040 | 504011173-53839-DETAIL-03_14_2023-GO95MLD-1^07114001.0276301 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004041 | 504079304-981-DTLSB-02_07_2023-GO95HV-1^06248001.0157203 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004042 | 504118524-95789-DTLSB-01_30_2023-GO95HV-1^06248001.0257000 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004043 | 504335064-14969-DETAIL-03_08_2023-GO95HV-1^668002/00 4/034 | OTHER | HFTD Tier 2 | Transmission | 2023-03-08 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004044 | 504487824-7519-ADMIN-11_18_2022-POLEDERP-1^668005/00 11/094 | POLE | Non-HFTD | Transmission | 2022-11-18 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004045 | 505191313-6529-DTLSB-08_31_2023-GO95HV-1^06243007.0293401 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004046 | 505519414-65749-DTLSB-02_21_2024-SVCROAD-1^07216001.0260704 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004047 | 505584631-40849-DETAIL-03_06_2023-GO95MLD-1^07216001.0297702 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004048 | 505764733-29649-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292603 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004049 | 506152954-87519-ADMIN-11_18_2022-POLEDERP-1^668005/00 14/094 | POLE | Non-HFTD | Transmission | 2022-11-18 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004050 | 506249154-80149-DETAIL-03_16_2023-GO95MLD-1^07114001.0283304 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004051 | 506381461-87781-DETAIL-03_12_2024-SVCENTCO-1^06147004.0062900 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004052 | 506499844-53540-DTLTRT-10_02_2023-GO95HV-1^668010/00 10/034 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004053 | 506499844-53540-DTLTRT-10_02_2023-GO95MLD-1^668010/00 10/034 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004054 | 458684813-19080-DETAIL-02_25_2025-GO95TCH-1^06240005.0016102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004055 | 459355356-35770-DETAIL-02_04_2025-GO95HV-1^06239004.0258400 | OTHER | HFTD Tier 3 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004056 | 459397314-96159-DETAIL-08_21_2024-GRDRODHI-2^06246005.0269541 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004057 | 459658880-69930-DETAIL-04_19_2023-GO95BLTC-1^06240004.0177701 | OTHER | HFTD Tier 2 | Distribution | 2023-04-19 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004058 | 459658880-69930-DETAIL-04_19_2023-SVCDEFLC-1^06240004.0177701 | OTHER | HFTD Tier 2 | Distribution | 2023-04-19 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004059 | 459749658-39759-DTLSB-02_13_2024-GO95MLD-1^07216001.0187403 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004060 | 459960559-1859-DETAIL-03_13_2023-SVCENTCO-1^07216001.0291540 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004061 | 460647462-8450-DETAIL-02_06_2025-GO95MLD-1^06239004.0137201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004062 | 461159446-3340-DETAIL-02_24_2025-GO95TCH-1^06240004.0152600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004063 | 461243363-44151-DETAIL-03_05_2025-GO95HV-1^06241005.0131901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004064 | 461259343-85669-DTLSB-08_27_2024-SVCENTCO-1^06245007.0116400 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004065 | 461395779-30022-DETAIL-06_12_2023-GO95MLD-1^06244009.0363501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004066 | 461395779-30022-DETAIL-06_12_2023-GUYHINS-1^06244009.0363501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004067 | 461395779-30022-DETAIL-06_12_2023-GUYHINS-2^06244009.0363501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004068 | 461471540-61799-DETAIL-11_08_2022-GO95HV-1^06246008.0041400 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004069 | 461876334-62910-DETAIL-03_17_2025-GO95HV-1^06238004.0159100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004070 | 461995235-51939-DETAIL-03_07_2023-GUYHINS-1^07216001.0294509 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004071 | 462760441-14959-DETAIL-05_10_2022-GO95MLD-1^07116001.0093900 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004072 | 463143439-43349-DTLSB-02_16_2024-GO95CL10-1^07216001.0261105 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004073 | 463143439-43349-DTLSB-02_16_2024-SVCENTCO-1^07216001.0261105 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004074 | 46356594-49849-DETAIL-03_30_2023-GO95MLD-1^06142016.0084908 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004075 | 463782972-14049-DETAIL-10_10_2024-GO95MLD-1^07216001.0206103 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004076 | 46390553-65940-DTLTRT-05_22_2024-GO95HV-1^06243001.0103700 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004077 | 46390553-65940-DTLTRT-05_22_2024-GO95MLD-1^06243001.0103700 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004078 | 464075136-31572-DETAIL-08_08_2024-GO95HV-1^06245006.0091341 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004079 | 506795108-15890-DETAIL-01_30_2025-SVCENTCO-1^06239004.0245605 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004080 | 507026169-80430-DETAIL-01_19_2023-SVCDEFLC-1^06240004.0081800 | OTHER | HFTD Tier 2 | Distribution | 2023-01-19 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004081 | 507392402-40459-DETAIL-02_21_2024-GUYNOINS-1^07113001.0148102 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004082 | 507479578-82678-DETAIL-03_16_2023-ENCHRW-1^07113001.0043503 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004083 | 507596974-13259-DETAIL-05_16_2022-GUYNOINS-1^07117001.0317941 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004084 | 507691148-28469-DRONE_HY-09_14_2023-GO95HV-1^668002/00 12/012 | OTHER | Non-HFTD | Transmission | 2023-09-14 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004085 | 507782990-39579-DETAIL-07_24_2024-ABNDEQPM-1^06244005.0133104 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004086 | 507808541-38081-DTLTRT-03_26_2024-POLEDERP-1^668044/00 6/061 | POLE | HFTD Tier 2 | Transmission | 2024-03-26 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004087 | 508459694-5999-DETAIL-03_11_2024-COPLLEAN-1^06147005.0173001 | POLE | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004088 | 508561626-50039-DETAIL-10_14_2024-GO95MLD-1^07216001.0200305 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004089 | 508834588-32781-DETAIL-02_06_2023-GO95MLD-1^06148002.0285301 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004090 | 508853850-59870-DETAIL-03_20_2025-GO95HV-1^06239002.0022502 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004091 | 509377848-3130-ADMIN-11_09_2024-POLEREPL-1^668010/00 6/011 | POLE | HFTD Tier 2 | Transmission | 2024-11-09 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004092 | 509750759-6149-DETAIL-03_01_2023-GRDRODHI-1^07216001.0293502 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004093 | 509750759-6149-DETAIL-03_01_2023-SVCWIND-1^07216001.0293502 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004094 | 510319248-39248-DETAIL-02_27_2023-CLRTOPOL-1^07216001.0297970 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004095 | 510514978-56499-DETAIL-04_01_2024-GO95MLD-1^06147005.0090901 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004096 | 510533138-74138-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0298707 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004097 | 5107135-52339-DRONE_HY-10_25_2023-GO95HV-1^668087/00 5/010 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004098 | 510778048-46359-DETAIL-03_01_2023-GO95MLD-1^07216001.0292604 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004099 | 464110479-89409-DTLSB-09_04_2024-GO95MLD-1^06245007.0016502 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004100 | 464531090-11019-DTLTRT-08_03_2022-POLETOP-1^668005/00 9/079 | POLE | Non-HFTD | Transmission | 2022-08-03 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004101 | 464732963-51850-DETAIL-01_23_2025-GO95BLTC-1^06239004.0257703 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004102 | 465220879-15549-ADMIN-07_19_2024-POLETOP-1^06245007.0224008 | POLE | Non-HFTD | Distribution | 2024-07-19 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004103 | 465443938-7643-DETAIL-03_14_2023-GO95MLD-1^07117002.0205240 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004104 | 465495050-55549-DETAIL-08_12_2024-CLMBTRE-1^06245006.0105501 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004105 | 465495050-55549-DETAIL-08_12_2024-GO95HV-1^06245006.0105501 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004106 | 465586139-70631-ADMIN-07_12_2024-POLEDERP-1^668038/00 1/068 | POLE | Non-HFTD | Transmission | 2024-07-12 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004107 | 465614001-80979-DETAIL-07_18_2024-GUYHINS-1^06244004.0055300 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-18 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004108 | 465628368-26459-DETAIL-04_24_2023-GO95MLD-1^07117003.0029700 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004109 | 465698637-40788-DTLSB-02_15_2024-GO95MLD-1^07216001.0263303 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004110 | 465966115-97115-DETAIL-08_13_2024-GO95MLD-1^06245005.0362302 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004111 | 465966115-97115-DETAIL-08_13_2024-GRDRODHI-1^06245005.0362302 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004112 | 466059204-64973-DETAIL-03_04_2024-SVCROAD-1^06245007.0274342 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004113 | 466091993-84469-DETAIL-08_20_2024-GO95HV-1^06245005.0137101 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004114 | 466158954-38749-DETAIL-05_08_2023-GO95MLD-1^06245006.0213601 | OTHER | Non-HFTD | Distribution | 2023-05-08 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004115 | 46621629-90440-DETAIL-02_06_2025-GO95MLD-1^06239003.0061103 | OTHER | HFTD Tier 3 | Distribution | 2025-02-06 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004116 | 466280629-57569-DTLTRT-10_25_2023-GO95BLTC-1^668010/00 23/012 | OTHER | HFTD Tier 2 | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004117 | 466305094-64139-DTLSB-02_07_2024-GO95MLD-1^07216001.0199202 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004118 | 466781204-59824-DETAIL-08_15_2024-GO95HV-1^06246005.0135300 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004119 | 466794099-43759-DETAIL-03_26_2024-GO95HV-1^06246005.0055500 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004120 | 467191002-67880-DETAIL-02_12_2025-GO95HV-1^06240004.0320800 | OTHER | HFTD Tier 3 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004121 | 46739223-75743-DETAIL-08_15_2024-GO95HV-1^06246005.0125100 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004122 | 467893852-87459-DETAIL-02_29_2024-GO95MLD-1^07113001.0140801 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004123 | 467960938-26343-DETAIL-04_12_2023-SVCROOF-1^06240004.0166509 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004124 | 468051635-65539-DETAIL-02_27_2024-SVCDEFLC-1^07113002.0183601 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004125 | 510959010-90110-DETAIL-08_01_2024-GO95HV-1^06245006.0152900 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004126 | 510992750-11409-DETAIL-03_04_2024-GO95MLD-1^06147004.0027202 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004127 | 510992750-11409-DETAIL-03_04_2024-GO95TCH-1^06147004.0027202 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004128 | 511000839-75769-ADMIN-02_07_2022-POLEDERP-1^668005/03 9/004 | POLE | Non-HFTD | Transmission | 2022-02-07 | 2025-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004129 | 511000839-75769-DTLTRT-10_10_2022-GO95HV-1^668005/03 9/004 | OTHER | Non-HFTD | Transmission | 2022-10-10 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004130 | 511171685-56459-DETAIL-04_01_2024-GO95HV-1^06247005.0342700 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004131 | 511734559-69999-DETAIL-04_01_2024-EQUIPOIL-1^06147005.0097700 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004132 | 511734559-69999-DETAIL-04_01_2024-GRDRODHI-1^06147005.0097700 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004133 | 511838870-33389-DETAIL-03_05_2024-GO95HV-1^06147004.0025400 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004134 | 511942124-68049-DETAIL-03_20_2023-GO95MLD-1^07114001.0284305 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004135 | 512186983-81869-DETAIL-12_18_2024-BIRDDMG-1^668002/00 7/064 | POLE | HFTD Tier 2 | Transmission | 2024-12-18 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004136 | 512251033-1180-DETAIL-02_25_2025-GO95TCH-1^06240005.0018200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004137 | 512640620-35730-DETAIL-09_23_2024-SVCDEFLC-1^06240004.0085043 | OTHER | HFTD Tier 2 | Distribution | 2024-09-23 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004138 | 513036299-64759-DETAIL-03_26_2024-GO95MLD-1^06246005.0056502 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004139 | 513060900-28900-DETAIL-01_24_2023-GO95TCH-1^06147003.0129501 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004140 | 513193819-31471-DETAIL-02_25_2025-GO95BLTC-1^06241005.0152701 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004141 | 513494716-1789-DETAIL-06_04_2024-GO95HV-1^06245006.0037000 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004142 | 513733185-48749-DETAIL-03_15_2023-GO95HV-1^07114001.0327000 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004143 | 51453459-50559-DETAIL-03_01_2023-SVCWIND-1^07216001.0292541 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004144 | 51453459-50559-DETAIL-03_01_2023-SVCWIND-2^07216001.0292541 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004145 | 514906151-66491-DETAIL-04_15_2024-GO95MLD-1^06145002.0066900 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004146 | 515129484-30713-DTLSB-05_02_2024-GO95MLD-1^06245007.0229941 | OTHER | HFTD Tier 2 | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004147 | 515473601-38250-DETAIL-02_11_2025-GO95TCH-1^06239004.0124902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004148 | 515537798-29599-DETAIL-03_06_2025-GO95HV-1^06240004.0272140 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004149 | 515592158-19449-DTLSB-02_26_2024-GO95MLD-1^07216001.0260910 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004150 | 468051635-65539-DETAIL-02_27_2024-SVCENTCO-1^07113002.0183601 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004151 | 468210583-77431-DTLSB-05_28_2024-GO95MLD-1^06243001.0126200 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004152 | 468441008-76089-DTLSB-07_02_2024-GO95HV-1^06245006.0186401 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004153 | 469130392-70392-DTLSB-02_14_2023-GO95MLD-1^06248001.0228503 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004154 | 469294514-90331-DETAIL-04_17_2024-POLISSUE-1^06144001.0122302 | POLE | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004155 | 469547205-88205-DETAIL-02_22_2024-GO95MLD-1^07113001.0154603 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004156 | 469609428-95149-DETAIL-10_08_2024-GO95MLD-1^07216001.0202001 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004157 | 46963070-35070-DETAIL-03_03_2025-SVCROAD-1^06241005.0132600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004158 | 469656106-52336-DETAIL-09_27_2021-SVCROOF-1^06148004.0355204 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004159 | 470074563-71409-DETAIL-07_15_2024-GO95MLD-1^06244005.0250400 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004160 | 470152070-39501-DETAIL-02_04_2025-GO95HV-1^06239004.0135104 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004161 | 470259067-72959-DETAIL-04_08_2024-GO95BLTC-1^06247005.0322103 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004162 | 470507685-98731-DETAIL-10_22_2024-GUYHINS-1^07216001.0207902 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004163 | 47052694-30390-DETAIL-03_27_2025-GO95HV-1^06239003.0019704 | OTHER | Non-HFTD | Distribution | 2025-03-27 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004164 | 470877513-75769-DTLTRT-06_07_2021-GO95HV-1^668041/00 4/011 | OTHER | Non-HFTD | Transmission | 2021-06-07 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004165 | 471066426-64223-DTLSB-04_29_2024-GO95TCH-1^06245007.0221642 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004166 | 471231631-38020-DETAIL-02_20_2025-GO95HV-1^06241005.0265300 | OTHER | HFTD Tier 3 | Distribution | 2025-02-20 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004167 | 471443034-38441-DTLSB-05_07_2024-GO95MLD-1^06245001.0192100 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004168 | 471979003-98313-DTLSB-04_25_2024-GUYHINS-1^06245007.0227549 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004169 | 472007899-94509-DETAIL-09_04_2024-GO95MLD-1^06245007.0016602 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004170 | 472216851-78659-DETAIL-06_17_2024-GO95MLD-1^06246006.0239100 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004171 | 472253533-55452-DETAIL-06_26_2023-SVCENTCO-1^06244009.0301600 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004172 | 472316525-1549-DTLSB-05_06_2024-GO95MLD-1^06245007.0222702 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004173 | 472355173-88799-DETAIL-07_31_2024-GRDRODHI-1^06244005.0337903 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004174 | 472421554-14554-DETAIL-03_28_2023-GO95MLD-1^06142016.0083805 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004175 | 515995411-45939-DETAIL-07_10_2024-GO95HV-1^06244004.0190702 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004176 | 516286048-64149-DETAIL-10_14_2024-SVCRUBLG-1^07216001.0204209 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004177 | 516690116-30279-DETAIL-03_19_2025-GO95HV-1^06239001.0052702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004178 | 516954791-21780-DETAIL-03_21_2023-GO95MLD-1^06240004.0167415 | OTHER | HFTD Tier 2 | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004179 | 516957555-96289-DTLSB-08_28_2024-SVCDEFLC-1^06245007.0142802 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004180 | 518343826-80990-DETAIL-02_11_2025-GO95BLTC-1^06240004.0351602 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004181 | 518343826-80990-DETAIL-02_11_2025-GO95MLD-1^06240004.0351602 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004182 | 518348083-17624-DETAIL-04_25_2024-GO95MLD-1^06142016.0175602 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004183 | 518448879-61701-DETAIL-04_11_2024-GO95HV-1^06245002.0105400 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004184 | 51851028-8899-DETAIL-08_06_2024-GO95MLD-1^06245006.0155002 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004185 | 519495024-30760-DETAIL-01_15_2025-SVCDEFLC-1^06240004.0095203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004186 | 519642461-72849-DTLSB-02_15_2024-GO95MLD-1^07216001.0263001 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004187 | 520050671-52620-DETAIL-03_08_2023-GO95MLD-1^07117002.0211102 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004188 | 52041733-12330-DETAIL-01_28_2025-GO95CL10-1^06240004.0172941 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004189 | 52041733-12330-DETAIL-01_28_2025-GO95HV-1^06240004.0172941 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004190 | 520498651-42701-DETAIL-03_13_2024-GO95MLD-1^06147004.0085101 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004191 | 520575753-22953-DETAIL-10_12_2022-GO95HV-1^668005/08 8X8/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004192 | 520575753-22953-DETAIL-10_12_2022-GUYHINS-1^668005/08 8X8/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004193 | 520575753-22953-DETAIL-10_12_2022-GUYHINS-2^668005/08 8X8/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004194 | 520575753-22953-DETAIL-10_12_2022-GUYHINS-3^668005/08 8X8/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004195 | 520611664-29040-DRONE_HY-10_27_2023-GO95HV-1^668033/00 4/037 | OTHER | HFTD Tier 2 | Transmission | 2023-10-27 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004196 | 52090185-62549-DETAIL-10_14_2024-GO95MLD-1^07216001.0203304 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004197 | 52090185-62549-DETAIL-10_14_2024-SVCNEUT-1^07216001.0203304 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004198 | 52110716-17219-DETAIL-03_25_2024-GO95HV-1^06147005.0133900 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004199 | 521528359-71401-DETAIL-05_02_2024-GO95MLD-1^06142012.0127200 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004200 | 472653794-60894-DETAIL-03_30_2023-ABNDEQPM-1^06142016.0084909 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004201 | 473741008-68290-DETAIL-01_28_2025-GO95HV-1^06239004.0245102 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004202 | 47426518-50760-DETAIL-10_21_2024-BIRDDMG-1^668014/00 6/053 | POLE | HFTD Tier 3 | Transmission | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004203 | 474340058-70830-DETAIL-02_17_2025-GUYHINS-1^06240003.0313602 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004204 | 474617379-66712-DETAIL-07_05_2023-GO95MLD-1^06244009.0241900 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004205 | 474681442-63370-DETAIL-01_13_2025-SVCDEFLC-1^06240004.0085301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004206 | 474687708-67760-DRONE_HY-10_18_2023-GO95HV-1^668033/00 15/004 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004207 | 475272653-3629-DETAIL-05_15_2024-GO95HV-1^06142012.0123900 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004208 | 475715194-79032-DETAIL-03_06_2025-GO95HV-1^06241005.0120402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004209 | 476126851-29-ADMIN-07_10_2024-POLEREPL-1^06243009.0137001 | POLE | Non-HFTD | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004210 | 476131988-88590-DETAIL-01_16_2025-GO95HV-1^06239004.0257304 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004211 | 476316491-64480-AUDIT-02_18_2025-SVCDEFLC-1^06240004.0169411 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004212 | 476316491-64480-DETAIL-02_11_2025-BIRDDMG-1^06240004.0169411 | POLE | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004213 | 476765740-54371-DETAIL-03_10_2025-GO95HV-1^06241005.0242300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004214 | 476778304-37141-DETAIL-10_16_2024-GO95MLD-1^07216001.0206703 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004215 | 476905423-68949-DETAIL-03_14_2023-SVCENTCO-1^07114001.0276408 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004216 | 477084618-7299-DTLSB-07_02_2024-GO95MLD-1^06245006.0183100 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004217 | 477913606-33606-DETAIL-01_29_2025-GO95MLD-1^06239004.0230101 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004218 | 478034988-33141-DTLSB-05_13_2024-GO95MLD-1^06244001.0225600 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004219 | 478080814-59140-DETAIL-02_26_2025-SVCDEFLC-1^06240004.0218941 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004220 | 478136715-98715-DETAIL-02_03_2025-BIRDDMG-1^06239004.0243801 | POLE | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004221 | 478136715-98715-DETAIL-02_03_2025-GO95TCH-1^06239004.0243801 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004222 | 478742443-54879-DTLTRT-10_03_2023-GO95MLD-1^668010/00 5/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004223 | 478822603-76299-DTLSB-08_29_2023-GO95MLD-1^06243009.0121102 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004224 | 479322483-92259-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0345004 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004225 | 521592954-85528-DTLSB-02_27_2024-GO95MLD-1^07216001.0278600 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004226 | 521645673-17589-ADMIN-03_05_2025-POLEREPL-1^06245007.0274202 | POLE | Non-HFTD | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004227 | 521679055-47889-AUDIT-02_06_2023-GO95MLD-1^06148004.0184203 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004228 | 521868119-64689-DETAIL-06_15_2022-GO95MLD-1^07116007.0112808 | OTHER | HFTD Tier 2 | Distribution | 2022-06-15 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004229 | 521914780-95079-ADMIN-01_23_2025-POLEREPL-1^06244007.0081302 | POLE | HFTD Tier 2 | Distribution | 2025-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004230 | 521921853-57460-DRONE_VS-11_13_2024-INSULBRK-2^668014/00 7/036 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004231 | 521921853-92230-DRONE_VS-11_13_2024-INSULBRK-1^668014/00 7/036 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004232 | 521970284-30049-ADMIN-03_18_2024-POLEDERP-1^07113001.0175500 | POLE | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004233 | 522216004-5101-DETAIL-10_16_2024-GO95MLD-1^07216001.0209805 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004234 | 522266978-59450-DETAIL-01_16_2025-RISEBKSP-1^06240004.0097506 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004235 | 522815991-43663-DETAIL-04_22_2024-SVCWIND-1^06245007.0226247 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004236 | 522815991-43663-DETAIL-04_22_2024-SVCWIND-2^06245007.0226247 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004237 | 523183484-39679-DETAIL-08_14_2024-GO95MLD-1^06246005.0254800 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004238 | 523318908-52209-AUDIT-03_21_2024-GRDRODHI-1^06147004.0010300 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004239 | 523657688-80369-DTLTRT-07_05_2022-GO95HV-1^668005/00 10/035 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004240 | 524180865-90411-DTLSB-05_14_2024-GO95MLD-1^06244001.0203200 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004241 | 524251424-72411-DETAIL-10_21_2024-GO95HV-1^07216001.0209403 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004242 | 524380824-34162-DETAIL-07_31_2024-GO95MLD-1^06244005.0340940 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004243 | 524825426-92279-DRONE_HY-10_16_2023-GO95HV-1^668033/00 10/002 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004244 | 52499796-8080-DETAIL-01_23_2025-GO95HV-1^06239004.0256647 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004245 | 525122080-85789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154100 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004246 | 525658313-52979-DETAIL-07_11_2024-GO95HV-1^06244005.0263400 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004247 | 525950083-71779-DETAIL-04_04_2024-SVCWIND-1^06247005.0280300 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004248 | 526314881-5881-DETAIL-06_26_2024-GO95MLD-1^06244005.0234840 | OTHER | Non-HFTD | Distribution | 2024-06-26 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004249 | 526515324-61311-DETAIL-02_09_2023-GO95HV-1^06146004.0161901 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004250 | 526515324-61311-DETAIL-02_09_2023-GO95MLD-1^06146004.0161901 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004251 | 526594585-10411-DETAIL-02_07_2023-GO95HV-1^06147002.0047400 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004252 | 526808584-66611-DETAIL-10_16_2024-GO95MLD-1^07216001.0207705 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004253 | 526880731-61680-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0169045 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004254 | 526912313-53519-DTLTRT-08_17_2022-POLETOP-1^668005/00 12/093 | POLE | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004255 | 479447529-99289-ADMIN-01_29_2025-POLEREPL-1^06245007.0106902 | POLE | HFTD Tier 2 | Distribution | 2025-01-29 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004256 | 479447529-99289-DTLSB-07_22_2024-GO95MLD-1^06245007.0106902 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004257 | 479946719-71824-DETAIL-03_14_2023-GUYHINS-1^07117003.0114800 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004258 | 479946719-71824-DETAIL-03_14_2023-SVCNEUT-1^07117003.0114800 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004259 | 480089259-27370-DETAIL-02_27_2025-SVCENTCO-1^06240004.0063206 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004260 | 480153809-88849-DETAIL-03_02_2023-GO95MLD-1^07216001.0293909 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004261 | 480153809-88849-DETAIL-03_02_2023-SVCWIND-1^07216001.0293909 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004262 | 480338063-14251-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049201 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004263 | 480457126-60470-DETAIL-01_23_2025-GO95HV-1^06239004.0256649 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004264 | 480457126-60470-DETAIL-01_23_2025-GO95MLD-1^06239004.0256649 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004265 | 480501319-37749-AUDIT-10_31_2024-BIRDDMG-1^06245005.0354903 | POLE | Non-HFTD | Distribution | 2024-10-31 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004266 | 480543533-27249-DETAIL-03_16_2023-GO95HV-1^07114001.0206003 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004267 | 480678930-34201-DETAIL-01_21_2025-SVCDEFLC-1^06239004.0255344 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004268 | 480745162-87551-DTLSB-02_13_2023-GO95MLD-1^06248001.0278301 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004269 | 480846998-36139-DETAIL-04_04_2024-SVCDEFLC-1^06244005.0149402 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004270 | 480886004-62979-DETAIL-01_23_2023-GO95MLD-1^06148004.0193200 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004271 | 481012290-73389-DETAIL-03_05_2024-GO95HV-1^06147004.0020301 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004272 | 48124436-90239-DETAIL-03_25_2024-GO95MLD-1^06244005.0141401 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004273 | 481345154-26759-DETAIL-06_05_2024-GO95MLD-1^06246006.0257800 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004274 | 48138651-29689-DETAIL-05_25_2023-ABNDEQPM-1^07117007.0226701 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004275 | 481388533-17051-DETAIL-02_08_2023-GO95MLD-1^06146004.0082000 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004276 | 481425531-89499-DETAIL-03_07_2024-GUYNOINS-1^06147004.0129200 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004277 | 481680938-21959-DETAIL-04_08_2024-GO95HV-1^06247005.0352401 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004278 | 482467499-89649-DTLSB-02_15_2024-GO95HV-1^07216001.0261001 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004279 | 482467499-89649-DTLSB-02_15_2024-GO95MLD-1^07216001.0261001 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004280 | 528097795-30711-DETAIL-04_24_2024-GO95MLD-1^06145001.0044001 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004281 | 528189395-53110-DETAIL-03_17_2025-PWRTRN-1^06238004.0114202 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004282 | 528843563-62749-DETAIL-02_29_2024-GO95MLD-1^07113001.0108000 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004283 | 528908345-69933-DETAIL-03_01_2023-GO95MLD-1^07117002.0195203 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004284 | 529057151-38859-DETAIL-06_05_2024-GO95BLTC-1^06246006.0269600 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004285 | 529580294-97269-DETAIL-08_05_2024-SVCENTCO-1^06244005.0119900 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004286 | 529762043-24703-DETAIL-05_30_2024-GO95HV-1^06246005.0150100 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004287 | 52980299-79129-DETAIL-04_29_2024-GO95MLD-1^06142016.0069005 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004288 | 530299381-79570-DETAIL-02_19_2025-GO95TCH-1^06241005.0277001 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004289 | 530345266-65770-DETAIL-01_22_2025-GO95TCH-1^06239004.0256652 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004290 | 530345266-65770-DETAIL-01_22_2025-SVCDEFLC-1^06239004.0256652 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004291 | 530394763-13640-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004292 | 530417675-35811-DETAIL-04_24_2024-GO95HV-1^06145001.0043000 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004293 | 531041253-98639-DTLSB-09_19_2022-GO95MLD-1^06243005.0113900 | OTHER | Non-HFTD | Distribution | 2022-09-19 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004294 | 53105629-78329-DTLTRT-10_25_2022-GO95HV-1^668075/00 13/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004295 | 531090416-62416-DETAIL-04_08_2024-GO95HV-1^06246005.0071101 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004296 | 531381153-79079-DETAIL-06_13_2022-GO95HV-1^07116007.0029002 | OTHER | HFTD Tier 2 | Distribution | 2022-06-13 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004297 | 531620854-11332-DETAIL-04_02_2025-SVCENTBK-1^06241005.0029201 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004298 | 531673428-54428-DETAIL-10_10_2024-SVCENTBK-1^07216001.0201201 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004299 | 531771324-29813-AUDIT-05_22_2024-RISEGRD-1^06245007.0228741 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004300 | 482476655-94870-DETAIL-01_22_2025-SVCDEFLC-1^06239004.0254401 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004301 | 482712803-38579-DETAIL-08_05_2024-GO95HV-1^06244005.0029200 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004302 | 482941889-17813-DETAIL-07_23_2024-GO95MLD-1^06245006.0144241 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004303 | 483552068-11999-DETAIL-04_02_2024-GO95MLD-1^06246005.0043600 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004304 | 484028070-65199-DETAIL-08_14_2024-ABNDEQPM-1^06245005.0360901 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004305 | 484049049-89951-DETAIL-04_11_2024-GUYNOINS-1^06245002.0102303 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004306 | 484229379-87459-DETAIL-03_01_2023-GO95MLD-1^07216001.0291840 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004307 | 484229379-87459-DETAIL-03_01_2023-SVCWIND-1^07216001.0291840 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004308 | 484367544-12940-DTLTRT-10_02_2023-GRDRODHI-1^668010/00 17/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004309 | 484414072-45929-DTLSB-08_30_2023-GO95MLD-1^06243008.0206900 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004310 | 484617093-7069-DETAIL-06_19_2024-SVCWIND-1^06245007.0340900 | OTHER | HFTD Tier 2 | Distribution | 2024-06-19 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004311 | 484652666-66959-DETAIL-03_27_2024-GO95HV-1^06247005.0322600 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004312 | 48488513-51839-DETAIL-07_08_2024-GO95HV-1^06244005.0017402 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004313 | 485044246-42649-DETAIL-10_09_2024-GO95MLD-1^07216001.0202101 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004314 | 485607465-60349-DETAIL-02_28_2023-GO95HV-1^07216001.0299804 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004315 | 486106306-22510-DETAIL-03_17_2025-GO95BLTC-1^06238004.0114001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004316 | 486288671-69470-DTLTRT-10_16_2023-GO95HV-1^668010/00 12/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004317 | 486435188-87459-DETAIL-06_03_2024-GO95MLD-1^06246005.0313000 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004318 | 486618418-24469-DETAIL-03_20_2024-GO95HV-1^06244005.0142001 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004319 | 486633364-60589-DTLSB-07_31_2023-GO95MLD-1^06243009.0085301 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004320 | 486856056-96650-DTLTRT-10_01_2020-GO95HV-1^668018/00 11/001 | OTHER | HFTD Tier 2 | Transmission | 2020-10-01 | 2025-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004321 | 487176771-3249-DETAIL-05_09_2022-GO95HV-1^07116001.0097001 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004322 | 487176771-3249-DETAIL-05_09_2022-GO95MLD-1^07116001.0097001 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004323 | 487176771-3249-DETAIL-05_09_2022-GUYHINS-1^07116001.0097001 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004324 | 48721808-21039-DETAIL-10_09_2024-GUYHINS-1^07216001.0200106 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004325 | 53205924-22750-DTLSB-02_06_2023-GO95HV-1^06248001.0259203 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004326 | 532146226-67979-DTLSB-01_31_2023-GO95MLD-1^06248001.0368803 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004327 | 532543651-20569-DRONE_HY-10_13_2023-GO95HV-1^668033/00 3/015 | OTHER | HFTD Tier 2 | Transmission | 2023-10-13 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004328 | 53254493-89930-DETAIL-02_27_2025-GO95HV-1^06240004.0066006 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004329 | 532703924-7721-DETAIL-10_25_2024-GO95MLD-1^07216001.0209907 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004330 | 532783999-41009-DETAIL-04_10_2024-GO95HV-1^06147005.0214901 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004331 | 533183332-77949-DETAIL-02_27_2024-GO95MLD-1^07113002.0183203 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004332 | 533297316-7121-DTLSB-08_29_2023-GO95MLD-1^06243009.0114800 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004333 | 533416511-96363-DTLSB-04_15_2024-SVCWIND-1^06245007.0224140 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004334 | 533487581-2052-DETAIL-06_26_2023-GO95MLD-1^06244009.0310701 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004335 | 533576029-66753-AUDIT-05_22_2024-SVCRUBLG-1^06245007.0226447 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004336 | 533580403-38079-DETAIL-06_11_2024-SVCDEFLC-1^06245007.0345104 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004337 | 533583131-83801-DETAIL-01_14_2025-SVCROAD-1^06239004.0255140 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004338 | 534020652-81821-DETAIL-05_15_2024-SVCDEFLC-1^06142012.0125800 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004339 | 534111173-54639-DTLSB-02_06_2024-GO95MLD-1^07216001.0308803 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004340 | 53425034-12810-DETAIL-03_13_2025-GO95HV-1^06238004.0152202 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004341 | 534340201-33780-DETAIL-03_19_2025-GO95HV-1^06239001.0062602 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004342 | 535141276-27399-DTLSB-09_05_2024-GO95HV-1^06245007.0237600 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004343 | 535308475-2139-DETAIL-03_13_2023-GO95MLD-1^07216001.0290700 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004344 | 535308475-2139-DETAIL-03_13_2023-GUYHINS-1^07216001.0290700 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004345 | 535548719-79719-DETAIL-03_04_2025-GO95TCH-1^06240004.0150001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004346 | 53572998-63998-DTLSB-02_08_2024-GO95HV-1^07216001.0309905 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004347 | 535947369-19979-DETAIL-04_11_2024-GO95HV-1^06245002.0102100 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004348 | 535947369-19979-DETAIL-04_11_2024-GO95MLD-1^06245002.0102100 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004349 | 535947369-19979-DETAIL-04_11_2024-POLISSUE-1^06245002.0102100 | POLE | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004350 | 536428272-83302-DETAIL-03_22_2023-GO95HV-1^06240004.0166306 | OTHER | HFTD Tier 2 | Distribution | 2023-03-22 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004351 | 536760575-28663-DETAIL-04_24_2023-GO95MLD-1^07117003.0082400 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004352 | 536760575-28663-DETAIL-04_24_2023-GO95TCH-1^07117003.0082400 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004353 | 536903703-38922-DETAIL-07_15_2024-ENCHRW-1^06244005.0269201 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004354 | 536929718-79409-ADMIN-01_23_2024-POLEREPL-1^06147005.0268301 | POLE | Non-HFTD | Distribution | 2024-01-23 | 2027-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004355 | 487365744-79240-DETAIL-02_26_2025-GUYHINS-1^06240004.0219843 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004356 | 487686766-45889-DETAIL-03_25_2024-SVCDEFLC-1^06244005.0145104 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004357 | 487928014-66039-DETAIL-02_08_2024-SVCENTBK-1^07216001.0197001 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004358 | 487928014-66039-DETAIL-02_08_2024-SVCROAD-1^07216001.0197001 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004359 | 488112638-69640-DETAIL-03_12_2025-GO95HV-1^06239003.0136000 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004360 | 488157116-45861-DTLSB-01_31_2023-GUYHINS-1^06248001.0368808 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004361 | 488732093-51749-DETAIL-03_21_2023-GO95MLD-1^07113001.0058504 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004362 | 488732093-51749-DETAIL-03_21_2023-GUYHINS-1^07113001.0058504 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004363 | 489396583-97861-DETAIL-02_16_2023-GO95BLTC-1^06247002.0161102 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004364 | 489396583-97861-DETAIL-02_16_2023-GO95MLD-1^06247002.0161102 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004365 | 489784918-94349-DTLSB-02_21_2024-GO95MLD-1^07216001.0260701 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004366 | 489857570-89261-DETAIL-07_16_2024-GO95HV-1^06244005.0275202 | OTHER | Non-HFTD | Distribution | 2024-07-16 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004367 | 489870554-7261-DETAIL-10_24_2024-GO95HV-1^07216001.0208707 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004368 | 489870554-7261-DETAIL-10_24_2024-GUYHINS-1^07216001.0208707 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004369 | 489952386-23386-DETAIL-01_26_2023-GO95HV-1^06147003.0168900 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004370 | 489976341-20693-DETAIL-04_24_2024-GO95TCH-1^06245007.0226601 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004371 | 490156254-99719-ADMIN-11_04_2024-GO95STUB-1^668036/00 10/032 | OTHER | Non-HFTD | Transmission | 2024-11-04 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004372 | 490214021-25320-DETAIL-03_08_2023-GRDRODHI-1^07117002.0211101 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004373 | 491130256-78039-DETAIL-10_14_2024-GO95MLD-1^07216001.0203309 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004374 | 491130256-78039-DETAIL-10_14_2024-SVCROAD-1^07216001.0203309 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004375 | 491136923-55959-DETAIL-06_06_2024-GO95MLD-1^06246006.0352500 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004376 | 49145914-92459-DETAIL-03_07_2024-SVCROAD-1^06245007.0278900 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004377 | 491466248-4949-DETAIL-04_13_2023-GO95MLD-1^06245006.0229600 | OTHER | Non-HFTD | Distribution | 2023-04-13 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004378 | 491676795-47600-DETAIL-03_26_2025-GO95HV-1^06239003.0019709 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004379 | 491730549-57699-DTLSB-10_02_2024-GO95MLD-1^06245007.0217603 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004380 | 537236814-14839-DTLSB-02_06_2024-GRDRODHI-1^07216001.0309916 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004381 | 537257984-16710-DETAIL-03_18_2025-GO95HV-1^06238004.0156400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004382 | 537682158-74650-DETAIL-01_16_2025-BIRDDMG-1^06240004.0095501 | POLE | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004383 | 537713588-12621-DETAIL-04_22_2024-GO95HV-1^06145001.0119401 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004384 | 538404289-22579-DTLSB-04_22_2024-SVCENTCO-1^06245007.0224407 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004385 | 538653892-24579-DTLSB-08_26_2024-GO95HV-1^06245007.0113401 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004386 | 538653892-24579-DTLSB-08_26_2024-GO95TCH-1^06245007.0113401 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004387 | 538745628-87730-DETAIL-01_22_2025-SVCDEFLC-1^06240004.0089602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004388 | 539172184-58810-DETAIL-03_13_2025-GO95BLTC-1^06238004.0150200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004389 | 539520571-28469-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004390 | 539520571-55702-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004391 | 539603843-36058-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096302 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004392 | 539838210-762-DTLSB-07_19_2023-GO95MLD-1^06243010.0034000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004393 | 540206200-47759-DETAIL-03_21_2024-GO95MLD-1^06246005.0066000 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004394 | 540244221-16431-DETAIL-04_15_2024-GO95MLD-1^06145002.0061501 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004395 | 540264622-11950-DETAIL-03_19_2025-SVCDEFLC-1^06238004.0027202 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004396 | 540585861-7731-ADMIN-02_09_2024-POLEREPL-1^06144006.0109901 | POLE | Non-HFTD | Distribution | 2024-02-09 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004397 | 540706713-90090-DETAIL-03_04_2025-GUYHINS-1^06240004.0150800 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004398 | 540777060-48263-DTLSB-04_17_2024-GO95MLD-1^06245007.0222444 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004399 | 541039473-92529-DETAIL-05_09_2024-GO95MLD-1^06142012.0121504 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004400 | 49197711-34099-ADMIN-06_18_2024-POLEREPL-1^06241009.0031500 | POLE | Non-HFTD | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004401 | 492147606-67606-DETAIL-01_29_2025-GO95MLD-1^06239004.0227202 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004402 | 492241556-52529-DETAIL-04_06_2023-GRDRODHI-1^06143014.0232800 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004403 | 492241556-52529-DETAIL-04_06_2023-RISEGRD-1^06143014.0232800 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004404 | 492284659-25422-DETAIL-06_28_2023-GO95MLD-1^06244009.0362101 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004405 | 492459089-9659-DETAIL-10_08_2024-CLMBTRE-1^07216001.0201142 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004406 | 49277688-56169-DTLTRT-10_10_2023-GUYHINS-1^668010/00 3/045 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004407 | 493181985-5219-DETAIL-03_25_2024-GO95TCH-1^06147005.0120000 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004408 | 493229761-91029-DETAIL-05_06_2024-GO95MLD-1^06142012.0123114 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004409 | 493383701-22742-ADMIN-06_05_2024-GO95STUB-1^06244008.0294000 | OTHER | HFTD Tier 2 | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004410 | 493423119-7479-DETAIL-03_04_2024-GO95MLD-1^06147004.0011203 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004411 | 493814308-78702-DTLSB-08_07_2023-ABNDEQPM-1^06243010.0131001 | OTHER | HFTD Tier 2 | Distribution | 2023-08-07 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004412 | 494037606-87149-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0297606 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004413 | 494176860-86860-DETAIL-02_21_2024-GO95TCH-1^07113001.0138208 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004414 | 494241970-12159-DTLSB-09_30_2024-RISEGRD-1^06245007.0230140 | OTHER | Non-HFTD | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004415 | 494351221-2280-DETAIL-02_27_2025-BIRDDMG-1^06240004.0236801 | POLE | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004416 | 494481684-20240-DTLTRT-10_02_2023-GO95HV-1^668010/00 4/034 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004417 | 49478444-96150-DTLTRT-10_11_2023-BIRDDMG-1^668010/00 9/040 | POLE | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004418 | 49478444-96150-DTLTRT-10_11_2023-GO95HV-1^668010/00 9/040 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004419 | 49478444-96150-DTLTRT-10_11_2023-GUYHINS-1^668010/00 9/040 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004420 | 494969828-42250-DETAIL-03_20_2025-SVCDEFLC-1^06239003.0016101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004421 | 494984341-15299-ADMIN-08_05_2024-GO95STUB-1^06245010.0218900 | OTHER | HFTD Tier 2 | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004422 | 495057918-2499-DETAIL-03_18_2024-GO95HV-1^06246005.0076200 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004423 | 495093818-38859-DETAIL-04_08_2024-GO95MLD-1^06246005.0072400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004424 | 495138694-46571-DETAIL-10_16_2024-GO95HV-1^07216001.0207706 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004425 | 541149306-79700-DTLTRT-11_01_2023-GO95HV-1^668010/00 10/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004426 | 541397736-27470-DETAIL-01_15_2025-GO95HV-1^06239004.0255245 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004427 | 541618446-72331-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004428 | 541618446-77960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004429 | 541809935-83831-DTLSB-05_08_2024-GO95MLD-1^06245001.0298200 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004430 | 541867836-72649-DETAIL-03_02_2023-GO95CL10-1^07216001.0293903 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004431 | 541867836-72649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293903 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004432 | 54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-2^668010/00 9/041 | CONNECTION DEVICE | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004433 | 54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-3^668010/00 9/041 | CONNECTION DEVICE | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004434 | 54236794-37289-DTLSB-08_28_2024-GO95MLD-1^06245007.0140202 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004435 | 542392959-5331-DTLSB-05_20_2024-GO95BLTC-1^06244003.0287700 | OTHER | Non-HFTD | Distribution | 2024-05-20 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004436 | 542698743-48039-DETAIL-07_25_2024-GO95HV-1^06244005.0347901 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004437 | 543014506-19631-DTLSB-01_30_2023-GO95MLD-1^06248001.0369800 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004438 | 543030253-10731-DTLSB-05_22_2024-GO95MLD-1^06243001.0104501 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004439 | 543464189-7189-DETAIL-03_16_2023-GO95MLD-1^07113001.0044906 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004440 | 544342143-94330-DETAIL-03_10_2025-GO95MLD-1^06240004.0064601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004441 | 544521778-29299-DTLSB-04_15_2024-SVCROAD-1^06245007.0224204 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004442 | 544581343-57370-DTLTRT-04_11_2024-BIRDDMG-1^668067/00 2/008 | POLE | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004443 | 545039676-59879-DTLSB-08_15_2023-GO95MLD-1^06243009.0263800 | OTHER | Non-HFTD | Distribution | 2023-08-15 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004444 | 545302681-18039-DETAIL-07_08_2024-GO95MLD-1^06244005.0136800 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004445 | 545587866-3089-DTLSB-08_24_2023-CLRTOUCH-1^06243009.0118603 | CONDUCTOR | Non-HFTD | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004446 | 545670064-66689-DETAIL-07_15_2024-GO95MLD-1^06244005.0264941 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004447 | 545720346-84572-DETAIL-08_08_2024-GRDRODHI-1^06245006.0091140 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004448 | 546067353-88639-DTLSB-02_28_2024-GO95MLD-1^07216001.0271600 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004449 | 546320042-64049-DETAIL-10_10_2024-GO95MLD-1^07216001.0205003 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004450 | 495416969-15249-DTLSB-10_02_2024-GO95MLD-1^06245007.0219501 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004451 | 495840491-31780-DETAIL-03_19_2025-GO95HV-1^06239001.0060600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004452 | 495877901-78599-DETAIL-07_06_2023-GO95MLD-1^06244008.0329901 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004453 | 495877901-78599-DETAIL-07_06_2023-GRDRODHI-1^06244008.0329901 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004454 | 496069209-38449-DTLTRT-02_15_2024-GUYHINS-1^07216001.0264003 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004455 | 496255146-40940-DETAIL-01_17_2023-SVCDEFLC-1^06240004.0082204 | OTHER | HFTD Tier 2 | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004456 | 496468638-73286-DETAIL-10_08_2024-SVCDEFLC-1^07216001.0201141 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004457 | 4965955-10160-DTLTRT-10_09_2023-GO95HV-1^668010/00 15/037 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004458 | 496669835-87449-ADMIN-03_14_2025-POLEREPL-1^06245007.0224605 | POLE | Non-HFTD | Distribution | 2025-03-14 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004459 | 497143546-91839-DETAIL-10_08_2024-SVCDEFLC-1^07216001.0200110 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004460 | 497402440-5559-DETAIL-03_08_2023-GO95CL10-1^07216001.0295506 | OTHER | Non-HFTD | Distribution | 2023-03-08 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004461 | 497402440-5559-DETAIL-03_08_2023-GUYHINS-1^07216001.0295506 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004462 | 497809195-86909-DETAIL-04_01_2024-GO95MLD-1^06147005.0126800 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004463 | 498374562-99071-DETAIL-02_08_2023-GO95HV-1^06146002.0272100 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004464 | 498488633-89171-DETAIL-02_09_2023-GO95CL10-1^06146004.0101000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004465 | 498488633-89171-DETAIL-02_09_2023-GO95MLD-1^06146004.0101000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004466 | 498916229-80129-DETAIL-05_07_2024-GO95HV-1^06142012.0124203 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004467 | 498990123-27239-DTLSB-02_13_2024-SVCROAD-1^07216001.0185102 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004468 | 499192181-80829-DTLSB-09_28_2023-GO95HV-1^06243008.0107700 | OTHER | HFTD Tier 2 | Distribution | 2023-09-28 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004469 | 499205789-62949-DTLSB-02_16_2024-GO95MLD-1^07216001.0261100 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004470 | 499876263-19263-DETAIL-04_29_2024-GO95MLD-1^06142016.0079902 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004471 | 499876263-19263-DETAIL-04_29_2024-GRDRODHI-1^06142016.0079902 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004472 | 499876263-19263-DETAIL-04_29_2024-SVCDEFLC-1^06142016.0079902 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004473 | 500410508-54830-DETAIL-01_15_2025-GO95HV-1^06240004.0096204 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004474 | 500511361-96859-DTLSB-02_15_2024-SVCENTCO-2^07216001.0261002 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004475 | 54637114-62779-DETAIL-08_20_2024-GO95HV-1^06246005.0366901 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004476 | 547151535-81535-DTLSB-04_10_2024-SVCWIND-1^06245007.0225009 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004477 | 547206549-4149-DETAIL-02_27_2024-GO95MLD-1^07113002.0183200 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004478 | 547206549-4149-DETAIL-02_27_2024-GO95TCH-1^07113002.0183200 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004479 | 547206549-4149-DETAIL-02_27_2024-GUYHINS-1^07113002.0183200 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004480 | 54736245-39623-DTLSB-05_02_2024-GO95MLD-1^06245007.0224502 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004481 | 547385671-21550-DETAIL-01_21_2025-GO95STUB-1^06239004.0256504 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004482 | 547518070-69070-DETAIL-03_19_2025-SVCDEFLC-1^06238004.0028606 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004483 | 547619723-71999-DETAIL-06_11_2024-SVCWIND-1^06245007.0341701 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004484 | 547629276-42409-DETAIL-04_02_2024-GO95MLD-1^06147005.0147200 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004485 | 547869936-7079-DETAIL-03_28_2024-GO95HV-1^06147005.0147701 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004486 | 548484453-76939-DETAIL-03_08_2023-GO95MLD-1^07216001.0295600 | OTHER | Non-HFTD | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004487 | 548619593-84779-DETAIL-07_31_2024-GO95MLD-1^06244005.0341900 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004488 | 548697413-81479-DTLSB-01_30_2023-GO95MLD-1^06248001.0257004 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004489 | 548932335-3741-DETAIL-04_23_2024-GO95HV-1^06145001.0035102 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004490 | 549067103-92589-DETAIL-06_10_2024-GO95MLD-1^06245007.0347004 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004491 | 549125377-75377-DETAIL-04_03_2023-GO95HV-1^06143013.0333801 | OTHER | Non-HFTD | Distribution | 2023-04-03 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004492 | 549125377-75377-DETAIL-04_03_2023-GO95MLD-1^06143013.0333801 | OTHER | Non-HFTD | Distribution | 2023-04-03 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004493 | 549682474-73849-ADMIN-07_15_2024-POLEDERP-1^07216001.0160801 | POLE | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004494 | 549869080-70180-DTLTRT-06_27_2022-GO95HV-1^668005/00 3A/025 | OTHER | Non-HFTD | Transmission | 2022-06-27 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004495 | 549992088-89043-DETAIL-03_09_2023-GO95MLD-1^07117002.0205209 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004496 | 550096146-75941-DETAIL-10_22_2024-GO95MLD-1^07216001.0207401 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004497 | 550542026-82080-DRONE_HY-11_10_2023-GO95HV-1^668033/00 5/048 | OTHER | HFTD Tier 2 | Transmission | 2023-11-10 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004498 | 550968603-53903-DETAIL-10_12_2022-GO95HV-1^668005/08 8X1/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004499 | 551393512-38241-DETAIL-05_14_2024-GO95HV-1^06142012.0124409 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004500 | 500625636-38989-DETAIL-01_23_2023-GO95MLD-1^06148004.0192900 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004501 | 500675690-60620-DETAIL-03_06_2025-GO95HV-1^06240004.0271801 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004502 | 500936573-54673-DETAIL-04_15_2024-GO95MLD-1^06145002.0065602 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004503 | 500984359-88183-DETAIL-08_01_2024-GO95MLD-1^06245006.0104002 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004504 | 501223218-30271-DETAIL-02_20_2023-GO95MLD-1^06247002.0297400 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004505 | 501555801-18330-DTLTRT-10_30_2023-GO95HV-1^668010/00 13/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-30 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004506 | 501706659-91409-DETAIL-04_10_2024-GO95MLD-1^06147005.0213900 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004507 | 501998121-54709-DTLSB-08_28_2024-GO95MLD-1^06245007.0113002 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004508 | 502105859-9513-DETAIL-03_05_2024-SVCDEFLC-1^06245007.0275343 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004509 | 502505799-4153-DTLSB-04_22_2024-SVCROOF-1^06245007.0225441 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004510 | 502505799-4153-DTLSB-04_22_2024-SVCWIND-1^06245007.0225441 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004511 | 502559129-98481-DETAIL-05_02_2024-SVCDEFLC-1^06142012.0125007 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004512 | 502760489-65389-AUDIT-07_01_2024-GO95MLD-1^06246005.0339300 | OTHER | Non-HFTD | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004513 | 502847218-42449-DETAIL-06_03_2024-SVCROAD-1^06245006.0024000 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004514 | 503337144-68549-DTLSB-02_06_2024-GO95MLD-1^07216001.0309805 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004515 | 503422719-31939-DTLSB-02_15_2024-GO95MLD-1^07216001.0191800 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004516 | 50413766-44770-DETAIL-01_14_2025-GO95HV-1^06239004.0256110 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004517 | 50413766-44770-DETAIL-01_14_2025-GUYHINS-1^06239004.0256110 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004518 | 50413766-44770-DETAIL-01_14_2025-SVCDEFLC-1^06239004.0256110 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004519 | 505033128-3550-DETAIL-03_26_2025-GO95HV-1^06239003.0018401 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004520 | 50506503-17779-DTLTRT-09_27_2023-GO95HV-1^668010/00 18/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004521 | 505106568-48960-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 9/064 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004522 | 505113600-11029-DETAIL-03_20_2017-SVCWIND-1^06142012.0133501 | OTHER | Non-HFTD | Distribution | 2017-03-20 | 2020-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004523 | 50515680-80399-DTLSB-08_17_2023-GO95MLD-1^06243009.0131003 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004524 | 5052350-17270-DETAIL-02_18_2025-GO95TCH-1^06240004.0220409 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004525 | 505398239-86639-DTLTRT-10_25_2022-GO95MLD-1^668075/00 15/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004526 | 551427674-46569-DTLSB-04_23_2024-GO95BLTC-1^06245007.0223701 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004527 | 551585525-18525-DETAIL-02_27_2024-GO95HV-1^07113002.0071102 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004528 | 551859979-71430-DETAIL-01_24_2025-SVCDEFLC-1^06240004.0081601 | OTHER | HFTD Tier 2 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004529 | 551948440-66201-DETAIL-01_21_2025-GO95HV-1^06239004.0255342 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004530 | 551948440-66201-DETAIL-01_21_2025-GO95TCH-1^06239004.0255342 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004531 | 551990345-53200-DETAIL-03_25_2025-GO95HV-1^06239003.0019504 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004532 | 552098426-60623-DTLSB-05_02_2024-GUYNOINS-1^06245007.0222541 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004533 | 552138813-10323-DETAIL-10_12_2022-GO95HV-1^668005/08 8X2/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004534 | 552392870-38009-DETAIL-11_08_2022-GO95MLD-1^06246008.0043301 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004535 | 552799451-79941-DTLSB-02_06_2023-GO95MLD-1^06248001.0259600 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004536 | 553438635-27551-DETAIL-10_25_2024-GO95MLD-1^07216001.0209800 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004537 | 553461728-14856-DETAIL-10_08_2024-SVCENTCO-1^07216001.0201040 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004538 | 553642103-20669-DTLTRT-06_04_2021-GO95HV-1^668041/00 3/009 | OTHER | Non-HFTD | Transmission | 2021-06-04 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004539 | 553987318-32450-DETAIL-03_26_2025-SVCDEFLC-1^06239003.0018407 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004540 | 554308039-74299-DETAIL-02_06_2019-SVCROAD-1^06147004.0014902 | OTHER | Non-HFTD | Distribution | 2019-02-06 | 2022-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004541 | 554308039-74299-DETAIL-03_11_2024-GO95HV-1^06147004.0014902 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004542 | 554308039-74299-DETAIL-03_11_2024-GO95MLD-1^06147004.0014902 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004543 | 554440141-72141-DETAIL-04_30_2024-GO95HV-1^06142015.0034900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004544 | 554572814-50560-DETAIL-09_10_2024-SVCDEFLC-1^06240004.0099045 | OTHER | HFTD Tier 2 | Distribution | 2024-09-10 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004545 | 554794587-59298-DETAIL-07_08_2024-GO95HV-1^06244005.0013502 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004546 | 554794587-59298-DETAIL-07_08_2024-GO95MLD-1^06244005.0013502 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004547 | 554934385-95551-DTLSB-02_02_2023-ENCHRW-1^06248001.0360901 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004548 | 554934461-36461-DETAIL-03_23_2023-GO95MLD-1^06142016.0051001 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004549 | 554943579-74759-DETAIL-02_22_2024-GO95HV-1^07216001.0346702 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004550 | 554943579-74759-DETAIL-02_22_2024-GO95MLD-1^07216001.0346702 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004551 | 505540078-85449-DETAIL-10_15_2024-GO95CL10-1^07216001.0203308 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004552 | 505584631-40849-DETAIL-03_06_2023-SVCWIND-1^07216001.0297702 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004553 | 50560451-17729-DTLSB-09_28_2023-GO95HV-1^06243008.0097600 | OTHER | HFTD Tier 2 | Distribution | 2023-09-28 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004554 | 50560451-17729-DTLSB-09_28_2023-GO95MLD-1^06243008.0097600 | OTHER | HFTD Tier 2 | Distribution | 2023-09-28 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004555 | 505615350-56769-DTLSB-09_04_2024-GO95MLD-1^06245007.0019400 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004556 | 505673798-80190-DETAIL-02_19_2025-GO95MLD-1^06239004.0365504 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004557 | 505764733-29649-DETAIL-03_01_2023-GO95MLD-1^07216001.0292603 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004558 | 506173222-76681-DETAIL-10_21_2024-GO95TCH-1^07216001.0209606 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004559 | 506209626-94689-DTLSB-08_24_2023-GO95MLD-1^06243009.0119502 | OTHER | Non-HFTD | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004560 | 506381461-87781-DETAIL-03_12_2024-SVCENTBK-1^06147004.0062900 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004561 | 506617200-64889-DETAIL-07_08_2024-GO95MLD-1^06244005.0136700 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004562 | 507479578-82678-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0043503 | CONDUCTOR | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004563 | 507892731-17731-DETAIL-04_25_2024-GO95HV-1^06142016.0041001 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004564 | 508063619-16029-AUDIT-10_09_2023-GO95HV-1^06243009.0242700 | OTHER | Non-HFTD | Distribution | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004565 | 508561626-50039-DETAIL-10_14_2024-GO95HV-1^07216001.0200305 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004566 | 508584841-14032-ADMIN-12_04_2024-GO95STUB-1^06244008.0324701 | OTHER | HFTD Tier 2 | Distribution | 2024-12-04 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004567 | 508807554-22549-DTLSB-02_27_2024-SVCROAD-1^07216001.0276902 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004568 | 508808588-3992-DETAIL-03_20_2024-GO95MLD-1^06244005.0144404 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004569 | 509059616-65881-DTLSB-05_14_2024-GO95MLD-1^06244001.0294800 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004570 | 509183170-15369-DTLTRT-06_15_2021-GO95HV-1^668041/00 17/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004571 | 509517293-91729-DTLSB-08_31_2023-GO95HV-1^06243008.0025900 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004572 | 509553835-28063-DETAIL-04_24_2023-GO95HV-1^07117003.0105600 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004573 | 509750759-6149-DETAIL-03_01_2023-GO95MLD-1^07216001.0293502 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004574 | 509758203-67539-DETAIL-07_02_2024-GO95MLD-1^06244005.0231700 | OTHER | Non-HFTD | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004575 | 509763562-26850-DETAIL-03_20_2025-GO95HV-1^06239003.0016104 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004576 | 555150588-69849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155700 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004577 | 555166386-67629-DETAIL-08_21_2024-BIRDDMG-1^06245008.0287301 | POLE | HFTD Tier 2 | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004578 | 555319197-24670-DETAIL-02_03_2025-SVCDEFLC-1^06240004.0165801 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004579 | 555319197-24670-DETAIL-09_18_2024-SVCDEFLC-1^06240004.0165801 | OTHER | HFTD Tier 2 | Distribution | 2024-09-18 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004580 | 555339846-73123-DTLSB-04_29_2024-GO95MLD-1^06245007.0221646 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004581 | 555543521-11449-DTLSB-04_24_2024-GO95HV-1^06245007.0225502 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004582 | 555633876-18876-DETAIL-07_07_2023-GO95MLD-1^06244008.0330700 | OTHER | Non-HFTD | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004583 | 555735049-8070-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/063 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004584 | 555923951-46469-DTLTRT-07_20_2022-GO95HV-1^668005/00 10/054 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004585 | 556894515-61269-DTLTRT-10_10_2023-GO95HV-1^668010/00 3/041 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004586 | 556996560-77149-DETAIL-07_01_2024-GRDRODHI-1^06245007.0190101 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004587 | 556996560-77149-DETAIL-07_01_2024-GRDRODHI-2^06245007.0190101 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004588 | 558214470-16221-DTLTRT-06_15_2021-CLRTOUCH-1^668041/00 1/022 | CONDUCTOR | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004589 | 558214470-16221-DTLTRT-06_15_2021-GO95HV-1^668041/00 1/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004590 | 558214470-16221-DTLTRT-06_15_2021-GO95MLD-1^668041/00 1/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004591 | 558214470-16221-DTLTRT-06_15_2021-GO95MLD-2^668041/00 1/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004592 | 558214470-16221-DTLTRT-06_15_2021-GRDRODHI-1^668041/00 1/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004593 | 558277775-87263-DETAIL-04_24_2023-GO95HV-1^07117003.0101600 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004594 | 558571029-38253-DTLSB-10_07_2024-GO95HV-1^06245006.0172500 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004595 | 558596468-35130-DETAIL-01_14_2025-GO95CL10-1^06240004.0098004 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004596 | 558618254-86860-DETAIL-09_10_2024-SVCROAD-1^06240004.0099141 | OTHER | HFTD Tier 2 | Distribution | 2024-09-10 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004597 | 558855475-83349-DETAIL-02_27_2023-GO95MLD-1^07216001.0294708 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004598 | 558941819-79243-DETAIL-03_26_2024-GO95MLD-1^06246005.0040602 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004599 | 558953990-69770-DETAIL-04_12_2023-SVCROOF-1^06240004.0167501 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004600 | 559283642-30520-DETAIL-02_24_2025-GO95HV-1^06240004.0272040 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004601 | 509763562-26850-DETAIL-03_20_2025-SVCDEFLC-1^06239003.0016104 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004602 | 509773733-29230-DETAIL-02_26_2025-SVCNEUT-1^06240004.0065103 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004603 | 510117793-35791-DTLSB-05_28_2024-GO95MLD-1^06243001.0126201 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004604 | 510533138-74138-DETAIL-02_28_2023-SVCWIND-1^07216001.0298707 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004605 | 511175416-74979-DETAIL-04_04_2024-GO95MLD-1^06147005.0238201 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004606 | 511290619-25659-DETAIL-04_02_2024-GO95MLD-1^06246005.0048901 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004607 | 511605823-93089-DETAIL-07_31_2024-GO95MLD-1^06244005.0346903 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004608 | 511657662-90440-DTLTRT-10_03_2023-GO95HV-1^668010/00 7/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004609 | 511657662-90440-DTLTRT-10_03_2023-GO95MLD-1^668010/00 7/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004610 | 511734559-69999-DETAIL-04_01_2024-GO95MLD-1^06147005.0097700 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004611 | 511804098-82891-DETAIL-04_16_2024-GO95MLD-1^06145001.0129000 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004612 | 512100119-4030-DTLTRT-10_25_2023-GO95HV-1^668010/00 5/013 | OTHER | HFTD Tier 2 | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004613 | 512186983-81870-DETAIL-12_18_2024-BIRDDMG-1^668002/00 7/064 | POLE | HFTD Tier 2 | Transmission | 2024-12-18 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004614 | 512248220-36759-DETAIL-03_21_2024-GO95HV-1^06246005.0067102 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004615 | 512653095-84691-DETAIL-02_23_2023-GO95MLD-1^07216001.0298904 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004616 | 512772009-3649-DTLSB-04_15_2024-SVCWIND-1^06245007.0224202 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004617 | 512957254-72679-DETAIL-07_08_2024-GUYNOINS-1^06244005.0013501 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-08 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004618 | 512957254-72679-DETAIL-07_08_2024-GUYNOINS-2^06244005.0013501 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-08 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004619 | 513237039-1259-DETAIL-05_30_2024-GO95MLD-1^06246005.0340403 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004620 | 513501988-33359-DTLSB-02_15_2024-GO95MLD-1^07216001.0191600 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004621 | 559366068-68351-DTLSB-05_13_2024-GO95HV-1^06244001.0215403 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004622 | 559622041-93041-DETAIL-04_30_2024-GO95HV-1^06142015.0033900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004623 | 559663638-24250-DETAIL-01_22_2025-BIRDDMG-1^06240004.0092504 | POLE | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004624 | 559930545-40851-DTLSB-05_08_2024-GO95MLD-1^06245001.0299101 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004625 | 560131516-86851-DETAIL-04_18_2024-GO95HV-1^06145001.0269300 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004626 | 560580491-5191-DETAIL-03_27_2023-ABNDEQPM-1^06142016.0082903 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004627 | 560580491-5191-DETAIL-03_27_2023-GO95MLD-1^06142016.0082903 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004628 | 560824531-72852-AUDIT-08_01_2023-GO95HV-1^06244009.0290700 | OTHER | Non-HFTD | Distribution | 2023-08-01 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004629 | 561011633-2639-DETAIL-07_03_2024-GO95MLD-1^06244005.0233800 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004630 | 561403034-35061-DETAIL-04_18_2024-GO95HV-1^06144001.0013900 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004631 | 561472448-67470-DETAIL-02_03_2025-PWRTRN-1^06240004.0169901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004632 | 561581869-89919-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 2/079 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-03 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004633 | 561842843-14561-DETAIL-10_22_2024-GO95HV-1^07216001.0209542 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004634 | 561842843-14561-DETAIL-10_22_2024-SVCNEUT-1^07216001.0209542 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004635 | 561860473-68659-DTLSB-02_13_2024-GO95MLD-1^07216001.0187100 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004636 | 561958383-51529-DTLSB-07_26_2023-GO95MLD-1^06243009.0082603 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004637 | 562003791-76791-DETAIL-03_23_2023-GO95MLD-1^06142016.0051004 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004638 | 562039784-63884-DETAIL-04_25_2024-GO95HV-1^06142016.0175800 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004639 | 562100713-97239-DETAIL-07_10_2024-ENCHRW-1^06244005.0289900 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004640 | 562211969-44099-DETAIL-07_25_2024-ABNDEQPM-1^06244005.0349200 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004641 | 562249546-32123-DTLSB-04_17_2024-GO95MLD-1^06245007.0224508 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004642 | 562318404-68404-DETAIL-10_17_2024-SVCDEFLC-1^07216001.0204411 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004643 | 562318404-68404-DETAIL-10_17_2024-SVCDEFLC-2^07216001.0204411 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004644 | 56243918-93670-DETAIL-04_12_2023-GO95HV-1^06240004.0167900 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004645 | 562513891-34902-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004646 | 562543083-58480-DETAIL-02_11_2025-GO95MLD-1^06240004.0167405 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004647 | 563079219-17349-DETAIL-06_03_2024-GO95HV-1^06245006.0028701 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004648 | 56350956-34829-DETAIL-05_13_2024-GO95MLD-1^06142012.0123308 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004649 | 563515646-65680-DETAIL-01_22_2025-GO95HV-1^06239004.0257640 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004650 | 563620089-25299-DETAIL-03_11_2024-GO95MLD-1^06147004.0014900 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004651 | 514186515-20569-DETAIL-02_26_2025-GO95TCH-1^06240004.0061100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004652 | 514348221-44091-DETAIL-02_21_2024-GO95MLD-1^07113001.0146101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004653 | 51453459-50559-DETAIL-03_01_2023-GO95MLD-1^07216001.0292541 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004654 | 51453459-50559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292541 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004655 | 514653269-23913-DETAIL-03_11_2024-GO95MLD-1^06245006.0120040 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004656 | 514678714-39391-DTLSB-05_08_2024-GO95MLD-1^06245001.0332800 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004657 | 514988968-87943-DETAIL-03_09_2023-GO95MLD-1^07117002.0205210 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004658 | 515473601-38250-DETAIL-02_11_2025-GO95MLD-1^06239004.0124902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004659 | 515793731-53743-DETAIL-03_07_2023-GO95MLD-1^07117002.0210700 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004660 | 516179316-32280-DETAIL-01_24_2025-GO95HV-1^06239004.0257945 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004661 | 516319123-60299-DETAIL-03_21_2024-GO95BLTC-1^06146004.0014400 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004662 | 516319123-60299-DETAIL-03_21_2024-GO95MLD-1^06146004.0014400 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004663 | 516319123-60299-DETAIL-03_21_2024-GRDRODHI-1^06146004.0014400 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004664 | 516420189-43649-DETAIL-08_20_2024-GO95HV-1^06245005.0250100 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004665 | 516804006-32231-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/045 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004666 | 516804006-53860-DRONE_HY-10_12_2023-GO95HV-1^668033/00 5/045 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004667 | 516954791-21780-DETAIL-03_21_2023-GO95TCH-1^06240004.0167415 | OTHER | HFTD Tier 2 | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004668 | 517498699-48701-DETAIL-01_24_2023-GO95HV-1^06148003.0259000 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004669 | 518348083-17624-DETAIL-04_25_2024-GO95HV-1^06142016.0175602 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004670 | 518393921-10349-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0139202 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004671 | 518508479-42391-DETAIL-06_01_2022-GO95HV-1^06241005.0031700 | OTHER | HFTD Tier 2 | Distribution | 2022-06-01 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004672 | 518650487-76701-DETAIL-03_19_2024-SVCENTCO-1^06245002.0014801 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004673 | 518907831-85789-DTLSB-08_14_2023-GO95MLD-1^06243009.0242300 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004674 | 518988543-58559-DETAIL-04_03_2024-BIRDDMG-1^06247005.0298902 | POLE | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004675 | 518988543-58559-DETAIL-04_03_2024-GO95MLD-1^06247005.0298902 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004676 | 563779128-35079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 17/075 | OTHER | HFTD Tier 2 | Transmission | 2023-09-21 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004677 | 563908773-38773-DETAIL-04_02_2025-TRESEC-1^06241005.0118306 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2026-04-30 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130004678 | 564086935-99199-DETAIL-04_04_2024-GO95MLD-1^06147005.0148000 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004679 | 564086935-99199-DETAIL-04_04_2024-SVCROAD-1^06147005.0148000 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004680 | 56431080-14369-DETAIL-02_25_2025-GO95TCH-1^06240004.0151412 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004681 | 56437859-13269-DTLTRT-07_05_2022-GO95HV-1^668005/00 5/034 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004682 | 56438543-48560-DTLSB-02_16_2023-GO95MLD-1^06248001.0334901 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004683 | 564565971-18699-DETAIL-11_07_2022-ABNDEQPM-1^06246008.0063003 | OTHER | HFTD Tier 2 | Distribution | 2022-11-07 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004684 | 564695422-869-DTLTRT-09_26_2023-GO95STUB-1^668010/00 2/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-26 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004685 | 56490293-95859-DETAIL-01_31_2023-GRDRODHI-1^668002/07 17/002 | OTHER | HFTD Tier 2 | Transmission | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004686 | 564946764-21061-DTLSB-02_06_2023-GO95MLD-1^06248001.0257200 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004687 | 565019724-33183-DETAIL-10_22_2024-GUYNOINS-1^07216001.0208540 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004688 | 565389029-80189-DETAIL-06_14_2023-GO95MLD-1^06243009.0022000 | OTHER | Non-HFTD | Distribution | 2023-06-14 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004689 | 565478008-97449-DETAIL-08_01_2024-GO95HV-1^06245006.0112001 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004690 | 565591216-97879-DETAIL-02_03_2025-GO95BLTC-1^06239004.0244948 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004691 | 565629076-24400-DTLTRT-11_02_2023-GO95HV-1^668010/00 19/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-02 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004692 | 565660026-78649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293904 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004693 | 565774733-30661-DETAIL-02_08_2023-GO95MLD-1^06146004.0083001 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004694 | 565788719-1389-DTLSB-10_03_2024-CLRTOPOL-1^06245007.0218700 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004695 | 565788719-1389-DTLSB-10_03_2024-CLRTOUCH-1^06245007.0218700 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004696 | 566390515-63000-DETAIL-03_13_2025-GO95HV-1^06239003.0242500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004697 | 566575073-16929-DETAIL-05_09_2024-GO95MLD-1^06142012.0121603 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004698 | 566575073-16929-DETAIL-05_09_2024-SVCDEFLC-1^06142012.0121603 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004699 | 566586766-66659-DETAIL-10_25_2024-ABNDEQPM-1^07216001.0201603 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004700 | 566666751-10582-DTLSB-07_18_2023-GO95MLD-1^06243010.0037801 | OTHER | HFTD Tier 2 | Distribution | 2023-07-18 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004701 | 519276743-25309-ADMIN-06_05_2024-GO95STUB-1^06245010.0323700 | OTHER | HFTD Tier 2 | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004702 | 519764185-84479-ADMIN-03_10_2023-GO95CL10-1^06148004.0187200 | OTHER | Non-HFTD | Distribution | 2023-03-10 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004703 | 519764185-84479-DETAIL-01_10_2023-GO95MLD-1^06148004.0187200 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004704 | 519869996-29279-DRONE_HY-09_23_2023-ABNDEQPM-1^668002/00 25/059 | OTHER | HFTD Tier 2 | Transmission | 2023-09-23 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004705 | 520201549-45549-DETAIL-03_18_2024-GO95MLD-1^06246005.0079300 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004706 | 520386313-88479-DETAIL-07_31_2024-GO95MLD-1^06244005.0339902 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004707 | 520468319-61701-DETAIL-05_02_2024-GO95MLD-1^06142012.0126001 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004708 | 520535455-85329-ADMIN-04_08_2025-RISEBKSP-1^06243010.0130403 | OTHER | HFTD Tier 2 | Distribution | 2025-04-08 | 2028-04-30 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130004709 | 520575753-22953-DETAIL-10_12_2022-GUYHINS-4^668005/08 8X8/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-12 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004710 | 520791606-12606-DETAIL-01_29_2025-GO95MLD-1^06239004.0231101 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004711 | 520899688-16001-DETAIL-04_10_2024-GO95MLD-1^06245002.0113100 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004712 | 521101882-42750-DETAIL-03_20_2025-GO95HV-1^06239003.0015303 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004713 | 521211548-54350-DETAIL-01_16_2025-BIRDDMG-1^06240004.0094900 | POLE | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004714 | 521231512-69219-DTLTRT-08_15_2022-GO95HV-1^668005/00 7/087 | OTHER | Non-HFTD | Transmission | 2022-08-15 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004715 | 521449401-62859-DETAIL-06_05_2024-GO95MLD-1^06246006.0267200 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004716 | 521514549-73023-DETAIL-02_25_2025-BIRDDMG-1^06240004.0218740 | POLE | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004717 | 521514549-73023-DETAIL-02_25_2025-SVCDEFLC-1^06240004.0218740 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004718 | 521644820-5269-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 10/034 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004719 | 521844420-11470-DETAIL-02_12_2025-CLRTOUCH-1^06240004.0167104 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-12 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004720 | 522266978-59450-DETAIL-01_16_2025-SVCDEFLC-1^06240004.0097506 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004721 | 522967961-64364-DETAIL-03_23_2023-GO95MLD-1^06142016.0050006 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004722 | 523163538-81849-DTLSB-04_29_2024-SVCROAD-1^06245007.0226401 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004723 | 523183484-39679-DETAIL-08_14_2024-GO95HV-1^06246005.0254800 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004724 | 523279913-5029-DETAIL-05_08_2024-SVCROAD-1^06142012.0120041 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004725 | 523290363-12502-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 3/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004726 | 56688489-2759-DTLSB-02_05_2024-GO95MLD-1^07216001.0191940 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004727 | 567060168-5561-DETAIL-03_18_2024-GO95HV-1^06245002.0036900 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004728 | 567119115-97489-DETAIL-06_07_2023-ABNDEQPM-1^06244006.0010601 | OTHER | Non-HFTD | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004729 | 567119115-97489-DETAIL-06_07_2023-GO95HV-1^06244006.0010601 | OTHER | Non-HFTD | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004730 | 568228508-39508-DETAIL-02_22_2024-GO95HV-1^07113001.0097400 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004731 | 56852113-9590-DETAIL-06_27_2024-SVCDEFLC-1^06240004.0064901 | OTHER | HFTD Tier 2 | Distribution | 2024-06-27 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004732 | 56859920-54960-DETAIL-05_06_2024-GUYHINS-1^06142012.0124003 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004733 | 568691524-61810-DETAIL-03_13_2025-SVCDEFLC-1^06238004.0152203 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004734 | 568831989-42271-DETAIL-04_11_2024-GO95MLD-1^06245002.0105301 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004735 | 56909367-90467-DTLSB-08_02_2022-GO95MLD-1^06242004.0193300 | OTHER | HFTD Tier 2 | Distribution | 2022-08-02 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004736 | 56941126-91960-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004737 | 569450461-93559-DETAIL-05_16_2022-GUYNOINS-1^07116001.0090401 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004738 | 569491599-9579-DETAIL-06_11_2024-GO95BLTC-1^06245007.0345341 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004739 | 56982115-21540-DETAIL-02_24_2025-SVCDEFLC-1^06240004.0152703 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004740 | 569934095-95319-DETAIL-10_24_2022-GO95HV-1^06247008.0316000 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004741 | 570017570-20749-DTLSB-04_17_2024-GO95MLD-1^06245007.0223402 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004742 | 570782785-72571-DTLSB-05_14_2024-GO95MLD-1^06244001.0202000 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004743 | 571262304-37780-DTLTRT-04_16_2024-GO95HV-1^668067/00 6/013 | OTHER | Non-HFTD | Transmission | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004744 | 571341503-1529-DETAIL-05_09_2024-GO95HV-1^06142012.0120603 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004745 | 571424853-74271-AUDIT-11_13_2024-SVCROAD-1^07216001.0205840 | OTHER | Non-HFTD | Distribution | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004746 | 571526063-48189-DTLSB-02_06_2023-GO95HV-1^06248001.0258701 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004747 | 571537865-79271-DETAIL-02_23_2023-GO95MLD-1^07216001.0294608 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004748 | 571747350-6089-DETAIL-07_23_2024-BIRDDMG-1^06245007.0316800 | POLE | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004749 | 572623858-15290-DETAIL-01_28_2025-GO95HV-1^06239004.0244203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004750 | 572781111-20271-DTLSB-03_29_2022-GO95HV-1^06144006.0105400 | OTHER | Non-HFTD | Distribution | 2022-03-29 | 2027-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004751 | 572781111-20271-DTLSB-03_29_2022-POLETOP-1^06144006.0105400 | POLE | Non-HFTD | Distribution | 2022-03-29 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004752 | 523290363-33502-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 3/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004753 | 523318908-52209-AUDIT-03_21_2024-GO95MLD-1^06147004.0010300 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004754 | 523526449-93713-DETAIL-07_29_2024-GO95MLD-1^06245006.0149841 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004755 | 523657688-80369-ADMIN-12_21_2022-UBPBGYBK-1^668005/00 10/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004756 | 524251424-72411-DETAIL-10_21_2024-GO95MLD-1^07216001.0209403 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004757 | 524251424-72411-DETAIL-10_21_2024-GRDBROKE-1^07216001.0209403 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004758 | 524544865-12339-DRONE_HY-10_25_2023-GO95HV-1^668087/00 8/010 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004759 | 524825426-92279-DRONE_HY-09_26_2023-GO95HV-1^668033/00 10/002 | OTHER | HFTD Tier 2 | Transmission | 2023-09-26 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004760 | 524837901-60720-DETAIL-02_17_2025-GO95HV-1^06240004.0278606 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004761 | 524959446-32311-DETAIL-02_15_2023-GO95MLD-1^06247002.0232700 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004762 | 524982078-64239-DETAIL-03_20_2024-GO95MLD-1^06244005.0141041 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004763 | 525113935-43919-ADMIN-09_14_2023-POLEREPL-1^668078/00 2/002 | POLE | Non-HFTD | Transmission | 2023-09-14 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004764 | 52553165-7449-DTLSB-04_17_2024-GO95MLD-1^06245007.0224507 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004765 | 525726347-62970-DETAIL-02_26_2025-SVCNEUT-1^06240004.0061304 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004766 | 526038943-98179-DTLSB-09_30_2024-GO95HV-1^06245007.0233401 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004767 | 526038943-98179-DTLSB-09_30_2024-GO95MLD-1^06245007.0233401 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004768 | 526038943-98179-DTLSB-09_30_2024-GO95TCH-1^06245007.0233401 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004769 | 526929034-65811-DTLSB-02_06_2023-GO95MLD-1^06248001.0353800 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004770 | 527198826-63280-DETAIL-01_24_2025-BIRDDMG-1^06239004.0257946 | POLE | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004771 | 527198826-63280-DETAIL-01_24_2025-GO95HV-1^06239004.0257946 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004772 | 527347643-94429-DTLSB-09_07_2023-GO95HV-1^06243008.0139900 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004773 | 573090855-28371-DETAIL-10_22_2024-GO95MLD-1^07216001.0207805 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004774 | 573143809-72209-DTLSB-08_17_2023-GO95MLD-1^06243009.0136401 | OTHER | HFTD Tier 2 | Distribution | 2023-08-17 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004775 | 573251026-9069-DTLTRT-10_23_2023-GO95MLD-1^668010/00 14/042 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004776 | 573571189-51071-DETAIL-04_24_2024-GO95HV-1^06145001.0062501 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004777 | 573571189-51071-DETAIL-04_24_2024-GO95MLD-1^06145001.0062501 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004778 | 574208941-82829-DETAIL-05_07_2024-GO95MLD-1^06142012.0122003 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004779 | 574269526-59571-DETAIL-02_01_2023-GO95HV-1^06147002.0319500 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004780 | 574492459-27610-DETAIL-02_20_2025-SVCDEFLC-1^06241005.0261200 | OTHER | HFTD Tier 3 | Distribution | 2025-02-20 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004781 | 574554803-71653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 7/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004782 | 574616043-99771-DTLSB-05_23_2024-GO95MLD-1^06243001.0149301 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004783 | 574793949-78049-DTLSB-02_21_2024-GO95MLD-1^07216001.0261505 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004784 | 574979079-4071-DETAIL-01_25_2023-CONDFRAY-1^06148003.0355700 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004785 | 57499168-88459-DTLSB-02_14_2024-GO95TCH-1^07216001.0180203 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004786 | 574997491-89479-DETAIL-01_31_2023-GO95MLD-1^06146002.0153701 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004787 | 575085966-83829-DETAIL-05_13_2024-GO95MLD-1^06142012.0123300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004788 | 575191478-40070-DRONE_HY-09_28_2023-GO95HV-1^668033/00 2/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-28 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004789 | 57526197-49460-DETAIL-03_20_2024-GO95HV-1^06245002.0124202 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004790 | 57526197-49460-DETAIL-03_20_2024-GO95MLD-1^06245002.0124202 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004791 | 575882678-2270-DETAIL-01_23_2025-SVCNEUT-1^06240004.0081000 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004792 | 575911092-51452-DETAIL-04_02_2025-TRESEC-1^06241005.0118602 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2026-04-30 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130004793 | 576906184-26481-DTLSB-05_07_2024-GO95MLD-1^06245001.0191400 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004794 | 577034102-51581-ADMIN-02_14_2023-GO95HV-1^06247002.0113101 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004795 | 577396250-32870-DETAIL-02_12_2025-SVCDEFLC-1^06240004.0166504 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004796 | 577533082-4781-DTLSB-05_22_2024-GO95HV-1^06243001.0110201 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004797 | 577533082-4781-DTLSB-05_22_2024-GO95MLD-1^06243001.0110201 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004798 | 527638291-76970-DETAIL-02_19_2025-GO95TCH-1^06241005.0275800 | OTHER | HFTD Tier 3 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004799 | 527854933-76411-DTLSB-05_23_2024-GO95HV-1^06243001.0117001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004800 | 52805483-39009-DTLSB-09_03_2024-GO95MLD-1^06245007.0143900 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004801 | 528229139-70069-DRONE_HY-09_14_2023-GO95HV-1^668002/00 12/041 | OTHER | HFTD Tier 2 | Transmission | 2023-09-14 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004802 | 528767493-90411-DTLSB-05_22_2024-GO95MLD-1^06243001.0047901 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004803 | 528873533-96979-DTLSB-03_31_2022-ENCHRW-1^06145006.0223502 | OTHER | Non-HFTD | Distribution | 2022-03-31 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004804 | 529236294-57999-DETAIL-03_11_2024-GO95HV-1^06147005.0173000 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004805 | 529696256-83249-DETAIL-03_14_2024-SVCDEFLC-1^06245006.0126604 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004806 | 52980299-79129-DETAIL-04_29_2024-GRDRODHI-1^06142016.0069005 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004807 | 529958635-13009-DETAIL-01_16_2023-COPLLEAN-1^06148004.0177300 | POLE | Non-HFTD | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004808 | 530109683-22783-DETAIL-03_30_2023-ENCHRW-1^06142016.0059005 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004809 | 530109683-22783-DETAIL-03_30_2023-ENCHRW-2^06142016.0059005 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004810 | 530302587-90599-DTLSB-08_22_2024-GO95MLD-1^06245006.0326602 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004811 | 530345266-65770-DETAIL-01_22_2025-GO95HV-1^06239004.0256652 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004812 | 530464393-37763-DTLSB-10_01_2024-GO95MLD-1^06245007.0230641 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004813 | 530464393-37763-DTLSB-10_01_2024-GO95MLD-2^06245007.0230641 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004814 | 530793531-34439-DETAIL-07_18_2024-GO95HV-1^06244004.0056600 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004815 | 530802486-63486-DTLSB-05_13_2024-RISEGRD-1^06244001.0154300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004816 | 530862668-97749-DTLSB-04_16_2024-SVCENTCO-1^06245007.0226300 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004817 | 531002633-85940-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/035 | OTHER | Non-HFTD | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004818 | 531041253-98639-DTLSB-09_19_2022-GO95HV-1^06243005.0113900 | OTHER | Non-HFTD | Distribution | 2022-09-19 | 2027-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004819 | 531079135-63600-DETAIL-03_27_2025-GO95HV-1^06239003.0016717 | OTHER | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004820 | 531079135-63600-DETAIL-03_27_2025-GRDRODHI-1^06239003.0016717 | OTHER | HFTD Tier 2 | Distribution | 2025-03-27 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004821 | 531193649-83249-DTLSB-02_21_2024-GO95MLD-1^07216001.0263600 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004822 | 531348639-9240-DRONE_VS-11_13_2024-INSULBRK-1^668014/00 1/063 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004823 | 531456039-52759-DETAIL-02_22_2024-GO95MLD-1^07216001.0353300 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004824 | 577534531-6531-DETAIL-04_25_2024-GO95HV-1^06142016.0040000 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004825 | 577535704-81649-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0030303 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004826 | 577806918-85689-DETAIL-03_25_2024-GO95MLD-1^06244005.0147240 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004827 | 577806918-85689-DETAIL-03_25_2024-GRDRODHI-1^06244005.0147240 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004828 | 578295936-95239-DETAIL-04_01_2024-GUYLOINS-1^06244005.0140401 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004829 | 578384299-62190-DETAIL-01_15_2025-GO95HV-1^06239004.0256103 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004830 | 578914702-98999-DETAIL-03_21_2024-COPLLEAN-1^06147004.0366400 | POLE | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004831 | 579187762-63831-DETAIL-02_27_2025-GO95MLD-1^06241005.0172600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004832 | 579673401-1489-DTLSB-08_25_2022-GO95MLD-1^06243004.0280500 | OTHER | Non-HFTD | Distribution | 2022-08-25 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004833 | 580233085-84649-DTLSB-02_22_2023-GO95MLD-1^07216001.0288700 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004834 | 580546697-26181-DETAIL-03_28_2024-GO95HV-1^06147005.0167900 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004835 | 58060108-8739-DTLSB-02_20_2024-GO95MLD-1^07216001.0261501 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004836 | 580620223-94259-DETAIL-06_11_2024-SVCDEFLC-1^06245007.0345240 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004837 | 580632406-89069-DTLTRT-10_12_2023-GO95BLTC-1^668010/00 11/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004838 | 580632406-89069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 11/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004839 | 580632406-89069-DTLTRT-10_12_2023-GRDRODHI-2^668010/00 11/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004840 | 580721971-52380-DETAIL-03_17_2025-GO95HV-1^06239001.0047702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004841 | 580730068-95699-DETAIL-03_26_2024-GO95MLD-1^06244005.0149001 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004842 | 580734283-15799-DETAIL-03_11_2024-GO95MLD-1^06147005.0178400 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004843 | 580976323-97323-DETAIL-03_27_2023-ENCHRW-1^06240004.0167030 | OTHER | HFTD Tier 2 | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004844 | 581159003-20081-DTLSB-05_28_2024-GO95HV-1^06243001.0126303 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004845 | 581185955-69499-DETAIL-08_07_2024-GO95TCH-1^06245008.0215600 | OTHER | HFTD Tier 2 | Distribution | 2024-08-07 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004846 | 58139215-71869-DTLTRT-10_10_2022-GO95HV-1^668005/03 7/005 | OTHER | Non-HFTD | Transmission | 2022-10-10 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004847 | 582074592-69450-DETAIL-03_19_2025-SVCDEFLC-1^06238004.0026201 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004848 | 582391963-4550-DETAIL-02_04_2025-GO95MLD-1^06239004.0245902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004849 | 582489299-270-DETAIL-02_11_2025-BIRDDMG-1^06240004.0168542 | POLE | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004850 | 58250664-87679-DETAIL-08_15_2024-GO95HV-1^06246005.0135102 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004851 | 582969169-66659-DETAIL-03_28_2024-GO95HV-1^06246005.0045700 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004852 | 583003084-87732-DETAIL-07_07_2023-GO95MLD-1^06244008.0330800 | OTHER | Non-HFTD | Distribution | 2023-07-07 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004853 | 583123811-29089-DETAIL-01_24_2023-CONDFRAY-1^06148003.0240100 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004854 | 583123811-29089-DETAIL-01_24_2023-GO95HV-1^06148003.0240100 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004855 | 583323230-66762-DTLSB-07_19_2023-GO95TCH-1^06243010.0039302 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004856 | 5833468-85630-DETAIL-02_27_2025-GO95MLD-1^06240003.0304400 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004857 | 583406426-43410-DETAIL-01_30_2025-GUYHINS-1^06240004.0163609 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004858 | 583430443-6059-DETAIL-03_06_2023-GO95MLD-1^07117002.0204204 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004859 | 58371444-66444-DETAIL-04_25_2024-GO95HV-1^06142016.0179901 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004860 | 58380913-17929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120604 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004861 | 58380913-17929-DETAIL-05_09_2024-SVCENTCO-1^06142012.0120604 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004862 | 583902501-28369-DTLTRT-06_03_2021-GO95HV-1^668041/00 3/006 | OTHER | Non-HFTD | Transmission | 2021-06-03 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004863 | 58406226-70419-DETAIL-10_24_2022-GO95HV-1^06247009.0249301 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004864 | 584105401-16591-DETAIL-03_01_2023-GO95HV-1^07216001.0298704 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004865 | 584105401-16591-DETAIL-03_01_2023-GO95MLD-1^07216001.0298704 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004866 | 584361860-83949-DTLSB-02_16_2024-GO95MLD-1^07216001.0262202 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004867 | 584482933-48950-DETAIL-01_23_2025-SVCROAD-1^06239004.0256801 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004868 | 584782377-67503-DTLSB-07_22_2024-GO95MLD-1^06245006.0060240 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004869 | 585036074-98491-DETAIL-10_25_2024-SVCROAD-1^07216001.0208704 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004870 | 585095830-68609-DETAIL-11_02_2022-GO95HV-1^06246008.0107700 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004871 | 585249973-70883-DTLTRT-11_07_2022-GO95MLD-1^668001/00 7/031 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004872 | 585442554-47009-ADMIN-09_20_2024-POLEREPL-1^06245007.0224706 | POLE | Non-HFTD | Distribution | 2024-09-20 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004873 | 58616859-94489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0174000 | POLE | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004874 | 586296690-55822-DETAIL-06_27_2023-SVCWIND-1^06244009.0285002 | OTHER | Non-HFTD | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004875 | 586747503-23891-DTLSB-05_28_2024-GO95MLD-1^06243001.0125102 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004876 | 586765671-60959-DETAIL-06_05_2024-GO95HV-1^06246006.0265600 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004877 | 586861060-51270-DETAIL-03_19_2025-GO95HV-1^06239002.0016600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004878 | 587096473-62899-DETAIL-07_11_2024-GO95HV-1^06244005.0260001 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004879 | 587096473-62899-DETAIL-07_11_2024-GO95MLD-1^06244005.0260001 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004880 | 587235888-89963-DETAIL-01_12_2023-GRDRODHI-1^06240004.0093200 | OTHER | HFTD Tier 2 | Distribution | 2023-01-12 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004881 | 587235888-89963-DETAIL-09_10_2024-BIRDDMG-1^06240004.0093200 | POLE | HFTD Tier 2 | Distribution | 2024-09-10 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004882 | 587377753-73670-DTLTRT-09_26_2023-GO95STUB-1^668010/00 13/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-26 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004883 | 587856314-33414-DETAIL-03_27_2023-GO95HV-1^06142016.0082805 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004884 | 587856314-33414-DETAIL-03_27_2023-GO95MLD-1^06142016.0082805 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004885 | 587856314-33414-DETAIL-03_27_2023-SVCROAD-1^06142016.0082805 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004886 | 588392839-3509-DTLSB-09_03_2024-GO95MLD-1^06245007.0014302 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004887 | 588772003-91950-DETAIL-01_30_2025-GO95HV-1^06239004.0131000 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004888 | 588772003-91950-DETAIL-01_30_2025-GO95MLD-1^06239004.0131000 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004889 | 588874984-87840-DTLTRT-10_02_2023-GO95MLD-1^668010/00 14/034 | OTHER | Non-HFTD | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004890 | 58905151-74983-DETAIL-10_16_2024-CLRTOUCH-1^07216001.0209803 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004891 | 589147957-30057-DETAIL-06_27_2023-GO95BLTC-1^06244009.0270201 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004892 | 589235276-55972-DETAIL-07_10_2023-GO95HV-1^06244008.0290201 | OTHER | Non-HFTD | Distribution | 2023-07-10 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004893 | 589343493-81791-DETAIL-02_22_2023-GRDRODHI-1^06247002.0032700 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004894 | 590217156-46899-DETAIL-04_02_2024-GO95MLD-1^06247005.0343300 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004895 | 59030795-76140-DETAIL-02_25_2025-BIRDDMG-1^06240004.0151901 | POLE | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004896 | 590333271-60591-DETAIL-04_11_2024-GO95MLD-1^06245002.0143300 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004897 | 590352165-21129-DETAIL-07_07_2023-GO95MLD-1^06244008.0337100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004898 | 590655366-36359-DETAIL-03_22_2024-GRDRODHI-1^06247005.0339203 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004899 | 590984270-2739-DTLSB-02_15_2024-GO95MLD-1^07216001.0262004 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004900 | 591254360-5360-DETAIL-04_08_2024-SVCENTCO-1^06147005.0223200 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004901 | 591292221-88849-DETAIL-02_22_2024-GUYNOINS-1^07113001.0094602 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004902 | 591324389-24259-DETAIL-06_04_2024-GO95HV-1^06246005.0337202 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004903 | 591568406-63449-DETAIL-10_14_2024-CLRTOUCH-1^07216001.0204212 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004904 | 591568406-63449-DETAIL-10_14_2024-GO95MLD-1^07216001.0204212 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004905 | 591762338-53338-DETAIL-10_14_2024-CLRTOUCH-1^07216001.0204211 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004906 | 591762338-53338-DETAIL-10_14_2024-GO95MLD-1^07216001.0204211 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004907 | 591762338-53338-DETAIL-10_14_2024-SVCNEUT-1^07216001.0204211 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004908 | 592108809-50213-DETAIL-07_29_2024-GO95HV-1^06245006.0147540 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004909 | 592190519-53229-DETAIL-05_08_2024-GO95HV-1^06142012.0120303 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004910 | 592216310-57310-DETAIL-08_07_2024-ABNDEQPM-1^06245008.0229500 | OTHER | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004911 | 592216310-57310-DETAIL-08_07_2024-GUYLOINS-1^06245008.0229500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-08-07 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004912 | 592604671-78199-DETAIL-04_04_2024-GO95HV-1^06244004.0066400 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004913 | 592926424-96469-DETAIL-07_31_2024-GO95HV-1^06245004.0073701 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004914 | 593029280-59759-DETAIL-03_27_2024-GO95HV-1^06246005.0069101 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004915 | 593123109-7249-ADMIN-02_19_2025-POLEREPL-1^06245007.0219701 | POLE | Non-HFTD | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004916 | 593149569-2859-DETAIL-03_13_2023-SVCENTBK-1^07216001.0291642 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004917 | 593406123-12949-DETAIL-05_09_2023-SVCROAD-1^06245006.0270800 | OTHER | Non-HFTD | Distribution | 2023-05-09 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004918 | 593475362-43831-DETAIL-02_27_2025-GO95MLD-1^06241005.0173600 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004919 | 593574341-32889-ADMIN-06_17_2024-ABNDEQPM-1^06246006.0242900 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004920 | 593773553-75653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 7/002 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004921 | 594062198-59339-DTLSB-02_22_2024-GO95HV-1^07216001.0262902 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004922 | 594427014-63459-DTLSB-02_26_2024-ENCHRW-1^07216001.0276702 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004923 | 594810934-89349-DETAIL-10_15_2024-GO95MLD-1^07216001.0206100 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004924 | 595017381-70684-DETAIL-03_28_2023-GO95HV-1^06142016.0054200 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004925 | 59517564-68564-DETAIL-10_16_2024-GO95MLD-1^07216001.0208816 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004926 | 59543395-50101-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 6/017 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004927 | 59567154-77479-DETAIL-04_02_2025-GO95TCH-1^06241005.0029106 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004928 | 595727273-72099-DETAIL-10_26_2022-GO95HV-1^06246009.0127703 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004929 | 595728487-51329-DTLSB-08_24_2022-GO95MLD-1^06243004.0105200 | OTHER | Non-HFTD | Distribution | 2022-08-24 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004930 | 596192966-39513-DETAIL-02_04_2025-GO95HV-1^06239004.0135046 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004931 | 596883106-24261-DETAIL-02_19_2025-GO95MLD-1^06239004.0365600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004932 | 596996889-64089-DTLSB-08_04_2022-GO95MLD-1^06243004.0212201 | OTHER | Non-HFTD | Distribution | 2022-08-04 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004933 | 596996889-64089-DTLSB-08_04_2022-GRDRODHI-1^06243004.0212201 | OTHER | Non-HFTD | Distribution | 2022-08-04 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004934 | 597072959-75699-DETAIL-03_06_2024-GO95TCH-1^06147004.0139400 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004935 | 597167674-68469-DTLTRT-07_20_2022-GO95HV-1^668005/00 3/055 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004936 | 597473373-82839-DETAIL-03_13_2023-GO95TCH-1^07216001.0293410 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004937 | 597490205-49989-DETAIL-07_29_2024-CONDFRAY-1^06245006.0118900 | CONDUCTOR | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004938 | 597542535-55101-DETAIL-04_24_2024-GO95MLD-1^06145001.0042002 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004939 | 597666959-46769-ADMIN-06_15_2021-POLEDERP-1^668005/03 11/004 | POLE | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004940 | 598360844-23099-DETAIL-07_08_2024-GO95MLD-1^06244005.0010301 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004941 | 598507249-91199-DTLSB-08_27_2024-GO95MLD-1^06245007.0121900 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004942 | 598769744-15189-DETAIL-01_23_2023-GO95MLD-1^06148004.0192003 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004943 | 598769744-15189-DETAIL-01_23_2023-SVCENTCO-1^06148004.0192003 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004944 | 599107797-30639-DETAIL-03_02_2023-SVCROAD-1^07216001.0292401 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004945 | 599146991-84469-AUDIT-08_29_2022-GO95HV-1^668005/00 6/054 | OTHER | Non-HFTD | Transmission | 2022-08-29 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004946 | 599418563-19339-DETAIL-06_25_2024-GO95MLD-1^06244005.0235600 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004947 | 599587531-13911-DETAIL-02_01_2023-GO95HV-1^06146002.0075301 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004948 | 599642919-79852-DETAIL-04_02_2025-LIGHT-1^06241005.0029001 | CONNECTION DEVICE | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004949 | 599653034-25911-DETAIL-02_09_2023-GO95MLD-1^06146004.0163901 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004950 | 599653542-2680-DETAIL-02_12_2025-GO95HV-1^06240004.0281602 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004951 | 59970351-95389-DETAIL-06_17_2024-GO95MLD-1^06246006.0241101 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004952 | 599842902-58340-DTLTRT-10_03_2023-GRDRODHI-1^668010/00 1/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004953 | 59987334-81629-DTLSB-08_02_2023-GO95HV-1^06243009.0196601 | OTHER | Non-HFTD | Distribution | 2023-08-02 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004954 | 599927996-80889-DTLSB-10_01_2024-GO95MLD-1^06245007.0230000 | OTHER | Non-HFTD | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004955 | 600357898-49459-DETAIL-05_31_2024-GO95HV-1^06246005.0312500 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004956 | 600505803-68511-DETAIL-02_02_2023-GO95HV-1^06148002.0337200 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004957 | 600506049-71309-ADMIN-01_23_2024-POLEREPL-1^06147005.0261702 | POLE | Non-HFTD | Distribution | 2024-01-23 | 2027-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004958 | 60058436-51570-DETAIL-01_23_2025-GO95HV-1^06239004.0256741 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004959 | 600655631-41829-DTLSB-09_07_2023-GO95HV-1^06243008.0109800 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004960 | 600730915-37979-DTLTRT-10_31_2023-GO95HV-1^668010/00 13/016 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004961 | 600794156-21661-DETAIL-02_24_2025-GO95MLD-1^06239004.0366804 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004962 | 600794156-21661-DETAIL-11_15_2022-SVCWIND-1^06239004.0366804 | OTHER | HFTD Tier 2 | Distribution | 2022-11-15 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004963 | 601102276-99079-DETAIL-03_25_2024-GO95MLD-1^06147005.0145900 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004964 | 601415679-63930-DTLTRT-10_19_2023-GO95MLD-1^668010/00 7/026 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004965 | 601786588-35979-ADMIN-06_13_2024-CUTOUTAR-1^06148005.0330902 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-06-13 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004966 | 601809733-82869-DTLTRT-06_07_2021-GO95HV-1^668041/00 1/012 | OTHER | Non-HFTD | Transmission | 2021-06-07 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004967 | 601822316-7910-ADMIN-06_18_2024-POLEREPL-1^06239003.0015900 | POLE | Non-HFTD | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004968 | 601839621-25249-DETAIL-02_20_2024-GO95MLD-1^07113001.0137201 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004969 | 602036319-46711-DETAIL-03_19_2024-GO95MLD-1^06245002.0053501 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004970 | 602088751-57711-DETAIL-04_15_2024-GO95MLD-1^06145001.0249901 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004971 | 602295238-46670-DETAIL-02_11_2025-CLMBHAZ-1^06240004.0169506 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004972 | 602295238-46670-DETAIL-02_11_2025-SVCROAD-1^06240004.0169506 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004973 | 602295238-46670-DETAIL-03_28_2023-GO95MLD-1^06240004.0169506 | OTHER | HFTD Tier 2 | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004974 | 602327569-61509-DTLSB-09_04_2024-GO95HV-1^06245007.0015500 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004975 | 602327569-61509-DTLSB-09_04_2024-GO95MLD-1^06245007.0015500 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004976 | 60260503-14270-DTLSB-02_14_2023-GO95HV-1^06248001.0341700 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004977 | 602634998-13149-DETAIL-10_15_2024-SVCNEUT-1^07216001.0204103 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004978 | 602709846-76560-DTLTRT-10_09_2023-GUYNOINS-1^668010/00 3A/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004979 | 602755541-40539-DETAIL-06_24_2024-GO95HV-1^06244005.0232202 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004980 | 602757874-56350-DTLTRT-11_03_2023-BIRDDMG-1^668010/00 15/036 | POLE | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004981 | 602926537-73949-DETAIL-03_15_2023-GO95HV-1^07114001.0341600 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004982 | 603456828-42839-DTLSB-02_21_2024-GO95MLD-1^07216001.0262506 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004983 | 603641516-8800-DTLTRT-10_17_2023-GO95HV-1^668010/00 21X/008 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004984 | 604008573-64929-DETAIL-05_09_2024-GO95HV-1^06142012.0120504 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004985 | 604008573-64929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120504 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004986 | 604108903-54811-ADMIN-06_24_2024-POLEDERP-1^07216001.0210801 | POLE | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004987 | 604326763-94329-DTLSB-08_29_2023-GO95MLD-1^06243009.0123503 | OTHER | HFTD Tier 2 | Distribution | 2023-08-29 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004988 | 604463168-45170-DETAIL-01_23_2025-GO95CL10-1^06240004.0080101 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004989 | 604463168-45170-DETAIL-09_17_2024-SVCDEFLC-1^06240004.0080101 | OTHER | HFTD Tier 2 | Distribution | 2024-09-17 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004990 | 604571885-1029-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0122110 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004991 | 604741103-40711-DTLSB-05_22_2024-GO95MLD-1^06243001.0113100 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004992 | 604766513-30449-DTLSB-02_27_2024-GO95TCH-1^07216001.0273806 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004993 | 60492413-54470-DETAIL-04_06_2023-GO95MLD-1^06143014.0236800 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004994 | 605065249-3733-DETAIL-03_13_2023-GO95HV-1^07117002.0270501 | OTHER | HFTD Tier 2 | Distribution | 2023-03-13 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130004995 | 60527055-4570-DETAIL-08_29_2024-SVCROAD-1^06240004.0089506 | OTHER | HFTD Tier 2 | Distribution | 2024-08-29 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004996 | 605334373-45121-DTLSB-02_20_2023-GO95MLD-1^06248001.0275002 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004997 | 605354734-60180-DTLTRT-09_27_2023-GO95MLD-1^668010/00 1/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004998 | 605460208-81650-DETAIL-01_16_2025-SVCDEFLC-1^06240004.0097500 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130004999 | 605535967-48319-DETAIL-06_28_2022-GO95MLD-1^07116007.0109209 | OTHER | HFTD Tier 2 | Distribution | 2022-06-28 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005000 | 605546004-51221-DTLSB-02_09_2023-GO95HV-1^06248001.0279601 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005001 | 605801380-1749-DETAIL-03_16_2023-GUYHINS-1^07113001.0042601 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005002 | 606090414-22729-DTLSB-08_01_2023-GO95HV-1^06243009.0173602 | OTHER | HFTD Tier 2 | Distribution | 2023-08-01 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005003 | 606146598-96019-DETAIL-06_15_2022-GO95MLD-1^07116007.0112506 | OTHER | HFTD Tier 2 | Distribution | 2022-06-15 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005004 | 606249279-93330-DRONE_HY-11_13_2023-GO95HV-1^668033/00 4/030 | OTHER | HFTD Tier 2 | Transmission | 2023-11-13 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005005 | 606339372-91750-DETAIL-03_20_2025-BIRDDMG-1^06239003.0016208 | POLE | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005006 | 606339372-91750-DETAIL-03_20_2025-GO95HV-1^06239003.0016208 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005007 | 606420406-47879-DETAIL-07_25_2024-GRDRODHI-1^06244005.0350601 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005008 | 606535698-92502-DETAIL-03_06_2025-GUYHINS-1^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005009 | 606535698-92502-DETAIL-03_06_2025-GUYNOINS-2^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005010 | 606814379-36409-DTLSB-08_27_2024-GO95MLD-1^06245007.0012100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005011 | 607086574-8010-DETAIL-03_13_2025-GO95HV-1^06238004.0156241 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005012 | 607382919-48670-DETAIL-02_26_2025-GO95TCH-1^06240004.0060401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005013 | 607609766-27789-DETAIL-03_20_2024-GO95MLD-1^06244005.0144406 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005014 | 607609766-27789-DETAIL-03_20_2024-GRDRODHI-1^06244005.0144406 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005015 | 607730256-11269-DTLTRT-10_09_2023-GO95MLD-1^668010/00 9/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005016 | 607941247-37246-DTLSB-02_27_2024-GO95MLD-1^07216001.0273805 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005017 | 608035931-88621-DETAIL-04_09_2024-GO95MLD-1^06147005.0255000 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005018 | 608035931-88621-DETAIL-04_09_2024-GUYHINS-1^06147005.0255000 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005019 | 608103940-93549-DETAIL-08_01_2024-GO95MLD-1^06245006.0105103 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005020 | 60841209-30079-DETAIL-03_04_2024-GO95MLD-1^06147004.0018200 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005021 | 608509722-67601-DTLSB-09_05_2023-GO95MLD-1^06243008.0161901 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005022 | 608576506-89169-DTLTRT-10_09_2023-GO95CL10-1^668010/00 14/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005023 | 608743014-43349-DTLSB-02_14_2024-GRDRODHI-1^07216001.0198400 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005024 | 6088862-32952-DETAIL-06_08_2023-GO95HV-1^06244009.0327801 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005025 | 60897149-39049-DTLSB-02_05_2024-GO95MLD-1^07216001.0191941 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005026 | 60897149-39049-DTLSB-02_05_2024-SVCROAD-1^07216001.0191941 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005027 | 609089151-13599-DETAIL-03_20_2024-GO95MLD-1^06244004.0066401 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005028 | 609171629-24999-DETAIL-06_12_2023-GO95MLD-1^06244009.0361102 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005029 | 609186758-81858-DETAIL-06_21_2023-GO95HV-1^06244009.0337600 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005030 | 609502419-90649-DETAIL-08_19_2024-GO95HV-1^06245005.0259600 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005031 | 609692421-63299-DETAIL-06_17_2024-GO95MLD-1^06246006.0241202 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005032 | 60980975-24190-DTLTRT-10_31_2023-GO95HV-1^668010/00 1/017 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005033 | 609832528-43528-DETAIL-10_08_2024-SVCENTCO-1^07216001.0201140 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005034 | 609887708-90466-DETAIL-03_08_2023-SVCROAD-1^07216001.0296542 | OTHER | Non-HFTD | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005035 | 609890837-42837-DTLSB-08_25_2023-GO95MLD-1^06243007.0180900 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005036 | 610112214-42249-DETAIL-03_16_2023-GO95HV-1^07114001.0299701 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005037 | 610116518-72869-DTLTRT-06_10_2021-GO95HV-1^668041/00 7/015 | OTHER | Non-HFTD | Transmission | 2021-06-10 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005038 | 6115159-56989-DETAIL-06_25_2024-GO95MLD-1^06244005.0237305 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005039 | 611760299-25321-DETAIL-05_02_2024-SVCDEFLC-1^06142012.0125101 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005040 | 612043225-73389-DETAIL-08_28_2024-GO95HV-1^06245007.0141602 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005041 | 612218986-57069-DTLTRT-10_12_2023-GO95HV-1^668010/00 2/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005042 | 612218986-57069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 2/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005043 | 612247852-28750-DETAIL-03_19_2025-SVCDEFLC-1^06238004.0026101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005044 | 612247852-28750-DETAIL-03_19_2025-SVCDEFLC-2^06238004.0026101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005045 | 612491893-2369-DRONE_HY-11_15_2023-GO95HV-1^668033/00 5/035 | OTHER | HFTD Tier 2 | Transmission | 2023-11-15 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005046 | 612493551-65879-DETAIL-01_10_2023-GRDRODHI-1^06148004.0170301 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005047 | 612759735-64821-DETAIL-04_24_2024-GO95HV-1^06145001.0031000 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005048 | 612759735-64821-DETAIL-04_24_2024-GO95MLD-1^06145001.0031000 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005049 | 612842733-92733-DETAIL-03_21_2023-GUYHINS-1^07113001.0058601 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005050 | 613496385-26321-DTLSB-05_15_2024-GO95HV-1^06244001.0190100 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005051 | 613690852-34929-DTLSB-08_30_2023-GO95HV-1^06243008.0176201 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005052 | 61385156-89680-DETAIL-01_30_2025-GO95HV-1^06239004.0245701 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005053 | 613995319-74213-DETAIL-07_29_2024-GO95MLD-1^06245006.0148641 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005054 | 614012421-83150-DETAIL-03_11_2025-GO95HV-1^06238004.0272742 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005055 | 614154391-44920-DETAIL-03_06_2025-GO95TCH-1^06240004.0271004 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005056 | 614493828-5828-DETAIL-03_23_2023-GO95HV-1^06142016.0081802 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005057 | 614873221-67201-DETAIL-02_04_2025-GO95HV-1^06239004.0135048 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005058 | 614879023-84350-DETAIL-03_24_2025-GO95HV-1^06239004.0135401 | OTHER | HFTD Tier 3 | Distribution | 2025-03-24 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005059 | 531492854-27821-DTLSB-05_07_2024-GO95MLD-1^06245001.0190400 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005060 | 531673428-54428-DETAIL-10_10_2024-GO95MLD-1^07216001.0201201 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005061 | 531673428-54428-DETAIL-10_10_2024-SVCENTBK-2^07216001.0201201 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005062 | 531771324-29813-AUDIT-05_22_2024-GO95TCH-1^06245007.0228741 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005063 | 531771324-29813-DTLSB-05_02_2024-GO95HV-1^06245007.0228741 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005064 | 614993384-59899-DETAIL-03_21_2024-GO95HV-1^06147005.0209502 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005065 | 615069155-95200-DETAIL-03_25_2025-GO95HV-1^06239003.0019505 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005066 | 615458223-39223-DETAIL-03_11_2024-GO95MLD-1^06147004.0013901 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005067 | 615757184-50549-DTLSB-04_23_2024-GO95MLD-1^06245007.0223706 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005068 | 615963911-85199-DETAIL-06_27_2023-GO95MLD-1^06244009.0289200 | OTHER | Non-HFTD | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005069 | 616416651-25149-DETAIL-02_26_2024-GO95MLD-1^07113001.0138306 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005070 | 616548673-10931-DETAIL-10_21_2024-GO95MLD-1^07216001.0209605 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005071 | 616602506-25699-DETAIL-07_25_2024-SVCDEFLC-1^06244005.0354904 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005072 | 616768261-2361-DETAIL-03_30_2023-GO95TCH-1^06142016.0054010 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005073 | 616802259-93649-DETAIL-08_19_2024-GO95HV-1^06245005.0250000 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005074 | 616802259-93649-DETAIL-08_19_2024-GO95MLD-1^06245005.0250000 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005075 | 616802259-93649-DETAIL-08_19_2024-GRDRODHI-1^06245005.0250000 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005076 | 617154201-54809-DETAIL-11_10_2022-ABNDEQPM-1^06246008.0063001 | OTHER | HFTD Tier 2 | Distribution | 2022-11-10 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005077 | 617226473-85179-DTLTRT-09_27_2023-GUYHINS-1^668010/00 20/005 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005078 | 617226473-85179-DTLTRT-09_27_2023-GUYHINS-2^668010/00 20/005 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005079 | 531814186-71319-DETAIL-10_24_2022-GO95HV-1^06247008.0315303 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005080 | 532204242-78421-DTLSB-02_20_2023-GO95HV-1^06248001.0345800 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005081 | 532204242-78421-DTLSB-02_20_2023-GO95MLD-1^06248001.0345800 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005082 | 532251514-14514-DETAIL-03_27_2023-GO95HV-1^06142016.0082806 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005083 | 532251514-14514-DETAIL-03_27_2023-GO95MLD-1^06142016.0082806 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005084 | 532953750-36749-DTLSB-02_16_2024-GO95HV-1^07216001.0263202 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005085 | 532953750-36749-DTLSB-02_16_2024-GO95MLD-1^07216001.0263202 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005086 | 533183332-77949-ADMIN-03_06_2024-ABNDEQPM-1^07113002.0183203 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005087 | 533223013-74879-AUDIT-02_07_2023-GO95HV-1^06248001.0256002 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005088 | 533327158-83989-DETAIL-03_25_2024-GO95MLD-1^06244005.0145302 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005089 | 533487581-2052-DETAIL-06_26_2023-GO95BLTC-1^06244009.0310701 | OTHER | Non-HFTD | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005090 | 533576029-66753-DTLSB-04_29_2024-GO95MLD-1^06245007.0226447 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005091 | 533580403-38079-DETAIL-06_11_2024-GRDRODHI-1^06245007.0345104 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005092 | 533580403-38079-DETAIL-06_11_2024-GRDRODHI-2^06245007.0345104 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005093 | 533835374-39479-DTLSB-07_25_2023-GO95MLD-1^06243009.0055500 | OTHER | Non-HFTD | Distribution | 2023-07-25 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005094 | 534002121-66709-DETAIL-11_02_2022-GO95TCH-1^06246008.0051603 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005095 | 534479826-70572-DETAIL-08_08_2024-GO95HV-1^06245006.0091440 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005096 | 535308475-2139-DETAIL-03_13_2023-SVCWIND-1^07216001.0290700 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005097 | 535382145-94600-DETAIL-03_27_2025-GO95HV-1^06239003.0016715 | OTHER | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005098 | 535573809-90613-DETAIL-05_31_2024-GO95HV-1^06246005.0333103 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005099 | 53572998-63998-DTLSB-02_08_2024-GO95MLD-1^07216001.0309905 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005100 | 535814280-94970-DETAIL-03_20_2025-GO95HV-1^06239002.0026501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005101 | 536962883-26239-DETAIL-07_17_2024-GO95HV-1^06244005.0281101 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005102 | 537236814-14839-DTLSB-02_06_2024-GO95MLD-1^07216001.0309916 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005103 | 537247597-81109-DTLSB-08_21_2023-GO95MLD-1^06243009.0219000 | OTHER | Non-HFTD | Distribution | 2023-08-21 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005104 | 537247597-81109-DTLSB-08_21_2023-GUYHINS-1^06243009.0219000 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-08-21 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005105 | 5377114-30214-DETAIL-03_29_2023-GO95HV-1^06142016.0085101 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005106 | 537873898-15269-DETAIL-05_24_2023-GO95HV-1^06245005.0192300 | OTHER | Non-HFTD | Distribution | 2023-05-24 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005107 | 538333675-12161-DETAIL-02_18_2025-BIRDDMG-1^06241005.0230600 | POLE | HFTD Tier 3 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005108 | 538364670-42329-DTLTRT-10_26_2022-GO95HV-1^668001/00 12/028 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005109 | 538393649-42259-DETAIL-05_31_2024-GO95HV-1^06246005.0338401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005110 | 538653892-24579-DTLSB-08_26_2024-GO95MLD-1^06245007.0113401 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005111 | 538839548-41959-DETAIL-04_08_2024-GO95BLTC-1^06247005.0352400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005112 | 53902316-31990-DTLTRT-04_18_2024-GO95HV-1^668067/00 5/020 | OTHER | Non-HFTD | Transmission | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005113 | 53902316-62402-DTLTRT-04_18_2024-GO95HV-1^668067/00 5/020 | OTHER | Non-HFTD | Transmission | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005114 | 539466649-80521-DETAIL-04_03_2025-GO95HV-1^06241005.0092000 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005115 | 539520571-24702-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005116 | 540008974-73339-DETAIL-06_24_2024-GO95MLD-1^06244005.0233040 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005117 | 54014171-45582-DETAIL-07_05_2023-GO95MLD-1^06244009.0124300 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005118 | 540977502-50450-DETAIL-01_31_2025-GO95HV-1^06239004.0136201 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005119 | 541116418-77418-DETAIL-04_17_2019-SVCROOF-1^06142012.0122002 | OTHER | Non-HFTD | Distribution | 2019-04-17 | 2022-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005120 | 541116418-77418-DETAIL-04_17_2019-SVCWIND-1^06142012.0122002 | OTHER | Non-HFTD | Distribution | 2019-04-17 | 2022-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005121 | 541128684-96679-DTLSB-02_07_2023-GO95HV-1^06248001.0156101 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005122 | 541278183-5129-DETAIL-05_09_2024-GO95MLD-1^06142012.0120500 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005123 | 541278183-5129-DETAIL-05_09_2024-SVCDEFLC-1^06142012.0120500 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005124 | 541388094-21531-DTLSB-05_09_2024-GO95MLD-1^06244001.0112900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005125 | 541618446-22331-DRONE_HY-10_12_2023-GO95HV-1^668033/00 2/046 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005126 | 541867836-72649-DETAIL-03_02_2023-GO95MLD-1^07216001.0293903 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005127 | 541867836-72649-DETAIL-03_02_2023-SVCENTBK-1^07216001.0293903 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005128 | 541889790-5890-DETAIL-01_21_2025-SVCENTCO-1^06239004.0255400 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005129 | 54203595-44269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 9/041 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005130 | 54203595-44269-DTLTRT-10_10_2023-UBPRMSHD-1^668010/00 9/041 | CONNECTION DEVICE | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005131 | 542275154-9049-DETAIL-03_14_2023-GO95MLD-1^07114001.0284204 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005132 | 542301073-31409-ADMIN-05_30_2024-ABNDEQPM-1^06246005.0219900 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005133 | 54236794-37289-DTLSB-08_28_2024-GO95HV-1^06245007.0140202 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005134 | 54236794-37289-DTLSB-08_28_2024-GO95TCH-1^06245007.0140202 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005135 | 543030253-10731-DTLSB-05_22_2024-GO95HV-1^06243001.0104501 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005136 | 543464189-7189-DETAIL-03_16_2023-GO95CL10-1^07113001.0044906 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005137 | 543753983-79279-DTLSB-02_02_2023-GO95MLD-1^06248001.0250000 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005138 | 543815098-73849-DTLSB-02_21_2024-GO95MLD-1^07216001.0260803 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005139 | 543919678-95169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 6/044 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005140 | 543919678-95169-DTLTRT-10_11_2023-GRDRODHI-1^668010/00 6/044 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005141 | 543964741-96350-DETAIL-02_11_2025-GUYHINS-1^06239004.0124904 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005142 | 544229683-97799-ADMIN-03_11_2024-GO95TCH-1^06147005.0177300 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005143 | 544281055-86449-DETAIL-03_15_2023-GO95CL10-1^07114001.0325100 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005144 | 544313963-17879-DTLSB-02_02_2023-GO95HV-1^06248001.0266000 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005145 | 544319248-22431-DTLSB-01_26_2023-GO95HV-1^06247001.0015901 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005146 | 544420149-13829-DETAIL-05_13_2024-GO95HV-1^06142012.0123304 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005147 | 544590039-95999-DETAIL-04_01_2024-GO95MLD-1^06147005.0097900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005148 | 544934648-13131-DETAIL-04_16_2024-GO95MLD-1^06145001.0129501 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005149 | 544979373-60799-DETAIL-06_18_2024-BIRDDMG-1^06245007.0291400 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005150 | 545238706-5798-DETAIL-05_09_2022-GO95HV-1^07116001.0096203 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005151 | 545312945-76451-DETAIL-02_24_2025-GO95MLD-1^06239004.0366705 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005152 | 545312945-76451-DETAIL-02_24_2025-SVCDEFLC-1^06239004.0366705 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005153 | 545587866-3089-DTLSB-08_24_2023-GO95MLD-1^06243009.0118603 | OTHER | Non-HFTD | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005154 | 546055566-8259-DETAIL-03_28_2024-GO95MLD-1^06247005.0332902 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005155 | 546150346-71169-DTLTRT-10_23_2023-GO95HV-1^668010/00 7/043 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005156 | 546491123-34005-DRONE_HY-09_27_2023-GO95HV-1^668033/00 5X1/003 | OTHER | Non-HFTD | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005157 | 546524553-68983-DETAIL-08_20_2024-GO95HV-1^06246004.0185141 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005158 | 547181519-85241-DETAIL-05_02_2024-GO95HV-1^06142012.0127102 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005159 | 547187722-48980-DETAIL-02_25_2025-SVCNEUT-1^06240005.0016000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005160 | 547414443-79950-DETAIL-02_03_2025-GO95MLD-1^06239004.0244949 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005161 | 547525541-10939-ADMIN-07_01_2024-POLEDERP-1^07216001.0033108 | POLE | Non-HFTD | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005162 | 54761075-71329-DTLSB-08_02_2023-GO95TCH-1^06243010.0132100 | OTHER | HFTD Tier 2 | Distribution | 2023-08-02 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005163 | 54767466-44289-DETAIL-02_06_2023-GO95MLD-1^06147002.0200600 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005164 | 547704533-72749-DTLSB-02_27_2024-GO95HV-1^07216001.0278805 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005165 | 548330817-48490-DETAIL-02_03_2025-GO95HV-1^06239004.0244946 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005166 | 548932335-3741-DETAIL-04_23_2024-GO95MLD-1^06145001.0035102 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005167 | 549280546-77549-DTLSB-02_22_2023-GO95MLD-1^07216001.0288702 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005168 | 549415962-84341-DETAIL-10_21_2024-GO95HV-1^07216001.0209402 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005169 | 549448374-36341-DETAIL-04_12_2022-SVCROAD-1^06142012.0130400 | OTHER | Non-HFTD | Distribution | 2022-04-12 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005170 | 549506588-91541-DETAIL-03_19_2024-GO95MLD-1^06245002.0028000 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005171 | 549780174-8229-DTLSB-08_16_2023-GO95HV-1^06243010.0134200 | OTHER | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005172 | 549819258-86110-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 6/056 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005173 | 550108633-44259-DETAIL-06_11_2024-SVCDEFLC-1^06245007.0344100 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005174 | 55033287-61609-DTLSB-09_04_2024-GO95MLD-1^06245006.0072903 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005175 | 550518575-62269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 16/040 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005176 | 550542026-83080-DRONE_HY-11_10_2023-GO95HV-1^668033/00 5/048 | OTHER | HFTD Tier 2 | Transmission | 2023-11-10 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005177 | 551277364-32460-DETAIL-01_23_2025-GO95BLTC-1^06239004.0257804 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005178 | 551427674-46569-DTLSB-04_23_2024-GO95MLD-1^06245007.0223701 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005179 | 552098426-60623-DTLSB-05_02_2024-GUYNOINS-2^06245007.0222541 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005180 | 552135201-79529-DTLSB-08_16_2023-GO95MLD-1^06243009.0281900 | OTHER | Non-HFTD | Distribution | 2023-08-16 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005181 | 552239344-1444-DETAIL-04_25_2024-SVCDEFLC-1^06142016.0174700 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005182 | 552717796-52269-DRONE_VS-11_13_2024-INSULBRK-1^668047/00 1/032 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005183 | 553370078-94840-DETAIL-03_26_2025-SVCDEFLC-1^06239003.0018205 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005184 | 553417844-60590-DETAIL-03_13_2025-GO95HV-1^06239003.0252300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005185 | 553457769-289-DETAIL-07_24_2024-GO95MLD-1^06244005.0359801 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005186 | 553457833-62109-DTLSB-09_06_2023-ABNDEQPM-1^06243007.0202700 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005187 | 553461728-14856-DETAIL-10_08_2024-SVCENTBK-1^07216001.0201040 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005188 | 553727951-43539-DETAIL-06_24_2024-GO95HV-1^06244005.0231102 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005189 | 553854954-65094-DETAIL-03_30_2023-GUYNOINS-1^06142016.0085805 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005190 | 55390411-47449-DETAIL-02_27_2024-GO95MLD-1^07113001.0139800 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005191 | 553987318-32450-DETAIL-03_26_2025-GO95HV-1^06239003.0018407 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005192 | 554063016-62470-DETAIL-01_23_2025-GO95HV-1^06239004.0256800 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005193 | 554300324-5129-DETAIL-04_03_2025-CLRTOUCH-1^06241005.0039700 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-04-03 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005194 | 554880706-37909-DETAIL-04_01_2024-GO95HV-1^06147005.0128701 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005195 | 555093478-67651-DETAIL-04_23_2024-GO95MLD-1^06145001.0025201 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005196 | 555678041-80539-DETAIL-07_18_2024-GO95HV-1^06244004.0086600 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005197 | 555721811-16289-DTLSB-08_26_2024-GO95MLD-1^06245007.0113501 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005198 | 555721811-16289-DTLSB-08_26_2024-GUYNOINS-1^06245007.0113501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005199 | 556996560-77149-DETAIL-07_01_2024-GO95MLD-1^06245007.0190101 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005200 | 557194091-41480-DETAIL-02_11_2025-BIRDDMG-1^06240004.0169413 | POLE | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005201 | 557417951-31280-DETAIL-03_20_2025-GO95HV-1^06239002.0046400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005202 | 557956654-74649-DETAIL-10_22_2024-CLRTOUCH-1^07216001.0208101 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005203 | 558161071-31171-DETAIL-06_17_2024-GO95MLD-1^06246006.0238600 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005204 | 558214470-16221-DTLTRT-06_15_2021-GRDRODHI-2^668041/00 1/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005205 | 558277775-87263-DETAIL-04_24_2023-GO95MLD-1^07117003.0101600 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005206 | 558335602-42651-DTLSB-02_20_2023-GO95MLD-1^06248001.0340900 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005207 | 558335602-42651-DTLSB-02_20_2023-GO95TCH-1^06248001.0340900 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005208 | 558336996-97569-DETAIL-06_06_2024-GO95MLD-1^06245006.0036601 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005209 | 558377586-49423-DTLSB-04_24_2024-GO95HV-1^06245007.0223641 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005210 | 558377586-49423-DTLSB-04_24_2024-GO95MLD-1^06245007.0223641 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005211 | 558464254-8040-DTLTRT-10_02_2023-GO95HV-1^668010/00 1/034 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005212 | 558478671-73229-DETAIL-05_08_2024-GO95HV-1^06142012.0120302 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005213 | 558478671-73229-DETAIL-05_08_2024-GO95MLD-1^06142012.0120302 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005214 | 558577353-63049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291603 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005215 | 558856502-86880-DETAIL-02_20_2025-GO95HV-1^06240004.0319800 | OTHER | HFTD Tier 3 | Distribution | 2025-02-20 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005216 | 558941819-79243-DETAIL-03_26_2024-GO95TCH-1^06246005.0040602 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005217 | 558953990-69770-DETAIL-02_12_2025-RISEGRD-1^06240004.0167501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005218 | 559179980-73349-DETAIL-02_19_2024-GO95MLD-1^07113002.0184101 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005219 | 559179980-73349-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0184101 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005220 | 559335161-18351-DETAIL-04_16_2024-GO95HV-1^06145002.0073500 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005221 | 559505688-43451-DTLSB-02_09_2023-GO95HV-1^06248001.0229501 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005222 | 55956259-84749-DTLSB-02_20_2024-SVCENTCO-1^07216001.0260503 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005223 | 55956259-84749-DTLSB-02_20_2024-SVCENTCO-2^07216001.0260503 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005224 | 559707106-58449-DETAIL-07_29_2024-GO95MLD-1^06245006.0115502 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005225 | 559707106-58449-DETAIL-07_29_2024-GUYHINS-1^06245006.0115502 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005226 | 559833491-28530-DETAIL-01_28_2025-GUYHINS-1^06240004.0171901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005227 | 559833491-28530-DETAIL-01_28_2025-GUYNOINS-1^06240004.0171901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005228 | 560151376-43870-DETAIL-01_16_2025-GO95HV-1^06239004.0256215 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005229 | 560151376-43870-DETAIL-01_16_2025-SVCENTCO-1^06239004.0256215 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005230 | 560275999-57149-DETAIL-02_19_2024-GO95MLD-1^07113002.0184003 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005231 | 560341048-7550-DETAIL-02_03_2025-SVCDEFLC-1^06240004.0163941 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005232 | 560824531-72852-DETAIL-06_15_2023-GO95MLD-1^06244009.0290700 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005233 | 561170835-39059-DETAIL-03_15_2023-SVCENTCO-1^07114001.0348200 | OTHER | HFTD Tier 2 | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005234 | 561842843-14561-DETAIL-10_22_2024-GO95MLD-1^07216001.0209542 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005235 | 56185653-6360-DETAIL-02_09_2023-GO95MLD-1^06146004.0089000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005236 | 561998340-44761-AUDIT-02_22_2023-GO95HV-1^06248001.0347600 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005237 | 561998340-44761-DTLSB-02_14_2023-GO95MLD-1^06248001.0347600 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005238 | 562100713-97239-DETAIL-07_10_2024-GO95MLD-1^06244005.0289900 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005239 | 56243918-93670-DETAIL-04_12_2023-GO95TCH-1^06240004.0167900 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005240 | 562513891-30170-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 4/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005241 | 562543083-58480-DETAIL-02_11_2025-RISEGRD-1^06240004.0167405 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005242 | 562622071-79950-DETAIL-03_24_2025-GO95MLD-1^06238004.0026701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005243 | 563275008-36008-DETAIL-03_16_2023-GO95HV-1^07114001.0281602 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005244 | 563275008-36008-DETAIL-03_16_2023-SVCENTCO-1^07114001.0281602 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005245 | 563683890-26459-DETAIL-05_10_2022-GO95MLD-1^07116001.0059402 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005246 | 563907868-92369-DETAIL-08_12_2024-GO95MLD-1^06245006.0102403 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005247 | 563998896-22839-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0297901 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005248 | 563998896-22839-DETAIL-02_23_2023-GO95CL10-1^07216001.0297901 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005249 | 564106824-58824-DETAIL-03_29_2023-GO95HV-1^06142016.0084706 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005250 | 564116759-82261-DETAIL-04_02_2024-GO95HV-1^06147005.0096000 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005251 | 56438543-48560-DTLSB-02_16_2023-ABNDEQPM-1^06248001.0334901 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005252 | 564591324-2240-DETAIL-03_02_2023-GO95MLD-1^07117002.0201307 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005253 | 564826093-47038-DETAIL-02_23_2023-CLRTOUCH-1^07216001.0298808 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005254 | 564826093-47038-DETAIL-02_23_2023-GO95MLD-1^07216001.0298808 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005255 | 617226473-85179-DTLTRT-09_27_2023-GUYHINS-3^668010/00 20/005 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005256 | 617480657-23959-DETAIL-04_08_2024-GO95MLD-1^06247005.0322200 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005257 | 617481448-94243-DETAIL-03_09_2023-GO95CL10-1^07117002.0208102 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005258 | 617777094-98469-DTLTRT-07_20_2022-GO95HV-1^668005/00 4/055 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005259 | 617837143-52231-DETAIL-10_21_2024-GUYNOINS-1^07216001.0209301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005260 | 617888123-9259-DETAIL-06_18_2024-BIRDDMG-1^06245007.0297202 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005261 | 618004741-49973-DETAIL-03_02_2023-GO95MLD-1^07117002.0200200 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005262 | 618067151-17331-DTLSB-02_20_2023-GO95MLD-1^06248001.0287400 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005263 | 618271961-42632-DETAIL-06_21_2023-GO95MLD-1^06244009.0282001 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005264 | 61829080-81143-DETAIL-03_26_2024-SVCENTBK-1^06246005.0050500 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005265 | 618513231-28431-DETAIL-04_15_2024-GO95HV-1^06145002.0064601 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005266 | 618513231-28431-DETAIL-04_15_2024-GO95MLD-1^06145002.0064601 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005267 | 618646698-79589-DETAIL-10_28_2021-ENCHRW-1^06148005.0254700 | OTHER | Non-HFTD | Distribution | 2021-10-28 | 2024-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005268 | 619216898-29739-DETAIL-10_08_2024-GUYHINS-1^07216001.0200111 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005269 | 619307588-32959-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 9/032 | OTHER | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005270 | 619307588-32959-DTLTRT-06_30_2022-GO95MLD-1^668005/00 9/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005271 | 619782632-42540-DTLTRT-10_03_2023-GUYNOINS-2^668010/00 11A/031 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005272 | 61995393-38709-DTLSB-07_23_2024-GO95HV-1^06245007.0108200 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005273 | 620050061-88609-DTLSB-08_27_2024-BIRDDMG-1^06245007.0119704 | POLE | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005274 | 620196125-55949-DETAIL-02_26_2024-GO95HV-1^07113001.0213400 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005275 | 620196125-55949-DETAIL-02_26_2024-GO95MLD-1^07113001.0213400 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005276 | 620509399-1579-DTLTRT-10_26_2023-GO95MLD-1^668010/00 5/023 | OTHER | Non-HFTD | Transmission | 2023-10-26 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005277 | 620928074-64009-DTLSB-04_24_2024-GO95HV-1^06245007.0223802 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005278 | 62097004-43529-DETAIL-05_30_2023-GO95HV-1^06244010.0347500 | OTHER | HFTD Tier 2 | Distribution | 2023-05-30 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005279 | 621021815-73349-DETAIL-02_28_2024-SVCROAD-1^07113002.0182604 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005280 | 621059118-57970-DETAIL-01_23_2025-GO95CL10-1^06240004.0081102 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005281 | 621503174-13080-DTLTRT-10_31_2023-GO95HV-1^668010/00 15/015 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005282 | 621914244-15244-DETAIL-04_22_2024-GRDRODHI-1^06146001.0365203 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005283 | 622291423-55423-DETAIL-04_30_2024-GO95HV-1^06142016.0061100 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005284 | 622415749-12259-DETAIL-05_31_2024-GO95HV-1^06246005.0338400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005285 | 622575944-14649-DETAIL-10_22_2024-GUYHINS-2^07216001.0208100 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005286 | 622785331-95080-DETAIL-04_17_2023-GO95BLTC-1^06240004.0165643 | OTHER | HFTD Tier 2 | Distribution | 2023-04-17 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005287 | 622785331-95080-DETAIL-04_17_2023-GO95CL10-1^06240004.0165643 | OTHER | HFTD Tier 2 | Distribution | 2023-04-17 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005288 | 622785331-95080-DETAIL-04_17_2023-GO95HV-1^06240004.0165643 | OTHER | HFTD Tier 2 | Distribution | 2023-04-17 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005289 | 62308650-14369-DTLTRT-06_15_2021-GO95HV-1^668041/00 15/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005290 | 62310008-76069-DTLTRT-10_11_2023-GO95MLD-1^668010/00 10/043 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005291 | 623198271-22379-DETAIL-01_17_2023-GO95MLD-1^06148004.0220501 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005292 | 623279820-45631-DETAIL-05_06_2024-GO95HV-1^06142012.0124004 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005293 | 623279820-45631-DETAIL-05_06_2024-GO95MLD-1^06142012.0124004 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005294 | 623405051-95831-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0123005 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005295 | 565412845-87361-DETAIL-04_23_2024-GO95MLD-1^06145001.0035200 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005296 | 565591216-97879-DETAIL-02_03_2025-GO95HV-1^06239004.0244948 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005297 | 565660026-78649-DETAIL-03_02_2023-SVCWIND-1^07216001.0293904 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005298 | 565696818-95799-DETAIL-03_22_2024-GO95MLD-1^06247005.0287403 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005299 | 565868210-30889-DETAIL-01_30_2023-GO95MLD-1^06148003.0223601 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005300 | 56634246-11760-DETAIL-02_23_2023-CLRTOPOL-1^07216001.0295707 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005301 | 56634246-11760-DETAIL-02_23_2023-GO95MLD-1^07216001.0295707 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005302 | 566490951-94369-DTLTRT-10_24_2022-GO95MLD-1^668001/00 11/024 | OTHER | Non-HFTD | Transmission | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005303 | 566574893-20839-DETAIL-07_08_2024-GO95HV-1^06244005.0015500 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005304 | 566629774-13329-ADMIN-07_16_2024-POLEREPL-1^668067/00 1/016 | POLE | Non-HFTD | Transmission | 2024-07-16 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005305 | 566629774-13329-DTLTRT-04_16_2024-XARMSPCR-1^668067/00 1/016 | CROSSARM | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005306 | 56706378-68270-DETAIL-02_14_2025-GO95HV-1^06240004.0169401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005307 | 567072805-90109-DETAIL-01_19_2023-GO95MLD-1^06148004.0199601 | OTHER | Non-HFTD | Distribution | 2023-01-19 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005308 | 567119115-97489-DETAIL-06_07_2023-GO95MLD-1^06244006.0010601 | OTHER | Non-HFTD | Distribution | 2023-06-07 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005309 | 5672018-40819-DETAIL-11_14_2023-INSULBRK-1^668036/00 17/050 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2023-11-14 | 2024-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005310 | 567210656-26610-DETAIL-03_13_2025-GO95BLTC-1^06238004.0225701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005311 | 567325788-169-DTLTRT-06_10_2021-ANCHIDLE-1^668041/00 5/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-10 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005312 | 567325788-169-DTLTRT-06_10_2021-GO95HV-1^668041/00 5/016 | OTHER | Non-HFTD | Transmission | 2021-06-10 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005313 | 567938860-29270-DETAIL-02_18_2025-SVCROAD-1^06240004.0220403 | OTHER | HFTD Tier 3 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005314 | 569392921-34921-DETAIL-01_12_2023-SVCDEFLC-1^06240004.0089507 | OTHER | HFTD Tier 2 | Distribution | 2023-01-12 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005315 | 623567493-51703-DETAIL-05_29_2024-GO95MLD-1^06246005.0210900 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005316 | 623713673-20569-DTLTRT-04_15_2024-BIRDDMG-1^668067/00 6/008 | POLE | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005317 | 623713673-24402-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 6/008 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005318 | 623713673-65402-DTLTRT-04_15_2024-BIRDDMG-1^668067/00 6/008 | POLE | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005319 | 623713673-65402-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 6/008 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005320 | 623842364-36549-DTLSB-02_07_2024-SVCROAD-1^07216001.0199305 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005321 | 624029279-4241-DETAIL-04_10_2024-GO95HV-1^06245002.0140901 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005322 | 624128642-52389-DTLSB-08_26_2024-GO95MLD-1^06245007.0113400 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005323 | 624513615-27890-AUDIT-11_10_2023-GO95HV-1^668010/00 12/017 | OTHER | HFTD Tier 2 | Transmission | 2023-11-10 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005324 | 624826183-7419-DTLTRT-08_16_2022-POLETOP-1^668005/00 6/092 | POLE | Non-HFTD | Transmission | 2022-08-16 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005325 | 624989611-25580-DETAIL-02_14_2025-GO95HV-1^06240004.0169343 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005326 | 625419245-21390-DTLTRT-10_31_2023-GO95HV-1^668010/00 8/017 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005327 | 625442707-96849-DETAIL-03_15_2023-GO95MLD-1^07114001.0342203 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005328 | 62593964-93039-DTLSB-02_08_2024-GO95MLD-1^07216001.0308900 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005329 | 625990724-65790-DETAIL-03_26_2025-GO95HV-1^06239003.0018511 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005330 | 626175053-28769-DTLTRT-06_07_2021-GO95HV-1^668041/00 9/011 | OTHER | Non-HFTD | Transmission | 2021-06-07 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005331 | 62629174-57229-DTLSB-08_02_2023-GO95MLD-1^06243010.0135002 | OTHER | HFTD Tier 2 | Distribution | 2023-08-02 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005332 | 626333329-38549-DTLSB-04_10_2024-SVCWIND-1^06245007.0222007 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005333 | 626571-56730-DRONE_HY-10_26_2023-GO95HV-1^668033/00 4/032 | OTHER | HFTD Tier 2 | Transmission | 2023-10-26 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005334 | 626656134-45032-DETAIL-07_11_2023-GO95MLD-1^06244008.0285100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-11 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005335 | 626847999-13489-DETAIL-04_13_2023-GO95MLD-1^06245006.0229001 | OTHER | Non-HFTD | Distribution | 2023-04-13 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005336 | 626853353-76360-DETAIL-03_17_2025-GO95HV-1^06240003.0369100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005337 | 627005426-66368-DETAIL-06_22_2022-GO95MLD-1^07116007.0110308 | OTHER | HFTD Tier 2 | Distribution | 2022-06-22 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005338 | 627510131-39350-DETAIL-03_11_2025-BIRDDMG-1^06238004.0270600 | POLE | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005339 | 627881622-43059-DETAIL-10_15_2024-GO95MLD-1^07216001.0207005 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005340 | 62788945-29020-DETAIL-12_06_2024-BIRDDMG-1^668014/00 7/045 | POLE | HFTD Tier 3 | Transmission | 2024-12-06 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005341 | 628549398-30949-DETAIL-08_01_2024-GO95MLD-1^06245006.0155801 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005342 | 628795723-26650-DETAIL-01_15_2025-BIRDDMG-1^06240004.0098500 | POLE | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005343 | 630204439-98249-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0294506 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005344 | 630204439-98249-DETAIL-03_07_2023-GO95CL10-1^07216001.0294506 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005345 | 56941126-43531-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005346 | 56941126-93531-DRONE_HY-10_12_2023-GO95HV-1^668033/00 6/045 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005347 | 569450033-14940-DTLTRT-10_04_2023-BIRDDMG-1^668010/00 15/029 | POLE | HFTD Tier 2 | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005348 | 569841534-98934-DETAIL-05_01_2024-GO95MLD-1^06143015.0336701 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005349 | 570064611-60523-DETAIL-06_19_2024-GO95MLD-1^06246006.0139900 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005350 | 570070893-23280-DETAIL-02_11_2025-GO95MLD-1^06240004.0356100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005351 | 5705003-24480-DETAIL-01_30_2025-SVCROOF-1^06240004.0163702 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005352 | 570851006-92671-DTLSB-02_01_2023-ABNDEQPM-1^06248001.0369709 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005353 | 570972615-57363-DETAIL-04_24_2023-GO95HV-1^07117003.0020000 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005354 | 571262304-37780-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 6/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005355 | 571262304-66811-DTLTRT-04_16_2024-GO95HV-1^668067/00 6/013 | OTHER | Non-HFTD | Transmission | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005356 | 571262304-66811-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 6/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005357 | 571262304-7811-DTLTRT-04_16_2024-GO95HV-1^668067/00 6/013 | OTHER | Non-HFTD | Transmission | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005358 | 571262304-7811-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 6/013 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005359 | 571341503-1529-DETAIL-05_09_2024-GO95MLD-1^06142012.0120603 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005360 | 571408408-28850-ADMIN-03_27_2025-POLEDERP-1^668014/00 2/055 | POLE | HFTD Tier 3 | Transmission | 2025-03-27 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005361 | 571408408-72660-ADMIN-03_27_2025-POLEDERP-1^668014/00 2/055 | POLE | HFTD Tier 3 | Transmission | 2025-03-27 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005362 | 571424853-74271-DETAIL-10_16_2024-SVCENTCO-1^07216001.0205840 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005363 | 571500238-11989-DTLSB-09_27_2022-GO95MLD-1^06243004.0094901 | OTHER | Non-HFTD | Distribution | 2022-09-27 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005364 | 571678080-31849-DETAIL-08_13_2024-GO95HV-1^06245005.0364303 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005365 | 571874912-99650-DETAIL-03_19_2025-SVCDEFLC-1^06238004.0026200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005366 | 572084718-88249-DETAIL-03_14_2024-CLMBTRE-1^06245006.0018001 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005367 | 572084718-88249-DETAIL-03_14_2024-GO95MLD-1^06245006.0018001 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005368 | 572148684-61079-DTLSB-04_23_2024-GO95MLD-1^06245007.0223805 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005369 | 57223439-89692-DETAIL-06_14_2023-GO95HV-1^06244010.0289500 | OTHER | HFTD Tier 2 | Distribution | 2023-06-14 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005370 | 630260598-94299-DTLSB-07_01_2024-GO95MLD-1^06245006.0180000 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005371 | 631072359-72870-DETAIL-02_18_2025-SVCDEFLC-1^06240004.0221903 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005372 | 631088314-18679-DETAIL-07_11_2024-SVCDEFLC-1^06244005.0220200 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005373 | 631215991-84213-DETAIL-07_06_2023-GO95MLD-1^06244008.0325800 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005374 | 631347203-4250-DETAIL-01_16_2025-GO95HV-1^06239004.0257602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005375 | 631375286-28959-DETAIL-03_27_2024-GO95MLD-1^06247005.0320700 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005376 | 631514230-90640-DETAIL-02_06_2025-GUYHINS-1^06239003.0061003 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005377 | 631976838-38243-DTLSB-04_30_2024-GO95MLD-1^06245007.0222942 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005378 | 632141229-35741-DETAIL-04_24_2024-GO95MLD-1^06145001.0053300 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005379 | 632342276-89189-DTLSB-08_29_2023-GO95MLD-1^06243009.0118400 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005380 | 632580298-66390-DTLTRT-09_30_2020-GO95HV-1^668018/00 3/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005381 | 632792504-93753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005382 | 632901770-5639-DETAIL-03_06_2023-GO95HV-1^07216001.0296606 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005383 | 632901770-5639-DETAIL-03_06_2023-GO95TCH-1^07216001.0296606 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005384 | 632901770-5639-DETAIL-03_06_2023-SVCWIND-1^07216001.0296606 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005385 | 633491479-50151-DETAIL-01_24_2023-GO95MLD-1^06147003.0129600 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005386 | 633744813-30499-DTLSB-09_28_2022-GO95HV-1^06243004.0085000 | OTHER | Non-HFTD | Distribution | 2022-09-28 | 2027-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005387 | 633752495-18449-DETAIL-07_22_2024-GO95MLD-1^06245006.0115503 | OTHER | Non-HFTD | Distribution | 2024-07-22 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005388 | 633817061-31820-DETAIL-03_06_2025-GO95HV-1^06240004.0272300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005389 | 634100318-20651-DETAIL-04_02_2024-GO95HV-1^06147005.0166500 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005390 | 634411260-32260-DTLSB-04_24_2024-GUYNOINS-1^06245007.0224600 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005391 | 634524499-85349-DETAIL-02_27_2023-GO95HV-1^07216001.0294603 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005392 | 634524499-85349-DETAIL-02_27_2023-SVCENTCO-1^07216001.0294603 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005393 | 634625896-3672-DETAIL-08_08_2024-GO95HV-1^06245006.0097141 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005394 | 63481083-74529-DTLSB-07_31_2023-GO95MLD-1^06243009.0087500 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005395 | 572439170-21332-DETAIL-06_15_2023-GO95HV-1^06244009.0335103 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005396 | 572566159-88449-DTLSB-02_16_2024-GO95MLD-1^07216001.0261103 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005397 | 572837473-13799-DETAIL-07_08_2024-GRDRODHI-1^06244005.0125001 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005398 | 572933085-16271-DETAIL-02_07_2023-GO95HV-1^06147002.0094100 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005399 | 573024956-52049-DTLSB-02_22_2023-GO95MLD-1^07216001.0280700 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005400 | 573090855-28371-DETAIL-10_22_2024-SVCNEUT-1^07216001.0207805 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005401 | 573143809-72209-DTLSB-08_17_2023-GO95HV-1^06243009.0136401 | OTHER | HFTD Tier 2 | Distribution | 2023-08-17 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005402 | 573217861-87879-DETAIL-03_12_2024-GO95MLD-1^06147004.0056801 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005403 | 573487674-81598-ADMIN-06_15_2021-POLEDERP-1^668005/03 16/005 | POLE | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005404 | 573487674-81598-DTLTRT-10_10_2022-GO95HV-1^668005/03 16/005 | OTHER | Non-HFTD | Transmission | 2022-10-10 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005405 | 573510881-59070-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005406 | 573510881-90302-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005407 | 573957698-15719-DETAIL-08_14_2023-POLETOP-1^668036/00 5/050 | POLE | HFTD Tier 2 | Transmission | 2023-08-14 | 2024-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005408 | 574127149-25173-DETAIL-01_22_2025-RISEGRD-1^06240004.0091000 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005409 | 574208941-82829-DETAIL-05_07_2024-GO95BLTC-1^06142012.0122003 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005410 | 574229713-28399-DETAIL-07_31_2024-GO95MLD-1^06244005.0339901 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005411 | 574396121-8180-DETAIL-03_18_2025-GO95HV-1^06239001.0057700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005412 | 574467261-42533-DETAIL-01_24_2023-GO95MLD-1^06240004.0077942 | OTHER | HFTD Tier 2 | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005413 | 574770541-5219-DETAIL-08_15_2022-GO95HV-1^668005/00 4/086 | OTHER | Non-HFTD | Transmission | 2022-08-15 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005414 | 574979079-4071-DETAIL-01_25_2023-COPLLEAN-1^06148003.0355700 | POLE | Non-HFTD | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005415 | 635304390-62249-DETAIL-02_27_2023-GO95MLD-1^07216001.0297807 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005416 | 635304390-62249-DETAIL-02_27_2023-SVCWIND-1^07216001.0297807 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005417 | 635358990-15359-DETAIL-05_16_2022-GUYSLACK-1^07116001.0090900 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005418 | 635371831-69330-DETAIL-02_19_2025-RISEGRD-1^06240004.0177900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005419 | 63546876-72349-DETAIL-03_02_2023-SVCWIND-1^07216001.0293901 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005420 | 635514212-55959-DETAIL-05_29_2024-GO95MLD-1^06246005.0178102 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005421 | 635629418-26890-DETAIL-01_24_2025-GO95TCH-1^06239004.0247140 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005422 | 635791764-25740-DTLTRT-10_04_2023-GO95HV-1^668010/00 13/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005423 | 636032631-83149-DTLSB-08_27_2024-GO95MLD-1^06245007.0116801 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005424 | 636285441-52819-DETAIL-05_25_2023-RISEGRD-1^07117007.0227400 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005425 | 636515310-93499-DETAIL-03_21_2024-GO95MLD-1^06246005.0067000 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005426 | 636548079-40570-DETAIL-02_14_2025-GO95BLTC-1^06240004.0166102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005427 | 636767432-289-DTLSB-02_16_2023-GO95TCH-1^06248001.0209201 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005428 | 63708869-12949-ADMIN-10_23_2023-POLEDERP-1^07116001.0091500 | POLE | HFTD Tier 2 | Distribution | 2023-10-23 | 2024-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005429 | 637274926-77980-DETAIL-01_28_2025-GO95BLTC-1^06240004.0070901 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005430 | 637274926-77980-DETAIL-01_28_2025-GO95HV-1^06240004.0070901 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005431 | 637630588-75250-DETAIL-03_26_2025-GO95HV-1^06239003.0018306 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005432 | 637849342-19479-DTLSB-09_06_2023-GRDRODHI-1^06243007.0202302 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005433 | 637905216-47139-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0294407 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005434 | 637935350-98350-DETAIL-02_24_2025-BIRDDMG-1^06240004.0150903 | POLE | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005435 | 638136990-25949-DTLTRT-02_19_2024-SVCENTCO-1^07216001.0262204 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005436 | 638530575-7039-DETAIL-03_09_2023-GO95HV-1^07216001.0295500 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005437 | 638530575-7039-DETAIL-03_09_2023-GO95MLD-1^07216001.0295500 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005438 | 63859384-55430-DETAIL-01_13_2025-GO95BLTC-1^06240004.0086041 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005439 | 638932453-51450-DETAIL-02_04_2025-RISEBKSP-1^06239004.0134042 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005440 | 639235893-98769-DRONE_HY-09_20_2023-GO95HV-1^668002/00 15/063 | OTHER | Non-HFTD | Transmission | 2023-09-20 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005441 | 639581401-84161-DTLTRT-06_15_2021-GO95HV-1^668041/00 7/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005442 | 639638878-43671-DTLTRT-04_04_2024-BIRDDMG-1^668067/00 4/023 | POLE | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005443 | 639708929-8351-DTLSB-05_07_2024-GO95MLD-1^06245002.0249701 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005444 | 639775018-83969-DTLTRT-04_04_2024-GO95HV-1^668067/00 11/024 | OTHER | HFTD Tier 2 | Transmission | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005445 | 574997491-89479-DETAIL-01_31_2023-GO95CL10-1^06146002.0153701 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005446 | 575026769-85489-DETAIL-01_26_2023-COPLLEAN-1^06148003.0204800 | POLE | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005447 | 575114919-10273-DETAIL-04_01_2024-GO95HV-1^06246005.0038901 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005448 | 575519823-45139-DETAIL-03_01_2023-GUYHINS-1^07216001.0291704 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005449 | 575737673-52879-DTLTRT-09_27_2023-GO95HV-1^668010/00 1/006 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005450 | 575782825-20872-DETAIL-06_06_2023-GO95HV-1^06244010.0342500 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005451 | 575911092-51452-DETAIL-04_02_2025-GO95TCH-1^06241005.0118602 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005452 | 576428090-6159-DTLSB-09_30_2024-GO95MLD-1^06245007.0232401 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005453 | 57694116-91249-DETAIL-02_28_2023-SVCWIND-1^07216001.0297701 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005454 | 576976196-54859-DETAIL-03_28_2024-GRDRODHI-1^06247005.0327500 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005455 | 57709191-78999-DTLSB-09_28_2023-GO95MLD-1^06243008.0102501 | OTHER | HFTD Tier 2 | Distribution | 2023-09-28 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005456 | 577210816-29360-DTLTRT-10_09_2023-GO95HV-1^668010/00 6/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005457 | 577332808-31681-DTLSB-02_08_2023-GO95MLD-1^06248001.0229701 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005458 | 577533082-4781-DTLSB-05_22_2024-COPLLEAN-1^06243001.0110201 | POLE | Non-HFTD | Distribution | 2024-05-22 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005459 | 577535704-81649-DETAIL-02_28_2024-GO95CL10-1^07113001.0030303 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005460 | 577721398-17881-DETAIL-02_02_2023-GO95HV-1^06148002.0287100 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005461 | 578475572-87579-DTLTRT-10_03_2023-GO95HV-1^668010/00 8/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005462 | 578685574-59190-DETAIL-03_11_2025-GO95HV-1^06239003.0362800 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005463 | 578914702-98999-DETAIL-03_21_2024-GO95HV-1^06147004.0366400 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005464 | 579286256-36419-DETAIL-07_27_2022-GO95HV-1^668005/00 5/069 | OTHER | Non-HFTD | Transmission | 2022-07-27 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005465 | 579723011-25399-DTLSB-04_24_2024-GO95MLD-1^06245007.0226500 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005466 | 580160871-43830-DETAIL-03_05_2025-ABNDEQPM-1^06240004.0204703 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005467 | 580632406-89069-DTLTRT-10_12_2023-GRDRODHI-1^668010/00 11/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005468 | 580734283-15799-DETAIL-03_11_2024-GO95HV-1^06147005.0178400 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005469 | 580752329-12669-DRONE_HY-09_14_2023-GO95HV-1^668002/00 15/039 | OTHER | HFTD Tier 2 | Transmission | 2023-09-14 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005470 | 639775018-83969-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 11/024 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005471 | 640222533-54029-DTLSB-08_25_2023-GO95HV-1^06243008.0137700 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005472 | 640311655-37132-DETAIL-07_12_2023-GO95MLD-1^06244008.0334200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005473 | 640313657-43970-DETAIL-02_26_2025-GO95TCH-1^06240004.0061307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005474 | 640313657-43970-DETAIL-02_26_2025-SVCNEUT-1^06240004.0061307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005475 | 640357578-28578-DTLSB-02_26_2024-SVCWIND-1^07216001.0277910 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005476 | 640919448-83643-DTLSB-04_30_2024-GO95MLD-1^06245007.0222847 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005477 | 640919448-83643-DTLSB-04_30_2024-SVCWIND-1^06245007.0222847 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005478 | 641004834-66061-DTLSB-05_08_2024-GO95MLD-1^06245001.0337300 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005479 | 64101309-55309-DETAIL-03_21_2024-CONDFRAY-1^06147004.0113900 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005480 | 641058373-54419-ADMIN-11_07_2022-POLEDERP-1^668005/00 13/091 | POLE | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005481 | 641251335-92449-DETAIL-07_22_2024-GO95MLD-1^06245006.0114901 | OTHER | Non-HFTD | Distribution | 2024-07-22 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005482 | 641272135-90349-DETAIL-02_28_2023-GO95MLD-1^07216001.0299803 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005483 | 641272135-90349-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299803 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005484 | 641398006-99890-DETAIL-02_11_2025-GO95MLD-1^06240004.0350600 | OTHER | HFTD Tier 3 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005485 | 641453574-35574-DETAIL-10_22_2024-GO95HV-1^07216001.0208903 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005486 | 642130396-72360-DTLTRT-10_09_2023-GO95HV-1^668010/00 4/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005487 | 642196628-43009-DETAIL-04_09_2024-GO95MLD-1^06147005.0216701 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005488 | 642444477-78659-DETAIL-10_09_2024-GO95MLD-1^07216001.0200100 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005489 | 642514763-81361-DETAIL-02_06_2023-GO95HV-1^06148002.0338001 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005490 | 64256171-12349-DETAIL-05_02_2022-SVCENTCO-1^07116001.0167905 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005491 | 643151903-92130-DETAIL-03_04_2025-GO95CL10-1^06240004.0064801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005492 | 643331652-12349-DETAIL-10_15_2024-GO95HV-1^07216001.0207003 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005493 | 643331652-12349-DETAIL-10_15_2024-SVCENTCO-1^07216001.0207003 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005494 | 643432318-48223-DETAIL-03_14_2023-SVCENTCO-1^07117003.0114901 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005495 | 58105331-56241-AUDIT-02_22_2023-GO95HV-1^06248001.0279921 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005496 | 581159003-20081-DTLSB-05_28_2024-GO95MLD-1^06243001.0126303 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005497 | 581161579-17430-DRONE_HY-11_03_2023-GO95HV-1^668033/00 12/028 | OTHER | HFTD Tier 2 | Transmission | 2023-11-03 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005498 | 581185955-69499-DETAIL-08_07_2024-GO95MLD-1^06245008.0215600 | OTHER | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005499 | 581221268-84270-DTLTRT-10_10_2023-BIRDDMG-1^668010/00 3A/045 | POLE | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005500 | 58139215-71869-ADMIN-05_15_2021-POLEDERP-1^668005/03 7/005 | POLE | Non-HFTD | Transmission | 2021-05-15 | 2024-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005501 | 581527490-82700-DETAIL-04_04_2024-GO95MLD-1^06147005.0243000 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005502 | 58178385-96729-DETAIL-05_01_2024-SVCENTCO-1^06142012.0123640 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005503 | 581877748-5859-DETAIL-04_03_2024-GO95HV-1^06246005.0074301 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005504 | 582018043-4499-DTLSB-10_01_2024-GO95MLD-1^06245007.0217200 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005505 | 582299642-49550-DETAIL-03_19_2025-SVCDEFLC-1^06238004.0025100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005506 | 582374244-26349-DTLSB-02_06_2024-GO95MLD-1^07216001.0309914 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005507 | 582374244-26349-DTLSB-02_06_2024-SVCENTCO-1^07216001.0309914 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005508 | 582852706-4298-DTLSB-08_16_2023-GUYHINS-1^06243009.0246200 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-08-16 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005509 | 582999556-87200-DTLTRT-11_01_2023-GO95HV-1^668010/00 16/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005510 | 583406426-43410-DETAIL-01_30_2025-GUYHINS-2^06240004.0163609 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005511 | 583469321-15719-ADMIN-03_25_2025-POLEDERP-1^668002/00 11/072 | POLE | HFTD Tier 2 | Transmission | 2025-03-25 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005512 | 584250393-41013-DTLSB-05_02_2024-GO95HV-1^06245007.0228740 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005513 | 584482933-48950-DETAIL-01_23_2025-GO95MLD-1^06239004.0256801 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005514 | 584588073-92680-DETAIL-02_13_2025-SVCROAD-1^06240004.0169102 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005515 | 584644045-17132-DETAIL-07_12_2023-GO95MLD-1^06244008.0335200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005516 | 584717251-11059-DTLSB-02_20_2024-GO95MLD-1^07216001.0262306 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005517 | 584717251-11059-DTLSB-02_20_2024-GO95TCH-1^07216001.0262306 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005518 | 584920539-61321-DETAIL-04_03_2025-GO95MLD-1^06241005.0093002 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005519 | 585217838-67169-DTLTRT-10_10_2023-GO95HV-1^668010/00 16/044 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005520 | 585217838-67169-DTLTRT-10_10_2023-GO95MLD-1^668010/00 16/044 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005521 | 643474088-35969-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 6/025 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005522 | 643554628-12399-DTLSB-07_02_2024-GO95HV-1^06245006.0185601 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005523 | 643594929-37479-DETAIL-04_03_2024-GO95MLD-1^06147005.0222700 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005524 | 64360018-46730-DETAIL-02_17_2025-GO95MLD-1^06240003.0314900 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005525 | 643703298-60969-DETAIL-03_25_2025-GO95HV-1^06239003.0019513 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005526 | 643767711-26580-DETAIL-03_20_2025-GO95HV-1^06239002.0036400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005527 | 644138927-20829-DTLSB-08_21_2023-GO95HV-1^06243009.0219200 | OTHER | Non-HFTD | Distribution | 2023-08-21 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005528 | 64429563-88919-DETAIL-08_17_2022-GO95MLD-1^668005/00 3/094 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005529 | 644395044-41661-DETAIL-10_21_2024-GO95MLD-1^07216001.0209504 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005530 | 644409120-12170-DETAIL-01_30_2025-SVCROAD-1^06240004.0165600 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005531 | 644600661-36611-DETAIL-06_01_2023-SVCWIND-1^06243009.0029502 | OTHER | HFTD Tier 2 | Distribution | 2023-06-01 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005532 | 644668491-57761-DETAIL-04_15_2024-GO95HV-1^06145001.0249903 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005533 | 644668491-57761-DETAIL-04_15_2024-GO95MLD-1^06145001.0249903 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005534 | 644813678-10250-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 2/059 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005535 | 644931116-5449-DETAIL-10_14_2024-GO95CL10-1^07216001.0202302 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005536 | 644959524-67699-DETAIL-03_06_2024-GO95HV-1^06147005.0172902 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005537 | 644962443-43443-DETAIL-01_22_2025-BIRDDMG-1^06239004.0255606 | POLE | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005538 | 645247633-70589-DETAIL-06_18_2024-BIRDDMG-1^06245007.0297201 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005539 | 645247633-70589-DETAIL-06_18_2024-SVCDEFLC-1^06245007.0297201 | OTHER | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005540 | 645557273-20761-DETAIL-02_16_2023-GO95MLD-1^06247002.0161103 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005541 | 645688254-60595-DETAIL-10_16_2024-GO95MLD-1^07216001.0205902 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005542 | 645763401-94363-DTLSB-04_23_2024-GO95MLD-1^06245007.0224440 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005543 | 645992814-11849-DETAIL-03_20_2023-GO95HV-1^07114001.0284306 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005544 | 646090844-53961-DETAIL-10_16_2024-SVCENTCO-1^07216001.0205802 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005545 | 646141391-6320-DETAIL-03_06_2025-GO95HV-1^06240004.0273402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005546 | 646379935-7063-DETAIL-04_24_2023-GO95MLD-1^07117003.0105601 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005547 | 646499344-38839-DTLSB-02_07_2024-GO95MLD-1^07216001.0199102 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005548 | 646739609-41969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 17/017 | POLE | Non-HFTD | Transmission | 2021-02-24 | 2024-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005549 | 646826521-80839-DRONE_HY-10_25_2023-GO95HV-1^668087/00 12/008 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005550 | 646911214-38214-ADMIN-04_21_2023-GO95TCH-1^06142016.0082804 | OTHER | Non-HFTD | Distribution | 2023-04-21 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005551 | 647311134-85839-DTLSB-02_08_2024-GO95MLD-1^07216001.0308903 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005552 | 647469431-87779-DETAIL-03_11_2024-GO95HV-1^06147004.0038600 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005553 | 647878589-97649-DETAIL-02_22_2024-GUYHINS-1^07216001.0347701 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005554 | 647889535-88971-DETAIL-03_09_2023-GUYHINS-1^07216001.0294504 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005555 | 648115869-59639-DTLSB-02_19_2024-GO95MLD-1^07216001.0262302 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005556 | 648115869-59639-DTLSB-02_19_2024-SVCENTCO-1^07216001.0262302 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005557 | 648128480-20171-DETAIL-03_19_2015-SVCWIND-2^06147001.0060800 | OTHER | Non-HFTD | Distribution | 2015-03-19 | 2018-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005558 | 648322224-69649-DTLSB-02_26_2024-GO95MLD-1^07216001.0276800 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005559 | 648400743-57829-DETAIL-03_28_2016-SVCWIND-1^06142012.0148701 | OTHER | Non-HFTD | Distribution | 2016-03-28 | 2019-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005560 | 648400743-57829-DETAIL-11_10_2021-SVCROAD-1^06142012.0148701 | OTHER | Non-HFTD | Distribution | 2021-11-10 | 2024-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005561 | 64858865-13663-DETAIL-04_24_2023-GO95MLD-1^07117003.0024101 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005562 | 648813343-55018-DETAIL-03_08_2023-GO95MLD-1^07117002.0212002 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005563 | 648813343-55018-DETAIL-03_08_2023-GO95TCH-1^07117002.0212002 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005564 | 648813343-55018-DETAIL-03_08_2023-SVCNEUT-1^07117002.0212002 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005565 | 649083706-86099-DETAIL-03_25_2024-GO95MLD-1^06244005.0148401 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005566 | 649185281-42531-DETAIL-02_27_2025-GO95MLD-1^06241005.0177700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005567 | 649301489-75753-DTLSB-05_01_2024-SECVINE-1^06245007.0225241 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005568 | 649301489-75753-DTLSB-05_01_2024-SVCWIND-1^06245007.0225241 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005569 | 649377678-3739-DETAIL-07_30_2024-GO95HV-1^06244005.0353101 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005570 | 649420451-61773-DETAIL-03_02_2023-GO95MLD-1^07117002.0200304 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005571 | 649420451-61773-DETAIL-03_02_2023-GO95TCH-1^07117002.0200304 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005572 | 649455610-69010-DTLTRT-11_16_2022-GO95HV-1^668075/00 9/026 | OTHER | Non-HFTD | Transmission | 2022-11-16 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005573 | 649455610-69010-DTLTRT-11_16_2022-GO95MLD-1^668075/00 9/026 | OTHER | Non-HFTD | Transmission | 2022-11-16 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005574 | 64951538-60679-DETAIL-03_28_2024-GO95TCH-1^06147005.0117200 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005575 | 649534924-1660-DTLTRT-04_08_2024-GO95HV-1^668062/00 4/006 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005576 | 649763581-33829-DETAIL-05_13_2024-GO95MLD-1^06142012.0123402 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005577 | 649883146-38663-DETAIL-04_03_2024-GO95MLD-1^06247005.0336900 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005578 | 64993376-15779-DETAIL-04_08_2024-CUTOUTAR-1^06147005.0245400 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005579 | 64993376-15779-DETAIL-04_08_2024-GO95MLD-1^06147005.0245400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005580 | 650066223-77059-DTLSB-09_30_2024-GO95MLD-1^06245007.0231500 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005581 | 650109321-51981-DETAIL-02_01_2023-GO95MLD-1^06146002.0074600 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005582 | 650262236-59949-DETAIL-08_20_2024-GO95HV-1^06245004.0194900 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005583 | 650451843-15309-ADMIN-06_05_2024-GO95STUB-1^06245010.0323800 | OTHER | HFTD Tier 2 | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005584 | 650499560-45849-DETAIL-03_21_2023-GO95HV-1^07113001.0049200 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005585 | 650725578-7578-DTLSB-02_26_2024-GO95TCH-1^07216001.0277707 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005586 | 650855233-13880-DETAIL-01_30_2025-PWRTRN-1^06240004.0162501 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005587 | 651059891-12480-DETAIL-03_20_2025-GO95HV-1^06239002.0032401 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005588 | 651114995-96172-DETAIL-07_07_2023-GO95MLD-1^06244008.0327500 | OTHER | HFTD Tier 2 | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005589 | 651253985-93985-DTLSB-04_16_2024-SVCWIND-1^06245007.0227207 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005590 | 651281210-15199-DETAIL-06_21_2023-GO95MLD-1^06244009.0337701 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005591 | 65161629-39149-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0185103 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005592 | 65161629-39149-DETAIL-03_26_2024-GO95MLD-1^07113002.0185103 | OTHER | HFTD Tier 2 | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005593 | 651650419-86042-DTLSB-08_14_2023-GRDRODHI-1^06243009.0244900 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005594 | 651967063-38063-DETAIL-10_24_2024-GO95CLSV-1^07216001.0208614 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005595 | 652021908-17269-DTLTRT-07_05_2022-GO95BLTC-1^668005/00 1/035 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005596 | 652661090-50452-DETAIL-04_02_2025-GO95TCH-1^06241005.0028041 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005597 | 653594855-80359-DTLSB-02_14_2024-GO95MLD-1^07216002.0139200 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005598 | 653682981-52209-DTLTRT-10_26_2022-GO95MLD-1^668001/00 19/028 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005599 | 653800393-34979-DETAIL-07_31_2024-GO95MLD-1^06244005.0292740 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005600 | 653806995-29995-DETAIL-03_22_2024-GO95HV-1^06247005.0338300 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005601 | 653917916-9759-DETAIL-03_27_2024-GO95HV-1^06247005.0327201 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005602 | 654179707-64970-DETAIL-02_25_2025-GO95MLD-1^06240004.0060100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005603 | 654249023-35959-DETAIL-06_06_2024-GO95MLD-1^06246006.0351500 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005604 | 654363628-7799-DETAIL-03_28_2024-GO95MLD-1^06147005.0151900 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005605 | 654452740-73079-ADMIN-07_24_2023-POLEREPL-1^06242009.0246903 | POLE | Non-HFTD | Distribution | 2023-07-24 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005606 | 654706843-78189-DTLSB-08_16_2023-GO95MLD-1^06243009.0283200 | OTHER | Non-HFTD | Distribution | 2023-08-16 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005607 | 655199743-19623-DTLSB-09_05_2024-BIRDDMG-1^06246006.0315340 | POLE | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005608 | 655217724-68724-DETAIL-04_25_2024-GO95HV-1^06142016.0161800 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005609 | 655462616-74616-DTLSB-02_16_2023-GO95MLD-1^06248001.0299002 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005610 | 655867016-86079-DETAIL-03_19_2025-GO95HV-1^06239001.0069603 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005611 | 656174001-53301-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299700 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005612 | 656257470-4549-DETAIL-08_06_2024-GO95HV-1^06245006.0105201 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005613 | 656405165-190-DTLTRT-04_17_2024-GO95HV-1^668067/00 7/016 | OTHER | Non-HFTD | Transmission | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005614 | 656405165-2111-DTLTRT-04_17_2024-GO95HV-1^668067/00 7/016 | OTHER | Non-HFTD | Transmission | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005615 | 656405165-2111-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 7/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005616 | 656405165-62111-DTLTRT-04_17_2024-GO95HV-1^668067/00 7/016 | OTHER | Non-HFTD | Transmission | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005617 | 656465355-74859-DETAIL-10_24_2024-SVCENTCO-1^07216001.0201505 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005618 | 656590351-62520-DETAIL-03_07_2023-GO95BLTC-1^07117002.0210300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005619 | 656808188-98570-DETAIL-02_26_2025-GO95TCH-1^06240004.0061103 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005620 | 657015826-50919-DETAIL-03_06_2025-GO95HV-1^06241005.0162900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005621 | 657193093-3299-DETAIL-04_01_2024-SVCROAD-1^06147005.0113900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005622 | 657294953-81939-DETAIL-10_10_2024-GO95MLD-1^07216001.0204107 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005623 | 657407392-87080-DETAIL-01_25_2023-GO95TCH-1^06240005.0015000 | OTHER | HFTD Tier 3 | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005624 | 657501156-20549-DETAIL-10_25_2024-GO95HV-1^07216001.0201401 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005625 | 657787963-15539-DETAIL-07_03_2024-GO95MLD-1^06244005.0230401 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005626 | 657787963-15539-DETAIL-07_03_2024-SVCDEFLC-1^06244005.0230401 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005627 | 657899678-97840-DETAIL-01_22_2025-GO95TCH-1^06240004.0092502 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005628 | 65793078-21430-DTLTRT-10_30_2023-GO95HV-1^668010/00 17X/009 | OTHER | Non-HFTD | Transmission | 2023-10-30 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005629 | 658280194-28059-ADMIN-10_13_2023-POLEDERP-1^07216001.0156400 | POLE | Non-HFTD | Distribution | 2023-10-13 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005630 | 65847215-57210-DETAIL-03_12_2025-GO95HV-1^06238004.0223600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005631 | 658523276-59989-DETAIL-07_25_2024-GO95MLD-1^06244005.0350802 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005632 | 658523276-59989-DETAIL-07_25_2024-GRDRODHI-1^06244005.0350802 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005633 | 658777181-52359-DETAIL-02_29_2024-RISEBKSP-1^07113001.0105501 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005634 | 659070054-87339-DTLSB-02_06_2024-GO95MLD-1^07216001.0308908 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005635 | 659415073-35989-DETAIL-06_24_2024-GO95MLD-1^06244005.0233100 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005636 | 659421095-91269-DTLTRT-10_10_2023-GO95HV-1^668010/00 2/041 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005637 | 659614385-35385-DETAIL-07_15_2024-GO95MLD-1^06244005.0253300 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005638 | 660006134-6753-DTLTRT-04_08_2024-GO95HV-1^668062/00 5/006 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005639 | 660006134-73660-DTLTRT-04_08_2024-GO95HV-1^668062/00 5/006 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005640 | 660006134-73660-DTLTRT-04_08_2024-INSULBRK-1^668062/00 5/006 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005641 | 660105400-15401-DETAIL-02_24_2025-SVCDEFLC-1^06241005.0158100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005642 | 660273109-50473-ADMIN-01_21_2025-ABNDEQPM-1^06240004.0092302 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005643 | 660539005-9539-DETAIL-07_10_2024-GO95MLD-1^06244004.0194000 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005644 | 661655811-24630-DETAIL-02_05_2025-GRDRODHI-2^06240004.0170701 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005645 | 662119534-54249-DETAIL-05_16_2022-GO95MLD-1^07117001.0316501 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005646 | 662451136-44579-DETAIL-04_03_2024-CLRTOUCH-1^06147005.0142200 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005647 | 663013867-87620-DTLTRT-10_24_2023-GO95HV-1^668010/00 8/009 | OTHER | HFTD Tier 2 | Transmission | 2023-10-24 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005648 | 663172973-3189-DETAIL-06_30_2023-POLEREPL-1^06247005.0214702 | POLE | Non-HFTD | Distribution | 2023-06-30 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005649 | 663304668-35668-DETAIL-10_24_2024-SVCENTCO-1^07216001.0202601 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005650 | 66373460-73080-DETAIL-02_27_2025-GO95BLTC-1^06240004.0230501 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005651 | 663828008-76270-DETAIL-01_29_2025-GO95CL10-1^06240004.0160140 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005652 | 664227948-97229-DETAIL-03_28_2016-SVCWIND-1^06142012.0148601 | OTHER | Non-HFTD | Distribution | 2016-03-28 | 2019-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005653 | 664246425-20759-DETAIL-03_06_2024-GO95MLD-1^06245007.0272904 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005654 | 664246425-20759-DETAIL-03_06_2024-POLETOP-1^06245007.0272904 | POLE | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005655 | 664415821-57739-DTLSB-02_16_2024-GO95TCH-1^07216001.0262003 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005656 | 664415821-57739-DTLSB-02_16_2024-SVCENTBK-1^07216001.0262003 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005657 | 664415821-57739-DTLSB-02_16_2024-SVCENTCO-1^07216001.0262003 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005658 | 664507112-22880-DETAIL-02_26_2025-GUYHINS-1^06240004.0150000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005659 | 664605046-12570-DETAIL-01_22_2025-GO95TCH-1^06239004.0256744 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005660 | 664626469-41269-DTLTRT-06_14_2021-GO95HV-1^668041/00 14/020 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005661 | 664661458-32289-DETAIL-08_12_2024-GUYHINS-1^06245006.0140200 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005662 | 664811359-33779-DETAIL-03_18_2024-GO95TCH-1^06245002.0035000 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005663 | 665231133-75489-DTLSB-05_22_2024-GO95MLD-1^06243001.0032000 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005664 | 665463979-8121-DETAIL-04_24_2024-GO95MLD-1^06145001.0089901 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005665 | 665503903-33529-DTLSB-07_31_2023-GO95MLD-1^06243009.0081201 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005666 | 665577628-67493-AUDIT-02_26_2025-CLRTOPOL-1^06240004.0098303 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005667 | 666076916-38270-DETAIL-01_15_2025-GO95HV-1^06239004.0255145 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005668 | 666076916-38270-DETAIL-01_15_2025-SVCDEFLC-1^06239004.0255145 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005669 | 666175239-67239-DETAIL-08_17_2022-GO95MLD-1^668005/00 3X/094 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005670 | 585509378-39069-DTLTRT-06_09_2021-ANCHIDLE-1^668041/00 2/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005671 | 585509378-39069-DTLTRT-06_09_2021-GO95HV-1^668041/00 2/016 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005672 | 585622848-2189-DETAIL-03_25_2024-GO95MLD-1^06244005.0147140 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005673 | 585998983-23391-DTLSB-05_22_2024-GO95HV-1^06243001.0106400 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005674 | 585998983-23391-DTLSB-05_22_2024-GO95MLD-1^06243001.0106400 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005675 | 666469301-29870-DETAIL-02_05_2025-SVCDEFLC-1^06240004.0166201 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005676 | 666638739-99473-ADMIN-04_27_2023-POLEREPL-1^06248007.0132001 | POLE | Non-HFTD | Distribution | 2023-04-27 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005677 | 666815641-29350-DETAIL-03_24_2025-GO95CL10-1^06238004.0028603 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005678 | 666815641-29350-DETAIL-03_24_2025-SVCROAD-1^06238004.0028603 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005679 | 667030942-42739-DETAIL-10_15_2024-GO95MLD-1^07216001.0206101 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005680 | 667059414-56949-DETAIL-02_26_2024-COPLLEAN-1^07113001.0085101 | POLE | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005681 | 667571355-4090-DTLTRT-09_26_2023-GUYHINS-2^668010/00 1X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-26 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005682 | 667837835-42031-DTLSB-05_07_2024-GO95HV-1^06245001.0302800 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005683 | 668456178-77144-DETAIL-02_04_2025-SVCDEFLC-1^06239004.0134041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005684 | 668510756-3323-DTLSB-04_29_2024-GO95MLD-1^06245007.0221540 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005685 | 669613768-27431-DETAIL-04_16_2024-GO95MLD-1^06145001.0129700 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005686 | 669753789-6930-DTLTRT-10_26_2023-GO95MLD-1^668010/00 4/023 | OTHER | HFTD Tier 2 | Transmission | 2023-10-26 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005687 | 669753789-6930-DTLTRT-10_26_2023-RISEGRD-1^668010/00 4/023 | OTHER | HFTD Tier 2 | Transmission | 2023-10-26 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005688 | 66981733-50309-DETAIL-01_18_2023-CONDFRAY-3^06148004.0210001 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005689 | 670026895-83599-ADMIN-04_01_2024-ABNDEQPM-1^06247005.0341800 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005690 | 670037368-90831-DETAIL-03_20_2024-GO95HV-1^06245002.0017300 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005691 | 670493038-69309-DETAIL-04_10_2024-GO95MLD-1^06147005.0212703 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005692 | 670522131-19231-DETAIL-04_16_2024-GO95MLD-1^06145001.0139901 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005693 | 670617930-8232-DETAIL-06_15_2023-GO95MLD-1^06244009.0335500 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005694 | 670638028-33243-DTLSB-04_30_2024-GO95MLD-1^06245007.0220841 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005695 | 670648283-3560-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 3/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005696 | 586142746-52746-DETAIL-01_29_2025-GO95MLD-1^06239004.0268800 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005697 | 586296690-55822-DETAIL-06_27_2023-GO95MLD-1^06244009.0285002 | OTHER | Non-HFTD | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005698 | 586334494-44269-DETAIL-05_26_2022-GO95HV-1^668002/00 2/001 | OTHER | Non-HFTD | Transmission | 2022-05-26 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005699 | 586350946-70691-DTLSB-05_14_2024-GO95MLD-1^06244001.0299101 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005700 | 586412073-39189-DETAIL-03_05_2024-GO95MLD-1^06245007.0277300 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005701 | 586412073-39189-DETAIL-03_05_2024-GUYHINS-1^06245007.0277300 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005702 | 586601846-11919-DETAIL-03_28_2024-GO95MLD-1^06247005.0341400 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005703 | 587121711-23711-DETAIL-04_30_2024-GO95HV-1^06142015.0029900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005704 | 587253983-66380-DETAIL-01_30_2025-GO95TCH-1^06240004.0163500 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005705 | 587290538-66689-DETAIL-08_01_2024-SVCROAD-1^06245006.0153400 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005706 | 587759789-9591-DETAIL-04_11_2024-GO95MLD-1^06245002.0143800 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005707 | 587806726-88470-DETAIL-01_24_2025-GO95HV-1^06239004.0257841 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005708 | 587856314-33414-DETAIL-03_27_2023-GRDRODHI-1^06142016.0082805 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005709 | 58788620-18899-ADMIN-01_23_2025-POLEREPL-1^06244007.0088702 | POLE | HFTD Tier 2 | Distribution | 2025-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005710 | 58804924-80959-DETAIL-05_16_2022-GO95MLD-1^07117001.0315501 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005711 | 588082218-27519-DETAIL-08_01_2022-GO95HV-1^668005/00 11/072 | OTHER | Non-HFTD | Transmission | 2022-08-01 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005712 | 588097681-97119-DETAIL-11_01_2022-GO95HV-1^06246010.0133800 | OTHER | HFTD Tier 2 | Distribution | 2022-11-01 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005713 | 588392839-3509-DTLSB-09_03_2024-GO95HV-1^06245007.0014302 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005714 | 588451453-47629-DETAIL-05_14_2024-GO95MLD-1^06142012.0122710 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005715 | 588772003-91950-DETAIL-01_30_2025-GUYHINS-1^06239004.0131000 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005716 | 588823053-889-DETAIL-05_23_2024-GO95HV-1^06243001.0120001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005717 | 588874984-87840-DTLTRT-10_02_2023-GO95HV-1^668010/00 14/034 | OTHER | Non-HFTD | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005718 | 589087435-48779-DETAIL-01_23_2023-GO95MLD-1^06148004.0192101 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005719 | 589147957-30057-DETAIL-06_27_2023-GO95MLD-1^06244009.0270201 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005720 | 589201708-16869-DTLTRT-06_09_2021-GO95HV-1^668041/00 9/016 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005721 | 670648283-72560-DTLTRT-04_09_2024-GO95HV-1^668062/00 3/003 | OTHER | Non-HFTD | Transmission | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005722 | 670965590-75409-ADMIN-01_22_2025-POLEREPL-1^06245007.0015001 | POLE | HFTD Tier 2 | Distribution | 2025-01-22 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005723 | 670965590-75409-DTLSB-09_03_2024-GO95HV-1^06245007.0015001 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005724 | 670967418-85250-DETAIL-02_23_2023-SVCENTCO-1^07216001.0297945 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005725 | 670974361-20539-DETAIL-02_26_2024-GO95HV-1^07113001.0138302 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005726 | 671878178-24359-DTLSB-02_15_2024-GO95HV-1^07216001.0191601 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005727 | 671883975-75349-DETAIL-10_24_2024-CLRTOUCH-1^07216001.0200504 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005728 | 671883975-75349-DETAIL-10_24_2024-GO95MLD-1^07216001.0200504 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005729 | 671883975-75349-DETAIL-10_24_2024-GO95TCH-1^07216001.0200504 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005730 | 671978608-92341-DETAIL-03_19_2024-GRDRODHI-1^06245002.0023001 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005731 | 672390424-37841-ADMIN-02_26_2021-COPLLEAN-1^668041/00 12/028 | POLE | Non-HFTD | Transmission | 2021-02-26 | 2024-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005732 | 672559733-94849-DETAIL-08_13_2024-GO95MLD-1^06245005.0361102 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005733 | 672978193-97763-DETAIL-03_11_2025-GO95HV-1^06238004.0274903 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005734 | 673054203-38059-DTLSB-10_07_2024-GO95MLD-1^06245007.0230500 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005735 | 673089523-72941-DTLTRT-02_14_2023-GO95BLTC-1^06248001.0342701 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005736 | 673344589-60069-DTLTRT-06_14_2021-GO95HV-1^668041/00 12/019 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005737 | 674064181-75963-DTLSB-04_17_2024-SVCROAD-1^06245007.0223344 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005738 | 674064181-75963-DTLSB-04_17_2024-SVCWIND-1^06245007.0223344 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005739 | 67408203-6303-DETAIL-03_23_2023-GO95MLD-1^06142016.0080707 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005740 | 674155571-56829-DETAIL-05_14_2024-SVCENTCO-1^06142012.0122406 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005741 | 674948213-29334-ADMIN-12_09_2024-POLEREPL-1^06143015.0335900 | POLE | HFTD Tier 2 | Distribution | 2024-12-09 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005742 | 674948213-29334-DETAIL-05_01_2024-GO95HV-1^06143015.0335900 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005743 | 675098153-50029-DTLSB-09_05_2023-GO95HV-1^06243008.0235000 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005744 | 675175274-65160-DETAIL-01_15_2025-BIRDDMG-1^06240004.0098043 | POLE | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005745 | 67527803-40139-DETAIL-02_29_2024-GO95MLD-1^07113001.0106401 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005746 | 589250919-77691-ADMIN-12_21_2022-GUYSLACK-1^668005/00 13A/028 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005747 | 589343493-81791-DETAIL-02_22_2023-GO95MLD-1^06247002.0032700 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005748 | 589954683-33291-DETAIL-04_05_2023-GO95MLD-1^06143014.0240801 | OTHER | HFTD Tier 2 | Distribution | 2023-04-05 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005749 | 59030795-76140-DETAIL-02_25_2025-GO95MLD-1^06240004.0151901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005750 | 59036723-89840-AUDIT-11_16_2023-GO95CN-1^668010/00 4/032 | OTHER | HFTD Tier 2 | Transmission | 2023-11-16 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005751 | 590777685-32529-DETAIL-05_13_2024-GO95MLD-1^06142012.0122301 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005752 | 590777685-32529-DETAIL-05_13_2024-GRDRODHI-1^06142012.0122301 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005753 | 590803871-57991-DETAIL-04_16_2024-GO95MLD-1^06145002.0182800 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005754 | 590830936-11419-DETAIL-04_02_2024-GO95HV-1^06147005.0132101 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005755 | 590984270-2739-DTLSB-02_15_2024-GO95HV-1^07216001.0262004 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005756 | 591142099-19249-DETAIL-03_14_2024-GO95MLD-1^06245005.0062502 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005757 | 591254360-5360-DETAIL-04_08_2024-GO95MLD-1^06147005.0223200 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005758 | 591589308-28259-DTLSB-02_14_2024-GO95MLD-1^07216001.0199901 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005759 | 591750684-39301-DTLSB-02_02_2023-GO95HV-1^06248001.0267002 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005760 | 591762338-53338-DETAIL-10_14_2024-GO95CL10-1^07216001.0204211 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005761 | 591863983-36893-DETAIL-05_29_2024-GO95HV-1^06246005.0178201 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005762 | 591863983-36893-DETAIL-05_29_2024-GO95MLD-1^06246005.0178201 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005763 | 591952157-82157-DTLSB-05_21_2024-GO95HV-1^06244002.0232800 | OTHER | Non-HFTD | Distribution | 2024-05-21 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005764 | 592108809-50213-DETAIL-07_29_2024-GO95MLD-1^06245006.0147540 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005765 | 592233254-73839-DTLSB-02_06_2024-GO95MLD-1^07216001.0308801 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005766 | 592233254-73839-DTLSB-02_06_2024-GRDRODHI-1^07216001.0308801 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005767 | 592604671-78199-DETAIL-04_04_2024-GO95MLD-1^06244004.0066400 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005768 | 592604671-78199-DETAIL-04_04_2024-GRDRODHI-1^06244004.0066400 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005769 | 593370241-23241-DETAIL-03_30_2023-GO95HV-1^06142016.0055201 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005770 | 59347615-44619-DETAIL-08_11_2019-POLEDERP-1^668005/00 10/096 | POLE | Non-HFTD | Transmission | 2019-08-11 | 2022-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005771 | 593500979-98149-DETAIL-04_05_2023-SVCRUBLG-1^06245006.0226000 | OTHER | Non-HFTD | Distribution | 2023-04-05 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005772 | 593500979-98149-DETAIL-04_05_2023-SVCWIND-1^06245006.0226000 | OTHER | Non-HFTD | Distribution | 2023-04-05 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005773 | 675650958-98340-ADMIN-06_18_2024-POLEREPL-1^06240003.0076102 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005774 | 67578335-23679-DTLSB-09_04_2024-GO95MLD-1^06245007.0141401 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005775 | 675857112-40051-DTLSB-02_16_2023-GO95HV-1^06248001.0209001 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005776 | 675894996-53051-DETAIL-04_18_2024-GO95HV-1^06145001.0268800 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005777 | 676034716-75579-DTLSB-01_31_2023-GO95MLD-1^06248001.0369701 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005778 | 676586401-69689-ADMIN-10_10_2024-POLEREPL-1^06146002.0034400 | POLE | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005779 | 676763801-74559-DTLSB-02_16_2024-SVCENTCO-1^07216001.0261006 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005780 | 676902468-98951-DTLSB-05_13_2024-GO95MLD-1^06244001.0155100 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005781 | 677364488-41940-DETAIL-01_21_2025-RISECLMB-1^06240004.0091601 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005782 | 678009902-31459-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0146103 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005783 | 678147265-98265-DTLSB-08_17_2023-GO95MLD-1^06243009.0131201 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005784 | 678868855-88949-DETAIL-10_08_2024-GO95MLD-1^07216001.0201000 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005785 | 679193636-64470-DETAIL-02_06_2025-GO95HV-1^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005786 | 679193636-64470-DETAIL-02_06_2025-SVCROAD-2^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005787 | 679260385-56385-DETAIL-06_28_2023-GO95MLD-1^06244008.0310901 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005788 | 679391395-7379-DETAIL-03_28_2024-GO95MLD-1^06147005.0118500 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005789 | 679530496-24361-DETAIL-02_06_2023-ABNDEQPM-1^06147002.0302200 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005790 | 679530496-24361-DETAIL-02_06_2023-GO95MLD-1^06147002.0302200 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005791 | 679943950-46263-DTLSB-04_17_2024-GO95HV-1^06245007.0222445 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005792 | 680192377-64377-DETAIL-01_16_2023-GO95MLD-1^06148004.0161305 | OTHER | Non-HFTD | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005793 | 593931746-22659-DETAIL-08_14_2024-GO95MLD-1^06246004.0311200 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005794 | 594062198-59339-DTLSB-02_22_2024-GO95MLD-1^07216001.0262902 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005795 | 594099941-72101-DETAIL-04_11_2024-GO95MLD-1^06245002.0140202 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005796 | 594155691-39002-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 3/002 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005797 | 594429618-12239-DETAIL-10_09_2024-SVCROAD-1^07216001.0204205 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005798 | 595080589-21540-ADMIN-01_24_2025-POLEREPL-1^06237005.0263102 | POLE | HFTD Tier 2 | Distribution | 2025-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005799 | 59567154-77479-DETAIL-04_02_2025-LWPAPS-1^06241005.0029106 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2026-04-30 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130005800 | 595720357-12099-DETAIL-06_22_2022-GO95MLD-1^07116007.0111305 | OTHER | HFTD Tier 2 | Distribution | 2022-06-22 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005801 | 596142846-47923-DTLSB-05_02_2024-GO95MLD-1^06245007.0222540 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005802 | 596660548-62409-DETAIL-04_09_2024-GO95MLD-1^06147005.0217701 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005803 | 596979273-52680-DETAIL-03_17_2025-GO95HV-1^06239002.0059700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005804 | 596996889-64089-DTLSB-08_04_2022-GRDRODHI-2^06243004.0212201 | OTHER | Non-HFTD | Distribution | 2022-08-04 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005805 | 597195339-82441-DETAIL-04_03_2025-GO95CL10-1^06241005.0089004 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2030-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005806 | 597195339-82441-DETAIL-04_03_2025-GO95MLD-1^06241005.0089004 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005807 | 597290949-73579-DETAIL-04_09_2024-GO95MLD-1^06147005.0217200 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005808 | 597699816-23509-DETAIL-04_04_2024-GO95HV-1^06147005.0238101 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005809 | 597816976-93149-DETAIL-10_09_2024-GO95MLD-1^07216001.0204201 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005810 | 597879960-31939-DETAIL-03_06_2023-GO95MLD-1^07216001.0297605 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005811 | 598205686-62321-DTLTRT-11_01_2023-GO95HV-1^668010/00 19/018 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005812 | 598389191-37701-DETAIL-04_16_2024-GO95HV-1^06145002.0184803 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005813 | 598389191-37701-DETAIL-04_16_2024-GO95MLD-1^06145002.0184803 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005814 | 598507249-91199-DTLSB-08_27_2024-GO95HV-1^06245007.0121900 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005815 | 598769744-15189-DETAIL-01_23_2023-GO95TCH-1^06148004.0192003 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005816 | 598880406-98070-DETAIL-01_15_2025-GO95MLD-1^06239004.0254142 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005817 | 598893539-58569-DTLTRT-06_09_2021-GO95HV-1^668041/00 7/014 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005818 | 599158349-75081-AUDIT-03_04_2025-ANCHIDLE-1^06241005.0152401 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005819 | 680596104-12749-DTLSB-02_26_2024-GO95MLD-1^07216001.0277705 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005820 | 680865646-90973-DTLSB-04_22_2024-SVCWIND-1^06245007.0227246 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005821 | 680865646-90973-DTLSB-04_22_2024-SVCWIND-2^06245007.0227246 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005822 | 681151799-4361-DETAIL-03_18_2024-GO95HV-1^06245002.0057900 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005823 | 68132273-2899-DTLSB-10_07_2024-GO95MLD-1^06245007.0219205 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005824 | 681404232-97109-DTLSB-08_26_2024-GO95MLD-1^06245007.0114303 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005825 | 681648778-89041-DETAIL-03_06_2025-GO95BLTC-1^06241005.0161800 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005826 | 681693796-35796-DTLSB-08_23_2023-GO95HV-1^06243009.0110340 | OTHER | Non-HFTD | Distribution | 2023-08-23 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005827 | 682272074-28849-DETAIL-03_13_2023-CLRTOPOL-1^07216001.0290701 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005828 | 682272074-28849-DETAIL-03_13_2023-SVCNEUT-1^07216001.0290701 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005829 | 682349924-11024-DETAIL-03_29_2023-GO95MLD-1^06142016.0084709 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005830 | 682349924-11024-DETAIL-03_29_2023-SVCROAD-1^06142016.0084709 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005831 | 682879741-87973-DETAIL-03_02_2023-SVCROAD-1^07117002.0201202 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005832 | 682905902-87880-DETAIL-02_12_2025-GO95HV-1^06240004.0320903 | OTHER | HFTD Tier 3 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005833 | 682946623-34171-DETAIL-02_22_2023-GO95HV-1^06247002.0030601 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005834 | 68312250-81369-DETAIL-03_21_2024-GO95MLD-1^06246005.0067101 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005835 | 683828248-67299-DTLSB-07_02_2024-GUYNOINS-1^06245006.0184101 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005836 | 683845615-18329-DETAIL-07_07_2023-GO95MLD-1^06244008.0335700 | OTHER | Non-HFTD | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005837 | 684007844-66464-DETAIL-06_24_2024-GO95MLD-1^06244005.0230000 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005838 | 684166759-55873-DETAIL-01_21_2025-BIRDDMG-1^06240004.0092201 | POLE | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005839 | 684760588-51019-ADMIN-03_13_2025-POLEREPL-1^06242009.0066401 | POLE | HFTD Tier 2 | Distribution | 2025-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005840 | 684843353-30171-DTLSB-02_16_2023-GO95MLD-1^06248001.0334900 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005841 | 685074806-86898-DETAIL-05_09_2022-GO95HV-1^07116001.0097100 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005842 | 685097671-95989-DETAIL-01_10_2023-GO95TCH-1^06148004.0186201 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005843 | 685265388-74010-DTLSB-02_13_2024-SVCDEFLC-1^07216001.0187200 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005844 | 685265388-74010-DTLSB-02_13_2024-SVCENTCO-1^07216001.0187200 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005845 | 685897466-20171-DTLSB-01_31_2023-GO95MLD-1^06248001.0369704 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005846 | 686070294-67171-DETAIL-04_17_2024-GO95HV-1^06144001.0122700 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005847 | 686266160-35789-DETAIL-01_09_2023-GO95MLD-1^06148003.0154302 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005848 | 686340488-50181-DTLSB-02_01_2023-GO95HV-1^06247001.0010901 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005849 | 59934178-36869-DRONE_HY-09_29_2023-GO95HV-1^668033/00 14/005 | OTHER | HFTD Tier 2 | Transmission | 2023-09-29 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005850 | 59987334-81629-DTLSB-08_02_2023-GO95MLD-1^06243009.0196601 | OTHER | Non-HFTD | Distribution | 2023-08-02 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005851 | 599928083-56059-DTLSB-09_30_2024-GO95BLTC-1^06245007.0234502 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005852 | 599928083-56059-DTLSB-09_30_2024-GO95HV-1^06245007.0234502 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005853 | 599928083-56059-DTLSB-09_30_2024-GO95MLD-1^06245007.0234502 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005854 | 599951468-21211-DETAIL-01_30_2023-GO95HV-1^06147003.0302800 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005855 | 600034721-60709-DTLSB-08_27_2024-SVCDEFLC-1^06245007.0114801 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005856 | 600291021-32021-AUDIT-05_30_2024-GUYHINS-1^06142016.0079904 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-05-30 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005857 | 600291021-32021-DETAIL-04_29_2024-GO95MLD-1^06142016.0079904 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005858 | 600326224-72790-DETAIL-03_13_2025-GO95HV-1^06239003.0255902 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005859 | 600404885-48411-DTLSB-05_08_2024-GO95MLD-1^06244001.0032800 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005860 | 600522756-98511-DTLSB-02_01_2023-GO95MLD-1^06248001.0369906 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005861 | 600730915-37979-DTLTRT-10_31_2023-GO95BLTC-1^668010/00 13/016 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005862 | 600794156-21661-DETAIL-02_24_2025-SVCDEFLC-1^06239004.0366804 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005863 | 600801406-53379-DETAIL-03_28_2024-GO95HV-1^06147005.0132700 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005864 | 600801406-53379-DETAIL-03_28_2024-GO95MLD-1^06147005.0132700 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005865 | 60082426-59879-DETAIL-03_25_2024-GO95MLD-1^06147005.0134901 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005866 | 600990896-61549-DETAIL-08_21_2024-SVCENTCO-1^06245006.0092200 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005867 | 601182208-30011-DETAIL-03_20_2024-GO95MLD-1^06245002.0017900 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005868 | 601360701-32511-DETAIL-01_21_2025-SVCROOF-1^06239004.0255248 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005869 | 601415848-66011-DETAIL-04_10_2024-GO95HV-1^06245002.0112500 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005870 | 60260239-37773-DTLSB-10_02_2024-GO95MLD-1^06245007.0217606 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005871 | 60260239-37773-DTLSB-10_02_2024-GRDRODHI-1^06245007.0217606 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005872 | 602696309-80549-DETAIL-05_17_2023-GO95HV-1^06245006.0350300 | OTHER | Non-HFTD | Distribution | 2023-05-17 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005873 | 602709846-76560-DTLTRT-10_09_2023-GUYNOINS-2^668010/00 3A/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005874 | 686342457-3309-DTLSB-07_22_2024-GO95MLD-1^06245006.0063200 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005875 | 686933654-94654-DETAIL-03_28_2023-GO95MLD-1^06142016.0083807 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005876 | 687395580-25549-DETAIL-08_12_2024-GO95HV-1^06245006.0105402 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005877 | 687665710-24649-DETAIL-03_16_2023-GO95HV-1^07113001.0042504 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005878 | 687984290-19670-DETAIL-03_21_2023-GO95HV-1^06240004.0167411 | OTHER | HFTD Tier 2 | Distribution | 2023-03-21 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005879 | 688303993-63139-DETAIL-07_31_2024-GO95MLD-1^06244005.0343900 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005880 | 688593179-32389-AUDIT-05_07_2024-GO95MLD-1^06245002.0101101 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005881 | 688965238-80399-DETAIL-02_27_2023-SVCENTCO-2^07216001.0298841 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005882 | 689106101-5669-DTLSB-09_05_2023-GO95MLD-1^06243008.0096600 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005883 | 689244663-41850-DETAIL-01_30_2025-GO95TCH-1^06239004.0133004 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005884 | 689324414-34889-DETAIL-06_10_2024-GO95HV-1^06245007.0347001 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005885 | 690064371-9889-DETAIL-07_03_2024-GO95HV-1^06244005.0234601 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005886 | 690163522-76599-DETAIL-06_08_2023-ABNDEQPM-1^06244009.0325700 | OTHER | HFTD Tier 2 | Distribution | 2023-06-08 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005887 | 690819066-79282-DETAIL-07_11_2023-GO95MLD-1^06244008.0321901 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005888 | 691230532-43449-DETAIL-02_27_2024-GO95HV-1^07113002.0182300 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005889 | 69129214-64190-DTLSB-05_08_2024-GO95MLD-1^06245001.0333701 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005890 | 69129214-64190-DTLSB-05_08_2024-GRDRODHI-1^06245001.0333701 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005891 | 691427064-60439-DTLSB-02_26_2024-SVCENTCO-1^07216001.0277901 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005892 | 691558036-69036-DTLSB-08_31_2023-GO95HV-1^06243008.0025700 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005893 | 691911034-37159-DETAIL-10_16_2024-GUYHINS-1^07216001.0205803 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005894 | 603232893-62739-DTLSB-02_16_2024-GO95MLD-1^07216001.0271001 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005895 | 603332934-40139-DETAIL-07_17_2024-GO95MLD-1^06244005.0277002 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005896 | 603456293-14252-DETAIL-06_13_2023-GO95MLD-1^06244010.0221400 | OTHER | HFTD Tier 2 | Distribution | 2023-06-13 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005897 | 603857339-89569-DETAIL-03_26_2024-GO95HV-1^06246005.0042700 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005898 | 603962126-50549-DETAIL-02_27_2024-GO95MLD-1^07113002.0076001 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005899 | 603963619-42759-DTLSB-02_05_2024-GO95HV-1^07216001.0190900 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005900 | 603963619-42759-DTLSB-02_05_2024-GO95MLD-1^07216001.0190900 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005901 | 604570584-52584-DETAIL-01_17_2023-GO95MLD-1^06148004.0174303 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005902 | 604911673-55449-DTLSB-02_28_2024-GO95HV-1^07216001.0272700 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005903 | 604911673-55449-DTLSB-02_28_2024-SVCENTCO-1^07216001.0272700 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005904 | 604911673-55449-DTLSB-02_28_2024-SVCENTCO-2^07216001.0272700 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005905 | 605065249-3733-DETAIL-03_13_2023-GO95MLD-1^07117002.0270501 | OTHER | HFTD Tier 2 | Distribution | 2023-03-13 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005906 | 605301941-44121-DETAIL-04_18_2024-GO95MLD-1^06145001.0130300 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005907 | 605551191-40870-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 2/002 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005908 | 605796097-64249-DETAIL-10_08_2024-GO95CL10-1^07216001.0203106 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005909 | 605796097-64249-DETAIL-10_08_2024-GO95MLD-1^07216001.0203106 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005910 | 605801380-1749-DETAIL-03_16_2023-CLRTOUCH-1^07113001.0042601 | CONDUCTOR | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005911 | 605896388-93399-DTLSB-07_02_2024-GO95HV-1^06245006.0188500 | OTHER | Non-HFTD | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005912 | 606261473-96279-DTLSB-02_02_2023-GO95MLD-1^06248001.0268001 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005913 | 606449262-10880-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0166307 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005914 | 606535698-92502-DETAIL-03_06_2025-GUYHINS-2^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005915 | 606535698-92502-DETAIL-03_06_2025-GUYHINS-3^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005916 | 606535698-92502-DETAIL-03_06_2025-GUYHINS-4^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005917 | 606535698-92502-DETAIL-03_06_2025-GUYNOINS-1^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005918 | 606535698-92502-DETAIL-03_06_2025-GUYNOINS-3^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005919 | 692123456-9819-DETAIL-07_24_2024-GO95HV-1^06244004.0190401 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005920 | 692123456-9819-DETAIL-07_24_2024-GRDRODHI-2^06244004.0190401 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005921 | 692130406-40272-DETAIL-07_05_2023-GO95MLD-1^06244008.0311900 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005922 | 692205961-62691-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0124002 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005923 | 692491658-22289-DETAIL-04_08_2024-GO95MLD-1^06247005.0285002 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005924 | 692714295-22191-DETAIL-10_22_2024-GO95HV-1^07216001.0208500 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005925 | 692729088-54290-DETAIL-01_30_2025-GO95HV-1^06239004.0245509 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005926 | 692854689-23659-DETAIL-10_14_2024-CLMBTRE-1^07216001.0204213 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005927 | 692962815-6645-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 6/001 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005928 | 693368121-99970-DETAIL-02_11_2025-SVCDEFLC-1^06240004.0167306 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005929 | 69336988-61739-DETAIL-07_30_2024-GO95MLD-1^06244005.0354100 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005930 | 693562970-21279-DETAIL-03_21_2024-GO95MLD-1^06147004.0119700 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005931 | 693562970-21279-DETAIL-03_21_2024-GO95TCH-1^06147004.0119700 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005932 | 693602216-94980-DETAIL-02_27_2025-GO95HV-1^06240004.0050140 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005933 | 693602216-94980-DETAIL-02_27_2025-GO95TCH-1^06240004.0050140 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005934 | 693710483-60351-DETAIL-03_04_2025-GO95MLD-1^06241005.0131803 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005935 | 693856629-34773-DTLSB-10_02_2024-GO95MLD-1^06245007.0217602 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005936 | 69417784-78810-DETAIL-03_13_2025-GO95HV-1^06238004.0152204 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005937 | 69426244-99890-DTLSB-05_09_2024-GO95HV-1^06244001.0119900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005938 | 69433721-11990-DETAIL-04_15_2024-GO95MLD-1^06145002.0062500 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005939 | 694437860-97860-DETAIL-03_05_2024-GO95HV-1^06147005.0174902 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005940 | 694599771-14430-DETAIL-02_05_2025-GO95MLD-1^06240004.0170601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005941 | 694771131-18709-DETAIL-10_27_2022-GO95HV-1^06246008.0069801 | OTHER | HFTD Tier 2 | Distribution | 2022-10-27 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005942 | 695005242-19209-DETAIL-03_05_2024-GO95MLD-1^06147005.0179100 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005943 | 695136384-13499-DETAIL-06_10_2024-GO95MLD-1^06245007.0349601 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005944 | 606535698-92502-DETAIL-03_06_2025-GUYNOINS-4^06241005.0120102 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005945 | 606569238-41270-DETAIL-12_05_2024-GUYBRK-1^668014/00 2/058 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-12-05 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005946 | 606686036-77149-DETAIL-02_28_2024-GO95HV-1^07113002.0180500 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005947 | 606686036-77149-DETAIL-02_28_2024-GO95MLD-1^07113002.0180500 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005948 | 60707560-72559-DETAIL-03_21_2024-GO95MLD-1^06246005.0060301 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005949 | 607558391-30491-DTLSB-08_14_2023-GO95HV-1^06243009.0236902 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005950 | 607609766-27789-DETAIL-03_20_2024-GRDRODHI-2^06244005.0144406 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005951 | 607730256-11269-DTLTRT-10_09_2023-GO95HV-1^668010/00 9/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005952 | 608035931-88621-DETAIL-04_09_2024-GO95TCH-1^06147005.0255000 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005953 | 608035931-88621-DETAIL-04_09_2024-POLISSUE-1^06147005.0255000 | POLE | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005954 | 608451860-97789-DETAIL-08_13_2024-SVCROAD-1^06245005.0353900 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005955 | 608502393-26349-DETAIL-02_23_2023-GO95MLD-1^07216001.0294607 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005956 | 608509722-67601-DTLSB-09_05_2023-GO95HV-1^06243008.0161901 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005957 | 608576506-89169-DTLTRT-10_09_2023-GO95MLD-1^668010/00 14/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005958 | 60863934-54934-DETAIL-05_01_2024-GO95MLD-1^06143015.0336700 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005959 | 60863934-54934-DETAIL-05_01_2024-GUYHINS-1^06143015.0336700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005960 | 608718254-63980-DTLTRT-09_27_2023-GO95HV-1^668010/00 3/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005961 | 608743014-43349-DTLSB-02_14_2024-GO95MLD-1^07216001.0198400 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005962 | 608905824-26009-DETAIL-04_01_2024-GO95HV-1^06147005.0090900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005963 | 609089151-13599-DETAIL-03_20_2024-GO95HV-1^06244004.0066401 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005964 | 609089151-13599-DETAIL-03_20_2024-SVCWIND-1^06244004.0066401 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005965 | 609110749-37770-DETAIL-09_29_2020-GO95HV-1^668018/00 13/006 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005966 | 609171629-24999-DETAIL-06_12_2023-GO95HV-1^06244009.0361102 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005967 | 609229889-29013-DETAIL-07_23_2024-GO95HV-1^06245006.0144540 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005968 | 609431760-44089-DETAIL-08_13_2024-GO95MLD-1^06245005.0367400 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005969 | 695136384-13499-DETAIL-06_10_2024-GRDRODHI-1^06245007.0349601 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005970 | 695136384-13499-DETAIL-06_10_2024-GRDRODHI-2^06245007.0349601 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005971 | 6952356-58819-DETAIL-08_18_2022-GO95CL10-1^668005/00 16/097 | OTHER | Non-HFTD | Transmission | 2022-08-18 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005972 | 695347701-22449-DTLSB-04_24_2024-GO95MLD-1^06245007.0225602 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005973 | 695372075-13749-DETAIL-02_29_2024-GO95MLD-1^07113001.0159902 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005974 | 695401181-13959-DETAIL-05_16_2022-GO95HV-1^07116001.0090800 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005975 | 695401181-13959-DETAIL-05_16_2022-GRDRODHI-1^07116001.0090800 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005976 | 695497093-26020-DETAIL-03_10_2025-SVCDEFLC-1^06240004.0288402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005977 | 695497093-26020-DETAIL-03_10_2025-SVCENTCO-1^06240004.0288402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005978 | 695534121-18943-DETAIL-05_12_2022-GO95CL10-1^07116001.0093700 | OTHER | HFTD Tier 2 | Distribution | 2022-05-12 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005979 | 695534121-18943-DETAIL-05_12_2022-SVCNEUT-1^07116001.0093700 | OTHER | HFTD Tier 2 | Distribution | 2022-05-12 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005980 | 695613514-47129-AUDIT-08_29_2023-GO95HV-1^06244008.0277700 | OTHER | HFTD Tier 2 | Distribution | 2023-08-29 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005981 | 695674832-67761-DTLSB-09_05_2023-GO95HV-1^06243008.0162801 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005982 | 696100661-69818-DTLSB-02_06_2024-GO95HV-1^07216001.0309700 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005983 | 696100661-69818-DTLSB-02_06_2024-GO95TCH-1^07216001.0309700 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005984 | 6963318-16512-DETAIL-06_20_2023-GO95MLD-1^06244009.0362500 | OTHER | Non-HFTD | Distribution | 2023-06-20 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005985 | 696359466-698-DETAIL-03_06_2024-GO95MLD-1^06147004.0017500 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005986 | 696604086-61239-AUDIT-04_30_2024-GO95MLD-1^06244005.0143300 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005987 | 697172866-26949-DETAIL-08_20_2024-GO95MLD-1^06245004.0200902 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005988 | 697351551-80432-AUDIT-08_01_2023-GO95HV-1^06244009.0282100 | OTHER | HFTD Tier 2 | Distribution | 2023-08-01 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005989 | 697390941-55999-DTLSB-05_01_2024-GO95MLD-1^06245007.0227500 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005990 | 697391435-14701-DETAIL-10_25_2024-GO95MLD-1^07216001.0209901 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005991 | 697391435-14701-DETAIL-10_25_2024-SVCNEUT-1^07216001.0209901 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005992 | 697672195-25211-DTLSB-05_08_2024-GO95HV-1^06244001.0033600 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130005993 | 697714928-16340-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 8/053 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005994 | 697714928-97360-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 8/053 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005995 | 69780505-37129-DETAIL-04_26_2022-RISEGRD-1^06143012.0258201 | OTHER | Non-HFTD | Distribution | 2022-04-26 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005996 | 698164489-68249-DETAIL-03_06_2023-GO95MLD-1^07216001.0297603 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005997 | 698164489-68249-DETAIL-03_06_2023-GO95TCH-1^07216001.0297603 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005998 | 698164489-68249-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297603 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130005999 | 698668040-60039-AUDIT-07_01_2024-RISEGRD-1^06244005.0243701 | OTHER | Non-HFTD | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006000 | 698668040-60039-DETAIL-06_12_2024-GO95MLD-1^06244005.0243701 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006001 | 698817181-55620-DETAIL-03_07_2023-SVCENTCO-1^07117002.0210501 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006002 | 698998563-86511-DETAIL-05_23_2024-GO95HV-1^06243001.0122000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006003 | 699381239-44111-DETAIL-05_06_2024-SVCENTCO-1^06142012.0124007 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006004 | 699465723-24839-DETAIL-03_02_2023-SVCROAD-1^07216001.0292503 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006005 | 699515935-10411-DETAIL-05_15_2024-GO95HV-1^06142012.0123703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006006 | 699515935-10411-DETAIL-05_15_2024-GO95MLD-1^06142012.0123703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006007 | 699647625-67529-DETAIL-08_07_2024-GO95HV-1^06245008.0228400 | OTHER | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006008 | 699650500-40669-DETAIL-11_09_2022-GO95MLD-1^06246008.0027600 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006009 | 699669484-82360-DETAIL-01_16_2025-GO95HV-1^06239004.0257504 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006010 | 699678539-60809-DTLSB-07_22_2024-GO95HV-1^06245007.0109700 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006011 | 699915666-6879-DETAIL-07_25_2024-SVCDEFLC-1^06244005.0350801 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006012 | 699927935-55872-DETAIL-03_14_2024-GO95MLD-1^06245006.0126901 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006013 | 700016313-72660-DETAIL-09_06_2024-SVCROAD-1^06240004.0076340 | OTHER | HFTD Tier 3 | Distribution | 2024-09-06 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006014 | 700080326-64311-DETAIL-04_23_2024-SVCNEUT-1^06145001.0038200 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006015 | 700157791-68311-DETAIL-04_16_2024-GO95MLD-1^06145002.0061002 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006016 | 70023123-37390-DETAIL-03_07_2023-GO95MLD-1^07216001.0293609 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006017 | 70023853-78360-DETAIL-01_13_2025-GO95HV-1^06240004.0079342 | OTHER | HFTD Tier 3 | Distribution | 2025-01-13 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006018 | 700315994-44959-DETAIL-10_10_2024-GO95TCH-1^07216001.0205004 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006019 | 700655606-65606-DETAIL-01_29_2025-GO95HV-1^06239004.0228200 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006020 | 70067713-6980-DETAIL-02_11_2025-CLRTOUCH-1^06240004.0356302 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-11 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006021 | 70067713-6980-DETAIL-02_11_2025-SVCDEFLC-1^06240004.0356302 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006022 | 700857682-79880-DETAIL-02_12_2025-GO95TCH-1^06240004.0165400 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006023 | 700857682-79880-DETAIL-02_12_2025-GUYHINS-1^06240004.0165400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006024 | 700892211-88512-DETAIL-07_24_2024-GO95HV-1^06244005.0131440 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006025 | 700939649-3489-DETAIL-01_26_2023-GO95HV-1^06148003.0174200 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006026 | 701429676-91279-DETAIL-03_05_2024-GO95HV-1^06245007.0278101 | OTHER | HFTD Tier 2 | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006027 | 701449608-44979-DETAIL-07_29_2024-GO95HV-1^06245006.0115501 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006028 | 701607514-4539-DETAIL-03_13_2023-GO95HV-1^07216001.0290707 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006029 | 701607514-4539-DETAIL-03_13_2023-GUYHINS-1^07216001.0290707 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006030 | 701743954-53779-DETAIL-02_16_2023-GO95MLD-1^06247002.0217900 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006031 | 701983181-40149-DETAIL-02_26_2024-GO95HV-1^07113001.0138403 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006032 | 702031901-7252-DETAIL-06_08_2023-GO95HV-1^06244009.0294502 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006033 | 702056718-10969-DTLTRT-06_09_2021-COPLLEAN-1^668041/00 10/017 | POLE | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006034 | 70207160-34232-DTLSB-07_19_2023-GO95MLD-1^06243010.0021203 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006035 | 702188384-98980-DTLTRT-09_27_2023-GO95MLD-1^668010/00 14/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006036 | 702255521-23801-DETAIL-01_14_2025-BIRDDMG-1^06239004.0255244 | POLE | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006037 | 702255521-23801-DETAIL-01_14_2025-SVCWIND-1^06239004.0255244 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006038 | 702396634-13149-DTLSB-02_07_2024-SVCENTCO-1^07216001.0199103 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006039 | 702544602-56580-DETAIL-02_12_2025-GO95HV-1^06240004.0282801 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006040 | 702567153-26750-DETAIL-01_23_2025-GO95TCH-1^06239004.0257605 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006041 | 702887300-49789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223701 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006042 | 702929319-32639-DETAIL-02_19_2024-GO95BLTC-1^07113002.0185201 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006043 | 703212619-99039-DETAIL-03_08_2023-GO95MLD-1^07117002.0207602 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006044 | 703212619-99039-DETAIL-03_08_2023-SVCNEUT-1^07117002.0207602 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006045 | 703449206-18999-DTLSB-04_15_2024-SVCWIND-1^06245007.0226100 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006046 | 70402048-93779-DTLSB-05_13_2024-SVCENTCO-1^06244001.0153100 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006047 | 704254371-70279-DETAIL-03_04_2024-GO95MLD-1^06147004.0025200 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006048 | 704323231-16549-DETAIL-02_28_2024-GO95HV-1^07113001.0149901 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006049 | 704376146-34200-DTLTRT-11_01_2023-GO95HV-1^668010/00 15/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006050 | 704501219-6549-DETAIL-03_14_2023-GO95MLD-1^07117002.0286900 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006051 | 704567781-40881-DETAIL-01_10_2023-GO95MLD-1^06148004.0187206 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006052 | 704567781-40881-DETAIL-01_10_2023-GO95MLD-2^06148004.0187206 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006053 | 704642053-29331-DETAIL-10_24_2024-GO95TCH-1^07216001.0208740 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006054 | 704715988-80631-AUDIT-04_15_2024-GO95BLTC-1^06245002.0127801 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006055 | 70516396-26539-DTLSB-02_21_2023-CLRTOUCH-1^07216001.0287704 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006056 | 705187265-23549-DETAIL-02_21_2024-GO95MLD-1^07113001.0158001 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006057 | 705924098-4859-DETAIL-03_18_2024-COPLLEAN-1^06246005.0077200 | POLE | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006058 | 706160382-66831-DETAIL-05_05_2022-GRDRODHI-1^07116001.0100001 | OTHER | HFTD Tier 2 | Distribution | 2022-05-05 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006059 | 706197814-3269-ADMIN-10_11_2023-GO95MLD-1^668010/00 8/040 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006060 | 706304711-16931-DETAIL-03_12_2024-GO95MLD-1^06147004.0059700 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006061 | 706788304-38729-DETAIL-05_01_2024-GO95MLD-1^06142012.0122506 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006062 | 706850521-66620-AUDIT-03_18_2025-GUYHINS-1^06240004.0274602 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006063 | 707036044-75289-DETAIL-08_15_2024-GO95HV-1^06246005.0144101 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006064 | 707036044-75289-DETAIL-08_15_2024-GO95MLD-1^06246005.0144101 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006065 | 707103809-43809-DETAIL-03_09_2023-GO95MLD-1^07117002.0208103 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006066 | 707112858-45641-DETAIL-03_13_2023-GO95TCH-1^07216001.0293440 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006067 | 707160999-94041-DETAIL-03_05_2025-ANCHIDLE-1^06241005.0134500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006068 | 707237296-90280-DETAIL-03_03_2025-GO95HV-1^06240004.0051002 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006069 | 707409902-679-DETAIL-04_08_2024-GUYHINS-1^06147005.0222400 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006070 | 707755803-50499-DTLSB-02_02_2023-GO95MLD-1^06248001.0254001 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006071 | 70872675-25629-DETAIL-08_21_2024-GO95HV-1^06245008.0249103 | OTHER | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006072 | 709189519-24059-DETAIL-10_15_2024-CLMBTRE-1^07216001.0202305 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006073 | 709459579-78251-DETAIL-04_24_2024-GO95MLD-1^06145001.0060700 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006074 | 709653060-48830-DETAIL-01_29_2025-SVCDEFLC-1^06240004.0176801 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006075 | 709766301-98620-DETAIL-02_17_2025-GO95HV-1^06240004.0278500 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006076 | 709793930-92551-DETAIL-01_26_2023-ABNDEQPM-1^06147003.0141100 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006077 | 710270600-66251-DETAIL-03_13_2025-GO95HV-1^06239002.0070400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006078 | 710380346-10670-DETAIL-01_24_2025-GO95HV-1^06239004.0257843 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006079 | 710566093-20970-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 7/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006080 | 710566093-44702-DTLTRT-04_16_2024-GO95HV-1^668067/00 7/011 | OTHER | Non-HFTD | Transmission | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006081 | 710713774-3151-DETAIL-10_22_2024-GO95HV-1^07216001.0208702 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006082 | 711073298-85999-DTLTRT-04_16_2024-SVCENTCO-1^06245007.0227312 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006083 | 712039879-95949-DTLSB-02_19_2024-GO95MLD-1^07216001.0260202 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006084 | 712095378-91851-DTLSB-01_30_2023-GO95HV-1^06248001.0369710 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006085 | 712109807-37579-DETAIL-04_09_2024-GO95MLD-1^06147005.0217003 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006086 | 71249331-12559-DETAIL-05_12_2022-GO95HV-1^07116001.0092800 | OTHER | Non-HFTD | Distribution | 2022-05-12 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006087 | 712638323-61753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 2/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006088 | 712638323-74560-DTLTRT-04_08_2024-GO95HV-1^668062/00 2/004 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006089 | 712679131-43249-DETAIL-02_21_2024-GO95MLD-1^07113001.0145101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006090 | 712688659-88990-DETAIL-01_28_2025-GO95HV-1^06239004.0245400 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006091 | 713016385-46761-DETAIL-03_09_2023-SVCENTCO-1^07216001.0295508 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006092 | 713279603-32899-DETAIL-03_11_2024-GO95HV-1^06147005.0174702 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006093 | 713306043-44949-DETAIL-03_16_2023-GO95MLD-1^07114001.0282403 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006094 | 713665373-63959-DETAIL-06_06_2024-GO95MLD-1^06246006.0350000 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006095 | 71381682-1200-DETAIL-05_13_2024-GO95HV-1^06142012.0124402 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006096 | 609431760-44089-DETAIL-08_13_2024-GUYHINS-1^06245005.0367400 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006097 | 609732603-56921-DETAIL-05_15_2024-GO95MLD-1^06142012.0124600 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006098 | 609895596-50280-DETAIL-01_31_2025-GO95MLD-1^06239004.0245905 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006099 | 610015081-29129-DETAIL-07_05_2023-GUYNOINS-1^06244008.0320700 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-07-05 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006100 | 610015081-29129-DETAIL-07_05_2023-GUYNOINS-2^06244008.0320700 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-07-05 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006101 | 610488493-32129-DETAIL-05_14_2024-GO95HV-1^06142012.0122805 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006102 | 610488493-32129-DETAIL-05_14_2024-GO95MLD-1^06142012.0122805 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006103 | 610527431-1852-DETAIL-06_15_2023-GO95MLD-1^06244009.0290701 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006104 | 610655163-54599-DETAIL-07_17_2024-GO95MLD-1^06244005.0262901 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006105 | 610673768-90390-DETAIL-01_14_2025-SVCENTCO-1^06239004.0255103 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006106 | 610923439-64439-DETAIL-02_26_2025-BIRDDMG-1^06240004.0217740 | POLE | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006107 | 611126065-52341-DETAIL-05_03_2022-SVCWIND-1^06241005.0013642 | OTHER | HFTD Tier 2 | Distribution | 2022-05-03 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006108 | 611266373-56269-DETAIL-07_15_2024-GO95MLD-1^06244005.0256000 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006109 | 611472932-35221-DETAIL-02_21_2023-CONDFRAY-1^06247002.0095400 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006110 | 611708793-94739-DETAIL-08_05_2024-GO95HV-1^06244005.0029001 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006111 | 611870848-33848-DETAIL-05_12_2022-GO95HV-1^07116001.0094800 | OTHER | HFTD Tier 2 | Distribution | 2022-05-12 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006112 | 611870848-33848-DETAIL-05_12_2022-GO95MLD-1^07116001.0094800 | OTHER | HFTD Tier 2 | Distribution | 2022-05-12 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006113 | 612152125-46009-DTLSB-08_28_2024-GO95HV-1^06245007.0141700 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006114 | 612493551-65879-DETAIL-01_10_2023-GO95HV-1^06148004.0170301 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006115 | 612493551-65879-DETAIL-01_10_2023-GO95MLD-1^06148004.0170301 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006116 | 612740571-84579-DTLTRT-10_05_2023-GO95HV-1^668010/00 15/027 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006117 | 612838678-33778-DETAIL-02_27_2025-SVCROAD-1^06240004.0063104 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006118 | 612842733-92733-DETAIL-03_21_2023-GO95TCH-1^07113001.0058601 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006119 | 612893513-15921-DTLSB-02_14_2023-GO95MLD-1^06248001.0339401 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006120 | 613017754-4113-DTLSB-05_01_2024-GO95MLD-1^06245007.0227440 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006121 | 613192606-90379-DETAIL-10_24_2022-GO95HV-1^06247008.0314903 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006122 | 613690852-34929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176201 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006123 | 61370858-28549-DETAIL-02_28_2024-GO95HV-1^07113001.0133900 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006124 | 613750749-63421-DETAIL-04_24_2024-GRDRODHI-1^06145001.0055100 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006125 | 61385156-89680-DETAIL-01_30_2025-GO95TCH-1^06239004.0245701 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006126 | 614241522-26621-DETAIL-02_08_2023-GO95MLD-1^06146002.0334300 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006127 | 614297415-76309-DETAIL-07_11_2024-GUYHINS-1^06244005.0221900 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006128 | 614323785-25459-DETAIL-04_24_2023-GO95MLD-1^07117003.0027300 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006129 | 614757009-56669-DTLSB-07_02_2024-GO95HV-1^06245006.0184700 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006130 | 615458223-39223-DETAIL-03_11_2024-GO95HV-1^06147004.0013901 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006131 | 616008823-83779-DETAIL-06_10_2024-GO95MLD-1^06245007.0346007 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006132 | 616055734-59715-DETAIL-01_24_2025-BIRDDMG-1^06240004.0187700 | POLE | HFTD Tier 2 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006133 | 61617286-40949-DTLSB-04_15_2024-SVCWIND-1^06245007.0226101 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006134 | 616325033-83831-DTLSB-05_23_2024-GO95MLD-1^06243001.0239500 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006135 | 616416651-25149-DETAIL-02_26_2024-GO95HV-1^07113001.0138306 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006136 | 616548673-10931-DETAIL-10_21_2024-SVCNEUT-1^07216001.0209605 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006137 | 616782635-19109-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207002 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006138 | 617480657-23959-DETAIL-04_08_2024-GO95HV-1^06247005.0322200 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006139 | 617481448-94243-DETAIL-03_09_2023-GO95MLD-1^07117002.0208102 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006140 | 617732813-60680-DETAIL-04_11_2023-GO95TCH-1^06240004.0168410 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006141 | 617837143-52231-DETAIL-10_21_2024-GUYNOINS-2^07216001.0209301 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006142 | 617962303-19079-ADMIN-08_05_2024-GO95STUB-1^07116007.0019302 | OTHER | HFTD Tier 2 | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006143 | 618460303-56079-DTLSB-05_28_2024-GO95HV-1^06243001.0125100 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006144 | 618460303-56079-DTLSB-05_28_2024-GO95MLD-1^06243001.0125100 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006145 | 618616774-67810-DETAIL-03_13_2025-GO95HV-1^06238004.0150102 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006146 | 619007961-34550-DETAIL-02_27_2025-GO95HV-1^06240004.0139400 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006147 | 619746411-57849-DETAIL-08_13_2024-GO95HV-1^06245005.0361303 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006148 | 619782632-42540-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 11A/031 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006149 | 619895141-93029-DETAIL-05_08_2024-GO95MLD-1^06142012.0120206 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006150 | 61996389-34370-DETAIL-03_28_2023-GO95HV-1^06240004.0167541 | OTHER | HFTD Tier 2 | Distribution | 2023-03-28 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006151 | 620126644-86644-DETAIL-01_09_2023-GO95MLD-1^06148003.0144201 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006152 | 620317722-13449-DETAIL-10_21_2024-GO95MLD-1^07216001.0209204 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006153 | 620333573-49179-DTLSB-05_28_2024-GO95HV-1^06243001.0125103 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006154 | 620579949-16769-ADMIN-06_15_2021-POLEDERP-1^668005/03 10/004 | POLE | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006155 | 621105063-76879-DTLSB-02_02_2023-GO95HV-1^06248001.0267000 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006156 | 621144343-72831-DETAIL-03_02_2023-GO95HV-1^07117002.0204203 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006157 | 621394333-26350-DETAIL-01_23_2025-GO95TCH-1^06239004.0256805 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006158 | 621494312-55709-DTLSB-08_26_2024-GO95HV-1^06245007.0111101 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006159 | 6215081-84770-DETAIL-02_19_2025-BIRDDMG-1^06241005.0274801 | POLE | HFTD Tier 3 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006160 | 621562851-61131-DETAIL-12_22_2022-GO95MLD-1^668001/00 13/023 | OTHER | Non-HFTD | Transmission | 2022-12-22 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006161 | 621878160-42459-DETAIL-07_23_2024-BIRDDMG-1^06245007.0315901 | POLE | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006162 | 621930580-32580-DETAIL-04_30_2024-GO95HV-1^06142015.0021900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006163 | 621985754-2980-DRONE_HY-10_18_2023-GO95HV-1^668033/00 4/022 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006164 | 622006350-61369-DETAIL-03_21_2024-GO95HV-1^06246005.0067100 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006165 | 622415749-12259-DETAIL-05_31_2024-GO95MLD-1^06246005.0338400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006166 | 622575944-14649-DETAIL-10_22_2024-CONDFRAY-1^07216001.0208100 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006167 | 622575944-14649-DETAIL-10_22_2024-GO95MLD-1^07216001.0208100 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006168 | 622575944-14649-DETAIL-10_22_2024-GUYHINS-1^07216001.0208100 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006169 | 622575944-14649-DETAIL-10_22_2024-POLANCRD-1^07216001.0208100 | POLE | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006170 | 622618915-80329-DTLSB-08_02_2023-GO95HV-1^06243010.0132303 | OTHER | HFTD Tier 2 | Distribution | 2023-08-02 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006171 | 71381682-1200-DETAIL-05_13_2024-SVCRUBLG-1^06142012.0124402 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006172 | 714103801-12861-DETAIL-04_16_2024-GO95MLD-1^06145002.0185900 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006173 | 714140195-26349-DETAIL-02_27_2024-GO95MLD-1^07113002.0184503 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006174 | 714183353-28861-DTLSB-05_28_2024-SVCENTCO-1^06243001.0125300 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006175 | 714219339-90439-DETAIL-07_18_2024-GO95HV-1^06244004.0042800 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006176 | 714441900-9749-DETAIL-08_13_2024-GO95MLD-1^06245005.0368300 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006177 | 71447243-36913-DTLSB-05_01_2024-GO95HV-1^06245007.0228645 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006178 | 71447243-36913-DTLSB-05_01_2024-GO95MLD-1^06245007.0228645 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006179 | 714543501-66230-DETAIL-03_04_2025-GUYHINS-1^06240004.0151303 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006180 | 714798569-5599-ADMIN-06_19_2024-GO95MLD-1^06242009.0284104 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006181 | 71508108-52849-DTLSB-02_28_2024-GO95HV-1^07216001.0260901 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006182 | 715538570-10670-DTLSB-02_22_2023-GO95MLD-1^07216001.0289604 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006183 | 715611473-44850-DETAIL-01_23_2025-BIRDDMG-1^06239004.0256900 | POLE | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006184 | 715982739-49449-DETAIL-05_09_2023-GO95HV-1^06245006.0363101 | OTHER | Non-HFTD | Distribution | 2023-05-09 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006185 | 716107138-35139-DETAIL-03_25_2024-GO95MLD-1^06244005.0146300 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006186 | 716134764-79839-DTLSB-02_06_2024-GUYHINS-1^07216001.0309911 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006187 | 716191674-56333-DETAIL-06_06_2024-GO95MLD-1^06246006.0354900 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006188 | 716235608-31409-DETAIL-04_10_2024-GRDRODHI-1^06147005.0214900 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006189 | 71630099-6300-DETAIL-03_18_2024-GO95HV-1^06245002.0057800 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006190 | 71652830-93170-DETAIL-02_12_2025-GO95MLD-1^06240004.0166507 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006191 | 716846955-20650-DTLTRT-10_10_2023-GO95MLD-1^668010/00 10/037 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006192 | 717223581-59379-ADMIN-10_27_2022-POLEREPL-1^06144007.0313500 | POLE | Non-HFTD | Distribution | 2022-10-27 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006193 | 718146523-3169-DTLSB-10_07_2024-GO95HV-1^06245007.0219100 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006194 | 718231143-62471-DETAIL-02_09_2023-GO95MLD-1^06146004.0086000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006195 | 719277843-42079-DTLSB-01_30_2023-GO95HV-1^06248001.0259002 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006196 | 719277843-42079-DTLSB-01_30_2023-GO95MLD-1^06248001.0259002 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006197 | 719327068-16159-DTLTRT-06_09_2021-INSULBRK-1^668041/00 1/017 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006198 | 719327068-16159-DTLTRT-06_09_2021-UBPBCTGD-1^668041/00 1/017 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006199 | 719570266-17419-ADMIN-07_29_2024-POLEDERP-1^668005/00 6/069 | POLE | Non-HFTD | Transmission | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006200 | 720766155-36789-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207400 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006201 | 720766155-36789-DETAIL-01_18_2023-COPLLEAN-1^06148004.0207400 | POLE | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006202 | 720777351-65180-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 1/003 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006203 | 720777351-65180-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | Non-HFTD | Transmission | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006204 | 720848916-75379-DETAIL-03_28_2024-GO95HV-1^06147005.0112201 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006205 | 721535088-47781-DTLSB-05_15_2024-GO95MLD-1^06244002.0234500 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006206 | 72174104-67659-DETAIL-05_16_2022-GUYHINS-1^07117001.0313700 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006207 | 721781521-18379-DETAIL-01_24_2023-GO95HV-1^06148004.0182203 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006208 | 721809451-81263-DTLSB-04_29_2024-RISEGRD-1^06245007.0221444 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006209 | 721946761-53980-DETAIL-03_19_2025-XARMBRAC-1^06239001.0069602 | CROSSARM | HFTD Tier 2 | Distribution | 2025-03-19 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006210 | 722035805-16442-DETAIL-03_05_2025-GO95BLTC-1^06241005.0121202 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006211 | 722239533-34879-DTLSB-01_30_2023-GO95HV-1^06248001.0258000 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006212 | 722307888-94881-ADMIN-01_25_2022-POLETOP-1^06246001.0335700 | POLE | Non-HFTD | Distribution | 2022-01-25 | 2025-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006213 | 722386598-89863-DTLSB-10_03_2024-GO95MLD-1^06245007.0218707 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006214 | 722560993-74280-DETAIL-02_11_2025-GO95MLD-1^06240004.0355200 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006215 | 722583422-31780-DETAIL-03_10_2025-GO95HV-1^06240004.0288900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006216 | 722680931-53680-DETAIL-03_20_2025-GO95HV-1^06239002.0039500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006217 | 723130269-72509-DETAIL-11_03_2022-GO95HV-1^06246009.0149900 | OTHER | HFTD Tier 2 | Distribution | 2022-11-03 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006218 | 723130269-72509-DETAIL-11_03_2022-GUYHINS-1^06246009.0149900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-11-03 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006219 | 723130269-72509-DETAIL-11_03_2022-GUYHINS-2^06246009.0149900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-11-03 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006220 | 72327082-56349-DETAIL-10_10_2024-GO95MLD-1^07216001.0207102 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006221 | 723271001-13859-DETAIL-06_05_2024-GO95STUB-1^06246006.0266302 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006222 | 723507108-62640-DETAIL-03_12_2025-BIRDDMG-1^06239003.0138200 | POLE | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006223 | 723544263-83009-ADMIN-03_01_2024-GO95STUB-1^06246009.0127801 | OTHER | HFTD Tier 2 | Distribution | 2024-03-01 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006224 | 723775003-24309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 18/030 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006225 | 723797451-53609-DETAIL-01_17_2023-COPLLEAN-1^06148004.0223003 | POLE | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006226 | 723866043-43499-DETAIL-06_19_2024-SVCENTCO-1^06245007.0341900 | OTHER | HFTD Tier 2 | Distribution | 2024-06-19 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006227 | 723978073-56009-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128701 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006228 | 723996670-65080-AUDIT-03_18_2025-CLRTOUCH-1^06240004.0343700 | CONDUCTOR | HFTD Tier 3 | Distribution | 2025-03-18 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006229 | 723996670-65080-AUDIT-03_18_2025-SVCDEFLC-1^06240004.0343700 | OTHER | HFTD Tier 3 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006230 | 724356631-8479-DTLSB-08_27_2024-GO95MLD-1^06245007.0117501 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006231 | 724404193-59239-DETAIL-06_20_2024-GO95HV-1^06244005.0239402 | OTHER | Non-HFTD | Distribution | 2024-06-20 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006232 | 725614684-68519-DTLTRT-08_17_2022-UBPBXARM-1^668005/00 1/095 | CROSSARM | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006233 | 725804319-87259-DETAIL-05_31_2024-GUYNOINS-1^06246005.0334402 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006234 | 72590211-84589-DTLSB-09_04_2024-GO95HV-1^06245007.0115301 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006235 | 726059743-56309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 4/031 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006236 | 72620773-69489-DTLSB-10_07_2024-GO95BLTC-1^06245007.0211200 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006237 | 726224121-27229-DETAIL-06_29_2020-SVCROAD-1^06142012.0118504 | OTHER | Non-HFTD | Distribution | 2020-06-29 | 2023-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006238 | 726495948-53023-DETAIL-03_14_2023-GO95MLD-1^07117003.0113704 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006239 | 726604724-82249-DETAIL-03_16_2023-SVCENTCO-1^07114001.0299802 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006240 | 7266096-86949-DETAIL-10_08_2024-CLRTOUCH-1^07216001.0203001 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006241 | 726796286-48139-DETAIL-03_20_2024-GUYNOINS-1^06244005.0145401 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006242 | 726854203-1491-DTLSB-05_28_2024-GO95MLD-1^06243001.0125004 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006243 | 726858099-94259-DETAIL-06_04_2024-GO95MLD-1^06246005.0337101 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006244 | 727217873-80939-DTLSB-02_27_2024-GO95MLD-1^07216001.0278702 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006245 | 727464179-88291-DETAIL-05_02_2024-GO95MLD-1^06142012.0125202 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006246 | 727862161-66029-DETAIL-05_06_2024-SVCENTCO-1^06142012.0123103 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006247 | 727934726-82260-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006248 | 727934726-82260-DTLTRT-10_09_2023-GUYHINS-1^668010/00 2/039 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006249 | 728225418-26383-DETAIL-03_07_2024-SVCWIND-1^06245007.0275842 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006250 | 728821153-55153-DETAIL-03_25_2025-GO95HV-1^06239003.0019320 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006251 | 729134485-76410-DETAIL-03_12_2025-GO95HV-1^06238004.0222501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006252 | 729268611-6901-DTLSB-02_15_2023-GO95HV-1^06248001.0309600 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006253 | 729293703-82921-ADMIN-02_18_2025-ANCHIDLE-1^06239004.0362506 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006254 | 729309296-899-DETAIL-06_04_2024-GO95MLD-1^06246006.0362002 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006255 | 729336706-92488-DTLSB-08_14_2023-GO95HV-1^06243009.0236700 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006256 | 729469404-20149-DETAIL-03_20_2023-SVCWIND-1^07114001.0284308 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006257 | 729674629-53499-DETAIL-03_18_2024-GO95MLD-1^06245006.0010703 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006258 | 729732029-26549-DETAIL-03_14_2023-GUYLOINS-1^07117002.0286801 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006259 | 729854668-77849-DETAIL-10_14_2024-GO95MLD-1^07216001.0204303 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006260 | 730206639-97770-DETAIL-01_29_2025-SVCDEFLC-2^06240004.0161403 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006261 | 730640764-20549-DTLSB-02_26_2024-GO95CL10-1^07216001.0277601 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006262 | 730751464-27479-DETAIL-06_05_2024-ABNDEQPM-1^06246006.0256800 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006263 | 73088473-87549-DTLSB-02_26_2024-GO95HV-1^07216001.0277907 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006264 | 731019299-20499-DETAIL-06_12_2023-GO95MLD-1^06244009.0362200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006265 | 73109728-24849-DTLSB-02_20_2024-GO95TCH-1^07216001.0260502 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006266 | 731465714-55239-DETAIL-07_17_2024-GO95MLD-1^06244005.0282103 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006267 | 731785947-60409-DETAIL-04_10_2024-GO95MLD-1^06147005.0212902 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006268 | 731785947-60409-DETAIL-04_10_2024-GRDRODHI-1^06147005.0212902 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006269 | 731787626-38090-DTLTRT-04_18_2024-GO95HV-1^668067/00 7/020 | OTHER | Non-HFTD | Transmission | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006270 | 731787626-52802-DTLTRT-04_18_2024-GO95HV-1^668067/00 7/020 | OTHER | Non-HFTD | Transmission | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006271 | 731790413-27130-DETAIL-04_24_2023-GO95BLTC-1^06240004.0065400 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006272 | 732020895-74269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 8/041 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006273 | 732125390-30311-DETAIL-02_23_2023-GRDRODHI-1^07216001.0295706 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006274 | 732259061-1950-DETAIL-03_11_2025-GO95MLD-1^06238004.0271643 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006275 | 73256324-83211-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 3/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006276 | 732782415-74415-DETAIL-02_28_2023-GO95MLD-1^07216001.0299808 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006277 | 733059612-1629-DETAIL-05_15_2024-GO95HV-1^06142012.0125903 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006278 | 733059612-1629-DETAIL-05_15_2024-GO95MLD-1^06142012.0125903 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006279 | 733126964-80722-DETAIL-07_07_2023-GO95TCH-1^06244008.0330200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006280 | 733162913-98529-DTLSB-08_01_2023-GO95STUB-1^06243009.0078001 | OTHER | HFTD Tier 2 | Distribution | 2023-08-01 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006281 | 733473706-91199-DETAIL-08_20_2024-GO95MLD-1^06246004.0325800 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006282 | 733529874-50160-DETAIL-01_24_2023-GO95MLD-1^06240004.0079300 | OTHER | HFTD Tier 2 | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006283 | 734220465-47979-DTLSB-02_01_2023-GO95MLD-1^06248001.0368001 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006284 | 734433216-8179-DETAIL-03_18_2024-GO95MLD-1^06245006.0127702 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006285 | 734638989-67170-DETAIL-04_11_2023-GO95TCH-1^06240004.0167548 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006286 | 734758314-81660-DTLTRT-04_08_2024-BIRDDMG-1^668062/00 3/006 | POLE | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006287 | 734775969-13833-DETAIL-03_14_2023-GO95MLD-1^07117002.0270601 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006288 | 734857843-51468-DETAIL-05_09_2022-GO95MLD-1^07116001.0096300 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006289 | 734857843-51468-DETAIL-05_09_2022-SVCROAD-1^07116001.0096300 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006290 | 734980971-90620-DETAIL-03_07_2023-GO95MLD-1^07117002.0210600 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006291 | 734987074-74299-DTLSB-04_23_2024-GO95MLD-1^06245007.0223601 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006292 | 735526024-10549-DTLSB-04_24_2024-GO95MLD-1^06245007.0224708 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006293 | 735559322-51780-DETAIL-03_10_2025-PWRTRN-1^06240004.0289700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006294 | 735599745-56600-DETAIL-03_27_2025-XARMSPCR-1^06239003.0016714 | CROSSARM | HFTD Tier 2 | Distribution | 2025-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006295 | 735701683-47749-DETAIL-03_16_2023-GO95TCH-1^07114001.0281703 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006296 | 735701683-47749-DETAIL-03_16_2023-GUYHINS-1^07114001.0281703 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006297 | 735949748-80848-DTLSB-05_23_2024-GO95MLD-1^06243001.0149603 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006298 | 736035053-5339-DETAIL-06_24_2024-GO95MLD-1^06244005.0233300 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006299 | 736035053-5339-DETAIL-06_24_2024-SVCDEFLC-2^06244005.0233300 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006300 | 736467651-88401-DETAIL-02_04_2025-GO95HV-1^06239004.0135146 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006301 | 736569028-78721-DETAIL-02_20_2023-GO95HV-1^06247002.0297701 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006302 | 736675268-62368-DTLSB-02_16_2024-SVCROAD-1^07216001.0260105 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006303 | 736763050-40840-DETAIL-02_10_2025-GO95MLD-1^06239003.0071907 | OTHER | HFTD Tier 3 | Distribution | 2025-02-10 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006304 | 736793804-4340-DTLTRT-10_04_2023-GO95MLD-1^668010/00 11/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006305 | 736793804-4340-DTLTRT-10_04_2023-GUYHINS-2^668010/00 11/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006306 | 736809193-17309-DETAIL-01_19_2023-CONDFRAY-1^06148004.0210602 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-19 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006307 | 736974548-6548-DETAIL-05_08_2024-GO95MLD-1^06142012.0120402 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006308 | 736990354-93549-DTLSB-02_07_2024-GO95TCH-1^07216001.0199204 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006309 | 736990354-93549-DTLSB-02_07_2024-SVCDEFLC-1^07216001.0199204 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006310 | 737170953-78621-DETAIL-04_06_2023-GO95MLD-1^06143014.0230500 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006311 | 738523171-71289-DTLSB-08_26_2024-GO95MLD-1^06245007.0113403 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006312 | 738547461-58939-DETAIL-03_02_2023-GO95MLD-1^07117002.0204300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006313 | 738911534-40521-DTLSB-05_07_2024-GO95MLD-1^06245001.0190502 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006314 | 738974070-81019-AUDIT-04_10_2024-GO95MLD-1^06147005.0143900 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006315 | 739267393-6649-DETAIL-03_14_2023-GO95MLD-1^07114001.0276302 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006316 | 739865880-76880-DETAIL-02_27_2025-GO95MLD-1^06240004.0065402 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006317 | 740198504-70604-DETAIL-03_18_2024-GO95MLD-1^06246005.0076100 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006318 | 740587141-86330-DETAIL-02_27_2025-GUYHINS-1^06240004.0154402 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006319 | 740587141-86330-DETAIL-02_27_2025-GUYNOINS-2^06240004.0154402 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006320 | 740836885-85489-DETAIL-06_10_2024-RISEGRD-1^06245007.0346740 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006321 | 74172557-65039-DETAIL-03_15_2023-GO95CL10-1^07114001.0347201 | OTHER | HFTD Tier 2 | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006322 | 741838540-97758-DETAIL-06_06_2024-GRDRODHI-1^06246006.0353702 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006323 | 741994823-93799-DETAIL-03_06_2024-GO95MLD-1^06147005.0179902 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006324 | 742616408-52459-DETAIL-06_03_2024-GO95MLD-1^06246005.0319902 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006325 | 742665746-75746-DETAIL-01_29_2025-GO95MLD-1^06239004.0265900 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006326 | 743290724-41740-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 1/039 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006327 | 743523991-53791-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/004 | OTHER | Non-HFTD | Transmission | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006328 | 743825824-80109-DETAIL-07_15_2024-GO95MLD-1^06244005.0256800 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006329 | 743977178-78741-DETAIL-04_22_2024-GO95HV-1^06145001.0119801 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006330 | 74403029-59529-DTLTRT-10_25_2022-GO95HV-1^668075/00 2/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006331 | 744033483-12221-DETAIL-02_18_2025-SVCDEFLC-1^06239004.0364802 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006332 | 744571179-92332-DTLTRT-06_06_2024-GO95HV-1^668084/00 1A/001 | OTHER | Non-HFTD | Transmission | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006333 | 744578465-98559-DETAIL-10_24_2024-GO95HV-1^07216001.0202600 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006334 | 744624199-67699-DTLTRT-10_25_2022-GO95HV-1^668075/00 10/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006335 | 744631479-81889-DTLSB-05_07_2024-GO95MLD-1^06245002.0134900 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006336 | 744855624-17624-DETAIL-04_25_2024-GO95HV-1^06142016.0160900 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006337 | 745409608-78141-DETAIL-04_17_2024-GO95MLD-1^06145001.0010301 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006338 | 745608796-5889-DETAIL-10_24_2022-GO95HV-1^06247008.0315300 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006339 | 745869738-85170-DETAIL-02_12_2025-GO95BLTC-1^06240004.0167504 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006340 | 74599240-78509-DTLSB-09_03_2024-GO95HV-1^06245007.0019001 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006341 | 74599240-78509-DTLSB-09_03_2024-GO95MLD-1^06245007.0019001 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006342 | 74605926-56472-DETAIL-05_30_2023-GO95MLD-1^06244010.0344900 | OTHER | HFTD Tier 2 | Distribution | 2023-05-30 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006343 | 746216573-25841-DETAIL-04_04_2023-GO95HV-1^06143014.0224701 | OTHER | HFTD Tier 2 | Distribution | 2023-04-04 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006344 | 746304146-13249-DETAIL-03_11_2024-GO95MLD-1^06245006.0123400 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006345 | 746638341-97040-DTLTRT-10_03_2023-GO95HV-1^668010/00 8/030 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006346 | 746638341-97040-DTLTRT-10_03_2023-GUYHINS-1^668010/00 8/030 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006347 | 746805014-58722-DETAIL-07_12_2023-GO95MLD-1^06244008.0276701 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006348 | 746812831-16201-DETAIL-01_21_2025-BIRDDMG-1^06239004.0255440 | POLE | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006349 | 746812831-16201-DETAIL-01_21_2025-GO95HV-1^06239004.0255440 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006350 | 747011516-64599-DETAIL-04_01_2024-BIRDDMG-1^06247005.0347101 | POLE | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006351 | 747264989-29099-DETAIL-03_18_2024-GO95MLD-1^06245005.0061604 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006352 | 747506958-85423-DRONE_HY-09_14_2023-GO95HV-1^668002/00 13/012 | OTHER | Non-HFTD | Transmission | 2023-09-14 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006353 | 747519018-31170-DETAIL-02_26_2025-SVCDEFLC-1^06240004.0062104 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006354 | 747810789-35451-DETAIL-03_09_2023-GUYHINS-1^07216001.0294502 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006355 | 747810789-35451-DETAIL-03_09_2023-SVCENTBK-1^07216001.0294502 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006356 | 747878130-53201-DETAIL-01_31_2025-GO95HV-1^06239004.0136105 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006357 | 747921863-92863-DETAIL-04_29_2024-GO95HV-1^06142016.0066800 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006358 | 747921863-92863-DETAIL-04_29_2024-SVCDEFLC-1^06142016.0066800 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006359 | 748220191-15279-DETAIL-11_08_2022-GO95MLD-1^06246008.0066700 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006360 | 748320707-82609-DTLSB-09_05_2024-GRDRODHI-1^06245006.0073800 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006361 | 748320707-82609-DTLSB-09_05_2024-GRDRODHI-2^06245006.0073800 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006362 | 748320707-82609-DTLSB-09_05_2024-GRDRODHI-3^06245006.0073800 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006363 | 748468641-18129-DETAIL-05_13_2024-GO95HV-1^06142012.0123307 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006364 | 748792720-99120-DTLTRT-10_26_2022-GO95MLD-1^668075/00 11/027 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006365 | 749146491-61459-DETAIL-02_21_2024-GUYNOINS-1^07113001.0147103 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006366 | 749227563-48049-DETAIL-02_21_2024-SVCENTCO-1^07113001.0139200 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006367 | 749332196-44079-DETAIL-04_03_2024-GO95MLD-1^06147005.0142003 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006368 | 749429711-19739-DRONE_HY-10_25_2023-GO95HV-1^668087/00 2/008 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006369 | 749760413-8759-DETAIL-02_28_2024-GO95MLD-1^07216001.0342901 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006370 | 749805351-33351-ADMIN-06_19_2024-POLEDERP-1^07216001.0020903 | POLE | Non-HFTD | Distribution | 2024-06-19 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006371 | 749830688-10730-DETAIL-02_27_2025-GO95MLD-1^06240003.0305201 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006372 | 749830708-44351-DTLSB-02_06_2023-GO95TCH-1^06247001.0019201 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006373 | 750262276-22851-AUDIT-02_07_2023-GO95MLD-1^06248001.0367807 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006374 | 750262276-22851-DTLSB-01_31_2023-GUYHINS-1^06248001.0367807 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006375 | 750262309-54309-DETAIL-02_11_2025-GO95HV-1^06240004.0354300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006376 | 750351146-40672-DETAIL-07_07_2023-GO95HV-1^06244008.0329800 | OTHER | Non-HFTD | Distribution | 2023-07-07 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006377 | 750456103-98261-DETAIL-02_06_2023-GUYSLACK-1^06148002.0286100 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006378 | 750483076-98770-DETAIL-01_24_2025-GO95HV-1^06239004.0258842 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006379 | 750522051-86689-DTLSB-08_26_2024-GO95HV-1^06245007.0114304 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006380 | 750715069-20789-DETAIL-03_18_2024-GO95HV-1^06245002.0059900 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006381 | 75136561-13700-DETAIL-04_15_2024-GO95MLD-1^06145001.0139501 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006382 | 751419118-80359-DETAIL-10_14_2024-GO95CL10-1^07216001.0202307 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006383 | 751707298-61398-DETAIL-01_24_2025-GO95HV-1^06239004.0247043 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006384 | 751736224-361-DETAIL-10_21_2024-GO95CL10-1^07216001.0209604 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006385 | 751736224-361-DETAIL-10_21_2024-GO95MLD-1^07216001.0209604 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006386 | 751786131-40331-DETAIL-05_12_2022-GO95TCH-1^07116001.0093800 | OTHER | HFTD Tier 2 | Distribution | 2022-05-12 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006387 | 751910274-88339-DTLSB-02_14_2024-GO95MLD-1^07216001.0198304 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006388 | 751955006-63370-DETAIL-01_16_2025-BIRDDMG-1^06239004.0256208 | POLE | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006389 | 751995102-87340-DTLTRT-10_03_2023-GO95HV-1^668010/00 18/030 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006390 | 752281574-89649-DTLSB-02_26_2024-GO95HV-1^07216001.0277909 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006391 | 75231032-23679-DETAIL-03_12_2024-GO95MLD-1^06147004.0070701 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006392 | 752516993-31093-ADMIN-04_27_2023-POLEREPL-1^06248007.0243301 | POLE | Non-HFTD | Distribution | 2023-04-27 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006393 | 752733326-2769-DTLTRT-10_12_2023-GO95HV-1^668010/00 12/041 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006394 | 752791560-42309-DETAIL-03_21_2024-GO95MLD-1^06147004.0117800 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006395 | 752791560-42309-DETAIL-03_21_2024-SVCENTCO-1^06147004.0117800 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006396 | 75302220-87218-ADMIN-03_13_2025-POLEREPL-2^06245007.0217703 | POLE | Non-HFTD | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006397 | 753507011-82899-DETAIL-07_02_2024-GO95MLD-1^06244005.0231704 | OTHER | Non-HFTD | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006398 | 753797600-50700-DETAIL-01_30_2025-GO95BLTC-1^06240004.0162504 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006399 | 754041397-85479-DETAIL-04_03_2024-GO95MLD-1^06147005.0152002 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006400 | 754341896-5479-DETAIL-08_21_2024-GO95MLD-1^06245006.0095100 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006401 | 754495348-66461-DTLSB-01_26_2023-GO95MLD-1^06247001.0016900 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006402 | 754759130-84170-DETAIL-02_13_2025-GO95CL10-1^06240004.0169106 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006403 | 754813113-41061-ADMIN-04_21_2023-GO95TCH-1^06143014.0235802 | OTHER | HFTD Tier 2 | Distribution | 2023-04-21 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006404 | 755069736-71340-DETAIL-02_24_2025-RISEGRD-1^06240004.0153600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006405 | 755246903-80863-DETAIL-03_11_2025-GO95HV-1^06238004.0274805 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006406 | 755786429-61259-AUDIT-11_13_2024-GO95HV-1^07216001.0200112 | OTHER | Non-HFTD | Distribution | 2024-11-13 | 2029-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006407 | 756190423-9329-DETAIL-06_26_2023-GO95HV-1^06244009.0300300 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006408 | 756391103-17560-DETAIL-09_09_2024-SVCROAD-1^06240004.0097240 | OTHER | HFTD Tier 2 | Distribution | 2024-09-09 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006409 | 756475459-36179-DETAIL-05_25_2023-ABNDEQPM-1^06246009.0136600 | OTHER | HFTD Tier 2 | Distribution | 2023-05-25 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006410 | 756606727-19490-DETAIL-02_03_2025-GO95HV-1^06239004.0244845 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006411 | 75696794-9939-DTLSB-02_08_2024-GO95CL10-1^07216001.0197002 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006412 | 757004212-67370-DETAIL-01_22_2025-GO95TCH-1^06240004.0087003 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006413 | 757110105-97571-DTLSB-05_13_2024-GO95MLD-1^06245001.0294300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006414 | 757660098-86549-DTLSB-02_07_2024-GO95MLD-1^07216001.0199212 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006415 | 758119568-62071-DETAIL-04_22_2024-GO95HV-1^06145001.0029000 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006416 | 758325581-83669-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0349100 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006417 | 75837083-17079-DTLSB-02_02_2023-ABNDEQPM-1^06248001.0269001 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006418 | 75837083-17079-DTLSB-02_02_2023-GO95MLD-1^06248001.0269001 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006419 | 75851489-57439-DETAIL-03_09_2023-GO95TCH-1^07216001.0293605 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006420 | 758640858-63519-ADMIN-12_31_2018-POLEDERP-1^668005/00 5/071 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006421 | 758847233-18243-DETAIL-01_28_2025-SVCDEFLC-1^06240004.0079600 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006422 | 758896411-48109-AUDIT-02_16_2023-GO95CLSV-1^06148004.0219500 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006423 | 758913500-78549-DETAIL-08_21_2024-GO95MLD-1^06245006.0108901 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006424 | 759143570-68668-DETAIL-06_07_2023-GO95HV-1^06244010.0276601 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006425 | 75916933-75560-DTLTRT-04_08_2024-POLETOP-1^668062/00 5/004 | POLE | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006426 | 75922980-65599-DETAIL-01_30_2023-GO95TCH-1^06148003.0223501 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006427 | 759233633-86849-DETAIL-05_10_2023-GUYHINS-1^06245006.0272802 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-05-10 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006428 | 759463964-27389-DETAIL-07_24_2024-GO95MLD-1^06244005.0227700 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006429 | 759760635-23951-DETAIL-02_24_2025-GO95HV-1^06239004.0366803 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006430 | 759834034-92743-DETAIL-09_27_2021-SVCWIND-1^06148004.0356307 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006431 | 76024216-83259-DETAIL-04_02_2024-GO95MLD-1^06247005.0339000 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006432 | 760753708-87081-ADMIN-01_11_2022-POLEDERP-1^06147001.0106501 | POLE | Non-HFTD | Distribution | 2022-01-11 | 2025-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006433 | 760900782-1782-DETAIL-02_19_2025-GO95HV-1^06240004.0219913 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006434 | 760946451-85880-DETAIL-02_14_2025-BIRDDMG-1^06240004.0168408 | POLE | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006435 | 76147765-82739-DETAIL-10_16_2024-GO95MLD-1^07216001.0200501 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006436 | 761704322-63250-DETAIL-01_23_2025-GO95HV-1^06239004.0257705 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006437 | 762114475-33109-DTLSB-08_28_2024-GO95MLD-1^06245007.0140002 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006438 | 762185258-12358-DETAIL-06_21_2023-GO95MLD-1^06244009.0337502 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006439 | 762263476-21399-DETAIL-04_01_2024-GO95MLD-1^06147005.0124900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006440 | 762441152-68391-DETAIL-02_13_2023-GO95HV-1^06247002.0118701 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006441 | 762555473-29339-DETAIL-06_25_2024-GO95MLD-1^06244005.0235701 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006442 | 762624894-93090-DTLTRT-10_31_2023-GO95HV-1^668010/00 5/016 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006443 | 762850524-5679-DTLTRT-11_14_2022-GO95HV-1^668001/00 5/042 | OTHER | HFTD Tier 2 | Transmission | 2022-11-14 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006444 | 762895438-5999-DETAIL-08_01_2024-SVCROAD-1^06245006.0155201 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006445 | 763058768-68479-DETAIL-04_09_2024-GO95MLD-1^06147005.0254600 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006446 | 763058768-68479-DETAIL-04_09_2024-GUYHINS-1^06147005.0254600 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006447 | 763169762-64929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176100 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006448 | 763272733-7503-DETAIL-02_28_2024-GO95HV-1^07215001.0025500 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006449 | 763712606-95379-DETAIL-01_19_2023-GO95BLTC-1^06148004.0209400 | OTHER | Non-HFTD | Distribution | 2023-01-19 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006450 | 763756231-67991-DTLTRT-10_24_2022-GO95MLD-1^668001/00 9/024 | OTHER | Non-HFTD | Transmission | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006451 | 7638284-69910-DETAIL-03_13_2025-GO95MLD-1^06238004.0151003 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006452 | 76390823-72823-DETAIL-03_23_2023-GO95MLD-1^06142016.0081703 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006453 | 76433054-26129-DETAIL-07_12_2023-GO95MLD-1^06244008.0274501 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006454 | 764347778-47900-ENHANCED-01_08_2025-IRSPOTOH-1^668067/00 4/022 | OTHER | HFTD Tier 2 | Transmission | 2025-01-08 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006455 | 764347778-99571-ENHANCED-01_08_2025-IRSPOTOH-1^668067/00 4/022 | OTHER | HFTD Tier 2 | Transmission | 2025-01-08 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006456 | 764347778-99571-ENHANCED-01_27_2025-IRSPOTOH-1^668067/00 4/022 | OTHER | HFTD Tier 2 | Transmission | 2025-01-27 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006457 | 764548983-24099-DETAIL-07_11_2024-GO95MLD-1^06244005.0260700 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006458 | 764756573-71999-DETAIL-03_12_2024-GO95HV-1^06245007.0289901 | OTHER | HFTD Tier 2 | Distribution | 2024-03-12 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006459 | 76481144-81939-DTLSB-02_07_2024-GO95MLD-1^07216001.0199211 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006460 | 76510718-65199-DTLSB-08_22_2024-GO95MLD-1^06245006.0328600 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006461 | 76510718-65199-DTLSB-08_22_2024-GRDRODHI-1^06245006.0328600 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006462 | 76571108-13469-DTLTRT-07_06_2022-GO95HV-1^668005/00 1/037 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006463 | 766276768-13849-DTLSB-04_22_2024-GO95MLD-1^06245007.0225401 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006464 | 766276768-13849-DTLSB-04_22_2024-SVCENTCO-1^06245007.0225401 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006465 | 76631846-6009-DTLSB-09_04_2024-GO95MLD-1^06245007.0140601 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006466 | 766585380-55701-DETAIL-02_06_2025-GO95MLD-1^06239004.0135205 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006467 | 766585380-55701-DETAIL-02_06_2025-GO95TCH-1^06239004.0135205 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006468 | 766612065-71072-DETAIL-08_07_2024-XARMBRAC-1^06245008.0229102 | CROSSARM | HFTD Tier 2 | Distribution | 2024-08-07 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006469 | 766992346-58069-DTLTRT-10_25_2023-GO95MLD-1^668010/00 16/042 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006470 | 767027443-82418-DETAIL-03_08_2023-GUYHINS-1^07117002.0213000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006471 | 767072231-25702-DETAIL-07_11_2023-GO95MLD-1^06244008.0309001 | OTHER | HFTD Tier 2 | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006472 | 767460289-91540-DETAIL-02_10_2025-BIRDDMG-1^06239003.0071902 | POLE | HFTD Tier 3 | Distribution | 2025-02-10 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006473 | 768127676-17979-DETAIL-03_25_2024-GO95HV-1^06244005.0145301 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006474 | 76823134-98134-DETAIL-03_29_2023-GO95HV-1^06142016.0085400 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006475 | 76823134-98134-DETAIL-03_29_2023-GO95MLD-1^06142016.0085400 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006476 | 768439801-77644-DETAIL-03_30_2023-COPLLEAN-1^06142016.0055102 | POLE | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006477 | 768439801-77644-DETAIL-03_30_2023-GO95MLD-1^06142016.0055102 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006478 | 768508151-1561-DETAIL-02_06_2023-GO95BLTC-1^06147002.0162101 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006479 | 768628189-80129-DTLSB-08_17_2023-GO95MLD-1^06243009.0131600 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006480 | 768670669-1669-DETAIL-03_25_2025-GO95HV-1^06239003.0019414 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006481 | 769345340-28749-DTLSB-02_20_2024-GO95MLD-1^07216001.0263301 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006482 | 769545503-43980-DETAIL-02_11_2025-GO95HV-1^06240004.0355404 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006483 | 769645466-68612-DETAIL-10_25_2024-ENCHRW-1^07216001.0208610 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006484 | 769948952-52052-DETAIL-03_02_2023-GO95HV-1^07117002.0201200 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006485 | 770043789-33512-DETAIL-04_11_2024-GO95HV-1^06245002.0105300 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006486 | 770208478-11802-DETAIL-03_05_2025-GO95MLD-1^06241005.0121002 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006487 | 770388560-13559-DETAIL-03_21_2024-GO95MLD-1^06246005.0060400 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006488 | 770700608-46859-DETAIL-03_21_2024-GO95MLD-1^06246005.0073002 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006489 | 77077040-41249-DTLSB-02_16_2024-GO95MLD-1^07216001.0263101 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006490 | 771025414-68431-DETAIL-01_14_2025-SVCROAD-1^06239004.0255101 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006491 | 771029871-64912-ADMIN-03_27_2024-ABNDEQPM-1^06147004.0056902 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006492 | 771172124-93212-DTLSB-05_09_2024-GO95MLD-1^06244001.0025000 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006493 | 771236248-31849-DTLSB-02_19_2024-GO95MLD-1^07216001.0264901 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006494 | 771255638-21740-DETAIL-03_20_2025-GO95HV-1^06239003.0018001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006495 | 771378443-743-DETAIL-10_12_2022-GO95HV-1^668005/08 8X6/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006496 | 771727485-25812-DETAIL-10_16_2024-GO95MLD-1^07216001.0207801 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006497 | 771795238-94349-DETAIL-02_23_2023-ABNDEQPM-1^07216001.0299705 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006498 | 77191680-26880-DTLSB-02_09_2023-GO95MLD-1^06248001.0279220 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006499 | 771930464-46880-DTLTRT-09_27_2023-GO95MLD-1^668010/00 12/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006500 | 772132347-3347-DTLSB-02_28_2024-GO95MLD-1^07216001.0273807 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006501 | 772480098-50812-DETAIL-03_19_2024-GO95MLD-1^06245002.0026001 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006502 | 772718281-11801-DETAIL-01_14_2025-SVCENTBK-1^06239004.0257342 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006503 | 77275301-61580-DETAIL-03_20_2025-GO95HV-1^06239002.0034400 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006504 | 772921416-60512-DTLSB-01_30_2023-GO95BLTC-1^06248001.0369900 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006505 | 772926554-71512-DTLSB-02_06_2023-GO95HV-1^06248001.0257001 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006506 | 773001908-10159-DETAIL-03_22_2024-GO95MLD-1^06247005.0289400 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006507 | 773127393-43259-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0345003 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006508 | 773147299-31612-DETAIL-04_11_2024-GO95MLD-1^06245002.0100100 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006509 | 773157776-70970-DETAIL-01_23_2025-GO95TCH-1^06239004.0256740 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006510 | 773508891-92339-DETAIL-06_25_2024-GO95HV-1^06244005.0236001 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006511 | 773831134-50629-DTLSB-08_07_2023-GO95MLD-1^06243009.0196201 | OTHER | HFTD Tier 2 | Distribution | 2023-08-07 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006512 | 774008336-86569-DETAIL-01_23_2025-GO95HV-1^06240004.0082203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006513 | 774008336-86569-DETAIL-01_23_2025-SVCDEFLC-1^06240004.0082203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006514 | 774297318-24589-DETAIL-11_01_2022-GO95MLD-1^06246009.0076200 | OTHER | HFTD Tier 2 | Distribution | 2022-11-01 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006515 | 774502352-96780-DETAIL-03_27_2023-GO95TCH-1^06240004.0167245 | OTHER | HFTD Tier 2 | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006516 | 774640561-89009-DETAIL-06_12_2024-GO95MLD-1^06244005.0241100 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006517 | 774640561-89009-DETAIL-06_12_2024-GRDRODHI-2^06244005.0241100 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006518 | 774782299-16781-DETAIL-02_24_2025-GO95HV-1^06241005.0153202 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006519 | 774986832-54559-DETAIL-02_27_2024-GO95HV-1^07113002.0182402 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006520 | 775182231-12829-DETAIL-05_13_2024-GRDRODHI-1^06142012.0122206 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006521 | 775796861-59243-DETAIL-10_25_2024-SVCENTBK-1^07216001.0201640 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006522 | 77598864-30964-DETAIL-03_19_2025-BIRDDMG-1^06238004.0028407 | POLE | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006523 | 776348368-66630-DETAIL-02_27_2025-GO95MLD-1^06240003.0304302 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006524 | 776387069-57699-DETAIL-03_06_2024-GO95HV-1^06147004.0139301 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006525 | 776399661-9730-DETAIL-01_28_2025-GUYHINS-1^06240004.0171900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006526 | 776582433-81529-DTLSB-09_06_2023-GO95HV-1^06243007.0202501 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006527 | 776719151-60140-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 8A/030 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006528 | 776746876-47249-DETAIL-03_18_2024-GO95HV-1^06245006.0128804 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006529 | 777276726-72479-DETAIL-01_24_2023-COPLLEAN-1^06148004.0182101 | POLE | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006530 | 777276726-72479-DETAIL-01_24_2023-GO95MLD-1^06148004.0182101 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006531 | 777626230-67230-DETAIL-07_24_2024-GO95MLD-1^06244005.0133304 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006532 | 778006186-81182-DETAIL-07_11_2023-GO95MLD-1^06244008.0320800 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006533 | 778258499-20129-DETAIL-05_08_2024-GO95HV-1^06142012.0120010 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006534 | 778465114-77659-DTLSB-02_14_2024-GO95MLD-1^07216001.0180200 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006535 | 778831351-36511-AUDIT-04_02_2025-GUYHINS-1^06239004.0362602 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006536 | 779128438-14349-DETAIL-03_14_2024-ENCHRW-1^06245006.0120900 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006537 | 779473434-62032-DETAIL-02_09_2023-GO95MLD-1^06146004.0164900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006538 | 779516951-21473-DETAIL-03_02_2023-GO95MLD-1^07117002.0201308 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006539 | 779516951-21473-DETAIL-03_02_2023-GRDRODHI-1^07117002.0201308 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006540 | 780458670-23270-DETAIL-03_11_2025-GO95HV-1^06238003.0019900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006541 | 780551433-71299-DETAIL-06_24_2024-GO95HV-1^06244005.0234201 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006542 | 780571105-77440-DETAIL-02_24_2025-SVCDEFLC-1^06240004.0151700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006543 | 780948823-69132-DETAIL-02_16_2023-SVCROAD-1^06247002.0165400 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006544 | 78139103-76479-DETAIL-07_11_2024-GO95MLD-1^06244005.0260403 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006545 | 781547649-26979-AUDIT-03_14_2024-GO95MLD-1^06147004.0010302 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006546 | 78159875-63410-DETAIL-03_12_2025-BIRDDMG-1^06238004.0224601 | POLE | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006547 | 781613001-7809-DETAIL-10_26_2022-GO95HV-1^06246008.0062103 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006548 | 781769086-31186-DTLSB-09_05_2024-GO95MLD-1^06245006.0076500 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006549 | 781798804-60349-DETAIL-03_20_2023-GO95MLD-1^07114001.0285402 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006550 | 781998247-95210-DTLSB-02_28_2024-GO95MLD-1^07216001.0273802 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006551 | 782130241-84189-DTLSB-08_27_2024-GO95MLD-1^06245007.0115900 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006552 | 782675398-24750-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0164740 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006553 | 782711340-64742-DETAIL-03_13_2024-GO95HV-1^06147004.0180101 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006554 | 783147474-54842-DTLSB-02_13_2023-GO95HV-1^06248001.0278740 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006555 | 783723731-45709-DETAIL-11_02_2022-GO95MLD-1^06246008.0053500 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006556 | 783746501-94663-ADMIN-01_10_2025-POLEREPL-1^06245007.0272102 | POLE | Non-HFTD | Distribution | 2025-01-10 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006557 | 784329078-42942-DTLSB-02_09_2023-GO95HV-1^06248001.0229401 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006558 | 784718279-57659-DETAIL-10_10_2024-GO95MLD-1^07216001.0201205 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006559 | 784749416-31990-DTLTRT-11_01_2023-GO95MLD-1^668010/00 6/010 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006560 | 78497811-38601-DETAIL-01_15_2025-SVCENTBK-1^06239004.0255243 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006561 | 785155288-72039-DETAIL-07_30_2024-GRDRODHI-1^06244005.0355401 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006562 | 785155288-72039-DETAIL-07_30_2024-GRDRODHI-2^06244005.0355401 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006563 | 785350468-22468-DETAIL-02_28_2023-GO95MLD-1^07216001.0298606 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006564 | 785734006-34931-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006565 | 785734006-63931-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006566 | 785734006-91860-DRONE_HY-10_12_2023-GO95HV-1^668033/00 4/045 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006567 | 785916435-54009-DTLSB-08_28_2024-GO95HV-1^06245007.0140402 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006568 | 786046193-5952-DTLSB-05_23_2024-GO95HV-1^06243001.0125001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006569 | 786046193-5952-DTLSB-05_23_2024-GO95MLD-1^06243001.0125001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006570 | 78607916-549-DETAIL-02_28_2024-GO95MLD-1^07113002.0073400 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006571 | 786104779-62013-DETAIL-07_23_2024-GO95HV-1^06245006.0144442 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006572 | 78622185-23140-DETAIL-02_24_2025-GO95TCH-1^06240004.0152802 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006573 | 786262118-88539-DETAIL-10_17_2024-SVCROOF-1^07216001.0204408 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006574 | 786415514-76429-DTLSB-07_26_2023-GO95HV-1^06243009.0058900 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006575 | 786508956-92479-DETAIL-03_28_2024-GO95MLD-1^06147005.0122500 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006576 | 786508956-92479-DETAIL-03_28_2024-GUYHINS-1^06147005.0122500 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006577 | 786537698-45559-DTLSB-02_13_2024-GO95HV-1^07216001.0185105 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006578 | 78656528-58749-AUDIT-11_13_2024-GO95HV-1^07216001.0201100 | OTHER | Non-HFTD | Distribution | 2024-11-13 | 2029-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006579 | 786592339-66109-DETAIL-03_04_2024-SVCDEFLC-1^06147004.0017300 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006580 | 786597081-79830-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 6/027 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006581 | 78691549-65110-DETAIL-04_22_2024-POLISSUE-1^06146001.0365501 | POLE | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006582 | 787563348-42899-DTLSB-08_15_2023-GO95MLD-1^06243009.0267001 | OTHER | Non-HFTD | Distribution | 2023-08-15 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006583 | 788056361-75279-DTLSB-04_23_2024-GO95MLD-1^06245007.0226700 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006584 | 788056361-75279-DTLSB-04_23_2024-GRDRODHI-1^06245007.0226700 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006585 | 788226370-97370-DTLSB-02_22_2023-SVCENTCO-1^07216001.0288601 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006586 | 788308306-54823-DTLSB-04_23_2024-GO95MLD-1^06245007.0222643 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006587 | 788326686-68686-DTLSB-02_28_2024-GO95TCH-1^07216001.0273801 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006588 | 788441804-24390-DETAIL-03_27_2025-GO95HV-1^06239003.0019705 | OTHER | Non-HFTD | Distribution | 2025-03-27 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006589 | 788669501-92579-DETAIL-08_13_2024-GO95HV-1^06245005.0360501 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006590 | 788669501-92579-DETAIL-08_13_2024-SVCROAD-1^06245005.0360501 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006591 | 788736180-32559-DETAIL-03_21_2024-GO95MLD-1^06246005.0060200 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006592 | 788946925-98000-DETAIL-03_25_2025-GO95HV-1^06239003.0019508 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006593 | 789155371-26062-DETAIL-04_16_2024-GO95MLD-1^06145002.0180800 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006594 | 789179331-80431-DETAIL-03_27_2023-GO95MLD-1^06142016.0052003 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006595 | 790027586-4179-DETAIL-04_08_2024-GO95MLD-1^06147005.0234003 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006596 | 790196506-89029-DETAIL-05_07_2024-GO95MLD-1^06142012.0123204 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006597 | 790235282-1880-DETAIL-02_13_2025-SVCDEFLC-1^06240004.0168000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006598 | 791176347-87590-AUDIT-02_25_2025-GO95CL10-1^06239004.0244843 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006599 | 791176347-87590-DETAIL-02_03_2025-GO95MLD-1^06239004.0244843 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006600 | 791364045-36762-DETAIL-05_15_2024-GO95MLD-1^06142012.0122700 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006601 | 791435076-55076-DETAIL-01_29_2025-GO95HV-1^06239004.0227301 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006602 | 791564673-33262-DETAIL-04_24_2024-GO95MLD-1^06245001.0017500 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006603 | 791564673-33262-DETAIL-04_24_2024-GRDRODHI-1^06245001.0017500 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006604 | 791774398-59749-ADMIN-03_19_2025-POLEREPL-1^06245006.0155301 | POLE | Non-HFTD | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006605 | 791774398-59749-DETAIL-08_12_2024-XARMSPCR-1^06245006.0155301 | CROSSARM | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006606 | 791784713-90489-DTLSB-08_10_2023-GO95MLD-1^06243009.0276100 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006607 | 791930641-37139-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0032100 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006608 | 792363429-51913-DETAIL-07_23_2024-GO95MLD-1^06245006.0142041 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006609 | 792393905-2489-DETAIL-10_28_2021-ENCHRW-1^06148005.0146103 | OTHER | Non-HFTD | Distribution | 2021-10-28 | 2024-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006610 | 792555829-94349-AUDIT-02_27_2024-SVCNEUT-1^07216001.0261102 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006611 | 793044638-57300-DETAIL-03_14_2023-GO95MLD-1^07117002.0275700 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006612 | 793157638-13643-DTLSB-05_02_2024-GO95MLD-1^06245007.0222846 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006613 | 793161404-66679-DTLSB-02_07_2023-GO95BLTC-1^06248001.0158100 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006614 | 793467963-19972-DETAIL-04_24_2024-GRDRODHI-1^06245001.0017501 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006615 | 793514483-18220-DETAIL-02_26_2025-GO95HV-1^06241005.0364902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006616 | 793534019-18169-DETAIL-07_23_2024-GO95MLD-1^06245006.0141002 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006617 | 793796405-26472-DETAIL-05_15_2024-GUYHINS-1^06142012.0124601 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006618 | 793837091-18472-DETAIL-04_11_2024-GO95MLD-1^06245002.0144100 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006619 | 793903359-19129-DETAIL-05_13_2024-SVCDEFLC-1^06142012.0123305 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006620 | 79416860-99399-ADMIN-02_19_2025-POLEREPL-1^06245007.0218803 | POLE | Non-HFTD | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006621 | 794445512-11780-DETAIL-03_10_2025-GO95HV-1^06240004.0289800 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006622 | 794528495-19972-DTLSB-05_08_2024-GO95HV-1^06244001.0032700 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006623 | 794999050-95313-DTLSB-09_30_2024-GO95MLD-1^06245007.0231441 | OTHER | Non-HFTD | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006624 | 79525823-2710-DETAIL-02_08_2023-GO95MLD-1^06146004.0081000 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006625 | 795379913-71660-DETAIL-01_14_2025-SVCDEFLC-1^06240004.0097143 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006626 | 795667081-26069-DETAIL-07_24_2024-GUYHINS-1^06244005.0132401 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006627 | 795709648-37716-DETAIL-10_08_2024-SVCDEFLC-1^07216001.0200141 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006628 | 795896568-91949-DTLSB-02_19_2024-GO95CL10-1^07216001.0265603 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006629 | 795896568-91949-DTLSB-02_19_2024-GO95MLD-1^07216001.0265603 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006630 | 795994328-27249-DETAIL-03_14_2024-GO95MLD-1^06245005.0060302 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006631 | 796110406-73840-DETAIL-01_27_2025-SVCDEFLC-1^06240004.0081302 | OTHER | HFTD Tier 2 | Distribution | 2025-01-27 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006632 | 796419088-70969-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 5/024 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006633 | 796551319-93479-DTLTRT-11_01_2023-GUYNOINS-1^668010/00 10A/018 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-01 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006634 | 796643081-95081-DETAIL-03_27_2023-GUYHINS-1^06142016.0052300 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006635 | 797069888-73259-DTLSB-02_08_2024-SVCDEFLC-1^07216001.0197101 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006636 | 79732681-85259-DETAIL-03_20_2023-ABNDEQPM-1^07118004.0020500 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006637 | 79740835-98800-DETAIL-03_13_2025-GO95HV-1^06239003.0242600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006638 | 797486159-73809-DTLSB-09_05_2024-GUYNOINS-1^06245007.0034000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006639 | 797539473-19882-DETAIL-02_05_2018-ENCHRW-1^06248001.0276600 | OTHER | Non-HFTD | Distribution | 2018-02-05 | 2021-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006640 | 797539473-19882-DTLSB-02_09_2023-GO95MLD-1^06248001.0276600 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006641 | 798102931-89859-ADMIN-10_23_2023-POLEDERP-1^07216001.0104301 | POLE | Non-HFTD | Distribution | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006642 | 798254478-70539-DTLSB-02_27_2024-GO95HV-1^07216001.0260904 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006643 | 798466601-6001-DETAIL-01_14_2025-SVCENTBK-1^06239004.0258341 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006644 | 798595741-46514-DETAIL-03_28_2023-GO95MLD-1^06142016.0053300 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006645 | 798595741-46514-DETAIL-03_28_2023-GRDRODHI-1^06142016.0053300 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006646 | 798691455-41729-DETAIL-05_16_2024-LIGHT-1^06142012.0124803 | CONNECTION DEVICE | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006647 | 799018963-96389-DETAIL-02_22_2023-CONDFRAY-1^06247002.0049200 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006648 | 799018963-96389-DETAIL-02_22_2023-GO95MLD-1^06247002.0049200 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006649 | 799021797-63182-DETAIL-03_20_2024-GO95HV-1^06245002.0123200 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006650 | 799327074-86782-DETAIL-03_20_2024-GO95MLD-1^06245001.0071600 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006651 | 799336916-30139-DETAIL-03_25_2024-GRDRODHI-1^06244005.0146102 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006652 | 799368144-19249-DTLSB-02_07_2024-GUYHINS-1^07216001.0199104 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006653 | 799487483-81490-DETAIL-03_10_2025-GO95CL10-1^06241004.0313100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006654 | 799533733-50729-DTLSB-09_07_2023-GO95HV-1^06243008.0023001 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006655 | 79987066-88513-DETAIL-02_04_2025-CLRTOUCH-1^06239004.0135045 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-04 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006656 | 79987066-88513-DETAIL-02_04_2025-GO95HV-1^06239004.0135045 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006657 | 799949168-38682-DETAIL-03_19_2024-GO95MLD-1^06245002.0013000 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006658 | 799949168-38682-DETAIL-03_19_2024-GRDRODHI-1^06245002.0013000 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006659 | 800000764-23579-DETAIL-01_16_2023-GO95MLD-1^06148004.0160300 | OTHER | Non-HFTD | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006660 | 800117361-89880-DETAIL-03_19_2025-GO95HV-1^06239001.0067600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006661 | 800256663-35529-DTLSB-07_26_2023-GO95HV-1^06243009.0087902 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006662 | 800854549-17630-DTLTRT-10_19_2023-GO95MLD-1^668010/00 2/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006663 | 80086013-20209-DTLSB-09_05_2023-GO95MLD-1^06243008.0178500 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006664 | 800860489-2049-DETAIL-03_01_2023-SVCROAD-1^07216001.0292540 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006665 | 801052691-82780-DETAIL-03_19_2025-GO95HV-1^06239001.0061600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006666 | 801273259-11559-DETAIL-03_01_2023-SVCENTBK-1^07216001.0292641 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006667 | 801841698-18459-DETAIL-06_03_2024-GUYHINS-1^06246005.0314101 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-06-03 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006668 | 802112441-94070-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006669 | 802240241-79899-DTLTRT-10_27_2022-GO95MLD-1^668001/00 6/029 | OTHER | Non-HFTD | Transmission | 2022-10-27 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006670 | 802550016-91970-DETAIL-03_18_2025-GO95HV-1^06240003.0368103 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006671 | 802647303-19759-DTLSB-02_16_2024-GUYNOINS-1^07216001.0270000 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006672 | 802938998-94502-DETAIL-04_22_2024-GO95HV-1^06145001.0119101 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006673 | 802999629-68349-DTLSB-02_20_2024-GO95MLD-1^07216001.0260340 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006674 | 803106481-92829-DETAIL-05_13_2024-GO95MLD-1^06142012.0122304 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006675 | 803186950-32949-DTLSB-04_22_2024-SVCROOF-1^06245007.0225200 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006676 | 803186950-32949-DTLSB-04_22_2024-SVCROOF-2^06245007.0225200 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006677 | 803295009-96942-DTLSB-08_23_2023-GO95HV-1^06243009.0133001 | OTHER | Non-HFTD | Distribution | 2023-08-23 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006678 | 803418863-4339-DETAIL-08_05_2024-GO95HV-1^06244005.0323001 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006679 | 804100210-20210-DETAIL-01_22_2025-SVCDEFLC-1^06240004.0089512 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006680 | 804174961-95961-DETAIL-06_20_2024-GUYNOINS-1^06246006.0233001 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-06-20 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006681 | 804983116-1861-DETAIL-02_24_2025-SVCDEFLC-1^06239004.0367800 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006682 | 805050561-29659-DETAIL-06_17_2024-GO95MLD-1^06246006.0239200 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006683 | 805075068-16169-DTLTRT-10_11_2023-GO95HV-1^668010/00 5/044 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006684 | 805236558-35849-DTLSB-02_20_2024-GO95CL10-1^07216001.0261508 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006685 | 805247108-31289-DETAIL-11_09_2022-GO95MLD-1^06246007.0063400 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006686 | 805283563-19641-DETAIL-03_04_2025-GO95HV-1^06241005.0131801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006687 | 805497570-5270-DETAIL-03_19_2025-GO95HV-1^06239002.0019602 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006688 | 806020133-56721-DETAIL-02_18_2025-CLRTOUCH-1^06239004.0361404 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-18 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006689 | 806099764-88039-DTLSB-02_07_2024-SVCENTBK-1^07216001.0199310 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006690 | 806426433-76113-DTLSB-05_01_2024-SVCWIND-1^06245007.0227641 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006691 | 806503823-55329-DTLSB-08_29_2023-GO95BLTC-1^06243009.0120101 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006692 | 806503823-55329-DTLSB-08_29_2023-GO95HV-1^06243009.0120101 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006693 | 806503823-55329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120101 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006694 | 806537670-24549-DETAIL-08_01_2024-GO95HV-1^06245006.0105100 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006695 | 807201144-26012-DTLSB-05_09_2024-GO95MLD-1^06244001.0118900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006696 | 80758849-12610-DETAIL-03_09_2023-SVCWIND-1^07216001.0293608 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006697 | 807892099-15399-DTLTRT-10_24_2022-GO95MLD-1^668075/00 17/024 | OTHER | Non-HFTD | Transmission | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006698 | 807894671-59689-DETAIL-01_09_2023-GO95MLD-2^06148003.0141200 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006699 | 80871128-28610-DETAIL-04_22_2024-GRDRODHI-1^06145001.0029600 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006700 | 808836875-98663-DETAIL-04_24_2023-GO95MLD-1^07117003.0025101 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006701 | 809072736-52380-DETAIL-01_22_2025-GO95MLD-1^06239004.0255543 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006702 | 810058476-89159-DETAIL-05_05_2022-GUYLOINS-1^07117001.0308301 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-05-05 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006703 | 810167404-36032-DTLSB-05_09_2024-GO95MLD-1^06244001.0112901 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006704 | 810173260-76260-DETAIL-10_26_2022-GUYHINS-1^06246009.0136902 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006705 | 810264073-57150-DETAIL-01_16_2025-GO95HV-1^06239004.0257609 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006706 | 810347106-67106-DETAIL-01_29_2025-GO95MLD-1^06239004.0250700 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006707 | 810428131-67570-DTLTRT-10_16_2023-GO95BLTC-1^668010/00 15X/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006708 | 810428131-67570-DTLTRT-10_16_2023-GO95MLD-1^668010/00 15X/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006709 | 810658605-93432-DTLSB-05_13_2024-GO95MLD-1^06245001.0294200 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006710 | 810965519-98519-DETAIL-03_30_2023-GO95TCH-1^06142016.0054300 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006711 | 810976490-8539-DETAIL-05_11_2022-GO95HV-1^07116001.0059601 | OTHER | HFTD Tier 2 | Distribution | 2022-05-11 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006712 | 810976490-8539-DETAIL-05_11_2022-GUYHINS-1^07116001.0059601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-05-11 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006713 | 811287614-20714-DETAIL-03_27_2023-GO95MLD-1^06142016.0082901 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006714 | 811452666-899-DETAIL-03_25_2024-GO95MLD-1^06147005.0141901 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006715 | 811680946-59149-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0297705 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006716 | 811824334-41629-DTLSB-08_07_2023-GO95HV-1^06243009.0196501 | OTHER | Non-HFTD | Distribution | 2023-08-07 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006717 | 811881406-5259-AUDIT-04_30_2024-GO95TCH-1^06247005.0339202 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006718 | 811910845-89379-DETAIL-01_10_2023-GO95BLTC-1^06148004.0170300 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006719 | 811964866-889-DETAIL-03_14_2024-GO95MLD-1^06245006.0126602 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006720 | 812303973-91680-DETAIL-02_13_2025-GO95CL10-1^06240004.0169105 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006721 | 812463028-14028-DETAIL-07_10_2023-GO95HV-1^06244008.0304001 | OTHER | Non-HFTD | Distribution | 2023-07-10 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006722 | 812463028-14028-DETAIL-07_10_2023-GO95MLD-1^06244008.0304001 | OTHER | Non-HFTD | Distribution | 2023-07-10 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006723 | 812463028-14028-DETAIL-07_10_2023-GO95TCH-1^06244008.0304001 | OTHER | Non-HFTD | Distribution | 2023-07-10 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006724 | 812649907-38309-DETAIL-04_10_2024-GO95HV-1^06147005.0160201 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006725 | 812792139-53240-DETAIL-03_24_2025-COPLLEAN-1^06238004.0011402 | POLE | HFTD Tier 2 | Distribution | 2025-03-24 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006726 | 812894973-77142-DETAIL-04_24_2024-GO95MLD-1^06245001.0018400 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006727 | 813197653-72920-ADMIN-03_06_2025-ANCHIDLE-1^06240004.0270000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006728 | 813197653-72920-DETAIL-03_06_2025-SVCDEFLC-1^06240004.0270000 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006729 | 813364203-60780-DETAIL-03_17_2025-GO95HV-1^06239002.0059600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006730 | 813959629-84249-DETAIL-03_09_2023-GO95HV-1^07216001.0294601 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006731 | 813959629-84249-DETAIL-03_09_2023-GO95MLD-1^07216001.0294601 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006732 | 814204068-67050-DETAIL-03_25_2025-GO95HV-1^06239003.0019413 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006733 | 814247675-90342-DTLSB-02_08_2023-GO95MLD-1^06248001.0163401 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006734 | 814330843-41099-DETAIL-06_25_2024-GO95MLD-1^06244005.0236600 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006735 | 814516068-78749-DTLSB-02_26_2024-GO95MLD-1^07216001.0260909 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006736 | 814550509-25442-DTLSB-05_28_2024-GO95MLD-1^06244003.0285601 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006737 | 814591096-10642-DTLSB-05_22_2024-GO95MLD-1^06244001.0337000 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006738 | 814597151-71249-DETAIL-02_26_2024-GO95MLD-1^07113001.0138308 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006739 | 815207180-77149-DETAIL-03_16_2023-GO95MLD-1^07113001.0042500 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006740 | 815439156-50023-DTLSB-04_29_2024-GO95TCH-1^06245007.0222647 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006741 | 815736097-17097-DETAIL-02_04_2025-BIRDDMG-1^06240004.0169546 | POLE | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006742 | 816085936-94559-DETAIL-08_19_2024-GUYNOINS-1^06246004.0326900 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-19 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006743 | 816477089-45612-ADMIN-06_27_2024-ABNDEQPM-2^06244009.0360003 | OTHER | HFTD Tier 2 | Distribution | 2024-06-27 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006744 | 817044704-20010-DETAIL-03_13_2025-GO95HV-1^06238004.0150101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006745 | 817793281-19439-DETAIL-07_18_2024-GO95HV-1^06244004.0056000 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006746 | 81793435-79640-DETAIL-02_24_2025-SVCDEFLC-1^06240004.0152704 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006747 | 818007221-97331-DETAIL-02_27_2025-GO95MLD-1^06241005.0178901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006748 | 818495418-69769-DTLTRT-06_30_2022-GO95MLD-1^668005/00 12/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006749 | 818513284-90150-DRONE_HY-10_16_2023-GO95HV-1^668033/01 20/002 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006750 | 818700959-47652-DETAIL-04_22_2024-GO95MLD-1^06146001.0360000 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006751 | 818788945-24449-DETAIL-07_29_2024-GO95MLD-1^06245006.0113901 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006752 | 819360553-19049-DTLSB-02_06_2024-CLMBTRE-1^07216001.0309800 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006753 | 819388553-15443-DETAIL-03_23_2023-GO95MLD-1^06142016.0081803 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006754 | 819410230-80230-DETAIL-07_24_2024-GO95MLD-1^06244005.0133301 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006755 | 81946208-55849-DTLSB-02_21_2024-GO95HV-1^07216001.0261400 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006756 | 819574293-67530-DETAIL-01_28_2025-BIRDDMG-1^06240004.0170940 | POLE | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006757 | 820196514-58762-DTLSB-02_07_2023-ABNDEQPM-1^06248001.0157201 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006758 | 820196514-58762-DTLSB-02_07_2023-GO95MLD-1^06248001.0157201 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006759 | 820400585-53359-DETAIL-02_29_2024-GO95MLD-1^07113001.0157901 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006760 | 820924590-45242-ADMIN-07_16_2024-POLEREPL-1^668044/00 4/060 | POLE | HFTD Tier 2 | Transmission | 2024-07-16 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006761 | 820924590-46162-ADMIN-07_16_2024-POLEREPL-1^668044/00 4/060 | POLE | HFTD Tier 2 | Transmission | 2024-07-16 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006762 | 820930255-16870-DETAIL-03_11_2025-GO95HV-1^06238004.0334305 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006763 | 82126539-21610-DETAIL-03_18_2024-GO95HV-1^06245002.0035001 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006764 | 821580561-38129-DETAIL-05_07_2024-GO95MLD-1^06142012.0122005 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006765 | 821595223-34560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006766 | 821595223-4560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006767 | 821758906-87162-DETAIL-02_06_2023-GO95MLD-1^06147002.0318900 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006768 | 821829974-69379-DETAIL-07_03_2024-GRDRODHI-1^06244005.0230841 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006769 | 821848668-72450-DETAIL-09_09_2024-SVCDEFLC-1^06240004.0098501 | OTHER | HFTD Tier 2 | Distribution | 2024-09-09 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006770 | 822182984-24094-DETAIL-03_29_2023-SVCROAD-1^06142016.0084904 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006771 | 82222856-31099-DTLSB-10_07_2024-GO95HV-1^06245006.0330000 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006772 | 822334889-90639-DETAIL-02_28_2023-GO95MLD-1^07216001.0299601 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006773 | 822357730-25649-DETAIL-08_12_2024-GO95HV-1^06245006.0101401 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006774 | 822717841-77479-DETAIL-03_11_2024-GO95MLD-1^06147004.0049801 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006775 | 822717841-77479-DETAIL-03_11_2024-GRDRODHI-1^06147004.0049801 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006776 | 822968393-44309-ADMIN-06_05_2024-GO95STUB-1^06245010.0322802 | OTHER | HFTD Tier 2 | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006777 | 82307245-36710-DTLSB-05_08_2024-GO95HV-1^06244001.0107600 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006778 | 82307245-36710-DTLSB-05_08_2024-GO95MLD-1^06244001.0107600 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006779 | 823105188-98002-DETAIL-03_05_2025-GO95HV-1^06241005.0121001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006780 | 823153619-31072-DETAIL-04_11_2024-GO95HV-1^06245002.0109502 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006781 | 823278728-33170-DETAIL-02_27_2025-SVCROAD-1^06240004.0063103 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006782 | 823483583-54583-DETAIL-04_04_2024-GO95MLD-1^06147005.0240400 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006783 | 823755861-40480-DETAIL-02_20_2025-SVCROAD-1^06240004.0304100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-20 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006784 | 823874069-80379-DRONE_HY-09_16_2023-GO95HV-1^668002/00 20/060 | OTHER | HFTD Tier 2 | Transmission | 2023-09-16 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006785 | 824097186-23740-AUDIT-03_18_2025-SVCROAD-1^06240004.0214701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006786 | 824097186-23740-AUDIT-03_25_2025-GO95TCH-1^06240004.0214701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006787 | 824327932-78602-DTLTRT-04_11_2024-BIRDDMG-1^668067/00 5/007 | POLE | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006788 | 824327932-89469-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 5/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006789 | 824327932-99602-DTLTRT-04_11_2024-BIRDDMG-1^668067/00 5/007 | POLE | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006790 | 824478106-19106-DETAIL-01_29_2025-GO95MLD-1^06239004.0269800 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006791 | 82466240-57601-DETAIL-06_02_2022-GO95HV-1^06241005.0030701 | OTHER | HFTD Tier 2 | Distribution | 2022-06-02 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006792 | 824673794-29469-DTLTRT-07_20_2022-GO95HV-1^668005/00 5/055 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006793 | 82483929-60910-DETAIL-03_05_2025-GO95MLD-1^06241005.0135500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006794 | 824930404-56889-DTLSB-07_26_2023-GO95MLD-1^06243009.0059901 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006795 | 824982243-68282-DETAIL-02_09_2023-GO95MLD-1^06146004.0085000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006796 | 825028489-45509-DTLSB-09_04_2024-GO95MLD-1^06245007.0016604 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006797 | 826047485-15349-DETAIL-02_27_2023-ABNDEQPM-1^07216001.0294740 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006798 | 826177106-49889-DTLSB-04_15_2024-SVCWIND-1^06245007.0225107 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006799 | 82633895-29910-DETAIL-04_23_2024-GUYLOINS-1^06145001.0037200 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006800 | 826374446-61672-DETAIL-06_06_2023-GO95MLD-1^06244010.0342300 | OTHER | HFTD Tier 2 | Distribution | 2023-06-06 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006801 | 826504133-36979-DTLSB-08_16_2023-GO95MLD-1^06243009.0105000 | OTHER | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006802 | 82668533-96739-DETAIL-03_14_2023-GO95HV-1^07114001.0276500 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006803 | 82668533-96739-DETAIL-03_14_2023-GO95MLD-1^07114001.0276500 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006804 | 82750425-71239-DETAIL-03_06_2023-SVCENTCO-1^07216001.0296706 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006805 | 827636678-61582-DETAIL-03_28_2024-GO95MLD-1^06147005.0165902 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006806 | 82785244-8244-DETAIL-04_29_2024-GO95MLD-1^06142016.0174200 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006807 | 828150224-99292-DTLSB-05_08_2024-GO95MLD-1^06245001.0334600 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006808 | 828198558-62392-DTLSB-05_15_2024-GO95HV-1^06244002.0217701 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006809 | 828252699-96939-DETAIL-10_15_2024-GO95MLD-1^07216001.0204203 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006810 | 828263588-5043-DTLSB-05_06_2024-GO95MLD-1^06245007.0221744 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006811 | 828366986-78189-DTLSB-08_29_2023-GO95TCH-1^06243009.0117401 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006812 | 828534038-54923-ADMIN-10_29_2024-SVCROOF-1^07217001.0273202 | OTHER | Non-HFTD | Distribution | 2024-10-29 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006813 | 82855024-84959-DTLSB-02_13_2024-SVCNEUT-1^07216001.0187401 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006814 | 828677623-13292-DTLSB-05_23_2024-GO95MLD-1^06243001.0239601 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006815 | 829047883-33560-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006816 | 829047883-63560-DTLTRT-04_09_2024-GO95HV-1^668062/00 4/003 | OTHER | Non-HFTD | Transmission | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006817 | 829047883-78653-DTLTRT-04_09_2024-GO95HV-1^668062/00 4/003 | OTHER | Non-HFTD | Transmission | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006818 | 829047883-78653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006819 | 829847215-61714-DETAIL-05_23_2022-SVCRUBLG-1^06242005.0368641 | OTHER | HFTD Tier 2 | Distribution | 2022-05-23 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006820 | 829956439-60849-DETAIL-02_19_2024-GO95MLD-1^07113002.0185104 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006821 | 829956439-60849-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0185104 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006822 | 829956439-60849-DETAIL-02_19_2024-SVCENTCO-1^07113002.0185104 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006823 | 830046259-96929-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0121102 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006824 | 8305000-9789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223700 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006825 | 830710687-74328-DETAIL-10_10_2024-SVCNEUT-1^07216001.0205113 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006826 | 830835106-55106-DETAIL-01_29_2025-GO95MLD-1^06239004.0251701 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006827 | 83084111-65602-DETAIL-06_25_2024-GO95HV-1^06244005.0238401 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006828 | 831014640-6149-DTLSB-02_19_2024-GO95MLD-1^07216001.0261300 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006829 | 831050599-66653-DTLSB-04_17_2024-SVCWIND-1^06245007.0223440 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006830 | 831078317-21859-DETAIL-03_27_2024-GO95MLD-1^06247005.0324301 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006831 | 831352732-11680-DETAIL-02_12_2025-GO95HV-1^06240004.0282600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006832 | 831611340-8879-DTLSB-07_17_2023-GO95MLD-1^06243010.0028101 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006833 | 831688253-35689-DETAIL-06_11_2024-GUYLOINS-1^06245007.0345103 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006834 | 832312553-48522-DETAIL-07_15_2024-GO95MLD-1^06244005.0269202 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006835 | 832594606-46740-DETAIL-01_22_2025-BIRDDMG-1^06240004.0083042 | POLE | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006836 | 83265633-88249-DETAIL-03_15_2023-GO95MLD-1^07216001.0291500 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006837 | 83265633-88249-DETAIL-03_15_2023-GUYHINS-1^07216001.0291500 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006838 | 832761608-98702-DETAIL-04_23_2024-GO95MLD-1^06145001.0028300 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006839 | 833084323-27180-DETAIL-01_30_2025-GO95HV-1^06240004.0162601 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006840 | 833087429-56713-DETAIL-05_30_2024-GO95MLD-1^06246005.0272902 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006841 | 833203443-62069-DTLSB-04_09_2024-SVCWIND-1^06245007.0228005 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006842 | 83352921-59650-DETAIL-01_24_2025-GO95HV-1^06239004.0258502 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006843 | 833596979-34559-DETAIL-05_10_2022-GO95CL10-1^07116001.0091400 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006844 | 833685711-68829-DETAIL-05_09_2024-GO95MLD-1^06142012.0121403 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006845 | 833812631-14711-DETAIL-01_21_2025-GO95HV-1^06239004.0255346 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006846 | 834067243-69789-DTLSB-05_23_2024-GO95MLD-1^06243001.0149200 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006847 | 834084228-53379-DETAIL-10_09_2024-CLMBTRE-1^07216001.0202142 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006848 | 834370198-3823-ADMIN-06_24_2024-POLEDERP-1^07217001.0273801 | POLE | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006849 | 835450348-97049-DTLSB-02_13_2024-GO95MLD-1^07216001.0187102 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006850 | 835450348-97049-DTLSB-02_13_2024-SVCROAD-1^07216001.0187102 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006851 | 83554526-27520-DTLSB-05_22_2024-GO95MLD-1^06244001.0333700 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006852 | 835547384-38384-DTLSB-08_22_2024-GO95CL10-1^06245006.0320500 | OTHER | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006853 | 835547384-38384-DTLSB-08_22_2024-GO95HV-1^06245006.0320500 | OTHER | HFTD Tier 2 | Distribution | 2024-08-22 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006854 | 835565905-74349-DETAIL-02_27_2024-GO95HV-1^07113002.0183705 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006855 | 835571650-7812-DETAIL-03_13_2024-GO95MLD-1^06147004.0190500 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006856 | 835575784-37812-DETAIL-03_20_2024-GO95MLD-1^06245001.0052101 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006857 | 835658360-88360-DTLSB-02_16_2024-GO95MLD-1^07216001.0279100 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006858 | 835684168-13450-DETAIL-03_20_2025-GO95HV-1^06239003.0015304 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006859 | 835742788-53390-DETAIL-01_28_2025-GO95HV-1^06239004.0244409 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006860 | 835742788-53390-DETAIL-01_28_2025-SVCROAD-1^06239004.0244409 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006861 | 835770848-48670-DETAIL-03_28_2023-GO95TCH-1^06240004.0169507 | OTHER | HFTD Tier 2 | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006862 | 835770848-48670-DETAIL-03_28_2023-SVCENTCO-1^06240004.0169507 | OTHER | HFTD Tier 2 | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006863 | 83589616-1049-DETAIL-10_09_2024-GO95MLD-1^07216001.0202205 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006864 | 836601679-15599-DETAIL-04_01_2024-GO95HV-1^06147005.0093800 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006865 | 836603229-50770-ADMIN-04_04_2025-SVCTREE-1^06240004.0063100 | OTHER | HFTD Tier 2 | Distribution | 2025-04-04 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006866 | 836603229-50770-DETAIL-04_26_2023-SVCENTCO-1^06240004.0063100 | OTHER | HFTD Tier 2 | Distribution | 2023-04-26 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006867 | 836720470-15649-DETAIL-03_16_2023-GO95MLD-1^07113001.0042501 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006868 | 83674553-15620-DETAIL-02_22_2023-GO95HV-1^06247002.0031900 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006869 | 836783816-66460-DTLTRT-10_09_2023-GO95HV-1^668010/00 2/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006870 | 836783816-66460-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006871 | 836783816-66460-DTLTRT-10_09_2023-GUYHINS-1^668010/00 2/038 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006872 | 837092141-31222-DETAIL-12_19_2022-GO95HV-1^668001/00 2/024 | OTHER | Non-HFTD | Transmission | 2022-12-19 | 2027-12-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006873 | 837524544-28090-DETAIL-03_26_2025-GO95HV-1^06239003.0018417 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006874 | 837571408-72408-DETAIL-03_16_2023-ABNDEQPM-1^07114001.0282604 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006875 | 837604244-73559-DTLSB-02_13_2024-GO95MLD-1^07216001.0199800 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006876 | 837802665-33009-DTLSB-08_28_2024-GO95MLD-1^06245007.0141500 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006877 | 838147676-96629-DETAIL-08_07_2024-XARMSPCR-1^06245008.0279800 | CROSSARM | HFTD Tier 2 | Distribution | 2024-08-07 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006878 | 838158625-4659-DETAIL-10_14_2024-CLMBTRE-1^07216001.0201240 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006879 | 838216285-38788-DETAIL-07_11_2023-SVCENTBK-1^06244008.0333901 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006880 | 838498341-6469-DTLTRT-07_20_2022-GO95HV-1^668005/00 9/054 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006881 | 838878443-6289-DETAIL-06_07_2023-GO95MLD-1^06244010.0275401 | OTHER | Non-HFTD | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006882 | 83916059-35379-DETAIL-03_04_2024-GO95HV-1^06147004.0012901 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006883 | 839259300-23800-DTLTRT-10_26_2022-GO95HV-1^668075/00 8/027 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006884 | 839338838-84203-DTLSB-07_22_2024-GO95MLD-1^06245006.0063940 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006885 | 840329963-43629-DETAIL-05_15_2024-GO95HV-1^06142012.0122900 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006886 | 840649539-12569-DETAIL-06_05_2024-GO95MLD-1^06246006.0264200 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006887 | 841359944-25622-DTLSB-05_08_2024-GO95MLD-1^06245001.0331901 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006888 | 841359944-25622-DTLSB-05_08_2024-GRDRODHI-1^06245001.0331901 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006889 | 84155189-29879-DETAIL-07_08_2024-GO95HV-1^06244005.0136802 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006890 | 841633039-49579-DETAIL-03_06_2024-GO95TCH-1^06147004.0011500 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006891 | 841648992-35831-DETAIL-02_27_2025-GO95BLTC-1^06241005.0171600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006892 | 841648992-35831-DETAIL-02_27_2025-GO95MLD-1^06241005.0171600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006893 | 841733634-41499-DTLSB-04_23_2024-GO95MLD-1^06245007.0224802 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006894 | 841733634-41499-DTLSB-04_23_2024-SVCENTCO-1^06245007.0224802 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006895 | 842842629-44300-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/005 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006896 | 842842629-63300-DTLTRT-09_29_2020-GO95HV-1^668018/00 1/005 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006897 | 842904418-65279-DETAIL-03_14_2024-GO95MLD-1^06245006.0127904 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006898 | 842904418-65279-DETAIL-03_14_2024-GUYHINS-1^06245006.0127904 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006899 | 843143401-76959-DETAIL-05_16_2022-SVCNEUT-1^07116001.0091900 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006900 | 843191949-74949-DTLSB-02_19_2024-SVCROAD-1^07216001.0261310 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006901 | 843213748-29443-DETAIL-03_06_2023-GO95MLD-1^07117002.0208301 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006902 | 843346816-84249-DETAIL-03_14_2024-GO95HV-1^06245006.0127701 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006903 | 843365700-71332-DTLTRT-06_06_2024-GO95HV-1^668084/00 1/001 | OTHER | Non-HFTD | Transmission | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006904 | 8434834-98079-DTLSB-05_09_2024-GO95MLD-1^06244001.0026002 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006905 | 843594020-42232-DETAIL-06_21_2023-GO95HV-1^06244009.0337900 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006906 | 843594020-42232-DETAIL-06_21_2023-GO95MLD-1^06244009.0337900 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006907 | 84455355-35049-DETAIL-02_26_2024-CUTOUTAR-3^07113001.0211403 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006908 | 84455355-35049-DETAIL-02_26_2024-CUTOUTAR-4^07113001.0211403 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006909 | 844657365-60759-DETAIL-03_06_2024-SVCENTCO-1^06245007.0272902 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006910 | 844820678-61849-DTLSB-02_19_2024-GO95CL10-1^07216001.0265800 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006911 | 844902261-48109-DTLSB-08_26_2024-GO95MLD-1^06245007.0114301 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006912 | 844961469-95639-DETAIL-07_30_2024-GO95MLD-1^06244005.0359200 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006913 | 844967944-56242-DETAIL-03_20_2024-GO95MLD-1^06245001.0063501 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006914 | 845346403-71859-DETAIL-10_24_2024-SVCRUBLG-1^07216001.0207940 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006915 | 845413988-2369-ADMIN-12_21_2022-UBPBGYBK-1^668005/00 11/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006916 | 845638115-61449-DETAIL-07_29_2024-GO95HV-1^06245006.0116900 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006917 | 845791136-12639-DETAIL-10_14_2024-SVCROAD-1^07216001.0200301 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006918 | 845942228-98549-AUDIT-03_12_2024-GO95HV-1^07113001.0133901 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006919 | 846356618-15959-DTLTRT-07_06_2022-GRDRODHI-1^668005/00 7/036 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006920 | 846455065-45733-DETAIL-03_01_2023-GO95MLD-1^07117002.0198302 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006921 | 846467890-31709-DETAIL-11_02_2022-GO95HV-1^06246008.0054502 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006922 | 846583268-49800-DETAIL-11_02_2023-GUYHINS-1^668010/00 8/020 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-11-02 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006923 | 846877540-41159-ADMIN-12_21_2022-UBPBCTGD-1^668005/00 12/034 | OTHER | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006924 | 846877540-41159-DTLTRT-07_05_2022-GO95MLD-1^668005/00 12/034 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006925 | 847063351-84351-DETAIL-03_22_2024-GO95HV-1^06247005.0340141 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006926 | 847063351-84351-DETAIL-03_22_2024-GO95MLD-1^06247005.0340141 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006927 | 847241743-15338-DETAIL-04_28_2022-GO95MLD-1^07116001.0095301 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006928 | 848001814-38742-DETAIL-03_20_2024-GO95MLD-1^06245001.0051401 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006929 | 848438868-89740-DETAIL-03_20_2025-GRDRODHI-1^06239003.0018202 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006930 | 849214516-21249-DETAIL-03_11_2024-GO95MLD-1^06245006.0121101 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006931 | 849419301-30401-DTLSB-02_21_2024-GO95MLD-1^07216001.0260810 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006932 | 849528521-40333-DETAIL-01_28_2025-SVCDEFLC-1^06240004.0079505 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006933 | 849704460-31909-DTLSB-09_30_2024-GO95HV-1^06245007.0230040 | OTHER | Non-HFTD | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006934 | 849885101-56663-DETAIL-02_25_2025-SVCROAD-1^06240005.0128904 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006935 | 850018081-9439-DETAIL-07_02_2024-GO95MLD-1^06244005.0231600 | OTHER | Non-HFTD | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006936 | 850064195-24652-DETAIL-02_07_2023-GO95HV-1^06147002.0047300 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006937 | 850241305-18533-DETAIL-01_13_2025-POLEREPL-1^06247004.0075540 | POLE | Non-HFTD | Distribution | 2025-01-13 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006938 | 850305789-85813-AUDIT-09_03_2024-CONDFRAY-1^06245006.0143140 | CONDUCTOR | Non-HFTD | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006939 | 850305789-85813-AUDIT-09_03_2024-CONDFRAY-2^06245006.0143140 | CONDUCTOR | Non-HFTD | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006940 | 850691204-5139-AUDIT-03_22_2023-GO95HV-1^07114001.0338501 | OTHER | Non-HFTD | Distribution | 2023-03-22 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006941 | 851057811-19482-DTLSB-08_14_2023-GO95MLD-1^06243009.0238400 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006942 | 851057811-19482-DTLSB-08_14_2023-GUYHINS-1^06243009.0238400 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-08-14 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006943 | 851101005-12449-DETAIL-02_28_2024-SVCROAD-1^07113002.0182501 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006944 | 851147414-89939-DTLSB-02_06_2024-SVCNEUT-1^07216001.0307900 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006945 | 85133975-13859-DETAIL-10_17_2024-GO95MLD-1^07216001.0201506 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006946 | 851544651-40349-DETAIL-02_23_2023-GO95MLD-1^07216001.0299708 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006947 | 851794616-52759-DETAIL-10_21_2024-GO95MLD-1^07216001.0200704 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006948 | 851870664-81664-DETAIL-10_16_2024-GO95MLD-1^07216001.0208815 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006949 | 851879889-4043-DETAIL-03_26_2024-GO95HV-1^06246005.0053401 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006950 | 851879889-4043-DETAIL-03_26_2024-GO95MLD-1^06246005.0053401 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006951 | 8523504-18849-DETAIL-03_15_2023-GO95MLD-1^07114001.0339500 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006952 | 852726204-2939-DTLSB-02_06_2024-SVCROAD-1^07216001.0309803 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006953 | 852825596-61562-DETAIL-03_29_2023-GO95MLD-1^06142016.0083500 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006954 | 852946475-93649-DTLSB-02_27_2024-SVCNEUT-1^07216001.0270700 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006955 | 852974885-28491-DRONE_VS-11_13_2024-BIRDDMG-1^668038/00 3/047 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006956 | 853049066-29649-DETAIL-10_15_2024-GO95TCH-1^07216001.0203400 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006957 | 853126776-84870-AUDIT-02_10_2025-CLRTOUCH-1^06239004.0254240 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-10 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006958 | 853280068-76459-DETAIL-04_24_2023-GO95HV-1^07117003.0010700 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006959 | 853433210-44269-DETAIL-11_07_2022-GO95TCH-1^06246008.0016300 | OTHER | HFTD Tier 2 | Distribution | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006960 | 853610508-76870-DETAIL-02_04_2025-SVCDEFLC-1^06240004.0169601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006961 | 853610508-76870-DETAIL-02_04_2025-SVCDEFLC-2^06240004.0169601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006962 | 853690780-74549-DETAIL-08_06_2024-GO95MLD-1^06245006.0105301 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006963 | 85379488-49520-DTLTRT-06_28_2022-GO95MLD-1^668005/00 16/027 | OTHER | Non-HFTD | Transmission | 2022-06-28 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006964 | 85408179-68929-DTLSB-08_17_2023-GO95HV-1^06243009.0134500 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006965 | 854097459-13056-DETAIL-06_14_2023-GO95MLD-1^06244010.0354700 | OTHER | HFTD Tier 2 | Distribution | 2023-06-14 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006966 | 854512820-86870-DETAIL-02_12_2025-CLRTOUCH-1^06240004.0166502 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-12 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006967 | 854512820-86870-DETAIL-02_12_2025-CLRTOUCH-2^06240004.0166502 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-12 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006968 | 854512820-86870-DETAIL-02_12_2025-GO95TCH-1^06240004.0166502 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006969 | 854663658-99299-DTLSB-07_02_2024-GO95MLD-1^06245006.0185200 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006970 | 854891987-4558-DETAIL-10_10_2024-GO95MLD-1^07216001.0205002 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006971 | 855347622-32989-DTLSB-08_26_2024-GO95TCH-1^06245007.0113101 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006972 | 855452743-91272-DRONE_HY-09_28_2023-GO95HV-1^668033/00 13X1/004 | OTHER | Non-HFTD | Transmission | 2023-09-28 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006973 | 85557931-99931-DETAIL-05_09_2024-RISESTRP-1^06142012.0120509 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006974 | 855908693-58249-DETAIL-02_20_2024-GO95HV-1^07113002.0181105 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006975 | 856067846-13080-DETAIL-03_03_2025-GO95HV-1^06240004.0050004 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006976 | 856343831-29549-DETAIL-02_28_2024-GO95MLD-1^07113001.0030100 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006977 | 856889528-49359-DETAIL-05_31_2024-GO95MLD-1^06246005.0320502 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006978 | 856916389-38199-ADMIN-06_03_2024-ABNDEQPM-1^06245006.0029500 | OTHER | Non-HFTD | Distribution | 2024-06-03 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006979 | 857751159-21612-DETAIL-06_20_2023-GO95MLD-1^06244009.0361402 | OTHER | Non-HFTD | Distribution | 2023-06-20 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006980 | 857782501-26501-DETAIL-03_28_2023-ABNDEQPM-1^06142016.0052901 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006981 | 857782501-26501-DETAIL-03_28_2023-GO95MLD-1^06142016.0052901 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006982 | 857785630-84669-DETAIL-06_12_2023-GO95HV-1^06244009.0363400 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006983 | 858042824-68259-DTLSB-02_05_2024-CLMBTRE-1^07216002.0249900 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006984 | 858042824-68259-DTLSB-02_05_2024-GO95HV-1^07216002.0249900 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006985 | 858106579-36209-DETAIL-03_04_2024-GO95HV-1^06147004.0011200 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006986 | 858119666-46300-DTLTRT-11_01_2023-GO95HV-1^668010/00 17/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006987 | 858455931-76931-DETAIL-03_23_2023-GO95MLD-1^06142016.0050002 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006988 | 858461645-76582-DETAIL-04_23_2024-GO95MLD-1^06145001.0033100 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006989 | 859332073-34073-DTLSB-08_30_2023-GO95HV-1^06243008.0205700 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006990 | 859604145-59869-DTLTRT-10_10_2023-GO95HV-1^668010/00 14/037 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006991 | 859803333-53792-DETAIL-05_16_2024-GO95MLD-1^06142012.0120700 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006992 | 859864149-75549-DETAIL-03_14_2023-GO95MLD-1^07117002.0285900 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006993 | 859898673-38083-DTLSB-10_02_2024-GO95MLD-1^06245007.0217440 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006994 | 860240199-17879-DETAIL-03_26_2024-GRDRODHI-1^06246005.0051300 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006995 | 860240199-17879-DETAIL-03_26_2024-SVCWIND-1^06246005.0051300 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006996 | 860346285-24659-DETAIL-10_21_2024-GUYHINS-1^07216001.0202700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006997 | 860415841-35109-DTLSB-08_28_2024-GO95MLD-1^06245007.0113000 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130006998 | 861437228-98543-DTLSB-05_06_2024-GO95MLD-1^06245007.0220740 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130006999 | 861437228-98543-DTLSB-05_06_2024-SVCENTCO-1^06245007.0220740 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007000 | 862652364-8469-DTLTRT-07_20_2022-GO95HV-1^668005/00 1/055 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007001 | 862655745-35948-DETAIL-10_14_2024-GO95HV-1^07216001.0203202 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007002 | 862655745-35948-DETAIL-10_14_2024-GO95MLD-1^07216001.0203202 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007003 | 863446189-40129-DETAIL-05_06_2024-GO95MLD-1^06142012.0123002 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007004 | 863446189-40129-DETAIL-05_06_2024-SVCENTCO-1^06142012.0123002 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007005 | 863560492-36702-DETAIL-05_15_2024-GO95HV-1^06142012.0125701 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007006 | 86369793-60549-DETAIL-03_16_2023-GO95MLD-1^07114001.0208002 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007007 | 863743769-36002-DETAIL-04_22_2024-GO95HV-1^06146001.0359100 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007008 | 863766603-8002-DTLSB-05_23_2024-GO95HV-1^06243001.0130900 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007009 | 863995081-70202-DETAIL-04_16_2024-GO95MLD-1^06145002.0183801 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007010 | 86401673-99330-DETAIL-02_26_2025-SVCNEUT-1^06240004.0066000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007011 | 864050186-57399-DTLSB-09_05_2024-GO95HV-1^06245007.0236601 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007012 | 864265743-51459-DETAIL-04_28_2022-GO95MLD-1^07116001.0096304 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007013 | 864535566-42902-DETAIL-02_06_2023-GO95MLD-1^06147002.0318901 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007014 | 864955668-47943-DTLSB-04_23_2024-GO95MLD-1^06245007.0224540 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007015 | 865004411-52849-DETAIL-05_16_2022-GUYHINS-1^07116001.0094201 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007016 | 86518011-77632-DETAIL-07_07_2023-GRDRODHI-1^06244008.0329801 | OTHER | Non-HFTD | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007017 | 865358809-67589-ADMIN-04_02_2024-ABNDEQPM-1^06246005.0042501 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007018 | 86565588-6799-DETAIL-02_13_2025-SVCENTBK-1^06240004.0169142 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007019 | 866150076-14149-DETAIL-10_15_2024-SVCENTCO-1^07216001.0203402 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007020 | 866338354-89999-DTLTRT-10_27_2022-GUYNOINS-1^668001/00 13A/031 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-27 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007021 | 866681050-65789-DTLSB-07_23_2024-RISEGRD-1^06245007.0107403 | OTHER | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007022 | 867402406-34406-DETAIL-02_23_2023-GO95HV-1^07216001.0298901 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007023 | 868382711-229-DETAIL-04_05_2023-GO95BLTC-1^06143014.0241800 | OTHER | HFTD Tier 2 | Distribution | 2023-04-05 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007024 | 86855811-99439-DETAIL-06_26_2024-GO95MLD-1^06244005.0232301 | OTHER | Non-HFTD | Distribution | 2024-06-26 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007025 | 868762424-52560-DETAIL-01_15_2025-BIRDDMG-1^06240004.0098040 | POLE | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007026 | 868928573-33480-DETAIL-02_11_2025-GO95HV-1^06240004.0167406 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007027 | 868928573-33480-DETAIL-04_11_2023-GO95MLD-1^06240004.0167406 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007028 | 868928573-33480-DETAIL-04_11_2023-SVCENTCO-1^06240004.0167406 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007029 | 869057771-51480-DETAIL-02_12_2025-GO95HV-1^06240004.0282900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007030 | 869760041-64899-DETAIL-07_09_2024-GO95MLD-1^06244005.0139300 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007031 | 869760041-64899-DETAIL-07_09_2024-GRDRODHI-1^06244005.0139300 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007032 | 869981596-84270-DETAIL-01_16_2025-GO95HV-1^06239004.0256212 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007033 | 870145359-75759-DETAIL-03_26_2024-GO95MLD-1^06246005.0052400 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007034 | 870207646-28229-DTLSB-08_24_2023-GO95MLD-1^06243009.0119503 | OTHER | Non-HFTD | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007035 | 870584673-73579-DETAIL-06_10_2024-GO95MLD-1^06245007.0346005 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007036 | 871205111-58119-ADMIN-08_05_2020-POLEDERP-1^668005/00 7/084 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007037 | 871562816-89532-DTLSB-05_14_2024-GO95MLD-1^06244001.0331900 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007038 | 871862474-2429-ADMIN-04_21_2023-GO95TCH-1^06143013.0241001 | OTHER | HFTD Tier 2 | Distribution | 2023-04-21 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007039 | 872104921-94020-DETAIL-03_06_2025-GO95HV-1^06240004.0273401 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007040 | 872181114-48169-DETAIL-08_15_2024-GO95HV-1^06246005.0144100 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007041 | 872508531-14439-DETAIL-07_18_2024-GO95HV-1^06244004.0057600 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007042 | 873584294-44132-DETAIL-03_06_2025-ANCHIDLE-1^06241005.0120403 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007043 | 873584294-44132-DETAIL-03_06_2025-GO95HV-1^06241005.0120403 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007044 | 875034205-38439-DETAIL-06_07_2023-GO95HV-1^06244006.0010600 | OTHER | Non-HFTD | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007045 | 875748978-14319-DETAIL-06_28_2022-GO95MLD-1^07116007.0109208 | OTHER | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007046 | 875991492-34492-DETAIL-04_04_2024-GO95MLD-1^06147005.0243100 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007047 | 87604999-35399-DTLTRT-10_25_2022-GO95HV-1^668075/00 11/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007048 | 87604999-35399-DTLTRT-10_25_2022-GO95MLD-1^668075/00 11/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007049 | 876067529-82699-DETAIL-10_27_2022-ABNDEQPM-1^06246009.0241700 | OTHER | HFTD Tier 2 | Distribution | 2022-10-27 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007050 | 876210014-67039-DTLSB-02_08_2024-SVCWIND-1^07216001.0308904 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007051 | 876463416-51443-ADMIN-02_08_2024-CUTOUTAR-1^07216001.0287801 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007052 | 876628774-33489-DETAIL-03_12_2024-GO95MLD-1^06245007.0275509 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007053 | 876752553-5779-DTLSB-02_06_2023-GO95TCH-1^06248001.0262000 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007054 | 876854921-83252-DETAIL-06_15_2023-GO95MLD-1^06244010.0356701 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007055 | 876854921-83252-DETAIL-06_15_2023-GRDRODHI-1^06244010.0356701 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007056 | 876925476-7752-DTLSB-01_30_2023-GO95MLD-1^06248001.0369711 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007057 | 877162284-29759-DETAIL-06_05_2024-GO95MLD-1^06246006.0251900 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007058 | 877427238-85590-AUDIT-03_13_2025-GO95BLTC-1^06239004.0245101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007059 | 877427238-85590-DETAIL-01_28_2025-GO95HV-1^06239004.0245101 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007060 | 877805469-42173-DETAIL-03_08_2023-GO95MLD-1^07117002.0206702 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007061 | 877805469-42173-DETAIL-03_08_2023-GO95TCH-1^07117002.0206702 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007062 | 87788416-60899-DETAIL-06_04_2024-GO95HV-1^06246006.0367001 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007063 | 878216799-59649-DTLSB-04_17_2024-GO95MLD-1^06245007.0224400 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007064 | 878390184-67859-DTLSB-02_06_2024-GO95MLD-1^07216001.0307801 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007065 | 878587248-72259-DTLSB-02_08_2024-SVCROAD-1^07216001.0196001 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007066 | 878717655-51349-DETAIL-03_14_2024-GO95HV-1^06245006.0124900 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007067 | 878717655-51349-DETAIL-03_14_2024-GO95MLD-1^06245006.0124900 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007068 | 879364178-77093-DETAIL-02_23_2023-SVCENTCO-1^07216001.0294643 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007069 | 879419221-80059-DTLSB-02_20_2024-GO95MLD-1^07216001.0260309 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007070 | 879458664-13952-DETAIL-05_14_2024-SVCDEFLC-1^06142012.0122606 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007071 | 879822212-16469-DRONE_HY-09_12_2023-POLETOP-1^668002/00 15/006 | POLE | Non-HFTD | Transmission | 2023-09-12 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007072 | 879873555-77549-DETAIL-05_18_2023-GO95MLD-1^06245005.0159400 | OTHER | Non-HFTD | Distribution | 2023-05-18 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007073 | 880540605-72150-DTLTRT-11_03_2023-GO95HV-1^668010/00 2/037 | OTHER | Non-HFTD | Transmission | 2023-11-03 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007074 | 880717653-93679-DETAIL-01_17_2023-COPLLEAN-1^06148004.0227801 | POLE | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007075 | 880717653-93679-DETAIL-01_17_2023-POLISSUE-1^06148004.0227801 | POLE | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007076 | 880837096-57089-ADMIN-03_06_2025-POLEREPL-1^06247007.0016201 | POLE | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007077 | 881115190-29669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 1/012 | OTHER | HFTD Tier 2 | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007078 | 881270005-76849-DETAIL-02_27_2023-SVCENTCO-1^07216001.0298804 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007079 | 881307419-31359-DETAIL-05_31_2024-GO95HV-1^06246005.0334501 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007080 | 881546123-91041-DETAIL-03_04_2025-GO95BLTC-1^06241005.0130703 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007081 | 881550413-30279-DETAIL-01_18_2023-CONDFRAY-2^06148004.0215002 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007082 | 881550413-30279-DETAIL-01_18_2023-CONDFRAY-3^06148004.0215002 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007083 | 881681581-3562-DTLSB-02_14_2023-GO95MLD-1^06248001.0275001 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007084 | 881847504-20549-AUDIT-03_07_2024-GO95HV-1^07216001.0277804 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007085 | 881946201-18369-DRONE_HY-09_21_2023-GO95HV-1^668002/00 10/069 | OTHER | HFTD Tier 2 | Transmission | 2023-09-21 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007086 | 882247005-329-DTLSB-08_02_2023-GO95MLD-1^06243010.0134100 | OTHER | HFTD Tier 2 | Distribution | 2023-08-02 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007087 | 882410783-62783-DTLSB-02_15_2024-GO95MLD-1^07216001.0264305 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007088 | 88268203-46059-DETAIL-05_29_2024-GO95MLD-1^06246005.0099002 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007089 | 882821149-20129-DTLSB-07_20_2023-GO95MLD-1^06243010.0023401 | OTHER | HFTD Tier 2 | Distribution | 2023-07-20 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007090 | 882821149-20129-DTLSB-07_20_2023-GO95MLD-2^06243010.0023401 | OTHER | HFTD Tier 2 | Distribution | 2023-07-20 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007091 | 883143271-53473-DETAIL-03_02_2023-GO95MLD-1^07117002.0202304 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007092 | 88321874-16639-DTLSB-02_06_2024-GO95MLD-1^07216001.0309806 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007093 | 883600687-86418-DTLSB-02_22_2023-GO95HV-1^07216001.0280704 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007094 | 884213868-42479-DETAIL-04_03_2024-GO95MLD-1^06147005.0227800 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007095 | 884684080-87389-DTLSB-09_03_2024-GO95MLD-1^06245007.0014103 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007096 | 885392458-76443-DTLSB-04_30_2024-SVCDEFLC-1^06245007.0221942 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007097 | 885396288-80619-ADMIN-10_08_2020-POLEDERP-1^668005/00 2/074 | POLE | Non-HFTD | Transmission | 2020-10-08 | 2023-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007098 | 8854370-72839-AUDIT-03_06_2024-GO95TCH-1^07113002.0180103 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007099 | 88547311-9311-DETAIL-03_27_2023-GUYHINS-1^06142016.0051201 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007100 | 885532885-40449-DETAIL-02_28_2024-POLISSUE-1^07113002.0181700 | POLE | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007101 | 885940388-62940-DETAIL-03_12_2025-GO95HV-1^06239003.0132101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007102 | 886041989-30959-DETAIL-10_14_2024-GO95MLD-1^07216001.0204341 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007103 | 886121016-48149-DETAIL-03_06_2023-GO95MLD-1^07216001.0297510 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007104 | 886204799-74439-DETAIL-02_27_2024-GO95MLD-1^07113002.0184103 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007105 | 886204799-74439-DETAIL-02_27_2024-GRDRODHI-1^07113002.0184103 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007106 | 886650599-34529-DETAIL-05_09_2024-GO95MLD-1^06142012.0121308 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007107 | 88670411-8119-ADMIN-08_05_2020-POLEDERP-1^668005/00 6A/084 | POLE | Non-HFTD | Transmission | 2020-08-05 | 2023-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007108 | 886881624-33624-DETAIL-04_25_2024-GO95HV-1^06142016.0160800 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007109 | 886999211-10320-DETAIL-03_08_2023-GO95MLD-1^07117002.0210206 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007110 | 88713355-76451-DETAIL-11_15_2022-GO95MLD-1^06239004.0366601 | OTHER | HFTD Tier 2 | Distribution | 2022-11-15 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007111 | 887194521-83282-DETAIL-02_23_2023-GO95TCH-1^07216001.0298903 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007112 | 887327363-4322-DETAIL-07_09_2024-SVCROAD-1^06244005.0260902 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007113 | 887513435-20240-DETAIL-02_24_2025-SVCDEFLC-1^06240004.0152803 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007114 | 887549941-3880-DETAIL-03_19_2025-GO95HV-1^06239001.0065601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007115 | 887585549-91230-DETAIL-02_06_2025-GO95HV-1^06240004.0164303 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007116 | 887587678-89789-DETAIL-05_22_2023-GO95MLD-1^06245005.0274102 | OTHER | Non-HFTD | Distribution | 2023-05-22 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007117 | 887712586-79249-DETAIL-10_10_2024-GO95MLD-1^07216001.0204004 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007118 | 888055394-16582-DETAIL-10_24_2024-POLISSUE-1^07216001.0209908 | POLE | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007119 | 888304764-24269-DTLTRT-10_11_2023-GO95MLD-1^668010/00 3/040 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007120 | 88859944-53044-DETAIL-03_14_2023-GUYHINS-1^07114001.0275400 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007121 | 889134000-17369-DTLTRT-06_15_2021-GO95HV-1^668041/00 21/022 | OTHER | Non-HFTD | Transmission | 2021-06-15 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007122 | 889155403-78182-DTLSB-05_28_2024-GO95MLD-1^06243001.0126302 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007123 | 889172731-82339-DETAIL-02_28_2024-GO95HV-1^07113001.0030402 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007124 | 889172731-82339-DETAIL-02_28_2024-GO95MLD-1^07113001.0030402 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007125 | 889288240-709-DETAIL-10_27_2022-GO95HV-1^06246008.0050704 | OTHER | HFTD Tier 2 | Distribution | 2022-10-27 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007126 | 889432605-38279-DETAIL-01_24_2023-GO95MLD-1^06148004.0182103 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007127 | 889466642-11288-DETAIL-07_05_2023-GO95MLD-1^06244009.0132000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007128 | 88979726-52079-ADMIN-04_04_2024-ABNDEQPM-1^06147005.0238102 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007129 | 88979726-52079-DETAIL-04_04_2024-GUYHINS-1^06147005.0238102 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007130 | 89007529-40049-DETAIL-10_09_2024-CLMBTRE-1^07216001.0201105 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007131 | 890117911-36059-DTLSB-02_19_2024-GO95MLD-1^07216001.0260205 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007132 | 890228423-29499-DETAIL-07_10_2024-GO95MLD-1^06244005.0271902 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007133 | 890239043-81489-DETAIL-06_27_2023-GO95HV-1^06243009.0032800 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007134 | 890239043-81489-DETAIL-06_27_2023-GO95MLD-1^06243009.0032800 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007135 | 890239043-81489-DETAIL-06_27_2023-GRDRODHI-1^06243009.0032800 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007136 | 89028965-52349-DETAIL-03_14_2024-GO95HV-1^06245006.0123900 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007137 | 890408721-65399-DETAIL-06_19_2023-GRDRODHI-1^06244010.0264501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-19 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007138 | 890532756-54639-DETAIL-10_24_2024-CLRTOPOL-1^07216001.0204502 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007139 | 890532756-54639-DETAIL-10_24_2024-GO95MLD-1^07216001.0204502 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007140 | 89054385-30879-DETAIL-04_01_2024-GO95MLD-1^06147005.0127601 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007141 | 89054385-30879-DETAIL-04_01_2024-GRDRODHI-1^06147005.0127601 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007142 | 890583928-68203-DETAIL-03_07_2023-GO95MLD-1^07216001.0294544 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007143 | 890862438-3688-DTLTRT-06_08_2021-GO95HV-1^668041/00 7/013 | OTHER | Non-HFTD | Transmission | 2021-06-08 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007144 | 890878505-51349-DETAIL-02_23_2023-ABNDEQPM-1^07216001.0298906 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007145 | 890976109-63973-DETAIL-03_08_2023-GO95MLD-1^07117002.0207803 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007146 | 891266669-20790-DETAIL-02_03_2025-GO95HV-1^06239004.0133041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007147 | 891266669-20790-DETAIL-02_03_2025-SVCDEFLC-1^06239004.0133041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007148 | 891682866-18069-DTLTRT-10_12_2023-GO95MLD-1^668010/00 16/041 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007149 | 891853374-5779-DETAIL-04_22_2024-GO95MLD-1^06145001.0149703 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007150 | 892121373-76092-DTLSB-02_05_2024-GO95HV-1^07216001.0185000 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007151 | 892629604-11199-DETAIL-08_05_2024-GO95MLD-1^06244005.0324701 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007152 | 892973804-22622-DETAIL-07_13_2023-GO95MLD-1^06244008.0337901 | OTHER | HFTD Tier 2 | Distribution | 2023-07-13 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007153 | 893010450-4930-DTLTRT-11_03_2023-GO95HV-1^668010/00 13/027 | OTHER | HFTD Tier 2 | Transmission | 2023-11-03 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007154 | 893053737-56979-DETAIL-07_02_2024-SVCWIND-1^06245006.0088801 | OTHER | Non-HFTD | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007155 | 893071810-92939-DTLSB-02_20_2024-GO95TCH-1^07216001.0263308 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007156 | 893683283-89749-DETAIL-08_13_2024-GUYLOINS-1^06245005.0368400 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-13 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007157 | 893868214-92050-DTLTRT-11_03_2023-BIRDDMG-1^668010/00 11/036 | POLE | HFTD Tier 2 | Transmission | 2023-11-03 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007158 | 894104475-56402-DETAIL-05_08_2024-GO95HV-1^06142012.0120105 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007159 | 894125789-14249-DTLSB-02_15_2024-GO95MLD-1^07216001.0260001 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007160 | 894207038-41202-DETAIL-04_10_2024-GO95MLD-1^06245002.0113300 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007161 | 8948796-20689-DETAIL-02_02_2023-GO95CL10-1^06147002.0172800 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007162 | 8948796-20689-DETAIL-02_02_2023-GO95MLD-1^06147002.0172800 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007163 | 895347715-62833-DETAIL-03_01_2023-GO95MLD-1^07117002.0197300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007164 | 895347715-62833-DETAIL-03_01_2023-RISESTRP-1^07117002.0197300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007165 | 895491413-58189-DETAIL-07_03_2024-GO95HV-1^06244005.0231900 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007166 | 895660527-43527-DETAIL-03_06_2025-GO95BLTC-1^06241005.0163902 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007167 | 895700534-78534-DETAIL-03_29_2023-GO95MLD-1^06142016.0085402 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007168 | 895772611-28212-DETAIL-04_18_2024-GO95TCH-1^06145001.0149700 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007169 | 895889007-38138-DETAIL-03_05_2025-ABNDEQPM-1^06241005.0121302 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007170 | 896026976-29080-DETAIL-03_03_2025-SVCDEFLC-1^06240004.0051000 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007171 | 896378479-29112-DETAIL-10_09_2024-SVCENTBK-1^07216001.0200240 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007172 | 896617526-63961-DETAIL-02_19_2025-GO95TCH-1^06239004.0365700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007173 | 896863926-62549-DETAIL-10_17_2024-GO95MLD-1^07216001.0204407 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007174 | 896863926-62549-DETAIL-10_17_2024-GO95TCH-1^07216001.0204407 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007175 | 897080301-6720-DETAIL-03_08_2023-GO95MLD-1^07117002.0211104 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007176 | 897080301-6720-DETAIL-03_08_2023-SVCNEUT-1^07117002.0211104 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007177 | 897082444-58149-DTLSB-02_26_2024-SVCROAD-1^07216001.0277806 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007178 | 897346541-71099-DETAIL-11_10_2022-GO95HV-1^06246008.0058300 | OTHER | HFTD Tier 2 | Distribution | 2022-11-10 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007179 | 897376306-77123-DTLSB-04_23_2024-GO95MLD-1^06245007.0223542 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007180 | 89768268-88439-DETAIL-10_09_2024-GO95MLD-1^07216001.0203104 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007181 | 89768268-88439-DETAIL-10_09_2024-GO95TCH-1^07216001.0203104 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007182 | 897897801-34199-DTLSB-02_20_2023-GO95HV-1^06248001.0286600 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007183 | 898220994-74860-DETAIL-01_23_2025-SVCDEFLC-1^06239004.0257610 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007184 | 898358359-46659-DETAIL-03_28_2024-GO95HV-1^06246005.0044700 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007185 | 898677329-19122-DETAIL-01_25_2023-ABNDEQPM-1^06147003.0023901 | OTHER | Non-HFTD | Distribution | 2023-01-25 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007186 | 898677329-19122-DETAIL-01_25_2023-GO95MLD-1^06147003.0023901 | OTHER | Non-HFTD | Distribution | 2023-01-25 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007187 | 899329168-79922-DETAIL-03_20_2024-GO95HV-1^06245002.0124400 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007188 | 899755936-76449-DETAIL-10_24_2024-GUYLOINS-1^07216001.0200308 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007189 | 899823993-98469-DRONE_HY-09_12_2023-XARMBRAC-1^668002/00 8/007 | CROSSARM | Non-HFTD | Transmission | 2023-09-12 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007190 | 899895947-64949-DETAIL-03_15_2023-GO95HV-1^07114001.0342802 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007191 | 900053265-41301-DTLTRT-04_17_2024-GO95HV-1^668067/00 8/016 | OTHER | Non-HFTD | Transmission | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007192 | 900054117-90089-DTLSB-10_07_2024-GO95HV-1^06245006.0332201 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007193 | 90050600-38839-DTLTRT-02_15_2024-SVCROAD-1^07216001.0264101 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007194 | 900920211-24580-DETAIL-02_13_2025-SVCDEFLC-1^06240004.0169040 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007195 | 90122503-80539-DETAIL-06_24_2024-GO95MLD-1^06244005.0232200 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007196 | 901429295-70395-DETAIL-01_30_2023-GO95MLD-1^06148003.0223400 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007197 | 901582313-749-DETAIL-03_16_2023-ABNDEQPM-1^07113001.0059502 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007198 | 901594903-59529-DTLSB-08_31_2023-GO95HV-1^06243007.0320400 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007199 | 901689719-66953-DTLSB-04_16_2024-SVCWIND-1^06245007.0225343 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007200 | 901844191-77942-DETAIL-06_08_2023-GO95HV-1^06244009.0296400 | OTHER | HFTD Tier 2 | Distribution | 2023-06-08 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007201 | 901856631-2380-DETAIL-02_20_2025-GUYHINS-1^06240004.0316702 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-20 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007202 | 902343143-19539-DETAIL-07_03_2024-GO95MLD-1^06244005.0230900 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007203 | 90291459-6170-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 4/063 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007204 | 903121578-18229-DETAIL-06_28_2023-GO95HV-1^06244009.0367700 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007205 | 903140488-44442-DETAIL-05_02_2024-GO95MLD-1^06142012.0125108 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007206 | 903161323-72729-DETAIL-05_14_2024-GO95MLD-1^06142012.0122604 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007207 | 903423561-61119-DTLTRT-08_04_2022-GUYHINS-1^668005/00 12/082 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-04 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007208 | 903964079-73979-DTLTRT-10_30_2023-GO95HV-1^668010/00 21/013 | OTHER | HFTD Tier 2 | Transmission | 2023-10-30 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007209 | 904127249-76390-DETAIL-01_14_2025-GO95MLD-2^06239004.0255003 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007210 | 904218243-89842-DETAIL-05_16_2024-GO95MLD-1^06142012.0120702 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007211 | 904356643-41929-DETAIL-05_14_2024-GO95MLD-1^06142012.0122601 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007212 | 904624980-17409-DTLSB-09_03_2024-GO95HV-1^06245007.0013100 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007213 | 904663135-151-DETAIL-02_18_2025-SVCROAD-1^06239004.0365908 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007214 | 905081371-22252-DTLSB-02_16_2023-GO95MLD-1^06248001.0197000 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007215 | 90526543-8120-DTLSB-05_23_2024-GO95MLD-1^06243001.0149001 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007216 | 906226042-26450-DETAIL-02_06_2025-BIRDDMG-1^06239004.0136210 | POLE | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007217 | 906339066-70249-DETAIL-10_09_2024-GO95HV-1^07216001.0202100 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007218 | 906521046-10179-DETAIL-04_02_2024-GO95TCH-1^06147005.0132200 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007219 | 906562258-79952-AUDIT-04_02_2024-SVCROAD-1^06245002.0037901 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007220 | 906562258-79952-DETAIL-03_18_2024-GO95MLD-1^06245002.0037901 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007221 | 906762845-12459-DETAIL-04_01_2024-GO95MLD-1^06247005.0346740 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007222 | 906887658-82399-DTLSB-10_07_2024-GO95MLD-1^06245006.0170401 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007223 | 906983053-12629-DETAIL-05_15_2024-GO95MLD-1^06142012.0124900 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007224 | 907037805-37241-DETAIL-05_09_2022-SVCROOF-1^06241005.0011707 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007225 | 907153980-49432-DETAIL-06_15_2023-GO95HV-1^06244009.0336102 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007226 | 907159768-1439-DTLSB-02_19_2024-GO95MLD-1^07216001.0264800 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007227 | 907234131-61763-DTLSB-04_22_2024-SVCWIND-1^06245007.0225242 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007228 | 907249969-41259-DETAIL-10_14_2024-GO95MLD-1^07216001.0200311 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007229 | 907479025-34162-DTLSB-02_01_2023-GO95HV-1^06248001.0369201 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007230 | 907647633-21692-DRONE_HY-09_27_2023-GO95HV-1^668033/00 7X1/003 | OTHER | Non-HFTD | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007231 | 908430639-80269-DTLTRT-07_05_2022-GO95HV-1^668005/00 16/033 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007232 | 908615521-39359-DETAIL-07_01_2024-BIRDDMG-1^06245007.0305701 | POLE | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007233 | 908881874-5939-AUDIT-02_27_2024-GO95MLD-1^07216001.0199001 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007234 | 908881874-5939-DTLSB-02_07_2024-GO95CL10-1^07216001.0199001 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007235 | 909188009-19409-DTLSB-09_03_2024-GO95MLD-1^06245007.0016300 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007236 | 909303081-63320-DETAIL-02_17_2025-GO95TCH-1^06240004.0279501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007237 | 909303081-63320-DETAIL-02_17_2025-GUYHINS-1^06240004.0279501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007238 | 909309589-53789-DETAIL-03_14_2024-GO95MLD-1^06245005.0062503 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007239 | 909406561-66248-DTLSB-02_08_2024-SVCWIND-1^07216001.0307905 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007240 | 90946875-39875-DETAIL-01_29_2025-GO95HV-1^06240004.0176803 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007241 | 909607020-5659-DETAIL-06_17_2024-GO95MLD-1^06246006.0132400 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007242 | 909674534-80159-DTLSB-02_05_2024-GO95HV-1^07216002.0249903 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007243 | 909674534-80159-DTLSB-02_05_2024-GO95MLD-1^07216002.0249903 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007244 | 909922129-46213-DETAIL-07_29_2024-GO95MLD-1^06245006.0148741 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007245 | 909922129-46213-DETAIL-07_29_2024-GRDRODHI-1^06245006.0148741 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007246 | 909973055-91319-DETAIL-10_24_2022-GO95HV-1^06247008.0303400 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007247 | 910099054-35393-DETAIL-02_23_2023-GO95MLD-1^07216001.0297907 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007248 | 910207911-91469-DETAIL-02_23_2023-GO95HV-1^668002/00 12/030 | OTHER | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007249 | 910328546-30289-DETAIL-08_19_2024-GO95MLD-1^06246004.0322700 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007250 | 910378506-92370-DETAIL-01_22_2025-GO95HV-1^06239004.0254402 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007251 | 910483224-57472-DETAIL-03_08_2023-GO95TCH-1^07216001.0296543 | OTHER | Non-HFTD | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007252 | 910548734-58153-ADMIN-04_21_2023-GO95TCH-1^06142016.0085701 | OTHER | Non-HFTD | Distribution | 2023-04-21 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007253 | 910602041-92880-DETAIL-03_19_2025-GO95HV-1^06239001.0064600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007254 | 910672595-25489-DETAIL-06_11_2024-GO95HV-1^06245007.0345701 | OTHER | Non-HFTD | Distribution | 2024-06-11 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007255 | 911087461-86879-DETAIL-01_24_2023-GO95MLD-1^06148004.0182200 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007256 | 911087461-86879-DETAIL-01_24_2023-GO95TCH-1^06148004.0182200 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007257 | 911220411-68599-DTLSB-08_27_2024-GO95HV-1^06245007.0113900 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007258 | 911575733-68772-DETAIL-10_16_2024-SVCENTCO-1^07216001.0206841 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007259 | 911681599-4182-DTLSB-05_20_2024-GO95HV-1^06244003.0227000 | OTHER | Non-HFTD | Distribution | 2024-05-20 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007260 | 911878464-22282-DETAIL-10_22_2024-SVCNEUT-1^07216001.0209711 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007261 | 911940904-87659-DETAIL-05_16_2022-GO95MLD-1^07117001.0313800 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007262 | 912278029-39389-ADMIN-05_20_2024-COPLLEAN-1^06148001.0253200 | POLE | Non-HFTD | Distribution | 2024-05-20 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007263 | 912987684-5549-DTLSB-02_07_2024-GUYHINS-1^07216001.0199403 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007264 | 913056914-95782-DTLSB-05_08_2024-GO95MLD-1^06245001.0332801 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007265 | 913189599-56849-DETAIL-02_16_2024-GUYHINS-1^07216001.0260104 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007266 | 913484918-13209-DETAIL-03_04_2024-GO95HV-1^06147004.0010500 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007267 | 913490657-75849-DETAIL-03_15_2023-GO95HV-1^07114001.0347202 | OTHER | HFTD Tier 2 | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007268 | 913892371-32349-DETAIL-02_26_2024-GO95MLD-1^07113001.0138405 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007269 | 913962186-79339-DETAIL-10_08_2024-GUYLOINS-1^07216001.0203004 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007270 | 913966506-66779-DETAIL-04_08_2024-GO95HV-1^06147005.0245100 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007271 | 914343688-17592-DETAIL-04_23_2024-GO95BLTC-1^06145001.0026304 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007272 | 914343688-17592-DETAIL-04_23_2024-GO95MLD-1^06145001.0026304 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007273 | 914562013-94959-DETAIL-06_06_2024-GO95MLD-1^06246006.0351401 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007274 | 914656193-22741-DETAIL-05_11_2022-GO95MLD-1^06241005.0132804 | OTHER | HFTD Tier 2 | Distribution | 2022-05-11 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007275 | 914749811-71680-DETAIL-02_27_2025-BIRDDMG-1^06240004.0139300 | POLE | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007276 | 914749811-71680-DETAIL-02_27_2025-GO95HV-1^06240004.0139300 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007277 | 914849439-42359-DETAIL-05_30_2024-GO95MLD-1^06246005.0273100 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007278 | 915141841-13120-DETAIL-03_06_2025-ABNDEQPM-1^06240004.0272503 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007279 | 915228226-81481-DETAIL-02_24_2025-BIRDDMG-1^06239004.0366840 | POLE | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007280 | 915613571-98192-AUDIT-04_15_2024-SVCROAD-1^06147004.0070100 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007281 | 915749884-21984-DETAIL-03_14_2023-GO95HV-1^07114001.0281201 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007282 | 915963620-6001-DETAIL-01_31_2025-GO95HV-1^06239004.0136109 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007283 | 916078788-67949-DETAIL-08_14_2024-GO95HV-1^06245005.0344900 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007284 | 91662835-32059-DETAIL-06_10_2024-GO95MLD-1^06245007.0349603 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007285 | 916789955-10055-DETAIL-03_24_2025-GO95HV-1^06238004.0029606 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007286 | 916899648-50939-DTLSB-02_13_2024-GO95MLD-1^07216001.0187103 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007287 | 917110323-14749-DETAIL-02_29_2024-GO95MLD-1^07113001.0107101 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007288 | 917134013-63559-DETAIL-04_04_2024-GO95HV-1^06247005.0298200 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007289 | 917198162-44989-DTLSB-08_30_2023-GO95MLD-1^06243008.0207900 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007290 | 91726251-18169-DETAIL-06_05_2024-GO95MLD-1^06246006.0264800 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007291 | 91726251-18169-DETAIL-06_05_2024-GRDRODHI-1^06246006.0264800 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007292 | 91726933-35779-DTLTRT-10_19_2023-GO95HV-1^668010/00 10/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007293 | 91726933-35779-DTLTRT-10_19_2023-GO95MLD-1^668010/00 10/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007294 | 917854253-14729-DETAIL-05_14_2024-GO95MLD-1^06142012.0122504 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007295 | 918451009-83069-DTLTRT-06_14_2021-GO95HV-1^668041/00 9/020 | OTHER | Non-HFTD | Transmission | 2021-06-14 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007296 | 918783825-56351-DETAIL-02_24_2025-GO95MLD-1^06239004.0366901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007297 | 918863281-44780-DETAIL-02_13_2025-GO95HV-1^06240004.0169143 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007298 | 919057950-49009-DETAIL-03_11_2024-GO95MLD-1^06147004.0028905 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007299 | 919162964-14964-DETAIL-04_29_2024-GO95HV-1^06142016.0175300 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007300 | 919346845-3112-DTLSB-05_08_2024-GO95HV-1^06245001.0299100 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007301 | 919346845-3112-DTLSB-05_08_2024-GO95MLD-1^06245001.0299100 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007302 | 919610779-98712-DETAIL-04_22_2024-GO95MLD-1^06145001.0029302 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007303 | 919740296-22296-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0030403 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007304 | 919750699-25589-DETAIL-01_30_2023-CONDFRAY-1^06148003.0295601 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007305 | 920187338-91312-DTLSB-01_26_2023-GUYSLACK-1^06247001.0017905 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007306 | 920301819-29612-DETAIL-01_24_2023-GO95MLD-1^06148003.0368901 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007307 | 920908134-21303-DETAIL-08_15_2024-GO95HV-1^06246005.0138041 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007308 | 922002681-68822-DETAIL-04_15_2024-GO95MLD-1^06145001.0136200 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007309 | 922220703-80139-DETAIL-07_31_2024-GUYHINS-1^06244005.0346902 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007310 | 922310760-23829-DETAIL-05_14_2024-GO95MLD-1^06142012.0122409 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007311 | 922358704-39022-DETAIL-10_16_2024-GO95MLD-1^07216001.0206802 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007312 | 922394063-86222-DTLSB-05_23_2024-GO95MLD-1^06243001.0123000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007313 | 922597919-14559-DTLSB-02_16_2024-GO95MLD-1^07216001.0262007 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007314 | 922908111-28030-DTLTRT-10_05_2023-GO95MLD-1^668010/00 18/027 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007315 | 923294513-25532-DETAIL-03_14_2024-GO95HV-1^06147004.0301700 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007316 | 923302716-42793-DTLSB-09_30_2024-GO95MLD-1^06245007.0232404 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007317 | 923432973-58779-DTLSB-02_02_2023-GO95MLD-1^06248001.0268000 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007318 | 923478989-84199-DETAIL-04_01_2024-GUYHINS-1^06147005.0107700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007319 | 923569928-58332-DETAIL-04_23_2024-GO95MLD-1^06145001.0023100 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007320 | 923690579-9839-DTLSB-02_16_2024-GO95HV-1^07216001.0262000 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007321 | 923726611-58611-DETAIL-04_30_2024-GO95HV-1^06142015.0028902 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007322 | 923766926-22370-DETAIL-01_14_2025-GO95HV-1^06239004.0256111 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007323 | 923964463-82439-DETAIL-10_10_2024-CLMBTRE-1^07216001.0207101 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007324 | 924391436-16939-DETAIL-02_27_2023-GO95HV-1^07216001.0297800 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007325 | 924391436-16939-DETAIL-02_27_2023-GO95MLD-1^07216001.0297800 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007326 | 924475863-6059-DETAIL-05_30_2024-GO95MLD-1^06246005.0150900 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007327 | 924504871-88070-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 2/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007328 | 924628801-97670-DTLTRT-10_16_2023-GO95MLD-1^668010/00 17X/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007329 | 924861285-22600-DETAIL-03_13_2025-GO95HV-1^06239003.0243000 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007330 | 9251171-2009-DTLSB-04_23_2024-GO95MLD-1^06245007.0225703 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007331 | 925143064-580-DTLTRT-09_27_2023-GO95MLD-1^668010/00 16X/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007332 | 925984023-39639-DETAIL-10_10_2024-GO95CL10-1^07216001.0205203 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007333 | 926340013-77642-DTLSB-05_23_2024-GO95MLD-1^06243001.0149700 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007334 | 927089198-25242-DTLSB-05_09_2024-GO95MLD-1^06244001.0224501 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007335 | 927266724-59759-DTLSB-02_13_2024-GO95HV-1^07216001.0186400 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007336 | 927266724-59759-DTLSB-02_13_2024-GO95MLD-1^07216001.0186400 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007337 | 927487811-27233-DETAIL-09_17_2024-SVCDEFLC-1^06240004.0079740 | OTHER | HFTD Tier 2 | Distribution | 2024-09-17 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007338 | 927566306-25339-DETAIL-10_14_2024-GO95MLD-1^07216001.0202300 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007339 | 927633057-63057-DETAIL-02_15_2023-GO95MLD-1^06247002.0232702 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007340 | 927962835-70639-DETAIL-10_08_2024-GUYHINS-1^07216001.0200003 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007341 | 928190775-58352-DETAIL-10_25_2024-GO95MLD-1^07216001.0207702 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007342 | 928729426-60849-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299701 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007343 | 928729426-60849-DETAIL-02_28_2023-GO95MLD-1^07216001.0299701 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007344 | 928899896-9979-DETAIL-10_24_2022-GO95MLD-1^06247009.0247500 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007345 | 928986915-27933-DETAIL-06_10_2024-RISEGRD-1^06245007.0346702 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007346 | 929033032-29589-DTLSB-08_24_2023-GO95MLD-1^06243008.0174901 | OTHER | HFTD Tier 2 | Distribution | 2023-08-24 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007347 | 93022255-24859-DETAIL-10_24_2024-GO95MLD-1^07216001.0201504 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007348 | 930275890-98632-DETAIL-06_15_2023-GO95MLD-1^06244009.0339100 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007349 | 930657093-17562-DETAIL-10_16_2024-GO95MLD-1^07216001.0206840 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007350 | 930762403-53729-DETAIL-03_06_2017-SVCWIND-1^06142012.0130611 | OTHER | Non-HFTD | Distribution | 2017-03-06 | 2020-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007351 | 930788530-47772-DTLSB-07_17_2023-GO95HV-1^06243010.0118200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007352 | 930788530-47772-DTLSB-07_17_2023-GO95MLD-1^06243010.0118200 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007353 | 930839338-94243-DTLSB-04_30_2024-GO95STUB-1^06245007.0220840 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007354 | 930992555-78310-DETAIL-03_12_2025-GO95HV-1^06238004.0223801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007355 | 931107092-96370-DETAIL-01_27_2025-SVCDEFLC-1^06240004.0085303 | OTHER | HFTD Tier 2 | Distribution | 2025-01-27 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007356 | 931120321-1321-DETAIL-07_15_2024-GO95HV-1^06244005.0250500 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007357 | 931637268-27443-DTLSB-04_30_2024-GO95MLD-1^06245007.0222849 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007358 | 931665989-49189-DETAIL-07_08_2024-GO95HV-1^06244005.0137700 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007359 | 931839514-93259-DETAIL-05_16_2022-GO95TCH-1^07117001.0316800 | OTHER | HFTD Tier 2 | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007360 | 931883049-98759-DETAIL-03_01_2023-SVCENTCO-1^07216001.0290743 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007361 | 931890384-73753-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007362 | 931890384-9560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007363 | 931986373-60799-DETAIL-06_10_2024-GO95MLD-1^06245007.0348003 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007364 | 932016692-15080-DETAIL-02_25_2025-SVCNEUT-1^06240005.0015001 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007365 | 932180009-6220-DETAIL-01_28_2025-GO95HV-1^06240004.0085042 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007366 | 932343232-25959-DETAIL-05_29_2024-GO95MLD-1^06246005.0178000 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007367 | 932452199-32389-ADMIN-01_30_2025-POLEREPL-1^06245007.0031300 | POLE | HFTD Tier 2 | Distribution | 2025-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007368 | 932526561-82531-DETAIL-05_30_2023-GRDRODHI-1^06243009.0027900 | OTHER | Non-HFTD | Distribution | 2023-05-30 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007369 | 932863114-46114-DETAIL-04_25_2024-GO95HV-1^06142016.0177900 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007370 | 933076134-10334-DETAIL-04_09_2024-GO95MLD-1^06147005.0219520 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007371 | 93311703-46830-DTLSB-05_22_2024-GO95MLD-1^06243001.0112100 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007372 | 93355921-71449-DETAIL-04_24_2024-SVCROAD-1^06245007.0225604 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007373 | 93355921-71449-DETAIL-04_24_2024-SVCROAD-2^06245007.0225604 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007374 | 933636913-42753-DETAIL-06_07_2023-SVCROAD-1^06244010.0275600 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007375 | 933718221-64333-ADMIN-11_14_2024-POLEDERP-1^07219001.0324301 | POLE | Non-HFTD | Distribution | 2024-11-14 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007376 | 934448852-51929-DTLSB-08_30_2023-GO95STUB-1^06243008.0176400 | OTHER | HFTD Tier 2 | Distribution | 2023-08-30 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007377 | 934466507-28490-DETAIL-02_03_2025-SVCDEFLC-1^06239004.0244941 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007378 | 934699873-5313-DTLSB-04_25_2024-SVCWIND-1^06245007.0228547 | OTHER | HFTD Tier 2 | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007379 | 934862871-64871-DETAIL-04_30_2024-GO95HV-1^06142015.0037900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007380 | 934898711-45750-DETAIL-03_24_2025-GO95TCH-1^06238004.0027700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007381 | 935062541-57109-DTLSB-08_26_2024-GO95MLD-1^06245007.0114305 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007382 | 935250260-52799-DETAIL-08_12_2024-GO95MLD-1^06245006.0102400 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007383 | 935294178-30249-DETAIL-10_09_2024-GO95MLD-1^07216001.0203102 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007384 | 935309799-95482-DTLSB-05_16_2024-GO95HV-1^06244003.0249200 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007385 | 935527576-84309-DETAIL-04_08_2024-GO95MLD-1^06147005.0234005 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007386 | 935588076-82299-AUDIT-09_03_2024-ABNDEQPM-1^06246004.0321501 | OTHER | Non-HFTD | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007387 | 936447263-62151-DETAIL-05_11_2022-GO95MLD-1^06241005.0131903 | OTHER | HFTD Tier 2 | Distribution | 2022-05-11 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007388 | 936510216-32980-DETAIL-02_27_2025-GO95HV-1^06240004.0050142 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007389 | 936510216-32980-DETAIL-02_27_2025-SVCDEFLC-1^06240004.0050142 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007390 | 936554034-25982-DETAIL-10_25_2024-SVCENTCO-1^07216001.0209905 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007391 | 937149279-5089-DETAIL-03_14_2024-GO95MLD-1^06245005.0062400 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007392 | 937237374-25259-DTLSB-02_07_2024-SVCRUBLG-1^07216001.0199203 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007393 | 937413341-98689-ADMIN-10_10_2024-POLEREPL-1^06146002.0034500 | POLE | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007394 | 937417383-22492-DETAIL-04_04_2023-GO95HV-1^06143014.0225800 | OTHER | HFTD Tier 2 | Distribution | 2023-04-04 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007395 | 937422088-32449-DETAIL-10_09_2024-GO95CL10-1^07216001.0204100 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007396 | 937460088-81709-DETAIL-03_28_2024-GO95HV-1^06147005.0117100 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007397 | 937461265-87032-DETAIL-07_07_2023-GO95MLD-1^06244008.0336100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007398 | 937515373-44251-ADMIN-08_05_2024-GO95STUB-1^06242004.0310700 | OTHER | HFTD Tier 2 | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007399 | 937593714-77714-DTLSB-01_30_2023-GO95TCH-1^06248001.0259201 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007400 | 937784506-80460-DTLTRT-10_12_2023-GO95HV-1^668010/00 10/041 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007401 | 937804212-71550-DETAIL-03_19_2025-CONDCOIL-1^06238004.0026203 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007402 | 938176180-27332-DETAIL-06_15_2023-GO95MLD-1^06244009.0336100 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007403 | 938202599-98589-DETAIL-05_31_2024-GO95MLD-1^06246005.0333301 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007404 | 938281254-92254-DETAIL-01_19_2023-GO95MLD-1^06148004.0210901 | OTHER | Non-HFTD | Distribution | 2023-01-19 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007405 | 938300510-13313-DTLSB-10_01_2024-GO95MLD-1^06245007.0230343 | OTHER | Non-HFTD | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007406 | 938362990-99270-DETAIL-04_12_2023-GO95BLTC-1^06240004.0166511 | OTHER | HFTD Tier 2 | Distribution | 2023-04-12 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007407 | 938572612-37731-DETAIL-02_27_2025-GO95MLD-1^06241005.0175601 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007408 | 939573607-98349-DETAIL-03_13_2023-GO95HV-1^07216001.0294405 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007409 | 939637863-88339-DETAIL-06_25_2024-GO95HV-1^06244005.0235603 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007410 | 939947713-7679-DETAIL-03_05_2025-GO95HV-1^06241005.0131802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007411 | 94019936-18570-DETAIL-01_24_2025-GO95HV-1^06239004.0257842 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007412 | 940248246-78663-DETAIL-03_28_2024-GO95HV-1^06247005.0331502 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007413 | 940248246-78663-DETAIL-03_28_2024-GO95MLD-1^06247005.0331502 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007414 | 940636816-75509-DETAIL-11_02_2022-GO95HV-1^06246008.0024401 | OTHER | HFTD Tier 2 | Distribution | 2022-11-02 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007415 | 94077648-25859-DETAIL-04_03_2024-GO95HV-1^06246005.0074400 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007416 | 94077648-25859-DETAIL-04_03_2024-GO95MLD-1^06246005.0074400 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007417 | 940875528-30389-DTLSB-10_03_2024-RISEBKSP-1^06245006.0333800 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007418 | 941332443-69503-DETAIL-02_22_2023-GO95HV-1^06247002.0031800 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007419 | 941404691-32330-DETAIL-01_29_2025-BIRDDMG-1^06240004.0176802 | POLE | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007420 | 942001116-52279-DRONE_HY-09_26_2023-GO95HV-1^668033/00 9/002 | OTHER | HFTD Tier 2 | Transmission | 2023-09-26 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007421 | 942074336-25103-DTLSB-01_30_2023-GO95MLD-1^06248001.0369802 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007422 | 942133444-93549-DETAIL-04_18_2023-GO95MLD-1^06245006.0259900 | OTHER | Non-HFTD | Distribution | 2023-04-18 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007423 | 942193888-82403-DETAIL-04_02_2024-GO95MLD-1^06147005.0092200 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007424 | 942193888-82403-DETAIL-04_02_2024-GO95TCH-1^06147005.0092200 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007425 | 942581718-84003-DETAIL-03_19_2024-CONDCOIL-1^06245002.0015600 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007426 | 94262081-379-DETAIL-01_24_2023-GO95MLD-1^06148004.0182000 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007427 | 943035438-37163-DETAIL-01_21_2025-BIRDDMG-1^06240004.0093201 | POLE | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007428 | 943049703-32480-DETAIL-03_04_2025-GO95TCH-1^06240004.0150500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007429 | 943079326-48619-DETAIL-08_11_2019-POLEDERP-1^668005/00 4/097 | POLE | Non-HFTD | Transmission | 2019-08-11 | 2022-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007430 | 943169156-28129-DETAIL-07_06_2023-GO95MLD-1^06244008.0329902 | OTHER | HFTD Tier 2 | Distribution | 2023-07-06 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007431 | 943334001-34829-DETAIL-05_06_2024-GO95HV-1^06142012.0122103 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007432 | 943334001-34829-DETAIL-05_06_2024-GO95MLD-1^06142012.0122103 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007433 | 943391628-88799-DETAIL-03_28_2024-GO95MLD-1^06147005.0156900 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007434 | 943405444-74574-DETAIL-03_07_2024-GO95MLD-1^06147004.0017600 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007435 | 94355955-58439-DETAIL-06_26_2024-GO95MLD-1^06244005.0232542 | OTHER | Non-HFTD | Distribution | 2024-06-26 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007436 | 943958774-60613-DETAIL-04_18_2024-GO95MLD-1^06145001.0148700 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007437 | 944017423-72613-DETAIL-02_08_2023-GO95MLD-1^06146004.0081001 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007438 | 944363512-93389-DETAIL-02_27_2023-GO95HV-1^07216001.0298801 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007439 | 944538756-51169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 8/043 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007440 | 944538756-51169-DTLTRT-10_11_2023-GUYHINS-1^668010/00 8/043 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007441 | 944863725-94813-DTLSB-05_07_2024-GO95MLD-1^06245001.0297301 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007442 | 944873315-53189-DETAIL-04_01_2024-GO95MLD-1^06247005.0342501 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007443 | 945300383-77349-DTLSB-05_01_2024-GO95MLD-1^06245007.0228601 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007444 | 945304693-2929-DETAIL-05_09_2024-GO95BLTC-1^06142012.0120505 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007445 | 945941738-42713-DETAIL-05_02_2024-GO95MLD-1^06142012.0125008 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007446 | 946712270-2859-DETAIL-03_21_2024-GO95MLD-1^06246005.0063400 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007447 | 947024173-32049-DRONE_HY-11_07_2023-GO95HV-1^668033/00 2/036 | OTHER | HFTD Tier 2 | Transmission | 2023-11-07 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007448 | 947255263-1129-DETAIL-05_14_2024-GO95HV-1^06142012.0122703 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007449 | 947255263-1129-DETAIL-05_14_2024-GO95MLD-2^06142012.0122703 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007450 | 947262784-5690-DETAIL-01_29_2025-GO95CL10-1^06240004.0178307 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007451 | 947311928-68909-DETAIL-03_28_2024-GO95MLD-1^06147005.0157905 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007452 | 947315956-99523-DTLSB-01_30_2023-GO95MLD-1^06248001.0367903 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007453 | 947541495-54530-DETAIL-01_27_2025-SVCDEFLC-1^06240004.0085340 | OTHER | HFTD Tier 2 | Distribution | 2025-01-27 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007454 | 947817638-30990-DETAIL-03_26_2025-GO95HV-1^06239004.0249900 | OTHER | HFTD Tier 3 | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007455 | 947883730-56499-DTLSB-09_03_2024-GO95MLD-1^06245007.0018000 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007456 | 948105200-58789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223800 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007457 | 948498906-10098-DETAIL-05_09_2022-GO95HV-1^07116001.0096101 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007458 | 948498906-10098-DETAIL-05_09_2022-GO95MLD-1^07116001.0096101 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007459 | 9489543-34750-DETAIL-02_04_2025-GO95MLD-1^06239004.0134200 | OTHER | HFTD Tier 3 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007460 | 94913283-86780-DETAIL-02_11_2025-GO95MLD-1^06240004.0355403 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007461 | 949717274-31779-DETAIL-08_15_2024-GO95HV-1^06246005.0147200 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007462 | 949792741-12180-DETAIL-02_06_2025-SVCROOF-1^06240004.0166304 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007463 | 949871181-50123-DETAIL-04_15_2024-GO95MLD-1^06145001.0139101 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007464 | 949887733-5560-DTLTRT-04_08_2024-BIRDDMG-1^668062/00 3/004 | POLE | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007465 | 950229814-61914-DETAIL-03_29_2023-GO95MLD-1^06142016.0085002 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007466 | 950403993-44993-DETAIL-06_24_2024-GO95HV-1^06244005.0235200 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007467 | 950403993-44993-DETAIL-06_24_2024-GO95MLD-1^06244005.0235200 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007468 | 950795141-63759-DETAIL-06_17_2024-GO95BLTC-1^06246006.0239900 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007469 | 950795141-63759-DETAIL-06_17_2024-GO95MLD-1^06246006.0239900 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007470 | 951490270-82633-DTLSB-08_29_2023-GO95TCH-1^06243009.0117400 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007471 | 951832592-39133-DTLSB-05_22_2024-GO95MLD-1^06243001.0110200 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007472 | 951839052-19099-DETAIL-01_29_2019-GO95HV-1^06147004.0350500 | OTHER | Non-HFTD | Distribution | 2019-01-29 | 2024-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007473 | 951839052-19099-DETAIL-03_14_2024-GRDRODHI-1^06147004.0350500 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007474 | 951845509-72289-DETAIL-05_31_2024-GO95MLD-1^06246005.0333201 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007475 | 952664879-19489-DTLSB-09_03_2024-GO95MLD-1^06245007.0018100 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007476 | 952795917-18755-DETAIL-08_14_2024-GO95MLD-1^06246005.0253742 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007477 | 952921883-58239-DETAIL-06_25_2024-GO95MLD-1^06244005.0237301 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007478 | 953053115-20733-DETAIL-02_28_2024-GO95MLD-1^07215001.0025900 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007479 | 953389205-21579-ADMIN-04_03_2024-ABNDEQPM-1^06147005.0142006 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007480 | 953642793-6030-DETAIL-03_04_2025-GO95BLTC-1^06240004.0064802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007481 | 953828783-9699-DETAIL-03_05_2024-GO95MLD-1^06147005.0177900 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007482 | 955265359-43251-DETAIL-04_03_2025-GO95MLD-1^06241005.0092001 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007483 | 955420331-6040-DTLTRT-10_03_2023-GUYNOINS-1^668010/00 7A/030 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007484 | 955420331-6040-DTLTRT-10_03_2023-GUYNOINS-2^668010/00 7A/030 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007485 | 955714319-70343-DTLSB-05_20_2024-GO95HV-1^06244003.0270800 | OTHER | Non-HFTD | Distribution | 2024-05-20 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007486 | 955803518-25670-DETAIL-04_11_2023-GO95HV-1^06240004.0167402 | OTHER | HFTD Tier 2 | Distribution | 2023-04-11 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007487 | 955820116-78370-DETAIL-01_24_2025-GO95HV-1^06239004.0257944 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007488 | 955890924-13924-DETAIL-03_29_2023-GO95HV-1^06142016.0084707 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007489 | 955963479-78039-DETAIL-07_08_2024-GO95HV-1^06244005.0135801 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007490 | 956298558-53249-ADMIN-09_24_2024-POLEDERP-1^07117001.0303401 | POLE | HFTD Tier 2 | Distribution | 2024-09-24 | 2025-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007491 | 956298558-53249-DETAIL-05_16_2022-GO95MLD-1^07117001.0303401 | OTHER | HFTD Tier 2 | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007492 | 956510374-62260-DETAIL-01_14_2025-SVCWIND-1^06239004.0256106 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007493 | 956857275-69949-DETAIL-03_01_2023-GO95MLD-1^07117002.0196203 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007494 | 956918113-81349-DETAIL-10_15_2024-SVCDEFLC-1^07216001.0207006 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007495 | 957416748-72243-DETAIL-03_19_2024-GO95MLD-1^06245002.0124900 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007496 | 957891070-40370-DETAIL-02_18_2025-PWRTRN-1^06240004.0343902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007497 | 958231879-16330-DETAIL-05_03_2023-GUYNOINS-1^668002/01 11/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-05-03 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007498 | 958234649-24749-DETAIL-10_08_2024-GO95HV-1^07216001.0202000 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007499 | 958234649-24749-DETAIL-10_08_2024-GO95MLD-1^07216001.0202000 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007500 | 958482644-53259-DETAIL-03_20_2023-GO95MLD-1^07114001.0285100 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007501 | 958583516-76843-DTLSB-05_14_2024-GO95MLD-1^06244001.0280000 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007502 | 958980875-8543-DTLSB-05_07_2024-GO95MLD-1^06245001.0291201 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007503 | 958986135-83199-DETAIL-10_24_2022-GO95MLD-1^06247008.0315500 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007504 | 959117324-40629-DTLSB-08_07_2023-GO95HV-1^06243009.0196202 | OTHER | HFTD Tier 2 | Distribution | 2023-08-07 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007505 | 959186661-45989-DETAIL-07_03_2024-GO95HV-1^06244005.0236900 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007506 | 959261595-13491-DRONE_VS-11_13_2024-XARMSPCR-1^668038/00 3/045 | CROSSARM | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007507 | 959516781-69479-DETAIL-01_31_2023-GO95MLD-1^06146002.0153700 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007508 | 959754644-41779-DETAIL-08_21_2024-GO95MLD-1^06246005.0269840 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007509 | 959754644-41779-DETAIL-08_21_2024-GRDRODHI-1^06246005.0269840 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007510 | 959873208-78799-DETAIL-07_23_2024-GRDRODHI-1^06245006.0143000 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007511 | 960029775-58170-DETAIL-02_27_2025-GO95HV-1^06240003.0180501 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007512 | 960178805-5053-DTLSB-05_09_2024-GO95MLD-1^06244001.0108901 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007513 | 960517582-57340-DTLTRT-10_03_2023-GO95HV-1^668010/00 17/030 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007514 | 960517582-57340-DTLTRT-10_03_2023-GO95MLD-1^668010/00 17/030 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007515 | 96062272-28430-DETAIL-02_21_2023-CONDFRAY-1^06247002.0045401 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007516 | 960637045-89453-DETAIL-10_25_2024-CLMBTRE-1^07216001.0209906 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007517 | 960651505-29929-DETAIL-04_06_2023-GUYHINS-1^06143014.0237700 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-04-06 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007518 | 960727683-49949-DTLSB-02_13_2024-GO95MLD-1^07216001.0187002 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007519 | 960731252-80319-ADMIN-12_27_2018-POLEREPL-1^668005/00 11/087 | POLE | Non-HFTD | Transmission | 2018-12-27 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007520 | 961298565-36949-DETAIL-02_26_2024-GO95MLD-1^07113001.0211401 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007521 | 961298565-36949-DETAIL-02_26_2024-SVCDEFLC-1^07113001.0211401 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007522 | 961384991-64780-DETAIL-02_13_2025-SVCNEUT-1^06240004.0168144 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007523 | 96146456-99849-DETAIL-02_27_2024-SVCRUBLG-1^07113002.0073300 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007524 | 962318919-95649-DETAIL-02_22_2024-GO95MLD-1^07216001.0349701 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007525 | 962610363-23049-DETAIL-03_15_2023-SVCWIND-1^07216001.0291502 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007526 | 963281853-45153-DTLSB-05_23_2024-GO95HV-1^06243001.0121000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007527 | 964146508-92369-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 13/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007528 | 964367613-66339-DETAIL-08_05_2024-GO95HV-1^06244005.0325601 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007529 | 965050416-77219-DETAIL-03_25_2024-GO95HV-1^06147005.0134900 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007530 | 965491739-46130-DETAIL-10_26_2023-GUYHINS-1^668010/00 14/021 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-26 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007531 | 966035438-3099-DETAIL-03_19_2024-GO95HV-1^06245002.0020000 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007532 | 966177945-70319-DETAIL-10_24_2022-GO95HV-1^06247008.0191000 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007533 | 966369138-52663-DETAIL-03_19_2024-SVCNEUT-1^06245002.0022001 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007534 | 966611171-39199-DETAIL-07_18_2024-GO95MLD-1^06244004.0052500 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007535 | 966738836-78129-DETAIL-07_06_2023-GO95MLD-1^06244008.0326700 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007536 | 966902071-91173-DTLSB-02_15_2023-GO95MLD-1^06248002.0340401 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007537 | 967430708-94359-DETAIL-05_31_2024-GO95MLD-1^06246005.0329401 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007538 | 967460597-43719-DTLTRT-08_18_2022-GO95HV-1^668005/00 6/098 | OTHER | Non-HFTD | Transmission | 2022-08-18 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007539 | 967554324-5629-DTLSB-08_09_2023-GO95MLD-1^06243009.0196100 | OTHER | HFTD Tier 2 | Distribution | 2023-08-09 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007540 | 967593585-60140-DETAIL-03_04_2025-SVCROOF-1^06240004.0150603 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007541 | 9677113-16650-DETAIL-01_24_2025-GO95TCH-1^06239004.0256907 | OTHER | HFTD Tier 2 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007542 | 967795288-52449-DETAIL-10_09_2024-GO95TCH-1^07216001.0204101 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007543 | 967853093-62249-DETAIL-03_16_2023-GO95TCH-1^07114001.0299702 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007544 | 967932234-61479-DETAIL-08_21_2024-GO95MLD-1^06246005.0269741 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007545 | 967968354-2010-DETAIL-03_13_2025-BIRDDMG-1^06238004.0156202 | POLE | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007546 | 968216199-72879-DETAIL-09_29_2020-GO95HV-1^668018/00 2/007 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007547 | 968442791-99859-DETAIL-06_05_2024-GO95STUB-1^06246006.0269901 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007548 | 969007341-56439-DETAIL-07_10_2024-GO95HV-1^06244004.0051400 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007549 | 969555653-42773-DTLSB-02_13_2023-GO95TCH-1^06248001.0276400 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007550 | 969642763-95180-DETAIL-02_11_2025-SVCDEFLC-1^06240004.0357100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007551 | 969667163-60029-DTLSB-08_25_2023-GO95HV-1^06243008.0133403 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007552 | 969697962-31319-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/088 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007553 | 969712141-34973-DETAIL-04_16_2024-GO95MLD-1^06145001.0139800 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007554 | 969729471-37820-DETAIL-03_06_2025-GO95MLD-1^06240004.0272401 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007555 | 97001434-3849-DETAIL-03_14_2023-GO95MLD-1^07114001.0284206 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007556 | 970224274-30374-DETAIL-03_02_2023-GO95MLD-1^07117002.0202300 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007557 | 970401923-20359-DETAIL-06_18_2024-BIRDDMG-1^06245007.0297301 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007558 | 970621159-41159-DETAIL-03_06_2024-GUYHINS-1^06147004.0011701 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007559 | 970987319-29170-DETAIL-02_18_2025-SVCDEFLC-1^06240004.0220702 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007560 | 97110436-82279-DTLSB-01_31_2023-GO95TCH-1^06248001.0369803 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007561 | 97119213-83589-DETAIL-07_30_2024-GO95MLD-1^06244005.0349601 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007562 | 971274073-99680-DETAIL-02_11_2025-GUYHINS-1^06240004.0355400 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-11 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007563 | 971726590-52859-DETAIL-03_21_2024-GO95MLD-1^06246005.0060100 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007564 | 971805091-48620-DETAIL-02_17_2025-GO95HV-1^06240004.0278502 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007565 | 972195474-19849-DTLSB-02_07_2024-GO95MLD-1^07216001.0199101 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007566 | 622677545-16600-DETAIL-03_12_2025-GO95MLD-1^06239003.0244904 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007567 | 622855420-16331-DETAIL-03_13_2024-GO95MLD-1^06147004.0180700 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007568 | 623354981-30339-DETAIL-06_25_2024-GO95HV-1^06244005.0238400 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007569 | 623567493-51703-DETAIL-05_29_2024-GRDRODHI-1^06246005.0210900 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007570 | 62359968-80889-ADMIN-03_20_2024-GO95STUB-1^06245002.0124301 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007571 | 623713673-20569-DTLTRT-04_15_2024-GUYNOINS-1^668067/00 6/008 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007572 | 623734781-6779-DTLTRT-10_16_2023-GO95HV-1^668010/00 18/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007573 | 624346758-84379-DETAIL-03_25_2024-GO95MLD-1^06244005.0140043 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007574 | 624519626-65582-DETAIL-07_06_2023-GO95MLD-1^06244008.0329603 | OTHER | Non-HFTD | Distribution | 2023-07-06 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007575 | 624842326-11049-DETAIL-08_20_2024-GO95HV-1^06245004.0191900 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007576 | 624849891-87920-DETAIL-02_17_2025-GO95HV-1^06240004.0277600 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007577 | 625392788-3290-DETAIL-02_19_2025-GO95HV-1^06239004.0365505 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007578 | 625485088-16279-DETAIL-04_02_2024-GO95MLD-1^06147005.0153900 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007579 | 625528115-25141-DTLSB-05_08_2024-GO95MLD-1^06244001.0035201 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007580 | 62600083-35749-DETAIL-02_29_2024-GO95HV-1^07113001.0107001 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007581 | 62650565-47669-DTLTRT-10_10_2023-GO95HV-1^668010/00 15/040 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007582 | 626741686-8500-DTLTRT-11_01_2023-GO95HV-1^668010/00 7/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007583 | 626842984-3290-DETAIL-03_26_2025-GO95HV-1^06239003.0019616 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007584 | 626980312-80250-DETAIL-03_19_2025-SVCROAD-1^06238004.0028640 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007585 | 627240069-45199-DETAIL-07_18_2024-GRDRODHI-1^06244004.0043700 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007586 | 6274278-36278-DETAIL-10_14_2024-GO95MLD-1^07216001.0204304 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007587 | 6274278-36278-DETAIL-10_14_2024-SVCENTBK-1^07216001.0204304 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007588 | 627563270-85270-DETAIL-03_19_2025-GO95HV-1^06239002.0019600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007589 | 627619941-48741-DETAIL-03_13_2024-GO95HV-1^06147004.0085100 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007590 | 627732161-33204-DETAIL-03_23_2023-GO95MLD-1^06142016.0050101 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007591 | 628533259-34279-DETAIL-05_31_2024-GRDRODHI-1^06246005.0337404 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007592 | 628533259-34279-DETAIL-05_31_2024-GRDRODHI-2^06246005.0337404 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007593 | 628713188-23989-DETAIL-04_17_2024-GO95MLD-1^06145001.0019502 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007594 | 629128444-72660-DTLTRT-04_08_2024-GO95HV-1^668062/00 7/006 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007595 | 630059700-66901-DETAIL-01_21_2025-GO95HV-1^06239004.0256542 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007596 | 630059700-66901-DETAIL-01_21_2025-GO95TCH-1^06239004.0256542 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007597 | 630260598-94299-ADMIN-07_01_2024-ABNDEQPM-1^06245006.0180000 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007598 | 630260598-94299-DTLSB-07_01_2024-GO95HV-1^06245006.0180000 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007599 | 630453195-36195-DETAIL-03_22_2024-GO95HV-1^06247005.0338500 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007600 | 630453195-36195-DETAIL-03_22_2024-GO95MLD-1^06247005.0338500 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007601 | 630513901-21499-DETAIL-11_08_2022-GO95MLD-1^06246008.0066600 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007602 | 63078741-81463-DTLSB-04_09_2024-GO95MLD-1^06245007.0221341 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007603 | 631141880-33499-DETAIL-11_10_2022-GO95MLD-1^06246008.0044301 | OTHER | HFTD Tier 2 | Distribution | 2022-11-10 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007604 | 631514230-90640-DETAIL-02_06_2025-GO95TCH-1^06239003.0061003 | OTHER | HFTD Tier 3 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007605 | 631562778-83143-ADMIN-03_14_2025-POLEREPL-1^06245007.0220540 | POLE | Non-HFTD | Distribution | 2025-03-14 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007606 | 631562778-83143-DTLSB-04_29_2024-GO95MLD-1^06245007.0220540 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007607 | 631562778-83143-DTLSB-04_29_2024-SVCENTCO-1^06245007.0220540 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007608 | 632236123-34699-DETAIL-07_24_2024-GO95MLD-1^06244005.0251002 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007609 | 632275384-90789-DETAIL-03_06_2025-SVCDEFLC-1^06241005.0120103 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007610 | 632792504-89560-DTLTRT-04_08_2024-GO95HV-1^668062/00 1/006 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007611 | 632792504-89560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007612 | 632823783-39629-DETAIL-05_14_2024-GO95MLD-1^06142012.0122707 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007613 | 632901770-5639-DETAIL-03_06_2023-GUYHINS-1^07216001.0296606 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007614 | 633098716-80951-DTLSB-05_22_2024-GO95MLD-1^06244001.0331800 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007615 | 633491479-50151-DETAIL-01_24_2023-GO95CL10-1^06147003.0129600 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007616 | 633510681-70080-DETAIL-03_27_2023-SVCENTCO-1^06240004.0167005 | OTHER | HFTD Tier 2 | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007617 | 633773403-66529-DTLSB-07_31_2023-GO95HV-1^06243009.0084100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007618 | 633914583-87969-DTLSB-10_07_2024-GO95MLD-1^06245007.0219204 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007619 | 634119676-90782-DETAIL-03_20_2024-GO95HV-1^06244005.0145402 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007620 | 634423478-13751-DETAIL-03_28_2024-SVCENTCO-1^06147005.0165901 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007621 | 635120493-35251-DTLSB-05_22_2024-GO95MLD-1^06243001.0108300 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007622 | 635275379-81490-DETAIL-01_16_2025-GO95HV-1^06239004.0257404 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007623 | 635275379-81490-DETAIL-01_16_2025-GO95MLD-1^06239004.0257404 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007624 | 635358990-15359-DETAIL-05_16_2022-ABNDEQPM-1^07116001.0090900 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007625 | 635358990-15359-DETAIL-05_16_2022-GO95TCH-1^07116001.0090900 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007626 | 63546876-72349-DETAIL-03_02_2023-GO95MLD-1^07216001.0293901 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007627 | 63546876-72349-DETAIL-03_02_2023-GO95MLD-2^07216001.0293901 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007628 | 635514212-55959-DETAIL-05_29_2024-GO95HV-1^06246005.0178102 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007629 | 635629418-26890-DETAIL-01_24_2025-GO95HV-1^06239004.0247140 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007630 | 635670793-17751-DETAIL-04_06_2023-ABNDEQPM-1^06143014.0234700 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007631 | 635697314-44839-DETAIL-08_05_2024-GO95HV-1^06244005.0031900 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007632 | 635946724-28051-DETAIL-10_25_2024-GO95HV-1^07216001.0208708 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007633 | 636032631-83149-DTLSB-08_27_2024-GO95HV-1^06245007.0116801 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007634 | 636064783-75150-DETAIL-01_24_2025-GO95HV-1^06239004.0258601 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007635 | 636244883-23351-DTLSB-05_22_2024-GO95MLD-1^06243001.0105401 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007636 | 636402485-93532-DETAIL-04_03_2025-GO95TCH-1^06241005.0028303 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007637 | 636422470-11132-DTLSB-07_19_2023-GO95MLD-1^06243010.0022202 | OTHER | HFTD Tier 2 | Distribution | 2023-07-19 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007638 | 63664801-29080-DTLTRT-09_27_2023-GO95MLD-1^668010/00 19X/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007639 | 636713553-84559-DETAIL-04_04_2024-GO95HV-1^06247005.0298401 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007640 | 636767432-289-DTLSB-02_16_2023-GO95MLD-1^06248001.0209201 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007641 | 636812517-76369-DETAIL-06_21_2023-GO95MLD-1^06244009.0270000 | OTHER | HFTD Tier 2 | Distribution | 2023-06-21 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007642 | 637093143-66143-DETAIL-04_29_2024-GO95HV-1^06142016.0078902 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007643 | 637581746-12746-DETAIL-01_29_2025-GO95MLD-1^06239004.0269802 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007644 | 637590628-56251-DETAIL-04_23_2024-GO95HV-1^06145001.0023000 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007645 | 637590628-56251-DETAIL-04_23_2024-GO95MLD-1^06145001.0023000 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007646 | 637849342-19479-DTLSB-09_06_2023-GRDRODHI-2^06243007.0202302 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007647 | 637905216-47139-DETAIL-03_13_2023-GO95CL10-1^07216001.0294407 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007648 | 637905216-47139-DETAIL-03_13_2023-SVCENTBK-1^07216001.0294407 | OTHER | Non-HFTD | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007649 | 637924538-48379-DETAIL-03_25_2024-GO95MLD-1^06244005.0141440 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007650 | 638162519-72759-ADMIN-03_07_2024-ABNDEQPM-1^07216001.0351400 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007651 | 638399404-41551-DETAIL-03_09_2023-SVCENTBK-1^07216001.0295540 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007652 | 638418219-63769-ADMIN-02_07_2022-POLEDERP-1^668005/03 5/004 | POLE | Non-HFTD | Transmission | 2022-02-07 | 2025-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007653 | 638447472-35950-DETAIL-03_19_2025-GO95TCH-1^06238004.0027241 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007654 | 638530575-7039-DETAIL-03_09_2023-GUYHINS-1^07216001.0295500 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007655 | 63859384-55430-DETAIL-01_13_2025-GO95CL10-1^06240004.0086041 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007656 | 63859384-55430-DETAIL-01_13_2025-PWRTRN-1^06240004.0086041 | OTHER | HFTD Tier 2 | Distribution | 2025-01-13 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007657 | 638703644-53644-DTLSB-02_07_2024-SVCENTCO-1^07216001.0199408 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007658 | 638744260-11713-DETAIL-06_19_2024-GO95MLD-1^06246006.0137701 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007659 | 638756726-73623-DTLSB-04_23_2024-GO95HV-1^06245007.0223547 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007660 | 638756726-73623-DTLSB-04_23_2024-GO95MLD-1^06245007.0223547 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007661 | 639221478-869-DTLTRT-06_30_2022-GO95MLD-1^668005/00 14/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007662 | 639367762-64780-DETAIL-02_12_2025-PWRTRN-1^06240004.0287601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007663 | 639638878-2320-DTLTRT-04_04_2024-BIRDDMG-1^668067/00 4/023 | POLE | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007664 | 639638878-43671-AUDIT-04_30_2024-XARMSPCR-1^668067/00 4/023 | CROSSARM | HFTD Tier 2 | Transmission | 2024-04-30 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007665 | 64002984-89-DETAIL-06_11_2024-GUYHINS-1^06245007.0346501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007666 | 64009168-39168-DTLSB-09_03_2024-BIRDDMG-1^06245007.0018403 | POLE | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007667 | 640218151-29180-DETAIL-02_12_2025-GO95TCH-1^06240004.0167041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007668 | 640297076-99319-DETAIL-10_24_2022-GO95HV-1^06247009.0248300 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007669 | 640683624-81240-DETAIL-02_26_2025-GO95MLD-1^06240004.0218940 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007670 | 640743601-98059-ADMIN-10_02_2024-POLEDERP-1^07217001.0266300 | POLE | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007671 | 640910249-91989-DETAIL-05_06_2024-GO95MLD-1^06245005.0047900 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007672 | 64094449-3869-ADMIN-06_15_2021-POLEDERP-1^668005/03 10/005 | POLE | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007673 | 640983933-66161-DRONE_HY-09_26_2023-GO95HV-1^668033/00 7X1/002 | OTHER | Non-HFTD | Transmission | 2023-09-26 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007674 | 641003518-83950-DETAIL-02_27_2023-GO95TCH-1^07216001.0297944 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007675 | 641194583-58929-ADMIN-12_23_2024-POLEREPL-1^06142012.0133708 | POLE | Non-HFTD | Distribution | 2024-12-23 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007676 | 641251134-76049-DETAIL-03_20_2023-GO95HV-1^07114001.0285300 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007677 | 641272135-90349-DETAIL-02_28_2023-CLRTOPOL-1^07216001.0299803 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007678 | 641272135-90349-DETAIL-02_28_2023-GO95HV-1^07216001.0299803 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007679 | 641453574-35574-DETAIL-10_22_2024-GO95MLD-1^07216001.0208903 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007680 | 642078779-13753-DTLSB-04_29_2024-GO95MLD-1^06245007.0226444 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007681 | 642078779-13753-DTLSB-04_29_2024-RISEGRD-1^06245007.0226444 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007682 | 642130396-72360-DTLTRT-10_09_2023-GO95MLD-1^668010/00 4/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007683 | 642196628-43009-DETAIL-04_09_2024-GRDRODHI-1^06147005.0216701 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007684 | 64256171-12349-DETAIL-05_02_2022-GO95MLD-1^07116001.0167905 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007685 | 64256171-12349-DETAIL-05_02_2022-GUYHINS-1^07116001.0167905 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007686 | 642632338-16599-DETAIL-06_04_2024-GO95MLD-1^06246005.0318701 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007687 | 642644712-86349-DETAIL-10_10_2024-GO95MLD-1^07216001.0206105 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007688 | 642869331-92920-DETAIL-03_07_2023-GO95MLD-1^07117002.0211201 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007689 | 643432318-48223-DETAIL-03_14_2023-GO95MLD-1^07117003.0114901 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007690 | 643594929-37479-DETAIL-04_03_2024-CLRTOUCH-1^06147005.0222700 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007691 | 644014623-99461-DTLSB-05_22_2024-GO95MLD-1^06243001.0030300 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007692 | 644183438-71999-DTLSB-08_22_2024-RISEBKSP-1^06245006.0323201 | OTHER | HFTD Tier 2 | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007693 | 644395044-41661-DETAIL-10_21_2024-GO95CL10-1^07216001.0209504 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007694 | 644638464-49239-DTLSB-02_06_2024-GO95MLD-1^07216001.0309902 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007695 | 644931116-5449-DETAIL-10_14_2024-GO95MLD-1^07216001.0202302 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007696 | 645557273-20761-DETAIL-02_16_2023-GO95BLTC-1^06247002.0161103 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007697 | 645557273-20761-DETAIL-02_16_2023-GRDRODHI-1^06247002.0161103 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007698 | 64566842-74009-DETAIL-04_09_2024-GO95MLD-1^06147005.0219503 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007699 | 645992814-11849-DETAIL-03_20_2023-GO95MLD-1^07114001.0284306 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007700 | 646120280-75759-DETAIL-05_02_2022-GO95TCH-1^07116001.0168903 | OTHER | Non-HFTD | Distribution | 2022-05-02 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007701 | 646161882-15229-DETAIL-05_09_2024-SVCDEFLC-1^06142012.0120405 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007702 | 646164629-83959-DTLTRT-06_30_2022-GO95BLTC-1^668005/00 21/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007703 | 646164629-83959-DTLTRT-06_30_2022-GO95HV-1^668005/00 21/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007704 | 646164629-83959-DTLTRT-06_30_2022-GO95MLD-1^668005/00 21/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007705 | 646571054-69189-DETAIL-07_25_2024-SVCDEFLC-1^06244005.0349301 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007706 | 647060875-60059-DETAIL-03_01_2023-GO95MLD-1^07117002.0197301 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007707 | 647222283-19771-DETAIL-04_24_2024-GO95MLD-1^06245001.0019400 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007708 | 647222283-19771-DETAIL-04_24_2024-GRDRODHI-1^06245001.0019400 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007709 | 647592891-9411-DETAIL-01_21_2025-GO95TCH-1^06239004.0255445 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007710 | 647592891-9411-DETAIL-01_21_2025-SVCROAD-1^06239004.0255445 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007711 | 647889535-88971-DETAIL-03_09_2023-GO95MLD-1^07216001.0294504 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007712 | 648115869-59639-DTLSB-02_19_2024-SVCENTCO-2^07216001.0262302 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007713 | 648322224-69649-DTLSB-02_26_2024-SVCROAD-1^07216001.0276800 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007714 | 64842301-90759-DETAIL-06_17_2024-GO95MLD-1^06246006.0239501 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007715 | 649282233-14639-DETAIL-02_27_2023-GO95MLD-1^07216001.0295703 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007716 | 649282233-14639-DETAIL-02_27_2023-GO95MLD-2^07216001.0295703 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007717 | 649308171-33599-DETAIL-07_05_2023-GO95HV-1^06244009.0128400 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007718 | 64951538-60679-DETAIL-03_28_2024-GO95MLD-1^06147005.0117200 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007719 | 64993376-15779-ADMIN-04_08_2024-ABNDEQPM-1^06147005.0245400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007720 | 64993376-15779-DETAIL-04_08_2024-POLISSUE-1^06147005.0245400 | POLE | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007721 | 65006818-79749-DTLSB-04_29_2024-CLRTOUCH-1^06245007.0226407 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007722 | 650351069-50090-DETAIL-01_16_2025-GO95HV-1^06239004.0257403 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007723 | 650824090-4180-DETAIL-02_27_2025-GUYHINS-1^06240004.0233600 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007724 | 650855233-13880-DETAIL-01_30_2025-ABNDEQPM-1^06240004.0162501 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007725 | 650948587-21519-ADMIN-07_29_2024-POLEDERP-1^668005/00 8/070 | POLE | Non-HFTD | Transmission | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007726 | 650961043-20289-DETAIL-10_25_2022-ABNDEQPM-1^06245010.0317301 | OTHER | HFTD Tier 2 | Distribution | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007727 | 651022278-87920-DETAIL-09_10_2024-SVCROAD-1^06240004.0098101 | OTHER | HFTD Tier 2 | Distribution | 2024-09-10 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007728 | 651321313-70913-DTLSB-05_01_2024-GO95MLD-1^06245007.0228641 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007729 | 651330359-56690-DETAIL-01_28_2025-GO95HV-1^06239004.0244306 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007730 | 651360024-65050-DTLTRT-10_11_2023-BIRDDMG-1^668010/00 8A/040 | POLE | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007731 | 651479536-22109-DETAIL-02_02_2023-GO95HV-1^06147002.0175901 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007732 | 651565833-2880-DETAIL-03_23_2023-GO95MLD-1^06240004.0163504 | OTHER | HFTD Tier 2 | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007733 | 651687380-37779-DETAIL-05_10_2023-ABNDEQPM-1^06245006.0271201 | OTHER | Non-HFTD | Distribution | 2023-05-10 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007734 | 652021908-17269-DTLTRT-07_05_2022-GO95HV-1^668005/00 1/035 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007735 | 652021908-17269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 1/035 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007736 | 65205700-56649-DTLSB-04_11_2024-GO95MLD-1^06245007.0222206 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007737 | 65211113-32209-DETAIL-01_17_2023-GO95MLD-1^06148004.0221700 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007738 | 652577018-4052-DETAIL-04_03_2025-CLRTOUCH-1^06241005.0029405 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-04-03 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007739 | 652661090-50452-DETAIL-04_02_2025-SVCENTCO-1^06241005.0028041 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007740 | 652984576-67563-DETAIL-03_28_2024-BIRDDMG-1^06247005.0332500 | POLE | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007741 | 653043290-47670-DETAIL-03_29_2023-GO95HV-1^06240004.0167407 | OTHER | HFTD Tier 2 | Distribution | 2023-03-29 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007742 | 653704330-34739-DTLSB-02_20_2024-GO95MLD-1^07216001.0260308 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007743 | 65402834-24173-DETAIL-03_04_2024-SVCDEFLC-1^06245007.0274441 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007744 | 654534048-26039-DETAIL-10_14_2024-CLRTOUCH-1^07216001.0202201 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007745 | 654534048-26039-DETAIL-10_14_2024-GO95TCH-1^07216001.0202201 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007746 | 654583095-5095-DETAIL-03_22_2024-GO95MLD-1^06247005.0338401 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007747 | 654704466-82329-DTLSB-08_29_2023-GO95MLD-1^06243009.0120100 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007748 | 654737529-18959-DETAIL-10_14_2024-GO95MLD-1^07216001.0204302 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007749 | 654854780-10139-ADMIN-04_21_2023-POLEREPL-1^668087/00 3/025 | POLE | Non-HFTD | Transmission | 2023-04-21 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007750 | 65505056-69171-DETAIL-11_14_2022-GO95MLD-1^06239004.0367944 | OTHER | HFTD Tier 2 | Distribution | 2022-11-14 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007751 | 655217724-68724-DETAIL-04_25_2024-CUTOUTAR-1^06142016.0161800 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007752 | 655217724-68724-DETAIL-04_25_2024-GO95MLD-1^06142016.0161800 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007753 | 655217724-68724-DETAIL-04_25_2024-GRDRODHI-1^06142016.0161800 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007754 | 655217724-68724-DETAIL-04_25_2024-GUYHINS-1^06142016.0161800 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007755 | 655358662-62070-DETAIL-03_18_2025-GRDRODHI-1^06238004.0124801 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007756 | 655386292-76950-DETAIL-03_19_2025-SVCENTCO-1^06238004.0027240 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007757 | 655863244-88839-DETAIL-03_14_2023-GO95MLD-1^07114001.0284205 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007758 | 656181281-24301-DETAIL-04_15_2024-GO95MLD-1^06145001.0139000 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007759 | 656257470-4549-DETAIL-08_06_2024-GO95MLD-1^06245006.0105201 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007760 | 656405165-190-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 7/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007761 | 656405165-62111-DTLTRT-04_17_2024-GUYNOINS-1^668067/00 7/016 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007762 | 656465355-74859-DETAIL-10_24_2024-GO95MLD-1^07216001.0201505 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007763 | 656572008-93801-DETAIL-03_19_2024-GO95MLD-1^06245002.0026000 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007764 | 656590351-62520-DETAIL-03_07_2023-GUYHINS-1^07117002.0210300 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007765 | 656973429-26469-DTLTRT-10_19_2023-GO95HV-1^668010/00 2/026 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007766 | 657037508-88030-DETAIL-01_14_2025-GO95TCH-1^06240004.0098200 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007767 | 657226673-44101-DTLSB-02_06_2023-GO95HV-1^06248001.0256900 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007768 | 657392968-41570-DETAIL-02_03_2025-GO95HV-1^06240004.0167802 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007769 | 657515869-35501-DETAIL-04_02_2024-GO95TCH-1^06147005.0096200 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007770 | 657515869-35501-DETAIL-04_02_2024-GRDRODHI-1^06147005.0096200 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007771 | 657707193-12601-DETAIL-05_16_2024-GO95HV-1^06142012.0121703 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007772 | 657707193-12601-DETAIL-05_16_2024-GO95MLD-1^06142012.0121703 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007773 | 657831831-71831-DETAIL-06_06_2024-GO95HV-1^06246006.0349300 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007774 | 657880561-98099-DETAIL-06_24_2024-GO95HV-1^06244005.0231101 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007775 | 657899678-97840-DETAIL-01_22_2025-GUYHINS-1^06240004.0092502 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007776 | 658069916-81589-DETAIL-08_20_2024-GO95HV-1^06245004.0190900 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007777 | 658178398-7069-DTLTRT-10_11_2023-GO95HV-1^668010/00 9/043 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007778 | 658305599-76249-DETAIL-03_14_2024-GO95MLD-1^06245005.0061601 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007779 | 658517410-57932-DETAIL-06_08_2023-GO95HV-1^06244009.0336601 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007780 | 658525023-1029-DTLSB-08_25_2023-GO95HV-1^06243008.0133401 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007781 | 658945193-64201-DETAIL-05_16_2024-GO95MLD-1^06142012.0121701 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007782 | 659283456-90501-DTLSB-05_14_2024-GO95MLD-1^06244001.0299100 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007783 | 659421095-91269-DTLTRT-10_10_2023-GO95MLD-1^668010/00 2/041 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007784 | 659504792-55901-DETAIL-05_05_2022-GO95MLD-1^07116001.0100000 | OTHER | HFTD Tier 2 | Distribution | 2022-05-05 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007785 | 659910746-62206-DETAIL-09_28_2021-SVCWIND-1^06148004.0356006 | OTHER | Non-HFTD | Distribution | 2021-09-28 | 2024-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007786 | 659919450-39701-DETAIL-02_24_2025-GO95HV-1^06241005.0158000 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007787 | 660273109-50473-DETAIL-01_18_2023-GO95MLD-1^06240004.0092302 | OTHER | HFTD Tier 2 | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007788 | 660273109-50473-DETAIL-01_18_2023-SVCROOF-1^06240004.0092302 | OTHER | HFTD Tier 2 | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007789 | 660273109-50473-DETAIL-01_21_2025-SVCROOF-1^06240004.0092302 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007790 | 660539005-9539-DETAIL-07_10_2024-GO95BLTC-1^06244004.0194000 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007791 | 660599190-13861-DETAIL-04_03_2025-BIRDDMG-1^06241005.0099300 | POLE | HFTD Tier 2 | Distribution | 2025-04-03 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007792 | 66066636-28249-DETAIL-02_22_2024-GO95MLD-1^07216001.0344803 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007793 | 660711464-30880-DTLTRT-09_27_2023-GO95HV-1^668010/00 11/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007794 | 660711464-30880-DTLTRT-09_27_2023-GO95MLD-1^668010/00 11/007 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007795 | 660983302-18302-DETAIL-03_30_2023-GO95HV-1^06142016.0056001 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007796 | 661141494-21340-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 10/043 | POLE | HFTD Tier 3 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007797 | 661237183-31239-DETAIL-07_17_2024-GO95HV-1^06244005.0284201 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007798 | 661237183-31239-DETAIL-07_17_2024-GO95MLD-1^06244005.0284201 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007799 | 661655811-24630-DETAIL-02_05_2025-GRDRODHI-1^06240004.0170701 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007800 | 661655811-24630-DETAIL-09_23_2024-SVCDEFLC-1^06240004.0170701 | OTHER | HFTD Tier 2 | Distribution | 2024-09-23 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007801 | 661890663-7959-DETAIL-06_06_2024-GO95MLD-1^06246006.0353800 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007802 | 662284669-27349-DETAIL-03_01_2023-GO95MLD-1^07216001.0292500 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007803 | 662451136-44579-DETAIL-04_03_2024-GO95MLD-1^06147005.0142200 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007804 | 662574410-60889-DETAIL-01_30_2023-GO95MLD-1^06148003.0223500 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007805 | 662958121-57180-DETAIL-03_18_2025-GO95HV-1^06239001.0057701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007806 | 663304668-35668-DETAIL-10_24_2024-GO95HV-1^07216001.0202601 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007807 | 663576673-41289-DTLSB-02_08_2023-GO95MLD-1^06248001.0157000 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007808 | 66370126-61560-DTLTRT-10_09_2023-GO95MLD-1^668010/00 2A/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007809 | 664123753-3859-DETAIL-03_15_2023-CLRTOPOL-1^07216001.0291606 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007810 | 664123753-3859-DETAIL-03_15_2023-CLRTOPOL-2^07216001.0291606 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007811 | 664123753-3859-DETAIL-03_15_2023-GO95MLD-1^07216001.0291606 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007812 | 664194000-42370-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166202 | OTHER | HFTD Tier 2 | Distribution | 2023-03-22 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007813 | 664405645-81121-DTLSB-05_08_2024-GO95MLD-1^06244001.0108400 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007814 | 664415821-57739-DTLSB-02_16_2024-SVCROAD-1^07216001.0262003 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007815 | 664507112-22880-DETAIL-02_26_2025-GUYHINS-2^06240004.0150000 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007816 | 664811359-33779-DETAIL-03_18_2024-SVCENTCO-1^06245002.0035000 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007817 | 66506840-72359-DETAIL-02_29_2024-GO95MLD-1^07113001.0107100 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007818 | 665195444-89444-DETAIL-04_25_2024-ENCHRW-1^06142016.0174800 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007819 | 665791531-37849-DETAIL-02_22_2024-GO95HV-1^07113001.0097500 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007820 | 665832106-41990-DTLTRT-10_18_2023-GO95HV-1^668010/00 11/010 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007821 | 666033949-30359-DETAIL-05_31_2024-GO95MLD-1^06246005.0330400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007822 | 666748501-79189-DETAIL-06_05_2024-GO95MLD-1^06246006.0267202 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007823 | 66708120-38049-DETAIL-10_10_2024-GUYHINS-1^07216001.0207008 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007824 | 667492620-69249-DETAIL-03_16_2023-GO95MLD-1^07113001.0043505 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007825 | 667551236-40329-DTLSB-08_24_2023-GO95MLD-1^06243009.0119500 | OTHER | Non-HFTD | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007826 | 667571355-4090-DTLTRT-09_26_2023-GUYHINS-1^668010/00 1X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-26 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007827 | 667571355-4090-DTLTRT-09_26_2023-GUYHINS-3^668010/00 1X/008 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-09-26 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007828 | 66781791-26780-DETAIL-04_15_2024-GO95MLD-1^06145001.0249800 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007829 | 667944603-75059-DETAIL-05_29_2024-GO95HV-1^06246005.0150800 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007830 | 66836594-13459-DTLSB-02_27_2024-SVCROAD-1^07216001.0277706 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007831 | 668501461-39559-DETAIL-05_09_2022-SVCENTCO-1^07116001.0096201 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007832 | 669192391-59809-DETAIL-03_11_2024-GO95HV-1^06147004.0049800 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007833 | 669753789-6930-DTLTRT-10_26_2023-GO95HV-1^668010/00 4/023 | OTHER | HFTD Tier 2 | Transmission | 2023-10-26 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007834 | 66981733-50309-DETAIL-01_18_2023-CONDFRAY-1^06148004.0210001 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007835 | 66981733-50309-DETAIL-01_18_2023-CONDFRAY-2^06148004.0210001 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007836 | 669923104-54799-DTLSB-04_17_2024-GO95MLD-1^06245007.0224505 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007837 | 670026895-83599-DETAIL-04_01_2024-GO95HV-1^06247005.0341800 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007838 | 670026895-83599-DETAIL-04_01_2024-GO95MLD-1^06247005.0341800 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007839 | 670342486-84042-DETAIL-04_03_2025-CLRTOPOL-1^06241005.0028401 | OTHER | HFTD Tier 2 | Distribution | 2025-04-03 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007840 | 670370410-23529-DETAIL-05_07_2024-GO95MLD-1^06142012.0122204 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007841 | 670493038-69309-DETAIL-04_10_2024-CLRTOUCH-1^06147005.0212703 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007842 | 670634851-39102-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0308000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007843 | 670648283-18653-DTLTRT-04_09_2024-BIRDDMG-1^668062/00 3/003 | POLE | Non-HFTD | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007844 | 670648283-18653-DTLTRT-04_09_2024-GO95HV-1^668062/00 3/003 | OTHER | Non-HFTD | Transmission | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007845 | 670648283-3560-DTLTRT-04_09_2024-GO95HV-1^668062/00 3/003 | OTHER | Non-HFTD | Transmission | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007846 | 670648283-72560-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 3/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007847 | 670661664-34439-DETAIL-07_03_2024-GO95MLD-1^06244005.0235841 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007848 | 671267829-31130-DRONE_HY-09_25_2023-GO95HV-1^668002/00 5/060 | OTHER | HFTD Tier 2 | Transmission | 2023-09-25 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007849 | 671544610-70341-DTLTRT-05_16_2024-GO95HV-1^668084/00 2/001 | OTHER | Non-HFTD | Transmission | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007850 | 671883975-75349-DETAIL-10_24_2024-SVCROAD-1^07216001.0200504 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007851 | 671978608-92341-DETAIL-03_19_2024-SVCENTCO-1^06245002.0023001 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007852 | 67238698-46929-DTLSB-08_16_2023-GO95MLD-1^06243009.0155901 | OTHER | HFTD Tier 2 | Distribution | 2023-08-16 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007853 | 672459743-96499-DETAIL-08_05_2024-GO95HV-1^06244005.0025100 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007854 | 673054203-38059-DTLSB-10_07_2024-GO95HV-1^06245007.0230500 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007855 | 673480341-46201-DETAIL-01_31_2025-GO95HV-1^06239004.0135002 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007856 | 673531983-97429-DTLSB-09_06_2023-GO95HV-1^06243007.0187500 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007857 | 673724298-47790-AUDIT-02_25_2025-GUYHINS-1^06239004.0246042 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007858 | 673859151-62209-DETAIL-01_17_2023-GO95HV-1^06148004.0222705 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007859 | 673966860-74570-DETAIL-02_12_2025-GO95BLTC-1^06240004.0167008 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007860 | 673966860-74570-DETAIL-02_12_2025-GO95CL10-1^06240004.0167008 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007861 | 675217289-8449-DTLSB-02_28_2024-GO95MLD-1^07216001.0260906 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007862 | 675253539-25500-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/004 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007863 | 675253539-55500-DTLTRT-09_30_2020-GO95HV-1^668018/00 9/004 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007864 | 67527803-40139-DETAIL-02_29_2024-GO95HV-1^07113001.0106401 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007865 | 675380084-88838-DETAIL-03_14_2023-GO95MLD-1^07114001.0281202 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007866 | 675486799-2351-DETAIL-05_02_2024-SVCDEFLC-1^06142012.0126202 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007867 | 675608490-98159-DETAIL-10_21_2024-GO95MLD-1^07216001.0200900 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007868 | 67566603-93259-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0345100 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007869 | 675873371-61051-DETAIL-04_15_2024-GO95MLD-1^06145001.0139301 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007870 | 676279125-83770-DETAIL-01_22_2025-GO95HV-1^06239004.0256602 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007871 | 676703974-10619-DTLTRT-08_17_2022-GO95MLD-1^668005/00 7/095 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007872 | 676703974-10619-DTLTRT-08_17_2022-UBPBCTGD-1^668005/00 7/095 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007873 | 676724434-28440-DTLTRT-10_04_2023-GUYNOINS-1^668010/00 11A/035 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007874 | 677046676-67579-DTLSB-09_30_2024-GO95MLD-1^06245007.0230003 | OTHER | Non-HFTD | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007875 | 677196265-15663-DETAIL-04_24_2023-GO95MLD-1^07117003.0088000 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007876 | 677378269-71719-DETAIL-07_28_2022-GO95MLD-1^668005/00 3/076 | OTHER | Non-HFTD | Transmission | 2022-07-28 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007877 | 678148400-30733-ADMIN-11_08_2023-POLETOP-1^07217001.0151500 | POLE | Non-HFTD | Distribution | 2023-11-08 | 2026-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007878 | 678741316-62890-DTLTRT-04_18_2024-GO95HV-1^668067/00 4/020 | OTHER | Non-HFTD | Transmission | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007879 | 678868855-88949-DETAIL-10_08_2024-SVCENTCO-1^07216001.0201000 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007880 | 678868855-88949-DETAIL-10_08_2024-SVCNEUT-1^07216001.0201000 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007881 | 678982400-45659-DETAIL-06_17_2024-GO95MLD-1^06246006.0131300 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007882 | 679193636-64470-DETAIL-02_06_2025-GO95BLTC-1^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007883 | 679193636-64470-DETAIL-02_06_2025-SVCDEFLC-1^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007884 | 679193636-64470-DETAIL-02_06_2025-SVCROAD-1^06239004.0135204 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007885 | 679257943-72730-DETAIL-03_04_2025-SVCNEUT-1^06240004.0063803 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007886 | 679391395-7379-DETAIL-03_28_2024-GO95HV-1^06147005.0118500 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007887 | 679514901-65569-DRONE_HY-10_06_2023-GO95HV-1^668033/00 4/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-06 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007888 | 679514901-75570-DRONE_HY-10_06_2023-GO95HV-1^668033/00 4/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-06 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007889 | 679755679-33173-DETAIL-03_08_2023-GO95HV-1^07117002.0207601 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007890 | 679755679-33173-DETAIL-03_08_2023-GO95MLD-1^07117002.0207601 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007891 | 679755679-33173-DETAIL-03_08_2023-GUYHINS-1^07117002.0207601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007892 | 679884106-78070-DETAIL-01_23_2025-GO95HV-1^06239004.0256645 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007893 | 679973499-41973-DETAIL-03_08_2023-GO95HV-1^07117002.0206703 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007894 | 679973499-41973-DETAIL-03_08_2023-GO95MLD-1^07117002.0206703 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007895 | 680106823-46769-DTLTRT-06_07_2021-GO95HV-1^668041/00 5/011 | OTHER | Non-HFTD | Transmission | 2021-06-07 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007896 | 680397926-54310-DETAIL-03_13_2025-GO95HV-1^06238004.0222900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007897 | 680441279-4361-DETAIL-03_18_2024-CUTOUTAR-3^06245002.0038300 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007898 | 680947297-32609-DTLSB-09_05_2024-GO95HV-1^06245006.0073801 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007899 | 681354739-15379-DRONE_HY-10_16_2023-GO95HV-1^668033/00 2/009 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007900 | 681439044-79249-DTLSB-02_05_2024-GO95MLD-1^07216002.0248902 | OTHER | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007901 | 681648778-89041-DETAIL-03_06_2025-GO95HV-1^06241005.0161800 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007902 | 681668681-74961-DETAIL-02_13_2023-CLRTOUCH-1^06247002.0018100 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007903 | 681668681-74961-DETAIL-02_13_2023-GO95MLD-1^06247002.0018100 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007904 | 681764136-36149-DETAIL-10_14_2024-SVCDEFLC-1^07216001.0201200 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007905 | 681873711-1280-DETAIL-02_18_2025-GUYHINS-1^06240004.0343901 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007906 | 682346693-49693-DETAIL-04_29_2024-GO95HV-1^06142016.0067903 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007907 | 682407571-46949-DETAIL-05_09_2022-GO95MLD-1^07116001.0099302 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007908 | 682855060-5734-DETAIL-03_27_2023-CLRTOPOL-1^06142016.0082701 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007909 | 682879741-87973-DETAIL-03_02_2023-GO95MLD-1^07117002.0201202 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007910 | 682946623-34171-DETAIL-02_22_2023-GO95MLD-1^06247002.0030601 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007911 | 683387150-38759-DETAIL-03_27_2024-GO95HV-1^06246005.0069202 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007912 | 683861591-82352-DETAIL-06_29_2023-GO95HV-1^06244009.0326301 | OTHER | HFTD Tier 2 | Distribution | 2023-06-29 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007913 | 684321939-17459-DTLSB-02_21_2024-CLRTOPOL-1^07216001.0260808 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007914 | 684460283-59330-DRONE_VS-11_13_2024-INSULBRK-1^668014/00 7/028 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007915 | 685097671-95989-DETAIL-01_10_2023-GRDRODHI-1^06148004.0186201 | OTHER | Non-HFTD | Distribution | 2023-01-10 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007916 | 685440078-55999-DETAIL-08_01_2024-GO95MLD-1^06245006.0155502 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007917 | 685475843-97843-DTLSB-08_02_2022-GO95MLD-1^06242005.0176300 | OTHER | HFTD Tier 2 | Distribution | 2022-08-02 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007918 | 685897466-20171-DTLSB-01_31_2023-GO95HV-1^06248001.0369704 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007919 | 685897466-20171-DTLSB-01_31_2023-GO95TCH-1^06248001.0369704 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007920 | 685987703-88451-DETAIL-03_04_2025-GO95MLD-1^06241005.0130502 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007921 | 686446436-81699-DETAIL-10_12_2021-ENCHRW-1^06148005.0322903 | OTHER | Non-HFTD | Distribution | 2021-10-12 | 2024-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007922 | 686599204-4959-DETAIL-03_18_2024-GO95MLD-1^06246005.0081201 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007923 | 687064149-75149-DTLSB-08_10_2023-GO95MLD-1^06243009.0141001 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007924 | 687395580-25549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105402 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007925 | 688029411-1511-DETAIL-04_30_2024-GO95HV-1^06142015.0027901 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007926 | 688257588-77260-DRONE_HY-10_16_2023-GO95HV-1^668033/00 9/003 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007927 | 688299490-12590-DETAIL-06_24_2024-SVCDEFLC-1^06244005.0233200 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007928 | 688514466-80269-DTLTRT-10_09_2023-GO95HV-1^668010/00 10/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007929 | 688597758-98758-DTLSB-07_24_2023-GO95HV-1^06243010.0025700 | OTHER | HFTD Tier 2 | Distribution | 2023-07-24 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007930 | 68869901-39480-DETAIL-03_20_2025-GO95HV-1^06239002.0034402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007931 | 688784703-82529-DTLSB-07_31_2023-GO95MLD-1^06243009.0081302 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007932 | 688851347-43959-DETAIL-04_08_2024-GO95HV-1^06247005.0321200 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007933 | 688965238-80399-DETAIL-02_27_2023-GO95TCH-1^07216001.0298841 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007934 | 688965238-80399-DETAIL-02_27_2023-SVCENTCO-1^07216001.0298841 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007935 | 688982649-28299-DTLSB-04_17_2024-GO95MLD-1^06245007.0223404 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007936 | 688990096-51123-DTLSB-04_29_2024-SVCENTCO-1^06245007.0221541 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007937 | 689148630-23559-DETAIL-02_19_2024-ENCHRW-1^07113002.0184001 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007938 | 689324414-34889-DETAIL-06_10_2024-BIRDDMG-1^06245007.0347001 | POLE | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007939 | 689443434-26280-DRONE_HY-10_18_2023-GO95HV-1^668033/00 4/023 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007940 | 689885579-14659-DETAIL-03_28_2024-GO95HV-1^06246005.0045701 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007941 | 69050909-65229-DETAIL-06_29_2023-GO95HV-1^06244009.0243201 | OTHER | HFTD Tier 2 | Distribution | 2023-06-29 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007942 | 690692741-72369-DTLTRT-06_02_2021-GO95HV-1^668041/00 6/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007943 | 690941203-70439-DETAIL-03_14_2023-GO95HV-1^07114001.0276410 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007944 | 690941203-70439-DETAIL-03_14_2023-GO95MLD-1^07114001.0276410 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007945 | 691778951-71191-DETAIL-04_16_2024-GO95MLD-1^06145001.0139700 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007946 | 692024624-930-DETAIL-05_01_2023-GO95MLD-1^06241005.0364301 | OTHER | HFTD Tier 2 | Distribution | 2023-05-01 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007947 | 692123456-9819-DETAIL-07_24_2024-GRDRODHI-1^06244004.0190401 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007948 | 692130406-40272-DETAIL-07_05_2023-GO95HV-1^06244008.0311900 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007949 | 692549431-46883-DETAIL-10_25_2024-GO95TCH-1^07216001.0208608 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007950 | 692714295-22191-DETAIL-10_22_2024-RISEGRD-1^07216001.0208500 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007951 | 692952303-33059-DETAIL-05_29_2024-GO95HV-1^06246005.0219700 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007952 | 692962815-6645-DTLTRT-04_10_2024-BIRDDMG-1^668067/00 6/001 | POLE | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007953 | 69308381-99381-DETAIL-03_27_2023-SVCENTCO-1^06142016.0052502 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007954 | 693108937-93949-DETAIL-03_15_2023-GO95HV-1^07114001.0342701 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007955 | 69327981-72389-DTLSB-08_26_2024-GO95HV-1^06245007.0114100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007956 | 693435643-5149-DETAIL-03_16_2023-ENCHRW-1^07114001.0282400 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007957 | 693679632-88340-DTLTRT-10_03_2023-GO95HV-1^668010/00 3/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007958 | 694228418-27340-DETAIL-03_12_2025-SVCDEFLC-1^06238004.0221300 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007959 | 69426244-99890-DTLSB-05_09_2024-GO95MLD-1^06244001.0119900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007960 | 694379788-66519-DTLTRT-07_28_2022-GUYSLACK-1^668005/00 7/072 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-07-28 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007961 | 694413976-57179-DTLTRT-10_09_2023-GO95HV-1^668010/00 6/038 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007962 | 694529848-16398-ENHANCED-01_09_2025-IRSPOTOH-1^668086/00 16/011 | OTHER | Non-HFTD | Transmission | 2025-01-09 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007963 | 694529848-16398-ENHANCED-01_27_2025-IRSPOTOH-1^668086/00 16/011 | OTHER | Non-HFTD | Transmission | 2025-01-27 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007964 | 694624328-49340-DETAIL-03_17_2025-SVCDEFLC-1^06238004.0141204 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007965 | 694839435-10919-DTLTRT-08_18_2022-GO95HV-1^668005/00 11/096 | OTHER | Non-HFTD | Transmission | 2022-08-18 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007966 | 695136384-13499-DETAIL-06_10_2024-GO95HV-1^06245007.0349601 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007967 | 695280809-21701-DETAIL-04_24_2024-GO95MLD-1^06145001.0051300 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007968 | 695347701-22449-DTLSB-04_24_2024-SVCROAD-1^06245007.0225602 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007969 | 695401181-13959-DETAIL-05_16_2022-GO95MLD-1^07116001.0090800 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007970 | 695534121-18943-DETAIL-05_12_2022-GO95MLD-1^07116001.0093700 | OTHER | HFTD Tier 2 | Distribution | 2022-05-12 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007971 | 695661694-14949-DETAIL-02_26_2024-GO95HV-1^07113001.0085401 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007972 | 696100661-69818-DTLSB-02_06_2024-CUTOUTAR-1^07216001.0309700 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007973 | 696128584-46729-DTLSB-08_01_2023-GO95MLD-1^06243009.0188701 | OTHER | HFTD Tier 2 | Distribution | 2023-08-01 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007974 | 696831988-76540-DETAIL-03_20_2025-SVCROAD-1^06239003.0018105 | OTHER | Non-HFTD | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007975 | 697203295-88410-DETAIL-03_12_2025-SVCENTCO-1^06238004.0224600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007976 | 697969085-78949-DETAIL-02_23_2023-GO95MLD-1^07216001.0299710 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007977 | 698409783-96883-DETAIL-03_23_2023-GO95MLD-1^06142016.0081904 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007978 | 698459854-77511-DETAIL-10_16_2024-GO95MLD-1^07216001.0207800 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007979 | 698533430-58339-DTLSB-02_19_2024-SVCROAD-1^07216001.0261303 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007980 | 699011261-18359-DETAIL-02_21_2024-GO95HV-1^07113001.0143101 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007981 | 699465723-24839-DETAIL-03_02_2023-GO95MLD-1^07216001.0292503 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007982 | 699515935-10411-DETAIL-05_15_2024-GRDRODHI-1^06142012.0123703 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007983 | 699568338-78250-AUDIT-03_25_2025-SVCRUBCM-1^06240004.0100501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-25 | 2028-03-31 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130007984 | 699568338-78250-DETAIL-09_09_2024-SVCDEFLC-1^06240004.0100501 | OTHER | HFTD Tier 2 | Distribution | 2024-09-09 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007985 | 699650500-40669-DETAIL-11_09_2022-GO95MLD-2^06246008.0027600 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007986 | 699896933-86030-DETAIL-02_25_2025-SVCNEUT-1^06241005.0253300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007987 | 700216310-42269-DTLTRT-06_02_2021-GO95HV-1^668041/00 13/003 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007988 | 70023123-37390-DETAIL-03_07_2023-CLRTOPOL-1^07216001.0293609 | OTHER | Non-HFTD | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007989 | 700876629-50939-DETAIL-10_14_2024-SVCENTBK-1^07216001.0202202 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007990 | 70129123-52215-AUDIT-03_13_2025-GO95BLTC-1^06239004.0137301 | OTHER | HFTD Tier 3 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007991 | 701429676-91279-DETAIL-03_05_2024-GO95MLD-1^06245007.0278101 | OTHER | HFTD Tier 2 | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007992 | 701618809-57281-DETAIL-02_24_2025-GO95TCH-1^06241005.0153100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007993 | 701638575-94269-DTLTRT-10_10_2023-GUYHINS-1^668010/00 7/041 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007994 | 701655981-91631-DTLSB-09_05_2023-GUYNOINS-1^06243008.0092500 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-09-05 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130007995 | 70184829-9809-DTLSB-08_27_2024-GO95MLD-1^06245007.0120800 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007996 | 701912671-86023-DETAIL-06_17_2024-GO95BLTC-1^06246006.0239901 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007997 | 701912671-86023-DETAIL-06_17_2024-GO95MLD-1^06246006.0239901 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007998 | 701915580-17580-DETAIL-04_30_2024-GO95HV-1^06142015.0022900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130007999 | 702396634-13149-DTLSB-02_07_2024-GO95MLD-1^07216001.0199103 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008000 | 702410804-66469-DETAIL-07_25_2024-ABNDEQPM-1^06244005.0347001 | OTHER | Non-HFTD | Distribution | 2024-07-25 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008001 | 702584696-94696-DETAIL-04_15_2024-SVCENTCO-1^06145001.0246902 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008002 | 702729234-91334-DETAIL-04_25_2024-GO95HV-1^06142016.0179201 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008003 | 702933978-53383-ADMIN-03_07_2024-POLEREPL-1^06245007.0275840 | POLE | Non-HFTD | Distribution | 2024-03-07 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008004 | 702983609-90521-DTLSB-05_16_2024-GO95HV-1^06244003.0247000 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008005 | 703110496-87249-DETAIL-03_18_2024-GO95MLD-1^06245006.0127900 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008006 | 703397368-75769-DRONE_HY-08_28_2023-BIRDWST-1^668002/00 21/048 | OTHER | HFTD Tier 2 | Transmission | 2023-08-28 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008007 | 703546070-9249-DETAIL-03_09_2023-GUYHINS-1^07216001.0295501 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008008 | 703546070-9249-DETAIL-03_09_2023-SVCWIND-1^07216001.0295501 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008009 | 703600011-6539-DETAIL-07_03_2024-GO95MLD-1^06244005.0230603 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008010 | 704235763-653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 2/001 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008011 | 704658345-78345-DETAIL-11_17_2022-GO95HV-1^668001/06 1X2/001 | OTHER | HFTD Tier 2 | Transmission | 2022-11-17 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008012 | 704715988-80631-DETAIL-03_20_2024-GRDRODHI-1^06245002.0127801 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008013 | 704993151-30582-DTLSB-08_23_2023-GO95MLD-1^06243009.0133000 | OTHER | Non-HFTD | Distribution | 2023-08-23 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008014 | 70516396-26539-DTLSB-02_21_2023-GO95TCH-1^07216001.0287704 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008015 | 705508596-58113-DETAIL-02_03_2025-GO95HV-1^06239004.0244942 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008016 | 705999990-38670-DETAIL-02_04_2025-SVCDEFLC-1^06240004.0165708 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008017 | 706118169-19029-DTLSB-08_17_2023-GO95MLD-1^06243009.0131002 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008018 | 706160382-66831-DETAIL-05_05_2022-GO95MLD-1^07116001.0100001 | OTHER | HFTD Tier 2 | Distribution | 2022-05-05 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008019 | 706197814-3269-DTLTRT-10_11_2023-BIRDDMG-1^668010/00 8/040 | POLE | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008020 | 706719718-67849-DETAIL-08_01_2024-GO95HV-1^06245006.0155401 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008021 | 706719718-67849-DETAIL-08_01_2024-GO95MLD-1^06245006.0155401 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008022 | 706762883-63239-DETAIL-07_17_2024-GO95HV-1^06244005.0282300 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008023 | 706850521-66620-DETAIL-03_06_2025-CLRTOUCH-1^06240004.0274602 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008024 | 706855726-93989-DETAIL-03_18_2024-GO95MLD-1^06245006.0127604 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008025 | 706956650-19170-DETAIL-03_19_2025-GO95HV-1^06239002.0015601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008026 | 707323053-65739-DETAIL-08_05_2024-GO95HV-1^06244005.0029202 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008027 | 707409902-679-DETAIL-04_08_2024-GO95MLD-1^06147005.0222400 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008028 | 707501966-60149-DETAIL-10_08_2024-CLRTOUCH-1^07216001.0202004 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008029 | 707501966-60149-DETAIL-10_08_2024-GO95MLD-1^07216001.0202004 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008030 | 707535516-14459-DETAIL-04_01_2024-GO95MLD-1^06247005.0342500 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008031 | 707746482-44080-DETAIL-02_25_2025-GO95CL10-1^06240005.0016003 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008032 | 708056185-36410-DETAIL-03_12_2025-GO95HV-1^06238004.0223501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008033 | 708550380-26049-DTLSB-02_15_2024-GO95HV-1^07216001.0264200 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008034 | 708743408-86409-DETAIL-04_01_2024-GO95MLD-1^06147005.0094900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008035 | 708848154-59519-ADMIN-08_11_2019-POLEDERP-1^668005/00 5/095 | POLE | Non-HFTD | Transmission | 2019-08-11 | 2022-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008036 | 708984164-86164-DETAIL-03_28_2023-GO95MLD-1^06142016.0053301 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008037 | 709008796-38959-DETAIL-03_27_2024-GO95MLD-1^06247005.0320800 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008038 | 709149576-18639-DETAIL-07_10_2024-SVCENTCO-1^06244004.0215500 | OTHER | HFTD Tier 2 | Distribution | 2024-07-10 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008039 | 709197374-90860-DETAIL-01_22_2025-GO95TCH-1^06239004.0255700 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008040 | 709299426-43979-DETAIL-04_08_2024-GO95MLD-1^06147005.0236200 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008041 | 709653060-48830-DETAIL-09_25_2024-SVCDEFLC-1^06240004.0176801 | OTHER | HFTD Tier 2 | Distribution | 2024-09-25 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008042 | 709793930-92551-DETAIL-01_26_2023-GO95MLD-1^06147003.0141100 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008043 | 709793930-92551-DETAIL-01_26_2023-GO95MLD-2^06147003.0141100 | OTHER | Non-HFTD | Distribution | 2023-01-26 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008044 | 710454894-23251-DTLSB-08_02_2022-GO95MLD-1^06242005.0177101 | OTHER | HFTD Tier 2 | Distribution | 2022-08-02 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008045 | 710486388-12651-DETAIL-04_22_2024-GO95MLD-1^06145001.0119601 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008046 | 710566093-20970-DTLTRT-04_16_2024-GO95HV-1^668067/00 7/011 | OTHER | Non-HFTD | Transmission | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008047 | 710566093-44702-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 7/011 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008048 | 710607098-97051-DETAIL-03_20_2024-CONDFRAY-1^06245002.0128700 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008049 | 710805596-45159-DTLSB-09_30_2024-GO95MLD-1^06245007.0232405 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008050 | 712095378-91851-DTLSB-01_30_2023-GO95MLD-1^06248001.0369710 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008051 | 712109807-37579-DETAIL-04_09_2024-GO95STUB-1^06147005.0217003 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008052 | 712129659-12073-DETAIL-01_21_2025-BIRDDMG-1^06240004.0092401 | POLE | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008053 | 712129659-12073-DETAIL-01_21_2025-CONDCOIL-1^06240004.0092401 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008054 | 712238591-42691-DETAIL-03_23_2023-GO95MLD-1^06142016.0051002 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008055 | 712324245-65703-DETAIL-03_06_2024-SVCROAD-1^06245007.0271900 | OTHER | HFTD Tier 2 | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008056 | 712387715-18551-DTLSB-05_07_2024-GO95MLD-1^06245001.0295301 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008057 | 71249331-12559-DETAIL-05_12_2022-GUYSLACK-1^07116001.0092800 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-05-12 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008058 | 712609835-73449-DETAIL-07_29_2024-GO95HV-1^06245006.0114902 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008059 | 712625619-83099-DETAIL-01_28_2025-SVCROAD-1^06239004.0243400 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008060 | 712638323-61753-DTLTRT-04_08_2024-GO95HV-1^668062/00 2/004 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008061 | 712688659-88990-DETAIL-01_28_2025-GO95TCH-1^06239004.0245400 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008062 | 713016385-46761-DETAIL-03_09_2023-GO95TCH-1^07216001.0295508 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008063 | 713016385-46761-DETAIL-03_09_2023-GUYHINS-1^07216001.0295508 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008064 | 713276879-27879-DETAIL-03_06_2025-GO95TCH-1^06240004.0272141 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008065 | 713446664-81350-DTLTRT-11_03_2023-GO95HV-1^668010/00 14/036 | OTHER | HFTD Tier 2 | Transmission | 2023-11-03 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008066 | 713621604-36260-DETAIL-01_29_2025-GO95BLTC-1^06240004.0160800 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008067 | 713647878-77043-DETAIL-03_09_2023-GO95MLD-1^07117002.0209105 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008068 | 713742013-1859-DTLSB-02_15_2024-GO95MLD-1^07216001.0184200 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008069 | 713742013-1859-DTLSB-02_15_2024-SVCDEFLC-1^07216001.0184200 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008070 | 713742013-1859-DTLSB-02_15_2024-SVCENTCO-1^07216001.0184200 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008071 | 713850641-9080-DETAIL-02_06_2025-SVCDEFLC-1^06240004.0166207 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008072 | 713850641-9080-DETAIL-02_06_2025-SVCDEFLC-2^06240004.0166207 | OTHER | HFTD Tier 2 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008073 | 714032839-43669-DTLTRT-06_09_2021-GO95HV-1^668041/00 8/014 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008074 | 714140195-26349-DETAIL-02_27_2024-GRDRODHI-1^07113002.0184503 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008075 | 714183353-28861-DTLSB-05_28_2024-GO95MLD-1^06243001.0125300 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008076 | 714399266-87999-DTLSB-04_22_2024-SVCWIND-1^06245007.0225101 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008077 | 714543501-66230-DETAIL-03_04_2025-GO95CL10-1^06240004.0151303 | OTHER | HFTD Tier 3 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008078 | 714864643-1529-DETAIL-06_07_2023-GO95TCH-1^06244010.0273800 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008079 | 71508108-52849-DTLSB-02_28_2024-GO95MLD-1^07216001.0260901 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008080 | 715162950-11862-DTLSB-07_26_2023-GO95HV-1^06243010.0119400 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008081 | 71526139-87209-DETAIL-03_04_2024-LIGHT-1^06147004.0011301 | CONNECTION DEVICE | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008082 | 71545691-71859-DETAIL-06_05_2024-GO95HV-1^06246006.0266200 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008083 | 715617468-86650-DETAIL-01_16_2025-BIRDDMG-1^06240004.0096501 | POLE | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008084 | 715758381-73480-DETAIL-02_13_2025-GO95TCH-1^06240004.0168242 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008085 | 716180789-10912-DETAIL-07_03_2023-GO95HV-1^06244009.0130001 | OTHER | HFTD Tier 2 | Distribution | 2023-07-03 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008086 | 716235608-31409-DETAIL-04_10_2024-GO95MLD-1^06147005.0214900 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008087 | 716306493-23721-DETAIL-02_19_2025-SVCDEFLC-1^06239004.0363900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008088 | 716568165-90770-DETAIL-01_14_2025-GO95HV-1^06240004.0078800 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008089 | 716703850-11270-DETAIL-03_19_2025-GO95HV-1^06239002.0016601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008090 | 71697536-3199-DETAIL-07_10_2024-GO95MLD-1^06244004.0191800 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008091 | 717049943-88089-DETAIL-06_10_2024-GO95MLD-1^06245007.0346003 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008092 | 717153908-66908-DETAIL-03_16_2023-GO95MLD-1^07113001.0043502 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008093 | 717607802-71269-DTLSB-08_28_2024-GO95HV-1^06245007.0158500 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008094 | 717680436-26659-DETAIL-03_06_2024-SVCROAD-1^06245007.0272701 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008095 | 717732226-56359-DETAIL-03_28_2024-GO95MLD-1^06247005.0340200 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008096 | 717756156-25080-DETAIL-03_03_2025-GO95HV-1^06240004.0052101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008097 | 717784199-70333-DETAIL-03_13_2023-GO95HV-1^07117002.0289502 | OTHER | HFTD Tier 2 | Distribution | 2023-03-13 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008098 | 717784199-70333-DETAIL-03_13_2023-GO95MLD-1^07117002.0289502 | OTHER | HFTD Tier 2 | Distribution | 2023-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008099 | 71799918-95400-DTLSB-05_14_2024-GO95MLD-1^06244001.0218403 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008100 | 718074606-84606-DETAIL-01_29_2025-GO95MLD-1^06239004.0229101 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008101 | 718231143-62471-DETAIL-02_09_2023-GO95MLD-2^06146004.0086000 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008102 | 718255480-50789-DETAIL-03_21_2024-GO95MLD-1^06246005.0063500 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008103 | 71828990-67269-DTLTRT-06_02_2021-GO95HV-1^668041/00 7/004 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008104 | 718682844-43849-DETAIL-05_23_2023-GO95MLD-1^06245006.0275401 | OTHER | Non-HFTD | Distribution | 2023-05-23 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008105 | 718785988-77949-DETAIL-04_13_2023-ENCHRW-1^06245006.0223800 | OTHER | Non-HFTD | Distribution | 2023-04-13 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008106 | 719217732-24520-DETAIL-03_06_2025-SVCENTCO-1^06240004.0289001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008107 | 719277843-42079-DTLSB-01_30_2023-GO95TCH-1^06248001.0259002 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008108 | 719327068-16159-DTLTRT-06_09_2021-UNIGRDSG-1^668041/00 1/017 | OTHER | Non-HFTD | Transmission | 2021-06-09 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008109 | 719399321-53559-DTLSB-02_15_2024-GO95MLD-1^07216001.0260000 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008110 | 719646384-40484-DETAIL-03_28_2023-GO95HV-1^06143016.0322101 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008111 | 720404804-38071-DETAIL-04_17_2024-GO95HV-1^06144001.0130900 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008112 | 720777351-4391-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | Non-HFTD | Transmission | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008113 | 720777351-4391-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 1/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008114 | 720777351-5391-DTLTRT-04_10_2024-GO95HV-1^668067/00 1/003 | OTHER | Non-HFTD | Transmission | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008115 | 720777351-5391-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 1/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008116 | 720777351-65180-DTLTRT-04_10_2024-GUYNOINS-1^668067/00 1/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008117 | 720822409-9789-DETAIL-07_29_2024-GO95MLD-1^06245006.0148401 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008118 | 720848916-75379-DETAIL-03_28_2024-GO95TCH-1^06147005.0112201 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008119 | 720977643-10552-DETAIL-06_13_2023-GO95HV-1^06244010.0227301 | OTHER | HFTD Tier 2 | Distribution | 2023-06-13 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008120 | 721179554-16681-DETAIL-10_22_2024-GO95CL10-1^07216001.0208501 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008121 | 721298408-34830-DETAIL-01_14_2025-GO95MLD-1^06240004.0079841 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008122 | 721378197-59179-DETAIL-08_21_2024-GO95HV-1^06245006.0331001 | OTHER | Non-HFTD | Distribution | 2024-08-21 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008123 | 721781521-18379-DETAIL-01_24_2023-GO95MLD-1^06148004.0182203 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008124 | 721783681-96109-DTLSB-08_26_2024-GO95HV-1^06245007.0114204 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008125 | 721946761-53980-DETAIL-03_19_2025-GO95HV-1^06239001.0069602 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008126 | 722138114-70249-DETAIL-05_11_2022-GO95MLD-1^07117001.0320404 | OTHER | Non-HFTD | Distribution | 2022-05-11 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008127 | 722969591-88689-DETAIL-02_22_2023-GO95HV-1^06247002.0030001 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008128 | 723199657-50790-DETAIL-01_30_2025-GO95MLD-1^06239004.0245603 | OTHER | HFTD Tier 3 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008129 | 723271001-13859-DETAIL-06_05_2024-GO95MLD-1^06246006.0266302 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008130 | 723669786-26378-DETAIL-06_14_2023-GO95HV-1^06244010.0288500 | OTHER | HFTD Tier 2 | Distribution | 2023-06-14 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008131 | 723797451-53609-DETAIL-01_17_2023-GO95HV-1^06148004.0223003 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008132 | 723889895-52700-DETAIL-03_26_2025-GO95HV-1^06239003.0019620 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008133 | 723996670-65080-AUDIT-03_18_2025-SVCDEFLC-2^06240004.0343700 | OTHER | HFTD Tier 3 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008134 | 724282053-62049-DETAIL-02_27_2024-GO95MLD-1^07113002.0181402 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008135 | 724521634-24634-DETAIL-03_29_2023-CLRTOUCH-1^06142016.0085601 | CONDUCTOR | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008136 | 725185119-45890-DETAIL-01_16_2025-ABNDEQPM-1^06239004.0257303 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008137 | 725614684-68519-DTLTRT-08_17_2022-GO95MLD-1^668005/00 1/095 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008138 | 726458001-35569-DRONE_HY-10_06_2023-GO95HV-1^668033/00 5/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-06 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008139 | 726458001-35570-DRONE_HY-10_06_2023-GO95HV-1^668033/00 5/014 | OTHER | HFTD Tier 2 | Transmission | 2023-10-06 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008140 | 726598258-89291-DTLSB-05_16_2024-GO95HV-1^06244002.0201400 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008141 | 727116676-22400-DTLTRT-10_17_2023-GO95HV-1^668010/00 24X/008 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008142 | 727353023-57239-AUDIT-08_27_2024-GO95MLD-1^06244005.0288900 | OTHER | Non-HFTD | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008143 | 727464179-88291-DETAIL-04_18_2019-SVCROAD-1^06142012.0125202 | OTHER | Non-HFTD | Distribution | 2019-04-18 | 2022-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008144 | 727862161-66029-DETAIL-05_06_2024-SVCDEFLC-1^06142012.0123103 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008145 | 727934726-82260-DTLTRT-10_09_2023-GUYHINS-2^668010/00 2/039 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008146 | 728116179-60201-DETAIL-05_08_2024-GO95MLD-1^06142012.0120102 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008147 | 728443155-7733-DETAIL-06_10_2024-GO95HV-1^06245007.0347640 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008148 | 728443155-7733-DETAIL-06_10_2024-SVCNEUT-1^06245007.0347640 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008149 | 728706-38119-ADMIN-07_29_2024-POLEDERP-1^668005/00 3/063 | POLE | Non-HFTD | Transmission | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008150 | 729309296-899-AUDIT-07_17_2024-CONDFRAY-1^06246006.0362002 | CONDUCTOR | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008151 | 729330686-83159-DETAIL-03_21_2023-ABNDEQPM-1^07113001.0056501 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008152 | 729363448-80569-DTLTRT-07_06_2022-GO95MLD-1^668005/00 1/038 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008153 | 729469404-20149-DETAIL-03_20_2023-GO95MLD-1^07114001.0284308 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008154 | 72967373-13339-DETAIL-08_05_2024-GO95HV-1^06244005.0325200 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008155 | 729854668-77849-DETAIL-10_14_2024-SVCNEUT-1^07216001.0204303 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008156 | 729918360-47129-ADMIN-08_05_2024-GO95STUB-1^06243009.0142000 | OTHER | Non-HFTD | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008157 | 729970666-71666-DTLSB-02_15_2023-GO95HV-1^06248001.0307101 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008158 | 730114300-21449-DETAIL-04_28_2022-GO95HV-1^07116001.0093301 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008159 | 730114300-21449-DETAIL-04_28_2022-GO95MLD-1^07116001.0093301 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008160 | 730114300-21449-DETAIL-04_28_2022-GO95TCH-1^07116001.0093301 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008161 | 730114300-21449-DETAIL-04_28_2022-SVCNEUT-1^07116001.0093301 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008162 | 730206639-97770-DETAIL-01_29_2025-SVCDEFLC-1^06240004.0161403 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008163 | 730260690-2922-DETAIL-06_27_2023-GO95BLTC-1^06244009.0270200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008164 | 730260690-2922-DETAIL-06_27_2023-GO95MLD-1^06244009.0270200 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008165 | 730281003-16889-DTLSB-09_05_2023-GO95MLD-1^06243008.0263800 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008166 | 730281043-3243-DETAIL-10_12_2022-GO95HV-1^668005/08 8X5/077 | OTHER | Non-HFTD | Transmission | 2022-10-12 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008167 | 730640764-20549-DTLSB-02_26_2024-GO95MLD-1^07216001.0277601 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008168 | 730751464-27479-DETAIL-06_05_2024-GO95MLD-1^06246006.0256800 | OTHER | Non-HFTD | Distribution | 2024-06-05 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008169 | 73088473-87549-DTLSB-02_26_2024-SVCROAD-1^07216001.0277907 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008170 | 731238996-49970-DETAIL-01_23_2025-GO95CL10-1^06239004.0256646 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008171 | 731238996-49970-DETAIL-01_23_2025-GO95MLD-1^06239004.0256646 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008172 | 731319694-84009-DTLSB-04_24_2024-GO95HV-1^06245007.0223800 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008173 | 731465714-55239-DETAIL-07_17_2024-GO95HV-1^06244005.0282103 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008174 | 73200753-74330-DETAIL-03_10_2025-GO95HV-1^06240004.0066005 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008175 | 732020895-74269-DTLTRT-10_10_2023-GO95HV-1^668010/00 8/041 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008176 | 732125390-30311-DETAIL-02_23_2023-GO95HV-1^07216001.0295706 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008177 | 732125390-30311-DETAIL-02_23_2023-GO95MLD-1^07216001.0295706 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008178 | 73256324-49980-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 3/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008179 | 73256324-53211-DTLTRT-04_16_2024-GUYNOINS-1^668067/00 3/014 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008180 | 732863711-33580-DETAIL-03_20_2025-GO95HV-1^06239002.0035402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008181 | 733171805-33805-DETAIL-02_19_2025-GUYHINS-1^06240004.0100200 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-19 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008182 | 733473706-91199-DETAIL-08_20_2024-GO95TCH-1^06246004.0325800 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008183 | 733949403-4841-DETAIL-03_05_2025-GUYHINS-1^06241005.0131904 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008184 | 733949403-4841-DETAIL-03_05_2025-GUYHINS-2^06241005.0131904 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008185 | 734276579-73149-DETAIL-10_15_2024-GO95TCH-1^07216001.0204400 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008186 | 734276579-73149-DETAIL-10_15_2024-SVCROAD-1^07216001.0204400 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008187 | 734349136-49920-DRONE_HY-10_12_2023-GO95HV-1^668033/00 9/043 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008188 | 734349136-92560-DRONE_HY-10_12_2023-GO95HV-1^668033/00 9/043 | OTHER | HFTD Tier 2 | Transmission | 2023-10-12 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008189 | 734387299-12712-DETAIL-06_12_2023-GO95MLD-1^06244009.0360102 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008190 | 734413803-73803-DETAIL-03_02_2023-SVCENTCO-1^07117002.0200308 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008191 | 734775969-13833-DETAIL-03_14_2023-GO95BLTC-1^07117002.0270601 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008192 | 734775969-13833-DETAIL-03_14_2023-GO95TCH-1^07117002.0270601 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008193 | 735109948-14169-DTLTRT-10_11_2023-GO95MLD-1^668010/00 2/044 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008194 | 73519679-79500-DETAIL-04_11_2024-GO95MLD-1^06245002.0101102 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008195 | 735223493-55669-DETAIL-07_15_2024-GO95HV-1^06244005.0255500 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008196 | 735559322-51780-DETAIL-03_10_2025-GO95TCH-1^06240004.0289700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008197 | 735599745-56600-DETAIL-03_27_2025-GO95HV-1^06239003.0016714 | OTHER | HFTD Tier 2 | Distribution | 2025-03-27 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008198 | 736035053-5339-DETAIL-06_24_2024-SVCDEFLC-1^06244005.0233300 | OTHER | Non-HFTD | Distribution | 2024-06-24 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008199 | 73603850-60129-DTLSB-08_17_2023-GO95MLD-1^06243009.0131503 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008200 | 736477883-74249-DTLSB-10_07_2024-GO95MLD-1^06245007.0214000 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008201 | 736793804-4340-DTLTRT-10_04_2023-GO95HV-1^668010/00 11/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008202 | 736793804-4340-DTLTRT-10_04_2023-GUYHINS-1^668010/00 11/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008203 | 736990354-93549-DTLSB-02_07_2024-GO95HV-1^07216001.0199204 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008204 | 737492780-48149-DTLSB-02_16_2024-GO95MLD-1^07216001.0262200 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008205 | 737533140-17170-DETAIL-03_19_2025-XARMBRAC-1^06239002.0014601 | CROSSARM | HFTD Tier 2 | Distribution | 2025-03-19 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008206 | 737901929-54659-AUDIT-10_28_2024-SVCENTBK-1^07216001.0201209 | OTHER | Non-HFTD | Distribution | 2024-10-28 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008207 | 737958266-34221-DTLSB-02_01_2023-GO95TCH-1^06248001.0369603 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008208 | 737969759-49169-ADMIN-07_24_2020-INSULPLM-1^668041/00 4/020 | INSULATOR AND BUSHING | Non-HFTD | Transmission | 2020-07-24 | 2023-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008209 | 738162623-96421-DETAIL-05_23_2024-GO95HV-1^06243001.0149501 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008210 | 739075750-73979-DETAIL-11_07_2022-GO95HV-1^06247008.0361000 | OTHER | HFTD Tier 2 | Distribution | 2022-11-07 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008211 | 739407870-32159-DTLSB-09_30_2024-GO95MLD-1^06245007.0230141 | OTHER | Non-HFTD | Distribution | 2024-09-30 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008212 | 739905728-94999-DTLSB-08_22_2024-GO95HV-1^06245006.0327740 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008213 | 739905728-94999-DTLSB-08_22_2024-GO95MLD-1^06245006.0327740 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008214 | 740023151-28219-ADMIN-12_31_2018-POLEREPL-1^668005/00 3/087 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008215 | 740587141-86330-DETAIL-02_27_2025-GUYNOINS-1^06240004.0154402 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008216 | 740587141-86330-DETAIL-02_27_2025-GUYNOINS-3^06240004.0154402 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008217 | 740795698-27949-DETAIL-08_14_2024-GO95HV-1^06245005.0344700 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008218 | 740874256-58359-DETAIL-04_01_2024-GO95HV-1^06247005.0342503 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008219 | 741302782-12782-DETAIL-02_19_2025-GO95BLTC-1^06240004.0219914 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008220 | 741302782-12782-DETAIL-02_19_2025-GO95HV-1^06240004.0219914 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008221 | 741838540-97758-DETAIL-06_06_2024-GO95MLD-1^06246006.0353702 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008222 | 741851478-47690-DETAIL-01_28_2025-GO95HV-1^06239004.0246142 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008223 | 742022303-18059-DTLSB-02_14_2024-GO95MLD-1^07216001.0188000 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008224 | 742110332-70731-DETAIL-02_08_2023-GO95MLD-1^06146002.0274901 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008225 | 74234608-37669-DTLTRT-10_11_2022-GO95HV-1^668005/03 4/003 | OTHER | Non-HFTD | Transmission | 2022-10-11 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008226 | 74234608-37669-DTLTRT-10_11_2022-GO95MLD-1^668005/03 4/003 | OTHER | Non-HFTD | Transmission | 2022-10-11 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008227 | 742401213-57279-DETAIL-04_04_2024-GO95MLD-1^06247005.0293200 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008228 | 742520831-2831-DETAIL-04_25_2024-GO95MLD-1^06142016.0041002 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008229 | 742723876-64323-DTLSB-04_24_2024-GRDRODHI-1^06245007.0223642 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008230 | 742775818-22009-DETAIL-04_09_2024-GO95TCH-1^06147005.0215800 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008231 | 742819454-94554-DETAIL-03_28_2023-GO95MLD-1^06142016.0084806 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008232 | 743909828-73179-ADMIN-04_04_2024-ABNDEQPM-1^06247005.0285100 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008233 | 743909828-73179-DETAIL-04_04_2024-GO95MLD-1^06247005.0285100 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008234 | 74397256-37643-DTLSB-02_22_2023-GO95MLD-1^07216001.0289700 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008235 | 744990934-55060-DETAIL-01_23_2025-GO95TCH-1^06239004.0257809 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008236 | 745299133-95559-DETAIL-04_04_2024-GO95HV-1^06247005.0297300 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008237 | 745305290-52180-DETAIL-02_11_2025-GO95MLD-1^06240004.0349600 | OTHER | HFTD Tier 3 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008238 | 745358513-34180-DETAIL-02_03_2025-GO95TCH-1^06240004.0164900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008239 | 745358513-34180-DETAIL-02_03_2025-SVCDEFLC-1^06240004.0164900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008240 | 745431831-86279-DETAIL-03_06_2024-GO95MLD-1^06147004.0127800 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008241 | 745431831-86279-DETAIL-03_06_2024-GO95TCH-1^06147004.0127800 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008242 | 74550006-81300-DTLSB-05_14_2024-GO95MLD-1^06244001.0293900 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008243 | 745604553-62629-DETAIL-05_15_2024-GO95HV-1^06142012.0123901 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008244 | 745608796-5889-DETAIL-10_24_2022-GO95MLD-1^06247008.0315300 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008245 | 745802746-40670-DETAIL-01_14_2025-SVCDEFLC-1^06239004.0256109 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008246 | 745869738-85170-DETAIL-04_11_2023-GUYHINS-1^06240004.0167504 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-04-11 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008247 | 745913313-31439-DETAIL-03_21_2023-GUYHINS-1^07113001.0056500 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008248 | 74605926-56472-ADMIN-10_22_2024-POLEREPL-1^06244010.0344900 | POLE | HFTD Tier 2 | Distribution | 2024-10-22 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008249 | 746525213-94480-DETAIL-02_14_2025-GO95HV-1^06240004.0164509 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008250 | 747026481-72079-DETAIL-03_12_2024-GO95MLD-1^06147004.0032700 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008251 | 747026481-72079-DETAIL-03_12_2024-GRDRODHI-1^06147004.0032700 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008252 | 747092139-23139-DTLTRT-03_22_2022-GUYNOINS-1^06146005.0133004 | ANCHOR/GUY | Non-HFTD | Distribution | 2022-03-22 | 2025-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008253 | 747519018-31170-DETAIL-02_26_2025-CLRTOUCH-1^06240004.0062104 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-26 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008254 | 747697533-80259-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0347002 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008255 | 747716725-92433-DETAIL-03_02_2023-GO95MLD-1^07117002.0198200 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008256 | 747865140-87540-DTLTRT-10_26_2022-GO95MLD-1^668075/00 14/027 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008257 | 74787051-97400-DETAIL-03_12_2024-GO95HV-1^06147004.0061900 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008258 | 74787051-97400-DETAIL-03_12_2024-GO95MLD-1^06147004.0061900 | OTHER | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008259 | 747878130-53201-DETAIL-01_31_2025-GO95MLD-1^06239004.0136105 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008260 | 748263039-61599-DTLSB-04_10_2024-POLETOP-1^06245007.0222005 | POLE | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008261 | 748468641-18129-DETAIL-05_13_2024-GO95MLD-1^06142012.0123307 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008262 | 748907306-22139-DETAIL-03_25_2024-GO95MLD-1^06244005.0145001 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008263 | 748907306-22139-DETAIL-03_25_2024-SVCDEFLC-1^06244005.0145001 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008264 | 749168511-1611-DETAIL-04_30_2024-GO95HV-1^06142015.0028901 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008265 | 749332196-44079-DETAIL-04_03_2024-GUYHINS-1^06147005.0142003 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-03 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008266 | 749648829-60769-DTLTRT-06_08_2021-GO95HV-1^668041/00 5/014 | OTHER | Non-HFTD | Transmission | 2021-06-08 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008267 | 749783914-86949-DETAIL-02_26_2024-SVCDEFLC-1^07113001.0085100 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008268 | 749830708-44351-DTLSB-02_06_2023-GO95MLD-1^06247001.0019201 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008269 | 750233223-70851-DTLSB-05_22_2024-GO95MLD-1^06243001.0030301 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008270 | 750409824-58049-DTLSB-02_14_2024-GO95MLD-1^07216001.0198300 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008271 | 750427254-29190-DETAIL-03_12_2025-SVCDEFLC-1^06239003.0252900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008272 | 75042973-58450-DETAIL-01_16_2025-GO95CL10-1^06240004.0095701 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008273 | 750466244-76244-DETAIL-04_22_2024-GRDRODHI-1^06146001.0365204 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008274 | 750468333-93309-DETAIL-01_17_2023-GO95HV-1^06148004.0227800 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008275 | 751354976-31161-DTLSB-01_30_2023-GO95MLD-1^06248001.0369712 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008276 | 751701365-8261-DTLSB-02_01_2023-GO95MLD-1^06248001.0368000 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008277 | 751736224-361-DETAIL-10_21_2024-SVCWIND-1^07216001.0209604 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008278 | 75231032-23679-AUDIT-03_27_2024-SVCROAD-2^06147004.0070701 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008279 | 75231032-23679-AUDIT-04_15_2024-GRDRODHI-1^06147004.0070701 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008280 | 752319628-29999-DETAIL-04_10_2024-GO95HV-1^06147005.0212900 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008281 | 752454018-27261-DTLSB-05_16_2024-GO95HV-1^06244002.0208500 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008282 | 752591980-27670-DETAIL-02_05_2025-SVCDEFLC-1^06240004.0166205 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008283 | 752733326-2769-DTLTRT-10_12_2023-GO95MLD-1^668010/00 12/041 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008284 | 753229422-89580-DETAIL-02_12_2025-GO95HV-1^06240004.0282702 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008285 | 753507011-82899-DETAIL-07_02_2024-GO95TCH-1^06244005.0231704 | OTHER | Non-HFTD | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008286 | 753797600-50700-DETAIL-01_30_2025-ABNDEQPM-1^06240004.0162504 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008287 | 754119371-18680-DETAIL-02_14_2025-SVCDEFLC-1^06240004.0168306 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008288 | 754234178-56079-DRONE_HY-09_21_2023-GO95HV-1^668002/00 22/075 | OTHER | HFTD Tier 2 | Transmission | 2023-09-21 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008289 | 754472418-74902-DETAIL-03_06_2025-GO95TCH-1^06241005.0120200 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008290 | 755525406-510-AUDIT-04_02_2025-GRDRODHI-1^06238004.0223543 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008291 | 755547959-52859-DETAIL-10_15_2024-GO95MLD-1^07216001.0202442 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008292 | 755580684-23360-DETAIL-01_21_2025-GO95TCH-1^06239004.0255301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008293 | 755580684-23360-DETAIL-01_21_2025-SVCDEFLC-1^06239004.0255301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008294 | 755696815-25071-DETAIL-04_24_2024-GO95HV-1^06145001.0048000 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008295 | 755696815-25071-DETAIL-04_24_2024-GO95MLD-1^06145001.0048000 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008296 | 756115820-41170-DETAIL-03_19_2025-GO95HV-1^06239002.0012500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008297 | 756404523-72071-DETAIL-04_03_2023-GO95HV-1^06143014.0162200 | OTHER | HFTD Tier 2 | Distribution | 2023-04-03 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008298 | 75696794-9939-AUDIT-02_27_2024-GO95MLD-1^07216001.0197002 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008299 | 75746568-12349-DETAIL-03_21_2024-GO95MLD-1^06245006.0014000 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008300 | 75749410-20870-DETAIL-02_04_2025-SVCDEFLC-1^06240004.0167603 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008301 | 758119568-62071-DETAIL-04_22_2024-GO95MLD-1^06145001.0029000 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008302 | 758130436-16652-DETAIL-10_22_2024-GO95MLD-1^07216001.0207400 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008303 | 758325581-83669-DETAIL-06_10_2024-GO95HV-1^06245007.0349100 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008304 | 758352138-27069-ADMIN-01_31_2023-POLEDERP-1^668041/00 12/015 | POLE | Non-HFTD | Transmission | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008305 | 75851489-57439-DETAIL-03_09_2023-GO95MLD-1^07216001.0293605 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008306 | 758845799-78299-DETAIL-04_11_2024-GO95MLD-1^06245002.0109500 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008307 | 758896411-48109-ADMIN-01_17_2023-ENCHRW-1^06148004.0219500 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008308 | 758896411-48109-DETAIL-01_17_2023-SVCENTCO-1^06148004.0219500 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008309 | 759016850-41509-DTLSB-09_04_2024-GO95MLD-1^06245007.0018405 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008310 | 759103671-39459-DETAIL-02_26_2024-GO95MLD-1^07113001.0138301 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008311 | 759153688-75390-DETAIL-01_28_2025-GO95HV-1^06239004.0244411 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008312 | 759591008-21549-DETAIL-10_25_2024-GO95TCH-1^07216001.0202406 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008313 | 759760635-23951-DETAIL-02_24_2025-SVCROAD-1^06239004.0366803 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008314 | 760032325-66381-DTLSB-05_07_2024-GO95MLD-1^06245001.0297300 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008315 | 760034954-42622-DETAIL-07_11_2023-GO95HV-1^06244008.0285103 | OTHER | HFTD Tier 2 | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008316 | 760158388-19869-ADMIN-04_13_2021-COPLLEAN-1^668041/00 5/017 | POLE | Non-HFTD | Transmission | 2021-04-13 | 2024-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008317 | 760513813-69459-DETAIL-02_20_2024-GO95MLD-1^07113002.0182000 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008318 | 760806408-52181-DETAIL-05_02_2024-GO95MLD-1^06142012.0125109 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008319 | 760970516-3759-DETAIL-10_24_2024-GO95MLD-1^07216001.0200703 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008320 | 760970516-3759-DETAIL-10_24_2024-RISEGRD-1^07216001.0200703 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008321 | 761315458-4981-DETAIL-04_17_2024-GO95MLD-1^06145001.0015400 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008322 | 761348222-20319-ADMIN-12_31_2018-POLEREPL-1^668005/00 9/087 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008323 | 761488369-85870-DRONE_VS-11_13_2024-BIRDDMG-1^668014/00 3/062 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008324 | 761592502-65381-DETAIL-03_13_2024-GO95MLD-1^06147004.0070201 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008325 | 76168385-6459-DETAIL-04_24_2023-GO95MLD-1^07117003.0028500 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008326 | 761758338-29799-DETAIL-03_28_2024-GO95MLD-1^06147005.0157900 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008327 | 761911310-8981-DETAIL-03_13_2024-GO95MLD-1^06147004.0180800 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008328 | 762114475-33109-DTLSB-08_28_2024-GO95HV-1^06245007.0140002 | OTHER | HFTD Tier 2 | Distribution | 2024-08-28 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008329 | 762645201-19849-DETAIL-08_13_2024-GO95HV-1^06245005.0360506 | OTHER | Non-HFTD | Distribution | 2024-08-13 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008330 | 763196498-45612-DETAIL-06_29_2023-RISEGRD-1^06244009.0255700 | OTHER | HFTD Tier 2 | Distribution | 2023-06-29 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008331 | 76329608-29769-ADMIN-12_21_2022-GUYHINS-1^668005/00 11/032 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008332 | 763514979-81269-DTLTRT-07_05_2022-GO95MLD-1^668005/00 20/033 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008333 | 764022569-74713-DETAIL-07_23_2024-ABNDEQPM-1^06245006.0141001 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008334 | 764085835-55959-DETAIL-10_17_2024-GO95MLD-1^07216001.0202500 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008335 | 764221548-43350-DETAIL-01_16_2025-GO95CL10-1^06240004.0094901 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008336 | 764347778-47900-ENHANCED-01_27_2025-IRSPOTOH-1^668067/00 4/022 | OTHER | HFTD Tier 2 | Transmission | 2025-01-27 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008337 | 764548983-24099-DETAIL-07_11_2024-GO95HV-1^06244005.0260700 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008338 | 764756573-71999-DETAIL-03_12_2024-GO95MLD-1^06245007.0289901 | OTHER | HFTD Tier 2 | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008339 | 765181102-47980-DETAIL-02_25_2025-SVCNEUT-1^06240005.0019101 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008340 | 76520389-33949-DTLSB-02_16_2024-SVCDEFLC-1^07216001.0260102 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008341 | 7658400-47449-DETAIL-10_14_2024-GO95MLD-1^07216001.0201301 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008342 | 765850756-21002-DETAIL-02_01_2023-GO95MLD-1^06147002.0319100 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008343 | 76612248-86219-DETAIL-03_28_2024-GO95MLD-1^06147005.0122000 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008344 | 766129603-59020-DETAIL-02_26_2025-SVCDEFLC-1^06241005.0360700 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008345 | 766141229-36679-DTLSB-08_15_2023-GO95MLD-1^06243009.0243601 | OTHER | Non-HFTD | Distribution | 2023-08-15 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008346 | 766221624-61090-DETAIL-01_15_2025-SVCDEFLC-1^06240004.0099005 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008347 | 766221624-61090-DETAIL-01_15_2025-SVCNEUT-1^06240004.0099005 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008348 | 766339812-44469-DTLTRT-10_16_2023-GO95MLD-1^668010/00 11/002 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008349 | 766508810-1309-DTLSB-08_17_2023-GO95MLD-1^06243009.0131602 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008350 | 76659464-44239-DTLSB-02_07_2024-GO95TCH-1^07216001.0199307 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008351 | 767016933-12730-DETAIL-02_25_2025-SVCDEFLC-1^06240004.0150904 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008352 | 767147376-45180-DETAIL-03_17_2025-GO95HV-1^06240003.0369000 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008353 | 767368828-89602-DTLSB-05_21_2024-GO95HV-1^06244002.0243301 | OTHER | Non-HFTD | Distribution | 2024-05-21 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008354 | 767481110-41329-DETAIL-06_28_2023-GO95MLD-1^06244009.0363000 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008355 | 767639029-32969-ADMIN-02_24_2021-COPLLEAN-1^668041/00 2/018 | POLE | Non-HFTD | Transmission | 2021-02-24 | 2024-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008356 | 76798206-11100-DTLSB-02_02_2023-GO95MLD-1^06247001.0121600 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008357 | 768286448-86069-ADMIN-06_15_2021-POLEDERP-1^668005/03 18/002 | POLE | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008358 | 768286448-86069-DTLTRT-10_11_2022-GO95HV-1^668005/03 18/002 | OTHER | Non-HFTD | Transmission | 2022-10-11 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008359 | 768512714-60602-AUDIT-04_28_2023-GO95MLD-1^06248001.0277601 | OTHER | Non-HFTD | Distribution | 2023-04-28 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008360 | 769047634-36589-DTLSB-04_24_2024-GRDRODHI-1^06245007.0224806 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008361 | 769545503-43980-DETAIL-02_11_2025-GO95MLD-1^06240004.0355404 | OTHER | HFTD Tier 2 | Distribution | 2025-02-11 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008362 | 769572498-98141-DETAIL-03_06_2025-GO95BLTC-1^06241005.0164900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008363 | 769782189-51149-DETAIL-10_08_2024-CLMBTRE-1^07216001.0203005 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008364 | 770043789-33512-DETAIL-04_11_2024-GO95MLD-1^06245002.0105300 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008365 | 770101324-75512-DTLSB-05_08_2024-GO95MLD-1^06245001.0335500 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008366 | 770328001-91369-DTLTRT-06_02_2021-GO95HV-1^668041/00 4/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008367 | 77066793-53183-DTLSB-10_02_2024-GO95MLD-1^06245007.0219440 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008368 | 771025414-68431-DETAIL-01_14_2025-GO95HV-1^06239004.0255101 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008369 | 771070582-15249-DETAIL-02_20_2024-GO95MLD-1^07113002.0181006 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008370 | 771130981-40212-DTLSB-02_20_2023-GO95MLD-1^06248001.0288403 | OTHER | Non-HFTD | Distribution | 2023-02-20 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008371 | 771181821-85689-DTLSB-03_12_2018-ENCHRW-1^06148003.0139101 | OTHER | Non-HFTD | Distribution | 2018-03-12 | 2021-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008372 | 771237369-9369-DTLSB-08_23_2023-GO95CLSV-1^06243009.0231600 | OTHER | Non-HFTD | Distribution | 2023-08-23 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008373 | 771237369-9369-DTLSB-08_23_2023-SVCWIND-1^06243009.0231600 | OTHER | Non-HFTD | Distribution | 2023-08-23 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008374 | 77149886-69419-ADMIN-07_29_2024-POLEDERP-1^668005/00 3/070 | POLE | Non-HFTD | Transmission | 2024-07-29 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008375 | 772004372-58831-DETAIL-03_04_2025-GO95MLD-1^06241005.0130705 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008376 | 772033154-63159-DETAIL-08_15_2024-GO95MLD-1^06246005.0130101 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008377 | 772194336-91699-DETAIL-08_19_2024-GO95MLD-1^06246004.0328800 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008378 | 773048158-59350-DETAIL-03_20_2025-BIRDDMG-1^06239003.0016203 | POLE | HFTD Tier 2 | Distribution | 2025-03-20 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008379 | 773157776-70970-DETAIL-01_23_2025-GO95MLD-1^06239004.0256740 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008380 | 773508891-92339-DETAIL-06_25_2024-GO95MLD-1^06244005.0236001 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008381 | 773570893-16799-DTLSB-09_08_2023-GO95MLD-1^06243008.0263801 | OTHER | HFTD Tier 2 | Distribution | 2023-09-08 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008382 | 773749771-81359-DETAIL-02_28_2024-SVCENTCO-1^07113001.0032301 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008383 | 773995185-69622-DTLSB-05_08_2024-GO95MLD-1^06244001.0031800 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008384 | 774222211-57959-DETAIL-02_21_2024-CLRTOUCH-1^07113001.0141000 | CONDUCTOR | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008385 | 774640561-89009-DETAIL-06_12_2024-GRDRODHI-1^06244005.0241100 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008386 | 774847159-59159-DETAIL-05_30_2024-GO95HV-1^06246005.0273001 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008387 | 774986832-54559-DETAIL-02_27_2024-GO95MLD-1^07113002.0182402 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008388 | 774986832-54559-DETAIL-02_27_2024-GUYHINS-1^07113002.0182402 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008389 | 775182231-12829-DETAIL-05_13_2024-GO95MLD-1^06142012.0122206 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008390 | 775253052-45540-DTLTRT-10_03_2023-GO95HV-1^668010/00 13/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008391 | 775308970-80179-DTLSB-06_23_2020-UNIGRDSG-1^06148001.0341600 | OTHER | Non-HFTD | Distribution | 2020-06-23 | 2023-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008392 | 775564069-98622-DETAIL-03_09_2023-GO95MLD-1^07216001.0294503 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008393 | 775704691-50822-DETAIL-04_25_2024-GO95MLD-1^06142016.0175903 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008394 | 775720468-34599-DETAIL-08_14_2024-GO95MLD-1^06245005.0344001 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008395 | 775880721-77939-DETAIL-06_12_2024-GO95MLD-1^06244005.0242100 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008396 | 776349483-89669-DTLTRT-06_08_2021-GO95HV-1^668041/00 7/010 | OTHER | Non-HFTD | Transmission | 2021-06-08 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008397 | 776399661-9730-DETAIL-01_28_2025-SVCDEFLC-1^06240004.0171900 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008398 | 776746876-47249-DETAIL-03_18_2024-GO95MLD-1^06245006.0128804 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008399 | 77674750-94750-DTLTRT-04_25_2024-SVCWIND-1^06245007.0228502 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008400 | 776956484-9484-DETAIL-10_22_2024-GO95MLD-1^07216001.0207204 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008401 | 777133633-22709-DETAIL-08_30_2021-SVCWIND-1^06148004.0354410 | OTHER | Non-HFTD | Distribution | 2021-08-30 | 2024-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008402 | 777276726-72479-DETAIL-01_24_2023-GO95CL10-1^06148004.0182101 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008403 | 777735391-19879-DTLSB-02_13_2023-GO95HV-1^06248001.0276000 | OTHER | Non-HFTD | Distribution | 2023-02-13 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008404 | 777955324-82143-DETAIL-09_27_2021-GO95MLD-1^06148004.0355415 | OTHER | Non-HFTD | Distribution | 2021-09-27 | 2024-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008405 | 778258499-20129-DETAIL-05_08_2024-GO95MLD-1^06142012.0120010 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008406 | 77851893-4700-DTLSB-02_06_2023-GO95MLD-1^06248001.0243100 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008407 | 778679778-50250-DETAIL-03_26_2025-GO95HV-1^06239003.0018302 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008408 | 779027717-88490-DETAIL-02_03_2025-GO95HV-1^06239004.0244847 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008409 | 77920721-40020-DETAIL-03_06_2025-GO95HV-1^06240004.0274500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008410 | 779315401-41469-DETAIL-02_23_2023-GO95HV-1^668002/00 10/030 | OTHER | HFTD Tier 2 | Transmission | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008411 | 779516951-21473-DETAIL-03_02_2023-SVCDEFLC-1^07117002.0201308 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008412 | 779725598-1730-DETAIL-02_27_2025-GO95MLD-1^06240003.0305100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008413 | 779773513-49579-DTLTRT-10_02_2023-GO95HV-1^668010/00 6/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008414 | 779773513-49579-DTLTRT-10_02_2023-GO95MLD-1^668010/00 6/033 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008415 | 779894521-39779-AUDIT-03_27_2024-GO95MLD-1^06147004.0085900 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008416 | 779943278-83570-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0222603 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008417 | 780575662-12080-DETAIL-02_25_2025-GO95TCH-1^06240005.0018300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008418 | 780948823-69132-DETAIL-02_16_2023-ABNDEQPM-1^06247002.0165400 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008419 | 780948823-69132-DETAIL-02_16_2023-ABNDEQPM-2^06247002.0165400 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008420 | 781139191-47249-DETAIL-02_21_2024-SVCENTCO-1^07113002.0180105 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008421 | 781405174-21549-DTLSB-02_07_2024-GO95HV-1^07216001.0199100 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008422 | 781572304-6349-ADMIN-06_19_2024-POLEDERP-1^07216001.0198311 | POLE | Non-HFTD | Distribution | 2024-06-19 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008423 | 781680856-69449-DETAIL-10_24_2024-GO95MLD-1^07216001.0201402 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008424 | 781690723-7230-DETAIL-03_04_2025-GO95HV-1^06240004.0063601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008425 | 781769086-31186-DTLSB-09_05_2024-GO95HV-1^06245006.0076500 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008426 | 782130241-84189-DTLSB-08_27_2024-GRDRODHI-1^06245007.0115900 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008427 | 782174153-56419-DTLTRT-08_16_2022-POLETOP-1^668005/00 4/092 | POLE | Non-HFTD | Transmission | 2022-08-16 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008428 | 782306706-15672-DETAIL-08_08_2024-GO95HV-1^06245006.0099141 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008429 | 782561202-51252-DETAIL-06_19_2023-GO95MLD-1^06244010.0261400 | OTHER | Non-HFTD | Distribution | 2023-06-19 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008430 | 782567918-83469-DTLTRT-07_06_2022-GO95HV-1^668005/00 3/037 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008431 | 782567918-83469-DTLTRT-07_06_2022-GO95MLD-1^668005/00 3/037 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008432 | 782952593-50799-DTLSB-08_25_2023-GO95MLD-1^06243008.0240800 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008433 | 783453496-86299-DETAIL-04_01_2024-CLRTOUCH-1^06147005.0117800 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008434 | 783453496-86299-DETAIL-04_01_2024-GO95HV-1^06147005.0117800 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008435 | 783453496-86299-DETAIL-04_01_2024-GO95TCH-1^06147005.0117800 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008436 | 783466324-19960-DETAIL-02_03_2025-GO95MLD-1^06239004.0134044 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008437 | 783814014-18949-DETAIL-10_22_2024-CLRTOUCH-1^07216001.0208805 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008438 | 783814014-18949-DETAIL-10_22_2024-GO95MLD-1^07216001.0208805 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008439 | 783873378-5099-ADMIN-07_19_2024-POLETOP-1^06245005.0061600 | POLE | Non-HFTD | Distribution | 2024-07-19 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008440 | 783873378-5099-AUDIT-04_05_2024-XARMSPCR-1^06245005.0061600 | CROSSARM | Non-HFTD | Distribution | 2024-04-05 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008441 | 783873378-5099-DETAIL-03_18_2024-GO95MLD-1^06245005.0061600 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008442 | 784204989-68829-DETAIL-05_09_2024-GO95HV-1^06142012.0121410 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008443 | 784824649-57442-DRONE_VS-11_13_2024-BIRDDMG-1^668038/00 5/064 | POLE | HFTD Tier 2 | Transmission | 2024-11-13 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008444 | 784898612-62742-DTLTRT-06_22_2021-LIGHT-1^668041/00 7/030 | CONNECTION DEVICE | Non-HFTD | Transmission | 2021-06-22 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008445 | 785046981-37939-DETAIL-06_12_2024-GO95MLD-1^06244005.0248940 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008446 | 785046981-37939-DETAIL-06_12_2024-GO95MLD-2^06244005.0248940 | OTHER | Non-HFTD | Distribution | 2024-06-12 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008447 | 785155288-72039-DETAIL-07_30_2024-GO95MLD-1^06244005.0355401 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008448 | 785277398-13959-DTLTRT-06_30_2022-ABNDEQPM-1^668005/00 10/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008449 | 78528238-32149-DETAIL-10_10_2024-GO95MLD-1^07216001.0204108 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008450 | 785350468-22468-DETAIL-02_28_2023-CLRTOUCH-1^07216001.0298606 | CONDUCTOR | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008451 | 785350468-22468-DETAIL-02_28_2023-GUYHINS-1^07216001.0298606 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008452 | 97295143-47880-DETAIL-03_10_2025-GO95HV-1^06239002.0180501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008453 | 973144739-75209-DETAIL-04_09_2024-GO95HV-1^06147005.0217100 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008454 | 973261800-77509-DTLSB-09_03_2024-GO95HV-1^06245007.0017000 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008455 | 973861359-59073-DETAIL-03_07_2023-GO95TCH-1^07117002.0207802 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008456 | 973861359-59073-DETAIL-03_07_2023-GUYHINS-1^07117002.0207802 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008457 | 785412681-40559-DETAIL-02_20_2024-ENCHRW-1^07113001.0139201 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008458 | 785883256-30169-DTLTRT-10_12_2023-GO95MLD-1^668010/00 8/042 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008459 | 785959958-93943-DTLSB-04_23_2024-GO95HV-1^06245007.0223941 | OTHER | HFTD Tier 2 | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008460 | 786104514-22799-DETAIL-02_17_2025-SVCROOF-1^06240004.0166643 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008461 | 786122268-81570-DETAIL-01_29_2025-GO95TCH-1^06240004.0161402 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008462 | 786217613-9429-DETAIL-05_09_2024-GO95MLD-1^06142012.0120602 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008463 | 786376234-12852-DETAIL-10_16_2024-GO95MLD-1^07216001.0205703 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008464 | 786376234-12852-DETAIL-10_16_2024-GO95TCH-1^07216001.0205703 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008465 | 786592339-66109-ADMIN-03_04_2024-GO95TCH-1^06147004.0017300 | OTHER | Non-HFTD | Distribution | 2024-03-04 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008466 | 786626503-57452-DETAIL-06_21_2023-GO95MLD-1^06244009.0309501 | OTHER | Non-HFTD | Distribution | 2023-06-21 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008467 | 787605301-47401-DETAIL-03_30_2023-GO95MLD-1^06142016.0055002 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008468 | 788056361-75279-DTLSB-04_23_2024-GRDRODHI-2^06245007.0226700 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008469 | 788226370-97370-DTLSB-02_22_2023-GO95MLD-1^07216001.0288601 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008470 | 788320823-62350-DETAIL-01_31_2025-GO95HV-1^06239004.0136203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008471 | 788324144-13810-DETAIL-03_17_2025-GO95HV-1^06238004.0157203 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008472 | 974136241-56241-DETAIL-01_30_2025-SVCDEFLC-1^06240004.0162604 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008473 | 974678536-72670-DETAIL-01_22_2025-GO95HV-1^06239004.0254500 | OTHER | HFTD Tier 3 | Distribution | 2025-01-22 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008474 | 974713941-87219-ADMIN-12_31_2018-POLEREPL-1^668005/00 1/087 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008475 | 974920931-38029-DETAIL-05_07_2024-SVCDEFLC-1^06142012.0123208 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008476 | 974927043-30143-DETAIL-04_29_2024-GO95MLD-1^06142016.0078900 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008477 | 975611084-95979-DTLTRT-10_30_2023-GO95HV-1^668010/00 1/015 | OTHER | HFTD Tier 2 | Transmission | 2023-10-30 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008478 | 9757039-69553-DTLSB-04_29_2024-GO95TCH-1^06245007.0226446 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008479 | 975760606-90606-DETAIL-01_29_2025-GO95MLD-1^06239004.0231000 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008480 | 975935786-33590-DTLTRT-10_16_2023-GO95HV-1^668010/00 11X/008 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008481 | 976084861-16893-DETAIL-04_11_2024-GO95HV-1^06245002.0143500 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008482 | 788326686-68686-DTLSB-02_28_2024-SVCDEFLC-1^07216001.0273801 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008483 | 788523894-79910-DETAIL-03_13_2025-GO95HV-1^06238004.0150001 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008484 | 788703292-24292-DETAIL-04_19_2023-GO95MLD-1^06240004.0167550 | OTHER | HFTD Tier 2 | Distribution | 2023-04-19 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008485 | 788854981-25030-DTLTRT-10_05_2023-GO95HV-1^668010/00 17/027 | OTHER | HFTD Tier 2 | Transmission | 2023-10-05 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008486 | 788951793-3793-DETAIL-04_29_2024-SVCROAD-1^06142016.0068000 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008487 | 789259021-75330-DTLTRT-10_05_2023-GUYHINS-1^668010/00 12/028 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-05 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008488 | 789754329-56973-DETAIL-03_08_2023-GO95BLTC-1^07117002.0207501 | OTHER | HFTD Tier 2 | Distribution | 2023-03-08 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008489 | 789754329-56973-DETAIL-03_08_2023-GUYHINS-1^07117002.0207501 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-03-08 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008490 | 789760096-13159-DTLSB-09_30_2024-GO95MLD-1^06245007.0231303 | OTHER | Non-HFTD | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008491 | 789806476-46609-DETAIL-08_08_2024-GO95MLD-1^06245006.0092701 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008492 | 790122168-56943-DETAIL-03_09_2023-GO95MLD-1^07117002.0209106 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008493 | 79023173-83339-DETAIL-03_16_2023-GO95CL10-1^07114001.0205002 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008494 | 79023173-83339-DETAIL-03_16_2023-GO95HV-1^07114001.0205002 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008495 | 79025024-64234-DTLTRT-06_08_2021-GO95HV-1^668041/00 1/014 | OTHER | Non-HFTD | Transmission | 2021-06-08 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008496 | 790317128-32219-DETAIL-02_28_2023-GO95TCH-1^07216001.0298840 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008497 | 79052506-9859-DETAIL-04_02_2024-BIRDDMG-1^06247005.0355700 | POLE | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008498 | 790767370-68570-DETAIL-02_13_2025-GO95HV-1^06240004.0169002 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008499 | 790836359-71409-DETAIL-04_09_2024-CUTOUTAR-1^06147005.0217601 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008500 | 790836359-71409-DETAIL-04_09_2024-GO95HV-1^06147005.0217601 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008501 | 790836359-71409-DETAIL-04_09_2024-GUYHINS-1^06147005.0217601 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008502 | 791176347-87590-DETAIL-02_03_2025-GO95HV-1^06239004.0244843 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008503 | 791182866-74662-DTLSB-02_01_2023-GO95MLD-1^06248001.0368701 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008504 | 792555829-94349-DTLSB-02_16_2024-GO95MLD-1^07216001.0261102 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008505 | 792917956-40672-DTLSB-01_30_2023-ABNDEQPM-1^06248001.0369901 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008506 | 792974819-40349-DTLSB-02_26_2024-GO95HV-1^07216001.0262800 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008507 | 79309604-32704-DETAIL-05_16_2023-ABNDEQPM-1^06245006.0277402 | OTHER | Non-HFTD | Distribution | 2023-05-16 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008508 | 793161404-66679-DTLSB-02_07_2023-GO95TCH-1^06248001.0158100 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008509 | 793208429-61630-DRONE_HY-09_13_2023-GO95HV-1^668002/00 18/060 | OTHER | HFTD Tier 2 | Transmission | 2023-09-13 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008510 | 793327204-34360-ADMIN-01_16_2025-GO95TCH-1^06239004.0256209 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008511 | 793327204-34360-DETAIL-01_16_2025-SVCROAD-1^06239004.0256209 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008512 | 793467963-19972-DETAIL-04_24_2024-GO95MLD-1^06245001.0017501 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008513 | 793578783-83898-ADMIN-06_15_2021-POLEDERP-1^668005/03 18/003 | POLE | Non-HFTD | Transmission | 2021-06-15 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008514 | 793797551-67219-ADMIN-12_31_2018-POLEREPL-1^668005/00 2/087 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008515 | 793903359-19129-DETAIL-05_13_2024-GO95MLD-1^06142012.0123305 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008516 | 794254106-74106-DETAIL-01_29_2025-GO95MLD-1^06239004.0251700 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008517 | 794359904-89549-DETAIL-03_15_2023-GO95MLD-1^07114001.0284304 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008518 | 794393071-64672-DETAIL-05_06_2024-GO95HV-1^06142012.0123004 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008519 | 794528495-19972-DTLSB-05_08_2024-GO95MLD-1^06244001.0032700 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008520 | 795069089-21759-DETAIL-05_10_2022-GO95MLD-1^07116001.0093102 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008521 | 79519160-32270-DETAIL-03_11_2025-BIRDDMG-1^06238003.0018902 | POLE | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008522 | 795238673-85050-DETAIL-01_24_2025-GO95HV-1^06239004.0258602 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008523 | 795280811-86849-DETAIL-04_30_2024-GO95HV-1^06142015.0030901 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008524 | 795303409-69599-DETAIL-07_30_2024-SVCDEFLC-1^06244005.0349602 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008525 | 795742660-50660-DTLTRT-10_26_2022-GO95MLD-1^668075/00 1/028 | OTHER | Non-HFTD | Transmission | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008526 | 795771070-2872-DETAIL-05_06_2024-GO95MLD-1^06142012.0123007 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008527 | 795795953-27953-DETAIL-03_23_2023-GO95MLD-1^06142016.0081901 | OTHER | Non-HFTD | Distribution | 2023-03-23 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008528 | 796207814-82459-DTLSB-02_26_2024-GO95MLD-1^07216001.0277703 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008529 | 796593118-96512-DETAIL-06_20_2023-SVCENTCO-1^06244009.0356001 | OTHER | Non-HFTD | Distribution | 2023-06-20 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008530 | 79694563-75440-DTLTRT-10_04_2023-GO95HV-1^668010/00 6/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008531 | 79694563-75440-DTLTRT-10_04_2023-GO95MLD-1^668010/00 6/035 | OTHER | Non-HFTD | Transmission | 2023-10-04 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008532 | 797174590-77789-DETAIL-01_30_2023-GO95MLD-1^06148003.0223900 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008533 | 797568233-60949-DETAIL-10_21_2024-ABNDEQPM-1^07216001.0209401 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008534 | 798254478-70539-DTLSB-02_27_2024-GO95MLD-1^07216001.0260904 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008535 | 798254478-70539-DTLSB-02_27_2024-GUYHINS-1^07216001.0260904 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008536 | 798421518-1243-DTLSB-04_30_2024-SVCWIND-1^06245007.0220843 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008537 | 798661209-58582-DTLSB-05_07_2024-GO95MLD-1^06245002.0137000 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008538 | 798780911-70280-DETAIL-02_27_2025-GUYHINS-1^06240004.0235700 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008539 | 799259371-4369-DTLTRT-06_02_2021-GO95HV-1^668041/00 8/005 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008540 | 799368144-19249-DTLSB-02_07_2024-GO95TCH-1^07216001.0199104 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008541 | 799487483-81490-DETAIL-06_27_2024-SVCDEFLC-1^06241004.0313100 | OTHER | HFTD Tier 2 | Distribution | 2024-06-27 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008542 | 799577194-68194-DETAIL-06_15_2023-GO95MLD-1^06244009.0291702 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008543 | 799592365-89082-DTLSB-02_19_2024-GO95MLD-1^07216001.0264501 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008544 | 800256663-35529-DTLSB-07_26_2023-GO95MLD-1^06243009.0087902 | OTHER | HFTD Tier 2 | Distribution | 2023-07-26 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008545 | 800668449-51353-DTLSB-04_17_2024-SVCWIND-1^06245007.0225341 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008546 | 801273259-11559-DETAIL-03_01_2023-GO95MLD-1^07216001.0292641 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008547 | 801451891-72829-DETAIL-05_13_2024-GO95MLD-1^06142012.0122407 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008548 | 801475824-58959-DTLSB-02_06_2024-GO95MLD-1^07216001.0309702 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008549 | 801602984-7460-DETAIL-01_23_2025-GO95BLTC-1^06239004.0257805 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008550 | 802112441-45202-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 3/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008551 | 802364829-61092-DTLSB-05_28_2024-GO95HV-1^06244003.0284601 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008552 | 803321823-64259-DETAIL-06_11_2024-SVCDEFLC-1^06245007.0345102 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008553 | 803370960-27570-DETAIL-02_04_2025-GO95HV-1^06240004.0167602 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008554 | 803673344-43749-DETAIL-10_21_2024-GO95HV-1^07216001.0209607 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008555 | 803909363-21009-DETAIL-10_26_2022-GO95HV-1^06246009.0126601 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008556 | 803938004-8839-DETAIL-10_16_2024-GO95MLD-1^07216001.0206803 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008557 | 804243826-82202-DETAIL-04_23_2024-GO95HV-1^06145001.0035301 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008558 | 804517623-41849-DETAIL-10_21_2024-GO95TCH-1^07216001.0209340 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008559 | 804627468-20168-DETAIL-02_28_2023-GO95MLD-1^07216001.0298601 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008560 | 804627468-20168-DETAIL-02_28_2023-GUYHINS-1^07216001.0298601 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008561 | 804803754-80702-DTLSB-01_30_2023-GO95HV-1^06248001.0257002 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008562 | 80496892-31779-DETAIL-02_14_2023-GO95MLD-1^06247002.0112900 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008563 | 804983116-1861-DETAIL-02_24_2025-SVCENTCO-1^06239004.0367800 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008564 | 805050561-29659-DETAIL-06_17_2024-GRDRODHI-1^06246006.0239200 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008565 | 805169117-66099-DTLSB-10_03_2024-GO95HV-1^06245006.0336400 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008566 | 805236558-35849-DTLSB-02_20_2024-SVCWIND-1^07216001.0261508 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008567 | 805265449-66990-DETAIL-01_28_2025-GO95HV-1^06239004.0245401 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008568 | 80552008-559-DETAIL-05_16_2022-GO95MLD-1^07116001.0059300 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008569 | 80552008-559-DETAIL-05_16_2022-POLETOP-1^07116001.0059300 | POLE | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008570 | 80556841-67841-DETAIL-06_11_2024-GO95HV-1^06245007.0345700 | OTHER | Non-HFTD | Distribution | 2024-06-11 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008571 | 80556841-67841-DETAIL-06_11_2024-GO95MLD-1^06245007.0345700 | OTHER | Non-HFTD | Distribution | 2024-06-11 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008572 | 806020133-56721-DETAIL-02_18_2025-SVCROAD-1^06239004.0361404 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008573 | 80643456-25012-DETAIL-05_10_2022-GO95HV-1^07116001.0091401 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008574 | 80643456-25012-DETAIL-05_10_2022-GO95MLD-1^07116001.0091401 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008575 | 806831391-33213-DETAIL-07_06_2023-GO95MLD-1^06244008.0325903 | OTHER | HFTD Tier 2 | Distribution | 2023-07-06 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008576 | 807107471-95589-DETAIL-06_06_2024-GO95MLD-1^06246006.0264000 | OTHER | Non-HFTD | Distribution | 2024-06-06 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008577 | 80710983-78679-DETAIL-08_20_2024-GO95HV-1^06246004.0185240 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008578 | 807229931-49529-DTLSB-08_07_2023-GO95STUB-1^06243009.0281805 | OTHER | Non-HFTD | Distribution | 2023-08-07 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008579 | 807892099-15399-DTLTRT-10_24_2022-GO95HV-1^668075/00 17/024 | OTHER | Non-HFTD | Transmission | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008580 | 807894671-59689-DETAIL-01_09_2023-GO95MLD-1^06148003.0141200 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008581 | 808313579-75949-DTLSB-02_19_2024-GO95HV-1^07216001.0261206 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008582 | 80871128-28610-DETAIL-04_22_2024-GO95MLD-1^06145001.0029600 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008583 | 80871128-28610-DETAIL-04_22_2024-POLISSUE-1^06145001.0029600 | POLE | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008584 | 808836875-98663-DETAIL-04_24_2023-GO95HV-1^07117003.0025101 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008585 | 809072736-52380-DETAIL-01_22_2025-GO95TCH-1^06239004.0255543 | OTHER | HFTD Tier 2 | Distribution | 2025-01-22 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008586 | 809422045-38479-DETAIL-08_07_2024-GO95MLD-1^06245008.0215701 | OTHER | HFTD Tier 2 | Distribution | 2024-08-07 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008587 | 809444713-36049-DETAIL-03_01_2023-GO95MLD-1^07216001.0291702 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008588 | 809597945-18039-DETAIL-02_27_2023-GO95MLD-1^07216001.0298806 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008589 | 809597945-18039-DETAIL-02_27_2023-SVCWIND-1^07216001.0298806 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008590 | 809697678-69822-DETAIL-02_05_2018-ENCHRW-1^06247001.0019902 | OTHER | Non-HFTD | Distribution | 2018-02-05 | 2021-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008591 | 809807299-89749-DTLSB-02_26_2024-GO95HV-1^07216001.0262901 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008592 | 809807299-89749-DTLSB-02_26_2024-GO95MLD-1^07216001.0262901 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008593 | 810017891-43080-DETAIL-03_19_2025-GO95HV-1^06239001.0053701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008594 | 810198066-12049-DETAIL-08_06_2024-GO95HV-1^06245004.0334100 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008595 | 810408178-96899-DETAIL-07_30_2024-GO95HV-1^06244005.0355100 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008596 | 810965519-98519-DETAIL-03_30_2023-GO95MLD-1^06142016.0054300 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008597 | 811120016-80332-DTLSB-05_14_2024-GO95MLD-1^06244001.0294801 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008598 | 811142384-95032-DETAIL-03_06_2025-GRDRODHI-1^06241005.0120504 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008599 | 811452666-899-DETAIL-03_25_2024-GO95CL10-1^06147005.0141901 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008600 | 811724138-38549-DTLSB-02_22_2024-GO95MLD-1^07216001.0263902 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008601 | 811881406-5259-DETAIL-03_22_2024-GO95MLD-1^06247005.0339202 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008602 | 811950613-98332-DTLSB-05_28_2024-SVCROAD-1^06243001.0126301 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008603 | 812246763-96429-DTLSB-09_06_2023-GO95HV-1^06243007.0185601 | OTHER | HFTD Tier 2 | Distribution | 2023-09-06 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008604 | 812275808-27599-ADMIN-08_05_2024-GO95STUB-1^06246012.0119503 | OTHER | HFTD Tier 2 | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008605 | 812792139-53240-DETAIL-03_24_2025-GO95HV-1^06238004.0011402 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008606 | 812850580-80909-DTLSB-08_27_2024-GO95HV-1^06245007.0014102 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008607 | 812884410-68070-DETAIL-03_19_2025-GO95HV-1^06239002.0011501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008608 | 813037370-38669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 10/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008609 | 813092808-14730-DETAIL-02_17_2025-GO95MLD-1^06240003.0304000 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008610 | 813776320-96962-DTLSB-07_17_2023-GO95MLD-1^06243010.0117700 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008611 | 813797845-1389-DTLSB-09_04_2024-GO95MLD-1^06245007.0142902 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008612 | 813837536-88069-DTLTRT-10_23_2023-GO95HV-1^668010/00 15/042 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008613 | 813959629-84249-DETAIL-03_09_2023-GUYHINS-1^07216001.0294601 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008614 | 814204068-67050-DETAIL-03_25_2025-SVCROAD-1^06239003.0019413 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008615 | 814204068-67050-DETAIL-03_25_2025-SVCROAD-2^06239003.0019413 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008616 | 815098910-74309-DETAIL-03_05_2024-CONDFRAY-1^06147004.0022000 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008617 | 815772678-5142-DETAIL-03_18_2024-GO95MLD-1^06245002.0035900 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008618 | 81582632-10750-DETAIL-03_25_2025-SVCDEFLC-1^06239003.0018409 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008619 | 815996070-72970-DETAIL-03_20_2025-GO95HV-1^06239002.0025502 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008620 | 816117740-97870-DETAIL-03_20_2025-GO95HV-1^06239002.0020501 | OTHER | HFTD Tier 2 | Distribution | 2025-03-20 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008621 | 816448351-58380-DETAIL-02_12_2025-GO95HV-1^06240004.0282902 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008622 | 816693176-38723-DTLSB-04_30_2024-GO95TCH-1^06245007.0220743 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008623 | 816790411-71529-DETAIL-05_08_2024-ABNDEQPM-1^06142012.0120003 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008624 | 816900893-41649-DETAIL-03_02_2023-GO95HV-1^07216001.0292507 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008625 | 816900893-41649-DETAIL-03_02_2023-GO95MLD-1^07216001.0292507 | OTHER | Non-HFTD | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008626 | 817424278-20099-DETAIL-08_14_2024-ABNDEQPM-1^06245005.0341000 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008627 | 817672890-27789-DETAIL-01_09_2023-GO95HV-1^06148003.0153001 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008628 | 817672890-27789-DETAIL-01_09_2023-GO95MLD-1^06148003.0153001 | OTHER | Non-HFTD | Distribution | 2023-01-09 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008629 | 817917591-47579-DTLTRT-10_03_2023-GUYHINS-1^668010/00 12/030 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-03 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008630 | 817988410-73449-DETAIL-03_16_2023-GO95MLD-1^07113001.0045500 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008631 | 817988410-73449-DETAIL-03_16_2023-GUYHINS-1^07113001.0045500 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008632 | 818007221-97331-DETAIL-02_27_2025-GO95HV-1^06241005.0178901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008633 | 818281441-469-DTLTRT-10_24_2022-GO95MLD-1^668001/00 1/024 | OTHER | Non-HFTD | Transmission | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008634 | 818281441-469-DTLTRT-10_24_2022-GUYHINS-1^668001/00 1/024 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-24 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008635 | 818508565-43829-DETAIL-05_16_2024-GO95MLD-1^06142012.0121900 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008636 | 818665516-85209-DETAIL-08_08_2024-GUYNOINS-1^06245006.0099940 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-08 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008637 | 818678934-97440-DETAIL-02_25_2025-BIRDDMG-1^06240004.0218800 | POLE | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008638 | 819266351-94880-DETAIL-03_19_2025-GO95HV-1^06239001.0066601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008639 | 819360553-19049-DTLSB-02_06_2024-GO95HV-1^07216001.0309800 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008640 | 81946208-55849-DTLSB-02_21_2024-GO95MLD-1^07216001.0261400 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008641 | 819834544-4860-DETAIL-01_15_2025-GO95HV-1^06239004.0255200 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008642 | 820435704-65704-DETAIL-01_16_2023-SVCDEFLC-1^06240004.0091503 | OTHER | HFTD Tier 2 | Distribution | 2023-01-16 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008643 | 820678451-86720-DETAIL-03_06_2025-GO95HV-1^06240004.0272302 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008644 | 820678451-86720-DETAIL-03_06_2025-PWRTRN-1^06240004.0272302 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008645 | 82082624-6459-DTLSB-02_27_2024-GO95HV-1^07216001.0279902 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008646 | 821111934-34262-DTLSB-05_07_2024-GO95MLD-1^06245001.0192200 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008647 | 821192669-65059-ADMIN-06_24_2024-POLEDERP-1^07116001.0093202 | POLE | HFTD Tier 2 | Distribution | 2024-06-24 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008648 | 821192669-65059-DETAIL-04_28_2022-GO95CL10-1^07116001.0093202 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008649 | 821192669-65059-DETAIL-04_28_2022-GO95TCH-1^07116001.0093202 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008650 | 821556990-36409-DETAIL-03_05_2024-CONDFRAY-1^06147004.0020300 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-05 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008651 | 821580561-38129-DETAIL-05_07_2024-SVCNEUT-1^06142012.0122005 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008652 | 821595223-90500-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 1/004 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008653 | 821605349-77659-DETAIL-03_28_2024-GO95HV-1^06246005.0043702 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008654 | 821829974-69379-DETAIL-07_03_2024-GO95MLD-1^06244005.0230841 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008655 | 821829974-69379-DETAIL-07_03_2024-GRDRODHI-2^06244005.0230841 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008656 | 822182984-24094-DETAIL-03_29_2023-GO95MLD-1^06142016.0084904 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008657 | 822233286-89272-DETAIL-04_18_2024-GO95HV-1^06145001.0363200 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008658 | 822320650-62650-DETAIL-07_30_2024-GO95MLD-1^06244005.0344901 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008659 | 822647014-24799-DETAIL-07_17_2024-GO95MLD-1^06244005.0284500 | OTHER | Non-HFTD | Distribution | 2024-07-17 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008660 | 822717841-77479-DETAIL-03_11_2024-GRDRODHI-2^06147004.0049801 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008661 | 822779671-23263-DTLSB-04_29_2024-GO95MLD-1^06245007.0221443 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008662 | 822781140-55170-DETAIL-02_13_2025-GO95CL10-1^06240004.0168106 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008663 | 82289979-55599-DETAIL-04_01_2024-GUYHINS-1^06147005.0093700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008664 | 823070401-48502-DETAIL-07_11_2023-GO95MLD-1^06244008.0309002 | OTHER | HFTD Tier 2 | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008665 | 823153619-31072-DETAIL-04_11_2024-GO95MLD-1^06245002.0109502 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008666 | 823278728-33170-DETAIL-06_27_2024-SVCDEFLC-1^06240004.0063103 | OTHER | HFTD Tier 2 | Distribution | 2024-06-27 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008667 | 823341056-63049-DETAIL-08_06_2024-GO95HV-1^06245004.0331000 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008668 | 823344649-57989-DTLSB-08_14_2023-GO95HV-1^06243009.0246101 | OTHER | Non-HFTD | Distribution | 2023-08-14 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008669 | 823483583-54583-DETAIL-04_04_2024-SVCROAD-1^06147005.0240400 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008670 | 823984080-40620-DETAIL-03_10_2025-GO95HV-1^06240004.0271702 | OTHER | HFTD Tier 3 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008671 | 824030043-79979-DTLSB-05_28_2024-GO95MLD-1^06243001.0125202 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008672 | 824097186-23740-DETAIL-02_20_2025-GO95HV-1^06240004.0214701 | OTHER | HFTD Tier 2 | Distribution | 2025-02-20 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008673 | 824139275-87423-DTLSB-05_01_2024-GO95MLD-1^06245007.0221600 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008674 | 824327932-78602-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 5/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008675 | 824327932-89469-DTLTRT-04_11_2024-BIRDDMG-1^668067/00 5/007 | POLE | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008676 | 824327932-99602-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 5/007 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008677 | 824930404-56889-DTLSB-07_26_2023-GO95HV-1^06243009.0059901 | OTHER | Non-HFTD | Distribution | 2023-07-26 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008678 | 825589881-51050-DETAIL-03_24_2025-GO95HV-1^06238004.0026700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008679 | 825829993-63529-DTLSB-07_31_2023-GO95MLD-1^06243009.0080100 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008680 | 826029279-25559-DETAIL-05_16_2022-GO95HV-1^07116001.0090400 | OTHER | HFTD Tier 2 | Distribution | 2022-05-16 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008681 | 826047485-15349-DETAIL-02_27_2023-GO95TCH-1^07216001.0294740 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008682 | 826047485-15349-DETAIL-02_27_2023-RISEGRD-1^07216001.0294740 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008683 | 826205234-27234-DETAIL-03_29_2023-GUYHINS-1^06142016.0083400 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008684 | 976533783-68629-DETAIL-05_16_2024-GO95MLD-1^06142012.0121706 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008685 | 976533783-68629-DETAIL-05_16_2024-SVCDEFLC-1^06142012.0121706 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008686 | 976627643-74318-DETAIL-04_28_2022-GO95MLD-1^07116001.0095401 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008687 | 976627643-74318-DETAIL-04_28_2022-GO95TCH-1^07116001.0095401 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008688 | 976663968-34359-DETAIL-05_30_2024-GO95HV-1^06246005.0272800 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008689 | 976827393-45009-DETAIL-10_26_2022-ABNDEQPM-1^06246009.0128802 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008690 | 977000995-77893-ADMIN-05_13_2024-ABNDEQPM-1^06244001.0207300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008691 | 977022009-19679-DTLSB-09_03_2024-GRDRODHI-1^06245007.0018400 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008692 | 97705309-3430-DETAIL-03_19_2024-GO95MLD-1^06245002.0055600 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008693 | 97708906-46823-DTLSB-04_30_2024-GO95HV-1^06245007.0220641 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008694 | 977235676-66479-AUDIT-04_30_2024-GRDRODHI-1^06247005.0352800 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008695 | 977293595-83393-DETAIL-02_01_2023-GO95MLD-1^06147002.0310000 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008696 | 977348665-69109-ADMIN-01_18_2023-ENCHRW-1^06148004.0207201 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008697 | 977863555-5133-DETAIL-03_06_2023-GO95MLD-1^07117002.0194001 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008698 | 977891505-85805-DETAIL-07_03_2024-GO95MLD-1^06244005.0234541 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008699 | 977974534-54222-DETAIL-07_11_2023-GO95MLD-1^06244008.0332800 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008700 | 978055818-25169-DTLTRT-10_23_2023-UBPBXARM-1^668010/00 9/044 | CROSSARM | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008701 | 978078751-90550-AUDIT-04_02_2025-BIRDDMG-1^06238004.0270501 | POLE | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008702 | 978308124-90559-DETAIL-05_16_2022-ABNDEQPM-1^07117001.0314601 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008703 | 979064536-42693-DETAIL-04_23_2024-GRDRODHI-1^06145001.0035501 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008704 | 979157090-3389-DTLSB-07_22_2024-GO95MLD-1^06245007.0106800 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008705 | 979345288-78959-DTLSB-02_06_2024-SVCDEFLC-1^07216001.0309840 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008706 | 979345288-78959-DTLSB-02_06_2024-SVCDEFLC-2^07216001.0309840 | OTHER | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008707 | 979439505-36049-DETAIL-08_06_2024-GO95HV-1^06245004.0329401 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008708 | 97957386-21823-DTLSB-04_23_2024-GO95MLD-1^06245007.0223540 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008709 | 979820576-85870-DETAIL-01_21_2025-SVCENTCO-1^06239004.0256406 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008710 | 979853923-47059-DTLSB-02_14_2024-GO95CL10-1^07216001.0189002 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008711 | 979853923-47059-DTLSB-02_14_2024-GO95MLD-1^07216001.0189002 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008712 | 980564584-14690-DETAIL-03_25_2025-SVCDEFLC-1^06239003.0019503 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008713 | 980669484-39560-DETAIL-04_08_2024-ANCHIDLE-1^668062/00 5/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008714 | 980669484-39560-DETAIL-04_08_2024-GO95HV-1^668062/00 5/005 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008715 | 980669484-93753-DETAIL-04_08_2024-GO95HV-1^668062/00 5/005 | OTHER | Non-HFTD | Transmission | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008716 | 980779261-68149-DETAIL-03_06_2023-SVCENTCO-1^07216001.0297604 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008717 | 981072861-37809-DETAIL-03_11_2024-GO95HV-1^06147004.0031801 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008718 | 981090928-21609-DETAIL-04_02_2024-GO95HV-1^06147005.0152902 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008719 | 981161603-64309-DTLTRT-11_07_2022-GO95MLD-1^668001/00 19/030 | OTHER | Non-HFTD | Transmission | 2022-11-07 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008720 | 981348634-55759-DETAIL-06_04_2024-GO95HV-1^06246006.0368100 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008721 | 981349543-69169-DETAIL-06_11_2024-GO95HV-1^06245007.0344540 | OTHER | HFTD Tier 2 | Distribution | 2024-06-11 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008722 | 981374259-99769-DTLTRT-10_19_2023-GO95HV-1^668010/00 5/026 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008723 | 981374259-99769-DTLTRT-10_19_2023-GO95MLD-1^668010/00 5/026 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008724 | 98142629-76389-DETAIL-04_24_2024-GO95MLD-1^06145001.0089900 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008725 | 982044254-46309-DETAIL-03_06_2024-GO95MLD-1^06147005.0172800 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008726 | 982574356-56572-DETAIL-08_08_2024-GO95HV-1^06245006.0092141 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008727 | 982574356-56572-DETAIL-08_08_2024-GO95MLD-1^06245006.0092141 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008728 | 982697453-89439-DETAIL-06_26_2024-GO95MLD-1^06244005.0232300 | OTHER | Non-HFTD | Distribution | 2024-06-26 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008729 | 982911176-36391-DRONE_VS-11_13_2024-XARMSPCR-1^668038/00 4/055 | CROSSARM | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008730 | 983055616-58579-DETAIL-03_28_2024-GUYHINS-1^06147005.0142700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008731 | 983375579-73199-DETAIL-04_01_2024-GO95HV-1^06147005.0107902 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008732 | 983378754-10629-DTLSB-08_07_2023-GO95MLD-1^06243009.0197001 | OTHER | HFTD Tier 2 | Distribution | 2023-08-07 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008733 | 983409784-19449-DTLSB-02_08_2024-GO95MLD-1^07216001.0198002 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008734 | 984081981-73813-DETAIL-04_16_2024-GO95MLD-1^06145002.0078001 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008735 | 984181048-13048-DETAIL-05_10_2022-GO95MLD-1^07116001.0094700 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008736 | 984218582-1213-DETAIL-03_14_2024-GO95HV-1^06147004.0325601 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008737 | 984287021-73213-DTLSB-02_15_2023-GO95HV-1^06248001.0309800 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008738 | 984387023-41399-DETAIL-07_03_2023-GO95MLD-1^06245006.0230801 | OTHER | Non-HFTD | Distribution | 2023-07-03 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008739 | 984444755-90009-DETAIL-01_18_2023-CONDFRAY-1^06148004.0207700 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008740 | 984577616-18520-DETAIL-04_04_2024-GO95MLD-1^06147005.0242901 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008741 | 98501075-4779-AUDIT-11_10_2023-GO95HV-1^668010/00 11/037 | OTHER | Non-HFTD | Transmission | 2023-11-10 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008742 | 98501075-4779-DTLTRT-10_10_2023-GO95MLD-1^668010/00 11/037 | OTHER | Non-HFTD | Transmission | 2023-10-10 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008743 | 985132668-93113-DETAIL-03_01_2023-GO95MLD-1^07117002.0195100 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008744 | 985275366-22959-DETAIL-04_02_2024-GO95MLD-1^06247005.0351800 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008745 | 985485258-98849-DTLSB-02_21_2024-GO95HV-1^07216001.0262600 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008746 | 985571308-84979-DETAIL-04_09_2024-CLRTOUCH-1^06147005.0212001 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008747 | 985822384-82032-DETAIL-03_06_2025-GUYHINS-1^06241005.0120601 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008748 | 985909784-37839-DTLSB-02_08_2024-GO95MLD-1^07216001.0307800 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008749 | 985983183-45959-DETAIL-05_29_2024-GO95MLD-1^06246005.0178100 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008750 | 986449181-89020-DETAIL-03_06_2025-GO95HV-1^06240004.0272800 | OTHER | HFTD Tier 3 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008751 | 986800988-82539-DTLSB-02_28_2024-GO95CLSV-1^07216001.0260903 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008752 | 986800988-82539-DTLSB-02_28_2024-SVCENTBK-1^07216001.0260903 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008753 | 986821869-18279-DETAIL-03_28_2024-GO95MLD-1^06246005.0044701 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008754 | 987106977-86123-DETAIL-04_02_2024-GO95MLD-1^06147005.0162904 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008755 | 987284446-79699-DETAIL-07_31_2024-GO95MLD-1^06244004.0193601 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008756 | 987879526-45629-DETAIL-08_21_2024-GO95HV-1^06245008.0246101 | OTHER | HFTD Tier 2 | Distribution | 2024-08-21 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008757 | 989223859-20090-DETAIL-01_28_2025-SVCROAD-1^06239004.0244301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008758 | 989357771-44709-DETAIL-11_08_2022-GO95MLD-1^06246008.0057400 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008759 | 989774611-16201-DETAIL-05_30_2023-SVCRUBLG-1^06243009.0029702 | OTHER | HFTD Tier 2 | Distribution | 2023-05-30 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008760 | 989802245-11349-DETAIL-03_14_2024-GO95HV-1^06245006.0125900 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008761 | 990002805-85049-DETAIL-08_06_2024-GO95HV-1^06245004.0329301 | OTHER | Non-HFTD | Distribution | 2024-08-06 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008762 | 990074506-98310-DETAIL-02_14_2025-GO95HV-1^06240004.0163607 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008763 | 990407171-17882-DTLSB-08_17_2023-GO95HV-1^06243009.0131801 | OTHER | Non-HFTD | Distribution | 2023-08-17 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008764 | 990569743-73279-DTLSB-10_01_2024-GO95MLD-1^06245007.0219102 | OTHER | Non-HFTD | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008765 | 990620161-36579-DETAIL-03_11_2024-GRDRODHI-1^06147004.0047801 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008766 | 99062791-40240-DETAIL-02_01_2023-GO95HV-1^06146002.0072900 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008767 | 990944564-10333-DETAIL-10_22_2024-GO95CLSV-1^07216001.0208700 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008768 | 990944564-10333-DETAIL-10_22_2024-GUYHINS-1^07216001.0208700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008769 | 991229733-35730-DETAIL-04_25_2023-GO95MLD-1^06240004.0064804 | OTHER | HFTD Tier 2 | Distribution | 2023-04-25 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008770 | 991229733-35730-DETAIL-04_25_2023-RISECLMB-1^06240004.0064804 | OTHER | HFTD Tier 2 | Distribution | 2023-04-25 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008771 | 99160080-38949-DTLSB-02_16_2024-GO95MLD-1^07216001.0262201 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008772 | 991741559-47512-DETAIL-06_28_2023-GUYHINS-1^06244009.0363301 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2023-06-28 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008773 | 992405181-73679-DETAIL-07_08_2024-GO95MLD-1^06244005.0136801 | OTHER | Non-HFTD | Distribution | 2024-07-08 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008774 | 992429563-38999-DTLSB-10_01_2024-GO95MLD-1^06245007.0230600 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008775 | 992495931-95883-DETAIL-10_25_2024-SVCENTBK-1^07216001.0208401 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008776 | 992700172-14444-DETAIL-03_31_2025-SVCROAD-1^06241005.0116606 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008777 | 992700172-14444-DETAIL-03_31_2025-SVCROAD-2^06241005.0116606 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008778 | 992805560-48539-DETAIL-02_26_2024-GO95MLD-1^07113001.0138402 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008779 | 992805560-48539-DETAIL-03_26_2024-GUYHINS-1^07113001.0138402 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008780 | 992882179-56819-DTLTRT-08_03_2022-GUYSLACK-1^668005/00 12/077 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-03 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008781 | 993001389-10190-DETAIL-01_28_2025-SVCDEFLC-1^06239004.0244402 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008782 | 993178314-46960-DETAIL-02_04_2025-SVCDEFLC-1^06239004.0244944 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008783 | 99387975-87479-DETAIL-08_19_2024-GO95MLD-1^06245004.0290502 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008784 | 994410138-6829-DTLSB-08_10_2023-GO95MLD-1^06243009.0156001 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008785 | 994501454-67534-DETAIL-05_01_2024-GO95HV-1^06143015.0341500 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008786 | 994552463-50059-DETAIL-05_30_2024-GO95HV-1^06246005.0222100 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008787 | 994604198-60143-DETAIL-05_02_2024-SVCDEFLC-1^06142012.0126102 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008788 | 994615018-37890-DETAIL-01_28_2025-GO95HV-1^06239004.0246141 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008789 | 994929249-75343-DETAIL-03_18_2024-XARMSPCR-1^06245002.0040901 | CROSSARM | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008790 | 994932021-26589-DETAIL-07_03_2024-GO95MLD-1^06244005.0234903 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008791 | 995248013-40643-DTLSB-05_22_2024-GO95MLD-1^06243001.0048700 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008792 | 995362251-89399-DETAIL-06_17_2024-GO95MLD-1^06246006.0241600 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008793 | 995500313-53843-DTLSB-05_23_2024-GO95HV-1^06243001.0130700 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008794 | 995770913-46243-DETAIL-03_14_2024-GO95HV-1^06147004.0300901 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008795 | 996016669-27259-DETAIL-05_31_2024-GO95HV-1^06246005.0333402 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008796 | 996016669-27259-DETAIL-05_31_2024-GO95MLD-1^06246005.0333402 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008797 | 996229348-43449-DETAIL-07_23_2024-SVCENTCO-1^06245006.0143100 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008798 | 996420858-9759-DTLSB-02_13_2024-GO95MLD-1^07216001.0187402 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008799 | 996638334-46259-DETAIL-05_17_2022-GO95TCH-1^07117001.0320500 | OTHER | HFTD Tier 2 | Distribution | 2022-05-17 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008800 | 996801898-70399-DTLSB-07_02_2024-GO95HV-1^06245006.0186301 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008801 | 996977408-96049-DTLSB-02_13_2024-ABNDEQPM-1^07216001.0185101 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008802 | 997390604-47789-DETAIL-06_10_2024-GO95MLD-1^06245007.0349004 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008803 | 997862064-51149-DETAIL-03_21_2023-ABNDEQPM-1^07113001.0057500 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008804 | 997862064-51149-DETAIL-03_21_2023-WASHOUT-1^07113001.0057500 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008805 | 998172008-93223-DETAIL-03_14_2023-SVCENTCO-1^07117003.0112603 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008806 | 998279446-26260-DTLTRT-10_23_2023-GUYNOINS-1^668010/00 15A/042 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008807 | 998279446-26260-DTLTRT-10_23_2023-GUYNOINS-3^668010/00 15A/042 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008808 | 998635078-67019-DETAIL-06_28_2022-GO95MLD-1^07116007.0111507 | OTHER | HFTD Tier 2 | Distribution | 2022-06-28 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008809 | 998924858-97349-DETAIL-10_09_2024-GO95HV-1^07216001.0200205 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008810 | 998924858-97349-DETAIL-10_09_2024-GO95MLD-1^07216001.0200205 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008811 | 999328889-22489-DTLSB-09_03_2024-GUYHINS-1^06245007.0123900 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008812 | 999391625-37232-DETAIL-07_07_2023-GO95TCH-1^06244008.0331700 | OTHER | Non-HFTD | Distribution | 2023-07-07 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008813 | 999600688-45729-DETAIL-05_13_2024-GO95MLD-1^06142012.0123407 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008814 | 826206264-50140-DTLTRT-10_02_2023-GO95HV-1^668010/00 2/034 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008815 | 826206264-50140-DTLTRT-10_02_2023-GRDRODHI-1^668010/00 2/034 | OTHER | HFTD Tier 2 | Transmission | 2023-10-02 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008816 | 82643198-87550-DETAIL-01_16_2025-SVCDEFLC-1^06240004.0097505 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008817 | 826490441-68949-DTLSB-04_09_2024-SVCENTCO-1^06245007.0227014 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008818 | 826562884-47249-DTLSB-02_28_2024-SVCROAD-1^07216001.0275901 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008819 | 826782063-54249-DTLSB-10_07_2024-GO95STUB-1^06245007.0211301 | OTHER | HFTD Tier 2 | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008820 | 827185679-83559-DETAIL-02_27_2023-GO95MLD-1^07216001.0294609 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008821 | 82750425-71239-DETAIL-03_06_2023-CLRTOPOL-1^07216001.0296706 | OTHER | Non-HFTD | Distribution | 2023-03-06 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008822 | 828252699-96939-DETAIL-10_15_2024-SVCROAD-1^07216001.0204203 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008823 | 828376659-16759-DETAIL-03_26_2024-GO95HV-1^06246005.0052401 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008824 | 828394861-33709-DTLSB-08_26_2024-GO95HV-1^06245007.0112700 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008825 | 828534038-54923-ADMIN-10_11_2024-POLEDERP-1^07217001.0273202 | POLE | Non-HFTD | Distribution | 2024-10-11 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008826 | 82855024-84959-DTLSB-02_13_2024-GO95MLD-1^07216001.0187401 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008827 | 828859205-35892-DETAIL-04_03_2023-GO95HV-1^06143014.0181300 | OTHER | HFTD Tier 2 | Distribution | 2023-04-03 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008828 | 828941344-52990-DETAIL-03_31_2025-SVCRUBCM-1^06239003.0016904 | OTHER | Non-HFTD | Distribution | 2025-03-31 | 2028-03-31 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130008829 | 829007598-8369-DETAIL-07_06_2022-GO95HV-1^668005/00 6/036 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008830 | 829047883-33560-DTLTRT-04_09_2024-GO95HV-1^668062/00 4/003 | OTHER | Non-HFTD | Transmission | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008831 | 829047883-63560-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 4/003 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008832 | 829266640-31669-ADMIN-07_24_2023-POLEREPL-1^06242009.0246902 | POLE | Non-HFTD | Distribution | 2023-07-24 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008833 | 829371913-93199-DETAIL-06_18_2024-BIRDDMG-1^06245007.0290600 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008834 | 830046259-96929-DETAIL-05_07_2024-SVCENTCO-1^06142012.0121102 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008835 | 83035318-94099-DTLSB-10_03_2024-GO95MLD-1^06245006.0333801 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008836 | 830422820-71140-DETAIL-02_06_2025-GUYHINS-1^06239003.0062101 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008837 | 830710687-74328-DETAIL-10_10_2024-GO95TCH-1^07216001.0205113 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008838 | 831290101-20492-DETAIL-01_31_2023-GO95MLD-1^06146002.0153500 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008839 | 831316289-35753-DTLSB-04_16_2024-SVCWIND-1^06245007.0226346 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008840 | 831354920-98509-DTLSB-09_03_2024-GO95HV-1^06245007.0019302 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008841 | 831651084-16839-DTLSB-02_08_2024-SVCWIND-1^07216001.0197003 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008842 | 832379721-35101-DETAIL-01_31_2025-GO95HV-1^06239004.0245903 | OTHER | HFTD Tier 2 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008843 | 832429398-70489-DTLSB-07_02_2024-GO95HV-1^06245006.0184600 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008844 | 832761608-98702-DETAIL-04_23_2024-GO95HV-1^06145001.0028300 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008845 | 832904508-92702-DETAIL-03_20_2024-GO95MLD-1^06245002.0121200 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008846 | 8330901-24780-DETAIL-03_19_2025-GO95HV-1^06239001.0062600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008847 | 833203443-62069-DTLSB-04_09_2024-SVCDEFLC-1^06245007.0228005 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008848 | 833381408-29823-DETAIL-03_20_2023-GO95MLD-1^07117004.0060700 | OTHER | HFTD Tier 2 | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008849 | 83354885-30420-DETAIL-05_15_2024-GO95MLD-1^06142012.0124502 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008850 | 833579195-91295-DTLSB-02_13_2024-GO95MLD-1^07216001.0187204 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008851 | 833596979-34559-DETAIL-05_10_2022-GO95MLD-1^07116001.0091400 | OTHER | HFTD Tier 2 | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008852 | 833729130-84659-DETAIL-06_19_2024-GO95MLD-1^06246006.0133400 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008853 | 833812631-14711-DETAIL-01_21_2025-BIRDDMG-1^06239004.0255346 | POLE | HFTD Tier 2 | Distribution | 2025-01-21 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008854 | 999616348-18899-DTLSB-08_22_2024-GO95HV-1^06245006.0326601 | OTHER | Non-HFTD | Distribution | 2024-08-22 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008855 | 999654415-52833-DTLSB-02_21_2023-GO95TCH-1^07216001.0287708 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008856 | 999654415-52833-DTLSB-02_21_2023-SVCROAD-1^07216001.0287708 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008857 | 834067243-69789-DTLSB-05_23_2024-GO95HV-1^06243001.0149200 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008858 | 834084228-53379-DETAIL-10_09_2024-SVCENTCO-1^07216001.0202142 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008859 | 834115768-56049-DETAIL-10_09_2024-SVCENTCO-1^07216001.0200104 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008860 | 834290834-50140-DTLTRT-10_02_2023-GO95BLTC-1^668010/00 17/034 | OTHER | Non-HFTD | Transmission | 2023-10-02 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008861 | 834339328-58369-DTLTRT-07_06_2022-GO95HV-1^668005/00 8/036 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008862 | 834542279-18833-DETAIL-03_14_2023-GO95MLD-1^07117002.0271600 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008863 | 835371221-51059-DTLSB-02_16_2024-GO95MLD-1^07216001.0262001 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008864 | 835450348-97049-AUDIT-03_07_2024-GO95HV-1^07216001.0187102 | OTHER | Non-HFTD | Distribution | 2024-03-07 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008865 | 835682199-57504-DETAIL-05_01_2024-GO95HV-1^06142015.0048901 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008866 | 83580152-63059-DETAIL-10_15_2024-SVCNEUT-1^07216001.0207004 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008867 | 836158199-1712-DETAIL-07_05_2023-GO95MLD-1^06244009.0132700 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008868 | 836603229-50770-DETAIL-02_27_2025-SVCENTCO-1^06240004.0063100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008869 | 836720470-15649-DETAIL-03_16_2023-GO95HV-1^07113001.0042501 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008870 | 836720470-15649-DETAIL-03_16_2023-SVCROAD-1^07113001.0042501 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008871 | 836799029-16912-DETAIL-05_02_2024-GO95MLD-1^06142012.0128100 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008872 | 837130658-89550-DETAIL-09_19_2024-SVCENTCO-1^06240004.0163942 | OTHER | HFTD Tier 2 | Distribution | 2024-09-19 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008873 | 837155353-7222-DETAIL-05_23_2024-GO95HV-1^06243001.0120000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008874 | 837431313-9039-DETAIL-07_30_2024-GO95HV-1^06244005.0345801 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008875 | 837523159-41552-DETAIL-04_02_2025-GO95TCH-1^06241005.0028142 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008876 | 837547890-39422-DETAIL-03_13_2024-GO95MLD-1^06147004.0190900 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008877 | 838216285-38788-DETAIL-07_11_2023-GO95MLD-1^06244008.0333901 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008878 | 838302813-95329-DTLSB-08_29_2023-GO95MLD-1^06243009.0121001 | OTHER | Non-HFTD | Distribution | 2023-08-29 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008879 | 838431011-55159-DETAIL-03_16_2023-GO95TCH-1^07113001.0042506 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008880 | 838615597-57722-DETAIL-03_20_2024-GO95MLD-1^06245002.0122200 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008881 | 838686523-47140-DTLTRT-10_19_2023-GUYNOINS-1^668010/00 9A/024 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2023-10-19 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008882 | 838711869-36339-DTLSB-08_23_2022-GO95MLD-1^06243004.0234200 | OTHER | Non-HFTD | Distribution | 2022-08-23 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008883 | 838822124-44939-DTLSB-02_08_2024-GUYHINS-1^07216001.0198201 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008884 | 838887059-48049-DTLSB-02_21_2024-GO95MLD-1^07216001.0261503 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008885 | 838891732-86070-DETAIL-03_18_2025-BIRDDMG-1^06238004.0125900 | POLE | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008886 | 838891732-86070-DETAIL-03_18_2025-SVCDEFLC-1^06238004.0125900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008887 | 839266937-41970-DETAIL-04_24_2023-SVCDEFLC-1^06240004.0061400 | OTHER | HFTD Tier 2 | Distribution | 2023-04-24 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008888 | 840017467-38999-DETAIL-04_10_2024-GO95HV-1^06147005.0163001 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008889 | 840262876-78869-DTLSB-08_16_2023-GO95MLD-1^06243009.0104201 | OTHER | HFTD Tier 2 | Distribution | 2023-08-16 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008890 | 840264853-26050-DETAIL-02_04_2025-SVCDEFLC-1^06239004.0244951 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008891 | 840542594-12622-DTLSB-05_09_2024-GO95MLD-1^06244001.0111900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008892 | 840689613-15899-DETAIL-03_05_2024-GO95HV-1^06147005.0179201 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008893 | 840801299-49249-DETAIL-03_14_2024-GO95MLD-1^06245005.0062601 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008894 | 840801299-49249-DETAIL-03_14_2024-SVCWIND-1^06245005.0062601 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008895 | 841163809-41899-DTLSB-04_15_2024-GO95CLSV-1^06245007.0224103 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008896 | 841253960-3069-AUDIT-08_29_2022-GO95HV-1^668005/00 1/047 | OTHER | Non-HFTD | Transmission | 2022-08-29 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008897 | 841378506-21019-DETAIL-03_28_2024-GO95HV-1^06147005.0112001 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008898 | 841592936-82859-DETAIL-03_27_2024-GO95HV-1^06247005.0324502 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008899 | 841633039-49579-DETAIL-03_06_2024-GO95MLD-1^06147004.0011500 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008900 | 841727224-59560-AUDIT-02_26_2025-GO95MLD-1^06240004.0099043 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008901 | 841733634-41499-DTLSB-04_23_2024-GRDRODHI-1^06245007.0224802 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008902 | 842699644-53639-DETAIL-03_01_2023-GO95MLD-1^07216001.0290704 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008903 | 842870754-62123-DTLSB-04_24_2024-GO95MLD-1^06245007.0224900 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008904 | 842883900-66549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105601 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008905 | 843056735-37529-DETAIL-08_07_2024-SVCENTCO-1^06245008.0229402 | OTHER | HFTD Tier 2 | Distribution | 2024-08-07 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008906 | 843137844-2379-DETAIL-08_15_2024-GO95MLD-1^06246005.0135101 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008907 | 843143401-76959-DETAIL-05_16_2022-GO95MLD-1^07116001.0091900 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008908 | 843143401-76959-DETAIL-05_16_2022-GO95TCH-1^07116001.0091900 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008909 | 843213748-29443-DETAIL-03_06_2023-GO95HV-1^07117002.0208301 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008910 | 843274411-4119-ADMIN-12_31_2018-POLEREPL-1^668005/00 7/083 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008911 | 844367566-27772-DETAIL-07_13_2023-GO95MLD-1^06244008.0328700 | OTHER | Non-HFTD | Distribution | 2023-07-13 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008912 | 84455355-35049-DETAIL-02_26_2024-CUTOUTAR-1^07113001.0211403 | LIGHTNING ARRESTER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008913 | 844820678-61849-DTLSB-02_19_2024-GO95MLD-1^07216001.0265800 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008914 | 845274577-73183-DTLSB-10_07_2024-GO95MLD-1^06245006.0339101 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008915 | 845274974-29432-DETAIL-03_05_2025-GO95HV-1^06241005.0131905 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008916 | 845346403-71859-DETAIL-10_24_2024-GUYNOINS-1^07216001.0207940 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008917 | 845417682-71369-ADMIN-12_21_2022-UBPBGYSL-1^668005/00 10A/035 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-21 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008918 | 845910564-25488-DETAIL-06_08_2023-GO95HV-1^06244009.0326600 | OTHER | Non-HFTD | Distribution | 2023-06-08 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008919 | 846356618-15959-DTLTRT-07_06_2022-GO95HV-1^668005/00 7/036 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008920 | 846356618-15959-DTLTRT-07_06_2022-GO95MLD-1^668005/00 7/036 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008921 | 846393328-97669-DETAIL-03_05_2025-SVCDEFLC-1^06240004.0206500 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008922 | 846398936-11680-DETAIL-01_30_2025-SVCDEFLC-1^06239004.0244601 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008923 | 846398936-11680-DETAIL-01_30_2025-SVCDEFLC-2^06239004.0244601 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008924 | 846728251-25880-DETAIL-03_19_2025-GO95HV-1^06239001.0066600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008925 | 847046054-43250-DRONE_HY-09_20_2023-GO95HV-1^668002/00 9C/058 | OTHER | HFTD Tier 2 | Transmission | 2023-09-20 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008926 | 847333024-29519-DTLTRT-08_17_2022-GO95HV-1^668005/00 3/095 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2027-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008927 | 847680175-44770-DETAIL-03_18_2025-GO95HV-1^06240003.0367004 | OTHER | Non-HFTD | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008928 | 848057116-87098-DETAIL-01_31_2025-GO95HV-1^06239004.0135200 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008929 | 848225498-91849-DETAIL-08_12_2024-GO95HV-1^06245006.0159300 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008930 | 848516801-7749-DETAIL-02_22_2024-SVCDEFLC-1^07113001.0102001 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008931 | 849368529-98109-DETAIL-03_06_2024-GO95HV-1^06147004.0011300 | OTHER | Non-HFTD | Distribution | 2024-03-06 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008932 | 849419301-30401-DTLSB-02_21_2024-GO95CL10-1^07216001.0260810 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008933 | 849479561-49609-DTLSB-08_27_2024-GO95MLD-1^06245007.0120700 | OTHER | HFTD Tier 2 | Distribution | 2024-08-27 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008934 | 849763493-75629-DTLSB-08_31_2023-GO95MLD-1^06243008.0025802 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008935 | 849774085-21479-DTLTRT-11_01_2023-GO95HV-1^668010/00 1/018 | OTHER | HFTD Tier 2 | Transmission | 2023-11-01 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008936 | 849849599-92953-DETAIL-04_16_2024-SVCWIND-1^06245007.0226345 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008937 | 849923960-71859-DETAIL-03_21_2024-GO95HV-1^06246005.0063401 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008938 | 850096560-11579-DTLSB-09_05_2024-GO95MLD-1^06245007.0015201 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008939 | 850114906-17109-DETAIL-03_22_2024-GO95MLD-1^06247005.0339201 | OTHER | Non-HFTD | Distribution | 2024-03-22 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008940 | 850283213-28152-DTLSB-05_22_2024-GO95MLD-1^06243001.0115000 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008941 | 850662392-8599-DTLSB-08_25_2023-GO95BLTC-1^06243008.0175500 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008942 | 850950784-12884-DETAIL-02_05_2018-SVCWIND-1^06142016.0084903 | OTHER | Non-HFTD | Distribution | 2018-02-05 | 2021-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008943 | 851101005-12449-DETAIL-02_28_2024-GO95HV-1^07113002.0182501 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008944 | 851101005-12449-DETAIL-02_28_2024-GO95MLD-1^07113002.0182501 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008945 | 851191724-44724-DETAIL-03_28_2023-GO95MLD-1^06142016.0084704 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008946 | 851794616-52759-DETAIL-10_21_2024-GO95CL10-1^07216001.0200704 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008947 | 851794616-52759-DETAIL-10_21_2024-GUYHINS-1^07216001.0200704 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008948 | 852033971-36480-DETAIL-02_27_2025-GO95HV-1^06240004.0135101 | OTHER | HFTD Tier 3 | Distribution | 2025-02-27 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008949 | 8523504-18849-DETAIL-03_15_2023-GO95HV-1^07114001.0339500 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008950 | 852437684-35062-DETAIL-02_15_2023-GO95HV-1^06247002.0144301 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008951 | 852529250-18170-DETAIL-02_13_2025-GO95TCH-1^06240004.0169107 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008952 | 852529250-18170-DETAIL-02_13_2025-SVCROAD-1^06240004.0169107 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008953 | 852737885-16070-DETAIL-01_24_2025-GO95HV-1^06239004.0258742 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008954 | 853049066-29649-DETAIL-10_15_2024-GO95MLD-1^07216001.0203400 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008955 | 853184051-64959-DETAIL-05_12_2022-GO95MLD-1^07116001.0093803 | OTHER | HFTD Tier 2 | Distribution | 2022-05-12 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008956 | 853248946-63249-DETAIL-03_11_2024-GO95MLD-1^06245006.0123500 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008957 | 853279570-88149-DETAIL-02_19_2024-SVCDEFLC-1^07113002.0187100 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008958 | 853610508-76870-DETAIL-02_04_2025-SVCENTCO-1^06240004.0169601 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008959 | 854080680-70609-DETAIL-11_08_2022-GO95HV-1^06246008.0043300 | OTHER | HFTD Tier 2 | Distribution | 2022-11-08 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008960 | 854169401-54080-DETAIL-03_18_2025-GO95HV-1^06239001.0054702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008961 | 854567000-95100-DTLSB-01_30_2023-GUYLOINS-1^06248001.0366900 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008962 | 854804219-45219-DTLSB-09_07_2022-GO95HV-1^06243004.0060502 | OTHER | HFTD Tier 2 | Distribution | 2022-09-07 | 2027-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008963 | 854871461-30649-DETAIL-02_28_2024-SVCDEFLC-1^07113001.0033100 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008964 | 854913524-57009-DETAIL-04_01_2024-GO95HV-1^06147005.0090600 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008965 | 855492993-52729-DETAIL-05_14_2024-GO95MLD-1^06142012.0122704 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008966 | 85557931-99931-DETAIL-05_09_2024-GO95MLD-1^06142012.0120509 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008967 | 855700508-87723-DTLSB-02_27_2024-GO95MLD-1^07216001.0278804 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008968 | 855833034-21959-DETAIL-03_18_2024-GRDBROKE-1^06246005.0088001 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008969 | 855959858-75272-DETAIL-04_10_2024-GO95MLD-1^06245002.0113402 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008970 | 85632844-23590-DETAIL-03_13_2025-GO95HV-1^06239003.0252401 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008971 | 856384384-67384-DETAIL-04_29_2024-GO95HV-1^06142016.0175501 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008972 | 856429770-66269-DTLTRT-06_02_2021-GO95HV-1^668041/00 5/004 | OTHER | Non-HFTD | Transmission | 2021-06-02 | 2026-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008973 | 856757034-65872-DTLSB-05_09_2024-GO95MLD-1^06244001.0026000 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008974 | 857270754-3579-AUDIT-08_12_2024-GRDRODHI-1^06244005.0125400 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008975 | 857335437-25368-DTLSB-02_26_2024-GO95MLD-1^07216001.0262801 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008976 | 857782501-26501-DETAIL-03_28_2023-GO95BLTC-1^06142016.0052901 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008977 | 857876813-36349-DTLSB-10_02_2024-SVCROAD-1^06245007.0218400 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008978 | 858338512-75780-DETAIL-02_05_2025-GO95CL10-1^06240004.0167240 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008979 | 858553614-15614-DETAIL-03_27_2023-GO95HV-1^06142016.0082900 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008980 | 858715182-49882-DETAIL-05_13_2024-GO95MLD-1^06142012.0123404 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008981 | 858715182-49882-DETAIL-05_13_2024-SVCDEFLC-1^06142012.0123404 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008982 | 858818363-17649-DETAIL-03_01_2023-GO95MLD-1^07216001.0291707 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008983 | 859769869-38859-DTLSB-02_21_2024-GO95CL10-1^07216001.0260804 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008984 | 859769869-38859-DTLSB-02_21_2024-GO95MLD-1^07216001.0260804 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008985 | 860240199-17879-DETAIL-03_26_2024-GO95MLD-1^06246005.0051300 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008986 | 860346285-24659-DETAIL-10_21_2024-GUYHINS-2^07216001.0202700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008987 | 860425241-95779-DETAIL-04_18_2024-GO95MLD-1^06145001.0130301 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008988 | 860425241-95779-DETAIL-04_18_2024-GRDRODHI-1^06145001.0130301 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008989 | 861437228-98543-DTLSB-05_06_2024-BIRDDMG-1^06245007.0220740 | POLE | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008990 | 861437228-98543-DTLSB-05_06_2024-COPLLEAN-1^06245007.0220740 | POLE | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008991 | 86165630-27870-DETAIL-03_22_2023-SVCDEFLC-1^06240004.0166103 | OTHER | HFTD Tier 2 | Distribution | 2023-03-22 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008992 | 862456369-10902-DETAIL-04_22_2024-GO95MLD-1^06146001.0359000 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008993 | 862460663-10380-DETAIL-02_17_2025-SVCDEFLC-1^06240004.0165701 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008994 | 863197739-15249-DTLSB-02_19_2024-GO95MLD-1^07216001.0261007 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008995 | 863812184-41102-DETAIL-10_25_2024-GO95HV-1^07216001.0209702 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008996 | 863812184-41102-DETAIL-10_25_2024-GO95MLD-1^07216001.0209702 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130008997 | 863978670-27930-DRONE_HY-10_26_2023-GO95HV-1^668033/00 4/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-26 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008998 | 864150405-49502-DETAIL-04_24_2024-GO95HV-1^06145001.0045000 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130008999 | 864187060-7839-DETAIL-02_25_2025-SVCDEFLC-1^06240004.0150410 | OTHER | HFTD Tier 3 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009000 | 864209735-73379-DTLSB-02_16_2023-GO95MLD-1^06248001.0210100 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009001 | 864265743-51459-DETAIL-04_28_2022-GO95HV-1^07116001.0096304 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2027-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009002 | 864265743-51459-DETAIL-04_28_2022-SVCNEUT-1^07116001.0096304 | OTHER | HFTD Tier 2 | Distribution | 2022-04-28 | 2025-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009003 | 864521598-12079-DRONE_HY-09_22_2023-GO95HV-1^668002/00 2/075 | OTHER | HFTD Tier 2 | Transmission | 2023-09-22 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009004 | 8645721-73219-DTLTRT-08_15_2022-GUYSLACK-1^668005/00 1/086 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-15 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009005 | 864837366-2540-ADMIN-03_13_2025-POLEREPL-1^668033/00 9/001 | POLE | HFTD Tier 2 | Transmission | 2025-03-13 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009006 | 86565588-6799-DETAIL-02_13_2025-SVCROAD-1^06240004.0169142 | OTHER | HFTD Tier 2 | Distribution | 2025-02-13 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009007 | 865938257-10590-DETAIL-02_03_2025-GO95HV-1^06239004.0243943 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009008 | 866150076-14149-DETAIL-10_15_2024-SVCROAD-1^07216001.0203402 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009009 | 866155159-82259-DETAIL-12_22_2022-GUYNOINS-1^668075/00 19A/025 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-12-22 | 2025-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009010 | 866332691-44029-DETAIL-05_07_2024-GO95MLD-1^06142012.0123109 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009011 | 866338354-89999-DTLTRT-10_27_2022-GUYNOINS-2^668001/00 13A/031 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-27 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009012 | 866338354-89999-DTLTRT-10_27_2022-GUYNOINS-3^668001/00 13A/031 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-10-27 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009013 | 866393691-27359-DETAIL-02_21_2024-GO95HV-1^07113001.0141102 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009014 | 866414498-53212-DTLSB-05_09_2024-GO95MLD-1^06244001.0223400 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009015 | 866837531-38212-DETAIL-04_11_2024-GO95MLD-1^06245002.0140200 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009016 | 867255255-84033-DETAIL-03_06_2023-GO95MLD-1^07117002.0195000 | OTHER | HFTD Tier 2 | Distribution | 2023-03-06 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009017 | 867576958-78859-DTLTRT-06_30_2022-GO95MLD-1^668005/00 13/032 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009018 | 867749335-435-DETAIL-10_10_2024-GO95MLD-1^07216001.0205011 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009019 | 867882943-86109-DETAIL-08_14_2024-GO95MLD-1^06245005.0360503 | OTHER | Non-HFTD | Distribution | 2024-08-14 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009020 | 867882943-86109-DETAIL-08_14_2024-GUYHINS-1^06245005.0360503 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-14 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009021 | 868125718-66722-DTLSB-05_14_2024-GO95MLD-1^06244001.0220400 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009022 | 868300218-66534-DETAIL-10_24_2024-GO95TCH-1^07216001.0208741 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009023 | 868488428-92622-DETAIL-05_06_2024-GO95MLD-1^06142012.0125005 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009024 | 868498800-68399-DETAIL-11_09_2022-GO95MLD-1^06246008.0046202 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009025 | 868783588-87122-DETAIL-03_20_2024-GUYHINS-1^06245002.0127700 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-03-20 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009026 | 86895993-99159-DETAIL-06_10_2024-SVCDEFLC-1^06245007.0349005 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009027 | 869072013-30889-DETAIL-07_24_2024-GO95HV-1^06244005.0250000 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009028 | 869368086-24449-DETAIL-10_09_2024-GO95MLD-1^07216001.0200103 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009029 | 869368509-38190-DETAIL-01_15_2025-GO95CL10-1^06239004.0256113 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009030 | 869551515-85000-DETAIL-03_25_2025-GO95HV-1^06239003.0019605 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009031 | 869895219-7219-DTLSB-07_25_2022-GO95MLD-1^06242005.0139630 | OTHER | HFTD Tier 2 | Distribution | 2022-07-25 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009032 | 869981596-84270-DETAIL-01_16_2025-GO95MLD-1^06239004.0256212 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009033 | 869981596-84270-DETAIL-01_16_2025-GO95TCH-1^06239004.0256212 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009034 | 870068290-34459-DETAIL-02_29_2024-GO95HV-1^07113001.0112001 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009035 | 870541841-18679-DTLSB-02_16_2023-GO95TCH-1^06248001.0299600 | OTHER | Non-HFTD | Distribution | 2023-02-16 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009036 | 870584673-73579-DETAIL-06_10_2024-GO95HV-1^06245007.0346005 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009037 | 870747123-8690-DETAIL-06_27_2024-SVCWIND-1^06241004.0314001 | OTHER | HFTD Tier 2 | Distribution | 2024-06-27 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009038 | 870864943-30249-DETAIL-03_16_2023-GO95HV-1^07114001.0280700 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009039 | 870935323-62852-DETAIL-06_13_2023-GO95MLD-1^06244010.0220400 | OTHER | HFTD Tier 2 | Distribution | 2023-06-13 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009040 | 871527276-58563-DETAIL-03_28_2024-GO95MLD-1^06247005.0331503 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009041 | 871862474-2429-DETAIL-04_04_2023-GO95MLD-1^06143013.0241001 | OTHER | HFTD Tier 2 | Distribution | 2023-04-04 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009042 | 872130416-35559-DETAIL-08_20_2024-GO95HV-1^06246004.0326801 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009043 | 872480471-9949-DETAIL-05_09_2022-GO95TCH-1^07116001.0097200 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009044 | 87267211-91820-DETAIL-03_12_2024-CONDFRAY-1^06147004.0085901 | CONDUCTOR | Non-HFTD | Distribution | 2024-03-12 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009045 | 872820653-19199-DETAIL-06_07_2023-GO95MLD-1^06244010.0275500 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009046 | 872900628-41449-DETAIL-05_25_2023-ENCHRW-1^06245005.0200400 | OTHER | Non-HFTD | Distribution | 2023-05-25 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009047 | 872944579-13129-DETAIL-05_06_2024-GO95MLD-1^06142012.0122001 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009048 | 872954975-98970-DETAIL-01_16_2025-GO95HV-1^06239004.0257305 | OTHER | HFTD Tier 2 | Distribution | 2025-01-16 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009049 | 873098536-23680-DETAIL-01_30_2025-GO95HV-1^06239004.0244604 | OTHER | HFTD Tier 2 | Distribution | 2025-01-30 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009050 | 873228383-34380-DETAIL-02_03_2025-SVCDEFLC-1^06240004.0163800 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009051 | 873465395-10189-DETAIL-07_09_2024-GO95MLD-1^06244005.0139400 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009052 | 873641344-13299-DETAIL-01_10_2025-POLEREPL-1^06243010.0231101 | POLE | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009053 | 873715044-78740-DETAIL-02_26_2025-CLRTOPOL-1^06240004.0219805 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009054 | 873757416-37389-DTLSB-02_02_2023-GO95MLD-1^06247001.0120501 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009055 | 873882178-91951-DETAIL-03_06_2025-GO95CL10-1^06241005.0160901 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009056 | 873898366-96449-DETAIL-10_24_2024-SVCENTCO-1^07216001.0200307 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009057 | 874075848-19643-DTLSB-04_30_2024-GO95HV-1^06245007.0222842 | OTHER | HFTD Tier 2 | Distribution | 2024-04-30 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009058 | 874885655-15733-DETAIL-03_01_2023-GO95MLD-1^07117002.0198303 | OTHER | HFTD Tier 2 | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009059 | 875232135-13449-ADMIN-03_04_2025-POLEDERP-1^07216001.0296408 | POLE | Non-HFTD | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009060 | 875477510-68870-DTLTRT-09_29_2020-GO95HV-1^668018/00 4/007 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009061 | 87609620-46120-DTLTRT-11_16_2022-GO95HV-1^668075/00 11/026 | OTHER | Non-HFTD | Transmission | 2022-11-16 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009062 | 876113328-31428-DRONE_HY-10_16_2023-GO95HV-1^668033/00 13/003 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009063 | 876210014-67039-DTLSB-02_08_2024-GO95MLD-1^07216001.0308904 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009064 | 876752553-5779-DTLSB-02_06_2023-GO95MLD-1^06248001.0262000 | OTHER | Non-HFTD | Distribution | 2023-02-06 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009065 | 876843441-10999-DTLTRT-10_27_2022-GO95MLD-1^668001/00 7/029 | OTHER | Non-HFTD | Transmission | 2022-10-27 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009066 | 876900562-75752-DETAIL-05_07_2024-GO95MLD-1^06142012.0121101 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009067 | 876925476-7752-DTLSB-01_30_2023-SVCWIND-1^06248001.0369711 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009068 | 877089521-15673-DETAIL-03_02_2023-GO95MLD-1^07117002.0202200 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009069 | 877692883-37299-DTLSB-02_07_2023-GO95MLD-1^06248001.0154304 | OTHER | Non-HFTD | Distribution | 2023-02-07 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009070 | 87788416-60899-DETAIL-06_04_2024-GO95MLD-1^06246006.0367001 | OTHER | Non-HFTD | Distribution | 2024-06-04 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009071 | 877902792-76370-DETAIL-01_28_2025-GO95HV-1^06240004.0085001 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009072 | 878210106-30106-DETAIL-01_29_2025-GO95MLD-1^06239004.0253600 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009073 | 878390184-67859-DTLSB-02_06_2024-GUYLOINS-1^07216001.0307801 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-06 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009074 | 878689067-30769-DTLSB-04_11_2024-SVCWIND-1^06245007.0221101 | OTHER | Non-HFTD | Distribution | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009075 | 8786985-83939-DETAIL-10_09_2024-GO95MLD-1^07216001.0201102 | OTHER | Non-HFTD | Distribution | 2024-10-09 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009076 | 878741439-95259-DETAIL-05_06_2024-GO95MLD-1^06245005.0045901 | OTHER | Non-HFTD | Distribution | 2024-05-06 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009077 | 878902940-65532-DETAIL-06_15_2023-GO95HV-1^06244009.0335301 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009078 | 878960530-34299-DTLSB-07_17_2023-SVCRUBLG-1^06243010.0117802 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009079 | 879364178-77093-DETAIL-02_23_2023-GO95TCH-1^07216001.0294643 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009080 | 879458664-13952-ADMIN-05_14_2024-GO95TCH-1^06142012.0122606 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009081 | 879541943-24049-DETAIL-03_15_2023-GO95MLD-1^07216001.0291605 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009082 | 879712041-13463-DTLSB-04_17_2024-GO95HV-1^06245007.0220442 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009083 | 879852709-30912-DETAIL-06_12_2023-SVCDEFLC-1^06244009.0362301 | OTHER | Non-HFTD | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009084 | 880717653-93679-DETAIL-01_17_2023-GO95MLD-1^06148004.0227801 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009085 | 880717653-93679-DETAIL-01_17_2023-GO95MLD-2^06148004.0227801 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009086 | 880717653-93679-DETAIL-01_17_2023-GO95TCH-1^06148004.0227801 | OTHER | Non-HFTD | Distribution | 2023-01-17 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009087 | 880828156-76662-DTLSB-01_31_2023-GO95MLD-1^06248001.0367908 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009088 | 881546123-91041-DETAIL-03_04_2025-GO95HV-1^06241005.0130703 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009089 | 881550413-30279-DETAIL-01_18_2023-CONDFRAY-1^06148004.0215002 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009090 | 88173739-90312-DETAIL-07_05_2023-GO95MLD-1^06244009.0132300 | OTHER | HFTD Tier 2 | Distribution | 2023-07-05 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009091 | 882247005-329-DTLSB-08_02_2023-GRDRODHI-1^06243010.0134100 | OTHER | HFTD Tier 2 | Distribution | 2023-08-02 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009092 | 882821149-20129-DTLSB-07_20_2023-GRDRODHI-1^06243010.0023401 | OTHER | HFTD Tier 2 | Distribution | 2023-07-20 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009093 | 883027069-55172-DETAIL-04_23_2024-GRDRODHI-1^06145001.0023204 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009094 | 883198053-72599-DETAIL-07_05_2024-SVCDEFLC-1^06244005.0232800 | OTHER | Non-HFTD | Distribution | 2024-07-05 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009095 | 883334417-35369-AUDIT-08_22_2023-GO95MLD-1^06244009.0287000 | OTHER | Non-HFTD | Distribution | 2023-08-22 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009096 | 883600687-86418-DTLSB-02_22_2023-GO95MLD-1^07216001.0280704 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009097 | 883600687-86418-DTLSB-02_22_2023-RISEGRD-1^07216001.0280704 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009098 | 883723306-55971-DETAIL-02_24_2025-GO95MLD-1^06239004.0367842 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009099 | 884209116-7523-DTLSB-05_02_2024-GO95MLD-1^06245007.0222544 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009100 | 884684080-87389-DTLSB-09_03_2024-BIRDDMG-1^06245007.0014103 | POLE | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009101 | 885032364-55839-DETAIL-03_01_2023-GO95CL10-1^07216001.0291802 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009102 | 885032364-55839-DETAIL-03_01_2023-GO95MLD-1^07216001.0291802 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009103 | 885032364-55839-DETAIL-03_01_2023-GO95TCH-1^07216001.0291802 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009104 | 885075738-53372-DTLSB-02_02_2023-GO95MLD-1^06247001.0014301 | OTHER | Non-HFTD | Distribution | 2023-02-02 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009105 | 885083964-32710-DETAIL-03_17_2025-GO95HV-1^06238004.0158200 | OTHER | HFTD Tier 2 | Distribution | 2025-03-17 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009106 | 885229916-96413-ADMIN-03_17_2025-POLEREPL-1^06239004.0135241 | POLE | HFTD Tier 2 | Distribution | 2025-03-17 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009107 | 8854370-72839-DETAIL-02_20_2024-GO95MLD-1^07113002.0180103 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009108 | 88546279-69409-DTLSB-09_04_2024-GO95HV-1^06245007.0016500 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009109 | 88547311-9311-DETAIL-03_27_2023-GO95TCH-1^06142016.0051201 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009110 | 885666638-6372-DETAIL-04_16_2024-GO95MLD-1^06145001.0129803 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009111 | 88577043-28649-DETAIL-03_16_2023-GUYHINS-1^07114001.0206000 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-16 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009112 | 885889655-60172-DTLSB-02_01_2023-GO95MLD-1^06248001.0369304 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009113 | 886144718-6299-DTLSB-07_02_2024-GO95MLD-1^06245006.0182001 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009114 | 886204799-74439-DETAIL-02_27_2024-SVCDEFLC-1^07113002.0184103 | OTHER | HFTD Tier 2 | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009115 | 886245726-38889-DTLSB-09_04_2024-SVCENTCO-1^06245007.0142401 | OTHER | HFTD Tier 2 | Distribution | 2024-09-04 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009116 | 886776329-52899-DTLSB-04_10_2024-SVCENTCO-1^06245007.0221001 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009117 | 886792354-99215-DETAIL-10_16_2024-GO95MLD-1^07216001.0205903 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009118 | 887170281-42281-DETAIL-03_27_2023-GO95HV-1^06142016.0052400 | OTHER | Non-HFTD | Distribution | 2023-03-27 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009119 | 887183848-34850-DETAIL-03_03_2025-GO95HV-1^06240004.0050041 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009120 | 887188586-47972-DETAIL-07_11_2023-ABNDEQPM-1^06244008.0291401 | OTHER | Non-HFTD | Distribution | 2023-07-11 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009121 | 887194521-83282-DETAIL-02_23_2023-GO95MLD-1^07216001.0298903 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009122 | 887194521-83282-DETAIL-02_23_2023-SVCENTCO-1^07216001.0298903 | OTHER | Non-HFTD | Distribution | 2023-02-23 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009123 | 887369603-37822-ADMIN-07_15_2024-ABNDEQPM-1^06244005.0254700 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009124 | 887478488-45588-DETAIL-02_29_2024-GUYHINS-1^07113001.0106304 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-29 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009125 | 887513435-20240-DETAIL-02_24_2025-CLRTOUCH-1^06240004.0152803 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-02-24 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009126 | 887749876-48209-DETAIL-08_08_2024-GO95HV-1^06245006.0095140 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009127 | 887844116-48379-DETAIL-03_18_2025-GO95HV-1^06239001.0041701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009128 | 887980298-3689-DETAIL-08_12_2024-GO95MLD-1^06245006.0105001 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009129 | 888734104-66739-DTLSB-02_26_2024-GO95MLD-1^07216001.0277704 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009130 | 888734104-66739-DTLSB-02_26_2024-GRDRODHI-1^07216001.0277704 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009131 | 889136179-32579-DTLTRT-10_19_2023-GO95HV-1^668010/00 5/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009132 | 889172731-82339-DETAIL-02_28_2024-GRDRODHI-1^07113001.0030402 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009133 | 88979726-52079-DETAIL-04_04_2024-GO95MLD-1^06147005.0238102 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009134 | 889994054-1739-DETAIL-07_24_2024-GO95MLD-1^06244005.0268140 | OTHER | Non-HFTD | Distribution | 2024-07-24 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009135 | 890239043-81489-DETAIL-06_27_2023-GRDRODHI-2^06243009.0032800 | OTHER | HFTD Tier 2 | Distribution | 2023-06-27 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009136 | 890408721-65399-DETAIL-06_19_2023-GO95MLD-1^06244010.0264501 | OTHER | HFTD Tier 2 | Distribution | 2023-06-19 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009137 | 890431731-54192-DETAIL-05_13_2024-SVCRUBLG-1^06142012.0122300 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009138 | 890520130-97849-DTLSB-04_22_2024-ENCHRW-1^06245007.0227204 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009139 | 890532756-54639-DETAIL-10_24_2024-SVCENTCO-1^07216001.0204502 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009140 | 89085383-44029-DETAIL-05_16_2024-GO95MLD-1^06142012.0122706 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009141 | 890968648-28428-DTLSB-02_08_2024-GO95MLD-1^07216001.0198004 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009142 | 891080394-3892-DETAIL-10_16_2024-SVCENTCO-1^07216001.0205901 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009143 | 891080394-3892-DETAIL-10_16_2024-SVCROAD-1^07216001.0205901 | OTHER | Non-HFTD | Distribution | 2024-10-16 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009144 | 891198495-19495-DETAIL-03_24_2025-GUYHINS-1^06238004.0029608 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009145 | 891198495-19495-DETAIL-03_24_2025-GUYHINS-2^06238004.0029608 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009146 | 891198495-19495-DETAIL-03_24_2025-SVCDEFLC-1^06238004.0029608 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009147 | 891266669-20790-DETAIL-02_03_2025-GO95MLD-1^06239004.0133041 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009148 | 891513203-88080-DETAIL-02_25_2025-GO95TCH-1^06240005.0017100 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009149 | 891697062-49892-DETAIL-05_13_2024-GO95MLD-1^06142012.0124400 | OTHER | Non-HFTD | Distribution | 2024-05-13 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009150 | 891853374-5779-DETAIL-04_22_2024-GRDRODHI-1^06145001.0149703 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009151 | 89206448-61690-DETAIL-01_28_2025-GO95HV-1^06239004.0245304 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009152 | 892099243-81343-DETAIL-04_29_2024-GO95MLD-1^06142016.0079704 | OTHER | HFTD Tier 2 | Distribution | 2024-04-29 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009153 | 892315090-32423-DETAIL-06_19_2024-GO95MLD-1^06246006.0136800 | OTHER | Non-HFTD | Distribution | 2024-06-19 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009154 | 892532726-77769-DETAIL-07_25_2022-GO95HV-1^668005/00 1/062 | OTHER | Non-HFTD | Transmission | 2022-07-25 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009155 | 892983992-31002-DETAIL-04_17_2024-GO95MLD-1^06145001.0012401 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009156 | 893053737-56979-DETAIL-07_02_2024-GO95MLD-1^06245006.0088801 | OTHER | Non-HFTD | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009157 | 894002490-84219-DETAIL-03_25_2024-GO95MLD-1^06147005.0130900 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009158 | 894125789-14249-DTLSB-02_15_2024-SVCRUBLG-1^07216001.0260001 | OTHER | Non-HFTD | Distribution | 2024-02-15 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009159 | 894245383-53259-DETAIL-06_10_2024-GO95MLD-1^06245007.0345001 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009160 | 894508023-51559-DETAIL-02_20_2024-GO95MLD-1^07113002.0193901 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009161 | 894520283-38899-DETAIL-06_18_2024-BIRDDMG-1^06245007.0291300 | POLE | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009162 | 894520283-38899-DETAIL-06_18_2024-SVCENTCO-1^06245007.0291300 | OTHER | HFTD Tier 2 | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009163 | 895067204-59469-DTLTRT-07_20_2022-GO95HV-1^668005/00 6/055 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009164 | 895162648-48269-DTLTRT-07_05_2022-GO95HV-1^668005/00 5/035 | OTHER | Non-HFTD | Transmission | 2022-07-05 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009165 | 895474226-76879-DETAIL-07_31_2024-ABNDEQPM-1^06244004.0194500 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009166 | 895772611-28212-DETAIL-04_18_2024-GO95MLD-1^06145001.0149700 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009167 | 895855431-18579-DETAIL-06_17_2024-GO95HV-1^06246006.0131401 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009168 | 895889007-38138-DETAIL-03_05_2025-GO95BLTC-1^06241005.0121302 | OTHER | HFTD Tier 2 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009169 | 896863926-62549-DETAIL-10_17_2024-SVCRUBLG-1^07216001.0204407 | OTHER | Non-HFTD | Distribution | 2024-10-17 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009170 | 896888890-52801-DETAIL-02_26_2025-BIRDDMG-1^06241005.0151800 | POLE | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009171 | 897067295-63349-DETAIL-03_14_2024-GO95MLD-1^06245006.0120901 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009172 | 897105781-11829-DTLSB-09_28_2023-GO95HV-1^06243008.0110801 | OTHER | HFTD Tier 2 | Distribution | 2023-09-28 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009173 | 897113085-30639-DETAIL-07_10_2024-GO95HV-1^06244004.0190000 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009174 | 897113085-30639-DETAIL-07_10_2024-GO95MLD-1^06244004.0190000 | OTHER | Non-HFTD | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009175 | 897376306-77123-DTLSB-04_23_2024-SVCENTCO-1^06245007.0223542 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009176 | 897376306-77123-DTLSB-04_23_2024-SVCENTCO-2^06245007.0223542 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009177 | 898220994-74860-DETAIL-01_23_2025-GO95HV-1^06239004.0257610 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009178 | 898312217-78222-DTLSB-08_10_2023-GO95MLD-1^06243009.0227800 | OTHER | Non-HFTD | Distribution | 2023-08-10 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009179 | 898679659-24353-DTLSB-04_22_2024-SVCENTCO-1^06245007.0226344 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009180 | 898937770-29759-DETAIL-03_27_2024-GO95HV-1^06246005.0069200 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009181 | 89930094-63549-AUDIT-02_27_2024-GO95MLD-1^07216001.0199205 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009182 | 899890468-4519-ADMIN-12_31_2018-POLEDERP-1^668005/00 7/071 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009183 | 899895947-64949-DETAIL-03_15_2023-GO95MLD-1^07114001.0342802 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009184 | 900054117-90089-DTLSB-10_07_2024-GO95MLD-1^06245006.0332201 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009185 | 901054953-74341-DTLSB-09_05_2023-GO95MLD-1^06243008.0240900 | OTHER | HFTD Tier 2 | Distribution | 2023-09-05 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009186 | 901166670-69098-DTLSB-02_22_2023-GO95HV-1^07216001.0289601 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009187 | 901226358-25259-DETAIL-03_15_2023-GO95MLD-1^07114001.0325200 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009188 | 9014886-56549-DTLSB-01_31_2023-GO95MLD-1^06248001.0367904 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009189 | 9014886-56549-DTLSB-01_31_2023-SVCENTCO-1^06248001.0367904 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009190 | 901549923-50339-DETAIL-07_09_2024-GO95HV-1^06244005.0276900 | OTHER | Non-HFTD | Distribution | 2024-07-09 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009191 | 902118443-88942-DTLSB-05_22_2024-GO95HV-1^06243001.0102800 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009192 | 902118443-88942-DTLSB-05_22_2024-GO95MLD-1^06243001.0102800 | OTHER | Non-HFTD | Distribution | 2024-05-22 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009193 | 902343143-19539-DETAIL-07_03_2024-SVCDEFLC-1^06244005.0230900 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009194 | 902648611-38473-DETAIL-03_09_2023-GO95MLD-1^07117002.0203207 | OTHER | HFTD Tier 2 | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009195 | 903099703-58459-DETAIL-04_04_2024-GO95MLD-1^06247005.0291001 | OTHER | Non-HFTD | Distribution | 2024-04-04 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009196 | 903423561-61119-DTLTRT-08_04_2022-GUYSLACK-1^668005/00 12/082 | ANCHOR/GUY | Non-HFTD | Transmission | 2022-08-04 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009197 | 903554579-94449-DTLSB-02_21_2024-GO95MLD-1^07216001.0264500 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009198 | 90384273-83649-DRONE_HY-10_17_2023-GO95HV-1^668033/00 14/037 | OTHER | HFTD Tier 2 | Transmission | 2023-10-17 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009199 | 90412435-3569-DTLTRT-07_20_2022-GO95HV-1^668005/00 6/056 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009200 | 904127249-76390-DETAIL-01_14_2025-GO95MLD-1^06239004.0255003 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009201 | 904344566-18271-DETAIL-05_09_2022-SVCRUBLG-1^06241005.0014500 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009202 | 904640414-72490-DETAIL-03_11_2025-GO95BLTC-1^06239003.0252101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009203 | 904640414-72490-DETAIL-03_11_2025-SVCDEFLC-1^06239003.0252101 | OTHER | HFTD Tier 2 | Distribution | 2025-03-11 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009204 | 904699350-97579-DETAIL-03_21_2024-GO95HV-1^06147004.0116800 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009205 | 904699350-97579-DETAIL-03_21_2024-GO95MLD-1^06147004.0116800 | OTHER | Non-HFTD | Distribution | 2024-03-21 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009206 | 904800769-37913-DETAIL-07_23_2024-ABNDEQPM-1^06245006.0145341 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009207 | 905731499-32970-DTLTRT-09_29_2020-GO95HV-1^668018/00 16/004 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009208 | 905947374-6160-DETAIL-01_14_2025-GO95MLD-1^06239004.0256107 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009209 | 906086291-62570-DTLTRT-10_16_2023-GO95HV-1^668010/00 14/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009210 | 906887658-82399-DTLSB-10_07_2024-GO95HV-1^06245006.0170401 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009211 | 906903828-76730-DETAIL-02_17_2025-GO95MLD-1^06240003.0314901 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009212 | 907159768-1439-DTLSB-02_19_2024-GO95HV-1^07216001.0264800 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009213 | 90730026-10460-DTLTRT-10_09_2023-GO95MLD-1^668010/00 7/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009214 | 907482474-49759-DETAIL-03_05_2024-GO95HV-1^06245007.0278102 | OTHER | HFTD Tier 2 | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009215 | 907578119-259-DETAIL-05_30_2024-GO95HV-1^06246005.0341600 | OTHER | Non-HFTD | Distribution | 2024-05-30 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009216 | 907785199-82453-DTLSB-04_29_2024-GO95MLD-1^06245007.0226442 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009217 | 908255348-47762-ADMIN-04_23_2024-ABNDEQPM-1^06145001.0022170-A | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009218 | 908661811-52580-DETAIL-02_04_2025-GO95HV-1^06240004.0165749 | OTHER | HFTD Tier 2 | Distribution | 2025-02-04 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009219 | 908696598-85679-DETAIL-04_08_2024-GO95MLD-1^06147005.0227003 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009220 | 909093106-14106-DETAIL-01_29_2025-GO95MLD-1^06239004.0252701 | OTHER | HFTD Tier 3 | Distribution | 2025-01-29 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009221 | 90923898-91529-DETAIL-05_02_2024-GO95MLD-1^06142012.0126101 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009222 | 90923898-91529-DETAIL-05_02_2024-SVCENTCO-1^06142012.0126101 | OTHER | Non-HFTD | Distribution | 2024-05-02 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009223 | 909261378-39549-DETAIL-02_28_2024-GO95HV-1^07113001.0125000 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009224 | 909544838-42209-ADMIN-07_18_2024-GO95STUB-1^06246009.0105500 | OTHER | HFTD Tier 2 | Distribution | 2024-07-18 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009225 | 909582380-84949-DTLSB-02_16_2024-GO95MLD-1^07216001.0263102 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009226 | 909607020-5659-DETAIL-06_17_2024-GRDRODHI-1^06246006.0132400 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009227 | 909674534-80159-DTLSB-02_05_2024-GUYNOINS-1^07216002.0249903 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-05 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009228 | 909832179-27919-ADMIN-06_18_2024-POLEREPL-1^06241009.0365801 | POLE | Non-HFTD | Distribution | 2024-06-18 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009229 | 910101824-22824-DETAIL-04_25_2024-GO95HV-1^06142016.0161900 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009230 | 910263933-49559-DTLSB-02_13_2024-GUYHINS-1^07216001.0187203 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009231 | 910359237-41970-DETAIL-02_27_2025-SVCDEFLC-1^06240004.0061401 | OTHER | HFTD Tier 2 | Distribution | 2025-02-27 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009232 | 910364574-9839-DETAIL-07_11_2024-GO95MLD-1^06244005.0221802 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009233 | 910421873-50653-DTLTRT-04_09_2024-GUYNOINS-1^668062/00 3/001 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009234 | 911057563-38139-DETAIL-02_27_2024-GO95MLD-1^07113002.0181400 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009235 | 911087461-86879-DETAIL-01_24_2023-ABNDEQPM-1^06148004.0182200 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009236 | 9112693-57649-DTLSB-05_23_2024-GO95MLD-1^06243001.0134901 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009237 | 911586298-40349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061900 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009238 | 911878464-22282-DETAIL-10_22_2024-GO95MLD-1^07216001.0209711 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009239 | 912145838-78103-DETAIL-10_15_2024-BIRDDMG-1^07216001.0204340 | POLE | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009240 | 912199254-32354-DETAIL-03_28_2023-GO95HV-1^06142016.0083801 | OTHER | Non-HFTD | Distribution | 2023-03-28 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009241 | 912419378-75082-ADMIN-01_25_2022-POLETOP-1^06246001.0334601 | POLE | Non-HFTD | Distribution | 2022-01-25 | 2025-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009242 | 912521697-54970-DETAIL-04_26_2023-GO95MLD-1^06240004.0060101 | OTHER | HFTD Tier 2 | Distribution | 2023-04-26 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009243 | 912798694-52059-DETAIL-02_29_2024-GO95HV-1^07113001.0157900 | OTHER | Non-HFTD | Distribution | 2024-02-29 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009244 | 913699143-33353-DETAIL-06_07_2023-GO95MLD-1^06244010.0275703 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009245 | 913699143-33353-DETAIL-06_07_2023-SVCWIND-1^06244010.0275703 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009246 | 913935694-83782-DETAIL-03_20_2024-GO95HV-1^06245001.0054100 | OTHER | Non-HFTD | Distribution | 2024-03-20 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009247 | 913962186-79339-DETAIL-10_08_2024-GO95CL10-1^07216001.0203004 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009248 | 913966506-66779-DETAIL-04_08_2024-GO95MLD-1^06147005.0245100 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009249 | 913966506-66779-DETAIL-04_08_2024-SVCENTCO-1^06147005.0245100 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009250 | 914458294-45590-DETAIL-03_12_2025-GO95BLTC-1^06239003.0252702 | OTHER | HFTD Tier 2 | Distribution | 2025-03-12 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009251 | 91447889-63879-DETAIL-03_19_2025-GO95HV-1^06239001.0063601 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009252 | 91468349-73312-DETAIL-06_12_2023-GO95MLD-1^06244009.0360103 | OTHER | HFTD Tier 2 | Distribution | 2023-06-12 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009253 | 914782523-90239-DETAIL-03_01_2023-GO95TCH-1^07216001.0293602 | OTHER | Non-HFTD | Distribution | 2023-03-01 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009254 | 91511155-81649-DTLSB-02_22_2023-ABNDEQPM-1^07216001.0287604 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009255 | 915141841-13120-DETAIL-03_06_2025-GO95HV-1^06240004.0272503 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009256 | 915141841-13120-DETAIL-03_06_2025-SVCENTBK-1^06240004.0272503 | OTHER | HFTD Tier 2 | Distribution | 2025-03-06 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009257 | 91525356-52339-DETAIL-10_08_2024-GO95MLD-1^07216001.0201003 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009258 | 915656899-42609-DTLTRT-10_25_2022-GO95HV-1^668075/00 12/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009259 | 915749884-21984-DETAIL-03_14_2023-GO95MLD-1^07114001.0281201 | OTHER | Non-HFTD | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009260 | 91669975-27819-DTLTRT-08_17_2022-GO95MLD-1^668005/00 3/096 | OTHER | Non-HFTD | Transmission | 2022-08-17 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009261 | 91676891-27929-DETAIL-05_09_2024-GO95MLD-1^06142012.0121409 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009262 | 91676891-27929-DETAIL-05_09_2024-SVCDEFLC-1^06142012.0121409 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009263 | 916964008-15008-DETAIL-03_16_2023-GO95HV-1^07114001.0281600 | OTHER | Non-HFTD | Distribution | 2023-03-16 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009264 | 917460196-38970-DETAIL-01_15_2025-GO95HV-1^06239004.0256104 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009265 | 917522801-24502-DTLSB-02_15_2023-GO95HV-1^06248001.0309400 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009266 | 91761335-36275-DETAIL-01_29_2025-SVCDEFLC-1^06240004.0179203 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009267 | 917960866-38319-DETAIL-10_24_2022-GO95HV-1^06247008.0301900 | OTHER | HFTD Tier 2 | Distribution | 2022-10-24 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009268 | 918090032-68340-DTLTRT-10_03_2023-GO95HV-1^668010/00 2/031 | OTHER | HFTD Tier 2 | Transmission | 2023-10-03 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009269 | 918451009-83069-DTLTRT-06_14_2021-ANCHIDLE-1^668041/00 9/020 | ANCHOR/GUY | Non-HFTD | Transmission | 2021-06-14 | 2024-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009270 | 918578034-10459-ADMIN-12_30_2024-POLEDERP-1^07113001.0144200 | POLE | Non-HFTD | Distribution | 2024-12-30 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009271 | 918774504-55903-DETAIL-01_28_2025-GO95CL10-1^06240004.0171941 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009272 | 918774504-55903-DETAIL-09_23_2024-SVCROAD-1^06240004.0171941 | OTHER | HFTD Tier 2 | Distribution | 2024-09-23 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009273 | 918783825-56351-DETAIL-02_24_2025-PWRTRN-1^06239004.0366901 | OTHER | HFTD Tier 2 | Distribution | 2025-02-24 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009274 | 919326500-9540-DETAIL-02_06_2025-GUYHINS-1^06239003.0070903 | ANCHOR/GUY | HFTD Tier 3 | Distribution | 2025-02-06 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009275 | 919490183-43279-DETAIL-07_18_2024-GO95HV-1^06244005.0129900 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009276 | 919992698-28449-DETAIL-08_01_2024-GO95HV-1^06245006.0111001 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009277 | 920301819-29612-DETAIL-01_24_2023-GO95HV-1^06148003.0368901 | OTHER | Non-HFTD | Distribution | 2023-01-24 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009278 | 920411060-23122-DETAIL-03_13_2024-GO95HV-1^06147004.0180901 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009279 | 920473993-5780-DTLTRT-09_27_2023-GO95HV-1^668010/00 16/006 | OTHER | HFTD Tier 2 | Transmission | 2023-09-27 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009280 | 92059004-83449-DTLSB-02_26_2024-GO95MLD-1^07216001.0277908 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009281 | 920808541-5220-DETAIL-03_10_2025-GO95HV-1^06240004.0271802 | OTHER | HFTD Tier 3 | Distribution | 2025-03-10 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009282 | 920916584-48584-DETAIL-04_25_2024-GO95HV-1^06142016.0175601 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009283 | 921011968-20009-DETAIL-04_10_2024-GO95MLD-1^06147005.0164001 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009284 | 921044660-6660-DTLSB-02_08_2023-GO95HV-1^06248001.0260001 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009285 | 921316711-20559-DETAIL-02_20_2024-GO95MLD-1^07216001.0261309 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009286 | 921335305-67170-DETAIL-01_24_2025-GO95HV-1^06239004.0258741 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009287 | 921445689-16809-DTLSB-09_05_2024-GO95HV-1^06245007.0030100 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009288 | 921790767-3989-DTLSB-10_03_2024-GO95BLTC-1^06245006.0331601 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009289 | 921790767-3989-DTLSB-10_03_2024-SVCROAD-1^06245006.0331601 | OTHER | Non-HFTD | Distribution | 2024-10-03 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009290 | 922114171-75171-DETAIL-10_08_2024-GO95TCH-1^07216001.0203109 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009291 | 922310760-23829-DETAIL-05_14_2024-SVCROAD-1^06142012.0122409 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009292 | 922579224-40549-DETAIL-02_07_2024-SVCDEFLC-1^07216001.0199107 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009293 | 922723149-73149-DETAIL-02_05_2025-SVCDEFLC-1^06240004.0167108 | OTHER | HFTD Tier 2 | Distribution | 2025-02-05 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009294 | 923035571-49281-DETAIL-10_07_2021-SVCWIND-1^06147005.0043900 | OTHER | Non-HFTD | Distribution | 2021-10-07 | 2024-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009295 | 923386709-51679-DETAIL-09_29_2020-GO95HV-1^668018/00 9/006 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009296 | 923455680-132-AUDIT-03_27_2024-GO95MLD-1^06147004.0180900 | OTHER | Non-HFTD | Distribution | 2024-03-27 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009297 | 92366401-29821-DETAIL-02_17_2025-GO95MLD-1^06241005.0230100 | OTHER | HFTD Tier 3 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009298 | 923727713-7152-DETAIL-06_26_2023-GO95MLD-1^06244009.0303903 | OTHER | HFTD Tier 2 | Distribution | 2023-06-26 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009299 | 923764724-52532-DETAIL-02_09_2023-GO95MLD-1^06146004.0160900 | OTHER | Non-HFTD | Distribution | 2023-02-09 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009300 | 923964463-82439-DETAIL-10_10_2024-GO95HV-1^07216001.0207101 | OTHER | Non-HFTD | Distribution | 2024-10-10 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009301 | 924167940-74423-DETAIL-07_01_2024-SVCRUBLG-1^06245007.0192002 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009302 | 924167940-74423-DETAIL-07_01_2024-SVCWIND-1^06245007.0192002 | OTHER | HFTD Tier 2 | Distribution | 2024-07-01 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009303 | 924504871-30691-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 2/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009304 | 924504871-88070-DTLTRT-04_11_2024-BIRDDMG-1^668067/00 2/006 | POLE | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009305 | 924628801-97670-DTLTRT-10_16_2023-GO95HV-1^668010/00 17X/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009306 | 924932049-4939-DETAIL-10_08_2024-CLRTOUCH-1^07216001.0202110 | CONDUCTOR | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009307 | 924932049-4939-DETAIL-10_08_2024-GO95CL10-1^07216001.0202110 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009308 | 92511034-43060-DETAIL-01_15_2025-BIRDDMG-1^06240004.0098102 | POLE | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009309 | 9251171-2009-DTLSB-04_23_2024-SVCENTCO-1^06245007.0225703 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009310 | 925255189-16710-DETAIL-02_20_2025-SVCDEFLC-1^06241005.0268000 | OTHER | HFTD Tier 2 | Distribution | 2025-02-20 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009311 | 925395678-6239-DETAIL-03_25_2024-GO95MLD-1^06244005.0141400 | OTHER | Non-HFTD | Distribution | 2024-03-25 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009312 | 925451495-31839-DETAIL-03_09_2023-CLRTOPOL-1^07216001.0294501 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009313 | 925451495-31839-DETAIL-03_09_2023-GO95MLD-1^07216001.0294501 | OTHER | Non-HFTD | Distribution | 2023-03-09 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009314 | 9262543-18113-DTLSB-05_01_2024-GO95MLD-1^06245007.0227640 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009315 | 9262543-18113-DTLSB-05_01_2024-SVCWIND-1^06245007.0227640 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009316 | 9262543-18113-DTLSB-05_01_2024-SVCWIND-2^06245007.0227640 | OTHER | Non-HFTD | Distribution | 2024-05-01 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009317 | 926664576-30400-DTLTRT-11_02_2023-GO95HV-1^668010/00 18/019 | OTHER | HFTD Tier 2 | Transmission | 2023-11-02 | 2028-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009318 | 927064488-26199-DETAIL-04_01_2024-SVCDEFLC-1^06147005.0108900 | OTHER | Non-HFTD | Distribution | 2024-04-01 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009319 | 927633057-63057-DETAIL-02_15_2023-GO95CL10-1^06247002.0232702 | OTHER | Non-HFTD | Distribution | 2023-02-15 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009320 | 927753733-85239-DETAIL-03_21_2023-GO95MLD-1^07113001.0055500 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009321 | 927957519-58259-DETAIL-05_31_2024-GO95HV-1^06246005.0334400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009322 | 927957519-58259-DETAIL-05_31_2024-GO95MLD-1^06246005.0334400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009323 | 927962835-70639-DETAIL-10_08_2024-SVCDEFLC-1^07216001.0200003 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009324 | 928015420-14069-DTLTRT-07_15_2022-GO95HV-1^668005/00 4/047 | OTHER | Non-HFTD | Transmission | 2022-07-15 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009325 | 928199969-42730-DTLTRT-10_19_2023-GO95HV-1^668010/00 4/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009326 | 928689498-38250-DETAIL-03_26_2025-SVCDEFLC-1^06239003.0018307 | OTHER | Non-HFTD | Distribution | 2025-03-26 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009327 | 928729426-60849-DETAIL-02_28_2023-SVCENTCO-1^07216001.0299701 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009328 | 928802369-49259-DETAIL-05_31_2024-GO95MLD-1^06246005.0336400 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009329 | 928826247-47590-DETAIL-01_31_2025-GO95HV-1^06239004.0242941 | OTHER | HFTD Tier 3 | Distribution | 2025-01-31 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009330 | 928940790-52569-DTLSB-09_30_2024-SVCROOF-1^06245007.0232408 | OTHER | HFTD Tier 2 | Distribution | 2024-09-30 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009331 | 928986915-27933-DETAIL-06_10_2024-ENCHRW-1^06245007.0346702 | OTHER | HFTD Tier 2 | Distribution | 2024-06-10 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009332 | 929384843-70330-DETAIL-02_26_2025-SVCDEFLC-1^06240004.0066002 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009333 | 929394144-37652-DTLSB-05_08_2024-GO95MLD-1^06245001.0338200 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009334 | 92947388-57870-DETAIL-02_26_2025-GO95CL10-1^06240004.0060300 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009335 | 930102606-15829-DETAIL-05_07_2024-GO95HV-1^06142012.0124204 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009336 | 93022255-24859-DETAIL-10_24_2024-GO95HV-1^07216001.0201504 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009337 | 930257763-42529-DTLSB-07_31_2023-GO95HV-1^06243009.0081301 | OTHER | HFTD Tier 2 | Distribution | 2023-07-31 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009338 | 930690925-30349-DETAIL-03_14_2024-GO95MLD-1^06245006.0019101 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009339 | 930922700-18349-DTLSB-02_20_2024-GO95HV-1^07216001.0261304 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009340 | 930922700-18349-DTLSB-02_20_2024-GO95MLD-1^07216001.0261304 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009341 | 931111408-19143-DTLSB-04_30_2024-GO95MLD-1^06245007.0221843 | OTHER | Non-HFTD | Distribution | 2024-04-30 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009342 | 93186834-11830-DETAIL-10_21_2024-GO95MLD-1^07216001.0209505 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009343 | 931890384-78560-DTLTRT-04_08_2024-GUYNOINS-1^668062/00 4/005 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009344 | 932343232-25959-DETAIL-05_29_2024-GO95HV-1^06246005.0178000 | OTHER | Non-HFTD | Distribution | 2024-05-29 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009345 | 932367616-29069-DTLTRT-10_23_2023-GO95HV-1^668010/00 13/042 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009346 | 932913948-60850-DETAIL-03_25_2025-GO95HV-1^06239003.0019404 | OTHER | Non-HFTD | Distribution | 2025-03-25 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009347 | 933636913-42753-DETAIL-06_07_2023-GO95MLD-1^06244010.0275600 | OTHER | HFTD Tier 2 | Distribution | 2023-06-07 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009348 | 933778517-3739-DETAIL-03_15_2023-GUYHINS-1^07114001.0340800 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009349 | 933935048-20859-DETAIL-10_15_2024-SVCDEFLC-1^07216001.0207045 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009350 | 933973412-71972-DETAIL-02_21_2023-GO95MLD-1^06247002.0096000 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009351 | 933998095-779-DETAIL-04_18_2024-SVCENTCO-1^06145001.0144700 | OTHER | Non-HFTD | Distribution | 2024-04-18 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009352 | 934354827-85949-DETAIL-03_15_2023-GO95MLD-1^07114001.0340801 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009353 | 934724932-34139-DETAIL-05_15_2024-RISEBKSP-1^06142012.0126801 | OTHER | Non-HFTD | Distribution | 2024-05-15 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009354 | 934898711-45750-DETAIL-03_24_2025-GO95MLD-1^06238004.0027700 | OTHER | HFTD Tier 2 | Distribution | 2025-03-24 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009355 | 935527576-84309-DETAIL-04_08_2024-GUYHINS-1^06147005.0234005 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-08 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009356 | 935782651-97082-DETAIL-03_13_2024-GO95MLD-1^06147004.0070001 | OTHER | Non-HFTD | Distribution | 2024-03-13 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009357 | 936510216-32980-AUDIT-03_18_2025-SVCNEUT-1^06240004.0050142 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009358 | 936642890-25840-DETAIL-03_19_2025-GUYHINS-1^06238004.0029504 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009359 | 936653873-98759-DTLSB-02_22_2024-GUYNOINS-1^07216001.0270040 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009360 | 93700345-57432-DETAIL-04_02_2025-GO95TCH-1^06241005.0028100 | OTHER | HFTD Tier 2 | Distribution | 2025-04-02 | 2028-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009361 | 937784506-80460-DTLTRT-10_12_2023-GO95MLD-1^668010/00 10/041 | OTHER | Non-HFTD | Transmission | 2023-10-12 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009362 | 937811298-11992-DTLSB-02_08_2023-GO95MLD-1^06248001.0227902 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009363 | 937892213-34992-DETAIL-04_06_2023-GO95HV-1^06143014.0235800 | OTHER | HFTD Tier 2 | Distribution | 2023-04-06 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009364 | 937958593-32349-DTLSB-10_07_2024-GO95MLD-1^06245007.0219203 | OTHER | Non-HFTD | Distribution | 2024-10-07 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009365 | 938281254-92254-DETAIL-01_19_2023-GO95MLD-2^06148004.0210901 | OTHER | Non-HFTD | Distribution | 2023-01-19 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009366 | 938572612-37731-AUDIT-03_04_2025-RISEGRD-1^06241005.0175601 | OTHER | HFTD Tier 3 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009367 | 938933383-61992-DETAIL-04_03_2023-GO95HV-1^06143014.0181301 | OTHER | HFTD Tier 2 | Distribution | 2023-04-03 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009368 | 939014868-76192-DETAIL-03_19_2024-GO95MLD-1^06245002.0124501 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009369 | 939329968-62590-DETAIL-01_14_2025-GO95HV-1^06239004.0255206 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009370 | 939888238-56859-DETAIL-05_10_2022-GO95MLD-1^07116001.0059500 | OTHER | Non-HFTD | Distribution | 2022-05-10 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009371 | 93992050-96559-DETAIL-07_05_2023-POLEREPL-1^06246006.0011500 | POLE | Non-HFTD | Distribution | 2023-07-05 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009372 | 940075708-15692-DTLSB-05_14_2024-GO95MLD-1^06244001.0221400 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009373 | 94019936-18570-DETAIL-01_24_2025-SVCROAD-1^06239004.0257842 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009374 | 940300783-38150-DETAIL-01_24_2025-GO95HV-1^06239004.0258600 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009375 | 940567703-40839-DETAIL-07_08_2024-GUYLOINS-1^06244005.0016401 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-07-08 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009376 | 940980012-94789-DTLSB-08_24_2023-GO95MLD-1^06243008.0171700 | OTHER | HFTD Tier 2 | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009377 | 940980012-94789-DTLSB-08_24_2023-GRDRODHI-1^06243008.0171700 | OTHER | HFTD Tier 2 | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009378 | 941486768-71870-DETAIL-02_26_2025-GO95TCH-1^06240004.0060301 | OTHER | HFTD Tier 2 | Distribution | 2025-02-26 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009379 | 941501509-49003-DTLSB-05_28_2024-GO95BLTC-1^06244003.0285600 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009380 | 941501509-49003-DTLSB-05_28_2024-GO95MLD-1^06244003.0285600 | OTHER | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009381 | 941558360-3870-DETAIL-02_14_2025-GO95HV-1^06240004.0168304 | OTHER | HFTD Tier 2 | Distribution | 2025-02-14 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009382 | 94170193-8139-DETAIL-07_31_2024-GO95HV-1^06244005.0342901 | OTHER | Non-HFTD | Distribution | 2024-07-31 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009383 | 941836047-85970-DETAIL-02_25_2025-SVCENTCO-1^06240004.0061110 | OTHER | HFTD Tier 2 | Distribution | 2025-02-25 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009384 | 942193888-82403-DETAIL-04_02_2024-GRDRODHI-1^06147005.0092200 | OTHER | Non-HFTD | Distribution | 2024-04-02 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009385 | 942228168-99249-DETAIL-10_08_2024-GO95HV-1^07216001.0204000 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009386 | 942749641-87201-DETAIL-01_21_2025-GO95MLD-1^06239004.0255545 | OTHER | HFTD Tier 2 | Distribution | 2025-01-21 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009387 | 943118403-22140-DTLTRT-10_19_2023-GO95HV-1^668010/00 8A/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009388 | 943118403-22140-DTLTRT-10_19_2023-GO95MLD-1^668010/00 8A/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009389 | 943291898-58803-DTLSB-02_14_2023-GO95MLD-1^06248001.0229600 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009390 | 943620124-91229-DTLSB-07_17_2023-GO95MLD-1^06243010.0148801 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009391 | 943693294-59460-DETAIL-01_23_2025-GO95HV-1^06239004.0257704 | OTHER | HFTD Tier 2 | Distribution | 2025-01-23 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009392 | 9438755-69200-DETAIL-03_13_2025-SVCDEFLC-1^06239003.0242100 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009393 | 943881671-82879-DETAIL-04_16_2024-GO95MLD-1^06145002.0075500 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009394 | 944068876-48679-DETAIL-07_30_2024-SVCDEFLC-1^06244005.0355900 | OTHER | Non-HFTD | Distribution | 2024-07-30 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009395 | 944267718-4170-DTLTRT-09_30_2020-GO95HV-1^668018/00 7/003 | OTHER | HFTD Tier 2 | Transmission | 2020-09-30 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009396 | 944309358-23213-DRONE_VS-11_13_2024-INSULBRK-1^668038/00 1/063 | INSULATOR AND BUSHING | HFTD Tier 2 | Transmission | 2024-11-13 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009397 | 944345905-21950-DRONE_HY-10_16_2023-GO95HV-1^668033/01 17/003 | OTHER | HFTD Tier 2 | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009398 | 944363512-93389-DETAIL-02_27_2023-GO95MLD-1^07216001.0298801 | OTHER | Non-HFTD | Distribution | 2023-02-27 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009399 | 944538756-51169-DTLTRT-10_11_2023-GO95HV-1^668010/00 8/043 | OTHER | Non-HFTD | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009400 | 944678571-39959-DTLSB-02_16_2024-SVCENTCO-1^07216001.0262106 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009401 | 945076758-76969-DTLTRT-06_30_2022-GO95HV-1^668005/00 1/031 | OTHER | Non-HFTD | Transmission | 2022-06-30 | 2027-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009402 | 945098473-47479-DETAIL-08_20_2024-GO95HV-1^06246005.0245100 | OTHER | Non-HFTD | Distribution | 2024-08-20 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009403 | 945118515-65113-DETAIL-02_21_2024-GO95CL10-1^07113001.0145200 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009404 | 945304693-2929-DETAIL-05_09_2024-GO95MLD-1^06142012.0120505 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009405 | 945641341-28149-DETAIL-02_21_2024-SVCDEFLC-1^07113001.0138204 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009406 | 945850566-67989-DETAIL-07_10_2024-GO95MLD-1^06244004.0215501 | OTHER | HFTD Tier 2 | Distribution | 2024-07-10 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009407 | 946230186-85070-DETAIL-01_24_2025-GO95HV-1^06239004.0257940 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009408 | 94623559-41073-DTLSB-10_02_2024-SVCENTCO-1^06245007.0217601 | OTHER | Non-HFTD | Distribution | 2024-10-02 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009409 | 946578779-70949-DTLSB-02_16_2024-GO95MLD-1^07216001.0260005 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009410 | 946597859-94749-DTLSB-02_20_2024-GO95MLD-1^07216001.0260504 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009411 | 946822584-16009-DTLSB-04_23_2024-GO95MLD-1^06245007.0223700 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009412 | 946876428-18330-DETAIL-02_24_2025-PWRTRN-1^06240003.0305800 | OTHER | HFTD Tier 3 | Distribution | 2025-02-24 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009413 | 947231752-68009-DETAIL-07_12_2023-GO95MLD-1^06243008.0054700 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009414 | 947255263-1129-DETAIL-05_14_2024-GRDRODHI-1^06142012.0122703 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009415 | 947538696-90949-DETAIL-04_15_2024-SVCROAD-1^06245007.0225106 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009416 | 947823489-40909-DTLSB-09_03_2024-GO95MLD-1^06245007.0014101 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009417 | 948433165-13223-DETAIL-04_23_2024-GO95MLD-1^06145001.0037100 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009418 | 948550112-8319-DETAIL-04_08_2024-GO95MLD-1^06147005.0220600 | OTHER | Non-HFTD | Distribution | 2024-04-08 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009419 | 948895446-50723-DTLSB-05_14_2024-GO95MLD-1^06244001.0298200 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009420 | 949255174-66273-ADMIN-01_13_2025-POLEREPL-1^06245007.0272040 | POLE | HFTD Tier 2 | Distribution | 2025-01-13 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009421 | 949717274-31779-DETAIL-08_15_2024-BIRDDMG-1^06246005.0147200 | POLE | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009422 | 949717274-31779-DETAIL-08_15_2024-GO95MLD-1^06246005.0147200 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009423 | 950055566-38770-DETAIL-02_19_2025-PWRTRN-1^06239004.0363302 | OTHER | HFTD Tier 2 | Distribution | 2025-02-19 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009424 | 950595619-33213-DETAIL-07_29_2024-GO95MLD-1^06245006.0147640 | OTHER | Non-HFTD | Distribution | 2024-07-29 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009425 | 950795141-63759-DETAIL-06_17_2024-GUYHINS-1^06246006.0239900 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-06-17 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009426 | 950799784-28923-DTLSB-05_09_2024-GO95HV-1^06244001.0110900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009427 | 950799784-28923-DTLSB-05_09_2024-GO95MLD-1^06244001.0110900 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009428 | 951839052-19099-DETAIL-01_29_2019-GO95MLD-1^06147004.0350500 | OTHER | Non-HFTD | Distribution | 2019-01-29 | 2022-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009429 | 9525169-913-DETAIL-03_11_2024-GO95HV-1^06245006.0120041 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009430 | 952664879-19489-DTLSB-09_03_2024-SVCENTCO-1^06245007.0018100 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009431 | 952921883-58239-DETAIL-06_25_2024-SVCDEFLC-1^06244005.0237301 | OTHER | Non-HFTD | Distribution | 2024-06-25 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009432 | 953151503-32840-DTLTRT-10_19_2023-GO95HV-1^668010/00 18/024 | OTHER | Non-HFTD | Transmission | 2023-10-19 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009433 | 953389205-21579-DETAIL-04_03_2024-GO95MLD-1^06147005.0142006 | OTHER | Non-HFTD | Distribution | 2024-04-03 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009434 | 953398765-60549-DETAIL-05_24_2023-GUYNOINS-1^06245005.0228001 | ANCHOR/GUY | Non-HFTD | Distribution | 2023-05-24 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009435 | 953438461-51433-DETAIL-05_07_2024-GO95MLD-1^06142012.0121104 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009436 | 953701183-42933-DETAIL-04_04_2023-GO95HV-1^06143014.0141001 | OTHER | HFTD Tier 2 | Distribution | 2023-04-04 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009437 | 953828783-9699-DETAIL-03_05_2024-GO95HV-1^06147005.0177900 | OTHER | Non-HFTD | Distribution | 2024-03-05 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009438 | 954442070-28969-DTLSB-04_17_2024-SVCRUBLG-1^06245007.0224346 | OTHER | Non-HFTD | Distribution | 2024-04-17 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009439 | 954510988-80988-DETAIL-01_25_2022-SVCROAD-1^06239004.0258009 | OTHER | HFTD Tier 2 | Distribution | 2022-01-25 | 2025-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009440 | 954916105-78109-DETAIL-01_23_2023-GO95HV-1^06148004.0200100 | OTHER | Non-HFTD | Distribution | 2023-01-23 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009441 | 955145984-17984-DETAIL-04_25_2024-GO95MLD-1^06142016.0175802 | OTHER | Non-HFTD | Distribution | 2024-04-25 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009442 | 955586122-90243-DETAIL-02_08_2023-GO95MLD-1^06146002.0335301 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009443 | 955890924-13924-DETAIL-03_29_2023-GO95MLD-1^06142016.0084707 | OTHER | Non-HFTD | Distribution | 2023-03-29 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009444 | 956059752-65289-DTLSB-08_26_2024-GO95HV-1^06245007.0112401 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009445 | 95620718-13949-DTLSB-02_22_2024-GO95MLD-1^07216001.0263904 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009446 | 956308610-67549-DETAIL-08_12_2024-GO95MLD-1^06245006.0105800 | OTHER | Non-HFTD | Distribution | 2024-08-12 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009447 | 956455860-51901-DETAIL-06_02_2022-GO95MLD-1^06241005.0031701 | OTHER | HFTD Tier 2 | Distribution | 2022-06-02 | 2025-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009448 | 956523235-59970-DETAIL-01_24_2025-SVCDEFLC-1^06239004.0258841 | OTHER | HFTD Tier 3 | Distribution | 2025-01-24 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009449 | 956918113-81349-DETAIL-10_15_2024-GO95MLD-1^07216001.0207006 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009450 | 957119713-143-DETAIL-02_14_2023-GO95HV-1^06247002.0214700 | OTHER | Non-HFTD | Distribution | 2023-02-14 | 2028-02-29 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009451 | 957534818-42309-DETAIL-11_01_2022-GO95HV-1^06246009.0073100 | OTHER | HFTD Tier 2 | Distribution | 2022-11-01 | 2027-11-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009452 | 95754525-73639-DETAIL-10_24_2024-GO95TCH-1^07216001.0200601 | OTHER | Non-HFTD | Distribution | 2024-10-24 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009453 | 957829458-59858-DETAIL-01_31_2023-GO95MLD-1^06147002.0349500 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009454 | 957998302-94159-DETAIL-02_21_2024-GO95MLD-1^07113001.0144201 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009455 | 958107903-95379-DTLSB-01_30_2023-GO95MLD-1^06248001.0255004 | OTHER | Non-HFTD | Distribution | 2023-01-30 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009456 | 958132114-8629-DTLSB-09_07_2023-GO95MLD-1^06243008.0026000 | OTHER | HFTD Tier 2 | Distribution | 2023-09-07 | 2026-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009457 | 958159521-91443-DETAIL-04_15_2024-GO95MLD-1^06145002.0052701 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009458 | 958234649-24749-DETAIL-10_08_2024-SVCNEUT-1^07216001.0202000 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009459 | 958536141-32639-DETAIL-06_26_2024-GUYNOINS-1^06244005.0233704 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-06-26 | 2027-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009460 | 958552043-69989-DETAIL-10_26_2022-GO95MLD-1^06246009.0127702 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009461 | 958736296-71149-DETAIL-10_08_2024-GO95MLD-1^07216001.0204002 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009462 | 958736296-71149-DETAIL-10_08_2024-GO95TCH-1^07216001.0204002 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009463 | 958962355-37543-DETAIL-04_23_2024-GO95MLD-1^06145001.0034101 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009464 | 959257213-73839-DETAIL-07_11_2024-GO95HV-1^06244005.0260500 | OTHER | Non-HFTD | Distribution | 2024-07-11 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009465 | 959300613-60613-DETAIL-04_09_2024-CONDFRAY-1^06147005.0254704 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009466 | 959300613-60613-DETAIL-04_09_2024-CONDFRAY-2^06147005.0254704 | CONDUCTOR | Non-HFTD | Distribution | 2024-04-09 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009467 | 959300613-60613-DETAIL-04_09_2024-GO95HV-1^06147005.0254704 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009468 | 959300613-60613-DETAIL-04_09_2024-GO95MLD-1^06147005.0254704 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009469 | 959348831-25929-DETAIL-05_08_2024-GO95BLTC-1^06142012.0120005 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009470 | 959348831-25929-DETAIL-05_08_2024-GO95MLD-1^06142012.0120005 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009471 | 959407448-61949-AUDIT-02_27_2024-GO95HV-1^07216001.0196103 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009472 | 959407448-61949-AUDIT-02_27_2024-GO95MLD-1^07216001.0196103 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009473 | 959516571-50059-DTLSB-02_16_2024-GO95MLD-1^07216001.0261200 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009474 | 959873208-78799-DETAIL-07_23_2024-GO95MLD-1^06245006.0143000 | OTHER | Non-HFTD | Distribution | 2024-07-23 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009475 | 960699002-26849-DETAIL-02_21_2024-GRDRODHI-1^07113001.0149100 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009476 | 961015216-10389-DTLSB-08_24_2023-GO95MLD-1^06243009.0118600 | OTHER | Non-HFTD | Distribution | 2023-08-24 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009477 | 961041983-23029-DTLSB-08_25_2023-GO95MLD-1^06243008.0241800 | OTHER | HFTD Tier 2 | Distribution | 2023-08-25 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009478 | 961153059-18390-DETAIL-01_15_2025-SVCDEFLC-1^06239004.0256112 | OTHER | HFTD Tier 2 | Distribution | 2025-01-15 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009479 | 96146456-99849-DETAIL-02_27_2024-GO95HV-1^07113002.0073300 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009480 | 96146456-99849-DETAIL-02_27_2024-GO95MLD-1^07113002.0073300 | OTHER | Non-HFTD | Distribution | 2024-02-27 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009481 | 96151026-40563-DTLSB-02_08_2024-GO95MLD-1^07216001.0198101 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009482 | 962168828-59828-DETAIL-03_30_2023-GO95BLTC-1^06142016.0055001 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009483 | 962168828-59828-DETAIL-03_30_2023-GO95MLD-1^06142016.0055001 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009484 | 962408341-41839-DRONE_HY-10_25_2023-GO95HV-1^668087/00 14/008 | OTHER | Non-HFTD | Transmission | 2023-10-25 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009485 | 962610363-23049-DETAIL-03_15_2023-GO95MLD-1^07216001.0291502 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009486 | 963166151-80853-DETAIL-05_08_2024-GO95MLD-1^06142012.0120104 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009487 | 963281853-45153-DTLSB-05_23_2024-GO95MLD-1^06243001.0121000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009488 | 963281853-45153-DTLSB-05_23_2024-GRDRODHI-1^06243001.0121000 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009489 | 963353788-85353-DETAIL-05_14_2024-GO95MLD-1^06142012.0124406 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009490 | 963916995-20263-DTLSB-02_01_2023-GO95MLD-1^06248001.0368302 | OTHER | Non-HFTD | Distribution | 2023-02-01 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009491 | 964215636-44380-DETAIL-03_18_2025-SVCDEFLC-1^06240003.0366003 | OTHER | Non-HFTD | Distribution | 2025-03-18 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009492 | 964343990-98669-DRONE_HY-10_11_2023-GO95HV-1^668033/00 12/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-11 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009493 | 964498435-54933-DTLSB-02_22_2023-GO95MLD-1^07216001.0287804 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009494 | 964498435-54933-DTLSB-02_22_2023-GO95TCH-1^07216001.0287804 | OTHER | Non-HFTD | Distribution | 2023-02-22 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009495 | 964564838-7170-AUDIT-02_18_2025-POLETOP-1^06240004.0168504 | POLE | HFTD Tier 2 | Distribution | 2025-02-18 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009496 | 964564838-7170-AUDIT-02_18_2025-SVCDEFLC-1^06240004.0168504 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009497 | 96458819-45630-DETAIL-03_19_2024-GO95MLD-1^06245002.0054600 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009498 | 964620121-86489-DETAIL-04_05_2023-ABNDEQPM-1^06245006.0229201 | OTHER | Non-HFTD | Distribution | 2023-04-05 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009499 | 96464880-32609-DETAIL-11_09_2022-GO95MLD-1^06246008.0046200 | OTHER | HFTD Tier 2 | Distribution | 2022-11-09 | 2025-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009500 | 964772313-239-DTLSB-02_28_2024-GO95HV-1^07216001.0273701 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009501 | 965332288-95449-DETAIL-10_14_2024-GO95HV-1^07216001.0203302 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009502 | 965332288-95449-DETAIL-10_14_2024-GO95MLD-1^07216001.0203302 | OTHER | Non-HFTD | Distribution | 2024-10-14 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009503 | 965344733-18563-DTLSB-05_28_2024-GUYNOINS-1^06243001.0126400 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-05-28 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009504 | 965372371-25879-DETAIL-06_17_2024-GO95MLD-1^06246006.0242801 | OTHER | Non-HFTD | Distribution | 2024-06-17 | 2029-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009505 | 965392366-32649-DTLSB-02_21_2023-SVCENTCO-1^07216001.0287701 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009506 | 965513964-29939-DETAIL-07_15_2024-GO95MLD-1^06244005.0264940 | OTHER | Non-HFTD | Distribution | 2024-07-15 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009507 | 965660099-6699-DTLTRT-10_25_2022-GO95MLD-1^668075/00 5/026 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009508 | 965850161-66469-DTLTRT-07_20_2022-GO95HV-1^668005/00 11/054 | OTHER | Non-HFTD | Transmission | 2022-07-20 | 2027-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009509 | 965885072-98109-DTLSB-08_26_2024-GO95MLD-1^06245007.0113402 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009510 | 966001668-56369-DTLTRT-07_06_2022-GO95MLD-1^668005/00 3/036 | OTHER | Non-HFTD | Transmission | 2022-07-06 | 2025-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009511 | 967184669-8249-DTLSB-02_19_2024-GO95MLD-1^07216001.0260300 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009512 | 967184669-8249-DTLSB-02_19_2024-GRDRODHI-1^07216001.0260300 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009513 | 967263773-84930-DETAIL-03_04_2025-CLRTOUCH-1^06240004.0064701 | CONDUCTOR | HFTD Tier 2 | Distribution | 2025-03-04 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009514 | 967263773-84930-DETAIL-03_04_2025-GO95CL10-1^06240004.0064701 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009515 | 967390479-23269-DRONE_HY-09_21_2023-GO95HV-1^668002/00 16/066 | OTHER | HFTD Tier 2 | Transmission | 2023-09-21 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009516 | 967922515-273-DTLSB-05_08_2024-GO95HV-1^06244001.0035200 | OTHER | Non-HFTD | Distribution | 2024-05-08 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009517 | 968216199-14000-DETAIL-09_29_2020-GO95HV-1^668018/00 2/007 | OTHER | HFTD Tier 2 | Transmission | 2020-09-29 | 2025-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009518 | 96863588-62030-DETAIL-04_16_2024-GO95MLD-1^06145001.0129300 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009519 | 96905795-9559-DETAIL-08_19_2024-GO95HV-1^06246004.0317400 | OTHER | Non-HFTD | Distribution | 2024-08-19 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009520 | 969087471-12901-DETAIL-01_14_2025-GO95MLD-1^06239004.0257441 | OTHER | HFTD Tier 2 | Distribution | 2025-01-14 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009521 | 969210691-76073-AUDIT-04_15_2024-SVCROAD-1^06147004.0070202 | OTHER | Non-HFTD | Distribution | 2024-04-15 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009522 | 969217135-13989-DETAIL-06_07_2023-GO95MLD-1^06244006.0025800 | OTHER | Non-HFTD | Distribution | 2023-06-07 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009523 | 96949313-92499-DTLSB-08_31_2023-GO95MLD-1^06243007.0320200 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009524 | 969804307-12999-DTLSB-08_22_2024-GO95MLD-1^06245006.0323200 | OTHER | HFTD Tier 2 | Distribution | 2024-08-22 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009525 | 970359393-62252-DETAIL-06_15_2023-RISEGRD-1^06244009.0309701 | OTHER | Non-HFTD | Distribution | 2023-06-15 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009526 | 970363130-92170-DETAIL-03_19_2025-GO95HV-1^06239002.0012600 | OTHER | HFTD Tier 2 | Distribution | 2025-03-19 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009527 | 971116123-17159-DETAIL-05_16_2022-GO95MLD-1^07116001.0090902 | OTHER | Non-HFTD | Distribution | 2022-05-16 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009528 | 971564361-74268-DTLSB-02_13_2024-GO95MLD-1^07216001.0198900 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009529 | 971919470-19570-DETAIL-02_12_2025-GO95BLTC-1^06240004.0166001 | OTHER | HFTD Tier 2 | Distribution | 2025-02-12 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009530 | 972160814-65629-DTLSB-08_09_2023-GO95MLD-1^06243009.0190500 | OTHER | HFTD Tier 2 | Distribution | 2023-08-09 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009531 | 973216199-14099-DTLTRT-10_25_2022-GO95MLD-1^668075/00 17/025 | OTHER | Non-HFTD | Transmission | 2022-10-25 | 2025-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009532 | 973261800-77509-DTLSB-09_03_2024-GO95MLD-1^06245007.0017000 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009533 | 973261800-77509-DTLSB-09_03_2024-GRDRODHI-1^06245007.0017000 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009534 | 973289557-61849-DETAIL-03_15_2023-SVCENTCO-1^07114001.0342200 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009535 | 973457393-86699-DTLSB-09_08_2023-GO95MLD-1^06243008.0262800 | OTHER | HFTD Tier 2 | Distribution | 2023-09-08 | 2028-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009536 | 973739811-87049-DETAIL-02_21_2024-GO95MLD-1^07113001.0139203 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009537 | 973806655-74483-DTLSB-02_08_2023-GO95MLD-1^06248001.0166400 | OTHER | Non-HFTD | Distribution | 2023-02-08 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009538 | 973861359-59073-DETAIL-03_07_2023-GO95MLD-1^07117002.0207802 | OTHER | HFTD Tier 2 | Distribution | 2023-03-07 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009539 | 973929126-88483-DETAIL-02_21_2023-SVCWIND-1^07216001.0280770 | OTHER | Non-HFTD | Distribution | 2023-02-21 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009540 | 973988830-93201-DETAIL-01_31_2025-BIRDDMG-1^06239004.0136108 | POLE | HFTD Tier 2 | Distribution | 2025-01-31 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009541 | 97408796-73672-DETAIL-08_08_2024-GO95MLD-1^06245006.0097140 | OTHER | Non-HFTD | Distribution | 2024-08-08 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009542 | 974167534-62890-DETAIL-03_13_2025-GO95MLD-1^06239003.0256900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009543 | 974313798-6929-DTLSB-08_16_2023-GO95MLD-1^06243009.0154601 | OTHER | HFTD Tier 2 | Distribution | 2023-08-16 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009544 | 974313798-6929-DTLSB-08_16_2023-GRDRODHI-1^06243009.0154601 | OTHER | HFTD Tier 2 | Distribution | 2023-08-16 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009545 | 975084229-23199-DETAIL-05_31_2024-GO95MLD-1^06246005.0334800 | OTHER | Non-HFTD | Distribution | 2024-05-31 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009546 | 975243470-44930-DETAIL-01_29_2025-SVCDEFLC-1^06240004.0176702 | OTHER | HFTD Tier 2 | Distribution | 2025-01-29 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009547 | 975337796-77859-DETAIL-03_28_2024-GO95MLD-1^06247005.0326501 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009548 | 975632556-20109-AUDIT-10_15_2024-ABNDEQPM-1^06245007.0142201 | OTHER | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009549 | 9757039-69553-DTLSB-04_29_2024-GO95MLD-1^06245007.0226446 | OTHER | Non-HFTD | Distribution | 2024-04-29 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009550 | 975785055-64949-DETAIL-02_22_2024-GO95HV-1^07113001.0156302 | OTHER | Non-HFTD | Distribution | 2024-02-22 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009551 | 975785055-64949-DETAIL-02_22_2024-GUYHINS-1^07113001.0156302 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-02-22 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009552 | 976304913-40339-DTLSB-02_13_2024-GO95MLD-1^07216001.0187001 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009553 | 976344954-99999-DTLSB-04_24_2024-GO95MLD-1^06245007.0224607 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009554 | 976650441-9373-DETAIL-03_02_2023-GO95MLD-1^07117002.0200302 | OTHER | HFTD Tier 2 | Distribution | 2023-03-02 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009555 | 977022009-19679-AUDIT-10_15_2024-ABNDEQPM-1^06245007.0018400 | OTHER | HFTD Tier 2 | Distribution | 2024-10-15 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009556 | 977022009-19679-DTLSB-09_03_2024-GO95MLD-1^06245007.0018400 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009557 | 977177691-36809-DETAIL-10_26_2022-ABNDEQPM-1^06246008.0063101 | OTHER | HFTD Tier 2 | Distribution | 2022-10-26 | 2027-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009558 | 977801883-44629-DETAIL-05_16_2024-GO95MLD-1^06142012.0122902 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009559 | 977801883-44629-DETAIL-05_16_2024-GRDRODHI-1^06142012.0122902 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009560 | 978055818-25169-DTLTRT-10_23_2023-GO95HV-1^668010/00 9/044 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009561 | 978055818-25169-DTLTRT-10_23_2023-GO95MLD-1^668010/00 9/044 | OTHER | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009562 | 978597606-9210-DETAIL-03_13_2025-GO95HV-1^06238004.0224900 | OTHER | HFTD Tier 2 | Distribution | 2025-03-13 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009563 | 978644562-35562-DETAIL-04_04_2024-BIRDDMG-1^06247005.0297102 | POLE | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009564 | 979064536-42693-DETAIL-04_23_2024-GO95MLD-1^06145001.0035501 | OTHER | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009565 | 979332764-20203-DTLSB-02_07_2024-GO95MLD-1^07216001.0199405 | OTHER | Non-HFTD | Distribution | 2024-02-07 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009566 | 980051188-14499-DTLSB-07_02_2024-GO95HV-1^06245006.0186201 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009567 | 980051188-14499-DTLSB-07_02_2024-GO95MLD-1^06245006.0186201 | OTHER | HFTD Tier 2 | Distribution | 2024-07-02 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009568 | 980113588-349-DETAIL-03_18_2024-GO95MLD-1^06245005.0061800 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009569 | 98016213-36529-DTLSB-08_31_2023-GO95HV-1^06243007.0293301 | OTHER | HFTD Tier 2 | Distribution | 2023-08-31 | 2028-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009570 | 980667696-6889-DETAIL-03_28_2024-BIRDDMG-1^06247005.0331600 | POLE | Non-HFTD | Distribution | 2024-03-28 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009571 | 980732234-33234-DETAIL-02_12_2025-GUYHINS-1^06240004.0284600 | ANCHOR/GUY | HFTD Tier 2 | Distribution | 2025-02-12 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009572 | 980844258-79730-DTLTRT-10_18_2023-GO95HV-1^668010/00 17/011 | OTHER | HFTD Tier 2 | Transmission | 2023-10-18 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009573 | 981159691-3230-DETAIL-09_24_2024-GRDSHDBK-1^668014/00 8/027 | OTHER | HFTD Tier 2 | Transmission | 2024-09-24 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009574 | 981234157-97590-DETAIL-02_03_2025-GO95HV-1^06239004.0244842 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009575 | 981234157-97590-DETAIL-02_03_2025-GO95TCH-1^06239004.0244842 | OTHER | HFTD Tier 2 | Distribution | 2025-02-03 | 2028-02-29 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009576 | 981280733-16309-DETAIL-01_18_2023-CONDFRAY-1^06148004.0215101 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009577 | 981280733-16309-DETAIL-01_18_2023-GO95HV-1^06148004.0215101 | OTHER | Non-HFTD | Distribution | 2023-01-18 | 2028-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009578 | 981371504-50059-DTLSB-02_08_2024-SVCENTBK-1^07216001.0197040 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009579 | 981548325-71703-DETAIL-05_16_2024-SVCENTCO-1^06142012.0120701 | OTHER | Non-HFTD | Distribution | 2024-05-16 | 2027-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009580 | 982027745-40319-ADMIN-08_05_2024-GO95STUB-1^06247008.0191100 | OTHER | HFTD Tier 2 | Distribution | 2024-08-05 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009581 | 982169336-65460-DTLTRT-10_09_2023-GO95HV-1^668010/00 8/039 | OTHER | Non-HFTD | Transmission | 2023-10-09 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009582 | 982487914-84999-DETAIL-04_17_2023-GO95CL10-1^06240004.0165750 | OTHER | HFTD Tier 2 | Distribution | 2023-04-17 | 2028-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009583 | 982669814-13332-DETAIL-07_12_2023-RISEGRD-1^06244008.0229000 | OTHER | HFTD Tier 2 | Distribution | 2023-07-12 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009584 | 982818989-94803-DTLSB-05_07_2024-GO95MLD-1^06245002.0136601 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009585 | 983052509-6149-DETAIL-02_19_2024-GO95MLD-1^07113002.0185002 | OTHER | HFTD Tier 2 | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009586 | 983055616-58579-DETAIL-03_28_2024-GO95HV-1^06147005.0142700 | OTHER | Non-HFTD | Distribution | 2024-03-28 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009587 | 983409784-19449-DTLSB-02_08_2024-GRDRODHI-1^07216001.0198002 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009588 | 983626914-22513-DTLSB-05_07_2024-GO95MLD-1^06245001.0191301 | OTHER | Non-HFTD | Distribution | 2024-05-07 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009589 | 98381838-47649-DTLSB-02_21_2024-GO95MLD-1^07216001.0260809 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009590 | 984063453-29252-DETAIL-06_20_2023-GO95HV-1^06244010.0253300 | OTHER | HFTD Tier 2 | Distribution | 2023-06-20 | 2028-06-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009591 | 984066752-91070-DETAIL-03_18_2025-GO95HV-1^06238004.0123802 | OTHER | HFTD Tier 2 | Distribution | 2025-03-18 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009592 | 984081981-73813-DETAIL-04_16_2024-GO95HV-1^06145002.0078001 | OTHER | Non-HFTD | Distribution | 2024-04-16 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009593 | 98419331-20539-DETAIL-07_18_2024-GO95HV-1^06244004.0086700 | OTHER | Non-HFTD | Distribution | 2024-07-18 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009594 | 984311598-82370-DETAIL-11_18_2024-BIRDDMG-1^668014/00 4/059 | POLE | HFTD Tier 2 | Transmission | 2024-11-18 | 2027-11-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009595 | 98432198-37579-DETAIL-02_17_2025-GO95HV-1^06240004.0277400 | OTHER | HFTD Tier 2 | Distribution | 2025-02-17 | 2030-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009596 | 984444755-90009-DETAIL-01_18_2023-CONDFRAY-2^06148004.0207700 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009597 | 984444755-90009-DETAIL-01_18_2023-CONDFRAY-3^06148004.0207700 | CONDUCTOR | Non-HFTD | Distribution | 2023-01-18 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009598 | 984577616-18520-DETAIL-04_04_2024-GUYHINS-1^06147005.0242901 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009599 | 984670736-68813-DTLSB-01_31_2023-GO95MLD-1^06248001.0367901 | OTHER | Non-HFTD | Distribution | 2023-01-31 | 2026-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009600 | 985571308-84979-DETAIL-04_09_2024-GO95MLD-1^06147005.0212001 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009601 | 985717690-61962-DTLSB-07_17_2023-ABNDEQPM-1^06243010.0118201 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2028-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009602 | 985717690-61962-DTLSB-07_17_2023-GO95MLD-1^06243010.0118201 | OTHER | HFTD Tier 2 | Distribution | 2023-07-17 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009603 | 985909784-37839-DTLSB-02_08_2024-GO95HV-1^07216001.0307800 | OTHER | Non-HFTD | Distribution | 2024-02-08 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009604 | 986121508-4779-DETAIL-04_09_2024-GO95MLD-1^06147005.0212003 | OTHER | Non-HFTD | Distribution | 2024-04-09 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009605 | 986800880-64489-DTLSB-07_22_2024-GO95MLD-1^06245007.0107802 | OTHER | HFTD Tier 2 | Distribution | 2024-07-22 | 2029-07-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009606 | 986800988-82539-DTLSB-02_28_2024-GO95TCH-1^07216001.0260903 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009607 | 987259911-56970-DETAIL-04_17_2023-GO95MLD-1^06240004.0165641 | OTHER | HFTD Tier 2 | Distribution | 2023-04-17 | 2026-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009608 | 987886334-42559-DTLSB-02_13_2024-GO95MLD-1^07216001.0198800 | OTHER | Non-HFTD | Distribution | 2024-02-13 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009609 | 988168332-99349-DETAIL-10_15_2024-GO95MLD-1^07216001.0205200 | OTHER | Non-HFTD | Distribution | 2024-10-15 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009610 | 988172589-44969-DTLSB-04_10_2024-SVCROAD-1^06245007.0222009 | OTHER | Non-HFTD | Distribution | 2024-04-10 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009611 | 988215071-36891-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009612 | 988215071-49469-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009613 | 988215071-5891-DTLTRT-04_11_2024-GUYNOINS-1^668067/00 1/006 | ANCHOR/GUY | Non-HFTD | Transmission | 2024-04-11 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009614 | 988508837-41849-DETAIL-03_15_2023-SVCENTCO-1^07114001.0342201 | OTHER | Non-HFTD | Distribution | 2023-03-15 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009615 | 988779181-59230-DETAIL-03_05_2025-GO95HV-1^06240004.0204403 | OTHER | HFTD Tier 3 | Distribution | 2025-03-05 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009616 | 988779181-59230-DETAIL-03_05_2025-GRDRODHI-1^06240004.0204403 | OTHER | HFTD Tier 3 | Distribution | 2025-03-05 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009617 | 988885496-8180-DETAIL-03_03_2025-GO95HV-1^06240004.0051003 | OTHER | HFTD Tier 2 | Distribution | 2025-03-03 | 2030-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009618 | 988911149-70549-DETAIL-05_17_2023-GO95HV-1^06245006.0350200 | OTHER | Non-HFTD | Distribution | 2023-05-17 | 2028-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009619 | 98896422-37049-DETAIL-02_21_2024-SVCDEFLC-1^07113002.0180200 | OTHER | Non-HFTD | Distribution | 2024-02-21 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009620 | 989002706-34039-DETAIL-10_08_2024-SVCENTCO-1^07216001.0201110 | OTHER | Non-HFTD | Distribution | 2024-10-08 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009621 | 989223859-20090-DETAIL-01_28_2025-GO95TCH-1^06239004.0244301 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009622 | 989235551-17551-DTLSB-02_14_2024-GO95MLD-1^07216001.0198920 | OTHER | Non-HFTD | Distribution | 2024-02-14 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009623 | 989354109-45133-ADMIN-04_22_2024-ABNDEQPM-1^06146001.0365101 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009624 | 989354109-45133-DETAIL-04_22_2024-GO95MLD-1^06146001.0365101 | OTHER | Non-HFTD | Distribution | 2024-04-22 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009625 | 989712101-470-DTLTRT-10_16_2023-GO95HV-1^668010/00 8/001 | OTHER | Non-HFTD | Transmission | 2023-10-16 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009626 | 989774611-16201-DETAIL-05_30_2023-GO95MLD-1^06243009.0029702 | OTHER | HFTD Tier 2 | Distribution | 2023-05-30 | 2026-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009627 | 990047329-20399-DETAIL-08_01_2024-GO95HV-1^06245006.0140900 | OTHER | Non-HFTD | Distribution | 2024-08-01 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009628 | 990047329-20399-DETAIL-08_01_2024-GUYHINS-1^06245006.0140900 | ANCHOR/GUY | Non-HFTD | Distribution | 2024-08-01 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009629 | 99033402-17320-DETAIL-10_21_2024-GO95MLD-1^07216001.0209405 | OTHER | Non-HFTD | Distribution | 2024-10-21 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009630 | 990620161-36579-DETAIL-03_11_2024-GO95MLD-1^06147004.0047801 | OTHER | Non-HFTD | Distribution | 2024-03-11 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009631 | 990943138-42969-DTLTRT-04_04_2024-GUYNOINS-1^668067/00 14/024 | ANCHOR/GUY | HFTD Tier 2 | Transmission | 2024-04-04 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009632 | 990944564-10333-DETAIL-10_22_2024-SVCROAD-1^07216001.0208700 | OTHER | Non-HFTD | Distribution | 2024-10-22 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009633 | 991208238-7300-DETAIL-03_14_2023-GO95HV-1^07117002.0274700 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009634 | 991432582-71429-DETAIL-05_09_2024-GO95MLD-1^06142012.0121307 | OTHER | Non-HFTD | Distribution | 2024-05-09 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009635 | 99160080-38949-DTLSB-02_16_2024-GO95HV-1^07216001.0262201 | OTHER | Non-HFTD | Distribution | 2024-02-16 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009636 | 991655088-60920-DETAIL-09_10_2024-SVCDEFLC-1^06240004.0098006 | OTHER | HFTD Tier 2 | Distribution | 2024-09-10 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009637 | 991741559-47512-DETAIL-06_28_2023-GO95MLD-1^06244009.0363301 | OTHER | HFTD Tier 2 | Distribution | 2023-06-28 | 2026-06-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009638 | 991808058-6668-DETAIL-02_28_2023-GO95MLD-1^07216001.0299802 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009639 | 991808058-6668-DETAIL-02_28_2023-GRDRODHI-1^07216001.0299802 | OTHER | Non-HFTD | Distribution | 2023-02-28 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009640 | 992429563-38999-DTLSB-10_01_2024-GO95HV-1^06245007.0230600 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2029-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009641 | 992429563-38999-DTLSB-10_01_2024-SVCENTCO-1^06245007.0230600 | OTHER | HFTD Tier 2 | Distribution | 2024-10-01 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009642 | 992495931-95883-DETAIL-10_25_2024-GO95TCH-1^07216001.0208401 | OTHER | Non-HFTD | Distribution | 2024-10-25 | 2027-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009643 | 992496787-12609-DTLSB-09_05_2024-GO95MLD-1^06245006.0072901 | OTHER | HFTD Tier 2 | Distribution | 2024-09-05 | 2029-09-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009644 | 992700172-14444-DETAIL-03_31_2025-SVCRUBCM-1^06241005.0116606 | OTHER | HFTD Tier 2 | Distribution | 2025-03-31 | 2028-03-31 | 2 | A | [6 empty] | PacifiCorp | 2025 | 1
1130009645 | 992805560-48539-DETAIL-02_26_2024-SVCENTCO-1^07113001.0138402 | OTHER | Non-HFTD | Distribution | 2024-02-26 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009646 | 992805560-48539-DETAIL-03_26_2024-SVCROAD-1^07113001.0138402 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2027-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009647 | 99310291-94229-DTLSB-08_08_2023-GO95MLD-1^06243009.0140701 | OTHER | Non-HFTD | Distribution | 2023-08-08 | 2026-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009648 | 993172049-50870-DETAIL-02_18_2025-CONDCOIL-1^06240004.0221900 | OTHER | HFTD Tier 2 | Distribution | 2025-02-18 | 2026-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009649 | 993329426-70679-DETAIL-03_26_2024-GO95MLD-1^06247005.0332000 | OTHER | Non-HFTD | Distribution | 2024-03-26 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009650 | 993345773-87243-ADMIN-05_23_2024-ABNDEQPM-1^06243001.0149600 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009651 | 993865485-27943-DETAIL-04_24_2024-GO95MLD-1^06145001.0044101 | OTHER | Non-HFTD | Distribution | 2024-04-24 | 2029-04-30 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009652 | 994076064-38960-DETAIL-01_28_2025-SVCDEFLC-1^06240004.0079406 | OTHER | HFTD Tier 3 | Distribution | 2025-01-28 | 2028-01-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009653 | 994406414-69909-DTLSB-04_23_2024-POLETOP-1^06245007.0224704 | POLE | Non-HFTD | Distribution | 2024-04-23 | 2027-04-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009654 | 994504990-79789-DTLSB-07_20_2023-GO95MLD-1^06243010.0026402 | OTHER | HFTD Tier 2 | Distribution | 2023-07-20 | 2026-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009655 | 99465879-86440-DETAIL-03_19_2024-GO95MLD-1^06245002.0039000 | OTHER | Non-HFTD | Distribution | 2024-03-19 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009656 | 994836983-3083-DETAIL-03_30_2023-GO95HV-1^06142016.0058001 | OTHER | Non-HFTD | Distribution | 2023-03-30 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009657 | 994857618-81390-DETAIL-01_28_2025-GO95HV-1^06239004.0246100 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009658 | 994932021-26589-DETAIL-07_03_2024-SVCDEFLC-1^06244005.0234903 | OTHER | Non-HFTD | Distribution | 2024-07-03 | 2027-07-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009659 | 995187201-73650-DETAIL-03_19_2025-BIRDDMG-1^06238004.0024040 | POLE | HFTD Tier 2 | Distribution | 2025-03-19 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009660 | 995500313-53843-DTLSB-05_23_2024-GO95MLD-1^06243001.0130700 | OTHER | Non-HFTD | Distribution | 2024-05-23 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009661 | 995571644-98929-DETAIL-05_14_2024-GO95MLD-1^06142012.0123502 | OTHER | Non-HFTD | Distribution | 2024-05-14 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009662 | 995571705-90890-DTLTRT-10_31_2023-GO95HV-1^668010/00 11/017 | OTHER | HFTD Tier 2 | Transmission | 2023-10-31 | 2028-10-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009663 | 99559872-61319-ADMIN-12_31_2018-POLEREPL-1^668005/00 2/088 | POLE | Non-HFTD | Transmission | 2018-12-31 | 2021-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009664 | 995750481-56059-DTLSB-02_19_2024-GO95MLD-1^07216001.0262206 | OTHER | Non-HFTD | Distribution | 2024-02-19 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009665 | 995765099-17190-DETAIL-01_28_2025-GO95HV-1^06239004.0245440 | OTHER | HFTD Tier 2 | Distribution | 2025-01-28 | 2030-01-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009666 | 995855342-39539-DETAIL-05_09_2022-GO95MLD-1^07116001.0100200 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009667 | 995855342-39539-DETAIL-05_09_2022-GO95SVC-1^07116001.0100200 | OTHER | HFTD Tier 2 | Distribution | 2022-05-09 | 2025-05-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009668 | 995903053-17343-ADMIN-12_03_2024-POLEREPL-1^06144006.0198900 | POLE | Non-HFTD | Distribution | 2024-12-03 | 2027-12-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009669 | 996176489-96249-DETAIL-03_14_2024-GO95HV-1^06245005.0061602 | OTHER | Non-HFTD | Distribution | 2024-03-14 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009670 | 996638334-46259-DETAIL-05_17_2022-ABNDEQPM-1^07117001.0320500 | OTHER | HFTD Tier 2 | Distribution | 2022-05-17 | 2027-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009671 | 997026778-1902-ADMIN-08_28_2024-POLEREPL-1^06244009.0366702 | POLE | HFTD Tier 2 | Distribution | 2024-08-28 | 2025-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009672 | 997400580-19349-DETAIL-02_20_2024-GO95BLTC-1^07113002.0182005 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2029-02-28 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009673 | 997400580-19349-DETAIL-02_20_2024-GO95MLD-1^07113002.0182005 | OTHER | Non-HFTD | Distribution | 2024-02-20 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009674 | 997680079-55699-DETAIL-08_15_2024-GO95HV-1^06246005.0135900 | OTHER | Non-HFTD | Distribution | 2024-08-15 | 2029-08-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009675 | 997723871-43649-DETAIL-02_28_2024-SVCENTCO-1^07113001.0031300 | OTHER | Non-HFTD | Distribution | 2024-02-28 | 2027-02-28 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009676 | 997862064-51149-DETAIL-03_21_2023-GO95HV-1^07113001.0057500 | OTHER | Non-HFTD | Distribution | 2023-03-21 | 2028-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009677 | 998037034-21139-DETAIL-03_20_2023-GO95MLD-1^07114001.0284402 | OTHER | Non-HFTD | Distribution | 2023-03-20 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009678 | 998235033-46033-DETAIL-03_14_2023-GO95MLD-1^07117003.0092002 | OTHER | HFTD Tier 2 | Distribution | 2023-03-14 | 2026-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009679 | 998279446-26260-DTLTRT-10_23_2023-GUYNOINS-2^668010/00 15A/042 | ANCHOR/GUY | Non-HFTD | Transmission | 2023-10-23 | 2026-10-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009680 | 998309371-2289-DTLSB-08_26_2024-GO95MLD-1^06245007.0113301 | OTHER | HFTD Tier 2 | Distribution | 2024-08-26 | 2027-08-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009681 | 998889023-21434-DETAIL-05_01_2024-GO95HV-1^06143015.0336801 | OTHER | HFTD Tier 2 | Distribution | 2024-05-01 | 2029-05-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009682 | 999199218-89889-DETAIL-03_18_2024-GO95HV-1^06245002.0039701 | OTHER | Non-HFTD | Distribution | 2024-03-18 | 2029-03-31 | 3 | C | [6 empty] | PacifiCorp | 2025 | 1
1130009683 | 999328889-22489-DTLSB-09_03_2024-GO95MLD-1^06245007.0123900 | OTHER | HFTD Tier 2 | Distribution | 2024-09-03 | 2027-09-30 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1
1130009684 | 999790346-11346-DETAIL-03_04_2025-GO95MLD-1^06241005.0130707 | OTHER | HFTD Tier 2 | Distribution | 2025-03-04 | 2028-03-31 | 2 | B | [6 empty] | PacifiCorp | 2025 | 1